NT10BIX5570122 | 2013 | $17,530.00 | FRBA's average cost per new mile is calculated by dividing total capital costs for network construction (less certain equipment categories) by 1,948 total route miles in the project to arrive at an average cost per mile of $17,530.00 | 0 | FRBA is a middle-mile network only and does not provide any direct last-mile residential access. Last-mile providers will provide such services utilizing FRBAâ€™s middle-mile capacity for backhaul to reach markets within the service area. | 0 | FRBA is a middle-mile network only and subscriber connections will only be made to community anchors throughout the region (as well as last-mile providers). Costs associated with such infrastructure are not included in this section. | 200Mbps | FRBA is a middle-mile network capable of providing wholesale capacity in increments of 200Mbps. | 200Mbps | FRBA is a middle-mile network but will provide last-mile services to community anchors. Anchors will be able to receive a maximum of 200Mbps, but additional capacity may be provisioned to increase that capacity to higher rates. | 200Mbps | FRBAâ€™s middle-mile wholesale access will provide transport and commodity Internet services between speeds of 5Mbps and 200Mbps. We anticipate the average middle-mile transport circuit at 200Mbps, based on the requirements of CAIs in the region and last-mile providers. Last-mile providers will require larger transport circuits for backhaul into local service areas. In addition, last-mile providers will require direct type 2 services to reach customers in these areas. | 10Mbps | Broadband connections to CAIs will range between 5Mbps and 150Mbps, with the average in the region being 10Mbps. These connections will provide broadband services to community anchors requiring both Internet and transport Broadband connections to CAIs will range between 5Mbps and 150Mbps, with the average in the region being 10Mbps. These connections will provide broadband services to community anchors requiring both Internet and transport services in FRBAâ€™s service area. Currently, many anchors utilize DSL, T1 or T1xN services and FRBAâ€™s services will provide a significant increase in capacity over legacy copper infrastructure. | The FRBA network will provide significant increases in broadband speeds to community anchors throughout the region. Through our market research, we have found that many CAIs in the service area receive DSL, Cable and NxT1 local access services, in most cases limited to 6Mbps or less. FRBAâ€™s network will provide bandwidth from 5Mbps to 200Mbps to CAIs, utilizing both shared and dedicated products. On average, and through our outreach programs, we have recognized that many CAIs will upgrade existing services by 3-5 times the amount of bandwidth they currently receive. On average, a 6Mbp customer will double or triple their bandwidth on the FRBA network, for competitive rates using FRBAâ€™s redundant middle-mile infrastructure. In addition, CAIs will be able to interconnect their facilities utilizing FRBAâ€™s transport services, allowing them to provision site-to-site connectivity, previously only possible through high-cost, legacy private line circuits and unreliable Internet-based VPNs. | FRBA will offer retail services to CAIs throughout the region. These services include point-to-point/multi-point transport and Internet services to community anchors as identified in this APR and its attachments. FRBA has identified many CAIs in its region that require a combination of transport and Internet services. Transport services will provide site-to-site connectivity for many of the local government, public safety and healthcare customers in the region, enabling them to upgrade or replace their costly copper-based WAN services with higher speed wireless WAN services. FRBA will also participate in the E-Rate program for Schools and Libraries as administered by USAC and will be an eligible E-Rate provider for these organizations. For these critical education-based CAIs, FRBAâ€™s network will provide high-performance Internet and site-to-site transport interconnections between schools, libraries and related facilities, helping ensure students have access to critical online resources. Pricing for services is also included in the attached rate sheet for dedicated transport and Internet capacity (Please see FRBA Rate Sheet 1.0.pdf) | FRBAâ€™s network management practices and policies will adhere to the principles contained in the FCCâ€™s Internet Policy Statement and not show favoritism to any lawful Internet applications and content over others. The FRBA network will not be a private closed network, but will instead be connected to the public Internet directly and provide open access to all Internet resources. FRBA will offer at least two classes of services to its customers depending on their particular needs and budgetary constraints. FRBA will offer both dedicated and shared access to customers. Dedicated access will provide committed rate services for CAIs and last-mile providers that require guaranteed bandwidth. Shared services will provide best-effort services to customers that donâ€™t require stringent performance requirements, geared primarily for smaller CAIs, branch offices and small businesses. Pricing for shared services will be significantly lower than dedicated services as a result. | The FRBA network is currently in the final phases of construction and does not have an aging customer base in which to gauge or forecast a churn rate. FRBA currently has 3 serviceable CAI's with the ability to connect to the network. A single test connection has been provided at a shared facility to beta test the connectivity. It is the intent that each of the 3 customers will ultimately contract directly with FRBA for primary Internet connectivity. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FRBA does not wholesale dark fiber. | 300 | 300 | 0 | 0 | FRBA has negotiated and purchased colocation space in two Level3 data centers in Orlando, FL and Tallahassee, FL. Both data centers have neutral access to significant regional and national carriers, through which FRBA will develop interconnection agreements and NNIs. Data centers have available cage and cabinet space to provide colocation services to potential subtenants who require local presence for peering and interconnection. FRBA will maintain direct cross-connects to other carriers in these facilities. Additionally, each of FRBAâ€™s tower sites is equipped with colocation facilities for last-mile providers, local exchange carriers and other entities. Interconnection for customers (last mile providers) will be accessed through switched IP/Ethernet multi-service access platforms located at each tower/wireless network site. These sites will enable local last-mile networks interconnect with FRBA's middle-mile backhaul to deliver new bandwidth to local service areas. In doing so, FRBA's network will offer a significant amount of points of interconnection into underserved service areas that lack adequate backhaul. Many regions maintain legacy T1 and DS3 backhaul and few offer bandwidth beyond those transport technologies. FRBA will deliver new wireless backhaul to these service areas as an upgrade to existing legacy copper backhaul networks | FRBA has not issued any subcontracts or subgrants to SDB firms. | N/A | Florida Rural Broadband Alliance, LLC | 178 | 28 | 6 | 18 | 70 | 97 |  | 124 | 272 | 11 | 804 | FRBA has not signed any interconnection agreements during the period in question. FRBA is actively identifying interconnection partners and will be establishing NNIs ("Network to network interconnections") for wholesale and type 2 services in the region. These activities will coincide with completion and activation of the network to ensure that NNIs and interconnections can be made immediately, allowing the network to begin providing services as soon as it is commissioned. FRBA is in the final stages of completing a definitive agreement with competitively chosen network operator. The network operator is a seasoned telecom provider with the potential to perform a more thorough outreach to a much wider audience of interconnection partners. | FRBA currently maintains IRU capacity with Level3 for back-haul connectivity between the wireless middle-mile core network and its two data centers in Tallahassee, FL and Orlando, FL. As the network nears completion, FRBA has identified commodity Internet, peering and interconnection partners to be integrated into the network. Initially FRBA has partnered with a "sister" project in NFBA to arrange an initial 500Mb of HSIP. Not only does this solution provide a service arrangement with a partner in the same data-center as FRBA, but is ultimately a Tier 1 wholesale connection provided directly from Level 3. | TRUE
NT10BIX5570123 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 20 Mbps/ $ | N/A | 0 | N/A | 3 Mbps /$ 20 | N/A | N/A; Service is contained to the existing network capacity. The project work has been in environmental planning for the BTOP funded expansion. Community Anchor Institutions will be connected as soon as possible following the construction of the expanded network. | The Nez Perce Tribe Information Systems broadband network currently serves the immediate Lapwai, Idaho area; the service includes internet subscriber accounts of up to 3 Mbps for a flat rate $20/month. | Bandwidth limitations based on service level subscribed to. Content has not been limited. | The Nez Perce Tribe Information Systems network service has152 residential subscribers; 11 dropped service, the reasons are not currently tracked; and, 99 new subscribers were connected in 2010. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No fiber in the Nez Perce Tribe project | 0 | 0 | 0 | 0 | N/A; no construction has taken place | N/A the Nez Perce Tribe is the primary and sole project recipient. | N/A | Nez Perce Tribe | 4 | 5 | 2 | 1 | 5 | 7 |  | 3 | 3 | 1 | 31 | N/A | N/A | TRUE
NT10BIX5570123 | 2011 | 3621/32.5 Mbps | To date the Nez Perce Tribe network has connected two CAI's: Lapwai Library at 20 Mbps and Clearwater County at 45 Mbps; these connection were made due to a BTOP upgrade to middle mile. Overall project build out has been delayed by weather conditions; one middle mile link is up and on line utilizing two existing towers (Bio-Control - Stoney Point). Across the entire BTOP network, the tower construction is complete; and an wireless equipment installation contract has been awarded and will be underway early 2012. With exception of the proposed route modification, the middle mile is expected to be complete and tested by Q2 2012. | 49.67 | The network has one last mile site active: Stoney Point. The project is considerable behind the projected baseline regarding last mile service delivery. Contracts have been awarded, equipment procured and the last mile access points installation will be project staff priority during Q1 - Q2 2012. | 1490.08 / 3Mbps | The technology for wireless last mile access is limited to line of sight signal transmission. The topography in the Stoney Point tower vicinity has limited the area of coverage. Network staff are busy doing site surveys; and the IT support staff are considering adding last mile equipment that might get the transmission rate up. In addition, project development staff are working to expand existing tower collocation agreements to include a tower above Spaulding, which would complement the service area of Stoney Pt. | 10+ | Rates are $ 100.Mb up to 10; above 10 Mb demand will be negotiated | 20 | Speed tiers offered include 3 Mbps, 10 Mbps and 20+ Mbps | 3621/32.5 Mbps | To date the Nez Perce Tribe network has connected two CAI's: Lapwai Library at 20 Mbps and Clearwater County at 45 Mbps; these connection were made due to a BTOP upgrade to middle mile. | 3 | To date residential subscribers are all at 3 Mbps connection; Lapwai library is connected with 20 Mbps | Last mile service is not built out across the entire network yet. Connections have been made to: Lapwai library where their previous connection rate/costs was 7 Mbps for $ 81/month; and now on the Nez Perce Tribe network is 20 Mbps for $ 50/month Clearwater County government office: where 45 Mbps provided at a cost savings advantage | Wireless high speed internet service is what we offer as a service. Three tiers are available: 3/1.5 Mbps $ 20/month; 10/10 Mbps $ 300/month; 20+ Mbps cost negotiated per month | Subscribers are provided the bandwidth capacity with no limitations of access based on the service tier they select. There are no limits or blocks on subscribers accessing lawful content, service or application; or that would prevent them from attaching any legal device to the network. | No (0%) dropped subscribers from the BTOP funded network. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 384 | 120 | 0 | 264 | NA The Nez Perce tribe does own, each tower site has a 8 x 12 communications building with space available for collocation equipment. The project focus has been on construction of towers. Towers range from 100' to 250' tall and there is ample room on most towers for collocation. Collocation requests will be considered first come first serve and be based on tower loading capacity limitations. | NA, no subcontracts with 8(a) businesses. However, there has been a subcontract awarded to Certified Indian owned businesses in accordance with the Nez Perce Tribal Employment Rights Ordinance: GEM Electric and B & C Development Inc | The Nez Perce Tribe entered into mutually beneficial collocation lease rates with its project partners for space on towers for wireless equipment. Staffing for network technician positions: Information Systems program partnership with Tribal workforce development program and interns were trained and able to compete for openings when jobs were advertised; resulting in two technicians hired in full time jobs with benefits. | Nez Perce Tribe | 4 | 5 | 2 | 1 | 5 | 7 |  | 3 | 3 | 1 | 31 | Two interconnection agreements have been established between the Nez Perce Tribe and XO Communications for access to ; and between the Nez Perce tribe and Idaho Regional Optic Network. There are no other agreements at this time; and, there have been no agreements denied. | NA; there are no peering or transit agreements | TRUE
NT10BIX5570123 | 2012 | 10090/200 Mbps | The middle mile network construction was completed Q2 2012 with 152 miles of wireless links installed and functional at speeds of 200 Mbps. Total middle mile project costs $ 1834657 for an average costs of $ 12070 | 115/3,6,9 Mbps | The project last mile delivery has reached 99% completion; testing and working to resolve non line of sight connection in several targeted community areas is underway. To resolve the lack of line of sight connectivity the project staff are placing neighborhood solutions (nanobridge connections to rooftops and distributing signal via sector or omni antenna). Residential subscribers have a choice of 3, 6 or 9 Mbps plans. To date last mile project costs are $ 416,711 and the project has passed 3610 residences for an average cost of $ 115 | 1096/3, 6, 9 Mbps | To date, the project has 380 subscribers; the average last mile cost is $ 1096 | 10+ Mbps | Up to 10 Mb connection is available at established rates; above 10 Mbps rates are negotiable. | 9 Mbps | There are three service levels advertised for last mile: 3, 6, 9 Mbps | 8.25 Mbps | The Nez Perce Network System has three libraries (20, 6,6 Mbps), two city governments (3 Mbps), one county government (15 Mbps), one rural fire district (3 Mbps) and one commercial provider (10 Mb) receiving middle mile connectivity. | 3 Mbps | The Nez Perce Network System has 288 subscribers at 3 Mbps, 75 at 6 Mbps, 16 at 9 Mbps, 1 at 10 Mbps and 1 at 20 Mbps. | As a result of Nez Perce Network Systems BTOP expansion the Connected CAI's include: Lapwai (library receives more affordable service - previous connection rate/costs was 7 Mbps for $ 81/month; and on the Nez Perce Tribe (NPT) network is 20 Mbps for $ 50/month); Culdesac City and Library (more affordable service - the City connection is part of an agreement (land use for tower location in exchange for free 3 Mbps connectivity; previous connection at the Library was $ 45 for 2 Mbps; and on the NPT network $ 40/mo for 6 Mbps) and Public safety entities receive first mobile access; Peck (library previous connection was $ 79 for satellite and Rural Fire District received its first broadband service available); Clearwater County(county received more affordable service previously $ 830/mo, on NPT network $ 700 for 20 Mbps and in addition the benefits of centralized management, WAN deployment and improved system support in remote locations); and Kamiah (senior center received a new broadband connection). In addition to fixed service the project expanded mobile broadband access in partnership with Inland Cellular; the mobile access was deployed in an area of the Reservation previously unserved and provided access to ID State Police, Lewis and Nez Perce County Sheriff Dept's, Tribal police and Emergency Mgmt entities greatly improving public safety along a dangerous section of State Hwy 95. | Residential and Business last mile services offered include three plan tiers: 3 Mbps ( $ 20/month); 6 Mbps ($ 40/month); and, 9 Mbps ($ 60/month). | Subscribers are provided with the bandwidth capacity with no limitations of access based on the service tier they select. There are no limitations or blocks on subscribers accessing lawful content, service or application. There are no blocks that would prevent subscribers from attaching any legal device to the network. | Over the past year two (2) subscribers dropped service (< 0.1%), the reason for discontinuing the service was at the base plan (3 Mbps) they experienced lag while streaming and this dissatisfied them. No, our technicians let perspective subscribers know if they plan to do a fair amount of streaming the higher bandwidth plans may be better suited for such use. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 864 | 288 | 100 | 476 | NA; the Nez Perce Tribe owns nine of the facility sites and space. Collocation on towers at each site will be considered on a first come first serve basis and be based on tower loading capacity/limitations. Currently, tower space and communication building space has been leased to one provider at one site. | There have been no 8A subcontracts let. Three Certified Indian owned businesses under the Nez Perce Tribal Employment Rights Ordinance have received subcontract opportunities (BOSS Heating & Air, B&C Development Inc, and GEM Electric). | The Nez Perce Tribe developed proactive partnerships with a regional mobile provider for tower space utilization and mutually agreeable collocation rates; this partnership enabled both entities to expand coverage affordably and efficiently. In addition, the Tribe pursued site use partnerships where possible in exchange for service delivery to implement its neighborhood solution equipment to reach customers outside of the main network line of sight coverage areas. The marketing effort is targeted to neighborhoods and the project staff found a tool offered by the US Postal Service - Direct Mail, enabling low cost bulk direct mailings delivery to targeted areas. | Nez Perce Tribe | 4 | 5 | 2 | 1 | 5 | 7 |  | 3 | 3 | 1 | 31 | The Nez Perce Tribe has two sources for interconnection: XO Communications; and the Idaho Regional Optic Network. There are no additional source for interconnection available. | The Nez Perce Tribe currently has two transit agreements: Washington RSA #8 Limited Partnership, dba Inland Cellular has contracted 10 Mbps of network middle mile to facilitate their expansion of mobile access; and the Education Network of America, Inc. to provide a dedicated 3 Mbps between Peck Elementary and Orofino High School, which is expected to be live early in Q1 2013. | TRUE
NT10BIX5570123 | 2013 | 10856 | 175 Miles of middle mile network was deployed across the Tribes wireless network with functional speed of 200 Mbps. Total cost to deploy middle mile $ 1,899,847. | 115 | Residential subscribers have the choice of three tiers: 3, 6 or 9 Mbps connectivity. Project costs to deploy last mile are $ 416,711 and the network has passed 3,601 households for an average cost of $ 115. | 590 | The network has 706 active subscribers; the average cost per subscriber is $ 590 | 10 + Mbps | Connections up to 10 Mbps are available at a set rate of $ 100/Mb; above 10 Mbps connections are possible and rates negotiated. | 9 Mbps | There are three tier levels available: 3, 6 and 9 Mbps | 10.44 Mbps | There are 18 CAI's connected at rates ranging from 3 - 20 Mbps; and one wholesale agreement at 3 Mbps established on the Tribes network. The average connection is 10.44 Mbps | 3 Mbps | There are 480 (68%) subscribers at 3 Mbps; 189 (26%)at 6 Mbps; and 33 (4%)at 9 Mbps | As a result of Nez Perce Network Systems BTOP expansion the Connected CAI's include: Lapwai (library receives more affordable service - previous connection rate/costs was 7 Mbps for $ 81/month; and on the Nez Perce Tribe (NPT) network is 20 Mbps for $ 50/month); Culdesac City and Library (more affordable service - the City connection is part of an agreement (land use for tower location in exchange for free 3 Mbps connectivity; previous connection at the Library was $ 45 for 2 Mbps; and on the NPT network $ 40/mo for 6 Mbps) and Public safety entities receive first mobile access; Peck (library previous connection was $ 79 for satellite and Rural Fire District received its first broadband service available); Clearwater County(county received more affordable service previously $ 830/mo, on NPT network $ 700 for 20 Mbps and in addition the benefits of centralized management, WAN deployment and improved system support in remote locations); the ID Fish-Game Clearwater Hatchery had only access to satellite or dial up connection and now has a wireless 6 Mbps connection; and the Dworshak National Fish Hatchery which also was limited by a copper line connection with slow speeds, now has a 6 Mbps connection via the TrIbes wireless network. In addition to fixed service the project expanded mobile broadband access in partnership with Inland Cellular; the mobile access was deployed in an area of the Reservation previously unserved and provided access to ID State Police, Lewis and Nez Perce County Sheriff Dept's, Tribal police and Emergency Mgmt entities greatly improving public safety along a dangerous section of State Hwy 95. | Residential and Business last mile services offered include three plan tiers: 3 Mbps ( $ 20/month); 6 Mbps ($ 40/month); and, 9 Mbps ($ 60/month). | Subscribers are provided with the bandwidth capacity with no limitations of access based on the service tier they select. There are no limitations or blocks on subscribers accessing lawful content, service or application. There are no blocks that would prevent subscribers from attaching any legal device to the network. | Since service delivery began less than1 percent, of the subscribers have discontinued service. The reason for discontinuing the service was at the base plan (3 Mbps) they experienced lag while streaming and this dissatisfied them. No, our technicians let perspective subscribers know if they plan to do a fair amount of streaming the higher bandwidth plans may be better suited for such use. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 1600 | 672 | 210 | 718 | NA; the Tribe owns nine of the facility sites used in the network. Collocation is being considered on a first come first serve basis. Currently, the Tribe has lees with Inland Cellular at two sites (Beard, Culdesac). | There have been no 8A subcontracts let. Three Certified Indian owned businesses under the Nez Perce Tribal Employment Rights Ordinance have received subcontract opportunities (BOSS Heating & Air, B&C Development Inc, and GEM Electric). | The Nez Perce Tribe developed proactive partnerships with a regional mobile provider for tower space utilization and mutually agreeable collocation rates; this partnership enabled both entities to expand coverage affordably and efficiently. In addition, the Tribe pursued site use partnerships where possible in exchange for service delivery to implement its neighborhood solution equipment to reach customers outside of the main network line of sight coverage areas. | Nez Perce Tribe | 4 | 5 | 2 | 1 | 5 | 7 |  | 3 | 3 | 1 | 31 | There are two sources for interconnection: XO Communications; and the Idaho Regional Optic Network for the Nez Perce Tribe's network. There are no other sources of interconnection available. | There are two transit agreements currently on the Nez Perce Tribe's network: Inland Cellular has contracted a dedicated 10 Mb path; and Education Networks of America has contracted a dedicated 3 Mbps path. QRO of Idaho had inquired about accessing bandwidth but no follow up occurred. The Nez Perce Tribe has not denied interconnection to any entitiy. | TRUE
NT10BIX5570125 | 2010 | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | n/a | n/a | n/a | n/a | 48240 | 0 | 0 | 0 | 756 | 378 | 47106 | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | Plumas Sierra Rural Electric Cooperative | 5 | 0 | 2 | 0 | 3 | 0 |  | 7 | 0 | 0 | 17 | n/a | n/a | TRUE
NT10BIX5570125 | 2011 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | Broadband speeds have not increased since construction/deployment has not begun. | Price plans have not been provided since construction/deployment has not begun. | We have not begun providing service as construction/deployment has not begun. | N/A | 48240 | 0 | 0 | 0 | 756 | 378 | 47106 | N/A at this time as construction/deployment has not begun. | 0 | 0 | 0 | 0 | N/A as construction deployment has not yet begun. | N/A | An unforeseen obstacle with increased vendor demand as a result of these grant funded projects occurred which has an impact on the construction time line for the project. With all of these grant funded projects having similar time lines, acquiring the materials needed has been a challenge to the project. Many fiber vendors have stopped taking orders as the demand has exceeded their plants production ability. In many cases delivery forecast have gone out farther than anticipated by anyone, during the grant writing process. As a result, having your material orders in to the vendors as quickly as possible is about all you can do with the hope that the materials will come timely enough to allow the project to stay within the tight construction time frames outlined by the grant requirements. | Plumas Sierra Rural Electric Cooperative | 5 | 0 | 2 | 0 | 3 | 0 |  | 7 | 0 | 0 | 17 | N/A | N/A | TRUE
NT10BIX5570125 | 2012 | 37,695 | This is $38,090 under the Baseline Key Project Indicator of $75,785. Route improvements accounted for $17,347 of this difference. The remaining difference of $20,743 is because there were indirect costs included in the Baseline Key Project Indicator. | n/a | n/a | n/a | n/a | 0 | Still to be determined. Baseline was OC-12 Service offering. | n/a | n/a | 0 | Service has not been provided. Baseline was 45 Mbp/s. | n/a | n/a | n/a | Retail service is not currently being provided. | 7a. - Network management policies are currently displayed on our web page (Attachment - Acceptable Use Policy). 7b. - No. Our network is not operational as of 12/31/12. | n/a | 43304 | 1396 | 0 | 40642 | 75 | 0 | 1191 | n/a. We are not currently providing services. | 600 | 450 | 0 | 150 | We will have two collocation spaces that we will not own. The details are as follows: 1.) Location: 200 S. Virginia St, Reno, NV 89501 Owner: Basin Street Properties Interconnecting With: Zayo Enterprises Method fo Interconnection: Electronics Interface. Electronic equipment will route traffic from Plumas Sierra Telecommunication Fiber Optic Cables to Zayo Fiber Optic Cables. 2.) Location: 210 Gardner St, Reno, NV 89501 Owner: California Broadband Cooperative (CBC) Interconnecting With: California Broadband Cooperative (CBC) Method fo Interconnection: Electronics Interface. Electronic equipment will route traffic from Plumas Sierra Telecommunication Fiber Optic Cables to California Broadband Cooperative (CBC) Fiber Optic Cables. | n/a | None this year of that were out of the normal scopes of construction. | Plumas Sierra Rural Electric Cooperative | 5 | 0 | 2 | 0 | 3 | 0 |  | 7 | 0 | 0 | 17 | 1.) Entered into: 0 2.) Negotiating: 2 3.) Denied: 0 | 1.) Entered into: 0 2.) Negotiating: 0 3.) Denied: 0 | TRUE
NT10BIX5570125 | 2013 | $47,164 | This is $28,621 under the Baseline Key Project Indicator of $75,785. Route improvements accounted for $17,347 of this difference. The remaining difference of $11,274 is because there were indirect costs included in the Baseline Key Project Indicator. | N/A | N/A | N/A | N/A | 1 GB | Baseline was OC-12 Service Offering. | N/A | N/A | 210 MB | 12 circuits. 7 Customers as of 12/31/213. | N/A | N/A | The average increase in broadband speed will be 294 Mb per CAI. Methodology used was (sum of new speeds (5,375 Mb) - sum of previous speeds (382.15)) / Total CAI's (17) | Retail services provided in 2013: 25 Mb Internet Access 40 Mb Internet Access 100 Mb Internet Access 100 Mb Internet Access Pricing plan info included in attachment. | 7a. - Network management policies are currently displayed on our web page (Attachment - Acceptable Use Policy) 7b. - No. | There have been no subscribers who have dropped our service. | 41953 | 2409 | 32 | 39512 | 0 | 0 | 0 | Zayo Group - 34 Miles. | 600 | 450 | 0 | 150 | We have two collocation spaces that we do not own. The details are as follows: 1.) Location: 200 S. Virginia St, Reno, NV 89501 Owner: Basin Street Properties Interconnecting With: Zayo Enterprises Method of Interconnection: Electronics Interface. Electronic equipment will route traffic from Plumas Sierra Telecommunication Fiber Optic Cables to Zayo Fiber Optic Cables. 2.) Location: 210 Gardner St, Reno, NV 89501 Owner: California Broadband Cooperative (CBC) Interconnecting With: California Broadband Cooperative (CBC) Method of Interconnection: Electronics Interface. Electronic equipment will route traffic from Plumas Sierra Telecommunication Fiber Optic Cables to California Broadband Cooperative (CBC) Fiber Optic Cables. | N/A | None this year that were out of the normal scopes of construction and Network Management. | Plumas Sierra Rural Electric Cooperative | 5 | 0 | 2 | 0 | 3 | 0 |  | 7 | 0 | 0 | 17 | 1.) Entered into in 2013: 0 2.) Negotiating in 2013: 0 3.) Denied in 2013: 0 | 1.) Entered into in 2013: 0 2.) Negotiating in 2013: 0 3.) Denied in 2013: 0 | TRUE
NT10BIX5570126 | 2010 | $0.00 | N/A | $0.00 | N/A | $0.00 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A construction has not yet begun | N/A construction has not yet begun | N/A construction has not yet begun | N/A construction has not yet begun | 62174 | 0 | 0 | 0 | 4510 | 600 | 57064 | N/A construction has not yet begun | 0 | 0 | 0 | 0 | N/A construction has not yet begun | N/A construction has not yet begun | We cannot stress enough how important and valuable community outreach efforts have been. Our project is quite large encompassing fiber construction in 18 counties in California. We have conducted site visits and follow-up meetings at each of our 63 anchor institutions to determine cabinet locations, building entry points, and plans for route diversity where appropriate. We met with road authorities in each county and each city our project construction effects to identify the best route through each community to minimize disruption of roadways. Each authority has expressed a willingness to work together to simplify the right-of-way process. We also met with government leadership in all 18 counties and the individual communities to determine how our project could best meet their economic development needs. We have been met with great enthusiasm by each county and community because they realize the enormous value our project brings to their area. These meetings have allowed us to create a good working relationship with each anchor institution, county and community. The information gathered will aid in the detailed engineering process, minimize route changes that could effect environmental assessment, streamline right-of-way procurement processes and simplify eventual turn-up of services. | CVIN, LLC | 1311 | 158 | 8 | 104 | 1460 | 400 |  | 2852 | 0 | 0 | 6293 | N/A | N/A | TRUE
NT10BIX5570126 | 2011 | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 62174 | 0 | 0 | 0 | 4510 | 600 | 57064 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | 0 | 0 | 0 | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | N/A | N/A | CVIN, LLC | 1311 | 158 | 8 | 104 | 1460 | 400 |  | 2852 | 0 | 0 | 6293 | We have entered into two wholesale service agreements with last mile ISP's, Sebastian Corp (DBA: Audeamus) and Sierra Tel Internet. We are negotiating 34 others. We have not received nor denied any other request for interconnection but since we are early in the construction phase, connection points are very limited at this time. | N/A | TRUE
NT10BIX5570126 | 2012 | $53,025.81 | Slightly below the projected cost in the baseline. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit and middle mile fiber. No last mile wireless has been installed. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit and middle mile fiber. No last mile wireless has been installed. | 10Gbps | No change from baseline plan. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit and middle mile fiber. No last mile wireless has been installed. | 1Gbps | Wholesale last mile provider bandwidth ranges from 100Mbps to 2.5Gbps. | 0 | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit and middle mile fiber. No last mile wireless has been installed. | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit and middle mile fiber. No last mile wireless has been installed. No CAI's have been turned-up. | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit and middle mile fiber. No last mile wireless has been installed. | We have not implemented any policies that limit bandwidth beyond the service provided nor applied any traffic prioritization. We also will not filter, limit nor block consumers from accessing any lawful content, service, service provider, or application, or prevent any consumer from attaching any legal device to the network. | Experienced delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit and middle mile fiber. No last mile wireless has been installed. | 62174 | 470 | 0 | 14400 | 4040 | 600 | 42664 | We have no wholesale dark fiber customers at this time. | 0 | 0 | 0 | 0 | Collocation space and fiber interconnection will be available for other providers at several "hub" locations across the project but these locations have not been established yet. Fiber interconnection will also be available at all of the proposed equipment cabinet locations. | N/A | N/A | CVIN, LLC | 1311 | 158 | 8 | 104 | 1460 | 400 |  | 2852 | 0 | 0 | 6293 | N/A | N/A | TRUE
NT10BIX5570126 | 2013 | $74,668 | Higher than baseline plan due to construction challenges associated with rocky terrain in northern mountainous segments. | 0 | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax. | 0 | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax. | 10Gbps | No change from baseline plan. | 0 | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax. | 1Gbps | Wholesale last mile provider bandwidth ranges from 100Mbps to 10Gbps. | 0 | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Public Safety Entities generally increase from current 100Mbps speeds to 1Gbps speeds. Libraries generally increase from current 10Mbps speeds to 1Gbps speeds. Community Colleges generally increase from current 1Gbps speeds to 1Gbps speeds with diverse routing. County Offices of Education generally increase from current 1Gbps speeds to 1Gbps speeds with diverse routing. California State Universities generally increase from current 1Gbps speeds to 10Gbps speeds with diverse routing. | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax last mile. | We have not implemented any policies that limit bandwidth beyond the service provided nor applied any traffic prioritization. We also will not filter, limit nor block consumers from accessing any lawful content, service, service provider, or application, or prevent any consumer from attaching any legal device to the network. | It was not feasible nor prudent to deploy proposed 3.65MHz WiMax last mile. | 62174 | 2782 | 46 | 33760 | 1728 | 554 | 23304 | We have one wholesale dark fiber customer, Kings County Office of Education, who is leasing 46 miles. | 1080 | 278 | 34 | 768 | Collocation space and fiber interconnection is available for other providers at several "hub" locations across the project. Fiber interconnection is also available at all of the equipment cabinet locations. | N/A | N/A | CVIN, LLC | 1311 | 158 | 8 | 104 | 1460 | 400 |  | 2852 | 0 | 0 | 6293 | We entered into nine interconnection agreements and did not deny any request for interconnection. | We have one peering and transit agreement with the Corporation for Educational Network Initiatives in California (CENIC). | TRUE
NT10BIX5570127 | 2010 | 0 | N/At | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | Not providing any services at this time. | Not providing any services at this time. | Not providing services at this time. | 14000 | 0 | 0 | 0 | 4000 | 0 | 10000 | Zero at this time. | 0 | 0 | 0 | 0 | N/A | N/A | None at this time | Utopia | 103 | 5 | 3 | 20 | 76 | 102 |  | 139 | 9 | 13 | 470 | N/A | N/A | TRUE
NT10BIX5570127 | 2011 | 147368 | This is consistent with the baseline plan. | 0 | N/A | 0 | N/A | 10 Gbps | This is consistent with the baseline plan. | 0 | N/A | 10 Mbps | This is lower than anticipated in the baseline plan. Cost is the most prohibiting factor for most CAI's. | 0 | N/A | Average increase in broadband speed estimated from existing T1 services (1.544Mbps) to an average connection speed of symmetrical 10 Mbps provided with fiber. This is 6.5 times faster. This was calculated by dividing 10 by 1.544. | UTOPIA does not provide retail services. UTOPIA is a government agency and operates an open access network wholesaling end to end transport services to various retail service providers. As a government agency, UTOPIA can also provide wholesale services directly to other government entities. Please see service offering attachment for details. | All network devices are managed by UTOPIA on a separate VLAN that is not customer or edge accessible. UTOPIA uses 802.1p prioritization tagging at customer sites to identify the priority of customer traffic based on the type of circuit that is ordered, giving priority to traffic in the following order from highest to lowest: Management, Public Safety/Security, Business Gold/TLS, Voip, IPTV, Business Data, Residential Data. Traffic queues are implemented on aggregation and core devices to enforce traffic priorities. All aggregation links and devices are actively monitored and upgraded when link capacity reaches 60% utilization at 95% percentile statistical useage. We have cooperated with FBI lawful interception requests. We also notify customers of copyright infringement complaints but do not actively block or disconnect customers from accessing unlawful content. | No subscribers have dropped the broadband service provided through this project. | 28212 | 1028 | 0 | 343 | 20131 | 0 | 6710 | None | 720 | 720 | 0 | 0 | We are extending our existing network using BTOP funds and do not have collocation space allocated in our BTOP project. However, our existing network does contain collocation space where we interconnect with providers and customers and in some cases we interconnect with the providers in their collocation facilities. | None have been made. | In UTOPIA's case, we are focused on providing network connectivity to many different public safety agencies. We have benefited by working closely with local government entities to form public safety partnerships. These partnerships have begun to increase collaborative use and help in the development of various uses of the network. | Utopia | 103 | 5 | 3 | 20 | 76 | 102 |  | 139 | 9 | 13 | 470 | Zero new agreements, 3 agreements in negotiation, No requests have been denied. | N/A | TRUE
NT10BIX5570127 | 2012 | 109142 | This is consistent with the baseline plan. | 0 | N/A | 0 | N/A | 10 Gbps | This is consistent with baseline plan. | 0 | N/A | 10 Mbps | This is lower than anticipated in the baseline plan. Cost is the most prohibiting factor for most CAI's. | 0 | N/A | Average increase in broadband speed estimated from existing T1 services (1.544Mbps) to an average connection speed of symmetrical 10 Mbps provided with fiber. This is 6.5 times faster. This was calculated by dividing 10 by 1.544. | UTOPIA does not provide retail services. UTOPIA is a government agency and operates an open access network wholesaling end to end transport services to various retail service providers. As a government agency, UTOPIA can also provide wholesale services directly to other government entities. Please see service offering attachment for details. | All network devices are managed by UTOPIA on a separate VLAN that is not customer or edge accessible. UTOPIA uses 802.1p prioritization tagging at customer sites to identify the priority of customer traffic based on the type of circuit that is ordered, giving priority to traffic in the following order from highest to lowest: Management, Public Safety/Security, Business Gold/TLS, Voip, IPTV, Business Data, Residential Data. Traffic queues are implemented on aggregation and core devices to enforce traffic priorities. All aggregation links and devices are actively monitored and upgraded when link capacity reaches 60% utilization at 95% percentile statistical useage. We have cooperated with FBI lawful interception requests. We also notify customers of copyright infringement complaints but do not actively block or disconnect customers from accessing unlawful content. | No subscribers have dropped the broadband service provided through this project. | 28212 | 11009 | 0 | 3670 | 10150 | 0 | 3383 | N/A | 3840 | 3840 | 0 | 0 | We are extending our existing network using BTOP funds and do not have collocation space allocated in our BTOP project. However, our existing network does contain collocation space where we interconnect with providers and customers and in some cases we interconnect with the providers in their collocation facilities. | None have been made. | In UTOPIA's case, we are focused on providing network connectivity to many different public safety agencies. We have benefited by working closely with local government entities to form public safety partnerships. These partnerships have begun to increase collaborative use and help in the development of various uses of the network. | Utopia | 103 | 5 | 3 | 20 | 76 | 102 |  | 139 | 9 | 13 | 470 | Two new agreements, One in negotiation, Zero denied | N/A | TRUE
NT10BIX5570128 | 2010 | 0 | Not yet deployed | 0 | N/A | 0 | N/A | 0 | Not yet deployed | 0 | N/A | 0 | Not yet deployed | 0 | N/A | N/A | N/A | N/A | N/A | 72793 | 0 | 0 | 0 | 34940 | 0 | 37853 | N/A | 0 | 0 | 0 | 0 | N/A not yet deployed | N/A | N/A | Troy Cablevision, Inc. | 62 | 10 | 5 | 1 | 15 | 68 |  | 16 | 16 | 5 | 198 | N/A | N/A | TRUE
NT10BIX5570128 | 2011 | [REDACTED] | Based on miles deployed (273) divided by budget cost classification number nine (9) - Construction. Average cost per mile is below the Baseline Projections. Although 273 miles have been constructed only 34.7% or approximately 95 miles have been activated. Additional construction cost will be incurred once the remaining miles are activated. | 0 | Not applicable. | 0 | Not applicable. | 1 Gbps | [REDACTED] | 0 | Not applicable. | 10.82 Mbps | 1 Mbps â€“ 1 Gbps are available. | 0 | Not applicable. | The actual increase per customer would be difficult to calculate because SmartBand would only increase speed based on customer request. Additionally, previous bandwidth speeds are not always known. The biggest improvement is the physical connection itself. Previously most of the physical connections in our service area were limited to 100 Mbps per second. Today all new connections and any upgraded connections will have capacity to receive 1 Gbps or 10 times most previous connections. Listed below are the known broadband speed increases since the CAIâ€™s direct connection to the network: Original SB Connection Upgraded -Local School System 10 Mbps 20 Mbps -Local School System 50 Mbps 100 Mbps | Service offerings include: -Switched Ethernet 10 Mbps to 1000 Mbps -Internet Access 1 Mbps to 1000 Mbps | 7a. SmartBand provides Internet services to Community Anchor Institutions (CAI's - organizations such as schools, community colleges, other institutions of higher education, and community support organizations) in an open, non-discriminatory manner. Any CAI within the SmartBand service area is eligible to connect at reasonable rates and terms. As a Middle Mile provider, SmartBand uses multiple upstream internet service providers that provide full access to the public Internet. SmartBand does not make any distinction in its treatment of customer traffic based on application or content. In some areas, SmartBand also provides lit capacity and other middle mile services to private-sector, Middle Mile operators and wholesalers in an open, provider-neutral and non-discriminatory fashion. Any Middle or Last Mile provider or wholesaler within the SmartBand service area is eligible to connect at reasonable rates and terms, at locations where are available. Bandwidth Limitations - Customer Bandwidth is capped based on the level of service or package purchased. For example, SmartBand does not limit Bandwidth based on application type. Traffic Prioritization - Voice Traffic is given priority in order to ensure quality of service for lifeline services as required by applicable regulatory requirements. 7b. No | Not applicable. | 74830 | 782 | 2037 | 33421 | 34158 | 0 | 4432 | Not applicable. | 3340 | 2348 | 18 | 974 | Not applicable. | [REDACTED] | Under the subject best practices/lessons learned Troy Cable found the following issues and resolutions: Lesson 1 - start early, plan extensively, build in expected and unexpected obstacles and develop a plan to resolve any issues that may arise; Lesson 2 â€“ during the Request for Proposal phase, develop a grading or rating system to include the following: contract price, references and past experience, financial availability, company attributes, or product lead time and warranty; Lesson 3 â€“ incorporate the potential for categorical awards into your Request for Proposal. Categorical awards will provide an opportunity for the Grant Recipient to award multiple contracts to potential vendors and will provide a backup plan for the Grant Recipient for those Vendors who do not follow through with their bid; Lesson 4 â€“ construction planning is critical to the overall success of the Project, there is never enough planning. When planning, make sure you incorporate the permitting process and lead times into your construction schedule; Lesson 5 â€“ secure the bid pricing with a bond for the length of your Grant, review the fine print of a Vendors proposal and anticipate how that will affect the outcome of your overall project and budget; Lesson 6 â€“ order materials in advance to allow for extended lead times or delays in delivery, at least 10 â€“ 12 weeks prior to scheduled construction start; Lesson 7 â€“ create job segments for your construction project to track the progress, material and equipment costs, and cost of goods associated with all areas of your project; and finally, Lesson 8 â€“ create a strong Project Team to develop, implement, maintain, manage, review, and execute all aspects of the Project. | Troy Cablevision, Inc. | 62 | 10 | 5 | 1 | 15 | 68 |  | 16 | 16 | 5 | 198 | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570128 | 2012 | [REDACTED] | Based on route miles deployed 424.38 divided by budget cost classification number nine (9) - Construction. Average cost per mile is below the Baseline Projections. Although 424.38 route miles have been constructed, only 90% or approximately 382.08 miles have been activated. Additional construction cost will be incurred once the remaining miles are activated. | 0 | Not Applicable | 0 | Not Applicable | 1 Gbps | [REDACTED] | 0 | Not Applicable | [REDACTED] | [REDACTED] | 0 | Not Applicable | [REDACTED] | Service offerings include: -Switched Ethernet 10 Mbps to 1000 Mbps -Internet Access 1 Mbps to 1000 Mbps See attached pricing schedule. | 7a. SmartBand provides Internet services to Community Anchor Institutions (CAI's - organizations such as schools, community colleges, other institutions of higher education, and community support organizations) in an open, non-discriminatory manner. Any CAI within the SmartBand service area is eligible to connect at reasonable rates and terms. As a Middle Mile provider, SmartBand uses multiple upstream Internet Service Providers that provide full access to the public Internet. SmartBand does not make any distinction in its treatment of customer traffic based on application or content. In some areas, SmartBand also provides lit capacity and other Middle Mile services to private-sector, Middle Mile operators and wholesalers in an open, provider-neutral and non-discriminatory fashion. Any Middle or Last Mile provider or wholesaler within the SmartBand service area is eligible to connect at reasonable rates and terms, at locations where available. Bandwidth Limitations - Customer Bandwidth is capped based on the level of service or package purchased. For example, SmartBand does not limit Bandwidth based on application type. Traffic Prioritization - Voice Traffic is given priority in order to ensure quality of service for lifeline services as required by applicable regulatory requirements. 7b. No | Not Applicable | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | Not Applicable | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | Not Applicable | [REDACTED] | Under the subject best practices/lessons learned Troy Cable found the following issues and resolutions: Lesson 1 - start early, plan extensively, build in expected and unexpected obstacles and develop a plan to resolve any issues that may arise; Lesson 2 â€“ during the Request for Proposal phase, develop a grading or rating system to include the following: contract price, references and past experience, financial availability, company attributes, or product lead time and warranty; Lesson 3 â€“ incorporate the potential for categorical awards into your Request for Proposal. Categorical awards will provide an opportunity for the Grant Recipient to award multiple contracts to potential vendors and will provide a backup plan for the Grant Recipient for those Vendors who do not follow through with their bid; Lesson 4 â€“ construction planning is critical to the overall success of the Project, there is never enough planning. When planning, make sure you incorporate the permitting process and lead times into your construction schedule; Lesson 5 â€“ secure the bid pricing with a bond for the length of your Grant, review the fine print of a Vendors proposal and anticipate how that will affect the outcome of your overall project and budget; Lesson 6 â€“ order materials in advance to allow for extended lead times or delays in delivery, at least 10 â€“ 12 weeks prior to scheduled construction start; Lesson 7 â€“ create job segments for your construction project to track the progress, material and equipment costs, and cost of goods associated with all areas of your project; and finally, Lesson 8 â€“ create a strong Project Team to develop, implement, maintain, manage, review, and execute all aspects of the Project. | Troy Cablevision, Inc. | 62 | 10 | 5 | 1 | 15 | 68 |  | 16 | 16 | 5 | 198 | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570128 | 2013 | [REDACTED] | [REDACTED] | 0 | Not Applicable. | 0 | Not Applicable. | 100Gbps | [REDACTED] | 0 | Not Applicable. | 58.43Mbps | [REDACTED] | 0 | Not Applicable. | [REDACTED] | Service offerings include: -Switched Ethernet 10 Mbps to 10,000 Mbps -Internet Access 1 Mbps to 10,000 Mbps See attached pricing schedule. | 7a. SmartBand provides Internet services to Community Anchor Institutions (CAI's - organizations such as schools, community colleges, other institutions of higher education, and community support organizations) in an open, non-discriminatory manner. Any CAI within the SmartBand service area is eligible to connect at reasonable rates and terms. As a Middle Mile provider, SmartBand uses multiple upstream Internet Service Providers that provide full access to the public Internet. SmartBand does not make any distinction in its treatment of customer traffic based on application or content. In some areas, SmartBand also provides lit capacity and other Middle Mile services to private-sector, Middle Mile operators and wholesalers in an open, provider-neutral and non-discriminatory fashion. Any Middle or Last Mile provider or wholesaler within the SmartBand service area is eligible to connect at reasonable rates and terms, at locations where available. Bandwidth Limitations - Customer Bandwidth is capped based on the level of service or package purchased. For example, SmartBand does not limit Bandwidth based on application type. Traffic Prioritization - Voice Traffic is given priority in order to ensure quality of service for lifeline services as required by applicable regulatory requirements. 7b. No | [REDACTED] | 74830 | 19712 | 2037 | 53081 | 0 | 0 | 0 | Not Applicable. | 3340 | 2348 | 18 | 974 | Not Applicable. | [REDACTED] | Under the subject best practices/lessons learned Troy Cable found the following issues and resolutions: Lesson 1 - start early, plan extensively, build in expected and unexpected obstacles and develop a plan to resolve any issues that may arise; Lesson 2 â€“ during the Request for Proposal phase, develop a grading or rating system to include the following: contract price, references and past experience, financial availability, company attributes, or product lead time and warranty; Lesson 3 â€“ incorporate the potential for categorical awards into your Request for Proposal. Categorical awards will provide an opportunity for the Grant Recipient to award multiple contracts to potential vendors and will provide a backup plan for the Grant Recipient for those Vendors who do not follow through with their bid; Lesson 4 â€“ construction planning is critical to the overall success of the Project, there is never enough planning. When planning, make sure you incorporate the permitting process and lead times into your construction schedule; Lesson 5 â€“ secure the bid pricing with a bond for the length of your Grant, review the fine print of a Vendors proposal and anticipate how that will affect the outcome of your overall project and budget; Lesson 6 â€“ order materials in advance to allow for extended lead times or delays in delivery, at least 10 â€“ 12 weeks prior to scheduled construction start; Lesson 7 â€“ create job segments for your construction project to track the progress, material and equipment costs, and cost of goods associated with all areas of your project; and finally, Lesson 8 â€“ create a strong Project Team to develop, implement, maintain, manage, review, and execute all aspects of the Project. | Troy Cablevision, Inc. | 62 | 10 | 5 | 1 | 15 | 68 |  | 16 | 16 | 5 | 198 | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570129 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Rockbridge, County of | 14 | 4 | 1 | 3 | 2 | 20 |  | 8 | 1 | 0 | 53 | N/A | N/A | TRUE
NT10BIX5570129 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 14750 | 0 | 0 | 0 | 14750 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Rockbridge, County of | 14 | 4 | 1 | 3 | 2 | 20 |  | 8 | 1 | 0 | 53 | N/A | N/A | TRUE
NT10BIX5570129 | 2012 | $29,000 | No variance | 0 | N/A | 0 | N/A | 1 Gbps | No variance | 0 | N/A | 100 Mbps | No variance | 0 | N/A | N/A | N/A | N/A | N/A | 14750 | 0 | 0 | 0 | 14750 | 0 | 0 | N/A | 4500 | 2250 | 0 | 2250 | N/A | N/A | N/A | Rockbridge, County of | 14 | 4 | 1 | 3 | 2 | 20 |  | 8 | 1 | 0 | 53 | N/A | N/A | TRUE
NT10BIX5570129 | 2013 | $43,577 | Variance from baseline from reduced original network mileage and increased cost from rock encountered during underground construction. | 0 | N/A | 0 | N/A | 1 Gbps | No variance | 0 | N/A | 100 Mbps | No variance | 0 | N/A | N/A - Rockbridge Area Network Authority (RANA) will not be providing any services to the end-users. RANA will sell wholesale services to service providers that will then offer services to the end-users. | N/A - Rockbridge Area Network Authority (RANA) will not be providing any services to the end-users. RANA will sell wholesale services to service providers that will offer services to the end-users. | Rockbridge Area Network Authority (RANA) limits the total bandwidth that the service provider can transport over the network for a certain monthly cost. If the service provider needs more bandwidth then they can upgrade their transport bandwidth. RANA has not limited or blocked end-users or service providers from accessing any lawful content. | 0 | 14750 | 0 | 0 | 0 | 14750 | 0 | 0 | N/A | 4500 | 2250 | 0 | 2250 | N/A | N/A | Please start early on community support and planning for marketing the new network. Our operating expenses were higher than anticipated in early project planning, but with the steady increase in network users, they are predicted to level out after the first year of operation. | Rockbridge, County of | 14 | 4 | 1 | 3 | 2 | 20 |  | 8 | 1 | 0 | 53 | N/A | N/A | TRUE
NT10BIX5570130 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A. Awaiting approval of Environmental Assessment | N/A. Awaiting approval of Environmental Assessment | 7a. Network Management policies are being developed and will be completed in April, 2011. 7b. N/A | N/A. Awaiting approval of Environmental Assessment | 140474 | 0 | 0 | 0 | 107210 | 16632 | 16632 | N/A | 0 | 0 | 0 | 0 | N/A. Awaiting approval of Environmental Assessment | N/A. Awaiting approval of Environmental Assessment | N/A. Awaiting approval of Environmental Assessment | Trillion Communications Corp. | 105 | 11 | 3 | 3 | 30 | 16 |  | 191 | 53 | 6 | 418 | N/A | N/A | TRUE
NT10BIX5570130 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | No variance | 1Gbps | No variance | 0 | N/A | 0 | N/A | The broadband speeds have not increased since construction/deployment has not begun | Pricing plans have not been provided, since construction/deployment have not begun | Network Management policies have not been provided, since the network has not begun providing services. | N/A | 140474 | 0 | 336 | 2016 | 107210 | 16632 | 16632 | We are currently proposing to lease dark fiber to the Alabama Department of Homeland Security and Emergency Management. | 0 | 0 | 0 | 0 | The network will collocate equipment within the following service provider interconnect locations: (1) Level 3 Communication's Marion Junction, AL Regeneration Facility , (2) Earthlink/Deltacom's Carrier Hotel in Montgomery, AL, (3) Atlanta's 55 Marietta Street Carrier Hotel, and (4) Level 3 Communication's Mobile, AL Carrier Hotel. The network has 31 terminals located throughout the footprint; any terminal can be used for incumbent service providers to interconnect to the network. This includes but not limited to Pinebelt Telephone, Hayneville Telephone, Frontier Com,, Magnolia Bell, etc. | A2D, Inc. is a small business that meets the requirements of SDB. A2D, Inc is the sub-recipient. Other SDB contractors include Concise and GlobaServe | 1) For an underground burial network, a significant amount of extra effort and resource allocation needs to go into utility data collection in rural demographics. We found that between severe lack of utility data by local municipalities and lack of utility locating services a significant amount of additional time, effort and resources went toward our GPS locate/permitting tasks. 2) The awareness of Broadband as a utility model versus and Service Provider model is much needed in the municipal sector so as to educate them on the legislative differences, as it relates to franchise fees, right of ways and etc. Trillion does not underestimate the amount of up front municipal understanding and support required to successfully advance this project. | Trillion Communications Corp. | 105 | 11 | 3 | 3 | 30 | 16 |  | 191 | 53 | 6 | 418 | Five (5) Interconnection Agreements are currently under negotiation. We have not denied any requests for interconnection. | One (1) Peering and Transit Agreement is currently negotiation. We have not denied any requests for Peering or Transit Interconnection | TRUE
NT10BIX5570130 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 10 Gbps | No Variance | 1Gbps | No Variance | 1Gbps | No Variance | 5Mbps | No Variance | The broadband speeds have not increased since the network construction and deployment effort have just began. | Pricing Plans were submitted to NTIA and NOAA during the July 2012 CAP Responses. The Plans covered potential revenue streams from Community Anchor Institutes and Businesses that were to be served in the project area. | 7a. No Network Management Policies are in place at this time. 7b. Construction of the network has terminated. Therefore, no services are provided. | N/A | 140474 | 0 | 0 | 0 | 107210 | 16632 | 16632 | N/A | 0 | 0 | 0 | 0 | Trillion was notified by NOAA of the project's termination on September 26, 2012. No co-location sites in place. | Since the projectâ€™s inception, A2D served as a Sub-Recipient and was also a small business that met the requirements of SDB. Other disadvantaged Small Businesses involved in the project as contractors included Concise Communications and GlobalServe. | N/A | Trillion Communications Corp. | 105 | 11 | 3 | 3 | 30 | 16 |  | 191 | 53 | 6 | 418 | Trillion was notified by NOAA of the project's termination on September 26, 2012. No additional negotiations planned. | Trillion was notified by NOAA of the project's termination on September 26, 2012. No additional negotiations planned. | TRUE
NT10BIX5570131 | 2010 | N/A | N/A | N/A | N/A | N/A | N/A | 1 GIG | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No Anchor Institutions have been connected to our network yet. There is no increase in broadband speed to report at this time. | No retail services are being provided at this time. | No network management policies are in place at this time. Pricing and policy development are on hold pending federal approval of our environmental assessment. | No subscribers are connected to our network yet, as construction is on hold pending federal approval of our environmental assessment. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We currently have no wholesale dark fiber customers and are not anticipating any with this project. | 0 | 0 | 0 | 0 | We have not yet constructed any facilities pending federal approval of our environmental assessment. | We have not issued any subcontracts or subgrants. | Start the environmental assessment process as early as possible. | Peoples Telephone Cooperative Inc. | 53 | 18 | 7 | 0 | 48 | 11 |  | 50 | 22 | 0 | 209 | N/A | N/A | TRUE
NT10BIX5570131 | 2011 | 32036.40 | N/A | N/A | N/A | N/A | N/A | 10 Gig | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | We plan to provide ethernet services at speeds from 10 Meg to 10 Gig. | We have a network management policy posted on our website at www.peoplescom.net. We have never, nor do we ever intend to, block consumers from accessing anything noted above nor will we prevent them from attaching any legal device to the network. | N/A | 73095 | 5956 | 0 | 0 | 67139 | 0 | 0 | We do not intend to wholesale dark fiber. | 0 | 0 | 0 | 0 | We have provided hand-holes approximately every mile for Last Mile provider interconnection to our network and to their customers. We do not contemplate leasing floor space in any of our cabinets or offices. We have terminal space in a carrier hotel in Dallas and access to one in Longview. Each of these places has extensive interconnection capabilities in various meet points. | N/A | Order fiber optic cable ahead of schedule. | Peoples Telephone Cooperative Inc. | 53 | 18 | 7 | 0 | 48 | 11 |  | 50 | 22 | 0 | 209 | One interconnection agreement was procured during 2011. We are currently negotiating 5 additional agreements. We have not denied any requests for interconnection and am, in fact, actively seeking interconnection with last mile providers. | None. | TRUE
NT10BIX5570131 | 2012 | 47,269.22 | Average cost per mile includes fiber and construction costs, but engineering fees were not included when calculating this figure. | N/A | N/A | N/A | N/A | 10 Gig | N/A | N/A | N/A | 252 Meg | N/A | N/A | N/A | The average increase in broadband speed is not available at this time. | Peoples offers ethernet services at speeds from 10 Meg to 10 Gig. | Currently, voice is prioritized throughout our network. We are presently developing a bandwidth prioritization schedule for medical and healthcare providers' traffic as well. We have not limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal devices to the network. | We have had no subscribers drop the bandwidth service provided through this project. | 44822 | 44822 | 0 | 0 | 40608 | 0 | 0 | We do not intend to wholesale dark fiber. | 0 | 0 | 0 | 0 | We have provided hand-holes approximately every mile to connect to ISPs, Last Mile Providers and end users to the fiber. We do not contemplate leasing floor space or space in any of our cabinets or offices. We have terminal space in a "carrier hotel" in Dallas and access to one in Longview. Each of these places has extensive interconnection capabilities for many carriers. | N/A | It is always prudent to order fiber optic cable ahead of schedule. In addition, do detailed engineering on routes early in the project so route changes have time to get through extremely long approval cycles. | Peoples Telephone Cooperative Inc. | 53 | 18 | 7 | 0 | 48 | 11 |  | 50 | 22 | 0 | 209 | We are providing data interconnection with one wireless private network provider interfacing to over 50 schools in Region 8. We are also providing fiber interconnection for seven small regional ISPs. We have twelve points of interconnection with Verizon through a SuddenLink cable TV subsidiary and several points of interconnection to a WISP known as Peoples Wireless. We have not denied any requests for interconnection. | We are providing internet to two ILECs in the area as network peers. We have not denied any requests for peering or transit agreements. | TRUE
NT10BIX5570132 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution; Dedicated Internet Access services and Long Distance Access services. | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR-Plateau does not and has not ever blocked our users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR-Plateau operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available to us. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to our customers, we have employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, however due to the increased demand for bandwidth; the DPI system will be brought back online in 2011 with the intention of prioritizing certain applications over others on our wireless access networks only. In managing our network through traffic prioritization, we intend to give a lower priority to peer to peer file sharing traffic and other traffic that does not noticeably impair our customer experience. Though a lower priority will be given to certain applicati | N/A | 18161 | 0 | 0 | 0 | 0 | 0 | 18161 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | E.N.M.R. Telephone Cooperative | 59 | 10 | 2 | 4 | 22 | 61 |  | 151 | 60 | 0 | 369 | N/A | N/A | TRUE
NT10BIX5570132 | 2011 | 0 | Minimal construction was completed as of 12/31/11. Only 15.5 miles of duct (with only 5 miles of fiber cabling) was placed as of the end of the year therefore an accurate average cost per mile could not be calculated. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution; Dedicated Internet Access services and Long Distance Access services. | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR-Plateau does not and has not ever blocked our users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR-Plateau operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available to us. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to our customers, we have employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, reinstated again in 2011 for approximately five months and then discontinued again around November of 2011. At this time ENMR-Plateau does not prioritize any network traffic and at no time will we block access to any lawful content, service, service provider, or application. | N/A | 15615 | 0 | 0 | 0 | 15615 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Interconnection with other network providers requires a physical fiber meet at one of Plateauâ€™s Points of Interconnection. The connecting entity would establish a fiber splice meet-point adjacent to Plateauâ€™s POI building. This fiber splice would connect the network providerâ€™s fiber to Plateauâ€™s single-mode fiber entering the building and terminating on Plateauâ€™s optical equipment. This enables optical level interconnection between the other network providerâ€™s optical equipment and Plateauâ€™s. Interconnections with customers of Plateauâ€™s services are established via direct last mile fiber connections terminating at the customer premise. | N/A | N/A | E.N.M.R. Telephone Cooperative | 59 | 10 | 2 | 4 | 22 | 61 |  | 151 | 60 | 0 | 369 | (1) 0, (2) 0, (3) ENMR-Plateau has not denied any requests for interconnection during this reporting period. | N/A | TRUE
NT10BIX5570132 | 2012 | $75,921.99 | Total cost of construction divided by the number of fiber miles constructed as of 12/31/12. | 0 | N/A | 0 | N/A | 1Gb | The maximum broadband speed advertised by ENMR-Plateau is 1Gb. | 0 | N/A | 0 | No CAIs have been connected as of 12/31/12. | 0 | N/A | N/A | Long Haul Special Access services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access services which are typically Ethernet services from the local Interconnection point to the anchor institution. | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR Telephone Cooperative does not and has not ever blocked users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR Telephone Cooperative operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to its customers, ENMR Telephone Cooperative has employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, reinstated again in 2011 for approximately five months and then discontinued again around November of 2011. ENMR reinstated the use of DPI rate shaping to limit peer to peer traffic only on the wireless internet product MMDS on July 13, 2012. | N/A | 15615 | 12997 | 0 | 0 | 2618 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Interconnection with other network providers requires a physical fiber meet at one of ENMR's Points of Interconnection. The connecting entity would establish a fiber splice meet-point adjacent to ENMR's POI building. This fiber splice would connect the network provider's fiber to ENMR's single-mode fiber entering the building and terminating on ENMR's optical equipment. This enables optical level interconnection between the other network provider's optical equipment and ENMR's. Interconnections with customers of ENMR's services are established via direct last mile fiber connections terminating at the customer premise. | N/A | N/A | E.N.M.R. Telephone Cooperative | 59 | 10 | 2 | 4 | 22 | 61 |  | 151 | 60 | 0 | 369 | (1) ENMR Telephone Cooperative has entered into 1 new interconnection agreement this annual reporting period with Conterra Ultra Broadband, (2) ENMR Telephone Cooperative is currently negotiating 1 new agreement, (3) ENMR Telephone Cooperative has not denied any requests for interconnection during this reporting period. | N/A | TRUE
NT10BIX5570132 | 2013 | $78,300.09 | Total cost of construction divided by the number of fiber miles constructed as of 7/31/13, the project's end date. | 0 | N/A | 0 | N/A | 1Gb | The maximum broadband speed advertised by ENMR-Plateau is 1Gb. | 0 | N/A | 0 | Even though all 369 CAI's had been connected as of 7/31/13, none were being provided with service by ENMR Telephone Cooperative at that time. | 0 | N/A | N/A | Long Haul Special Access services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access services which are typically Ethernet services from the local Interconnection point to the anchor institution. | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR Telephone Cooperative does not and has not ever blocked users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR Telephone Cooperative operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to its customers, ENMR Telephone Cooperative has employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, reinstated again in 2011 for approximately five months and then discontinued again around November of 2011. ENMR reinstated the use of DPI rate shaping to limit peer to peer traffic only on the wireless internet product MMDS on July 13, 2012. | No CAI subscribers were activated for service by the end date of 7/31/13. | 15615 | 15615 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Interconnection with other network providers requires a physical fiber meet at one of ENMR's Points of Interconnection. The connecting entity would establish a fiber splice meet-point adjacent to ENMR's POI building. This fiber splice would connect the network provider's fiber to ENMR's single-mode fiber entering the building and terminating on ENMR's optical equipment. This enables optical level interconnection between the other network provider's optical equipment and ENMR's. Interconnections with customers of ENMR's services are established via direct last mile fiber connections terminating at the customer premise. | N/A | N/A | E.N.M.R. Telephone Cooperative | 59 | 10 | 2 | 4 | 22 | 61 |  | 151 | 60 | 0 | 369 | (1) ENMR Telephone Cooperative has entered into 3 new interconnection agreements this annual reporting period with Verizon Wireless, North Central Economic Development and Northern New Mexico Telecom, (2) ENMR Telephone Cooperative is currently negotiating 1 new agreement, (3) ENMR Telephone Cooperative has not denied any requests for interconnection during this reporting period. | N/A | TRUE
NT10BIX5570133 | 2010 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 92128 | 0 | 0 | 0 | 76989 | 15139 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | ION Newco Corp | 9 | 2 | 7 | 27 | 48 | 7 |  | 23 | 5 | 0 | 128 | N/A | N/A | TRUE
NT10BIX5570133 | 2011 | 37759 | Baseline=$35,168. As of December 31 we have a relatively small amount of new miles completed upon which to compute an average cost. A disproportionately high amount of buried construction in the sample compared to the overall new build to be completed tends to increase the average cost compared to the baseline plan. | 0 | N/A | 0 | N/A | 10GBPS | No variance | 0 | N/A | 10GBPS | No variance | 0 | N/A | Average increase is 2.5 times their current capacity. Calculated as follows - one CAI went from 45 Mbit/s to 150 Mbit/s, the other doubled their capacity by adding a second link. Two customers have been connected but are not yet receiving service. | N/A | (7a)Network management policies are found on the ION website: www.i-o-n.com. (7b)ION has not limited or blocked consumers from accessing the network. | N/A | 96885 | 18192 | 0 | 0 | 63554 | 15139 | 0 | N/A | 0 | 0 | 0 | 0 | Option 1) In order to facilitate connectivity ION will provision a fiber optic tie cable between its equipment and other last mile carriers located in the carrier hotel, this generally requires a one time construction expense of between $1500 and $3500 in order to enable the connection. Option 2) In the event the last mile service provider wishes to connect at the Incumbent Local Exchange Carrier (ILEC) central office (CO), we will construct our own collocation space within the ILEC CO which enables us to use Unbundled Network Elements (UNEs) such as fiber ties between cages at a nominal monthly rate. | N/A | N/A | ION Newco Corp | 9 | 2 | 7 | 27 | 48 | 7 |  | 23 | 5 | 0 | 128 | (1)Four agreements entered. (2)Thirteen agreements being negotiated. (3) No request for interconnection has been denied. | N/A | TRUE
NT10BIX5570133 | 2012 | 38817 | Baseline=35,168. For various reasons there have been more buried fiber miles than originally planned. Also, make ready costs have been greater per mile than anticipated. | 0 | N/A | 0 | N/A | 10GBPS | No variance | 0 | N/A | 10GBPS | No variance | 0 | N/A | Average increase is 4 times their current capacity. Calculated based on sampling of connected CAI's where we are aware of the speed of their prior broadband service. | ION provides only wholesale services. The Development Authority of the North Country primarily sells wholesale services, however, we do have two retail Healthcare networks to which we are providing retail services. Service is Ethernet transport between healthcare sites with a shared internet component. Prices are $600 for 10 Mbps, $2,268 for 100 Mbps, and $3,218 for 1 Gbps circuits. | (7a)Network management policies are found on the ION website: www.i-o-n.com. (7b)As a wholesale service provider we do not rate limit or block any lawful content or service provider on the network. We do have several methods for prioritization of traffic, however, we have not had any customer requests to do that at this time. | N/A | 96939 | 54214 | 0 | 0 | 25009 | 17716 | 0 | N/A | 0 | 0 | 0 | 0 | Option 1) In order to facilitate connectivity ION will provision a fiber optic tie cable between its equipment and other last mile carriers located in the carrier hotel, this generally requires a one time construction expense of between $1500 and $3500 in order to enable the connection. Option 2) In the event the last mile service provider wishes to connect at the Incumbent Local Exchange Carrier (ILEC) central office (CO), we will construct our own collocation space within the ILEC CO which enables us to use Unbundled Network Elements (UNEs) such as fiber ties between cages at a nominal monthly rate. | N/A | 1. Engage pole owners early in process and frequently to avoid delays in make ready work. 2. Use the same architectural and engineering firm(s) throughout the project to build a high level of knowledge of the project and to minimize re-work. 3. Proactively engage local government, economic development agencies, chambers of commerce and industrial development agencies before project implementation to gain feedback on local needs. 4. Publish a newsletter to inform the communities of all aspects of the project. 5. Communicate with state broadband and technology office proactively providing them maps and updates of project progress and availability. 6. Continue to engage the Environmental Agencies as necessary throughout the project, paying close attention to any Special Award Conditions that were identified during the award phase. | ION Newco Corp | 9 | 2 | 7 | 27 | 48 | 7 |  | 23 | 5 | 0 | 128 | (1) 10 agreements entered. (2) 8 agreements being negotiated. (3) No request for interconnection has been denied. | N/A | TRUE
NT10BIX5570133 | 2013 | 39,455 | Baseline=35,168. For various reasons there have been more buried fiber miles than originally planned. Also, make ready costs have been greater per mile than anticipated. | 0 | N/A | 0 | N/A | 10GBPS | No variance | 0 | N/A | 10GBPS | No variance | 0 | N/A | Average increase is 4 times their current capacity. Calculated based on sampling of connected CAI's where we are aware of the speed of their prior broadband service. | ION provides only wholesale services. The Development Authority of the North Country primarily sells wholesale services, however, we do have two retail Healthcare networks to which we are providing retail services. Service is Ethernet transport between healthcare sites with a shared internet component. Prices are $600 for 10 Mbps, $2,268 for 100 Mbps, and $3,218 for 1 Gbps circuits. | (7a)Network management policies are found on the ION website: www.i-o-n.com. (7b)As a wholesale service provider we do not rate limit or block any lawful content or service provider on the network. We do have several methods for prioritization of traffic, however, we have not had any customer requests to do that at this time. | N/A | 91795 | 91795 | 0 | 0 | 0 | 0 | 0 | N/A | 2950 | 2950 | 0 | 2950 | Option 1) In order to facilitate connectivity ION will provision a fiber optic tie cable between its equipment and other last mile carriers located in the carrier hotel, this generally requires a one time construction expense of between $1500 and $3500 in order to enable the connection. Option 2) In the event the last mile service provider wishes to connect at the Incumbent Local Exchange Carrier (ILEC) central office (CO), we will construct our own collocation space within the ILEC CO which enables us to use Unbundled Network Elements (UNEs) such as fiber ties between cages at a nominal monthly rate. | N/A | 1. Engage pole owners early in process and frequently to avoid delays in make ready work. 2. Use the same architectural and engineering firm(s) throughout the project to build a high level of knowledge of the project and to minimize re-work. 3. Proactively engage local government, economic development agencies, chambers of commerce and industrial development agencies before project implementation to gain feedback on local needs. 4. Publish a newsletter to inform the communities of all aspects of the project. 5. Communicate with state broadband and technology office proactively providing them maps and updates of project progress and availability. 6. Continue to engage the Environmental Agencies as necessary throughout the project, paying close attention to any Special Award Conditions that were identified during the award phase. | ION Newco Corp | 9 | 2 | 7 | 27 | 48 | 7 |  | 23 | 5 | 0 | 128 | (1) 29 agreements entered. (2) 0 agreements being negotiated. (3) No request for interconnection has been denied. | N/A | TRUE
NT10BIX5570135 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No community anchor were connected during this reporting period | N/A | 7a.No network management policies exist that impact consumer access. Commercial access to the One Maryland Broadband Network infrastructure is limited to wholesale, dark fiber lease, over which each access seeker will be able to implement network management policies according to their own requirements. 7b. N/A | 0-percent | 153201 | 0 | 0 | 0 | 97383 | 3000 | 52818 | None this reporting period | 0 | 0 | 0 | 0 | Network providers and/or customers can access One Maryland Broadband Network dark fiber infrastructure at outdoor fiber optic splice enclosures, which occur regularly throughout the outside fiber optic plant infrastructure. | - The Canton Group is an IT services company and is providing resources for grant financial administration, project management, and construction quality assurance. The Canton Group is an existing subcontractor for the Maryland Department of IT (DOIT), and has been subcontracted work by the prime contractor to DOIT to comply with State MBE goals. | For other BTOP projects, particularly those involving multiple government recipients and sub recipients over a large geographic area, we offer the following best practices: 1) Reach out early to permitting authorities to creating awareness of the scale, scope and timing of project. Solicit permitting authority needs, and coordinate application submission logistics. This includes Right of Way owners, utilities pole owners and utility locators. 2) Closely coordinate with your Federal Program Officer on all challenges. 3) Reach out to the vendor community via a vendor fair to ensure open and competitive procurement, as well as to efficiently disseminate relevant information regarding Program requirements, limitations, and opportunities 4) Meet with all stakeholders early to establish recurring touch points to leverage their support with permitting regulatory issues, and ensure a proper understanding of financial requirements and eligible uses of Federal funds. 5) Centralize accounting and reporting functions among multiple sub recipients to the greatest degree possible, thereby leveraging economies of scale for expert resources required and minimizing the risk of errors. | Information Technology, Maryland Department of | 497 | 58 | 16 | 9 | 7 | 250 |  | 190 | 41 | 0 | 1068 | 1) 0 2) We are currently finalizing an interconnection agreement with the Maryland Broadband Cooperative, who will become a sub-recepient of the grant and will leverage fiber infrastructure constructed by the Project to provide a range of middle mile commercial services. 3) No request for interconnection have been denied. | N/A | TRUE
NT10BIX5570135 | 2011 | $79,277 | Our baseline is $72,181. We are confident that our trend will keep us well within budget. The ICBN sub recipient has averaged $61,815 per mile. This average was brought up by the DOIT portion of the project, which averaged $98,510. This latter number is not indicative of a trend as it represents all underground construction and was awarded on the previous Stateâ€™s Cable & Wire contract, which had a limited number of vendors cable of work on this scale. The Cable & Wire contract has since been re-competed and re-issued. New awards are coming in under our baseline. | 0 | N/A | 0 | N/A | 10Gbps | This the planned back haul speed. | 0 | N/A | 1Gbps | This is the average broadband speed for middle mile. | 0 | N/A | The average increase in broadband speed to CAIs as a result of the OMBN project is approximately 1 Gbps, or 1,000 Mbps. Nearly all CAIs encompassed by this project had, or still have, very limited broadband connectivity; typical connections prior to upgrade through the OMBN project were T1 circuits providing dedicated 1.5 Mbps. All new and planned CAI connections range from dedicated, symmetrical speeds of 100Mbps to 1 Gbps. One CAI was increased from 1.5Mbps to 100 Mbps, or 98.5Mbps increase. The other 9 CAIs were increased from 1.5Mbps to 1Gbps, or a 998.5Mbps increase. The overall average increase in broadband speed for OMBN is calculated at 908Mbps. | N/A | 7a. In the context of open access interconnection and non-discriminatory network management, the OMBN project is comprised of two primary components. DOIT / MdBC â€“ The Maryland Broadband cooperative is providing the open access requirement for the DOIT portion of the project. The MdBc is being granted 96 fibers through an IRU with DOIT. These fibers will be available along all backbone route miles constructed as part of the DOIT portion of the grant Program. MdBC does not provide active â€œmanagedâ€ network transport services to commercial providers, and as such will not be capable of imposing bandwidth limitations (beyond the leased amount), prioritizing traffic, or otherwise controlling network traffic carried over leased fiber strands.â€ ICBN â€“ The subgrant award to ICBN is based on the provision of a minimum of 24-fiber strands for open access lease to qualified commercial providers on a non-discriminatory basis. These fibers will be available along all route miles constructed as part of the ICBN portion of the grant Program. Currently ICBN consortium members are not planning to provide active â€œmanagedâ€ network transport services to commercial providers, and as such will not be capable of imposing bandwidth limitations, prioritizing traffic, or otherwise controlling network traffic carried over leased fiber strands.â€ 7b. No | 0-percent | 234796 | 1638 | 1684 | 0 | 97597 | 53662 | 80215 | 0 | 5860 | 3400 | 330 | 2130 | Where One Maryland Broadband Network does not have collocation access, network providers and/or customer can access dark fiber infrastructure at outdoor fiber optic splice enclosures, which occur regularly throughout the outside fiber optic plant infrastructure. | The Canton Group is an IT services company and is providing resources for grant financial administration, project management, and construction quality assurance. The Canton Group is an existing subcontractor for the Maryland Department of IT (DOIT), and has been subcontracted work by the prime contractor to DOIT to comply with State MBE goals. IPX International system Inc. is the warehousing vendor for ICBN. | For other BTOP projects, particularly those involving multiple government recipients and sub recipients over a large geographic area, we offer the following best practices: 1) Closely coordinate with your Federal Program Officer on all challenges. 2) Take advantage and attend all BTOP/NTIA drop-in calls and conferences, ensure that BTOP updates are shared with the compliance team ensuring compliance cohesiveness. 3) Reach out early to permitting authorities to creating awareness of the scale, scope and timing of project. Solicit permitting authority needs, and coordinate application submission logistics. This includes Right of Way owners, utilities pole owners and utility locators. 4) Mitigate some of the risk by the centralizing accounting and reporting functions thereby leveraging economies of scale for expert resources required and minimizing the risk of errors. 5) Meet with all stakeholders early to establish recurring touch points to leverage their support with permitting regulatory issues, and ensure a proper understanding of financial requirements and eligible uses of Federal funds. | Information Technology, Maryland Department of | 497 | 58 | 16 | 9 | 7 | 250 |  | 190 | 41 | 0 | 1068 | 1) 8 2) We currently are negotiating 12 agreement with broadband wholesalers. 3) No request for interconnection has been denied. | N/A | TRUE
NT10BIX5570135 | 2012 | $76,629 | Our baseline is $72,181. The ICBN sub recipient has averaged $79,372 per mile. The DOIT portion of the project, which averaged $72,559. We are confident that our trend will keep us well within budget, since most of the remaining work is aerial construction, which is less costly than our underground construction cost. | 0 | N/A | 0 | N/A | 40Gbps | 40Gbps is the maximum advertised broadband speed. | 0 | N/A | 1Gbps | 1Gbps is the average broadband speed for middle mile. We offer the following speed tiers 10Mgps, 100Mgps, 1Gbps, 10Gbps and 40Gbps. | 0 | N/A | The average increase in broadband speed to CAIs as a result of the OMBN project is approximately 1 Gbps, or 1,000 Mbps. Nearly all CAIs encompassed by this project had, or still have, very limited broadband connectivity; typical connections prior to upgrade through the OMBN project were T1 circuits providing dedicated 1.5 Mbps. All new and planned CAI connections range from dedicated, symmetrical speeds of 100Mbps to 1 Gbps. One CAI was increased from 1.5Mbps to 100 Mbps, or 98.5Mbps increase. All the other CAIs were increased from 1.5Mbps to 1Gbps, or a 998.5Mbps increase. The overall average increase in broadband speed for OMBN is calculated at 996.9Mbps. | Not providing retail services. | 7a. In the context of open access interconnection and non-discriminatory network management, the OMBN project is comprised of two primary components. DOIT / MdBC â€“ The Maryland Broadband cooperative is providing the open access requirement for the DOIT portion of the project. The MdBc is being granted 96 fibers through an IRU with DOIT. These fibers will be available along all backbone route miles constructed as part of the DOIT portion of the grant Program. MdBC does not provide active â€œmanagedâ€ network transport services to commercial providers, and as such will not be capable of imposing bandwidth limitations (beyond the leased amount), prioritizing traffic, or otherwise controlling network traffic carried over leased fiber strands.â€ ICBN â€“ The subgrant award to ICBN is based on the provision of a minimum of 24-fiber strands for open access lease to qualified commercial providers on a non-discriminatory basis. These fibers will be available along all route miles constructed as part of the ICBN portion of the grant Program. Currently ICBN consortium members are not planning to provide active â€œmanagedâ€ network transport services to commercial providers, and as such will not be capable of imposing bandwidth limitations, prioritizing traffic, or otherwise controlling network traffic carried over leased fiber strands.â€ 7b. No | 0-percent | 244024 | 3828 | 1466 | 0 | 100596 | 55413 | 82721 | 0 | 5860 | 3400 | 330 | 2130 | Where One Maryland Broadband Network does not have collocation access, network providers and/or customer can access dark fiber infrastructure at outdoor fiber optic splice enclosures, which occur regularly throughout the outside fiber optic plant infrastructure. | The Canton Group is an IT services company and is providing resources for grant financial administration, project management, and construction quality assurance. The Canton Group is an existing subcontractor for the Maryland Department of IT (DOIT), and has been subcontracted work by the prime contractor to DOIT to comply with State MBE goals. IPX International system Inc. is the warehousing vendor for ICBN. Baytek is an engineering subcontractor for DoIT Mack Communication is an engineering subcontractor for both ICBN & DoIT CTC is an engineering subcontractor for ICBN | For other BTOP projects, particularly those involving multiple government recipients and sub recipients over a large geographic area, we offer the following best practices: 1) Closely coordinate with your Federal Program Officer on all challenges. 2) Take advantage and attend all BTOP/NTIA drop-in calls and conferences, ensure that BTOP updates are shared with the compliance team ensuring compliance cohesiveness. 3) Reach out early to permitting authorities to creating awareness of the scale, scope and timing of project. Solicit permitting authority needs, and coordinate application submission logistics. This includes Right of Way owners, utilities pole owners and utility locators. 4) Mitigate some of the risk by the centralizing accounting and reporting functions thereby leveraging economies of scale for expert resources required and minimizing the risk of errors. 5) Meet with all stakeholders early to establish recurring touch points to leverage their support with permitting regulatory issues, and ensure a proper understanding of financial requirements and eligible uses of Federal funds. | Information Technology, Maryland Department of | 497 | 58 | 16 | 9 | 7 | 250 |  | 190 | 41 | 0 | 1068 | 1) 8 2) We currently are negotiating 42 agreement with broadband wholesalers. 3) No request for interconnection has been denied. | N/A | TRUE
NT10BIX5570135 | 2013 | $86,235 | Final average cost per new mile | 0 | N/A | 0 | N/A | 40Gbps | 40Gbps is the maximum advertised broadband speed. | 0 | N/A | 1Gbps | 1Gbps is the average broadband speed for middle mile. We offer the following speed tiers 10Mgps, 100Mgps, 1Gbps, 10Gbps and 40Gbps. | 0 | N/A | The average increase in broadband speed to CAIs as a result of the OMBN project is approximately 1 Gbps, or 1,000 Mbps. Nearly all CAIs encompassed by this project had, or still have, very limited broadband connectivity; typical connections prior to upgrade through the OMBN project were T1 circuits providing dedicated 1.5 Mbps. All new and planned CAI connections range from dedicated, symmetrical speeds of 100Mbps to 1 Gbps. One CAI was increased from 1.5Mbps to 100 Mbps, or 98.5Mbps increase. All the other CAIs were increased from 1.5Mbps to 1Gbps, or a 998.5Mbps increase. The overall average increase in broadband speed for OMBN is calculated at 996.9Mbps. | Not providing retail services. | 7a. In the context of open access interconnection and non-discriminatory network management, the OMBN project is comprised of two primary components. DOIT / MdBC â€“ The Maryland Broadband cooperative is providing the open access requirement for the DOIT portion of the project. The MdBc is being granted 96 fibers through an IRU with DOIT. These fibers will be available along all backbone route miles constructed as part of the DOIT portion of the grant Program. MdBC does not provide active â€œmanagedâ€ network transport services to commercial providers, and as such will not be capable of imposing bandwidth limitations (beyond the leased amount), prioritizing traffic, or otherwise controlling network traffic carried over leased fiber strands.â€ ICBN â€“ The subgrant award to ICBN is based on the provision of a minimum of 24-fiber strands for open access lease to qualified commercial providers on a non-discriminatory basis. These fibers will be available along all route miles constructed as part of the ICBN portion of the grant Program. Currently ICBN consortium members are not planning to provide active â€œmanagedâ€ network transport services to commercial providers, and as such will not be capable of imposing bandwidth limitations, prioritizing traffic, or otherwise controlling network traffic carried over leased fiber strands.â€ 7b. No | 0-percent | 203650 | 88696 | 53824 | 61130 | 0 | 0 | 0 | 0 | 6760 | 3900 | 330 | 2530 | Where One Maryland Broadband Network does not have collocation access, network providers and/or customer can access dark fiber infrastructure at outdoor fiber optic splice enclosures, which occur regularly throughout the outside fiber optic plant infrastructure. | The Canton Group is an IT services company and is providing resources for grant financial administration, project management, and construction quality assurance. The Canton Group is an existing subcontractor for the Maryland Department of IT (DOIT), and has been subcontracted work by the prime contractor to DOIT to comply with State MBE goals. IPX International system Inc. is the warehousing vendor for ICBN. Baytek is an engineering subcontractor for DoIT Mack Communication is an engineering subcontractor for both ICBN & DoIT CTC is an engineering subcontractor for ICBN | For other BTOP projects, particularly those involving multiple government recipients and sub recipients over a large geographic area, we offer the following best practices: As a state government agency with sub recipients of different types, there were a number of lessons that we learned along the way. The first lesson and most important is that we cannot do this project alone. We needed the help and collaboration of many of the state and local government agencies to get this done. Some of the relationships were not developed ahead of time so we had to create them as needed. The second, is that things will take longer to get done, than the forms or guidance says it will. Time must always be allotted for people and agencies to do their work and then get it back to you. The third, make sure to pay attention to and attend the webinars and circulars that are put out by the respective agencies for your project. The information can be invaluable in helping get through the project. Lastly, make sure to build a strong relationship with your federal officers on the project. As we faced challenges and successes on this project, the relationship with our team helped us to navigate the changes and move forward. | Information Technology, Maryland Department of | 497 | 58 | 16 | 9 | 7 | 250 |  | 190 | 41 | 0 | 1068 | 1) 12 2) We currently are negotiating 56 agreement with broadband wholesalers. 3) No request for interconnection has been denied. | N/A | TRUE
NT10BIX5570136 | 2010 | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | As construction has not started, an average increase estimated would be from a T1 (1.5 Mbps), which most community anchor institutions currently utilize, to having access to a 100 Mbps drop as a result of this project. | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | GovNET will have customer interconnection available on every tower, monopole and roof mount installed. Collocation space varies per Backbone or Node location, and the actual amount will be calculated when construction begins. Other network providers will be able to connect with this network at any of the equipment shelters or cabinet area drop points in the rural communities. GovNET operates as a 'carrier's carrier' and welcomes any interest in interconnection. | GovNET has issued one vendor project contract to date - the Environmental Assessment - and it was to a Woman-owned business named "Tierra Right of Way" from Tucson Arizona. | Be lucky enough to be assigned to a Federal Program Officer like Mary Rudokas (and the assistance of Norman Davis, BAH)! Her knowledge and suggestions have been instrumental for a first-time federal grantee. The BTOP Handbook is very well put together and an excellent reference utilized often. The Compliance Conference in November 2010 was very valuable to meet other recipients and network together. | GOVNET, INC. | 196 | 75 | 3 | 13 | 36 | 1 |  | 59 | 0 | 0 | 383 | Currently negotiating with two (2) last mile providers for interconnection. | Currently negotiating a Peering Agreement with Level 3. | TRUE
NT10BIX5570136 | 2011 | 0 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be in sync with its Baseline Plan by the end of Q3 2012. | 0 | n/a | 0 | n/a | 0 | Behind baseline plan due to delay in EA approval, which restricted construction. | 0 | n/a | 0 | Behind baseline plan due to delay in EA approval, which restricted construction. | 0 | n/a | Construction has not begun. However, we expect the average increase in broadband speed will increase from a T1 (1.5 Mbps) to a 100 Mbps drop as a result of this project. Most Community Anchor Institutions currently utilize 1.5 Mbps broadband speed. | n/a | We have not begun providing service due to the delay in EA approval. GovNET received its FONSI in November 2011 and construction activities are now underway. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - We do not have a fiber project. | 0 | 0 | 0 | 0 | Collocation space varies per backbone or node location. GovNET has conducted a significant amount of public outreach to develop partnerships for interconnection. Customers will be able to interconnect through almost every tower, monopole and roof mount installed through this project. Other network providers will be able to connect to the network at a majority of the equipment shelters or cabinet area drop points in the rural communities included in the network. | GovNET has issued two vendor contracts to women-owned businesses: 1. A contract with Kestrel Consulting Inc. of Hood River, Oregon, was signed in January 2011 for grant management services. 2. A contract with Tierra Right of Way Services of Tucson, Arizona, was signed in November 2010 for preparation of the Environmental Assessment. | The learning curve that went into completing the Environmental Assessment was significant and in retrospect, having a team who is aggressive on working through the detailed items to achieve FONSI is critical. It may be helpful to be directly connected with other projects that the FPO's may see similar issues so as to have someone to bounce ideas off that could benefit both projects, as often each project is an island in their own state. | GOVNET, INC. | 196 | 75 | 3 | 13 | 36 | 1 |  | 59 | 0 | 0 | 383 | We signed zero agreements last mile providers for interconnection. We have not denied any request for interconnection. | We signed two peering agreements for 2 Gigabytes of Tier One Internet access with a provider. | TRUE
NT10BIX5570136 | 2012 | 0 | FONSI not received until November 2011, and project has been under suspension since May 2012. | 0 | n/a | 0 | n/a | 0 | FONSI not received until November 2011, and project has been under suspension since May 2012. | 0 | n/a | 0 | FONSI not received until November 2011, and project has been under suspension since May 2012. | 0 | n/a | Connection to Community Anchor Institutions had not yet occurred in 2012. However, we expect the average increase in broadband speed will increase from a T1 (1.5 Mbps) to access to 100 Mbps capability as a result of this project. | n/a | Network is not yet active. | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | GovNET currently has towers available for collocation space, but no equipment shelters yet installed on the sites prior to suspension. The amount of available space varies per backbone or node location. GovNET has conducted a significant amount of public outreach to develop partnerships for interconnection. Other network providers will be able to interconnect through almost every tower, monopole and roof mount installed as Community Interconnect Points in the rural communities included in the network. | No subcontracts were made in 2012 to SDBs. | n/a | GOVNET, INC. | 196 | 75 | 3 | 13 | 36 | 1 |  | 59 | 0 | 0 | 383 | There were no interconnection agreements signed in 2012, although three (3) agreements were being negotiated. GovNET has not denied any requests for interconnection. | GovNET entered into two (2) peering agreements with a provider for 2 Gbps for Tier One internet. | TRUE
NT10BIX5570136 | 2013 | 0 | FONSI not received until November 2011, and project was under suspension from May 2012 to September 2013. Construction is currently underway. | 0 | n/a | 0 | n/a | 0 | FONSI not received until November 2011, and project was under suspension from May 2012 to September 2013. Construction is currently underway. | 0 | n/a | 0 | FONSI not received until November 2011, and project was under suspension from May 2012 to September 2013. Construction is currently underway. | 0 | n/a | We expect the average increase in broadband speed will increase from 1.5 - 10 Mbps to access to over 100Mbps - 1Gbps capability as a result of this project. | n/a | Network is not fully active yet. | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | GovNET owns collocation space, and will have towers and cabinet space available for collocation. | No subcontracts were made in 2013 to SDBs. | n/a | GOVNET, INC. | 196 | 75 | 3 | 13 | 36 | 1 |  | 59 | 0 | 0 | 383 | Due to project suspension and lift occurring in September 2013, here were no interconnection agreements signed in 2013, although two (2) agreements were being revived and negotiated. GovNET has not denied any requests for interconnection. | GovNET had entered into two (2) peering agreements with a provider for 2 Gbps for Tier One internet, which were terminated due to suspension. One agreement was reinstated at the end of 2013. | TRUE
NT10BIX5570138 | 2010 | 0 | NA at this time as construction has not begun | 0 | NA | 0 | NA | 0 | NA at this time as construction has not begun | 0 | NA | 0 | NA at this time as construction has not begun | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | NA | NA | Region 18 Education Svc Ctr. | 19 | 4 | 0 | 0 | 2 | 12 |  | 20 | 1 | 5 | 63 | NA | NA | TRUE
NT10BIX5570138 | 2011 | 57881 | This amount represents a 28% reduction in cost per mile. This is due to the inclusion of 48.05 air miles in the calculation. The air miles were not included in our original mile count. | NA | NA | NA | NA | 1GBS | No variance to baseline | NA | NA | 100mg | No variance to baseline | NA | NA | Current bandwidth is 1.5 Mbps to 45.0 Mbps with most locations falling under 10 Mbps. These locations have a cost per meg of $106.67. New speeds will be 50 Mbps to 100 Mbps with all but 3 locations moving to 100 Mbps. New cost per meg will range from $4.75 per meg to $31.47 per meg and will represent a 70% - 90% cost reduction while providing in most cases an over 90% increase in speed. | NA | NA | NA | 5080 | 8 | 0 | 1282 | 300 | 0 | 3490 | NA | 0 | 0 | 0 | 0 | There are 4 peering points in our network. These were identified in our baseline and are shown on our network map that was presented during our site visit in October 2010. 1. Dell City/Pecos where Delcom and Hill Country Telephone connect. 2. Wes-Tex Midland where Wes-Tex Telephone Coop and Poka Lambro connect. 3. Big Bend Midland where Big Bend and Wes-Tex connect. 4. TLSN McCamey HUB where Big Bend and Hill Country Telephone meet. Contracts with each of these companies have been negotiated and signed. | NA | We have learned that working together with local companies that are experts in their field and also have a vested and long term investment in the community has helped the success of our project. | Region 18 Education Svc Ctr. | 19 | 4 | 0 | 0 | 2 | 12 |  | 20 | 1 | 5 | 63 | NA | There are 4 peering points in our network. These were identified in our baseline and are shown on our network map that was presented during our site visit in October 2010. 1. Dell City/Pecos where Delcom and Hill Country Telephone connect. 2. WesTex Midland where WesTex Telephone Coop and Poka Lambro connect. 3. Big Bend Midland where Big Bend and WesTex connect. 4. TLSN McCamey HUB where Big Bend and Hill Country Telephone meet. Contracts with each of these companies have been negotiated and signed. | TRUE
NT10BIX5570138 | 2012 | 57881 | This amount represents a 28% reduction in cost per mile. This is due to the inclusion of 48.05 air miles in the calculation. The air miles were not included in our original mile count. This is the same amount and information provided in the 2011 annual report. | NA | NA | NA | NA | 1GBS | No variance to baseline | NA | NA | 100 MG | No variance to baseline | NA | NA | Current bandwidth is 1.5 Mbps to 45.0 Mbps with most locations falling under 10 Mbps. These locations have a cost per Mbps of$106.67. New speeds will be 50 Mbps to 100 Mbps with all but 3 locations moving to 100 Mbps. New cost per Mbps from $4.75 per Mbps to $31.47 per Mbps and will represent a 70% - 90% cost reduction while providing in most cases an over 90% increase in speed. | NA | NA | NA | 5080 | 8 | 0 | 1282 | 300 | 0 | 3490 | NA | 0 | 0 | 0 | 0 | There are 4 peering points in our network. These were identified in our baseline and are shown on our network map that was presented during our site visit in October 2011. 1. Dell City/Pecos where Delcom and Hill Country Telephone connect. 2. WesTex Midland where WesTex Telephone Coopand Poka Lambro connect. 3. Big Bend Midland where Big Bend Telephone and WesTex Telephonecoop connect. 4. TLSN McCamey HUB where Big Bend Telephone and Hill Country Telephone meet. Contracts with each of these companies have been negotiated and signed. | NA | We have learned the benefits of working with local telephone companies on this project. Their industry knowledge and expertise in the area of fiber and wireless installation has contributed to our ability to stay on and ahead of our construction schedule. Also working with local companies helps the local communities and has helped in the community support of our project as we look to expand our reach beyond our ISD (Independent School Districts) to the surrounding community anchor institutions. By forming long term agreements with long standing local companies we can feel confident in the long term success of our project. | Region 18 Education Svc Ctr. | 19 | 4 | 0 | 0 | 2 | 12 |  | 20 | 1 | 5 | 63 | NA | There are 4 peering points in our network. These were identified in our baseline and are shown on our network map that was presented during our site visit in October 2011. 1. Dell City/Pecos, where Delcom and Hill Country Telephone connect. 2. WestTex Midland where WesTex Telephone Coop and Poka Lambro connect. 3. Big Bend Midland where Big Bend Telephone and WesTex Connect. 4. TLSN McCamey HUB where Big Bend Telephone and Hill Country Telephone meet. Contracts with each of these companies have been negotiated and signed. | TRUE
NT10BIX5570138 | 2013 | $54,560 | Final project miles are 244. Final construction and equipment cost for the project are$13,312,645. Equipment costs are favorable to baseline. Miles greater than baseline due to the inclusion of wireless miles as requested during site visit. | NA | NA | NA | NA | 1 GBS | No variance | NA | NA | 100 MG | No variance | NA | NA | Current bandwidth is 1.5 Mbps to 45.0 Mbps with most locations falling under 10 Mbps. These locations have an average cost per M.G. of $106.67. New speeds will be 50 Mbps to 100 Mbps with all but 3 locations moving to 100 Mbps. New cost per MG will range from $4.75 to $31.47 and will represent approximately 70% to 90% cost reduction while providing in most cases a 90% increase in speed. | NA | NA | NA | 5530 | 781 | 0 | 4749 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | There are 4 peering points in our network. They were identified in our baseline and are shown on our network map that was presented during our site visit in October 2011. Dell City/Pecos, where Delcom and Hill Country Telephone interconnect. 2. WesTex Midland where WesTex Telephone Co-op and Poka Lambro connect. 3. Big Bend Midland where Big Bend Telephone and WesTex connect. 4. TLSN McCamey HUB where Big Bend Telephone and Hill Country Telephone meet. Contracts with each of these companies have been negotiated and signed. | NA | We have learned the benefits of working with local telephone companies on this project. Their industry knowledge and expertise in the area of fiber and wireless installation has contributed to our ability to successfully complete all forecast project routes and to connect all primary CAI locations as well as many secondary locations. With fixed price contracts we were able to stay on track with our budget. Working with local companies has been beneficial to the local economies and has helped the community support of our project. By forming long term agreements with long standing local companies we can feel confident in the long term success of our project. | Region 18 Education Svc Ctr. | 19 | 4 | 0 | 0 | 2 | 12 |  | 20 | 1 | 5 | 63 | NA | There are 4 peering points in our network. They were identified in our baseline and are shown on our network map that was presented during our site visit in October 2011. Dell City/Pecos, where Delcom and Hill Country Telephone interconnect. 2. WesTex Midland where WesTex Telephone Co-op and Poka Lambro connect. 3. Big Bend Midland where Big Bend Telephone and WesTex connect. 4. TLSN McCamey HUB where Big Bend Telephone and Hill Country Telephone meet. Contracts with each of these companies have been negotiated and signed. | TRUE
NT10BIX5570139 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A (Dark fiber only) | 0 | N/A | 0 | N/A (Dark fiber only) | 0 | N/A | Dark fiber only, service providers do not disclose | None, dark fiber on a wholesale basis | Dark fiber only, open access/non-discrimination policy posted on MFC website | N/A | 159319 | 0 | 55 | 1728 | 0 | 0 | 157536 | 55 strand miles are currently in use, amongst the customers outlined earlier in this report. | 0 | 0 | 0 | 0 | Network providers may interconnect anywhere on the Three-Ring Binder that is technically feasible, and MFC is providing splice cases every 15,000 feet, and slack loops every 1,500 to 2,400 feet to facilitate interconnection wherever possible. | None at this time. | - Convene stakeholder advisory board to assist with CAI connection issues. - Meeting with pole owners biweekly to prioritize make-ready and resolve issues. - Post google route map publicly to encourage uptake. - Provide periodic construction schedule updates to interested service providers to assist them with broadband adoption efforts. | Maine Fiber Company, Inc. | 39 | 6 | 10 | 10 | 5 | 5 |  | 20 | 5 | 0 | 100 | None (Dark fiber only) | None (Dark fiber only) | TRUE
NT10BIX5570139 | 2011 | $18,893 | At the moment, this cost per new mile is less than the projected baseline cost. However, the current cost is based on make-ready and construction costs on segments with lower cost make-ready which allowed them to complete first. In addition, these segments also have lower-count fiber which is less expensive. We anticipate this cost per new mile to increase to the projected baseline number as we complete segments with heavier, more expensive make-ready and with higher-count, more expensive fiber. | N/A | N/A | N/A | N/A | 0 | N/A (Dark fiber only) | N/A | N/A | 0 | N/A (Dark fiber only) | N/A | N/A | Dark fiber only, service providers do not disclose | None, dark fiber on a wholesale basis | Dark fiber only, open access/non-discrimination policy posted on MFC website | N/A | 171028 | 0 | 353 | 83267 | 0 | 18000 | 69408 | We are leasing 353 miles to six customers with whom we have signed dark fiber leases. | 0 | 0 | 0 | 0 | Network providers may interconnect anywhere on the Three Ring Binder that is technically feasible. MFC is providing splice cases every 15, 000 feet and slack loops every 1, 500 to 2,500 feet to facilitate interconnection wherever possible. | None at this time. | - Meeting with pole owners biweekly to prioritize make-ready and resolve issues. Provided make-ready prioritization and requested completion dates to the pole owners to coordinate the make-ready process. - Post route map publicly to encourage service provider uptake. - Weekly meetings with contractors and vendors to review the project's status and coordinated items. - Worked closely with the fiber vendor to coordinate fiber production and delivery times with the project's schedule to limit the impact of fiber rationing imposed upon the project due to global fiber shortage. - Utilized Google Earth KMZ maps to coordinate fine engineering among the subcontractors. | Maine Fiber Company, Inc. | 39 | 6 | 10 | 10 | 5 | 5 |  | 20 | 5 | 0 | 100 | -We have six dark fiber lease agreements with various service providers to date. Each lease agreement varies in terms of overall mileage leased and number of interconnection points depending on service provider need. - We have not denied service to any provider. - We continue to negotiate additional dark fiber lease agreements. | - None (Dark fiber only) | TRUE
NT10BIX5570139 | 2012 | $23,414 | Ability to release major RFPs early in the project resulted in better than anticipated pricing for labor and materials. Tight management and good working relationships with pole owners helped to keep Make Ready costs in line. These along with other less material factors have resulted in better than projected cost per new mile, when compared to the baseline. | N/A | N/A | N/A | N/A | 0 | N/A (Dark fiber only) | N/A | N/A | 0 | N/A (Dark fiber only) | N/A | N/A | We only provide the dark fiber, service providers do not provide this information to us. | None, we offer dark fiber on a wholesale basis. | We do not offer any lit service so there are no restrictions on content, applications, etc. The dark fiber strands are offered on an open access/non-discriminatory basis, as advertised on the MFC website. | N/A | 187467 | 0 | 7026 | 180429 | 0 | 4 | 8 | Our 16 customers are currently utilizing 7,026 strand miles on our network. Our current customers are GWI, Axiom Technologies, Pioneer Broadband, University of Maine System, Cornerstone, Town of Scarborough, OTT, Oxford, segTEL, Southern Maine Community College, Town of Greenwood, BayRing, TDS Telecom, Unity Telephone and two unnamed parties (under NDA). | 240 | 0 | 40 | 200 | The primary way customers of MFC interconnect with the network is aerially along the route using splice cans at existing butt splice or ring cut locations, or by utilizing a slackloop by turning it into a ring cut. Slackloops and/or splice locations exist around the network about every 2,500' or less. This aerial model represents most of the 225 interconnection points being used on the network. | N/A | - We utilized Google Earth KMZ maps to coordinate fine engineering among the subcontractors. Limited the number of trips into the field and provided high level of detail. - Sales cycles for leasing dark fiber are long and often require educating potential customers on use and benefit. Plan on both of these to ensure sales/sustainability goals are reasonable and can be achieved within set time lines. - Have a plan to document and track 'asbuilt' network data. Ability to track each strand of fiber for each customer in addition to knowing what is available for lease where is a critical path item. - Meet with pole owners biweekly to prioritize make-ready and resolve issues. Provide make-ready prioritization and request completion dates to the pole owners to coordinate the make-ready process. - Hold weekly, in person, meetings with contractors and vendors to review the project's status and work through any 'problem' items. | Maine Fiber Company, Inc. | 39 | 6 | 10 | 10 | 5 | 5 |  | 20 | 5 | 0 | 100 | 1) We have executed 10 new dark fiber lease agreements in calendar year 2012, bringing our total to date to 16. All agreements are for the leasing of dark fiber, we do not offer any other service. Each lease agreement varies in terms of overall mileage leased and number of interconnection points being utilized depending on service provider need. 2) We are currently in various stages of negotiations with 8 additional entities. All agreements are for the leasing of dark fiber. 3) We have not denied service to any provider | None - we only offer dark fiber. | TRUE
NT10BIX5570139 | 2013 | $23,048 | MFC achieved favorable results in releasing major RFPs early in the project, which resulted in better than anticipated pricing for sub-contract labor and materials. Rigorous oversight and good working relationships with pole owners helped to keep Make Ready costs reasonable. These along with other less material factors have resulted in better than anticipated â€˜cost per new mileâ€™, when compared to the baseline. | N/A | N/A | N/A | N/A | 0 | N/A (Dark Fiber Only) | N/A | N/A | N/A | N/A (Dark Fiber Only) | N/A | N/A | We only provide the dark fiber, service providers do not provide this information to us. | None, we offer dark fiber on a wholesale basis. | We do not offer any lit service so there are no restrictions on content, applications, etc. The dark fiber strands are offered on an open access/non-discriminatory basis, as advertised on the MFC website. | N/A | 189910 | 0 | 8586 | 181324 | 0 | 0 | 0 | Our 19 customers are currently utilizing 8,586 strand miles on our network. Our current customers are GWI, Axiom Technologies, Pioneer Broadband, University of Maine System, Cornerstone, Town of Scarborough, OTT, Oxford, segTEL, Southern Maine Community College, Town of Greenwood, BayRing, TDS Telecom, Unity Telephone, Northeast Wireless, Bowdoin College and three unnamed parties (NAMES REDACTED DUE TO NDA). | 1610 | 0 | 268 | 1342 | Although MFC has collocation space available,the primary way customers of MFC interconnect with the network is aerially along the route using splice cans at existing butt splice or ring cut locations, or by utilizing a slack loop by turning it into a ring cut. Slack loops and/or splice locations exist around the network about every 2,500' or less. This aerial model represents most of the 225 interconnection points being used on the network. These points are made available on the MFC website in a Google Earth layer. | N/A | - Google Earth is a highly effective, free, software package that allows detailed information, such as KMZ maps to incorporating fine engineering, to be conveyed in an effective way to subcontractors, as well as to distribute 'as built' information to customers. - Plan to incorporate software to document and track 'asbuilt' network data. The ability to track each strand of fiber for each customer in addition to knowing what is available for lease where is a critical path item for operating success. - Meet with pole owners biweekly to prioritize make-ready and resolve issues. Provide make-ready prioritization lists and request completion dates to the pole owners to help coordinate the make-ready process. - Hold weekly, in person, meetings with contractors and vendors to review the project's status and work through any 'problem' items. - Be detail oriented and set realistic, tangible, goals and hold team members, suppliers and contracts accountable for meeting the goals. Review goals and expectations often during regular and established get-togethers. | Maine Fiber Company, Inc. | 39 | 6 | 10 | 10 | 5 | 5 |  | 20 | 5 | 0 | 100 | 1) We have executed 3 new dark fiber lease agreements in calendar year 2013 (YTD), bringing our total to date to 19. All agreements are for the leasing of dark fiber, we do not offer any other service. Each lease agreement varies in terms of overall mileage leased and number of interconnection points being utilized depending on service provider need. 2) We are currently in various stages of negotiations with 5 additional entities. All agreements are for the leasing of dark fiber. 3) We have not denied service to any provider. | None - we only offer dark fiber. | TRUE
NT10BIX5570140 | 2010 | 0 | Since this project started 9/1/10, our first annual report contains only 4 months and there have been no costs during this time. It is expected that the actual costs will match the Baseline after a full year has passed. | 0 | N/A | 0 | N/A | 0 | Baseline listed 10Gbps projected speed, based on Year 1 of 4 quarters. Since this project started 9/1/10, our first annual report contains only 4 months and there has been no actual construction yet. It is expected that the actual speed will match the Baseline after a full year has passed. | 0 | N/A | 0 | Baseline listed 1Gbps projected speed, based on Year 1 of 4 quarters. Since this project started 9/1/10, our first annual report contains only 4 months and there has been no actual construction yet. It is expected that the actual speed will match the Baseline after a full year has passed. | 0 | N/A | N/A | N/A | N/A | N/A | 3266 | 1540 | 0 | 0 | 1726 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | None at this time. | University of Hawaii Systems | 274 | 50 | 21 | 29 | 0 | 0 |  | 10 | 0 | 0 | 384 | N/A | N/A | TRUE
NT10BIX5570140 | 2011 | $40,000 | Some fiber was already installed as part of previous jobs and portions were used, thus lowering the cost/mile calculation. Original estimate of $/mile was $10/foot, or roughly $53,000 per mile. | 0 | n/a | 0 | n/a | 10Gbps | Maximum speed provided to Higher Education institutions is 10Gbps. | 0 | n/a | 2Gbps | Roughly 340 sites (K12, Libraries, some Higher Ed sites) receive 1Gbps, the remaining 40 receive 10Gbps. Weighted average is just under 2Gbps. | 0 | n/a | The average site had its bandwidth increased by over 75 times. Almost all community colleges and higher educational institutions went from 1 Gbps to 10Gbps. Almost all K-12 sites went for 6 Mbps to 1Gbps. The increase across all sites were summed and divided by the number of sites to reach the weighted average increase in bandwidth. | n/a | There are no bandwidth limitations or traffic prioritization on the network. Each network (K-12, Library, Community College/Higher Ed) is fully independent of each other and is solely managed by the respective entity. | n/a | 3266 | 1540 | 0 | 0 | 1726 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | University of Hawaii Systems | 274 | 50 | 21 | 29 | 0 | 0 |  | 10 | 0 | 0 | 384 | n/a | n/a | TRUE
NT10BIX5570140 | 2012 | $41,211 | Some fiber was already installed as part of previous jobs and portions were used, thus lowering the cost/mile calculation. Original estimate of $/mile was $10/foot, or roughly $53,000 per mile. | 0 | n/a | 0 | n/a | 10Gbps | Maximum speed provided to Higher Education institutions is 10Gbps. | 0 | n/a | 2Gbps | Roughly 340 sites (K12, Libraries, some Higher Ed sites) receive 1Gbps, the remaining 40 receive 10Gbps. Weighted average is just under 2Gbps. | 0 | n/a | The average site had its bandwidth increased by over 75 times. Almost all community colleges and higher educational institutions went from 1 Gbps to 10Gbps. Almost all K-12 sites went for 6 Mbps to 1Gbps. The increase across all sites were summed and divided by the number of sites to reach the weighted average increase in bandwidth. | n/a | There are no bandwidth limitations or traffic prioritization on the network. Each network (K-12, Library, Community College/Higher Ed) is fully independent of each other and is solely managed by the respective entity. | n/a | 3266 | 1540 | 0 | 0 | 1726 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | University of Hawaii Systems | 274 | 50 | 21 | 29 | 0 | 0 |  | 10 | 0 | 0 | 384 | n/a | n/a | TRUE
NT10BIX5570140 | 2013 | 48,046 | Some fiber was already installed as part of previous jobs and portions were used, thus lowering the cost/mile calculation. Original estimate of $/mile was $10/foot, or roughly $53,000 per mile. | 0 | n/a | 0 | n/a | 10Gbps | Maximum speed provided to Higher Education Institutions is 10Gbps | 0 | n/a | 2Gbps | Roughly 339 sites (K12, Libraries, some Higher Ed Sites) receive 1Gbps, the remaining 40 receive 10Gbps. Weighted average is just under 2Gbps | 0 | n/a | The average site had its bandwidth increased by over 75 times Almost all community colleges and higher educational institutions went from 1Gbps to 10Gbps. Almost all K-12 sites went from 6Mbps to 1Gbps. All Libraries went from 1Mbps to 1Gbps. The increase across all sites were summed and divided by the number of sites to obtain the weighted average increase in bandwidth. | n/a | There are no bandwidth limitations or traffic prioritization on the optical network. Each network (K-12, Library, Community College/Higher Education) is fully independent of each other and is solely managed by their respective entity. | n/a | 3186 | 3178 | 0 | 0 | 8 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | University of Hawaii Systems | 274 | 50 | 21 | 29 | 0 | 0 |  | 10 | 0 | 0 | 384 | n/a | n/a | TRUE
NT10BIX5570144 | 2010 | 0 | no variance | 0 | no variance | 0 | no variance | 0 | no variance | 0 | no variance | 0 | no variance | 0 | no variance | N/A | N/A | N/A | N/A | 100800 | 0 | 0 | 0 | 2800 | 13368 | 84632 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | Northern Illinois University (NIU) has been working collaboratively together with the DeKalb County BTOP finding project by collaborating weekly on strategic interconnections between the networks and their methodology. NIU has regular correspondence with the IBOP-EC project to assure that the Illinois Century Network interconnection points as successfully executed for delivery of content to ICN constituents. In addition, the IBOP-NW has needs for fiber routes that will be provided by NIU that avoids any overlay in the projects. The synergies between NIU and IBOP-EC are in process by regular e-mails, phone or in person meetings. NIU has been working with the Partnership for Connected Illinois (PCI) on developing the necessary information and processes to meet their goals. Currently NIU is working with PCI to assist in providing seminars for the State of Illinois BTOP projects to help PCI deliver their goals and requirements of Illinois BTOP projects. | Northern Illinois University, Inc. | 202 | 31 | 11 | 5 | 71 | 61 |  | 87 | 14 | 5 | 487 | N/A | N/A | TRUE
NT10BIX5570144 | 2011 | 68,682 | N/A | 0 | N/A | 0 | N/A | 10 gig | N/A | 0 | N/A | 100 mb | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 100800 | 0 | 0 | 4176 | 2800 | 13368 | 84632 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Northern Illinois University, Inc. | 202 | 31 | 11 | 5 | 71 | 61 |  | 87 | 14 | 5 | 487 | N/A | N/A | TRUE
NT10BIX5570144 | 2012 | 64,662 | This cost is lower than baseline primarily due to the fact that completed mileage to date is more heavily weighted toward plow miles. The remaining miles to be built are mainly bore which will shift the average up as we near completion. | 0 | n/a | 0 | n/a | 10 gig | n/a | 0 | n/a | 100 mb | n/a | 0 | n/a | In general, our CAIs will transition from around 1.54 to 4.5 mb on T-1 lines with a small percent on connections with speeds that can go up to 20 mb. The new installation for CAIs will be 1 gig increasing speeds on average of 995 mb. | N/A | Network policies based on port speed will use protocol PBB-TE and IEEE 802.1Q with IP prioritizing network traffic. | N/A | 89678 | 0 | 571 | 60084 | 16226 | 13368 | 60084 | N/A | 0 | 0 | 0 | 0 | The project has access to co-location rack space in 36 CAI locations where space was available. Some facilities are willing to lease space where available to other entities. For access to the iFiber equipment, interconnections also can be provided through hand hole locations that are within 1500' of any facilities along an intra-municipal route or 4000' along a rural route. | N/A | All duct in the project contains multiple sub-ducts that allow additional cable to be installed during the project and the future. This reduced the costs overall to the project in helping to centralize splice locations and reducing the overall splicing. The duct reserves future capabilities without ground disturbance when adding fiber to the system. This will reduce future costs to the project as we move past the grant period. | Northern Illinois University, Inc. | 202 | 31 | 11 | 5 | 71 | 61 |  | 87 | 14 | 5 | 487 | N/A | N/A | TRUE
NT10BIX5570145 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 100 Mbs | 100 MB Fiber connection | 10Mbs | 802.11 Wireless. | N/A | At this time not connections are active so we can not get an average reading. | N/A | At this time not connections are active so we can not get an average reading. | N/A - Averages are not available for this project at this time. | 100 MB Fiber data/Voice over IP connection per anchor institution, charge of $400 per month per connection. | Middle mile fiber connections will be provided to 42 CAI and 10 Businesses, most of which are Ute Tribe Government offices. Fiber connections will be limited by network hardware to 100Mbs. Content may be filtered (depending on department policies) for reasonable use. This filtering will not violate the FCC's Internet Policy Statement (FCC 05-151) or any other subsequent ruling or statement, as we understand them. This project will not favor any lawful internet application, or any particular content over another. Network management policies will be openly displayed. The middle mile fiber will have the capacity and be technically capable of offering interconnection points to other providers, however, at this time, no third party providers have currently expressed interest. If this should change, we would welcome any opportunity to enhance this project and look forward to the possibility to any future opportunities this project may bring. Last mile open Wireless access will be provided to households in around the Fort Duchesne area. This access will be 10MBs per connection and only best effort Inherent delivery limitations (network management) will be used to allocate capacity, and only to reasonably insure oversubscribing or bottlenecks are kept to a minimum. Content will not be blocked or monitored, and not content will be favored. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Currently the project does not have collocation facilities in place, however, the Tribe as a contingency plan in place should opportunity present it self. | N/A | The amount of time required for reporting on this project was under estimated. | Ute Indian Tribe | 1 | 1 | 1 | 1 | 1 | 5 |  | 27 | 5 | 0 | 42 | Total number of interconnection points will be 1, thus 0 other negotiations are currently ongoing. The Ute Tribe has engaged Strata Networks and has an ongoing relationship with them. We plan to use them in this project to provide Internet connectivity to our middle mile as well as to the end mile portion of this project. Currently this is our only agreement and interconnect point. However, the Uintah and Ouray Reservation finds themselves technologically inadequate to support sustainable economic growth, especially in areas of technology. In large part, as with most other reservations, of a unique set of difficulties as it pertains to technology-based economic development. These areas or target markets are extremely depressed, low-income, and are geographically isolated; providing little or no upside for potential investors. Furthermore, investors often do not have the confidence in the sovereign government to protect the investment of a project of significant scope. The Uintah and Ouray reservation finds itself in just this situation; however, the hope is that this project will provide adequate and affordable Internet connectivity to future opportunities. This project has not currently denied any request for interconnection. | N/A | TRUE
NT10BIX5570145 | 2011 | $433,261 | This number does not reflect a true average. We have purchased much of the equipment and supplies, but have just started to lay the fiber. Thus the numbers show the expenses, roughly 44 % of money spent (outside plant), but only represents 1 mile of new middle mile fiber. This will come back into line as more middle mile fiber is installed. | N/A | We have most of the network installed and are in the testing phase, but have not yet connected any last mile subscribers. | N/A | We have not currently connected any LM Subscribers. | 100 Mbs | 100 Mbs Fiber Connection | 10Mbs | 802.11 Wireless Connection | 100 Mbs | 100 Mbs Fiber Connection | 10 Mbs | 802.11 Wireless Connection, With 10 Mbs feed | Some of the locations that we have connected had no previous connectivity, others had connections via dedicated lattice circuits with an aggregate speed of 1028K, all new connections are 100MB Fiber. | 100 MB Fiber data/Voice over IP connection per anchor institution, charge of $400 per month per connection. | Middle mile fiber connections will be provided to 42 CAI and 10 Businesses, most of which are Ute Tribe Government offices. Fiber connections will be limited by network hardware to 100Mbs. Content may be filtered (depending on department policies) for reasonable use. This filtering will not violate the FCC's Internet Policy Statement (FCC 05-151) or any other subsequent rulings or statements, as we understand them. This project will not favor any lawful internet application, or any particular content over another. Network management policies will be openly displayed. The middle mile fiber will have the capacity and be technically capable of offering interconnection points to other providers, however, at this time, no third party providers have currently expressed interest. If this should change, we would welcome any opportunity to enhance this project and look forward to the possibility to any future opportunities this project may bring. Last mile open Wireless access will be provided to households in around the Fort Duchesne area. This access will be 10MBs per connection and only best effort Inherent delivery limitations (network management) will be used to allocate capacity, and only to reasonably insure oversubscribing or bottlenecks are kept to a minimum. Content will not be blocked or monitored, and no content will be favored. | N/A | 912 | 18 | 0 | 6 | 780 | 0 | 108 | N/A | 0 | 0 | 0 | 0 | Currently the project does not have collocation facilities in place and there has been now demand for such. However the Tribe does have a contingency plan in place if such a demand should present itself. | N/A | The amount of time required for reporting on this project was under estimated. | Ute Indian Tribe | 1 | 1 | 1 | 1 | 1 | 5 |  | 27 | 5 | 0 | 42 | Total number of interconnection points will be 1, thus 0 other negotiations are currently ongoing. The Ute Tribe has engaged Strata Networks and has an ongoing relationship with them. We plan to use them in this project to provide Internet connectivity to our middle mile as well as to the end mile portion of this project. Currently this is our only agreement and interconnect point. However, the Uintah and Ouray Reservation finds themselves technologically inadequate to support sustainable economic growth, especially in areas of technology. In large part, as with most other reservations, of a unique set of difficulties as it pertains to technology-based economic development. These areas or target markets are extremely depressed, low-income, and are geographically isolated; providing little or no upside for potential investors. Furthermore, investors often do not have the confidence in the sovereign government to protect the investment of a project of significant scope. The Uintah and Ouray reservation finds itself in just this situation; however, the hope is that this project will provide adequate and affordable Internet connectivity to future opportunities. This project has not currently denied any request for interconnection. | N/A | TRUE
NT10BIX5570145 | 2012 | $197,274.13 | We currently have 9 miles of fiber completed and have spent 2,019,871.66 87.90% of which is costed to MM which gives us a total spent for middle mile of 1,775.467.19. Divide this by miles completed 9 to get 197,274.13 | $1358 | We have currently spent 2,019,871.66 dollars of which 12.10 % or $244,404.47 is allocated to the Last Mile portion of this project. We have passed180 total households leaving us with a current cost per household passed of $1,358.00 | $1629 | We have currently spent 2,019,871.66 dollars of which 12.10 % or 244,404.47 of is allocated to Last Mile portion of this project. We have connected a total of 150 households, which leaves us with a current cost per household connected at roughly $1,629.00 | 100 Mbs | 100 Mbs Fiber Connection | 10 Mbs | 802.11 Wireless Connection | 100 Mbs | 100 Mbs Fiber Connection | 10 Mbs | 802.11 Wireless connection, with 10 Mbs feed | Some of the locations that we have connected had no previous connectivity, others had connections via dedicated lattice circuits with an aggregate speed of 1028K, all new connections are 100MB Fiber. | 100 MB Fiber data/Voice over IP connection per anchor institution, we plan to charge $400 per month per connection. | Middle mile fiber connections will be provided to 42 CAI and 10 Businesses, most of which are Ute Tribe Government offices. Fiber connections will be limited by network hardware to 100Mbs. Content may be filtered (depending on department policies) for reasonable use. This filtering will not violate the FCC's Internet Policy Statement (FCC 05-151) or any other subsequent rulings or statements, as we understand them. This project will not favor any lawful internet application, or any particular content over another. Network management policies will be openly displayed. The middle mile fiber will have the capacity and be technically capable of offering interconnection points to other providers, however, at this time, no third party providers have currently expressed interest. If this should change, we would welcome any opportunity to enhance this project and look forward to the possibility to any future opportunities this project may bring. Last mile open Wireless access will be provided to households in around the Fort Duchesne area. This access will be 10MBs per connection and only best effort Inherent delivery limitations (network management) will be used to allocate capacity, and only to reasonably insure oversubscribing or bottlenecks are kept to a minimum. Content will not be blocked or monitored, and no content will be favored. | N/A | 912 | 798 | 0 | 114 | 0 | 0 | 0 | We currently do not have any wholesale customers, but we have set aside 12 strands of fiber for future the possibility of leasing fiber to a third-party. | 0 | 0 | 0 | 0 | Currently the project does not have collocation facilities in place and there has been now demand for such. However the Tribe does have a contingency plan in place if such a demand should present itself. | N/A | The amount of time required for reporting on this project was under estimated. | Ute Indian Tribe | 1 | 1 | 1 | 1 | 1 | 5 |  | 27 | 5 | 0 | 42 | Total number of interconnection points will be 1, thus 0 other negotiations are currently ongoing. The Ute Tribe has engaged Strata Networks and has an ongoing relationship with them. We plan to use them in this project to provide Internet connectivity to our middle mile as well as to the end mile portion of this project. Currently this is our only agreement and interconnect point. However, the Uintah and Ouray Reservation finds themselves technologically inadequate to support sustainable economic growth, especially in areas of technology. In large part, as with most other reservations, of a unique set of difficulties as it pertains to technology-based economic development. These areas or target markets are extremely depressed, low-income, and are geographically isolated; providing little or no upside for potential investors. Furthermore, investors often do not have the confidence in the sovereign government to protect the investment of a project of significant scope. The Uintah and Ouray reservation finds itself in just this situation; however, the hope is that this project will provide adequate and affordable Internet connectivity to future opportunities. This project has not currently denied any request for interconnection. | N/A | TRUE
NT10BIX5570146 | 2010 | 0 | Construction has not yet begun. | N/A | N/A | N/A | N/A | 0 | Construction has not yet begun. | N/A | N/A | 0 | Construction has not yet begun. | N/A | N/A | We have not yet begun connecting community anchor institutions since construction has not yet begun. We anticipate several CAIs will be upgrading from copper based T1 services to fiber speeds ranging from 10Mb/s up to GigE service. | Pricing has not yet been finalized for this project. DS-1, DS-3, OC-3, OC-12, OC-48, 2.5G Lambda, 10G Lambda, 10Mb/s, 20Mb/s, 50Mb/s, 100Mb/s, 200Mb/s, 500Mb/s and GigE. | Have not yet completed our network management policies for the stimulus funded network. We will abide by all interconnection and open access requirements of the program. | Have not yet begun construction. | 36520 | 0 | 0 | 3520 | 16500 | 8250 | 8250 | N/A | 0 | 0 | 0 | 0 | We will own collocation space but construction has not yet begun therefore no facility collocation capacity to report at this time. | N/A | Attending the BTOP Recipient Workshop was very helpful. We took away a lot of good information that has allowed us to stay on top of reporting requirements as well as overall project requirements. Meeting the grant officers and other Federal project staff provided useful tips for managing the project. We also believe that weekly update meetings with engineering, finance, purchasing, environmental and right of way staff help to minimize any project surprises. These weekly meetings coincide nicely with our weekly Federal Project Officer meetings allowing us to seek answers to questions quickly and share that information with the entire project staff. | SHO-ME Technologies, L.L.C. | 30 | 13 | 3 | 3 | 11 | 13 |  | 28 | 0 | 0 | 101 | Interconnection agreements are currently in progress. | Peering and Transit Agreements are currently in progress. | TRUE
NT10BIX5570146 | 2011 | $40,520 | Sho-Me Technologies' baseline estimated $9,332.74 per mile for new build. However, this calculation was flawed and was based on overall costs rather than simply capital costs. The first segments built were comprised primarily of underground fiber and were the most expensive routes. The cost per mile, $40,520, falls within Sho-Me's overall estimates for per mile costs for underground fiber. At the end of 2011, Sho-Me calculates overall per mile costs for the entire project to be $30,677 which includes approximately $42,000 per mile for underground builds and approximately $18,000 per mile for aerial builds. | N/A | N/A | N/A | N/A | 10G | No variance. | N/A | N/A | 100Mps | No variance. | N/A | N/A | Average broadband speeds increase two-fold from a non-symmetrical T1 via copper pairs at 1.5Mb/s to a 3Mb/s via fiber on protected GigE rings. | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence. | 7a. The Sho-Me MO fiber project will comply with the non-discrimination and network interconnection obligations set forth in section V.D.3.b of the NOFA and in Section 6001(j) of the Recovery Act. The project will meet or exceed the requirements set forth by the FCCâ€™s Internet Policy Statement (FCC 05-151) which can be found online at http://fjallfoss.fcc.gov/edocs_public/attachmatch/FCC-05-151A1.pdf, or any subsequent ruling or statement regarding non-discrimination and actively encourages broadband deployment and the preservation and promotion of the open and interconnected nature of the public Internet. Sho-Me MOâ€™s predominantly middle mile service offering will be high-capacity, point-to-point private line transport services. Sho-Me Technologies, LLC will not manage or limit the content of communications traffic transiting the projectâ€™s network, except to the extent necessary to maintain reliable service. The project will utilize neutral traffic routing, and will enable connections to other carriers and to the public Internet; not favor any lawful Internet applications and content over others; display any network management policies in a prominent location on its web page and provide notice to customer of changes to these policies; connect to the public Internet directly or indirectly, such that the project is not an entirely private closed network; offer interconnection, where technically feasible without exceeding current or reasonably anticipated capacity limitat | None. 0% | 32488 | 1840 | 0 | 5184 | 3552 | 0 | 21912 | N/A | 3246 | 1388 | 0 | 1858 | N/A | N/A | Sho-Me Technologies, LLC often uses checklists as a way to ensure procedures are followed when various types of transactions are completed. For example, before a contractor is awarded a job, a checklist is completed to make sure that Sho-Me has all required documents on file from the contractor, a cost/price analysis is performed, and that the contractor is suitable for the job. Pre-Construction meetings are held with each contractor prior to construction beginning. This has helped to ensure contractors know what is expected of them regarding prevailing wages, daily reports, signage, etc. Internal communication has also been a vital part of Sho-Me's project. Biweekly meetings are held between the project's key personnel where issues and concerns are raised, progress is acknowledged, and upcoming events are discussed. | SHO-ME Technologies, L.L.C. | 30 | 13 | 3 | 3 | 11 | 13 |  | 28 | 0 | 0 | 101 | 1) Total number of interconnection agreements entered into during this annual reporting period = 4 2) Total number of interconnection agreements currently negotiating = 8 3) No requests for interconnection have been denied. | N/A | TRUE
NT10BIX5570146 | 2012 | $31,340 | Sho-Me Technologies' baseline estimated $9,332.74 per mile for new build. However, this calculation was flawed. The first segments built were comprised primarily of underground fiber and were the most expensive routes. The cost per mile, $31,340, falls within Sho-Me's overall estimates for per mile costs for underground fiber. At the end of 2012, Sho-Me calculates overall per mile costs for the entire project to be $32,045 which includes approximately $42,000 per mile for underground builds and approximately $18,000 per mile for aerial builds. | N/A | N/A | N/A | N/A | 10G | No variance. | N/A | N/A | 100Mps | No variance. | N/A | N/A | Average broadband speeds increase two-fold from a non-symmetrical T1 via copper pairs at 1.5Mb/s to a 3Mb/s via fiber on protected GigE rings. | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence. | 7a. The Sho-Me MO fiber project will comply with the non-discrimination and network interconnection obligations set forth in section V.D.3.b of the NOFA and in Section 6001(j) of the Recovery Act. The project will meet or exceed the requirements set forth by the FCCâ€™s Internet Policy Statement (FCC 05-151) which can be found online at http://fjallfoss.fcc.gov/edocs_public/attachmatch/FCC-05-151A1.pdf, or any subsequent ruling or statement regarding non-discrimination and actively encourages broadband deployment and the preservation and promotion of the open and interconnected nature of the public Internet. Sho-Me MOâ€™s predominantly middle mile service offering will be high-capacity, point-to-point private line transport services. Sho-Me Technologies, LLC will not manage or limit the content of communications traffic transiting the projectâ€™s network, except to the extent necessary to maintain reliable service. The project will utilize neutral traffic routing, and will enable connections to other carriers and to the public Internet; not favor any lawful Internet applications and content over others; display any network management policies in a prominent location on its web page and provide notice to customer of changes to these policies; connect to the public Internet directly or indirectly, such that the project is not an entirely private closed network; offer interconnection, where technically feasible without exceeding current or reasonably anticipated capacity limitat | None. 0% | 35961 | 1612 | 0 | 25346 | 4021 | 0 | 4982 | N/A | 3104 | 1334 | 0 | 1770 | N/A | N/A | Sho-Me Technologies, LLC often uses checklists as a way to ensure procedures are followed when various types of transactions are completed. For example, before a contractor is awarded a job, a checklist is completed to make sure that Sho-Me has all required documents on file from the contractor, a cost/price analysis is performed, and that the contractor is suitable for the job. Pre-Construction meetings are held with each contractor prior to construction beginning. This has helped to ensure contractors know what is expected of them regarding prevailing wages, daily reports, signage, etc. Internal communication has also been a vital part of Sho-Me's project. Biweekly meetings are held between the project's key personnel where issues and concerns are raised, progress is acknowledged, and upcoming events are discussed. | SHO-ME Technologies, L.L.C. | 30 | 13 | 3 | 3 | 11 | 13 |  | 28 | 0 | 0 | 101 | 1) Total number of interconnection agreements entered into during this annual reporting period = 22 2) Total number of interconnection agreements currently negotiating = 3 3) No requests for interconnection have been denied. | N/A | TRUE
NT10BIX5570146 | 2013 | $31,026.23 | Sho-Me Technologies' baseline estimated $9,332.74 per mile for new build. However, this calculation was flawed. The first segments built were comprised primarily of underground fiber and were the most expensive routes. Sho-Me calculates average cost per mile to be $31,026.23 for the entire middle-mile project which estimated approximately $42,000 per mile for underground builds and approximately $18,000 per mile for aerial builds. | N/A | N/A | N/A | N/A | 10G | No variance. | N/A | N/A | 100Mps | No variance. | N/A | N/A | Average broadband speeds increase two-fold from a non-symmetrical T1 via copper pairs at 1.5Mb/s to a 3Mb/s via fiber on protected GigE rings. | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence. | 7a. The Sho-Me MO fiber project will comply with the non-discrimination and network interconnection obligations set forth in section V. D.3.b of the NOFA and in Section 6001(j) of the Recovery Act. The project will meet or exceed the requirements set forth by the FCCâ€™s Internet Policy Statement (FCC 05-151) which can be found online at http://fjallfoss.fcc.gov/edocs_public/attachmatch/FCC-05-151A1. pdf, or any subsequent ruling or statement regarding non-discrimination and actively encourages broadband deployment and the preservation and promotion of the open and interconnected nature of the public Internet. Sho-Me MOâ€™s predominantly middle mile service offering will be high-capacity, point-to-point private line transport services. Sho-Me Technologies, LLC will not manage or limit the content of communications traffic transiting the projectâ€™s network, except to the extent necessary to maintain reliable service. The project will utilize neutral traffic routing, and will enable connections to other carriers and to the public Internet; not favor any lawful Internet applications and content over others; display any network management policies in a prominent location on its web page and provide notice to customer of changes to these policies; connect to the public Internet directly or indirectly, such that the project is not an entirely private closed network; offer interconnection, where technically feasible without exceeding current or reasonably anticipated capacity limi | None. 0% | 36442 | 5959 | 0 | 30483 | 0 | 0 | 0 | N/A | 3104 | 1334 | 0 | 1770 | N/A | N/A | Sho-Me Technologies, LLC implemented use of checklists as a way to ensure procedures are followed when various types of transactions are completed. For example, before a contractor is awarded a job, a checklist is completed to make sure that Sho-Me has all required documents on file from the contractor, a cost/price analysis is performed, and that the contractor is suitable for the job. Also, pre-construction meetings are necessary with each contractor prior to construction start to reinforce what is expected of them regarding time lines, safety, prevailing wages, daily reports, signage, etc. Internal communication has also been a vital part of the "Sho-Me MO" middle mile project. Biweekly update meetings are held with the project's key personnel from engineering, accounting, purchasing, human resources, IT, environmental and right of way staff. Project milestones are reviewed, construction progress is acknowledged, budget issues and concerns are discussed, and upcoming community outreach events are announced. These meetings coincide with our biweekly status calls with our Federal Project Officer allowing us to seek answers to questions quickly and share that information with the BTOP team. | SHO-ME Technologies, L.L.C. | 30 | 13 | 3 | 3 | 11 | 13 |  | 28 | 0 | 0 | 101 | 1) Total number of interconnection agreements entered into during this annual reporting period = 13 2) Total number of interconnection agreements currently negotiating = 6 3) No requests for interconnection have been denied. | N/A | TRUE
NT10BIX5570148 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | Construction has not started yet. | Construction has not started yet. | Construction has not started yet. | Construction has not started yet. | 29760 | 0 | 0 | 0 | 17856 | 5952 | 5952 | We are negotiating with another provider for their lease of dark fiber along part of the planned route once completed. Construction has not started yet. | 400 | 50 | 50 | 350 | We will connect with other network providers at the Fiber Hotel in Missoula, the Flathead Electric Coop in Kalispell, the Northern Telephone Exchange to 360networks in Santa Rita, and at the Westin Fiber Hotel in Seattle. | No subcontracts or sub grants have been made. | Most important....get started on the EA early, and stay tuned in to what your consultant is doing. Finding a good EA consultant is extremely important. If dealing with Tribes, determine early on what the Tribal Employment Rights Ordinance says and what it means to your budget. It may be possible to negotiate the TERO fees and maybe these fees and right of way fees can be paid for with some form of partial ownership of infrastructure across Tribal lands. | Ronan Telephone Co. | 4 | 3 | 3 | 1 | 8 | 6 |  | 4 | 1 | 3 | 33 | N/A | N/A | TRUE
NT10BIX5570148 | 2011 | $0 | 55.7 miles of fiber/conduit installed at a cost of $1,795,661 for labor and materials, however not ready for deployment as these segments are only those that permits were available for. Deployment is dependent on splicing, fiber availablity, additional segment build, and interconnection to the Internet in Missoula and Seattle. | 0 | N/A Construction is not completed yet. | 0 | N/A Construction is not completed yet. | 0 | N/A Construction is not completed yet. | 0 | N/A Construction is not completed yet. | 0 | N/A Construction is not completed yet. | 0 | N/A Construction is not completed yet. | No CAI's yet, still under construction. | No CAI's yet, passed some but still under construction. See attached CAI projections spreadsheet. | Ronan Telephone Company already has non-descrimination and network managment policies in place and Montana West will be modifying these policies to accommodate the additional requirements necessary for the provision of service to other providers. These policies will be in place before the network is finished and service is offered. We anticipate standard traffic prioritization allowing for virtual private networking, some dark fiber sales, and priority given to voice service when it becomes available. We have not blocked consumers from any lawful content or prevented any consumers from attaching any legal device to the network and do not intend to do so when the network is turned up. | N/A We have not lost any subscribers yet as we are still under construction. | 29760 | 0 | 0 | 0 | 27648 | 1780 | 332 | We have a contract to provide 165.9 miles of 2 dark fibers to another provider on a 20 year IRU, between Kalispell and Missoula, with a delivery date of August 1, 2012, at a rate of $1750 per fiber mile, prepaid upon delivery. | 544 | 50 | 50 | 444 | We will connect with other network providers at the Fiber Hotel in Missoula, the Flathead Electric Coop in Kalispell, the Northern Telephone Exchange in Santa Rita, and the Westin Fiber Hotel in Seattle. | No subcontracts of sub grants have been made to socially and economically disadvantaged small business concerns. | In the event of fiber shortage, and the resulting increase in fiber pricing, it may be advantageous to place conduit and pull in fiber when it becomes available. | Ronan Telephone Co. | 4 | 3 | 3 | 1 | 8 | 6 |  | 4 | 1 | 3 | 33 | 1. (0) We have not entered into any interconnection, peering, and/or transit agreements during this annual reporting period. 2. Currently negotiating (0) interconnection agreements. 3. We have not denied any requests for interconnection. | A. Currently negotiating (0) peering agreements B. Currently negotiating (2) transit agreements for upstream transport | TRUE
NT10BIX5570148 | 2012 | $48,901 | $8.9Million to date, divided by 182 miles completed (includes conduit ready for fiber) | $14,590 | $8.9 Million, divided by 610 households passed. Evaro 70, Arlee 105, St., Ravalli 35, Ignatius 140, Ronan 170, Pablo 90 | $787/3Mb | 70 last mile wireless subscribers in Arlee..base station $36,173 plus 70 CPE's at $270, total $55,073 for 70 subscribers...average cost per sub $787.00 | 1Gb | No variance | 4Mb | No Variance | 1.1Gb | (1) customer at 200Mb, (1) customer at 2Gb...average broadband speed provided is 2.2Gb divided by 2. | 2.0Mb | 55 customers at 1.5Mb and 15 at 4.0Mb | No CAI's yet, still under construction. | No CAI's yet, construction to CAI's is scheduled for Q2 and Q3 2013. See attached CAI projections spreadsheet. We are providing retail wireless services to the community of Arlee...upgraded 60 customers and added 10 new ones. Retail charges are $29.95 for 1.5mb, and $49.95 for 4.0Mb | Ronan Telephone Company already has non-discrimination and network management policies in place and Montana West has modified these policies to accommodate the additional requirements necessary for the provision of service to other providers. These policies are in place and are stated in the Montana West Master Services Agreement. We anticipate standard traffic prioritization allowing for virtual private networking, some dark fiber sales, and priority given to voice service when it becomes available. We have not blocked consumers from any lawful content or prevented any consumers from attaching any legal device to the network. | N/A..we have not lost any subscribers to the network. | 29760 | 11616 | 0 | 0 | 17812 | 0 | 332 | We have a contract to provide 166 miles of 2 dark fibers to Bresnan on a 20 year IRU, between Kalispell and Missoula, with a delivery date of August 1, 2012, at a rate of $1750 per fiber mile, prepaid upon delivery. Presently this is re-scheduled for delivery April 15, 2013. | 544 | 50 | 50 | 444 | We connect with other network providers at the fiber hotel in Missoula, the Kalispell Regional Medical Center in Kalispell, the Northern Telephone Exchange in Santa Rita, and the Westin Fiber Hotel in Seattle. | No subcontracts or sub grants have been made to socially and economically disadvantaged small business concerns. | When depending on work from a contractor for a significant part of your build, be sure to put in enough late delivery penalty to motivate the contractor to finish on time, no matter how large the company is. You can't start early enough on the permitting part of the project. Have a backup plan or a "plan B" for everything that you intend to do. | Ronan Telephone Co. | 4 | 3 | 3 | 1 | 8 | 6 |  | 4 | 1 | 3 | 33 | 1. (0) We have not entered into any interconnection, peering, during this annual reporting period. We have entered into one transit agreement, with Cutthroat Communications. (CCI) Montana West is providing 2Gb transport to CCI between Missoula and Seattle. 2. Currently negotiating (0) interconnection, peering and/or transit agreements 3. We have not denied any requests for interconnection. | Two transit agreements with Cutthroat Communications (CCI). CCI is providing 1Gb transport to Montana West between Missoula and Santa Rita, and Montana West is providing 2Gb transport to CCI between Missoula and Seattle. | TRUE
NT10BIX5570148 | 2013 | $51,574 | $13.1M to date, divided by 254 miles completed. | $30.16 | Households in Arlee 235 Households in Elmo/Big Arm 124 Wireless costs $102,586 divided by 359 = $30.16 | $915.95 | 107 last mile subscribers in Arlee, 5 last mile subscribers in Elmo/Big Arm, (2) base stations at $36,173 plus 112 CPE's at $270, total $102,586 for 112 subscribers...average cost per sub $915.95 | 1Gb | No Variance | 4Mb | No Variance | 233Mb | 100Mb (13), 200Mb (1), 2Gb (1) 3500Mb/15=233.33Mb | 10.68Mb | Residences: 1.5Mb* (28)=42, 2.5Mb* (5)=12.5, 4Mb* (74)=296, 100Mb* (5)=500 Businesses: 100Mb*(3)=300 50Mb*(2)=100 100+300+500+296+12.5+42=1250.5/117=10.68Mb | Broadband speed has been increased to 100Mb as this is the lowest offering we have for CAI's Original New % CAI Bandwidth (Mb) Bandwidth (Mb) Increase (Mb) Increase Salish Kootenai College 10 100 90 900 St. Luke Medical Center 10 100 90 900 Ronan City Library 4 100 96 2400 Polson School District 10 100 90 900 Ronan School District 10 100 90 900 Ronan Fire Department 4 100 96 2400 Lake County Housing 4 100 96 2400 Kalispell Regional Med Ctr. 10 100 90 900 Flathead Comm. College 10 100 90 900 Salish Kootenai Headquarters 10 100 90 900 Ronan City Hall 4 100 96 2400 Mission Valley Power 10 100 90 900 Valley View School 4 100 96 2400 | Retail services are being offered in both wireless and fiber broadband from 1.0Mb to 100Mb Wireless Internet 1Mb...$24.95 2Mb...$34.95 4Mb...$44.95 Residential Internet via fiber 100Mb...$100 Business Internet via fiber ranging from $11 to $18 per Mb Port connections for WAN 1Gb Dedicated...$1400 1Gb Best Effort...$750 100Mb Dedicated...$750 100Mb Best Effort...$250 | Ronan Telephone Company already has a non-descrimination and network management policies in place and Montana West has modified these policies to accommodate the additional requirements necessary for the provision of service to other providers. These policies are in place and are stated in the Montana West Master Services Agreement. We anticipate standard traffic prioritization allowing for virtual private networking, some dark fiber sales, and priority given to voice service when it becomes available. We have not blocked consumers from any lawful content or prevented any consumers from attaching any legal device to our network. | N/A..we have not lost any subscirbers to the network. | 26784 | 22944 | 332 | 0 | 3508 | 0 | 0 | We have provided 166 miles of 2 dark fibers to Bresnan on a 20 year IRU. | 544 | 50 | 50 | 444 | We connect with other network providers at the fiber hotel in Missoula, the Kalispell Regional Medical Center in Kalispell, the Northern Telephone Exchange in Santa Rita, and the Westin Fiber Hotel in Seattle. | No subcontracts or sub grants have been made to socially and economically disadvantaged small business concerns. | Even though you have a grant, never take anything for granted. Always have a backup plan. | Ronan Telephone Co. | 4 | 3 | 3 | 1 | 8 | 6 |  | 4 | 1 | 3 | 33 | Interconnection agreement with Cogent Communications at the Westin Fiber Hotel in Seattle | 1. (0) We have not entered into any interconnection, transit or peering agreements during this annual reporting period. 2. Currently negotiating (1) Interconnection agreement, (0) peering and (0) transit agreements. (Qwest) 3. We have not denied any requests for interconnection | TRUE
NT10BIX5570150 | 2010 | 0 | Deployment not yet started | 0 | N/A | 0 | N/A | 0 | Deployment not yet started | 0 | N/A | 0 | Deployment not yet started | 0 | N/A | Deployment not yet started, not applicable for this reporting period | N/A | Deployment not yet started, not applicable for this reporting period | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 5336 | 2668 | 0 | 2668 | N/A | None at this time | Start discussions early with any Environmental Assessment related entities/agencies. This often takes longer than anticipated and seems to involve additional entities/agencies that were previously unknown. | Department of Administration Services Bureau of Enterprise Systems & Technology | 1049 | 192 | 14 | 31 | 0 | 875 |  | 6 | 5 | 0 | 2172 | N/A | N/A | TRUE
NT10BIX5570150 | 2011 | 50,000 | Original baseline utilized total project miles for this calculation because all miles were considered to be new (as they have never been in service or utilized by the State). Because of the projects use of fiber IRU, later guidance has directed that miles are now classified as either new miles or upgraded miles. Total new miles under this formulation are 880 new miles and 4664 miles are upgraded. | 0 | N/A | 0 | N/A | 1000 Mbps | No Variance | 0 | N/A | 1000Mbps | No Variance | 0 | N/A | Average speed at the connected entities has gone from no connectivity in most CAI to 1000Mbps availability. For CAI that had prior service, it has increased from 8 Mbps to 1000 Mbps. | None at this time. | The network has the capacity to perform traffic prioritization and bandwidth shaping policies. However, these polices have not been implemented or required because most CPE devices are interfacing into the network at 10 or 100 Mbps. Additionally, we have not limited or blocked any subscribers access. | N/A | 15224 | 4164 | 0 | 2870 | 2260 | 0 | 5930 | N/A | 5336 | 2668 | 0 | 2668 | N/A | None at this time | Continual contact with FPO is extremely beneficial. Many guidance changes have been implemented during the program period. Be meticulous in the record keeping, showing all notes and explanations pertaining to a particular item. | Department of Administration Services Bureau of Enterprise Systems & Technology | 1049 | 192 | 14 | 31 | 0 | 875 |  | 6 | 5 | 0 | 2172 | None at this time. | None at this time. | TRUE
NT10BIX5570150 | 2012 | 50,000 | As this project utilizes 100% IRU facilities, all new mile costs are fixed at $50,000 per new mile. Original baseline utilized total project miles for this calculation because all miles were considered new (as they have never been in service or utilized by the State). Because of the projects use of Fiber IRU, later guidance had directed that miles are now classified as either new miles or upgraded miles. Total new miles under this formulation are 1053 new miles and 7827 miles are upgraded. Additionally, PPR reporting guidance was changed to now reflect route miles. Under this new guidance, there are 1053 route miles of new fiber and 2293 route miles are upgraded. If all route miles are taken into consideration for this calculation, the current cost per route mile would be $21,035. | 0 | N/A | 0 | N/A | 1000 Mbps | No Variance | 0 | N/A | 533 Mbps | The network offers 3 speed tiers - 10 Mbps - 306 subscribers currently connected 100 Mbps - 111 subscribers currently connected 1000 Mbps - 425 subscribers currently connected | 0 | N/A | Average speed at the connected entities has increased approximately 1087%, increasing from an average of 4.9 Mbps (as measured across the 840 connected entities) to an average of 533 Mbps. This was calculated based on 321 CAI's having 10 Mbps service and 408 CAI's having no connectivity at all. Once BTOP funded facilities were in place, 111 CAI's increased from 10 Mbps to 1000 Mbps and 408 increased from zero connectivity to 1000 Mbps. Additionally, the improved 321 CAI's while technically not receiving additional bandwidth, benefit dramatically from vastly increased backbone link connectivity that has had a 100% increase in capacity (from single 10Gbps link to two 10Gbps links) as a result of BTOP funds. | None at this time | The project is fully committed to providing access to any entity requesting connection to the network as outlined in the NOFA under Section D.3.b (Nondiscrimination and Interconnection obligations for CCI projects). As of the filing of this report, we have not blocked or limited any subscribers access to service or lawful content at the connected locations. From a network management standpoint, the network has the inherent capability to perform application separation, traffic prioritization and bandwidth shaping should these requirements be necessary. Applicable policies and determination guidelines are currently being revised and/or developed and will be posted as required as soon as they are complete. | N/A | 20463 | 9528 | 0 | 9600 | 405 | 0 | 930 | N/A | 5088 | 3816 | 0 | 1272 | N/A | None at this time and none planned in this project. | Continual contact with FPO and Grants office is extremely beneficial. As the project has progressed, many guidance changes have been implemented. Make sure that all information is kept updated in the grants files along with all notes and explanations. | Department of Administration Services Bureau of Enterprise Systems & Technology | 1049 | 192 | 14 | 31 | 0 | 875 |  | 6 | 5 | 0 | 2172 | None at this time | None at this time | TRUE
NT10BIX5570150 | 2013 | 50,000 | As this project utilizes 100% IRU facilities, all new mile costs are fixed at $50,000 per new mile. The original baseline utilized total project miles for this calculation because all miles were considered new (as they had never been in service or utilized by the State). Because of the projects use of Fiber IRU only, later guidance had directed that miles are now classified as either new miles or upgraded miles. Total new miles under this formulation are 1053 new miles and 7827 upgraded miles. Additionally, PPR reporting guidance was changed to now reflect route miles. Under this guidance, there are 1053 route miles of new fiber and 2293 route miles are upgraded. If all route miles are taken into consideration, the cost per route mile would be $21,450 based on final expenditures. | 0 | N/A | 0 | N/A | 1000 Mbps | No variance | 0 | N/A | 533 Mbps | The network offers 3 speed tiers - 10 Mbps - 306 subscribers connected 100 Mbps - 111 subscribers connected 1000 Mbps - 525 subscribers connected | 0 | N/A | Average speed at the connected entities has increased approximately 1087%, increasing from an average of 4.9 Mbps (as measured across the 940 connected entities) to an average of 533 Mbps. This was calculated based on 321 CAI's having 10 Mbps service and 508 CAI's having no connectivity at all. Once BTOP funded facilities were in place, 111 CAI's increased from 10 Mbps to 1000 Mbps and 508 increased from zero connectivity to 1000 Mbps. Additionally, the improved 321 CAI's while technically not receiving additional bandwidth, benefit dramatically from vastly increased backbone link connectivity that has had a 100% increase in capacity (from single 10Gbps link to two 10Gbps links) as a result of BTOP funds. | None at this time | The project is fully committed to providing access to any entity requesting connection to the network as outlined in the NOFA under Section D.3.b (Nondiscrimination and Interconnection obligations for CCI projects). As of the filing of this report, we have not blocked or limited any subscribers access to service or lawful content at the connected locations. From a network management standpoint, while the network has the inherent capability to perform application separation, traffic prioritization and bandwidth shaping should these requirements be necessary, no limiting or blocking has been implemented. Should the need arise, applicable policies and determination guidelines would be developed and/or revised. As required, these policy changes would be posted as soon as they were completed and ready to implement. | N/A | 22427 | 17760 | 0 | 4712 | 0 | 0 | 0 | N/A | 5088 | 3816 | 0 | 1272 | N/A | N/A | Continual contact with FPO and Grants office has been extremely beneficial and should be emphasized to any current or future grantee as a critical success factor. As the project progressed, many guidance changes occurred and had to be implemented and followed. Without the support of the FPO and Grants office, compliance with these changes would have been difficult if not impossible to achieve. Additionally, be sure that all information, correspondence and documentation that is related to the grant is retained and kept up to date in the grant files. Supporting documentation for everything will smooth the compliance process. Finally, if issues occur, be sure to inform your FPO and Grants officer for their awareness to the situation as soon as possible and seek their assistance as necessary. | Department of Administration Services Bureau of Enterprise Systems & Technology | 1049 | 192 | 14 | 31 | 0 | 875 |  | 6 | 5 | 0 | 2172 | None at this time | None at this time | TRUE
NT10BIX5570153 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Ocean State Higher Education Economic Development Administrative Network | 383 | 72 | 4 | 34 | 114 | 31 |  | 132 | 144 | 39 | 953 | 1.) N/A 2.) N/A 3.) N/A | 1.) N/A 2.) N/A 3.) N/A Transit Agreements: 1.) N/A 2.) In 2010, OSHEAN provided tentative award to one fiber vendor in Rhode Island and one fiber vendor in Massachusetts. OSHEAN is currently negotiating the terms and conditions of the IRU with both vendors. 3.) N/A | TRUE
NT10BIX5570153 | 2011 | 0 | Network not yet complete, nor in service | 0 | Network not yet complete, nor in service | 0 | Network not yet complete, nor in service | 0 | Network not yet complete, nor in service | 0 | Network not yet complete, nor in service | 0 | Network not yet complete, nor in service | 0 | Network not yet complete, nor in service | The backbone fiber was not lit as of 2011 Q4. Therefore, no CAIs were provided with service. When connected, broadband service speeds from 1Gbps to 10Gbps will be provided. | Pricing plans have not been provided because fiber deployment is not complete. | Provision of services had not begun as on 2011 Q4. However, an Acceptable Use Policy, Interconnection Policy, Network Management Policy, and Nondiscrimination Policy have been established for the project. | N/A | 15288 | 0 | 0 | 0 | 0 | 0 | 15228 | N/A | 0 | 0 | 0 | 0 | The network was not complete as of 2011 Q4, so interconnections were not yet available. | N/A | None. | Ocean State Higher Education Economic Development Administrative Network | 383 | 72 | 4 | 34 | 114 | 31 |  | 132 | 144 | 39 | 953 | 1. 0 2. 0 3. No request was denied | 1. 0 2. 0 3. No request was denied | TRUE
NT10BIX5570153 | 2012 | 52,958 | Average cost is lower than that projected in the baseline. Through competitive bid, OSHEAN was able to secure lower IRU pricing. | 0 | N/A - No last mile provided | 0 | N/A - No last mile provided | 10G | No change | 0 | N/A - No last mile provided | 3G | Per the baseline, OSHEAN is offering a 1G and 10G handoff. 3G is the average handoff speed of CAIs connected as of 12/31/12. | 0 | N/A - No last mile provided | The average increase in broadband speed is 2.5G. This is calculated as the average of the average of broadband speed increases for CAIs receiving new or improved access. | No retail services are being provided by this project. | OSHEAN's network management policy includes provisions stating that bandwidth will not be preferentially allocated or limited to any specific class of users, applications, providers or sources. Except for enforcing contracted bandwidth limits, OSHEAN does not limit bandwidth usage by its users, peers, or providers via mechanisms such as rate limiting or policing. OSHEAN does not restrict a user's access to specific content, block the use of specific applications, or limit the type of devices that can be used to access to network. | No subscribers have dropped bandwidth service. | 18081 | 17337 | 0 | 48 | 0 | 0 | 696 | N/A | 0 | 0 | 0 | 0 | Network providers and/or customers may interconnect with the OSHEAN network at any of the points of interconnection. OSHEAN has also installed slack loops along the backbone routes so that laterals can easily be installed to directly connect to new facilities to the network. | N/A | OSHEAN has utilized IRUs for the procurement of fiber, and found this to be a cost and time savings vehicle. | Ocean State Higher Education Economic Development Administrative Network | 383 | 72 | 4 | 34 | 114 | 31 |  | 132 | 144 | 39 | 953 | 1. 0 2. 0 3. No request was denied | 1. 0 2. 0 3. No request was denied | TRUE
NT10BIX5570153 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10G | No change | 0 | N/A | 1.4G | Per the baseline, OSHEAN is offering a 1G and 10G handoff. 1.4G is the average speed of all CAIs included in the final project total. | 0 | N/A | The average increase in broadband speed is 1.0G. This is calculated as the average of the broadband speed increases for all CAIs included in the project. For CAIs where the previous service was being provided by another provider or otherwise unknown, estimates were used. | OSHEAN provides our member organizations with the following retail services under this project (see attachment for current price lists): 1) IP transport services - connectivity of up to 10Gbps per individual site via the BTOP network for IP transport between member locations, to other OSHEAN, regional, and national on-net services, and to OSHEAN POPs for delivery of commodity Internet service. 2) Commodity Internet service which includes multiple upstream ISPs, redundant POP locations, 1.5x burst capability, and unmetered access to Internet2. 3) OSHEAN Safe Harbor service: On-net colocation rack, power, and pipe service for backup and disaster recovery. | OSHEAN's network management policy includes provisions stating that bandwidth will not be preferentially allocated or limited to any specific class of users, applications, providers or sources. Except for enforcing contracted bandwidth limits, OSHEAN does not limit bandwidth usage by its users, peers, or providers via mechanisms such as rate limiting or policing. OSHEAN does not restrict a user's access to specific content, block the use of specific applications, or limit the type of devices that can be used to access to network. | No subscribers have dropped bandwidth service to date. | 20397 | 2399 | 0 | 17998 | 0 | 0 | 0 | OSHEAN makes available wholesale dark fiber, but currently have no wholesale customers and no fiber miles being leased. | 0 | 0 | 0 | 0 | Network providers and/or customers may interconnect with the OSHEAN network at any of the points of interconnection. OSHEAN has also installed slack loops along the backbone routes so that laterals can easily be installed to directly connect to new facilities to the network. | N/A | OSHEAN has utilized IRUs for the procurement of fiber, and found this to be a cost and time savings vehicle. | Ocean State Higher Education Economic Development Administrative Network | 383 | 72 | 4 | 34 | 114 | 31 |  | 132 | 144 | 39 | 953 | N/A - no formal requests have been made to date | As part of the IRU maintenance agreement with Cox Communications, a peering relationship was established providing for settlement free peering between the Cox (RI) network and OSHEAN, allowing traffic destined for each other's network to pass directly without going out to the Internet. This provides better performance for both OSHEAN and Cox customers' local traffic that traverses our networks. This peering connection is being made physically at OSHEAN's AP1 facility at 235 Promenade Street in Providence. In addition, as part of our IRU agreement with the BTOP recipient OpenCape, we have a peering arrangement where they connect to our network at OSHEAN's AP1 facility at 235 Promenade Street in Providence. | TRUE
NT10BIX5570156 | 2010 | 0 | n/a Network not yet deployed. | 0 | n/a Network not yet deployed. When operating will be Middle Mile only. | 0 | n/a Network not yet deployed. When operating will be Middle Mile only. | 0 | n/a Network not yet deployed. | 0 | n/a Network not yet deployed. When operating will be Middle Mile only. | 0 | n/a Network not yet deployed. | 0 | n/a Network not yet deployed. When operating will be Middle Mile only. | n/a The network has not yet been deployed as we are waiting for a Grantee Substitution finalization. Once this is complete, we can begin the Environmental Assessment and Network Design. | n/a The network has not yet been deployed so we are not yet at this step. | n/a The network has not yet been deployed so we are not yet at this step. | n/a The network has not yet been deployed so we are not yet at this step. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a The network has not yet been deployed so we are not yet at this step. | 0 | 0 | 0 | 0 | n/a The network has not yet been deployed so we are not yet at this step. | n/a The network has not yet been deployed so we are not yet at this step. | Due to the pending Grantee Substitution request, we have not spent any grant funds through the fourth quarter. The request should be finalized in January 2011. Because we were the first grant recipient to request this, the process was unclear and there were many starts and stops. The lessons learned were to work closely with the Federal Program Officer and to be extremely flexible with time frame targets whenever engaged in a process that is not part of the normal program processes. | Centennial Board of Cooperative Educational Services | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | n/a | n/a | TRUE
NT10BIX5570157 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | As the project is still completing the Environmental Assessment, we have not implemented any new fiber. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | As we did not accept the grant until mid-October our experience has been limited. Our primary activities have been centered around establishing all necessary policies, procedures and other foundational aspects in order to properly administer the grant and begin the development of our project. | Adams County Communications Center, Inc. | 1 | 0 | 0 | 0 | 0 | 15 |  | 6 | 0 | 0 | 22 | N/A | N/A | TRUE
NT10BIX5570157 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | For one CAI, the speed shifted from a standard T1 line to a 10GB/sec connection. For the remaining connections they shifted from 1GB/sec to 10GB/sec. | N/A | The network in question is a closed public safety network. | N/A | 2072 | 40 | 0 | 160 | 1872 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Adams County Communications Center, Inc. | 1 | 0 | 0 | 0 | 0 | 15 |  | 6 | 0 | 0 | 22 | N/A | N/A | TRUE
NT10BIX5570157 | 2012 | 45,239 | This number varies from the previous APR and Baseline Plan because it was previously believed our project did not count as a Middle Mile provider. Our fiber project connects directly between Community Anchor Institutions, but does not interconnect to fiber provided by 3rd party re-sellers. Therefore, we considered the fiber as "home run" and was unreported. Upon further clarification from the Grants Office, we are now counting this as middle mile connectivity. This number is calculated based on true costs incurred from the installation of the fiber. This is higher than the baseline estimate, because that was an estimate only - it was generated using the install cost of one run of fiber through one specific area. We had no empirical data to use for the various terrains, terrain etc. that would be required when formulating the original project plan. We also had to revise our originally planned route to accommodate changes to the project, and the distance of the new routes did not match original estimates. | 0 | N/A | 0 | N/A | 100 Mbps | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. | 0 | N/A | 100 Mbps | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. | 0 | N/A | For one CAI, this was the first connectivity they had to the network - 100% increase. Several CAIs were upgraded from a T1 line (1.5 Mbps) to the fiber network (100 Mbps) - 66.6% increase. Another CAI was upgraded from a Microwave connection (50 Mbps) to the fiber network (100 Mpbs) - 50% increase. One additional CAI was added to our list - Southwest Adams County Fire. This was not in our original project plan because it was originally intended as an LTE site alone. We have since formed an agreement with the agency to provide network access through the installed backhaul to our facility and other CAI locations. This CAI will be added to the project plan when the project plan revision is submitted. | N/A | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. This limitation is imposed at the network device connecting to the CAI. Each CAI uses the connection to access servers and data hosted at the ADCOM911 facility, or share data directly between each other. Since this is a closed network that does not link to the internet or other 3rd party network, no other blocking mechanism has been established. | N/A | 871 | 57 | 0 | 646 | 56 | 0 | 112 | N/A | 1570 | 1364 | 0 | 206 | The majority of interconnection and peering points are facilities owned and maintained by Community Anchor Institutions. Those entities allow us to use collocation space in return for us providing them service on the network. We typically connect to each CAI inside their existing data center. Therefore they own their own space, and we do not pay any lease for use of that space. Our project does not include connection to other 3rd party or internet based networks. | N/A | Accurate documentation of each segment of fiber that exists between two interconnection points is critical. Most network diagrams simply list the connectivity between Point A and Point B, without listing any patch panels or interconnections between them. To help facilitate more accurate reporting, and for internal tracking purposes, projects should list the number of strands and distance of those strands between each interconnection point, whether equipment terminates at that location or not. | Adams County Communications Center, Inc. | 1 | 0 | 0 | 0 | 0 | 15 |  | 6 | 0 | 0 | 22 | N/A | N/A | TRUE
NT10BIX5570157 | 2013 | 40,495 | This number varies from the Baseline Plan because it was previously believed our project did not count as a Middle Mile provider. Our fiber project connects directly between Community Anchor Institutions, but does not interconnect to fiber provided by 3rd party re-sellers. Therefore, we considered the fiber as "home run" and was unreported. Upon further clarification from the Grants Office, we are now counting this as middle mile connectivity. This number is calculated based on true costs incurred from the installation of the fiber. This is higher than the baseline estimate, because that was an estimate only - it was generated using the install cost of one run of fiber through one specific area. We had no empirical data to use for the various terrains, terrain etc. that would be required when formulating the original project plan. We also had to revise our originally planned route to accommodate changes to the project, and the distance of the new routes did not match original estimates. | 0 | N/A | 0 | N/A | 100 Mbps | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. | 0 | N/A | 100 Mbps | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. | 0 | N/A | The only new connection to a CAI's for 2013 was connected via new fiber optic installed to those locations, which represents a 100% increase. One of the CAI's listed in the 2013 addendum (Adams County Sheriffs Office) had not been reported in previous PPR or APR's. The link had been established in 2011. I am unsure as to why the discrepancy exists, but that CAI was also not listed in the 2012 APR addendum. I have corrected that mistake and it will be accounted for in future reports. The total number of CAI's increased from the 2012 report because of the addition of 5 CAI's which are represented in our route modification. | N/A | Our primary aggregation points provide a speed of 10 Gbps, and the intermediary aggregation points provide a speed of 1 Gbps. However, these links provide backhaul to multiple CAI connection points. Therefore, we only offer 100 Mbps connection to each CAI, to prevent oversubscription on the backhaul network. We can provide service to 10 CAIs on any single intermediary link without encountering network congestion. This limitation is imposed at the network device connecting to the CAI. Each CAI uses the connection to access servers and data hosted at the ADCOM911 facility, or share data directly between each other. Since this is a closed network that does not link to the internet or other 3rd party network, no other blocking mechanism has been established. | N/A | 1290 | 104 | 0 | 1186 | 0 | 0 | 0 | N/A | 1570 | 1364 | 0 | 206 | The majority of interconnection and peering points are facilities owned and maintained by Community Anchor Institutions. Those entities allow us to use collocation space in return for us providing them service on the network. We typically connect to each CAI inside their existing data center. Therefore they own their own space, and we do not pay any lease for use of that space. Our project does not include connection to other 3rd party or internet based networks. | N/A | Accurate documentation of each segment of fiber that exists between two interconnection points is critical. Most network diagrams simply list the connectivity between Point A and Point B, without listing any patch panels or interconnections between them. To help facilitate more accurate reporting, and for internal tracking purposes, projects should list the number of strands and distance of those strands between each interconnection point, whether equipment terminates at that location or not. | Adams County Communications Center, Inc. | 1 | 0 | 0 | 0 | 0 | 15 |  | 6 | 0 | 0 | 22 | N/A | N/A | TRUE
NT10BIX5570158 | 2010 | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | Not at this time. | Los Angeles Regional Interoperable Communications System Authority | 916 | 0 | 9 | 1 | 121 | 421 |  | 0 | 14 | 0 | 1482 | N/A | N/A | TRUE
NT10BIX5570158 | 2011 | 0 | On July 28, 2011, the LA-RICS Authority Board of Directors passed a motion to cancel the existing procurement. Per Counselâ€™s review, the original procurement for a turn-key system was not in compliance with California Public Contracts Code. The Authority released a new Request for Proposal (RFP) for the Telecommunications System on November 8, 2011. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | None. | Los Angeles Regional Interoperable Communications System Authority | 916 | 0 | 9 | 1 | 121 | 421 |  | 0 | 14 | 0 | 1482 | N/A | N/A | TRUE
NT10BIX5570158 | 2012 | 0 | While the proposals for the second procurement were being evaluated, HR 3630 was signed into law by President Obama. It mandates public agencies to vacate the T-Band spectrum which had been the cornerstone of the LA-RICS system design. After evaluating different options and deciding on a hybrid system to comply with the new law, the LA-RICS Authority Board decided to cancel the second procurement. A decision was also made to conduct separate procurements for telecom contractors for the Long Term Evolution (LTE) and the Land Mobile Radio (LMR) systems. On October 25, 2012, the RFP for the LMR system was released. Proposals are being evaluated and a contract is expected to be executed by June, 2013. By mid February, 2013, the RFP for the LTE system should be substantially complete pending decision by FirstNet and instructions from NITA. | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | None. | Los Angeles Regional Interoperable Communications System Authority | 916 | 0 | 9 | 1 | 121 | 421 |  | 0 | 14 | 0 | 1482 | N/A | N/A | TRUE
NT10BIX5570158 | 2013 | 0 | In April, 2010, LA-RICS began its first procurement of an LTE contract. During its course, concerns were raised about the request for proposal's compliance with the State of California Public Contracts Code, leading to its cancellation in July, 2011. In November, 2011, the second procurement started and was deep in the evaluation of proposals when Public Law 112-96 was signed by President Obama in February, 2012. The new law mandated public agencies to vacate the T-Band, which is the heart of the LA-RICS system design. The impact on the system design caused the second procurement to be cancelled in August, 2012. Also on May 11, 2012, the NTIA suspended all LTE-related activities and would not lift it until Aug 9, 2013. These events continue to hurt the project's ability to move forward: planned progress in network design, rights of way, construction permits and other approvals have been delayed. | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | Contracting Lessons regarding Site Selection to facilitate environmental clearances: Specifying a list of sites known to have least environmental issues and mandating vendors to use all sites enabled evaluators to analyze system capabilities, site lists, and costs on an equal platform. | Los Angeles Regional Interoperable Communications System Authority | 916 | 0 | 9 | 1 | 121 | 421 |  | 0 | 14 | 0 | 1482 | N/A | N/A | TRUE
NT11BIX5570001 | 2011 | 0 | n/a. No construction in 2011. | 0 | n/a. Middle mile network only. | 0 | n/a. Middle mile network only. | 1 | Will offer 1G as norm; some future subscribers may request up to 10 G. | 0 | n/a. Middle mile network only. | 93 | Current subscribers averaging 93.29 mbps. | 0 | n/a. Middle mile network only. | n/a. | n/a. EAGLE-Net is a middle-mile project and is not providing retail services directly to the public. | EAGLE-Net has Acceptable Use and Non-Discrimination and Interconnection Practice Policies (see http://www.co-eaglenet.net/Support.aspx for further details). EAGLE-Net does not impose any bandwidth limitations or access limitations to lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to its existing infrastructure or on proposed BTOP infrastructure. | n/a. | 6776 | 392 | 0 | 3300 | 3084 | 0 | 0 | n/a. | 0 | 0 | 0 | 0 | Currently lease rack space in 8 locations plus a room in our own leased building space. Square footage of facilities, total leased and available space is unknown. Locations are: Comfluent: 3 racks. Point of Interconnection Type: POP. Longmont-CBOCES: 2 racks. Point of Interconnection Type: Internet Exchange Point. Longmont-Kimbark: 1 rack. Point of Interconnection Type: POP. Tri-State: 4 racks. Point of Interconnection Type: Internet Exchange Point. FRGP: 1 rack. Point of Interconnection Type: POP Zayo: 5 racks. Point of Interconnection Type: Internet Exchange Point. Level 3: 1 rack. Point of Interconnection Type: POP. tw telecom: 2 racks. Point of Interconnection Type: POP. EAGLE-Net Alliance: 4 racks and 153 sq feet in server room of our office. Point of Interconnection Type: Internet Exchange Point. | n/a. | Two main things come to mine: 1. Hire a good, experienced contractor. The knowledge provided by our design/build contractor, G4S Technologies has been invaluable in this process. 2. The procurement process can often take longer than anticipated, so make sure that you plan on sufficient lead time to meet your deadlines. | Eagle-Net Alliance | 1765 | 260 | 16 | 3 | 450 | 308 |  | 770 | 78 | 113 | 3763 | n/a. | n/a. | TRUE
NT11BIX5570001 | 2012 | 49036 | This calculation is based on 660 miles of completed new fiber construction in several areas of the state. Variance to baseline is mostly based on change from microwave to fiber build in most areas of the state. | 0 | n/a. Middle mile network only. | 0 | n/a. Middle mile network only. | 1 | We offer 1G as the norm; some future subscribers may request up to 10G. | 0 | n/a. Middle mile network only. | 76.2 | For current subscribers, the highest speed currently requested is 500mbps and the lowest is 10mbps. | 0 | n/a. Middle mile network only. | The average increase in broadband speed to CAI's has varied from entities that have received 20 Mbps increases to CAI's that have received 300 Mbps increases in broadband speed. | n/a. EAGLE-Net is a middle-mile project and is not providing retail services directly to the public. | EAGLE-Net has Acceptable Use and Non-Discrimination and Interconnection Practice Policies (see http://www.co-eaglenet.net/support.aspx for further details). EAGLE-Net does not impose any bandwidth limitations or access limitations to lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to its existing intrastructure or on proposed BTOP infrastructure. | 1 CAI. School district now purchases service from the local provider, although EAGLE-Net now supplies service to the local provider for this customer. | 38944 | 3712 | 0 | 23584 | 1165 | 0 | 10483 | n/a. No dark fiber leased out at this time. | 0 | 0 | 0 | 0 | Currently lease rack space in several locations throughout the state. Locations are: Colorado Springs POI: 1 rack, 4 sq feet 910 15th St Denver POI: 1 rack, 4 sq feet Akron POI: 1 rack, 4 sq feet Aurora POP: 2 racks, 8 sq feet Byers POI: 1 rack, 4 sq feet Cheyenne Wells POI: 1 rack, 4 sq feet Flagler POI: 1 rack, 4 sq feet Fort Morgan POI: 1 rack, 4 sq feet Limon POI: 1 rack, 4 sq feet Prospect Valley POI: 1 rack, 4 sq feet Pueblo Peer: 1 rack, 4 sq feet Rifle POI: 1 rack, 4 sq feet Sterling POI: 1 rack, 4 sq feet Wray POI: 1 rack, 4 sq feet Cahone POI: 1 rack, 4 sq feet Durango POP: 1 rack, 4 sq feet Empire POI: 1 rack, 4 sq feet Montrose POI: 1 rack, 4 sq feet Nucla POI: 1 rack, 4 sq feet Haystack Butte POI: 1 rack, 4 sq feet Lynn POI: 1 rack, 4 sq feet Pueblo DC POI: 4 racks, 16 sq feet, 200 sq feet available Pueblo Peer: 1 rack, 4 sq feet Grand Junction Peer: 1 rack, 4 sq feet Durango Peer: 1 rack, 4 sq feet Denver Peer: 4 racks, 16 sq feet Colorado Springs Peer: 3 racks, 12 sq feet, 400 sq feet available | n/a | The building of a large network such as our statewide project will result in many changes from the original plan and design for many reasons. Our primary lesson learned is to ensure that all changes are discussed in detail and approved. | Eagle-Net Alliance | 1765 | 260 | 16 | 3 | 450 | 308 |  | 770 | 78 | 113 | 3763 | EAGLE-Net currently has 8 interconnection agreements and is in negotiations for 5 more. No requested agreements have been denied. | EAGLE-Net currently has 1 Peering agreement and is in negotiations for 6 more. No requested agreements have been denied. | TRUE
NT11BIX5570001 | 2013 | 44,212 | This calculation is based on 809 miles of completed new fiber construction in several areas of the state. Variance to baseline is mostly based on change from microwave to fiber build in most areas of the state. | 0 | n/a. Middle mile network only. | 0 | n/a. Middle mile network only. | 1 | We offer 1G as the norm; some future subscribers may request up to 10G. | 0 | n/a. Middle mile network only. | 107.7 | For current subscribers, the highest speed currently requested is 800mbps and the lowest is 10mbps. | 0 | n/a. Middle mile network only. | The average increase in broadband speed to CAI's has varied from entities that have received 20 Mbps increases to CAI's that have received 300 Mbps increases in broadband speed. | n/a. EAGLE-Net is a middle mile project and is not providing retail services directly to the public. | EAGLE-Net has Acceptable Use and Non-Discrimination and Interconnection Practice Policies (see http://www.co-eaglenet.net/support.aspx for further details). EAGLE-Net does not impose any bandwidth limitations or access limitations to lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to its existing intrastructure or on proposed BTOP infrastructure. | No subscribers dropped EAGLE-Net service during this year. | 37656 | 3860 | 0 | 27790 | 104 | 3456 | 2446 | n/a. No dark fiber leased at this time. | 0 | 0 | 0 | 0 | Currently lease rack space in several locations throughout the state. Locations are: Colorado Springs POI: 1 rack, 4 sq feet 910 15th St Denver POI: 1 rack, 4 sq feet Akron POI: 1 rack, 4 sq feet Aurora POP: 2 racks, 8 sq feet Byers POI: 1 rack, 4 sq feet Cheyenne Wells POI: 1 rack, 4 sq feet Flagler POI: 1 rack, 4 sq feet Fort Morgan POI: 1 rack, 4 sq feet Limon POI: 1 rack, 4 sq feet Prospect Valley POI: 1 rack, 4 sq feet Pueblo Peer: 1 rack, 4 sq feet Rifle POI: 1 rack, 4 sq feet Sterling POI: 1 rack, 4 sq feet Wray POI: 1 rack, 4 sq feet Cahone POI: 1 rack, 4 sq feet Durango POP: 1 rack, 4 sq feet Empire POI: 1 rack, 4 sq feet Montrose POI: 1 rack, 4 sq feet Nucla POI: 1 rack, 4 sq feet Haystack Butte POI: 1 rack, 4 sq feet Lynn POI: 1 rack, 4 sq feet Pueblo DC POI: 4 racks, 16 sq feet, 200 sq feet available Pueblo Peer: 1 rack, 4 sq feet Grand Junction Peer: 1 rack, 4 sq feet Durango Peer: 1 rack, 4 sq feet Denver Peer: 4 racks, 16 sq feet Colorado Springs Peer: 3 racks, 12 sq feet, 400 sq feet available Craig POI: 1 rack, 4 sq feet | n/a. | One of our key decisions was to sign an agreement with a network operator. This process started with an Invitation to Negotiate for interested parties to become involved. The end result was definitely what we wanted and it is working out very well for both parties. However, if a grantee intends to follow a similar process, please be sure to anticipate the amount of time and resources that the process may take, as it can become very time consuming. | Eagle-Net Alliance | 1765 | 260 | 16 | 3 | 450 | 308 |  | 770 | 78 | 113 | 3763 | EAGLE-Net currently has eight service agreements with wholesale and last mile providers to whom it is providing service. In addition, it has 26 signed Master Service Agreements that provide the framework for future service agreements, and it is in negotiations with another 33 providers for future agreements. No requests for interconnection have been denied. | EAGLE-Net currently has service agreements with seven providers from whom it is purchasing peering and transit services. No other agreements are currently being negotiated to obtain additional transit services. | TRUE
NT12BIX5570001 | 2012 | $54,263.56 | Based on the miles constructed versus estimated funds to Zayo is tracking on budget. | 0 | N/A | 0 | N/A | 10G | This matches our baseline. | 0 | N/A | 1G | This matches our baseline. | 0 | N/A | 10 GBPS based on the unserved areas | This is a middle mile project. | Zayo standard. Zayo has never blocked customers from accessing any lawful content, service, service provider, or application and we have never prevented any customer from attaching any legal devise to our network.. | 0 | 64128 | 1334 | 298 | 62399 | 1 | 2 | 94 | Comcast Cable - 17, Extenet Systems - 12, I-Light - 692, Windstream - 210, Lightbound - 45, Smithville Digital - 146, ETC/Sunman - 16, Trelleborg - 14.5, | 0 | 0 | 0 | 0 | Customer interconnection points can be located at any of the Zayo splice locations throughout the entire build. | 4 - Gray and Pape, Eustis Cable, Baseline NXC, ECOP Cable | From the sales perspective, it's important to engage with any prospects, whether CAIs or wholesale companies, early on. We found that the wholesale customer understand the challenges faced with any build, and will therefore order early and wait on delivery. CAIs, however, need to understand that the project is done before committing to using service. | Zayo Group, LLC | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 9 | 38 agreement, combination of both lit and dark services. Currently negotiating 57 agreements. We have denied no request for interconnection. | Zayo does not enter into Peering and Transit Agreements, except at the national level, which is not impacted by Indiana's assets. | TRUE
NT12BIX5570002 | 2012 | $65,077/10G | Based on the miles constructed versus estimated funds to Zayo is tracking on budget. | 0 | N/A | 0 | N/A | 10G | This matches our baseline. | 0 | N/A | 1G | This matches our baseline. | 0 | N/A | 10 GBPS based on the unserved areas | Current retail services are 0. | Zayo standard. Zayo has never blocked customers from accessing any lawful content, service, service provider, or application and we have never prevented any customer from attaching any legal devise to our network.. | 0 | 35532 | 1952 | 3112 | 12702 | 0 | 0 | 17766 | Anoka County for 12 Dark Fibers in the core ring as well as 4 dark fibers throughout the distribution network. | 0 | 0 | 0 | 0 | Customer interconnection points can be located at any of the Zayo splice locations throughout the entire build, or the Zayo existing POP site located at 511 11th Ave South Suite 110 Minneapolis, MN | 4 - Fiber Engineering and Design, Entagon, Power and Telephone, ECOP Cable | N/A | Zayo Group, LLC | 4 | 12 | 3 | 1 | 2 | 56 |  | 0 | 53 | 0 | 131 | Zayo current agreements - Anoka County IRU Agreement also Master Services Agreement. 0 Negotiating - Zayo has not denied any request for services. | 0 - Currently, 0 - Negotiating, Zayo has not denied any request for services. | TRUE