NT10BIX5570066 | 2012 | Q3 | Q3 - 2012 | 8030 | 6721 | FALSE | 89 | Project an estimated 40 miles to be build out. | 100 | Grant Management | Complete | 100 | All current route environmental assessments complete. | 100 | All current route network design complete. | 89 | Based on mileage completed. | 95 | We have changed tracking method of this category from expensed versus projected dollars to actual tracking of known outstanding easement and permits versus total needed easements and permits. Original assumption was that easements and permits would be received during engineering phase did not hold, thus the need to change tracking method. | 87 | Correlated with Network Build so percentage will concur with that category. | 80 | Expect 17 routes to be completed and lit by end of 2012-Q4. | 87 | Basically in line with baseline schedule. Baseline estimated at 88% at end of Q4-2012. As noted previously, BVU can bring in additional crews when easements obtained. | 80 | Allocation done in conjunction with Equipment Procurement, so percentage is consistent with Equipment Procurement percentage. | 47 | Expect multiple routes to be completed and lit in 2012-Q4 with an effect that network testing will increase significantly. | 2012-11-26 11:34 | 2012-11-26 11:34 | 7556 | 7556 | BVU Authority | TRUE
NT10BIX5570066 | 2012 | Q4 | Q4 - 2012 | 8700 | 7509 | FALSE | 93 | Note: Change in calculation method per request from Federal Program Officer. Was based on mileage, but now based on expensed/in-kind versus project dollars. | 100 | Grant Prep | Complete | 100 | All current route environmental assessments complete. | 100 | All current route network design complete unless issues found during built out which may cause a very minor adjustment. | 91 | Note: Change in calculation method per request from Federal Program Officer. Was based on mileage, but now based on construction expensed/in-kind versus project dollars. | 100 | Expect all permits and "quick-take" condemnations completed by end of quarter. | 91 | Based on expensed/in-kind versus project dollars for construction. Site prep is allocated of 0.5% of construction dollars, so projection is consistent with [Network Build] percentage. | 80 | Based on expensed/in-kind versus project dollars for equipment. Allocation done in conjunction with [Equipment Deployment], so percentage is consistent with [Equipment Deployment] percentage. | 91 | Based on expensed/in-kind versus project dollars for construction. Network Build is allocated of 0.5% of construction dollars, so projection is consistent with [Site Preparation] percentage. | 80 | Based on expensed/in-kind versus project dollars for equipment. Allocation done in conjunction with [Equipment Procurement], so percentage is consistent with [Equipment Procurement] percentage. | 65 | Based on expensed versus project dollars. | 2013-02-11 12:05 | 2013-02-11 12:05 | 7556 | 7556 | BVU Authority | TRUE
NT10BIX5570066 | 2013 | Q1 | Q1 - 2013 | 9830 | 8451 | FALSE | 100 | Expect project to be complete except for any award closing tasks. | 100 | Grant prep | Complete. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 2013-05-20 14:32 | 2013-05-20 14:32 | 7556 | 7556 | BVU Authority | TRUE
NT10BIX5570066 | 2013 | Q2 | Q2 - 2013 | 10650 | 8985 | FALSE | 100 | Expect project to be complete except for any award closing tasks. | 100 | Grant Preparation | Completed. | 100 | Completed. | 100 | Completed. | 100 | Completed. | 100 | Completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 100 | Expect to be completed. | 2013-08-20 10:16 | 2013-08-20 10:16 | 7556 | 7556 | BVU Authority | TRUE
NT10BIX5570066 | 2013 | Q3 | Q3 - 2013 | 12288 | 10459 | FALSE | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Grant Preparation | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 100 | Next quarter milestones are not applicable due to project being completed. | 2014-06-24 10:52 | 2014-06-24 10:52 | 5759 | 5759 | BVU Authority | TRUE
NT10BIX5570067 | 2010 | Q4 | Q4 - 2010 | 1254 | 2284 | FALSE | 27 | Based on overall budget vs planned spend through 3/31/2011. Almost all equipment and materials will have been received by quarter end (>$13mm) | 0 |  | N/A | 100 | The EA will be completed with the FONSI. | 95 | % complete as a % of effort. Estimate to complete is based on initial design being completed after EA approval, and additional ongoing design activities continue as network is built. Most of the matching funds in this category will be expended on the ongoing design optimization activities. | 0 | We do not foresee the need for any new Rights of Way in Q2-2011, as we will just be starting construction. It was assumed for planning purposes some new rights of way might be needed. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. We do still anticipate we may need one or two. As these are encountered, and budget from the "Land, Structures, Rights of Way" is expended, it will be reported here. | 71 | Percent complete is based on % of budget from the project budget category of "Land, Structures, Rights of Way" (424-C category), which we mapped into this PPR and baseline milestone category. So as a % of budget allocated to this milestone category, we will ramp up of "make ready" (MR) engineering activities by utility companies by quarter end. | 11 | Percent complete based on % of budget. Matching funds will be spent on existing hub site upgrade in Q2 2011. | 42 | Percent complete based on: fed funding - receipt of additional equipment shipments from PO's placed in December (for equipment) and January (for fiber); and matching funding from payments by sub-recipients in preparation of their network build outs. | 11 | Percent complete based on ramp up of make ready on aerial routes post-FONSI; commencement of underground where plausible on underground routes. Of 13 overall ring segments we are planning to start work on the top five (5) rings. | 17 | Percent complete based on work at existing core network sites; post-FONSI when deployment can begin. Less than 1% of total project. Plus matching funds spent by sub-recipients on equipment installation. | 0 | This will be continuous throughout, but with construction ramping up we do not anticipate a significant amount of effort here through 3/31/2011. | 2011-02-20 22:33 | 2011-02-20 22:33 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2011 | Q1 | Q1 - 2011 | 1942 | 2716 | FALSE | 27 | Based on overall budget vs planned spend through 6/30/2011. Almost all equipment and materials will have been received by quarter end (>$13mm). This % complete is based on anticipated spend versus total project funds; it is behind plan, due to elongated payment terms for equipment, fiber, and construction materials. | 0 |  | N/A | 100 | Complete | 100 | The % complete is expressed as a % of budget consumed. | 0 | We do not foresee the need for any new Rights of Way in Q2-2011, as we will just be starting construction. It was assumed for planning purposes some new rights of way might be needed. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. We do still anticipate we may need one or two. As these are encountered, and budget from the "Land, Structures, Rights of Way" is expended, it will be reported here. | 50 | Percent complete is based on % of budget from the project budget category of "Land, Structures, Rights of Way" (424-C category), which we mapped into this PPR and baseline milestone category. So as a % of budget allocated to this milestone category, we will ramp up of "make ready" (MR) engineering activities by utility companies by quarter end. We will still be behind the baseline for the project, as the utility companies have been slow to respond to requests, due to the volume of requests they are dealing with from the federal programs and other requests. NOTE: this is an area where, given current turn around times and fees, we anticipate being significantly over budgeted amounts for "make ready" work. | 60 | Percent complete based on % of budget. Matching funds will be spent on existing hub site upgrade in Q2 2011. | 80 | Percent complete based on: fed funding - receipt of additional equipment shipments from PO's placed in December (for equipment) and January (for fiber); and matching funding from payments by sub-recipients in preparation of their network build outs. | 11 | Percent complete based on ramp up of make ready on aerial routes post-FONSI; commencement of underground where plausible on underground routes. Of 13 overall ring segments we are planning to start work on the top five (5) rings. | 17 | Percent complete is based on percent of budget available vs anticipated spending in the quarter. We anticipate being ahead of baseline in upgrading our exsiting hub sites. | 0 | This will be continuous throughout, but with construction ramping up we do not anticipate a significant amount of effort here through 6/30/2011, as we will push to complete "make ready" and permitting while ramping up construction | 2011-05-11 13:15 | 2011-05-11 13:15 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2011 | Q2 | Q2 - 2011 | 3186 | 3353 | FALSE | 56 | Based on overall budget vs planned spend through 9/30/2011 at 56% complete as part of total budget (fed and match), with baseline at 48%. | 0 |  | n/a | 100 | complete | 95 | designs will be completed. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. We recognize we may need one or two additional new ROW's. As these are encountered, and budget from the 424C category of "Land, Structures, Rights of Way" is expended, it will be reported here. | 80 | Percent complete is based on % of budget from the project budget category of "Land, Structures, Rights of Way" (424-C category), which we mapped into this PPR and baseline milestone category. So as a % of budget allocated to this milestone category, we will ramp up of "make ready" (MR) engineering activities by utility companies by quarter end. We will still be behind the baseline for the project - 70% vs 90% baseline - as the utility companies have been slow to respond to requests, due to the volume of requests they are dealing with from the federal programs and other requests. NOTE: this is an area where, given current turn around times and fees, we anticipate being significantly over budgeted amounts for "make ready" work. | 20 | Percent complete based on % of budget. Matching funds will be spent on existing hub site upgrade in Q3 2011. | 92 | Percent complete based on fed funding matching funding from payments by sub-recipients in preparation of their network build outs. | 21 | Percent complete estimated at 12.8% (vs baseline of 15%). | 9 | Percent complete is based on percent of budget available vs anticipated spending in the quarter. We anticipate being ahead of baseline in upgrading our exsiting hub sites (18% vs 10% in baseline) | 6 | This will be continuous throughout, but with construction ramping up we do not anticipate a significant amount of effort here through 6/30/2011, as we will push to complete "make ready" and permitting while ramping up construction. | 2011-08-18 08:43 | 2011-08-18 08:43 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2011 | Q3 | Q3 - 2011 | 4130 | 3911 | FALSE | 58 | Percentage complete is based on total project budget expended, including federal and matching portions. We are aggressively pursuing make ready and other permitting on over 70% of the network in program scope. We are pushing to have "make ready" paid for and in progress by December 31, 2011, allowing us plenty of time in Q1 and Q2 to finish those ring segments. | 100 | miscellaneous items | Additional planned incidental expenses will be less that 0.5% in total | 100 | complete. Incidental EA costs are incurred as our Special Award Conditions (SACs) are enforced for Environmental Protection Measures to which we committed. | 100 | Complete. Incidental design costs are incurred as route optimization continues during the build phase. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. We recognize we may need one or two additional new ROW's. As these are encountered, and budget from the 424C category of "Land, Structures, Rights of Way" is expended, it will be reported here. | 80 | We are aggressively pursuing make ready and other permitting on over 70% of the network in program scope. We are pushing to have "make ready" paid for and in progress by December 31, 2011, allowing us plenty of time in Q1 and Q2 to finish those ring segments. | 20 | On plan based on location preparations. We are under budget, as we've only had to spend 20% of budgeted funds in order to get sites prepared to move into. I anticipate the remaining budget, however, may be needed for several new locations yet to be identified. With respect to our 2/3 milestone in June, 2013, we have updated all locations required to support that 2/3 build out, so we are on plan but under budget. | 95 | We anticipate having almost all equipment in-house by quarter-end / year-end for the major backbones and laterals for the program. | 9 | We anticipate build phase will continue to expand as pathways are cleared for "make ready". | 70 | We anticipate being able to finish up to 70% of the Equipment Deployment phase, as fiber is run and terminated in our hub sites. This is dependent on the Network Build, however, which is dependent on the Construction Permits for "make ready". | 32 | With the continued deployment of equipment and "lighting" of the fiber, Network Testing will continue on plan. | 2011-11-18 12:09 | 2011-11-18 12:09 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2011 | Q4 | Q4 - 2011 | 5288 | 4956 | FALSE | 54 | Against a baseline of 65%, the project will make significant headway in getting back on track as a result of intense efforts with utility pole owners to complete make ready. Key risk to the project schedule at this point is the weather. | 100 | legal, admin, misc | Additional planned incidental expenses will be less that .5% of total grant | 100 | Our environmental assessment is complete and on file; enforcement of all Environmental Protection Measures (EPMs) continues through construction. | 100 | The core network design was completed in Q1 2011; design work continues as needed as a result of route optimization and EPM enforcement. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. | 80 | Percent complete expressed as a percent of the total core network which has been "cleared" for all make ready and permitting. | 24 | Site preparation will continue as required for core network hub sites. We do not anticipate needing any additional work during the quarter, so we are under budget at this point (i.e., behind baseline of 65% of budget) | 100 | We anticipate receipt of the final shipments of fiber, completing receipt of all equipment and materials for the core network. Equipment purchases going forward will primarily be related to customer premise equipment (CPE) to replenish inventories as CAI's are connected. | 10 | Expressed as a percent of budget. Baseline is at 40%. We are behind due to make ready work, however, we are also seeing favorable actual expenses as compared to budgets for work that has been completed. | 64 | Against a baseline of 40% complete, we will be over 50% complete, as all equipment is staged and awaiting the arrival of fiber at the facilities. | 24 | Against a baseline of 30%, testing activities should begin to ramp up as more hub site locations are reached during the quarter | 2012-02-27 13:29 | 2012-02-27 13:29 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2012 | Q1 | Q1 - 2012 | 6118 | 5661 | FALSE | 58 | Baseline is at 72% of budget. "Two thirds" complete milestone is due at end of Q2 2102, and we anticipate reaching that milestone with over 70% of FEDERAL funds having been invested in 24 counties in northeast Ohio, and 58% of TOTAL funds available (fed funds + match funds / program total funds budgeted). | 100 |  | Additional planned incidental expenses will be less that .5% of the total grant | 100 | Our environmental assessment is complete and on file; enforcement of all Environmental Protection Measures (EPMs) continues through construction. | 100 | The core network design was completed in Q1 2011; design work continues as needed as a result of route optimization and EPM enforcement. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. | 90 | Baseline is at 98% | 24 | Baseline is at 80%. We are trending to be under budget against estimated site prep costs for the program | 100 | Baseline is at 85%. | 25 | Baseline is at 55%. We are trending towards 2/3 completion by 6/30. Two factors are holding down % complete forecast - invoicing for work is lagging production into the following quarter, and we are trending to be under construction cost estimates overall for the project. | 43 | Baseline is at 55% | 24 | Baseline is at 40%. We are trending to be below costs in this category as well. | 2012-05-15 21:01 | 2012-05-15 21:01 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2012 | Q2 | Q2 - 2012 | 7102 | 6178 | FALSE | 60 | Baseline for total funds expended for Q3 is at 72%. We will be behind due to make ready invoicing catching up, and matching funds. | 100 |  | Additional planned incidental expenses will be less that .5% of the total grant | 100 | Our environmental assessment is complete and on file; enforcement of all Environmental Protection Measures (EPMs) continues through construction. | 100 | The core network design was completed in Q1 2011; design work continues as needed as a result of route optimization and EPM enforcement. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. | 92 | We will continue to press utility pole owners to invoice make ready for the fiber deployed and being deployed. % complete is expressed as a percent of make ready work vs. budget. | 24 | Site prep work continues as needed | 100 | Completed. Equipment purchases for customer builds will continue as needed | 20 | Baseline of 70%. We are experiencing some cost savings / reductions here from what was planned. | 36 | Baseline of 75%. We are experiencing some cost savings / reductions here from what was planned. | 25 | Baseline of 50%. We are experiencing some cost savings / reductions here from what was planned. | 2012-08-15 20:04 | 2012-08-15 20:04 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2012 | Q3 | Q3 - 2012 | 8076 | 6744 | FALSE | 68 | Percent complete based on total of funds expended, based on original grant and matching fund amounts. | 100 |  | Additional planned incidental expenses will be less than .5% of total grant. | 100 | Our environmental assessment is complete and on file; enforcement of all Environmental Protection Measures (EPMs) continues through construction. | 100 | The core network design was completed in Q1 2011; design work continues as needed as a result of route optimization and EPM enforcement. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. | 94 | Percent complete is based on poles submitted to utility pole owners for "make ready" versus percent of budget. Achieving this percent complete is dependent on utility pole owners' invoicing for make ready work. | 40 | Site preparation work continues as needed to complete the rings | 100 | Completed. Equipment purchases will continue for customer premise equipment and to support large services contracts. | 30 | Percent complete expressed as a percent of original project budget for grant funds and matching contributions. Based on actual work completed, we anticipate being over 70% complete in Q4 with all original middle mile routes. | 41 | Percent complete expressed as a percent of original project budget (grant funds plus matching contributions). Based on actual work completed we will be over 70% complete in Q4 with all hub site work. | 26 | Percent complete expressed as a percent of original project budget (grant funds plus matching contributions). Based on actual work completed we will be over 50% complete in Q4 with all testing & acceptance work. | 2012-11-27 15:25 | 2012-11-27 15:25 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2012 | Q4 | Q4 - 2012 | 9066 | 7839 | FALSE | 83 | Percent complete based on total of funds expended, based on original grant and matching fund amounts. | 41 |  | Incidental expenses will be less than 0.5% in total for the grant. | 100 | Our environmental assessment is complete and on file; enforcement of all Environmental Protection Measures (EPMs) continues through construction. | 77 | The core network design was completed in Q1 2011; design work continues as needed as a result of route optimization and EPM enforcement. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. | 77 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q1 2013. | 31 | Site preparation work continues as needed to complete the rings | 96 | Equipment purchases will continue for customer premise equipment and to support large services contracts. | 71 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q1 2013. | 100 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q1 2013. | 49 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q1 2013. | 2013-02-28 12:12 | 2013-02-28 12:12 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2013 | Q1 | Q1 - 2013 | 10036 | 8568 | FALSE | 89 | The project will reach 89% completion during Q2 2013, based on total funds expended (federal & matching) against the revised budget. Main expenditures in Q2 will be construction invoices for several large contracts with CAI's which will in turn generate program income which will be reinvested as matching funds, as well as "make ready" expenses. | 100 |  | Incidental expenses will be less than 0.5% in total for the grant. | 100 | Environmental Assessment was completed in Q1 2013, and EA activities continue through the enforcement of our Environmental Protection Measures. | 80 | Network design will be at 80% of revised budget. Network design activities continue as needed for redesign of routes due to EPM enforcement. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. | 83 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q2 2013. | 42 | Site preparation work continues as needed to complete the rings | 100 | Equipment purchases will continue for customer premise equipment & OSP materials replenishment, expending all of revised budget funds. | 77 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q2 2013. | 94 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q2 2013. | 60 | Percent complete is based on budgeted amount (revised budget) and actual expenditures through Q2 2013. | 2013-05-31 16:13 | 2013-05-31 16:13 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2013 | Q2 | Q2 - 2013 | 10814 | 9079 | FALSE | 98 | All construction and related activities will be completed ON OR BEFORE 9/30/2013. Expressed as a percent of budget, we anticipate most bills will be paid in the quarter, however, some invoices are anticipated to come in during the close out period, but again for all work completed prior to 9/30/2013. | 100 | miscellaneous | percent complete is based on budgeted amount (revised budget) and actual expenditures through Q3 2013. | 100 | Environmental Assessment was completed in Q1 2013, and EA activities continue through the enforcement of our Environmental Protection Measures. | 100 | Network design activities continue as needed for redesign of routes due to EPM enforcement. | 0 | We do not foresee the need for any new Rights of Way during this project, as we are deploying in existing Rights of Way. To-date we have found no need for new Rights of Way for the project - we are in existing rights of way and are seeking permit approvals from the utility infrastructure owners. Hence the variance from the baseline will continue. | 100 | percent complete is based on budgeted amount (revised budget) and actual expenditures through Q3 2013. | 42 | Site preparation work is expected to continue as needed to complete the rings | 100 | Equipment purchases may continue for customer premise equipment & OSP materials replenishment, but only as needed in order to complete work by 9/30. | 95 | All construction and related activities will be completed ON OR BEFORE 9/30/2013. Expressed as a percent of budget, we anticipate most bills will be paid in the quarter, however, some invoices are anticipated to come in during the close out period, but again for all work completed prior to 9/30/2013. | 100 | percent complete is based on budgeted amount (revised budget) and actual expenditures through Q3 2013. | 90 | All construction and related activities will be completed ON OR BEFORE 9/30/2013. Expressed as a percent of budget, we anticipate most bills will be paid in the quarter, however, some invoices are anticipated to come in during the close out period, but again for all work completed prior to 9/30/2013. | 2013-08-29 17:10 | 2013-08-29 17:10 | 6117 | 6117 | ONECOMMUNITY | TRUE
NT10BIX5570067 | 2013 | Q3 | Q3 - 2013 | 12522 | 10699 | FALSE | 100 | completed | 100 | miscellaneous | completed | 100 | completed | 100 | completed | 0 | N/A | 100 | completed, however OneCommunity remains responsible for a substantial amount of "make ready", as the incumbent pole owners were NOT able to meet the volumes demanded for the BTOP programs in their areas. | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 100 | completed | 2014-10-07 10:41 | 2014-10-07 10:41 | 7897 | 7897 | ONECOMMUNITY | TRUE
NT10BIX5570068 | 2010 | Q3 | Q3 - 2010 | 260 | 1396 | FALSE | 14 | N/A | 0 | N/A | N/A | 100 | Planned completion in early January 2011 | 10 | Engineering Implementation | 10 | Engineering Implementation | 10 | Engineering Implementation | 10 | Engineering Implementation | 0 | Not started | 0 | Not started | 0 | Not started | 0 | Not started | 2010-10-29 16:52 | 2010-10-29 16:52 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2010 | Q4 | Q4 - 2010 | 502 | 1525 | FALSE | 1 | Awaiting EA Approval | 50 | Land | 3 properties under contract | 100 | Submitted draft EA on Dec 22, 2010 | 35 | Awaiting EA Approval | 25 | Awaiting EA Approval | 0 | Awaiting EA Approval | 50 | Awaiting EA Approval | 0 | Awaiting EA Approval | 10 | Awaiting EA Approval | 0 | Awaiting EA Approval | 0 | Awaiting EA Approval | 2011-01-21 09:02 | 2011-01-21 09:02 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2011 | Q1 | Q1 - 2011 | 1510 | 2468 | FALSE | 2 | See below | 50 | Land & Buildings | Close on 3 properties under contract in Brownsville, Weslaco and Edinburg | 100 | Obtain EA Approval and FONSI | 35 | Duct search in AT&T service areas; Engineer at participant anchor institutions | 25 | ROW in engineering routes | 0 | Not started | 50 | Brownsville, Weslaco, and Edinburg properties | 0 | Not required | 10 | Start network build at anchor institutions | 0 | Not required | 0 | Not started | 2011-04-27 09:58 | 2011-04-27 09:58 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2011 | Q2 | Q2 - 2011 | 2926 | 3220 | FALSE | 11 | See notes below | 63 | land and buildings | Complete design of buildings in Brownsville, Weslaco and Edinburg | 100 | Final EA on 4/8/11 | 48 | Engineering validating route design | 33 | Engineering soliciting ROW permits (Rio Grande City) | 9 | Soliciting city, county, state and federal permits | 100 | complete site prep for 3 properties | 35 | Fiber is scheduled for delivery every month starting in July. Purchase is being delayed until construction is scheduled. | 0 | Awaiting Engineering completition | 0 | Awaiting building construction completition | 0 | Testing will commence as route segments are completed | 2011-08-04 16:57 | 2011-08-04 16:57 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2011 | Q3 | Q3 - 2011 | 4338 | 4025 | FALSE | 14 | See Notes Below | 24 | Land & Building | All land has been purchased. Building design is completed in Brownsville, Weslaco, & Edinburg. RFP's going to contractors for construction. | 100 | FONSI received on April 8, 2011 | 12 | Engineering validating route design | 0 | Engineering soliciting ROW Permits (Rio Grande City) | 0 | Soliciting City, County, State & Federal permits | 0 | Complete site prep for 3 properties | 52 | Fiber is scheduled for delivery every month starting in July. Purchase is being delayed until construction is scheduled. Equipment to be purchased due to longer delivery | 7 | Construction in Rio Grande City | 0 | Awaiting building construction completion | 0 | Testing will commence as route segments are completed | 2011-11-30 14:40 | 2011-11-30 14:40 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2011 | Q4 | Q4 - 2011 | 5014 | 4685 | FALSE | 43 | This includes approval of our In-Kind Contribution request of $3,168,194 (includes mainline Urban and Mainline Rural fiber network) See Infrastructure Budget Detail. | 77 | Land & Buildings | Complete design of buildings in Brownsville, Weslaco, & Edinburg & start construction | 100 | FINAL EA on April 8, 2011 | 47 | Engineering: Campuses, Capital Duct Lease, Middle mile from Brownsville-Weslaco-Hidalgo validating route design | 0 | We have received permits but there are no separate budget dollars for this line item so actuals are not reported separately. Engineering obtained ROW Permits (Rio Grande City) | 0 | We have received engineering and construction permits but there are no separate budget dollars for this line item so actuals are not reported separately. Soliciting City, County, State & Federal permits | 100 | Complete site prep for 3 properties | 92 | Equipment purchased due to longer delivery intervals. | 31 | Construction: Complete Rio Grande City Construction; Complete duct routes in Brownsville, Harlingen, Edinburg, McAllen; Complete Building Construction in Brownsville, Weslaco & Edinburg. Start construction on Brownsville-Weslaco-Hidalgo route | 0 | Contingent on building construction completion | 0 | Testing will commence as route segments are completed | 2012-02-14 18:09 | 2012-02-14 18:09 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2012 | Q1 | Q1 - 2012 | 6220 | 5712 | FALSE | 83 | This includes approval of our In-Kind Contribution request of $3,168,194 (includes mainline Urban and Mainline Rural fiber network) See Infrastructure Budget Detail | 77 | Land & Buildings | Complete construction of Brownsville, Weslaco, and Edinburg buildings | 100 | Complete | 80 | Engineering: Campuses, McAllen East and McAllen West metro routes | 0 | We have received permits but there are no separate budget dollars for this line item so actuals are not reported separately | 0 | We have received engineering and construction permits but there are no separate budget dollars for this line item so actuals are not reported separately. Soliciting City, County, State & Federal permits | 100 | Site preparation invoices charged to Land & Building budget (will correct cash allocation in next reporting period) | 100 | Equipment purchased due to longer delivery intervals | 81 | Construction: Complete duct routes in Brownsville, Harlingen, Edinburg, McAllen; complete construction on Brownsville-Weslaco-Hidalgo route, start Brownsville & Harlingen metro routes | 0 | Contingent on building construction completion | 0 | Testing will commence as route segments are completed | 2012-05-21 09:13 | 2012-05-21 09:13 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2012 | Q2 | Q2 - 2012 | 7050 | 6152 | FALSE | 89 | This projection is in line with estimated values for the PIP | 95 | Land & Building | Any remaining post-construction work for the POP buildings | 100 | N/A | 87 | Engineering P-CAI campuses | 0 | N/A | 0 | N/A | 100 | N/A | 100 | N/A | 88 | Construction of McAllen routes | 0 | N/A | 0 | N/A | 2012-08-13 17:28 | 2012-08-13 17:28 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2012 | Q3 | Q3 - 2012 | 8126 | 6770 | FALSE | 90 | This projection is in line with estimated values for the PIP | 95 | Land & Building | Any remaining post-construction work for the POP buildings | 100 | N/A | 87 | Engineering P-CAI campuses | 0 | N/A | 0 | N/A | 100 | N/A | 100 | N/A | 88 | Construction of McAllen routes | 0 | N/A | 0 | N/A | 2012-11-28 17:47 | 2012-11-28 17:47 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2012 | Q4 | Q4 - 2012 | 9086 | 7858 | FALSE | 91 | This projection is in line with estimated values for the PIP | 93 | Land & Building | Any remaining post-construction work for the POP buildings | 100 | N/A | 89 | Engineering P-CAI campuses and Edinburg routes | 0 | N/A | 0 | N/A | 100 | N/A | 100 | N/A | 91 | Construction of McAllen routes, P-CAI campuses, Edinburg route | 0 | N/A | 0 | N/A | 2013-02-28 14:43 | 2013-02-28 14:43 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2013 | Q1 | Q1 - 2013 | 9792 | 8431 | FALSE | 100 | N/A | 100 | Land & Building | Expected completion under budget | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | Expected completion slightly over budget | 100 | N/A | 100 | N/A | 2013-05-17 12:01 | 2013-05-17 12:01 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | 2013 | Q2 | Q2 - 2013 | 11282 | 9435 | FALSE | 100 | N/A | 100 | Land & Building | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 2013-11-19 08:02 | 2013-11-19 08:02 | 5762 | 5762 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570069 | 2010 | Q4 | Q4 - 2010 | 986 | 2031 | FALSE | 4 | Substantive portions contributing to overall project completion in the next reporting period consist of issuance of FONSI, Lamoni to Leon construction, release and processing of all RFPâ€™s, clearance of all Special Award Conditions, including BIP/BTOP overlap analysis, active sub recipient project planning, and mobilization efforts including equipment procurement and staging. | 0 |  | NA | 100 | Pending final approval by NTIA a FONSI should be issued by 2/1/11. | 95 | High level network design will be 100% complete and it is anticipated that substantially all of final network design will be completed prior the end of the next reporting period. | 33 | It is anticipated that Rights of Way related to Lamoni to Leon fiber build will be completed by the next reporting period. | 33 | It is anticipated that Construction Permitting related to Lamoni to Leon fiber build will be completed by the next reporting period | 0 | No variance from revised Baseline Plan | 8 | It is anticipated that equipment orders / procurement will be begin prior to the end of the upcoming reporting period. | 0 | No variance from revised Baseline Plan | 0 | Due to minor delay in RFP release Ethernet site deployment will begin towards the beginning of the Q4 reporting period. | 0 | No variance from revised Baseline Plan | 2011-02-07 11:25 | 2011-02-07 11:25 | 5888 | 5888 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2011 | Q1 | Q1 - 2011 | 1948 | 2719 | FALSE | 14 | No expected variance from baseline. | 0 |  | N/A | 100 | Completed in First quarter 2011 | 100 | The Iowa Communications Network is 100% complete on network design in | 0 | The Lamoni to Leon fiber build was removed from the project. It is not anticipated that the Sub Recipients will begin work in the next quarter. | 0 | The Lamoni to Leon fiber build was removed from the project. It is not anticipated that the Sub Recipients will begin work in the next quarter. | 3 | Varies from the infrastrucure budget page due to inclusion of EA preparation expenditures to Fuberutilities Group being classified as Site Preparation costs on SF-424. | 15 | It is expected that all equipment contracts will be awarded and the first equipment orders will be placed. | 0 | It is now expected that IRU services will not be contracted until the 3rd quarter of 2011. | 10 | It is expected that work will begin on deployment of the core electronics to the southwest quadrant of Iowa. Expenditures included with Site Preparation on SF-424 | 5 | It is expected that a portion of the core equipment installed in the next quarter will have passed operational testing. Expenditures included with Site Preparation on SF-424 | 2011-05-11 17:19 | 2011-05-11 17:19 | 5888 | 5888 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2011 | Q2 | Q2 - 2011 | 3248 | 3386 | FALSE | 8 | Variance due to Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Delays in drawing funds due to adminstrative and waiting for vendor invoicing. | 0 |  | NA | 100 | No variance from baseline | 3 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Network Design included on Site work line of Infrastructure Budget Execution Details and 424C. It is expected that engineering resources will be fully in place by mid quarter. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | NA The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 13 | Baseline shows 100. In the projections for this quarter it was expected that the approval from the Iowa Legislature to exceed the codified contract limit for the term of this project would be forth coming during the first part of the previous quarter. Legislative approval did not occur until near the end of the previous quarter. No contracts could be awarded or equipment ordered until this had occurred. This has delayed equipment procurement. Equipment procurement expected to pick up in the next quarter with the installation of the DWDM equipment to be completed around the first week of December. Invoicing of DWDM equipment will not occur until after each ring is installed per contract with vendor, this will result in % complete reporting to be behind baseline until the end of the fourth quarter 2011 and possibly into the 1st quarter of 2012, depending on how quickly we are invoiced by the vendor. DWDM equipment makes up 56% of all equipment purchases. Purchasing of edge equipment | 3 | Baseline report shows 15. Variance is due to sub-recipients still in the planning and network design phase. Sub-recipient Decorah expects to have construction RFP issued beginning of 4th quarter with construction to begin in 4th quarter of calendar year 2011. Payments for 15 year IRU's to begin this quarter as contracts are signed and we begin to turn up services. | 3 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Equipment Deployment included on Site work line of Infrastructure Budget Execution Details and 424C. ARRA Contract amendment expected to be signed with current network maintenance provider as well as contract for independent installers to be put into place. | 3 | No specific budget line for network testing. Milestone completion to be tied to site equipment deployment milestone. | 2011-08-20 09:14 | 2011-08-20 09:14 | 5888 | 5888 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2011 | Q3 | Q3 - 2011 | 4210 | 3953 | FALSE | 28 | Variance due to Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Delays in drawing funds due to adminstrative and waiting for vendor invoicing. | 0 |  | NA | 100 | No variance from baseline. | 28 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Network Design included on Site work line of Infrastructure Budget Execution Details and 424C. Engineering resources are fully in place. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | NA The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 28 | Baseline shows 100. Equipment procurement expected to pick up in the next quarter with the installation of the DWDM equipment to be completed around the first week of December. Invoicing of DWDM equipment will not occur until after each ring is installed per contract with vendor, this will result in % complete reporting to be behind baseline until the end of the fourth quarter 2011 and possibly into the 1st quarter of 2012, depending on how quickly we are invoiced by the vendor. DWDM equipment makes up 56% of all equipment purchases. Purchasing of edge equipment continues. | 5 | Baseline shows 13. Variance is due to sub-recipients still in the planning and network design phase. Sub-recipient Decorah expects to have construction RFP issued beginning of 4th quarter with construction to begin in 4th quarter of calendar year 2011. Payments for 15 year IRU's to begin 4th quarter as contracts are signed and we begin to turn up services. | 28 | Baseline shows 15. Variance from baseline due to baseline milestones being calculated on actual work done versus expenditures. | 0 | No specific budget line for network testing. Milestone completion to be tied to site equipment deployment milestone. | 2011-11-22 10:00 | 2011-11-22 10:00 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2011 | Q4 | Q4 - 2011 | 5420 | 5106 | FALSE | 58 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. | 0 |  | NA | 100 | No variance from baseline. | 58 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Network Design included on Site work line of Infrastructure Budget Execution Details and 424C. Engineering resources are fully in place. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | NA The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 85 | Baseline shows 100. The vast majority of equipment for site installations has been purchased. Remaining budget in this category is assigned to IRUs. | 50 | Baseline shows 38. Expect significant progress in IRU installations in coming quarter. | 36 | No variance from baseline. | 25 | No variance from baseline. | 2012-02-29 17:53 | 2012-02-29 17:53 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2012 | Q1 | Q1 - 2012 | 5936 | 5567 | FALSE | 62 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. | 0 |  | NA | 100 | No variance from baseline. | 62 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Network Design included on Site work line of Infrastructure Budget Execution Details and 424C. Engineering resources are fully in place. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 85 | Baseline shows 100. The vast majority of equipment for site installations has been purchased. Remaining budget in this category is assigned to IRUs. | 50 | No variance from baseline. | 47 | No variance from baseline. | 36 | No variance from baseline. | 2012-05-07 09:13 | 2012-05-07 09:13 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2012 | Q2 | Q2 - 2012 | 6854 | 6053 | FALSE | 71 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. | 0 | N/A | N/A | 100 | No variance from baseline. | 71 | Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Network Design included on Site work line of Infrastructure Budget Execution Details and 424C. Engineering resources are fully in place. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 95 | No variance from baseline. | 63 | No variance from baseline. | 60 | No variance from baseline. | 40 | No variance from baseline. | 2012-08-03 16:20 | 2012-08-03 16:20 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2012 | Q3 | Q3 - 2012 | 7956 | 6683 | FALSE | 78 | Baseline shows 95%. Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. | 0 |  | N/A | 100 | No variance from baseline. | 85 | Baseline shows 100%. Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Network Design included on Site work line of Infrastructure Budget Execution Details and 424C. Engineering resources are fully in place. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 99 | Baseline shows 100%. Variance from baseline is due to the amount of consumables yet to be purchased. | 75 | No variance from baseline. | 72 | No variance from baseline. | 60 | No variance from baseline. | 2012-11-19 12:55 | 2012-11-19 12:55 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2012 | Q4 | Q4 - 2012 | 9126 | 7907 | FALSE | 88 | Baseline shows 97%. Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. | 0 |  | N/A | 100 | No variance from baseline. | 88 | Baseline shows 100%. Variance from baseline due to baseline milestones being calculated on actual work done vs. expenditures. Expenditures for Network Design included on Site work line of Infrastructure Budget Execution Details and 424C. Engineering resources are fully in place. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 88 | Baseline shows 100%. Variance from baseline represents the IRU's that will not be completed by the end of 2013-2Q. | 83 | No variance from baseline. | 85 | No variance from baseline. | 72 | No variance from baseline. | 2013-03-06 08:43 | 2013-03-06 08:43 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2013 | Q1 | Q1 - 2013 | 9776 | 8422 | FALSE | 100 | No variance from baseline. | 0 |  | N/A | 100 | No variance from baseline. | 100 | No variance from baseline. | 0 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 0 | The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 2013-05-16 15:25 | 2013-05-16 15:25 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570069 | 2013 | Q2 | Q2 - 2013 | 11840 | 10015 | FALSE | 100 | The ICN dropped 283 total CAI's from ICN's original planned list of 3,101. A total of 2,818 CAI's were served through the project activities resulting in 95% or total funds expected to be spent. | 100 | N/A | N/A | 100 | No variance from baseline. | 100 | The ICN dropped 283 total CAI's from ICN's original planned list of 3,101. A total of 2,818 CAI's were served through the project activities resulting in 95% or total funds expected to be spent. | 100 | No separate budget for Rights of Way, percent complete to be tied to Network build milestone percent complete. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 100 | No separate budget for construction permits, milestone percent complete tied to Network build. Construction being done on sub-recipient owned property, not subject to approval by outside governing bodies. | 100 | The ICN does not have activities that meet the definition of Site Preparation per the Baseline instructions. Breakout of Site Work from the Infrastructure Budget Execution Detail page are located in EA, Network Design and Equipment Deployment. | 100 | The ICN dropped 283 total CAI's from ICN's original planned list of 3,101. This will result in total spending on equipment being $988,727 less than budgeted. | 100 | All money for IRU's budgeted in the June 2013 budget revision, AAR #2407490 was spent. | 100 | The ICN's dropped 283 total CAI's from ICN's original planned list of 3,101. This will result in total spending on equipment being $988,727 less than budgeted. | 100 | The ICN dropped 283 total CAI's from ICN's original planned list of 3,101. | 2014-02-19 12:52 | 2014-02-19 12:52 | 7309 | 7309 | Iowa Communications Network | TRUE
NT10BIX5570070 | 2010 | Q4 | Q4 - 2010 | 1010 | 2056 | FALSE | 12 | Planned expenditures for Overall Project for the upcoming quarter are on target with baseline projections. | 63 |  | Planned expenditures for Other for the upcoming quarter are expected to be 5% behind baseline projections due to prior ramp up time of the Federal Compliance Manager position through Q2. | 100 | Planned expenditures for Environmental Assessment for the upcoming quarter are on target with baseline projections. | 30 | Planned expenditures for Network Design for the upcoming quarter are expected to be on target with baseline projections. | 23 | Planned expenditures for Rights of Way for the upcoming quarter are expected to be 4% below baseline projections due to the many complicated pole attachment and conduit agreement negotiations we are involved in and the impact of weather on pole surveying. | 1 | Construction Permits for the upcoming quarter are on target with the baseline projections. | 0 | N/A | 0 | N/A | 14 | Planned expenditures for Network Build for the upcoming quarter are on target with baseline projections. | 0 | N/A | 0 | N/A | 2011-02-08 18:01 | 2011-02-08 18:01 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2011 | Q1 | Q1 - 2011 | 2274 | 2882 | FALSE | 15 | Planned expenditures for Overall Project for the upcoming quarter are 1% behind, but expected to ramp up as the Make Ready work increases to full capacity allowing construction to reach higher production rates. | 94 |  | Planned expenditures are 20% ahead of baseline projections, due to protracted negotiations in procurements and agreements, and the associated costs of legal counsel and outside consultants. | 100 | EA completed. No further expenditures planned. Compliance requirements with environmental mitigation was included in the Design Build Request For Proposal (RFP) and the Owner's Project Manager will oversee this work. | 61 | Planned expenditures are 25% ahead of baseline, but expected to even out as majority of costs will transition into Network Build category as construction approaches. | 43 | Planned expenditures for Rights of Way for the upcoming quarter are on target with baseline projections. | 5 | Planned expenditures for Construction Permits and Other Approvals for the upcoming quarter are 1% behind baseline projections, but expected to ramp up as the Make Ready Work increases to full capacity. | 0 | No expenditures planned for upcoming quarter. | 0 | No expenditures planned for upcoming quarter. | 13 | Planned expenditures for next quarter are 4% behind baseline projections, but expected to ramp up as we enter construction stage. | 0 | No expenditures planned for upcoming quarter. | 0 | No expenditures planned for upcoming quarter. | 2011-05-24 10:50 | 2011-05-24 10:50 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2011 | Q2 | Q2 - 2011 | 3120 | 3317 | FALSE | 24 | Overall project expenditures will ramp up rapidly in the next quarter due to (a) pre-payment of make-ready costs, (b) ordering of fiber and construction materials, (c) finalization of design by network segment including CAI and POI designs, and (d) start of construction. | 97 |  | Expect small increase in total percentage; outside legal and other procurement-related fees are mostly complete | 100 | EA Completed. No further expenditures planned. Compliance requirements with environmental mitigation was included in the Design Build Request For Proposal (RFP) and the Owner's Project Manager will oversee this work. | 69 | Only a 4% increase off last quarter due to costs shifting from Network Design to Rights of Way | 43 | 16% increase anticipated due to final push in field data collection and increased costs associated with make ready application fees | 29 | Expected to apply for many railroad, environmental and road permits, held because Design-Build firm required to complete construction drawings. Continue with pole applications and make-ready. | 25 | First expenditures in this category anticipated to occur along the projected baseline | 1 | Equipment design will be completed this quarter and sufficient equipment to construct a test lab is planned to be ordered. Prepayment or a deposit may be required. | 19 | Percentage may vary based on timeline for potential IRU acquisitions. Fiber deployment unlikely until the next quarter due to delivery delays and make ready lead time. | 0 | On par with baseline projection | 0 | On par with baseline projection | 2011-08-16 14:16 | 2011-08-16 14:16 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2011 | Q3 | Q3 - 2011 | 3974 | 3825 | FALSE | 37 | Ramp up activities are consistent with last quarter: overall project expenditures will continue to catch up to budgeted expectations next quarter due to (a) prepayment of make-ready costs, (b)ordering fiber and construction materials (c) finalization of design by network segment including CAI and POI designs, and (d) start of construction, | 99 |  | Expected to be ahead on percentage by 19%, however; there are no significant expenditures from this category planned next quarter which aligns with PPR projections and baseline. Costs included in the Other category are as follows: â€¢ Federal Compliance Staff related costs â€¢ BTOP Non-Construction Staffing and Other costs (i.e. NTIA Conference travel, non-construction BTOP related staff time) â€¢ Application and Post Application Submission Costs as allowed under the NOFA and included in our approved budget including staffing and professional services â€¢ Staff, Consulting and Legal Costs associated with the Network Operator Procurement | 100 | EA Completed. No further expenditures planned. Compliance requirements with environmental mitigation were included in the Design Build Request For Proposal (RFP) and the Owner's Project Manager will oversee this work. | 100 | Expected to be ahead on budgeted expenditures by 52%, due to front-loaded costs in areas of Owner, Owner's Project Manager, Design Builder and other consultants as network design progresses. Costs are now projected to be higher than were projected in original NTIA budget | 100 | Expected to be ahead on budgeted expenditures by 25%. We plan to be close to complete with all make ready and conduit applications as well as complete the majority of expenditures for the pole survey ahead of schedule | 40 | Expected to be ahead of budgeted expenditures by 3% due due make ready costs coming in higher than budgeted in baseline budget | 25 | Expected to be behind on expenditures by 25% due to the activities of this category being pushed out for scheduling reasons | 13 | Expected to continue to be on par with baseline projections | 28 | Expected to remain behind on percentage by 12%. Slower than expected Design Build ramp-up and make ready construction work by utilities have led to expectation of less expenditures to date than initially planned. Additionally, some costs included in the baseline report under this category are being captured under Network Design. | 13 | Equipment likely to be first implemented next quarter | 0 | On par with baseline projections | 2011-11-10 16:49 | 2011-11-10 16:49 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2011 | Q4 | Q4 - 2011 | 5160 | 4824 | FALSE | 55 | Expected ahead on budgeted expenditures by 3% due to anticipation of high expenditures for make ready work, which has been forecast higher than in initial baseline plan | 99 |  | Expected to be ahead on percentage by 16%, however; no significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs included in approved budget â€¢ Staff, Consulting and Legal Costs with procurements | 100 | EA Completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Expected ahead on budgeted expenditures by 43%, due to front-loaded costs in areas of Owner, Owner's Project Manager, Design Builder and other consultants. Costs are now projected to be higher than in original baseline | 100 | Expected to be ahead on budgeted expenditures by 9%. We plan to be complete with all make ready, conduit applications andpole surveying ahead of schedule | 79 | Expected to be ahead of budgeted expenditures by 26% due to the anticipation of high expenditures for make ready work costs, which has been forecast higher than in initial baseline plan | 0 | Behind on percentage by 75% due to activities now being projected to occur in Year2 Quarter4. Costs will be less than baseline projection. | 47 | Expected to be ahead on expenditures by 9% due to procurement scheduling occurring early | 31 | Expected to be behind on percentage by 21%. Slower than expected Design Build ramp-up and make ready construction work by utilities have led to less projected expenditures in quarter. Additionally, some costs of this category are being captured under Network Design. | 46 | Expected to be ahead by 8% due to equipment deployment costs starting to ramp up | 0 | On par with baseline projections | 2012-02-21 09:54 | 2012-02-21 09:54 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2012 | Q1 | Q1 - 2012 | 6036 | 5617 | FALSE | 72 | Ahead on projected expenditures by 5% due to higher than anticipated expenditures for make ready work and network design costs, both of which are higher than initial baseline plan | 100 |  | Ahead on projected expenditures by 12%; however; no significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs included in approved budget â€¢ Staff, Consulting and Legal Costs with procurements | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Ahead on projected expenditures by 33%, due to front-loaded costs in areas of Owner, Owner's Project Manager, Design Builder and other consultants. Costs are projected to be higher than original baseline | 100 | Ahead on projected expenditures by 2% due to being ahead of schedule and complete with aerial and conduit applications and pole surveying work | 100 | Ahead on projected expenditures by 32% due to higher than anticipated for make ready work costs, which has been forecast higher than in initial baseline plan | 14 | Behind on projected expenditures by 86% due to anticipated costs now forecast to be less than baseline projection, with portions captured in Network Design | 99 | Ahead on projected expenditures by 26%. Equipment and materials will be procured and paid for earlier than schedule due to industry-wide lengthened lead times on delivery. Costs are also now projected to be higher than baseline plan. | 31 | Behind on projected expenditures by 34%, due to some projected costs accounted for under Network Design. Design Build costs will continue to rise over remainder of project as construction fully ramps up | 100 | Ahead on projected expenditures by 25% due to higher equipment installation costs than in initial baseline plan. | 0 | On par with baseline and projected expenditures | 2012-05-11 10:14 | 2012-05-11 10:14 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2012 | Q2 | Q2 - 2012 | 7080 | 6167 | FALSE | 86 | Throughout this report, we are calculating Percent Complete with reference to the original NTIA budget. Costs are now projected to be higher than that original budget, and MTC has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the original NTIA budget. Tracking closely with baseline percentage as compared to original budget; ahead by 1% | 100 |  | Ahead on projected expenditures by 8%; however; no significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs â€¢ Staff, Consulting and Legal Costs with procurements | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Ahead on projected expenditures by 24%, due to front-loaded costs in areas of Owner, Owner's Project Manager, Design Builder and other consultants. | 100 | On par with baseline projections; pole surveying and make ready applications projected to fully complete | 100 | Ahead on projected expenditures by 21% due to higher than anticipated for make ready work costs than in baseline projection | 38 | Behind on projected expenditures by 62% due to costs now forecasted to be less than baseline projection, with portions captured in Network Design. MTC does not anticipate reaching 100% expenditures for this line item | 100 | Ahead on projected expenditures by 2%. Equipment and materials are being procured and paid for earlier than schedule due to industry-wide lengthened lead times on delivery. | 43 | Behind on projected expenditures by 43% due to (a) some projected costs accounted for under Network Design, (b) slower than anticipated make-ready completion by utilities has delayed crew ramp-up, and (c) certain work is delayed pending NTIA approval of Award Action Requests. | 100 | On par with baseline projections | 3 | Behind on projected expenditures by 19% due construction delays which have pushed back the anticipated start of testing | 2012-08-15 14:20 | 2012-08-15 14:20 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2012 | Q3 | Q3 - 2012 | 7962 | 6687 | FALSE | 92 | Throughout this report, we are calculating Percent Complete with reference to the original NTIA budget. Costs are now projected to be higher than that original budget, and MTC has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the original NTIA budget. Tracking closely with baseline percentage as compared to original budget; ahead by 1%. Against new budget with extra funds, expected to be at 72% complete | 100 |  | Ahead on projected expenditures by 5%; however; no significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs â€¢ Staff, Consulting and Legal Costs with procurements | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Ahead on projected expenditures by 15%, due to front-loaded costs in areas of Owner, Owner's Project Manager, Design Builder and other consultants. | 100 | On par with baseline projections; pole surveying and make ready applications projected to fully complete | 100 | Ahead on projected expenditures by 10% due to higher than anticipated for make ready work costs than in baseline projection | 41 | Behind on projected expenditures by 59% due to costs now forecasted to be less than baseline projection, with portions captured in other categories. MTC does not anticipate reaching 100% expenditures for this line item | 100 | On par with baseline projections | 54 | Behind on projected expenditures by 37% due to (a) some projected costs accounted for under other categories, (b) slower than anticipated make-ready completion by utilities has delayed crew ramp-up, and (c) schedule recovery from the delay pending NTIA approval of Award Action Requests. | 100 | On par with baseline projections | 35 | Behind on projected expenditures by 9% due to construction delays which have pushed back the anticipated progress of testing | 2012-11-19 16:55 | 2012-11-19 16:55 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2012 | Q4 | Q4 - 2012 | 9008 | 7781 | FALSE | 100 | Throughout this report, we are calculating Percent Complete with reference to the original NTIA budget. Costs are now projected to be higher than that original budget, and MTC has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the original NTIA budget. Tracking closely with baseline percentage as compared to original budget; ahead by 3%. Against new budget with extra funds, expected to be at 79% complete | 100 |  | Ahead on projected expenditures by 2%; however; no significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs â€¢ Staff, Consulting and Legal Costs with procurements | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Ahead on projected expenditures by 5%, due to front-loaded costs in areas of Owner, Owner's Project Manager, Design Builder and other consultants. | 100 | On par with baseline projections; pole surveying and make ready applications projected to fully complete | 100 | On par with baseline projections; make ready expected to conclude during quarter | 100 | On par with baseline projections, based on required improvements to Points of Interconnection buildings during installation | 100 | On par with baseline projections | 71 | Behind on projected expenditures by 25% due to (a) some projected costs accounted for under other categories, (b) slower than anticipated make-ready completion by utilities has delayed crew ramp-up, and (c) schedule recovery from the delay pending NTIA approval of Award Action Requests. | 100 | On par with baseline projections | 16 | Behind on projected expenditures by 51% due to construction delays which have pushed back the anticipated progress of testing, and the subsequent payment milestones | 2013-02-27 11:23 | 2013-02-27 11:23 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2013 | Q1 | Q1 - 2013 | 9890 | 8485 | FALSE | 100 | Throughout this report, we are calculating Percent Complete with reference to the original NTIA budget. Costs are now projected to be higher than that original budget, and MTC has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the original NTIA budget. Against new budget with extra funds, expected to be at 90% complete | 100 |  | On par with baseline percentage no significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs â€¢ Staff, Consulting and Legal Costs with procurements | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | On par with baseline percentage; costs projected to be higher than baseline budget and accounted for with additional funds from the Commonwealth of Massachusetts | 100 | On par with baseline percentage; costs projected to be higher than baseline budget and accounted for with additional funds from the Commonwealth of Massachusetts | 100 | On par with baseline percentage; costs projected to be higher than baseline budget and accounted for with additional funds from the Commonwealth of Massachusetts | 79 | Behind on projected expenditures by 21% based on work being categorized in other budget categories | 100 | On par with baseline percentage; costs projected to be higher than baseline budget and accounted for with additional funds from the Commonwealth of Massachusetts | 87 | Behind on projected expenditures by 13% due to (a) some projected costs accounted for under other categories, (b) schedule recovery from the delay pending NTIA approval of Award Action Requests. | 100 | On par with baseline percentage; costs projected to be higher than baseline budget and accounted for with additional funds from the Commonwealth of Massachusetts | 82 | Behind on projected expenditures by 18% due to construction delays which have pushed back the anticipated progress of testing, and the subsequent payment milestones | 2013-05-23 16:07 | 2013-05-23 16:07 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2013 | Q2 | Q2 - 2013 | 10780 | 9059 | FALSE | 100 | In this section, we are calculating Percent Complete with reference to the original NTIA budget. Costs are now projected to be 121% of the original budget, and MassTech has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the original NTIA budget. Against new budget with extra funds, expected to be at 95% complete | 100 |  | No significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs â€¢ Staff, Consulting and Legal Costs with procurements Costs are 131% of the baseline budget | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Costs projected to be 259% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 133% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 140% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 92 | Behind on projected expenditures by 8% based on work being categorized in other budget categories | 100 | Costs projected to be 131% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 95 | Behind on projected expenditures by 5% due to (a) some projected costs accounted for under other categories, (b) schedule recovery from the delay pending NTIA approval of Award Action Requests. | 100 | Costs projected to be 334% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 137% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 2013-08-28 09:06 | 2013-08-28 09:06 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2013 | Q3 | Q3 - 2013 | 11412 | 9524 | FALSE | 100 | In this section, we are calculating Percent Complete with reference to the original NTIA budget. Costs are now projected to be 124% of the original budget, and MassTech has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the original NTIA budget. Against new budget with extra funds, expected to be at 99% complete | 100 |  | No significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs â€¢ Staff, Consulting and Legal Costs with procurements Costs are projected to be 136% of the baseline budget | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Costs projected to be 259% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 133% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 143% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Site Preparation expected to be completed. Actual projected costs will be 101% of the baseline budget. | 100 | Costs projected to be 145% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 96 | Behind on projected expenditures by 4% due to (a) some projected costs accounted for under other categories, (b) schedule recovery from the project delays | 100 | Equipment Deployment expected to be completed. Actual costs projected to be 334% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 153% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 2013-11-26 17:25 | 2013-11-26 17:25 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | 2013 | Q4 | Q4 - 2013 | 12044 | 10203 | FALSE | 100 | In this section, we are calculating Percent Complete with reference to the original NTIA budget. Costs are now projected to be 125% of the original budget, and MassTech has secured additional non-federal funds from the Commonwealth of Massachusetts to cover those amounts that exceed the original NTIA budget. Against new budget with extra funds, expected to be at 100% complete | 100 |  | No significant expenditures planned next quarter which aligns with PPR projections and baseline. Costs include: â€¢ Federal Compliance Staff â€¢ BTOP Non-Construction Staffing â€¢ Application and Post Application Submission Costs â€¢ Staff, Consulting and Legal Costs with procurements Costs are projected to be 139% of the baseline budget | 100 | Environmental Assessment completed. No further expenditures planned. Compliance requirements with environmental mitigation included in the Design Build Request For Proposal and the Owner's Project Manager will oversee work | 100 | Costs projected to be 260% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 132% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 143% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Site Preparation expected to be completed. Actual projected costs will be 103% of the baseline budget. | 100 | Costs projected to be 145% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Network Build will be 98% of the baseline budget as some projected costs accounted for under other categories | 100 | Equipment Deployment expected to be completed. Actual costs projected to be 334% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 100 | Costs projected to be 162% of the baseline budget and are funded with additional funds from the Commonwealth of Massachusetts | 2014-04-16 14:15 | 2014-04-16 14:15 | 5934 | 5934 | Massachusetts Technology Park | TRUE
NT10BIX5570071 | 2010 | Q4 | Q4 - 2010 | 480 | 1506 | FALSE | 13 | N/A | 0 |  | N/A | 95 | N/A | 20 | N/A | 0 | N/A | 0 | N/A | 9 | N/A | 9 | N/A | 9 | N/A | 9 | N/A | 5 | N/A | 2011-01-11 19:35 | 2011-01-11 19:35 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570071 | 2011 | Q1 | Q1 - 2011 | 2362 | 2926 | FALSE | 7 | Zayo be ahead of schedule by 2.30%. This is based on us having our FONSI and being able to proceed. | 0 |  | N/A | 100 | N/A | 60 | Zayo will be ahead of schedule. This is based on us having our FONSI and being able to proceed. | 0 | N/A | 0 | N/A | 0 | N/A. | 10 | Zayo will be ahead of schedule. This is based on us having our FONSI and being able to proceed. | 0 | N/A | 10 | Zayo will be ahead of schedule. This is based on us having our FONSI and being able to proceed. | 0 | N/A. | 2011-05-26 18:45 | 2011-05-26 18:45 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570071 | 2011 | Q2 | Q2 - 2011 | 3184 | 3352 | FALSE | 17 | This is 3.9% ahead of the baseline. Which is based on resolution of the state shutdown soon and us being able to catch up with Equipment Procurement and Equipment Deployment. | 0 | N/A | N/A | 100 | This is 5% ahead of the baseline. | 70 | This is 50% ahead of the baseline. This is an estimate based on a quick resolution to the state shutdown and our engineering contractors being able to maintain the pace that they have set. | 30 | This is 30% ahead of the baseline. This is based on resolution of the state shutdown. | 30 | This is 30% ahead of the baseline. This is based on resolution of the state shutdown. | 0 | This is 9% behind the baseline and that is because of permitting and making sure that we have the official route before we do land acquisition and site preparation. | 9 | N/A | 9 | N/A | 9 | N/A | 5 | N/A | 2011-08-17 22:57 | 2011-08-17 22:57 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570071 | 2011 | Q3 | Q3 - 2011 | 4128 | 3910 | FALSE | 27 | This is 1.7% ahead of baseline. | 0 |  | This is on target with our baseline. | 100 | This is on target with our baseline. | 90 | This is 30% ahead of our baseline based on an early start. | 0 | This is on target with our baseline. | 90 | This is 30% ahead of our baseline. | 23 | This is on target with our baseline. | 81 | This is 58% ahead of our baseline. | 15 | This is 8% behind schedule because of our permitting pole attachment issues discussed in section 3 of this report. | 15 | This is 8% behind schedule because of our permitting pole attachment issues discussed in section 3 of this report. | 0 | This is 20 percent behind our baseline because of our build issues. | 2011-11-18 11:43 | 2011-11-18 11:43 | 6743 | 6743 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570072 | 2010 | Q4 | Q4 - 2010 | 1050 | 2089 | FALSE | 7 | This represents a negative variance of 3% to the Baseline. This is primarily driven by the fact that Com Net originally planned to receive shipment of a full 475,000' of Outside Plant Fiber Optic Cable and other Outside Plant materials. Given the short lead time between award of the OSP materials RFP and the start of construction, Com Net is now planning on a partial release of OSP materials including 100,000' of OSP fiber-optic cable. Furthermore, based on Com Net's decision to structure the DWDM electronics/optronics RFP to be a turn key furnish and install request, Com Net does not anticipate any cash outlay on this equipment until it is accepted which will occur in the May 2011 time frame. Com Net's administrative costs continue to run above budgeted expectation and will continue to do so throughout the project based on underestimates of time and project audit expenses | 100 | Pre-Award Acceptance | Other Baseline Items-Percent completions are: Project Management & Administration Reporting -19%, Contractual Sale of Services - 0% and Operation Support Systems - 0%. | 100 | No Variance | 17 | This represent a positive variance of seven (7) percent versus baseline. This positive variance is a carryover from the gains made in the second quarter by having the Route Design Firm pull ahead activities during the drive-out of routes for the Environmental Assessment. | 6 | A negative variance of three percent is reported as Com Net does not project to receive its FONSI until mid-February at the earliest. The finalization of certain Right-of-Way applications dependent on first completing compliance reviews against the final Environmental Assessment report. | 13 | A negative variance of three percent is reported as Com Net does not project to receive its FONSI until mid-February at the earliest. The finalization of certain Construction Permits and other Approvals are dependent on first completing a compliance reviews against the final Environmental Assessment report. | 11 | No Variance | 26 | This represents a six percent positive variance to the baseline. Com Net elected during the RFP process to structure the DWDM electronics/optronics RFP to be a turn key furnish and install request, Com Net does not anticipate any cash outlay on this equipment until it is accepted which will occur in the May 2011 time frame. The actual procurment will be completed however the cash requirement will be delayed until the 2nd quarter of 2011. Com Net also plans to make positive gains on equipment procurement by working with sub-recipient OARnet to pull ahead in-kind electronics/optronic match obligation, as well as new equipment procurement within reason.` Com Net and OARnet verified that OARnet as a state agency can purchase using State of Ohio contracts as it satisfies the procurement requirements associated with the project. | 1 | Based on full percentage point reporting no variance is visible, however Com Net originally planned to receive shipment of a full 475,000' of Outside Plant Fiber Optic Cable and other Outside Plant materials in the 1st Quarter of 2011. Given the short lead time between award of the OSP materials RFP and the start of construction, Com Net is now planning on a partial release of OSP materials including 100,000' of OSP fiber-optic cable. | 1 | This represents a 9% negative variance. Com Net elected during the RFP process to structure the DWDM electronics/optronics RFP to be a turn key furnish and install request, Com Net does not anticipate any cash outlay on this equipment until it is accepted which will occur in the May 2011 time frame. The actual work of placing the equipment on site may represent a minimum percent completion however the cash requirement will not occur until the 2nd quarter of 2011 after acceptance testing of deployed equipment is completed..` | 1 | No Variance | 2011-02-10 14:39 | 2011-02-10 14:39 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2011 | Q1 | Q1 - 2011 | 2290 | 2890 | FALSE | 11 | Negative Variance of 14% due to Com Net not yet receiving its initial FONSI and original baseline based on receipt of FONSI in early February 2011 and construction commencing by March 1, 2011. This 11% overall project completion is aggressive given that as of the date of submission Com Net had not yet received its FONSI. All projections are based on receipt of FONSI by first day of business May 2011. | 100 | PreAward Acceptance & Application | Other items included in the Baseline report included Project Management and Administration Reporting at 28% complete, Contractual Solution Sales at 3% and Operation Support Systems at 20%. | 100 | Com Net projects submitting its final EA by mid April. Com Net's projection are based on receipt of initial FONSI on the 1st day of business in May 2011 | 28 | Positive Variance of 6%. Com Net was able to ramp ahead of schedule on Route Design activities without FONSI. Com Net plans to expand and maintain design progress ahead of schedule in order to present the opportunity for timeline GAP closure against baseline on long lead time item, fiber plan construction. | 23 | Positive Variance of 2%. Most Road Right of Way applications are non-fee based. Progress in this area is primarily judged against receipt of approval on all applications for occupancy in Road Right of Way including crossing of non-navigable and navigable waterways. Com Net will attempt to balance receipt of Road Right of Way against start of construction to avoid applications and Right of Way expiring. | 6 | Negative Variance of 28%. Many permits and occupancy agreements require work to be completed within 30-120 days of issuance depending on the Authority Having Jurisdiction. Without Com Net's FONSI, tasks have been reprioritized to place priority on design and initial construction of fiber routes that do not involve largest share of RR crossing, navigable waterway crossings, pole attachments/pole make readies. This is a planned variance as part of Com Net's GAP closure measures. | 0 | Negative Variance of 42% due to Com Net not yet in receipt of its initial FONSI, therefore Com Net is placing a lower priority on Site preparation work for Telecommunications Shelter (Huts) while it focuses on the long lead time item of Outside Plant fiber construction. Com Net will place greater emphasis on Site Preparation and Hut Deployment in the 3rd and 4th Quarters of 2011 | 25 | Negative Variance of 1%. Com Net will focus on sub-recipient in-kind equipment being made part of the project on receipt of the FONSI and equipment to be deployed at existing Sites that aren't dependent on 2f above in order to close the GAP on this high value item. | 5 | Negative Variance of 6% due to Com Net not yet receiving its initial FONSI. Com Net originally planned to have crews fully ramped by mid April with significant construction progress being made for over 2/3rds of the Quarter. At this point Com Net projects not being able to begin ramping the deployment of crews on segments until early to mid-May weather permitting. Com Net will attempt to accelerate by securing leases and IRUs where planned ahead of schedule provided the facilities can be put to use. Com Net's initial focus will be on an accelerated ramp to deploy crews and on daily progress rates. This will be dependent on weather due to the fact that year to date weather conditions for outside plant construction have been less than favorable. | 13 | 35% Variance due to CNI not yet receiving FONSI and planning to refocus efforts on long lead time outside plant fiber optic cable construction on receipt of FONSI and delay equipment activities that have a shorter turn around time | 10 | 14% Variance due to CNI not yet receiving FONSI and placing initial emphasis on closing GAP associated with high dollar, long lead time outside plant fiber construction upon receipt of FONSI expected by 1st day of business in May | 2011-05-24 23:23 | 2011-05-24 23:23 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2011 | Q2 | Q2 - 2011 | 3254 | 3389 | FALSE | 16 | Negative Variance of 21% as Com Net continues to ramp efforts to close gap created by delay in ability to commence ground disturbing activities versus the assumptions included in its baseline report | 100 | Preaward Acceptance and Application | Other items included in the baseline report were Project Management and Administration Reporting projected to be at 41% versus a baseline of 38%, Contractual Solution Sales projected to be at 15% versus a baseline of 12% and Operation Support Systems at 14% versus a baseline of 67% based on deferring a decision on a platform for mapping facility assets since route design firm will retain mapping record system until completion of construction and decision to evaluate CYAN CYMS monitoring and management system capabilities before pursing a purchase of a third party Network Management System. | 100 | Initial Assessment completed with receipt of FONSI and lifting of Special Award Conditions in May 2011 | 35 | One percent positive versus baseline. Actual progress will be managed based on implementation time line requirements placed on permits and progress of construction | 33 | Negative Variance of 13% versus baseline but projecting significant progress based on implementing follow-up program with AHJs on permit status | 21 | Negative variance of 25%. Potential to exceed percentage based on financial criteria as permits for the upcoming quarter will be in the vicinity of I-75 where we will encounter more Railroad crossings and pole attachments that carry fees | 7 | Negative Variance of 34%. See comments on current quarter as this is a carry forward on a non-critical path item. Com Net is projecting to make significant progress on site preparation commencing in the Spring of 2012. The site preparation activities are short lead time and low dollar items based on the overall scope of the project. Com Net will progress the work in this area as needed to satisfy commitments with Community Anchor Institutions throughout the balance of 2011 and winter of 2012 | 29 | Negative Variance of 10%. Com Net plans to place delays in forecast of purchases with CYAN based on delays in equipment deployment as described in the current quarter progress reporting | 10 | Negative Variance of 12% projected as Com Net plans to delay purchase of fiber IRU in Columbus market by one quarter based on delay in start of construction. As mentioned in the comments associated with performance for work completed in 2011Q2, Com Net is projecting closure on the gap in network build progress by June of 2012 based on moderate-optimistic and pessimistic projections. | 6 | Negative variance of 62%. This is a carry-forward delay based on explanation provided for 2011Q2 progress reporting. Several sites scheduled for equipment deployment are dependent on the completion of fiber route construction through acceptance, which is projected to occur in September. Com Net, also, projects to complete its power audit and schedule any corrective actions in August of 2011. This will put Com Net in a position to begin deploying equipment, as well as, completing upgrades to existing leased fiber facilities. Once manufacturer personnel is deployed to the field, equipment deployment will progress in an accelerated pace to allow full gap closure against this matrix by August 2012. | 7 | Negative Variance of 30% driven by delays in equipment deployment. Majority of progress on network testing is in the area of passive facility inspection and testing. | 2011-08-22 11:09 | 2011-08-22 11:09 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2011 | Q3 | Q3 - 2011 | 4252 | 3976 | FALSE | 19 | Negative Variance of 30% versus Baseline. Com Net is projecting minimal progress during the 4th quarter of 2011 after November 23, 2011 due to holiday vacations affecting ability to obtain permits especially from villages, townships and counties due to limited staffing. Furthermore, Com Net is projecting limited progress due to moratoriums imposed by carriers and utility providers from mid-December until after the 1st of the year. Com Net projects that unliquidated obligations will increase significantly as we are unable to fully finalize items leaving them as work-in-progress rather than finished goods. | 100 | Pre-Award Acceptance and Application | Project Management and Administrative Reporting projected at 60% complete versus a baseline of 44% as Com Net plans to use November and December for budget analysis and route modification activities. Contractual Sales solutions at 12% versus baseline of 14% with community anchor institution term contract sales remaining ahead of projections but Broadband Service Provider contracts lagging behind due to delays in network builds. Operation Support System projected at 11% versus a baseline of 90% as Com Net continues to defer NISC IVUE plant and trouble module implementation, as well as, decision to defer mapping until the end of project when records are transferred from route design firm to Com Net. | 100 | Com Net projects to realize expenditure in this category as it pursues route modifications, as well as, receipt of invoices from EA consultant for EA protocols and measures. | 38 | Negative Variance of 3% versus Baseline as some of the work ahead progress is given up due to limited permitting activity expected in December of 2011 by Authorities Having Jurisdiction. | 35 | Negative Variance of 19% versus Baseline. Com Net is projecting minimal progress during the 4th quarter of 2011 after November 23, 2011 due to holiday vacations affecting ability to obtain permits especially from villages, townships and counties due to limited staffing. | 16 | Negative Variance of 30% versus Baseline. Com Net is projecting minimal progress during the 4th quarter of 2011 after November 23, 2011 due to holiday vacations affecting ability to obtain permits especially from villages, townships and counties due to limited staffing. | 13 | Negative Variance of 52% versus Baseline. Com Net is projecting to satisfy EA Area of Potential Effect concerns, as well as, site surveys and site acquisition activities. Com Net doesn't expect to see significant construction progress until after the 1st of the year. | 34 | Negative Variance of 17% versus baseline. Com Net sees the ability to increase shipment from the factory to Com Net warehouse inventory, but Com Net does not expect Cyan personnel to progress installation of equipment during the month of January so Com Net plans to continue to have inventory held at the factory. | 12 | Negative Variance of 20% versus baseline. Com Net is projecting minimal measurable progress for reporting as we are projecting that very few routes will be fully completed prior to year-end leaving a significant amount of work in progress or as unliquidated obligations. | 8 | Negative Variance of 74% versus baseline. Com Net is projecting to make progress early in the quarter but with limited progress after November 23, 2011 due to holiday vacation time and company cut-backs in travel time as year-end approaches. | 25 | Negative Variance of 23% versus baseline. Network testing will continue to lag as network build and equipment deployment lag behind baseline projections. | 2011-11-23 12:47 | 2011-11-23 12:47 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2011 | Q4 | Q4 - 2011 | 5238 | 4899 | FALSE | 29 | Negative Variance of 27% versus baseline down 3% from prior quarter variance. Com Net is projecting aggressive progress for the 2012 Winter Quarter based on favorable weather during the month of January. Com Net's projections are based on segments that have been a work-in-progress for some time, receiving the necessary authorizations to proceed to completion. Com Net is projecting that it will achieve 67% completion of the overall project by the end of the 3rd Quarter of 2012, full completion by the end of the 2nd Quarter of 2013 and that the gap between baseline and actual will not be closed until the 1st Quarter of 2013. | 100 | Pre-Award Acceptance and Application | Project Management and Administrative Reporting projected at 64% versus baseline of 53%. This gap is projected to narrow based on reduced time and expenses with legal counsel on contracts and right-of-way agreements. Contractual Sales Solutions are expected to increase as Com Net is optimistic about converting several bids submitted in December of 2011 into contracts in the 1st Quarter of 2012. This is why Com Net is projecting Contractual Sales Solution increase to 20% complete versus a baseline of 19%. Other Pre-Award Operation Support Systems are projected to show minimal progress at 12% versus baseline projections of 100%. A portion of this is based on Com Net continuing to hold on the purchase of the NISC plant and trouble management modules, as well as our planned delay in the purchasing of a mapping solutions until the end of the project when the CAD drawings will be transferred from the route design firm to Com Net. Com Net is also questioning the need for a Network | 100 | Expenditures with Environment Assessment Consultant are being tracked under Construction Permits and Other Approvals as services are requested on a per segment basis to pursue route modification or to assist in implementation of protocols and measures identified in the project FONSI. | 67 | Positive Variance versus baseline of 12%. This is as planned by Com Net as we pull-ahead design and permitting activities in preparation for an aggressive construction period from the Spring of 2012 thru the Fall of 2012. | 42 | Com Net is expecting to finalize arrangements with several Counties to allow for the direct plow method of construction. This arrangement should allow for the release of over 50 Miles of Right-of-Way in a short time frame. This backlog of right-of-way mileage, along with right-of-way applications submitted with standard lead times, should allow for a substantial amount of mileage to be released for construction by the end of the 1st Quarter of 2012. | 39 | Com Net is projecting a negative variance versus baseline of 26%. From a financial perspective, this gap is expected to close as Com Net's construction moves to more congested areas where authorities will apply more stringent requirements; therefore resulting in higher permitting fees. As Com Net approaches metropolitan areas, pole attachment applications and make ready fees will increase as the planned aerial mileage increases. Com Net will also encounter record and capacity checks as it pursues access to existing conduit routes. Com Net isn't projecting these fees to be liquidated until the 2nd and 3rd Quarters of 2012. | 11 | Projection is based on a negative variance of 62% versus baseline. Com Net will continue to progress surveying, material acquisition and negotiation of leased space during the 1st Quarter of 2012. This work will be in preparation of construction activities at Points-of-Presence Sites in the 2nd and 3rd Quarters of 2012. | 36 | Projection is based on a negative variance of 27% versus baseline. Com Net continues to reassess its plans for MPLS Network Equipment as it becomes more familiar with the capabilities of the Cyan Z-Series equipment. The capabilities of the Cyan and its ability to meet the majority of our service requirements have caused Com Net to reconsider the need for MPLS Network Equipment given its higher on-going cost of ownership. | 24 | Negative Variance of 14% versus baseline down 6% from prior quarter. Com Net views this as positive progress toward gap closure especially for winter quarter construction. | 15 | Negative Variance of 68% versus baseline. Com Net plans to continue to aggressively deploy equipment ahead of the completion of fiber segments in order to be in a position to shorten the lead time from acceptance of passive facilities to active cut over in the network. | 73 | Positive Variance versus baseline of 53% using financial measurements. This is based on Com Net's decision to increase inspection and testing in order to accept portions of segments. This is being done such that Community Anchor Institutions can be cut into service prior to completion and acceptance of an entire segment. Com Net is projecting a budget overrun for Network Testing of ~$150,000, which is less than 0.5% of the overall project budget. | 2012-02-23 18:23 | 2012-02-23 18:23 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2012 | Q1 | Q1 - 2012 | 6234 | 5719 | FALSE | 40 | Negative Variance to baseline of 28% Increase over prior quarter of 13%. Com Net projects construction progress to increase, however due to the lag in the invoicing and payment cycle, the liquidated run rate is projected to remain the same as 2012 Q1. The other factors driving the increase in the overall project progress involve the start of ground disturbing activities at two new construction point-of-presence (hut) sites and site preparation for occupancy at two new point-of-presence sites. In addition, Com Net is projecting an increase in the run rate for equipment procurement and equipment deployment through OARnet's planned receipt and partial deployment of equipment in the May-June 2012 time frame. ZAYO will be active with route design and permitting activities as it implements the ZAYO managed network build through Toledo following an acquired metro route. Com Net projects to be 64% by the end of the third quarter of 2012 and 78% complete by the end of the fourth quar | 100 | Application and Pre-Acceptance Period | Project management and admin reporting at 76%. Contract Sales continue to progress toward baseline goals at a 55% projected completion rate. Operation Support Systems at 23%. Com Net projects it will have connected 58 Community Anchor Institutions and signed agreement with 26 wholesale/last mile providers. | 100 | Initial Environmental Assessment is complete. All future services will be for route modification, which will be recorded as a construction permit and other approval expense or a construction expense depending on point of origination of change order. | 79 | Negative variance to baseline of 1%. Increase over prior quarter of 12%. See overall project narrative and planned activities for upcoming quarter. | 45 | Negative variance to baseline of 33%. Increase over prior quarter of 6%. See overall project narrative and planned activities for upcoming quarter. | 38 | Negative variance to baseline of 46%. Increase over prior quarter of 4%. See overall project narrative and planned activities for upcoming quarter. Highly dependent on invoice timing and final negotiated charges for accessing City of Perrysburg conduit over the Maumee river. | 14 | Negative variance to baseline of 74%. Increase over prior quarter of 5%. See overall project narrative and planned activities for upcoming quarter. | 59 | Negative variance to baseline of 12%. Increase over prior quarter of 20%. See overall project narrative and planned activities for upcoming quarter. | 30 | Negative variance to baseline of 25%. Increase over prior quarter of 9%. See overall project narrative and planned activities for upcoming quarter. Com Net projects to have placed 342 miles of fiber cable by the end of the 2nd Quarter of 2012. | 31 | Negative variance to baseline of 57%. Increase over prior quarter of 13%. See overall project narrative and planned activities for upcoming quarter. | 93 | Positive variance to baseline of 23%. Increase over prior quarter of 33%. See overall project narrative and planned activities for upcoming quarter. | 2012-05-21 15:50 | 2012-05-21 15:50 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2012 | Q2 | Q2 - 2012 | 6924 | 6089 | FALSE | 45 | This projection represents an 8% increase over prior quarter and a negative 31% versus baseline. | 100 | Application and Pre-Acceptance Period | Pre-Award Acceptance and Application is 100% complete from a liquidated obligations perspective, which represents a 0% variance versus baseline. Project Management and Admin Reporting is projected to be 83% complete. Contractual Sales Solutions is projected to be 60% complete, which represents a negative 3% variance to baseline. Operation Support Systems are projected to be 33% complete, which represents a 67% negative variance to baseline. | 100 | Initial Environmental Assessment is complete. All future services will be for route modification, which will be recorded as a construction permit and other approval expense or a construction expense depending on point of origination of change order. | 66 | This projection represents an 4% increase over prior quarter and a negative 25% versus baseline. | 67 | This projection represents an 13% increase over prior quarter and a negative 11% versus baseline. | 56 | This projection represents an 4% increase over prior quarter and a negative 32% versus baseline. | 28 | This projection represents an 17% increase over prior quarter and a negative 60% versus baseline. | 61 | This projection represents an 6% increase over prior quarter and a negative 22% versus baseline. | 37 | This projection represents an 8% increase over prior quarter and a negative 26% versus baseline. | 28 | This projection represents an 10% increase over prior quarter and a negative 64% versus baseline. | 100 | This projection represents an 31% increase over prior quarter and a positive 51% versus baseline. This is consistent with Com Net's project improvement plan whereby we indicated that network testing would exceed budget due to the need to test and accept partial route segments in order to satisfy Community Anchor Institution commitments. | 2012-08-08 12:21 | 2012-08-08 12:21 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2012 | Q3 | Q3 - 2012 | 7964 | 6688 | FALSE | 61 | Com Net is planning an aggressive build-out plan for the final quarter of 2012 with 15% progress over prior quarter. This plan is highly dependent on favorable weather. The aggressive plan is made possible through the additional equipment and labor available to the project through KG Myers sub-contracting efforts along with Com Net's pursuing permits and release to KG Myers on all portions of segments where the Authority Having Jurisdiction is permitting the use of direct plow installation. | 100 |  | Project Management and Administrative Reporting liquidated for a positive variance versus baseline of 7%. The 7% positive variance versus baseline is down from 8% from the prior quarter, which represents further gap closure against baseline projections. Contract Sales is projected to continue to be negatively impacted by the network build posting an 8% gain from the prior quarter for a 5% negative variance versus baseline. Operation Support progress based on liquidated expenses is projected to show no gain for the quarter. This continues to be related to two factors. The first is that Com Net did not draw federal funds for the implementation of plant and trouble on its NISC iVUE billing platform as originally planned. The reason for this was due to the fact that NISC is a cooperative and NISC was requiring additional administrative work prior to entering into a contract with Com Net. Com Net determined that the additional administrative expense negated the benefit of using | 100 | All future activity by environmental consultant shall be considered part of construction and/or as a construction permit or other approval | 86 | Com Net will continue to engage Sigma Technologies in association with route design and permitting activities on its pending route modification, as well as, to work with Authorities Having Jurisdiction to obtain outstanding permits and work through any issues that may arise in order to ensure construction crews have adequate mileage permitted for the scheduling of crews. | 72 | Com Net is projecting the spread between baseline and quarterly projections to remain the same as prior quarter with the bulk of the closure to occur in the 1st and 2nd quarter of 2013. | 64 | Permits and other approvals continue to lag behind baseline as the Authorities continue to issue permits marginally ahead of construction. This measurement against liquidated expenses, also, tends to be impacted by the fact that expenses for construction permits and other approvals continue to run favorable to budget. | 56 | Site Preparation work in the upcoming quarter is projected to be limited to outstanding invoices and clean-up work in association with the Wood County, Findlay and Huntsville new construction sites, as well as finalization of power requirements allowing for the transfer of space at Independents Fiber Networks site in Lima, OH. In addition, Com Net will be finalizing the lease of space in Springfield, OH rather than the construction of a new site moving this site to an unfunded operating expense, as well as a capital lease for space at a remote shelter in West Milton, OH. On completion of these activities, Com Net will have one new construction site remaining for completion in the spring in Greenville, OH. | 70 | Com Net's procurement of MPLS network equipment is pending a route modification, which will reduce the amount of equipment to be procured based on Com Net's election to reduce the number of MPLS Network nodes in the regional network. In addition, the acquisition of equipment for the final hut, as well as for ZAYO to equip its PoP sites on its managed routes, will not occur until the Spring of 2013. | 56 | A 31% negative variance versus baseline, but with an 18% increase over prior quarter, which represents significant progress for the final quarter of the year. This 18% increase from the prior quarter is driven by the fact that, throughout the quarter, KG Myers will have four plow trains with accompanying directional drilling crews, as well as thirteen additional directional drilling crews active on the project. Com Net has, also, secured ~7 miles of existing conduit along with an additional 7 miles of currently placed but unoccupied innerduct for the placement of cable during the quarter. ZAYO is projected to upgrade a portion of its aerial plant in the Toledo metropolitan area during the quarter. Finally, since the baseline is measured against liquidated expenses, the percent of progress will increase at a faster pace per mile of cable placed as construction costs increase with the build approaching the Metropolitan areas of Toledo, Dayton, Springfield and Columbus. | 47 | Com Net is projecting the cut-over of Cyan city-pairs during the upcoming quarter, which will move additional equipment from Work-in-Progress to the active working network. This will result in a 14% progress rate over prior quarter, but a negative variance versus budget of 53% as ZAYO is not expected to deploy its equipment until the Spring of 2013 and the deployment of equipment by OARnet during the quarter remains questionable. | 100 | As disclosed in the prior quarter projections, Com Net is experiencing an overrun in network testing/inspection costs as we release partial segments in order to allow for the activation of service to Community Anchor Institutions prior to full segment completion. The budget overrun for network testing will be offset through savings in the areas of equipment procurement and network build. | 2012-11-19 17:59 | 2012-11-19 17:59 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2012 | Q4 | Q4 - 2012 | 8828 | 7612 | FALSE | 72 | Negative 23 percent variance versus baseline. Variance is reduced by 5 percent when evaluated against CNI's forecasted project expenditure total, which is 8.77 percent under budget. | 100 | Application and Award Acceptance Period, Project Management and Project Administrative Reporting, Contract Sales and Operation Support Systems | Application and award acceptance period budget continues to be closed at one-hundred percent complete. Project Management and Administrative Reporting are expected to still run ahead of baseline primarily due to the rate of expenditure early in the project associated with reporting administration. Contractual sales will continue to lag behind with Community Anchor Institutions as we continue to work to secure commitments. Operational support systems will continue to lag behind as CNI continues to have Sigma Technologies maintain mapping records as its Route Design and Permitting Firm with final transfer to occur during the last quarter, as well as, CNI's decision not to utilize federal funds on the NISC plant and trouble module upgrade. | 100 | No Variance. | 99 | Positive 2 percent variance versus baseline. This indicates that network design and supporting permit application expenses may exceed budget by a marginal amount. This is based on route changes being requested by authorities having jurisdiction, as well as, having to address areas where underground construction is encountering rock, preventing cost effective underground construction. | 78 | Negative variance of 20 percent versus baseline. This negative variance based on liquidated expenses is partially offset by the fact that the budget category from an expense perspective is projected to come in under budget. | 70 | Negative variance of 30 percent versus baseline. This negative variance based on liquidated expenses is partially offset by the fact that the budget category from an expense perspective is projected to come in under budget | 80 | Negative variance of 20 percent versus baseline. This budget category will remain open; and therefore, behind baseline until project completion as the Greenville hut site preparation activity is not projected to conclude until the final quarter of the project. | 72 | Negative variance of 28 percent versus baseline. This negative variance will persist through the final quarter of the project as CNI's purchase and deployment of MPLS Network equipment is currently pending NTIA approval of a technology change. In addition, ZAYO has indicated it will not be installing equipment until the final quarter of the project to light the facilities in the GigE PLUS project that ZAYO will be responsible for managing. | 68 | Negative variance of 22 percent versus baseline. This variance will persist as CNI does not project completing construction activities until June 2013. | 55 | Negative variance of 55 percent versus baseline. This variance is driven by CNI's decision to hold on the cut-over of city-pairs on the Cyan DWDM equipment until the next software version is released, as well as, due to the delays in equipment procurement, upon which equipment deployment is dependent. | 100 | No variance, however this is due to unfavorable performance on expenses versus budget as this category is in an overrun state. | 2013-02-15 22:38 | 2013-02-15 22:38 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2013 | Q1 | Q1 - 2013 | 9918 | 8500 | FALSE | 84 | Negative variance of 16 percent versus baseline. This variance is driven by CNI's election not to procure and deploy MPLS network equipment until the Cyan equipped city-pairs were activated, delays in sub-recipients purchasing and deploying equipment on the facilities they will be managing and operating as part of the project, and delays associated with the outstanding route modifications. | 100 | Application and Award Acceptance Period, Project Management and Project Administrative Reporting, Contractual Sales and Operation Support Systems | No variance in the Application and Award Acceptance Period milestone as it continues to be complete at 100%. Project Management and Administrative Reporting milestone expenditures continue to run ahead of projections due to administrative costs incurred prior to ground disturbing activities commencing. Contractual Sales milestones continue to lag behind in direct relationship to construction progress as community anchor institutions continue to withhold firm order commitments. Progress on the Operational Support System milestone was closed to within seven percent of baseline in the first quarter of 2013 and is expected to hold at this level unless software or programming expenditures are required to convert CAD drawings into KML files for as-built mapping records. | 100 | No variance versus baseline for planned completion. Actual expenditures against this milestone are closed with all additional environmental assessment work associated with change orders being reported under the Construction Permits and Other Approvals milestone. Actual expenditures for this milestone ran 4 percent over budget. | 88 | Negative variance of 12 percent versus baseline. Network Design expenditures are projected to close out on this milestone slightly under budget. The route design and permitting firm continues to be engaged in establishing a design that the authority having jurisdiction will issue a permit on within the city of Columbus, city of Springfield, city of West Alexandria and Clark county. The route design and permitting firm will also have time and expense involved in finalizing the permits and construction package for two route segments included in the route modification award action request. | 90 | Negative variance of 10 percent versus baseline. The route design and permitting firm is still working to secure permits with the authority having jurisdiction of the city of Columbus, city of Springfield, city of West Alexandria and Clark county. | 73 | Negative variance of 27 percent versus baseline. The expenditures for Construction permits and other approvals are still outstanding with the environmental assessment firm, several railroad companies, pole owners and one private property owner. | 100 | No variance versus baseline. CNI is projecting aggressive progress against this milestone for the quarter. It is anticipated that although the physical work may be completed by the end of the quarter, outstanding expenditures will cause a shortfall versus planned progress for performance progress reporting purposes. | 94 | Negative variance of 6 percent versus baseline. CNI plans to procure and deploy MPLS network equipment during the 2nd quarter of 2013. Furthermore, CNI plans to increase sub-recipient monitoring activities to ensure sub-recipients are progressing with the purchase of equipment and deployment on facilities the sub-recipient will be responsible for operating and managing as part of the project. | 81 | Negative variance of 19 percent versus baseline. CNI projects to come in under budget on this milestone, however several risk areas for potential cost overruns continue to exist. The major area of concern is in association with the cost to construct the route in the city of Dayton if conduit space is not available and/or can not be secured. Progress toward this milestone is dependent on approval of the route modification by May 10, 2013 to allow adequate time to complete the route segments included in the modification. | 45 | Negative variance of 55 percent versus baseline. This is primarily driven by CNI's decision not to procure and deploy MPLS network equipment until after the Cyan DWDM equipped city-pairs are fully deployed. The other reason for the lack of progress versus the milestone is related to the procurement and deployment of equipment by the sub-recipients on facilities they will be operating and managing as part of the project. | 100 | An overrun of 82 percent is projected on liquidated expenditures with respect to this milestone. The reason for the overrun is related to the up front delay in the project before ground disturbing activities could commence. As a result of this CNI modified its plans to test and accept partial segments rather than fully completed segments, which drove-up the cost. CNI also deviated from its original plan to internalize the network testing and inspection function. This plan was abandoned due to the expertise and training requirements not being conducive to the reduced time frame for construction after receipt of the project FONSI. | 2013-05-28 09:59 | 2013-05-28 09:59 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2013 | Q2 | Q2 - 2013 | 10750 | 9040 | FALSE | 97 | Negative variance of 3 percent versus baseline. This is financial only from a liquidated expenses perspective. CNI fully anticipates completing the project based on the milestones set forth as part of the no-cost increase project extension. The overall favorable financial performance is driven through the favorable financial performance on the network build, construction permitting and network design. | 100 | Applications and Award Acceptance Period, Project Management and Project Administrative Reporting, Contract Sales and Operation Support Systems | No variance in the Application and Award Acceptance Period milestone as it continues to be complete at 100%. Project Management and Administrative Reporting milestone expenditures continue to run ahead of projections due to administrative costs incurred prior to ground disturbing activities commencing. Contractual Sales milestones are expected to be complete at 100% as community anchor institution connectivity goals are met as construction progresses to completion. In the 1stquarter of 2013 progress on the Operational Support System milestone was closed to within seven percent of baseline during the quarter with CNI executing on the purchase of the plant records module for its NISC iVUE customer care system. The liquidated expenditures for this milestone are projected to hold at this level as we do not anticipate the need for software or programming expenditures in order to convert CAD drawings into KML files for as-built mapping records. | 100 | No variance versus baseline for planned completion | 94 | Negative variance of 6 percent versus baseline. The network design milestone variance is financial only from a liquidated expenses perspective. The favorable financial performance was related to the saving in permit and right-of-way applications as well as a favorable mix of rural, urban and metropolitan route mileage. | 94 | Negative variance of 6 percent versus baseline. The variance in rights of way tracks with the variance in network design. | 82 | Negative variance of 18 percent versus baseline. CNI fully expects to complete the project. The variance is strictly financial from a liquidated expenses perspective. CNI constructed the majority of its project underground avoiding expensive make ready fees associated with pole attachments. CNI was also able to avoid the need to cross railroad tracks on private property, which dramatically reduced the cost associated with railroad crossing. | 100 | No variance versus baseline. CNI is actually projecting a slight overrun on this budget category primarily driven by costs associated with completing Area of Potential Effect (APE) studies on its prefabricated hut locations as required as part of the EA FONSI. | 100 | No variance versus baseline. CNI is actually projecting a slight overrun of 2% due to the need to secure additional rectifiers and battery back-up equipment at sites where CNI expanded its Cyan DWDM and packet metro Ethernet capabilities rather than deploying MPLS network equipment. | 95 | Negative variance of 5 percent versus baseline. This variance is strictly from a liquidated expenses perspective. Provided CNI receives approval of its route modifications by August 1, 2013 it fully anticipates completing the network build. The favorable financial performance is related to managements ability to secure approval to proceed with the preferred method of construction in areas it originally did not anticipate being able to. | 49 | Negative variance of 51 percent versus baseline. CNI will successfully complete deployment the variance versus baseline is strictly financial from a liquidated expenses perspective. This may require further analysis of professional expenses booked agains equipment procurement and network testing to determine if they should have been applied against equipment deployment as part of the project closeout. | 100 | No variance versus baseline. From a liquidated expenses perspective this category continue to run over budget based on managements decision to accept partial route segments in order to advance the objectives of the BTOP program. | 2013-08-27 06:55 | 2013-08-27 06:55 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570072 | 2013 | Q3 | Q3 - 2013 | 12062 | 10222 | FALSE | 100 | NA | 100 |  | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 2014-04-23 11:03 | 2014-04-23 11:03 | 5924 | 5924 | COM Net, Inc. | TRUE
NT10BIX5570073 | 2010 | Q4 | Q4 - 2010 | 1060 | 2096 | FALSE | 5 | N/A | 100 | Other | Award of contracts = 100%; | 100 | FONSI is expected with no major changes to design. | 100 | N/A | 88 | Anticipate to obtain more permits / franchises by end of the quarter. | 88 | Anticipate to obtain more permits / franchises by end of the quarter. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-10 16:38 | 2011-02-10 16:38 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2011 | Q1 | Q1 - 2011 | 2312 | 2901 | FALSE | 10 | Behind due to delay in obtaining FONSI. | 0 |  | At this time, no other progress milestones exist. | 100 | Delayed due to various items. We expect to receive FONSI next quarter with our team's follow-up reporting on mitigated items and requested monitoring of construction where necessary. | 5 | Network design of GePON complete. Will work with technology vendors to complete the OTN and MOE network designs. | 80 | We are progressing along with ensuring we have the necessary ROW language in place. | 80 | We are progressing along with obtainment of construction permits. Once we receive FONSI, the remaining federal agency permits should flow through. | 0 | If we are able to receive FONSI next quarter, we will start to build at least one leg depending on the attainment of the one outstanding permit. | 80 | We are receiving equipment for all the builds plus the MOE specific equipment. OTN and GePON specific technology will be ordered closer to installation. | 0 | We estimate construction will start either end of June or beginning of July. | 0 | We will install once the network is built. | 0 | This will be done in a later phase of the project. | 2011-05-25 16:50 | 2011-05-25 16:50 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2011 | Q2 | Q2 - 2011 | 3198 | 3359 | FALSE | 27 | Received FONSI and will begin construction | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Anticipate to be complete | 100 | Anticipate to be complete | 30 | We will begin construction of 3 out of the five legs and five GePON builds. | 90 | We have received all materials except for the specific technologies of OTN and GePON. | 1 | Start construction mid September | 0 | Start construction mid September | 0 | The infrastructure will not be completely constructed yet. | 2011-08-18 12:57 | 2011-08-18 12:57 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2011 | Q3 | Q3 - 2011 | 4274 | 3987 | FALSE | 40 | Based on projected dollars expended. | 0 |  | NA | 100 | Complete | 100 | Complete | 98 | One more ROW to receive from private entity for site that will be built in 2012. Anticipate completing by January 2012. | 100 | Complete | 0 | We estimate that we'll be 30% complete with construction in Q1 2012. | 80 | We will award the two remaining equipment technology in Q4 and purchase in Q12012. | 20 | We will start all our main legs by 12/1/2011. We will be back on track with our baseline in Q2 2012. | 0 | Will start in Q2 2012 and complete in Q3 2012. | 0 | The routes will not be complete until 2012. | 2011-11-25 14:44 | 2011-11-25 14:44 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2011 | Q4 | Q4 - 2011 | 5032 | 4702 | FALSE | 53 | Construction progress | 0 | 0 | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 20 | Construction in progress; target project completion Q3 2012. | 100 | Award RFPs and purchase remaining GePON and OTN equipment. | 12 | Main fiber routes construction in progress; three of five main routes will be complete. Will begin two to three GePON builds. Target project completion Q3 2012 | 0 | Main fiber routes construction in progress; three of five main routes will be complete. Will begin two to three GePON builds. Target project completion Q3 2012 | 0 | Main fiber routes construction in progress; three of five main routes will be complete. Will begin two to three GePON builds. Target project completion Q3 2012 | 2012-02-15 12:53 | 2012-02-15 12:53 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2012 | Q1 | Q1 - 2012 | 5972 | 5585 | FALSE | 70 | Four of five main routes complete and begin construction for GePONs. | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 80 | Construction in progress; target project completion Q3 2012. | 100 | Award RFPs and purchase GePON and OTN equipment. | 80 | Four of five main routes will be complete. Will complete three GePON builds. Target project completion Q3 2012 | 20 | Will complete three GePON builds. Target project completion of all main routes and GePON builds Q3 2012. | 20 | Network testing of three GePON builds. Target project completion of all main routes and GePON builds Q3 2012. | 2012-05-08 15:52 | 2012-05-08 15:52 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2012 | Q2 | Q2 - 2012 | 7038 | 6146 | FALSE | 90 | Complete except for OTN equipment installation | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 87 | All main routes and Passive Optical Networks (PONs) to be complete in Q3 except for possibly Prineville Passive Optical Network (PON) to be complete in Q4. | 87 | All main routes and Passive Optical Networks (PONs) to be complete in Q3 except for possibly Prineville Passive Optical Network (PON) to be complete in Q4. | 87 | All main routes and Passive Optical Networks (PONs) to be complete in Q3 except for possibly Prineville Passive Optical Network (PON) to be complete in Q4. | 2012-08-11 18:42 | 2012-08-11 18:42 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2012 | Q3 | Q3 - 2012 | 8066 | 6739 | FALSE | 97 | 97% budget wise; 99% complete project wise. Final make ready completion/payments | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2012-11-27 11:04 | 2012-11-27 11:04 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2012 | Q4 | Q4 - 2012 | 8708 | 7513 | FALSE | 97 | 97% budget wise; 99% project wise. Minimal construction for Community Anchor Institutions as they sign their contracts. | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-02-11 16:44 | 2013-02-11 16:44 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2013 | Q1 | Q1 - 2013 | 10010 | 8549 | FALSE | 100 | Complete | 0 |  | NA | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-05-30 14:38 | 2013-05-30 14:38 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | 2013 | Q2 | Q2 - 2013 | 11368 | 9489 | FALSE | 100 | NA | 100 |  | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 2013-11-24 19:06 | 2013-11-24 19:06 | 5904 | 5904 | Bend Cable Communications, LLC | TRUE
NT10BIX5570074 | 2010 | Q4 | Q4 - 2010 | 992 | 2034 | FALSE | 3 | Delay in submission of Environmental Assessment and consequential delay in the receipt of Finding Of No Significant Impact has caused all aspects of the project to be delayed. | 0 |  | No Variance | 100 | No Variance from Baseline | 90 | Unforeseen variables arose during the last quarter due to additional needs surrounding the Environmental Assessment. Resources that would have been used to design the network had to be pulled and used for Environmental Assessment needs which affected network design last quarter and again in this quarter. | 25 | After discussions with several of the entities involved in Rights Of Way, Contact Network Inc. now sees that Rights of Way need to be submitted on a county/service area basis. Therefore our percent complete as reported in the baseline will not be accurate based on how the Rights Of Way are currently being processed. | 25 | Unforeseen variables arose during last quarter that delayed the submittal of the Environmental Assessment. While we were able to submit before the due date, we did not submit as early as planned in the baseline, therefore the FONSI was not received as anticipated when the baseline was submitted. This caused a difference in the category again this quarter. | 15 | No Variance from Baseline | 20 | No Variance from Baseline | 1 | When Finding Of No Significant Impact is received we intend to purchase fiber. This expenditure represents the first fiber purchase assuming receipt of Finding Of No Significant Impact. | 0 | No Variance | 0 | No Variance | 2011-02-07 13:01 | 2011-02-07 13:01 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2011 | Q1 | Q1 - 2011 | 2102 | 2796 | FALSE | 6 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 0 |  | N/A | 100 | No Variance | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs are held with various utilities and permits are negotiated with various entities the network design may need to be updated/changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 15 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 7 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 12 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 11 | Since the baseline report was submitted it has become evident to Contact Network Inc. the equipment procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Due to delays in issuing the Equipment request for proposal we are behind in procurement. We will be placing equipment orders this quarter to somewhat catch up in this category versus our initial baseline projections. | 4 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 7 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 7 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 2011-05-17 17:44 | 2011-05-17 17:44 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2011 | Q2 | Q2 - 2011 | 2880 | 3197 | FALSE | 18 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No Variance | 100 | No Variance | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 17 | During this quarter a total of fifteen Community Anchor Institutions were connected to our network. The site preparation was complete for these fifteen entities. Our projects for this quarter were to connect a total of twenty-two Community Anchor Institutions. The construction and site preparation for remaining seven institutions were not complete as of June 30, 2011 causing a variance in our projections. | 35 | No Variance | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 17 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 2011-08-01 14:58 | 2011-08-01 14:58 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2011 | Q3 | Q3 - 2011 | 4122 | 3904 | FALSE | 28 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. | 0 |  | No variance from baseline. | 100 | No Variance from baseline. | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 21 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 21 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 19 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 19 | Equipment is being purchased on an as needed basis. | 29 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. | 19 | Focus will be on the Institutions that have signed contracts, site work and equipment deployment will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 19 | Focus will be on the Institutions that have signed contracts, testing will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 2011-11-17 17:27 | 2011-11-17 17:27 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2011 | Q4 | Q4 - 2011 | 5344 | 5017 | FALSE | 33 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. | 0 |  | No variance from baseline | 100 | No variance from baseline. | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 25 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 25 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 25 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 25 | Equipment is being purchased on an as needed basis. | 36 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. | 21 | Focus will be on the Institutions that have signed contracts, site work and equipment deployment will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 19 | Focus will be on the Institutions that have signed contracts, site work and equipment deployment will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 2012-02-28 13:35 | 2012-02-28 13:35 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2012 | Q1 | Q1 - 2012 | 5942 | 5570 | FALSE | 67 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. | 0 |  | No variance from baseline. | 100 | No variance from baseline | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 40 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 67 | Equipment is being purchased on an as needed basis. | 67 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. | 40 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 40 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 2012-05-07 15:04 | 2012-05-07 15:04 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2012 | Q2 | Q2 - 2012 | 7132 | 6193 | FALSE | 77 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. |  | N/A | No variance from baseline. | 100 | No variance from baseline | 90 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 84 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 84 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 56 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 67 | Equipment is being purchased on an as needed basis. | 77 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. | 56 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 56 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 2012-08-17 17:16 | 2012-08-17 17:16 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2012 | Q3 | Q3 - 2012 | 8014 | 6713 | FALSE | 94 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category is a little ahead of our initial baseline report. | 0 |  | No variance from baseline | 100 | No variance from baseline | 95 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 94 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 94 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 60 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 70 | Equipment is being purchased on an as needed basis. | 94 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category is a little ahead of our initial baseline report. | 60 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 60 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 2012-11-21 11:07 | 2012-11-21 11:07 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2012 | Q4 | Q4 - 2012 | 8848 | 7630 | FALSE | 96 | This percentage is slightly ahead of our projected baseline report | 0 |  | No variance from baseline | 100 | No variance from baseline | 97 | This percentage is slightly ahead of our projected baseline report | 94 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 92% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 94 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 92% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 63 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 59 | Equipment is being purchased on an as needed basis. | 96 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the end users for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable and vaults. While we received a few shipments of fiber during this quarter it was much less than promised. As a result the actual percent complete in this category is a little ahead of our initial baseline report. | 63 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 63 | Focus will be on the Institutions that have signed contracts, site work will commence for these entities as contracts permit, thus causing a variance from our baseline projections. | 2013-02-19 16:12 | 2013-02-19 16:12 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2013 | Q1 | Q1 - 2013 | 9840 | 8456 | FALSE | 100 | No variance from baseline | 0 |  | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2013-05-20 16:53 | 2013-05-20 16:53 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2013 | Q2 | Q2 - 2013 | 10762 | 9046 | FALSE | 100 | No variance from baseline | 0 |  | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2013-08-27 13:37 | 2013-08-27 13:37 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | 2013 | Q3 | Q3 - 2013 | 11486 | 9603 | FALSE | 100 | No variance from baseline | 0 |  | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2013-12-16 13:35 | 2013-12-16 13:35 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570075 | 2010 | Q4 | Q4 - 2010 | 1356 | 2371 | FALSE | 34 | NA | 0 |  | NA | 0 | NA | 100 | NA | 0 | NA | 0 | NA | 0 | NA | 33 | The timing of our optical equipment purchase has improved, thus the increase in this estimate over baseline. | 25 | This is a bit low due to delay in signing IRU agreement | 10 | The requirement to upgrade core routers so that the existing core routers can be deployed to the peering service has accelerated this activity over baseline. | 0 | NA | 2011-02-24 08:32 | 2011-02-24 08:32 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2011 | Q1 | Q1 - 2011 | 1974 | 2732 | FALSE | 43 | The overall project, in terms of funds spent, is lagging slightly for this particular quarter due to the length of time required to finalize major contracts, as well as the need to realign our rate of purchases so that we do not incur operations costs for facilities longer than required before they have been put in production. We are, however, making progress on improving this metric and expect to have expenditures be on plan by the end of the year. | 0 |  | NA | 0 | NA | 100 | NA | 0 | NA | 0 | NA | 0 | NA | 46 | We expect to bring this on plan by end of the year. | 70 | We expect to bring this on plan by end of the year. | 30 | We expect to bring this on plan by end of the year. | 0 | NA | 2011-05-12 14:24 | 2011-05-12 14:24 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2011 | Q2 | Q2 - 2011 | 3298 | 3411 | FALSE | 43 | The overall project is lagging slightly for this particular quarter in expenditures due to the length of time required to finalize major contracts, and the need to realign our purchase rate so that we avoid operations costs for facilities longer than required before they have been put in production. We are making progress in improving this metric and expect expenditures be on plan in the near future. | 0 |  | NA | 0 | NA | 100 | NA | 0 | NA | 0 | NA | 0 | NA | 45 | At this point the project has caught up and slightly passed the baseline. | 30 | We expect to bring this on plan by the end of the year | 44 | NA | 0 | NA | 2011-08-24 16:37 | 2011-08-24 16:37 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2011 | Q3 | Q3 - 2011 | 4180 | 3938 | FALSE | 54 | Our build-out process continues to be on schedule, even ahead of schedule. The buildout schedule includes designing and engineering the segments of the network installation, ordering equipment, receiving and testing equipment, deploying and installing equipment, and final installation testing. Approval and acceptance of all aspects of this process provides the trigger for releasing final payment to vendors. However, in an effort to make certain all of the details in all segments of the build are addressed to our satisfaction, acceptance is withheld until all questions are answered and all remedial actions taken. Payment (expenditure of project dollars) will catch up but currently lags behind the actual production due to the issues noted above. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 55 | This number is slightly behind baseline because approval and acceptance of the equipment determine when payment is made. | 70 | This metric represents the total % of IRUs paid for against the total IRU budget. All segments required for the current phase have been ordered. | 55 | This number is slightly behind baseline because approval and acceptance of the equipment determine when payment is made. Actual deployment is on schedule. | 0 | NA | 2011-11-21 14:28 | 2011-11-21 14:28 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2011 | Q4 | Q4 - 2011 | 5358 | 5026 | FALSE | 65 | Internet2 is expecting to place orders for its third phase of optical networking equipment in the 3rd Quarter of Year 2. Deployment of that equipment is expected to be largely complete by Year 2, Quarter 4, a full year ahead of the project schedule projections. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 68 | Internet2 expects to procure all remaining Phase 3 equipment in Q12012. | 95 | Network design was completed Year 1, Quarter 1. | 68 | Internet2 expects to procure all remaining Phase 3 equipment in Q12012. | 0 | NA | 2012-02-28 14:46 | 2012-02-28 14:46 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2012 | Q1 | Q1 - 2012 | 6094 | 5649 | FALSE | 81 | Internet2 expects to deploy the remaining Phase 3 equipment in Year 2, Quarter 4, nearly a year ahead of project schedule projections with the exception of the Northern Tier route and the remaining router and switch equipment. | 0 | true | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 85 | Internet2 expects to exceed the baseline for this metric in Year 2, Quarter 4. | 95 | Internet2 has completed procurements and installation is ongoing. Once installation, test, turn up, and billing are complete, this metric will catch up with the baseline. | 85 | Internet2 expects to exceed the baseline for this metric in Year 2, Quarter 4. | 0 | NA | 2012-05-15 13:29 | 2012-05-15 13:29 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2012 | Q2 | Q2 - 2012 | 7052 | 6153 | FALSE | 90 | Internet2 expects to catch up to the baseline next quarter in terms of expenditures. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 96 | Internet2 expects to exceed the baseline for this metric in Year 3, Quarter 1. | 100 | Internet2 expects to exceed the baseline for this metric in Year 3, Quarter 1. | 96 | Internet2 expects to exceed the baseline for this metric in Year 3, Quarter 1. | 0 | NA | 2012-08-14 08:15 | 2012-08-14 08:15 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2012 | Q3 | Q3 - 2012 | 8144 | 6782 | FALSE | 94 | Internet2 expects to meet the baseline for this metric. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 100 | Internet2 expects to meet the baseline for this metric. | 100 | Internet2 expects to meet the baseline for this metric. | 100 | Internet2 expects to meet the baseline for this metric. | 0 | NA | 2012-11-29 14:39 | 2012-11-29 14:39 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2012 | Q4 | Q4 - 2012 | 8978 | 7756 | FALSE | 96 | Internet2 expects to exceed the baseline for this metric in Year 3, Quarter 2. | 0 |  | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 100 | Internet2 expects to exceed the baseline for this metric in Year 3, Quarter 2. | 100 | Internet2 expects to meet the baseline for this metric in Year 3, Quarter 2. | 100 | Internet2 expects to exceed the baseline for this metric in Year 3, Quarter 2. | 0 | NA | 2013-02-26 14:21 | 2013-02-26 14:21 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2013 | Q1 | Q1 - 2013 | 9856 | 8465 | FALSE | 100 | Internet2 expects to meet the baseline for this metric. | 0 | true | NA | 0 | NA | 100 | Network design was completed Year 1, Quarter 1. | 0 | NA | 0 | NA | 0 | NA | 100 | Internet2 expects to meet the baseline for this metric. | 100 | NA | 100 | Internet2 expects to meet the baseline for this metric. | 0 | NA | 2013-05-21 17:57 | 2013-05-21 17:57 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | 2013 | Q2 | Q2 - 2013 | 12040 | 10201 | FALSE | 100 | Internet2 expects to meet the baseline for this metric. | 0 | true | NA | 0 | NA | 100 | Internet2 expects to meet the baseline for this metric. | 0 | NA | 0 | NA | 0 | NA | 100 | Internet2 expects to meet the baseline for this metric. | 100 | Internet2 expects to meet the baseline for this metric. | 100 | Internet2 expects to meet the baseline for this metric. | 0 | NA | 2014-04-15 15:39 | 2014-04-15 15:39 | 5983 | 5983 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570076 | 2010 | Q4 | Q4 - 2010 | 1300 | 2329 | FALSE | 3 | Delayed by overlap issue; working to resolve EA action items. Baseline report estimated 5%. | 0 |  | N/A | 100 | Baseline report estimated 100%. | 15 | Previously delayed by overlap issue; working to resolve EA action items. Baseline report estimated 25%. Once the FONSI is received, the schedule will be accelerated. | 0 | N/A - Project uses Public Right of Way | 25 | Previously delayed by overlap issue; working to resolve EA action items. Baseline report estimated 30%. Once the FONSI is received, the schedule will be accelerated. | 10 | Previously delayed by overlap issue; working to resolve EA action items. Baseline report estimated 20%. Once the FONSI is received, the schedule will be accelerated. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-22 14:53 | 2011-02-22 14:53 | 6614 | 6614 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2011 | Q1 | Q1 - 2011 | 2414 | 2952 | FALSE | 6 | Once the FONSI has been received, make ready work will begin and the engineering professional services will ramp up to complete the network design and move the project to the construction phase. This ramp up will bring the project closer to the original target spend and will enable the project to meet the 67% timeline after 8 quarters. Much of the project expense will come from the fiber optic cable and construction costs which will ramp up after the FONSI is received and the project moves into the construction phase. | 0 | N/A | N/A | 100 | Waiting for final approval from National Telecommunications and Information Administration (NTIA) | 19 | The project design on which an engineering firm would work could have been impacted by changes to the project implemented to mitigate environmental impacts. As a result, Sovernet decided to dedicate the time of key staff to completing work on the EA and delay completing the engineering firm RFP process. SFC has selected an engineering firm who is very familiar with our project and has extensive experience with fiber build projects. After consulting with them, we feel confident that we can proceed quickly with network design and reach our original target spend rates by the end of the first quarter of 2012. | 0 | Project uses public rights of way | 40 | SFC has made pole attachment license applications for over 5500 (20%) poles and pole surveys are ongoing. We will continue to pursue additional pole applications once the FONSI is released. SFC expect 30% of pole attachment license applications to be completed by June 2011. | 28 | Previously delayed by overlap issue; working to resolve EA action items. The completion of pole make ready work was held up pending the lifting of the EA SAC, and we do not expect any pole make ready work to be completed by the end of June 2011. | 0 | N/A | 0 | N/A | 4 | Expect to file colocation applications this quarter | 0 | N/A | 2011-05-31 17:24 | 2011-05-31 17:24 | 5890 | 5890 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2011 | Q2 | Q2 - 2011 | 3126 | 3320 | FALSE | 8 | Spending on work planned: continue core route surveying, additional make ready work; develop plans, specifications, Request For Questions's and Request For Proposal's for cable, Oust Side Plant construction, and Dense Wavelength Division Multiplexing network equipment. Much of the spending on this project will be for construction and purchase of fiber optic cable. Work on network design will set the stage for further increases in spending in coming quarters as the project moves into the construction phase. Please note that, consistent with NTIA guidance, the overall planned percent complete represents funds spent as a share of total project budget. | 0 |  | N/A | 50 | Our baseline projection stated 100% by the end of the next quarter. The projection is lower because the Finding of No Significant Impact was obtained at less than the cost budgeted. However, we may incur additional expense on the Environmental Assessment relative to archaeological work or route modifications. | 25 | Our baseline projection was 50% by the end of the next quarter. The projection is lower because network design was deferred pending issuance of the Finding of No Significant Impact and resolution of overlap issues that may have affected network design. Network design activities during the next quarter will include developing plans, specifications, RFQ's and RFP's for cable, outside plant construction and Dense Wave Division Multiplexing network equipment. | 0 | N/A | 57 | Our projected spending for the next quarter is ahead of baseline plan. Continue to survey core route and apply for pole attachment licenses. | 28 | Our baseline projection was 50% by the end of the next quarter. The projection is lower because route selection was deferred pending of resolution of overlap issues that may have affected the location of sites in need of preparation. | 1 | Our baseline projection was 20% by the end of the next quarter. The projection is lower because we deferred the selection of an engineer firm pending issuance of the Finding of No Significant Impact and resolution of overlap issues. Dense Wavelength Division Multiplexing testing equipment was ordered in June and will be received in this quarter. | 0 | The baseline projection was 30%. The projection for the next quarter is lower because route selection, network design make-ready requests were deferred pending resolution of overlap issues and issuance of the Finding of No Signficiant Impact. Sovernet Fiber Corp. does not anticipate construction spending before September 30, 2011. However, we anticipate significant spending on construction in subsequent quarters as make-ready work is completed. | 15 | Sovernet Fiber Corp. anticipates additional spending in the next quarter on colocation augments and additional colocation applications. Our baseline projection for the next quarter was 0%. | 0 | The baseline projection was 20%. The projection for the next quarter is lower because construction of the network was deferred pending resolution of overlap issues and issuance of the Finding of No Signficiant Impact. Testing will converge with our baseline projection in coming quarters as network is constructed and lit. | 2011-08-16 14:56 | 2011-08-16 14:56 | 6334 | 6334 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2011 | Q3 | Q3 - 2011 | 4148 | 3922 | FALSE | 13 | Make-ready surveys and work will continue during the quarter. Construction of 90 route miles of outside plant will begin during the quarter. Compilation of a bid package for over 200 miles of additional outside plant construction will be started this quarter. In addition, design, permitting, and make-ready that is prerequisite to further construction will continue. No CAI's will be connected during the quarter. Discussion of service arrangements between SFC and broadband wholesalers and last-mile providers will continue. In most cases, service agreements will not be entered until shortly before service can be turned up. Accordingly, no agreements are anticipated during the next quarter. | 48 | Admin & Legal Expenses |  | 46 | Additional expenses will be incurred if route modifications are proposed. | 30 | Engineering firms will continue to assist SFC with network design, route surveys and overall project management. | 0 | Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. SFC will continue to identify parcels for which rights-of-way must be obtained, and where necessary will contact property owners to obtain easements or other consents. | 80 | SFC will continue to request make-ready surveys and apply for pole attachments. Rail permits covering approximately one quarter of the project's total route miles will be submitted during the quarter. | 22 | SFC anticipates applying for attachments to roughly 5,500 utility poles -- slightly over 20% of those required for the project -- in the next quarter. The total applied for by end of quarter will be approximately 77% of those required for the project. | 2 | A primary vendor will be selected and engaged during the quarter to provide the packet optical electronic equipment for the network. RFP's will be released for routing and Operations Support Systems. | 9 | Outside plant construction activity and associated contracts is proceeding in waves, as network design is completed, permits obtained and make-ready completed. Construction of approx. 90 route miles will begin this quarter as well as the fiber service entry to a building that serves as a major network hub for an community anchor institution. We anticipate strand will be attached to poles on approximately 50 route miles by the end of the quarter. A bid package for Outside Plant Construction for over 200 miles should be approximately 80% complete by the end of the quarter. No new network miles will be leased. | 15 | SFC anticipates applying for collocations at most remaining sites during the quarter. Owners of collo sites are expected to take the full 91 days allowed under tariffs to review the applications and perform the build out of the space. Several collo projects already initiated are expected to complete. SFC will begin to install equipment in collo sites when site owners provide notices of completion. | 5 | Although no budgeted expenses fall within this reporting category, a baseline projection for Network Testing was made to reflect anticipated fiber testing and network verification. Other than pre-deployment testing of fiber delivered by vendors, network testing will follow completion of network segments, construction of which was delayed pending resolution of grant overlap issues and issuance of the Finding of No Significant Impact. | 2011-11-18 16:14 | 2011-11-18 16:14 | 6334 | 6334 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2011 | Q4 | Q4 - 2011 | 5196 | 4865 | FALSE | 24 | Overall spending should reach 24% of the award by the end of the quarter as fiber-optic cable purchases continue and outside plant construction accelerates. Construction should be complete on roughly 92 miles of outside plant. Contracts will be released and construction in progress for approximately 300 miles of outside plant. Bids requests covering as much as 486 miles of plant will be released. Primary vendors for packet optical equipment and routers will be selected during the quarter. Design and fit-up of collocation facilities will continue. SFC anticipates obtaining additional CAI service commitments, including for libraries and K-12 schools that will close their e-rate open solicitations during the quarter. | 58 | Admin & Legal |  | 74 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work that may be required is not known at present. | 49 | Engineering firms will continue to assist SFC with network design, route surveys and overall project management. | 0 | Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. SFC will continue to identify parcels for which rights-of-way must be obtained, and where necessary will contact property owners to obtain easements or other consents. | 82 | Make-ready surveys will be requested for an additional 2,300 utility poles during the quarter, bringing the total surveyed to roughly 81% of those required for completion of the project. | 32 | Winter weather conditions and shorter work days will reduce make-ready productivity. Accordingly, the pace of make-ready work and expenditures may be slower than in the previous quarter. SFC anticipates authorizing, during the quarter, make-ready work on roughly 3,600 utility poles -- slightly over 15% of those required for the project -- in the next quarter. By end of quarter, make-ready work will have been authorized for approximately 75% of those required for the project. | 16 | Equipment Procurement expenditures are presently expected to increase substantially in 2Q2012 and 3Q2012, as contracts with electronics vendors are executed and equipment ordered. An RFP for IP router equipment will be issued. Vendors will be selected and engaged during the quarter for packet optical equipment and IP routers. A portion of the packet optical network equipment will be purchased. | 19 | Assuming AAR's pending for route revisions are timely approved, the bulk of construction of the first 90 miles awarded will be completed by the end of the quarter. A contract will be entered, and construction started on the second bid package (62 miles). Overall, we estimate construction will be completed by end of quarter on 92 route miles, with strand attached on another 20 to 50 route miles. Six separate outside plant construction bid packages covering all remaining core/backbone routes as well as a large portion of lateral routes, covering over 550 route miles overall, should be released during the quarter. Bids on four of the six packages will be due during the quarter. | 6 | SFC will apply for collocations at the 6 remaining third-party sites during the quarter. We anticipate the 6 collo sites will be turned over to SFC during the quarter. | 0 | Network testing will follow completion of OSP construction. Slower-than-expected completion of make-ready has delayed completion of OSP construction. | 2012-02-22 17:34 | 2012-02-22 17:34 | 6334 | 6334 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2012 | Q1 | Q1 - 2012 | 6002 | 5600 | FALSE | 39 | Initial purchase orders for packet optical network equipment and routers will result in a signficant pick-up in spending during the quarter, as will the start of construction for several more bid packages. Overall spending should reach 38% of the award by the end of the quarter. Construction should be complete on roughly 200 miles of outside plant. Contracts will have been released for six bid packages, comprising about 750 miles of outside plant. Design and fit-up of collocation facilities will continue. SFC anticipates obtaining additional CAI service commitments. | 75 | Admin & Legal Expenses | Other expenses are expected to be roughly in line with budget. | 49 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work is not known at this time. | 60 | Engineering firms will continue to assist SFC with network design, route surveys and overall project management. Other than for any future route changes that may be proposed to NTIA, SFC expects that route surveys for the entire project will be substantially complete by the end of the quarter. | 0 | Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will continue during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 100 | Make-ready surveys will be requested for an additional 1,500 utility poles during the quarter, bringing the total requested to roughly 84% of those required for completion of project. | 46 | "Given mild Spring weather conditions and a substantial queue of pole make-ready requests pending with pole owners, SFC anticipates pole owners wil complete make-ready and issue pole attachment licenses for a substantial number of poles during the quarter. SFC anticipates authorizing, during the quarter, make-ready work on roughly 3,600 utility poles â€“ slightly over 15% of those required for the project. By end of quarter, make-ready work will have been authorized for approximately 19,500 (83)% of poles required for the project. SFC estimates pole-owners will have completed make-ready work and issued attachment licenses for roughly 12,000 poles (51%) by the end of the quarter, though not entirely in contiguous segments." | 28 | Equipment Procurement expenditures are expected to increase substantially in 2Q2012 and 3Q2012. Contracts for both packet optical and router equipment, which comprise substantially all of the budget for this category, should be executed in the quarter, with equipment purchase orders to follow shortly thereafter. | 34 | Overall, SFC estimates outside plant construction will be completed during the quarter on approximately 175 route miles, depending primarily on the extent to which make-ready is completed on contiguous runs, bringing the cumulative total to approximately 200 miles. Two additional bid packages for all remaining outside plant construction should be released during the quarter, with the goal of starting construction on one before the end of the quarter and on the other early in 3Q2012. | 39 | SFC anticipates three additional collocations will be released to SFC by the end of the quarter. | 20 | Network testing will follow completion of OSP construction. An initial network segment will likely be ready for testing during this quarter. | 2012-05-10 10:30 | 2012-05-10 10:30 | 6334 | 6334 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2012 | Q2 | Q2 - 2012 | 7242 | 6248 | FALSE | 44 | Additional purchase orders for packet optical network equipment will result in a significant pick-up in spending during the quarter, as will the start of construction for several more bid packages. Overall spending should reach 43% of the award by the end of the quarter. Construction should be complete on roughly 300 miles of outside plant, with contracts in place for all network segments. Design and fit-up of collocation facilities will continue. Packet electronic equipment, ordered late in 2Q2012, with a cost of $2.4 million, will be installed. Additional equipment orders will be placed. Packet electronic equipment will be installed and turned-up on several core network routes. SFC anticipates obtaining additional CAI service commitments. | 95 | Admin & Legal Expenses | Other expenses are expected to be roughly in line with budget. | 49 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work is not known at this time. | 78 | Engineering firms will continue to assist SFC with network design, route surveys and overall project management. Other than for any future route changes that may be proposed to NTIA, SFC route surveys for the entire project are substantially complete at the start of of the quarter. | 0 | Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will continue during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 100 | Make-ready surveys will be requested for substantially all remaining utility poles during the quarter. | 53 | SFC anticipates authorizing, during the quarter, make-ready work on roughly 2,500 utility poles. By end of quarter, make-ready work will have been authorized for approximately 20,800 (87%) (another 2,400 during quarter) of poles required for the project. SFC estimates pole-owners will have completed make-ready work and issued attachment licenses for roughly 16,500 (70%) by the end of the quarter, though not entirely in contiguous segments. | 36 | Equipment Procurement expenditures are expected to increase substantially in 3Q2012. The contract for packet optical equipment, the largest dollar equipment contract, was executed late in 2Q2012. The initial $2.4 million service order will be received during the quarter. A contract for router equipment will be entered during the quarter, and purchase orders placed. | 36 | Overall, SFC estimates approximately 200 route miles of cable will be placed during the quarter, depending primarily on the extent to which make-ready is completed on contiguous runs, bringing the cumulative total to approximately 300 route miles. | 43 | SFC anticipates three additional collocations -- all but one -- required for the project -- will be released to SFC by the end of the quarter. | 20 | Select core network routes will be tested during the quarter, once core electronic equipment is installed and continuous network routes are place. | 2012-08-24 16:01 | 2012-08-24 16:01 | 6334 | 6334 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2012 | Q3 | Q3 - 2012 | 8146 | 6783 | FALSE | 57 | Overall spending should reach 56% of the award by the end of the quarter. Construction should be complete on roughly 480 miles (cumulative) of outside plant. Additional packet optical and router equipment will be installed, tuned, tested and placed in service. SFC anticipates obtaining additional CAI service commitments. Service over the VFC network to several CAI locations will be initiated during the quarter. | 100 | Admin & Legal Expenses |  | 49 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work is not known at this time. | 92 | Engineering firms will continue to assist SFC with network design, route surveys and overall project management. Other than for any future route changes that may be proposed to NTIA, SFC expects that route surveys for the entire project are substantially complete. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will continue during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 100 | Through the preceding quarter, surveys have been requested for approximately 95% of the utility poles involved in the project. Any remaining surveys are likely to be associated with minor route or design changes. In addition, permit applications will continue to be submitted for railroad crossings, interstate highway crossings, and for work along municipal and state roadways. | 62 | Given the substantial volume of pending make-ready requests pending with pole owners, SFC anticipates pole owners will complete make-ready and issue pole attachment licenses for an additional 3,000 poles during the quarter, bringing the total to 19,500 poles (roughly 83% of those required for the project). SFC anticipates authorizing, during the quarter, make-ready work an additional 2,500 utility poles â€“ slightly over 10% of those required for the project. | 66 | During the quarter, additional DWDM nodes will be ordered and installed. Additional network segments will be lit as fiber construction is completed. IP routers are expected to be delivered, and preliminary installs started, during the quarter, with the majority of testing and turn-up occurring in 1Q2013. | 46 | Overall, SFC estimates outside plant construction will be completed during the quarter on approximately 190 route miles, depending primarily on the extent to which make-ready is completed on contiguous runs and on degree to which winter weather conditions restrict roadside construction. Construction of several core network routes should be completed during the quarter. | 47 | All but one collocation site has been licensed and fitted-up. SFC anticipates obtaining a license for the one additional collocation site during 1Q2013. | 25 | Network testing will follow completion of OSP construction. One or more network segments will likely be tested during this quarter. | 2012-11-29 14:39 | 2012-11-29 14:39 | 5928 | 5928 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2012 | Q4 | Q4 - 2012 | 8782 | 7580 | FALSE | 78 | Overall spending should reach 78% of budget by the end of the quarter. Construction should be complete on roughly 610 miles (cumulative) of outside plant. Additional packet optical and router equipment will be installed, tuned, tested and placed in service. SFC anticipates obtaining additional CAI service commitments. Service over the VFC network to additional CAI locations will be initiated during the quarter. | 100 | na | na | 49 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work is not known at this time. | 97 | Engineering firms will continue to assist SFC with network design, route surveys and overall project management. Route surveys for the entire project are substantially complete, other than for route changes that require NTIA approval. Most design work during the quarter will focus on CAI and POI entrance facilities. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will continue during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 100 | Most remaining permits, including for railroad crossings, interstate highway crossings, work along municipal and state roadways and land-use permits will be applied for during the quarter. | 73 | SFC anticipates pole owners will complete make-ready and issue pole attachment licenses for an additional 2,900 poles during the quarter, bringing the total to 21,000 poles (roughly 89% of those required for the project). SFC will submit the majority of remaining pole applications, primarily in New Hampshire, during the quarter. | 100 | Packet optical equipment will be installed and tested at two additional network notes. IP routers will be tested and turned-up during the quarter. | 59 | Overall, SFC estimates outside plant construction will be completed during the quarter on approximately 230 route miles, depending primarily on the extent to which make-ready is completed on contiguous runs and on degree to which winter weather conditions restrict roadside construction. Construction of several additional core network routes should be completed during the quarter. | 70 | The one remaining collocation site is likely to be released to SFC and fit-up during 2Q2013. | 35 | Network testing will continue to follow completion of OSP construction. | 2013-02-14 15:52 | 2013-02-14 15:52 | 5928 | 5928 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2013 | Q1 | Q1 - 2013 | 9944 | 8515 | FALSE | 83 | With approximately 13% of pole license requests still pending with pole owners at the start of the 2nd quarter, and permits needed for certain network segments, roughly 110 miles of outside plant have yet to be released to construction. Remaining routes will be released for construction as permits and pole attachment licenses allow. The volume of network miles and service locations released to construction will continue remaining pole attachment licenses and permits are obtained. 183 miles of aerial plant will be placed, leaving approximately 150 miles to place to complete the project. Electronics installation is on track for completion before outside plant construction. 30 CAI locations are scheduled be connected, with design and construction continuing on the remaining locations. | 100 | 100 | Administration of the project is in-going. | 49 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work is not known at this time. | 100 | Engineering firms will continue to assist SFC with network design, route surveys and overall project management. Route surveys for the entire project are substantially complete. Most design work during the quarter will focus on CAI and POI entrance facilities. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will continue during the quarter to identify parcels for which rights of way must be obtained, and where necessary contacted property owners to obtain easements or other consents. | 100 | Most remaining permits, including for railroad crossings, river crossings, interstate highway crossings, municipal and state roadway work permits, and land-use permits will be obtained during the quarter. | 77 | SFC had requested make-ready for over 98% of poles as the start of the quarter, and obtained licenses on 87%. SFC anticipates pole owners will complete make-ready and issue pole attachment licenses for an additional 2,300 poles during the quarter, bringing the total to 22,800 poles (roughly 97% of those required for the project). | 100 | DWDM nodes will be ordered, received and installed. | 70 | SFC estimates outside plant construction will be completed on 183 network miles, dependant on quantity of pole licenses issued by pole owners, make-ready is completion on contiguous runs, and receipt of permits. 150 miles will remain for completion of the project. | 100 | The primary activity in this category is preparation of conditioned collocation space. All collocation space has been fully prepared. | 45 | Network testing will continue to follow completion of OSP construction. | 2013-05-28 16:27 | 2013-05-28 16:27 | 5928 | 5928 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2013 | Q2 | Q2 - 2013 | 10426 | 8855 | FALSE | 95 | Delays have been stated above and in previous PPRs concerning the overall project variances. | 100 | NA | Administration of the project is ongoing. | 49 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. | 100 | Engineering firms will continue to assist SFC with network design and overall project management. Route surveys for the entire project are substantially complete. Most design work during the quarter will focus on CAI and POI entrance facilities. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will continue during the quarter to obtain easements or other consents where required. | 100 | Almost all permits, including for railroad crossings, river crossings, interstate highway crossings, municipal and state roadway work permits, and land-use permits have been obtained. The remainder are expected to be received during this quarter. | 72 | As of the start of the quarter, SFC had requested make-ready for all poles involved with the project, and obtained licenses on 94%. SFC anticipates pole owners will complete make-ready and issue pole attachment licenses for the remaining 1,360 poles. | 100 | Installation, configuration and launch of all remaining routers and DWDM nodes will be completed during the quarter. | 84 | Core and lateral outside plant will be completed during the quarter on the remaining 159 network miles, although completion requires issuance of attachment licenses issued by pole owners and on obtaining permits and property owner consents. Installation of entrances, drops and electronics for a portion of service locations will carry over into 4Q2013. 260 CAI locations should be ready for service by end of 3Q2013, and all CAI locations are projected to be ready for service by October 31, 2013. | 100 | The primary activity in this category is preparation of conditioned collocation space. All collocation space has been fully prepared. | 55 | Network testing will continue to follow completion of OSP construction. | 2013-07-30 21:15 | 2013-07-30 21:15 | 5928 | 5928 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2013 | Q3 | Q3 - 2013 | 11422 | 9532 | FALSE | 100 | The project will be completed during 4Q2013. Construction of the Vermont FiberConnect network, and installation of facilities all remaining community anchor institutions and points of interconnection will be completed. | 100 | Administration | Administration of the project is on-going, and will be completed during the quarter with the exception of award close-out. | 100 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work is not known at this time, but are likely to be insignificant given the late stage of the project. | 100 | Engineering firms will continue to assist SFC with network design and overall project management. Route surveys and network design for the entire project are substantially complete. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will obtain all remaining easements or other consents where required. | 100 | All remaining permits, including for railroad crossings, river crossings, interstate highway crossings, municipal and state roadway work permits, and land-use permits will be obtained during the quarter. | 100 | Pole owners will issue pole attachment licenses and complete make-ready for the remaining [5]% of poles. | 100 | Installation, testing and configuration of all remaining drops and entrances to anchor institutions and points of interconnection will be completed. All remaining core network segments will be lit, tested and configured. | 100 | The remaining 46 miles of aerial plant will be placed. All remaining core network segments will be lit, tested and configured, as will electronics serving the remaining CAI locations. | 100 | All remaining core network segments will be tested, configured and lit, as will be electronics to the remaining CAI locations. | 100 | Network testing is on-going, and will be completed during the quarter, as OSP construction is completed. | 2013-11-27 12:20 | 2013-11-27 12:20 | 5928 | 5928 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | 2013 | Q4 | Q4 - 2013 | 12638 | 10905 | FALSE | 99 | Construction of the remaining miles of core network routes will be completed. Most permits and land-owner access consents required for construction of the remaining 20 Points of Interconnection will be obtained. Although the network is presently carrying traffic and providing service, installation, testing and configuration of the network will continue to implement its full capabilities. | 100 | Administration | Administration of the project is on-going, and will be completed during the quarter with the exception of award close-out. | 49 | Additional expenses may be incurred as necessary if required for NTIA review of possible route modifications, or for archeological site assessments. The extent of such work is not known at this time, but are likely to be insignificant given the late stage of the project. | 100 | Engineering firms will continue to assist SFC with network design and overall project management. Route surveys and network design for the entire project are substantially complete. | 0 | N/A. Expenditures for rights of way are budgeted under Network Design, consistent with NTIA project accounting guidance. However, SFC's right of way contractor will obtain all remaining easements or other consents where required. | 100 | All remaining permits, including land-use permits and for interstate highway crossings will be obtained during the quarter. | 75 | Complete. | 100 | Installation, testing and configuration of all remaining drops and entrances to anchor institutions and points of interconnection will be completed. All remaining core network segments will be lit, tested and configured. | 83 | The remaining fiber will be placed on core network routes. All remaining core network segments will be lit, tested and configured, as will electronics serving the remaining CAI locations. | 90 | All remaining core network segments will be lit, tested and configured, as will be electronics to the remaining CAI locations. | 0 | This budget category has been included in line 2h above. Network testing continues through this period. Network testing is on-going until all construction is completed and any performance defects identified during contract close-out and testing are corrected. | 2015-01-21 14:19 | 2015-01-21 14:19 | 5928 | 5928 | Vermont Telecommunications Authority | TRUE
NT10BIX5570077 | 2010 | Q4 | Q4 - 2010 | 786 | 1823 | FALSE | 4 | No variance | 0 |  | No variance | 100 | No variance | 100 | No variance | 0 | N/A | 100 | No variance | 0 | N/A | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-01-28 15:20 | 2011-01-28 15:20 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2011 | Q1 | Q1 - 2011 | 2388 | 2939 | FALSE | 23 | Ahead of projection based on earlier construction start than anticipated. | 0 |  | N/A | 100 | NO VARIANCE | 100 | NO VARIANCE | 0 | N/A | 100 | NO VARIANCE | 0 | N/A | 10 | Ahead of the projected 0% based on the accelerated proposed schedule of the acceptable responsive bidder. | 20 | Ahead of the projected 0% based on the accelerated proposed schedule of the acceptable responsive bidder. | 0 | NO VARIANCE | 0 | NO VARIANCE | 2011-05-27 15:19 | 2011-05-27 15:19 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2011 | Q2 | Q2 - 2011 | 3212 | 3367 | FALSE | 60 | Accelerated construction by the Outside Plant Contractor | 0 |  | No variance | 100 | No variance | 100 | No variance | 0 | No variance | 100 | No variance | 0 | No variance | 10 | No variance | 80 | Accelerated construction by the Outside Plant Contractor | 0 | No variance | 0 | No variance | 2011-08-18 17:44 | 2011-08-18 17:44 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2011 | Q3 | Q3 - 2011 | 4040 | 3860 | FALSE | 83 | Accelerated construction schedule | 0 |  | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 0 | No variance | 20 | Accelerated construction schedule | 68 | Accelerated construction schedule | 20 | No variance | 20 | No variance | 2011-11-14 17:04 | 2011-11-14 17:04 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2011 | Q4 | Q4 - 2011 | 5428 | 5114 | FALSE | 86 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | Variance due to accelerated construction progress | 80 | Variance due to accelerated construction progress | 80 | Variance due to accelerated construction progress | 80 | Variance due to accelerated construction progress | 2012-03-01 09:46 | 2012-03-01 09:46 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2012 | Q1 | Q1 - 2012 | 6020 | 5609 | FALSE | 98 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 80 | Variance due to accelerated construction progress | 80 | Variance due to accelerated construction progress | 80 | Variance due to accelerated construction progress | 2012-05-10 15:08 | 2012-05-10 15:08 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2012 | Q2 | Q2 - 2012 | 6992 | 6123 | FALSE | 100 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 100 | Variance due to accelerated construction progress | 100 | Variance due to accelerated construction progress | 100 | Variance due to accelerated construction progress | 100 | Variance due to accelerated construction progress | 2012-08-09 18:31 | 2012-08-09 18:31 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2012 | Q3 | Q3 - 2012 | 8032 | 6722 | FALSE | 100 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 100 | Variance due to accelerated construction progress | 100 | Variance due to accelerated construction progress | 100 | Variance due to accelerated construction progress | 100 | Variance due to accelerated construction progress | 2012-11-26 12:10 | 2012-11-26 12:10 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | 2012 | Q4 | Q4 - 2012 | 9018 | 7791 | FALSE | 100 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-02-27 14:15 | 2013-02-27 14:15 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2010 | Q4 | Q4 - 2010 | 1322 | 2347 | FALSE | 5 | No variance | 0 |  | N/a | 100 | No variance | 100 | No variance | 0 | N/A | 100 | No variance | 0 | N/A | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-02-23 10:24 | 2011-02-23 10:24 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2011 | Q1 | Q1 - 2011 | 1760 | 2623 | FALSE | 20 | NO VARIANCE | 0 |  | N/A | 100 | NO VARIANCE | 100 | NO VARIANCE | 0 | N/A | 100 | NO VARIANCE | 0 | N/A | 0 | NO VARIANCE | 20 | Ahead of the 0% projected based on the construction contractor's accelerated schedule as planned. | 10 | Ahead of the 0% projected based on the construction contractor's accelerated schedule as planned. | 0 | NO VARIANCE | 2011-04-29 18:14 | 2011-04-29 18:14 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2011 | Q2 | Q2 - 2011 | 3214 | 3368 | FALSE | 60 | SLIGHTLY AHEAD OF SCHEDULE | 0 |  | N/A | 100 | NO VARIANCE | 100 | NO VARIANCE | 100 | NO VARIANCE | 100 | NO VARIANCE | 0 | N/A | 10 | NO VARIANCE | 20 | NO VARIANCE | 20 | NO VARIANCE | 20 | NO VARIANCE | 2011-08-18 18:10 | 2011-08-18 18:10 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2011 | Q3 | Q3 - 2011 | 4184 | 3940 | FALSE | 54 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 0 | No Variance | 10 | No Variance | 45 | Accelerated construction schedule | 20 | No Variance | 20 | No Variance | 2011-11-21 15:22 | 2011-11-21 15:22 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2011 | Q4 | Q4 - 2011 | 5350 | 5022 | FALSE | 57 | Variance is due to construction halt during winter weather and recipient budget cycle | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 10 | No Variance | 37 | Variance is due to anticipated construction progress | 0 | Variance is result of equipment procurement timeframe and, therefore, no equipment being installed | 0 | Variance is result of equipment procurement timeframe and, therefore, no equipment being installed | 2012-02-28 14:08 | 2012-02-28 14:08 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2012 | Q1 | Q1 - 2012 | 6022 | 5610 | FALSE | 61 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 75 | No Variance | 45 | No Variance | 45 | No Variance | 65 | No Variance | 2012-05-10 15:10 | 2012-05-10 15:10 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2012 | Q2 | Q2 - 2012 | 6938 | 6096 | FALSE | 91 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 80 | Variance due to construction progress and anticipation of project completion by year-end | 50 | No Variance | 50 | No Variance | 70 | Variance due to construction progress | 2012-08-08 17:04 | 2012-08-08 17:04 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2012 | Q3 | Q3 - 2012 | 8034 | 6723 | FALSE | 100 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | Variance due to accelerated construction progress | 0 | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | Variance due to accelerated construction progress | 2012-11-26 12:14 | 2012-11-26 12:14 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2012 | Q4 | Q4 - 2012 | 9132 | 7914 | FALSE | 100 | Variance due to accelerated construction progress | 0 |  | N/A | 100 | No variance | 100 | No variance | 0 | N/A | 100 | Variance due to accelerated construction progress | 0 | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | Variance due to accelerated construction progress | 2013-03-06 18:29 | 2013-03-06 18:29 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | 2013 | Q1 | Q1 - 2013 | 11432 | 9547 | FALSE | 100 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 0 | N/A | 100 | No Variance | 0 | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-12-03 11:30 | 2013-12-03 11:30 | 5935 | 5935 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570079 | 2010 | Q4 | Q4 - 2010 | 1000 | 2044 | FALSE | 10 | Consistent with Baseline | 0 | CAI Connection | Consistent with Baseline | 100 | Consistent with Baseline | 39 | Consistent with Baseline | 43 | Consistent with Baseline | 40 | Consistent with Baseline | 15 | Consistent with Baseline | 16 | Consistent with Baseline | 3 | Consistent with Baseline | 0 | Consistent with Baseline | 0 | Consistent with Baseline | 2011-02-07 19:01 | 2011-02-07 19:01 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2011 | Q1 | Q1 - 2011 | 2064 | 2777 | FALSE | 11 | Under projected 27% Baseline - delays from make-ready, anchor site changes and related design changes, and Railroad permits. However, with several concurrent phases beginning construction, will get caught up to baseline quickly over next 2 quarters. | 12 | CAI Connection | Under projected 18% Baseline - delays from make-ready, anchor site changes and related design changes, and EA review and approval. This is not based on budget but actual % of connected CAI sites. With several concurrent phases beginning construction, will get caught up to baseline quickly over next 2 quarters. | 0 | Under projected 100% baseline - percentage completed based on grant funding - EA currently funded outside of the grant so 0% grant funding completion. Actual project completion is 85% as the initial FONSI has been received. Current work is monitoring and EA amendments. Future activities may impact this funding. | 39 | Under projected 57% Baseline - delays from make-ready, anchor site changes and related design changes, and EA review and approval. However, with several concurrent phases beginning construction, will get caught up to baseline quickly over next 2 quarters. | 0 | Under projected 56% Baseline - budget for this was minimal to cover contractor processing of applications which is currently under design budget. Actual project progress is expected to be 50% complete. This will change with Award Action Request to adjust budget to recognize ROW as in-kind. This will adjust when approved to reflect change in ROW accounting. | 0 | Under projected 60% Baseline - budget for this was minimal to cover contractor processing of applications which is currently under design budget. Actual project progress is estimated to be 40% complete. This will change with Award Action Request to adjust budget to recognize ROW as in-kind and will cause break out of permitting from design budget. | 12 | Under projected 30% Baseline - delays from make-ready, anchor site changes and related design changes, and building code issues. This is not based on budget as actual site preparation of anchor sites is responsibility of CAI, this is based on the % of anchor sites expected to be connected. | 8 | Under projected 38% Baseline - delays from make-ready, anchor site changes and related design changes, and anticipated vendor delays. However, with several concurrent phases beginning construction, will get caught up to baseline quickly over next 2 quarters. Award Action Request to adjust In-Kind budget will also adjust this as anchor site equipment will no longer be counted but moved to ROW. | 8 | Under projected 16% Baseline - delays from make-ready, anchor site changes and related design changes, and anticipated vendor delays. However, with several concurrent phases beginning construction, will get caught up to baseline quickly over next 2 quarters. As a design/build project, this also includes costs of fiber which will incur large procurements over next 2 quarters. | 12 | Under projected 25% Baseline - delays from make-ready, anchor site changes and related design changes, CAI purchasing delays due to budget cuts. This is not based on budget but actual % of connected CAI sites. | 0 | Under projected 10% Baseline - delays from make-ready, anchor site changes and related design changes, and EA review and approval. | 2011-05-16 18:36 | 2011-05-16 18:36 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2011 | Q2 | Q2 - 2011 | 3106 | 3310 | FALSE | 33 | Under projected 43% baseline - due to delays from make-ready, fiber deliveries, permitting, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. | 12 | CAI Connection | Below the projected 55 of Baseline - currently waiting for FODU installation to connect CAI sites and signing of Service Agreements. Expect next quarter the CAI sites to rapidly begin connection. Once Award Action Request for route change is submitted and approved - expected next quarter - the completion of lateral connections to CAI will progress quickly. | 95 | Next quarter the Award Action Request for route change should be submitted with associated Environmental Amendment - waiting for approval. | 49 | Under projected 76% baseline - due to delays from make-ready, fiber deliveries, permitting, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. | 50 | Under projected 68% baseline - recently approved budget Award Action request for change to RoW for matching has caused change in process to recognize RoW. Accounting and approval process for RoW quickly adjusting to document RoW - will soon be at 100%. | 55 | Under projected 80% baseline - due to delays from make-ready, fiber deliveries, permitting, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. | 35 | Under projected 45% baseline - This is not based on budget as actual site preparation of anchor sites is responsibility of CAI, this is based on the % of anchor sites expected to be connected. Will quickly escalate as the FODUs are completed and CAI sign the Service Agreement. | 0 | NA | 35 | Consistent with Baseline - total 66 miles of 180 projected miles completed | 0 | NA | 0 | Should commence this next quarter as the FODU installations progress. | 2011-08-16 00:46 | 2011-08-16 00:46 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2011 | Q3 | Q3 - 2011 | 4164 | 3930 | FALSE | 46 | Under projected 56% baseline - due to delays from Portland General Electric make-ready, RoW permitting/franchising, route changes and related design changes. Current escalated construction should realign with baseline over next few quarters. | 11 | CAI Connections | Below the projected 68% of Baseline - currently waiting for Fiber Optic Distribution Units (FODU) installation to connect anchor site sites and signing of Service Level Agreements. Once Award Action Request for route change is submitted and approved - the completion of lateral connections to anchor site will progress quickly. Expect to reach baseline projections by 2012 Q1 or Q2. | 97 | The Award Action Request for route change will be submitted with associated Environmental Amendment. | 90 | Over projected 86% baseline â€“ Fiber route through Canby and Highway 26 will be resolved and the design finalized by end of Q4. | 77 | At projected 77% baseline. Project to have 2 more cities in next quarter for total of 7 of 9. | 90 | At projected 90% baseline - due to delays from city RoWâ€™s permitting/franchising. Once these issues are resolved, escalated construction should realign with baseline over next few quarters. | 85 | Over projected 70% baseline - This is not based on budget as actual site preparation of anchor sites is responsibility of anchor site, this is based on the % of anchor sites expected to be connected. Will quickly escalate as the Fiber Optic Distribution Units (FODU) are completed and anchor sites sign the Service Level Agreement. | 0 | N/A | 41 | Under projected 43% Baseline - total 75 miles of 180 projected miles completed. | 0 | N/A | 7 | Under projected 36% baseline-Two of the three Fiber Optic Distribution Units (FODU) installed and tested. Phases 1A and 2 fully tested. Once FODU is installed in Sandy, escalation of testing will realign with baseline. | 2011-11-20 17:37 | 2011-11-20 17:37 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2011 | Q4 | Q4 - 2011 | 5060 | 4730 | FALSE | 68 | Under projected 71% baseline - due to delays regarding RoW permitting/franchising, route changes and related design changes. Construction should realign with baseline over next few quarters. | 31 | CAI Connection | Under projected 82% baseline - Waiting for more signed Service Level Agreements from anchor sites. Once Award Action Request for route change is submitted and approved, the completion of lateral connections to anchor sites will progress quickly. Due to the anticipated delay of constructing the Highway 26 spur to Government Camp, we will be unable to connect the final CAI sites until Q2 2013. | 99 | An Award Action Request for route changes will be submitted with associated Environmental Amendments. Excluding the possibility of a re-route around Oregon City, all EA has been completed with the exception of the 2.3 mile section along Highway 26. | 87 | On target with projected 87% baseline â€“ Fiber route from Molalla through Oregon City will be resolved and the design finalized by end of Q2. | 78 | Under projected 82% baseline â€“ Rights of Way still need to be approved through Oregon City and Canby. We expect Rights of Way to realign with projected baseline by the end of Q2 2012 by reaching an agreement with the City of Canby. | 90 | Continue to stay on target with projected 90% baseline. | 90 | Over projected 80% baseline. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 56 | Under projected 61% Baseline â€“ total of 100 miles completed by the end of Q1 out of 180 total project miles. We expect network build to realign with projection during Q2 2012. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 41 | Under projected 52% baseline for reasons previously stated. We expect network testing to realign with projections in Q2 2013. | 2012-02-15 20:37 | 2012-02-15 20:37 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2012 | Q1 | Q1 - 2012 | 5904 | 5551 | FALSE | 79 | Under projected 82% baseline - due to delays regarding RoW permitting/franchising, route changes and related design changes. Construction should realign with baseline by end of Q3 2012. | 71 |  | Under projected 96% baseline - Waiting for more signed Service Level Agreements from anchor sites. Once Award Action Request for route change is submitted and approved, the completion of lateral connections to anchor sites will progress quickly. Due to the anticipated delay of constructing the Highway 26 spur to Government Camp, we will be unable to connect the final CAI sites until Q2 2013. | 87 | Under projected 100% baseline - With some difficulties with a couple municipalities, we are exploring a new route for phase 5. The Environmental Assessment is underway for the phase 5 route change and will accompany an Award Action Request by the end of Q3 2012. | 87 | Under projected 89% baseline â€“ Fiber route for phase 5 will be resolved and the design finalized by end of Q3 2012. We plan on submitting an Award Action Request to get approval of the final route. | 88 | Over projected 87% baseline â€“ Rights of Way still need to be approved for 2 other cities. We expect Rights of Way to realign with projected baseline by the end of Q3 2012. | 90 | Continue to stay on target with projected 90% baseline | 95 | Continue to stay on target with projected 95% baseline. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 78 | Over projected 74% Baseline â€“ total of 130 miles completed by the end of Q2 2012 out of 167 total project miles. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 61 | Under projected 68% baseline for reasons previously stated. We expect network testing to realign with projections in Q3 2013. | 2012-05-01 20:49 | 2012-05-01 20:49 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2012 | Q2 | Q2 - 2012 | 6830 | 6041 | FALSE | 93 | Meeting projected 93% baseline. | 89 |  | Under projected 100% baseline - Due to the anticipated delay of constructing the Highway 26 spur to Government Camp, we will be unable to connect the final CAI sites until Q2 2013. | 100 | Complete | 97 | Over projected 95% baseline. All phases will be designed with the exception of the 4 miles for the Portland General Electric relocation project located on Mt Hood. | 89 | Under projected 94% baseline â€“ Rights of Way still need to be approved for 2 other cities. We expect Rights of Way to realign with projected baseline by the end of Q4 2012. | 98 | Continue to stay on target with projected 98% baseline. | 100 | Complete | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 95 | Over projected 87% Baseline â€“ total of 158 miles completed by the end of Q3 2012 out of 167 total project miles. | 0 | N/A - Award Action Request approved to remove equipment as matching component, so site equipment is not part of grant. | 93 | Over projected 84% baseline. | 2012-08-01 17:10 | 2012-08-01 17:10 | 5569 | 5569 | Clackamas, County of | TRUE
NT10BIX5570079 | 2012 | Q3 | Q3 - 2012 | 7894 | 6651 | FALSE | 95 | Under projected 99% baseline. | 98 |  | Under projected 100% baseline - Due to the anticipated delay of constructing the Highway 26 spur to Government Camp, we will be unable to connect the final CAI sites until Q2 2013. | 100 | Complete. | 100 | Design will be complete. | 78 | Under projected 100% baseline â€“ Rights of Way still need to be approved for 2 other cities. We expect Rights of Way to realign with projected baseline by the end of Q4 2012. | 100 | Complete. | 100 | Complete. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 98 | Under projected 100% Baseline â€“ total of 165 miles completed by the end of Q4 2012 out of 169 total project miles. The last 4 miles will be complete when Portland General Electric finishes their reliability project on Highway 26 to Government Camp. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 98 | Under projected 100% baseline. Once Portland General Electric finishes their work on HWY 26, we can then install the last 4 miles of the network and test the Government Camp spur. This will complete the testing of the network. We expect the final testing to be complete by the end of Q2 2013. | 2012-11-15 10:31 | 2012-11-15 10:31 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2012 | Q4 | Q4 - 2012 | 8894 | 7682 | FALSE | 97 | Under projected 100% baseline. The project will not realign with baseline until Q2 2013. | 98 | Anchor Site Connection | Under projected 100% baseline - Due to the anticipated delay of constructing the Highway 26 spur to Government Camp, we will be unable to connect the final CAI sites until Q2 2013. | 100 | Complete | 98 | Under projected 100% baseline. The project will realign with baseline once PGE finalizes the design on HWY 26. | 78 | Under projected 100% baseline â€“ Rights of Way still need to be approved for 2 other cities. We expect Rights of Way to realign with projected baseline by the end of Q2 2013. | 99 | The permitting will realign with baseline when PGE finalizes their design for HWY 26. | 100 | Complete | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 98 | Under projected 100% Baseline â€“The last 5 miles will be complete by the end of Q2 2013. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 98 | Under projected 100% baseline. Once Portland General Electric finishes their work on HWY 26, we can then install the last 4 miles of the network and test the Government Camp spur. This will complete the testing of the network. We expect the final testing to be complete by the end of Q2 2013. | 2013-02-21 20:17 | 2013-02-21 20:17 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2013 | Q1 | Q1 - 2013 | 9854 | 8464 | FALSE | 100 | Project complete. Project completion is actually 101%, but we can only enter up to 100% in the box. We are at 101% because we have booked an additional $134,556 in in-kind match. | 100 |  | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 100 | Project complete. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 100 | Project complete. | 2013-05-21 17:44 | 2013-05-21 17:44 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2013 | Q2 | Q2 - 2013 | 10682 | 9002 | FALSE | 100 | Project complete. Project completion is actually 101%, but we can only enter up to 100% in the box. We are at 101% because we have booked an additional $134,556 in in-kind match. | 100 |  | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 100 | Project complete. | 0 | N/A - AAR approved to remove equipment as matching component, so site equipment is not part of grant. | 100 | Project complete. | 2013-08-21 15:17 | 2013-08-21 15:17 | 5568 | 5568 | Clackamas, County of | TRUE
NT10BIX5570079 | 2013 | Q3 | Q3 - 2013 | 11946 | 10111 | FALSE | 100 | N/A. Project is complete. | 100 | N/A | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 100 | N/A. Project is complete. | 2014-03-13 10:03 | 2014-03-13 10:03 | 5569 | 5569 | Clackamas, County of | TRUE
NT10BIX5570080 | 2010 | Q4 | Q4 - 2010 | 1250 | 2280 | FALSE | 30 | No Deviation from the Baseline | 0 |  | No Deviation from the Baseline | 100 | No Deviation from the Baseline | 100 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 2011-02-20 21:39 | 2011-02-20 21:39 | 6335 | 6335 | ONWAV INC. | TRUE
NT10BIX5570080 | 2011 | Q1 | Q1 - 2011 | 2242 | 2866 | FALSE | 11 | Due to the delay in receipt of a FONSI, OnWav's will still be not have been able to begin and expend funds related to components of the deployment which have the FONSI as a prerequisite until more than half way through the quarter. | 26 | OSS-BSS Support | No Deviation from the Baseline | 100 | No Deviation from the Baseline | 100 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 6 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 0 | No Deviation from the Baseline | 2011-05-23 10:11 | 2011-05-23 10:11 | 6335 | 6335 | ONWAV INC. | TRUE
NT10BIX5570080 | 2011 | Q2 | Q2 - 2011 | 3236 | 3380 | FALSE | 12 | Due to the delay in receipt of a FONSI, OnWav will need to rush to finalize work and contracts to expend funds and begin deployment. OnWav is revising its budget and plan in order to facilitate a faster deployment and funds expenditure. | 0 | BSS-OSS | OnWav's plans for BSS and OSS systems have been demporarily put on hold pending the 3rd party match support. OnWav is working on a plan which will not only bring progress on this category back to schedule, but complete it early. In the meantime, progress will be slow until the new plan can be implemented. OnWav hopes to have this resolved by the end of 2011 if not sooner. | 100 | No Deviation from the Baseline | 100 | No Deviation from the Baseline | 0 | OnWav is expecting to experience some delays in this category due to a technology change facilitated by a new relationship with a 3rd party. Once this is complete, OnWav plans to aggressively move forward with deployment. The technology change itself will not impact this category, however the planning associated with it needs to be complete prior to begin. OnWav does not expect delays to last longer than 1 quarter. | 6 | OnWav is expecting to experience some delays in this category due to a technology change facilitated by a new relationship with a 3rd party. Once this is complete, OnWav plans to aggressively move forward with deployment. The technology change itself will not impact this category, however the planning associated with it needs to be complete prior to begin. OnWav does not expect delays to last longer than 1 quarter. | 0 | No deviation from the baseline next quarer. OnWav is still intending to being work on this milestone in late 2011. Some of the delay in getting environmental clearance, as well as the 3rd party match funding may propogate to delay this milestone, but OnWav is making efforts to mitigate that risk. | 0 | No deviation from the baseline next quarer. OnWav is still intending to being work on this milestone in late 2011. Some of the delay in getting environmental clearance, as well as the 3rd party match funding may propogate to delay this milestone, but OnWav is making efforts to mitigate that risk. | 0 | No Deviation from the Baseline | 0 | No deviation from the baseline next quarer. OnWav is still intending to being work on this milestone in late 2011. Some of the delay in getting environmental clearance, as well as the 3rd party match funding may propogate to delay this milestone, but OnWav is making efforts to mitigate that risk. | 0 | No Deviation from the Baseline | 2011-08-19 14:10 | 2011-08-19 14:10 | 6335 | 6335 | ONWAV INC. | TRUE
NT10BIX5570080 | 2011 | Q3 | Q3 - 2011 | 4292 | 3996 | FALSE | 53 | OnWav plans to have completed the entire matching contribution, as well as begun funding many of the more expensive components of its network deployment. | 100 | BSS-OSS | OnWav's plans for BSS and OSS systems were temporarily put on hold pending the 3rd party match support and the pending change in ownership. OnWav has a plan which will not only bring progress on this category back to schedule, but complete it early. OnWav hopes to have this resolved by the end of the next quarter. | 100 | No Deviation from the Baseline | 100 | OnWav anticipates having hired an RF Engineering firm which will have completed work finalizing OnWav's network design based on a newly chosen equipment vendor. | 100 | OnWav anticipates having completed all necessary leasing and land acquisition related to the new towers and collocation sites. | 50 | OnWav anticipates making substantial progress on this category. However, many of the necessary steps may required extensive time durations, and so OnWav will be working to catch up, but may not be successful. This work has been delayed by the process of getting the initial FONSI as well as the delays resulting from the pending change in ownership | 10 | OnWav anticipates beginning work on new tower construction, however only a small portion of the total cost of the tower construction is expected to be paid upfront. There will be substantial opportunity for OnWav to exceed this goal and OnWav will take advantage of that if possible. | 25 | OnWav anticipates choosing an Equipment vendor and making an initial order. While most equipment will not arrive before the end of the next quarter, OnWav anticipates accepting delivery of some equipment immediately, and placing deposits on other orders. | 100 | OnWav anticipates completing acquisition of 100% of IRUs planned for in the network. | 0 | No deviation from the baseline next quarter. OnWav may be able to deploy a very small portion of equipment next quarter, however the majority will not be available for deployment until next year. Some of the delay in getting the 3rd party match funding has propagated to delay this milestone, but OnWav is has made efforts to minimize that effect. | 0 | No Deviation from the Baseline | 2011-11-28 16:41 | 2011-11-28 16:41 | 6335 | 6335 | ONWAV INC. | TRUE
NT10BIX5570080 | 2011 | Q4 | Q4 - 2011 | 5126 | 4792 | FALSE | 54 | OnWav's progress in early 2012 will revolve predominantly around completion of the awarding of the Equipment and Tower construction RFPs and initial work on those fronts. OnWav anticipates that it will be back on schedule in early 3rd Quarter 2012 | 100 | BSS-OSS | OnWav's plans for BSS and OSS systems are pending finalization based on the Equipment Contract award. However, once this is complete, OnWav expects it will not only bring progress on this category back to schedule, but complete it early. | 100 | OnWav's Environmental assessment is complete, however OnWav will be conducting additional environmental work to create an EA amendment covering the additional work related to the planned fiber network. | 100 | OnWav has hired an RF Engineering firm which will be able to complete work finalizing OnWav's network design based on chosen equipment vendor's offering. | 100 | No Variance from baseline | 50 | OnWav anticipates making progress in this category. However, this is dependent on the timing of the award of the tower construction RFP and the completion of the necessary engineering work. | 50 | OnWav anticipates awarding the tower construction RFP as well as completing the engineering work for the new towers. As a result, OnWav should be able to begin work related to site preparation for the new towers. | 25 | OnWav anticipates choosing an Equipment vendor and making an initial order. While most equipment will not arrive before the end of the next quarter, OnWav anticipates accepting delivery of some equipment immediately, and placing deposits on other orders. | 99 | The final portions of the fiber network build will not be finalized until tower construction and site leasing is complete so that all portions of fiber can be constructed and deployed. | 0 | OnWav will deploy a very small portion of equipment next quarter, predominately related to the fiber network and the portion for which the IRU was recently signed. However the majority will not be available for deployment until the equipment vendor is chosen and new equipment arrives, which is likely to be delayed until next quarter. | 0 | No Deviation from the Baseline | 2012-02-17 18:04 | 2012-02-17 18:04 | 6335 | 6335 | ONWAV INC. | TRUE
NT10BIX5570080 | 2012 | Q1 | Q1 - 2012 | 5968 | 5583 | FALSE | 62 | OnWav's progress in Q2 2012 will revolve predominantly around completion of contracts and beginning of work related to Equipment and Tower construction contracts, including the installation of the first site and initial customers. OnWav anticipates that it will be back on schedule in early 3rd Quarter 2012 | 100 | BSS-OSS | OnWav's plans for BSS and OSS systems are pending finalization based on the Equipment Contract award. However, once this is complete, OnWav expects it will not only bring progress on this category back to schedule, but complete it entirely. | 100 | OnWav's Environmental assessment is complete, however OnWav will be conducting additional environmental work to create an EA amendment covering the additional work related to the planned fiber network. OnWav expects to receive the SHPO and FWS concurrences, and submit the EA-Amendment to NTIA in Q2 2012. | 100 | OnWav has hired an RF Engineering firm which will be able to complete work finalizing OnWav's network design based on chosen equipment vendor's offering. | 100 | No Variance from baseline | 50 | OnWav anticipates making progress in this category. However, this is dependent on the timing of the signing of the tower construction contract and the completion of the necessary engineering work. | 50 | OnWav anticipates signing the tower construction Contract as well as completing the engineering work for the new towers. As a result, OnWav should be able to begin work related to site preparation for the new towers. | 25 | OnWav anticipates signing an Equipment contract and making an initial order. OnWav has already arranged with the vendor for the initial equipment and initial site installation to be entirely completed in the next quarter. | 99 | The final portions of the fiber network build will not be finalized until environmental clearance is received. | 15 | OnWav anticipates having the first RAN site up and running with customers active. | 0 | No Deviation from the Baseline | 2012-05-08 14:25 | 2012-05-08 14:25 | 6335 | 6335 | ONWAV INC. | TRUE
NT10BIX5570080 | 2012 | Q2 | Q2 - 2012 | 7070 | 6162 | FALSE | 78 | OnWav expects to show significant progress on this project during the next quarter. OnWav's equipment has already mostly arrived, and should be invoiced soon. Tower construction is expected to make considerable progress on Towers in late Q3. The first two collocation sites should be completed. | 100 | BSS/OSS | OnWav expects to have the final remaining piece of equipment for the BSS/OSS system installed and operating by the end of the Q3 2012 | 100 | OnWav's Environmental assessment is complete, additionally, OnWav expects to complete the additional environmental work for the additional work related to the planned fiber network. | 100 | No deviation from baseline | 100 | No Deviation from baseline | 100 | OnWav expects to have permits for all sites by the end of Q3 2012 | 50 | OnWav expects to have begun site preparation on all three new tower constructions, however depending on timing of the remaining construction permits, work may not complete until Q4 2012 | 89 | OnWav expects that all equipment will be delivered and a large fraction of it installed and turned-up in the field by the end of Q3 2012 | 100 | OnWav hopes to have the final tribal clearance completed in time to construction the remaining portion of the fiber network prior to the end of Q3 2012 | 50 | OnWav anticipates having 2 of the 6 sites deployed with 3 more in progress by the end of Q3 2012. | 0 | N/A | 2012-08-15 09:05 | 2012-08-15 09:05 | 6335 | 6335 | ONWAV INC. | TRUE
NT10BIX5570080 | 2012 | Q3 | Q3 - 2012 | 7938 | 6673 | FALSE | 83 | OnWav expects to show significant progress on this project during the next quarter. Tower construction is expected to make considerable progress on Towers in late Q4. | 100 | BSS/OSS | OnWav expects to have the final remaining piece of equipment for the BSS/OSS system installed and operating by the end of the Q4 2012 | 100 | OnWav's Environmental assessment is complete, additionally, OnWav expects to complete the additional environmental work for the additional work related to the planned fiber network. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has reached agreement with the owners of the water towers for the the lease agreements for the collocation sites, but has received approval from the owners and does not expect any issues or additional expenses. | 100 | OnWav expects to have permits for all sites by the end of Q4 2012 | 100 | OnWav expects to have completed site preparation on all three new tower constructions. | 100 | OnWav expects that the final pieces of equipment (generators) will be delivered and a large fraction of it installed and turned-up in the field by the end of Q4 2012 | 100 | OnWav expects to construct the remaining portion of the fiber network prior to the end of Q4 2012 | 83 | OnWav anticipates having 5 of the 6 sites deployed with the final one to be completed in early 2013. | 0 | N/A | 2012-11-16 17:21 | 2012-11-16 17:21 | 7560 | 7560 | ONWAV INC. | TRUE
NT10BIX5570080 | 2012 | Q4 | Q4 - 2012 | 8820 | 7608 | FALSE | 87 | OnWav made significant progress on this project during the last quarter, which is not entirely represented by the money spent. OnWav's three new towers are under construction. Foundations are complete and ground work is nearly complete. The CAIs in the first two markets are nearly entirely turned up. Due to the delay between work complete and invoice date, payment for this work will not show up until Q1 2013. | 100 | OSS/BSS | OnWav expects to have the final remaining piece of equipment for the BSS/OSS system installed and operating by the end of the Q4 2012 | 100 | OnWav's Environmental assessment is complete, additionally, OnWav expects to complete the additional environmental work for the additional work related to the planned fiber network. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has reached agreement with the owners of the water towers for the the lease agreements for the collocation sites, but has received approval from the owners and does not expect any issues or additional expenses. | 100 | OnWav has completed all permits for the construction of the three new towers. Construction has commenced. | 100 | OnWav has completed all surveys and geological analysis. Site Clearing and grading is complete. Initial construction has begun at the fully prepared sites. | 100 | OnWav has received the final pieces of equipment (generators) and expects that final payments will be complete in Q1 2013 | 100 | OnWav expects to construct the remaining portion of the fiber network prior to the end of Q1 2013 | 83 | OnWav anticipates having 5 of the 6 sites deployed with the final one to be completed in early 2013. | 0 | N/A | 2013-02-15 16:30 | 2013-02-15 16:30 | 7560 | 7560 | ONWAV INC. | TRUE
NT10BIX5570080 | 2013 | Q1 | Q1 - 2013 | 9636 | 8350 | FALSE | 93 | OnWav expects to make significant progress on this project during the next quarter, in particular with invoices and payments for work completed. OnWav will make substantial progress towards completion of installation at it's final site. Additionally, OnWav expects to near its target number of CAIs connected | 100 | OSS/BSS | OnWav has deployed all of it's new BSS/OSS system integrated with Twin Lake's system. OnWav will have completed the final Acceptance and testing Procedure. | 100 | OnWav's Environmental assessment is complete, additionally, OnWav expects to complete the additional environmental work for the additional work related to the planned fiber network. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has signed leases with the owners of the water towers for the the lease agreements for the collocation sites. OnWav has reached agreement with the owner of the final collocation site and expects to sign a lease in early Q2 2013 | 100 | OnWav has completed all permits for the construction of the three new towers. Construction has completed. | 100 | OnWav has completed all surveys and geological analysis. Site Clearing and grading is complete. Construction is complete at the three new sites. | 100 | OnWav has received and made payment on the Generators. All equipment is either deployed or awaiting construction in OnWav's warehouse. | 100 | OnWav expects to have all legal documents complete on the newly constructed fiber. OnWav expects new fiber for the final, 6th, site to be active and lit and be finalizing legal documents for the new fiber. | 100 | OnWav expects to have all 6 of the 6 sites complete with CAIs active on the entire network. | 0 | N/A | 2013-05-08 17:58 | 2013-05-08 17:58 | 7560 | 7560 | ONWAV INC. | TRUE
NT10BIX5570080 | 2013 | Q2 | Q2 - 2013 | 10758 | 9044 | FALSE | 93 | OnWav expects to make significant progress on this project during the next quarter, in particular with invoices and payments for work completed. OnWav will complete installation at it's final site. Additionally, OnWav expects to reach its target number of CAIs connected. | 100 | OSS/BSS | OnWav has deployed all of it's new BSS/OSS system integrated with Twin Lake's system. OnWav will have completed the final Acceptance and testing Procedure. | 100 | OnWav's Environmental assessment is complete, additionally, OnWav has completed all additional environmental work and compliance with OnWav's additional environmental requirements. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has signed leases with the owners of the water towers and the owner of the cell tower that will serve as the final site. | 100 | OnWav has completed all permits for the construction of the three new towers. Construction has completed. | 100 | OnWav has completed all surveys and geological analysis. Site Clearing and grading is complete. Construction is complete at the three new sites. | 100 | OnWav has received and made payment on the Generators. All equipment is either deployed or awaiting construction in OnWav's warehouse. | 99 | OnWav has constructed the new portion of the fiber network, and has finalized the legal documents; the fiber is lit and active. Final invoicing is not expected until the closeout period. | 100 | OnWav expects to have all 6 of the 6 sites complete with CAIs active on the entire network. | 0 | N/A | 2013-08-27 11:02 | 2013-08-27 11:02 | 7560 | 7560 | ONWAV INC. | TRUE
NT10BIX5570080 | 2013 | Q3 | Q3 - 2013 | 11872 | 10044 | FALSE | 100 | OnWav anticipates completing the closeout process on schedule, including paying all remaining invoices and closing all active contracts. | 100 | OSS/BSS | OnWav has deployed all of it's new BSS/OSS system integrated with Twin Lake's system. | 100 | OnWav's Environmental assessment is complete, additionally, OnWav has completed all additional environmental work and compliance with OnWav's additional environmental requirements. | 100 | OnWav has completed it's network design based on chosen equipment vendor's offering. Each site has a completed RF design along with appropriate Fiber backhaul. | 100 | OnWav has completed all land acquisition and Rights of way associated with the construction of the three new towers. OnWav has signed leases with the owners of the water towers and the owner of the cell tower that serves as the final site. | 100 | OnWav has completed all permits for the construction of the three new towers. Construction has completed. | 100 | OnWav has completed all surveys and geological analysis. Site Clearing and grading is complete. Construction is complete at the three new sites. | 100 | OnWav has received and made payment on the Generators. All equipment is deployed. | 100 | OnWav has constructed the new portion of the fiber network, and has finalized the legal documents; the fiber is lit and active. Final invoicing is not expected until the closeout period. | 100 | OnWav has activated 6 of the 6 sites with CAIs active on the network. | 0 | N/A | 2014-02-24 12:08 | 2014-02-24 12:08 | 7560 | 7560 | ONWAV INC. | TRUE
NT10BIX5570081 | 2010 | Q4 | Q4 - 2010 | 1092 | 2132 | FALSE | 6 | Consistent with Baseline. | 19 | Project management; financial compliance. | Level-spend project management. | 100 | Consistent with Baseline. | 35 | Consistent with Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 9 | Consistent with Baseline. | 2 | Consistent with Baseline. | 2 | Consistent with Baseline. | 2 | Consistent with Baseline. | 2011-02-11 16:22 | 2011-02-11 16:22 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2011 | Q1 | Q1 - 2011 | 2170 | 2830 | FALSE | 28 | Consistent with Baseline. | 28 | Finance, Project Management, Compliance | Consistent with Baseline. | 100 | Complete. | 40 | Consistent with Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 48 | Consistent with Baseline. | 7 | Consistent with Baseline. | 14 | Consistent with Baseline. | 7 | Consistent with Baseline. | 2011-05-19 11:46 | 2011-05-19 11:46 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2011 | Q2 | Q2 - 2011 | 3038 | 3276 | FALSE | 37 | Consistent with Baseline. | 37 | Finance, Project Management, Compliance. | Consistent with Baseline. | 100 | Complete. | 50 | Consistent with Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 48 | Consistent with Baseline. | 26 | Consistent with Baseline. | 27 | Consistent with Baseline. | 26 | Consistent with Baseline. | 2011-08-12 11:16 | 2011-08-12 11:16 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2011 | Q3 | Q3 - 2011 | 4076 | 3881 | FALSE | 42 | Delays in the DC-CAN project caused by fiber procurement and unforeseen weather conditions may take longer than next quarter to catch up with the baseline. Original baseline was 66%. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, for the overall project. | 44 | Finance, Project Management, Reporting, Compliance. | Consistent with Baseline target. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, on this metric. | 100 | Completed. | 60 | Consistent with Baseline target. | 0 | N/A | 0 | N/A | 0 | N/A | 58 | Equipment procurement slowed slightly, as DC-CAN could not deploy equipment as quickly as desired, due to a lack of installed fiber to connect to anchors. Original baseline was 90%. OCTO's DC-Net commits to procurement levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, on this metric. | 26 | Delays in the DC-CAN project caused by fiber procurement and unforeseen weather conditions may take longer than next quarter to catch up with the baseline. Original baseline was 44%. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, on this metric. | 30 | Equipment can only be deployed to new and upgraded anchors, and to megaPOPs, as planned. While we will have procured approximately 50% of equipment, we estimate approximately 30% of DC-CAN project equipment will have been deployed by Dec 2011. Original baseline was 41%. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, on this metric. | 26 | Network testing can only be completed against installed fiber and anchors. Delays in the DC-CAN project caused by fiber procurement and unforeseen weather conditions may take longer than next quarter to catch up with the baseline. Original baseline was 44%. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, on this metric. | 2011-11-16 15:52 | 2011-11-16 15:52 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2011 | Q4 | Q4 - 2011 | 5360 | 5028 | FALSE | 44 | Delays in the DC-CAN project caused by fiber procurement may take longer than next quarter to catch up with the baseline. Revised forecast is 44%; original baseline was 66%. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, for the overall project. A new fiber procurement is currently out for public bid, through District's Office of Contracts and Procurement (OCP). A contract is expected to be awarded in early March. | 55 | Finance, Project Management, Reporting, Compliance. | Consistent with Baseline target. OCTO's DC-Net commits to levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, for the overall project. | 100 | Completed. | 70 | Consistent with Baseline Target. | 0 | N/A | 0 | N/A | 0 | N/A | 61 | Original baseline was 90% of total Equipment budget. Revised forecast is 61%. OCTO's DC-Net commits to deployment levels of 67% and 100% by June 30, 2012 and June 30, 2013, respectively, for the overall project. DC-Net is managing the DC-CAN equipment purchases consistent with the Community Anchor turnup, to support more just-in-time delivery of equipment. | 37 | Original baseline was 51% of total. Revised forecast is 37%. OCTO's DC-Net commits to deployment levels of 67% and 100% by September 30, 2012 and June 30, 2013, respectively, for the overall project. | 44 | Original baseline was 51% of total. Revised forecast is 44%. OCTO's DC-Net commits to deployment levels of 67% and 100% by September 30, 2012 and June 30, 2013, respectively, for the overall project. | 36 | Original baseline was 51% of total. Revised forecast is 36%. Testing efforts are proportional to the amount of fiber installed. OCTO's DC-Net commits to deployment levels of 67% and 100% by September 30, 2012 and June 30, 2013, respectively, for the overall project. | 2012-02-28 15:02 | 2012-02-28 15:02 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2012 | Q1 | Q1 - 2012 | 6166 | 5685 | FALSE | 56 | OCTO's DC-Net commits to spending levels of 56% for the quarter ending June 30, 2012. We will be slightly behind our baseline targets for the coming quarter, as the list of Community Anchor Institutions (CAIs) is being modified from the original baseline, for three reasons. First, some CAIs originally proposed have closed. Second, some CAIs have longer-term service contracts in place with their existing service providers, preventing them from signing onto DC-CAN during the grant period. Third, some CAIs are unable to justify the switch to DC-CAN, as the savings from current services are not significant enough to justify the transition costs. To assure a sufficient set of CAIs, we have submitted route modification requests, seeking approval of a modified set of community anchors. Upon approval, DC-CAN anticipates not more than four (4) months to complete deployment of the newly-approved anchors. | 64 | Finance, Project Management, Reporting, Compliance. | Consistent with Baseline target. | 100 | Completed. | 80 | Consistent with Baseline target. | 0 | N/A | 0 | N/A | 0 | N/A | 67 | Original baseline was 100% of project total. As earlier committed, OCTO's DC-Net commits to equipment procurement levels of at least 67% for the quarter ending June 30, 2012. | 52 | Original baseline was 64% of project total. DC-CAN target is eighty-seven (87) miles of fiber installed, or 50% of project total. For new CAIs, DC-CAN target is ninety-two (92) CAIs, or 41% of project total of 223. For upgraded CAIs, target is to complete all sixty-eight (68) upgrades, of 100% of target. Approximately 20 wireless access points (WAPs) will be installed at operational CAIs. DC-CAN target is to install one (1) new point of inter-connection (POI), to bring the total to four (4) operational POIs, or 40% of project total. We have submitted route modification requests, seeking approval of a modified set of community anchors. Upon approval, DC-CAN anticipates not more than four (4) months to complete deployment of the newly-approved anchors. These pending CAI changes will finalize the fiber route plan. With new shipments of fiber being ordered, the earlier shortages of fiber will no longer be a constraint on fiber installation. Fiber network build will be behind th | 67 | Original baseline was 64% of project total. For new Community Anchor Institutions (CAIs), DC-CAN target is ninety-two (92) CAIs, or 41% of project total of 223. For upgraded CAIs, target is to complete all sixty-eight (68) upgrades, of 100% of target. DC-CAN target is to install one (1) new point of inter-connection (POI), to bring the total to four (4) operational POIs, or 40% of project total. As CAIs and POIs are turned up, equipment will be immediately deployed. Once submitted route modifications are approved, equipment will be deployed as soon as possible to contracted CAIs and committed POIs. | 51 | Original baseline was 64% of project total. Revised forecast is 51%, proportional to the amount of fiber installed (87 miles) of the planned fiber installed for the project (173 miles). | 2012-05-17 18:24 | 2012-05-17 18:24 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2012 | Q2 | Q2 - 2012 | 7202 | 6228 | FALSE | 67 | OCTO's DC-Net commits to spending levels of 67% for the quarter ending September 30, 2012. We will be slightly behind our baseline targets for the coming quarter, as the list of Community Anchor Institutions (CAIs) is being modified from the original baseline, for three reasons. First, some CAIs originally proposed have closed. Second, some CAIs have longer-term service contracts in place with their existing service providers, preventing them from signing onto DC-CAN during the grant period. Third, some CAIs are unable to justify the switch to DC-CAN services, as the savings from current services are not significant enough to justify the transition costs and effort. With the route modifications now approved, we have a sufficient set of new CAIs. We anticipate most of those new CAIs will be installed and operational this quarter, with the remainder completed by end October 2012. | 69 | Finance, Project Management, Reporting, Compliance. | Original baseline was 73% of project total. Projected total will be slightly behind baseline target. | 100 | Completed. | 90 | Consistent with Baseline target. | 0 | N/A | 0 | N/A | 0 | N/A | 67 | Original baseline was 100% of project total. OCTO's DC-Net commits to equipment procurement levels of at least 67% for the quarter ending September 30, 2012. | 64 | Original baseline was 73% of project total. DC-CAN target is one hundred ten (110) miles of fiber installed, or 64% of project total. DC-CAN target is for two (2) additional points of inter-connection (POI), bringing the total to seven (7) operational POIs, or 50% of project total. With the receipt of new fiber, DC-CAN will have installed one hundred ten (110) miles of new fiber by end September, 2012. DC-CAN will be above the two-thirds (2/3) mark of one hundred eighteen (118) miles of fiber installed by December 2012. | 65 | Original baseline was 74% of project total. For new CAIs, DC-CAN target is one hundred thirty-two (132) by quarter end, or 59% of project total of 223. For upgraded CAIs, target is to complete all sixty-eight (68) upgrades, or 100% of target. Approximately sixty (60) wireless access points (WAPs) will be installed at operational CAIs, representing 21% of target total of 291. DC-CAN target is for two (2) additional points of inter-connection (POI), bringing the total to seven (7) operational POIs, or 50% of project total. As contracted CAIs and committed POIs are turned up, equipment will be immediately deployed. | 64 | Original baseline was 73% of project total. Revised forecast is 64%, proportional to the amount of fiber installed (110 miles) of the planned fiber installed for the project (173 miles). | 2012-08-21 17:22 | 2012-08-21 17:22 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2012 | Q3 | Q3 - 2012 | 8116 | 6765 | FALSE | 73 | OCTO's DC-Net commits to spending levels of 73% for the quarter ending December 31, 2012. Original baseline had projected project would be 93% complete at this point. We will be slightly behind our baseline targets for the coming quarter, as the list of Community Anchor Institutions (CAIs) is being modified from the original baseline, for several reasons (e.g. - planned CAI sites being closed, or CAIs committed to longer-term service contracts with other providers). | 74 |  | Original baseline was 82% of project total. Projected total will be slightly behind baseline target. | 100 | Completed. | 90 | Baseline had indicated project would be 100% complete with Network Design next quarter. Due to selection of final community anchor institutions (CAIs), final route design will not be complete until quarter following next. | 0 | N/A | 0 | N/A | 0 | N/A | 71 | Original baseline was 100% of project total. OCTO's DC-Net commits to equipment procurement levels of at least 71% for the quarter ending December 31, 2012. | 72 | Original baseline was 86% of project total. DC-CAN target is one hundred twenty-five (125) miles of fiber installed, or 72% of project total. DC-CAN target is for two (2) additional points of inter-connection (POI), bringing the total to nine (9) operational POIs, or 64% of project total. With the receipt of new fiber, DC-CAN will have installed one hundred twenty-five (125) miles of new fiber by end December 2012. DC-CAN will be just below the three-quarter (3/4) mark for fiber installed. | 72 | Original baseline was 87% of project total. For new CAIs, DC-CAN target is one hundred fifty-five (155) by year end, or 70% of project total of 223. For upgraded CAIs, target is to complete all sixty-eight (68) upgrades, or 100% of target. Approximately eighty (80) wireless access points (WAPs) will be installed at operational CAIs, representing 27% of target total of 291. DC-CAN target is for two (2) additional points of inter-connection (POI), bringing the total to nine (9) operational POIs, or 64% of project total. As contracted CAIs and committed POIs are turned up, equipment will be immediately deployed. | 72 | Original baseline was 86% of project total. Revised forecast is 72%, proportional to the amount of fiber installed (125 miles) of the planned fiber installed for the project (173 miles). | 2012-11-28 15:16 | 2012-11-28 15:16 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2012 | Q4 | Q4 - 2012 | 8942 | 7724 | FALSE | 86 | OCTO's DC-Net commits to spending levels of 86% for the quarter ending March 31, 2013. Original baseline had projected project would be 94% complete at this point. We will be slightly behind our baseline targets for the coming quarter, as the list of Community Anchor Institutions (CAIs) is being modified from the original baseline, for several reasons (e.g. - planned CAI sites being closed, or CAIs committed to longer-term service contracts with other providers). DC-CAN expects to have just the one existing partner agreement executed by the end of the quarter, with DC Access. | 91 | Finance, Project Management, Compliance, Reporting | Original baseline was 91% of project total. Consistent with Baseline target. | 100 | Completed per Baseline. | 100 | Baseline had indicated project would be 100% complete with Network Design next quarter. Due to selection of final community anchor institutions (CAIs), final route design will not be complete next quarter. | 0 | N/A | 0 | N/A | 0 | N/A | 86 | Original baseline was 100% of project total. OCTO's DC-Net commits to equipment procurement levels of at least 86% for the quarter ending March 31, 2013. | 85 | Original baseline was 88% of project total. DC-CAN target is one hundred fifty-four (154) miles of fiber installed, or 88% of project total. DC-CAN target is for three (3) additional points of inter-connection (POI), bringing the total to twelve (12) operational POIs, or 86% of project total. | 85 | Original baseline was 87% of project total. For new CAIs, DC-CAN target is one hundred eighty-five (185) by year end, or 83% of project total of 223. All sixty-eight (68) upgraded CAIs are complete. Approximately one hundred one (101) wireless access points (WAPs) will be installed at operational CAIs, representing 45% of target total of two hundred twenty-three (223) new CAIs. WAP installation at upgrade sites is pending NTIA approval. DC-CAN target is for three (3) additional points of inter-connection (POI), bringing the total to twelve (12) operational POIs, or 86% of project total. As contracted CAIs and committed POIs are turned up, equipment will be immediately deployed. | 88 | Original baseline was 88% of project total. Revised forecast is 88%, proportional to the amount of fiber installed (154 miles) of the planned fiber installed for the project (173 miles). | 2013-02-25 16:17 | 2013-02-25 16:17 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2013 | Q1 | Q1 - 2013 | 9824 | 8448 | FALSE | 88 | Office of the Chief Technology Officer (OCTO) will be applying for a three-month no-cost extension of the grant project through September 30, 2013, to permit completion of two of the committed program goals: for installed community anchor institutions (CAIs) and for rooftop wireless access points (WAPs). Assuming approval of final route modification quickly, DC-CAN will make every effort to meet all its project goals. All equipment will be purchased, all fiber installed, and WAPs will be installed as approved. As per the guidance for PPR reports, overall project progress is measured by the proportion of total program spend. DC-CAN expects to spend all the grant money consistent with the approved end of the grant period. If an extension is approved, that will permit DC-CAN to make all of its WAP goal. | 100 | Finance, Reporting, Compliance, Project Management | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. All equipment will be procured; equipment not yet installed as of the end of the grant period will be warehoused, and installed afterwards. | 100 | Per Baseline. | 90 | All equipment will be deployed per plan, except that only one hundred fifty (150) wireless access points (WAPs) will be installed, of a planned two hundred ninety-one (291). | 100 | Per Baseline. Network testing includes testing of the fiber, and for all installed equipment. At locations where only fiber is installed (and where equipment is not installed, due to potential customers electing not to receive service at present), testing will obviously not include uninstalled equipment. Everything installed will be tested; hence 100%. | 2013-05-20 12:41 | 2013-05-20 12:41 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2013 | Q2 | Q2 - 2013 | 10688 | 9005 | FALSE | 100 | Office of the Chief Technology Officer (OCTO) commits that the entire federal grant will be spent, along with its recipient match contribution, consistent with the award agreement. All program goals committed in the Baseline will be met. OCTO will start with grant closeout activities. | 100 | Finance, Reporting, Compliance, Project Management | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. | 100 | Per Baseline. All equipment will be procured; equipment not yet installed as of the end of the grant period will be warehoused, and installed afterwards. | 100 | Per Baseline. | 100 | Per Baseline. All equipment will be procured; equipment not yet installed as of the end of the grant period will be warehoused, and installed afterwards. | 100 | Per Baseline. Network testing includes testing of the fiber, and for all installed equipment. At locations where only fiber is installed (and where equipment is not installed, due to potential customers electing not to receive service at present), testing will obviously not include uninstalled equipment. Everything installed will be tested, and therefore 100%. | 2013-08-21 15:47 | 2013-08-21 15:47 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570081 | 2013 | Q3 | Q3 - 2013 | 11500 | 9623 | FALSE | 100 | Completed as committed. | 100 | Finance, Project Management, Reporting, Compliance | Completed as committed. | 100 | Completed as committed. | 100 | Completed as committed. | 0 | N/A | 0 | N/A | 0 | N/A | 100 | Completed as committed. | 100 | Completed as committed. | 100 | Completed as committed. | 100 | Completed as committed. | 2013-12-18 12:26 | 2013-12-18 12:26 | 5943 | 5943 | District of Columbia Government | TRUE
NT10BIX5570082 | 2010 | Q3 | Q3 - 2010 | 182 | 1357 | FALSE | 8 | RFP selections will be made by Dec 2010; construction contracts drafted | 10 | Project Management | Project reporting and tracking along with outreaching taking place | 47 | Filing for SHPO review and state review will be completed | 56 | RFP responses will solidify pathways and design | 0 | In Progress | 3 | Pole Attachment Agreements will be underway | 0 | In Progress | 7 | Early construction contracts will begin to complete make-ready | 0 | In Progress | 0 | In Progress | 0 | In Progress | 2010-10-28 10:50 | 2010-10-28 10:50 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2010 | Q4 | Q4 - 2010 | 1246 | 2276 | FALSE | 6 | Variance - 2%; Delay in construction start due to RFP negotiations. | 22 | Project Mgmnt. | Consistent with Baseline Plan. | 100 | Consistent with Baseline Plan. | 62 | Consistent with Baseline Plan. | 1 | Consistent with Baseline Plan. | 19 | Consistent with Baseline Plan. | 0 | Delay in vendor contract completion may result in lower than expected progress in Q1 2011. | 8 | Equipment purchases in multiple stages to take advantage of early fiber. | 3 | Delay in vendor contract completion may result in lower than expected progress in Q1 2011. | 5 | Consistent with Baseline Plan. | 0 | Consistent with Baseline Plan. | 2011-02-20 14:39 | 2011-02-20 14:39 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2011 | Q1 | Q1 - 2011 | 2110 | 2800 | FALSE | 9 | -15%; Construction was delayed due to lengthy contract negotiations with vendors. We are planning to be back on baseline by end of Q5. | 19 | Proj. Mngmnt. | -12%; Expect recovery with completed contract negotiations for all project areas in this quarter. | 100 | Consistent with Baseline Plan. | 67 | -13%; Related to construction delay caused by extended contract negotiations with vendors. Anticipate recovery in next quarter. | 0 | -18%; Related to construction delay caused by extended contract negotiations with vendor. Project tasks have been completed in this area that has not yet incurred project funds draw. We anticipate an update in recovery in the next quarterly report. | 21 | -17%; Related to construction delay caused by extended contract negotiations with vendor. Project tasks have been completed in this area that has not yet incurred project funds draw. We anticipate an update in recovery in the next quarterly report. | 0 | -100%; Only the NHDOT project has site prep needs and this is slated to start in the following quarter (Q5/Summer 2011). | 2 | -8%; Purchases being held off until construction vendors are signed. | 0 | -6%; Related to construction delay caused by extended contract negotiations with vendors. Anticipate recovery in next quarter. | 9 | -18%; Purchases being held off until construction vendors are signed. Anticipate moderate gains. | 1 | -2%; Anticipate recovery through next quarter. | 2011-05-17 18:11 | 2011-05-17 18:11 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2011 | Q2 | Q2 - 2011 | 3088 | 3301 | FALSE | 13 | (Baseline 42% - Variance from baseline is -29%. We anticipate accellerated progress as vendor work progresses. | 40 | Project Management | (Baseline 40% - anticipate no variance in baseline) On track to meet baseline | 100 | Complete | 80 | (Baseline 92% - Variance from Baseline is -12%) FastRoads will be hiring a construction vendor (Q5) and once that occurs, it is expected much of the remaining Network Design will be addressed. | 25 | (Baseline 44% Variance from baseline is -19%) Awaiting results of required Make Ready estimates - unknown at this time as to actual costs and timeframes that will be required to complete this work. Anticipate Make-Ready estimates to be returned in earnest in Q5 and Q6. | 10 | (Baseline 53% Variance from baseline is -43%) Dependent on rights of way make ready work. | 0 | (Baseline 100% Variance from baseline is -100%) NHDOT's site preparation will be complete in 2012. Originally planned for 2011. The DOT portion of the project budget is 10%. | 20 | (Baseline 20% - anticipate no variance in baseline) Working with vendors to acquire fiber. There could be challenges in delivery from vendors as current quotes do not offer any commitments to a delivery timeframe. DWDM equipment phase 1 equipment will be invoiced. A substantial portion of the microwave equipment will be ordered. | 5 | (Baseline 15% - Variance from baseline is -10%) Dependent on rights of way make ready work. NH Department of Transportation delay and all project vendor hire delays will push this activity into subsequent quarters. | 0 | (Baseline 35% - Variance from baseline is -35%) Dependent on success in equipment procurement. | 0 | (Baseline 8%- Variance from baseline is -8%) Dependent on success in equipment procurement, make ready work, and construction work. | 2011-08-15 16:29 | 2011-08-15 16:29 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2011 | Q3 | Q3 - 2011 | 4078 | 3882 | FALSE | 26 | Baseline 50% We continue to work with utilities to process payments for Make Ready work in as soon as estimates are received and validated. We are also seeking opportunities to increase throughput on pole licensing requests with utility stakeholders. We will be addressing building entrance connections to CAIs in the coming quarter. | 35 | Project Management | Baseline was estimated at 48% and was based on project plan activity. Our project plan indicates we will be at 44%. Percent of budget expended is projected at 35%. Original estimates in this milestone were based on project progress. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. | 100 | Complete | 75 | Baseline was estimated at 95% and was based on project plan activity. Our project plan indicates we will be at 80%. Percent of budget expended is projected at 75%. Original estimates in this milestone were based on project progress. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. Once the FastRoads engineering and construction RFP is awarded in October we will work with the vendor to obtain a revised timeline on remaining network design work. | 100 | Baseline was estimated at 68% and was based on project plan activity. Percent of budget expended is N/A as there are no financial expenditures budgeted for Rights of Way. Project activity for this category has been moved to the Site Preparation category. Going forward the projection will continue to be 100. | 48 | Baseline was estimated at 58% and was based on project plan activity. Our project plan indicates we will be at 21%. Percent of budget expended is projected at 48%. Original estimates in this milestone were based on project progress of submitting applications and receiving pole licenses earlier than actually occurred. We continue to work with utilities to accelerate the timelines for licensure. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. | 52 | Baseline was estimated at 100% and was based on project plan activity. Our project plan indicates we will be at 51%. Percent of budget expended is projected at 52%. Original estimates in this milestone were based on project progress on receiving make ready quotes. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. All NH Pole applications have been submitted, and it is anticipated that we will have received 50% of Make Ready estimates and that we will have received 15% of our pole licenses on the route. | 19 | Baseline was estimated at 25% and was based on project plan activity. Our project plan indicates we will be at 11%. Percent of budget expended is projected at 19%. Original estimates in this milestone were based on project progress. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. Portions of fiber optic cable are expected to be delivered in the next quarter. | 14 | Baseline was estimated at 22% and was based on project plan activity. Our project plan indicates we will be at 8%. Percent of budget expended is projected at 14%. Original estimates in this milestone were based on project progress. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. | 16 | Baseline was estimated at 42% and was based on project plan activity. Our project plan indicates we will be at 33%. Percent of budget expended is projected at 16%. Original estimates in this milestone were based on project progress. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. | 0 | Baseline was estimated at 9% and was based on project plan activity. Our project plan indicates we will be at 0%. Percent of budget expended is projected at 0%. Original estimates in this milestone were based on project progress. We have aligned our budget to these milestone categories and this and future reports will include both financial and project plan estimates. | 2011-11-16 15:54 | 2011-11-16 15:54 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2011 | Q4 | Q4 - 2011 | 5028 | 4699 | FALSE | 45 | Baseline 59% Delays in hiring engineering and construction vendor are the primary reason for the discrepancy between baseline and next quarter's projected % complete. Anticipate to complete pole applications for the middle mile in the coming quarter and to complete a substantial amount of Make-Ready work and obtain an estimated 25% of pole licenses across the route. DOT anticipated to purchase components for its portion of the project Engineering work continues on last mile. Mountaintop builds continue across NH. | 50 | Project Management | Baseline 57% Project Plan 51% | 100 | Completed | 100 | Baseline 98% Project Plan 85% Actual spend is anticipated be 107% and will include additional engineering and pole application expenses. | 100 | No expenditures scheduled in this milestone | 46 | Baseline 71% Project Plan 30%. Continue to work with Utilities and Third Parties to accelerate licensure of poles. | 61 | Baseline 100% Project Plan 74% Anticipate surveys to be complete on the middle mile and Make Ready expenses to be available for 90% of the route. Last Mile engineering and Make-Ready continues. | 32 | Baseline 38% Project Plan 14% Continue to obtain fiber optic cable. Microwave equipment expected to be invoiced this quarter. | 40 | Baseline 30% Project Plan 2%. Anticipate increased middle mile construction in the coming quarter. | 25 | Baseline 51% Project Plan 34% Anticipate invoice for 3 mountaintop builds from this quarter and expenses for additional mountaintop builds during the coming quarter. | 0 | Baseline 9% Project Plan 0%. Network testing is anticipated to begin in Q3 2012. | 2012-02-15 11:55 | 2012-02-15 11:55 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2012 | Q1 | Q1 - 2012 | 6008 | 5603 | FALSE | 70 | Baseline 74% Delays in hiring engineering and construction vendor are the primary reason for the discrepancy between baseline and next quarter's projected percent completion. Anticipate to complete pole surveys for the Middle Mile in the coming quarter and to complete a substantial amount of Make-Ready work and obtain an estimated 90% of pole licenses across the route. DOT anticipated to purchase components for its portion of the project. Make-Ready work continues on the Last Mile. Mountaintop builds continue across NH. | 60 | Project Management | Baseline 66% | 100 | Completed. | 100 | Baseline 100% Actual is at 122% due to increased Make-Ready costs. | 100 | No expenditures scheduled in this milestone. | 56 | Baseline 87% Anticipate increased middle mile and last mile construction in the coming quarter. | 100 | Baseline 100% Anticipate all Make Ready expenses to be finalized this quarter. | 66 | Baseline 47% Continue to obtain fiber optic cable. Procurement of equipment for FastRoads network and construction and DOT construction will occur this quarter. | 56 | Baseline 57% | 34 | Baseline 59% FastRoads network equipment anticipated to be deployed. | 0 | Baseline 14% Network testing is anticipated to begin in Q3 2012. | 2012-05-10 12:16 | 2012-05-10 12:16 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2012 | Q2 | Q2 - 2012 | 7014 | 6134 | FALSE | 74 | Baseline forecast 85. | 64 | Project Mgmt. | Baseline forecast 75. | 100 | Completed. | 100 | Baseline forecast 100; Forecast to be at 130%. | 100 | No expenditures scheduled in this milestone. | 59 | Baseline forecast 100. | 100 | Baseline forecast 100; Forecast to be 111%. | 67 | Baseline forecast 96. | 63 | Baseline forecast 83. | 40 | Baseline forecast 71. | 0 | Baseline forecast 23. | 2012-08-10 14:20 | 2012-08-10 14:20 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2012 | Q3 | Q3 - 2012 | 7842 | 6625 | FALSE | 80 | Baseline 92 | 70 | Proj. Managment | Baseline 82 | 100 | Completed | 100 | Baseline 100;Actual Q4 PPR forecast 127 | 100 | n/a | 86 | Baseline 100 | 100 | Baseline 100;Actual Q4 PPR forecast 126 | 70 | Baseline 100; Actual Q4 PPR forecast 126 | 66 | Baseline 96 - see item 3 below | 54 | Baseline 87- see item 3 below | 50 | Baseline 55- see item 3 below | 2012-11-13 13:11 | 2012-11-13 13:11 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2012 | Q4 | Q4 - 2012 | 9006 | 7780 | FALSE | 87 | Baseline 97.5 | 84 | Project Management | Baseline 91 | 100 | Completed | 100 | Baseline 100 PPR Actual Q1-2013 forecast 138 | 100 | N/A | 100 | Baseline 100 PPR Actual Q1-2013 forecast 122 | 100 | Baseline 100 PPR Actual Q1-2013 forecast 139 | 75 | Baseline 100 -see item 3 below | 70 | Baseline 97 -see item 3 below | 66 | Baseline 98 -see item 3 below | 50 | Baseline 85 -see item 3 below | 2013-02-27 11:14 | 2013-02-27 11:14 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2013 | Q1 | Q1 - 2013 | 10024 | 8561 | FALSE | 95 | Baseline 100. Requesting an extension to complete remaining work. | 80 | Project Management | Baseline 100. Requesting an extension to complete remaining work. | 100 | Complete. | 100 | Actual 139 Baseline 100. Requesting an extension to complete remaining work. | 100 | No expenditures scheduled in this milestone. | 100 | Actual 116 Baseline 100. Requesting an extension to complete remaining work. | 100 | Actual 140 Baseline 100. Requesting an extension to complete remaining work. | 81 | Baseline 100. Requesting an extension to complete remaining work. | 85 | Baseline 100. Requesting an extension to complete remaining work. | 76 | Baseline 100. Requesting an extension to complete remaining work. | 46 | Baseline 100. Requesting an extension to complete remaining work. | 2013-05-31 11:44 | 2013-05-31 11:44 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2013 | Q2 | Q2 - 2013 | 10734 | 9030 | FALSE | 98 | Baseline 100. Received an extension to complete remaining work. | 96 | Project Mgmnt. | Baseline 100. Ongoing Project Management due to extension. | 100 | Complete. | 100 | Actual 104 Baseline 100. Received an extension to complete remaining work. FastRoads projected to complete additional 1% in Q4 2013. | 100 | No expenditures scheduled in this milestone. | 100 | Baseline 100. This category is projected to be complete in Q3 2013. The project has received an extension to complete remaining work. | 100 | Actual 102 Baseline 100. This category is projected to be complete in Q3 2013. The project has received an extension to complete remaining work. | 95 | Baseline 100. Received an extension to complete remaining work. Datacasting equipment scheduled to be purchased during Q3 2013. | 97 | Baseline 100. Received an extension to complete remaining work. NHOS and NH FastRoads network Build will continue in Q3 2013. | 98 | Baseline 100. Received an extension to complete remaining work. UNH deploying equipment to CAIs. NH FastRoads deploying to CAIs, residences, and businesses. | 78 | Baseline 100. Received an extension to complete remaining work. NH FastRoads testing to occur after final equipment deployment. | 2013-08-26 11:54 | 2013-08-26 11:54 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2013 | Q3 | Q3 - 2013 | 11404 | 9514 | FALSE | 99 | Baseline Projection 100. USNH does not expect cost overruns in the overall project. | 100 | Project Mngmnt. | Baseline Projection 100 Actual spend is projected to be 101%. | 100 | Complete | 100 | Baseline Projection 100 Actual spend is projected to be 106%. | 100 | Baseline Projection 100 | 100 | Baseline Projection 100 | 100 | Baseline Projection 100 Actual spend is projected to be 102%. | 99 | Baseline Projection 100 | 98 | Baseline Projection 100 | 98 | Baseline Projection 100 | 100 | Baseline Projection 100 | 2013-11-26 15:17 | 2013-11-26 15:17 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570082 | 2013 | Q4 | Q4 - 2013 | 12282 | 10452 | FALSE | 100 | Complete | 100 | Project Mngmnt. | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-06-20 12:55 | 2014-06-20 12:55 | 5843 | 5843 | University System of New Hampshire | TRUE
NT10BIX5570084 | 2010 | Q4 | Q4 - 2010 | 1180 | 2213 | FALSE | 4 | Substantive portions contributing to overall project completion in the next reporting period consist of issuance of FONSI. If EA is delayed based on SHPO and no FONSI is issued, no procurement, no releases of RFPs, or site preparation tasks during the construction season will occur. Project planning is in-process and mobilization efforts including equipment procurement and staging may also be delayed due to the â€œAll or Noneâ€ EA requirements. | 0 |  | No variance from revised Baseline Plan | 100 | Pending final approval by NTIA a FONSI needs to be issued in Q3. Iowa SHPO approval is a major concern to overall project completion process. At this reporting period this benchmark is of great concern and question. | 60 | High level network design will be 100% complete and it is anticipated that substantial portion of final network design will be completed prior the end of the next reporting period. | 0 | It is anticipated that Rights of Way related to all site locations will be in jeopardy due to current FONSI conditional EA requirements. Currently, no variance from project Baseline Plan. | 0 | No Construction or Permitting related activities will begin until land acquisition is completed/secured and OSP engineering RFQâ€™s released. | 0 | No variance from revised Baseline Plan | 10 | It is anticipated that equipment orders / procurement will be begin prior to the end of the upcoming reporting period. Again this is pending EA â€œAll or Noneâ€ conditional approval. Currently, there is No variance from revised Baseline Plan. | 0 | No variance from revised Baseline Plan | 0 | No variance from revised Baseline Plan | 0 | No variance from revised Baseline Plan | 2011-02-16 14:11 | 2011-02-16 14:11 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2011 | Q1 | Q1 - 2011 | 2086 | 2788 | FALSE | 2 | Due to the project modification, we are not going to meet the milestones or expenditures forecasted. | 0 |  | No variance from Baseline Report | 35 | Due to the project modification, we submitted a request for a Programmatic Agreement. | 45 | Due to the project modification, we have not completed the network design for the previous quarter. | 0 | Due to the project modification, we are not projecting to receive a FONSI until Qtr 2, Year 2. Therefore, we will not begin ROW work next quarter. | 0 | Due to the project modification, we do not project that we will start obtaining construction permits during the next quarter. | 0 | No variance from Baseline Report | 0 | Due to the project modification and not obtaining a FONSI, we do not project that we will be procuring equipment next quarter. | 0 | Due to the project modification and not obtaining a FONSI, we do not project finalizing the Blenco to Logan Fiber Lease and Hut Agreement. | 0 | No variance from Baseline Report | 0 | No variance from Baseline Report | 2011-05-17 12:49 | 2011-05-17 12:49 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2011 | Q2 | Q2 - 2011 | 3086 | 3300 | FALSE | 4 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. However, during this qrt IHS will finish identifying the hut locations for the Main, North, West, and South Rings. OSP Design for the Main, North, West, and South Rings will be started and in process. ISP Design for the North, West, South, East Long Haul, West Long Haul, and Central Rings will be in process with ISP design completion of the Main Ring. The negotiations for the IRU will be completed and pending finalization on receiving a FONSI. | 0 |  | No variance from the Baseline Report | 45 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. However, IHS anticipates that the EA/Section 106 for the hut locations will be near completion. IHS anticipates receiving a "no objection" response from USFWS and to correspond with tribes interested in the IHS BTOP project. | 70 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. However, IHS anticipates the ISP statewide network design will be in process for North, West, East Long Haul, West Long Haul and the Central Ring. The OSP Design will be in process for the Main, North, West, and South Ring. | 0 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure stainability. IHS anticipates that the Right of Way work will start qtr 4 (Oct-Dec 2011). | 0 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. IHS anticipates that Construction Permits and Other Approvals will start qtr 4 (Oct-Dec 2011). | 0 | No variance from the Baseline Report. IHS anticipates Site Preparation RFPs to be issued qtr 4 (Oct-Dec 2011). Site work will not actually start until qtr 1 (Jan-Mar 2012) after receiving a FONSI and the ground is ready to dig. | 0 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. IHS is working on completing Equipment RFPs currently and next qtr will start procuring after selecting equipment vendors. | 0 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. IRU Negotiations are under way. IHS anticipates to finalize IRU negotiations in qtr 4 (Oct-Dec 2011). | 0 | The variance from the originally approved baseline report was caused by the need to complete a modification to the original project to ensure sustainability. IHS will start the DWDM Development RFP vendor selection to procure equipment. | 0 | No variance from the Baseline Report. IHS anticipates that equipment will be tested during qtr 4 (Oct-Dec 2011). | 2011-08-15 14:13 | 2011-08-15 14:13 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2011 | Q3 | Q3 - 2011 | 3928 | 3802 | FALSE | 60 | IHS anticipates that during the next quarter a Programmatic Agreement will be negotiated and the FONSI signed. The Start Up Support Services Vendor Kick-Off meeting will be scheduled and a middle mile extension interconnection plan in place. IHS will procure the DWDM equipment in December. OSP Engineering for the fiber laterals will be completed and ISP Engineering will be completed as well. The IRU negotiations will be completed. IHS anticipates the land permitting will be underway during this quarter as well. | 0 |  | No variance from baseline report. | 50 | IHS anticipates that during the next quarter a Programmatic Agreement will be negotiated and the FONSI signed. | 75 | OSP Engineering for the fiber laterals will be completed and ISP Engineering will be completed as well. | 0 | IHS anticipates that the Right of Way work will start Quarter 3, Year 2 (Jan-Mar 2012). | 40 | IHS anticipates the permitting for the 9 hut locations will be in process and near completion. | 0 | IHS anticipates the site preparation to being Quarter 3, Year 2 (Jan-Mar 2012) | 25 | IHS anticipates procuring preliminary returnable equipment that can be stored prior to obtaining a FONSI. | 3 | IHS anticipates finalizing the IRU in Quarter 2, Year 2 (Oct-Dec 2011) | 0 | IHS anticipates the equipment installation to be in-process Quarter 3, Year 2 (Jan-Mar 2012). | 0 | IHS anticipates that equipment will begin being tested during Quarter 3, Year 2 (Jan-Mar 2012). | 2011-11-08 17:35 | 2011-11-08 17:35 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2011 | Q4 | Q4 - 2011 | 5100 | 4770 | FALSE | 68 | Iowa Health System (IHS) anticipates that during the next quarter a FONSI will be obtained and it can proceed forward with finalizing the land leases and IRU negotiations for the Moorehead location. IHS also anticipates the OSP and ISP engineering will be completed allowing the construction RFP to be released and a vendor selected to start construction the following quarter. The Router RFP will also be released and a vendor selected. During the next quarter, IHS anticipates that there will be 4 Last Mile Provider agreements. The ISP equipment and material lab testing and staging will be in process. The OSP equipment staging will be in process. Permitting and Right of Way approvals will be obtained and site preparation for the 9 hut installations on all rings will be in process. | 0 |  | No variance from the baseline report. | 60 | IHS anticipates that during the next quarter a FONSI will be obtained and IHS will work towards fulfilling the Programmatic Agreement requirements for reporting and Middle Mile Extensions. | 85 | IHS anticipates that during the next quarter the OSP engineering will be complete for the 9 hut locations and started for the Last Mile Provider connections. | 50 | IHS anticipates that during the next quarter the Rights of Way will be completed for the 9 hut locations and Rights of Way will be started for the Last Mile Provider connections. | 60 | IHS anticipates that during the next quarter, the construction permits will be completed for the 9 hut locations and the Last Mile Provider connections will be started. | 20 | IHS anticipates that the site preparation for the 9 hut locations will be started during this quarter. | 83 | IHS anticipates that the Routers will be procured during the next quarter and the fiber laterals for the 9 hut locations will be procured as well. | 40 | IHS anticipates finalizing the IRU to lease 99.5 miles of fiber during the next quarter. | 10 | IHS anticipates the equipment installation to be started during the next quarter. | 10 | IHS anticipates that network/equipment testing will begin during the next quarter to allow for deployment. | 2012-02-17 14:47 | 2012-02-17 14:47 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2012 | Q1 | Q1 - 2012 | 5938 | 5568 | FALSE | 71 | IHS/BBI anticipates installing the 9 hut locations pending fiber lateral installation upon review of the reroute modification. IHS/BBI anticipate staging the equipment in the huts, finalizing the IRU with Long Lines, and executing customer agreements with at least 3 more customers. | 0 |  | No variance from the baseline report. | 65 | IHS/BBI anticipates that the OSP and ISP engineering will be completed allowing the construction RFQs to be released and a vendor selected to start construction for the 9 hut locations and laterals that have not changed. IHS/BBI anticipates that at least 3 more agreements will be executed and Middle Mile Extensions will be engineered to move forward complying with the Programmatic Agreement. | 90 | IHS/BBI anticipates that during the next quarter the OSP engineering will be complete for the 9 hut locations and started for the middle mile extensions. | 50 | IHS/BBi anticipates that during the next quarter the ROW will be complete for the 9 hut locations and started for the middle mile extensions. | 60 | IHS/BBI anticipates that during the next quarter the construction permits will be complete for the 9 hut locations, underway for the hut laterals, and started for the middle mile extensions. | 50 | IHS/BBI anticipates that during the next quarter the site preparation will be complete for the 9 hut location, underway for the hut laterals, and started for the middle mile extensions. | 80 | IHS/BBI anticipates that the equipment procurement for the Ethernet Switches and Installation Kits will be underway. | 40 | IHS/BBI anticipates the IRU negotiations will be finalized and the fiber lateral builds will begin. | 30 | IHS/BBI anticipates that the equipment deployment will be underway and equipment installation will be started for the 9 hut locations. | 0 | No variance from the baseline report. IHS/BBI anticipates that the Network Testing will begin during Q3 2012 (Jul-Aug). | 2012-05-07 10:41 | 2012-05-07 10:41 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2012 | Q2 | Q2 - 2012 | 7006 | 6130 | FALSE | 77 | IHS anticipates completing the 9 hut and lateral installations dependent up on EA approvals. Staging and deploying equipment will be under way and moving towards bringing up the main ring by end of Q4 2012. IHS anticipates executing customer agreements will at least 3 more customers. | 0 |  | No variance from the baseline report. | 80 | IHS anticipates that the middle mile extension route modifications will be approved in Q3 2012 allowing IHS to start constructing fiber to our newly signed customers. Therefore, the only environmental assessment left will be for the newly signed customers in Q3 2012, Q4 2012, and Q1 2012. | 90 | No variance from baseline report. | 60 | IHS anticipates the ROW will be completed for the 9 hut locations and started for the middle mile extensions. | 70 | IHS anticipates the construction permits and other approvals will be finalized early in Q3 2012 for the 9 hut locations and underway for the middle mile extensions. | 50 | IHS anticipates the site prep will be completed early in Q3 2012 and under way for the middle mile extensions pending EA approval. | 90 | IHS anticipates the ethernet switches for the three last mile providers will be completed during Q3 2012 and the installation kits will continually be ordered as we start deploying equipment. | 80 | IHS anticipates the 9 hut laterals will be completed and the 3 middle mile extensions under way. | 30 | IHS anticipates that the equipment deployment will be underway and equipment installation completed for the 9 hut locations. | 30 | IHS anticipates network testing will be started for the main ring. | 2012-08-10 13:38 | 2012-08-10 13:38 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2012 | Q3 | Q3 - 2012 | 7990 | 6701 | FALSE | 80 | IHS anticipates that the main ring will be activated by end of Q4 2012. IHS anticipates executing customer agreements will at least 4 more customers. | 0 |  | No variance from the baseline report | 90 | IHS anticipates that the middle mile extension route modifications will be approved in Q4 2012 allowing IHS to start constructing fiber to our newly signed customers. Therefore, the only environmental assessment left will be for the newly signed customers in Q1 2012. | 95 | No variance from baseline report. | 75 | IHS anticipates the ROW will be started for the additional middle mile extensions. | 80 | IHS anticipates the construction permits and other approvals will be finalized for the 3 middle mile extensions. | 85 | IHS anticipates the site prep will be started and partially completed for the 3 middle mile extensions pending EA approval. | 95 | IHS anticipates the DWDM equipment will be procured for the western long haul route upgrade and installation kits will continually be ordered as are deploying equipment. | 90 | IHS anticipates the 9th hut laterals will be completed and the 3 middle mile extensions under way. | 50 | IHS anticipates that the equipment deployment will be finalized on the main ring. | 50 | IHS anticipates network testing will be completed for the main ring. | 2012-11-20 16:37 | 2012-11-20 16:37 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2012 | Q4 | Q4 - 2012 | 8836 | 7621 | FALSE | 93 | IHS anticipates the north, wester rings will be activated by end of Q1 2013. IHS anticipates the 4 newly proposed routes will be near approvals from NTIA | 0 |  | No variance from the baseline report | 100 | Complete | 100 | Complete | 95 | IHS anticipates the ROWs will be finalized by end of Q1 2013 | 95 | IHS anticipates the permitting will be finalized by end of Q1 2013 | 95 | IHS anticipates the site prep will remain the same for the next quarter until the 4 newly submitted proposed routes in Q 1 2013 are approved by NTIA | 100 | IHS anticipates all equipment will be procured during the next quarter. | 95 | IHS anticipates the 3 middle mile routes will be completed. | 95 | IHS anticiaptes that the equipment deployment will be finalized on the north and western rings....and start on long haul routes. | 95 | IHS anticipates network testing will be completed on the north and western rings. | 2013-02-19 12:17 | 2013-02-19 12:17 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2013 | Q1 | Q1 - 2013 | 9902 | 8492 | FALSE | 96 | IHS anticipates the 1st group of customer fiber builds will be close to completion and the 2nd group of customer fiber builds will be a third of the way complete by the end of Q2 2013. IHS Anticipates completing the construction activities to build out the fiber network connecting customers due to heavy snowfall and rainfall during end of Q2 2013 and Q3 2013. | 0 | N/A | No variance from the baseline report | 100 | Complete | 100 | Complete | 100 | IHS anticipates the ROWs will be finalized. | 100 | IHS anticipates the construction permits will be completed. | 100 | IHS anticipates the site prep will be completed. | 100 | IHS anticipates the equipment procurement will be completed. | 95 | IHS anticipates the 1st group of customer fiber builds will start up mid May and will be completed by July 2013. The 2nd group of customer fiber builds will be completed July/August 2013. | 95 | IHS anticipates that the equipment deployment for the 1st group of customer will be close to completion and the 2nd group of customer deployments will be a third of the way complete. Delays due to weather dependent construction activities. | 95 | IHS anticipates network testing will be completed on the north and western rings. Delays due to weather dependent construction activities. | 2013-05-24 14:02 | 2013-05-24 14:02 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2013 | Q2 | Q2 - 2013 | 10698 | 9011 | FALSE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-08-22 16:21 | 2013-08-22 16:21 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570084 | 2013 | Q3 | Q3 - 2013 | 11836 | 10012 | FALSE | 100 | Complete | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-02-18 15:32 | 2014-02-18 15:32 | 6985 | 6985 | Iowa Health System | TRUE
NT10BIX5570085 | 2010 | Q4 | Q4 - 2010 | 1372 | 2385 | FALSE | 2 | Baseline Report 2% | 0 | 0 | N/A | 90 | Baseline Report 90% | 50 | Baseline Report 50% | 10 | Baseline Report 10% | 10 | Baseline Report 10% | 5 | Baseline Report 5% | 12 | Baseline Report 12% | 10 | Baseline Report 10% | 5 | Baseline Report 5% | 5 | Baseline Report 5% | 2011-02-25 08:50 | 2011-02-25 08:50 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2011 | Q1 | Q1 - 2011 | 2336 | 2913 | FALSE | 2 | Baseline 18%. Our original baseline was derived from our awarded project of $17,509,274. The recently-approved overlap resolution and project rescope has changed our project to be $12,861,126. While our percent complete is behind where our original baseline had estimated it is due to the significant project scope change. A new baseline is being developed to be submitted during the next quarter that will more accurately reflect the project schedule going forward. | 100 | Vehicles | VTel purchased two broadband vehicles. | 100 | Baseline 100% | 60 | Baseline 100% Please see narrative above regarding overall project completion and milestones. | 2 | Baseline 30%. Please see narrative above regarding overall project completion and milestones. | 2 | Baseline 30%. Please see narrative above regarding overall project completion and milestones. | 1 | Baseline 15%. Please see narrative above regarding overall project completion and milestones. | 2 | Baseline 47%. Please see narrative above regarding overall project completion and milestones. | 0 | Baseline 30%. Please see narrative above regarding overall project completion and milestones. | 0 | Baseline 23%. Please see narrative above regarding overall project completion and milestones. | 0 | Baseline 23%. Please see narrative above regarding overall project completion and milestones. | 2011-05-26 11:33 | 2011-05-26 11:33 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2011 | Q2 | Q2 - 2011 | 3250 | 3387 | FALSE | 6 | No variance with updated baseline. | 50 | Vehicles | VTel purchased two broadband vehicles. | 100 | Our environmental assessment has been complete. | 60 | A firm is currently in the field working on the network design. | 10 | No variance with updated baseline. | 10 | No variance with updated baseline. | 10 | No variance with updated baseline. | 55 | No variance with updated baseline. | 0 | No variance with updated baseline. | 1 | No variance with updated baseline. | 1 | No variance with updated baseline. | 2011-08-22 09:07 | 2011-08-22 09:07 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2011 | Q3 | Q3 - 2011 | 4136 | 3914 | FALSE | 46 | No variance with baseline. | 0 | Vehicles | Working with the grants office and BTOP staff we have determined that the vehicles are not an allowable expense. We are working with the staff to determine how these funds can be used/allocated appropriately. | 100 | Our environmental assessment has been completed. | 90 | We expect field engineering to be completed in January 2012, which is 30 days behind our original estimate of 4Q11. Work was delayed due to impact of Hurricane/Tropical Storm Irene. | 40 | No variance with baseline. | 40 | No variance with baseline. | 19 | No variance with baseline. | 75 | No variance with baseline. The equipment has already started to arrive. | 0 | No variance with baseline. | 72 | Site visits are now occurring, and we are scheduled to begin turn-up during this quarter. No variance from baseline. | 72 | The network will be tested as DWDM/Optical sites come online. No variance from baseline. | 2011-11-18 14:12 | 2011-11-18 14:12 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2011 | Q4 | Q4 - 2011 | 5176 | 4840 | FALSE | 50 | Much of our progress will be dictated by the speed at which we are able to receive permits, and make-ready construction schedules. We plan on having the applications submitted, however, we are unable to control the turnaround time by the pole-owning utilities. We are expecting make ready work to take approximately 90 days after make ready payment has been made. | 100 |  | Network testing equipment procurement occurred in Q4 2011. | 100 | Our environmental assessment has been completed. | 100 | Our outside engineer should have all miles staked by the end of Q1 2012 | 60 | No variance with baseline. | 60 | No variance with baseline. | 29 | No variance with baseline. | 95 | No variance with baseline. | 11 | No variance with baseline. | 75 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 75 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 2012-02-21 17:21 | 2012-02-21 17:21 | 5847 | 5847 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2012 | Q1 | Q1 - 2012 | 6238 | 5721 | FALSE | 60 | Much of our progress will be dictated by the speed at which we are able to receive permits, and make-ready construction schedules. We are also working directly with state officials and the pole-owning utilities to get pole make ready completed in a timely fashion. We are expecting make ready work to take approximately 90 days after make ready payment has been made. We will continue to monitor the progress in this area and address areas of concern. | 90 | N/A | No variance with baseline. | 100 | Our environmental assessment has been completed. If there are approved route changes additional environmental assessments will be completed. | 100 | Our outside engineer has staked the major routes in our original project. They will continue to stake any route changes that occur. | 80 | No variance with baseline | 80 | No variance with baseline. | 79 | No variance with baseline. | 80 | We expect additional deployment of electrical equipment through the end of 2012. | 42 | No variance with baseline. | 75 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 75 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 2012-05-21 16:28 | 2012-05-21 16:28 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2012 | Q2 | Q2 - 2012 | 7246 | 6250 | FALSE | 60 | Progress continues to be dictated by make-ready construction schedules. We will continue to monitor this and work with pole owners as well as state officials to assure that positive progress continues. | 60 | Testing Equip. | Testing equipment has been purchased and any remaining funds within this category may be used for other construction costs if needed. | 100 | Our environmental assessment has been completed. If there are approved route changes additional environmental assessments will be completed. | 100 | Our outside engineer has staked the major routes in our original project. They will continue to stake any route changes that occur. | 75 | There have been delays in make-ready progress, however our team is actively managing the process, and progress has improved in the 2nd quarter of 2012 and we expect that to continue in the third quarter 2012. | 75 | Federal, state, and local permits have been monitored by the outside engineering firm, and any delays have been addressed. | 75 | This category is 25% under baseline, but is expected to meet it by the end of 2012. | 85 | We expect additional deployment of electrical equipment through the end of 2012. | 35 | Network construction is progressing. We are behind our baseline projections; however we feel confident that this will not negatively impact completion. | 75 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 75 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 2012-08-24 16:25 | 2012-08-24 16:25 | 7374 | 7374 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2012 | Q3 | Q3 - 2012 | 8140 | 6780 | FALSE | 67 | Progress continues to be dictated by make-ready construction schedules. We will continue to monitor this and work with pole owners as well as state officials to assure that positive progress continues. | 90 | Testing Equipment | Testing equipment has been purchased and any remaining funds within this category may be used for other construction costs if needed. | 100 | Our environmental assessment has been completed. If there are approved route changes additional environmental assessments will be completed. | 100 | Our outside engineer has staked the major routes in our original project. They will continue to stake any route changes that occur. | 80 | There have been delays in make-ready progress, however our team is actively managing the process, and progress has improved in the 3rd quarter of 2012 and we expect that to continue in the fourth quarter 2012. | 80 | Federal, state, and local permits have been monitored by the outside engineering firm, and any delays have been addressed. | 80 | This category is 25% under baseline, but is expected to meet it by the end of 2012. | 90 | We expect additional deployment of electrical equipment through the end of 2012 and into the first quarter of 2013. | 40 | Network construction is progressing. We are behind our baseline projections; however we feel confident that this will not negatively impact completion. | 80 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 80 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 2012-11-29 14:29 | 2012-11-29 14:29 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2012 | Q4 | Q4 - 2012 | 8734 | 7531 | FALSE | 65 | With make ready problem resolution expected early in the quarter, construction will progress more quickly. The deployment of equipment will also be accelerated in order for us to meet construction deadlines. | 90 | Testing Equipment | Testing equipment has been purchased and any remaining funds within this category may be used for other construction costs if needed. | 100 | Our environmental assessment has been completed. If there are approved route changes additional environmental assessments will be completed. | 100 | Our outside engineer has staked the major routes in our original project. They will continue to stake any route changes that occur. | 90 | There have been delays in make-ready progress, however our team is actively managing the process, and progress has improved upon contracting with an inspector that knows the local contacts and can resolve specific make ready problems as they come up. | 90 | Federal, state, and local permits have been monitored by the outside engineering firm, and any delays are being addressed. | 90 | Federal, state, and local permits have been monitored by the outside engineering firm, and any delays are being addressed. | 90 | We expect additional deployment of electrical equipment through the first quarter of 2013. | 50 | Network construction is progressing. We are behind our baseline projections; however we feel confident that this will not negatively impact completion. | 85 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 85 | Equipment deployment has had some delays due to coordination efforts between utility companies, landowners, and equipment vendor. It is not felt that this will delay the completion of the project. | 2013-02-12 16:34 | 2013-02-12 16:34 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2013 | Q1 | Q1 - 2013 | 10030 | 8565 | FALSE | 74 | Extension AAR Filed | 95 |  | Extension AAR Filed | 100 | Extension AAR Filed | 75 | Extension AAR Filed | 75 | Extension AAR Filed | 60 | Extension AAR Filed | 96 | Extension AAR Filed | 75 | Extension AAR Filed | 50 | Extension AAR Filed | 85 | Extension AAR Filed | 85 | Extension AAR Filed | 2013-05-31 15:43 | 2013-05-31 15:43 | 7374 | 7374 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2013 | Q2 | Q2 - 2013 | 10714 | 9020 | FALSE | 71 | see AAR & Extension Request | 95 |  | see AAR & Extension Request | 100 | see AAR & Extension Request | 90 | see AAR & Extension Request | 85 | see AAR & Extension Request | 85 | see AAR & Extension Request | 90 | see AAR & Extension Request | 85 | see AAR & Extension Request | 58 | see AAR & Extension Request | 78 | see AAR & Extension Request | 58 | see AAR & Extension Request | 2013-08-23 16:22 | 2013-08-23 16:22 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2013 | Q3 | Q3 - 2013 | 11352 | 9477 | FALSE | 83 | See AAR & Extension Request | 95 | n/a | See AAR & Extension Request | 100 | See AAR & Extension Request | 90 | See AAR & Extension Request | 90 | See AAR & Extension Request | 90 | See AAR & Extension Request | 90 | See AAR & Extension Request | 85 | See AAR & Extension Request | 68 | See AAR & Extension Request | 78 | See AAR & Extension Request | 68 | See AAR & Extension Request | 2013-11-22 15:35 | 2013-11-22 15:35 | 5849 | 5849 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | 2013 | Q4 | Q4 - 2013 | 12472 | 10651 | FALSE | 81 | We do not expect to construct much as the winter season is upon us. There will be some expenditures for make ready and permitting but no significant build | 86 | admin & consulting | there should be little or no activity in this category | 97 | Spending remains flat as we have completed FONSI work and do not expect additional costs | 66 | Little work done in this area during the next quarter but expect to see increased activity in Q2 & Q3 | 86 | We have 6 easements left to obtain and hope to have them in hand by the end of Q2 | 90 | The majority of applications have been filed and we now await license issuance and make ready cost true-ups | 73 | We continue to methodically deploy and as such have staggered sites. We will continue this approach throughout the project | 81 | Little progress is expected in Q1 due to the inability to deploy or construct due to weather. | 88 | We are right on track with our permitting costs slightly ahead of network build percentages | 81 | Little progress is expected in Q1 due to the inability to deploy or construct due to weather. | 85 | Little progress is expected in Q1 due to the inability to deploy or construct due to weather. | 2014-08-29 15:57 | 2014-08-29 15:57 | 7797 | 7797 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570086 | 2010 | Q4 | Q4 - 2010 | 580 | 1597 | FALSE | 6 | No variance | 0 |  | N/A | 100 | No variance | 75 | No variance | 75 | No variance | 75 | No variance | 0 | No variance | 10 | We will have started ordering equipment but do not anticipate receipt prior to the end of this quarter. We expect we will be back on track to meet our projected percentage of completion as reported by the next quarter. | 0 | No variance | 0 | No variance | 0 | No variance | 2011-01-27 09:56 | 2011-01-27 09:56 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2011 | Q1 | Q1 - 2011 | 2058 | 2774 | FALSE | 5 | Continue to be behind due to delays with the Environmental Assessment and other reasons listed below. | 0 |  | N/A | 100 | No variance | 75 | Additional EA challenges, developing route change modifications and construction permit requirements have consumed all available resources. This requires us to extend these tasks out an additional quarter. These delays were unanticipated. We expect this to be completed one quarter later than initially planned. | 75 | Additional EA challenges, developing route change modifications and construction permit requirements have consumed all available resources. This requires us to extend these tasks out an additional quarter. These delays were unanticipated. We expect this to be completed one quarter later than initially planned. | 75 | Additional EA challenges, developing route change modifications and construction permit requirements have consumed all available resources. This requires us to extend these tasks out an additional quarter. These delays were unanticipated. We expect this to be completed one quarter later than initially planned. | 0 | No Variance | 50 | The remaining OSP materials for the 2nd segment will not be delivered until November for the 2012 construction season. No room for all materials at once. | 0 | No Variance | 0 | The RFP hasn't been completed yet so equipment has not been ordered. We have not received our FONSI yet so we canâ€™t construct until we get that. | 0 | No Variance | 2011-05-16 17:16 | 2011-05-16 17:16 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2011 | Q2 | Q2 - 2011 | 2998 | 3256 | FALSE | 21 | Slightly delayed due to reasons listed below | 0 |  | N/A | 100 | No Variance | 95 | We expect the final design for the Brainerd to Moorhead route to complete one quarter later due to earlier delays. | 90 | We anticipate a continued slight delay due to the State government shutdown | 90 | We anticipate a continued slight delay due to the State government shutdown | 30 | Slight variance due to delay in securing building sites and delay in receiving our FONSI. We have now purchased property and will continue moving forward with this milestone. | 0 | We expect this milestone to continue behind plan as a result of delays in obtaining signed CAI contracts with two of our partners. We expect an equipment ship date in October. | 22 | This will vary from baseline because we included some of the construction materials in the equipment category for the baseline report. This line will track ahead of baseline because of that. | 0 | We expect this milestone to continue behind plan as a result of delays in obtaining signed CAI contracts with two of our partners. We continue pursuing other CAI contracts. | 0 | No variance | 2011-08-10 16:34 | 2011-08-10 16:34 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2011 | Q3 | Q3 - 2011 | 4112 | 3899 | FALSE | 32 | We expect that we will remain behind our planned baseline. We are working on an EA addendum and working diligently to get signed contracts for CAI sites. It has proven difficult to sign contracts for service to CAIs when we do not have an anticipated completion date due to weather and unforeseen hindrances such as the delays in receiving the FONSI and a number of permits. We are hopeful that these efforts will help us get closer to our baseline report estimates. In addition, there is always a timing lag between work completion and the invoicing. Most invoices are being processed now and will increase spending in the next quarter, allowing us to catch up. | 0 |  | N/A | 100 | No variance | 95 | We are working through an EA addendum which will push this milestone out slightly. | 90 | We are working through an EA addendum and need to wait for approval before we can finalize the remaining Rights of Way. | 75 | An EA addendum is being prepared for the remaining route. Permits cannot be applied for until we are cleared for a construction path so we can submit our applications to the various permitting entities. We expect approval of the EA addendum in Year 2, Q3 with permits to follow shortly after that. | 50 | No variance | 40 | This milestone will continue to show a variance from the baseline because this line only references CO and electronics equipment and other materials had been included in the original baseline. We are also experiencing difficulty with getting CAI contracts signed. | 38 | N/A-ahead of baseline | 40 | No variance | 0 | No variance | 2011-11-17 14:44 | 2011-11-17 14:44 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2011 | Q4 | Q4 - 2011 | 4994 | 4667 | FALSE | 54 | This milestone will be slightly behind our baseline since we do not expect to do any construction during the winter months. We continue to work on preparations to allow us to begin construction as soon as weather permits. This will help us to be closer to plan the following quarter. This will not hinder our ability to be 2/3 complete by the end of year 2. | 0 |  | N/A | 100 | N/A | 100 | N/A | 95 | This is just slightly behind our baseline due to work on the EA addendum. We will continue working on these once the EA addendum is approved. | 85 | This is just slightly behind our baseline due to work on the EA addendum. We will continue working on these once the EA addendum is approved. | 50 | N/A | 20 | This milestone will continue to show a variance from the baseline because this line only references CO and electronics equipment. Other materials had been included in the original baseline. We do not anticipate receiving any additional equipment this quarter due to difficulty in getting CAI contracts signed. In addition, we will not need equipment this quarter because there is no construction planned during winter months. | 37 | This is just slightly behind our baseline. We do not expect this number to change this quarter since we are unable to build in winter conditions. | 15 | This milestone will remain the same this quarter since there is no construction planned during winter months. | 5 | This milestone will remain the same this quarter since we do not expect to deploy any equipment this quarter. | 2012-02-14 11:18 | 2012-02-14 11:18 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2012 | Q1 | Q1 - 2012 | 6024 | 5611 | FALSE | 67 | We expect to be just slightly behind our baseline. This will not hinder project completion by July 31, 2013. | 0 |  | N/A | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 50 | This is just slightly behind baseline and we continue working to catch up. | 31 | This line only references CO and the electronics equipment. This line will continue to show a variance from baseline because other materials were included in that report. We have started ordering and receiving equiment but due to difficulty in securing CAI's, the amount of equipment ordered is less than anticipated. | 60 | This is slightly behind our baseline but we continue working to catch up. | 15 | This milestone continues to lag due to difficulty with getting CAI contracts signed. We are on schedule for deployment of equipment in the middle mile routes. Once the CAI's are confirmed, we will be working on a schedule for CAI deployments. We do not anticipate this will hinder our ability to be 2/3 complete by the end of year 2. | 20 | No variance | 2012-05-10 15:40 | 2012-05-10 15:40 | 6162 | 6162 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2012 | Q2 | Q2 - 2012 | 7010 | 6132 | FALSE | 77 | This is slightly behind baseline but we continue working to catch up. | 0 |  | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 98 | We expect this to be just slightly behind baseline but do not expect this to impact our scheduled completion. | 80 | This is slightly behind our baseline. This includes the building sites and COs only. We do not expect this to impact our scheduled completion. | 35 | This line only references CO and the electronics equipment. This line will continue to show a variance from baseline because other materials were included in that report. They are actually part of the construction portion of the budget. We have started ordering, receiving and installing equipment but due to difficulty in securing CAIs, the amount of equipment ordered is less than originally anticipated. In addition, the needs of potential CAIs have changed resulting in less equipment. | 80 | No variance | 30 | This milestone continues to lag due to difficulty in securing CAI contracts. We continue working to catch up. | 30 | This milestone will be behind baseline as we work to install and deploy equipment. | 2012-08-10 14:11 | 2012-08-10 14:11 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2012 | Q3 | Q3 - 2012 | 8114 | 6764 | FALSE | 84 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 0 |  | N/A | 100 | No variance | 71 | This is slightly behind baseline and varies from previous reports due to a change in how this is calculated. This is now based solely on expenditure. Work continues and we expect no delay in completion. | 71 | This is slightly behind baseline and varies from previous reports due to a change in how this is calculated. This is now based solely on expenditure. Work continues and we expect no delay in completion. | 71 | This is slightly behind baseline and varies from previous reports due to a change in how this is calculated. This is now based solely on expenditure. Work continues and we expect no delay in completion. | 90 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 48 | This line only references central office and electronics equipment. This line will continue to show a variance from baseline because other materials were included in that report. In addition, the needs of potential CAIs have changed resulting in less equipment being needed. We do not anticipate any purchases this quarter. | 92 | This number is slightly above baseline. | 23 | This milestone continues to lag due to delay in securing CAI contracts. We continue to focus on this. | 44 | This is slightly behind baseline. We do not plan to do any additional testing until the route construction is complete. We do not expect this to delay completion. | 2012-11-28 14:54 | 2012-11-28 14:54 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2012 | Q4 | Q4 - 2012 | 8784 | 7582 | FALSE | 84 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 0 |  | N/A | 100 | No variance | 67 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 94 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 94 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 80 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 60 | This line only references central office and electronics equipment. This line will continue to show a variance from baseline because other materials were included in that report. In addition, the needs of potential CAIs have changed resulting in less equipment being needed. We do not anticipate any purchases this quarter. | 89 | This is slightly below baseline. Work continues and we expect no delay in completion of the project. | 19 | This milestone continues to lag due to delay in securing CAI contracts. We continue to focus on this. | 90 | This is slightly ahead of baseline | 2013-02-14 17:10 | 2013-02-14 17:10 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2013 | Q1 | Q1 - 2013 | 10016 | 8554 | FALSE | 90 | This is slightly behind baseline. We continue to work towards completion. | 0 |  | N/A | 100 | No variance | 77 | This is slightly behind baseline. Work continues and we expect no delay in completion. | 100 | No variance | 100 | No variance | 80 | This is slightly behind baseline. Work continues and we expect no delay in completion. | 66 | This line is behind baseline but only references central office and electronics equipment. This line will continue to show a variance from baseline because other materials were included in that report. In addition, the needs of potential CAI's have changed resulting in less equipment being needed. | 93 | This is slightly behind baseline. Work continues and we expect no delay in completion. | 37 | This milestone continues to lag due to delay in securing CAI contracts. We continue to focus on this. | 94 | This is slightly behind baseline. | 2013-05-30 16:55 | 2013-05-30 16:55 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2013 | Q2 | Q2 - 2013 | 10364 | 8808 | FALSE | 89 | We will be 100% complete with the project but this number will remain behind baseline due to cost savings. | 0 |  | N/A | 100 | No variance | 77 | We will be 100% complete with the project but this number will remain behind baseline due to cost savings. | 100 | We are reporting 100% for this milestone. Our spending for this category is higher than baseline but will not cause us to go over our total budget. | 100 | We are reporting 100% for this milestone. Our spending for this category is higher than baseline but will not cause us to go over our total budget. | 82 | We will be 100% complete with the project but this number will remain behind baseline due to cost savings. | 71 | We will be 100% complete with the project but this number will remain behind baseline due to cost savings and a decreased number of CAI's with signed contracts. | 94 | We will be 100% complete with the project but this number will remain behind baseline due to cost savings. | 31 | We will be 100% complete with the project but this number will remain behind baseline due to cost savings and a decreased number of CAI's with signed contracts. | 94 | We will be 100% complete with the project but this number will remain behind baseline due to cost savings and a decreased number of CAI's with signed contracts. | 2013-07-30 15:27 | 2013-07-30 15:27 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | 2013 | Q3 | Q3 - 2013 | 11682 | 9803 | FALSE | 100 | All tasks are complete. This is the final report so there is no next quarter | 0 |  | No variance | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 100 | All tasks are complete. This is the final report so there is no next quarter | 2014-01-28 10:17 | 2014-01-28 10:17 | 6163 | 6163 | Enventis Telecom, Inc. | TRUE
NT10BIX5570087 | 2010 | Q4 | Q4 - 2010 | 1132 | 2169 | FALSE | 2 | â€¢ Select an Engineering firm to complete the field engineering and submit permits â€¢ Draft and have signed the Engineering Services contract â€¢ Submit the Final EA to the NTIA â€¢ Gain approval of Interconnection point permits (4) â€¢ Submit other required permits â€¢ Compile a list of perspective construction vendors â€¢ Prepare the Construction and Procurement RFP | 0 |  | N/A | 90 | Submit final draft after network design is complete. | 95 | Re-bid delayed design start. Complete in 2011 Q2. | 70 | Re-bid delayed Rights of Way requests. Complete in 2011 Q2. | 70 | Rebid delayed other permit requests. Complete in 2011 Q2 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-14 11:50 | 2011-02-14 11:50 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2011 | Q1 | Q1 - 2011 | 2096 | 2793 | FALSE | 4 | Design changes, moving of one interconnection point and the need for joint-use agreements are delaying the start date of the cable build and expenditures as budgeted. | 0 |  | N/A | 90 | Design changes will delay EA approval until Y2Q1 (3rd qtr 2011) | 100 | N/A | 100 | N/A | 100 | N/A | 0 | Easements have been secured for two of the four sites; RFPs are being prepared for site work. | 0 | N/A | 0 | Construction of cable to begin in Y2Q1. Unforeseen changes in route delayed completion of design and EA; therefore, construction start date is pushed back a quarter. | 0 | N/A | 0 | N/A | 2011-05-17 15:11 | 2011-05-17 15:11 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2011 | Q2 | Q2 - 2011 | 2940 | 3227 | FALSE | 9 | Construction start delayed due to EA approval. Will receive some fiber optic cable, network equipment and huts during quarter. | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 30 | Delay in EA approval delayed site preparation activities. | 10 | Received some network equipment ahead of schedule. | 0 | Construction scheduled to start Y2Q2 | 0 | N/A | 0 | N/A | 2011-08-05 16:56 | 2011-08-05 16:56 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2011 | Q3 | Q3 - 2011 | 4002 | 3840 | FALSE | 34 | Construction start delayed until approval of EA(expected11/2011) moving forward with procurement and start construction in 12/2011 | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 20 | Cannot start until approval of EA (expected 11/2011) | 98 | Approximately 20% of cable received, but not invoiced. Awaiting nextowrk build to start in 12/2011 | 5 | Arrival of remainder of transport equipment. Network build to start in 12/2011 | 0 | N/A | 0 | N/A | 2011-11-14 08:21 | 2011-11-14 08:21 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2011 | Q4 | Q4 - 2011 | 5410 | 5091 | FALSE | 50 | Construction started in January 2012 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 90 | Awaiting on utility to place new duct | 25 | Site work to being March 2012 | 100 | Complete | 12 | Will construct 20 miles of cable in Y3Q1 (Y2Q3) | 0 | Equipment deployed after completion of site work | 0 | Network testing to begin after completion of equipment installation | 2012-02-29 15:09 | 2012-02-29 15:09 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2012 | Q1 | Q1 - 2012 | 5964 | 5581 | FALSE | 58 | Construction delayed due to delay in EA approval | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 95 | Bridge bids to be awarded in Y2Q4 (June 2012 qtr) | 66 | Will complete site work on 3 of 4 hut sites in Y2Q4, June qtr 2012 | 100 | Complete | 33 | Construct 40 miles in Y2Q4, June qtr 2012 for total of 56 miles | 0 | Awaiting completion of cable and site work | 0 | Awaiting completion of equipment installation | 2012-05-08 14:23 | 2012-05-08 14:23 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2012 | Q2 | Q2 - 2012 | 7220 | 6237 | FALSE | 67 | Construction delayed due to delay in EA approval | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 77 | Construct 50 miles in 3rd qtr of 2012 | 0 | Awaiting completion of cable | 0 | Awaiting complettion of equipment installation | 2012-08-23 10:39 | 2012-08-23 10:39 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2012 | Q3 | Q3 - 2012 | 7750 | 6569 | FALSE | 79 | Moved from 64% to 79% completed. Construction delayed due to EA approval delay & permitting with Suffolk & Chesapeake. | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 94 | Construct 30 miles in Y3Q4 (Y3Q2) | 15 | To start after completion of huts (nodes) | 0 | Awaiting completion of equipment installation | 2012-11-01 13:31 | 2012-11-01 13:31 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2012 | Q4 | Q4 - 2012 | 8998 | 7776 | FALSE | 75 | Delayed awaiting approval of agreements with Chesapeake and Surry | 0 | true | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 96 | Construct 20 miles in Y3Q3 | 35 | To continue after completion of nodes | 35 | Awaiting completion of equipment installation | 2013-02-27 10:33 | 2013-02-27 10:33 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2013 | Q1 | Q1 - 2013 | 9674 | 8369 | FALSE | 88 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-05-10 08:38 | 2013-05-10 08:38 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2013 | Q2 | Q2 - 2013 | 10602 | 8958 | FALSE | 86 | Project Complete by 9/30/13 | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Construction, installation and testing complete by 8/31/13 | 100 | Construction, installation and testing complete by 8/31/13 | 100 | Construction, installation and testing complete by 8/31/13 | 2013-08-15 11:17 | 2013-08-15 11:17 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | 2013 | Q3 | Q3 - 2013 | 12326 | 10499 | FALSE | 100 | Complete: 86% of Grant Funds Spent | 0 |  | N/A | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 100 | Complete: 86% of Grant Funds Spent | 2014-07-25 16:21 | 2014-07-25 16:21 | 5495 | 5495 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570088 | 2010 | Q4 | Q4 - 2010 | 520 | 1541 | FALSE | 1 | An additional .5% will be completed for next quarter indicating a 1% completion for next quarter. This is consistent with our baseline. | 25 | Admin, Legal, Arch/ Engr. Fees | Match / Staff Time | 90 | Possible changes to Charlotte's network design approach may change the final EA study required. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-01-25 08:46 | 2011-01-25 08:46 | 6166 | 6166 | Charlotte, City of | TRUE
NT10BIX5570088 | 2011 | Q1 | Q1 - 2011 | 1892 | 2691 | FALSE | 2 | Due to new RFP Re-issue, overall project will not meet baseline expectations. | 33 | Admin, Legal, Arch/ Engr. Fee | No variance | 90 | Due to new RFP issued E/A will not complete until solution/vendor is determined | 0 | No variance | 2 | EA Draft + New Tech. Contractor + Contractor for Contracting support | 0 | No variance | 0 | N/A | 0 | Due to New RFP issued, no equipment will be purchased in this quarter. | 0 | No variance | 0 | No variance | 0 | No variance | 2011-05-05 09:59 | 2011-05-05 09:59 | 6166 | 6166 | Charlotte, City of | TRUE
NT10BIX5570088 | 2011 | Q2 | Q2 - 2011 | 2930 | 3222 | FALSE | 1 | Not 20% due to restructuring of project and reissued a new RFP. | 85 | Admin, Legal, Arch/Engr. Fee | Not 41% because additional staff time will be spent completing procurement process for a BTOP Vendor. | 90 | Not 100% complete until vendor and solution is selected and design approve. | 0 | Not 100% due to restructuring of project and reissued a new RFP. | 1 | Not 0% because invested in Technical Consultant services to assist in project restructuring. | 0 | No Variance | 0 | N/A | 0 | Not 5% until vendor & solution is selected and approved. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-08-04 17:40 | 2011-08-04 17:40 | 6166 | 6166 | Charlotte, City of | TRUE
NT10BIX5570088 | 2011 | Q3 | Q3 - 2011 | 3478 | 3505 | FALSE | 11 | Not 21%. Charlotte will be about 3 months behind baseline milestones. | 100 | a. Admin. & Legal, d. Arch & Engr. | Not. 50%. Due to additional staff effort needed to re-issue 2nd RFP, evaluation & negotiations processes or a BTOP contractor. | 100 | No Variance - Charlotte will be seeking a categorical exclusion in this quarter. | 100 | No Variance | 1 | Not 14%. Charlotte has not yet recognized tower space opportunity cost and original budget erroneously budget space that was not compliant with OMB. | 0 | No Variance | 0 | N/A | 0 | Not 5%. The re issuance of a 2nd RFP put Charlotte behind schedule. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-10-26 14:14 | 2011-10-26 14:14 | 6166 | 6166 | Charlotte, City of | TRUE
NT10BIX5570088 | 2011 | Q4 | Q4 - 2011 | 4858 | 4555 | FALSE | 20 | Not 59%. Charlotte expects to be back on course by end of Q2 2012. | 52 | a. Admin. & Legal, d. Arch & Engr. | Not 58%. Mostly due to Re-budgeting | 100 | No Variance | 100 | No Variance | 32 | Not 29%. Charlotte expects to be on course by end of Q2 2012. | 75 | Not 100%. Charlotte expects to complete all permitting by June 2012. | 0 | N/A | 13 | Not 100%. Charlotte expects to have all equipment delivered by mid Q2 2012. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2012-02-01 13:31 | 2012-02-01 13:31 | 6166 | 6166 | Charlotte, City of | TRUE
NT10BIX5570088 | 2012 | Q1 | Q1 - 2012 | 5598 | 5396 | FALSE | 28 | Not 60%. Expect to be back on course in 2012 Q3. | 91 | a.Admin & Legal | Not 60%. More staff and time needed than realized. | 100 | No Variance | 100 | No Variance | 38 | Not 43%. Expect to be back on course in 2012 Q3. | 22 | Not 100%. Permitting may be extended thru July 2012. | 0 | No Variance | 15 | Not 100%. Phase 2 Equipment will be delayed beyond this quarter. | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2012-04-27 09:54 | 2012-04-27 09:54 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570088 | 2012 | Q2 | Q2 - 2012 | 6922 | 6088 | FALSE | 22 | Not 60%. Project on Suspension | 100 |  | More staff and time was used when re-issue RFP and Project was redefined. | 95 | Suspension | 100 | No Variance | 32 | Not 57%. Due to Suspension | 4 | Not 100%. Due to Suspension. | 0 | No Variance | 13 | Not 100%. Due to Suspension | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2012-08-08 09:33 | 2012-08-08 09:33 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570088 | 2012 | Q3 | Q3 - 2012 | 7756 | 6572 | FALSE | 23 | Project Suspension | 100 | a. Admin. Legal, d. Arch & Engr | More staff required when re-issue RFP and Project was redefined. | 95 | Project Suspension | 100 | No Variance | 32 | Project Suspension | 4 | Project Suspension | 0 | No Variance | 13 | Project Suspension | 0 | Project Suspension | 0 | Project Suspension | 0 | Project Suspension | 2012-11-01 14:50 | 2012-11-01 14:50 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570088 | 2012 | Q4 | Q4 - 2012 | 8652 | 7472 | FALSE | 23 | Project under suspension | 100 | a. Admin & Legal | More staff time on re-issued RFP and redefining Project. | 95 | Project under suspension | 100 | No Variance | 48 | Active tower leases signed before suspension | 4 | Project under suspension | 0 | No Variance | 13 | Project under suspension | 0 | Project under suspension | 0 | Project under suspension | 0 | Project under suspension | 2013-02-04 11:27 | 2013-02-04 11:27 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570088 | 2013 | Q1 | Q1 - 2013 | 9678 | 8371 | FALSE | 25 | Project under suspension | 100 | a. Admin | More staff time required when original RFP was revised & reissued | 95 | Project under suspension | 100 | No Variance | 61 | Active Tower Leases before suspension. | 4 | Project under suspension | 0 | No Variance | 13 | Project under suspension | 0 | Project under suspension | 0 | Project under suspension | 0 | Project under suspension | 2013-05-10 10:37 | 2013-05-10 10:37 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570088 | 2013 | Q2 | Q2 - 2013 | 10122 | 8624 | FALSE | 26 | Project is under suspension | 100 | A; Admin & Legal | Extra staff time occurred when RFP process was repeated. | 95 | Project is under suspension | 100 | No variance | 61 | Tower leases obligated before suspension | 4 | Project is under suspension | 0 | No variance | 13 | Project is under suspension | 0 | Project is under suspension | 0 | Project is under suspension | 0 | Project is under suspension | 2013-07-23 11:37 | 2013-07-23 11:37 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570088 | 2013 | Q3 | Q3 - 2013 | 10974 | 9203 | FALSE | 27 | Project is under suspension | 100 | a: Admin & Legal | Extra staff time when repeated RFP process | 95 | Project is under suspension | 100 | No Variance | 61 | Obligated Tower Leases | 4 | Project is under suspension | 0 | No Variance | 13 | Project is under suspension | 0 | Project is under suspension | 0 | Project is under suspension | 0 | Project is under suspension | 2013-10-28 16:06 | 2013-10-28 16:06 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570088 | 2013 | Q4 | Q4 - 2013 | 11850 | 10022 | FALSE | 47 | Projections may not reflect accurately due to a Project restructure and future re-budget. | 100 | a:Admin & Legal | Accrued as a result of repeated RFP process and project suspension Reflects substantial increases from ALU closeout. | 95 | Projections may not reflect accurately due to a Project restructure and future re-budget. | 100 | No Variance | 65 | Projections may not reflect accurately due to a Project restructure and future re-budget. Reflects substantial increases from ALU closeout. | 4 | Projections may not reflect accurately due to a Project restructure and future re-budget. | 0 | No Variance | 25 | Projections may not reflect accurately due to a Project restructure and future re-budget. Reflects substantial increases from ALU closeout. | 0 | Projections may not reflect accurately due to a Project restructure and future re-budget. | 0 | Projections may not reflect accurately due to a Project restructure and future re-budget. | 50 | Projections may not reflect accurately due to a Project restructure and future re-budget. Reflects substantial increases from ALU closeout. | 2014-02-20 09:06 | 2014-02-20 09:06 | 7273 | 7273 | Charlotte, City of | TRUE
NT10BIX5570089 | 2010 | Q4 | Q4 - 2010 | 1088 | 2128 | FALSE | 2 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of delays in the finalization and readiness of sites and other initial program delays. | 12 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of delays in the finalization and readiness of sites and other initial program delays. | 51 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of delays in the finalization and readiness of sites and other initial program delays. | 5 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-11 15:38 | 2011-02-11 15:38 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2011 | Q1 | Q1 - 2011 | 2080 | 2785 | FALSE | 3 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 14 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 76 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 18 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | N/A | 2011-05-17 10:38 | 2011-05-17 10:38 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2011 | Q2 | Q2 - 2011 | 2984 | 3249 | FALSE | 5 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 17 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays.165 | 76 | Although SAC #12 was lifted, additional work identified to this milestone is yet to be completed. | 73 | No variance. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 2011-08-09 15:46 | 2011-08-09 16:12 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2011 | Q3 | Q3 - 2011 | 3632 | 3599 | FALSE | 4 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 18 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 26 | Fewer SHPO consultations were required at this point in the project. | 80 | No variance. | 0 | N/A | 0 | N/A | 35 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 2011-10-28 15:10 | 2011-10-28 15:10 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2011 | Q4 | Q4 - 2011 | 4860 | 4558 | FALSE | 5 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 21 | PMO | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. These Program Management and Project Management resources are projected to be included in future budget amendment. | 41 | Fewer SHPO consultations were required at this point in the project. | 100 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 2012-02-02 14:20 | 2012-02-02 14:26 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2012 | Q1 | Q1 - 2012 | 5934 | 5566 | FALSE | 6 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 24 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. These Program Management and Project Management resources are projected to be included in future budget amendments. | 41 | Fewer SHPO consultations were required at this point in the project. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 90% complete by the end of next quarter, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of continuing delays in the finalization and readiness of sites and other program delays. | 2012-05-07 08:53 | 2012-05-07 08:53 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2012 | Q2 | Q2 - 2012 | 6886 | 6069 | FALSE | 7 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 29 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 28 | Fewer SHPO consultations were required at this point in the project. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. Although the Project Baseline report indicates that Motorola Solutions should be 90% complete by the end of next quarter, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 2012-08-07 13:01 | 2012-08-07 13:03 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2012 | Q3 | Q3 - 2012 | 7804 | 6605 | FALSE | 8 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 34 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 28 | Fewer SHPO consultations were required at this point in the project. The indicated variance from the baseline plan for the next quarter is anticipated due to additional environmental SACs that will result as a part of the approval of the Route Modification Request. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 2012-11-08 16:23 | 2012-11-08 16:23 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2012 | Q4 | Q4 - 2012 | 8504 | 7225 | FALSE | 9 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 34 | Other | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 28 | Fewer SHPO consultations were required at this point in the project. The indicated variance from the baseline plan for the next quarter is anticipated due to additional environmental SACs that will result as a part of the approval of the Route Modification Request. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 2013-01-30 15:29 | 2013-01-30 15:29 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2013 | Q1 | Q1 - 2013 | 9680 | 8372 | FALSE | 10 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 36 |  | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 28 | Fewer SHPO consultations were required at this point in the project. The indicated variance from the baseline plan for the next quarter is anticipated due to additional environmental SACs that will result as a part of the approval of the Route Modification Request. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and other program delays, and due to the uncertainties introduced by the partial suspension of LTE related activities. | 2013-05-10 12:26 | 2013-05-10 12:26 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2013 | Q2 | Q2 - 2013 | 10166 | 8659 | FALSE | 10 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 37 | Project Mgmt | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 53 | Fewer SHPO consultations were required at this point in the project. The indicated variance from the baseline plan for the next quarter is anticipated due to additional environmental reviews that will result. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 2013-07-26 09:45 | 2013-07-26 09:45 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2013 | Q3 | Q3 - 2013 | 11206 | 9392 | FALSE | 11 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 40 | Other | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 100 | Fewer SHPO consultations were required at this point in the project. The indicated variance from the baseline plan for the next quarter is anticipated due to additional environmental reviews that will result. | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements. Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of additional effort required in the finalization and readiness of sites and other program requirements. | 0 | N/A | 0 | N/A | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 0 | Motorola Solutions is anticipating that the indicated variance from the baseline plan for the next quarter will occur as a result of the continuing delays in the finalization and readiness of sites and due to the uncertainties introduced by the partial suspension of LTE related activities. | 2013-11-07 14:58 | 2013-11-07 14:58 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | 2013 | Q4 | Q4 - 2013 | 12170 | 10354 | FALSE | 12 | The indicated variance from the baseline plan is due to the expiration of the Grant. The cost incurred during this quarter are related to the close out of the Grant. | 41 | N/A | Fewer State Historic Preservation Office consultations were required at this point in the project. The indicated variance from the baseline plan for the next quarter is anticipated due to additional environmental reviews that will result. | 55 | No further State Historic Preservation Office consultations will be required at this point in the project. See 1 above for further explanation | 100 | Although the Project Baseline report indicates that Motorola Solutions should be 100% complete, Motorola Solutions has currently exceeded 100% (maximum allowed to be reported is 100%). Motorola Solutions is anticipating that the indicated variance from the baseline plan is the result of additional effort required in the finalization and readiness of sites and other program requirements). The network was fully designed, but not implemented due to the partial suspension of the Grant. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2014-05-07 11:23 | 2014-05-07 11:23 | 6531 | 6531 | Motorola Solutions, Inc. | TRUE
NT10BIX5570090 | 2010 | Q4 | Q4 - 2010 | 1272 | 2298 | FALSE | 20 | On Schedule | 0 |  | N/A | 100 | On Schedule | 50 | On Schedule | 30 | On Schedule | 30 | On Schedule | 0 | N/A | 80 | On Schedule | 0 | On Schedule | 40 | On Schedule | 0 | On Schedule | 2011-02-22 10:09 | 2011-02-22 10:09 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2011 | Q1 | Q1 - 2011 | 2278 | 2884 | FALSE | 15 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline | 0 |  | N/A | 100 | On Schedule | 60 | On Schedule | 30 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline. | 60 | On Schedule | 0 | N/A | 80 | Behind schedule, not an issue at this time. Construction will shift to 2012 but finish before deadline. | 10 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline. | 40 | Behind schedule, not an issue at this time. Construction will shift to 2012 but finish before deadline. | 0 | On Schedule | 2011-05-24 12:39 | 2011-05-24 12:39 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2011 | Q2 | Q2 - 2011 | 3362 | 3444 | FALSE | 24 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline | 0 |  | N/A | 100 | On Schedule | 60 | On Schedule | 60 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline. | 60 | On Schedule | 0 | N/A | 50 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline. | 15 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline. | 40 | Behind schedule due to Environmental Assessment. Construction will shift to 2012 but finish before deadline. | 0 | On Schedule | 2011-08-29 17:50 | 2011-08-29 17:50 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2011 | Q3 | Q3 - 2011 | 4178 | 3937 | FALSE | 20 | Behind schedule due to EA. Construction will shift to 2012 but will finish before deadline. | 0 |  | N/A | 100 | On schedule | 60 | On schedule | 60 | Behind schedule due to EA. Construction will shift to 2012 but finish before deadline. | 60 | On schedule | 0 | N/A | 50 | Behind schedule due to EA. Construction will shift to 2012 but finish before deadline. | 20 | Behind schedule due to EA. Construction will shift to 2012 but finish before deadline. | 40 | Behind schedule due to EA. Construction will shift to 2012 but finish before deadline. | 0 | On schedule | 2011-11-21 10:56 | 2011-11-21 10:56 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2011 | Q4 | Q4 - 2011 | 5042 | 4712 | FALSE | 32 | Behind schedule due to environmental assessment. Construction will shift to 2012, but DCN will finish before the deadline. | 0 |  | N/A | 100 | On schedule. | 80 | On Schedule | 80 | Behind schedule due to environmental assessment. Construction will shift to 2012, but DCN will finish before the deadline. | 80 | On schedule. | 0 | N/A | 90 | Behind schedule due to environmental assessment. Construction will shift to 2012, but DCN will finish before the deadline. | 23 | Behind schedule due to environmental assessment. Construction will shift to 2012, but DCN will finish before the deadline. | 90 | Behind schedule due to environmental assessment. Construction will shift to 2012, but DCN will finish before the deadline. | 20 | On schedule based on fiber miles deployed. | 2012-02-15 15:25 | 2012-02-15 15:25 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2012 | Q1 | Q1 - 2012 | 6294 | 5749 | FALSE | 62 | On Schedule. | 0 |  | N/A | 100 | On Schedule. | 90 | On Schedule. | 90 | On Schedule. | 80 | On Schedule. | 0 | N/A | 100 | On Schedule. | 45 | On Schedule. | 95 | On Schedule. | 40 | On schedule based on fiber miles deployed | 2012-05-25 10:08 | 2012-05-25 10:08 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2012 | Q2 | Q2 - 2012 | 7206 | 6230 | FALSE | 82 | On Schedule. | 0 |  | N/A | 100 | On Schedule. | 100 | On Schedule. | 95 | On Schedule. | 95 | On Schedule. | 0 | N/A | 100 | On Schedule. | 70 | On Schedule. | 95 | On Schedule. | 70 | On schedule based on fiber miles deployed | 2012-08-22 12:45 | 2012-08-22 12:45 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2012 | Q3 | Q3 - 2012 | 8082 | 6747 | FALSE | 87 | On Schedule. | 0 |  | N/A | 100 | On Schedule. | 100 | On Schedule. | 95 | On Schedule. | 95 | On Schedule. | 0 | N/A | 100 | On Schedule. | 80 | On Schedule. | 95 | On Schedule. | 80 | On Schedule based on fiber miles deployed. | 2012-11-27 16:23 | 2012-11-27 16:23 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2012 | Q4 | Q4 - 2012 | 9060 | 7835 | FALSE | 90 | On Schedule. | 0 |  | N/A | 100 | On Schedule. | 100 | On Schedule. | 95 | On Schedule. | 95 | On Schedule. | 0 | N/A | 100 | On Schedule. | 80 | On Schedule. | 95 | On Schedule. | 80 | On Schedule based on fiber miles deployed. | 2013-02-28 11:47 | 2013-02-28 11:47 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2013 | Q1 | Q1 - 2013 | 9704 | 8385 | FALSE | 96 | On Schedule. | 0 |  | N/A | 100 | On Schedule. | 100 | On Schedule. | 100 | On Schedule. | 100 | On Schedule. | 0 | N/A | 100 | On Schedule. | 80 | On Schedule. | 99 | On Schedule. | 95 | On Schedule based on fiber miles deployed. | 2013-05-13 15:55 | 2013-05-13 15:55 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2013 | Q2 | Q2 - 2013 | 10578 | 8945 | FALSE | 100 | On schedule | 0 |  | N/A | 100 | On schedule | 100 | On schedule | 100 | On schedule | 100 | On schedule | 0 | N/A | 100 | On schedule | 100 | On schedule | 100 | On schedule | 100 | On schedule based on fiber miles deployed | 2013-08-14 11:12 | 2013-08-14 11:12 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570090 | 2013 | Q3 | Q3 - 2013 | 11936 | 10104 | FALSE | 100 | On Schedule | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 0 | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-03-07 16:32 | 2014-03-07 16:32 | 6433 | 6433 | DCN, LLC | TRUE
NT10BIX5570091 | 2010 | Q4 | Q4 - 2010 | 1154 | 2195 | FALSE | 32 | None | 50 |  | None | 95 | extended EA deadline to 4/1/11 | 100 | Design will be completed by 3/31/11 | 95 | None | 5 | None | 20 | delayed due to route changes relating to exclusive right-of-ways | 20 | includes RFP process, setting up contracts after bids, no expenditures during quarter | 5 | No actual build will be completed, but work will be completed for contracts and all bids will be recieved | 0 | None | 10 | None | 2011-02-15 17:13 | 2011-02-15 17:13 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2011 | Q1 | Q1 - 2011 | 2224 | 2857 | FALSE | 20 | Delayed due to structure of delayed payments to engineering/environmental firms and construction firms. The delay is also caused by proposing route changes during Q1-2011. Actual expenditures during this perion will not be as high as forecasted in our baseline plan. | 50 |  | None | 100 | None | 100 | None | 100 | None | 5 | The delay caused by the proposed route changes during Q1-2011. This in return will delay the issue of a FONSI delaying construction permits and other approvals. | 10 | The delay caused by the proposed route changes during Q1-2011. This in return will delay the issue of a FONSI delaying construction permits and other approvals. | 10 | The delay caused by the proposed route changes during Q1-2011. This in return will delay the issue of a FONSI delaying construction permits and other approvals. | 10 | The delay caused by the proposed route changes during Q1-2011. This in return will delay the issue of a FONSI delaying construction permits and other approvals. | 20 | The delay caused by the proposed route changes during Q1-2011. This in return will delay the issue of a FONSI delaying construction permits and other approvals. | 0 | The delay caused by the proposed route changes during Q1-2011. This in return will delay the issue of a FONSI delaying construction permits and other approvals. | 2011-05-20 16:00 | 2011-05-20 16:00 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2011 | Q2 | Q2 - 2011 | 2970 | 3242 | FALSE | 15 | The delay will be caused by the approved route changes during Q1-2011. This in return delayed the issue of a Finding of Non Significant Impact on the environment delaying construction permits and other approvals. | 25 | OSS Software | Bluebird Media was focused on the route changes and FONSI during Q1 and Q2 2011 delaying the roll out of OSS software. Bluebird plans to work diligently the next two quarters to implement the software. | 95 | Bluebird Media was issued a Finding of Non Significant Impact on the environment during Q2 2011, continued environmental monitoring during the construction period will be the remaining 5 percent to complete. | 100 | None | 100 | None | 55 | The advance of construction permits and other approvals will be caused by completing agreements with state agencies and starting all fiber build routes during this quarter. | 33 | The delay will be caused by the timing to complete agreements with state agencies. This in return delayed the state site selections delaying the site preparation. | 49 | The advance of equipment procurement will be caused by completing several contracts and starting all fiber build routes during this quarter. | 8 | The delay will be caused by the approved route changes during Q1-2011. This in return delayed the issue of a Finding of Non Significant Impact on the environment delaying construction permits and other approvals. | 10 | The delay will be caused by the approved route changes during Q1-2011. This in return delayed the issue of a Finding of Non Significant Impact on the environment delaying construction permits and other approvals. | 0 | The delay will be caused by the approved route changes during Q1-2011. This in return delayed the issue of a Finding of Non Significant Impact on the environment delaying construction permits and other approvals. | 2011-08-09 12:22 | 2011-08-09 12:22 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2011 | Q3 | Q3 - 2011 | 4250 | 3975 | FALSE | 20 | The delay will be caused by the approved route changes during Q1-2011. This in return delayed the issue of a Finding of Non Significant Impact on the environment delaying construction permits and other approvals. | 50 | OSS Software | Bluebird Media was focused on the route changes and FONSI during Q1 and Q2 2011 delaying the roll out of OSS software. Bluebird entered into agreements with software companies during Q3-2011 and plans to implement the OSS software during Q4-2011. | 95 | Bluebird Media was issued a Finding of Non Significant Impact on the environment during Q2 2011, continued environmental monitoring during the construction period will be the remaining 5 percent to complete. | 100 | None | 100 | None | 75 | The advance of construction permits and other approvals will be caused by completing agreements with Railroad companies and continuing all fiber build routes during this quarter. | 55 | None | 45 | Delay caused by the under estimated amount of time needed to negotiate final equipment contracts. One of two of these contracts were finalized during Q3 2011 and purchase orders have been put in place to procure equipment in Q4 2011. The plan is to catch up to the revised baseline during Q1-2012 once another contract is finalized during Q4-2011 and equipment is shipped during Q1-2012. | 28 | The delay was caused by the approved route changes during Q1-2011. This in return delayed the issue of a Finding of Non Significant Impact on the environment delaying construction permits and other approvals. | 20 | None | 10 | None | 2011-11-23 12:39 | 2011-11-23 12:39 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2011 | Q4 | Q4 - 2011 | 5004 | 4677 | FALSE | 37 | The delay will be caused by not having an independent appraisal completed for the in-kind contribution by the end of the quarter. Currently Bluebird estimated the contribution of $10.5 million. The plan is to catch up to the revised baseline during Q2-2012 once the appraisal of the in-kind contribution has been completed. | 50 | OSS Software | Bluebird entered into agreements with software companies during Q3-2011 and plans to implement the OSS software during Q1-2012. | 95 | None | 100 | None | 100 | None | 85 | The delay will be caused by Bluebird not filling out the appropriate permits until the timing is appropriate. The remaining permits that have yet to be submitted are associated with portions of construction targeted late in the project plan. The plan is to catch up to the revised baseline during Q2-2012. | 75 | The delay will be caused by the approved route changes during Q1-2011. This in return delayed the issue of a Finding of Non Significant Impact on the environment delaying construction permits and other approvals. The plan is to catch up to the revised baseline during Q2-2012. | 63 | Delay caused by the under estimated amount of time needed to negotiate final equipment contracts. The plan is to catch up to the revised baseline during Q2-2012 once equipment is shipped and billed during Q1-2012. | 48 | None | 30 | None | 20 | None | 2012-02-14 15:38 | 2012-02-14 15:38 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2012 | Q1 | Q1 - 2012 | 6116 | 5660 | FALSE | 77 | None | 100 | OSS | None | 95 | None | 100 | None | 100 | None | 95 | The delay will be caused by various permits and other approvals that come up during construction during Q2-2012 that will be unforeseeable. The plan is to catch up to the revised baseline during Q3-2012 completing all permits and approvals. | 100 | None | 90 | The delay will be caused by the timing of recieving equipment and remitting payment for equipment. The delay will also be caused by making final adjustments to equipment orders during Q2-2012 with all equipment being in place by end of Q3-2012. | 90 | All projects have deadlines prior to Q2-2012 ending. Bluebird plans to be ahead of the baseline after this quarter with just laterals left to build. | 50 | None | 30 | None | 2012-05-15 17:27 | 2012-05-15 17:27 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2012 | Q2 | Q2 - 2012 | 6734 | 5993 | FALSE | 88 | None | 100 | OSS Software | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 90 | The delay will be caused by the timing of recieving equipment and remitting payment for equipment. The delay will also be caused by making final adjustments to equipment orders during Q3-2012 with all equipment being in place by early Q4-2012. | 90 | Ahead of schedule due to several build segments being completed during Q3-2012 along with all fiber IRU being signed. | 60 | None | 50 | None | 2012-07-30 17:46 | 2012-07-30 17:46 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2012 | Q3 | Q3 - 2012 | 7986 | 6699 | FALSE | 95 | None | 100 |  | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 95 | The delay will be caused by the timing of recieving equipment and remitting payment for equipment. The delay will also be caused by making final adjustments to equipment orders during Q4-2012 with all equipment being in place by early Q1-2013. | 91 | None | 75 | None | 60 | None | 2012-11-20 16:18 | 2012-11-20 16:18 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2012 | Q4 | Q4 - 2012 | 8456 | 7176 | FALSE | 98 | None | 100 |  | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 98 | The delay will be caused by the timing of recieving equipment and remitting payment for equipment. The delay will also be caused by making final adjustments to equipment orders during Q1-2013 with all equipment being in place and invoiced by late Q1-2013. | 95 | None | 90 | None | 75 | None | 2013-01-30 13:36 | 2013-01-30 13:36 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2013 | Q1 | Q1 - 2013 | 9936 | 8511 | FALSE | 100 | None | 100 |  | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 2013-05-28 14:24 | 2013-05-28 14:24 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2013 | Q2 | Q2 - 2013 | 10478 | 8887 | FALSE | 100 | None | 100 |  | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 2013-08-02 15:24 | 2013-08-02 15:24 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | 2013 | Q3 | Q3 - 2013 | 11584 | 9705 | FALSE | 100 | None | 100 |  | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 100 | None | 2014-01-10 14:05 | 2014-01-10 14:05 | 6101 | 6101 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570093 | 2010 | Q4 | Q4 - 2010 | 894 | 1938 | FALSE | 5 | No Variance | 0 | N/A | No Variance | 100 | No Variance | 90 | No Variance | 100 | No Variance | 100 | No Variance | 0 | No Variance | 13 | No Variance | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-01-29 10:54 | 2011-01-29 10:54 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2011 | Q1 | Q1 - 2011 | 2026 | 2758 | FALSE | 5 | no Variance - With regards to project progression and budget expenditures Citizens and it's contractor have began preliminary Engineering work. Citizens has absorbed all of these costs and will look to get reimbursement for the Federal portion once FONSI has been issued and we can begin drawing down funds. | 0 | N/A | no Variance | 100 | no Variance | 100 | no Variance | 100 | no Variance | 100 | no Variance | 50 | no Variance | 13 | no Variance | 0 | no Variance | 0 | no Variance | 0 | no Variance | 2011-05-13 16:15 | 2011-05-13 16:15 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2011 | Q2 | Q2 - 2011 | 2994 | 3254 | FALSE | 23 | No Variance | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 50 | No Variance | 90 | Citizens worked together with Mid-Atlantic Broadband Cooperative and the Virginia Tech Foundation in order to procure equipment on a large order at a bulk rate for a larger discount. Due to coordinating this bulk order between 4 BTOP projects, we were able to procure the majority of our equipment sooner than originally anticipated. | 5 | Construction will be impacted by the long lead time in obtaining fiber and possibly other materials. | 0 | No Variance | 0 | No Variance | 2011-08-10 11:20 | 2011-08-10 11:20 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2011 | Q3 | Q3 - 2011 | 4070 | 3878 | FALSE | 19 | Citizens had anticipated having approximately 71 miles (39%) of aerial and buried fiber construction completed by the end of quarter 6. Start of construction has been delayed due to the unavailability of fiber optic cable and the delay in getting ship dates for the fiber cable. Starting construction on Contract I and Contract II had been delayed 15 weeks by the end of the 5th quarter and will be approximately 23 weeks behind the original planned start dates by the end of the 6th quarter. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 50 | No Variance | 95 | Citizens worked together with Mid-Atlantic Broadband Cooperative and the Virginia Tech Foundation in order to procure equipment on a large order at a bulk rate for a larger discount. Due to coordinating this bulk order between 4 BTOP projects, we were able to procure the majority of our equipment sooner than originally anticipated. The order was placed in the 5th quarter and received and paid for during the 6th quarter. | 9 | Citizens had anticipated having 38% of the network construction completed by the end of the 6th quarter. Construction will be impacted by the long lead time in obtaining fiber cable and other materials. | 0 | No Variance | 0 | No Variance | 2011-11-16 14:33 | 2011-11-16 14:33 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2011 | Q4 | Q4 - 2011 | 4638 | 4282 | FALSE | 26 | Citizens had anticipated having approximately 89 miles (47%) of aerial and buried fiber construction complete by the end of quarter 7. Start of construction has been delayed due to the unavailability of fiber optic cable. Starting construction on Contract I and Contract II has been delayed approximately 23 weeks by the end of the 6th quarter. Citizens, Thompson&Litton, and the contractors are exploring options on how to increase production and bring the milestones in line with the original projections. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | Citizens had projected having 50% of the site work completed for the two telecommunication huts proposed in the project. The contractor expedited this work in order to beat the winter season. The Pulaski site has a small amount of cleanup work remaining to be completed at the end of the quarter. | 95 | Citizens worked together with Mid-Atlantic Broadband Cooperative and the Virginia Tech Foundation in order to procure equipment on a large order at a bulk rate for a larger discount. Due to coordinating this bulk order between 4 BTOP projects, we were able to procure the majority of our equipment sooner than originally anticipated. The order was placed in the 5th quarter and received in the 6th quarter. | 23 | Citizens had anticipated having 47% of the network construction completed by the end of the 7th quarter. Construction has been impacted by the long lead time in obtaining fiber cable and other materials. Citizens had anticipated having 38% of the network construction completed by the end of the 6th quarter. Construction will be impacted by the long lead time in obtaining fiber cable and other materials. | 0 | No Variance | 0 | No Variance | 2012-01-30 10:37 | 2012-01-30 10:37 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2012 | Q1 | Q1 - 2012 | 5812 | 5505 | FALSE | 38 | Citizens had anticipated having 69% of the network construction completed by the end of the 8th quarter. Construction was impacted by the long lead time in obtaining fiber cable and other materials. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 56 | Citizens had anticipated having 68% of the network construction completed by the end of the 8th quarter. Construction was impacted by the long lead time in obtaining fiber cable and other materials. If Network build continues at the current pace, the project will be within 12% of the original projected milestones by the end of the 8th quarter. | 0 | Citizens had anticipated having 60% of the equipment installed at the end of the 8th quarter. Delays in starting construction due to the lead time of fiber cable and waiting for approval of the EA has limited the amount of Equipment Deployment. | 20 | No Variance | 2012-04-30 16:37 | 2012-04-30 16:37 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2012 | Q2 | Q2 - 2012 | 7148 | 6201 | FALSE | 57 | Lag time between construction being completed and invoices being created, verified, and approved represents the difference between the overall project and the Network Build. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 89 | Citizens had projected having approximately 144 miles (77%) of aerial and buried fiber construction complete by the end of quarter 9. At the current pace and schedule, the project should be ahead of the original projections by the end of this quarter. | 60 | No Variance | 68 | No Variance | 2012-08-20 09:57 | 2012-08-20 09:57 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2012 | Q3 | Q3 - 2012 | 7948 | 6679 | FALSE | 84 | Citizens originally projected having 93% of the project complete by the end of the 10th Quarter. Since this Milestone is calculated on Federal Funds that have been spent, the delay in percentage complete is due to the delay in invoicing from the Contractors performing the construction. Actual construction on the project is projected to be 100% complete at the end of the 10th Quarter. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | Citizens had projected having approximately 173 miles (93%) of aerial and buried fiber construction complete by the end of quarter 10. At the current pace and schedule of the construction, the project should be ahead of the original projections by the end of this quarter. | 80 | No Variance | 77 | No Variance | 2012-11-19 08:56 | 2012-11-19 08:56 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2012 | Q4 | Q4 - 2012 | 8432 | 7129 | FALSE | 85 | Citizens originally projected having 95% of the project complete by the end of the 11th Quarter. Since this Milestone is calculated on Federal Funds that have been spent, the delay in percentage complete is due to the delay in invoicing from the Contractors performing the construction. Actual construction on the project is projected to be 96% complete at the end of the 11th Quarter. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 96 | No Variance | 80 | No Variance | 96 | All testing should be finished on all completed fiber. Only the construction delayed by make-ready issues will remain. | 2013-01-30 10:52 | 2013-01-30 10:52 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2013 | Q1 | Q1 - 2013 | 10026 | 8563 | FALSE | 94 | Citizens originally projected having 100% of the project complete by the end of the 12th Quarter. Since this Milestone is calculated on Federal Funds that have been spent, the delay in percentage complete is due to the delay in invoicing from the Contractors performing the construction. Actual construction on the project is projected to be 100% complete at the end of the 12th Quarter. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-05-31 14:47 | 2013-05-31 14:47 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2013 | Q2 | Q2 - 2013 | 10774 | 9052 | FALSE | 96 | Citizens originally projected this amount to be 100% by the end of the project. Since this percentage is calculated on actual expenditures and Citizens will be coming in under budget on the project, this amount is lower than 100%. As of the end of the project on July 31, 2013, 100% of the project was complete. | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-08-27 16:42 | 2013-08-27 16:42 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | 2013 | Q3 | Q3 - 2013 | 11470 | 9583 | FALSE | 100 | No Variance | 100 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-12-11 11:40 | 2013-12-11 11:40 | 6099 | 6099 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570094 | 2010 | Q4 | Q4 - 2010 | 556 | 1575 | FALSE | 22 | N/A | 7 | Engineering Services | N/A | 0 | N/A | 21 | N/A | 0 | N/A | 0 | N/A | 100 | N/A | 20 | N/A | 43 | N/A | 4 | N/A | 0 | N/A | 2011-01-26 16:14 | 2011-01-26 16:14 | 5293 | 5293 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2011 | Q1 | Q1 - 2011 | 2018 | 2754 | FALSE | 15 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds and "BTOP Grant" payments for microwave link design and certain MEDCOM equipment during the 4th quarter (2nd Calendar Quarter 2011). Projected payments for microwave equipment is now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. The continuing efforts by the FCC and the ERIC Committee have impacted the State's ability to define the technical specifications in our procurement instructions. | 11 | Engineering Services | The State anticipated procurement activities for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds and "BTOP Grant" payments for microwave link design and certain MEDCOM equipment during the 4th quarter (2nd Calendar Quarter 2011). Projected payments for microwave equipment is now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. The continuing efforts by the FCC and the ERIC Committee have impacted the State's ability to define the technical specifications in our procurement instructions. | 0 | N/A | 13 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds and "BTOP Grant" payments for microwave link design and certain MEDCOM equipment during the 4th quarter (2nd Calendar Quarter 2011). Projected payments for microwave equipment is now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. The continuing efforts by the FCC and the ERIC Committee have impacted the State's ability to define the technical specifications in our procurement instructions. | 0 | N/A | 0 | N/A | 0 | Site preparation for equipment at UMMC has been delayed until Year 2 Q1. | 11 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds and "BTOP Grant" payments for microwave link design and certain MEDCOM equipment during the 4th quarter (2nd Calendar Quarter 2011). Projected payments for microwave equipment is now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. The continuing efforts by the FCC and the ERIC Committee have impacted the State's ability to define the technical specifications in our procurement instructions. | 37 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds and "BTOP Grant" payments for microwave link design and certain MEDCOM equipment during the 4th quarter (2nd Calendar Quarter 2011). Projected payments for microwave equipment is now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. The continuing efforts by the FCC and the ERIC Committee have impacted the State's ability to define the technical specifications in our procurement instructions. | 9 | No variance from baseline. | 0 | No variance from baseline. | 2011-05-13 14:49 | 2011-05-13 14:49 | 5293 | 5293 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2011 | Q2 | Q2 - 2011 | 3050 | 3282 | FALSE | 32 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds, "BTOP Grant" payments for microwave link design, initial LTE engineering design and certain MEDCOM equipment during the next quarter (3rd Calendar Quarter 2011). Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. Projected payments for LTE Core and eNodeB equipment will be based on a negotiated project schedule and payment milestones in the LTE Broadband contract currently in negotiations with Motorola Solutions, Inc. | 32 |  | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds, "BTOP Grant" payments for microwave link design, initial LTE engineering design and certain MEDCOM equipment during the next quarter (3rd Calendar Quarter 2011). Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. Projected payments for LTE Core and eNodeB equipment will be based on a negotiated project schedule and payment milestones in the LTE Broadband contract currently in negotiations with Motorola Solutions, Inc. | 0 | N/A | 42 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds, "BTOP Grant" payments for microwave link design, initial LTE engineering design and certain MEDCOM equipment during the next quarter (3rd Calendar Quarter 2011). Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. Projected payments for LTE Core and eNodeB equipment will be based on a negotiated project schedule and payment milestones in the LTE Broadband contract currently in negotiations with Motorola Solutions, Inc. | 0 | N/A | 0 | N/A | 100 | Site preparation for equipment at UMMC has been delayed until Year 2 Q1. | 25 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds, "BTOP Grant" payments for microwave link design, initial LTE engineering design and certain MEDCOM equipment during the next quarter (3rd Calendar Quarter 2011). Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. Projected payments for LTE Core and eNodeB equipment will be based on a negotiated project schedule and payment milestones in the LTE Broadband contract currently in negotiations with Motorola Solutions, Inc. | 62 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds, "BTOP Grant" payments for microwave link design, initial LTE engineering design and certain MEDCOM equipment during the next quarter (3rd Calendar Quarter 2011). Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. Projected payments for LTE Core and eNodeB equipment will be based on a negotiated project schedule and payment milestones in the LTE Broadband contract currently in negotiations with Motorola Solutions, Inc. | 21 | No variance from baseline. | 13 | No variance from baseline. | 2011-08-12 15:14 | 2011-08-12 15:14 | 5293 | 5293 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2011 | Q3 | Q3 - 2011 | 4368 | 4040 | FALSE | 37 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds, "BTOP Grant" payments for microwave link design, initial LTE engineering design and certain MEDCOM equipment during the next quarter. Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. Planned percentages are based on the negotiated project schedule and payment milestones in the LTE Broadband contract executed on August 11, 2011 with Motorola Solutions, Inc. | 66 |  | Microwave backhaul project management components of payment milestones will occur during the fourth quarter. initial milestones for training of state staff on eNodeBs will also occur during the quarter. | 0 | N/A | 59 | Significant payment milestones for the LTE microwave backhaul network engineering design services will be achieved during the next quarter. The first contractual payment milestone for the design and provisioning of eNodeBs will occur in the fourth quarter 2011. | 0 | N/A | 0 | N/A | 100 | Site preparation for equipment at UMMC has been delayed until Year 2 Q2. | 28 | The detailed design plan approval milestone for the eNodeBs will be achieved during next quarter. Microwave backhaul installation, integration and acceptance testing milestones will be achieved for the sites in MSWIN Phase 2. MS MedCom is scheduled to complete procurement of a major component of their ambulance data transmission equipment. | 58 | Payment milestones will be met on the design for 5 new MSWIN towers that will be used as BTOP match. Tower lease payments (Cash Match) will continue on leased tower sites. Due Diligence payments on Phase 3 tower sites(cash Match, will be paid during the fourth quarter, 2011. | 16 | Contractual payment milestones for the detailed design on the Core and eNodeB network will be achieved during the fourth quarter. Delivery of eNode B equipment to the tower sites will begin during the fourth quarter. | 0 | Baseline for year 2 quarter 2 is 25%. Network testing will not begin during the next quarter. | 2011-12-02 09:56 | 2011-12-02 09:56 | 5293 | 5293 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2011 | Q4 | Q4 - 2011 | 5044 | 4718 | FALSE | 37 | The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds, "BTOP Grant" payments for microwave link design, initial LTE engineering design and certain MEDCOM equipment during the next quarter. Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the contract Change Order with the State's MSWIN vendor. Planned percentages are based on the negotiated project schedule and payment milestones in the LTE Broadband contract executed on August 11, 2011 with Motorola Solutions, Inc. | 54 |  | Microwave backhaul project management components of payment milestones will occur during the quarter. | 0 | N/A | 7 | Significant payment milestones for the LTE microwave backhaul network engineering design services will be achieved during the next quarter. The first contractual payment milestone for the design and provisioning of eNodeBs will occur in the first quarter 2012. | 0 | N/A | 0 | N/A | 0 | The site preparation has been delayed for two reasons. First, Mississippi MED-COM is housed in the State of Mississippiâ€™s only Level I Trauma center and there are three large construction projects going on in and around MED-COMâ€™s physical location. Our construction is a component of the three other larger programs in terms of allocation of resources, generator emergency power allocation and to ensure that our current MED-COM operations will not be hampered by loss of electrical, HVAC or other utilities during the three construction projects. The expansion of the equipment room is into physical space currently used by our Cardiovascular Services- a mission critical component of the medical center. We have been waiting re-location of that service for a smaller than originally planned portion of that area. Second- we have been awaiting the final electrical specifications of the PSAP component of the grant- in order to have completed the electrical planning and quotation. Those | 34 | The detailed design plan approval milestone for the Core will be achieved during next quarter. Microwave backhaul installation, integration and acceptance testing milestones will be achieved for the sites in MSWIN Phase 2 C& D. 33 sets of antenna arrays will be installed on MSWIN sites. The eNodeB equipment will be delivered to 45 MSWIN sites. | 46 | Payment milestones will be met on the design for 5 new MSWIN towers that will be used as BTOP match. Tower lease payments (Cash Match) will continue on leased tower sites. | 49 | The detailed design plan approval milestone for the RAN equipment will be achieved during the next quarter. | 0 | Baseline for year 2 quarter 3 is 37.5%. Network testing will begin once the core is delivered to ITS and some of the LTE sites are brought up. This is projected to begin in second quarter 2012. | 2012-02-15 16:36 | 2012-02-15 20:16 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2012 | Q1 | Q1 - 2012 | 5832 | 5515 | FALSE | 46 | The LTE Core will be installed at the State Data Center and the core is expected to be tested and fully operational during this quarter. The remainder of the 135 eNodeB's will be delivered to the warehouse in Mississippi and delivered directly to the LMR tower sites. 25 eNodeBs will be installed at tower sites in the central part of the State. 50 sets of LTE antenna arrays will be installed on MSWIN sites during the quarter. The construction of the Tower Sites in North Mississippi being used by match by the State will be complete. The microwave backhaul equipment will be installed for 40 MSWIN LTE network links. The State anticipated procurement activities and manufacturing for microwave links and MS MEDCOM access equipment to take less time than it has. The revised budget reflects primarily "Match" payments of tower leases, engineering services, tower builds. Projected payments for microwave equipment are now based on a negotiated project schedule and payment milestones in the | 51 |  | Microwave backhaul project management components of payment milestones will occur during the quarter. Engineering services for training of state staff will be performed. | 0 | N/A | 32 | Significant payment milestones for the LTE microwave backhaul network engineering design services will be achieved during the next quarter. The system integration for the eNodeBs will continue during the next quarter. | 0 | N/A | 0 | N/A | 0 | As the site preparation construction is completed, the next phase includes the installation of various components of the new infrastructure equipment (console furniture, PSAP system, PTP MSWIN connection). As installation is completed, the next phase will be testing and acceptance of the new hardware and software. Employee training has been scheduled following anticipated equipment acceptance. | 42 | The LTE Core will be installed at the State Data Center and the core is expected to be tested and fully operational during this quarter. The remainder of the 135 eNodeB's will be delivered to the warehouse in Mississippi and delivered directly to the LMR tower sites. 25 eNodeBs will be installed at tower sites in the central part of the State. 50 sets of LTE antenna arrays will be installed on MSWIN sites during the quarter. The microwave backhaul equipment will be installed for 40 MSWIN LTE network links. | 69 | Payment milestones will be met on all of the MSWIN tower sites that are being used as BTOP match. Tower lease payments (cash match) will continue on leased tower sites. The microwave backhaul equipment will be installed for 40 MSWIN LTE network links. | 45 | The LTE Core will be installed at the State Data Center and the core is expected to be tested and fully operational during this quarter. The remainder of the 135 eNodeB's will be delivered to the warehouse in Mississippi and delivered directly to the LMR tower sites. 25 eNodeBs will be installed at tower sites in the central part of the State. 50 sets of LTE antenna arrays will be installed on MSWIN sites during the quarter. | 0 | Network testing will begin once the core is delivered to ITS and some of the LTE sites are brought up. This testing is projected to begin in QTR 3, 2012. | 2012-04-30 17:21 | 2012-04-30 17:21 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2012 | Q2 | Q2 - 2012 | 7044 | 6149 | FALSE | 51 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. The State anticipates the microwave backhaul equipment will be installed for 25 MSWIN LTE network links. | 57 |  | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. The State anticipates the microwave backhaul equipment will be installed for 25 MSWIN LTE network links. | 0 | N/A | 52 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. The State anticipates the microwave backhaul equipment will be installed for 25 MSWIN LTE network links. | 0 | N/A | 0 | N/A | 3 | As the site construction is completed (approximately $2400.00), the next steps will include testing and acceptance of the new consoles and software. | 45 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. The State anticipates the microwave backhaul equipment will be installed for 25 MSWIN LTE network links. | 77 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. The State anticipates the microwave backhaul equipment will be installed for 25 MSWIN LTE network links. | 45 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. The State anticipates the microwave backhaul equipment will be installed for 25 MSWIN LTE network links. | 0 | N/A | 2012-08-13 14:36 | 2012-08-13 14:36 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2012 | Q3 | Q3 - 2012 | 7864 | 6636 | FALSE | 54 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3, delivery of EnodeBs to MSWIN tower sites, Antenna and Line installs for 20 MSWIN tower sites, services related to the LTE core, and microwave services for Phase 2 and Phase 3 tower sites. The State anticipates the microwave backhaul equipment will be installed for 20 MSWIN LTE network links. | 78 |  | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include microwave services for Phase 2 and Phase 3 tower sites. | 0 | N/A | 65 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3, services related to the LTE core, and microwave services for Phase 2 and Phase 3 tower sites. | 0 | N/A | 0 | N/A | 1 | No site work is expected | 46 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include microwave services for Phase 2 and Phase 3 tower sites. | 88 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3 and microwave services for Phase 2 and Phase 3 tower sites. | 44 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for Antenna and Line installs for 20 MSWIN tower sites. The State anticipates the microwave backhaul equipment will be installed for 20 MSWIN LTE network links. | 0 | N/A | 2012-11-14 09:36 | 2012-11-14 09:36 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2012 | Q4 | Q4 - 2012 | 8842 | 7626 | FALSE | 50 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3, delivery of EnodeBs to MSWIN tower sites, Antenna and Line installs for 20 MSWIN tower sites and services related to the LTE core. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if Davis Bacon Act compliance issues are resolved. | 61 |  | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if Davis Bacon Act compliance issues are resolved. | 0 | N/A | 51 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3, services related to the LTE core. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if Davis Bacon Act compliance issues are resolved. | 0 | N/A | 0 | N/A | 4 | No actual work site preparation is expected. Outstanding invoices for smaller portions of the project are pending drawdown completion. Examples of outstanding invoices include but are not limited to additional emergency power switches and fees to relocate work-stations. | 42 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. | 86 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if we are able to resolve issues issues related to the Davis Bacon Act. | 44 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for Antenna and Line installs for 20 MSWIN tower sites. The State anticipates payment milestones being met for the installation of 20 MSWIN LTE network links if Davis Bacon Act compliance issues are resolved during the quarter. | 0 | N/A | 2013-02-19 14:59 | 2013-02-21 10:36 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2013 | Q1 | Q1 - 2013 | 9694 | 8380 | FALSE | 51 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3, delivery of EnodeBs to MSWIN tower sites, Antenna and Line installs for 20 MSWIN tower sites and services related to the LTE core. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if Davis Bacon Act compliance issues are resolved. | 61 |  | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if Davis Bacon Act compliance issues are resolved. | 0 | N/A | 51 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3, services related to the LTE core. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if Davis Bacon Act compliance issues are resolved. | 0 | N/A | 0 | N/A | 4 | LMR installation continues. Two informational meetings were held in north Mississippi for area hospital and emergency service personnel. The meetings outlined the LMR component of the grant project. | 42 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. | 89 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for the approval of the Detail Design Plan for Phase 3. Additional milestones related to microwave installation in Phase 3 may be achieved during this quarter if we are able to resolve issues issues related to the Davis Bacon Act. | 44 | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. This should include payment milestones for Antenna and Line installs for 20 MSWIN tower sites. The State anticipates payment milestones being met for the installation of 20 MSWIN LTE network links if Davis Bacon Act compliance issues are resolved during the quarter. | 0 | N/A | 2013-05-13 14:43 | 2013-05-13 14:43 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2013 | Q2 | Q2 - 2013 | 10300 | 8766 | FALSE | 49 | We expect to install 23 new microwave links this quarter and perform Microwave integration milestones for 43 new sites. | 60 |  | We expect to install 23 new microwave links this quarter and perform Microwave integration milestones for 43 new sites. | 0 | N/A | 38 | We expect to install 23 new microwave links this quarter and perform Microwave integration milestones for 43 new sites. | 0 | N/A | 0 | N/A | 2 | Labor and materials for installation of electrical receptacles connected to existing emergency power circuits and fire stop | 43 | WCC:We expect to install 23 new microwave links this quarter and perform Microwave integration milestones for 43 new sites. MedCom: - Labor and materials for installation of electrical receptacles connected to existing emergency power circuits and fire stop conduits. | 85 | We expect to install 23 new microwave links this quarter and perform Microwave integration milestones for 43 new sites. | 43 | We expect to install 23 new microwave links this quarter and perform Microwave integration milestones for 43 new sites. | 0 | N/A | 2013-07-30 10:56 | 2013-07-30 10:56 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2013 | Q3 | Q3 - 2013 | 11410 | 9522 | FALSE | 55 | WCC: No additional work/payments expected to be processed this quarter. MedCom: Expected work/payments for: Completion of physical site upgrades to accommodate additional consoles in MedCom, door installation, electrical upgrades and lighting on emergency power circuits, fire-caulking around wall penetrations. Purchase, reconfiguration and integration of Microwave link, purchase and integration of 2 additional consoles, purchase of PSAP phone system with additional hardware and line cards | 78 |  | No additional work/payments expected to be processed this quarter. | 0 | N/A | 61 | No additional work/payments expected to be processed this quarter. | 0 | N/A | 0 | N/A | 6 | MedCom: Completion of physical site upgrades to accommodate additional consoles in MedCom: door installation, electrical upgrades and lighting on emergency power circuits, fire-caulking around wall penetrations. | 47 | WCC: No additional work/payments expected to be processed this quarter. MedCom: Purchase, reconfiguration and integration of Microwave link, purchase and integration of 2 additional consoles, purchase of PSAP phone system with additional hardware and line cards | 95 | No additional work/payments expected to be processed this quarter. | 44 | No additional work/payments expected to be processed this quarter. | 0 | Budget modification removed this category as a tracking component of the Grant reporting. | 2013-11-26 16:50 | 2013-11-26 16:50 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | 2013 | Q4 | Q4 - 2013 | 11708 | 9846 | FALSE | 54 | Mississippi filed a BTOP Modification with NTIA in December and requested additional time to work with FirstNet and develop a sustainable business model for the LTE Network & to be allowed to use BTOP funds to purchase multi-band devices for first responders which could be used on Band Class 14 at a later date. The BTOP Modification request was denied, without any request for clarification, and NTIA notified Mississippi that the Grant is considered terminated as of December 31, 2013. | 78 |  | Mississippi filed a BTOP Modification with NTIA in December and requested additional time to work with FirstNet and develop a sustainable business model for the LTE Network & to be allowed to use BTOP funds to purchase multi-band devices for first responders which could be used on Band Class 14 at a later date. The BTOP Modification request was denied, without any request for clarification, and NTIA notified Mississippi that the Grant is considered terminated as of December 31, 2013. | 0 | N/A | 61 | Mississippi filed a BTOP Modification with NTIA in December and requested additional time to work with FirstNet and develop a sustainable business model for the LTE Network & to be allowed to use BTOP funds to purchase multi-band devices for first responders which could be used on Band Class 14 at a later date. The BTOP Modification request was denied, without any request for clarification, and NTIA notified Mississippi that the Grant is considered terminated as of December 31, 2013. | 0 | N/A | 0 | N/A | 2 | No construction or site preparation activities are anticipated. | 45 | Mississippi filed a BTOP Modification with NTIA in December and requested additional time to work with FirstNet and develop a sustainable business model for the LTE Network & to be allowed to use BTOP funds to purchase multi-band devices for first responders which could be used on Band Class 14 at a later date. The BTOP Modification request was denied, without any request for clarification, and NTIA notified Mississippi that the Grant is considered terminated as of December 31, 2013. MedCom: Installation of land mobile and hospital radios, control station and antenna. | 95 | Mississippi filed a BTOP Modification with NTIA in December and requested additional time to work with FirstNet and develop a sustainable business model for the LTE Network & to be allowed to use BTOP funds to purchase multi-band devices for first responders which could be used on Band Class 14 at a later date. The BTOP Modification request was denied, without any request for clarification, and NTIA notified Mississippi that the Grant is considered terminated as of December 31, 2013. | 44 | Mississippi filed a BTOP Modification with NTIA in December and requested additional time to work with FirstNet and develop a sustainable business model for the LTE Network & to be allowed to use BTOP funds to purchase multi-band devices for first responders which could be used on Band Class 14 at a later date. The BTOP Modification request was denied, without any request for clarification, and NTIA notified Mississippi that the Grant is considered terminated as of December 31, 2013. | 0 | Budget modification removed this category as a tracking component of the Grant reporting. | 2014-01-30 10:45 | 2014-01-30 10:45 | 7345 | 7345 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570095 | 2010 | Q4 | Q4 - 2010 | 1020 | 2064 | FALSE | 10 | Timing circumstances around FONSI receipt expected to push actual. | 0 | N/A | N/A | 100 | N/A | 75 | RF Propagation redesign(s) required. | 100 | N/A | 100 | N/A | 0 | N/A | 25 | N/A | 25 | N/A | 0 | N/A | 0 | N/A | 2011-02-09 12:25 | 2011-02-09 12:25 | 5990 | 5990 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2011 | Q1 | Q1 - 2011 | 1924 | 2707 | FALSE | 10 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 0 |  | N/A | 100 | N/A | 75 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 100 | N/A | 75 | US Forestry Service lost our initial application and generated delays until it was located. | 0 | N/A | 0 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 15 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 0 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 0 | N/A | 2011-05-10 11:56 | 2011-05-10 11:56 | 5990 | 5990 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2011 | Q2 | Q2 - 2011 | 2954 | 3234 | FALSE | 25 | Finding of No Significant Impact (FONSI) was delayed beyond the projected time, decreasing the activities that could be undertaken. Also, the tsunami in Japan created a world wide fiber shortage and increased our delivery time line for fiber cable by ten weeks. | 0 |  | n/a | 100 | n/a | 85 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 100 | n/a | 75 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 0 | n/a | 0 | Delays in receiving FONSI has delayed all construction related baseline time lines. | 15 | Finding of No Significant Impact (FONSI) was delayed beyond the projected time, decreasing the activities that could be undertaken. Also, the tsunami in Japan created a world wide fiber shortage and increased our delivery time line for fiber cable by ten weeks. | 0 | Finding of No Significant Impact (FONSI) was delayed beyond the projected time, decreasing the activities that could be undertaken. Also, the tsunami in Japan created a world wide fiber shortage and increased our delivery time line for fiber cable by ten weeks. Equipment should begin in 1st qtr 2012. | 0 | n/a | 2011-08-08 13:44 | 2011-08-08 13:44 | 5990 | 5990 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2011 | Q3 | Q3 - 2011 | 4198 | 3947 | FALSE | 29 | Environmental Assessments, US Forestry permitting and world wide fiber shortages have caused significant variances to our project. Construction will begin in the upcoming quarter, therefore funds will be obligated but not necessarily expensed until the following quarter. | 0 |  | N/A | 100 | Complete | 85 | Low-cost engineering firm was producing incomplete and inaccurate documentation. We were required to release the initial engineering firm and hire a new firm. | 100 | complete | 77 | Delays due to Environmental Assessments and permitting with US Forestry have delayed state approvals. Poor quality engineering with our initial firm is requiring re-work of several permit applications. | 0 | N/A | 0 | All installation of equipment is delayed due to the construction delays releated to receipt of the FONSI last quarter. | 34 | Changes with the networks of two partners have caused significant delays in the proposed leases and IRUs. We anticipate the following quarter, going into 2012 to reflect a percentage change in this category. | 0 | N/A | 0 | N/A | 2011-11-21 17:01 | 2011-11-21 17:01 | 5990 | 5990 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2011 | Q4 | Q4 - 2011 | 4900 | 4588 | FALSE | 33 | Previous reports detailed the delays with FONSI and tsunami issues for fiber delivery, as well as delays with initial engineering firm. Construction has commenced with fiber placement initiated and connectivity to 3 CAI's in 1Q2012. Outstanding permit issues will be resolved allowing for additional construction crew(s) deployment. Equipment delivery will commence and critical collocation agreements are finalized allowing site preparation and equipment installation. Wireless RF Engineering will be finalized during 1Q2012 for preparation of equipment selection in 2Q2012. | 0 |  | N/A | 100 | complete | 90 | Previous reports detailed the delays with FONSI and tsunami issues. Design is being held open to accommodate changes required by construction issues. Additional changes may be driven by CAI (Community Anchor Institutions) changes (some CAIs have moved or ceased operations) and FCC (Federal Communications Commission) rule changes to the wireless component. | 90 | Previous reports detailed the delays with FONSI and tsunami issues, hindering permit applications. Additional delays in permitting have been driven by poor performance of original engineering firm, staff shortages in Alabama DOT; previously unplanned road construction and construction driven changes. | 95 | Previous reports detailed the delays with FONSI and tsunami issues. Additional delays in permitting have been driven by poor performance of original engineering firm, staff shortages in Alabama DOT; unplanned road construction and construction driven changes. | 0 | N/A | 35 | Network construction has been delayed as noted above, reducing the requirement to purchase equipment earlier. However, responses to Request for Proposals were completed this quarter and narrowed to 3 vendors with final selection due early January. | 40 | Previous reports detailed the delays with FONSI and tsunami issues. Additional delays in permitting have been driven by poor performance of original engineering firm, staff shortages in Alabama DOT, new previously unplanned road construction and construction driven changes. Acquisition of leased/IRU fibers have been hampered by economic impact of tornadoes to James Cable and the withdrawal of AFO from the project. | 25 | Network construction has been delayed as noted in 2g above, reducing the requirement to purchase equipment earlier. | 5 | Testing for the McClellan campus and Main Campus for Jacksonville State University will be completed this quarter, allowing us to begin testing earlier than expected. | 2012-02-07 12:02 | 2012-02-07 12:02 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2012 | Q1 | Q1 - 2012 | 6262 | 5733 | FALSE | 77 | N/A | 0 | N/A | N/A | 100 | N/A | 95 | N/A | 95 | N/A | 95 | N/A | 100 | N/A | 50 | N/A | 75 | N/A | 70 | N/A | 50 | N/A | 2012-05-23 11:09 | 2012-05-23 11:09 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2012 | Q2 | Q2 - 2012 | 6838 | 6045 | FALSE | 81 | On track with PIP filed in first quarter | 0 |  | n/a | 100 | n/a | 90 | On track with PIP filed in first quarter | 90 | On track with PIP filed in first quarter | 90 | On track with PIP filed in first quarter | 0 | n/a | 50 | On track with PIP filed in first quarter | 75 | On track with PIP filed in first quarter | 50 | On track with PIP filed in first quarter | 30 | On track with PIP filed in first quarter | 2012-08-02 12:22 | 2012-08-02 12:22 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2012 | Q3 | Q3 - 2012 | 7774 | 6584 | FALSE | 88 | N/A | 0 | N/A | N/A | 100 | N/A | 96 | N/A | 96 | N/A | 96 | N/A | 0 | N/A | 65 | N/A | 80 | N/A | 60 | N/A | 35 | N/A | 2012-11-06 12:02 | 2012-11-06 12:02 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2012 | Q4 | Q4 - 2012 | 8984 | 7762 | FALSE | 98 | N/A | 0 | N/A | N/A | 100 | N/A | 99 | N/A | 99 | N/A | 99 | N/A | 0 | N/A | 99 | N/A | 90 | Negotiations for the planned IRU from Southern Company have become much more difficult that originally envisioned and may be difficult to complete by end of next quarter. | 90 | N/A | 99 | N/A | 2013-02-26 15:09 | 2013-02-26 15:09 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2013 | Q1 | Q1 - 2013 | 9952 | 8520 | FALSE | 99 | N/A | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 90 | N/A | 100 | N/A | 2013-05-28 20:29 | 2013-05-28 20:29 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2013 | Q2 | Q2 - 2013 | 10550 | 8929 | FALSE | 99 | n/a | 0 |  | n/a | 100 | n/a | 100 | n/a | 100 | n/a | 100 | n/a | 100 | n/a | 100 | n/a | 100 | n/a | 99 | Selected vender for TVWS RF network has withdrawn from the market and we will need to find alternative manufacturer or alternate technology | 100 | n/a | 2013-08-09 18:22 | 2013-08-09 18:22 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | 2013 | Q3 | Q3 - 2013 | 11948 | 10117 | FALSE | 100 | N/A | 0 |  | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 0 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 2014-03-13 17:04 | 2014-03-13 17:04 | 5988 | 5988 | JKM Consulting, Inc. | TRUE
NT10BIX5570096 | 2010 | Q4 | Q4 - 2010 | 1380 | 2392 | FALSE | 2 | Project is on schedule. All field verification will be completed this quarter | 0 |  | N/A | 100 | Enronmental Assessment will be completed. FONSI expected by March 15, 2011. | 25 | We are seeking ways to improve upon this number. | 25 | We may improve upon this number since move FAP sites are on Government owned property. | 30 | We may improve upon this number since move FAP sites are on Government owned property. | 10 | We are on target here but will seek to improve upon it since most of the FAP sites are on Government property. | 5 | We may improve upon this number since we plan to preconfigure the network gear before shipping to the NAP of Americas. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-25 16:57 | 2011-02-25 16:57 | 5238 | 5238 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2011 | Q1 | Q1 - 2011 | 2236 | 2863 | FALSE | 35 | We expect to exceed this number since we anticipate paying up front for our long term IRU agreements. | 15 |  | We anticipate no variance from the the baseline plan. | 100 | We expect no variance from the baseline plan since we fully expect to have received our FONSI. | 100 | We anticipate no variance from the the baseline plan. | 50 | We anticipate no variance from the the baseline plan. The rights of way are primarily on government property; consequently, much of the expenses will be incurred trying to negotiate with private owners. We expect to expend project funds in this category. | 50 | We anticipate no variance from the the baseline plan. Our approach will be combining our permitting applications for as many parts of the construction routes as possible. Road construction represents over 50% of the project permitting requirement. We will be submitting the permits for the road construction by next quarter. We anticipate to receive permitting within the quarter; therefore, we believe we will be at better than 50% completed in this category by the end of June 2011. | 35 | Achievement of this goal by the end of June 2011 is ambitious. Underachievement will not have a dire impact on the project overall since FAPs will be significantly complete before network completion. We will continue permitting en masse and will manage the outcome to overall achievement. | 25 | We anticipate no variance from the the baseline plan. Once the construction of the local FAPs begin we also anticipate that we may exceed this number very easily with the placement of network equipment in our own FAPs and at CAI locations. | 15 | We expect to significantly exceed this number since we expect to complete our IRU negotiations and make up front payments for long term leases and IRUs, filing of applicable and appropriate Award Action Requests notwithstanding. | 10 | We may exceed this number since we expect to deploy network gear in at least three collocation facilities. Also, once the construction of the local FAPs begin we also anticipate that we may exceed this number very easily with the placement of network equipment in our own FAPs and at CAI locations. | 10 | We anticipate no variance from the the baseline plan. | 2011-05-20 22:56 | 2011-05-20 22:56 | 5238 | 5238 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2011 | Q2 | Q2 - 2011 | 3376 | 3451 | FALSE | 43 | No variance from the baseline plan. Despite where we are in the current quarter, we believe we can make up the stagger very quickly with the execution of the IRU contracts and MOA with VIWAPA. Other material purchases for the underground network system and the beginning of major construction for the FAPs and the underground duct bank system will pick up pace over the next three months. | 25 | n/a | No variance from the baseline plan. | 100 | No variance from the baseline plan. | 100 | No variance from the baseline plan. | 50 | We expect to have have a significant reduction in expenditures in this category since a decision has been made to locate over 80% of FAP sites on Government property. this will reduce the need to expend major funds in this category. | 100 | We anticipate being ahead of the baseline plan on this milestone. | 50 | No variance from the baseline plan. | 35 | No variance from the baseline plan. | 25 | No variance from the baseline plan. Execution of the Global Crossing IRU contracts and finalizing the MOA with WAPA will result in over 25% of the network being built. | 25 | No variance from the baseline plan. | 25 | No variance from the baseline plan. | 2011-08-30 12:45 | 2011-08-30 12:45 | 5238 | 5238 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2011 | Q3 | Q3 - 2011 | 4364 | 4038 | FALSE | 12 | Additional progress is expected during Quarter 4, CY 2011, as reflected in the project accomplishments planned that are outlined in Item #1 above and based on total anticipated expenditures through Quarter 4, CY 2011. We do, however,anticipate under performing against this baseline indicator, given the delays in the start of trenching and build-out of the aerial and underground network to date. As we move ahead to initiate and conclude procurements related to these "deliverables" and realign our construction schedule to include parallel construction activities, we anticipate that we will be able to significantly narrow the gap between the baseline indicators and our actual performance by the end of Q2, CY 2012. | 0 |  | Under performance against this baseline indicator is associated with the reasons for the variance from the baseline plan, as noted in 2a. through 2j above. | 100 | No variance from the baseline plan | 90 | Additional progress is expected during Quarter 4, CY 2011, as reflected in the project accomplishments planned that are outlined in Item #1 above and based on total anticipated expenditures through Quarter 4, CY 2011. We do, however,anticipate under performing against this baseline indicator as a result of adjustments which were made in the location of a few FAPs and the finalization of beach manhole landings. Additional design work will be required for the FAP and beach manhole landing relocations. | 95 | Additional progress is expected during Quarter 4, CY 2011, as the majority of real estate included in the construction footprint for the trench work, FAP construction, manhole placement, etc. is owned by the Government of the U.S. Virgin Islands (GVI) and GVI stakeholders have been very cooperative. We do, however,anticipate under performing against this baseline indicator as a result of adjustments which were made in the location of a few FAPs which require additional approvals of rights of way. | 95 | Additional progress is expected during Quarter 4, CY 2011, given the full cooperation of the governmental entities involved in providing approval. Many of the locations which will be affected during construction are owned by the GVI and are covered by master agreements. We do, however,anticipate slightly under performing against this baseline indicator as a result of adjustments which were made in the location of a few FAPs and beach manhole landings. | 2 | Projected under performance in this area is based on the fact that construction-related procurements were suspended as a result of the stop work order. The delay in the procurement processes have, in turn, resulted in the delay of construction-related activities. Resumption of all procurement work related to this task will resume during Q4, CY 2011, and revised implementation schedules and related budgets will be finalized during Q4, CY 2011. | 15 | Projected under performance in this area is based on the fact that equipment-related procurements were suspended as a result of the stop work order. The delay in the equipment procurement processes have, in turn, resulted in the delay of construction-related activities. Resumption of all work related to this task will resume during Q4, CY 2011. | 7 | We project under performance against this baseline indicator as a result of the delays in the commencement of construction activities. We, however, have made some progress with our IRU contract negotiations and expect to further advance these negotiations with Global Crossing/Level 3 and AT&T with the lifting of the stop work order. Revised implementation schedules and related budgets will also be finalized during Q4, CY 2011. | 0 | We project under performance against this baseline indicator, given the delays in the commencement of construction activities. With the lifting of the stop work order, contract negotiations will resume, and revised implementation schedules and related budgets will be finalized during Q4, CY 2011. | 10 | We project under performance against this baseline because of delays in the Alpha testing by UDT. We anticipate that this testing can begin and possibly conclude during Q4, CY 2011. | 2011-11-30 22:11 | 2011-11-30 22:11 | 6449 | 6449 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2011 | Q4 | Q4 - 2011 | 5422 | 5108 | FALSE | 31 | Additional progress is expected during Quarter 1, CY 2012, as reflected in the project accomplishments planned that are outlined in Item #1 above and based on total anticipated expenditures through Quarter 1, CY 2012. The team does, however,anticipate under performing against this baseline milestone target, given the delays in the start of excavation, trenching and build-out of the aerial and underground network to date. As VIPFA/viNGN begins its excavation, trenching and fiber pulling activities and continues with the SuperFAP and regular FAP construction through Quarter 2, CY 2012, the team will coordinate with contractors to work on accelerated schedules. Also, as the team proceeds ahead to initiate and conclude procurements related to these "deliverables" and realign its construction schedule to include parallel construction activities, it is anticipated that the team will be able to significantly narrow the gap between the Baseline Milestone targets and actual performance by the e | 0 |  | The VIPFA/viNGN team has mobilized and made progress towards meeting the Baseline Milestone targets. The combination of the planned accomplishments, as outlined above, and the total expenditures anticipated through Quarter 1, CY 2012 document the new management team's commitment to continue to accelerate the implementation of the program, despite facing the challenges outlined in 3 below. Significant progress is expected during the next two quarters. | 100 | No variance from the baseline plan | 100 | No variance from the baseline plan | 80 | Additional progress is expected during Quarter 1, CY 2012, as the majority of real estate included in the construction footprint for the trench work, FAP construction, manhole placement, etc. is owned by the Government of the U.S. Virgin Islands (GVI), and GVI stakeholders have been very cooperative. The VIPFA/viNGN team does, however, anticipate under performing against this baseline indicator as a result of adjustments which were made in the location of a few FAPs which require additional approvals of rights of way but still anticipate progress against the previous quarter. | 100 | No variance from the baseline plan | 5 | Additional progress is expected during Quarter 1, CY 2012 with the anticipated finalization of the solicitation for excavation and trenching work. The team does, however,anticipate under performing against this baseline milestone, given the delays in the start of excavation and trenching and build-out of the aerial and underground network. Also, as the team proceeds ahead to initiate and conclude procurements related to these "deliverables" and realign its construction schedule to include parallel construction activities, it is anticipated that the team will be able to significantly narrow the gap between the Baseline Milestone targets and actual performance by the end of Quarter 2, CY 2012. | 30 | Additional progress is expected during Quarter 1, CY 2012 with the build out of the network, including the start of construction of the SuperFAPs; the purchase of additional electronics and other technical equipment; and, the purchase of additional fiber. Also, equipment procurements are expected to be accelerated with the hiring of additional staff to support implementation activities. | 15 | Additional progress is expected during Quarter 1, CY 2012 with the anticipated finalization of the solicitation for excavation and trenching work. The team does, however,anticipate under performing against this baseline milestone, given the delays in the start of excavation and trenching and build-out of the aerial and underground network. Also, as the team proceeds ahead to initiate and conclude procurements related to these "deliverables" and realign its construction schedule to include parallel construction activities, it is anticipated that the team will be able to significantly narrow the gap between the Baseline Milestone targets and actual performance by the end of Quarter 3, CY 2012. | 3 | Additional progress is expected during Quarter 1, CY 2012 with the build out of the network, including the start of construction of the SuperFAPs; the purchase of additional electronics and other technical equipment; and, the purchase of additional fiber. | 10 | Additional progress is expected during Quarter 1, CY 2012 with the purchase of additional electronics and other technical equipment; the build out of the network, including the start of construction of the SuperFAPS; and, the purchase of additional fiber. | 2012-02-29 19:00 | 2012-02-29 19:00 | 7323 | 7323 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2012 | Q1 | Q1 - 2012 | 6350 | 5777 | FALSE | 31 | Additional progress is expected during Quarter 2, CY 2012, as reflected in the project accomplishments planned that are outlined in Item #1 above and based on total anticipated expenditures through Quarter 2, CY 2012. The team does anticipate under performing against this baseline milestone target, given the delays in the start of excavation, trenching and build-out of the aerial and underground network to date. As VIPFA/viNGN begins its excavation, trenching and fiber pulling and splicing activities and continues with the SuperFAP and regular FAP construction through Quarter 3, CY 2012, the team will coordinate with contractors to work on accelerated schedules. Also, as the team proceeds to initiate and conclude procurements related to these "deliverables" and realign its construction schedule to include parallel construction activities, it is anticipated that the team will be able to significantly narrow the gap between the Baseline Milestone targets and actual performance by the end | 0 |  | The combination of the planned accomplishments, as outlined above, and the total expenditures anticipated through Quarter 2, CY 2012 document the new management team's commitment to continue to accelerate the implementation of the program, despite facing the challenges outlined in 3 below. Significant progress is expected during the next two quarters. | 100 | No variance from Baseline Milestone target | 100 | No variance from Baseline Milestone target | 90 | Additional progress is expected during Quarter 2, CY 2012, as the majority of real estate included in the construction footprint for the trench work, FAP construction, manhole placement, etc. is owned by the Government of the U.S. Virgin Islands (GVI), and GVI stakeholders have been very cooperative. The VIPFA/viNGN team does, however, anticipate under performing against this baseline indicator as a result of adjustments which were made in the location of a few FAPs which require additional approvals of rights of way but still anticipate progress against the previous quarter. | 100 | No variance from Baseline Milestone target | 5 | Additional progress is expected during Quarter 2, CY 2012, with the anticipated finalization of the solicitations for additional FAP construction and excavation and trenching work. The team does, however, anticipate under performing against this Baseline Milestone, given the delays in the start of excavation and trenching and build-out of the aerial and underground network. Also, as the team proceeds to initiate and conclude procurements related to these "deliverables" and realign its construction schedule to include parallel construction activities, it is anticipated that the team will be able to significantly narrow the gap between the Baseline Milestone targets and actual performance by the end of Quarter 3, CY 2012. | 90 | VIPFA/viNGN anticipates over performing against this Baseline Milestone target. The VIPFA/viNGN team has made significant progress in its equipment procurement activities and currently exceeds the percentage completion against this Baseline Milestone target. The team has purchased more than 90% of the network management equipment needed for the build-out of the network. The team is awaiting delivery and final testing of these routers and switches to begin the staging for the placement of the equipment. Once the SuperFAPs and FAPs are built, the routers and switches will be installed to await final connection to the fiber to bring the network on line. Further, the team purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network during the past quarter. | 15 | Additional progress is expected during Quarter 2, CY 2012, with the construction of the two SuperFAPs; completion of the construction of the SuperFAPs is expected during late Quarter 2, CY 2012/early Quarter 3, CY 2012. Once they are completed, progress against this milestone will improve. Delays are anticipated in the core network build out until excavation and trenching and aerial and underground fiber pulling and splicing activities commence during the next two quarters and until the lease agreement for the SONET OC-48 with AT&T to connect St. Thomas and St. Croix is executed. Based on the status of current negotiations with AT&T, the agreement is expected to be fully executed during Quarter 2, CY 2012. A fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami were signed with Global Crossing/Level 3 during the past quarter. Alternative plans to illuminate the network are currently being considered, e.g. consideration is being gi | 3 | Additional progress is expected during Quarter 2, CY 2012. Given that 1) VIPFA/viNGN has purchased a large portion of the network management equipment, 2) significant progress has been made with the construction of the two SuperFAPs, 3) the construction of the SuperFAPs is expected to be completed during late Quarter 2, CY 2012/early Quarter 3, CY 2012, 4) construction of the remaining FAPs is expected to begin during Quarter 2, CY 2012, 5) fiber pulling and splicing in underground conduit is expected to begin during Quarter 3, CY 2012, and 6) aerial fiber pulling and splicing is expected to begin during Quarter 3, CY 2012, progress against this milestone will improve during the next two quarters, as the equipment can be deployed with the start and completion of these activities. | 5 | Additional progress is expected during Quarter 2, CY 2012. Network testing will be ongoing in alignment with equipment purchases and network build out. The initial alpha testing of the network's core gateway routers in a lab environment was completed during Quarter 4, CY 2011. With the purchase of a large portion of the network management equipment during Quarter 1, CY 2012 and the planned completion of construction of the SuperFAPs by late Quarter 2, CY 2012/early Quarter 3, CY 2012, final testing and staging for placement of the routers and switches will begin during the latter part of Quarter 2, CY 2012 or early in Quarter 3, CY 2012. Once the FAPs are built, the routers and switches will be installed to await final connection to the fiber to bring the network on line. | 2012-05-30 13:06 | 2012-05-30 13:06 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2012 | Q2 | Q2 - 2012 | 7258 | 6256 | FALSE | 35 | The SuperFAP construction is expected to be completed, and the Team intends to begin the construction of an additional six (6) FAPs during Quarter 3, CY 2012. Additional progress is expected during Quarter 3, CY 2012, based on the project accomplishments planned that are outlined in Item #1 above and based on total anticipated expenditures through Quarter 3, CY 2012. The team will coordinate with contractors to work on accelerated schedules. Also, as the team proceeds to initiate and conclude procurements and realign its construction schedule to include parallel construction activities, it is anticipated that the team will be able to significantly narrow the gap between the Baseline Milestone targets and actual performance by the end of Quarter 3, CY 2012. | 0 |  | The combination of the planned accomplishments, as outlined above, and the total expenditures anticipated through Quarter 3, CY 2012 document the new management team's commitment to continue to accelerate the implementation of the program, despite facing the challenges outlined in 3 below. Significant progress is expected during the next two quarters. | 100 | No variance from Baseline Milestone target; The VIPFA/viNGN team does plan to complete additional archeological surveys for FAPs that are located near historical sites during Quarter 3, CY 2012/early Quarter 4, 2012. | 100 | No variance from Baseline Milestone target | 95 | Additional progress is expected during Quarter 3, CY 2012, as additional Rights of Way are obtained for the locations of a few FAPs on private properties. The majority of real estate included in the construction footprint for the trench work, FAP construction, manhole placement, etc. is owned by the Government of the U.S. Virgin Islands (GVI). | 100 | No variance from Baseline Milestone target | 80 | Additional progress is expected during Quarter 3, CY 2012 with the anticipated finalization of FAP construction and the posting of RFPs for Excavation and Underground Trenching, Underground Fiber Pulling and Splicing, and Aerial Fiber Pulling and Splicing Construction. As the Team proceeds to initiate and conclude procurements related to these "deliverables" and realign its construction schedule to include parallel construction activities, it is anticipated that the Team will be able to significantly narrow the gap between the Baseline Milestone targets and actual performance by the end of Quarter 3, CY 2012. | 92 | VIPFA/viNGN anticipates over performing against this Baseline Milestone target. The VIPFA/viNGN team has made significant progress in its equipment procurement activities and currently exceeds the percentage completion against this Baseline Milestone target. During Quarter 2, CY 2012, the team received the routers and switches needed to begin the staging for the placement of the equipment. Once permanent power is installed in the Super FAPs and the other FAPs are built, the routers and switches will be installed to await final connection to the fiber to bring the network on line. Further, the team has purchased all of the needed fiber optic cable and is awaiting delivery of the final order, which is expected during Quarter 3, CY 2012. | 20 | Significant progress has been made with the construction of the two Super FAPs; completion of the construction of the Super FAPs is expected during Quarter 3, CY 2012. Once the SuperFAPs and FAPs are built, the routers and switches will be installed to await final connection to the fiber to bring the network on line. Further, RFPs for excavation/trenching and aerial and underground fiber pulling and splicing activities are scheduled to be posted during Quarter 3, CY 2012. The VIPFA/viNGN team has also made significant progress in its equipment procurement activities and currently exceeds the percentage completion against the related Baseline Milestone target. The team has purchased all of the fiber required for its network, with the final order expected to be delivered during Quarter 3, CY 2012. During Quarter 2, CY 2012, the team received the routers and switches needed to begin the staging for the placement of the equipment. Once permanent power is installed in the Super FAPs and | 10 | When the construction of the two Super FAPs is completed during Quarter 3 CY, 2012, equipment can be deployed. As the regular FAPs are built, the routers and switches and other equipment will be installed to await final connection to the fiber to bring the network on line. | 40 | With the planned completion of construction of the two Super FAPs during Quarter 3, CY 2012, the final testing and staging for placement of the routers and switches will begin during late Quarter 3, CY 2012 or early Quarter 4, CY 2012. Once connection of the FAPs is completed, the routers and switches will be installed and will await final activation to the fiber to bring the network on line. | 2012-08-27 17:33 | 2012-08-27 17:33 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2012 | Q3 | Q3 - 2012 | 8094 | 6754 | FALSE | 41 | The Super FAP construction is completed, and the VIPFA/viNGN intends to begin the construction of additional FAPs during Quarter 4, CY 2012. Additional progress is expected during Quarter 4, CY 2012. At the end of the 3rd quarter, the VIPFA/viNGN team worked to finalize eight (8) construction service contracts for the construction of eight (8) additional FAPs, six on St. Thomas and two on St. Croix. During Quarter 4, CY 2012, VIPFA/viNGN will finalize any environmental, archeological studies and will award contracts for the execution of these FAPs. This will be an aggressive schedule to which most of VIPFA/viNGN project activities will be field bound. The RFPs for the aerial fiber pulling and splicing was issued during Quarter 3, CY 2012. As a result, VIPFA/viNGN and it contractors will begin aeiral fiber installation during Quarter 4, CY 2012. This implies VIPFA/viNGN will have an aggressive schedule of activities to include FAP construction, aerial fiber pulling, underground fiber | 0 |  | The combination of the planned accomplishments, as outlined above, and the total expenditures anticipated through Quarter 4, CY 2012 document the new management team's commitment to continue to accelerate the implementation of the program, despite facing the challenges outlined in 3 below. Significant progress is expected during the next two quarters. | 96 | No variance from Baseline Milestone target; VIPFA/viNGN team does plan to complete additional archaeological surveys for all FAPs that were relocated. | 100 | Future network will handle security monitoring and utilizing SNMP (Simple Network Management Protocol) enable devices and IP (Internet Protocol). cameras. There are no variances from Baseline Milestone target. | 95 | Additional progress is expected during Quarter 4, CY 2012, as additional Rights of Way are obtained for the locations of a few FAPs on private properties. The majority of real estate included in the construction footprint for the trench work, FAP construction, manhole placement, etc. is owned by the Government of the U.S. Virgin Islands (GVI). | 96 | Due to the relocation of a few FAPs, new environmental, archaeological and building permits are required prior to construction. As a result of reapplying for building permits, the percentage was reduce. | 80 | In the first section of Quarter 4 CY 2012, VIPFA/viNGN project team will make a site visit to identify fiber optic trench crossings such as storm drains, sewer lines and any noticeable mechanically laid underground crossing. In addition, a site visit will be conducted with the trench contractor to identify existing underground obstructions and to establish the path of the trench work for the entire trench project. In preparation for FAP construction, site visits will be conducted with construction contractors to identify lay down areas, traffic patterns and any other safety concerns applicable to the particular project site. This will include participation with the current land owner in vetting any concerns that maybe of significance of the project completion. | 94 | During Quarter 4, CY 2012, the team plans to continue to over preform against the Baseline as it will begin to install traffic rated vaults during the trench work on both St. Thomas and St. Croix. Additionally, during Quarter 4, CY 2012, VIPFA/viNGN will procure a stocking equipment for the warehouse team. | 25 | Significant progress has been made with the construction of the two Super FAPs. The Super FAPs were completed during Quarter 3, CY 2012. Permanent power was installed in the Super FAPs. However, once the other FAPs are built, the routers and switches will be installed to await final connection to the aerial or underground fiber to bring the network on line. The lease agreement for the SONET OC-48 with AT&T to connect St. Thomas and St. Croix was executed during Quarter 2, CY 2012, and a fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami were signed with Global Crossing/Level 3 during Quarter 4, CY 2011. No route changes are anticipated. | 11 | Significant progress has been made with the construction of the two Super FAPs. The Super FAPs were completed during Quarter 3, CY 2012. Permanent power was installed in the Super FAPs. However, once the other FAPs are built, the routers and switches will be installed to await final connection to the aerial or underground fiber to bring the network on line in the final quarter. The lease agreement for the SONET OC-48 with AT&T to connect St. Thomas and St. Croix was executed during Quarter 2, CY 2012, and a fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami were signed with Global Crossing/Level 3 during Quarter 4, CY 2011. | 40 | Construction of the two Super FAPs are complete. Once connection of the FAPs are completed, the routers and switches will be installed and will await final activation to the fiber to bring the network on line. In Quarter 2, CY 2013, the final testing and staging for placement of the routers and switches will begin. | 2012-11-28 09:58 | 2012-11-28 09:58 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2012 | Q4 | Q4 - 2012 | 9052 | 7825 | FALSE | 40 | By the end of Quarter 4, CY 2012, VIPFA/viNGN constructed a total of three FAPs and intends to begin the construction of additional FAPs during Quarter 1, CY 2013. Additional progress is expected during Quarter 1, CY 2013. At the end of Quarter 4, CY 2012, the VIPFA/viNGN team worked to finalize construction service contracts for the construction of eight (8) additional FAPs, six on St. Thomas and two on St. Croix. During Quarter 1, CY 2013, VIPFA/viNGN expects to execute contracts for the construction of these FAPs. With the signing of these contracts, the team will be on aggressive schedule with most of its construction activities in process. The contractors for the aerial fiber pulling and splicing were selected during Quarter 4, CY 2012. As a result, VIPFA/viNGN and it contractors expect to begin aerial fiber installation during Quarter 1, CY 2013. With work initiated under these contracts, the team will be engaged in an aggressive schedule of activities to include aerial fibe | 0 |  | The combination of the planned accomplishments, as outlined above, and the total expenditures anticipated through Quarter 1, CY 2013 document the new management team's commitment to continue to accelerate the implementation of the program, despite facing the challenges outlined in 3 below. Significant progress is expected during the next two quarters. | 96 | There is no variance from the Baseline Milestone target. An addendum to the Phase 1 Archaeological Survey and an addendum to the Environmental Assessment were completed to address ten FAP relocations. During Quarter 1, CY 2013, VIPFA/viNGN will submit the official request to NTIA and NOAA to relocate the ten FAPs, based on the results of the addendum to the Archeological Survey and the Environmental Assessment, both of which identified no significant impact, and in some cases, lesser impact. No potentially significant archeological resources were identified during the Phase I Archaeological Survey for the Fiber Access Point locations on both islands either. Thus, from the archaeological perspective, it was recommended that the State Historic Preservation Office issues a conditioned finding of no objection to the proposed construction activities. The VIPFA/viNGN team continues to monitor its construction site during the build-out process for any endangered species that viNGN or its c | 100 | There are no variances from the Baseline Milestone target. | 95 | Additional progress is expected during Quarter 1, CY 2013, as additional Rights of Way are obtained for the locations of a few FAPs on semi-autonomous government agency properties. The majority of real estate included in the construction footprint for the trench work, FAP construction, traffic-rated vault/manhole placement, etc. is owned by the Government of the U.S. Virgin Islands (GVI). The VIPFA/viNGN team has an agreement with the U.S. Virgin Islands Department of Public Works for the trenching of four segments of highway, two on St. Thomas and St. Croix. During Quarter 4, CY 2012, VIPFA/viNGN began trenching on both islands, St. Croix and St. Thomas. VIPFA/viNGN will continue to work with the U.S. Virgin Islands Department of Planning and Natural Resources to ensure that VIPFA/viNGN's permits are updated and in compliance with the previous permits issued. The team will also engaged with the State Historic Preservation office and current land owners to also insure that FAPs are c | 96 | VIPFA/viNGN will continue to work with the local Planning and Natural Resources Department to ensure that VIPFA/viNGN permits are updated and in compliance with the previous permits issued. The team will was also continue to engage with the State Historic Preservation office and current land owners to ensure that FAPs are constructed in the approved rights of way. During Quarter 4, CY 2012, VIPFA/viNGN received seventeen (17) building permits for FAP construction. VIPFA/viNGN is anticipating that all remaining building permits for FAP construction will be issued by the end of Quarter 1, CY 2013. | 81 | During the first half of Quarter 1, CY 2013, the VIPFA/viNGN project team will rcontinue to conduct site visits to formalize installation procedures for aerial fiber installation; to identify impediments, such as tree branches, sagging power lines, etc.; and to work to address these issues. In preparation for the remaining FAP construction, site visits will be conducted with construction contractors to identify lay down areas, traffic patterns and any other safety concerns applicable to the particular project site. This will include participation with the current land custodians in vetting any concerns that may be of significance to the completion of the project. Silt barriers, fencing, and land clearing measures will be implemented to ensure a smooth transition into the construction process for all future FAPs. VIPFA/viNGN and its contractors will continue to assess the roads on which trench work will be performed. Traffic patterns, road construction and other potential obstructio | 94 | VIPFA/viNGN and its contractors will continue to install underground fiber optic conduits on all four segments of the project. With the aim to reduce traffic interference, conduits will be installed without traffic vaults. Further, aerial installation will begin, and FAP construction and equipping will continue. Traffic-rated vaults are expected to be installed, beginning late Quarter 1, CY 2013/Quarter 2, CY 2013. | 25 | By the end of Quarter 4, CY 2012, VIPFA/viNGN completed a total of three FAPs. The construction of additional FAPs will begin during Quarter 1, CY 2013. Once the other FAPs are built, the routers and switches will be installed to await final connection to the aerial or underground fiber to bring the network on line. VIPFA/viNGN trenched approximately 7 miles during Quarter 4, CY 2012, which was limited due to the impact of the holiday seasons during November 2012 and December 2012. VIPFA/viNGN expects to trench the remaining 39 miles with four trenching teams operating simultaneously, two on St. Thomas and two on St. Croix. VIPFA/viNGN also plans to begin the installation of the total 46.6 miles of aerial construction on St. Thomas and St. John and 36.6 miles on St. Croix. | 11 | Under performance against the Baseline Indicator is due to the fact that VIPFA\viNGN has not completed the build-out of the network segments that will enable viNGN to provide improved access to providers. However, as the FAP construction is completed, the Community Anchor Institutions are connected and all backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator targets. The lease agreement for the SONET OC-48 with AT&T to connect St. Thomas and St. Croix was executed during Quarter 2, CY 2012, and a fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami were signed with Global Crossing/Level 3 during Quarter 4, CY 2011. At the Global Crossing/Level 3 facility in Miami, the ASR 9006 installation process is complete, with the ASR 9006 powered up and tested. | 40 | During Quarter 1, CY 2013, the aerial installation contractors will begin testing of the fiber optic reels at the warehouse locations prior to installation. Network testing will be ongoing in alignment with equipment purchases and network build out. The initial alpha testing of the network's core gateway routers in a lab environment was completed during Quarter 4, CY 2011. Testing was also completed from Proof of Design from the NAPs (Network Access Point) to the Super FAPs to Community Anchor Institutions (CAIs). No testing was carried out during Quarter 4, CY 2012; however, with the purchase of a large portion of the network management equipment during Quarter 1, CY 2012 and the completion of the construction of the Super FAPs by Quarter 3, CY 2012, final testing and staging for placement of the routers and switches will begin during late Quarter 1, CY 2013. Once connection of the FAPs is complete, the routers and switches will be installed and will await final activation to the fib | 2013-02-28 08:29 | 2013-02-28 08:29 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2013 | Q1 | Q1 - 2013 | 9996 | 8542 | FALSE | 58 | The remaining trenching will be completed during Quarter 2, CY 2013. By the end of the Quarter 4, CY 2012, VIPFA/viNGN completed the construction of a total of three FAPs. VIPFA/viNGN is 90% completed with a fourth FAP as of March 31, 2013 and expects to complete it during Quarter 4, CY 2013. Additional FAP construction will be the main priority during Quarter 2, CY 2013 and Quarter 3, CY 2013. The VIPFA/viNGN team will finalize construction service contracts for the construction of seven (7) additional FAPs on St. Thomas and will make awards for the construction of FAPs on St John. During Quarter 1, CY 2013, a Notice to Proceed was issued to the aerial fiber pulling and splicing contractor for work on St. Thomas, St. John and St. Croix. The contractor began aerial fiber installation during Quarter 1, CY 2013 and will continue installations on an aggressive schedule. Underground fiber installation will also continue on an aggressive schedule during Quarter 2, CY 2013. | 0 |  | The combination of the planned accomplishments, as outlined above, and the total expenditures anticipated through July 31, 2013 document the management team's commitment to continue to accelerate the implementation of the program, in spite of the challenges outlined in 3 below. Significant progress is expected during Quarter 2, CY 2013. | 98 | An addendum to the Phase 1 Archaeological Survey was completed to address ten FAP relocations. No potentially significant cultural resources were identified during the Phase I Archaeological Survey for the Fiber Access Point locations on both islands. As a result of the archaeological review, VISHPO had no objection to the proposed construction activities. The VIPFA/viNGN team will continue to monitor its construction site during the build-out process for any endangered species that viNGN or its contractors might encounter, such as the Ameiva polops, Epicrates monensis granti, and Eretmochelys imbricata. To date, viNGN and its contractors have not encountered any of the above species and their habitat on any of the construction sites. | 100 | The routing protocol design has been finalized, and redundancy plans have been updated to best utilize new and existing network nodes. Once the FAPs (Fiber Access Points) are built and the network equipment is installed, the network is expected to be ready to "go live". The team has determined that security monitoring of the network will be managed utilizing SNMP (Simple Network Management Protocol)-enabled devices and IP (Internet Protocol) cameras. Awards to contractors to provide and install the required equipment is expected during late Quarter 2, CY 2013 or Quarter 3, CY 2013. | 98 | Additional Rights of Way were obtained for the locations of a few FAPs on semi-autonomous government agency properties. The majority of real estate included in the construction footprint for the trench work, FAP construction, manhole placement, etc. is owned by the Government of the U.S. Virgin Islands (GVI). The VIPFA/viNGN team has an agreement with the U.S. Virgin Islands Department of Public Works (DPW) for the trenching of four segments of highway, two on St. Thomas and St. Croix. During Quarter 4, CY 2013, VIPFA/viNGN began trenching on St. Croix and on St. Thomas. VIPFA/viNGN trenched approximately 32 miles as of March 31, 2013 and expects to trench the remaining 12.5 miles during Quarter 2, CY 2013. The VIPFA/viNGN team will continue to work with the U.S. Virgin Islands Department of Planning and Natural Resources to ensure that VIPFA/viNGN's permits are updated and in compliance with the previous permits issued. The team will also continue to engage with the U.S. Virgin I | 96 | VIPFA/viNGN will continue to work with the local U.S. Virgin Islands Department of Planning and Natural Resources Department to ensure that VIPFA/viNGN's permits are updated and in compliance with the previous permits issued. During Quarter 4, CY 2012, VIPFA/viNGN received seventeen (17) building permits for FAP construction. VIPFA/viNGN is anticipating that all building permits for FAP construction will be issued by late Quarter 2, CY 2013. The team will also continue to engage with the U.S. Virgin Islands Historic Preservation Office and current land owners to ensure that FAPs are constructed in the approved rights of way. | 90 | In preparation for the aerial and innerduct contractor, the VIPFA/viNGN project team conducted site visits to identify the installation precedence for aerial fiber installation to monitor any impediments, such as tree branches, sagging power lines, etc. during Quarter 1, CY 2013. Site visits were also conducted with construction contractors to identify traffic patterns and any other safety concerns applicable to the particular project site. Future site preparation visits may include participation by the current land custodians to address any concerns that may impact the project completion schedule. During Quarter 2, CY 2013, silt barriers, fencing, and land clearing measures will be executed to ensure a smooth transition into the construction process for all the remaining FAPs. VIPFA/viNGN and its contractors will continue to assess the roads on which trench work will be performed. Traffic patterns, road construction and other potential obstructions that may cause unsafe conditions o | 94 | During Quarter 2, CY 2013, VIPFA/viNGN's contractors will continue to install aerial fiber and pull innerduct and Maxcell linings. Additionally, VIPFA/viNGN will procure any additional needed equipment for the network build out. The team also plans to install traffic rated vaults during the trench work on both St. Thomas and St. Croix. | 60 | By the end of Quarter 4, CY 2012, VIPFA/viNGN completed the construction of a total of three FAPs. VIPFA/viNGN is 90% completed with a fourth FAP as of March 31, 2013 and expects to complete it during Quarter 2, CY 2013. FAP construction on St. Croix is expected to continue, and the construction of seven (7) FAPs on St. Thomas is expected to begin during late Quarter 2, CY 2013. An award for the construction of FAPs on St. John is expected to be issued during Quarter 2, CY 2013. Once the other FAPs are built, the routers and switches will be installed to await final connection to the aerial or underground fiber to bring the network on line. The AT&T SONET OC-48 Link was initiated for activation during Quarter 1, CY 2013. VIPFA/viNGN anticipates 60 days to 90 days for activation; thus, the connection should be available during Quarter 2, CY 2013 or Quarter 3, CY 2013. VIPFA/viNGN trenched approximately 32 miles as of March 31, 2013. VIPFA/viNGN expects to trench the remaining 12.5 m | 50 | Under performance against the Baseline Indicator is due to the fact that VIPFA/viNGN has not completed the build-out of the additional network segments that will enable additional equipment deployment. However, as the FAP construction is completed, the Community Anchor Institutions are connected and all backbone nodes equipment are installed, the team will be positioned to come in line with the Baseline Indicator targets. The lease agreement for the SONET OC-48 with AT&T to connect St. Thomas and St. Croix was executed during Quarter 2, CY 2012, and a fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami were signed with Global Crossing/Level 3 during Quarter 4, CY 2011. The AT&T SONET OC-48 Link was initiated for activation during Quarter 1, CY 2013. VIPFA/viNGN anticipates 60 days to 90 days for activation; thus, the connection is expected to be available during Quarter 2, CY 2013 or Quarter 3, CY 2013. At the Level 3 facility in M | 45 | During Quarter 2, CY 2013, the aerial installation contractor will continue to test fiber optic reels at the warehouse location prior to installation. Also, network testing will be ongoing in alignment with equipment purchases and network build out. The initial alpha testing of the network's core gateway routers in a lab environment was completed during Quarter 4, CY 2011. Testing was also completed from Proof of Design from the NAPs (Network Access Point) to the Super FAPs to Community Anchor Institutions (CAIs). No testing was carried out during Quarter 4, CY 2012; however, with the purchase of a large portion of the network management equipment during Quarter 1, CY 2012 and the completion of the Super FAPs during Quarter 3, CY 2012, final testing and staging for placement of the routers and switches will begin during the latter part of Quarter 2, CY 2013. Once connection of the FAPs is completed, the routers and switches will be installed and will await final activation to the fibe | 2013-05-29 23:15 | 2013-05-29 23:15 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2013 | Q2 | Q2 - 2013 | 10670 | 8996 | FALSE | 59 | The VIPFA/viNGN team made tremendous progress with the construction of its middle mile network during Quarter 2, CY 2013, and the momentum is expected to continue through Quarter 3, CY 2013. Refer to the response to Question 1 immediately above for a summary of the significant accomplishments planned during the next reporting quarter. The aerial backbone, underground backbone and lateral fiber installations will continue on St. Croix, St. Thomas, Water Island and St. John. In addition, the construction of FAPs (Fiber/Facility Access Points) and the installation of fiber patch panels, AC (Air Conditioning) units, racking equipment and DC Power installation will continue on St. Croix and St. Thomas. Also, the construction of additional FAPs will begin on St. Thomas and St. John. Further, expenditures are expected to increase significantly, starting in Quarter 3, CY 2013, as construction contractors begin to invoice for work that is confirmed as completed by the team's engineers and | 0 |  | N/A | 100 | During Quarter 2, CY 2013, an addendum to the Environmental Assessment and an update to the Phase I Archeological Survey were completed to address FAP relocations and aesthetic modifications to FAPs. The FAP relocations and modifications that were addressed in the assessments that were completed during Quarter 2, CY 2013 were deemed to be minor changes, as the new locations or orientations do not result in any significant adverse impacts on the natural environment nor the human environment and, although some do include changes in earth moving activities, all represent equivalent impact or in several cases even a reduction of impact. No potentially significant cultural resources were identified during the archaeological survey for the FAP relocations on St. Thomas or St. Croix. From the archaeological perspective, it was recommended that the State Historic Preservation Office issues a conditioned finding of no objection to the proposed construction activities. The team hopes to re | 100 | The core network design is complete. The routing protocol design will continue to be updated to best utilize new and existing network nodes. | 100 | All Rights of Way have been obtained. | 100 | During Quarter 2, CY 2013, VIPFA/viNGN prepared two (2) additional permit applications for FAPs to be constructed on St. John. The two permits are anticipated to be approved during early Quarter 3, CY 2013. The VIPFA/viNGN team will continue to work with the U.S. Virgin Islands Department of Planning and Natural Resources to ensure that VIPFA/viNGN's permits are updated and that FAP construction meets local building codes. | 50 | The VIPFA/viNGN team will continues to conduct site visits to ensure that sites are ready for aerial fiber installation by identifying impediments, such as tree branches, sagging power lines, etc. The team will continue to coordinate with WAPA to address these impediments. Also, for all new and continuing FAP construction, site visits will be conducted, along with construction contractors and current land custodians (as needed), to identify and address traffic patterns, any other safety concerns, any environmental concerns, any concerns that may impact the project completion schedule, etc. For example, in areas where new FAP construction is expected to start, the site will be examined for any preexisting utilities lines, including water lines, sewer lines and electric lines. Further, silt barriers and silt fencing will be monitored on applicable sites to ensure that seepage from the construction zone does not occur. | 98 | The majority of the equipment that is needed for the network build-out has been procured. Any additional equipment procurement will be the result of needs identified as the final phases of the network build-out continues, as network and equipment testing continues and as network connection activities continue. VIPFA/viNGN will continue to receive equipment as a result of prior procurement activities, including fiber, FAP racking equipment, DC power equipment and minor materials like plastic straps, belts, and screws, for example. | 60 | During Quarter 3, CY 2013, the VIPFA/viNGN team plans to install/deploy a cumulative total of 95.3 new fiber miles on St. Croix, St. Thomas, Water Island and St. John and connect 120 CAIs. The VIPFA/viNGN team also plans to finalize the following during Quarter 3, CY 2013: â€¢ Continue the construction of FAPs (Fiber/Facility Access Points) and the installation of fiber patch panels, AC (Air Conditioning) units, racking equipment and DC Power on St. Croix and St. Thomas; â€¢ Begin the construction of additional FAPs on St. Thomas, St. Croix and St. John; â€¢ As the FAPs are built, install routers and switches to await the final connections to the aerial or underground fiber to bring the network on line; and â€¢ Continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the construction activities. Further, the AT&T SONET OC-48 Link was initiated for activation during Quarter 1, CY 2013, and the connection is e | 50 | Under performance against the Baseline Indicator is due to VIPFA/viNGN not completing the build-out of the network segments that will enable VIPFA/viNGN to provide new access to Internet Service Providers and other service providers. As FAP construction is completed, the Community Anchor Institutions are connected and all backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator targets. Equipment will be deployed as FAPs are built and equipment racks are installed. During Quarter 2, CY 2013, VIPFA/viNGN installed a core distribution switch in the Level 3 facilities on St. Croix to provide bandwidth to customers, with the anticipation of providing service on the portion of the network that will be completed as of Quarter 3, CY 2013, as an alternate way for customers to access VIPFA/viNGN's network prior to the complete build-out of the network. Further, the AT&T SONET OC-48 Link was initiated for activation during Quarter 1, CY 201 | 75 | Under performance against the Baseline Indicator is due to the fact that VIPFA/viNGN has not completed the build-out of the additional network segments that will enable additional network testing. As the FAP construction is completed, the Community Anchor Institutions are connected and all backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator targets. Network testing will be ongoing in alignment with network build out and equipment deployment. As the construction of all other FAPs is completed, the routers and switches will be installed, and final testing and activation will begin to bring the network fully on line. Further, the last batch of fiber that was procured will be tested prior to installation, and additional fiber testing will occur prior to connections to the routers and switches being made. | 2013-08-20 19:17 | 2013-08-20 19:17 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2013 | Q3 | Q3 - 2013 | 11300 | 9449 | FALSE | 87 | The VIPFA/viNGN team continued to make progress with the construction of its middle mile network during Quarter 3, CY 2013, and the momentum is expected to continue through Quarter 4, CY 2013 until the completion of the overall project. Refer to the response to Question 1 immediately above for a summary of the significant accomplishments planned during the next reporting quarter. Payments against invoices for work completed during Quarter 3, CY 2013 through to the end of the project are expected to continue throughout final close-out, as construction contractors begin to invoice for work that is confirmed as completed by the team's engineers and architects. The aerial backbone, underground backbone and lateral fiber installations will continue on St. Croix, St. Thomas, Water Island and St. John, as applicable. Also, the construction of FAPs (Fiber/Facility Access Points); the installation of fiber patch panels, AC (Air Conditioning) units, racking equipment and DC Power; CAI co | 0 |  | N/A | 100 | No additional environmental assessments are anticipated during Quarter 4, CY 2013, unless a determination is later made that additional work will be required to address any final issues with the right of way on the east end of St. Croix. The VIPFA/viNGN team will continue to monitor its construction sites for artifacts as work is performed near sensitive archaeological sites and for any endangered species that viNGN or its contractors might encounter. | 100 | The core network design is complete. The routing protocol design will continue to be updated to best utilize new and existing network nodes. | 100 | All Rights of Way will be obtained, unless a determination is later made that additional work will be required to address any final issues with the right of way on the east end of St. Croix. | 100 | The VIPFA/viNGN team will continue to work with the U.S. Virgin Islands Department of Planning and Natural Resources to ensure that VIPFA/viNGN's permits are updated and that construction activities continue to meet local building codes. | 100 | The VIPFA/viNGN team will continue FAP construction and backfilling activities. Site visits will be conducted along with construction contractors and current land custodians (as needed) to identify and address traffic patterns, any other safety concerns, any environmental concerns, any concerns that may impact the project completion schedule, etc. Further, silt barriers and silt fencing will be monitored on applicable sites to ensure that seepage from the construction zone does not occur. | 100 | VIPFA/viNGN will continue to receive equipment as a result of prior procurement activities. Any additional equipment procurement will be the result of needs identified as the final phases of the network build-out continues, as network and equipment testing continues and as network connection activities continue. | 100 | During Quarter 4, CY 2013, the VIPFA/viNGN team plans to install/deploy a cumulative total of 26 new fiber miles on St. Croix, St. Thomas, Water Island and St. John and connect 315 CAIs. The VIPFA/viNGN team also plans to finalize the following during Quarter 4, CY 2013: â€¢ Continue the construction of FAPs (Fiber/Facility Access Points) and the installation of fiber patch panels, AC (Air Conditioning) units, racking equipment and DC Power on St. Croix, St. Thomas and St. John; â€¢ Install routers and switches to await the final connections to the aerial or underground fiber to bring the network on line; â€¢ Continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the construction activities; and â€¢ Continue to assess the project implementation schedule and the network design to identify ways to speed up the build-out and coordinate with the construction contractors, NTIA and NOAA to determine whether a | 100 | As the remaining FAP construction is completed, the equipment racks are installed in the FAPs, the Community Anchor Institutions are connected and all backbone node equipment is installed, equipment will be deployed, and the team will be positioned to come in line with the Baseline Indicator targets. | 100 | As the remaining FAP construction is completed, the equipment racks are installed in the FAPs, Community Anchor Institutions are connected and the remaining backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator targets. Network testing will be ongoing in alignment with network build out and equipment deployment. As the construction of all other FAPs is completed, the routers and switches will be installed, and final testing and activation will bring the network fully on line. | 2013-11-19 16:37 | 2013-11-19 16:37 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | 2013 | Q4 | Q4 - 2013 | 11920 | 10084 | FALSE | 88 | The VIPFA/viNGN team continued to make progress with the construction of its middle mile network during Quarter 4, CY 2013, and the momentum is expected to continue through Quarter 1, CY 2014 until the completion of the overall project. Refer to the response to Question 1 immediately above for a summary of the significant accomplishments planned during the next reporting quarter. Payments against invoices for work completed during Quarter 4, CY 2013 through to the end of the project are expected to continue throughout final close-out, as construction contractors begin to invoice for work that is confirmed as completed by the team's engineers and architects. The construction of FAPs (Fiber/Facility Access Points); the installation of fiber patch panels, AC (Air Conditioning) units, racking equipment and DC Power; CAI connections; and, network testing and monitoring will continue. Also, the aerial backbone, underground backbone and lateral fiber installations will continue, | 0 |  | N/A | 100 | No additional environmental assessments are anticipated during Quarter 1, CY 2014, unless a determination is later made by the U.S. Virgin Islands State Historic Preservation Office (VISHPO) and/or NTIA that additional work will be required to address any final issues with the proposed underground installation on the east end of St. Croix and the proposed aerial installation on the east end of St. Thomas that were outlined in the above-referenced request for a project modification. The VIPFA/viNGN team will continue to monitor its construction sites for artifacts as work is performed near sensitive archaeological sites and for any endangered species that viNGN or its contractors might encounter. | 100 | The core network design is complete. During Quarter 4, CY 2013, the VIPFA/viNGN team requested approval of the following project modifications for St. Croix and St. Thomas: 1. On St. Croix, approximately 800 feet of aerial network needs to be changed from aerial to underground. This change is necessary because it was determined that the Virgin Islands Water and Power Authority (WAPA) does not have a right of way for aerial installation along this section of the network. Originally, the plan was to span this gap without the use of poles, but the landowner will not approve any aerial plan; and, 2. On St. Thomas, approximately 2,500 feet of underground network needs to be changed to aerial. This modification is temporary to allow for a recently-approved major road repair project by the U.S. Virgin Islands Department of Public Works along this section of the network and because the portion of the conduit that is contributed by WAPA is blocked and cannot be cleared in the near-ter | 100 | All Rights of Way that were needed have been obtained to date. A determination may be made later for additional work to address any issues with the right of way for the proposed underground installation on the east end of St. Croix. | 100 | The VIPFA/viNGN team will continue to work with the U.S. Virgin Islands Department of Planning and Natural Resources to ensure that VIPFA/viNGN's permits are updated and that construction activities continue to meet local building codes. | 100 | Site preparation will be complete, with the exception of those that may be related to any remaining CAI connections. | 100 | VIPFA/viNGN will continue to receive equipment as a result of prior procurement activities. Any additional equipment procurements will be the result of needs identified as the final phases of the network build-out continues, as network and equipment testing continues, and as network connection activities continue. | 100 | During Quarter 1, CY 2014, the VIPFA/viNGN team plans to install/deploy a cumulative total of 8 new fiber miles across St. Croix, St. Thomas, St. John and Water Island and connect 314 CAIs. The VIPFA/viNGN team also plans to finalize the following during Quarter 1, CY 2014: â€¢ Continue the construction of FAPs (Fiber/Facility Access Points) and the installation of equipment; Continue the installation of the remaining equipment in the already-constructed FAPS; â€¢ Continue the connections of CAIs and the testing of the connections; â€¢ Continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the construction activities; and â€¢ Continue to assess the project implementation schedule and the network design to identify ways to speed up the build-out and â€œlighting upâ€ of the network and to reduce network construction, operational and maintenance costs. | 100 | As the remaining FAP construction is completed, the remaining equipment is installed in the FAPs, the Community Anchor Institutions are connected, and all backbone node equipment is installed, equipment will be tested and deployed, and the team will be positioned to come in line with the Baseline Indicator target. | 100 | As the remaining FAP construction is completed, the remaining equipment is installed in the FAPs, Community Anchor Institutions are connected, and the remaining backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator target. Network testing will be ongoing in alignment with network build out and equipment deployment. | 2014-02-28 11:50 | 2014-02-28 11:50 | 7316 | 7316 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570097 | 2010 | Q4 | Q4 - 2010 | 990 | 2033 | FALSE | 3 | N/A | 0 |  | N/A | 70 | Final contracts will be awarded mid-quarter and the EA's will be started. Given timing and winter weather conditions, the EA's will not be totally completed until Q4. State regulations and the type of contracts will push expenditures into Q4. While they will not be completed a significant amount of information will be gathered for input into the Draft EA which will be submitted early Y1Q4. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-07 11:56 | 2011-02-07 11:56 | 6064 | 6064 | Department of Information Technology | TRUE
NT10BIX5570097 | 2011 | Q1 | Q1 - 2011 | 1468 | 2447 | FALSE | 11 | N/A | 24 | Administer and oversee performance in all aspects of grant | Contracts negotiated for construction of DMW sites; Activities to define the RFP for the 700MHz LTE work will begin. | 90 | While funds have been encumbered, some actual expenditures may be pushed into the next quarter due to the timing/completion of tasks required. Also, much of the State is experiencing extremely dry conditions with numerous fires already occurring. This could have an affect on completion due to an inability to access certain areas. | 10 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | The State will be signing the initial contracts for Design and Planning on the DMW sites during this quarter. This will be presented for approval to/by the State's Project Certification Committee in May. However, equipment cannot be purchased until a) the design has been approved for a particular site, and b) the State's Project Certification Committee approves the release of funds for the Project Implementation Phase. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-04-25 17:46 | 2011-04-25 17:46 | 6064 | 6064 | Department of Information Technology | TRUE
NT10BIX5570097 | 2011 | Q2 | Q2 - 2011 | 3146 | 3333 | FALSE | 20 | no variance | 75 | Administer and oversee performance in all aspects of grant | Contracts will be negotiated for construction of DMW sites; Activities to define the RFP for the 700MHz LTE work will begin. The $11.6M in-kind match will be allocated. | 100 | The Draft EA was submitted on 07/13 and comments received from NTIA 08/04. DoIT will be addressing the comments and will resubmit the final version during the quarter. Final expenditures for Environmental Assessments will cross into the next quarter due to the timing/completion of tasks required. | 10 | Network design will be started once the DMW contracts have been executed. | 0 | N/A | 20 | Permits and other approvals will be started during the design phase. | 0 | no variance | 10 | The State will process contract for design and planning on the DMW sites next quarter. Equipment cannot be purchased until a) the design has been approved for a particular site, and b) the State's Project Certification Committee approves the release of funds for the Project Implementation Phase. | 5 | no variance | 0 | no variance | 0 | no variance | 2011-08-17 11:36 | 2011-08-17 11:36 | 7092 | 7092 | Department of Information Technology | TRUE
NT10BIX5570097 | 2011 | Q3 | Q3 - 2011 | 4366 | 4039 | FALSE | 20 | $1.5 million will be awarded in construction contracts. Additional purchase orders will be awarded in the amount of Ten Million dollars. | 75 | Admi nister and oversee performance in all aspects of grant | Contracts will be negotiated for construction of DMW sites; Activities to define the RFP for the 700MHz LTE work will begin. | 100 | The Draft EA was submitted on 07/13 and comments received from NTIA 08/04. The final EA can not be completed until site design details are coordinated with USFS. Therefore, a Programmatic Agreement (PA) was drafted by NTIA in September 2011 which will allow a conditional FONSI to be issued which allows site design and construction to take place. The PA is being reviewed and signed by all interested parties. | 10 | Three construction contracts will be awarded in Q2-Y2. System design will commence. | 0 | N/A | 0 | Construction Contracts not awarded. Estimate no construction to be completed in Year 2 Quarter 2. | 0 | Construction Contracts not awarded. Estimate no site construction during Year 2 Quarter 2. | 10 | Purchase agreements for major hardware item (Radio Kit, Shelter, Tower and Battery Vendors) will be awarded in Q2-Y2. | 0 | No network components will be installed in Q2-Y2. First deployment anticipated in Q3-Y2 | 0 | No network components will be installed in Q2-Y2. First deployment anticipated in Q3-Y2 | 0 | No network components will be installed in Q2-Y2. First deployment anticipated in Q3-Y2 | 2011-12-01 12:17 | 2011-12-01 12:17 | 7092 | 7092 | Department of Information Technology | TRUE
NT10BIX5570097 | 2011 | Q4 | Q4 - 2011 | 4434 | 4083 | FALSE | 18 | 1. Overall hardware acquisition accelerated and hardware delivered 2. Civil construction accelerated at all site where winter weather is not a factor. Other sites will be addressed as weather permits; likely April 2012 and beyond | 55 | Admi nister and oversee performance in all aspects of grant | Assumes management, administrative, and legal effort is linear across 36 month grant period. | 100 | FONSI has been issued. | 54 | Radio Frequency (RF) design completed. Civil design (Professional Engineer Stamped Drawings) 50% to 60% completed. Network Integration and Test Plan drafted. System Transition Plan drafted. | 0 | N/A | 13 | Civil construction commencing at 6 to 10 sites | 13 | Civil construction commencing at 6 to 10 sites | 30 | 1. Procure 10 DMW RF Kits 2. Procure 12 DMW towers 3. Procure 12 DMW shelter 4. Procure 7 DMW battery/rectifier systems 5. Procure 20 DMW network routers | 13 | Civil construction commencing at 6 to 10 sites 1. Towers deployed at 2 sites 2. Shelters deployed at 2 sites 3. Battery/rectifiers deployed at 5 sites | 4 | 1. RF kits deployed at 2 to 5 sites 2. Network routersw deployed at 2 to 5 sites | 4 | Network testing at 2 sites. Limited network testing during factory acceptance testing (FAT) | 2012-01-24 19:50 | 2012-01-24 19:50 | 7092 | 7092 | Department of Information Technology | TRUE
NT10BIX5570097 | 2012 | Q1 | Q1 - 2012 | 6200 | 5702 | FALSE | 54 | No funds will be expended on 700MHz LTE equipment until directed by NTIA/Firstnet. Middle Mile Percentage Completed is based on: Middle Mile $30,018,996 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $47,018,999 Expended $29,869,280 Percentage 63% 700MHz LTE Percentage Completed is based on: LTE $8,681,001 Cash Match $0.00 Total $8,681,001 Expended $0.00 Percentage 0% Overall Percentage Completed is based on: Middle Mile $38,699,997 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $55,700,000 Expended $29,869,280 Percentage 54% | 64 |  | Assumes management, administrative, and legal effort is linear across 36 month grant period. | 100 | No Variance | 82 | 100% of the DMW design has been completed, no design for LTE can start until an equipment decision has been made/directed. | 0 | N\A | 95 | Expected delays in getting permits processed through other federal agencies. | 60 | Expected that 20 of the 29 sites will have begun construction. | 50 | All DMW equipment will have been procured and paid for except the Security Systems, which will have been ordered but will not be paid for until delivered and installed. Batteries will have been paid for, but installation will be contingent on construction schedules. We do not expect to expend any funds on LTE equipment this quarter. | 20 | Installation will be in conjunction with the RF installation. Equipment installation will not begin until mid-to-late May. | 50 | Equipment deployment is predicated on the construction and implementation schedules. While all equipment will be received and paid for, actual delivery and installation will be done on a just-in-time basis. | 50 | Limited network testing will be conducted during factory acceptance testing (FAT). Final testing is predicated on construction and implementation schedules over the next eight months. | 2012-05-18 15:39 | 2012-05-18 15:39 | 7310 | 7310 | Department of Information Technology | TRUE
NT10BIX5570097 | 2012 | Q2 | Q2 - 2012 | 7022 | 6138 | FALSE | 63 | All equipment was ordered and has been accepted and paid for during the quarter. Construction has been started at over 20 sites: Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $34,693,497 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $51,693,500 Expended $35,019,000 Percentage 68% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0% Overall Percentage Completed is based on: Overall $38,699,997 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $55,700,000 Expended $35,019,000 Percentage 63% | 72 |  | Assumes management, administrative, and legal effort is linear across 36 month grant period ending 07/31/2013. | 100 | EA's will be completed as needed for the nine out of scope sites that are expected to be approved. | 90 | 100% of the DMW design, to include approved out of scope sites, will be completed, no design for LTE will commence until after approval of the budget amendment. | 0 | N/A | 100 | All permits and approvals will be completed | 90 | Construction should be started at all but one or two sites | 67 | Area New Budget Amount Spent % Spent Remaining % Remaining DMW 17,293,716.00 13,251,129.58 77% 4,042,586.42 23% LTE 2,443,000.00 0 0% 2,443,000.00 100% Overall 19,736,716.00 13,251,129.58 67% 6,485,586.42 33% In the Budget modification an additional $3.4 million has been reallocated from LTE to the DMW in the Equipment Market. Additional equipment will be procured for the proposed Out of Scope sites once the budget modification is approved. We do not expect to expend any funds on LTE equipment this quarter due to the suspension | 10 | Installation will be in conjunction with the RF installation. Equipment installation will not begin until September. | 70 | Equipment deployment is predicated on the construction and implementation schedules. While all equipment will be received and paid for, actual delivery and installation will be done on a just-in-time basis. The majority of the towers and shelter will be installed, deployment of radios and routers will begin in September. | 50 | Limited network testing will be conducted during factory acceptance testing (FAT). Final testing is predicated on construction and implementation schedules over the next eight months. | 2012-08-10 16:56 | 2012-08-10 16:56 | 7310 | 7310 | Department of Information Technology | TRUE
NT10BIX5570097 | 2012 | Q3 | Q3 - 2012 | 7792 | 6597 | FALSE | 71 | All equipment was ordered and has been accepted and paid for during the quarter. Construction has been started at over 20 sites: Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $34,693,497 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $51,693,500 Expended $39,677,000 Percentage 76% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0% Overall Percentage Completed is based on: Overall $38,699,997 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $55,700,000 Expended $39,677,000 Percentage 71% | 83 |  | Assumes management, administrative, and legal effort is linear across 36 month grant period ending 07/31/2013. | 100 | EA's will be completed as needed for the nine out of scope sites that are expected to be approved. | 90 | 100% of the DMW design, to include approved out of scope sites, will be completed. No design for LTE will commence until after approval of the budget amendment. | 0 | N/A | 89 | Waiting on USFS internal process approval of Risk Assessment. ABQ NOAA is on hold pending final determination of use. | 89 | Site prep will be completed at 26 sites. | 74 | Area Budget Spent % Spent DMW $17,293,716 $14,647,500 85 LTE $ 2,443,000 $ 0 0 Overall $19,736,716 $14,647,500 74 Additional equipment will be procured for the proposed Out of Scope sites once the route modification is approved. We do not expect to expend any funds on LTE equipment this quarter due to the suspension. | 10 | Installation will be in conjunction with the RF installation. Equipment installation will continue through the quarter. | 80 | Towers and Shelters will be installed at all but two sites. Antennas, waveguides, and radio/router equipment will be installed at an estimated 40 sites. | 50 | Limited network testing will be done as part of the installation. Final network testing will be completed prior to putting a link into production. | 2012-11-07 16:29 | 2012-11-07 16:29 | 7599 | 7599 | Department of Information Technology | TRUE
NT10BIX5570097 | 2012 | Q4 | Q4 - 2012 | 8338 | 7010 | FALSE | 72 | Final equipment will be ordered, with most of it being accepted and paid for during the quarter. Construction will be completed at 27 of the 29 sites and the other 2 started (weather permitting). Continued installation of all radio/network equipment with additional links brought up for testing. Preparation for implementation. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $34,693,497 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $51,693,500 Expended $40,356,055 Percentage 78% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0% Overall Percentage Completed is based on: Overall $38,699,997 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $55,700,000 Expended $40,356,055 | 88 |  | Assumes management, administrative, and legal effort is linear across 36 month grant period ending 07/31/2013. | 100 | No variance | 90 | 100% of the DMW design, to include approved out of scope sites, will be completed. No design for LTE will commence until after the suspension is lifted. | 0 | N/A | 93 | Waiting on insurance to finalize new USFS leases. | 93 | Site prep will be completed at 27 sites | 79 | Area Budget Spent % Spent DMW $17,293,716 $15,624,487.28 90 LTE $ 2,443,000 $ 0 0 Overall $19,736,716 $15,624,487.28 79 Additional equipment will be procured for the proposed Out of Scope sites. We do not expect to expend any funds on LTE equipment this quarter due to the suspension. | 10 | Installation will be in conjunction with the RF installation. Equipment installation will continue through the quarter. | 80 | Towers and Shelters will be installed at all but two sites. Antennas, waveguides, and radio/router equipment will be installed at an estimated 54 sites. | 50 | Limited network testing will be done as part of the installation. Final network testing will be completed prior to putting a link into production. | 2013-01-29 12:23 | 2013-01-29 12:23 | 7599 | 7599 | Department of Information Technology | TRUE
NT10BIX5570097 | 2013 | Q1 | Q1 - 2013 | 9190 | 8023 | FALSE | 85 | The DMW portion will be almost complete. The LTE project will be in the early stages of negotiating MOA's/Leases and starting the Design Phase. | 96 |  | Assumes management, administrative, and legal effort is linear across 36 month grant period ending 07/31/2013. | 100 | No Variance | 100 | No Variance | 0 | NA | 100 | USFS leases should be finalized | 96 | Depending on date of lease/permits, site preparation may still be on-going | 100 | All additional equipment will be delivered and paid for. | 65 | Current plans call for 1184 network miles to be going through the "burn in" and testing | 90 | All batteries, waveguides, antennas, radios, and routers will be installed at all but two sites. | 70 | DoIT will still be conducting limited network testing as part of the installation. Final network testing will be completed prior to putting a link into production. | 2013-04-18 15:19 | 2013-04-18 15:19 | 7599 | 7599 | Department of Information Technology | TRUE
NT10BIX5570097 | 2013 | Q2 | Q2 - 2013 | 10456 | 8874 | FALSE | 81 | The DMW portion will be almost complete. The LTE project Spectrum Lease Agreement will be signed, in the early stages of negotiating MOA's/Leases with Texas and other Stakeholders (Federal Agencies, Counties, Etc.) and starting developing the 700MHz RFP. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $34,693,497 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $51,693,500 Expended $44,954,149 Percentage 87% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0% Admin & Legal Percentage Completed is based on: Total $2,708,999 Expended $1,544,900 Percentage 57% Admin funds have been expended for general project support to include legal support for LTE Spectrum Lease Agreement negotiations. Overall Percent | 100 |  | Assumes management, administrative, and legal effort is linear across 38 month grant period ending 09/30/2013. If the extension to 2015 is granted this number will be recalculated to cover the new time frame. | 100 | No variance | 100 | No variance | 0 | NA | 84 | All DMW permits & approvals should be finalized. Final count of permits/approvals for LTE will be for installation at 8 to 13 sites (16%) depending on final design. | 96 | Depending on date of lease/permits, site preparation may still be on-going | 88 | Area Budget Amt. Amt. Spent % Spent DMW $17,293,715.62 $17,293,715.62 100 LTE $ 2,443,000.00 $ 0.00 0.0 Overall $19,736,715.62 $16,914,463.69 88 100% of the DMW equipment will have been purchased. The remaining 12% of the total is for LTE equipment. The LTE equipment will be purchased in a later quarter. | 90 | All but two DMW links should be up and operational. | 90 | All DMW equipment operational except at two sites being constructed. | 90 | DoIT will still be conducting limited network testing as part of the installation. Final network testing will be completed prior to putting a link into production. | 2013-07-31 11:48 | 2013-07-31 11:48 | 7599 | 7599 | Department of Information Technology | TRUE
NT10BIX5570097 | 2013 | Q3 | Q3 - 2013 | 11222 | 9401 | FALSE | 81 | The DMW portion will be almost complete. The LTE project Spectrum Lease Agreement will be signed, in the early stages of negotiating MOA's/Leases with Texas and other Stakeholders (Federal Agencies, Counties, Etc.) and starting developing the 700MHz RFP. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $34,693,497 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $51,693,500 Expended $43,973,387 Percentage 85% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0.00 Total $4,006,500 Expended $0.00 Percentage 0.0% Admin & Legal Percentage Completed is based on: Total $2,708,999 Expended $1,695,760 Percentage 62% Admin funds have been expended for gen | 70 |  | Assumes management, administrative, and legal effort is linear across the 60 month grant period. This has been recalculated due to the 24 month extension. | 100 | No variance | 100 | No variance | 0 | NA | 84 | Final count of permits/ approvals for LTE will be for installation at 8 to 13 sites (16%) depending on final design. | 93 | 2 of the DMW sites will not begin until Q2CY14. | 88 | Area Budget Amt. Amt. Spent % Spent DMW $17,293,715.62 $17,293,715.62 100 LTE $ 2,443,000.00 $ 0.00 0.0 Overall $19,736,715.62 $16,914,463.69 88 100% of the DMW equipment will have been purchased. The remaining 12% of the total is for LTE equipment. This will be purchased in a later quarter after design has been completed. | 90 | All links (BTOP/non-BTOP) will be up with a large percentage operational. Only those the new links at Coyote and Eureka will not be completed. | 90 | All DMW equipment operational except at two sites to be constructed. | 90 | Limited network testing as part of installation will be nearly completed. Tinal testing will be completed on many of the links with the links going into a production status. | 2013-11-08 10:59 | 2013-11-08 10:59 | 7599 | 7599 | Department of Information Technology | TRUE
NT10BIX5570097 | 2013 | Q4 | Q4 - 2013 | 11876 | 10046 | FALSE | 83 | The DMW portion will be almost complete. The LTE project Spectrum Lease Agreement was signed. Still in the early stages of negotiating MOA's/Leases with Texas and other Stakeholders (Federal Agencies, Counties, etc. ) and starting developing the 700 LTE RFP. Percentage breakdowns: Middle Mile Percentage Completed is based on: Middle Mile $31,984,498 Cash Match $5,399,999 In-Kind Match $11,600,004 Total $48,984,501 Expended $44,037,509 Percentage 89.9% 700MHz LTE Percentage Completed is based on: LTE $4,006,500 Cash Match $0 Total $4,006,500 Expended $0 Percentage 0.0% Admin & Legal Percentage Completed is based on: Total $2,708,999 Expended $2,423,389 Percentage | 70 |  | Assumes management, administrative, and legal effort is linear across the 60 month grant period. This has been recalculated due to the 24 month extension. | 100 | No variance | 100 | No variance | 0 | NA | 88 | Pending the outcome of the February 24, 2014 CBP meeting, the number of permits and other approvals will be determined. | 93 | 2 of the DMW sites will not begin until Q2CY14. | 88 | Area Budget Amt. Amt. Spent % Spent DMW $17,293,715 $16,790,659 97.1 LTE $ 2,443,000 $ 0 0.0 Overall $19,736,715 $16,790,659 85.1 97% of the DMW equipment will have been purchased. The remaining 3% will be purchased the following quarter. The remaining 12% of the total equipment budget is for LTE equipment. This will be purchased in a later quarter after design has been completed. | 64 | All links (BTOP/non-BTOP) will be up with a large percentage operational. Only those the new links at Coyote and Eureka will not be completed due to winter weather and contract issues. | 90 | All DMW equipment operational except at two sites to be constructed. Delay incurred due to winter weather and contract issues. | 90 | Limited network testing as part of installation will be nearly completed. Final testing will be completed on many of the links with the links going into a production status. | 2014-02-24 13:05 | 2014-02-24 13:05 | 7599 | 7599 | Department of Information Technology | TRUE
NT10BIX5570098 | 2010 | Q4 | Q4 - 2010 | 1206 | 2237 | FALSE | 5 | N/A | 0 | N/A | N/A | 95 | N/A | 21 | N/A | 26 | N/A | 40 | N/A | 0 | N/A | 5 | N/A | 0 | N/A | 5 | N/A | 0 | N/A | 2011-02-17 13:25 | 2011-02-17 13:25 | 6104 | 6104 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2011 | Q1 | Q1 - 2011 | 2084 | 2787 | FALSE | 8 | While there will be an acceleration of spending, overall project will under run next quarter largely due to withholding activities (such as permits and initial materials orders) that are dependent on the issuance of a FONSI. This is expected in early October. | 0 |  | NA | 95 | Revisions to the environmental assessment will extend into June, with agency and public commentary beginning in late June. In addition a new Programmatic agreement will be circulating in May, which will define cultural study parameters to complete field studies. | 37 | No Variance | 25 | We expect the rights-of-way to under run budget due to timeframes for negotiations and documentation with larger federal and state agencies. | 40 | Construction permits from key state and federal agencies will likely follow the issuance of the FONSI in October. Permits that can be issued prior to that are being paid. | 0 | There will be no site preparation until after FONSI is issued in October. | 5 | The baseline plan called for the initial acquisition of Node buildings in Quarter 3. This has been deferred until Quarter 4 since the FONSI date is scheduled in October. There is no need to acquire structures at this time only to store them. Project plan calls for the development of significant RFPs in the next Quarter. | 0 | No Variance | 8 | No Variance | 0 | No Variance | 2011-05-17 11:27 | 2011-05-17 11:27 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2011 | Q2 | Q2 - 2011 | 2992 | 3253 | FALSE | 12 | Although we expect an acceleration of spending in the next quarter, overall project spending will underrun due to delay of EA until October and materials acquisitions in September - October. | 0 |  | NA | 100 | No Variance | 50 | 3% underun. Working drawings for backbone designs 80% complete. 25% distribution area deisigns complete | 89 | No Variance | 60 | 40% underrun. Construction permits will not be available in 3QTR11, since DOT permits will not be issued until after FONSI and Mitigated Negative Declaration is issued. We anticipate Permits in all federal lands. | 6 | 60% underrun, as site preparation will no be allowed prior to FONSI. Aquisition of all sites will be finalized. RFPs will be issued and we will be ready to construct for October once FONSI in place. | 12 | 10% under-run. Due to the anticipated October issuance of FONSI, Electronics RFP process has been deferred until August Timeframe. Equipment purchase is expected 4QTR2011. | 0 | 25% underrun. Construction not started until permits are made available | 8 | 14% underrun. No equipment has been deployed due to delay in FONSI and Construction | 0 | No Variance | 2011-08-09 18:10 | 2011-08-09 18:10 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2011 | Q3 | Q3 - 2011 | 3966 | 3821 | FALSE | 15 | 33% Variance. Delays in receiving environmental permits which has delayed Finding of No Significant Impact and delayed the construction start date. All other gaps in planned progress emanate from this. | 0 |  | NA | 99 | 1% Variance. Request for Proposal issued and awarded for Monitoring Contractor. Monitoring plan initiated. Programmatic Agreement work continues into next Quarter. | 70 | Ahead 7%. Backbone and cable 95% complete. Distribution Engineering 20% complete. Anchor-Points of Interconnection entrance facilities and laterals 10% complete. All Node site engineering complete. | 95 | 5% Variance. Private Right of Way issues, Bureau of Indian Affairs and Tribal issues to be resolved. | 75 | 25% Variance. Backbone in pipeline, pending 30 day review cycle. Some county and city permits remain. | 25 | 75% Variance. Architectural renderings and site engineering complete and site prep Request for Proposal issued. | 12 | 42% Variance. Node Request for Proposal issued. Receiving deliveries of cable, conduit and vaults in northern construction zone. Additional tools, equipment and motor vehicles acquired. | 10 | 34% Variance. Anticipate receiving Finding of No Significant Impact . Material deliveries begun. All depots sites identified. Gardnerville depot fully operational. | 12 | 33% Variance. Receiving deliveries of cable, conduit and vaults in northern construction zone. Additional tools, equipment and motor vehicles acquired. | 0 | 6% Variance. Construction Not Started | 2011-11-10 15:34 | 2011-11-10 15:34 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2011 | Q4 | Q4 - 2011 | 5128 | 4794 | FALSE | 27 | Underrun of baseline by 31% -- while all pre-construction activities for the project are essentially complete, challenges initiating construction account for the underrun, due to delays in FONSI and related permits. | 0 |  | NA | 95 | Under-run by 5% -- While biological issues will resolve and the FONSI be issued, reissuing of the Programmatic Agreement for signature and the review of an additional 110 cultural sites will extend the site reviews into the May timeframe. | 85 | Exceed baseline by 11% -- Working drawings of backbone complete in all sections, 70% of distribution plant finalized, completion of Anchor site surveys | 95 | Under-run of baseline by 5% -- Rights of Way in a 6.4 mile section of Hwy 58 and select tribal lands will require additional time for resolution. Initiatives on the private sections are underway and BIA processes have begun with tribal councils and allotments. | 80 | Underrun of baseline by 20% - Mitigation plans and construction permits will not be issued until just prior to construction in each section of the route. On the whole, major permits will have been obtained from water quality and wildlife monitoring agencies. | 50 | Underrun of baseline by 50% - physical site preparation has been restrained until FONSI issued. Architectural plans and construction awards will complete. Node permits on 9 sites will be issued and 4 special permits will follow in April. Physical site construction will begin mid-March on several sites and accelerating toward 2Qtr12 finish. | 80 | Exceeds baseline by 16% -- all major material procurements for nodes, Outside Plant (cable, conduit, vaults, and apparatus), electronics will complete. | 14 | Underrun of baseline by 38% - due to delays in the issue of FONSI and PA, the project will initiate ground-breaking in several of the 20 segments in Nevada and California devoid of cultural sites | 35 | Underrun of baseline by 21% -- deliveries of materials, (175 miles of cable and 240 trench miles of conduit, nodes and electronics) will not complete until the following quarter. | 0 | Underrun of baseline by 15% -- due to permit delays and placement of cable. | 2012-02-17 18:59 | 2012-02-17 18:59 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2012 | Q1 | Q1 - 2012 | 6334 | 5769 | FALSE | 49 | 26% Variance - delays in Federal and State permits. | 0 |  | NA | 97 | Under-run by 3% - Mitigation Monitoring & Reporting Plan, Finding of No Significant Impact and initial Programmatic Agreement Segment Reports will have been issued. Half of the Programmatic Agreement Segment Reports will have been reviewed and approved according to the NTIA schedule. | 90 | Exceed baseline by 5%, all back bone work drawings to be complete, distribution work drawings will be 90% complete, network electronic architecture design will be 85% complete, all anchor surveys will be completed, and 35% of anchor contracts will be secured. | 100 | No variance - All Right of Ways secured. | 100 | No variance - all permits secured | 70 | 30% variance - all but (5) node sites will have been completed. The remaining (5) are scheduled for completion in July 2012 | 90 | Ahead by 12% - Project equipment secured with exception of NOC equipment and billing systems. | 20 | 55% Variance - Conduit placement underway in all (5) contractor bid zones, most all Node will enclosures installed, some cable placement commencing. | 35 | 39% Variance - Delay in project start will not permit placement of transmission electronics until 7/2012. | 0 | 25% variance - Delayed project start has pushed splicing into end of 3rd and 4th quarter respectively. | 2012-05-29 16:09 | 2012-05-29 16:09 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2012 | Q2 | Q2 - 2012 | 6848 | 6050 | FALSE | 48 | 42% Variance - delays due to Programmatic Agreement delayed construction start. | 0 | true | NA | 98 | 2% Variance - The last three groups of Programmatic Agreement Segment Reports remain to be reviewed. | 100 | Exceed baseline by 3% - All distribution engineering will be complete, network electronic architecture will be complete, and most anchor contracts will be secured. Remaining engineering relates to anchor connections and "as-built" validations. | 100 | No Variance - Rights of Way secured. | 85 | 15% Variance - Issuance of Notice to Proceed by the agencies will be based upon the release of the Programmatic Agreement Segment Groups. | 75 | 25% Variance - Half of the Node sites remain until approval of Programmatic Agreement Segment Groups. | 100 | Exceed baseline by 8% - All equipment to be secured. | 30 | 63% Variance - Conduit placement underway in all (5) contractor bid zones, half of the nodes built and cable placement continuing. | 50 | 50% Variance - All transmission electronics dependent on node construction, which are dependant on PA approval. | 0 | 41% Variance - No complete sections of the network available until 4th quarter. | 2012-08-03 12:00 | 2012-08-03 12:00 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2012 | Q3 | Q3 - 2012 | 8124 | 6769 | FALSE | 63 | (32% Variance)Delays due to the Programmatic Agreement | 0 |  | NA | 98 | (2% Variance) Programmatic Agreement Segment Groups 9 and 10 will not be approved until the first quarter of 2013. | 95 | No Variance | 100 | No Variance | 95 | (5% Variance)Programmatic Agreement Segment Groups 9 and 10 and associated Encroachment Permits will not be approved until the first quarter of 2013. Bureau of Indian Affairs will rule on Nevada Allotments. | 80 | (20% Variance) All node sites will be prepared, except for three nodes in areas not approved under Programmatic Agreement. | 97 | No Variance | 30 | (67% Variance) 40% of the backbone construction will be completed, 5% of anchors connected, and 5% of distribution conduit and cable will be deployed. | 60 | (38% Variance) Electronic equipment will be deployed and tested to seven of 11 nodes, including end-nodes (Reno and Barstow) | 30 | (40% Variance) Testing for 2 node spans will be completed in Mono County. | 2012-11-28 16:09 | 2012-11-28 16:09 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2012 | Q4 | Q4 - 2012 | 9026 | 7796 | FALSE | 72 | 25% Variance - Due to delayed permits and winter conditions. We will continue to close gap | 0 |  | NA | 100 | No Variance | 99 | No Variance | 100 | No Variance | 100 | No Variance | 85 | 15% under run of target, due to final construction of the Olancha and Independence Nodes sites | 98 | Ahead 1% - Due to acquisition of distribution cable in Q4 2012 | 60 | 40% Variance - All but three nodes will be completed. 75% of backbone to be completed, Ridgecrest distribution to be completed, and connection of 25 anchors and points of interconnection will be complete. | 75 | 24% Variance - Due to electronics not deployed in four nodes | 60 | 25% Variance - Due to inability to end to end test backbone and select potions of the distribution system cable. | 2013-02-27 15:37 | 2013-02-27 15:37 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2013 | Q1 | Q1 - 2013 | 9938 | 8512 | FALSE | 83 | The variance of 17% is due to delays in permits and winter weather impacts in areas where permitting was allowed, largely Mono County. | 0 |  | NA | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 75 | Variance of 25% under run due to final construction of anchors, Points of interconnection, and potential areas where Route Changes are still being approved. | 100 | No Variance | 85 | Variance to of 15% to 100% target due to having sub-system testing completed only. End-to-end network, Operational Support Systems integration testilng and testing of uncompleted anchor connections will continue into the following quarter. | 2013-05-28 15:08 | 2013-05-28 15:08 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2013 | Q2 | Q2 - 2013 | 10536 | 8922 | FALSE | 96 | 4% Variance - Due to late construction start due to Programmatic Agreement requirements and execution, delays in permit issuance and route changes. The latter consist of anchor routes and five changes required on the backbone. | 0 |  | NA | 99 | 1% Variance - Due to environmental studies for anchor route changes and the Inyo National Forest Service. Agency(s) review of planned supplemental surveys in progress. Environmental studies completed for (18) anchor route changes in addition to test pits and supplemental field survey analysis being performed on the last backbone segment required by the Inyo National Forest Service. | 99 | 1% Variance - Due to the special studies needed for the Inyo National Forest Service and anchor route changes. | 100 | All Rights of Way completed | 99 | 1% Variance - Due to pending approval of anchor route changes by the NTIA and approval of supplemental environmental plan for Segment M112 by the Inyo National Forest Service. | 100 | All Site Preparation completed | 100 | No Variance - All equipment procured | 95 | 5% Variance - Due to pending approval of anchor route changes by the NTIA and approval of supplemental environmental plan for Segment M112 by the Inyo National Forest Service. | 100 | No variance - all equipment deployed | 70 | 30% Variance - Due to incomplete end-to-end fiber spans held up by multiple NDOT parallel drainage variance approvals, multiple ESA long bores and delayed P.A. segment approval for M122. | 2013-08-09 11:43 | 2013-08-09 11:43 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2013 | Q3 | Q3 - 2013 | 11326 | 9463 | FALSE | 100 | No Variance | 0 |  | NA | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2013-11-21 13:02 | 2013-11-21 13:02 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | 2013 | Q4 | Q4 - 2013 | 11874 | 10045 | FALSE | 100 | We will expend 107% of our overall budget. | 0 | true | NA | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2014-02-24 12:23 | 2014-02-24 12:23 | 6103 | 6103 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570099 | 2010 | Q4 | Q4 - 2010 | 1328 | 2350 | FALSE | 1 | There has been delay due to revision of final route for efficiency and the unanticipated Engineering RFP process. Also unusually heavy snowfall in the 1st quarter of 2011 is expected to cause delay. | 0 |  | N/A | 100 | N/A | 5 | There has been delay due to revision of final route for efficiency and the unanticipated Engineering RFP process. Also unusually heavy snowfall in the 1st quarter of 2011 is expected to cause delay. | 0 | There has been delay due to revision of final route for efficiency and the unanticipated Engineering RFP process. Also unusually heavy snowfall weather in the 1st quarter of 2011 is expected to cause delay. | 0 | There has been delay due to revision of final route for efficiency and the unanticipated Engineering RFP process. Also unusually heavy snowfall weather in the 1st quarter of 2011 is expected to cause delay. | 0 | There has been delay due to revision of final route for efficiency and the unanticipated Engineering RFP process. Also unusually heavy snowfall weather in the 1st quarter of 2011 is expected to cause delay. | 0 | N/A | 0 | There has been delay due to revision of final route for efficiency and the unanticipated Engineering RFP process. Also unusually heavy snowfall weather in the 1st quarter of 2011 is expected to cause delay. | 0 | N/A | 0 | N/A | 2011-02-23 11:36 | 2011-02-23 11:36 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2011 | Q1 | Q1 - 2011 | 1966 | 2728 | FALSE | 6 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 20% completion of the overall project. However, as stated previously, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to make significant project progress by the end of Quarter 2, 2011. | 0 |  | N/A | 100 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the environmental assessment, therefore this projection is on target with the baseline plan submitted. | 60 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the Network Design. However, as stated previously, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to make significant network design progress by the end of Quarter 2, 2011. | 50 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the Rights of Way. However, as stated previously there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to make significant rights of way progress by the end of Quarter 2, 2011. | 50 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the Construction Permits and Other Approvals. However, as stated previously, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Q1 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to make significant construction permits and other approval progress by the end of Quarter 2, 2011. | 0 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 75% completion of the Site Preparation. However, as stated previously, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Q1 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to be back on schedule soon after the end of Quarter 2, 2011. | 0 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 5% completion of the Equipment Procurement. However, as stated previously, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. plans to be back on schedule soon after the end of Quarter 2, 2011. | 0 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 25% completion of the Network Build. However, as stated previously, there were some initial delays due to revision of final route for efficiency and the unanticipated Engineering Request for Proposals process. Also unusually heavy snowfall in Quarter 1, 2011 has caused some delay. With the revised route being approved, the engineering firm selected, and warmer weather around the corner, Bloomingdale Communications, Inc. anticipates the network build to be pushed back two quarters later than initially projected. | 0 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 0% completion of the equipment deployment, therefore this projection is on target with the baseline plan submitted. | 0 | For Year 1 Quarter 4 of the award period which is next quarter (Quarter 2, 2011), Bloomingdale Communications, Inc. initially projected 0% completion of network testing, therefore this projection is on target with the baseline plan submitted. | 2011-05-12 12:04 | 2011-05-12 12:04 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2011 | Q2 | Q2 - 2011 | 2980 | 3247 | FALSE | 20 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 40% completion of the overall project. However, as stated previously, there were some initial delays, however with the Finding of No Significant Impacts and the fiber vendor being selected as well as a warm summer quarter, Bloomingdale Communications, Inc. plans to make significant overall project progress by the end of Quarter 3 of 2011. | 0 |  | N/A | 100 | Completed. | 95 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the Network Design, therefore this category is expected to be on schedule. | 100 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the Rights of Way, therefore this category is expected to be on schedule. | 100 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the Construction Permits and Other Approvals, therefore this category is expected to be on schedule. | 75 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the Site Preparation. However, as stated previously, there were some initial delays, however with the Finding of No Significant Impacts and the fiber vendor being selected as well as a warm summer quarter, Bloomingdale Communications, Inc. plans to make significant site preparation progress in Quarter 3 of 2011. | 0 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 90% completion of the Equipment Procurement. However, as stated previously, there were some initial delays, however with the Finding of No Significant Impacts and the fiber vendor being selected as well as a warm summer quarter, Bloomingdale Communications, Inc. plans to be back on schedule soon after the outside plant construction contract is awarded. | 25 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 75% completion of the Network Build. However, as stated previously, there were some initial delays, however with the Finding of No Significant Impacts and the fiber vendor being selected as well as a warm summer quarter, Bloomingdale Communications, Inc. plans to make significant progress with network build, however it is anticipated to remain pushed back two quarters later than initially projected. | 0 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 0% completion of the equipment deployment, therefore this projection is on target with the baseline plan submitted. | 0 | For Year 2 Quarter 1 of the award period which is next quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 25% completion of network testing. However, as stated previously, there were some initial delays, however with the Finding of No Significant Impacts and the fiber vendor being selected as well as a warm summer quarter, Bloomingdale Communications, Inc. plans to make significant progress with network build, however it is anticipated to remain pushed back two quarters later than initially projected as there is an expected fiber shipment delay. | 2011-08-09 14:53 | 2011-08-09 16:50 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2011 | Q3 | Q3 - 2011 | 3908 | 3792 | FALSE | 5 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 0 |  | N/A | 100 | Completed. | 80 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the network design. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 90 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 90 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 95% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 2 of the award period which is next quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor next quarter, the project will begin moving forward rapidly once winter is over. | 2011-11-07 14:15 | 2011-11-07 14:15 | 5994 | 5994 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2011 | Q4 | Q4 - 2011 | 4988 | 4662 | FALSE | 10 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 0 |  | N/A | 100 | Completed. | 80 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the network design. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 95 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 95 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 15 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 0 | For Year 2 Quarter 3 of the award period which is next quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however with selecting the outside plant contractor this quarter, the project will begin moving forward rapidly once winter is over. | 2012-02-14 07:58 | 2012-02-14 07:58 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2012 | Q1 | Q1 - 2012 | 6198 | 5701 | FALSE | 35 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the overall project. However, as stated previously, there were some initial delays, however the project began moving forward rapidly once winter ended. | 0 |  | N/A | 100 | Completed. | 98 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the network design. However, as stated previously, there were some initial delays, however the project began moving forward rapidly once winter ended. | 98 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the rights of way. Bloomingdale Communications, Inc. anticipates this goal to be met next quarter. | 100 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the construction permits and other approvals. Bloomingdale Communications, Inc. anticipates this goal to be met next quarter. | 50 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the site preparation. However, as stated previously, there were some initial delays, however the project began moving forward rapidly once winter ended. | 0 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the equipment procurement. However, as stated previously, there were some initial delays, however the project began moving forward rapidly once winter ended. The equipment Request for Proposal is scheduled to go out by the end of May in next quarter, once the Request for Proposal is released the responses will be reviewed, vendor selected, and then the equipment will be evaluated for the project. This will begin to move forward since construction began this quarter. | 43 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the network build. As stated previously, there were some initial delays, however the project began moving forward rapidly once winter ended and will be on target within the 3 year project completion timeline. | 0 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the equipment deployment. However, as stated previously, there were some initial delays, however the project began moving forward rapidly once winter ended. As mentioned previously, the equipment Request for Proposal is anticipated to be released by the end of May 2012, next quarter, therefore there is no equipment deployment anticipated by the end of next quarter as once the Request for Proposal is released the responses will be reviewed, vendor selected, and then the equipment will be evaluated for the project. The project is moving forward rapildly and will be completed within the 3 year project timeline. | 0 | For Year 2 Quarter 4 of the award period which is next quarter (Quarter 2 of 2012), Bloomingdale Communications, Inc. initially projected 100% completion of the network testing. However, as stated previously, there were some initial delays, however the project began moving forward rapidly once winter ended. | 2012-05-18 14:13 | 2012-05-18 14:13 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2012 | Q2 | Q2 - 2012 | 6974 | 6114 | FALSE | 69 | The BCI project was initially projected to be completed before Year 3 Quarter 1 which is next quarter (Quarter 3 of 2012), however due to initial delays stated in other quarterly reports as well as the re-bid of construction for budget constraints pushed the overall project timeline back. However, this project will be 100% completed within the three year grant window. | 0 |  | N/A | 100 | Completed. | 98 | The network design portion of the project is complete until network testing is completed. | 100 | All rights of ways for easements should be completed by the end of next quarter. | 100 | Completed. | 90 | The majority of the site preparation should be complete by the end of next quarter as the huts will be delivered and installed. | 83 | The majority of the equipment procurement should be completed by the end of next quarter as the vendor will be selected and equipment ordered. | 66 | With the re-bid of the construction portion of the project, the overall timeline was pushed back for the project. However, this project will be completed within the three year timeline of the award period. | 0 | The equipment will not be deployed next quarter, but should be soon after in the following quarter. | 0 | Network testing cannot take place until after the network is constructed and equipment is deployed. The network will be finished prior to the three year award period end. | 2012-08-09 15:03 | 2012-08-09 15:03 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2012 | Q3 | Q3 - 2012 | 8132 | 6773 | FALSE | 88 | The BCI project was initially projected to be completed before Year 3 Quarter 1 which was this quarter (Quarter 3 of 2012), however due to initial delays stated in other quarterly reports as well as the re-bid of construction for budget constraints pushed the overall project timeline back. However, construction is moving along rapidly and this project will be 100% completed within the three year grant window. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 98 | The network design portion of the project is complete until network testing is completed. | 100 | All rights of ways for easements should be completed by the end of next quarter. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 100 | The site preparation should be complete by the end of next quarter. | 83 | The majority of the equipment procurement should be completed by the end of next quarter as the vendor has been selected and some equipment has been ordered. The remaining equipment should be ordered and received this quarter. | 90 | With the re-bid of the construction portion of the project, the overall timeline was pushed back for the project. However, the construction has been moving along rapidly and the project will be completed within the three year timeline of the award period. | 60 | The equipment will be delivered next quarter and therefore the physical installation will begin. | 75 | Network testing should begin next quarter as fiber and splicing are finalizing and equipment will begin installation. If the weather continues to cooperate, the network testing should move right along next quarter. The network will be finished prior to the three year award period end. | 2012-11-29 10:09 | 2012-11-29 10:09 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2012 | Q4 | Q4 - 2012 | 8996 | 7775 | FALSE | 96 | The BCI project was initially projected to be completed before Year 3 Quarter 2 which was this quarter (Quarter 4 of 2012), however due to initial delays stated in other quarterly reports as well as the re-bid of construction for budget constraints pushed the overall project timeline back. However, construction is moving along rapidly and this project will be 100% completed within the three year grant window. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 99 | The network design portion of the project is complete until network testing is completed. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 95 | The majority of the equipment procurement should be completed by the end of next quarter as the majority of the equipment has been received. Installation of the transport equipment will be taking place next quarter. | 95 | With the re-bid of the construction portion of the project, the overall timeline was pushed back for the project. However, the construction has been moving along rapidly as expected and the project will be completed within the three year timeline of the award period. Much progress is expect on all components of the network next quarter. | 95 | Significant progress of the equipment deployment will be made next quarter as the transport equipment will be installed. The DC power and AC upgrade may not be complete until the following quarter. | 98 | Network Testing should be almost complete by the end of next quarter. The network will be finished prior to the three year award period end. | 2013-02-27 08:29 | 2013-02-27 08:29 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2013 | Q1 | Q1 - 2013 | 9812 | 8441 | FALSE | 99 | The BCI project was initially projected to be completed before Year 3 Quarter 2 (Quarter 4 of 2012), however due to initial delays stated in other quarterly reports as well as the re-bid of construction for budget constraints pushed the overall project timeline back. However, construction is moving along rapidly and this project will be 100% completed within the three year grant window. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 99 | The network design portion of the project is complete until network testing is completed. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 97 | The majority of the equipment procurement should be completed by the end of next quarter as the majority of the equipment has been received. Installation of the transport equipment will be taking place next quarter. | 99 | With the re-bid of the construction portion of the project, the overall timeline was pushed back for the project. However, the construction has been moving along rapidly as expected and the project will be completed within the three year timeline of the award period. Much progress is expect on all components of the network next quarter. | 99 | Significant progress of the equipment deployment will be made next quarter as the transport equipment will be installed. The DC power and AC upgrade may not be complete until the following quarter. | 99 | Network Testing should be almost complete by the end of next quarter. The network will be finished prior to the three year award period end. | 2013-05-20 09:32 | 2013-05-20 09:32 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2013 | Q2 | Q2 - 2013 | 10648 | 8984 | FALSE | 100 | The BCI project was initially projected to be completed before Year 3 Quarter 2 (Quarter 4 of 2012), however due to initial delays stated in other quarterly reports as well as the re-bid of construction for budget constraints pushed the overall project timeline back. However, construction is complete and only few items notated above remain for this project. Therefore the project will be 100% completed by the end of next quarter. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 100 | The network design portion of the project will be complete by the end of next quarter. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 100 | The equipment procurement will be complete by the end of next quarter. | 100 | The network build will be complete by the end of next quarter. | 100 | The equipment deployment will be complete by the end of next quarter. | 100 | The network testing will be complete by the end of next quarter. | 2013-08-20 09:36 | 2013-08-20 09:36 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | 2013 | Q3 | Q3 - 2013 | 11908 | 10077 | FALSE | 100 | Although the project is completed, the total budget will not be expended for the project. Overall about 95% of the budget has been expended. | 0 |  | N/A | 100 | Completed Year 1 in 4th Quarter, which was Quarter 2 of 2011. | 100 | Completed Year 4 in 1st Quarter, which was Quarter 3 of 2013. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 100 | Completed Year 2 in 4th Quarter, which was Quarter 2 of 2012. | 100 | Completed Year 3 in 2nd Quarter, which was Quarter 4 of 2012. | 100 | Although the project is completed, the entire Equipment budget will not be expended for the project. About 99% of the Equipment budget has been expended. | 100 | Although the project is completed, the entire Construction budget will not be expended for the project. All construction invoices have been paid in full, therefore about 96% of the Construction budget has been expended. | 100 | Completed Year 4 in 1st Quarter, which was Quarter 3 of 2013. | 100 | Completed Year 4 in 1st Quarter, which was Quarter 3 of 2013. | 2014-02-27 15:46 | 2014-02-27 15:46 | 5995 | 5995 | Bloomingdale Communications Inc | TRUE
NT10BIX5570100 | 2010 | Q4 | Q4 - 2010 | 1230 | 2259 | FALSE | 25 | Baseline is 21%. Slightly ahead of schedule | 0 | N/A | No variance | 100 | No variance | 100 | No variance | 15 | Baseline is 10%. Slightly ahead of schedule | 15 | Baseline is 10%. Slightly ahead of schedule | 0 | No variance | 50 | No variance | 10 | No variance | 0 | No variance | 0 | No variance | 2011-02-18 16:18 | 2011-02-18 16:18 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2011 | Q1 | Q1 - 2011 | 1932 | 2711 | FALSE | 49 | Baseline is 35. Continued progress on construction should keep us ahead of baseline projections. | 0 |  | N/A | 100 | Completed and in line with baseline | 100 | Completed and in line with baseline | 34 | In line with baseline | 22 | In line with baseline | 0 | N/A | 65 | In line with baseline | 30 | Baseline is 19. Continued progress on construction should keep us ahead of baseline projections. | 10 | In line with baseline | 0 | In line with baseline | 2011-05-10 15:40 | 2011-05-10 15:40 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2011 | Q2 | Q2 - 2011 | 3048 | 3281 | FALSE | 60 | Baseline is 41% | 0 |  | N/A | 100 | In line with Baseline | 100 | In line with Baseline | 63 | Baseline is 47% Staying ahead of what is needed for construction | 46 | Baseline is 34% Staying ahead of what is needed for construction | 0 | N/A | 80 | In line with Baseline | 43 | Baseline is 30%. Continue to be ahead of schedule on network construction. | 23 | In line with Baseline | 20 | In line with Baseline | 2011-08-12 14:36 | 2011-08-12 14:36 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2011 | Q3 | Q3 - 2011 | 4032 | 3856 | FALSE | 74 | Baseline is 52. Weather permitting we will stay ahead of schedule. | 0 | NA | NA | 100 | On Baseline | 100 | On Baseline | 78 | Baseline 62. Staying ahead of schedule | 70 | Baseline 47. Staying ahead of schedule | 0 | NA | 74 | Baseline 100. Continue to stay under budget on equipment | 60 | Baseline 40. Staying ahead of schedule | 50 | Baseline 42. Staying ahead of schedule | 33 | On Baseline | 2011-11-14 15:08 | 2011-11-14 15:08 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2011 | Q4 | Q4 - 2011 | 4974 | 4648 | FALSE | 83 | Remain ahead of baseline which is 60 | 0 | None | N/A | 100 | In line with baseline | 100 | In line with baseline | 88 | Ahead of baseline which is 72 | 82 | Ahead of baseline which is 62 | 0 | N/A | 76 | Baseline is 100. We still have some equipment to purchase, but the main reason for the lower figure is being able to acquire equipment below budgeted costs. | 71 | Ahead of baseline which is 51 | 75 | Ahead of baseline which is 50 | 55 | Ahead of baseline which is 52 | 2012-02-13 12:44 | 2012-02-13 12:44 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2012 | Q1 | Q1 - 2012 | 5996 | 5597 | FALSE | 97 | Remain ahead of baseline of 68. | 0 |  | N/A | 100 | In line with baseline. | 100 | In line with baseline. | 93 | Ahead of baseline of 84. | 87 | Ahead of baseline of 72. | 0 | N/A | 83 | Baseline is 100. We still have some equipment to purchase, but the main reason for the lower figure is being able to acquire equipment below budgeted costs. | 90 | Ahead of baseline of 64. | 79 | Ahead of baseline of 63. | 64 | Slightly ahead of baseline of 60. | 2012-05-09 17:12 | 2012-05-09 17:12 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2012 | Q2 | Q2 - 2012 | 7146 | 6200 | FALSE | 100 | 106 Costs have been higher, making up with private money | 0 |  | N/A | 100 | In line | 100 | In line | 96 | In line | 92 | Ahead of baseline of 84 | 0 | N/A | 87 | Baseline is 100. We still have some equipment to purchase, but the main reason for the lower figure is being able to acquire equipment below budgeted costs. | 100 | 102 Construction costs have been higher than estimated, making up with private money | 84 | Ahead of baseline of 74 | 73 | In line | 2012-08-20 09:44 | 2012-08-20 09:44 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2012 | Q3 | Q3 - 2012 | 7850 | 6629 | FALSE | 100 | Actual will be 115% due to higher engineering cost. Remaining costs are being covered by private funds. | 0 | NA | NA | 100 | In line with baseline | 100 | In line with baseline | 96 | Slightly behind baseline of 100. | 92 | Ahead of baseline of 96 | 0 | NA | 84 | Baseline is 100. We will still have some equipment to purchase, but the main reason for the lower figure is being able to acquire equipment below budgeted costs. | 95 | Actual will be 111% due to higher engineering cost. Overruns are being covered by private funds. | 82 | Slightly ahead of baseline of 85 | 73 | In line with baseline | 2012-11-13 17:02 | 2012-11-13 17:02 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2012 | Q4 | Q4 - 2012 | 8720 | 7522 | FALSE | 100 | Actual is over 100% due to running over budget. Remaining costs will be covered by private funds. | 0 | NA | NA | 100 | In line with baseline | 100 | In line with baseline | 96 | Actual will be at 100%. Additional amount covered by private funds | 92 | Actual is over 100% due to running over budget. Remaining costs will be covered by private funds. | 0 | NA | 84 | Actual will be around 90%. Lower costs than expected | 95 | Actual is over 100% due to running over budget. Remaining costs will be covered by private funds. | 82 | Will be completed and additional costs covered by private funds | 73 | Will be completed and additional costs covered by private funds | 2013-02-12 10:13 | 2013-02-12 10:13 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2013 | Q1 | Q1 - 2013 | 9962 | 8525 | FALSE | 100 | Actual spend is 127% of original budget due to cost overruns in engineering. | 0 | NA | NA | 100 | Actual spend is 143% due to much higher engineering costs required to complete EA. | 100 | Actual spend is 272% due to much higher engineering costs required to complete the network design. | 0 | NA | 100 | Actual spend is 243% due to much higher costs of railroad and various permits than originally budgeted for. | 0 | NA | 86 | Actual spend is 86% due to lower costs of equipment than originally budgeted. | 100 | Actual spend is 139% as we continue to complete our build. | 0 | NA. Costs were included in Network Build. | 0 | NA. Costs were included in Network Build. | 2013-05-29 14:17 | 2013-05-29 14:17 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2013 | Q2 | Q2 - 2013 | 10760 | 9045 | FALSE | 100 | Actual spend is 127% of original budget due to cost overruns in engineering. | 0 | NA | NA | 100 | Actual Spend is 143% due to much higher engineering costs required to complete EA. | 100 | Actual spend is 272% due to much higher engineering costs required to complete the network design. | 0 | NA | 100 | Actual spend is 243% due to much higher costs of railroad and various permits than originally budgeted | 0 | NA | 86 | Lower costs of equipment than originally budgeted. | 100 | Actual spend is 138% due to higher construction costs than expected. | 0 | NA. Costs were included in Network Build | 0 | NA. Costs were included in Network Build | 2013-08-27 11:48 | 2013-08-27 11:48 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | 2013 | Q3 | Q3 - 2013 | 11858 | 10028 | FALSE | 100 | Actual spend is 121% of original budget due to higher costs in engineering and permitting. | 0 | NA | NA | 100 | Actual spend is 143% due to much higher engineering costs required to complete EA. | 100 | Actual spend is 272% due to much higher engineering costs required to complete the network design. | 0 | NA | 100 | Actual spend is 243% due to much higher costs of railroad and various permits than originally budgeted. | 0 | NA | 100 | Actual spend was 86% due to lower costs of equipment than originally budgeted | 100 | Actual spend is 129% due to higher construction costs than budgeted. | 0 | NA. Costs were included in Network Build. | 0 | NA. Costs were included in Network Build. | 2014-02-21 09:24 | 2014-02-21 09:24 | 6055 | 6055 | Delta Communications, L.L.C. | TRUE
NT10BIX5570101 | 2010 | Q4 | Q4 - 2010 | 976 | 2021 | FALSE | 17 | No variance | 19 | Admin, legal | No variance | 100 | No variance | 40 | Original goal was to complete 81% of network design by the end of March 2011. This may be delayed due to delay in completion of EA. Route refinement for EA purposes must be completed before engineering surveys can commence for those areas. We expect to make up this time and complete 100% by the end of June 2011 as planned. | 44 | No variance | 20 | No variance | 0 | No variance | 88 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 2011-02-04 14:28 | 2011-02-04 14:28 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2011 | Q1 | Q1 - 2011 | 2176 | 2833 | FALSE | 21 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 8%. | 32 | Admin & Legal | No variance is expected. | 100 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 30%. | 100 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 25%. | 100 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 0%. | 48 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 0%. | 0 | N/A | 100 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 1%. | 28 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 4%. | 87 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 0%. | 28 | Our planned percent complete (baseline) goal was based on task completion instead of spend. We are restating our forecast for this quarter (based on forecasted spend) at 0%. | 2011-05-19 14:43 | 2011-05-19 14:43 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2011 | Q2 | Q2 - 2011 | 3010 | 3262 | FALSE | 40 | Our baseline % complete for this quarter was 44%. Reasons for this variance are cumulative per the below. | 39 | Admin & Legal | Our baseline % complete for this quarter was 43%. We have been slightly under budget for far for costs in this category, which accounts for the small variance. | 76 | Our baseline % complete for this quarter was 100%. We have struggled to completed our EA, but it has now been submitted and is under review by NTIA. | 72 | Our baseline % complete for this quarter was 100%. We went through extensive route refinement and had all route changes approved this quarter. This caused some delays with our engineering efforts, but we expect to fully recover in the next quarter. | 62 | Our baseline % complete for this quarter was 100%. This is a relatively small portion of our overall budget. While we have not completed 100% of our right of way attainment, our franchise and other processes are proceeding well and we expect to fully recover in the next quarter. We have also been under budget on this item so far, and this does/will affect our attainment percentage (which is based on % of spend). | 18 | Our baseline % complete for this quarter was 77%. This is a relatively small portion of our overall budget. While we have not completed 77% of our right of way attainment, our permitting process is proceeding well and we expect to fully recover in the next quarter. We have also been under budget on this item so far, and this does/will affect our attainment percentage (which is based on % of spend). | 0 | Our baseline % complete for this quarter was 0%. | 45 | Our baseline % complete for this quarter was 100%. This is a relatively small portion of our overall budget. The baseline report was prepared comtemplating all equipment would be paid in full once procured, however, certain equipment will not be paid in full until construction commences. | 35 | Our baseline % complete for this quarter was 38%. This category dominates our overall budget ($20M of the total budget). We have only a small variance in this category, and we expect to be able to fully recover next quarter as we receive our FONSI and construction begins. | 0 | Our baseline % complete for this quarter was 87%. We have $0 allocated to this category and therefore we have no variance. | 0 | Our baseline % complete for this quarter was 38%. We have $0 allocated to this category and therefore we have no variance. | 2011-08-11 10:56 | 2011-08-11 10:56 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2011 | Q3 | Q3 - 2011 | 3922 | 3799 | FALSE | 49 | Our baseline goal was to be 55%. Our overall project was delayed due to our EA. | 48 |  | Our baseline goal was to be 55%. The small variance is due mainly to our general liability insurance costs being lower than expected due to the delay in starting construction. | 78 | Our baseline goal was to be 100%. We completed our environmental assessment under budget. We expect no more costs to be incurred in this category unless issues related to our SAC come up. | 69 | Our baseline goal was to be 100%. Our costs to date have been lower than expected, however we expect additional costs to be incurred as our engineering is completed. | 21 | Our baseline goal was to be 100%. Costs for this category have been lower than expected to date. $548k of the $878k in this category was for joint use (pole attachment) fees. The constraints on setting new poles imposed in our EA SAC has discouraged the use of poles altogether. | 54 | Our baseline goal was to be 100%. Costs have been lower than expected to date, however we expect these costs to increase as we move forward with more expensive permits like our railroad crossings. | 0 | N/A. No costs were allocated for this category. | 71 | Our baseline goal was to be 100%. This is a relatively small portion of our overall budget. These costs are occurring later than expected due to the delay in the start of our construction. | 48 | Our baseline goal was to be 47%. No variance is expected. | 0 | Even though we had $0 allocated to this category in our detailed budget, we still recorded projections for % complete for each quarter in our original baseline. In hindsight, it would have been more appropriate to record 0% or N/A in our baseline projections. At this point, we project $0.00 spend on this category for next quarter, and since our original projection was to spend $0.00, we feel it is appropriate to record that we expect to have "no variance." Alternatively, we could record our % complete each quarter to be the same as our baseline projections, but this would be "X% complete of $0.00." | 0 | Even though we had $0 allocated to this category in our detailed budget, we still recorded projections for % complete for each quarter in our original baseline. In hindsight, it would have been more appropriate to record 0% or N/A in our baseline projections. At this point, we project $0.00 spend on this category for next quarter, and since our original projection was to spend $0.00, we feel it is appropriate to record that we expect to have "no variance." Alternatively, we could record our % complete each quarter to be the same as our baseline projections, but this would be "X% complete of $0.00." | 2011-11-08 13:36 | 2011-11-08 13:36 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2011 | Q4 | Q4 - 2011 | 4874 | 4569 | FALSE | 57 | Original baseline goal was 62%. Delayed fiber availability and lower than expected costs in some categories are primary reasons for expected variance. | 57 |  | Original baseline goal was 68%. Continued lower than expected admin, legal and other professional services costs is primary reason for expected variance. | 78 | Original baseline goal was 100%. The work related to our EA is essentially complete, but since we ended up under budget from what we original projected to spend on this milestone, we will show a "variance" for the remainder of the program. | 69 | Original baseline goal was 100%. Continued lower than expected costs from NW Georgia Regional Commission is the primary reason for expected variance. | 1 | Original baseline goal was 100%. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 25 | Original baseline goal was 100%. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. | 87 | Original baseline goal was 100%. Continued lower than expected equipment costs are primary reason for expected variance. | 58 | Original baseline goal was 58%. No variance projected. | 0 | We had no costs allocated in our budget specifically for this baseline category. | 0 | We had no costs allocated in our budget specifically for this baseline category. | 2012-02-05 19:06 | 2012-02-05 19:06 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2012 | Q1 | Q1 - 2012 | 6298 | 5751 | FALSE | 69 | Original baseline goal was to be 75% complete. Delayed fiber availability and lower than expected costs in some categories are the primary reasons for the expected variance. | 61 |  | Original baseline goal was to be 88% complete. Continued lower than expected admin, legal and other professional services costs is primary reason for expected variance. | 81 | Original baseline goal was to be 100% complete. We expect to be under budget for this category, however due to current activities to conduct cultural and archeological monitoring under our FONSI and SAC obligations, we expect additional spend between now and the end of the program. | 70 | Original baseline goal was to be 100% complete. Lower than expected costs from NW Georgia Regional Commission is the primary reason for the expected variance. | 1 | Original baseline goal was to be 100% complete. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 29 | Original baseline goal was to be 100% complete. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance | 100 | Original baseline goal was to be 100% complete. No variance. | 71 | Original baseline goal was to be 79% complete. Delayed fiber delivery has been the primary reason for the small variance in this category. We expect to catch up in this category before the end of the program. | 0 | Original baseline goal was to be 90% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance. | 0 | Original baseline goal was to be 79% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance. | 2012-05-25 11:38 | 2012-05-25 11:38 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2012 | Q2 | Q2 - 2012 | 6872 | 6062 | FALSE | 81 | No variance expected. | 65 |  | Original baseline goal was to be 88% complete. Continued lower than expected admin, legal and other professional services costs is primary reason for expected variance. | 82 | Original baseline goal was to be 100% complete. We expect to be under budget for this category, however due to current activities to conduct cultural and archeological monitoring under our FONSI and SAC obligations, we expect additional spend between now and the end of the program. | 83 | Original baseline goal was to be 100% complete. Lower than expected costs from NW Georgia Regional Commission is the primary reason for the expected variance. | 0 | Original baseline goal was to be 100% complete. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 32 | Original baseline goal was to be 100% complete. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance | 97 | No variance expected. | 85 | No variance. | 0 | Original baseline goal was to be 90% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance. | 0 | Original baseline goal was to be 79% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance. | 2012-08-06 15:58 | 2012-08-06 15:58 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2012 | Q3 | Q3 - 2012 | 8050 | 6731 | FALSE | 86 | No variance expected. | 74 |  | Original baseline goal was to be 90% complete. Continued lower than expected admin, legal and other professional services costs is primary reason for expected variance. | 82 | Original baseline goal was to be 100% complete. We expect to be under budget for this category, however due to current activities to conduct cultural and archeological monitoring under our FONSI and SAC obligations, we expect additional spend between now and the end of the program. | 88 | Original baseline goal was to be 100% complete. Lower than expected costs from NW Georgia Regional Commission is the primary reason for the expected variance. | 0 | Original baseline goal was to be 100% complete. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 56 | Original baseline goal was to be 100% complete. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance expected. | 97 | No variance expected. | 89 | No variance expected. | 0 | Original baseline goal was to be 92% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance expected. | 0 | Original baseline goal was to be 79% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance expected. | 2012-11-26 16:37 | 2012-11-26 16:37 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2012 | Q4 | Q4 - 2012 | 9124 | 7899 | FALSE | 90 | Original baseline goal was to be 94% complete. Delayed permitting in Alabama is the primary reason for the expected variance. | 80 |  | Original baseline goal was to be 100% complete. Continued lower than expected admin, legal and other professional services costs is primary reason for expected variance. | 80 | Original baseline goal was to be 100% complete. We expect to be under budget for this category, however due to current activities to conduct cultural and archeological monitoring under our FONSI and SAC obligations, we expect additional spend between now and the end of the program. | 92 | Original baseline goal was to be 100% complete. Lower than expected costs from NW Georgia Regional Commission is the primary reason for the expected variance. | 0 | Original baseline goal was to be 100% complete. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 68 | Original baseline goal was to be 100% complete. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance expected. | 97 | No variance expected. | 93 | No variance expected. | 0 | Original baseline goal was to be 97% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance expected. | 0 | Original baseline goal was to be 96% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance expected. | 2013-03-04 17:30 | 2013-03-04 17:30 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2013 | Q1 | Q1 - 2013 | 9710 | 8388 | FALSE | 95 | Original baseline goal was to be 100% complete. Delayed start of Alabama construction is the primary reason for the expected variance. | 87 |  | Original baseline goal was to be 100% complete. Continued lower than expected admin, legal and other professional services costs is primary reason for expected variance. Back-loaded legal costs for competion of UCC filings are also a reason. | 83 | Original baseline goal was to be 100% complete. We expect to be under budget for this category, however due to current activities to do the route modification for our 7 CAIs, we expect additional spend between now and the end of the program. | 94 | Original baseline goal was to be 100% complete. Lower than expected costs from NW Georgia Regional Commission is the primary reason for the expected variance. | 0 | Original baseline goal was to be 100% complete. Continued lower than expected costs for right of way perfection and joint use (pole) fees are the primary reasons for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 70 | Original baseline goal was to be 100% complete. Continued lower than expected railroad permit costs is primary reason for expected variance. Despite the large % variance, this is a very small part of our overall project/budget. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance expected. | 98 | Original baseline goal was to be 100% complete. | 98 | Original baseline goal was to be 100% complete. | 0 | Original baseline goal was to be 100% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance expected. | 0 | Original baseline goal was to be 100% complete, however, we had no costs allocated in our budget specifically for this baseline category. No variance expected. | 2013-05-13 17:04 | 2013-05-13 17:04 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2013 | Q2 | Q2 - 2013 | 10696 | 9010 | FALSE | 99 | Funds unspent at end of this quarter will be used for eligible close-out costs. | 83 |  | Funds unspent in this category at end of this quarter will be used for eligible close-out costs. | 100 | No variance expected. | 100 | No variance expected. | 0 | No variance expected. | 100 | No variance expected. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance expected. | 98 | Funds unspent in this category at end of this quarter will be used for eligible close-out costs. | 100 | No variance expected. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance expected. | 0 | We had no costs allocated in our budget specifically for this baseline category. No variance expected. | 2013-08-22 14:51 | 2013-08-22 14:51 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | 2013 | Q3 | Q3 - 2013 | 11254 | 9417 | FALSE | 100 | Not applicable. Project was completed this quarter. | 100 |  | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 100 | Not applicable. Project was completed this quarter. | 2013-11-14 16:07 | 2013-11-14 16:07 | 6397 | 6397 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570102 | 2010 | Q4 | Q4 - 2010 | 626 | 1651 | FALSE | 7 | --- | 3 |  | --- | 100 | --- | 75 | --- | 0 | --- | 0 | --- | 0 | N/A | 4 | --- | 8 | --- | 10 | --- | 0 | --- | 2011-01-27 16:56 | 2011-01-27 16:56 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2011 | Q1 | Q1 - 2011 | 2286 | 2888 | FALSE | 6 | The Environmental Assessment and subsequent FONSI were expected to be completed by the beginning of this year and deployment was expected to be well underway by this quarter. However, we now expect the FONSI to be issued by the end of the quarter, which will allow the project to move into its implementation phase, in which BTOP funding and match are largely concentrated. | 4 |  | The Baseline Report assumed the FONSI would have been issued in the first quarter of 2011, which would have allowed for huts to be purchased and installed at fiber sites. Fiber hut purchase and installation can commence following the issuance of the FONSI. The 4% completion reported here comprises the payment of salaries and indirect costs. | 84 | The Baseline Report assumed all EA work would be completed once the FONSI was issued; however, the project will now continue to purchase the services of our EA Consultant for on-going site evaluations throughout the implementation of the project, thus reserving a percentage of this category's completion to be distributed over the remaining quarters. | 100 | --- | 0 | N/A | 50 | --- | 0 | N/A | 0 | The Baseline Report assumed the FONSI would have been issued in the first quarter of 2011, which would have allowed the purchase of infrastructure and some telemedicine equipment during the second quarter of 2011. However, since the final EA will be submitted this quarter and consequently no FONSI has been issued to date, equipment will not be procured. The project has elected to minimize the time equipment is "warehoused" while the EA is still under review, as equipment warranties would be active during the warehouse time when this equipment is not being tested or employed. An Equipment RFP, however, is expected to issue this quarter, which will ready the project to purchase and deploy equipment quickly following the issuance of a FONSI. | 8 | The Baseline Report assumed the FONSI would have been issued in the first quarter of 2011. However, without this expected development, the project will not have the opportunity to install circuits, as planned. The 8% completion reported here comprises the payment of IRU agreements. | 9 | Equipment Deployment to-date largely comprises in-kind match items that are contributed proportionally to the federal funds drawn down for the project. The Baseline Report assumed more federal funds would be drawn down in this quarter; however, for the reasons described in the other sections of this report, fewer funds will be drawn down than projected in the Baseline Report. As such, the "equipment deployment" match reflects the proportional decrease in the federal draw down. | 0 | The Baseline Report assumed the FONSI would have been issued in the first quarter of 2011, which would have allowed for equipment to be purchased and deployed, thus allowing for appropriate network testing. Therefore, network testing can commence following the issuance of the FONSI, at which time equipment can be purchased and deployed. | 2011-05-24 17:32 | 2011-05-24 17:32 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2011 | Q2 | Q2 - 2011 | 2604 | 3050 | FALSE | 20 | --- | 8 | Indirect costs, huts, easements, project management costs | --- | 86 | --- | 100 | --- | 0 | --- | 100 | --- | 0 | N/A | 25 | --- | 18 | --- | 28 | --- | 82 | --- | 2011-07-28 14:51 | 2011-07-28 14:51 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2011 | Q3 | Q3 - 2011 | 4036 | 3858 | FALSE | 29 | --- | 12 | - | --- | 89 | --- | 100 | --- | 0 | N/A | 9 | The Revised Baseline Report assumed that permits would be at 100% by Year 2 Quarter 1. However, fewer miles of fiber are being constructed; therefore, there are fewer railroad crossings and, thus, fewer required permits. However, other permit fees may be incurred in coming quarters for fiber construction. We anticipate permits to be approximately $10,000 per quarter for the remainder of the grant. Budgeted permits amount to $96,000. | 0 | N/A | 37 | --- | 27 | --- | 41 | --- | 82 | --- | 2011-11-14 15:47 | 2011-11-14 15:47 | 6618 | 6618 | University of Arkansas System | TRUE
NT10BIX5570102 | 2011 | Q4 | Q4 - 2011 | 5026 | 4697 | FALSE | 48 | --- | 21 |  | --- | 92 | --- | 100 | --- | 0 | N/A | 9 | The Revised Baseline Report assumed that permits would be at 100% by Year 2 Quarter 2. However, fewer miles of fiber are being constructed; therefore, there are fewer railroad crossings and, thus, fewer required permits. However, other permit fees may be incurred in coming quarters for fiber construction. We anticipate permits to be approximately $10,000 per quarter for the remainder of the grant. Budgeted permits amount to $96,000. However, no permits were acquired this quarter and we do not anticipate any future acquisitions by our sub-recipient. We anticipate an 81% variance throughout the end of the project. | 0 | N/A | 56 | --- | 47 | --- | 69 | --- | 82 | --- | 2012-02-15 11:00 | 2012-02-15 11:00 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2012 | Q1 | Q1 - 2012 | 6052 | 5625 | FALSE | 72 | --- | 40 | Indirects, huts, easements, project management costs | --- | 100 | No additional charges are anticipated for Environmental Assessment resulting in a +5% variance against the revised Baseline projections. | 100 | --- | 0 | N/A | 9 | --- | 100 | Site preparation for ARE-ON huts are projected to be completed in the next quarter. | 94 | --- | 67 | --- | 93 | --- | 82 | --- | 2012-05-14 09:45 | 2012-05-14 09:45 | 6618 | 6618 | University of Arkansas System | TRUE
NT10BIX5570102 | 2012 | Q2 | Q2 - 2012 | 7210 | 6232 | FALSE | 87 | We have successfully managed the project and have over-achieved. We expect this to continue resulting in a +3 variance for planned completion by Q3 2012. | 71 | Indirects, huts, easements, project management costs | Fiber hut placement has progressed faster than projected resulting in variance of +7%. | 100 | No additional charges are anticipated for Environmental Assessment resulting in a +3% variance against the revised Baseline projections. | 100 | --- | 0 | N/A | 9 | The Revised Baseline Report assumed that permits would be at 100% by Q3 2012. Because of the use of IRUs there is a lesser need for railroad crossings and, thus, fewer required permits. We anticipate a -91% variance throughout the end of the project. | 0 | N/A | 97 | --- | 81 | --- | 94 | --- | 66 | We anticipate the optical network to be completed over the next two quarters. Therefore, since network testing cannot occur until completion of the optical network itself, testing will fall short of the revised Baseline figure resulting in a variance of -34% for Q3 2012. | 2012-08-22 13:30 | 2012-08-22 13:30 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2012 | Q3 | Q3 - 2012 | 7988 | 6700 | FALSE | 84 | As instructed by the FPO, the projections were calculated using the Revised PIP of October 2012 resulting from the stop-work order. | 71 | Indirects, huts, easements, project management costs | --- | 100 | The Environmental Assessment was completed in June 2011. No additional costs were anticipated. However, as a result of the CAP, we were directed to enter into new consultations with the State Historic Preservation Office (SHPO). | 100 | --- | 0 | N/A | 100 | --- | 0 | N/A | 92 | --- | 81 | --- | 93 | --- | 100 | --- | 2012-11-20 16:35 | 2012-11-20 16:35 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2012 | Q4 | Q4 - 2012 | 8810 | 7603 | FALSE | 94 | As instructed by the FPO, the projections were calculated using the Revised PIP of October 2012 resulting from the stop-work order. | 89 | Indirects, huts, easements, project management costs | --- | 100 | --- | 100 | --- | 0 | N/A | 100 | --- | 0 | N/A | 98 | --- | 92 | --- | 97 | --- | 100 | --- | 2013-02-15 16:00 | 2013-02-15 16:00 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2013 | Q1 | Q1 - 2013 | 9396 | 8189 | FALSE | 94 | As instructed by the FPO, these projections are calculated using the Revised PIP of October 2012 resulting from the Corrective Action Plan (CAP) changes and resulting project delays. a. The CAP affected budget and expenditure timing for the sub-recipient, necessitating a project time extension ending September 30, 2013 instead of July 31, 2013 was approved by FPO. b. The project time extension also required CAP delayed budget expenditures to be shifted within budget categories to compensate for CAP timing delays. NTIA gave guidance for this budget modification. In compliance with NTIA guidelines, the budget shifts do not exceed 10% variance guidelines, and there is no change in scope of work for Q1 2013. FPO approval for budget shifts received in March 2013. c. The PPR quarterly projections use 12 fiscal quarters, however, the CAP and weather-related delays affected project time-lines and budget expenditures by one (1) quarter. To adjust | 82 | Indirects, huts, easements, project management costs | --- | 100 | --- | 99 | --- | 0 | N/A | 83 | --- | 0 | N/A | 99 | --- | 96 | --- | 97 | --- | 79 | --- | 2013-04-29 18:03 | 2013-04-29 18:03 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2013 | Q2 | Q2 - 2013 | 10612 | 8964 | FALSE | 100 | --- | 100 | Indirects, huts, easements, project management costs | --- | 100 | --- | 100 | --- | 0 | N/A | 100 | --- | 0 | N/A | 100 | --- | 100 | --- | 100 | --- | 100 | --- | 2013-08-15 14:10 | 2013-08-15 14:10 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570102 | 2013 | Q3 | Q3 - 2013 | 11520 | 9647 | FALSE | 0 | N/A | 0 |  | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2013-12-23 09:51 | 2013-12-23 09:51 | 6617 | 6617 | University of Arkansas System | TRUE
NT10BIX5570103 | 2010 | Q4 | Q4 - 2010 | 1228 | 2257 | FALSE | 10 | No variance from Baseline Plan. | 0 | Network Management/Operations | No variance from Baseline Plan. | 50 | Progress pending Final FONSI appoval. | 30 | Progress pending Final EA approval. | 0 | Progress pending Final network/route designs. | 0 | Progress pending Final network/route designs. | 0 | Progress pending Final network/route designs. | 0 | Progress pending Final network/route designs. | 0 | Progress pending Final network/route designs. | 0 | Progress pending Final network/route designs. | 0 | No variance from Baseline Plan. | 2011-02-18 15:54 | 2011-02-18 15:54 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2011 | Q1 | Q1 - 2011 | 2392 | 2941 | FALSE | 10 | Progress limited by project route design timeline and final FONSI approval. | 0 | Network Management/Operations | No variance from Baseline Plan. | 100 | No variance from Baseline Plan. | 100 | No variance from Baseline Plan. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | No variance from Baseline Plan. | 2011-05-27 15:47 | 2011-05-27 15:47 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2011 | Q2 | Q2 - 2011 | 2936 | 3225 | FALSE | 11 | Progress limited by project route design timeline and final FONSI approval. | 0 | Network Management/Operations | No variance from Baseline Plan. | 100 | No variance from Baseline Plan. | 100 | No variance from Baseline Plan. | 15 | Progress limited by project route design timeline and final FONSI approval. | 5 | Progress limited by project route design timeline and final FONSI approval. | 2 | Progress limited by project route design timeline and final FONSI approval. | 2 | Progress limited by project route design timeline and final FONSI approval. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | Progress limited by project route design timeline and final FONSI approval. | 0 | No variance from Baseline Plan. | 2011-08-05 14:50 | 2011-08-05 14:50 | 6961 | 6961 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2011 | Q3 | Q3 - 2011 | 4124 | 3905 | FALSE | 21 | Progress limited by delays in FONSI approval. | 0 | Network Management/Operations | Progress limited by delays in FONSI approval. | 100 | No variance from Baseline Plan. | 100 | No variance from Baseline Plan. | 10 | Progress limited by delays in FONSI approval. | 10 | Progress limited by delays in FONSI approval. | 0 | Progress limited by delays in FONSI approval. | 50 | Procurement schedules accelerated to offset any potential delays associated with supplier inventory. | 0 | Progress limited by delays in FONSI approval. | 0 | Progress limited by delays in FONSI approval. | 0 | Progress limited by delays in FONSI approval. | 2011-11-17 18:46 | 2011-11-17 18:46 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2011 | Q4 | Q4 - 2011 | 5352 | 5023 | FALSE | 35 | Progress delayed by extended EA and FONSI approval process | 0 | true | N/A | 100 | No variance from Baseline Plan | 100 | No variance from Baseline Plan | 30 | Progress delayed by extended EA and FONSI approval process | 30 | Progress delayed by extended EA and FONSI approval process | 0 | Progress delayed by extended EA and FONSI approval process | 100 | Progress expedited to exceed Baseline Plan projections | 35 | Progress delayed by extended EA and FONSI approval process | 35 | Progress delayed by extended EA and FONSI approval process | 35 | Progress delayed by extended EA and FONSI approval process | 2012-02-28 14:20 | 2012-02-28 14:28 | 7311 | 7311 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2012 | Q1 | Q1 - 2012 | 6168 | 5686 | FALSE | 43 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 0 |  | N/A | 100 | No variance from Baseline Plan. | 100 | No variance from Baseline Plan. | 60 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 60 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 55 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 100 | Accelerated to meet project build time line. | 0 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 0 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 0 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 2012-05-17 19:07 | 2012-05-17 19:07 | 7311 | 7311 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2012 | Q2 | Q2 - 2012 | 7084 | 6169 | FALSE | 44 | Progress pending execution of agreements, specifically with utility providers, and completion of fiber delivery. | 0 |  | N/A | 100 | No variance from baseline plan. | 100 | No variance from baseline plan. | 60 | Progress pending approval of Rights of Way from Bureau of Land Management, various Tribal entities, and acceptance of attachment applications. | 60 | New requirements, such as stationing on drawing and traffic control plans, needed from contractors doing work. Also, ongoing negotiations with landowners, some of which are out of state and slow to respond. | 55 | Pending approval of engineering re-design (route modifications) due to a utility not allowing use of substations for shelter placement. | 80 | Time frame of procurement modified to ensure the extension of equipment warranty period during actual deployment. | 1 | Progress pending execution of agreements, specifically with utility providers, and fiber delivery in 3Q12. | 25 | Pending granting of access to member hospitals, as well as installation of shelters at sites near substations. | 10 | Network testing not feasible until network has been deployed and activated. | 2012-08-15 15:33 | 2012-08-15 15:33 | 7311 | 7311 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2012 | Q3 | Q3 - 2012 | 8026 | 6719 | FALSE | 46 | Projected progress meaningfully altered due to previous delay in fiber delivery, as well as agreement with utility providers. However, fiber delivery anticipated to be complete in 4Q12. Right-of-Way agreements with Tribal entities and approval of design modifications also anticipated to be received in 4Q12. | 0 |  | N/A | 100 | No variance from baseline plan. | 100 | No variance from baseline plan. | 60 | Progress pending approval of Rights-of-Way from Bureau of Land Management, various Tribal entities, and acceptance of attachment applications. | 40 | Progress pending ongoing negotiations with landowners, some of which are out of State and slow to respond. | 20 | Progress pending approval of engineering redesigned (route modifications). | 90 | Timeframe of procurement modified to ensure the extension of equipment warranty period through project deployment. | 10 | Projected progress meaningfully altered due to previous delay in fiber delivery, as well as agreement with utility providers. However, fiber delivery anticipated to be complete in 4Q12. Right-of-Way agreements with Tribal entities and approval of design modifications also anticipated to be received in 4Q12. | 15 | Progress pending granting of access to member hospitals, as well as installation of shelters at sites near substations. | 10 | Projected progress meaningfully altered due to delay in network deployment in previous quarter. | 2012-11-23 17:15 | 2012-11-23 17:15 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2012 | Q4 | Q4 - 2012 | 8824 | 7610 | FALSE | 63 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, the approval of route modifications is anticipated in 1Q13 and approval of pending ROW applications are expected to be received. It is also expected that utility providers will approve pending permits. | 0 |  | N/A | 100 | No variance from baseline plan | 100 | No variance from baseline plan | 75 | Progress pending approval of Rights-of-Way from US Forest Service, Bureau of Land Management, Bureau of Reclamation and various Tribal entities. | 70 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | 30 | Progress pending approval of engineering redesigned (route modifications). | 90 | Time frame of procurement modified to ensure the extension of equipment warranty period through project deployment. | 40 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, the approval of route modifications and ROW applications are anticipated in 1Q13. Pending permits from the utility providers are also expected to be released. | 15 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, the approval of route modifications and ROW applications are anticipated in 1Q13. Pending permits from the utility providers are also expected to be released. | 30 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, A delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, it is anticipated that Reno-Silver Springs will be tested in the next quarter. | 2013-02-15 16:50 | 2013-02-15 16:50 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2013 | Q1 | Q1 - 2013 | 9930 | 8508 | FALSE | 60 | Projected progress meaningfully altered due to a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, the approval of route modifications is anticipated in 2Q13 and approval of pending ROW applications are expected to be received. | 0 |  | N/A | 100 | No variance from baseline plan | 100 | No variance from baseline plan | 100 | No variance from baseline plan | 100 | No variance from baseline plan | 30 | Progress pending approval of engineering redesigned (route modifications). | 90 | Time frame of procurement modified to ensure the extension of equipment warranty period through project deployment. | 20 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, the approval of route modifications, ROW applications and easements are anticipated in 2Q13. | 12 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, the approval of route modifications, ROW applications and easements are anticipated in 2Q13. | 30 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, A delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, it is anticipated that Reno-Silver Springs will be tested in the next quarter. | 2013-05-28 13:50 | 2013-05-28 13:50 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2013 | Q2 | Q2 - 2013 | 10644 | 8982 | FALSE | 53 | Project progress meaningfully altered due to a delay on the approval of final agreements with Federal agencies and Tribal entities related to ROW significantly affected the network project time line. However, the approval of route modifications is anticipated in 3Q13 and approval of pending ROW applications are expected to be received. | 0 |  | N/A | 100 | Project extension will allow completion of redesigned network route. | 100 | Projected extension will allow completion of redesigned network route. | 100 | Project extension and funding will allow time for negotiations and completion of ROW applications. | 100 | Project extension and funding will allow time for acquiring all permits and approvals for redesigned network route. | 30 | Progress pending approval of engineering redesign (route modifications). | 90 | Time frame of procruement modified to ensure the extension of equipment warranty period through project deployment. | 20 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with Federal agencies and Tribal entitiesrelated to ROW significantly affected the network project time line. However, the approval of route modifications, ROW applications and easements are anticipated in 3Q13. | 12 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. However, the approval of route modifications, ROW applications and easements are anticipated in 3Q13. | 30 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, A delay on the approval of final agreements with Federal agencies and Tribal entities related to ROW significantly affected the network project time line. However, it is anticipated that Reno-Silver Springs will be tested in the next quarter. | 2013-08-19 19:06 | 2013-08-19 19:06 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2013 | Q3 | Q3 - 2013 | 11244 | 9412 | FALSE | 48 | Upon federal approval we anticipate submission of an in-kind match to rectify grant match ratio; and reimbursement of basic charges to sustain project activity including ROW and construction permit completion | 0 |  | N/A | 100 | Project extension will allow completion of EA | 100 | Project extension will allow completion of redesigned network route | 98 | Due to the additional interruption into project advancement all rights of way are not anticipated until end of January 2014, if project reengages by early November | 100 | Re-engaging utilities and federal/state/tribal agencies to finalize permits in order to begin construction Q1 2014 | 30 | Anticipate further advancement of site prep work towards the end of Q1 2014 | 90 | Will order long lead items to be delivered shortly before construction | 14 | No activity expected based on project and funding hold. If re-engaged in early November, we can anticipate building in Q1 2014. | 8 | No activity expected based on project and funding hold. If re-engaged in early November, we can anticipate further deployment in late Q1 2014. | 20 | No activity expected based on project and funding hold. | 2013-11-13 18:03 | 2013-11-13 18:03 | 6121 | 6121 | Nevada Hospital Association | TRUE
NT10BIX5570103 | 2013 | Q4 | Q4 - 2013 | 11830 | 10006 | FALSE | 48 | Upon federal approval we anticipate submission of invoices for work completed ; and reimbursement of basic charges to sustain project activity including ROW and construction permit completion. The budget reflects anticipated payment of past due invoices, including fiber, next quarter. | 0 |  | N/A | 100 | CAP approval will allow completion of EA. | 100 | CAP approval will allow completion of redesigned network route. | 98 | Pending CAP approval project advancement on all rights of way are not anticipated until end of May 2014. | 100 | RE-engaging utilities and federal/state/tribal agencies to finalize permits in order to begin construction Q2 2014. | 30 | Anticipate further advancement of site prep work towards the end of Q2 2014. | 90 | Will order long lead items to be delivered shortly before construction. | 14 | No activity expected pending approval of CAP. | 8 | No activity expected until CAP approved. | 20 | No activity pending CAP approval | 2014-02-14 19:27 | 2014-02-14 19:27 | 7786 | 7786 | Nevada Hospital Association | TRUE
NT10BIX5570104 | 2010 | Q4 | Q4 - 2010 | 994 | 2036 | FALSE | 3 | Unforeseen variables arose during the last quarter due to additional needs surrounding the Environmental Assessment. Therefore spending of funds was delayed in the last quarter thus affecting this quarter as well. | 0 |  | No Variance | 100 | No Variance from Baseline | 90 | Unforeseen variables arose during the last quarter due to additional needs surrounding the Environmental Assessment. Resources that would have been used to design the network had to be pulled and used for Environmental Assessment needs which affected network design last quarter and again in this quarter. | 25 | After discussions with several of the entities involved in Rights Of Way, Contact Network Inc. now sees that Rights of Way need to be submitted on a county/service area basis. Therefore our percent complete as reported in the baseline will not be accurate based on how the Rights Of Way are currently being processed. | 25 | Environmental Assessment submitted during this quarter and Finding Of No Significant Impact is anticipated to be received, however there was a delay in receipt of the response from the Mississippi State Historic Preservation Officer that we anticipate will delay the receipt of Finding Of No Significant Impact. As per the Environmental Assessment Special Awards Condition only allowable funds will be spent prior to receipt of Finding Of No Significant Impact causing the variance from the baseline report. | 15 | No Variance from baseline | 20 | No Variance from baseline | 1 | When Finding Of No Significant Impact is received we intend to purchase fiber. This expenditure represents the first fiber purchase assuming receipt of Finding Of No Significant Impact. | 0 | No Variance | 0 | No Variance | 2011-02-07 13:04 | 2011-02-07 13:04 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2011 | Q1 | Q1 - 2011 | 2104 | 2797 | FALSE | 15 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 0 |  | No variance from baseline | 100 | No Variance from baseline | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs are held with various utilities and permits are negotiated with various entities the network design may need to be updated/changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 37 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 20 | Since the baseline report was submitted it has become evident to Contact Network Inc. the equipment procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Due to delays in issuing the Equipment request for proposal we are behind in procurement. We will be placing equipment orders this quarter to somewhat catch up in this category versus our initial baseline projections. | 15 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services to be delivered as of July 1, 2011. Our primary focus for design, engineering, permitting etc. was on the counties where these districts are located due to the strict time lines to deliver services on July 1, 2011. We now have a new tool to use to help us pinpoint our total dollars spent on this category. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 2011-05-17 17:46 | 2011-05-17 17:46 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2011 | Q2 | Q2 - 2011 | 2928 | 3221 | FALSE | 27 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. |  |  |  | 100 | No Variance from Baseline | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 37 | During this quarter an additional ten Community Anchor Institutions will be connected to our network. This brings the total to forty seven anchor institutions which exceeds our baseline projections. | 20 | Equipment is being purchased on an as needed basis. We expect significant purchases to be made during the next quarter. | 28 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 37 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 16 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 2011-08-04 17:12 | 2011-08-04 17:12 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2011 | Q3 | Q3 - 2011 | 3904 | 3790 | FALSE | 29 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline. | 100 | No variance from baseline. | 75 | Since the baseline was submitted it became evident that the network design will be fluid as we move forward. While the network design is 75% complete, as ride outs and meetings are held with various utilities and local government agencies and as permits are negotiated the network design may need to be updated and/or changed. As a result the actual percent complete in this category varies from our initial baseline report which assumed that we would be working on all sections of the build simultaneously during the first year thus causing the variance between actual and our baseline projections. | 18 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 18 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 37 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 20 | Equipment is being purchased on an as needed basis. | 31 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 37 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 37 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2011-11-07 11:44 | 2011-11-07 11:44 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2011 | Q4 | Q4 - 2011 | 5346 | 5019 | FALSE | 37 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  |  | 100 | No variance from baseline. | 75 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 25 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 25 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 40 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 27 | Equipment is being purchased on an as needed basis. | 25 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 40 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 40 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2012-02-28 13:42 | 2012-02-28 13:42 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2012 | Q1 | Q1 - 2012 | 5944 | 5571 | FALSE | 67 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No Variance from baseline. | 100 | No variance from baseline. | 75 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 52 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report.Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. wil | 67 | Equipment is being purchased on an as needed basis. | 60 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 52 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 52 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2012-05-07 15:06 | 2012-05-07 15:06 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2012 | Q2 | Q2 - 2012 | 6740 | 5996 | FALSE | 74 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline | 100 | No variance from baseline | 75 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 52 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report.Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. wil | 67 | Equipment is being purchased on an as needed basis. | 74 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2012-07-30 17:49 | 2012-07-30 17:49 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2012 | Q3 | Q3 - 2012 | 8048 | 6730 | FALSE | 77 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline | 100 | No variance from baseline | 85 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 50 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 69 | Equipment is being purchased on an as needed basis. | 77 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2012-11-26 16:11 | 2012-11-26 16:11 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2012 | Q4 | Q4 - 2012 | 8850 | 7632 | FALSE | 86 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 0 |  | No variance from baseline | 100 | No variance from baseline | 95 | During this project it has become evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. has been and will continue to be on the Community Anchor Institutions for which we have contracts. Also, we are experiencing delays in the delivery of the fiber optic cable. We anticipated to receive fiber in this quarter, however did not thus our expenditures were lower than projected. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the districts for which we have signed contracts in place for services. Our primary focus for design, engineering, permitting etc. will be on these Community Anchor Institutions. As a result the actual percent complete in this category varies from our initial baseline report. | 55 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 69 | Equipment is being purchased on an as needed basis. | 86 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 67 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2013-02-19 16:16 | 2013-02-19 16:16 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2013 | Q1 | Q1 - 2013 | 9838 | 8455 | FALSE | 93 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 0 |  | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 93 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 93 | Since the baseline was submitted it became evident to Contact Network Inc. that the design, build and procurement should be conducted in such a way as to accommodate the Community Anchor Institutions for which we have executed contracts. Our primary focus for design, engineering, permitting etc. will be on these Institutions. As a result the actual percent complete in this category varies from our initial baseline report which assumed we would be working on all sections of the build simultaneously thus causing the variance between actual and baseline projections. | 2013-05-20 16:52 | 2013-05-20 16:52 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2013 | Q2 | Q2 - 2013 | 10660 | 8990 | FALSE | 100 | No variance from baseline. | 0 |  | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 100 | No variance from baseline. | 2013-08-20 13:11 | 2013-08-20 13:11 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2013 | Q3 | Q3 - 2013 | 11182 | 9372 | FALSE | 100 | No variance from baseline | 0 |  | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2013-11-04 14:05 | 2013-11-04 14:05 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | 2013 | Q4 | Q4 - 2013 | 11906 | 10075 | FALSE | 100 | No variance from baseline | 0 |  | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2014-02-27 11:17 | 2014-02-27 11:17 | 5678 | 5678 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570105 | 2010 | Q4 | Q4 - 2010 | 1002 | 2047 | FALSE | 10 | N/A | 0 |  | N/A | 100 | N/A | 50 | The compeletion of the network design is dependant upon the awarding of a contract to a qualified vendor. | 25 | N/A | 10 | N/A | 10 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-08 10:11 | 2011-02-08 10:11 | 6169 | 6169 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2011 | Q1 | Q1 - 2011 | 2228 | 2859 | FALSE | 10 | In line with baseline report | 0 |  | No Change from baseline | 100 | In line with baseline report | 25 | The back-haul network design has been reconfigured to remove 100 miles of fiber. As a result the percent complete has been revised from 100% to 25%.The network design will not be complete until a vendor is selected and completes a comprehensive design process. | 0 | Right of Way is no longer needed since fiber construction has been removed from the project | 5 | In line with baseline report | 0 | No Change from baseline | 0 | No Change from baseline | 0 | No Change from baseline | 0 | No Change from baseline | 0 | No Change from baseline | 2011-05-20 16:23 | 2011-05-20 16:23 | 6169 | 6169 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2011 | Q2 | Q2 - 2011 | 3224 | 3373 | FALSE | 2 | Overall progress has been revised from 15 to 2% to align with budget expenditure. | 0 |  | In line with baseline report. | 80 | Overall progress has been revised from 100 to 80% to align with budget expenditure. | 5 | The back-haul network design has been reconfigured to remove 100 miles of fiber. As a result the percent complete has been revised to 5%.The network design will not be complete until a vendor is selected and completes a comprehensive design process. | 0 | Right of Way is no longer needed since fiber construction has been removed from the project | 0 | With the removal of the 100 mile backhaul we do not anticipate the need for construction permits at this time. | 0 | Revised 0%. Site prep is expected to begin in following quarter. | 0 | In line with baseline report. | 0 | In line with baseline report. | 0 | In line with baseline report. | 0 | In line with baseline report. | 2011-08-19 09:59 | 2011-08-19 09:59 | 6169 | 6169 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2011 | Q3 | Q3 - 2011 | 3900 | 3788 | FALSE | 2 | We expect to have a vendor selected and contract negotiations almost complete. The delay in the overall project completion is a result of the change in scope to remove the dark fiber and add additional towers to the design. | 0 |  | In line with baseline report. | 90 | EA's are complete for the 114 sites in the project. However, we have left the percent complete at 90% in case we need to supplement any new sites. | 5 | The back-haul network design has been reconfigured to remove 100 miles of fiber. As a result the percent complete has been revised from 100% to 5%.The network design will not be complete until a vendor is selected and completes a comprehensive design process. | 0 | Right of Way is no longer needed since fiber construction has been removed from the project | 0 | As a result of the re-scoped design the construction requirement has been significantly reduced. The baseline report projected 25% complete by the end of this period. We believe we will catch up in the next two quarters. | 0 | As a result of the re-scoped design the construction requirement has been significantly reduced. The baseline report projected 30% complete by the end of this period. We believe we will catch up in the next two quarters. | 0 | Since we have not secured a vendor we have not been in a position to purchase equipment. We believe we will catch up in the next two quarters. | 0 | In line with baseline report. | 0 | In line with baseline report. | 0 | In line with baseline report. | 2011-11-04 16:15 | 2011-11-04 16:15 | 6169 | 6169 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2011 | Q4 | Q4 - 2011 | 4722 | 4370 | FALSE | 5 | By the end of the quarter a contract should be executed and site development work started at tower sites. | 0 |  | N/A | 90 | EA's are complete for the 114 sites in the project. we may need to replace or supplement these sites so the percent complete will remain at 90% | 25 | A preliminary design should be completed by the vendor. Final approval will occur in the second quarter of 2012 | 0 | Rights of Way is no longer needed since the fiber component has been removed form the project | 0 | The project scope does not call for construction of any new towers. Any permits needed for attachment will be obtained by the contractor starting in the second quarter of 2012 | 0 | Site preparation has been delayed until contractor selection and contract execution. Site prep should commence is the 2nd quarter | 0 | The State expects to make equipment purchases for Microwave Radios and eNodeB's by the end of the second quarter of 2012. | 0 | The State expects network build to start in the second quarter of 2012. | 0 | Equipment purchases for Microwave Radios and eNodeB's by the end of the second quarter of 2012. Equipment will be deployed in a phased in approach outlined in the project plan. | 10 | Initial testing shall commence with equipment deployment | 2012-01-30 16:15 | 2012-01-30 16:15 | 6169 | 6169 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2012 | Q1 | Q1 - 2012 | 5954 | 5576 | FALSE | 1 | See narrative in section 3. | 0 |  | No Change | 90 | EA's are complete for the 114 sites in the project. we may need to replace or supplement these sites so the percent complete will remain at 90% | 5 | See narrative in section 3. | 0 | Rights of Way is no longer needed since the fiber component has been removed form the project | 0 | The project scope does not call for construction of any new towers. Any permits needed for attachment will be obtained by the contractor when the project starts. | 0 | Under the State's revised plan, an RFP will be issued for site evaluation services. Site development services may be included as part of the RFP. The State is working with the NTIA on an agreeable plan. See answer to question (3) for more detail. | 0 | See narrative in section 3. | 0 | See narrative in section 3. | 0 | See narrative in section 3. | 0 | See narrative in section 3. | 2012-05-08 10:07 | 2012-05-08 10:07 | 6169 | 6169 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2012 | Q2 | Q2 - 2012 | 6376 | 5796 | FALSE | 1 | See narrative in (Project Indicators Next Quarter section 1) | 50 | Site identification | See narrative in (Project Indicators Next Quarter section 1) | 90 | EA's are complete for the 114 sites in the project. we may need to replace or supplement these sites so the percent complete will remain at 90% | 5 | See narrative in (Project Indicators Next Quarter section 1) | 0 | Rights of Way is no longer needed since the fiber component has been removed form the project | 0 | The project scope does not call for construction of any new towers. | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 2012-07-10 16:05 | 2012-07-10 16:05 | 6169 | 6169 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2012 | Q3 | Q3 - 2012 | 7870 | 6639 | FALSE | 1 | See narrative in (Project Indicators Next Quarter section 1) | 0 | Site Identification | See narrative in (Project Indicators Next Quarter section 1) | 90 | EA's are complete for the 114 sites in the project. we may need to replace or supplement these sites so the percent complete will remain at 90% | 5 | See narrative in (Project Indicators Next Quarter section 1) | 0 | Rights of Way is no longer needed since the fiber component has been removed form the project | 0 | The project scope does not call for construction of any new towers. | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 2012-11-14 11:50 | 2012-11-14 11:50 | 7541 | 7541 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2012 | Q4 | Q4 - 2012 | 8640 | 7453 | FALSE | 5 | See narrative in (Project Indicators Next Quarter section 1) | 50 | Site Identification/Coverage Design Map | Begin Site Identification of government owned sites and develop initial coverage design map. See narrative in (Project Indicators Next Quarter section 1) | 90 | EA's are complete for the 114 sites in the project. we may need to replace or supplement these sites so the percent complete will remain at 90% | 5 | See narrative in (Project Indicators Next Quarter section 1) | 0 | Rights of Way is no longer needed since the fiber component has been removed form the project | 0 | The project scope does not call for construction of any new towers. | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 0 | See narrative in (Project Indicators Next Quarter section 1) | 2013-01-31 15:38 | 2013-01-31 15:38 | 7645 | 7645 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2013 | Q1 | Q1 - 2013 | 9682 | 8373 | FALSE | 3 | See narrative above in Project Indicators (Next Quarter) | 100 | Site Identification/Coverage Design Map | Onboard site identification resources and begin site identification of government owned sites and develop initial coverage design map. | 90 | Assessments are complete for the 114 sites in the project. Team may need to replace or supplement these sites so the percent complete will remain at 90% | 5 | See narrative above in Project Indicators (Next Quarter) | 0 | Rights of Way is no longer needed since the fiber component has been removed from the project | 0 | The project scope does not call for construction of any new towers. | 0 | See narrative above in Project Indicators (Next Quarter) | 0 | See narrative above in Project Indicators (Next Quarter) | 0 | See narrative above in Project Indicators (Next Quarter) | 0 | See narrative above in Project Indicators (Next Quarter) | 0 | See narrative above in Project Indicators (Next Quarter) | 2013-05-10 13:40 | 2013-05-13 12:55 | 7645 | 7645 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2013 | Q2 | Q2 - 2013 | 10182 | 8669 | FALSE | 4 | See narrative above in Question 1 | 100 | Site Identification/Initial Coverage Design/Site Assessment | Onboard site assessment resources and begin site assessment activities; finalize site identification activities and update initial coverage design | 90 | Assessments are complete for the 114 sites in the project. Team may need to replace or supplement these sites so the percent complete will remain at 90% | 5 | See narrative in Question 1 | 0 | Rights of way is no longer needed since the fiber component has been removed from the project. | 0 | The project scope does not call for construction of any new towers. | 0 | See narrative above in Question 1 | 0 | See narrative above in Question 1 | 0 | See narrative above in Question 1 | 0 | See narrative above in Question 1 | 0 | See narrative above in Question 1 | 2013-07-26 13:34 | 2013-07-26 13:34 | 7645 | 7645 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2013 | Q3 | Q3 - 2013 | 11180 | 9371 | FALSE | 5 | See narrative above in Question 1 | 100 | Site Identification / Initial Coverage Design | Site identification and initial coverage design is complete. | 90 | Assessments are complete for the 114 sites initially defined for the project. Team may need to replace or supplement these sites so the project complete will remain at 90%. | 5 | See narrative above in Question 1 | 0 | Rights of way is no longer needed since the fiber component has been removed from the project. | 0 | See narrative above in Question 1 | 0 | Until project direction is defined, the project team will delay all site preparation activities. | 0 | See narrative above in Question 1 | 0 | See narrative above in Question 1 | 0 | See narrative above in Question 1 | 0 | See narrative above in Question 1 | 2013-11-01 17:43 | 2013-11-01 17:43 | 7645 | 7645 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | 2013 | Q4 | Q4 - 2013 | 11846 | 10019 | FALSE | 4 | See narrative in Question 1 | 100 | Site Identification/Initial Coverage Design | Based on the the previously approved project scope in the UASI region, site identification was completed in August 2013 and the initial coverage design was completed in September 2013. Site identification for deployable assets in the Route 21 Corridor, Camden, and Atlantic City have begun and reflected in Site Preparation (2f). | 90 | The project team submitted the revised EHP Pre-Screening list to NTIA; currently under review with NTIA Environmental team. New Jersey anticipates a response from the environmental team. | 30 | Network design activities will continue based on identified deployable locations. | 0 | The newly approved project scope does not call for right of way requirements. | 0 | The newly approved project scope does not call for construction of any new towers. Any permits needed will be obtained by the contractor. | 10 | Potential sites have been identified for deployable assets. The project team will continue to identify locations for the deployable assets and conduct site visits. New Jersey also anticipates collaborating with electrical companies to support providing electrical capacity to the deployable assets once placed. | 0 | See narrative in Question 1. | 0 | Construction of the network has not started and was delayed due to the LTE suspension and change in project scope. | 0 | Equipment deployment is delayed until a vendor has been procured to purchase and integrate equipment and upon construction of Cell on Wheels. | 0 | Network testing will begin upon construction and deployment of Cell on Wheels. | 2014-02-19 14:26 | 2014-02-19 14:26 | 7645 | 7645 | Treasury, New Jersey Department of | TRUE
NT10BIX5570106 | 2010 | Q4 | Q4 - 2010 | 1026 | 2070 | FALSE | 5 | No variance from baseline | 75 | IRU acquisition | No variance from baseline | 90 | Slight delay due to SHPO final report resulting in the variance | 60 | No variance from baseline | 20 | Baseline is 10 but we think we may be further ahead by the end of the quarter | 20 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 2011-02-09 17:32 | 2011-02-09 17:32 | 6703 | 6703 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2011 | Q1 | Q1 - 2011 | 2282 | 2886 | FALSE | 4 | Environmental Assessment and dark fiber lease agreement are causing delays with the project moving forward. We are approximately a quarter behind. We are accelerating the State Historical Preservation Office report by providing them with a preliminary survey report. We are also bringing in a project manager that will help us get more accomplished on the tasks. | 100 |  | No variance from baseline | 100 | NA | 90 | Environmental Assessment delays have delayed final approval of the fiber route. We will move ahead with the network design on the preliminary route because the survey results and initial discussions with the Nevada State Department of Transportaion on their right of ways indicate it should be clear for approval | 50 | No variance from baseline | 40 | The node sites haven't been given final approval, so we are slightly behind in getting construction approvals. We anticipate having most of the permitting documentation ready by the end of the quarter. We will have the realty office expedite the permitting as they review the right of way and easements and site approvals. | 25 | There is no variance from the baseline | 3 | Delays with the environmental assessment, construction contract and hiring of the project manager have us slightly behind schedule on procurement. Our efforts should improve as the new project manager will be hired and on board by the middle of this quarter. Finalizing the contract with our primary contractor will be their primary task. The modified EA/six month budget includes all significant construction material, so that will be the first order of business for the contractor. We will have the contractor prepare the procurement orders as we complete the overall construction contract. | 0 | NA | 0 | NA | 0 | NA | 2011-05-24 15:47 | 2011-05-24 15:47 | 6703 | 6703 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2011 | Q2 | Q2 - 2011 | 3208 | 3365 | FALSE | 28 | We will be slightly behind overall on the project by the end of the next quarter. However we are expecting significant improvement in meeting our milestones and bringing the project back to the established schedule. | 100 |  | Fiber agreement and appraisal completed. | 100 | No Variance from baseline | 75 | We should have the network designs completed for the outside plant. We are behind due to the contract issues from the prior quarter, so the final network designs for the connections and nodes might not be completed in time to bring us on schedule during this quarter. We are pressuring the attorneys to resolve these contract issues and initiating design discussions with our contractor prior to the finalization of the contract. | 75 | We will have made significant improvement on the rights of way to bring us close to schedule during this quarter, but because we expect to have the final outside plant designs completed near the end of the quarter, that probably isn't enough time for the department of transportation to review and give the clearance before this quarter ends. | 100 | No Variance from baseline | 0 | Because our environmental assessment will be completed just before this quarter ends, we probably won't be able to begin site preparation until the very end of the quarter. | 1 | Although we will not be on schedule with the procurement, we expect to have all the proposals from the vendors for the outside plant materials and equipment. The orders for the materials and equipment will be in process by the end of this quarter. | 20 | No Variance from baseline | 0 | No Variance from baseline | 0 | No Variance from baseline | 2011-08-18 17:30 | 2011-08-18 17:30 | 6703 | 6703 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2011 | Q3 | Q3 - 2011 | 4120 | 3903 | FALSE | 27 | The environmental assessment, Cultural survey, Praxis contract, and IRU agreement with level 3 have put us behind. The EA and cultural survey have been completed and submitted. The praxis contract and IRU contract are going before council in the next quarter. We should be able to start procurement and construction in the next quarter. Once we start construction we will be able to get back on track with our spending and developplan to meet the 2/3 rds spending by August 1st 2012. | 0 | true | No variance from baseline | 100 | Complete | 75 | The ability to complete the design is reliant on the signing of the praxis contract. We are expecting to have the high level design completed within 30 days of the signing. | 100 | Complete | 100 | No variance from baseline | 5 | We have identified the locations and are getting the land appraised. Once the contract with Praxis is signed we will begin preparing the sites. | 5 | We are ready to start the outside plant procurement but are waiting for the Praxis contract to be signed. | 5 | We are looking at starting procurement and construction in this quarter. The IRU will give us 40 network miles deployed. | 6 | We expect to have at least 6 miles deployed by the end of this quarter contingenton the signing of the Praxis contract. | 0 | No variance from baseline | 2011-11-17 16:53 | 2011-11-17 16:53 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2011 | Q4 | Q4 - 2011 | 5292 | 4958 | FALSE | 27 | The Contract with Praxis is holding up the project. Praxis as of yet has not been able to secure a bond for the project. They are waiting to hear from anotherbonding agent and preparing the waiver request documentation. We expect this to be cleared up in the next quarter. | 100 |  | We are working on correcting the IRU and expect it to be complete in the next quarter. | 100 | Complete | 75 | The ability to complete the design is reliant on the signing of the praxis contract. We are expecting to have the mid level design completed within 30 days of the signing. | 100 | complete | 100 | Complete | 50 | We expect to have the node sites prepared for construction in the next quarter. If the contract with praxis is signed early in the next quarter then we will have the node sites completed. | 25 | We are ready to start the outside plant procurement but are waiting for the Praxis contract to be signed. Praxis has started the Procurement process and as soon as the contract is signed the equipment will begin to be delivered. | 40 | We are expecting the IRU to be completed in the next quarter equating to 40 leased miles. If a bonding waiver is required we will have no new network mile s constructed and subsequently no CAIs connected. | 6 | We expect to have at least 6 miles deployed by the end of this quarter contingent the signing of the Praxis contract. | 0 | No Variance from baseline | 2012-02-27 13:33 | 2012-02-27 13:43 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2012 | Q1 | Q1 - 2012 | 6134 | 5669 | FALSE | 23 | The bonding waiver has prevented us from signing the contract, but we expect it to be cleared up in the next early quarter. | 100 |  | The Sovereign immunity issue has been resolved. | 100 | Complete | 75 | The ability to complete the design is reliant on the signing of the praxis contract. We are expecting to have the low level design completed within 30 days of the signing. | 100 | Complete | 100 | Complete | 50 | We expect to have the node sites prepared for construction in the next quarter. If the contract with praxis is signed early in the next quarter then we will have the node sites completed. | 25 | We are ready to start the procurement but are waiting for the Praxis contract to be signed. | 15 | We are expecting the IRU to be completed in the next quarter as well as having the contract with Praxis signed. We should see significant progress over the next two quarters. | 6 | We expect to have at least 6 miles deployed by the end of this quarter contingent the signing of the Praxis contract. | 0 | No Variance from baseline | 2012-05-16 13:02 | 2012-05-16 13:02 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2012 | Q2 | Q2 - 2012 | 7092 | 6173 | FALSE | 27 | With construction starting next quarter we expect to be caught up with in 2-4 months. | 100 |  | The IRU will be complete in the next quarter | 100 | Complete | 100 | We expect to have the Network design complete in the next quarter. | 100 | Complete | 100 | Complete | 100 | Complete | 30 | The request for proposals should come in in the next quarter but not completed until the following quarter | 40 | With construction starting we expect the network build to be at least 40% complete. | 25 | We expect to have at least 24 miles deployed this quarter. | 12 | Testing will start in conjunction with the fiber deployment. | 2012-08-15 15:50 | 2012-08-15 15:50 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2012 | Q3 | Q3 - 2012 | 7960 | 6686 | FALSE | 77 | We expect to be approximately seventy seven percent complete by the end of the next quarter. | 100 |  | The IRU and easement will be complete in the next quarter | 100 | Complete | 100 | The outside plant, fiber route, and node engineering is complete. The request for proposal for the inside plant and electronics have been completed and we are expecting the inside plant and electronic engineering to be complete in the next quarter. | 100 | Complete | 100 | Complete | 100 | Complete | 75 | We are expecting the equipment procurement to begin in the next quarter. The result of the request for proposals have us using Ericsson equipment and the procurement is dependant on the completion of the detailed network design. | 50 | With construction starting we expect the network build to be at least fifty percent complete. | 40 | We expect to have deployed forty percent of the equipment next quarter. | 12 | Testing will start in conjunction with the fiber deployment. | 2012-11-19 16:49 | 2012-11-19 16:49 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2012 | Q4 | Q4 - 2012 | 8808 | 7601 | FALSE | 63 | The late start in construction have us slightly behind but we expect the back bone, 40 miles, to be completed in the next quarter. We are planning on having all of the CAIs' hooked up in the second quarter of 2013. | 100 |  | The Sovereign immunity issue has been resolved. | 100 | Complete | 100 | The outside plant, fiber route, and node engineering is complete. We are expecting the inside plant and electronic engineering to be complete in the next quarter. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | We are expecting to complete this in the next quarter | 100 | We are expecting to complete this in the next quarter | 85 | With the project being delayed by the construction start date we are expecting to have only 85 percent deployed in the next quarter. | 50 | We are expecting fifty percent of the testing to be complete by the end of next quarter. | 2013-02-15 15:10 | 2013-02-15 15:10 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2013 | Q1 | Q1 - 2013 | 9946 | 8517 | FALSE | 94 | The projects late start still has us behind on our baseline data but we are on track to finish the project within the specified grant period. | 100 |  | The sovereign immunity issue has been resolved | 100 | Complete | 100 | We expect this to be completed and installed in the next quarter. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | We expect this to be completed in the beginning of the next quarter | 100 | We are on track to have this completed in the next quarter | 90 | We expect to have a majority of the equipment deployed in the next quarter. | 65 | We are expecting to start the testing in the next quarter. | 2013-05-28 17:10 | 2013-05-28 17:10 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2013 | Q2 | Q2 - 2013 | 10606 | 8961 | FALSE | 100 | Complete | 100 |  | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-08-15 12:00 | 2013-08-15 12:00 | 7227 | 7227 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2013 | Q3 | Q3 - 2013 | 11258 | 9419 | FALSE | 99 | We expect project to be online and operational, with complete testing and resolution of minor issues to be resolved. | 100 | NA | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 80 | We expect operational testing to reveal some minor configuration issues | 2013-11-14 19:13 | 2013-11-14 19:13 | 6703 | 6703 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2013 | Q4 | Q4 - 2013 | 11884 | 10051 | FALSE | 100 | NA | 100 |  | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 2014-02-25 12:33 | 2014-02-25 12:33 | 6703 | 6703 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | 2014 | Q1 | Q1 - 2014 | 12290 | 10460 | FALSE | 100 | NA | 100 |  | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 100 | NA | 2014-06-24 12:37 | 2014-06-24 12:37 | 6703 | 6703 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570107 | 2010 | Q4 | Q4 - 2010 | 938 | 1985 | FALSE | 10 | N/A | 0 |  | N/A | 100 | N/A | 85 | N/A | 15 | N/A | 15 | N/A | 20 | N/A | 46 | N/A | 8 | N/A | 5 | N/A | 5 | N/A | 2011-01-30 16:40 | 2011-01-30 16:40 | 6748 | 6748 | Texas A&M University | TRUE
NT10BIX5570107 | 2011 | Q1 | Q1 - 2011 | 2318 | 2904 | FALSE | 13 | No Variance | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 70 | No Variance | 70 | No Variance | 8 | No Variance | 30 | No Variance | 8 | No Variance | 2 | No Variance | 8 | No Variance | 2011-05-25 17:47 | 2011-05-25 17:47 | 6973 | 6973 | Texas A&M University | TRUE
NT10BIX5570107 | 2011 | Q2 | Q2 - 2011 | 3192 | 3356 | FALSE | 19 | No Variance | 0 |  | No Variance | 100 | No Variance | 100 | No Variance | 95 | Delays due to TxDOT | 95 | San Antonio aerial construction pending receipt of insurance certificate from Verizon. | 16 | Delay due to FONSI approval 06/07/2011 | 30 | Delay due to FONSI approval 06/07/2011 | 7 | Delay due to FONSI approval 06/07/2011 | 2 | Delay due to FONSI approval 06/07/2011 | 7 | Delay due to FONSI approval 06/07/2011 | 2011-08-18 11:52 | 2011-08-18 11:52 | 6973 | 6973 | Texas A&M University | TRUE
NT10BIX5570107 | 2011 | Q3 | Q3 - 2011 | 4360 | 4036 | FALSE | 27 | No Variance | 0 |  | N/A | 100 | FONSI received 06/07/2011 No modifications | 100 | No Variance | 95 | See Below | 95 | See Below | 35 | See Below | 60 | Engineering modifications negatively impacted procurement | 13 | Engineering modifications and permitting issues negatively impacted schedule | 10 | Procurement of materials has impacted deployment | 10 | Testing follows Deployment | 2011-11-30 17:55 | 2011-11-30 17:55 | 6973 | 6973 | Texas A&M University | TRUE
NT10BIX5570107 | 2011 | Q4 | Q4 - 2011 | 5182 | 4845 | FALSE | 30 | We will just begin the start of construction for two of the largest fiber segments of the project in mid February. We anticipate an increase in the overall project percentages for this quarter. | 0 |  | N/A | 100 | FONSI received 6/7/2011. No Modifications anticipated. | 100 | No Variance | 95 | We project that 95 percent of the Lease agreements and permits will be executed by the end of the next quarter. All permitting agencies have been contacted and are working through the process with us as our project goes forward. | 95 | All known permitting entities have been contacted for approval. Some governing authorities, such as county commissioners courts, meet at specific intervals to make permitting decisions and this can impact the schedule. We can only anticipate these processes are swiftly passed through the appropriate channels for approvals. We have done due diligence in reaching out and communicating the benefits of the project. | 35 | With the multitude of project sites across the state site preparation is contingent upon permit approvals. We project this projected percent will increase with the start of construction projected in the next quarter. | 80 | Equipment orders have been placed for the majority but not all deployment sites at this time we are projecting 80 percent will be procured by the end of next quarter. | 13 | Projection remains low based on the current construction schedule. | 10 | This projection is based on the number of fiber miles constructed. The largest fiber construction projects will be starting next quarter. | 10 | We cannot improve the projected network testing percentage until we have fiber placed which is progressing at a slower pace than expected, however, will see improvements with the start of the two larger projects next quarter. | 2012-02-21 18:09 | 2012-02-21 18:09 | 6973 | 6973 | Texas A&M University | TRUE
NT10BIX5570107 | 2012 | Q1 | Q1 - 2012 | 6364 | 5787 | FALSE | 46 | Two additional TxDOT leases executed has allowed us to improve percentage on the overall project. The remaining outstanding permits both City and TxDOT are a factor in improving this overall number. City of Waco is requiring a franchise agreement which is in progress and has to be executed prior to permitting. | 0 |  | N/A | 100 | No Variance | 100 | No Variance | 98 | The remaining outstanding permits both City and TxDOTare a factor in improving this overall number. City of Waco is requiring a franchise agreement which is in progress and has to be executed prior to permitting. | 98 | The remaining outstanding permits both City and TxDOTare a factor in improving this overall number. City of Waco is requiring a franchise agreement which is in progress and has to be executed prior to permitting. | 100 | No variance | 75 | Industry wide manufacturer delays for fiber will impact fiber deployment. | 22 | We intend to be in line with the baseline project schedule by February 1, 2013. | 18 | We intend to be in line with the baseline project schedule by March 1, 2013 | 15 | We intend to be in line with the baseline project schedule by March 1, 2013. | 2012-05-31 14:44 | 2012-05-31 14:44 | 6171 | 6171 | Texas A&M University | TRUE
NT10BIX5570107 | 2012 | Q2 | Q2 - 2012 | 7098 | 6176 | FALSE | 68 | We anticipate completing the majority of both the Stephenville and Texarkana construction. In addition, the TAMU CIS core routers are being installed, all of the access routers are now on order, and the Campbell generator will be installed. | 0 |  | n/a | 100 | No Variance | 100 | No Variance | 100 | We anticipate resolution with City of Waco Franchise Agreement | 100 | Resolution with City of Waco andPermit approvals granted thereafter | 100 | No Variance | 80 | Remaining equipment will continue to be ordered in the 30-60 day window prior to deployment for warranty purposes. | 68 | The 70% completion rate will keep us on track for completing by the revised February 2013 date. | 35 | This remains dependent on fiber terminations, testing and specific interconnections being completed. We are aggressively pursuing our established project goals for deployment. | 25 | Network Testing remains dependent on fiber placing/splicing/terminations and will follow a close schedule behind equipment deployment. | 2012-08-15 17:36 | 2012-08-15 17:36 | 6973 | 6973 | Texas A&M University | TRUE
NT10BIX5570107 | 2012 | Q3 | Q3 - 2012 | 8162 | 6791 | FALSE | 82 | We anticipate 20 additional miles being constructed by 12/31/2012. We anticipate completing both Stephenville and Texarkana. Midplains has begun construction in Canyon, TX schedule for completion during the 4th quarter 2012. | 0 |  | n/a | 100 | No variance | 100 | No variance | 100 | We anticipate resolution for City of Waco franchise agreement | 100 | Pending permits should follow City of Waco Franchise agreement resolution | 100 | No varaiance | 90 | Remaining equipment will continue to be ordered in the 30-60 day window prior to deployment for warranty purposes. | 80 | The 80% completion rate will keep us on track for completing by the revised February 2013 date. | 50 | This remains dependent on fiber terminations, testing and specific interconnections being completed. We are aggressively pursuing our established project goals for deployment. | 50 | Network Testing remains dependent on fiber placing/splicing/terminations and will follow a close schedule behind equipment deployment. | 2012-11-29 19:54 | 2012-11-29 19:54 | 6186 | 6186 | Texas A&M University | TRUE
NT10BIX5570107 | 2012 | Q4 | Q4 - 2012 | 8958 | 7733 | FALSE | 74 | We anticipate a large portion of the construction on the remaining project sites to be completed by the end of Q1 2013. These include Texarkana, Waco, the remainder of West Texas A&M University in Canyon, Tx, (5.6 miles total: 2.7 Waco; 2.96 WTAMU) | 0 |  | n/a | 100 | No variance | 100 | No variance | 100 | We anticipate resolution for City of Waco franchise agreement. | 100 | Pending permits should follow City of Waco Franchise agreement resolution. | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 40 | No variance | 2013-02-25 19:19 | 2013-02-25 19:19 | 6186 | 6186 | Texas A&M University | TRUE
NT10BIX5570107 | 2013 | Q1 | Q1 - 2013 | 9920 | 8501 | FALSE | 100 | During Q2 2013 we will place 2.17 miles of fiber in Waco and 1.7 miles in Texarkana, wrapping up all fiber placement for the project. Once fiber is placed, we will pursue completion of network build and network testing. We anticipate 150.82 total miles upon project completion. | 0 |  | n/a | 100 | No variance | 100 | No variance | 100 | The final rights of way issue, the franchise agreement with Waco will be fully executed during 2nd Qtr 2013, to be immediately following by construction, fiber placement, splicing/ termination. | 100 | Permits follow franchise agreement with City of Waco | 100 | No variance | 100 | No variance | 90 | Delays due to third party dependencies negative 10% variance | 100 | No variance | 90 | Delays due to third party dependencies negative 10% variance | 2013-05-28 11:00 | 2013-05-28 11:00 | 6777 | 6777 | Texas A&M University | TRUE
NT10BIX5570107 | 2013 | Q2 | Q2 - 2013 | 10812 | 9078 | FALSE | 98 | According to the Budget Execution Details section, we plan to expend 98% of your overall budget by the end of next quarter. The Overall Project Milestone has been updated to reflect planned expenditures. | 0 |  | n/a | 100 | No variance | 100 | No variance | 100 | The final rights of way issue, and agreements with Waco were fully executed during 2nd Qtr 2013, construction, fiber placement, splicing/ termination to be complete during Q3 2013. | 100 | Permits issued Traffic control plans approved for construction start July 2013. | 100 | No Variance | 100 | No Variance | 100 | There is a negative 10% variance from the baseline. | 100 | No Variance | 100 | There is a negative 10% variance from the baseline. | 2013-08-29 15:39 | 2013-08-30 22:55 | 6186 | 6186 | Texas A&M University | TRUE
NT10BIX5570107 | 2013 | Q3 | Q3 - 2013 | 12002 | 10166 | FALSE | 100 | No Variance | 0 |  | n/a | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 2014-03-28 12:31 | 2014-03-28 12:31 | 6186 | 6186 | Texas A&M University | TRUE
NT10BIX5570108 | 2010 | Q4 | Q4 - 2010 | 1232 | 2262 | FALSE | 3 | No variance | 6 | Administrative | No variance | 100 | No variance | 15 | No variance | 2 | No variance | 0 | NA - included in 2h Network Build | 1 | No variance | 8 | No variance | 0 | No variance | 0 | No variance | 0 | NA. Using existing staff not charged to project plus contractual resources reported in 2k Other. | 2011-02-18 17:08 | 2011-02-18 17:08 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2011 | Q1 | Q1 - 2011 | 1926 | 2708 | FALSE | 8 | Target 6%. CMS anticipates being slightly ahead of schedule as a result of faster than anticipated progress with leased fiber IRUs and Rights of Way. Last quarter CMS secured one leased fiber IRU ahead of schedule and has signed a second that will be recorded as an expenditure in the next quarter. The engineering firm is progressing faster than expected on researching and preparing Rights of Way permits. More details on these two activities are covered below. | 9 |  | Target 10%. Costs for office equipment were lower then expected and project staff started later then expected. | 92 | Target 100%. The final environmental assessment report was submitted in April and a FONSI received was received April 22. We are anticipating the final costs for the environmental report and analysis will be about $70,000 lower then budgeted; however, SHPO has requested unanticipated archeological surveys in select areas. The remaining Environmental Assessment funds plus cost savings from other areas will be needed for the surveys. We are awaiting a final cost estimate before re-budgeting. | 32 | Target 35%. The costs for Network Design are looking to be less than anticipated which is reflected in the 3% difference between the targeted amount in the project baseline and the new projection for the next quarter. We anticipate the difference between the budgeted amount and revised projection to be used for the archeological surveys. We are on track to complete detailed design on 25% of the backbone and 25% of the lateral network miles. | 15 | Target 2%. The project baseline included conservative targets during the first year as we were unsure of the time needed for this milestone. The engineering firm is making better progress than anticipated in researching and preparing right of way/easement requests. | 0 | NA | 11 | Target 11%. Most of the effort for this milestone is focused on preparing network Point of Presence (POP) sites to support the optical equipment. | 25 | Target 26%. The variance is due to equipment costs coming in slightly lower then expected. | 3 | Target 0%. CMS has secured new fiber lease agreements sooner then anticipated. This will allow us to light a major route between Collinsville to Chicago sooner then projected. | 0 | Target 0% | 0 | NA | 2011-05-10 13:45 | 2011-05-10 13:45 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2011 | Q2 | Q2 - 2011 | 3082 | 3298 | FALSE | 10 | Baseline target is 12%. The construction phase has been delayed by about 30 days due to the rebidding of the solicitation. Contracts have been awarded and construction will be starting in this quarter. | 15 |  | Baseline target is 21%. Costs mapped to this milestone will need to be re-budgted as the original budget included costs associated with annual maintenance for leased fiber which is an ineligible cost. | 100 | Baseline target is 100% Actually projecting 109% due to anticipated CAI and tower location changes that will require changes/additions to the approved Environmental Assessment. | 36 | Baseline target is 55%. Actual project activity is tracking as planned; however, we overestimated the rate of spend in the baseline. By the end of next quarter we expect to have completed detailed design for 50% of the network miles. | 27 | Baseline target is 2%. The engineering firm is making faster than anticipated progress on researching and preparing right of way permits. CMS established conservative targets through Y2Q2 with all Rights of way permits to be completed by Y2Q3. As the project is moving forward we have better insight into the time needed for this activity and have adjusted our forecasts accordingly. | 0 | NA | 6 | Baseline target is 36%. The projected milestone target is behind the baseline target due to unanticipated contract amendments with landlords. Since most of the POP sites are leased facilities, the power upgrades need to be performed by the landlords. The current contracts do not address how CMS will pay the landlord for these costs so legal counsel has been working with the landlord to amend the contracts. An engineering assessment is needed at another State facility POP location to determine the overall electrical needs. CMS is working with the engineering firm to initiate that study by the end of the quarter. Actual spend for the electrical upgrades at the leased sites and State facility is not anticipated to occur until 2011Q4. The delay does not have an impact on the overall project timeline as the critical path is the fiber construction. The electrical work will continue in parallel with the fiber construction. | 33 | Baseline target is 26%. We are moving forward with ordering and installing equipment for the leased fiber miles as well as the new construction routes. We are beginning to stage the orders and installations for the optical equipment. | 3 | Baseline target is 5%. The construction phase has been delayed by about 30 days due to the rebidding of the solicitation. Contracts have been awarded and construction will be starting in this quarter. | 0 | 0 | 0 | NA | 2011-08-15 13:49 | 2011-08-15 13:49 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2011 | Q3 | Q3 - 2011 | 4024 | 3852 | FALSE | 13 | Baseline target is 20%. The variance is a combination of delays with Rights of Way, Site Preparation and Network Build activities. More details on the cause of the delays and the impact to the overall project timeline are described in the respective Milestone Categories below. | 35 | Professional services such as Project Management, Web Design, Project Engineering | Baseline target is 31%. The 35% projection reflects the re-budgeting of the easement activities to the Administrative and Legal budget line which is reflected in the Other milestone category. | 100 | Baseline target is 100%. No variance. | 68 | Baseline target is 70%. We are expecting to have all network design activities complete by the end of the quarter; however, all invoices for the complete activity will not be received until January. | 24 | Baseline target is 100%. Permits are taking longer then anticipated; however, they are not impacting construction activities at this time. We will likely be behind this baseline for several quarters as the majority of the budgeted permitting fees will be paid to the Illinois Department of Transportation and are expected to be paid through a single Intergovernmental Agreement. This Agreement will likely not be finalized until after the majority of the permits are issued. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 7 | Baseline target is 36%. As reported earlier, POP site upgrades have been delayed due to contract amendments with the site landlords, contract for electrical upgrades, and an engineering assessment. The POP site amendments and contract for electrical upgrades have been finalized and work is beginning. The engineering assessment is underway. This delay is not impacting the overall schedule as these activities are happening in parallel with the fiber construction. | 45 | Baseline target is 26%. CMS is ahead of schedule in lighting leased fiber. We are working to stage and distribute equipment as POP sites are ready. This approach enables a quicker turn-up of leased and built fiber. We are also able to use in house staff instead of contractors which is resulting in a cost savings. | 4 | Baseline target is 13%. Now that construction contracts are established, we expect to see increased activity for network build. While construction activities will start during this quarter, significant expenditures will likely not be recognized until after the first of the year due to the delay in completing the activity and processing vendor payments. | 5 | Baseline target is 30%. CMS originally anticipated utilizing contractual services for equipment deployment. So far, we are using in-house staff that are not billed to the project. The savings will be rebudgeted to another milestone category. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2011-11-14 13:13 | 2011-11-14 13:13 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2011 | Q4 | Q4 - 2011 | 4996 | 4669 | FALSE | 19 | Baseline target is 42%. The difference is primarily due to the unanticipated time to complete the Environmental Assessment. See details below. | 33 | Professional Services such as Project Management, Web Design, Project Enginer | Baseline target is 40%. The majority of the funds budgeted to this milestone are for contractual resources. The shortfall is due to delays on boarding resources earlier in the project. | 96 | Baseline target is 100%. This past quarter we reallocated money to this budget item to cover future costs associated with an amendment to the Environmental Assessment for necessary route modifications. The budgeted amount increased from $920,322 to $984,627. | 85 | Baseline target is 100%. In working with our sub recipient, we have a identified they will be a little behind schedule. We anticipate completing all design activities by the end of next quarter. Because of the billing cycle we project about $700,000 will not be paid until the following quarter resulting in a 15% shortfall of the baseline. | 38 | Baseline target is 100%. Due to the longer then anticipated time for the Environmental Assessment process, permits and rights of way activities are behind what was targeted in the baseline. Permits and rights of way requests have been requested or approved for 56% of the new construction miles. Right of Way fees are primarily charged by the rail roads. The final costs will likely be less then the budgeted amount. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 9 | Baseline target is 61%. Nearly half of this milestone category is for an in kind contribution of space for network equipment within the sub recipient's portion of the project. CMS originally anticipated this space would be secured and booked to the project at this point in the project; however, in working with the sub we're forecasting this activity will occur in Q2-2012. | 68 | Baseline target is 46%. CMS is ahead of schedule in lighting leased fiber. We have purchased most of the optical equipment and have deployed it to the network node sites. This approach enables a quicker turn-up of leased and built fiber. We have also used in house staff instead of contractors which has resulting in a cost savings that will be reinvested in the project. | 6 | Baseline target is 35%. Construction on the first network span started in November. While construction is starting later then anticipated in the baseline we are forecasting completion in Q4-2012 which would be ahead of schedule. We have condensed the construction schedule by utilizing 4 vendors with multiple crews working simultaneously on the 12 network spans. Most, if not all, network spans will be under construction by the end of the next quarter. | 5 | Baseline target is 40%. CMS originally anticipated utilizing contractual services for equipment deployment. So far, we are using in-house staff that are not billed to the project. We are forecasting a savings of $500,000 of the $1,050,000 budgeted to this milestone. The savings will be re-budgeted to another milestone category. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to the project plus contractual resources reported in 2k Other. | 2012-02-14 11:33 | 2012-02-14 11:33 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2012 | Q1 | Q1 - 2012 | 6010 | 5604 | FALSE | 32 | Baseline target is 68%. The revised project schedule set a target of 33%. Fiber deployment is behind for a variety of reasons including unanticipated time needed for the Environmental Assessment, delays finalizing construction contracts, and fiber delivery delays. CMS has developed a revised project schedule considering all these factors. The revised schedule demonstrates completion by year three. The forecast for next quarter is $543,988 less then the revised forecast which is less then 1%. | 49 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 46%. The revised project schedule set a target of 49%. Forecasted cumulative spend is $789,042 of $1,613,923. | 98 | Baseline target is 100%. The revised project schedule set a target of 99%. The forecasted cumulative spend is $984,883 of $1,007,144. The EA is complete and a FONSI received. Any additional spend in this milestone category will be associated with route changes. | 77 | Baseline target is 100%. The revised project schedule set a target of 94%. The forecasted cumulative spend is $3,756,690 of $4,904,937. The network design for outside plant is complete. Spend for two of the three pending route changes is expected to be less then anticipated. | 54 | Baseline target is 100%. The revised project schedule set a target of 88%. The forecasted cumulative spend is $586,449 of $1,076,929. The revised project schedule forecasted spend included $200,000 for A/E on site observations which should have been mapped to the Network Build milestone. Based on this correction, the revised project scheduled target for this quarter is 69%. This leaves a difference of $156,693. Costs for the remaining permit preparation is coming in at a cost lower then expected as are overall permit fees. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 8 | Baseline target is 61%. The revised project schedule set a target of 8%. Forecasted cumulative spend is $308,362 of $3,797,000. | 68 | Baseline target is 46%. The revised project schedule set a target of 71%. Forecasted cumulative spend is $8,041,408 of $11,881,943. The variance is $412,401 and attributable to optical cards that require fiber characterizations for pending fiber leases before ordering. | 23 | Baseline target is 70%. The revised project schedule set a target of 22%. The forecasted cumulative spend is $16,486,416 of $71,400,252. CMS is expecting construction activities to meet or exceed the forecasted target. | 7 | Baseline target is 60%. The revised project schedule set a target of 7%. Forecasted cumulative spend is $51,864 of $699,901. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2012-05-10 12:49 | 2012-05-10 12:49 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2012 | Q2 | Q2 - 2012 | 7134 | 6194 | FALSE | 47 | Baseline target is 72%. The revised project schedule set a target of 55%.The forecast for next quarter is $7,814,330 less then the revised forecast as a result of costs coming in below budget for network design, rights of way, and construction and delays with construction, inside plant and final equipment purchases. | 58 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 52%. The revised project schedule set a target of 63%. The public relations contractual resource working for the sub recipient rolled off earlier then anticipated. The sub recipient plans to reassign these duties to existing resources which will result in overall lower spend for this milestone. | 98 | Baseline target is 100%. The revised project schedule set a target of 99%. The EA is complete and a FONSI received. The remaining funds may be used for EA work associated with pending and future route change requests. | 81 | Baseline target is 100%. The revised project schedule set a target of 98%. All design work for the fiber routes are complete and paid. The sub recipient anticipates completing the design work for wireless towers and inside plant at the end of next quarter, although some of the payments may lag into the following quarter. Any additional spend for this category will be associated with routes changes. | 83 | Baseline target is 100%. The revised project schedule set a target of 97%. 90% of the permits and easements have been secured. Projected cumulative spend for next quarter is $890,796 of $1,076,929. CMS estimates the final costs will be about 10% ($100k) below the budgeted amount. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 20 | Baseline target is 61%. The revised project schedule set a target of 37%. CMS anticipated completing inside plant work for 25 CAIs by this point in the project. The time required to finalize the scope of work, secure vendor quotes, place orders, receive materials and complete the work is taking longer then anticipated. CMS has started placing orders; however, we do not anticipate payments for inside plant work to start until Y3Q2. | 71 | Baseline target is 46%. The revised project schedule set a target of 78%. CMS has purchased and installed about 80% of the optical, switching and routing equipment. We had planned to purchase the remaining 3 optical switches in this quarter but are holding off while we evaluate the feasibility of upgrading the equipment from 40G to 100G. Overall, equipment costs are less then budgeted. The sub recipient anticipates awarding bids for generators, wireless equipment, servers, racks and fiber panels in this quarter but invoices will carry over to the following quarter. | 40 | Baseline target is 75%. The revised project schedule set a target of 48%. The revised project schedule anticipated spending an additional $1.1M for fiber leases and $4M for construction. One of the leases is executed and payment is pending fiber acceptance. Bids have been accepted for three additional leases and contracts are in negotiations. The remaining lease will be with another governmental entity and is in contract review. Construction spending for next quarter will be less then anticipated as work on 3 routes started late. The run rate for these routes will not have reached the forecasted level. Additionally constructions costs are coming in below budget. | 5 | Baseline target is 75%. The revised project schedule set a target of 18%. $600,000 is budgeted to this milestone for fiber characterization by the optical equipment vendor. CMS is waiting to take receipt of a 3 mile leased fiber path from the owner at which time the optical vendor will be deployed to complete the work. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2012-08-17 17:46 | 2012-08-17 17:46 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2012 | Q3 | Q3 - 2012 | 7930 | 6669 | FALSE | 64 | Baseline target is 81%. The revised project schedule set a target of 70%.The forecast for next quarter is $6.4M less then the revised forecast as a result of delays starting construction, construction costs coming in below budget, and delays starting inside plant. | 69 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 62%. The revised project schedule set a target of 70%. The public relations contractual resource working for the sub recipient rolled off earlier then anticipated. The sub recipient plans to reassign these duties to existing resources which will result in overall lower spend for this milestone. | 100 | Baseline target is 100%. The revised project schedule set a target of 99%. The EA is complete and a FONSI received. CMS will have additional costs for EA work associated with a pending route change, if approved. | 81 | Baseline target is 100%. The revised project schedule set a target of 98%. All design work for the fiber routes are complete and paid. The sub recipient anticipates design work for inside plant will continue through the first quarter of 2013. CMS will have additional costs for design work associated with a pending route change, if approved. | 100 | Baseline target is 100%. The revised project schedule set a target of 97%. 95% of the permits have been secured. CMS is forecasting to spend more then originally budgeted for this milestone due to permitting work associated with route changes and higher then anticipated permit fees from railroads. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 44 | Baseline target is 80%. The revised project schedule set a target of 73%. CMS anticipated completing inside plant work for 50% of CMS' CAIs by this point in the project (new target is 30%). The time required to finalize the scope of work, secure vendor quotes, place orders, receive materials and complete the work is taking longer then anticipated. Inside plant work has started and will continue through the remainder of the project. | 71 | Baseline target is 46%. The revised project schedule set a target of 90%. CMS has purchased and installed about 80% of the optical, switching and routing equipment. CMS had planned to purchase the remaining 3 optical switches by now but are holding off while we evaluate the feasibility of upgrading the equipment from 40G to 100G. Overall, equipment costs are less then budgeted. The sub recipient anticipates ordering wireless equipment and generators in this quarter but invoices will carry over to the following quarter. | 62 | Baseline target is 85%. The revised project schedule set a target of 64%. Construction spending for next quarter is approximately $1.7M below the revised target. The difference is partially attributable to delayed starts with several routes, but mainly a result of lower then budgeted construction costs for the early fiber routes. As of the end of September, 76% of the conduit is complete and 30% of the fiber which puts the project on schedule to be completed by the grant deadline. | 6 | Baseline target is 90%. The revised project schedule set a target of 28%. $600,000 of the $699,000 budgeted to this milestone is for fiber characterization by the optical equipment vendor. CMS is waiting to take receipt of a 3 mile leased fiber path from the owner at which time the optical vendor will be deployed to complete the work. In the meantime, CMS is in process of purchasing the tools to perform this work internally. Depending on timing, CMS may not require the services of the optical equipment vendor. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2012-11-16 15:39 | 2012-11-16 15:39 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2012 | Q4 | Q4 - 2012 | 9056 | 7831 | FALSE | 72 | Baseline target is 81%. The difference between the Baseline and the PPR projection is approximately $22 million which is a result of costs coming in below budget for construction and delays early in the project starting construction, inside plant and final equipment purchases. | 78 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 81%. The public relations contractual resource working for the sub recipient rolled off earlier then anticipated. The sub recipient has reassigned these duties to existing resources which will result in overall lower spend for this milestone. | 100 | Baseline target is 100%. The EA is complete and a FONSI received. CMS will have additional costs for EA work associated with a recently approved route change and a pending route exapansion, if approved. | 88 | Baseline target is 100%. All design work for the fiber routes is complete and paid. The sub recipient has completed the design work for wireless towers and inside plant but has not yet received all the invoices. Any additional spend for this category will be associated with routes changes. | 83 | Baseline target is 100%. CMS has secured 99% of the permits. Additional charges will be associated with permit preparation/fees for the pending route changes. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 62 | Baseline target is 100%. Inside plant work started later then originally planned but is underway and making good progress. This milestone category included $1.5M for network node space contributed by CAI participants. The space value will be reduced due to the timing the space was put into service. The project will make up the difference for the in kind contribution within the Other milestone category. The sub recipient is completing a third party assessment to validate the value of the space. | 78 | Baseline target is 100%. CMS has purchased and installed about 86% of the optical, switching and routing equipment. The sub recipient has ordered the wireless equipment and generators in this quarter but invoices will carry over to the following quarter. | 71 | Baseline target is 95%. Construction activities started later then expected. Costs of the early routes have been lower then budgeted. By the end of the quarter CMS is forecasting to have 75% of the fiber installed. | 7 | Baseline target is 100%. The money budgeted to this milestone is for fiber characterization by the optical equipment vendor. CMS is in process of purchasing the tools to perform this work internally. CMS anticipates that the remaining money budgeted for Equipment Deployment will be reallocated to other expenses. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2013-02-28 11:04 | 2013-02-28 11:04 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2013 | Q1 | Q1 - 2013 | 10008 | 8548 | FALSE | 80 | Baseline target is 100%. The difference between the Baseline and the PPR projection is approximately $19M which is a result of costs coming in below budget for construction and delays early in the project starting construction, inside plant and final equipment purchases. CMS has received approval to add additional routes and will be working on those routes/CAIs through the remainder of the project. | 59 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 100%. The original projections included ineligible expenses associated with fiber maintenance costs. Final spend will be less than originally budgeted. | 100 | Actual spend is 120% due to higher engineering costs required to complete the EA. | 90 | Baseline target is 100%. All design work for the original scope is complete and paid. Any additional spend for this category will be associated with design work for the recently approved route changes. | 100 | Actual spend is 107% due to higher engineering costs required to complete permits. Additional charges will be associated with permit preparation/fees for the recently approved route changes. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 52 | Baseline target is 100%. Fifty percent of the money budgeted to this milestone category is for an in kind match of network node space contributed by CAI participants. The space value will be reduced due to the timing the space was put into service. The project will make up the difference for the in kind contribution within the Other milestone category. | 95 | Baseline target is 100%. CMS will have additional spend for customer premise equipment associated with recently approved route changes/CAI additions; however, we anticipate final costs will be less than budgeted. | 84 | Baseline target is 100%. By the end of the quarter CMS is forecasting to have 99% of the fiber installed; however, vendor payments will continue into the third quarter of 2013. CMS will be requesting an extension to complete the recently approved Chicago reroute and to continue with the approved expansion routes/CAIs. | 3 | Baseline target is 100%. CMS is using in house staff to deploy equipment and does not anticipate any additional spend in this category. The money is being reallocated to other expenses. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2013-05-30 13:24 | 2013-05-30 13:24 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2013 | Q2 | Q2 - 2013 | 10822 | 9083 | FALSE | 95 | Baseline target is 100%. CMS has completed 99% of the construction at the start of the quarter. CMS will complete the remaining scope plus several miles of expansion routes by the end of the quarter. CMS anticipates that some of the construction activity will continue through late September pushing payment of final invoices into the close out period. | 79 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 100%. The original projections included ineligible expenses associated with fiber maintenance costs. Final spend will be less than originally budgeted. The remaining funds will be spend in the other milestone categories where expenses have been higher than originally forecasted. | 100 | Actual spend is 123% due to higher engineering costs required to complete the EA. | 100 | Actual spend is 102% as result of design work for route changes and expansion routes. | 100 | Actual spend is 124% due to higher engineering costs required to compelte permits for original scope as well as the additional work for route changes and expansion routes. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 73 | Baseline target is 100%. CMS will not spend the amount originally budgeted for Site Preparation. The remaining funds will be spend in the other milestone categories where expenses have been higher than originally forecasted. | 97 | Baseline target is 100%. CMS anticipates a few final invoices received at the end of the quarter which will push the payments into the close out period. | 97 | Baseline target is 100%. CMS anticipates that some of the construction activity will continue through late September pushing payment of final invoices into the close out period. | 3 | Baseline target is 100%. CMS is using in house staff to deploy equipment and does not anticipate any additional spend in this category. The money is being reallocated to other expenses. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2013-08-30 14:13 | 2013-08-30 14:13 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2013 | Q3 | Q3 - 2013 | 11390 | 9503 | FALSE | 99 | Baseline target is 100%. The remaining funds are budgeted for eligible close out expenses that will be incurred after December 2013. | 86 | Professional Services such as Project Management, Web Design, Project Engineer | Baseline target is 100%. The original projections included ineligible expenses associated with fiber maintenance costs. Final spend will be less than originally budgeted. The remaining funds will be spent in other milestone categories where expenses have been higher than originally forecasted. | 100 | Final spend is forecasted to be 123% due to higher engineering costs required to complete the EA. | 100 | Final spend is forecasted to be 102% as result of design work for route changes and expansion routes. | 100 | Final spend is forecasted to be 129% due to higher engineering costs required for permits. | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 60 | Baseline target is 100%. CMS will not spend the amount originally budgeted for Site Preparation. The remaining funds will be spent in the other milestone categories where expenses have been higher than originally forecasted. | 100 | Final spend is forecasted to be 135% due to upgrading some of the optical equipment from 40G to 100G. | 97 | Baseline target is 100%. Final spend is forecasted to be 97% due to overall lower than originally budgeted construction costs. The remaining funds will be spent in other milestone categories where expenses have been higher than originally forecasted. | 3 | Baseline target is 100%. CMS is using in house staff to deploy equipment and will not have additional spend in this category. The money is being reallocated to other expenses. | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2013-11-26 13:16 | 2013-11-26 13:16 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | 2013 | Q4 | Q4 - 2013 | 12468 | 10647 | FALSE | 100 | None | 100 | Professional Services such as Project Management, Web Design, Project Engineer | None | 100 | None | 100 | None | 100 | None | 0 | NA - CMS has no spend mapped to this milestone. These expenditures are included in 2h Network Build. | 100 | None | 100 | None | 100 | None | 100 | None | 0 | NA - CMS has no spend mapped to this milestone. CMS is using existing staff not charged to project plus contractual resources reported in 2k Other. | 2014-08-28 17:24 | 2014-08-28 17:24 | 6095 | 6095 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570109 | 2010 | Q4 | Q4 - 2010 | 984 | 2027 | FALSE | 3 | N/A | 0 |  | N/A | 100 | N/A | 50 | N/A | 100 | N/A | 50 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-04 17:15 | 2011-02-04 17:15 | 6173 | 6173 | Carver, County of | TRUE
NT10BIX5570109 | 2011 | Q1 | Q1 - 2011 | 1958 | 2724 | FALSE | 8 | N/A |  |  |  | 100 | N/A | 100 | N/A | 100 | N/A | 75 | N/A | 0 | N/A | 0 | N/A | 4 | N/A | 0 | N/A | 0 | N/A | 2011-05-12 07:57 | 2011-05-12 07:57 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2011 | Q2 | Q2 - 2011 | 3382 | 3454 | FALSE | 20 | We will be adding construction crews to the project in efforts to regain lost progress from the previous quarters. We will also be working further into the fourth quarter fall/winter construction season, as weather permits, to regain lost progress. | 0 |  | N/A | 100 | No variance from baseline as this task was completed in the current quarter. | 100 | No variance from baseline. We look to meet this completion percentage by adding engineering resources to the project to regain lost progress from the previous quarter. | 100 | No variance from baseline. We look to meet this completion percentage once we receive final sign off of our EA addendum in this next quarter. | 100 | No variance from baseline. We look to meet this completion percentage by adding engineering resources, which will finalize network design, allowing for permitting to be completed. | 25 | No variance from baseline. We look to meet this completion percentage by beginning initial groundwork for the construction of our first fiber hut. | 0 | No variance from baseline and we are not anticipating making efforts in this category during this next quarter. | 0 | With fiber scheduled for delivery in the 4th quarter of 2011, we are currently working to install conduit and once fiber arrives, we will regain lost progress of our network build by blowing in fiber and splicing after the conduit is in place. | 0 | No variance from baseline and we are not anticipating making efforts in this category during this next quarter. | 0 | No variance from baseline and we are not anticipating making efforts in this category during this next quarter. | 2011-08-30 15:07 | 2011-08-30 15:07 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2011 | Q3 | Q3 - 2011 | 3912 | 3794 | FALSE | 64 | No variance from baseline |  |  | N/A | 100 | No variance from baseline | 50 | Our network design is at 50%, which is less than our originally stated 100%. This lower percentage was created by conversations with our community anchor institutions (CAI's) and other interested parties. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. This change has allowed us time to discuss additional connections that CAI's and other interested parties are requesting outside of the original project scope and budget. Based on these discussions we are holding our network design finalization until the spring of 2012, which is when we will be able to begin construction again after the winter. At that time we will finalize our network design to best accommodate any additional outside the original project scope connections in which CAI's would pay for out of their own non ARRA funds. | 100 | No variance from baseline | 75 | Our construction permits and other approvals is at 75%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Many of the required permits for these locations have limited timeframes in which the defined work is able to be competed. So instead, we will be obtaining the remainder of the permits in the spring and summer of 2012 as we are closer to the time in which we will actually be constructing to those locations. | 0 | Our site preparation is at 0%, which is less than our originally stated 50%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the site preparation for our huts will not be needed until the spring/summer of 2012. As such, we will not be doing any site preparation until that time so that we can accommodate any increase in hut size that may be needed from potential out of scope project expansion discussions that may take place over the winter months. | 20 | No variance from baseline | 0 | Our network build is at 0%, which is less than our originally stated 60%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, we will not be completing final network build until the end of the project, at which time we would promptly be at 100%. | 0 | Our equipment deployment is at 0%, which is less than our originally stated 20%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the equipment deployment will not be needed until the spring/summer of 2012. As such, we will not be doing any equipment deployment until that time. | 0 | No variance from baseline | 2011-11-07 16:10 | 2011-11-07 16:10 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2011 | Q4 | Q4 - 2011 | 4980 | 4654 | FALSE | 60 | Our overall project is at 60%, which is less than our originally stated 63%. This lower percentage is based on our anticipation of not receiving the final shipments of our fiber until April of 2012, at which time the expenditures will be reported. | 0 |  | N/A | 100 | No variance from baseline | 50 | Our network design is at 50%, which is less than our originally stated 100%. This lower percentage was created by conversations with our community anchor institutions (CAI's) and other interested parties. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. This change has allowed us time to discuss additional connections that CAI's and other interested parties are requesting outside of the original project scope and budget. Based on these discussions we are holding our network design finalization until the spring of 2012, which is when we will be able to begin construction again after the winter. At that time we will finalize our network design to best accommodate any additional outside the original project scope connections in which CAI's would pay for out of their own non ARRA funds. | 100 | No variance from baseline | 75 | Our construction permits and other approvals is at 75%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Many of the required permits for these locations have limited timeframes in which the defined work is able to be competed. So instead, we will be obtaining the remainder of the permits in the spring and summer of 2012 as we are closer to the time in which we will actually be constructing to those locations. | 0 | Our site preparation is at 0%, which is less than our originally stated 75%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the site preparation for our huts will not be needed until the spring/summer of 2012. As such, we will not be doing any site preparation until that time so that we can accommodate any increase in hut size that may be needed from potential out of scope project expansion discussions that may take place over the winter months. | 40 | No variance from baseline | 0 | Our network build is at 0%, which is less than our originally stated 60%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, we will not be completing final network build until the end of the project, at which time we would promptly be at 100%. | 0 | Our equipment deployment is at 0%, which is less than our originally stated 40%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the equipment deployment will not be needed until the spring/summer of 2012. As such, we will not be doing any equipment deployment until that time. | 0 | No variance from baseline | 2012-02-13 15:12 | 2012-02-13 15:12 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2012 | Q1 | Q1 - 2012 | 6266 | 5735 | FALSE | 74 | No variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 85 | Our construction permits and other approvals is at 85%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Many of the required permits for these locations have limited timeframes in which the defined work is able to be competed. So instead, we will be obtaining the remainder of the permits in the spring and summer of 2012 as we are closer to the time in which we will actually be constructing to those locations. | 50 | Our site preparation is at 50%, which is less than our originally stated 100%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the site preparation for our huts will not be needed until the spring/summer of 2012. As such, we will not be doing any site preparation until that time so that we can accommodate any increase in hut size that may be needed from potential out of scope project expansion discussions that may take place over the winter months. | 60 | No variance from baseline | 0 | Our equipment deployment is at 0%, which is less than our originally stated 68%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the equipment deployment will not be needed until the spring/summer of 2012. As such, we will not be doing any equipment deployment until that time. | 0 | Our equipment deployment is at 0%, which is less than our originally stated 60%. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We will now be installing fiber to our lateral locations in the spring and summer of 2012. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, the equipment deployment will not be needed until the spring/summer of 2012. As such, we will not be doing any equipment deployment until that time. | 0 | No variance from baseline | 2012-05-23 13:51 | 2012-05-23 13:51 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2012 | Q2 | Q2 - 2012 | 7270 | 6262 | FALSE | 86 | Our overall project is at 86%, which is less than our originally stated 90%. Based on our equipment procurement not taking place until late summer, the expense for equipment will not be fully incurred until 4th quarter 2012. | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 80 | No variance from baseline | 84 | No variance from baseline | 80 | No variance from baseline | 0 | No variance from baseline | 2012-08-28 17:17 | 2012-08-28 17:17 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2012 | Q3 | Q3 - 2012 | 8012 | 6712 | FALSE | 90 | Our overall project is at 90%, which is less than our originally stated 99%. This is created by our equipment procurement not taking place until this quarter and the finalizing of the network build out so that we can pay our construction retainage. | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 94 | No variance from baseline | 90 | Our overall project is at 90%, which is less than our originally stated 100%. This is created by our equipment procurement not taking place until this quarter. | 0 | No variance from baseline | 2012-11-21 10:52 | 2012-11-21 10:52 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2012 | Q4 | Q4 - 2012 | 9082 | 7855 | FALSE | 96 | Our overall project is at 96%, which is less than our originally stated 99%. This is created by our equipment procurement not taking place until this quarter and the finalizing of the network build out so that we can pay our construction retainage. | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 31 | Our equipment procurement is at 31%, which is less than our originally stated 100%. This lower percentage was created based on our implementation of a design build approach to our network and equipment planning bid. The equipment will be arriving late this quarter and billing is not anticipated to be received until next quarter when the expenditure will be realized. | 100 | No variance from baseline | 90 | Our overall project is at 90%, which is less than our originally stated 100%. This is created by our equipment procurement not taking place until this quarter. | 50 | No variance from baseline | 2013-02-28 14:29 | 2013-02-28 14:29 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2013 | Q1 | Q1 - 2013 | 9298 | 8102 | FALSE | 100 | No variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2013-04-26 16:28 | 2013-04-26 16:28 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2013 | Q2 | Q2 - 2013 | 10752 | 9041 | FALSE | 100 | No variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2013-08-27 09:46 | 2013-08-27 09:46 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570109 | 2013 | Q3 | Q3 - 2013 | 11602 | 9729 | FALSE | 100 | No variance from baseline | 0 |  | N/A | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 100 | No variance from baseline | 2014-01-14 10:43 | 2014-01-14 10:43 | 7020 | 7020 | Carver, County of | TRUE
NT10BIX5570111 | 2010 | Q4 | Q4 - 2010 | 758 | 1792 | FALSE | 2 | Based on anticipation of the Environmental Assessment being completed and progress in the permitting area, Northwest Open Access Network will be closer to 2% complete with the Overall Project Milestone. | 0 | N/A | N/A | 100 | N/A | 35 | N/A | 15 | N/A | 5 | N/A | 5 | N/A | 10 | Equipment expenditures will more than likely fall into the following quarter, therefore not reflected in this baseline milestone. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-01-28 14:07 | 2011-01-28 14:07 | 5529 | 5529 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2011 | Q1 | Q1 - 2011 | 2000 | 2745 | FALSE | 1 | Expenditures do not meet the anticipated Baseline, since the original forecast included equipment purchases during the early stages of the project. Timeline delays due to finalizing the project budget with the NTIA Program Office has pushed back execution of sub recipient agreements and equipment purchases to better align with plant construction timelines. NoaNet will manage completion of the overall project metrics by increasing resources in the compressed schedule. | 0 | N/A | N/A | 100 | No variance. | 45 | No variance. | 20 | Initial variance to milestone will gradually dissipate as the project progresses. Initial delays in the project caused the milestone to be short of anticipated projections. The project is expected to meet this milestone by end of year two of the project by adding additional resources to the task. | 20 | It is anticipated permitting will achieve the anticipated project timeline included in the baseline by the end of 2011. As stated above, initial delays caused permitting to lag initial projections. Additional resources will be deployed to close the gap by end 2011. | 5 | Site preparation varies from the baseline as the project awaits the receipt of the FONSI (Finding of No Significant Impact). Original projections anticipated this metric to be further along, once again, additional resources will be deployed to gain ground by end of year two of the project timeline. | 10 | Equipment procurement initially planned will be delayed due to initial delays in acceptance of the award. We anticipate this milestone to be attained late in 2011. | 0 | No variance. | 0 | Equipment will not be deployed until the third or fourth quarter. We anticipate reaching our baseline projection by end of 2011. | 0 | No variance. | 2011-05-13 09:27 | 2011-05-13 09:27 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2011 | Q2 | Q2 - 2011 | 2586 | 3041 | FALSE | 20 | When the anticipated approval of the In Kind Asset for Land and Equipment is received, the overall progress of the project will surpass the Baseline projections. | 0 | NA | NA | 100 | No variance. | 60 | No variance. | 25 | Rights of Way will lag an aggressive Baseline projection well into this year. Anticipation was that the Environmental process would not take as much time and the process would have began sooner. | 30 | See comment above in reference to permitting. | 20 | Site preparation is scheduled to start in this quarter with an accelerated timeline. Completion of this particular milestone will fall into the final year of the project and may not attain the Baseline projection until final completion. | 75 | Approval of In Kind assets will drive this metric beyond the original Baseline projections. Assets booked to the project and implemented into the Network will be attributable towards the build. | 0 | Earlier Baseline projections had Network Build starting in the first quarter of year two of the project. However, as a result of the longer than anticipated Environmental process, this metric will not start until the following quarter. | 75 | As In Kind Assets are allowable to the Project, Equipment in place will be deployed. | 0 | Network testing will follow the Network Build Metric once that portion of the Project is started. It is anticipated that this metric will attain the Baseline projection by end of year two of the Project. | 2011-07-28 11:02 | 2011-07-28 11:02 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2011 | Q3 | Q3 - 2011 | 4220 | 3958 | FALSE | 21 | With the addition of In Kind assets to the project, the gap in actual to Baseline has shortened, bringing the milestone closer to projection. NoaNet will exercise all available resources to complete the project as outlined in the Broadband Technologies Opportunity Program guidelines. Over 67% of the project budget is in the Construction Category of which has not begun. Spending 1% or $7,799,890 ($650,000 weekly) in one quarter at this stage of the project is difficult to reach. Non ground disturbing activities account for the majority of the work being completed on the project until FONSI is received. It is anticipated that we will be ready to proceed and expenditures will escalate into 2012. | 0 |  | N/A | 100 | No Variance. | 75 | No Variance. | 35 | Rights of Way acquisition will lag Baseline projections into next calendar year as the environmental approval process has taken longer than planned. Additional resources will be utilized to bring this metric in line with projections during the end of quarter two 2012. | 40 | Permitting will follow the right of way process and lag baseline into year three of the project. Permitting will meet baseline by end of quarter two year 2012. Once again, additional resources will be deployed to expedite the process. | 20 | Site preparation is well underway in what we see as an accelerated rate to make up some of the lag in the Baseline projection and an expedited construction schedule. Anticipation is to bring this metric in line with Baseline by the end of quarter three in 2012. | 40 | In Kind asset approval was received and the majority of it has been attributed toward this project last quarter, as this metric is making some gap closure as we end the second year of the project life cycle. Equipment procurement has been delayed to coincide with construction of routes and anticipated to proceed during the second quarter of 2012 to coincide with the start of construction. | 0 | Earlier Baseline projections had the Network Build starting in the first quarter of year two of the project. With the longer than anticipated environmental process and ultimate construction start, this metric will lag baseline well into the final year of the project. This metric will be met by the end of quarter three 2012. | 0 | With approval of the Environmental Assessment and construction activity taking place, equipment will be deployed during the fiber placement phase. This will mirror the Network Build schedule and attain the Baseline projection by end of quarter three 2012. | 0 | Network testing will follow the network build metric once that portion of the Project is started. It is anticipated that this metric will attain the Baseline projection by the end of quarter three 2012. A compressed schedule will allow this to be completed as required. | 2011-11-22 14:42 | 2011-11-22 14:42 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2011 | Q4 | Q4 - 2011 | 5396 | 5079 | FALSE | 22 | With the addition of In Kind assets to the project, the gap in actual to Baseline has shortened, bringing the milestone closer to projection. NoaNet will exercise all available resources to complete the project as outlined in the Broadband Technologies Opportunity Program guidelines. Over 67% of the project budget is in the Construction Category of which has not begun. It is anticipated that we will be ready to proceed and expenditures will escalate in 2012 in order to meet the projected metrics by the end of Q4 2012. | 0 |  | N/A | 100 | Meeting Baseline projection. | 85 | No Variance. | 65 | Rights of Way acquisition will lag Baseline projections into next calendar year as the environmental approval process has taken longer than planned. Additional resources will be utilized to bring this metric in line with projections during the end of quarter two 2012. | 65 | Permitting will follow the right of way process and lag baseline into year three of the project. Permitting will meet baseline by end of quarter two year 2012. Once again, additional resources will be deployed to expedite the process. | 35 | Site preparation is well underway in what we see as an accelerated rate to make up some of the lag in the Baseline projection and an expedited construction schedule. Anticipation is to bring this metric in line with Baseline by the end of quarter three in 2012. | 26 | The majority of In Kind equipment has been attributed toward this project in previous quarters, as this metric is making some gap closure as we end the second year of the project life cycle. Equipment procurement has been delayed to coincide with construction of routes and anticipated to proceed during the second quarter of 2012 to coincide with the start of construction. | 5 | Earlier Baseline projections had the Network Build starting in the first quarter of year two of the project. With the longer than anticipated environmental process and ultimate construction start, this metric will lag baseline well into the final year of the project. This metric will be met by the end of quarter three 2012. | 0 | With approval of the Environmental Assessment and construction activity taking place, equipment will be deployed during the fiber placement phase. This will mirror the Network Build schedule and attain the Baseline projection by end of quarter three 2012. | 0 | Network testing will follow the network build metric once that portion of the Project is started. It is anticipated that this metric will attain the Baseline projection by the end of quarter three 2012. A compressed schedule will allow this to be completed as required. | 2012-02-29 13:19 | 2012-02-29 13:19 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2012 | Q1 | Q1 - 2012 | 6016 | 5607 | FALSE | 23 | With the two categories of construction and equipment accounting for 87% of the budget it is difficult to see significant progress in this metric until construction begins and equipment specifications are completed for bidding and eventual purchase. This metric will start to see significant gain as we continue on to the construction phase of the project. It is projected to meet our baseline metric at the end of Q2 2013. | 0 |  | N/A | 100 | No variance. | 90 | No variance. | 65 | Rights of Way acquisition will lag Baseline projections into next calendar year as the environmental approval process has taken longer than planned. Additional resources will be utilized to bring this metric in line with projections during the end of quarter two 2012. | 65 | Permitting will follow the right of way process and lag baseline into year three of the project. Permitting will meet baseline by end of quarter two year 2012. Once again, additional resources will be deployed to expedite the process. | 45 | Site preparation is well underway in what we see as an accelerated rate to make up some of the lag in the Baseline projection and an expedited construction schedule. Anticipation is to bring this metric in line with Baseline by the end of quarter three in 2012. | 26 | The majority of In Kind equipment has been attributed toward this project in previous quarters, as this metric is making some gap closure as we end the second year of the project life cycle. Equipment procurement has been delayed to coincide with construction of routes and anticipated to proceed during the third and fourth quarters of 2012 to coincide with the start of construction. We anticipate meeting our baseline projections at the end of Q1 2013. | 5 | Earlier Baseline projections had the Network Build starting in the first quarter of year two of the project. With the longer than anticipated environmental process and ultimate construction start, this metric will lag baseline well into the final year of the project. This metric will be met by the end of quarter three 2012. | 10 | With approval of the Environmental Assessment and construction activity taking place, equipment will be deployed during the fiber placement phase. This will mirror the Network Build schedule and attain the Baseline projection by end of quarter three 2012. | 0 | Network testing will follow the network build metric once that portion of the Project is started. It is anticipated that this metric will attain the Baseline projection by the end of quarter three 2012. A compressed schedule will allow this to be completed as required. | 2012-05-10 14:01 | 2012-05-10 14:01 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2012 | Q2 | Q2 - 2012 | 6610 | 5922 | FALSE | 32 | With the two categories of construction and equipment accounting for 87% of the budget it is difficult to see significant progress in this metric until construction begins and equipment specifications are completed for bidding and eventual purchase. This metric will start to see significant gain as we continue on in the construction phase of the project. It is projected to meet our baseline metric at the end of Q2 2013. | 0 |  | N/A | 100 | No Variance. | 90 | Network design is nearing completion with final adjustments taking place in Q4 2012. | 70 | Rights of Way acquisition will lag Baseline projections into next calendar year as the environmental approval process has taken longer than planned. Additional resources will be utilized to bring this metric in line with projections during the end of Q1 2013. | 65 | Permitting will follow the right of way process and lag baseline into year three of the project. Permitting will meet baseline by end of quarter four of year 2012. Once again, additional resources will be deployed to expedite the process. | 60 | Site preparation is well underway in what we see as an accelerated rate to make up some of the lag in the Baseline projection and an expedited construction schedule. Anticipation is to bring this metric in line with Baseline by the end of quarter one in 2013. | 32 | The majority of In Kind equipment has been attributed toward this project in previous quarters, as this metric is making some gap closure as we end the second year of the project life cycle. Equipment procurement has been delayed to coincide with construction of routes and anticipated to proceed during the third and fourth quarters of 2012 to coincide with the start of construction. We anticipate meeting our baseline projections at the end of Q1 2013. | 10 | Earlier Baseline projections had the Network Build starting in the first quarter of year two of the project. With the longer than anticipated environmental process and ultimate construction start, this metric will lag baseline well into the final year of the project. This metric will be met by the end of quarter one 2013. | 32 | With approval of the Environmental Assessment and construction activity taking place, equipment will be deployed during the fiber placement phase. This will mirror the Network Build schedule and attain the Baseline projection by end of quarter one 2013. | 0 | Network testing will follow the network build metric once that portion of the Project is started. It is anticipated that this metric will attain the Baseline projection by the end of quarter two 2013. A compressed schedule will allow this to be completed as required. | 2012-07-30 11:43 | 2012-07-30 11:43 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2012 | Q3 | Q3 - 2012 | 7928 | 6668 | FALSE | 50 | With the two categories of construction and equipment accounting for 87% of the budget it is difficult to see significant progress in this metric until construction begins and equipment specifications are completed for bidding and eventual purchase. This metric will start to see significant gain as we continue on in the construction phase of the project. It is projected to meet our baseline metric at the end of Q2 2013. | 0 |  | N/A | 100 | No Variance. | 95 | No Variance. | 80 | Rights of Way acquisition will lag Baseline projections into next calendar year as the environmental approval process has taken longer than planned. Additional resources will be utilized to bring this metric in line with projections during the end of Q1 2013. | 75 | Permitting will follow the right of way process and lag baseline into year three of the project. Permitting will meet baseline by end of quarter four of year 2012. Once again, additional resources will be deployed to expedite the process. | 80 | Site preparation is well underway in what we see as an accelerated rate to make up some of the lag in the Baseline projection and an expedited construction schedule. Anticipation is to bring this metric in line with Baseline by the end of quarter one in 2013. | 62 | The majority of In Kind equipment has been attributed toward this project in previous quarters, as this metric is making some gap closure as we end the second year of the project life cycle. Equipment procurement has been delayed to coincide with construction of routes and anticipated to proceed during the third and fourth quarters of 2012 to coincide with the start of construction. We anticipate meeting our baseline projections at the end of Q1 2013. | 34 | Earlier Baseline projections had the Network Build starting in the first quarter of year two of the project. With the longer than anticipated environmental process and ultimate construction start, this metric will lag baseline well into the final year of the project. This metric will be met by the end of quarter one 2013. | 55 | With approval of the Environmental Assessment and construction activity taking place, equipment will be deployed during the fiber placement phase. This will mirror the Network Build schedule and attain the Baseline projection by end of quarter one 2013. | 20 | Network testing will follow the network build metric once that portion of the Project is started. It is anticipated that this metric will attain the Baseline projection by the end of quarter two 2013. A compressed schedule will allow this to be completed as required. | 2012-11-16 14:41 | 2012-11-16 14:41 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2012 | Q4 | Q4 - 2012 | 8796 | 7592 | FALSE | 71 | With the two categories of construction and equipment accounting for 87% of the budget, WE WILL SEE A LARGE INCREASE IN THE METRIC AS CONSTRUCTION IS IN FULL OPERATION AND EQUIPMENT PURCHASES ARE BEING COMPLETED. WITH THE TWO METRICS ABOVE EXPENDING LARGER AMOUNTS OF ITS BUDGET, DOUBLE DIGIT INCREASES WILL NOT BE UNCOMMON FOR THIS METRIC. It is projected to meet our baseline metric at the end of Q2 2013. | 0 | N/A | N/A | 100 | No Variance. | 100 | No Variance. | 90 | Rights of Way are still in process of being secured for some routes and will be forecasted to be complete by Q2 2013. | 85 | A minimal number of permits will need to be obtained going into the final quarter of the project timeline. This metric will be met at the end of Q2 2013. | 90 | Site preparation is well underway in what we see as an accelerated rate to make up some of the lag in the Baseline projection and an expedited construction schedule. Anticipation is to bring this metric in line with Baseline by the end of quarter two in 2013. | 64 | The majority of In Kind equipment has been attributed toward this project in previous quarters, as this metric is making some gap closure as we end the second year of the project life cycle. Equipment procurement has been delayed to coincide with construction of routes and anticipated to proceed during the third and fourth quarters of 2012 to coincide with the start of construction. We anticipate meeting our baseline projections at the end of Q2 2013. | 38 | Earlier Baseline projections had the Network Build starting in the first quarter of year two of the project. With the longer than anticipated environmental process and ultimate construction start, this metric will lag baseline well into the final year of the project. This metric will be met by the end of quarter two 2013. | 55 | With approval of the Environmental Assessment and construction activity taking place, equipment will be deployed during the fiber placement phase. This will mirror the Network Build schedule and attain the Baseline projection by end of quarter two 2013. | 50 | Network testing will follow the network build metric now that construction of routes has started. It is anticipated that this metric will attain the Baseline projection by the end of quarter two 2013. A compressed schedule will allow this to be completed as required. | 2013-02-14 23:15 | 2013-02-14 23:15 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2013 | Q1 | Q1 - 2013 | 9910 | 8496 | FALSE | 70 | With the two categories of construction and equipment accounting for 87% of the budget, we will continue to see a large increase in the metric as construction is in full operation and equipment purchases are being completed. With the two metrics above expending larger amounts of it's budget,double digit increases will not be uncommon for this metric. It is projected to meet our baseline metric during the final quarter of the project. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 95 | Site preparation will continue into July, the final month of the project, as some remaining work will be needed on the routes finishing up that month. | 51 | With the In Kind equipment having been attributed toward this project in previous quarters, this metric will continue to lag into the remaining quarter of the project life cycle. Equipment procurement has been delayed to coincide with construction of routes and anticipated meeting our baseline projections at the end of the project timeframe. | 72 | Earlier Baseline projections had the Network Build starting in the first quarter of year two of the project. With the longer than anticipated environmental process and ultimate construction start, this metric will lag baseline well into the final year of the project. This metric will be met by the end of the project life cycle in July 2013. | 45 | With equipment purchases well underway, equipment will be deployed during the fiber placement phase. This will mirror the Network Build schedule and attain the Baseline projection by end of July 2013. | 55 | Network testing will follow the network build metric now that construction of routes is in full production. It is anticipated that this metric will attain the Baseline projection by the end of July 2013. A compressed schedule will allow this to be completed as required. | 2013-05-24 17:08 | 2013-05-24 17:08 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2013 | Q2 | Q2 - 2013 | 10652 | 8986 | FALSE | 71 | Although construction activities will be completed at the end of the quarter, final invoices will remain to be paid and closeout activities will continue into the final quarter of 2013. | 0 |  | N/A | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 100 | No Variance. | 2013-08-20 11:23 | 2013-08-20 11:23 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570111 | 2013 | Q3 | Q3 - 2013 | 12322 | 10496 | FALSE | 100 | Project is complete. | 0 | N/A | N/A | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 100 | Project is complete. | 2014-07-25 14:45 | 2014-07-25 14:45 | 5528 | 5528 | Northwest Open Access Network | TRUE
NT10BIX5570112 | 2010 | Q4 | Q4 - 2010 | 1198 | 2231 | FALSE | 26 | N/A | 0 |  | N/A | 100 | Complete | 60 | Working with Engineering consultant on Contractor RFP's. | 50 | N/A | 25 | N/A | 10 | N/A | 45 | N/A | 44 | N/A | 45 | N/A | 32 | N/A | 2011-02-17 11:12 | 2011-02-17 11:12 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2011 | Q1 | Q1 - 2011 | 1894 | 2692 | FALSE | 26 | We are behind due to the Environmental Assessment, but do not anticipate any other major project impacts. | 0 |  | N/A | 100 | Complete | 65 | We are currently on target with our project baseline for next quarter. | 45 | The delay in receiving our FONSI has pushed our timeframe back slightly. | 50 | We are currently on target with our project baseline for next quarter. | 15 | The delay in receiving our FONSI has pushed our timeframe back slightly. | 52 | We are currently on target with our project baseline for next quarter for equipment procurement. | 50 | We are currently on target with our project baseline for next quarter for our network build components. | 40 | The variance is due to the delay in receiving our FONSI. | 15 | The delay in receiving our FONSI has pushed our timeframe back slightly. | 2011-05-05 12:38 | 2011-05-05 12:38 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2011 | Q2 | Q2 - 2011 | 3008 | 3261 | FALSE | 32 | We will continue to lag for this quarter due to the delay in starting construction and being able to order equipment needed due to late award of our FONSI as well as the delay in receiving our fiber ordered. We anticipate catching this up in the following quarter to be more in line with our baseline projection. | 0 |  | N/A | 100 | Completed | 70 | We are currently on target with our projected baseline for next quarter. | 50 | We will continue to lag for this quarter due to the delay in starting our project due to the late award of our FONSI. We anticipate catching this up in the following quarter to be more in line with our baseline projection. | 50 | NebraskaLink will continue to lag for this quarter due to the delay in starting our project due to the late award of our FONSI. We anticipate catching this up in the following quarter to be more in line with our baseline projection. | 36 | We are currently on target with our projected baseline for next quarter. | 65 | We are currently on target with our projected baseline for next quarter. | 60 | We anticipate being close to our targeted projection for next quarter. We have experienced weather delays at the start of this quarter. | 45 | We anticipate a delay on this milestone due to the late award of our FONSI and we were not able to purchase enclosures for all or our equipment to be deployed as planned. | 40 | We will continue to lag for this quarter due to the delay in starting our project due to the late award of our FONSI. We anticipate catching this up in the following quarter to be more in line with our baseline projection. | 2011-08-11 08:40 | 2011-08-11 08:40 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2011 | Q3 | Q3 - 2011 | 4134 | 3913 | FALSE | 53 | We expect to be on target with our baseline for next quarter. | 0 |  | N/A | 100 | Completed | 75 | We are currently on target with our baseline for next quarter. We continue to work closely with our Engineering firm to map/ stake our routes. | 80 | We expect to be on target with our baseline for next quarter by working closely with our consultants and state agencies to obtain right of way permits. | 80 | We are working closely with our Engineering Consultant to align this closer with our baseline for 1st quarter 2012. | 36 | We are currently on target with our baseline for next quarter. | 70 | We are currently on target with our baseline for next quarter. | 62 | We expect to be slightly behind target with our baseline for next quarter due to our miles of fiber constructed. | 70 | We anticipate being on target with our baseline for next quarter. | 55 | We anticipate being behind target with our baseline for next quarter due to the our miles of fiber constructed. | 2011-11-18 13:41 | 2011-11-18 13:41 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2011 | Q4 | Q4 - 2011 | 4908 | 4592 | FALSE | 52 | NebraskaLink expects to be behind on this target compared to the baseline plan due to the the winter season. | 0 |  | N/A | 100 | Completed | 80 | NebraskaLink expects to be on target with our baseline plan. | 90 | NebraskaLink expects to be on target with our baseline plan. | 90 | NebraskaLink will continue to work closely with our Engineering Consultant to align this with our baseline plan for next quarter. | 50 | NebraskaLInk is on target with our baseline report for next quarter. | 75 | NebraskaLink is on target with our baseline report for next quarter. | 74 | NebraskaLink expects to be on target with our baseline report for next quarter. | 75 | NebraskaLink expects to be on target with our baseline for next quarter. | 60 | We anticipate being slightly behind with our baseline for the next quarter due to our miles of fiber constructed during the peak winter season. | 2012-02-07 15:28 | 2012-02-07 15:28 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2012 | Q1 | Q1 - 2012 | 5910 | 5554 | FALSE | 60 | NebraskaLink expects to be slightly behind on our overall project due to orders / invoices that we expect will be submitted during mid summer for projects and materials. | 0 |  | N/A | 100 | Completed | 85 | NebraskaLink expects to be on target with our baseline plan. | 90 | NebraskaLInk expects to be close to target with our baseline plan. We have some areas that will only allow us to obtain our permits inside a 60 day window for construction. | 95 | NebraskaLInk expects to be close to target with our baseline report for this milestone. We have some areas that will only allow us to obtain our permits inside a 60 day window for construction. | 76 | NebraskaLink expects to be on target with our baseline plan. | 80 | NebraskaLink expects to be on target with our baseline plan. | 75 | NebraskaLink expects to catch this milestone up in the upcoming quarter which will coincide with a better construction season. | 80 | NebraskaLink expects to be on target with our baseline plan for this milestone. | 70 | NebraskaLink expects to be close to target with our baseline plan for this milestone for the upcoming quarter. | 2012-05-02 12:12 | 2012-05-02 12:12 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2012 | Q2 | Q2 - 2012 | 7222 | 6238 | FALSE | 86 | NebraskaLink expects to be slightly behind the targeted milestone due to invoices that we expect after the end of the quarter for materials to be delivered toward the end of the quarter. | 0 |  | N/A | 100 | Completed | 90 | NebraskaLink expects to be on target with our baseline for this milestone. | 95 | NebraskaLink expects to be close to target with our baseline plan. We have a few areas that will only allow us a brief period prior to construction to obtain necessary permits. | 97 | NebraskaLink expects to be close to target with our baseline plan. Again there are a few areas that will only allow us a 60 day window to obtain permits to construct in their areas. | 95 | NebraskaLink expects to be close to target with our baseline plan. | 87 | NebraskaLink expects to be close to target with our baseline plan. | 93 | NebraskaLink expects to be on target with our baseline plan for this milestone. | 87 | NebraskaLink expects to be close to target with our baseline plan. | 85 | NebraskaLink expects to be slightly behind target on this milestone for the upcoming quarter. | 2012-08-23 12:11 | 2012-08-23 12:11 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2012 | Q3 | Q3 - 2012 | 7898 | 6653 | FALSE | 88 | NebraskaLink expects to be behind on this milestone as compared to our baseline. NebraskaLink is waiting for an approval from BTOP on an award action request for a possible change in routes in some of our project cities. | 0 |  | N/A | 100 | Completed | 95 | NebraskaLink expects to be on target for this milestone. | 100 | NebraskaLink expects to be on target for this milestone. | 100 | NebraskaLink expects to be on target for this milestone. | 97 | NebraskaLink expects to be close to target for this milestone. | 98 | NebraskaLink expects to be close to target with this milestone for equipment procurement - hoping to receive all invoices by close of quarter. | 97 | NebraskaLink expects to be on target for this milestone. | 95 | NebraskaLink expects to be on target for this milestone. | 92 | NebraskaLink expects to be on target for this milestone. | 2012-11-15 15:21 | 2012-11-15 15:21 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2012 | Q4 | Q4 - 2012 | 8680 | 7496 | FALSE | 93 | NebraskaLink expencts to be behind on this milestone as compared to our baseline. NebraskaLink is waiting for an approval from BTOP on an award action request for a possible change in routes in some of our project cities. | 0 |  | N/A | 100 | Completed | 99 | NebraskaLink expects to be close to target with this milestone | 100 | NebraskaLink expects to be on target with this milestone. | 100 | NebraskaLink expects to be on target with this milestone. | 95 | NebraskaLink expects to be behind on this milestone, completing in 2nd quarter 2013. | 89 | NebraskaLink expects to be close to target with this milestone, completing in 2nd quarter 2013. | 98 | NebraskaLink expects to be close to target with this milestone. | 95 | NebraskaLink expects to be closet to target with this milestone, complete in 2nd quarter 2013. | 95 | NebraskaLink expects to be on target with this milestone. | 2013-02-08 13:56 | 2013-02-08 13:56 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2013 | Q1 | Q1 - 2013 | 9354 | 8136 | FALSE | 98 | NebraskaLink expects to be close to completion of this milestone. | 0 |  | N/A | 100 | Completed | 100 | NebraskaLink expects to be completed with this milestone. | 100 | NebraskaLink expects to be completed with this milestone. | 100 | NebraskaLink expects to be completed with this milestone. | 100 | NebraskaLink expects to be completed with this milestone. | 100 | NebraskaLink expects to be completed with this milestone. | 100 | NebraskaLink expects to be completed with this milestone | 100 | NebraskaLink expects to be completed with this milestone | 98 | NebraskaLink expects to be close to completion of this milestone. | 2013-04-29 12:51 | 2013-04-29 12:51 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2013 | Q2 | Q2 - 2013 | 10316 | 8775 | FALSE | 100 | Complete | 0 |  | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-07-30 11:51 | 2013-07-30 11:51 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | 2013 | Q3 | Q3 - 2013 | 11640 | 9761 | FALSE | 100 | Complete | 0 | true | N/A | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2014-01-22 11:41 | 2014-01-22 11:41 | 6001 | 6001 | Nebraskalink, LLC | TRUE
NT10BIX5570113 | 2010 | Q4 | Q4 - 2010 | 1012 | 2057 | FALSE | 1 | No variance from Baseline. | 0 |  | N/A | 100 | No variance from Baseline. | 2 | No variance from Baseline. | 0 | N/A | 54 | No variance from Baseline. | 0 | N/A | 0 | No variance from Baseline. | 1 | No variance from Baseline. | 0 | No variance from Baseline. | 0 | No variance from Baseline. | 2011-02-09 10:09 | 2011-02-09 10:09 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2011 | Q1 | Q1 - 2011 | 2308 | 2899 | FALSE | 1 | Variance from Baseline. The State has proceeded on segments of the project while awaiting the Finding Of No Significant Impact (FONSI) on the Environmental Assessment. Critical segments of the project will be expedited - see narratives in 2e and 2h. | 0 | None | N/A | 100 | No variance from Baseline. | 3 | No variance from Baseline. | 0 | N/A | 54 | Variance from Baseline due to awaiting the Finding Of No Significant Impact (FONSI) on the Environmental Assessment. The State has proceeded with work on this milestone while awaiting the FONSI and is developing required documents for acquiring needed construction permits, railroad permits and other approvals. The State will expedite this process with the goal of completing this milestone on schedule. | 0 | N/A | 0 | No variance from Baseline. | 0 | Variance from Baseline due to awaiting Finding Of No Significant Impact (FONSI) on the Environmental Assessment. The State is revising internal project plans to expedite the network build in order to complete this milestone on schedule. The State will engage multiple engineering design firms and will divide the network build into 40-50 mini-projects with multiple construction firms and project partners. The State will release an RFP and will purchase all materials (fiber optic cable, conduit, etc.) directly from suppliers. | 0 | No variance from Baseline. | 0 | No variance from Baseline. | 2011-05-25 16:24 | 2011-05-25 16:24 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2011 | Q2 | Q2 - 2011 | 2962 | 3238 | FALSE | 8 | Variance from Baseline. The State proceeded on segments of the project while awaiting the Finding Of No Significant Impact (FONSI) on the Environmental Assessment. Critical segments of the project will be expedited - see narratives in 2e and 2h. | 0 | None | N/A | 100 | No variance from Baseline. | 6 | No variance from Baseline. Matching funds expended to date include salaries and fringe for ODOT internal engineering staff and payments to engineering firms for preliminary design work. | 0 | N/A | 81 | Variance from Baseline due to awaiting the Finding Of No Significant Impact (FONSI) on the Environmental Assessment. The State has proceeded with work on this milestone while awaiting the FONSI and has developed required documents for acquiring needed construction permits, railroad permits and other approvals. The State will expedite this process with the goal of completing this milestone on schedule. | 0 | N/A | 0 | No variance from Baseline. The State will issue RFP(s) and will purchase all materials (fiber optic cable, conduit, communications huts, etc.) directly from multiple suppliers. | 2 | Variance from Baseline due to awaiting Finding Of No Significant Impact (FONSI) on the Environmental Assessment. The State is revising internal project plans to expedite the network build in order to complete this milestone on schedule. The State will engage multiple engineering design firms and will divide the network build into 40-50 mini-projects with multiple construction firms and project partners. As noted in number 1, the State will evaluate responses to Request for Proposal (RFP) to solicit and consider proposals from qualified offerors willing to enter into one or multiple agreements for public-private initiative/partnership(s) or shared resources project(s) for the construction of fiber optic cables, conduit and ground boxes along the OCAN Broadband project construction routes, and will conduct negotiations and sign contracts with selected partners. | 0 | No variance from Baseline. | 0 | No variance from Baseline | 2011-08-08 16:21 | 2011-08-08 16:21 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2011 | Q3 | Q3 - 2011 | 3496 | 3518 | FALSE | 30 | Variance from Baseline. Critical segments of the project are being expedited - see narratives in 2e, 2g and 2h. | 0 |  | N/A | 100 | No variance from Baseline. | 84 | Variance from Baseline. This milestone is ahead of schedule. Projected matching funds expended include salaries and fringe for ODOT internal engineering staff and payments to engineering firms for preliminary design work. | 100 | See narrative in 2d above. | 90 | Variance from Baseline. The State has developed required documents for acquiring needed construction permits, railroad permits and other approvals. The State is expediting this process with the goal of completing this milestone on schedule. It is projected this milestone will be completed under the budgeted amount. | 0 | N/A | 49 | Variance from Baseline. The State has issued a RFP for Fiber Optic Cable for the OCAN project. The RFP was posted on September 28, 2011 with a close date of October 27, 2011. The State will issue RFP(s) for additional required materials (conduit, handholes, etc.). | 13 | Variance from Baseline. The State will complete Indefeasible Right of Use (IRU) Agreements to meet the purpose of the grant on certain segments of the OCAN project. The State will issue Request for Proposal (RFP) packages for construction of the OCAN project on remaining segments. | 0 | No variance from Baseline. | 0 | No variance from Baseline. | 2011-10-27 11:36 | 2011-10-27 11:36 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2011 | Q4 | Q4 - 2011 | 4910 | 4594 | FALSE | 32 | Variance from Baseline. Critical segments of the project are being expedited. | 0 |  | N/A | 100 | No variance from Baseline. | 100 | Variance from Baseline. This milestone will be completed ahead of the schedule projected in the Baseline. | 100 | NOTE: This milestone was not included in the Baseline as the State is donating Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | No variance from Baseline. | 0 | N/A | 49 | Variance from Baseline. The State issued a Request for Proposal (RFP) for Fiber Optic Cable for the OCAN project. Bids have been received and evaluated. Purchase Orders will be issued in January, 2012. A RFP will be issued in January for the additional network equipment needed for the OCAN project. Bids will be evaluated and purchase orders will be issued. | 14 | Variance from Baseline. The State plans to complete Indefeasible Right of Use (IRU) Agreements to meet the purpose of the grant on certain segments of the OCAN project. The State will award the bids for construction of the OCAN project on segments not included in the proposed Indefeasible Right of Use (IRU) Agreements. | 0 | Variance from Baseline. Network equipment will be deployed when delivered, initially on segments included in the IRU Agreements. Remaining network equipment will be deployed when fiber optic cable is installed. | 0 | Variance from Baseline. Network equipment will be tested when it is deployed, initially on segments included in the IRU Agreements. Remaining network equipment will be tested when deployed after fiber optic cable is installed. | 2012-02-07 15:59 | 2012-02-07 15:59 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2012 | Q1 | Q1 - 2012 | 5960 | 5579 | FALSE | 63 | Variance from Baseline. All critical milestones of the project are being expedited to meet the overall 67 percent project completion milestone by the end of year two of the project. | 0 |  | N/A | 100 | No variance from Baseline. | 100 | Variance from Baseline. This milestone was completed ahead of schedule. | 100 | NOTE: This milestone was not included in the Baseline as the State is donating Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | No variance from Baseline. | 0 | N/A | 64 | Variance from Baseline. All communications huts will be completed and installed. All fiber optic cable will be delivered. Bids for network equipment will be awarded and purchase orders issued. | 50 | Variance from Baseline. The State will execute two additional Indefeasible Right of Use (IRU) Agreements for existing fiber optic facility to meet the purpose of the grant on certain segments of the OCAN project. The State has awarded bids for construction on on all segments of the OCAN project not included in the IRU Agreements. | 20 | No variance from Baseline. Equipment donated as match for the OCAN project has been deployed. New network equipment will be deployed when delivered, initially on segments included in the IRU Agreements. Remaining network equipment will be deployed when fiber optic cable is installed. | 20 | No variance from Baseline. Network testing has been completed on the network delivered to the OCAN project on the first executed IRU and will be completed on the network delivered on the two additional IRU Agreements. Network equipment will be tested when it is deployed, initially on segments included in the IRU Agreements. Remaining network equipment will be tested when deployed after fiber optic cable is installed. | 2012-05-08 12:11 | 2012-05-08 12:11 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2012 | Q2 | Q2 - 2012 | 6866 | 6059 | FALSE | 93 | Variance from Baseline. All critical milestones of the project are being expedited to meet the overall 67 percent project completion milestone by the end of year two of the project. | 0 |  | N/A | 100 | No variance from Baseline. | 100 | Variance from Baseline. This milestone was completed ahead of schedule. | 100 | NOTE: This milestone was not included in the Baseline as the State is donating Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | No variance from Baseline. | 0 | N/A | 100 | No variance from Baseline. All equipment is projected to be purchased by end of next quarter. | 100 | Variance from Baseline. The State will execute two additional Indefeasible Right of Use (IRU) Agreements for existing fiber optic facility to meet the purpose of the grant on certain segments of the OCAN project. The State is projecting to have all OCAN project segments, not included in the IRU's, constructed and fiber pulled. | 40 | No variance from Baseline. Equipment donated as match for the OCAN project has been deployed. New network equipment will be deployed when delivered, initially on segments included in the IRU Agreements. Remaining network equipment will be deployed when fiber optic cable is installed. | 40 | No variance from Baseline. Network testing has been completed on the network delivered to the OCAN project on the first executed IRU and will be completed on the network delivered on the two additional IRU Agreements. Network equipment will be tested when it is deployed, initially on segments included in the IRU Agreements. Remaining network equipment will be tested when deployed after fiber optic cable is installed. | 2012-08-06 13:37 | 2012-08-06 13:37 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2012 | Q3 | Q3 - 2012 | 7816 | 6611 | FALSE | 97 | Variance from Baseline. All critical milestones of the project are being expedited to meet the overall 98 percent project completion milestone by the end of Q2 of year three of the project. | 0 |  | N/A | 100 | No Variance from Baseline. | 100 | No variance from Baseline. | 100 | NOTE: This milestone was not included in the Baseline as the State is donating Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | No variance from Baseline. | 0 | N/A | 93 | Variance from Baseline. All equipment is projected to be purchased by end of Q2 of year three of the project. | 93 | Variance from Baseline. The State is projecting to have all OCAN project segments constructed and fiber pulled by the end of the first month in Q3 of year three of the project. | 70 | No variance from Baseline. Equipment donated as match for the OCAN project has been deployed. New network equipment is in process of being deployed. | 70 | No variance from Baseline. Network testing has been completed on the network delivered to the OCAN project on the executed IRU Agreements and completed segments of the OCAN project. | 2012-11-09 14:49 | 2012-11-09 14:49 | 6060 | 6060 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2012 | Q4 | Q4 - 2012 | 8706 | 7512 | FALSE | 98 | Variance from Baseline. All critical milestones of the project are being expedited to meet the overall 100 percent project completion milestone by the end of Year3-Q3 of the project. | 0 |  | N/A | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | Note: This milestone was not included in the Baseline as the State is donating Right of Way as match. The match value of $4,522,500 for Right of Way has been booked to the OCAN project and posted to Actuals in Row b in the Infrastructure Budget Execution Details. | 100 | No variance from Baseline. | 0 | N/A | 95 | Variance from Baseline. Remaining network equipment to be purchased has been sent out for bid with a deadline to be procured by Year3-Q4 of the project. | 100 | No variance from Baseline. The State is projecting to have all OCAN project segments constructed and fiber pulled by the end of the first month in Year3-Q3 of the project. | 95 | Variance from Baseline. Remaining network equipment to be purchased has been sent out for bid with a deadline to be procured and deployed by Year3-Q4 of the project. | 100 | No variance from Baseline. Network testing has been completed on the network delivered to the OCAN project on the executed IRU Agreements and completed segments of the OCAN project. | 2013-02-11 15:28 | 2013-02-11 15:28 | 7631 | 7631 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2013 | Q1 | Q1 - 2013 | 9626 | 8344 | FALSE | 100 | No variance from Baseline. | 0 |  | N/A | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 2013-05-07 17:23 | 2013-05-07 17:23 | 7631 | 7631 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2013 | Q2 | Q2 - 2013 | 10320 | 8778 | FALSE | 100 | No variance from Baseline. | 0 |  | N/A | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 0 | N/A | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 100 | No variance from Baseline. | 2013-07-30 12:25 | 2013-07-30 12:25 | 7631 | 7631 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | 2013 | Q3 | Q3 - 2013 | 12516 | 10691 | FALSE | 100 | Project complete. | 0 |  | N/A | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 0 | N/A | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 100 | Project complete. | 2014-09-22 14:45 | 2014-09-22 14:45 | 7631 | 7631 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570114 | 2010 | Q4 | Q4 - 2010 | 1366 | 2381 | FALSE | 7 | None Noted | 26 | Staffing | None Noted | 95 | None Noted | 50 | The slow contract negotiations Merit does not feel that we will catch up with Network Design. Weather conditions will also determine the speed at which the engineers will be able to work. Merit feels that next quarter engineering will be up to speed and on track considering the process we have put in place. | 50 | None Noted | 10 | Merit doesn't feel that we will be up to speed in this category considering the contract negotiations. Merit feels that next quarter permitting will be up to speed and on track considering the process we have put in place. | 5 | None Noted | 10 | None Noted | 3 | None Noted | 0 | None Noted | 0 | None Noted | 2011-02-24 13:47 | 2011-02-24 13:47 | 5484 | 5484 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2011 | Q1 | Q1 - 2011 | 2268 | 2879 | FALSE | 4 | Our overall project spending will be significantly less than the projected 22% as a result of unexpected delays in the issuance of our FONSI. Even if the FONSI was issued today, any work performed would not be invoiced during 2011 Quarter 2. | 8 | Staffing | We have not hired staff at the rate originally projected because we overestimated the staffing levels that would be required for this pre-FONSI stage of the project. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we estimate will be at 385% next quarter. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the EA, we are considering a revision to the budget to incorporate the latest estimate of the EA cost at completion, which will be xx% above the original budget. | 28 | The bulk of network design costs are incurred during field engineering. To avoid wasting federal funds engineering routes that we may be required to change, we are not beginning the detailed engineering work until our route is approved. Even if the FONSI was issued today, any work performed would not be invoiced during 2011 Quarter 2. | 36 | We are able to send out Metropolitan Extension Telecommunications Rights-of-Way Oversight (METRO) permits with our EA route, and are beginning that this quarter. Because other permits require an approved engineered route, our ability to move forward with the remaining ROW permits depends on having our route accepted by the NTIA so the CAD drawings can be finalized. | 10 | Because permits require an approved engineered route, our ability to move forward with the remaining ROW permits depends on having our route accepted by the NTIA so the CAD drawings can be finalized. | 3 | Merit did not receive the FONSI, so we could not begin hut site construction. Sites for the huts have been identified and Merit will continue to negotiate easements. Even if the FONSI was issued today, any work performed would not be invoiced during 2011 Quarter 2. | 0 | Merit did not include equipment in our revised expenditure plan, so we cannot begin procuring equipment until we receive our FONSI. In addition, we are waiting on a determination on using a sole source justification for equipment vendor selection. If we order optical equipment this quarter, it is unlikely that we would pay the invoice during 2011 Quarter 2. | 3 | We anticipated having finalized IRU Agreements in place by this point; however, negotiations are underway, and we believe that we will be purchasing the existing infrastructure. However, construction cannot occur until the FONSI is issued, and will most likely begin in June, towards the end of 2011 Quarter 2. | 0 | With construction and equipment purchase approximately one quarter behind schedule, we do not anticipate incurring any costs for deployment this quarter. | 0 | With construction and equipment purchase approximately one quarter behind schedule, we do not anticipate incurring any costs for deployment this quarter. | 2011-05-24 09:31 | 2011-05-24 09:31 | 5484 | 5484 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2011 | Q2 | Q2 - 2011 | 3028 | 3271 | FALSE | 6 | Our overall project spending is less than we projected as a result of unexpected delays in the issuance of our Finding of No Significant Impact. Merit believed we would be able to begin field engineering and construction this quarter. Once Merit has clearance to move forward with construction, we believe that we will catch up over the next few quarters. | 17 |  | The construction delays have led to a slower staffing ramp up than originally projected. With the hire of a Project Manager, Environmental Assessor, and several clerks pending, we anticipate a gradually aligning with the Baseline Report. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 474%. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the Environmental Assessment, we are considering a revision to the budget to incorporate the latest estimate of the cost at completion, which will be around 700%. | 27 | We are waiting for our Finding of No Significant Impact to proceed with most of the field engineering, but have attempted to do as much planning as is covered by the revised expenditure plan. Due to weather conditions, pre-construction planning and engineering work wasn't done at the projected pace in the Upper Peninsula. | 66 | Many permits require an approved engineered route; while we are waiting for the engineering work to be completed and our route to be accepted, we have prepped many permits so they can be sent out as soon as the Finding of No Significant Impact is received and the route is finalized. | 23 | Many permits require an approved engineered route; while we are waiting for the engineering work to be completed and our route to be accepted, we have prepped many permits so they can be sent out as soon as the Finding of No Significant ImpactI is received and the route is finalized. | 0 | Merit did not receive the Finding of No Significant Impact, so we could not begin hut site construction. Sites for the huts have been identified and Merit began to negotiate easements. | 5 | Merit did not include equipment in our revised expenditure plan, so we requested a pre-Environmental Assessment budget revision. Our sole source was approved at the end of the quarter, and the order will be placed next quarter. | 5 | We anticipated having finalized Indefeasible Right to Use Agreements and the Finding of No Significant Impact in place by this point; however, negotiations are underway, and we believe that we will be purchasing the existing infrastructure and beginning construction in the next quarter. | 0 | We were waiting for our Environmental Assessment budget approval and sole source approval to order equipment. Equipment has been selected, and will be deployed as soon as it is received and tested. | 0 | Network construction has not begun. | 2011-08-11 16:37 | 2011-08-11 16:37 | 5484 | 5484 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2011 | Q3 | Q3 - 2011 | 3950 | 3813 | FALSE | 24 | Merit just recently received its notice of our Finding of No Significant Impact and has recently completed all field engineering. Our engineering firm is in the process of drafting the appropriate prints for permit applications. We have submitted all permits for Round 2 based on the prints weâ€™ve received thus far so we anticipate a heavy construction season starting next quarter. | 10 |  | With the hire of a Project Manager, Environmental Assessor and several clerks we anticipate a gradual alignment with the Baseline Report. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 565%. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the Environmental Assessment, we are considering a revision to the budget to incorporate the latest estimate of the cost at completion, which will be around 600%. | 58 | Since receiving our Finding of No Significant Impact we have completed most if not all of our field engineering. Permitting has started and some segments are already ready to go from a construction and environmental permit standpoint. The route has been finalized, engineered and assigned segment numbers that will be released to our selected construction contractors. Much of the pre-construction planning has been completed such as material purchases and route engineering in both the Upper and Lower Peninsula. | 90 | Many permits require an approved engineered route; and with most, if not all, of the field engineering complete we will have completed submission of almost all our Rights-of-way permit applications with the appropriate entities. As these permits are approved, we can then start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most if not all of the engineering work necessary. | 85 | We will have submitted almost all of the permits necessary for Round 2 construction since we received our Finding of No Significant Impact, and will spend this quarter resolving make-ready issues and following up with permitting agencies on permits that have not been issued. | 27 | Sites for the huts have been identified. We have submitted and closed an RFP for the construction of huts and are also in the process of acquiring easement agreements for the placement of said huts. As of today we have almost all of the easement agreements signed and forecast all easement issues resolved by the end of next quarter. We have also started interviewing contractors to construct our huts. | 6 | We anticipate ordering the bulk of our equipment in the next quarter, and being invoiced for that order in the quarter after that. | 33 | We have received our Indefeasible Right of Use Agreements as well as our Finding of No Significant Impact for Round 2. We have begun our negotiations to purchase existing infrastructure in both Michigan and Wisconsin and expect to have those agreements completed by the end of the next quarter. We anticipate doing a significant amount of make-ready work, and beginning underground construction. | 13 | Equipment has been selected and will be deployed as soon as it is received and tested. As of this quarter, since receiving the Environmental Assessment budget approval and sole source approval, the process of purchasing this equipment began this quarter. | 25 | Network construction has not begun, but with small sections of construction being deployed next quarter we anticipate testing to commence next quarter. | 2011-11-10 08:22 | 2011-11-10 08:22 | 5485 | 5485 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2011 | Q4 | Q4 - 2011 | 5328 | 5000 | FALSE | 26 | Merit anticipates construction moving into full swing. We will select vendors for hut construction, continue to procure optical equipment, and begin to procure switches and routers. Our Finding of No Significant Impact was received approximately two quarters later than we had projected, so many of our key indicators are also two quarters behind, including new network miles deployed (updated projection: 0), network miles leased (updated projection: 54), and new interconnection points (updated projection: 4). We anticipate having all agreements with broadband wholesalers in place by the end of the next quarter. | 11 |  | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 550%. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the Environmental Assessment, we are considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 600%. | 79 | While most of the field engineering is complete, we anticipate continued costs for incorporating redlines and doing final CADs, and the project will be at budget at completion. | 89 | We have prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 30 | We have prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 23 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. We will have increased the number of staff working on site preparation from one individual to four individuals. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 22 | More optical equipment will be ordered. The procurement process for routers and switches will be completed, and route/switch equipment will be ordered. Merit anticipates being at budget by project completion. | 26 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 26 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field deploying equipment, and spending in this category will increase. Merit will be at or close to budget by completion. | 20 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2012-02-28 07:33 | 2012-02-28 07:33 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2012 | Q1 | Q1 - 2012 | 6244 | 5724 | FALSE | 33 | Merit anticipates construction moving into full swing. We will select vendors for hut construction, continue to procure optical equipment, and begin to procure switches and routers. Our Finding of No Significant Impact was received approximately two quarters later than we had projected, so many of our key indicators are also two quarters behind | 29 | Staffing, Miscellaneous | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 554%. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the Environmental Assessment, we are considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 600%. | 90 | While most of the field engineering is complete, we anticipate continued costs for incorporating redlines and doing final CADs, and the project will be at budget at completion. | 88 | We have prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 57 | We have prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 24 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. We will have increased the number of staff working on site preparation from one individual to four individuals. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 22 | More optical equipment will be ordered. The procurement process for routers and switches will be completed, and route/switch equipment will be ordered. Merit anticipates being at budget by project completion. | 34 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 28 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field deploying equipment, and spending in this category will increase. Merit will be at or close to budget by completion. | 20 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2012-05-22 07:48 | 2012-05-22 07:48 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2012 | Q2 | Q2 - 2012 | 6948 | 6101 | FALSE | 43 | Merit anticipates construction increasing and continuing at full speed. We have selected vendors for hut construction, continue to procure optical equipment, and begin to procure switches and routers. Our Finding of No Significant Impact was received approximately two quarters later than we had projected, so many of our key indicators are also two quarters behind | 46 | Staffing | Now that the project is fully staffed, Merit anticipates gradually coming into line with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment (EA) costs; we are currently at 556%. This is partially due to an underestimate based on RFP responses we had received in the past, and partially due to unexpected challenges in obtaining clearances for in Wisconsin and Minnesota. Since we will continue to incur costs related to the Environmental Assessment, we are considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 600%. | 96 | While most of the field engineering is complete, we anticipate continued costs for incorporating redlines and doing final CADs, and the project will be at budget at completion. | 91 | We have prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 62 | We have prepped and submitted most permits so they can be approved as we start deploying construction crews. Since receiving our Finding of No Significant Impact we have finalized the route and completed most of the engineering work necessary. | 36 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. We will have increased the number of staff working on site preparation from one individual to four individuals. Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 29 | More optical equipment will be ordered. The procurement process for routers and switches will be completed, and route/switch equipment will be ordered. Merit anticipates being at budget by project completion. | 47 | Merit has contracts with seven construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 40 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field deploying equipment, and spending in this category will increase. Merit will be at or close to budget by completion. | 25 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2012-08-09 09:13 | 2012-08-09 09:13 | 7498 | 7498 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2012 | Q3 | Q3 - 2012 | 8038 | 6725 | FALSE | 58 | Merit expects construction to continue at full speed. The Finding of No Significant Impact was received approximately two (2) quarters behind the projected date thus many of our key indicators are also two (2) quarters behind. | 55 | Staffing Miscellaneous | The project is now fully staffed and Merit anticipates a gradual alignment with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 556% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 600%. | 100 | While most of the field engineering is completed Merit anticipates continued costs for incorporating redlines and final CADs. | 96 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. | 71 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. | 44 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. Merit will have increased the number of staff working on site preparation from one (1) individual to four (4). Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 39 | Merit is ordering additional optical equipment. The procurement process for routers and switches will be completed and router and switch equipment will be ordered. Merit anticipates being at budget by project completion. | 65 | Merit has contracts with seven (7) construction firms, each with multiple construction crews, and has begun aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 47 | Merit has been behind our Baseline Report due to delays in the start of construction. However, with construction actively underway, our engineers will be field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by project completion. | 34 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2012-11-26 12:39 | 2012-11-26 12:39 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2012 | Q4 | Q4 - 2012 | 9020 | 7792 | FALSE | 76 | Merit expects construction to continue at full speed. The Finding of No Significant Impact was received approximately two (2) quarters behind the projected date thus many of our key indicators are also two (2) quarters behind. | 67 | Staffing, Miscellaneous | The project is now fully staffed and Merit anticipates a gradual alignment with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 610% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 620%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Currently Merit is at 151% of the original budget. Site Prep expenses are being applied to this category as well. | 100 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. | 88 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. | 58 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. Merit will have increased the number of staff working on site preparation from one (1) individual to four (4). Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 59 | Merit is ordering additional optical equipment and anticipates being at budget by project completion. | 81 | Merit has contracts with seven (7) construction firms, each with multiple construction crews, and is continuing aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 74 | Merit has been behind our Baseline Report due to delays in the start of construction. However, with construction actively underway, our engineers will be field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by project completion. | 50 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2013-02-27 14:39 | 2013-02-27 14:39 | 7498 | 7498 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2013 | Q1 | Q1 - 2013 | 9954 | 8521 | FALSE | 81 | Merit expects construction to continue at full speed. The Finding of No Significant Impact was received approximately two (2) quarters behind the projected date thus many of our key indicators are also two (2) quarters behind. | 68 | Staffing, Miscellaneous | The project is now fully staffed and Merit anticipates a gradual alignment with the Baseline Report by project completion. 3. Please describe any challenges or issues anticipated during the next quarter that may impact planned progress | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 635% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 641%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Merit anticipates spending to continue in the next quarter in this category, with the overrun being absorbed by another category. Merit anticpates spending continuing in the next quarter and will be around 187%. | 100 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Merit anticipates being near 118% by the end of next quarter. | 89 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. | 60 | Merit anticipates being invoiced for site preparation work performed in the previous quarter. Merit will have increased the number of staff working on site preparation from one (1) individual to four (4). Our strategy includes prepping each site prior to the arrival of the backbone fiber to the anchor, which allows Merit to complete site preparation more efficiently and in a timely manner. | 60 | Merit is ordering additional optical equipment and anticipates being at budget by project completion. | 87 | Merit has contracts with seven (7) construction firms, each with multiple construction crews, and is continuing aerial construction and underground construction across the funded network. Merit anticipates a significant increase in the spending rate in this budget category, and will be at budget by project completion. | 74 | Merit has been behind our Baseline Report due to delays in the start of construction. However, with construction actively underway, our engineers will be field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by project completion. | 50 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2013-05-29 06:10 | 2013-05-29 06:10 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2013 | Q2 | Q2 - 2013 | 10732 | 9029 | FALSE | 86 | Merit expects construction to continue at full speed. The Finding of No Significant Impact was received approximately two (2) quarters behind the projected date thus many of our key indicators are also two (2) quarters behind. | 50 | Staffing, Miscellaneous | The project is now fully staffed and Merit anticipates a gradual alignment with the Baseline Report by project completion. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 637% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 643%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Merit anticipates spending to continue in the next quarter in this category, with the overrun being absorbed by another category. Merit anticpates spending continuing in the next quarter and will be around 212%. Some project salary has been applied to this category. | 100 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Merit anticipates being near 137% by the end of next quarter. | 100 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. | 37 | Merit anticipates additional spending in the coming quarter as sites are being completed as backbone fiber passes by. | 39 | Merit is ordering additional optical equipment and anticipates being at budget by project completion. | 100 | Merit has contracts with seven (7) construction firms, each with multiple construction crews, and is continuing aerial construction and underground construction across the funded network. Merit anticipates continued spending during the next quarter and will likely be over budget. The overrun should be able to be absorbed into another category. | 58 | Merit has been behind our Baseline Report due to delays in the start of construction. However, with construction actively underway, our engineers will be field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by project completion. | 20 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2013-08-26 11:00 | 2013-08-26 11:00 | 5993 | 5993 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2013 | Q3 | Q3 - 2013 | 11342 | 9471 | FALSE | 100 | Merit expects construction to continue be at or near completion. The Finding of No Significant Impact was received approximately two (2) quarters behind the projected date thus many of our key indicators are also two (2) quarters behind. | 60 | Staffing Miscellaneous | The project is now fully staffed and Merit anticipates a gradual alignment with the Baseline Report by project completion. Some staffing costs has been allocated to Network Design rather than this category which is part of the reason our spending is low. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 643% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur minor costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 643%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Merit anticipates spending to continue in the next quarter in this category, with the overrun being absorbed by another category. Merit anticipates spending continuing in the next quarter and will be around 231%. Some project salary has been applied to this category. | 100 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Merit anticipates being near 214% by the end of next quarter. | 100 | Merit has prepped and submitted most permits for approval as construction crews are deployed. Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Merit anticipates being at 124% of budget during the next quarter. | 29 | Merit anticipates additional spending in the coming quarter as sites are being completed as backbone fiber passes by. | 38 | Merit is had ordered equipment. Expenses that were originally budgeted for this category have been applied to other categories. This category will absorb overages from other areas. | 100 | Merit has contracts with seven (7) construction firms, each with multiple construction crews, and is continuing aerial construction and underground construction across the funded network. Merit anticipates continued spending during the next quarter and will likely be over budget. The overrun should be able to be absorbed into another category. | 100 | Merit has been behind our Baseline Report due to delays in the start of construction. However, with construction actively underway, our engineers will be field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by project completion. | 61 | Merit has been behind our baseline due to delays in starting from construction. However, with construction actively underway, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2013-11-22 09:11 | 2013-11-22 09:11 | 7498 | 7498 | Merit Network Inc. | TRUE
NT10BIX5570114 | 2013 | Q4 | Q4 - 2013 | 11898 | 10066 | FALSE | 100 | The Finding of No Significant Impact was received approximately two (2) quarters behind the projected date thus many of our key indicators are also two (2) quarters behind. Merit anticipates completing the project in the next quarter. | 53 | Staffing Miscellaneous | The project is now fully staffed and Merit anticipates a gradual alignment with the Baseline Report by project completion. Some staffing costs has been allocated to Network Design rather than this category which is part of the reason our spending is low. | 100 | Merit has exceeded our Environmental Assessment costs. We are currently at 687% of original budget. This overage is due to the underestimated line item based on Request For Proposal responses to Merit and unexpected challenges in obtaining clearances in Wisconsin and Minnesota. Since Merit will continue to incur minor costs related to the Environmental Assessment, Merit is considering a revision to the budget to incorporate the latest estimate of the Environmental Assessment cost at completion, which will be around 690%. | 100 | Since receiving Meritâ€™s Finding of No Significant Impact, Merit has completed the required field engineering. Merit anticipates continued costs for incorporating redlines and doing final CADs. Merit anticipates spending to continue in the next quarter in this category, with the overrun being absorbed by another category. Merit anticipates spending continuing in the next quarter and will be around 261%. Some project salary has been applied to this category. | 100 | Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Permitting is essentially complete. Merit anticipates being near 180% by the end of next quarter. | 100 | Since receiving the Finding of No Significant Impact Merit has finalized the route and completed the necessary engineering work. Permitting is essentially complete. Merit anticipates being near 103% by the end of next quarter. | 29 | Site preparation work is esentially complete. Costs have been absorbed in other categories to date. Merit anticipates little spending to occur in this category and will absorb overages from other categories. | 39 | Merit is had ordered equipment. Expenses that were originally budgeted for this category have been applied to other categories. This category will absorb overages from other areas. | 100 | Construction is nearing completion, as soon as next quarter. Merit anticipates continued spending during the next quarter and will likely be over budget. The overrun should be able to be absorbed into another category. | 100 | Merit has been behind our Baseline Report due to delays in the start of construction. However, with construction near completion, our engineers will be field testing completed fiber and finishing up equipment installs. Merit will be at or close to budget by project completion. | 100 | Merit has been behind our baseline due to delays in starting from construction. However, with construction near complete, our engineers will be out in the field testing completed fiber, and spending in this category will increase. Merit will be at or close to budget by completion. | 2014-02-26 14:50 | 2014-02-26 14:50 | 7498 | 7498 | Merit Network Inc. | TRUE
NT10BIX5570115 | 2010 | Q4 | Q4 - 2010 | 1080 | 2116 | FALSE | 3 | No variance from plan. | 0 | Fiscal compliance and project management | Fiscal compliance is expected to be 24% complete and project management is expected to be 19% complete | 100 | No variance from plan. | 16 | No variance from plan. | 1 | No variance from plan. | 77 | No variance from plan. | 0 | No variance from plan. | 0 | No variance from plan. | 0 | No variance from plan. | 7 | No variance from plan. | 0 | No variance from plan. | 2011-02-11 13:57 | 2011-02-11 13:57 | 7018 | 7018 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2011 | Q1 | Q1 - 2011 | 1962 | 2726 | FALSE | 18 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 30 | Fiscal compliance and project management | Fiscal compliance in baseline is 33% complete and project management is 28% complete. | 100 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 27 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 4 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 80 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 0 | na | 0 | na | 19 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 7 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 100 | Percents listed are from the baseline plan. Adjustments may be necessary after the Finding of No Significant Impact is issued. | 2011-05-12 11:32 | 2011-05-12 11:32 | 7054 | 7054 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2011 | Q2 | Q2 - 2011 | 3148 | 3334 | FALSE | 31 | Overall, actual spending of federal and match funds for build was delayed while wainting for the Finding of No Significant Impact. | 25 | Fiscal Compliance and Project Manager | Staff did not start in project as early as initially expected. | 100 | na | 5 | Design activities could not start until after Finding of No Significant Impact was received in late May. | 100 | na | 42 | Majority of permit activities could not start until after Finding of No Significant Impact was received in late May. | 0 | na | 0 | na | 34 | Network build could not start until after Finding of No Significant Impact was received in late May. | 4 | Equipment deployment could not start until after Finding of No Significant Impact was received in late May. | 0 | Network testing cannot begin until fiber is installed later this year. | 2011-08-17 11:49 | 2011-08-17 11:49 | 7054 | 7054 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2011 | Q3 | Q3 - 2011 | 4092 | 3889 | FALSE | 47 | Actual spending was delayed when build was not started as planned due to delays in the Finding of No Significant Impact process. We expect significant spending to continue for extra construction crews with catch up to occur by next quarter. We also have expenditure delays due to payments being cost reimbursement to our sub-recipients. | 30 | Fiscal compliance and Project Manager | Staff did not start in project as early as initially expected so expenses are not likely to equal budget. | 100 | na | 9 | Outside consultants have not been required to the extent originally planned. | 100 | na | 58 | See 2a above. | 0 | na | 0 | na | 50 | See 2a above. | 30 | Now that build has started with receipt of Finding of No Significant Impact, another third of equipment will be ordered. However, actual spending may not occur until next quarter because of the delays in reimbursing sub-recipients. | 50 | Now that build has started with receipt of Finding of No Significant Impact, approximately half the testing equipment has been ordered. We expect equipment delivery and subsequent invoices this quarter. The other half will occur next quarter due to delays with reimbursing sub-recipients. | 2011-11-16 16:24 | 2011-11-16 16:24 | 7054 | 7054 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2011 | Q4 | Q4 - 2011 | 5276 | 4945 | FALSE | 45 | Actual spending was delayed when build was not started as planned due to delays in the Finding of No Significant Impact process. We expect significant spending to continue for extra construction crews with catch up to occur by April to June quarter. We still have expenditure delays due to payments being cost reimbursement to our sub-recipients. | 36 | Fiscal and Project Management | Staff did not start in project as early as initially expected so expenses are not likely to equal budget. | 100 | NA | 12 | Outside consultants have not been required to the extent originally planned. | 100 | NA | 63 | See 2a above. | 0 | NA | 0 | NA | 44 | See 2a above. | 44 | Now that build has started, half of the equipment can be ordered. However payment may not occur until next quarter due to delays with reimbursing sub-recipients. | 97 | Purchase of network testing equipment is complete. | 2012-02-27 09:43 | 2012-02-27 09:43 | 7054 | 7054 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2012 | Q1 | Q1 - 2012 | 5946 | 5572 | FALSE | 55 | Actual spending was delayed when build was not started as planned due to delays in the Finding of No Significant Impact process. We expect a slow start to spring construction activities due to permitting delays, but expect to make up the time with additional crews so fiber installation can be completed by December 2012. Expenditures will be delayed for one quarter since sub-recipients are paid on a cost reimbursement basis. | 43 | Fiscal and Project Management | Since staff did not start in project as early as initially expected, expenses are not likely to equal budget. | 100 | Activity is complete. | 13 | Outside consultants have not been required to the extent originally planned. | 100 | Activity is complete. | 64 | See 2a explanation above. | 0 | NA | 0 | NA | 52 | See 2a explanation above. | 66 | Now that build has started, equipment orders and related invoices are being processed. There are delays in reporting expenses since sub-recipients are on a cost reimbursement basis. | 97 | Purchase of network testing equipment is complete. | 2012-05-07 16:02 | 2012-05-07 16:02 | 7054 | 7054 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2012 | Q2 | Q2 - 2012 | 7062 | 6158 | FALSE | 60 | Actual recorded federal and match spending for network build are lower caused by build delays due to late receipt of the Finding of No Significant Impact and the further delays in 2012 pending negotiations between NTIA and U.S Fish and Wildlife Service regarding the Karner Blue Butterfly. Plans for catch up spending will be determined once work resumes in full. | 62 | Fiscal and Project Management | Staff expenses are not likely to meet budget. Early project expenses were not as high as originally planned. | 100 | Activity is complete. | 27 | Outside consultants have not been required to the extent originally planned. | 100 | Activity is complete. | 71 | See explanation in 2a above. | 0 | NA | 0 | NA | 58 | See explanation in 2a above. | 60 | See explanation in 2a above. | 97 | Purchase of network testing equipment is complete. | 2012-08-14 14:46 | 2012-08-14 14:46 | 7054 | 7054 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2012 | Q3 | Q3 - 2012 | 7862 | 6635 | FALSE | 73 | Actual recorded federal and match spending for network build are lower caused by build delays due to late receipt of the Finding of No Significant Impact and the further delays in 2012 pending negotiations between NTIA and U. S. Fish and Wildlife Service regarding the Karner Blue Butterfly. Plans for catch up will be determined once work resumes in full. | 69 | Fiscal and Project Management | Staff expenses are not likely to meet budget. Early project expenses were not as high as originally planned. | 100 | Activity is complete. | 28 | Outside consultants have not been required to the extent originally planned. | 100 | Activity is complete. | 73 | See explanation in 2a above. | 0 | NA | 0 | NA | 75 | See explanation in 2a above. | 62 | See explanation in 2a above. | 97 | Purchase of network testing is complete. | 2012-11-14 09:35 | 2012-11-14 09:35 | 7110 | 7110 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2012 | Q4 | Q4 - 2012 | 8730 | 7529 | FALSE | 83 | Actual recorded federal and match spending for network build are lower caused by build delays due to late receipt of the Finding of No Significant Impact and the further delays in 2012 pending negotiations between NTIA and U.S. Fish and Wildlife Services regarding the Karner Blue Butterfly. Given the success with construction catch up last quarter, we plan to complete construction before the end of the grant. | 87 | Fiscal and Project Management | Staff expenses are not likely to meet budget. Early project expenses were not as high as originally planned. | 100 | Activity is complete. | 31 | Outside consultants have not been required to the extent originally planned. | 100 | Activity is complete. | 74 | See explanation in 2a above. | 0 | NA | 0 | NA | 87 | See explanation in 2a above. | 62 | See explanation in 2a above. | 97 | Purchase of network testing equipment is complete. | 2013-02-12 16:02 | 2013-02-12 16:02 | 7110 | 7110 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2013 | Q1 | Q1 - 2013 | 9624 | 8343 | FALSE | 92 | Actual recorded federal and match spending for network build are lower caused by delays due to late receipt of the Finding of No Significant Impact and environmental permitting delays in 2012. While actual project work is expected to be completed this quarter. Final invoices will be processed next quarter. | 96 | Fiscal and Project Management | Staff expenses are not likely to meet budget. Early project expenses were not as high as originally planned. | 100 | Activity is complete. | 34 | Use of outside consultants have not been required to the extent originally planned. | 100 | Activity is complete. | 74 | See explanation in 2a above. | 0 | NA | 0 | NA | 97 | See explanation in 2a above. | 79 | See explanation in 2a above. | 97 | Purchase of network testing equipment is complete. | 2013-05-07 15:08 | 2013-05-07 15:08 | 7110 | 7110 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2013 | Q2 | Q2 - 2013 | 10580 | 8946 | FALSE | 100 | The project will be complete at the end of this quarter. | 100 | Fiscal and Project Management | All federal funds will be expended. Closeout activities will be paid with other cash resources. | 100 | Activity is complete. | 35 | Use of outside consultants have not been required to the extent originally planned | 100 | Activity is complete. | 75 | The need for permit costs was not as great as originally planned. | 0 | NA | 0 | NA | 100 | Activity will be complete at the end of this quarter. | 90 | The need for permit costs was not as great as originally planned. | 97 | The need for permit costs was not as great as originally planned. | 2013-08-14 12:40 | 2013-08-14 12:40 | 7110 | 7110 | University of Wisconsin System | TRUE
NT10BIX5570115 | 2013 | Q3 | Q3 - 2013 | 11950 | 10120 | FALSE | 100 | Project is complete and final invoices have been paid. | 100 | Fiscal and Project Management | Activity will be completed with other cash resources. | 100 | Activity is complete. | 100 | Use of outside consultants had not been required to the extent originally planned. Activity is complete. | 100 | Activity is complete. | 100 | The need for permit costs was not as great as originally planned. Activity is complete. | 0 | NA | 0 | NA | 100 | Activity is complete. Actual spending exceeded budget. | 100 | Equipment costs were not as great as originally planned. Activity is complete. | 100 | Network testing costs were not as great as originally planned. Activity is complete. | 2014-03-17 11:43 | 2014-03-17 11:43 | 6687 | 6687 | University of Wisconsin System | TRUE
NT10BIX5570116 | 2010 | Q4 | Q4 - 2010 | 1344 | 2362 | FALSE | 9 | NCNMEDD and its contractors were unable to draw down federal funds until the six month budget was approved in January 2011. With 78.9% of the funds for all activities to come from the BTOP grant, it was difficult to spend all of the money anticipated until federal funds were released. Aggressive work on the construction contract and materials procurement should allow achievement of milestones, depending on the completion of Special Award Conditions and receiving the FONSI or mitigated FONSI. The increase to 9% from the baseline estimate of 7% will be due to advance procurment of materials. | 24 | Project management | This is in line with the original Baseline report. | 100 | The draft EA is on target for submittal, but some of the agencies may not finish their review as fast as others. Particular issues with the Bureau of Indain Affairs have been described elsewhere and in conversation with the FPO. | 71 | The Baseline assumed 85% completion by this time. This variance is due to the time spent in the previous quarter executing the Engineering contract and in obtaining permission to draw down funds for the six month budget. However, all key milestones are anticipated to be completed within this forecasted quarter, including final engineering design, construction prints, pole review, materials and equipment specifications, in line with the Baseline report. | 100 | The JPA governing the network, which was signed by all parties, indicates their willingness to provide rights of way for this project. Some concerns, elsewhere described, have arisen with some of the Pueblos. In the event that this delays activities, a report will be filed immediately. These issues have already been discussed with the FPO. | 75 | Applications will be initiated with all jurisdictions, with maps, descriptions and all information required, with the exception of that which can only be obtained after the execution of the construction contract. In addition, it is not possible to guarantee that all federal agencies will have completed their review of the EA and issued permits, where required. The percent of completion is listed at 75%, not 100%, because of the need to have the contractor in place to complete the application process. | 25 | Site preparation for the POP in Los Alamos will go forward as planned. Site preparation for the POP in Espanola may be delayed, depending on the timing of the FONSI. | 0 | None | 0 | None | 0 | None | 0 | None | 2011-02-23 15:17 | 2011-02-23 15:17 | 6052 | 6052 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2011 | Q1 | Q1 - 2011 | 1842 | 2664 | FALSE | 6 | In addition to the project activities discussed above, major milestones anticipated to be completed in Q4 include completion of engineering design, permits and rights-of-way, and finalizing contracts with a construction contract and materials supplier. Awards have already been made to project finalists and contract negotiations are underway. | 30 | Project Management |  | 100 | The agency accepted the revised Environmental Assessment on April 8, and copies were sent to agencies and tribes for review during the week April 11. The agencies and tribes have been given a two-week review window, which will close out the comment period in early May. Assuming a FONSI is issued in a timely manner, we should be able to begin drawing down construction funds by June 2011. | 90 | A 90% engineering design review meeting is scheduled for April 29, 2011, after which 100% drawings will be finalized. All engineering design is scheduled for completion by the end of May 2011, to enable construction to begin in June. The final engineering prints will become part of the construction contract documents, and serve as a baseline for the final implementation schedule. While engineering work will be 100% complete in Quarter 4, we are reserving 10% of the total engineering budget to cover activities in the construction phase. | 100 | Securing of rights-of-way was 75% complete in Quarter 3, and should be fully complete in Quarter 4. | 100 | Securing of construction permits and approvals was 75% complete in Quarter 3, and should be fully complete in Quarter 4. | 25 | If a FONSI is issued in May 2011, site preparation for the primary and secondary POPs will occur in Quarter 4. | 25 | If a FONSI is issued in May 2011, materials and network equipment procurement will begin in May and early June, in preparation for construction commencement in June. REDI Net has requested funding draw down, pre-FONSI, for qualifying expenses, as lead-times on the fiber cable have been extended due to raw materials shortages. This advance procurement will assist in keeping the overall project timeline on track. | 5 | Assuming construction commences in June, work would begin on the primary backbone fiber routes and primary POP installation. This is only an estimate until contract negotiations conclude in May and the final implementation schedule is set. | 0 | None | 0 | None | 2011-05-02 12:43 | 2011-05-02 12:43 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2011 | Q2 | Q2 - 2011 | 2548 | 3022 | FALSE | 39 | The project is anticipated to remain slightly behind schedule due to delays in receiving the FONSI, which put construction activities one quarter behind schedule. However, we will begin making up for these delays during Quarter 1, Year 2, as construction proceeds. | 45 | Project Management | Construction management and overall project implementation will continue as forecasted in the baseline. | 100 | Completed. | 100 | Completed. | 100 | Completed. | 100 | Completed. | 100 | Completed. | 95 | Construction-related activities are approximately one quarter behind schedule due to delays with the FONSI. However, equipment procurement has been properly planned for, and NCNMEDD is ready to issue a Purchase Order for this milestone. Therefore, we anticipate 95% of our equipment budget will be expended in Quarter 1 of Year 2. | 36 | Construction activities are approximately one quarter behind schedule due to delays with the FONSI. 36% completion was expected in this quarter, and is therefore projected for Quarter 1 of Year 2. | 30 | It is anticipated that customer premise equipment will be installed in 40 of the 118 CAIs that are receiving CPE, along with placing the 2 core routers in the POPs. | 0 | Network testing may commence late in Quarter 1 of Year 2, although the assumption in the Baseline report projected Quarter 2 of Year 2. Therefore, we are still forecasting in-line with the Baseline. | 2011-07-27 12:42 | 2011-07-27 12:42 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2011 | Q3 | Q3 - 2011 | 4208 | 3952 | FALSE | 60 | Construction activity will continue to ramp up through Q4 2011, bringing the project closer to baseline performance goals. | 54 | Project Management | Project management work continued as anticipated, providing construction management, procurement, and general oversight. | 100 | Complete | 100 | Complete | 100 | Complete | 98 | Local government permits are being phased in closer to initiating the construction activities, so it is feasible that a small number of permits might be applied for after the upcoming reporting period. However, this will not impact overall project delivery. | 100 | Complete | 98 | All major equipment orders are already complete, although it is possible that some smaller elements (servers, additional CPE) might be needed after the upcoming reporting period, so 2% of the budget is being reserved. | 43 | Construction and procurement activities started late June 2011, due to delays with the FONSI. Since initiating construction, there were some additional challenges with pole attachment applications, make-ready, and materials supply, all of which have been resolved. Construction and procurement are now ramping up. We are incrementally catching up on network build and will continue to do so in Q4 2011. Upcoming activities include make-ready, pole replacements, aerial fiber installation, boring, conduit placement, underground fiber installation, and POP construction. | 50 | Core routing equipment and a portion of the CPE will be installed in Q4 2011. | 25 | Field testing will commence on the core routing equipment in Q4 2011. | 2011-11-21 23:38 | 2011-11-21 23:38 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2011 | Q4 | Q4 - 2011 | 5218 | 4885 | FALSE | 67 | Construction activity will continue to ramp up through Q1 2012, bringing the project closer to performance goals. | 58 | Project Management | Project management work continued as anticipated, providing construction management, procurement, and general oversight. | 100 | Complete | 100 | Complete | 100 | Complete | 98 | Local government permits are being phased in closer to initiating the construction activities, so it is feasible that a small number of permits might be applied for after the upcoming reporting period. However, this will not impact overall project delivery. | 100 | Complete | 98 | All major equipment orders are already complete, although it is possible that some smaller elements (servers, additional CPE) might be needed after the upcoming reporting period, so 2% of the budget is being reserved. | 65 | Construction and procurement activities started late June 2011, due to delays with the FONSI. Since initiating construction, there were some additional challenges with pole attachment applications, make-ready, and materials supply, all of which have been resolved. Construction and procurement are now ramping up. We are incrementally catching up on network build and will continue to do so in the upcoming reporting period. Upcoming activities include significant focus on pole replacements, then resuming aerial fiber installation. Continued progress will be made on boring, conduit placement, underground fiber installation, and POP setup. | 50 | Core routing equipment and a portion of the CPE will be installed in Q1 2012. | 25 | Field testing will commence on the core routing equipment in Q1 2012. | 2012-02-23 15:25 | 2012-02-23 15:25 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2012 | Q1 | Q1 - 2012 | 6098 | 5651 | FALSE | 66 | Construction activity will increase as make-ready ramps up, bringing the project closer to performance goals. | 70 | Project Management | Project management work continued as anticipated, providing construction management, procurement, and general oversight. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 99 | We anticipate receiving Certificates of Occupancy (COs) for the Espanola and Santa Fe POPs. The CO for the Los Alamos POP may take additional time due to changes requested in the EA Addendum. | 98 | All major equipment orders are already complete, although it is possible that some smaller elements (servers, additional CPE, subscriber aggregation equipment) might be needed after the upcoming reporting period, so 2% of the budget is being reserved. | 62 | Construction and procurement activities started late June 2011, due to delays with the FONSI. Since initiating construction, there have been some additional challenges with pole attachment applications, make-ready, and materials supply, all of which have been resolved. Construction is now ramping up and will continue to do so in the upcoming reporting period. Upcoming activities include significant focus on pole replacements, aerial fiber installation, and completing underground construction. | 50 | Core routing equipment and additional CPE will be installed in the upcoming reporting period, to prepare for limited network activation in Q3 2012. | 50 | We forecast that 50% of the network testing will be complete in the upcoming reporting period. | 2012-05-15 13:51 | 2012-05-15 13:51 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2012 | Q2 | Q2 - 2012 | 7252 | 6253 | FALSE | 89 | Construction activity consistently ramping up closer to baseline projections. | 80 | Project Management | Project management work continued as anticipated, providing construction management, procurement, and general oversight. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 75 | Construction and procurement activities started late June 2011, due to delays with the FONSI. Since initiating construction, there were some additional challenges with pole attachment applications, make-ready, and materials supply, all of which have been resolved. Construction in now well underway and will continue to meet our revised quarterly projections. Upcoming activities include completing Phase I construction and beginning Phase II (route changes). Phase II construction will be dependent upon approval of the route changes proposed in the EA Addendum. | 75 | CAI equipment deployment will be completed for Phase I locations and the core routing equipment will be installed, tested, and activated in the secondardy POP. | 70 | Network testing will be completed on Phase I construction, which represents approximately 70% of the overall network to be deployed. | 2012-08-27 13:59 | 2012-08-27 13:59 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2012 | Q3 | Q3 - 2012 | 7910 | 6659 | FALSE | 92 | Project close-out draws near as construction activity focuses on routes approved in the EA Addendum. | 90 | Project Management | Project management work should continue as planned, providing construction management, procurement, and general oversight. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 90 | Construction and procurement activities started late June 2011, due to delays with the FONSI. Since initiating construction, there were some additional challenges with pole attachment applications, make-ready, and materials supply, all of which have been resolved. Construction in now well underway and will continue to meet our revised quarterly projections. Upcoming activities are focused on building the route changes authorized under the EA Addendum. | 100 | Complete | 80 | The majority of network testing will be completed in the upcoming reporting period, reflective of the route changes completed. | 2012-11-15 19:24 | 2012-11-15 19:24 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2012 | Q4 | Q4 - 2012 | 9034 | 7803 | FALSE | 98 | Per descriptions below | 95 |  | Project management work should continue as planned, providing construction management, procurement, and general oversight. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 95 | Construction and procurement activities started late June 2011, due to delays with the FONSI. Since initiating construction, there were some additional challenges with pole attachment agreements, applications, and pole replacements. Construction in now near completion and continue to closely meet our revised quarterly projections. Upcoming activities are focused on completing the route changes authorized under the EA Addendum. | 100 | Complete | 90 | The majority of network testing will be completed in the upcoming reporting period, reflective of the route changes completed. | 2013-02-27 16:17 | 2013-02-27 16:17 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2013 | Q1 | Q1 - 2013 | 10046 | 8577 | FALSE | 98 | per description below | 98 | Project Management | Customary Project Management will continue, such as construction oversight, verification, testing, and reporting on completed network segments, with a minimal reserve for the final project close-out activities. | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 98 | Testing will continue on completed network segments, with a minimal reserve for the final project close-out activities. | 2013-06-03 11:49 | 2013-06-03 11:49 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2013 | Q2 | Q2 - 2013 | 10528 | 8917 | FALSE | 100 | Complete based project activities and reference to budget | 100 | Project Management | Complete based project activities and reference to budget | 100 | Complete based project activities | 100 | Complete based project activities | 100 | Complete based project activities | 100 | Complete based project activities | 100 | Complete based project activities | 100 | Complete based project activities | 100 | Complete based project activities and reference to budget | 100 | Complete based project activities | 100 | Complete based project activities | 2013-08-08 15:14 | 2013-08-08 15:14 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | 2013 | Q3 | Q3 - 2013 | 12058 | 10217 | FALSE | 100 | The overall project is completed at 100%, The actual spent was 102.95% of the original planned budget as NCNMEDD made additional match contributions. | 100 | Project Management | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 100 | Award end date 9/30/13. | 2014-04-22 12:23 | 2014-04-22 12:23 | 7089 | 7089 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570117 | 2010 | Q4 | Q4 - 2010 | 1318 | 2342 | FALSE | 18 | NA | 0 | 0 | NA | 100 | NA | 70 | NA | 70 | NA | 70 | NA | 0 | NA | 20 | NA | 10 | NA | 20 | NA | 10 | NA | 2011-02-22 20:48 | 2011-02-22 20:48 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2011 | Q1 | Q1 - 2011 | 2036 | 2763 | FALSE | 38 | na | 0 |  | na | 100 | na | 90 | na | 90 | na | 90 | na | 0 | na | 35 | na | 30 | na | 35 | na | 25 | na | 2011-05-16 10:39 | 2011-05-16 10:39 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2011 | Q2 | Q2 - 2011 | 3260 | 3392 | FALSE | 38 | We are behind schedule due to the fiber installation RFP being released again. Fiber is in high demand at this time due to all the projects and other various reasons. Fiber demand may play a part in the project being off target. | 0 |  | na | 100 | na | 90 | We are behind schedule due to the fiber installation RFP being released again. We decided to complete our project in phases. The team had to rework network design to best fit phase 1, 2, & 3. | 90 | We are behind schedule due to the fiber installation RFP being released again. We awarded a contract for the permitting & engineering in quarter three. We hope to have all the permitting/drawings completed by the end of the third quarter. The SCDOT will then approve the drawings and then the permits will be issued. We hope to be on target by the end of the fourth quarter. | 90 | We are behind schedule due to the fiber installation RFP being released again. We awarded a contract for the permitting & engineering in quarter three. We hope to have all the permitting/drawings completed by the end of the third quarter. The SCDOT will then approve the drawings and then the permits will be issued. We hope to be on target by the end of the fourth quarter. | 0 | na | 35 | We are behind schedule due to the fiber installation RFP being released again. We are working with Procurement Office to get a Request for Proposal/Bid out to equipment vendors at this time. We hope to have that completed by the end of the third quarter. | 30 | We are behind schedule due to the fiber installation RFP being released again. This has delayed the network build. | 35 | We are behind schedule due to the fiber installation RFP being released again. This has delayed the equipment deployment. | 25 | We are behind schedule due to the fiber installation RFP being released again. This has delayed the network build and equipment deployment, so in turn there is not any network testing necessary at this time. | 2011-08-22 14:17 | 2011-08-22 14:17 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2011 | Q3 | Q3 - 2011 | 4194 | 3945 | FALSE | 37 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. Fiber has been an issue but we hope to have large shipments in the beginning of 2012. We will release the request for proposals for Phase 2 and 3. Hopefully this will help us get back on track. | 0 |  | na | 100 | na | 95 | na | 95 | na | 95 | na | 0 | na | 60 | na | 45 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. Fiber has been an issue but we hope to have large shipments in the beginning of 2012. We will release the request for proposals for Phase 2 and 3. Hopefully this will help us get back on track. | 50 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. Fiber has been an issue but we hope to have large shipments in the beginning of 2012. We will release the request for proposals for Phase 2 and 3. Hopefully this will help us get back on track. | 40 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. Fiber has been an issue but we hope to have large shipments in the beginning of 2012. We will release the request for proposals for Phase 2 and 3. Hopefully this will help us get back on track. | 2011-11-21 16:28 | 2011-11-21 16:28 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2011 | Q4 | Q4 - 2011 | 5390 | 5068 | FALSE | 45 | We are behind schedule. This will be an ongoing problem since we had to re-release the RFP during the 2nd quarter of 2011. The crews have accomplished a lot in the 4th quarter. We hope to continue great progress and meet our goals in the quarters to come. | 0 |  | na | 100 | na | 95 | na | 95 | na | 95 | na | 0 | na | 70 | na | 50 | We are behind schedule. This will be an ongoing problem since we had to re-release the RFP during the 2nd quarter of 2011. The crews have accomplished a lot in the 4th quarter. We hope to continue great progress and meet our goals in the quarters to come. | 45 | We are behind schedule. This will be an ongoing problem since we had to re-release the RFP during the 2nd quarter of 2011. The crews have accomplished a lot in the 4th quarter. We hope to continue great progress and meet our goals in the quarters to come. | 40 | We are behind schedule. This will be an ongoing problem since we had to re-release the RFP during the 2nd quarter of 2011. The crews have accomplished a lot in the 4th quarter. We hope to continue great progress and meet our goals in the quarters to come. | 2012-02-29 11:45 | 2012-02-29 11:45 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2012 | Q1 | Q1 - 2012 | 6050 | 5624 | FALSE | 65 | Right of way issues may cause a slight delay in overall project. Receiving all equipment and materials necessary may cause certain delays of overall project. | 0 |  | na | 100 | na | 95 | na | 95 | na | 95 | na | 0 | na | 80 | na | 70 | na | 60 | This will depend on the Network Operation Centers being setup and operational. It will also depend on construction of network. | 30 | This will depend on the Network Operation Centers being setup and operational. It will also depend on construction of network. | 2012-05-14 09:09 | 2012-05-14 09:09 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2012 | Q2 | Q2 - 2012 | 7212 | 6233 | FALSE | 90 | na | 0 |  | na | 100 | na | 95 | na | 95 | na | 95 | na | 0 | na | 90 | na | 80 | na | 90 | na | 80 | na | 2012-08-22 16:01 | 2012-08-22 16:01 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2012 | Q3 | Q3 - 2012 | 8046 | 6729 | FALSE | 95 | na | 0 |  | na | 100 | na | 100 | na | 95 | na | 95 | na | 0 | na | 100 | na | 90 | na | 100 | na | 85 | na | 2012-11-26 15:09 | 2012-11-26 15:09 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2012 | Q4 | Q4 - 2012 | 9122 | 7894 | FALSE | 95 | Due to installation of fiber and equipment being installed in anchors through the first quarter of 2013, testing may be pushed back til the following quarter. | 0 |  | na | 100 | na | 100 | na | 100 | na | 100 | na | 0 | na | 100 | na | 100 | na | 100 | na | 95 | Due to installation of fiber and equipment being installed in anchors through the first quarter of 2013, testing may be pushed back til the following quarter. | 2013-03-04 14:02 | 2013-03-04 14:02 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2013 | Q1 | Q1 - 2013 | 9698 | 8382 | FALSE | 99 | The teams feels that we will be so close to our baseline goal, but may need a few more weeks to determine all equipment is operating properly. | 0 |  | na | 100 | na | 100 | na | 100 | na | 100 | na | 100 | na | 100 | na | 100 | na | 100 | na | 99 | The teams feels that we will be so close to our baseline goal, but will need a few more weeks to determine all equipment is operating properly. | 2013-05-13 14:57 | 2013-05-13 14:57 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2013 | Q2 | Q2 - 2013 | 10656 | 8988 | FALSE | 100 | na | 100 |  | na | 100 | na | 100 | na | 100 | na | 100 | na | 0 | na | 100 | na | 100 | na | 100 | na | 100 | na | 2013-08-20 12:18 | 2013-08-20 12:18 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570117 | 2013 | Q3 | Q3 - 2013 | 11510 | 9635 | FALSE | 100 | N/A | 100 | NA | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 0 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 2013-12-20 09:16 | 2013-12-20 09:16 | 6058 | 6058 | Oconee County | TRUE
NT10BIX5570118 | 2010 | Q4 | Q4 - 2010 | 794 | 1830 | FALSE | 25 | Overall project delayed 45-6- days due to delay in acquisition of engineering services. | 0 | N/A | N/A | 90 | Environmental delayed 45-60 days beyond initial timelines due to re-assignment of engineering contract. Current engineers proceeding ahead of schedule of preparation of draft environmental assessment. | 90 | Engineering design and bid package due this quarter | 90 | Acquisition on schedule | 90 | Acquisition on schedule | 50 | Acquisition of needed sites on schedule | 50 | Engineering design and bid package due this quarter | 10 | Construction expected to begin next quarter (Spring 2011) | 0 | Not planned in current quarter | 0 | Not planned in current quarter | 2011-01-28 15:31 | 2011-01-28 15:31 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2011 | Q1 | Q1 - 2011 | 2342 | 2916 | FALSE | 20 | Environmental review complete; bids released; construction begin by end of quarter. Overall delays due to engineering re-assignment. | 0 |  | N/A | 100 | Environmental review complete. Overall delays due to engineering re-assignment. | 100 | Design complete; bids to be released this quarter. | 90 | Rights of way secured for major segments; railways pending | 90 | Permits secured for major segments; railways pending | 90 | Sites secured; pending delivery of co-location buildings and install of services. | 50 | Network equipment to be ordered; held pending construction schedule. | 20 | Network build to commence by end of quarter; delayed due to environmental assessments. Construction and network build to commence by end of quarter; delayed due to engineering and environmental. | 0 | Not planned in current quarter | 0 | Not planned in current quarter | 2011-05-26 12:50 | 2011-05-26 12:50 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2011 | Q2 | Q2 - 2011 | 3210 | 3366 | FALSE | 50 | Significant construction to be accomplished during quarter. Prior delays due to engineering re-assignment. | 0 |  | N/A | 100 | Environmental review complete. Prior delays due to engineering re-assignment. | 100 | Design complete; equipment to be secured and tested as construction schedule allows. | 100 | Rights of way secured. | 100 | Permits to be completed. Prior delays due to railroad permit demands. | 90 | Sites secured; pending delivery of co-location buildings and install of services | 80 | Network equipment on order; testing and installation pending construction schedule. | 40 | Significant network build to be accomplished by end of quarter; prior delays due to delayed engineering and environmental assessments. | 40 | Equipment deployment and testing to coincide with construction schedule. | 40 | Segments of network to be tested as construction deployment allows. | 2011-08-18 17:38 | 2011-08-18 17:38 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2011 | Q3 | Q3 - 2011 | 4326 | 4013 | FALSE | 72 | Project is on schedule for completion. | 0 |  | N/A | 100 | Environmental review is completed. | 100 | Design modifications, if any, will be completed. | 100 | Rights of way secured | 100 | Kansas City Southern is the only permit remaining; will be completed. | 100 | Sites and colo buildings secured; pending delivery and setup. | 100 | Network switch/router equipment is remaining; will be received | 65 | Construction will be substantially complete with network fiber lighted for northern sections of the route projected. | 65 | Equipment deployment and testing to coincide with construction schedule. | 65 | Segments of network to be tested as construction deployment allows. | 2011-11-29 16:31 | 2011-11-29 16:31 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2011 | Q4 | Q4 - 2011 | 5216 | 4884 | FALSE | 84 | Project is on schedule for completion | 0 | N/A | N/A | 100 | Environmental review is completed | 100 | Design modifications, if any in construction completion, will be completed | 100 | Rights of way secured | 100 | Permits secured | 100 | Co-location buildings projected to be compled | 100 | Network switch/routing equipment to be secured | 90 | Lighted fiber to be in place; remaining percentage completion to be for anchor insitutions | 90 | Remaining percentage completion to be for anchor institutions | 90 | Primary route fiber testing to be completed. Remaining percentage completion to be for anchor institutions. | 2012-02-23 15:06 | 2012-02-23 15:06 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2012 | Q1 | Q1 - 2012 | 6282 | 5743 | FALSE | 72 | Project is on schedule for original planned completion. Project modifications noted above may extend final completion date, but will not impede services schedules. | 0 | N/A | N/A | 100 | Original environmental review is complete. Additional environmental review may be required due to project modification being requested. The percent complete is noted at 100% in anticipation there will be no additional environmental requirements. | 95 | Original network design will be completed. Modifications in design may be required due to project modification being requested. | 100 | Rights of way secured for original design and planned project modification | 100 | Permits secured for original design and planned project modification | 95 | Original site preparation will be completed. Minor additions due to planned project modification may be required. | 95 | Original equipment procurement will be completed. Equipment additions due to planned project modification will be required. | 90 | Original fiber network build will be completed. Planned project modification may require some network build modifications. Nexus has secured permission to add additional critical anchor institutions through cooperative agreement with the State. The additions will incorporate approximately 120 miles additional fiber to the network. These additions will be presented for approval through a project modification during the next quarter. | 90 | Original equipment deployment will be completed. Planned project modification will require additional equipment deployment. | 90 | Final network testing of all components will be extended due to additions from planned project modification. | 2012-05-24 13:47 | 2012-05-24 13:47 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2012 | Q2 | Q2 - 2012 | 7056 | 6155 | FALSE | 86 | Project is on schedule for original planned completion. Project modifications noted above may extend final completion date, but will not impede services schedules. | 0 |  | N/A | 95 | Original environmental review is complete. Additional environmental review may be required due to project modification being requested. The percent complete is noted at 100% based on the original project but proposed project modification may require additional environmental review. | 95 | Original network design is complete with minor modifications due to proposed project modification. | 100 | Rights of way secured for original design and planned project modification. | 95 | Permits secured for original design. Note proposed project modification will require permits from Core of Engineers and Levy Board. | 95 | Original site preparation will be completed. Minor additions due to planned project modification may be required. | 95 | Original equipment procurement is completed. Equipment additions due to planned project modification will be required. | 90 | Original fiber network build will be completed. Planned project modification may require some network build modifications. The additions will incorporate approximately 120 miles additional fiber to the network. These additions have been presented for approval through a project modification during the next quarter. | 95 | Original equipment deployment will be completed. Planned project modification will require additional equipment deployment. | 90 | Final network testing of all components will be extended due to additions from planned project modification. | 2012-08-14 11:49 | 2012-08-14 11:49 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2012 | Q3 | Q3 - 2012 | 8064 | 6738 | FALSE | 92 | Project is on schedule for original planned completion. Project modifications noted above may extend final completion date, but will not impede services schedules. | 0 | N/A | N/A | 95 | Original environmental review is complete. Additional environmental review is underway for proposed project modification. The percent complete is noted at 100% based on the original project but proposed project modification will require additional environmental review. | 95 | Original network design is complete with minor modifications due to proposed project modification. | 100 | Rights of way secured for original design and planned project modification. Additional right of way is being secured for railroad crossing in Arcadia with proposed project modification. | 95 | Rights of way secured for original design and planned project modification. Additional right of way is being secured for railroad crossing in Arcadia with proposed project modification. | 95 | Original site preparation will be completed. Minor additions due to planned project modification may be required. | 95 | Original equipment procurement is completed. Equipment additions due to planned project modification will be required. | 90 | Original fiber network build is completed. Planned project modification will require some network build modifications. The additions will incorporate approximately 120 miles additional fiber to the network. These additions have been presented for approval through a project modification during the next quarter. | 95 | Original equipment deployment will be completed. Planned project modification will require additional equipment deployment. | 90 | Final network testing of all components will be extended due to additions from planned project modification. | 2012-11-27 09:58 | 2012-11-27 09:58 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2012 | Q4 | Q4 - 2012 | 8930 | 7714 | FALSE | 97 | Project is on schedule for original planned completion. Project modifications noted above may extend final completion date, but will not impede services schedules. Overall project will be completed as scheduled. | 0 | N/A | N/A | 95 | Original environmental review is complete. Additional environmental review is underway for proposed project modification. The percent complete is noted at 100% based on the original project but proposed project modification will require additional environmental review. | 95 | Original network design is complete with minor modifications due to proposed project modification | 100 | Rights of way secured for original design and planned project modification. Additional right of way is being secured for railroad crossing in Arcadia with proposed project modification. | 95 | Rights of way secured for original design and planned project modification. Additional right of way is being secured for railroad crossing in Arcadia with proposed project modification | 95 | Original site preparation will be completed. Minor additions due to planned project modification may be required. | 95 | Original equipment procurement is completed. Equipment additions due to planned project modification will be required. Equipment has been staged at vendor warehouse awaiting release from project modification. | 90 | Original fiber network build is completed. Planned project modification will require some network build modifications. The additions will incorporate approximately 120 miles additional fiber to the network. These additions have been presented for approval through a project modification during the next quarter | 95 | Original equipment deployment will be completed. Planned project modification will require additional equipment deployment. | 90 | Final network testing of all components will be extended due to additions from planned project modification | 2013-02-25 11:34 | 2013-02-25 11:34 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2013 | Q1 | Q1 - 2013 | 9858 | 8466 | FALSE | 97 | Overall project with program modification will be completed as scheduled | 0 | N/A | N/A | 100 | Environmental assessment for original project and program modification is completed | 100 | Network design will be completed at end of period. | 100 | Rights of way are completed. | 100 | Permits will be completed. | 100 | Site preparation will be completed. | 100 | Equipment procurement will be completed. | 100 | Network build will be completed. | 100 | Equipment deployment will be completed. | 95 | Network testing will be essentially completed with possible closeout changes for CAI sites and network providers. | 2013-05-21 18:42 | 2013-05-21 18:42 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2013 | Q2 | Q2 - 2013 | 10748 | 9038 | FALSE | 100 | Overall project with program modification will be completed as scheduled | 0 | N/A | N/A | 100 | Environmental assessment for original project and program modification is completed | 100 | Network design will be completed at end of period. | 100 | Rights of way are completed. | 100 | Permits will be completed. | 100 | Site preparation will be completed. | 100 | Equipment procurement will be completed. | 100 | Network build will be completed. | 100 | Equipment deployment will be completed. | 100 | Network testing will be essentially completed with possible closeout changes for CAI sites and network providers. | 2013-08-26 17:51 | 2013-08-26 17:51 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | 2013 | Q3 | Q3 - 2013 | 12064 | 10226 | FALSE | 100 | Project completed | 0 | N/A | N/A | 100 | Project completed | 100 | Project completed | 100 | Project completed | 100 | Project completed | 100 | Project completed | 100 | Project completed | 100 | Project completed | 100 | Project completed | 100 | Project completed | 2014-04-24 00:18 | 2014-04-24 00:18 | 6037 | 6037 | Nexus Systems, Inc. | TRUE
NT10BIX5570119 | 2010 | Q4 | Q4 - 2010 | 1018 | 2063 | FALSE | 25 | n/a | 0 |  | n/a | 100 | n/a | 100 | n/a | 35 | n/a | 30 | n/a | 35 | n/a | 30 | n/a | 5 | n/a | 0 | n/a | 0 | n/a | 2011-02-09 12:21 | 2011-02-09 12:21 | 6072 | 6072 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2011 | Q1 | Q1 - 2011 | 2122 | 2806 | FALSE | 5 | Project remains behind due to delays in start of construction from required environmental assessment. | 0 | n/a | n/a | 99 | We expect our FONSI to be issued in this quarter. Per the programmatic agreement with NTIA and the Ohio Historic Preservation Office, there will be continued assessment of POP sites as they are identified. | 10 | Engineering of lateral routes will be finalized as we begin to sign up CAIs. | 98 | Estimate in baseline project milestones is low. Most ROWs for this project are in utility corridors, where we have permission to build already. | 10 | Permits for rail and road crossings have been submitted, so we are farther along than expected. | 10 | Identification and acquisition of POP sites has been faster than projected and will continue this quarter. | 50 | Contracts for fiber materials and electronics were awarded in late Q1. First orders of equipment and fiber will be placed in this quarter. | 2 | Baseline projected 15%; however, we assumed we would be cleared for construction earlier. This assumes begin of construction in June. | 2 | Baseline projected 30%, which is inaccurate. Equipment deployment will run roughly concurrent with network build. | 2 | Baseline projected 30%, which is inaccurate. Equipment deployment will run roughly concurrent with network build. | 2011-05-18 10:24 | 2011-05-18 10:24 | 6072 | 6072 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2011 | Q2 | Q2 - 2011 | 3188 | 3354 | FALSE | 19 | Project will remain behind projected schedule due to delays in start of construction by environmental assessment. | 0 | n/a | n/a | 98 | We will continue to assess POP sites and routes as needed. | 25 | Engineering of lateral routes will begin as we begin to sign up CAIs. | 99 | Estimate in baseline project milestones is low. Most ROWs for this project are in utility corridors, where we have permission to build already. | 25 | We will continue to secure permits for rail and road crossings. Permitting is budgeted as part of network design. | 25 | Identification and acquisition of POP sites will continue. | 50 | Large orders for fiber and materials were placed late in the quarter. Continued orders will pace network construction. | 24 | Baseline projected 30%, but that assumed we would be cleared for construction earlier. Construction of the backbone will ramp up in this quarter. | 53 | We expect to have deployed equipment to 18 of 34 POP sites by the end of the Q3. | 53 | Baseline projected 30%, which is inaccurate. Testing will run roughly concurrent with equipment deployment. | 2011-08-18 11:25 | 2011-08-18 11:25 | 6072 | 6072 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2011 | Q3 | Q3 - 2011 | 4108 | 3897 | FALSE | 37 | Significant progress will be made this quarter to catch baseline projections. | 0 |  | n/a | 98 | Continued assessment with engineers and Environmental Assessment (EA) consultant as routes are finalized. | 72 | As final backbone routes are completed, engineering will turn toward the lateral build to begin to reach CAIs. | 98 | We continue to be ahead of projections due to our relationship with electric provider. | 72 | Included in network design. | 72 | Included in network design. | 81 | Procurement will see the largest jump in percentage as we receive and approve significant invoices from vendor. | 25 | While our accelerated build schedule will bring us closer to baseline, we will probably have some weather issues keeping us slightly behind.. | 20 | As we have just broken ground on our first PoP the equipment deployment is behind and will pick up. | 20 | Testing will run roughly concurrent with the network build. | 2011-11-17 12:48 | 2011-11-17 12:48 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2011 | Q4 | Q4 - 2011 | 5270 | 4936 | FALSE | 57 | With most hurdles out of the way, Horizon will catch and bypass baseline projections within the next six months. | 0 | n/a | n/a | 98 | Continues assessment with engineers and Environmental Assessment (EA) consultant as routes are finalized. | 78 | The fiber backbone should be complete by the end of this quarter. Work will begin on laterals. | 98 | We have an agreement with an electric provider which has provided permission for us to use their Rights of Way (ROWs). We are experiencing difficulties with another utility when we do need to use their poles. Hopefully that will be resolved soon. | 78 | Included in Network Design. | 78 | Included in Network Design. | 92 | Horizon expect most equipment will be purchased by the end of this quarter. | 50 | Horizon expects to finish the fiber backbone by the end of this quarter. | 45 | Equipment Deployment will pick up as more Points of Presence (POPs) are completed. | 40 | Testing will run fairly concurrent with equipment deployment. | 2012-02-26 14:09 | 2012-02-26 14:09 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2012 | Q1 | Q1 - 2012 | 6174 | 5689 | FALSE | 67 | With our major permitting issue out of the way, Horizon will make significant progress in the next six months. | 0 | n/a | n/a | 98 | Horizon continues the ongoing assessments in coordination with our engineering and environmental assessment consultants. | 98 | Design of the laterals will make significant progress during this term. | 98 | With our largest hurdle resolved most rights-of-way will be perfunctory. | 98 | Included in Network Design. | 98 | Included in Network Design. | 90 | Horizon is only paying for electronics after they have been installed. | 60 | Horizon expects to have 700 miles of the backbone finished and 125 miles of laterals built. | 50 | Equipment Deployments roughly follows network build. | 45 | Testing runs fairly concurrent with equipment deployment. | 2012-05-18 10:47 | 2012-05-18 10:47 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2012 | Q2 | Q2 - 2012 | 7122 | 6188 | FALSE | 76 | Horizon reaches the two-thirds milestone during the first month of this quarter as is required by July 31. | 0 | n/a | n/a | 98 | Horizon continues the ongoing assessments in coordination with our engineering and environmental assessment consultants. | 98 | Distribution laterals are in the final stages of design and engineering. | 98 | Rights-of-way are virtually complete with very few issues remaining. | 98 | Included in Network Design. | 98 | Included in Network Design. | 92 | All electronics have been received and installed, we will pay for them as they are tested and come online. | 60 | Horizon expects to build approximately 200 miles of backbone and another 100 miles of distribution fiber. | 62 | Is jumping ahead of Network Build, but waits for fiber to come online. | 45 | Testing waits for fiber to connect the electronics. | 2012-08-17 16:21 | 2012-08-17 16:21 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2012 | Q3 | Q3 - 2012 | 8170 | 6795 | FALSE | 87 | Our largest hurdle this quarter will be the lack of crews available to do power make-ready due to Hurricane Sandy. | 0 | n/a | n/a | 98 | Horizon will continue the ongoing assessments in coordination with our engineering and environmental assessment consultants. | 96 | Finalizing distribution lateral design. | 98 | Almost complete. | 96 | Included in Network Design. | 96 | Included in Network Design. | 92 | Payment occurs after they are tested and come online. | 70 | We expect the build to reach 900 miles of fiber by the end of the quarter. | 70 | Waits for fiber to come online. | 55 | Waits for fiber for the connections to test. | 2012-11-30 10:30 | 2012-11-30 10:30 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2012 | Q4 | Q4 - 2012 | 8972 | 7752 | FALSE | 93 | Horizon will continue to look for ways to increase our build rate and still minimize costs associated with the build. | 0 | n/a | n/a | 98 | Continues as necessary. | 95 | Reaching final stages. | 98 | Continues as necessary. | 95 | Included in Network Design. | 95 | Included in Network Design. | 92 | In line with baseline. | 75 | As construction continues to make steady progress, we expect to reach the 1200 mile mark in our build. | 70 | Awaits backbone completion to bring online. | 60 | Awaits backbone completion to bring online. | 2013-02-26 13:51 | 2013-02-26 13:51 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2013 | Q1 | Q1 - 2013 | 10012 | 8551 | FALSE | 97 | Expect to serve 20 additional CAIs this quarter. | 0 | n/a | n/a | 100 | Continues as necessary. | 100 | Virtually complete. | 100 | Continues as necessary. | 100 | Included in Network Design. | 100 | Included in Network Design. | 100 | With three additional POPs online this category will go from 106% to 110%. | 85 | Expect to have 1250 miles built by the end of the quarter. | 88 | We have three POPs scheduled to be turned up this quarter. | 75 | Awaits backbone completion to bring online. | 2013-05-30 16:22 | 2013-05-30 16:22 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2013 | Q2 | Q2 - 2013 | 10830 | 9087 | FALSE | 100 | Virtually all construction should be completed and final POPs brought online. AARs will be filed during this quarter. | 0 | n/a | n/a | 100 | Continues as needed. | 100 | Virtually complete. | 100 | Continues as needed. | 100 | Included in Network Design. | 100 | Included in Network Design. | 100 | Currently at 106%, will rise as final POPs are brought online. | 100 | Virtually complete. | 98 | Final POPs are expected to be brought online over the next two quarters. | 95 | Awaits backbone completion to bring online in order to test. | 2013-08-30 16:14 | 2013-08-30 16:14 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2013 | Q3 | Q3 - 2013 | 11362 | 9484 | FALSE | 100 | The final 17.5 miles will be built this quarter as we wrap up network construction. Most, if not all, of these will be in areas where previous issues (make-ready, easement, permit, etc) blocked completion. This quarter will be spent on resolving those issues. | 100 | OARnet | This category is complete. | 100 | Complete upon acceptance of distribution route changes. | 100 | Complete. | 0 | n/a | 0 | n/a | 0 | n/a | 100 | All electronics have been received and installed. | 100 | The vast majority of the network has been completed. All that remains are those small pieces where make-ready, easement, permit, etc issues have blocked sections. This quarter will be spent on resolving those issues. | 100 | When final backbone routes are finished the final provisioning can be completed. | 0 | n/a | 2013-11-22 17:27 | 2013-11-22 17:27 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | 2013 | Q4 | Q4 - 2013 | 11914 | 10080 | FALSE | 100 | The project is substantially complete and will be at approximately 108% of budget. | 100 | OARnet | This category is complete at 85% of budget. | 100 | This category is complete. | 100 | This category is complete at 113% of budget. | 0 | n/a | 0 | n/a | 0 | n/a | 100 | Equipment procurement will be 118% of budget. | 100 | Construction is complete at 106% of budget | 100 | This category will be complete. | 0 | n/a | 2014-02-27 17:02 | 2014-02-27 17:02 | 6021 | 6021 | Horizon Telecom, Inc. | TRUE
NT10BIX5570120 | 2010 | Q4 | Q4 - 2010 | 676 | 1705 | FALSE | 8 | N/A | 0 |  | N/A | 75 | The EA will be completed within the 6 months timeframe required by the grant. We do not note 100% completion though until FONSI is received | 53 | N/A | 53 | Lessons learned from BTOP 1 provided valuable information in applying for ROWs for this award; namely, ensuring that Encroachment Agreements include all required elements and documents, at the time of submission, which we anticipate will expedite the process of ROWs for this grant. | 26 | Lessons learned from BTOP 1 provided valuable information in applying for permits required for this award; namely, ensuring that permit applications include all required elements and documents, at the time of submission, which we anticipate will expedite the processing or permits for this grant. | 10 | The goal is to identify all HUT locations within this quarter. | 0 | N/A | 1 | N/A | 0 | N/A | 0 | N/A | 2011-01-28 08:35 | 2011-01-28 08:35 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2011 | Q1 | Q1 - 2011 | 1886 | 2688 | FALSE | 5 | We overestimated expenses related to engineering to this point. Until procurement of materials commences and construction activities start, it will be difficult to pass our estimates for expenditures. | 0 |  | na | 100 | If we receive the FONSI in the 4th quarter we will meet the projection. | 60 | We potentially will be back on track related to this activity, but given where we're at now, we choose to remain conservative. If behind in 4th quarter, we will be at projection by Y2Q1. | 30 | This activity closely tracks the network design. Given some of the pace of permitting at the start of Q4, we believe we'll be ahead of pace on this activity by end of quarter. | 10 | Construction permits come with successful ROW completion and review by NC DOT in the majority of the cases. Due to applications starting to happen in broader basis by completion of this report in April we believe we'll have closure on some by end of June, but given late start, will still be behind pace. We will recover by end of Y2Q1 we believe. | 5 | Discussions with the community colleges that are providing locations for the project are ongoing. We believe by end of the quarter we will have material agreement with all of these locations which is a small portion of site preparation. The exercised right to locate here from a legal standpoint is a part of the overall activity. | 2 | A small amount of equipment procurement may commence in June to light some of the IRU'd fiber in late summer, but cannot commence until FONSI, so this is not a given. Given this uncertainty, we project we'll be behind pace slightly. | 9 | With execution of IRU's and completion of some of the BTOP1 fiber builds, we believe we'll have approximately 150 of the planned miles secured and thus slightly ahead of schedule. | 0 | Given where we're at in the receipt of the FONSI and design, we don't anticipate deployment by end of June, meaning we're behind. | 9 | With execution of IRU's and completion of some of the BTOP1 fiber builds, we believe we'll have approximately 150 of the planned miles secured. We will test these fibers as we receive/complete them. | 2011-05-04 13:30 | 2011-05-04 13:30 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2011 | Q2 | Q2 - 2011 | 2948 | 3231 | FALSE | 20 | Even with a delay to start of construction, we believe that we will recover enough in the next quarter to be back on schedule. If not next quarter, we have no concerns with this being true by the following quarter. | 0 |  | N/A | 100 | N/A | 100 | N/A | 75 | Based on the timing of getting permits applied for, we expect to be right at schedule on this. | 65 | Due to a slower approval process with permitting agencies (primarily NC DOT), we project we will still be slightly behind the original forecast of around 76% complete. | 15 | We will see some more activity toward placement of huts, but it will take us two quarters to catch up due to a slower start. This does not impact our planned execution of the project as we will prioritize these toward areas where construction will start on the physical fiber. | 13 | If we complete execution of land easements and IRU's we believe we can in the quarter, this will drive some of our equipment procurement needs as it relates to huts. If that occurs, even with the delay to the start of the project, we expect to be right at our projection on this. | 12 | If all IRU's that are planned get executed, we will be able to meet our projection. | 13 | If we complete execution of land easements and IRU's we believe we can in the quarter, this will drive some of our equipment procurement needs as it relates to huts. If that occurs, even with the delay to the start of the project, we expect to be right at our projection on this. | 12 | We will test our fibers that we IRU as we acquire them, and if the IRU's happen, we will meet this projection. With the ramp up start time of our project starting, the projections to the baseline for this and many other areas of the project identified here are a bit fluid. | 2011-08-08 09:47 | 2011-08-08 09:47 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2011 | Q3 | Q3 - 2011 | 4226 | 3961 | FALSE | 20 | Even with a delay to start of construction, we believe that we will recover sufficiently in the next quarter to be back on schedule if we close on IRU's that we anticipate and can realize between 50-75 miles of conduit construction per month as we ramp up our construction efforts. Once at full capacity, we have advised our contractors that we want to meet 100 miles a month if possible. | 0 |  | NA | 100 | N/A | 85 | With some of the reroutes not officially approved to begin formal design work, we likely will have this effort slip in to the following quarter, where we would anticipate it being completed then. | 85 | While this is behind our baseline, with the approach we're now taking, we believe it in line with where we will be in the process. We would anticipate closing all of these activities out in first quarter of FY12. Because the areas not yet applied for are lower in priority for construction, being behind in baseline here is not of material concern to us in completing the project. | 80 | While this is behind our baseline, with the approach we're now taking, we believe it in line with where we will be in the process. We would anticipate closing all of these activities out in first quarter of FY12. Because the areas not yet applied for are lower in priority for construction, being behind in baseline here is not of material concern to us in completing the project. | 50 | We will start placement of huts in this quarter. Our desire is to have all easements required by end of the quarter. Acquisition of the easements is in many cases more than half of the challenge in getting the huts established. As such, if we secure all of them, we will consider this element half completed. We forecast all huts being placed by summer of 2012. | 1 | We anticipate making final selection of the equipment to be utilized in this quarter. We forecasted equipment expenditures too quickly based on how our selection criteria through an RFP and Proof of Concept lab worked out. Due to this, we likely will not procure any equipment in this quarter, but would anticipate making a great deal of orders in the first quarter of 2012, and be fully caught up on orders by summer of 2012, at least in terms of orders committed. | 33 | We anticipate building between 125-150 miles of the conduit during this quarter, and finalizing IRU acquisitions on another approximately 250 miles, which would put us at about 550 miles of our project, or about 33%. If we we are able to realize that amount of rate, we would be ahead of our baseline. | 0 | We anticipate making final selection of the equipment to be utilized in this quarter. We forecasted equipment expenditures too quickly based on how our selection criteria through an RFP and Proof of Concept lab worked out. Due to this, we likely will not procure any equipment in this quarter, but would anticipate making a great deal of orders in the first quarter of 2012, and be fully caught up on orders by summer of 2012, at least in terms of orders committed. | 0 | We test our fibers as we acquire or build, and as such we correspond projection for this line item relative to the project completion to be 67% by July 2012 and 100% by March 2013. We did not have significant budget as part of this line item in the budget as these costs were part of the construction line item and to date have not incurred expense for this. | 2011-11-22 15:07 | 2011-11-22 15:07 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2011 | Q4 | Q4 - 2011 | 4972 | 4647 | FALSE | 34 | We will be behind in expenditures to baseline by approximately 10% for this quarter. The winter months with required shutdowns around holiday's with DOT and slower permitting will impact the amount of work performed in late December and early January, and thus billings that will occur from our contractors. We expect to be back on pace in February and that will allow us to recover from this variance to budget by the 3rd quarter of 2012. Percent completion is based on dollars spent relative to budget. | 0 | NA | NA | 100 | NA | 90 | Depending on timing of the reroute reviews from NTIA, this task could show 100% completion. Percent completeness is based on acquisition and design of miles relative to approved route. | 90 | Depending on timing of the reroute reviews from NTIA, this task could show 100% completion. Percent completeness is based on number of rights of way acquired relative to number required for completion. | 90 | Depending on timing of the reroute reviews from NTIA, this task could show 100% completion. Percent completeness is based on number of construction permits acquired relative to number required for completion. | 22 | We will still be ahead of schedule and expect to have the first 4-6 locations fully implemented per their now completed construction designs. | 50 | Once the vendor has been selected, we anticipate making a large first order so that we can begin receiving the equipment in advance of deployment. We are a bit concerned about potential manufacturing delays and due to that we anticipate making a large order initially for the backbone equipment. | 33 | We anticipate being right at baseline relative to dollars or slightly ahead based on forecasted efforts for the spring. | 15 | We will be behind to baseline for this metric due to a slower than anticipated closing of IRU's and construction start. Deployment of equipment moves fairly briskly, however, and we anticipate recovering in the next 2-3 quarters. | 25 | As more of our constructed fiber is deployed, we anticipate catching up on this metric, but acknowledge we will continue to be behind the baseline for another quarter. | 2012-02-13 12:41 | 2012-02-13 12:41 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2012 | Q1 | Q1 - 2012 | 6102 | 5653 | FALSE | 61 | We anticipate being slightly behind to baseline for the end of June quarter. Some of this relates to slower start and ramping up to full construction. We also have discovered that our ability to forecast payment for the end of quarter for construction contractors trails by several weeks due to confirmation of completeness for what's being billed, all documentation required for Davis-Bacon, lien waivers, etc. such that we can't always book dollars by the end of the quarter. However, we believe from a reporting standpoint this will correct by the September 2012 reporting period to where we're ahead of baseline. | 0 | NA | N/A | 100 | This activity is forecasted to be completed. | 100 | This activity is forecasted to be completed. | 100 | This activity is forecasted to be completed. | 99 | We anticipate to still be working with the US Forest Service on access to the Nantahala by end of next reporting quarter. This is only for about 13 miles of the entire project so is not a concern to us at this time on our ability to deliver on the project. | 100 | This activity is forecasted to be completed. | 66 | We expect to be back above baseline as we will make some fairly significant initial purchases in this current quarter. | 56 | We anticipate being right at baseline relative to dollars or slightly ahead based on forecasted efforts for the spring. | 25 | We will be behind to baseline for this metric due to a slower than anticipated closing of IRU's and construction start. Deployment of equipment moves fairly briskly, however, and we anticipate recovering in the next 2-3 quarters and being behind in this metric is not a concern to us in being able to deliver on the project. Once fiber completes, we can deploy fairly quickly. | 50 | As more of our constructed fiber is deployed, we anticipate catching up on this metric, but acknowledge we will continue to be behind the baseline for another quarter, but are not concerned with it impacting our ability to deliver on the project. | 2012-05-15 14:39 | 2012-05-15 14:39 | 5748 | 5748 | MCNC | TRUE
NT10BIX5570120 | 2012 | Q2 | Q2 - 2012 | 7140 | 6197 | FALSE | 80 | Based on our baseline projection of 81%, we will be slightly below baseline, but essentially right on schedule. No concerns at this time with being able to deliver fully on the project. | 0 | N/A | N/A | 100 | We are forecasting this activity will be completed. | 100 | We are forecasting this activity will be completed. | 100 | We are forecasting this activity will be completed. | 100 | We are forecasting this activity will be completed. | 100 | We are forecasting this activity will be completed. | 100 | We are forecasting this activity will be completed. | 77 | We are forecasting at being ahead of baseline (71%) by the end of the next reporting quarter | 33 | While we will still be below baseline, activity will start picking up in the last quarter of the year and we anticipate being back on baseline by Y3Q2. The variance to baseline here is solely tied to the delay in time of ordering equipment to when we forecasted. | 77 | We have tied network testing to network miles acquired or built, and as such we will be slightly ahead of baseline established of 71%. | 2012-08-20 07:34 | 2012-08-20 07:34 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2012 | Q3 | Q3 - 2012 | 7926 | 6667 | FALSE | 87 | We anticipate being slightly behind baseline of 90% as it relates to dollars expended, but ahead in terms of actual effort related to work in the project. | 0 |  | N/A | 100 | This activity is 100% complete. | 100 | This activity is 100% complete. | 100 | This activity is 100% complete. | 100 | This activity is 100% complete. | 100 | We are forecasting this activity to be 100% complete. | 100 | We are forecasting this activity to be nearly 100% complete. The ordering of customer premise equipment is being performed in close proximity to the need which is a bit different than what was planned initially. | 87 | This activity will nearly be on schedule with baseline of 88%. | 50 | Equipment deployment to CAI's is taking longer than anticipated. We, however, expect to catch up on this when all fiber is in place toward end of the first quarter of 2013. | 90 | We expect to be at or ahead of baseline on this function by end of next quarter. | 2012-11-16 14:22 | 2012-11-16 14:22 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2012 | Q4 | Q4 - 2012 | 9068 | 7840 | FALSE | 93 | Based on dollars spent at the end of the March quarter we anticipate being ahead of baseline of 90%. | 0 |  | N/A | 100 | This activity is 100% complete. | 100 | This activity is 100% complete. | 100 | This activity is 100% complete. | 100 | This activity is 100% complete. | 100 | This activity is 100% complete. | 100 | We project this activity to be 100% complete next quarter | 99 | We project this activity to be at 99% complete next quarter, the only dependency being the Graham County build referenced above | 95 | We project this activity to be at baseline of 95% | 95 | We project this activity to be 100% complete next quarter | 2013-02-28 12:23 | 2013-02-28 12:23 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2013 | Q1 | Q1 - 2013 | 9752 | 8410 | FALSE | 99 | Dollar percent complete is 99%, but overall project is 100% complete | 0 |  | NA | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 2013-05-16 07:54 | 2013-05-16 07:54 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2013 | Q2 | Q2 - 2013 | 10542 | 8925 | FALSE | 100 | This activity is 100% complete | 0 |  | N/A | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 2013-08-09 15:17 | 2013-08-09 15:17 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570120 | 2013 | Q3 | Q3 - 2013 | 10998 | 9222 | FALSE | 100 | We came in under budget, so when measured against dollars budgeted, we are 99% complete. | 0 |  | N/A | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 97 | We came in under budget, so when measured against dollars budgeted, we are 97% complete. | 100 | This activity is 100% complete | 100 | This activity is 100% complete | 2013-10-29 11:54 | 2013-10-29 11:54 | 5479 | 5479 | MCNC | TRUE
NT10BIX5570122 | 2010 | Q4 | Q4 - 2010 | 1236 | 2267 | FALSE | 15 | On target. | 25 | IN-KIND | On target. | 0 | N/A. Exempt. | 50 | On target. | 0 | N/A. This project does not include this activity. | 5 | On target. | 5 | On target. | 30 | On target. RFP development for network and data center equipment should be near completion by the end of next quarter. Vendor selections and approvals are anticipated for next quarter and subsequent quarters. | 5 | On target. IRU negotiations with Level 3 and upstream engineering and provisioning requirements are expected to progress as planned through the next reporting period. | 0 | On target. | 0 | On target. | 2011-02-18 19:34 | 2011-02-18 19:34 | 5502 | 5502 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2011 | Q1 | Q1 - 2011 | 2232 | 2861 | FALSE | 16 | Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. In previous Performance Progress Reports, overall project progress was based on pending expenditures and committed costs as determined by work completed instead of actual budget expenditures. From this point forward we will report milestone completion percentages based on budget expenditures in the milestones calculation, incorporating both Federal funds and non-Federal share in-kind contributions where applicable in the milestones calculation, per Additional Guidance instructions. | 0 | In-Kind Capital Leases | Please see Section 1, Item #3 for more details regarding the reasons for variance from our baseline plan. In previous Performance Progress Reports, milestone completion percentages for this category were based on work completed instead of actual budget expenditures. Going forward, progress toward this milestone category will be reported against actual expenditures, incorporating non-Federal share in-kind contributions as applicable per the Additional Guidance instructions. As part of our efforts to catch up to the Baseline Plan, the Florida Rural Broadband Alliance's General Counsel has been working closely with the Grants Office and the Program Office to finalize the format and acceptable language required in all lease documents for the project, including the in-kind leases. | 0 | N/A. Categorically exempt from Environmental Assessment. | 12 | Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. The variance from estimated Baseline Plan progress is the result of additional steps taken this past quarter to validate the preliminary network design against current network-to-network integration plans, and this process impacted subsequent engineering activities. In addition, in previous Performance Progress Reports, network design progress was based on pending expenditures and committed costs as determined by work completed instead of actual budget expenditures. From this point forward we will report milestone completion percentages based on budget expenditures in the milestones calculation, per Additional Guidance instructions. In order to catch up to the Baseline Plan, we are pushing the design process move forward by synchronizing engineering activities among the two network regions. In addition, the General | 0 | N/A | 0 | Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. In order to catch up with the Baseline Plan, steps have been taken to identify tower company requirements for site access, and permit acquisition procedures will be determined for each county in the core network footprint as the project transitions into its pre-deployment phase. | 0 | N/A. Please see Section #1, Item 2f for an explanation. | 12 | Please see Section 1, Items #2 and #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan. The variance from estimated Baseline Plan progress is the result of additional steps taken this past quarter to validate the preliminary network design against network-to-network integration plans in order to establish equipment performance specifications. This process impacted the subsequent development of equipment procurement specifications, but as we move forward with remaining engineering tasks, we expect Equipment Procurement progress to get back on track with the Baseline Plan over the next quarter. | 15 | This milestone category is expected to remain on schedule. | 0 | This milestone category is expected to remain on schedule. | 0 | This milestone category is expected to remain on schedule. | 2011-05-20 19:50 | 2011-05-20 19:50 | 5502 | 5502 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2011 | Q2 | Q2 - 2011 | 3312 | 3418 | FALSE | 52 | This milestone category is expected to remain on schedule. | 45 |  | This milestone category is expected to remain on schedule. | 0 | N/A | 90 | This milestone category is expected to remain on schedule. | 0 | N/A | 70 | This milestone category is expected to remain on schedule. | 60 | This milestone category is expected to remain on schedule. | 30 | This milestone will be behind plan. The request for bids will be released for materials, equipment, and services. The actual reciept use of the equipment will be in the following quarter, bringing this milestone percentage of completion back on track and in line with expectations for construction. | 30 | This milestone category is expected to remain on schedule. | 10 | This milestone category is expected to remain on schedule. | 10 | This milestone category is expected to remain on schedule. | 2011-08-25 12:45 | 2011-08-25 16:46 | 7164 | 7164 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2011 | Q3 | Q3 - 2011 | 4350 | 4031 | FALSE | 63 | The overall project has been redesigned to run in parallel which will begin to show significant progress the first half of 2012 as network deployment accelerates. | 73 |  | This milestone category is expected to remain on schedule. | 0 | N/A | 63 | The network design and equipment selection have been completed. The site engineering and final engineering configurations will begin during the 4th quarter of 2011 and be substantially complete by the end of the 1st quarter of 2012. These efforts are running in parallel with the site selection, permittingand tower agreements and consistent with the revised project plan. | 0 | N/A | 63 | The permits and tower agreements are underway and significant progress is expected over the next two quarters. | 35 | Site preparation will begin for the new locations as tower agreements and construction permits are received. Significant progress this quarter will lead to the acceleration of deployment the 1st and 2nd quarter of 2012. | 48 | The request for Bid and selection will be completed this quarter. The equipment purchase orders and warehousing of equipment during this period will bring the equipment procurement back in line with baseline expectations. | 42 | The network build out and expansion beyond Hardee County will initiate the later part of Q4 2011. It is expected that much of the work this quarter will be in staging and preparation for deployment. | 48 | Although the equipment deployment will begin this quarter, significant progress will not begin until Q1 and Q2 of 2012. It is anticipated that the equipment deployment will come back within baseline by the middle of 2012. | 10 | Most of the network testing to date has come from the deployment of Hardee County. This work effort and spend will increase significantly during the first quarter of 2012 and is anticipated to come back to baseline by the 2nd quarter of 2012. | 2011-11-30 15:45 | 2011-11-30 15:45 | 7164 | 7164 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2011 | Q4 | Q4 - 2011 | 5376 | 5046 | FALSE | 74 | This milestone is expected to approach FRBAs original objectives by the end of the 1st Quarter of 2012 as construction kicks off. | 100 |  | This milestone category is expected to remain on schedule. | 0 | N/A | 69 | The network design has been finalized and site/service engineering will bring the estimated percentage of completion back in line with original estimates by the end of the 1st quarter of 2012. | 0 | N/A | 69 | Construction permits and approvals will slightly lag the original projections but will not have an effect on the actual deployment schedule. Instead of batching the permitting process, the permits are being requested as site engineering is completed. This follows standard practices for wireless tower deployments. | 58 | Site preparation will lag the original projections since the new work teams are aligned with tower/link deployment which aligns with wireless deployment best practices and provides FRBA with live services as towers and links are installed. This work is done within 7 to 10 days of the actual tower work. | 73 | Equipment procurement is well underway. The percentage of completion will lag the original estimated milestone since FRBA elected to purchase and receive equipment closer to the projected install dates. | 66 | The network build begins in earnest during the first quarter of 2012. Although the project has been accelerated it will lag the original milestone until the end of the second quarter of 2012. | 73 | FRBA has accelerated the equipment deployment and will complete the data center build-out and have substantially completed a large number of towers during the first quarter, bring the equipment installation back in line with the original projections. Much of this equipment will be activated and go live during the second quarter of 2012. | 10 | Testing will begin during the 1st quarter of 2012 as approximate 18 new towers/links will go live. Much of the testing and link certification work will begin in earnest during the second quarter of 2012. | 2012-02-28 18:44 | 2012-02-28 18:44 | 7164 | 7164 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2012 | Q1 | Q1 - 2012 | 6316 | 5760 | FALSE | 73 | The overall project is accelerating and will approach its original targeted objectives in 2012 and is slated to complete construction the 4th quarter of 2012. | 82 |  | This milestone category is expected to remain on schedule. | 0 | N/A | 68 | The network design has been finalized and site/service engineering was authorized at the end of the first quarter and expected to accelerate through the second quarter. Some restructuring of the tasking has shifted work effort and the structural engineering of a number of towers is taking longer than expected. However this will not slow down construction since the core routes and towers have been approved and site walk-outs and engineering has begun in earnest. This effort will align with the original milestones during the 3rd quarter of 2012. | 0 | N/A | 68 | Construction permits and approvals will slightly lag the original projections but will not have an effect on the actual deployment schedule. Instead of bundling the permitting process, the permits are being requested as site engineering is completed. This follows standard practices for wireless tower deployments. | 59 | Site preparation will lag the original projections since the new work teams are aligned with tower/link deployment which aligns with wireless deployment best practices and provides FRBA with live services as towers and links are installed. This work is done within 7 to 10 days of the actual tower work. Approximately 20 towers are ready for permitting and construction to begin during the second quarter of 2012. | 82 | The majority of the equipment has been received with the exception of cabinets and steel. Construction is slated to begin during the second quarter of 2012. The percentage of completion will lag the original estimated milestone since FRBA elected to purchase and receive equipment closer to the projected install dates. | 45 | Construction contracts were executed with G4S and rapid Systems during the first quarter. The network build begins in earnest during the second quarter of 2012. Although the project has been accelerated it will lag the original milestone until the end of the second half of 2012. | 82 | FRBA has begun staging the data center equipment and the tower equipment and is preparing for approximately 20 installs during the second quarter of 2012. FRBA will substantially complete the data center build-out and have substantially completed a large number of towers during the second quarter, bringing the equipment installation in alignment with the updated project schedule. Much of this equipment will be activated and go live during the second half of 2012. | 10 | Testing of the Sebring extension was completed during the1st quarter of 2012 and approximately 20 new towers/links will go live during the second quarter. Much of the testing and link certification work will begin in earnest during the second half of 2012. | 2012-05-29 11:02 | 2012-05-29 11:02 | 7164 | 7164 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2012 | Q2 | Q2 - 2012 | 7284 | 6269 | FALSE | 77 | The overall project is accelerating and will approach its original targeted objectives in 2012 and is slated to complete construction the 4th quarter of 2012. | 100 | In-Kind Capital Leases | This milestone category is expected to remain on schedule. | 0 | N/A | 74 | The network design has been finalized and site/service engineering was authorized at the end of the first quarter and expected to accelerate through the 2nd half of 2012. Some restructuring of the tasking has shifted work effort and the structural engineering of a number of towers is taking longer than expected. However this will not slow down construction since the core routes and towers have been approved and site walk-outs and engineering has begun in earnest. This effort will align with the original milestones during the 3rd quarter of 2012. | 0 | N/A | 74 | Construction permits and approvals will slightly lag the original projections but will not have an effect on the actual deployment schedule. Instead of bundling the permitting process, the permits are being requested as site engineering is completed. This follows standard practices for wireless tower deployments. | 59 | Site preparation will lag the original projections since the new work teams are aligned with tower/link deployment which aligns with wireless deployment best practices and provides FRBA with live services as towers and links are installed. This work is done within 7 to 10 days of the actual tower work. | 79 | The majority of the equipment has been received with the exception of steel which is order on a site readiness basis. Construction is slated to begin during the second half of 2012. The percentage of completion will lag the original estimated milestone since FRBA elected to purchase and receive equipment closer to the projected install dates. | 67 | Construction contracts were executed with G4S and Rapid Systems during the first quarter. The network build begins in earnest during the 2nd half of 2012. Although the project has been accelerated it will lag the original milestone until the end of the 2nd half of 2012. | 79 | FRBA has begun staging the data center equipment and the tower equipment and is preparing for deployment during the 2nd half of 2012. FRBA will substantially complete the data center build-out and have substantially completed a large number of towers during the next quarter, bringing the equipment installation in alignment with the updated project schedule. Much of this equipment will be activated and go live during the second half of 2012. | 10 | Much of the testing and link certification work will begin in earnest during the 2nd half of 2012. | 2012-08-29 17:57 | 2012-08-29 17:57 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2012 | Q3 | Q3 - 2012 | 8154 | 6787 | FALSE | 69 | The overall project is accelerating and will approach its original targeted objectives in 2012 and is slated to complete construction the 4th quarter of 2012. | 76 | In-Kind Capital | this milestone category is expected to remain on schedule. | 0 | N/A | 81 | The major effort of completing the overall design and establishing the equipment specifications for the FRBA network has been completed. Even though the expenditures are behind baseline projections the work effort completed will allow FRBA to accelerate the site engineering as site lease agreements and civil site work during the 3rd quarter of 2012. This work will accelerate throughout the second quarter and expected to be back on target during the 2nd half of 2012. | 0 | N/A | 81 | Construction permits and approvals will slightly lag the original projections but will not have an effect on the actual deployment schedule. Instead of bundling the permitting process, the permits are being requested as site engineering is completed. This follows standard practices for wireless tower deployments. | 64 | Site preparation will lag the original projections since the new work teams are aligned with tower/link deployment which aligns with wireless deployment best practices and provides FRBA with live services as towers and links are installed. This work is done within 7 to 10 days of the actual tower work. | 65 | The majority of the equipment has been received with the exception of steel which is order on a site readiness basis. Construction is slated to begin during the second half of 2012. The percentage of completion will lag the original estimated milestone since FRBA elected to purchase and receive equipment closer to the projected install dates. | 17 | Construction contracts were executed during the first quarter. The network build begins in earnest during the 2nd half of 2012. Although the project has been accelerated it will lag the original milestone until the end of the 2nd half of 2012. | 65 | FRBA has begun staging the data center equipment and the tower equipment and is preparing for deployment during the 2nd half of 2012. FRBA will substantially complete the data center build-out and have substantially completed a large number of towers during the next quarter, bringing the equipment installation in alignment with the updated project schedule. Much of this equipment will be activated and go live during the second half of 2012. | 10 | Much of the testing and link certification work will begin in earnest during the 2nd half of 2012. | 2012-11-29 16:39 | 2012-11-29 16:39 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2012 | Q4 | Q4 - 2012 | 9136 | 7929 | FALSE | 79 | ASSUMPTIONS: 85% of milestones completed on links that have leases and do not require lease amendments + 50% of milestones completed associated with links that do not have lease now or need a lease amendment | 90 |  | In-Kind Capital Leases | 0 | N/A | 85 | ASSUMPTIONS: 15% of designs can not be finalized due to failed permits & approvals on leases secured in quarter 1. | 0 | N/A | 85 | ASSUMPTIONS: Same as 2a | 100 | ASSUMPTIONS: All leases will be executed in quarter 1. | 63 | ASSUMPTIONS: Same as 2a | 42 | ASSUMPTIONS: Construction completed on 85% of links that currently have leases and do not require a lease amendment | 63 | ASSUMPTIONS: Same as 2h | 50 | ASSUMPTIONS: Same as 2h | 2013-03-12 16:17 | 2013-03-12 16:17 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2013 | Q1 | Q1 - 2013 | 9978 | 8533 | FALSE | 80 | Overall incremental progress in 2Q2013 will not be significant due to: (1) transition of work between sub-contractors for North sites, and (2) execution of lease amendments at commercial sites which are expected to be completed in mid-2Q2013. | 90 | In-Kind Assets | In-kind capital leases | 0 | N/A | 75 | Incremental progress in 2Q2013 for Network Design will be limited to sites where lease amendments are executed in early May. Design work for sites where lease amendments are executed in later May will be pushed into 3Q2013 pending completion of dependencies listed above. | 0 | N/A | 75 | Incremental progress in 2Q2013 for Permits will be limited to sites where lease amendments are executed in early May. Permits for sites where lease amendments are executed in later May will be pushed into 3Q2013 pending completion of dependencies listed above. | 0 | N/A | 62 | Minimal incremental Equipment Purchases will be made in 2Q2013 pending executed lease amendments, Design Work, Permits and finalization of IRU re-configuration negotiations, as described in 2c-f. Purchase of additional equipment will be pushed into 3Q2013 pending completion of dependencies listed above. | 57 | Incremental progress in 2Q2013 for Network Build will be limited to sites where lease amendments were executed in early May and Permits were secured by the new sub-contractor for North sites. Construction will begin on a broader scale in 3Q2013 pending the completion of the dependencies listed above. | 62 | Minimal incremental Equipment Purchases will be made in 2Q2013 pending executed lease amendments, Design Work, Permits and finalization of IRU re-configuration negotiations, as described in 2c-f. Purchase of additional equipment will be pushed into 3Q2013 pending completion of dependencies listed above. | 10 | Minimal incremental Network Testing will be completed in 2Q2013 and will be pushed to 3Q2013 pending the completion of dependent construction activities listed in 2h) above. | 2013-05-29 17:24 | 2013-05-29 17:24 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2013 | Q2 | Q2 - 2013 | 10778 | 9058 | FALSE | 86 | Overall incremental progress in 3Q2013 will be significant with many of our hurdles being cleared. Construction has already seen a significant advance and pathing/integration is scheduled to conclude for the majority of sites by the end of 3Q2013. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 90 | In-Kind Assets | In-kind capital leases | 0 | N/A | 75 | Final Network Design will be submitted in 3Q2013 essentially locking the design in place all the way to grant closeout. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 0 | N/A | 75 | Majority of Leases and Lease Amendments have been approved and received; paving the way for remaining building permits to be applied for and received in a timely fashion. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 0 | N/A | 62 | Majority of all required site equipment will be procured during the remainder of 3Q2013. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 57 | Construction will commence on a broader scale in 3Q2013. Firm projections of substantial Network Build completion are already targeted for the end of 3Q2013. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 62 | Majority of all procured equipment will be deployed in 3Q2013 in correlation with the substantial completion of the Network Build.This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 50 | It is estimated that a significant portion of network testing will begin and possibly conclude in 3Q2013 with any remaining site requiring testing to occur in 4Q2013. This percentage compete is actually higher based on FRBA's recent budget realignment, submitted to NTIA for approval. | 2013-08-28 01:21 | 2013-08-28 01:21 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2013 | Q3 | Q3 - 2013 | 11416 | 9528 | FALSE | 100 | To be completed in full. | 100 |  | To be completed in full. | 0 | N/A | 100 | To be completed in full. | 0 | N/A | 100 | To be completed in full. | 0 | N/A | 100 | To be completed in full. | 100 | To be completed in full. | 100 | To be completed in full. | 100 | To be completed in full. | 2013-11-26 20:35 | 2013-11-26 20:35 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | 2013 | Q4 | Q4 - 2013 | 11918 | 10083 | FALSE | 100 | Completed | 100 |  | Completed | 0 | N/A | 100 | Completed | 0 | N/A | 100 | Completed | 0 | N/A | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2014-02-28 10:44 | 2014-02-28 10:44 | 7570 | 7570 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570123 | 2010 | Q4 | Q4 - 2010 | 604 | 1622 | FALSE | 15 | N/A | 100 | Tower Site leases | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 75 | N/A | 0 | N/A | 3 | N/A | 10 | N/A | 15 | N/A | 0 | N/A | 2011-01-27 13:41 | 2011-01-27 13:41 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2011 | Q1 | Q1 - 2011 | 2066 | 2778 | FALSE | 25 | During the next quarter (Y1Q4) we anticipate having site development contracts in place; network equipment ordered and installed on existing towers; and deployment of the network where we can connect existing tower equipment to the Tribes network. Construction season is behind approximately one month due to late snow and cold wet spring conditions; site development and construction actives will ramp up during the next two quarters, which will get us back on track. | 100 |  | On track | 100 | On track | 100 | On track | 100 | Expect to have all utility service line agreements with BIA complete and utility corridor rights of way agreements in place with private landowners. | 100 | Expect to be back on track and have permitting completed | 50 | Expect road construction/reconstruction work to be underway for site development and utility installation in progress. | 30 | Expect to have network equipment purchased; tower contracts under negotiations well underway. | 20 | Expect to have network equipment installed on three of the seven existing towers. | 15 | Expect to be on track | 0 | NA too early | 2011-05-16 19:40 | 2011-05-16 19:40 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2011 | Q2 | Q2 - 2011 | 3332 | 3428 | FALSE | 40 | Infrastructure should be 70% procured but installation timing and logistics (concrete dry/set time) will set back the implementation accomplishment rate. Through this next quarter project activities will be strongly tied to site development and construction, where network wireless equipment installation and service capacity will be deployed across the western side of the Reservation. Work on the eastern side of the Reservation will focus on resolving the TU 71 utility access issue. | 100 | Tower Land Leases | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 60 | Contracts for all network wireless equipment, utilities and towers will be awarded. | 40 | Network build out will prioritize the western loop of existing and new towers connected. In the Baseline the projection was based on getting towers erected across the Reservation; the project will focus on sections and get service up in phases that offer redundancy and looped pathways. | 20 | Equipment deployment will mirror network build out; once towers are constructed the equipment can be installed in the prioritized loops. | 10 | Testing will docus on delivery to targeted CAI's along the pathways developed in phases. | 2011-08-26 15:38 | 2011-08-26 15:38 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2011 | Q3 | Q3 - 2011 | 3976 | 3826 | FALSE | 60 | Narrowly lagging behind baseline due to anticipated weather set backs related to last mile equipment deployment. | 100 | Tribe-Prvt agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 85 | Wireless equipment procured for all existing towers and six of the new towers | 75 | Six towers constructed; wireless equipment installed on Teaken, Stoney Pt, Hubbard, Peck, TU 17, TU 99-101, Culdesac towers | 60 | Network equipment on line for middle and last mile across the western half of the Reservation. | 25 | Testing complete for Stoney Pt, Hubbard, Peck sites | 2011-11-10 16:57 | 2011-11-10 16:57 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2011 | Q4 | Q4 - 2011 | 5190 | 4856 | FALSE | 72 | Narrowly lagging behind baseline due to anticipated weather set backs related to last mile equipment deployment. | 100 | Tribe-Prvt agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 85 | Middle mile complete on 11 of the 13 link paths; Last mile access points installed on 4 of the 11 designated towers. | 65 | Middle mile 85% complete; Last mile 40% complete | 75 | Testing complete for Middle mile ring, Stoney Pt, Hubbard, Peck & Culdesac sites | 2012-02-22 14:32 | 2012-02-22 14:32 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2012 | Q1 | Q1 - 2012 | 6028 | 5613 | FALSE | 85 | Subscriber connection behind the baseline but is NPT-IS tech staff priority during the next quarter. | 100 | Pvt Site lease agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 95 | Middle & Last mile equipment deployment underway | 95 | Middle mile network equipment installation at Nuxoll, KIYE & TU 64 will be ealy Q2 2012; Last mile access point installation well underway in Q2 2012 | 95 | Testing to be done on Nuxoll - KIYE-TU 64 middle link & at last mile sites: Hubbard, Peck, Beard, TU 60, TU 17 to be initiated in Q2 2012. | 2012-05-10 16:37 | 2012-05-10 16:37 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2012 | Q2 | Q2 - 2012 | 7060 | 6157 | FALSE | 89 | With construction activities complete the project staff and technicians can focus on subscriber connection and marketing. The construction schedule for the project is in line with baseline. | 100 | Site lease agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 97 | The KIYE-TU 64 middle mile link is being troubleshot and should be complete enabling last mile testing to get underway by the end of Q2 | 2012-08-14 13:07 | 2012-08-14 13:07 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2012 | Q3 | Q3 - 2012 | 7980 | 6696 | FALSE | 97 | During Q4 2012 efforts will be focused on subscriber connection and completing the in kind match obligation. | 100 | Site lease agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 99 | Deployment of neighborhood solution equipment is underway with 3 of the 4 site lease agreements with landowners approved by tribal Resolution. Tech staff have initiated radio configuration and installations are being scheduled. | 99 | The neighborhood solution equipment will be tested as it gets deployed. Winter weather may become a factor for field technicians. | 2012-11-20 14:03 | 2012-11-20 14:03 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2012 | Q4 | Q4 - 2012 | 9142 | 7957 | FALSE | 100 | Complete | 100 | Site Lease Agmt | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-03-22 13:38 | 2013-03-22 13:38 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2013 | Q1 | Q1 - 2013 | 9628 | 8346 | FALSE | 99 | We are line with baseline and will work on project details remaining to reach completion. | 100 | Site Use Agmts | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-05-08 13:38 | 2013-05-08 13:38 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2013 | Q2 | Q2 - 2013 | 10716 | 9021 | FALSE | 100 | Complete | 100 | Site Use Agmt | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-08-23 16:56 | 2013-08-23 16:56 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570123 | 2013 | Q3 | Q3 - 2013 | 11458 | 9571 | FALSE | 100 | Complete | 100 | Site Use Agmt | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 100 | Complete | 2013-12-09 19:13 | 2013-12-09 19:13 | 6176 | 6176 | Nez Perce Tribe | TRUE
NT10BIX5570125 | 2010 | Q4 | Q4 - 2010 | 1224 | 2254 | FALSE | 11 | n/a | 47 | Administration | n/a | 82 | n/a | 65 | n/a | 61 | n/a | 24 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 2011-02-18 15:40 | 2011-02-18 15:40 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2011 | Q1 | Q1 - 2011 | 2340 | 2915 | FALSE | 14 | None | 57 | Administration | None | 88 | None | 85 | None | 84 | None | 59 | None | 0 | None | 0 | None | 0 | None | 0 | None | 0 | None | 2011-05-26 12:33 | 2011-05-26 12:33 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2011 | Q2 | Q2 - 2011 | 3286 | 3405 | FALSE | 36 | No anticipated variance at this time. | 66 | Administration | No anticipated variance at this time. | 100 | No anticipated variance at this time. | 97 | No anticipated variance at this time. | 87 | No anticipated variance at this time. | 77 | No anticipated variance at this time. | 100 | No anticipated variance at this time. | 18 | No anticipated variance at this time. | 34 | No anticipated variance at this time. | 0 | No anticipated variance at this time. | 13 | No anticipated variance at this time. | 2011-08-23 17:38 | 2011-08-23 17:38 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2011 | Q3 | Q3 - 2011 | 4042 | 3861 | FALSE | 23 | Baseline had a forecast of 53%. See below categories to see shifting. All updates provided below are based on information known as of 11/10/11. | 69 | Administration | The baseline had projected 75%. Due to delay in construction beginning, this shifted as well. | 100 | No change. | 100 | Baseline projected 98% we are tracking to have this milestone completed by the end of the quarter. | 27 | The Baseline projected 90%. The variance is largely due to the budgeted $110,000 for node site acquisition, which has not yet occurred. This item is being evaluated. | 49 | The baseline had projected 93%. The variance is due to the delay in receiving FONSI and construction fees that have not yet occurred as construction has not begun. | 0 | The baseline had projected 100%. The variance is due to the delay in receiving FONSI which trickled down to delay in equipment procurement for site preparation work to occur. We do not forsee expending these funds in this quarter. | 26 | The baseline had projected 36%, delay in FONSI created delay in equipment procurement. With the FONSI being projected to be acquired this quarter, material procurement will pick up. | 4 | The baseline had projected 47%. This was delayed due to FONSI not occuring last quarter and construction not being able to begin. With FONSI likely being acquired this quarter, this percent will increase in future quarters, weather depending. | 0 | The baseline had projected 53% based on network build. This has a trickle down effect from network build. | 0 | The baseline had projected 25% based on the network build. The has a trickle down effect from the network build. | 2011-11-14 19:32 | 2011-11-14 19:32 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2011 | Q4 | Q4 - 2011 | 5264 | 4932 | FALSE | 30 | Baseline had a forecast of 67% see below categories to see shifting. | 89 | Administration | The baseline had projected 84%, this will be addressed in the upcoming budget realignment as dollars need to be shifted to be realigned with the current build and scope of the project. | 100 | No change | 100 | Baseline projected 98% we completed this work. | 48 | The Baseline projected 94%. The variance is largely due to a budgeted $110,000 for node site acquisition. This will be addressed in an upcoming budget realignment. | 73 | The baseline had projected 96%. The variance is due to the delay in receiving our FONSI and construction fees that have not yet been incurred as construction related activities are just beginning. | 0 | The baseline had projected 100%. With the delay in FONSI our Node buildings have not yet been acquired. We have completed the RFP but delivery of the item will likely occur in quarter 2 of 2012. | 41 | The baseline had projected 49%. Equipment procurement is occurring and most RFP's and orders are in process. Delivery from vendors is taking longer than anticipated with the demands of the broadband projects occurring along similar timelines. | 6 | The baseline had projected 63% This continues to lag behind due to delay in FONSI and now more recently with delay in material delivery. If the material comes in ahead of current projected delivery dates from the vendor then this percentage would increase. | 0 | The baseline had projected 77% based on network build. This has a trickle down effect from Network Build. | 0 | The baseline had projected 40% based on the network build, this has a trickle down effect from Network Build. | 2012-02-24 20:07 | 2012-02-24 20:07 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2012 | Q1 | Q1 - 2012 | 6096 | 5650 | FALSE | 57 | Baseline had a forecast of 97% see below categories to see shifting. | 100 | Administration | The baseline had projected 93%, this will be addressed in the upcoming budget realignment as dollars need to be shifted to be realigned with the revised project route and scope of the project. | 100 | No change | 100 | Baseline projected 99%; we completed this work. | 46 | Baseline had projected 97%. The variance is largely due to a budged $110,000 for node site acquisition. This will be addressed in an upcoming budget realignment. | 100 | No change | 94 | Baseline had projected 100%. With the delay in FONSI our Node buildings have not yet been acquired. Vendor has been selected and this work will be beginning this quarter. | 100 | Baseline had projected 83%. This number will shift with the upcoming budget realignment. | 24 | Baseline had projected 93%. This continues to lag behind due to the delay in FONSI that occurred and the delay in material delivery. | 12 | The baseline had projected 92% based on the network build. This continues to have a trickle down effect from Network Build. | 27 | The baseline had a projected 63% based on network build projections, this has a trickle down effect. | 2012-05-15 13:37 | 2012-05-15 13:37 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2012 | Q2 | Q2 - 2012 | 7208 | 6231 | FALSE | 81 | Baseline had a forecast of 99%. See categories below for changes. | 100 | Administration | Baseline had projected 97%. This will be addressed in an upcoming budget realignment. Dollars need to be shifted for proper realignment with revised project route and scope of project. | 100 | No change | 100 | No change | 46 | Baseline had projected 100%. The variance is largely due to a budged $110,000 for node site acquisition. This will be addressed in an upcoming budget realignment. | 100 | No change | 100 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 42 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%. All equipment should be purchased by the end of September. This will be addressed in an upcoming budget realignment. | 30 | Baseline had projected 79%. Construction delays have resulted in network testing delays. This will be addressed in an upcoming budget realignment. | 2012-08-22 13:22 | 2012-08-22 13:22 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2012 | Q3 | Q3 - 2012 | 8164 | 6792 | FALSE | 84 | Baseline had a forecast of 100%. See Categories below for changes. | 100 | Administration | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. Dollars need to be shifted for proper realignment with revised project route and scope of project. | 100 | No change | 100 | No change | 66 | Baseline had projected 100%. The variance is largely due to a budged $110,000 for node site acquisition. This will be addressed in an upcoming budget realignment. | 100 | No change. | 100 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 43 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%. All equipment should be purchased by the end of December. This will be addressed in an upcoming budget realignment | 35 | Baseline had projected 100%. Construction delays have resulted in network testing delays. This will be addressed in an upcoming budget realignment. | 2012-11-29 23:27 | 2012-11-29 23:27 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2012 | Q4 | Q4 - 2012 | 9152 | 7976 | FALSE | 89 | Baseline had a forecast of 100%. See Categories below for changes. Overall, budgeted costs need to be shifted for proper realignment with revised project route and scope of project. | 100 | Administration | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | No change | 100 | No change | 100 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | No change. This will be addressed in an upcoming budget realignment. | 100 | No change. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 44 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%. All equipment should be purchased by the end of December. This will be addressed in an upcoming budget realignment | 22 | Baseline had projected 100%. Construction delays have resulted in network testing delays. This will be addressed in an upcoming budget realignment. | 2013-03-28 14:00 | 2013-03-28 14:00 | 6040 | 6040 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2013 | Q1 | Q1 - 2013 | 9942 | 8514 | FALSE | 96 | Baseline had a forecast of 100%. See Categories below for changes. Overall, budgeted costs need to be shifted for proper realignment with revised project route and scope of project. | 100 | Administration | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | No Change | 100 | No Change | 75 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | No change. This will be addressed in an upcoming budget realignment. | 100 | No change. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 100 | Baseline had projected 100%. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 52 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%.This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 48 | Baseline had projected 100%. Construction delays have resulted in network testing delays. This will be addressed in an upcoming budget realignment. | 2013-05-28 16:08 | 2013-05-28 16:08 | 6039 | 6039 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2013 | Q2 | Q2 - 2013 | 10630 | 8975 | FALSE | 100 | Baseline had a forecast of 100%. See Categories below for changes. Overall, budgeted costs need to be shifted for proper realignment with revised project route and scope of project. | 100 | Administration | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | No Change | 100 | No Change | 77 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | No change. This will be addressed in an upcoming budget realignment. | 100 | No change. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 100 | Baseline had projected 100%. This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 57 | Baseline had projected 100%. This will be addressed in an upcoming budget realignment. | 100 | Baseline had projected 100%.This line item will be addressed by allocating additional funds to it in our upcoming budget realignment. | 20 | Baseline had projected 100%. Construction delays have resulted in network testing delays. This will be addressed in an upcoming budget realignment. | 2013-08-19 05:04 | 2013-08-19 05:04 | 7691 | 7691 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | 2013 | Q3 | Q3 - 2013 | 12452 | 10634 | FALSE | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 |  | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 100 | Baseline had a forecast of 100%. This project is finished. This Milestone will not change going forward. | 2014-08-22 16:25 | 2014-08-22 16:25 | 6039 | 6039 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570126 | 2010 | Q4 | Q4 - 2010 | 1324 | 2348 | FALSE | 1 | N/A | 0 | N/A | N/A | 90 | N/A | 50 | Originally planned to be 15% complete during Q1-2011. This percentage represented preliminary design work only. Detailed engineering was not originally planned to begin until the Environmental Assessment (EA) was complete. We have now moved up detailed engineering efforts ahead of the EA completion and will include in EA extension budget. This equates to a planned 50% complete this quarter. It is expected that Network Design quarterly Percent Complete figures will remain ahead of schedule until eventual completion in Q3-2011 as planned. | 0 | Originally planned to be 15% complete during Q1-2011. Rights-of-Way was originally planned to begin prior to detailed engineering efforts. It will now begin as part of the detailed engineering process which starts this quarter and will extend beyond completion of the detailed engineering process. It is expected to be back in line with the baseline in Q2-2011. | 0 | Originally planned to be 15% complete during Q1-2011. Permitting was originally planned to begin prior to detailed engineering efforts. It will now begin as part of the detailed engineering process which starts this quarter and will extend beyond completion of the detailed engineering process. It is expected to be back in line with the baseline in Q2-2011. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-23 10:48 | 2011-02-23 10:48 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2011 | Q1 | Q1 - 2011 | 2156 | 2823 | FALSE | 12 | No change from the baseline | 0 | N/A | N/A | 100 | No change from the baseline | 75 | No change from the baseline | 35 | No change from the baseline | 35 | No change from the baseline | 10 | No change from the baseline | 15 | No change from the baseline | 10 | No change from the baseline | 10 | No change from the baseline | 0 | No change from the baseline | 2011-05-18 18:37 | 2011-05-18 18:37 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2011 | Q2 | Q2 - 2011 | 2924 | 3219 | FALSE | 15 | Construction is delayed until the FONSI is issued. CVIN anticipates construction will commence during Quarter 3, 2011 and significant progress is anticipated during Quarter 4, 2011. | 0 | N/A | N/A | 100 | Complete | 100 | Complete | 65 | No change from the baseline plan. | 65 | No change from the baseline plan. | 12 | Construction is delayed until the FONSI is issued. CVIN anticipates construction will commence during Quarter 3, 2011 and significant progress is anticipated during Quarter 4, 2011. | 25 | Construction is delayed until the FONSI is issued. CVIN anticipates construction will commence during Quarter 3, 2011 and significant progress is anticipated during Quarter 4, 2011. | 12 | Construction is delayed until the FONSI is issued. CVIN anticipates construction will commence during Quarter 3, 2011 and significant progress is anticipated during Quarter 4, 2011. | 12 | Construction is delayed until the FONSI is issued. CVIN anticipates construction will commence during Quarter 3, 2011 and significant progress is anticipated during Quarter 4, 2011. | 0 | No change from the baseline plan. | 2011-08-04 13:06 | 2011-08-04 13:06 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2011 | Q3 | Q3 - 2011 | 3984 | 3830 | FALSE | 16 | Construction is delayed since FONSI was not issued until September 30, 2011. Construction will commence during Q4-2011 and significant progress is anticpated during Q1-2012. | 0 |  | N/A | 100 | Complete | 100 | Complete | 85 | No change from the baseline. | 85 | No change from the baseline. | 20 | Construction is delayed since FONSI was not issued until September 30, 2011. Construction will commence during Q4-2011 and significant progress is anticpated during Q1-2012. | 35 | Construction is delayed since FONSI was not issued until September 30, 2011. Construction will commence during Q4-2011 and significant progress is anticpated during Q1-2012. | 20 | Construction is delayed since FONSI was not issued until September 30, 2011. Construction will commence during Q4-2011 and significant progress is anticpated during Q1-2012. | 20 | Construction is delayed since FONSI was not issued until September 30, 2011. Construction will commence during Q4-2011 and significant progress is anticpated during Q1-2012. | 5 | Construction is delayed since FONSI was not issued until September 30, 2011. Construction will commence during Q4-2011 and significant progress is anticpated during Q1-2012. | 2011-11-10 19:19 | 2011-11-10 19:19 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2011 | Q4 | Q4 - 2011 | 5370 | 5038 | FALSE | 30 | Behind schedule on construction due to delays in acquiring FONSI and construction permits and availability of fiber optic cable. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 20 | Behind schedule on construction due to delays in acquiring FONSI and construction permits and availability of fiber optic cable. | 50 | Behind schedule on construction due to delays in acquiring FONSI and construction permits and availability of fiber optic cable. | 30 | Behind schedule on construction due to delays in acquiring FONSI and construction permits and availability of fiber optic cable. | 20 | Behind schedule on construction due to delays in acquiring FONSI and construction permits and availability of fiber optic cable. | 5 | Behind schedule on construction due to delays in acquiring FONSI and construction permits and availability of fiber optic cable. | 2012-02-28 17:15 | 2012-02-28 17:15 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2012 | Q1 | Q1 - 2012 | 6146 | 5675 | FALSE | 60 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 98 | Slightly behind baseline. It is anticipated that everything but Caltrans permits will be complete. | 98 | Slightly behind baseline. It is anticipated that everything but Caltrans permits will be complete. | 30 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 60 | Slightly behind schedule and should be complete next quarter. | 60 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 15 | Behind schedule due to construction delays. | 15 | Behind schedule due to construction delays. | 2012-05-16 19:57 | 2012-05-16 19:57 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2012 | Q2 | Q2 - 2012 | 7082 | 6168 | FALSE | 70 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 50 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 95 | Slightly behind schedule but significant progress from last quarter. Should be complete next quarter. | 70 | Behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 25 | Behind schedule due to construction delays. Significant progress will be made next quarter. | 20 | Behind schedule due to construction delays. | 2012-08-15 14:59 | 2012-08-15 14:59 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2012 | Q3 | Q3 - 2012 | 8044 | 6728 | FALSE | 86 | Significant progress will be made on underground construction and fiber optic cable installation this quarter. Still slightly behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 0 | N/A | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 75 | Significant progress on underground construction will allow for substantial progress on cabinet and hut site preparation. Still slightly behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 97 | All but the last few equipment items will have been purchased. | 86 | Significant progress will be made on underground construction and fiber optic cable installation this quarter. Still slightly behind schedule on construction because of initial delays in acquiring FONSI and construction permits. | 35 | Behind schedule due to construction delays. Significant progress will be made again next quarter. | 35 | Behind schedule due to construction delays. Testing will closely follow equipment deployment. | 2012-11-26 13:03 | 2012-11-26 13:03 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2012 | Q4 | Q4 - 2012 | 8764 | 7559 | FALSE | 95 | Slightly behind the baseline due to initial underground construction delays. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 85 | Continued progress on underground construction will allow for increased progress on cabinet and hut site preparation. Still slightly behind schedule on baseline. | 100 | No change from the baseline. | 95 | Slightly behind the baseline due to initial underground construction delays. | 60 | Continued progress on site preparation will allow for increased progress on equipment deployment. Still behind schedule on baseline. | 60 | Continued progress on equipment deployment will allow for increased progress on network testing. Still behind schedule on baseline. | 2013-02-13 18:59 | 2013-02-13 18:59 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2013 | Q1 | Q1 - 2013 | 9988 | 8538 | FALSE | 99 | Only last few items to wrap up before end of grant period. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 99 | Only last few items to wrap up before end of grant period. | 95 | Only last few items to wrap up before end of grant period. The 95% for these less costly items indicate that there will still be a bit of work to be done for these items while the Network Build and Overall Project is still expected to reach 99%. | 95 | Only last few items to wrap up before end of grant period. The 95% for these less costly items indicate that there will still be a bit of work to be done for these items while the Network Build and Overall Project is still expected to reach 99%. | 2013-05-29 18:50 | 2013-05-29 18:50 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2013 | Q2 | Q2 - 2013 | 10546 | 8927 | FALSE | 100 | Only last few items to wrap up before end of grant period. Anticipated expenditures are expected to be 110% of our overall budget. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline | 100 | No change from the baseline. | 99 | Only last few items to wrap up before end of grant period. | 95 | Only last few items to wrap up before end of grant period. The 95% for these less costly items indicate that there will still be some work to be done for these items while the Network Build and Overall Project are expected to reach higher percentages. | 95 | Only last few items to wrap up before end of grant period. The 95% for these less costly items indicate that there will still be some work to be done for these items while the Network Build and Overall Project are expected to reach higher percentages. | 2013-08-09 17:38 | 2013-08-09 17:38 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2013 | Q3 | Q3 - 2013 | 11264 | 9423 | FALSE | 100 | Anticipated expenditures are expected to be 111% of our overall budget. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 2013-11-15 12:11 | 2013-11-15 12:11 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570126 | 2013 | Q4 | Q4 - 2013 | 11828 | 10005 | FALSE | 100 | Anticipated expenditures are expected to be 117% of our overall budget. | 0 |  | N/A | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 100 | No change from the baseline. | 98 | Final sections of network turn-up and testing left to complete. | 100 | No change from the baseline. | 98 | Final sections of network turn-up and testing left to complete. | 2014-02-14 18:52 | 2014-02-14 18:57 | 6105 | 6105 | CVIN, LLC | TRUE
NT10BIX5570127 | 2010 | Q4 | Q4 - 2010 | 1038 | 2077 | FALSE | 2 | See 2g for reason for variance | 0 | Connect Anchors | No Variance | 100 | No Variance, excluding any potential post FONSI activities | 29 | No Variance | 29 | No Variance | 29 | No Variance | 0 | No Variance | 0 | RFP's will be awarded during this QTR for materials and equipment with the initial orders being placed in Q1-2011. The delay in confirming availability of matching funds to pay for the planned equipment and materials delayed the initial RFP release and UTOPIA will not actually incur the initial costs originally planned for the end of Q1-2011 until the first month of Q2-2011. A Waiver for proportional draw down has been requested to allow the project to continue as planned until matching funds are available. Matching funds will be available sometime during YR1-Q4 (Q2-2011). The milestone baseline for equipment procurement should be fully recovered in YR1-Q4 (Q2-2011) | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-02-10 10:19 | 2011-02-10 10:19 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2011 | Q1 | Q1 - 2011 | 2022 | 2756 | FALSE | 12 | See 2g for reason for variance | 9 |  | No Variance. Community Anchor institutions will be connected during the QTR with progress as planned. This projection anticipates 37 completed community anchor institution connections. | 100 | No Variance, excluding any potential post FONSI activities | 29 | No Variance. Activities will continue to see ongoing progress throughout the QTR as planned. This projection anticipates an additional 45 miles of network design engineering. | 29 | No Variance. Activities will continue to see ongoing progress throughout the QTR as planned. This projection anticipates an additional 45 miles of secured Rights of Way. | 29 | No Variance. Activities will continue to see ongoing progress throughout the QTR as planned. This projection anticipates an additional 45 miles of secured Permitting and other approvals. | 9 | No Variance. Site preparations will begin during the QTR as planned. This projection anticipates site preparations necessary to support 8 miles of fiber network construction. | 27 | As indicated in section 2 above, the delay in Q4-2010 confirming availability of matching funds to pay for the planned equipment also delayed the initial RFP release and UTOPIA will not actually incur the costs originally planned for the end of Q1-2011 until Q2-2011. A Waiver for proportional draw down was approved to allow the project to continue as planned until matching funds are available. Matching funds will be available sometime during YR1-Q4 (Q2-2011).The milestone baseline for equipment procurement will be partially recovered during Q2-2011 and fully recovered by the end of this QTR. This projection anticipates the purchase of Equipment necessary to support 8 miles of fiber network construction this QTR and an additional 31 miles next QTR. | 9 | No Variance. Construction activities will start during the QTR with progress as planned. This projection anticipates 8 miles of fiber network construction. | 9 | No Variance. Equipment will be deployed during the QTR with progress as planned. This projection anticipates equipment deployment necessary to support 8 miles of fiber network construction and connections to 37 anchor institutions. | 9 | No Variance. Network testing will commence during the QTR with progress as planned. This projection anticipates testing as required to support 8 miles of fiber network construction and connections to 37 community anchor institutions | 2011-05-13 15:27 | 2011-05-13 15:27 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2011 | Q2 | Q2 - 2011 | 2976 | 3245 | FALSE | 17 | Milestone baseline will continue into this quarter. Reasons for variance are indicated below. Overall the project continues to track closely with most key indicators, but cost factors are lagging due to lower than expected project costs or pending payments for goods or services received. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2011. | 22 |  | Milestone baseline variance will continue into this quarter but the project will make significant gain and track much closer to the original baseline. An additional 70 community anchor institutions will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2011. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic Structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements, and inspection/supervision during and after installations. | 33 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and Orem. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to significantly impact project completion, key indicators, and initial construction activities. We anticipate catching up to our baseline projections by end of Q4-2011. | 33 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and Orem. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to significantly impact project completion, key indicators, and initial construction activities. We anticipate catching up to our baseline projections by end of Q4-2011. | 33 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, Orem, and West Valley. The construction permits and other approvals are dependent on securing these sites, and completing the network design and detailed route engineering. These delays are not expected to significantly impact project completion, key indicators, and initial construction activities. We anticipate catching up to our baseline projections by end of Q4-2011. | 8 | Milestone baseline variance continues due to delays in securing permits and other approvals for the Rights of Way. Six points of interconnection will be completed during this quarter with six additional points of interconnect in process. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2011. | 28 | Milestone baseline variance will continue into this quarter but the project will make significant gains and track much closer to the original baseline. Additional equipment will be ordered but costs will not be incurred during this quarter as planned. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2011. | 15 | Milestone baseline variance will continue into this quarter but the project will make significant gain and track much closer to the original baseline. An additional 20 miles of fiber and six points of interconnect will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2011. | 15 | Milestone baseline variance will continue into this quarter but the project will make significant gain and track much closer to the original baseline. An additional 20 miles of fiber and six points of interconnect will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2011. | 15 | Milestone baseline variance will continue into this quarter but the project will make significant gain and track much closer to the original baseline. An additional 20 miles of fiber and six points of interconnect will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2011. | 2011-08-09 13:55 | 2011-08-09 13:55 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2011 | Q3 | Q3 - 2011 | 4316 | 4008 | FALSE | 27 | Milestone baseline variance will continue into this quarter. Reasons for variance are indicated below. Overall the project continues to track behind with most key indicators as cost factors are lagging due to lower than expected project costs or pending payments for goods or services received. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by the end of Q1-2012. | 25 |  | Milestone baseline variance will continue into this quarter but the project will make significant gains and track much closer to the original baseline. An additional 50 community anchor institutions will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q1-2012. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. | 75 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2012. | 75 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem. The network design and detailed route engineering is dependent upon securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2012. | 75 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem. The network design and detailed route engineering is dependent upon securing these sites in order for work to begin. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Construction Permits and Other Approvals lags slightly behind the completion of the Network Design. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2012. | 20 | Milestone baseline variance continues due to delays in securing permits and other approvals for the Rights of Way. Six additional points of interconnection will be completed during this quarter with six more points of interconnect in process. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q1-2012. | 30 | Milestone baseline variance will continue into this quarter but the project will make significant gains and track much closer to the original baseline. Additional equipment is ordered and costs will be incurred during this quarter as planned. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q1-2012. | 24 | Milestone baseline variance will continue into this quarter but the project will make significant gains and track much closer to the original baseline. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 25 miles of fiber and six points of interconnect will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q1-2012. | 24 | Milestone baseline variance will continue into this quarter but the project will make significant gains and track much closer to the original baseline. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Equipment Deployment lags slightly behind the completion of the Network Build. An additional 25 miles of fiber and six points of interconnect will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q1-2012. | 24 | Milestone baseline variance will continue into this quarter but the project will make significant gains and track much closer to the original baseline. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Generally the physical completion of the Network Testing lags slightly behind the completion of the Network Build. An additional 25 miles of fiber and six points of interconnect will be completed during this quarter. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q1-2012. | 2011-11-29 13:54 | 2011-11-29 13:54 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2011 | Q4 | Q4 - 2011 | 5224 | 4888 | FALSE | 42 | Milestone baseline variance will continue into this quarter but will be much closer to the original baseline. Reasons for variance are indicated below. Overall the project will track closely with most key indicators as cost factors are lagging due to lower than expected project costs or pending payments for goods or services received. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by the end of Q2-2012. | 40 |  | Milestone baseline will be met during this Quarter. This indicator will continue to track closely to the original baseline based on costs associated with community anchor institution connections. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. | 80 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, and Orem. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for design work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q2-2012. | 80 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, and Orem. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q2-2012. | 80 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, and Orem. The Construction Permits and Other Approvals are dependent upon finalizing design and route engineering. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q2-2012. | 45 | Milestone baseline will be exceeded during this Quarter. Sixteen additional points of interconnection will be completed during this quarter with six more progress. | 55 | Milestone baseline variance will continue into this quarter but the project will make significant gains and track much closer to the original baseline. Additional equipment is ordered and costs are incurred as they are needed rather than procuring all the equipment up front. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q3-2012. | 38 | Milestone baseline will be met and continue to track much closer to the original baseline. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 47 miles of fiber and 18 points of interconnect will be completed during this quarter. | 38 | Milestone baseline will be met and continue to track much closer to the original baseline. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 47 miles of fiber and 18 points of interconnect will be completed during this quarter. | 38 | Milestone baseline will be met and continue to track much closer to the original baseline. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 47 miles of fiber and 18 points of interconnect will be completed during this quarter. | 2012-02-23 16:14 | 2012-02-23 16:14 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2012 | Q1 | Q1 - 2012 | 6032 | 5615 | FALSE | 52 | Milestone baseline variance will continue into this quarter but will be much closer to the original baseline. Reasons for variance are indicated below. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by the end of Q3-2012. | 38 |  | Milestone baseline will be met during this Quarter. This indicator will continue to track closely to the original baseline based on costs associated with community anchor institution connections. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures to be implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. | 85 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for design work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q3-2012. | 85 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q3-2012. | 85 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The Construction Permits and Other Approvals are dependent upon finalizing design and route engineering. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q3-2012. | 51 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. Twenty additional points of interconnection will be completed during this quarter with more in progress. We anticipate catching up to our baseline projections by the end of Q3-2012 | 35 | Milestone baseline variance will continue into this quarter. Additional equipment is ordered and costs are incurred as they are needed rather than procuring all the equipment up front as indicated in the original baseline. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2012. | 52 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 60 miles of fiber and 20 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q4-2012. | 52 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 60 miles of fiber and 20 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q4-2012. | 52 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 60 miles of fiber and 20 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q4-2012. | 2012-05-10 19:59 | 2012-05-10 19:59 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2012 | Q2 | Q2 - 2012 | 7002 | 6128 | FALSE | 67 | Milestone baseline variance will continue into this quarter but will be much closer to the original baseline. Reasons for variance are indicated below. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by the end of Q4-2012. | 38 |  | Milestone baseline will be met during this Quarter. This indicator will continue to track closely to the original baseline based on costs associated with community anchor institution connections. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 98 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for design work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q33-2012. | 98 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q3-2012. | 98 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The Construction Permits and Other Approvals are dependent upon finalizing design and route engineering. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q3-2012. | 51 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. Twenty-nine additional points of interconnection will be completed during this quarter with more in progress. We anticipate catching up to our baseline projections by the end of Q4-2012 | 52 | Milestone baseline variance will continue into this quarter. Additional equipment is ordered and costs are incurred as they are needed rather than procuring all the equipment up front as indicated in the original baseline. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q4-2012. | 68 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 50 miles of fiber and 29 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q4-2012. | 68 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 50 miles of fiber and 29 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q4-2012. | 68 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 50 miles of fiber and 29 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q4-2012. | 2012-08-10 12:15 | 2012-08-10 12:15 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2012 | Q3 | Q3 - 2012 | 8078 | 6745 | FALSE | 67 | Milestone baseline variance will continue into this quarter but will be much closer to the original baseline. Reasons for variance are indicated below. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by the end of Q1-2013. | 44 |  | Milestone baseline variance will continue into this quarter. We anticipate catching up to our baseline projections by the end of Q2-2013. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 96 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for design work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2013. | 96 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2013. | 96 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The Construction Permits and Other Approvals are dependent upon finalizing design and route engineering. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2013. | 62 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. 14 additional points of interconnection will be completed during this quarter with more in progress. We anticipate catching up to our baseline projections by the end of Q1-2013 | 52 | Milestone baseline variance will continue into this quarter. Additional equipment is ordered and costs are incurred as they are needed rather than procuring all the equipment up front as indicated in the original baseline. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q1-2013. | 69 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 53 miles of fiber and 14 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q1-2013. | 69 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 53 miles of fiber and 14 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q1-2013. | 69 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 53 miles of fiber and 14 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q1-2013. | 2012-11-27 15:31 | 2012-11-27 15:31 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2012 | Q4 | Q4 - 2012 | 8914 | 7696 | FALSE | 76 | Milestone baseline variance will continue into this quarter but will be much closer to the original baseline. Reasons for variance are indicated below. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by the end of Q2-2013. | 39 |  | Milestone baseline variance will continue into this quarter. We anticipate catching up to our baseline projections by the end of Q2-2013. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 100 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for design work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2013. | 100 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2013. | 100 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The Construction Permits and Other Approvals are dependent upon finalizing design and route engineering. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q1-2013. | 62 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. 6 additional points of interconnection will be completed during this quarter with more in progress. We anticipate catching up to our baseline projections by the end of Q2-2013 | 54 | Milestone baseline variance will continue into this quarter. Additional equipment is ordered and costs are incurred as they are needed rather than procuring all the equipment up front as indicated in the original baseline. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q2-2013. | 80 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 70 miles of fiber and 6 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q1-2013. | 80 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 70 miles of fiber and 6 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q2-2013. | 80 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 70 miles of fiber and 6 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q1-2013. | 2013-02-22 15:22 | 2013-02-22 15:22 | 6034 | 6034 | Utopia | TRUE
NT10BIX5570127 | 2013 | Q1 | Q1 - 2013 | 10040 | 8571 | FALSE | 86 | Milestone baseline variance will continue into this quarter but will be much closer to the original baseline. Reasons for variance are indicated below. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by the end of Q2-2013. | 45 |  | Milestone baseline variance will continue into this quarter. We anticipate catching up to our baseline projections by the end of the award period. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 100 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for design work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q2-2013. | 100 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q2-2013. | 100 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. The Construction Permits and Other Approvals are dependent upon finalizing design and route engineering. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. We anticipate catching up to our baseline projections by end of Q2-2013. | 62 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale and West Valley. 18 additional points of interconnection will be completed during this quarter with more in progress. We anticipate catching up to our baseline projections by the end of Q2-2013 | 54 | Milestone baseline variance will continue into this quarter. Additional equipment is ordered and costs are incurred as they are needed rather than procuring all the equipment up front as indicated in the original baseline. This variance will not negatively impact completion of the project. We anticipate catching up to our baseline projections by end of Q2-2013. | 91 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 95 miles of fiber and 18 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q2-2013. | 91 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 95 miles of fiber and 18 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q2-2013. | 91 | Milestone baseline variance will continue into this quarter. Additional resources have been added to the project and significant gains will be made. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 95 miles of fiber and 18 points of interconnect will be completed during this quarter. We anticipate catching up to our baseline projections by the end of Q2-2013. | 2013-05-31 18:29 | 2013-05-31 18:29 | 6069 | 6069 | Utopia | TRUE
NT10BIX5570127 | 2013 | Q2 | Q2 - 2013 | 10826 | 9085 | FALSE | 96 | Milestone baseline variance will continue into this quarter but will be much closer to the original baseline. Reasons for variance are indicated below. This variance will not negatively impact completion of the project. Project will be completed by September 30, 2013. | 100 |  | Milestone baseline variance will continue into this quarter. We anticipate catching up to our baseline projections by the end of the award period. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities are being implemented. Additional surveys have been completed to add new community anchor institutions and required route changes to the project. | 100 | The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Generally the physical completion of the Network Design lags slightly behind the completion of the associated Rights of Way. The network design and detailed route engineering is dependent on securing these sites in order for design work to begin. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. Project will be completed by September 30, 2013 | 100 | The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. Project will be completed by September 30, 2013 | 100 | The Construction Permits and Other Approvals are dependent upon finalizing design and route engineering. The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. These delays are not expected to significantly impact project completion, key indicators and initial construction activities. Project will be completed by September 30, 2013 | 65 | Site prep for 62 sites will be completed and the project will be completed by September 30, 2013. | 92 | Milestone baseline variance will continue into this quarter. Additional equipment is ordered and costs are incurred as they are needed rather than procuring all the equipment up front as indicated in the original baseline. This variance will not negatively impact completion of the project. Project will be completed by September 30, 2013 | 98 | Milestone baseline variance will continue into this quarter. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 45 miles of fiber and 3 points of interconnect will be completed during this quarter. Project will be completed by September 30, 2013 | 92 | Milestone baseline variance will continue into this quarter. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 45 miles of fiber and 3 points of interconnect will be completed during this quarter. Project will be completed by September 30, 2013 | 98 | Milestone baseline variance will continue into this quarter. The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. An additional 45 miles of fiber and 3 points of interconnect will be completed during this quarter. Project will be completed by September 30, 2013 | 2013-08-30 14:22 | 2013-08-30 14:22 | 6069 | 6069 | Utopia | TRUE
NT10BIX5570127 | 2013 | Q3 | Q3 - 2013 | 12300 | 10474 | FALSE | 100 | Project has been completed but will continue to see a variance in our baseline as we continue to occur some costs as final inspections and retention are released. | 100 | N/A | Project has been completed. | 100 | No Variance. A FONSI was issued for the project. UTOPIA has implemented protocols and measures to ensure compliance with required Best Management Practices for Attaching to Broadband Cable to Historic structures provided by NTIA and in concurrence the State Historic Preservation Society requirements. Protocols and measures implemented include technical training, compliance directives, site specific surveys identifying special compliance requirements and inspection/supervision during and after installations. Project Protection Protocols and Measurement activities were implemented. | 100 | The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Project has been completed. | 100 | The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Project has been completed. | 100 | The expenditures for 2c, 2d, and 2e are captured collectively as the engineering for the project. Project has been completed. | 100 | The site prep for 62 sites have been completed. Project has been completed. | 100 | All of the equipment has been purchased and deployed. Project has been completed. | 100 | The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Project has been completed. | 100 | The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Project has been completed. | 100 | The expenditures for 2h, 2i, and 2j are captured collectively as the construction for the project. Project has been completed. | 2014-07-03 11:28 | 2014-07-03 11:28 | 6069 | 6069 | Utopia | TRUE
NT10BIX5570128 | 2010 | Q4 | Q4 - 2010 | 1112 | 2151 | FALSE | 24 | N/A | 0 |  | N/A | 100 | N/A | 74 | N/A | 78 | N/A | 78 | N/A | 40 | N/A | 21 | N/A | 17 | N/A | 16 | N/A | 10 | N/A | 2011-02-11 18:03 | 2011-02-11 18:03 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2011 | Q1 | Q1 - 2011 | 2182 | 2836 | FALSE | 45 | Overall project was slowed down by the Environmental Assessment process. |  |  | N/A | 100 | N/A | 92 | N/A | 94 | Troy Cable has hired an additional contractor to assist the mapping department catch up with the initial Project projections contained within the baseline. | 94 | Troy Cable has hired an additional contractor to assist the mapping department catch up with the initial Project projections contained within the baseline. | 60 | Troy Cable has hired an additional contractor to assist the mapping department catch up with the initial Project projections contained within the baseline. | 42 | Overall project was slowed down by the Environmental Assessment process. | 40 | Overall project was slowed down by the Environmental Assessment process. | 16 | N/A | 5 | Overall project was slowed down by the Environmental Assessment process. | 2011-05-19 16:21 | 2011-05-19 16:21 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2011 | Q2 | Q2 - 2011 | 2938 | 3226 | FALSE | 25 | Overall Project was slowed down by the Environmental Assessment process. | 0 |  | N/A | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 60 | N/A | 60 | Troy Cable has hired an additional contractor to assist the mapping department with the initial Project projections contained within the baseline. | 60 | Troy Cable has hired an additional contractor to assist the mapping department with the initial Project projections contained within the baseline. | 0 | This section is misleading. Based on discussions with the Project's cash match lender, Troy Cable elected to remove land for the hub sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the Project. Additionally, Troy Cable elected not to use to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project - the purchase of one hub site with an existing building and the purchase of two other parcels of land for hub site locations; with the completion of concrete foundations, ground work and fencing for these two locations. | 21 | Overall Project was slowed down by the Environmental Assessment process. | 25 | Overall Project was slowed down by the Environmental Assessment process. | 17 | Overall Project was slowed down by the Environmental Assessment process. | 5 | Overall Project was slowed down by the Environmental Assessment process. | 2011-08-05 16:22 | 2011-08-05 16:22 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2011 | Q3 | Q3 - 2011 | 3914 | 3795 | FALSE | 27 | Overall Project was slowed down by the Environmental Assessment process. | 0 |  | N/A | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 90 | Overall Project was slowed down by the Environmental Assessment process. | 90 | Troy Cable has hired an additional contractor to assist the mapping department with the initial Project projections contained within the baseline. | 90 | Troy Cable has hired an additional contractor to assist the mapping department with the initial Project projections contained within the baseline. | 0 | This section is misleading. Based on discussions with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the hub sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the Project. Additionally, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project - the purchase of one hub site with an existing building and the purchase of two other parcels of land for hub site locations; with the completion of concrete foundations, ground work and fencing for these two locations. Prefabricated Hub Sites have been delivered to Enterprise # 2 and Midland City and the other Hub Site in Enterprise has been secured but none of those sites have been brought on line. | 67 | Troy Cable will award and contract various Request for Proposals during the Fourth Quarter for additional Equipment and order additional equipment and materials for Request for Proposals that were released in late September 2011, including: GPON and Access Equipment; DWDM Network; Installer Truck(s); Switches; VOD System; and Routers. | 33 | Due to lead times on materials the Project did not get as many miles as projected after receiving the FONSI. Troy Cable has added one additional Underground crew and three additional construction employees to existing Aerial Crew. The awarded Construction Contractor has also added one additional Aerial crew to their construction crew. A total of five (5) Aerial Crews and two (2) Underground Crews are currently working on the Project to catch Troy Cable up to the Projections. | 61 | Troy Cable will award and contract various Request for Proposals during the Fourth Quarter for additional Equipment and order additional equipment and materials for Request for Proposals that were released in late September 2011, including: GPON and Access Equipment; DWDM Network; Installer Truck(s); Switches; VOD System; and Routers. | 35 | Network testing is based on fiber deployment and build out. Troy Cable has implemented an aggressive plan to catch up to the projections as outlined in the original baseline. | 2011-11-07 17:00 | 2011-11-07 17:00 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2011 | Q4 | Q4 - 2011 | 5374 | 5044 | FALSE | 48 | Overall Project was delayed from original Baseline due to Environmental Assessment process. | 0 |  | N/A | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2012. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 90 | Overall Project was delayed from original Baseline due to Environmental Assessment process. | 90 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan and has hired an additional contractor to assist the mapping department with initial Project projections noted in the Baseline. | 90 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan and has hired an additional contractor to assist the mapping department with initial Project projections noted in the Baseline. | 0 | This section is misleading. Based on discussions with the Projectâ€™s cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the project. Additionally, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Sites with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, ground work and fencing for these two locations. Prefabricated Hub Sites have been delivered to the following locations: Enterprise # 2 (North) and Midland City. The following Hub Sites have been brought on line as of December 31, 2011: Enterprise #1 (South) and Enterprise #2 (North). Both Enterprise sites will have the DWDM Network installed next quarter. Next quarter, the following existi | 61 | Troy Cable will launch a Request for Proposal during the First Quarter 2012 for Equipment relevant to the Firewall. The Team has awarded contracts and has continued ordering and receiving equipment for Request for Proposals released during previous quarters. Troy Cable has ordered and begun receiving equipment including: Business Support Systems (â€œOSS/BSSâ€); DC Power System; VOD System; DWDM Network; Installer Vans; Routers; Switches; and GPON and Access Equipment. The Billing Support Systems (â€œOSS/BSSâ€) is scheduled to go on line March 1, 2012. | 38 | Due to lead times on materials the Project did not get as many miles constructed as projected after receiving the FONSI. Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on twenty-eight (28) of the fifty-two (52) job segments. The construction crews consist of three (3) Underground crews and three (3) Aerial crews. The addition of the Underground and Aerial crews reflects the progress Troy Cable is making to catch-up to the Baseline projections. | 56 | Troy Cable will launch a Request for Proposal during the First Quarter 2012 for Equipment relevant to the Firewall. The Team has awarded contracts and has continued ordering and receiving equipment for Request for Proposals released during previous quarters. Troy Cable has ordered and begun receiving equipment including: Business Support Systems (â€œOSS/BSSâ€); DC Power System; VOD System; DWDM Network; Installer Vans; Routers; Switches; and GPON and Access Equipment. The Billing Support Systems (â€œOSS/BSSâ€) is scheduled to go on line March 1, 2012. | 60 | Network testing is based on fiber deployment and Build Out. Troy Cable has implemented an aggressive plan to catch up to the Baseline projections. | 2012-02-28 17:56 | 2012-02-28 17:56 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2012 | Q1 | Q1 - 2012 | 6014 | 5606 | FALSE | 62 | Project Team Members will continually monitor progress of the total Project using % complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters Performance Progress Report projection was related to an aggressive | 0 |  | N/A | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 88 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have engineered forty-five (45) of the fifty-four (54) job segments based on maps received from our consultants. Troy Cable employees have engineered and produced forty-nine (49) bill of material for current job segments. | 91 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan and has hired an additional contractor to assist the mapping department with initial Project projections noted in the Baseline. | 91 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan and has hired an additional contractor to assist the mapping department with initial Project projections noted in the Baseline. | 0 | This section is misleading. Based on discussions with the Projectâ€™s cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the project. Additionally, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, ground work and fencing for these two locations. Prefabricated Hub Sites have been delivered to the following locations: Enterprise # 2 (North) and Midland City. The following Hub Sites have been brought on line as of December 31, 2011: Enterprise #1 (South) and Enterprise #2 (North). Both Enterprise sites will have the DWDM Network installed next quarter. Next quarter, the following existin | 92 | The Team has awarded contracts and continues to order and receive materials from the awarded Vendors for additional equipment and materials for Request for Proposals released during previous quarters like: DWDM Network; Switches; Routers; Access Gear ("ADTRAN"); Provisioning; Light Meters; Bucket Trucks; and Access Controllers. Troy Cable has ordered and begun receiving equipment for the Headend Upgrade for Fiber Distribution System. The Engineering Team has deployed the following network equipment: DWDM Network Equipment; Routers; Switches; and Access Gear. | 49 | Troy Cable has completed 383.04 fiber miles of the total 595 mile Project. Troy Cable has also placed 4.50 miles of empty pipe and 5.32 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 109.83 fiber miles were constructed during the First Quarter. The total fiber miles constructed represents 64.38% completion of the overall fiber construction. Troy Cable estimates completing 475 fiber miles of the total 595 mile Project by June 30, 2012. This estimate represents 79.83% completion. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 193.57 miles of fiber as of March 31, 2012. The Engineering Team has brought on-line a temporary ring to meet co-location requirements in Houston County. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas and has begun negotiating three (3) Interconnection Agreements. | 75 | Troy Cable has completed 383.04 fiber miles of the total 595 mile Project. Troy Cable has also placed 4.50 miles of empty pipe and 5.32 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 109.83 fiber miles were constructed during the First Quarter. The total fiber miles constructed represents 64.38% completion of the overall fiber construction. Troy Cable estimates completing 475 fiber miles of the total 595 mile Project by June 30, 2012. This estimate represents 79.83% completion. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 193.57 miles of fiber as of March 31, 2012. The Engineering Team has brought on-line a temporary ring to meet co-location requirements in Houston County. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas and has begun negotiating three (3) Interconnection Agreements. | 63 | SmartBand has tested thirty (30) of the fifty-four (54) job segments. | 2012-05-10 13:27 | 2012-05-10 13:27 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2012 | Q2 | Q2 - 2012 | 6908 | 6080 | FALSE | 67 | Project Team Members will continually monitor progress of the total Project using % complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quartersâ€™ Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. | 0 |  | Not Applicable. | 86 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 89 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have engineered forty-seven (47) of the fifty-five (55) job segments based on maps received from our consultants. Troy Cable employees have engineered and produced forty-nine (49) bills of materials for current job segments. | 92 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 92 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussions with the Projectâ€™s cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the project. Additionally, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and colocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements and | 89 | Troy Cable has ordered and installed equipment for the following Request for Proposals: Headend Upgrade for Fiber Distribution System; Billing Support System ("OSS/BSS"); DWDM Network Equipment; Routers; Switches; and Access Gear. The following existing Hub Sites and colocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements and will be connected to the DWDM Network by Third Quarter 2012. The Team has brought online a temporary ring to meet co-location requirements in Houston and Montgomery Counties. Co-location equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on five (5) Interconnection Agreements. | 48 | Troy Cable has completed 477.79 fiber miles of the total 595 mile Project. Troy Cable has also placed 26.44 miles of empty pipe and 15.52 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 94.75 fiber miles were constructed during the Second Quarter. The total fiber miles constructed represents 80.30% completion of the overall fiber construction. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 336.73 miles of fiber as of June 30, 2012. The Team has brought online a temporary ring to meet co-location requirements in Houston and Montgomery Counties. Co-location equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on five (5) Interconnection Agreements. | 84 | Troy Cable has completed 477.79 fiber miles of the total 595 mile Project. Troy Cable has also placed 26.44 miles of empty pipe and 15.52 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 94.75 fiber miles were constructed during the Second Quarter. The total fiber miles constructed represents 80.30% completion of the overall fiber construction. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 336.73 miles of fiber as of June 30, 2012. The Team has brought online a temporary ring to meet co-location requirements in Houston and Montgomery Counties. Co-location equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on five (5) Interconnection Agreements. | 62 | SmartBand has tested approximately thirty-four (34) of the fifty-five (55) job segments. | 2012-08-07 18:42 | 2012-08-07 18:42 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2012 | Q3 | Q3 - 2012 | 7972 | 6692 | FALSE | 78 | Project Team Members will continually monitor progress of the total Project using % complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quartersâ€™ Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable has connected and turned-up fifty-two (52) Community Anchor Institutions. Troy Cable has connected and turned up fifty-eight (58) Businesses. | 0 |  | Not Applicable. | 87 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task 14% under budget. | 94 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have produced fifty-two (52) bills of materials for current job segments. | 94 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 94 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussions with the Projectâ€™s cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use cash match or grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and colocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements and will b | 90 | Troy Cable has ordered and installed equipment for the following Request for Proposals: Headend Upgrade for Fiber Distribution System; Billing Support System ("OSS/BSS"); DWDM Network Equipment; Routers; Switches; Access Gear; Intelligent Policy Management; and Firewall. The following existing Hub Sites and colocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements and will be connected to the DWDM Network by Fourth Quarter 2012. The Team has brought online a temporary ring to meet colocation requirements in Houston and Montgomery Counties. Colocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed colocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection A | 55 | Troy Cable has completed 566.73 fiber miles of the total 595 mile Project. Troy Cable has also placed 24.21 miles of empty pipe and 4.02 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 88.94 fiber miles were constructed during the Third Quarter. Troy Cable projects an aggressive goal of 627 fiber miles constructed through the end of the Fourth Quarter. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 511.12 fiber miles as of September 30, 2012. The Team has brought online a temporary ring to meet colocation requirements in Houston and Montgomery Counties. Colocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed colocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 85 | Troy Cable has completed 566.73 fiber miles of the total 595 mile Project. Troy Cable has also placed 24.21 miles of empty pipe and 4.02 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 88.94 fiber miles were constructed during the Third Quarter. Troy Cable projects an aggressive goal of 627 fiber miles constructed through the end of the Fourth Quarter. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated approximately 511.12 fiber miles as of September 30, 2012. The Team has brought online a temporary ring to meet colocation requirements in Houston and Montgomery Counties. Colocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed colocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 91 | SmartBand has tested approximately forty-nine (49) of the fifty-six (56) job segments. | 2012-11-20 11:33 | 2012-11-20 11:33 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2012 | Q4 | Q4 - 2012 | 8852 | 7637 | FALSE | 87 | Project Team Members will continually monitor progress of the total Project using # complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters' Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable has connected and turned-up fifty-one (51) Community Anchor Institutions. Troy Cable has connected and turned-up one hundred fifty-one (151) Businesses. | 0 |  | Not Applicable | 91 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task under budget. | 96 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have produced fifty-four (54) bills of materials for current job segments. | 96 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 98 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussion with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use Cash Match or Grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements. | 96 | The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties with one node remaining offline in Brantley. Troy Cable anticipates the completion of the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrie | 75 | Troy Cable has completed 635.96 fiber miles, to include 424.38 route miles of new construction. Troy Cable has also placed 10.95 miles of empty pipe and 3.91 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 635.96 fiber miles, 69.23 fiber miles were constructed during the Fourth Quarter 2012. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated 382.08 fiber miles as of December 31, 2012. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties with one node remaining offline in Brantley. Troy Cable anticipates the completion of the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on one (1) Interconnection Agreement. | 92 | Troy Cable has completed 635.96 fiber miles, to include 424.38 route miles of new construction. Troy Cable has also placed 10.95 miles of empty pipe and 3.91 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 635.96 fiber miles, 69.23 fiber miles were constructed during the Fourth Quarter 2012. Troy Cable has activated certain portions of the constructed job segments. Troy Cable has activated 382.08 fiber miles as of December 31, 2012. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties with one node remaining offline in Brantley. Troy Cable anticipates the completion of the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on one (1) Interconnection Agreement. | 92 | SmartBand has tested approximately forty-nine (49) of the fifty-six (56) job segments. | 2013-02-19 22:50 | 2013-02-19 22:50 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2013 | Q1 | Q1 - 2013 | 9574 | 8314 | FALSE | 88 | Project Team Members will continually monitor progress of the total Project using # complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters' Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable has connected and turned-up ninety-four (94) Community Anchor Institutions. Troy Cable has connected and turned-up two hundred forty-seven (247) Businesses. | 0 |  | Not Applicable | 90 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task under budget. | 98 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have produced fifty-six (56) bills of materials for current job segments. | 98 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 99 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussion with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use Cash Match or Grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. | 99 | The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Troy Cable completed the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on two (2) Interconnection Agreements. | 87 | Troy Cable has completed 700.51 fiber miles, to include 458.85 route miles of new construction. Troy Cable has also placed 9.23 miles of empty pipe and .22 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 700.51 fiber miles, 34.47 fiber miles were constructed during the First Quarter. Troy Cable has activated 388.95 route miles as of March 31, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Troy Cable completed the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on two (2) Interconnection Agreements. | 96 | Troy Cable has completed 700.51 fiber miles, to include 458.85 route miles of new construction. Troy Cable has also placed 9.23 miles of empty pipe and .22 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 700.51 fiber miles, 34.47 fiber miles were constructed during the First Quarter. Troy Cable has activated 388.95 route miles as of March 31, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Troy Cable completed the entire ring by end of the First Quarter 2013. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on two (2) Interconnection Agreements. | 95 | SmartBand has tested approximately fifty (50) of the fifty-six (56) job segments. | 2013-04-30 21:20 | 2013-04-30 21:20 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2013 | Q2 | Q2 - 2013 | 10576 | 8944 | FALSE | 96 | Project Team Members will continually monitor progress of the total Project using # complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters' Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable has connected and turned-up one hundred thirty-nine (139) Community Anchor Institutions. Troy Cable has connected and turned-up three hundred fifty-seven (357) Businesses. Troy Cable anticipates connecting to an additional eight (8) CAI's. | 0 |  | Not Applicable | 90 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task under budget. | 99 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have produced fifty-eight (58) bills of materials for current job segments. | 99 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 2 of the Build Out Plan. | 99 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. | 0 | This section is misleading. Based on discussion with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use Cash Match or Grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. | 100 | The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 87 | Troy Cable has completed 474.02 route miles of new construction. Troy Cable has activated 474.02 route miles as of June 30, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 97 | Troy Cable has completed 474.02 route miles of new construction. Troy Cable has activated 474.02 route miles as of June 30, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 100 | SmartBand has tested approximately fifty (58) of the fifty-eight (58) job segments. | 2013-08-13 20:10 | 2013-08-13 20:10 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2013 | Q3 | Q3 - 2013 | 11296 | 9446 | FALSE | 100 | Project Team Members will continually monitor progress of the total Project using # complete construction reports along with budget to actual reports to measure financial milestones. Overall Project was delayed from original Baseline due to Environmental Assessment process delay. Variance from previous quarters' Performance Progress Report projection was related to an aggressive projection from previous quarters with a more realistic goal. Troy Cable connected and turned-up one hundred forty-six (146) Community Anchor Institutions. Troy Cable has connected and turned-up four hundred (400) Businesses. Troy Cable anticipates connecting to an additional fifty-two (52) CAI's. | 0 |  | Not Applicable. | 100 | The Environmental Assessment was completed and approved by the National Telecommunications and Information Administration during the First Quarter 2011. The percent complete is misleading for the Environmental Assessment because our consultant completed the task under budget. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. | 100 | Our Engineering Consultants have completed 100% of the mapping field work. Troy Cable employees have produced approximately eighty (80) bills of materials for current job segments. | 100 | Troy Cable has continued requesting the necessary permits for Rights of Way for areas included in Phase 3 of the Build Out Plan. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. | 100 | Troy Cable has continued to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 3 of the Build Out Plan. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. | 0 | This section is misleading. Based on discussion with the Project's cash match lender and NTIA, Troy Cable elected to remove land for the Hub Sites from the Project. Troy Cable did not use Cash Match or Grant funds to purchase land for the Project. In addition, Troy Cable elected not to use match or grant funds to make improvements to the land. The following activities have been completed outside of the Project: the purchase of one (1) Hub Site with an existing building; and the purchase of two (2) other parcels of land for Hub Site locations with the completion of concrete foundations, prefab Telecom Shelters, ground work and fencing for these two locations. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. | 100 | The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. The following existing Hub Sites and collocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; Brantley; and Montgomery. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 100 | Troy Cable has completed 501.00 route miles of new construction. Troy Cable has activated 501.00 route miles as of September 30, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 100 | Troy Cable has completed 501.00 route miles of new construction. Troy Cable has activated 501.00 route miles as of September 30, 2013. The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston & Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. | 100 | SmartBand has will test approximately eighty (80) job segments. Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. | 2013-11-19 16:15 | 2013-11-19 16:15 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | 2013 | Q4 | Q4 - 2013 | 12260 | 10430 | FALSE | 100 | No variance from the Baseline. | 0 |  | No variance from the Baseline. | 100 | No variance from the Baseline. | 100 | No variance from the Baseline. | 100 | No variance from the Baseline. | 100 | No variance from the Baseline. | 0 | No variance from the Baseline. | 100 | No variance from the Baseline. | 100 | No variance from the Baseline. | 100 | No variance from the Baseline. | 100 | No variance from the Baseline. | 2014-06-02 15:01 | 2014-06-02 15:01 | 6116 | 6116 | Troy Cablevision, Inc. | TRUE
NT10BIX5570129 | 2010 | Q4 | Q4 - 2010 | 1358 | 2373 | FALSE | 3 | Total expenditures for next quarter are anticipated to be 3% of total project budget. The baseline plan anticipated expenditures of 20% total project cost. This variance is due to several factors, including discrepancy of network procurement timeline between baseline data and project plan. Also, site preparation on the data center will not take place during the next quarter, as was anticipated in the plan. | 25 | Grant Administration | N/A | 73 | This is alligned with baseline data and indicates the EA is on schedule for completion by next quarter. | 38 | N/A | 0 | Baseline plan anticipated 5% completion by end of quarter. Due to delay with data center construction, the anticipated draw downs associated with contract award are not anticpated to occur during the quarter. | 9 | This is based on anticipated draw downs for engineering fees pertaining to linear construction. Due to potential route change holdups and data center delay, draw downs for this milestone are 23% less complete than expected. | 0 | The baseline plan anticipated 10% of this milestone completed by the end of the quarter. This is based on the scheduled site preparation activities for the data center. There is a discrepancy between the baseline data and baseline project plan. Baseline project plan calls for the award of contract for data center design and engineering, but no site preparation will occur, as is projected in the baseline data. | 9 | This is based on anticipated purchase of DSLAM equipment. Baseline plan anticipated 19% completion. | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-24 09:26 | 2011-02-24 09:26 | 6108 | 6108 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2011 | Q1 | Q1 - 2011 | 2298 | 2894 | FALSE | 4 | Estimated expenditures of $433,747 represents 4% of total project funds. The data center design procurement is nearly complete, with interviews conducted on May 20th. Contract negotiations have begun, and the design of the data center will be under way before the end of June. Interview with four different firms competing for the design work all indicated that the construction of the facility can be completed in eight months, for an overall start to finish for the data center of no more than one year, or only slightly behind original timeframe. Fiber route survey work will be 100% complete at the end of May, and fiber route engineering is estimated to be 60% complete by the end of June. Issues with rocky soil and aerial pole agreements have slowed engineering. The three localities have agreed on an approach for equitably sharing local match and distribution of fiber connections, and approval is anticipated at the first project review meeting in June. Terms for the Washington and Lee | 34 | Grant Administration | N/A | 100 | N/A | 70 | N/A | 80 | N/A | 66 | N/A | 2 | The baseline plan indicated 30% of milestone complete. Based on estimated expenditure of $60,000 on cabinet site work, 2% of milestone category will be complete. Discrepancy based on data center rebid. | 3 | Purchase of $75,000 of cabinet equipment represent 3% of equipment budget. Baseline plan indicated 43% completion by end of quarter. This is explained by discrepancy in project plan timeline | 0 | The variance from the baseline plan, which anticipated this milestone as 12% complete is due to the decision to rebid the data center. | 0 | N/A | 0 | N/A | 2011-05-25 13:30 | 2011-05-25 13:30 | 6108 | 6108 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2011 | Q2 | Q2 - 2011 | 3150 | 3335 | FALSE | 9 | Estimated expenditures of $929,820 represents 9% of total project funds. Baseline plan indicated 60% of overall project completion by end of quarter. As has been explained in previous reports, delays to the environmental assessment, data center design, and route engineering have set the project off of its baseline time line. However, data center design firm is now under contract and construction on the data center is likely to be complete is less than one year. Route engineering is complete and fiber construction is on schedule to begin in the fall. | 42 | Grant Administration | No variance | 100 | The environmental assessment final submission was delayed due to the need for a Phase 1 survey on the data center site. This survey has been complete. The environmental assessment is on track for late July submission. | 100 | No variance | 28 | Baseline Plan anticipated 100% percent completion of milestone by end of quarter. Planned completion is approximately 72% lower. Negative variance from baseline plan is attributed to delays to the environmental assessment and route engineering. It is likely that Rights of way will be fully complete by 2011, Q4, only delaying completion of milestone by 1 quarter. | 67 | Baseline Plan anticipated 96% percent completion of milestone by end of quarter. Planned completion is approximately 30% lower. Negative variance from baseline plan is attributed to delays in selection of data center design firm selection and route engineering. Due to these delays, it is anticipated that all relative permits will be drafted and submitted, but approval of all permits is not anticipated until 2011, Q4. | 23 | Planned expenditures of $10,000 for DSL site prep represents 23% of budgeted site prep work. The baseline's anticipated milestone to be 50% complete. Variance is explained by the delay in DSL construction due to the environmental assessment submission delay. | 9 | Planned purchase of $200,000 for cabinet and network equipment represents 9% of equipment budget. Baseline plan indicated 67% completion of milestone by end of quarter. This negative variance is explained by discrepancy in project plan timeline and delays resulting from the environmental assessment. | 0 | Baseline Plan anticipated 23% completion of milestone. Due to delays with the environmental assessment, construction is not anticipated to begin during this quarter. | 0 | Baseline Plan anticipated 12% completion of milestone. Due to delays with the environmental assessment, construction is not anticipated to begin during this quarter. Equipment for the DSL cabinets and fiber network will be ordered during the quarter, but no deployment is anticipated during this quarter. | 0 | Baseline Plan anticipated 10% completion of milestone. Due to delays with the environmental assessment, construction is not anticipated to begin during this quarter. Testing cannot take place if equipment is not deployed. | 2011-08-17 12:23 | 2011-08-17 12:23 | 6108 | 6108 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2011 | Q3 | Q3 - 2011 | 4168 | 3932 | FALSE | 18 | Estimated expenditures of $1,814,820 represents 18% of the total project funds. Baseline plan indicated 69% of overall project completion by the end of the quarter. As has been explained in previous reports, delays to the environmental assessment, data center design, and route engineering have set the project off of its baseline time line. However, data center construction is likely to start during this quarter and be completed by Summer 2012. Route engineering is complete. The fiber construction RFP will be released during the first week of December and will be due back four weeks later. We expect to make an award for that work in January, and work will start in February. | 50 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 49 | 100% of the needed easements have been identified which makes up 15% of this overall milestone and there will be about 40% of the needed easements gathered during 2011, Q4. The combination of the 15% from the completion of the identification of the easements and 40% of the easements being gathered gives the 49% completion of this overall milestone. Baseline plan indicated 100% of the ROW's would have been completed by end of this quarter. This has been delayed by the route engineering and deciding on the placement of some of the DSL sites. Delays have also been because of a legal delay on approving the easement agreements. | 89 | All relative permits should be submitted by the end of the quarter and we will be waiting on some of the approvals. Most of the permit approvals should be granted by the end of the quarter. Baseline plan anticipated 100% completion of milestone by the end of the quarter. Negative variance is attributed to delays in the selection of data center design firm and route engineering. | 23 | Planned expenditures of $10,000 for DSL site prep represents 23% of budgeted site prep work. The baseline plan anticipated a milestone completion of 70%. Variance is explained by the delay in DSL construction due to the environmental assessment submission and approval delay. | 22 | Planned purchase of $500,000 for cabinet and network equipment represents 22% of equipment budget. Baseline plan indicated 89% completion of milestone by end of quarter. This negative variance is explained by discrepancy in project plan timeline and delays resulting from the environmental assessment. Also, delays in easement procurement has delayed the ordering of equipment. | 2 | Baseline plan anticipated 33% completion of milestone. Negative variance is due to delays with the environmental assessment. Data Center construction is expected to begin during this quarter. | 0 | Baseline plan anticipated 24% completion of milestone. Due to delays with the environmental assessment, DSL construction is not anticipated to begin during this quarter. Equipment for the DSL cabinets and fiber network will be ordered during the quarter, but no deployment is anticipated. DSL equipment (DSLAMs, UPSes, batteries, patch panels) will be installed in the DSL cabinets as construction in complete at each of the 29 sites. This work will begin in 2012 Q1. Customers will be able to begin purchasing services on a rolling basis as soon as the equipment is installed, so some customers should be receiving service in 2012 Q2. The data center is scheduled for completion in 2012 Q2, and fiber equipment will be installed in the data center as soon as all major construction and mechanical work is completed. Network equipment in fiber cabinets will be installed as the fiber construction on fiber segments connected to the cabinet are complete. Portions of the network will be lit and cu | 0 | Baseline plan anticipated 22% completion of milestone. Due to delays with the environmental assessment, DSL construction is not anticipated to begin during this quarter. Testing cannot take place if equipment is not deployed. Network testing will begin as soon as the data center and the first fiber segments are completed in 2012 Q2. Network testing will continue on a rolling basis as additional fiber route segments are completed, with all testing complete in 2012 Q4. | 2011-11-21 09:46 | 2011-11-21 09:46 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2011 | Q4 | Q4 - 2011 | 5226 | 4890 | FALSE | 35 | Estimated expenditures of $3,525,392 represents 35% of the total project funds. Baseline plan indicated 70% of overall project completion by the end of the quarter. As has been explained in previous reports, delays in submission and approval of the environmental assessment, data center design, data center contract negotiations, and route engineering have set the project off of its baseline time line. However, data center construction will start during this quarter and will be completed by Summer 2012. Route engineering has been completed. We are expecting to make an award for the cabinet procurement, fiber procurement, conduit procurement, fiber network construction, and cabinet construction during 2012 Q1. The fiber network construction and the cabinet construction is expected to begin late 2012 Q1 or early 2012 Q2. | 58 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 80 | Baseline plan indicated 100% completion of this milestone by the end of this quarter. Negative variance has been caused by the delay in the submission and approval of the environmental assessment, the delay in route engineering, and the delay in the planned placement of some of the DSL cabinet sites. Delays have also come from the delay in the legal review of the easement agreements. The County has been actively getting easement agreements signed and will continue to get the needed easements. The easements that are needed will NOT delay the start of construction as the majority of the route does not need easements or they will have already been gathered. | 96 | All relative permits should be submitted by the end of the quarter and we will only be waiting on the approval of the cabinet construction permit. Baseline plan anticipated 100% completion of this milestone by the end of the quarter. Negative variance is attributed to delays in the submission and approval of the environmental assessment, the selection of the data center design firm, and fiber route engineering. | 27 | Planned expenditures of $10,000 for cabinet site preparation represents 27% of what is budgeted for site preparation work. The baseline plan anticipated a milestone completion of 100%. Negative variance is explained by the delay in cabinet construction due to the environmental assessment submission and approval delay. It can also be attributed by the delay in the legal review of the cabinet site construction bid documents. The cabinet construction bid was advertised during 2011 Q4 and is expected to be awarded during 2012 Q1. We are anticipating the cabinet construction to begin in late 2012 Q1 or early 2012 Q2. | 28 | Planned purchase of $641,816 for cabinets, fiber, and conduit represents over 28% of the equipment budget. Baseline plan indicated 100% completion of this milestone by the end of the quarter. This negative variance is explained by discrepancy in project plan timeline and delays resulting from the environmental assessment. Also, delays in the legal review of the bid documents has delayed the advertisement of the equipment procurement bids. The bid documents were advertised during 2011 Q4 and are due back early 2012 Q1. We are anticipating issuing a purchase order for the fiber, conduit, and cabinets during 2012 Q1. | 20 | Baseline plan anticipated 45% completion of this milestone. Negative variance is due to delays with the environmental assessment, delay with legal review of the network construction bid documents, and lengthy data center contract negotiations. The data center contract has been signed and construction is anticipated to start during 2012 Q1. Also, the fiber network construction and cabinet construction contracts are expected to be awarded during 2012 Q1 with construction beginning late 2012 Q1 or early 2012 Q2. | 0 | Baseline plan anticipated 37% completion of this milestone. Due to delays with the environmental assessment, cabinet construction is not anticipated to begin until late 2012 Q1 or early 2012 Q2. The cabinets, fiber, and conduit will be ordered during this quarter, but no deployment is anticipated. DSL equipment (DSLAMs, UPSes, patch panels) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. Customers will be able to begin purchasing services on a rolling basis as soon as the equipment is installed. The data center is scheduled for completion in 2012 Q2, and fiber equipment will be installed in the data center as soon as all major construction and mechanical work is completed. Network equipment in fiber cabinets will be installed as the fiber construction on fiber segments connected to the cabinets are complete. Portions of the network will be lit and customers will be connected on a rolling basis once the data center is complete and the first fib | 0 | Baseline plan anticipated 35% completion of this milestone. Due to delays with the environmental assessment and legal review of the network construction bid documents, cabinet construction is not anticipated to begin until late 2012 Q1 or early 2012 Q2. The data center contract negotiations also delayed the start of the data center construction, which is anticipated to start 2012 Q1. Network testing will begin as soon as the data center and the first fiber segments are completed. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2012-02-23 16:23 | 2012-02-23 16:23 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2012 | Q1 | Q1 - 2012 | 6132 | 5668 | FALSE | 52 | Estimated expenditures of $5,195,512 represents over 52% of the total project funds. Baseline plan indicated 82% overall project completion by the end of the quarter. As has been explained in previous reports, delays in the submission and approval of the environmental assessment, data center design, data center contract negotiations, route engineering, and delays in the legal review of the network construction bid documents and contracts have set the project off of its baseline time line. However, data center construction has begun and will be completed by Summer 2012. Route engineering has been completed. We have made an award for the cabinet, conduit, and fiber procurements. There has also been an award made for the cabinet and fiber network construction contracts and we expect to have those contracts signed and for construction to begin next quarter. | 66 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 90 | Baseline plan indicated 100% completion of this milestone by the end of this quarter. Negative variance has been caused by the delay in the submission and approval of the environmental assessment, the delay in route engineering, and the delay in the planned placement of some of the DSL cabinet sites and in locating the existing Century Link easement. Delays have also come from the delay in the legal review of the easement agreements. A local firm has been hired to locate and pursue these easements. The easements that are needed will NOT delay the start of construction as the majority of the routes do not need easements or they have already been gathered. | 100 | No variance | 27 | Planned expenditures of $10,000 for cabinet site preparation represents 27% of what is budgeted for site preparation work. The baseline plan anticipated a milestone completion of 100%. Negative variance is explained by the delay in cabinet construction due to the environmental assessment submission and approval delay. It can also be attributed by the delay in the legal review of the cabinet site construction bid documents and the delay in contract preparation. The cabinet construction is expected to be signed and construction started during the next quarter. | 28 | Planned purchase of $641,816 for cabinets, fiber, and conduit represents over 28% of the equipment budget. Baseline plan anticipated 100% completion of this milestone by the end of the quarter. Negative variance is explained by discrepancies in the project plan timeline and delays resulting from the environmental assessment. Discrepancies in the project plan timeline are due to the lead times on fiber. We have issued the purchase order for the fiber but it will not be invoiced until the fiber is delivered. We are expecting fiber to begin being delivered during 2012 Q3. This delay however will not hold up construction as the contractor will be installing the conduit first. Also, delays in the legal review of the bid documents delayed the advertisement of the equipment procurement bids. The bids were advertised during 2011 Q4 and were due back during 2012 Q1. The awards for Conduit, Fiber, and Cabinets were made in February and we are expecting to receive equipment shipments throughout n | 30 | Baseline plan anticipated 55% completion of this milestone. Negative variance is due to delays with the environmental assessment, delay with the legal review of the network construction bid documents, delay in the legal preparation and review of the construction contracts, and lengthy data center contract negotiations. The data center construction has begun and is scheduled to be completed during 2012 Q2. The cabinet and fiber network construction will begin during 2012 Q2. | 5 | Baseline plan anticipated 50% completion of this milestone. Due to delays with the environmental assessment, cabinet construction did not begin this quarter, 2012 Q1, but is expected to start during next quarter, 2012 Q2. Cabinets and conduit are expected to begin being placed in the ground and at their location throughout 2012 Q2. DSL equipment (DSLAMs, UPSes, patch panels, etc.) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. Customers will be able to begin purchasing services on a rolling basis as soon as the equipment is installed. The data center is scheduled for completion in 2012 Q2, and fiber equipment will be installed in the data center as soon as all major construction and mechanical work is completed. Network equipment in fiber cabinets will be installed as the fiber construction on fiber segments connected to the cabinets are complete. Portions of the network will be lit and customers will be connected on a rolling basis once the | 0 | Baseline plan anticipated 48% completion of this milestone. Due to delays with the environmental assessment and legal review of the network construction bid documents and preparation of the construction contracts, cabinet construction is anticipated to begin during 2012 Q2 but no network equipment will be deployed. The data center contract negotiations also delayed the start of the data center construction, which began during 2012 Q1 and is expected to be completed 2012 Q2. Network testing will begin as soon as the data center and the first fiber segments are completed. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2012-05-16 12:19 | 2012-05-16 12:19 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2012 | Q2 | Q2 - 2012 | 7130 | 6192 | FALSE | 60 | Estimated expenditures of $5,957,000 represents 60% of the total project funds. Baseline plan indicated 87% overall project completion by the end of the quarter. As has been explained in previous reports, delays in the submission and approval of the environmental assessment, data center design, data center contract negotiations, route engineering, delays in the legal review of the network construction bid documents and contracts, and delays in getting the Rockbridge County-City of Lexington agreement and VDOT permits have set the project off of its baseline time line. However, data center construction is almost complete and is scheduled for completion during 2012 Q3. Route engineering has been completed and construction for both the DSL cabinets and the fiber network are underway. We are expecting to get the VDOT permits next quarter, 2012 Q3, and the Rockbridge County-City of Lexington agreement has been signed. All of the cabinets and conduit are on site and we are expecting to have | 75 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 90 | Baseline plan indicated 100% completion of this milestone by the end of this quarter. Negative variance has been caused by the delay in the submission and approval of the environmental assessment, the delay in route engineering, and the delay in the planned placement of some of the DSL cabinet sites and in locating the existing Century Link easement. Delays have also come from the delay in the legal review of the easement agreements. A local firm has been hired to locate and pursue these easements. The easements that are needed will NOT delay construction as the majority of the routes do not need easements or they have already been gathered. We anticipate to have all of the needed easements for the project before the end of 2012. | 100 | No variance | 30 | Baseline plan anticipated a milestone completion of 100%. Negative variance is explained by the delay in cabinet construction due to the environmental assessment submission and approval delay. It can also be attributed by the delay in the legal review of the cabinet site construction bid documents and the delay in contract preparation. The cabinet construction contract is signed and construction has begun. | 58 | Planned purchase of $1,300,000 for fiber and other equipment represents over 58% of the equipment budget. Baseline plan anticipated 100% completion of this milestone by the end of the quarter. Negative variance is explained by discrepancies in the project plan time line and delays resulting from the environmental assessment. We are expecting fiber to be delivered during 2012 Q3. Other equipment purchases will be made by the fiber contractor for handholes, splice closures, etc., and will be invoiced for during 2012 Q3. Also, delays in the legal review of the procurement bid documents delayed the advertisement of the equipment procurement bids. The have since been advertised and received and purchase orders sent out. All of the conduit and cabinets are on site and we are anticipating the entire shipment of fiber to be made next quarter, 2012 Q3. | 45 | Baseline plan anticipated 67% completion of this milestone. Negative variance is due to delays with the environmental assessment, delay with the legal review of the network construction bid documents, delay in the legal preparation and review of the construction contracts, and lengthy data center contract negotiations. The data center construction has begun and is scheduled to be completed during 2012 Q3. The cabinet and fiber network construction has begun. We expect to have the VDOT permits and the Rockbridge County-City of Lexington agreement next quarter, 2012 Q3, and for the fiber network construction to pick up speed. | 15 | Baseline plan anticipated 62% completion of this milestone. Negative variance is due to delays with the environmental assessment and legal reviews of the bid documents and the construction contracts. Cabinet and fiber network construction have begun. DSL equipment (DSLAMs, UPSes, patch panels, etc.) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. Customers will be able to begin purchasing services on a rolling basis as soon as the equipment is installed. The data center is scheduled for completion in 2012 Q3, and fiber equipment will be installed in the data center as soon as all major construction and mechanical work is completed. Network equipment in fiber cabinets will be installed as the fiber construction on fiber segments connected to the cabinets are complete. Portions of the network will be lit and customers will be connected on a rolling basis once the data center is complete and the first fiber segments are completed. | 0 | Baseline plan anticipated 61% completion of this milestone. Due to delays with the environmental assessment and legal review of the network construction bid documents and preparation of the construction contracts, cabinet construction has begun but no DSL network equipment has been deployed. The data center contract negotiations also delayed the start of the data center construction, which has now begun and is expected to be completed 2012 Q3. Network testing will begin as soon as the data center and the first fiber segments are completed. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2012-08-17 16:59 | 2012-08-17 16:59 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2012 | Q3 | Q3 - 2012 | 8134 | 6775 | FALSE | 69 | Estimated expenditures of $6,954,000 represents over 69% of the total project funds. Baseline plan indicated 91% overall project completion by the end of the quarter. As has been explained in previous reports, delays in the submission and approval of the environmental assessment, data center design, data center contract negotiations, route engineering, delays in the legal review of the network construction bid documents and contracts, and delays in getting the Rockbridge County-City of Lexington agreement and VDOT permits have set the project off of its baseline time line. However, data center construction is almost complete and is scheduled for completion and acceptance during 2012 Q4. Route engineering has been completed and construction for both the DSL cabinets and the fiber network are underway. All of the cabinets, conduit, and fiber is on site and we are expecting to begin getting the fiber and DSL network equipment shipped throughout the next quarter. | 83 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 62 | Baseline plan anticipated a milestone completion of 100%. Negative variance is explained by the delay in cabinet construction due to the environmental assessment submission and approval delay. It can also be attributed by the delay in the legal review of the cabinet site construction bid documents and the delay in contract preparation. The cabinet construction contract is signed and construction is underway. We are currently waiting on CenturyLink to get back on the cabinet placement requirements for the remaining cabinets. We are expecting to being getting those requirements during the next quarter, 2012 Q4. | 67 | Planned purchase of $1,500,000 for fiber and other equipment represents 67% of the equipment budget. Baseline plan anticipated 100% completion of this milestone by the end of the quarter. Negative variance is explained by discrepancies in the project plan time line and delays resulting from the environmental assessment. Fiber has been delivered and we are expecting to have some of the fiber and DSL network equipment delivered during 2012 Q4.Also, delays in the legal review of the procurement bid documents delayed the advertisement of the equipment procurement bids. The have since been advertised and received and purchase orders are being sent out as the bids are evaluated. All of the conduit, cabinets, and fiber are on site and we are anticipating shipments of fiber and DSL equipment to be made next quarter, 2012 Q4. | 65 | Baseline plan anticipated 77% completion of this milestone. Negative variance is due to delays with the environmental assessment, delay with the legal review of the network construction bid documents, delay in the legal preparation and review of the construction contracts, and lengthy data center contract negotiations. The data center construction is very close to completion and is scheduled for completion and acceptance during 2012 Q4. The cabinet and fiber network construction is underway. The fiber contractor has finished construction in downtown Lexington and we are expecting them to make substantial progress now that they have started working in the County. | 25 | Baseline plan anticipated 75% completion of this milestone. Negative variance is due to delays with the environmental assessment and legal reviews of the bid documents and the construction contracts. Cabinet and fiber network construction are underway and both contractors have been making substantial progress towards completion. DSL equipment (DSLAMs, UPSes, patch panels, etc.) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. Customers will be able to begin purchasing services on a rolling basis as soon as the equipment is installed. The data center is scheduled for completion and acceptance in 2012 Q4 with W&L installing their equipment over the Thanksgiving holiday. Network equipment in fiber cabinets will be installed as the fiber construction on fiber segments connected to the cabinets are complete. Portions of the network will be lit and customers will be connected on a rolling basis once the data center is complete and the first fiber seg | 5 | Baseline plan anticipated 74% completion of this milestone. Due to delays with the environmental assessment and legal review of the network construction bid documents and preparation of the construction contracts, cabinet construction is underway but no DSL network equipment has been deployed. The data center contract negotiations also delayed the start of the data center construction, which has now begun and is expected to be completed 2012 Q4. Network testing will begin as soon as the data center and the first fiber segments are completed. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2012-11-29 11:33 | 2012-11-29 11:33 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2012 | Q4 | Q4 - 2012 | 8944 | 7725 | FALSE | 80 | Estimated expenditures of $7,935,234 represents a little under 80% of the total project funds. Baseline plan indicated 95% overall project completion by the end of the quarter. As has been explained in previous reports, delays in the submission and approval of the environmental assessment, data center design, data center contract negotiations, route engineering, delays in the legal review of the network construction bid documents and contracts, and delays in getting the Rockbridge County-City of Lexington agreement and VDOT permits have set the project off of its baseline time line. However, data center construction is complete. Route engineering has been completed and construction for both the DSL cabinets and the fiber network are underway. All of the cabinets, conduit, and fiber is on site and we have begun getting the fiber and DSL network equipment shipped and will continue to have more delivered during next quarter. We are also expecting the fiber equipment vendors to come and be | 91 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 80 | Baseline plan anticipated a milestone completion of 100%. Negative variance is explained by the delay in cabinet construction due to the environmental assessment submission and approval delay. It can also be attributed to the delay in the legal review of the cabinet site construction bid documents and the delay in contract preparation. The cabinet construction contract is signed and construction is underway. We are expecting CenturyLink to get back to us on the cabinet placement requirements for the remaining cabinets during the next quarter and for the cabinet contractor to be cleared to work in the remaining cabinet sites. | 72 | Planned purchase of $1,600,000 for fiber and other equipment represents 72% of the equipment budget. Baseline plan anticipated 100% completion of this milestone by the end of the quarter. Negative variance is explained by discrepancies in the project plan time line and delays resulting from the environmental assessment. Fiber has been delivered and we are expecting to to continue to have the fiber and DSL network equipment delivered during 2013 Q1.Also, delays in the legal review of the procurement bid documents delayed the advertisement of the equipment procurement bids. The have since been advertised and received and purchase orders are being sent out as the bids are evaluated. All of the conduit, cabinets, and fiber are on site and we are anticipating the remaining shipments of fiber and DSL equipment to be made next quarter, 2013 Q1. The fiber equipment vendors will be installing and configuring the core and edge network equipment during next quarter, 2013 Q1. | 80 | Baseline plan anticipated 88% completion of this milestone. Negative variance is due to delays with the environmental assessment, delay with the legal review of the network construction bid documents, delay in the legal preparation and review of the construction contracts, and lengthy data center contract negotiations. The data center construction is complete. The cabinet and fiber network construction is underway. The fiber contractor has finished construction in downtown Lexington and they are making substantial progress now that they are working in the County. | 60 | Baseline plan anticipated 87% completion of this milestone. Negative variance is due to delays with the environmental assessment and legal reviews of the bid documents and the construction contracts. Cabinet and fiber network construction are underway and both contractors have been making substantial progress towards completion. DSL equipment (DSLAMs, UPSes, patch panels, etc.) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. Customers will be able to begin purchasing services on a rolling basis as soon as the equipment is installed. The data center construction is complete and W&L has installed their equipment and are operating their network out of the data center. Network equipment in fiber cabinets will begin being installed next quarter, 2013 Q1. Portions of the network will be lit and customers will be connected on a rolling basis throughout next quarter 2013, Q1. | 50 | Baseline plan anticipated 87% completion of this milestone. Due to delays with the environmental assessment and legal review of the network construction bid documents and preparation of the construction contracts, cabinet construction is underway but no DSL network equipment has been deployed. The data center contract negotiations also delayed the start of the data center construction, which is now complete. Network testing has begun as the DSL equipment has been delivered. Fiber vendors are expected to conduct the installation and configuration of the core and edge network equipment. Once installation and configuration is complete network testing will begin on the fiber network. The DSL equipment is also expected to be installed in the cabinets that are completed and testing of the DSL network will also be taking place during the next quarter, 2013 Q1. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2013-02-25 16:18 | 2013-02-25 16:18 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2013 | Q1 | Q1 - 2013 | 9884 | 8480 | FALSE | 95 | Estimated expenditures of $9,521,000 represents over 95% of the total project funds. Baseline plan indicated 100% overall project completion by the end of the quarter. As has been explained in previous reports, delays in the submission and approval of the environmental assessment, data center design, data center contract negotiations, route engineering, delays in the legal review of the network construction bid documents and contracts, delays in getting the Rockbridge County-City of Lexington agreement and VDOT permits have set the project off of its baseline time line, and delays in the approval of the business connections approval by the Environmental Assessment team. However, data center construction is complete. Route engineering has been completed and construction for both the DSL cabinets and the fiber network are underway. All of the cabinets, conduit, and fiber is on site as well as the fiber and DSL network equipment. We are also expecting the fiber equipment testing and to be | 95 | Grant Administration | Negative variance is because the grant period extends into 2013 Q3 and that was not reflected in the baseline plan. | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 95 | Baseline plan anticipated 100% completion of this milestone. Negative variance is due to delays with the environmental assessment, delay with the legal review of the network construction bid documents, delay in the legal preparation and review of the construction contracts, delay in the approval of the business connections approval by the Environmental Assessment team, and lengthy data center contract negotiations. The data center construction is complete. The cabinet and fiber network construction is underway. The fiber contractor has finished construction in downtown Lexington and other routes throughout the County, and they are making substantial progress now that they are working in the County. | 85 | Baseline plan anticipated 100% completion of this milestone. Negative variance is due to delays with the environmental assessment and legal reviews of the bid documents and the construction contracts. Cabinet and fiber network construction are underway and both contractors have been making substantial progress towards completion. DSL equipment (DSLAMs, UPSes, patch panels, etc.) will be installed in the DSL cabinets as construction is complete at each of the 29 sites. Customers will be able to begin purchasing services on a rolling basis as soon as the equipment is installed. The data center construction is complete and W&L has installed their equipment and are operating their network out of the data center. Network equipment in fiber cabinets has begun. Portions of the network will be lit and customers will be connected on a rolling basis throughout next quarter 2013, Q2. | 85 | Baseline plan anticipated 100% completion of this milestone. Due to delays with the environmental assessment and legal review of the network construction bid documents and preparation of the construction contracts, cabinet construction is underway and DSL network equipment deployment has begun. The data center contract negotiations also delayed the start of the data center construction, which is now complete. Network testing has begun on the DSL equipment as well as the fiber equipment. Fiber vendors have completed the installation and configuration of the core and edge network equipment. The DSL equipment is continuing to be installed in the cabinets that are completed and testing of the DSL network will also be taking place during the next quarter, 2013 Q2. Network testing will continue on a rolling basis as additional fiber route segments are completed. | 2013-05-23 11:29 | 2013-05-23 11:29 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2013 | Q2 | Q2 - 2013 | 10736 | 9031 | FALSE | 100 | No variance | 100 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 2013-08-26 12:00 | 2013-08-26 12:00 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570129 | 2013 | Q3 | Q3 - 2013 | 11994 | 10155 | FALSE | 100 | No variance | 100 | Grant Administration | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 2014-03-26 15:36 | 2014-03-26 15:36 | 7215 | 7215 | Rockbridge, County of | TRUE
NT10BIX5570130 | 2010 | Q4 | Q4 - 2010 | 1292 | 2314 | FALSE | 22 | Awaiting Approval of Environmental Assessment | 70 | Project notification | Project Notifications and Scheduling and General Administration/Oversight | 100 | Complete Environmental Assessment to Begin Construction | 100 | Complete Construction Drawings for Permitting | 45 | Acquire the necessary access permits for City, County, State, Utility, Private and Railroad Right of Way Access | 75 | Acquire the necessary AL DOT Permits for State Highway and Bridge Access Permits | 22 | Stage Materials/Equipment, Clear Easements, and Set-up Construction Management Sites | 24 | Purchase, Stage, Test and Burn-In Equipment | 10 | Install Infrastructure and Terminals | 23 | Deploy Core Routing, Switching at Terminals and Implement Customer Premise Devices | 19 | Test Fiber Connectivity, Network Terminals and Validate Customer Premise Connectivity | 2011-02-22 12:32 | 2011-02-22 12:32 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | 2011 | Q1 | Q1 - 2011 | 1934 | 2712 | FALSE | 11 | The Trillion team will continue to work out all site mobilization, construction, materials logistics, and systems testing and validation processes. Project timeline has been delayed as FONSI was not received as previously expected. | 55 | Project Notification | The South Central Alabama Broadband Commission authority still enrolling members. Several Municipalities have signed resolutions to join the South Central Alabama Broadband Commission. | 100 | N/A | 96 | The Trillion Team will concentrate on producing the required permit-ready drawings. Each county completed represents a 0.5% completion in the network design. | 50 | The Trillion Team will continue negotiating leases with property owners. However, no leases will be executed for terminals until the end of 2011. | 10 | The Trillion Team has applied for a permit to encompass the entire middle mile portion of the network with the Alabama DOT. The Trillion Team will secure city and county permits 1 month before construction activity starts in that area. | 10 | N/A | 20 | N/A | 5 | Begin to install infrastructure and terminals. Delayed because of FONSI | 15 | N/A | 5 | N/A | 2011-05-10 19:37 | 2011-05-10 19:37 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | 2011 | Q2 | Q2 - 2011 | 3344 | 3435 | FALSE | 18 | We are making strides to catch up with the baseline. The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 60 |  | Public Notification will be implemented across eight (8) counties in South Central Alabama. The Notification Program is being developed via a collaboration with the Broadband Authority and Stakeholders. Lowndes County Notification in currently in process. We are entering Wave 2 which will have a direct impact to all anchor institutions, businesses, and residences in the last mile FTTP serving area. | 100 | EA is complete | 97 | We are making strides to catch up with the baseline. The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 50 | There is no variance | 18 | We are making strides to catch up with the baseline. The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 13 | We are making strides to catch up with the baseline. The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 25 | There is no variance | 8 | We are making strides to catch up with the baseline. The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 18 | We are making strides to catch up with the baseline. The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 10 | We are making strides to catch up with the baseline. The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 2011-08-29 11:39 | 2011-08-29 11:39 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | 2011 | Q3 | Q3 - 2011 | 4356 | 4034 | FALSE | 25 | We plan to commence infrastructure construction of phase 1 | 33 | Notification | Public Notification Program & Service Provider Integration: With the commencement of construction, we anticipate a comprehensive public awareness and project notification of all the first phase counties (Lowndes and Dallas) Lowndes County Middle Mile Notification will be 85% completed; Dallas County Middle Mile Notification will be well underway with all anchors and businesses and households. | 100 | N/A | 99 | This task is complete subject to final route design adjustments | 50 | We anticipate getting closer to our baseline in Q4, 2011. Once phase 1 construction begins we can be assured our construction program is streamlined and then put heavy focus on securing future phase Right Of Way (ROW) agreements, permits and etc. | 25 | We plan to have permits for Phase 1 backbone, site surveys complete for anchor institutions and distribution routes in permit phase. | 25 | The impact of the delay of our Finding of No Significant Impact (FONSI) report required us to ramp up construction operations in a short period of time. However, we have not fully caught up with our baseline and anticipate catching up in the next quarter given that construction will start and we will be able to ramp up site preparation at a quicker pace. | 25 | The impact of the delay of our Finding of No Significant Impact (FONSI) report required us to hold back on a significant amount of equipment purchases. We have not fully caught up with our baseline and anticipate catching up in the next quarter since construction will start and we can justify ordering more equipment to stay ahead of the construction materials demand. | 8 | We plan to begin construction on phase 1 backbone | 18 | We plan to begin construction on phase 1 backbone | 15 | With construction beginning, there will be a real time testing of fiber and network terminals installed. | 2011-11-30 16:20 | 2011-11-30 16:20 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | 2011 | Q4 | Q4 - 2011 | 5086 | 4756 | FALSE | 46 | N/A | 37 | Notification | Phase 1 and Phase 2 Notification complete | 100 | N/A | 100 | N/A | 65 | We anticipate having the core local NOC leased | 35 | Based on meetings with ALDOT and Other State Officials we anticipate a significant improvement in the permitting process and timeline | 60 | We should get much closer to baseline in this area as the second A2D construction office is scheduled to be operational in this quarter | 40 | Catching up to baseline will be a direct correlation with construction activities. This area will increase significantly the next quarter as we move into phase 2 backbone and phase one CAI and premise connections. | 35 | We anticipate taking a few quarters to catch up to baseline, however, we plan to mitigate this by commencing more simultaneous construction efforts with more construction crews. | 20 | Related to 2g above. Catching up to baseline will be a direct correlation with construction activities. This area will increase significantly the next quarter as we move into phase 2 backbone and phase one CAI and premise connections. | 20 | Based on the current construction progress we anticipate having the Network lit and several CAI's connected | 2012-02-17 10:44 | 2012-02-17 10:44 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | 2012 | Q1 | Q1 - 2012 | 6354 | 5779 | FALSE | 23 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 42 | Project/Construction Notification | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 100 | N/A | 20 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 57 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 18 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 40 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 19 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 12 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 11 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 18 | Work was delayed due to the suspension of the Project's funding and the stop work order initiated by NTIA and NOAA. Once suspension has been lifted, an accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 2012-05-30 16:56 | 2012-05-30 16:56 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | 2012 | Q2 | Q2 - 2012 | 7232 | 6243 | FALSE | 24 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 42 | Project/Construction Notification | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 100 | N/A | 20 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 57 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 18 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 40 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 19 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 12 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 11 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 18 | Work was cancelled due to the Project's suspension and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 2012-08-23 14:27 | 2012-08-23 14:27 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | 2012 | Q3 | Q3 - 2012 | 7718 | 6546 | FALSE | 24 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 12 |  | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 100 | N/A | 20 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 57 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 18 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 40 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 19 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 12 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 11 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 18 | Work was cancelled due to the Project's suspension/termination and the stop work order initiated by NTIA and NOAA. An accelerated schedule has been developed to ensure the project completes its deliverable by the end of the project period. | 2012-10-31 00:19 | 2012-10-31 00:19 | 5992 | 5992 | Trillion Communications Corp. | TRUE
NT10BIX5570131 | 2010 | Q4 | Q4 - 2010 | 1260 | 2288 | FALSE | 2 | N/A | 26 | land acquisition | N/A | 43 | N/A | 36 | N/A | 0 | N/A | 19 | N/A | 1 | N/A | 50 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 2011-02-21 16:26 | 2011-02-21 16:26 | 6061 | 6061 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2011 | Q1 | Q1 - 2011 | 2300 | 2895 | FALSE | 10 | N/A | 32 | Land Acquisition | Environmental delays | 61 | N/A | 41 | Environmental delays | 0 | N/A | 26 | Environmental delays | 0 | Environmental delays | 34 | Environmental delays | 3 | N/A | 6 | N/A | 4 | N/A | 2011-05-25 13:55 | 2011-05-25 13:55 | 6061 | 6061 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2011 | Q2 | Q2 - 2011 | 3280 | 3402 | FALSE | 12 | No Variance | 4 | Land Acquisition | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 68 | No Variance | 37 | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 0 | No Variance | 25 | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 0 | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 1 | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 2 | No Variance | 2 | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 2 | We have experienced environmental delays and have made route changes which affects many of our milestone categories. Our fiber suppliers have not delivered any fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 2011-08-23 16:01 | 2011-08-23 16:01 | 6061 | 6061 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2011 | Q3 | Q3 - 2011 | 4352 | 4032 | FALSE | 21 | No variance | 0 | Land Acquisition | We have experienced environmental delays and have made route changes which affect many of our milestone categories. Our fiber suppliers have just recently begun delivering fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 100 | No variance | 27 | We have experienced environmental delays and have made route changes which affect many of our milestone categories. Our fiber suppliers have just recently begun delivering fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 0 | No variance | 12 | We have experienced environmental delays and have made route changes which affect many of our milestone categories. Our fiber suppliers have just recently begun delivering fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 5 | We have experienced environmental delays and have made route changes which affect many of our milestone categories. Our fiber suppliers have just recently begun delivering fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 29 | We have experienced environmental delays and have made route changes which affect many of our milestone categories. Our fiber suppliers have just recently begun delivering fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 16 | No variance | 0 | We have experienced environmental delays and have made route changes which affect many of our milestone categories. Our fiber suppliers have just recently begun delivering fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 0 | We have experienced environmental delays and have made route changes which affect many of our milestone categories. Our fiber suppliers have just recently begun delivering fiber, so these expenditures have been delayed and pushed back from their anticipated expense dates, again affecting our milestone categories. | 2011-11-30 15:50 | 2011-11-30 15:50 | 6061 | 6061 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2011 | Q4 | Q4 - 2011 | 5254 | 4919 | FALSE | 27 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | Land Acquisition | To date, we are leasing and using public right-of-way instead of purchasing land so Land Acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 35 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | No variance. | 16 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 10 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 34 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 25 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2012-02-24 15:24 | 2012-02-24 15:24 | 6061 | 6061 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2012 | Q1 | Q1 - 2012 | 6346 | 5775 | FALSE | 33 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so Land Acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 37 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | No variance. | 13 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 17 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 34 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 32 | The baseline prediction was higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2012-05-30 11:03 | 2012-05-30 11:03 | 6062 | 6062 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2012 | Q2 | Q2 - 2012 | 7078 | 6166 | FALSE | 43 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so land acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 51 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | No variance. | 13 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 17 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 43 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 42 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2012-08-15 14:20 | 2012-08-15 14:20 | 6062 | 6062 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2012 | Q3 | Q3 - 2012 | 7828 | 6617 | FALSE | 59 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so land acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 63 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | No variance. | 15 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 18 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 45 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 60 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2012-11-12 13:22 | 2012-11-12 13:22 | 6062 | 6062 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2012 | Q4 | Q4 - 2012 | 9102 | 7873 | FALSE | 70 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so land acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 78 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | No variance. | 15 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 15 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 51 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 73 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2013-02-28 16:33 | 2013-02-28 16:33 | 6062 | 6062 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2013 | Q1 | Q1 - 2013 | 9906 | 8494 | FALSE | 86 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. We anticipate filing for an extension and completing the project by the end of third quarter, 2013. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so land acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 90 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | No variance. | 18 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 20 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 71 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 94 | The baseline prediction is higher than this but this represents a significant improvement over last quarter. Now that we are procuring and installing fiber, we are "catching up" to baseline predictions. The length of time it takes for approval of our Environmental Assessment is keeping us from getting caught up, however. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2013-05-24 16:47 | 2013-05-24 16:47 | 6062 | 6062 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2013 | Q2 | Q2 - 2013 | 10678 | 9000 | FALSE | 100 | No variance. | 0 | Land Acquisition | To date, we are leasing and using public rights-of-way instead of purchasing land so land acquisition has not been as high as we predicted it would be at this stage. | 100 | No variance. | 100 | No variance. | 0 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 0 | Peoples' employees are doing all equipment deployment. No expenses expected in this category. | 0 | Peoples' employees are doing all network testing. No expenses expected in this category. | 2013-08-21 10:51 | 2013-08-21 10:51 | 6062 | 6062 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | 2013 | Q3 | Q3 - 2013 | 12180 | 10365 | FALSE | 100 | No variance. The project exceeded anticipated budget by .5%, however, the budgeted federal portion of the project is still on-budget. The overrun shows to be in the "percent match" category; in other words, we overspent our own funds. | 0 | Land Acquisition | No variance. | 100 | No variance. | 100 | No variance. | 0 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. The network build milestone exceeded anticipated budget by .5%, however, the budgeted federal portion of the project is still on-budget. The overrun shows to be in the "percent match" category; in other words, we overspent our own funds. | 0 | No variance. | 0 | No variance. | 2014-05-12 11:43 | 2014-05-12 11:43 | 6062 | 6062 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570132 | 2010 | Q4 | Q4 - 2010 | 1134 | 2171 | FALSE | 0 | Even though the planned percent complete reflects "0" there is progress being made on the project; this is due to the amount that is planned to be complete by the end of this reporting period being so minute compared to the overall size of the project that it reflects a total percentage completion of less than 1. | 0 | N/A | N/A | 90 | The draft Environmental Assessment was submitted to NTIA for review on 1/15/11. NTIA responded with questions on the draft EA, which ENMR-Plateau and the environmental consultants are currently addressing. In order to meet this milestone in this quarter concurrence from NTIA, SHPO, NMDOT, etc. should be in the final stages of completion. | 85 | For this percentage of the milestone to be met in this quarter approximately 85% of the activities associated with this milestone, which is comprised of the designing of the network, must be completed by the engineering consultants. | 50 | For this percentage of the milestone to be met in this quarter approximately half of the activities associated with this milestone, including contacting the governing parties and negotiating agreements with those parties, must be completed. | 50 | For this percentage of the milestone to be met in this quarter approximately half of the activities associated with this milestone, including obtaining all required permits in NMDOT right of ways, must be completed. ENMR-Plateau will be coordinating with the NMDOT in obtaining these permits. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 0 | No variance. | 2011-02-14 12:55 | 2011-02-14 15:38 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2011 | Q1 | Q1 - 2011 | 1518 | 2472 | FALSE | 16 | No variance. | 0 | N/A | N/A | 100 | No variance. The final Environmental Assessment was submitted to NTIA on 4/8 and we expect the FONSI to be issued by 4/30. | 100 | No variance. Network design is expected to be completed by 6/30. | 100 | No variance. | 75 | No variance. | 0 | No variance. | 0 | Pushed back. Waiting on the FONSI to be completed. Contract negotiations, planning, and invoicing must be completed prior to any funds being expensed. At this time we do not anticipate expensing any funds by 6/30. | 0 | Pushed back. Waiting on FONSI to be completed, RFP's must be finalized and submitted to contractors. | 0 | Pushed back due to equipment procurement schedule. | 0 | No variance. | 2011-04-27 11:34 | 2011-04-27 11:34 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2011 | Q2 | Q2 - 2011 | 3252 | 3388 | FALSE | 4 | Please see section #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 0 | Please see section #3 below. | 4 | Please see section #3 below. | 0 | Please see section #3 below. | 0 | Please see section #3 below. | 0 | Please see section #3 below. | 2011-08-22 10:57 | 2011-08-22 10:57 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2011 | Q3 | Q3 - 2011 | 4190 | 3943 | FALSE | 17 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 80 | Continuing acquisition of rights of way. Expected to be complete by the end of Q2 2012. Rights of way and permits cannot be obtained until construction planning is complete. Since the environmental process took longer than was expected, it resulted in a delay in the construction planning and also the acquisition of the rights of way and permits. Rights of way and permits are requested through government agencies such as the NMDOT. Rights of way and permits are obtained for each location based on the construction schedule so even though all rights of way and permits are not complete at this time there should be no impact to the project schedule. | 60 | Continuing acquisition of rights of way. Expected to be complete by the end of Q2 2012. Rights of way and permits cannot be obtained until construction planning is complete. Since the environmental process took longer than was expected, it resulted in a delay in the construction planning and also the acquisition of the rights of way and permits. Rights of way and permits are requested through government agencies such as the NMDOT. Rights of way and permits are obtained for each location based on the construction schedule so even though all rights of way and permits are not complete at this time there should be no impact to the project schedule. | 52 | No variance. | 14 | Equipment procurement has started in October and is expected to proceed throughout the quarter. | 16 | Outside plant construction started on October 10th and will be progressing throughout the quarter. Based on the efficiency of the contractor and having four construction crews going simultaneously we are expecting to catch up to milestones included in baseline report around the second quarter of next year. | 12 | Equipment installation is expected to begin in Quarter 4. Based on the efficiency of the equipment installers we expect to catch up to milestones included in the baseline report around the second quarter of next year. | 0 | Network testing follows equipment procurement and installation. Once installation has been completed to a point the testing of the network will begin. | 2011-11-21 16:01 | 2011-11-21 16:13 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2011 | Q4 | Q4 - 2011 | 4504 | 4152 | FALSE | 32 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 80 | Continuing acquisition of rights of way. Expected to be complete by the end of Q2 2012. Rights of way and permits cannot be obtained until construction planning was complete. Since the environmental process took longer than was expected, it resulted in a delay in the construction planning and also the acquisition of the rights of way and permits. Rights of way and permits are requested through government agencies such as the NMDOT. Rights of way and permits are obtained for each location based on the construction schedule so even though all rights of way and permits are not complete at this time there should be no impact to the project schedule. | 80 | CO buildings construction will begin Q1 2012 and is anticipated to be complete by the end of Q2 2012. | 37 | Equipment procurement began in Q4 2011 and is expected to ramp up in Q1 and Q2 of 2012. The majority of the equipment will be procured by July 31st 2012. | 27 | Outside plant construction started on October 10th and will be progressing throughout the next quarter. Based on the efficiency of the contractor and have multiple construction crews going simultaneously we are anticipating to catch up to milestones included in the baseline report in subsequent quarters. | 25 | Equipment installation began in Q4 2011. Based on the efficiency of the equipment installers we anticipating to catch up to milestones included in the baseline report in subsequent quarters. | 25 | Network testing follows network build and equipment deployment. | 2012-01-27 11:24 | 2012-01-27 11:24 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2012 | Q1 | Q1 - 2012 | 5980 | 5589 | FALSE | 56 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 87 | Positive variance. | 83 | The majority of the equipment is expected to be procured by July 31st 2012. We anticipate catching up to milestones included in the baseline report in subsequent quarters. | 48 | Outside plant construction began on October 10th and is progressing quickly. Based on the efficiency of the contractor and the fact that there are currently 12 separate construction crews working on this project simultaneously we are anticipating to catch up to milestones included in the baseline report in subsequent quarters. | 50 | Equipment installation began in Q4 2011. Based on the efficiency of the equipment installers we anticipate catching up to milestones included in the baseline report in subsequent quarters. | 50 | Network testing follows network build and equipment deployment. | 2012-05-08 17:31 | 2012-05-08 17:31 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2012 | Q2 | Q2 - 2012 | 6940 | 6097 | FALSE | 74 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 67 | We anticipate catching up to milestones included in the baseline report in subsequent quarters. | 74 | Outside plant construction began on October 10th and is progressing quickly. Based on the efficiency of the contractor and the fact that there are currently 12 separate construction crews working on this project simultaneously we are anticipating to catch up to milestones included in the baseline report in subsequent quarters. | 65 | Equipment installation began in Q4 2011. Based on the efficiency of the equipment installers we anticipate catching up to milestones included in the baseline report in subsequent quarters. | 65 | Network testing follows network build and equipment deployment. | 2012-08-08 18:07 | 2012-08-08 18:07 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2012 | Q3 | Q3 - 2012 | 7566 | 6441 | FALSE | 82 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 89 | We anticipate catching up to milestones included in the baseline report in subsequent quarters. | 79 | Outside plant construction began on October 10, 2011 and is progressing quickly. We anticipate catching up to milestones included in the baseline report in subsequent quarters. | 89 | Equipment installation began in Q4 2011. Based on the efficiency of the equipment installers we anticipate catching up to milestones included in the baseline report in subsequent quarters. | 70 | Network testing follows network build and equipment deployment. | 2012-10-30 11:57 | 2012-10-30 11:57 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2012 | Q4 | Q4 - 2012 | 9004 | 7779 | FALSE | 90 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 95 | ENMR anticipates completing equipment procurement by the award period end date. | 87 | ENMR anticipates completing the network build by the award period end date. | 95 | ENMR anticipates completing equipment deployment by the award period end date. | 95 | ENMR anticipates completing network testing by the award period end date. | 2013-02-27 11:03 | 2013-02-27 11:03 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2013 | Q1 | Q1 - 2013 | 9968 | 8528 | FALSE | 95 | See explanation in part #3 below. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 95 | ENMR anticipates completing the network build by the award period end date. | 100 | No variance. | 100 | No variance. | 2013-05-29 14:51 | 2013-05-29 14:51 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2013 | Q2 | Q2 - 2013 | 10756 | 9043 | FALSE | 100 | No variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 2013-08-27 10:45 | 2013-08-27 10:45 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | 2013 | Q3 | Q3 - 2013 | 11284 | 9438 | FALSE | 100 | No variance. | 0 | N/A | N/A | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 2013-11-19 10:36 | 2013-11-19 10:36 | 5498 | 5498 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570133 | 2010 | Q3 | Q3 - 2010 | 340 | 1436 | FALSE | 13 | Zero variance | 72 | Grant Administration | Zero variance | 100 | Zero variance | 100 | Zero variance | 30 | Zero variance | 25 | Zero variance | 18 | Zero variance | 14 | Zero variance | 8 | Zero variance | 10 | Zero variance | 9 | Zero variance | 2010-11-17 13:07 | 2010-11-17 13:07 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2010 | Q4 | Q4 - 2010 | 1036 | 2076 | FALSE | 8 | Zero variance | 19 | Grant Administration | Zero variance | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | Zero variance | 36 | Zero variance | 35 | Zero variance | 1 | Zero variance | 10 | Zero variance | 6 | Zero variance | 0 | Zero variance | 0 | Zero variance | 2011-02-10 10:13 | 2011-02-10 10:13 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2011 | Q1 | Q1 - 2011 | 2124 | 2807 | FALSE | 15 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 27 | Grant Administration | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 51 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 48 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 4 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 21 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 12 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 11 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 8 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we expect to begin construction and to be able to catch up to our budgeted level of expenditures during the second quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 2011-05-18 11:22 | 2011-05-18 11:22 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2011 | Q2 | Q2 - 2011 | 3172 | 3346 | FALSE | 22 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 35 | Grant Administration | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 17 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 24 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 19 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 17 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 10 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 2011-08-17 18:39 | 2011-08-17 18:39 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2011 | Q3 | Q3 - 2011 | 4284 | 3992 | FALSE | 30 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 43 | Grant Administration | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 0 | The original grant for the project was awarded in December, 2009. As a result of the entity change process, a new grant was assigned in September 2010 which necessitated a revised budget for the remaining amount of the grant expenditures. As required by the original grant Special Award Conditions, the Environmental Assessment (EA) work was budgeted as part of the original grant expenditures. Since the milestones are measured against dollars expended vs. budgeted, and all EA budgeted dollars were expended under the original grant, zero percent is reported here. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 33 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 26 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 28 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 20 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 20 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the fourth quarter of 2011. Non-Federal matching funds will be fully available during the next quarter. | 2011-11-28 10:31 | 2011-11-28 10:31 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2011 | Q4 | Q4 - 2011 | 5306 | 4976 | FALSE | 39 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 52 | Grant Administration | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 0 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 49 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 35 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 35 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 28 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 28 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the first quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 2012-02-27 15:55 | 2012-02-28 17:22 | 6712 | 6712 | ION Newco Corp | TRUE
NT10BIX5570133 | 2012 | Q1 | Q1 - 2012 | 5988 | 5593 | FALSE | 54 | Baseline = 61%; Variance between actual percent complete for overall project compared to baseline is not significant. As shown below, for some categories we are under budget, for some over budget. Non-Federal matching funds will be fully available during the next quarter. | 60 | Grant Administration | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the second quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 0 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the second quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. An under-budgeting of this item is indicated, and a revision to our budget is pending. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. An over-budgeting of this item is indicated, and a revision to our budget is pending. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the second quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 64 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the second quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 83 | Baseline = 47%; Ahead of budget anticipated due to faster than anticipated delivery of equipment. Non-Federal matching funds will be fully available during the next quarter. | 50 | Baseline = 62%; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the second quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 36 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the second quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 36 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the second quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 2012-05-09 15:13 | 2012-05-09 15:13 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2012 | Q2 | Q2 - 2012 | 7192 | 6223 | FALSE | 65 | Baseline = 79%; Variance between actual percent complete for overall project compared to baseline is not significant. As shown below, for some categories we are under budget, for some over budget. Non-Federal matching funds will be fully available during the next quarter. | 68 | Grant Administration | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 0 | Zero variance; Environmental Assessment activity was performed during the Grant in effect prior to the Entity Change. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. An under-budgeting of this item is indicated, and a revision to our budget is pending. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. An over-budgeting of this item is indicated, and a revision to our budget is pending. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 80 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 88 | Baseline = 61%; Ahead of budget anticipated due to faster than anticipated delivery of equipment. Non-Federal matching funds will be fully available during the next quarter. | 63 | Baseline = 82%; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 63 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 63 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the third quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 2012-08-21 15:00 | 2012-08-21 15:00 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2012 | Q3 | Q3 - 2012 | 7840 | 6624 | FALSE | 74 | Baseline = 88%; Variance between actual percent complete for overall project compared to baseline is not significant. As shown below, for some categories we are under budget, for some over budget. Non-Federal matching funds will be fully available during the next quarter. | 84 | Grant Administration | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the forth quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 0 | Zero variance; Environmental Assessment activity was performed during the Grant in effect prior to the Entity Change. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. An under-budgeting of this item is indicated, and a revision to our budget is pending. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. An over-budgeting of this item is indicated, and a revision to our budget is pending. Non-Federal matching funds will be fully available during the next quarter. | 100 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the forth quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 82 | Baseline = 80%; Variance is immaterial. Non-Federal matching funds will be fully available during the next quarter. | 86 | Baseline = 80%; Ahead of budget anticipated due to faster than anticipated delivery of equipment. Non-Federal matching funds will be fully available during the next quarter. | 70 | Baseline = 90%; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the forth quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 86 | Baseline = 81%; Ahead of budget anticipated due to faster than anticipated delivery of equipment. Non-Federal matching funds will be fully available during the next quarter. | 81 | Zero variance; Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010 and early 2011. As a result, we have not been able to expend all of the funds as budgeted. Now that we have our FONSI, we have begun construction and expect to be able to catch up to our budgeted level of expenditures during the forth quarter of 2012. Non-Federal matching funds will be fully available during the next quarter. | 2012-11-13 10:01 | 2012-11-13 10:01 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2012 | Q4 | Q4 - 2012 | 8768 | 7563 | FALSE | 82 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 85 | Grant Administration | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 0 | Zero variance; Environmental Assessment activity was performed during the Grant in effect prior to the Entity Change. | 94 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 96 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 92 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 76 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 0 | Variance to original Baseline is not relevant due to the approval during the forth quarter of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 2013-02-14 09:07 | 2013-02-14 09:07 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2013 | Q1 | Q1 - 2013 | 9614 | 8338 | FALSE | 94 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 96 | Grant Administration | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 0 | Zero variance; Environmental Assessment activity was performed during the Grant in effect prior to the Entity Change. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 99 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 92 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 0 | Network Testing costs included in Equipment Deployment. | 2013-05-06 16:06 | 2013-05-06 16:06 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2013 | Q2 | Q2 - 2013 | 10582 | 8948 | FALSE | 99 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 89 | Grant Administration | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 0 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 0 | Network Testing costs included in Equipment Deployment. | 2013-08-14 14:11 | 2013-08-14 14:11 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570133 | 2013 | Q3 | Q3 - 2013 | 11894 | 10063 | FALSE | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Grant Administration | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 100 | Variance to original Baseline is not relevant due to the approval during the forth quarter 2012 of a revised budget. Non-Federal matching funds will be fully available during the next quarter. | 2014-02-26 10:39 | 2014-02-26 10:39 | 6083 | 6083 | ION Newco Corp | TRUE
NT10BIX5570135 | 2010 | Q4 | Q4 - 2010 | 1082 | 2118 | FALSE | 7 | N/A | 19 | Administration | N/A | 100 | N/A | 3 | N/A | 3 | N/A | 3 | N/A | 17 | N/A | 12 | N/A | 3 | N/A | 0 | N/A | 0 | N/A | 2011-02-11 14:08 | 2011-02-11 14:08 | 6377 | 6377 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2011 | Q1 | Q1 - 2011 | 1640 | 2541 | FALSE | 15 | N/A | 28 | Administration | N/A | 100 | N/A | 18 | N/A | 18 | N/A | 18 | N/A | 67 | N/A | 16 | N/A | 9 | N/A | 12 | N/A | 12 | N/A | 2011-04-29 11:04 | 2011-04-29 11:04 | 6377 | 6377 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2011 | Q2 | Q2 - 2011 | 3320 | 3422 | FALSE | 18 | Planned is 27%. The FONSI came in a month later then expected which delayed our efforts. | 28 | Administration | We anticipate to recover from the attritions that has occured, we are confident that we will be in line to meeting our projected milestone during the coming quarters. | 100 | Milestone is at a 100% (Completed) | 34 | Preliminary logical diagraming is currently at 90% completion and plant design is currently at 45%. We anticipate that we will meet our milestone projection and exceed projections during the last quarters in 2012. | 20 | We anticipate starting in 9 other counties to come on line early next quarter i.e. Charles, Calvert, Cecil, Kent, Queen Annes, Annarundel, Prince Georges, Montgomary, Annapolis & Hartford counties. Also we anticipate railroad ROW to be approved. | 25 | We anticipate obtaining our construction permits within the 9 counties that are to come online early next quarter. We anticipate achieving our baseline milestone during the next reporting quarters. | 0 | Site visits have been completed for all hut sites, this includes location and path identification. Site preparation will commence in Q4 2011. | 44 | Total equipment procurement is valued at $3.4M of which $1.6M have been procured. | 22 | We anticipate to meet our baseline projections. | 0 | We don't anticipate that equipment deployment will occur until Q4. | 0 | We don't anticipate that the Network Testing will occur until Q4. | 2011-08-26 08:17 | 2011-08-26 08:17 | 6377 | 6377 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2011 | Q3 | Q3 - 2011 | 4006 | 3842 | FALSE | 20 | We anticipate our planned percentage to increase as the construction phase is ramping up. | 34 | Administration | We are confident that we will meet our projected milestone during the coming quarters. | 100 | Milestone is at a 100% (Completed) | 26 | Preliminary logical diagraming is currently at 90% completion and plant design is currently at 50%. We anticipate that we will meet our milestone projection and exceed projections during the last quarters in 2012. | 26 | We anticipate starting in 8 other counties early next quarter. Also, we anticipate railroad ROW permits to be approved during the coming reporting quarters. | 26 | We anticipate obtaining our construction permits within the 8 counties that are to come online early next quarter. We anticipate achieving our baseline milestone during 2012. | 0 | Site visits have been completed for all sites, this includes location and path identification, Huts would have been purchased and installation commence within the next reporting quarters. | 23 | Current total equipment procured is valued at $5.7M. We anticipate to come in line with our plan percentage with additional equipment procurement scheduled for the next reporting quarters. | 16 | The Network Build component will increase exponentially as construction continues to ramp up. | 6 | Network architecture designs are ongoing. We anticipate continued equipment deployment during upcoming quarters. | 6 | Network architecture designs are ongoing. We anticipate continued network testing during upcoming quarters. | 2011-11-14 09:54 | 2011-11-14 09:54 | 6377 | 6377 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2011 | Q4 | Q4 - 2011 | 5278 | 4946 | FALSE | 28 | We anticipate our planned percentage to increase as the construction phase is ramping up. | 40 | Administration | As construction gains momentum during the next reporting quarters, we anticipate that we will obtain our project goals. | 100 | Milestone is at a 100% (Completed) | 32 | Preliminary logical diagraming is currently being completed. We anticipate that we will meet our milestone projection and exceed projections reported during this reporting quarter. | 32 | We anticipate receiving ROW permits in all counties in the next reporting quarter. | 32 | We anticipate obtaining our construction permits within the 7 counties that are to come online early next quarter. | 6 | The installation schedule will have us ahead of schedule in Q3. Hut orders were completed in December 2012 with the first delivery in Q1 and subsequent deliveries in Q2 & final delivery and installation in Q3. | 22 | Current total equipment procured is valued at $7.1M. We anticipate to come in line with our planned goal during the next reporting quarters. | 12 | Network build component will increase exponentially as construction continues to ramp up. | 13 | Network architecture designs are ongoing, equipment deployment will maintain pace equipment procurement and network build. | 5 | We anticipate network testing during the upcoming quarters as the completion of the network architecture is occurs. | 2012-02-27 10:12 | 2012-02-27 10:12 | 6377 | 6377 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2012 | Q1 | Q1 - 2012 | 6300 | 5752 | FALSE | 48 | We anticipate our planned percentage to rapidly increase as the construction phase continues ramping up. | 42 | Administration | As construction gains momentum during the next reporting quarters, we anticipate that we will obtain our project goals. | 100 | Milestone is at a 100% (Completed) | 48 | Preliminary logical diagraming is currently being completed. Detailed splice engineering begins. Plant infrastructure design will be completed. | 58 | We anticipate receiving ROW permits as needed in all counties in the next reporting quarter. | 58 | We anticipate receiving pole attachment licenses from multiple utilities as well as encroachment agreements from multiple Railroads. | 20 | Hut orders were completed in December 2012 with the first delivery in Q1 and subsequent deliveries in Q2 & final delivery and installation in Q3. | 40 | $7M of equipment procurements are currently in process. | 51 | The network build component will increase exponentially as construction continues to ramp up. | 15 | Network architecture designs are ongoing. Equipment deployment will maintain pace with equipment procurement and network build. | 10 | Network testing will lag other metrics due to the need to have contiguous fiber paths and CAI/POP connections, which will not occur until later in the project. | 2012-05-25 11:48 | 2012-05-25 11:48 | 6374 | 6374 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2012 | Q2 | Q2 - 2012 | 7164 | 6209 | FALSE | 69 | We anticipate our planned percentage to rapidly increase since the construction phase is well on its way. | 47 | Administration | As construction continues to gains momentum during the next reporting quarters, we anticipate that we will obtain our project goals. | 100 | Milestone is at a 100% (Completed) | 79 | Preliminary logical diagraming is currently being completed. Detailed splice engineering has begun. Plant infrastructure design to be completed. | 80 | We continue to receive ROW permits as needed in all counties and anticipate continued receipt in the next reporting quarter. | 80 | We anticipate continued receipt of pole attachment licenses from all utility companies as well as encroachment agreements from the various Railroad company. | 55 | The initial 4 Huts received have been installed during Q1. We anticipate the subsequent deliveries and installation during the Q3 and Q4 period., with final installation of all Huts completed in Q1 2013. | 51 | Our projection indicates that we would have procured over $14M of equipment during the next reporting quarter. | 78 | The network build component will increase exponentially as construction continues to ramp up. | 14 | Network architecture designs are ongoing. Equipment deployment will maintain pace with the network design and build. | 14 | Network testing will lag other metrics due to the need to have contiguous fiber paths and CAI/POP connections, which will not occur until later in the project. | 2012-08-20 13:01 | 2012-08-20 13:01 | 6374 | 6374 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2012 | Q3 | Q3 - 2012 | 7970 | 6691 | FALSE | 77 | We anticipate our planned percentage to rapidly increase since the construction phase is well on its way. | 50 | Administration | We continue to find efficiencies in our program management allowing us to contain overhead cost. | 100 | Milestone is at a 100% (Completed) | 80 | Preliminary logical diagraming is currently being completed. Detailed splice engineering has begun. Plant infrastructure design to be completed. | 95 | We continue to receive ROW permits as needed in all counties and anticipate continued receipt in the next reporting quarter. | 95 | We anticipate continued receipt of pole attachment licenses from all utility companies as well as encroachment agreements from the various Railroad company. | 65 | 8 Huts have been received and installed. We anticipate the subsequent deliveries and installation during Q4 period with final installation of all Huts completed in Q1 2013. | 37 | Our projection indicates that we would have procured over $10M of equipment during the next reporting quarter. | 73 | The network build component will increase steadily as construction continues current high rates of production. | 28 | Network architecture designs are ongoing. Equipment deployment will maintain pace with the network design and build. | 26 | Network testing will lag other metrics due to the need to have contiguous fiber paths and CAI/POP connections, which will not occur until later in the project. | 2012-11-20 10:51 | 2012-11-20 10:51 | 6374 | 6374 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2012 | Q4 | Q4 - 2012 | 9144 | 7958 | FALSE | 84 | Planned is 79% | 55 | Administration | We continue to find efficiencies in our program management allowing us to contain overhead cost. | 100 | Milestone is at a 100% (Completed) | 86 | Planned is 95%, logical network design is taking longer than anticipated since we must coordinate with 23 different networks. | 95 | Planned is 95% | 95 | Planned is 95% | 85 | Planned is 87% Three Huts that were scheduled for 4Q 2012 are now to be installed during Q1 2013. In all three cases, easement delays caused the Hut installation schedule to slip into the first quarter. | 52 | Our projection indicates that we would have procured over $8M of equipment during the next reporting quarter. | 73 | Planned is 74%, The network build component will increase steadily as construction continues current high rates of production. | 52 | Planned is 70%, Network architecture designs are ongoing. Equipment deployment will maintain pace with the network design and build. | 37 | Planned is 70%Network testing will lag other metrics due to the need to have contiguous fiber paths and CAI/POP connections, which will not occur until later in the project. | 2013-03-22 13:49 | 2013-03-22 13:49 | 6374 | 6374 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2013 | Q1 | Q1 - 2013 | 9974 | 8531 | FALSE | 94 | Currently on schedule to completing the project on time. | 57 | Administration | We continue to find efficiencies in our program management allowing us to contain overhead cost. | 100 | Milestone is at a 100% (Completed) | 94 | Currently on schedule to completing the Network Design during the remaining months of the project. | 98 | On schedule to obtain all required Rights of Way by the end of Q2. | 98 | On schedule to obtain all required Rights of Way by the end of Q2. | 94 | Hut number 13 will be installed during 2Q 2013. Hut number 14 is awaiting easements from the State. The Hut is currently scheduled to be installed in late 2Q or early 3Q 2013. | 88 | Our projection indicates that we would have cumulatively procured over $16M of equipment during our next reporting quarter. | 94 | Network build will continue to maintain its current build out pace throughout the remaining months of the project. | 56 | Network architecture designs are ongoing. Equipment deployment will maintain pace with the network design and build. | 92 | Network Testing is currently on schedule to be completed during the remaining months of the project. | 2013-05-29 16:10 | 2013-05-29 16:10 | 6374 | 6374 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2013 | Q2 | Q2 - 2013 | 10702 | 9013 | FALSE | 100 | Small amount funds will remain for the 90 day closeout period. | 99 | Administration | Small amount funds will remain for the 90 day closeout period. | 100 | Milestone Completed. | 100 | Milestone Completed. | 100 | Milestone Completed. | 100 | Milestone Completed. | 100 | Milestone Completed. | 100 | Milestone Completed. | 100 | Milestone Completed. | 100 | Milestone Completed. | 100 | Milestone Completed. | 2013-08-22 17:36 | 2013-08-22 17:36 | 6374 | 6374 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | 2013 | Q3 | Q3 - 2013 | 11628 | 9748 | FALSE | 100 | Milestone Completed | 100 | Administration | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 100 | Milestone Completed | 2014-01-20 14:05 | 2014-01-20 14:05 | 6374 | 6374 | Information Technology, Maryland Department of | TRUE
NT10BIX5570136 | 2010 | Q4 | Q4 - 2010 | 1122 | 2161 | FALSE | 9 | EA completed; mitigations will be necessary after FONSI is issued that may have an impact on progress of project. | 5 | IRU Leases | Legal review delay, and approval time for local board/council at next meetings. | 90 | Draft EA will be submitted prior to SAC deadline of March 1, 2011. | 70 | Early snow caused some outlying node location access issues; on hold to Spring. Several route changes for loss of BLM Backbone site being evaluated. | 30 | Applications filed; waiting for approvals | 0 | Permitting process will be pursued at locations ready to be built upon issuance of 'FONSI', anticipated in April 2011 | 0 | 0 | 6 | Begin purchase of some items in 6-month Environmental Budget | 0 | 0 | 0 | 0 | 0 | 0 | 2011-02-12 11:32 | 2011-02-12 11:32 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2011 | Q1 | Q1 - 2011 | 1498 | 2462 | FALSE | 27 | No variance from baseline plan. | 32 | (in-kind IRU Leases) | No variance from baseline plan. We expect continued progress toward obtaining 316 in-kind IRU leases. | 100 | No variance from baseline plan. | 80 | Slightly behind baseline projections. Completion of network designs in dependent upon the acquisition of all necessary permits and approvals. | 35 | Slightly behind baseline projections based on processing time from gov't entities. | 9 | Slightly behind baseline projections due to delay in approval of Environmental Assessment. | 12 | No variance from baseline plan. We expect to begin construction of the backbone in June 2011. | 25 | No variance from baseline plan; 7-10 RFPs will be released next quarter. | 9 | No variance from baseline plan. | 9 | No variance from baseline plan. | 0 | Slightly behind baseline projections due to delay in approval of Environmental Assessment and subsequent delayed construction start | 2011-04-26 19:21 | 2011-04-26 19:21 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2011 | Q2 | Q2 - 2011 | 3292 | 3408 | FALSE | 15 | Behind baseline projections due to delay in FONSI and inability to construct. | 31 | 203 leases | Slightly behind of baseline plan. We expect continued progress toward obtaining 203 in-kind leases. | 100 | We expect to be slightly over budget on this milestone. | 63 | Slightly behind baseline projections based on actual expenditures for this category. Completion of network node design is dependent upon final FCC licensing, which is on hold until construction is imminent. | 31 | Slightly behind expenditures, but ROWs continue to be secured. | 2 | Slightly behind due to correlation with construction timing. | 1 | Behind baseline projections due to delay in approval of Environmental Assessment. | 2 | Behind baseline projections due to delay in Environmental Assessment. | 25 | Ahead of baseline expenditures as major pieces of the network are being secured. | 1 | Behind baseline projections due to delay in approval of Environmental Assessment and subsequent delayed construction start. | 1 | Behind baseline plan due to no construction, although some network testing has occurred as part of the equipment procurement process. | 2011-08-24 12:10 | 2011-08-24 12:10 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2011 | Q3 | Q3 - 2011 | 3898 | 3787 | FALSE | 36 | Behind baseline projections due to delay in FONSI and late construction start. GovNET expects to be back in sync with its Baseline Plan by the end of Y2 Q4 | 60 | 203 leases | On track with baseline plan. | 100 | Expect receipt of FONSI determination. No deviation from baseline plan. | 62 | Behind baseline projections due to delay in FONSI and late construction start. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 74 | Slightly behind baseline projections due to delay in FONSI and late construction start. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 3 | Behind baseline projections due to delay in FONSI and late construction start. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 3 | Behind baseline projections due to delay in FONSI and late construction start. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 10 | Behind baseline projections due to delay in FONSI and late construction start. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 30 | Behind baseline projections due to delay in FONSI and late construction start. Locations will be secured and construction will begin next quarter. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 3 | Behind baseline projections due to delay in FONSI and late construction start. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 8 | Behind baseline projections due to delay in FONSI and late construction start. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 2011-11-04 15:52 | 2011-11-04 15:52 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2011 | Q4 | Q4 - 2011 | 4904 | 4590 | FALSE | 45 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 66 | 203 in-kind IRU leases | No variance from Baseline Plan. | 73 | GovNET completed its EA and received its FONSI during this reporting period. Additional funding remains in this category to cover any future EA amendments. | 73 | Behind baseline plan due to delay in EA approval, which restricted construction.GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 66 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 7 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 7 | GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012.Behind baseline plan due to delay in EA approval, which restricted construction. | 33 | Behind baseline plan due to delay in EA approval, which restricted construction.GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 52 | On track with Baseline Plan. We have secured a significant number of leases and will be purchasing a significant amount of equipment next quarter. We expect to be back in sync with its Baseline Plan by the end of Q3 2012. | 7 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 25 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 2012-02-07 13:06 | 2012-02-07 13:06 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2012 | Q1 | Q1 - 2012 | 6046 | 5622 | FALSE | 48 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 62 | 203 in-kind IRU leases | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET expects to make continued progress toward obtaining 203 in-kind leases in the next quarter. | 89 | GovNET completed its EA and received its FONSI in Q4 2011. Additional funding remains in this category to cover any future EA amendments. | 85 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 62 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 19 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 19 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 40 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 53 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 19 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 32 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be back in sync with its Baseline Plan by the end of Q3 2012. | 2012-05-11 16:30 | 2012-05-11 16:30 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2012 | Q2 | Q2 - 2012 | 7262 | 6258 | FALSE | 44 | Project restart anticipated with outstanding unpaid reimbursements received, putting the project % complete numbers more in line since they are based on dollars expended. Multiple crews will be utilized statewide for construction & installations. | 95 | 203 in-kind IRU leases | Ahead of baseline plan projections with expected approval to add CAIs who already signed leases into project. | 95 | GovNET achieved this milestone & received a FONSI in Q4 2011. Additional funding remains in this category to cover future EA amendments and/or compliance administrative costs. | 85 | Slightly behind baseline plan projections due to review of the project by NTIA in Summer 2012. FCC licenses are held in Prior Coordination Notice (PCN) and are filed as site construction is imminent. | 72 | Slightly behind baseline plan projections due to delay in EA approval, which restricted construction, and a review of the project by NTIA in Summer 2012. | 34 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a review of the project by NTIA in Summer 2012. Any construction permits required are filed just prior to imminent work due to limited time frame valid. | 56 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a review of the project by NTIA in Summer 2012. | 40 | Slightly behind baseline plan projections due to delay in EA approval, which restricted construction, and a review of the project by NTIA in Summer 2012. | 37 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a review of the project by NTIA in Summer 2012. | 20 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a review of the project by NTIA in Summer 2012. | 27 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a review of the project by NTIA in Summer 2012. | 2012-08-28 14:53 | 2012-08-28 14:53 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2012 | Q3 | Q3 - 2012 | 8016 | 6714 | FALSE | 47 | Project restart anticipated with outstanding unpaid reimbursements received, putting the project % complete numbers more in line since they are based on dollars expended. Multiple crews will be utilized statewide for expedited construction & installations. | 95 |  | Ahead of baseline plan projections with expected approval to add CAIs who already signed leases into project. | 95 | GovNET achieved this milestone & received a FONSI in Q4 2011. Additional funding remains in this category to cover future EA amendments and/or compliance administrative costs. | 88 | Slightly behind baseline plan projections due to project suspension by NTIA. FCC licenses are held in Prior Coordination Notice (PCN) and are filed as site construction is imminent. | 72 | Slightly behind baseline plan projections due to delay in EA approval, which restricted construction, and a project hold by NTIA. | 34 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a project suspension by NTIA. Any construction permits required are filed just prior to imminent work due to limited time frame valid. | 56 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a project suspension by NTIA. | 40 | Slightly behind baseline plan projections due to delay in EA approval, which restricted construction, and a project suspension by NTIA. | 37 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a project suspension by NTIA. | 20 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a project suspension by NTIA. | 27 | Behind baseline plan projections due to delay in EA approval, which restricted construction, and a project suspension by NTIA. | 2012-11-21 11:14 | 2012-11-21 11:14 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2012 | Q4 | Q4 - 2012 | 8822 | 7609 | FALSE | 49 | Increase in project spending in March if suspension is lifted in February. | 90 | In-Kind Leases | Anticipated approval by NTIA for 'exempt' sites to be added to project. | 90 | Increase in environmental/cultural work if suspension is lifted. | 82 | FCC licenses will be held until site construction is imminent. | 64 | No change due to necessary lead time to re-engage. | 30 | Increase in advance activity. | 40 | No change | 42 | Increase due to outstanding vendor payments | 28 | Increase due to restarting of construction activity | 15 | Increase due to restarting of construction activity | 17 | No change | 2013-02-15 16:31 | 2013-02-15 16:31 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2013 | Q1 | Q1 - 2013 | 9784 | 8426 | FALSE | 49 | Projected increase in funds reimbursed for outstanding vendors. | 90 | In-Kind leases | Anticipated approval by NTIA for 'exempt' sites to be added to project. | 90 | Increase in environmental/cultural work if suspension is lifted. | 82 | FCC licenses will be held until site construction is imminent. | 64 | No change due to necessary lead time to re-engage. | 30 | Increase in advance activity. | 40 | No change. | 42 | Increase due to outstanding vendor invoice payments. | 28 | Increase due to restarting of project activity. | 15 | Increase due to restarting of project activity. | 17 | No change. | 2013-05-16 19:49 | 2013-05-16 19:49 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2013 | Q2 | Q2 - 2013 | 10706 | 9015 | FALSE | 50 | Projected increase in funds reimbursed for outstanding vendors and forward progress on the network build. | 90 |  | Anticipated approval by NTIA for 'exempt' sites to be added to project. | 90 | Increase in environmental/cultural work to progress project. | 82 | FCC licenses will be held until site construction is imminent. | 68 | Increase in advance activity. | 30 | Increase in advance activity. | 42 | Slight increase as construction activity restarts. | 48 | Increase due to outstanding vendor invoice payments and new purchases. | 28 | Increase due to restarting of project activity. | 15 | Increase due to restarting of project activity. | 17 | No change. | 2013-08-22 19:18 | 2013-08-22 19:18 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2013 | Q3 | Q3 - 2013 | 11268 | 9425 | FALSE | 58 | Project increase in funds reimbursed for outstanding vendors and forward progress on the network build. | 65 |  | Additional CAI leases signed and returned. | 90 | Increase in environmental/ cultural work to progress project. | 82 | FCC Licenses will be held until site construction is imminent | 70 | Increase in advance activity | 30 | Increase in advance activity | 42 | Slight Increase as construction activity restarts | 48 | Slight Increase as construction activity restarts; invoicing will be following quarter | 28 | Increase due to restarting of project activity | 18 | Increase due to restarting of project activity | 17 | No Change | 2013-11-15 13:22 | 2013-11-15 13:22 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570136 | 2013 | Q4 | Q4 - 2013 | 11818 | 9995 | FALSE | 63 | Project increase in funds being spent and reimbursed for equipment and construction items committed for the network build. | 65 |  | Additional CAI & in-kind leases signed and returned | 93 | Increase in environmental/ cultural work to progress project as required. | 82 | FCC Licenses in advance activity | 70 | Increase in activity and signed documents | 30 | Increase in activity | 48 | Increase as construction activity restarts | 52 | Increase as construction activity restarts; sizable invoicing and reimbursement request will be following quarter | 30 | Increase due to restarting of project activity | 18 | Increase due to restarting of project activity | 19 | Increase due to restarting of project activity | 2014-02-13 23:16 | 2014-02-13 23:16 | 6337 | 6337 | GOVNET, INC. | TRUE
NT10BIX5570138 | 2010 | Q4 | Q4 - 2010 | 708 | 1744 | FALSE | 2 | No variance from baseline | 50 | (Power Pole Make Ready) (HC) | No variance from baseline | 75 | No variance from baseline | 70 | No variance from baseline | 20 | No variance from baseline | 10 | No variance from baseline | 0 | No variance from baseline | 0 | No variance from baseline | 0 | Construction has not begun as FONSI has not yet been recieved | 0 | No variance from baseline | 0 | No variance from baseline | 2011-01-28 11:57 | 2011-01-28 11:57 | 6339 | 6339 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2011 | Q1 | Q1 - 2011 | 1848 | 2667 | FALSE | 7 | No variance from baseline | 100 |  | Power pole make ready HCTC. | 100 | No variance from baseline | 90 | No variance from baseline | 100 | No variance from baseline | 50 | No variance from baseline | 12 | No variance from baseline | 6 | No variance from baseline | 22 | No variance from baseline | 4 | No variance from baseline | 5 | No variance from baseline | 2011-05-02 14:35 | 2011-05-02 14:35 | 6339 | 6339 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2011 | Q2 | Q2 - 2011 | 3074 | 3294 | FALSE | 15 | -15% Variance due to construction delay. This variance should be eliminated in Q4 of 2011 (Q2 of BTOP Project Year 2). Region 18 is tracking project completion based upon actual work completed not on $ spent. The additional dollars forecast are reflective of two items. 1. An up front payment of $1,000,000 to Dell City Telephone for the purpose of purchasing equipment. 2. The annual up front payment on the contract for Project Management. The amount of this payment will be $220,000. These two items total $1,220,000 which bridges the gap between the projection of 15% of work completed and the projected spending of 22.05%. | 50 | Power Pole Make-Ready | Delay due to FONSI not issued. Expect to move forward this quarter and complete in Q4 of 2011 | 100 | No Variance | 100 | No Variance | 100 | No Variance | 30 | - 45% As stated above, construction permits are valid for 60 days. We expect that 30% will have been requested and approved by the end of the next quarter. | 15 | -55% Site prep will be in line with overall project completion. Some variation due to later start of construction. Also, baseline estimate of 70% completion at this stage not in line with construction time frame of overall project. | 75 | +59% We will be ahead of baseline projection and in line with overall current project projections. Baseline estimate was not in line with construction time frame of overall project. | 5 | -30% Network build will be in line with overall project completion. Some variation due to later start of construction. Also, baseline estimate of 35% was high expectation for this stage of the project. | 6 | No Variance | 0 | -6% Do not expect to have enough CAI's connected to perform network testing prior to end of next quarter. Expect to be back on track by the end of Q4 2011 | 2011-08-15 10:27 | 2011-08-15 10:27 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2011 | Q3 | Q3 - 2011 | 4046 | 3863 | FALSE | 30 | -10% variance to baseline. Delay in start of construction. This gap should be closed by the end of the following reporting quarter (Q1 2012). | 100 | Power Pole make ready (HCTC) | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 50 | -40% variance to baseline. Due to the fact that permits are valid for 60 days and must be acquired closer to the start of each construction route. | 80 | No variance | 80 | No variance | 7 | -38% variance to baseline, due to delay in construction start. Will be closing gap rapidly as construction begins. | 35 | No variance | 7 | -57% variance again due to delay of construction start | 2011-11-15 10:45 | 2011-11-15 10:45 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2011 | Q4 | Q4 - 2011 | 5242 | 4903 | FALSE | 48 | -7% variance to baseline. As noted we anticipate making great progress during this quarter. | 100 | HCTC pole make ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 60 | -40% to baseline. Permits are only valid for 60 days. These are being acquired as needed throughout the project. | 80 | -10% variance to baseline. We anticipated closing the gap to baseline by the end of Q3 2012. | 90 | No variance | 48 | -10% variance to baseline. | 55 | No variance | 35 | -30% variance to baseline. | 2012-02-24 10:32 | 2012-02-24 10:32 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2012 | Q1 | Q1 - 2012 | 6278 | 5741 | FALSE | 71 | This will be on track with our baseline forecast. We expect that with construction moving forward as it has been and with the CAI's planned for connection that we will be able to attain this % complete. | 100 | HCTC Pole make Ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 80 | -20% variance to baseline. Permits are only valid for 60 days. These are being acquired as needed through the project. | 90 | No variance to baseline | 90 | No variance to baseline | 60 | -10% variance to baseline. | 70 | No variance to baseline | 14 | -54% variance to baseline. We anticipate approximately 14% of our CAI's to be connected and tested by the end of Q2 2012. We will have a much greater % of fiber run but not necessarily connected by the end of Q2. | 2012-05-24 10:14 | 2012-05-24 10:14 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2012 | Q2 | Q2 - 2012 | 7096 | 6175 | FALSE | 90 | This will put us 8% ahead of baseline. At the end of Q3 2012 we forecast that 97% of construction dollars will have been spent with three of five telephone companies having completed their construction phase of the project (Poka Lambro, WesTex and Dell City) though not all CAI connections made. Poka Lambro and WesTex have completed their CAI connections. Hill Country Telephone has 17 of 21 miles completed as of Q2 and we anticipate progress on the remaining miles in Q3. Big Bend will complete the wireless miles as well as several important CAI connections. A total of 90% of program dollars will have been spent. The reason for the 80% planned completion is due to the number of CAI's still to be connected as well as the network testing that will need to be completed. | 100 | HCTC Pole Makeready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 90 | -10% variance to baseline. Construction permits are only valid for 60 days and are being acquired as needed. Big Bend is more than 60 days from completion of all construction. | 100 | No variance to baseline | 100 | No variance to baseline | 60 | -15% to baseline. We will have 100% of our interconnection (peering) points connected and approximately 90% of our fiber laid with 44% of committed CAI's connected. | 90 | 9% ahead of baseline. Construction moving ahead of plan. | 15 | -55% off baseline. Baseline projections were off. Planned testing to be completed will be in line with the % complete we are forecasting for CAI connections (19.5% of CAI's forecast). | 2012-08-15 17:09 | 2012-08-15 17:09 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2012 | Q3 | Q3 - 2012 | 7856 | 6632 | FALSE | 89 | +15% ahead of baseline. Majority of project $ related to construction. We are ahead of schedule with fiber installation. | 100 | HCTC Pole Make Ready | No variance to baseline | 100 | No variance | 100 | No variance | 100 | No variance | 90 | -10 variance to baseline. Construction permits only valid for 60 days. Big Bend is greater than 60 days from project completion. | 100 | No variance | 100 | No variance | 70 | -15% to baseline. We are ahead on construction. We will progress with our build by adding service to additional CAI locations. | 90 | No variance to baseline | 15 | -65% to baseline. Baseline projections were off. Planned testing to be completed on CAI connections receiving service. | 2012-11-13 23:06 | 2012-11-13 23:06 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2012 | Q4 | Q4 - 2012 | 9000 | 7777 | FALSE | 93 | -2% variance to baseline. Slightly off of baseline projection due to stoppage of construction for route change request review. | 100 | HCTC Pole Make Ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 90 | -10% variance to baseline. Construction permits only valid for 60 days. Big Bend is greater than 60 days from project completion. | 95 | Big Bend still has routes to complete | 100 | No variance | 90 | -5% to baseline. Due to work stoppage on Big Bend routes will not complete construction this quarter. | 90 | -10% to baseline. Ongoing service connection and 2 wireless sites still to be connected. | 50 | -45% to baseline. Service connections are ongoing. Due to work stoppage on Big Bend routes cannot plan to have connected by end of Q1. | 2013-02-27 10:56 | 2013-02-27 10:56 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2013 | Q1 | Q1 - 2013 | 9966 | 8527 | FALSE | 95 | -5% to baseline. Delay due to route change requests. Based on program dollars forecast spent to date. | 100 | HCTC pole make ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 95 | -5% to baseline. Delay due to route change requests. Permits only valid for 60 days. | 95 | -5% to baseline. Delay due to route change requests. | 95 | -5% to baseline. Delay due to route change requests. | 95 | -5% to baseline. Delay due to route change requests. | 95 | -5 to baseline. Delay due to route change requests. | 65 | -35% to baseline. Construction still ongoing. | 2013-05-29 14:34 | 2013-05-29 14:34 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2013 | Q2 | Q2 - 2013 | 10632 | 8976 | FALSE | 100 | No variance | 100 | HCTC Pole Make Ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 2013-08-19 08:47 | 2013-08-19 08:47 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2013 | Q3 | Q3 - 2013 | 11364 | 9487 | FALSE | 97 | Project will complete favorable to planned budget. | 100 | HCTC Pole Make Ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | NO variance | 100 | NO variance | 2013-11-22 23:16 | 2013-11-22 23:16 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | 2013 | Q4 | Q4 - 2013 | 12212 | 10384 | FALSE | 100 | project is complete and is 3.3% favorable to budget. | 100 | HCTC Pole Make Ready | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 100 | No variance | 2014-05-19 15:27 | 2014-05-19 15:27 | 6341 | 6341 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570139 | 2010 | Q4 | Q4 - 2010 | 1248 | 2278 | FALSE | 10 | No variance | 0 | N/A | N/A | 100 | No variance | 100 | No variance | 35 | No variance | 25 | No variance | 10 | No variance | 10 | No variance | 10 | No variance | 0 | N/A | 2 | No variance | 2011-02-20 20:05 | 2011-02-20 20:05 | 5742 | 5742 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2011 | Q1 | Q1 - 2011 | 2144 | 2817 | FALSE | 20 | Better than anticipated make-ready completion | 0 |  | N/A | 100 | No variance | 100 | No variance | 45 | No variance | 35 | No variance | 35 | Better than anticipated make-ready completion | 7 | The original baseline listed 10% completion of Equipment Procurement by this quarter's end to match the 10% Overall Project completion also listed. However, the baseline percentage was calculated incorrectly as construction follows significantly behind make-ready completion. The calculation error was only discovered on this quarter's PPR. The Equipment Procurement percentage listed for next quarter's PPR is an accurate prediction. | 7 | The original baseline listed 10% completion of Network Build by this quarter's end to match the 10% Overall Project completion also listed. However, the baseline percentage was calculated incorrectly as construction follows significantly behind make-ready completion and equipment procurement. The calculation error was only discovered on this quarter's PPR. In this quarter, Network Build followed close enough behind Equipment Procurement to match percentages. Going forward, Network Build may match Equipment Procurement or follow closely behind. The percentage listed for next quarter's PPR is an accurate prediction. | 0 | N/A | 3 | The original baseline listed 10% completion of Network Testing by next quarter's end to match the 15% Overall Project completion also listed. However, that calculation is incorrect as there is a time lag between construction completion and Network Testing. This means that the percentage of Network Testing will track more slowly against the Overall Project rate than the percentages calculated in the original baseline. The calculation error was only discovered on this quarter's PPR. The percentage listed for next quarter's PPR is an accurate prediction. | 2011-05-18 16:16 | 2011-05-18 16:16 | 5742 | 5742 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2011 | Q2 | Q2 - 2011 | 3314 | 3419 | FALSE | 43 | Better than anticipated make-ready completion is moving the project along faster than anticipated | 0 |  | N/A | 100 | No variance | 100 | No variance | 55 | No variance | 55 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 55 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 20 | No variance | 20 | No variance | 0 | N/A | 20 | No variance | 2011-08-25 13:14 | 2011-08-25 13:14 | 5742 | 5742 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2011 | Q3 | Q3 - 2011 | 4328 | 4014 | FALSE | 50 | Better than anticipated make-ready completion is moving the project along faster than anticipated. | 0 |  | N/A | 100 | No variance | 100 | No variance | 65 | No variance | 75 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 75 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 25 | No variance | 25 | No variance | 0 | N/A | 25 | There is an error in the baseline calculation as it lists 30 percent planned completion, but testing cannot happen in advance of network build. | 2011-11-29 18:06 | 2011-11-29 18:06 | 5461 | 5461 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2011 | Q4 | Q4 - 2011 | 5076 | 4748 | FALSE | 70 | Better than anticipated make-ready completion will allow for faster than anticipated construction. | 0 |  | N/A | 100 | No variance. | 100 | No variance. | 75 | No variance. | 85 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 82 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 100 | In the next quarter, we anticipate executing the contract, ordering the equipment, receiving the equipment and paying for the equipment. This will complete this section. | 55 | Better than anticipated make-ready completion continues to allow for faster than anticipated construction. | 30 | No variance. | 55 | Better than anticipated make-ready and construction completion continues to allow for faster than anticipated network testing. | 2012-02-16 19:08 | 2012-02-16 19:08 | 5461 | 5461 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2012 | Q1 | Q1 - 2012 | 6026 | 5612 | FALSE | 76 | Better than anticipated make-ready completion will allow for faster than anticipated construction. | 0 |  | N/A | 100 | No variance. | 100 | No variance. | 90 | Better than anticipated make-ready completion will allow for faster than anticipated complete rights of way. | 97 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 92 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 100 | The final materials have shipped and the vendor shall invoice for the equipment; payment will be made in accordance with the contract terms and should complete in the upcoming quarter. | 70 | Better than anticipated make-ready completion will allow for faster than anticipated construction. | 0 | N/A | 65 | Better than anticipated make-ready completion will allow for faster than anticipated network testing. | 2012-05-10 16:22 | 2012-05-10 16:22 | 7216 | 7216 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2012 | Q2 | Q2 - 2012 | 6894 | 6073 | FALSE | 85 | Better than anticipated make-ready completion accelerated better than anticipated construction completion. | 0 |  | N/A | 100 | No variance. | 100 | No variance. | 99 | Better than anticipated make-ready completion will allow for faster than anticipated complete rights of way. | 99 | Better than anticipated make-ready completion. | 98 | Better than anticipated make-ready completion; the site preparation tracks closely with the construction permits and other approvals. | 100 | No variance. | 98 | While the backbone is complete, we are working on the approved route extension and the remaining CAI's. | 0 | N/A | 98 | While the backbone is complete, we are working on the approved route extension and the remaining CAI's; testing follows construction completion. | 2012-08-07 14:40 | 2012-08-07 14:40 | 7216 | 7216 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2012 | Q3 | Q3 - 2012 | 8018 | 6715 | FALSE | 86 | We will remain ahead of baseline due to backbone construction completing ahead of schedule. | 0 |  | N/A | 100 | No variance. | 100 | No variance. | 100 | All Rights-of-Ways should be complete | 99 | Better than anticipated make-ready completion. | 99 | Continues ahead of schedule progress; the site preparation tracks closely with the construction permits and other approvals. | 100 | All DWDM gear has been received. | 97 | All construction on remaining CAIs and route extensions is expected to be complete, with Regeneration Shelter work to continue into 2013 | 0 | N/A | 100 | All testing on remaining CAIs and route extensions is expected to be complete | 2012-11-21 13:16 | 2012-11-21 13:16 | 7216 | 7216 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2012 | Q4 | Q4 - 2012 | 8696 | 7507 | FALSE | 86 | We will remain ahead of baseline due to backbone construction completing ahead of schedule. | 0 |  | N/A | 100 | No variance. | 100 | No variance. | 100 | All Rights-of-Ways should be complete | 100 | All permits, including for regeneration shelters, are expected to be complete | 99 | Minimal Site prep work for regeneration shelters may still exist | 100 | All DWDM gear has been received. | 98 | Only Regeneration Shelter work expected to continue into Q2 2013 | 0 | N/A | 100 | All testing on remaining 4 CAIs is expected to be complete | 2013-02-11 10:30 | 2013-02-11 10:30 | 7216 | 7216 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2013 | Q1 | Q1 - 2013 | 9864 | 8469 | FALSE | 97 | Anticipates IRUs and regeneration shelters completing in Q2 | 0 |  | n/a | 100 | No variance | 100 | No variance | 100 | All known rights of way will be complete | 100 | All known permitting will be complete | 100 | All known Make Ready will be complete | 100 | All DWDM gear has been recived | 99 | Minimal costs may remain for Q3, but work should be substantially complete (this includes regeneration shelters and the approved IRUs) | 0 | n/a | 100 | All known testing will be complete | 2013-05-22 08:25 | 2013-05-22 08:25 | 7216 | 7216 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2013 | Q2 | Q2 - 2013 | 10458 | 8875 | FALSE | 100 | All items to be complete, no variance from baseline | 0 |  | n/a | 100 | No variance from baseline | 100 | No variance from baseline | 100 | All items to be complete, no variance from baseline | 100 | All items to be complete, no variance from baseline | 100 | All items to be complete, no variance from baseline | 100 | All DWDM gear received, no variance from baseline | 100 | All items to be complete, no variance from baseline | 0 | n/a | 100 | All items to be complete, no variance from baseline | 2013-07-31 12:12 | 2013-07-31 12:12 | 7216 | 7216 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | 2013 | Q3 | Q3 - 2013 | 11614 | 9741 | FALSE | 100 | All items remain complete | 0 |  | n/a | 100 | All items remain complete | 100 | All items remain complete | 100 | All items remain complete | 100 | All items remain complete | 100 | All items remain complete | 100 | All items remain complete | 100 | All items remain complete | 0 | n/a | 100 | All items remain complete | 2014-01-16 10:06 | 2014-01-16 10:06 | 7216 | 7216 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570140 | 2010 | Q4 | Q4 - 2010 | 1168 | 2203 | FALSE | 20 | Since overall completion includes site surveys, detailed planning, engineering, and other pre-construction costs which have no associated matching costs or Federal expenditures in this quarter, the overall completion percentage is greater than the projected total expenditures budgeted in the next quarter. | 0 | 0 | n/a | 100 | per baseline | 100 | per baseline | 0 | n/a | 0 | n/a | 100 | per baseline | 36 | per baseline | 20 | per baseline | 30 | per baseline | 20 | per baseline | 2011-02-15 21:59 | 2011-02-15 21:59 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2011 | Q1 | Q1 - 2011 | 2234 | 2862 | FALSE | 20 | We expect that the overall project will be behind the baseline due to the delays in the FONSI and equipment deliveries. | 0 | 0 | n/a | 100 | Anticipated that the FONSI will be issued during the next quarter, allowing the project to start construction. | 100 | per baseline | 0 | n/a | 0 | n/a | 100 | per baseline | 100 | per baseline | 15 | Network build completion percentage will be lower than baseline, with the actual amount depending upon when the FONSI is issued.. | 25 | We expect the equipment deployment to slow catch up to baseline percentages after all equipment is received next quarter. | 15 | Network testing completion percentage will be lower than baseline, with the actual amount depending upon when the FONSI is issued next quarter, | 2011-05-20 21:01 | 2011-05-20 21:01 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2011 | Q2 | Q2 - 2011 | 3064 | 3289 | FALSE | 20 | Overall project completion percentage will still be below the baseline as the project catches up with delays from the FONSI and equipment deployment. Although closely related, overall project percent completion will not directly correspond to percentage expended and is not expected to do so for this project for a number of reasons including: equipment may be received but not installed in exactly the same quarter, equipment may be received and installed but not paid for or drawn down within the same quarter, work may be done but not yet paid for and drawn down in the same quarter, specific item costs might vary slightly (up or down) from budgeted amounts, etc. In this next quarter, which is our actual project startup from a construction perspective, we expect to buy more equipment than can be deployed within the quarter in order to streamline administrative processing and maximize discounts. | 0 |  | n/a | 100 | FONSI has been issued. No further action on this milestone required. | 100 | per baseline | 0 | n/a | 0 | n/a | 100 | per baseline | 45 | Purchasing of the remainder of equipment has been delayed due to the delay in the construction schedule which could not begin until the FONSI was issued. Partial orders of additional equipment will be done during the next quarter. It is not expected that all of the equipment will be purchased until the end of the 2nd year. | 20 | Network build completion percentage will continue to be lower than Baseline until delays caused by the late issuance of the FONSI (June 2011) can be made up but construction will start during this quarter. . | 25 | Equipment deployment will be lower than the Baseline this quarter since it was not possible to procure all equipment until construction could begin. We expect to ramp up the deployment this quarter but will not catch up to Baseline until later this calendar year due to late issuance of FONSI. | 20 | Network testing will commence as fiber is installed to locations. Network testing percentage will be behind the baseline as the project catches up with installations. | 2011-08-12 16:31 | 2011-08-12 16:31 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2011 | Q3 | Q3 - 2011 | 4314 | 4007 | FALSE | 37 | Previous delays have caused the project to fall behind the baseline. However recent installations and the start of construction is allowing the project to slowly catch up to the baseline numbers. Project should see significant progress in completion percentages over the next quarter with a corresponding increase in matching funds as construction progresses. Although closely related, overall project percent completion will not directly correspond to percentage expended and is not expected to do so for this project for a number of reasons including: equipment may be received but not installed in exactly the same quarter, equipment may be received and installed but not paid for or drawn down within the same quarter, work may be done but not yet paid for and drawn down in the same quarter and specific item costs might vary slightly (up or down) from budgeted amounts. | 0 |  | n/a | 100 | completed per baseline | 100 | completed per baseline | 0 | n/a | 0 | n/a | 100 | completed per baseline | 95 | Almost all equipment in the network design will have been purchased by the end of the quarter. Procurement will be slightly less than the Baseline until construction can progress to the point where the additional equipment will be needed and procured. | 24 | Previous delays have caused the project to fall behind baseline. All interisland links should be completed by this quarter and more CAIs will be connected to the network. | 50 | Although over the next quarter the DOE and HSPLS will be making a push to complete the installs on Oahu and begin the installation of the equipment on the neighbor islands, deployment is not expected to catch up to the Baseline projections during this quarter. | 24 | Network testing will track Network Build and will continue to be behind the Baseline until the project catches up with installations. As sites are connected, the links will be fully tested and then put into production. | 2011-11-29 13:34 | 2011-11-29 13:34 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2011 | Q4 | Q4 - 2011 | 4922 | 4602 | FALSE | 48 | Previous delays due to the late receipt of the FONSI and a decreased construction work schedule during the holidays have caused the project to fall behind the Baseline. Significant progress is expected over the next quarter as sites are being lined up for actual fiber construction and more pole applications are being approved. Overall project percent completion will not directly correspond to percentage expended for a number of reasons, including: equipment may not be installed in exactly the same quarter as received or may be received and installed but not paid or drawn down in the same quarter. Work may be performed but not paid or drawn down in the same quarter and specific item costs may be slightly more or less that budgeted. | 0 |  | n/a | 100 | completed per baseline | 100 | completed per baseline | 0 | n/a | 0 | n/a | 100 | completed per baseline | 98 | Almost all equipment will have been received, inventoried and paid for by the end of this quarter. Procurement will be slightly less than the Baseline until construction can progress to the point where the final equipment is needed and is procured. | 34 | All interisland links will have been completed and activated by the end of this quarter. Significant progress will be made with new or improved CAIs as the fiber construction progresses. The network build percentage is below the baseline due to the previous quarters' delays in the EA process and the resulting delay in construction. | 60 | Installation of equipment will continue on all islands but deployment is not expected to catch up to the Baseline projections this quarter. UH will be working with DOE and HSPLS to complete the installs on Oahu and begin the installation of the equipment on the neighbor islands over the next quarters. | 34 | Network testing will track network build and will continue to be behind the baseline until the project catches up on installations. As sites are connected, the links will be fully tested and put into production. | 2012-02-08 16:54 | 2012-02-08 16:54 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2012 | Q1 | Q1 - 2012 | 6208 | 5706 | FALSE | 52 | Overall completion is still behind the Baseline due to the late receipt of FONSI and resulting construction delays in previous quarters. The process for pole approvals has improved so significant progress in fiber construction is expected over the next quarter. Overall project percent completion will not directly correspond to percentage expended since equipment may not be deployed in the same quarter as paid and siginifcant construction work completed near the end of the quarter may not be paid until the following quarter. | 0 |  | n/a | 100 | Completed per baseline | 100 | Completed per baseline | 0 | n/a | 0 | n/a | 100 | Completed per baseline | 98 | Almost all equipment will have been received and paid by the end of this quarter. Procurement will be slightly less than the Baseline until construction progresses to the point where final equipment is needed and procured. | 38 | All interisland links have been completed and significant progress will be made with new or improved CAIs as the fiber construction progresses. The network build percentage is still below the Baseline due to the previous quarters' delays in the EA process and the resulting construction delays. The project is expecting to reach baseline numbers towards the later quarters of Year 3. | 71 | Installation of equipment will continue on all islands but deployment is not expected to catch up to the Baseline projections this quarter. UH continues to work with DOE and HSPLS to complete the installs on Oahu and begin the installation of the equipment on the neighbor islands over the next quarters. The project is expecting to reach baseline numbers towards the later quarters of Year 3. | 38 | Network testing will track network build and will continue to be behind the Baseline until the project catches up on installations. As sites are connected, the links will be fully tested and put into production.The project is expecting to reach baseline numbers towards the later quarters of Year 3. | 2012-05-18 16:50 | 2012-05-18 16:50 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2012 | Q2 | Q2 - 2012 | 7024 | 6139 | FALSE | 43 | Overall Project percentage reported is based on funds expended (Total funds including match). The actual project based on the fiber construction, equipment installation and site activation is expected to be 61% completed. Overall completion is still behind the baseline due to previous delays in previous quarters from late receipt of the FONSI. Construction is progressing at a steady and more rapid rate than the previous quarter and this activity rate is expected to be carried through the following quarter. Overall project completion will not directly correspond to percentage expended since equipment may not be deployed in the same quarter as paid and construction work completed and invoiced may not result in immediate turn up of sites. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 0 |  | n/a | 100 | Completed | 100 | Completed | 0 | n/a | 0 | n/a | 100 | Completed | 98 | Almost all equipment has been purchased. Remaining equipment will be purchased later during the project as required so will remain at slightly less than Baseline until then. | 50 | All interisland links have been completed and significant progress will be made with new or improved CAIs as the fiber construction progresses. The network build percentage is still below the Baseline due to the previous quarters' delays in the EA process and the resulting construction delays. The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 80 | Installation of equipment will continue on all islands but deployment is not expected to catch up to the Baseline projections this quarter. UH continues to work with DOE and HSPLS to complete the installs on Oahu and begin the installation of the equipment on the neighbor islands over the next quarters. The project is expecting to reach baseline numbers towards the later quarters of Year 3. | 50 | Network testing will track network build and will continue to be behind the Baseline until the project catches up on installations. As sites are connected, the links will be fully tested and put into production.The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 2012-08-10 17:41 | 2012-08-10 17:41 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2012 | Q3 | Q3 - 2012 | 7886 | 6647 | FALSE | 52 | Overall project completion percentage is based on funds expended (total funds including match). It is expected that the major subcontractor, Oceanic Time Warner, will catch up on invoicing during this quarter so that project expenditures will more closely match the actual project completion, projected at close to 70%. Overall completion is still behind the baseline due to previous delays in previous quarters from late receipt of the FONSI. Construction is progressing at a steady and more rapid rate than the previous quarter and this activity rate is expected to be carried through the following quarter. Overall project completion will not directly correspond to percentage expended since equipment may not be deployed in the same quarter as paid and construction work completed and invoiced may not result in immediate turn up of sites. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 0 |  | n/a | 100 | Completed | 100 | Completed | 0 | n/a | 0 | n/a | 100 | Completed | 98 | Almost all equipment has been purchased. Remaining equipment will be purchased later during the project as required so will remain at slightly less than Baseline until then. | 70 | All interisland links have been completed and significant progress will be made with new or improved CAIs as the fiber construction progresses. The network build percentage is still below the Baseline due to the previous quarters' delays in the EA process and the resulting construction delays. The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 85 | Installation of equipment will continue on all islands but deployment is not expected to catch up to the Baseline projections this quarter. UH continues to work with DOE and HSPLS to complete the installs on Oahu and begin the installation of the equipment on the neighbor islands over the next quarters. The project is expecting to reach baseline numbers towards the later quarters of Year 3. | 70 | Network testing will track network build and will continue to be behind the Baseline until the project catches up on installations. As sites are connected, the links will be fully tested and put into production.The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 2012-11-14 20:30 | 2012-11-14 20:30 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2012 | Q4 | Q4 - 2012 | 8754 | 7550 | FALSE | 54 | Overall project completion percentage is based on funds expended (total funds including match). It is expected that the major subcontractor, Oceanic Time Warner, will catch up on invoicing during this quarter so that project expenditures will more closely match the actual project completion, projected at 75%. Overall completion is still behind the baseline due to previous delays in previous quarters from late receipt of the FONSI. Construction is progressing at a steady and more rapid rate than the previous quarter and this activity rate is expected to be carried through the following quarter. Overall project completion will not directly correspond to percentage expended since equipment may not be deployed in the same quarter as paid and construction work completed and invoiced may not result in immediate turn up of sites. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 0 |  | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 98 | Almost all equipment has been purchased. Remaining equipment will be purchased later during the project as required so will remain at slightly less than Baseline until then. | 75 | All interisland links have been completed and significant progress will be made with new or improved CAIs as the fiber construction progresses. The network build percentage is still below the Baseline due to the previous quarters' delays in the EA process and the resulting construction delays. The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 90 | Installation of equipment will continue on all islands but deployment is not expected to catch up to the Baseline projections this quarter. UH continues to work with DOE and HSPLS to complete the installs on Oahu and begin the installation of the equipment on the neighbor islands over the next quarters. Some equipment will be installed when sites are activated due to logistical issues. As such, deployment will not be fully completed until all sites have been activated. | 75 | Network testing will track network build and will continue to be behind the Baseline until the project catches up on installations. As sites are connected, the links will be fully tested and put into production.The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 2013-02-13 14:15 | 2013-02-13 14:15 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2013 | Q1 | Q1 - 2013 | 9806 | 8438 | FALSE | 69 | Overall project completion percentage is based on funds expended (total funds including match). It is expected that the major subcontractor, Oceanic Time Warner, will catch up on invoicing during this quarter so that project expenditures will more closely match the actual project completion, projected at 90%. Overall completion is still behind the baseline due to previous delays in previous quarters from late receipt of the FONSI. Construction is progressing at a steady and more rapid rate than the previous quarter and this activity rate is expected to be carried through the following quarter. Overall project completion will not directly correspond to percentage expended since equipment may not be deployed in the same quarter as paid and construction work completed and invoiced may not result in immediate turn up of sites. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 0 |  | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 100 | completed | 90 | All interisland links have been completed and significant progress will be made with new or improved CAIs as the fiber construction progresses. The network build percentage is still below the Baseline due to the previous quarters' delays in the EA process and the resulting construction delays. The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 95 | Installation of equipment will continue on all islands but deployment is not expected to catch up to the Baseline projections this quarter. UH continues to work with DOE and HSPLS to complete the installs on Oahu and begin the installation of the equipment on the neighbor islands over the next quarters. Some equipment will be installed when sites are activated due to logistical issues. As such, deployment will not be fully completed until all sites have been activated. | 90 | Network testing will track network build and will continue to be behind the Baseline until the project catches up on installations. As sites are connected, the links will be fully tested and put into production.The project is expecting to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. | 2013-05-17 18:00 | 2013-05-17 18:00 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2013 | Q2 | Q2 - 2013 | 10590 | 8952 | FALSE | 96 | Overall project completion percentage is based on funds expended (total funds including match). The actual construction completion percentage is also estimated at 96%. The initial delay of nearly a year for Environmental Assessment (EA) caused more applications for utility poles and conduits to be submitted than could be processed in that shorter time frame. This is a major reason why completion is less than Baseline and why we are requesting a 6-month no cost extension to complete the remaining sites. | 0 |  | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 100 | completed | 96 | All but approximately 19 sites would have been completed. These 19 are part of the requested no cost extension. | 100 | completed | 96 | Network testing will track the Network Build. | 2013-08-14 19:54 | 2013-08-14 19:54 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2013 | Q3 | Q3 - 2013 | 11288 | 9441 | FALSE | 97 | Overall project completion percentage is based on funds expended (total funds including match). The actual construction completion percentage is estimated at 98% as the project continues to work on the extension sites. | 0 | true | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 99 | Almost all equipment will have been purchased by the next quarter. Previous quarter estimation was that all equipment was to be purchased. Due to the extension, some equipment purchases were delayed to wait for fiber build completion of the extension sites. | 98 | Network build will be almost all completed - we are expecting the last few extension sites to still be in construction by the end of next quarter per the extension project plan. | 98 | Almost all equipment will have been deployed to the sites and will be awaiting the fiber build. Previous quarter estimation was that all equipment was to be purchased. Due to the extension, some equipment installations were delayed to wait for fiber build completion of the extension sites. | 98 | Network testing tracks the network build. | 2013-11-19 12:13 | 2013-11-19 12:13 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570140 | 2013 | Q4 | Q4 - 2013 | 11902 | 10069 | FALSE | 99 | Overall project completion percentage is based on funds expended (total funds including match). Actual construction completion percentage will be 100%. The project will not be able to spend 100% of the funds. | 0 |  | n/a | 100 | completed | 100 | completed | 0 | n/a | 0 | n/a | 100 | completed | 100 | All equipment for the project will have been purchased. | 100 | Network will be fully built. | 100 | All equipment will have been deployed | 100 | Network will be 100% tested | 2014-02-26 21:15 | 2014-02-26 21:15 | 6701 | 6701 | University of Hawaii Systems | TRUE
NT10BIX5570144 | 2010 | Q4 | Q4 - 2010 | 1256 | 2285 | FALSE | 11 | no variance | 0 | n/a | not applicable | 100 | no variance | 14 | no variance | 28 | no variance | 28 | no variance | 0 | no variance | 8 | no variance | 4 | no variance | 2 | no variance | 2 | no variance | 2011-02-21 13:17 | 2011-02-21 13:17 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2011 | Q1 | Q1 - 2011 | 2398 | 2944 | FALSE | 4 | Based on the shortened first quarter issue noted in 3 above, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Additionally we will be submitting a revised baseline plan to reflect progress based on expenditures rather than activity. Given the time lag between expenditures incurred and federal draw down, there will be more activity than federal funds drawn. | 0 | not applicable | not applicable | 100 | no variance | 2 | Based on the shortened first quarter issue noted in 3 above, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Additionally we will be submitting a revised baseline plan to reflect progress based on expenditures rather than activity. Given the time lag between expenditures incurred and federal draw down, there will be more activity than federal funds drawn. | 0 | Based on the shortened first quarter issue noted in 3 above, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Additionally we will be submitting a revised baseline plan to reflect progress based on expenditures rather than activity. Given the time lag between expenditures incurred and federal draw down, there will be more activity than federal funds drawn. | 17 | Based on the shortened first quarter issue noted in 3 above, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Additionally we will be submitting a revised baseline plan to reflect progress based on expenditures rather than activity. Given the time lag between expenditures incurred and federal draw down, there will be more activity than federal funds drawn. | 0 | no variance | 0 | Based on the shortened first quarter issue noted in 3 above, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Additionally we will be submitting a revised baseline plan to reflect progress based on expenditures rather than activity. Given the time lag between expenditures incurred and federal draw down, there will be more activity than federal funds drawn. | 3 | Based on the shortened first quarter issue noted in 3 above, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Additionally we will be submitting a revised baseline plan to reflect progress based on expenditures rather than activity. Given the time lag between expenditures incurred and federal draw down, there will be more activity than federal funds drawn. | 13 | no variance | 11 | no variance | 2011-05-31 11:39 | 2011-05-31 11:39 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2011 | Q2 | Q2 - 2011 | 3162 | 3341 | FALSE | 27 | Variance 3% - Construction will begin in mid July with the first contractor. The second contractor will begin construction in mid August. Two contractors on the project will facilitate progress in the next quarter. Permitting and rights of way will be in full gear and should progress in advance of construction. | 0 | n/a | not applicable | 100 | no variance | 31 | Variance -11% There will be more activities than federal dollars spent during the report period. Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there will be positive variance from the baseline plan for the project at twelve months and two weeks from initiation. The core network design will be 65% completed during this quarter. Additionally we anticipate having a majority of CAIs with commitments to the project and will be in the process of finalizing last mile routes and engineering. | 10 | Variance -43% There will be more activities than federal dollars spent during the report period. Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there will be little variance from the baseline plan for the project at twelve months and two weeks from initiation. Permitting and rights of way will continue through the quarter to get ahead of construction by 3 - 6 months. We anticipate submitting all applications for rights of way during this quarter. | 10 | Variance -43% There will be more activities than federal dollars spent during the report period. Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there will be little variance from the baseline plan for the project at twelve months and two weeks from initiation. Permitting and rights of way will continue through the quarter to get ahead of construction by 3 - 6 months. We anticipate having permits for all submitted applications during this quarter. | 0 | Variance -17% There will be more activities than federal dollars spent during the report period. Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there will be positive variance from the baseline plan for the project at twelve months and two weeks from initiation. Construction will begin during the quarter which may not generate site preparation expenditures until the following quarter. | 16 | Variance -17% There will be more activities than federal dollars spent during the report period. Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted above. The wireless installation and equipment RFP will be released during this quarter. We anticipate the start of equipment procurement however, activities will outpace expenditures during the quarter. | 21 | no variance | 10 | Variance -15% There will be more activities than federal dollars spent during the report period. Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there will be positive variance from the baseline plan for the project at twelve months and two weeks from initiation. Construction will begin during the quarter. We anticipate the start of equipment deployment however, activities will outpace expenditures during the quarter. | 10 | Variance -15% There will be more activities than federal dollars spent during the report period. Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there will be positive variance from the baseline plan for the project at twelve months and two weeks from initiation. Construction will begin during the quarter. We anticipate the start of network testing however, activities will outpace expenditures during the quarter. | 2011-08-17 16:53 | 2011-08-17 16:53 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2011 | Q3 | Q3 - 2011 | 3936 | 3806 | FALSE | 24 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 0 | n/a | not applicable | 100 | no variance | 23 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 29 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 50 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 23 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 20 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 25 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 25 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 15 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. | 2011-11-09 13:39 | 2011-11-09 13:39 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2011 | Q4 | Q4 - 2011 | 5142 | 4808 | FALSE | 37 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate nearing completion of the new fiber optic network design and significant permitting during the next quarter. Construction activity will continue despite the winter weather with more activity focused on boring rather than plowing. We anticipate having more than 40% of conduit completed and 20% of fiber blown by the end of the next quarter. The wireless vendor contract will be executed with design on the initial wireless links initiated. We anticipate reaching over 90% of our CAIs and securing commitments from 60%. The CAI equipment will be received during February with installation activities beginning late in the quarter. The core network equipment RFP will be released by mid February. | 0 | N/A | N/A | 100 | no variance | 40 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate having over 95% of the new fiber optic network designed and submitted with 60% of the network permitted. Engineering will begin on 6 of the wireless network links during the quarter. | 61 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate having 60% of the new fiber optic network permitted during the quarter. | 72 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate having 60% of the new fiber optic network permitted during the quarter. | 32 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate having more than 40% of conduit completed and 20% of fiber blown by the end of the next quarter. The wireless vendor contract will be executed with design on the initial wireless links initiated. | 15 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be received during February with installation activities beginning late in the quarter. The core network equipment RFP will be released by mid February. | 41 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate having more than 40% of conduit completed and 20% of fiber blown by the end of the quarter. The wireless vendor contract will be executed with design on the initial wireless links initiated. We anticipate executing IRUs for 60 of the leased miles planned. | 20 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be received during February with deployment/installation activities beginning late in the quarter. The core network equipment RFP will be released by mid February. | 21 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate having more than 40% of conduit completed and 20% of fiber blown by the end of the next quarter. Network testing will take place on a majority of the completed new fiber miles. | 2012-02-20 05:56 | 2012-02-20 05:56 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2012 | Q1 | Q1 - 2012 | 6152 | 5678 | FALSE | 56 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate nearing completion of the new fiber optic network design and significant permitting during the next quarter. We anticipate having more than 60% of conduit completed and 40% of fiber blown by the end of the next quarter. The wireless vendor will begin construction with 5 links and complete design for another 7 links. We anticipate reaching nearly all of our CAIs and securing commitments from 90%. The CAI equipment will be installed at connected locations. The core network equipment RFP will be awarded and initial equipment purchased. | 0 | N/A | N/A | 100 | no variance | 55 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We are near completion with the fiber optic network design and anticipate permitting near 90% during the next quarter. | 80 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We are near completion with the fiber optic network design and anticipate permitting near 90% during the next quarter. | 83 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We are near completion with the fiber optic network design and anticipate permitting near 90% during the next quarter. | 61 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate nearing completion of the new fiber optic network design and significant permitting during the next quarter. We anticipate having more than 420 miles of conduit completed and 325 miles of fiber blown by the end of the next quarter. The wireless vendor will begin construction with 5 links and complete design for another 7 links. We anticipate reaching nearly all of our CAIs and securing commitments from 90%. The CAI equipment will be installed at connected locations. The core network equipment RFP will be awarded and initial equipment purchased. | 32 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be awarded and initial equipment purchased. | 61 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate nearing completion of the new fiber optic network design and significant permitting during the next quarter. We anticipate having more than 420 miles of conduit completed and 325 miles of fiber blown by the end of the next quarter. The wireless vendor will begin construction with 5 links and complete design for another 7 links. We anticipate reaching nearly all of our CAIs and securing commitments from 90%. The CAI equipment will be installed at connected locations. The core network equipment RFP will be awarded and initial equipment purchased. | 24 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be awarded and initial equipment purchased. | 41 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate nearing completion of the new fiber optic network design and significant permitting during the next quarter. We anticipate having more than 420 miles of conduit completed and 325 miles of fiber blown by the end of the next quarter. The wireless vendor will begin construction with 5 links and complete design for another 7 links. We anticipate reaching nearly all of our CAIs and securing commitments from 90%. The CAI equipment will be installed at connected locations. The core network equipment RFP will be awarded and initial equipment purchased. | 2012-05-17 11:36 | 2012-05-17 11:36 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2012 | Q2 | Q2 - 2012 | 6928 | 6091 | FALSE | 71 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 95% permitted. We anticipate having more than 85% of conduit completed and 70% of fiber blown by the end of the next quarter. The wireless vendor will complete 5 links and begin construction for another 7 links. We anticipate reaching nearly all of our CAIs and securing commitments from 100%. The CAI equipment will be installed at connected locations. The core network equipment RFP will be received and installation initiated. | 0 | N/A | N/A | 100 | no variance | 60 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We are near completion with the fiber optic network design and anticipate permitting near 95% during the next quarter. | 100 | no variance | 100 | no variance | 79 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 95% permitted. We anticipate having more than 85% of conduit completed and 70% of fiber blown by the end of the next quarter. | 42 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be received and installation initiated. | 71 | no variance | 50 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be received and installation initiated. | 51 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 95% permitted. We anticipate having more than 85% of conduit completed and 70% of fiber blown by the end of the next quarter. The wireless vendor will complete 5 links and begin construction for another 7 links. | 2012-08-08 15:04 | 2012-08-21 07:35 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2012 | Q3 | Q3 - 2012 | 7830 | 6618 | FALSE | 73 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. Pending route modifications are delaying progress. We anticipate 100% completion of the new fiber optic network design and 95% permitted. We anticipate having more than 90% of conduit completed and 85% of fiber blown for existing fiber routes by the end of the next quarter. The wireless vendor will complete 3 links, several more are pending route modifications. We anticipate reaching nearly all of our CAIs and securing commitments from 100%. The CAI equipment will be installed at connected locations. The core network equipment RFP will be received and installation initiated. | 0 | N/A | N/A | 100 | no variance | 74 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We are near completion with the fiber optic network design and anticipate permitting near 95% during the next quarter. | 100 | no variance | 100 | no variance | 94 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 95% permitted. We anticipate having more than 90% of conduit in existing approved routes completed and 85% of fiber blown by the end of the next quarter. | 51 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be installed. | 78 | no variance | 43 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be installed. | 35 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 95% permitted. We anticipate having more than 90% of conduit in existing approved routes completed and 85% of fiber blown by the end of the next quarter. The wireless vendor will complete 3 links, the remaining are on hold pending route modifications. | 2012-11-13 06:22 | 2012-11-13 06:22 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2012 | Q4 | Q4 - 2012 | 9156 | 7982 | FALSE | 83 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. Pending route modifications are delaying progress. We anticipate 100% completion of the new fiber optic network design and 100% permitted. We anticipate having more than 95% of conduit in existing approved routes completed and 90% of fiber blown for existing fiber routes by the end of the next quarter. The wireless vendor will complete 3 links, several more are pending route modifications. We anticipate reaching nearly all of our CAIs and securing commitments from 100%. The CAI equipment will be installed at connected locations. The core network equipment RFP will be received and installation initiated. | 0 | N/A | N/A | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 95 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 100% permitted. We anticipate having more than 95% of conduit in existing approved routes completed and 90% of fiber blown by the end of the next quarter. | 100 | no variance | 90 | no variance | 56 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be installed. | 68 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 100% permitted. We anticipate having more than 95% of conduit in existing approved routes completed and 90% of fiber blown by the end of the next quarter. Testing will be completed for most of the completed miles. | 2013-03-29 14:31 | 2013-03-29 14:31 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2013 | Q1 | Q1 - 2013 | 9634 | 8349 | FALSE | 90 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. Pending route modifications are delaying progress. We anticipate 100% completion of the new fiber optic network design and 100% permitted. We anticipate having 100% of conduit in existing approved routes completed and 100% of fiber blown for existing fiber routes by the end of the next quarter. The wireless vendor will complete 3 links, several more are pending route modifications. We anticipate reaching nearly all of our CAIs and securing commitments from 100%. The CAI equipment will be installed at connected locations. The core network equipment will be lit during the next quarter. | 0 | N/A | N/A | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 85 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be installed. | 92 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 100% permitted. We anticipate having 100% of conduit in existing approved routes completed and 95% of fiber blown by the end of the next quarter. Testing will be completed for most of the completed miles. | 90 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The CAI equipment will be installed at connected locations. The core network equipment RFP will be installed. | 85 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to pending route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. We anticipate 100% completion of the new fiber optic network design with 100% permitted. We anticipate having 100% of conduit in existing approved routes completed and 95% of fiber blown by the end of the next quarter. Testing will be completed for most of the completed miles. | 2013-05-08 16:44 | 2013-05-08 16:44 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2013 | Q2 | Q2 - 2013 | 10494 | 8898 | FALSE | 89 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The route modification process delayed construction progress. We anticipate 100% completion of the new fiber optic network design and 100% permitted. We anticipate having 100% of conduit in existing approved routes completed and 99% of fiber blown for existing fiber routes by the end of the next quarter. The wireless vendor will complete 5 links. We anticipate reaching an additional 80 CAIs and securing commitments from 100%. The CAI equipment will be installed at connected locations. The last core site and 80% of the remaining distribution network equipment will be installed and lit during the next quarter. | 0 | N/A | N/A | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 90 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The route modification process delayed construction progress. We anticipate 100% completion of the new fiber optic network design and 100% permitted. We anticipate having 100% of conduit in existing approved routes completed and 99% of fiber blown for existing fiber routes by the end of the next quarter. The wireless vendor will complete 5 links. We anticipate reaching an additional 80 CAIs and securing commitments from 100%. The CAI equipment will be installed at connected locations. The last core site and 80% of the remaining distribution network equipment will be installed and lit during the next quarter. | 85 | There will be more activity than federal dollars expended during the quarter. Variance is also due in part to route modifications, permitting, delayed FONSI, and Shortened First Quarter issue noted in Q3. The route modification process delayed construction progress. We anticipate 100% completion of the new fiber optic network design and 100% permitted. We anticipate having 100% of conduit in existing approved routes completed and 99% of fiber blown for existing fiber routes by the end of the next quarter. The wireless vendor will complete 5 links. We anticipate reaching an additional 80 CAIs and securing commitments from 100%. The CAI equipment will be installed at connected locations. The last core site and 80% of the remaining distribution network equipment will be installed and lit during the next quarter. | 100 | no variance | 2013-08-06 14:15 | 2013-08-06 14:15 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2013 | Q3 | Q3 - 2013 | 11386 | 9501 | FALSE | 100 | no variance | 0 | N/A | N/A | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 100 | no variance | 2013-11-26 10:00 | 2013-11-26 10:00 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | 2013 | Q4 | Q4 - 2013 | 12176 | 10359 | FALSE | 100 | N/A | 0 | N/A | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 100 | N/A | 2014-05-07 16:46 | 2014-05-07 16:46 | 6512 | 6512 | Northern Illinois University, Inc. | TRUE
NT10BIX5570145 | 2010 | Q4 | Q4 - 2010 | 1014 | 2059 | FALSE | 30 | If we can get the EA SAC completed the project will be on schedule. | 95 | Grant Prep-Other | N/A | 100 | The EA SAC should be complete. | 90 | Mostly done, just leaving room for unanticipated changes. | 100 | These will be given from the Tribe to the Tribe. | 100 | Permits and Applications will be issued by the Tribe. | 30 | Begin to trench first leg of project. | 30 | We will begin to purchase most of leg one equipment. | 30 | Network build will coincide closely with over project completion. | 30 | All equipment purchased will be deployed. | 30 | Testing will be done before fiber is laid and then again at end of project. | 2011-02-09 10:28 | 2011-02-09 10:28 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2011 | Q1 | Q1 - 2011 | 2354 | 2922 | FALSE | 41 | We believe the project will get back on track. |  |  |  | 100 | The EA SAC is complete. | 90 | Mostly done, just leaving room for unanticipated changes. | 100 | These will be given from the Tribe to the Tribe. | 100 | Permits and Applications will be issued by the Tribe. | 30 | Begin to trench first leg of project. | 30 | We will begin to purchase most of leg one equipment. | 30 | Network build will coincide closely with over project completion. | 30 | All equipment purchased will be deployed. | 30 | Testing will be done before fiber is laid and then again at end of project. | 2011-05-26 14:55 | 2011-05-26 14:55 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2011 | Q2 | Q2 - 2011 | 3108 | 3311 | FALSE | 67 | This will show significant change from last quarter. | 100 |  | The funds in this category will be expended. | 100 | Complete | 90 | Mostly complete | 100 | Complete | 100 | Complete | 30 | We don't see any reason that this can't be accomplished. | 30 | We should meet or exceed this goal during this quarter | 30 | Construction should be well on its way. | 30 | We believe we can accomplish this goal. | 30 | Pretesting will be complete and possibly some of the main loop power meter. | 2011-08-16 10:17 | 2011-08-16 10:17 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2011 | Q3 | Q3 - 2011 | 3892 | 3784 | FALSE | 44 | We are reducing are projections to 44% because we think it more accurately reflect were we will be by the end of next quarter. | 100 | N/A | The funds in this category will be expended | 100 | Complete | 90 | Mostly Complete | 100 | Complete | 100 | Complete | 30 | Weather permitting we will meet this projection | 65 | We have purchased a good portion of our equipment and will configure it and install it so that we can light up the fiber when it is ready. | 30 | Construction will be started, and we hope to get a section of fiber done before we can not dig due to weather. We do not anticipate that we will get it all in, but are hoping on completing the majority of the main fiber run. | 30 | Equipment will configured and deployed and this goal should easily be met. | 30 | Pretesting will be complete and possibly some of the main loop power meter and OCR testing will be completed. | 2011-11-03 21:23 | 2011-11-28 12:38 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2011 | Q4 | Q4 - 2011 | 5018 | 4689 | FALSE | 54 | We don't expect there to be a lot of change in this next quarter, however, we will be ramping up for a big 2nd quarter 2012. | 100 | Misc. | This category should be completed. | 100 | Complete | 90 | Mostly Complete | 100 | Complete | 100 | Complete | 15 | Weather Permitting we will meet this projection | 90 | We will purchase a good portion of the remainder of the needed equipment. | 50 | We believe we should be well on our way to being 50% complete by this quarters end. | 90 | We will be spending a significant portion of our time this quarter on equipment deployment, as it can be done in-doors and is not contingent on weather conditions. | 50 | We will be testing all the runs and equipment as deployed and thus should be about 50% or greater on the testing phase. | 2012-02-14 21:49 | 2012-02-14 21:49 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2012 | Q1 | Q1 - 2012 | 6324 | 5764 | FALSE | 79 | We should complete 3 of the 4 fiber legs on the main fiber loop. We also should be able to connect 9 new CAI during this next quarter. | 100 | n/a | Complete | 100 | Complete | 95 | We are mostly complete with the network design, however, we will still have some remaining issues that may arise from lateral connections. | 100 | Complete | 100 | Complete | 76 | We should be well on our way to being over 50 percent done with the main fiber loop, and we will begin construction on some of the lateral connections. | 98 | We will purchase a good portion of the remainder of the needed equipment. | 65 | We believe we should be well on our way to being 65% complete by this quarters end. | 95 | We will continue to spend a significant portion of our time this quarter on equipment deployment, as it can be done in-doors and is not contingent on weather conditions. | 65 | We will be testing all the runs and equipment as deployed and thus should be about 65% or greater on the testing phase. | 2012-05-29 13:58 | 2012-05-29 13:58 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2012 | Q2 | Q2 - 2012 | 6932 | 6093 | FALSE | 83 | We should complete 3 of the 4 fiber legs on the main fiber loop. We also should be able to connect new CAI's during this next quarter. | 100 |  | Complete | 100 | Complete | 95 | We are mostly complete with the network design, however, we will still have some remaining issues that may arise from lateral connections. | 100 | Complete | 100 | Complete | 78 | We should be well on our way to being over 60 percent done with the main fiber loop, and we will begin construction on some of the lateral connections. | 100 | Complete | 65 | We believe we should be well on our way to being 65% complete by this quarters end. | 100 | Complete | 65 | We will be testing all the runs and equipment as deployed and thus should be about 65% or greater on the testing phase. | 2012-08-08 15:40 | 2012-08-08 15:40 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2012 | Q3 | Q3 - 2012 | 8090 | 6751 | FALSE | 95 | We will be connecting most of the CAI in this next quarter. | 100 | n/a | Complete | 100 | Complete | 98 | We are mostly complete with the network design, however, we will still have some remaining issues that may arise from lateral connections. | 100 | Complete | 100 | Complete | 90 | With the main loop completed and the laterals mostly complete we will be working on connections of main to lateral and laterals to CAI's | 100 | Complete | 80 | We believe we should be well on our way to being 95 complete by this quarters end. We will be terminating at our CAI's this next qrt and completing portions of the network. | 100 | Complete | 85 | Due to weather concerns we chose to deploy the construction elements and forgo the testing so that we could complete that phase. Testing will be implemented during this quarter. | 2012-11-27 19:25 | 2012-11-27 19:25 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2012 | Q4 | Q4 - 2012 | 8786 | 7585 | FALSE | 100 | We should be complete by the end of next quarter. | 100 |  | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We have a few buildings that we were not able to get to last fall. We will have to connect them in the spring, as winter does not allow digging. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 2013-02-14 18:19 | 2013-02-14 18:19 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2013 | Q1 | Q1 - 2013 | 9816 | 8444 | FALSE | 100 | We should be complete by the end of next quarter. | 100 | N/A | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 100 | We should be complete by the end of next quarter. | 2013-05-20 10:41 | 2013-05-20 10:41 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2013 | Q2 | Q2 - 2013 | 10084 | 8602 | FALSE | 100 | We will be complete by the end of grant period. | 100 | N/A | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 100 | We will be complete by the end of grant period. | 2013-07-02 12:40 | 2013-07-02 12:40 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570145 | 2013 | Q3 | Q3 - 2013 | 10860 | 9114 | FALSE | 100 | Completed | 100 | N/A | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 100 | Completed | 2013-09-28 17:47 | 2013-09-28 17:47 | 6429 | 6429 | Ute Indian Tribe | TRUE
NT10BIX5570146 | 2010 | Q4 | Q4 - 2010 | 1226 | 2255 | FALSE | 12 | No Variance | 27 | Admin | No Variance | 100 | No Variance | 25 | Slight increase due to start of construction phase 1 | 0 | No Variance | 0 | No Variance | 0 | No Variance | 26 | No Variance | 0 | No Variance | 0 | No Variance | 0 | No Variance | 2011-02-18 15:49 | 2011-02-18 15:49 | 6425 | 6425 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2011 | Q1 | Q1 - 2011 | 1724 | 2590 | FALSE | 18 | Slight variance below budget 1% due to anticipated fiber procurement delay. | 37 | Admin. | No variance. | 100 | EA delayed but expected to be final in Y1 Q4. | 30 | No variance. | 41 | No variance. | 16 | No variance. | 84 | No variance. | 31 | Slight variance below budget due to anticipated fiber procurement delay. | 4 | No variance. | 10 | No variance. | 0 | Original Category items "test equipment" moved to Procurement and "testing fiber" moved to Network Build. | 2011-04-29 17:07 | 2011-04-29 17:07 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2011 | Q2 | Q2 - 2011 | 2960 | 3237 | FALSE | 32 | Some expenses moved from 2012 to 3rd Qtr 2011 due to expectation that portions of project will occur more quickly than anticipated. | 50 | Admin | Legal expenses are expected to be underbudget, thus a Portion of legal expenses moved to Site Preparation. | 100 | No variance. | 40 | No variance. | 77 | Cable easements are expected to be underbudget, thus a portion of cable easement expense moved to Site Preparation. | 32 | No variance. | 60 | Shelters will be arriving, but will not be invoiced in 3rd Qtr, some budgeted expenses were moved from other categories. | 55 | Cost of DWDM equipment less than budgeted. | 10 | Portion of Carrier Construction labor moved from 2012 to 3rd Qtr 2011 | 30 | No variance. | 0 | N/A | 2011-08-08 15:48 | 2011-08-08 15:48 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2011 | Q3 | Q3 - 2011 | 4256 | 3978 | FALSE | 55 | Fiber delay has caused a slight delay in the Overall Project's progress compared to the baseline projections. However, with the contribution of in-kind fiber and the progress of construction, Sho-Me anticipates catching up to near baseline projections in 4th Qtr 2011. | 58 | Legal, Administrative, Pre-Award Expenses | Above Baseline 2%, however, Legal expenses are expected to be under budget, thus a portion of Legal expenses budgeted were moved to Site Preparation. | 100 | No variance. | 60 | Above Baseline 10% because more time actually devoted prior to construction than will be needed later in project, though Network Design was budgeted evenly throughout project. | 77 | Below Baseline by 6% since cable easements are expected to be under budget, thus a portion of cable easement expense moved to Site Preparation. | 48 | No variance. | 91 | Below Baseline by 9%, however, extended budgeted costs into 2012 to account for work that will be performed throughout the construction process. | 63 | Below Baseline by 5% as cost of DWDM equipment less than budgeted. | 46 | No variance. | 82 | Above Baseline 35% due to the Increased cost of innerduct. The purchase of innerduct is near completion. The increased cost is not anticipated to affect the category budget by more than 10%. | 0 | Below Baseline by 46% because these expenses were moved to another category for budgeting purposes. Sho-Me does not anticipate having any costs in this category for the remainder of the project. | 2011-11-23 13:39 | 2011-11-23 13:39 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2011 | Q4 | Q4 - 2011 | 5104 | 4773 | FALSE | 67 | 1% below Baseline due to fiber availability issues, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. However, Sho-Me is catching up to Baseline quickly and anticipates being at the Baseline Projections by the end of 4th Qtr 2012. | 52 | Legal, Administrative, Pre-Award Expenses | 13% below Baseline Due to legal and administrative costs being lower than anticipated. | 88 | 12% below Baseline due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 73 | 13% above Baseline due to more engineering and design work being performed at the onset of the project than anticipated. | 38 | 53% below Baseline due to lower than anticipated rights of way costs | 87 | 23% above Baseline due to Warsaw River Crossing Agreement with MODOT. | 100 | No Variance. | 64 | 11% below Baseline due to lower than anticipated costs relating to DWDM equipment. | 66 | 5% above Budget due to contribution of in-kind fiber. | 100 | 36% above Baseline due to increased costs of innerduct and because Sho-Me chose to buy most of the innerduct up front rather than spreading it throughout the project. | 0 | Below Baseline by 61% because these expenses were moved to another category for budgeting purposes. Sho-Me does not anticipate having any costs in this category for the remainder of the project. | 2012-02-17 15:04 | 2012-02-17 15:04 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2012 | Q1 | Q1 - 2012 | 5928 | 5563 | FALSE | 69 | 6% below baseline due to fiber availability issues, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. However, Sho-Me is catching up to Baseline quickly and anticipates being at the Baseline Projections by the end of 4th Qtr 2012. | 69 | Legal, Administrative, Pre-Award Expenses | 5% below baseline due to legal and administrative costs being lower than anticipated. | 90 | 10% below baseline due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. Sho-Me anticipates catching up to baseline by the end of 2012. | 80 | 10% above baseline due to more engineering and design work being performed at the onset of the project than anticipated. | 75 | 25% below baseline due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as right of way costs continue to come in under budget. | 80 | No variance. | 100 | No variance. | 59 | 24% below baseline due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates catching up to baseline by the end of 2012. | 72 | 4% above baseline due to contribution of in-kind fiber. | 100 | 28% above baseline due to increased costs of innerduct. Also, Sho-Meâ€™s baseline reflects buying innerduct throughout the project as it is needed, but instead Sho-Me chose to buy most of the innerduct up front in order to secure a lower price per foot. | 0 | Below Baseline by 61% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2012-05-04 11:19 | 2012-05-04 11:19 | 6426 | 6426 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2012 | Q2 | Q2 - 2012 | 6554 | 5891 | FALSE | 76 | Below Baseline by 9% due to fiber availability issues, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. Sho-Me anticipates it will meet baseline projections by the end of 2012. | 67 | Legal, Administrative, Pre- Award Expenses | Below Baseline by 16% due to legal and administrative costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 96 | Below Baseline by 4% due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 89 | Above Baseline by 9% due to more engineering and design work being performed at the onset of the project than anticipated. | 38 | Below Baseline by 62% due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as right of way costs continue to come in under budget. | 96 | Below Baseline by 4% due to costs being lower than anticipated. Sho-Me does anticipate catching up to baseline by the end of 2012 as construction continues. | 100 | No variance. | 74 | Below Baseline by 21% due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 76 | Below Baseline by 2% due to the delay in fiber optic cable. However, Sho-Me anticipates it will meet baseline projections by the end of 2012. | 100 | Above Baseline by 17% due to increased costs of innerduct. Also, Sho-Meâ€™s baseline reflects buying innerduct throughout the project as it is needed, but instead Sho-Me chose to buy most of the innerduct up front in order to secure a lower price per foot. | 0 | Below Baseline by 78% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2012-07-27 18:15 | 2012-07-27 18:15 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2012 | Q3 | Q3 - 2012 | 7908 | 6658 | FALSE | 87 | Below Baseline by 5% due to fiber availability issues, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. Sho-Me anticipates it will meet baseline projections by 1st Quarter 2013. | 73 | Legal, Administrative, Pre-Award Expenses | Below Baseline by 19% due to legal and administrative costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 90 | Below Baseline by 10% due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 88 | Below Baseline by 2% due to more engineering and design work being performed at the onset of the project, the costs attributable to Network Design are expected to decrease. | 38 | Below Baseline by 62% due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as rights of way costs continue to come in under budget. | 79 | Below Baseline by 21% due to costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project as permitting costs continue to come in under budget. | 100 | No variance. | 80 | Below Baseline by 20% due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 97 | Above Baseline by 13% due to construction costs being greater than anticipated. | 100 | Above Baseline by 8% due to increased cost of innerduct. | 0 | Below Baseline by 84% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2012-11-15 17:23 | 2012-11-15 17:23 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2012 | Q4 | Q4 - 2012 | 8712 | 7516 | FALSE | 97 | Below Baseline by 2% due to unforeseen fiber availability constraints from manufacturers in 2011, a longer than anticipated EA process, and because many costs have come in lower than anticipated thus far. Sho-Me anticipates it will meet baseline projections by 2nd Quarter 2013. | 81 | Legal, Administrative, Pre- Award Expenses | Below Baseline by 19% due to legal and administrative costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 91 | Below Baseline by 9% due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 92 | Below Baseline by 8% due to fewer engineering hours needed than anticipated. | 38 | Below Baseline by 62% due to lower than anticipated rights of way costs. Sho- Me anticipates this category will remain under budget for the remainder of the project as rights of way costs continue to come in under budget. | 80 | Below Baseline by 20% due to costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project as permitting costs continue to come in under budget. | 100 | No variance. | 87 | Below Baseline by 13% due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 100 | Above Baseline by 3% due to construction costs being greater than anticipated. | 100 | Above Baseline by 3% due to increased cost of innerduct. | 0 | Below Baseline by 97% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2013-02-11 17:04 | 2013-02-11 17:04 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2013 | Q1 | Q1 - 2013 | 9210 | 8040 | FALSE | 100 | No variance. | 78 | Legal, Administrative, Pre- Award Expenses | Below Baseline by 22% due to legal and administrative costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 97 | Below Baseline by 3% due to costs being lower than anticipated. A minimal amount of EA related work is possible in the future, thus the remaining budgeted amount may be expended at a future date. | 94 | Below baseline by 6% due to less engineering hours being needed than expected. | 38 | Below Baseline by 62% due to lower than anticipated rights of way costs. Sho-Me anticipates this category will remain under budget for the remainder of the project as rights of way costs continue to come in under budget. | 80 | Below Baseline by 20% due to costs being lower than anticipated. Sho-Me anticipates this category will remain under budget for the remainder of the project as permitting costs continue to come in under budget. | 100 | No variance. | 91 | Below Baseline by 9% due to lower than anticipated costs relating to DWDM equipment. Sho-Me anticipates this category will remain under budget for the remainder of the project due to lower than anticipated costs. | 100 | No variance. | 100 | No variance. | 0 | Below Baseline by 100% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2013-04-22 13:14 | 2013-04-22 13:14 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2013 | Q2 | Q2 - 2013 | 10252 | 8728 | FALSE | 100 | No variance. | 87 | Legal, Administrative, Pre-Award Expenses | Below Baseline by 13% due to costs being lower than anticipated. Sho-Me does not anticipate any future expenses in this category. | 97 | Below Baseline by 3% due to costs being lower than anticipated. Sho-Me does not anticipate any future expenses in this category. | 94 | Below Baseline by 6% due to costs being lower than anticipated. Sho-Me does not anticipate any future expenses in this category. | 38 | Below Baseline by 62% due to costs being lower than anticipated. Sho-Me does not anticipate any future expenses in this category. | 80 | Below Baseline by 20% due to costs being lower than anticipated. Sho-Me does not anticipate any future expenses in this category. | 100 | No variance. | 96 | Below Baseline by 4% due to costs being lower than anticipated. Sho-Me does not anticipate any future expenses in this category. | 100 | No variance. | 100 | No variance. | 0 | Below Baseline by 100% because these expenses were moved to another category in Sho-Me's approved 2010 budget revision. Sho-Me will not use this baseline category for remainder of the project. | 2013-07-29 17:23 | 2013-07-29 17:23 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | 2013 | Q3 | Q3 - 2013 | 11626 | 9747 | FALSE | 100 | No variance. | 100 | Legal, Administrative,Pre-Award Expenses | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 100 | No variance. | 2014-01-17 16:22 | 2014-01-17 16:22 | 7114 | 7114 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570148 | 2010 | Q4 | Q4 - 2010 | 1210 | 2243 | FALSE | 5 | We projected 30% percent this quarter, based largely on the expenditure for equipment, which was held up with getting the Montana West bank account authorized for drawdown...(which has now happened) We will catch up next quarter, now that we can buy necessary materials and equipment. | 16 | Admin and Match | No Variance | 100 | No Variance..we expect the EA to be done early next quarter. | 0 | No Variance | 37 | We projected to have 54% of the rights of way done by this time. We are encountering complexities related to State Department of Transportation rights of way and easements on the Reservations, which is slowing this process down. We are focusing on the rights of way for the first construction segments so that we can get started on schedule for those parts of the project, and continue on the rest of the rights of way while we are putting installation crews to work. | 10 | We projected to be 16% completed on this by this time...permitting will be slowed down by delays in getting rights of way on the Reservations. | 0 | No Variance | 0 | We projected 94% in the baseline for this quarter, and did not issue RFP's for the equipment until we were assured we have drawdown status for Montana West...we now have that status, and are issuing RFP's for fiber and construction equipment. We will expend these funds in next quarter. | 5 | No Variance | 0 | Projection for this quarter was 12%...this is for the actual build, which was scheduled to start in March. We do not expect to start until next quarter (April) due to delays in the EA and equipment procurement. We will catch up at that time. | 0 | We projected a 12% completion on network testing, however construction startup is being delayed by problems encountered with obtaining rights of way on the Reservations. | 2011-02-17 18:48 | 2011-02-17 18:48 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2011 | Q1 | Q1 - 2011 | 2060 | 2775 | FALSE | 13 | We projected to have 48 percent of the project done based on expenditures by this time. The time to accomplish the EA process has delayed our start date. We now expect to have the EA completed by 11Q2 and to start at the end of 11Q2. | 24 | Admin/Match | No Variance from baseline. | 100 | We expect to have the EA done in 11Q2. | 100 | No Variance from baseline. | 40 | We are working with State and local authorities for rights of way on those portions of State and County roadway rights of way that are not on reservations. We still have challenges obtaining rights of way on the reservations, particularly on the Blackfeet. Planned construction effort is shifting from the Blackfeet reservation to the Flathead reservation in order to focus on areas where we can obtain timely rights of way, while still working with the BIA and the Blackfeet Tribal council. | 20 | We are getting some verbal approvals on county roads, prior to permitting, based on obtaining the FONSI. This will get us a head start on the actual permitting process. | 0 | Projected 52% by this time....This is for preparation for the wireless delivery part of our project, which has been rescheduled later as a result of the overall EA delay. | 95 | No Variance from baseline. | 10 | Projected 37% by this time. We expect to start in June after the FONSI is obtained. | 10 | Projected 26% by this time. We expect to start at the end of 11Q2 after the FONSI is obtained. | 0 | Projected 26% by this time. We expect to start at the end of 11Q2 after the FONSI is obtained. | 2011-05-16 17:46 | 2011-05-16 17:46 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2011 | Q2 | Q2 - 2011 | 3094 | 3304 | FALSE | 54 | Projected 56% | 76 | Admin & Match | Projected 32%--Recording 100% of In Kind Match | 100 | Projected 100%--Fonsi awarded 7/5/11 | 57 | Projected 100%--We plan to purchase the Juniper equipment first and hold off on the Cisco and Occam equipment for a few months. | 60 | Projected 100%--Negotiating with the Blackfeet Tribe | 32 | Projected 32%--No Variance | 0 | Projected 64%--delayed by the EA | 54 | Projected 96%--We are holding off on additional equipment for the Blackfeet route until the Right of Way issues are closer to resolution. | 37 | Projected 45%--We lost a full quarter of construction due to the delay with the EA. | 26 | Projected 41%--We lost a full quarter of construction due to the delay with the EA. | 26 | Projected 41%--We lost a full quarter of construction due to the delay with the EA. | 2011-08-15 17:03 | 2011-08-15 17:03 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2011 | Q3 | Q3 - 2011 | 3918 | 3797 | FALSE | 56 | Projected 63% Put 100% of in Kind Match into the project last quarter. | 78 | Admin & Match | Projected 40%--Put 100% of in Kind Match in project last quarter | 100 | Projected 100% | 85 | Projected 100%--Delays obtaining upstream contracts impacting this item | 55 | Projected 100%-negotiating with the Blackfeet | 25 | Projected 40%--MDOT delays on permitting | 0 | Projected 64%--Overall schedule delays associated with the EA | 54 | Projected 96%--Holding off on some of the equipment until we can start on the Blackfeet Reservation | 46 | Projected 53%--hired a subcontractor to start work on the section from Missoula to Evaro to get us more on schedule. | 32 | Projected 53%--We started late, but are catching up. | 10 | Projected 53%--Lost a full quarter of construction due to the delay with the EA. | 2011-11-07 18:22 | 2011-11-07 18:22 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2011 | Q4 | Q4 - 2011 | 5130 | 4795 | FALSE | 62 | Projected 69%. Late start due to EA. We are in catch-up mode. | 50 | Admin & Legal | Projected 48%-- Audit Expense and Insurance due this quarter | 90 | Projected 100%--Cultural walkthrough taking place on a segmented basis, to allow us to start in parallel with the rest of the walkthrough. We will receive final approval from the Blackfeet Nation when completed. | 100 | Projected 100%--We will purchase all of the Network Hardware | 44 | Projected 100% Still working with the Blackfeet Tribe on Rights of Ways | 80 | Projected 48%--Most of the permits have been obtained. The rest of the project is on State Highway Right of Ways that don't charge for permits. We still need permits on some BIA roadways on the Blackfeet Reservation. | 28 | Projected 64%--The Arlee Building will be completed this quarter and we will start on the other sites in the spring. | 70 | Projected 96%--Will order Wireless Equipment and Radios in the spring. | 39 | Projected 61%--We will purchase the IRU this quarter, once we obtain BTOP approval for our budget realignment. | 62 | Projected 65%. Fiber availability is impacting this parameter. | 0 | Projected 65%--Projected Milestone changed with budget modification. We will perform our own network testing instead of outsourcing this function. None of the wireless equipment has been installed yet and is not ready for testing. | 2012-02-17 18:59 | 2012-02-17 18:59 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2012 | Q1 | Q1 - 2012 | 6100 | 5652 | FALSE | 73 | Projected 82% Construction is going as planned and fiber is here. The Kalispell to Polson section is behind what we had anticipated but will be back on schedule by the end of August. | 52 | Admin and Legal | Projected 58% | 100 | Projected 100% All cultural walk outs will have been completed | 100 | Projected 100% All Electronic Hardware will be purchased | 58 | Projected 58% Engineering will continue as anticipated | 100 | Projected 60% Most of the permits have been obtained | 76 | Projected 76% The main sites will have been completed. Working on tower sites. | 77 | Projected 96% Most of the large equipment needed for the project has been purchased | 54 | Projected 55% Proceeding as anticipated | 77 | Projected 88% We are holding off on the Last Mile deployment for the moment and concentrating on the middle mile | 0 | Projected 22% We are holding off on the Last Mile deployment for the moment and concentrating on the middle mile. | 2012-05-15 14:05 | 2012-05-15 14:05 | 6343 | 6343 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2012 | Q2 | Q2 - 2012 | 7032 | 6143 | FALSE | 79 | Projected 87%..DOT Permitting delays on the Blackfeet Reservation has impacted out schedule. | 60 | Admin & Legal | Projected 66%...delays commensurate with overall project delays. | 100 | Projected 100%...no variance | 100 | Projected 100%...no variance | 80 | Projected 70%...BIA approvals have accelerated the progress for State highways on the reservation. | 100 | Projected 70%...permits are all applied for and waiting approval | 32 | Projected 88%...overall project delays have impacted site preparation | 81 | Projected 98%...some equipment may still be needed on the Blackfeet build | 59 | Projected 68%...Delays on the Blackfeet have contributed to this variance. | 84 | Projected 91% Delayed by permitting issues. | 0 | Projected 38%...final network testing will commence upon completion of the northern route. | 2012-08-10 18:28 | 2012-08-10 18:28 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2012 | Q3 | Q3 - 2012 | 8042 | 6727 | FALSE | 80 | Projected 87%. Work stoppage on the Blackfeet has impacted miles planned for completion. | 72 |  | Projected 72%. No Variance | 95 | Projected 100%. No Variance | 95 | Projected 100%. No Variance | 90 | Projected 100%. Work stoppage on the Blackfeet has impacted miles planned for completion. | 100 | Projected 72%. All construction permits have been obtained | 40 | Projected 88%. Work stoppage on the Blackfeet has impacted miles planned for completion. | 90 | Projected 99%. Some wireless equipment will need to be procured for the remainder of the build on the Blackfeet and other locations. | 65 | Projected 85%. Work stoppage on the Blackfeet has impacted miles planned for completion. | 90 | Projected 90%. No Variance | 50 | Projected 90%. Network testing will have been done on the southern portion of the network. Shortfall due to Blackfeet work stoppages. | 2012-11-26 13:03 | 2012-11-26 13:03 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2012 | Q4 | Q4 - 2012 | 8992 | 7770 | FALSE | 87 | Projected 92%--Work stoppage on the Blackfeet and delays on the northern route are impacting schedule | 76 | Admin & Legal | Projected 80%--As anticipated. Legal fees are high concerning the Glacier county portion of the build. | 95 | Projected 100%--Some EA work still to be completed in Glacier County | 100 | Projected100% | 92 | Projected 100%--Work still to be completed in Glacier County. | 100 | Projected 80% | 67 | Projected 88%--Engineering work on the wireless portion of the project will continue this quarter. | 87 | Projected 99%--Work stoppage on the Blackfeet and delays on the northern route are impacting schedule | 63 | Projected 93%--Work stoppage on the Blackfeet and delays on the northern route are impacting schedule | 93 | Projected 94%--As anticipated | 44 | Projected 94%--Testing work scheduled to start on the southern portion of the project. | 2013-02-26 17:35 | 2013-02-26 17:35 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2013 | Q1 | Q1 - 2013 | 9736 | 8402 | FALSE | 89 | Projected 97%. Work stoppage on the Blackfeet and delays on the northern route have impacted the schedule. | 78 | Admin & Legal | Projected 93% Holding In Kind Labor Match to Fund With Program Income Match | 99 | Projected 100%. EA work still unfinished for the CAI's. | 100 | Projected 100% | 93 | Projected 100%. ROW impacted by the Blackfeet work stoppage. | 100 | Projected 100% | 66 | Projected 100% 3.65 Sites will need site preparation and have been slipped to to overall construction slippage. | 95 | Projected 100% Work stoppage on the Blackfeet and delays on the northern route have impacted the schedule. | 69 | Projected 89% Work stoppage on the Blackfeet and delays on the northern route have impacted the schedule. | 94 | Projected 99% Work stoppage on the Blackfeet and delays on the northern route have impacted the schedule. | 100 | Projected 100% | 2013-05-15 13:58 | 2013-05-15 13:58 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2013 | Q2 | Q2 - 2013 | 10668 | 8995 | FALSE | 91 | Projected 100%. Work stoppage on the Blackfeet and delays on the northern route have impacted the schedule for completion. | 81 | Admin & Legal | Projected 100%. Holding in Kind Labor Match to Fund with Program Income Match. | 99 | Projected 100%..Still working on EA review for the new builds for the CAI's. | 100 | Projected 100% | 96 | Projected 100%. ROW impacted by the Blackfeet work stoppage. | 100 | Projected 100% | 33 | Projected 100%. Most site prep is for the final wireless sites and they are at the end of the project which has slipped due to work stoppage on the Blackfeet | 100 | Projected 100% | 64 | Projected 100%. Work stoppage on the Blackfeet and delays on the northern route have impacted the schedule for completion. | 97 | Projected 100%. Work stoppage on the Blackfeet and delays on the northern route have impacted the schedule for completion. | 100 | Projected 100% | 2013-08-20 19:03 | 2013-08-20 19:03 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2013 | Q3 | Q3 - 2013 | 11306 | 9452 | FALSE | 92 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. After completion of construction on the West side, and microwave to Heart Butte, what will remain is the fiber build to St. Mary/Babb on the Blackfeet Reservation, or the remaining 42 miles. | 88 | Admin & Legal | Projected 100% | 100 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. We are waiting on EA approval on our CAI builds and project modification regarding route changes. | 100 | Projected 100% | 100 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. After completion of construction on the West side, and microwave to Heart Butte, what will remain is the fiber build to St. Mary/Babb on the Blackfeet Reservation, or the remaining 42 miles, for which we will need to obtain rights of way. (14% of the miles of the project) | 100 | Projected 100% | 100 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. The only site prep left is the wireless sites. We have installed two (Arlee and Elmo/Big Arm) of the five wireless sites with three left. (Evaro, Heart Butte and St. Mary) | 100 | Projected 100% | 63 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. After completion of construction on the West side, and microwave to Heart Butte, what will remain is the fiber build to St. Mary/Babb on the Blackfeet Reservation, or the remaining 42 miles. | 97 | Projected 100% | 100 | Projected 100%. Our project slipped due to contractor delays, and Difficulties in obtaining rights of way has impacted the project schedule.. We have been granted another year to finish. After completion of construction on the West side, and microwave to Heart Butte, what will remain is the fiber build to St. Mary/Babb on the Blackfeet Reservation, or the remaining 42 miles, which when done, will need network testing. (14% of the miles of the network) | 2013-11-20 12:02 | 2013-11-20 12:02 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | 2013 | Q4 | Q4 - 2013 | 11934 | 10102 | FALSE | 95 | Projected 100. All that remains is to complete the builds on the Blackfeet and build to the CAI's. We are on track to complete within the one-year extension. | 94 | Admin and Legal | Projected 100. We still have some costs in this activity, due to the one year extension we were granted and work that remains on the Blackfeet. | 100 | Projected 100 | 100 | Projected 100 | 100 | Projected 100 | 100 | Projected 100 | 50 | Projected 100. Actual is 38%--this is Wireless Site Prep. Overall project slippage has impacted this schedule. Site prep will be required for the remaining wireless sites...Evaro, Heart Butte, and St. Mary/Babb. | 100 | Projected 100 | 94 | Projected 100. Project slippage due to rights of way and work stoppage by the Blackfeet. All that remains is microwave to Heart Butte and a 43 mile fiber build on the Blackfeet | 99 | Projected 100 | 100 | Projected 100 | 2014-03-06 18:47 | 2014-03-06 18:47 | 6091 | 6091 | Ronan Telephone Co. | TRUE
NT10BIX5570150 | 2010 | Q4 | Q4 - 2010 | 554 | 1573 | FALSE | 5 | Zero variance | 50 | Professional Services, Fiber route valadation | Zero variance | 100 | Zero variance | 75 | Zero variance | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 2011-01-26 15:35 | 2011-01-26 15:35 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2011 | Q1 | Q1 - 2011 | 1666 | 2554 | FALSE | 25 | Later than anticipated receipt of FONSI (40+ days) will delay starting of deployment activities. It is anticipated that these delays will be compensated for over the next 2 quarters and the project back on schedule prior to close of 3Q2011. | 45 | Professional Services, Fiber Route validation | Later than anticipated receipt of FONSI (40+ days) will delay starting of deployment activities. It is anticipated that these delays will be compensated for over the next 2 quarters and the project back on schedule prior to close of 3Q2011. | 100 | Zero Variance | 100 | Zero Varience | 0 | N/A | 0 | N/A | 0 | N/A | 31 | Equipment procurement will be ahead of schedule due to available match funds and desire to insure adequate equipment is on hand to meet deployment scheduling | 21 | Later than anticipated receipt of FONSI (40+ days) will delay starting of deployment activities. It is anticipated that these delays will be compensated for over the next 2 quarters and the project back on schedule prior to close of 3Q2011. | 5 | Later than anticipated receipt of FONSI (40+ days) will delay starting of deployment activities. It is anticipated that these delays will be compensated for over the next 2 quarters and the project back on schedule prior to close of 3Q2011. | 5 | Later than anticipated receipt of FONSI (40+ days) will delay starting of deployment activities. It is anticipated that these delays will be compensated for over the next 2 quarters and the project on schedule prior to close of 3Q2011. | 2011-04-29 13:35 | 2011-04-29 13:35 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2011 | Q2 | Q2 - 2011 | 2920 | 3217 | FALSE | 32 | Later than anticipated receipt of FONSI has delayed deployment activities. Project anticipates being back on schedule by end of Q1-2012 | 45 | Professional Services | Later than anticipated receipt of FONSI has delayed deployment activities. Project anticipates being back on schedule by end of Q1-2012 | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 38 | Later than anticipated receipt of FONSI has delayed deployment activities. Project anticipates being back on schedule by end of Q1-2012 | 30 | Later than anticipated receipt of FONSI has delayed deployment activities. Project anticipates being back on schedule by end of Q1-2012 | 15 | Later than anticipated receipt of FONSI has delayed deployment activities. Project anticipates being back on schedule by end of Q1-2012 | 15 | Later than anticipated receipt of FONSI has delayed deployment activities. Project anticipates being back on schedule by end of Q1-2012 | 2011-08-04 08:03 | 2011-08-04 08:03 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2011 | Q3 | Q3 - 2011 | 3958 | 3817 | FALSE | 41 | Later than anticipated start of deployment reduced number of projected POI completed this quarter | 12 | Professional Services, Fiber Route validation | On schedule | 100 | Zero Variance from plan | 100 | Zero Variance from plan | 0 | N/A | 0 | N/A | 0 | N/A | 44 | Later than anticipated start of deployment reduced equipment expenditure requirements | 43 | On Schedule | 30 | Later than anticipated start of deployment reduced number of projected POI completed this quarter | 30 | Later than anticipated start of deployment reduced number of projected POI completed this quarter | 2011-11-10 12:33 | 2011-11-10 12:33 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2011 | Q4 | Q4 - 2011 | 4662 | 4303 | FALSE | 56 | Later than anticipated start of fiber deployment due to delayed FONSI receipt resulted in overall expenditures being less than projected. Additionally, vendor invoice timing reduced total expenditures for this quarter. | 21 |  | Later than anticipated deployment of equipment delayed expenditures in this category. | 100 | Zero variance | 100 | Zero variance | 0 | N/A | 0 | N/A | 0 | N/A | 67 | Ahead of schedule | 54 | On schedule | 45 | Later than anticipated start of deployment reduced the number of total projected POI for this quarter | 45 | Later than anticipated start of deployment reduced the number of total projected POI for this quarter | 2012-01-30 12:56 | 2012-01-30 12:56 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2012 | Q1 | Q1 - 2012 | 6018 | 5608 | FALSE | 68 | Slightly behind planned schedule. Later than anticipated start of project due to initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 35 |  | Slightly behind planned schedule. Later than anticipated start of project due to initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 83 | Ahead of schedule | 63 | Physical build will be slightly ahead of schedule but vendor invoice timing and payments will likely reduced reported expenditures | 65 | Slightly behind planned schedule. Later than anticipated start of project due to initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 65 | Slightly behind planned schedule. Later than anticipated start of project due to initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 2012-05-10 14:27 | 2012-05-10 14:27 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2012 | Q2 | Q2 - 2012 | 6878 | 6065 | FALSE | 77 | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 46 |  | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 100 | Zero variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 85 | Ahead of schedule | 76 | Physical build will be slightly ahead of schedule but vendor invoice timing and payments will likely reduced reported expenditures | 76 | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 76 | Slightly behind planned schedule. Later than anticipated start of project due to delayed initial FONSI receipt and longer than anticipated installation coordination times has reduced the overall completion of sites from original baseline. Additionally, vendor invoice timing reduces planned expenditures verses physical completion. It is anticipated that this schedule variance from the baseline will gradually be reduced over the next 2 quarters and will be fully mitigated by the end of Q4-2012. | 2012-08-07 08:37 | 2012-08-07 08:37 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2012 | Q3 | Q3 - 2012 | 7906 | 6657 | FALSE | 85 | Zero Variance | 64 |  | Slightly behind schedule. This milestone category includes ongoing project management activities and professional services activities (equipment installations, site surveys, site mitigation activities). Because of invoice timing and acceptance verifications, expenditures are delayed. It is anticipated that this milestone will continue to lag behind schedule until Q2-2013. | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 83 | Zero Variance | 88 | Slightly ahead of schedule | 86 | Slightly ahead of schedule | 86 | Slightly ahead of schedule | 2012-11-15 17:06 | 2012-11-15 17:06 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2012 | Q4 | Q4 - 2012 | 9140 | 7940 | FALSE | 93 | Zero Variance | 64 |  | Slightly behind schedule. This milestone category includes ongoing project management activities and professional services activities (equipment installations, site surveys, site mitigation activities). Because of invoice timing and acceptance verifications, expenditures are delayed. It is anticipated that this milestone will continue to lag behind schedule until Q2-2013. | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/A | 97 | Slightly ahead of schedule | 95 | Slightly ahead of schedule | 93 | Slightly ahead of schedule | 93 | Slightly ahead of schedule | 2013-03-15 10:16 | 2013-03-15 10:16 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2013 | Q1 | Q1 - 2013 | 9328 | 8120 | FALSE | 99 | On schedule | 93 | Professional Services | On schedule | 100 | Zero variance | 100 | Zero variance | 0 | N/A | 0 | N/A | 0 | N/A | 100 | On schedule | 100 | On schedule | 99 | On schedule | 99 | On schedule | 2013-04-28 20:41 | 2013-04-28 20:41 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2013 | Q2 | Q2 - 2013 | 10304 | 8769 | FALSE | 100 | Zero Variance | 100 | Professional Services | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 0 | N/A | 0 | N/A | 0 | N/a | 100 | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 100 | Zero Variance | 2013-07-30 11:27 | 2013-07-30 11:27 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | 2013 | Q3 | Q3 - 2013 | 11642 | 9767 | FALSE | 100 | Zero variance - grant in close-out | 100 | Professional services | Zero variance - grant in close-out | 100 | Zero variance - grant in close-out | 100 | Zero variance - grant in close-out | 0 | N/A | 0 | N/A | 0 | N/A | 100 | Zero variance - grant in close-out | 100 | Zero variance - grant in close-out | 100 | Zero variance -grant in close-out | 100 | Zero variance - grant in close-out | 2014-01-23 07:32 | 2014-01-23 07:32 | 6528 | 6528 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570153 | 2010 | Q4 | Q4 - 2010 | 734 | 1766 | FALSE | 17 | Detail Below | 50 |  | Reimbursement for Eligible Pre-Award Expenses | 0 | N/A | 61 | Hire Field Project Engineer, Field Project Manager, Traffic Systems Management Contractor. Complete Node and Community Anchor Institution Design | 0 | N/A | 0 | N/A | 3 | Begin Site Prep for 4 Massachusetts Nodes | 32 | Receive 10G Network Upgrade Equipment, Issue RFP for Optical Equipment | 42 | Hire Project Manager, Execute IRU with Fiber Vendors; Provide First Payment, Begin Contract Negotiations with Community Anchor Institutions | 25 | Configure and Install 10G Network Upgrade Equipment | 0 | N/A | 2011-01-28 13:17 | 2011-01-28 13:17 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2011 | Q1 | Q1 - 2011 | 2288 | 2889 | FALSE | 25 | See Below. | 21 |  | Limited activity anticipated | 0 | N/A | 77 | Network Design efforts will continue for the additional Community Anchor Institutions. No significant impact on the project time line is anticipated. | 0 | N/A | 0 | N/A | 4 | Site Preparation efforts will continue. However, few associated expenses are anticipated in the next quarter. | 6 | Optical Equipment will be ordered during this quarter, but no payments are scheduled. Payment will be made in 2011 Q3 | 33 | Because of the 20% advance payment and 40% Providence County, RI segment payment, no significant network build expenditure is expected. However, both backbone fiber and CAI lateral installation and will commence in Providence County, RI. 45 backbone miles and 5 CAI sites are projected for completion. | 5 | Optical equipment will be ordered, but no significant deployment is scheduled. | 0 | No Activity. | 2011-05-24 17:41 | 2011-05-24 17:41 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2011 | Q2 | Q2 - 2011 | 3282 | 3403 | FALSE | 31 | See below. | 46 |  | The OMB Circular A-133 audit will occur during this quarter. Community Outreach efforts will continue. | 0 | N/A | 100 | Networkdesign efforts are scheduled for completion. | 0 | N/A | 0 | N/A | 15 | Site preparation for optical node sites is expected to be complete by September 30, 2011. | 51 | OSHEAN will place the order for the Optical Equipment required for Beacon 2.0. Phase I order will include the Optical Node Equipment; Phase II order will include the CAI equipment. | 32 | Because of the IRU payment structure, few payments are scheduled. However, Cox Communications is expected to deploy 100 miles of backbone fiber and commence CAI lateral installations. These efforts remain in line with the overall project plan. | 5 | Deployment of Optical equipment is not expected during this quarter. | 0 | Network testing is not expected during this quarter. | 2011-08-23 16:38 | 2011-08-23 16:38 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2011 | Q3 | Q3 - 2011 | 4232 | 3964 | FALSE | 51 | See Below | 52 |  | No major change from baseline | 0 | N/A | 100 | Network design efforts are scheduled for completion, except for CAI change orders. | 0 | N/A | 0 | N/A | 15 | Site Prep efforts will be complete; total funds expended will be below baseline budget. | 94 | OSHEAN will continue to receive and verify Phase I DWDM optical equipment, and place order for Phase II CPT 50 optical equipment. | 55 | Because of the IRU payment structure, few payments are scheduled. However, Cox Communications is expected to have deployed approximately 200 total miles of backbone fiber and commence CAI lateral installations. These efforts remain in line with the overall project plan. | 100 | Actual % = 179% Because of an alternate valuation of equipment deployment, over 100% of the baseline projected funds will have been expended. However, actual deployment efforts are only approximated at 15% completion. | 14 | Testing of the Providence County IRU fiber is scheduled. | 2011-11-22 16:21 | 2011-11-22 16:21 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2011 | Q4 | Q4 - 2011 | 4948 | 4627 | FALSE | 60 | See Below. | 56 |  | No major change from baseline. | 0 | N/A | 100 | The core network design for Beacon 2.0 is complete. The only foreseen need for further network design efforts result from any required Change Orders for Community Anchor Institution laterals. | 0 | N/A | 0 | N/A | 15 | All Site Prep requirements are expected to be completed. Preparation efforts are projected to be under budget overall. | 100 | All optical equipment is expected to be ordered and delivered during this quarter. | 59 | Kent County, RI fiber totalling 72 miles is expected to be tested and accepted by OSHEAN. Cox is scheduled to begin the 78 mile build in Washington County, RI. Sidera is scheduled to begin pulling fiber in Bristol and Plymouth Counties, MA. OSHEAN expects 15 Community Anchor Institution laterals to be installed during this quarter. | 100 | Cisco 15454 optical equipment will be installed at the optical node locations. | 25 | The Kent County, RI backbone fiber will be tested. | 2012-02-10 14:39 | 2012-02-10 14:39 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2012 | Q1 | Q1 - 2012 | 6252 | 5728 | FALSE | 67 | Total percent complete is in line with the 68% projected in the baseline. | 60 |  | No major change from baseline | 0 | N/A | 100 | The core network design for Beacon 2.0 is complete. | 0 | N/A | 0 | N/A | 100 | All site prep efforts are scheduled for completion | 100 | All equipment is expected to be ordered. | 71 | No major change from baseline | 100 | Cisco 15454 node equipment is scheduled for deployment; OSHEAN will begin the deployment of CAI CPT 50 equipment. | 31 | No major change from baseline | 2012-05-22 15:28 | 2012-05-22 15:28 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2012 | Q2 | Q2 - 2012 | 7142 | 6198 | FALSE | 72 | Per the baseline, the project is behind the 83% projection due to a modification request pending. This variance will have minimal impact on the overall project time line | 73 |  | While the percent complete is below that projected in the baseline, efforts are still consistent with key milestones. | 0 | N/A | 100 | The core network design for Beacon 2.0 is complete. | 0 | N/A | 0 | N/A | 100 | All site preparation efforts are scheduled for completion | 100 | All equipment is expected to be ordered | 87 | Per the baseline, the project is ahead of 81% projection due to ahead of schedule installation efforts | 100 | Installation of CAI optical equipment shall continue | 27 | Network Testing efforts are expected to be under budget. | 2012-08-20 07:50 | 2012-08-20 07:50 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2012 | Q3 | Q3 - 2012 | 8028 | 6720 | FALSE | 86 | Per the baseline, the project is behind the 97% projection due to a modification request pending. This variance will have minimal impact on the overall project time line. | 79 |  | While the percent complete is below that projected in the baseline, efforts are still consistent with key milestones. | 0 | N/A | 100 | The core network design is complete | 0 | N/A | 0 | N/A | 45 | Site Preparation efforts are under budget, but projected to be complete by 12/31/12. | 100 | All equipment is expected to be ordered | 76 | Network build expenses are under budget, but the work performed is consistent with the 94% completion indicated in the baseline. | 100 | Equipment deployment efforts are greater than budget, and shall continue for the installation of CAI optical equipment | 43 | Network testing efforts are projected to be under budget. | 2012-11-26 09:50 | 2012-11-26 09:50 | 6375 | 6375 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2012 | Q4 | Q4 - 2012 | 9040 | 7809 | FALSE | 92 | Baseline = 99% complete. Variance due to slight project delay from a pending route modification request. The route modification was approved in December, 2012. This variance will have minimal impact on the overall project time line. | 75 |  | While the percent complete is below that projected in the baseline, efforts are still consistent with key milestones. | 0 | N/A | 100 | The core network design is complete | 0 | N/A | 0 | N/A | 41 | Site Preparation efforts are under budget, but projected to be complete by January, 2013. | 100 | All equipment is expected to be ordered | 98 | Projected completion is only 1% below the baseline. This variance will have little impact on the overall project. | 100 | Equipment deployment efforts are greater than budget, and shall continue for the installation of CAI optical equipment | 50 | Network testing efforts are projected to be under budget. | 2013-02-27 16:53 | 2013-02-27 16:53 | 7671 | 7671 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2013 | Q1 | Q1 - 2013 | 9738 | 8403 | FALSE | 97 | Baseline = 100% complete. Variance due to slight project delay from a pending route modification request. The route modification was approved in December, 2012. This variance will have minimal impact on the overall project time line. | 72 |  | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. Efforts are consistent with key milestones, and are projected to be under budget. | 0 | N/A | 100 | The core network design is complete. | 0 | N/A | 0 | N/A | 97 | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. | 100 | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. | 99 | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. | 100 | Actual % expected to be 103%. Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. Equipment deployment is greater than budget due to implementation delays pending the post award modification approval, but will not impact the overall project budget. | 93 | Change in reported percentage from Q4 2012 PPR due to recently approved post award modification budget. Network testing efforts are projected to be under budget. | 2013-05-15 14:15 | 2013-05-15 14:15 | 7671 | 7671 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2013 | Q2 | Q2 - 2013 | 10492 | 8897 | FALSE | 100 | Project will be complete and final budget generated for closeout. | 100 |  | Project will be complete and final budget generated for closeout. | 0 | N/A | 100 | Project will be complete and final budget generated for closeout. | 0 | N/A | 0 | N/A | 100 | Project will be complete and final budget generated for closeout. | 100 | Project will be complete and final budget generated for closeout. | 100 | Project will be complete and final budget generated for closeout. | 100 | Project will be complete and final budget generated for closeout. | 100 | Project will be complete and final budget generated for closeout. | 2013-08-06 12:28 | 2013-08-06 12:28 | 7671 | 7671 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | 2013 | Q3 | Q3 - 2013 | 11594 | 9724 | FALSE | 100 | All project documentation and final budget submitted for closeout. | 100 |  | All project documentation and final budget submitted for closeout. | 0 | N/A | 100 | All project documentation and final budget submitted for closeout. | 0 | N/A | 0 | N/A | 100 | All project documentation and final budget submitted for closeout. | 100 | All project documentation and final budget submitted for closeout. | 100 | All project documentation and final budget submitted for closeout. | 100 | All project documentation and final budget submitted for closeout. | 100 | All project documentation and final budget submitted for closeout. | 2014-01-13 16:53 | 2014-01-13 16:53 | 7671 | 7671 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570156 | 2010 | Q4 | Q4 - 2010 | 1382 | 2394 | FALSE | 6 | Due to the previously described delays with the Grantee Substitution process, most project tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 14%. | 5 |  | Due to the previously described delays with the Grantee Substitution process, most Other miscellaneous tasks such as compliance reporting systems and warehouse staging will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 13%. | 50 | Due to the previously described delays with the Grantee Substitution process, most Environmental Assessment tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 100%. | 43 | Due to the previously described delays with the Grantee Substitution process, most Network Design tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 86%. | 0 | This is consistent with the baseline report. | 0 | This is consistent with the baseline report. | 13 | Due to the previously described delays with the Grantee Substitution process, most Site Preparation tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 23%. | 9 | Due to the previously described delays with the Grantee Substitution process, most Equipment Procurement tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 18%. | 5 | Due to the previously described delays with the Grantee Substitution process, most Network Build tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 13%. | 7 | Due to the previously described delays with the Grantee Substitution process, most Equipment Deployment tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 16%. | 3 | Due to the previously described delays with the Grantee Substitution process, most Network Testing tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 9%. | 2011-02-27 16:40 | 2011-02-27 16:40 | 6346 | 6346 | Centennial Board of Cooperative Educational Services | TRUE
NT10BIX5570156 | 2011 | Q1 | Q1 - 2011 | 3886 | 3781 | FALSE | 6 | Due to the previously described delays with the Grantee Substitution process, most project tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 14%. | 5 |  | Due to the previously described delays with the Grantee Substitution process, most Other miscellaneous tasks such as compliance reporting systems and warehouse staging will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 13%. | 50 | Due to the previously described delays with the Grantee Substitution process, most Environmental Assessment tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 100%. | 43 | Due to the previously described delays with the Grantee Substitution process, most Network Design tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 86%. | 0 | This is consistent with the baseline report. | 0 | This is consistent with the baseline report. | 13 | Due to the previously described delays with the Grantee Substitution process, most Site Preparation tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 23%. | 9 | Due to the previously described delays with the Grantee Substitution process, most Equipment Procurement tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 18%. | 5 | Due to the previously described delays with the Grantee Substitution process, most Network Build tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 13%. | 7 | Due to the previously described delays with the Grantee Substitution process, most Equipment Deployment tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 16%. | 3 | Due to the previously described delays with the Grantee Substitution process, most Network Testing tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 9%. | 2011-11-01 17:50 | 2011-11-01 17:50 | 6346 | 6346 | Centennial Board of Cooperative Educational Services | TRUE
NT10BIX5570157 | 2010 | Q4 | Q4 - 2010 | 954 | 1999 | FALSE | 5 | N/A | 0 |  | N/A | 100 | N/A | 40 | N/A | 50 | N/A | 80 | N/A | 0 | N/A | 10 | N/A | 10 | N/A | 10 | N/A | 0 | N/A | 2011-02-01 11:24 | 2011-02-01 11:24 | 6432 | 6432 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2011 | Q1 | Q1 - 2011 | 1612 | 2527 | FALSE | 10 | N/A | 0 |  | N/A | 100 | N/A | 60 | N/A | 100 | N/A | 100 | N/A | 30 | N/A | 30 | N/A | 15 | N/A | 15 | N/A | 0 | N/A | 2011-04-28 18:36 | 2011-04-28 18:36 | 6432 | 6432 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2011 | Q2 | Q2 - 2011 | 3062 | 3288 | FALSE | 22 | No Variance | 0 | N/A | No Variance | 100 | No Variance | 80 | No Variance | 70 | Due to changes in the system configuration there were delays in obtaining the Rights of Way (ROW). Now that the design is finalized we will ensure all ROW's are completed. | 80 | Due to changes in site location we were delayed in obtaining all permits. Now that the sites have been finalized we are actively working on all permitting and expect to have all secured by the time site development begins. | 33 | Due to the delays in the EA process and the final site installation schedule the schedule for preparing sites may be adjusted. The overall preparation and installation of sites will remain on schedule. | 31 | With the extended time to finalize the contract for LTE equipment and services the overall procurement will be pushed back, however, we expect to be on schedule by the next reporting period. | 7 | Due to delays in the EA we were not able to begin fiber development when planned. We are currently working on the required RFP's and will have all fiber operational by the time the sites are developed. | 20 | The delays in the LTE contract and EA have caused some delay in deployment. We expect this element to be back on schedule by the next reporting period. | 0 | No Variance | 2011-08-12 16:22 | 2011-08-12 16:22 | 6432 | 6432 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2011 | Q3 | Q3 - 2011 | 4050 | 3868 | FALSE | 40 | No Variance | 0 | true | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 90 | Due to election cycles within local governments we may experience some delay in getting zoning/approval permits completed. | 60 | While we continue to make-up time lost awaiting the FONSI it may take us one more reporting period to be back on schedule. We are currently under contract for renovations at the Cherokee/West tower site and work will begin soon. We have accomplished approximately 70% of the required renovations at the ADCOM 911 facility and have all UPS and generators ordered. The primary site work remaining will be any installation work required (electrical, pads, etc.) for the eNodeB installations which will be performed during the site implementation. | 29 | Procurement is actually on schedule based on revised budget. | 25 | A majority of the network build, eNodeB installations will take place in the Spring/Summer of 2012. | 25 | A majority of fiber-optic equipment for existing fiber will be in place. As stated earlier, a majority of eNodeB installations will take place in Spring/Summer of 2012. | 10 | No Variance | 2011-11-15 17:16 | 2011-11-15 17:16 | 6432 | 6432 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2011 | Q4 | Q4 - 2011 | 5002 | 4676 | FALSE | 60 | No Variance | 0 | N/A | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 95 | Timing is dependant on route modification. All permits may be obtained by the end of March. | 75 | We anticipate all major site work will be completed. The only remaining work will be the specific electrical and mounting work at each site as the eNodeB's are mounted. | 54 | We expect to begin receiving the eNodeB's in March and anticipate a majority of all equipment will be on hand by the end of the quarter. Again, based on contract parameters the financial outlays will not exactly correspond to equipment receipt. | 30 | We anticipate having a majority of the fiber live with the exception of our final run to the Cherokee site and the 6th avenue path. | 25 | As a majority of the remaining equipment is tied to the eNodeB sites the deployment schedule will be concentrated during the 2nd and 3rd quarters of 2012. | 15 | While we can being to test specific elements, the overall testing of the network cannot take place until the eNodeB sites begin to be installed. We anticipate the testing process to increase towards the end of the 2nd quarter of 2012 and ramp up from there. | 2012-02-14 15:37 | 2012-02-14 15:37 | 6432 | 6432 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2012 | Q1 | Q1 - 2012 | 6352 | 5778 | FALSE | 73 | No Variance | 0 | N/A | N/A | 100 | No Variance | 100 | No Variance | 100 | No Variance | 100 | No Variance | 85 | We anticipate all major site work will be completed. The only remaining work will be the specific electrical and mounting work at each site as the eNodeB's are mounted. | 80 | This is base on our original schedule. Any modifications by the NTIA will affect this schedule. | 50 | This is base on our original schedule. Any modifications by the NTIA will affect this schedule. | 50 | This is base on our original schedule. Any modifications by the NTIA will affect this schedule. | 35 | ADCOM 911 has begun testing specific elements of the broadband network. The LTE network has been tested in a limited fashion using the ENodeB located at the ADCOM 911 facility. The overall testing of the network will continue as the eNodeB sites are installed. Additional testing to start in Q2 of 2012. | 2012-05-30 14:19 | 2012-05-30 14:19 | 7504 | 7504 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2012 | Q2 | Q2 - 2012 | 7020 | 6137 | FALSE | 58 | At least one additional CAI link will either be deployed or activated. Some CAI locations are preparing facilities to house the broadband equipment. If their work is completed in the next quarter, then their links can be activated as well. | 0 |  | N/A | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 55 | Additional site work will be performed for each new CAI link activated, and for any intermediary transport connections that are activated. Some site work performed in the previous quarters took longer, or required more work, than originally anticipated. Therefore, this number is lower than previously reported. If the project plan is re-scoped, the number will need to be adjusted again. | 85 | All of the LTE specific equipment was purchased prior to the suspension notice. A vast majority of that has been received on site today and is currently housed in a roll-off storage unit. Additional network equipment will be purchased to provide links for additional broadband network connectivity. | 55 | At least one additional CAI link will be activated in the coming quarter. At least one more intermediary transport connection will be activated in the coming quarter. If the project is re-scoped, it will require additional network build efforts, and will vary this number. | 55 | At least one additional CAI link will be activated in the coming quarter. At least one more intermediary transport connection will be activated in the coming quarter. If the project is re-scoped, it will require additional network build efforts, and will vary this number. | 25 | At least one additional CAI link will be activated in the coming quarter. At least one more intermediary transport connection will be activated in the coming quarter. These links will be tested before they are placed into production availability. No new LTE site equipment will be tested unless the partial suspension is lifted. | 2012-08-10 16:43 | 2012-08-10 16:43 | 7504 | 7504 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2012 | Q3 | Q3 - 2012 | 7316 | 6287 | FALSE | 62 | At least 4 additional sites will have microwave links upgraded or installed, and the network equipment for each will be installed and configured. This will allow each to serve as an interconnection point back to the overall fiber transport network. | 0 | true | N/A | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 60 | We anticipate the site improvement work will be completed at the Cherokee site, allowing us to install and configure additional networking equipment. Construction should begin at the Fire Station 54 monopole tower site. Additional microwave links may be installed to more of the remote sites. | 80 | All of the LTE specific equipment was purchased prior to the suspension notice. A vast majority of that has been received on site today and is currently housed in a roll-off storage unit. We anticipate we will need to purchase additional network transport equipment whether we move forward with LTE or with a Broadband Network only. However, we won't know which equipment until we are advised whether LTE will move forward or not. | 55 | At least four more intermediary transport connections will be activated in the coming quarter. If the project is re-scoped, it will require additional network build efforts, and will vary this number. | 45 | At least one additional microwave link and three additional network switches will be deployed to activate 4 microwave transport paths. | 35 | At least 4 additional interconnection points will be activated. At that time, additional testing will be performed to verify the links will transport end-user data. | 2012-10-04 13:27 | 2012-10-04 13:27 | 7504 | 7504 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2012 | Q4 | Q4 - 2012 | 8684 | 7498 | FALSE | 70 | At least 4 more sites should have network equipment deployed to use with the microwave links already installed. This will allow each to serve as an interconnection point back to the overall fiber transport network. The new fiber connection being installed to Jefferson County should be completed to the Denver network. Once the links are tested along each, we should have fiber connectivity from ADCOM911 to the City of Denver, and then to Jefferson County. | 0 |  | N/A | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 65 | We anticipate the construction of the monopole at Fire Station 54 will be completed, and remodel work at the Cherokee site should be completed. | 81 | Some additional network equipment may need to be purchased to activate some of the fiber links being installed. Otherwise, no additional equipment will be purchased until we know if LTE will proceed or we need to re-purpose the grant. | 70 | At least 4 more sites should become active with the deployment of network equipment. If the final work related to the Jefferson County link is completed, a substantial portion of the fiber network will be completed. | 45 | The network equipment required to activate the 4 additional microwave sites should be deployed. | 50 | If the Jefferson County link is completed, a substantial portion of the fiber network will be completed and can be tested. The additional microwave links will also be tested before being activated. | 2013-02-08 16:54 | 2013-02-08 16:54 | 7504 | 7504 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2013 | Q1 | Q1 - 2013 | 9668 | 8366 | FALSE | 71 | At least 4 more sites should have network equipment deployed to use with the microwave links already installed. This will allow each to serve as an interconnection point back to the overall fiber transport network. The new fiber connection being installed to Jefferson County should be completed to the Denver network. Once the links are tested along each, we should have fiber connectivity from ADCOM911 to the City of Denver, and then to Jefferson County. | 0 |  | N/A | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 100 | No Variance, unless the project plan is re-scoped. | 67 | We anticipate going under contract for services to provide security equipment at 3 key sites. | 82 | We anticipate the purchase of new security cameras, and site access equipment to deploy to 3 key sites. Otherwise, no additional equipment will be purchased until we know if LTE will proceed or we need to re-purpose the grant. | 75 | We anticipate the completion of the fiber into our Cherokee site. We are hopeful that we can finalize the links between 2 additional CAI's. We also anticipate the completion of the splicing and terminations for the Jefferson County, Denver, Adcom fiber connection. | 50 | We anticipate placing equipment at the 2 additional CAI's. | 50 | If the Jefferson County link is completed, a substantial portion of the fiber network will be completed and can be tested. The additional microwave links will also be tested before being activated. | 2013-05-09 15:12 | 2013-05-09 15:12 | 7688 | 7688 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2013 | Q2 | Q2 - 2013 | 10258 | 8738 | FALSE | 71 | At least 4 more sites should have network equipment deployed to use with the microwave links already installed. This will allow each to serve as an interconnection point back to the overall fiber transport network. The new fiber connection being installed to Jefferson County should be completed to the Denver network. Once the links are tested along each, we should have fiber connectivity from ADCOM911 to the City of Denver, and then to Jefferson County. | 0 |  | N/A | 100 | No variance unless the grant is modified. | 100 | No variance unless the grant is modified. | 100 | No variance unless the grant is modified. | 100 | No variance unless the grant is modified. | 70 | We anticipate we will have awarded the contract to install security equipment at 3 key sites. Additional electrical work should be completed at additional sites that will house microwave and network equipment. | 85 | We anticipate the purchase of new security cameras, and site access equipment to deploy to 3 key sites. We also plan to purchase and deploy new core network switches which are used to interconnect the CAI locations to the server applications housed at ADCOM911. Otherwise, no additional equipment will be purchased unless we modify the grant. | 75 | We anticipate the completion of the fiber into our Cherokee site. We are hopeful that we can finalize the links with one additional CAI. We also anticipate the completion of the splicing and terminations for the Jefferson County, Denver, Adcom fiber connection. | 50 | We anticipate deployment of equipment at 1 additional CAI. We anticipate installation and activation of at least 3 microwave links to continue the broadband buildout. | 50 | If the Jefferson County link is completed, a substantial portion of the fiber network will be completed and can be tested. The additional microwave links will also be tested before being activated. | 2013-07-29 19:02 | 2013-07-29 19:02 | 7504 | 7504 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2013 | Q3 | Q3 - 2013 | 10918 | 9162 | FALSE | 72 | We anticipate completion of the administrative tasks associated with the grant extension. This includes the formulation of a revised budget, and a route modification. Assuming a timely acceptance of these documents, we anticipate beginning the process of vendor selection to complete portions of the broadband network build out. | 0 |  | N/A | 100 | We anticipate one additional EA, or a modification to our existing EA based upon our plans for network expansion. This additional EA is predicated upon the acceptance of ADCOM911's route modification. | 100 | We anticipate additional network design activities to take place based upon the assumption of acceptance of ADCOM911's route modification. | 100 | We anticipate some additional Rights of Way for fiber optic development based upon the assumption of acceptance of ADCOM911's route modification. | 100 | We anticipate some additional Construction Permits for fiber optic development based upon the assumption of acceptance of ADCOM911's route modification. | 75 | We anticipate Site Preparation work to take place during the 4th quarter of 2013 once ADCOM911 awards a contract for site security measures, for which we have already obtained competative bids. | 82 | We do not anticipate significant equipment procurement during the 4th quarter of 2013, as much of the planned work will focus on achieving approval for the route modification, and the procurement of competitive bids to complete equipment purchases. | 75 | We have resolved the easement issues with the City of Northglenn related to the Cherokee Site fiber, and anticipate this work to be completed during the 4th quarter of 2013. We also anticipate the completion of the splicing and terminations for the Jefferson County, Denver, Adcom fiber connection. | 50 | We do not anticipate significant equipment deployment during the 4th quarter of 2013, as much of the planned work will focus on achieving approval for the route modification, and the procurement of competitive bids to complete equipment purchases. | 60 | If the Jefferson County link and the Cherokee Site fiber work is completed, a substantial portion of the fiber network will be completed and can be tested. | 2013-10-23 16:29 | 2013-10-23 16:29 | 7688 | 7688 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | 2013 | Q4 | Q4 - 2013 | 11900 | 10067 | FALSE | 72 | We anticipate selecting vendors and awarding contracts to two major components of the overall system, the fiber optic line along E 120th Ave, and the deployment of the LTE gear. We also anticipate the approval of the revised budget and route modification to allow us to complete the project. | 0 |  | N/A | 100 | We anticipate one additional EA, or a modification to our existing EA based upon our plans for network expansion. This additional EA is predicated upon the acceptance of ADCOM911's route modification. | 100 | We anticipate additional network design activities to take place based upon the assumption of acceptance of ADCOM911's route modification. | 100 | We anticipate some additional Rights of Way for fiber optic development based upon the assumption of acceptance of ADCOM911's route modification. | 100 | We anticipate some additional Construction Permits for fiber optic development based upon the assumption of acceptance of ADCOM911's route modification. | 85 | We anticipate that the site security project will be completed, as well as some tower strengthening which may be necessary. | 85 | We anticipate that the fiber optic equipment will be purchased during the 1st quarter of 2014, related to the 120th ave construction. There may also be some network equipment purchases, routers, switches etc. | 75 | While we anticipate the fiber optic construction to begin in the 1st quarter of 2014, we do not anticipate this work to be significantly completed by the end of the quarter. Other microwave backhaul used in the LTE network will probably not be installed until the 2nd quarter of 2014. | 50 | We do not anticipate significant equipment deployment during the 1st quarter of 2014. | 60 | We do not anticipate significant network testing to take place in the 1st quarter of 2014. | 2014-02-26 15:47 | 2014-02-26 15:47 | 7688 | 7688 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570158 | 2010 | Q4 | Q4 - 2010 | 974 | 2020 | FALSE | 1 | Zero variance. | 0 |  | N/A | 60 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 10 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 0 | Zero variance. | 2011-02-04 12:00 | 2011-02-04 12:00 | 6478 | 6478 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2011 | Q1 | Q1 - 2011 | 1870 | 2680 | FALSE | 3 | Zero variance | 0 |  | Zero variance | 80 | Zero variance | 0 | Zero variance | 5 | Zero variance | 10 | The Authority has begun outreach to relevant permitting bodies, regulatory agencies, and other stakeholders with oversight responsibilities. However, the Authority will delay formally submitting for most permits and approvals until the completion of a draft EA, which occurs mid-way through this quarter, and the conclusion of contract negotiations, which will happen near the end of this quarter. Progress on this milestone will thus be slowed through this calendar year. | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 2011-05-02 18:52 | 2011-05-02 18:52 | 6479 | 6479 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2011 | Q2 | Q2 - 2011 | 3020 | 3267 | FALSE | 3 | Pending negotiations resuming, the project schedule will be moving forward. | 0 |  | Zero variance | 90 | We will be soliciting CEQA / Environmental services contract in this quarter to assist with completing the EA. | 50 | Delay in the procurement process has delayed design review. We project this will be underway once negotiations are concluded and the contract is executed. | 15 | Zero variance | 15 | The Authority continues outreach to permitting bodies, regulatory agencies, and other stakeholders with oversight responsibilities. However, the Authority will delay formally submitting for most permits and approvals until conclusion of contract negotiations. Progress on this milestone will thus be slowed through this calendar year. | 0 | No site preparation will begin until the FONSI is issued. | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 0 | Zero variance | 2011-08-11 14:21 | 2011-08-11 14:21 | 6478 | 6478 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2011 | Q3 | Q3 - 2011 | 3498 | 3519 | FALSE | 4 | Due to canceled procurement. | 0 |  | N/A | 50 | Due to canceled procurement. | 2 | Due to canceled procurement. | 1 | Due to canceled procurement. | 1 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Zero variance. | 2011-10-27 11:58 | 2011-10-27 11:58 | 6478 | 6478 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2011 | Q4 | Q4 - 2011 | 4706 | 4354 | FALSE | 10 | Due to canceled procurement. | 0 |  | N/A | 60 | Due to canceled procurement. | 60 | Due to canceled procurement. | 1 | Due to canceled procurement. | 10 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Due to canceled procurement. | 0 | Zero variance. | 2012-01-30 15:27 | 2012-01-30 15:27 | 6478 | 6478 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2012 | Q1 | Q1 - 2012 | 5916 | 5557 | FALSE | 5 | LA-RICS anticipates further progress in site acquisition, environmental assessment. | 0 |  | N/A | 55 | Finalize technical reports, continue environmental analysis, pending initiation of federal consultations. | 25 | No updates until a contract is executed with Telecommunications System vendor. | 10 | Site acquisition and valuation of in-kind land/property contribution. | 10 | Site use agreements | 0 | Due to cancelled procurement. | 0 | Due to cancelled procurement. | 0 | Due to cancelled procurement. | 0 | Due to cancelled procurement. | 0 | Zero variance | 2012-05-02 17:19 | 2012-05-02 17:19 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2012 | Q2 | Q2 - 2012 | 6850 | 6051 | FALSE | 6 | LA-RICS anticipates release of addendum or new RFP to address LTE related equipment in proposed specifications. | 0 |  | N/A | 55 | Continue refining the NEPA environmental assessment/CEQA initial study document structure and continue the outreach to key stakeholders, inlcude local land use agencies. | 25 | No further updates on design until a contract is executed with a telecommunications vendor. | 6 | Analysis of site valuations for proposed design of 255 sites. | 2 | Working with legal counsel to determine strategies on obtaining permits and site use agreements. | 0 | No updates until a contract is executed with a telecommunications vendor and design is finalized. | 0 | Procurement on hold. Partial suspension on LTE-related equipment purchases will not allow for such activity. | 0 | Procurement on hold. Partial suspension on LTE-related equipment purchases will not allow for such activity. | 0 | Procurement on hold. Partial suspension on LTE-related equipment purchases will not allow for such activity. | 0 | Procurement on hold. Partial suspension on LTE-related equipment purchases will not allow for such activity. | 2012-08-03 12:29 | 2012-08-03 12:29 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2012 | Q3 | Q3 - 2012 | 7824 | 6615 | FALSE | 7 | Staff will continue to draft the RFP for the LTE system. | 0 |  | N/A | 60 | Continue to evaluate the LTE sites for potential CEQA exemption eligibility | 25 | No further updates on design until a contract is executed with a telecommunications vendor. | 6 | Analysis of site valuations for proposed design of 255 sites. | 4 | Working with legal counsel to determine strategies on obtaining permits and site use agreements. | 0 | No updates until a contract is executed with a telecommunications vendor and design is finalized. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 2012-11-09 16:03 | 2012-11-09 16:03 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2012 | Q4 | Q4 - 2012 | 8648 | 7468 | FALSE | 8 | The RFP for the LTE system should be substantially complete for FirstNet review by Feb, 2013, and industry review by March, 2013. |  |  | N/A | 60 | Continue to evaluate the LTE sites for potential CEQA exemption eligibility | 25 | No further updates on design until a contract is executed with a telecommunications vendor. | 6 | Analysis of site valuations for proposed design of 255 sites. | 4 | Working with legal counsel to determine strategies on obtaining permits and site use agreements. | 0 | No updates until a contract is executed with a telecommunications vendor and system design is finalized. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 2013-02-01 12:17 | 2013-02-01 12:17 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2013 | Q1 | Q1 - 2013 | 9706 | 8386 | FALSE | 9 | LA-RICS anticipates more progress on: the environmental front, in the preparation of the RFP-LTE, extension of the BTOP deadline and lifting of partial suspension. | 0 |  | N/A | 61 | Continue CEQA exemption eligibility assessment including additional field surveys; continue to assess a modified approach to NEPA and CEQA documentation to provide more clarity. | 27 | No further updates on design until a contract is executed with a telecommunications vendor. | 6 | Analysis of site valuations for proposed design of 255 sites. | 6 | Working with legal counsel to determine strategies on obtaining permits and site use agreements. | 0 | No updates until a contract is executed with a telecommunications vendor and system design is finalized. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 0 | On hold, until suspension on LTE-related equipment purchases is lifted. | 2013-05-13 16:09 | 2013-05-13 16:09 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2013 | Q2 | Q2 - 2013 | 10152 | 8642 | FALSE | 3 | Procurement process for the LTE system is expected to start soon |  |  |  | 65 | Provide project information needed to initiate consultation with federal resource agencies. Continue to consult with NTIA on NEPA document approach and methodology. Re-initiate local outreach. | 29 | Complete the RFP for the LTE system and begin the procurement process | 7 | Conduct detailed site and land valuation analysis; will begin site use agreement consultation with cities. | 3 | Working with legal counsel to plan for permitting of LTE sites | 0 | Procurement process on hold | 0 | Procurement process on hold | 0 | Procurement process on hold | 0 | Procurement process on hold | 0 | Procurement process on hold | 2013-07-24 15:28 | 2013-07-24 15:28 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2013 | Q3 | Q3 - 2013 | 11192 | 9377 | FALSE | 4 | The procurement process for the LTE contractor should be nearly completed. | 0 |  | N/A | 70 | Complete Chapters 1 and 2 of the preliminary working draft NEPA EA and Chapters 3 and 4 for three resource areas (socioeconomics, human health and safety, and geology and soils). Complete virtual (i.e. desktop) planning level survey to identify National Register of Historic Places (NRHP) eligible sites around proposed project sites and complete windshield surveys for these sites. Continue consultation coordination with California SHPO and federal resource agencies. Start coastal consistency certification process for proposed project sites in the coastal zone. | 29 | Will start immediately after LTE contractor is hired. | 8 | Detailed site and land valuation analysis is being conducted; consultations with potential LTE sites continue on site use agreement. | 3 | Work continues with legal counsel for permitting of LTE sites | 0 | Pending contract execution with selected LTE contractor. | 0 | Pending contract execution with selected LTE contractor. | 0 | Pending contract execution with selected LTE contractor. | 0 | Pending contract execution with selected LTE contractor. | 0 | Pending contract execution with selected LTE contractor. | 2013-11-05 13:57 | 2013-11-05 13:57 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | 2013 | Q4 | Q4 - 2013 | 11912 | 10079 | FALSE | 5 | The initial phase of the project begins. | 0 |  | N/A | 95 | Complete an administrative draft NEPA EA. Continue the resource agency (USFWS and California Office of Historic Preservation (SHPO)) and federal land-administering agencies consultation and coordination processes to completion. | 35 | Will start immediately after LTE system contractor is hired. | 10 | Continue progress on outreach activities and site access agreement preparation. | 5 | Continue legal counsel work on permitting for LTE sites. | 0 | Pending LTE system project schedule | 0 | Pending LTE system project schedule | 0 | Pending LTE system project schedule | 0 | Pending LTE system project schedule | 0 | Pending LTE system project schedule | 2014-02-27 15:49 | 2014-02-27 15:49 | 7411 | 7411 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT11BIX5570001 | 2010 | Q3 | Q3 - 2010 | 2430 | 2960 | FALSE | 0 | n/a | 0 | n/a | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 2011-06-27 12:06 | 2011-06-27 12:06 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2010 | Q4 | Q4 - 2010 | 2424 | 2957 | FALSE | 6 | Due to the previously described delays with the Grantee Substitution process, most project tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 14%. | 5 |  | Due to the previously described delays with the Grantee Substitution process, most Other miscellaneous tasks such as compliance reporting systems and warehouse staging will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 13%. | 50 | Due to the previously described delays with the Grantee Substitution process, most Environmental Assessment tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 100%. | 43 | Due to the previously described delays with the Grantee Substitution process, most Network Design tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 86%. | 0 | This is consistent with the baseline report. | 0 | This is consistent with the baseline report. | 13 | Due to the previously described delays with the Grantee Substitution process, most Site Preparation tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 23%. | 9 | Due to the previously described delays with the Grantee Substitution process, most Equipment Procurement tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 18%. | 5 | Due to the previously described delays with the Grantee Substitution process, most Network Build tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 13%. | 7 | Due to the previously described delays with the Grantee Substitution process, most Equipment Deployment tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 16%. | 3 | Due to the previously described delays with the Grantee Substitution process, most Network Testing tasks will not be started until the project's third quarter. We will expedite all possible processes to catch up, but we will not achieve our baseline target of 9%. | 2011-06-02 10:18 | 2011-06-02 10:18 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2011 | Q1 | Q1 - 2011 | 2040 | 2765 | FALSE | 10 | While this percentage looks high for a pre-FONSI amount, it includes the in-kind match of $8.9 million booked in March. It is still below our baseline projection of 27%. | 0 |  | With no equipment ready for deployment this quarter, we won't have the need to lease warehouse space. Thus, we will not meet our baseline projection of 23%. | 100 | We fully expect the Environmental Assessment to be complete and anticipate approval during this quarter, with a FONSI received by the end of June. This is in line with the baseline completion of 100%. | 10 | The logical network design should be complete, but with the design/build firm hired late in the quarter, The network design will remain behind the baseline projection of 100%. | 92 | This is the same percentage complete as for the first quarter of 2011. It is double the baseline projection of 46%. | 0 | We anticipate that the design/build firm that we engage will complete all permitting, so until that procurement is complete, permitting costs will remain at 0%. This is below the baseline target of 11%. | 0 | We anticipate that the design/build firm that we engage will complete all site preparation, so until that procurement is complete, site preparation costs will remain at 0%. This is below the baseline target of 35%. | 0 | There will be a small spend this quarter, but not enough to reach 1%. The equipment RFP will be complete and possibly a bid selection made, but the dollars won't actually be spent until the next quarter. We will not make the baseline target of 29%. | 4 | The 4% includes project network overhead, which is included in this category. However the actual Network Build won't begin until after the FONSI has been obtained. This is below the baseline target of 23%. | 0 | As we don't anticipate having our FONSI until the very end of the quarter, we won't be able to deploy any of our purchased equipment during this quarter or meet our baseline goal of 26%. However, once the FONSI is received we will deploy equipment to connect 345 community anchor institutions. | 0 | We will not meet our baseline goal of 18% as we will not have network components to start testing yet. | 2011-05-16 11:53 | 2011-05-16 11:53 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2011 | Q2 | Q2 - 2011 | 2908 | 3211 | FALSE | 16 | The overall picture is that we are behind our baseline schedule to the earlier delays caused by the grant transfer. This has resulted in us not receiving our FONSI yet, although we should receive it within days of this report. By the end of the next quarter,we will just be beginning the start of our build process. However, we have planned for accelerated activity with our design/build contractor once the FONSI is issued. So, we anticipate being 16% complete versus our baseline target of 41% complete, but in subsequent quarters we plan to bridge that gap and make significant progress to catch up to our milestones. | 0 |  | With no equipment ready for deployment this quarter, we won't have the need to lease warehouse space. This, we will not meet our baseline projection of 35%. | 100 | Once the FONSI has been issued, we will receive the final invoice from our Environmental contractor, which will take us to 100% complete spend for this category. | 98 | The network design will be substantially complete by the end of the quarter, although there may be a little open cost for possible future changes. The 98% complete will be just slightly behind the baseline target of 100% complete. | 92 | 92% is consistent with the baseline amount. | 0 | The baseline target is 25% complete, but with the physical network design just beginning this quarter, there well be no spend for permits. | 0 | The baseline target is 44% complete, but with the physical network design just beginning this quarter, there well be no spend for permits. | 1 | The baseline target is 40% complete. While we do anticipate the Equipment RFP to be awarded by the end of the quarter, there will probably be no actual spend until the beginning of the subsequent quarter. | 10 | While the baseline target is 44%, we anticipate very little build activity in this quarter as the physical design is completed. However, we will continue with a significant effort in procuring IRUs according to the route parameters. The Legacy network is also purchased during this quarter, which, with some upgraded equipment, will allow us to show improved service to over 400 subscribers. | 0 | Without the large equipment procurement, there will be no deployment. This is below our baseline goal of 37%. | 0 | We will not meet our baseline goal of 29% as we will not have network components to start testing yet. | 2011-08-01 18:02 | 2011-08-01 18:02 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2011 | Q3 | Q3 - 2011 | 4176 | 3936 | FALSE | 26 | Due to the delays caused by the grant transfer and the statewide Environmental Assessment process which resulted in the delay in receiving our FONSI, we are behind our baseline projection of 50% of our dollars spent. Now that the FONSI has been received, we have accelerated our activity with our design/build contractor and have issued two RFIs to help us obtain information for the final decision-making of the lease versus build options for our network design. This process will be substantially completed during this quarter. | 0 |  | The main cost of the baseline projection, which is at 44% complete this quarter, is for warehousing to store and stage equipment. While equipment is being procured this quarter, at this time we won't need outside warehouse space. | 100 | Our Environmental Assessment has been approved and this step is complete. | 100 | Although there will be future fine-tuning of design activity as we move forward with the network build, based on the baseline spend projections, this initial logical network and network equipment design category will be complete this quarter | 92 | The Rights of Way baseline projections are at 95%, so we will be slightly behind the activity in this category. The CDOT rights of way will be approved, but negotiations for smaller segments will be ongoing. | 0 | This category will be behind the baseline projection of 35% of the dollars spent because the following quarter will commence with the major construction, and many permitting fees will be paid then. | 0 | This category will be behind the baseline projection of 55% of the dollars spent because the following quarter will commence with the major construction, and many site preparation costs will be paid then. | 22 | While we're behind the baseline projection of 50% of the spend complete, this is a category where we'll quickly catch up. The first major order for layer 2 and 3 equipment will be placed this quarter, putting us at 22% complete on our equipment spending. Please note that in the budget categories (last page of this report) layer 2-3 equipment is part of the Construction category. | 20 | The network build baseline projection is 44% complete through this quarter. Obviously, build activities have been delayed due to the grant transfer process and the subsequent FONSI delays. However, activity has now picked up in obtaining IRUs, and as a result of the RFI process, RFPs and direct negotiations will commence this quarter according to the route parameters, and spending should increase dramatically in this category. | 2 | The baseline projection is to have 47% of the spend complete, but with equipment just arriving in this quarter, the spend will be very minor. | 36 | The baseline projection was to have 40% of the testing complete. This 36% estimate is for "lab" and equipment testing costs. With the network build delays described earlier, these costs will mostly be incurred in subsequent quarters. | 2011-11-21 10:31 | 2011-11-21 10:31 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2011 | Q4 | Q4 - 2011 | 5398 | 5080 | FALSE | 33 | Due to the delays caused by the grant transfer and the statewide Environmental Assessment process that resulted in the delay in receiving our FONSI, we are behind our baseline projection of 60% of our dollars spent. During the next quarter, the focus will be on finalizing the remaining IRUs and beginning construction to deploy the peering sites. Then, construction will begin on several routes in the state, with the majority of that activity falling into the second and third quarters of 2012. | 11 |  | The main cost for this category is for warehousing to store and stage equipment. A space will be leased this quarter and equipment verification will begin in this space. However, it is behind the 55% baseline projection for spend. | 100 | Our Environmental Assessment has been approved and this step is complete. | 100 | Although there will be future fine-tuning of design activity as we move forward with the network build, this logical network and network equipment design is complete. | 92 | This is the same as the current quarter, although discussions are in progress for additional rights of way. This will be behind our baseline projection of 97%. | 27 | The 27% projected completion will be behind the 48% baseline projection as the permitting activities will just start in earnest during this quarter. They will accelerate over the subsequent quarters. | 1 | Site preparation costs are minimal during this quarter will just involve the initial peering sites. This is behind the baseline projection of 70%. | 24 | Equipment Procurement is behind the baseline projection of 63% complete although more layer 2-3 equipment has been ordered this quarter. However, the equipment won't be received or invoiced until the beginning of the next quarter, so the spend remains flat through March 31. Please note that in the budget categories (last page of this report) layer 2-3 equipment is part of the Construction category. | 29 | The Network Build baseline projection is 55% complete through this quarter. Obviously, build activities have been delayed due to the grant transfer process and the subsequent FONSI delays. During this quarter as RFPs are awarded and the final IRUs are negotiated, construction will begin and will ramp up to full activity over the next couple of quarters. | 14 | As the first layer 2-3 equipment as been delivered, Equipment Deployment has begun, although well behind the 59% baseline projection. | 0 | No spend is anticipated here yet, which is behind the 51% projection. Please note that there was an error in this category in the last quarter, as spend projected here was actually for the Equipment Deployment category above. | 2012-02-29 13:22 | 2012-02-29 13:22 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2012 | Q1 | Q1 - 2012 | 6072 | 5635 | FALSE | 46 | Due to the previously described delays, we'll still be behind our baseline projection of 74% complete. However, this quarter starts a period of significant build progress for us. As described above, construction is starting in 5 parts of the state simultaneously. | 14 |  | The major cost for this category is for warehousing to store, test and stage equipment for deployment. We will be behind our 70% spend as we just recently leased the space, and the rent will be static through the remainder of the project. | 100 | Our Environmental Assessment has been approved and this step is complete. | 100 | Although there will be future fine-tuning of design activity as we move forward with the network build, this logical network and network equipment design is complete. | 100 | Rights of way negotiations and approvals will be completed this quarter. | 34 | Although this is behind our baseline projection of 67% complete, this activity will have more spend as pre-construction work throughout the state is ramping up. | 3 | This category is significantly behind the baseline projection of 85%. Site preparation will be done at the peering site locations and the CAIs that are connected this quarter. Spend should increase significantly during the third quarter as more laterals are built and CAIs are connected. | 48 | We will remain behind the baseline projection of 78% complete, but equipment procurement does continue this quarter as more layer 2-3 equipment is purchased and we begin the procurement of wireless equipment. Please note that in the budget categories (the last page of this report), layer 2-3 equipment is part of the Construction category. | 40 | The Network Build baseline projection is 70% complete through this quarter. Obviously, build activities have been delayed due to the grant transfer process and the subsequent FONSI delays. However, during this quarter there will be new IRUs signed as well as the start of physical construction costs. This quarter and the next will be key periods to build in several parts of the state to take advantage of milder weather. | 16 | Equipment deployment has begun, although well behind the 74% baseline projection. Equipment will be deployed as CAIs are connected during the construction phase. | 17 | Network Testing spending begins this quarter, and will accelerate as the network is constructed. We will be behind our baseline projection of 67%, but this category will ramp up in conjunction with the Network Build. | 2012-05-14 18:11 | 2012-05-14 18:11 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2012 | Q2 | Q2 - 2012 | 7274 | 6264 | FALSE | 64 | Due to the previously described delays, we'll still be behind our baseline projection of 87% complete. However, this quarter will continue with significant construction activity in several parts of the state simultaneously. | 32 |  | The major cost for this category is for warehousing to store, test and stage equipment for deployment. While this expense is behind our 85% baseline projection, both the cost and the timing of the warehouse space will result in a budget savings in this category. | 100 | Our Environmental Assessment has been approved and this step is complete. | 100 | Although there will be future fine-tuning of design activity as we move forward with the network build, this logical network and network equipment design is complete. | 100 | Although currently at 100%, this category will continue to have activity as we begin construction on additional CDOT rights of way in the next quarter. | 100 | Although currently at 100% of the baseline projection, costs in this category will continue to be incurred as the baseline amount was understated. | 9 | This amount is significantly behind the baseline projection of 94% as site preparation activity is just getting underway this quarter as construction continues and the laterals are built. However, some of this activity is being included in the Network Build category as not all Site Preparation costs have been broken out separately. | 68 | Equipment procurement will remain behind the baseline projection of 90% complete despite the second wave of layer 2 and 3 equipment arriving this quarter. Part of the difference is that the equipment total actual cost is lower than the original projection amount, so this category should see a savings that is applied to other categories. Please note that in the budget categories (the last page of this report), layer 2-3 equipment costs are part of the Construction category. | 62 | Although less than the baseline projection, the network build continues to ramp up as construction continues in several parts of the state. Obviously, the build activities have been delayed due to the grant transfer process and the subsequent FONSI delays. However, with both construction in full swing and the addition of 5 IRU's that will be signed this quarter, our deployed miles will greatly increase throughout the state. | 39 | Equipment deployment continues this quarter as more site builds are completed. However, this category remains behind the baseline projection of 87% complete. | 0 | This category is actually being absorbed into the Network Build costs as these expenses are not being specifically broken out. So the roughly $500,000 in total budget will be reallocated to Network Build. | 2012-08-29 14:50 | 2012-08-29 14:50 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2012 | Q3 | Q3 - 2012 | 8122 | 6768 | FALSE | 67 | Due to the previously described delays as well as the construction invoicing process taking additional time, we will be behind hour 94% baseline projection. However, there will still be continuing construction activities in various parts of the state where weather is less of an issue. | 18 |  | The major cost for this category is for warehousing to store, test and stage equipment for deployment. While this expense will be behind our 94% baseline projection, both the cost and the timing of the warehouse space will result in a budget savings in this category. | 100 | Our Environmental Assessment has been approved and this step is complete. | 100 | Although there will be future fine-tuning of design activity as we move forward with the network build, this logical network and network equipment design is complete. | 100 | As part of the submitted budget reprogram, we anticipate that the CDOT rights of way spend will be completed. | 100 | Although currently at 100% of the baseline projection, costs in this category will continue to be incurred as the baseline amount was understated. | 7 | This amount will be far behind the original baseline projection of 98% complete due to an overstatement in the baseline estimate. These amounts have been corrected in the submitted budget reprogram. | 74 | The Equipment spend amount will be behind the baseline projection of 96% due to both the timing of invoicing as well as an actual cost savings in the equipment purchased versus the original budgeted amount. So, equipment purchases will see savings that are applied to other categories. Please note that in the budget categories (the last page of this report), layer 2-3 equipment costs are part of the Construction category. | 66 | The network build is continuing at full bore through the end of the Fall build season. However, because of the timing of the invoicing of our major contractors, work performed in the Fall will mostly be paid in the first quarter of 2013. So, although physically more than 66% complete, based on payments we will be behind our baseline projections. We also anticipate the signing of one more IRU, but again payment will not occur until January. | 32 | With the delays in construction, equipment deployment will also be behind the baseline projection of 95% complete. However, spending will continue in this category over the next three quarters. | 0 | This category is actually being absorbed into the Network Build costs as these expenses are not being specifically broken out. So, the roughly $500,000 in total budget will be reallocated to Network Build. | 2012-11-28 15:56 | 2012-11-28 15:56 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2012 | Q4 | Q4 - 2012 | 9002 | 7778 | FALSE | 58 | Due to the previously described delays including the construction suspension, we will be far below our baseline projection of 98% complete. Again, this calculation is based on actual dollars spent, and not work completed, so once we pay for our completed construction activities, and once we are again actively constructing the network, the percentage complete will be significantly higher. | 22 |  | The major cost for this category is for warehousing to store, test and stage equipment for deployment. While this expense will be below our 98% baseline projection, both the cost and the timing of the warehouse space will result in a budget savings in this category. | 100 | More costs will be incurred in this category due to the required supplemental Environmental Assessment, however, based on dollars spent, this step is complete. | 100 | Although there will be future fine-tuning of design activity as we move forward with the network build, this logical network and network equipment design is complete. | 92 | Once the submitted budget reprogram has been approved, the CDOT rights of way spend will be completed. | 100 | Although currently at 100% of the baseline projection, costs in this category will continue to be incurred as the original baseline estimate was understated. | 8 | This amount will be far behind the original baseline projection of 100% complete due to an overstatement in the baseline estimate. These amounts have been corrected in the submitted budget reprogram. | 49 | The Equipment spend amount will be below the baseline projection of 99% due to the timing of equipment payments, the timing of the ordering of the final equipment, as well as an actual cost savings in the equipment purchased versus the original baseline projection amount. So, this category will result in savings that have been rebudgeted to other categories in the budget reprogram. Please note that in the budget categories (the last page of this report), layer 2 and 3 equipment costs are part of the Construction category. | 56 | Due to the construction suspension and the corresponding hold restrictions on construction payments, the Network Build completion percentage will remain far below its 98% baseline projection. However, once the supplemental Environmental Assessment has been approved and the funds are released to pay for build activities, the completion percentage in this category will quickly accelerate. There are many routes that are nearly complete where activity can promptly resume. | 26 | With the delays in construction, equipment deployment will also be behind the baseline projection of 99% complete. Spending will continue in this category as the network construction is completed and equipment is actually deployed. | 0 | This category is actually being absorbed into the Network Build costs as there expenses are not being specifically broken out. So, the roughly $500,000 in total budget is being reallocated to the Network Build category. | 2013-02-27 10:58 | 2013-02-27 10:58 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2013 | Q1 | Q1 - 2013 | 9986 | 8537 | FALSE | 93 | This total will be behind our original projection of 100% percent complete because of the delays at the beginning of the project as well as the recent temporary construction suspension. However, we anticipate the suspension to be lifted and funds freed up to pay for completed work as well as to begin the work on the final approved routes. | 25 |  | The costs of the outside testing and warehouse facilities will be well behind the baseline projection of 100% as the facilities were obtained later than anticipated and are less expensive than the projected amount. | 100 | More costs will be incurred in this category due to the required supplemental Environmental Assessment, however, based on dollars spent, this step is complete. | 100 | Although there will be future fine-tuning of design activity as we move forward with the network build, this logical network and network equipment design is complete. | 100 | We anticipate the change in the CDOT match amount to be approved, and the amount on routes already completed or in progress will be booked this quarter. Although this amount will be below our rebudgeted amount, it will far exceed the original baseline projection. | 100 | Although currently at 100% of the baseline projection, costs in this category will continue to be incurred as the original baseline estimate was understated. | 9 | This amount is lower than the baseline projection of 100% as some costs that were originally in this category are now part of the Network Build category. We have revised this budget amount in our submitted budget reprogram. | 76 | The Equipment spend amount will be below the baseline projection of 100% due to the timing of equipment payments, the timing of the ordering of the final equipment, as well as an actual cost savings in the equipment purchased versus the original baseline projection amount. So, this category will result in savings that have been rebudgeted to other categories in the budget reprogram. | 76 | The network build amount is behind the projection of 100% complete due to the previously mentioned delays. | 45 | Equipment deployment will be far below the 100% projection as pending the lifting of the suspension during this quarter, construction will be mobilized, but the equipment can only be installed as the routes are completed. | 0 | This category is actually being absorbed into the Network Build costs as these expenses are not being specifically broken out. So, the roughly $500,000 in total budget is being reallocated to the Network Build category. | 2013-05-29 17:56 | 2013-05-29 17:56 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2013 | Q2 | Q2 - 2013 | 10788 | 9064 | FALSE | 94 | The project will not be completed by the end of the next quarter, so an extension request will be submitted. The final remaining dollars have been committed to complete builds to 29 CAIs, most of which will be complete by the end of the year, with the exception of the Silverton build, which won't be completed until the latter part of 2014. | 28 |  | Some costs that were in this category are now in the Network Build category, as shown in the approved budget reprogram. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 8 | Some costs that were in this category are now in the Network Build category, as shown in the approved budget reprogram. | 96 | There will be some new equipment purchases for wireless equipment, but probably not until the 4th quarter. | 74 | Construction will resume in full in July, with much activity during this quarter. However, a lot of the activity is to complete previously started routes and laterals and to splice previously laid fiber. Most of the remaining spend will be in this category. | 30 | Some costs that were in this category are now in the Network Build category, as shown in the approved budget reprogram. | 0 | Some costs that were in this category are now in the Network Build category, as shown in the approved budget reprogram. | 2013-08-28 11:02 | 2013-08-28 11:02 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2013 | Q3 | Q3 - 2013 | 11346 | 9473 | FALSE | 96 | A project extension was approved through December 31, 2014. The final remaining dollars have been committed to complete builds to 29 school district CAIs, with the wireless builds and the Silverton build not completed until their scheduled completion in 2014. | 30 |  | Most costs that were initially in this category are now in the Network Build category, as shown in the the approved budget reprogram. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 8 | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 97 | Although almost complete, there will be additional purchases for wireless equipment in 2014. | 76 | Most of the remaining spend will be in this category, although it will be reduced during the winter months. The Silverton build is expected to start in the Spring of 2014 and be completed the latter part of that year, so the budgeted money for that build won't be spent until then. | 42 | Most costs that were initially in this category are now in the Network Build category, as shown in the the approved budget reprogram. | 0 | All costs that were initially in this category are now in the Network Build category, as shown in the the approved budget reprogram. | 2013-11-22 11:06 | 2013-11-22 11:06 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | 2013 | Q4 | Q4 - 2013 | 11852 | 10024 | FALSE | 97 | A project extension was approved through December 31, 2014. The final remaining dollars have been will be used in this quarter to continue with the wireless build as well as to start the first steps toward the Silverton build. It's expected that we will connect five new CAIs this quarter. | 33 |  | Most costs that were initially in this category are now in the Network Build category, as shown in the the approved budget reprogram. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 100 | This spend category is complete. | 8 | Most costs that were initially in this category are now in the Network Build category, as shown in the approved budget reprogram. | 98 | Although almost complete, there will be additional purchases for wireless equipment in 2014. | 76 | Most of the remaining spend will be in this category, although it will be reduced during the winter months. The Silverton build contractor will be selected and the build will begin this Spring and be completed the latter part of that year, so the budgeted money for that build won't be spent until then. | 42 | Most costs that were initially in this category are now in the Network Build category, as shown in the the approved budget reprogram. | 0 | All costs that were initially in this category are now in the Network Build category, as shown in the the approved budget reprogram. | 2014-02-20 13:37 | 2014-02-20 13:37 | 7044 | 7044 | Eagle-Net Alliance | TRUE
NT12BIX5570001 | 2012 | Q1 | Q1 - 2012 | 6360 | 5782 | FALSE | 74 | This is 26% behind our baseline and this is because of cost savings and delays in permitting and pole attachment. Zayo has requested some route changes that required a revised EA Addendum. | 0 |  | N/A | 0 | Zayo did not plan for this in our budget. This was part of our network design. | 99 | This percentage is based on spend based on the total for both awards. This is 5% behind our baseline. Zayo is currently running way under budget. | 0 | Zayo did not plan for this in our budget. This was part of our network design. | 0 | Zayo built this costs into our construction budget. We did not make it a separate line item. | 88 | This percentage is based on spend based on the total for both awards. This is 22% behind our baseline. Zayo is currently running way under budget. | 100 | This is in line with our baseline. | 73 | This percentage is based on spend based on the total for both awards. This is 27% behind our baseline. Zayo is currently running way under budget. | 0 | This is 100% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. This is 100% behind our baseline. | 2012-05-30 19:15 | 2012-05-30 19:15 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570001 | 2012 | Q2 | Q2 - 2012 | 7294 | 6274 | FALSE | 74 | This is 26% behind our baseline and this is because of cost savings. | 0 | N/A | N/A | 0 | Zayo did not plan for this in our budget. This was part of our network design. | 96 | This percentage is based on spend based on the total for both awards. This is 4% behind our baseline. Zayo is currently running under budget. | 0 | Zayo did not plan for this in our budget. This was part of our network design. | 0 | Zayo built this costs into our construction budget. We did not make it a separate line item. | 88 | This percentage is based on spend based on the total for both awards. This is 22% behind our baseline. Zayo is currently running way under budget. | 100 | This is in line with our baseline. | 73 | This percentage is based on spend based on the total for both awards. This is 27% behind our baseline. Zayo is currently running way under budget. | 0 | This is 100% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. This is 100% behind our baseline. | 2012-08-31 12:32 | 2012-08-31 12:32 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570001 | 2012 | Q3 | Q3 - 2012 | 8174 | 6798 | FALSE | 100 | This is based on actual spend as outlined below. | 0 | 0 | N/A | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 100 | This is in line with our baseline. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 100 | This is based on projected spend. Zayo is way under budget. | 100 | This is based on projected spend. Zayo is way under budget. | 100 | This is based on projected spend. Zayo is way under budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 2012-11-30 14:50 | 2012-11-30 14:50 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570001 | 2012 | Q4 | Q4 - 2012 | 8970 | 7751 | FALSE | 100 | This is in line with our baseline. | 0 | 0 | N/A | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 100 | This is in line with our baseline. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 100 | This is in line with our baseline. | 100 | This is in line with our baseline. | 100 | This is in line with our baseline. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 2013-02-26 13:01 | 2013-02-26 13:03 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570001 | 2013 | Q1 | Q1 - 2013 | 10068 | 8592 | FALSE | 100 | This is in line with our baseline. | 0 | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is in line with our baseline. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 73 | This is in line with our baseline. | 96 | This is in line with our baseline. | 84 | This is in line with our baseline. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 0 | This is because Zayo included this in our baseline plan, but did not plan for it in our detailed budget. | 2013-06-20 18:19 | 2013-06-20 18:19 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570002 | 2012 | Q1 | Q1 - 2012 | 6358 | 5781 | FALSE | 73 | This percentage is based on spend based on the total for both awards. This is 47.7% ahead of our baseline. This is because of proper planning and execution of the project on Zayo's part. | 0 |  | N/A | 100 | This is in line with the detailed budget attached to the original grant. | 100 | This is based on total dollars spent for both awards. This is 15% ahead of our baseline. This is because of proper planning and execution of the project on Zayo's part. | 0 | N/A | 0 | N/A | 0 | This is 38% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget because after review, zayo is not building any hut sites. | 93 | This percentage is based on spend based on the total for both awards. This is 55% ahead of our baseline. This is because Zayo should be ahead of our build as outlined in 2a above and will be preparing to install the equipment.. | 69 | This percentage is based on spend based on the total for both awards. This is 17% ahead our baseline. This is because of proper planning and execution of the project on Zayo's part. | 0 | This is 38% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. If you look at the Network Build percentage above, Zayo is 17% ahead. Zayo figures that Build equals deployment. | 0 | N/A | 2012-05-30 19:13 | 2012-05-30 19:13 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570002 | 2012 | Q2 | Q2 - 2012 | 7282 | 6268 | FALSE | 68 | This percentage is based on spend based on the total for both awards. This is 17.8% ahead of our baseline. This is because of proper planning and execution of the project on Zayo's part. | 0 | N/A | N/A | 100 | This is in line with the detailed budget attached to the original grant. | 100 | This is based on total dollars spent for both awards. This is in line with our baseline. | 0 | N/A | 0 | N/A | 0 | This is 52% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget because after review, zayo is not building any hut sites. | 93 | This percentage is based on spend based on the total for both awards. This is 41% ahead of our baseline. This is because Zayo should be ahead of our build as outlined in 2a above and will be preparing to install the equipment. | 71 | This percentage is based on spend based on the total for both awards. This is 19% ahead our baseline. This is because of proper planning and execution of the project on Zayo's part. | 0 | This is 52% below our baseline. This is because Zayo included this in our baseline plan but did not plan for it in our detailed budget. If you look at the Network Build percentage above, Zayo is 17% ahead. Zayo figures that Build equals deployment. | 0 | N/A | 2012-08-29 17:42 | 2012-08-29 17:42 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570002 | 2012 | Q3 | Q3 - 2012 | 8176 | 6799 | FALSE | 100 | This is based on the projected spend for the entire project. | 0 | 0 | N/A | 100 | This is in line with our baseline. | 100 | This is in line with our baseline. | 0 | N/A | 0 | N/A | 0 | This is below our baseline, because Zayo projected building some hut sites that are not required for this build. | 100 | This is based on projected spend. | 100 | This is based on projected spend. | 0 | This is because Zayo included this in our baseline but did not include it in our detailed budget. | 0 | N/A | 2012-11-30 14:53 | 2012-11-30 14:53 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570002 | 2012 | Q4 | Q4 - 2012 | 8954 | 7730 | FALSE | 100 | This is in line with our baseline. | 0 | 0 | N/A | 100 | This is in line with our baseline. | 100 | This is in line with our baseline. | 0 | N/A | 0 | N/A | 0 | This is below our baseline, because Zayo projected building some hut sites that are not required for this build. | 100 | This is in line with our baseline. | 100 | This is in line with our baseline. | 0 | This is because Zayo included this in our baseline but did not include it in our detailed budget. | 0 | N/A | 2013-02-25 18:07 | 2013-02-25 18:07 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570002 | 2013 | Q1 | Q1 - 2013 | 10062 | 8589 | FALSE | 95 | This is about ~1M under our detailed budget. | 0 |  | This is in line with our detailed budget. | 100 | This is in line with our detailed budget. Zayo plans to move funds from construction to cover the variance from last quarter. | 100 | This is in line with our detailed budget. | 0 | This is in line with our detailed budget. | 0 | This is in line with our detailed budget. | 0 | This is in line with our detailed budget. | 9 | This is in line with our detailed budget. | 92 | This is about ~1M under our detailed budget. | 0 | This is in line with our detailed budget. | 0 | This is in line with our detailed budget. | 2013-06-18 16:38 | 2013-06-18 16:38 | 6743 | 6743 | Zayo Group, LLC | TRUE
NT12BIX5570002 | 2013 | Q2 | Q2 - 2013 | 12676 | 10989 | FALSE | 100 | Project is 12% under budget based on actual spend. | 0 |  | N/A | 100 | Zayo has completed all construction. | 100 | This is in line with our detailed budget. | 0 | N/A | 0 | N/A | 0 | Zayo included this in our baseline, but did not include this in our detailed budget. | 100 | This is based on actual spend. | 100 | This is based on actual spend. | 0 | Zayo included this in our baseline, but did not include this in our detailed budget. | 0 | N/A | 2015-02-03 14:13 | 2015-02-03 14:13 | 7919 | 7919 | Zayo Group, LLC | TRUE

## CCI_Expenditures
Award_Num | ProjectType_Cd | Year_Desc | Quarter_Cd | YearQuarter | TotCostPlan_Equipmnt_Amt | MatchFundPlan_Equipmnt_Amt | FedFundPlan_Equipmnt_Amt | TotCostActl_Equipmnt_Amt | MatchFundActl_Equipmnt_Amt | FedFundActl_Equipmnt_Amt | TotCostAntcp_Equipmnt_Amt | MatchFundAntcp_Equipmnt_Amt | FedFundAntcp_Equipmnt_Amt | TotCostPlan_Constructn_Amt | MatchFundPlan_Constructn_Amt | FedFundPlan_Constructn_Amt | TotCostActl_Constructn_Amt | MatchFundActl_Constructn_Amt | FedFundActl_Constructn_Amt | TotCostAntcp_Constructn_Amt | MatchFundAntcp_Constructn_Amt | FedFundAntcp_Constructn_Amt | TotCostPlan_LegalExp_Amt | MatchFundPlan_LegalExp_Amt | FedFundPlan_LegalExp_Amt | TotCostActl_LegalExp_Amt | MatchFundActl_LegalExp_Amt | FedFundActl_LegalExp_Amt | TotCostAntcp_LegalExp_Amt | MatchFundAntcp_LegalExp_Amt | FedFundAntcp_LegalExp_Amt | TotCostPlan_LandApprsl_Amt | MatchFundPlan_LandApprsl_Amt | FedFundPlan_LandApprsl_Amt | TotCostActl_LandApprsl_Amt | MatchFundActl_LandApprsl_Amt | FedFundActl_LandApprsl_Amt | TotCostAntcp_LandApprsl_Amt | MatchFundAntcp_LandApprsl_Amt | FedFundAntcp_LandApprsl_Amt | TotCostPlan_RelocExp_Amt | MatchFundPlan_RelocExp_Amt | FedFundPlan_RelocExp_Amt | TotCostActl_RelocExp_Amt | MatchFundActl_RelocExp_Amt | FedFundActl_RelocExp_Amt | TotCostAntcp_RelocExp_Amt | MatchFundAntcp_RelocExp_Amt | FedFundAntcp_RelocExp_Amt | TotCostPlan_ArchFee_Amt | MatchFundPlan_ArchFee_Amt | FedFundPlan_ArchFee_Amt | TotCostActl_ArchFee_Amt | MatchFundActl_ArchFee_Amt | FedFundActl_ArchFee_Amt | TotCostAntcp_ArchFee_Amt | MatchFundAntcp_ArchFee_Amt | FedFundAntcp_ArchFee_Amt | TotCostPlan_OtherArchFee_Amt | MatchFundPlan_OtherArchFee_Amt | FedFundPlan_OtherArchFee_Amt | TotCostActl_OtherArchFee_Amt | MatchFundActl_OtherArchFee_Amt | FedFundActl_OtherArchFee_Amt | TotCostAntcp_OtherArchFee_Amt | MatchFundAntcp_OtherArchFee_Amt | FedFundAntcp_OtherArchFee_Amt | TotCostPlan_ProjInspFee_Amt | MatchFundPlan_ProjInspFee_Amt | FedFundPlan_ProjInspFee_Amt | TotCostActl_ProjInspFee_Amt | MatchFundActl_ProjInspFee_Amt | FedFundActl_ProjInspFee_Amt | TotCostAntcp_ProjInspFee_Amt | MatchFundAntcp_ProjInspFee_Amt | FedFundAntcp_ProjInspFee_Amt | TotCostPlan_SiteWork_Amt | MatchFundPlan_SiteWork_Amt | FedFundPlan_SiteWork_Amt | TotCostActl_SiteWork_Amt | MatchFundActl_SiteWork_Amt | FedFundActl_SiteWork_Amt | TotCostAntcp_SiteWork_Amt | MatchFundAntcp_SiteWork_Amt | FedFundAntcp_SiteWork_Amt | TotCostPlan_Demolitn_Amt | MatchFundPlan_Demolitn_Amt | FedFundPlan_Demolitn_Amt | TotCostActl_Demolitn_Amt | MatchFundActl_Demolitn_Amt | FedFundActl_Demolitn_Amt | TotCostAntcp_Demolitn_Amt | MatchFundAntcp_Demolitn_Amt | FedFundAntcp_Demolitn_Amt | TotCostPlan_OtherMisc_Amt | MatchFundPlan_OtherMisc_Amt | FedFundPlan_OtherMisc_Amt | TotCostActl_OtherMisc_Amt | MatchFundActl_OtherMisc_Amt | FedFundActl_OtherMisc_Amt | TotCostAntcp_OtherMisc_Amt | MatchFundAntcp_OtherMisc_Amt | FedFundAntcp_OtherMisc_Amt | TotCostPlan_DirCh_SubTot_Amt | MatchFundPlan_DirCh_SubTot_Amt | FedFundPlan_DirCh_SubTot_Amt | TotCostActl_DirCh_SubTot_Amt | MatchFundActl_DirCh_SubTot_Amt | FedFundActl_DirCh_SubTot_Amt | TotCostAntcp_DirCh_SubTot_Amt | MatchFundAntcp_DirCh_SubTot_Amt | FedFundAntcp_DirCh_SubTot_Amt | TotCostPlan_Total_Amt | MatchFundPlan_Total_Amt | FedFundPlan_Total_Amt | TotCostActl_Total_Amt | MatchFundActl_Total_Amt | FedFundActl_Total_Amt | TotCostAntcp_Total_Amt | MatchFundAntcp_Total_Amt | FedFundAntcp_Total_Amt | BudgetIncome_Amt | ToDateIncome_Amt | Recipient | April 11, 2014 Cutoff Date
NT10BIX5570003 | CCI | 2010 | Q3 | Q3 - 2010 | 3513857 | 702770 | 2811087 | 1936723 | 387345 | 1549378 | 2120000 | 424000 | 1696000 | 16511000 | 3302200 | 13208800 | 1458032 | 291606 | 1166426 | 3000000 | 600000 | 2400000 | 75000 | 15000 | 60000 | 30848 | 6170 | 24678 | 35000 | 7000 | 28000 | 700000 | 140000 | 560000 | 2000 | 400 | 1600 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533729 | 706746 | 2826983 | 870673 | 174135 | 696538 | 1100000 | 220000 | 890000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381717 | 276343 | 1105374 | 78977 | 15795 | 63182 | 90000 | 18000 | 72000 | 25715303 | 5143059 | 20572244 | 4377253 | 875451 | 3501802 | 6350000 | 1270000 | 5090000 | 25715303 | 5143059 | 20572244 | 4377253 | 875451 | 3501802 | 6350000 | 1270000 | 5090000 | 0 | 0 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | CCI | 2010 | Q4 | Q4 - 2010 | 3513850 | 702770 | 2811080 | 2186972 | 437394 | 1749578 | 3000000 | 600000 | 2400000 | 16511000 | 3302200 | 13208800 | 3292868 | 658574 | 2634294 | 4000000 | 800000 | 3200000 | 75000 | 15000 | 60000 | 66332 | 13266 | 53066 | 70000 | 14000 | 56000 | 700000 | 140000 | 560000 | 2000 | 400 | 1600 | 2000 | 400 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533729 | 706746 | 2826983 | 1124860 | 224972 | 899888 | 1750000 | 350000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381740 | 276343 | 1105370 | 151379 | 30276 | 121103 | 182000 | 36400 | 145600 | 25715319 | 5143059 | 20572233 | 6824411 | 1364882 | 5459529 | 9004000 | 1800800 | 7203200 | 25715319 | 5143059 | 20572233 | 6824411 | 1364882 | 5459529 | 9004000 | 1800800 | 7203200 | 0 | 0 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | CCI | 2011 | Q1 | Q1 - 2011 | 3513857 | 702771 | 2811086 | 2197168 | 439434 | 1757734 | 2800000 | 560000 | 2240000 | 16511000 | 3302200 | 13208800 | 3533768 | 706752 | 2827016 | 4300000 | 860000 | 3440000 | 75000 | 15000 | 60000 | 101758 | 20352 | 81406 | 140000 | 28000 | 112000 | 700000 | 140000 | 560000 | 2000 | 400 | 1600 | 100000 | 20000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533729 | 706746 | 2826983 | 1229983 | 245997 | 983986 | 1600000 | 320000 | 1280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381717 | 276344 | 1105373 | 169449 | 33890 | 135559 | 185000 | 37000 | 148000 | 25715303 | 5143061 | 20572242 | 7234126 | 1446825 | 5787301 | 9125000 | 1825000 | 7300000 | 25715303 | 5143061 | 20572242 | 7234126 | 1446825 | 5787301 | 9125000 | 1825000 | 7300000 | 0 | 0 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | CCI | 2011 | Q2 | Q2 - 2011 | 3513857 | 702771 | 2811086 | 2507102 | 501420 | 2005682 | 3900000 | 780000 | 3120000 | 16511000 | 3302200 | 13208800 | 5919391 | 1183878 | 4735513 | 8500000 | 1700000 | 6800000 | 75000 | 15000 | 60000 | 123835 | 24767 | 99068 | 160000 | 32000 | 128000 | 700000 | 140000 | 560000 | 31086 | 6217 | 24869 | 300000 | 60000 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533729 | 706746 | 2826983 | 1543591 | 308718 | 1234873 | 2000000 | 400000 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381717 | 276344 | 1105373 | 318556 | 63711 | 254845 | 350000 | 70000 | 280000 | 25715303 | 5143061 | 20572242 | 10443561 | 2088711 | 8354850 | 15210000 | 3042000 | 12168000 | 25715303 | 5143061 | 20572242 | 10443561 | 2088711 | 8354850 | 15210000 | 3042000 | 12168000 | 0 | 54549 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | CCI | 2011 | Q3 | Q3 - 2011 | 3513857 | 702771 | 2811086 | 3473565 | 694713 | 2778852 | 5500000 | 1100000 | 4400000 | 16511000 | 3302200 | 13208800 | 9161567 | 1832313 | 7329254 | 11000000 | 2200000 | 8800000 | 75000 | 15000 | 60000 | 123835 | 24767 | 99068 | 125000 | 25000 | 100000 | 700000 | 140000 | 560000 | 317329 | 63466 | 253863 | 425000 | 85000 | 340000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533729 | 706746 | 2826983 | 1817839 | 363568 | 1454271 | 2000000 | 400000 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381717 | 276344 | 1105373 | 370890 | 74178 | 296712 | 420000 | 84000 | 336000 | 25715303 | 5143061 | 20572242 | 15265025 | 3053005 | 12212020 | 19470000 | 3894000 | 15576000 | 25715303 | 5143061 | 20572242 | 15265025 | 3053005 | 12212020 | 19470000 | 3894000 | 15576000 | 0 | 101966 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | CCI | 2011 | Q4 | Q4 - 2011 | 3513857 | 702771 | 2811086 | 4279896 | 855979 | 3423917 | 4300000 | 860000 | 3440000 | 16511000 | 3302200 | 13208800 | 12218619 | 2443724 | 9774895 | 14000000 | 2800000 | 11200000 | 75000 | 15000 | 60000 | 128320 | 25664 | 102656 | 140000 | 28000 | 112000 | 700000 | 140000 | 560000 | 512980 | 102596 | 410384 | 550000 | 110000 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533729 | 706746 | 2826983 | 2020777 | 404156 | 1616621 | 2500000 | 500000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381717 | 276344 | 1105373 | 400942 | 80188 | 320754 | 450000 | 90000 | 360000 | 25715303 | 5143061 | 20572242 | 19561534 | 3912307 | 15649227 | 21940000 | 4388000 | 17552000 | 25715303 | 5143061 | 20572242 | 19561534 | 3912307 | 15649227 | 21940000 | 4388000 | 17552000 | 0 | 216025 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | CCI | 2012 | Q1 | Q1 - 2012 | 3513857 | 702771 | 2811086 | 4578942 | 915788 | 3663154 | 4670000 | 934000 | 3736000 | 16511000 | 3302200 | 13208800 | 13190984 | 2638197 | 10552787 | 14800000 | 2960000 | 11840000 | 75000 | 15000 | 60000 | 129855 | 25971 | 103884 | 131000 | 26200 | 104800 | 700000 | 140000 | 560000 | 512980 | 102596 | 410384 | 520000 | 104000 | 416000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3533729 | 706746 | 2826983 | 2125653 | 425131 | 1700522 | 2150000 | 430000 | 1720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381717 | 276344 | 1105373 | 410166 | 82033 | 328133 | 450000 | 90000 | 360000 | 25715303 | 5143061 | 20572242 | 20948580 | 4189716 | 16758864 | 22721000 | 4544200 | 18176800 | 25715303 | 5143061 | 20572242 | 20948580 | 4189716 | 16758864 | 22721000 | 4544200 | 18176800 | 0 | 333405 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | CCI | 2012 | Q2 | Q2 - 2012 | 4670270 | 934054 | 3736216 | 4632892 | 926578 | 3706314 | 4670270 | 934054 | 3736216 | 17558230 | 3511646 | 14046584 | 14609432 | 2921886 | 11687546 | 16000000 | 3200000 | 12800000 | 150000 | 30000 | 120000 | 129913 | 25983 | 103930 | 131000 | 26200 | 104800 | 520000 | 104000 | 416000 | 512980 | 102596 | 410384 | 512980 | 102596 | 410384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173894 | 434779 | 1739115 | 2170610 | 434122 | 1736488 | 2173894 | 434779 | 1739115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642909 | 128582 | 514327 | 442623 | 88525 | 354098 | 500000 | 100000 | 400000 | 25715303 | 5143061 | 20572242 | 22498450 | 4499690 | 17998760 | 23988144 | 4797629 | 19190515 | 25715303 | 5143061 | 20572242 | 22498450 | 4499690 | 17998760 | 23988144 | 4797629 | 19190515 | 0 | 558600 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | CCI | 2012 | Q3 | Q3 - 2012 | 4670270 | 934054 | 3736216 | 4634383 | 926877 | 3707507 | 4670270 | 934054 | 3736216 | 17558230 | 3511646 | 14046584 | 15392367 | 3078473 | 12313894 | 17625034 | 3525007 | 14100027 | 150000 | 30000 | 120000 | 132484 | 26497 | 105987 | 141984 | 28397 | 113587 | 520000 | 104000 | 416000 | 512980 | 102596 | 410384 | 512980 | 102596 | 410384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173894 | 434779 | 1739115 | 2193075 | 438615 | 1754459 | 2198075 | 439615 | 1758460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642909 | 128582 | 514327 | 454984 | 90997 | 363987 | 507724 | 101544 | 406180 | 25715303 | 5143061 | 20572242 | 23320273 | 4664055 | 18656218 | 25656067 | 5131213 | 20524854 | 25715303 | 5143061 | 20572242 | 23320273 | 4664055 | 18656218 | 25656067 | 5131213 | 20524854 | 0 | 687905 | South Dakota Network, LLC | TRUE
NT10BIX5570003 | CCI | 2012 | Q4 | Q4 - 2012 | 4670270 | 934054 | 3736216 | 4634384 | 926877 | 3707507 | 4634383 | 926876 | 3707507 | 17558230 | 3511646 | 14046584 | 17843886 | 3667055 | 14176831 | 17843886 | 3667055 | 14176831 | 150000 | 30000 | 120000 | 132484 | 26497 | 105987 | 132484 | 26497 | 105987 | 520000 | 104000 | 416000 | 512980 | 102596 | 410384 | 512980 | 102596 | 410384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173894 | 434779 | 1739115 | 2211716 | 442342 | 1769374 | 2211717 | 442343 | 1769374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642909 | 128582 | 514327 | 502699 | 100540 | 402159 | 502699 | 100540 | 402159 | 25715303 | 5143061 | 20572242 | 25838149 | 5265907 | 20572242 | 25838149 | 5265907 | 20572242 | 25715303 | 5143061 | 20572242 | 25838149 | 5265907 | 20572242 | 25838149 | 5265907 | 20572242 | 0 | 770923 | South Dakota Network, LLC | TRUE
NT10BIX5570004 | CCI | 2010 | Q3 | Q3 - 2010 | 14660971 | 2932194 | 11728776 | 58508 | 11702 | 46806 | 507860 | 101572 | 406288 | 269450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1628750 | 325750 | 1303000 | 428394 | 85679 | 342715 | 884994 | 176999 | 707995 | 4110896 | 822179 | 3288717 | 28500 | 5700 | 22800 | 43500 | 8700 | 34800 | 250000 | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 557000 | 111400 | 445600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 103410 | 413640 | 0 | 0 | 0 | 0 | 0 | 0 | 20113922 | 4022784 | 16091137 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 37500 | 7500 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42145539 | 8375217 | 33500870 | 515402 | 103081 | 412321 | 1586354 | 317271 | 1269083 | 42145539 | 8375217 | 33500870 | 515402 | 103081 | 412321 | 1586354 | 317271 | 1269083 | 0 | 0 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | CCI | 2010 | Q4 | Q4 - 2010 | 14660970 | 2932194 | 11728776 | 131919 | 26384 | 105535 | 1000000 | 200000 | 800000 | 269450 | 0 | 0 | 21432 | 4286 | 17146 | 0 | 0 | 0 | 1628750 | 325750 | 1303000 | 741282 | 148256 | 593026 | 250000 | 50000 | 200000 | 4110896 | 822179 | 3288717 | 35700 | 7140 | 28560 | 0 | 0 | 0 | 250000 | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 557000 | 111400 | 445600 | 5723 | 1145 | 4578 | 125000 | 25000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 103410 | 413640 | 0 | 0 | 0 | 0 | 0 | 0 | 20113922 | 4022784 | 16091137 | 96056 | 19211 | 76845 | 1000000 | 200000 | 800000 | 37500 | 7500 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42145538 | 8375217 | 33500870 | 1032112 | 206422 | 825690 | 2375000 | 475000 | 1900000 | 42145538 | 8375217 | 33500870 | 1032112 | 206422 | 825690 | 2375000 | 475000 | 1900000 | 0 | 0 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | CCI | 2011 | Q1 | Q1 - 2011 | 14660971 | 3057253 | 11603718 | 415485 | 83097 | 332388 | 3120247 | 624049 | 2496198 | 269450 | 56188 | 213262 | 21432 | 4286 | 17146 | 41432 | 8286 | 33146 | 1628750 | 339643 | 1289107 | 976968 | 195394 | 781575 | 1219010 | 243802 | 975208 | 4110896 | 857245 | 3253651 | 43200 | 8640 | 34560 | 50200 | 10040 | 40160 | 250000 | 52133 | 197867 | 0 | 0 | 0 | 0 | 0 | 0 | 557000 | 116151 | 440849 | 5723 | 1145 | 4578 | 10723 | 2145 | 8578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 107820 | 409230 | 0 | 0 | 0 | 50000 | 10000 | 40000 | 20113922 | 4194357 | 15919565 | 225116 | 45023 | 180092 | 411268 | 82254 | 329014 | 37500 | 7820 | 29680 | 0 | 0 | 0 | 0 | 0 | 0 | 168810 | 35202 | 133608 | 0 | 0 | 0 | 0 | 0 | 0 | 42314349 | 8823812 | 33490537 | 1687924 | 337585 | 1350339 | 4902880 | 980576 | 3922304 | 42314349 | 8823812 | 33490537 | 1687924 | 337585 | 1350339 | 4902880 | 980576 | 3922304 | 0 | 0 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | CCI | 2011 | Q2 | Q2 - 2011 | 14660971 | 3057253 | 11603718 | 1622320 | 324464 | 1297856 | 8750000 | 1750000 | 7000000 | 269450 | 56188 | 213262 | 21432 | 4286 | 17146 | 31500 | 6300 | 25200 | 1628750 | 339643 | 1289107 | 1146587 | 229318 | 917269 | 1500000 | 300000 | 1200000 | 4110896 | 857245 | 3253651 | 86081 | 17216 | 68865 | 266081 | 53216 | 212865 | 250000 | 52133 | 197867 | 0 | 0 | 0 | 25000 | 5000 | 20000 | 557000 | 116151 | 440849 | 5723 | 1145 | 4578 | 25000 | 5000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 107820 | 409230 | 0 | 0 | 0 | 20000 | 5000 | 20000 | 20113922 | 4194357 | 15919565 | 541697 | 108339 | 433358 | 2833923 | 566785 | 2267138 | 37500 | 7820 | 29680 | 0 | 0 | 0 | 5000 | 1000 | 4000 | 168810 | 35202 | 133608 | 0 | 0 | 0 | 0 | 0 | 0 | 42314349 | 8823812 | 33490537 | 3423840 | 684768 | 2739072 | 13456504 | 2692301 | 10769203 | 42314349 | 8823812 | 33490537 | 3423840 | 684768 | 2739072 | 13456504 | 2692301 | 10769203 | 0 | 0 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | CCI | 2011 | Q3 | Q3 - 2011 | 14660971 | 3057253 | 11603718 | 7748777 | 1549756 | 6199021 | 11902121 | 2380424 | 9521697 | 269450 | 56188 | 213262 | 21432 | 4286 | 17146 | 224450 | 44890 | 179560 | 1628750 | 339643 | 1289107 | 1376831 | 275366 | 1101465 | 1550730 | 310146 | 1240584 | 4110896 | 857245 | 3253651 | 98188 | 19638 | 78550 | 4589796 | 917959 | 3671837 | 250000 | 52133 | 197867 | 0 | 0 | 0 | 250000 | 50000 | 200000 | 557000 | 116151 | 440849 | 6051 | 1210 | 4841 | 445694 | 89139 | 356555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 107820 | 409230 | 0 | 0 | 0 | 486500 | 97300 | 389200 | 20113922 | 4194357 | 15919565 | 3196245 | 639249 | 2556996 | 8894859 | 1778972 | 7115887 | 37500 | 7820 | 29680 | 0 | 0 | 0 | 37500 | 7500 | 30000 | 168810 | 35202 | 133608 | 0 | 0 | 0 | 0 | 0 | 0 | 42314349 | 8823812 | 33490537 | 12447524 | 2489505 | 9958019 | 28381650 | 5676330 | 22705320 | 42314349 | 8823812 | 33490537 | 12447524 | 2489505 | 9958019 | 28381650 | 5676330 | 22705320 | 0 | 0 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | CCI | 2011 | Q4 | Q4 - 2011 | 14660971 | 3057253 | 11603718 | 13034983 | 2632865 | 10402118 | 13504983 | 2683331 | 10803986 | 269450 | 56188 | 213262 | 101266 | 20454 | 80812 | 153488 | 30698 | 122790 | 1628750 | 339643 | 1289107 | 1604219 | 323985 | 1280234 | 1936568 | 387314 | 1549254 | 4110896 | 857245 | 3253651 | 4072706 | 863500 | 3209206 | 4233290 | 863500 | 3386632 | 250000 | 52133 | 197867 | 13187 | 2664 | 10524 | 49517 | 9903 | 39614 | 557000 | 116151 | 440849 | 54647 | 11038 | 43609 | 357589 | 71518 | 286071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 107820 | 409230 | 21203 | 4283 | 16920 | 26203 | 5241 | 20962 | 20113922 | 4194357 | 15919565 | 8155671 | 1582870 | 6572801 | 11251597 | 2250319 | 9001278 | 37500 | 7820 | 29680 | 11000 | 2222 | 8778 | 16000 | 3200 | 12800 | 168810 | 35202 | 133608 | 207525 | 41917 | 165608 | 207525 | 41917 | 166020 | 42314349 | 8823812 | 33490537 | 27276407 | 5485798 | 21790610 | 31736760 | 6346941 | 25389407 | 42314349 | 8823812 | 33490537 | 27276407 | 5485798 | 21790610 | 31736760 | 6346941 | 25389407 | 0 | 0 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | CCI | 2012 | Q1 | Q1 - 2012 | 14660971 | 3057253 | 11603718 | 13428633 | 2682441 | 10746192 | 14243985 | 2848797 | 11395188 | 269450 | 56188 | 213262 | 101266 | 20253 | 81013 | 262396 | 52479 | 209917 | 1628750 | 339643 | 1289107 | 1715640 | 343128 | 1372512 | 2138995 | 427799 | 1711196 | 4110896 | 857245 | 3253651 | 4277806 | 863500 | 3414306 | 4576603 | 915321 | 3661282 | 250000 | 52133 | 197867 | 18779 | 3756 | 15023 | 73668 | 14734 | 58934 | 557000 | 116151 | 440849 | 79009 | 15802 | 63207 | 514242 | 102848 | 411393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 107820 | 409230 | 21203 | 4241 | 16962 | 28203 | 5641 | 22562 | 20113922 | 4194357 | 15919565 | 8512930 | 1697932 | 6814998 | 13630013 | 2726003 | 10904011 | 37500 | 7820 | 29680 | 11000 | 2200 | 8800 | 11000 | 2200 | 8800 | 168810 | 35202 | 133608 | 207525 | 41505 | 166020 | 207525 | 41505 | 166020 | 42314349 | 8823812 | 33490537 | 28373791 | 5674758 | 22699033 | 35686630 | 7137327 | 28549303 | 42314349 | 8823812 | 33490537 | 28373791 | 5674758 | 22699033 | 35686630 | 7137327 | 28549303 | 0 | 0 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | CCI | 2012 | Q2 | Q2 - 2012 | 14660971 | 3057253 | 11603718 | 14137676 | 2824250 | 11313426 | 14435596 | 2883834 | 11551762 | 269450 | 56188 | 213262 | 101266 | 20253 | 81013 | 118746 | 23749 | 94997 | 1628750 | 339643 | 1289107 | 1875266 | 375053 | 1500213 | 2527765 | 505553 | 2022212 | 4110896 | 857245 | 3253651 | 4434271 | 894793 | 3539478 | 4596518 | 927242 | 3669276 | 250000 | 52133 | 197867 | 18779 | 3756 | 15023 | 32579 | 6516 | 26063 | 557000 | 116151 | 440849 | 117410 | 23482 | 93928 | 370411 | 74082 | 296327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 107820 | 409230 | 21203 | 4241 | 16962 | 21203 | 4241 | 16962 | 20113922 | 4194357 | 15919565 | 10721455 | 2139637 | 8581818 | 16609509 | 3317249 | 13292262 | 37500 | 7820 | 29680 | 11000 | 2200 | 8800 | 11000 | 2200 | 8800 | 168810 | 35202 | 133608 | 207525 | 41505 | 166020 | 207525 | 41505 | 166020 | 42314349 | 8823812 | 33490537 | 31645851 | 6329170 | 25316681 | 38930852 | 7786171 | 31144681 | 42314349 | 8823812 | 33490537 | 31645851 | 6329170 | 25316681 | 38930852 | 7786171 | 31144681 | 0 | 0 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | CCI | 2012 | Q3 | Q3 - 2012 | 14660971 | 3057253 | 11603718 | 14499344 | 2896583 | 11602761 | 16270387 | 3392864 | 12877523 | 269450 | 56188 | 213262 | 101266 | 20253 | 81013 | 209902 | 43771 | 166131 | 1628750 | 339643 | 1289107 | 2140994 | 428199 | 1712795 | 2686025 | 560117 | 2125908 | 4110896 | 857245 | 3253651 | 5867039 | 1181347 | 4685692 | 5997692 | 1250699 | 4746993 | 250000 | 52133 | 197867 | 18779 | 3756 | 15023 | 21625 | 4510 | 17116 | 557000 | 116151 | 440849 | 181355 | 36271 | 145084 | 290257 | 60527 | 229730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517050 | 107820 | 409230 | 73248 | 14650 | 58598 | 73248 | 14650 | 58598 | 20113922 | 4194357 | 15919565 | 13271019 | 2649550 | 10621469 | 16546688 | 3452969 | 13093718 | 37500 | 7820 | 29680 | 11000 | 2200 | 8800 | 11000 | 2200 | 8800 | 168810 | 35202 | 133608 | 207525 | 41505 | 166020 | 207525 | 41505 | 166020 | 42314349 | 8823812 | 33490537 | 36371569 | 7274314 | 29097255 | 42314349 | 8823812 | 33490537 | 42314349 | 8823812 | 33490537 | 36371569 | 7274314 | 29097255 | 42314349 | 8823812 | 33490537 | 0 | 188730 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570004 | CCI | 2012 | Q4 | Q4 - 2012 | 15460345 | 3092069 | 12368276 | 15359463 | 3071893 | 12287570 | 15359963 | 3071993 | 12287970 | 147875 | 29575 | 118300 | 125729 | 25146 | 100583 | 136929 | 27386 | 109543 | 2731699 | 546339 | 2185360 | 2517847 | 503569 | 2014278 | 2593847 | 518768 | 2075079 | 6033034 | 1206606 | 4826428 | 6064642 | 1212928 | 4851714 | 6065117 | 1213023 | 4852094 | 22589 | 4518 | 18071 | 22589 | 4518 | 18071 | 22589 | 4518 | 18071 | 277062 | 55413 | 221649 | 271854 | 54371 | 217483 | 338354 | 67671 | 270683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73248 | 14650 | 58598 | 73248 | 14650 | 58598 | 73248 | 14650 | 58598 | 16880394 | 3376079 | 13504315 | 16811131 | 3362226 | 13448905 | 17036199 | 3407240 | 13628959 | 11000 | 2200 | 8800 | 11000 | 2200 | 8800 | 11000 | 2200 | 8800 | 225925 | 45185 | 180740 | 225925 | 45185 | 180740 | 225925 | 45185 | 180740 | 41863171 | 8372634 | 33490537 | 41483428 | 8296686 | 33186742 | 41863171 | 8372634 | 33490537 | 41863171 | 8372634 | 33490537 | 41483428 | 8296686 | 33186742 | 41863171 | 8372634 | 33490537 | 0 | 367490 | North Georgia Network Cooperative, Inc. | TRUE
NT10BIX5570006 | CCI | 2010 | Q3 | Q3 - 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994907.6 | 198981.52 | 795926.08 | 994907.6 | 198981.52 | 795926.08 | 0 | 0 | Biddeford Internet Corp. | TRUE
NT10BIX5570007 | CCI | 2010 | Q3 | Q3 - 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 982033.13 | 196406.62 | 785626.51 | 982033.13 | 196406.62 | 785626.51 | 0 | 0 | ION HOLDCO, LLC | TRUE
NT10BIX5570009 | CCI | 2010 | Q3 | Q3 - 2010 | 5485955 | 1097192 | 4388763 | 156 | 31 | 125 | 548751 | 109750 | 439001 | 25357463 | 5071492 | 20285971 | 0 | 0 | 0 | 507149 | 101430 | 405719 | 422027 | 84405 | 337622 | 176369 | 35273 | 141096 | 202512 | 40502 | 162010 | 676200 | 135240 | 540959 | 156546 | 31309 | 125237 | 596076 | 119215 | 476861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 117603 | 23521 | 94082 | 1803778 | 360756 | 1443022 | 1424305 | 284861 | 1139444 | 97158 | 19432 | 77726 | 243205 | 48641 | 194564 | 1690497 | 338100 | 1352398 | 0 | 0 | 0 | 0 | 0 | 0 | 1696897 | 339380 | 1357518 | 0 | 0 | 0 | 169690 | 33938 | 135752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 22699 | 4540 | 18159 | 42699 | 8540 | 34159 | 41611527 | 8322306 | 33289222 | 570531 | 114106 | 456425 | 4113860 | 822772 | 3291088 | 41611527 | 8322306 | 33289222 | 570531 | 114106 | 456425 | 4113860 | 822772 | 3291088 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570009 | CCI | 2010 | Q4 | Q4 - 2010 | 5485955 | 1097191 | 4388764 | 0 | 0 | 0 | 1645944 | 329189 | 1316755 | 25357463 | 5071493 | 20285970 | 175546 | 35109 | 140437 | 2539621 | 507924 | 2031697 | 422027 | 84405 | 337622 | 166701 | 33340 | 133361 | 229043 | 45809 | 183234 | 676199 | 135240 | 540959 | 464205 | 92841 | 371364 | 676199 | 135240 | 540959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 400953 | 80191 | 320762 | 2873826 | 574765 | 2299061 | 1424305 | 284861 | 1139444 | 253419 | 50684 | 202735 | 247923 | 49585 | 198338 | 1690497 | 338099 | 1352398 | 0 | 0 | 0 | 0 | 0 | 0 | 1696897 | 339379 | 1357518 | 0 | 0 | 0 | 343342 | 68668 | 274674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30966 | 123861 | 72369 | 14474 | 57895 | 88459 | 17692 | 70767 | 41611526 | 8322305 | 33289221 | 1533193 | 306639 | 1226554 | 8644357 | 1728872 | 6915485 | 41611526 | 8322305 | 33289221 | 1533193 | 306639 | 1226554 | 8644357 | 1728872 | 6915485 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570009 | CCI | 2011 | Q1 | Q1 - 2011 | 5485955 | 1097192 | 4388763 | 542069 | 108414 | 433655 | 987472 | 197494 | 789978 | 25357463 | 5071492 | 20285971 | 582841 | 116568 | 466273 | 1081918 | 216384 | 865535 | 422027 | 84405 | 337622 | 136710 | 27342 | 109368 | 159496 | 31899 | 127596 | 676199 | 135240 | 540959 | 1166334 | 233267 | 933067 | 1169824 | 233965 | 935859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 953946 | 190789 | 763156 | 1005946 | 201189 | 804756 | 1424305 | 284861 | 1139444 | 154417 | 30883 | 123533 | 180153 | 36031 | 144122 | 1690497 | 338100 | 1352398 | 0 | 0 | 0 | 0 | 0 | 0 | 1696897 | 339380 | 1357518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 84935 | 16987 | 67948 | 99091 | 19818 | 79273 | 41611526 | 8322306 | 33289222 | 3621252 | 724250 | 2897000 | 4683900 | 936780 | 3747119 | 41611526 | 8322306 | 33289222 | 3621252 | 724250 | 2897000 | 4683900 | 936780 | 3747119 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570009 | CCI | 2011 | Q2 | Q2 - 2011 | 5485955 | 1097192 | 4388763 | 825184 | 165037 | 660147 | 1601979 | 320396 | 1281583 | 25357463 | 5071492 | 20285971 | 2148789 | 429758 | 1719031 | 6016901 | 1203380 | 4813521 | 422027 | 84405 | 337622 | 210923 | 42185 | 168738 | 246107 | 49221 | 196885 | 676199 | 135240 | 540959 | 1324011 | 264802 | 1059209 | 1325702 | 265140 | 1060561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 1042322 | 208464 | 833858 | 1652495 | 330499 | 1321996 | 1424305 | 284861 | 1139444 | 112720 | 22544 | 90176 | 331318 | 66264 | 265054 | 1690497 | 338100 | 1352398 | 0 | 0 | 0 | 281749 | 56350 | 225400 | 1696897 | 339380 | 1357518 | 0 | 0 | 0 | 282816 | 56563 | 226253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 128957 | 25791 | 103166 | 150450 | 30090 | 120360 | 41611526 | 8322306 | 33289222 | 5792906 | 1158581 | 4634325 | 11889517 | 2377903 | 9511613 | 41611526 | 8322306 | 33289222 | 5792906 | 1158581 | 4634325 | 11889517 | 2377903 | 9511613 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570009 | CCI | 2011 | Q3 | Q3 - 2011 | 5485955 | 1097192 | 4388763 | 825184 | 165037 | 660147 | 1712847 | 342573 | 1370293 | 25357463 | 5071492 | 20285971 | 5116034 | 1023207 | 4092828 | 17686214 | 3537243 | 14148971 | 422027 | 84405 | 337622 | 246967 | 49393 | 197573 | 266832 | 53366 | 213466 | 676199 | 135240 | 540959 | 1604156 | 320831 | 1283325 | 1609156 | 321831 | 1287325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 1209895 | 241979 | 967916 | 2038706 | 407741 | 163095 | 1424305 | 284861 | 1139444 | 199857 | 39972 | 159885 | 509677 | 101935 | 407741 | 1690497 | 338100 | 1352398 | 0 | 0 | 0 | 0 | 0 | 0 | 1696897 | 339380 | 1357518 | 1545 | 309 | 1236 | 47199 | 9440 | 37759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 134600 | 26920 | 107680 | 266832 | 53366 | 213466 | 41611526 | 8322306 | 33289222 | 9338238 | 1867648 | 7470590 | 24137463 | 4827495 | 17842116 | 41611526 | 8322306 | 33289222 | 9338238 | 1867648 | 7470590 | 24137463 | 4827495 | 17842116 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570009 | CCI | 2011 | Q4 | Q4 - 2011 | 5485955 | 1097192 | 4388763 | 1123892 | 224778 | 899114 | 1712867 | 342573 | 1370294 | 25357463 | 5071492 | 20285971 | 9744308 | 1948862 | 7795446 | 18864952 | 3772990 | 15091961 | 422027 | 84405 | 337622 | 264893 | 52978 | 211915 | 296480 | 59296 | 237184 | 676199 | 135240 | 540959 | 1797399 | 359480 | 1437919 | 1847338 | 369468 | 1477870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 1323164 | 264633 | 1058531 | 2463347 | 492669 | 1970678 | 1424305 | 284861 | 1139444 | 298273 | 59655 | 238618 | 615837 | 123167 | 492670 | 1690497 | 338100 | 1352398 | 0 | 0 | 0 | 0 | 0 | 0 | 1696897 | 339380 | 1357518 | 1545 | 309 | 1236 | 96208 | 19242 | 76966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 244426 | 48885 | 195541 | 247653 | 49531 | 198122 | 41611526 | 8322306 | 33289222 | 14797900 | 2959580 | 11838320 | 26144682 | 5228936 | 20915745 | 41611526 | 8322306 | 33289222 | 14797900 | 2959580 | 11838320 | 26144682 | 5228936 | 20915745 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570009 | CCI | 2012 | Q1 | Q1 - 2012 | 5485955 | 1097192 | 4388763 | 2545586 | 509117 | 2036469 | 3570430 | 714086 | 2856344 | 25357463 | 5071492 | 20285971 | 11302052 | 2260410 | 9041642 | 16997686 | 3399537 | 13598149 | 422027 | 84405 | 337622 | 278384 | 55677 | 222707 | 304291 | 60858 | 243433 | 676199 | 135240 | 540959 | 1822357 | 364472 | 1457885 | 1859775 | 371955 | 1487820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 1713394 | 342679 | 1370715 | 2702571 | 540514 | 2162057 | 1424305 | 284861 | 1139444 | 374950 | 74990 | 299960 | 675643 | 135129 | 540514 | 1690497 | 338100 | 1352397 | 1545 | 309 | 1236 | 125745 | 25149 | 100596 | 1696897 | 339380 | 1357517 | 7140 | 1428 | 5712 | 21419 | 4284 | 17135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 284801 | 56960 | 227841 | 302861 | 60572 | 242289 | 41611526 | 8322306 | 33289220 | 18330209 | 3666042 | 14664167 | 26560421 | 5312084 | 21248337 | 41611526 | 8322306 | 33289220 | 18330209 | 3666042 | 14664167 | 26560421 | 5312084 | 21248337 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570009 | CCI | 2012 | Q2 | Q2 - 2012 | 5485955 | 1097192 | 4388763 | 3661640 | 732328 | 2929312 | 4967280 | 993456 | 3973824 | 25357463 | 5071492 | 20285971 | 14411518 | 2882304 | 11529214 | 23884620 | 4776924 | 19107696 | 422027 | 84405 | 337622 | 282459 | 56492 | 225967 | 340728 | 68146 | 272582 | 676199 | 135240 | 540959 | 1871520 | 374304 | 1497216 | 1919926 | 383985 | 1535941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 1881506 | 376301 | 1505205 | 3801966 | 760393 | 3041573 | 1424305 | 284861 | 1139444 | 417293 | 83459 | 333835 | 950491 | 190098 | 760393 | 1690497 | 338100 | 1352397 | 1545 | 309 | 1236 | 154952 | 30990 | 123962 | 1696897 | 339380 | 1357517 | 7140 | 1428 | 5712 | 21419 | 4284 | 17135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 287452 | 57490 | 229961 | 292153 | 58431 | 233722 | 41611526 | 8322306 | 33289220 | 22822073 | 4564415 | 18257658 | 36333535 | 7266707 | 29066828 | 41611526 | 8322306 | 33289220 | 22822073 | 4564415 | 18257658 | 36333535 | 7266707 | 29066828 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570009 | CCI | 2012 | Q3 | Q3 - 2012 | 5485955 | 1097192 | 4388763 | 5032749 | 1006550 | 4026199 | 5485955 | 1097191 | 4388764 | 25357463 | 5071492 | 20285971 | 19451910 | 3890382 | 15561528 | 25357463 | 5071493 | 20285970 | 422027 | 84405 | 337622 | 282459 | 56492 | 225967 | 400926 | 80185 | 320741 | 676199 | 135240 | 540959 | 1937131 | 387426 | 1549705 | 2037131 | 407426 | 1629705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 1970122 | 394024 | 1576098 | 3173453 | 634691 | 2538763 | 1424305 | 284861 | 1139444 | 605456 | 121091 | 484365 | 1424305 | 284861 | 1139444 | 1690497 | 338100 | 1352397 | 1545 | 309 | 1236 | 1690497 | 338099 | 1352398 | 1696897 | 339380 | 1357517 | 7140 | 1428 | 5712 | 1696897 | 339379 | 1357518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 303796 | 60759 | 243037 | 323798 | 64760 | 259037 | 41611526 | 8322306 | 33289220 | 29592308 | 5918461 | 23673847 | 41590425 | 8318085 | 33272340 | 41611526 | 8322306 | 33289220 | 29592308 | 5918461 | 23673847 | 41590425 | 8318085 | 33272340 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570009 | CCI | 2012 | Q4 | Q4 - 2012 | 5485955 | 1097192 | 4388763 | 5588992 | 1117798 | 4471193 | 5640511 | 1128102 | 4512409 | 25357463 | 5071492 | 20285971 | 26521466 | 5304293 | 21217173 | 27147862 | 5429572 | 21718289 | 422027 | 84405 | 337622 | 287656 | 57531 | 230125 | 302876 | 60575 | 242301 | 676199 | 135240 | 540959 | 1956183 | 391237 | 1564946 | 1956183 | 391237 | 1564946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 2036199 | 407240 | 1628959 | 4808102 | 961620 | 3846481 | 1424305 | 284861 | 1139444 | 813134 | 162627 | 650507 | 1194511 | 238902 | 955609 | 1690497 | 338100 | 1352397 | 1545 | 309 | 1236 | 184160 | 36832 | 147328 | 1696897 | 339380 | 1357517 | 7140 | 1428 | 5712 | 7140 | 1428 | 5712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 354273 | 70855 | 283419 | 370181 | 74038 | 296143 | 41611526 | 8322306 | 33289220 | 37566588 | 7513318 | 30053270 | 41611526 | 8322306 | 33289218 | 41611526 | 8322306 | 33289220 | 37566588 | 7513318 | 30053270 | 41611526 | 8322306 | 33289218 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570009 | CCI | 2013 | Q1 | Q1 - 2013 | 5485955 | 1097192 | 4388763 | 5757525 | 1151505 | 4606020 | 5757525 | 1151505 | 4606020 | 25357463 | 5071492 | 20285971 | 29158902 | 5831780 | 23327122 | 29915349 | 5983070 | 23932280 | 422027 | 84405 | 337622 | 287656 | 57531 | 230125 | 291325 | 58265 | 233060 | 676199 | 135240 | 540959 | 1486230 | 297246 | 1188984 | 1486230 | 297246 | 1188984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 2077535 | 415507 | 1662028 | 2283919 | 456784 | 1827135 | 1424305 | 284861 | 1139444 | 842147 | 168429 | 673717 | 842147 | 168429 | 673717 | 1690497 | 338100 | 1352397 | 1545 | 309 | 1236 | 182630 | 36526 | 146104 | 1696897 | 339380 | 1357517 | 10858 | 2172 | 8686 | 10858 | 2172 | 8686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 366340 | 73268 | 293073 | 370777 | 74156 | 296622 | 41611526 | 8322306 | 33289220 | 39988738 | 7997747 | 31990991 | 41140760 | 8228153 | 32912608 | 41611526 | 8322306 | 33289220 | 39988738 | 7997747 | 31990991 | 41140760 | 8228153 | 32912608 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570009 | CCI | 2013 | Q2 | Q2 - 2013 | 5485955 | 1097192 | 4388763 | 5757525 | 1151505 | 4606020 | 5757525 | 1151505 | 4606020 | 25357463 | 5071492 | 20285971 | 29871066 | 5974213 | 23896852 | 29966712 | 5993343 | 23973369 | 422027 | 84405 | 337622 | 287656 | 57531 | 230125 | 287656 | 57531 | 230125 | 676199 | 135240 | 540959 | 1525958 | 305192 | 1220767 | 1525958 | 305192 | 1220767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4703356 | 940671 | 3762685 | 2105954 | 421191 | 1684763 | 2249423 | 449885 | 1799538 | 1424305 | 284861 | 1139444 | 1206147 | 241229 | 964918 | 1349617 | 269925 | 1079692 | 1690497 | 338100 | 1352397 | 1545 | 309 | 1236 | 49368 | 9874 | 39494 | 1696897 | 339380 | 1357517 | 11010 | 2202 | 8808 | 11010 | 2202 | 8808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154827 | 30965 | 123862 | 366435 | 73287 | 293148 | 414257 | 82849 | 331407 | 41611526 | 8322306 | 33289220 | 41133296 | 8226659 | 32906637 | 41611526 | 8322306 | 33289220 | 41611526 | 8322306 | 33289220 | 41133296 | 8226659 | 32906637 | 41611526 | 8322306 | 33289220 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570009 | CCI | 2013 | Q3 | Q3 - 2013 | 5883232 | 1176646 | 4706586 | 5966394 | 1259808 | 4706586 | 5966394 | 1259808 | 4706586 | 26194837 | 5249501 | 20945336 | 26356884 | 5411548 | 20945336 | 26356884 | 5411548 | 20945336 | 733260 | 146652 | 586608 | 855266 | 268658 | 586608 | 855266 | 268658 | 586608 | 5739050 | 1147810 | 4591240 | 5703683 | 1112443 | 4591240 | 5703683 | 1112443 | 4591240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1422664 | 284533 | 1138131 | 1608230 | 470099 | 1138131 | 1608230 | 470099 | 1138131 | 1354550 | 270910 | 1083640 | 1207036 | 123396 | 1083640 | 1207036 | 123396 | 1083640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231266 | 46253 | 185013 | 212403 | 27390 | 185013 | 212403 | 27390 | 185013 | 41558859 | 8322305 | 33236554 | 41909896 | 8673342 | 33236554 | 41909896 | 8673342 | 33236554 | 41558859 | 8322305 | 33236554 | 41909896 | 8673342 | 33236554 | 41909896 | 8673342 | 33236554 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570011 | CCI | 2010 | Q3 | Q3 - 2010 | 6415529 | 4346473 | 2069056 | 0 | 0 | 0 | 300000 | 662582 | 233748 | 32081915 | 7084933 | 24996982 | 500 | 111 | 389 | 1424071 | 314490 | 1109581 | 329500 | 72766 | 256734 | 279494 | 61723 | 217771 | 300000 | 66252 | 233748 | 150000 | 33126 | 116874 | 0 | 0 | 0 | 27550 | 6084 | 21466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1005142 | 221974 | 783168 | 925509 | 204388 | 721121 | 1005142 | 221974 | 783168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3470 | 766 | 2704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39985556 | 11760038 | 28225518 | 1205503 | 266222 | 939281 | 3056763 | 1271382 | 2381711 | 39985556 | 11760038 | 28225518 | 1205503 | 266222 | 939281 | 3056763 | 1271382 | 2381711 | 0 | 0 | MCNC | TRUE
NT10BIX5570011 | CCI | 2010 | Q4 | Q4 - 2010 | 6415529 | 4346474 | 2069055 | 88 | 20 | 68 | 4105996 | 3621177 | 484819 | 31439915 | 6943153 | 24496762 | 223811 | 49426 | 174385 | 8587467 | 1896446 | 6691021 | 379500 | 83808 | 295692 | 310802 | 68637 | 242165 | 370802 | 81887 | 288915 | 350000 | 77294 | 272706 | 212373 | 46900 | 165473 | 270829 | 59810 | 211019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397142 | 308543 | 1088599 | 1438478 | 317672 | 1120806 | 1589341 | 350988 | 1238353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3470 | 766 | 2704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39985556 | 11760038 | 28225518 | 2185552 | 482655 | 1702897 | 14924435 | 6010308 | 8914127 | 39985556 | 11760038 | 28225518 | 2185552 | 482655 | 1702897 | 14924435 | 6010308 | 8914127 | 0 | 0 | MCNC | TRUE
NT10BIX5570011 | CCI | 2011 | Q1 | Q1 - 2011 | 6415529 | 4346474 | 2069055 | 3133472 | 2473601 | 659871 | 3843351 | 2630370 | 1212981 | 31439915 | 6943153 | 24496762 | 3112656 | 687395 | 2425261 | 14728785 | 3252687 | 11476098 | 379500 | 83808 | 295692 | 356718 | 78777 | 277941 | 381718 | 84298 | 297420 | 350000 | 77294 | 272706 | 318428 | 70321 | 248107 | 328428 | 72530 | 255898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397142 | 308543 | 1088599 | 1577058 | 348276 | 1228782 | 1696017 | 374546 | 1321471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3470 | 766 | 2704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39985556 | 11760038 | 28225518 | 8498332 | 3658370 | 4839962 | 20978299 | 6414431 | 14563868 | 39985556 | 11760038 | 28225518 | 8498332 | 3658370 | 4839962 | 20978299 | 6414431 | 14563868 | 0 | 0 | MCNC | TRUE
NT10BIX5570011 | CCI | 2011 | Q2 | Q2 - 2011 | 6415529 | 4346474 | 2069055 | 3928115 | 2649089 | 1279026 | 4750000 | 2830593 | 1919407 | 31439915 | 6943153 | 24496762 | 14623077 | 3914995 | 10708082 | 23000000 | 5079292 | 17920708 | 379500 | 83808 | 295692 | 409949 | 98324 | 311625 | 450000 | 99377 | 350623 | 350000 | 77294 | 272706 | 362267 | 80002 | 282265 | 383475 | 84686 | 298789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397142 | 308543 | 1088599 | 1750579 | 386596 | 1363983 | 1800000 | 397510 | 1402490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3470 | 766 | 2704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39985556 | 11760038 | 28225518 | 21073987 | 7129006 | 13944981 | 30383475 | 8491458 | 21892017 | 39985556 | 11760038 | 28225518 | 21073987 | 7129006 | 13944981 | 30383475 | 8491458 | 21892017 | 0 | 0 | MCNC | TRUE
NT10BIX5570011 | CCI | 2011 | Q3 | Q3 - 2011 | 6415529 | 4346474 | 2069055 | 4590513 | 2795372 | 1795141 | 4700000 | 2819551 | 1880449 | 31439915 | 6943153 | 24496762 | 16189408 | 3575250 | 12614158 | 21000000 | 4637615 | 16362385 | 379500 | 83808 | 295692 | 416395 | 91956 | 324439 | 420000 | 92752 | 327248 | 350000 | 77294 | 272706 | 361727 | 79883 | 281844 | 395000 | 87231 | 307769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397142 | 308543 | 1088599 | 1667908 | 368339 | 1299569 | 1750000 | 386468 | 1363532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3470 | 766 | 2704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39985556 | 11760038 | 28225518 | 23225951 | 6910800 | 16315151 | 28265000 | 8023617 | 20241383 | 39985556 | 11760038 | 28225518 | 23225951 | 6910800 | 16315151 | 28265000 | 8023617 | 20241383 | 0 | 0 | MCNC | TRUE
NT10BIX5570011 | CCI | 2011 | Q4 | Q4 - 2011 | 6415529 | 4346474 | 2069055 | 5059652 | 2898976 | 2160676 | 5119410 | 2912173 | 2207237 | 31439915 | 6943153 | 24496762 | 19342352 | 4271542 | 15070810 | 23457500 | 5180326 | 18277174 | 379500 | 83808 | 295692 | 435768 | 96234 | 339534 | 535000 | 118149 | 416851 | 350000 | 77294 | 272706 | 399108 | 88139 | 310969 | 415000 | 91648 | 323352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397142 | 308543 | 1088599 | 1772855 | 391515 | 1381340 | 1813000 | 400381 | 1412619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3470 | 766 | 2704 | 3717 | 821 | 2896 | 3717 | 821 | 2896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39985556 | 11760038 | 28225518 | 27013452 | 7747227 | 19266225 | 31343627 | 8703498 | 22640129 | 39985556 | 11760038 | 28225518 | 27013452 | 7747227 | 19266225 | 31343627 | 8703498 | 22640129 | 0 | 0 | MCNC | TRUE
NT10BIX5570011 | CCI | 2012 | Q1 | Q1 - 2012 | 4942064 | 2873009 | 2069055 | 5108820 | 2909835 | 2198985 | 5108820 | 2909835 | 2198985 | 31439915 | 6943153 | 24496762 | 22120396 | 4885042 | 17235354 | 25120396 | 5547558 | 19572838 | 379500 | 83808 | 295692 | 451918 | 99801 | 352117 | 451918 | 99801 | 352117 | 350000 | 77294 | 272706 | 429734 | 94902 | 334832 | 434734 | 96006 | 338728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1397142 | 308543 | 1088599 | 1784937 | 394183 | 1390754 | 1834937 | 405225 | 1429712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3470 | 766 | 2704 | 3717 | 821 | 2896 | 3717 | 821 | 2896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38512091 | 10286573 | 28225518 | 29899522 | 8384584 | 21514938 | 32954522 | 9059246 | 23895276 | 38512091 | 10286573 | 28225518 | 29899522 | 8384584 | 21514938 | 32954522 | 9059246 | 23895276 | 0 | 0 | MCNC | TRUE
NT10BIX5570011 | CCI | 2012 | Q2 | Q2 - 2012 | 8470800 | 3652290 | 4818510 | 5679353 | 2751437 | 2927916 | 6000000 | 2822248 | 3177752 | 27250151 | 6017891 | 21232260 | 23954045 | 5574376 | 18379669 | 26791000 | 6200886 | 20590114 | 476900 | 105318 | 371582 | 460797 | 101762 | 359035 | 469797 | 103749 | 366048 | 430000 | 94961 | 335039 | 435479 | 96171 | 339308 | 440000 | 97169 | 342831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1884240 | 416113 | 1468127 | 1795562 | 396530 | 1399032 | 1884240 | 416113 | 1468127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38512091 | 10286573 | 28225518 | 32325236 | 8920276 | 23404960 | 35585037 | 9640165 | 25944872 | 38512091 | 10286573 | 28225518 | 32325236 | 8920276 | 23404960 | 35585037 | 9640165 | 25944872 | 0 | 0 | MCNC | TRUE
NT10BIX5570011 | CCI | 2012 | Q3 | Q3 - 2012 | 8470800 | 3652290 | 4818510 | 8151321 | 3297343 | 4853978 | 8470800 | 3367896 | 5102904 | 27250151 | 6017891 | 21232260 | 24267299 | 5643555 | 18623744 | 25794953 | 5980920 | 19814033 | 476900 | 105318 | 371582 | 463156 | 102283 | 360873 | 468000 | 103353 | 364647 | 430000 | 94961 | 335039 | 440400 | 97258 | 343142 | 441000 | 97390 | 343610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1884240 | 416113 | 1468127 | 1863311 | 411491 | 1451820 | 1900000 | 419594 | 1480406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38512091 | 10286573 | 28225518 | 35185487 | 9551930 | 25633557 | 37074753 | 9969153 | 27105600 | 38512091 | 10286573 | 28225518 | 35185487 | 9551930 | 25633557 | 37074753 | 9969153 | 27105600 | 0 | 0 | MCNC | TRUE
NT10BIX5570011 | CCI | 2012 | Q4 | Q4 - 2012 | 8990427 | 3229401 | 5761026 | 8570391 | 3136640 | 5433751 | 8585000 | 3139867 | 5445133 | 26410266 | 6370055 | 20040211 | 26307654 | 6347395 | 19960259 | 26308000 | 6347471 | 19960529 | 466201 | 169207 | 296994 | 463599 | 102381 | 361218 | 465000 | 102690 | 362310 | 740417 | 97261 | 643156 | 445449 | 98372 | 347077 | 450000 | 99377 | 350623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1904780 | 420649 | 1484131 | 1936082 | 427562 | 1508520 | 1950000 | 430636 | 1519364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38512091 | 10286573 | 28225518 | 37723175 | 10112350 | 27610825 | 37758000 | 10120041 | 27637959 | 38512091 | 10286573 | 28225518 | 37723175 | 10112350 | 27610825 | 37758000 | 10120041 | 27637959 | 0 | 0 | MCNC | TRUE
NT10BIX5570011 | CCI | 2013 | Q1 | Q1 - 2013 | 8990427 | 3229401 | 5761026 | 8585017 | 33139870 | 5445147 | 9285135 | 3294483 | 5990652 | 26410266 | 6370055 | 20040211 | 26625672 | 6417625 | 20208047 | 26300643 | 6345846 | 19954797 | 466201 | 169207 | 296994 | 469390 | 103660 | 365730 | 470000 | 103794 | 366206 | 740417 | 97261 | 643156 | 458212 | 101191 | 357021 | 458212 | 101191 | 357021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1904780 | 420649 | 1484131 | 1964828 | 433910 | 1530918 | 1985000 | 438365 | 1546635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38512091 | 10286573 | 28225518 | 38103119 | 40196256 | 27906863 | 38498990 | 10283679 | 28215311 | 38512091 | 10286573 | 28225518 | 38103119 | 40196256 | 27906863 | 38498990 | 10283679 | 28215311 | 0 | 0 | MCNC | TRUE
NT10BIX5570011 | CCI | 2013 | Q2 | Q2 - 2013 | 8990427 | 3229401 | 5761026 | 8956144 | 3221829 | 5734315 | 8956144 | 3221829 | 5734315 | 26410266 | 6370055 | 20040211 | 26647777 | 6422507 | 20225270 | 26647777 | 6422507 | 20225270 | 466201 | 169207 | 296994 | 472530 | 104353 | 368177 | 472530 | 104353 | 368177 | 740417 | 97261 | 643156 | 460862 | 101776 | 359086 | 460862 | 101776 | 359086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1904780 | 420649 | 1484131 | 1970902 | 435252 | 1535650 | 1974778 | 436108 | 1538670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38512091 | 10286573 | 28225518 | 38508215 | 10285717 | 28222498 | 38512091 | 10286573 | 28225518 | 38512091 | 10286573 | 28225518 | 38508215 | 10285717 | 28222498 | 38512091 | 10286573 | 28225518 | 0 | 0 | MCNC | TRUE
NT10BIX5570011 | CCI | 2013 | Q3 | Q3 - 2013 | 8990427 | 3229401 | 5761026 | 8954245 | 3221410 | 5732835 | 8954245 | 3221410 | 5732835 | 26410266 | 6370055 | 20040211 | 26650831 | 6423181 | 20227650 | 26650831 | 6423181 | 20227650 | 466201 | 169207 | 296994 | 473791 | 104632 | 369159 | 473791 | 104632 | 369159 | 740417 | 97261 | 643156 | 454023 | 100266 | 353757 | 454023 | 100266 | 353757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1904780 | 420649 | 1484131 | 1979201 | 437084 | 1542117 | 1979201 | 437084 | 1542117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38512091 | 10286573 | 28225518 | 38512091 | 10286573 | 28225518 | 38512091 | 10286573 | 28225518 | 38512091 | 10286573 | 28225518 | 38512091 | 10286573 | 28225518 | 38512091 | 10286573 | 28225518 | 0 | 0 | MCNC | TRUE
NT10BIX5570016 | CCI | 2010 | Q3 | Q3 - 2010 | 300000 | 60000 | 240000 | 3220 | 0 | 3220 | 54025 | 10805 | 43220 | 5500000 | 1100000 | 4400000 | 0 | 0 | 0 | 996949 | 199390 | 797559 | 150000 | 30000 | 120000 | 47862 | 0 | 47862 | 97328 | 19466 | 77862 | 300000 | 60000 | 240000 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362500 | 72500 | 290000 | 29359 | 0 | 29359 | 199199 | 39840 | 159359 | 20000 | 4000 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 27000 | 108000 | 0 | 0 | 0 | 25000 | 5000 | 20000 | 90000 | 18000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 6925000 | 1385000 | 5540000 | 80441 | 0 | 80441 | 1385001 | 277001 | 1108000 | 6925000 | 1385000 | 5540000 | 80441 | 0 | 80441 | 1385001 | 277001 | 1108000 | 0 | 0 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | CCI | 2010 | Q4 | Q4 - 2010 | 300000 | 60000 | 240000 | 27953 | 20100 | 7853 | 47953 | 40100 | 7853 | 5500000 | 1100000 | 4400000 | 0 | 0 | 0 | 750000 | 0 | 750000 | 150000 | 30000 | 120000 | 51521 | 0 | 51521 | 81521 | 0 | 81521 | 300000 | 60000 | 240000 | 30708 | 30708 | 0 | 130708 | 130708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362500 | 72500 | 290000 | 192952 | 9819 | 183133 | 203021 | 9819 | 193202 | 20000 | 4000 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 27000 | 108000 | 0 | 0 | 0 | 13000 | 0 | 13000 | 90000 | 18000 | 72000 | 0 | 0 | 0 | 22000 | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 6925000 | 1385000 | 5540000 | 303134 | 60627 | 242507 | 1248203 | 180627 | 1067576 | 6925000 | 1385000 | 5540000 | 303134 | 60627 | 242507 | 1248203 | 180627 | 1067576 | 0 | 0 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | CCI | 2011 | Q1 | Q1 - 2011 | 300000 | 60000 | 240000 | 88443 | 88443 | 0 | 309667 | 309667 | 0 | 5500000 | 1100000 | 4400000 | 151323 | 0 | 151323 | 376323 | 0 | 376323 | 150000 | 30000 | 120000 | 85604 | 0 | 85604 | 100604 | 0 | 100604 | 300000 | 60000 | 240000 | 124421 | 110746 | 13675 | 124421 | 110746 | 13675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362500 | 72500 | 290000 | 580132 | 0 | 580132 | 580132 | 0 | 580132 | 20000 | 4000 | 16000 | 41917 | 0 | 41917 | 50917 | 0 | 50917 | 135000 | 27000 | 108000 | 4337 | 0 | 4337 | 16337 | 0 | 16337 | 90000 | 18000 | 72000 | 0 | 0 | 0 | 53000 | 53000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 20058 | 20058 | 0 | 20058 | 20058 | 0 | 6925000 | 1385000 | 5540000 | 1096235 | 219247 | 876988 | 1631459 | 493471 | 1137988 | 6925000 | 1385000 | 5540000 | 1096235 | 219247 | 876988 | 1631459 | 493471 | 1137988 | 0 | 0 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | CCI | 2011 | Q2 | Q2 - 2011 | 300000 | 60000 | 240000 | 173585 | 173585 | 0 | 176585 | 176585 | 0 | 5500000 | 1100000 | 4400000 | 528575 | 51719 | 476856 | 2946618 | 51719 | 2894899 | 150000 | 30000 | 120000 | 108262 | 0 | 108262 | 128262 | 0 | 128262 | 300000 | 60000 | 240000 | 124706 | 110746 | 13960 | 129706 | 115746 | 13960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362500 | 72500 | 290000 | 580132 | 0 | 580132 | 580132 | 0 | 580132 | 20000 | 4000 | 16000 | 56647 | 0 | 56647 | 71647 | 0 | 71647 | 135000 | 27000 | 108000 | 16992 | 0 | 16992 | 24992 | 0 | 24992 | 90000 | 18000 | 72000 | 0 | 0 | 0 | 77000 | 77000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 20058 | 20058 | 0 | 20058 | 20058 | 0 | 6925000 | 1385000 | 5540000 | 1608957 | 356108 | 1252849 | 4155000 | 441108 | 3713892 | 6925000 | 1385000 | 5540000 | 1608957 | 356108 | 1252849 | 4155000 | 441108 | 3713892 | 0 | 0 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | CCI | 2011 | Q3 | Q3 - 2011 | 436000 | 436000 | 0 | 412571 | 406806 | 5765 | 426571 | 420806 | 5765 | 5113795 | 588565 | 4525230 | 1357611 | 88026 | 1269585 | 2594100 | 518820 | 2075280 | 214963 | 14963 | 200000 | 132946 | 17076 | 115870 | 144946 | 17076 | 127870 | 264041 | 134190 | 129851 | 171523 | 33902 | 137621 | 221523 | 83902 | 137621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600454 | 118946 | 481508 | 579453 | 106552 | 472901 | 599453 | 106552 | 492901 | 61948 | 15537 | 46411 | 57897 | 10282 | 47615 | 61897 | 14282 | 47615 | 80867 | 867 | 80000 | 37363 | 896 | 36467 | 54148 | 896 | 53252 | 127000 | 50000 | 77000 | 0 | 0 | 0 | 77000 | 0 | 77000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25932 | 25932 | 0 | 25932 | 25932 | 0 | 25932 | 25932 | 0 | 6925000 | 1385000 | 5540000 | 2775296 | 689472 | 2085824 | 4205570 | 1188266 | 3017304 | 6925000 | 1385000 | 5540000 | 2775296 | 689472 | 2085824 | 4205570 | 1188266 | 3017304 | 0 | 0 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | CCI | 2011 | Q4 | Q4 - 2011 | 436000 | 436000 | 0 | 414436 | 408671 | 5765 | 422436 | 416671 | 5765 | 5113795 | 588565 | 4525230 | 1912365 | 113502 | 1798863 | 4085343 | 496503 | 3588840 | 214963 | 14963 | 200000 | 144944 | 17076 | 127868 | 169944 | 17076 | 152868 | 264041 | 134190 | 129851 | 174865 | 37244 | 137621 | 179865 | 42244 | 137621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600454 | 118946 | 481508 | 581920 | 106552 | 475368 | 585920 | 106552 | 479368 | 61948 | 15537 | 46411 | 57897 | 10282 | 47615 | 57897 | 10282 | 47615 | 80867 | 867 | 80000 | 55563 | 896 | 54667 | 71163 | 896 | 70267 | 127000 | 50000 | 77000 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25932 | 25932 | 0 | 25932 | 25932 | 0 | 25932 | 25932 | 0 | 6925000 | 1385000 | 5540000 | 3367922 | 720155 | 2647767 | 5678500 | 1136156 | 4542344 | 6925000 | 1385000 | 5540000 | 3367922 | 720155 | 2647767 | 5678500 | 1136156 | 4542344 | 0 | 0 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | CCI | 2012 | Q1 | Q1 - 2012 | 1059170 | 565453 | 493717 | 418726 | 409295 | 9431 | 744658 | 435227 | 309431 | 3815772 | 405788 | 3409984 | 3060636 | 361561 | 2699075 | 3710636 | 393495 | 3317141 | 232913 | 24418 | 208495 | 182920 | 21279 | 161641 | 207920 | 21279 | 186641 | 839327 | 134190 | 705137 | 174865 | 37244 | 137621 | 257865 | 120244 | 137621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600452 | 118945 | 481507 | 579800 | 106127 | 473673 | 598800 | 118127 | 480673 | 80000 | 15536 | 64464 | 57897 | 10282 | 47615 | 76897 | 12433 | 64464 | 92132 | 1186 | 90946 | 64695 | 971 | 63724 | 79695 | 971 | 78724 | 178924 | 93174 | 85750 | 96254 | 18174 | 78080 | 116254 | 38174 | 78080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26310 | 26310 | 0 | 25932 | 25932 | 0 | 25932 | 25932 | 0 | 6925000 | 1385000 | 5540000 | 4661725 | 990865 | 3670860 | 5818657 | 1165882 | 4652775 | 6925000 | 1385000 | 5540000 | 4661725 | 990865 | 3670860 | 5818657 | 1165882 | 4652775 | 0 | 21840 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | CCI | 2012 | Q2 | Q2 - 2012 | 1059170 | 565453 | 493717 | 426665 | 409352 | 17313 | 868665 | 509352 | 359313 | 3815772 | 405788 | 3409984 | 3420354 | 401090 | 3019264 | 3720354 | 401090 | 3319264 | 232913 | 24418 | 208495 | 215997 | 22957 | 193040 | 221997 | 22957 | 199040 | 839327 | 134190 | 705137 | 174865 | 37244 | 137621 | 504865 | 127244 | 377621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600452 | 118945 | 481507 | 580021 | 106348 | 473673 | 590021 | 116348 | 473673 | 80000 | 15536 | 64464 | 58942 | 10282 | 48660 | 78942 | 15282 | 63660 | 92132 | 1186 | 90946 | 81537 | 971 | 80566 | 86537 | 971 | 85566 | 178924 | 93174 | 85750 | 96888 | 18174 | 78714 | 146888 | 68174 | 78714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26310 | 26310 | 0 | 25932 | 25932 | 0 | 25932 | 25932 | 0 | 6925000 | 1385000 | 5540000 | 5081201 | 1032350 | 4048851 | 6244201 | 1287350 | 4956851 | 6925000 | 1385000 | 5540000 | 5081201 | 1032350 | 4048851 | 6244201 | 1287350 | 4956851 | 0 | 28800 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | CCI | 2012 | Q3 | Q3 - 2012 | 1059170 | 565453 | 493717 | 1025749 | 532132 | 493617 | 1057617 | 564000 | 493617 | 3815772 | 405788 | 3409984 | 3531455 | 401090 | 3130365 | 3814000 | 404588 | 3409412 | 232913 | 24418 | 208495 | 223624 | 22957 | 200667 | 232600 | 24400 | 208200 | 839327 | 134190 | 705137 | 327300 | 66374 | 260927 | 839150 | 134111 | 705039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600452 | 118945 | 481507 | 585270 | 106348 | 478922 | 600300 | 118900 | 481400 | 80000 | 15536 | 64464 | 68535 | 10282 | 58253 | 78900 | 15500 | 63400 | 92132 | 1186 | 90946 | 90820 | 971 | 89849 | 92010 | 1180 | 90830 | 178924 | 93174 | 85750 | 96888 | 18174 | 78714 | 178700 | 93100 | 85600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26310 | 26310 | 0 | 25932 | 25932 | 0 | 25932 | 25932 | 0 | 6925000 | 1385000 | 5540000 | 5975573 | 1184260 | 4791314 | 6919209 | 1381711 | 5537498 | 6925000 | 1385000 | 5540000 | 5975573 | 1184260 | 4791314 | 6919209 | 1381711 | 5537498 | 0 | 40200 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | CCI | 2012 | Q4 | Q4 - 2012 | 1059170 | 565453 | 493717 | 1037871 | 544254 | 493617 | 1057871 | 564254 | 493617 | 3815772 | 405788 | 3409984 | 3650494 | 402732 | 3247762 | 3808494 | 402732 | 3405762 | 232913 | 24418 | 208495 | 231809 | 23510 | 208299 | 232256 | 23957 | 208299 | 839327 | 134190 | 705137 | 679487 | 130217 | 549270 | 699487 | 130217 | 569270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600452 | 118945 | 481507 | 597800 | 118878 | 478922 | 599487 | 120556 | 478931 | 80000 | 15536 | 64464 | 75544 | 15282 | 60262 | 79535 | 15282 | 64253 | 92132 | 1186 | 90946 | 91014 | 971 | 90043 | 92014 | 971 | 90946 | 178924 | 93174 | 85750 | 104558 | 25844 | 78714 | 169558 | 90844 | 78714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26310 | 26310 | 0 | 26310 | 26310 | 0 | 26310 | 26310 | 0 | 6925000 | 1385000 | 5540000 | 6494887 | 1287998 | 5206889 | 6765012 | 1375123 | 5389792 | 6925000 | 1385000 | 5540000 | 6494887 | 1287998 | 5206889 | 6765012 | 1375123 | 5389792 | 0 | 61852 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | CCI | 2013 | Q1 | Q1 - 2013 | 1059170 | 565453 | 493717 | 1054439 | 555471 | 498968 | 1074421 | 565453 | 508968 | 3815772 | 405788 | 3409984 | 3675739 | 416455 | 3259284 | 3806544 | 417260 | 3389284 | 232913 | 24418 | 208495 | 236939 | 23510 | 213429 | 245838 | 23510 | 222328 | 839327 | 134190 | 705137 | 680005 | 130217 | 549788 | 685005 | 130217 | 554788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600452 | 118945 | 481507 | 599478 | 120556 | 478922 | 604588 | 120556 | 484032 | 80000 | 15536 | 64464 | 75544 | 15282 | 60262 | 77535 | 15282 | 62253 | 92132 | 1186 | 90946 | 91014 | 971 | 90043 | 92014 | 971 | 91043 | 178924 | 93174 | 85750 | 104558 | 25844 | 78714 | 157558 | 78844 | 78714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26310 | 26310 | 0 | 26310 | 26310 | 0 | 26310 | 26310 | 0 | 6925000 | 1385000 | 5540000 | 6544026 | 1314616 | 5229410 | 6769813 | 1378403 | 5391410 | 6925000 | 1385000 | 5540000 | 6544026 | 1314616 | 5229410 | 6769813 | 1378403 | 5391410 | 0 | 87502 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570016 | CCI | 2013 | Q2 | Q2 - 2013 | 1059170 | 565453 | 493717 | 1068159 | 569191 | 498968 | 1068159 | 569191 | 498968 | 3815772 | 405788 | 3409984 | 3838991 | 424518 | 3414473 | 3838991 | 424518 | 3414473 | 232913 | 24418 | 208495 | 271070 | 30092 | 240978 | 271070 | 30092 | 240978 | 839327 | 134190 | 705137 | 743386 | 131337 | 612049 | 743386 | 131337 | 612049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600452 | 118945 | 481507 | 607739 | 121507 | 486232 | 607739 | 121507 | 486232 | 80000 | 15536 | 64464 | 75544 | 15282 | 60262 | 75544 | 15282 | 60262 | 92132 | 1186 | 90946 | 92310 | 971 | 91339 | 92310 | 971 | 91339 | 178924 | 93174 | 85750 | 136198 | 52732 | 83466 | 136198 | 52732 | 83466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26310 | 26310 | 0 | 20310 | 25110 | -4800 | 20310 | 25110 | -4800 | 6925000 | 1385000 | 5540000 | 6853707 | 1370740 | 5482967 | 6853707 | 1370740 | 5482967 | 6925000 | 1385000 | 5540000 | 6853707 | 1370740 | 5482967 | 6853707 | 1370740 | 5482967 | 0 | 92228 | Virginia Tech Foundation, Inc. | TRUE
NT10BIX5570017 | CCI | 2010 | Q3 | Q3 - 2010 | 10895450 | 1332516 | 9562934 | 0 | 0 | 0 | 0 | 0 | 0 | 4995267 | 734493 | 4260774 | 0 | 0 | 0 | 0 | 0 | 0 | 2881250 | 0 | 2881250 | 31251 | 30157 | 1093 | 2110065 | 0 | 2110065 | 5323484 | 5128994 | 194490 | 358441 | 358441 | 0 | 512655 | 512655 | 347710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 32795 | 32795 | 0 | 32795 | 32795 | 0 | 495125 | 0 | 495125 | 0 | 0 | 0 | 0 | 0 | 0 | 1763200 | 0 | 1763200 | 0 | 0 | 0 | 0 | 0 | 0 | 6628767 | 0 | 6628767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 422487 | 421393 | 1093 | 2655515 | 545450 | 2457775 | 35980017 | 7196003 | 28784014 | 422487 | 421393 | 1093 | 2655515 | 545450 | 2457775 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | CCI | 2010 | Q4 | Q4 - 2010 | 12005450 | 1332516 | 10672934 | 0 | 0 | 0 | 0 | 393743 | 506778 | 2736593 | 560077 | 2176516 | 0 | 0 | 0 | 0 | 0 | 0 | 2881250 | 0 | 2881250 | 102708 | 0 | 102708 | 154007 | 0 | 154007 | 5497900 | 5303410 | 194490 | 750077 | 750077 | 0 | 666873 | 666873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 208954 | 208954 | 0 | 398344 | 0 | 398344 | 495125 | 0 | 495125 | 0 | 0 | 0 | 347710 | 0 | 347710 | 1763200 | 0 | 1763200 | 0 | 0 | 0 | 250000 | 0 | 250000 | 7603025 | 0 | 7603025 | 0 | 0 | 0 | 210000 | 0 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 1061739 | 959031 | 102708 | 2026934 | 1060616 | 1866839 | 35980017 | 7196003 | 28784014 | 1061739 | 959031 | 102708 | 2026934 | 1060616 | 1866839 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | CCI | 2011 | Q1 | Q1 - 2011 | 12005450 | 1332516 | 10672934 | 0 | 0 | 0 | 1835868 | 393743 | 1442125 | 2736593 | 560077 | 2176516 | 0 | 0 | 0 | 0 | 0 | 0 | 2881250 | 0 | 2881250 | 152575 | 0 | 152575 | 191696 | 0 | 191696 | 5497900 | 5303410 | 194490 | 666873 | 666873 | 0 | 821088 | 821088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 305374 | 40234 | 265140 | 848980 | 0 | 848980 | 495125 | 0 | 495125 | 168720 | 0 | 168720 | 347710 | 0 | 347710 | 1763200 | 0 | 1763200 | 0 | 0 | 0 | 343828 | 0 | 343828 | 7603025 | 0 | 7603025 | 0 | 0 | 0 | 1052001 | 0 | 1052001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 1293542 | 707107 | 586435 | 5441171 | 1214831 | 4226340 | 35980017 | 7196003 | 28784014 | 1293542 | 707107 | 586435 | 5441171 | 1214831 | 4226340 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | CCI | 2011 | Q2 | Q2 - 2011 | 12327062 | 1332516 | 10994546 | 383758 | 0 | 383758 | 1451508 | 393741 | 1057767 | 2414984 | 560077 | 1854907 | 0 | 0 | 0 | 475768 | 34961 | 440807 | 2881250 | 0 | 2881250 | 199506 | 0 | 199506 | 566429 | 0 | 566429 | 5497900 | 5303410 | 194490 | 821088 | 821088 | 0 | 2165148 | 2165148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 814600 | 0 | 814600 | 980164 | 0 | 980164 | 495125 | 0 | 495125 | 168720 | 0 | 168720 | 347710 | 0 | 347710 | 1763200 | 0 | 1763200 | 348478 | 0 | 348478 | 492102 | 0 | 492102 | 7603022 | 0 | 7603022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 2736150 | 821088 | 1915062 | 6478829 | 2593850 | 3884979 | 35980017 | 7196003 | 28784014 | 2736150 | 821088 | 1915062 | 6478829 | 2593850 | 3884979 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | CCI | 2011 | Q3 | Q3 - 2011 | 12327062 | 1332516 | 10994546 | 2559751 | 393741 | 2166010 | 2899455 | 475186 | 2424269 | 2414984 | 560077 | 1854907 | 475767 | 34960 | 440807 | 1038413 | 198678 | 839735 | 2881250 | 0 | 2881250 | 623900 | 0 | 623900 | 744989 | 0 | 744988 | 5497900 | 5303410 | 194490 | 2377435 | 2377435 | 0 | 4419350 | 4419350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 814600 | 0 | 814600 | 1837287 | 0 | 1837287 | 495125 | 0 | 495125 | 347710 | 0 | 347710 | 347710 | 0 | 347710 | 1763200 | 0 | 1763200 | 365393 | 0 | 365393 | 1489406 | 0 | 1489406 | 7603022 | 0 | 7603022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 7564556 | 2806136 | 4758420 | 12776610 | 5093214 | 7683395 | 35980017 | 7196003 | 28784014 | 7564556 | 2806136 | 4758420 | 12776610 | 5093214 | 7683395 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | CCI | 2011 | Q4 | Q4 - 2011 | 12327062 | 1332516 | 10994546 | 4990307 | 706104 | 4284203 | 6155370 | 1018277 | 5137093 | 2414984 | 560077 | 1854907 | 1523938 | 498463 | 1025475 | 1585551 | 560076 | 1025475 | 2881250 | 0 | 2881250 | 1156039 | 0 | 1156039 | 1976341 | 0 | 1976341 | 5497900 | 5303410 | 194490 | 5125890 | 5125890 | 0 | 5146440 | 5146440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 1142536 | 0 | 1142536 | 1315199 | 0 | 1315199 | 495125 | 0 | 495125 | 347710 | 0 | 347710 | 347710 | 0 | 347710 | 1763200 | 0 | 1763200 | 742644 | 0 | 742644 | 958412 | 0 | 958412 | 7603022 | 0 | 7603022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 15029064 | 6330457 | 8698607 | 17485023 | 6724793 | 10760230 | 35980017 | 7196003 | 28784014 | 15029064 | 6330457 | 8698607 | 17485023 | 6724793 | 10760230 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | CCI | 2012 | Q1 | Q1 - 2012 | 12327062 | 1332516 | 10994546 | 5217527 | 706104 | 4511424 | 6878126 | 1040449 | 5837677 | 2414984 | 560077 | 1854907 | 1523938 | 498463 | 1025475 | 1754889 | 498463 | 1256426 | 2881250 | 0 | 2881250 | 1231489 | 0 | 1231489 | 2206560 | 0 | 2206560 | 5497900 | 5303410 | 194490 | 5125890 | 5125890 | 0 | 5270367 | 5125890 | 144477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 1282624 | 0 | 1282624 | 1532790 | 0 | 1532790 | 495125 | 0 | 495125 | 347710 | 0 | 347710 | 381360 | 0 | 381360 | 1763200 | 0 | 1763200 | 910757 | 0 | 910757 | 1075000 | 0 | 1075000 | 7603022 | 0 | 7603022 | 60000 | 0 | 60000 | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 15699935 | 6330457 | 9369479 | 19159092 | 6664802 | 12494290 | 35980017 | 7196003 | 28784014 | 15699935 | 6330457 | 9369479 | 19159092 | 6664802 | 12494290 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | CCI | 2012 | Q2 | Q2 - 2012 | 12327062 | 1332516 | 10994546 | 6155212 | 946904 | 5208308 | 10238522 | 946904 | 9291618 | 2414984 | 560077 | 1854907 | 1527339 | 498463 | 1028876 | 2276011 | 498463 | 1777548 | 2881250 | 0 | 2881250 | 1316890 | 0 | 1316890 | 2582870 | 0 | 2582871 | 5497900 | 5303410 | 194490 | 5270367 | 5125890 | 144477 | 5270367 | 5125890 | 144477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 1422728 | 0 | 1422728 | 2054925 | 0 | 2054925 | 495125 | 0 | 495125 | 374670 | 0 | 374670 | 414345 | 0 | 414345 | 1763200 | 0 | 1763200 | 1026623 | 0 | 1026623 | 1329960 | 0 | 1329960 | 7603022 | 0 | 7603022 | 84520 | 0 | 84520 | 4841608 | 0 | 4841608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 17178349 | 6571257 | 10607092 | 29008608 | 6571257 | 22437352 | 35980017 | 7196003 | 28784014 | 17178349 | 6571257 | 10607092 | 29008608 | 6571257 | 22437352 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | CCI | 2012 | Q3 | Q3 - 2012 | 12327062 | 1332516 | 10994546 | 6912563 | 1042947 | 5869616 | 11783296 | 1332516 | 10450780 | 2414984 | 560077 | 1854907 | 1688138 | 498463 | 1189675 | 1985790 | 498463 | 1487327 | 2881250 | 0 | 2881250 | 2200268 | 0 | 2200268 | 2752335 | 0 | 2752335 | 5497900 | 5303410 | 194490 | 5270367 | 5125890 | 144477 | 5320380 | 5125890 | 194490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 1422729 | 0 | 1422729 | 2639783 | 0 | 2639783 | 495125 | 0 | 495125 | 374670 | 0 | 374670 | 414345 | 0 | 414345 | 1763200 | 0 | 1763200 | 1033908 | 0 | 1033908 | 1393544 | 0 | 1393544 | 7603022 | 0 | 7603022 | 131010 | 0 | 131010 | 4845208 | 0 | 4845208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 19033653 | 6667300 | 12366353 | 31134681 | 6956869 | 24177812 | 35980017 | 7196003 | 28784014 | 19033653 | 6667300 | 12366353 | 31134681 | 6956869 | 24177812 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | CCI | 2012 | Q4 | Q4 - 2012 | 12327062 | 1332516 | 10994546 | 7906342 | 1042947 | 6863395 | 11150913 | 1568718 | 9582195 | 2414984 | 560077 | 1854907 | 1754888 | 498463 | 1256425 | 1991789 | 498463 | 1493326 | 2881250 | 0 | 2881250 | 2346182 | 0 | 2346182 | 2780400 | 0 | 2780400 | 5497900 | 5303410 | 194490 | 5873400 | 5125890 | 747510 | 5873400 | 5125890 | 747510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 1816150 | 0 | 1816150 | 2891650 | 0 | 2891650 | 495125 | 0 | 495125 | 402620 | 0 | 402620 | 425620 | 0 | 425620 | 1763200 | 0 | 1763200 | 1110712 | 0 | 1110712 | 1398997 | 0 | 1398997 | 7603022 | 0 | 7603022 | 347282 | 0 | 347282 | 6715126 | 0 | 6715126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 21557576 | 6667300 | 14890276 | 33227895 | 7193071 | 26034824 | 35980017 | 7196003 | 28784014 | 21557576 | 6667300 | 14890276 | 33227895 | 7193071 | 26034824 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | CCI | 2013 | Q1 | Q1 - 2013 | 12689105 | 1571649 | 11117456 | 11031931 | 1042947 | 9988984 | 12237998 | 1568718 | 10669280 | 2040021 | 498464 | 1541557 | 1958470 | 498463 | 1460007 | 2036990 | 498463 | 1538527 | 2993093 | 0 | 2993093 | 2410731 | 0 | 2410731 | 2850400 | 0 | 2850400 | 5873400 | 5125890 | 747510 | 5873400 | 5125890 | 747510 | 5873400 | 5125890 | 747510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 1959750 | 0 | 1959750 | 2807461 | 0 | 2807461 | 495125 | 0 | 495125 | 415595 | 0 | 415595 | 432645 | 0 | 432645 | 1600436 | 0 | 1600436 | 1378854 | 0 | 1378854 | 1477364 | 0 | 1477364 | 7291363 | 0 | 7291363 | 6051885 | 0 | 6051885 | 7060248 | 0 | 7060248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 31080616 | 6667300 | 24413316 | 34776506 | 7193071 | 27583435 | 35980017 | 7196003 | 28784014 | 31080616 | 6667300 | 24413316 | 34776506 | 7193071 | 27583435 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | CCI | 2013 | Q2 | Q2 - 2013 | 12689105 | 1571649 | 11117456 | 11382169 | 1251025 | 10131144 | 12689105 | 1571649 | 11117456 | 2040021 | 498464 | 1541557 | 1958470 | 498463 | 1460007 | 2040021 | 498464 | 1541557 | 2993093 | 0 | 2993093 | 2795413 | 0 | 2795413 | 2993093 | 0 | 2993093 | 5873400 | 5125890 | 747510 | 5873400 | 5125890 | 747510 | 5873400 | 5125890 | 747510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 2636687 | 0 | 2636687 | 2997474 | 0 | 2997474 | 495125 | 0 | 495125 | 415595 | 0 | 415595 | 495125 | 0 | 495125 | 1600436 | 0 | 1600436 | 1505681 | 0 | 1505681 | 1600436 | 0 | 1600436 | 7291363 | 0 | 7291363 | 6299292 | 0 | 6299292 | 7291363 | 0 | 7291363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 32866707 | 6875378 | 25991329 | 35980017 | 7196003 | 28784014 | 35980017 | 7196003 | 28784014 | 32866707 | 6875378 | 25991329 | 35980017 | 7196003 | 28784014 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570017 | CCI | 2013 | Q3 | Q3 - 2013 | 12689105 | 1571649 | 11117456 | 11634984 | 1332516 | 10302468 | 12670285 | 1571649 | 11098636 | 2040021 | 498464 | 1541557 | 2028960 | 498463 | 1530497 | 2028961 | 498464 | 1530497 | 2993093 | 0 | 2993093 | 2795812 | 0 | 2795812 | 2923878 | 0 | 2923878 | 5873400 | 5125890 | 747510 | 5873400 | 5125890 | 747510 | 5873400 | 5125890 | 747510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2997474 | 0 | 2997474 | 2641330 | 0 | 2641330 | 2986153 | 0 | 2986153 | 495125 | 0 | 495125 | 438695 | 0 | 438695 | 490270 | 0 | 490270 | 1600436 | 0 | 1600436 | 1507056 | 0 | 1507056 | 1606526 | 0 | 1606526 | 7291363 | 0 | 7291363 | 6776989 | 0 | 6776989 | 7400544 | 0 | 7400544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35980017 | 7196003 | 28784014 | 33697226 | 6956869 | 26740357 | 35980017 | 7196003 | 28784014 | 35980017 | 7196003 | 28784014 | 33697226 | 6956869 | 26740357 | 35980017 | 7196003 | 28784014 | 1567257 | 0 | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | TRUE
NT10BIX5570018 | CCI | 2010 | Q3 | Q3 - 2010 | 2149732 | 760950 | 1388782 | 40837 | 0 | 40837 | 816353 | 657586 | 158767 | 622031 | 0 | 622031 | 65295 | 0 | 65295 | 128915 | 0 | 128915 | 462500 | 0 | 462500 | 62433 | 0 | 62433 | 103185 | 0 | 103185 | 27151000 | 5840000 | 21311000 | 270000 | 270000 | 0 | 25615000 | 4940000 | 20675000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 39482 | 0 | 39482 | 93345 | 0 | 93345 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 3084 | 0 | 3084 | 198918 | 0 | 198918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 2808 | 0 | 2808 | 6372 | 0 | 6372 | 32288795 | 6606425 | 25682370 | 488439 | 270000 | 218439 | 26966588 | 5597586 | 21369002 | 32288795 | 6606425 | 25682370 | 488439 | 270000 | 218439 | 26966588 | 5597586 | 21369002 | 0 | 0 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | CCI | 2010 | Q4 | Q4 - 2010 | 2149732 | 760950 | 1388782 | 115214 | 0 | 115214 | 828565 | 653842 | 174723 | 622031 | 0 | 622031 | 141929 | 0 | 141929 | 205963 | 0 | 205963 | 462500 | 0 | 462500 | 103328 | 0 | 103328 | 138561 | 0 | 138561 | 27151000 | 5840000 | 21311000 | 26515000 | 5840000 | 20675000 | 26515000 | 5840000 | 20675000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 95139 | 0 | 95139 | 155043 | 0 | 155043 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 82208 | 0 | 82208 | 401876 | 0 | 401876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 4653 | 0 | 4653 | 6990 | 0 | 6990 | 32288795 | 6606425 | 25682370 | 27061971 | 5840000 | 21221971 | 28256498 | 6493842 | 21762656 | 32288795 | 6606425 | 25682370 | 27061971 | 5840000 | 21221971 | 28256498 | 6493842 | 21762656 | 0 | 1264 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | CCI | 2011 | Q1 | Q1 - 2011 | 2149732 | 760950 | 1388782 | 874088 | 578380 | 295708 | 953857 | 578380 | 375477 | 622031 | 0 | 622031 | 208793 | 0 | 208793 | 298235 | 0 | 298235 | 462500 | 0 | 462500 | 134295 | 0 | 134295 | 204422 | 0 | 204422 | 27151000 | 5840000 | 21311000 | 26515000 | 5840000 | 20675000 | 26515000 | 5840000 | 20675000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 139154 | 0 | 139154 | 214199 | 0 | 214199 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 331717 | 0 | 331717 | 453050 | 0 | 453050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 4915 | 0 | 4915 | 7339 | 0 | 7339 | 32288795 | 6606425 | 25682370 | 28212462 | 6418380 | 21794082 | 28650602 | 6418380 | 22232222 | 32288795 | 6606425 | 25682370 | 28212462 | 6418380 | 21794082 | 28650602 | 6418380 | 22232222 | 0 | 7000 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | CCI | 2011 | Q2 | Q2 - 2011 | 2149732 | 760950 | 1388782 | 927995 | 578380 | 349615 | 1006214 | 578380 | 427834 | 622031 | 0 | 622031 | 300171 | 0 | 300171 | 387222 | 0 | 387222 | 462500 | 0 | 462500 | 169258 | 0 | 169258 | 236123 | 0 | 236123 | 27151000 | 5840000 | 21311000 | 26515000 | 5840000 | 20675000 | 27105000 | 5840000 | 21265000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 212095 | 0 | 212095 | 304670 | 0 | 304670 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 368828 | 0 | 368828 | 446459 | 0 | 446459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 6073 | 0 | 6073 | 7186 | 0 | 7339 | 32288795 | 6606425 | 25682370 | 28503920 | 6418380 | 22085540 | 29497374 | 6418380 | 23079147 | 32288795 | 6606425 | 25682370 | 28503920 | 6418380 | 22085540 | 29497374 | 6418380 | 23079147 | 0 | 20800 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | CCI | 2011 | Q3 | Q3 - 2011 | 2149732 | 760950 | 1388782 | 1155265 | 578380 | 576885 | 2313238 | 978380 | 1334858 | 622031 | 0 | 622031 | 384466 | 0 | 384466 | 465469 | 0 | 465469 | 462500 | 0 | 462500 | 224823 | 0 | 224823 | 267961 | 0 | 267961 | 27151000 | 5840000 | 21311000 | 26515000 | 5840000 | 20675000 | 27151000 | 5840000 | 21311000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 312934 | 0 | 312934 | 386640 | 0 | 386640 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 481388 | 0 | 481388 | 505212 | 0 | 505212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 8477 | 0 | 8477 | 36157 | 0 | 36157 | 32288795 | 6606425 | 25682370 | 29086853 | 6418380 | 22668473 | 31130177 | 6818380 | 24311797 | 32288795 | 6606425 | 25682370 | 29086853 | 6418380 | 22668473 | 31130177 | 6818380 | 24311797 | 0 | 48193 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | CCI | 2011 | Q4 | Q4 - 2011 | 2149732 | 760950 | 1388782 | 1165387 | 578380 | 587007 | 2291410 | 978380 | 1313030 | 622031 | 0 | 622031 | 479948 | 0 | 479948 | 622031 | 0 | 622031 | 462500 | 0 | 462500 | 257731 | 0 | 257731 | 285793 | 0 | 285793 | 27151000 | 5840000 | 21311000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 383009 | 0 | 383009 | 505971 | 0 | 505971 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 483496 | 0 | 483496 | 538370 | 0 | 538370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 37959 | 0 | 37959 | 41825 | 0 | 41825 | 32288795 | 6606425 | 25682370 | 30058030 | 6418380 | 23639650 | 31535900 | 6818380 | 24717520 | 32288795 | 6606425 | 25682370 | 30058030 | 6418380 | 23639650 | 31535900 | 6818380 | 24717520 | 0 | 65685 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | CCI | 2012 | Q1 | Q1 - 2012 | 2149732 | 760950 | 1388782 | 1308855 | 578380 | 730475 | 2421984 | 978380 | 1443604 | 622031 | 0 | 622031 | 562986 | 0 | 562986 | 646552 | 0 | 646552 | 462500 | 0 | 462500 | 305784 | 0 | 305784 | 344109 | 0 | 344109 | 27151000 | 5840000 | 21311000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 482671 | 0 | 482671 | 610517 | 0 | 610517 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 483007 | 0 | 483007 | 483007 | 0 | 483007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 38606 | 0 | 38606 | 40661 | 0 | 40661 | 32288795 | 6606425 | 25682370 | 30432409 | 6418380 | 24014029 | 31797330 | 6818380 | 24978950 | 32288795 | 6606425 | 25682370 | 30432409 | 6418380 | 24014029 | 31797330 | 6818380 | 24978950 | 0 | 192251 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | CCI | 2012 | Q2 | Q2 - 2012 | 2149732 | 760950 | 1388782 | 1781377 | 760935 | 1020442 | 2027019 | 760935 | 1266084 | 622031 | 0 | 622031 | 647771 | 0 | 647771 | 720706 | 0 | 720706 | 462500 | 0 | 462500 | 330845 | 0 | 330845 | 347801 | 0 | 347801 | 27151000 | 5840000 | 21311000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 605024 | 0 | 605024 | 701758 | 0 | 701758 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 483116 | 0 | 483116 | 484116 | 0 | 484116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 43280 | 0 | 43280 | 47719 | 0 | 47719 | 32288795 | 6606425 | 25682370 | 31141913 | 6600935 | 24540978 | 31579619 | 6600935 | 24978684 | 32288795 | 6606425 | 25682370 | 31141913 | 6600935 | 24540978 | 31579619 | 6600935 | 24978684 | 0 | 276709 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | CCI | 2012 | Q3 | Q3 - 2012 | 2149732 | 760950 | 1388782 | 2013475 | 764504 | 1248971 | 2163475 | 764504 | 1398971 | 622031 | 0 | 622031 | 710882 | 0 | 710882 | 774690 | 0 | 774690 | 462500 | 0 | 462500 | 351429 | 0 | 351429 | 378044 | 0 | 378044 | 27151000 | 5840000 | 21311000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 692153 | 0 | 692153 | 787130 | 0 | 787130 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 486515 | 0 | 486515 | 486515 | 0 | 486515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 43788 | 0 | 43788 | 45438 | 0 | 45438 | 32288795 | 6606425 | 25682370 | 31548742 | 6604504 | 24944238 | 31885792 | 6604504 | 25281288 | 32288795 | 6606425 | 25682370 | 31548742 | 6604504 | 24944238 | 31885792 | 6604504 | 25281288 | 0 | 378736 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | CCI | 2012 | Q4 | Q4 - 2012 | 2149732 | 760950 | 1388782 | 2132591 | 764504 | 1368087 | 2221120 | 764504 | 1456616 | 622031 | 0 | 622031 | 785128 | 0 | 785128 | 907685 | 0 | 907685 | 462500 | 0 | 462500 | 386045 | 0 | 386045 | 405160 | 0 | 405160 | 27151000 | 5840000 | 21311000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 761132 | 0 | 761132 | 860808 | 0 | 860808 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 492547 | 0 | 492547 | 503327 | 0 | 503327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 52085 | 0 | 52085 | 61381 | 1921 | 59460 | 32288795 | 6606425 | 25682370 | 31860028 | 6604504 | 25255524 | 32209981 | 6606425 | 25603556 | 32288795 | 6606425 | 25682370 | 31860028 | 6604504 | 25255524 | 32209981 | 6606425 | 25603556 | 0 | 480516 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | CCI | 2013 | Q1 | Q1 - 2013 | 2149732 | 760950 | 1388782 | 2157430 | 764504 | 1392926 | 2184706 | 764504 | 1420202 | 622031 | 0 | 622031 | 835102 | 0 | 835102 | 884108 | 0 | 884108 | 462500 | 0 | 462500 | 406159 | 0 | 406159 | 427274 | 0 | 427274 | 27151000 | 5840000 | 21311000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 837879 | 0 | 837879 | 899548 | 0 | 899548 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 505327 | 0 | 505327 | 508327 | 0 | 508327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 56371 | 0 | 56371 | 58721 | 1921 | 56800 | 32288795 | 6606425 | 25682370 | 32048768 | 6604504 | 25444264 | 32213184 | 6606425 | 25606759 | 32288795 | 6606425 | 25682370 | 32048768 | 6604504 | 25444264 | 32213184 | 6606425 | 25606759 | 0 | 600258 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | CCI | 2013 | Q2 | Q2 - 2013 | 2149732 | 760950 | 1388782 | 2151559 | 766425 | 1385134 | 2151559 | 766425 | 1385134 | 622031 | 0 | 622031 | 884108 | 0 | 884108 | 912112 | 0 | 912112 | 462500 | 0 | 462500 | 416157 | 0 | 416157 | 449313 | 0 | 449313 | 27151000 | 5840000 | 21311000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331091 | 0 | 1331091 | 899369 | 0 | 899369 | 931434 | 0 | 931434 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538370 | 0 | 538370 | 511340 | 0 | 511340 | 511340 | 0 | 511340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29571 | 5475 | 24096 | 57058 | 0 | 57058 | 57058 | 0 | 57058 | 32288795 | 6606425 | 25682370 | 32170091 | 6606425 | 25563666 | 32263316 | 6606425 | 25656891 | 32288795 | 6606425 | 25682370 | 32170091 | 6606425 | 25563666 | 32263316 | 6606425 | 25656891 | 0 | 707551 | Critical Hub Networks, Inc | TRUE
NT10BIX5570018 | CCI | 2013 | Q3 | Q3 - 2013 | 2351537 | 966403 | 1385134 | 2351537 | 966403 | 1385134 | 2351537 | 966403 | 1385134 | 1361914 | 449802 | 912112 | 1361914 | 449802 | 912112 | 1361914 | 449802 | 912112 | 479639 | 6027 | 473612 | 479639 | 6027 | 473612 | 479639 | 6027 | 473612 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 27246000 | 5840000 | 21406000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1013295 | 80681 | 932614 | 1013295 | 80681 | 932614 | 1013295 | 80681 | 932614 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 611466 | 100126 | 511340 | 611466 | 100126 | 511340 | 611466 | 100126 | 511340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57058 | 0 | 57058 | 57058 | 0 | 57058 | 57058 | 0 | 57058 | 33125409 | 7443039 | 25682370 | 33125409 | 7443039 | 25682370 | 33125409 | 7443039 | 25682370 | 33125409 | 7443039 | 25682370 | 33125409 | 7443039 | 25682370 | 33125409 | 7443039 | 25682370 | 0 | 836614 | Critical Hub Networks, Inc | TRUE
NT10BIX5570019 | CCI | 2010 | Q3 | Q3 - 2010 | 67500 | 13500 | 54000 | 40178 | 0 | 40178 | 80000 | 80000 | 0 | 14728655 | 2945731 | 11782924 | 0 | 0 | 0 | 2365387 | 394231 | 1971156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 2250 | 0 | 2250 | 110000 | 80000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191208 | 638242 | 2552966 | 295702 | 0 | 295702 | 1449242 | 241540 | 1207702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1568000 | 313600 | 1254400 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 338130 | 0 | 338130 | 4004629 | 795771 | 3208858 | 20055363 | 4011073 | 16044290 | 338130 | 0 | 338130 | 4004629 | 795771 | 3208858 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | CCI | 2010 | Q4 | Q4 - 2010 | 67500 | 13500 | 54000 | 144863 | 82879 | 61984 | 444863 | 382879 | 61984 | 14728655 | 2945731 | 11782924 | 0 | 0 | 0 | 1641000 | 341000 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 25495 | 0 | 25495 | 125495 | 0 | 125495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191208 | 638242 | 2552966 | 939640 | 186361 | 753279 | 1409640 | 186361 | 1223279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 0 | 0 | 0 | 45000 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1568000 | 313600 | 1254400 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 1109998 | 269240 | 840758 | 3665998 | 910240 | 2755758 | 20055363 | 4011073 | 16044290 | 1109998 | 269240 | 840758 | 3665998 | 910240 | 2755758 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | CCI | 2011 | Q1 | Q1 - 2011 | 1840754 | 457635 | 1383119 | 86565 | 82878 | 3687 | 511352 | 482176 | 29176 | 14728655 | 2945731 | 11782924 | 1759939 | 0 | 1759939 | 3259939 | 0 | 3259939 | 447423 | 0 | 447423 | 236159 | 0 | 236159 | 286000 | 0 | 286000 | 400000 | 80000 | 320000 | 224242 | 221492 | 2750 | 254242 | 251472 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864748 | 372950 | 1491798 | 1380857 | 186361 | 1194496 | 1480857 | 186361 | 1294496 | 305298 | 61060 | 244238 | 147853 | 0 | 147853 | 187853 | 0 | 187853 | 178947 | 35789 | 143158 | 1426 | 0 | 1426 | 1191 | 0 | 1191 | 222038 | 44408 | 177630 | 0 | 0 | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 25490 | 0 | 25490 | 503 | 503 | 0 | 20055363 | 4011073 | 16044290 | 3862531 | 490731 | 3371800 | 6041937 | 980512 | 5061405 | 20055363 | 4011073 | 16044290 | 3862531 | 490731 | 3371800 | 6041937 | 980512 | 5061405 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | CCI | 2011 | Q2 | Q2 - 2011 | 1840754 | 457635 | 1383119 | 125236 | 125236 | 0 | 1675851 | 1675851 | 0 | 14728655 | 2945731 | 11782924 | 2674897 | 0 | 2674897 | 6733896 | 0 | 6733896 | 447423 | 0 | 447423 | 252925 | 0 | 252925 | 312295 | 0 | 312295 | 400000 | 80000 | 320000 | 306638 | 303888 | 2750 | 346638 | 343888 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864748 | 372950 | 1491798 | 1384128 | 186361 | 1197767 | 1464128 | 186361 | 1277767 | 305298 | 61060 | 244238 | 201615 | 0 | 201615 | 251615 | 0 | 251615 | 178947 | 35789 | 143158 | 70343 | 0 | 70343 | 95343 | 0 | 95343 | 222038 | 44408 | 177630 | 0 | 0 | 0 | 85000 | 0 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 59683 | 0 | 59683 | 65683 | 0 | 65683 | 20055363 | 4011073 | 16044290 | 5075465 | 615485 | 4459980 | 11030449 | 2206100 | 8824349 | 20055363 | 4011073 | 16044290 | 5075465 | 615485 | 4459980 | 11030449 | 2206100 | 8824349 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | CCI | 2011 | Q3 | Q3 - 2011 | 1840754 | 457635 | 1383119 | 836093 | 776228 | 59864 | 1076228 | 776228 | 300000 | 14728655 | 2945731 | 11782924 | 4734783 | 0 | 4734783 | 7234783 | 0 | 7234783 | 447423 | 0 | 447423 | 295058 | 0 | 295058 | 335058 | 0 | 335058 | 400000 | 80000 | 320000 | 224408 | 221492 | 2916 | 243711 | 221492 | 22219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864748 | 372950 | 1491798 | 1510851 | 186361 | 1324490 | 1686361 | 186361 | 1500000 | 305298 | 61060 | 244238 | 223022 | 0 | 223022 | 272022 | 0 | 272022 | 178947 | 35789 | 143158 | 89317 | 0 | 89317 | 102317 | 0 | 102317 | 222038 | 44408 | 177630 | 0 | 0 | 0 | 170000 | 30000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 7913532 | 1184081 | 6729450 | 11120480 | 1214081 | 9906399 | 20055363 | 4011073 | 16044290 | 7913532 | 1184081 | 6729450 | 11120480 | 1214081 | 9906399 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | CCI | 2011 | Q4 | Q4 - 2011 | 1840754 | 457635 | 1383119 | 890434 | 827937 | 62497 | 1090434 | 1027937 | 62497 | 14728655 | 2945731 | 11782924 | 7268571 | 885528 | 6383043 | 11496536 | 3015145 | 8481391 | 447423 | 0 | 447423 | 334944 | 0 | 334944 | 374944 | 0 | 374944 | 400000 | 80000 | 320000 | 298510 | 221492 | 77018 | 428510 | 351492 | 77018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864748 | 372950 | 1491798 | 1511837 | 186361 | 1325476 | 1536837 | 211361 | 1325476 | 305298 | 61060 | 244238 | 222022 | 0 | 222022 | 272022 | 0 | 272022 | 178947 | 35789 | 143158 | 105800 | 0 | 105800 | 136002 | 0 | 136002 | 222038 | 44408 | 177630 | 4142 | 0 | 4142 | 164142 | 0 | 164142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 10636260 | 2121318 | 8514942 | 15499427 | 4605935 | 10893492 | 20055363 | 4011073 | 16044290 | 10636260 | 2121318 | 8514942 | 15499427 | 4605935 | 10893492 | 0 | 66078 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | CCI | 2012 | Q1 | Q1 - 2012 | 1840754 | 457635 | 1383119 | 1065726 | 999602 | 66124 | 1542839 | 1182537 | 360302 | 14728655 | 2945731 | 11782924 | 8589833 | 1225985 | 7363848 | 9689833 | 1298034 | 8391799 | 447423 | 0 | 447423 | 383346 | 0 | 383346 | 413346 | 3617 | 409729 | 400000 | 80000 | 320000 | 230912 | 223862 | 7050 | 360912 | 288862 | 72050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864748 | 372950 | 1491798 | 1649658 | 20720 | 1628938 | 1719658 | 90720 | 1628938 | 305298 | 61060 | 244238 | 239676 | 0 | 239676 | 299676 | 0 | 299676 | 178947 | 35789 | 143158 | 111655 | 0 | 111655 | 141655 | 0 | 141655 | 222038 | 44408 | 177630 | 108933 | 0 | 108933 | 150933 | 0 | 150933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67500 | 13500 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 12379739 | 2470169 | 9909570 | 14318852 | 2863770 | 11455082 | 20055363 | 4011073 | 16044290 | 12379739 | 2470169 | 9909570 | 14318852 | 2863770 | 11455082 | 0 | 112094 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | CCI | 2012 | Q2 | Q2 - 2012 | 2437851 | 2000000 | 437851 | 1114453 | 1008070 | 106383 | 1917086 | 1808070 | 109016 | 13927318 | 1267903 | 12659415 | 10300668 | 1449553 | 8851115 | 11521517 | 1267903 | 10253614 | 447423 | 3617 | 443806 | 406481 | 0 | 406481 | 431481 | 3607 | 427874 | 400000 | 322000 | 78000 | 235273 | 226040 | 9233 | 393273 | 316040 | 77233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061771 | 373000 | 1688771 | 1951860 | 225729 | 1726131 | 2008378 | 319607 | 1688771 | 315000 | 153 | 314847 | 245991 | 0 | 245991 | 285991 | 153 | 285838 | 176000 | 0 | 176000 | 130608 | 0 | 130608 | 142608 | 0 | 142608 | 290000 | 44400 | 245600 | 158304 | 0 | 158304 | 278304 | 40000 | 238304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 14543638 | 2909392 | 11634246 | 16978638 | 3755380 | 13223258 | 20055363 | 4011073 | 16044290 | 14543638 | 2909392 | 11634246 | 16978638 | 3755380 | 13223258 | 0 | 151750 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | CCI | 2012 | Q3 | Q3 - 2012 | 2699851 | 1900409 | 799442 | 2554828 | 1900409 | 654419 | 2699851 | 1900409 | 799442 | 13315318 | 1697624 | 11617694 | 11268477 | 1655069 | 9613408 | 13298476 | 1685068 | 11613408 | 547423 | 0 | 547423 | 418322 | 0 | 418322 | 478322 | 0 | 478322 | 470000 | 323040 | 146960 | 235273 | 226040 | 9233 | 460273 | 321040 | 139233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2111771 | 40000 | 2071771 | 1800210 | 39369 | 1760841 | 1890210 | 39369 | 1850841 | 375000 | 0 | 375000 | 245991 | 0 | 245991 | 335991 | 0 | 335991 | 226000 | 0 | 226000 | 150127 | 0 | 150127 | 163127 | 0 | 163127 | 310000 | 50000 | 260000 | 158304 | 0 | 158304 | 258304 | 0 | 258304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 16831532 | 3820887 | 13010645 | 19584554 | 3945886 | 15638668 | 20055363 | 4011073 | 16044290 | 16831532 | 3820887 | 13010645 | 19584554 | 3945886 | 15638668 | 0 | 210626 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | CCI | 2012 | Q4 | Q4 - 2012 | 2699851 | 1900409 | 799442 | 2561453 | 1900409 | 661044 | 2681452 | 1900409 | 781043 | 13315318 | 1697624 | 11617694 | 11905130 | 1655069 | 10250061 | 12518895 | 1655069 | 10863826 | 547423 | 0 | 547423 | 442965 | 0 | 442965 | 491700 | 0 | 491700 | 470000 | 323040 | 146960 | 345388 | 226040 | 119348 | 433639 | 286679 | 146960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2111771 | 40000 | 2071771 | 1824145 | 39369 | 1784776 | 1884146 | 39369 | 1844777 | 375000 | 0 | 375000 | 278844 | 0 | 278844 | 308844 | 0 | 308844 | 226000 | 0 | 226000 | 162127 | 0 | 162127 | 175127 | 0 | 175127 | 310000 | 50000 | 260000 | 158304 | 0 | 158304 | 250304 | 0 | 250304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 17678356 | 3820887 | 13857469 | 18744107 | 3881526 | 14862581 | 20055363 | 4011073 | 16044290 | 17678356 | 3820887 | 13857469 | 18744107 | 3881526 | 14862581 | 0 | 433759 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | CCI | 2013 | Q1 | Q1 - 2013 | 2699851 | 1900409 | 799442 | 2595351 | 1908592 | 686760 | 2695351 | 1908592 | 786760 | 13315318 | 1697624 | 11617694 | 12454868 | 1746375 | 10708493 | 13076868 | 1796375 | 11280493 | 547423 | 0 | 547423 | 462920 | 0 | 462920 | 482920 | 0 | 482920 | 470000 | 323040 | 146960 | 346067 | 226040 | 120027 | 346067 | 226040 | 120027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2111771 | 40000 | 2071771 | 1874091 | 39369 | 1834722 | 1884091 | 39369 | 1844722 | 375000 | 0 | 375000 | 278844 | 0 | 278844 | 303844 | 0 | 303844 | 226000 | 0 | 226000 | 170127 | 0 | 170127 | 178127 | 0 | 178127 | 310000 | 50000 | 260000 | 238256 | 38574 | 199682 | 238256 | 38574 | 199682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 18420524 | 3958950 | 14461575 | 19205524 | 4008950 | 15196575 | 20055363 | 4011073 | 16044290 | 18420524 | 3958950 | 14461575 | 19205524 | 4008950 | 15196575 | 0 | 605449 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570019 | CCI | 2013 | Q2 | Q2 - 2013 | 2699851 | 1900409 | 799442 | 2644236 | 1935121 | 709115 | 2644236 | 1935121 | 709115 | 13315318 | 1697624 | 11617694 | 12933400 | 1761839 | 11171561 | 12933400 | 1761839 | 11171561 | 547423 | 0 | 547423 | 519651 | 0 | 519651 | 519651 | 0 | 519651 | 470000 | 323040 | 146960 | 346067 | 226040 | 120027 | 346067 | 226040 | 120027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2111771 | 40000 | 2071771 | 1902880 | 39369 | 1863511 | 1902880 | 39369 | 1863511 | 375000 | 0 | 375000 | 297491 | 0 | 297491 | 297491 | 0 | 297491 | 226000 | 0 | 226000 | 171296 | 0 | 171296 | 171296 | 0 | 171296 | 310000 | 50000 | 260000 | 238256 | 38574 | 199682 | 238256 | 38574 | 199682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20055363 | 4011073 | 16044290 | 19053277 | 4000943 | 15052334 | 19053277 | 4000943 | 15052334 | 20055363 | 4011073 | 16044290 | 19053277 | 4000943 | 15052334 | 19053277 | 4000943 | 15052334 | 0 | 719790 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570023 | CCI | 2010 | Q3 | Q3 - 2010 | 15667576 | 0 | 15667576 | 0 | 0 | 0 | 1250000 | 0 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542568 | 0 | 542568 | 405215 | 0 | 405215 | 732505 | 0 | 732505 | 20247000 | 9220000 | 11020000 | 1432000 | 0 | 1432000 | 10587262 | 0 | 10587262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536000 | 0 | 1536000 | 1402605 | 0 | 1402605 | 2420251 | 0 | 2420251 | 384000 | 0 | 384000 | 53193 | 0 | 53193 | 200982 | 0 | 200982 | 753432 | 0 | 753432 | 0 | 0 | 0 | 0 | 0 | 0 | 129500 | 0 | 129500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109600 | 0 | 109600 | 1042790 | 0 | 104279 | 104279 | 0 | 104279 | 39369676 | 9220000 | 30142676 | 4335803 | 0 | 3397292 | 15295279 | 0 | 15295279 | 39369676 | 9220000 | 30142676 | 4335803 | 0 | 3397292 | 15295279 | 0 | 15295279 | 0 | 0 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | CCI | 2010 | Q4 | Q4 - 2010 | 15667576 | 0 | 15667576 | 0 | 0 | 0 | 1250000 | 0 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542568 | 0 | 542568 | 571334 | 0 | 571334 | 936416 | 0 | 936416 | 20247000 | 9227000 | 11020000 | 1432000 | 0 | 1432000 | 7261262 | 0 | 7261262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536000 | 0 | 1536000 | 2138215 | 0 | 2138215 | 2976427 | 0 | 2976427 | 384000 | 0 | 384000 | 53193 | 0 | 53193 | 103193 | 0 | 103193 | 753432 | 0 | 753432 | 0 | 0 | 0 | 0 | 0 | 0 | 129500 | 0 | 129500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109600 | 0 | 109600 | 104279 | 0 | 104279 | 104279 | 0 | 104279 | 39369676 | 9227000 | 30142676 | 4299021 | 0 | 4299021 | 12631577 | 0 | 12631577 | 39369676 | 9227000 | 30142676 | 4299021 | 0 | 4299021 | 12631577 | 0 | 12631577 | 0 | 0 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | CCI | 2011 | Q1 | Q1 - 2011 | 15667576 | 0 | 15667576 | 671884 | 0 | 671884 | 5222625 | 0 | 5222625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542568 | 0 | 542568 | 802279 | 0 | 802279 | 860779 | 0 | 860779 | 20247000 | 9227000 | 11020000 | 1432000 | 0 | 1432000 | 10150462 | 0 | 10150462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536000 | 0 | 1536000 | 1532681 | 0 | 1532681 | 2073312 | 0 | 2073312 | 384000 | 0 | 384000 | 1243121 | 0 | 1243121 | 1503486 | 0 | 1503486 | 753432 | 0 | 753432 | 0 | 0 | 0 | 0 | 0 | 0 | 129500 | 0 | 129500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109600 | 0 | 109600 | 140924 | 65030 | 75894 | 167924 | 65030 | 102894 | 39369676 | 9227000 | 30142676 | 5822889 | 65030 | 5757859 | 19978588 | 65030 | 19913558 | 39369676 | 9227000 | 30142676 | 5822889 | 65030 | 5757859 | 19978588 | 65030 | 19913558 | 0 | 0 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | CCI | 2011 | Q2 | Q2 - 2011 | 15667576 | 0 | 15667576 | 1008879 | 0 | 1008879 | 5736879 | 0 | 5736879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542568 | 0 | 542568 | 863729 | 0 | 863729 | 963549 | 0 | 963549 | 20247000 | 9227000 | 11020000 | 1543258 | 0 | 1543258 | 9662520 | 0 | 9662520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536000 | 0 | 1536000 | 1945931 | 0 | 1945931 | 2314948 | 0 | 2314948 | 384000 | 0 | 384000 | 1433666 | 0 | 1433666 | 1690347 | 0 | 1690347 | 753432 | 0 | 753432 | 0 | 0 | 0 | 375000 | 0 | 375000 | 129500 | 0 | 129500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109600 | 0 | 109600 | 253438 | 150545 | 102893 | 280438 | 150545 | 129893 | 39369676 | 9227000 | 30142676 | 7048901 | 150545 | 6898356 | 21023681 | 150545 | 20873136 | 39369676 | 9227000 | 30142676 | 7048901 | 150545 | 6898356 | 21023681 | 150545 | 20873136 | 0 | 0 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | CCI | 2011 | Q3 | Q3 - 2011 | 15667576 | 0 | 15667576 | 4598907 | 0 | 4598907 | 4627157 | 0 | 4627157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542568 | 0 | 542568 | 1288773 | 0 | 1288773 | 1426273 | 0 | 1426273 | 20247000 | 9227000 | 11020000 | 6708802 | 0 | 6708802 | 16135752 | 9075854 | 7059898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536000 | 0 | 1536000 | 1945931 | 0 | 1945931 | 2430345 | 0 | 2430345 | 384000 | 0 | 384000 | 1433666 | 0 | 1433666 | 1814396 | 0 | 1814396 | 753432 | 0 | 753432 | 140300 | 0 | 140300 | 289640 | 0 | 289640 | 129500 | 0 | 129500 | 129500 | 0 | 129500 | 129500 | 0 | 129500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109600 | 0 | 109600 | 281039 | 151146 | 129893 | 308039 | 151146 | 156893 | 39369676 | 9227000 | 30142676 | 16526918 | 151146 | 16375772 | 27161102 | 9227000 | 17934102 | 39369676 | 9227000 | 30142676 | 16526918 | 151146 | 16375772 | 27161102 | 9227000 | 17934102 | 0 | 0 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | CCI | 2011 | Q4 | Q4 - 2011 | 15667576 | 0 | 15667576 | 4762623 | 0 | 4762623 | 5877565 | 0 | 5877565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542568 | 0 | 542568 | 1884685 | 0 | 1884685 | 2419685 | 0 | 2419685 | 20247000 | 9227000 | 11020000 | 12276612 | 5132101 | 7144511 | 13559368 | 6339857 | 7219511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536000 | 0 | 1536000 | 2543771 | 0 | 2543771 | 3293771 | 0 | 3293771 | 384000 | 0 | 384000 | 1734137 | 0 | 1734137 | 1769137 | 0 | 1769137 | 753432 | 0 | 753432 | 140300 | 0 | 140300 | 365300 | 0 | 365300 | 129500 | 0 | 129500 | 129500 | 0 | 129500 | 129500 | 0 | 129500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109600 | 0 | 109600 | 334387 | 151146 | 183241 | 423592 | 185351 | 238241 | 39369676 | 9227000 | 30142676 | 23806015 | 5283247 | 18522768 | 27837918 | 6525208 | 21312710 | 39369676 | 9227000 | 30142676 | 23806015 | 5283247 | 18522768 | 27837918 | 6525208 | 21312710 | 0 | 0 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | CCI | 2012 | Q1 | Q1 - 2012 | 15667576 | 0 | 15667576 | 5174159 | 0 | 5174159 | 5652021 | 0 | 5652021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542568 | 0 | 542568 | 2054383 | 0 | 2054383 | 2246383 | 0 | 2246383 | 20247000 | 9227000 | 11020000 | 14397917 | 7136406 | 7261511 | 17000460 | 8118949 | 8881511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536000 | 0 | 1536000 | 3316898 | 0 | 3316898 | 4091898 | 0 | 4091898 | 384000 | 0 | 384000 | 2187183 | 0 | 2187183 | 2222183 | 0 | 2222183 | 753432 | 0 | 753432 | 140300 | 0 | 140300 | 365300 | 0 | 365300 | 129500 | 0 | 129500 | 129500 | 0 | 129500 | 646638 | 0 | 646638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109600 | 0 | 109600 | 413622 | 151146 | 262476 | 527827 | 185351 | 342476 | 39369676 | 9227000 | 30142676 | 27813962 | 7287552 | 20526410 | 32752710 | 8304300 | 24448410 | 39369676 | 9227000 | 30142676 | 27813962 | 7287552 | 20526410 | 32752710 | 8304300 | 24448410 | 0 | 0 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | CCI | 2012 | Q2 | Q2 - 2012 | 5652021 | 0 | 5652021 | 4722315 | 0 | 4722315 | 5369315 | 0 | 5369315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3747257 | 0 | 3747257 | 2562339 | 0 | 2562339 | 3070339 | 0 | 3070339 | 18425747 | 9041649 | 9384098 | 15172319 | 7856322 | 7315997 | 15914584 | 8533587 | 7380997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269653 | 0 | 5269653 | 3953751 | 0 | 3953751 | 4703751 | 0 | 4703751 | 2328080 | 0 | 2328080 | 2296948 | 0 | 2296948 | 2299448 | 0 | 2299448 | 795230 | 0 | 795230 | 616756 | 0 | 616756 | 755756 | 0 | 755756 | 2530396 | 0 | 2530396 | 1092208 | 0 | 1092208 | 2067208 | 0 | 2067208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621292 | 185351 | 435941 | 562568 | 232063 | 330505 | 592568 | 232063 | 360505 | 39369676 | 9227000 | 30142676 | 30979204 | 8088385 | 22890819 | 34772969 | 8765650 | 26007319 | 39369676 | 9227000 | 30142676 | 30979204 | 8088385 | 22890819 | 34772969 | 8765650 | 26007319 | 0 | 0 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | CCI | 2012 | Q3 | Q3 - 2012 | 5652021 | 0 | 5652021 | 5120441 | 0 | 5120441 | 5545441 | 0 | 5545441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3747257 | 0 | 3747257 | 3138769 | 0 | 3138769 | 3713769 | 0 | 3713769 | 18425747 | 9041649 | 9384098 | 16007510 | 8653447 | 7354063 | 16675295 | 8821232 | 7854063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269653 | 0 | 5269653 | 4397284 | 0 | 4397284 | 5186284 | 0 | 5186284 | 2328080 | 0 | 2328080 | 2304539 | 0 | 2304539 | 2325539 | 0 | 2325539 | 795230 | 0 | 795230 | 616756 | 0 | 616756 | 776756 | 0 | 776756 | 2530396 | 0 | 2530396 | 1633909 | 0 | 1633909 | 2463909 | 0 | 2463909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621292 | 185351 | 435941 | 606251 | 232063 | 374188 | 616251 | 232063 | 384188 | 39369676 | 9227000 | 30142676 | 33825459 | 8885510 | 24939949 | 37303244 | 9053295 | 28249949 | 39369676 | 9227000 | 30142676 | 33825459 | 8885510 | 24939949 | 37303244 | 9053295 | 28249949 | 0 | 2078 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | CCI | 2012 | Q4 | Q4 - 2012 | 5652021 | 0 | 5652021 | 5377892 | 0 | 5377892 | 5652021 | 0 | 5652021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3747257 | 0 | 3747257 | 3440126 | 0 | 3440126 | 3747257 | 0 | 3747257 | 18425747 | 9041649 | 9384098 | 18525156 | 9464563 | 9060593 | 18848661 | 9464563 | 9384098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269653 | 0 | 5269653 | 4988566 | 0 | 4988566 | 5234808 | 0 | 5234808 | 2328080 | 0 | 2328080 | 2362925 | 0 | 2362925 | 2362925 | 0 | 2362925 | 795230 | 0 | 795230 | 616756 | 0 | 616756 | 795230 | 0 | 795230 | 2530396 | 0 | 2530396 | 2053110 | 0 | 2053110 | 2530396 | 0 | 2530396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621292 | 185351 | 435941 | 665102 | 232063 | 433039 | 668004 | 232063 | 435941 | 39369676 | 9227000 | 30142676 | 38029633 | 9696626 | 28333007 | 39839302 | 9696626 | 30142676 | 39369676 | 9227000 | 30142676 | 38029633 | 9696626 | 28333007 | 39839302 | 9696626 | 30142676 | 0 | 2078 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | CCI | 2013 | Q1 | Q1 - 2013 | 5652021 | 0 | 5652021 | 5545206 | 0 | 5545206 | 5635206 | 0 | 5635206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3747257 | 0 | 3747257 | 3717582 | 0 | 3717582 | 3747257 | 0 | 3747257 | 18425747 | 9041649 | 9384098 | 18378236 | 8994937 | 9383299 | 18378236 | 8994937 | 9383299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269653 | 0 | 5269653 | 5303186 | 0 | 5303186 | 5303186 | 0 | 5303186 | 2328080 | 0 | 2328080 | 2365333 | 0 | 2365333 | 2365333 | 0 | 2365333 | 795230 | 0 | 795230 | 677130 | 0 | 677130 | 697130 | 0 | 697130 | 2530396 | 0 | 2530396 | 2133395 | 0 | 2133395 | 2260524 | 0 | 2260524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621292 | 185351 | 435941 | 715999 | 232063 | 483936 | 715999 | 232063 | 483936 | 39369676 | 9227000 | 30142676 | 38836067 | 9227000 | 29609067 | 39102871 | 9227000 | 29875871 | 39369676 | 9227000 | 30142676 | 38836067 | 9227000 | 29609067 | 39102871 | 9227000 | 29875871 | 0 | 26878 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | CCI | 2013 | Q2 | Q2 - 2013 | 5652021 | 0 | 5652021 | 5662676 | 0 | 5662676 | 5662676 | 0 | 5662676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3747257 | 0 | 3747257 | 3747257 | 0 | 3747257 | 3747257 | 0 | 3747257 | 18425747 | 9041649 | 9384098 | 18637469 | 8994937 | 9642532 | 18675545 | 8994937 | 9680608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269653 | 0 | 5269653 | 5303186 | 0 | 5303186 | 5303186 | 0 | 5303186 | 2328080 | 0 | 2328080 | 2365333 | 0 | 2365333 | 2365333 | 0 | 2365333 | 795230 | 0 | 795230 | 677130 | 0 | 677130 | 677130 | 0 | 677130 | 2530396 | 0 | 2530396 | 2222550 | 0 | 2222550 | 2222550 | 0 | 2222550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621292 | 185351 | 435941 | 715999 | 232063 | 483936 | 715999 | 232063 | 483936 | 39369676 | 9227000 | 30142676 | 39331600 | 9227000 | 30104600 | 39369676 | 9227000 | 30142676 | 39369676 | 9227000 | 30142676 | 39331600 | 9227000 | 30104600 | 39369676 | 9227000 | 30142676 | 0 | 35478 | North Florida Broadband Authority | TRUE
NT10BIX5570023 | CCI | 2013 | Q3 | Q3 - 2013 | 5652021 | 0 | 5652021 | 5662676 | 0 | 5662676 | 5662676 | 0 | 5662676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3747257 | 0 | 3747257 | 3747257 | 0 | 3747257 | 3747257 | 0 | 3747257 | 18425747 | 9041649 | 9384098 | 18675545 | 8994937 | 9680608 | 18675545 | 8994937 | 9680608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269653 | 0 | 5269653 | 5303186 | 0 | 5303186 | 5303186 | 0 | 5303186 | 2328080 | 0 | 2328080 | 2365333 | 0 | 2365333 | 2365333 | 0 | 2365333 | 795230 | 0 | 795230 | 677130 | 0 | 677130 | 677130 | 0 | 677130 | 2530396 | 0 | 2530396 | 2222550 | 0 | 2222550 | 2222550 | 0 | 2222550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621292 | 185351 | 435941 | 715999 | 232063 | 483936 | 715999 | 232063 | 483936 | 39369676 | 9227000 | 30142676 | 39369676 | 9227000 | 30142676 | 39369676 | 9227000 | 30142676 | 39369676 | 9227000 | 30142676 | 39369676 | 9227000 | 30142676 | 39369676 | 9227000 | 30142676 | 0 | 0 | North Florida Broadband Authority | TRUE
NT10BIX5570024 | CCI | 2010 | Q3 | Q3 - 2010 | 3708900 | 741780 | 2967120 | 0 | 0 | 0 | 0 | 0 | 0 | 7742930 | 1908078 | 5834852 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 2362 | 473 | 1890 | 2363 | 473 | 1890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 65166 | 13033 | 52133 | 65166 | 13033 | 52133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 50607 | 10092 | 40515 | 118136 | 23598 | 94538 | 17495691 | 4094595 | 13401096 | 118135 | 23598 | 94538 | 185665 | 37104 | 148561 | 17495691 | 4094595 | 13401096 | 118135 | 23598 | 94538 | 185665 | 37104 | 148561 | 0 | 0 | University of Utah, The | TRUE
NT10BIX5570024 | CCI | 2010 | Q4 | Q4 - 2010 | 3708900 | 741780 | 2967120 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 7742930 | 1908078 | 5834852 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 2363 | 472 | 1890 | 2363 | 472 | 1890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 76697 | 15339 | 61357 | 76697 | 15339 | 61357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 57335 | 11438 | 45898 | 183526 | 36705 | 146821 | 17495691 | 4094595 | 13401096 | 136395 | 27249 | 109145 | 412586 | 82516 | 330068 | 17495691 | 4094595 | 13401096 | 136395 | 27249 | 109145 | 412586 | 82516 | 330068 | 0 | 0 | University of Utah, The | TRUE
NT10BIX5570024 | CCI | 2011 | Q1 | Q1 - 2011 | 3708900 | 741780 | 2967120 | 111549 | 22310 | 89240 | 242073 | 48415 | 193658 | 7742930 | 1908078 | 5834852 | 0 | 0 | 0 | 1458172 | 359335 | 1098837 | 3500 | 3500 | 0 | 2363 | 2363 | 0 | 2363 | 2363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 51931 | 24171 | 27760 | 302847 | 14375 | 288472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 79896 | 18139 | 61757 | 80648 | 18890 | 61757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 68590 | 13688 | 54901 | 528742 | 468796 | 59945 | 17495691 | 4094595 | 13401096 | 314329 | 80671 | 233658 | 2614845 | 912174 | 1702669 | 17495691 | 4094595 | 13401096 | 314329 | 80671 | 233658 | 2614845 | 912174 | 1702669 | 0 | 0 | University of Utah, The | TRUE
NT10BIX5570024 | CCI | 2011 | Q2 | Q2 - 2011 | 3708900 | 741780 | 2967120 | 244912 | 48982 | 195930 | 374808 | 74962 | 299846 | 7742930 | 1908078 | 5834852 | 156813 | 39203 | 117610 | 2252995 | 495406 | 1757589 | 3500 | 3500 | 0 | 2363 | 2363 | 0 | 2363 | 2363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 273475 | 14375 | 259100 | 456476 | 14375 | 442101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 89590 | 22833 | 66757 | 157679 | 37442 | 120237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 585918 | 516429 | 69489 | 585918 | 516429 | 69489 | 17495691 | 4094595 | 13401096 | 1353071 | 644185 | 708886 | 3830239 | 1140977 | 2689262 | 17495691 | 4094595 | 13401096 | 1353071 | 644185 | 708886 | 3830239 | 1140977 | 2689262 | 0 | 0 | University of Utah, The | TRUE
NT10BIX5570024 | CCI | 2011 | Q3 | Q3 - 2011 | 3708900 | 741780 | 2967120 | 364199 | 72840 | 291360 | 476096 | 95219 | 380877 | 7742930 | 1908078 | 5834852 | 855835 | 213959 | 641876 | 2487027 | 621757 | 1865270 | 3500 | 3500 | 0 | 2363 | 2363 | 0 | 2363 | 2363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 461820 | 14375 | 447445 | 688587 | 14375 | 674212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 151929 | 37120 | 114808 | 211180 | 49486 | 161694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 589034 | 516429 | 72605 | 594312 | 516429 | 77883 | 17495691 | 4094595 | 13401096 | 2425180 | 857086 | 1568094 | 4459565 | 1299629 | 3159936 | 17495691 | 4094595 | 13401096 | 2425180 | 857086 | 1568094 | 4459565 | 1299629 | 3159936 | 0 | 0 | University of Utah, The | TRUE
NT10BIX5570024 | CCI | 2011 | Q4 | Q4 - 2011 | 3708900 | 741780 | 2967120 | 365096 | 73019 | 292077 | 1686107 | 337221 | 1348886 | 7742930 | 1908078 | 5834852 | 3101345 | 775336 | 2326009 | 5417301 | 1354325 | 4062976 | 3500 | 3500 | 0 | 2363 | 2363 | 0 | 2363 | 2363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 655592 | 14375 | 641217 | 872015 | 14375 | 857640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 207849 | 51654 | 156195 | 228682 | 52988 | 175694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 594604 | 516429 | 78175 | 594604 | 516429 | 78175 | 17495691 | 4094595 | 13401096 | 4926849 | 1433176 | 3493673 | 8801072 | 2277701 | 6523371 | 17495691 | 4094595 | 13401096 | 4926849 | 1433176 | 3493673 | 8801072 | 2277701 | 6523371 | 0 | 0 | University of Utah, The | TRUE
NT10BIX5570024 | CCI | 2012 | Q1 | Q1 - 2012 | 3702446 | 740489 | 2961957 | 1701646 | 339946 | 1361700 | 1762714 | 352160 | 1410554 | 7742930 | 1908078 | 5834852 | 3888748 | 972187 | 2916561 | 4260681 | 1065170 | 3195511 | 3500 | 3500 | 0 | 3490 | 3490 | 0 | 3490 | 3490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 728213 | 14375 | 713838 | 850527 | 14375 | 836152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 283432 | 68322 | 215110 | 339032 | 79442 | 259590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579770 | 496851 | 82919 | 594604 | 516429 | 78175 | 594604 | 516429 | 78175 | 17495691 | 4094595 | 13401096 | 7200133 | 1914749 | 5285384 | 7811048 | 2031066 | 5779982 | 17495691 | 4094595 | 13401096 | 7200133 | 1914749 | 5285384 | 7811048 | 2031066 | 5779982 | 0 | 0 | University of Utah, The | TRUE
NT10BIX5570024 | CCI | 2012 | Q2 | Q2 - 2012 | 3708900 | 741780 | 2967120 | 1857613 | 371522 | 1486091 | 2451512 | 490302 | 1961210 | 7742930 | 1908078 | 5834852 | 4785785 | 1196442 | 3589343 | 5514424 | 1378602 | 4135822 | 3500 | 3500 | 0 | 3490 | 3490 | 0 | 3490 | 3490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 834280 | 14375 | 819905 | 867816 | 14375 | 853441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 368015 | 91344 | 276671 | 444267 | 106594 | 337673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 603503 | 518209 | 85294 | 603503 | 518209 | 85294 | 17495691 | 4094595 | 13401096 | 8452686 | 2195382 | 6257304 | 9885012 | 2511572 | 7373440 | 17495691 | 4094595 | 13401096 | 8452686 | 2195382 | 6257304 | 9885012 | 2511572 | 7373440 | 0 | 0 | University of Utah, The | TRUE
NT10BIX5570024 | CCI | 2012 | Q3 | Q3 - 2012 | 3708900 | 741780 | 2967120 | 2298283 | 459656 | 1838627 | 3928455 | 785691 | 3142764 | 7742930 | 1908078 | 5834852 | 5556922 | 1388969 | 4167953 | 5700546 | 1424875 | 4275671 | 3500 | 3500 | 0 | 3490 | 3490 | 0 | 3490 | 3490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 891999 | 14375 | 877624 | 951999 | 14375 | 937624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4193670 | 931302 | 3262368 | 443702 | 106957 | 336745 | 445934 | 107403 | 338531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573316 | 495560 | 77756 | 603503 | 518209 | 85294 | 603503 | 518209 | 85294 | 17495691 | 4094595 | 13401096 | 9797899 | 2491656 | 7306243 | 11633927 | 2854043 | 8779884 | 17495691 | 4094595 | 13401096 | 9797899 | 2491656 | 7306243 | 11633927 | 2854043 | 8779884 | 0 | 0 | University of Utah, The | TRUE
NT10BIX5570024 | CCI | 2012 | Q4 | Q4 - 2012 | 7150931 | 1430186 | 5720745 | 2347805 | 469561 | 1878244 | 4059816 | 811963 | 3247853 | 7742930 | 1908078 | 5834852 | 5700546 | 1424875 | 4275671 | 5737262 | 1434054 | 4303208 | 3500 | 3500 | 0 | 3490 | 3490 | 0 | 3490 | 3490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 977306 | 14375 | 962931 | 1009306 | 14375 | 994931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685185 | 229597 | 455588 | 446673 | 107551 | 339122 | 447784 | 107773 | 340011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 639770 | 508859 | 130911 | 603503 | 518209 | 85294 | 630172 | 523543 | 106629 | 17495691 | 4094595 | 13401096 | 10079323 | 2538061 | 7541262 | 11887830 | 2895198 | 8992632 | 17495691 | 4094595 | 13401096 | 10079323 | 2538061 | 7541262 | 11887830 | 2895198 | 8992632 | 0 | 0 | University of Utah, The | TRUE
NT10BIX5570024 | CCI | 2013 | Q1 | Q1 - 2013 | 7150931 | 1430186 | 5720745 | 3668965 | 733790 | 2935175 | 7177255 | 1435451 | 5741804 | 7742930 | 1908078 | 5834852 | 5738097 | 1434263 | 4303834 | 6938980 | 1734484 | 5204496 | 3500 | 3500 | 0 | 3490 | 3490 | 0 | 3490 | 3490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 1069626 | 14375 | 1055251 | 1084626 | 14375 | 1070251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685185 | 229597 | 455588 | 447923 | 107801 | 340122 | 449923 | 109801 | 340122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 639770 | 508859 | 130911 | 611374 | 519783 | 91591 | 659024 | 529313 | 129711 | 17495691 | 4094595 | 13401096 | 11539475 | 2813502 | 8725973 | 16313298 | 3826914 | 12486384 | 17495691 | 4094595 | 13401096 | 11539475 | 2813502 | 8725973 | 16313298 | 3826914 | 12486384 | 0 | 0 | University of Utah, The | TRUE
NT10BIX5570024 | CCI | 2013 | Q2 | Q2 - 2013 | 7150931 | 1430186 | 5720745 | 6809912 | 1361982 | 5447930 | 6809912 | 1361982 | 5447930 | 7742930 | 1908078 | 5834852 | 7273567 | 1818130 | 5455437 | 7273567 | 1818130 | 5455437 | 3500 | 3500 | 0 | 3490 | 3490 | 0 | 3490 | 3490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273375 | 14375 | 1259000 | 1152588 | 14375 | 1138213 | 1152588 | 14375 | 1138213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685185 | 229597 | 455588 | 448332 | 108210 | 340122 | 448332 | 108210 | 340122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 639770 | 508859 | 130911 | 657385 | 528985 | 128400 | 657385 | 528985 | 128400 | 17495691 | 4094595 | 13401096 | 16345274 | 3835172 | 12510102 | 16345274 | 3835172 | 12510102 | 17495691 | 4094595 | 13401096 | 16345274 | 3835172 | 12510102 | 16345274 | 3835172 | 12510102 | 0 | 0 | University of Utah, The | TRUE
NT10BIX5570025 | CCI | 2010 | Q3 | Q3 - 2010 | 1113000 | 222600 | 890400 | 0 | 0 | 0 | 0 | 0 | 0 | 32260736 | 5572147 | 22288589 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 991980 | 198396 | 793584 | 398621 | 79724 | 318897 | 174596 | 34819 | 139677 | 939678 | 187936 | 751742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35825394 | 6285079 | 24852315 | 518621 | 103724 | 414897 | 294596 | 58819 | 235677 | 35825394 | 6285079 | 24852315 | 518621 | 103724 | 414897 | 294596 | 58819 | 235677 | 0 | 0 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570025 | CCI | 2010 | Q4 | Q4 - 2010 | 1113000 | 222600 | 890400 | 0 | 0 | 0 | 556500 | 111300 | 445200 | 30336358 | 9587272 | 20749086 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1741602 | 348320 | 1393282 | 56733 | 11347 | 45386 | 113466 | 22693 | 90773 | 2114434 | 422887 | 1691547 | 0 | 0 | 0 | 951495 | 190299 | 761196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 0 | 0 | 0 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35825394 | 10685079 | 25140315 | 176733 | 35347 | 141386 | 1941461 | 388292 | 1553169 | 35825394 | 10685079 | 25140315 | 176733 | 35347 | 141386 | 1941461 | 388292 | 1553169 | 0 | 0 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570025 | CCI | 2011 | Q1 | Q1 - 2011 | 1113000 | 222600 | 890400 | 0 | 0 | 0 | 0 | 0 | 0 | 30336358 | 9587272 | 20749086 | 36067 | 7213 | 28854 | 1800000 | 360000 | 1440000 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1741602 | 348320 | 1393282 | 765142 | 153029 | 612113 | 1315143 | 263029 | 1052114 | 2114434 | 422887 | 1691547 | 721868 | 144374 | 577495 | 956383 | 191277 | 756106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 0 | 0 | 0 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35825394 | 10685079 | 25140315 | 1643077 | 328616 | 1314462 | 4391526 | 878306 | 3504220 | 35825394 | 10685079 | 25140315 | 1643077 | 328616 | 1314462 | 4391526 | 878306 | 3504220 | 0 | 0 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570025 | CCI | 2011 | Q2 | Q2 - 2011 | 1113000 | 222600 | 890400 | 0 | 0 | 0 | 222600 | 44520 | 178080 | 30336358 | 9587272 | 20749086 | 3223987 | 644797 | 2579190 | 10906018 | 2181204 | 8724814 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1741602 | 348320 | 1393282 | 1212451 | 242490 | 969961 | 1508984 | 301797 | 1207187 | 2114434 | 422887 | 1691547 | 997485 | 199497 | 797988 | 1336584 | 267317 | 1069267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 14626 | 2925 | 11701 | 98444 | 19689 | 78755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35825394 | 10685079 | 25140315 | 5568549 | 1113709 | 4454840 | 14192630 | 2838527 | 11354103 | 35825394 | 10685079 | 25140315 | 5568549 | 1113709 | 4454840 | 14192630 | 2838527 | 11354103 | 0 | 0 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570025 | CCI | 2011 | Q3 | Q3 - 2011 | 1113000 | 222600 | 890400 | 0 | 0 | 0 | 1113000 | 222600 | 890400 | 30336358 | 9587272 | 20749086 | 6468227 | 1293645 | 5174582 | 10168227 | 2033645 | 8134582 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 120000 | 24000 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1741602 | 348320 | 1393282 | 1450329 | 290066 | 1160263 | 1632507 | 326502 | 1306005 | 2114434 | 422887 | 1691547 | 1290281 | 258056 | 1032225 | 1646281 | 329256 | 1317025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 106372 | 21154 | 84618 | 218015 | 43603 | 174412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35825394 | 10685079 | 25140315 | 9435209 | 1886921 | 7547688 | 14898030 | 2979606 | 11918424 | 35825394 | 10685079 | 25140315 | 9435209 | 1886921 | 7547688 | 14898030 | 2979606 | 11918424 | 0 | 0 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570026 | CCI | 2010 | Q3 | Q3 - 2010 | 5850000 | 1610000 | 4240000 | 0 | 0 | 0 | 0 | 0 | 0 | 119429848 | 24229170 | 95200678 | 0 | 0 | 0 | 20000 | 0 | 20000 | 1153183 | 1153183 | 0 | 252226 | 252226 | 0 | 362726 | 362726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 155000 | 220000 | 24974 | 10489 | 14485 | 54974 | 23089 | 31885 | 1625000 | 1625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 277200 | 262715 | 14485 | 437700 | 385815 | 51885 | 128958031 | 29297353 | 99660678 | 277200 | 262715 | 14485 | 437700 | 385815 | 51885 | 0 | 0 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | CCI | 2010 | Q4 | Q4 - 2010 | 5850000 | 1610000 | 4240000 | 0 | 0 | 0 | 0 | 0 | 0 | 118892448 | 23691770 | 95200678 | 0 | 0 | 0 | 20000 | 0 | 20000 | 3513083 | 3513083 | 0 | 334210 | 334210 | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 51390 | 36905 | 14485 | 72860 | 50000 | 22860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 385600 | 371115 | 14485 | 592860 | 550000 | 42860 | 128958031 | 29297353 | 99660678 | 385600 | 371115 | 14485 | 592860 | 550000 | 42860 | 0 | 0 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | CCI | 2011 | Q1 | Q1 - 2011 | 5850000 | 1610000 | 4240000 | 0 | 0 | 0 | 0 | 0 | 0 | 118892448 | 23691770 | 95200678 | 19250 | 0 | 19250 | 34417863 | 6879722 | 27538141 | 3513083 | 3513083 | 0 | 418853 | 418853 | 0 | 579091 | 579091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 125137 | 51443 | 73694 | 149377 | 51443 | 97934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 563240 | 470296 | 92944 | 35146331 | 7510256 | 27636075 | 128958031 | 29297353 | 99660678 | 563240 | 470296 | 92944 | 35146331 | 7510256 | 27636075 | 0 | 0 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | CCI | 2011 | Q2 | Q2 - 2011 | 5850000 | 1610000 | 4240000 | 0 | 0 | 0 | 0 | 0 | 0 | 118892448 | 23691770 | 95200678 | 27455436 | 5487237 | 21968199 | 37093597 | 7093597 | 30000000 | 3513083 | 3513083 | 0 | 645159 | 645159 | 0 | 895159 | 895159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 339059 | 202254 | 136805 | 425994 | 259254 | 166740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 28439654 | 6334650 | 22105004 | 38414750 | 8248010 | 30166740 | 128958031 | 29297353 | 99660678 | 28439654 | 6334650 | 22105004 | 38414750 | 8248010 | 30166740 | 0 | 0 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | CCI | 2011 | Q3 | Q3 - 2011 | 5850000 | 1610000 | 4240000 | 715196 | 0 | 715196 | 3258235 | 543039 | 2715196 | 118892448 | 23691770 | 95200678 | 32785119 | 6553174 | 26231945 | 69385119 | 13153174 | 56231945 | 3513083 | 3513083 | 0 | 777186 | 777186 | 0 | 927186 | 927186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 444497 | 292500 | 151997 | 469497 | 292500 | 176997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 34721998 | 7622860 | 27099138 | 74040037 | 14915899 | 59124138 | 128958031 | 29297353 | 99660678 | 34721998 | 7622860 | 27099138 | 74040037 | 14915899 | 59124138 | 0 | 0 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | CCI | 2011 | Q4 | Q4 - 2011 | 5850000 | 1610000 | 4240000 | 4596314 | 1981118 | 2615196 | 6300000 | 2300000 | 4000000 | 118892448 | 23691770 | 95200678 | 61997789 | 12395708 | 49602081 | 80053989 | 16006948 | 64047041 | 3513083 | 3513083 | 0 | 1023552 | 1023552 | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 459913 | 292500 | 167413 | 506163 | 292500 | 213663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 68077568 | 15692878 | 52384690 | 88360152 | 20099448 | 68260704 | 128958031 | 29297353 | 99660678 | 68077568 | 15692878 | 52384690 | 88360152 | 20099448 | 68260704 | 0 | 0 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | CCI | 2012 | Q1 | Q1 - 2012 | 5850000 | 1610000 | 4240000 | 5260592 | 1610000 | 3650592 | 5850000 | 1610000 | 4240000 | 118892448 | 23691770 | 95200678 | 83930814 | 16782313 | 67148501 | 99500000 | 19500000 | 80000000 | 3513083 | 3513083 | 0 | 3041347 | 3041347 | 0 | 3513083 | 3513083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 483038 | 292500 | 190538 | 507500 | 292500 | 215000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 92905791 | 21916160 | 70989631 | 109560583 | 25105583 | 84455000 | 128958031 | 29297353 | 99660678 | 92905791 | 21916160 | 70989631 | 109560583 | 25105583 | 84455000 | 0 | 0 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | CCI | 2012 | Q2 | Q2 - 2012 | 5850000 | 1610000 | 4240000 | 5460837 | 1610000 | 3850837 | 5610000 | 1610000 | 4000000 | 118892448 | 23691770 | 95200678 | 84149308 | 16782313 | 67366995 | 99500000 | 19500000 | 80000000 | 3513083 | 3513083 | 0 | 3122670 | 3122670 | 0 | 3250000 | 3250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 93435315 | 21997483 | 71437832 | 109062500 | 24842500 | 84220000 | 128958031 | 29297353 | 99660678 | 93435315 | 21997483 | 71437832 | 109062500 | 24842500 | 84220000 | 0 | 0 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | CCI | 2012 | Q3 | Q3 - 2012 | 5850000 | 1610000 | 4240000 | 5473356 | 1610000 | 3863356 | 5557240 | 1610000 | 3947240 | 118892448 | 23691770 | 95200678 | 96582465 | 19268944 | 77313521 | 103785294 | 20709510 | 83075784 | 3513083 | 3513083 | 0 | 3217400 | 3217400 | 0 | 3513083 | 3513083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 105975721 | 24578844 | 81396877 | 113558117 | 26315093 | 87243024 | 128958031 | 29297353 | 99660678 | 105975721 | 24578844 | 81396877 | 113558117 | 26315093 | 87243024 | 0 | 500000 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | CCI | 2012 | Q4 | Q4 - 2012 | 5850000 | 1610000 | 4240000 | 5473356 | 1610000 | 3863356 | 5850000 | 1610000 | 4240000 | 118892448 | 23691770 | 95200678 | 108971911 | 21833553 | 87138358 | 113000000 | 23000000 | 90000000 | 3513083 | 3513083 | 0 | 3513083 | 3513083 | 0 | 3513083 | 3513083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 118660850 | 27439136 | 91221714 | 123065583 | 28605583 | 94460000 | 128958031 | 29297353 | 99660678 | 118660850 | 27439136 | 91221714 | 123065583 | 28605583 | 94460000 | 0 | 543526 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | CCI | 2013 | Q1 | Q1 - 2013 | 5850000 | 1610000 | 4240000 | 5739994 | 1610000 | 4129994 | 5850000 | 1610000 | 4240000 | 118892448 | 23691770 | 95200678 | 112882085 | 22615588 | 90266497 | 118892448 | 23691770 | 95200678 | 3513083 | 3513083 | 0 | 3513083 | 3513083 | 0 | 3513083 | 3513083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 122837662 | 28221171 | 94616491 | 128958031 | 29297353 | 99660678 | 128958031 | 29297353 | 99660678 | 122837662 | 28221171 | 94616491 | 128958031 | 29297353 | 99660678 | 0 | 578562 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570026 | CCI | 2013 | Q2 | Q2 - 2013 | 5850000 | 1610000 | 4240000 | 5850000 | 1610000 | 4240000 | 5850000 | 1610000 | 4240000 | 118892448 | 23691770 | 95200678 | 118892448 | 23691770 | 95200578 | 118892448 | 23691770 | 95200678 | 3513083 | 3513083 | 0 | 3513083 | 3513083 | 0 | 3513083 | 3513083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 512500 | 292500 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128958031 | 29297353 | 99660678 | 128958031 | 29297353 | 99660578 | 128958031 | 29297353 | 99660678 | 128958031 | 29297353 | 99660678 | 128958031 | 29297353 | 99660578 | 128958031 | 29297353 | 99660678 | 0 | 578562 | Keystone Initiative For Network Based Education and Research | TRUE
NT10BIX5570027 | CCI | 2010 | Q3 | Q3 - 2010 | 5360084 | 1608025 | 3752059 | 0 | 0 | 0 | 0 | 0 | 0 | 10076115 | 3392658 | 6683458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 76500 | 178500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911500 | 273450 | 638050 | 78793 | 23638 | 55155 | 558162 | 167449 | 390713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252067 | 78793 | 23638 | 55155 | 558162 | 167449 | 390713 | 16602699 | 5350633 | 11252067 | 78793 | 23638 | 55155 | 558162 | 167449 | 390713 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | CCI | 2010 | Q4 | Q4 - 2010 | 5360084 | 1608025 | 3752059 | 0 | 0 | 0 | 0 | 0 | 0 | 10076115 | 3392658 | 6683457 | 0 | 0 | 0 | 510000 | 153000 | 357000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 76500 | 178500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911500 | 273450 | 638050 | 399225 | 119768 | 279457 | 576036 | 172811 | 403225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 399225 | 119768 | 279457 | 1086036 | 325811 | 760225 | 16602699 | 5350633 | 11252066 | 399225 | 119768 | 279457 | 1086036 | 325811 | 760225 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | CCI | 2011 | Q1 | Q1 - 2011 | 5360084 | 1608025 | 3752059 | 0 | 0 | 0 | 1182930 | 354879 | 828051 | 10076115 | 3392658 | 6683457 | 563915 | 169174 | 394740 | 3526640 | 1057992 | 2468648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 76500 | 178500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911500 | 273450 | 638050 | 604090 | 181227 | 422863 | 821987 | 246596 | 575391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 1168005 | 350401 | 817603 | 5531557 | 1659467 | 3872090 | 16602699 | 5350633 | 11252066 | 1168005 | 350401 | 817603 | 5531557 | 1659467 | 3872090 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | CCI | 2011 | Q2 | Q2 - 2011 | 5360084 | 1608025 | 3752059 | 1024773 | 307432 | 717341 | 3367294 | 1010188 | 2357106 | 10076115 | 3392658 | 6683457 | 3300576 | 990173 | 2310403 | 5138644 | 1541593 | 3597051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 76500 | 178500 | 0 | 0 | 0 | 105147 | 31544 | 73603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911500 | 273450 | 638050 | 907802 | 272341 | 635461 | 1041516 | 312455 | 729061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 5233151 | 1569946 | 3663205 | 9652601 | 2895780 | 6756821 | 16602699 | 5350633 | 11252066 | 5233151 | 1569946 | 3663205 | 9652601 | 2895780 | 6756821 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | CCI | 2011 | Q3 | Q3 - 2011 | 5360084 | 1608025 | 3752059 | 2543066 | 762920 | 1780146 | 2793066 | 837920 | 1955146 | 10076115 | 3392658 | 6683457 | 5442284 | 1892379 | 3549905 | 6983487 | 2354740 | 4628747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 76500 | 178500 | 157502 | 47251 | 110251 | 307502 | 92250 | 215251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911500 | 273450 | 638050 | 1308816 | 392645 | 916171 | 1772863 | 531859 | 1241004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 9451668 | 3095195 | 6356473 | 11856918 | 3816769 | 8040148 | 16602699 | 5350633 | 11252066 | 9451668 | 3095195 | 6356473 | 11856918 | 3816769 | 8040148 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | CCI | 2011 | Q4 | Q4 - 2011 | 4858938 | 1457797 | 3401141 | 4069330 | 1220799 | 2848531 | 4615991 | 1384797 | 3231194 | 9416893 | 3194720 | 6222173 | 7055746 | 2376418 | 4679328 | 8375350 | 2772299 | 5603051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 572995 | 171912 | 401083 | 281907 | 84572 | 197335 | 515696 | 154709 | 360987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753873 | 526204 | 1227669 | 1657055 | 497117 | 1159938 | 1753873 | 526204 | 1227669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 13064038 | 4178906 | 8885132 | 15260910 | 4838009 | 10422901 | 16602699 | 5350633 | 11252066 | 13064038 | 4178906 | 8885132 | 15260910 | 4838009 | 10422901 | 0 | 95961 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | CCI | 2012 | Q1 | Q1 - 2012 | 5040447 | 1546333 | 3494114 | 4554946 | 1389976 | 3164970 | 5040447 | 1546333 | 3494114 | 8998342 | 3017732 | 5980610 | 8083897 | 2723558 | 5360339 | 8998342 | 3017732 | 5980610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 666018 | 204324 | 461694 | 666018 | 204324 | 461694 | 666018 | 204324 | 461694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1897892 | 582244 | 1315648 | 1754719 | 535466 | 1219253 | 1897892 | 582244 | 1315648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 15059580 | 4853324 | 10206256 | 16602699 | 5350633 | 11252066 | 16602699 | 5350633 | 11252066 | 15059580 | 4853324 | 10206256 | 16602699 | 5350633 | 11252066 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | CCI | 2012 | Q2 | Q2 - 2012 | 4969701 | 1601610 | 3368091 | 4568987 | 1395671 | 3173316 | 4969701 | 1601610 | 3368091 | 8998342 | 2899939 | 6098403 | 8570792 | 2875754 | 5695039 | 8998342 | 2899939 | 6098403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 736764 | 237441 | 499323 | 736764 | 237441 | 499323 | 736764 | 237441 | 499323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1897892 | 611643 | 1286249 | 1800797 | 550083 | 1250714 | 1897892 | 611643 | 1286249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 15677340 | 5058949 | 10618392 | 16602699 | 5350633 | 11252066 | 16602699 | 5350633 | 11252066 | 15677340 | 5058949 | 10618392 | 16602699 | 5350633 | 11252066 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | CCI | 2012 | Q3 | Q3 - 2012 | 4969701 | 1524629 | 3445072 | 4709129 | 1440993 | 3268136 | 4969701 | 1524629 | 3445072 | 8953674 | 3004028 | 5949646 | 8575884 | 2881687 | 5694197 | 8953674 | 3004028 | 5949646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 736764 | 226028 | 510736 | 736764 | 226028 | 510736 | 736764 | 226028 | 510736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1942560 | 595948 | 1346612 | 1942560 | 595948 | 1346612 | 1942560 | 595948 | 1346612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 15964337 | 5144656 | 10819681 | 16602699 | 5350633 | 11252066 | 16602699 | 5350633 | 11252066 | 15964337 | 5144656 | 10819681 | 16602699 | 5350633 | 11252066 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | CCI | 2012 | Q4 | Q4 - 2012 | 4831569 | 1482252 | 3349317 | 4709129 | 1440993 | 3268136 | 4831569 | 1482252 | 3349317 | 9085464 | 3044459 | 6041005 | 8575884 | 2881687 | 5694197 | 9085464 | 3044459 | 6041005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 736764 | 226028 | 510736 | 736764 | 226028 | 510736 | 736764 | 226028 | 510736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1948902 | 597894 | 1351008 | 1942560 | 595948 | 1346612 | 1948902 | 597894 | 1351008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16602699 | 5350633 | 11252066 | 15964337 | 5144656 | 10819681 | 16602699 | 5350633 | 11252066 | 16602699 | 5350633 | 11252066 | 15964337 | 5144656 | 10819681 | 16602699 | 5350633 | 11252066 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570027 | CCI | 2013 | Q1 | Q1 - 2013 | 4764147 | 1461396 | 3302751 | 4764147 | 1461396 | 3302751 | 4764147 | 1461396 | 3302751 | 9085464 | 3044144 | 6041320 | 9085464 | 3044144 | 6041320 | 9085464 | 3044144 | 6041320 | 29630 | 9089 | 20541 | 29630 | 9089 | 20541 | 29630 | 9089 | 20541 | 736764 | 226001 | 510763 | 736764 | 226001 | 510763 | 736764 | 226001 | 510763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1948902 | 597823 | 1351079 | 1948902 | 597823 | 1351079 | 1948902 | 597823 | 1351079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16564907 | 5338453 | 11226454 | 16564907 | 5338453 | 11226454 | 16564907 | 5338453 | 11226454 | 16564907 | 5338453 | 11226454 | 16564907 | 5338453 | 11226454 | 16564907 | 5338453 | 11226454 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570028 | CCI | 2010 | Q3 | Q3 - 2010 | 10625045 | 2125009 | 8500036 | 0 | 0 | 0 | 0 | 0 | 0 | 15625518 | 3125104 | 12500415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1937786 | 387557 | 1550229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534610 | 106922 | 427688 | 0 | 0 | 0 | 0 | 0 | 0 | 28722959 | 5744592 | 22978368 | 0 | 0 | 0 | 0 | 0 | 0 | 28722959 | 5744592 | 22978368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Administration, Wisconsin Department of | TRUE
NT10BIX5570028 | CCI | 2010 | Q4 | Q4 - 2010 | 10625045 | 2125009 | 8500036 | 0 | 0 | 0 | 106300 | 85040 | 21260 | 15625518 | 3125104 | 12500414 | 0 | 0 | 0 | 74000 | 14800 | 59200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1937786 | 387557 | 1550229 | 0 | 0 | 0 | 30100 | 6020 | 24080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534610 | 106922 | 427688 | 0 | 0 | 0 | 481100 | 96220 | 384880 | 28722959 | 5744592 | 22978367 | 0 | 0 | 0 | 691500 | 202080 | 489420 | 28722959 | 5744592 | 22978367 | 0 | 0 | 0 | 691500 | 202080 | 489420 | 0 | 0 | Administration, Wisconsin Department of | TRUE
NT10BIX5570028 | CCI | 2011 | Q1 | Q1 - 2011 | 10625045 | 2125009 | 8500036 | 0 | 0 | 0 | 0 | 0 | 0 | 15625518 | 3125104 | 12500414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1937786 | 387557 | 1550229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534610 | 106922 | 427688 | 0 | 0 | 0 | 45761 | 9152 | 36609 | 28722959 | 5744592 | 22978367 | 0 | 0 | 0 | 45761 | 9152 | 36609 | 28722959 | 5744592 | 22978367 | 0 | 0 | 0 | 45761 | 9152 | 36609 | 0 | 0 | Administration, Wisconsin Department of | TRUE
NT10BIX5570028 | CCI | 2011 | Q2 | Q2 - 2011 | 10625045 | 2125009 | 8500036 | 0 | 0 | 0 | 0 | 0 | 0 | 15625518 | 3125104 | 12500414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1937786 | 387557 | 1550229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534610 | 106922 | 427688 | 45761 | 9152 | 36609 | 45761 | 9152 | 36609 | 28722959 | 5744592 | 22978367 | 45761 | 9152 | 36609 | 45761 | 9152 | 36609 | 28722959 | 5744592 | 22978367 | 45761 | 9152 | 36609 | 45761 | 9152 | 36609 | 0 | 0 | Administration, Wisconsin Department of | TRUE
NT10BIX5570029 | CCI | 2010 | Q3 | Q3 - 2010 | 2310149 | 515404 | 1794745 | 0 | 0 | 0 | 0 | 0 | 0 | 12901016 | 2878274 | 10022742 | 0 | 0 | 0 | 0 | 0 | 0 | 367574 | 82007 | 285567 | 0 | 0 | 0 | 0 | 0 | 0 | 917537 | 204707 | 712830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917573 | 204715 | 712858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917610 | 204723 | 712887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20006 | 4463 | 15543 | 0 | 0 | 0 | 0 | 0 | 0 | 18351465 | 4094293 | 14257172 | 0 | 0 | 0 | 0 | 0 | 0 | 18351465 | 4094293 | 14257172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Education Networks of America, Inc. | TRUE
NT10BIX5570029 | CCI | 2010 | Q4 | Q4 - 2010 | 2310149 | 515404 | 1794745 | 0 | 0 | 0 | 0 | 0 | 0 | 12901016 | 2878274 | 10022742 | 0 | 0 | 0 | 0 | 0 | 0 | 367574 | 82007 | 285567 | 0 | 0 | 0 | 0 | 0 | 0 | 917537 | 204707 | 712830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917573 | 204715 | 712858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917610 | 204723 | 712887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20006 | 4463 | 15543 | 0 | 0 | 0 | 0 | 0 | 0 | 18351465 | 4094293 | 14257172 | 0 | 0 | 0 | 0 | 0 | 0 | 18351465 | 4094293 | 14257172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Education Networks of America, Inc. | TRUE
NT10BIX5570029 | CCI | 2011 | Q1 | Q1 - 2011 | 2310149 | 515404 | 1794745 | 0 | 0 | 0 | 0 | 0 | 0 | 12901016 | 2878274 | 10022742 | 0 | 0 | 0 | 0 | 0 | 0 | 367574 | 82007 | 285567 | 0 | 0 | 0 | 0 | 0 | 0 | 917537 | 204707 | 712830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917573 | 204715 | 712858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917610 | 204723 | 712887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20006 | 4463 | 15543 | 0 | 0 | 0 | 0 | 0 | 0 | 18351465 | 4094293 | 14257172 | 0 | 0 | 0 | 0 | 0 | 0 | 18351465 | 4094293 | 14257172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Education Networks of America, Inc. | TRUE
NT10BIX5570030 | CCI | 2010 | Q3 | Q3 - 2010 | 1695000 | 694950 | 1000050 | 0 | 0 | 0 | 225600 | 65600 | 160000 | 10969239 | 766223 | 10203016 | 0 | 0 | 0 | 855882 | 55882 | 800000 | 39000 | 7800 | 31200 | 15015 | 3003 | 12012 | 21000 | 4200 | 16800 | 1435485 | 996922 | 438563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 89500 | 17900 | 71600 | 114500 | 22900 | 91600 | 45000 | 9000 | 36000 | 0 | 0 | 0 | 25000 | 5000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 104515 | 20903 | 83612 | 1241982 | 153582 | 1088400 | 14830204 | 2966040 | 11864164 | 104515 | 20903 | 83612 | 1241982 | 153582 | 1088400 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | CCI | 2010 | Q4 | Q4 - 2010 | 1695000 | 694950 | 1000050 | 0 | 0 | 0 | 300000 | 60000 | 240000 | 10969239 | 766223 | 10203016 | 0 | 0 | 0 | 1040866 | 208173 | 832693 | 39000 | 7800 | 31200 | 20967 | 4194 | 16773 | 30000 | 6000 | 24000 | 1435485 | 996922 | 438563 | 0 | 0 | 0 | 251000 | 50200 | 200800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 92500 | 18500 | 74000 | 195000 | 39000 | 156000 | 45000 | 9000 | 36000 | 0 | 0 | 0 | 5000 | 10001 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 113467 | 22694 | 90773 | 1821866 | 373374 | 1457493 | 14830204 | 2966040 | 11864164 | 113467 | 22694 | 90773 | 1821866 | 373374 | 1457493 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | CCI | 2011 | Q1 | Q1 - 2011 | 1695000 | 694950 | 1000050 | 0 | 0 | 0 | 40000 | 16400 | 23600 | 10969239 | 766223 | 10203016 | 595022 | 110871 | 484151 | 2840015 | 268021 | 2571994 | 39000 | 7800 | 31200 | 29001 | 5801 | 22786 | 35000 | 7000 | 28000 | 1435485 | 996922 | 438563 | 142808 | 10151 | 132656 | 688143 | 459806 | 228336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 151022 | 56254 | 94768 | 272422 | 141971 | 130451 | 45000 | 9000 | 36000 | 0 | 0 | 0 | 22500 | 4500 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 917853 | 183077 | 734361 | 3898080 | 897698 | 3000381 | 14830204 | 2966040 | 11864164 | 917853 | 183077 | 734361 | 3898080 | 897698 | 3000381 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | CCI | 2011 | Q2 | Q2 - 2011 | 1695000 | 694950 | 1000050 | 260167 | 106668 | 153499 | 340167 | 139468 | 200698 | 10969239 | 766223 | 10203016 | 2977699 | 189185 | 2788514 | 6040239 | 403563 | 5636676 | 39000 | 7800 | 31200 | 32907 | 6582 | 26325 | 39917 | 7984 | 31933 | 1435485 | 996922 | 438563 | 830119 | 523504 | 306615 | 1158544 | 802778 | 355766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 178470 | 73830 | 104640 | 293470 | 179390 | 114080 | 45000 | 9000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 4279362 | 899769 | 3379593 | 7872337 | 1533183 | 6339153 | 14830204 | 2966040 | 11864164 | 4279362 | 899769 | 3379593 | 7872337 | 1533183 | 6339153 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | CCI | 2011 | Q3 | Q3 - 2011 | 1695000 | 694950 | 1000050 | 280698 | 115086 | 165612 | 1040718 | 426706 | 614012 | 10969239 | 766223 | 10203016 | 5406021 | 359168 | 5046854 | 7373161 | 496868 | 6876293 | 39000 | 7800 | 31200 | 39761 | 7953 | 31808 | 47440 | 9497 | 37943 | 1435485 | 996922 | 438563 | 951299 | 533198 | 418101 | 1572877 | 953296 | 619581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 310928 | 206288 | 104640 | 377832 | 273192 | 104640 | 45000 | 9000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 6988707 | 1221693 | 5767015 | 10412028 | 2159559 | 8252469 | 14830204 | 2966040 | 11864164 | 6988707 | 1221693 | 5767015 | 10412028 | 2159559 | 8252469 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | CCI | 2011 | Q4 | Q4 - 2011 | 1695000 | 694950 | 1000050 | 351306 | 144035 | 207271 | 1186306 | 486385 | 699921 | 10969239 | 766223 | 10203016 | 6731633 | 451961 | 6279672 | 8908306 | 604328 | 8303978 | 39000 | 7800 | 31200 | 47485 | 9498 | 37987 | 53905 | 10782 | 43123 | 1435485 | 996922 | 438563 | 1565294 | 980364 | 584930 | 1785294 | 1181964 | 603330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 435556 | 276429 | 159127 | 532460 | 345013 | 187447 | 45000 | 9000 | 36000 | 244 | 49 | 195 | 10619 | 2124 | 8496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 9131518 | 1862336 | 7269182 | 12476890 | 2630596 | 9846295 | 14830204 | 2966040 | 11864164 | 9131518 | 1862336 | 7269182 | 12476890 | 2630596 | 9846295 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | CCI | 2012 | Q1 | Q1 - 2012 | 1695000 | 694950 | 1000050 | 407655 | 167138 | 240517 | 813655 | 333598 | 480057 | 10969239 | 766223 | 10203016 | 7836571 | 629307 | 7207264 | 9284921 | 730691 | 8554230 | 39000 | 7800 | 31200 | 53881 | 10777 | 43104 | 60321 | 12065 | 48256 | 1435485 | 996922 | 438563 | 1565294 | 980364 | 584930 | 1585294 | 981964 | 603330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 502463 | 343336 | 159127 | 569367 | 410240 | 159127 | 45000 | 9000 | 36000 | 11219 | 2244 | 8975 | 11594 | 2319 | 9275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 10377083 | 2133166 | 8243917 | 12325152 | 2470877 | 9854275 | 14830204 | 2966040 | 11864164 | 10377083 | 2133166 | 8243917 | 12325152 | 2470877 | 9854275 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | CCI | 2012 | Q2 | Q2 - 2012 | 1695000 | 694950 | 1000050 | 453748 | 186036 | 267712 | 1185952 | 486240 | 699712 | 10969239 | 766223 | 10203016 | 8520629 | 677191 | 7843438 | 9847307 | 770058 | 9077249 | 39000 | 7800 | 31200 | 61929 | 12387 | 49542 | 69369 | 13875 | 55494 | 1435485 | 996922 | 438563 | 1565915 | 980413 | 585502 | 1585915 | 982013 | 603902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 584881 | 403530 | 181351 | 614881 | 405210 | 209671 | 45000 | 9000 | 36000 | 11219 | 2244 | 8975 | 31769 | 6354 | 25415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 11198321 | 2261801 | 8936520 | 13335193 | 2663750 | 10671443 | 14830204 | 2966040 | 11864164 | 11198321 | 2261801 | 8936520 | 13335193 | 2663750 | 10671443 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | CCI | 2012 | Q3 | Q3 - 2012 | 1695000 | 694950 | 1000050 | 1091827 | 447277 | 644550 | 1194327 | 489302 | 705025 | 10969239 | 766223 | 10203016 | 9158352 | 818449 | 8339903 | 10475352 | 818449 | 9656903 | 39000 | 7800 | 31200 | 69675 | 13868 | 55807 | 78097 | 15212 | 62885 | 1435485 | 996922 | 438563 | 1648699 | 1063197 | 585502 | 1849170 | 1228984 | 620186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 339102 | 129874 | 209228 | 490102 | 237450 | 252652 | 45000 | 9000 | 36000 | 32839 | 6568 | 26271 | 53839 | 10768 | 43071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 12340494 | 2479233 | 9861261 | 14140887 | 2800165 | 11340722 | 14830204 | 2966040 | 11864164 | 12340494 | 2479233 | 9861261 | 14140887 | 2800165 | 11340722 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | CCI | 2012 | Q4 | Q4 - 2012 | 1695000 | 694950 | 1000050 | 1098480 | 447277 | 651203 | 1192049 | 447277 | 744772 | 10969239 | 766223 | 10203016 | 10253648 | 951231 | 9302417 | 10253648 | 951231 | 9302417 | 39000 | 7800 | 31200 | 77739 | 13868 | 63871 | 90571 | 13868 | 76703 | 1435485 | 996922 | 438563 | 1755857 | 1150355 | 605502 | 1796875 | 1189373 | 607502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646480 | 491145 | 155335 | 378205 | 168977 | 209228 | 428095 | 218867 | 209228 | 45000 | 9000 | 36000 | 41139 | 7168 | 33971 | 54484 | 15713 | 38771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 13605068 | 2738876 | 10866192 | 13815722 | 2836329 | 10979393 | 14830204 | 2966040 | 11864164 | 13605068 | 2738876 | 10866192 | 13815722 | 2836329 | 10979393 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | CCI | 2013 | Q1 | Q1 - 2013 | 1361740 | 460277 | 901463 | 1187992 | 447277 | 740715 | 1187992 | 447277 | 740715 | 10573648 | 961231 | 9612417 | 10156133 | 951231 | 9204902 | 10156133 | 951231 | 9204902 | 215713 | 38019 | 177694 | 91844 | 13868 | 77976 | 109844 | 13868 | 95976 | 1894495 | 1184904 | 709591 | 1740542 | 1134381 | 606161 | 1740542 | 1134381 | 606161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595124 | 285896 | 309228 | 447323 | 209071 | 238252 | 502323 | 254071 | 248252 | 189484 | 35713 | 153771 | 56614 | 17843 | 38771 | 56614 | 17843 | 38771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 13680448 | 2773671 | 10906777 | 13753448 | 2818671 | 10934777 | 14830204 | 2966040 | 11864164 | 13680448 | 2773671 | 10906777 | 13753448 | 2818671 | 10934777 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | CCI | 2013 | Q2 | Q2 - 2013 | 1361740 | 460277 | 901463 | 1187992 | 447277 | 740715 | 1360816 | 459353 | 901463 | 10573648 | 961231 | 9612417 | 10186598 | 951231 | 9235367 | 10573648 | 961231 | 9612417 | 215713 | 38019 | 177694 | 119848 | 13868 | 105980 | 215713 | 38019 | 177694 | 1894495 | 1184904 | 709591 | 1791989 | 1185828 | 606161 | 1895419 | 1185828 | 709591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595124 | 285896 | 309228 | 479733 | 241481 | 238252 | 595124 | 285896 | 309228 | 189484 | 35713 | 153771 | 57074 | 17843 | 39231 | 189484 | 35713 | 153771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 13823234 | 2857528 | 10965706 | 14830204 | 2966040 | 11864164 | 14830204 | 2966040 | 11864164 | 13823234 | 2857528 | 10965706 | 14830204 | 2966040 | 11864164 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570030 | CCI | 2013 | Q3 | Q3 - 2013 | 1865962 | 505789 | 1360173 | 1645554 | 447277 | 1198277 | 1645554 | 447277 | 1198277 | 10386598 | 951231 | 9435367 | 10265436 | 951231 | 9314205 | 10265436 | 951231 | 9314205 | 155848 | 13868 | 141980 | 158742 | 13868 | 144874 | 158742 | 13868 | 144874 | 1791989 | 1185828 | 606161 | 1791989 | 1185828 | 606161 | 1791989 | 1185828 | 606161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 567733 | 291481 | 276252 | 515504 | 289080 | 226424 | 515504 | 289080 | 226424 | 62074 | 17843 | 44231 | 57074 | 17843 | 39231 | 57074 | 17843 | 39231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14830204 | 2966040 | 11864164 | 14434299 | 2905127 | 11529172 | 14434299 | 2905127 | 11529172 | 14830204 | 2966040 | 11864164 | 14434299 | 2905127 | 11529172 | 14434299 | 2905127 | 11529172 | 0 | 0 | De Kalb, County of (Inc.) | TRUE
NT10BIX5570031 | CCI | 2010 | Q3 | Q3 - 2010 | 56278640 | 2690000 | 53588640 | 0 | 0 | 0 | 27500000 | 2690000 | 24810000 | 70904657 | 21810000 | 49094657 | 0 | 0 | 0 | 12500000 | 5000000 | 7500000 | 0 | 0 | 0 | 0 | 0 | 0 | 51500 | 0 | 51500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28639999 | 5000000 | 23639999 | 99058 | 0 | 99058 | 4710240 | 2610240 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159823296 | 33500000 | 126323296 | 99058 | 0 | 99058 | 44761740 | 10300240 | 34461500 | 159823296 | 33500000 | 126323296 | 99058 | 0 | 99058 | 44761740 | 10300240 | 34461500 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | CCI | 2010 | Q4 | Q4 - 2010 | 56278640 | 2690000 | 53588640 | 27421187 | 3371582 | 24049605 | 36190000 | 2690000 | 33500000 | 70904657 | 21810000 | 49094657 | 0 | 0 | 0 | 16200000 | 5000000 | 11200000 | 0 | 0 | 0 | 21047 | 0 | 21047 | 75500 | 0 | 75500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28639999 | 5000000 | 23639999 | 1331778 | 420489 | 911289 | 5110240 | 2610240 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159823296 | 33500000 | 126323296 | 28774012 | 3792071 | 24981941 | 57575740 | 10300240 | 47275500 | 159823296 | 33500000 | 126323296 | 28774012 | 3792071 | 24981941 | 57575740 | 10300240 | 47275500 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | CCI | 2011 | Q1 | Q1 - 2011 | 56278640 | 2690000 | 53588640 | 28087957 | 3371583 | 24716375 | 27832457 | 2432457 | 25400000 | 70904657 | 21810000 | 49094657 | 0 | 0 | 0 | 33386055 | 27386055 | 6000000 | 0 | 0 | 0 | 46138 | 0 | 46138 | 200000 | 105000 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28639999 | 5000000 | 23639999 | 1745444 | 0 | 1745444 | 2600000 | 0 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 0 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 420488 | 420488 | 0 | 495488 | 420488 | 75000 | 159823296 | 33500000 | 126323296 | 30300027 | 3792071 | 26507957 | 65514000 | 30344000 | 35170000 | 159823296 | 33500000 | 126323296 | 30300027 | 3792071 | 26507957 | 65514000 | 30344000 | 35170000 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | CCI | 2011 | Q2 | Q2 - 2011 | 53236719 | 2432457 | 50804262 | 29400388 | 2432457 | 26967931 | 51682457 | 2432457 | 49250000 | 82322630 | 30542055 | 51780575 | 26712640 | 25886055 | 826585 | 36242055 | 30542055 | 5700000 | 3980000 | 105000 | 3875000 | 81776 | 0 | 81776 | 775000 | 25000 | 750000 | 463200 | 0 | 463200 | 260280 | 0 | 260280 | 300000 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11170236 | 0 | 11170236 | 1557660 | 0 | 1557660 | 3950000 | 0 | 3950000 | 7407800 | 0 | 7407800 | 555725 | 0 | 555725 | 2200000 | 0 | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 412367 | 0 | 412367 | 525000 | 0 | 525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 420488 | 197223 | 429470 | 420488 | 8982 | 455488 | 420488 | 35000 | 159823296 | 33500000 | 126323296 | 59410306 | 28739000 | 30671306 | 96130000 | 33420000 | 62710000 | 159823296 | 33500000 | 126323296 | 59410306 | 28739000 | 30671306 | 96130000 | 33420000 | 62710000 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | CCI | 2011 | Q3 | Q3 - 2011 | 53236719 | 2432457 | 50804262 | 29006260 | 1624457 | 27381803 | 40056260 | 1624457 | 38431803 | 82322630 | 30542055 | 51780575 | 28769673 | 25886055 | 2883618 | 32812492 | 25886055 | 6926437 | 3980000 | 105000 | 3875000 | 102008 | 0 | 102008 | 374550 | 25000 | 349550 | 463200 | 0 | 463200 | 327300 | 0 | 327300 | 463200 | 0 | 463200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11170236 | 0 | 11170236 | 2325416 | 0 | 2325416 | 4632000 | 0 | 4632000 | 7407800 | 0 | 7407800 | 910961 | 0 | 910961 | 1250000 | 0 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 420488 | 197223 | 452812 | 420488 | 32324 | 453952 | 420488 | 33464 | 159823296 | 33500000 | 126323296 | 61894430 | 27931000 | 33963430 | 80042454 | 27956000 | 52086454 | 159823296 | 33500000 | 126323296 | 61894430 | 27931000 | 33963430 | 80042454 | 27956000 | 52086454 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | CCI | 2011 | Q4 | Q4 - 2011 | 53236719 | 2432457 | 50804262 | 34050562 | 2432457 | 31618105 | 44154657 | 2432457 | 41722200 | 82322630 | 30542055 | 51780575 | 33807730 | 29788191 | 4019539 | 39207730 | 29788191 | 9419539 | 3980000 | 105000 | 3875000 | 224031 | 77951 | 146080 | 294031 | 77951 | 216080 | 463200 | 0 | 463200 | 327300 | 0 | 327300 | 377300 | 0 | 377300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11170236 | 0 | 11170236 | 5327590 | 0 | 5327590 | 6327590 | 0 | 6327590 | 7407800 | 0 | 7407800 | 1246748 | 0 | 1246748 | 2096740 | 0 | 2096740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 24573 | 0 | 24573 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 420488 | 197223 | 477303 | 420488 | 56815 | 482988 | 420488 | 62500 | 159823296 | 33500000 | 126323296 | 75485837 | 32719087 | 42766750 | 92971036 | 32719087 | 60251949 | 159823296 | 33500000 | 126323296 | 75485837 | 32719087 | 42766750 | 92971036 | 32719087 | 60251949 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | CCI | 2012 | Q1 | Q1 - 2012 | 56736719 | 2432457 | 54304262 | 41770133 | 2432457 | 39337676 | 54707457 | 2432457 | 52275000 | 78722630 | 30542055 | 48180575 | 34484641 | 29788191 | 4696450 | 42013191 | 29788191 | 12225000 | 3980000 | 105000 | 3875000 | 281125 | 77951 | 203174 | 398176 | 77951 | 320225 | 463200 | 0 | 463200 | 335763 | 0 | 335763 | 385763 | 0 | 385763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11270236 | 0 | 11270236 | 8023334 | 0 | 8023334 | 9110000 | 0 | 9110000 | 7407800 | 0 | 7407800 | 1636920 | 0 | 1636920 | 2733000 | 0 | 2733000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 30853 | 0 | 30853 | 225300 | 0 | 225300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 420488 | 197223 | 487632 | 420488 | 67144 | 687632 | 420488 | 267144 | 159823296 | 33500000 | 126323296 | 87050401 | 32719087 | 54331314 | 110260519 | 32719087 | 77541432 | 159823296 | 33500000 | 126323296 | 87050401 | 32719087 | 54331314 | 110260519 | 32719087 | 77541432 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | CCI | 2012 | Q2 | Q2 - 2012 | 56736719 | 2432457 | 54304262 | 42109385 | 2432457 | 39676928 | 49337676 | 2432457 | 46905219 | 78722630 | 30542055 | 48180575 | 35420578 | 29788191 | 5632387 | 51113560 | 29788191 | 21325369 | 3980000 | 105000 | 3875000 | 605717 | 77951 | 527766 | 867585 | 77951 | 789634 | 463200 | 0 | 463200 | 335763 | 0 | 335763 | 429763 | 0 | 429763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11270236 | 0 | 11270236 | 9215170 | 0 | 9215170 | 9560170 | 0 | 9560170 | 7407800 | 0 | 7407800 | 1843602 | 0 | 1843602 | 1843602 | 0 | 1843602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 325272 | 0 | 325272 | 325272 | 0 | 325272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 420488 | 197223 | 494364 | 420488 | 73876 | 496362 | 420488 | 75874 | 159823296 | 33500000 | 126323296 | 90349851 | 32719087 | 57630764 | 113973990 | 32719087 | 81254903 | 159823296 | 33500000 | 126323296 | 90349851 | 32719087 | 57630764 | 113973990 | 32719087 | 81254903 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | CCI | 2012 | Q3 | Q3 - 2012 | 56736719 | 2432457 | 54304262 | 47585623 | 2432457 | 45153166 | 51557457 | 2432457 | 49125000 | 78722630 | 30542055 | 48180575 | 41209142 | 29788191 | 11420951 | 53203000 | 30703000 | 22500000 | 3980000 | 105000 | 3875000 | 733097 | 77951 | 655146 | 1030000 | 105000 | 925000 | 463200 | 0 | 463200 | 335763 | 0 | 335763 | 375000 | 0 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11270236 | 0 | 11270236 | 10192877 | 0 | 10192877 | 10500000 | 0 | 10500000 | 7407800 | 0 | 7407800 | 2130001 | 0 | 2130001 | 2525000 | 0 | 2525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 447662 | 0 | 447662 | 475000 | 0 | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 420488 | 197223 | 495924 | 420488 | 75436 | 348043 | 259543 | 88500 | 159823296 | 33500000 | 126323296 | 103130089 | 32719087 | 70411002 | 120013500 | 33500000 | 86513500 | 159823296 | 33500000 | 126323296 | 103130089 | 32719087 | 70411002 | 120013500 | 33500000 | 86513500 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | CCI | 2012 | Q4 | Q4 - 2012 | 56736719 | 6203000 | 50533719 | 55783639 | 6203000 | 49580639 | 56169176 | 6203000 | 49966176 | 78722630 | 27192000 | 51530630 | 42608993 | 27192000 | 15416993 | 52692355 | 27192000 | 25500355 | 3980000 | 105000 | 3875000 | 987810 | 105000 | 882810 | 1455000 | 105000 | 1350000 | 463200 | 0 | 463200 | 409965 | 0 | 409965 | 463200 | 0 | 463200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11270236 | 0 | 11270236 | 10896509 | 0 | 10896509 | 12500000 | 0 | 12500000 | 7407800 | 0 | 7407800 | 2130001 | 0 | 2130001 | 3130000 | 0 | 3130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 447662 | 0 | 447662 | 525000 | 0 | 525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 0 | 617711 | 90726 | 0 | 90726 | 575000 | 0 | 575000 | 159823296 | 33500000 | 126323296 | 113355305 | 33500000 | 79855305 | 127509731 | 33500000 | 94009731 | 159823296 | 33500000 | 126323296 | 113355305 | 33500000 | 79855305 | 127509731 | 33500000 | 94009731 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | CCI | 2013 | Q1 | Q1 - 2013 | 56736719 | 6203000 | 50533719 | 55796705 | 6203000 | 49593705 | 56296705 | 6203000 | 50093705 | 78722630 | 27192000 | 51530630 | 43413472 | 27192000 | 16221472 | 56163472 | 27192000 | 28971472 | 3980000 | 105000 | 3875000 | 1506569 | 105000 | 1401569 | 2030000 | 105000 | 1925000 | 463200 | 0 | 463200 | 409965 | 0 | 409965 | 434500 | 0 | 434500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11270236 | 0 | 11270236 | 12112739 | 0 | 12112739 | 12225800 | 0 | 12225800 | 7407800 | 0 | 7407800 | 2130001 | 0 | 2130001 | 4150000 | 0 | 4150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 625000 | 447662 | 0 | 447662 | 625000 | 0 | 625000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 0 | 617711 | 121319 | 0 | 121319 | 225000 | 0 | 225000 | 159823296 | 33500000 | 126323296 | 115938432 | 33500000 | 82438432 | 132150477 | 33500000 | 98650477 | 159823296 | 33500000 | 126323296 | 115938432 | 33500000 | 82438432 | 132150477 | 33500000 | 98650477 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | CCI | 2013 | Q2 | Q2 - 2013 | 56736719 | 6203000 | 50533719 | 55796705 | 6203000 | 49593705 | 56736719 | 6203000 | 50533719 | 78722630 | 27192000 | 51530630 | 47640821 | 27192000 | 20448821 | 69640821 | 27192000 | 42448821 | 3830000 | 105000 | 3725000 | 2064630 | 105000 | 1959630 | 3364630 | 105000 | 3259630 | 538200 | 0 | 538200 | 409965 | 0 | 409965 | 538200 | 0 | 538200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13270236 | 0 | 13270236 | 12112739 | 0 | 12112739 | 13270236 | 0 | 13270236 | 5407800 | 0 | 5407800 | 2130001 | 0 | 2130001 | 3405000 | 0 | 3405000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 700000 | 677237 | 0 | 677237 | 700000 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 0 | 617711 | 130000 | 0 | 130000 | 205000 | 0 | 205000 | 159823296 | 33500000 | 126323296 | 120962098 | 33500000 | 87462098 | 147860606 | 33500000 | 114360606 | 159823296 | 33500000 | 126323296 | 120962098 | 33500000 | 87462098 | 147860606 | 33500000 | 114360606 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | CCI | 2013 | Q3 | Q3 - 2013 | 56736719 | 6203000 | 50533719 | 55796822 | 6203000 | 49593705 | 56736719 | 6203000 | 50533719 | 78722630 | 27192000 | 51530630 | 49811115 | 27192000 | 22619115 | 67392800 | 27192000 | 40200800 | 3830000 | 105000 | 3725000 | 2687046 | 105000 | 2536056 | 3100000 | 105000 | 2995000 | 538200 | 0 | 538200 | 409965 | 0 | 409965 | 425000 | 0 | 425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13270236 | 0 | 13270236 | 12404958 | 0 | 12404958 | 13150100 | 0 | 13150100 | 5407800 | 0 | 5407800 | 2130001 | 0 | 2130001 | 5125000 | 0 | 5125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 700000 | 677237 | 0 | 677237 | 700000 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617711 | 0 | 617711 | 146416 | 0 | 144426 | 200000 | 0 | 200000 | 159823296 | 33500000 | 126323296 | 124063560 | 33500000 | 90515463 | 146829619 | 33500000 | 113329619 | 159823296 | 33500000 | 126323296 | 124063560 | 33500000 | 90515463 | 146829619 | 33500000 | 113329619 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570031 | CCI | 2013 | Q4 | Q4 - 2013 | 55572909 | 2646342 | 52926567 | 55572909 | 2646342 | 52926567 | 55572909 | 2646342 | 52926567 | 84320609 | 30748658 | 53571951 | 82372311 | 30748658 | 51623653 | 82372311 | 30748658 | 51623653 | 3160851 | 105000 | 3055851 | 3160851 | 105000 | 3055851 | 3160851 | 105000 | 3055851 | 554403 | 0 | 554403 | 554403 | 0 | 554403 | 554403 | 0 | 554403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13530373 | 0 | 13530373 | 13530373 | 0 | 13530373 | 13530373 | 0 | 13530373 | 489954 | 0 | 489954 | 489954 | 0 | 489954 | 489954 | 0 | 489954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2103280 | 0 | 2103280 | 2103280 | 0 | 2103280 | 2103280 | 0 | 2103280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90917 | 0 | 90917 | 90917 | 0 | 90917 | 90917 | 0 | 90917 | 159823296 | 33500000 | 126323296 | 157874998 | 33500000 | 124374998 | 157874998 | 33500000 | 124374998 | 159823296 | 33500000 | 126323296 | 157874998 | 33500000 | 124374998 | 157874998 | 33500000 | 124374998 | 0 | 0 | Executive Office State of West Virginia | TRUE
NT10BIX5570032 | CCI | 2010 | Q3 | Q3 - 2010 | 1538655 | 0 | 1538675 | 0 | 0 | 0 | 0 | 0 | 0 | 8390480 | 2030505 | 6359975 | 0 | 0 | 0 | 50000 | 0 | 50000 | 39000 | 39000 | 0 | 37469 | 37469 | 0 | 38270 | 38270 | 0 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 184480 | 0 | 184480 | 300000 | 10000 | 290000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 4627 | 884 | 3743 | 5400 | 884 | 4500 | 10439035 | 2113505 | 8325550 | 226576 | 38353 | 188223 | 413670 | 49154 | 364500 | 10439035 | 2113505 | 8325550 | 226576 | 38353 | 188223 | 413670 | 49154 | 364500 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570032 | CCI | 2010 | Q4 | Q4 - 2010 | 1538655 | 0 | 1538678 | 0 | 0 | 0 | 100000 | 0 | 100000 | 8390480 | 2030505 | 6359975 | 0 | 0 | 0 | 50000 | 0 | 50000 | 39000 | 39000 | 0 | 38467 | 41115 | 0 | 38467 | 38467 | 0 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 289722 | 0 | 289005 | 320000 | 20000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40070 | 4627 | 884 | 3743 | 5400 | 884 | 4516 | 10439035 | 2113505 | 8325153 | 332816 | 41999 | 292748 | 531867 | 77351 | 454516 | 10439035 | 2113505 | 8325153 | 332816 | 41999 | 292748 | 531867 | 77351 | 454516 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570032 | CCI | 2011 | Q1 | Q1 - 2011 | 1538655 | 0 | 1538678 | 0 | 0 | 0 | 0 | 0 | 0 | 8390480 | 2030505 | 6359975 | 0 | 0 | 0 | 100000 | 0 | 100000 | 39000 | 39000 | 0 | 38467 | 38467 | 0 | 38467 | 38467 | 0 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 398170 | 14000 | 384170 | 469170 | 67000 | 402170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 4627 | 884 | 3743 | 4627 | 884 | 3743 | 10439035 | 2113505 | 8325553 | 441264 | 53351 | 387913 | 630264 | 124351 | 505913 | 10439035 | 2113505 | 8325553 | 441264 | 53351 | 387913 | 630264 | 124351 | 505913 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570032 | CCI | 2011 | Q2 | Q2 - 2011 | 1538655 | 0 | 1538655 | 0 | 0 | 0 | 250000 | 0 | 250000 | 8390480 | 2030505 | 6359975 | 1763664 | 1644581 | 0 | 2313664 | 1763664 | 550000 | 39000 | 39000 | 0 | 38467 | 38467 | 0 | 38467 | 38467 | 0 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 522533 | 79732 | 439058 | 522533 | 79732 | 442801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 4627 | 884 | 3743 | 6650 | 0 | 6650 | 10439035 | 2113505 | 8325530 | 2329291 | 1763664 | 442801 | 3149314 | 1899863 | 1249451 | 10439035 | 2113505 | 8325530 | 2329291 | 1763664 | 442801 | 3149314 | 1899863 | 1249451 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570032 | CCI | 2011 | Q3 | Q3 - 2011 | 1538655 | 0 | 1538655 | 0 | 0 | 0 | 250000 | 0 | 250000 | 8390480 | 2030505 | 6359975 | 2033502 | 1675661 | 357841 | 2488139 | 1876502 | 611637 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 39311 | 39311 | 0 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 402533 | 48475 | 354058 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 4627 | 884 | 3743 | 6650 | 0 | 6650 | 10439035 | 2113505 | 8325530 | 2479973 | 1764331 | 715642 | 3225005 | 1982288 | 1242717 | 10439035 | 2113505 | 8325530 | 2479973 | 1764331 | 715642 | 3225005 | 1982288 | 1242717 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570032 | CCI | 2011 | Q4 | Q4 - 2011 | 1538655 | 0 | 1538655 | 0 | 0 | 0 | 1072044 | 0 | 1072044 | 8390480 | 2030505 | 6359975 | 3195525 | 1885310 | 1221545 | 4067310 | 1867310 | 2200000 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 39311 | 39311 | 0 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 18500 | 18000 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 471380 | 48475 | 422905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 5461 | 884 | 4577 | 5780 | 884 | 4897 | 10439035 | 2113505 | 8325530 | 3663202 | 1973980 | 1600552 | 5674325 | 1973980 | 3700346 | 10439035 | 2113505 | 8325530 | 3663202 | 1973980 | 1600552 | 5674325 | 1973980 | 3700346 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570032 | CCI | 2012 | Q1 | Q1 - 2012 | 1538655 | 0 | 1538655 | 943642 | 0 | 943642 | 950000 | 0 | 950000 | 8390480 | 2030505 | 6359975 | 4693139 | 1890734 | 2802405 | 5878760 | 1890734 | 3988026 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 39311 | 39311 | 0 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 5461 | 884 | 4577 | 10268 | 884 | 9384 | 10439035 | 2113505 | 8325530 | 6104458 | 1979404 | 4125054 | 7319244 | 1997404 | 5321840 | 10439035 | 2113505 | 8325530 | 6104458 | 1979404 | 4125054 | 7319244 | 1997404 | 5321840 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570032 | CCI | 2012 | Q2 | Q2 - 2012 | 1538655 | 0 | 1538655 | 943642 | 0 | 943642 | 960000 | 0 | 960000 | 8390480 | 2030505 | 6359975 | 5625426 | 1894731 | 3730695 | 6200000 | 1930000 | 4270000 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 39311 | 39311 | 0 | 30000 | 18000 | 12000 | 18000 | 18000 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 7108 | 884 | 6224 | 7538 | 884 | 6654 | 10439035 | 2113505 | 8325530 | 7056392 | 2001401 | 5054991 | 7647754 | 2036670 | 5611084 | 10439035 | 2113505 | 8325530 | 7056392 | 2001401 | 5054991 | 7647754 | 2036670 | 5611084 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570032 | CCI | 2012 | Q3 | Q3 - 2012 | 1538655 | 0 | 1538655 | 1146001 | 0 | 1146001 | 1538655 | 0 | 1538655 | 8390480 | 2030505 | 6359975 | 5799941 | 1894731 | 3905210 | 6940000 | 2030505 | 4909495 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 39311 | 39311 | 0 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 7108 | 884 | 6224 | 7538 | 884 | 6654 | 10439035 | 2113505 | 8325530 | 7445266 | 2001401 | 5443865 | 8978409 | 2137175 | 6841234 | 10439035 | 2113505 | 8325530 | 7445266 | 2001401 | 5443865 | 8978409 | 2137175 | 6841234 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570032 | CCI | 2012 | Q4 | Q4 - 2012 | 1538655 | 0 | 1538655 | 1146001 | 0 | 1146001 | 1396500 | 0 | 1396500 | 8390480 | 2030505 | 6359975 | 6775416 | 1957412 | 4849435 | 7525416 | 2030505 | 5494911 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 39311 | 39311 | 0 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 7108 | 884 | 6224 | 7500 | 884 | 6616 | 10439035 | 2113505 | 8325530 | 8420741 | 2064082 | 6388090 | 9421632 | 2137175 | 7284457 | 10439035 | 2113505 | 8325530 | 8420741 | 2064082 | 6388090 | 9421632 | 2137175 | 7284457 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570032 | CCI | 2013 | Q1 | Q1 - 2013 | 1538655 | 0 | 1538655 | 1146001 | 0 | 1146001 | 1538655 | 0 | 1538655 | 8390480 | 2030505 | 6359975 | 7375037 | 2030505 | 5463056 | 8196480 | 2036505 | 6159975 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 39311 | 39311 | 0 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 36000 | 24000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 7108 | 884 | 6224 | 7500 | 884 | 6616 | 10439035 | 2113505 | 8325530 | 9020362 | 2137175 | 7001711 | 10240851 | 2149175 | 8091676 | 10439035 | 2113505 | 8325530 | 9020362 | 2137175 | 7001711 | 10240851 | 2149175 | 8091676 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570032 | CCI | 2013 | Q2 | Q2 - 2013 | 1538655 | 0 | 1538655 | 1146001 | 0 | 1146001 | 1538655 | 0 | 1538655 | 8390480 | 2030505 | 6359975 | 8092165 | 1962935 | 6129230 | 8347056 | 2006835 | 6340221 | 39000 | 39000 | 0 | 39311 | 39311 | 0 | 93311 | 39311 | 54000 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 7108 | 884 | 6224 | 7108 | 884 | 6224 | 10439035 | 2113505 | 8325530 | 9737490 | 2069605 | 7667885 | 10439035 | 2113505 | 8325530 | 10439035 | 2113505 | 8325530 | 9737490 | 2069605 | 7667885 | 10439035 | 2113505 | 8325530 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570032 | CCI | 2013 | Q3 | Q3 - 2013 | 1538660 | 0 | 1538660 | 1538660 | 0 | 1538660 | 1538660 | 0 | 1538660 | 8390475 | 2030505 | 6359970 | 8326079 | 2006835 | 6319244 | 8326079 | 2006835 | 6319244 | 39000 | 39000 | 0 | 110000 | 39311 | 70689 | 110000 | 39311 | 70689 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 30000 | 18000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400430 | 26000 | 374430 | 422905 | 48475 | 374430 | 422905 | 48475 | 374430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40470 | 0 | 40470 | 8438 | 884 | 7554 | 8438 | 884 | 7554 | 10439035 | 2113505 | 8325530 | 10436082 | 2113505 | 8322577 | 10436082 | 2113505 | 8322577 | 10439035 | 2113505 | 8325530 | 10436082 | 2113505 | 8322577 | 10436082 | 2113505 | 8322577 | 0 | 0 | Lane Council of Government | TRUE
NT10BIX5570033 | CCI | 2010 | Q3 | Q3 - 2010 | 7489453 | 0 | 7489453 | 0 | 0 | 0 | 0 | 0 | 0 | 2038396 | 0 | 2038396 | 0 | 0 | 0 | 0 | 0 | 0 | 1202000 | 0 | 1202000 | 411383 | 0 | 411383 | 903000 | 8000 | 895000 | 4805650 | 3412500 | 1393150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 178000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630175 | 0 | 630175 | 0 | 0 | 0 | 0 | 0 | 0 | 16343674 | 3412500 | 12931174 | 411383 | 0 | 411383 | 903000 | 8000 | 895000 | 16343674 | 3412500 | 12931174 | 411383 | 0 | 411383 | 903000 | 8000 | 895000 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | CCI | 2010 | Q4 | Q4 - 2010 | 7489453 | 0 | 7489453 | 44000 | 0 | 44000 | 64000 | 0 | 64000 | 2038396 | 0 | 2038396 | 0 | 0 | 0 | 0 | 0 | 0 | 1202000 | 0 | 1202000 | 490455 | 0 | 490455 | 560285 | 0 | 560285 | 4805650 | 3412500 | 1393150 | 4000 | 4000 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 178000 | 0 | 0 | 0 | 35000 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630175 | 0 | 630175 | 0 | 0 | 0 | 0 | 0 | 0 | 16343674 | 3412500 | 12931174 | 538455 | 4000 | 534455 | 689285 | 30000 | 659285 | 16343674 | 3412500 | 12931174 | 538455 | 4000 | 534455 | 689285 | 30000 | 659285 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | CCI | 2011 | Q1 | Q1 - 2011 | 7489453 | 0 | 7489453 | 44000 | 0 | 44000 | 156000 | 0 | 156000 | 2038396 | 0 | 2038396 | 0 | 0 | 0 | 6300 | 0 | 6300 | 1202000 | 0 | 1202000 | 574744 | 0 | 574744 | 668574 | 0 | 668574 | 4805650 | 3412500 | 1393150 | 8750 | 6250 | 2500 | 280750 | 156250 | 124500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 178000 | 65125 | 0 | 65125 | 97125 | 0 | 97125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630175 | 0 | 630175 | 0 | 0 | 0 | 0 | 0 | 0 | 16343674 | 3412500 | 12931174 | 692619 | 6250 | 686369 | 1208749 | 156250 | 1052499 | 16343674 | 3412500 | 12931174 | 692619 | 6250 | 686369 | 1208749 | 156250 | 1052499 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | CCI | 2011 | Q2 | Q2 - 2011 | 7489453 | 0 | 7489453 | 178804 | 0 | 178804 | 1569454 | 0 | 1569454 | 2038396 | 0 | 2038396 | 13665 | 0 | 13665 | 68665 | 0 | 68665 | 1202000 | 0 | 1202000 | 702630 | 0 | 702630 | 848630 | 0 | 848630 | 4805650 | 3412500 | 1393150 | 208044 | 158750 | 49294 | 1113048 | 858750 | 254294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 178000 | 107250 | 0 | 107250 | 147250 | 0 | 147250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630175 | 0 | 630175 | 0 | 0 | 0 | 90000 | 0 | 90000 | 16343674 | 3412500 | 12931174 | 1210393 | 158750 | 1051643 | 3837047 | 858750 | 2978293 | 16343674 | 3412500 | 12931174 | 1210393 | 158750 | 1051643 | 3837047 | 858750 | 2978293 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | CCI | 2011 | Q3 | Q3 - 2011 | 7429453 | 0 | 7429453 | 355076 | 0 | 355076 | 3551076 | 0 | 3551076 | 2038396 | 0 | 2038396 | 16534 | 0 | 16534 | 289534 | 0 | 289534 | 1662000 | 400000 | 1262000 | 882616 | 46562 | 836054 | 1065616 | 109562 | 956054 | 4405650 | 3012500 | 1393150 | 785294 | 687600 | 97694 | 1266293 | 1028599 | 237694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 178000 | 137150 | 0 | 137150 | 167150 | 0 | 167150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630175 | 0 | 630175 | 7527 | 0 | 7527 | 343526 | 0 | 343526 | 16343674 | 3412500 | 12931174 | 2184197 | 734162 | 1450035 | 6683195 | 1138161 | 5545034 | 16343674 | 3412500 | 12931174 | 2184197 | 734162 | 1450035 | 6683195 | 1138161 | 5545034 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | CCI | 2011 | Q4 | Q4 - 2011 | 7429453 | 0 | 7429453 | 3077422 | 0 | 3077422 | 6611422 | 0 | 6611422 | 2038396 | 0 | 2038396 | 185566 | 0 | 185566 | 869566 | 0 | 869566 | 1662000 | 400000 | 1262000 | 1066991 | 92062 | 974929 | 1236991 | 132062 | 1104929 | 4405650 | 3012500 | 1393150 | 1036567 | 887443 | 149124 | 2161568 | 1927443 | 234124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 178000 | 151875 | 0 | 151875 | 172875 | 0 | 172875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630175 | 0 | 630175 | 187438 | 0 | 187438 | 453438 | 0 | 453438 | 16343674 | 3412500 | 12931174 | 5705859 | 979505 | 4726354 | 11505860 | 2059505 | 9446354 | 16343674 | 3412500 | 12931174 | 5705859 | 979505 | 4726354 | 11505860 | 2059505 | 9446354 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | CCI | 2012 | Q1 | Q1 - 2012 | 7429453 | 0 | 7429453 | 7127939 | 0 | 7127939 | 7427939 | 0 | 7427939 | 2038396 | 0 | 2038396 | 338054 | 0 | 338054 | 1178054 | 0 | 1178054 | 1662000 | 400000 | 1262000 | 1252761 | 130006 | 1122755 | 1438761 | 177006 | 1261755 | 4405650 | 3012500 | 1393150 | 2523235 | 2045749 | 477486 | 2830235 | 2189749 | 640486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178000 | 0 | 178000 | 157000 | 0 | 157000 | 162000 | 0 | 162000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630175 | 0 | 630175 | 416651 | 0 | 416651 | 437651 | 0 | 437651 | 16343674 | 3412500 | 12931174 | 11815640 | 2175755 | 9639885 | 13474640 | 2366755 | 11107885 | 16343674 | 3412500 | 12931174 | 11815640 | 2175755 | 9639885 | 13474640 | 2366755 | 11107885 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | CCI | 2012 | Q2 | Q2 - 2012 | 7704173 | 0 | 7704173 | 7300949 | 0 | 7300949 | 7409949 | 0 | 7409949 | 1754595 | 0 | 1754595 | 615302 | 0 | 615302 | 1124302 | 0 | 1124302 | 1904782 | 645219 | 1259563 | 1495395 | 238270 | 1257125 | 1697833 | 438270 | 1259563 | 4374703 | 2767281 | 1607422 | 3301722 | 2135649 | 1166073 | 3954722 | 2375649 | 1579073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448421 | 0 | 448421 | 425257 | 0 | 425257 | 432887 | 0 | 432887 | 16343674 | 3412500 | 12931174 | 13295625 | 2373919 | 10921706 | 14776693 | 2813919 | 11962774 | 16343674 | 3412500 | 12931174 | 13295625 | 2373919 | 10921706 | 14776693 | 2813919 | 11962774 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | CCI | 2012 | Q3 | Q3 - 2012 | 7704173 | 0 | 7704173 | 7386339 | 0 | 7386339 | 7704173 | 0 | 7704173 | 1754595 | 0 | 1754595 | 724779 | 0 | 724779 | 1683780 | 0 | 1683780 | 1904782 | 645219 | 1259563 | 1695070 | 437132 | 1257938 | 1885070 | 625507 | 1259563 | 4374703 | 2767281 | 1607422 | 3642747 | 2161022 | 1481725 | 3937443 | 2330022 | 1607421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448421 | 0 | 448421 | 429768 | 0 | 429768 | 448421 | 0 | 448421 | 16343674 | 3412500 | 12931174 | 14035703 | 2598154 | 11437549 | 15815887 | 2955529 | 12860358 | 16343674 | 3412500 | 12931174 | 14035703 | 2598154 | 11437549 | 15815887 | 2955529 | 12860358 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | CCI | 2012 | Q4 | Q4 - 2012 | 7902256 | 119659 | 7782597 | 7782598 | 0 | 7782598 | 7896274 | 113676 | 7782598 | 1902043 | 190119 | 1711924 | 1483722 | 0 | 1483722 | 1881127 | 169203 | 1711924 | 2006759 | 747150 | 1259609 | 1885717 | 626108 | 1259609 | 2004919 | 745310 | 1259609 | 3936561 | 2355572 | 1580989 | 3864561 | 2283572 | 1580989 | 3936561 | 2355572 | 1580989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439055 | 0 | 439055 | 439054 | 0 | 439054 | 439055 | 0 | 439055 | 16343674 | 3412500 | 12931174 | 15612652 | 2909680 | 12702972 | 16314936 | 3383761 | 12931175 | 16343674 | 3412500 | 12931174 | 15612652 | 2909680 | 12702972 | 16314936 | 3383761 | 12931175 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | CCI | 2013 | Q1 | Q1 - 2013 | 7902256 | 119659 | 7782597 | 7809803 | 27205 | 7782598 | 7902256 | 119659 | 7782597 | 1902043 | 190119 | 1711924 | 1593513 | 24000 | 1569513 | 1902043 | 190119 | 1711924 | 2006759 | 747150 | 1259609 | 1994750 | 735141 | 1259609 | 2006759 | 747150 | 1259609 | 3936561 | 2355572 | 1580989 | 3869661 | 2288672 | 1580989 | 3936561 | 2355572 | 1580989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439055 | 0 | 439055 | 439055 | 0 | 439054 | 439055 | 0 | 439055 | 16343674 | 3412500 | 12931174 | 15863782 | 3075018 | 12788763 | 16343674 | 3412500 | 12931174 | 16343674 | 3412500 | 12931174 | 15863782 | 3075018 | 12788763 | 16343674 | 3412500 | 12931174 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | CCI | 2013 | Q2 | Q2 - 2013 | 7742060 | 90946 | 7651114 | 7692675 | 41561 | 7651114 | 7742060 | 90946 | 7651114 | 1875258 | 24000 | 1851258 | 1839004 | 24000 | 1815004 | 1875258 | 24000 | 1851258 | 2230041 | 970432 | 1259609 | 2230041 | 970432 | 1259609 | 2230041 | 970432 | 1259609 | 3908111 | 2327122 | 1580989 | 3908111 | 2327122 | 1580989 | 3908111 | 2327122 | 1580989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431204 | 0 | 431204 | 431204 | 0 | 431204 | 431204 | 0 | 431204 | 16343674 | 3412500 | 12931174 | 16258035 | 3363115 | 12894920 | 16343674 | 3412500 | 12931174 | 16343674 | 3412500 | 12931174 | 16258035 | 3363115 | 12894920 | 16343674 | 3412500 | 12931174 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570033 | CCI | 2013 | Q3 | Q3 - 2013 | 7712648 | 61534 | 7651114 | 7712648 | 61534 | 7651114 | 7712648 | 61534 | 7651114 | 1876517 | 25258 | 1851258 | 1876517 | 25258 | 1851258 | 1876517 | 25258 | 1851258 | 2258195 | 998586 | 1259609 | 2258195 | 998586 | 1259609 | 2258195 | 998586 | 1259609 | 3908111 | 2327122 | 1580989 | 3908111 | 2327122 | 1580989 | 3908111 | 2327122 | 1580989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 157000 | 0 | 157000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431204 | 0 | 431204 | 431204 | 0 | 431204 | 431204 | 0 | 431204 | 16343675 | 3412500 | 12931174 | 16343675 | 3412500 | 12931174 | 16343675 | 3412500 | 12931174 | 16343675 | 3412500 | 12931174 | 16343675 | 3412500 | 12931174 | 16343675 | 3412500 | 12931174 | 0 | 0 | Iniciativa Tecnologica Centro Oriental (INTECO) | TRUE
NT10BIX5570034 | CCI | 2010 | Q3 | Q3 - 2010 | 5462091 | 535825 | 4926266 | 0 | 0 | 0 | 2680965 | 131548 | 2549417 | 3000000 | 294296 | 2705704 | 81289 | 16258 | 65031 | 466000 | 23300 | 442700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1743207 | 171007 | 1572200 | 3480 | 696 | 2784 | 1186350 | 59317 | 1127033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 8829 | 81171 | 9435 | 1887 | 7548 | 90000 | 4500 | 85500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111000 | 10889 | 100111 | 0 | 0 | 0 | 111000 | 5550 | 105450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1325517 | 1325517 | 0 | 0 | 0 | 0 | 938815 | 938815 | 0 | 11731815 | 2346363 | 9385452 | 94204 | 18841 | 75363 | 5473130 | 1163030 | 4310100 | 11731815 | 2346363 | 9385452 | 94204 | 18841 | 75363 | 5473130 | 1163030 | 4310100 | 0 | 0 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | CCI | 2010 | Q4 | Q4 - 2010 | 5462091 | 535825 | 4926266 | 2919671 | 487062 | 2432609 | 4613671 | 666020 | 3947651 | 2660000 | 260943 | 2399057 | 501861 | 96086 | 405775 | 1197861 | 235286 | 962575 | 15000 | 1472 | 13528 | 0 | 0 | 0 | 14500 | 2900 | 11600 | 1993207 | 195531 | 1797676 | 593302 | 42789 | 550513 | 962558 | 116640 | 845918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 8829 | 81171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 18246 | 167754 | 146574 | 0 | 146574 | 146574 | 0 | 146574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1325517 | 1325517 | 0 | 0 | 0 | 0 | 937608 | 937608 | 0 | 11731815 | 2346363 | 9385452 | 4161408 | 625937 | 3535471 | 7872772 | 1958454 | 5914318 | 11731815 | 2346363 | 9385452 | 4161408 | 625937 | 3535471 | 7872772 | 1958454 | 5914318 | 0 | 0 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | CCI | 2011 | Q1 | Q1 - 2011 | 5462091 | 562086 | 4900005 | 4435531 | 562086 | 3873445 | 4647530 | 562086 | 4085444 | 2446157 | 99675 | 2346482 | 1083592 | 99675 | 983917 | 1451592 | 99675 | 1351917 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1106550 | 96134 | 1010416 | 1334550 | 96133 | 1238417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 899774 | 899774 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 7714846 | 1670743 | 6044103 | 9252431 | 2400328 | 6852103 | 11731815 | 2400329 | 9331486 | 7714846 | 1670743 | 6044103 | 9252431 | 2400328 | 6852103 | 0 | 0 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | CCI | 2011 | Q2 | Q2 - 2011 | 5462091 | 562086 | 4900005 | 4552353 | 562086 | 3990267 | 4742003 | 562086 | 4179917 | 2446157 | 99675 | 2346482 | 1327063 | 99675 | 1227388 | 1590562 | 99675 | 1490887 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1220185 | 96134 | 1124051 | 1463185 | 96134 | 1367051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 8918360 | 2400329 | 6518031 | 9614509 | 2400329 | 7214180 | 11731815 | 2400329 | 9331486 | 8918360 | 2400329 | 6518031 | 9614509 | 2400329 | 7214180 | 0 | 0 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | CCI | 2011 | Q3 | Q3 - 2011 | 5462091 | 562086 | 4900005 | 5037138 | 562086 | 4475052 | 5088138 | 562086 | 4526052 | 2446157 | 99675 | 2346482 | 1560576 | 99675 | 1460901 | 1728408 | 99675 | 1628733 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1247604 | 96134 | 1151470 | 1273925 | 96134 | 1177791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 9664077 | 2400329 | 7263748 | 9909230 | 2400329 | 7508901 | 11731815 | 2400329 | 9331486 | 9664077 | 2400329 | 7263748 | 9909230 | 2400329 | 7508901 | 0 | 0 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | CCI | 2011 | Q4 | Q4 - 2011 | 5462091 | 562086 | 4900005 | 5065183 | 562086 | 4503097 | 5290183 | 562086 | 4728097 | 2446157 | 99675 | 2346482 | 2013792 | 99675 | 1914117 | 2114309 | 99675 | 2014634 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1429827 | 96134 | 1333693 | 1494827 | 96134 | 1398693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 10327561 | 2400329 | 7927232 | 10718078 | 2400329 | 8317749 | 11731815 | 2400329 | 9331486 | 10327561 | 2400329 | 7927232 | 10718078 | 2400329 | 8317749 | 0 | 0 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | CCI | 2012 | Q1 | Q1 - 2012 | 5462091 | 562086 | 4900005 | 5112409 | 562086 | 4550323 | 5368409 | 562086 | 4806323 | 2446157 | 99675 | 2346482 | 2063558 | 99675 | 1963883 | 2164075 | 99675 | 2064400 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1444017 | 96134 | 1347883 | 1509017 | 96134 | 1412883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 10438743 | 2400329 | 8038414 | 10860260 | 2400329 | 8459931 | 11731815 | 2400329 | 9331486 | 10438743 | 2400329 | 8038414 | 10860260 | 2400329 | 8459931 | 0 | 0 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | CCI | 2012 | Q2 | Q2 - 2012 | 5462091 | 562086 | 4900005 | 5124433 | 562086 | 4562347 | 5380433 | 562086 | 4818347 | 2446157 | 99675 | 2346482 | 2101420 | 99675 | 2001745 | 2117920 | 99675 | 2018245 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1508183 | 96134 | 1412049 | 1536183 | 96134 | 1440049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 10552795 | 2400329 | 8152466 | 10853295 | 2400329 | 8452966 | 11731815 | 2400329 | 9331486 | 10552795 | 2400329 | 8152466 | 10853295 | 2400329 | 8452966 | 0 | 0 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | CCI | 2012 | Q3 | Q3 - 2012 | 5462091 | 562086 | 4900005 | 5123383 | 562086 | 4561297 | 5655288 | 562086 | 5093202 | 2446157 | 99675 | 2346482 | 2113140 | 99675 | 2013465 | 2113890 | 99675 | 2014215 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1530086 | 96134 | 1433952 | 1639667 | 96134 | 1543533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 10585368 | 2400329 | 8185039 | 11227604 | 2400329 | 8827275 | 11731815 | 2400329 | 9331486 | 10585368 | 2400329 | 8185039 | 11227604 | 2400329 | 8827275 | 0 | 0 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | CCI | 2012 | Q4 | Q4 - 2012 | 5462091 | 562086 | 4900005 | 5400288 | 562086 | 4838202 | 5400288 | 562086 | 4838202 | 2446157 | 99675 | 2346482 | 2109366 | 99675 | 2009691 | 2109366 | 99675 | 2009691 | 15000 | 0 | 15000 | 13561 | 0 | 13561 | 13561 | 0 | 13561 | 1993207 | 96134 | 1897073 | 1530086 | 96134 | 1433952 | 1530086 | 96134 | 1433952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 10858499 | 2400329 | 8458170 | 10858499 | 2400329 | 8458170 | 11731815 | 2400329 | 9331486 | 10858499 | 2400329 | 8458170 | 10858499 | 2400329 | 8458170 | 0 | 0 | DeltaCom, Inc. | TRUE
NT10BIX5570034 | CCI | 2013 | Q1 | Q1 - 2013 | 5462091 | 562086 | 4900005 | 5400288 | 562086 | 4838202 | 5400288 | 562086 | 4838202 | 2446157 | 99675 | 2346482 | 1916228 | 99675 | 1816553 | 1916228 | 99675 | 1816553 | 15000 | 0 | 15000 | 75192 | 0 | 75192 | 75192 | 0 | 75192 | 1993207 | 96134 | 1897073 | 1526291 | 96134 | 1430157 | 1526291 | 96134 | 1430157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 13074 | 172926 | 175838 | 13074 | 162764 | 175838 | 13074 | 162764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 1629360 | 1629360 | 0 | 11731815 | 2400329 | 9331486 | 10723197 | 2400329 | 8322868 | 10723197 | 2400329 | 8322868 | 11731815 | 2400329 | 9331486 | 10723197 | 2400329 | 8322868 | 10723197 | 2400329 | 8322868 | 0 | 0 | DeltaCom, Inc. | TRUE
NT10BIX5570035 | CCI | 2010 | Q3 | Q3 - 2010 | 947990 | 381962 | 566028 | 75481 | 75481 | 0 | 75481 | 75481 | 0 | 2186252 | 432142 | 1754110 | 355284 | 355284 | 0 | 355284 | 355284 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 7500 | 0 | 7500 | 205133 | 4983 | 200150 | 4983 | 4983 | 0 | 46116 | 4983 | 41133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 0 | 0 | 0 | 241136 | 0 | 241136 | 0 | 0 | 0 | 0 | 0 | 0 | 41152 | 41152 | 0 | 83980 | 0 | 83980 | 0 | 0 | 0 | 0 | 0 | 0 | 60357 | 58362 | 1995 | 69453 | 69453 | 0 | 97019 | 95024 | 1995 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 71404 | 66422 | 4983 | 71404 | 66421 | 0 | 71404 | 66421 | 4983 | 4145630 | 943871 | 3201760 | 576605 | 571622 | 0 | 935092 | 638345 | 296747 | 4145630 | 943871 | 3201760 | 576605 | 571622 | 0 | 935092 | 638345 | 296747 | 0 | 0 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | CCI | 2010 | Q4 | Q4 - 2010 | 947990 | 381962 | 566028 | 75481 | 75481 | 0 | 150962 | 75481 | 75481 | 2186252 | 432142 | 1754110 | 355284 | 355284 | 0 | 355284 | 355284 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 7500 | 0 | 7500 | 205133 | 4983 | 200150 | 4983 | 4983 | 0 | 28383 | 4983 | 23400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 324102 | 324102 | 0 | 454901 | 0 | 454901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83980 | 0 | 83980 | 0 | 0 | 0 | 0 | 0 | 0 | 60357 | 58362 | 1995 | 69453 | 69453 | 0 | 69453 | 69453 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 71404 | 66421 | 4983 | 25082 | 25082 | 0 | 71404 | 66421 | 4983 | 4145630 | 943870 | 3201760 | 854385 | 854385 | 0 | 1137887 | 571622 | 566265 | 4145630 | 943870 | 3201760 | 854385 | 854385 | 0 | 1137887 | 571622 | 566265 | 0 | 0 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | CCI | 2011 | Q1 | Q1 - 2011 | 947990 | 381962 | 566028 | 0 | 0 | 0 | 404353 | 381962 | 22391 | 2186252 | 432142 | 1754110 | 505201 | 432142 | 73059 | 925201 | 432142 | 493059 | 7500 | 0 | 7500 | 25082 | 17582 | 7500 | 25082 | 17582 | 7500 | 205133 | 0 | 205133 | 0 | 0 | 0 | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 490398 | 0 | 490398 | 713695 | 223297 | 490398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83980 | 0 | 83980 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4015864 | 814104 | 3201760 | 1020681 | 449724 | 570957 | 2128331 | 1054983 | 1073348 | 4015864 | 814104 | 3201760 | 1020681 | 449724 | 570957 | 2128331 | 1054983 | 1073348 | 0 | 0 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | CCI | 2011 | Q2 | Q2 - 2011 | 947990 | 381962 | 566028 | 45355 | 43863 | 1492 | 45355 | 43863 | 1492 | 2186252 | 432142 | 1754110 | 398026 | 398026 | 0 | 1061120 | 398026 | 663094 | 7500 | 0 | 7500 | 24232 | 16732 | 7500 | 24232 | 16732 | 7500 | 205133 | 0 | 205133 | 25200 | 0 | 25200 | 25200 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 415168 | 0 | 415168 | 576323 | 0 | 576323 | 0 | 0 | 0 | 277009 | 277009 | 0 | 392292 | 392292 | 0 | 83980 | 0 | 83980 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4015864 | 814104 | 3201760 | 1184990 | 735630 | 449360 | 2124522 | 850913 | 1273609 | 4015864 | 814104 | 3201760 | 1184990 | 735630 | 449360 | 2124522 | 850913 | 1273609 | 0 | 0 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | CCI | 2011 | Q3 | Q3 - 2011 | 947990 | 381962 | 566028 | 43863 | 43863 | 0 | 267452 | 43863 | 223589 | 2186252 | 432142 | 1754110 | 422536 | 422536 | 0 | 2326300 | 770241 | 1556059 | 7500 | 0 | 7500 | 24232 | 16732 | 7500 | 24232 | 16732 | 7500 | 205133 | 0 | 205133 | 25200 | 0 | 25200 | 89354 | 0 | 89354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 569010 | 0 | 569010 | 578636 | 0 | 578636 | 0 | 0 | 0 | 288020 | 288020 | 0 | 392049 | 392049 | 0 | 83980 | 0 | 83980 | 0 | 0 | 0 | 83980 | 0 | 83980 | 1995 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4015864 | 814104 | 3201760 | 1372861 | 771151 | 601710 | 3762003 | 1222885 | 2539118 | 4015864 | 814104 | 3201760 | 1372861 | 771151 | 601710 | 3762003 | 1222885 | 2539118 | 0 | 0 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | CCI | 2011 | Q4 | Q4 - 2011 | 947990 | 381962 | 566028 | 226005 | 159867 | 66138 | 249555 | 159867 | 89688 | 2186252 | 432142 | 1754110 | 1293553 | 644695 | 648857 | 1537982 | 644695 | 893286 | 7500 | 0 | 7500 | 24232 | 0 | 24232 | 24232 | 0 | 24232 | 205133 | 0 | 205133 | 25200 | 0 | 25200 | 25200 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 1118532 | 9542 | 1108990 | 1126934 | 9542 | 1117392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83980 | 0 | 83980 | 43884 | 0 | 43884 | 139720 | 0 | 139720 | 1995 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2716 | 0 | 2716 | 4015864 | 814104 | 3201760 | 2731406 | 814104 | 1917301 | 3106339 | 814104 | 2292234 | 4015864 | 814104 | 3201760 | 2731406 | 814104 | 1917301 | 3106339 | 814104 | 2292234 | 0 | 0 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | CCI | 2012 | Q1 | Q1 - 2012 | 947990 | 381962 | 566028 | 259097 | 169409 | 89688 | 398675 | 169409 | 229266 | 2186252 | 432142 | 1754110 | 2013146 | 644695 | 1368451 | 2067599 | 644695 | 1422903 | 7500 | 0 | 7500 | 24232 | 0 | 24232 | 24232 | 0 | 24232 | 205133 | 0 | 205133 | 25200 | 0 | 25200 | 25200 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 1155787 | 0 | 1155787 | 1296034 | 0 | 1296034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83980 | 0 | 83980 | 157497 | 0 | 157497 | 204124 | 0 | 204125 | 1995 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5416 | 0 | 5416 | 0 | 0 | 0 | 4015864 | 814104 | 3201760 | 3640375 | 814104 | 2826271 | 4015864 | 814104 | 3201760 | 4015864 | 814104 | 3201760 | 3640375 | 814104 | 2826271 | 4015864 | 814104 | 3201760 | 0 | 0 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | CCI | 2012 | Q2 | Q2 - 2012 | 947990 | 381962 | 566028 | 323042 | 169409 | 153633 | 323042 | 169409 | 153633 | 2186252 | 432142 | 1754110 | 2152614 | 644695 | 1507919 | 2152614 | 644695 | 1507919 | 7500 | 0 | 7500 | 24232 | 0 | 24232 | 24232 | 0 | 24232 | 205133 | 0 | 205133 | 25200 | 0 | 25200 | 25200 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 1207712 | 0 | 1207712 | 1202333 | 0 | 1202333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83980 | 0 | 83980 | 184089 | 0 | 184089 | 278687 | 0 | 278687 | 1995 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9756 | 0 | 9756 | 9756 | 0 | 9756 | 4015864 | 814104 | 3201760 | 3926645 | 814104 | 3112541 | 4015864 | 814104 | 3201760 | 4015864 | 814104 | 3201760 | 3926645 | 814104 | 3112541 | 4015864 | 814104 | 3201760 | 0 | 0 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | CCI | 2012 | Q3 | Q3 - 2012 | 947990 | 381962 | 566028 | 311798 | 153262 | 158536 | 311798 | 153262 | 158536 | 2186252 | 432142 | 1754110 | 2219065 | 660842 | 1558223 | 2227465 | 660842 | 1566623 | 7500 | 0 | 7500 | 24232 | 0 | 24232 | 24232 | 0 | 24232 | 205133 | 0 | 205133 | 25200 | 0 | 25200 | 25200 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579642 | 0 | 579642 | 1148482 | 0 | 1148482 | 1148482 | 0 | 1148482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83980 | 0 | 83980 | 278687 | 0 | 278687 | 278687 | 0 | 278687 | 1995 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 3372 | 0 | 3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4015864 | 814104 | 3201760 | 4007464 | 814104 | 3193360 | 4015864 | 814104 | 3201760 | 4015864 | 814104 | 3201760 | 4007464 | 814104 | 3193360 | 4015864 | 814104 | 3201760 | 0 | 377 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570035 | CCI | 2012 | Q4 | Q4 - 2012 | 418898 | 230934 | 187964 | 418898 | 230934 | 187964 | 418898 | 230934 | 187964 | 2501256 | 969062 | 1532194 | 2501256 | 969062 | 1532194 | 2501256 | 969062 | 1532194 | 24232 | 0 | 24232 | 24232 | 0 | 24232 | 24232 | 0 | 24232 | 25200 | 0 | 25200 | 25200 | 0 | 25200 | 25200 | 0 | 25200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1393482 | 292741 | 1100741 | 1393482 | 292741 | 1100741 | 1393482 | 292741 | 1100741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326429 | 0 | 326429 | 326429 | 0 | 326429 | 326429 | 0 | 326429 | 5000 | 0 | 5000 | 5000 | 0 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4694497 | 1492737 | 3201760 | 4694497 | 1492737 | 3201760 | 4694497 | 1492737 | 3201760 | 4694497 | 1492737 | 3201760 | 4694497 | 1492737 | 3201760 | 4694497 | 1492737 | 3201760 | 0 | 319 | Hardy Telecommunications, Inc. | TRUE
NT10BIX5570036 | CCI | 2010 | Q3 | Q3 - 2010 | 1419750 | 354937 | 1064813 | 0 | 0 | 0 | 675000 | 168750 | 506250 | 169600 | 42400 | 127200 | 0 | 0 | 0 | 100000 | 25000 | 75000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 8000 | 2000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 2500 | 675 | 1875 | 30000 | 7500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431912 | 1295738 | 2500 | 675 | 1875 | 817000 | 204250 | 612750 | 1727650 | 431912 | 1295738 | 2500 | 675 | 1875 | 817000 | 204250 | 612750 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | CCI | 2010 | Q4 | Q4 - 2010 | 1419750 | 354937 | 1064813 | 0 | 0 | 0 | 0 | 0 | 0 | 169600 | 42400 | 127200 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 8000 | 2000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 10000 | 2500 | 7500 | 30000 | 7500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431912 | 1295738 | 10000 | 2500 | 7500 | 122000 | 30500 | 91500 | 1727650 | 431912 | 1295738 | 10000 | 2500 | 7500 | 122000 | 30500 | 91500 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | CCI | 2011 | Q1 | Q1 - 2011 | 1419750 | 354938 | 1064812 | 479032 | 119758 | 359274 | 520000 | 130000 | 390000 | 169600 | 42400 | 127200 | 0 | 0 | 0 | 75000 | 18750 | 56250 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 10000 | 2500 | 7500 | 10000 | 2500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 489032 | 122258 | 366774 | 609000 | 152250 | 456750 | 1727650 | 431913 | 1295737 | 489032 | 122258 | 366774 | 609000 | 152250 | 456750 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | CCI | 2011 | Q2 | Q2 - 2011 | 1419750 | 354938 | 1064812 | 517075 | 129269 | 387806 | 520000 | 130000 | 390000 | 169600 | 42400 | 127200 | 0 | 0 | 0 | 75000 | 18750 | 56250 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 85 | 21 | 64 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 10000 | 2500 | 7500 | 10000 | 2500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 527160 | 131790 | 395370 | 609500 | 152375 | 457125 | 1727650 | 431913 | 1295737 | 527160 | 131790 | 395370 | 609500 | 152375 | 457125 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | CCI | 2011 | Q3 | Q3 - 2011 | 1419750 | 354938 | 1064812 | 591654 | 147913 | 443741 | 605000 | 151250 | 453750 | 169600 | 42400 | 127200 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 85 | 21 | 64 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 9850 | 2463 | 7387 | 9850 | 2463 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 623166 | 155791 | 467375 | 720350 | 180088 | 540262 | 1727650 | 431913 | 1295737 | 623166 | 155791 | 467375 | 720350 | 180088 | 540262 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | CCI | 2011 | Q4 | Q4 - 2011 | 1419750 | 354938 | 1064812 | 591654 | 147913 | 443741 | 596654 | 149163 | 447491 | 169600 | 42400 | 127200 | 112125 | 28031 | 84094 | 117000 | 29250 | 87750 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 9850 | 2463 | 7387 | 9850 | 2463 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 735811 | 183952 | 551859 | 749109 | 187277 | 561832 | 1727650 | 431913 | 1295737 | 735811 | 183952 | 551859 | 749109 | 187277 | 561832 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | CCI | 2012 | Q1 | Q1 - 2012 | 1419750 | 354938 | 1064812 | 591697 | 147924 | 443773 | 591697 | 147924 | 443773 | 169600 | 42400 | 127200 | 121877 | 30469 | 91408 | 121877 | 30469 | 91408 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 9850 | 2463 | 7387 | 9850 | 2463 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 745606 | 186401 | 559205 | 745606 | 186401 | 559205 | 1727650 | 431913 | 1295737 | 745606 | 186401 | 559205 | 745606 | 186401 | 559205 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | CCI | 2012 | Q2 | Q2 - 2012 | 1419750 | 354938 | 1064812 | 591697 | 147924 | 443773 | 591697 | 147924 | 443773 | 169600 | 42400 | 127200 | 121877 | 30469 | 91408 | 121877 | 30469 | 91408 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 9850 | 2463 | 7387 | 9850 | 2463 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 745606 | 186401 | 559205 | 745606 | 186401 | 559205 | 1727650 | 431913 | 1295737 | 745606 | 186401 | 559205 | 745606 | 186401 | 559205 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | CCI | 2012 | Q3 | Q3 - 2012 | 1419750 | 354938 | 1064812 | 591697 | 147924 | 443773 | 591697 | 147924 | 443773 | 169600 | 42400 | 127200 | 121877 | 30469 | 91408 | 121877 | 30469 | 91408 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 9850 | 2463 | 7387 | 9850 | 2463 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 745886 | 186471 | 559415 | 745886 | 186471 | 559415 | 1727650 | 431913 | 1295737 | 745886 | 186471 | 559415 | 745886 | 186471 | 559415 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | CCI | 2012 | Q4 | Q4 - 2012 | 1419750 | 354938 | 1064812 | 591697 | 147924 | 443773 | 591697 | 147924 | 443773 | 169600 | 42400 | 127200 | 121877 | 30469 | 91408 | 121877 | 30469 | 91408 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 47577 | 11894 | 35683 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 9850 | 2463 | 7387 | 9850 | 2463 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 745886 | 186471 | 559415 | 771886 | 192971 | 578915 | 1727650 | 431913 | 1295737 | 745886 | 186471 | 559415 | 771886 | 192971 | 578915 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570036 | CCI | 2013 | Q1 | Q1 - 2013 | 1419750 | 354938 | 1064812 | 591697 | 147924 | 443773 | 591697 | 147924 | 443773 | 169600 | 42400 | 127200 | 121877 | 30469 | 91408 | 121877 | 30469 | 91408 | 80000 | 20000 | 60000 | 55859 | 13965 | 41894 | 55859 | 13965 | 41894 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 9850 | 2463 | 7387 | 9850 | 2463 | 7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727650 | 431913 | 1295737 | 780168 | 195042 | 585126 | 780168 | 195042 | 585126 | 1727650 | 431913 | 1295737 | 780168 | 195042 | 585126 | 780168 | 195042 | 585126 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570037 | CCI | 2010 | Q3 | Q3 - 2010 | 3023304 | 1634147 | 1389157 | 1434624 | 1434624 | 0 | 1434624 | 1434624 | 0 | 10424137 | 2340987 | 8083150 | 0 | 0 | 0 | 408500 | 0 | 408500 | 664602 | 328902 | 335700 | 176092 | 97320 | 78772 | 436092 | 107092 | 329000 | 1314425 | 72500 | 1241925 | 81988 | 81988 | 0 | 81988 | 81988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706186 | 0 | 706186 | 300963 | 0 | 300963 | 500963 | 0 | 500963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1238739 | 0 | 1238739 | 0 | 0 | 0 | 40000 | 0 | 40000 | 480975 | 0 | 480975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149763 | 142591 | 7172 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 1993667 | 1613932 | 379735 | 2902167 | 1623704 | 1278463 | 18002131 | 4519127 | 13483004 | 1993667 | 1613932 | 379735 | 2902167 | 1623704 | 1278463 | 1849500 | 0 | Columbia, County of | TRUE
NT10BIX5570037 | CCI | 2010 | Q4 | Q4 - 2010 | 3023304 | 1634147 | 1389157 | 1464567 | 1463787 | 780 | 1500000 | 1470000 | 30000 | 10424137 | 2340987 | 8083150 | 8050 | 0 | 8050 | 2500000 | 0 | 2500000 | 664602 | 328902 | 335700 | 289705 | 106738 | 182967 | 430000 | 118000 | 312000 | 1314425 | 72500 | 1241925 | 81988 | 81988 | 0 | 81988 | 81988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706186 | 0 | 706186 | 539504 | 0 | 539504 | 650000 | 0 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1238739 | 0 | 1238739 | 0 | 0 | 0 | 250000 | 0 | 250000 | 480975 | 0 | 480975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149763 | 142591 | 7172 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 2383814 | 1652513 | 731301 | 5411988 | 1669988 | 3742000 | 18002131 | 4519127 | 13483004 | 2383814 | 1652513 | 731301 | 5411988 | 1669988 | 3742000 | 1849500 | 0 | Columbia, County of | TRUE
NT10BIX5570037 | CCI | 2011 | Q1 | Q1 - 2011 | 2923304 | 1634147 | 1289157 | 1463787 | 1463787 | 0 | 1543787 | 1478787 | 65000 | 10424137 | 2340987 | 8083150 | 614835 | 0 | 614835 | 3000000 | 300000 | 2700000 | 732102 | 328902 | 403200 | 417434 | 137049 | 280385 | 450000 | 150000 | 300000 | 1314425 | 72500 | 1241925 | 81988 | 81988 | 0 | 881988 | 81988 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 740049 | 0 | 740049 | 900000 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688739 | 0 | 688739 | 92884 | 0 | 92884 | 300000 | 0 | 300000 | 480975 | 0 | 480975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149763 | 142591 | 7172 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 3410977 | 1682824 | 1728153 | 7075775 | 2010775 | 5065000 | 18002131 | 4519127 | 13483004 | 3410977 | 1682824 | 1728153 | 7075775 | 2010775 | 5065000 | 1849500 | 0 | Columbia, County of | TRUE
NT10BIX5570037 | CCI | 2011 | Q2 | Q2 - 2011 | 2923304 | 1634147 | 1289157 | 1555868 | 1463787 | 92081 | 1555868 | 1463787 | 92081 | 10424137 | 2340987 | 8083150 | 3136704 | 0 | 3136704 | 7000000 | 700000 | 6300000 | 732102 | 328902 | 403200 | 417434 | 137049 | 280385 | 500000 | 150000 | 350000 | 1314425 | 72500 | 1241925 | 100777 | 81988 | 18789 | 1200000 | 81988 | 1281988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 855281 | 0 | 855281 | 950000 | 0 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688739 | 0 | 688739 | 211028 | 0 | 211028 | 350000 | 0 | 350000 | 480975 | 0 | 480975 | 0 | 0 | 0 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149763 | 142591 | 7172 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 6277092 | 1682824 | 4594268 | 11755868 | 2395775 | 9524069 | 18002131 | 4519127 | 13483004 | 6277092 | 1682824 | 4594268 | 11755868 | 2395775 | 9524069 | 1849500 | 0 | Columbia, County of | TRUE
NT10BIX5570037 | CCI | 2011 | Q3 | Q3 - 2011 | 2923304 | 1634147 | 1289157 | 1643361 | 1463787 | 179574 | 1643361 | 1463787 | 179574 | 10424137 | 2340987 | 8083150 | 5933987 | 0 | 5933987 | 7500000 | 1400000 | 6000000 | 732102 | 328902 | 403200 | 449704 | 195026 | 254678 | 600000 | 200000 | 400000 | 1314425 | 72500 | 1241925 | 100777 | 81988 | 18789 | 836988 | 81988 | 755000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 855281 | 0 | 855281 | 950000 | 0 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688739 | 0 | 688739 | 348427 | 0 | 348427 | 500000 | 0 | 500000 | 480975 | 0 | 480975 | 0 | 0 | 0 | 392000 | 0 | 392000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149763 | 142591 | 7172 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 9331537 | 1740801 | 7590736 | 12422349 | 3145775 | 9176574 | 18002131 | 4519127 | 13483004 | 9331537 | 1740801 | 7590736 | 12422349 | 3145775 | 9176574 | 1849500 | 0 | Columbia, County of | TRUE
NT10BIX5570037 | CCI | 2011 | Q4 | Q4 - 2011 | 2632427 | 1418817 | 1213610 | 1531506 | 1389627 | 141879 | 1531506 | 1389627 | 141879 | 10424137 | 2304000 | 8120137 | 6925323 | 0 | 6925323 | 9500000 | 1800000 | 7700000 | 1033890 | 619958 | 413932 | 841113 | 554055 | 287058 | 950000 | 575000 | 375000 | 1403277 | 176352 | 1226925 | 931352 | 176352 | 755000 | 1376352 | 176352 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 1021590 | 0 | 1021590 | 1100000 | 0 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738739 | 0 | 738739 | 514864 | 0 | 514864 | 675000 | 0 | 675000 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 12246723 | 2120034 | 10126689 | 15613833 | 3940979 | 11672854 | 18002131 | 4519127 | 13483004 | 12246723 | 2120034 | 10126689 | 15613833 | 3940979 | 11672854 | 1849500 | 0 | Columbia, County of | TRUE
NT10BIX5570037 | CCI | 2012 | Q1 | Q1 - 2012 | 2632427 | 1418817 | 1213610 | 1531506 | 1389627 | 141879 | 1531506 | 1389627 | 141879 | 10424137 | 2304000 | 8120137 | 8415068 | 1410320 | 7004748 | 10000000 | 2000000 | 8000000 | 1033890 | 619958 | 413932 | 980954 | 585047 | 395907 | 1000000 | 600000 | 400000 | 1403277 | 176352 | 1226925 | 931352 | 176352 | 755000 | 1376352 | 176352 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 1260813 | 0 | 1260813 | 1275000 | 0 | 1275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738739 | 0 | 738739 | 611594 | 0 | 611594 | 700000 | 0 | 700000 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 14212262 | 3561346 | 10650916 | 16363833 | 4165979 | 12197854 | 18002131 | 4519127 | 13483004 | 14212262 | 3561346 | 10650916 | 16363833 | 4165979 | 12197854 | 1849500 | 0 | Columbia, County of | TRUE
NT10BIX5570037 | CCI | 2012 | Q2 | Q2 - 2012 | 2632427 | 1418817 | 1213610 | 1559366 | 1389627 | 169739 | 2350000 | 1389627 | 960373 | 10424137 | 2304000 | 8120137 | 8935027 | 1858767 | 7076260 | 10126480 | 2126480 | 8000000 | 1033890 | 619958 | 413932 | 1015865 | 619958 | 395907 | 1015865 | 619958 | 395907 | 1403277 | 176352 | 1226925 | 1333272 | 176352 | 1156920 | 1403277 | 176352 | 1226925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 1260813 | 0 | 1260813 | 1260813 | 0 | 1260813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738739 | 0 | 738739 | 738739 | 0 | 738739 | 738739 | 0 | 738739 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 15324057 | 4044704 | 11279353 | 17376149 | 4312417 | 13063732 | 18002131 | 4519127 | 13483004 | 15324057 | 4044704 | 11279353 | 17376149 | 4312417 | 13063732 | 1849500 | 0 | Columbia, County of | TRUE
NT10BIX5570037 | CCI | 2012 | Q3 | Q3 - 2012 | 2632427 | 1418817 | 1213610 | 1730196 | 1389627 | 340569 | 2632427 | 1418817 | 1213610 | 10424137 | 2304000 | 8120137 | 9587583 | 2191833 | 7395750 | 10424137 | 2304000 | 8120137 | 1033890 | 619958 | 413932 | 1018476 | 619958 | 398518 | 1033890 | 619958 | 413932 | 1403277 | 176352 | 1226925 | 1333272 | 176352 | 1156920 | 1403277 | 176352 | 1226925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 1260813 | 0 | 1260813 | 1288686 | 0 | 1288686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738739 | 0 | 738739 | 738739 | 0 | 738739 | 738739 | 0 | 738739 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 480975 | 0 | 480975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 16150054 | 4377770 | 11772284 | 18002131 | 4519127 | 13483004 | 18002131 | 4519127 | 13483004 | 16150054 | 4377770 | 11772284 | 18002131 | 4519127 | 13483004 | 1849500 | 0 | Columbia, County of | TRUE
NT10BIX5570037 | CCI | 2012 | Q4 | Q4 - 2012 | 2632427 | 1418817 | 1213610 | 2684195 | 1408638 | 1275557 | 2725081 | 1408638 | 1316443 | 10424137 | 2304000 | 8120137 | 10126625 | 2314179 | 7812446 | 10273829 | 2314179 | 7959650 | 1033890 | 619958 | 413932 | 980539 | 619958 | 360581 | 980539 | 619958 | 360581 | 1403277 | 176352 | 1226925 | 1351312 | 176352 | 1174960 | 1412113 | 176352 | 1235761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 1191262 | 0 | 1191262 | 1191262 | 0 | 1191262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738739 | 0 | 738739 | 743765 | 0 | 743765 | 743765 | 0 | 743765 | 480975 | 0 | 480975 | 675542 | 0 | 675542 | 675542 | 0 | 675542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 17753240 | 4519127 | 13234113 | 18002131 | 4519127 | 13483004 | 18002131 | 4519127 | 13483004 | 17753240 | 4519127 | 13234113 | 18002131 | 4519127 | 13483004 | 1849500 | 0 | Columbia, County of | TRUE
NT10BIX5570037 | CCI | 2013 | Q1 | Q1 - 2013 | 2632427 | 1418817 | 1213610 | 2725081 | 1408638 | 1316210 | 2725081 | 1408638 | 1316210 | 10424137 | 2304000 | 8120137 | 10273829 | 2314179 | 7959883 | 10273829 | 2314179 | 7959883 | 1033890 | 619958 | 413932 | 980539 | 619958 | 360581 | 980539 | 619958 | 360581 | 1403277 | 176352 | 1226925 | 1412113 | 176352 | 1235761 | 1412113 | 176352 | 1235761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1288686 | 0 | 1288686 | 1191262 | 0 | 1191262 | 1191262 | 0 | 1191262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738739 | 0 | 738739 | 743765 | 0 | 743765 | 743765 | 0 | 743765 | 480975 | 0 | 480975 | 675542 | 0 | 675542 | 675542 | 0 | 675542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18002131 | 4519127 | 13483004 | 18002131 | 4519127 | 13483004 | 18002131 | 4519127 | 13483004 | 18002131 | 4519127 | 13483004 | 18002131 | 4519127 | 13483004 | 18002131 | 4519127 | 13483004 | 1849500 | 0 | Columbia, County of | TRUE
NT10BIX5570038 | CCI | 2010 | Q3 | Q3 - 2010 | 2246125 | 561531 | 1684594 | 0 | 0 | 0 | 850000 | 212500 | 637500 | 288300 | 72075 | 216225 | 0 | 0 | 0 | 150000 | 37500 | 112500 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 8000 | 6000 | 2000 | 19950 | 4988 | 14963 | 0 | 0 | 0 | 8500 | 2125 | 6375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 100000 | 25000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066251 | 14700 | 3675 | 11025 | 1116500 | 283125 | 833375 | 2755000 | 688750 | 2066251 | 14700 | 3675 | 11025 | 1116500 | 283125 | 833375 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | CCI | 2010 | Q4 | Q4 - 2010 | 2246125 | 561531 | 1684594 | 24030 | 6008 | 18022 | 850000 | 212500 | 637500 | 288300 | 72075 | 216225 | 0 | 0 | 0 | 150000 | 37500 | 112500 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 8000 | 2000 | 6000 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 8500 | 2125 | 6375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 100000 | 25000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 38730 | 9683 | 29047 | 1116500 | 279125 | 837375 | 2755000 | 688750 | 2066250 | 38730 | 9683 | 29047 | 1116500 | 279125 | 837375 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | CCI | 2011 | Q1 | Q1 - 2011 | 2246125 | 561531 | 1684594 | 561902 | 140476 | 421426 | 580000 | 145000 | 435000 | 288300 | 72075 | 216225 | 0 | 0 | 0 | 150000 | 37500 | 112500 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 8000 | 2000 | 6000 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 576602 | 144151 | 432451 | 752700 | 188175 | 564525 | 2755000 | 688750 | 2066250 | 576602 | 144151 | 432451 | 752700 | 188175 | 564525 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | CCI | 2011 | Q2 | Q2 - 2011 | 2246125 | 561531 | 1684594 | 684321 | 171081 | 513240 | 710000 | 177500 | 532500 | 288300 | 72075 | 216225 | 16865 | 4216 | 12649 | 40000 | 10000 | 30000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 8000 | 2000 | 6000 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 149 | 37 | 112 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 716035 | 179009 | 537026 | 773200 | 193300 | 579900 | 2755000 | 688750 | 2066250 | 716035 | 179009 | 537026 | 773200 | 193300 | 579900 | 0 | 17651 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | CCI | 2011 | Q3 | Q3 - 2011 | 2246125 | 561531 | 1684594 | 832467 | 208117 | 624350 | 838000 | 209500 | 628500 | 288300 | 72075 | 216225 | 129095 | 32274 | 96821 | 135000 | 33750 | 101250 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 149 | 37 | 112 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 997988 | 249497 | 748491 | 1013200 | 253300 | 759900 | 2755000 | 688750 | 2066250 | 997988 | 249497 | 748491 | 1013200 | 253300 | 759900 | 0 | 639576 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | CCI | 2011 | Q4 | Q4 - 2011 | 2246125 | 561531 | 1684594 | 832467 | 208117 | 624350 | 837467 | 209367 | 628100 | 288300 | 72075 | 216225 | 198096 | 49524 | 148572 | 203096 | 50774 | 152322 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3329 | 832 | 2497 | 3329 | 832 | 2497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 1070169 | 267542 | 802627 | 1083592 | 270898 | 812694 | 2755000 | 688750 | 2066250 | 1070169 | 267542 | 802627 | 1083592 | 270898 | 812694 | 0 | 900740 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | CCI | 2012 | Q1 | Q1 - 2012 | 2246125 | 561531 | 1684594 | 832467 | 208117 | 624350 | 832467 | 208117 | 624350 | 288300 | 72075 | 216225 | 201195 | 50299 | 150896 | 201195 | 50299 | 150896 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3329 | 832 | 2497 | 3329 | 832 | 2497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 1073268 | 268317 | 804951 | 1073268 | 268317 | 804951 | 2755000 | 688750 | 2066250 | 1073268 | 268317 | 804951 | 1073268 | 268317 | 804951 | 0 | 900740 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | CCI | 2012 | Q2 | Q2 - 2012 | 2246125 | 561531 | 1684594 | 832467 | 208117 | 624350 | 832467 | 208117 | 624350 | 288300 | 72075 | 216225 | 201195 | 50299 | 150896 | 201195 | 50299 | 150896 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3329 | 832 | 2497 | 3329 | 832 | 2497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 1073268 | 268317 | 804951 | 1073268 | 268317 | 804951 | 2755000 | 688750 | 2066250 | 1073268 | 268317 | 804951 | 1073268 | 268317 | 804951 | 0 | 900740 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | CCI | 2012 | Q3 | Q3 - 2012 | 2246125 | 561531 | 1684594 | 832467 | 208117 | 624350 | 832467 | 208117 | 624350 | 288300 | 72075 | 216225 | 201195 | 50299 | 150896 | 201195 | 50299 | 150896 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3749 | 937 | 2812 | 3749 | 937 | 2812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 1073688 | 268422 | 805266 | 1073688 | 268422 | 805266 | 2755000 | 688750 | 2066250 | 1073688 | 268422 | 805266 | 1073688 | 268422 | 805266 | 0 | 781682 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | CCI | 2012 | Q4 | Q4 - 2012 | 2246125 | 561531 | 1684594 | 832467 | 208117 | 624350 | 832467 | 208117 | 624350 | 288300 | 72075 | 216225 | 201195 | 50299 | 150896 | 201195 | 50299 | 150896 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 47577 | 11894 | 35683 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3749 | 937 | 2812 | 3749 | 937 | 2812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 1073688 | 268422 | 805266 | 1099688 | 274922 | 824766 | 2755000 | 688750 | 2066250 | 1073688 | 268422 | 805266 | 1099688 | 274922 | 824766 | 0 | 1137204 | Level 3 EON, LLC | TRUE
NT10BIX5570038 | CCI | 2013 | Q1 | Q1 - 2013 | 2246125 | 561531 | 1684594 | 832467 | 208117 | 624350 | 832467 | 208117 | 624350 | 288300 | 72075 | 216225 | 201195 | 50299 | 150896 | 201195 | 50299 | 150896 | 80000 | 20000 | 60000 | 61696 | 15424 | 46272 | 61696 | 15424 | 46272 | 19950 | 4988 | 14962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3749 | 937 | 2812 | 3749 | 937 | 2812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118125 | 29531 | 88594 | 14700 | 3675 | 11025 | 14700 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755000 | 688750 | 2066250 | 1113807 | 278452 | 835355 | 1113807 | 278452 | 835355 | 2755000 | 688750 | 2066250 | 1113807 | 278452 | 835355 | 1113807 | 278452 | 835355 | 0 | 1268539 | Level 3 EON, LLC | TRUE
NT10BIX5570039 | CCI | 2010 | Q3 | Q3 - 2010 | 6725161 | 0 | 6725161 | 4554 | 0 | 4554 | 4554 | 0 | 4554 | 30625132 | 6920000 | 23705132 | 282477 | 0 | 282477 | 494077 | 27600 | 466477 | 919300 | 419300 | 500000 | 649881 | 386185 | 263696 | 813756 | 407560 | 406196 | 750000 | 750000 | 0 | 0 | 0 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286600 | 0 | 286600 | 0 | 0 | 0 | 0 | 0 | 0 | 755200 | 0 | 755200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 936912 | 386185 | 550727 | 2062387 | 1185160 | 877227 | 40161393 | 8089300 | 32072093 | 936912 | 386185 | 550727 | 2062387 | 1185160 | 877227 | 0 | 0 | OpenCape Corporation | TRUE
NT10BIX5570039 | CCI | 2010 | Q4 | Q4 - 2010 | 6725161 | 0 | 6725161 | 4555 | 0 | 4555 | 0 | 0 | 0 | 30625132 | 6920000 | 23705132 | 228797 | 0 | 148547 | 1300000 | 150000 | 1150000 | 919300 | 419300 | 500000 | 829065 | 339300 | 442880 | 919300 | 419300 | 500000 | 750000 | 750000 | 0 | 0 | 0 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286600 | 0 | 286600 | 215640 | 0 | 215640 | 286600 | 0 | 286600 | 755200 | 0 | 755200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 1278057 | 339300 | 811622 | 3255900 | 1319300 | 1936600 | 40161393 | 8089300 | 32072093 | 1278057 | 339300 | 811622 | 3255900 | 1319300 | 1936600 | 127133 | 127133 | OpenCape Corporation | TRUE
NT10BIX5570039 | CCI | 2011 | Q1 | Q1 - 2011 | 11336564 | 0 | 11336564 | 135196 | 0 | 135196 | 250000 | 0 | 250000 | 24364298 | 6920000 | 17444298 | 1639150 | 25882 | 1613268 | 4600000 | 467000 | 4133000 | 1280532 | 419300 | 861232 | 873585 | 339300 | 534285 | 1110000 | 416184 | 694000 | 750000 | 750000 | 0 | 4200 | 4200 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 0 | 1515885 | 315696 | 0 | 315696 | 700000 | 0 | 700000 | 814114 | 0 | 814114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 2967827 | 369382 | 2598445 | 7410000 | 1633184 | 5777000 | 40161393 | 8089300 | 32072093 | 2967827 | 369382 | 2598445 | 7410000 | 1633184 | 5777000 | 5000000 | 218748 | OpenCape Corporation | TRUE
NT10BIX5570039 | CCI | 2011 | Q2 | Q2 - 2011 | 11336564 | 0 | 11336564 | 352931 | 43547 | 309384 | 1000000 | 43457 | 956543 | 24364298 | 6920000 | 17444298 | 3038204 | 648259 | 2389945 | 6000000 | 1000000 | 5000000 | 1280532 | 419300 | 861232 | 1057284 | 416184 | 641100 | 1131676 | 416184 | 715492 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 0 | 1515885 | 881077 | 264633 | 616444 | 1181077 | 264633 | 916444 | 814114 | 0 | 814114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 6079496 | 2122623 | 3956873 | 10112753 | 2474274 | 7638479 | 40161393 | 8089300 | 32072093 | 6079496 | 2122623 | 3956873 | 10112753 | 2474274 | 7638479 | 5000000 | 555413 | OpenCape Corporation | TRUE
NT10BIX5570039 | CCI | 2011 | Q3 | Q3 - 2011 | 11336564 | 2300000 | 9036564 | 680187 | 43547 | 636640 | 4000000 | 750000 | 3250000 | 24364298 | 4110000 | 20254298 | 3633645 | 869070 | 2764575 | 5000000 | 1000000 | 4000000 | 1280532 | 419300 | 861232 | 1146158 | 416191 | 729967 | 1216000 | 416191 | 799809 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 325000 | 1190885 | 1165838 | 374135 | 791703 | 1300000 | 395046 | 904954 | 814114 | 165000 | 649114 | 9000 | 0 | 9000 | 50000 | 9000 | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 360 | 360 | 0 | 100000 | 20000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 7385188 | 2453303 | 4931885 | 12416000 | 3340237 | 9075763 | 40161393 | 8089300 | 32072093 | 7385188 | 2453303 | 4931885 | 12416000 | 3340237 | 9075763 | 5000000 | 649913 | OpenCape Corporation | TRUE
NT10BIX5570039 | CCI | 2011 | Q4 | Q4 - 2011 | 11336564 | 2300000 | 9036564 | 2026835 | 63547 | 1963288 | 6500000 | 500000 | 6000000 | 24364298 | 4110000 | 20254298 | 4591699 | 1209659 | 3382040 | 8500000 | 2000000 | 6500000 | 1280532 | 419300 | 861232 | 1238555 | 416191 | 822364 | 1325000 | 416191 | 908809 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 325000 | 1190885 | 1404408 | 467692 | 936716 | 1450000 | 395046 | 1054954 | 814114 | 165000 | 649114 | 35000 | 0 | 35000 | 70000 | 9000 | 61000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 48360 | 48360 | 0 | 70000 | 48360 | 21640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 10094857 | 2955449 | 7139408 | 18665000 | 4118597 | 14546403 | 40161393 | 8089300 | 32072093 | 10094857 | 2955449 | 7139408 | 18665000 | 4118597 | 14546403 | 5000000 | 1069774 | OpenCape Corporation | TRUE
NT10BIX5570039 | CCI | 2012 | Q1 | Q1 - 2012 | 11336564 | 2300000 | 9036564 | 6465505 | 347207 | 6118298 | 8000000 | 800000 | 7200000 | 24364298 | 4110000 | 20254298 | 8526788 | 2106217 | 6420571 | 13000000 | 2500000 | 10500000 | 1280532 | 419300 | 861232 | 1360062 | 416184 | 943878 | 1530000 | 416191 | 1113809 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 325000 | 1190885 | 1472158 | 520925 | 951233 | 1572000 | 495000 | 1077000 | 814114 | 165000 | 649114 | 72000 | 9000 | 63000 | 125000 | 40000 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 88484 | 85654 | 2830 | 98000 | 85654 | 12346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 18734997 | 4235187 | 14499810 | 25075000 | 5086845 | 19988155 | 40161393 | 8089300 | 32072093 | 18734997 | 4235187 | 14499810 | 25075000 | 5086845 | 19988155 | 5000000 | 1827337 | OpenCape Corporation | TRUE
NT10BIX5570039 | CCI | 2012 | Q2 | Q2 - 2012 | 11336564 | 2300000 | 9036564 | 7909996 | 347207 | 7562789 | 10000000 | 1250000 | 8750000 | 24364298 | 4110000 | 20254298 | 11805115 | 2782290 | 9022825 | 16500000 | 3150000 | 13350000 | 1280532 | 419300 | 861232 | 1418622 | 416184 | 1002438 | 1530000 | 416191 | 1113809 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 325000 | 1190885 | 1604743 | 565662 | 1039081 | 1700000 | 495000 | 1205000 | 814114 | 165000 | 649114 | 146500 | 9000 | 137500 | 200000 | 9000 | 191000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 88483 | 85653 | 2830 | 88485 | 85653 | 2832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 23723459 | 4955996 | 18767463 | 30768485 | 6155844 | 24612641 | 40161393 | 8089300 | 32072093 | 23723459 | 4955996 | 18767463 | 30768485 | 6155844 | 24612641 | 5000000 | 2646218 | OpenCape Corporation | TRUE
NT10BIX5570039 | CCI | 2012 | Q3 | Q3 - 2012 | 11336564 | 2300000 | 9036564 | 8355565 | 716057 | 7639508 | 10500000 | 1500000 | 9000000 | 24364298 | 4110000 | 20254298 | 13776050 | 2870065 | 10872382 | 18000000 | 3150000 | 14850000 | 1280532 | 419300 | 861232 | 1728532 | 633144 | 1095389 | 1850000 | 633144 | 1216856 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 325000 | 1190885 | 1619950 | 580869 | 1039082 | 1887000 | 580869 | 1306131 | 814114 | 165000 | 649114 | 182000 | 9000 | 173000 | 600000 | 165000 | 435000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 88483 | 85653 | 2830 | 88485 | 85653 | 2832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 26500580 | 5644788 | 20822191 | 33675485 | 6864666 | 26810819 | 40161393 | 8089300 | 32072093 | 26500580 | 5644788 | 20822191 | 33675485 | 6864666 | 26810819 | 5000000 | 3064950 | OpenCape Corporation | TRUE
NT10BIX5570039 | CCI | 2012 | Q4 | Q4 - 2012 | 11336564 | 2300000 | 9036564 | 9448179 | 1177397 | 8270782 | 10994012 | 1499649 | 9494363 | 24364298 | 4110000 | 20254298 | 16955664 | 2962569 | 13993096 | 20036545 | 3562569 | 16473976 | 1280532 | 419300 | 861232 | 1790311 | 637274 | 1153037 | 1955311 | 637274 | 1318037 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515885 | 325000 | 1190885 | 1686950 | 580869 | 1106082 | 1941760 | 610869 | 1330891 | 814114 | 165000 | 649114 | 250704 | 9954 | 240750 | 250704 | 9954 | 240750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 88835 | 86005 | 2830 | 88835 | 86005 | 2830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 30970643 | 6204068 | 24766577 | 36017167 | 7156320 | 28860847 | 40161393 | 8089300 | 32072093 | 30970643 | 6204068 | 24766577 | 36017167 | 7156320 | 28860847 | 5000000 | 3574636 | OpenCape Corporation | TRUE
NT10BIX5570039 | CCI | 2013 | Q1 | Q1 - 2013 | 11200689 | 2000000 | 9200689 | 10052640 | 1627093 | 8425547 | 11114288 | 1912999 | 9201289 | 22939955 | 3906449 | 19033506 | 18646565 | 3129040 | 15517525 | 22682955 | 3906449 | 18776506 | 2228962 | 616188 | 1612773 | 1912709 | 616189 | 1296520 | 2070334 | 616189 | 1454145 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887204 | 565662 | 1321542 | 1719103 | 580870 | 1138233 | 1917618 | 596077 | 1321541 | 1066100 | 165000 | 901100 | 342954 | 9954 | 333000 | 911054 | 59954 | 851100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88483 | 86000 | 2483 | 88835 | 86005 | 2830 | 88835 | 86005 | 2830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089299 | 32072093 | 33512806 | 6799151 | 26713655 | 39535084 | 7927673 | 31607411 | 40161393 | 8089299 | 32072093 | 33512806 | 6799151 | 26713655 | 39535084 | 7927673 | 31607411 | 5000000 | 3877897 | OpenCape Corporation | TRUE
NT10BIX5570039 | CCI | 2013 | Q2 | Q2 - 2013 | 11200689 | 2000000 | 9200689 | 10570968 | 1720692 | 8850276 | 11200689 | 2000000 | 9200689 | 22939955 | 3906449 | 19033506 | 20367755 | 3226478 | 17141277 | 22467158 | 3684004 | 18783154 | 2228962 | 616188 | 1612773 | 2007994 | 616583 | 1391411 | 2078966 | 616583 | 1462383 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887204 | 565662 | 1321542 | 1766628 | 587707 | 1178921 | 1909249 | 587707 | 1321542 | 1066100 | 165000 | 901100 | 692319 | 80149 | 612170 | 1066100 | 165000 | 901100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88483 | 86000 | 2483 | 88835 | 86005 | 2830 | 88835 | 86005 | 2830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089299 | 32072093 | 36244499 | 7067614 | 29176885 | 39560997 | 7889299 | 31671698 | 40161393 | 8089299 | 32072093 | 36244499 | 7067614 | 29176885 | 39560997 | 7889299 | 31671698 | 5000000 | 4219398 | OpenCape Corporation | TRUE
NT10BIX5570039 | CCI | 2013 | Q3 | Q3 - 2013 | 11200689 | 2000000 | 9200689 | 11012081 | 1786449 | 9225632 | 11225632 | 2000000 | 9225632 | 22939955 | 3906449 | 19033506 | 21540211 | 3296903 | 18243308 | 22915012 | 3906449 | 19008563 | 2228962 | 616189 | 1612773 | 2083393 | 616583 | 1466810 | 2229356 | 616583 | 1612773 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887204 | 565662 | 1321542 | 1807053 | 597086 | 1209967 | 1918628 | 597086 | 1321542 | 1066100 | 165000 | 901100 | 800002 | 107346 | 692656 | 1033930 | 133177 | 900753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88483 | 86000 | 2483 | 88835 | 86005 | 2830 | 88835 | 86005 | 2830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 38081575 | 7240372 | 30841203 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 38081575 | 7240372 | 30841203 | 40161393 | 8089300 | 32072093 | 0 | 0 | OpenCape Corporation | TRUE
NT10BIX5570039 | CCI | 2013 | Q4 | Q4 - 2013 | 11200689 | 2000000 | 9200689 | 11192814 | 1786930 | 9405884 | 11192814 | 1786930 | 9405884 | 22939955 | 3906449 | 19033506 | 22998163 | 3955570 | 19042594 | 22998163 | 3955570 | 19042594 | 2228962 | 616189 | 1612773 | 2262644 | 673910 | 1588734 | 2262644 | 673910 | 1588734 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887204 | 565662 | 1321542 | 1881516 | 597974 | 1283541 | 1881516 | 597974 | 1283541 | 1066100 | 165000 | 901100 | 987421 | 238911 | 748510 | 987421 | 238911 | 748510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88483 | 86000 | 2483 | 88835 | 86005 | 2830 | 88835 | 86005 | 2830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 40161393 | 8089300 | 32072093 | 0 | 0 | OpenCape Corporation | TRUE
NT10BIX5570040 | CCI | 2010 | Q3 | Q3 - 2010 | 1903080 | 475770 | 1427310 | 0 | 0 | 0 | 800000 | 600000 | 200000 | 178100 | 44525 | 133575 | 0 | 0 | 0 | 95000 | 23750 | 71250 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 6500 | 1625 | 4875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 2000 | 500 | 1500 | 28000 | 7000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2221160 | 555290 | 1665870 | 2000 | 500 | 1500 | 933500 | 633375 | 300125 | 2221160 | 555290 | 1665870 | 2000 | 500 | 1500 | 933500 | 633375 | 300125 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | CCI | 2010 | Q4 | Q4 - 2010 | 1903080 | 475770 | 1427310 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 178100 | 44525 | 133575 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 6500 | 1625 | 4875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 8000 | 2000 | 6000 | 28000 | 7000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2221160 | 555290 | 1665870 | 8000 | 2000 | 6000 | 198500 | 49625 | 148875 | 2221160 | 555290 | 1665870 | 8000 | 2000 | 6000 | 198500 | 49625 | 148875 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | CCI | 2011 | Q1 | Q1 - 2011 | 1585000 | 396250 | 1188750 | 393835 | 98459 | 295376 | 400000 | 100000 | 300000 | 178100 | 44525 | 133575 | 0 | 0 | 0 | 40000 | 10000 | 30000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 8000 | 2000 | 6000 | 8000 | 2000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 401835 | 100459 | 301376 | 452000 | 113000 | 339000 | 1903080 | 475770 | 1427310 | 401835 | 100459 | 301376 | 452000 | 113000 | 339000 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | CCI | 2011 | Q2 | Q2 - 2011 | 1585000 | 396250 | 1188750 | 559471 | 139868 | 419603 | 650000 | 162500 | 487500 | 178100 | 44525 | 133575 | 0 | 0 | 0 | 50000 | 12500 | 37500 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 85 | 21 | 64 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 8000 | 2000 | 6000 | 20000 | 5000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 567556 | 141889 | 425667 | 724500 | 181125 | 543375 | 1903080 | 475770 | 1427310 | 567556 | 141889 | 425667 | 724500 | 181125 | 543375 | 0 | 13368 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | CCI | 2011 | Q3 | Q3 - 2011 | 1585000 | 396250 | 1188750 | 595493 | 148873 | 446620 | 600000 | 150000 | 450000 | 178100 | 44525 | 133575 | 8264 | 2066 | 6197 | 70000 | 17500 | 52500 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 18750 | 6250 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 85 | 21 | 64 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 633299 | 158324 | 474974 | 703380 | 188345 | 515035 | 1903080 | 475770 | 1427310 | 633299 | 158324 | 474974 | 703380 | 188345 | 515035 | 0 | 10331 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | CCI | 2011 | Q4 | Q4 - 2011 | 1585000 | 396250 | 1188750 | 595494 | 148874 | 446620 | 600494 | 150124 | 450370 | 178100 | 44525 | 133575 | 72457 | 18115 | 54343 | 77457 | 19364 | 58093 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 698013 | 174504 | 523510 | 711436 | 177859 | 533577 | 1903080 | 475770 | 1427310 | 698013 | 174504 | 523510 | 711436 | 177859 | 533577 | 0 | 17949 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | CCI | 2012 | Q1 | Q1 - 2012 | 1585000 | 396250 | 1188750 | 595493 | 148873 | 446620 | 595493 | 148873 | 446620 | 178100 | 44525 | 133575 | 77815 | 19454 | 58361 | 77815 | 19454 | 58361 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 703370 | 175842 | 527528 | 703370 | 175842 | 527528 | 1903080 | 475770 | 1427310 | 703370 | 175842 | 527528 | 703370 | 175842 | 527528 | 0 | 26803 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | CCI | 2012 | Q2 | Q2 - 2012 | 1585000 | 396250 | 1188750 | 595493 | 148873 | 446620 | 595493 | 148873 | 446620 | 178100 | 44525 | 133575 | 77815 | 19454 | 58361 | 77815 | 19454 | 58361 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 703370 | 175842 | 527528 | 703370 | 175842 | 527528 | 1903080 | 475770 | 1427310 | 703370 | 175842 | 527528 | 703370 | 175842 | 527528 | 0 | 35672 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | CCI | 2012 | Q3 | Q3 - 2012 | 1585000 | 396250 | 1188750 | 595493 | 148873 | 446620 | 595493 | 148873 | 446620 | 178100 | 44525 | 133575 | 77815 | 19454 | 58361 | 77815 | 19454 | 58361 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 703650 | 175912 | 527738 | 703650 | 175912 | 527738 | 1903080 | 475770 | 1427310 | 703650 | 175912 | 527738 | 703650 | 175912 | 527738 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | CCI | 2012 | Q4 | Q4 - 2012 | 1585000 | 396250 | 1188750 | 595493 | 148873 | 446620 | 595493 | 148873 | 446620 | 178100 | 44525 | 133575 | 77815 | 19454 | 58361 | 77815 | 19454 | 58361 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 47577 | 11894 | 35683 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 703650 | 175912 | 527738 | 729650 | 182412 | 547238 | 1903080 | 475770 | 1427310 | 703650 | 175912 | 527738 | 729650 | 182412 | 547238 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570040 | CCI | 2013 | Q1 | Q1 - 2013 | 1585000 | 396250 | 1188750 | 595493 | 148873 | 446620 | 595493 | 148873 | 446620 | 178100 | 44525 | 133575 | 77815 | 19454 | 58361 | 77815 | 19454 | 58361 | 80000 | 20000 | 60000 | 55859 | 13965 | 41894 | 55859 | 13965 | 41894 | 12480 | 3120 | 9360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1903080 | 475770 | 1427310 | 737932 | 184483 | 553449 | 737932 | 184483 | 553449 | 1903080 | 475770 | 1427310 | 737932 | 184483 | 553449 | 737932 | 184483 | 553449 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | CCI | 2010 | Q3 | Q3 - 2010 | 5256000 | 1314000 | 3942000 | 0 | 0 | 0 | 750000 | 187500 | 562500 | 662200 | 165550 | 496650 | 0 | 0 | 0 | 400000 | 100000 | 300000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 8000 | 2000 | 6000 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 12000 | 3000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47813 | 143438 | 32500 | 8125 | 24375 | 120000 | 30000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559263 | 4677789 | 32500 | 8125 | 24375 | 1290000 | 322500 | 967500 | 6237051 | 1559263 | 4677789 | 32500 | 8125 | 24375 | 1290000 | 322500 | 967500 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | CCI | 2010 | Q4 | Q4 - 2010 | 5256000 | 1314000 | 3942000 | 0 | 0 | 0 | 100000 | 25000 | 75000 | 662200 | 165550 | 496650 | 0 | 0 | 0 | 100000 | 25000 | 75000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 8000 | 2000 | 6000 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 12000 | 3000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 34000 | 8500 | 25500 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 34000 | 8500 | 25500 | 300000 | 75000 | 225000 | 6237051 | 1559262 | 4677789 | 34000 | 8500 | 25500 | 300000 | 75000 | 225000 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | CCI | 2011 | Q1 | Q1 - 2011 | 5256000 | 1314000 | 3942000 | 655403 | 170226 | 485177 | 700000 | 175000 | 525000 | 662200 | 165550 | 496650 | 0 | 0 | 0 | 235000 | 58750 | 176250 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47813 | 143437 | 34000 | 8500 | 25500 | 34000 | 8500 | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559263 | 4677788 | 689403 | 178726 | 510677 | 973000 | 243250 | 729750 | 6237051 | 1559263 | 4677788 | 689403 | 178726 | 510677 | 973000 | 243250 | 729750 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | CCI | 2011 | Q2 | Q2 - 2011 | 5256000 | 1314000 | 3942000 | 2074314 | 518578 | 1555735 | 2200000 | 550000 | 1650000 | 662200 | 165550 | 496650 | 15243 | 3811 | 11432 | 150000 | 37500 | 112500 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 362 | 91 | 271 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 34000 | 8500 | 25500 | 70000 | 17500 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 2123919 | 530980 | 1592938 | 2424500 | 606125 | 1818375 | 6237051 | 1559262 | 4677789 | 2123919 | 530980 | 1592938 | 2424500 | 606125 | 1818375 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | CCI | 2011 | Q3 | Q3 - 2011 | 5256000 | 1314000 | 3942000 | 2151173 | 537793 | 1613380 | 2155000 | 538750 | 1616250 | 662200 | 165550 | 496650 | 86394 | 21598 | 64796 | 550000 | 137500 | 412500 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 362 | 91 | 271 | 400 | 100 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 33970 | 8492 | 25478 | 33970 | 8492 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 2293476 | 573368 | 1720108 | 2764370 | 691092 | 2073278 | 6237051 | 1559262 | 4677789 | 2293476 | 573368 | 1720108 | 2764370 | 691092 | 2073278 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | CCI | 2011 | Q4 | Q4 - 2011 | 5256000 | 1314000 | 3942000 | 2320392 | 580098 | 1740294 | 2325992 | 581498 | 1744494 | 662200 | 165550 | 496650 | 516699 | 129175 | 387524 | 531699 | 132925 | 398774 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 2572 | 643 | 1929 | 2572 | 643 | 1929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 33970 | 8492 | 25478 | 33970 | 8492 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 2895210 | 723802 | 2171408 | 2919233 | 729808 | 2189425 | 6237051 | 1559262 | 4677789 | 2895210 | 723802 | 2171408 | 2919233 | 729808 | 2189425 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | CCI | 2012 | Q1 | Q1 - 2012 | 5256000 | 1314000 | 3942000 | 2320391 | 580097 | 1740294 | 2320391 | 580097 | 1740294 | 662200 | 165550 | 496650 | 575079 | 143770 | 431309 | 575079 | 143770 | 431309 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 2572 | 643 | 1929 | 2572 | 643 | 1929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 33970 | 8492 | 25478 | 33970 | 8492 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 2953589 | 738396 | 2215193 | 2953589 | 738396 | 2215193 | 6237051 | 1559262 | 4677789 | 2953589 | 738396 | 2215193 | 2953589 | 738396 | 2215193 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | CCI | 2012 | Q2 | Q2 - 2012 | 5256000 | 1314000 | 3942000 | 2320391 | 580097 | 1740294 | 2320391 | 580097 | 1740294 | 662200 | 165550 | 496650 | 575079 | 143770 | 431309 | 575079 | 143770 | 431309 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 2572 | 643 | 1929 | 2572 | 643 | 1929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 33970 | 8492 | 25478 | 33970 | 8492 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 2953589 | 738396 | 2215193 | 2953589 | 738396 | 2215193 | 6237051 | 1559262 | 4677789 | 2953589 | 738396 | 2215193 | 2953589 | 738396 | 2215193 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | CCI | 2012 | Q3 | Q3 - 2012 | 5256000 | 1314000 | 3942000 | 2320391 | 580097 | 1740294 | 2320391 | 580097 | 1740294 | 662200 | 165550 | 496650 | 575079 | 143770 | 431309 | 575079 | 143770 | 431309 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3552 | 888 | 2664 | 3552 | 888 | 2664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 33970 | 8492 | 25478 | 33970 | 8492 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 2954569 | 738641 | 2215928 | 2954569 | 738641 | 2215928 | 6237051 | 1559262 | 4677789 | 2954569 | 738641 | 2215928 | 2954569 | 738641 | 2215928 | 0 | 16137 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | CCI | 2012 | Q4 | Q4 - 2012 | 5256000 | 1314000 | 3942000 | 2320391 | 580097 | 1740294 | 2320391 | 580097 | 1740294 | 662200 | 165550 | 496650 | 575079 | 143770 | 431309 | 575079 | 143770 | 431309 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 47577 | 11894 | 35683 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3552 | 888 | 2664 | 3552 | 888 | 2664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 33970 | 8492 | 25478 | 33970 | 8492 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 2954569 | 738641 | 2215928 | 2980569 | 745141 | 2235428 | 6237051 | 1559262 | 4677789 | 2954569 | 738641 | 2215928 | 2980569 | 745141 | 2235428 | 0 | 25936 | Level 3 EON, LLC | TRUE
NT10BIX5570041 | CCI | 2013 | Q1 | Q1 - 2013 | 5256000 | 1314000 | 3942000 | 2320391 | 580097 | 1740294 | 2320391 | 580097 | 1740294 | 662200 | 165550 | 496650 | 575079 | 143770 | 431309 | 575079 | 143770 | 431309 | 80000 | 20000 | 60000 | 81153 | 20288 | 60865 | 81153 | 20288 | 60865 | 45101 | 11275 | 33826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3552 | 888 | 2664 | 3552 | 888 | 2664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191250 | 47812 | 143438 | 33970 | 8492 | 25478 | 33970 | 8492 | 25478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6237051 | 1559262 | 4677789 | 3014145 | 753535 | 2260610 | 3014145 | 753535 | 2260610 | 6237051 | 1559262 | 4677789 | 3014145 | 753535 | 2260610 | 3014145 | 753535 | 2260610 | 0 | 14309 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | CCI | 2010 | Q3 | Q3 - 2010 | 3671875 | 917969 | 2753906 | 0 | 0 | 0 | 800000 | 200000 | 600000 | 474900 | 118725 | 356175 | 0 | 0 | 0 | 240000 | 60000 | 180000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 10000 | 2500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30938 | 92813 | 5500 | 1375 | 4125 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097332 | 3291994 | 5500 | 1375 | 4125 | 1134000 | 283500 | 850500 | 4389325 | 1097332 | 3291994 | 5500 | 1375 | 4125 | 1134000 | 283500 | 850500 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | CCI | 2010 | Q4 | Q4 - 2010 | 3671875 | 917969 | 2753906 | 0 | 0 | 0 | 0 | 0 | 0 | 474900 | 118725 | 356175 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 10000 | 2500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30938 | 92812 | 22000 | 5500 | 16500 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097332 | 3291993 | 22000 | 5500 | 16500 | 174000 | 43500 | 130500 | 4389325 | 1097332 | 3291993 | 22000 | 5500 | 16500 | 174000 | 43500 | 130500 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | CCI | 2011 | Q1 | Q1 - 2011 | 3671875 | 917969 | 2753906 | 549441 | 137360 | 412081 | 650000 | 162500 | 487500 | 474900 | 118725 | 356175 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 22000 | 5500 | 16500 | 22000 | 5500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 571441 | 142860 | 428581 | 756000 | 189000 | 567000 | 4389325 | 1097331 | 3291994 | 571441 | 142860 | 428581 | 756000 | 189000 | 567000 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | CCI | 2011 | Q2 | Q2 - 2011 | 3671875 | 917969 | 2753906 | 734388 | 183597 | 550791 | 820000 | 205000 | 615000 | 474900 | 118725 | 356175 | 66730 | 16683 | 50047 | 125000 | 31250 | 93750 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 234 | 59 | 175 | 500 | 125 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 22000 | 5500 | 16500 | 22000 | 5500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 823352 | 205839 | 617513 | 971500 | 242875 | 728625 | 4389325 | 1097331 | 3291994 | 823352 | 205839 | 617513 | 971500 | 242875 | 728625 | 0 | 82327 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | CCI | 2011 | Q3 | Q3 - 2011 | 3671875 | 917969 | 2753906 | 1022329 | 255582 | 766747 | 1050000 | 262500 | 787500 | 474900 | 118725 | 356175 | 192969 | 48242 | 144727 | 200000 | 50000 | 150000 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 234 | 59 | 175 | 400 | 100 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 24870 | 6218 | 18652 | 24870 | 6218 | 18652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 1261979 | 315495 | 946484 | 1300270 | 325068 | 975202 | 4389325 | 1097331 | 3291994 | 1261979 | 315495 | 946484 | 1300270 | 325068 | 975202 | 0 | 65498 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | CCI | 2011 | Q4 | Q4 - 2011 | 3671875 | 917969 | 2753906 | 1031711 | 257928 | 773783 | 1036711 | 259178 | 777533 | 474900 | 118725 | 356175 | 312750 | 78188 | 234562 | 317750 | 79438 | 238312 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3184 | 796 | 2388 | 3184 | 796 | 2388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 24870 | 6218 | 18652 | 24870 | 6218 | 18652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 1394092 | 348524 | 1045568 | 1407515 | 351880 | 1055635 | 4389325 | 1097331 | 3291994 | 1394092 | 348524 | 1045568 | 1407515 | 351880 | 1055635 | 0 | 105166 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | CCI | 2012 | Q1 | Q1 - 2012 | 3671875 | 917969 | 2753906 | 1034007 | 258502 | 775505 | 1034007 | 258502 | 775505 | 474900 | 118725 | 356175 | 330049 | 82512 | 247537 | 330049 | 82512 | 247537 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3184 | 796 | 2388 | 3184 | 796 | 2388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 24870 | 6218 | 18652 | 24870 | 6218 | 18652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 1413687 | 353422 | 1060265 | 1413687 | 353422 | 1060265 | 4389325 | 1097331 | 3291994 | 1413687 | 353422 | 1060265 | 1413687 | 353422 | 1060265 | 0 | 157976 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | CCI | 2012 | Q2 | Q2 - 2012 | 3671875 | 917969 | 2753906 | 1034007 | 258502 | 775505 | 1034007 | 258502 | 775505 | 474900 | 118725 | 356175 | 330049 | 82512 | 247537 | 330049 | 82512 | 247537 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3184 | 796 | 2388 | 3184 | 796 | 2388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 24870 | 6218 | 18652 | 24870 | 6218 | 18652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 1413687 | 353422 | 1060265 | 1413687 | 353422 | 1060265 | 4389325 | 1097331 | 3291994 | 1413687 | 353422 | 1060265 | 1413687 | 353422 | 1060265 | 0 | 201061 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | CCI | 2012 | Q3 | Q3 - 2012 | 3671875 | 917969 | 2753906 | 1034007 | 258502 | 775505 | 1034007 | 258502 | 775505 | 474900 | 118725 | 356175 | 330049 | 82512 | 247537 | 330049 | 82512 | 247537 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3744 | 936 | 2808 | 3744 | 936 | 2808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 24870 | 6218 | 18652 | 24870 | 6218 | 18652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 1414247 | 353562 | 1060685 | 1414247 | 353562 | 1060685 | 4389325 | 1097331 | 3291994 | 1414247 | 353562 | 1060685 | 1414247 | 353562 | 1060685 | 0 | 30028 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | CCI | 2012 | Q4 | Q4 - 2012 | 3671875 | 917969 | 2753906 | 1034007 | 258502 | 775505 | 1034007 | 258502 | 775505 | 474900 | 118725 | 356175 | 330049 | 82512 | 247537 | 330049 | 82512 | 247537 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 47577 | 11894 | 35683 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3744 | 936 | 2808 | 3744 | 936 | 2808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 24870 | 6218 | 18652 | 24870 | 6218 | 18652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 1414247 | 353562 | 1060685 | 1440247 | 360062 | 1080185 | 4389325 | 1097331 | 3291994 | 1414247 | 353562 | 1060685 | 1440247 | 360062 | 1080185 | 0 | 69695 | Level 3 EON, LLC | TRUE
NT10BIX5570042 | CCI | 2013 | Q1 | Q1 - 2013 | 3671875 | 917969 | 2753906 | 1034007 | 258502 | 775505 | 1034007 | 258502 | 775505 | 474900 | 118725 | 356175 | 330049 | 82512 | 247537 | 330049 | 82512 | 247537 | 80000 | 20000 | 60000 | 69478 | 17370 | 52109 | 69478 | 17370 | 52109 | 36300 | 9075 | 27225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 3744 | 936 | 2808 | 3744 | 936 | 2808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123750 | 30937 | 92813 | 24870 | 6218 | 18652 | 24870 | 6218 | 18652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389325 | 1097331 | 3291994 | 1462148 | 365538 | 1096611 | 1462148 | 365538 | 1096611 | 4389325 | 1097331 | 3291994 | 1462148 | 365538 | 1096611 | 1462148 | 365538 | 1096611 | 0 | 73119 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | CCI | 2010 | Q3 | Q3 - 2010 | 1047125 | 261781 | 785343 | 0 | 0 | 0 | 480000 | 120000 | 360000 | 145800 | 36450 | 109350 | 0 | 0 | 0 | 120000 | 30000 | 90000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 3200 | 800 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 2000 | 500 | 1500 | 32000 | 8000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998418 | 2000 | 500 | 1500 | 639200 | 159800 | 479400 | 1331225 | 332806 | 998418 | 2000 | 500 | 1500 | 639200 | 159800 | 479400 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | CCI | 2010 | Q4 | Q4 - 2010 | 1047125 | 261781 | 785343 | 25973 | 6493 | 19480 | 120000 | 30000 | 90000 | 145800 | 36450 | 109350 | 0 | 0 | 0 | 80000 | 20000 | 60000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 3200 | 800 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 8000 | 2000 | 6000 | 32000 | 8000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998418 | 33973 | 8493 | 25480 | 239200 | 59800 | 179400 | 1331225 | 332806 | 998418 | 33973 | 8493 | 25480 | 239200 | 59800 | 179400 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | CCI | 2011 | Q1 | Q1 - 2011 | 1047125 | 261781 | 785344 | 247391 | 61848 | 185543 | 275000 | 69000 | 206000 | 145800 | 36450 | 109350 | 0 | 0 | 0 | 40000 | 10000 | 30000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 3200 | 800 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 8000 | 2000 | 6000 | 8000 | 2000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 255391 | 63848 | 191543 | 330200 | 82800 | 247400 | 1331225 | 332806 | 998419 | 255391 | 63848 | 191543 | 330200 | 82800 | 247400 | 0 | 0 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | CCI | 2011 | Q2 | Q2 - 2011 | 1047125 | 261781 | 785344 | 359376 | 89844 | 269532 | 390000 | 97500 | 292500 | 145800 | 36450 | 109350 | 32207 | 8052 | 24155 | 80000 | 20000 | 60000 | 80000 | 20000 | 60000 | 0 | 0 | 0 | 4000 | 1000 | 3000 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 3200 | 800 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 85 | 21 | 64 | 1000 | 250 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 8000 | 2000 | 6000 | 30000 | 7500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 399668 | 99917 | 299751 | 508200 | 127050 | 381150 | 1331225 | 332806 | 998419 | 399668 | 99917 | 299751 | 508200 | 127050 | 381150 | 0 | 55301 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | CCI | 2011 | Q3 | Q3 - 2011 | 1047125 | 261781 | 785344 | 424688 | 106172 | 318516 | 424688 | 106172 | 318516 | 145800 | 36450 | 109350 | 79089 | 19772 | 59317 | 85000 | 21250 | 63750 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 85 | 21 | 64 | 400 | 100 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 533319 | 133329 | 399990 | 542968 | 135742 | 407226 | 1331225 | 332806 | 998419 | 533319 | 133329 | 399990 | 542968 | 135742 | 407226 | 0 | 38376 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | CCI | 2011 | Q4 | Q4 - 2011 | 1047125 | 261781 | 785344 | 434689 | 108672 | 326017 | 439689 | 109922 | 329767 | 145800 | 36450 | 109350 | 118848 | 29712 | 89136 | 123848 | 30962 | 92886 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 25000 | 6250 | 18750 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 583599 | 145899 | 437700 | 597022 | 149255 | 447767 | 1331225 | 332806 | 998419 | 583599 | 145899 | 437700 | 597022 | 149255 | 447767 | 0 | 54511 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | CCI | 2012 | Q1 | Q1 - 2012 | 1047125 | 261781 | 785344 | 434688 | 108672 | 326016 | 434688 | 108672 | 326016 | 145800 | 36450 | 109350 | 120619 | 30155 | 90464 | 120619 | 30155 | 90464 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 585369 | 146342 | 439027 | 585369 | 146342 | 439027 | 1331225 | 332806 | 998419 | 585369 | 146342 | 439027 | 585369 | 146342 | 439027 | 0 | 70646 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | CCI | 2012 | Q2 | Q2 - 2012 | 1047125 | 261781 | 785344 | 434688 | 108672 | 326016 | 434688 | 108672 | 326016 | 145800 | 36450 | 109350 | 120619 | 30155 | 90464 | 120619 | 30155 | 90464 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 605 | 151 | 454 | 605 | 151 | 454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 585369 | 146342 | 439027 | 585369 | 146342 | 439027 | 1331225 | 332806 | 998419 | 585369 | 146342 | 439027 | 585369 | 146342 | 439027 | 0 | 86806 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | CCI | 2012 | Q3 | Q3 - 2012 | 1047125 | 261781 | 785344 | 434688 | 108672 | 326016 | 434688 | 108672 | 326016 | 145800 | 36450 | 109350 | 120619 | 30155 | 90464 | 120619 | 30155 | 90464 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 21577 | 5394 | 16183 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 585649 | 146412 | 439237 | 585649 | 146412 | 439237 | 1331225 | 332806 | 998419 | 585649 | 146412 | 439237 | 585649 | 146412 | 439237 | 0 | 20414 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | CCI | 2012 | Q4 | Q4 - 2012 | 1047125 | 261781 | 785344 | 434688 | 108672 | 326016 | 434688 | 108672 | 326016 | 145800 | 36450 | 109350 | 120619 | 30155 | 90464 | 120619 | 30155 | 90464 | 80000 | 20000 | 60000 | 21577 | 5394 | 16183 | 47577 | 11894 | 35683 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 585649 | 146412 | 439237 | 611649 | 152912 | 458737 | 1331225 | 332806 | 998419 | 585649 | 146412 | 439237 | 611649 | 152912 | 458737 | 0 | 36587 | Level 3 EON, LLC | TRUE
NT10BIX5570043 | CCI | 2013 | Q1 | Q1 - 2013 | 1047125 | 261781 | 785344 | 434688 | 108672 | 326016 | 434688 | 108672 | 326016 | 145800 | 36450 | 109350 | 120619 | 30155 | 90464 | 120619 | 30155 | 90464 | 80000 | 20000 | 60000 | 55859 | 13965 | 41859 | 55859 | 13965 | 41894 | 10800 | 2700 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 625 | 1875 | 885 | 221 | 664 | 885 | 221 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 11250 | 33750 | 7880 | 1970 | 5910 | 7880 | 1970 | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1331225 | 332806 | 998419 | 619931 | 154983 | 464913 | 619931 | 154983 | 464948 | 1331225 | 332806 | 998419 | 619931 | 154983 | 464913 | 619931 | 154983 | 464948 | 0 | 33407 | Level 3 EON, LLC | TRUE
NT10BIX5570044 | CCI | 2010 | Q3 | Q3 - 2010 | 4722756 | 0 | 4722756 | 0 | 0 | 0 | 0 | 0 | 0 | 23499307 | 6852149 | 16647158 | 0 | 0 | 0 | 640000 | 225000 | 415000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254990 | 0 | 254990 | 0 | 0 | 0 | 254990 | 0 | 254990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 783992 | 0 | 783992 | 0 | 0 | 0 | 0 | 0 | 0 | 33500 | 0 | 33500 | 0 | 0 | 0 | 0 | 0 | 0 | 74880 | 0 | 74880 | 0 | 0 | 0 | 0 | 0 | 0 | 17500 | 0 | 17500 | 0 | 0 | 0 | 9000 | 0 | 9000 | 29386925 | 6852149 | 22534776 | 0 | 0 | 0 | 903990 | 225000 | 678990 | 29386925 | 6852149 | 22534776 | 0 | 0 | 0 | 903990 | 225000 | 678990 | 0 | 0 | University of Illinois | TRUE
NT10BIX5570044 | CCI | 2010 | Q4 | Q4 - 2010 | 4722756 | 0 | 4722756 | 0 | 0 | 0 | 0 | 0 | 0 | 23499307 | 6852149 | 16647158 | 144944 | 52678 | 92266 | 2144944 | 825000 | 1319944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254990 | 0 | 254990 | 0 | 0 | 0 | 254990 | 0 | 254990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 783992 | 0 | 783992 | 0 | 0 | 0 | 0 | 0 | 0 | 33500 | 0 | 33500 | 0 | 0 | 0 | 0 | 0 | 0 | 74880 | 0 | 74880 | 0 | 0 | 0 | 0 | 0 | 0 | 17500 | 0 | 17500 | 8993 | 0 | 8993 | 8993 | 0 | 8993 | 29386925 | 6852149 | 22534776 | 153937 | 52678 | 101259 | 2408927 | 825000 | 1583927 | 29386925 | 6852149 | 22534776 | 153937 | 52678 | 101259 | 2408927 | 825000 | 1583927 | 0 | 0 | University of Illinois | TRUE
NT10BIX5570044 | CCI | 2011 | Q1 | Q1 - 2011 | 4722756 | 0 | 4722756 | 0 | 0 | 0 | 2400000 | 0 | 2400000 | 23499307 | 6852149 | 16647158 | 287221 | 152548 | 134672 | 500000 | 300000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254990 | 0 | 254990 | 430772 | 0 | 430772 | 1800000 | 900000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 783992 | 0 | 783992 | 0 | 0 | 0 | 0 | 0 | 0 | 33500 | 0 | 33500 | 0 | 0 | 0 | 0 | 0 | 0 | 74880 | 0 | 74880 | 0 | 0 | 0 | 0 | 0 | 0 | 17500 | 0 | 17500 | 10735 | 0 | 10735 | 12000 | 0 | 12000 | 29386925 | 6852149 | 22534776 | 728728 | 152548 | 576179 | 4712000 | 1200000 | 3512000 | 29386925 | 6852149 | 22534776 | 728728 | 152548 | 576179 | 4712000 | 1200000 | 3512000 | 0 | 0 | University of Illinois | TRUE
NT10BIX5570044 | CCI | 2011 | Q2 | Q2 - 2011 | 3592892 | 0 | 3592892 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | 22232196 | 4852149 | 17380047 | 329236 | 245402 | 83834 | 2729872 | 300000 | 2429872 | 23200 | 0 | 23200 | 0 | 0 | 0 | 11600 | 0 | 11600 | 23200 | 0 | 23200 | 0 | 0 | 0 | 11600 | 0 | 11600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1000000 | 1000000 | 0 | 1200000 | 1200000 | 0 | 742471 | 500000 | 242471 | 402981 | 402981 | 0 | 600000 | 500000 | 100000 | 783992 | 0 | 783992 | 0 | 0 | 0 | 0 | 0 | 0 | 33500 | 0 | 33500 | 0 | 0 | 0 | 8000 | 0 | 8000 | 74880 | 0 | 74880 | 0 | 0 | 0 | 25000 | 0 | 25000 | 78115 | 0 | 78115 | 76999 | 0 | 76999 | 78115 | 0 | 78115 | 29386925 | 6852149 | 22534776 | 1809216 | 1648383 | 160833 | 5664187 | 2000000 | 3664187 | 29386925 | 6852149 | 22534776 | 1809216 | 1648383 | 160833 | 5664187 | 2000000 | 3664187 | 0 | 0 | University of Illinois | TRUE
NT10BIX5570044 | CCI | 2011 | Q3 | Q3 - 2011 | 3592892 | 0 | 3592892 | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 22232196 | 4852149 | 17380047 | 630775 | 318979 | 311796 | 3000000 | 375000 | 2625000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 10000 | 0 | 10000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1000000 | 1000000 | 0 | 1300000 | 1300000 | 0 | 742471 | 500000 | 242471 | 402981 | 402981 | 0 | 500000 | 500000 | 0 | 783992 | 0 | 783992 | 0 | 0 | 0 | 15000 | 0 | 15000 | 33500 | 0 | 33500 | 0 | 0 | 0 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 0 | 0 | 0 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 76999 | 0 | 76999 | 76999 | 0 | 76999 | 29386925 | 6852149 | 22534776 | 2110755 | 1721960 | 388795 | 6520379 | 2175000 | 4345379 | 29386925 | 6852149 | 22534776 | 2110755 | 1721960 | 388795 | 6520379 | 2175000 | 4345379 | 0 | 0 | University of Illinois | TRUE
NT10BIX5570044 | CCI | 2011 | Q4 | Q4 - 2011 | 3592892 | 0 | 3592892 | 0 | 0 | 0 | 1400000 | 0 | 1400000 | 22232196 | 4852149 | 17380047 | 2755514 | 488334 | 2267180 | 8100000 | 1100000 | 7000000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 10000 | 0 | 10000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1000000 | 1000000 | 0 | 1300000 | 1300000 | 0 | 742471 | 500000 | 242471 | 402981 | 402981 | 0 | 500000 | 500000 | 0 | 783992 | 0 | 783992 | 0 | 0 | 0 | 100000 | 0 | 100000 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 76999 | 0 | 76999 | 76999 | 0 | 76999 | 29386925 | 6852149 | 22534776 | 4343874 | 1891315 | 2452559 | 11605379 | 2900000 | 8705379 | 29386925 | 6852149 | 22534776 | 4343874 | 1891315 | 2452559 | 11605379 | 2900000 | 8705379 | 0 | 0 | University of Illinois | TRUE
NT10BIX5570044 | CCI | 2012 | Q1 | Q1 - 2012 | 3592892 | 0 | 3592892 | 100000 | 0 | 100000 | 2500000 | 0 | 2500000 | 22232196 | 4852149 | 17380047 | 5367851 | 939657 | 4428194 | 15000000 | 2500000 | 12500000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 15000 | 0 | 15000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1000000 | 1000000 | 0 | 1300000 | 1300000 | 0 | 742471 | 500000 | 242471 | 468890 | 468890 | 0 | 500000 | 500000 | 0 | 783992 | 0 | 783992 | 300000 | 300000 | 0 | 600000 | 500000 | 100000 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 35000 | 0 | 35000 | 40000 | 0 | 40000 | 29386925 | 6852149 | 22534776 | 7380121 | 2708547 | 4671574 | 20073380 | 4800000 | 15273380 | 29386925 | 6852149 | 22534776 | 7380121 | 2708547 | 4671574 | 20073380 | 4800000 | 15273380 | 0 | 0 | University of Illinois | TRUE
NT10BIX5570044 | CCI | 2012 | Q2 | Q2 - 2012 | 3592892 | 0 | 3592892 | 900000 | 0 | 900000 | 2500000 | 0 | 2500000 | 22232196 | 4852149 | 17380047 | 10188453 | 2497341 | 7691111 | 16000000 | 3500000 | 12500000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 15000 | 0 | 15000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1468890 | 1468890 | 0 | 1700000 | 1500000 | 200000 | 742471 | 500000 | 242471 | 50000 | 0 | 50000 | 200000 | 0 | 200000 | 783992 | 0 | 783992 | 500000 | 0 | 500000 | 700000 | 0 | 700000 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 40000 | 0 | 40000 | 45000 | 0 | 45000 | 29386925 | 6852149 | 22534776 | 13255723 | 3966231 | 9289491 | 21278380 | 5000000 | 16278380 | 29386925 | 6852149 | 22534776 | 13255723 | 3966231 | 9289491 | 21278380 | 5000000 | 16278380 | 0 | 60000 | University of Illinois | TRUE
NT10BIX5570044 | CCI | 2012 | Q3 | Q3 - 2012 | 3592892 | 0 | 3592892 | 2120761 | 0 | 2120761 | 2500000 | 0 | 2500000 | 22232196 | 4852149 | 17380047 | 11029156 | 3021019 | 8008137 | 16000000 | 4800000 | 11200000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 20000 | 0 | 20000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1468890 | 1468890 | 0 | 1700000 | 1500000 | 200000 | 742471 | 500000 | 242471 | 200000 | 0 | 200000 | 400000 | 0 | 400000 | 783992 | 0 | 783992 | 500000 | 0 | 500000 | 600000 | 0 | 600000 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 48886 | 0 | 48886 | 51500 | 0 | 51500 | 29386925 | 6852149 | 22534776 | 15476073 | 4489909 | 10986164 | 21394880 | 6300000 | 15094880 | 29386925 | 6852149 | 22534776 | 15476073 | 4489909 | 10986164 | 21394880 | 6300000 | 15094880 | 0 | 60000 | University of Illinois | TRUE
NT10BIX5570044 | CCI | 2012 | Q4 | Q4 - 2012 | 3592892 | 0 | 3592892 | 2500000 | 0 | 2500000 | 2500000 | 0 | 2500000 | 22232196 | 4852149 | 17380047 | 13489164 | 3186065 | 10303099 | 15000000 | 3200000 | 11800000 | 23200 | 0 | 23200 | 20000 | 0 | 20000 | 53000 | 0 | 53000 | 23200 | 0 | 23200 | 20000 | 0 | 20000 | 23200 | 0 | 23200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1668890 | 1500000 | 168890 | 1700000 | 1500000 | 200000 | 742471 | 500000 | 242471 | 300000 | 57529 | 242471 | 400000 | 157529 | 242471 | 783992 | 0 | 783992 | 550000 | 0 | 550000 | 600000 | 0 | 600000 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 60000 | 0 | 60000 | 70000 | 0 | 70000 | 29386925 | 6852149 | 22534776 | 18716434 | 4743594 | 13972840 | 20454580 | 4857529 | 15597051 | 29386925 | 6852149 | 22534776 | 18716434 | 4743594 | 13972840 | 20454580 | 4857529 | 15597051 | 0 | 717187 | University of Illinois | TRUE
NT10BIX5570044 | CCI | 2013 | Q1 | Q1 - 2013 | 3592892 | 2391345 | 1201547 | 3166295 | 1692993 | 1473302 | 3250000 | 2048453 | 1201547 | 22126108 | 2854716 | 19271392 | 13555046 | 2000000 | 11555046 | 17000000 | 2000000 | 15000000 | 23200 | 0 | 23200 | 53000 | 0 | 53000 | 70000 | 0 | 70000 | 23200 | 0 | 23200 | 23200 | 0 | 23200 | 23200 | 0 | 23200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1700000 | 1500000 | 200000 | 1802479 | 1500000 | 302479 | 742471 | 0 | 742471 | 400000 | 157529 | 242471 | 500000 | 257529 | 242471 | 783992 | 0 | 783992 | 600000 | 0 | 600000 | 650000 | 0 | 650000 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 60000 | 0 | 60000 | 65000 | 0 | 65000 | 29280837 | 6746061 | 22534776 | 19665921 | 5350522 | 14315399 | 23469059 | 5805982 | 17663077 | 29280837 | 6746061 | 22534776 | 19665921 | 5350522 | 14315399 | 23469059 | 5805982 | 17663077 | 0 | 945673 | University of Illinois | TRUE
NT10BIX5570044 | CCI | 2013 | Q2 | Q2 - 2013 | 3592892 | 2391345 | 1201547 | 3200000 | 2093056 | 450000 | 3592892 | 2391345 | 1201547 | 22126108 | 2854716 | 19271392 | 17441046 | 2200000 | 15897990 | 22079308 | 2654716 | 19224592 | 23200 | 0 | 23200 | 70000 | 0 | 70000 | 70000 | 0 | 70000 | 23200 | 0 | 23200 | 23200 | 0 | 23200 | 23200 | 0 | 23200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1750000 | 1500000 | 250000 | 1802479 | 1500000 | 302479 | 742471 | 0 | 742471 | 500000 | 200000 | 300000 | 742471 | 200000 | 542471 | 783992 | 0 | 783992 | 650000 | 0 | 650000 | 783992 | 0 | 783992 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 65000 | 0 | 65000 | 78115 | 0 | 78115 | 29280837 | 6746061 | 22534776 | 23807626 | 5993056 | 17814570 | 29280837 | 6746061 | 22334776 | 29280837 | 6746061 | 22534776 | 23807626 | 5993056 | 17814570 | 29280837 | 6746061 | 22334776 | 0 | 78765 | University of Illinois | TRUE
NT10BIX5570044 | CCI | 2013 | Q3 | Q3 - 2013 | 3592892 | 2391345 | 1201547 | 2844388 | 2352142 | 492246 | 2844388 | 2352142 | 492246 | 22126108 | 2854716 | 19271392 | 22838991 | 2906013 | 19932978 | 22838991 | 2906013 | 19932978 | 23200 | 0 | 23200 | 111605 | 0 | 111605 | 111605 | 0 | 111605 | 23200 | 0 | 23200 | 46750 | 0 | 46750 | 46750 | 0 | 46750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1802479 | 1500000 | 302479 | 1851949 | 1487965 | 363984 | 1851949 | 1487965 | 363984 | 742471 | 0 | 742471 | 836299 | 0 | 836299 | 836299 | 0 | 836299 | 783992 | 0 | 783992 | 619447 | 0 | 619447 | 619447 | 0 | 619447 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 33500 | 0 | 33500 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 74880 | 0 | 74880 | 78115 | 0 | 78115 | 23087 | 0 | 23087 | 23087 | 0 | 23087 | 29280837 | 6746061 | 22534776 | 29280896 | 6746120 | 22534776 | 29280896 | 6746120 | 22534776 | 29280837 | 6746061 | 22534776 | 29280896 | 6746120 | 22534776 | 29280896 | 6746120 | 22534776 | 0 | 0 | University of Illinois | TRUE
NT10BIX5570045 | CCI | 2010 | Q3 | Q3 - 2010 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 0 | 0 | 0 | 3673242 | 3223242 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 0 | 0 | 0 | 45000 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 0 | 0 | 0 | 3728242 | 3223242 | 505000 | 8859615 | 3753242 | 5106373 | 0 | 0 | 0 | 3728242 | 3223242 | 505000 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570045 | CCI | 2010 | Q4 | Q4 - 2010 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 0 | 0 | 0 | 3673242 | 3223242 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 29880 | 1455 | 28425 | 45000 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 29880 | 1455 | 28425 | 3728242 | 3223242 | 505000 | 8859615 | 3753242 | 5106373 | 29880 | 1455 | 28425 | 3728242 | 3223242 | 505000 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570045 | CCI | 2011 | Q1 | Q1 - 2011 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 0 | 0 | 0 | 465200 | 206000 | 259200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 36464 | 2035 | 34429 | 55000 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 36464 | 2035 | 34429 | 520200 | 206000 | 314200 | 8859615 | 3753242 | 5106373 | 36464 | 2035 | 34429 | 520200 | 206000 | 314200 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570045 | CCI | 2011 | Q2 | Q2 - 2011 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 400710 | 183022 | 217688 | 4297163 | 3754841 | 542322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 44405 | 0 | 44405 | 58160 | 0 | 58160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 445115 | 183022 | 262093 | 4365323 | 3754841 | 610482 | 8859615 | 3753242 | 5106373 | 445115 | 183022 | 262093 | 4365323 | 3754841 | 610482 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570045 | CCI | 2011 | Q3 | Q3 - 2011 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 3910418 | 3436185 | 474233 | 4686185 | 3436185 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 76101 | 0 | 76101 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 3986519 | 3436185 | 550334 | 4796185 | 3436185 | 1360000 | 8859615 | 3753242 | 5106373 | 3986519 | 3436185 | 550334 | 4796185 | 3436185 | 1360000 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570045 | CCI | 2011 | Q4 | Q4 - 2011 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 4762194 | 3460027 | 1211043 | 5560027 | 3460027 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 91124 | 0 | 91124 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 4853318 | 3460027 | 1302167 | 5710027 | 3460027 | 2250000 | 8859615 | 3753242 | 5106373 | 4853318 | 3460027 | 1302167 | 5710027 | 3460027 | 2250000 | 298800 | 5400 | University of Wisconsin System | TRUE
NT10BIX5570045 | CCI | 2012 | Q1 | Q1 - 2012 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 5421441 | 3493857 | 1927584 | 5651441 | 3523857 | 2127584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 123293 | 0 | 123293 | 160000 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 5544734 | 3493857 | 2050877 | 5811441 | 3523857 | 2287584 | 8859615 | 3753242 | 5106373 | 5544734 | 3493857 | 2050877 | 5811441 | 3523857 | 2287584 | 298800 | 0 | University of Wisconsin System | TRUE
NT10BIX5570045 | CCI | 2012 | Q2 | Q2 - 2012 | 131764 | 0 | 131764 | 0 | 0 | 0 | 0 | 0 | 0 | 8180587 | 3753242 | 4427345 | 5530584 | 3522261 | 2008323 | 5990584 | 3572261 | 2418323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537264 | 0 | 537264 | 156534 | 0 | 156534 | 181534 | 0 | 181534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8859615 | 3753242 | 5106373 | 5687118 | 3522261 | 2164857 | 6182118 | 3572261 | 2609857 | 8859615 | 3753242 | 5106373 | 5687118 | 3522261 | 2164857 | 6182118 | 3572261 | 2609857 | 298800 | 0 | University of Wisconsin System | TRUE
NT10BIX5570045 | CCI | 2012 | Q3 | Q3 - 2012 | 1625712 | 0 | 1625712 | 0 | 0 | 0 | 1625712 | 0 | 1625712 | 6834082 | 3753242 | 3080840 | 5760535 | 3548833 | 2211702 | 6834082 | 3753242 | 3080840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339821 | 0 | 339821 | 169488 | 0 | 169488 | 260000 | 0 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 50000 | 0 | 50000 | 8859615 | 3753242 | 5106373 | 5930023 | 3548833 | 2381190 | 8779794 | 3753242 | 5026552 | 8859615 | 3753242 | 5106373 | 5930023 | 3548833 | 2381190 | 8779794 | 3753242 | 5026552 | 298000 | 0 | University of Wisconsin System | TRUE
NT10BIX5570045 | CCI | 2012 | Q4 | Q4 - 2012 | 1625712 | 0 | 1625712 | 0 | 0 | 0 | 1625712 | 0 | 1625712 | 6834082 | 3753242 | 3080840 | 6355835 | 3574330 | 2781505 | 6920353 | 3753242 | 3167111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339821 | 0 | 339821 | 179549 | 0 | 179549 | 253550 | 0 | 253550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 50000 | 0 | 50000 | 8859615 | 3753242 | 5106373 | 6535384 | 3574330 | 2961054 | 8859615 | 3753242 | 5106373 | 8859615 | 3753242 | 5106373 | 6535384 | 3574330 | 2961054 | 8859615 | 3753242 | 5106373 | 298000 | 0 | University of Wisconsin System | TRUE
NT10BIX5570045 | CCI | 2013 | Q1 | Q1 - 2013 | 1625712 | 0 | 1625712 | 1625712 | 0 | 1625712 | 1625712 | 0 | 1625712 | 6834082 | 3753242 | 3080840 | 6473070 | 3461360 | 3011710 | 6834082 | 3753242 | 3080840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339821 | 0 | 339821 | 295671 | 0 | 295671 | 339821 | 0 | 339821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 50000 | 0 | 50000 | 8859615 | 3753242 | 5106373 | 8394453 | 3461360 | 4933093 | 8859615 | 3753242 | 5106373 | 8859615 | 3753242 | 5106373 | 8394453 | 3461360 | 4933093 | 8859615 | 3753242 | 5106373 | 298000 | 71200 | University of Wisconsin System | TRUE
NT10BIX5570045 | CCI | 2013 | Q2 | Q2 - 2013 | 1625712 | 0 | 1625712 | 1523464 | 0 | 1523464 | 1523464 | 0 | 1523464 | 6834082 | 3753242 | 3080840 | 7121335 | 3869042 | 3252293 | 7121335 | 3869042 | 3252293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339821 | 0 | 339821 | 298304 | 0 | 298304 | 298304 | 0 | 298304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 9735 | 0 | 9735 | 9735 | 0 | 9735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 | 22577 | 0 | 22577 | 22577 | 0 | 22577 | 8859615 | 3753242 | 5106373 | 8975415 | 3869042 | 5106373 | 8975415 | 3869042 | 5106373 | 8859615 | 3753242 | 5106373 | 8975415 | 3869042 | 5106373 | 8975415 | 3869042 | 5106373 | 298000 | 115800 | University of Wisconsin System | TRUE
NT10BIX5570046 | CCI | 2010 | Q3 | Q3 - 2010 | 21118145 | 7343730 | 13774415 | 0 | 219140 | 219140 | 219140 | 219140 | 0 | 60232098 | 1810098 | 58422000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9766289 | 5266289 | 4500000 | 5075490 | 5075490 | 0 | 5075490 | 5075490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3900000 | 0 | 0 | 0 | 493301 | 0 | 493301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 5075490 | 5294630 | 219140 | 5787931 | 5294630 | 493301 | 95016532 | 14420117 | 80596415 | 5075490 | 5294630 | 219140 | 5787931 | 5294630 | 493301 | 0 | 0 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | CCI | 2010 | Q4 | Q4 - 2010 | 21118145 | 7343730 | 13774415 | 218476 | 218476 | 0 | 3534532 | 3484532 | 50000 | 60232098 | 1810098 | 58422000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9766289 | 5266289 | 4500000 | 5075490 | 5075490 | 0 | 5075490 | 5075490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3900000 | 735 | 0 | 735 | 900735 | 0 | 900735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 5294701 | 5293966 | 735 | 9510757 | 8560022 | 950735 | 95016532 | 14420117 | 80596415 | 5294701 | 5293966 | 735 | 9510757 | 8560022 | 950735 | 0 | 0 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | CCI | 2011 | Q1 | Q1 - 2011 | 21118145 | 7343730 | 13774415 | 3486840 | 3486840 | 0 | 3547204 | 3486840 | 60364 | 60232098 | 1810098 | 58422000 | 1810098 | 1810098 | 0 | 1810098 | 1810098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9766289 | 5266289 | 4500000 | 0 | 0 | 0 | 5266289 | 5266289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3900000 | 366359 | 0 | 366359 | 1746359 | 0 | 1746359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 5663297 | 5296938 | 366359 | 12369950 | 10563227 | 1806723 | 95016532 | 14420117 | 80596415 | 5663297 | 5296938 | 366359 | 12369950 | 10563227 | 1806723 | 0 | 0 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | CCI | 2011 | Q2 | Q2 - 2011 | 21118145 | 7343730 | 13774415 | 3552228 | 3486840 | 65388 | 0 | 0 | 0 | 60232098 | 1810098 | 58422000 | 1810098 | 1810098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9766289 | 5266289 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3900000 | 366359 | 0 | 366359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 5728685 | 5296938 | 431747 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 5728685 | 5296938 | 431747 | 0 | 0 | 0 | 0 | 0 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | CCI | 2011 | Q3 | Q3 - 2011 | 21118145 | 7343730 | 13774415 | 286837 | 221448 | 65389 | 0 | 0 | 0 | 60232098 | 1810098 | 58422000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9766289 | 5266289 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3900000 | 528858 | 0 | 528858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 815695 | 221448 | 594247 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 815695 | 221448 | 594247 | 0 | 0 | 0 | 0 | 0 | Louisiana Board of Regents | TRUE
NT10BIX5570046 | CCI | 2011 | Q4 | Q4 - 2011 | 21118145 | 7343730 | 13774415 | 3539156 | 3486840 | 52316 | 0 | 0 | 0 | 60232098 | 1810098 | 58422000 | 1810098 | 1810098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551 | 551 | 0 | 0 | 0 | 0 | 9766289 | 5266289 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3900000 | 684295 | 0 | 684295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 6034100 | 5297489 | 736611 | 0 | 0 | 0 | 95016532 | 14420117 | 80596415 | 6034100 | 5297489 | 736611 | 0 | 0 | 0 | 0 | 0 | Louisiana Board of Regents | TRUE
NT10BIX5570047 | CCI | 2010 | Q3 | Q3 - 2010 | 15517288 | 7414371 | 8102917 | 0 | 0 | 0 | 2500000 | 0 | 2500000 | 70065546 | 11209538 | 58856008 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 1385673 | 0 | 1385673 | 0 | 0 | 0 | 0 | 0 | 0 | 3845935 | 3574685 | 271250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 598165 | 0 | 598165 | 1000000 | 0 | 1000000 | 2136368 | 0 | 2136368 | 0 | 0 | 0 | 50000 | 0 | 50000 | 8194858 | 0 | 8194858 | 377622 | 0 | 377622 | 700000 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 0 | 0 | 0 | 0 | 0 | 0 | 106546591 | 22198594 | 84347997 | 975787 | 0 | 975787 | 4350000 | 20000 | 4330000 | 106546591 | 22198594 | 84347997 | 975787 | 0 | 975787 | 4350000 | 20000 | 4330000 | 2022249 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570047 | CCI | 2010 | Q4 | Q4 - 2010 | 15517288 | 7414371 | 8102917 | 1993702 | 0 | 1993702 | 3000000 | 0 | 3000000 | 70065546 | 11209538 | 58856008 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | 1385673 | 0 | 1385673 | 0 | 0 | 0 | 0 | 0 | 0 | 3845935 | 3574685 | 271250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 1164824 | 0 | 1164824 | 2250000 | 0 | 2250000 | 2136368 | 0 | 2136368 | 344948 | 0 | 344948 | 1000000 | 0 | 1000000 | 8194858 | 0 | 8194858 | 961349 | 0 | 961349 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207687 | 0 | 0 | 0 | 0 | 0 | 0 | 106546591 | 22198594 | 84348006 | 4464823 | 0 | 4464823 | 9250000 | 0 | 9250000 | 106546591 | 22198594 | 84348006 | 4464823 | 0 | 4464823 | 9250000 | 0 | 9250000 | 2022249 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570047 | CCI | 2011 | Q1 | Q1 - 2011 | 15517288 | 7414371 | 8102917 | 2651274 | 0 | 2651274 | 4000000 | 0 | 4000000 | 70065546 | 11209538 | 58856008 | 66205 | 57635 | 62078 | 2000000 | 100000 | 1900000 | 1385673 | 0 | 1385673 | 0 | 0 | 0 | 0 | 0 | 0 | 3845935 | 3574685 | 271250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 1379394 | 246 | 1379148 | 2000000 | 500 | 1999500 | 2136368 | 0 | 2136368 | 837886 | 0 | 837886 | 1300000 | 0 | 1300000 | 8194858 | 0 | 8194858 | 1532447 | 2949 | 1529498 | 2200000 | 5000 | 2195000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 0 | 0 | 0 | 0 | 0 | 0 | 106546591 | 22198594 | 84347997 | 6467206 | 60830 | 6459884 | 11500000 | 105500 | 11394500 | 106546591 | 22198594 | 84347997 | 6467206 | 60830 | 6459884 | 11500000 | 105500 | 11394500 | 2022249 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570047 | CCI | 2011 | Q2 | Q2 - 2011 | 15517288 | 7414371 | 8102917 | 2742881 | 0 | 2742881 | 14000000 | 9000000 | 5000000 | 70065546 | 11209538 | 58856008 | 411548 | 255608 | 155940 | 7500000 | 5000000 | 2500000 | 1385673 | 0 | 1385673 | 0 | 0 | 0 | 0 | 0 | 0 | 3845935 | 3574685 | 271250 | 4000 | 0 | 4000 | 3500000 | 3455000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 2784033 | 246 | 2783787 | 4200000 | 0 | 4200000 | 2136368 | 0 | 2136368 | 1662144 | 0 | 1662144 | 2500000 | 0 | 2500000 | 8194858 | 0 | 8194858 | 2286890 | 2949 | 2283941 | 3000000 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 137433 | 0 | 137433 | 170000 | 0 | 170000 | 106546591 | 22198594 | 84347997 | 10028929 | 258803 | 9770126 | 34870000 | 17455000 | 17375000 | 106546591 | 22198594 | 84347997 | 10028929 | 258803 | 9770126 | 34870000 | 17455000 | 17375000 | 2022249 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570047 | CCI | 2011 | Q3 | Q3 - 2011 | 15517288 | 7414371 | 8102917 | 13270584 | 8925408 | 4345176 | 14000000 | 9000000 | 5000000 | 70065546 | 11209538 | 58856008 | 6870011 | 5280454 | 1589557 | 21000000 | 6000000 | 15000000 | 1385673 | 0 | 1385673 | 0 | 0 | 0 | 0 | 0 | 0 | 3845935 | 3574685 | 271250 | 3446687 | 3438187 | 8500 | 3600000 | 3500000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 3509870 | 0 | 3509870 | 4000000 | 0 | 4000000 | 2136368 | 0 | 2136368 | 2962656 | 0 | 2962656 | 3500000 | 0 | 3500000 | 8194858 | 0 | 8194858 | 2831443 | 0 | 2831443 | 4000000 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 148871 | 0 | 148871 | 160000 | 0 | 160000 | 106546591 | 22198594 | 84347997 | 33040122 | 17644049 | 15396073 | 50260000 | 18500000 | 31760000 | 106546591 | 22198594 | 84347997 | 33040122 | 17644049 | 15396073 | 50260000 | 18500000 | 31760000 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570047 | CCI | 2011 | Q4 | Q4 - 2011 | 15517288 | 7414371 | 8102917 | 13822766 | 8925408 | 4897358 | 14000000 | 9000000 | 5000000 | 70065546 | 11209538 | 58856008 | 21274518 | 6056020 | 15218499 | 35000000 | 7000000 | 28000000 | 1385673 | 0 | 1385673 | 0 | 0 | 0 | 0 | 0 | 0 | 3845935 | 3574685 | 271250 | 3450473 | 3438187 | 12286 | 3600000 | 3580000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 3961296 | 0 | 3961296 | 4500000 | 0 | 4500000 | 2136368 | 0 | 2136368 | 3632456 | 0 | 3632456 | 4100000 | 0 | 4100000 | 8194858 | 0 | 8194858 | 5016575 | 0 | 5016575 | 6500000 | 0 | 6500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 158181 | 0 | 158181 | 175000 | 0 | 175000 | 106546591 | 22198594 | 84347997 | 51316265 | 18419615 | 32896651 | 67875000 | 19580000 | 48295000 | 106546591 | 22198594 | 84347997 | 51316265 | 18419615 | 32896651 | 67875000 | 19580000 | 48295000 | 0 | 7686 | Northwest Open Access Network | TRUE
NT10BIX5570047 | CCI | 2012 | Q1 | Q1 - 2012 | 15517288 | 7414371 | 8102917 | 14807631 | 8925408 | 5882223 | 15500000 | 8926000 | 6574000 | 70065546 | 11209538 | 58856008 | 26447066 | 6329759 | 20117307 | 34000000 | 7000000 | 27000000 | 1385673 | 0 | 1385673 | 470 | 0 | 470 | 500 | 0 | 500 | 3845935 | 3574685 | 271250 | 3456204 | 3438187 | 18017 | 3550000 | 3500000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 4278912 | 0 | 4278912 | 5266912 | 0 | 5266912 | 2136368 | 0 | 2136368 | 4440091 | 0 | 4440091 | 4440091 | 0 | 4440091 | 8194858 | 0 | 8194858 | 6089689 | 0 | 6089689 | 6800000 | 0 | 6800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 158181 | 0 | 158181 | 160000 | 0 | 160000 | 106546591 | 22198594 | 84347997 | 59678244 | 18693354 | 40984890 | 69717503 | 19426000 | 50291503 | 106546591 | 22198594 | 84347997 | 59678244 | 18693354 | 40984890 | 69717503 | 19426000 | 50291503 | 0 | 16302 | Northwest Open Access Network | TRUE
NT10BIX5570047 | CCI | 2012 | Q2 | Q2 - 2012 | 15517288 | 7414371 | 8102917 | 15243998 | 8925408 | 6318590 | 15800000 | 8926000 | 6874000 | 70065546 | 11209538 | 58856008 | 34869041 | 7189045 | 27679996 | 41516621 | 8000000 | 33516621 | 1385673 | 0 | 1385673 | 470 | 0 | 470 | 470 | 0 | 470 | 3845935 | 3574685 | 271250 | 3465736 | 3438187 | 27549 | 3473187 | 3438187 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 4510065 | 0 | 4510065 | 5321215 | 0 | 5321215 | 2136368 | 0 | 2136368 | 4908610 | 0 | 4908610 | 5400000 | 0 | 5400000 | 8194858 | 0 | 8194858 | 7154273 | 0 | 7154273 | 7600000 | 0 | 7600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 158182 | 0 | 158182 | 160000 | 0 | 160000 | 106546591 | 22198594 | 84347997 | 70310375 | 19552640 | 50757735 | 79271493 | 20364187 | 58907306 | 106546591 | 22198594 | 84347997 | 70310375 | 19552640 | 50757735 | 79271493 | 20364187 | 58907306 | 0 | 25863 | Northwest Open Access Network | TRUE
NT10BIX5570047 | CCI | 2012 | Q3 | Q3 - 2012 | 15517288 | 7414371 | 8102917 | 16248688 | 8925408 | 7323280 | 17548688 | 8925408 | 8623280 | 70065546 | 11209538 | 58856008 | 44637624 | 7490737 | 37146887 | 48000000 | 8000000 | 40000000 | 1385673 | 0 | 1385673 | 470 | 0 | 470 | 470 | 0 | 470 | 3845935 | 3574685 | 271250 | 3463856 | 3438187 | 25669 | 3463856 | 3438187 | 25669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 4231198 | 0 | 4231198 | 4750000 | 0 | 4750000 | 2136368 | 0 | 2136368 | 5269490 | 0 | 5269490 | 5300000 | 0 | 5300000 | 8194858 | 0 | 8194858 | 9240771 | 0 | 9240771 | 10000000 | 0 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 146743 | 0 | 146743 | 165000 | 0 | 165000 | 106546591 | 22198594 | 84347997 | 83238840 | 19854332 | 63384508 | 89228014 | 20363595 | 68864419 | 106546591 | 22198594 | 84347997 | 83238840 | 19854332 | 63384508 | 89228014 | 20363595 | 68864419 | 0 | 47174 | Northwest Open Access Network | TRUE
NT10BIX5570047 | CCI | 2012 | Q4 | Q4 - 2012 | 15517288 | 7414371 | 8102917 | 16793949 | 8925408 | 7868541 | 17548688 | 8925408 | 8623280 | 70065546 | 11209538 | 58856008 | 51627191 | 7522142 | 44105049 | 55100000 | 8020000 | 47080000 | 1385673 | 0 | 1385673 | 470 | 0 | 470 | 470 | 0 | 470 | 3845935 | 3574685 | 271250 | 3463856 | 3438187 | 25669 | 3463856 | 3438187 | 25669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 4329645 | 0 | 4329645 | 4750000 | 0 | 4750000 | 2136368 | 0 | 2136368 | 5492079 | 0 | 5492079 | 5800000 | 0 | 5800000 | 8194858 | 0 | 8194858 | 10392561 | 0 | 10392561 | 11000000 | 0 | 11000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 146743 | 0 | 146743 | 146743 | 0 | 146743 | 106546591 | 22198594 | 84347997 | 92246494 | 19885737 | 72360757 | 97809757 | 20383595 | 77426162 | 106546591 | 22198594 | 84347997 | 92246494 | 19885737 | 72360757 | 97809757 | 20383595 | 77426162 | 0 | 120873 | Northwest Open Access Network | TRUE
NT10BIX5570047 | CCI | 2013 | Q1 | Q1 - 2013 | 15517288 | 7414371 | 8102917 | 19535101 | 8925408 | 10609693 | 20000000 | 8925408 | 11074592 | 70065546 | 11209538 | 58856008 | 56349041 | 7722078 | 48626963 | 60000000 | 8669270 | 51330730 | 1385673 | 0 | 1385673 | 470 | 0 | 470 | 470 | 0 | 470 | 3845935 | 3574685 | 271250 | 3463856 | 3438187 | 25669 | 3463856 | 3438187 | 25669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 4411019 | 0 | 4411019 | 4500000 | 0 | 4500000 | 2136368 | 0 | 2136368 | 5684827 | 101 | 5684726 | 5800000 | 101 | 5799899 | 8194858 | 0 | 8194858 | 10920527 | 0 | 10920527 | 11200000 | 0 | 11200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 196441 | 0 | 196441 | 200000 | 0 | 200000 | 106546591 | 22198594 | 84347997 | 100561282 | 20085774 | 80475508 | 105164326 | 21032966 | 84131360 | 106546591 | 22198594 | 84347997 | 100561282 | 20085774 | 80475508 | 105164326 | 21032966 | 84131360 | 0 | 194626 | Northwest Open Access Network | TRUE
NT10BIX5570047 | CCI | 2013 | Q2 | Q2 - 2013 | 15517288 | 7414371 | 8102917 | 19457262 | 8925408 | 10531854 | 19457262 | 8925408 | 10531854 | 70065546 | 11209538 | 58856008 | 56962020 | 7821703 | 49140317 | 57381304 | 7900000 | 49481304 | 1385673 | 0 | 1385673 | 470 | 0 | 470 | 470 | 0 | 470 | 3845935 | 3574685 | 271250 | 3463856 | 3438187 | 25669 | 3463856 | 3438187 | 25669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 4463881 | 0 | 4463881 | 4500000 | 0 | 4500000 | 2136368 | 0 | 2136368 | 5784368 | 0 | 5784368 | 6000000 | 0 | 6000000 | 8194858 | 0 | 8194858 | 11139390 | 0 | 11139390 | 11500000 | 0 | 11500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 198241 | 0 | 198241 | 200000 | 0 | 200000 | 106546591 | 22198594 | 84347997 | 101469488 | 20185298 | 81284190 | 102502892 | 20263595 | 82239297 | 106546591 | 22198594 | 84347997 | 101469488 | 20185298 | 81284190 | 102502892 | 20263595 | 82239297 | 0 | 177752 | Northwest Open Access Network | TRUE
NT10BIX5570047 | CCI | 2013 | Q3 | Q3 - 2013 | 17028234 | 8925407 | 8102827 | 20113221 | 8925407 | 11187814 | 20113221 | 8925407 | 11187814 | 68691098 | 9835000 | 58856098 | 60718783 | 9835000 | 50883783 | 60718783 | 9835000 | 50883783 | 1385673 | 0 | 1385673 | 4217 | 0 | 4217 | 4217 | 0 | 4217 | 3709437 | 3438187 | 271250 | 3510414 | 3438187 | 72227 | 3510414 | 3438187 | 72227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5193245 | 0 | 5193245 | 4585264 | 0 | 4585264 | 4585264 | 0 | 4585264 | 2136368 | 0 | 2136368 | 5993575 | 0 | 5993575 | 5993575 | 0 | 5993575 | 8194858 | 0 | 8194858 | 11417716 | 0 | 11417716 | 11417716 | 0 | 11417716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207678 | 0 | 207678 | 203401 | 0 | 203401 | 203401 | 0 | 203401 | 106546591 | 22198594 | 84347997 | 106546591 | 22198594 | 84347997 | 106546591 | 22198594 | 84347997 | 106546591 | 22198594 | 84347997 | 106546591 | 22198594 | 84347997 | 106546591 | 22198594 | 84347997 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570049 | CCI | 2010 | Q3 | Q3 - 2010 | 781714 | 156343 | 625371 | 0 | 0 | 0 | 0 | 0 | 0 | 750883 | 150177 | 600706 | 0 | 0 | 0 | 0 | 0 | 0 | 197666 | 39533 | 158133 | 22402 | 4480 | 17922 | 74304 | 14861 | 59443 | 234020 | 46804 | 187216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165775 | 33155 | 132620 | 12213 | 2443 | 9770 | 81133 | 16227 | 64906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131250 | 26250 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 4400 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 34615 | 6923 | 27692 | 155437 | 31088 | 124349 | 2283308 | 456662 | 1826646 | 34615 | 6923 | 27692 | 155437 | 31088 | 124349 | 0 | 0 | Nelson, County of | TRUE
NT10BIX5570049 | CCI | 2010 | Q4 | Q4 - 2010 | 781714 | 156343 | 625371 | 0 | 0 | 0 | 0 | 0 | 0 | 750883 | 150177 | 600706 | 0 | 0 | 0 | 0 | 0 | 0 | 197666 | 39533 | 158133 | 80784 | 16157 | 64627 | 143250 | 28650 | 114600 | 234020 | 46804 | 187216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165775 | 33155 | 132620 | 68742 | 13748 | 54994 | 149674 | 29935 | 119739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131250 | 26250 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 4400 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 149526 | 29905 | 119621 | 292924 | 58585 | 234339 | 2283308 | 456662 | 1826646 | 149526 | 29905 | 119621 | 292924 | 58585 | 234339 | 0 | 0 | Nelson, County of | TRUE
NT10BIX5570049 | CCI | 2011 | Q1 | Q1 - 2011 | 781714 | 156343 | 625371 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 750883 | 150177 | 600706 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 197666 | 39533 | 158133 | 130454 | 26091 | 104363 | 160453 | 32090 | 128363 | 234020 | 46804 | 187216 | 0 | 0 | 0 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165775 | 33155 | 132620 | 120567 | 24113 | 96454 | 170568 | 34114 | 136454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131250 | 26250 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 4400 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 251021 | 50204 | 200817 | 646021 | 129204 | 516817 | 2283308 | 456662 | 1826646 | 251021 | 50204 | 200817 | 646021 | 129204 | 516817 | 0 | 0 | Nelson, County of | TRUE
NT10BIX5570049 | CCI | 2011 | Q2 | Q2 - 2011 | 781714 | 156343 | 625371 | 0 | 0 | 0 | 415039 | 83008 | 332031 | 750883 | 150177 | 600706 | 0 | 0 | 0 | 187721 | 37544 | 150177 | 197666 | 39533 | 158133 | 169921 | 31146 | 138775 | 182921 | 36584 | 146337 | 234020 | 46804 | 187216 | 0 | 0 | 0 | 2500 | 500 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165775 | 33155 | 132620 | 204468 | 36660 | 167808 | 258000 | 51600 | 206400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131250 | 26250 | 105000 | 0 | 0 | 0 | 4200 | 840 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 4400 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 374389 | 67806 | 306583 | 1050381 | 210076 | 840305 | 2283308 | 456662 | 1826646 | 374389 | 67806 | 306583 | 1050381 | 210076 | 840305 | 0 | 0 | Nelson, County of | TRUE
NT10BIX5570049 | CCI | 2011 | Q3 | Q3 - 2011 | 618991 | 123799 | 495193 | 0 | 0 | 0 | 271632 | 54326 | 217306 | 830297 | 166060 | 664237 | 0 | 0 | 0 | 30000 | 6000 | 24000 | 229666 | 45933 | 183733 | 201609 | 40322 | 161287 | 220600 | 44120 | 176480 | 234020 | 46804 | 187215 | 4850 | 970 | 3880 | 14850 | 2970 | 11880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282692 | 56538 | 226154 | 282337 | 56467 | 225870 | 324868 | 64974 | 259894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87642 | 17528 | 70114 | 0 | 0 | 0 | 10000 | 2000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 488796 | 97759 | 391037 | 871950 | 174390 | 697560 | 2283308 | 456662 | 1826646 | 488796 | 97759 | 391037 | 871950 | 174390 | 697560 | 0 | 0 | Nelson, County of | TRUE
NT10BIX5570049 | CCI | 2011 | Q4 | Q4 - 2011 | 618991 | 123799 | 495193 | 275719 | 55144 | 220575 | 482250 | 96450 | 385800 | 830297 | 166060 | 664237 | 0 | 0 | 0 | 664238 | 132848 | 531390 | 229666 | 45933 | 183733 | 224768 | 44954 | 179814 | 229666 | 45933 | 183733 | 234020 | 46804 | 187215 | 4850 | 970 | 3880 | 20850 | 4170 | 16680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282692 | 56538 | 226154 | 315869 | 63174 | 252695 | 322692 | 64538 | 258154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87642 | 17528 | 70114 | 7750 | 1550 | 6200 | 20350 | 4070 | 16280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 828956 | 165792 | 663164 | 1740046 | 348009 | 1392037 | 2283308 | 456662 | 1826646 | 828956 | 165792 | 663164 | 1740046 | 348009 | 1392037 | 0 | 0 | Nelson, County of | TRUE
NT10BIX5570049 | CCI | 2012 | Q1 | Q1 - 2012 | 618984 | 123797 | 495187 | 375044 | 75009 | 300035 | 402340 | 80468 | 321872 | 830304 | 166061 | 664243 | 153428 | 30686 | 122742 | 498182 | 99636 | 398546 | 241880 | 48376 | 193504 | 241386 | 48277 | 193109 | 241386 | 48277 | 193109 | 234020 | 46804 | 187216 | 4850 | 970 | 3880 | 24850 | 4970 | 19880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315870 | 63174 | 252696 | 315869 | 63174 | 252695 | 315869 | 63174 | 252695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42250 | 8450 | 33800 | 26437 | 5287 | 21150 | 27463 | 3493 | 23970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 1117014 | 223403 | 893611 | 1510090 | 300018 | 1210072 | 2283308 | 456662 | 1826646 | 1117014 | 223403 | 893611 | 1510090 | 300018 | 1210072 | 0 | 0 | Nelson, County of | TRUE
NT10BIX5570049 | CCI | 2012 | Q2 | Q2 - 2012 | 618984 | 123797 | 495187 | 439230 | 87846 | 351384 | 464238 | 92848 | 371390 | 830304 | 166061 | 664243 | 549194 | 109839 | 439355 | 736700 | 147340 | 589360 | 241880 | 48376 | 193504 | 241386 | 48277 | 193109 | 241386 | 48277 | 193109 | 234020 | 46804 | 187216 | 4850 | 970 | 3880 | 140412 | 28082 | 112330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315870 | 63174 | 252696 | 315870 | 63174 | 252696 | 315870 | 63174 | 252696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 1592780 | 318556 | 1274224 | 1940856 | 388171 | 1552685 | 2283308 | 456662 | 1826646 | 1592780 | 318556 | 1274224 | 1940856 | 388171 | 1552685 | 0 | 0 | Nelson, County of | TRUE
NT10BIX5570049 | CCI | 2012 | Q3 | Q3 - 2012 | 618984 | 123797 | 495187 | 562625 | 112525 | 450100 | 618984 | 123797 | 495187 | 830304 | 166061 | 664243 | 806065 | 161213 | 644852 | 830304 | 166061 | 664243 | 241880 | 48376 | 193504 | 241386 | 48277 | 193109 | 241386 | 48277 | 193109 | 234020 | 46804 | 187216 | 12950 | 2590 | 10360 | 152000 | 30400 | 121600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315870 | 63174 | 252696 | 315870 | 63174 | 252696 | 315870 | 63174 | 252696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 1981146 | 396229 | 1584917 | 2200794 | 440159 | 1760635 | 2283308 | 456662 | 1826646 | 1981146 | 396229 | 1584917 | 2200794 | 440159 | 1760635 | 0 | 0 | Nelson, County of | TRUE
NT10BIX5570049 | CCI | 2012 | Q4 | Q4 - 2012 | 618984 | 123797 | 495187 | 581417 | 116283 | 465134 | 618984 | 123797 | 495187 | 830304 | 166061 | 664243 | 830304 | 166061 | 664243 | 830304 | 166061 | 664243 | 241880 | 48376 | 193504 | 241386 | 48277 | 193109 | 241386 | 48277 | 193109 | 234020 | 46804 | 187216 | 120094 | 24965 | 95129 | 234515 | 46903 | 187612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315870 | 63174 | 252696 | 315869 | 63173 | 252696 | 315869 | 63174 | 252695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 2131320 | 427209 | 1704111 | 2283308 | 456662 | 1826646 | 2283308 | 456662 | 1826646 | 2131320 | 427209 | 1704111 | 2283308 | 456662 | 1826646 | 0 | 0 | Nelson, County of | TRUE
NT10BIX5570049 | CCI | 2013 | Q1 | Q1 - 2013 | 618984 | 123797 | 495187 | 618984 | 123797 | 495187 | 618984 | 123797 | 495187 | 830304 | 166061 | 664243 | 830304 | 166061 | 664243 | 830304 | 166061 | 664243 | 241880 | 48376 | 193504 | 241386 | 48277 | 193109 | 241386 | 48277 | 193109 | 234020 | 46804 | 187216 | 224899 | 45926 | 178973 | 234515 | 46904 | 187611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315870 | 63174 | 252696 | 315869 | 63173 | 252696 | 315869 | 63173 | 252696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 2273692 | 455684 | 1818008 | 2283308 | 456662 | 1826646 | 2283308 | 456662 | 1826646 | 2273692 | 455684 | 1818008 | 2283308 | 456662 | 1826646 | 0 | 0 | Nelson, County of | TRUE
NT10BIX5570049 | CCI | 2013 | Q2 | Q2 - 2013 | 618984 | 123797 | 495187 | 618984 | 123797 | 495187 | 618984 | 123797 | 495187 | 830304 | 166061 | 664243 | 830304 | 166061 | 664243 | 830304 | 166061 | 664243 | 241880 | 48376 | 193504 | 241386 | 48277 | 193109 | 241386 | 48277 | 193109 | 234020 | 46804 | 187216 | 234515 | 46904 | 187611 | 234515 | 46904 | 187611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315870 | 63174 | 252696 | 315869 | 63173 | 252696 | 315869 | 63173 | 252696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 42250 | 8450 | 33800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283308 | 456662 | 1826646 | 2283308 | 456662 | 1826646 | 2283308 | 456662 | 1826646 | 2283308 | 456662 | 1826646 | 2283308 | 456662 | 1826646 | 2283308 | 456662 | 1826646 | 0 | 0 | Nelson, County of | TRUE
NT10BIX5570050 | CCI | 2010 | Q3 | Q3 - 2010 | 1913804 | 382761 | 1531043 | 0 | 0 | 0 | 113911 | 22782 | 91129 | 1663723 | 332745 | 1330978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762000 | 752400 | 3009600 | 21450 | 4290 | 17160 | 688716 | 137743 | 550973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229003 | 45801 | 183202 | 106709 | 21342 | 84366 | 223149 | 44630 | 178519 | 102600 | 20520 | 82080 | 41486 | 8297 | 33189 | 66821 | 13364 | 53457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534227 | 6136903 | 169645 | 33929 | 134715 | 1092597 | 218519 | 874078 | 7671130 | 1534227 | 6136903 | 169645 | 33929 | 134715 | 1092597 | 218519 | 874078 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | CCI | 2010 | Q4 | Q4 - 2010 | 1913804 | 382761 | 1531043 | 90623 | 18125 | 72498 | 554146 | 110829 | 443317 | 1663723 | 332745 | 1330978 | 2575 | 515 | 2060 | 486535 | 97307 | 389228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762000 | 752400 | 3009600 | 1093212 | 218643 | 874570 | 1688400 | 337680 | 1350720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229003 | 45801 | 183202 | 225814 | 45162 | 180652 | 229003 | 45801 | 183202 | 102600 | 20520 | 82080 | 68446 | 13689 | 54756 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534227 | 6136903 | 1480670 | 296134 | 1184536 | 3060684 | 612137 | 2448547 | 7671130 | 1534227 | 6136903 | 1480670 | 296134 | 1184536 | 3060684 | 612137 | 2448547 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | CCI | 2011 | Q1 | Q1 - 2011 | 1913804 | 382761 | 1531043 | 90623 | 18125 | 72498 | 554146 | 110829 | 443317 | 1663723 | 332745 | 1330978 | 49783 | 9957 | 39827 | 486535 | 97307 | 389228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762000 | 752400 | 3009600 | 1333526 | 266705 | 1066821 | 1880735 | 376147 | 1504588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229003 | 45801 | 183202 | 226266 | 45253 | 181013 | 229003 | 45801 | 183202 | 102600 | 20520 | 82080 | 95059 | 19012 | 76047 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534227 | 6136903 | 1795257 | 359052 | 1436206 | 3253019 | 650604 | 2602415 | 7671130 | 1534227 | 6136903 | 1795257 | 359052 | 1436206 | 3253019 | 650604 | 2602415 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | CCI | 2011 | Q2 | Q2 - 2011 | 1913804 | 382761 | 1531043 | 90623 | 18125 | 72498 | 238543 | 47709 | 190834 | 1663723 | 332745 | 1330978 | 49784 | 9957 | 39827 | 245566 | 49113 | 196453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762000 | 752400 | 3009600 | 1803428 | 361954 | 1441474 | 2385842 | 477168 | 1908674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229003 | 45801 | 183202 | 226866 | 45373 | 181493 | 229003 | 45801 | 183202 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534227 | 6136903 | 2273301 | 455929 | 1817372 | 3201554 | 640311 | 2561243 | 7671130 | 1534227 | 6136903 | 2273301 | 455929 | 1817372 | 3201554 | 640311 | 2561243 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | CCI | 2011 | Q3 | Q3 - 2011 | 1913804 | 382761 | 1531043 | 529067 | 105814 | 423253 | 1159067 | 231814 | 927253 | 1663723 | 332745 | 1330978 | 49784 | 9957 | 39827 | 881645 | 176329 | 705316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762000 | 752400 | 3009600 | 2907038 | 581407 | 2325631 | 3288181 | 657636 | 2630545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229003 | 45801 | 183202 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534227 | 6136903 | 3817563 | 763513 | 3054050 | 5660567 | 1132114 | 4528453 | 7671130 | 1534227 | 6136903 | 3817563 | 763513 | 3054050 | 5660567 | 1132114 | 4528453 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | CCI | 2011 | Q4 | Q4 - 2011 | 1913804 | 382761 | 1531043 | 1009723 | 201945 | 807778 | 1375000 | 275000 | 1100000 | 1663723 | 332745 | 1330978 | 231602 | 46320 | 185282 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762000 | 752400 | 3009600 | 3480056 | 696011 | 2784045 | 3650000 | 730000 | 2920000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229003 | 45801 | 183202 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534227 | 6136903 | 5053055 | 1010611 | 4042444 | 6806674 | 1361335 | 5445339 | 7671130 | 1534227 | 6136903 | 5053055 | 1010611 | 4042444 | 6806674 | 1361335 | 5445339 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | CCI | 2012 | Q1 | Q1 - 2012 | 1913804 | 382761 | 1531043 | 1273302 | 254661 | 1018641 | 1600000 | 320000 | 1280000 | 1663723 | 332745 | 1330978 | 453136 | 90627 | 362509 | 950000 | 190000 | 760000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3762000 | 752400 | 3009600 | 3798592 | 759718 | 3038874 | 3798592 | 759718 | 3038874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229003 | 45801 | 183202 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534227 | 6136903 | 5856704 | 1171341 | 4685363 | 6680266 | 1336053 | 5344213 | 7671130 | 1534227 | 6136903 | 5856704 | 1171341 | 4685363 | 6680266 | 1336053 | 5344213 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | CCI | 2012 | Q2 | Q2 - 2012 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1855798 | 371160 | 1484639 | 986105 | 197221 | 788884 | 1780798 | 356160 | 1424638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4210356 | 842070 | 3368285 | 4178614 | 835722 | 3342892 | 4210356 | 842071 | 3368285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534226 | 6136904 | 6769695 | 1353939 | 5415756 | 7596130 | 1519227 | 6076903 | 7671130 | 1534226 | 6136904 | 6769695 | 1353939 | 5415756 | 7596130 | 1519227 | 6076903 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | CCI | 2012 | Q3 | Q3 - 2012 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1855798 | 371160 | 1484639 | 1307862 | 261572 | 1046290 | 1830798 | 366160 | 1464638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4210356 | 842070 | 3368285 | 4180484 | 836096 | 3344388 | 4210356 | 842070 | 3368285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534226 | 6136904 | 7093322 | 1418664 | 5674658 | 7646130 | 1529226 | 6116903 | 7671130 | 1534226 | 6136904 | 7093322 | 1418664 | 5674658 | 7646130 | 1529226 | 6116903 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | CCI | 2012 | Q4 | Q4 - 2012 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1855798 | 371160 | 1484639 | 1806799 | 361359 | 1445440 | 1855798 | 371160 | 1484639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4210356 | 842070 | 3368285 | 4192063 | 838412 | 3353651 | 4210356 | 842070 | 3368285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534226 | 6136904 | 7603838 | 1520767 | 6083071 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7603838 | 1520767 | 6083071 | 7671130 | 1534226 | 6136904 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | CCI | 2013 | Q1 | Q1 - 2013 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1855798 | 371160 | 1484639 | 1855798 | 371160 | 1484639 | 1855798 | 371160 | 1484639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4210356 | 842070 | 3368285 | 4210356 | 842070 | 3368285 | 4210356 | 842070 | 3368285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | CCI | 2013 | Q2 | Q2 - 2013 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1855798 | 371160 | 1484639 | 1855798 | 371160 | 1484639 | 1855798 | 371160 | 1484639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4210356 | 842070 | 3368285 | 4210356 | 842070 | 3368285 | 4210356 | 842070 | 3368285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570050 | CCI | 2013 | Q3 | Q3 - 2013 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1273302 | 254661 | 1018641 | 1855798 | 371160 | 1484639 | 1855798 | 371160 | 1484639 | 1855798 | 371160 | 1484639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4210356 | 842070 | 3368285 | 4210356 | 842070 | 3368285 | 4210356 | 842070 | 3368285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 229074 | 45815 | 183259 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 102600 | 20520 | 82080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 7671130 | 1534226 | 6136904 | 0 | 0 | Zito Media Communications II, LLC | TRUE
NT10BIX5570051 | CCI | 2010 | Q3 | Q3 - 2010 | 1251330 | 173866 | 1077464 | 389 | 389 | 0 | 350000 | 70000 | 280000 | 1021226 | 222890 | 798336 | 58465 | 58465 | 0 | 85000 | 67000 | 18000 | 149950 | 149950 | 0 | 6369 | 6369 | 0 | 30043 | 0 | 30043 | 430230 | 22000 | 408230 | 0 | 0 | 0 | 350000 | 15000 | 335000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89893 | 0 | 0 | 0 | 15000 | 3000 | 12000 | 2992029 | 598406 | 2393923 | 86923 | 86923 | 0 | 861743 | 176700 | 685043 | 2992029 | 598406 | 2393923 | 86923 | 86923 | 0 | 861743 | 176700 | 685043 | 440000 | 0 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | CCI | 2010 | Q4 | Q4 - 2010 | 1251330 | 173866 | 1077464 | 389 | 389 | 0 | 350000 | 70000 | 280000 | 1021226 | 222890 | 798336 | 66852 | 66852 | 0 | 85000 | 67000 | 18000 | 149950 | 149950 | 0 | 11987 | 11987 | 0 | 30043 | 30043 | 0 | 430230 | 22000 | 408230 | 150 | 150 | 0 | 350000 | 15000 | 335000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89893 | 0 | 0 | 0 | 15000 | 3000 | 12000 | 2992029 | 598406 | 2393923 | 101078 | 101078 | 0 | 861743 | 206743 | 655000 | 2992029 | 598406 | 2393923 | 101078 | 101078 | 0 | 861743 | 206743 | 655000 | 440000 | 0 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | CCI | 2011 | Q1 | Q1 - 2011 | 1251330 | 173866 | 1077464 | 1576 | 1576 | 0 | 200000 | 6576 | 193424 | 1021226 | 222890 | 798336 | 75866 | 75866 | 0 | 83866 | 83866 | 0 | 149950 | 149950 | 0 | 25579 | 25579 | 0 | 37579 | 37579 | 0 | 430230 | 22000 | 408230 | 99916 | 700 | 99916 | 224916 | 700 | 224216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89893 | 0 | 0 | 0 | 0 | 0 | 0 | 2992029 | 598406 | 2393923 | 224637 | 125421 | 99916 | 578061 | 150421 | 427640 | 2992029 | 598406 | 2393923 | 224637 | 125421 | 99916 | 578061 | 150421 | 427640 | 440000 | 0 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | CCI | 2011 | Q2 | Q2 - 2011 | 1251330 | 173866 | 1077464 | 225285 | 14045 | 211240 | 565285 | 29045 | 536240 | 1021226 | 222890 | 798336 | 99278 | 99278 | 0 | 304278 | 154278 | 150000 | 149950 | 149950 | 0 | 45995 | 45995 | 0 | 60000 | 60000 | 0 | 430230 | 22000 | 408230 | 328270 | 700 | 327570 | 430230 | 22000 | 408230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 18127 | 0 | 18127 | 37627 | 0 | 37627 | 2992029 | 598406 | 2393623 | 738655 | 181718 | 556937 | 1439120 | 287023 | 1152097 | 2992029 | 598406 | 2393623 | 738655 | 181718 | 556937 | 1439120 | 287023 | 1152097 | 440000 | 0 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | CCI | 2011 | Q3 | Q3 - 2011 | 1251330 | 173866 | 1077464 | 526671 | 20898 | 505773 | 691671 | 40898 | 650773 | 1021226 | 222890 | 798336 | 133670 | 130424 | 3246 | 275670 | 195424 | 80246 | 149950 | 149950 | 0 | 47839 | 47839 | 0 | 80000 | 80000 | 0 | 430230 | 22000 | 408230 | 407644 | 5813 | 401831 | 430230 | 22000 | 408230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 38641 | 0 | 38641 | 45641 | 0 | 45641 | 2992029 | 598406 | 2393623 | 1196165 | 226674 | 969491 | 1564912 | 360022 | 1204890 | 2992029 | 598406 | 2393623 | 1196165 | 226674 | 969491 | 1564912 | 360022 | 1204890 | 440000 | 0 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | CCI | 2011 | Q4 | Q4 - 2011 | 1251330 | 173866 | 1077464 | 612327 | 37937 | 574390 | 912327 | 80000 | 832327 | 1021226 | 222890 | 798336 | 202937 | 182471 | 20466 | 275000 | 204534 | 70466 | 149950 | 149950 | 0 | 51073 | 51073 | 0 | 80000 | 80000 | 0 | 430230 | 22000 | 408230 | 435231 | 7322 | 427909 | 435231 | 7322 | 427909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 42605 | 0 | 42605 | 54740 | 2000 | 52740 | 2992029 | 598406 | 2393623 | 1385873 | 300503 | 1085370 | 1798998 | 395556 | 1403442 | 2992029 | 598406 | 2393623 | 1385873 | 300503 | 1085370 | 1798998 | 395556 | 1403442 | 440000 | 4541 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | CCI | 2012 | Q1 | Q1 - 2012 | 1251330 | 173866 | 1077464 | 771785 | 46764 | 725021 | 921785 | 96764 | 825021 | 1021226 | 222890 | 798336 | 229260 | 206110 | 23150 | 247000 | 222000 | 25000 | 149950 | 149950 | 0 | 52875 | 52875 | 0 | 80000 | 80000 | 0 | 430230 | 22000 | 408230 | 435231 | 7322 | 427909 | 435231 | 7322 | 427909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 51215 | 0 | 51215 | 55307 | 0 | 55307 | 2992029 | 598406 | 2393623 | 1582066 | 334771 | 1247295 | 1781023 | 427786 | 1353237 | 2992029 | 598406 | 2393623 | 1582066 | 334771 | 1247295 | 1781023 | 427786 | 1353237 | 440000 | 10249 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | CCI | 2012 | Q2 | Q2 - 2012 | 1251330 | 173866 | 1077464 | 867116 | 51762 | 815354 | 1100000 | 70000 | 1030000 | 1021226 | 222890 | 798336 | 247276 | 203061 | 44215 | 290000 | 230000 | 60000 | 149950 | 149950 | 0 | 55076 | 55076 | 0 | 80000 | 80000 | 0 | 430230 | 22000 | 408230 | 435231 | 7322 | 427909 | 435231 | 7322 | 427909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 56310 | 1621 | 54689 | 74000 | 2000 | 72000 | 2992029 | 598406 | 2393623 | 1702709 | 340542 | 1362167 | 2020931 | 411022 | 1609909 | 2992029 | 598406 | 2393623 | 1702709 | 340542 | 1362167 | 2020931 | 411022 | 1609909 | 440000 | 16316 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | CCI | 2012 | Q3 | Q3 - 2012 | 1251330 | 173866 | 1077464 | 902527 | 52894 | 849633 | 1100000 | 65000 | 1035000 | 931456 | 222890 | 798336 | 275312 | 221785 | 53527 | 350000 | 265785 | 84215 | 149950 | 149950 | 0 | 55162 | 55162 | 0 | 60000 | 60000 | 0 | 520000 | 22000 | 408230 | 476071 | 20294 | 455777 | 520000 | 25000 | 495000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 57303 | 2614 | 54689 | 75000 | 8000 | 67000 | 2992029 | 598406 | 2393623 | 1808075 | 374449 | 1433626 | 2146700 | 445485 | 1701215 | 2992029 | 598406 | 2393623 | 1808075 | 374449 | 1433626 | 2146700 | 445485 | 1701215 | 440000 | 22559 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | CCI | 2012 | Q4 | Q4 - 2012 | 1251330 | 173866 | 1077464 | 1069577 | 59200 | 1010377 | 1136664 | 59200 | 1077464 | 931456 | 222890 | 708566 | 327388 | 243803 | 83585 | 377388 | 263803 | 113585 | 149950 | 149950 | 0 | 57693 | 57693 | 0 | 70000 | 70000 | 0 | 520000 | 22000 | 498000 | 510316 | 20294 | 490022 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 69917 | 8629 | 61288 | 83629 | 8629 | 75000 | 2992029 | 598406 | 2393623 | 2076591 | 411319 | 1665272 | 2229381 | 443626 | 1785755 | 2992029 | 598406 | 2393623 | 2076591 | 411319 | 1665272 | 2229381 | 443626 | 1785755 | 440000 | 29614 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | CCI | 2013 | Q1 | Q1 - 2013 | 1251330 | 173866 | 1077464 | 1145424 | 70848 | 1074576 | 1245424 | 90848 | 1154576 | 931456 | 222890 | 708566 | 383316 | 272426 | 110890 | 483316 | 292426 | 190890 | 149950 | 149950 | 0 | 58458 | 58458 | 0 | 78458 | 78458 | 0 | 520000 | 22000 | 498000 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 70745 | 2749 | 67996 | 74725 | 3500 | 71225 | 2992029 | 598406 | 2393623 | 2219643 | 446475 | 1773168 | 2443623 | 507226 | 1936397 | 2992029 | 598406 | 2393623 | 2219643 | 446475 | 1773168 | 2443623 | 507226 | 1936397 | 440000 | 36408 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | CCI | 2013 | Q2 | Q2 - 2013 | 1351330 | 173866 | 1177464 | 1213610 | 74017 | 1139593 | 1251330 | 80000 | 1171330 | 831456 | 222890 | 608566 | 428843 | 288134 | 140709 | 485000 | 320000 | 165000 | 149950 | 149950 | 0 | 59150 | 59150 | 0 | 80000 | 80000 | 0 | 520000 | 22000 | 498000 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 73386 | 2942 | 70444 | 97593 | 4000 | 93593 | 2992029 | 598406 | 2393623 | 2336689 | 466237 | 1870452 | 2475623 | 525994 | 1949629 | 2992029 | 598406 | 2393623 | 2336689 | 466237 | 1870452 | 2475623 | 525994 | 1949629 | 440000 | 7374 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | CCI | 2013 | Q3 | Q3 - 2013 | 1351330 | 173866 | 1177464 | 1235850 | 76390 | 1159460 | 1435850 | 81779 | 1354071 | 831456 | 222890 | 608566 | 485816 | 329040 | 156776 | 500816 | 332040 | 168776 | 149950 | 149950 | 0 | 59454 | 59454 | 0 | 84454 | 84454 | 0 | 520000 | 22000 | 498000 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 75176 | 4732 | 70444 | 89176 | 6032 | 83144 | 2992029 | 598406 | 2393623 | 2417996 | 511610 | 1906386 | 2671996 | 546299 | 2125697 | 2992029 | 598406 | 2393623 | 2417996 | 511610 | 1906386 | 2671996 | 546299 | 2125697 | 440000 | 50367 | First Step Internet, L.L.C. | TRUE
NT10BIX5570051 | CCI | 2013 | Q4 | Q4 - 2013 | 1351330 | 173866 | 1177464 | 1289850 | 86469 | 1203381 | 1289850 | 86469 | 1203381 | 831456 | 222890 | 608566 | 502853 | 346077 | 156776 | 525000 | 346077 | 178923 | 149950 | 149950 | 0 | 69486 | 61341 | 8145 | 100000 | 65000 | 35000 | 520000 | 22000 | 498000 | 520000 | 20294 | 499706 | 520000 | 20294 | 499706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 21700 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97593 | 8000 | 89593 | 76429 | 5985 | 70444 | 76429 | 5985 | 70444 | 2992029 | 598406 | 2393623 | 2500318 | 541866 | 1958452 | 2552979 | 545525 | 2007454 | 2992029 | 598406 | 2393623 | 2500318 | 541866 | 1958452 | 2552979 | 545525 | 2007454 | 440000 | 62157 | First Step Internet, L.L.C. | TRUE
NT10BIX5570053 | CCI | 2010 | Q3 | Q3 - 2010 | 5225979 | 0 | 5225979 | 671 | 0 | 671 | 1974675 | 0 | 1974675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499200 | 0 | 499200 | 4063 | 0 | 4063 | 148777 | 0 | 148777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759456 | 264000 | 495456 | 100596 | 100596 | 0 | 504672 | 176635 | 328037 | 2553604 | 1328400 | 1225204 | 18060 | 13560 | 4500 | 1696917 | 882397 | 814520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354013 | 0 | 354013 | 0 | 0 | 0 | 199821 | 0 | 199821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670740 | 430800 | 239940 | 33333 | 2968 | 30365 | 32383 | 12629 | 19753 | 10062992 | 2023200 | 8039792 | 156723 | 117124 | 39599 | 4557245 | 1071661 | 3485583 | 10062992 | 2023200 | 8039792 | 156723 | 117124 | 39599 | 4557245 | 1071661 | 3485583 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | CCI | 2010 | Q4 | Q4 - 2010 | 5225979 | 0 | 5225979 | 1115625 | 0 | 1115625 | 2350223 | 0 | 2350223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499200 | 0 | 499200 | 20725 | 0 | 20725 | 189696 | 0 | 189696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759456 | 264000 | 495456 | 293476 | 264000 | 29476 | 658388 | 264000 | 394388 | 2553604 | 1328400 | 1225204 | 25192 | 25192 | 0 | 2213975 | 1151267 | 1062708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354013 | 0 | 354013 | 7620 | 0 | 7620 | 140330 | 0 | 140330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670740 | 430800 | 239940 | 58158 | 15688 | 42470 | 146624 | 93839 | 52785 | 10062992 | 2023200 | 8039792 | 1520796 | 304880 | 1215916 | 5699236 | 1509106 | 4190130 | 10062992 | 2023200 | 8039792 | 1520796 | 304880 | 1215916 | 5699236 | 1509106 | 4190130 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | CCI | 2011 | Q1 | Q1 - 2011 | 5225979 | 0 | 5225979 | 2152922 | 6868 | 2146053 | 5159914 | 0 | 5159914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499200 | 0 | 499200 | 36648 | 0 | 36648 | 298147 | 0 | 298147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759456 | 264000 | 495456 | 459811 | 421759 | 38052 | 685639 | 239974 | 445665 | 2553604 | 1328400 | 1225204 | 0 | 0 | 0 | 2305905 | 1199071 | 1106834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354013 | 0 | 354013 | 14418 | 153 | 14265 | 204478 | 0 | 204478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670740 | 430800 | 239940 | 75297 | 30442 | 44855 | 219093 | 140220 | 78873 | 10062992 | 2023200 | 8039792 | 2739096 | 459222 | 2279873 | 8873176 | 1579265 | 7293911 | 10062992 | 2023200 | 8039792 | 2739096 | 459222 | 2279873 | 8873176 | 1579265 | 7293911 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | CCI | 2011 | Q2 | Q2 - 2011 | 5225979 | 0 | 5225979 | 4365807 | 217758 | 4148050 | 5215109 | 0 | 5215109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499200 | 0 | 499200 | 71162 | 0 | 71162 | 361248 | 0 | 361248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759456 | 264000 | 495456 | 473971 | 264000 | 209971 | 678102 | 237336 | 440766 | 2553604 | 1328400 | 1225204 | 358321 | 358321 | 0 | 2298368 | 1195152 | 1103217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354013 | 0 | 354013 | 64103 | 9609 | 54494 | 212519 | 0 | 212519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670740 | 430800 | 239940 | 150593 | 77947 | 72646 | 391887 | 250808 | 141079 | 10062992 | 2023200 | 8039792 | 5483957 | 927635 | 4556323 | 9157233 | 1683296 | 7473938 | 10062992 | 2023200 | 8039792 | 5483957 | 927635 | 4556323 | 9157233 | 1683296 | 7473938 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | CCI | 2011 | Q3 | Q3 - 2011 | 5225979 | 0 | 5225979 | 5431528 | 325293 | 5106235 | 5536035 | 310056 | 5225979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499200 | 0 | 499200 | 85945 | 0 | 85945 | 464256 | 0 | 464256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759456 | 264000 | 495456 | 473971 | 264000 | 209971 | 691105 | 264000 | 427105 | 2553604 | 1328400 | 1225204 | 557053 | 541372 | 15681 | 2374852 | 1234923 | 1139929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354013 | 0 | 354013 | 67588 | 13094 | 54494 | 329232 | 13094 | 316138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670740 | 430800 | 239940 | 205515 | 130089 | 75426 | 596959 | 382054 | 214905 | 10062992 | 2023200 | 8039792 | 6821600 | 1273848 | 5547752 | 9992439 | 2204127 | 7788312 | 10062992 | 2023200 | 8039792 | 6821600 | 1273848 | 5547752 | 9992439 | 2204127 | 7788312 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | CCI | 2011 | Q4 | Q4 - 2011 | 5225979 | 0 | 5225979 | 5334299 | 429473 | 4904826 | 6535044 | 745278 | 5789766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499200 | 0 | 499200 | 221455 | 114908 | 106547 | 245745 | 127408 | 118337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759456 | 264000 | 495456 | 1033135 | 337030 | 696105 | 1043135 | 347030 | 696105 | 2553604 | 1328400 | 1225204 | 713045 | 353977 | 359068 | 1399150 | 618176 | 780974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354013 | 0 | 354013 | 128904 | 59439 | 69465 | 138904 | 69439 | 69465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670740 | 430800 | 239940 | 233414 | 153531 | 79883 | 251852 | 161969 | 89883 | 10062992 | 2023200 | 8039792 | 7664252 | 1448358 | 6215894 | 9613830 | 2069300 | 7544530 | 10062992 | 2023200 | 8039792 | 7664252 | 1448358 | 6215894 | 9613830 | 2069300 | 7544530 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | CCI | 2012 | Q1 | Q1 - 2012 | 5789766 | 0 | 5789766 | 5578366 | 447508 | 5130858 | 5987536 | 491951 | 5495585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268147 | 0 | 268147 | 260003 | 136487 | 123516 | 315902 | 146229 | 169673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188651 | 492546 | 696105 | 1057673 | 361568 | 696105 | 1090418 | 394313 | 696105 | 2349110 | 1262684 | 1086426 | 1229876 | 634524 | 595352 | 1819685 | 851564 | 968121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138904 | 69439 | 69465 | 129389 | 59924 | 69465 | 129389 | 59924 | 69465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328414 | 198531 | 129883 | 235544 | 154986 | 80558 | 261761 | 160872 | 100889 | 10062992 | 2023200 | 8039792 | 8490851 | 1794997 | 6695854 | 9604691 | 2104853 | 7499838 | 10062992 | 2023200 | 8039792 | 8490851 | 1794997 | 6695854 | 9604691 | 2104853 | 7499838 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | CCI | 2012 | Q2 | Q2 - 2012 | 5789766 | 0 | 5789766 | 6162001 | 510602 | 5651399 | 6286349 | 588827 | 5697521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268147 | 0 | 268147 | 271658 | 143476 | 128182 | 328973 | 154136 | 174837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188651 | 492546 | 696105 | 1057673 | 361568 | 696105 | 1101332 | 405227 | 696105 | 2349110 | 1262684 | 1086426 | 1415656 | 789402 | 626254 | 1726807 | 947163 | 779645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138904 | 69439 | 69465 | 129389 | 59924 | 69465 | 129389 | 59924 | 69465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328414 | 198531 | 129883 | 246378 | 157872 | 88506 | 273723 | 171425 | 102298 | 10062992 | 2023200 | 8039792 | 9282755 | 2022844 | 7259911 | 9846573 | 2326702 | 7519871 | 10062992 | 2023200 | 8039792 | 9282755 | 2022844 | 7259911 | 9846573 | 2326702 | 7519871 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | CCI | 2012 | Q3 | Q3 - 2012 | 5789766 | 0 | 5789766 | 6168864 | 517465 | 5651399 | 5789766 | 0 | 5789766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268147 | 0 | 268147 | 289568 | 143476 | 146092 | 329568 | 143476 | 186092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188651 | 492546 | 696105 | 1057673 | 361568 | 696105 | 1188651 | 492546 | 696105 | 2349110 | 1262684 | 1086426 | 1877048 | 975298 | 901750 | 2170958 | 1119208 | 1051750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138904 | 69439 | 69465 | 129389 | 59924 | 69465 | 138904 | 69439 | 69465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328414 | 198531 | 129883 | 260333 | 171827 | 88506 | 299414 | 198531 | 100883 | 10062992 | 2023200 | 8039792 | 9782875 | 2229558 | 7553317 | 9917261 | 2023200 | 7894061 | 10062992 | 2023200 | 8039792 | 9782875 | 2229558 | 7553317 | 9917261 | 2023200 | 7894061 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | CCI | 2012 | Q4 | Q4 - 2012 | 5789766 | 0 | 5789766 | 5775626 | 95751 | 5679875 | 5885517 | 95751 | 5789766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268147 | 0 | 268147 | 330798 | 163225 | 167573 | 431372 | 163225 | 268147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188651 | 492546 | 696105 | 1057673 | 361568 | 696105 | 1057673 | 361568 | 696105 | 2349110 | 1262684 | 1086426 | 2071725 | 1160911 | 910814 | 2247337 | 1160911 | 1086426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138904 | 69439 | 69465 | 129389 | 59924 | 69465 | 129389 | 59924 | 69465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328414 | 198531 | 129883 | 284204 | 181821 | 102383 | 311704 | 181821 | 129883 | 10062992 | 2023200 | 8039792 | 9649415 | 2023200 | 7626215 | 10062992 | 2023200 | 8039792 | 10062992 | 2023200 | 8039792 | 9649415 | 2023200 | 7626215 | 10062992 | 2023200 | 8039792 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570053 | CCI | 2013 | Q1 | Q1 - 2013 | 5789766 | 0 | 5789766 | 6484248 | 662937 | 5821311 | 6484248 | 662937 | 5821311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268147 | 0 | 268147 | 378338 | 138686 | 239652 | 378338 | 138686 | 239652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188651 | 492546 | 696105 | 1322880 | 580036 | 742844 | 1322880 | 580036 | 742844 | 2349110 | 1262684 | 1086426 | 2386782 | 1354356 | 1032426 | 2386782 | 1354356 | 1032426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138904 | 69439 | 69465 | 133086 | 60171 | 72915 | 133086 | 60171 | 72915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328414 | 198531 | 129883 | 311220 | 180576 | 130644 | 311220 | 180576 | 130644 | 10062992 | 2023200 | 8039792 | 11016554 | 2976762 | 8039792 | 11016554 | 2976762 | 8039792 | 10062992 | 2023200 | 8039792 | 11016554 | 2976762 | 8039792 | 11016554 | 2976762 | 8039792 | 0 | 0 | PTI Pacifica, Inc., dba: IT&E | TRUE
NT10BIX5570054 | CCI | 2010 | Q3 | Q3 - 2010 | 705331 | 141066 | 564265 | 0 | 0 | 0 | 0 | 0 | 0 | 1018203 | 203641 | 814562 | 0 | 0 | 0 | 0 | 0 | 0 | 82756 | 16553 | 66212 | 0 | 0 | 0 | 25000 | 5000 | 20000 | 25567 | 5113 | 20454 | 0 | 0 | 0 | 3000 | 600 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171560 | 34312 | 137248 | 0 | 0 | 0 | 50000 | 10000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57750 | 11550 | 46200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061167 | 412235 | 1648941 | 0 | 0 | 0 | 78000 | 15600 | 62400 | 2061167 | 412235 | 1648941 | 0 | 0 | 0 | 78000 | 15600 | 62400 | 0 | 0 | Page County Broadband Authority | TRUE
NT10BIX5570054 | CCI | 2010 | Q4 | Q4 - 2010 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 67494 | 13499 | 53995 | 453730 | 90746 | 362984 | 0 | 0 | 0 | 6125 | 1225 | 4900 | 320362 | 64073 | 256289 | 58815 | 11763 | 47052 | 77544 | 15509 | 62035 | 374522 | 74904 | 299618 | 0 | 0 | 0 | 31250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 0 | 0 | 0 | 126763 | 25353 | 101410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 58815 | 11763 | 47052 | 309176 | 55586 | 222340 | 2061176 | 412235 | 1648941 | 58815 | 11763 | 47052 | 309176 | 55586 | 222340 | 0 | 0 | Page County Broadband Authority | TRUE
NT10BIX5570054 | CCI | 2011 | Q1 | Q1 - 2011 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 0 | 0 | 0 | 453730 | 90746 | 362984 | 0 | 0 | 0 | 0 | 0 | 0 | 320362 | 64073 | 256289 | 74524 | 14905 | 59619 | 102110 | 20422 | 81688 | 374522 | 74904 | 299618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 15761 | 3152 | 12609 | 118761 | 23752 | 95009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 1200 | 240 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 90285 | 18057 | 72228 | 222071 | 44414 | 177657 | 2061176 | 412235 | 1648941 | 90285 | 18057 | 72228 | 222071 | 44414 | 177657 | 0 | 0 | Page County Broadband Authority | TRUE
NT10BIX5570054 | CCI | 2011 | Q2 | Q2 - 2011 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 0 | 0 | 0 | 453730 | 90746 | 362984 | 0 | 0 | 0 | 0 | 0 | 0 | 320362 | 64073 | 256289 | 103364 | 20673 | 82691 | 118935 | 23787 | 95148 | 374522 | 74904 | 299618 | 0 | 0 | 0 | 62500 | 12500 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 28010 | 5602 | 22408 | 121354 | 24271 | 97083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 436 | 87 | 349 | 436 | 87 | 349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 131810 | 26362 | 105448 | 303225 | 60645 | 242580 | 2061176 | 412235 | 1648941 | 131810 | 26362 | 105448 | 303225 | 60645 | 242580 | 0 | 0 | Page County Broadband Authority | TRUE
NT10BIX5570054 | CCI | 2011 | Q3 | Q3 - 2011 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 0 | 0 | 0 | 453730 | 90746 | 362984 | 0 | 0 | 0 | 0 | 0 | 0 | 320362 | 64073 | 256289 | 151104 | 30221 | 120883 | 162000 | 32400 | 129600 | 374522 | 74904 | 299618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 32595 | 6526 | 26069 | 38500 | 7700 | 30800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 436 | 87 | 349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 183699 | 36747 | 146952 | 200936 | 40187 | 160749 | 2061176 | 412235 | 1648941 | 183699 | 36747 | 146952 | 200936 | 40187 | 160749 | 0 | 0 | Page County Broadband Authority | TRUE
NT10BIX5570054 | CCI | 2011 | Q4 | Q4 - 2011 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 320619 | 64124 | 256495 | 453730 | 90746 | 362984 | 0 | 0 | 0 | 0 | 0 | 0 | 320362 | 64073 | 256289 | 126342 | 25109 | 101233 | 142000 | 28400 | 113600 | 374522 | 74904 | 299618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 37117 | 7423 | 29694 | 44500 | 8900 | 35600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 163459 | 32532 | 130927 | 589619 | 117924 | 471695 | 2061176 | 412235 | 1648941 | 163459 | 32532 | 130927 | 589619 | 117924 | 471695 | 0 | 0 | Page County Broadband Authority | TRUE
NT10BIX5570054 | CCI | 2012 | Q1 | Q1 - 2012 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 641237 | 128247 | 512990 | 453730 | 90746 | 362984 | 30746 | 6149 | 24597 | 35000 | 7000 | 28000 | 320362 | 64073 | 256289 | 149442 | 29730 | 119712 | 150000 | 30000 | 120000 | 374522 | 74904 | 299618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 187618 | 37523 | 150095 | 188825 | 37765 | 151060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 13679 | 2736 | 10943 | 22000 | 4000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 381485 | 76138 | 305347 | 1037062 | 207012 | 830050 | 2061176 | 412235 | 1648941 | 381485 | 76138 | 305347 | 1037062 | 207012 | 830050 | 0 | 0 | Page County Broadband Authority | TRUE
NT10BIX5570054 | CCI | 2012 | Q2 | Q2 - 2012 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 600000 | 128247 | 512990 | 453730 | 90746 | 362984 | 30746 | 6149 | 24597 | 300000 | 60000 | 240000 | 320362 | 64073 | 256289 | 150309 | 29902 | 120407 | 200000 | 40000 | 160000 | 374522 | 74904 | 299618 | 53834 | 10767 | 43067 | 374522 | 74904 | 299618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 139886 | 27977 | 111909 | 188825 | 37765 | 151060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 13805 | 2761 | 11044 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 388580 | 77556 | 311024 | 1745847 | 357416 | 1429668 | 2061176 | 412235 | 1648941 | 388580 | 77556 | 311024 | 1745847 | 357416 | 1429668 | 0 | 0 | Page County Broadband Authority | TRUE
NT10BIX5570054 | CCI | 2012 | Q3 | Q3 - 2012 | 641237 | 128247 | 512990 | 0 | 0 | 0 | 641237 | 128247 | 512990 | 453730 | 90746 | 362984 | 30746 | 6149 | 24597 | 453730 | 90746 | 362984 | 320362 | 64073 | 256289 | 156249 | 31090 | 125160 | 160000 | 32000 | 128000 | 374522 | 74904 | 299618 | 59681 | 11936 | 47745 | 300000 | 60000 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188825 | 37765 | 151060 | 139886 | 27977 | 111909 | 188825 | 37765 | 151060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 13805 | 2761 | 11044 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 400367 | 79913 | 320455 | 1826292 | 365258 | 1461034 | 2061176 | 412235 | 1648941 | 400367 | 79913 | 320455 | 1826292 | 365258 | 1461034 | 0 | 0 | Page County Broadband Authority | TRUE
NT10BIX5570054 | CCI | 2012 | Q4 | Q4 - 2012 | 620746 | 124149 | 496597 | 292465 | 58493 | 233972 | 641237 | 128247 | 512990 | 543551 | 108710 | 434841 | 254279 | 50856 | 203423 | 453730 | 90746 | 362984 | 330363 | 66073 | 264290 | 172247 | 34289 | 137958 | 300000 | 60000 | 240000 | 55000 | 11000 | 44000 | 288 | 58 | 230 | 55000 | 11000 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451516 | 90303 | 361213 | 200109 | 40022 | 160087 | 451516 | 90303 | 361213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 12000 | 48000 | 13805 | 2761 | 11044 | 60000 | 12000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 933193 | 186479 | 746714 | 1961483 | 392296 | 1569187 | 2061176 | 412235 | 1648941 | 933193 | 186479 | 746714 | 1961483 | 392296 | 1569187 | 0 | 0 | Page County Broadband Authority | TRUE
NT10BIX5570054 | CCI | 2013 | Q1 | Q1 - 2013 | 620746 | 124149 | 496597 | 292466 | 58493 | 233973 | 292466 | 58493 | 233973 | 543551 | 108710 | 434841 | 1003867 | 200773 | 803094 | 1003867 | 200773 | 803094 | 330363 | 66073 | 264290 | 201976 | 40236 | 161740 | 201976 | 40236 | 161740 | 55000 | 11000 | 44000 | 288 | 58 | 230 | 288 | 58 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451516 | 90303 | 361213 | 203787 | 40757 | 163030 | 203787 | 40757 | 163030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 12000 | 48000 | 13805 | 2761 | 11044 | 13805 | 2761 | 11044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061176 | 412235 | 1648941 | 1716189 | 343078 | 1373111 | 1716189 | 343078 | 1373111 | 2061176 | 412235 | 1648941 | 1716189 | 343078 | 1373111 | 1716189 | 343078 | 1373111 | 0 | 0 | Page County Broadband Authority | TRUE
NT10BIX5570055 | CCI | 2010 | Q3 | Q3 - 2010 | 2253000 | 574166 | 1678833 | 80030 | 79590 | 440 | 114328 | 89879 | 24449 | 36819229 | 12171576 | 24647652 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 85849 | 0 | 85849 | 100000 | 0 | 100000 | 890000 | 250000 | 640000 | 148088 | 67760 | 80328 | 211554 | 86799 | 124754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996657 | 800000 | 1196657 | 36961 | 34422 | 2539 | 102801 | 54174 | 48627 | 9600 | 0 | 9600 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 0 | 3529823 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 0 | 387500 | 385958 | 113456 | 272502 | 551368 | 163079 | 388289 | 45985809 | 13795742 | 32190065 | 736886 | 295228 | 441658 | 1184551 | 393931 | 790619 | 45985809 | 13795742 | 32190065 | 736886 | 295228 | 441658 | 1184551 | 393931 | 790619 | 0 | 0 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | CCI | 2010 | Q4 | Q4 - 2010 | 2253000 | 490958 | 1762042 | 695226 | 208568 | 486658 | 150000 | 45000 | 105000 | 36736021 | 12171577 | 24564444 | 484822 | 145447 | 339375 | 1065000 | 319500 | 745500 | 100000 | 0 | 100000 | 99145 | 0 | 99145 | 855 | 0 | 855 | 890000 | 250000 | 640000 | 820315 | 246094 | 574220 | 69685 | 3906 | 65780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 800000 | 1196658 | 544432 | 163330 | 381102 | 250000 | 75000 | 175000 | 9600 | 0 | 9600 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 0 | 3529823 | 100132 | 0 | 10132 | 199089 | 0 | 199089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 0 | 387500 | 5427 | 0 | 5427 | 7500 | 0 | 7500 | 45902602 | 13712535 | 32190067 | 2749499 | 763439 | 1896059 | 1746629 | 443406 | 1303224 | 45902602 | 13712535 | 32190067 | 2749499 | 763439 | 1896059 | 1746629 | 443406 | 1303224 | 0 | 0 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | CCI | 2011 | Q1 | Q1 - 2011 | 2253000 | 490958 | 1762042 | 461458 | 138437 | 323021 | 611458 | 183437 | 428021 | 36736021 | 12171577 | 24564444 | 1202437 | 362360 | 840077 | 2267437 | 681860 | 1585577 | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 890000 | 250000 | 640000 | 948448 | 284534 | 663914 | 1018133 | 288440 | 729694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 800000 | 1196658 | 642010 | 192603 | 449407 | 892010 | 267603 | 624407 | 9600 | 0 | 9600 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 0 | 3529823 | 155764 | 46729 | 109035 | 354853 | 46729 | 308124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 0 | 387500 | 5427 | 0 | 5427 | 12927 | 0 | 12927 | 45902602 | 13712535 | 32190067 | 3515544 | 1024663 | 2490881 | 5261318 | 1468069 | 3793250 | 45902602 | 13712535 | 32190067 | 3515544 | 1024663 | 2490881 | 5261318 | 1468069 | 3793250 | 0 | 0 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | CCI | 2011 | Q2 | Q2 - 2011 | 2253000 | 490958 | 1762042 | 650533 | 195160 | 455374 | 1261991 | 378597 | 883395 | 36736021 | 12171577 | 24564444 | 3177490 | 954876 | 2222614 | 5444926 | 1635107 | 3809819 | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 890000 | 250000 | 640000 | 1374752 | 412425 | 962326 | 2392886 | 700865 | 1692020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 800000 | 1196658 | 1003139 | 300951 | 702188 | 1895149 | 568554 | 1326595 | 9600 | 0 | 9600 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 0 | 3529823 | 168853 | 50646 | 118207 | 523706 | 97375 | 426331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 0 | 387500 | 5427 | 0 | 5427 | 18354 | 0 | 18354 | 45902602 | 13712535 | 32190067 | 6480194 | 1914058 | 4566136 | 11641512 | 3380498 | 8261014 | 45902602 | 13712535 | 32190067 | 6480194 | 1914058 | 4566136 | 11641512 | 3380498 | 8261014 | 0 | 0 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | CCI | 2011 | Q3 | Q3 - 2011 | 2253000 | 490958 | 1762042 | 1090650 | 327196 | 763454 | 1814880 | 427607 | 1387273 | 36736021 | 12171577 | 24564444 | 8331618 | 2501113 | 5830505 | 13776544 | 4136220 | 9640324 | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 890000 | 250000 | 640000 | 750000 | 225000 | 525000 | 890000 | 250000 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 800000 | 1196658 | 1245939 | 373791 | 872148 | 1996658 | 800000 | 1196658 | 9600 | 0 | 9600 | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 0 | 3529823 | 1081356 | 324397 | 756959 | 2055235 | 556814 | 1498421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 0 | 387500 | 5427 | 0 | 5427 | 18354 | 0 | 18354 | 45902602 | 13712535 | 32190067 | 12604990 | 3751497 | 8853493 | 20656171 | 6170641 | 14485530 | 45902602 | 13712535 | 32190067 | 12604990 | 3751497 | 8853493 | 20656171 | 6170641 | 14485530 | 56160 | 56160 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | CCI | 2011 | Q4 | Q4 - 2011 | 2253000 | 673041 | 1579959 | 1090650 | 327197 | 763453 | 1555590 | 466678 | 1088912 | 36736021 | 10974192 | 25761829 | 12597411 | 3809939 | 8787472 | 22252855 | 6706572 | 15546282 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 750000 | 225000 | 525000 | 850000 | 255000 | 595000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 596464 | 1400194 | 1245939 | 373791 | 872148 | 1496179 | 448863 | 1047316 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 1094389 | 427624 | 666765 | 1906200 | 671168 | 1235033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 5427 | 1628 | 3799 | 5427 | 1628 | 3799 | 45902602 | 13712535 | 32190067 | 16883816 | 5195052 | 11688764 | 28175851 | 8582650 | 19593201 | 45902602 | 13712535 | 32190067 | 16883816 | 5195052 | 11688764 | 28175851 | 8582650 | 19593201 | 56160 | 56160 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | CCI | 2012 | Q1 | Q1 - 2012 | 2253000 | 673041 | 1579959 | 1136675 | 339560 | 797115 | 1364010 | 407472 | 956538 | 36736021 | 10974193 | 25761829 | 22881640 | 6856529 | 16025111 | 27457964 | 8227832 | 19230132 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 344661 | 102961 | 241700 | 413593 | 123553 | 290040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 596464 | 1400194 | 1065378 | 318261 | 747117 | 1278454 | 381914 | 896540 | 9600 | 2868 | 6732 | 2100 | 627 | 1473 | 2519 | 752 | 1767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 2978117 | 889656 | 2088461 | 3275927 | 978621 | 2297306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 327616 | 97869 | 229747 | 360377 | 107656 | 252721 | 45902602 | 13712536 | 32190067 | 28836187 | 8635336 | 20200851 | 34252844 | 10257673 | 23995171 | 45902602 | 13712536 | 32190067 | 28836187 | 8635336 | 20200851 | 34252844 | 10257673 | 23995171 | 20983 | 77173 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | CCI | 2012 | Q2 | Q2 - 2012 | 2253000 | 673041 | 1579959 | 1221645 | 364943 | 856702 | 1608339 | 480461 | 1127878 | 36736021 | 10974193 | 25761829 | 28253261 | 8440128 | 19813133 | 33108617 | 9890574 | 23218043 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 596464 | 1400194 | 1701092 | 508169 | 1192923 | 1996658 | 596464 | 1400194 | 9600 | 2868 | 6732 | 9302 | 2779 | 6523 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 3150575 | 941175 | 2209400 | 3529823 | 1054468 | 2475355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 327616 | 97869 | 229747 | 387500 | 115758 | 271742 | 45902602 | 13712536 | 32190067 | 35653491 | 10650807 | 25002684 | 41630537 | 12436337 | 29194200 | 45902602 | 13712536 | 32190067 | 35653491 | 10650807 | 25002684 | 41630537 | 12436337 | 29194200 | 0 | 148070 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | CCI | 2012 | Q3 | Q3 - 2012 | 2253000 | 673041 | 1579959 | 1292068 | 385981 | 906087 | 1737006 | 518898 | 1218108 | 36736021 | 10974193 | 25761828 | 31108412 | 9293050 | 21815362 | 35757306 | 10681820 | 25075486 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265870 | 624129 | 831014 | 248250 | 582764 | 890000 | 265871 | 624129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 596464 | 1400194 | 1597349 | 477178 | 1120171 | 1996658 | 596464 | 1400194 | 9600 | 2868 | 6732 | 1500 | 448 | 1052 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 3203550 | 957000 | 2246550 | 3529823 | 1054468 | 2475355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 302671 | 90417 | 212254 | 387500 | 115758 | 271742 | 45902602 | 13712535 | 32190066 | 38436564 | 11482197 | 26954367 | 44407893 | 13266020 | 31141873 | 45902602 | 13712535 | 32190066 | 38436564 | 11482197 | 26954367 | 44407893 | 13266020 | 31141873 | 0 | 197444 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | CCI | 2012 | Q4 | Q4 - 2012 | 2253000 | 673041 | 1579959 | 1747233 | 521953 | 1225280 | 1747407 | 522005 | 1225402 | 36736021 | 10974192 | 25761829 | 32781201 | 9792764 | 22988437 | 33941555 | 10178374 | 23763181 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 596464 | 1400194 | 1856538 | 554606 | 1301932 | 1895650 | 554661 | 1340989 | 9600 | 2868 | 6732 | 9302 | 2779 | 6523 | 9302 | 2779 | 6523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 3296172 | 984669 | 2311503 | 3296501 | 984767 | 2311734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 303467 | 90655 | 212812 | 303497 | 90664 | 212833 | 45902602 | 13712535 | 32190067 | 40983913 | 12243170 | 28740743 | 42183912 | 12628994 | 29554918 | 45902602 | 13712535 | 32190067 | 40983913 | 12243170 | 28740743 | 42183912 | 12628994 | 29554918 | 0 | 265596 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | CCI | 2013 | Q1 | Q1 - 2013 | 2253000 | 673041 | 1579959 | 1842764 | 550491 | 1292273 | 1887011 | 563709 | 1323302 | 36736021 | 10974193 | 25761829 | 36064314 | 11035997 | 25028317 | 36496119 | 11146356 | 25349763 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 596464 | 1400194 | 1996658 | 596464 | 1400196 | 1996658 | 596464 | 1400194 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 3529824 | 1054468 | 2475356 | 3529824 | 1054468 | 2475355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 327485 | 97830 | 229655 | 327956 | 97970 | 229985 | 45902602 | 13712536 | 32190067 | 44760645 | 13633862 | 31126785 | 45237168 | 13757579 | 31479587 | 45902602 | 13712536 | 32190067 | 44760645 | 13633862 | 31126785 | 45237168 | 13757579 | 31479587 | 0 | 304098 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | CCI | 2013 | Q2 | Q2 - 2013 | 2253000 | 673041 | 1579959 | 1965316 | 673041 | 1292275 | 2253000 | 673041 | 1579959 | 36736021 | 10974193 | 25761829 | 39746810 | 14116247 | 25630563 | 39948657 | 14186828 | 25761829 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996658 | 596464 | 1400194 | 1996659 | 596465 | 1400194 | 1996659 | 596465 | 1400194 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 3529823 | 1054468 | 2475355 | 3529823 | 1054468 | 2475355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 345413 | 115758 | 229655 | 387500 | 115758 | 271742 | 45902602 | 13712536 | 32190067 | 48583621 | 16854591 | 31729030 | 49115239 | 16925172 | 32190067 | 45902602 | 13712536 | 32190067 | 48583621 | 16854591 | 31729030 | 49115239 | 16925172 | 32190067 | 0 | 442827 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | CCI | 2013 | Q3 | Q3 - 2013 | 1842763 | 550490 | 1292273 | 1997314 | 705041 | 1292273 | 1997314 | 705041 | 1292273 | 37146257 | 11096743 | 26049515 | 40876810 | 15246247 | 25630563 | 41545762 | 15496247 | 26049515 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996659 | 596465 | 1400194 | 1996659 | 596465 | 1400194 | 1996659 | 596465 | 1400194 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529823 | 1054468 | 2475355 | 3529823 | 1054468 | 2475355 | 3529823 | 1054468 | 2475355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 345416 | 115759 | 229657 | 387501 | 115759 | 271742 | 45902602 | 13712536 | 32190067 | 49745622 | 18016592 | 31729030 | 50456659 | 18266592 | 32190067 | 45902602 | 13712536 | 32190067 | 49745622 | 18016592 | 31729030 | 50456659 | 18266592 | 32190067 | 0 | 567230 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570055 | CCI | 2013 | Q4 | Q4 - 2013 | 1842764 | 550491 | 1292273 | 2058006 | 765733 | 1292273 | 2058006 | 765733 | 1292273 | 37014569 | 11057402 | 25957167 | 52050350 | 26093183 | 25957167 | 52050350 | 26093183 | 25957167 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 100000 | 29873 | 70127 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 890000 | 265871 | 624129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1996657 | 596464 | 1400193 | 1996654 | 596461 | 1400193 | 1996654 | 596461 | 1400193 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 9600 | 2868 | 6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3661512 | 1093808 | 2567704 | 16358199 | 13790495 | 2567704 | 16358199 | 13790495 | 2567704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387500 | 115758 | 271742 | 387500 | 115758 | 271742 | 387500 | 115758 | 271742 | 45902602 | 13712535 | 32190067 | 73850309 | 41660242 | 32190067 | 73850309 | 41660242 | 32190067 | 45902602 | 13712535 | 32190067 | 73850309 | 41660242 | 32190067 | 73850309 | 41660242 | 32190067 | 0 | 1335979 | Navajo Tribal Utility Authority Company | TRUE
NT10BIX5570056 | CCI | 2010 | Q3 | Q3 - 2010 | 963842 | 192768 | 771074 | 0 | 0 | 0 | 0 | 0 | 0 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 64398 | 12880 | 51518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 7350 | 29400 | 0 | 0 | 0 | 11025 | 2205 | 8820 | 6591 | 1318 | 5273 | 0 | 0 | 0 | 1978 | 396 | 1582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8325 | 1665 | 6660 | 0 | 0 | 0 | 0 | 0 | 0 | 1230167 | 246033 | 984134 | 0 | 0 | 0 | 77401 | 15481 | 61920 | 1230167 | 246033 | 984134 | 0 | 0 | 0 | 77401 | 15481 | 61920 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | CCI | 2010 | Q4 | Q4 - 2010 | 963842 | 192768 | 771074 | 0 | 0 | 0 | 481921 | 96384 | 385537 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 7350 | 29400 | 0 | 0 | 0 | 11025 | 2205 | 8820 | 6591 | 1318 | 5273 | 0 | 0 | 0 | 1978 | 396 | 1582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8325 | 1665 | 6660 | 0 | 0 | 0 | 0 | 0 | 0 | 1230167 | 246033 | 984134 | 0 | 0 | 0 | 709583 | 141917 | 567666 | 1230167 | 246033 | 984134 | 0 | 0 | 0 | 709583 | 141917 | 567666 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | CCI | 2011 | Q1 | Q1 - 2011 | 963842 | 192768 | 771074 | 0 | 0 | 0 | 0 | 0 | 0 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 7350 | 29400 | 7350 | 7350 | 0 | 7350 | 7350 | 0 | 6591 | 1318 | 5273 | 1318 | 1318 | 0 | 1318 | 1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8325 | 1665 | 6660 | 1665 | 1665 | 0 | 1665 | 1665 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | CCI | 2011 | Q2 | Q2 - 2011 | 963842 | 192768 | 771074 | 0 | 0 | 0 | 0 | 0 | 0 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 7350 | 29400 | 7350 | 7350 | 0 | 7350 | 7350 | 0 | 6591 | 1318 | 5273 | 1318 | 1318 | 0 | 1318 | 1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8325 | 1665 | 6660 | 1665 | 1665 | 0 | 1665 | 1665 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | CCI | 2011 | Q3 | Q3 - 2011 | 963842 | 192768 | 771074 | 0 | 0 | 0 | 0 | 0 | 0 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 7350 | 29400 | 7350 | 7350 | 0 | 7350 | 7350 | 0 | 6591 | 1318 | 5273 | 1318 | 1318 | 0 | 1318 | 1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8325 | 1665 | 6660 | 1665 | 1665 | 0 | 1665 | 1665 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | CCI | 2011 | Q4 | Q4 - 2011 | 963842 | 192768 | 771074 | 0 | 0 | 0 | 0 | 0 | 0 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 7350 | 29400 | 7350 | 7350 | 0 | 7350 | 7350 | 0 | 6591 | 1318 | 5273 | 1318 | 1318 | 0 | 1318 | 1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8325 | 1665 | 6660 | 1665 | 1665 | 0 | 1665 | 1665 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570056 | CCI | 2012 | Q1 | Q1 - 2012 | 963842 | 192768 | 771074 | 0 | 0 | 0 | 0 | 0 | 0 | 214659 | 42932 | 171727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 7350 | 29400 | 7350 | 7350 | 0 | 7350 | 7350 | 0 | 6591 | 1318 | 5273 | 1318 | 1318 | 0 | 1318 | 1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8325 | 1665 | 6660 | 1665 | 1665 | 0 | 1665 | 1665 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 1230167 | 246033 | 984134 | 10333 | 10333 | 0 | 10333 | 10333 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | CCI | 2010 | Q3 | Q3 - 2010 | 992417 | 198483 | 793934 | 0 | 0 | 0 | 198483 | 39697 | 158786 | 572424 | 114485 | 457939 | 0 | 0 | 0 | 114485 | 22897 | 91588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 21280 | 85120 | 0 | 0 | 0 | 21280 | 4256 | 17024 | 7375 | 1475 | 5900 | 0 | 0 | 0 | 1475 | 295 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22200 | 4440 | 17760 | 0 | 0 | 0 | 4440 | 888 | 3552 | 1700816 | 340163 | 1360653 | 0 | 0 | 0 | 340163 | 68033 | 272130 | 1700816 | 340163 | 1360653 | 0 | 0 | 0 | 340163 | 68033 | 272130 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | CCI | 2010 | Q4 | Q4 - 2010 | 992417 | 198483 | 793934 | 0 | 0 | 0 | 198483 | 39697 | 158786 | 572424 | 114485 | 457939 | 0 | 0 | 0 | 114485 | 22897 | 91588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 21280 | 85120 | 0 | 0 | 0 | 21280 | 4256 | 17024 | 7375 | 1475 | 5900 | 0 | 0 | 0 | 1475 | 295 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22200 | 4440 | 17760 | 0 | 0 | 0 | 4440 | 888 | 3552 | 1700816 | 340163 | 1360653 | 0 | 0 | 0 | 340163 | 68033 | 272130 | 1700816 | 340163 | 1360653 | 0 | 0 | 0 | 340163 | 68033 | 272130 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | CCI | 2011 | Q1 | Q1 - 2011 | 992417 | 198483 | 793934 | 0 | 0 | 0 | 0 | 0 | 0 | 572424 | 114485 | 457939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 21280 | 85120 | 21280 | 21280 | 0 | 21280 | 21280 | 0 | 7375 | 1475 | 5900 | 1475 | 1475 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22200 | 4440 | 17780 | 4440 | 4440 | 0 | 4440 | 4440 | 0 | 1700816 | 340163 | 1360673 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 1700816 | 340163 | 1360673 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | CCI | 2011 | Q2 | Q2 - 2011 | 992417 | 198483 | 793934 | 0 | 0 | 0 | 0 | 0 | 0 | 572424 | 114485 | 457939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 21280 | 85120 | 21280 | 21280 | 0 | 21280 | 21280 | 0 | 7375 | 1475 | 5900 | 1475 | 1475 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22200 | 4440 | 17760 | 4440 | 4440 | 0 | 4440 | 4440 | 0 | 1700816 | 340163 | 1360653 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 1700816 | 340163 | 1360653 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | CCI | 2011 | Q3 | Q3 - 2011 | 992417 | 198483 | 793934 | 0 | 0 | 0 | 0 | 0 | 0 | 572424 | 114485 | 457939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 21280 | 85120 | 21280 | 21280 | 0 | 21280 | 21280 | 0 | 7375 | 1475 | 5900 | 1475 | 1475 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22220 | 4440 | 17780 | 4440 | 4440 | 0 | 4440 | 4440 | 0 | 1700836 | 340163 | 1360673 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 1700836 | 340163 | 1360673 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | CCI | 2011 | Q4 | Q4 - 2011 | 992417 | 198483 | 793934 | 0 | 0 | 0 | 0 | 0 | 0 | 572424 | 114485 | 457939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 21280 | 85120 | 21280 | 21280 | 0 | 21280 | 21280 | 0 | 7375 | 1475 | 5900 | 1475 | 1475 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22220 | 4460 | 17760 | 4440 | 4440 | 0 | 4440 | 4440 | 0 | 1700836 | 340183 | 1360653 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 1700836 | 340183 | 1360653 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570057 | CCI | 2012 | Q1 | Q1 - 2012 | 992417 | 198483 | 793934 | 0 | 0 | 0 | 0 | 0 | 0 | 572424 | 114485 | 457939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106400 | 21280 | 85120 | 21280 | 21280 | 0 | 21280 | 21280 | 0 | 7375 | 1475 | 5900 | 1475 | 1475 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22200 | 4440 | 17780 | 4440 | 4440 | 0 | 4440 | 4440 | 0 | 1700816 | 340163 | 1360673 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 1700816 | 340163 | 1360673 | 27195 | 27195 | 0 | 27195 | 27195 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570058 | CCI | 2010 | Q3 | Q3 - 2010 | 468660 | 93732 | 374928 | 0 | 0 | 0 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 0 | 0 | 0 | 45744 | 9149 | 36595 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 1000 | 200 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 0 | 0 | 0 | 527904 | 105581 | 422323 | 669135 | 133827 | 535308 | 0 | 0 | 0 | 527904 | 105581 | 422323 | 0 | 0 | City of Williamstown | TRUE
NT10BIX5570058 | CCI | 2010 | Q4 | Q4 - 2010 | 468660 | 93732 | 374928 | 61385 | 16734 | 44651 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 0 | 0 | 0 | 90000 | 18000 | 72000 | 5000 | 1000 | 4000 | 11708 | 7708 | 4000 | 11708 | 7708 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 5925 | 0 | 5925 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 79018 | 24442 | 54576 | 582868 | 121940 | 460928 | 669135 | 133827 | 535308 | 79018 | 24442 | 54576 | 582868 | 121940 | 460928 | 0 | 0 | City of Williamstown | TRUE
NT10BIX5570058 | CCI | 2011 | Q1 | Q1 - 2011 | 468660 | 93732 | 374928 | 330804 | 120720 | 210085 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 0 | 0 | 0 | 182975 | 36595 | 146380 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 11425 | 1145 | 10000 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 347229 | 122865 | 224085 | 669135 | 133827 | 535308 | 669135 | 133827 | 535308 | 347229 | 122865 | 224085 | 669135 | 133827 | 535308 | 0 | 0 | City of Williamstown | TRUE
NT10BIX5570058 | CCI | 2011 | Q2 | Q2 - 2011 | 468660 | 93732 | 374928 | 353650 | 70730 | 282920 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 138647 | 27729 | 110918 | 182975 | 36595 | 146380 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 509797 | 101959 | 407838 | 669135 | 133827 | 535308 | 669135 | 133827 | 535308 | 509797 | 101959 | 407838 | 669135 | 133827 | 535308 | 0 | 0 | City of Williamstown | TRUE
NT10BIX5570058 | CCI | 2011 | Q3 | Q3 - 2011 | 468660 | 93732 | 374928 | 355280 | 71056 | 284224 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 138647 | 27729 | 110919 | 182975 | 36595 | 146380 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 511427 | 102285 | 409143 | 669135 | 133827 | 535308 | 669135 | 133827 | 535308 | 511427 | 102285 | 409143 | 669135 | 133827 | 535308 | 0 | 7666 | City of Williamstown | TRUE
NT10BIX5570058 | CCI | 2011 | Q4 | Q4 - 2011 | 468660 | 93732 | 374928 | 387676 | 77535 | 310141 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 182975 | 36595 | 146380 | 182975 | 36595 | 146380 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 588151 | 117630 | 470521 | 669135 | 133827 | 535308 | 669135 | 133827 | 535308 | 588151 | 117630 | 470521 | 669135 | 133827 | 535308 | 0 | 24960 | City of Williamstown | TRUE
NT10BIX5570058 | CCI | 2012 | Q1 | Q1 - 2012 | 468660 | 93732 | 374928 | 387676 | 77535 | 310141 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 182975 | 36595 | 146380 | 182975 | 36595 | 146380 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 588151 | 117630 | 470521 | 669135 | 133827 | 535308 | 669135 | 133827 | 535308 | 588151 | 117630 | 470521 | 669135 | 133827 | 535308 | 0 | 24576 | City of Williamstown | TRUE
NT10BIX5570058 | CCI | 2012 | Q2 | Q2 - 2012 | 468660 | 93732 | 374928 | 387676 | 77535 | 310141 | 468660 | 93732 | 374928 | 182975 | 36595 | 146380 | 182975 | 36595 | 146380 | 182975 | 36595 | 146380 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 12500 | 2500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669135 | 133827 | 535308 | 588151 | 117630 | 470521 | 669135 | 133827 | 535308 | 669135 | 133827 | 535308 | 588151 | 117630 | 470521 | 669135 | 133827 | 535308 | 0 | 33175 | City of Williamstown | TRUE
NT10BIX5570058 | CCI | 2012 | Q3 | Q3 - 2012 | 384844 | 76969 | 307875 | 385446 | 77570 | 307875 | 0 | 0 | 0 | 210652 | 42130 | 168522 | 210652 | 42130 | 168521 | 0 | 0 | 0 | 10500 | 2100 | 8400 | 18174 | 9774 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18237 | 3647 | 14590 | 18437 | 3848 | 14590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624233 | 124846 | 499387 | 632709 | 133322 | 499386 | 0 | 0 | 0 | 624233 | 124846 | 499387 | 632709 | 133322 | 499386 | 0 | 0 | 0 | 0 | 37609 | City of Williamstown | TRUE
NT10BIX5570059 | CCI | 2010 | Q3 | Q3 - 2010 | 1183317 | 236663 | 946654 | 0 | 0 | 0 | 0 | 0 | 0 | 25505940 | 5101188 | 20404752 | 0 | 0 | 0 | 0 | 0 | 0 | 258100 | 51620 | 206480 | 2809 | 562 | 2248 | 5000 | 1000 | 4000 | 1073800 | 214760 | 859040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448373 | 689675 | 2758698 | 126469 | 25294 | 101175 | 400000 | 80000 | 320000 | 666811 | 133362 | 533449 | 15775 | 3155 | 12620 | 30000 | 6000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 0 | 0 | 0 | 0 | 0 | 0 | 34072297 | 6814459 | 27257838 | 145053 | 29011 | 116043 | 435000 | 87000 | 348000 | 34072297 | 6814459 | 27257838 | 145053 | 29011 | 116043 | 435000 | 87000 | 348000 | 2316050 | 0 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | CCI | 2010 | Q4 | Q4 - 2010 | 1183317 | 236663 | 946654 | 77653 | 77653 | 0 | 500000 | 100000 | 400000 | 25505940 | 5101188 | 20404752 | 1713370 | 1710462 | 2908 | 1713370 | 1710462 | 2908 | 258100 | 51620 | 206480 | 8124 | 1625 | 6499 | 10000 | 2000 | 8000 | 1073800 | 214760 | 859040 | 184279 | 184279 | 0 | 184279 | 184279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448373 | 689675 | 2758698 | 542521 | 108504 | 434017 | 1000000 | 200000 | 800000 | 666811 | 133362 | 533449 | 42127 | 8425 | 33702 | 75000 | 15000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 0 | 0 | 0 | 0 | 0 | 0 | 34072297 | 6814459 | 27257838 | 2568074 | 2090948 | 477126 | 3482649 | 2211741 | 1270908 | 34072297 | 6814459 | 27257838 | 2568074 | 2090948 | 477126 | 3482649 | 2211741 | 1270908 | 0 | 0 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | CCI | 2011 | Q1 | Q1 - 2011 | 1183317 | 236663 | 946654 | 77653 | 77653 | 0 | 500000 | 100000 | 400000 | 25505940 | 5101188 | 20404752 | 1739662 | 1715721 | 23941 | 2250000 | 1750000 | 500000 | 258100 | 51620 | 206480 | 15597 | 3119 | 12477 | 25000 | 5000 | 20000 | 1073800 | 214760 | 859040 | 184279 | 184279 | 0 | 184279 | 184279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448373 | 689675 | 2758698 | 883020 | 176604 | 706416 | 1300000 | 260000 | 1040000 | 666811 | 133362 | 533449 | 91195 | 18239 | 72956 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 0 | 0 | 0 | 0 | 0 | 0 | 34072297 | 6814459 | 27257838 | 2991406 | 2175615 | 815790 | 4409279 | 2329279 | 2080000 | 34072297 | 6814459 | 27257838 | 2991406 | 2175615 | 815790 | 4409279 | 2329279 | 2080000 | 0 | 0 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | CCI | 2011 | Q2 | Q2 - 2011 | 1183317 | 236663 | 946654 | 77653 | 77653 | 0 | 100000 | 75000 | 25000 | 25505940 | 5101188 | 20404752 | 2199321 | 1807652 | 391669 | 3200000 | 2000000 | 1200000 | 258100 | 51620 | 206480 | 22816 | 4563 | 18253 | 25000 | 5000 | 20000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 190000 | 185000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448373 | 689675 | 2758698 | 1503780 | 300756 | 1203024 | 2100000 | 420000 | 1680000 | 666811 | 133362 | 533449 | 147892 | 29578 | 118314 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 0 | 0 | 0 | 0 | 0 | 0 | 34072297 | 6814459 | 27257838 | 4137993 | 2404931 | 1733062 | 5815000 | 2725000 | 3090000 | 34072297 | 6814459 | 27257838 | 4137993 | 2404931 | 1733062 | 5815000 | 2725000 | 3090000 | 0 | 0 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | CCI | 2011 | Q3 | Q3 - 2011 | 1183317 | 236663 | 946654 | 77653 | 77653 | 0 | 100000 | 75000 | 25000 | 25505940 | 5101188 | 20404752 | 4189958 | 2035847 | 2154111 | 7000000 | 2000000 | 5000000 | 258100 | 51620 | 206480 | 21462 | 4292 | 17170 | 30000 | 6000 | 24000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 250000 | 200000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448373 | 689675 | 2758698 | 2094852 | 418970 | 1675882 | 2400000 | 480000 | 1920000 | 666811 | 133362 | 533449 | 190273 | 38055 | 152218 | 250000 | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 0 | 0 | 0 | 0 | 0 | 0 | 34072297 | 6814459 | 27257838 | 6760729 | 2759546 | 4001183 | 10030000 | 2811000 | 7219000 | 34072297 | 6814459 | 27257838 | 6760729 | 2759546 | 4001183 | 10030000 | 2811000 | 7219000 | 0 | 0 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | CCI | 2011 | Q4 | Q4 - 2011 | 1183317 | 236663 | 946654 | 78610 | 77781 | 829 | 100000 | 99000 | 1000 | 25505940 | 5101188 | 20404752 | 6380558 | 2323878 | 4056680 | 8500000 | 2700000 | 5800000 | 258100 | 51620 | 206480 | 52569 | 10514 | 42055 | 80000 | 16000 | 64000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 190000 | 188000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3448373 | 689675 | 2758698 | 2838694 | 567739 | 2270955 | 3100000 | 620000 | 2480000 | 666811 | 133362 | 533449 | 256166 | 51233 | 204933 | 325000 | 55000 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 15323 | 3064 | 12259 | 25000 | 5000 | 20000 | 34072297 | 6814459 | 27257838 | 9808451 | 3218938 | 6589513 | 12320000 | 3683000 | 8637000 | 34072297 | 6814459 | 27257838 | 9808451 | 3218938 | 6589513 | 12320000 | 3683000 | 8637000 | 0 | 0 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | CCI | 2012 | Q1 | Q1 - 2012 | 3200000 | 640000 | 2560000 | 78889 | 77817 | 1072 | 80100 | 79000 | 1100 | 21737630 | 4347526 | 17390104 | 7772820 | 2506940 | 5265880 | 11000000 | 3000000 | 8000000 | 258100 | 51620 | 206480 | 101141 | 20228 | 80913 | 150000 | 30000 | 120000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 190000 | 188000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200000 | 1040000 | 4160000 | 3280052 | 656010 | 2624042 | 3600000 | 720000 | 2880000 | 666811 | 133362 | 533449 | 333414 | 66683 | 266731 | 420000 | 84000 | 336000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 15323 | 3064 | 12259 | 20000 | 4000 | 16000 | 34072297 | 6814459 | 27257838 | 11768170 | 3515471 | 8252699 | 15460100 | 4105000 | 11355100 | 34072297 | 6814459 | 27257838 | 11768170 | 3515471 | 8252699 | 15460100 | 4105000 | 11355100 | 0 | 0 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | CCI | 2012 | Q2 | Q2 - 2012 | 3200000 | 640000 | 2560000 | 142179 | 86221 | 55958 | 2900000 | 580000 | 2320000 | 21737630 | 4347526 | 17390104 | 12263437 | 3097389 | 9166048 | 16800000 | 3600000 | 13200000 | 258100 | 51620 | 206480 | 187601 | 37520 | 150081 | 230000 | 46000 | 184000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 190000 | 188000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200000 | 1040000 | 4160000 | 3540321 | 708064 | 2832257 | 3900000 | 780000 | 3120000 | 666811 | 133362 | 533449 | 393016 | 78603 | 314413 | 450000 | 90000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935956 | 387191 | 1548765 | 15324 | 3065 | 12259 | 15324 | 3065 | 12259 | 34072297 | 6814459 | 27257838 | 16728409 | 4195591 | 12532818 | 24485324 | 5287065 | 19198259 | 34072297 | 6814459 | 27257838 | 16728409 | 4195591 | 12532818 | 24485324 | 5287065 | 19198259 | 0 | 0 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | CCI | 2012 | Q3 | Q3 - 2012 | 3200000 | 640000 | 2560000 | 1221132 | 229478 | 991654 | 2600000 | 520000 | 2080000 | 21737630 | 4347526 | 17390104 | 14749607 | 3424283 | 11325324 | 17500000 | 3500000 | 14000000 | 258100 | 51620 | 206480 | 231901 | 46380 | 185521 | 250000 | 50000 | 200000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 190000 | 188000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6200000 | 1240000 | 4960000 | 5319522 | 1063904 | 4255618 | 6000000 | 1200000 | 4800000 | 666811 | 133362 | 533449 | 468734 | 93747 | 374987 | 575000 | 115000 | 460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935956 | 187191 | 748765 | 15324 | 3065 | 12259 | 15324 | 3065 | 12259 | 34072297 | 6814459 | 27257838 | 22192751 | 5045586 | 17147165 | 27130324 | 5576065 | 21554259 | 34072297 | 6814459 | 27257838 | 22192751 | 5045586 | 17147165 | 27130324 | 5576065 | 21554259 | 0 | 0 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | CCI | 2012 | Q4 | Q4 - 2012 | 3200000 | 640000 | 2560000 | 3483948 | 529921 | 2954027 | 3500000 | 530000 | 2970000 | 21737630 | 4347526 | 17390104 | 18904020 | 3970526 | 14933494 | 20000000 | 4020000 | 15080000 | 258100 | 51620 | 206480 | 267511 | 53502 | 214009 | 270000 | 54000 | 216000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 190000 | 188000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6200000 | 1240000 | 4960000 | 7200978 | 1440196 | 5760782 | 7500000 | 1500000 | 6000000 | 666811 | 133362 | 533449 | 524850 | 104970 | 419880 | 620000 | 124000 | 496000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935956 | 187191 | 748765 | 15324 | 3065 | 12259 | 15323 | 3064 | 12259 | 34072297 | 6814459 | 27257838 | 30583162 | 6286909 | 24296253 | 32095323 | 6419064 | 24776259 | 34072297 | 6814459 | 27257838 | 30583162 | 6286909 | 24296253 | 32095323 | 6419064 | 24776259 | 0 | 0 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | CCI | 2013 | Q1 | Q1 - 2013 | 3200000 | 640000 | 2560000 | 3791871 | 570806 | 3221065 | 3800000 | 575000 | 3225000 | 21737630 | 4347526 | 17390104 | 19869895 | 4097524 | 15772371 | 20500000 | 4137577 | 16362423 | 258100 | 51620 | 206480 | 272840 | 54568 | 218272 | 275000 | 55000 | 220000 | 1073800 | 214760 | 859040 | 186531 | 184729 | 1802 | 186531 | 184729 | 1802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6200000 | 1240000 | 4960000 | 7487646 | 1497529 | 5990117 | 8000000 | 1600000 | 6400000 | 666811 | 133362 | 533449 | 583512 | 116702 | 466810 | 600000 | 120000 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935956 | 187191 | 748765 | 15324 | 3065 | 12259 | 15324 | 3065 | 12259 | 34072297 | 6814459 | 27257838 | 32207619 | 6524923 | 25682696 | 33376855 | 6675371 | 26701484 | 34072297 | 6814459 | 27257838 | 32207619 | 6524923 | 25682696 | 33376855 | 6675371 | 26701484 | 0 | 0 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | CCI | 2013 | Q2 | Q2 - 2013 | 3588747 | 717749 | 2870998 | 3588747 | 532461 | 3056286 | 3588747 | 532461 | 3056286 | 21153596 | 4230718 | 16922878 | 21429121 | 4323689 | 17105432 | 21429121 | 4323689 | 17105432 | 290270 | 58054 | 232216 | 290270 | 58054 | 232216 | 290270 | 58054 | 232216 | 292921 | 58584 | 234337 | 186531 | 184729 | 1802 | 186531 | 184729 | 1802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6064628 | 1212926 | 4851702 | 6064628 | 1212926 | 4851702 | 6064628 | 1212926 | 4851702 | 666811 | 133363 | 533448 | 625941 | 125188 | 500753 | 625941 | 125188 | 500753 | 2000000 | 400000 | 1600000 | 1871735 | 374347 | 1497388 | 1871735 | 374347 | 1497388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15324 | 3065 | 12259 | 15324 | 3065 | 12259 | 15324 | 3065 | 12259 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 0 | 278 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570059 | CCI | 2013 | Q3 | Q3 - 2013 | 3204993 | 682669 | 2522324 | 3588747 | 532461 | 3056286 | 3588747 | 532461 | 3056286 | 21153596 | 3824940 | 17328656 | 21429121 | 4323689 | 17105432 | 21429121 | 4323689 | 17105432 | 258100 | 51620 | 206480 | 290270 | 58054 | 232216 | 290270 | 58054 | 232216 | 921395 | 184279 | 737116 | 186531 | 184729 | 1802 | 186531 | 184729 | 1802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5867402 | 1537588 | 4329814 | 6064628 | 1212926 | 4851702 | 6064628 | 1212926 | 4851702 | 666811 | 133363 | 533448 | 625941 | 125188 | 500753 | 625941 | 125188 | 500753 | 2000000 | 400000 | 1600000 | 1871735 | 374347 | 1497388 | 1871735 | 374347 | 1497388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15324 | 3065 | 12259 | 15324 | 3065 | 12259 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 34072297 | 6814459 | 27257838 | 0 | 19119 | Public Utility District of Pend Oreille County | TRUE
NT10BIX5570060 | CCI | 2010 | Q3 | Q3 - 2010 | 6040947 | 1208190 | 4832757 | 0 | 0 | 0 | 3382930 | 676586 | 2706344 | 2495000 | 499000 | 1966000 | 0 | 0 | 0 | 311875 | 62375 | 249500 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 62632 | 12526 | 50106 | 1508445 | 301689 | 1206756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 286000 | 0 | 0 | 0 | 179200 | 35840 | 143360 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 48720 | 9744 | 38976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 5438 | 1088 | 4350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 222632 | 44526 | 178106 | 5596608 | 1119322 | 4477286 | 11840098 | 2368020 | 9472078 | 222632 | 44526 | 178106 | 5596608 | 1119322 | 4477286 | 400000 | 0 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | CCI | 2010 | Q4 | Q4 - 2010 | 6040947 | 1208190 | 4832757 | 0 | 0 | 0 | 3382930 | 676586 | 2706344 | 2495000 | 499000 | 1996000 | 0 | 0 | 0 | 324350 | 64870 | 259480 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 181248 | 36250 | 144998 | 538730 | 107746 | 430984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 0 | 0 | 0 | 0 | 0 | 0 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 8700 | 1740 | 6960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 341248 | 68250 | 272998 | 4414710 | 882942 | 3531768 | 11840098 | 2368020 | 9472078 | 341248 | 68250 | 272998 | 4414710 | 882942 | 3531768 | 400000 | 0 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | CCI | 2011 | Q1 | Q1 - 2011 | 6040947 | 1208190 | 4832757 | 781819 | 156364 | 625455 | 1812284 | 362457 | 1449827 | 2495000 | 499000 | 1996000 | 88423 | 17685 | 70738 | 374250 | 74850 | 299400 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 422293 | 84459 | 337834 | 808095 | 161619 | 646476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 0 | 0 | 0 | 0 | 0 | 0 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 13050 | 2610 | 10440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 1452535 | 290508 | 1162027 | 3167679 | 633536 | 2534143 | 11840098 | 2368020 | 9472078 | 1452535 | 290508 | 1162027 | 3167679 | 633536 | 2534143 | 700000 | 0 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | CCI | 2011 | Q2 | Q2 - 2011 | 6040947 | 1208190 | 4832757 | 838078 | 167616 | 670462 | 1812284 | 362457 | 1449827 | 2495000 | 499000 | 1996000 | 657217 | 131443 | 525774 | 1497000 | 299400 | 1197600 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 543166 | 108633 | 434533 | 1616191 | 323238 | 1292953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 0 | 0 | 0 | 0 | 0 | 0 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 26100 | 5220 | 20880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 2198461 | 439692 | 1758769 | 5111575 | 1022315 | 4089260 | 11840098 | 2368020 | 9472078 | 2198461 | 439692 | 1758769 | 5111575 | 1022315 | 4089260 | 970000 | 0 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | CCI | 2011 | Q3 | Q3 - 2011 | 6040947 | 1208190 | 4832757 | 876852 | 175370 | 701482 | 2718426 | 543685 | 2174741 | 2495000 | 499000 | 1996000 | 1243149 | 248630 | 994519 | 1871250 | 374250 | 1497000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 565332 | 113067 | 452265 | 2020238 | 404048 | 1616190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 12692 | 2538 | 10154 | 96000 | 19200 | 76800 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 32625 | 6525 | 26100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 2858025 | 571605 | 2286420 | 6898539 | 1379708 | 5518831 | 11840098 | 2368020 | 9472078 | 2858025 | 571605 | 2286420 | 6898539 | 1379708 | 5518831 | 1200000 | 0 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | CCI | 2011 | Q4 | Q4 - 2011 | 6040947 | 1208190 | 4832757 | 1187791 | 237558 | 950233 | 4530710 | 906142 | 3624568 | 2495000 | 499000 | 1996000 | 1689452 | 337890 | 1351562 | 1871250 | 374250 | 1497000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 1009794 | 201959 | 807835 | 2020238 | 404048 | 1616190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 30402 | 6081 | 24321 | 96000 | 19200 | 76800 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 32625 | 6525 | 26100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 4077439 | 815488 | 3261951 | 8710823 | 1742165 | 6968658 | 11840098 | 2368020 | 9472078 | 4077439 | 815488 | 3261951 | 8710823 | 1742165 | 6968658 | 1516090 | 0 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | CCI | 2012 | Q1 | Q1 - 2012 | 6040947 | 1208190 | 4832757 | 4398879 | 879775 | 3519104 | 4711939 | 942388 | 3769551 | 2495000 | 499000 | 1996000 | 2191640 | 438328 | 1753312 | 2195600 | 439120 | 1756480 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 1505748 | 301150 | 1204598 | 2020238 | 404048 | 1616190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 30402 | 6081 | 24321 | 240000 | 48000 | 192000 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 65250 | 13050 | 52200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 32625 | 6525 | 26100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 8286669 | 1657334 | 6629335 | 9425652 | 1885131 | 7540521 | 11840098 | 2368020 | 9472078 | 8286669 | 1657334 | 6629335 | 9425652 | 1885131 | 7540521 | 0 | 0 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | CCI | 2012 | Q2 | Q2 - 2012 | 6040947 | 1208190 | 4832757 | 4399118 | 879824 | 3519294 | 4711939 | 942388 | 3769551 | 2495000 | 499000 | 1996000 | 2037834 | 407566 | 1630268 | 2195600 | 439120 | 1756480 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 1875916 | 375183 | 1500733 | 2020238 | 404048 | 1616190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 30402 | 6081 | 24321 | 240000 | 48000 | 192000 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 65250 | 13050 | 52200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 32625 | 6525 | 26100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 8503270 | 1700654 | 6802616 | 9425652 | 1885131 | 7540521 | 11840098 | 2368020 | 9472078 | 8503270 | 1700654 | 6802616 | 9425652 | 1885131 | 7540521 | 0 | 5899 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | CCI | 2012 | Q3 | Q3 - 2012 | 6040947 | 1208190 | 4832757 | 4402878 | 880576 | 3522302 | 4711939 | 942388 | 3769551 | 2495000 | 499000 | 1996000 | 2048761 | 409752 | 1639009 | 2195600 | 439120 | 1756480 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 1972449 | 394490 | 1577959 | 2020238 | 404048 | 1616190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 30402 | 6081 | 24321 | 240000 | 48000 | 192000 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 65250 | 13050 | 52200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 32625 | 6525 | 26100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 8614490 | 1722899 | 6891591 | 9425652 | 1885131 | 7540521 | 11840098 | 2368020 | 9472078 | 8614490 | 1722899 | 6891591 | 9425652 | 1885131 | 7540521 | 0 | 25807 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | CCI | 2012 | Q4 | Q4 - 2012 | 6040947 | 1208190 | 4832757 | 4464272 | 892854 | 3571418 | 4832758 | 966552 | 3866206 | 2495000 | 499000 | 1996000 | 2071384 | 414277 | 1657107 | 2370250 | 474050 | 1896200 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 2089183 | 417837 | 1671346 | 2558968 | 511794 | 2047174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 48689 | 9738 | 38951 | 240000 | 48000 | 192000 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 65250 | 13050 | 52200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 32625 | 6525 | 26100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 8833528 | 1766706 | 7066822 | 10259851 | 2051971 | 8207880 | 11840098 | 2368020 | 9472078 | 8833528 | 1766706 | 7066822 | 10259851 | 2051971 | 8207880 | 0 | 54490 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | CCI | 2013 | Q1 | Q1 - 2013 | 6040947 | 1208190 | 4832757 | 5050441 | 1010088 | 4040353 | 6040947 | 1208189 | 4832758 | 2495000 | 499000 | 1996000 | 2430703 | 486141 | 1944562 | 2495000 | 499000 | 1996000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 2476450 | 495290 | 1981160 | 2693651 | 538730 | 2154921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 50099 | 10020 | 40079 | 320000 | 64000 | 256000 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 10167693 | 2033539 | 8134154 | 11840098 | 2368019 | 9472079 | 11840098 | 2368020 | 9472078 | 10167693 | 2033539 | 8134154 | 11840098 | 2368019 | 9472079 | 0 | 98133 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570060 | CCI | 2013 | Q2 | Q2 - 2013 | 6040947 | 1208190 | 4832757 | 6483335 | 1299686 | 5183649 | 6483335 | 1299686 | 5183649 | 2495000 | 499000 | 1996000 | 2691879 | 538376 | 2153503 | 2691879 | 538376 | 2153503 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 160000 | 32000 | 128000 | 2693651 | 538730 | 2154921 | 2442767 | 488553 | 1954214 | 2442767 | 488553 | 1954214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320000 | 64000 | 256000 | 65890 | 13178 | 52712 | 65890 | 13178 | 52712 | 87000 | 17400 | 69600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43500 | 8700 | 34800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11840098 | 2368020 | 9472078 | 11843871 | 2371793 | 9472078 | 11843871 | 2371793 | 9472078 | 11840098 | 2368020 | 9472078 | 11843871 | 2371793 | 9472078 | 11843871 | 2371793 | 9472078 | 0 | 146591 | Pine Telephone Company, Inc. | TRUE
NT10BIX5570062 | CCI | 2010 | Q3 | Q3 - 2010 | 1871500 | 374300 | 1497200 | 0 | 0 | 0 | 374300 | 74860 | 299440 | 357765 | 71553 | 286212 | 0 | 0 | 0 | 71553 | 14311 | 57242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78050 | 15610 | 62440 | 0 | 0 | 0 | 15610 | 3122 | 12488 | 6556 | 1311 | 5245 | 0 | 0 | 0 | 1331 | 267 | 1064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 11100 | 2775 | 0 | 0 | 0 | 11100 | 2220 | 8880 | 2327746 | 473874 | 1853872 | 0 | 0 | 0 | 473894 | 94780 | 379114 | 2327746 | 473874 | 1853872 | 0 | 0 | 0 | 473894 | 94780 | 379114 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | CCI | 2010 | Q4 | Q4 - 2010 | 1871500 | 374300 | 1497200 | 0 | 0 | 0 | 374300 | 74860 | 299440 | 357765 | 71553 | 286212 | 0 | 0 | 0 | 71553 | 14311 | 57242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78050 | 15610 | 62440 | 0 | 0 | 0 | 15610 | 3122 | 12488 | 6556 | 1311 | 5245 | 0 | 0 | 0 | 1331 | 267 | 1064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 11100 | 2775 | 0 | 0 | 0 | 11100 | 2220 | 8880 | 2327746 | 473874 | 1853872 | 0 | 0 | 0 | 473894 | 94780 | 379114 | 2327746 | 473874 | 1853872 | 0 | 0 | 0 | 473894 | 94780 | 379114 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | CCI | 2011 | Q1 | Q1 - 2011 | 1871599 | 374300 | 1497200 | 0 | 0 | 0 | 0 | 0 | 0 | 357765 | 71553 | 286212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78050 | 15610 | 62440 | 15610 | 15610 | 0 | 15610 | 15610 | 0 | 6556 | 1311 | 5245 | 1311 | 1311 | 0 | 1311 | 1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 2775 | 11100 | 11100 | 11100 | 0 | 11100 | 11100 | 0 | 2327845 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 2327845 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | CCI | 2011 | Q2 | Q2 - 2011 | 1871599 | 374300 | 1497200 | 0 | 0 | 0 | 0 | 0 | 0 | 357765 | 71553 | 286212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78050 | 15610 | 62440 | 15610 | 15610 | 0 | 15610 | 15610 | 0 | 6556 | 1311 | 5245 | 1311 | 1311 | 0 | 1311 | 1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 2775 | 11100 | 11100 | 11100 | 0 | 11100 | 11100 | 0 | 2327845 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 2327845 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | CCI | 2011 | Q3 | Q3 - 2011 | 1871500 | 374300 | 1497200 | 0 | 0 | 0 | 0 | 0 | 0 | 357765 | 71553 | 286212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78050 | 15610 | 62440 | 15610 | 15610 | 0 | 15610 | 15610 | 0 | 6556 | 1311 | 5245 | 1311 | 1311 | 0 | 1311 | 1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 2775 | 11100 | 11100 | 11100 | 0 | 11100 | 11100 | 0 | 2327746 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 2327746 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | CCI | 2011 | Q4 | Q4 - 2011 | 1871500 | 374300 | 1497200 | 0 | 0 | 0 | 0 | 0 | 0 | 357765 | 71553 | 286212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78050 | 15610 | 62440 | 15610 | 15610 | 0 | 15610 | 15610 | 0 | 6556 | 1311 | 5245 | 1311 | 1311 | 0 | 1311 | 1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 2775 | 11100 | 11100 | 11100 | 0 | 11100 | 11100 | 0 | 2327746 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 2327746 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570062 | CCI | 2012 | Q1 | Q1 - 2012 | 1871599 | 374300 | 1497200 | 0 | 0 | 0 | 0 | 0 | 0 | 357765 | 71553 | 286212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78050 | 15610 | 62440 | 15610 | 15610 | 0 | 15610 | 15610 | 0 | 6556 | 1311 | 5245 | 1311 | 1311 | 0 | 1311 | 1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13875 | 2775 | 11100 | 11100 | 11100 | 0 | 11100 | 11100 | 0 | 2327845 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 2327845 | 465549 | 1862197 | 28021 | 28021 | 0 | 28021 | 28021 | 0 | 0 | 0 | DigitalBridge Communications Corp. | TRUE
NT10BIX5570065 | CCI | 2010 | Q3 | Q3 - 2010 | 17041210 | 3252984 | 13788226 | 0 | 0 | 0 | 0 | 0 | 0 | 1321850 | 214017 | 1107833 | 0 | 0 | 0 | 0 | 0 | 0 | 277131 | 62428 | 214703 | 0 | 0 | 0 | 15000 | 0 | 15000 | 1256150 | 203380 | 1052770 | 0 | 0 | 0 | 50000 | 10000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 9714 | 50286 | 0 | 0 | 0 | 0 | 146581 | 146581 | 1807524 | 292651 | 1514873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577150 | 93445 | 483705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1617682 | 846430 | 771252 | 0 | 0 | 0 | 0 | 0 | 0 | 23958697 | 4975049 | 18983648 | 0 | 0 | 0 | 65000 | 156581 | 201581 | 23958697 | 4975049 | 18983648 | 0 | 0 | 0 | 65000 | 156581 | 201581 | 0 | 0 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | CCI | 2010 | Q4 | Q4 - 2010 | 17041210 | 3252984 | 13788226 | 0 | 0 | 0 | 0 | 0 | 0 | 1321850 | 214017 | 1107833 | 0 | 0 | 0 | 0 | 0 | 0 | 277131 | 62428 | 214703 | 0 | 0 | 0 | 20000 | 16000 | 4000 | 1256150 | 203380 | 1052770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 9714 | 50286 | 0 | 0 | 0 | 60000 | 48000 | 12000 | 1807524 | 292651 | 1514873 | 0 | 0 | 0 | 390000 | 312000 | 78000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 577150 | 93445 | 483705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1617682 | 846430 | 771252 | 0 | 0 | 0 | 0 | 0 | 0 | 23958697 | 4975049 | 18983648 | 0 | 0 | 0 | 470000 | 376000 | 94000 | 23958697 | 4975049 | 18983648 | 0 | 0 | 0 | 470000 | 376000 | 94000 | 0 | 0 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | CCI | 2011 | Q1 | Q1 - 2011 | 22003511 | 3864959 | 18138552 | 0 | 0 | 0 | 8483849 | 1562079 | 6921770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 17558 | 250000 | 0 | 0 | 0 | 168318 | 0 | 168318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 146581 | 445296 | 0 | 0 | 0 | 368292 | 21875 | 346417 | 361435 | 361435 | 0 | 0 | 0 | 0 | 361435 | 361435 | 0 | 142800 | 0 | 142800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 584516 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 23958697 | 4975049 | 18983648 | 0 | 0 | 0 | 9381894 | 1945389 | 7436505 | 23958697 | 4975049 | 18983648 | 0 | 0 | 0 | 9381894 | 1945389 | 7436505 | 0 | 0 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | CCI | 2011 | Q2 | Q2 - 2011 | 22003511 | 4143394 | 17860117 | 396270 | 396270 | 0 | 2513176 | 703247 | 1809929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 59975 | 207583 | 38385 | 16813 | 21572 | 38760 | 16813 | 21947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 100423 | 491454 | 203254 | 3196 | 200058 | 235479 | 3196 | 232283 | 361435 | 61324 | 300111 | 145946 | 118251 | 27695 | 145946 | 27695 | 118251 | 142800 | 24229 | 118571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 585704 | 5812 | 528688 | 528688 | 0 | 528688 | 528688 | 0 | 23958697 | 4975049 | 18983648 | 1312543 | 1063218 | 249325 | 3462049 | 1279639 | 2182410 | 23958697 | 4975049 | 18983648 | 1312543 | 1063218 | 249325 | 3462049 | 1279639 | 2182410 | 0 | 0 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | CCI | 2011 | Q3 | Q3 - 2011 | 22003511 | 4143394 | 17860117 | 5604462 | 1232834 | 4371629 | 9121153 | 1812131 | 7309022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 59975 | 207583 | 38385 | 16813 | 21572 | 47006 | 16813 | 30193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 100423 | 491454 | 258101 | 3196 | 254904 | 280234 | 25330 | 254904 | 361435 | 61324 | 300111 | 145946 | 118251 | 27695 | 145946 | 27695 | 118251 | 142800 | 24229 | 118571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 585704 | 5812 | 542188 | 528688 | 13500 | 546688 | 529876 | 16812 | 23958697 | 4975049 | 18983648 | 6589082 | 1899782 | 4689300 | 10141027 | 2411845 | 7729182 | 23958697 | 4975049 | 18983648 | 6589082 | 1899782 | 4689300 | 10141027 | 2411845 | 7729182 | 0 | 0 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | CCI | 2011 | Q4 | Q4 - 2011 | 22003511 | 4143394 | 17860117 | 11649266 | 2267615 | 9381651 | 14828809 | 2928506 | 11900303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 59975 | 207583 | 56175 | 16814 | 39361 | 56175 | 16814 | 39361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 100423 | 491454 | 340208 | 21704 | 318504 | 383917 | 21705 | 362212 | 361435 | 61324 | 300111 | 150731 | 121876 | 28855 | 150731 | 121876 | 28855 | 142800 | 24229 | 118571 | 16830 | 0 | 16830 | 27625 | 0 | 27625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 585704 | 5812 | 631836 | 529876 | 101960 | 635934 | 529876 | 106058 | 23958697 | 4975049 | 18983648 | 12845046 | 2957885 | 9887161 | 16083191 | 3618777 | 12464414 | 23958697 | 4975049 | 18983648 | 12845046 | 2957885 | 9887161 | 16083191 | 3618777 | 12464414 | 0 | 0 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | CCI | 2012 | Q1 | Q1 - 2012 | 22003511 | 4143394 | 17860117 | 16174664 | 2988724 | 13185940 | 17239334 | 3193728 | 14045606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 59975 | 207583 | 63608 | 16814 | 46794 | 213608 | 16814 | 196794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 100423 | 491454 | 436776 | 82909 | 353867 | 496695 | 82909 | 413786 | 361435 | 61324 | 300111 | 150731 | 121876 | 28855 | 150731 | 121876 | 28855 | 142800 | 24229 | 118571 | 43095 | 17085 | 26010 | 63495 | 37485 | 26010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 585704 | 5812 | 687707 | 529876 | 157831 | 721213 | 529876 | 191337 | 23958697 | 4975049 | 18983648 | 17556581 | 3757284 | 13799297 | 18885076 | 3982688 | 14902388 | 23958697 | 4975049 | 18983648 | 17556581 | 3757284 | 13799297 | 18885076 | 3982688 | 14902388 | 0 | 0 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | CCI | 2012 | Q2 | Q2 - 2012 | 22003511 | 4143394 | 17860117 | 17239334 | 3193728 | 14045606 | 17339334 | 3218728 | 14120606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 59975 | 207583 | 223908 | 16814 | 207094 | 238908 | 31814 | 207094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 100423 | 491454 | 502761 | 82909 | 419852 | 577761 | 97909 | 479852 | 361435 | 61324 | 300111 | 150731 | 121876 | 28855 | 150731 | 121876 | 28855 | 142800 | 24229 | 118571 | 67665 | 37485 | 30180 | 67665 | 37485 | 30180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 585704 | 5812 | 755294 | 529876 | 225418 | 830294 | 529876 | 300418 | 23958697 | 4975049 | 18983648 | 18939693 | 3982688 | 14957005 | 19204693 | 4037688 | 15167005 | 23958697 | 4975049 | 18983648 | 18939693 | 3982688 | 14957005 | 19204693 | 4037688 | 15167005 | 0 | 2337 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | CCI | 2012 | Q3 | Q3 - 2012 | 22003511 | 4143394 | 17860117 | 17265321 | 3217963 | 14047358 | 17265321 | 3217963 | 14047358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 59975 | 207583 | 223908 | 16814 | 207094 | 223908 | 16814 | 207094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 100423 | 491454 | 575116 | 94070 | 481046 | 660116 | 111070 | 549046 | 361435 | 61324 | 300111 | 150731 | 121876 | 28855 | 150731 | 121876 | 28855 | 142800 | 24229 | 118571 | 79807 | 37485 | 42322 | 79807 | 37485 | 42322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 585704 | 5812 | 798809 | 529876 | 268933 | 848809 | 539876 | 308933 | 23958697 | 4975049 | 18983648 | 19093692 | 4018084 | 15075608 | 19228692 | 4045084 | 15183608 | 23958697 | 4975049 | 18983648 | 19093692 | 4018084 | 15075608 | 19228692 | 4045084 | 15183608 | 0 | 5804 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | CCI | 2012 | Q4 | Q4 - 2012 | 22003511 | 4143394 | 17860117 | 17305121 | 3217963 | 14087158 | 17305121 | 3217963 | 14087158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 59975 | 207583 | 232830 | 16814 | 216016 | 232830 | 16814 | 216016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 100423 | 491454 | 608569 | 94070 | 514499 | 608569 | 94070 | 608569 | 361435 | 61324 | 300111 | 150731 | 121876 | 28855 | 150731 | 121876 | 28855 | 142800 | 24229 | 118571 | 79807 | 37485 | 42322 | 79807 | 37485 | 42322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 585704 | 5812 | 801959 | 529876 | 272083 | 801959 | 529876 | 272083 | 23958697 | 4975049 | 18983648 | 19179017 | 4018084 | 15160933 | 19179017 | 4018084 | 15255003 | 23958697 | 4975049 | 18983648 | 19179017 | 4018084 | 15160933 | 19179017 | 4018084 | 15255003 | 0 | 5804 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | CCI | 2013 | Q1 | Q1 - 2013 | 21482710 | 4607804 | 16874906 | 17810410 | 3761129 | 14049281 | 17810410 | 3761129 | 14049281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286813 | 16813 | 270000 | 232829 | 16813 | 216016 | 253452 | 16813 | 236639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1108868 | 177082 | 931786 | 611283 | 92657 | 518626 | 691748 | 173122 | 518626 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 142800 | 48873 | 93927 | 75680 | 37485 | 38195 | 75680 | 37485 | 38195 | 383825 | 1188 | 382637 | 296670 | 1188 | 295483 | 383825 | 1188 | 382637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401537 | 0 | 401537 | 0 | 0 | 0 | 198217 | 0 | 198217 | 23958697 | 4975049 | 18983648 | 19179016 | 4032561 | 15146456 | 19565476 | 4113026 | 15452450 | 23958697 | 4975049 | 18983648 | 19179016 | 4032561 | 15146456 | 19565476 | 4113026 | 15452450 | 0 | 5804 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | CCI | 2013 | Q2 | Q2 - 2013 | 21482710 | 4607804 | 16874906 | 17810410 | 3761128 | 14049282 | 17810410 | 3761128 | 14049282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286813 | 16813 | 270000 | 280901 | 16813 | 264088 | 293812 | 16813 | 276999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1108868 | 177082 | 931786 | 825385 | 225997 | 599388 | 864218 | 246110 | 618108 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 142800 | 48873 | 93927 | 76695 | 38500 | 38195 | 76695 | 38500 | 38195 | 383825 | 1188 | 382637 | 383825 | 1188 | 382637 | 383825 | 1188 | 382637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401537 | 0 | 401537 | 267387 | 0 | 267387 | 343632 | 0 | 343632 | 23958697 | 4975049 | 18983648 | 19796747 | 4166915 | 15629832 | 19924736 | 4187028 | 15737708 | 23958697 | 4975049 | 18983648 | 19796747 | 4166915 | 15629832 | 19924736 | 4187028 | 15737708 | 0 | 5804 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | CCI | 2013 | Q3 | Q3 - 2013 | 22003511 | 3864959 | 18138552 | 18194234 | 3762316 | 14431918 | 18534235 | 3832316 | 14701919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 17558 | 250000 | 417590 | 32220 | 385370 | 427590 | 16813 | 410777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 146581 | 445296 | 881846 | 261360 | 620486 | 890836 | 270350 | 620486 | 361435 | 361435 | 0 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 142800 | 0 | 142800 | 76695 | 38500 | 38195 | 76695 | 38500 | 38195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 584516 | 7000 | 340181 | 0 | 340181 | 421181 | 0 | 421181 | 23958697 | 4975049 | 18983648 | 20062690 | 4217685 | 15845005 | 20502681 | 4281268 | 16221413 | 23958697 | 4975049 | 18983648 | 20062690 | 4217685 | 15845005 | 20502681 | 4281268 | 16221413 | 0 | 5804 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570065 | CCI | 2013 | Q4 | Q4 - 2013 | 22003511 | 3864959 | 18138552 | 18365548 | 3762566 | 14602982 | 18632106 | 3845919 | 14786187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267558 | 17558 | 250000 | 380796 | 16813 | 363983 | 412796 | 16813 | 395983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591877 | 146581 | 445296 | 917338 | 281617 | 635721 | 939337 | 281181 | 658156 | 361435 | 361435 | 0 | 152144 | 123289 | 28855 | 152144 | 123289 | 28855 | 142800 | 0 | 142800 | 76695 | 38500 | 38195 | 76695 | 38500 | 38195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591516 | 584516 | 7000 | 445095 | 11575 | 433520 | 514214 | 31446 | 482768 | 23958697 | 4975049 | 18983648 | 20337616 | 4234360 | 16103256 | 20727292 | 4337148 | 16390144 | 23958697 | 4975049 | 18983648 | 20337616 | 4234360 | 16103256 | 20727292 | 4337148 | 16390144 | 0 | 28277 | Buggs Island Telephone Cooperative | TRUE
NT10BIX5570066 | CCI | 2010 | Q4 | Q4 - 2010 | 1688279 | 850452 | 837827 | 0 | 0 | 0 | 253242 | 127568 | 125674 | 31203526 | 11304543 | 19898983 | 94211 | 20020 | 75369 | 1248141 | 452182 | 795959 | 60000 | 0 | 60000 | 55454 | 0 | 55454 | 60000 | 0 | 60000 | 1242231 | 962231 | 280000 | 0 | 0 | 0 | 186335 | 144335 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1388148 | 277630 | 1110518 | 39333 | 8358 | 31467 | 319274 | 63855 | 255419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 0 | 0 | 0 | 6383 | 1276 | 5107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522526 | 22698010 | 188998 | 28378 | 162290 | 2073375 | 789216 | 1284159 | 36220536 | 13522526 | 22698010 | 188998 | 28378 | 162290 | 2073375 | 789216 | 1284159 | 0 | 0 | BVU Authority | TRUE
NT10BIX5570066 | CCI | 2011 | Q1 | Q1 - 2011 | 1942231 | 1102231 | 840000 | 892231 | 892231 | 0 | 932271 | 900239 | 32032 | 31203526 | 11306715 | 19896810 | 6592361 | 6384483 | 207801 | 9985128 | 7063036 | 2922092 | 60000 | 0 | 60000 | 59009 | 0 | 59009 | 60000 | 0 | 60000 | 988279 | 708279 | 280000 | 638279 | 638279 | 0 | 638279 | 638279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1388148 | 277630 | 1110518 | 210462 | 42092 | 168370 | 416444 | 83289 | 333156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 0 | 0 | 0 | 12767 | 10214 | 2553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698010 | 8392342 | 7957085 | 435180 | 12044889 | 8695057 | 3349833 | 36220536 | 13522525 | 22698010 | 8392342 | 7957085 | 435180 | 12044889 | 8695057 | 3349833 | 0 | 0 | BVU Authority | TRUE
NT10BIX5570066 | CCI | 2011 | Q2 | Q2 - 2011 | 1942231 | 1102231 | 840000 | 892231 | 892231 | 0 | 918595 | 897504 | 21091 | 31203526 | 11306715 | 19896810 | 10311226 | 7128271 | 3182955 | 14030091 | 7872029 | 6158062 | 60000 | 0 | 0 | 59209 | 0 | 59209 | 60906 | 339 | 60567 | 988279 | 708279 | 280000 | 638279 | 638279 | 0 | 638279 | 638279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1388148 | 277630 | 1110518 | 434824 | 86965 | 347859 | 659184 | 131837 | 527347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 0 | 0 | 0 | 12767 | 2553 | 10214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22638010 | 12335769 | 8745746 | 3590023 | 16319822 | 9542541 | 6777281 | 36220536 | 13522525 | 22638010 | 12335769 | 8745746 | 3590023 | 16319822 | 9542541 | 6777281 | 0 | 0 | BVU Authority | TRUE
NT10BIX5570066 | CCI | 2011 | Q3 | Q3 - 2011 | 2278724 | 1538724 | 740000 | 1353724 | 1353724 | 0 | 1367261 | 1356431 | 10830 | 39731915 | 19704727 | 20027188 | 22292746 | 16216893 | 6075853 | 25908851 | 16940114 | 8968737 | 65000 | 1000 | 64000 | 59217 | 0 | 59217 | 65000 | 1000 | 64000 | 991431 | 751431 | 240000 | 691431 | 691431 | 0 | 698345 | 692814 | 5531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 624066 | 124813 | 499253 | 813309 | 162662 | 650647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45100598 | 22402587 | 22698011 | 25021184 | 18386861 | 6634323 | 28852766 | 19153021 | 9699745 | 45100598 | 22402587 | 22698011 | 25021184 | 18386861 | 6634323 | 28852766 | 19153021 | 9699745 | 0 | 0 | BVU Authority | TRUE
NT10BIX5570066 | CCI | 2011 | Q4 | Q4 - 2011 | 1817231 | 1077231 | 740000 | 275948 | 275948 | 0 | 532828 | 409495 | 123333 | 31366498 | 11339310 | 20027188 | 13520898 | 4270987 | 9249911 | 16495165 | 5449041 | 11046124 | 65000 | 1000 | 64000 | 61834 | 951 | 60883 | 62362 | 959 | 61403 | 938279 | 698279 | 240000 | 324222 | 222769 | 101453 | 426565 | 302021 | 124544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 884472 | 176894 | 707578 | 969589 | 193917 | 775672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 15067374 | 4947549 | 10119825 | 18486509 | 6355433 | 12131076 | 36220536 | 13522525 | 22698011 | 15067374 | 4947549 | 10119825 | 18486509 | 6355433 | 12131076 | 0 | 0 | BVU Authority | TRUE
NT10BIX5570066 | CCI | 2012 | Q1 | Q1 - 2012 | 1817231 | 1077231 | 740000 | 922807 | 615720 | 307086 | 1101692 | 708022 | 393669 | 31366498 | 11339310 | 20027188 | 17283111 | 6516727 | 10766384 | 20099789 | 7481244 | 12618545 | 65000 | 1000 | 64000 | 65303 | 1005 | 64299 | 65303 | 1005 | 64299 | 938279 | 698279 | 240000 | 514751 | 411390 | 103361 | 599457 | 468768 | 130689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 1060530 | 212106 | 848424 | 1127459 | 225492 | 901967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 17416 | 3483 | 13933 | 141603 | 28321 | 113283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 19863918 | 7760431 | 12103487 | 23135303 | 8912852 | 14222452 | 36220536 | 13522525 | 22698011 | 19863918 | 7760431 | 12103487 | 23135303 | 8912852 | 14222452 | 0 | 0 | BVU Authority | TRUE
NT10BIX5570066 | CCI | 2012 | Q2 | Q2 - 2012 | 1817231 | 1077231 | 740000 | 1049163 | 742077 | 307086 | 1241181 | 825866 | 415315 | 31366498 | 11339310 | 20027188 | 22165403 | 8210948 | 13954455 | 24465677 | 8993039 | 15472638 | 65000 | 1000 | 64000 | 73685 | 1134 | 72551 | 76755 | 1181 | 75574 | 938279 | 698279 | 240000 | 710313 | 522816 | 187497 | 767305 | 566682 | 200623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 1387105 | 277421 | 1109684 | 1389123 | 277825 | 1111298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 76771 | 15354 | 61417 | 217166 | 43433 | 173733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 25462440 | 9769750 | 15692690 | 28157207 | 10708026 | 17449181 | 36220536 | 13522525 | 22698011 | 25462440 | 9769750 | 15692690 | 28157207 | 10708026 | 17449181 | 0 | 0 | BVU Authority | TRUE
NT10BIX5570066 | CCI | 2012 | Q3 | Q3 - 2012 | 1817231 | 1077231 | 740000 | 1116210 | 809123 | 307087 | 1349883 | 898492 | 451391 | 31366498 | 11339310 | 20027188 | 24394899 | 9037208 | 15357691 | 26718764 | 9804575 | 16914189 | 65000 | 1000 | 64000 | 78589 | 3718 | 74871 | 81500 | 3856 | 77644 | 938279 | 698279 | 240000 | 778493 | 574823 | 203670 | 831755 | 615975 | 215780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 1847788 | 369558 | 1478230 | 1916224 | 383245 | 1532979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 133627 | 26725 | 106902 | 301868 | 60373 | 241495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 28349606 | 10821155 | 17528451 | 31199994 | 11766516 | 19433478 | 36220536 | 13522525 | 22698011 | 28349606 | 10821155 | 17528451 | 31199994 | 11766516 | 19433478 | 0 | 0 | BVU Authority | TRUE
NT10BIX5570066 | CCI | 2012 | Q4 | Q4 - 2012 | 1817231 | 1077231 | 740000 | 1116209 | 809123 | 307086 | 1466720 | 943177 | 523543 | 31366498 | 11339310 | 20027188 | 25819151 | 9322058 | 16497093 | 28592825 | 10330684 | 18262141 | 65000 | 1000 | 64000 | 78589 | 3718 | 74871 | 81500 | 3856 | 77644 | 938279 | 698279 | 240000 | 1112691 | 641662 | 471029 | 1156701 | 669971 | 486730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 2113066 | 422614 | 1690452 | 2183501 | 436701 | 1746800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 198140 | 39628 | 158512 | 418246 | 83649 | 334597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 30437846 | 11238803 | 19199043 | 33899493 | 12468038 | 21431455 | 36220536 | 13522525 | 22698011 | 30437846 | 11238803 | 19199043 | 33899493 | 12468038 | 21431455 | 0 | 0 | BVU Authority | TRUE
NT10BIX5570066 | CCI | 2013 | Q1 | Q1 - 2013 | 1817231 | 1077231 | 740000 | 1182525 | 875439 | 307086 | 1420659 | 1077231 | 343428 | 31366498 | 11339310 | 20027188 | 27109951 | 9969906 | 17140045 | 30509668 | 11339310 | 19170358 | 65000 | 1000 | 64000 | 79211 | 3718 | 75493 | 81500 | 3856 | 77644 | 938279 | 698279 | 240000 | 1476980 | 752473 | 724507 | 1501782 | 775275 | 726507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 2255803 | 451161 | 1804642 | 2274475 | 464833 | 1809642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 256574 | 51315 | 205259 | 357220 | 127670 | 229550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 32361044 | 12104012 | 20257032 | 36145304 | 13788175 | 22357129 | 36220536 | 13522525 | 22698011 | 32361044 | 12104012 | 20257032 | 36145304 | 13788175 | 22357129 | 0 | 0 | BVU Authority | TRUE
NT10BIX5570066 | CCI | 2013 | Q2 | Q2 - 2013 | 1817231 | 1077231 | 740000 | 1276089 | 969003 | 307086 | 1355528 | 999135 | 356393 | 31366498 | 11339310 | 20027188 | 28649198 | 10795850 | 17853348 | 30300805 | 11113031 | 19187774 | 65000 | 1000 | 64000 | 79211 | 3718 | 75493 | 83503 | 3746 | 79757 | 938279 | 698279 | 240000 | 1578334 | 826290 | 752044 | 1613857 | 845822 | 768035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 2328519 | 465704 | 1862815 | 2410693 | 473509 | 1937184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 318550 | 63710 | 254840 | 356148 | 67281 | 288867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 34229901 | 13124275 | 21105626 | 36120534 | 13502524 | 22618010 | 36220536 | 13522525 | 22698011 | 34229901 | 13124275 | 21105626 | 36120534 | 13502524 | 22618010 | 0 | 0 | BVU Authority | TRUE
NT10BIX5570066 | CCI | 2013 | Q3 | Q3 - 2013 | 1817231 | 1077231 | 740000 | 1276089 | 969003 | 307086 | 1276089 | 969003 | 307086 | 31366498 | 11339310 | 20027188 | 30057793 | 11077568 | 18980225 | 30057793 | 11077568 | 18980225 | 65000 | 1000 | 64000 | 80833 | 4167 | 76666 | 80833 | 4167 | 76666 | 938279 | 698279 | 240000 | 2055998 | 921823 | 1134175 | 2055998 | 921823 | 1134175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395176 | 279035 | 1116141 | 2365092 | 473019 | 1892073 | 2365092 | 473019 | 1892073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638352 | 127670 | 510682 | 384731 | 76946 | 307785 | 384731 | 76946 | 307785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36220536 | 13522525 | 22698011 | 36220536 | 13522526 | 22698010 | 36220536 | 13522526 | 22698010 | 36220536 | 13522525 | 22698011 | 36220536 | 13522526 | 22698010 | 36220536 | 13522526 | 22698010 | 0 | 0 | BVU Authority | TRUE
NT10BIX5570067 | CCI | 2010 | Q4 | Q4 - 2010 | 28631231 | 8404716 | 20226515 | 5513168 | 3867462 | 1645706 | 9069213 | 3867462 | 5201751 | 35225331 | 15494088 | 19731243 | 0 | 0 | 0 | 501437 | 357282 | 144155 | 268147 | 24379 | 243768 | 72391 | 12088 | 60303 | 87867 | 12088 | 75779 | 4261800 | 0 | 4261800 | 5000 | 0 | 5000 | 2717180 | 0 | 2717180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1222148 | 65824 | 1156324 | 1330420 | 96032 | 1234388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 0 | 0 | 0 | 144156 | 0 | 144156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 525 | 0 | 525 | 525 | 0 | 525 | 69982479 | 25188433 | 44794046 | 6813232 | 3945374 | 2867858 | 13850798 | 4332864 | 9517934 | 69982479 | 25188433 | 44794046 | 6813232 | 3945374 | 2867858 | 13850798 | 4332864 | 9517934 | 0 | 0 | ONECOMMUNITY | TRUE
NT10BIX5570067 | CCI | 2011 | Q1 | Q1 - 2011 | 28631231 | 8404716 | 20226515 | 8459386 | 3268414 | 5190972 | 19560982 | 3616862 | 15944120 | 35225331 | 15494088 | 19731243 | 18911 | 0 | 18913 | 3947957 | 394917 | 3553040 | 268147 | 24379 | 243768 | 175848 | 12088 | 163760 | 181488 | 12088 | 169400 | 4261800 | 0 | 4261800 | 164760 | 0 | 164760 | 5593582 | 0 | 5593582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1245402 | 65824 | 1179578 | 1295058 | 65824 | 1229235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 39189 | 0 | 39189 | 39189 | 0 | 39189 | 69982479 | 25188433 | 44794046 | 10123496 | 3366326 | 6757172 | 30638256 | 4109691 | 26528566 | 69982479 | 25188433 | 44794046 | 10123496 | 3366326 | 6757172 | 30638256 | 4109691 | 26528566 | 0 | 0 | ONECOMMUNITY | TRUE
NT10BIX5570067 | CCI | 2011 | Q2 | Q2 - 2011 | 28631231 | 8404716 | 20226515 | 14630545 | 3262348 | 11368197 | 19356109 | 3420796 | 15935313 | 35225331 | 15494088 | 19731243 | 690944 | 291174 | 399770 | 9939070 | 1085345 | 8853725 | 268147 | 24379 | 243768 | 188160 | 12088 | 176072 | 192160 | 1208 | 180072 | 4261800 | 0 | 4261800 | 644877 | 0 | 644877 | 8188523 | 0 | 8188523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1314350 | 77913 | 1236437 | 1420088 | 77913 | 1342175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 39189 | 0 | 39189 | 66708 | 0 | 66708 | 69982479 | 25188433 | 44794046 | 17528065 | 3663523 | 13864542 | 39182658 | 4605262 | 34566516 | 69982479 | 25188433 | 44794046 | 17528065 | 3663523 | 13864542 | 39182658 | 4605262 | 34566516 | 0 | 0 | ONECOMMUNITY | TRUE
NT10BIX5570067 | CCI | 2011 | Q3 | Q3 - 2011 | 28631231 | 8404716 | 20226515 | 19110085 | 3232968 | 15877117 | 23622231 | 3391416 | 20230815 | 35225331 | 15494088 | 19731243 | 1543025 | 289409 | 1253616 | 4572838 | 1236356 | 3336482 | 268147 | 24379 | 243768 | 73026 | 12089 | 60937 | 127026 | 12089 | 114937 | 4261800 | 0 | 4261800 | 2008381 | 0 | 2008381 | 10354219 | 0 | 10354219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1685896 | 65824 | 1620072 | 2000810 | 255824 | 1744986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 10079 | 0 | 10079 | 122579 | 100000 | 22579 | 69982479 | 25188433 | 44794046 | 24450492 | 3620290 | 20830202 | 40819703 | 5015685 | 35804018 | 69982479 | 25188433 | 44794046 | 24450492 | 3620290 | 20830202 | 40819703 | 5015685 | 35804018 | 0 | 0 | ONECOMMUNITY | TRUE
NT10BIX5570067 | CCI | 2011 | Q4 | Q4 - 2011 | 28631231 | 8404716 | 20226515 | 22432494 | 3196850 | 19235644 | 24888873 | 3683792 | 21205081 | 35225331 | 15494088 | 19731243 | 2944523 | 721530 | 2222993 | 5234752 | 1528489 | 3706263 | 268147 | 24379 | 243768 | 83962 | 12088 | 71874 | 97299 | 12088 | 85211 | 4261800 | 0 | 4261800 | 2509819 | 24419 | 2485400 | 5904699 | 24419 | 5880280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1773114 | 82516 | 1690598 | 1805088 | 82516 | 1722572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 23955 | 23955 | 0 | 23955 | 23955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 17464 | 2974 | 14490 | 21964 | 2974 | 18990 | 69982479 | 25188433 | 44794046 | 29785331 | 4064332 | 25720999 | 37976630 | 5358233 | 32618397 | 69982479 | 25188433 | 44794046 | 29785331 | 4064332 | 25720999 | 37976630 | 5358233 | 32618397 | 0 | 0 | ONECOMMUNITY | TRUE
NT10BIX5570067 | CCI | 2012 | Q1 | Q1 - 2012 | 28631231 | 8404716 | 20226515 | 22607986 | 3196850 | 19411136 | 24531172 | 4214158 | 20317014 | 35225331 | 15494088 | 19731243 | 4932410 | 760931 | 4171479 | 8896161 | 1447476 | 7448685 | 268147 | 24379 | 243768 | 84081 | 12088 | 71993 | 84081 | 12088 | 71993 | 4261800 | 0 | 4261800 | 3775913 | 24419 | 3751494 | 5485263 | 24419 | 5460844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1536709 | 82516 | 1454192 | 1611874 | 82516 | 1529358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 23955 | 23955 | 0 | 123955 | 123955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 37697 | 2974 | 34723 | 40697 | 2974 | 37723 | 69982479 | 25188433 | 44794046 | 32998751 | 4103733 | 28895017 | 40773203 | 5907586 | 34865617 | 69982479 | 25188433 | 44794046 | 32998751 | 4103733 | 28895017 | 40773203 | 5907586 | 34865617 | 0 | 0 | ONECOMMUNITY | TRUE
NT10BIX5570067 | CCI | 2012 | Q2 | Q2 - 2012 | 28631231 | 8404716 | 20226515 | 22688469 | 3198364 | 19490105 | 23974261 | 3784754 | 20189508 | 35225331 | 15494088 | 19731243 | 7657728 | 852805 | 6804922 | 9547443 | 1318850 | 8228593 | 268147 | 24379 | 243768 | 91998 | 12088 | 79910 | 91998 | 12088 | 79910 | 4261800 | 0 | 4261800 | 4906403 | 24776 | 4881626 | 5974984 | 24776 | 5950207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1627287 | 107513 | 1519774 | 1638599 | 107513 | 1531085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 43475 | 43475 | 0 | 143475 | 143475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 39130 | 1155 | 37976 | 40631 | 1155 | 39476 | 69982479 | 25188433 | 44794046 | 37054490 | 4240176 | 32814313 | 41411391 | 5392611 | 36018779 | 69982479 | 25188433 | 44794046 | 37054490 | 4240176 | 32814313 | 41411391 | 5392611 | 36018779 | 0 | 0 | ONECOMMUNITY | TRUE
NT10BIX5570067 | CCI | 2012 | Q3 | Q3 - 2012 | 28631231 | 8404716 | 20226515 | 24550001 | 4173998 | 20376003 | 25947771 | 5305632 | 20642139 | 35225331 | 15494088 | 19731243 | 10172578 | 961860 | 9210718 | 13300202 | 3039127 | 10261075 | 268147 | 24379 | 243768 | 92320 | 12088 | 80232 | 92320 | 12088 | 80232 | 4261800 | 0 | 4261800 | 5652548 | 24776 | 5627772 | 6095646 | 24776 | 6070870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230720 | 900000 | 330720 | 1652767 | 121068 | 1531699 | 1668162 | 121068 | 1547094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180250 | 180250 | 0 | 43475 | 43475 | 0 | 143475 | 143475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000 | 185000 | 0 | 43859 | 2781 | 41078 | 48359 | 2781 | 45578 | 69982479 | 25188433 | 44794046 | 42207548 | 5340046 | 36867502 | 47295935 | 8648947 | 38646988 | 69982479 | 25188433 | 44794046 | 42207548 | 5340046 | 36867502 | 47295935 | 8648947 | 38646988 | 0 | 0 | ONECOMMUNITY | TRUE
NT10BIX5570067 | CCI | 2012 | Q4 | Q4 - 2012 | 26433236 | 5385499 | 21047737 | 25042536 | 4288603 | 20538174 | 25429063 | 4491996 | 20937067 | 21437183 | 5594707 | 15842476 | 11437954 | 608207 | 10541448 | 15157173 | 3608001 | 11549172 | 255856 | 12088 | 243768 | 98823 | 12088 | 86735 | 108823 | 22088 | 86735 | 10510119 | 4452625 | 6057494 | 5878035 | 57594 | 5818812 | 8097197 | 2276756 | 5820440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1652586 | 111093 | 1541493 | 1624024 | 93505 | 1527774 | 1649024 | 93505 | 1555519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112870 | 112870 | 0 | 34750 | 34750 | 0 | 34750 | 34750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130645 | 69567 | 61078 | 45813 | 2980 | 42832 | 50313 | 7480 | 42832 | 60532495 | 15738449 | 44794046 | 44161935 | 5097727 | 38555775 | 50526343 | 10534576 | 39991765 | 60532495 | 15738449 | 44794046 | 44161935 | 5097727 | 38555775 | 50526343 | 10534576 | 39991765 | 0 | 0 | ONECOMMUNITY | TRUE
NT10BIX5570067 | CCI | 2013 | Q1 | Q1 - 2013 | 26433236 | 5385499 | 21047737 | 25986170 | 5272534 | 20713637 | 26881758 | 6044122 | 20837637 | 21437183 | 5594707 | 15842476 | 12424611 | 1518742 | 10905870 | 16272119 | 3455306 | 12816812 | 255856 | 12088 | 243768 | 99767 | 13671 | 86096 | 99767 | 13671 | 86096 | 10510119 | 4452624 | 6057494 | 7732389 | 1736925 | 5995464 | 8760768 | 2705860 | 6054908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1652586 | 111093 | 1541493 | 1668464 | 119331 | 1549133 | 1682464 | 119331 | 1563133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112870 | 112870 | 0 | 37545 | 37545 | 0 | 47545 | 47545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130645 | 69567 | 61078 | 72945 | 30434 | 42511 | 147945 | 45434 | 102511 | 60532495 | 15738448 | 44794046 | 48021891 | 8729182 | 39292711 | 53892366 | 12431269 | 41461097 | 60532495 | 15738448 | 44794046 | 48021891 | 8729182 | 39292711 | 53892366 | 12431269 | 41461097 | 0 | 0 | ONECOMMUNITY | TRUE
NT10BIX5570067 | CCI | 2013 | Q2 | Q2 - 2013 | 26433236 | 5385499 | 21047737 | 26533136 | 5496546 | 21036590 | 27281492 | 5936345 | 21345147 | 21437183 | 5594707 | 15842476 | 14410619 | 2991481 | 11419137 | 18925929 | 4205679 | 14720250 | 255856 | 12088 | 243768 | 99511 | 13671 | 85840 | 99511 | 13671 | 85840 | 10510119 | 4452624 | 6057494 | 8083477 | 2073222 | 6010256 | 11576555 | 5354711 | 6221844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1652586 | 111093 | 1541493 | 1719160 | 145508 | 1573652 | 1734160 | 145508 | 1588652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112870 | 112870 | 0 | 37545 | 37545 | 0 | 47545 | 47545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130645 | 69567 | 61078 | 74956 | 32148 | 42807 | 89956 | 32148 | 57807 | 60532495 | 15738448 | 44794046 | 50958404 | 10790121 | 40168282 | 59755148 | 15735607 | 44019540 | 60532495 | 15738448 | 44794046 | 50958404 | 10790121 | 40168282 | 59755148 | 15735607 | 44019540 | 0 | 0 | ONECOMMUNITY | TRUE
NT10BIX5570067 | CCI | 2013 | Q3 | Q3 - 2013 | 25858454 | 5063987 | 20794467 | 0 | 0 | 0 | 0 | 0 | 0 | 22404414 | 7309091 | 15095323 | 0 | 0 | 0 | 0 | 0 | 0 | 235233 | 25038 | 210195 | 0 | 0 | 0 | 0 | 0 | 0 | 10224939 | 3181754 | 7043185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1663175 | 59644 | 1603531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37545 | 37545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108734 | 61389 | 47345 | 0 | 0 | 0 | 0 | 0 | 0 | 60532494 | 15738448 | 44794046 | 0 | 0 | 0 | 0 | 0 | 0 | 60532494 | 15738448 | 44794046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ONECOMMUNITY | TRUE
NT10BIX5570068 | CCI | 2010 | Q3 | Q3 - 2010 | 2195529 | 658659 | 1536870 | 0 | 0 | 0 | 0 | 0 | 0 | 15745589 | 4723677 | 11021912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 0 | 0 | 0 | 200000 | 60000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754390 | 826317 | 1928073 | 76025 | 22808 | 53217 | 265000 | 79500 | 185500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425508 | 6727653 | 15697855 | 76025 | 22808 | 53217 | 465000 | 139500 | 325500 | 22425508 | 6727653 | 15697855 | 76025 | 22808 | 53217 | 465000 | 139500 | 325500 | 0 | 0 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | CCI | 2010 | Q4 | Q4 - 2010 | 2195529 | 658659 | 1536870 | 0 | 0 | 0 | 0 | 0 | 0 | 15745589 | 4723677 | 11021912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 0 | 0 | 0 | 354900 | 106470 | 248430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 293438 | 88031 | 205407 | 849928 | 254978 | 594950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 293438 | 88031 | 205407 | 1255828 | 376748 | 879080 | 22425509 | 6727653 | 15697856 | 293438 | 88031 | 205407 | 1255828 | 376748 | 879080 | 0 | 0 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | CCI | 2011 | Q1 | Q1 - 2011 | 2195529 | 658659 | 1536870 | 0 | 0 | 0 | 0 | 0 | 0 | 15745589 | 4723677 | 11021912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 0 | 0 | 0 | 742966 | 222890 | 520076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 293438 | 88031 | 205406 | 760568 | 228170 | 532398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 25500 | 7650 | 17850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 293438 | 88031 | 205406 | 1529034 | 458710 | 1070324 | 22425509 | 6727653 | 15697856 | 293438 | 88031 | 205406 | 1529034 | 458710 | 1070324 | 0 | 0 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | CCI | 2011 | Q2 | Q2 - 2011 | 2195529 | 658659 | 1536870 | 0 | 0 | 0 | 0 | 0 | 0 | 15745589 | 4723677 | 11021912 | 0 | 0 | 0 | 959969 | 287991 | 671978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 440491 | 132147 | 308344 | 1064000 | 319200 | 744800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 294363 | 88309 | 206054 | 326363 | 97909 | 228454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 734854 | 220456 | 514398 | 2401332 | 720400 | 1680932 | 22425509 | 6727653 | 15697856 | 734854 | 220456 | 514398 | 2401332 | 720400 | 1680932 | 0 | 0 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | CCI | 2011 | Q3 | Q3 - 2011 | 2195529 | 658659 | 1536870 | 0 | 0 | 0 | 2000000 | 600000 | 1400000 | 15745589 | 4723677 | 11021912 | 0 | 0 | 0 | 959968 | 287990 | 671978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 445491 | 133647 | 311844 | 495491 | 148647 | 346844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 378618 | 113585 | 265033 | 461118 | 138335 | 322783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 30000 | 9000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 824109 | 247232 | 576877 | 3946577 | 1183972 | 2762605 | 22425509 | 6727653 | 15697856 | 824109 | 247232 | 576877 | 3946577 | 1183972 | 2762605 | 0 | 0 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | CCI | 2011 | Q4 | Q4 - 2011 | 2195529 | 658659 | 1536870 | 2012658 | 603797 | 1408860 | 2012658 | 603797 | 1408860 | 15745589 | 4723677 | 11021912 | 0 | 0 | 0 | 4895826 | 3686484 | 1209343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 466691 | 140007 | 326684 | 1287439 | 386232 | 901207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 1429916 | 428975 | 1000941 | 1456416 | 436925 | 1019491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 6299 | 1890 | 4409 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 3915564 | 1174669 | 2740894 | 9703339 | 5128738 | 4574601 | 22425509 | 6727653 | 15697856 | 3915564 | 1174669 | 2740894 | 9703339 | 5128738 | 4574601 | 0 | 0 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | CCI | 2012 | Q1 | Q1 - 2012 | 2195529 | 658659 | 1536870 | 1986436 | 595931 | 1390505 | 2195529 | 658689 | 1536840 | 15745589 | 4723677 | 11021912 | 7824661 | 2350303 | 5474358 | 12818901 | 3845670 | 8973231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 771545 | 231464 | 540082 | 1236439 | 370932 | 865507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 1357670 | 407301 | 950369 | 2190776 | 657233 | 1533543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 11991312 | 3600299 | 8391014 | 18492645 | 5547824 | 12944821 | 22425509 | 6727653 | 15697856 | 11991312 | 3600299 | 8391014 | 18492645 | 5547824 | 12944821 | 0 | 0 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | CCI | 2012 | Q2 | Q2 - 2012 | 2195529 | 658659 | 1536870 | 2043252 | 612976 | 1430276 | 2195529 | 658659 | 1536870 | 15745589 | 4723677 | 11021912 | 12452569 | 3735771 | 8716798 | 13917591 | 4175277 | 9742314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 1430001 | 429000 | 1001001 | 1430001 | 429000 | 1001001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 1835297 | 550589 | 1284708 | 2383501 | 715053 | 1668448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 17812119 | 5343636 | 12468483 | 19977622 | 5993289 | 13984333 | 22425509 | 6727653 | 15697856 | 17812119 | 5343636 | 12468483 | 19977622 | 5993289 | 13984333 | 0 | 0 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | CCI | 2012 | Q3 | Q3 - 2012 | 2195529 | 658659 | 1536870 | 2063356 | 619007 | 1444349 | 2195529 | 658659 | 1536870 | 15745589 | 4723677 | 11021912 | 12948128 | 3884438 | 9063690 | 13917591 | 4175277 | 9742314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 1539452 | 461836 | 1077616 | 1679000 | 503700 | 1175300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 1994423 | 598327 | 1396096 | 2383501 | 715050 | 1668451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 18596359 | 5578908 | 13017451 | 20226621 | 6067986 | 14158635 | 22425509 | 6727653 | 15697856 | 18596359 | 5578908 | 13017451 | 20226621 | 6067986 | 14158635 | 0 | 0 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | CCI | 2012 | Q4 | Q4 - 2012 | 2195529 | 658659 | 1536870 | 2098127 | 629438 | 1468689 | 2195529 | 658659 | 1536870 | 15745589 | 4723677 | 11021912 | 13008887 | 3902666 | 9106221 | 14263663 | 4279099 | 9984564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 1550082 | 465025 | 1085057 | 1550082 | 465025 | 1085057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 2190607 | 657182 | 1533425 | 2458903 | 737671 | 1721232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 18898703 | 5669611 | 13229092 | 20519177 | 6155754 | 14363423 | 22425509 | 6727653 | 15697856 | 18898703 | 5669611 | 13229092 | 20519177 | 6155754 | 14363423 | 0 | 0 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | CCI | 2013 | Q1 | Q1 - 2013 | 2195529 | 658659 | 1536870 | 2098127 | 629438 | 1468689 | 2195529 | 658659 | 1536870 | 15745589 | 4723677 | 11021912 | 14639163 | 4391749 | 10247414 | 15874507 | 4762352 | 11112155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | 503700 | 1175300 | 1550082 | 465025 | 1085057 | 1550082 | 465025 | 1085057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754391 | 826317 | 1928074 | 2334843 | 700453 | 1634390 | 2754391 | 826317 | 1928074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697856 | 20673215 | 6201965 | 14471250 | 22425509 | 6727653 | 15697856 | 22425509 | 6727653 | 15697856 | 20673215 | 6201965 | 14471250 | 22425509 | 6727653 | 15697856 | 0 | 0 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570068 | CCI | 2013 | Q2 | Q2 - 2013 | 1931148 | 579344 | 1351804 | 1931148 | 579344 | 1351804 | 1931148 | 579344 | 1351804 | 16063135 | 4818941 | 11244195 | 16063135 | 4818941 | 11244195 | 16063135 | 4818941 | 11244195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550082 | 465025 | 1085057 | 1550082 | 465025 | 1085057 | 1550082 | 465025 | 1085057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2830144 | 849043 | 1981101 | 2830144 | 849043 | 1981101 | 2830144 | 849043 | 1981101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 51000 | 15300 | 35700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22425509 | 6727653 | 15697857 | 22425509 | 6727653 | 15697857 | 22425509 | 6727653 | 15697857 | 22425509 | 6727653 | 15697857 | 22425509 | 6727653 | 15697857 | 22425509 | 6727653 | 15697857 | 0 | 0 | Valley Telephone Cooperative, Inc. | TRUE
NT10BIX5570069 | CCI | 2010 | Q4 | Q4 - 2010 | 8240330 | 2068846 | 6171484 | 0 | 0 | 0 | 649205 | 0 | 649205 | 13533583 | 3474949 | 10058634 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2068631 | 2068631 | 0 | 246400 | 246400 | 0 | 503600 | 503600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 271400 | 271400 | 0 | 1177805 | 528600 | 649205 | 23867544 | 7637426 | 16230118 | 271400 | 271400 | 0 | 1177805 | 528600 | 649205 | 0 | 0 | Iowa Communications Network | TRUE
NT10BIX5570069 | CCI | 2011 | Q1 | Q1 - 2011 | 19452467 | 6086722 | 13365745 | 0 | 0 | 0 | 2983783 | 933983 | 2049800 | 1831073 | 553626 | 1277447 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 249001 | 249001 | 0 | 332671 | 275775 | 56896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 274001 | 274001 | 0 | 3341454 | 1234758 | 2106696 | 23867544 | 7637426 | 16230118 | 274001 | 274001 | 0 | 3341454 | 1234758 | 2106696 | 0 | 0 | Iowa Communications Network | TRUE
NT10BIX5570069 | CCI | 2011 | Q2 | Q2 - 2011 | 19452467 | 6086722 | 13365745 | 162121 | 162121 | 0 | 1498638 | 469103 | 1029535 | 1831073 | 553626 | 1277447 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 249001 | 249001 | 0 | 323401 | 274780 | 48621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 436122 | 436122 | 0 | 1847039 | 768883 | 1078156 | 23867544 | 7637426 | 16230118 | 436122 | 436122 | 0 | 1847039 | 768883 | 1078156 | 0 | 0 | Iowa Communications Network | TRUE
NT10BIX5570069 | CCI | 2011 | Q3 | Q3 - 2011 | 19452467 | 6086722 | 13365745 | 1483328 | 464311 | 1019017 | 6097923 | 1908770 | 4189153 | 1831073 | 553626 | 1277447 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 329335 | 274147 | 55188 | 559989 | 346346 | 213643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 1837663 | 763458 | 1074205 | 6682912 | 2280116 | 4402796 | 23867544 | 7637426 | 16230118 | 1837663 | 763458 | 1074205 | 6682912 | 2280116 | 4402796 | 0 | 5370 | Iowa Communications Network | TRUE
NT10BIX5570069 | CCI | 2011 | Q4 | Q4 - 2011 | 19452467 | 6086722 | 13365745 | 7937745 | 2808714 | 5129031 | 13031433 | 4079095 | 8952338 | 1831073 | 553626 | 1277447 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 482586 | 322117 | 160469 | 729969 | 399553 | 330416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 8445331 | 3155831 | 5289500 | 13786402 | 4503648 | 9282754 | 23867544 | 7637426 | 16230118 | 8445331 | 3155831 | 5289500 | 13786402 | 4503648 | 9282754 | 0 | 8151 | Iowa Communications Network | TRUE
NT10BIX5570069 | CCI | 2012 | Q1 | Q1 - 2012 | 19452467 | 6086722 | 13365745 | 9958987 | 3117046 | 6841941 | 12870625 | 4024217 | 8846408 | 1831073 | 553626 | 1277447 | 0 | 0 | 0 | 550367 | 165110 | 385257 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 899995 | 453775 | 446220 | 1466671 | 630156 | 836515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 10883982 | 3595821 | 7288161 | 14912663 | 4844483 | 10068180 | 23867544 | 7637426 | 16230118 | 10883982 | 3595821 | 7288161 | 14912663 | 4844483 | 10068180 | 0 | 26898 | Iowa Communications Network | TRUE
NT10BIX5570069 | CCI | 2012 | Q2 | Q2 - 2012 | 19452467 | 6086722 | 13365745 | 13251576 | 4145396 | 9106180 | 13755028 | 4303545 | 9451483 | 1831073 | 553626 | 1277447 | 285783 | 85735 | 200048 | 926420 | 277926 | 648494 | 25000 | 25000 | 0 | 27064 | 25619 | 1445 | 176639 | 70492 | 106147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 1377382 | 585032 | 792350 | 2024151 | 804658 | 1219493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 14941805 | 4841782 | 10100023 | 16882238 | 5456621 | 11425617 | 23867544 | 7637426 | 16230118 | 14941805 | 4841782 | 10100023 | 16882238 | 5456621 | 11425617 | 0 | 525205 | Iowa Communications Network | TRUE
NT10BIX5570069 | CCI | 2012 | Q3 | Q3 - 2012 | 19452467 | 6086722 | 13365745 | 13802302 | 4315839 | 9486463 | 15052302 | 4711667 | 10340635 | 1831073 | 553626 | 1277447 | 529302 | 158791 | 370511 | 1535925 | 462877 | 1073048 | 25000 | 25000 | 0 | 28047 | 25914 | 2133 | 200000 | 77500 | 122500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 1645629 | 686173 | 959456 | 1927635 | 774447 | 1153188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 16005280 | 5186717 | 10818563 | 18715862 | 6026491 | 12689371 | 23867544 | 7637426 | 16230118 | 16005280 | 5186717 | 10818563 | 18715862 | 6026491 | 12689371 | 0 | 1241444 | Iowa Communications Network | TRUE
NT10BIX5570069 | CCI | 2012 | Q4 | Q4 - 2012 | 19452467 | 6086722 | 13365745 | 14696488 | 4595737 | 10100751 | 17120416 | 5355721 | 11764695 | 1831073 | 553626 | 1277447 | 518354 | 155506 | 362848 | 1432846 | 429854 | 1002992 | 25000 | 25000 | 0 | 28047 | 25914 | 2133 | 28047 | 25914 | 2133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113097 | 33929 | 79168 | 243033 | 72910 | 170123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 1825692 | 742537 | 1083155 | 2179097 | 853159 | 1325938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 17181678 | 5553623 | 11628055 | 21003439 | 6737558 | 14265881 | 23867544 | 7637426 | 16230118 | 17181678 | 5553623 | 11628055 | 21003439 | 6737558 | 14265881 | 0 | 1833565 | Iowa Communications Network | TRUE
NT10BIX5570069 | CCI | 2013 | Q1 | Q1 - 2013 | 19452467 | 6086722 | 13365745 | 16718919 | 5219787 | 11499132 | 19686612 | 6163555 | 13523057 | 1831073 | 553626 | 1277447 | 572322 | 171697 | 400625 | 1526324 | 457897 | 1068427 | 25000 | 25000 | 0 | 28047 | 25914 | 2133 | 28047 | 25914 | 2133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113097 | 33929 | 79168 | 243033 | 72910 | 170123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2559004 | 972078 | 1586926 | 1979272 | 790610 | 1188662 | 2383528 | 917150 | 1466378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 19411657 | 6241937 | 13169720 | 23867544 | 7637426 | 16230118 | 23867544 | 7637426 | 16230118 | 19411657 | 6241937 | 13169720 | 23867544 | 7637426 | 16230118 | 0 | 2628105 | Iowa Communications Network | TRUE
NT10BIX5570069 | CCI | 2013 | Q2 | Q2 - 2013 | 18781048 | 5874182 | 12906866 | 17791911 | 5686097 | 12105814 | 17791911 | 5686097 | 12105814 | 1451448 | 438119 | 1013329 | 1409381 | 422814 | 986567 | 1409381 | 422814 | 986567 | 29000 | 26200 | 2800 | 30054 | 26516 | 3538 | 30054 | 26516 | 3538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193033 | 57910 | 135123 | 192063 | 57619 | 134444 | 192063 | 57619 | 134444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3413015 | 1241015 | 2172000 | 3315876 | 1083525 | 2232351 | 3315876 | 1083525 | 2232351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23867544 | 7637426 | 16230118 | 22739285 | 7276571 | 15462714 | 22739285 | 7276571 | 15462714 | 23867544 | 7637426 | 16230118 | 22739285 | 7276571 | 15462714 | 22739285 | 7276571 | 15462714 | 0 | 3659603 | Iowa Communications Network | TRUE
NT10BIX5570070 | CCI | 2010 | Q4 | Q4 - 2010 | 7044808 | 2252680 | 4792129 | 0 | 0 | 0 | 0 | 0 | 0 | 51193858 | 19660308 | 31533549 | 197470 | 63151 | 134319 | 5493536 | 5046990 | 446546 | 1871196 | 598342 | 1272854 | 846407 | 270681 | 575726 | 942032 | 301262 | 640770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 969844 | 310156 | 659688 | 1735263 | 554937 | 1180326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 221856 | 70950 | 150906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 2013721 | 643988 | 1369733 | 8392687 | 5974139 | 2418548 | 71645444 | 26200000 | 45445444 | 2013721 | 643988 | 1369733 | 8392687 | 5974139 | 2418548 | 0 | 0 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | CCI | 2011 | Q1 | Q1 - 2011 | 7044808 | 2252680 | 4792129 | 0 | 0 | 0 | 0 | 0 | 0 | 51193858 | 19660308 | 31533549 | 4952317 | 4782129 | 170188 | 6707920 | 5435350 | 1272569 | 1871196 | 598342 | 1272854 | 1331941 | 425955 | 905986 | 1499793 | 479634 | 1020159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 1576918 | 504298 | 1072620 | 2671461 | 854333 | 1817128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 7861176 | 5712382 | 2148794 | 10879174 | 6769317 | 4109856 | 71645444 | 26200000 | 45445444 | 7861176 | 5712382 | 2148794 | 10879174 | 6769317 | 4109856 | 0 | 15111 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | CCI | 2011 | Q2 | Q2 - 2011 | 7044808 | 2252680 | 4792129 | 0 | 0 | 0 | 46755 | 14952 | 31803 | 51193858 | 19660308 | 31533549 | 5642994 | 5018484 | 624510 | 12259053 | 7134300 | 5124753 | 1871196 | 598342 | 1272854 | 1497887 | 479024 | 1018863 | 1579815 | 505225 | 1074590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 2846470 | 910301 | 1936169 | 3384774 | 1082451 | 2302323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 9987351 | 6407809 | 3579542 | 17270397 | 8736928 | 8533469 | 71645444 | 26200000 | 45445444 | 9987351 | 6407809 | 3579542 | 17270397 | 8736928 | 8533469 | 0 | 55111 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | CCI | 2011 | Q3 | Q3 - 2011 | 7044808 | 2252680 | 4792129 | 0 | 0 | 0 | 890098 | 284653 | 605445 | 51193858 | 19660308 | 31533549 | 9908471 | 6428779 | 3479692 | 18635507 | 9219685 | 9415822 | 1871196 | 598342 | 1272854 | 1718696 | 549639 | 1169057 | 1800624 | 575840 | 1224784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 4114915 | 1315950 | 2798965 | 4814312 | 1539617 | 3274695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 221856 | 70950 | 150906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 15742082 | 8294368 | 7447714 | 26362397 | 11690745 | 14671652 | 71645444 | 26200000 | 45445444 | 15742082 | 8294368 | 7447714 | 26362397 | 11690745 | 14671652 | 0 | 95111 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | CCI | 2011 | Q4 | Q4 - 2011 | 7044808 | 2252680 | 4792129 | 1699347 | 543451 | 1155896 | 3316645 | 1060663 | 2255982 | 51193858 | 19660308 | 31533549 | 15381787 | 8139996 | 7241791 | 25544436 | 11390011 | 14154425 | 1871196 | 598342 | 1272854 | 1815016 | 580442 | 1234574 | 1933655 | 618383 | 1315272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 6110610 | 1954173 | 4156437 | 8201510 | 2622843 | 5578667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 75000 | 23985 | 51015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 25006760 | 11218062 | 13788698 | 39071246 | 15715885 | 23355361 | 71645444 | 26200000 | 45445444 | 25006760 | 11218062 | 13788698 | 39071246 | 15715885 | 23355361 | 0 | 135111 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | CCI | 2012 | Q1 | Q1 - 2012 | 7044808 | 2252680 | 4792129 | 2874533 | 984809 | 1889724 | 7051038 | 2613646 | 4437392 | 51193858 | 19660308 | 31533549 | 20859979 | 10172730 | 10687249 | 31166673 | 14192341 | 16974332 | 1871196 | 598342 | 1272854 | 1931425 | 621752 | 1309673 | 2021674 | 656949 | 1364725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 9073047 | 3042602 | 6030445 | 11229743 | 3883713 | 7346030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 75000 | 29250 | 45750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 34738984 | 14821893 | 19917091 | 51544128 | 21375899 | 30168229 | 71645444 | 26200000 | 45445444 | 34738984 | 14821893 | 19917091 | 51544128 | 21375899 | 30168229 | 0 | 186444 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | CCI | 2012 | Q2 | Q2 - 2012 | 7044808 | 2252680 | 4792129 | 5418177 | 1998521 | 3419656 | 8934594 | 3371293 | 5563301 | 51193858 | 19660308 | 31533549 | 30123324 | 13872606 | 16250718 | 37608277 | 16797240 | 20811037 | 1871196 | 598342 | 1272854 | 2033736 | 663459 | 1370277 | 2211693 | 732954 | 1478739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 10811236 | 3748386 | 7062850 | 12445750 | 4387598 | 8058152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 106233 | 41431 | 64802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 48386473 | 20282972 | 28103501 | 61306547 | 25330516 | 35976031 | 71645444 | 26200000 | 45445444 | 48386473 | 20282972 | 28103501 | 61306547 | 25330516 | 35976031 | 0 | 256444 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | CCI | 2012 | Q3 | Q3 - 2012 | 7044808 | 2252680 | 4792129 | 7639986 | 3064989 | 4574997 | 9304801 | 3864101 | 5440700 | 51193858 | 19660308 | 31533549 | 35402062 | 16406634 | 18995428 | 40794872 | 18995154 | 21799718 | 1871196 | 598342 | 1272854 | 2198879 | 742738 | 1456141 | 2383885 | 831540 | 1552345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 11297966 | 3980055 | 7317911 | 13137090 | 4862834 | 8274256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 145000 | 69600 | 75400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 56538893 | 24194416 | 32344477 | 65765648 | 28623229 | 37142419 | 71645444 | 26200000 | 45445444 | 56538893 | 24194416 | 32344477 | 65765648 | 28623229 | 37142419 | 0 | 326444 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | CCI | 2012 | Q4 | Q4 - 2012 | 7044808 | 2252680 | 4792129 | 8311382 | 3377799 | 4933583 | 9173116 | 3791431 | 5381685 | 51193858 | 19660308 | 31533549 | 40146090 | 18495369 | 21650721 | 46775127 | 21677278 | 25097849 | 1871196 | 598342 | 1272854 | 2318187 | 793108 | 1525079 | 2520055 | 890005 | 1630050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 12225955 | 4350107 | 7875848 | 13234137 | 4834034 | 8400103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 0 | 0 | 0 | 343264 | 164767 | 178497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 63001614 | 27016383 | 35985231 | 72045699 | 31357515 | 40688184 | 71645444 | 26200000 | 45445444 | 63001614 | 27016383 | 35985231 | 72045699 | 31357515 | 40688184 | 0 | 396444 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | CCI | 2013 | Q1 | Q1 - 2013 | 7044808 | 2252680 | 4792129 | 9323284 | 3819265 | 5504019 | 10193254 | 4236850 | 5956403 | 51193858 | 19660308 | 31533549 | 47998725 | 21871344 | 26127381 | 53313234 | 24422309 | 28890925 | 1871196 | 598342 | 1272854 | 2380725 | 818977 | 1561748 | 2510774 | 881400 | 1629374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 13001906 | 4669276 | 8332630 | 15496891 | 5866869 | 9630022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 258854 | 105492 | 153362 | 489841 | 216365 | 273476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 72963494 | 31284354 | 41679140 | 82003994 | 35623793 | 46380200 | 71645444 | 26200000 | 45445444 | 72963494 | 31284354 | 41679140 | 82003994 | 35623793 | 46380200 | 0 | 469677 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | CCI | 2013 | Q2 | Q2 - 2013 | 7044808 | 2252680 | 4792129 | 10140947 | 4293076 | 5847871 | 10247217 | 4399346 | 5847871 | 51193858 | 19660308 | 31533549 | 53255744 | 24917630 | 28338114 | 55869406 | 27531292 | 28338114 | 1871196 | 598342 | 1272854 | 2520701 | 900089 | 1620612 | 2731931 | 1111319 | 1620612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 15431289 | 6077031 | 9354258 | 16746847 | 7392589 | 9354258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 570904 | 286315 | 284589 | 934717 | 650128 | 284589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 81919585 | 36474141 | 45445444 | 86530118 | 41084674 | 45445444 | 71645444 | 26200000 | 45445444 | 81919585 | 36474141 | 45445444 | 86530118 | 41084674 | 45445444 | 0 | 551301 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | CCI | 2013 | Q3 | Q3 - 2013 | 7044808 | 2252680 | 4792129 | 10460006 | 4612135 | 5847871 | 11159892 | 5312021 | 5847871 | 51193858 | 19660308 | 31533549 | 55084769 | 26746655 | 28338114 | 56085466 | 27747352 | 28338114 | 1871196 | 598342 | 1272854 | 2603564 | 982952 | 1620612 | 2775505 | 1154893 | 1620612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 16161593 | 6807335 | 9354258 | 17227926 | 7873668 | 9354258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 898570 | 613981 | 284589 | 1241906 | 957317 | 284589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 85208502 | 39763058 | 45445444 | 88490695 | 43045251 | 45445444 | 71645444 | 26200000 | 45445444 | 85208502 | 39763058 | 45445444 | 88490695 | 43045251 | 45445444 | 0 | 603479 | Massachusetts Technology Park | TRUE
NT10BIX5570070 | CCI | 2013 | Q4 | Q4 - 2013 | 7044808 | 2252680 | 4792129 | 10720121 | 4872250 | 5847871 | 11161203 | 5313332 | 5847871 | 51193858 | 19660308 | 31533549 | 55501812 | 27163698 | 28338114 | 56445180 | 28107066 | 28338114 | 1871196 | 598342 | 1272854 | 2742104 | 1121492 | 1620612 | 2917042 | 1296430 | 1620612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9317022 | 2979253 | 6337769 | 17283720 | 7929462 | 9354258 | 17685291 | 8331033 | 9354258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2218560 | 709417 | 1509143 | 1175221 | 890632 | 284589 | 1476469 | 1191880 | 284589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71645444 | 26200000 | 45445444 | 87422978 | 41977534 | 45445444 | 89685185 | 44239741 | 45445444 | 71645444 | 26200000 | 45445444 | 87422978 | 41977534 | 45445444 | 89685185 | 44239741 | 45445444 | 0 | 612896 | Massachusetts Technology Park | TRUE
NT10BIX5570071 | CCI | 2010 | Q4 | Q4 - 2010 | 2647380 | 794214 | 1853166 | 0 | 0 | 0 | 800000 | 240000 | 560000 | 15271893 | 4581568 | 10690325 | 0 | 0 | 0 | 1313255 | 393976 | 919279 | 172263 | 51679 | 120884 | 0 | 0 | 0 | 172263 | 51679 | 120884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 0 | 0 | 0 | 250000 | 75000 | 175000 | 422675 | 126803 | 295872 | 0 | 0 | 0 | 120000 | 36000 | 84000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19117990 | 5735398 | 13382892 | 0 | 0 | 0 | 2655518 | 796655 | 1859163 | 19117990 | 5735398 | 13382892 | 0 | 0 | 0 | 2655518 | 796655 | 1859163 | 0 | 0 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570071 | CCI | 2011 | Q1 | Q1 - 2011 | 2647380 | 794214 | 1853166 | 0 | 0 | 0 | 400000 | 120000 | 280000 | 15271893 | 4581567 | 10690326 | 1610 | 483 | 1127 | 451610 | 135483 | 316127 | 172263 | 51679 | 120584 | 172263 | 51679 | 120584 | 172263 | 51679 | 120584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 260881 | 78264 | 182617 | 327491 | 98247 | 229244 | 422675 | 126803 | 295872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19117990 | 5735397 | 13382593 | 434754 | 130426 | 304328 | 1351364 | 405409 | 945955 | 19117990 | 5735397 | 13382593 | 434754 | 130426 | 304328 | 1351364 | 405409 | 945955 | 0 | 0 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570071 | CCI | 2011 | Q2 | Q2 - 2011 | 2647380 | 794214 | 1853166 | 7231 | 2169 | 5062 | 1607231 | 482169 | 1125062 | 15271893 | 4581568 | 10690325 | 74517 | 22355 | 52162 | 1069517 | 320855 | 748662 | 172263 | 51679 | 120584 | 172263 | 51679 | 120584 | 172263 | 51679 | 120584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 357772 | 107332 | 250440 | 421127 | 126338 | 294789 | 422675 | 126802 | 295873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19117990 | 5735397 | 13382593 | 611783 | 183535 | 428248 | 3270138 | 981041 | 2289097 | 19117990 | 5735397 | 13382593 | 611783 | 183535 | 428248 | 3270138 | 981041 | 2289097 | 0 | 0 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570071 | CCI | 2011 | Q3 | Q3 - 2011 | 2647380 | 794214 | 1853166 | 1897727 | 569318 | 1328409 | 2157727 | 647318 | 1510409 | 15271893 | 4581568 | 10690325 | 826081 | 247824 | 578257 | 2360081 | 708024 | 1652057 | 172263 | 51679 | 120584 | 172263 | 51679 | 120584 | 172263 | 51679 | 120584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 0 | 0 | 0 | 110000 | 33000 | 77000 | 422675 | 126803 | 295872 | 425931 | 127779 | 298152 | 425931 | 127779 | 298152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19117990 | 5735398 | 13382592 | 3322002 | 996600 | 2325402 | 5226002 | 1567800 | 3658202 | 19117990 | 5735398 | 13382592 | 3322002 | 996600 | 2325402 | 5226002 | 1567800 | 3658202 | 0 | 0 | Zayo Bandwidth, LLC | TRUE
NT10BIX5570072 | CCI | 2010 | Q4 | Q4 - 2010 | 8758868 | 3877761 | 4881107 | 189385 | 189385 | 0 | 2135250 | 1727623 | 407627 | 30306281 | 7831123 | 22475158 | 31409 | 7538 | 23871 | 323966 | 125581 | 198385 | 186863 | 75013 | 111850 | 110983 | 26636 | 84347 | 176969 | 67303 | 109666 | 1497801 | 542165 | 955636 | 8600 | 2064 | 6536 | 117899 | 53083 | 64816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 143984 | 34556 | 109428 | 266890 | 64054 | 202836 | 282530 | 84759 | 197771 | 184852 | 51127 | 133725 | 208852 | 58327 | 150525 | 130000 | 31200 | 98800 | 0 | 0 | 0 | 2600 | 624 | 1976 | 205600 | 61680 | 143920 | 0 | 0 | 0 | 20700 | 6210 | 14490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 669213 | 311306 | 357907 | 3253126 | 2102805 | 1150321 | 42904268 | 12872419 | 30031849 | 669213 | 311306 | 357907 | 3253126 | 2102805 | 1150321 | 0 | 0 | COM Net, Inc. | TRUE
NT10BIX5570072 | CCI | 2011 | Q1 | Q1 - 2011 | 8758868 | 3877761 | 4881107 | 206831 | 193572 | 13259 | 2219070 | 1751678 | 467392 | 30306281 | 7831123 | 22475158 | 48117 | 11548 | 36569 | 1439859 | 359966 | 1079893 | 186863 | 75013 | 111850 | 148967 | 35752 | 113215 | 179484 | 44591 | 134893 | 1497801 | 542165 | 955636 | 21350 | 5124 | 16226 | 65100 | 16824 | 48276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 197529 | 47407 | 150122 | 430698 | 103368 | 327330 | 282530 | 84759 | 197771 | 210099 | 57186 | 152913 | 210099 | 57186 | 152913 | 130000 | 31200 | 98800 | 0 | 0 | 0 | 19607 | 4706 | 14901 | 205600 | 61680 | 143920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 832893 | 350589 | 482304 | 4563917 | 2338319 | 2225598 | 42904268 | 12872419 | 30031849 | 832893 | 350589 | 482304 | 4563917 | 2338319 | 2225598 | 0 | 0 | COM Net, Inc. | TRUE
NT10BIX5570072 | CCI | 2011 | Q2 | Q2 - 2011 | 8758868 | 3877761 | 4881107 | 1880202 | 1648647 | 231555 | 2692997 | 2361339 | 331658 | 30306281 | 7831123 | 22475158 | 614972 | 320655 | 294317 | 2939687 | 1532794 | 1406893 | 186863 | 75013 | 111850 | 198772 | 60095 | 138677 | 224490 | 85913 | 138577 | 1497801 | 542165 | 955636 | 45300 | 10872 | 34428 | 113566 | 27256 | 86310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 393995 | 94559 | 299436 | 541891 | 130054 | 411837 | 282530 | 84759 | 197771 | 215002 | 58363 | 156639 | 215002 | 58363 | 156639 | 130000 | 31200 | 98800 | 9677 | 2322 | 7355 | 12764 | 3829 | 8935 | 205600 | 61680 | 143920 | 0 | 0 | 0 | 20000 | 6000 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 3357920 | 2195513 | 1162407 | 6760397 | 4205548 | 2554849 | 42904268 | 12872419 | 30031849 | 3357920 | 2195513 | 1162407 | 6760397 | 4205548 | 2554849 | 0 | 1190 | COM Net, Inc. | TRUE
NT10BIX5570072 | CCI | 2011 | Q3 | Q3 - 2011 | 8758868 | 3877761 | 4881107 | 2475470 | 1827227 | 648243 | 3158300 | 2331247 | 827053 | 30306281 | 7831123 | 22475158 | 2230100 | 769165 | 1460935 | 3589093 | 1237884 | 2351209 | 186863 | 75013 | 111850 | 259995 | 74788 | 185207 | 344965 | 99230 | 245735 | 1497801 | 542165 | 955636 | 121376 | 30663 | 90713 | 176940 | 44700 | 132240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 535919 | 128621 | 407298 | 587202 | 140929 | 446273 | 282530 | 84759 | 197771 | 215002 | 58363 | 156639 | 215001 | 58363 | 156638 | 130000 | 31200 | 98800 | 48118 | 11549 | 36569 | 76028 | 18247 | 57781 | 205600 | 61680 | 143920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 5885980 | 2900376 | 2985604 | 8147529 | 3930600 | 4216929 | 42904268 | 12872419 | 30031849 | 5885980 | 2900376 | 2985604 | 8147529 | 3930600 | 4216929 | 0 | 0 | COM Net, Inc. | TRUE
NT10BIX5570072 | CCI | 2011 | Q4 | Q4 - 2011 | 8758868 | 3877761 | 4881107 | 2960289 | 1972673 | 987616 | 3408761 | 2080308 | 1328453 | 30306281 | 7831123 | 22475158 | 3651645 | 1110336 | 2541309 | 7072918 | 1931441 | 5141477 | 186863 | 75013 | 111850 | 331771 | 92835 | 238936 | 441374 | 125716 | 315658 | 1497801 | 542165 | 955636 | 195454 | 49162 | 146292 | 253405 | 66547 | 186858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 694040 | 166570 | 527470 | 988133 | 254797 | 733336 | 282530 | 84759 | 197771 | 215001 | 58363 | 156638 | 241136 | 66204 | 174932 | 130000 | 31200 | 98800 | 93185 | 22364 | 70821 | 131455 | 33846 | 97609 | 205600 | 61680 | 143920 | 4040 | 1212 | 2828 | 25272 | 7582 | 17690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 8145425 | 3473515 | 4671910 | 12562454 | 4566441 | 7996013 | 42904268 | 12872419 | 30031849 | 8145425 | 3473515 | 4671910 | 12562454 | 4566441 | 7996013 | 0 | 0 | COM Net, Inc. | TRUE
NT10BIX5570072 | CCI | 2012 | Q1 | Q1 - 2012 | 8758868 | 3877761 | 4881107 | 3690023 | 2236403 | 1453620 | 5595449 | 3391220 | 2204229 | 30306281 | 7831123 | 22475158 | 6200772 | 1722127 | 4478646 | 9030631 | 2508057 | 6522574 | 186863 | 75013 | 111850 | 433892 | 117344 | 316548 | 489000 | 132248 | 356752 | 1497801 | 542165 | 955636 | 267984 | 66569 | 201415 | 301687 | 74941 | 226746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 877450 | 210588 | 666862 | 1165410 | 279698 | 885712 | 282530 | 84759 | 197771 | 215001 | 58363 | 156638 | 278757 | 75670 | 203087 | 130000 | 31200 | 98800 | 123828 | 29718 | 94109 | 166589 | 39981 | 126608 | 205600 | 61680 | 143920 | 4040 | 1212 | 2828 | 31272 | 9382 | 21890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 11812990 | 4442324 | 7370666 | 17058795 | 6511197 | 10547598 | 42904268 | 12872419 | 30031849 | 11812990 | 4442324 | 7370666 | 17058795 | 6511197 | 10547598 | 0 | 0 | COM Net, Inc. | TRUE
NT10BIX5570072 | CCI | 2012 | Q2 | Q2 - 2012 | 8758868 | 3877761 | 4881107 | 5135871 | 2880399 | 2255472 | 5728191 | 3471670 | 2256521 | 30306281 | 7831123 | 22475158 | 8627650 | 2316407 | 6311243 | 11138633 | 3093508 | 8045125 | 186863 | 75013 | 111850 | 485532 | 129738 | 355794 | 492992 | 133327 | 359665 | 1497801 | 542165 | 955636 | 398808 | 97962 | 300846 | 366897 | 91140 | 275757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 959536 | 230289 | 729247 | 983987 | 236157 | 747830 | 282530 | 84759 | 197771 | 215001 | 58363 | 156638 | 300976 | 81701 | 219275 | 130000 | 31200 | 98800 | 174079 | 41779 | 132300 | 213734 | 51296 | 162438 | 205600 | 61680 | 143920 | 4486 | 1319 | 3167 | 63200 | 18960 | 44240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 16000963 | 5756256 | 10244707 | 19288610 | 7177759 | 12110851 | 42904268 | 12872419 | 30031849 | 16000963 | 5756256 | 10244707 | 19288610 | 7177759 | 12110851 | 0 | 0 | COM Net, Inc. | TRUE
NT10BIX5570072 | CCI | 2012 | Q3 | Q3 - 2012 | 8758868 | 3877761 | 4881107 | 5587352 | 3042442 | 2544910 | 6463092 | 3519304 | 2943788 | 30306281 | 7831123 | 22475158 | 11587812 | 3036779 | 8551033 | 16657215 | 4365302 | 12291913 | 186863 | 75013 | 111850 | 522939 | 138716 | 384223 | 576201 | 152844 | 423357 | 1497801 | 542165 | 955636 | 528660 | 135929 | 392731 | 607772 | 156270 | 451502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 1140111 | 273627 | 866484 | 1298558 | 311654 | 986904 | 282530 | 84759 | 197771 | 229476 | 61837 | 167639 | 241685 | 65127 | 176558 | 130000 | 31200 | 98800 | 209449 | 50267 | 159182 | 274349 | 65844 | 208505 | 205600 | 61680 | 143920 | 74709 | 22329 | 52380 | 118475 | 35410 | 83065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 19880508 | 6761926 | 13118582 | 26237347 | 8671755 | 17565592 | 42904268 | 12872419 | 30031849 | 19880508 | 6761926 | 13118582 | 26237347 | 8671755 | 17565592 | 0 | 0 | COM Net, Inc. | TRUE
NT10BIX5570072 | CCI | 2012 | Q4 | Q4 - 2012 | 8758868 | 3877761 | 4881107 | 6239273 | 3211420 | 3027853 | 6658258 | 3337116 | 3321142 | 30306281 | 7831123 | 22475158 | 15367047 | 3962741 | 11404306 | 20205928 | 5412615 | 14793313 | 186863 | 75013 | 111850 | 574245 | 151029 | 423216 | 607310 | 165798 | 441512 | 1497801 | 542165 | 955636 | 659388 | 172551 | 486837 | 757993 | 205934 | 552059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 1289194 | 309407 | 979787 | 2018933 | 504734 | 1514199 | 282530 | 84759 | 197771 | 242814 | 65038 | 177776 | 242814 | 65038 | 177776 | 130000 | 31200 | 98800 | 253027 | 60726 | 192301 | 259921 | 64980 | 194941 | 205600 | 61680 | 143920 | 74709 | 22329 | 52380 | 91871 | 28377 | 63494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 24699697 | 7955241 | 16744456 | 30843028 | 9784592 | 21058436 | 42904268 | 12872419 | 30031849 | 24699697 | 7955241 | 16744456 | 30843028 | 9784592 | 21058436 | 0 | 0 | COM Net, Inc. | TRUE
NT10BIX5570072 | CCI | 2013 | Q1 | Q1 - 2013 | 8758868 | 3877761 | 4881107 | 6757333 | 3366838 | 3390495 | 8752578 | 4376289 | 4376289 | 30306281 | 7831123 | 22475158 | 18447936 | 4729767 | 13718169 | 23834356 | 5958589 | 17875767 | 186863 | 75013 | 111850 | 648616 | 177552 | 471064 | 687453 | 192487 | 494966 | 1497801 | 542165 | 955636 | 728763 | 193323 | 535440 | 764763 | 198838 | 565925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 1316702 | 316008 | 1000694 | 1366072 | 327857 | 1038215 | 282530 | 84759 | 197771 | 255180 | 68006 | 187174 | 269180 | 69987 | 199193 | 130000 | 31200 | 98800 | 294971 | 70793 | 224178 | 344593 | 79256 | 265337 | 205600 | 61680 | 143920 | 74709 | 22329 | 52380 | 196262 | 56916 | 139346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 28524210 | 8944616 | 19579594 | 36215257 | 11260219 | 24955038 | 42904268 | 12872419 | 30031849 | 28524210 | 8944616 | 19579594 | 36215257 | 11260219 | 24955038 | 0 | 0 | COM Net, Inc. | TRUE
NT10BIX5570072 | CCI | 2013 | Q2 | Q2 - 2013 | 8758868 | 3877761 | 4881107 | 6924905 | 3503460 | 3421445 | 9493779 | 4649627 | 4844152 | 30306281 | 7831123 | 22475158 | 22341769 | 5636674 | 16705095 | 28235192 | 6776446 | 21458746 | 186863 | 75013 | 111850 | 683260 | 185867 | 497393 | 802594 | 240778 | 561816 | 1497801 | 542165 | 955636 | 804726 | 213256 | 591470 | 921313 | 276394 | 644919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 1368724 | 328494 | 1040230 | 1455526 | 349326 | 1106200 | 282530 | 84759 | 197771 | 271166 | 71842 | 199324 | 300694 | 90208 | 210486 | 130000 | 31200 | 98800 | 334097 | 80183 | 253914 | 359448 | 87788 | 271660 | 205600 | 61680 | 143920 | 74709 | 22329 | 52380 | 148971 | 44691 | 104280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 32803356 | 10042105 | 22761251 | 41717517 | 12515258 | 29202259 | 42904268 | 12872419 | 30031849 | 32803356 | 10042105 | 22761251 | 41717517 | 12515258 | 29202259 | 0 | 0 | COM Net, Inc. | TRUE
NT10BIX5570072 | CCI | 2013 | Q3 | Q3 - 2013 | 8758868 | 3877761 | 4881107 | 9356354 | 4158259 | 5198095 | 9356354 | 4158259 | 5198095 | 30306281 | 7831123 | 22475158 | 26940177 | 6898563 | 20041614 | 26940177 | 6898563 | 20041614 | 186863 | 75013 | 111850 | 781208 | 212516 | 568692 | 781208 | 212516 | 568692 | 1497801 | 542165 | 955636 | 961835 | 258390 | 703445 | 961835 | 258390 | 703445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536325 | 368718 | 1167607 | 1388419 | 333606 | 1054813 | 1388419 | 333606 | 1054813 | 282530 | 84759 | 197771 | 280507 | 74089 | 206418 | 280507 | 74089 | 206418 | 130000 | 31200 | 98800 | 379809 | 91154 | 288655 | 379809 | 91154 | 288655 | 205600 | 61680 | 143920 | 112532 | 33675 | 78857 | 112532 | 33675 | 78857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42904268 | 12872419 | 30031849 | 40200841 | 12060252 | 28140589 | 40200841 | 12060252 | 28140589 | 42904268 | 12872419 | 30031849 | 40200841 | 12060252 | 28140589 | 40200841 | 12060252 | 28140589 | 0 | 0 | COM Net, Inc. | TRUE
NT10BIX5570073 | CCI | 2010 | Q4 | Q4 - 2010 | 1047656 | 314297 | 733359 | 0 | 0 | 0 | 0 | 0 | 0 | 4788511 | 1436553 | 3351958 | 0 | 0 | 0 | 0 | 0 | 0 | 329125 | 98738 | 230387 | 33199 | 9960 | 23239 | 77949 | 23385 | 54564 | 121855 | 36557 | 85298 | 7500 | 2250 | 5250 | 37500 | 11250 | 26250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25375 | 7612 | 17763 | 16915 | 5075 | 11840 | 25375 | 7612 | 17763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 57614 | 17285 | 40329 | 140824 | 42247 | 98577 | 6312522 | 1893757 | 4418765 | 57614 | 17285 | 40329 | 140824 | 42247 | 98577 | 0 | 0 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | CCI | 2011 | Q1 | Q1 - 2011 | 1047656 | 314297 | 733359 | 0 | 0 | 0 | 314998 | 220499 | 94499 | 4788511 | 1436553 | 3351958 | 0 | 0 | 0 | 169577 | 118704 | 50873 | 329125 | 98738 | 230387 | 33199 | 9960 | 23239 | 86688 | 47402 | 39286 | 121855 | 36557 | 85298 | 7500 | 2250 | 5250 | 53370 | 34359 | 19011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25375 | 7612 | 17763 | 16915 | 5075 | 11840 | 35375 | 17997 | 17378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 57614 | 17285 | 40329 | 660008 | 438961 | 221047 | 6312522 | 1893757 | 4418765 | 57614 | 17285 | 40329 | 660008 | 438961 | 221047 | 0 | 0 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | CCI | 2011 | Q2 | Q2 - 2011 | 1856242 | 556873 | 1299369 | 7898 | 2369 | 5529 | 1409682 | 422905 | 986777 | 3914725 | 1174417 | 2740308 | 0 | 0 | 0 | 26833 | 8050 | 18783 | 349700 | 104910 | 244790 | 81753 | 24526 | 57226 | 144936 | 43480 | 101456 | 121855 | 36557 | 85298 | 47955 | 14387 | 33569 | 57955 | 17387 | 40568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 28210 | 8464 | 19747 | 48210 | 14463 | 33747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 165816 | 49746 | 116071 | 1687616 | 506285 | 1181331 | 6312522 | 1893757 | 4418765 | 165816 | 49746 | 116071 | 1687616 | 506285 | 1181331 | 0 | 0 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | CCI | 2011 | Q3 | Q3 - 2011 | 1856242 | 556873 | 1299369 | 1417685 | 425306 | 992379 | 1842991 | 425306 | 1417685 | 3914725 | 1174417 | 2740308 | 0 | 0 | 0 | 735015 | 220505 | 514510 | 349700 | 104910 | 244790 | 141842 | 42553 | 99289 | 214422 | 64327 | 150095 | 121855 | 36557 | 85298 | 71155 | 21347 | 49809 | 100740 | 30222 | 70518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 49473 | 14842 | 34631 | 62308 | 18692 | 43616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 1680155 | 504048 | 1176108 | 2955476 | 759052 | 2196424 | 6312522 | 1893757 | 4418765 | 1680155 | 504048 | 1176108 | 2955476 | 759052 | 2196424 | 0 | 0 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | CCI | 2011 | Q4 | Q4 - 2011 | 1856242 | 556873 | 1299369 | 1417685 | 425306 | 992379 | 1417685 | 425306 | 992379 | 3914725 | 1174417 | 2740308 | 61271 | 18381 | 42890 | 2999482 | 899845 | 2099637 | 349700 | 104910 | 244790 | 175573 | 52668 | 122905 | 220578 | 66173 | 154405 | 121855 | 36557 | 85298 | 107788 | 32337 | 75451 | 117795 | 35339 | 82456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 91354 | 27407 | 63948 | 91354 | 27407 | 63948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 1853671 | 556099 | 1297573 | 4846894 | 1454070 | 3392825 | 6312522 | 1893757 | 4418765 | 1853671 | 556099 | 1297573 | 4846894 | 1454070 | 3392825 | 0 | 0 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | CCI | 2012 | Q1 | Q1 - 2012 | 1856242 | 556873 | 1299369 | 1469933 | 440980 | 1028953 | 1559933 | 467980 | 1091953 | 3914725 | 1174417 | 2740308 | 157014 | 47104 | 109910 | 2357014 | 707104 | 1649910 | 349700 | 104910 | 244790 | 218919 | 65672 | 153247 | 235947 | 70784 | 165163 | 121855 | 36557 | 85298 | 112038 | 33612 | 78426 | 117038 | 35111 | 81927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 102518 | 30756 | 71762 | 127518 | 38255 | 89263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 2060422 | 618124 | 1442298 | 4397450 | 1319234 | 3078216 | 6312522 | 1893757 | 4418765 | 2060422 | 618124 | 1442298 | 4397450 | 1319234 | 3078216 | 0 | 0 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | CCI | 2012 | Q2 | Q2 - 2012 | 1856242 | 556873 | 1299369 | 1552525 | 465757 | 1086768 | 1817243 | 545173 | 1272070 | 3914725 | 1174417 | 2740308 | 1076385 | 322917 | 753467 | 3269279 | 980784 | 2288495 | 349700 | 104910 | 244790 | 235640 | 70692 | 164948 | 251074 | 75322 | 175752 | 121855 | 36557 | 85298 | 114038 | 34211 | 79827 | 119038 | 35711 | 83327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 120764 | 36229 | 84535 | 195762 | 58729 | 137033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 3099352 | 929806 | 2169545 | 5652396 | 1695719 | 3956677 | 6312522 | 1893757 | 4418765 | 3099352 | 929806 | 2169545 | 5652396 | 1695719 | 3956677 | 0 | 0 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | CCI | 2012 | Q3 | Q3 - 2012 | 1856242 | 556873 | 1299369 | 1729224 | 518768 | 1210456 | 1900000 | 570000 | 1330000 | 3914725 | 1174417 | 2740308 | 2620205 | 786061 | 1834144 | 3650000 | 1095000 | 2555000 | 349700 | 104910 | 244790 | 268030 | 80409 | 187621 | 293030 | 87909 | 205121 | 121855 | 36557 | 85298 | 114038 | 34211 | 79827 | 114038 | 34211 | 79827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 153426 | 46028 | 107398 | 153426 | 46028 | 107398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 4884923 | 1465477 | 3419446 | 6110494 | 1833148 | 4277346 | 6312522 | 1893757 | 4418765 | 4884923 | 1465477 | 3419446 | 6110494 | 1833148 | 4277346 | 0 | 4400 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | CCI | 2012 | Q4 | Q4 - 2012 | 1856242 | 556873 | 1299369 | 1891150 | 567346 | 1323804 | 1891150 | 567346 | 1323804 | 3914725 | 1174417 | 2740308 | 3242446 | 972734 | 2269712 | 3650000 | 1095000 | 2555000 | 349700 | 104910 | 244790 | 281664 | 84499 | 197165 | 300000 | 90000 | 210000 | 121855 | 36557 | 85298 | 115118 | 34535 | 80583 | 115118 | 34535 | 80583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 155273 | 46582 | 108691 | 155273 | 46582 | 108691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 5685651 | 1705696 | 3979955 | 6111541 | 1833463 | 4278078 | 6312522 | 1893757 | 4418765 | 5685651 | 1705696 | 3979955 | 6111541 | 1833463 | 4278078 | 0 | 34052 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | CCI | 2013 | Q1 | Q1 - 2013 | 1856242 | 556873 | 1299369 | 2053076 | 615923 | 1437153 | 2223181 | 666912 | 1556269 | 3914725 | 1174417 | 2740308 | 3528370 | 1058554 | 2469816 | 3528370 | 1058554 | 2469816 | 349700 | 104910 | 244790 | 290440 | 87132 | 203308 | 290440 | 87132 | 203308 | 121855 | 36557 | 85298 | 115258 | 34577 | 80681 | 115258 | 34577 | 80681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 155273 | 46582 | 108691 | 155273 | 46582 | 108691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 6142417 | 1842768 | 4299649 | 6312522 | 1893757 | 4418765 | 6312522 | 1893757 | 4418765 | 6142417 | 1842768 | 4299649 | 6312522 | 1893757 | 4418765 | 0 | 15000 | Bend Cable Communications, LLC | TRUE
NT10BIX5570073 | CCI | 2013 | Q2 | Q2 - 2013 | 1856242 | 556873 | 1299369 | 2266652 | 723464 | 1543188 | 2266652 | 723464 | 1543188 | 3914725 | 1174417 | 2740308 | 3535315 | 1060595 | 2474720 | 3535315 | 1060595 | 2474720 | 349700 | 104910 | 244790 | 295177 | 88553 | 206624 | 295177 | 88553 | 206624 | 121855 | 36557 | 85298 | 122203 | 36661 | 85542 | 122203 | 36661 | 85542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 21000 | 49000 | 155273 | 46582 | 108691 | 155273 | 46582 | 108691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6312522 | 1893757 | 4418765 | 6374620 | 1955855 | 4418765 | 6374620 | 1955855 | 4418765 | 6312522 | 1893757 | 4418765 | 6374620 | 1955855 | 4418765 | 6374620 | 1955855 | 4418765 | 0 | 56144 | Bend Cable Communications, LLC | TRUE
NT10BIX5570074 | CCI | 2010 | Q4 | Q4 - 2010 | 2865257 | 573051 | 2292206 | 137052 | 27410 | 109642 | 329652 | 65930 | 263722 | 21603817 | 4320764 | 17283053 | 90645 | 18130 | 72515 | 277610 | 55522 | 222088 | 93905 | 18781 | 75124 | 21700 | 4340 | 17360 | 73948 | 14789 | 59159 | 768000 | 153600 | 614400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 31062 | 6212 | 24850 | 56062 | 11213 | 44849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 22550 | 4510 | 18040 | 37550 | 7510 | 30040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 303009 | 60602 | 242407 | 774822 | 154964 | 619858 | 25906278 | 5181256 | 20725022 | 303009 | 60602 | 242407 | 774822 | 154964 | 619858 | 0 | 0 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | CCI | 2011 | Q1 | Q1 - 2011 | 2865257 | 573051 | 2292206 | 143591 | 28718 | 114873 | 315791 | 63158 | 252633 | 21603817 | 4320764 | 17283053 | 185895 | 37179 | 148715 | 967724 | 193545 | 774179 | 93905 | 18781 | 75124 | 75884 | 15177 | 60707 | 85884 | 17177 | 68707 | 768000 | 153600 | 614400 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 119023 | 23805 | 95218 | 119163 | 23833 | 95330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 60411 | 12082 | 48329 | 66411 | 13282 | 53129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 584804 | 116961 | 467842 | 1637473 | 327495 | 1309978 | 25906278 | 5181256 | 20725022 | 584804 | 116961 | 467842 | 1637473 | 327495 | 1309978 | 0 | 0 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | CCI | 2011 | Q2 | Q2 - 2011 | 2865257 | 573051 | 2292206 | 409288 | 81858 | 327430 | 915791 | 183158 | 732633 | 21603817 | 4320764 | 17283053 | 856044 | 171208 | 684836 | 3356045 | 671209 | 2684836 | 93905 | 18781 | 75124 | 77654 | 15531 | 62123 | 78654 | 15731 | 62923 | 768000 | 153600 | 614400 | 72144 | 14429 | 57715 | 88024 | 17605 | 70419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 119740 | 23948 | 95792 | 125740 | 25148 | 100592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 81299 | 16260 | 65039 | 99299 | 19860 | 79439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 1616169 | 323234 | 1292935 | 4663553 | 932711 | 3730842 | 25906278 | 5181256 | 20725022 | 1616169 | 323234 | 1292935 | 4663553 | 932711 | 3730842 | 0 | 0 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | CCI | 2011 | Q3 | Q3 - 2011 | 2865258 | 573052 | 2292206 | 435893 | 87179 | 348714 | 538834 | 107767 | 431067 | 21603816 | 4320763 | 17283053 | 1906208 | 381242 | 1524966 | 6297797 | 1259559 | 5038238 | 93905 | 18781 | 75124 | 78866 | 15773 | 63093 | 80866 | 16173 | 64693 | 768000 | 153600 | 614400 | 72144 | 14429 | 57715 | 88024 | 17605 | 70419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 120835 | 24167 | 96668 | 125740 | 25148 | 100592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 91944 | 18389 | 73555 | 112944 | 22589 | 90355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 2705890 | 541179 | 2164711 | 7244205 | 1448841 | 5795364 | 25906278 | 5181256 | 20725022 | 2705890 | 541179 | 2164711 | 7244205 | 1448841 | 5795364 | 444621 | 390000 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | CCI | 2011 | Q4 | Q4 - 2011 | 2865258 | 573052 | 2292206 | 663399 | 132680 | 530719 | 718620 | 143724 | 574896 | 21603816 | 4320763 | 17283053 | 5220523 | 1044105 | 4176418 | 8363374 | 1672675 | 6690699 | 93905 | 18781 | 75124 | 80144 | 16029 | 64115 | 81000 | 16200 | 64800 | 768000 | 153600 | 614400 | 72144 | 14429 | 57715 | 154180 | 30836 | 123344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 125740 | 25148 | 100592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 110500 | 22100 | 88400 | 140500 | 28100 | 112400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 6268104 | 1253622 | 5014482 | 9583414 | 1916683 | 7666731 | 25906278 | 5181256 | 20725022 | 6268104 | 1253622 | 5014482 | 9583414 | 1916683 | 7666731 | 889241 | 166340 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | CCI | 2012 | Q1 | Q1 - 2012 | 2865258 | 573052 | 2292206 | 784361 | 156872 | 627489 | 1985661 | 397132 | 1588529 | 21603816 | 4320763 | 17283053 | 7682542 | 1536509 | 6146033 | 14741794 | 2948213 | 11792581 | 93905 | 18781 | 75124 | 83257 | 16651 | 66606 | 93905 | 18781 | 75124 | 768000 | 153600 | 614400 | 87701 | 17540 | 70161 | 200401 | 40080 | 160321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 129975 | 25995 | 103980 | 186175 | 37235 | 148940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 8889230 | 1777846 | 7111384 | 17357936 | 3471441 | 13885495 | 25906278 | 5181256 | 20725022 | 8889230 | 1777846 | 7111384 | 17357936 | 3471441 | 13885495 | 1443041 | 276831 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | CCI | 2012 | Q2 | Q2 - 2012 | 2865258 | 573052 | 2292206 | 879408 | 175882 | 703526 | 1985661 | 397132 | 1588529 | 21603816 | 4320763 | 17283053 | 13899806 | 2779960 | 11119846 | 16993440 | 3398688 | 13594752 | 93905 | 18781 | 75124 | 83926 | 16785 | 67141 | 93905 | 18781 | 75124 | 768000 | 153600 | 614400 | 498413 | 99683 | 398730 | 565840 | 113168 | 452672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 167588 | 33518 | 134070 | 227175 | 45435 | 181740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 15650535 | 3130107 | 12520428 | 20016021 | 4003204 | 16012817 | 25906278 | 5181256 | 20725022 | 15650535 | 3130107 | 12520428 | 20016021 | 4003204 | 16012817 | 1107600 | 502907 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | CCI | 2012 | Q3 | Q3 - 2012 | 2865258 | 573052 | 2292206 | 1478737 | 295747 | 1182990 | 1985000 | 397000 | 1588000 | 21603816 | 4320763 | 17283053 | 18275321 | 3655065 | 14620256 | 21713973 | 4342795 | 17371178 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 768000 | 153600 | 614400 | 637299 | 127460 | 509839 | 675000 | 135000 | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 199252 | 39850 | 159402 | 228000 | 45600 | 182400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 20805908 | 4161182 | 16644726 | 24845878 | 4969176 | 19876702 | 25906278 | 5181256 | 20725022 | 20805908 | 4161182 | 16644726 | 24845878 | 4969176 | 19876702 | 2550642 | 650694 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | CCI | 2012 | Q4 | Q4 - 2012 | 2865258 | 573052 | 2292206 | 1609309 | 321862 | 1287447 | 1700000 | 340000 | 1360000 | 21603816 | 4320763 | 17283053 | 21078909 | 4215781 | 16863128 | 21778909 | 4355782 | 17423127 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 768000 | 153600 | 614400 | 768000 | 153600 | 614400 | 768000 | 153600 | 614400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 239753 | 47951 | 191802 | 250000 | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 23911270 | 4782254 | 19129016 | 24740814 | 4948163 | 19792651 | 25906278 | 5181256 | 20725022 | 23911270 | 4782254 | 19129016 | 24740814 | 4948163 | 19792651 | 3104443 | 1665250 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | CCI | 2013 | Q1 | Q1 - 2013 | 2865258 | 573052 | 2292206 | 1609309 | 321862 | 1287447 | 2865258 | 573052 | 2292206 | 21603816 | 4320763 | 17283053 | 21203825 | 4240764 | 16963061 | 21603816 | 4320763 | 17283053 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 768000 | 153600 | 614400 | 768000 | 153600 | 614400 | 768000 | 153600 | 614400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 216000 | 43200 | 172800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 295151 | 59031 | 236120 | 359299 | 71860 | 287439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 24091584 | 4818317 | 19273267 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 24091584 | 4818317 | 19273267 | 25906278 | 5181256 | 20725022 | 3866020 | 2121913 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | CCI | 2013 | Q2 | Q2 - 2013 | 2865258 | 573052 | 2292206 | 1890007 | 378001 | 1512006 | 1890832 | 378826 | 1512006 | 21603816 | 4320763 | 17283053 | 22771786 | 4554357 | 18217429 | 23000000 | 4805553 | 18194447 | 93905 | 18781 | 75124 | 110544 | 22109 | 88435 | 110544 | 22109 | 88435 | 768000 | 153600 | 614400 | 706274 | 141255 | 565019 | 710595 | 145576 | 565019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 121394 | 24279 | 97115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 306273 | 61255 | 245018 | 335000 | 67000 | 268000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 26168365 | 5443343 | 20725022 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 26168365 | 5443343 | 20725022 | 4627598 | 2654843 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570074 | CCI | 2013 | Q3 | Q3 - 2013 | 2865258 | 573052 | 2292206 | 1894665 | 378933 | 1515732 | 1894665 | 378933 | 1515732 | 21603816 | 4320763 | 17283053 | 22718616 | 4543723 | 18174893 | 22718616 | 4543723 | 18174893 | 93905 | 18781 | 75124 | 110544 | 22109 | 88435 | 110544 | 22109 | 88435 | 768000 | 153600 | 614400 | 743485 | 148697 | 594788 | 743485 | 148697 | 594788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 43200 | 172800 | 121394 | 24279 | 97115 | 121394 | 24279 | 97115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 317574 | 63515 | 254059 | 317574 | 63515 | 254059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 25906278 | 5181256 | 20725022 | 5334176 | 3270148 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570075 | CCI | 2010 | Q4 | Q4 - 2010 | 86655145 | 28058852 | 58596293 | 8861813 | 2443684 | 6418129 | 29205000 | 6800000 | 22405000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 432566 | 448031 | 0 | 3215000 | 800000 | 2415000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 9993807 | 3591143 | 6418129 | 33119428 | 8299428 | 24820000 | 96793607 | 34253445 | 62540162 | 9993807 | 3591143 | 6418129 | 33119428 | 8299428 | 24820000 | 0 | 0 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | CCI | 2011 | Q1 | Q1 - 2011 | 86655145 | 28058852 | 58596293 | 20822547 | 3199906 | 17622641 | 40440235 | 7124239 | 33315996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 846154 | 846154 | 0 | 1246154 | 1246154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 22368129 | 4745488 | 17622641 | 42385817 | 9069821 | 33315996 | 96793607 | 34253445 | 62540162 | 22368129 | 4745488 | 17622641 | 42385817 | 9069821 | 33315996 | 0 | 0 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | CCI | 2011 | Q2 | Q2 - 2011 | 86655145 | 28058852 | 58596293 | 27562567 | 4789149 | 22773418 | 38862567 | 6989149 | 31873418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 1286652 | 1286652 | 0 | 1686652 | 1686652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 29548647 | 6775229 | 22773418 | 41248647 | 9375229 | 31873418 | 96793607 | 34253445 | 62540162 | 29548647 | 6775229 | 22773418 | 41248647 | 9375229 | 31873418 | 0 | 0 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | CCI | 2011 | Q3 | Q3 - 2011 | 86655145 | 28058852 | 58596293 | 39956741 | 6355610 | 33601131 | 47956741 | 9155610 | 38801131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 2455882 | 2455882 | 0 | 3555882 | 3555882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 43112051 | 9510920 | 33601131 | 52212051 | 13410920 | 38801131 | 96793607 | 34253445 | 62540162 | 43112051 | 9510920 | 33601131 | 52212051 | 13410920 | 38801131 | 0 | 0 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | CCI | 2011 | Q4 | Q4 - 2011 | 86655145 | 28058852 | 58596293 | 49837859 | 10397350 | 39440509 | 58840000 | 15740000 | 43100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 2900209 | 2900209 | 0 | 3380000 | 3380000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 53437496 | 13996987 | 39440509 | 62919428 | 19819428 | 43100000 | 96793607 | 34253445 | 62540162 | 53437496 | 13996987 | 39440509 | 62919428 | 19819428 | 43100000 | 0 | 0 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | CCI | 2012 | Q1 | Q1 - 2012 | 86655145 | 28058852 | 58596293 | 61212579 | 13668116 | 47544463 | 73760572 | 19800000 | 53960572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 3264186 | 3264186 | 0 | 3740000 | 3740000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 65176193 | 17631730 | 47544463 | 78200000 | 24239428 | 53960572 | 96793607 | 34253445 | 62540162 | 65176193 | 17631730 | 47544463 | 78200000 | 24239428 | 53960572 | 0 | 0 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | CCI | 2012 | Q2 | Q2 - 2012 | 86655145 | 28058852 | 58596293 | 69305524 | 18566707 | 50738818 | 83305525 | 23566707 | 59738818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 2815320 | 2815320 | 0 | 3165320 | 3165320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 72820272 | 22081455 | 50738818 | 87170273 | 27431455 | 59738818 | 96793607 | 34253445 | 62540162 | 72820272 | 22081455 | 50738818 | 87170273 | 27431455 | 59738818 | 0 | 0 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | CCI | 2012 | Q3 | Q3 - 2012 | 86655145 | 28058852 | 58596293 | 83877012 | 23989349 | 59887663 | 86400000 | 24500000 | 61900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 3170031 | 3170031 | 0 | 3520000 | 3520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 87746471 | 27858808 | 59887663 | 90619428 | 28719428 | 61900000 | 96793607 | 34253445 | 62540162 | 87746471 | 27858808 | 59887663 | 90619428 | 28719428 | 61900000 | 0 | 0 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | CCI | 2012 | Q4 | Q4 - 2012 | 86655145 | 28058852 | 58596293 | 85027327 | 25139664 | 59887664 | 89040000 | 26500000 | 62540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024497 | 1024497 | 0 | 699428 | 699428 | 0 | 699428 | 699428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9113965 | 5170096 | 3943869 | 3170031 | 3170031 | 0 | 3170031 | 3170031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 88896786 | 29009123 | 59887664 | 92909459 | 30369459 | 62540000 | 96793607 | 34253445 | 62540162 | 88896786 | 29009123 | 59887664 | 92909459 | 30369459 | 62540000 | 0 | 0 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | CCI | 2013 | Q1 | Q1 - 2013 | 89392955 | 31791803 | 57601152 | 84513328 | 23140804 | 61372524 | 89354322 | 27339305 | 62015017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504833 | 504833 | 0 | 504833 | 504833 | 0 | 504833 | 504833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6895819 | 1956809 | 4939010 | 6934452 | 6409307 | 525145 | 6934452 | 6409307 | 525145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 91952613 | 30054944 | 61897669 | 96793607 | 34253445 | 62540162 | 96793607 | 34253445 | 62540162 | 91952613 | 30054944 | 61897669 | 96793607 | 34253445 | 62540162 | 0 | 0 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | CCI | 2013 | Q2 | Q2 - 2013 | 89392955 | 31791803 | 57601152 | 89452174 | 27437157 | 62015017 | 89452174 | 27437157 | 62015017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504833 | 504833 | 0 | 504833 | 504833 | 0 | 504833 | 504833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6895819 | 1956809 | 4939010 | 7006202 | 6481057 | 525145 | 7006202 | 6481057 | 525145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 96963209 | 34423047 | 62540162 | 96963209 | 34423047 | 62540162 | 96793607 | 34253445 | 62540162 | 96963209 | 34423047 | 62540162 | 96963209 | 34423047 | 62540162 | 0 | 0 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570075 | CCI | 2013 | Q3 | Q3 - 2013 | 89392955 | 31791803 | 57601152 | 89452174 | 27437157 | 62015017 | 89452174 | 27437157 | 62015017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504833 | 504833 | 0 | 504833 | 504833 | 0 | 504833 | 504833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6895819 | 1956809 | 4939010 | 7006202 | 6481057 | 525145 | 7006202 | 6481057 | 525145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96793607 | 34253445 | 62540162 | 96963209 | 34423047 | 62540162 | 96963209 | 34423047 | 62540162 | 96793607 | 34253445 | 62540162 | 96963209 | 34423047 | 62540162 | 96963209 | 34423047 | 62540162 | 0 | 0 | University Corporation For Advanced Internet Development | TRUE
NT10BIX5570076 | CCI | 2010 | Q4 | Q4 - 2010 | 7054996 | 2116499 | 4938497 | 0 | 0 | 0 | 30000 | 9000 | 21000 | 30720083 | 9216025 | 21504058 | 0 | 0 | 0 | 0 | 0 | 0 | 1951241 | 585372 | 1365869 | 292306 | 87692 | 204614 | 375871 | 112761 | 263110 | 1151500 | 345450 | 806050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 0 | 0 | 0 | 480000 | 144000 | 336000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 8757 | 2627 | 6130 | 308757 | 92627 | 216130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 0 | 0 | 0 | 250000 | 75000 | 175000 | 47704860 | 14311458 | 33393402 | 301063 | 90319 | 210744 | 1444628 | 433388 | 1011240 | 47704860 | 14311458 | 33393402 | 301063 | 90319 | 210744 | 1444628 | 433388 | 1011240 | 4900 | 4900 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | CCI | 2011 | Q1 | Q1 - 2011 | 7522996 | 2584499 | 4938497 | 0 | 0 | 0 | 0 | 0 | 0 | 30720083 | 9216025 | 21504058 | 100000 | 100000 | 0 | 1990735 | 667220 | 1323515 | 1956141 | 590272 | 1365869 | 430547 | 134064 | 301383 | 647137 | 194141 | 452996 | 1151500 | 345450 | 806050 | 0 | 0 | 0 | 50000 | 15000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 87081 | 26124 | 60957 | 641527 | 192458 | 449069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 0 | 0 | 0 | 35000 | 10500 | 24500 | 48177760 | 14784358 | 33393402 | 617628 | 260188 | 362340 | 3364399 | 1079319 | 2285080 | 48177760 | 14784358 | 33393402 | 617628 | 260188 | 362340 | 3364399 | 1079319 | 2285080 | 0 | 0 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | CCI | 2011 | Q2 | Q2 - 2011 | 7522996 | 2584499 | 4938497 | 0 | 0 | 0 | 70550 | 21165 | 49385 | 30720083 | 9216025 | 21504058 | 681166 | 274350 | 406816 | 2088220 | 858932 | 1229287 | 1956141 | 590272 | 1365869 | 574538 | 176702 | 397836 | 643190 | 363662 | 279528 | 1151500 | 345450 | 806050 | 22301 | 6690 | 15611 | 213831 | 73070 | 140761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 27083 | 8125 | 18958 | 62082 | 29458 | 32625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 249389 | 74817 | 174572 | 850000 | 354756 | 495244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 0 | 0 | 0 | 0 | 0 | 0 | 48177760 | 14784358 | 33393402 | 1554477 | 540684 | 1013793 | 3927873 | 1701043 | 2226830 | 48177760 | 14784358 | 33393402 | 1554477 | 540684 | 1013793 | 3927873 | 1701043 | 2226830 | 0 | 0 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | CCI | 2011 | Q3 | Q3 - 2011 | 7522996 | 2584499 | 4938497 | 63714 | 19114 | 44600 | 113714 | 34114 | 79600 | 30720083 | 9216025 | 21504058 | 1303311 | 460993 | 842318 | 3856711 | 1227013 | 2629698 | 1956141 | 590272 | 1365869 | 704768 | 216591 | 488177 | 821537 | 251621 | 569916 | 1151500 | 345450 | 806050 | 45530 | 13659 | 31871 | 190276 | 57083 | 133193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 100451 | 30135 | 70316 | 361730 | 108519 | 253211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 642140 | 192642 | 449498 | 1033740 | 310122 | 723618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 0 | 0 | 0 | 190000 | 57000 | 133000 | 48177760 | 14784358 | 33393402 | 2859914 | 933134 | 1926780 | 6567708 | 2045472 | 4522236 | 48177760 | 14784358 | 33393402 | 2859914 | 933134 | 1926780 | 6567708 | 2045472 | 4522236 | 0 | 0 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | CCI | 2011 | Q4 | Q4 - 2011 | 7522996 | 2584499 | 4938497 | 122723 | 36817 | 85906 | 1122723 | 336817 | 785906 | 30720083 | 9216025 | 21504058 | 4025559 | 1277668 | 2747891 | 7116309 | 2204893 | 4911416 | 1956141 | 590272 | 1365869 | 846722 | 257177 | 589545 | 1024941 | 310642 | 714299 | 1151500 | 345450 | 806050 | 65425 | 19627 | 45797 | 91924 | 27577 | 64347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 189887 | 56966 | 132921 | 389887 | 116966 | 272921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 1160954 | 348286 | 812668 | 1658254 | 497476 | 1160778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 173775 | 52133 | 121643 | 189776 | 56933 | 132843 | 48177760 | 14784358 | 33393402 | 6585045 | 2048674 | 4536371 | 11593814 | 3551304 | 8042510 | 48177760 | 14784358 | 33393402 | 6585045 | 2048674 | 4536371 | 11593814 | 3551304 | 8042510 | 0 | 0 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | CCI | 2012 | Q1 | Q1 - 2012 | 7522996 | 2584499 | 4938497 | 125961 | 37788 | 88173 | 1949993 | 584998 | 1364995 | 30720083 | 9216025 | 21504058 | 6242527 | 1942758 | 4299769 | 12133859 | 3850158 | 8283701 | 1956141 | 590272 | 1365869 | 983419 | 301632 | 681787 | 1125387 | 344222 | 781165 | 1151500 | 345450 | 806050 | 84914 | 25474 | 59440 | 491311 | 147393 | 343918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 368693 | 110608 | 258085 | 747893 | 224368 | 523525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 1668283 | 500485 | 1167798 | 2043283 | 612985 | 1430298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 175531 | 52659 | 122872 | 350531 | 105159 | 245372 | 48177760 | 14784358 | 33393402 | 9649328 | 2971404 | 6677924 | 18842257 | 5869283 | 12972974 | 48177760 | 14784358 | 33393402 | 9649328 | 2971404 | 6677924 | 18842257 | 5869283 | 12972974 | 0 | 0 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | CCI | 2012 | Q2 | Q2 - 2012 | 7522996 | 2584499 | 4938497 | 125961 | 37788 | 88173 | 2525960 | 757788 | 1768172 | 30720083 | 9216025 | 21504058 | 9026026 | 2777808 | 6248218 | 13016027 | 4114808 | 8901219 | 1956141 | 590272 | 1365869 | 1162212 | 349607 | 812605 | 1291711 | 388457 | 903254 | 1151500 | 345450 | 806050 | 174380 | 52314 | 122066 | 476380 | 142914 | 333466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 519542 | 155863 | 363679 | 933542 | 280063 | 653479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 2224380 | 667314 | 1557066 | 2649380 | 794814 | 1854566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 365069 | 109521 | 255548 | 540069 | 162021 | 378048 | 48177760 | 14784358 | 33393402 | 13597570 | 4150215 | 9447355 | 21433069 | 6640865 | 14792204 | 48177760 | 14784358 | 33393402 | 13597570 | 4150215 | 9447355 | 21433069 | 6640865 | 14792204 | 0 | 0 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | CCI | 2012 | Q3 | Q3 - 2012 | 7522996 | 2584499 | 4938497 | 2269023 | 680707 | 1588316 | 4669023 | 1400707 | 3268316 | 30720083 | 9216025 | 21504058 | 11467994 | 3540398 | 8027596 | 16365194 | 5119558 | 11245636 | 1956141 | 590272 | 1365869 | 1098322 | 398137 | 914466 | 1455103 | 440887 | 1014216 | 1151500 | 345450 | 806050 | 542010 | 162603 | 379407 | 642010 | 192603 | 449407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 725801 | 217740 | 508061 | 725801 | 217740 | 508061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 2717854 | 815356 | 1902498 | 3142854 | 942856 | 2199998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 365069 | 109521 | 255548 | 485069 | 145521 | 339548 | 48177760 | 14784358 | 33393402 | 19186073 | 5924462 | 13575892 | 27485054 | 8459872 | 19025182 | 48177760 | 14784358 | 33393402 | 19186073 | 5924462 | 13575892 | 27485054 | 8459872 | 19025182 | 0 | 0 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | CCI | 2012 | Q4 | Q4 - 2012 | 7522996 | 2584499 | 4938497 | 5227803 | 1568341 | 3659462 | 10073580 | 3022074 | 7051506 | 30720083 | 9216025 | 21504058 | 14849542 | 4524862 | 10324680 | 20052542 | 6225763 | 13826779 | 1956141 | 590272 | 1365869 | 1487929 | 450734 | 1037195 | 1594677 | 482758 | 1111919 | 1151500 | 345450 | 806050 | 539336 | 161801 | 377535 | 808116 | 242435 | 565681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 803199 | 240960 | 562239 | 1304698 | 391409 | 913289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 3100827 | 930248 | 2170579 | 3310828 | 993248 | 2317580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 365069 | 109521 | 255548 | 827569 | 248271 | 579298 | 48177760 | 14784358 | 33393402 | 26373705 | 7986467 | 18387238 | 37972010 | 11605958 | 26366052 | 48177760 | 14784358 | 33393402 | 26373705 | 7986467 | 18387238 | 37972010 | 11605958 | 26366052 | 0 | 0 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | CCI | 2013 | Q1 | Q1 - 2013 | 7522996 | 2584499 | 4938497 | 6571719 | 1971516 | 4600203 | 8748669 | 2624601 | 6124068 | 30720083 | 9216025 | 21504058 | 17093844 | 5128153 | 11965691 | 22768450 | 6830535 | 15937915 | 1956141 | 590272 | 1365869 | 1582684 | 479161 | 1103523 | 1685563 | 510109 | 1175454 | 1151500 | 345450 | 806050 | 708816 | 212645 | 496171 | 999826 | 299948 | 699878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 1407588 | 422276 | 985312 | 2012615 | 603785 | 1408830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 3311201 | 993360 | 2317841 | 3471927 | 1041578 | 2430349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 489889 | 146967 | 342922 | 747569 | 224271 | 523298 | 48177760 | 14784358 | 33393402 | 31165741 | 9354078 | 21811663 | 40434619 | 12134827 | 28299792 | 48177760 | 14784358 | 33393402 | 31165741 | 9354078 | 21811663 | 40434619 | 12134827 | 28299792 | 0 | 0 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | CCI | 2013 | Q2 | Q2 - 2013 | 7522996 | 2584499 | 4938497 | 6989879 | 2096964 | 4892915 | 10616168 | 3184850 | 7431318 | 30720083 | 9216025 | 21504058 | 19475300 | 5842590 | 13632710 | 25765759 | 7729728 | 18036031 | 1956141 | 590272 | 1365869 | 1685484 | 510002 | 1175482 | 1813432 | 548386 | 1265046 | 1151500 | 345450 | 806050 | 747394 | 224218 | 523176 | 957394 | 287218 | 670176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 1768478 | 530543 | 1237935 | 2644487 | 793346 | 1851141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 3343026 | 1002908 | 2340118 | 3531926 | 1059578 | 2472348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 500160 | 150048 | 350112 | 780269 | 234081 | 546188 | 48177760 | 14784358 | 33393402 | 34509721 | 10357273 | 24152448 | 46109435 | 13837187 | 32272248 | 48177760 | 14784358 | 33393402 | 34509721 | 10357273 | 24152448 | 46109435 | 13837187 | 32272248 | 0 | 0 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | CCI | 2013 | Q3 | Q3 - 2013 | 7522996 | 2584499 | 4938497 | 8864995 | 2659499 | 6205496 | 10633021 | 3189906 | 7443115 | 30720083 | 9216025 | 21504058 | 22393531 | 6718060 | 15675471 | 26892602 | 8207711 | 18684891 | 1956141 | 590272 | 1365869 | 1817373 | 549568 | 1267805 | 1935706 | 584142 | 1351564 | 1151500 | 345450 | 806050 | 800533 | 240160 | 560373 | 983337 | 295001 | 688336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 2152945 | 645883 | 1507062 | 2870796 | 861238 | 2009558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 3455526 | 1036658 | 2418868 | 3671926 | 1101578 | 2570348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 532603 | 159781 | 372822 | 880269 | 264081 | 616188 | 48177760 | 14784358 | 33393402 | 40017506 | 12009609 | 28007897 | 47867657 | 14503657 | 33364000 | 48177760 | 14784358 | 33393402 | 40017506 | 12009609 | 28007897 | 47867657 | 14503657 | 33364000 | 0 | 0 | Vermont Telecommunications Authority | TRUE
NT10BIX5570076 | CCI | 2013 | Q4 | Q4 - 2013 | 7522996 | 2584499 | 4938497 | 9945910 | 2983773 | 6962137 | 10935911 | 3280773 | 7655138 | 30720083 | 9216025 | 21504058 | 24844805 | 7453442 | 17391363 | 25219705 | 7635842 | 17583863 | 1956141 | 590272 | 1365869 | 2182453 | 659156 | 1523297 | 2224852 | 671690 | 1553162 | 1151500 | 345450 | 806050 | 802917 | 240875 | 562042 | 877917 | 263375 | 614542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017040 | 905112 | 2111928 | 2437946 | 731383 | 1706563 | 2692946 | 807883 | 1885063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000 | 1020000 | 2380000 | 3496026 | 1048808 | 2447218 | 3521026 | 1056308 | 2464718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410000 | 123000 | 287000 | 1023509 | 307053 | 716456 | 1053509 | 316053 | 737456 | 48177760 | 14784358 | 33393402 | 44733566 | 13424490 | 31309076 | 46525866 | 14031924 | 32493942 | 48177760 | 14784358 | 33393402 | 44733566 | 13424490 | 31309076 | 46525866 | 14031924 | 32493942 | 0 | 0 | Vermont Telecommunications Authority | TRUE
NT10BIX5570077 | CCI | 2010 | Q4 | Q4 - 2010 | 562825 | 267495 | 295330 | 0 | 0 | 0 | 0 | 0 | 0 | 5043298 | 275005 | 4768293 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 3039 | 3039 | 0 | 5039 | 5039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 216835 | 216835 | 0 | 266459 | 266459 | 0 | 9700 | 9700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304800 | 304800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 219874 | 219874 | 0 | 271498 | 271498 | 0 | 6346571 | 1282948 | 5063623 | 219874 | 219874 | 0 | 271498 | 271498 | 0 | 0 | 0 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | CCI | 2011 | Q1 | Q1 - 2011 | 562825 | 267494 | 295330 | 0 | 0 | 0 | 56282 | 31282 | 25000 | 5043298 | 275006 | 4768293 | 0 | 0 | 0 | 1008660 | 0 | 1008660 | 20000 | 20000 | 0 | 5685 | 5685 | 0 | 8700 | 8700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 316686 | 316686 | 0 | 341486 | 341486 | 0 | 9700 | 9700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304800 | 304800 | 0 | 3638 | 3638 | 0 | 54902 | 54902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 326009 | 326009 | 0 | 1470030 | 436370 | 1033660 | 6346571 | 1282948 | 5063623 | 326009 | 326009 | 0 | 1470030 | 436370 | 1033660 | 0 | 0 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | CCI | 2011 | Q2 | Q2 - 2011 | 562825 | 267494 | 295330 | 0 | 0 | 0 | 56282 | 56282 | 0 | 5043298 | 275006 | 4768293 | 239993 | 0 | 239993 | 3782473 | 0 | 3782473 | 20000 | 20000 | 0 | 7916 | 7916 | 0 | 10016 | 10016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 373997 | 373997 | 0 | 405948 | 405948 | 0 | 9700 | 9700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304800 | 304800 | 0 | 33561 | 33561 | 0 | 93561 | 93561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 655467 | 415474 | 239993 | 4348280 | 565807 | 3782473 | 6346571 | 1282948 | 5063623 | 655467 | 415474 | 239993 | 4348280 | 565807 | 3782473 | 0 | 0 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | CCI | 2011 | Q3 | Q3 - 2011 | 562825 | 267494 | 295330 | 47383 | 47383 | 0 | 112565 | 47383 | 65182 | 5043298 | 275006 | 4768293 | 3441477 | 68000 | 3373477 | 4538832 | 136000 | 4402832 | 20000 | 20000 | 0 | 5262 | 5262 | 0 | 7762 | 7762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 426693 | 426693 | 0 | 432693 | 432693 | 0 | 9700 | 9700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304800 | 304800 | 0 | 181480 | 181480 | 0 | 201480 | 201480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 4102295 | 728818 | 3373477 | 5293332 | 825318 | 4468014 | 6346571 | 1282948 | 5063623 | 4102295 | 728818 | 3373477 | 5293332 | 825318 | 4468014 | 0 | 0 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | CCI | 2011 | Q4 | Q4 - 2011 | 562825 | 267494 | 295330 | 374561 | 288905 | 85656 | 474561 | 94912 | 379649 | 5043298 | 275006 | 4768293 | 3920792 | 162680 | 3758112 | 4237000 | 200000 | 4037000 | 20000 | 20000 | 0 | 6375 | 6375 | 0 | 10375 | 10375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 446747 | 446747 | 0 | 479948 | 479948 | 0 | 9700 | 9700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304800 | 304800 | 0 | 259898 | 259898 | 0 | 269898 | 269898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 5008373 | 1164605 | 3843768 | 5471782 | 1055133 | 4416649 | 6346571 | 1282948 | 5063623 | 5008373 | 1164605 | 3843768 | 5471782 | 1055133 | 4416649 | 0 | 0 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | CCI | 2012 | Q1 | Q1 - 2012 | 562825 | 267494 | 295330 | 363792 | 288950 | 85655 | 682742 | 308950 | 373792 | 5043298 | 275006 | 4768293 | 3939078 | 170152 | 3758113 | 4769078 | 240000 | 4529078 | 20000 | 20000 | 0 | 6753 | 6753 | 0 | 14253 | 14253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 444875 | 444874 | 0 | 474874 | 474874 | 0 | 9700 | 9700 | 0 | 356 | 356 | 0 | 3356 | 3356 | 0 | 304800 | 304800 | 0 | 290089 | 290089 | 0 | 300089 | 300089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 5044943 | 1201174 | 3843768 | 6244392 | 1341522 | 4902870 | 6346571 | 1282948 | 5063623 | 5044943 | 1201174 | 3843768 | 6244392 | 1341522 | 4902870 | 0 | 750 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | CCI | 2012 | Q2 | Q2 - 2012 | 562825 | 267494 | 295330 | 383803 | 287333 | 96470 | 582664 | 267494 | 295330 | 5043298 | 275006 | 4768293 | 4029673 | 185152 | 3844521 | 5043298 | 275006 | 4768293 | 20000 | 20000 | 0 | 13267 | 13267 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 486072 | 486072 | 0 | 405948 | 405948 | 0 | 9700 | 9700 | 0 | 4979 | 4979 | 0 | 9700 | 9700 | 0 | 304800 | 304800 | 0 | 324778 | 324778 | 0 | 304800 | 304800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 5242572 | 1301581 | 3940991 | 6366410 | 1282948 | 5063623 | 6346571 | 1282948 | 5063623 | 5242572 | 1301581 | 3940991 | 6366410 | 1282948 | 5063623 | 0 | 0 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | CCI | 2012 | Q3 | Q3 - 2012 | 562825 | 267494 | 295330 | 551965 | 267494 | 259548 | 562825 | 267494 | 295330 | 5043298 | 275006 | 4768293 | 4417065 | 185152 | 4231913 | 5043298 | 275006 | 4768293 | 20000 | 20000 | 0 | 17945 | 17945 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 40594 | 405948 | 0 | 405948 | 405948 | 0 | 9700 | 9700 | 0 | 6656 | 6656 | 0 | 9700 | 9700 | 0 | 304800 | 304800 | 0 | 304800 | 304800 | 0 | 304800 | 304800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 5339025 | 1187995 | 4491461 | 6346571 | 1282948 | 5063623 | 6346571 | 1282948 | 5063623 | 5339025 | 1187995 | 4491461 | 6346571 | 1282948 | 5063623 | 0 | 3248 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570077 | CCI | 2012 | Q4 | Q4 - 2012 | 578901 | 267494 | 311407 | 603823 | 292417 | 311407 | 603823 | 292417 | 311407 | 5027222 | 275006 | 4752216 | 5046244 | 294028 | 4752216 | 5046244 | 294028 | 4752216 | 20000 | 20000 | 0 | 20274 | 20274 | 0 | 20274 | 20274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405948 | 405948 | 0 | 500456 | 500456 | 0 | 500456 | 500456 | 0 | 9700 | 9700 | 0 | 9953 | 9953 | 0 | 9953 | 9953 | 0 | 304800 | 304800 | 0 | 372443 | 372443 | 0 | 372443 | 372443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6346571 | 1282948 | 5063623 | 6553193 | 1489571 | 5063623 | 6553193 | 1489571 | 5063623 | 6346571 | 1282948 | 5063623 | 6553193 | 1489571 | 5063623 | 6553193 | 1489571 | 5063623 | 0 | 22039 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | CCI | 2010 | Q4 | Q4 - 2010 | 881968 | 787068 | 94900 | 0 | 0 | 0 | 0 | 0 | 0 | 5133770 | 40491 | 5093279 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 2789 | 2789 | 0 | 4800 | 4800 | 0 | 393000 | 0 | 393000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 243058 | 243058 | 0 | 385797 | 385797 | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289400 | 289400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7234820 | 1626641 | 5608179 | 245847 | 245847 | 0 | 390597 | 390597 | 0 | 7234820 | 1626641 | 5608179 | 245847 | 245847 | 0 | 390597 | 390597 | 0 | 0 | 0 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | CCI | 2011 | Q1 | Q1 - 2011 | 881968 | 787068 | 94900 | 0 | 0 | 0 | 0 | 0 | 0 | 5133770 | 40491 | 5093279 | 0 | 0 | 0 | 1026754 | 0 | 1026754 | 20000 | 20000 | 0 | 5101 | 5101 | 0 | 7101 | 7101 | 0 | 393000 | 0 | 393000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 355928 | 355928 | 0 | 410628 | 410628 | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289400 | 289400 | 0 | 787 | 787 | 0 | 49819 | 49819 | 0 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7234820 | 1626441 | 5608179 | 361816 | 361816 | 0 | 1494302 | 467548 | 1026754 | 7234820 | 1626441 | 5608179 | 361816 | 361816 | 0 | 1494302 | 467548 | 1026754 | 0 | 0 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | CCI | 2011 | Q2 | Q2 - 2011 | 881968 | 787068 | 94900 | 0 | 0 | 0 | 0 | 0 | 0 | 5133770 | 40491 | 5093279 | 1176376 | 0 | 1176376 | 3080262 | 0 | 3080262 | 20000 | 20000 | 0 | 7343 | 7343 | 0 | 14443 | 14443 | 0 | 393000 | 0 | 393000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 406699 | 406699 | 0 | 766882 | 766882 | 0 | 60000 | 60000 | 0 | 12015 | 12015 | 0 | 45000 | 45000 | 0 | 289400 | 289400 | 0 | 40124 | 40124 | 0 | 80248 | 80248 | 0 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7234820 | 1626641 | 5608179 | 1642557 | 466181 | 1176376 | 3986835 | 906573 | 3080262 | 7234820 | 1626641 | 5608179 | 1642557 | 466181 | 1176376 | 3986835 | 906573 | 3080262 | 0 | 0 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | CCI | 2011 | Q3 | Q3 - 2011 | 881968 | 787068 | 94900 | 2431 | 2431 | 0 | 86000 | 86000 | 0 | 5133770 | 40491 | 5093279 | 2033944 | 0 | 2033944 | 2973944 | 0 | 2973944 | 20000 | 20000 | 0 | 4462 | 4462 | 0 | 6662 | 6662 | 0 | 393000 | 0 | 393000 | 155126 | 0 | 155126 | 185126 | 0 | 185126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 438009 | 438009 | 0 | 438009 | 438009 | 0 | 60000 | 60000 | 0 | 12015 | 12015 | 0 | 30000 | 30000 | 0 | 289400 | 289400 | 0 | 94621 | 94621 | 0 | 124621 | 124621 | 0 | 27000 | 0 | 27000 | 0 | 0 | 0 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7234820 | 1626641 | 5608179 | 2740608 | 551538 | 2189070 | 3871362 | 685292 | 3186070 | 7234820 | 1626641 | 5608179 | 2740608 | 551538 | 2189070 | 3871362 | 685292 | 3186070 | 0 | 0 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | CCI | 2011 | Q4 | Q4 - 2011 | 881968 | 787068 | 94900 | 107803 | 56455 | 51346 | 207803 | 100000 | 0 | 5133770 | 40491 | 5093279 | 2820527 | 0 | 2820527 | 2964527 | 0 | 144000 | 20000 | 20000 | 0 | 5436 | 5436 | 0 | 7500 | 7500 | 0 | 393000 | 0 | 393000 | 208791 | 0 | 208791 | 258791 | 0 | 258791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 438565 | 438565 | 0 | 448115 | 448115 | 0 | 60000 | 60000 | 0 | 15350 | 15350 | 0 | 30000 | 30000 | 0 | 289400 | 289400 | 0 | 172802 | 172802 | 0 | 180802 | 180802 | 0 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 7234820 | 1626641 | 5608179 | 3796274 | 688608 | 3107664 | 4136738 | 778617 | 429791 | 7234820 | 1626641 | 5608179 | 3796274 | 688608 | 3107664 | 4136738 | 778617 | 429791 | 0 | 0 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | CCI | 2012 | Q1 | Q1 - 2012 | 881968 | 787068 | 94900 | 62066 | 62066 | 0 | 262066 | 262066 | 0 | 5133770 | 40491 | 5093279 | 2820527 | 0 | 2820527 | 3120527 | 0 | 3120527 | 20000 | 20000 | 0 | 6616 | 6616 | 0 | 8616 | 8616 | 0 | 393000 | 0 | 393000 | 260138 | 0 | 260138 | 300138 | 0 | 300138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 461702 | 461702 | 0 | 471702 | 471702 | 0 | 60000 | 60000 | 0 | 15350 | 15350 | 0 | 30350 | 30350 | 0 | 289400 | 289400 | 0 | 189498 | 189498 | 0 | 209498 | 209498 | 0 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 661 | 661 | 0 | 12200 | 12200 | 0 | 7234820 | 1626641 | 5608179 | 3843558 | 735893 | 3107665 | 4442097 | 994432 | 3447665 | 7234820 | 1626641 | 5608179 | 3843558 | 735893 | 3107665 | 4442097 | 994432 | 3447665 | 0 | 750 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | CCI | 2012 | Q2 | Q2 - 2012 | 881968 | 787068 | 94900 | 230483 | 183241 | 47243 | 497241 | 404798 | 45200 | 5133770 | 40491 | 5093279 | 3057994 | 0 | 3057994 | 4857994 | 0 | 4857994 | 20000 | 20000 | 0 | 12693 | 12694 | 0 | 18793 | 18793 | 0 | 393000 | 0 | 393000 | 208156 | 0 | 208156 | 308156 | 0 | 308156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 528657 | 528658 | 0 | 536157 | 536157 | 0 | 60000 | 60000 | 0 | 15350 | 15350 | 0 | 48350 | 48350 | 0 | 289400 | 289400 | 0 | 228090 | 228090 | 0 | 274089 | 274089 | 0 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 1292 | 1292 | 0 | 6000 | 6000 | 0 | 7234820 | 1626641 | 5608179 | 4309715 | 969325 | 3340393 | 6573780 | 1288187 | 5238350 | 7234820 | 1626641 | 5608179 | 4309715 | 969325 | 3340393 | 6573780 | 1288187 | 5238350 | 0 | 0 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | CCI | 2012 | Q3 | Q3 - 2012 | 881968 | 787068 | 94900 | 280159 | 230004 | 50155 | 881968 | 787068 | 94900 | 5133770 | 40491 | 5093279 | 3664914 | 0 | 3664914 | 5133770 | 40491 | 5093279 | 20000 | 20000 | 0 | 16357 | 16357 | 0 | 20000 | 20000 | 0 | 393000 | 0 | 393000 | 241981 | 0 | 241981 | 393000 | 0 | 393000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 538128 | 538128 | 0 | 417482 | 417482 | 0 | 60000 | 60000 | 0 | 15350 | 15350 | 0 | 60000 | 60000 | 0 | 289400 | 289400 | 0 | 271525 | 271525 | 0 | 289400 | 289400 | 0 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 10521 | 10522 | 0 | 12200 | 12200 | 0 | 7234820 | 1626641 | 5608179 | 5065935 | 1081886 | 3984050 | 7234820 | 1626641 | 5608179 | 7234820 | 1626641 | 5608179 | 5065935 | 1081886 | 3984050 | 7234820 | 1626641 | 5608179 | 0 | 0 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | CCI | 2012 | Q4 | Q4 - 2012 | 881968 | 787068 | 94900 | 777609 | 727454 | 50155 | 882908 | 788008 | 94900 | 5133770 | 40491 | 5093279 | 4931044 | 40454 | 4890589 | 5133770 | 40491 | 5093279 | 20000 | 20000 | 0 | 20179 | 20179 | 0 | 20179 | 20179 | 0 | 393000 | 0 | 393000 | 241981 | 0 | 241981 | 393000 | 0 | 393000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 572634 | 572634 | 0 | 572634 | 572634 | 0 | 60000 | 60000 | 0 | 15350 | 15350 | 0 | 60000 | 60000 | 0 | 289400 | 289400 | 0 | 342583 | 342583 | 0 | 342583 | 342583 | 0 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 19879 | 19879 | 0 | 19879 | 19879 | 0 | 7234820 | 1626641 | 5608179 | 6948259 | 1738533 | 5209725 | 7451953 | 1843774 | 5608179 | 7234820 | 1626641 | 5608179 | 6948259 | 1738533 | 5209725 | 7451953 | 1843774 | 5608179 | 0 | 263 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570078 | CCI | 2013 | Q1 | Q1 - 2013 | 905679 | 787068 | 118611 | 845901 | 727290 | 118611 | 845901 | 727290 | 118611 | 5145213 | 40491 | 5104722 | 5142252 | 37530 | 5104722 | 5142252 | 37530 | 5104722 | 20000 | 20000 | 0 | 20294 | 20294 | 0 | 20294 | 20294 | 0 | 357846 | 0 | 357846 | 357846 | 0 | 357846 | 357846 | 0 | 357846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417482 | 417482 | 0 | 566792 | 566792 | 0 | 566792 | 566792 | 0 | 60000 | 60000 | 0 | 15649 | 15649 | 0 | 15649 | 15649 | 0 | 289400 | 289400 | 0 | 329104 | 329104 | 0 | 329104 | 329104 | 0 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 27000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12200 | 12200 | 0 | 18633 | 18633 | 0 | 18633 | 18633 | 0 | 7234820 | 1626641 | 5608179 | 7323471 | 1715292 | 5608179 | 7323471 | 1715292 | 5608179 | 7234820 | 1626641 | 5608179 | 7323471 | 1715292 | 5608179 | 7323471 | 1715292 | 5608179 | 0 | 66678 | Silver Star Telephone Company, INC. | TRUE
NT10BIX5570079 | CCI | 2010 | Q4 | Q4 - 2010 | 2320000 | 2320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6827555 | 0 | 6827555 | 0 | 0 | 0 | 624867 | 0 | 624867 | 612580 | 612580 | 0 | 91000 | 91000 | 0 | 160000 | 160000 | 0 | 205611 | 100000 | 105611 | 0 | 0 | 0 | 82242 | 82242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 312069 | 871015 | 78420 | 23526 | 54894 | 181741 | 72413 | 109328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 169420 | 114526 | 54894 | 1048850 | 314655 | 734195 | 11148830 | 3344649 | 7804181 | 169420 | 114526 | 54894 | 1048850 | 314655 | 734195 | 0 | 0 | Clackamas, County of | TRUE
NT10BIX5570079 | CCI | 2011 | Q1 | Q1 - 2011 | 2320000 | 2320000 | 0 | 4490 | 4490 | 0 | 184490 | 184490 | 0 | 6827555 | 0 | 6827555 | 0 | 0 | 0 | 530000 | 0 | 530000 | 612580 | 612580 | 0 | 61546 | 61546 | 0 | 94546 | 94546 | 0 | 205611 | 100000 | 105611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 312069 | 871015 | 314801 | 48215 | 266586 | 465647 | 103369 | 362278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 380837 | 114251 | 266586 | 1274683 | 382405 | 892278 | 11148830 | 3344649 | 7804181 | 380837 | 114251 | 266586 | 1274683 | 382405 | 892278 | 0 | 0 | Clackamas, County of | TRUE
NT10BIX5570079 | CCI | 2011 | Q2 | Q2 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 790499 | 0 | 790499 | 1947642 | 0 | 1947642 | 416498 | 309498 | 107000 | 90834 | 90834 | 0 | 120834 | 120834 | 0 | 2516082 | 2516082 | 0 | 444554 | 444554 | 0 | 993200 | 993200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 458540 | 0 | 458540 | 651397 | 0 | 651397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 1784427 | 535388 | 1249039 | 3713073 | 1114034 | 2599039 | 11148830 | 3344649 | 7804181 | 1784427 | 535388 | 1249039 | 3713073 | 1114034 | 2599039 | 0 | 0 | Clackamas, County of | TRUE
NT10BIX5570079 | CCI | 2011 | Q3 | Q3 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 1920575 | 0 | 1920575 | 3220575 | 0 | 3220575 | 416498 | 309498 | 107000 | 119139 | 119139 | 0 | 148139 | 148138 | 0 | 2516082 | 2516082 | 0 | 694424 | 694424 | 0 | 894424 | 894424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 696848 | 0 | 696848 | 896848 | 0 | 896848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 3430986 | 813563 | 2617423 | 5159986 | 1042562 | 4117423 | 11148830 | 3344649 | 7804181 | 3430986 | 813563 | 2617423 | 5159986 | 1042562 | 4117423 | 0 | 0 | Clackamas, County of | TRUE
NT10BIX5570079 | CCI | 2011 | Q4 | Q4 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 2902949 | 0 | 2902949 | 4251109 | 0 | 4251109 | 416498 | 309498 | 107000 | 155244 | 155244 | 0 | 191350 | 191350 | 0 | 2516082 | 2516082 | 0 | 817299 | 817299 | 0 | 2043000 | 2043000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 778220 | 0 | 778220 | 962060 | 0 | 962060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 4653712 | 972543 | 3681169 | 7447519 | 2234350 | 5213169 | 11148830 | 3344649 | 7804181 | 4653712 | 972543 | 3681169 | 7447519 | 2234350 | 5213169 | 0 | 0 | Clackamas, County of | TRUE
NT10BIX5570079 | CCI | 2012 | Q1 | Q1 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 4163243 | 0 | 4163243 | 5263243 | 0 | 5263243 | 416498 | 309498 | 107000 | 202937 | 202937 | 0 | 238937 | 238937 | 0 | 2516082 | 2516082 | 0 | 2410835 | 2410835 | 0 | 2410835 | 2410835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 829223 | 0 | 829223 | 894223 | 0 | 894223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 7606238 | 2613772 | 4992466 | 8807238 | 2649772 | 6157466 | 11148830 | 3344649 | 7804181 | 7606238 | 2613772 | 4992466 | 8807238 | 2649772 | 6157466 | 0 | 0 | Clackamas, County of | TRUE
NT10BIX5570079 | CCI | 2012 | Q2 | Q2 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 5097328 | 0 | 5097328 | 6463243 | 0 | 6463243 | 416498 | 309498 | 107000 | 298412 | 250989 | 47423 | 328412 | 265989 | 62423 | 2516082 | 2516082 | 0 | 2568309 | 2568309 | 0 | 2568309 | 2568309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 884137 | 0 | 884137 | 964223 | 0 | 964223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 8848186 | 2819298 | 6028888 | 10324187 | 2834298 | 7489889 | 11148830 | 3344649 | 7804181 | 8848186 | 2819298 | 6028888 | 10324187 | 2834298 | 7489889 | 0 | 3750 | Clackamas, County of | TRUE
NT10BIX5570079 | CCI | 2012 | Q3 | Q3 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 5889849 | 80911 | 5808938 | 6739849 | 114411 | 6625438 | 416498 | 309498 | 107000 | 347309 | 286486 | 60823 | 399309 | 338486 | 60823 | 2516082 | 2516082 | 0 | 2568309 | 2568309 | 0 | 2568309 | 2568309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 898658 | 0 | 898658 | 918674 | 0 | 918674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 9704125 | 2935706 | 6768419 | 10626141 | 3021206 | 7604935 | 11148830 | 3344649 | 7804181 | 9704125 | 2935706 | 6768419 | 10626141 | 3021206 | 7604935 | 0 | 3750 | Clackamas, County of | TRUE
NT10BIX5570079 | CCI | 2012 | Q4 | Q4 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 6497985 | 150000 | 6347985 | 6847985 | 262000 | 6585985 | 416498 | 309498 | 107000 | 347309 | 286486 | 60823 | 361461 | 300638 | 60823 | 2516082 | 2516082 | 0 | 2659638 | 2659638 | 0 | 2659638 | 2659638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 914909 | 0 | 914909 | 926974 | 0 | 926974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 10419841 | 3096124 | 7323717 | 10796058 | 3222276 | 7573782 | 11148830 | 3344649 | 7804181 | 10419841 | 3096124 | 7323717 | 10796058 | 3222276 | 7573782 | 0 | 30000 | Clackamas, County of | TRUE
NT10BIX5570079 | CCI | 2013 | Q1 | Q1 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7033166 | 519069 | 6514097 | 6703231 | 189134 | 6514097 | 7033166 | 519069 | 6514097 | 416498 | 309498 | 107000 | 366091 | 305267 | 60823 | 416498 | 309498 | 107000 | 2516082 | 2516082 | 0 | 2659638 | 2659638 | 0 | 2659638 | 2659638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183084 | 0 | 1183084 | 925409 | 0 | 925409 | 1183084 | 0 | 1183084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11148830 | 3344649 | 7804181 | 10654369 | 3154039 | 7500329 | 11292386 | 3488205 | 7804181 | 11148830 | 3344649 | 7804181 | 10654369 | 3154039 | 7500329 | 11292386 | 3488205 | 7804181 | 0 | 82250 | Clackamas, County of | TRUE
NT10BIX5570079 | CCI | 2013 | Q2 | Q2 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7238804 | 519069 | 6719735 | 6870000 | 355903 | 6514097 | 7238804 | 519069 | 6719735 | 439093 | 309498 | 129595 | 370321 | 309498 | 60823 | 439093 | 309498 | 129595 | 2659638 | 2659638 | 0 | 2659638 | 2659638 | 0 | 2659638 | 2659638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 954851 | 0 | 954851 | 952085 | 0 | 952085 | 954851 | 0 | 954851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11292386 | 3488205 | 7804181 | 10852044 | 3325039 | 7527005 | 11292386 | 3488205 | 7804181 | 11292386 | 3488205 | 7804181 | 10852044 | 3325039 | 7527005 | 11292386 | 3488205 | 7804181 | 96750 | 123750 | Clackamas, County of | TRUE
NT10BIX5570079 | CCI | 2013 | Q3 | Q3 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7238804 | 519069 | 6719735 | 7244288 | 521787 | 6722501 | 7244288 | 521787 | 6722501 | 439093 | 309498 | 129595 | 636295 | 506700 | 129595 | 636295 | 506700 | 129595 | 2659638 | 2659638 | 0 | 2659638 | 2659638 | 0 | 2659638 | 2659638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 954851 | 0 | 954851 | 952085 | 0 | 952085 | 952085 | 0 | 952085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11292386 | 3488205 | 7804181 | 11492306 | 3688125 | 7804181 | 11492306 | 3688125 | 7804181 | 11292386 | 3488205 | 7804181 | 11492306 | 3688125 | 7804181 | 11492306 | 3688125 | 7804181 | 0 | 199920 | Clackamas, County of | TRUE
NT10BIX5570080 | CCI | 2010 | Q4 | Q4 - 2010 | 2368083 | 189281 | 2178802 | 0 | 0 | 0 | 0 | 0 | 0 | 267975 | 199575 | 68400 | 0 | 0 | 0 | 0 | 0 | 0 | 405000 | 405000 | 0 | 0 | 0 | 0 | 122000 | 122000 | 0 | 2303662 | 88600 | 2215062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 0 | 0 | 0 | 94000 | 94000 | 0 | 30417 | 0 | 30417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994918 | 427592 | 567326 | 0 | 0 | 0 | 0 | 0 | 0 | 6501995 | 1317548 | 5184447 | 0 | 0 | 0 | 216000 | 216000 | 0 | 6501995 | 1317548 | 5184447 | 0 | 0 | 0 | 216000 | 216000 | 0 | 0 | 0 | ONWAV INC. | TRUE
NT10BIX5570080 | CCI | 2011 | Q1 | Q1 - 2011 | 2368083 | 189281 | 2178802 | 0 | 0 | 0 | 50000 | 0 | 50000 | 267975 | 199575 | 68400 | 0 | 0 | 0 | 0 | 0 | 0 | 405000 | 405000 | 0 | 218014 | 218014 | 0 | 327031 | 327031 | 0 | 2303662 | 88600 | 2215062 | 0 | 0 | 0 | 157600 | 0 | 157600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 10645 | 0 | 10645 | 74237 | 0 | 74237 | 30417 | 0 | 30417 | 0 | 0 | 0 | 30417 | 0 | 30417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994918 | 427592 | 567326 | 0 | 0 | 0 | 70250 | 0 | 70250 | 6501995 | 1317548 | 5184447 | 228659 | 218014 | 10645 | 717035 | 334531 | 382504 | 6501995 | 1317548 | 5184447 | 228659 | 218014 | 10645 | 717035 | 334531 | 382504 | 0 | 0 | ONWAV INC. | TRUE
NT10BIX5570080 | CCI | 2011 | Q2 | Q2 - 2011 | 2368083 | 189281 | 2178802 | 0 | 0 | 0 | 0 | 0 | 0 | 267975 | 199575 | 68400 | 0 | 0 | 0 | 37500 | 37500 | 0 | 405000 | 405000 | 0 | 308967 | 308967 | 0 | 496830 | 496830 | 0 | 2303662 | 88600 | 2215062 | 2500 | 0 | 2500 | 94786 | 0 | 94786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 17575 | 0 | 17575 | 82496 | 0 | 82496 | 30417 | 0 | 30417 | 0 | 0 | 0 | 24334 | 0 | 24334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994918 | 427592 | 567326 | 0 | 0 | 0 | 63112 | 0 | 63112 | 6501995 | 1317548 | 5184447 | 329042 | 308967 | 20075 | 806558 | 541830 | 264728 | 6501995 | 1317548 | 5184447 | 329042 | 308967 | 20075 | 806558 | 541830 | 264728 | 0 | 0 | ONWAV INC. | TRUE
NT10BIX5570080 | CCI | 2011 | Q3 | Q3 - 2011 | 3406069 | 1317548 | 2088521 | 0 | 0 | 0 | 2352018 | 1419203 | 932815 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 1145000 | 0 | 1145000 | 340570 | 0 | 340570 | 468070 | 0 | 468070 | 1054911 | 0 | 1054911 | 2500 | 0 | 2500 | 487500 | 0 | 487500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 17575 | 0 | 17575 | 36838 | 0 | 36838 | 30417 | 0 | 30417 | 0 | 0 | 0 | 30417 | 0 | 30417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583658 | 0 | 583658 | 0 | 0 | 0 | 82112 | 0 | 82112 | 6501995 | 1317548 | 5184447 | 360645 | 0 | 360645 | 3456955 | 1419203 | 2037752 | 6501995 | 1317548 | 5184447 | 360645 | 0 | 360645 | 3456955 | 1419203 | 2037752 | 0 | 0 | ONWAV INC. | TRUE
NT10BIX5570080 | CCI | 2011 | Q4 | Q4 - 2011 | 3406069 | 1317548 | 2088521 | 2079605 | 1317548 | 762057 | 2194972 | 1317548 | 877424 | 150000 | 0 | 150000 | 0 | 0 | 0 | 37500 | 0 | 37500 | 1145000 | 0 | 1145000 | 435796 | 0 | 435796 | 563296 | 0 | 563296 | 1054911 | 0 | 1054911 | 103751 | 0 | 103751 | 567411 | 0 | 567411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 17575 | 0 | 17575 | 36838 | 0 | 36838 | 30417 | 0 | 30417 | 0 | 0 | 0 | 30417 | 0 | 30417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583658 | 0 | 583658 | 0 | 0 | 0 | 86522 | 0 | 86522 | 6501995 | 1317548 | 5184447 | 2636727 | 1317548 | 1319179 | 3524456 | 1317548 | 2206908 | 6501995 | 1317548 | 5184447 | 2636727 | 1317548 | 1319179 | 3524456 | 1317548 | 2206908 | 0 | 0 | ONWAV INC. | TRUE
NT10BIX5570080 | CCI | 2012 | Q1 | Q1 - 2012 | 3406069 | 1317548 | 2088521 | 2104746 | 1317548 | 787198 | 2671476 | 1317548 | 1353928 | 150000 | 0 | 150000 | 0 | 0 | 0 | 12500 | 0 | 12500 | 1145000 | 0 | 1145000 | 460796 | 0 | 460796 | 525796 | 0 | 525796 | 1054911 | 0 | 1054911 | 103751 | 0 | 103751 | 411920 | 0 | 411920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 18558 | 0 | 18558 | 89150 | 0 | 89150 | 30417 | 0 | 30417 | 17575 | 0 | 17575 | 30417 | 0 | 30417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583658 | 0 | 583658 | 0 | 0 | 0 | 256026 | 0 | 256026 | 6501995 | 1317548 | 5184447 | 2705426 | 1317548 | 1387878 | 4004785 | 1317548 | 2687237 | 6501995 | 1317548 | 5184447 | 2705426 | 1317548 | 1387878 | 4004785 | 1317548 | 2687237 | 0 | 0 | ONWAV INC. | TRUE
NT10BIX5570080 | CCI | 2012 | Q2 | Q2 - 2012 | 3406069 | 1317548 | 2088521 | 2567029 | 1317548 | 1249481 | 3129769 | 1317548 | 1812221 | 150000 | 0 | 150000 | 0 | 0 | 0 | 50000 | 0 | 50000 | 1145000 | 0 | 1145000 | 576496 | 0 | 576496 | 635896 | 0 | 635896 | 1054911 | 0 | 1054911 | 382169 | 0 | 382169 | 941559 | 0 | 941559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 52979 | 0 | 52979 | 81890 | 0 | 81890 | 30417 | 0 | 30417 | 18375 | 0 | 18375 | 24995 | 0 | 24995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583658 | 0 | 583658 | 12269 | 0 | 12269 | 204538 | 0 | 204538 | 6501995 | 1317548 | 5184447 | 3609317 | 1317548 | 2291769 | 5068647 | 1317548 | 3751099 | 6501995 | 1317548 | 5184447 | 3609317 | 1317548 | 2291769 | 5068647 | 1317548 | 3751099 | 0 | 0 | ONWAV INC. | TRUE
NT10BIX5570080 | CCI | 2012 | Q3 | Q3 - 2012 | 3406069 | 1317548 | 2088521 | 3021292 | 1317548 | 1703744 | 3379696 | 1317548 | 2062148 | 150000 | 0 | 150000 | 19162 | 0 | 19162 | 49662 | 0 | 49662 | 1145000 | 0 | 1145000 | 623496 | 0 | 623496 | 678496 | 0 | 678496 | 1054911 | 0 | 1054911 | 382169 | 0 | 382169 | 980299 | 0 | 980299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 97066 | 0 | 97066 | 109566 | 0 | 109566 | 30417 | 0 | 30417 | 18375 | 0 | 18375 | 24995 | 0 | 24995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583658 | 0 | 583658 | 62805 | 0 | 62805 | 165383 | 0 | 165383 | 6501995 | 1317548 | 5184447 | 4224365 | 1317548 | 2906817 | 5395597 | 1317548 | 4078049 | 6501995 | 1317548 | 5184447 | 4224365 | 1317548 | 2906817 | 5395597 | 1317548 | 4078049 | 0 | 0 | ONWAV INC. | TRUE
NT10BIX5570080 | CCI | 2012 | Q4 | Q4 - 2012 | 3406069 | 1317548 | 2088521 | 3032142 | 1317548 | 1714594 | 3531355 | 1317548 | 2213807 | 150000 | 0 | 150000 | 56435 | 0 | 56435 | 56435 | 0 | 56435 | 1145000 | 0 | 1145000 | 683496 | 0 | 683496 | 713496 | 0 | 713496 | 1054911 | 0 | 1054911 | 400639 | 0 | 400639 | 960604 | 0 | 960604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 114269 | 0 | 114269 | 160534 | 0 | 160534 | 30417 | 0 | 30417 | 23495 | 0 | 23495 | 24995 | 0 | 24995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583658 | 0 | 583658 | 74002 | 0 | 74002 | 227696 | 0 | 227696 | 6501995 | 1317548 | 5184447 | 4384478 | 1317548 | 3066930 | 5675115 | 1317548 | 4357567 | 6501995 | 1317548 | 5184447 | 4384478 | 1317548 | 3066930 | 5675115 | 1317548 | 4357567 | 0 | 0 | ONWAV INC. | TRUE
NT10BIX5570080 | CCI | 2013 | Q1 | Q1 - 2013 | 3406069 | 1317548 | 2088521 | 3151629 | 1317548 | 1834081 | 3666784 | 1317548 | 2349236 | 150000 | 0 | 150000 | 56435 | 0 | 56435 | 56435 | 0 | 56435 | 1145000 | 0 | 1145000 | 714296 | 0 | 714296 | 760376 | 0 | 760376 | 1054911 | 0 | 1054911 | 405766 | 0 | 405766 | 1147483 | 0 | 1147483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124440 | 0 | 124440 | 128160 | 0 | 128160 | 158160 | 0 | 158160 | 30417 | 0 | 30417 | 24695 | 0 | 24695 | 24695 | 0 | 24695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583658 | 0 | 583658 | 111375 | 0 | 111375 | 241169 | 0 | 241169 | 6501995 | 1317548 | 5184447 | 4592356 | 1317548 | 3274808 | 6055102 | 1317548 | 4737554 | 6501995 | 1317548 | 5184447 | 4592356 | 1317548 | 3274808 | 6055102 | 1317548 | 4737554 | 0 | 0 | ONWAV INC. | TRUE
NT10BIX5570080 | CCI | 2013 | Q2 | Q2 - 2013 | 3790131 | 1317548 | 2472583 | 3272085 | 1317548 | 1954537 | 3489270 | 1317548 | 2171722 | 56436 | 0 | 56436 | 56435 | 0 | 56435 | 59920 | 0 | 59920 | 912140 | 0 | 912140 | 759296 | 0 | 759296 | 801796 | 0 | 801796 | 1176793 | 0 | 1176793 | 1132051 | 0 | 1132051 | 1293838 | 0 | 1293838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191500 | 0 | 191500 | 150073 | 0 | 150073 | 170073 | 0 | 170073 | 24995 | 0 | 24995 | 24695 | 0 | 24695 | 24695 | 0 | 24695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 350000 | 154465 | 0 | 154465 | 237373 | 0 | 237373 | 6501995 | 1317548 | 5184447 | 5549100 | 1317548 | 4231552 | 6076965 | 1317548 | 4759417 | 6501995 | 1317548 | 5184447 | 5549100 | 1317548 | 4231552 | 6076965 | 1317548 | 4759417 | 0 | 0 | ONWAV INC. | TRUE
NT10BIX5570080 | CCI | 2013 | Q3 | Q3 - 2013 | 3790131 | 1317548 | 2472583 | 3814450 | 2496902 | 1957347 | 3814450 | 1317548 | 2496902 | 56436 | 0 | 56436 | 60477 | 0 | 60477 | 60477 | 0 | 60477 | 912140 | 0 | 912140 | 877305 | 0 | 877305 | 877305 | 0 | 877305 | 1176793 | 0 | 1176793 | 1257390 | 0 | 1257390 | 1257390 | 0 | 1257390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191500 | 0 | 191500 | 191709 | 0 | 191709 | 191709 | 0 | 191709 | 24995 | 0 | 24995 | 24695 | 0 | 24695 | 24695 | 0 | 24695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 350000 | 275969 | 0 | 275969 | 275969 | 0 | 275969 | 6501995 | 1317548 | 5184447 | 6501995 | 2496902 | 4644892 | 6501995 | 1317548 | 5184447 | 6501995 | 1317548 | 5184447 | 6501995 | 2496902 | 4644892 | 6501995 | 1317548 | 5184447 | 0 | 0 | ONWAV INC. | TRUE
NT10BIX5570081 | CCI | 2010 | Q4 | Q4 - 2010 | 13369978 | 7498090 | 5871888 | 0 | 0 | 0 | 1060342 | 486360 | 573982 | 8139804 | 0 | 8139804 | 8716 | 0 | 8716 | 340802 | 0 | 340802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 36031 | 0 | 36031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77146 | 2 | 62148 | 62148 | 0 | 77148 | 77148 | 0 | 25033000 | 7575236 | 17457764 | 70864 | 62148 | 8716 | 1514323 | 563508 | 950815 | 25033000 | 7575236 | 17457764 | 70864 | 62148 | 8716 | 1514323 | 563508 | 950815 | 0 | 0 | District of Columbia Government | TRUE
NT10BIX5570081 | CCI | 2011 | Q1 | Q1 - 2011 | 13369978 | 7498090 | 5871888 | 0 | 0 | 0 | 5770644 | 3465910 | 2304734 | 8139804 | 0 | 8139804 | 3291 | 0 | 3291 | 1190793 | 15000 | 1175793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 52500 | 0 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77146 | 2 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 117939 | 62148 | 55791 | 7023585 | 3543058 | 3480527 | 25033000 | 7575236 | 17457764 | 117939 | 62148 | 55791 | 7023585 | 3543058 | 3480527 | 0 | 0 | District of Columbia Government | TRUE
NT10BIX5570081 | CCI | 2011 | Q2 | Q2 - 2011 | 13369978 | 7498088 | 5871890 | 907304 | 317971 | 589333 | 5448463 | 3480910 | 1967553 | 8139804 | 0 | 8139804 | 199511 | 0 | 199511 | 3407469 | 0 | 3407469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 48143 | 0 | 48143 | 80000 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 343181 | 0 | 343181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 1217106 | 380119 | 836987 | 9341261 | 3543058 | 5798203 | 25033000 | 7575236 | 17457764 | 1217106 | 380119 | 836987 | 9341261 | 3543058 | 5798203 | 0 | 0 | District of Columbia Government | TRUE
NT10BIX5570081 | CCI | 2011 | Q3 | Q3 - 2011 | 13369978 | 7498088 | 5871890 | 1976881 | 317971 | 1658910 | 7942067 | 5468830 | 2473237 | 8139804 | 0 | 8139804 | 366835 | 0 | 366835 | 2315543 | 0 | 2315543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 85398 | 0 | 85398 | 215000 | 0 | 215000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 2491262 | 380119 | 2111143 | 10534758 | 5530978 | 5003780 | 25033000 | 7575236 | 17457764 | 2491262 | 380119 | 2111143 | 10534758 | 5530978 | 5003780 | 0 | 0 | District of Columbia Government | TRUE
NT10BIX5570081 | CCI | 2011 | Q4 | Q4 - 2011 | 13369978 | 7498088 | 5871890 | 5906013 | 4160950 | 1745063 | 8200000 | 4300000 | 3900000 | 8139804 | 0 | 8139804 | 1045071 | 0 | 1045071 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 919789 | 0 | 919789 | 1115000 | 0 | 1115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 7933021 | 4223098 | 3709923 | 10877148 | 4362148 | 6515000 | 25033000 | 7575236 | 17457764 | 7933021 | 4223098 | 3709923 | 10877148 | 4362148 | 6515000 | 0 | 0 | District of Columbia Government | TRUE
NT10BIX5570081 | CCI | 2012 | Q1 | Q1 - 2012 | 13369978 | 7498088 | 5871890 | 7150443 | 4160951 | 2989492 | 9550000 | 5150000 | 4400000 | 8139804 | 0 | 8139804 | 2008486 | 0 | 2008486 | 3450000 | 0 | 3450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 959318 | 0 | 959318 | 1150000 | 0 | 1150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 10180395 | 4223099 | 5957296 | 14212148 | 5212148 | 9000000 | 25033000 | 7575236 | 17457764 | 10180395 | 4223099 | 5957296 | 14212148 | 5212148 | 9000000 | 0 | 0 | District of Columbia Government | TRUE
NT10BIX5570081 | CCI | 2012 | Q2 | Q2 - 2012 | 13369978 | 7498088 | 5871890 | 8572864 | 4161304 | 4411560 | 10485000 | 5010000 | 5475000 | 8139804 | 0 | 8139804 | 4158058 | 0 | 4158058 | 5000000 | 0 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 995425 | 0 | 995425 | 1200000 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 13788495 | 4223452 | 9565043 | 16747148 | 5072148 | 11675000 | 25033000 | 7575236 | 17457764 | 13788495 | 4223452 | 9565043 | 16747148 | 5072148 | 11675000 | 0 | 128118 | District of Columbia Government | TRUE
NT10BIX5570081 | CCI | 2012 | Q3 | Q3 - 2012 | 13369978 | 7498088 | 5871890 | 9160711 | 4161304 | 4999407 | 11262852 | 5637852 | 5625000 | 8139804 | 0 | 8139804 | 5136804 | 0 | 5136804 | 5700000 | 0 | 5700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 1024213 | 0 | 1024213 | 1175000 | 0 | 1175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 15383876 | 4223452 | 11160424 | 18200000 | 5700000 | 12500000 | 25033000 | 7575236 | 17457764 | 15383876 | 4223452 | 11160424 | 18200000 | 5700000 | 12500000 | 0 | 277264 | District of Columbia Government | TRUE
NT10BIX5570081 | CCI | 2012 | Q4 | Q4 - 2012 | 13369978 | 7498088 | 5871890 | 11586642 | 5180064 | 6406578 | 13247852 | 6447852 | 6800000 | 8139804 | 0 | 8139804 | 6092310 | 0 | 6092310 | 6600000 | 0 | 6600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 1045518 | 0 | 1045518 | 1450000 | 0 | 1450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 18786618 | 5242212 | 13544406 | 21510000 | 6510000 | 15000000 | 25033000 | 7575236 | 17457764 | 18786618 | 5242212 | 13544406 | 21510000 | 6510000 | 15000000 | 0 | 360608 | District of Columbia Government | TRUE
NT10BIX5570081 | CCI | 2013 | Q1 | Q1 - 2013 | 13369978 | 7498088 | 5871890 | 12313172 | 5827245 | 6485927 | 13369978 | 6498088 | 6871890 | 8139804 | 0 | 8139804 | 6683912 | 0 | 6683912 | 7185874 | 0 | 7185874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 1072633 | 0 | 1072633 | 1200000 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 77148 | 77148 | 0 | 25033000 | 7575236 | 17457764 | 20131865 | 5889393 | 14242472 | 21833000 | 6575236 | 15257764 | 25033000 | 7575236 | 17457764 | 20131865 | 5889393 | 14242472 | 21833000 | 6575236 | 15257764 | 0 | 371938 | District of Columbia Government | TRUE
NT10BIX5570081 | CCI | 2013 | Q2 | Q2 - 2013 | 13369978 | 7498088 | 5871890 | 13107863 | 6618855 | 6489008 | 15180020 | 7513088 | 7666932 | 8139804 | 0 | 8139804 | 7384980 | 0 | 7384980 | 8366822 | 0 | 8366822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1629320 | 0 | 1629320 | 1094813 | 0 | 1094813 | 1424010 | 0 | 1424010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816750 | 0 | 1816750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77148 | 77148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 21649804 | 6681003 | 14968801 | 25033000 | 7575236 | 17457764 | 25033000 | 7575236 | 17457764 | 21649804 | 6681003 | 14968801 | 25033000 | 7575236 | 17457764 | 0 | 408484 | District of Columbia Government | TRUE
NT10BIX5570081 | CCI | 2013 | Q3 | Q3 - 2013 | 13628980 | 6815232 | 6813748 | 14269362 | 6322015 | 7947347 | 14269362 | 6322015 | 7947347 | 9710851 | 697856 | 9012995 | 9137462 | 1191072 | 7946390 | 9137462 | 1191072 | 7946390 | 133678 | 0 | 133678 | 66684 | 0 | 66684 | 66684 | 0 | 66684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1497343 | 0 | 1497343 | 1497343 | 0 | 1497343 | 1497343 | 0 | 1497343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 62148 | 62148 | 0 | 25033000 | 7575236 | 17457764 | 25032999 | 7575235 | 17457764 | 25032999 | 7575235 | 17457764 | 25033000 | 7575236 | 17457764 | 25032999 | 7575235 | 17457764 | 25032999 | 7575235 | 17457764 | 449197 | 449197 | District of Columbia Government | TRUE
NT10BIX5570082 | CCI | 2010 | Q3 | Q3 - 2010 | 24022352 | 1411170 | 22611182 | 0 | 0 | 0 | 28927 | 0 | 28927 | 23333015 | 17709650 | 5623365 | 0 | 0 | 0 | 0 | 0 | 0 | 4855407 | 15000 | 4840407 | 84350 | 0 | 84350 | 414474 | 16153 | 398321 | 96000 | 28800 | 67200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4922273 | 1404550 | 3517723 | 0 | 0 | 0 | 34020 | 10151 | 23868 | 78425 | 0 | 78425 | 0 | 0 | 0 | 0 | 0 | 0 | 153939 | 46182 | 107757 | 0 | 0 | 0 | 0 | 0 | 0 | 7359864 | 645119 | 6714745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 106429 | 920188 | 175296 | 0 | 175296 | 273296 | 29400 | 243896 | 65847892 | 21366900 | 44480992 | 259646 | 0 | 259646 | 750717 | 55704 | 695012 | 65847892 | 21366900 | 44480992 | 259646 | 0 | 259646 | 750717 | 55704 | 695012 | 0 | 0 | University System of New Hampshire | TRUE
NT10BIX5570082 | CCI | 2010 | Q4 | Q4 - 2010 | 24022352 | 1411170 | 22611182 | 0 | 0 | 0 | 1681670 | 680000 | 1001670 | 23333015 | 17709650 | 5623365 | 0 | 0 | 0 | 1202175 | 70000 | 1132175 | 4855407 | 15000 | 4840407 | 720432 | 0 | 720432 | 1033710 | 29400 | 1004310 | 96000 | 28800 | 67200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4922273 | 1404550 | 3517723 | 1097 | 0 | 1097 | 148963 | 48676 | 100288 | 78425 | 0 | 78425 | 0 | 0 | 0 | 0 | 0 | 0 | 153939 | 46182 | 107757 | 0 | 0 | 0 | 0 | 0 | 0 | 7359864 | 645119 | 6714745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 106429 | 920188 | 0 | 0 | 0 | 0 | 0 | 0 | 65847892 | 21366900 | 44480992 | 721529 | 0 | 721529 | 4066518 | 828076 | 3238443 | 65847892 | 21366900 | 44480992 | 721529 | 0 | 721529 | 4066518 | 828076 | 3238443 | 0 | 0 | University System of New Hampshire | TRUE
NT10BIX5570082 | CCI | 2011 | Q1 | Q1 - 2011 | 24022352 | 1411170 | 22611182 | 0 | 0 | 0 | 449772 | 256889 | 192883 | 23333015 | 17709650 | 5623365 | 0 | 0 | 0 | 0 | 0 | 0 | 4855407 | 15000 | 4840407 | 1042581 | 0 | 1042581 | 1487059 | 4476 | 1482583 | 96000 | 28800 | 67200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4922273 | 1404550 | 3517723 | 118999 | 46566 | 72433 | 436109 | 144823 | 291286 | 78425 | 0 | 78425 | 0 | 0 | 0 | 0 | 0 | 0 | 153939 | 46182 | 107757 | 0 | 0 | 0 | 0 | 0 | 0 | 7359864 | 645119 | 6714745 | 0 | 0 | 0 | 1691494 | 521416 | 1170078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 106429 | 920188 | 0 | 0 | 0 | 0 | 0 | 0 | 65847892 | 21366900 | 44480992 | 1161580 | 46566 | 1115014 | 4064434 | 927604 | 3136830 | 65847892 | 21366900 | 44480992 | 1161580 | 46566 | 1115014 | 4064434 | 927604 | 3136830 | 0 | 0 | University System of New Hampshire | TRUE
NT10BIX5570082 | CCI | 2011 | Q2 | Q2 - 2011 | 18481355 | 2321328 | 16160027 | 0 | 0 | 0 | 449772 | 252360 | 197412 | 30815467 | 18555862 | 12259605 | 0 | 0 | 0 | 27900 | 8370 | 19530 | 5386259 | 87018 | 5299241 | 1644827 | 20000 | 1624827 | 1785347 | 33403 | 1751944 | 72000 | 21485 | 50515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 282874 | 4509735 | 698824 | 467493 | 231331 | 2057577 | 1341176 | 716401 | 176530 | 0 | 176530 | 110118 | 11956 | 98162 | 143430 | 16360 | 127070 | 153939 | 46182 | 107757 | 0 | 0 | 0 | 0 | 0 | 0 | 5298403 | 0 | 5298403 | 2396829 | 596829 | 1800000 | 4022546 | 596829 | 3425717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671330 | 52151 | 619179 | 29400 | 29400 | 0 | 98000 | 29400 | 68600 | 65847892 | 21366900 | 44480992 | 4879998 | 1125678 | 3754320 | 8584572 | 2277898 | 6306674 | 65847892 | 21366900 | 44480992 | 4879998 | 1125678 | 3754320 | 8584572 | 2277898 | 6306674 | 0 | 0 | University System of New Hampshire | TRUE
NT10BIX5570082 | CCI | 2011 | Q3 | Q3 - 2011 | 23073047 | 15918722 | 7154325 | 2204406 | 1808956 | 395450 | 5768974 | 3822021 | 1946953 | 23982324 | 2555718 | 21426606 | 232255 | 0 | 232255 | 297700 | 65445 | 232255 | 5210962 | 87543 | 5123419 | 1910696 | 40000 | 1870696 | 2229874 | 50054 | 2179820 | 72000 | 21482 | 50518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 551338 | 4241271 | 2332251 | 265942 | 2066309 | 3281906 | 1050821 | 2231085 | 176530 | 18860 | 157670 | 128910 | 13960 | 114950 | 163290 | 17860 | 145430 | 153939 | 45930 | 108009 | 0 | 0 | 0 | 0 | 0 | 0 | 7359864 | 2061461 | 5298403 | 1970100 | 0 | 1970100 | 6763964 | 0 | 6763964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 105846 | 920771 | 98000 | 29400 | 68600 | 98000 | 29400 | 68600 | 65847892 | 21366900 | 44480992 | 8876618 | 2158258 | 6718360 | 18603708 | 5035601 | 13568107 | 65847892 | 21366900 | 44480992 | 8876618 | 2158258 | 6718360 | 18603708 | 5035601 | 13568107 | 0 | 0 | University System of New Hampshire | TRUE
NT10BIX5570082 | CCI | 2011 | Q4 | Q4 - 2011 | 23073047 | 15918722 | 7154325 | 5540093 | 4628460 | 911634 | 13206914 | 11085175 | 2121739 | 23982324 | 2555718 | 21426606 | 1857894 | 0 | 1857894 | 3321893 | 56385 | 3265508 | 5210962 | 87543 | 5123419 | 2247877 | 50058 | 2197819 | 2580385 | 60356 | 2520029 | 72000 | 21482 | 50518 | 0 | 0 | 0 | 72000 | 21600 | 50400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 551338 | 4241271 | 4280659 | 274478 | 4006180 | 4666590 | 375682 | 4290907 | 176530 | 18860 | 157670 | 136110 | 21160 | 114950 | 161470 | 21160 | 140310 | 153939 | 45930 | 108009 | 0 | 0 | 0 | 51313 | 15394 | 35919 | 7359864 | 2061461 | 5298403 | 3049593 | 0 | 3049593 | 5581505 | 0 | 5581505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 105846 | 920771 | 98000 | 29400 | 68600 | 98000 | 29400 | 68600 | 65847892 | 21366900 | 44480992 | 17210226 | 5003556 | 12206670 | 29740070 | 11665152 | 18074917 | 65847892 | 21366900 | 44480992 | 17210226 | 5003556 | 12206670 | 29740070 | 11665152 | 18074917 | 0 | 0 | University System of New Hampshire | TRUE
NT10BIX5570082 | CCI | 2012 | Q1 | Q1 - 2012 | 23073047 | 15918722 | 7154325 | 13269067 | 11290281 | 1978785 | 17796160 | 14690739 | 3105420 | 23982324 | 2555718 | 21426606 | 4557801 | 167403 | 4390398 | 9693402 | 1103120 | 8590282 | 5210962 | 87543 | 5123419 | 2608775 | 75130 | 2533645 | 2978328 | 81525 | 2896803 | 72000 | 21482 | 50518 | 4819 | 1300 | 3519 | 72000 | 21482 | 50518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 551338 | 4241271 | 5042169 | 376807 | 4665362 | 5375125 | 431068 | 4944058 | 176530 | 18860 | 157670 | 150630 | 23560 | 127070 | 163870 | 24560 | 139310 | 153939 | 45930 | 108009 | 0 | 0 | 0 | 0 | 0 | 0 | 7359864 | 2061461 | 5298403 | 5870250 | 0 | 5870250 | 9463623 | 2061461 | 7402162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 105846 | 920771 | 116454 | 29400 | 87054 | 254966 | 68600 | 186366 | 65847892 | 21366900 | 44480992 | 31619965 | 11963881 | 19656083 | 45797474 | 18482555 | 27314919 | 65847892 | 21366900 | 44480992 | 31619965 | 11963881 | 19656083 | 45797474 | 18482555 | 27314919 | 0 | 0 | University System of New Hampshire | TRUE
NT10BIX5570082 | CCI | 2012 | Q2 | Q2 - 2012 | 23073047 | 15918723 | 7154324 | 15923486 | 13175137 | 2748349 | 17095177 | 13555274 | 3539904 | 23982324 | 2555718 | 21426606 | 7301695 | 458804 | 6842891 | 12530658 | 1393954 | 11136704 | 5210963 | 87543 | 5123420 | 2942507 | 79695 | 2862812 | 3357628 | 101716 | 3255912 | 72000 | 21482 | 50518 | 4819 | 1300 | 3519 | 72000 | 21482 | 50518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 551338 | 4241271 | 5121067 | 394864 | 4726203 | 5684118 | 483518 | 5200600 | 176530 | 18860 | 157670 | 143430 | 16360 | 127070 | 154463 | 17193 | 137270 | 153939 | 45930 | 108009 | 0 | 0 | 0 | 0 | 0 | 0 | 7359864 | 2061461 | 5298403 | 9087915 | 2061461 | 7026454 | 9403967 | 2061461 | 7342506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 105846 | 920771 | 124054 | 29400 | 94654 | 480126 | 106007 | 374119 | 65847893 | 21366901 | 44480992 | 40648973 | 16217021 | 24431952 | 48778137 | 17740605 | 31037533 | 65847893 | 21366901 | 44480992 | 40648973 | 16217021 | 24431952 | 48778137 | 17740605 | 31037533 | 0 | 0 | University System of New Hampshire | TRUE
NT10BIX5570082 | CCI | 2012 | Q3 | Q3 - 2012 | 23073047 | 15918723 | 7154324 | 17148024 | 13508453 | 3639572 | 18088071 | 13839705 | 4248367 | 23982324 | 2555718 | 21426606 | 10143763 | 883833 | 9259930 | 13708129 | 1373196 | 12334933 | 5210962 | 87542 | 5123420 | 3309472 | 104587 | 3204885 | 3682223 | 115579 | 3566644 | 72000 | 21482 | 50518 | 4819 | 1300 | 3519 | 72000 | 21485 | 50515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 551338 | 4241271 | 5439490 | 466617 | 4972872 | 5660570 | 519219 | 5141350 | 176530 | 18860 | 157670 | 144630 | 16360 | 128270 | 177730 | 16360 | 161370 | 153939 | 45930 | 108009 | 0 | 0 | 0 | 51313 | 15310 | 36003 | 7359864 | 2061461 | 5298403 | 10570197 | 2061461 | 8508736 | 10570197 | 2061461 | 8508736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 105846 | 920771 | 348137 | 29400 | 318737 | 447449 | 29400 | 418049 | 65847892 | 21366900 | 44480992 | 47108532 | 17072011 | 30036521 | 52457682 | 17991715 | 34465967 | 65847892 | 21366900 | 44480992 | 47108532 | 17072011 | 30036521 | 52457682 | 17991715 | 34465967 | 0 | 0 | University System of New Hampshire | TRUE
NT10BIX5570082 | CCI | 2012 | Q4 | Q4 - 2012 | 23073046 | 15918722 | 7154324 | 17631494 | 13687857 | 3943637 | 19064908 | 14326764 | 4738144 | 23982324 | 2555718 | 21426606 | 12772279 | 1273163 | 11499116 | 14991576 | 1621354 | 13370222 | 5210963 | 87543 | 5123420 | 3614318 | 114079 | 3500239 | 4567733 | 139410 | 4428323 | 72000 | 21482 | 50518 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 551338 | 4241271 | 6061830 | 503917 | 5557913 | 6145220 | 533199 | 5612021 | 176530 | 18860 | 157670 | 144630 | 16360 | 128270 | 144630 | 16360 | 128270 | 153939 | 45930 | 108009 | 0 | 0 | 0 | 51313 | 15310 | 36003 | 7359864 | 2061461 | 5298403 | 11570433 | 2061461 | 9508972 | 11570433 | 2061461 | 9508972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 105846 | 920771 | 624097 | 29400 | 594697 | 723409 | 29400 | 694009 | 65847892 | 21366900 | 44480992 | 52423900 | 17687537 | 34736363 | 57264041 | 18744558 | 38519483 | 65847892 | 21366900 | 44480992 | 52423900 | 17687537 | 34736363 | 57264041 | 18744558 | 38519483 | 0 | 0 | University System of New Hampshire | TRUE
NT10BIX5570082 | CCI | 2013 | Q1 | Q1 - 2013 | 23073046 | 15918722 | 7154324 | 18155232 | 13896388 | 4258844 | 20222746 | 14398004 | 5824742 | 23982324 | 2555718 | 21426606 | 13957788 | 1523602 | 12434186 | 19084291 | 2326339 | 16757952 | 5210963 | 87543 | 5123420 | 3940125 | 116410 | 3823715 | 4257153 | 123763 | 4133390 | 72000 | 21482 | 50518 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792609 | 551338 | 4241271 | 6157188 | 532533 | 5624655 | 6317545 | 568765 | 5748780 | 176530 | 18860 | 157670 | 144630 | 16360 | 128270 | 144630 | 16360 | 128270 | 153939 | 45930 | 108009 | 0 | 0 | 0 | 62500 | 18650 | 43850 | 7359864 | 2061461 | 5298403 | 11570433 | 2061461 | 9508972 | 11570433 | 2061461 | 9508972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026617 | 105846 | 920771 | 624097 | 29400 | 594697 | 624097 | 29400 | 594697 | 65847892 | 21366900 | 44480992 | 54554312 | 18177454 | 36376858 | 62288214 | 19544042 | 42744172 | 65847892 | 21366900 | 44480992 | 54554312 | 18177454 | 36376858 | 62288214 | 19544042 | 42744172 | 0 | 0 | University System of New Hampshire | TRUE
NT10BIX5570082 | CCI | 2013 | Q2 | Q2 - 2013 | 16989927 | 10903618 | 6086309 | 17270483 | 12599706 | 4670777 | 16571750 | 10776531 | 5795219 | 20337047 | 2572036 | 17765011 | 16366740 | 2009150 | 14357590 | 19481902 | 2521478 | 16960424 | 4933387 | 341553 | 4591834 | 4247511 | 119227 | 4128284 | 4691752 | 337016 | 4354736 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6240228 | 556668 | 5683560 | 6396494 | 531521 | 5864973 | 6546007 | 550979 | 5995028 | 176530 | 17140 | 159390 | 145470 | 16360 | 129110 | 176530 | 16360 | 160170 | 125000 | 37300 | 87700 | 0 | 0 | 0 | 30000 | 9000 | 21000 | 13319536 | 3810564 | 9508972 | 13565341 | 3805564 | 9759777 | 13565341 | 3805564 | 9759777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624097 | 29400 | 594697 | 624097 | 29400 | 594697 | 624097 | 29400 | 594697 | 62750571 | 18269579 | 44480992 | 58620955 | 19112228 | 39508727 | 61692198 | 18047628 | 43644570 | 62750571 | 18269579 | 44480992 | 58620955 | 19112228 | 39508727 | 61692198 | 18047628 | 43644570 | 0 | 0 | University System of New Hampshire | TRUE
NT10BIX5570082 | CCI | 2013 | Q3 | Q3 - 2013 | 16989927 | 10903618 | 6086309 | 15824489 | 10695776 | 5128713 | 16975012 | 10943612 | 6031400 | 20337047 | 2572036 | 17765011 | 18658381 | 2362501 | 16295880 | 19689831 | 2534745 | 17155086 | 4933387 | 341553 | 4591834 | 4513194 | 119227 | 4393967 | 4917800 | 351119 | 4566681 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6240228 | 556668 | 5683560 | 6427161 | 540722 | 5886439 | 6579790 | 557604 | 6022186 | 176530 | 17140 | 159390 | 145470 | 16360 | 129110 | 179234 | 16049 | 163185 | 125000 | 37300 | 87700 | 13633 | 4090 | 9543 | 124343 | 30185 | 94158 | 13319536 | 3810564 | 9508972 | 13565341 | 3805564 | 9759777 | 13565341 | 3805564 | 9759777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624097 | 29400 | 594697 | 624097 | 29400 | 594697 | 624097 | 29400 | 594697 | 62750571 | 18269579 | 44480992 | 59776585 | 17574940 | 42201645 | 62660267 | 18269578 | 44390689 | 62750571 | 18269579 | 44480992 | 59776585 | 17574940 | 42201645 | 62660267 | 18269578 | 44390689 | 0 | 0 | University System of New Hampshire | TRUE
NT10BIX5570082 | CCI | 2013 | Q4 | Q4 - 2013 | 16989927 | 10903618 | 6086309 | 17141439 | 11028845 | 6112594 | 17141439 | 11028845 | 6112594 | 20337047 | 2572036 | 17765011 | 19143714 | 2435596 | 16708118 | 19143714 | 2435596 | 16708118 | 4933387 | 341553 | 4591834 | 5237362 | 370929 | 4866433 | 5237362 | 370929 | 4866433 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 4819 | 1300 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6240228 | 556668 | 5683560 | 6420020 | 561069 | 5858951 | 6420020 | 561069 | 5858951 | 176530 | 17140 | 159390 | 176520 | 17393 | 159127 | 176520 | 17393 | 159127 | 125000 | 37300 | 87700 | 45436 | 13542 | 31894 | 45436 | 13542 | 31894 | 13319536 | 3810564 | 9508972 | 14001659 | 3805564 | 10196095 | 14001659 | 3805564 | 10196095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624097 | 29400 | 594697 | 543778 | 29400 | 514378 | 543778 | 29400 | 514378 | 62750571 | 18269579 | 44480992 | 62714747 | 18263638 | 44451109 | 62714747 | 18263638 | 44451109 | 62750571 | 18269579 | 44480992 | 62714747 | 18263638 | 44451109 | 62714747 | 18263638 | 44451109 | 0 | 0 | University System of New Hampshire | TRUE
NT10BIX5570084 | CCI | 2010 | Q4 | Q4 - 2010 | 18648743 | 9853848 | 8794895 | 0 | 0 | 0 | 1320000 | 0 | 1320000 | 1153002 | 0 | 1153002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4597038 | 0 | 4597038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2309100 | 0 | 2309100 | 123776 | 0 | 123776 | 685000 | 0 | 685000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 789800 | 0 | 789800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71084 | 0 | 71084 | 2704 | 0 | 2704 | 0 | 0 | 0 | 27568767 | 9853848 | 17714919 | 126480 | 0 | 126480 | 2005000 | 0 | 2005000 | 27568767 | 9853848 | 17714919 | 126480 | 0 | 126480 | 2005000 | 0 | 2005000 | 0 | 0 | Iowa Health System | TRUE
NT10BIX5570084 | CCI | 2011 | Q1 | Q1 - 2011 | 18648743 | 9853848 | 8794895 | 0 | 0 | 0 | 0 | 0 | 0 | 1153002 | 0 | 1153002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4597038 | 0 | 4597038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2309100 | 0 | 2309100 | 289549 | 0 | 289549 | 741719 | 0 | 741719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 789800 | 0 | 789800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71084 | 0 | 71084 | 2704 | 0 | 2704 | 2704 | 0 | 2704 | 27568767 | 9853848 | 17714919 | 292253 | 0 | 292253 | 744423 | 0 | 744423 | 27568767 | 9853848 | 17714919 | 292253 | 0 | 292253 | 744423 | 0 | 744423 | 0 | 0 | Iowa Health System | TRUE
NT10BIX5570084 | CCI | 2011 | Q2 | Q2 - 2011 | 17079303 | 9355655 | 7723648 | 0 | 0 | 0 | 0 | 0 | 0 | 3071873 | 0 | 3071873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1146600 | 0 | 1146600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2140825 | 0 | 2140825 | 512527 | 0 | 512527 | 991069 | 0 | 991069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 2835 | 0 | 2835 | 10782 | 0 | 10782 | 24102285 | 9355655 | 14746630 | 515362 | 0 | 515362 | 1001851 | 0 | 1001851 | 24102285 | 9355655 | 14746630 | 515362 | 0 | 515362 | 1001851 | 0 | 1001851 | 0 | 0 | Iowa Health System | TRUE
NT10BIX5570084 | CCI | 2011 | Q3 | Q3 - 2011 | 17079303 | 9355655 | 7723648 | 0 | 0 | 0 | 13091137 | 6871848 | 6219289 | 3071873 | 0 | 3071873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1146600 | 0 | 1146600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2140825 | 0 | 2140825 | 954886 | 0 | 954886 | 1368407 | 0 | 1368407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 2835 | 0 | 2835 | 14085 | 0 | 14084 | 24102285 | 9355655 | 14746630 | 957721 | 0 | 957721 | 14473629 | 6871848 | 7601780 | 24102285 | 9355655 | 14746630 | 957721 | 0 | 957721 | 14473629 | 6871848 | 7601780 | 0 | 0 | Iowa Health System | TRUE
NT10BIX5570084 | CCI | 2011 | Q4 | Q4 - 2011 | 17079303 | 9355655 | 7723648 | 11695425 | 6871848 | 4823577 | 14255655 | 9355655 | 4900000 | 3071873 | 0 | 3071873 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 46025 | 0 | 46025 | 46025 | 0 | 46025 | 1146600 | 0 | 1146600 | 251451 | 0 | 251451 | 300000 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2140825 | 0 | 2140825 | 1552074 | 0 | 1552074 | 1750000 | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 0 | 0 | 0 | 50260 | 0 | 50260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 9071 | 0 | 9071 | 15000 | 0 | 15000 | 24102285 | 9355655 | 14746630 | 13554046 | 6871848 | 6682198 | 16516940 | 9355655 | 7161285 | 24102285 | 9355655 | 14746630 | 13554046 | 6871848 | 6682198 | 16516940 | 9355655 | 7161285 | 0 | 0 | Iowa Health System | TRUE
NT10BIX5570084 | CCI | 2012 | Q1 | Q1 - 2012 | 16226313 | 9355655 | 6870658 | 12977831 | 8154254 | 4823577 | 14255655 | 9355655 | 4900000 | 3071873 | 0 | 3071873 | 0 | 0 | 0 | 100000 | 0 | 100000 | 85800 | 0 | 85800 | 46025 | 0 | 46025 | 65000 | 0 | 65000 | 1146600 | 0 | 1146600 | 251451 | 0 | 251451 | 600000 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908015 | 0 | 2908015 | 1552074 | 0 | 1552074 | 1950000 | 0 | 1950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 9071 | 0 | 9071 | 25000 | 0 | 25000 | 24102285 | 9355655 | 14746630 | 14836452 | 8154254 | 6682198 | 17095655 | 9355655 | 7740000 | 24102285 | 9355655 | 14746630 | 14836452 | 8154254 | 6682198 | 17095655 | 9355655 | 7740000 | 0 | 0 | Iowa Health System | TRUE
NT10BIX5570084 | CCI | 2012 | Q2 | Q2 - 2012 | 16226313 | 9355655 | 6870658 | 14096789 | 8154254 | 5942535 | 14754254 | 8154254 | 6600000 | 3071873 | 0 | 3071873 | 145322 | 0 | 145322 | 745322 | 0 | 745322 | 85800 | 0 | 85800 | 60612 | 0 | 60612 | 70000 | 0 | 70000 | 1146600 | 0 | 1146600 | 531525 | 0 | 531525 | 800000 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908015 | 0 | 2908015 | 1846345 | 0 | 1846345 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 20185 | 0 | 20185 | 45000 | 0 | 45000 | 24102285 | 9355655 | 14746630 | 16700778 | 8154254 | 8546524 | 18514576 | 8154254 | 10360322 | 24102285 | 9355655 | 14746630 | 16700778 | 8154254 | 8546524 | 18514576 | 8154254 | 10360322 | 0 | 0 | Iowa Health System | TRUE
NT10BIX5570084 | CCI | 2012 | Q3 | Q3 - 2012 | 16226313 | 9355655 | 6870658 | 14203968 | 8154254 | 6049714 | 14903968 | 8154254 | 6749714 | 3071873 | 0 | 3071873 | 491929 | 0 | 491929 | 1000000 | 0 | 1000000 | 85800 | 0 | 85800 | 60612 | 0 | 60612 | 80000 | 0 | 80000 | 1146600 | 0 | 1146600 | 539448 | 0 | 539448 | 1000000 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908015 | 0 | 2908015 | 1899817 | 0 | 1899817 | 1980000 | 0 | 1980000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 300400 | 0 | 300400 | 380400 | 0 | 380400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 56185 | 0 | 56185 | 75000 | 0 | 75000 | 24102285 | 9355655 | 14746630 | 17552359 | 8154254 | 9398105 | 19419368 | 8154254 | 11265114 | 24102285 | 9355655 | 14746630 | 17552359 | 8154254 | 9398105 | 19419368 | 8154254 | 11265114 | 0 | 25000 | Iowa Health System | TRUE
NT10BIX5570084 | CCI | 2012 | Q4 | Q4 - 2012 | 16226313 | 9355655 | 6870658 | 14785274 | 8154254 | 6631020 | 15870658 | 9000000 | 6870658 | 3071873 | 0 | 3071873 | 1786000 | 0 | 1786000 | 2500000 | 0 | 2500000 | 85800 | 0 | 85800 | 75645 | 0 | 75645 | 85800 | 0 | 85800 | 1146600 | 0 | 1146600 | 925000 | 0 | 925000 | 1000000 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908015 | 0 | 2908015 | 2361127 | 0 | 2361127 | 2500000 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 423000 | 0 | 423000 | 475000 | 0 | 475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 101235 | 0 | 101235 | 125000 | 0 | 125000 | 24102285 | 9355655 | 14746630 | 20457281 | 8154254 | 12303027 | 22556458 | 9000000 | 13556458 | 24102285 | 9355655 | 14746630 | 20457281 | 8154254 | 12303027 | 22556458 | 9000000 | 13556458 | 0 | 48000 | Iowa Health System | TRUE
NT10BIX5570084 | CCI | 2013 | Q1 | Q1 - 2013 | 16226313 | 9355655 | 6870658 | 15127610 | 8154254 | 6973356 | 16329011 | 9355655 | 6973356 | 3071873 | 0 | 3071873 | 1854398 | 0 | 1854398 | 2500000 | 0 | 2500000 | 85800 | 0 | 85800 | 75645 | 0 | 75645 | 75645 | 0 | 75645 | 1146600 | 0 | 1146600 | 952303 | 0 | 952303 | 972303 | 0 | 972303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908015 | 0 | 2908015 | 2888194 | 0 | 2888194 | 2908015 | 0 | 2908015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 423000 | 0 | 423000 | 423000 | 0 | 423000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 131235 | 0 | 131235 | 131235 | 0 | 131235 | 24102285 | 9355655 | 14746630 | 21452385 | 8154254 | 13298131 | 23339209 | 9355655 | 13983554 | 24102285 | 9355655 | 14746630 | 21452385 | 8154254 | 13298131 | 23339209 | 9355655 | 13983554 | 0 | 93033 | Iowa Health System | TRUE
NT10BIX5570084 | CCI | 2013 | Q2 | Q2 - 2013 | 16226313 | 9355655 | 6870658 | 15127610 | 8154254 | 6973356 | 16329011 | 9355655 | 6973356 | 3071873 | 0 | 3071873 | 1854398 | 0 | 1854398 | 3071873 | 0 | 3071873 | 85800 | 0 | 85800 | 75645 | 0 | 75645 | 85800 | 0 | 85800 | 1146600 | 0 | 1146600 | 952303 | 0 | 952303 | 1123502 | 0 | 1123502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908015 | 0 | 2908015 | 2888194 | 0 | 2888194 | 2908015 | 0 | 2908015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502600 | 0 | 502600 | 423000 | 0 | 423000 | 423000 | 0 | 423000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161084 | 0 | 161084 | 131235 | 0 | 131235 | 161084 | 0 | 161084 | 24102285 | 9355655 | 14746630 | 21452385 | 8154254 | 13298131 | 24102285 | 9355655 | 14746630 | 24102285 | 9355655 | 14746630 | 21452385 | 8154254 | 13298131 | 24102285 | 9355655 | 14746630 | 0 | 93033 | Iowa Health System | TRUE
NT10BIX5570084 | CCI | 2013 | Q3 | Q3 - 2013 | 16224699 | 8558654 | 7666045 | 16224699 | 8558654 | 7666045 | 16224699 | 8558654 | 7666045 | 3065856 | 574701 | 2491155 | 3065856 | 574701 | 2491155 | 3065856 | 574701 | 2491155 | 57259 | 0 | 57259 | 57259 | 0 | 57259 | 57259 | 0 | 57259 | 1123506 | 0 | 1123506 | 1123506 | 0 | 1123506 | 1123506 | 0 | 1123506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2958658 | 222300 | 2736358 | 2958658 | 222300 | 2736358 | 2958658 | 222300 | 2736358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541071 | 0 | 541071 | 541071 | 0 | 541071 | 541071 | 0 | 541071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131236 | 0 | 131236 | 131236 | 0 | 131236 | 131236 | 0 | 131236 | 24102285 | 9355655 | 14746630 | 24102285 | 9355655 | 14746630 | 24102285 | 9355655 | 14746630 | 24102285 | 9355655 | 14746630 | 24102285 | 9355655 | 14746630 | 24102285 | 9355655 | 14746630 | 93033 | 93033 | Iowa Health System | TRUE
NT10BIX5570085 | CCI | 2010 | Q4 | Q4 - 2010 | 3763176 | 1088627 | 2674549 | 79990 | 23140 | 56850 | 79990 | 23140 | 56850 | 7824210 | 2451048 | 5373162 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 28928 | 71072 | 35522 | 10276 | 25246 | 49522 | 14476 | 35046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 30482 | 74888 | 76198 | 22043 | 54155 | 104198 | 30443 | 73755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 23143 | 56857 | 0 | 0 | 0 | 0 | 0 | 0 | 5544518 | 1603940 | 3940578 | 4206 | 1217 | 2989 | 75799 | 22694 | 53105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 26614 | 65386 | 46433 | 13432 | 33001 | 34000 | 10200 | 23800 | 17509274 | 5252782 | 12256492 | 242349 | 70108 | 172241 | 343509 | 100953 | 242556 | 17509274 | 5252782 | 12256492 | 242349 | 70108 | 172241 | 343509 | 100953 | 242556 | 0 | 0 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | CCI | 2011 | Q1 | Q1 - 2011 | 3763176 | 1088627 | 2674549 | 79990 | 23140 | 56850 | 79990 | 23140 | 56850 | 7824210 | 2451048 | 5373162 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 28928 | 71072 | 35522 | 10276 | 25246 | 35522 | 10276 | 25246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 30482 | 74888 | 121752 | 35221 | 86531 | 298366 | 89510 | 208856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 23143 | 56857 | 0 | 0 | 0 | 0 | 0 | 0 | 5544518 | 1603940 | 3940578 | 4206 | 1217 | 2989 | 4206 | 1217 | 2989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 26614 | 65386 | 46433 | 13432 | 33001 | 46433 | 13432 | 33001 | 17509274 | 5252782 | 12256492 | 287903 | 83286 | 204617 | 464517 | 137575 | 326942 | 17509274 | 5252782 | 12256492 | 287903 | 83286 | 204617 | 464517 | 137575 | 326942 | 0 | 0 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | CCI | 2011 | Q2 | Q2 - 2011 | 6400083 | 1920025 | 4480058 | 79990 | 23997 | 55993 | 79990 | 23997 | 55993 | 3650203 | 1095061 | 2555142 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 30000 | 70000 | 35522 | 10657 | 24865 | 45522 | 13657 | 31865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 118232 | 35469 | 82762 | 448366 | 134510 | 313856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 2433470 | 730041 | 1703429 | 59529 | 17859 | 41671 | 196010 | 58803 | 137207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 46433 | 13930 | 32503 | 46433 | 27600 | 64400 | 12861126 | 3858338 | 9002788 | 339706 | 101912 | 237794 | 816321 | 258567 | 603321 | 12861126 | 3858338 | 9002788 | 339706 | 101912 | 237794 | 816321 | 258567 | 603321 | 0 | 0 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | CCI | 2011 | Q3 | Q3 - 2011 | 6400083 | 1920025 | 4480058 | 79990 | 23997 | 55993 | 5389990 | 1616997 | 3772993 | 3650203 | 1095061 | 2555142 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 30000 | 70000 | 39186 | 11756 | 27430 | 47862 | 14359 | 33503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 326280 | 97884 | 228395 | 747276 | 224183 | 523093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 2433470 | 730041 | 1703429 | 59528 | 17858 | 41670 | 462359 | 138708 | 323651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 0 | 0 | 0 | 0 | 0 | 0 | 12861126 | 3858338 | 9002788 | 504984 | 151495 | 353488 | 6647487 | 1994247 | 4653240 | 12861126 | 3858338 | 9002788 | 504984 | 151495 | 353488 | 6647487 | 1994247 | 4653240 | 0 | 0 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | CCI | 2011 | Q4 | Q4 - 2011 | 6400083 | 1920025 | 4480058 | 3185836 | 955750 | 2230086 | 4579990 | 1373997 | 3205993 | 3650203 | 1095061 | 2555142 | 560292 | 168087 | 392204 | 340462 | 102139 | 238323 | 100000 | 30000 | 70000 | 41346 | 12404 | 28943 | 73523 | 22057 | 51466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 99255 | 29777 | 69478 | 848366 | 254510 | 593856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 0 | 0 | 0 | 9091 | 2727 | 6364 | 2433470 | 730041 | 1703429 | 582603 | 174781 | 407822 | 582085 | 174625 | 407460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 32837 | 9852 | 22985 | 43838 | 13151 | 30687 | 12861126 | 3858338 | 9002788 | 4502169 | 1350651 | 3151518 | 6477355 | 1943206 | 4534149 | 12861126 | 3858338 | 9002788 | 4502169 | 1350651 | 3151518 | 6477355 | 1943206 | 4534149 | 0 | 0 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | CCI | 2012 | Q1 | Q1 - 2012 | 6400083 | 1920025 | 4480058 | 3523924 | 1057176 | 2466748 | 5023924 | 1507177 | 3516747 | 3650203 | 1095061 | 2555142 | 723678 | 217103 | 506574 | 1223678 | 367103 | 856575 | 100000 | 30000 | 70000 | 41346 | 12404 | 28943 | 49615 | 14885 | 34730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 151449 | 45435 | 106014 | 181739 | 54522 | 127217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 0 | 0 | 0 | 25000 | 7500 | 17500 | 2433470 | 730041 | 1703429 | 975286 | 292586 | 682700 | 1170343 | 351103 | 819240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 72639 | 21793 | 50847 | 82639 | 24792 | 57847 | 12861126 | 3858338 | 9002788 | 5488322 | 1646497 | 3841826 | 7756938 | 2327082 | 5429856 | 12861126 | 3858338 | 9002788 | 5488322 | 1646497 | 3841826 | 7756938 | 2327082 | 5429856 | 0 | 0 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | CCI | 2012 | Q2 | Q2 - 2012 | 6400083 | 1920025 | 4480058 | 4156922 | 1247076 | 2909846 | 4500000 | 1350000 | 3150000 | 3650203 | 1095061 | 2555142 | 922034 | 276610 | 645424 | 1250000 | 375000 | 875000 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 49615 | 14885 | 34730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 169277 | 50784 | 118493 | 186205 | 55862 | 130343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 0 | 0 | 0 | 25000 | 7500 | 17500 | 2433470 | 730041 | 1703429 | 1423986 | 427196 | 996790 | 1725000 | 517500 | 1207500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52792 | 15838 | 36954 | 60000 | 18000 | 42000 | 12861126 | 3858338 | 9002788 | 6766357 | 2029908 | 4736449 | 7795820 | 2338747 | 5457073 | 12861126 | 3858338 | 9002788 | 6766357 | 2029908 | 4736449 | 7795820 | 2338747 | 5457073 | 0 | 0 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | CCI | 2012 | Q3 | Q3 - 2012 | 6400083 | 1920025 | 4480058 | 4135909 | 1240772 | 2895137 | 4963091 | 1488927 | 3474163 | 3650203 | 1095061 | 2555142 | 1171734 | 351520 | 820214 | 1406082 | 421825 | 984257 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 50000 | 15000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 197005 | 59102 | 137903 | 200000 | 60000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 30000 | 9000 | 21000 | 60000 | 18000 | 42000 | 2433470 | 730041 | 1703429 | 1580057 | 474017 | 1106040 | 1896068 | 568820 | 1327248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52791 | 15837 | 36954 | 52791 | 15839 | 36954 | 12861126 | 3858338 | 9002788 | 7208842 | 2162652 | 5046190 | 8628032 | 2588411 | 6039622 | 12861126 | 3858338 | 9002788 | 7208842 | 2162652 | 5046190 | 8628032 | 2588411 | 6039622 | 0 | 0 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | CCI | 2012 | Q4 | Q4 - 2012 | 6400083 | 1920025 | 4480058 | 4182113 | 1254633 | 2927480 | 4500000 | 1350000 | 3150000 | 3650203 | 1095061 | 2555142 | 1242882 | 372864 | 870018 | 1600000 | 480000 | 1120000 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 50000 | 15000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 210972 | 63292 | 147680 | 225000 | 67500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 75673 | 22702 | 52971 | 85000 | 25500 | 59500 | 2433470 | 730041 | 1703429 | 1802013 | 540604 | 1261409 | 1900000 | 570000 | 1330000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52792 | 15838 | 36954 | 53000 | 15900 | 37100 | 12861126 | 3858338 | 9002788 | 7607791 | 2282337 | 5325454 | 8413000 | 2523900 | 5889100 | 12861126 | 3858338 | 9002788 | 7607791 | 2282337 | 5325454 | 8413000 | 2523900 | 5889100 | 938470 | 13934 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | CCI | 2013 | Q1 | Q1 - 2013 | 6400083 | 1920025 | 4480058 | 4309252 | 1292775 | 3016477 | 4800000 | 1440000 | 3360000 | 3650203 | 1095061 | 2555142 | 1433266 | 429980 | 1003287 | 1800000 | 540000 | 1260000 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 51346 | 15404 | 35942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 539443 | 161834 | 377610 | 839443 | 251834 | 587609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 75673 | 22702 | 52971 | 75673 | 22702 | 52971 | 2433470 | 730041 | 1703429 | 1959310 | 587793 | 1371517 | 2000000 | 600000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52793 | 15838 | 36954 | 70000 | 21000 | 59000 | 12861126 | 3858338 | 9002788 | 8411083 | 2523326 | 5887758 | 9636462 | 2890940 | 6755522 | 12861126 | 3858338 | 9002788 | 8411083 | 2523326 | 5887758 | 9636462 | 2890940 | 6755522 | 938470 | 31868 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | CCI | 2013 | Q2 | Q2 - 2013 | 6400083 | 1920025 | 4480058 | 4334428 | 1300328 | 3034101 | 4990000 | 1497000 | 3493000 | 3650203 | 1095061 | 2555142 | 1577878 | 473363 | 1104514 | 2100000 | 632100 | 1467900 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 50000 | 15050 | 34950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 654388 | 196317 | 458071 | 700000 | 210700 | 489300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 75673 | 22702 | 52971 | 77500 | 23327 | 54173 | 2433470 | 730041 | 1703429 | 2035014 | 610504 | 1424510 | 2200000 | 662200 | 1537800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52793 | 15838 | 36954 | 52793 | 15838 | 36954 | 12861126 | 3858338 | 9002788 | 8771520 | 2631456 | 6140063 | 10170293 | 3056215 | 7114077 | 12861126 | 3858338 | 9002788 | 8771520 | 2631456 | 6140063 | 10170293 | 3056215 | 7114077 | 938470 | 78893 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | CCI | 2013 | Q3 | Q3 - 2013 | 6400083 | 1920025 | 4480058 | 4424238 | 1327271 | 3096967 | 5421000 | 1626300 | 3794700 | 3650203 | 1095061 | 2555142 | 1912551 | 573765 | 1338786 | 2100000 | 630000 | 1470000 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 50000 | 15050 | 34950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 876900 | 263070 | 613830 | 950000 | 285000 | 665000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 75673 | 22702 | 52971 | 77500 | 23327 | 54173 | 2433470 | 730041 | 1703429 | 2151330 | 645399 | 1505931 | 2300000 | 690000 | 1610000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52793 | 15838 | 36954 | 52793 | 15838 | 36954 | 12861126 | 3858338 | 9002788 | 9534831 | 2860449 | 6674381 | 10951293 | 3285515 | 7665777 | 12861126 | 3858338 | 9002788 | 9534831 | 2860449 | 6674381 | 10951293 | 3285515 | 7665777 | 938470 | 0 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570085 | CCI | 2013 | Q4 | Q4 - 2013 | 6400083 | 1920025 | 4480058 | 4424989 | 1327496 | 3097493 | 4893612 | 1468084 | 3425528 | 3650203 | 1095061 | 2555142 | 2080021 | 624006 | 1456015 | 2400000 | 720000 | 1680000 | 100000 | 30000 | 70000 | 41346 | 12404 | 28942 | 50000 | 15050 | 34950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105370 | 31611 | 73759 | 958230 | 287469 | 670761 | 1000000 | 300000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 24000 | 56000 | 75673 | 22702 | 52971 | 77500 | 23327 | 54173 | 2433470 | 730041 | 1703429 | 2315869 | 694761 | 1621108 | 2400000 | 720000 | 1680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 27600 | 64400 | 52793 | 15838 | 36954 | 77500 | 23327 | 54173 | 12861126 | 3858338 | 9002788 | 9948921 | 2984676 | 6964244 | 10898612 | 3269788 | 7628824 | 12861126 | 3858338 | 9002788 | 9948921 | 2984676 | 6964244 | 10898612 | 3269788 | 7628824 | 938470 | 0 | Vermont Telephone Company, Inc. | TRUE
NT10BIX5570086 | CCI | 2010 | Q4 | Q4 - 2010 | 2751000 | 825300 | 1925700 | 0 | 0 | 0 | 0 | 0 | 0 | 13382331 | 4014699 | 9367632 | 0 | 0 | 0 | 0 | 0 | 0 | 652966 | 195890 | 457076 | 29445 | 29445 | 0 | 59445 | 59445 | 0 | 551505 | 165452 | 386053 | 114813 | 114813 | 0 | 264813 | 264813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384746 | 715424 | 1669322 | 35527 | 35527 | 0 | 75527 | 75527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072060 | 921618 | 2150442 | 0 | 0 | 0 | 0 | 0 | 0 | 1018443 | 305533 | 712910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 57250 | 57250 | 0 | 57250 | 57250 | 0 | 24032051 | 7209616 | 16822435 | 237035 | 237035 | 0 | 457035 | 457035 | 0 | 24032051 | 7209616 | 16822435 | 237035 | 237035 | 0 | 457035 | 457035 | 0 | 0 | 0 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | CCI | 2011 | Q1 | Q1 - 2011 | 2751000 | 825300 | 1925700 | 0 | 0 | 0 | 300000 | 120000 | 180000 | 13382331 | 4014699 | 9367632 | 0 | 0 | 0 | 140000 | 56000 | 84000 | 652966 | 195890 | 457076 | 77414 | 30966 | 46448 | 125000 | 50000 | 75000 | 551505 | 165452 | 386053 | 189257 | 75703 | 113554 | 324000 | 129600 | 194400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384746 | 715424 | 1669322 | 153512 | 61405 | 92107 | 275000 | 110000 | 165000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072060 | 921618 | 2150442 | 228 | 91 | 137 | 228 | 91 | 137 | 1018443 | 305533 | 712910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 57250 | 22900 | 34350 | 57250 | 22900 | 34350 | 24032051 | 7209616 | 16822435 | 477661 | 191065 | 286596 | 1221478 | 488591 | 732887 | 24032051 | 7209616 | 16822435 | 477661 | 191065 | 286596 | 1221478 | 488591 | 732887 | 0 | 0 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | CCI | 2011 | Q2 | Q2 - 2011 | 2751000 | 825300 | 1925700 | 5545 | 1930 | 3615 | 5545 | 1774 | 3771 | 13382331 | 4014699 | 9367632 | 37282 | 12978 | 24304 | 3546607 | 1134914 | 2411693 | 652967 | 195890 | 457077 | 118085 | 41105 | 76980 | 142856 | 45714 | 97142 | 551506 | 165452 | 386054 | 272864 | 94984 | 177880 | 302864 | 96916 | 205948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384746 | 715424 | 1669322 | 336764 | 117228 | 219536 | 521764 | 166964 | 354800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072060 | 921618 | 2150442 | 11415 | 3974 | 7441 | 459368 | 146998 | 312370 | 1018443 | 305533 | 712910 | 0 | 0 | 0 | 45000 | 14400 | 30600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 61719 | 21475 | 40244 | 66719 | 21350 | 45369 | 24032053 | 7209616 | 16822437 | 843674 | 293674 | 550000 | 5090723 | 1629030 | 3461693 | 24032053 | 7209616 | 16822437 | 843674 | 293674 | 550000 | 5090723 | 1629030 | 3461693 | 0 | 0 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | CCI | 2011 | Q3 | Q3 - 2011 | 2751000 | 825300 | 1925700 | 19950 | 5985 | 13965 | 471000 | 141300 | 329700 | 13382331 | 4014699 | 9367632 | 4593994 | 1378198 | 3215796 | 5246380 | 1573914 | 3672466 | 652967 | 195890 | 457077 | 145377 | 43613 | 101764 | 200000 | 60000 | 140000 | 551506 | 165452 | 386054 | 451238 | 135371 | 315867 | 550000 | 165000 | 385000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384746 | 715424 | 1669322 | 485585 | 145676 | 339909 | 961023 | 288307 | 672716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072060 | 921618 | 2150442 | 51719 | 15516 | 36203 | 111719 | 33516 | 78203 | 1018443 | 305533 | 712910 | 41491 | 12447 | 29044 | 51053 | 15316 | 35737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 82347 | 24704 | 57643 | 82347 | 24704 | 57643 | 24032053 | 7209616 | 16822437 | 5871701 | 1761510 | 4110191 | 7673522 | 2302057 | 5371465 | 24032053 | 7209616 | 16822437 | 5871701 | 1761510 | 4110191 | 7673522 | 2302057 | 5371465 | 0 | 0 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | CCI | 2011 | Q4 | Q4 - 2011 | 2751000 | 825300 | 1925700 | 471331 | 141399 | 329932 | 501331 | 150400 | 350931 | 13382331 | 4014699 | 9367632 | 10502690 | 3150807 | 7351883 | 10602693 | 3180808 | 7421885 | 652967 | 195890 | 457077 | 179583 | 53875 | 125708 | 200000 | 60000 | 140000 | 551506 | 165452 | 386054 | 666530 | 199959 | 466571 | 676530 | 202959 | 473571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384746 | 715424 | 1669322 | 574845 | 172454 | 402392 | 624845 | 187454 | 437391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072060 | 921618 | 2150442 | 90850 | 27255 | 63595 | 90850 | 27255 | 63595 | 1018443 | 305533 | 712910 | 205070 | 61521 | 143549 | 225070 | 67521 | 157549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 99614 | 29884 | 69730 | 120000 | 36000 | 84000 | 24032053 | 7209616 | 16822437 | 12790513 | 3837154 | 8953360 | 13041319 | 3912397 | 9128922 | 24032053 | 7209616 | 16822437 | 12790513 | 3837154 | 8953360 | 13041319 | 3912397 | 9128922 | 0 | 0 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | CCI | 2012 | Q1 | Q1 - 2012 | 2751000 | 825300 | 1925700 | 480347 | 144104 | 336243 | 915350 | 274605 | 640745 | 13382331 | 4014699 | 9367632 | 10669475 | 3200842 | 7468633 | 12663557 | 3799067 | 8864490 | 652967 | 195890 | 457077 | 196002 | 58801 | 137201 | 220000 | 66000 | 154000 | 551506 | 165452 | 386054 | 691947 | 207584 | 484363 | 778639 | 233592 | 545047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384746 | 715424 | 1669322 | 698463 | 209539 | 488924 | 865556 | 259667 | 605889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072060 | 921618 | 2150442 | 108604 | 32581 | 76023 | 141903 | 42571 | 99332 | 1018443 | 305533 | 712910 | 114692 | 34408 | 80284 | 155692 | 46708 | 108984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 227896 | 68369 | 159527 | 250000 | 75000 | 175000 | 24032053 | 7209616 | 16822437 | 13187426 | 3956228 | 9231198 | 15990697 | 4797210 | 11193487 | 24032053 | 7209616 | 16822437 | 13187426 | 3956228 | 9231198 | 15990697 | 4797210 | 11193487 | 0 | 0 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | CCI | 2012 | Q2 | Q2 - 2012 | 2751000 | 825300 | 1925700 | 486484 | 145945 | 340539 | 926314 | 277894 | 648420 | 13382331 | 4014699 | 9367632 | 11664422 | 3499327 | 8165095 | 14840894 | 4452268 | 10388626 | 652967 | 195890 | 457077 | 280035 | 84011 | 196024 | 310035 | 93011 | 217024 | 551506 | 165452 | 386054 | 737938 | 221381 | 516557 | 742938 | 222881 | 520057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384746 | 715424 | 1669322 | 809358 | 242807 | 566551 | 1029358 | 308807 | 720551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072060 | 921618 | 2150442 | 162955 | 48886 | 114069 | 207331 | 62199 | 145132 | 1018443 | 305533 | 712910 | 135829 | 40749 | 95080 | 185829 | 55749 | 130080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 166415 | 49925 | 116490 | 166415 | 49925 | 116490 | 24032053 | 7209616 | 16822437 | 14443436 | 4333031 | 10110405 | 18409114 | 5522734 | 12886380 | 24032053 | 7209616 | 16822437 | 14443436 | 4333031 | 10110405 | 18409114 | 5522734 | 12886380 | 0 | 0 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | CCI | 2012 | Q3 | Q3 - 2012 | 1905514 | 571654 | 1333860 | 923588 | 277076 | 646512 | 963588 | 289076 | 674512 | 17963245 | 5388973 | 12574272 | 14921116 | 4476335 | 10444781 | 16484656 | 4945397 | 11539259 | 652967 | 195890 | 457077 | 317421 | 95226 | 222195 | 367421 | 110226 | 257195 | 808259 | 242478 | 565781 | 763611 | 229083 | 534528 | 763611 | 229083 | 534528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500796 | 450239 | 1050557 | 915242 | 274573 | 640669 | 1011142 | 303343 | 707799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270801 | 81240 | 189561 | 221493 | 66448 | 155045 | 244698 | 73409 | 171289 | 767106 | 230132 | 536974 | 153834 | 46150 | 107684 | 193834 | 58150 | 135684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163365 | 49010 | 114355 | 163302 | 48990 | 114312 | 163302 | 48990 | 114312 | 24032053 | 7209616 | 16822437 | 18379607 | 5513881 | 12865726 | 20192252 | 6057674 | 14134578 | 24032053 | 7209616 | 16822437 | 18379607 | 5513881 | 12865726 | 20192252 | 6057674 | 14134578 | 0 | 690 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | CCI | 2012 | Q4 | Q4 - 2012 | 1905514 | 571654 | 1333860 | 950636 | 285191 | 665445 | 1142636 | 342791 | 799845 | 17963245 | 5388973 | 12574272 | 16270681 | 4881204 | 11389477 | 16275681 | 4882704 | 11392977 | 652967 | 195890 | 457077 | 349851 | 104955 | 244896 | 399851 | 119955 | 279896 | 808259 | 242478 | 565781 | 758595 | 227579 | 531016 | 758595 | 227579 | 531016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500796 | 450239 | 1050557 | 977508 | 293252 | 684256 | 1035508 | 310652 | 724856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270801 | 81240 | 189561 | 261467 | 78440 | 183027 | 267967 | 80390 | 187577 | 767106 | 230132 | 536974 | 236867 | 71060 | 165807 | 256867 | 77060 | 179807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163365 | 49010 | 114355 | 163302 | 48990 | 114312 | 163302 | 48990 | 114312 | 24032053 | 7209616 | 16822437 | 19968907 | 5990671 | 13978236 | 20300407 | 6090121 | 14210286 | 24032053 | 7209616 | 16822437 | 19968907 | 5990671 | 13978236 | 20300407 | 6090121 | 14210286 | 0 | 69457 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | CCI | 2013 | Q1 | Q1 - 2013 | 1905514 | 571654 | 1333860 | 1026017 | 307805 | 718212 | 1264016 | 379205 | 884811 | 17963245 | 5388973 | 12574272 | 16243330 | 4872999 | 11370331 | 17131164 | 5139349 | 11991815 | 652967 | 195890 | 457077 | 373430 | 112030 | 261400 | 413430 | 124029 | 289401 | 808259 | 242478 | 565781 | 806511 | 241953 | 564558 | 814101 | 244230 | 569871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500796 | 450239 | 1050557 | 1049381 | 314814 | 734567 | 1156813 | 347044 | 809769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270801 | 81240 | 189561 | 263319 | 78996 | 184323 | 268231 | 80469 | 187762 | 767106 | 230132 | 536974 | 294542 | 88363 | 206179 | 333542 | 100063 | 233479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163365 | 49010 | 114355 | 163302 | 48990 | 114312 | 163302 | 48990 | 114312 | 24032053 | 7209616 | 16822437 | 20219832 | 6065950 | 14153882 | 21544599 | 6463379 | 15081220 | 24032053 | 7209616 | 16822437 | 20219832 | 6065950 | 14153882 | 21544599 | 6463379 | 15081220 | 0 | 221296 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | CCI | 2013 | Q2 | Q2 - 2013 | 1905514 | 571654 | 1333860 | 1348246 | 404474 | 943772 | 1350999 | 405300 | 945699 | 17963245 | 5388973 | 12574272 | 16218556 | 4865567 | 11352989 | 16770000 | 5031000 | 11739000 | 652967 | 195890 | 457077 | 399658 | 119897 | 279761 | 480000 | 144000 | 336000 | 808259 | 242478 | 565781 | 811415 | 243424 | 567991 | 814000 | 244200 | 569800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500796 | 450239 | 1050557 | 1101935 | 330580 | 771355 | 1163000 | 348900 | 814100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270801 | 81240 | 189561 | 277375 | 83212 | 194163 | 281000 | 84300 | 196700 | 767106 | 230132 | 536974 | 312482 | 93745 | 218737 | 325489 | 97647 | 227842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163365 | 49010 | 114355 | 163302 | 48990 | 114312 | 163302 | 48990 | 114312 | 24032053 | 7209616 | 16822437 | 20632969 | 6189889 | 14443080 | 21347790 | 6404337 | 14943453 | 24032053 | 7209616 | 16822437 | 20632969 | 6189889 | 14443080 | 21347790 | 6404337 | 14943453 | 0 | 496466 | Enventis Telecom, Inc. | TRUE
NT10BIX5570086 | CCI | 2013 | Q3 | Q3 - 2013 | 1905514 | 571654 | 1333860 | 1305748 | 391724 | 914024 | 1305748 | 391724 | 914024 | 17963245 | 5388973 | 12574272 | 16146089 | 4843827 | 11302262 | 16146089 | 4843827 | 11302262 | 652967 | 195890 | 457077 | 432046 | 129614 | 302432 | 432046 | 129614 | 302432 | 808259 | 242478 | 565781 | 829339 | 248802 | 580537 | 829339 | 248802 | 580537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500796 | 450239 | 1050557 | 1148548 | 344564 | 803984 | 1148548 | 344564 | 803984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270801 | 81240 | 189561 | 295420 | 88626 | 206794 | 295420 | 88626 | 206794 | 767106 | 230132 | 536974 | 775038 | 232511 | 542527 | 775038 | 232511 | 542527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163365 | 49010 | 114355 | 163407 | 49022 | 114385 | 163407 | 49022 | 114385 | 24032053 | 7209616 | 16822437 | 21095635 | 6328690 | 14766945 | 21095635 | 6328690 | 14766945 | 24032053 | 7209616 | 16822437 | 21095635 | 6328690 | 14766945 | 21095635 | 6328690 | 14766945 | 0 | 562802 | Enventis Telecom, Inc. | TRUE
NT10BIX5570087 | CCI | 2010 | Q4 | Q4 - 2010 | 2937139 | 587428 | 2349711 | 307 | 0 | 0 | 160000 | 160000 | 0 | 8260120 | 1652024 | 6608096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332000 | 66400 | 265600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 159960 | 639840 | 14686 | 0 | 15815 | 200465 | 0 | 200465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 14993 | 0 | 15815 | 360465 | 160000 | 200465 | 12529059 | 2505812 | 10023247 | 14993 | 0 | 15815 | 360465 | 160000 | 200465 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | CCI | 2011 | Q1 | Q1 - 2011 | 2937139 | 587428 | 2349711 | 307 | 0 | 307 | 85000 | 85000 | 0 | 8260120 | 1652024 | 6608096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332000 | 66400 | 265600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 159960 | 639840 | 48646 | 0 | 48646 | 380646 | 0 | 380646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 48953 | 0 | 48953 | 465646 | 85000 | 380646 | 12529059 | 2505812 | 10023247 | 48953 | 0 | 48953 | 465646 | 85000 | 380646 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | CCI | 2011 | Q2 | Q2 - 2011 | 2937139 | 587428 | 2349711 | 175386 | 175386 | 0 | 275386 | 275386 | 0 | 8260120 | 1652024 | 6608096 | 0 | 0 | 0 | 240000 | 0 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332000 | 66400 | 265600 | 0 | 0 | 0 | 24000 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 159960 | 639840 | 432745 | 258580 | 174165 | 567050 | 406046 | 161004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 608131 | 433966 | 174165 | 1166436 | 921432 | 461004 | 12529059 | 2505812 | 10023247 | 608131 | 433966 | 174165 | 1166436 | 921432 | 461004 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | CCI | 2011 | Q3 | Q3 - 2011 | 2937139 | 587428 | 2349711 | 436807 | 105047 | 331760 | 2900000 | 600000 | 2300000 | 8260120 | 1652024 | 6608096 | 0 | 0 | 0 | 557000 | 112000 | 445000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332000 | 66400 | 265600 | 0 | 0 | 0 | 240000 | 48000 | 192000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 159960 | 639840 | 501642 | 329223 | 172419 | 582487 | 329223 | 253264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 40000 | 8000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 938449 | 434270 | 504179 | 4319487 | 1097223 | 3222264 | 12529059 | 2505812 | 10023247 | 938449 | 434270 | 504179 | 4319487 | 1097223 | 3222264 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | CCI | 2011 | Q4 | Q4 - 2011 | 2937139 | 587428 | 2349711 | 2926669 | 620528 | 2306141 | 2941669 | 635528 | 2306141 | 8260120 | 1652024 | 6608096 | 1528971 | 62111 | 1466860 | 2178971 | 312111 | 1866860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332000 | 66400 | 265600 | 238638 | 47728 | 190910 | 248138 | 47228 | 200910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 159960 | 639840 | 592124 | 339104 | 253020 | 717124 | 364105 | 353020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 125000 | 25000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 5286402 | 1069471 | 4216931 | 6210902 | 1383972 | 4826931 | 12529059 | 2505812 | 10023247 | 5286402 | 1069471 | 4216931 | 6210902 | 1383972 | 4826931 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | CCI | 2012 | Q1 | Q1 - 2012 | 3760076 | 630000 | 3130076 | 2945075 | 622782 | 2322293 | 3022782 | 622782 | 2400000 | 5862934 | 1393441 | 4469493 | 1770954 | 115775 | 1655179 | 2850954 | 358998 | 2491956 | 630000 | 1971 | 628029 | 91470 | 1972 | 89498 | 173988 | 1972 | 172016 | 603637 | 66400 | 537237 | 355873 | 50474 | 305399 | 361384 | 50474 | 310910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 352000 | 447800 | 448557 | 342332 | 106225 | 530321 | 342332 | 187989 | 298012 | 22000 | 276012 | 178012 | 21764 | 156248 | 208012 | 21764 | 186248 | 154000 | 0 | 154000 | 24991 | 0 | 24991 | 32991 | 0 | 32991 | 420000 | 40000 | 380000 | 0 | 0 | 0 | 120000 | 40000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12528459 | 2505812 | 10022647 | 5814932 | 1155099 | 4659833 | 7300432 | 1438322 | 5862110 | 12528459 | 2505812 | 10022647 | 5814932 | 1155099 | 4659833 | 7300432 | 1438322 | 5862110 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | CCI | 2012 | Q2 | Q2 - 2012 | 3760076 | 630000 | 3130076 | 2945132 | 622782 | 2322350 | 3352350 | 630000 | 2722350 | 5862934 | 1393441 | 4469493 | 2733661 | 475170 | 2258491 | 3693544 | 875170 | 2818374 | 630000 | 1971 | 628029 | 106557 | 1971 | 104586 | 136557 | 1971 | 134586 | 603637 | 66400 | 537237 | 241337 | 48502 | 192835 | 381336 | 58501 | 322835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 352000 | 447800 | 449883 | 343022 | 106861 | 489883 | 343022 | 146861 | 298012 | 22000 | 276012 | 180101 | 21764 | 158337 | 210101 | 21764 | 188337 | 154000 | 0 | 154000 | 40695 | 0 | 40695 | 52695 | 0 | 52695 | 420000 | 40000 | 380000 | 0 | 0 | 0 | 120000 | 40000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12528459 | 2505812 | 10022647 | 6697366 | 1513211 | 5184155 | 8436466 | 1970428 | 6466038 | 12528459 | 2505812 | 10022647 | 6697366 | 1513211 | 5184155 | 8436466 | 1970428 | 6466038 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | CCI | 2012 | Q3 | Q3 - 2012 | 3760076 | 630000 | 3130076 | 3011465 | 622782 | 2388683 | 3111465 | 622782 | 2488683 | 5862934 | 1393441 | 4470093 | 3853815 | 523955 | 3329860 | 5053815 | 723955 | 4329860 | 630000 | 1971 | 628029 | 118271 | 1971 | 116300 | 198271 | 1971 | 196300 | 603637 | 66400 | 537237 | 246278 | 48502 | 197776 | 446278 | 48502 | 397776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 352000 | 447800 | 493966 | 349793 | 144173 | 553966 | 349793 | 204173 | 298012 | 22000 | 276012 | 180101 | 21764 | 158337 | 205101 | 21764 | 183337 | 154000 | 0 | 154000 | 58044 | 0 | 58044 | 70044 | 0 | 70044 | 420000 | 40000 | 380000 | 48789 | 0 | 48789 | 198789 | 150000 | 48789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12528459 | 2505812 | 10023247 | 8010729 | 1568767 | 6441962 | 9837729 | 1918767 | 7918962 | 12528459 | 2505812 | 10023247 | 8010729 | 1568767 | 6441962 | 9837729 | 1918767 | 7918962 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | CCI | 2012 | Q4 | Q4 - 2012 | 3760076 | 630000 | 3130076 | 2932392 | 606819 | 2325573 | 3232392 | 606819 | 2625573 | 5862934 | 1393441 | 4470093 | 4273160 | 614124 | 3659036 | 4473159 | 814124 | 3659035 | 630000 | 1971 | 628029 | 125972 | 1971 | 124001 | 191972 | 1971 | 190001 | 603637 | 66400 | 537237 | 333704 | 64466 | 269238 | 343704 | 64466 | 279238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 352000 | 447800 | 520207 | 349793 | 170414 | 570207 | 349793 | 220414 | 298012 | 22000 | 276012 | 196178 | 21764 | 174414 | 226178 | 21764 | 204414 | 154000 | 0 | 154000 | 76876 | 0 | 76876 | 88876 | 0 | 88876 | 420000 | 40000 | 380000 | 97575 | 48786 | 48789 | 207575 | 20000 | 187575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12528459 | 2505812 | 10023247 | 8556064 | 1707723 | 6848341 | 9334063 | 1878937 | 7455126 | 12528459 | 2505812 | 10023247 | 8556064 | 1707723 | 6848341 | 9334063 | 1878937 | 7455126 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | CCI | 2013 | Q1 | Q1 - 2013 | 3760076 | 630000 | 3130076 | 2949996 | 620950 | 2329046 | 3559046 | 630000 | 2929046 | 5863534 | 1393441 | 4470093 | 4571186 | 685994 | 3885192 | 5770935 | 1344373 | 4426562 | 630000 | 1971 | 628029 | 144632 | 1971 | 142661 | 174883 | 1971 | 172912 | 603637 | 66400 | 537237 | 340074 | 65486 | 274588 | 347074 | 65486 | 281588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 352000 | 447800 | 553553 | 350489 | 203064 | 603553 | 350489 | 253064 | 298012 | 22000 | 276012 | 196178 | 21764 | 174414 | 226178 | 21764 | 204414 | 154000 | 0 | 154000 | 88876 | 0 | 88876 | 100876 | 0 | 100876 | 420000 | 40000 | 380000 | 167870 | 48786 | 119084 | 256656 | 48786 | 207870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 9012365 | 1795440 | 7216925 | 11039201 | 2462869 | 8576332 | 12529059 | 2505812 | 10023247 | 9012365 | 1795440 | 7216925 | 11039201 | 2462869 | 8576332 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | CCI | 2013 | Q2 | Q2 - 2013 | 3760076 | 630000 | 3130076 | 2987320 | 624020 | 2363300 | 3184024 | 624020 | 2560004 | 5863534 | 1393441 | 4470093 | 5002388 | 985910 | 4016478 | 5786659 | 1060910 | 4725749 | 630000 | 1971 | 628029 | 168992 | 1971 | 167021 | 259127 | 1971 | 257156 | 603637 | 66400 | 537237 | 343888 | 66341 | 277547 | 343888 | 66340 | 277548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 352000 | 447800 | 566964 | 350489 | 216475 | 597904 | 350489 | 247415 | 298012 | 22000 | 276012 | 204471 | 21764 | 182707 | 204471 | 21764 | 182707 | 154000 | 0 | 154000 | 90701 | 0 | 90701 | 96871 | 0 | 96871 | 420000 | 40000 | 380000 | 167870 | 0 | 167870 | 267870 | 0 | 267870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 9532594 | 2050495 | 7482099 | 10740814 | 2125494 | 8615320 | 12529059 | 2505812 | 10023247 | 9532594 | 2050495 | 7482099 | 10740814 | 2125494 | 8615320 | 0 | 0 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570087 | CCI | 2013 | Q3 | Q3 - 2013 | 3760076 | 630000 | 3130076 | 3355545 | 655442 | 2700103 | 3355545 | 655442 | 2700103 | 5863534 | 1393441 | 4470093 | 5833983 | 1090234 | 4743749 | 5833983 | 1090234 | 4743749 | 630000 | 1971 | 628029 | 243478 | 4387 | 239092 | 243478 | 4387 | 239092 | 603637 | 66400 | 537237 | 340988 | 66341 | 274647 | 340988 | 66341 | 274647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799800 | 352000 | 447800 | 608161 | 350489 | 257672 | 608161 | 350489 | 257672 | 298012 | 22000 | 276012 | 204471 | 21764 | 182707 | 204471 | 21764 | 182707 | 154000 | 0 | 154000 | 93000 | 0 | 93000 | 93000 | 0 | 93000 | 420000 | 40000 | 380000 | 168076 | 0 | 168076 | 168076 | 0 | 168076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12529059 | 2505812 | 10023247 | 10847702 | 2188657 | 8659046 | 10847702 | 2188657 | 8659046 | 12529059 | 2505812 | 10023247 | 10847702 | 2188657 | 8659046 | 10847702 | 2188657 | 8659046 | 0 | 6616 | Mid-Atlantic Broadband Cooperative | TRUE
NT10BIX5570088 | CCI | 2010 | Q4 | Q4 - 2010 | 15239990 | 0 | 15239990 | 0 | 0 | 0 | 0 | 0 | 0 | 1176000 | 0 | 1176000 | 0 | 0 | 0 | 0 | 0 | 0 | 37291 | 37291 | 0 | 17900 | 17900 | 0 | 32000 | 32000 | 0 | 4077000 | 4077000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275662 | 275662 | 0 | 44399 | 44399 | 0 | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286500 | 0 | 286500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389953 | 16702490 | 62299 | 62299 | 0 | 112000 | 112000 | 0 | 21092443 | 4389953 | 16702490 | 62299 | 62299 | 0 | 112000 | 112000 | 0 | 0 | 0 | Charlotte, City of | TRUE
NT10BIX5570088 | CCI | 2011 | Q1 | Q1 - 2011 | 15239990 | 0 | 15239990 | 0 | 0 | 0 | 0 | 0 | 0 | 1176000 | 0 | 1176000 | 0 | 0 | 0 | 0 | 0 | 0 | 37291 | 37291 | 0 | 26240 | 26240 | 0 | 32240 | 32240 | 0 | 4077000 | 4077000 | 0 | 14523 | 14523 | 0 | 84523 | 84523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275662 | 275662 | 0 | 82037 | 82037 | 0 | 117037 | 117037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286500 | 0 | 286500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389953 | 16702490 | 122800 | 122800 | 0 | 233800 | 233800 | 0 | 21092443 | 4389953 | 16702490 | 122800 | 122800 | 0 | 233800 | 233800 | 0 | 0 | 0 | Charlotte, City of | TRUE
NT10BIX5570088 | CCI | 2011 | Q2 | Q2 - 2011 | 15239990 | 0 | 15239990 | 0 | 0 | 0 | 0 | 0 | 0 | 1176000 | 0 | 1176000 | 0 | 0 | 0 | 0 | 0 | 0 | 37291 | 37291 | 0 | 60772 | 60772 | 0 | 98738 | 98738 | 0 | 4077000 | 4077000 | 0 | 27111 | 27111 | 0 | 94229 | 94229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275662 | 275662 | 0 | 117796 | 117796 | 0 | 167796 | 167796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286500 | 0 | 286500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389953 | 16702490 | 205679 | 205679 | 0 | 360763 | 360763 | 0 | 21092443 | 4389953 | 16702490 | 205679 | 205679 | 0 | 360763 | 360763 | 0 | 0 | 0 | Charlotte, City of | TRUE
NT10BIX5570088 | CCI | 2011 | Q3 | Q3 - 2011 | 15239990 | 0 | 15239990 | 0 | 0 | 0 | 1906642 | 0 | 1906642 | 1176000 | 0 | 1176000 | 0 | 0 | 0 | 0 | 0 | 0 | 37291 | 37291 | 0 | 100754 | 100754 | 0 | 171633 | 171633 | 0 | 4077000 | 4077000 | 0 | 44774 | 44774 | 0 | 119227 | 119227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275662 | 275662 | 0 | 162343 | 162343 | 0 | 192343 | 192343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286500 | 0 | 286500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389953 | 16702490 | 307871 | 307871 | 0 | 2389845 | 483203 | 1906642 | 21092443 | 4389953 | 16702490 | 307871 | 307871 | 0 | 2389845 | 483203 | 1906642 | 0 | 0 | Charlotte, City of | TRUE
NT10BIX5570088 | CCI | 2011 | Q4 | Q4 - 2011 | 9576630 | 3400195 | 6176435 | 0 | 0 | 0 | 1271095 | 0 | 1271095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 380005 | 289193 | 90812 | 622016 | 334343 | 287673 | 2123797 | 520159 | 1603638 | 318953 | 318953 | 0 | 697590 | 318953 | 378637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 41312 | 0 | 41312 | 482648 | 0 | 482648 | 920857 | 0 | 920857 | 0 | 0 | 0 | 828113 | 0 | 828113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 0 | 0 | 0 | 354370 | 0 | 354370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389954 | 16702489 | 740270 | 608146 | 132124 | 4255832 | 653296 | 3602536 | 21092443 | 4389954 | 16702489 | 740270 | 608146 | 132124 | 4255832 | 653296 | 3602536 | 0 | 0 | Charlotte, City of | TRUE
NT10BIX5570088 | CCI | 2012 | Q1 | Q1 - 2012 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 1382495 | 0 | 1382495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 643476 | 367801 | 275674 | 834688 | 429801 | 404887 | 2123797 | 520159 | 1603638 | 697590 | 318953 | 378637 | 806090 | 318953 | 487137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 417603 | 0 | 417603 | 417603 | 0 | 417603 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 874485 | 0 | 874485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 236638 | 0 | 236638 | 1561638 | 0 | 1561638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 122582 | 0 | 122582 | 21092443 | 4389954 | 16702489 | 4094516 | 686754 | 3407761 | 5999581 | 748754 | 5250827 | 21092443 | 4389954 | 16702489 | 4094516 | 686754 | 3407761 | 5999581 | 748754 | 5250827 | 0 | 0 | Charlotte, City of | TRUE
NT10BIX5570088 | CCI | 2012 | Q2 | Q2 - 2012 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 1271095 | 0 | 1271095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 772607 | 433489 | 339118 | 841000 | 471000 | 370000 | 2123797 | 520159 | 1603638 | 781743 | 318953 | 462790 | 812101 | 318953 | 492257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 460945 | 0 | 460945 | 460945 | 0 | 460945 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 828114 | 0 | 828114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 380696 | 0 | 380696 | 380696 | 0 | 380696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389954 | 16702489 | 4495200 | 752442 | 3742758 | 4593951 | 789953 | 3803107 | 21092443 | 4389954 | 16702489 | 4495200 | 752442 | 3742758 | 4593951 | 789953 | 3803107 | 0 | 0 | Charlotte, City of | TRUE
NT10BIX5570088 | CCI | 2012 | Q3 | Q3 - 2012 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 1271095 | 0 | 1271095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 846300 | 468931 | 377369 | 912000 | 497000 | 415000 | 2123797 | 520159 | 1603638 | 843172 | 318953 | 524219 | 904601 | 318953 | 585648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 460945 | 0 | 460945 | 460945 | 0 | 460945 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 828114 | 0 | 828114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 380696 | 0 | 380696 | 380696 | 0 | 380696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389954 | 16702489 | 4630322 | 787884 | 3842438 | 4757451 | 815953 | 3941498 | 21092443 | 4389954 | 16702489 | 4630322 | 787884 | 3842438 | 4757451 | 815953 | 3941498 | 0 | 0 | Charlotte, City of | TRUE
NT10BIX5570088 | CCI | 2012 | Q4 | Q4 - 2012 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 1271095 | 0 | 1271095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 909312 | 501480 | 407832 | 979000 | 536000 | 443000 | 2123797 | 520159 | 1603638 | 921527 | 318953 | 602574 | 1020953 | 318953 | 702000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 460945 | 0 | 460945 | 460945 | 0 | 460945 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 828114 | 0 | 828114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 380696 | 0 | 380696 | 380696 | 0 | 380696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389954 | 16702489 | 4771689 | 820433 | 3951256 | 4940803 | 854953 | 4085850 | 21092443 | 4389954 | 16702489 | 4771689 | 820433 | 3951256 | 4940803 | 854953 | 4085850 | 0 | 0 | Charlotte, City of | TRUE
NT10BIX5570088 | CCI | 2013 | Q1 | Q1 - 2013 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 1271095 | 0 | 1271095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 984109 | 533019 | 451090 | 1064109 | 568019 | 496090 | 2123797 | 520159 | 1603638 | 1201580 | 529062 | 672517 | 1301579 | 529062 | 772517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 460945 | 0 | 460945 | 460945 | 0 | 460945 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 828114 | 0 | 828114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 380696 | 0 | 380696 | 380696 | 0 | 380696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389954 | 16702489 | 5126539 | 1062081 | 4064457 | 5306538 | 1097081 | 4209457 | 21092443 | 4389954 | 16702489 | 5126539 | 1062081 | 4064457 | 5306538 | 1097081 | 4209457 | 0 | 0 | Charlotte, City of | TRUE
NT10BIX5570088 | CCI | 2013 | Q2 | Q2 - 2013 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 1271095 | 0 | 1271095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 1093191 | 581435 | 511756 | 1205979 | 602223 | 603756 | 2123797 | 520159 | 1603638 | 1252877 | 529062 | 723815 | 1304175 | 529062 | 775113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 460945 | 0 | 460945 | 460945 | 0 | 460945 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 828114 | 0 | 828114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 380696 | 0 | 380696 | 380696 | 0 | 380696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389954 | 16702489 | 5286918 | 1110497 | 4176421 | 5451004 | 1131285 | 4319719 | 21092443 | 4389954 | 16702489 | 5286918 | 1110497 | 4176421 | 5451004 | 1131285 | 4319719 | 0 | 0 | Charlotte, City of | TRUE
NT10BIX5570088 | CCI | 2013 | Q3 | Q3 - 2013 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 1271095 | 0 | 1271095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 1182144 | 603254 | 578889 | 1253890 | 625000 | 628890 | 2123797 | 520159 | 1603638 | 1377729 | 583690 | 794039 | 1383690 | 583690 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 460945 | 0 | 460945 | 460945 | 0 | 460945 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 828114 | 0 | 828114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 380696 | 0 | 380696 | 380696 | 0 | 380696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 0 | 0 | 0 | 21092443 | 4389954 | 16702489 | 5500723 | 1186944 | 4313778 | 5578430 | 1208690 | 4369740 | 21092443 | 4389954 | 16702489 | 5500723 | 1186944 | 4313778 | 5578430 | 1208690 | 4369740 | 0 | 0 | Charlotte, City of | TRUE
NT10BIX5570088 | CCI | 2013 | Q4 | Q4 - 2013 | 9576630 | 3400195 | 6176435 | 1271095 | 0 | 1271095 | 2388937 | 769751 | 1619186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284094 | 469600 | 814494 | 1266065 | 623294 | 642771 | 1645822 | 633000 | 1012822 | 2123797 | 520159 | 1603638 | 1048759 | 583690 | 465069 | 1380142 | 583690 | 796452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859911 | 0 | 859911 | 495775 | 0 | 495775 | 524836 | 0 | 524836 | 920857 | 0 | 920857 | 828114 | 0 | 828114 | 920857 | 0 | 920857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5990044 | 0 | 5990044 | 380695 | 0 | 380695 | 2826170 | 0 | 2826170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337110 | 0 | 337110 | 0 | 0 | 0 | 170607 | 0 | 170607 | 21092443 | 4389954 | 16702489 | 5290503 | 1206984 | 4083519 | 9857371 | 1986441 | 7870930 | 21092443 | 4389954 | 16702489 | 5290503 | 1206984 | 4083519 | 9857371 | 1986441 | 7870930 | 0 | 0 | Charlotte, City of | TRUE
NT10BIX5570089 | CCI | 2010 | Q4 | Q4 - 2010 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 342000 | 103000 | 239000 | 642000 | 194000 | 448000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 0 | 0 | 0 | 265000 | 80000 | 185000 | 3362099 | 1319009 | 2043090 | 139000 | 42000 | 97000 | 353000 | 107000 | 246000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 5000 | 11000 | 73000 | 22000 | 51000 | 72483637 | 21890086 | 50593551 | 497000 | 150000 | 347000 | 1333000 | 403000 | 930000 | 72483637 | 21890086 | 50593551 | 497000 | 150000 | 347000 | 1333000 | 403000 | 930000 | 0 | 0 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | CCI | 2011 | Q1 | Q1 - 2011 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 549000 | 166000 | 383000 | 574000 | 173000 | 401000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 157000 | 47000 | 110000 | 537000 | 162000 | 375000 | 3362099 | 1319009 | 2043090 | 263000 | 79000 | 184000 | 531000 | 161000 | 370000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 16000 | 35000 | 127000 | 38000 | 89000 | 72483637 | 21890086 | 50593551 | 1020000 | 308000 | 712000 | 1769000 | 534000 | 1235000 | 72483637 | 21890086 | 50593551 | 1020000 | 308000 | 712000 | 1769000 | 534000 | 1235000 | 0 | 0 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | CCI | 2011 | Q2 | Q2 - 2011 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 549000 | 166000 | 383000 | 574000 | 173000 | 401000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 187000 | 57000 | 130000 | 1247000 | 377000 | 870000 | 3362099 | 1319009 | 2043090 | 494000 | 149000 | 345000 | 725000 | 219000 | 506000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103000 | 31000 | 72000 | 180000 | 54000 | 126000 | 72483637 | 21890086 | 50593551 | 1333000 | 403000 | 930000 | 2726000 | 823000 | 1903000 | 72483637 | 21890086 | 50593551 | 1333000 | 403000 | 930000 | 2726000 | 823000 | 1903000 | 0 | 0 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | CCI | 2011 | Q3 | Q3 - 2011 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 549000 | 166000 | 383000 | 694000 | 210000 | 484000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 483000 | 146000 | 337000 | 1228000 | 371000 | 857000 | 3362099 | 1319009 | 2043090 | 431000 | 130000 | 301000 | 579000 | 175000 | 404000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 51000 | 119000 | 266000 | 80000 | 186000 | 72483637 | 21890086 | 50593551 | 1633000 | 493000 | 1140000 | 2767000 | 836000 | 1931000 | 72483637 | 21890086 | 50593551 | 1633000 | 493000 | 1140000 | 2767000 | 836000 | 1931000 | 0 | 0 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | CCI | 2011 | Q4 | Q4 - 2011 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 708276 | 213899 | 494377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 868864 | 262397 | 606467 | 2090435 | 631311 | 1459124 | 3362099 | 1319009 | 2043090 | 574802 | 173590 | 401212 | 749602 | 226380 | 523222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251881 | 76068 | 175813 | 364514 | 110083 | 254431 | 72483637 | 21890086 | 50593551 | 2378823 | 718404 | 1660419 | 3912827 | 1181673 | 2731154 | 72483637 | 21890086 | 50593551 | 2378823 | 718404 | 1660419 | 3912827 | 1181673 | 2731154 | 0 | 0 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | CCI | 2012 | Q1 | Q1 - 2012 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 708276 | 213899 | 494377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 1260422 | 380647 | 879775 | 2237282 | 675659 | 1561623 | 3362099 | 1319009 | 2043090 | 773370 | 233559 | 539811 | 948170 | 286347 | 661823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322607 | 97427 | 225180 | 401457 | 121240 | 280217 | 72483637 | 21890086 | 50593551 | 3039675 | 917982 | 2121693 | 4295185 | 1297145 | 2998040 | 72483637 | 21890086 | 50593551 | 3039675 | 917982 | 2121693 | 4295185 | 1297145 | 2998040 | 0 | 0 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | CCI | 2012 | Q2 | Q2 - 2012 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 683279 | 206349 | 476927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 2119863 | 640199 | 1479664 | 2733090 | 825393 | 1907697 | 3362099 | 1319009 | 2043090 | 1014178 | 306282 | 707896 | 1314178 | 396882 | 917296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392200 | 118444 | 273756 | 460919 | 139198 | 321721 | 72483637 | 21890086 | 50593551 | 4209517 | 1271274 | 2938243 | 5191466 | 1567822 | 3623641 | 72483637 | 21890086 | 50593551 | 4209517 | 1271274 | 2938243 | 5191466 | 1567822 | 3623641 | 0 | 0 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | CCI | 2012 | Q3 | Q3 - 2012 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 693276 | 209369 | 483907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 2778334 | 839057 | 1939277 | 3340800 | 1008922 | 2331878 | 3362099 | 1319009 | 2043090 | 1223655 | 369544 | 854111 | 1420002 | 428841 | 991161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521856 | 157601 | 364255 | 577256 | 174331 | 402925 | 72483637 | 21890086 | 50593551 | 5207121 | 1572551 | 3634570 | 6031334 | 1821463 | 4209871 | 72483637 | 21890086 | 50593551 | 5207121 | 1572551 | 3634570 | 6031334 | 1821463 | 4209871 | 0 | 0 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | CCI | 2012 | Q4 | Q4 - 2012 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 683276 | 206349 | 476927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 3711826 | 1120971 | 2590855 | 3869026 | 1168446 | 2700580 | 3362099 | 1319009 | 2043090 | 1405085 | 424336 | 980749 | 1606898 | 485283 | 1121615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 569142 | 171881 | 397261 | 591490 | 178630 | 412860 | 72483637 | 21890086 | 50593551 | 6369329 | 1923537 | 4445792 | 6750690 | 2038708 | 4711982 | 72483637 | 21890086 | 50593551 | 6369329 | 1923537 | 4445792 | 6750690 | 2038708 | 4711982 | 0 | 0 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | CCI | 2013 | Q1 | Q1 - 2013 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 683276 | 206349 | 476927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 3817045 | 1152747 | 2664298 | 3974245 | 1200222 | 2774023 | 3362099 | 1319009 | 2043090 | 1598031 | 482606 | 1115425 | 1799844 | 543553 | 1256291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580875 | 175425 | 405451 | 589142 | 177921 | 411221 | 72483637 | 21890086 | 50593551 | 6679227 | 2017127 | 4662101 | 7046507 | 2128045 | 4918462 | 72483637 | 21890086 | 50593551 | 6679227 | 2017127 | 4662101 | 7046507 | 2128045 | 4918462 | 0 | 0 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | CCI | 2013 | Q2 | Q2 - 2013 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 703276 | 212389 | 490887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 3979169 | 1201709 | 2777460 | 4298769 | 1298228 | 3000541 | 3362099 | 1319009 | 2043090 | 1750555 | 528668 | 1221887 | 1938105 | 585308 | 1352797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578419 | 174683 | 403736 | 602349 | 181909 | 420440 | 72483637 | 21890086 | 50593551 | 6991419 | 2111409 | 4880010 | 7542499 | 2277834 | 5264665 | 72483637 | 21890086 | 50593551 | 6991419 | 2111409 | 4880010 | 7542499 | 2277834 | 5264665 | 0 | 0 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | CCI | 2013 | Q3 | Q3 - 2013 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 683276 | 206349 | 476927 | 794901 | 240060 | 554841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 4174577 | 1260722 | 2913855 | 4758577 | 1437090 | 3321487 | 3362099 | 1319009 | 2043090 | 2009317 | 606814 | 1402503 | 2199317 | 664194 | 1535123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486598 | 146953 | 339645 | 510501 | 154171 | 356330 | 72483637 | 21890086 | 50593551 | 7353768 | 2220838 | 5132930 | 8263296 | 2495515 | 5767781 | 72483637 | 21890086 | 50593551 | 7353768 | 2220838 | 5132930 | 8263296 | 2495515 | 5767781 | 0 | 0 | Motorola Solutions, Inc. | TRUE
NT10BIX5570089 | CCI | 2013 | Q4 | Q4 - 2013 | 44668046 | 10877290 | 33790756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 165000 | 0 | 808101 | 244046 | 564055 | 808101 | 244046 | 564055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24288492 | 9528787 | 14759705 | 5003818 | 1511154 | 3492664 | 5003818 | 1511154 | 3492664 | 3362099 | 1319009 | 2043090 | 2247933 | 678876 | 1569057 | 2247933 | 678876 | 1569057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455286 | 137496 | 317790 | 455286 | 137496 | 317790 | 72483637 | 21890086 | 50593551 | 8515138 | 2571572 | 5943566 | 8515138 | 2571572 | 5943566 | 72483637 | 21890086 | 50593551 | 8515138 | 2571572 | 5943566 | 8515138 | 2571572 | 5943566 | 0 | 0 | Motorola Solutions, Inc. | TRUE
NT10BIX5570090 | CCI | 2010 | Q4 | Q4 - 2010 | 3448757 | 1034627 | 2414130 | 0 | 0 | 0 | 2759005 | 827701 | 1931304 | 9860644 | 2958193 | 6902451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 0 | 0 | 0 | 106706 | 32012 | 74694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 12023 | 3607 | 8416 | 313841 | 94152 | 219689 | 167377 | 50213 | 117164 | 1365 | 409 | 956 | 167377 | 50213 | 117164 | 941506 | 282452 | 659054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 13388 | 4016 | 9372 | 3346929 | 1004078 | 2342851 | 15401653 | 4620496 | 10781157 | 13388 | 4016 | 9372 | 3346929 | 1004078 | 2342851 | 0 | 0 | DCN, LLC | TRUE
NT10BIX5570090 | CCI | 2011 | Q1 | Q1 - 2011 | 3448757 | 1034627 | 2414130 | 212563 | 63769 | 148794 | 2759005 | 827701 | 1931304 | 9860644 | 2958193 | 6902451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 0 | 0 | 0 | 106706 | 32012 | 74694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 65339 | 19602 | 45737 | 376609 | 112983 | 263626 | 167377 | 50213 | 117164 | 56421 | 16926 | 39495 | 167377 | 50213 | 117164 | 941506 | 282452 | 659054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 334323 | 100297 | 234026 | 3409697 | 1022909 | 2386788 | 15401653 | 4620496 | 10781157 | 334323 | 100297 | 234026 | 3409697 | 1022909 | 2386788 | 0 | 0 | DCN, LLC | TRUE
NT10BIX5570090 | CCI | 2011 | Q2 | Q2 - 2011 | 3448757 | 1034627 | 2414130 | 212563 | 63769 | 148794 | 2759005 | 827701 | 1931304 | 9860644 | 2958193 | 6902451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 0 | 0 | 0 | 213412 | 64023 | 149389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 102658 | 30797 | 71861 | 406609 | 121982 | 284627 | 167377 | 50213 | 117164 | 77470 | 23241 | 54229 | 167377 | 50213 | 117164 | 941506 | 282452 | 659054 | 0 | 0 | 0 | 94150 | 28245 | 65905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 392691 | 117807 | 274884 | 3640553 | 1092164 | 2548389 | 15401653 | 4620496 | 10781157 | 392691 | 117807 | 274884 | 3640553 | 1092164 | 2548389 | 0 | 0 | DCN, LLC | TRUE
NT10BIX5570090 | CCI | 2011 | Q3 | Q3 - 2011 | 3448757 | 1034627 | 2414130 | 391309 | 117393 | 273916 | 800000 | 240000 | 560000 | 9860644 | 2958193 | 6902451 | 0 | 0 | 0 | 1700000 | 510000 | 1190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 0 | 0 | 0 | 100000 | 30000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 165172 | 49552 | 115620 | 230000 | 69000 | 161000 | 167377 | 50213 | 117164 | 82470 | 24741 | 57729 | 110000 | 33000 | 77000 | 941506 | 282452 | 659054 | 777 | 233 | 544 | 70000 | 21000 | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 639728 | 191919 | 447809 | 3010000 | 903000 | 2107000 | 15401653 | 4620496 | 10781157 | 639728 | 191919 | 447809 | 3010000 | 903000 | 2107000 | 0 | 0 | DCN, LLC | TRUE
NT10BIX5570090 | CCI | 2011 | Q4 | Q4 - 2011 | 3448757 | 1034627 | 2414130 | 1402907 | 420872 | 982035 | 2500000 | 750000 | 1750000 | 9860644 | 2958193 | 6902451 | 1274665 | 382399 | 892266 | 1700000 | 510000 | 1190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 0 | 0 | 0 | 100000 | 30000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 271140 | 81342 | 189798 | 350000 | 105000 | 245000 | 167377 | 50213 | 117164 | 94225 | 28268 | 65957 | 120000 | 36000 | 84000 | 941506 | 282452 | 659054 | 119438 | 35832 | 83606 | 140000 | 42000 | 98000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 3162375 | 948713 | 2213662 | 4910000 | 1473000 | 3437000 | 15401653 | 4620496 | 10781157 | 3162375 | 948713 | 2213662 | 4910000 | 1473000 | 3437000 | 0 | 0 | DCN, LLC | TRUE
NT10BIX5570090 | CCI | 2012 | Q1 | Q1 - 2012 | 3448757 | 1034627 | 2414130 | 2397623 | 719287 | 1678336 | 3448757 | 1034627 | 2414130 | 9860644 | 2958193 | 6902451 | 2206575 | 661973 | 1544602 | 5097000 | 1529100 | 3567900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 28165 | 8449 | 19716 | 35000 | 10500 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 344626 | 103388 | 241238 | 546140 | 163842 | 382298 | 167377 | 50213 | 117164 | 109188 | 32756 | 76432 | 140000 | 42000 | 98000 | 941506 | 282452 | 659054 | 194797 | 58439 | 136358 | 419438 | 125831 | 293607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 5280974 | 1584292 | 3696682 | 9686335 | 2905900 | 6780435 | 15401653 | 4620496 | 10781157 | 5280974 | 1584292 | 3696682 | 9686335 | 2905900 | 6780435 | 0 | 0 | DCN, LLC | TRUE
NT10BIX5570090 | CCI | 2012 | Q2 | Q2 - 2012 | 3448757 | 1034627 | 2414130 | 4535927 | 1360777 | 3175150 | 4535927 | 1360778 | 3175149 | 9860644 | 2958193 | 6902451 | 3136115 | 940835 | 2195280 | 6743064 | 2022919 | 4720145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 76765 | 23029 | 53736 | 80000 | 24000 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 478469 | 143541 | 334928 | 576140 | 172842 | 403298 | 167377 | 50213 | 117164 | 135130 | 40539 | 94591 | 150000 | 45000 | 105000 | 941506 | 282452 | 659054 | 235626 | 70688 | 164938 | 500000 | 150000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 8598032 | 2579409 | 6018623 | 12585131 | 3775539 | 8809592 | 15401653 | 4620496 | 10781157 | 8598032 | 2579409 | 6018623 | 12585131 | 3775539 | 8809592 | 0 | 0 | DCN, LLC | TRUE
NT10BIX5570090 | CCI | 2012 | Q3 | Q3 - 2012 | 3448757 | 1034627 | 2414130 | 4339105 | 1301731 | 3037374 | 4339105 | 1301731 | 3037374 | 9860644 | 2958193 | 6902451 | 5662808 | 1698842 | 3963966 | 7533000 | 2259900 | 5273100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 86605 | 25982 | 60623 | 90000 | 27000 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 494074 | 148222 | 345852 | 596140 | 178842 | 417298 | 167377 | 50213 | 117164 | 151409 | 45423 | 105986 | 160000 | 48000 | 112000 | 941506 | 282452 | 659054 | 514737 | 154421 | 360316 | 650000 | 195000 | 455000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 11248738 | 3374621 | 7874117 | 13368245 | 4010473 | 9357772 | 15401653 | 4620496 | 10781157 | 11248738 | 3374621 | 7874117 | 13368245 | 4010473 | 9357772 | 0 | 0 | DCN, LLC | TRUE
NT10BIX5570090 | CCI | 2012 | Q4 | Q4 - 2012 | 3448757 | 1034627 | 2414130 | 4351385 | 1305415 | 3045970 | 4351385 | 1305415 | 3045970 | 9860644 | 2958193 | 6902451 | 7189227 | 2156768 | 5032459 | 7983000 | 2394900 | 5588100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 86605 | 25982 | 60623 | 90000 | 27000 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 516520 | 154956 | 361564 | 616140 | 184842 | 431298 | 167377 | 50213 | 117164 | 166874 | 50061 | 116813 | 175000 | 52500 | 122500 | 941506 | 282452 | 659054 | 629425 | 188827 | 440598 | 734438 | 220331 | 514107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 12940036 | 3882009 | 9058027 | 13949963 | 4184988 | 9764975 | 15401653 | 4620496 | 10781157 | 12940036 | 3882009 | 9058027 | 13949963 | 4184988 | 9764975 | 0 | 0 | DCN, LLC | TRUE
NT10BIX5570090 | CCI | 2013 | Q1 | Q1 - 2013 | 3448757 | 1034627 | 2414130 | 4570876 | 1371263 | 3199613 | 4570876 | 1371263 | 3199613 | 9860644 | 2958193 | 6902451 | 7391164 | 2217349 | 5173815 | 8500000 | 2550000 | 5950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 87155 | 26146 | 61009 | 90000 | 27000 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 638973 | 191692 | 447281 | 650000 | 195000 | 455000 | 167377 | 50213 | 117164 | 173860 | 52158 | 121702 | 180000 | 54000 | 126000 | 941506 | 282452 | 659054 | 697642 | 209293 | 488349 | 850000 | 255000 | 595000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 13559670 | 4067901 | 9491769 | 14840876 | 4452263 | 10388613 | 15401653 | 4620496 | 10781157 | 13559670 | 4067901 | 9491769 | 14840876 | 4452263 | 10388613 | 0 | 0 | DCN, LLC | TRUE
NT10BIX5570090 | CCI | 2013 | Q2 | Q2 - 2013 | 3448757 | 1034627 | 2414130 | 4570876 | 1371263 | 3199613 | 4598580 | 1379575 | 3219005 | 9860644 | 2958193 | 6902451 | 7429399 | 2228820 | 5200579 | 8983608 | 2695082 | 6288526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355687 | 106706 | 248981 | 87155 | 26146 | 61009 | 90000 | 27000 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 641554 | 192466 | 449088 | 665000 | 199500 | 465500 | 167377 | 50213 | 117164 | 179702 | 53911 | 125791 | 200000 | 60000 | 140000 | 941506 | 282452 | 659054 | 699970 | 209991 | 489979 | 864465 | 259339 | 605126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 13608656 | 4082597 | 9526059 | 15401653 | 4620496 | 10781157 | 15401653 | 4620496 | 10781157 | 13608656 | 4082597 | 9526059 | 15401653 | 4620496 | 10781157 | 0 | 0 | DCN, LLC | TRUE
NT10BIX5570090 | CCI | 2013 | Q3 | Q3 - 2013 | 3448757 | 1034627 | 2414130 | 4487315 | 1346194 | 3141121 | 4487315 | 1346194 | 3141121 | 9860644 | 2958193 | 6902451 | 8841647 | 2652494 | 6189153 | 8841647 | 2652494 | 6189153 | 0 | 0 | 0 | 149373 | 44812 | 104561 | 149373 | 44812 | 104561 | 355687 | 106706 | 248981 | 88105 | 26432 | 61673 | 88105 | 26432 | 61673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627682 | 188305 | 439377 | 705278 | 211583 | 493695 | 705278 | 211583 | 493695 | 167377 | 50213 | 117164 | 203290 | 60987 | 142303 | 203290 | 60987 | 142303 | 941506 | 282452 | 659054 | 926645 | 277994 | 648651 | 926645 | 277994 | 648651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15401653 | 4620496 | 10781157 | 15401653 | 4620496 | 10781157 | 15401653 | 4620496 | 10781157 | 15401653 | 4620496 | 10781157 | 15401653 | 4620496 | 10781157 | 15401653 | 4620496 | 10781157 | 0 | 0 | DCN, LLC | TRUE
NT10BIX5570091 | CCI | 2010 | Q4 | Q4 - 2010 | 17879350 | 3036520 | 14842830 | 0 | 0 | 0 | 0 | 0 | 0 | 29509500 | 4932099 | 24577401 | 0 | 0 | 0 | 0 | 0 | 0 | 1818980 | 303120 | 1515860 | 289742 | 49256 | 240486 | 379894 | 64582 | 315312 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 492650 | 2457350 | 278678 | 47375 | 231302 | 1970000 | 334900 | 1635100 | 1250000 | 208750 | 1041250 | 0 | 0 | 0 | 0 | 0 | 0 | 704720 | 129629 | 575091 | 0 | 0 | 0 | 0 | 0 | 0 | 190800 | 55332 | 135468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 568420 | 96631 | 471788 | 2349894 | 399482 | 1950412 | 64803350 | 19658100 | 45145250 | 568420 | 96631 | 471788 | 2349894 | 399482 | 1950412 | 0 | 0 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | CCI | 2011 | Q1 | Q1 - 2011 | 17879350 | 3036520 | 14842830 | 0 | 0 | 0 | 3575870 | 607898 | 2967972 | 29509500 | 4932099 | 24577401 | 0 | 0 | 0 | 1250000 | 212500 | 1037500 | 1818980 | 303120 | 1515860 | 401582 | 68269 | 333313 | 657894 | 111842 | 546052 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 492650 | 2457350 | 1468487 | 249643 | 1218844 | 2950000 | 501500 | 2448500 | 1250000 | 208750 | 1041250 | 0 | 0 | 0 | 0 | 0 | 0 | 704720 | 129629 | 575091 | 0 | 0 | 0 | 117000 | 19890 | 97110 | 190800 | 55332 | 135468 | 0 | 0 | 0 | 48000 | 8160 | 39840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 1870069 | 317912 | 1552157 | 8598764 | 1461790 | 7136974 | 64803350 | 19658100 | 45145250 | 1870069 | 317912 | 1552157 | 8598764 | 1461790 | 7136974 | 0 | 0 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | CCI | 2011 | Q2 | Q2 - 2011 | 15886941 | 2678732 | 13208209 | 1065288 | 181099 | 884189 | 2000000 | 340000 | 1660000 | 33319581 | 5620036 | 27699545 | 7042 | 1197 | 5845 | 415000 | 70550 | 344450 | 1611500 | 271699 | 1339801 | 885288 | 150499 | 734789 | 1005000 | 170850 | 834150 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 2463781 | 418843 | 2044938 | 2900000 | 493000 | 2407000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 20438 | 3474 | 16964 | 111328 | 18777 | 92551 | 0 | 0 | 0 | 30738 | 5225 | 25513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 4421399 | 751638 | 3669761 | 11371176 | 6083099 | 5288077 | 64803350 | 19658100 | 45145250 | 4421399 | 751638 | 3669761 | 11371176 | 6083099 | 5288077 | 0 | 0 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | CCI | 2011 | Q3 | Q3 - 2011 | 15886941 | 2678732 | 13208209 | 2309191 | 392563 | 1916629 | 4500000 | 765000 | 3735000 | 33319581 | 5620036 | 27699545 | 802796 | 136475 | 666321 | 4250000 | 722500 | 3527500 | 1611500 | 271699 | 1339801 | 1154871 | 196328 | 958543 | 1355000 | 230350 | 1124650 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 2689957 | 457293 | 2232664 | 2900000 | 493000 | 2407000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 12000 | 2040 | 9960 | 111328 | 18777 | 92551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 6956815 | 1182659 | 5774157 | 13017000 | 2212890 | 10804110 | 64803350 | 19658100 | 45145250 | 6956815 | 1182659 | 5774157 | 13017000 | 2212890 | 10804110 | 0 | 0 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | CCI | 2011 | Q4 | Q4 - 2011 | 15886941 | 2678732 | 13208209 | 6517837 | 1108032 | 5409805 | 10000000 | 1700000 | 8300000 | 33319581 | 5620036 | 27699545 | 5000105 | 850018 | 4150087 | 9000000 | 1530000 | 7470000 | 1611500 | 271699 | 1339801 | 1349482 | 229412 | 1120070 | 1500000 | 255000 | 1245000 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 2943443 | 500385 | 2443058 | 3200000 | 544000 | 2656000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 50000 | 8500 | 41500 | 111328 | 18777 | 92551 | 0 | 0 | 0 | 29297 | 4980 | 24317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 15810867 | 2687847 | 13123020 | 23779297 | 4042480 | 19736817 | 64803350 | 19658100 | 45145250 | 15810867 | 2687847 | 13123020 | 23779297 | 4042480 | 19736817 | 0 | 0 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | CCI | 2012 | Q1 | Q1 - 2012 | 15886941 | 2678732 | 13208209 | 8148479 | 1385242 | 6763238 | 14298247 | 2430702 | 11867545 | 33319581 | 5620036 | 27699545 | 11744101 | 1996497 | 9747604 | 19500000 | 3315000 | 16185000 | 1611500 | 271699 | 1339801 | 1506226 | 256058 | 1250168 | 1750000 | 297500 | 1452500 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 3161047 | 537378 | 2623669 | 3240000 | 550800 | 2689200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 350000 | 59500 | 290500 | 111328 | 18777 | 92551 | 0 | 0 | 0 | 90000 | 15300 | 74700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 24559853 | 4175175 | 20384679 | 49728247 | 17168802 | 32559445 | 64803350 | 19658100 | 45145250 | 24559853 | 4175175 | 20384679 | 49728247 | 17168802 | 32559445 | 0 | 0 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | CCI | 2012 | Q2 | Q2 - 2012 | 15886941 | 2678732 | 13208209 | 11797174 | 2005520 | 9791654 | 14298247 | 2430702 | 11867545 | 33319581 | 5620036 | 27699545 | 20131727 | 3422394 | 16709333 | 26750000 | 4547500 | 22202500 | 1611500 | 271699 | 1339801 | 1507189 | 256222 | 1250967 | 1610000 | 273700 | 1336300 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 3489155 | 593156 | 2895999 | 3600000 | 612000 | 2988000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 350000 | 59500 | 290500 | 111328 | 18777 | 92551 | 44037 | 7486 | 36551 | 90000 | 15300 | 74700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 36969282 | 6284778 | 30684504 | 57198247 | 18438702 | 38759545 | 64803350 | 19658100 | 45145250 | 36969282 | 6284778 | 30684504 | 57198247 | 18438702 | 38759545 | 0 | 0 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | CCI | 2012 | Q3 | Q3 - 2012 | 15886941 | 2678732 | 13208209 | 12799209 | 2175866 | 10623343 | 15500000 | 2635000 | 12865000 | 33319581 | 5620036 | 27699545 | 27734367 | 4714842 | 23019525 | 30000000 | 5100000 | 24900000 | 1611500 | 271699 | 1339801 | 1640623 | 278906 | 1361717 | 1675000 | 284750 | 1390250 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 3550877 | 603649 | 2947228 | 3600000 | 612000 | 2988000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 350000 | 59500 | 290500 | 111328 | 18777 | 92551 | 44426 | 7552 | 36874 | 90000 | 15300 | 74700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 56269502 | 18280815 | 37988687 | 61715000 | 19206550 | 42508450 | 64803350 | 19658100 | 45145250 | 56269502 | 18280815 | 37988687 | 61715000 | 19206550 | 42508450 | 0 | 0 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | CCI | 2012 | Q4 | Q4 - 2012 | 15886941 | 2678732 | 13208209 | 13098954 | 2226822 | 10872132 | 13500000 | 2295000 | 11205000 | 33319581 | 5620036 | 27699545 | 31362792 | 5331674 | 26031118 | 33500000 | 5695000 | 27805000 | 1611500 | 271699 | 1339801 | 1652003 | 280841 | 1371162 | 1667003 | 283391 | 1383612 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 3612940 | 614200 | 2998740 | 3624940 | 616240 | 3008700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 350000 | 59500 | 290500 | 111328 | 18777 | 92551 | 44426 | 7552 | 36874 | 90000 | 15300 | 74700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 60271115 | 18961089 | 41310026 | 63231943 | 19464431 | 43767512 | 64803350 | 19658100 | 45145250 | 60271115 | 18961089 | 41310026 | 63231943 | 19464431 | 43767512 | 0 | 0 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | CCI | 2013 | Q1 | Q1 - 2013 | 15886941 | 2678732 | 13208209 | 13517732 | 2298014 | 11219717 | 13667732 | 2323514 | 11344217 | 33319581 | 5620036 | 27699545 | 33828896 | 5750912 | 28077984 | 35328896 | 6384729 | 28944167 | 1611500 | 271699 | 1339801 | 1764705 | 300000 | 1464706 | 1774705 | 301700 | 1473006 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 3632940 | 617600 | 3015340 | 3636940 | 618280 | 3018660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 350000 | 59500 | 290500 | 111328 | 18777 | 92551 | 44426 | 7552 | 36874 | 90000 | 15300 | 74700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 63288699 | 19474078 | 43814621 | 65348273 | 20203023 | 45145250 | 64803350 | 19658100 | 45145250 | 63288699 | 19474078 | 43814621 | 65348273 | 20203023 | 45145250 | 0 | 0 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | CCI | 2013 | Q2 | Q2 - 2013 | 15886941 | 2678732 | 13208209 | 13618005 | 2315061 | 11302944 | 13722603 | 2419659 | 11302944 | 33319581 | 5620036 | 27699545 | 36211132 | 6894224 | 29316908 | 41001548 | 11647290 | 29354258 | 1611500 | 271699 | 1339801 | 1770920 | 301056 | 1469864 | 1780146 | 347632 | 1432514 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 10500000 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 3636940 | 618280 | 3018660 | 3650940 | 632280 | 3018660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 0 | 0 | 0 | 111328 | 18777 | 92551 | 44426 | 7552 | 36874 | 44426 | 7552 | 36874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 65781423 | 20636173 | 45145250 | 70699663 | 25554413 | 45145250 | 64803350 | 19658100 | 45145250 | 65781423 | 20636173 | 45145250 | 70699663 | 25554413 | 45145250 | 0 | 234647 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570091 | CCI | 2013 | Q3 | Q3 - 2013 | 15886941 | 2678732 | 13208209 | 13707690 | 2405007 | 11302683 | 13707690 | 2405007 | 11302683 | 33319581 | 5620036 | 27699545 | 39834289 | 10494741 | 29339548 | 39834289 | 10494741 | 29339548 | 1611500 | 271699 | 1339801 | 1756390 | 321079 | 1435311 | 1756390 | 321079 | 1435311 | 10500000 | 10500000 | 0 | 12675000 | 12675000 | 0 | 12675000 | 12675000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2950000 | 497370 | 2452630 | 3651607 | 620773 | 3030834 | 3651607 | 620773 | 3030834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424000 | 71486 | 352514 | 0 | 0 | 0 | 0 | 0 | 0 | 111328 | 18777 | 92551 | 44426 | 7552 | 36874 | 44426 | 7552 | 36874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803350 | 19658100 | 45145250 | 71669402 | 26524152 | 45145250 | 71669402 | 26524152 | 45145250 | 64803350 | 19658100 | 45145250 | 71669402 | 26524152 | 45145250 | 71669402 | 26524152 | 45145250 | 0 | 326923 | Bluebird Media, L.L.C. | TRUE
NT10BIX5570093 | CCI | 2010 | Q4 | Q4 - 2010 | 1090000 | 218000 | 872000 | 0 | 0 | 0 | 545000 | 109000 | 436000 | 9819064 | 1581304 | 8237760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 0 | 0 | 0 | 80000 | 16000 | 64000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 0 | 0 | 0 | 625000 | 125000 | 500000 | 11560803 | 2323043 | 9237760 | 0 | 0 | 0 | 625000 | 125000 | 500000 | 2583000 | 0 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | CCI | 2011 | Q1 | Q1 - 2011 | 1090000 | 218000 | 872000 | 0 | 0 | 0 | 545000 | 109000 | 436000 | 9819064 | 1581304 | 8237760 | 0 | 0 | 0 | 403000 | 80600 | 322400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 0 | 0 | 0 | 140000 | 28000 | 112000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 49654 | 49654 | 0 | 77404 | 77404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 49654 | 49654 | 0 | 1165404 | 295004 | 870400 | 11560803 | 2323043 | 9237760 | 49654 | 49654 | 0 | 1165404 | 295004 | 870400 | 2583000 | 0 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | CCI | 2011 | Q2 | Q2 - 2011 | 1090000 | 218000 | 872000 | 0 | 0 | 0 | 900000 | 180000 | 720000 | 9819064 | 1581304 | 8237760 | 0 | 0 | 0 | 635984 | 127197 | 508787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 0 | 0 | 0 | 223130 | 44626 | 178504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 74767 | 74767 | 0 | 101880 | 101880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 74767 | 74767 | 0 | 1860994 | 453703 | 1407291 | 11560803 | 2323043 | 9237760 | 74767 | 74767 | 0 | 1860994 | 453703 | 1407291 | 2583000 | 0 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | CCI | 2011 | Q3 | Q3 - 2011 | 1090000 | 218000 | 872000 | 0 | 0 | 0 | 872000 | 174400 | 697600 | 9819064 | 1581304 | 8237760 | 586069 | 117214 | 468855 | 962736 | 192547 | 770189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 143365 | 28673 | 114692 | 227928 | 45586 | 182342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 95943 | 95943 | 0 | 122807 | 122807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 825377 | 241830 | 583547 | 2185471 | 535340 | 1650131 | 11560803 | 2323043 | 9237760 | 825377 | 241830 | 583547 | 2185471 | 535340 | 1650131 | 2583000 | 0 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | CCI | 2011 | Q4 | Q4 - 2011 | 1090000 | 218000 | 872000 | 452153 | 90431 | 361722 | 871548 | 174310 | 697238 | 9819064 | 1581304 | 8237760 | 660657 | 132131 | 528526 | 1774255 | 354851 | 1419404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 230131 | 46026 | 184105 | 234513 | 46902 | 187611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 120693 | 120693 | 0 | 148352 | 148352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 1463634 | 389281 | 1074353 | 3028668 | 724415 | 2304253 | 11560803 | 2323043 | 9237760 | 1463634 | 389281 | 1074353 | 3028668 | 724415 | 2304253 | 2583000 | 1000 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | CCI | 2012 | Q1 | Q1 - 2012 | 1090000 | 218000 | 872000 | 871548 | 174310 | 697238 | 916841 | 183368 | 733473 | 9819064 | 1581304 | 8237760 | 1389717 | 277943 | 1111774 | 3030809 | 606162 | 2424647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 235499 | 47100 | 188399 | 274353 | 54871 | 219482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 144594 | 144594 | 0 | 171102 | 171102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 2641358 | 643947 | 1997411 | 4393105 | 1015503 | 3377602 | 11560803 | 2323043 | 9237760 | 2641358 | 643947 | 1997411 | 4393105 | 1015503 | 3377602 | 2583000 | 2500 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | CCI | 2012 | Q2 | Q2 - 2012 | 1090000 | 218000 | 872000 | 871548 | 174310 | 697238 | 871548 | 174310 | 697238 | 9819064 | 1581304 | 8237760 | 1952808 | 390561 | 1562247 | 5200000 | 1040000 | 4160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 314829 | 62966 | 251863 | 314829 | 62966 | 251863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 177556 | 177556 | 0 | 216639 | 216639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 3316741 | 805393 | 2511348 | 6603016 | 1493915 | 5109101 | 11560803 | 2323043 | 9237760 | 3316741 | 805393 | 2511348 | 6603016 | 1493915 | 5109101 | 2583000 | 4000 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | CCI | 2012 | Q3 | Q3 - 2012 | 1090000 | 218000 | 872000 | 871548 | 174310 | 697238 | 871548 | 174310 | 697238 | 9819064 | 1581304 | 8237760 | 3511854 | 702371 | 2809483 | 8293263 | 1658653 | 6634610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 321566 | 64313 | 257253 | 321566 | 64313 | 257253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 209094 | 209094 | 0 | 241344 | 241344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 4914062 | 1150088 | 3763974 | 9727721 | 2138620 | 7589101 | 11560803 | 2323043 | 9237760 | 4914062 | 1150088 | 3763974 | 9727721 | 2138620 | 7589101 | 2583000 | 6500 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | CCI | 2012 | Q4 | Q4 - 2012 | 1090000 | 218000 | 872000 | 871548 | 174310 | 697238 | 871548 | 174310 | 697238 | 9819064 | 1581304 | 8237760 | 6021949 | 1204390 | 4817559 | 8360081 | 1672016 | 6688065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 322566 | 64513 | 258053 | 322566 | 64513 | 258053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 247441 | 247441 | 0 | 282384 | 282384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 7463504 | 1690654 | 5772850 | 9836579 | 2193223 | 7643356 | 11560803 | 2323043 | 9237760 | 7463504 | 1690654 | 5772850 | 9836579 | 2193223 | 7643356 | 2583000 | 12500 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | CCI | 2013 | Q1 | Q1 - 2013 | 1090000 | 218000 | 872000 | 871548 | 174310 | 697238 | 871548 | 174310 | 697238 | 9819064 | 1581304 | 8237760 | 7970099 | 1594020 | 6376079 | 9404966 | 1811280 | 7593686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 323896 | 64779 | 259117 | 323896 | 64779 | 259117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 258077 | 258077 | 0 | 272674 | 272674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 9423620 | 2091186 | 7332434 | 10873084 | 2323043 | 8550041 | 11560803 | 2323043 | 9237760 | 9423620 | 2091186 | 7332434 | 10873084 | 2323043 | 8550041 | 2583000 | 20000 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | CCI | 2013 | Q2 | Q2 - 2013 | 1090000 | 218000 | 872000 | 871548 | 174310 | 697238 | 1172934 | 174310 | 998624 | 9819064 | 1581304 | 8237760 | 8415015 | 1683003 | 6732012 | 9285795 | 1699659 | 7586136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 323896 | 64779 | 259117 | 323896 | 64779 | 259117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 268685 | 268685 | 0 | 272221 | 272221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 9879144 | 2190777 | 7688367 | 11054846 | 2210969 | 8843877 | 11560803 | 2323043 | 9237760 | 9879144 | 2190777 | 7688367 | 11054846 | 2210969 | 8843877 | 2583000 | 27500 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570093 | CCI | 2013 | Q3 | Q3 - 2013 | 1090000 | 218000 | 872000 | 1197782 | 174310 | 1023472 | 1197782 | 174310 | 1023472 | 9819064 | 1581304 | 8237760 | 9283920 | 1705777 | 7578143 | 9283920 | 1705777 | 7578143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 32000 | 128000 | 337946 | 64779 | 273167 | 337946 | 64779 | 273167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491739 | 491739 | 0 | 273829 | 273829 | 0 | 273829 | 273829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11560803 | 2323043 | 9237760 | 11093477 | 2218695 | 8874782 | 11093477 | 2218695 | 8874782 | 11560803 | 2323043 | 9237760 | 11093477 | 2218695 | 8874782 | 11093477 | 2218695 | 8874782 | 2583000 | 68371 | Citizens' Telephone Co-operative | TRUE
NT10BIX5570094 | CCI | 2010 | Q4 | Q4 - 2010 | 51441480 | 1133078 | 50308402 | 0 | 0 | 0 | 9125937 | 1133079 | 7586338 | 75000 | 0 | 75000 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12799710 | 12799710 | 0 | 0 | 0 | 0 | 7319873 | 7319873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17985220 | 0 | 17985220 | 0 | 0 | 0 | 1791995 | 0 | 1791995 | 1686378 | 0 | 1686378 | 0 | 0 | 0 | 406520 | 0 | 406520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 0 | 0 | 0 | 18719325 | 8452952 | 9859853 | 83987788 | 13932788 | 70055000 | 0 | 0 | 0 | 18719325 | 8452952 | 9859853 | 0 | 0 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | CCI | 2011 | Q1 | Q1 - 2011 | 51441480 | 1133078 | 50308402 | 1184979 | 1184979 | 0 | 6301861 | 2083193 | 4218668 | 75000 | 0 | 75000 | 0 | 0 | 0 | 867917 | 0 | 867917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12799710 | 12799710 | 0 | 3677823 | 3677823 | 0 | 5440866 | 5440866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17985220 | 0 | 17985220 | 106165 | 106165 | 0 | 700104 | 107700 | 592403 | 1686378 | 0 | 1686378 | 0 | 0 | 0 | 938983 | 0 | 938983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 4968967 | 4968967 | 0 | 14249731 | 7631759 | 6617971 | 83987788 | 13932788 | 70055000 | 4968967 | 4968967 | 0 | 14249731 | 7631759 | 6617971 | 0 | 0 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | CCI | 2011 | Q2 | Q2 - 2011 | 51233355 | 2083193 | 49150162 | 2015789 | 2015789 | 0 | 12090698 | 1252383 | 10838315 | 11813924 | 0 | 11813924 | 0 | 0 | 0 | 3212091 | 0 | 3212091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11846954 | 11846954 | 0 | 5109503 | 5109503 | 0 | 7821900 | 7821900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7512236 | 107700 | 7404536 | 106165 | 106165 | 0 | 2308660 | 107700 | 2200960 | 1686378 | 0 | 1686378 | 0 | 0 | 0 | 1301740 | 0 | 1301740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84092847 | 14037847 | 70055000 | 7231457 | 7231457 | 0 | 26735089 | 9181983 | 17553106 | 84092847 | 14037847 | 70055000 | 7231457 | 7231457 | 0 | 26735089 | 9181983 | 17553106 | 0 | 0 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | CCI | 2011 | Q3 | Q3 - 2011 | 51233355 | 2083193 | 49150162 | 4816028 | 2015789 | 2800239 | 15834302 | 1252383 | 14581919 | 11813924 | 0 | 11813924 | 385634 | 0 | 385634 | 3182546 | 0 | 3182546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11846954 | 11846954 | 0 | 5886703 | 5886703 | 0 | 7138159 | 7138159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7512236 | 107700 | 7404536 | 256082 | 106165 | 149917 | 1801604 | 107700 | 1693904 | 1686378 | 0 | 1686378 | 0 | 0 | 0 | 4851 | 0 | 4851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84092847 | 14037847 | 70055000 | 11344447 | 8008657 | 3335790 | 27961462 | 8498242 | 19463220 | 84092847 | 14037847 | 70055000 | 11344447 | 8008657 | 3335790 | 27961462 | 8498242 | 19463220 | 0 | 0 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | CCI | 2011 | Q4 | Q4 - 2011 | 51128296 | 1978134 | 49150162 | 12356624 | 2015789 | 10340835 | 16633513 | 2015789 | 14617724 | 11813924 | 0 | 11813924 | 1041210 | 0 | 1041210 | 5622511 | 0 | 5622511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11846954 | 11846954 | 0 | 6518553 | 6518553 | 0 | 6518553 | 6518553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7512236 | 107700 | 7404536 | 510940 | 106165 | 404775 | 1914914 | 106165 | 1808749 | 1686378 | 0 | 1686378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 20427327 | 8640507 | 11786820 | 30689491 | 8640507 | 22048984 | 83987788 | 13932788 | 70055000 | 20427327 | 8640507 | 11786820 | 30689491 | 8640507 | 22048984 | 0 | 0 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | CCI | 2012 | Q1 | Q1 - 2012 | 51128296 | 1978134 | 49150162 | 18568009 | 1903814 | 16664195 | 24394867 | 1903814 | 22491053 | 11813924 | 0 | 11813924 | 2547265 | 0 | 2547265 | 4064832 | 0 | 4064832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11846954 | 11846954 | 0 | 7832817 | 7832817 | 0 | 8939585 | 8939585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7512236 | 107700 | 7404536 | 1219345 | 106165 | 1113180 | 1581564 | 106165 | 1475399 | 1686378 | 0 | 1686378 | 5187 | 0 | 5187 | 5187 | 0 | 5187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 30172623 | 9842796 | 20329827 | 38986035 | 10949564 | 28036471 | 83987788 | 13932788 | 70055000 | 30172623 | 9842796 | 20329827 | 38986035 | 10949564 | 28036471 | 0 | 0 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | CCI | 2012 | Q2 | Q2 - 2012 | 51128296 | 1978134 | 49150162 | 21468249 | 1903814 | 19564435 | 26635770 | 1903814 | 24731956 | 11813924 | 0 | 11813924 | 3336542 | 0 | 3336542 | 4374689 | 0 | 4374689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11846954 | 11846954 | 0 | 9315783 | 9315783 | 0 | 9871800 | 9871800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7512236 | 107700 | 7404536 | 1252326 | 106165 | 1146161 | 2022746 | 106165 | 1916581 | 1686378 | 0 | 1686378 | 5188 | 0 | 5188 | 5188 | 0 | 5188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 35378088 | 11325762 | 24052326 | 42910193 | 11881779 | 31028414 | 83987788 | 13932788 | 70055000 | 35378088 | 11325762 | 24052326 | 42910193 | 11881779 | 31028414 | 0 | 0 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | CCI | 2012 | Q3 | Q3 - 2012 | 51128296 | 1978134 | 49150162 | 22616408 | 1903814 | 20712594 | 27077788 | 1903814 | 25173974 | 11813924 | 0 | 11813924 | 3598391 | 0 | 3598391 | 5269340 | 0 | 5269340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11846954 | 11846954 | 0 | 9808085 | 9808085 | 0 | 10358870 | 10358870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7512236 | 107700 | 7404536 | 1449637 | 106165 | 1343472 | 2424132 | 106165 | 2317967 | 1686378 | 0 | 1686378 | 5188 | 0 | 5188 | 5188 | 0 | 5188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 37477709 | 11818064 | 25659645 | 45135318 | 12368849 | 32766469 | 83987788 | 13932788 | 70055000 | 37477709 | 11818064 | 25659645 | 45135318 | 12368849 | 32766469 | 0 | 0 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | CCI | 2012 | Q4 | Q4 - 2012 | 59196021 | 2074111 | 57121910 | 22680140 | 1903814 | 20776326 | 24615512 | 1903814 | 22711698 | 6626607 | 0 | 626607 | 3598616 | 0 | 3598616 | 4547184 | 0 | 4547184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11710484 | 11710484 | 0 | 10341186 | 10341186 | 0 | 10810536 | 10810536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427270 | 148193 | 3279077 | 1449638 | 106165 | 1343473 | 2024467 | 106165 | 1918302 | 3027406 | 0 | 3027406 | 5187 | 0 | 5187 | 5187 | 0 | 5187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 64055000 | 38074767 | 12351165 | 25723602 | 42002886 | 12820515 | 29182371 | 83987788 | 13932788 | 64055000 | 38074767 | 12351165 | 25723602 | 42002886 | 12820515 | 29182371 | 0 | 0 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | CCI | 2013 | Q1 | Q1 - 2013 | 59196021 | 2074111 | 57121910 | 22680140 | 1903814 | 20776326 | 25023761 | 1903814 | 23119947 | 6626607 | 0 | 6626607 | 3598616 | 0 | 3598616 | 4552326 | 0 | 4552326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11710484 | 11710484 | 0 | 10810536 | 10810536 | 0 | 11279886 | 11279886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427270 | 148193 | 3279077 | 1449638 | 106165 | 1343473 | 2026466 | 106165 | 1920301 | 3027406 | 0 | 3027406 | 5187 | 0 | 5187 | 5187 | 0 | 5187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 38544117 | 12820515 | 25723602 | 42887626 | 13289865 | 29597761 | 83987788 | 13932788 | 70055000 | 38544117 | 12820515 | 25723602 | 42887626 | 13289865 | 29597761 | 0 | 0 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | CCI | 2013 | Q2 | Q2 - 2013 | 59196021 | 2074111 | 57121910 | 24006409 | 1903814 | 22102595 | 26437594 | 1903814 | 24533780 | 6626607 | 0 | 6626607 | 4549490 | 0 | 4549490 | 5365841 | 0 | 5365841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11710484 | 11710484 | 0 | 11319853 | 11319853 | 0 | 11331276 | 11331276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427270 | 148193 | 3279077 | 2026465 | 106165 | 1920300 | 2343317 | 106165 | 2237152 | 3027406 | 0 | 3027406 | 5187 | 0 | 5187 | 5187 | 0 | 5187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 41907404 | 13329832 | 28577572 | 45483215 | 13341255 | 32141960 | 83987788 | 13932788 | 70055000 | 41907404 | 13329832 | 28577572 | 45483215 | 13341255 | 32141960 | 0 | 0 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | CCI | 2013 | Q3 | Q3 - 2013 | 59196021 | 2074111 | 57121910 | 26399978 | 1903814 | 24496164 | 27281704 | 1903814 | 25377890 | 6626607 | 0 | 6626607 | 5361116 | 0 | 5361116 | 5365226 | 0 | 5365226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11710484 | 11710484 | 0 | 11331275 | 11331275 | 0 | 11331275 | 11331275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427270 | 148193 | 3279077 | 2341957 | 106165 | 2235792 | 2341958 | 106165 | 2235793 | 3027406 | 0 | 3027406 | 5186 | 0 | 5186 | 5186 | 0 | 5186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 45439512 | 13341254 | 32098258 | 46325349 | 13341254 | 32984095 | 83987788 | 13932788 | 70055000 | 45439512 | 13341254 | 32098258 | 46325349 | 13341254 | 32984095 | 0 | 0 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570094 | CCI | 2013 | Q4 | Q4 - 2013 | 59196021 | 2074111 | 57121910 | 26412928 | 1903814 | 24509114 | 26453242 | 1903814 | 24549428 | 6626607 | 0 | 6626607 | 5362391 | 0 | 5362391 | 5361117 | 0 | 5361117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11710484 | 11710484 | 0 | 11331275 | 11331275 | 0 | 11331275 | 11331275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427270 | 148193 | 3279077 | 2341957 | 106165 | 2235792 | 2341957 | 106165 | 2235792 | 3027406 | 0 | 3027406 | 5186 | 0 | 5186 | 5186 | 0 | 5186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83987788 | 13932788 | 70055000 | 45453737 | 13341254 | 32112483 | 45492777 | 13341254 | 32151523 | 83987788 | 13932788 | 70055000 | 45453737 | 13341254 | 32112483 | 45492777 | 13341254 | 32151523 | 0 | 0 | Executive Office of the State of Mississippi | TRUE
NT10BIX5570095 | CCI | 2010 | Q4 | Q4 - 2010 | 2078817 | 162000 | 1916817 | 0 | 0 | 0 | 3000 | 0 | 3000 | 4470516 | 1312540 | 3157976 | 0 | 0 | 0 | 410000 | 400000 | 10000 | 510200 | 0 | 510200 | 55180 | 0 | 55180 | 157000 | 0 | 157000 | 486000 | 441000 | 45000 | 0 | 0 | 0 | 14500 | 13250 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 34092 | 0 | 34092 | 142000 | 0 | 142000 | 75000 | 0 | 75000 | 0 | 0 | 0 | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 15000 | 50000 | 39787 | 28739 | 11048 | 45787 | 28739 | 17048 | 8199737 | 1930540 | 6269197 | 129059 | 28739 | 100320 | 797287 | 441989 | 355298 | 8199737 | 1930540 | 6269197 | 129059 | 28739 | 100320 | 797287 | 441989 | 355298 | 0 | 0 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | CCI | 2011 | Q1 | Q1 - 2011 | 2078817 | 162000 | 1916817 | 2797 | 0 | 2797 | 7787 | 0 | 7787 | 4470516 | 1312540 | 3157976 | 35507 | 0 | 35507 | 85000 | 0 | 85000 | 510200 | 0 | 510200 | 131599 | 0 | 131599 | 192000 | 0 | 192000 | 486000 | 441000 | 45000 | 0 | 0 | 0 | 90000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 146111 | 0 | 146111 | 180000 | 0 | 180000 | 75000 | 0 | 75000 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 15000 | 50000 | 46262 | 28739 | 17523 | 51262 | 28739 | 22523 | 8199737 | 1930540 | 6269197 | 362276 | 28739 | 333537 | 621049 | 118739 | 502310 | 8199737 | 1930540 | 6269197 | 362276 | 28739 | 333537 | 621049 | 118739 | 502310 | 0 | 0 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | CCI | 2011 | Q2 | Q2 - 2011 | 2078817 | 162000 | 1916817 | 2797 | 0 | 2797 | 5500 | 0 | 5500 | 4470516 | 1312540 | 3157976 | 44248 | 0 | 44248 | 1420529 | 1312540 | 107989 | 510200 | 0 | 510200 | 197524 | 0 | 197524 | 263449 | 0 | 263449 | 486000 | 441000 | 45000 | 110250 | 110250 | 0 | 112500 | 112500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 178562 | 0 | 178562 | 221013 | 0 | 221013 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 15000 | 50000 | 51185 | 28739 | 22446 | 56108 | 28739 | 27369 | 8199737 | 1930540 | 6269197 | 584566 | 138989 | 445577 | 2079099 | 1453779 | 625320 | 8199737 | 1930540 | 6269197 | 584566 | 138989 | 445577 | 2079099 | 1453779 | 625320 | 0 | 0 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | CCI | 2011 | Q3 | Q3 - 2011 | 2078817 | 162000 | 1916817 | 5618 | 0 | 5618 | 10000 | 0 | 10000 | 4470516 | 1312540 | 3157976 | 73974 | 0 | 73974 | 1500000 | 1000000 | 500000 | 510200 | 0 | 510200 | 247253 | 0 | 247253 | 328000 | 0 | 328000 | 486000 | 441000 | 45000 | 148500 | 148500 | 0 | 181500 | 181500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 204116 | 0 | 204116 | 305000 | 0 | 305000 | 75000 | 0 | 75000 | 930 | 0 | 930 | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 15000 | 50000 | 53544 | 28739 | 24805 | 56108 | 28739 | 27369 | 8199737 | 1930540 | 6269197 | 733935 | 177239 | 556696 | 2405608 | 1210239 | 1195369 | 8199737 | 1930540 | 6269197 | 733935 | 177239 | 556696 | 2405608 | 1210239 | 1195369 | 0 | 0 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | CCI | 2011 | Q4 | Q4 - 2011 | 2078817 | 162000 | 1916817 | 5618 | 0 | 5618 | 250000 | 0 | 250000 | 4470516 | 1312540 | 3157976 | 859963 | 0 | 859963 | 1365000 | 200000 | 1165000 | 510200 | 0 | 510200 | 314573 | 0 | 314573 | 365000 | 0 | 365000 | 486000 | 441000 | 45000 | 488890 | 475500 | 13390 | 493390 | 480000 | 13390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 231947 | 0 | 231947 | 275000 | 0 | 275000 | 75000 | 0 | 75000 | 930 | 0 | 930 | 65000 | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 15000 | 50000 | 61577 | 28739 | 32838 | 64739 | 28739 | 36000 | 8199737 | 1930540 | 6269197 | 1963498 | 504239 | 1459259 | 2878129 | 708739 | 2169390 | 8199737 | 1930540 | 6269197 | 1963498 | 504239 | 1459259 | 2878129 | 708739 | 2169390 | 0 | 0 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | CCI | 2012 | Q1 | Q1 - 2012 | 2078817 | 112000 | 1916817 | 147403 | 0 | 147403 | 950000 | 0 | 950000 | 4470516 | 1312540 | 3157976 | 1416438 | 0 | 1416438 | 4071000 | 1571000 | 2500000 | 510200 | 0 | 510200 | 357798 | 0 | 357798 | 397798 | 0 | 397798 | 536000 | 491000 | 45000 | 502117 | 477759 | 24358 | 505759 | 477759 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 254542 | 0 | 254542 | 314542 | 0 | 314542 | 75000 | 0 | 75000 | 930 | 0 | 930 | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 15000 | 50000 | 66082 | 28739 | 37343 | 69082 | 28739 | 40343 | 8249737 | 1930540 | 6269197 | 2745310 | 506498 | 2238812 | 6309111 | 2077498 | 4206413 | 8249737 | 1930540 | 6269197 | 2745310 | 506498 | 2238812 | 6309111 | 2077498 | 4206413 | 0 | 0 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | CCI | 2012 | Q2 | Q2 - 2012 | 2078817 | 0 | 2078817 | 606150 | 0 | 606150 | 1200000 | 0 | 1200000 | 4587316 | 1591340 | 2995976 | 3505259 | 1571340 | 1933919 | 4151340 | 1571340 | 2580000 | 510200 | 0 | 510200 | 421875 | 0 | 421875 | 470000 | 0 | 470000 | 355461 | 310461 | 45000 | 331995 | 285320 | 46675 | 346675 | 300000 | 46675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 341276 | 0 | 341276 | 400000 | 0 | 400000 | 75000 | 0 | 75000 | 930 | 0 | 930 | 35000 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78739 | 28739 | 50000 | 71509 | 28739 | 42770 | 78739 | 28739 | 50000 | 8199737 | 1930540 | 6269197 | 5278994 | 1885399 | 3393595 | 6681754 | 1900079 | 4781675 | 8199737 | 1930540 | 6269197 | 5278994 | 1885399 | 3393595 | 6681754 | 1900079 | 4781675 | 0 | 0 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | CCI | 2012 | Q3 | Q3 - 2012 | 1838817 | 0 | 1838817 | 957314 | 0 | 957314 | 1250000 | 0 | 1250000 | 4687316 | 1591340 | 3095976 | 4307940 | 1571340 | 2736600 | 4491340 | 1591340 | 2900000 | 610200 | 0 | 610200 | 477581 | 0 | 477581 | 525000 | 0 | 525000 | 385461 | 310461 | 75000 | 347450 | 285320 | 62130 | 360320 | 285320 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 461371 | 0 | 461371 | 480000 | 0 | 480000 | 75000 | 0 | 75000 | 930 | 0 | 930 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88739 | 28739 | 60000 | 80199 | 28739 | 51460 | 90199 | 28739 | 61460 | 8199737 | 1930540 | 6269197 | 6632785 | 1885399 | 4747386 | 7216859 | 1905399 | 5311460 | 8199737 | 1930540 | 6269197 | 6632785 | 1885399 | 4747386 | 7216859 | 1905399 | 5311460 | 0 | 0 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | CCI | 2012 | Q4 | Q4 - 2012 | 1838817 | 0 | 1838817 | 1098548 | 0 | 1098548 | 1198548 | 0 | 1198548 | 4687316 | 1591340 | 3095976 | 4857158 | 1571340 | 3285818 | 5057158 | 1571340 | 3485818 | 610200 | 0 | 610200 | 547872 | 0 | 547872 | 647872 | 0 | 647872 | 385461 | 310461 | 75000 | 372938 | 285320 | 87618 | 2955818 | 2853200 | 102618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 595025 | 0 | 595025 | 625025 | 0 | 625025 | 75000 | 0 | 75000 | 930 | 0 | 930 | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88739 | 28739 | 60000 | 92441 | 28739 | 63702 | 94441 | 28739 | 65702 | 8199737 | 1930540 | 6269197 | 7564912 | 1885399 | 5679513 | 10579792 | 4453279 | 6126513 | 8199737 | 1930540 | 6269197 | 7564912 | 1885399 | 5679513 | 10579792 | 4453279 | 6126513 | 0 | 0 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | CCI | 2013 | Q1 | Q1 - 2013 | 1838817 | 0 | 1838817 | 1196794 | 0 | 1196794 | 1196794 | 0 | 1196794 | 4687316 | 1591340 | 3095976 | 4984803 | 1571340 | 3413463 | 5184803 | 1571340 | 3613463 | 610200 | 0 | 610200 | 616825 | 24467 | 592358 | 626825 | 34467 | 592358 | 385461 | 310461 | 75000 | 385749 | 285320 | 100429 | 385749 | 285330 | 100429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 641761 | 0 | 641761 | 641761 | 0 | 641761 | 75000 | 0 | 75000 | 930 | 0 | 930 | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88739 | 28739 | 60000 | 95211 | 28739 | 66472 | 95211 | 28739 | 66472 | 8199737 | 1930540 | 6269197 | 7922073 | 1909866 | 6012207 | 8132073 | 1919876 | 6212207 | 8199737 | 1930540 | 6269197 | 7922073 | 1909866 | 6012207 | 8132073 | 1919876 | 6212207 | 0 | 0 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | CCI | 2013 | Q2 | Q2 - 2013 | 1838817 | 0 | 1838817 | 1263241 | 0 | 1263241 | 1263241 | 0 | 1263241 | 4687316 | 1591340 | 3095976 | 5100450 | 1581340 | 3519110 | 5150387 | 1581340 | 3569047 | 610200 | 0 | 610200 | 646571 | 35145 | 611426 | 646571 | 35145 | 611426 | 385461 | 310461 | 75000 | 398173 | 285316 | 112857 | 398173 | 285316 | 112857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514204 | 0 | 514204 | 643878 | 0 | 643878 | 643878 | 0 | 643878 | 75000 | 0 | 75000 | 930 | 0 | 930 | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88739 | 28739 | 60000 | 96557 | 28739 | 67818 | 96557 | 28739 | 67818 | 8199737 | 1930540 | 6269197 | 8149800 | 1930540 | 6219260 | 8199737 | 1930540 | 6269197 | 8199737 | 1930540 | 6269197 | 8149800 | 1930540 | 6219260 | 8199737 | 1930540 | 6269197 | 0 | 0 | JKM Consulting, Inc. | TRUE
NT10BIX5570095 | CCI | 2013 | Q3 | Q3 - 2013 | 1263241 | 0 | 1263241 | 1263241 | 0 | 1263241 | 1263241 | 0 | 1263241 | 5150387 | 1581340 | 3569047 | 5150387 | 1581340 | 3569047 | 5150387 | 1581340 | 3569047 | 646571 | 35145 | 611426 | 646571 | 35145 | 611426 | 646571 | 35145 | 611426 | 398173 | 285316 | 112857 | 398173 | 285316 | 112857 | 398173 | 285316 | 112857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 643878 | 0 | 646878 | 643878 | 0 | 643878 | 643878 | 0 | 643878 | 930 | 0 | 930 | 930 | 0 | 930 | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96557 | 28739 | 67818 | 96557 | 28739 | 67818 | 96557 | 28739 | 67818 | 8199737 | 1930540 | 6272197 | 8199737 | 1930540 | 6269197 | 8199737 | 1930540 | 6269197 | 8199737 | 1930540 | 6272197 | 8199737 | 1930540 | 6269197 | 8199737 | 1930540 | 6269197 | 0 | 0 | JKM Consulting, Inc. | TRUE
NT10BIX5570096 | CCI | 2010 | Q4 | Q4 - 2010 | 66838777 | 28886379 | 37952398 | 0 | 0 | 0 | 600000 | 300000 | 300000 | 2880000 | 0 | 2880000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 450000 | 0 | 0 | 0 | 150000 | 50000 | 100000 | 1500108 | 0 | 1500108 | 0 | 0 | 0 | 150000 | 50000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 0 | 0 | 0 | 700000 | 200000 | 500000 | 280320 | 0 | 280320 | 0 | 0 | 0 | 250000 | 50000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 0 | 0 | 0 | 150000 | 50000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 0 | 0 | 0 | 0 | 0 | 0 | 88274848 | 29386379 | 58888469 | 0 | 0 | 0 | 2000000 | 700000 | 1300000 | 88274848 | 29386379 | 58888469 | 0 | 0 | 0 | 2000000 | 700000 | 1300000 | 0 | 0 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | CCI | 2011 | Q1 | Q1 - 2011 | 66838777 | 28886379 | 37952398 | 1165696 | 1165696 | 0 | 16890019 | 13750000 | 3140019 | 2880000 | 0 | 2880000 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | 450000 | 0 | 450000 | 0 | 0 | 0 | 300000 | 0 | 300000 | 1500108 | 0 | 1500108 | 0 | 0 | 0 | 350000 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 378378 | 193629 | 184749 | 700000 | 150000 | 550000 | 280320 | 0 | 280320 | 235071 | 235071 | 0 | 280320 | 0 | 280320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 0 | 0 | 0 | 300000 | 100000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 88274848 | 29386379 | 58888469 | 1779145 | 1594396 | 184749 | 31000000 | 14000000 | 17000000 | 88274848 | 29386379 | 58888469 | 1779145 | 1594396 | 184749 | 31000000 | 14000000 | 17000000 | 0 | 0 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | CCI | 2011 | Q2 | Q2 - 2011 | 66838777 | 28886379 | 37952398 | 1204724 | 1204724 | 0 | 20500000 | 15500000 | 5000000 | 2880000 | 0 | 2880000 | 0 | 0 | 0 | 2880000 | 0 | 2880000 | 450000 | 0 | 450000 | 0 | 0 | 0 | 185339 | 0 | 185339 | 1500108 | 0 | 1500108 | 13755 | 13755 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 773519 | 773519 | 0 | 2500000 | 500000 | 2000000 | 280320 | 0 | 280320 | 235393 | 50644 | 184749 | 280000 | 0 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 0 | 0 | 0 | 400000 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 45934 | 45934 | 0 | 6000000 | 0 | 6000000 | 88274848 | 29386379 | 58888469 | 2273325 | 2088576 | 184749 | 32820339 | 16000000 | 16820339 | 88274848 | 29386379 | 58888469 | 2273325 | 2088576 | 184749 | 32820339 | 16000000 | 16820339 | 0 | 0 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | CCI | 2011 | Q3 | Q3 - 2011 | 66838777 | 28886379 | 37952398 | 1596909 | 690152 | 906757 | 7797956 | 3370120 | 4427836 | 2880000 | 0 | 2880000 | 33796 | 0 | 33796 | 41956 | 0 | 41956 | 450000 | 0 | 450000 | 0 | 0 | 0 | 133477 | 0 | 133477 | 1500108 | 0 | 1500108 | 13775 | 0 | 13775 | 13775 | 0 | 13775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 1383430 | 166521 | 1216910 | 1978342 | 238129 | 1740213 | 280320 | 0 | 280320 | 235071 | 0 | 235071 | 286278 | 0 | 286278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 70283 | 0 | 70283 | 100733 | 0 | 100733 | 88274848 | 29386379 | 58888469 | 3333264 | 856673 | 2476592 | 10352517 | 3608249 | 6744268 | 88274848 | 29386379 | 58888469 | 3333264 | 856673 | 2476592 | 10352517 | 3608249 | 6744268 | 0 | 0 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | CCI | 2011 | Q4 | Q4 - 2011 | 66838777 | 28886379 | 37952398 | 23996264 | 15247966 | 8748298 | 24599114 | 15247966 | 9351148 | 2880000 | 0 | 2880000 | 41956 | 0 | 41956 | 186956 | 0 | 186956 | 450000 | 0 | 450000 | 22859 | 0 | 22859 | 332607 | 0 | 332607 | 1500108 | 0 | 1500108 | 13775 | 0 | 13775 | 13775 | 0 | 13775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 1939953 | 233508 | 1706445 | 2080453 | 250420 | 1830033 | 280320 | 0 | 280320 | 268989 | 0 | 268989 | 268989 | 0 | 268989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 121399 | 0 | 121399 | 121399 | 0 | 121399 | 88274848 | 29386379 | 58888469 | 26405195 | 15481474 | 10923721 | 27603293 | 15498386 | 12104907 | 88274848 | 29386379 | 58888469 | 26405195 | 15481474 | 10923721 | 27603293 | 15498386 | 12104907 | 0 | 0 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | CCI | 2012 | Q1 | Q1 - 2012 | 66838777 | 28886379 | 37952398 | 24399654 | 15330277 | 9069376 | 24554014 | 15361774 | 9192239 | 2880000 | 0 | 2880000 | 149648 | 0 | 149648 | 240409 | 0 | 240409 | 450000 | 0 | 450000 | 316656 | 0 | 316656 | 316656 | 0 | 316656 | 1500108 | 0 | 1500108 | 24950 | 0 | 24950 | 29897 | 0 | 29897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 2084060 | 250854 | 1833206 | 2084060 | 250854 | 1833206 | 280320 | 0 | 280320 | 269029 | 0 | 269029 | 271042 | 0 | 271042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 0 | 0 | 0 | 18900 | 0 | 18900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 265277 | 0 | 265277 | 268266 | 0 | 268266 | 88274848 | 29386379 | 58888469 | 27509274 | 15581131 | 11928142 | 27783244 | 15612628 | 12170615 | 88274848 | 29386379 | 58888469 | 27509274 | 15581131 | 11928142 | 27783244 | 15612628 | 12170615 | 0 | 0 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | CCI | 2012 | Q2 | Q2 - 2012 | 66838777 | 28886379 | 37952398 | 24039141 | 15232764 | 8806377 | 26039141 | 15232764 | 10806377 | 2880000 | 0 | 2880000 | 269362 | 0 | 269362 | 519362 | 0 | 519362 | 450000 | 0 | 450000 | 493621 | 0 | 493621 | 493621 | 0 | 493621 | 1500108 | 0 | 1500108 | 50231 | 0 | 50231 | 50231 | 0 | 50231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 2226370 | 340317 | 1886053 | 2426370 | 340317 | 2086053 | 280320 | 0 | 280320 | 269351 | 0 | 269351 | 299351 | 0 | 299351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 18900 | 0 | 18900 | 21600 | 0 | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 291087 | 0 | 291087 | 679816 | 0 | 679816 | 88274848 | 29386379 | 58888469 | 27658063 | 15573081 | 12084982 | 30529492 | 15573081 | 14956411 | 88274848 | 29386379 | 58888469 | 27658063 | 15573081 | 12084982 | 30529492 | 15573081 | 14956411 | 0 | 0 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | CCI | 2012 | Q3 | Q3 - 2012 | 66838777 | 28886379 | 37952398 | 24741799 | 15232764 | 9509035 | 25714499 | 15232764 | 10481735 | 2880000 | 0 | 2880000 | 983050 | 0 | 983050 | 1508400 | 0 | 1508400 | 450000 | 0 | 450000 | 507474 | 0 | 507474 | 507474 | 0 | 507474 | 1500108 | 0 | 1500108 | 45626 | 0 | 45626 | 70626 | 0 | 70626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 2556055 | 340317 | 2215738 | 2626370 | 340317 | 2286053 | 280320 | 0 | 280320 | 271364 | 0 | 271364 | 314351 | 0 | 314351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 25100 | 0 | 25100 | 84100 | 0 | 84100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 608486 | 0 | 608486 | 701346 | 0 | 701346 | 88274848 | 29386379 | 58888469 | 29738954 | 15573081 | 14165873 | 31527166 | 15573081 | 15954085 | 88274848 | 29386379 | 58888469 | 29738954 | 15573081 | 14165873 | 31527166 | 15573081 | 15954085 | 0 | 0 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | CCI | 2012 | Q4 | Q4 - 2012 | 66838777 | 28886379 | 37952398 | 25119267 | 15232764 | 9886503 | 27585529 | 15232764 | 12352765 | 2880000 | 0 | 2880000 | 1687845 | 0 | 1687845 | 2880000 | 0 | 2880000 | 450000 | 0 | 450000 | 507829 | 0 | 507829 | 507829 | 0 | 507829 | 1500108 | 0 | 1500108 | 68726 | 0 | 68726 | 101226 | 0 | 101226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4153932 | 500000 | 3653932 | 2820454 | 340317 | 2480137 | 3291114 | 340317 | 2950797 | 280320 | 0 | 280320 | 271364 | 0 | 271364 | 314351 | 0 | 314351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992050 | 0 | 992050 | 25100 | 0 | 25100 | 84100 | 0 | 84100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11179661 | 0 | 11179661 | 755414 | 0 | 755414 | 855500 | 0 | 855500 | 88274848 | 29386379 | 58888469 | 31255999 | 15573081 | 15682918 | 35619649 | 15573081 | 20046568 | 88274848 | 29386379 | 58888469 | 31255999 | 15573081 | 15682918 | 35619649 | 15573081 | 20046568 | 0 | 0 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | CCI | 2013 | Q1 | Q1 - 2013 | 38700857 | 15247966 | 23452891 | 26546919 | 15192227 | 11354692 | 30139677 | 15192227 | 14947450 | 40591368 | 14138413 | 26452955 | 5060043 | 324543 | 4735500 | 15059845 | 324543 | 14735303 | 1550790 | 0 | 1550790 | 739404 | 0 | 739404 | 943999 | 0 | 943999 | 100000 | 0 | 100000 | 85200 | 0 | 85200 | 85200 | 0 | 85200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6250000 | 0 | 6250000 | 2959275 | 0 | 2959275 | 3773524 | 0 | 3773524 | 425000 | 0 | 425000 | 348410 | 0 | 348410 | 367410 | 0 | 367410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646833 | 0 | 646833 | 536900 | 0 | 536900 | 612874 | 0 | 612874 | 88274848 | 29386379 | 58888469 | 36276151 | 15516770 | 20759381 | 50992529 | 15516770 | 35475760 | 88274848 | 29386379 | 58888469 | 36276151 | 15516770 | 20759381 | 50992529 | 15516770 | 35475760 | 0 | 0 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | CCI | 2013 | Q2 | Q2 - 2013 | 38700857 | 15247966 | 23452891 | 27796334 | 15192227 | 12604107 | 30139677 | 15192227 | 14947450 | 40591368 | 14138413 | 26452955 | 10166767 | 324543 | 9842224 | 15166767 | 324543 | 14842224 | 1550790 | 0 | 1550790 | 755929 | 0 | 755929 | 943999 | 0 | 943999 | 100000 | 0 | 100000 | 85200 | 0 | 85200 | 90200 | 0 | 90200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6250000 | 0 | 6250000 | 3620656 | 0 | 3620656 | 4470656 | 0 | 4470656 | 425000 | 0 | 425000 | 379243 | 0 | 379243 | 405243 | 0 | 405243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646833 | 0 | 646833 | 605843 | 0 | 605843 | 646833 | 0 | 646833 | 88274848 | 29386379 | 58888469 | 43409972 | 15516770 | 27893202 | 51873375 | 15516770 | 36356605 | 88274848 | 29386379 | 58888469 | 43409972 | 15516770 | 27893202 | 51873375 | 15516770 | 36356605 | 0 | 0 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | CCI | 2013 | Q3 | Q3 - 2013 | 35646004 | 10474987 | 25171017 | 26162397 | 10474987 | 15687410 | 33033707 | 10474987 | 22558720 | 29598639 | 4247130 | 25351509 | 15246956 | 324543 | 14922413 | 24075646 | 324543 | 23751103 | 2194110 | 0 | 2194110 | 1128864 | 0 | 1128864 | 1760800 | 0 | 1760800 | 125000 | 0 | 125000 | 85200 | 0 | 85200 | 90200 | 0 | 90200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950000 | 0 | 4950000 | 4109066 | 0 | 4109066 | 4602182 | 0 | 4602182 | 425000 | 0 | 425000 | 396995 | 0 | 396995 | 405243 | 0 | 405243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661833 | 0 | 661833 | 660921 | 0 | 660921 | 661833 | 0 | 661833 | 73610586 | 14722117 | 58888469 | 47790399 | 10799530 | 36990869 | 64639611 | 10799530 | 53840081 | 73610586 | 14722117 | 58888469 | 47790399 | 10799530 | 36990869 | 64639611 | 10799530 | 53840081 | 0 | 0 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570096 | CCI | 2013 | Q4 | Q4 - 2013 | 35646004 | 10474987 | 25171017 | 28195238 | 10474987 | 17720251 | 30224987 | 10474987 | 19750000 | 29598639 | 4247130 | 25351509 | 18160441 | 324543 | 17835898 | 21160441 | 324543 | 20835898 | 2194110 | 0 | 2194110 | 1472688 | 0 | 1472688 | 1532688 | 0 | 1532688 | 125000 | 0 | 125000 | 88700 | 0 | 88700 | 93200 | 0 | 93200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950000 | 0 | 4950000 | 4561607 | 0 | 4561607 | 4696607 | 0 | 4696607 | 425000 | 0 | 425000 | 276697 | 0 | 276697 | 300000 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661833 | 0 | 661833 | 666882 | 0 | 666882 | 666882 | 0 | 666882 | 73610586 | 14722117 | 58888469 | 53422253 | 10799530 | 42622723 | 58679805 | 10799530 | 47880275 | 73610586 | 14722117 | 58888469 | 53422253 | 10799530 | 42622723 | 58679805 | 10799530 | 47880275 | 0 | 0 | Virgin Islands Public Finance Authority | TRUE
NT10BIX5570097 | CCI | 2010 | Q4 | Q4 - 2010 | 23203458 | 0 | 23203458 | 0 | 0 | 0 | 0 | 0 | 0 | 5563136 | 4049216 | 1513920 | 0 | 0 | 0 | 0 | 0 | 0 | 2708999 | 0 | 2708999 | 17181 | 0 | 17181 | 111984 | 0 | 111984 | 3390037 | 0 | 3390037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314083 | 0 | 7314083 | 0 | 0 | 0 | 322500 | 0 | 322500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860283 | 1350783 | 509500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 55700000 | 17000003 | 38699997 | 17181 | 0 | 17181 | 434484 | 0 | 434484 | 55700000 | 17000003 | 38699997 | 17181 | 0 | 17181 | 434484 | 0 | 434484 | 0 | 0 | Department of Information Technology | TRUE
NT10BIX5570097 | CCI | 2011 | Q1 | Q1 - 2011 | 23203458 | 0 | 23203458 | 0 | 0 | 0 | 0 | 0 | 0 | 5563136 | 4049216 | 1513920 | 0 | 0 | 0 | 0 | 0 | 0 | 2708999 | 0 | 2708999 | 106476 | 0 | 106476 | 338766 | 0 | 338766 | 3390037 | 0 | 3390037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314083 | 0 | 7314083 | 612682 | 0 | 612682 | 793884 | 0 | 793884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860283 | 1350783 | 509500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 55700000 | 17000003 | 38699997 | 719158 | 0 | 719158 | 1132650 | 0 | 1132650 | 55700000 | 17000003 | 38699997 | 719158 | 0 | 719158 | 1132650 | 0 | 1132650 | 0 | 0 | Department of Information Technology | TRUE
NT10BIX5570097 | CCI | 2011 | Q2 | Q2 - 2011 | 23203458 | 0 | 23203458 | 0 | 0 | 0 | 0 | 0 | 0 | 5563136 | 4049216 | 1513920 | 0 | 0 | 0 | 0 | 0 | 0 | 2708999 | 0 | 2708999 | 200375 | 0 | 200375 | 338766 | 0 | 338766 | 3390037 | 0 | 3390037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314083 | 0 | 7314083 | 346235 | 0 | 346235 | 793884 | 0 | 793884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860283 | 1350783 | 509500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 136652 | 136652 | 0 | 11601004 | 11600004 | 1000 | 55700000 | 17000003 | 38699997 | 683262 | 136652 | 546610 | 12733654 | 11600004 | 1133650 | 55700000 | 17000003 | 38699997 | 683262 | 136652 | 546610 | 12733654 | 11600004 | 1133650 | 0 | 0 | Department of Information Technology | TRUE
NT10BIX5570097 | CCI | 2011 | Q3 | Q3 - 2011 | 23203458 | 0 | 23203458 | 0 | 0 | 0 | 0 | 0 | 0 | 5563136 | 4049216 | 1513920 | 0 | 0 | 0 | 0 | 0 | 0 | 2708999 | 0 | 2708999 | 315346 | 0 | 315346 | 578815 | 0 | 578815 | 3390037 | 0 | 3390037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314083 | 0 | 7314083 | 630034 | 0 | 630034 | 1309151 | 0 | 1309151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860283 | 1350783 | 509500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 12545384 | 11600004 | 945380 | 13487970 | 11600004 | 1887966 | 55700000 | 17000003 | 38699997 | 12545384 | 11600004 | 945380 | 13487970 | 11600004 | 1887966 | 0 | 0 | Department of Information Technology | TRUE
NT10BIX5570097 | CCI | 2011 | Q4 | Q4 - 2011 | 23203458 | 0 | 23203458 | 0 | 0 | 0 | 3615000 | 0 | 3615000 | 5563136 | 4049216 | 1513920 | 0 | 0 | 0 | 1030000 | 0 | 1030000 | 2708999 | 0 | 2708999 | 439427 | 0 | 439427 | 624795 | 0 | 624795 | 3390037 | 0 | 3390037 | 0 | 0 | 0 | 1040000 | 0 | 1040000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314083 | 0 | 7314083 | 763336 | 0 | 763336 | 1733536 | 0 | 1733536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860283 | 1350783 | 509500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 12802767 | 11600004 | 1202763 | 19643335 | 11600004 | 8043331 | 55700000 | 17000003 | 38699997 | 12802767 | 11600004 | 1202763 | 19643335 | 11600004 | 8043331 | 0 | 0 | Department of Information Technology | TRUE
NT10BIX5570097 | CCI | 2012 | Q1 | Q1 - 2012 | 23203458 | 0 | 23203458 | 4583020 | 0 | 4583020 | 12387586 | 2752260 | 9635326 | 5563136 | 4049216 | 1513920 | 0 | 0 | 0 | 850000 | 0 | 850000 | 2708999 | 0 | 2708999 | 611703 | 0 | 611703 | 770000 | 0 | 770000 | 3390037 | 0 | 3390037 | 92709 | 0 | 92709 | 2359690 | 2245188 | 114502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314083 | 0 | 7314083 | 931257 | 0 | 931257 | 1800000 | 0 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860283 | 1350783 | 509500 | 0 | 0 | 0 | 102000 | 0 | 102000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 17818693 | 11600004 | 6218689 | 29869280 | 16597452 | 13271828 | 55700000 | 17000003 | 38699997 | 17818693 | 11600004 | 6218689 | 29869280 | 16597452 | 13271828 | 0 | 0 | Department of Information Technology | TRUE
NT10BIX5570097 | CCI | 2012 | Q2 | Q2 - 2012 | 23203458 | 0 | 23203458 | 12633420 | 3089119 | 9544301 | 13268420 | 3089118 | 10179301 | 5563136 | 4049216 | 1513920 | 522421 | 0 | 522421 | 4437421 | 0 | 4437421 | 2708999 | 0 | 2708999 | 942061 | 0 | 942062 | 1076691 | 0 | 1076691 | 3390037 | 0 | 3390037 | 2337897 | 2245188 | 92709 | 2337897 | 2245188 | 92710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7314083 | 0 | 7314083 | 1781567 | 0 | 1781567 | 1935567 | 0 | 1935567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860283 | 1350783 | 509500 | 0 | 0 | 0 | 363000 | 0 | 363000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 29817370 | 16934311 | 12883060 | 35019000 | 16934310 | 18084690 | 55700000 | 17000003 | 38699997 | 29817370 | 16934311 | 12883060 | 35019000 | 16934310 | 18084690 | 0 | 0 | Department of Information Technology | TRUE
NT10BIX5570097 | CCI | 2012 | Q3 | Q3 - 2012 | 19736716 | 3089118 | 16647597 | 13147458 | 3089119 | 10058339 | 14628608 | 3089118 | 11539490 | 6501107 | 0 | 6501107 | 1373527 | 0 | 1373527 | 6230762 | 0 | 6230762 | 2708999 | 0 | 2708999 | 1091723 | 0 | 1091723 | 1166723 | 0 | 1166723 | 2384958 | 2245188 | 139770 | 2359690 | 2245188 | 114502 | 2359690 | 2245188 | 114502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050223 | 65693 | 8984531 | 2249023 | 0 | 2249023 | 2249023 | 0 | 2249023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 553385 | 0 | 553385 | 1442288 | 0 | 1442288 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 32374810 | 16934311 | 15440499 | 39677098 | 16934310 | 22742788 | 55700000 | 17000003 | 38699997 | 32374810 | 16934311 | 15440499 | 39677098 | 16934310 | 22742788 | 0 | 0 | Department of Information Technology | TRUE
NT10BIX5570097 | CCI | 2012 | Q4 | Q4 - 2012 | 19736716 | 3089118 | 16647597 | 14908008 | 3089119 | 11818890 | 15722164 | 3089118 | 12633046 | 6501107 | 0 | 6501107 | 4094121 | 0 | 4094121 | 4775972 | 0 | 4775972 | 2708999 | 0 | 2708999 | 1244330 | 0 | 1244330 | 1374734 | 0 | 1374734 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050223 | 65693 | 8984531 | 2820220 | 0 | 2820220 | 3654079 | 0 | 3654079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 840542 | 0 | 840542 | 852857 | 0 | 852857 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 37883470 | 16934311 | 20949160 | 40356055 | 16934310 | 23421745 | 55700000 | 17000003 | 38699997 | 37883470 | 16934311 | 20949160 | 40356055 | 16934310 | 23421745 | 0 | 0 | Department of Information Technology | TRUE
NT10BIX5570097 | CCI | 2013 | Q1 | Q1 - 2013 | 19736716 | 3089118 | 16647597 | 15183545 | 3089118 | 12094426 | 16983544 | 3089118 | 13894426 | 6501107 | 0 | 6501107 | 5065559 | 0 | 5065559 | 5267269 | 0 | 5267269 | 2708999 | 0 | 2708999 | 1341636 | 0 | 1341636 | 1423436 | 0 | 1423436 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050223 | 65693 | 8984531 | 3399393 | 0 | 3399393 | 3741393 | 0 | 3741393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 1065045 | 0 | 1065045 | 1325098 | 0 | 1325098 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 40031427 | 16934310 | 23097116 | 42716989 | 16934310 | 25782679 | 55700000 | 17000003 | 38699997 | 40031427 | 16934310 | 23097116 | 42716989 | 16934310 | 25782679 | 0 | 0 | Department of Information Technology | TRUE
NT10BIX5570097 | CCI | 2013 | Q2 | Q2 - 2013 | 19736716 | 3089118 | 16647597 | 17166021 | 3089118 | 14076903 | 17527021 | 3089118 | 14437903 | 6501107 | 0 | 6501107 | 5408302 | 0 | 5408302 | 5661302 | 0 | 5661302 | 2708999 | 0 | 2708999 | 1464819 | 0 | 1464819 | 1502819 | 0 | 1502819 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050223 | 65693 | 8984531 | 4019255 | 0 | 4019255 | 4785255 | 0 | 4785255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 1451503 | 0 | 1451503 | 1501503 | 0 | 1501503 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 43486149 | 16934310 | 26551839 | 44954149 | 16934310 | 28019839 | 55700000 | 17000003 | 38699997 | 43486149 | 16934310 | 26551839 | 44954149 | 16934310 | 28019839 | 0 | 0 | Department of Information Technology | TRUE
NT10BIX5570097 | CCI | 2013 | Q3 | Q3 - 2013 | 19736716 | 3089118 | 16647597 | 17583018 | 3089118 | 14493900 | 17596518 | 3089118 | 14507400 | 6501107 | 0 | 6501107 | 5556919 | 0 | 5556919 | 5556919 | 0 | 5556919 | 2708999 | 0 | 2708999 | 1591060 | 0 | 1591060 | 1695760 | 0 | 1695760 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050223 | 65693 | 8984531 | 4404785 | 1605 | 4403180 | 5263685 | 1605 | 5262080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 1536416 | 0 | 1536416 | 1580016 | 0 | 1580016 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 44648447 | 16935915 | 27712532 | 45669147 | 16935915 | 28733232 | 55700000 | 17000003 | 38699997 | 44648447 | 16935915 | 27712532 | 45669147 | 16935915 | 28733232 | 0 | 0 | Department of Information Technology | TRUE
NT10BIX5570097 | CCI | 2013 | Q4 | Q4 - 2013 | 19736715 | 3089118 | 16647597 | 16687691 | 3089118 | 13598573 | 16790659 | 3089118 | 13701541 | 6501107 | 0 | 6501107 | 5662000 | 0 | 5662000 | 5675466 | 0 | 5675466 | 2708999 | 0 | 2708999 | 2358455 | 0 | 2358455 | 2423389 | 0 | 2423389 | 2384958 | 2245188 | 139770 | 2376245 | 2245188 | 131057 | 2376245 | 2245188 | 131057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050224 | 65693 | 8984531 | 5948349 | 1605 | 5946744 | 6109349 | 1605 | 6107744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2157993 | 0 | 2157993 | 1421698 | 0 | 1421698 | 1421698 | 0 | 1421698 | 1500000 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 11660004 | 11600004 | 60000 | 11600004 | 11600004 | 0 | 11600004 | 11600004 | 0 | 55700000 | 17000003 | 38699997 | 46054442 | 16935915 | 29118527 | 46396810 | 16935915 | 29460895 | 55700000 | 17000003 | 38699997 | 46054442 | 16935915 | 29118527 | 46396810 | 16935915 | 29460895 | 0 | 0 | Department of Information Technology | TRUE
NT10BIX5570098 | CCI | 2010 | Q4 | Q4 - 2010 | 8573312 | 1714663 | 6858649 | 0 | 0 | 0 | 275255 | 0 | 275255 | 69013409 | 13802688 | 55210721 | 0 | 0 | 0 | 118230 | 0 | 118230 | 15109345 | 3021870 | 12087475 | 670517 | 0 | 670517 | 2069215 | 0 | 2069215 | 2285826 | 457166 | 1828660 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 201040 | 0 | 201040 | 706383 | 0 | 706383 | 2906663 | 581333 | 2325330 | 689972 | 0 | 689972 | 1586856 | 0 | 1586856 | 164635 | 32927 | 131708 | 0 | 0 | 0 | 0 | 0 | 0 | 314813 | 62963 | 251850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 0 | 0 | 0 | 0 | 0 | 0 | 101435997 | 20287209 | 81148788 | 1561529 | 0 | 1561529 | 4805939 | 0 | 4805939 | 101435997 | 20287209 | 81148788 | 1561529 | 0 | 1561529 | 4805939 | 0 | 4805939 | 0 | 0 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | CCI | 2011 | Q1 | Q1 - 2011 | 8573312 | 1714663 | 6858649 | 83572 | 0 | 83572 | 512924 | 0 | 512924 | 69013409 | 13802688 | 55210721 | 10905 | 0 | 10905 | 20905 | 0 | 20905 | 15109345 | 3021870 | 12087475 | 1322396 | 0 | 1322396 | 2178121 | 0 | 2178121 | 2285826 | 457166 | 1828660 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 475069 | 0 | 475069 | 855069 | 0 | 855069 | 2906663 | 581333 | 2325330 | 1294849 | 0 | 1294849 | 1968849 | 0 | 1968849 | 164635 | 32927 | 131708 | 0 | 0 | 0 | 0 | 0 | 0 | 314813 | 62963 | 251850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 0 | 0 | 0 | 0 | 0 | 0 | 101435997 | 20287209 | 81148788 | 3186791 | 0 | 3186791 | 5537868 | 0 | 5537868 | 101435997 | 20287209 | 81148788 | 3186791 | 0 | 3186791 | 5537868 | 0 | 5537868 | 0 | 0 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | CCI | 2011 | Q2 | Q2 - 2011 | 8573312 | 1714663 | 6858649 | 547342 | 0 | 547342 | 565542 | 0 | 595542 | 69013409 | 13802688 | 55210721 | 25621 | 0 | 25621 | 25621 | 0 | 25621 | 15109345 | 3021870 | 12087475 | 1795952 | 0 | 1795952 | 2664952 | 0 | 2664952 | 2285826 | 457166 | 1828660 | 18655 | 0 | 18655 | 599927 | 0 | 599927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 751122 | 0 | 751122 | 854571 | 0 | 854571 | 2906663 | 581333 | 2325330 | 1750866 | 0 | 1750866 | 2315866 | 0 | 2315866 | 164635 | 32927 | 131708 | 0 | 0 | 0 | 0 | 0 | 0 | 314813 | 62963 | 251850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 0 | 0 | 0 | 0 | 0 | 0 | 101435997 | 20287209 | 81148788 | 4889558 | 0 | 4889558 | 7026479 | 0 | 7056479 | 101435997 | 20287209 | 81148788 | 4889558 | 0 | 4889558 | 7026479 | 0 | 7056479 | 0 | 0 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | CCI | 2011 | Q3 | Q3 - 2011 | 8573312 | 1714663 | 6858649 | 633739 | 0 | 633739 | 1251654 | 161594 | 1090060 | 69013409 | 13802688 | 55210721 | 35669 | 0 | 35669 | 4674258 | 603473 | 4070786 | 15109345 | 3021870 | 12087475 | 2504630 | 0 | 2504630 | 4260484 | 550051 | 3710432 | 2285826 | 457166 | 1828660 | 17237 | 0 | 17237 | 67237 | 8681 | 58556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 1034923 | 0 | 1034923 | 2330923 | 300935 | 2029988 | 2906663 | 571333 | 2325330 | 2374478 | 0 | 2374478 | 2906663 | 375266 | 2531397 | 164635 | 32927 | 131708 | 0 | 0 | 0 | 0 | 0 | 0 | 314813 | 62963 | 251850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 0 | 0 | 0 | 0 | 0 | 0 | 101435997 | 20277209 | 81148788 | 6600676 | 0 | 6600676 | 15491219 | 2000000 | 13491219 | 101435997 | 20277209 | 81148788 | 6600676 | 0 | 6600676 | 15491219 | 2000000 | 13491219 | 0 | 0 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | CCI | 2011 | Q4 | Q4 - 2011 | 8573312 | 1714663 | 6858649 | 787561 | 0 | 787561 | 5486319 | 405607 | 5080712 | 69013409 | 13802688 | 55210721 | 4975289 | 0 | 4975289 | 8238333 | 609065 | 7629268 | 15109345 | 3021870 | 12087475 | 3483698 | 0 | 3483698 | 6556933 | 484758 | 6072175 | 2285826 | 457166 | 1828660 | 37323 | 0 | 37323 | 697583 | 51573 | 646010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 1576914 | 0 | 1576914 | 2200220 | 162664 | 2037556 | 2906663 | 581333 | 2325330 | 2681887 | 0 | 2681887 | 3873003 | 286333 | 3586670 | 164635 | 32927 | 131708 | 0 | 0 | 0 | 0 | 0 | 0 | 314813 | 62963 | 251850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 0 | 0 | 0 | 0 | 0 | 0 | 101435997 | 20287209 | 81148788 | 13542672 | 0 | 13542672 | 27052391 | 2000000 | 25052391 | 101435997 | 20287209 | 81148788 | 13542672 | 0 | 13542672 | 27052391 | 2000000 | 25052391 | 0 | 0 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | CCI | 2012 | Q1 | Q1 - 2012 | 8573312 | 1714663 | 6858649 | 1008050 | 0 | 1008050 | 6612476 | 961341 | 5651135 | 69013409 | 13802688 | 55210721 | 7373202 | 0 | 7373202 | 24675637 | 3587415 | 21088222 | 15109345 | 3021870 | 12087475 | 4822682 | 0 | 4822682 | 8295003 | 1206432 | 7088571 | 2285826 | 457166 | 1828660 | 56598 | 0 | 56598 | 2087728 | 303520 | 1784208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 2147561 | 0 | 2147561 | 2664740 | 387408 | 2277332 | 2906663 | 581333 | 2325330 | 3981764 | 0 | 3981764 | 5185503 | 753884 | 4431619 | 164635 | 32927 | 131708 | 0 | 0 | 0 | 0 | 0 | 0 | 314813 | 62963 | 251850 | 3300 | 0 | 3300 | 3300 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 0 | 0 | 0 | 0 | 0 | 0 | 101435997 | 20287209 | 81148788 | 19393157 | 0 | 19393157 | 49524387 | 7200000 | 42324387 | 101435997 | 20287209 | 81148788 | 19393157 | 0 | 19393157 | 49524387 | 7200000 | 42324387 | 0 | 0 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | CCI | 2012 | Q2 | Q2 - 2012 | 8573312 | 1714663 | 6858649 | 4645336 | 0 | 4645336 | 5670794 | 242055 | 5428739 | 69013409 | 13802688 | 55210721 | 12896961 | 0 | 12896961 | 24952423 | 2845641 | 22106782 | 15109345 | 3021870 | 12087475 | 6104533 | 0 | 6104533 | 7789858 | 397814 | 7392044 | 2285826 | 457166 | 1828660 | 555290 | 0 | 555290 | 1057562 | 118559 | 939003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 2875069 | 0 | 2875069 | 3393159 | 122293 | 3270866 | 2906663 | 581333 | 2325330 | 3857870 | 0 | 3857870 | 5739638 | 444183 | 5295455 | 164635 | 32927 | 131708 | 0 | 0 | 0 | 125667 | 29663 | 96004 | 314813 | 62963 | 251850 | 23800 | 0 | 23800 | 342000 | 75110 | 266890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 2169 | 0 | 2169 | 2169 | 0 | 2169 | 101435997 | 20287209 | 81148788 | 30961028 | 0 | 30961028 | 49073270 | 4275318 | 44797952 | 101435997 | 20287209 | 81148788 | 30961028 | 0 | 30961028 | 49073270 | 4275318 | 44797952 | 0 | 0 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | CCI | 2012 | Q3 | Q3 - 2012 | 8573312 | 1714663 | 6858649 | 3182393 | 32196 | 3150197 | 6371092 | 654944 | 5716148 | 69013409 | 13802688 | 55210721 | 17539985 | 100241 | 17439744 | 34228438 | 3518660 | 30709778 | 15109345 | 3021870 | 12087475 | 7364717 | 352204 | 7012513 | 10174341 | 1045914 | 9128427 | 2285826 | 457166 | 1828660 | 1101620 | 508809 | 592811 | 1970597 | 600000 | 1370597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 3344057 | 33358 | 3310699 | 3578718 | 268019 | 3310699 | 2906663 | 581333 | 2325330 | 4419970 | 377282 | 4042688 | 5557749 | 671204 | 4886545 | 164635 | 32927 | 131708 | 65130 | 65130 | 0 | 348481 | 66000 | 282481 | 314813 | 62963 | 251850 | 28850 | 0 | 28850 | 734540 | 75510 | 659030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 3753 | 0 | 3753 | 95953 | 9864 | 86089 | 101435997 | 20287209 | 81148788 | 37050475 | 1469220 | 35581255 | 63059909 | 6910115 | 56149794 | 101435997 | 20287209 | 81148788 | 37050475 | 1469220 | 35581255 | 63059909 | 6910115 | 56149794 | 0 | 0 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | CCI | 2012 | Q4 | Q4 - 2012 | 8573312 | 1714663 | 6858649 | 3521288 | 306094 | 3215194 | 4729325 | 691260 | 4038065 | 69013409 | 13802688 | 55210721 | 22683418 | 2257744 | 20425674 | 43614731 | 5639548 | 37975183 | 15109345 | 3021870 | 12087475 | 8621554 | 1049511 | 7572043 | 9778030 | 1429202 | 8348828 | 2285826 | 457166 | 1828660 | 1780676 | 558509 | 1222167 | 1781245 | 558509 | 1222736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 3664860 | 173337 | 3491523 | 3954949 | 400000 | 3554949 | 2906663 | 581333 | 2325330 | 5491185 | 1292902 | 4198283 | 7282089 | 1450000 | 5832089 | 164635 | 32927 | 131708 | 288790 | 173375 | 115415 | 581347 | 175000 | 406347 | 314813 | 62963 | 251850 | 537173 | 222312 | 314861 | 754927 | 250000 | 504927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 3753 | 0 | 3753 | 100477 | 14686 | 85791 | 101435997 | 20287209 | 81148788 | 46592697 | 6033784 | 40558913 | 72577120 | 10608205 | 61968915 | 101435997 | 20287209 | 81148788 | 46592697 | 6033784 | 40558913 | 72577120 | 10608205 | 61968915 | 0 | 0 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | CCI | 2013 | Q1 | Q1 - 2013 | 8573312 | 1714663 | 6858649 | 5726883 | 306094 | 5420789 | 6934920 | 1073785 | 5861135 | 69013409 | 13802688 | 55210721 | 29454768 | 2700805 | 26753963 | 50386081 | 7801652 | 42584429 | 15109345 | 3021870 | 12087475 | 9796055 | 1068443 | 8727612 | 10952531 | 1401390 | 9551141 | 2285826 | 457166 | 1828660 | 1991953 | 558509 | 1433444 | 1992522 | 558509 | 1434013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 3949901 | 173337 | 3776564 | 4239990 | 400000 | 3839990 | 2906663 | 581333 | 2325330 | 6292675 | 1292902 | 4999773 | 8083579 | 1400000 | 6683579 | 164635 | 32927 | 131708 | 500107 | 173375 | 326732 | 792664 | 180000 | 612664 | 314813 | 62963 | 251850 | 619485 | 222312 | 397173 | 837239 | 225000 | 612239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 3753 | 0 | 3753 | 100478 | 15558 | 84920 | 101435997 | 20287209 | 81148788 | 58335580 | 6495777 | 51839803 | 84320004 | 13055894 | 71264110 | 101435997 | 20287209 | 81148788 | 58335580 | 6495777 | 51839803 | 84320004 | 13055894 | 71264110 | 0 | 82500 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | CCI | 2013 | Q2 | Q2 - 2013 | 8573312 | 1714663 | 6858649 | 6147574 | 306094 | 5841480 | 6245351 | 306094 | 5939257 | 69013409 | 13802688 | 55210721 | 50673329 | 4983701 | 45689628 | 62691124 | 12379864 | 50311260 | 15109345 | 3021870 | 12087475 | 10887560 | 1082193 | 9805367 | 11690383 | 1782193 | 9908190 | 2285826 | 457166 | 1828660 | 2114768 | 558509 | 1556259 | 2114769 | 558509 | 1556260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 4231418 | 173337 | 4058081 | 4421618 | 200000 | 4221618 | 2906663 | 581333 | 2325330 | 8248413 | 1292902 | 6955511 | 8420960 | 1400000 | 7020960 | 164635 | 32927 | 131708 | 812721 | 173375 | 639346 | 961121 | 180000 | 781121 | 314813 | 62963 | 251850 | 628118 | 222312 | 405806 | 630619 | 224250 | 406369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 3753 | 0 | 3753 | 3753 | 0 | 3753 | 101435997 | 20287209 | 81148788 | 83747654 | 8792423 | 74955231 | 97179698 | 17030910 | 80148788 | 101435997 | 20287209 | 81148788 | 83747654 | 8792423 | 74955231 | 97179698 | 17030910 | 80148788 | 0 | 96250 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | CCI | 2013 | Q3 | Q3 - 2013 | 8573312 | 1714663 | 6858649 | 6561964 | 519829 | 6042135 | 6700000 | 657865 | 6042135 | 69013409 | 13802688 | 55210721 | 59642229 | 9712630 | 49929599 | 62940353 | 13010754 | 49929599 | 15109345 | 3021870 | 12087475 | 11990484 | 1695591 | 10294893 | 13500000 | 3205107 | 10294893 | 2285826 | 457166 | 1828660 | 2123968 | 559709 | 1564259 | 2132905 | 568646 | 1564259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 4404517 | 267644 | 4136873 | 4601618 | 464745 | 4136873 | 2906663 | 581333 | 2325330 | 8704103 | 1384116 | 7319987 | 9000000 | 1680013 | 7319987 | 164635 | 32927 | 131708 | 933070 | 233449 | 699621 | 961121 | 261500 | 699621 | 314813 | 62963 | 251850 | 1369407 | 229903 | 1139504 | 1500000 | 360496 | 1139504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 45276 | 23359 | 21917 | 100000 | 78083 | 21917 | 101435997 | 20287209 | 81148788 | 95775018 | 14626230 | 81148788 | 101435997 | 20287209 | 81148788 | 101435997 | 20287209 | 81148788 | 95775018 | 14626230 | 81148788 | 101435997 | 20287209 | 81148788 | 0 | 110000 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570098 | CCI | 2013 | Q4 | Q4 - 2013 | 8573312 | 1714663 | 6858649 | 7034196 | 992061 | 6042135 | 7442135 | 1400000 | 6042135 | 69013409 | 13802688 | 55210721 | 64822747 | 14893148 | 49929599 | 68866898 | 18937299 | 49929599 | 15109345 | 3021870 | 12087475 | 12200574 | 1905681 | 10294893 | 13694893 | 3400000 | 10294893 | 2285826 | 457166 | 1828660 | 2141817 | 577558 | 1564259 | 2164259 | 600000 | 1564259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3006194 | 601239 | 2404955 | 4455295 | 318422 | 4136873 | 4536873 | 400000 | 4136873 | 2906663 | 581333 | 2325330 | 8827755 | 1507768 | 7319987 | 9119987 | 1800000 | 7319987 | 164635 | 32927 | 131708 | 971655 | 272034 | 699621 | 1049621 | 350000 | 699621 | 314813 | 62963 | 251850 | 1414822 | 275318 | 1139504 | 1489504 | 350000 | 1139504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61800 | 12360 | 49440 | 133059 | 111142 | 21917 | 221917 | 200000 | 21917 | 101435997 | 20287209 | 81148788 | 102001920 | 20853132 | 81148788 | 108586087 | 27437299 | 81148788 | 101435997 | 20287209 | 81148788 | 102001920 | 20853132 | 81148788 | 108586087 | 27437299 | 81148788 | 0 | 199525 | California Broadband Cooperative, Inc. | TRUE
NT10BIX5570099 | CCI | 2010 | Q4 | Q4 - 2010 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 4535892 | 907179 | 3628713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 0 | 0 | 0 | 50400 | 10080 | 40320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 0 | 0 | 0 | 50400 | 10080 | 40320 | 7058092 | 1411619 | 5646473 | 0 | 0 | 0 | 50400 | 10080 | 40320 | 0 | 0 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | CCI | 2011 | Q1 | Q1 - 2011 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 4535892 | 907179 | 3628713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 36715 | 7343 | 29372 | 140000 | 112000 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 36715 | 7343 | 29372 | 140000 | 112000 | 28000 | 7058092 | 1411619 | 5646473 | 36715 | 7343 | 29372 | 140000 | 112000 | 28000 | 0 | 0 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | CCI | 2011 | Q2 | Q2 - 2011 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 4535892 | 907179 | 3628713 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 207221 | 41444 | 165777 | 282000 | 56400 | 225600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 207221 | 41444 | 165777 | 387000 | 77400 | 309600 | 7058092 | 1411619 | 5646473 | 207221 | 41444 | 165777 | 387000 | 77400 | 309600 | 0 | 0 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | CCI | 2011 | Q3 | Q3 - 2011 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 4535892 | 907179 | 3628713 | 0 | 0 | 0 | 50000 | 10000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 5000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 262350 | 52470 | 209880 | 302000 | 60400 | 241600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 440 | 88 | 352 | 2000 | 400 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 262790 | 52558 | 210232 | 359000 | 71800 | 287200 | 7058092 | 1411619 | 5646473 | 262790 | 52558 | 210232 | 359000 | 71800 | 287200 | 0 | 0 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | CCI | 2011 | Q4 | Q4 - 2011 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 100000 | 20000 | 80000 | 4535892 | 907179 | 3628713 | 319023 | 63805 | 255218 | 500000 | 100000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 5000 | 4000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 288954 | 57791 | 231163 | 310000 | 62000 | 248000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 1095 | 219 | 876 | 6000 | 1200 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 609072 | 121815 | 487257 | 921000 | 187200 | 733800 | 7058092 | 1411619 | 5646473 | 609072 | 121815 | 487257 | 921000 | 187200 | 733800 | 0 | 0 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | CCI | 2012 | Q1 | Q1 - 2012 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 0 | 0 | 0 | 4535892 | 907179 | 3628713 | 580377 | 116075 | 464302 | 2000000 | 400000 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 1600 | 320 | 1280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 291183 | 58257 | 232926 | 320000 | 64000 | 256000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 1095 | 219 | 876 | 170000 | 34000 | 136000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 872655 | 174551 | 698104 | 2491600 | 498320 | 1993280 | 7058092 | 1411619 | 5646473 | 872655 | 174551 | 698104 | 2491600 | 498320 | 1993280 | 0 | 0 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | CCI | 2012 | Q2 | Q2 - 2012 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 1200000 | 240000 | 960000 | 4535892 | 907179 | 3628713 | 1545596 | 309119 | 1236476 | 3000000 | 600000 | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 1600 | 320 | 1280 | 135000 | 27000 | 108000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 368470 | 73694 | 294776 | 395000 | 79000 | 316000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 36721 | 7344 | 29377 | 170000 | 34000 | 136000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 1952387 | 390477 | 1561909 | 4900000 | 980000 | 3920000 | 7058092 | 1411619 | 5646473 | 1952387 | 390477 | 1561909 | 4900000 | 980000 | 3920000 | 0 | 0 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | CCI | 2012 | Q3 | Q3 - 2012 | 1450000 | 290000 | 1160000 | 0 | 0 | 0 | 1200000 | 240000 | 960000 | 4535892 | 907179 | 3628713 | 3009082 | 601816 | 2407266 | 4300000 | 860000 | 3440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 30000 | 120000 | 140101 | 28020 | 112081 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403500 | 80700 | 322800 | 377688 | 75538 | 302150 | 395000 | 79000 | 316000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518700 | 103740 | 414960 | 91925 | 18385 | 73540 | 170000 | 34000 | 136000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 3618796 | 723759 | 2895037 | 6215000 | 1243000 | 4972000 | 7058092 | 1411619 | 5646473 | 3618796 | 723759 | 2895037 | 6215000 | 1243000 | 4972000 | 0 | 0 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | CCI | 2012 | Q4 | Q4 - 2012 | 1150000 | 230000 | 920000 | 60885 | 12177 | 48708 | 1092500 | 218500 | 874000 | 4535892 | 907179 | 3628713 | 3698305 | 739661 | 2958644 | 4309097 | 861819 | 3447278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 90000 | 360000 | 250398 | 50080 | 200318 | 450000 | 90000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553500 | 110700 | 442800 | 404065 | 80813 | 323252 | 542430 | 108486 | 433944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368700 | 73740 | 294960 | 180033 | 36007 | 144026 | 361326 | 72265 | 289061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 4593686 | 918738 | 3674948 | 6755353 | 1351070 | 5404283 | 7058092 | 1411619 | 5646473 | 4593686 | 918738 | 3674948 | 6755353 | 1351070 | 5404283 | 0 | 0 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | CCI | 2013 | Q1 | Q1 - 2013 | 1150000 | 230000 | 920000 | 830933 | 166187 | 664746 | 1115500 | 223100 | 892400 | 4535892 | 907179 | 3628713 | 4014644 | 802929 | 3211715 | 4535892 | 907179 | 3628713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 90000 | 360000 | 266087 | 53217 | 212870 | 450000 | 90000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553500 | 110700 | 442800 | 436120 | 87224 | 348896 | 530145 | 106029 | 424116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368700 | 73740 | 294960 | 207194 | 41439 | 165755 | 365013 | 73003 | 292010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 5754978 | 1150996 | 4603982 | 6996550 | 1399311 | 5597239 | 7058092 | 1411619 | 5646473 | 5754978 | 1150996 | 4603982 | 6996550 | 1399311 | 5597239 | 0 | 0 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | CCI | 2013 | Q2 | Q2 - 2013 | 1370000 | 274000 | 1096000 | 979308 | 195862 | 783446 | 1370000 | 274000 | 1096000 | 4535892 | 907179 | 3628713 | 4363838 | 872768 | 3491070 | 4535892 | 907179 | 3628713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310000 | 62000 | 248000 | 271861 | 54372 | 217489 | 310000 | 62000 | 248000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553500 | 110700 | 442800 | 458909 | 91782 | 367127 | 553500 | 110700 | 442800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288700 | 57740 | 230960 | 212285 | 42457 | 169828 | 288700 | 57740 | 230960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 6286201 | 1257241 | 5028960 | 7058092 | 1411619 | 5646473 | 7058092 | 1411619 | 5646473 | 6286201 | 1257241 | 5028960 | 7058092 | 1411619 | 5646473 | 0 | 0 | Bloomingdale Communications Inc | TRUE
NT10BIX5570099 | CCI | 2013 | Q3 | Q3 - 2013 | 1370000 | 274000 | 1096000 | 1350638 | 270128 | 1080510 | 1350638 | 270128 | 1080510 | 4535892 | 907179 | 3628713 | 4363838 | 872767 | 3491071 | 4363838 | 872767 | 3491071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310000 | 62000 | 248000 | 280193 | 56039 | 224154 | 280193 | 56039 | 224154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553500 | 110700 | 442800 | 480779 | 96156 | 384623 | 480779 | 96156 | 384623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288700 | 57740 | 230960 | 214366 | 42873 | 171493 | 214366 | 42873 | 171493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7058092 | 1411619 | 5646473 | 6689814 | 1337963 | 5351851 | 6689814 | 1337963 | 5351851 | 7058092 | 1411619 | 5646473 | 6689814 | 1337963 | 5351851 | 6689814 | 1337963 | 5351851 | 0 | 0 | Bloomingdale Communications Inc | TRUE
NT10BIX5570100 | CCI | 2010 | Q4 | Q4 - 2010 | 15318520 | 4683718 | 10634802 | 119630 | 46347 | 73283 | 7659260 | 2341859 | 5317401 | 27051500 | 8271139 | 18780361 | 1075000 | 416475 | 658525 | 1182500 | 361556 | 820944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 436390 | 169066 | 267324 | 436390 | 133429 | 302961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 1759574 | 681692 | 1077882 | 1935531 | 591799 | 1343732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 3390594 | 1313580 | 2077014 | 11213681 | 3428643 | 7785038 | 45395020 | 13879767 | 31515253 | 3390594 | 1313580 | 2077014 | 11213681 | 3428643 | 7785038 | 0 | 4 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | CCI | 2011 | Q1 | Q1 - 2011 | 15318520 | 4683718 | 10634802 | 8672215 | 1581217 | 7090998 | 8672215 | 2651576 | 6020639 | 27051500 | 8271139 | 18780361 | 5244651 | 956264 | 4288386 | 9178139 | 2806265 | 6371875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 436390 | 79567 | 356822 | 436390 | 133429 | 302961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 2826014 | 515271 | 2310743 | 2826014 | 864069 | 1961945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 17179270 | 3132319 | 14046949 | 21112758 | 6455339 | 14657420 | 45395020 | 13879767 | 31515253 | 17179270 | 3132319 | 14046949 | 21112758 | 6455339 | 14657420 | 0 | 196 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | CCI | 2011 | Q2 | Q2 - 2011 | 15318520 | 4683718 | 10634802 | 10049486 | 2599297 | 7450189 | 12254816 | 3746975 | 8507841 | 27051500 | 8271139 | 18780361 | 8721362 | 2255778 | 6465583 | 11721362 | 3583868 | 8137493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 436389 | 112872 | 323517 | 436390 | 133428 | 302961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 2784049 | 720094 | 2063956 | 2784049 | 851238 | 1932811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 21991286 | 5688041 | 16303245 | 27196617 | 8315509 | 18881106 | 45395020 | 13879767 | 31515253 | 21991286 | 5688041 | 16303245 | 27196617 | 8315509 | 18881106 | 0 | 910 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | CCI | 2011 | Q3 | Q3 - 2011 | 15318520 | 4683718 | 10634802 | 10408677 | 3215397 | 7193280 | 11408677 | 3488263 | 7920414 | 27051500 | 8271139 | 18780361 | 12247296 | 3783375 | 8463922 | 16247296 | 4967697 | 11279600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 442265 | 136622 | 305642 | 442265 | 135225 | 307040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 4510849 | 1393469 | 3117380 | 5510849 | 1684971 | 3825878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 27609087 | 8528863 | 19080224 | 33609087 | 10276156 | 23332932 | 45395020 | 13879767 | 31515253 | 27609087 | 8528863 | 19080224 | 33609087 | 10276156 | 23332932 | 0 | 981 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | CCI | 2011 | Q4 | Q4 - 2011 | 15318520 | 4683718 | 10634802 | 11154503 | 3315717 | 7838786 | 11654503 | 3563426 | 8091077 | 27051500 | 8271139 | 18780361 | 17258492 | 5130151 | 12128341 | 19258492 | 5888386 | 13370106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 445865 | 132535 | 313330 | 445865 | 136326 | 309539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 5598653 | 1664220 | 3934433 | 6098653 | 1864695 | 4233958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 34457513 | 10242623 | 24214890 | 37457513 | 11452833 | 26004680 | 45395020 | 13879767 | 31515253 | 34457513 | 10242623 | 24214890 | 37457513 | 11452833 | 26004680 | 992 | 992 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | CCI | 2012 | Q1 | Q1 - 2012 | 15318520 | 4683718 | 10634802 | 12147204 | 3671839 | 8475365 | 12647204 | 3866949 | 8780255 | 27051500 | 8271139 | 18780361 | 22323722 | 6747983 | 15575740 | 24323722 | 7437106 | 16886616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 445865 | 134775 | 311089 | 445865 | 136326 | 309539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 5952317 | 1799258 | 4153059 | 6452317 | 1972830 | 4479487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 40869108 | 12353855 | 28515253 | 43869108 | 13413211 | 30455897 | 45395020 | 13879767 | 31515253 | 40869108 | 12353855 | 28515253 | 43869108 | 13413211 | 30455897 | 0 | 0 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | CCI | 2012 | Q2 | Q2 - 2012 | 15318520 | 4683718 | 10634802 | 12837591 | 3883439 | 8954152 | 13337591 | 4283439 | 9054152 | 27051500 | 8271139 | 18780361 | 25655370 | 7760886 | 17894484 | 27655370 | 9760886 | 17894484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 445865 | 134877 | 310988 | 445865 | 134877 | 310988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 6029621 | 1823992 | 4205629 | 6529621 | 2323992 | 4205629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 44968447 | 13603194 | 31365253 | 47968447 | 16503194 | 31465253 | 45395020 | 13879767 | 31515253 | 44968447 | 13603194 | 31365253 | 47968447 | 16503194 | 31465253 | 0 | 0 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | CCI | 2012 | Q3 | Q3 - 2012 | 15318520 | 4683718 | 10634802 | 12843228 | 3887094 | 8956134 | 12843228 | 3887094 | 8956134 | 27051500 | 8271139 | 18780361 | 25928207 | 7937782 | 17990424 | 25928207 | 7937782 | 17990424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 445865 | 134877 | 310988 | 445865 | 134877 | 310988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 6177720 | 1920014 | 4257706 | 6177720 | 1920014 | 4257706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515252 | 45395020 | 13879767 | 31515252 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515252 | 45395020 | 13879767 | 31515252 | 0 | 0 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | CCI | 2012 | Q4 | Q4 - 2012 | 15318520 | 4683718 | 10634802 | 12843228 | 3887094 | 8956134 | 12843228 | 3887094 | 8956134 | 27051500 | 8271139 | 18780361 | 25928207 | 7937782 | 17990424 | 25928207 | 7937782 | 17990424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 445865 | 134877 | 310988 | 445865 | 134877 | 310988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 6177720 | 1920014 | 4257706 | 6177720 | 1920014 | 4257706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515252 | 45395020 | 13879767 | 31515252 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515252 | 45395020 | 13879767 | 31515252 | 0 | 936567 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | CCI | 2013 | Q1 | Q1 - 2013 | 15318520 | 4683718 | 10634802 | 12843228 | 3887094 | 8956134 | 12843228 | 3887094 | 8956134 | 27051500 | 8271139 | 18780361 | 25928207 | 7937783 | 17990424 | 25928207 | 7937783 | 17990424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 445865 | 134877 | 310988 | 445865 | 134877 | 310988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 6177720 | 1920013 | 4257707 | 6177720 | 1920013 | 4257707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 0 | 1551711 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | CCI | 2013 | Q2 | Q2 - 2013 | 15318520 | 4683718 | 10634802 | 12843228 | 3887094 | 8956134 | 12843228 | 3887094 | 8956134 | 27051500 | 8271139 | 18780361 | 25928207 | 7937783 | 17990424 | 25928207 | 7937783 | 17990424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 445865 | 134877 | 310988 | 445865 | 134877 | 310988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 6177720 | 1920013 | 4257707 | 6177720 | 1920013 | 4257707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 45395020 | 13879767 | 31515253 | 0 | 2297358 | Delta Communications, L.L.C. | TRUE
NT10BIX5570100 | CCI | 2013 | Q3 | Q3 - 2013 | 15318520 | 4683718 | 10634802 | 13121595 | 5603198 | 7518397 | 13121595 | 5603198 | 7518397 | 27051500 | 8271139 | 18780361 | 34387889 | 14684354 | 19703535 | 34387889 | 14684354 | 19703535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525000 | 160522 | 364478 | 1315263 | 561645 | 753618 | 1315263 | 561645 | 753618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 764388 | 1735612 | 6177720 | 2638017 | 3539703 | 6177720 | 2638017 | 3539703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45395020 | 13879767 | 31515253 | 55002467 | 23487214 | 31515253 | 55002467 | 23487214 | 31515253 | 45395020 | 13879767 | 31515253 | 55002467 | 23487214 | 31515253 | 55002467 | 23487214 | 31515253 | 0 | 2556898 | Delta Communications, L.L.C. | TRUE
NT10BIX5570101 | CCI | 2010 | Q4 | Q4 - 2010 | 4116961 | 3844461 | 272500 | 0 | 0 | 0 | 3631426 | 3622926 | 8500 | 13276889 | 0 | 13276889 | 0 | 0 | 0 | 0 | 0 | 0 | 2885803 | 152882 | 2732921 | 539935 | 22882 | 459866 | 247600 | 0 | 247600 | 4513019 | 1346000 | 3167019 | 735000 | 0 | 735000 | 482978 | 0 | 482978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 120963 | 0 | 120963 | 175500 | 0 | 175500 | 586469 | 0 | 586469 | 24000 | 0 | 24000 | 97000 | 0 | 97000 | 279877 | 0 | 279877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270300 | 100000 | 170300 | 563 | 0 | 563 | 63315 | 0 | 63315 | 26730257 | 5443343 | 21286914 | 1420461 | 22882 | 1340392 | 4697819 | 3622926 | 1074893 | 26730257 | 5443343 | 21286914 | 1420461 | 22882 | 1340392 | 4697819 | 3622926 | 1074893 | 0 | 0 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | CCI | 2011 | Q1 | Q1 - 2011 | 4116961 | 3844461 | 272500 | 4003 | 0 | 4003 | 321692 | 287895 | 33797 | 13276889 | 0 | 13276889 | 0 | 0 | 0 | 0 | 0 | 0 | 2885803 | 152882 | 2732921 | 657323 | 22882 | 634441 | 926351 | 22882 | 903469 | 4513019 | 1346000 | 3167019 | 735000 | 0 | 735000 | 3260000 | 1166000 | 2070000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 304820 | 0 | 304820 | 480320 | 0 | 480320 | 586469 | 0 | 586469 | 24000 | 0 | 24000 | 32011 | 0 | 32011 | 279877 | 0 | 279877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270300 | 100000 | 170300 | 10811 | 0 | 10811 | 23163 | 0 | 23163 | 26730257 | 5443343 | 21286914 | 1735957 | 22882 | 1713075 | 5043537 | 1476777 | 3542760 | 26730257 | 5443343 | 21286914 | 1735957 | 22882 | 1713075 | 5043537 | 1476777 | 3542760 | 0 | 0 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | CCI | 2011 | Q2 | Q2 - 2011 | 4116961 | 3844461 | 272500 | 105337 | 0 | 105337 | 3916819 | 3794461 | 122358 | 13276889 | 0 | 13276889 | 0 | 0 | 0 | 1062856 | 0 | 1062856 | 2885803 | 152882 | 2732921 | 837778 | 22882 | 814896 | 1062405 | 22882 | 1039523 | 4513019 | 1346000 | 3167019 | 735000 | 0 | 735000 | 3303000 | 1166000 | 2137000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 673026 | 0 | 673026 | 800939 | 0 | 813026 | 586469 | 0 | 586469 | 93000 | 0 | 93000 | 204087 | 0 | 192000 | 279877 | 0 | 279877 | 20000 | 0 | 20000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270300 | 100000 | 170300 | 31460 | 0 | 31460 | 38460 | 0 | 38460 | 26730257 | 5443343 | 21286914 | 2495601 | 22882 | 2472719 | 10438566 | 4983343 | 5455223 | 26730257 | 5443343 | 21286914 | 2495601 | 22882 | 2472719 | 10438566 | 4983343 | 5455223 | 0 | 0 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | CCI | 2011 | Q3 | Q3 - 2011 | 560395 | 287895 | 272500 | 419476 | 287895 | 131581 | 482538 | 287895 | 194643 | 18279455 | 5002566 | 13276889 | 5958913 | 5002566 | 956347 | 7603738 | 5002566 | 2601172 | 2885804 | 152882 | 2732922 | 1126493 | 22882 | 1103611 | 1418804 | 22882 | 1395922 | 3167019 | 0 | 3167019 | 2085000 | 0 | 2085000 | 2349556 | 0 | 2349556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 790026 | 0 | 790026 | 800939 | 0 | 800939 | 586469 | 0 | 586469 | 116351 | 0 | 116351 | 165910 | 0 | 165910 | 279877 | 0 | 279877 | 24750 | 0 | 24750 | 150695 | 0 | 150695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 32160 | 0 | 32160 | 36676 | 0 | 36676 | 26730258 | 5443343 | 21286915 | 10553169 | 5313343 | 5239826 | 13008856 | 5313343 | 7695513 | 26730258 | 5443343 | 21286915 | 10553169 | 5313343 | 5239826 | 13008856 | 5313343 | 7695513 | 0 | 0 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | CCI | 2011 | Q4 | Q4 - 2011 | 560395 | 287895 | 272500 | 499013 | 287895 | 211118 | 524905 | 287895 | 237010 | 18279455 | 5002566 | 13276889 | 6548598 | 5002566 | 1546032 | 9808490 | 5002566 | 4805924 | 2885804 | 152882 | 2732922 | 1300152 | 22882 | 1277270 | 1690682 | 152882 | 1537800 | 3167019 | 0 | 3167019 | 2085389 | 0 | 2085389 | 2095000 | 0 | 2095000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 791076 | 0 | 791076 | 800939 | 0 | 800939 | 586469 | 0 | 586469 | 116393 | 0 | 116393 | 171393 | 0 | 171393 | 279877 | 0 | 279877 | 23764 | 0 | 23764 | 70418 | 0 | 70418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 33372 | 0 | 33372 | 57368 | 0 | 57368 | 26730258 | 5443343 | 21286915 | 11397757 | 5313343 | 6084414 | 15219195 | 5443343 | 9775852 | 26730258 | 5443343 | 21286915 | 11397757 | 5313343 | 6084414 | 15219195 | 5443343 | 9775852 | 0 | 0 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | CCI | 2012 | Q1 | Q1 - 2012 | 1496395 | 287895 | 1208500 | 509993 | 287895 | 222098 | 1477985 | 287895 | 1190090 | 17874455 | 5002566 | 12871889 | 9620189 | 5002566 | 4617623 | 11933645 | 5002566 | 6931079 | 2885804 | 152882 | 2732922 | 1431605 | 22882 | 1408723 | 1768102 | 152882 | 1615220 | 2636019 | 0 | 2636019 | 2085989 | 0 | 2085989 | 2110601 | 0 | 2110601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 791076 | 0 | 791076 | 800939 | 0 | 800939 | 586469 | 0 | 586469 | 124266 | 0 | 124266 | 183266 | 0 | 183266 | 279877 | 0 | 279877 | 70188 | 0 | 70188 | 80188 | 0 | 80188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 34290 | 0 | 34290 | 89807 | 0 | 89807 | 26730258 | 5443343 | 21286915 | 14667596 | 5313343 | 9354253 | 18444533 | 5443343 | 13001190 | 26730258 | 5443343 | 21286915 | 14667596 | 5313343 | 9354253 | 18444533 | 5443343 | 13001190 | 0 | 0 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | CCI | 2012 | Q2 | Q2 - 2012 | 1496395 | 287895 | 1208500 | 518110 | 287895 | 230215 | 1486792 | 287895 | 1198897 | 17874455 | 5002566 | 12871889 | 12758529 | 5002566 | 7755963 | 14758529 | 5002566 | 9755963 | 2885804 | 152882 | 2732922 | 1691596 | 22882 | 1668714 | 1882074 | 152882 | 1729192 | 2636019 | 0 | 2636019 | 2122424 | 0 | 2122424 | 2122424 | 0 | 2122424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 795580 | 0 | 795580 | 800939 | 0 | 800939 | 586469 | 0 | 586469 | 244638 | 0 | 244638 | 346318 | 0 | 346318 | 279877 | 0 | 279877 | 75043 | 0 | 75043 | 90043 | 0 | 90043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 84659 | 0 | 84659 | 89175 | 0 | 89175 | 26730258 | 5443343 | 21286915 | 18290579 | 5313343 | 12977236 | 21576294 | 5443343 | 16132951 | 26730258 | 5443343 | 21286915 | 18290579 | 5313343 | 12977236 | 21576294 | 5443343 | 16132951 | 0 | 0 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | CCI | 2012 | Q3 | Q3 - 2012 | 1596395 | 287895 | 1308500 | 1495151 | 287895 | 1207256 | 1562590 | 287895 | 1274695 | 17874455 | 5002566 | 12871889 | 14106600 | 5002566 | 9104034 | 15672801 | 5002566 | 10670235 | 2885804 | 152882 | 2732922 | 1858087 | 22882 | 1835205 | 2191997 | 152882 | 2039115 | 2636019 | 0 | 2636019 | 2151807 | 0 | 2151807 | 2152196 | 0 | 2152196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 797552 | 0 | 797552 | 800939 | 0 | 800939 | 586469 | 0 | 586469 | 358949 | 0 | 358949 | 407429 | 0 | 407429 | 179877 | 0 | 179877 | 95337 | 0 | 95337 | 100337 | 0 | 100337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 76682 | 0 | 76682 | 82685 | 0 | 82685 | 26730258 | 5443343 | 21286915 | 20940165 | 5313343 | 15626822 | 22970974 | 5443343 | 17527631 | 26730258 | 5443343 | 21286915 | 20940165 | 5313343 | 15626822 | 22970974 | 5443343 | 17527631 | 0 | 0 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | CCI | 2012 | Q4 | Q4 - 2012 | 1596395 | 287895 | 1308500 | 1553165 | 287895 | 1265269 | 1595165 | 287895 | 1307270 | 17874455 | 5002566 | 12871889 | 15145383 | 5002566 | 10142817 | 16356715 | 5002566 | 11354149 | 2885804 | 152882 | 2732922 | 2046194 | 22882 | 2023312 | 2368787 | 152882 | 2215905 | 2636019 | 0 | 2636019 | 2164902 | 0 | 2164902 | 2169902 | 0 | 2169902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 797552 | 0 | 797553 | 800939 | 0 | 800939 | 586469 | 0 | 586469 | 439888 | 0 | 439888 | 463233 | 0 | 463233 | 179877 | 0 | 179877 | 97406 | 0 | 97406 | 122406 | 0 | 122406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 77247 | 0 | 77247 | 77997 | 0 | 77997 | 26730258 | 5443343 | 21286915 | 22321737 | 5313343 | 17008394 | 23955144 | 5443343 | 18511801 | 26730258 | 5443343 | 21286915 | 22321737 | 5313343 | 17008394 | 23955144 | 5443343 | 18511801 | 0 | 64837 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | CCI | 2013 | Q1 | Q1 - 2013 | 1596395 | 287895 | 1308500 | 1555489 | 287895 | 1267594 | 1595781 | 287895 | 1307886 | 17874455 | 5002566 | 12871889 | 15793108 | 5002566 | 10790542 | 17433108 | 5002566 | 12430542 | 2885804 | 152882 | 2732922 | 2237888 | 22882 | 2215006 | 2562577 | 152882 | 2409695 | 2636019 | 0 | 2636019 | 2178410 | 0 | 2178410 | 2191920 | 0 | 2191920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 797553 | 0 | 797553 | 800342 | 0 | 800342 | 586469 | 0 | 586469 | 439888 | 0 | 439888 | 481888 | 0 | 481888 | 179877 | 0 | 179877 | 120093 | 0 | 120093 | 125093 | 0 | 125093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 78550 | 0 | 78550 | 90100 | 0 | 90100 | 26730258 | 5443343 | 21286915 | 23200979 | 5313343 | 17887636 | 25280809 | 5443343 | 19837466 | 26730258 | 5443343 | 21286915 | 23200979 | 5313343 | 17887636 | 25280809 | 5443343 | 19837466 | 0 | 116613 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | CCI | 2013 | Q2 | Q2 - 2013 | 1635018 | 287895 | 1347123 | 1633233 | 287895 | 1345338 | 1635018 | 287895 | 1347122 | 18325058 | 5002566 | 13322492 | 16976134 | 5002566 | 11973568 | 18325058 | 5002566 | 13322492 | 2885803 | 152882 | 2732921 | 2438741 | 22882 | 2415859 | 2716095 | 152882 | 2563213 | 2185416 | 0 | 2185416 | 2180592 | 0 | 2180592 | 2185416 | 0 | 2185416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 800342 | 0 | 800342 | 800939 | 0 | 800939 | 586469 | 0 | 586469 | 462106 | 0 | 462106 | 586469 | 0 | 586469 | 141254 | 0 | 141254 | 123419 | 0 | 123419 | 141254 | 0 | 141254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170300 | 0 | 170300 | 91085 | 0 | 91085 | 170300 | 0 | 170300 | 26730257 | 5443343 | 21286914 | 24705652 | 5313343 | 19392309 | 26560549 | 5443343 | 21117205 | 26730257 | 5443343 | 21286914 | 24705652 | 5313343 | 19392309 | 26560549 | 5443343 | 21117205 | 0 | 181617 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570101 | CCI | 2013 | Q3 | Q3 - 2013 | 1716750 | 287895 | 1428855 | 1636203 | 287895 | 1348308 | 1716750 | 287895 | 1428855 | 18226586 | 5002566 | 13224020 | 18151900 | 5002566 | 13149334 | 18226586 | 5002566 | 13224020 | 3025178 | 152882 | 2872296 | 2696102 | 152882 | 2543220 | 3025178 | 152882 | 2872296 | 2180913 | 0 | 2180913 | 2180913 | 0 | 2180913 | 2180913 | 0 | 2180913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800939 | 0 | 800939 | 800342 | 0 | 800342 | 800939 | 0 | 800939 | 570858 | 0 | 570858 | 570642 | 0 | 570642 | 570858 | 0 | 570858 | 119248 | 0 | 119248 | 119248 | 0 | 119248 | 119248 | 0 | 119248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89786 | 0 | 89786 | 91285 | 0 | 91285 | 89786 | 0 | 89786 | 26730258 | 5443343 | 21286915 | 26246635 | 5443343 | 20803292 | 26730258 | 5443343 | 21286915 | 26730258 | 5443343 | 21286915 | 26246635 | 5443343 | 20803292 | 26730258 | 5443343 | 21286915 | 0 | 231272 | Appalachian Valley Fiber Network | TRUE
NT10BIX5570102 | CCI | 2010 | Q4 | Q4 - 2010 | 43605098 | 15998347 | 27606751 | 18163 | 18163 | 0 | 3243231 | 1724106 | 1519126 | 28195212 | 0 | 28195212 | 0 | 0 | 0 | 0 | 0 | 0 | 10709094 | 88400 | 10620694 | 70132 | 0 | 70132 | 583157 | 0 | 583157 | 10711692 | 9851632 | 860060 | 0 | 0 | 0 | 40474 | 0 | 40474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 0 | 0 | 0 | 406737 | 0 | 406737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 0 | 0 | 0 | 4107688 | 0 | 4107688 | 128581820 | 26450427 | 102131393 | 88295 | 18163 | 70132 | 8381287 | 1724106 | 6657182 | 128581820 | 26450427 | 102131393 | 88295 | 18163 | 70132 | 8381287 | 1724106 | 6657182 | 0 | 0 | University of Arkansas System | TRUE
NT10BIX5570102 | CCI | 2011 | Q1 | Q1 - 2011 | 43605098 | 15998347 | 27606751 | 153397 | 153397 | 0 | 1389853 | 1389853 | 0 | 28195212 | 0 | 28195212 | 266351 | 0 | 266351 | 4548485 | 0 | 4548485 | 10709094 | 88400 | 10620694 | 325950 | 0 | 325950 | 420950 | 0 | 420950 | 10711692 | 9851632 | 860060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 0 | 0 | 0 | 271985 | 0 | 271985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 0 | 0 | 0 | 125133 | 0 | 125133 | 128581820 | 26450427 | 102131393 | 745698 | 153397 | 592301 | 6756406 | 1389853 | 5366553 | 128581820 | 26450427 | 102131393 | 745698 | 153397 | 592301 | 6756406 | 1389853 | 5366553 | 0 | 0 | University of Arkansas System | TRUE
NT10BIX5570102 | CCI | 2011 | Q2 | Q2 - 2011 | 43605098 | 15998347 | 27606751 | 476323 | 476323 | 0 | 12139702 | 5246969 | 6892733 | 28195212 | 0 | 28195212 | 849269 | 0 | 849269 | 6478830 | 0 | 6478830 | 10709094 | 88400 | 10620694 | 717597 | 0 | 717597 | 1112210 | 0 | 1112210 | 10711692 | 9851632 | 860060 | 0 | 0 | 0 | 501855 | 0 | 501855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 9062 | 0 | 9062 | 1072923 | 0 | 1072923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 263268 | 0 | 263268 | 4201244 | 0 | 4201244 | 128581820 | 26450427 | 102131393 | 2315519 | 476323 | 1839196 | 25506764 | 5246969 | 20259795 | 128581820 | 26450427 | 102131393 | 2315519 | 476323 | 1839196 | 25506764 | 5246969 | 20259795 | 0 | 0 | University of Arkansas System | TRUE
NT10BIX5570102 | CCI | 2011 | Q3 | Q3 - 2011 | 43605098 | 15998347 | 27606751 | 1830425 | 1562285 | 268140 | 17820121 | 7770683 | 10049438 | 28195212 | 0 | 28195212 | 4337618 | 0 | 4337618 | 13323856 | 0 | 13323856 | 10709094 | 88400 | 10620694 | 1111100 | 0 | 1111100 | 1383670 | 0 | 1383670 | 10711692 | 9851632 | 860060 | 0 | 0 | 0 | 1048733 | 0 | 1048733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 9062 | 0 | 9062 | 905247 | 0 | 905247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 306434 | 0 | 306434 | 3293513 | 0 | 3293513 | 128581820 | 26450427 | 102131393 | 7594639 | 1562285 | 6032354 | 37775140 | 7770683 | 30004457 | 128581820 | 26450427 | 102131393 | 7594639 | 1562285 | 6032354 | 37775140 | 7770683 | 30004457 | 0 | 0 | University of Arkansas System | TRUE
NT10BIX5570102 | CCI | 2011 | Q4 | Q4 - 2011 | 43605098 | 15998347 | 27606751 | 13652238 | 5375145 | 8277093 | 28049199 | 12769706 | 15279493 | 28195212 | 0 | 28195212 | 8791538 | 0 | 8791538 | 22254747 | 0 | 22254747 | 10709094 | 88400 | 10620694 | 1600119 | 0 | 1600119 | 1966587 | 0 | 1966587 | 10711692 | 9851632 | 860060 | 820355 | 0 | 820355 | 2401179 | 0 | 2401179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 349591 | 0 | 349591 | 1727606 | 0 | 1727606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 916021 | 0 | 916020 | 5677263 | 0 | 5677263 | 128581820 | 26450427 | 102131393 | 26129862 | 5375145 | 20754716 | 62076581 | 12769706 | 49306875 | 128581820 | 26450427 | 102131393 | 26129862 | 5375145 | 20754716 | 62076581 | 12769706 | 49306875 | 0 | 0 | University of Arkansas System | TRUE
NT10BIX5570102 | CCI | 2012 | Q1 | Q1 - 2012 | 43605098 | 15998347 | 27606751 | 30295266 | 11269510 | 19025756 | 42514142 | 16862432 | 25651710 | 28195212 | 0 | 28195212 | 15124668 | 0 | 15124668 | 30159180 | 0 | 30159181 | 10709094 | 88400 | 10620694 | 2653828 | 0 | 2653828 | 3385052 | 431840 | 2953212 | 10711692 | 9851632 | 860060 | 2202902 | 0 | 2202902 | 4699099 | 1295520 | 3403579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 1949839 | 0 | 1949839 | 3492963 | 0 | 3492963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 2557266 | 0 | 2557266 | 8608151 | 512048 | 8096103 | 128581820 | 26450427 | 102131393 | 54783769 | 11269510 | 43514259 | 92858587 | 19101840 | 73756748 | 128581820 | 26450427 | 102131393 | 54783769 | 11269510 | 43514259 | 92858587 | 19101840 | 73756748 | 0 | 0 | University of Arkansas System | TRUE
NT10BIX5570102 | CCI | 2012 | Q2 | Q2 - 2012 | 43605098 | 15998347 | 27606751 | 39255851 | 16826106 | 22429745 | 43502827 | 16826106 | 26676721 | 28195212 | 0 | 28195212 | 20043544 | 0 | 20043544 | 27300579 | 0 | 27300579 | 10709094 | 88400 | 10620694 | 7114310 | 0 | 7114310 | 7748859 | 0 | 7748859 | 10711692 | 9851632 | 860060 | 4790229 | 1389108 | 3401121 | 9979639 | 5778836 | 4200803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 2360448 | 0 | 2360448 | 3105327 | 0 | 3105327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 17473295 | 512048 | 16961247 | 20739957 | 512048 | 20227909 | 128581820 | 26450427 | 102131393 | 91037677 | 18727262 | 72310415 | 112377188 | 23116990 | 89260198 | 128581820 | 26450427 | 102131393 | 91037677 | 18727262 | 72310415 | 112377188 | 23116990 | 89260198 | 0 | 0 | University of Arkansas System | TRUE
NT10BIX5570102 | CCI | 2012 | Q3 | Q3 - 2012 | 43605098 | 15998347 | 27606751 | 41655641 | 16844269 | 24811372 | 44068320 | 18325883 | 25742437 | 28195212 | 0 | 28195212 | 21893236 | 0 | 21893236 | 23003135 | 0 | 23003135 | 10709094 | 88400 | 10620694 | 7491920 | 0 | 7491920 | 8396699 | 528771 | 7867928 | 10711692 | 9851632 | 860060 | 5935408 | 2655255 | 3280153 | 8872980 | 4006388 | 4866592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 2383964 | 0 | 2383964 | 3121384 | 0 | 3121384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 17920845 | 512048 | 17408797 | 20388754 | 484694 | 19904060 | 128581820 | 26450427 | 102131393 | 97281014 | 20011572 | 77269442 | 107851272 | 23345736 | 84505536 | 128581820 | 26450427 | 102131393 | 97281014 | 20011572 | 77269442 | 107851272 | 23345736 | 84505536 | 0 | 0 | University of Arkansas System | TRUE
NT10BIX5570102 | CCI | 2012 | Q4 | Q4 - 2012 | 43605098 | 15998347 | 27606751 | 42729502 | 16844269 | 25885233 | 42729502 | 16862432 | 25867070 | 28195212 | 0 | 28195212 | 24014690 | 0 | 24014690 | 30571902 | 0 | 30571902 | 10709094 | 88400 | 10620694 | 7755741 | 0 | 7755741 | 9096236 | 920147 | 8176089 | 10711692 | 9851632 | 860060 | 7382533 | 3707269 | 3675264 | 13085407 | 6467712 | 6617695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 2576165 | 0 | 2576165 | 3028386 | 0 | 3028386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 17936474 | 512048 | 17424426 | 22679695 | 512048 | 22167647 | 128581820 | 26450427 | 102131393 | 102395105 | 21063586 | 81331519 | 121191128 | 24762339 | 96428789 | 128581820 | 26450427 | 102131393 | 102395105 | 21063586 | 81331519 | 121191128 | 24762339 | 96428789 | 0 | 0 | University of Arkansas System | TRUE
NT10BIX5570102 | CCI | 2013 | Q1 | Q1 - 2013 | 43605098 | 15998347 | 27606751 | 43221753 | 16844269 | 26377484 | 43960192 | 16844269 | 27115923 | 28195212 | 0 | 28195212 | 24312270 | 0 | 24312270 | 24678023 | 0 | 24678023 | 10709094 | 88400 | 10620694 | 8079684 | 0 | 8079684 | 9069925 | 35360 | 9034565 | 10711692 | 9851632 | 860060 | 8279485 | 4184936 | 4094549 | 10542482 | 6105980 | 4436502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 2785399 | 0 | 2785399 | 3130439 | 0 | 3130439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 18038566 | 512048 | 17526518 | 29262305 | 512048 | 28750256 | 128581820 | 26450427 | 102131393 | 104717157 | 21541253 | 83175904 | 120643366 | 23497657 | 97145708 | 128581820 | 26450427 | 102131393 | 104717157 | 21541253 | 83175904 | 120643366 | 23497657 | 97145708 | 0 | 0 | University of Arkansas System | TRUE
NT10BIX5570102 | CCI | 2013 | Q2 | Q2 - 2013 | 43605098 | 15998347 | 27606751 | 42375446 | 15697330 | 26678115 | 43791782 | 15697331 | 28094451 | 28195212 | 0 | 28195212 | 24549072 | 0 | 24549073 | 25225336 | 0 | 25225336 | 10709094 | 88400 | 10620694 | 8423884 | 0 | 8423884 | 10625418 | 88400 | 10537018 | 10711692 | 9851632 | 860060 | 11039861 | 5961348 | 5078513 | 15274159 | 10195596 | 5078563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 3130545 | 0 | 3130545 | 3647999 | 0 | 3647999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 18049588 | 469100 | 17580488 | 30017126 | 469100 | 29548026 | 128581820 | 26450427 | 102131393 | 107568396 | 22127778 | 85440618 | 128581820 | 26450427 | 102131393 | 128581820 | 26450427 | 102131393 | 107568396 | 22127778 | 85440618 | 128581820 | 26450427 | 102131393 | 0 | 0 | University of Arkansas System | TRUE
NT10BIX5570102 | CCI | 2013 | Q3 | Q3 - 2013 | 43605098 | 15998347 | 27606751 | 45326575 | 17481259 | 27845316 | 45326575 | 17481259 | 27845316 | 28195212 | 0 | 28195212 | 25134127 | 0 | 25134127 | 25134127 | 0 | 25134127 | 10709094 | 88400 | 10620694 | 10742058 | 88400 | 10653658 | 10742617 | 88400 | 10654217 | 10711692 | 9851632 | 860060 | 13784726 | 8368720 | 5416006 | 13784726 | 8368720 | 5416006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2172357 | 0 | 2172357 | 3266467 | 0 | 3266467 | 3266467 | 0 | 3266467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33188367 | 512048 | 32676319 | 30327308 | 512048 | 29815260 | 30327308 | 512048 | 29815260 | 128581820 | 26450427 | 102131393 | 128581261 | 26450427 | 102130834 | 128581820 | 26450427 | 102131393 | 128581820 | 26450427 | 102131393 | 128581261 | 26450427 | 102130834 | 128581820 | 26450427 | 102131393 | 0 | 0 | University of Arkansas System | TRUE
NT10BIX5570103 | CCI | 2010 | Q4 | Q4 - 2010 | 8776597 | 1872462 | 6904135 | 0 | 0 | 0 | 0 | 0 | 0 | 9469288 | 2020246 | 7449042 | 0 | 0 | 0 | 0 | 0 | 0 | 258125 | 55070 | 203055 | 77718 | 17471 | 60248 | 138540 | 29557 | 108983 | 25000 | 5334 | 19666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2591513 | 552892 | 2038621 | 36125 | 9101 | 27024 | 820728 | 175100 | 645628 | 1712850 | 365432 | 1347418 | 521971 | 100598 | 421373 | 1541017 | 328772 | 1212245 | 63961 | 13646 | 50315 | 0 | 0 | 0 | 0 | 0 | 0 | 408975 | 87254 | 321721 | 0 | 0 | 0 | 0 | 0 | 0 | 29750 | 6347 | 23403 | 0 | 0 | 0 | 0 | 0 | 0 | 1635208 | 348867 | 1286341 | 0 | 0 | 0 | 0 | 0 | 0 | 24971267 | 5327550 | 19643717 | 635814 | 127170 | 508645 | 2500285 | 533429 | 1966856 | 24971267 | 5327550 | 19643717 | 635814 | 127170 | 508645 | 2500285 | 533429 | 1966856 | 0 | 0 | Nevada Hospital Association | TRUE
NT10BIX5570103 | CCI | 2011 | Q1 | Q1 - 2011 | 8776597 | 1872462 | 6904135 | 0 | 0 | 0 | 0 | 0 | 0 | 9469288 | 2020246 | 7449042 | 0 | 0 | 0 | 0 | 0 | 0 | 258125 | 55070 | 203055 | 114693 | 25114 | 89579 | 138540 | 29557 | 108983 | 25000 | 5334 | 19666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2591513 | 552892 | 2038621 | 350247 | 76118 | 274128 | 1520728 | 324443 | 1196285 | 1712850 | 365432 | 1347418 | 661005 | 129501 | 531503 | 841017 | 179429 | 661588 | 63961 | 13646 | 50315 | 0 | 0 | 0 | 0 | 0 | 0 | 408975 | 87254 | 321721 | 0 | 0 | 0 | 0 | 0 | 0 | 29750 | 6347 | 23403 | 0 | 0 | 0 | 0 | 0 | 0 | 1635208 | 348867 | 1286341 | 0 | 0 | 0 | 0 | 0 | 0 | 24971267 | 5327550 | 19643717 | 1125945 | 230733 | 895210 | 2500285 | 533429 | 1966856 | 24971267 | 5327550 | 19643717 | 1125945 | 230733 | 895210 | 2500285 | 533429 | 1966856 | 0 | 0 | Nevada Hospital Association | TRUE
NT10BIX5570103 | CCI | 2011 | Q2 | Q2 - 2011 | 8776597 | 1872462 | 6904135 | 0 | 0 | 0 | 175532 | 37449 | 138083 | 9469288 | 2020246 | 7449042 | 0 | 0 | 0 | 4000 | 853 | 3147 | 258125 | 55070 | 203055 | 128236 | 28826 | 99410 | 149236 | 31839 | 117397 | 25000 | 5334 | 19666 | 0 | 0 | 0 | 3750 | 800 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2591513 | 552892 | 2038621 | 765840 | 164784 | 601056 | 1520728 | 324443 | 1196285 | 1712850 | 365432 | 1347418 | 802236 | 166270 | 635966 | 841017 | 179429 | 661588 | 63961 | 13646 | 50315 | 0 | 0 | 0 | 0 | 0 | 0 | 408975 | 87254 | 321721 | 0 | 0 | 0 | 8180 | 1745 | 6434 | 29750 | 6347 | 23403 | 0 | 0 | 0 | 0 | 0 | 0 | 1635208 | 348867 | 1286341 | 0 | 0 | 0 | 0 | 0 | 0 | 24971267 | 5327550 | 19643717 | 1696312 | 359880 | 1336432 | 2702443 | 576558 | 2125884 | 24971267 | 5327550 | 19643717 | 1696312 | 359880 | 1336432 | 2702443 | 576558 | 2125884 | 0 | 0 | Nevada Hospital Association | TRUE
NT10BIX5570103 | CCI | 2011 | Q3 | Q3 - 2011 | 4225003 | 1259161 | 2965843 | 0 | 0 | 0 | 2112502 | 450696 | 1661805 | 10548955 | 3143862 | 7405093 | 0 | 0 | 0 | 0 | 0 | 0 | 1452700 | 432942 | 1019757 | 227003 | 177105 | 49898 | 251003 | 53551 | 197452 | 5186778 | 1545794 | 3640984 | 0 | 0 | 0 | 518678 | 110658 | 408019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 695560 | 1638330 | 1401590 | 1101170 | 300420 | 1916032 | 408780 | 1507252 | 1740318 | 518660 | 1221658 | 1001729 | 792898 | 208831 | 1171792 | 249998 | 921793 | 1832629 | 546171 | 1286458 | 0 | 0 | 0 | 0 | 0 | 0 | 663264 | 197670 | 465594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983536 | 8339820 | 19643717 | 2630322 | 2071173 | 559149 | 5970007 | 1273683 | 4696321 | 27983536 | 8339820 | 19643717 | 2630322 | 2071173 | 559149 | 5970007 | 1273683 | 4696321 | 0 | 0 | Nevada Hospital Association | TRUE
NT10BIX5570103 | CCI | 2011 | Q4 | Q4 - 2011 | 4225003 | 1520599 | 2704404 | 0 | 0 | 0 | 4225003 | 901393 | 3323610 | 10548955 | 3763638 | 6785317 | 0 | 0 | 0 | 0 | 0 | 0 | 1452699 | 309929 | 1142770 | 429031 | 93000 | 336031 | 453031 | 96653 | 356378 | 5186778 | 1170020 | 4016758 | 0 | 0 | 0 | 1556033 | 331975 | 1224058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2064442 | 441837 | 1622605 | 2333889 | 497929 | 1835960 | 1740318 | 371292 | 1369026 | 1161327 | 242881 | 918446 | 1331391 | 284049 | 1047342 | 1832629 | 390986 | 1441643 | 0 | 0 | 0 | 0 | 0 | 0 | 663264 | 315425 | 347839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983535 | 8339818 | 19643717 | 3654800 | 777718 | 2877082 | 9899347 | 2111999 | 7787348 | 27983535 | 8339818 | 19643717 | 3654800 | 777718 | 2877082 | 9899347 | 2111999 | 7787348 | 0 | 0 | Nevada Hospital Association | TRUE
NT10BIX5570103 | CCI | 2012 | Q1 | Q1 - 2012 | 4225003 | 1520599 | 2704404 | 0 | 0 | 0 | 4225003 | 901393 | 3323610 | 10548955 | 3763638 | 6785317 | 0 | 0 | 0 | 0 | 0 | 0 | 1452699 | 309929 | 1142770 | 516281 | 111472 | 404809 | 540281 | 115267 | 425014 | 5186778 | 1170020 | 4016758 | 511930 | 109219 | 402712 | 3112067 | 663951 | 2448116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2332025 | 497531 | 1833100 | 2333889 | 497929 | 1835960 | 1740318 | 371292 | 1369026 | 1293042 | 272519 | 1021917 | 1463106 | 312150 | 1150956 | 1832629 | 390986 | 1441643 | 0 | 0 | 0 | 0 | 0 | 0 | 663264 | 315425 | 347839 | 0 | 0 | 0 | 364795 | 77828 | 286967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983535 | 8339818 | 19643717 | 4653278 | 990741 | 3662538 | 12039141 | 2568518 | 9470623 | 27983535 | 8339818 | 19643717 | 4653278 | 990741 | 3662538 | 12039141 | 2568518 | 9470623 | 0 | 0 | Nevada Hospital Association | TRUE
NT10BIX5570103 | CCI | 2012 | Q2 | Q2 - 2012 | 4225003 | 1520599 | 2704404 | 0 | 0 | 0 | 4225003 | 901393 | 3323610 | 10548955 | 3763638 | 6785317 | 3409 | 727 | 2682 | 105490 | 22506 | 82984 | 1452699 | 309929 | 1142770 | 630314 | 134476 | 495838 | 720314 | 153677 | 566637 | 5186778 | 1170020 | 4016758 | 944138 | 201429 | 742709 | 3112067 | 663951 | 2448116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2283652 | 487211 | 1796441 | 2333889 | 497929 | 1835960 | 1740318 | 371292 | 1369026 | 1426164 | 304268 | 1121896 | 1516164 | 323469 | 1192695 | 1832629 | 390986 | 1441643 | 0 | 0 | 0 | 0 | 0 | 0 | 663264 | 315425 | 347839 | 0 | 0 | 0 | 364795 | 77828 | 286967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983535 | 8339818 | 19643717 | 5287677 | 1128111 | 4159566 | 12377722 | 2640753 | 9736969 | 27983535 | 8339818 | 19643717 | 5287677 | 1128111 | 4159566 | 12377722 | 2640753 | 9736969 | 0 | 0 | Nevada Hospital Association | TRUE
NT10BIX5570103 | CCI | 2012 | Q3 | Q3 - 2012 | 4225003 | 1520599 | 2704404 | 2599462 | 586930 | 2012532 | 3802502 | 811253 | 2991249 | 10548955 | 3763638 | 6785317 | 75021 | 16004 | 59017 | 1054896 | 225059 | 829837 | 1452699 | 309929 | 1142770 | 770245 | 164330 | 605915 | 860245 | 183531 | 676714 | 5186778 | 1170020 | 4016758 | 1993495 | 425307 | 1568188 | 3112067 | 663951 | 2448116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2299148 | 490517 | 1808631 | 2333889 | 497929 | 1835960 | 1740318 | 371292 | 1369026 | 1516570 | 323556 | 1193014 | 1606570 | 342757 | 1263813 | 1832629 | 390986 | 1441643 | 167149 | 35661 | 131488 | 632649 | 134974 | 497675 | 663264 | 315425 | 347839 | 0 | 0 | 0 | 132653 | 28301 | 104352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983535 | 8339818 | 19643717 | 9421090 | 2042305 | 7378785 | 13535471 | 2887755 | 10647716 | 27983535 | 8339818 | 19643717 | 9421090 | 2042305 | 7378785 | 13535471 | 2887755 | 10647716 | 0 | 0 | Nevada Hospital Association | TRUE
NT10BIX5570103 | CCI | 2012 | Q4 | Q4 - 2012 | 4225003 | 1520599 | 2704404 | 3362102 | 749637 | 2612465 | 3802502 | 811253 | 2991249 | 10548955 | 3763638 | 6785317 | 404721 | 92869 | 311852 | 4219582 | 900236 | 3319346 | 1452699 | 309929 | 1142770 | 784496 | 167370 | 617126 | 874496 | 186571 | 687925 | 5186778 | 1170020 | 4016758 | 1477900 | 315305 | 1162595 | 3890083 | 829938 | 3060145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2299082 | 490503 | 1808579 | 2333889 | 497929 | 1835960 | 1740318 | 371292 | 1369026 | 1522503 | 324822 | 1197681 | 1612502 | 344023 | 1268479 | 1832629 | 390986 | 1441643 | 353259 | 75367 | 277892 | 725658 | 154817 | 570841 | 663264 | 315425 | 347839 | 0 | 0 | 0 | 198980 | 42452 | 156528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983535 | 8339818 | 19643717 | 10204063 | 2215873 | 7988190 | 17657692 | 3767219 | 13890473 | 27983535 | 8339818 | 19643717 | 10204063 | 2215873 | 7988190 | 17657692 | 3767219 | 13890473 | 0 | 0 | Nevada Hospital Association | TRUE
NT10BIX5570103 | CCI | 2013 | Q1 | Q1 - 2013 | 5365839 | 1520599 | 3845240 | 3362102 | 749637 | 2612465 | 4959255 | 1058043 | 3901212 | 11246049 | 3763638 | 7482411 | 404721 | 92869 | 311852 | 2049210 | 437193 | 1612017 | 1452699 | 309929 | 1142770 | 784496 | 167370 | 617126 | 874496 | 186571 | 687925 | 3422544 | 1170020 | 2252524 | 1477901 | 315306 | 1162595 | 1507901 | 321706 | 1186195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2299082 | 490503 | 1808579 | 2333889 | 497929 | 1835960 | 1740317 | 371292 | 1369025 | 1522503 | 324822 | 1197681 | 1612502 | 344023 | 1268479 | 1832629 | 390986 | 1441643 | 353259 | 75367 | 277892 | 1368808 | 292031 | 1076777 | 589568 | 315425 | 274143 | 0 | 0 | 0 | 176871 | 37735 | 139136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983534 | 8339818 | 19643716 | 10204064 | 2215874 | 7988190 | 14882932 | 3175231 | 11707701 | 27983534 | 8339818 | 19643716 | 10204064 | 2215874 | 7988190 | 14882932 | 3175231 | 11707701 | 0 | 0 | Nevada Hospital Association | TRUE
NT10BIX5570103 | CCI | 2013 | Q2 | Q2 - 2013 | 5365839 | 1520599 | 3845240 | 3362102 | 749637 | 2612465 | 4959255 | 1058043 | 3901212 | 11246049 | 3763638 | 7482411 | 404721 | 92869 | 311852 | 2049210 | 437193 | 1612017 | 1452699 | 309929 | 1142770 | 784496 | 167370 | 617126 | 874496 | 186571 | 687925 | 3422544 | 1170020 | 2252524 | 1477901 | 315306 | 1162595 | 1507901 | 321706 | 1186195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2299082 | 490503 | 1808579 | 2333889 | 497929 | 1835960 | 1740317 | 371292 | 1369025 | 1522503 | 324822 | 1197681 | 1612502 | 344023 | 1268479 | 1832629 | 390986 | 1441643 | 353259 | 75367 | 277892 | 1368808 | 292031 | 1076777 | 589568 | 315425 | 274143 | 0 | 0 | 0 | 176871 | 37735 | 139136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983534 | 8339818 | 19643716 | 10204064 | 2215874 | 7988190 | 14882932 | 3175231 | 11707701 | 27983534 | 8339818 | 19643716 | 10204064 | 2215874 | 7988190 | 14882932 | 3175231 | 11707701 | 0 | 0 | Nevada Hospital Association | TRUE
NT10BIX5570103 | CCI | 2013 | Q3 | Q3 - 2013 | 5365839 | 1520599 | 3845240 | 4102677 | 749637 | 3353040 | 4104150 | 749952 | 3354199 | 11246049 | 3763638 | 7482411 | 1350201 | 92869 | 1257332 | 2251376 | 681533 | 1569842 | 1452699 | 309929 | 1142770 | 934283 | 172449 | 761835 | 1008915 | 188371 | 820544 | 3422544 | 1170020 | 2252524 | 1531661 | 315306 | 1216355 | 1556661 | 320640 | 1236022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2332950 | 490503 | 1842447 | 2332950 | 490503 | 1842447 | 1740317 | 371292 | 1369025 | 1532002 | 326848 | 1205154 | 1569002 | 334742 | 1234260 | 1832629 | 390986 | 1441643 | 533938 | 75367 | 458572 | 533938 | 75367 | 458572 | 589568 | 315425 | 274143 | 147400 | 0 | 147400 | 147400 | 0 | 147400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983534 | 8339818 | 19643716 | 12465112 | 2222979 | 10242135 | 13504392 | 2841108 | 10663286 | 27983534 | 8339818 | 19643716 | 12465112 | 2222979 | 10242135 | 13504392 | 2841108 | 10663286 | 0 | 0 | Nevada Hospital Association | TRUE
NT10BIX5570103 | CCI | 2013 | Q4 | Q4 - 2013 | 5365839 | 1520599 | 3845240 | 4102677 | 749637 | 3353040 | 4104150 | 749952 | 3354199 | 11246049 | 3763638 | 7482411 | 1350201 | 92869 | 1257332 | 2251376 | 681533 | 1569842 | 1452699 | 309929 | 1142770 | 934283 | 172449 | 761835 | 1008915 | 188371 | 820544 | 3422544 | 1170020 | 2252524 | 1531661 | 315306 | 1216355 | 1556661 | 320640 | 1236022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2333889 | 497929 | 1835960 | 2332950 | 490503 | 1842447 | 2332950 | 490503 | 1842447 | 1740317 | 371292 | 1369025 | 1532002 | 326848 | 1205154 | 1569002 | 334742 | 1234260 | 1832629 | 390986 | 1441643 | 533938 | 75367 | 458572 | 533938 | 75367 | 458572 | 589568 | 315425 | 274143 | 147400 | 0 | 147400 | 147400 | 0 | 147400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27983534 | 8339818 | 19643716 | 12465112 | 2222979 | 10242135 | 13504392 | 2841108 | 10663286 | 27983534 | 8339818 | 19643716 | 12465112 | 2222979 | 10242135 | 13504392 | 2841108 | 10663286 | 0 | 0 | Nevada Hospital Association | TRUE
NT10BIX5570104 | CCI | 2010 | Q4 | Q4 - 2010 | 2117516 | 423503 | 1694013 | 8016 | 1603 | 6413 | 136416 | 27283 | 109133 | 11339864 | 2267973 | 9071891 | 22487 | 449 | 17989 | 166318 | 33264 | 133054 | 93905 | 18781 | 75124 | 21000 | 4200 | 16800 | 75396 | 15079 | 60317 | 384000 | 76800 | 307200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 5007 | 1001 | 4006 | 42907 | 8582 | 34325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 3058 | 612 | 2446 | 18058 | 3612 | 14446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 59568 | 7865 | 47654 | 439095 | 87820 | 351275 | 14480584 | 2896117 | 11584467 | 59568 | 7865 | 47654 | 439095 | 87820 | 351275 | 0 | 0 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | CCI | 2011 | Q1 | Q1 - 2011 | 2117516 | 423503 | 1694013 | 9762 | 1952 | 7810 | 420762 | 84152 | 336610 | 11339864 | 2267973 | 9071891 | 115615 | 23123 | 92492 | 1655296 | 331059 | 1324237 | 93905 | 18781 | 75124 | 80025 | 16005 | 64020 | 89863 | 17973 | 71890 | 384000 | 76800 | 307200 | 0 | 0 | 0 | 82500 | 16500 | 66000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 29939 | 5988 | 23951 | 42323 | 8465 | 33858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 5970 | 1194 | 4776 | 35970 | 7194 | 28776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 241311 | 48262 | 193049 | 2326714 | 465343 | 1861371 | 14480584 | 2896117 | 11584467 | 241311 | 48262 | 193049 | 2326714 | 465343 | 1861371 | 0 | 0 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | CCI | 2011 | Q2 | Q2 - 2011 | 2117516 | 423503 | 1694013 | 247210 | 49442 | 197768 | 425210 | 85042 | 340168 | 11339864 | 2267973 | 9071891 | 1578316 | 315633 | 1262653 | 3178166 | 635633 | 2542533 | 93905 | 18781 | 75124 | 80025 | 16005 | 64020 | 83125 | 16625 | 66500 | 384000 | 76800 | 307200 | 72144 | 14429 | 57715 | 88024 | 17605 | 70419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 45880 | 9176 | 36704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 26866 | 5373 | 21493 | 56866 | 11373 | 45493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 2047441 | 409458 | 1637953 | 3877271 | 775454 | 3101817 | 14480584 | 2896117 | 11584467 | 2047441 | 409458 | 1637953 | 3877271 | 775454 | 3101817 | 0 | 0 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | CCI | 2011 | Q3 | Q3 - 2011 | 2117516 | 423503 | 1694013 | 254796 | 50959 | 203837 | 414112 | 82822 | 331290 | 11339864 | 2267973 | 9071891 | 3128457 | 625665 | 2502792 | 3551983 | 710397 | 2841586 | 93905 | 1878 | 75124 | 80363 | 16073 | 64290 | 83125 | 16625 | 66500 | 384000 | 76800 | 307200 | 72144 | 14429 | 57715 | 88024 | 17605 | 70419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 45880 | 9176 | 36704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 61306 | 12261 | 49045 | 71447 | 14289 | 57158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2879214 | 11584467 | 3639946 | 727963 | 2911983 | 4254571 | 850914 | 3403657 | 14480584 | 2879214 | 11584467 | 3639946 | 727963 | 2911983 | 4254571 | 850914 | 3403657 | 185043 | 182883 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | CCI | 2011 | Q4 | Q4 - 2011 | 2117516 | 423503 | 1694013 | 504597 | 100919 | 403678 | 529494 | 105899 | 423595 | 11339864 | 2267973 | 9071891 | 4062838 | 812563 | 3250271 | 4422196 | 884439 | 3537757 | 93905 | 18781 | 75124 | 81430 | 16286 | 65144 | 83125 | 16625 | 66500 | 384000 | 76800 | 307200 | 72144 | 14429 | 57715 | 154180 | 30836 | 123344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 45880 | 9176 | 36704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 74018 | 14804 | 59214 | 84029 | 16806 | 67223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 4837907 | 967577 | 3870326 | 5318904 | 1063781 | 4255123 | 14480584 | 2896117 | 11584467 | 4837907 | 967577 | 3870326 | 5318904 | 1063781 | 4255123 | 370085 | 323190 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | CCI | 2012 | Q1 | Q1 - 2012 | 2117516 | 423503 | 1694013 | 568352 | 113670 | 454681 | 1468996 | 293799 | 1175197 | 11339864 | 2267973 | 9071891 | 4275854 | 855158 | 3420696 | 7755710 | 1551142 | 6204568 | 93905 | 18781 | 75124 | 81431 | 16286 | 65145 | 93905 | 18781 | 75124 | 384000 | 76800 | 307200 | 94995 | 18999 | 75996 | 175500 | 35100 | 140400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 57880 | 11576 | 46304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 100240 | 20048 | 80192 | 150000 | 30000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 5163752 | 1032737 | 4131014 | 9701991 | 1940398 | 7761593 | 14480584 | 2896117 | 11584467 | 5163752 | 1032737 | 4131014 | 9701991 | 1940398 | 7761593 | 675463 | 510471 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | CCI | 2012 | Q2 | Q2 - 2012 | 2117516 | 423503 | 1694013 | 781033 | 156207 | 624826 | 1468996 | 293799 | 1175197 | 11339864 | 2267973 | 9071891 | 5476746 | 1095349 | 4381397 | 8662990 | 1732598 | 6930392 | 93905 | 18781 | 75124 | 81641 | 16328 | 65313 | 93905 | 18781 | 75124 | 384000 | 76800 | 307200 | 239577 | 47915 | 191662 | 256500 | 51300 | 205200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 57880 | 11576 | 46304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 148960 | 29792 | 119168 | 167950 | 33590 | 134360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 6770837 | 1354167 | 5416670 | 10708221 | 2141644 | 8566577 | 14480584 | 2896117 | 11584467 | 6770837 | 1354167 | 5416670 | 10708221 | 2141644 | 8566577 | 610756 | 473186 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | CCI | 2012 | Q3 | Q3 - 2012 | 2117516 | 423503 | 1694013 | 999550 | 199910 | 799640 | 1468996 | 293799 | 1175197 | 11339864 | 2267973 | 9071891 | 7215381 | 1443077 | 5772304 | 8990600 | 1798120 | 7192480 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 384000 | 76800 | 307200 | 285821 | 57164 | 228657 | 290000 | 58000 | 232000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 57880 | 11576 | 46304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 189278 | 37856 | 151422 | 215000 | 43000 | 172000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 8826815 | 1765364 | 7061451 | 11116381 | 2223276 | 8893105 | 14480584 | 2896117 | 11584467 | 8826815 | 1765364 | 7061451 | 11116381 | 2223276 | 8893105 | 1286219 | 868632 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | CCI | 2012 | Q4 | Q4 - 2012 | 2117516 | 423503 | 1694013 | 1026671 | 205334 | 821337 | 1468996 | 293799 | 1175197 | 11339864 | 2267973 | 9071891 | 8710405 | 1742044 | 6968361 | 10210405 | 2042081 | 8168324 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 384000 | 76800 | 307200 | 315628 | 63126 | 252502 | 340000 | 68000 | 272000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 57880 | 11576 | 46304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 224102 | 44820 | 179282 | 260102 | 52020 | 208082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 10413591 | 2082681 | 8330910 | 12431288 | 2486257 | 9945031 | 14480584 | 2896117 | 11584467 | 10413591 | 2082681 | 8330910 | 12431288 | 2486257 | 9945031 | 1591597 | 1097880 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | CCI | 2013 | Q1 | Q1 - 2013 | 2117516 | 423503 | 1694013 | 1045967 | 209193 | 836774 | 2117516 | 423503 | 1694013 | 11339864 | 2267973 | 9071891 | 8946774 | 1789319 | 7157455 | 10500000 | 2100000 | 8400000 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 93905 | 18781 | 75124 | 384000 | 76800 | 307200 | 315665 | 63133 | 252532 | 384000 | 76800 | 307200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 60000 | 12000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 231087 | 46217 | 184870 | 280000 | 56000 | 224000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 10676278 | 2135219 | 8541059 | 13435421 | 2687084 | 10748337 | 14480584 | 2896117 | 11584467 | 10676278 | 2135219 | 8541059 | 13435421 | 2687084 | 10748337 | 2038689 | 1398904 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | CCI | 2013 | Q2 | Q2 - 2013 | 2117516 | 423503 | 1694013 | 1650718 | 330144 | 1320574 | 2650000 | 530000 | 2120000 | 11339864 | 2267973 | 9071891 | 10444363 | 2088872 | 8355491 | 10949923 | 2189984 | 8759939 | 93905 | 18781 | 75124 | 108148 | 21630 | 86518 | 108148 | 21630 | 86518 | 384000 | 76800 | 307200 | 352072 | 70414 | 281658 | 370334 | 74067 | 296267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 42880 | 8576 | 34304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 303680 | 60736 | 242944 | 359299 | 71860 | 287439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 12901861 | 2580372 | 10321489 | 14480584 | 2896117 | 11584467 | 14480584 | 2896117 | 11584467 | 12901861 | 2580372 | 10321489 | 14480584 | 2896117 | 11584467 | 2485782 | 1650651 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | CCI | 2013 | Q3 | Q3 - 2013 | 2117516 | 423503 | 1694013 | 2182735 | 436548 | 1746187 | 2214763 | 442952 | 1771811 | 11339864 | 2267973 | 9071891 | 10802955 | 2160590 | 8642365 | 11339864 | 2267973 | 9071891 | 93905 | 18781 | 75124 | 109143 | 21829 | 87314 | 109143 | 21829 | 87314 | 384000 | 76800 | 307200 | 370741 | 74148 | 296593 | 370741 | 74148 | 296593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 42880 | 8576 | 34304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 368193 | 73639 | 294554 | 403193 | 80639 | 322554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 13876647 | 2775330 | 11101317 | 14480584 | 2896117 | 11584467 | 14480584 | 2896117 | 11584467 | 13876647 | 2775330 | 11101317 | 14480584 | 2896117 | 11584467 | 0 | 1994382 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570104 | CCI | 2013 | Q4 | Q4 - 2013 | 2117516 | 423503 | 1694013 | 2348287 | 469657 | 1878630 | 2348287 | 469657 | 1878630 | 11339864 | 2267973 | 9071891 | 11270331 | 2331860 | 8938797 | 11310331 | 2371534 | 8938797 | 93905 | 18781 | 75124 | 109175 | 21835 | 87340 | 109175 | 21835 | 87340 | 384000 | 76800 | 307200 | 390933 | 78187 | 312746 | 390933 | 78187 | 312746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186000 | 37200 | 148800 | 42880 | 8576 | 34304 | 42880 | 8576 | 34304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359299 | 71860 | 287439 | 415812 | 83162 | 332650 | 415812 | 83162 | 332650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14480584 | 2896117 | 11584467 | 14577418 | 2993277 | 11584467 | 14617418 | 3032951 | 11584467 | 14480584 | 2896117 | 11584467 | 14577418 | 2993277 | 11584467 | 14617418 | 3032951 | 11584467 | 0 | 2354253 | Contact Network Inc. d/b/a InLine | TRUE
NT10BIX5570105 | CCI | 2010 | Q4 | Q4 - 2010 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 0 | 0 | 0 | 30000 | 0 | 30000 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 2287497 | 2287497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 0 | 0 | 0 | 250000 | 0 | 250000 | 1618825 | 0 | 1618825 | 0 | 0 | 0 | 94000 | 0 | 94000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 0 | 0 | 0 | 0 | 0 | 0 | 51188152 | 11550000 | 39638152 | 0 | 0 | 0 | 2661497 | 2287497 | 374000 | 51188152 | 11550000 | 39638152 | 0 | 0 | 0 | 2661497 | 2287497 | 374000 | 0 | 0 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | CCI | 2011 | Q1 | Q1 - 2011 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 0 | 0 | 0 | 30000 | 0 | 30000 | 14390880 | 11550000 | 2840880 | 589682 | 589682 | 0 | 689682 | 689682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 0 | 0 | 0 | 250000 | 0 | 250000 | 1618825 | 0 | 1618825 | 14477 | 0 | 14477 | 134000 | 0 | 134000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 0 | 0 | 0 | 0 | 0 | 0 | 51188152 | 11550000 | 39638152 | 604159 | 589682 | 14477 | 1103682 | 689682 | 414000 | 51188152 | 11550000 | 39638152 | 604159 | 589682 | 14477 | 1103682 | 689682 | 414000 | 0 | 0 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | CCI | 2011 | Q2 | Q2 - 2011 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 63458 | 0 | 63458 | 126801 | 0 | 126801 | 14390880 | 11550000 | 2840880 | 689682 | 689682 | 0 | 1086682 | 1086682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 0 | 0 | 0 | 250000 | 0 | 250000 | 1618825 | 0 | 1618825 | 90673 | 0 | 90673 | 115673 | 0 | 115673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 0 | 0 | 0 | 0 | 0 | 0 | 51188152 | 11550000 | 39638152 | 843813 | 689682 | 154131 | 1579156 | 1086682 | 492474 | 51188152 | 11550000 | 39638152 | 843813 | 689682 | 154131 | 1579156 | 1086682 | 492474 | 0 | 0 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | CCI | 2011 | Q3 | Q3 - 2011 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 78458 | 15000 | 63458 | 180000 | 30000 | 150000 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 0 | 0 | 0 | 250000 | 0 | 250000 | 1618825 | 0 | 1618825 | 133747 | 0 | 133747 | 133747 | 0 | 133747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 0 | 0 | 0 | 0 | 0 | 0 | 51188152 | 11550000 | 39638152 | 212205 | 15000 | 197205 | 663747 | 130000 | 533747 | 51188152 | 11550000 | 39638152 | 212205 | 15000 | 197205 | 663747 | 130000 | 533747 | 0 | 0 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | CCI | 2011 | Q4 | Q4 - 2011 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 150852 | 30000 | 120852 | 280000 | 30000 | 250000 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 0 | 0 | 0 | 250000 | 0 | 250000 | 1618825 | 0 | 1618825 | 133747 | 0 | 133747 | 133747 | 0 | 133747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 0 | 0 | 0 | 0 | 0 | 0 | 51188152 | 11550000 | 39638152 | 284599 | 30000 | 254599 | 763747 | 130000 | 633747 | 51188152 | 11550000 | 39638152 | 284599 | 30000 | 254599 | 763747 | 130000 | 633747 | 0 | 0 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | CCI | 2012 | Q1 | Q1 - 2012 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 148852 | 28000 | 120852 | 178000 | 28000 | 150000 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 43918 | 0 | 43918 | 150000 | 0 | 150000 | 1618825 | 0 | 1618825 | 134604 | 0 | 134604 | 134604 | 0 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 595 | 0 | 595 | 2000 | 0 | 2000 | 51188152 | 11550000 | 39638152 | 327969 | 28000 | 299969 | 464604 | 28000 | 436604 | 51188152 | 11550000 | 39638152 | 327969 | 28000 | 299969 | 464604 | 28000 | 436604 | 0 | 0 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | CCI | 2012 | Q2 | Q2 - 2012 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 148852 | 28000 | 120852 | 295591 | 28000 | 267591 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 43918 | 0 | 43918 | 100024 | 0 | 100024 | 1618825 | 0 | 1618825 | 134604 | 0 | 134604 | 134504 | 0 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 595 | 0 | 595 | 1800 | 0 | 1800 | 51188152 | 11550000 | 39638152 | 327969 | 28000 | 299969 | 531919 | 28000 | 504019 | 51188152 | 11550000 | 39638152 | 327969 | 28000 | 299969 | 531919 | 28000 | 504019 | 0 | 0 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | CCI | 2012 | Q3 | Q3 - 2012 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 323671 | 53975 | 269696 | 434344 | 0 | 434344 | 14390880 | 11550000 | 2840880 | 28000 | 28000 | 0 | 28000 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 43918 | 0 | 43918 | 100024 | 0 | 100024 | 1618825 | 0 | 1618825 | 134604 | 0 | 134604 | 134604 | 0 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 595 | 0 | 595 | 595 | 0 | 595 | 51188152 | 11550000 | 39638152 | 530788 | 81975 | 448813 | 697567 | 28000 | 669567 | 51188152 | 11550000 | 39638152 | 530788 | 81975 | 448813 | 697567 | 28000 | 669567 | 0 | 0 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | CCI | 2012 | Q4 | Q4 - 2012 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 457189 | 0 | 457189 | 789516 | 0 | 789516 | 14390880 | 11550000 | 2840880 | 28000 | 28000 | 0 | 28000 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 43918 | 0 | 43918 | 86638 | 0 | 86638 | 1618825 | 0 | 1618825 | 134604 | 0 | 134604 | 321804 | 0 | 321804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 822 | 0 | 822 | 822 | 0 | 822 | 51188152 | 11550000 | 39638152 | 664533 | 28000 | 636533 | 1226780 | 28000 | 1198780 | 51188152 | 11550000 | 39638152 | 664533 | 28000 | 636533 | 1226780 | 28000 | 1198780 | 0 | 0 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | CCI | 2013 | Q1 | Q1 - 2013 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 628852 | 0 | 628852 | 853935 | 0 | 853935 | 14390880 | 11550000 | 2840880 | 28000 | 28000 | 0 | 28000 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 107985 | 0 | 107985 | 108057 | 0 | 108057 | 1618825 | 0 | 1618825 | 134604 | 0 | 134604 | 238460 | 0 | 238460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 1755 | 0 | 1755 | 1755 | 0 | 1755 | 51188152 | 11550000 | 39638152 | 901196 | 28000 | 873196 | 1230207 | 28000 | 1202207 | 51188152 | 11550000 | 39638152 | 901196 | 28000 | 873196 | 1230207 | 28000 | 1202207 | 0 | 0 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | CCI | 2013 | Q2 | Q2 - 2013 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 882871 | 52960 | 829911 | 1294704 | 464792 | 829911 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 110309 | 0 | 110309 | 160611 | 50302 | 110309 | 1618825 | 0 | 1618825 | 162604 | 28000 | 134604 | 255124 | 120520 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 1755 | 0 | 1755 | 1755 | 0 | 1755 | 51188152 | 11550000 | 39638152 | 1157539 | 80960 | 1076579 | 1712194 | 635614 | 1076579 | 51188152 | 11550000 | 39638152 | 1157539 | 80960 | 1076579 | 1712194 | 635614 | 1076579 | 0 | 0 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | CCI | 2013 | Q3 | Q3 - 2013 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 1098598 | 256003 | 842595 | 1467182 | 348683 | 1118499 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 130611 | 20302 | 110309 | 157999 | 20302 | 137697 | 1618825 | 0 | 1618825 | 242735 | 108131 | 134604 | 270805 | 136202 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 1756 | 0 | 1756 | 1756 | 0 | 1756 | 51188152 | 11550000 | 39638152 | 1473700 | 384436 | 1089264 | 1897742 | 505187 | 1392556 | 51188152 | 11550000 | 39638152 | 1473700 | 384436 | 1089264 | 1897742 | 505187 | 1392556 | 0 | 0 | Treasury, New Jersey Department of | TRUE
NT10BIX5570105 | CCI | 2013 | Q4 | Q4 - 2013 | 13544926 | 0 | 13544926 | 0 | 0 | 0 | 0 | 0 | 0 | 11090600 | 0 | 11090600 | 0 | 0 | 0 | 0 | 0 | 0 | 502200 | 0 | 502200 | 1387503 | 531005 | 856498 | 1608180 | 728455 | 879726 | 14390880 | 11550000 | 2840880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2129868 | 0 | 2129868 | 139923 | 20302 | 119621 | 182549 | 20302 | 162247 | 1618825 | 0 | 1618825 | 270805 | 136202 | 134604 | 270805 | 136202 | 134604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7786518 | 0 | 7786518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124335 | 0 | 124335 | 1756 | 0 | 1756 | 1756 | 0 | 1756 | 51188152 | 11550000 | 39638152 | 1799987 | 687509 | 1112479 | 2063290 | 884959 | 1178333 | 51188152 | 11550000 | 39638152 | 1799987 | 687509 | 1112479 | 2063290 | 884959 | 1178333 | 0 | 0 | Treasury, New Jersey Department of | TRUE
NT10BIX5570106 | CCI | 2010 | Q4 | Q4 - 2010 | 198937 | 0 | 198937 | 0 | 0 | 0 | 0 | 0 | 0 | 7612371 | 2300000 | 5312371 | 0 | 0 | 0 | 0 | 0 | 0 | 895066 | 6000 | 889066 | 0 | 0 | 0 | 24000 | 2000 | 22000 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 15000 | 5000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 0 | 0 | 0 | 0 | 0 | 0 | 266356 | 36000 | 230356 | 0 | 0 | 0 | 61000 | 36000 | 25000 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 0 | 0 | 0 | 100000 | 43000 | 57000 | 9502006 | 2432000 | 7070006 | 0 | 0 | 0 | 100000 | 43000 | 57000 | 0 | 0 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | CCI | 2011 | Q1 | Q1 - 2011 | 198937 | 0 | 198937 | 0 | 0 | 0 | 0 | 0 | 0 | 7612371 | 2300000 | 5312371 | 0 | 0 | 0 | 230000 | 0 | 230000 | 895066 | 6000 | 889066 | 0 | 0 | 0 | 30000 | 0 | 30000 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 22500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 0 | 0 | 0 | 15000 | 0 | 15000 | 266356 | 36000 | 230356 | 15784 | 0 | 15784 | 75000 | 36000 | 39000 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 15784 | 0 | 15784 | 372500 | 58500 | 314000 | 9502006 | 2432000 | 7070006 | 15784 | 0 | 15784 | 372500 | 58500 | 314000 | 0 | 0 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | CCI | 2011 | Q2 | Q2 - 2011 | 198937 | 0 | 198937 | 0 | 0 | 0 | 3000 | 0 | 3000 | 7612371 | 2300000 | 5312371 | 0 | 0 | 0 | 2400000 | 2300000 | 100000 | 895066 | 6000 | 889066 | 7629 | 0 | 7629 | 20000 | 0 | 20000 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 110000 | 100000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 0 | 0 | 0 | 150000 | 0 | 150000 | 266356 | 36000 | 230356 | 15784 | 0 | 15784 | 55784 | 0 | 55784 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 23413 | 0 | 23413 | 2738784 | 2400000 | 338784 | 9502006 | 2432000 | 7070006 | 23413 | 0 | 23413 | 2738784 | 2400000 | 338784 | 0 | 0 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | CCI | 2011 | Q3 | Q3 - 2011 | 198937 | 0 | 198937 | 0 | 0 | 0 | 0 | 0 | 0 | 7612371 | 2300000 | 5312371 | 0 | 0 | 0 | 2400000 | 2400000 | 0 | 895066 | 6000 | 889066 | 38788 | 0 | 38788 | 62788 | 2000 | 60788 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 15000 | 5000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 13600 | 0 | 13600 | 266356 | 36000 | 230356 | 40002 | 0 | 40002 | 101002 | 36000 | 65002 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 92390 | 0 | 92390 | 2592390 | 2443000 | 149390 | 9502006 | 2432000 | 7070006 | 92390 | 0 | 92390 | 2592390 | 2443000 | 149390 | 0 | 0 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | CCI | 2011 | Q4 | Q4 - 2011 | 198937 | 0 | 198937 | 4363 | 0 | 4363 | 4363 | 0 | 4363 | 7612371 | 2300000 | 5312371 | 0 | 0 | 0 | 2400000 | 2400000 | 0 | 895066 | 6000 | 889066 | 63592 | 0 | 63592 | 122844 | 0 | 122844 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 15000 | 5000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 13600 | 0 | 13600 | 266356 | 36000 | 230356 | 40002 | 0 | 40002 | 40002 | 0 | 40002 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 121557 | 0 | 121557 | 2595809 | 2405000 | 190809 | 9502006 | 2432000 | 7070006 | 121557 | 0 | 121557 | 2595809 | 2405000 | 190809 | 0 | 0 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | CCI | 2012 | Q1 | Q1 - 2012 | 198937 | 0 | 198937 | 4363 | 0 | 4363 | 4363 | 0 | 4363 | 7612371 | 2300000 | 5312371 | 0 | 0 | 0 | 1886591 | 60000 | 1826591 | 895066 | 6000 | 889066 | 124963 | 0 | 124963 | 118759 | 0 | 118759 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 15000 | 5000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 13600 | 0 | 13600 | 266356 | 36000 | 230356 | 40002 | 0 | 40002 | 75079 | 35077 | 40002 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 182928 | 0 | 182928 | 2156167 | 130077 | 2026090 | 9502006 | 2432000 | 7070006 | 182928 | 0 | 182928 | 2156167 | 130077 | 2026090 | 0 | 0 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | CCI | 2012 | Q2 | Q2 - 2012 | 198937 | 0 | 198937 | 4363 | 0 | 4363 | 13000 | 8637 | 4363 | 7612371 | 2300000 | 5312371 | 150048 | 0 | 150048 | 4570808 | 2300000 | 2270808 | 895066 | 6000 | 889066 | 161486 | 0 | 161486 | 192506 | 6000 | 186506 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 70000 | 60000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 13600 | 0 | 13600 | 266356 | 36000 | 230356 | 65705 | 0 | 65705 | 65705 | 36000 | 65705 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 395202 | 0 | 395202 | 4968394 | 2440637 | 2563757 | 9502006 | 2432000 | 7070006 | 395202 | 0 | 395202 | 4968394 | 2440637 | 2563757 | 0 | 0 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | CCI | 2012 | Q3 | Q3 - 2012 | 198937 | 0 | 198937 | 4363 | 0 | 4363 | 18000 | 0 | 18000 | 7612371 | 2300000 | 5312371 | 2450048 | 2300000 | 874834 | 6870808 | 2300000 | 4570808 | 895066 | 6000 | 889066 | 130111 | 6000 | 124111 | 259126 | 6000 | 253126 | 185051 | 60000 | 125051 | 185051 | 60000 | 125051 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 13600 | 0 | 13600 | 266356 | 36000 | 230356 | 101705 | 36000 | 65705 | 101705 | 36000 | 65705 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 0 | 0 | 0 | 0 | 0 | 0 | 9502006 | 2432000 | 7070006 | 2927653 | 2432000 | 1220439 | 7491065 | 2432000 | 5059065 | 9502006 | 2432000 | 7070006 | 2927653 | 2432000 | 1220439 | 7491065 | 2432000 | 5059065 | 0 | 0 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | CCI | 2012 | Q4 | Q4 - 2012 | 198937 | 0 | 198937 | 17452 | 0 | 17452 | 198937 | 0 | 198937 | 7612371 | 2300000 | 5312371 | 4303394 | 2300000 | 2003394 | 5100000 | 2300000 | 2800000 | 895066 | 6000 | 889066 | 260439 | 6000 | 254439 | 483004 | 6000 | 477004 | 185051 | 60000 | 125051 | 103005 | 60000 | 43005 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 88456 | 0 | 88456 | 266356 | 36000 | 230356 | 101705 | 36000 | 65705 | 101705 | 36000 | 65705 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 15069 | 0 | 15069 | 15069 | 0 | 15069 | 9502006 | 2432000 | 7070006 | 4857439 | 2432000 | 2425439 | 6214997 | 2432000 | 3782997 | 9502006 | 2432000 | 7070006 | 4857439 | 2432000 | 2425439 | 6214997 | 2432000 | 3782997 | 0 | 0 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | CCI | 2013 | Q1 | Q1 - 2013 | 198937 | 0 | 198937 | 17452 | 0 | 17452 | 198937 | 0 | 198937 | 7612371 | 2300000 | 5312371 | 4623812 | 2300000 | 2323812 | 7612371 | 2300000 | 5312371 | 895066 | 6000 | 889066 | 488799 | 6000 | 482799 | 732799 | 6000 | 726799 | 185051 | 60000 | 125051 | 103005 | 60000 | 43005 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 88456 | 0 | 88456 | 266356 | 36000 | 230356 | 101705 | 36000 | 65705 | 101705 | 36000 | 65705 | 45600 | 0 | 45600 | 0 | 0 | 0 | 0 | 0 | 0 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 15069 | 0 | 15069 | 15069 | 0 | 15069 | 9502006 | 2432000 | 7070006 | 5406217 | 2432000 | 2974217 | 8977163 | 2432000 | 6545163 | 9502006 | 2432000 | 7070006 | 5406217 | 2432000 | 2974217 | 8977163 | 2432000 | 6545163 | 0 | 0 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | CCI | 2013 | Q2 | Q2 - 2013 | 198937 | 0 | 198937 | 17452 | 0 | 17452 | 198937 | 0 | 198937 | 7612371 | 2300000 | 5312371 | 5145801 | 2300000 | 2845801 | 7612371 | 2300000 | 5312371 | 895066 | 6000 | 889066 | 510039 | 6000 | 504039 | 895066 | 6000 | 889066 | 185051 | 60000 | 125051 | 103005 | 60000 | 43005 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 13600 | 0 | 13600 | 189600 | 0 | 189600 | 266356 | 36000 | 230356 | 101705 | 36000 | 65705 | 266356 | 36000 | 230356 | 45600 | 0 | 45600 | 0 | 0 | 0 | 45600 | 0 | 45600 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 22939 | 0 | 22939 | 66250 | 0 | 66250 | 9502006 | 2432000 | 7070006 | 5957316 | 2432000 | 3525316 | 9502006 | 2432000 | 7070006 | 9502006 | 2432000 | 7070006 | 5957316 | 2432000 | 3525316 | 9502006 | 2432000 | 7070006 | 0 | 0 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | CCI | 2013 | Q3 | Q3 - 2013 | 198937 | 0 | 198937 | 189900 | 0 | 189900 | 198937 | 0 | 198937 | 7612371 | 2300000 | 5312371 | 6137831 | 2300000 | 3837831 | 7612371 | 2300000 | 5312371 | 895066 | 6000 | 889066 | 668528 | 6000 | 662528 | 895066 | 6000 | 889066 | 185051 | 60000 | 125051 | 185051 | 60000 | 125051 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 189600 | 0 | 189600 | 189600 | 0 | 189600 | 266356 | 36000 | 230356 | 266356 | 36000 | 230356 | 266356 | 36000 | 230356 | 45600 | 0 | 45600 | 0 | 0 | 0 | 45600 | 0 | 45600 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 66250 | 0 | 66250 | 66250 | 0 | 66250 | 9502006 | 2432000 | 7070006 | 7746291 | 2432000 | 5314291 | 9502006 | 2432000 | 7070006 | 9502006 | 2432000 | 7070006 | 7746291 | 2432000 | 5314291 | 9502006 | 2432000 | 7070006 | 0 | 0 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | CCI | 2013 | Q4 | Q4 - 2013 | 198937 | 0 | 198937 | 198937 | 0 | 198937 | 198937 | 0 | 198937 | 7612371 | 2300000 | 5312371 | 6362280 | 2300000 | 4062280 | 7612371 | 2300000 | 5312371 | 895066 | 6000 | 889066 | 773581 | 6000 | 767581 | 895066 | 6000 | 889066 | 185051 | 60000 | 125051 | 185051 | 60000 | 125051 | 185051 | 60000 | 125051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189600 | 0 | 189600 | 189600 | 0 | 189600 | 189600 | 0 | 189600 | 266356 | 36000 | 230356 | 266356 | 36000 | 230356 | 266356 | 36000 | 230356 | 45600 | 0 | 45600 | 0 | 0 | 0 | 45600 | 0 | 45600 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 42775 | 30000 | 12775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 66250 | 0 | 66250 | 66250 | 0 | 66250 | 9502006 | 2432000 | 7070006 | 8084830 | 2432000 | 5652830 | 9502006 | 2432000 | 7070006 | 9502006 | 2432000 | 7070006 | 8084830 | 2432000 | 5652830 | 9502006 | 2432000 | 7070006 | 0 | 0 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570106 | CCI | 2014 | Q1 | Q1 - 2014 | 283594 | 0 | 283594 | 276054 | 0 | 276054 | 276054 | 0 | 276054 | 7631252 | 2336000 | 5295252 | 7615798 | 2336000 | 5279798 | 7615798 | 2336000 | 5279798 | 844749 | 0 | 844749 | 804912 | 0 | 804912 | 804912 | 0 | 804912 | 192551 | 66000 | 126551 | 192551 | 66000 | 126551 | 192551 | 66000 | 126551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204600 | 0 | 204600 | 204600 | 0 | 204600 | 204600 | 0 | 204600 | 217347 | 0 | 217347 | 217347 | 0 | 217347 | 217347 | 0 | 217347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61663 | 30000 | 31663 | 61663 | 30000 | 31663 | 61663 | 30000 | 31663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66250 | 0 | 66250 | 66250 | 0 | 66250 | 66250 | 0 | 66250 | 9502006 | 2432000 | 7070006 | 9439175 | 2432000 | 7007175 | 9439175 | 2432000 | 7007175 | 9502006 | 2432000 | 7070006 | 9439175 | 2432000 | 7007175 | 9439175 | 2432000 | 7007175 | 0 | 0 | Pyramid Lake Paiute Tribe | TRUE
NT10BIX5570107 | CCI | 2010 | Q4 | Q4 - 2010 | 1867707 | 911907 | 956700 | 0 | 0 | 0 | 342281 | 198790 | 143491 | 6819905 | 1923210 | 4895795 | 0 | 0 | 0 | 440978 | 123474 | 317504 | 113322 | 0 | 113322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687127 | 157169 | 529958 | 0 | 0 | 0 | 547458 | 157169 | 390289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 0 | 0 | 0 | 1330717 | 479433 | 851284 | 9543061 | 2992286 | 6550775 | 0 | 0 | 0 | 1330717 | 479433 | 851284 | 0 | 0 | Texas A&M University | TRUE
NT10BIX5570107 | CCI | 2011 | Q1 | Q1 - 2011 | 55000 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 8687612 | 2835117 | 5852495 | 0 | 0 | 0 | 1651633 | 581295 | 1070338 | 71820 | 0 | 71820 | 4624 | 0 | 4624 | 9000 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 8540 | 0 | 8540 | 567651 | 177213 | 390438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 13164 | 0 | 13164 | 2228284 | 758508 | 1469776 | 9543061 | 2992286 | 6550775 | 13164 | 0 | 13164 | 2228284 | 758508 | 1469776 | 0 | 0 | Texas A&M University | TRUE
NT10BIX5570107 | CCI | 2011 | Q2 | Q2 - 2011 | 55000 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 8687612 | 2835117 | 5852495 | 90 | 25 | 65 | 1328530 | 853499 | 475031 | 71820 | 0 | 71820 | 15959 | 0 | 15959 | 17959 | 0 | 17959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 23497 | 0 | 23497 | 549391 | 141922 | 407469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 39546 | 25 | 39521 | 1895880 | 995421 | 900459 | 9543061 | 2992286 | 6550775 | 39546 | 25 | 39521 | 1895880 | 995421 | 900459 | 0 | 0 | Texas A&M University | TRUE
NT10BIX5570107 | CCI | 2011 | Q3 | Q3 - 2011 | 55000 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 8687612 | 2835117 | 5852495 | 46561 | 0 | 46561 | 1075096 | 371157 | 703939 | 71820 | 0 | 71820 | 26286 | 0 | 26286 | 28286 | 0 | 28286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 33991 | 0 | 33991 | 525894 | 157169 | 368725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 106838 | 0 | 106838 | 1629276 | 528326 | 1100950 | 9543061 | 2992286 | 6550775 | 106838 | 0 | 106838 | 1629276 | 528326 | 1100950 | 0 | 0 | Texas A&M University | TRUE
NT10BIX5570107 | CCI | 2011 | Q4 | Q4 - 2011 | 55000 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 8687612 | 2835117 | 5852495 | 898815 | 374271 | 524544 | 2805993 | 915296 | 1890697 | 71820 | 0 | 71820 | 27295 | 0 | 27295 | 56442 | 0 | 56442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 33045 | 0 | 33045 | 34635 | 0 | 34635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 959155 | 374271 | 584884 | 2897070 | 915296 | 1981774 | 9543061 | 2992286 | 6550775 | 959155 | 374271 | 584884 | 2897070 | 915296 | 1981774 | 0 | 0 | Texas A&M University | TRUE
NT10BIX5570107 | CCI | 2012 | Q1 | Q1 - 2012 | 55000 | 0 | 55000 | 0 | 0 | 0 | 55000 | 0 | 55000 | 8687612 | 2835117 | 5852495 | 2651322 | 1080103 | 1571219 | 3858545 | 1466414 | 2392131 | 71820 | 0 | 71820 | 29011 | 0 | 29011 | 33000 | 0 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 419685 | 0 | 419685 | 439685 | 6400 | 433285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 3100018 | 1080103 | 2019915 | 4386230 | 1472814 | 2913416 | 9543061 | 2992286 | 6550775 | 3100018 | 1080103 | 2019915 | 4386230 | 1472814 | 2913416 | 0 | 0 | Texas A&M University | TRUE
NT10BIX5570107 | CCI | 2012 | Q2 | Q2 - 2012 | 55000 | 0 | 55000 | 0 | 0 | 0 | 55000 | 0 | 55000 | 8687612 | 2835117 | 5852495 | 3505607 | 1585644 | 1919962 | 5958470 | 2200000 | 3758470 | 71820 | 0 | 71820 | 29444 | 0 | 29444 | 37000 | 0 | 37000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 439644 | 0 | 439644 | 459644 | 6000 | 453644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 3974695 | 1585644 | 2389050 | 6510114 | 2206000 | 4304114 | 9543061 | 2992286 | 6550775 | 3974695 | 1585644 | 2389050 | 6510114 | 2206000 | 4304114 | 0 | 0 | Texas A&M University | TRUE
NT10BIX5570107 | CCI | 2012 | Q3 | Q3 - 2012 | 55000 | 0 | 55000 | 0 | 0 | 0 | 55000 | 0 | 55000 | 8687612 | 2835117 | 5852495 | 5247703 | 1899121 | 3348582 | 7247703 | 2499121 | 4748582 | 71820 | 0 | 71820 | 31190 | 0 | 31190 | 35000 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 451156 | 0 | 451156 | 471156 | 6000 | 465156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 5730049 | 1899121 | 3830928 | 7808859 | 2505121 | 5303738 | 9543061 | 2992286 | 6550775 | 5730049 | 1899121 | 3830928 | 7808859 | 2505121 | 5303738 | 0 | 0 | Texas A&M University | TRUE
NT10BIX5570107 | CCI | 2012 | Q4 | Q4 - 2012 | 55000 | 0 | 55000 | 23292 | 0 | 23292 | 34730 | 0 | 34730 | 8687612 | 2835117 | 5852495 | 5532658 | 2044235 | 3488423 | 6486155 | 2330284 | 4155871 | 71820 | 0 | 71820 | 35233 | 0 | 35233 | 39000 | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 470431 | 2319 | 468112 | 488431 | 5400 | 483031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 6061614 | 2046554 | 4015060 | 7048316 | 2335684 | 4712632 | 9543061 | 2992286 | 6550775 | 6061614 | 2046554 | 4015060 | 7048316 | 2335684 | 4712632 | 0 | 0 | Texas A&M University | TRUE
NT10BIX5570107 | CCI | 2013 | Q1 | Q1 - 2013 | 55000 | 0 | 55000 | 23292 | 0 | 23292 | 55000 | 0 | 55000 | 8687612 | 2835117 | 5852495 | 6917401 | 2085053 | 4832348 | 8562642 | 2740045 | 5822597 | 71820 | 0 | 71820 | 35957 | 0 | 35957 | 40957 | 0 | 40957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 490530 | 2319 | 488211 | 714056 | 149951 | 564105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 7467180 | 2087372 | 5379808 | 9372655 | 2889996 | 6482659 | 9543061 | 2992286 | 6550775 | 7467180 | 2087372 | 5379808 | 9372655 | 2889996 | 6482659 | 0 | 0 | Texas A&M University | TRUE
NT10BIX5570107 | CCI | 2013 | Q2 | Q2 - 2013 | 26333 | 0 | 26333 | 23292 | 0 | 23292 | 26364 | 0 | 26364 | 8716279 | 2835117 | 5881162 | 7808776 | 2405845 | 5402931 | 8952683 | 2988359 | 5964324 | 71820 | 0 | 71820 | 39522 | 1608 | 37914 | 52198 | 1608 | 50590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728629 | 157169 | 571460 | 502259 | 2319 | 499940 | 511814 | 2319 | 509495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 8373849 | 2409772 | 5964077 | 9543059 | 2992286 | 6550773 | 9543061 | 2992286 | 6550775 | 8373849 | 2409772 | 5964077 | 9543059 | 2992286 | 6550773 | 0 | 0 | Texas A&M University | TRUE
NT10BIX5570107 | CCI | 2013 | Q3 | Q3 - 2013 | 26364 | 0 | 26364 | 26364 | 0 | 26364 | 26364 | 0 | 26364 | 8949402 | 2988359 | 5961043 | 8949402 | 2988359 | 5961043 | 8949402 | 2988359 | 5961043 | 55481 | 1608 | 53873 | 55481 | 1608 | 53873 | 55481 | 1608 | 53873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511814 | 2319 | 509495 | 511814 | 2319 | 509495 | 511814 | 2319 | 509495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9543061 | 2992286 | 6550775 | 9543061 | 2992286 | 6550775 | 9543061 | 2992286 | 6550775 | 9543061 | 2992286 | 6550775 | 9543061 | 2992286 | 6550775 | 9543061 | 2992286 | 6550775 | 0 | 0 | Texas A&M University | TRUE
NT10BIX5570108 | CCI | 2010 | Q4 | Q4 - 2010 | 11275418 | 538950 | 10736468 | 0 | 0 | 0 | 905197 | 0 | 905197 | 63338112 | 30000000 | 33338112 | 0 | 0 | 0 | 0 | 0 | 0 | 2428175 | 222637 | 2205538 | 6359 | 6359 | 0 | 132151 | 24912 | 107239 | 1862000 | 1512000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 0 | 0 | 0 | 1540211 | 0 | 1540211 | 600000 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 124800 | 0 | 124800 | 0 | 0 | 0 | 11232 | 0 | 11232 | 1050000 | 0 | 1050000 | 0 | 0 | 0 | 34570 | 0 | 34570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 0 | 0 | 0 | 49000 | 0 | 49000 | 96382028 | 34486746 | 61895282 | 6359 | 6359 | 0 | 2672361 | 24912 | 2647449 | 96382028 | 34486746 | 61895282 | 6359 | 6359 | 0 | 2672361 | 24912 | 2647449 | 0 | 0 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | CCI | 2011 | Q1 | Q1 - 2011 | 11275418 | 538950 | 10736468 | 696413 | 0 | 696413 | 2797247 | 0 | 2797247 | 63338112 | 30000000 | 33338112 | 0 | 0 | 0 | 0 | 0 | 0 | 2428175 | 222637 | 2205538 | 187615 | 46199 | 141416 | 370993 | 0 | 370993 | 1862000 | 1512000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 1133512 | 0 | 1133512 | 2240678 | 0 | 2240678 | 600000 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 124800 | 0 | 124800 | 0 | 0 | 0 | 29952 | 0 | 29952 | 1050000 | 0 | 1050000 | 41160 | 0 | 41160 | 391160 | 0 | 391160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 2145272 | 2113326 | 31946 | 2250512 | 2218566 | 31946 | 96382028 | 34486746 | 61895282 | 4203972 | 2159525 | 2044447 | 8080542 | 2218566 | 5861976 | 96382028 | 34486746 | 61895282 | 4203972 | 2159525 | 2044447 | 8080542 | 2218566 | 5861976 | 0 | 0 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | CCI | 2011 | Q2 | Q2 - 2011 | 11275418 | 538950 | 10736468 | 714172 | 0 | 714172 | 3691381 | 0 | 3691381 | 63338112 | 30000000 | 33338112 | 0 | 0 | 0 | 0 | 0 | 0 | 2428175 | 222637 | 2205538 | 379533 | 92189 | 287344 | 634894 | 110967 | 523927 | 1862000 | 1512000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 1603702 | 0 | 1603702 | 2551578 | 0 | 2551578 | 600000 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 124800 | 0 | 124800 | 0 | 0 | 0 | 62400 | 0 | 62400 | 1050000 | 0 | 1050000 | 41160 | 0 | 41160 | 217516 | 0 | 217516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 2250512 | 2218566 | 31946 | 2250512 | 2218566 | 31946 | 96382028 | 34486746 | 61895282 | 4989079 | 2310755 | 2678324 | 9408281 | 2329533 | 7078748 | 96382028 | 34486746 | 61895282 | 4989079 | 2310755 | 2678324 | 9408281 | 2329533 | 7078748 | 0 | 0 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | CCI | 2011 | Q3 | Q3 - 2011 | 11275418 | 538950 | 10736468 | 3363817 | 0 | 3363817 | 5391115 | 0 | 5391115 | 63338112 | 30000000 | 33338112 | 22655 | 0 | 22655 | 432071 | 53674 | 378397 | 2309142 | 222637 | 2086505 | 544305 | 131652 | 412653 | 763183 | 176659 | 586524 | 1862000 | 1512000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5524880 | 0 | 5524880 | 2327211 | 0 | 2327211 | 3365211 | 0 | 3365211 | 600000 | 0 | 600000 | 0 | 0 | 0 | 51869 | 0 | 51869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 144381 | 0 | 144381 | 256173 | 0 | 256173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10422476 | 2213159 | 8209317 | 2286663 | 2227638 | 59025 | 2321113 | 2227638 | 93475 | 96382028 | 34486746 | 61895282 | 8689032 | 2359290 | 6329742 | 12580735 | 2457971 | 10122764 | 96382028 | 34486746 | 61895282 | 8689032 | 2359290 | 6329742 | 12580735 | 2457971 | 10122764 | 0 | 0 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | CCI | 2011 | Q4 | Q4 - 2011 | 11911943 | 538950 | 11372993 | 5267616 | 0 | 5267616 | 8098096 | 7535 | 8090561 | 64182920 | 30249603 | 33933317 | 22655 | 0 | 22655 | 2250899 | 2250899 | 0 | 2451362 | 222637 | 2228725 | 692477 | 179372 | 513105 | 902890 | 189872 | 713018 | 1862000 | 1512000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5173002 | 0 | 5173002 | 2894189 | 0 | 2894189 | 4041636 | 0 | 4041636 | 600000 | 0 | 600000 | 0 | 0 | 0 | 51864 | 0 | 51864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 276588 | 0 | 276588 | 308725 | 0 | 308725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9150801 | 1963556 | 7187245 | 2287906 | 2227638 | 60268 | 2289964 | 2227638 | 62326 | 96382028 | 34486746 | 61895282 | 11441431 | 2407010 | 9034421 | 17944074 | 4675944 | 13268130 | 96382028 | 34486746 | 61895282 | 11441431 | 2407010 | 9034421 | 17944074 | 4675944 | 13268130 | 538950 | 207510 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | CCI | 2012 | Q1 | Q1 - 2012 | 11275418 | 538950 | 10736468 | 6936014 | 0 | 6936014 | 8041408 | 0 | 8041408 | 63338112 | 30000000 | 33338112 | 3793811 | 3739320 | 54491 | 14018447 | 12463956 | 1554491 | 2428175 | 222637 | 2205538 | 1144170 | 216428 | 927742 | 1230761 | 222637 | 1008124 | 1862000 | 1512000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 4599436 | 0 | 4599436 | 4962251 | 0 | 4962251 | 600000 | 0 | 600000 | 31527 | 0 | 31527 | 51864 | 0 | 51864 | 124800 | 0 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 308362 | 0 | 308362 | 308362 | 0 | 308362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 2289964 | 2227638 | 62326 | 2389964 | 2227638 | 162326 | 96382028 | 34486746 | 61895282 | 19103284 | 6183386 | 12919898 | 31003057 | 14914231 | 16088826 | 96382028 | 34486746 | 61895282 | 19103284 | 6183386 | 12919898 | 31003057 | 14914231 | 16088826 | 538950 | 237368 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | CCI | 2012 | Q2 | Q2 - 2012 | 11275418 | 538950 | 10736468 | 8119998 | 0 | 8119998 | 8480718 | 0 | 8480718 | 63338112 | 30000000 | 33338112 | 13450046 | 11130510 | 2319536 | 25438137 | 20955630 | 4482507 | 2428175 | 222637 | 2205538 | 1258150 | 222637 | 1035513 | 1618880 | 222637 | 1396243 | 1862000 | 1512000 | 350000 | 269400 | 269400 | 0 | 404400 | 404400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 4942378 | 0 | 4942378 | 5467378 | 0 | 5467378 | 600000 | 0 | 600000 | 31527 | 0 | 31527 | 31527 | 0 | 31527 | 124800 | 0 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 310717 | 0 | 310717 | 350459 | 0 | 350459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 2289964 | 2227638 | 62326 | 3149687 | 2231238 | 918449 | 96382028 | 34486746 | 61895282 | 30672180 | 13850185 | 16821995 | 44941186 | 23813905 | 21127281 | 96382028 | 34486746 | 61895282 | 30672180 | 13850185 | 16821995 | 44941186 | 23813905 | 21127281 | 538950 | 459943 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | CCI | 2012 | Q3 | Q3 - 2012 | 11275418 | 538950 | 10736468 | 8216162 | 0 | 8216162 | 8572068 | 0 | 8572068 | 63338112 | 30000000 | 33338112 | 20627208 | 16493516 | 4133692 | 40599844 | 25874737 | 14725107 | 2428175 | 222637 | 2205538 | 1708398 | 378296 | 1330102 | 2321945 | 423296 | 1898649 | 1862000 | 1512000 | 350000 | 423500 | 423500 | 0 | 555650 | 555650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 5327409 | 0 | 5327409 | 5840232 | 0 | 5840232 | 600000 | 0 | 600000 | 41696 | 0 | 41696 | 41696 | 0 | 41696 | 124800 | 0 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 343795 | 0 | 343795 | 480760 | 0 | 480760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 3051229 | 2227638 | 823591 | 3299156 | 2227638 | 1071518 | 96382028 | 34486746 | 61895282 | 39739397 | 19522950 | 20216447 | 61711351 | 29081321 | 32630030 | 96382028 | 34486746 | 61895282 | 39739397 | 19522950 | 20216447 | 61711351 | 29081321 | 32630030 | 538950 | 499674 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | CCI | 2012 | Q4 | Q4 - 2012 | 11275418 | 538950 | 10736468 | 9135057 | 69044 | 9066013 | 9567863 | 180294 | 9387569 | 63338112 | 30000000 | 33338112 | 35762277 | 28434417 | 7327860 | 46572661 | 29032369 | 17540293 | 2428175 | 222637 | 2205538 | 2123685 | 434607 | 1689078 | 2220670 | 474607 | 1746063 | 1862000 | 1512000 | 350000 | 555650 | 555650 | 0 | 672850 | 672850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 5685717 | 0 | 5685717 | 5954315 | 0 | 5954315 | 600000 | 0 | 600000 | 41696 | 0 | 41696 | 41696 | 0 | 41696 | 124800 | 0 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 458098 | 0 | 458098 | 489807 | 0 | 489807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 3245539 | 2227638 | 1017901 | 4186414 | 2227638 | 1958776 | 96382028 | 34486746 | 61895282 | 57007719 | 31721356 | 25286363 | 69706276 | 32587758 | 37118519 | 96382028 | 34486746 | 61895282 | 57007719 | 31721356 | 25286363 | 69706276 | 32587758 | 37118519 | 538950 | 615807 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | CCI | 2013 | Q1 | Q1 - 2013 | 11275418 | 538950 | 10736468 | 9451186 | 179372 | 9271814 | 10991410 | 522150 | 10469260 | 63338112 | 30000000 | 33338112 | 44115588 | 29032368 | 15083220 | 52449030 | 29032369 | 23416661 | 2428175 | 222637 | 2205538 | 2261752 | 498915 | 1762837 | 2391273 | 561507 | 1829766 | 1862000 | 1512000 | 350000 | 642650 | 642650 | 0 | 642650 | 642650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 5833613 | 0 | 5833613 | 6018481 | 0 | 6018481 | 600000 | 0 | 600000 | 41696 | 0 | 41696 | 41696 | 0 | 41696 | 124800 | 0 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 531803 | 0 | 531803 | 571988 | 0 | 571988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 3245539 | 2227638 | 1017901 | 4334164 | 2227638 | 2106526 | 96382028 | 34486746 | 61895282 | 66123827 | 32580943 | 33542884 | 77440692 | 32986314 | 44454378 | 96382028 | 34486746 | 61895282 | 66123827 | 32580943 | 33542884 | 77440692 | 32986314 | 44454378 | 538950 | 630807 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | CCI | 2013 | Q2 | Q2 - 2013 | 11275418 | 538950 | 10736468 | 10778330 | 528950 | 10249380 | 11245402 | 550739 | 10694663 | 63338112 | 30000000 | 33338112 | 51311009 | 29032368 | 22278641 | 65224955 | 29032369 | 36192586 | 2428175 | 222637 | 2205538 | 2928141 | 931048 | 1997093 | 3156067 | 1094048 | 2062019 | 1862000 | 1512000 | 350000 | 628800 | 628800 | 0 | 628800 | 628800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 6759786 | 0 | 6759786 | 7035734 | 0 | 7035734 | 600000 | 0 | 600000 | 41696 | 0 | 41696 | 41696 | 0 | 41696 | 124800 | 0 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 667465 | 0 | 667465 | 667465 | 0 | 667465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 4184487 | 2227638 | 1956849 | 4226724 | 2227638 | 1999086 | 96382028 | 34486746 | 61895282 | 77299714 | 33348804 | 43950910 | 92226843 | 33533594 | 58693249 | 96382028 | 34486746 | 61895282 | 77299714 | 33348804 | 43950910 | 92226843 | 33533594 | 58693249 | 538950 | 630807 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | CCI | 2013 | Q3 | Q3 - 2013 | 11275418 | 538950 | 10736468 | 11675040 | 528950 | 11146090 | 15527526 | 541209 | 14986317 | 63338112 | 30000000 | 33338112 | 56200931 | 29032369 | 27168562 | 63965629 | 30018120 | 33947509 | 2428175 | 222637 | 2205538 | 3201402 | 1055896 | 2145506 | 3458138 | 1269085 | 2189053 | 1862000 | 1512000 | 350000 | 245912 | 245912 | 0 | 371463 | 371463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5266954 | 0 | 5266954 | 6932879 | 0 | 6932879 | 6980358 | 0 | 6980358 | 600000 | 0 | 600000 | 41696 | 0 | 41696 | 41696 | 0 | 41696 | 124800 | 0 | 124800 | 0 | 0 | 0 | 0 | 0 | 0 | 1050000 | 0 | 1050000 | 684626 | 0 | 684626 | 686692 | 0 | 686692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10436569 | 2213159 | 8223410 | 4227564 | 2227638 | 1999926 | 5297529 | 2258870 | 3038659 | 96382028 | 34486746 | 61895282 | 83210050 | 33090765 | 50119285 | 96329031 | 34458747 | 61870284 | 96382028 | 34486746 | 61895282 | 83210050 | 33090765 | 50119285 | 96329031 | 34458747 | 61870284 | 538950 | 632292 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570108 | CCI | 2013 | Q4 | Q4 - 2013 | 15514534 | 541209 | 14973325 | 15515296 | 541289 | 14974007 | 15515296 | 541289 | 14974007 | 63968722 | 30018120 | 33950602 | 62754769 | 29580054 | 33174715 | 62754769 | 29580054 | 33174715 | 3467696 | 1269084 | 2198612 | 3512189 | 1278979 | 2233210 | 3512189 | 1278979 | 2233210 | 399463 | 399463 | 0 | 399463 | 399463 | 0 | 399463 | 399463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7005603 | 0 | 7005603 | 6976457 | 0 | 6976457 | 6976457 | 0 | 6976457 | 41696 | 0 | 41696 | 41696 | 0 | 41696 | 41696 | 0 | 41696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 686691 | 0 | 686691 | 686691 | 0 | 686691 | 686691 | 0 | 686691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5297623 | 2258870 | 3038753 | 5287961 | 2249798 | 3038163 | 5287961 | 2249798 | 3038163 | 96382028 | 34486746 | 61895282 | 95174522 | 34049583 | 61124939 | 95174522 | 34049583 | 61124939 | 96382028 | 34486746 | 61895282 | 95174522 | 34049583 | 61124939 | 95174522 | 34049583 | 61124939 | 0 | 0 | Central Management Services, Illinois Department of | TRUE
NT10BIX5570109 | CCI | 2010 | Q4 | Q4 - 2010 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 0 | 0 | 0 | 5474045 | 1094809 | 4379236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 0 | 0 | 0 | 175000 | 35000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 0 | 0 | 0 | 175000 | 35000 | 140000 | 7494500 | 1498900 | 5995600 | 0 | 0 | 0 | 175000 | 35000 | 140000 | 0 | 0 | Carver, County of | TRUE
NT10BIX5570109 | CCI | 2011 | Q1 | Q1 - 2011 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 0 | 0 | 0 | 5474045 | 1094809 | 4379236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 9067 | 1814 | 7253 | 180000 | 36000 | 144000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494498 | 1498900 | 5995600 | 9067 | 1814 | 7253 | 180000 | 36000 | 144000 | 7494498 | 1498900 | 5995600 | 9067 | 1814 | 7253 | 180000 | 36000 | 144000 | 0 | 0 | Carver, County of | TRUE
NT10BIX5570109 | CCI | 2011 | Q2 | Q2 - 2011 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 0 | 0 | 0 | 5474045 | 1094809 | 4379236 | 0 | 0 | 0 | 2262002 | 452400 | 1809602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 64061 | 12812 | 51249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 13320 | 2664 | 10656 | 450000 | 90000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 19305 | 3861 | 15444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494498 | 1498900 | 5995600 | 13320 | 2664 | 10656 | 2795368 | 559073 | 2236295 | 7494498 | 1498900 | 5995600 | 13320 | 2664 | 10656 | 2795368 | 559073 | 2236295 | 0 | 0 | Carver, County of | TRUE
NT10BIX5570109 | CCI | 2011 | Q3 | Q3 - 2011 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 0 | 0 | 0 | 5474045 | 1094809 | 4379236 | 1184393 | 236879 | 947514 | 4496700 | 3597360 | 899340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 237936 | 47587 | 190349 | 300000 | 240000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 1422329 | 284466 | 1137863 | 4796700 | 3837360 | 959340 | 7494500 | 1498900 | 5995600 | 1422329 | 284466 | 1137863 | 4796700 | 3837360 | 959340 | 0 | 0 | Carver, County of | TRUE
NT10BIX5570109 | CCI | 2011 | Q4 | Q4 - 2011 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 0 | 0 | 0 | 5474045 | 1094809 | 4379236 | 2659872 | 531974 | 2127898 | 4126000 | 825200 | 3300800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 269975 | 53995 | 215980 | 370000 | 74000 | 296000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 2929847 | 585969 | 2343878 | 4496000 | 899200 | 3596800 | 7494500 | 1498900 | 5995600 | 2929847 | 585969 | 2343878 | 4496000 | 899200 | 3596800 | 0 | 0 | Carver, County of | TRUE
NT10BIX5570109 | CCI | 2012 | Q1 | Q1 - 2012 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 0 | 0 | 0 | 5474045 | 1094809 | 4379236 | 4109181 | 821837 | 3287344 | 5020930 | 1004186 | 4016744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 424009 | 84801 | 339208 | 525000 | 105000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 4533190 | 906638 | 3626552 | 5545930 | 1109186 | 4436744 | 7494500 | 1498900 | 5995600 | 4533190 | 906638 | 3626552 | 5545930 | 1109186 | 4436744 | 0 | 0 | Carver, County of | TRUE
NT10BIX5570109 | CCI | 2012 | Q2 | Q2 - 2012 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 400000 | 80000 | 320000 | 5474045 | 1094809 | 4379236 | 4875647 | 975129 | 3900518 | 5300000 | 1060000 | 4240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 454039 | 90808 | 363231 | 550000 | 110000 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 375 | 75 | 300 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 5329686 | 1065937 | 4263749 | 6500097 | 1300019 | 5200078 | 7494500 | 1498900 | 5995600 | 5329686 | 1065937 | 4263749 | 6500097 | 1300019 | 5200078 | 0 | 75000 | Carver, County of | TRUE
NT10BIX5570109 | CCI | 2012 | Q3 | Q3 - 2012 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 300000 | 60000 | 240000 | 5474045 | 1094809 | 4379236 | 5647615 | 1129523 | 4518092 | 5647615 | 1129523 | 4518092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 488539 | 97708 | 390831 | 600000 | 120000 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 375 | 75 | 300 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 6136154 | 1227231 | 4908923 | 6797712 | 1359542 | 5438170 | 7494500 | 1498900 | 5995600 | 6136154 | 1227231 | 4908923 | 6797712 | 1359542 | 5438170 | 0 | 75000 | Carver, County of | TRUE
NT10BIX5570109 | CCI | 2012 | Q4 | Q4 - 2012 | 803598 | 160720 | 642878 | 0 | 0 | 0 | 250000 | 50000 | 200000 | 5474045 | 1094809 | 4379236 | 5733798 | 1146760 | 4587038 | 6080000 | 1216000 | 4864000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 522097 | 104419 | 417678 | 625000 | 125000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 6255895 | 1251179 | 5004716 | 7204722 | 1440944 | 5763778 | 7494500 | 1498900 | 5995600 | 6255895 | 1251179 | 5004716 | 7204722 | 1440944 | 5763778 | 0 | 75000 | Carver, County of | TRUE
NT10BIX5570109 | CCI | 2013 | Q1 | Q1 - 2013 | 803598 | 160720 | 642878 | 51368 | 10274 | 41094 | 803598 | 160720 | 642878 | 5474045 | 1094809 | 4379236 | 5733798 | 1146760 | 4587038 | 5869483 | 1173896 | 4695586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 95249 | 19050 | 76199 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 827321 | 165464 | 661857 | 966760 | 193352 | 773408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 375 | 75 | 300 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 6707736 | 1341548 | 5366188 | 7889938 | 1577987 | 6311950 | 7494500 | 1498900 | 5995600 | 6707736 | 1341548 | 5366188 | 7889938 | 1577987 | 6311950 | 0 | 395438 | Carver, County of | TRUE
NT10BIX5570109 | CCI | 2013 | Q2 | Q2 - 2013 | 803598 | 160720 | 642878 | 191394 | 38279 | 153115 | 803598 | 160720 | 642878 | 5474045 | 1094809 | 4379236 | 5770109 | 1154022 | 4616087 | 5770109 | 1154022 | 4616087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 95249 | 19050 | 76199 | 191807 | 38361 | 153446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 835360 | 167072 | 668288 | 966760 | 193352 | 773408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 375 | 75 | 300 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 6892112 | 1378423 | 5513689 | 7790564 | 1558113 | 6232451 | 7494500 | 1498900 | 5995600 | 6892112 | 1378423 | 5513689 | 7790564 | 1558113 | 6232451 | 0 | 395438 | Carver, County of | TRUE
NT10BIX5570109 | CCI | 2013 | Q3 | Q3 - 2013 | 803598 | 160720 | 642878 | 653085 | 130617 | 522468 | 653085 | 130617 | 522468 | 5474045 | 1094809 | 4379236 | 6147198 | 1524670 | 4622528 | 6147198 | 1524670 | 4622528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191807 | 38361 | 153446 | 95249 | 19050 | 76199 | 95249 | 19050 | 76199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966760 | 193352 | 773408 | 994406 | 220001 | 774405 | 994406 | 220001 | 774405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 75 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 57915 | 11583 | 46332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7494500 | 1498900 | 5995600 | 7889938 | 1894338 | 5995600 | 7889938 | 1894338 | 5995600 | 7494500 | 1498900 | 5995600 | 7889938 | 1894338 | 5995600 | 7889938 | 1894338 | 5995600 | 0 | 395438 | Carver, County of | TRUE
NT10BIX5570111 | CCI | 2010 | Q4 | Q4 - 2010 | 15239344 | 4672381 | 10566963 | 0 | 0 | 0 | 500000 | 0 | 500000 | 52877030 | 16403258 | 36473772 | 0 | 0 | 0 | 0 | 0 | 0 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100722 | 2018722 | 82000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 74820 | 7431420 | 0 | 0 | 0 | 400000 | 0 | 400000 | 21573 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77998901 | 23444746 | 54554155 | 0 | 0 | 0 | 900000 | 0 | 900000 | 77998901 | 23444746 | 54554155 | 0 | 0 | 0 | 900000 | 0 | 900000 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570111 | CCI | 2011 | Q1 | Q1 - 2011 | 15239344 | 4672381 | 10566963 | 0 | 0 | 0 | 0 | 0 | 0 | 52877030 | 16526459 | 36350571 | 0 | 0 | 0 | 0 | 0 | 0 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100722 | 2018722 | 82000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 288044 | 153979 | 134065 | 750000 | 350000 | 400000 | 21573 | 0 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77998901 | 23546554 | 54452347 | 288044 | 153979 | 134065 | 750000 | 350000 | 400000 | 77998901 | 23546554 | 54452347 | 288044 | 153979 | 134065 | 750000 | 350000 | 400000 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570111 | CCI | 2011 | Q2 | Q2 - 2011 | 15239344 | 4672381 | 10566963 | 0 | 0 | 0 | 11500000 | 11500000 | 0 | 52877030 | 16526459 | 36350571 | 0 | 0 | 0 | 0 | 0 | 0 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100722 | 2018722 | 82000 | 0 | 0 | 0 | 3000000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 699993 | 153979 | 546014 | 1000000 | 200000 | 800000 | 21573 | 0 | 21573 | 25225 | 0 | 25225 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77998901 | 23546554 | 54452347 | 725218 | 153979 | 571239 | 15575000 | 14700000 | 875000 | 77998901 | 23546554 | 54452347 | 725218 | 153979 | 571239 | 15575000 | 14700000 | 875000 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570111 | CCI | 2011 | Q3 | Q3 - 2011 | 15239344 | 4672381 | 10566963 | 3968916 | 3968916 | 0 | 3968916 | 3968916 | 0 | 52877030 | 16526459 | 36350571 | 7357073 | 7357073 | 0 | 7357073 | 7357073 | 0 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100722 | 2018722 | 82000 | 3053368 | 3053368 | 0 | 3053368 | 3053368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 983851 | 153979 | 829873 | 1500000 | 154000 | 1346000 | 21573 | 0 | 21573 | 102329 | 0 | 102329 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77998901 | 23546554 | 54452347 | 15465537 | 14533336 | 932202 | 16079357 | 14533357 | 1546000 | 77998901 | 23546554 | 54452347 | 15465537 | 14533336 | 932202 | 16079357 | 14533357 | 1546000 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570111 | CCI | 2011 | Q4 | Q4 - 2011 | 15239344 | 4672381 | 10566963 | 3968916 | 3968916 | 0 | 3968916 | 3968916 | 0 | 52877030 | 16526459 | 36350571 | 7357073 | 7357073 | 0 | 7357073 | 7357073 | 0 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100722 | 2018722 | 82000 | 3053368 | 3053368 | 0 | 3053368 | 3053368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 1434030 | 153979 | 1280051 | 2750000 | 153979 | 2596021 | 21573 | 0 | 21573 | 357447 | 0 | 357447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77998901 | 23546554 | 54452347 | 16170834 | 14533336 | 1637498 | 17129357 | 14533336 | 2596021 | 77998901 | 23546554 | 54452347 | 16170834 | 14533336 | 1637498 | 17129357 | 14533336 | 2596021 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570111 | CCI | 2012 | Q1 | Q1 - 2012 | 15689615 | 5122652 | 10566963 | 3968916 | 3968916 | 0 | 3968916 | 3968916 | 0 | 48655161 | 12304590 | 36350571 | 7357073 | 7357073 | 0 | 7357073 | 7357073 | 0 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3180508 | 3098508 | 82000 | 3053368 | 3053368 | 0 | 3053368 | 3053368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 2385083 | 153979 | 2231104 | 3100000 | 153979 | 2946021 | 21573 | 0 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75307089 | 20854742 | 54452347 | 16764440 | 14533336 | 2231104 | 17479357 | 14533336 | 2946021 | 75307089 | 20854742 | 54452347 | 16764440 | 14533336 | 2231104 | 17479357 | 14533336 | 2946021 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570111 | CCI | 2012 | Q2 | Q2 - 2012 | 15689615 | 5122652 | 10566963 | 4664490 | 3968916 | 695574 | 5000000 | 3968916 | 1031084 | 48655161 | 12304590 | 36350571 | 8193530 | 7506448 | 687082 | 11993530 | 7900000 | 4093530 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3180508 | 3098508 | 82000 | 3053368 | 3053368 | 0 | 3053368 | 3053368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 3115021 | 153979 | 2961042 | 4156171 | 153979 | 4002192 | 21573 | 0 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75307089 | 20854742 | 54452347 | 19026409 | 14682711 | 4343698 | 24203069 | 15076263 | 9126806 | 75307089 | 20854742 | 54452347 | 19026409 | 14682711 | 4343698 | 24203069 | 15076263 | 9126806 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570111 | CCI | 2012 | Q3 | Q3 - 2012 | 15689615 | 5122652 | 10566963 | 5596246 | 3968916 | 1627330 | 6596246 | 3968916 | 2627330 | 48655161 | 12304590 | 36350571 | 13604772 | 7728726 | 5876046 | 23364772 | 9000000 | 14364772 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3180508 | 3098508 | 82000 | 3053368 | 3053368 | 0 | 3053368 | 3053368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 3988487 | 0 | 3988487 | 5000000 | 0 | 5000000 | 21573 | 0 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 536 | 0 | 536 | 1000 | 0 | 1000 | 75307089 | 20854742 | 54452347 | 26243409 | 14751010 | 11492399 | 38015386 | 16022284 | 21993102 | 75307089 | 20854742 | 54452347 | 26243409 | 14751010 | 11492399 | 38015386 | 16022284 | 21993102 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570111 | CCI | 2012 | Q4 | Q4 - 2012 | 15689615 | 5122652 | 10566963 | 6186044 | 3968916 | 2217128 | 10000000 | 4000000 | 6000000 | 48655161 | 12304590 | 36350571 | 26648395 | 8012214 | 18636181 | 34000000 | 9500000 | 24500000 | 199992 | 199992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3180508 | 3098508 | 82000 | 3056139 | 3053368 | 2771 | 3056139 | 3053368 | 2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 5042327 | 0 | 5042327 | 6000000 | 0 | 6000000 | 21573 | 0 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 536 | 0 | 536 | 1000 | 0 | 1000 | 75307089 | 20854742 | 54452347 | 40933441 | 15034498 | 25898943 | 53057139 | 16553368 | 36503771 | 75307089 | 20854742 | 54452347 | 40933441 | 15034498 | 25898943 | 53057139 | 16553368 | 36503771 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570111 | CCI | 2013 | Q1 | Q1 - 2013 | 15689615 | 5122652 | 10566963 | 6927305 | 3968916 | 2958389 | 8050000 | 3968916 | 4081084 | 48655161 | 12304590 | 36350571 | 27930683 | 8066313 | 19864370 | 34000000 | 9000000 | 25000000 | 199992 | 199992 | 0 | 740 | 0 | 740 | 1000 | 0 | 1000 | 3180508 | 3098508 | 82000 | 3056139 | 3053368 | 2771 | 3056139 | 3053368 | 2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 6444908 | 0 | 6444908 | 7250000 | 0 | 7250000 | 21573 | 0 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 835 | 0 | 835 | 1000 | 0 | 1000 | 75307089 | 20854742 | 54452347 | 44360610 | 15088597 | 29272013 | 52358139 | 16022284 | 36335855 | 75307089 | 20854742 | 54452347 | 44360610 | 15088597 | 29272013 | 52358139 | 16022284 | 36335855 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570111 | CCI | 2013 | Q2 | Q2 - 2013 | 15689615 | 5122652 | 10566963 | 7487030 | 3968916 | 3518114 | 8050000 | 3968916 | 4081084 | 48655161 | 12304590 | 36350571 | 29298798 | 8179513 | 21119285 | 34000000 | 9000000 | 25000000 | 199992 | 199992 | 0 | 740 | 0 | 740 | 740 | 0 | 740 | 3180508 | 3098508 | 82000 | 3360873 | 3053368 | 307505 | 3360873 | 3053368 | 307505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 7267741 | 0 | 7267741 | 7900000 | 0 | 7900000 | 21573 | 0 | 21573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 32074 | 0 | 32074 | 32074 | 0 | 32074 | 75307089 | 20854742 | 54452347 | 47447256 | 15201797 | 32245459 | 53343687 | 16022284 | 37321403 | 75307089 | 20854742 | 54452347 | 47447256 | 15201797 | 32245459 | 53343687 | 16022284 | 37321403 | 0 | 4343 | Northwest Open Access Network | TRUE
NT10BIX5570111 | CCI | 2013 | Q3 | Q3 - 2013 | 15689615 | 5122652 | 10566963 | 10042810 | 3968916 | 6073894 | 10042810 | 3968916 | 6073894 | 48655161 | 12304590 | 36350571 | 39336582 | 10431181 | 28905401 | 39336582 | 10431181 | 28905401 | 199992 | 199992 | 0 | 740 | 0 | 740 | 740 | 0 | 740 | 3180508 | 3098508 | 82000 | 3366523 | 3053368 | 313155 | 3366523 | 3053368 | 313155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7506240 | 75000 | 7431240 | 6496891 | 0 | 6496891 | 6496891 | 0 | 6496891 | 21573 | 0 | 21573 | 3396309 | 0 | 3396309 | 3396309 | 0 | 3396309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54000 | 54000 | 0 | 163405 | 0 | 163405 | 163405 | 0 | 163405 | 75307089 | 20854742 | 54452347 | 62803260 | 17453465 | 45349795 | 62803260 | 17453465 | 45349795 | 75307089 | 20854742 | 54452347 | 62803260 | 17453465 | 45349795 | 62803260 | 17453465 | 45349795 | 0 | 0 | Northwest Open Access Network | TRUE
NT10BIX5570112 | CCI | 2010 | Q4 | Q4 - 2010 | 3588505 | 1076552 | 2511953 | 1121773 | 1121773 | 0 | 1121773 | 1121773 | 0 | 9349257 | 2804777 | 6544480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 0 | 0 | 0 | 15000 | 4500 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753523 | 526057 | 1227466 | 199413 | 184745 | 14668 | 509182 | 277676 | 231506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075249 | 322575 | 752674 | 59737 | 17921 | 41816 | 139866 | 41960 | 97906 | 16496952 | 4949086 | 11547866 | 1380923 | 1324439 | 56484 | 1785821 | 1445909 | 339912 | 16496952 | 4949086 | 11547866 | 1380923 | 1324439 | 56484 | 1785821 | 1445909 | 339912 | 0 | 0 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | CCI | 2011 | Q1 | Q1 - 2011 | 3588505 | 1076552 | 2511953 | 1121773 | 1121773 | 0 | 2321773 | 1121773 | 1200000 | 9349257 | 2804777 | 6544480 | 0 | 0 | 0 | 1150000 | 0 | 1150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753523 | 526057 | 1227466 | 379433 | 184835 | 194598 | 554433 | 184835 | 369598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075249 | 322575 | 752674 | 154732 | 17921 | 136811 | 254732 | 17921 | 236811 | 16496952 | 4949086 | 11547866 | 1655938 | 1324529 | 331409 | 4295938 | 1324529 | 2971409 | 16496952 | 4949086 | 11547866 | 1655938 | 1324529 | 331409 | 4295938 | 1324529 | 2971409 | 0 | 0 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | CCI | 2011 | Q2 | Q2 - 2011 | 3588505 | 1076552 | 2511953 | 2051720 | 1121773 | 929947 | 2151720 | 1121773 | 1029947 | 9349257 | 2804777 | 6544480 | 4587 | 0 | 4587 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 8031 | 0 | 8031 | 23000 | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753253 | 526057 | 1227466 | 517635 | 184745 | 332890 | 657635 | 184745 | 472890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075249 | 322575 | 752674 | 270910 | 17921 | 252989 | 385910 | 17921 | 367989 | 16496682 | 4949086 | 11547866 | 2852883 | 1324439 | 1528444 | 5268265 | 1324439 | 3943826 | 16496682 | 4949086 | 11547866 | 2852883 | 1324439 | 1528444 | 5268265 | 1324439 | 3943826 | 0 | 35239 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | CCI | 2011 | Q3 | Q3 - 2011 | 3706362 | 1111909 | 2594453 | 2353241 | 1136423 | 1216818 | 2753231 | 1316423 | 1436808 | 9349257 | 2804777 | 6544480 | 1734997 | 71004 | 1663993 | 4284997 | 871004 | 3413993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 8031 | 0 | 8031 | 32031 | 7200 | 24831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366720 | 410016 | 956704 | 603645 | 188110 | 415535 | 848645 | 296610 | 552035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 0 | 0 | 0 | 50000 | 15000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344195 | 403259 | 940936 | 585537 | 19966 | 565571 | 770537 | 110466 | 660071 | 16496952 | 4949086 | 11547866 | 5285451 | 1415503 | 3869948 | 8739441 | 2616703 | 6122738 | 16496952 | 4949086 | 11547866 | 5285451 | 1415503 | 3869948 | 8739441 | 2616703 | 6122738 | 0 | 195771 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | CCI | 2011 | Q4 | Q4 - 2011 | 3706362 | 1111909 | 2594453 | 2578721 | 1211484 | 1367237 | 2828721 | 1286484 | 1542237 | 9349257 | 2804777 | 6544480 | 2587316 | 407151 | 2180165 | 3837316 | 782151 | 3055165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 26623 | 5578 | 21045 | 51623 | 13078 | 38545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366720 | 410016 | 956704 | 732125 | 242340 | 489785 | 907125 | 294840 | 612285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 0 | 0 | 0 | 10000 | 3000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344195 | 403259 | 940936 | 720912 | 91746 | 629166 | 870912 | 136746 | 734166 | 16496952 | 4949086 | 11547866 | 6645697 | 1958299 | 4687398 | 8505697 | 2516299 | 5989398 | 16496952 | 4949086 | 11547866 | 6645697 | 1958299 | 4687398 | 8505697 | 2516299 | 5989398 | 0 | 0 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | CCI | 2012 | Q1 | Q1 - 2012 | 3706362 | 1111909 | 2594453 | 2750048 | 1266578 | 1483470 | 2900047 | 1311578 | 1588469 | 9349257 | 2804777 | 6544480 | 3421283 | 689818 | 2731465 | 4421283 | 989818 | 3431465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 46722 | 12010 | 34712 | 86722 | 24010 | 62712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366720 | 410016 | 956704 | 1052333 | 338945 | 713388 | 1227333 | 391445 | 835888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 3027 | 908 | 2119 | 18027 | 5408 | 12619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344195 | 403259 | 940936 | 914906 | 152652 | 762254 | 1094906 | 206652 | 888254 | 16496952 | 4949086 | 11547866 | 8188319 | 2460911 | 5727408 | 9748318 | 2928911 | 6819407 | 16496952 | 4949086 | 11547866 | 8188319 | 2460911 | 5727408 | 9748318 | 2928911 | 6819407 | 0 | 0 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | CCI | 2012 | Q2 | Q2 - 2012 | 3706362 | 1111909 | 2594453 | 2859307 | 1299356 | 1559951 | 3154307 | 1387856 | 1766451 | 9349257 | 2804777 | 6544480 | 5609699 | 1346343 | 4263356 | 8062670 | 2082234 | 5980436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 77383 | 21208 | 56175 | 169092 | 48717 | 120375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366720 | 410016 | 956704 | 1179046 | 376959 | 802087 | 1278046 | 406659 | 871387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 3027 | 908 | 2119 | 45027 | 13508 | 31519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344195 | 403259 | 940936 | 1149909 | 223153 | 926756 | 1352833 | 284030 | 1068803 | 16496952 | 4949086 | 11547866 | 10878371 | 3267927 | 7610444 | 14061975 | 4223004 | 9838971 | 16496952 | 4949086 | 11547866 | 10878371 | 3267927 | 7610444 | 14061975 | 4223004 | 9838971 | 0 | 0 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | CCI | 2012 | Q3 | Q3 - 2012 | 3706362 | 1111909 | 2594453 | 3135065 | 1382083 | 1752982 | 3185065 | 1397083 | 1787982 | 9349257 | 2804777 | 6544480 | 7654781 | 1959868 | 5694913 | 8154781 | 2109868 | 6044913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 119079 | 33717 | 85362 | 129079 | 36717 | 92362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366720 | 410016 | 956704 | 1220155 | 389291 | 830864 | 1330155 | 422291 | 907864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 55969 | 16791 | 39178 | 120969 | 36291 | 84678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344195 | 403259 | 940936 | 1372904 | 290051 | 1082853 | 1552903 | 344051 | 1208852 | 16496952 | 4949086 | 11547866 | 13557953 | 4071801 | 9486152 | 14472952 | 4346301 | 10126651 | 16496952 | 4949086 | 11547866 | 13557953 | 4071801 | 9486152 | 14472952 | 4346301 | 10126651 | 0 | 626464 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | CCI | 2012 | Q4 | Q4 - 2012 | 3706362 | 1111909 | 2594453 | 3169637 | 1392455 | 1777182 | 3269637 | 1422455 | 1847182 | 9349257 | 2804777 | 6544480 | 7835871 | 2014194 | 5821676 | 8635871 | 2254195 | 6381676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 122216 | 34658 | 87558 | 132216 | 37658 | 94558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366720 | 410016 | 956704 | 1282062 | 407863 | 874199 | 1292062 | 410863 | 881199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 115722 | 34717 | 81005 | 125722 | 37717 | 88005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344195 | 403259 | 940936 | 1644933 | 371660 | 1273273 | 1804933 | 419660 | 1385273 | 16496952 | 4949086 | 11547866 | 14170441 | 4255547 | 9914893 | 15260441 | 4582548 | 10677893 | 16496952 | 4949086 | 11547866 | 14170441 | 4255547 | 9914893 | 15260441 | 4582548 | 10677893 | 0 | 900475 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | CCI | 2013 | Q1 | Q1 - 2013 | 3706362 | 1111909 | 2594453 | 3219440 | 1407396 | 1812044 | 3247658 | 1415862 | 1831796 | 9349257 | 2804777 | 6544480 | 8893387 | 2331449 | 6561938 | 9283182 | 2443972 | 6839210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604700 | 181410 | 423290 | 122216 | 34658 | 87558 | 122216 | 34658 | 87558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366720 | 410016 | 956704 | 1327104 | 421376 | 905727 | 1428503 | 451796 | 976707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125718 | 37715 | 88003 | 129641 | 38892 | 90749 | 200641 | 60192 | 140449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344195 | 403259 | 940936 | 1884812 | 443624 | 1441188 | 1884812 | 443624 | 1441188 | 16496952 | 4949086 | 11547866 | 15576600 | 4677395 | 10899204 | 16167012 | 4850104 | 11316908 | 16496952 | 4949086 | 11547866 | 15576600 | 4677395 | 10899204 | 16167012 | 4850104 | 11316908 | 0 | 1069632 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | CCI | 2013 | Q2 | Q2 - 2013 | 3247659 | 974298 | 2273361 | 3229553 | 1410430 | 1819123 | 3229553 | 1410430 | 1819123 | 9613119 | 2883936 | 6729183 | 9216523 | 2428390 | 6788133 | 9631235 | 2552804 | 7078431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122215 | 36664 | 85551 | 122216 | 34658 | 87558 | 122216 | 34658 | 87558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1428504 | 428551 | 999953 | 1377339 | 436446 | 940893 | 1428503 | 449603 | 978900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200642 | 60193 | 140449 | 133581 | 40074 | 93507 | 200633 | 57967 | 142666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1884813 | 565444 | 1319369 | 1884812 | 443624 | 1441188 | 1884812 | 443624 | 1441188 | 16496952 | 4949086 | 11547866 | 15964024 | 4793622 | 11170402 | 16496952 | 4949086 | 11547866 | 16496952 | 4949086 | 11547866 | 15964024 | 4793622 | 11170402 | 16496952 | 4949086 | 11547866 | 0 | 999532 | Nebraskalink, LLC | TRUE
NT10BIX5570112 | CCI | 2013 | Q3 | Q3 - 2013 | 3247659 | 974298 | 2273361 | 3229553 | 1410430 | 1819123 | 3229553 | 1410430 | 1819123 | 9613119 | 2883936 | 6729183 | 9639161 | 2560730 | 7078431 | 9639161 | 2560730 | 7078431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122215 | 36664 | 85551 | 122216 | 34658 | 87558 | 122216 | 34658 | 87558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1428504 | 428551 | 999953 | 1413684 | 439991 | 973693 | 1413684 | 439991 | 973693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200642 | 60193 | 140449 | 207525 | 59653 | 147872 | 207525 | 59653 | 147872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1884813 | 565444 | 1319369 | 1884813 | 443624 | 1441189 | 1884813 | 443624 | 1441189 | 16496952 | 4949086 | 11547866 | 16496952 | 4949086 | 11547866 | 16496952 | 4949086 | 11547866 | 16496952 | 4949086 | 11547866 | 16496952 | 4949086 | 11547866 | 16496952 | 4949086 | 11547866 | 0 | 908224 | Nebraskalink, LLC | TRUE
NT10BIX5570113 | CCI | 2010 | Q4 | Q4 - 2010 | 27996536 | 8850000 | 19146536 | 0 | 0 | 0 | 0 | 0 | 0 | 52600000 | 0 | 52600000 | 0 | 0 | 0 | 526000 | 0 | 526000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5872500 | 4522500 | 1350000 | 0 | 0 | 0 | 147131 | 147131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 0 | 0 | 0 | 29869 | 29869 | 0 | 600000 | 0 | 600000 | 0 | 0 | 0 | 324000 | 0 | 324000 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 0 | 0 | 0 | 58000 | 40000 | 18000 | 92907816 | 18909548 | 73998268 | 0 | 0 | 0 | 1085000 | 217000 | 868000 | 92907816 | 18909548 | 73998268 | 0 | 0 | 0 | 1085000 | 217000 | 868000 | 22877800 | 0 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | CCI | 2011 | Q1 | Q1 - 2011 | 27996536 | 8850000 | 19146536 | 0 | 0 | 0 | 0 | 0 | 0 | 52600000 | 0 | 52600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5872500 | 4522500 | 1350000 | 0 | 0 | 0 | 108053 | 108053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 29869 | 29869 | 0 | 382069 | 382069 | 8512 | 600000 | 0 | 600000 | 0 | 0 | 0 | 324000 | 0 | 324000 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 251343 | 251343 | 0 | 352021 | 352021 | 0 | 92907816 | 18909548 | 73998268 | 281212 | 281212 | 0 | 1166143 | 842143 | 332512 | 92907816 | 18909548 | 73998268 | 281212 | 281212 | 0 | 1166143 | 842143 | 332512 | 22877800 | 0 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | CCI | 2011 | Q2 | Q2 - 2011 | 27996536 | 8850000 | 19146536 | 5003792 | 5003792 | 0 | 5003792 | 5003792 | 0 | 52600000 | 0 | 52600000 | 0 | 0 | 0 | 1052000 | 0 | 1052000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5872500 | 4522500 | 1350000 | 0 | 0 | 0 | 117450 | 90450 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 501545 | 501545 | 0 | 881545 | 881545 | 0 | 600000 | 0 | 600000 | 0 | 0 | 0 | 486000 | 0 | 486000 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 311198 | 311198 | 0 | 347000 | 347000 | 0 | 92907816 | 18909548 | 73998268 | 5816535 | 5816535 | 0 | 7887787 | 6322787 | 1565000 | 92907816 | 18909548 | 73998268 | 5816535 | 5816535 | 0 | 7887787 | 6322787 | 1565000 | 22877800 | 0 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | CCI | 2011 | Q3 | Q3 - 2011 | 27996536 | 8850000 | 19146536 | 8850000 | 8850000 | 0 | 13850000 | 8850000 | 5000000 | 50109380 | 0 | 50109380 | 0 | 0 | 0 | 6630000 | 0 | 6630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8363120 | 4522500 | 3840620 | 4522500 | 4522500 | 0 | 5482655 | 4522500 | 960155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 929468 | 929468 | 0 | 1493438 | 1493438 | 0 | 600000 | 0 | 600000 | 27635 | 0 | 27635 | 100000 | 0 | 100000 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 343054 | 343054 | 0 | 375000 | 375000 | 0 | 92907816 | 18909548 | 73998268 | 14672657 | 14645022 | 27635 | 27931093 | 15240938 | 12690155 | 92907816 | 18909548 | 73998268 | 14672657 | 14645022 | 27635 | 27931093 | 15240938 | 12690155 | 22877800 | 0 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | CCI | 2011 | Q4 | Q4 - 2011 | 27996536 | 8850000 | 19146536 | 8850000 | 8850000 | 0 | 13850000 | 8850000 | 5000000 | 50109380 | 0 | 50109380 | 0 | 0 | 0 | 7111500 | 0 | 7111500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8363120 | 4522500 | 3840620 | 4522500 | 4522500 | 0 | 6442810 | 4522500 | 1920310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 2004858 | 2004858 | 0 | 2291438 | 2007706 | 283732 | 600000 | 0 | 600000 | 27635 | 0 | 27635 | 55000 | 0 | 55000 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 384579 | 384579 | 0 | 426000 | 426000 | 0 | 92907816 | 18909548 | 73998268 | 15789572 | 15761937 | 27635 | 30176748 | 15806206 | 14370542 | 92907816 | 18909548 | 73998268 | 15789572 | 15761937 | 27635 | 30176748 | 15806206 | 14370542 | 22877800 | 0 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | CCI | 2012 | Q1 | Q1 - 2012 | 28860022 | 8850000 | 20010022 | 11280161 | 8850000 | 2430161 | 18448554 | 8850000 | 9598554 | 48945894 | 0 | 48945894 | 0 | 0 | 0 | 24279993 | 0 | 24279993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663120 | 4522500 | 4140620 | 5527295 | 4522500 | 1004795 | 8663120 | 4522500 | 4140620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 4817836 | 4817836 | 0 | 5101568 | 4817836 | 283732 | 600000 | 0 | 600000 | 27635 | 0 | 27635 | 62270 | 0 | 62270 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 1917404 | 1917404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 423653 | 423653 | 0 | 480727 | 462727 | 18000 | 92907816 | 18909548 | 73998268 | 22076580 | 18613989 | 3462591 | 58953636 | 20570467 | 38383169 | 92907816 | 18909548 | 73998268 | 22076580 | 18613989 | 3462591 | 58953636 | 20570467 | 38383169 | 0 | 0 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | CCI | 2012 | Q2 | Q2 - 2012 | 28860022 | 8850000 | 20010022 | 13840540 | 8850000 | 4990540 | 24627734 | 8850000 | 15777734 | 48945894 | 0 | 48945894 | 18974225 | 0 | 18974225 | 44407233 | 0 | 44407233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663120 | 4522500 | 4140620 | 8131479 | 4522500 | 3608979 | 8663120 | 4522500 | 4140620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 4817836 | 4817836 | 0 | 5101568 | 4817836 | 283732 | 600000 | 0 | 600000 | 47435 | 0 | 47435 | 49435 | 0 | 49435 | 3834807 | 3834807 | 0 | 1159171 | 1159171 | 0 | 3067845 | 3067845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 460548 | 460548 | 0 | 515351 | 497351 | 18000 | 92907816 | 18909548 | 73998268 | 47431234 | 19810055 | 27621179 | 86432286 | 21755532 | 64676754 | 92907816 | 18909548 | 73998268 | 47431234 | 19810055 | 27621179 | 86432286 | 21755532 | 64676754 | 0 | 0 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | CCI | 2012 | Q3 | Q3 - 2012 | 28860022 | 8850000 | 20010022 | 23887755 | 8850000 | 15037755 | 26789340 | 8850000 | 17939340 | 48945894 | 0 | 48945894 | 35344776 | 0 | 35344776 | 45459304 | 0 | 45459304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663120 | 4522500 | 4140620 | 8218666 | 4522500 | 3696166 | 8322603 | 4522500 | 3800103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 5101568 | 4817836 | 283732 | 5101568 | 4817836 | 283732 | 600000 | 0 | 600000 | 49435 | 0 | 49435 | 49435 | 0 | 49435 | 3834807 | 3834807 | 0 | 2092090 | 2092090 | 0 | 3758111 | 3758111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 544732 | 528547 | 16185 | 625020 | 607829 | 17191 | 92907816 | 18909548 | 73998268 | 75239022 | 20810973 | 54428049 | 90105381 | 22556276 | 67549105 | 92907816 | 18909548 | 73998268 | 75239022 | 20810973 | 54428049 | 90105381 | 22556276 | 67549105 | 0 | 0 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | CCI | 2012 | Q4 | Q4 - 2012 | 28860022 | 8850000 | 20010022 | 23914705 | 8850000 | 15064705 | 27360022 | 8850000 | 18510022 | 48945894 | 0 | 48945894 | 40477220 | 0 | 40477220 | 45459304 | 0 | 45459304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663120 | 4522500 | 4140620 | 8222873 | 4522500 | 3700373 | 8322603 | 4522500 | 3800103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 5101568 | 4817836 | 283732 | 5101568 | 4817836 | 283732 | 600000 | 0 | 600000 | 49435 | 0 | 49435 | 49435 | 0 | 49435 | 3834807 | 3834807 | 0 | 3356541 | 3356541 | 0 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 741653 | 724462 | 17191 | 850322 | 833131 | 17191 | 92907816 | 18909548 | 73998268 | 81863995 | 22271339 | 59592656 | 90978061 | 22858274 | 68119787 | 92907816 | 18909548 | 73998268 | 81863995 | 22271339 | 59592656 | 90978061 | 22858274 | 68119787 | 0 | 0 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | CCI | 2013 | Q1 | Q1 - 2013 | 28860022 | 8850000 | 20010022 | 24843181 | 8850000 | 15993181 | 28860022 | 8850000 | 20010022 | 48945894 | 0 | 48945894 | 40885120 | 0 | 40885120 | 48945894 | 0 | 48945894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663120 | 4522500 | 4140620 | 8256228 | 4522500 | 3733728 | 8663120 | 4522500 | 4140620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 4052075 | 3768343 | 283732 | 4052075 | 3216969 | 835106 | 600000 | 0 | 600000 | 49435 | 0 | 49435 | 49435 | 0 | 49435 | 3834807 | 3834807 | 0 | 2833455 | 2833455 | 0 | 3834807 | 3834807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 828816 | 811625 | 17191 | 950560 | 933369 | 17191 | 92907816 | 18909548 | 73998268 | 81748310 | 20785923 | 60962387 | 95355913 | 21357645 | 73998268 | 92907816 | 18909548 | 73998268 | 81748310 | 20785923 | 60962387 | 95355913 | 21357645 | 73998268 | 0 | 0 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | CCI | 2013 | Q2 | Q2 - 2013 | 28860022 | 8850000 | 20010022 | 24843181 | 8850000 | 15993181 | 29819683 | 8850000 | 20969683 | 48945894 | 0 | 48945894 | 41758670 | 0 | 41758670 | 46598524 | 0 | 46598524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663120 | 4522500 | 4140620 | 8262553 | 4522500 | 3740053 | 8566508 | 4522500 | 4044008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 4140895 | 3857163 | 283732 | 4346956 | 2328245 | 2018711 | 600000 | 0 | 600000 | 49435 | 0 | 49435 | 49435 | 0 | 49435 | 3834807 | 3834807 | 0 | 2942750 | 2942750 | 0 | 3000000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 871799 | 854608 | 17191 | 899493 | 581586 | 317907 | 92907816 | 18909548 | 73998268 | 82869283 | 21027021 | 61842262 | 93280599 | 19282331 | 73998268 | 92907816 | 18909548 | 73998268 | 82869283 | 21027021 | 61842262 | 93280599 | 19282331 | 73998268 | 0 | 0 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570113 | CCI | 2013 | Q3 | Q3 - 2013 | 28860022 | 8850000 | 20010022 | 29798898 | 8850000 | 20948898 | 29798898 | 8850000 | 20948898 | 48945894 | 0 | 48945894 | 44845316 | 0 | 44845316 | 44845316 | 0 | 44845316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8663120 | 4522500 | 4140620 | 8603750 | 4522500 | 4081250 | 8603750 | 4522500 | 4081250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1777170 | 1493438 | 283732 | 3857163 | 2349855 | 1507308 | 3857163 | 2349855 | 1507308 | 600000 | 0 | 600000 | 49435 | 0 | 49435 | 49435 | 0 | 49435 | 3834807 | 3834807 | 0 | 2978390 | 2978390 | 0 | 2978390 | 2978390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226803 | 208803 | 18000 | 1338840 | 564566 | 774274 | 1338840 | 564566 | 774274 | 92907816 | 18909548 | 73998268 | 91471792 | 19265311 | 72206481 | 91471792 | 19265311 | 72206481 | 92907816 | 18909548 | 73998268 | 91471792 | 19265311 | 72206481 | 91471792 | 19265311 | 72206481 | 0 | 0 | Finance, Oklahoma Office of State | TRUE
NT10BIX5570114 | CCI | 2010 | Q4 | Q4 - 2010 | 28244599 | 5648920 | 22595679 | 0 | 0 | 0 | 0 | 0 | 0 | 51151342 | 10230268 | 40921074 | 1400 | 280 | 1120 | 511913 | 409531 | 102383 | 621845 | 124369 | 497476 | 33415 | 6683 | 26732 | 64835 | 51868 | 12967 | 1116000 | 223200 | 892800 | 0 | 0 | 0 | 12000 | 9600 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 62550 | 12510 | 50040 | 1066871 | 853497 | 213374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 0 | 0 | 0 | 723009 | 144602 | 578407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 87691 | 17538 | 70152 | 112691 | 90153 | 22538 | 87049114 | 17409823 | 69639291 | 185056 | 37011 | 148044 | 1768310 | 1414649 | 353662 | 87049114 | 17409823 | 69639291 | 185056 | 37011 | 148044 | 1768310 | 1414649 | 353662 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570114 | CCI | 2011 | Q1 | Q1 - 2011 | 28244599 | 5648920 | 22595679 | 0 | 0 | 0 | 0 | 0 | 0 | 51151342 | 10230268 | 40921074 | 529 | 106 | 423 | 1784704 | 356941 | 1427764 | 621845 | 124369 | 497476 | 68140 | 13628 | 54512 | 102211 | 20442 | 81768 | 1116000 | 223200 | 892800 | 12501 | 2500 | 10000 | 21690 | 4338 | 17352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 202896 | 40579 | 162317 | 693731 | 138746 | 554985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 0 | 0 | 0 | 723009 | 144602 | 578407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31679 | 126717 | 246879 | 49376 | 197504 | 341833 | 68367 | 273466 | 86890718 | 17409823 | 69639291 | 530945 | 106189 | 424756 | 2944169 | 588834 | 2355335 | 86890718 | 17409823 | 69639291 | 530945 | 106189 | 424756 | 2944169 | 588834 | 2355335 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570114 | CCI | 2011 | Q2 | Q2 - 2011 | 28244599 | 5648920 | 22595679 | 0 | 0 | 0 | 1412230 | 282446 | 1129784 | 51151342 | 10230268 | 40921074 | 62303 | 12461 | 49843 | 2619870 | 523974 | 2095896 | 621845 | 124369 | 497476 | 109009 | 21802 | 87207 | 173113 | 34623 | 138791 | 1116000 | 223200 | 892800 | 9000 | 1800 | 7200 | 9000 | 1800 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 581611 | 116322 | 465289 | 1122880 | 224576 | 898304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 0 | 0 | 0 | 723009 | 144602 | 578407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 289836 | 57967 | 231868 | 242225 | 48445 | 193780 | 87049114 | 17409823 | 69639291 | 1051759 | 210352 | 841407 | 5579318 | 1115864 | 4463755 | 87049114 | 17409823 | 69639291 | 1051759 | 210352 | 841407 | 5579318 | 1115864 | 4463755 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570114 | CCI | 2011 | Q3 | Q3 - 2011 | 28244599 | 5648920 | 22595679 | 0 | 0 | 0 | 1605711 | 321142 | 1284569 | 51151342 | 10230268 | 40921074 | 219126 | 43825 | 175301 | 17203373 | 3440675 | 13762698 | 621845 | 124369 | 497476 | 150325 | 30065 | 120260 | 241846 | 48369 | 193477 | 1116000 | 223200 | 892800 | 9000 | 1800 | 7200 | 25133 | 5027 | 20106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 1278093 | 255619 | 1022474 | 1628698 | 325740 | 1302958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 0 | 0 | 0 | 723009 | 144602 | 578407 | 0 | 0 | 0 | 5601 | 1120 | 4481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 374546 | 74909 | 299637 | 354340 | 70868 | 283472 | 87049114 | 17409823 | 69639291 | 2031090 | 406218 | 1624872 | 21064702 | 4212941 | 16851761 | 87049114 | 17409823 | 69639291 | 2031090 | 406218 | 1624872 | 21064702 | 4212941 | 16851761 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570114 | CCI | 2011 | Q4 | Q4 - 2011 | 28244599 | 5648920 | 22595679 | 768041 | 153608 | 614433 | 6285648 | 1257130 | 5028518 | 51151342 | 10230268 | 40921074 | 4227478 | 845496 | 3381982 | 13951704 | 2790341 | 11161363 | 621845 | 124369 | 497476 | 153607 | 30721 | 122886 | 261063 | 52213 | 208850 | 1116000 | 223200 | 892800 | 30272 | 6054 | 24218 | 30272 | 6054 | 24218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 1861558 | 372312 | 1489246 | 1949940 | 389988 | 1559952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 0 | 0 | 0 | 723009 | 144602 | 578407 | 0 | 0 | 0 | 4567 | 913 | 3654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 394949 | 78990 | 315959 | 522737 | 104547 | 418189 | 87049114 | 17409823 | 69639291 | 7435905 | 1487181 | 5948724 | 23005931 | 4601186 | 18404744 | 87049114 | 17409823 | 69639291 | 7435905 | 1487181 | 5948724 | 23005931 | 4601186 | 18404744 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570114 | CCI | 2012 | Q1 | Q1 - 2012 | 28244599 | 5648920 | 22595679 | 826001 | 165200 | 660801 | 6333412 | 1266682 | 5066729 | 51151342 | 10230268 | 40921074 | 9624082 | 1924817 | 7699265 | 18303829 | 3660766 | 14643063 | 621845 | 124369 | 497476 | 170389 | 34078 | 136311 | 455756 | 91151 | 364605 | 1116000 | 223200 | 892800 | 31410 | 6282 | 25128 | 174191 | 34838 | 139353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 2238211 | 447642 | 1790569 | 2240912 | 448182 | 1792729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 0 | 0 | 0 | 723009 | 144602 | 578407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 407177 | 81435 | 325742 | 1292882 | 258576 | 1034306 | 87049114 | 17409823 | 69639291 | 13297270 | 2659454 | 10637816 | 28800982 | 5760195 | 23040785 | 87049114 | 17409823 | 69639291 | 13297270 | 2659454 | 10637816 | 28800982 | 5760195 | 23040785 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570114 | CCI | 2012 | Q2 | Q2 - 2012 | 28244599 | 5648920 | 22595679 | 1362844 | 272569 | 1090275 | 8117094 | 1623419 | 6493675 | 51151342 | 10230268 | 40921074 | 16086586 | 3217317 | 12869269 | 24939975 | 4987995 | 19951980 | 621845 | 124369 | 497476 | 173948 | 34790 | 139158 | 335745 | 67149 | 268596 | 1116000 | 223200 | 892800 | 82111 | 16422 | 65689 | 636140 | 127228 | 508912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 2757138 | 551428 | 2205710 | 2966921 | 593384 | 2373537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 0 | 0 | 0 | 723009 | 144602 | 578407 | 0 | 0 | 0 | 5682 | 1136 | 4546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 498977 | 99795 | 399182 | 559574 | 111915 | 447659 | 87049114 | 17409823 | 69639291 | 20961604 | 4192321 | 16769283 | 37561131 | 7512226 | 30048905 | 87049114 | 17409823 | 69639291 | 20961604 | 4192321 | 16769283 | 37561131 | 7512226 | 30048905 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570114 | CCI | 2012 | Q3 | Q3 - 2012 | 28244599 | 5648920 | 22595679 | 2197701 | 439540 | 1758161 | 10919411 | 2183882 | 8735528 | 51151342 | 10230268 | 40921074 | 24928290 | 4985658 | 19942632 | 33571501 | 6714300 | 26857201 | 621845 | 124369 | 497476 | 173948 | 34790 | 139158 | 399626 | 79925 | 319701 | 1116000 | 223200 | 892800 | 82111 | 16422 | 65689 | 718959 | 143792 | 575167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 3449620 | 689924 | 2759696 | 3692021 | 738404 | 2953617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 7540 | 1508 | 6032 | 723009 | 144602 | 578407 | 11226 | 2245 | 8981 | 319824 | 63965 | 255859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 599523 | 119905 | 479618 | 666043 | 133209 | 532835 | 87049114 | 17409823 | 69639291 | 31442419 | 6288484 | 25153935 | 50294925 | 10058985 | 40235940 | 87049114 | 17409823 | 69639291 | 31442419 | 6288484 | 25153935 | 50294925 | 10058985 | 40235940 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570114 | CCI | 2012 | Q4 | Q4 - 2012 | 28244599 | 5648920 | 22595679 | 5003147 | 1000629 | 4002518 | 16674482 | 3334896 | 13339585 | 51151342 | 10230268 | 40921074 | 33302710 | 6660542 | 26642168 | 42381304 | 8476261 | 33905043 | 621845 | 124369 | 497476 | 221643 | 44329 | 177315 | 492520 | 98504 | 394016 | 1116000 | 223200 | 892800 | 276614 | 55323 | 221291 | 890181 | 178036 | 712145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 4221816 | 844363 | 3377452 | 4853427 | 970685 | 3882742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 11257 | 2251 | 9005 | 723009 | 144602 | 578407 | 11226 | 2245 | 8981 | 420620 | 84124 | 336496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 621003 | 124201 | 496802 | 820865 | 164174 | 656691 | 87049114 | 17409823 | 69639291 | 43658159 | 8731632 | 34926527 | 66544656 | 13308931 | 53235723 | 87049114 | 17409823 | 69639291 | 43658159 | 8731632 | 34926527 | 66544656 | 13308931 | 53235723 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570114 | CCI | 2013 | Q1 | Q1 - 2013 | 28244599 | 5648920 | 22595679 | 5753967 | 1150793 | 4603174 | 17049892 | 3409978 | 13639913 | 51151342 | 10230268 | 40921074 | 38764957 | 7752991 | 31011966 | 45107670 | 9021534 | 36086136 | 621845 | 124369 | 497476 | 219432 | 43886 | 175546 | 494425 | 98885 | 395540 | 1116000 | 223200 | 892800 | 276794 | 55359 | 221435 | 903219 | 180644 | 722575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 4719351 | 943870 | 3775481 | 5385788 | 1077158 | 4308631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 0 | 0 | 0 | 11257 | 2251 | 9005 | 723009 | 144602 | 578407 | 38578 | 7716 | 30863 | 434297 | 86859 | 347437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 635915 | 127184 | 508730 | 824043 | 164809 | 659234 | 87049114 | 17409823 | 69639291 | 50408994 | 10081799 | 40327195 | 70210591 | 14042118 | 56168471 | 87049114 | 17409823 | 69639291 | 50408994 | 10081799 | 40327195 | 70210591 | 14042118 | 56168471 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570114 | CCI | 2013 | Q2 | Q2 - 2013 | 28244599 | 5648920 | 22595679 | 6764508 | 1352902 | 5411606 | 11090978 | 2218196 | 8872782 | 51151342 | 10230268 | 40921074 | 48747244 | 9749449 | 38997795 | 55229862 | 11045972 | 44183890 | 621845 | 124369 | 497476 | 224795 | 44959 | 179836 | 243464 | 48693 | 194771 | 1116000 | 223200 | 892800 | 300780 | 60156 | 240624 | 1018818 | 203764 | 815055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 5289847 | 1057969 | 4231878 | 5913777 | 1182755 | 4731021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 1780 | 356 | 1424 | 4567 | 913 | 3654 | 723009 | 144602 | 578407 | 46761 | 9352 | 37409 | 267615 | 53523 | 214092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 680276 | 136055 | 544221 | 730393 | 146079 | 584314 | 87049114 | 17409823 | 69639291 | 62055991 | 12411198 | 49644793 | 74499474 | 14899895 | 59599579 | 87049114 | 17409823 | 69639291 | 62055991 | 12411198 | 49644793 | 74499474 | 14899895 | 59599579 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570114 | CCI | 2013 | Q3 | Q3 - 2013 | 28244599 | 5648920 | 22595679 | 10928246 | 2185649 | 8742597 | 10945260 | 2189052 | 8756208 | 51151342 | 10230268 | 40921074 | 58455899 | 11691180 | 46764719 | 66985690 | 13397138 | 53588552 | 621845 | 124369 | 497476 | 228844 | 45769 | 183075 | 289971 | 57994 | 231977 | 1116000 | 223200 | 892800 | 403689 | 80738 | 322951 | 1314318 | 262864 | 1051454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 5726327 | 1145265 | 4581062 | 6423027 | 1284605 | 5138422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 12227 | 2445 | 9782 | 13721 | 2744 | 10977 | 723009 | 144602 | 578407 | 52390 | 10478 | 41912 | 207215 | 41443 | 165772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 844380 | 168877 | 675503 | 869912 | 173982 | 695930 | 87049114 | 17409823 | 69639291 | 76652002 | 15330401 | 61321601 | 87049114 | 17409822 | 69639292 | 87049114 | 17409823 | 69639291 | 76652002 | 15330401 | 61321601 | 87049114 | 17409822 | 69639292 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570114 | CCI | 2013 | Q4 | Q4 - 2013 | 28244599 | 5648920 | 22595679 | 11089300 | 2217860 | 8871440 | 11106830 | 2221366 | 8885464 | 51151342 | 10230268 | 40921074 | 64147491 | 12829498 | 51317993 | 66313852 | 13262770 | 53051082 | 621845 | 124369 | 497476 | 232724 | 46545 | 186179 | 259741 | 51948 | 207793 | 1116000 | 223200 | 892800 | 408928 | 81786 | 327142 | 900504 | 180101 | 720403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4301298 | 860260 | 3441038 | 6268229 | 1253646 | 5014583 | 7173292 | 1434658 | 5738634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732625 | 146525 | 586100 | 29159 | 5832 | 23327 | 104808 | 20962 | 83846 | 723009 | 144602 | 578407 | 65714 | 13143 | 52571 | 210864 | 42173 | 168691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158396 | 31679 | 126717 | 941498 | 188299 | 753199 | 979223 | 195845 | 783378 | 87049114 | 17409823 | 69639291 | 83183043 | 16636609 | 66546434 | 87049114 | 17409823 | 69639291 | 87049114 | 17409823 | 69639291 | 83183043 | 16636609 | 66546434 | 87049114 | 17409823 | 69639291 | 0 | 0 | Merit Network Inc. | TRUE
NT10BIX5570115 | CCI | 2010 | Q4 | Q4 - 2010 | 6553615 | 1966084 | 4587531 | 0 | 0 | 0 | 454350 | 107394 | 346956 | 28819806 | 8669749 | 20150057 | 0 | 0 | 0 | 36391 | 8602 | 27789 | 1660444 | 498133 | 1162311 | 0 | 0 | 0 | 322293 | 109613 | 212680 | 3805578 | 1141673 | 2663905 | 0 | 0 | 0 | 247444 | 58488 | 188956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 0 | 0 | 0 | 362389 | 97453 | 264936 | 7500 | 2250 | 5250 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 0 | 0 | 0 | 27339 | 27339 | 0 | 42726744 | 12841830 | 29884914 | 0 | 0 | 0 | 1457706 | 416389 | 1041317 | 42726744 | 12841830 | 29884914 | 0 | 0 | 0 | 1457706 | 416389 | 1041317 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570115 | CCI | 2011 | Q1 | Q1 - 2011 | 6553615 | 1966084 | 4587531 | 0 | 0 | 0 | 536416 | 126792 | 409624 | 28819806 | 8669749 | 20150057 | 0 | 0 | 0 | 5570206 | 1495209 | 4074997 | 1660444 | 498133 | 1162311 | 112065 | 0 | 77837 | 477710 | 146349 | 331361 | 3805578 | 1141673 | 2663905 | 0 | 0 | 0 | 472328 | 138372 | 333956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 122526 | 0 | 122526 | 543096 | 140166 | 402930 | 7500 | 2250 | 5250 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 0 | 34228 | 0 | 41589 | 30707 | 10882 | 42726744 | 12841830 | 29884914 | 234591 | 34228 | 200363 | 7648845 | 2085095 | 5563750 | 42726744 | 12841830 | 29884914 | 234591 | 34228 | 200363 | 7648845 | 2085095 | 5563750 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570115 | CCI | 2011 | Q2 | Q2 - 2011 | 6553615 | 1966084 | 4587531 | 0 | 0 | 0 | 300000 | 0 | 300000 | 28819806 | 8669749 | 20150057 | 1027237 | 333288 | 693949 | 10458838 | 2301718 | 8157120 | 1660444 | 498133 | 1162311 | 203772 | 74367 | 129405 | 389607 | 74367 | 315240 | 3805578 | 1141673 | 2663905 | 0 | 0 | 0 | 1651469 | 1509000 | 142469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 233670 | 45424 | 188246 | 397498 | 45424 | 352074 | 7500 | 2250 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 33658 | 33658 | 0 | 33658 | 33658 | 0 | 42726744 | 12841830 | 29884914 | 1498337 | 486737 | 1011600 | 13231070 | 3964167 | 9266903 | 42726744 | 12841830 | 29884914 | 1498337 | 486737 | 1011600 | 13231070 | 3964167 | 9266903 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570115 | CCI | 2011 | Q3 | Q3 - 2011 | 6553615 | 1966084 | 4587531 | 0 | 0 | 0 | 2000000 | 0 | 2000000 | 28819806 | 8669749 | 20150057 | 5216483 | 825500 | 4390983 | 14252769 | 4332568 | 9920201 | 1660444 | 498133 | 1162311 | 394740 | 74367 | 320373 | 472440 | 74367 | 398073 | 3805578 | 1141673 | 2663905 | 1639772 | 1509000 | 130772 | 1639772 | 1509000 | 130772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 481542 | 60871 | 420671 | 1638524 | 60871 | 1577653 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 33658 | 33658 | 0 | 33658 | 33658 | 0 | 42726744 | 12841830 | 29884914 | 7773695 | 2510896 | 5262799 | 20044663 | 6017964 | 14026699 | 42726744 | 12841830 | 29884914 | 7773695 | 2510896 | 5262799 | 20044663 | 6017964 | 14026699 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570115 | CCI | 2011 | Q4 | Q4 - 2011 | 6553615 | 1966084 | 4587531 | 2828637 | 250000 | 2578637 | 3016219 | 250000 | 2766219 | 28819806 | 8669749 | 20150057 | 12198281 | 3293037 | 8905244 | 13165220 | 3815911 | 9349309 | 1660444 | 498133 | 1162311 | 508024 | 74368 | 433656 | 568438 | 74367 | 494071 | 3805578 | 1141673 | 2663905 | 1724379 | 1509000 | 215379 | 1748172 | 1509000 | 239172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 537394 | 60871 | 476523 | 560592 | 60871 | 499721 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 33658 | 33658 | 0 | 33658 | 33658 | 0 | 42726744 | 12841830 | 29884914 | 17837873 | 5228434 | 12609439 | 19099799 | 5751307 | 13348492 | 42726744 | 12841830 | 29884914 | 17837873 | 5228434 | 12609439 | 19099799 | 5751307 | 13348492 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570115 | CCI | 2012 | Q1 | Q1 - 2012 | 6553615 | 1966084 | 4587531 | 3021876 | 250000 | 2771876 | 4472408 | 700000 | 3772408 | 28819806 | 8669749 | 20150057 | 14415670 | 4185998 | 10229672 | 15898076 | 4674265 | 11223811 | 1660444 | 498133 | 1162311 | 632675 | 74367 | 558308 | 699212 | 74367 | 624845 | 3805578 | 1141673 | 2663905 | 1751919 | 1509000 | 242919 | 1751919 | 1509000 | 242919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 559084 | 60871 | 498213 | 591249 | 60871 | 530378 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 33658 | 33658 | 0 | 33658 | 33658 | 0 | 42726744 | 12841830 | 29884914 | 20422382 | 6121394 | 14300988 | 23454022 | 7059661 | 16394361 | 42726744 | 12841830 | 29884914 | 20422382 | 6121394 | 14300988 | 23454022 | 7059661 | 16394361 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570115 | CCI | 2012 | Q2 | Q2 - 2012 | 6553615 | 1966084 | 4587531 | 4316766 | 500000 | 3816766 | 4320078 | 500000 | 3820078 | 28819806 | 8669749 | 20150057 | 16027039 | 4930271 | 11096768 | 17627112 | 5505484 | 12121628 | 1660444 | 498133 | 1162311 | 764921 | 74367 | 690554 | 1006813 | 74367 | 932446 | 3805578 | 1141673 | 2663905 | 1771829 | 1509000 | 262829 | 1793446 | 1509000 | 284446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 727637 | 60871 | 666766 | 769875 | 60871 | 709004 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 33658 | 33658 | 0 | 33658 | 33658 | 0 | 42726744 | 12841830 | 29884914 | 23649350 | 7115667 | 16533683 | 25558482 | 7690880 | 17867602 | 42726744 | 12841830 | 29884914 | 23649350 | 7115667 | 16533683 | 25558482 | 7690880 | 17867602 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570115 | CCI | 2012 | Q3 | Q3 - 2012 | 6553615 | 1966084 | 4587531 | 4480278 | 550000 | 3930278 | 4480278 | 550000 | 3930278 | 28819806 | 8669749 | 20150057 | 17965563 | 5630643 | 12334920 | 22777465 | 7093193 | 15684272 | 1660444 | 498133 | 1162311 | 1054891 | 74367 | 980524 | 1140318 | 74367 | 1065951 | 3805578 | 1141673 | 2663905 | 1796795 | 1509000 | 287795 | 1801195 | 1509000 | 292195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 759604 | 60871 | 698733 | 797153 | 60871 | 736282 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 33658 | 33658 | 0 | 33658 | 33658 | 0 | 42726744 | 12841830 | 29884914 | 26098289 | 7866039 | 18232250 | 31037567 | 9328589 | 21708978 | 42726744 | 12841830 | 29884914 | 26098289 | 7866039 | 18232250 | 31037567 | 9328589 | 21708978 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570115 | CCI | 2012 | Q4 | Q4 - 2012 | 6553615 | 1966084 | 4587531 | 4480278 | 550000 | 3930278 | 4742484 | 550000 | 4192484 | 28819806 | 8669749 | 20150057 | 24572272 | 7787880 | 16784392 | 25872809 | 8241159 | 17631650 | 1660444 | 498133 | 1162311 | 1262279 | 74367 | 1187912 | 1429304 | 74367 | 1354937 | 3805578 | 1141673 | 2663905 | 2185005 | 1509000 | 676005 | 2428995 | 1661000 | 767995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 797272 | 60871 | 736401 | 842705 | 60871 | 781834 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 34006 | 33658 | 348 | 34006 | 33658 | 348 | 42726744 | 12841830 | 29884914 | 33338612 | 10023276 | 23315336 | 35357803 | 10628555 | 24729248 | 42726744 | 12841830 | 29884914 | 33338612 | 10023276 | 23315336 | 35357803 | 10628555 | 24729248 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570115 | CCI | 2013 | Q1 | Q1 - 2013 | 6553615 | 1966084 | 4587531 | 5094935 | 550000 | 4544935 | 5594935 | 550000 | 5044935 | 28819806 | 8669749 | 20150057 | 25584290 | 8299263 | 17285027 | 27794405 | 9059263 | 18735142 | 1660444 | 498133 | 1162311 | 1479067 | 74368 | 1404699 | 1581567 | 74368 | 1507199 | 3805578 | 1141673 | 2663905 | 3015448 | 1814000 | 1201448 | 3515448 | 2064000 | 1451448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 841657 | 60871 | 780786 | 886657 | 60871 | 825786 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 34006 | 33658 | 348 | 34006 | 33658 | 348 | 42726744 | 12841830 | 29884914 | 36056903 | 10839660 | 25217243 | 39414518 | 11849660 | 27564858 | 42726744 | 12841830 | 29884914 | 36056903 | 10839660 | 25217243 | 39414518 | 11849660 | 27564858 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570115 | CCI | 2013 | Q2 | Q2 - 2013 | 6553615 | 1966084 | 4587531 | 5817896 | 550000 | 5267896 | 6258680 | 550000 | 5708680 | 28819806 | 8669749 | 20150057 | 27572145 | 9145622 | 18426523 | 30473165 | 10181433 | 20291732 | 1660444 | 498133 | 1162311 | 1643549 | 74368 | 1569181 | 1728291 | 74368 | 1653923 | 3805578 | 1141673 | 2663905 | 3315817 | 1934000 | 1381817 | 3317567 | 1934000 | 1383567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 881535 | 60871 | 820664 | 907535 | 60871 | 846664 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 34006 | 33658 | 348 | 34006 | 33658 | 348 | 42726744 | 12841830 | 29884914 | 39272448 | 11806019 | 27466429 | 42726744 | 12841830 | 29884914 | 42726744 | 12841830 | 29884914 | 39272448 | 11806019 | 27466429 | 42726744 | 12841830 | 29884914 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570115 | CCI | 2013 | Q3 | Q3 - 2013 | 6553615 | 1966084 | 4587531 | 6584360 | 655000 | 5929360 | 6584360 | 655000 | 5929360 | 28819806 | 8669749 | 20150057 | 29875825 | 10076433 | 19799392 | 29875825 | 10076433 | 19799392 | 1660444 | 498133 | 1162311 | 1901432 | 74368 | 1827064 | 1901432 | 74368 | 1827064 | 3805578 | 1141673 | 2663905 | 3412400 | 1934000 | 1478400 | 3412400 | 1934000 | 1478400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1791619 | 537486 | 1254133 | 911221 | 60871 | 850350 | 911221 | 60871 | 850350 | 7500 | 2250 | 5250 | 7500 | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88182 | 26455 | 61727 | 34006 | 33658 | 348 | 34006 | 33658 | 348 | 42726744 | 12841830 | 29884914 | 42726744 | 12841830 | 29884914 | 42726744 | 12841830 | 29884914 | 42726744 | 12841830 | 29884914 | 42726744 | 12841830 | 29884914 | 42726744 | 12841830 | 29884914 | 0 | 0 | University of Wisconsin System | TRUE
NT10BIX5570116 | CCI | 2010 | Q4 | Q4 - 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 2277755 | 8517228 | 0 | 0 | 0 | 500000 | 0 | 394500 | 150000 | 31664 | 118336 | 14763 | 3115 | 11648 | 34763 | 7335 | 27428 | 867400 | 183036 | 684364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 96940 | 20454 | 76485 | 694889 | 104854 | 548267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 111703 | 23569 | 88133 | 1229652 | 112189 | 970195 | 13391443 | 2825651 | 10565792 | 111703 | 23569 | 88133 | 1229652 | 112189 | 970195 | 0 | 0 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | CCI | 2011 | Q1 | Q1 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 2277755 | 8517228 | 0 | 0 | 0 | 373500 | 0 | 373500 | 150000 | 31664 | 118336 | 30567 | 6450 | 24117 | 45852 | 9675 | 36177 | 867400 | 183036 | 684364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 417633 | 88122 | 329511 | 824360 | 173943 | 650417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 448200 | 94572 | 353628 | 1243712 | 183618 | 1060094 | 13391443 | 2825651 | 10565792 | 448200 | 94572 | 353628 | 1243712 | 183618 | 1060094 | 0 | 0 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | CCI | 2011 | Q2 | Q2 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 2277755 | 8517228 | 111000 | 23421 | 87579 | 3886194 | 819987 | 3066207 | 150000 | 31664 | 118336 | 49036 | 10347 | 38689 | 59809 | 12620 | 47189 | 867400 | 183036 | 684364 | 0 | 0 | 0 | 400000 | 84000 | 316000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 716073 | 151094 | 564979 | 826073 | 174194 | 651879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 876109 | 184862 | 691247 | 5172076 | 1090801 | 4081275 | 13391443 | 2825651 | 10565792 | 876109 | 184862 | 691247 | 5172076 | 1090801 | 4081275 | 0 | 0 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | CCI | 2011 | Q3 | Q3 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 2277755 | 8517228 | 2994721 | 628891 | 2365830 | 6132221 | 1287766 | 4844455 | 150000 | 31664 | 118336 | 81012 | 17094 | 63918 | 112012 | 23094 | 88918 | 867400 | 183036 | 684364 | 823900 | 823900 | 0 | 867400 | 867400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 819323 | 172882 | 646441 | 922320 | 193687 | 728633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 4718956 | 1642767 | 3076189 | 8033953 | 2371947 | 5662006 | 13391443 | 2825651 | 10565792 | 4718956 | 1642767 | 3076189 | 8033953 | 2371947 | 5662006 | 0 | 0 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | CCI | 2011 | Q4 | Q4 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 2277755 | 8517228 | 5461525 | 1149397 | 4312128 | 7046844 | 1095593 | 5951251 | 150000 | 31664 | 118336 | 102445 | 21616 | 80828 | 122785 | 25367 | 97418 | 867400 | 183036 | 684364 | 823900 | 823900 | 0 | 823900 | 823900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 944112 | 199213 | 744899 | 1042320 | 219008 | 823312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 7331982 | 2194126 | 5137855 | 9035849 | 2163868 | 6871981 | 13391443 | 2825651 | 10565792 | 7331982 | 2194126 | 5137855 | 9035849 | 2163868 | 6871981 | 0 | 0 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | CCI | 2012 | Q1 | Q1 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 2277755 | 8517228 | 5873856 | 1233510 | 4640346 | 6640856 | 1365510 | 5275346 | 150000 | 31664 | 118336 | 125144 | 26280 | 98864 | 133144 | 28280 | 104864 | 867400 | 183036 | 684364 | 823900 | 823900 | 0 | 823900 | 823900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 1148128 | 241107 | 907021 | 1188128 | 250107 | 938021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 7971028 | 2324797 | 5646231 | 8786028 | 2467797 | 6318231 | 13391443 | 2825651 | 10565792 | 7971028 | 2324797 | 5646231 | 8786028 | 2467797 | 6318231 | 0 | 0 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | CCI | 2012 | Q2 | Q2 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 1593391 | 9201592 | 8257719 | 1233510 | 7024209 | 9517769 | 1404868 | 8112901 | 150000 | 31664 | 118336 | 158407 | 33439 | 124968 | 162611 | 34326 | 128285 | 867400 | 867400 | 0 | 823900 | 823900 | 0 | 823900 | 823900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 1275356 | 269112 | 1006244 | 1427208 | 301154 | 1126054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 10515382 | 2359961 | 8155421 | 11931488 | 2564248 | 9367240 | 13391443 | 2825651 | 10565792 | 10515382 | 2359961 | 8155421 | 11931488 | 2564248 | 9367240 | 169480 | 0 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | CCI | 2012 | Q3 | Q3 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 1593391 | 9201592 | 8986712 | 1270717 | 7715995 | 9845740 | 1453278 | 8392462 | 150000 | 31664 | 118336 | 180290 | 35198 | 145092 | 189998 | 37247 | 152751 | 867400 | 867400 | 0 | 823900 | 823900 | 0 | 823900 | 823900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 1327062 | 269112 | 1057950 | 1490754 | 314563 | 1176191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 11317964 | 2398927 | 8919037 | 12350392 | 2628988 | 9721404 | 13391443 | 2825651 | 10565792 | 11317964 | 2398927 | 8919037 | 12350392 | 2628988 | 9721404 | 169480 | 0 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | CCI | 2012 | Q4 | Q4 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 1593391 | 9201592 | 9924088 | 1453278 | 8470810 | 10495122 | 1549130 | 8945992 | 150000 | 31664 | 118336 | 189998 | 37247 | 152751 | 244398 | 77247 | 167151 | 867400 | 867400 | 0 | 823900 | 823900 | 0 | 867400 | 867400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 1490754 | 314563 | 1176191 | 1535197 | 323941 | 1211257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 12428740 | 2628988 | 9799752 | 13142117 | 2817718 | 10324400 | 13391443 | 2825651 | 10565792 | 12428740 | 2628988 | 9799752 | 13142117 | 2817718 | 10324400 | 169480 | 0 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | CCI | 2013 | Q1 | Q1 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 1593391 | 9201592 | 10110456 | 1518929 | 8591527 | 10529252 | 1593391 | 8935861 | 150000 | 31664 | 118336 | 189998 | 37247 | 152751 | 189998 | 37247 | 152751 | 867400 | 867400 | 0 | 823900 | 823900 | 0 | 867400 | 867400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 1534387 | 333196 | 1201191 | 1599060 | 333196 | 1265864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 12658741 | 2713272 | 9945469 | 13185710 | 2831234 | 10354476 | 13391443 | 2825651 | 10565792 | 12658741 | 2713272 | 9945469 | 13185710 | 2831234 | 10354476 | 169480 | 0 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | CCI | 2013 | Q2 | Q2 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 1593391 | 9201592 | 10542535 | 1532818 | 9009717 | 10734985 | 1587808 | 9147177 | 150000 | 31664 | 118336 | 189998 | 37247 | 152751 | 189998 | 37247 | 152751 | 867400 | 867400 | 0 | 843900 | 843900 | 0 | 867400 | 867400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 1599060 | 333196 | 1265864 | 1599060 | 333196 | 1265864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 13175493 | 2747161 | 10428332 | 13391443 | 2825651 | 10565792 | 13391443 | 2825651 | 10565792 | 13175493 | 2747161 | 10428332 | 13391443 | 2825651 | 10565792 | 169480 | 0 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570116 | CCI | 2013 | Q3 | Q3 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10794983 | 1593391 | 9201592 | 10840875 | 1693698 | 9147177 | 10840875 | 1693698 | 9147177 | 150000 | 31664 | 118336 | 258641 | 105890 | 152751 | 258641 | 105890 | 152751 | 867400 | 867400 | 0 | 867400 | 867400 | 0 | 867400 | 867400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579060 | 333196 | 1245864 | 1634060 | 368196 | 1265864 | 1634060 | 368196 | 1265864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13391443 | 2825651 | 10565792 | 13600976 | 3035184 | 10565792 | 13600976 | 3035184 | 10565792 | 13391443 | 2825651 | 10565792 | 13600976 | 3035184 | 10565792 | 13600976 | 3035184 | 10565792 | 169480 | 92853 | North Central New Mexico Economic Development District | TRUE
NT10BIX5570117 | CCI | 2010 | Q4 | Q4 - 2010 | 12818604 | 4101953 | 8716651 | 4886 | 1564 | 3322 | 2708617 | 866757 | 1841860 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628760 | 314763 | 313997 | 356903 | 227769 | 129134 | 556903 | 291769 | 265134 | 483500 | 154720 | 328780 | 0 | 0 | 0 | 177500 | 56800 | 120700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 5742 | 1895 | 3847 | 34500 | 11040 | 23460 | 14306764 | 4701924 | 9604840 | 367531 | 231228 | 136303 | 3477520 | 1226366 | 2251154 | 14306764 | 4701924 | 9604840 | 367531 | 231228 | 136303 | 3477520 | 1226366 | 2251154 | 0 | 0 | Oconee County | TRUE
NT10BIX5570117 | CCI | 2011 | Q1 | Q1 - 2011 | 12818604 | 4101953 | 8716651 | 34037 | 11331 | 22706 | 4888827 | 1564425 | 3324402 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628760 | 314763 | 313997 | 356903 | 227769 | 129134 | 528760 | 282763 | 245997 | 483500 | 154720 | 328780 | 0 | 0 | 0 | 177500 | 56800 | 120700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 11339 | 3628 | 7711 | 50000 | 16000 | 34000 | 14306764 | 4701924 | 9619840 | 402279 | 242728 | 159551 | 5645087 | 1919988 | 3725099 | 14306764 | 4701924 | 9619840 | 402279 | 242728 | 159551 | 5645087 | 1919988 | 3725099 | 0 | 0 | Oconee County | TRUE
NT10BIX5570117 | CCI | 2011 | Q2 | Q2 - 2011 | 12818604 | 4101953 | 8716651 | 34037 | 11331 | 22706 | 4888827 | 1564425 | 3324402 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628760 | 314763 | 313997 | 356903 | 227769 | 129134 | 528760 | 282763 | 245997 | 483500 | 154720 | 328780 | 0 | 0 | 0 | 177500 | 56800 | 120700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 14410 | 4611 | 9799 | 53701 | 16983 | 36088 | 14306764 | 4701924 | 9619840 | 405350 | 243711 | 161639 | 5648788 | 1920971 | 3727187 | 14306764 | 4701924 | 9619840 | 405350 | 243711 | 161639 | 5648788 | 1920971 | 3727187 | 0 | 0 | Oconee County | TRUE
NT10BIX5570117 | CCI | 2011 | Q3 | Q3 - 2011 | 12818604 | 4101953 | 8716651 | 534808 | 171577 | 363228 | 4534808 | 1451577 | 3083231 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628760 | 314763 | 313997 | 371928 | 232577 | 139351 | 571928 | 296577 | 275351 | 483500 | 154720 | 328780 | 0 | 0 | 0 | 100000 | 32000 | 68000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 29790 | 9475 | 20135 | 129610 | 41475 | 88135 | 14306764 | 4701924 | 9604840 | 936526 | 413629 | 522714 | 5336346 | 1821629 | 3514717 | 14306764 | 4701924 | 9604840 | 936526 | 413629 | 522714 | 5336346 | 1821629 | 3514717 | 0 | 0 | Oconee County | TRUE
NT10BIX5570117 | CCI | 2011 | Q4 | Q4 - 2011 | 12818604 | 4101953 | 8716651 | 2493270 | 798285 | 1694985 | 5493271 | 1757847 | 3735424 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628760 | 314763 | 313997 | 431090 | 251509 | 179581 | 531090 | 283509 | 247581 | 483500 | 154720 | 328780 | 100238 | 32076 | 68162 | 300238 | 96076 | 204162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 33128 | 10601 | 22527 | 113128 | 36201 | 76927 | 14306764 | 4701924 | 9604840 | 3057726 | 1092471 | 1965255 | 6437727 | 2173633 | 4264094 | 14306764 | 4701924 | 9604840 | 3057726 | 1092471 | 1965255 | 6437727 | 2173633 | 4264094 | 0 | 0 | Oconee County | TRUE
NT10BIX5570117 | CCI | 2012 | Q1 | Q1 - 2012 | 12280364 | 3929716 | 8350648 | 5127970 | 1641389 | 3486581 | 7921199 | 2534784 | 5386415 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805760 | 371403 | 434357 | 668229 | 327393 | 340836 | 793229 | 367393 | 425836 | 844740 | 270317 | 574423 | 154239 | 49356 | 104883 | 454239 | 145356 | 308883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 33128 | 10601 | 22527 | 100000 | 32000 | 68000 | 14306764 | 4701924 | 9604840 | 5983566 | 2028739 | 3954827 | 9268667 | 3079533 | 6189134 | 14306764 | 4701924 | 9604840 | 5983566 | 2028739 | 3954827 | 9268667 | 3079533 | 6189134 | 0 | 0 | Oconee County | TRUE
NT10BIX5570117 | CCI | 2012 | Q2 | Q2 - 2012 | 12280364 | 3929716 | 8350648 | 8181776 | 2618607 | 5563169 | 11340341 | 3628909 | 7711432 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805760 | 371403 | 434357 | 767102 | 359033 | 408069 | 805760 | 371404 | 434356 | 844740 | 270317 | 574423 | 212189 | 67900 | 144289 | 512189 | 163900 | 348289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 41710 | 13347 | 28363 | 241710 | 77347 | 164363 | 14306764 | 4701924 | 9604840 | 9202777 | 3058887 | 6143890 | 12900000 | 4241560 | 8658440 | 14306764 | 4701924 | 9604840 | 9202777 | 3058887 | 6143890 | 12900000 | 4241560 | 8658440 | 0 | 0 | Oconee County | TRUE
NT10BIX5570117 | CCI | 2012 | Q3 | Q3 - 2012 | 12280364 | 3929716 | 8350648 | 9096723 | 2911390 | 6185333 | 11700000 | 3744000 | 7956000 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805760 | 371403 | 434357 | 782462 | 363948 | 418514 | 805760 | 371403 | 434357 | 844740 | 270317 | 574423 | 378220 | 121030 | 257190 | 844740 | 270317 | 574423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 41710 | 13347 | 28363 | 300000 | 96000 | 204000 | 14306764 | 4701924 | 9604840 | 10299115 | 3409715 | 6889400 | 13650500 | 4481720 | 9168780 | 14306764 | 4701924 | 9604840 | 10299115 | 3409715 | 6889400 | 13650500 | 4481720 | 9168780 | 0 | 0 | Oconee County | TRUE
NT10BIX5570117 | CCI | 2012 | Q4 | Q4 - 2012 | 12280364 | 3929716 | 8350648 | 11224120 | 3592157 | 7631963 | 12280364 | 3929716 | 8350648 | 15000 | 15000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016060 | 438699 | 577361 | 815792 | 374613 | 441179 | 1016060 | 438699 | 577361 | 634440 | 203021 | 431419 | 504990 | 161597 | 343393 | 634440 | 203021 | 431419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360900 | 115488 | 245412 | 41710 | 13347 | 28363 | 360900 | 115488 | 245412 | 14306764 | 4701924 | 9604840 | 12586612 | 4141714 | 8444898 | 14306764 | 4701924 | 9604840 | 14306764 | 4701924 | 9604840 | 12586612 | 4141714 | 8444898 | 14306764 | 4701924 | 9604840 | 0 | 0 | Oconee County | TRUE
NT10BIX5570117 | CCI | 2013 | Q1 | Q1 - 2013 | 12502265 | 4000725 | 8501540 | 11993313 | 3838299 | 8155014 | 12377242 | 3960718 | 8416525 | 15000 | 15000 | 0 | 2893 | 2893 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016060 | 438699 | 577361 | 925314 | 409660 | 515654 | 1016060 | 438699 | 577361 | 713027 | 228169 | 484858 | 713027 | 228169 | 484858 | 713027 | 228169 | 484858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60412 | 19331 | 41081 | 41710 | 13347 | 28363 | 60412 | 19331 | 41081 | 14306764 | 4701924 | 9604840 | 13676257 | 4492368 | 9183889 | 14181741 | 4661917 | 9519825 | 14306764 | 4701924 | 9604840 | 13676257 | 4492368 | 9183889 | 14181741 | 4661917 | 9519825 | 0 | 0 | Oconee County | TRUE
NT10BIX5570117 | CCI | 2013 | Q2 | Q2 - 2013 | 12502265 | 4000725 | 8501540 | 12332135 | 3946722 | 8385413 | 12502265 | 4000725 | 8501540 | 15000 | 15000 | 0 | 5670 | 5670 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016060 | 438699 | 577361 | 948354 | 417033 | 531321 | 1016060 | 438699 | 577361 | 713027 | 228169 | 484858 | 713027 | 228169 | 484858 | 713027 | 228169 | 484858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60412 | 19331 | 41081 | 60412 | 19331 | 41081 | 60412 | 19331 | 41081 | 14306764 | 4701924 | 9604840 | 14059598 | 4616925 | 9442673 | 14306764 | 4701924 | 9604840 | 14306764 | 4701924 | 9604840 | 14059598 | 4616925 | 9442673 | 14306764 | 4701924 | 9604840 | 0 | 0 | Oconee County | TRUE
NT10BIX5570117 | CCI | 2013 | Q3 | Q3 - 2013 | 12433575 | 3979183 | 8454392 | 12433575 | 3979183 | 8454392 | 12433575 | 3979183 | 8454392 | 15000 | 15000 | 0 | 15000 | 15000 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1084750 | 460241 | 624509 | 1084750 | 460241 | 624509 | 1084750 | 460241 | 624509 | 713027 | 228169 | 484858 | 713027 | 228169 | 484858 | 713027 | 228169 | 484858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60412 | 19331 | 41081 | 60412 | 19331 | 41081 | 60412 | 19331 | 41081 | 14306764 | 4701924 | 9604840 | 14306764 | 4701924 | 9604840 | 14306764 | 4701924 | 9604840 | 14306764 | 4701924 | 9604840 | 14306764 | 4701924 | 9604840 | 14306764 | 4701924 | 9604840 | 0 | 0 | Oconee County | TRUE
NT10BIX5570118 | CCI | 2010 | Q4 | Q4 - 2010 | 1435980 | 570000 | 865980 | 0 | 0 | 0 | 100000 | 0 | 100000 | 8329504 | 1035600 | 7293904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642500 | 1005000 | 637500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 0 | 216000 | 0 | 0 | 0 | 108000 | 0 | 108000 | 570000 | 570000 | 0 | 0 | 0 | 0 | 123750 | 123750 | 0 | 150000 | 0 | 150000 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12343984 | 3180600 | 9163384 | 0 | 0 | 0 | 406750 | 123750 | 283000 | 12343984 | 3180600 | 9163384 | 0 | 0 | 0 | 406750 | 123750 | 283000 | 0 | 0 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | CCI | 2011 | Q1 | Q1 - 2011 | 1435980 | 570000 | 865980 | 0 | 0 | 0 | 0 | 0 | 0 | 8329504 | 1035600 | 7293904 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642500 | 1005000 | 637500 | 0 | 0 | 0 | 1205000 | 1005000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 0 | 216000 | 238234 | 0 | 238234 | 600000 | 0 | 600000 | 570000 | 570000 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 150000 | 0 | 150000 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12343984 | 3180600 | 9163384 | 238234 | 0 | 238234 | 3005000 | 1105000 | 1900000 | 12343984 | 3180600 | 9163384 | 238234 | 0 | 238234 | 3005000 | 1105000 | 1900000 | 0 | 0 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | CCI | 2011 | Q2 | Q2 - 2011 | 1435980 | 570000 | 865980 | 0 | 0 | 0 | 750000 | 500000 | 250000 | 8329504 | 1035600 | 7293904 | 765000 | 0 | 0 | 3000000 | 50000 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642500 | 1005000 | 637500 | 765227 | 765227 | 0 | 1642500 | 1005000 | 637500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 0 | 216000 | 530196 | 0 | 530196 | 530196 | 0 | 530196 | 570000 | 570000 | 0 | 125000 | 125000 | 0 | 190000 | 190000 | 0 | 150000 | 0 | 150000 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12343984 | 3180600 | 9163384 | 2185423 | 890227 | 530196 | 6212696 | 1745000 | 4017696 | 12343984 | 3180600 | 9163384 | 2185423 | 890227 | 530196 | 6212696 | 1745000 | 4017696 | 0 | 0 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | CCI | 2011 | Q3 | Q3 - 2011 | 1435980 | 570000 | 865980 | 702716 | 136290 | 566426 | 1000000 | 400000 | 600000 | 8329504 | 1035600 | 7293904 | 1262560 | 325567 | 936993 | 5600000 | 1000000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642500 | 1005000 | 637500 | 382333 | 330733 | 51600 | 1080733 | 830733 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 0 | 216000 | 707520 | 65379 | 642141 | 800000 | 65379 | 734621 | 570000 | 570000 | 0 | 72588 | 32258 | 40330 | 272588 | 232258 | 40330 | 150000 | 0 | 150000 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1685 | 0 | 1685 | 1685 | 0 | 1685 | 12343984 | 3180600 | 9163384 | 3129402 | 890227 | 2239175 | 8855006 | 2528370 | 5726636 | 12343984 | 3180600 | 9163384 | 3129402 | 890227 | 2239175 | 8855006 | 2528370 | 5726636 | 0 | 0 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | CCI | 2011 | Q4 | Q4 - 2011 | 1435980 | 570000 | 865980 | 973942 | 403047 | 570895 | 1415000 | 550000 | 865000 | 8329504 | 1035600 | 7293904 | 4028642 | 776090 | 3252552 | 6500000 | 1000000 | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642500 | 1005000 | 637500 | 1145863 | 1094263 | 51600 | 1145863 | 1094263 | 51600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 0 | 216000 | 901802 | 114083 | 787719 | 1000000 | 164083 | 835917 | 570000 | 570000 | 0 | 257976 | 217646 | 40330 | 307976 | 267646 | 40330 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1686 | 0 | 1686 | 1686 | 0 | 1686 | 12343984 | 3180600 | 9163384 | 7309911 | 2605129 | 4704782 | 10370525 | 3075992 | 7294533 | 12343984 | 3180600 | 9163384 | 7309911 | 2605129 | 4704782 | 10370525 | 3075992 | 7294533 | 0 | 0 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | CCI | 2012 | Q1 | Q1 - 2012 | 1435980 | 570000 | 865980 | 977395 | 403047 | 574348 | 1250000 | 403047 | 846953 | 8329504 | 1035600 | 7293904 | 4621518 | 776090 | 3845428 | 5000000 | 776090 | 4223910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642500 | 1005000 | 637500 | 1226421 | 1094263 | 132158 | 1226421 | 1094263 | 132158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216000 | 0 | 216000 | 1111748 | 144293 | 967455 | 1111748 | 144293 | 967455 | 570000 | 570000 | 0 | 299218 | 258888 | 40330 | 340330 | 300000 | 40330 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1686 | 0 | 1686 | 1686 | 0 | 1686 | 12343984 | 3180600 | 9163384 | 8237986 | 2676581 | 5561405 | 8930185 | 2717693 | 6212492 | 12343984 | 3180600 | 9163384 | 8237986 | 2676581 | 5561405 | 8930185 | 2717693 | 6212492 | 0 | 0 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | CCI | 2012 | Q2 | Q2 - 2012 | 1810980 | 570000 | 1240980 | 1162206 | 403047 | 759159 | 1403047 | 403047 | 1000000 | 7004505 | 1035600 | 5968905 | 5133870 | 776090 | 4357780 | 6000000 | 1035600 | 4964400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642500 | 1005000 | 637500 | 1443830 | 1094263 | 349567 | 1500000 | 1094263 | 405737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165999 | 0 | 1165999 | 1234018 | 144293 | 1089725 | 1244293 | 144293 | 1100000 | 570000 | 570000 | 0 | 258888 | 258888 | 0 | 340000 | 340000 | 0 | 150000 | 0 | 150000 | 127714 | 0 | 127714 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12343984 | 3180600 | 9163384 | 9360526 | 2676581 | 6683945 | 10637340 | 3017203 | 7620137 | 12343984 | 3180600 | 9163384 | 9360526 | 2676581 | 6683945 | 10637340 | 3017203 | 7620137 | 0 | 0 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | CCI | 2012 | Q3 | Q3 - 2012 | 1810980 | 570000 | 1240980 | 1669893 | 403047 | 1266846 | 1800000 | 500000 | 1300000 | 7004505 | 1035600 | 5968905 | 5522492 | 776090 | 4746402 | 6000000 | 1000000 | 5000000 | 0 | 0 | 0 | 2967 | 0 | 2967 | 2967 | 0 | 2967 | 1642500 | 1005000 | 637500 | 1451726 | 1094263 | 357463 | 1594263 | 1094263 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165999 | 0 | 1165999 | 1213558 | 144293 | 1069265 | 1350000 | 150000 | 1200000 | 570000 | 570000 | 0 | 342188 | 342188 | 0 | 400000 | 400000 | 0 | 150000 | 0 | 150000 | 168044 | 0 | 168044 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12343984 | 3180600 | 9163384 | 10370868 | 2759881 | 7610987 | 11347230 | 3144263 | 8202967 | 12343984 | 3180600 | 9163384 | 10370868 | 2759881 | 7610987 | 11347230 | 3144263 | 8202967 | 0 | 0 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | CCI | 2012 | Q4 | Q4 - 2012 | 1810980 | 570000 | 1240980 | 1674807 | 403047 | 1271760 | 1900000 | 403047 | 1496953 | 7004505 | 1035600 | 5968905 | 5569126 | 776090 | 4793036 | 6500000 | 850000 | 5650000 | 0 | 0 | 0 | 2967 | 0 | 2967 | 2967 | 0 | 2967 | 1642500 | 1005000 | 637500 | 1451726 | 1094263 | 357463 | 1500000 | 1094263 | 405737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165999 | 0 | 1165999 | 1350491 | 232257 | 1118234 | 1400000 | 250000 | 1150000 | 570000 | 570000 | 0 | 390499 | 390499 | 0 | 450000 | 450000 | 0 | 150000 | 0 | 150000 | 168044 | 0 | 168044 | 175000 | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 2200 | 2200 | 0 | 2200 | 12343984 | 3180600 | 9163384 | 10609860 | 2896156 | 7713704 | 11930167 | 3047310 | 8882857 | 12343984 | 3180600 | 9163384 | 10609860 | 2896156 | 7713704 | 11930167 | 3047310 | 8882857 | 0 | 0 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | CCI | 2013 | Q1 | Q1 - 2013 | 1810980 | 570000 | 1240980 | 1674807 | 403047 | 1271760 | 1900000 | 403047 | 1496953 | 7004505 | 1035600 | 5968905 | 5569126 | 776090 | 4793036 | 6500000 | 850000 | 5650000 | 0 | 0 | 0 | 2967 | 0 | 2967 | 2967 | 0 | 2967 | 1642500 | 1005000 | 637500 | 1451726 | 1094263 | 357463 | 1500000 | 1094263 | 405737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165999 | 0 | 1165999 | 1359988 | 241754 | 1118234 | 1400000 | 250000 | 1150000 | 570000 | 570000 | 0 | 427044 | 427044 | 0 | 450000 | 450000 | 0 | 150000 | 0 | 150000 | 168044 | 0 | 168044 | 175000 | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 2200 | 2200 | 0 | 2200 | 12343984 | 3180600 | 9163384 | 10655902 | 2942198 | 7713704 | 11930167 | 3047310 | 8882857 | 12343984 | 3180600 | 9163384 | 10655902 | 2942198 | 7713704 | 11930167 | 3047310 | 8882857 | 0 | 0 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | CCI | 2013 | Q2 | Q2 - 2013 | 1810980 | 570000 | 1240980 | 1739898 | 403047 | 1336851 | 1975431 | 403047 | 1572384 | 7004505 | 1035600 | 5968905 | 6280554 | 776090 | 5504464 | 6350000 | 776090 | 5573910 | 0 | 0 | 0 | 2967 | 0 | 2967 | 2967 | 0 | 2967 | 1642500 | 1005000 | 637500 | 1453606 | 1094263 | 359343 | 1642500 | 1094263 | 548237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165999 | 0 | 1165999 | 1459636 | 293746 | 1165890 | 1584142 | 377888 | 1206254 | 570000 | 570000 | 0 | 427044 | 427044 | 0 | 570000 | 570000 | 0 | 150000 | 0 | 150000 | 168044 | 0 | 168044 | 168044 | 0 | 168044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50900 | 48575 | 2325 | 50900 | 48575 | 2325 | 12343984 | 3180600 | 9163384 | 11582649 | 3042765 | 8539884 | 12343984 | 3269863 | 9074121 | 12343984 | 3180600 | 9163384 | 11582649 | 3042765 | 8539884 | 12343984 | 3269863 | 9074121 | 0 | 0 | Nexus Systems, Inc. | TRUE
NT10BIX5570118 | CCI | 2013 | Q3 | Q3 - 2013 | 1810980 | 570000 | 1240980 | 2340806 | 655259 | 1685547 | 2340806 | 655259 | 1685547 | 7004505 | 1035600 | 5968905 | 6569761 | 798164 | 5771597 | 6569761 | 798164 | 5771597 | 0 | 0 | 0 | 7266 | 4299 | 2967 | 7266 | 4299 | 2967 | 1642500 | 1005000 | 637500 | 1466014 | 1101216 | 364798 | 1466014 | 1101216 | 364798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165999 | 0 | 1165999 | 1505983 | 335877 | 1170106 | 1505983 | 335877 | 1170106 | 570000 | 570000 | 0 | 436482 | 436482 | 0 | 436482 | 436482 | 0 | 150000 | 0 | 150000 | 213523 | 45479 | 168044 | 213523 | 45479 | 168044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66059 | 65734 | 325 | 66059 | 65734 | 325 | 12343984 | 3180600 | 9163384 | 12605894 | 3442510 | 9163384 | 12605894 | 3442510 | 9163384 | 12343984 | 3180600 | 9163384 | 12605894 | 3442510 | 9163384 | 12605894 | 3442510 | 9163384 | 0 | 0 | Nexus Systems, Inc. | TRUE
NT10BIX5570119 | CCI | 2010 | Q4 | Q4 - 2010 | 14259128 | 4277738 | 9981390 | 0 | 0 | 0 | 12237736 | 3671321 | 8566415 | 66228948 | 19868684 | 46360264 | 0 | 0 | 0 | 4850000 | 1455000 | 3395000 | 1485174 | 445552 | 1039622 | 433932 | 130180 | 303752 | 125000 | 37500 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 94174 | 28252 | 65922 | 1021647 | 306494 | 715153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 0 | 0 | 0 | 0 | 0 | 0 | 94963210 | 28488963 | 66474247 | 528106 | 158432 | 369674 | 18234383 | 5470315 | 12764068 | 94963210 | 28488963 | 66474247 | 528106 | 158432 | 369674 | 18234383 | 5470315 | 12764068 | 0 | 0 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | CCI | 2011 | Q1 | Q1 - 2011 | 14259128 | 4277738 | 9981390 | 843221 | 252966 | 590255 | 1843221 | 552966 | 1290254 | 66228948 | 19868684 | 46360264 | 0 | 0 | 0 | 1144482 | 343345 | 801137 | 1485174 | 445552 | 1039622 | 694620 | 208386 | 486234 | 1101877 | 330563 | 771314 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 331429 | 99429 | 232000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 472496 | 141749 | 330747 | 1141230 | 342369 | 798861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 0 | 0 | 0 | 0 | 0 | 0 | 94963210 | 28488963 | 66474247 | 2111637 | 633491 | 1478146 | 5562239 | 1668672 | 3893566 | 94963210 | 28488963 | 66474247 | 2111637 | 633491 | 1478146 | 5562239 | 1668672 | 3893566 | 0 | 0 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | CCI | 2011 | Q2 | Q2 - 2011 | 14259128 | 4277738 | 9981390 | 843221 | 252966 | 590254 | 6225223 | 1867567 | 4357656 | 66228948 | 19868684 | 46360264 | 265635 | 79690 | 185945 | 5694346 | 1708304 | 3986042 | 1485174 | 445552 | 1039622 | 1019324 | 305797 | 713527 | 1167842 | 350353 | 817489 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 1398213 | 419464 | 978749 | 4512224 | 1353667 | 3158557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 0 | 0 | 0 | 0 | 0 | 0 | 94963210 | 28488963 | 66474247 | 3627693 | 1088307 | 2539385 | 17700935 | 5310281 | 12390654 | 94963210 | 28488963 | 66474247 | 3627693 | 1088307 | 2539385 | 17700935 | 5310281 | 12390654 | 0 | 0 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | CCI | 2011 | Q3 | Q3 - 2011 | 14259128 | 4277738 | 9981390 | 882486 | 264746 | 617740 | 11587719 | 3476316 | 8111403 | 66228948 | 19868684 | 46360264 | 5368691 | 1610607 | 3758084 | 16627612 | 4988283 | 11639329 | 1485174 | 445552 | 1039622 | 1217025 | 365108 | 851917 | 1365542 | 409663 | 955879 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 3281594 | 984478 | 2297116 | 5617102 | 1685130 | 3931972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 0 | 0 | 0 | 0 | 0 | 0 | 94963210 | 28488963 | 66474247 | 10851096 | 3255329 | 7595767 | 35299275 | 10589782 | 24709493 | 94963210 | 28488963 | 66474247 | 10851096 | 3255329 | 7595767 | 35299275 | 10589782 | 24709493 | 0 | 0 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | CCI | 2011 | Q4 | Q4 - 2011 | 14259128 | 4277738 | 9981390 | 10228544 | 3068563 | 7159981 | 13148153 | 3944446 | 9203707 | 66228948 | 19868684 | 46360264 | 13279164 | 3983749 | 9295415 | 33147849 | 9944355 | 23203494 | 1485174 | 445552 | 1039622 | 1374407 | 412322 | 962085 | 1493221 | 447966 | 1045255 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 4939721 | 1481916 | 3457805 | 6107475 | 1832242 | 4275233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 0 | 0 | 0 | 0 | 0 | 0 | 94963210 | 28488963 | 66474247 | 29923136 | 8976940 | 20946196 | 53997998 | 16199399 | 37798599 | 94963210 | 28488963 | 66474247 | 29923136 | 8976940 | 20946196 | 53997998 | 16199399 | 37798599 | 0 | 0 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | CCI | 2012 | Q1 | Q1 - 2012 | 14259128 | 4277738 | 9981390 | 10375930 | 3112779 | 7263150 | 12895929 | 3868779 | 9027150 | 66228948 | 19868684 | 46360264 | 27413608 | 8224082 | 19189526 | 40064491 | 12019347 | 28045144 | 1485174 | 445552 | 1039622 | 1559248 | 467774 | 1091474 | 1679248 | 503774 | 1175474 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 6741131 | 2022339 | 4718792 | 7629327 | 2288798 | 5340529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 0 | 0 | 0 | 1197134 | 359140 | 837994 | 94963210 | 28488963 | 66474247 | 46191217 | 13857364 | 32333852 | 63567429 | 19070228 | 44497201 | 94963210 | 28488963 | 66474247 | 46191217 | 13857364 | 32333852 | 63567429 | 19070228 | 44497201 | 0 | 0 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | CCI | 2012 | Q2 | Q2 - 2012 | 14259128 | 4277738 | 9981390 | 12367552 | 3710266 | 8657286 | 14867552 | 4460266 | 10407286 | 66228948 | 19868684 | 46360264 | 34395988 | 10318796 | 24077192 | 44395988 | 13318796 | 31077192 | 1485174 | 445552 | 1039622 | 2086676 | 626003 | 1460673 | 2236676 | 671003 | 1565673 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8141090 | 2442327 | 5698763 | 8641090 | 2592327 | 6048763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 0 | 0 | 0 | 1608995 | 482698 | 1126297 | 94963210 | 28488963 | 66474247 | 57092606 | 17127782 | 39964824 | 71851601 | 21555480 | 50296121 | 94963210 | 28488963 | 66474247 | 57092606 | 17127782 | 39964824 | 71851601 | 21555480 | 50296121 | 0 | 0 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | CCI | 2012 | Q3 | Q3 - 2012 | 14259128 | 4277738 | 9981390 | 14242099 | 4272630 | 9969469 | 15242099 | 4572630 | 10669468 | 66228948 | 19868684 | 46360264 | 45980808 | 13794242 | 32186566 | 54980808 | 16494242 | 38486566 | 1485174 | 445552 | 1039622 | 1861428 | 558428 | 1303000 | 1891428 | 567428 | 1324000 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8691121 | 2607336 | 6083785 | 8741121 | 2622336 | 6118785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 1428463 | 428540 | 999923 | 1608995 | 482699 | 1126297 | 94963210 | 28488963 | 66474247 | 72305219 | 21691566 | 50613653 | 82565751 | 24769725 | 57796026 | 94963210 | 28488963 | 66474247 | 72305219 | 21691566 | 50613653 | 82565751 | 24769725 | 57796026 | 0 | 0 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | CCI | 2012 | Q4 | Q4 - 2012 | 14259128 | 4277738 | 9981390 | 14706494 | 4411948 | 10294546 | 15476494 | 4642948 | 10833545 | 66228948 | 19868684 | 46360264 | 56017094 | 16805128 | 39211966 | 60517094 | 18155128 | 42361966 | 1485174 | 445552 | 1039622 | 2030191 | 609057 | 1421134 | 2130191 | 639057 | 1491134 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8691121 | 2607336 | 6083785 | 8741121 | 2622336 | 6118785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 1428463 | 428539 | 999924 | 1608995 | 482699 | 1126297 | 94963210 | 28488963 | 66474247 | 82974663 | 24892398 | 58082265 | 88575195 | 26572558 | 62002637 | 94963210 | 28488963 | 66474247 | 82974663 | 24892398 | 58082265 | 88575195 | 26572558 | 62002637 | 0 | 0 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | CCI | 2013 | Q1 | Q1 - 2013 | 14259128 | 4277738 | 9981390 | 15062742 | 4518823 | 10543919 | 15762742 | 4728823 | 11033919 | 66228948 | 19868684 | 46360264 | 62204332 | 18661300 | 43543032 | 63704332 | 19111300 | 44593032 | 1485174 | 445552 | 1039622 | 2095643 | 628693 | 1466950 | 2145643 | 643693 | 1501950 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8691121 | 2607336 | 6083785 | 8691121 | 2607336 | 6083785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 1428463 | 428539 | 999924 | 1608995 | 482698 | 1126297 | 94963210 | 28488963 | 66474247 | 89583601 | 26875081 | 62708520 | 92014133 | 27604240 | 64409893 | 94963210 | 28488963 | 66474247 | 89583601 | 26875081 | 62708520 | 92014133 | 27604240 | 64409893 | 0 | 0 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | CCI | 2013 | Q2 | Q2 - 2013 | 14259128 | 4277738 | 9981390 | 15133437 | 4589518 | 10543919 | 15938437 | 5394518 | 10543919 | 66228948 | 19868684 | 46360264 | 64410453 | 19363482 | 45046971 | 65610453 | 20563482 | 45046971 | 1485174 | 445552 | 1039622 | 2326769 | 698031 | 1628738 | 2376769 | 748031 | 1628738 | 0 | 0 | 0 | 101300 | 30390 | 70910 | 101300 | 30390 | 70910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8691121 | 2607336 | 6083785 | 8691121 | 2607336 | 6083785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 4428463 | 1328539 | 3099924 | 4428463 | 1328539 | 3099924 | 94963210 | 28488963 | 66474247 | 95091543 | 28617296 | 66474247 | 97146543 | 30672296 | 66474247 | 94963210 | 28488963 | 66474247 | 95091543 | 28617296 | 66474247 | 97146543 | 30672296 | 66474247 | 0 | 0 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | CCI | 2013 | Q3 | Q3 - 2013 | 14259128 | 4277738 | 9981390 | 15227797 | 4683878 | 10543919 | 16811672 | 6267753 | 10543919 | 66228948 | 19868684 | 46360264 | 68801320 | 23754349 | 45046971 | 69337048 | 24290077 | 45046971 | 1485174 | 445552 | 1039622 | 2385094 | 756356 | 1628738 | 2650000 | 1021262 | 1628738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8792421 | 2637726 | 6154695 | 8792421 | 2637726 | 6154695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 4428463 | 1328539 | 3099924 | 4428463 | 1328539 | 3099924 | 94963210 | 28488963 | 66474247 | 99635095 | 33160848 | 66474247 | 102019604 | 35545357 | 66474247 | 94963210 | 28488963 | 66474247 | 99635095 | 33160848 | 66474247 | 102019604 | 35545357 | 66474247 | 0 | 0 | Horizon Telecom, Inc. | TRUE
NT10BIX5570119 | CCI | 2013 | Q4 | Q4 - 2013 | 14259128 | 4277738 | 9981390 | 16059090 | 5515171 | 10543919 | 16859090 | 6315171 | 10543919 | 66228948 | 19868684 | 46360264 | 70032061 | 24985090 | 45046971 | 70282061 | 25235090 | 45046971 | 1485174 | 445552 | 1039622 | 2430662 | 801924 | 1628738 | 2480663 | 851925 | 1628738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7785028 | 2335508 | 5449520 | 8792421 | 2637726 | 6154695 | 8792421 | 2637726 | 6154695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5204932 | 1561481 | 3643451 | 4428463 | 1328539 | 3099924 | 4428493 | 1328539 | 3099924 | 94963210 | 28488963 | 66474247 | 101742697 | 35268450 | 66474247 | 102842728 | 36368451 | 66474247 | 94963210 | 28488963 | 66474247 | 101742697 | 35268450 | 66474247 | 102842728 | 36368451 | 66474247 | 0 | 0 | Horizon Telecom, Inc. | TRUE
NT10BIX5570120 | CCI | 2010 | Q4 | Q4 - 2010 | 6971935 | 1693210 | 5278725 | 4585 | 1114 | 3471 | 4585 | 1114 | 3471 | 87329001 | 25240320 | 62088681 | 12160 | 2953 | 9207 | 12160 | 2953 | 9207 | 757080 | 183865 | 573215 | 572625 | 139068 | 433557 | 640080 | 155450 | 484630 | 3401000 | 1363539 | 2037461 | 0 | 0 | 0 | 470000 | 114145 | 355855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 187280 | 45483 | 141797 | 3300663 | 801602 | 2499061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 0 | 0 | 0 | 100000 | 24286 | 75714 | 106091969 | 30334680 | 75757289 | 776650 | 188618 | 588032 | 4527488 | 1099550 | 3427938 | 106091969 | 30334680 | 75757289 | 776650 | 188618 | 588032 | 4527488 | 1099550 | 3427938 | 0 | 0 | MCNC | TRUE
NT10BIX5570120 | CCI | 2011 | Q1 | Q1 - 2011 | 6971935 | 1693210 | 5278725 | 47006 | 11416 | 35590 | 47006 | 11416 | 35590 | 85037468 | 24683797 | 60353671 | 34025 | 8263 | 25762 | 4394274 | 1067197 | 3327077 | 757080 | 183865 | 573215 | 595054 | 144516 | 450538 | 670054 | 162730 | 507324 | 5692533 | 1920062 | 3772471 | 46978 | 11409 | 35569 | 441978 | 107339 | 334639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 1887752 | 458461 | 1429291 | 4255352 | 1033459 | 3221893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 0 | 0 | 0 | 100000 | 24286 | 75714 | 106091969 | 30334680 | 75757289 | 2610815 | 634065 | 1976750 | 9908664 | 2406427 | 7502237 | 106091969 | 30334680 | 75757289 | 2610815 | 634065 | 1976750 | 9908664 | 2406427 | 7502237 | 0 | 0 | MCNC | TRUE
NT10BIX5570120 | CCI | 2011 | Q2 | Q2 - 2011 | 6971935 | 1693210 | 5278725 | 47006 | 11416 | 35590 | 297006 | 72131 | 224875 | 85037468 | 24683797 | 60353671 | 4849166 | 3661089 | 1188077 | 8598716 | 4571708 | 4027008 | 757080 | 183865 | 573215 | 696990 | 191986 | 505004 | 800000 | 194289 | 605711 | 5692533 | 1920062 | 3772471 | 127796 | 31037 | 96759 | 427796 | 103895 | 323901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 3045045 | 739522 | 2305523 | 4545000 | 1103803 | 3441197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 106091969 | 30334680 | 75757289 | 8766003 | 4635050 | 4130953 | 14868518 | 6094398 | 8774120 | 106091969 | 30334680 | 75757289 | 8766003 | 4635050 | 4130953 | 14868518 | 6094398 | 8774120 | 0 | 0 | MCNC | TRUE
NT10BIX5570120 | CCI | 2011 | Q3 | Q3 - 2011 | 6971935 | 1693210 | 5278725 | 47006 | 11416 | 35590 | 47006 | 11416 | 35590 | 85037468 | 24683797 | 60353671 | 6738932 | 3889849 | 2849083 | 15000000 | 6126329 | 8873671 | 757080 | 183865 | 573215 | 742946 | 180432 | 562514 | 792946 | 192576 | 600370 | 5692533 | 1920062 | 3772471 | 261155 | 63424 | 197731 | 522310 | 126849 | 395461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 3713805 | 901938 | 2811867 | 4500000 | 1092874 | 3407126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 129975 | 31566 | 98409 | 200000 | 48572 | 151428 | 106091969 | 30334680 | 75757289 | 11633819 | 5078625 | 6555194 | 21062262 | 7598616 | 13463646 | 106091969 | 30334680 | 75757289 | 11633819 | 5078625 | 6555194 | 21062262 | 7598616 | 13463646 | 0 | 0 | MCNC | TRUE
NT10BIX5570120 | CCI | 2011 | Q4 | Q4 - 2011 | 6971935 | 1693210 | 5278725 | 68019 | 16519 | 51500 | 100000 | 24286 | 75714 | 85037468 | 24683797 | 60353671 | 17531320 | 6741088 | 10790232 | 28400000 | 9380665 | 19019335 | 757080 | 183865 | 573215 | 823518 | 200000 | 623518 | 845000 | 205217 | 639783 | 5692533 | 1920062 | 3772471 | 405324 | 166649 | 238675 | 1250000 | 371788 | 878212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 4745461 | 1152487 | 3592974 | 5393000 | 1309749 | 4083251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 158214 | 38424 | 119790 | 185000 | 44929 | 140071 | 106091969 | 30334680 | 75757289 | 23731856 | 8315167 | 15416689 | 36173000 | 11336634 | 24836366 | 106091969 | 30334680 | 75757289 | 23731856 | 8315167 | 15416689 | 36173000 | 11336634 | 24836366 | 0 | 0 | MCNC | TRUE
NT10BIX5570120 | CCI | 2012 | Q1 | Q1 - 2012 | 6971935 | 1693210 | 5278725 | 73552 | 17863 | 55689 | 4500000 | 1092874 | 3407126 | 85037468 | 24683797 | 60353671 | 32909457 | 12451600 | 20457857 | 47909457 | 16094514 | 31814943 | 757080 | 183865 | 573215 | 884166 | 214729 | 669437 | 925000 | 224646 | 700354 | 5692533 | 1920062 | 3772471 | 1157311 | 354347 | 802964 | 5000000 | 1287586 | 3712414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 5454850 | 1324770 | 4130080 | 6500000 | 1578596 | 4921404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 186365 | 45261 | 141104 | 200000 | 48572 | 151428 | 106091969 | 30334680 | 75757289 | 40665701 | 14408570 | 26257131 | 65034457 | 20326788 | 44707669 | 106091969 | 30334680 | 75757289 | 40665701 | 14408570 | 26257131 | 65034457 | 20326788 | 44707669 | 0 | 0 | MCNC | TRUE
NT10BIX5570120 | CCI | 2012 | Q2 | Q2 - 2012 | 6971935 | 1693210 | 5278725 | 4321486 | 1049520 | 3271966 | 6000000 | 1457165 | 4542835 | 85037468 | 24683797 | 60353671 | 50698471 | 17214320 | 33484151 | 65698471 | 20857233 | 44841238 | 757080 | 183865 | 573215 | 941811 | 228729 | 713082 | 996811 | 242086 | 754725 | 5692533 | 1920062 | 3772471 | 2911273 | 808252 | 2103021 | 5692533 | 1483712 | 4208821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 5278479 | 1281936 | 3996543 | 6000000 | 1457165 | 4542835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 303845 | 73792 | 230053 | 350000 | 85001 | 264999 | 106091969 | 30334680 | 75757289 | 64455365 | 20656549 | 43798816 | 84737815 | 25582362 | 59155453 | 106091969 | 30334680 | 75757289 | 64455365 | 20656549 | 43798816 | 84737815 | 25582362 | 59155453 | 0 | 0 | MCNC | TRUE
NT10BIX5570120 | CCI | 2012 | Q3 | Q3 - 2012 | 6971935 | 1693210 | 5278725 | 5224988 | 1268945 | 3956043 | 6000000 | 1457165 | 4542835 | 85037468 | 24683797 | 60353671 | 63261929 | 20265492 | 42996437 | 74000000 | 22873349 | 51126651 | 757080 | 183865 | 573215 | 962773 | 233820 | 728953 | 975000 | 236789 | 738211 | 5692533 | 1920062 | 3772471 | 3335470 | 911273 | 2424197 | 5000000 | 1315522 | 3684478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 5380422 | 1306694 | 4073728 | 5600000 | 1360021 | 4239979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 288107 | 69970 | 218137 | 308000 | 74801 | 233199 | 106091969 | 30334680 | 75757289 | 78453689 | 24056194 | 54397495 | 91883000 | 27317647 | 64565353 | 106091969 | 30334680 | 75757289 | 78453689 | 24056194 | 54397495 | 91883000 | 27317647 | 64565353 | 0 | 0 | MCNC | TRUE
NT10BIX5570120 | CCI | 2012 | Q4 | Q4 - 2012 | 6971935 | 1693210 | 5278725 | 5729521 | 1391476 | 4338045 | 6250000 | 1517881 | 4732119 | 85037468 | 24683797 | 60353671 | 74049369 | 22885339 | 51164030 | 81851354 | 24289020 | 57562334 | 757080 | 183865 | 573215 | 994371 | 241494 | 752877 | 1000000 | 242861 | 757139 | 5692533 | 1920062 | 3772471 | 3966714 | 1121923 | 2844791 | 5000000 | 1372867 | 3627133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 5540730 | 1345626 | 4195104 | 6000000 | 1457165 | 4542835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 300242 | 72917 | 227325 | 350000 | 85001 | 264999 | 106091969 | 30334680 | 75757289 | 90580947 | 27058775 | 63522172 | 100451354 | 28964795 | 71486559 | 106091969 | 30334680 | 75757289 | 90580947 | 27058775 | 63522172 | 100451354 | 28964795 | 71486559 | 0 | 0 | MCNC | TRUE
NT10BIX5570120 | CCI | 2013 | Q1 | Q1 - 2013 | 6971935 | 1693210 | 5278725 | 6184646 | 1502008 | 4682638 | 6971935 | 1693210 | 5278725 | 85037468 | 24683797 | 60353671 | 79721744 | 23312532 | 56409212 | 86500000 | 24958705 | 61541295 | 757080 | 183865 | 573215 | 998780 | 242565 | 756215 | 1000000 | 242861 | 757139 | 5692533 | 1920062 | 3772471 | 4931473 | 1815514 | 3115959 | 5000000 | 1832157 | 3167843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 5590114 | 1357620 | 4232494 | 5700000 | 1384307 | 4315693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 302736 | 73523 | 229213 | 370000 | 89859 | 280141 | 106091969 | 30334680 | 75757289 | 97729493 | 28303762 | 69425731 | 105549140 | 30202849 | 75346291 | 106091969 | 30334680 | 75757289 | 97729493 | 28303762 | 69425731 | 105549140 | 30202849 | 75346291 | 0 | 0 | MCNC | TRUE
NT10BIX5570120 | CCI | 2013 | Q2 | Q2 - 2013 | 6971935 | 1693210 | 5278725 | 7682670 | 1865820 | 5816850 | 7682670 | 1865820 | 5816850 | 85037468 | 24683797 | 60353671 | 83296661 | 24180739 | 59115922 | 86533094 | 24966742 | 61566352 | 757080 | 183865 | 573215 | 1015775 | 246692 | 769083 | 1022000 | 248204 | 773796 | 5692533 | 1920062 | 3772471 | 4945821 | 1818999 | 3126822 | 4946000 | 1819042 | 3126958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 5544068 | 1346437 | 4197631 | 5575000 | 1353949 | 4221051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 7205 | 1750 | 5455 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 305882 | 74287 | 231595 | 326000 | 79173 | 246827 | 106091969 | 30334680 | 75757289 | 102798082 | 29534724 | 73263358 | 106091969 | 30334680 | 75757289 | 106091969 | 30334680 | 75757289 | 102798082 | 29534724 | 73263358 | 106091969 | 30334680 | 75757289 | 0 | 0 | MCNC | TRUE
NT10BIX5570120 | CCI | 2013 | Q3 | Q3 - 2013 | 6971935 | 1693210 | 5278725 | 7820412 | 1899272 | 5921140 | 7820412 | 1899272 | 5921140 | 87329001 | 25240320 | 62088681 | 84959325 | 24584535 | 60374790 | 84959325 | 24584535 | 60374790 | 757080 | 183865 | 573215 | 1064529 | 258532 | 805997 | 1064529 | 258532 | 805997 | 3401000 | 1363539 | 2037461 | 4944441 | 1818664 | 3125777 | 4944441 | 1818664 | 3125777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7425748 | 1803424 | 5622324 | 5722349 | 1389735 | 4332614 | 5722349 | 1389735 | 4332614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7205 | 1750 | 5455 | 7205 | 1750 | 5455 | 7205 | 1750 | 5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 48572 | 151428 | 336402 | 81699 | 254703 | 336402 | 81699 | 254703 | 106091969 | 30334680 | 75757289 | 104854663 | 30034187 | 74820476 | 104854663 | 30034187 | 74820476 | 106091969 | 30334680 | 75757289 | 104854663 | 30034187 | 74820476 | 104854663 | 30034187 | 74820476 | 0 | 0 | MCNC | TRUE
NT10BIX5570122 | CCI | 2010 | Q4 | Q4 - 2010 | 21503295 | 6000000 | 15503295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 1750000 | 1020215 | 0 | 1020215 | 1433138 | 0 | 1433138 | 816370 | 456000 | 360370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 0 | 0 | 0 | 212000 | 0 | 212000 | 1539000 | 0 | 1539000 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34149665 | 10456000 | 23693665 | 1020215 | 0 | 1020215 | 1645138 | 0 | 1645138 | 34149665 | 10456000 | 23693665 | 1020215 | 0 | 1020215 | 1645138 | 0 | 1645138 | 0 | 0 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | CCI | 2011 | Q1 | Q1 - 2011 | 21503295 | 6000000 | 15503295 | 0 | 0 | 0 | 3040000 | 0 | 3040000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 1750000 | 638576 | 0 | 638576 | 712808 | 0 | 712808 | 816370 | 456000 | 360370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 779883 | 0 | 779883 | 1603338 | 0 | 1603338 | 1539000 | 0 | 1539000 | 115318 | 0 | 115318 | 191318 | 0 | 191318 | 450000 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 60438 | 60438 | 0 | 60438 | 60438 | 0 | 34149665 | 10456000 | 23693665 | 1594215 | 60438 | 1533777 | 5607902 | 60438 | 5547464 | 34149665 | 10456000 | 23693665 | 1594215 | 60438 | 1533777 | 5607902 | 60438 | 5547464 | 0 | 0 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | CCI | 2011 | Q2 | Q2 - 2011 | 21503295 | 6000000 | 15503295 | 2045000 | 1445000 | 600000 | 4950400 | 2150400 | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 1750000 | 678064 | 0 | 678064 | 1074279 | 0 | 1074279 | 816370 | 456000 | 360370 | 425000 | 425000 | 0 | 481000 | 425000 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 1249638 | 0 | 1249638 | 1823362 | 0 | 1823362 | 1539000 | 0 | 1539000 | 163002 | 0 | 163002 | 189179 | 0 | 189179 | 450000 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 1959000 | 1959000 | 0 | 2818438 | 2818438 | 0 | 34149665 | 10456000 | 23693665 | 6519704 | 3829000 | 2690704 | 11336658 | 5393838 | 5942820 | 34149665 | 10456000 | 23693665 | 6519704 | 3829000 | 2690704 | 11336658 | 5393838 | 5942820 | 0 | 0 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | CCI | 2011 | Q3 | Q3 - 2011 | 21503295 | 6000000 | 15503295 | 6198353 | 3993353 | 2205000 | 13823209 | 4105343 | 9717866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 1750000 | 858329 | 0 | 858329 | 1069018 | 0 | 1069018 | 816370 | 456000 | 360370 | 456000 | 456000 | 0 | 456000 | 456000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 1524529 | 0 | 1524529 | 2579362 | 0 | 2579362 | 1539000 | 0 | 1539000 | 191627 | 0 | 191627 | 544229 | 0 | 544229 | 450000 | 0 | 450000 | 0 | 0 | 0 | 190085 | 0 | 190085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 1541057 | 1541057 | 0 | 2913423 | 2913423 | 0 | 34149665 | 10456000 | 23693665 | 10769895 | 5990410 | 4779485 | 21575326 | 7474766 | 14100560 | 34149665 | 10456000 | 23693665 | 10769895 | 5990410 | 4779485 | 21575326 | 7474766 | 14100560 | 0 | 0 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | CCI | 2011 | Q4 | Q4 - 2011 | 21503295 | 6000000 | 15503295 | 10292030 | 4063354 | 6228676 | 15425037 | 4105343 | 11319694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 1750000 | 1050738 | 0 | 1050738 | 1168833 | 0 | 1168833 | 816370 | 456000 | 360370 | 456000 | 456000 | 0 | 816370 | 456000 | 360370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 1758948 | 0 | 1758948 | 2804361 | 0 | 2804361 | 1539000 | 0 | 1539000 | 278277 | 0 | 278277 | 899279 | 0 | 899279 | 450000 | 0 | 450000 | 0 | 0 | 0 | 315810 | 0 | 315810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 2913423 | 2913423 | 0 | 4000000 | 4000000 | 0 | 34149665 | 10456000 | 23693665 | 16749416 | 7432777 | 9316639 | 25429690 | 8561343 | 16868347 | 34149665 | 10456000 | 23693665 | 16749416 | 7432777 | 9316639 | 25429690 | 8561343 | 16868347 | 0 | 0 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | CCI | 2012 | Q1 | Q1 - 2012 | 18632393 | 5662097 | 12970296 | 11638300 | 3337165 | 8301135 | 14070359 | 3379154 | 10691205 | 3259189 | 726190 | 2532999 | 1040285 | 726189 | 314096 | 1988845 | 726189 | 1262656 | 1750000 | 0 | 1750000 | 1163268 | 0 | 1163268 | 1333068 | 0 | 1333068 | 816370 | 456000 | 360370 | 456000 | 456000 | 0 | 456000 | 456000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 2257743 | 0 | 2257743 | 2789794 | 0 | 2789794 | 1539000 | 0 | 1539000 | 431515 | 0 | 431515 | 902623 | 0 | 902623 | 450000 | 0 | 450000 | 0 | 0 | 0 | 276870 | 0 | 276870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3611713 | 3611713 | 0 | 2913423 | 2913423 | 0 | 3266765 | 3266765 | 0 | 34149665 | 10456000 | 23693665 | 19900534 | 7432777 | 12467757 | 25084324 | 7828108 | 17256216 | 34149665 | 10456000 | 23693665 | 19900534 | 7432777 | 12467757 | 25084324 | 7828108 | 17256216 | 0 | 0 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | CCI | 2012 | Q2 | Q2 - 2012 | 18632393 | 5662097 | 12970296 | 11089046 | 1720000 | 9369046 | 11089046 | 1720000 | 9369046 | 3259189 | 726190 | 2532999 | 726189 | 726189 | 0 | 1373980 | 1373980 | 0 | 1750000 | 0 | 1750000 | 1256804 | 0 | 1256804 | 1389833 | 0 | 1389833 | 816370 | 456000 | 360370 | 4307637 | 4307637 | 0 | 5495637 | 5495637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 2547034 | 0 | 2547034 | 3011421 | 0 | 3011421 | 1539000 | 0 | 1539000 | 589981 | 0 | 589981 | 906040 | 0 | 906040 | 450000 | 0 | 450000 | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3611713 | 3611713 | 0 | 421782 | 421782 | 0 | 421782 | 421782 | 0 | 34149665 | 10456000 | 23693665 | 20938473 | 7175608 | 13762865 | 23726739 | 9011399 | 14715340 | 34149665 | 10456000 | 23693665 | 20938473 | 7175608 | 13762865 | 23726739 | 9011399 | 14715340 | 0 | 9998 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | CCI | 2012 | Q3 | Q3 - 2012 | 17127343 | 4157048 | 12970295 | 9450660 | 0 | 9450660 | 9840799 | 337415 | 9503384 | 4375952 | 1842952 | 2533000 | 0 | 0 | 0 | 752530 | 752530 | 0 | 1750000 | 0 | 1750000 | 1344387 | 0 | 1344387 | 1607672 | 0 | 1607672 | 816370 | 456000 | 360370 | 4307637 | 3586800 | 0 | 6497315 | 6497315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 2814206 | 0 | 2814206 | 3325105 | 0 | 3325105 | 1539000 | 0 | 1539000 | 638345 | 0 | 638345 | 1022784 | 0 | 1022784 | 450000 | 0 | 450000 | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 421782 | 0 | 0 | 594707 | 594707 | 0 | 34149665 | 10456000 | 23693665 | 18977017 | 3586800 | 14247598 | 23679912 | 8181967 | 15497945 | 34149665 | 10456000 | 23693665 | 18977017 | 3586800 | 14247598 | 23679912 | 8181967 | 15497945 | 0 | 0 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | CCI | 2012 | Q4 | Q4 - 2012 | 17127343 | 4157048 | 12970295 | 10250482 | 0 | 10250482 | 10818568 | 0 | 10818568 | 4375952 | 1842952 | 2533000 | 0 | 0 | 0 | 1834586 | 0 | 1834586 | 1750000 | 0 | 1750000 | 1612448 | 0 | 1612448 | 1826950 | 0 | 1826950 | 816370 | 456000 | 360370 | 3586800 | 3586800 | 0 | 4900000 | 4900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 2883374 | 0 | 2883374 | 3487187 | 0 | 3487187 | 1539000 | 0 | 1539000 | 1068267 | 0 | 1068267 | 1687716 | 0 | 1687716 | 450000 | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 3589608 | 3589608 | 0 | 3589608 | 3589608 | 0 | 34149665 | 10456000 | 23693665 | 22990979 | 7176408 | 15814571 | 28144615 | 8489608 | 19655007 | 34149665 | 10456000 | 23693665 | 22990979 | 7176408 | 15814571 | 28144615 | 8489608 | 19655007 | 0 | 0 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | CCI | 2013 | Q1 | Q1 - 2013 | 17127343 | 4157048 | 12970295 | 10275510 | 0 | 10275510 | 10693063 | 0 | 10693063 | 4375952 | 1842952 | 2533000 | 0 | 0 | 0 | 1622639 | 0 | 1622639 | 1750000 | 0 | 1750000 | 1726371 | 0 | 1726371 | 2221949 | 0 | 2221948 | 816370 | 456000 | 360370 | 3586800 | 3586800 | 0 | 3586800 | 3586800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 2883374 | 0 | 2883374 | 3068074 | 0 | 3068074 | 1539000 | 0 | 1539000 | 1726546 | 0 | 1726546 | 2550000 | 0 | 2550000 | 450000 | 0 | 450000 | 0 | 0 | 0 | 83997 | 0 | 83997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 3588808 | 3588808 | 0 | 3791036 | 3588808 | 202228 | 34149665 | 10456000 | 23693665 | 23787409 | 7175608 | 16611801 | 27617558 | 7175608 | 20441949 | 34149665 | 10456000 | 23693665 | 23787409 | 7175608 | 16611801 | 27617558 | 7175608 | 20441949 | 0 | 9998 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | CCI | 2013 | Q2 | Q2 - 2013 | 17127343 | 4157048 | 12970295 | 10631598 | 0 | 10631598 | 10693063 | 0 | 10693063 | 4375952 | 1842952 | 2533000 | 56160 | 0 | 56160 | 1622639 | 0 | 1622639 | 1750000 | 0 | 1750000 | 2133085 | 0 | 2133085 | 2221948 | 0 | 2221948 | 816370 | 456000 | 360370 | 3586800 | 3586800 | 0 | 3586800 | 3586800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4091000 | 0 | 4091000 | 2883374 | 0 | 2883374 | 3068074 | 0 | 3068074 | 1539000 | 0 | 1539000 | 2560667 | 0 | 2560667 | 2550667 | 0 | 2550667 | 450000 | 0 | 450000 | 0 | 0 | 0 | 83997 | 0 | 83997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 4000000 | 0 | 3588808 | 3588808 | 0 | 5636036 | 5433808 | 202228 | 34149665 | 10456000 | 23693665 | 25440492 | 7175608 | 18264884 | 29463224 | 9020608 | 20442616 | 34149665 | 10456000 | 23693665 | 25440492 | 7175608 | 18264884 | 29463224 | 9020608 | 20442616 | 0 | 9998 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | CCI | 2013 | Q3 | Q3 - 2013 | 20145569 | 8960000 | 11185569 | 18032569 | 7175608 | 10856961 | 20145569 | 8960000 | 11185569 | 4762182 | 1221000 | 3541182 | 401698 | 0 | 401698 | 4762182 | 1221000 | 3541182 | 3853561 | 275000 | 3578561 | 2505967 | 0 | 2505967 | 3853561 | 275000 | 3578561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3058759 | 0 | 3058759 | 2916958 | 0 | 2916958 | 3058759 | 0 | 3058759 | 2224594 | 0 | 2224594 | 2996931 | 0 | 2996931 | 2224594 | 0 | 2224594 | 105000 | 0 | 105000 | 11400 | 0 | 11400 | 105000 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34149665 | 10456000 | 23693665 | 26865523 | 7175608 | 19689915 | 34149665 | 10456000 | 23693665 | 34149665 | 10456000 | 23693665 | 26865523 | 7175608 | 19689915 | 34149665 | 10456000 | 23693665 | 0 | 0 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570122 | CCI | 2013 | Q4 | Q4 - 2013 | 20145569 | 8960000 | 11185569 | 18221364 | 7175608 | 11045756 | 20145569 | 8960000 | 11185569 | 4762182 | 1221000 | 3541182 | 1797652 | 0 | 1797652 | 4424593 | 1221000 | 3203593 | 3853561 | 275000 | 3578561 | 2708697 | 0 | 2708697 | 3183697 | 275000 | 2908697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3058759 | 0 | 3058759 | 3224598 | 0 | 3224598 | 3224598 | 0 | 3224598 | 2224594 | 0 | 2224594 | 3066208 | 0 | 3066208 | 3066208 | 0 | 3066208 | 105000 | 0 | 105000 | 47923 | 0 | 47923 | 105000 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34149665 | 10456000 | 23693665 | 29066442 | 7175608 | 21890834 | 34149665 | 10456000 | 23693665 | 34149665 | 10456000 | 23693665 | 29066442 | 7175608 | 21890834 | 34149665 | 10456000 | 23693665 | 0 | 0 | Florida Rural Broadband Alliance, LLC | TRUE
NT10BIX5570123 | CCI | 2010 | Q4 | Q4 - 2010 | 680684 | 28300 | 652384 | 0 | 0 | 0 | 60000 | 0 | 60000 | 453000 | 0 | 453000 | 0 | 0 | 0 | 0 | 0 | 0 | 440022 | 257377 | 182645 | 8184 | 4733 | 3451 | 22259 | 9433 | 12826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 0 | 0 | 0 | 3510 | 0 | 3510 | 229750 | 0 | 229750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 51143 | 51143 | 0 | 51000 | 51000 | 0 | 2282589 | 713480 | 1569109 | 59327 | 55876 | 3451 | 136769 | 60433 | 76336 | 2282589 | 713480 | 1569109 | 59327 | 55876 | 3451 | 136769 | 60433 | 76336 | 0 | 0 | Nez Perce Tribe | TRUE
NT10BIX5570123 | CCI | 2011 | Q1 | Q1 - 2011 | 680684 | 28300 | 652384 | 58962 | 0 | 58962 | 58548 | 0 | 58548 | 453000 | 0 | 453000 | 0 | 0 | 0 | 60000 | 0 | 60000 | 440022 | 257377 | 182645 | 22203 | 7533 | 14670 | 31575 | 12033 | 43608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 0 | 0 | 0 | 3510 | 0 | 3510 | 229750 | 0 | 229750 | 0 | 0 | 0 | 212950 | 0 | 212950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 106690 | 106690 | 0 | 50815 | 50815 | 0 | 2282589 | 713480 | 1569109 | 187855 | 114223 | 73632 | 417398 | 62848 | 378616 | 2282589 | 713480 | 1569109 | 187855 | 114223 | 73632 | 417398 | 62848 | 378616 | 0 | 0 | Nez Perce Tribe | TRUE
NT10BIX5570123 | CCI | 2011 | Q2 | Q2 - 2011 | 680688 | 28300 | 652388 | 58962 | 0 | 58962 | 242487 | 0 | 242487 | 731555 | 85953 | 645602 | 25139 | 15116 | 10023 | 177483 | 19365 | 158118 | 238263 | 171424 | 66839 | 18099 | 5689 | 12410 | 26853 | 8797 | 18056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 0 | 0 | 0 | 3612 | 0 | 3612 | 152950 | 0 | 152950 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 93418 | 93418 | 0 | 153418 | 129678 | 23740 | 2282589 | 713480 | 1569109 | 195618 | 114223 | 81395 | 703853 | 157840 | 546013 | 2282589 | 713480 | 1569109 | 195618 | 114223 | 81395 | 703853 | 157840 | 546013 | 0 | 0 | Nez Perce Tribe | TRUE
NT10BIX5570123 | CCI | 2011 | Q3 | Q3 - 2011 | 680688 | 28300 | 652388 | 293905 | 0 | 293905 | 420536 | 70536 | 321700 | 731555 | 85953 | 645602 | 58129 | 25449 | 32680 | 615499 | 35799 | 579700 | 238263 | 171424 | 66839 | 60227 | 9961 | 50266 | 78500 | 11661 | 66839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 0 | 0 | 0 | 3510 | 0 | 3510 | 152950 | 0 | 152950 | 65596 | 0 | 65596 | 152950 | 0 | 152950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 150897 | 150897 | 0 | 185639 | 163900 | 21739 | 2282589 | 713480 | 1569109 | 628754 | 186307 | 442447 | 1456634 | 281896 | 1146438 | 2282589 | 713480 | 1569109 | 628754 | 186307 | 442447 | 1456634 | 281896 | 1146438 | 0 | 0 | Nez Perce Tribe | TRUE
NT10BIX5570123 | CCI | 2011 | Q4 | Q4 - 2011 | 680688 | 28300 | 652388 | 356788 | 24635 | 332153 | 442843 | 53189 | 389634 | 731555 | 85953 | 645602 | 572147 | 34646 | 537501 | 686147 | 43646 | 642501 | 238263 | 171424 | 66839 | 95117 | 24606 | 70511 | 117317 | 34806 | 82511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 3612 | 0 | 3612 | 8650 | 0 | 8650 | 152950 | 0 | 152950 | 79748 | 0 | 79748 | 113414 | 0 | 113414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 222017 | 188429 | 33588 | 267017 | 223429 | 43588 | 2282589 | 713480 | 1569109 | 1329429 | 272316 | 1057113 | 1635388 | 355070 | 1280298 | 2282589 | 713480 | 1569109 | 1329429 | 272316 | 1057113 | 1635388 | 355070 | 1280298 | 0 | 0 | Nez Perce Tribe | TRUE
NT10BIX5570123 | CCI | 2012 | Q1 | Q1 - 2012 | 680688 | 28300 | 652388 | 468544 | 47189 | 421355 | 478544 | 47189 | 431355 | 731555 | 85953 | 645602 | 753919 | 35625 | 718294 | 833803 | 55625 | 778178 | 238263 | 171424 | 66839 | 117249 | 37229 | 80020 | 152368 | 61948 | 90420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 5037 | 0 | 5037 | 5037 | 0 | 5037 | 152950 | 0 | 152950 | 79748 | 0 | 79748 | 144748 | 0 | 144748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 281369 | 238282 | 43087 | 331369 | 278282 | 53087 | 2282589 | 713480 | 1569109 | 1705866 | 358325 | 1347541 | 1945869 | 443044 | 1502825 | 2282589 | 713480 | 1569109 | 1705866 | 358325 | 1347541 | 1945869 | 443044 | 1502825 | 0 | 544 | Nez Perce Tribe | TRUE
NT10BIX5570123 | CCI | 2012 | Q2 | Q2 - 2012 | 680688 | 28300 | 652388 | 488567 | 47189 | 441377 | 500283 | 47189 | 453094 | 731555 | 85953 | 645602 | 811610 | 39601 | 772009 | 948707 | 59575 | 889132 | 238263 | 171424 | 66839 | 120819 | 37229 | 83590 | 152369 | 61949 | 90420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 5037 | 0 | 5037 | 5037 | 0 | 5037 | 152950 | 0 | 152950 | 79748 | 0 | 79748 | 79748 | 0 | 79748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 334643 | 292733 | 41910 | 374642 | 332732 | 41910 | 2282589 | 713480 | 1569109 | 1840424 | 416752 | 1423671 | 2060786 | 501445 | 1559341 | 2282589 | 713480 | 1569109 | 1840424 | 416752 | 1423671 | 2060786 | 501445 | 1559341 | 0 | 0 | Nez Perce Tribe | TRUE
NT10BIX5570123 | CCI | 2012 | Q3 | Q3 - 2012 | 680688 | 28300 | 652388 | 540770 | 89896 | 450874 | 540770 | 89896 | 450874 | 731555 | 85953 | 645602 | 947568 | 55102 | 892466 | 947568 | 55102 | 892466 | 238263 | 171424 | 66839 | 143364 | 53641 | 89723 | 165641 | 68641 | 97000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 5037 | 0 | 5037 | 5037 | 0 | 5037 | 152950 | 0 | 152950 | 80688 | 940 | 79748 | 80688 | 940 | 79748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 378460 | 336550 | 41910 | 478460 | 436550 | 41910 | 2282589 | 713480 | 1569109 | 2095887 | 536129 | 1559758 | 2218164 | 651129 | 1567035 | 2282589 | 713480 | 1569109 | 2095887 | 536129 | 1559758 | 2218164 | 651129 | 1567035 | 0 | 0 | Nez Perce Tribe | TRUE
NT10BIX5570123 | CCI | 2012 | Q4 | Q4 - 2012 | 680688 | 28300 | 652388 | 543285 | 89896 | 453389 | 543285 | 89896 | 453292 | 731555 | 85953 | 645602 | 936724 | 75917 | 860807 | 953371 | 95917 | 857551 | 238263 | 171424 | 66839 | 145627 | 54144 | 91483 | 186714 | 55143 | 131571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 5037 | 0 | 5037 | 5037 | 0 | 5037 | 152950 | 0 | 152950 | 80688 | 940 | 79748 | 80688 | 940 | 79748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 480496 | 438586 | 41910 | 513494 | 471584 | 41910 | 2282589 | 713480 | 1569109 | 2191857 | 659483 | 1532374 | 2282589 | 713480 | 1569109 | 2282589 | 713480 | 1569109 | 2191857 | 659483 | 1532374 | 2282589 | 713480 | 1569109 | 0 | 28730 | Nez Perce Tribe | TRUE
NT10BIX5570123 | CCI | 2013 | Q1 | Q1 - 2013 | 680688 | 28300 | 652388 | 543285 | 89896 | 453389 | 543285 | 89896 | 453389 | 731555 | 85953 | 645602 | 952015 | 87231 | 864784 | 952015 | 87231 | 864784 | 238263 | 171424 | 66839 | 150869 | 54144 | 96725 | 155369 | 54144 | 101225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 5037 | 0 | 5037 | 5037 | 0 | 5037 | 152950 | 0 | 152950 | 80688 | 940 | 79748 | 80688 | 940 | 79748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 523179 | 481269 | 41910 | 523179 | 481269 | 41910 | 2282589 | 713480 | 1569109 | 2255073 | 713480 | 1541593 | 2259573 | 713480 | 1546093 | 2282589 | 713480 | 1569109 | 2255073 | 713480 | 1541593 | 2259573 | 713480 | 1546093 | 0 | 46193 | Nez Perce Tribe | TRUE
NT10BIX5570123 | CCI | 2013 | Q2 | Q2 - 2013 | 680688 | 28300 | 652388 | 543285 | 89896 | 453389 | 543285 | 89896 | 453389 | 731555 | 85953 | 645602 | 952015 | 87231 | 864784 | 952015 | 87231 | 864784 | 238263 | 171424 | 66839 | 158178 | 54144 | 104033 | 158178 | 54144 | 104033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 5037 | 0 | 5037 | 5037 | 0 | 5037 | 152950 | 0 | 152950 | 80688 | 940 | 79748 | 80688 | 940 | 79748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 523991 | 481269 | 42722 | 523991 | 481269 | 42722 | 2282589 | 713480 | 1569109 | 2263194 | 713480 | 1549713 | 2263194 | 713480 | 1549713 | 2282589 | 713480 | 1569109 | 2263194 | 713480 | 1549713 | 2263194 | 713480 | 1549713 | 0 | 58884 | Nez Perce Tribe | TRUE
NT10BIX5570123 | CCI | 2013 | Q3 | Q3 - 2013 | 680688 | 28300 | 652388 | 543285 | 89896 | 453389 | 543285 | 89896 | 453389 | 731555 | 85953 | 645602 | 952015 | 87231 | 864784 | 952015 | 87231 | 864784 | 238263 | 171424 | 66839 | 160581 | 54144 | 106437 | 160581 | 54144 | 106437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | 3510 | 5037 | 0 | 5037 | 5037 | 0 | 5037 | 152950 | 0 | 152950 | 80688 | 940 | 79748 | 80688 | 940 | 79748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475623 | 427803 | 47820 | 523991 | 481269 | 42722 | 523991 | 481269 | 42722 | 2282589 | 713480 | 1569109 | 2265597 | 713480 | 1552117 | 2265597 | 713480 | 1552117 | 2282589 | 713480 | 1569109 | 2265597 | 713480 | 1552117 | 2265597 | 713480 | 1552117 | 0 | 58884 | Nez Perce Tribe | TRUE
NT10BIX5570125 | CCI | 2010 | Q4 | Q4 - 2010 | 639339 | 127868 | 511471 | 0 | 0 | 0 | 62431 | 0 | 62431 | 14337357 | 2867471 | 11469886 | 192933 | 0 | 192933 | 810116 | 0 | 810116 | 434100 | 86820 | 347280 | 140359 | 0 | 140359 | 214500 | 0 | 214500 | 298083 | 58617 | 234466 | 0 | 0 | 0 | 96400 | 0 | 96400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 53939 | 0 | 53939 | 279000 | 0 | 279000 | 714775 | 142955 | 571820 | 216701 | 0 | 216701 | 446750 | 0 | 446750 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 0 | 0 | 0 | 0 | 0 | 0 | 17217800 | 3442560 | 13770240 | 603932 | 0 | 603932 | 1909197 | 0 | 1909197 | 17217800 | 3442560 | 13770240 | 603932 | 0 | 603932 | 1909197 | 0 | 1909197 | 0 | 0 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | CCI | 2011 | Q1 | Q1 - 2011 | 639339 | 127868 | 511471 | 470 | 0 | 470 | 83212 | 0 | 83212 | 14337357 | 2867471 | 11469886 | 366794 | 0 | 366794 | 1022288 | 50000 | 972288 | 434100 | 86820 | 347280 | 172903 | 0 | 172903 | 242600 | 0 | 242600 | 293083 | 58617 | 234466 | 0 | 0 | 0 | 137800 | 0 | 137800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 213908 | 0 | 213908 | 430000 | 0 | 430000 | 714775 | 142955 | 571820 | 419706 | 0 | 419706 | 480250 | 0 | 480250 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 0 | 0 | 0 | 0 | 0 | 0 | 17212800 | 3442560 | 13770240 | 1173781 | 0 | 1173781 | 2396150 | 50000 | 2346150 | 17212800 | 3442560 | 13770240 | 1173781 | 0 | 1173781 | 2396150 | 50000 | 2346150 | 0 | 0 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | CCI | 2011 | Q2 | Q2 - 2011 | 639339 | 127868 | 511471 | 917 | 0 | 917 | 87312 | 0 | 87312 | 14337357 | 2867471 | 11469886 | 575623 | 0 | 575623 | 4474920 | 420000 | 4054920 | 434100 | 86820 | 347280 | 192378 | 0 | 192378 | 309200 | 0 | 309200 | 293083 | 58617 | 234466 | 0 | 0 | 0 | 267283 | 80000 | 187283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 381692 | 0 | 381692 | 489400 | 100000 | 389400 | 714775 | 142955 | 571820 | 549995 | 0 | 549995 | 563250 | 0 | 563250 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 9120 | 0 | 9120 | 45475 | 9095 | 36380 | 0 | 0 | 0 | 45475 | 0 | 45475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 0 | 0 | 0 | 28924 | 0 | 28924 | 17212800 | 3442560 | 13770240 | 1700605 | 0 | 1700605 | 6274884 | 600000 | 5674884 | 17212800 | 3442560 | 13770240 | 1700605 | 0 | 1700605 | 6274884 | 600000 | 5674884 | 0 | 0 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | CCI | 2011 | Q3 | Q3 - 2011 | 639339 | 127868 | 511471 | 917 | 0 | 917 | 16917 | 0 | 16917 | 14337357 | 2867471 | 11469886 | 1054861 | 34453 | 1020408 | 2558704 | 385000 | 2173704 | 434100 | 86820 | 347280 | 231043 | 11592 | 219450 | 283290 | 0 | 283290 | 293083 | 58617 | 234466 | 18271 | 0 | 18271 | 18271 | 0 | 18271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 487893 | 2097 | 485795 | 513893 | 250000 | 263893 | 714775 | 142955 | 571820 | 555063 | 0 | 555063 | 575063 | 0 | 575063 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 8801 | 0 | 8801 | 8801 | 0 | 8801 | 17212800 | 3442560 | 13770240 | 2356849 | 48142 | 2308705 | 3974939 | 635000 | 3339939 | 17212800 | 3442560 | 13770240 | 2356849 | 48142 | 2308705 | 3974939 | 635000 | 3339939 | 0 | 0 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | CCI | 2011 | Q4 | Q4 - 2011 | 639339 | 127868 | 511471 | 17518 | 0 | 17518 | 17667 | 0 | 17667 | 14337357 | 2867471 | 11469886 | 2385235 | 150654 | 2234581 | 3550656 | 249087 | 3301569 | 434100 | 86820 | 347280 | 299660 | 70381 | 229279 | 449705 | 90654 | 359051 | 293083 | 58617 | 234466 | 22019 | 0 | 22019 | 22550 | 0 | 22550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 568874 | 16504 | 552369 | 568874 | 16504 | 552369 | 714775 | 142955 | 571820 | 555063 | 0 | 555063 | 555063 | 0 | 555063 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 9177 | 0 | 9177 | 9177 | 0 | 9177 | 17212800 | 3442560 | 13770240 | 3857546 | 237539 | 3620006 | 5173692 | 356245 | 4817446 | 17212800 | 3442560 | 13770240 | 3857546 | 237539 | 3620006 | 5173692 | 356245 | 4817446 | 0 | 0 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | CCI | 2012 | Q1 | Q1 - 2012 | 639339 | 127868 | 511471 | 18300 | 0 | 18300 | 19300 | 0 | 19300 | 14337357 | 2867471 | 11469886 | 4083046 | 329737 | 3753309 | 7924874 | 753937 | 7170937 | 434100 | 86820 | 347280 | 448672 | 92362 | 356310 | 531972 | 167662 | 364310 | 293083 | 58617 | 234466 | 22196 | 0 | 22196 | 22727 | 0 | 22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 568874 | 16504 | 552370 | 568874 | 16504 | 552370 | 714775 | 142955 | 571820 | 591868 | 0 | 591868 | 618868 | 0 | 618868 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 0 | 0 | 0 | 45475 | 32500 | 12975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 9177 | 0 | 9177 | 9177 | 0 | 9177 | 17212800 | 3442560 | 13770240 | 5742133 | 438603 | 5303530 | 9741267 | 970603 | 8770664 | 17212800 | 3442560 | 13770240 | 5742133 | 438603 | 5303530 | 9741267 | 970603 | 8770664 | 0 | 0 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | CCI | 2012 | Q2 | Q2 - 2012 | 639339 | 127868 | 511471 | 18449 | 0 | 18449 | 431223 | 412774 | 18449 | 14337357 | 2867471 | 11469886 | 8555034 | 1254551 | 7300483 | 11595492 | 1781777 | 9813715 | 434100 | 86820 | 347280 | 560653 | 191298 | 369355 | 671652 | 302297 | 369355 | 293083 | 58617 | 234466 | 22373 | 0 | 22373 | 22904 | 0 | 22904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 568874 | 16504 | 552370 | 568874 | 16504 | 552369 | 714775 | 142955 | 571820 | 601975 | 0 | 601975 | 601975 | 0 | 601975 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 40033 | 1787 | 38246 | 48433 | 1787 | 46646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 9177 | 0 | 9177 | 9177 | 0 | 9177 | 17212800 | 3442560 | 13770240 | 10376568 | 1464140 | 8912428 | 13949730 | 2515139 | 11434590 | 17212800 | 3442560 | 13770240 | 10376568 | 1464140 | 8912428 | 13949730 | 2515139 | 11434590 | 0 | 0 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | CCI | 2012 | Q3 | Q3 - 2012 | 639339 | 127868 | 511471 | 19415 | 0 | 19415 | 2169415 | 900000 | 1269415 | 14337357 | 2867471 | 11469886 | 9318965 | 1371234 | 7947731 | 10159870 | 1371234 | 8788636 | 434100 | 86820 | 347280 | 695984 | 242721 | 453263 | 833484 | 331235 | 502249 | 293083 | 58617 | 234466 | 22373 | 0 | 22373 | 22904 | 0 | 22904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 568874 | 16504 | 552370 | 568874 | 16504 | 552370 | 714775 | 142955 | 571820 | 601975 | 0 | 601975 | 637975 | 0 | 637975 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 127380 | 1787 | 125593 | 127380 | 1787 | 125593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 9177 | 0 | 9177 | 9177 | 0 | 9177 | 17212800 | 3442560 | 13770240 | 11364143 | 1632246 | 9731897 | 14529079 | 2620760 | 11908319 | 17212800 | 3442560 | 13770240 | 11364143 | 1632246 | 9731897 | 14529079 | 2620760 | 11908319 | 0 | 0 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | CCI | 2012 | Q4 | Q4 - 2012 | 639339 | 127868 | 511471 | 1707499 | 1261368 | 446131 | 1917499 | 1261368 | 656131 | 14337357 | 2867471 | 11469886 | 9369907 | 1386234 | 7983673 | 10434007 | 1386234 | 9047773 | 434100 | 86820 | 347280 | 841084 | 242721 | 598363 | 976084 | 242721 | 733363 | 293083 | 58617 | 234466 | 530699 | 0 | 530699 | 531230 | 0 | 531230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 568874 | 16504 | 552370 | 568874 | 16504 | 552370 | 714775 | 142955 | 571820 | 601975 | 0 | 601975 | 601975 | 0 | 601975 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 127380 | 1787 | 125593 | 127380 | 1787 | 125593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 119676 | 0 | 119676 | 125676 | 0 | 125676 | 17212800 | 3442560 | 13770240 | 13867094 | 2908614 | 10958480 | 15282725 | 2908614 | 12374111 | 17212800 | 3442560 | 13770240 | 13867094 | 2908614 | 10958480 | 15282725 | 2908614 | 12374111 | 0 | 0 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | CCI | 2013 | Q1 | Q1 - 2013 | 639339 | 127868 | 511471 | 1926004 | 976633 | 949371 | 2276004 | 1316633 | 959371 | 14337357 | 2867471 | 11469886 | 9832926 | 1390622 | 8442304 | 11129526 | 1426749 | 9702777 | 434100 | 86820 | 347280 | 938707 | 242721 | 695986 | 1083707 | 277721 | 805986 | 293083 | 58617 | 234466 | 533698 | 0 | 533698 | 534229 | 0 | 534229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 568874 | 16504 | 552370 | 568874 | 16504 | 552370 | 714775 | 142955 | 571820 | 601975 | 0 | 601975 | 601975 | 0 | 601975 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 129536 | 1787 | 127749 | 129536 | 1787 | 127749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 155837 | 0 | 155837 | 161837 | 0 | 161837 | 17212800 | 3442560 | 13770240 | 14687557 | 2628267 | 12059290 | 16485688 | 3039394 | 13446294 | 17212800 | 3442560 | 13770240 | 14687557 | 2628267 | 12059290 | 16485688 | 3039394 | 13446294 | 0 | 0 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | CCI | 2013 | Q2 | Q2 - 2013 | 639339 | 127868 | 511471 | 2359863 | 1530515 | 829348 | 2429863 | 1580515 | 849348 | 14337357 | 2867471 | 11469886 | 10966618 | 1417773 | 9548845 | 11664315 | 1553605 | 10110710 | 434100 | 86820 | 347280 | 1085857 | 290149 | 795708 | 1093357 | 290149 | 803208 | 293083 | 58617 | 234466 | 534054 | 0 | 534054 | 534410 | 0 | 534410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489400 | 97880 | 391520 | 568874 | 16504 | 552370 | 568874 | 16504 | 552370 | 714775 | 142955 | 571820 | 601975 | 0 | 601975 | 601975 | 0 | 601975 | 91200 | 18240 | 72960 | 0 | 0 | 0 | 0 | 0 | 0 | 45475 | 9095 | 36380 | 129536 | 1787 | 127749 | 129536 | 1787 | 127749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168071 | 33614 | 134457 | 190470 | 0 | 190470 | 190470 | 0 | 190470 | 17212800 | 3442560 | 13770240 | 16437247 | 3256728 | 13180519 | 17212800 | 3442560 | 13770240 | 17212800 | 3442560 | 13770240 | 16437247 | 3256728 | 13180519 | 17212800 | 3442560 | 13770240 | 0 | 0 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570125 | CCI | 2013 | Q3 | Q3 - 2013 | 2771330 | 1730041 | 1041289 | 2485683 | 1600051 | 885632 | 2485683 | 1600051 | 885632 | 11217409 | 1319262 | 9898147 | 11785927 | 1525493 | 10260434 | 11785927 | 1525493 | 10260434 | 1278591 | 345692 | 932899 | 1087807 | 269028 | 818779 | 1087807 | 269028 | 818779 | 530214 | 0 | 530214 | 534144 | 0 | 534144 | 534144 | 0 | 534144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568874 | 1891 | 566983 | 568874 | 0 | 568874 | 568874 | 0 | 568874 | 555063 | 0 | 555063 | 555063 | 0 | 555063 | 555063 | 0 | 555063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291319 | 45674 | 245645 | 195302 | 47988 | 147314 | 195302 | 47988 | 147314 | 17212800 | 3442560 | 13770240 | 17212800 | 3442560 | 13770240 | 17212800 | 3442560 | 13770240 | 17212800 | 3442560 | 13770240 | 17212800 | 3442560 | 13770240 | 17212800 | 3442560 | 13770240 | 0 | 0 | Plumas Sierra Rural Electric Cooperative | TRUE
NT10BIX5570126 | CCI | 2010 | Q4 | Q4 - 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 0 | 0 | 0 | 0 | 0 | 0 | 227000 | 68100 | 158900 | 187557 | 56267 | 131290 | 211432 | 63430 | 148002 | 215963 | 64789 | 151174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 51754 | 15526 | 36228 | 582504 | 174752 | 407752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 239311 | 71793 | 167518 | 793936 | 238182 | 555754 | 66599667 | 19979910 | 46619757 | 239311 | 71793 | 167518 | 793936 | 238182 | 555754 | 0 | 0 | CVIN, LLC | TRUE
NT10BIX5570126 | CCI | 2011 | Q1 | Q1 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 11126 | 3338 | 7788 | 4556720 | 1367017 | 3189703 | 227000 | 68100 | 158900 | 196557 | 58967 | 137590 | 227000 | 68100 | 158900 | 215963 | 64789 | 151174 | 0 | 0 | 0 | 215963 | 64789 | 151174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 246317 | 73895 | 172422 | 1950000 | 585000 | 1365000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 454000 | 136200 | 317800 | 6949683 | 2084906 | 4864777 | 66599667 | 19979910 | 46619757 | 454000 | 136200 | 317800 | 6949683 | 2084906 | 4864777 | 0 | 0 | CVIN, LLC | TRUE
NT10BIX5570126 | CCI | 2011 | Q2 | Q2 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 45655 | 17401 | 28254 | 6556000 | 1966801 | 4589199 | 227000 | 68100 | 158900 | 231610 | 69484 | 162126 | 271610 | 81483 | 190127 | 215963 | 64789 | 151174 | 7348 | 2205 | 5143 | 215963 | 64789 | 151174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 1239311 | 371794 | 867517 | 1950000 | 585000 | 1365000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 1523924 | 460884 | 1063040 | 8993573 | 2698073 | 6295500 | 66599667 | 19979910 | 46619757 | 1523924 | 460884 | 1063040 | 8993573 | 2698073 | 6295500 | 0 | 0 | CVIN, LLC | TRUE
NT10BIX5570126 | CCI | 2011 | Q3 | Q3 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 147475 | 87655 | 59820 | 6556000 | 1966801 | 4589199 | 227000 | 68100 | 158900 | 294890 | 96008 | 198882 | 334890 | 100467 | 234423 | 215963 | 64789 | 151174 | 329160 | 124012 | 205148 | 500000 | 150000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 2537350 | 847277 | 1690073 | 3000000 | 900000 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 0 | 0 | 0 | 75000 | 22500 | 52500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 3308875 | 1154952 | 2153923 | 10465890 | 3139768 | 7326122 | 66599667 | 19979910 | 46619757 | 3308875 | 1154952 | 2153923 | 10465890 | 3139768 | 7326122 | 0 | 0 | CVIN, LLC | TRUE
NT10BIX5570126 | CCI | 2011 | Q4 | Q4 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 4098623 | 1229588 | 2869035 | 15000000 | 4500000 | 10500000 | 227000 | 68100 | 158900 | 348453 | 104536 | 243917 | 450000 | 135000 | 315000 | 215963 | 64789 | 151174 | 524717 | 157415 | 367302 | 800000 | 240000 | 560000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 2759232 | 827770 | 1931462 | 3000000 | 900000 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 16884 | 5065 | 11819 | 150000 | 45000 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 7747909 | 2324374 | 5423535 | 19400000 | 5820000 | 13580000 | 66599667 | 19979910 | 46619757 | 7747909 | 2324374 | 5423535 | 19400000 | 5820000 | 13580000 | 0 | 0 | CVIN, LLC | TRUE
NT10BIX5570126 | CCI | 2012 | Q1 | Q1 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 14506475 | 4351945 | 10154530 | 35000000 | 10500000 | 24500000 | 227000 | 68100 | 158900 | 460135 | 138041 | 322094 | 560000 | 168000 | 392000 | 215963 | 64789 | 151174 | 937313 | 281194 | 656119 | 1100000 | 330000 | 770000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 2983682 | 895105 | 2088577 | 3200000 | 960000 | 2240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 277061 | 83118 | 193943 | 600000 | 180000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 19164666 | 5749403 | 13415263 | 40460000 | 12138000 | 28322000 | 66599667 | 19979910 | 46619757 | 19164666 | 5749403 | 13415263 | 40460000 | 12138000 | 28322000 | 0 | 0 | CVIN, LLC | TRUE
NT10BIX5570126 | CCI | 2012 | Q2 | Q2 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 21876436 | 6562934 | 15313502 | 40000000 | 12000006 | 27999994 | 227000 | 68100 | 158900 | 546729 | 164019 | 382710 | 650000 | 195000 | 455000 | 215963 | 64789 | 151174 | 1576452 | 472936 | 1103516 | 1600000 | 480000 | 1120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 3655258 | 1096578 | 2558680 | 3800000 | 1140001 | 2659999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 818187 | 245456 | 572731 | 900000 | 270000 | 630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 28473062 | 8541923 | 19931139 | 46950000 | 14085007 | 32864993 | 66599667 | 19979910 | 46619757 | 28473062 | 8541923 | 19931139 | 46950000 | 14085007 | 32864993 | 0 | 0 | CVIN, LLC | TRUE
NT10BIX5570126 | CCI | 2012 | Q3 | Q3 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 35283757 | 10585133 | 24698624 | 49000000 | 14700007 | 34299993 | 227000 | 68100 | 158900 | 669441 | 200832 | 468609 | 750000 | 225000 | 525000 | 215963 | 64789 | 151174 | 1660760 | 498228 | 1162532 | 1700000 | 510000 | 1190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 4032865 | 1209860 | 2823005 | 4100000 | 1230001 | 2869999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 1360902 | 408271 | 952631 | 1500000 | 450000 | 1050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 43007725 | 12902324 | 30105401 | 57050000 | 17115008 | 39934992 | 66599667 | 19979910 | 46619757 | 43007725 | 12902324 | 30105401 | 57050000 | 17115008 | 39934992 | 0 | 0 | CVIN, LLC | TRUE
NT10BIX5570126 | CCI | 2012 | Q4 | Q4 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 40946710 | 12284019 | 28662691 | 55000000 | 16500009 | 38499991 | 227000 | 68100 | 158900 | 705723 | 211717 | 494006 | 750000 | 225000 | 525000 | 215963 | 64789 | 151174 | 1711516 | 513455 | 1198061 | 1740000 | 522000 | 1218000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 4223939 | 1267183 | 2956756 | 4300000 | 1290001 | 3009999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 1867257 | 560177 | 1307080 | 2000000 | 600000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 49455145 | 14836551 | 34618594 | 63790000 | 19137010 | 44652990 | 66599667 | 19979910 | 46619757 | 49455145 | 14836551 | 34618594 | 63790000 | 19137010 | 44652990 | 0 | 832484 | CVIN, LLC | TRUE
NT10BIX5570126 | CCI | 2013 | Q1 | Q1 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 44255537 | 13276668 | 30978869 | 57000000 | 17100009 | 39899991 | 227000 | 68100 | 158900 | 795133 | 238540 | 556593 | 850000 | 255000 | 595000 | 215963 | 64789 | 151174 | 1757311 | 527194 | 1230117 | 1760000 | 528000 | 1232000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 4490411 | 1347124 | 3143287 | 4500000 | 1350001 | 3149999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 2339626 | 701888 | 1637738 | 2400000 | 720000 | 1680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 53638018 | 16091414 | 37546604 | 66510000 | 19953010 | 46556990 | 66599667 | 19979910 | 46619757 | 53638018 | 16091414 | 37546604 | 66510000 | 19953010 | 46556990 | 0 | 216158 | CVIN, LLC | TRUE
NT10BIX5570126 | CCI | 2013 | Q2 | Q2 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 49895793 | 14968745 | 34927048 | 62605667 | 23001536 | 39604131 | 227000 | 68100 | 158900 | 830138 | 249042 | 581096 | 870000 | 288904 | 581096 | 215963 | 64789 | 151174 | 1868522 | 560557 | 1307965 | 1900000 | 592035 | 1307965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 4598448 | 1379535 | 3218913 | 4600000 | 1381087 | 3218913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 2725218 | 817566 | 1907652 | 3000000 | 1092348 | 1907652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 59918119 | 17975445 | 41942674 | 72975667 | 26355910 | 46619757 | 66599667 | 19979910 | 46619757 | 59918119 | 17975445 | 41942674 | 72975667 | 26355910 | 46619757 | 0 | 216158 | CVIN, LLC | TRUE
NT10BIX5570126 | CCI | 2013 | Q3 | Q3 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 59642245 | 20038114 | 39604131 | 63038836 | 23434705 | 39604131 | 227000 | 68100 | 158900 | 935669 | 354573 | 581096 | 950000 | 368904 | 581096 | 215963 | 64789 | 151174 | 1971085 | 663120 | 1307965 | 2000000 | 692035 | 1307965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 4662950 | 1444037 | 3218913 | 4700000 | 1481087 | 3218913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 3162778 | 1255126 | 1907652 | 3300000 | 1392348 | 1907652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 70374727 | 23754970 | 46619757 | 73988836 | 27369079 | 46619757 | 66599667 | 19979910 | 46619757 | 70374727 | 23754970 | 46619757 | 73988836 | 27369079 | 46619757 | 0 | 266389 | CVIN, LLC | TRUE
NT10BIX5570126 | CCI | 2013 | Q4 | Q4 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64214212 | 19264273 | 44949939 | 64763443 | 25159312 | 39604131 | 66000000 | 26395869 | 39604131 | 227000 | 68100 | 158900 | 983738 | 402642 | 581096 | 1000000 | 418904 | 581096 | 215963 | 64789 | 151174 | 1996377 | 688412 | 1307965 | 2000000 | 692035 | 1307965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212173 | 363652 | 848521 | 4906466 | 1687553 | 3218913 | 4910000 | 1691087 | 3218913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730319 | 219096 | 511223 | 3657275 | 1749623 | 1907652 | 3700000 | 1792348 | 1907652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66599667 | 19979910 | 46619757 | 76307299 | 29687542 | 46619757 | 77610000 | 30990243 | 46619757 | 66599667 | 19979910 | 46619757 | 76307299 | 29687542 | 46619757 | 77610000 | 30990243 | 46619757 | 0 | 391524 | CVIN, LLC | TRUE
NT10BIX5570127 | CCI | 2010 | Q4 | Q4 - 2010 | 2171421 | 722124 | 1449297 | 0 | 0 | 0 | 0 | 0 | 0 | 16130066 | 5010193 | 11119873 | 0 | 0 | 0 | 0 | 0 | 0 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 45000 | 45000 | 0 | 1879920 | 583926 | 1295994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 9811 | 3047 | 6764 | 317274 | 3047 | 314227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 42001 | 20285 | 21716 | 73501 | 20285 | 53216 | 1560000 | 484555 | 1075445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 96812 | 68332 | 28480 | 435775 | 68332 | 367443 | 24071690 | 7842369 | 16229321 | 96812 | 68332 | 28480 | 435775 | 68332 | 367443 | 953688 | 0 | Utopia | TRUE
NT10BIX5570127 | CCI | 2011 | Q1 | Q1 - 2011 | 2171421 | 722124 | 1449297 | 0 | 0 | 0 | 590711 | 187946 | 402765 | 16130066 | 5010193 | 11119873 | 0 | 0 | 0 | 1275109 | 396064 | 879045 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 45555 | 45172 | 383 | 1879920 | 583926 | 1295994 | 0 | 0 | 0 | 140994 | 43794 | 97200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 139809 | 3047 | 136762 | 379809 | 117973 | 261836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 83172 | 29956 | 53216 | 162172 | 75999 | 86173 | 1560000 | 484555 | 1075445 | 0 | 0 | 0 | 117000 | 36342 | 80658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 267981 | 78003 | 189978 | 2711350 | 903290 | 1808060 | 24071690 | 7842369 | 16229321 | 267981 | 78003 | 189978 | 2711350 | 903290 | 1808060 | 953688 | 0 | Utopia | TRUE
NT10BIX5570127 | CCI | 2011 | Q2 | Q2 - 2011 | 2171421 | 722124 | 1449297 | 2814 | 0 | 2814 | 608956 | 199495 | 409461 | 16130066 | 5010193 | 11119873 | 515009 | 191826 | 323183 | 2492600 | 806090 | 1686510 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 46365 | 45424 | 941 | 1879920 | 583926 | 1295994 | 0 | 0 | 0 | 140994 | 43794 | 97200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 229350 | 27374 | 201976 | 429349 | 133361 | 295988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 151393 | 87677 | 63716 | 245513 | 142006 | 103507 | 1560000 | 484555 | 1075445 | 0 | 0 | 0 | 117000 | 36342 | 80658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 943566 | 351877 | 591689 | 4080777 | 1406512 | 2674265 | 24071690 | 7842369 | 16229321 | 943566 | 351877 | 591689 | 4080777 | 1406512 | 2674265 | 953688 | 0 | Utopia | TRUE
NT10BIX5570127 | CCI | 2011 | Q3 | Q3 - 2011 | 2171421 | 722124 | 1449297 | 9595 | 0 | 9595 | 651427 | 216638 | 434789 | 16130066 | 5010193 | 11119873 | 1218372 | 325773 | 892599 | 4032517 | 1252549 | 2779968 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 46500 | 45466 | 1034 | 1879920 | 583926 | 1295994 | 81808 | 0 | 81808 | 187992 | 58393 | 129599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 348177 | 39124 | 309053 | 910019 | 282663 | 627356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 232473 | 168757 | 63716 | 337920 | 193204 | 144716 | 1560000 | 484555 | 1075445 | 31251 | 31251 | 0 | 312000 | 96911 | 215089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 1966676 | 609905 | 1356771 | 6478375 | 2145824 | 4332551 | 24071690 | 7842369 | 16229321 | 1966676 | 609905 | 1356771 | 6478375 | 2145824 | 4332551 | 953688 | 4310 | Utopia | TRUE
NT10BIX5570127 | CCI | 2011 | Q4 | Q4 - 2011 | 2171421 | 722124 | 1449297 | 352689 | 22879 | 329810 | 1194281 | 397168 | 797113 | 16130066 | 5010193 | 11119873 | 1947127 | 592394 | 1354733 | 6290725 | 1953975 | 4336750 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 47250 | 47250 | 0 | 1879920 | 583926 | 1295994 | 225910 | 38923 | 186987 | 520593 | 161703 | 358890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 482684 | 83396 | 399288 | 970686 | 301507 | 669179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 289048 | 225333 | 63715 | 528000 | 301881 | 226119 | 1560000 | 484555 | 1075445 | 129608 | 114367 | 15241 | 624000 | 193822 | 430178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 3472066 | 1122292 | 2349774 | 10175535 | 3357306 | 6818229 | 24071690 | 7842369 | 16229321 | 3472066 | 1122292 | 2349774 | 10175535 | 3357306 | 6818229 | 953688 | 4840 | Utopia | TRUE
NT10BIX5570127 | CCI | 2012 | Q1 | Q1 - 2012 | 2171421 | 722124 | 1449297 | 441388 | 111578 | 329810 | 767101 | 219897 | 547204 | 16130066 | 5010193 | 11119873 | 4270415 | 1465912 | 2804503 | 8302931 | 2268460 | 6034471 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 47250 | 47250 | 0 | 1879920 | 583926 | 1295994 | 445082 | 102770 | 342312 | 968708 | 223676 | 745032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 758864 | 195557 | 563307 | 1037937 | 282240 | 755697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 419464 | 349388 | 70076 | 525064 | 409764 | 115300 | 1560000 | 484555 | 1075445 | 269778 | 227421 | 42357 | 790066 | 666020 | 124046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 6649991 | 2497626 | 4152365 | 12439057 | 4117307 | 8321750 | 24071690 | 7842369 | 16229321 | 6649991 | 2497626 | 4152365 | 12439057 | 4117307 | 8321750 | 953688 | 9070 | Utopia | TRUE
NT10BIX5570127 | CCI | 2012 | Q2 | Q2 - 2012 | 2171421 | 722124 | 1449297 | 592986 | 242188 | 350798 | 1135842 | 422719 | 713123 | 16130066 | 5010193 | 11119873 | 7044078 | 2421190 | 4622888 | 11076594 | 3223738 | 7852856 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 47250 | 47250 | 0 | 1879920 | 583926 | 1295994 | 728958 | 102770 | 626188 | 1231687 | 173645 | 1058042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 968569 | 261698 | 706871 | 1211240 | 337075 | 874165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 546458 | 441302 | 105155 | 652058 | 501678 | 150380 | 1560000 | 484555 | 1075445 | 270988 | 227421 | 43567 | 794900 | 667102 | 127798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 10197037 | 3741569 | 6455467 | 16149571 | 5373207 | 10776364 | 24071690 | 7842369 | 16229321 | 10197037 | 3741569 | 6455467 | 16149571 | 5373207 | 10776364 | 953688 | 10616 | Utopia | TRUE
NT10BIX5570127 | CCI | 2012 | Q3 | Q3 - 2012 | 2171421 | 722124 | 1449297 | 834387 | 483588 | 350799 | 1122456 | 505105 | 617351 | 16130066 | 5010193 | 11119873 | 8279660 | 2508882 | 5770778 | 11160598 | 3571391 | 7589207 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 47250 | 47250 | 0 | 1879920 | 583926 | 1295994 | 728958 | 102770 | 626188 | 887042 | 177409 | 709633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 1060795 | 264678 | 796117 | 1177346 | 329657 | 847689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 668930 | 306292 | 362638 | 791402 | 316561 | 474841 | 1560000 | 484555 | 1075445 | 371177 | 227421 | 143756 | 967682 | 483841 | 483841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 11988907 | 3938631 | 8050276 | 16153776 | 5431214 | 10722562 | 24071690 | 7842369 | 16229321 | 11988907 | 3938631 | 8050276 | 16153776 | 5431214 | 10722562 | 953688 | 15374 | Utopia | TRUE
NT10BIX5570127 | CCI | 2012 | Q4 | Q4 - 2012 | 2171421 | 722124 | 1449297 | 993708 | 572485 | 421223 | 1168708 | 525920 | 642789 | 16130066 | 5010193 | 11119873 | 10556262 | 3131486 | 7424776 | 12832864 | 4106516 | 8726348 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 55000 | 55000 | 0 | 1879920 | 583926 | 1295994 | 1026887 | 254612 | 772275 | 1196887 | 239377 | 957509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 1157045 | 307836 | 849209 | 1207045 | 337973 | 869072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 774929 | 389411 | 385518 | 880928 | 449273 | 431655 | 1560000 | 484555 | 1075445 | 487436 | 293350 | 194086 | 967682 | 464487 | 503195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 15041267 | 4994180 | 10047087 | 18309114 | 6178546 | 12130568 | 24071690 | 7842369 | 16229321 | 15041267 | 4994180 | 10047087 | 18309114 | 6178546 | 12130568 | 953688 | 28896 | Utopia | TRUE
NT10BIX5570127 | CCI | 2013 | Q1 | Q1 - 2013 | 2171421 | 722124 | 1449297 | 1005685 | 572484 | 433201 | 1155685 | 520058 | 635627 | 16130066 | 5010193 | 11119873 | 12658029 | 3630936 | 9027093 | 14759796 | 4575537 | 10184259 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 55000 | 55000 | 0 | 1879920 | 583926 | 1295994 | 1112103 | 338917 | 773186 | 1503936 | 451181 | 1052755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 1261560 | 359012 | 902548 | 1321560 | 370037 | 951523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 827251 | 426223 | 401028 | 879572 | 448582 | 430990 | 1560000 | 484555 | 1075445 | 607847 | 312219 | 295628 | 967682 | 464487 | 503195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 17517475 | 5684791 | 11832684 | 20643231 | 6884882 | 13758349 | 24071690 | 7842369 | 16229321 | 17517475 | 5684791 | 11832684 | 20643231 | 6884882 | 13758349 | 953688 | 44902 | Utopia | TRUE
NT10BIX5570127 | CCI | 2013 | Q2 | Q2 - 2013 | 2171421 | 722124 | 1449297 | 1317925 | 572484 | 745441 | 2000000 | 760000 | 1240000 | 16130066 | 5010193 | 11119873 | 14649501 | 4372355 | 10277146 | 15800000 | 4740000 | 11060000 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 60925 | 60925 | 0 | 1879920 | 583926 | 1295994 | 1514048 | 480586 | 1033462 | 1800000 | 522000 | 1278000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 1351819 | 385950 | 965869 | 1380000 | 386400 | 993600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 977725 | 543217 | 434508 | 1050000 | 588000 | 462000 | 1560000 | 484555 | 1075445 | 712268 | 333902 | 378366 | 1000000 | 480000 | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 20568286 | 6733494 | 13834792 | 23090925 | 7537325 | 15553600 | 24071690 | 7842369 | 16229321 | 20568286 | 6733494 | 13834792 | 23090925 | 7537325 | 15553600 | 953688 | 62050 | Utopia | TRUE
NT10BIX5570127 | CCI | 2013 | Q3 | Q3 - 2013 | 2171421 | 722124 | 1449297 | 1448238 | 593965 | 854273 | 1448238 | 593965 | 854273 | 16130066 | 5010193 | 11119873 | 16707719 | 4839201 | 11868518 | 16707719 | 4839201 | 11868518 | 60925 | 60925 | 0 | 45000 | 45000 | 0 | 45000 | 45000 | 0 | 1879920 | 583926 | 1295994 | 1711450 | 580274 | 1131176 | 1711450 | 580274 | 1131176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1213358 | 376884 | 836474 | 1440762 | 399656 | 1041106 | 1440762 | 399656 | 1041106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000 | 603762 | 452238 | 1070465 | 597993 | 472472 | 1070465 | 597993 | 472472 | 1560000 | 484555 | 1075445 | 956387 | 476504 | 479883 | 956387 | 476504 | 479883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24071690 | 7842369 | 16229321 | 23380021 | 7532593 | 15847428 | 23380021 | 7532593 | 15847428 | 24071690 | 7842369 | 16229321 | 23380021 | 7532593 | 15847428 | 23380021 | 7532593 | 15847428 | 953688 | 82218 | Utopia | TRUE
NT10BIX5570128 | CCI | 2010 | Q4 | Q4 - 2010 | 1137016 | 228158 | 908858 | 0 | 0 | 0 | 481041 | 96528 | 384513 | 16923915 | 3396017 | 13527898 | 0 | 0 | 0 | 3033645 | 608743 | 2424902 | 1770811 | 355337 | 1415474 | 389869 | 78233 | 311636 | 467950 | 93901 | 374049 | 1394639 | 279853 | 1114786 | 1700 | 341 | 1359 | 693713 | 139204 | 554509 | 21600 | 4333 | 17267 | 0 | 0 | 0 | 7200 | 1440 | 5760 | 847460 | 170055 | 677405 | 41680 | 8364 | 33316 | 629103 | 126239 | 502864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 0 | 0 | 0 | 19250 | 3863 | 15387 | 10411565 | 2089224 | 8322341 | 0 | 0 | 0 | 1993520 | 400028 | 1593492 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 13700 | 2750 | 10950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 433249 | 86938 | 346311 | 7339122 | 1472696 | 5866426 | 32612412 | 6544128 | 26068284 | 433249 | 86938 | 346311 | 7339122 | 1472696 | 5866426 | 0 | 0 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | CCI | 2011 | Q1 | Q1 - 2011 | 1137016 | 228158 | 908858 | 14333 | 2875 | 11457 | 220175 | 44181 | 175994 | 16923915 | 3396017 | 13527898 | 0 | 0 | 0 | 1100000 | 220730 | 879270 | 1770811 | 355337 | 1415474 | 505179 | 103514 | 401665 | 589624 | 118318 | 471308 | 1394639 | 279853 | 1114786 | 1700 | 342 | 1359 | 157400 | 31584 | 125816 | 21600 | 4333 | 17267 | 0 | 0 | 0 | 10000 | 2007 | 7993 | 847460 | 170055 | 677405 | 60292 | 12099 | 48193 | 314276 | 63064 | 251212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 0 | 0 | 0 | 9751 | 1957 | 7794 | 10411565 | 2089224 | 8322341 | 701 | 141 | 560 | 1000000 | 200664 | 799336 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 5000 | 1003 | 3997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 582205 | 118971 | 463234 | 3406226 | 683508 | 2722720 | 32612412 | 6544128 | 26068284 | 582205 | 118971 | 463234 | 3406226 | 683508 | 2722720 | 0 | 0 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | CCI | 2011 | Q2 | Q2 - 2011 | 1137016 | 228158 | 908858 | 84344 | 16925 | 67419 | 284254 | 57040 | 227214 | 16923915 | 3396017 | 13527898 | 1108103 | 224693 | 883410 | 4230979 | 849004 | 3381975 | 1770811 | 355337 | 1415474 | 664715 | 133384 | 531331 | 815700 | 163681 | 652019 | 1394639 | 279853 | 1114786 | 6721 | 1349 | 5372 | 348660 | 69963 | 278697 | 21600 | 4333 | 17267 | 0 | 0 | 0 | 5400 | 1084 | 4316 | 847460 | 170055 | 677405 | 344523 | 69133 | 275390 | 404523 | 81173 | 323350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 0 | 0 | 0 | 7800 | 1565 | 6235 | 10411565 | 2089224 | 8322341 | 741613 | 148815 | 592798 | 2602891 | 522306 | 2080585 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 2950019 | 594299 | 2355720 | 8700207 | 1745816 | 6954391 | 32612412 | 6544128 | 26068284 | 2950019 | 594299 | 2355720 | 8700207 | 1745816 | 6954391 | 0 | 0 | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | CCI | 2011 | Q3 | Q3 - 2011 | 1137016 | 228158 | 908858 | 424654 | 85213 | 339441 | 764964 | 153501 | 611463 | 16923915 | 3396017 | 13527898 | 2334063 | 468362 | 1865701 | 3545439 | 711441 | 2833998 | 1770811 | 355337 | 1415474 | 799758 | 160482 | 639276 | 934801 | 187581 | 747220 | 1394639 | 279853 | 1114786 | 258162 | 51804 | 206358 | 509603 | 102259 | 407344 | 21600 | 4333 | 17267 | 5102 | 1024 | 4078 | 10204 | 2048 | 8156 | 847460 | 170055 | 677405 | 388172 | 77892 | 310280 | 431821 | 86651 | 345170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 14831 | 2976 | 11855 | 29662 | 5952 | 23710 | 10411565 | 2089224 | 8322341 | 1642246 | 329539 | 1312707 | 2542879 | 510264 | 2032615 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 5866988 | 1177292 | 4689696 | 8769373 | 1759697 | 7009676 | 32612412 | 6544128 | 26068284 | 5866988 | 1177292 | 4689696 | 8769373 | 1759697 | 7009676 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | CCI | 2011 | Q4 | Q4 - 2011 | 1137016 | 228158 | 908858 | 564541 | 113283 | 451258 | 833903 | 167334 | 666569 | 16923915 | 3396017 | 13527898 | 4455242 | 894006 | 3561236 | 6593758 | 1323129 | 5270629 | 1770811 | 355337 | 1415474 | 913040 | 183214 | 729826 | 1026257 | 205933 | 820324 | 1394639 | 279853 | 1114786 | 276606 | 55505 | 221101 | 301456 | 60491 | 240965 | 21600 | 4333 | 17267 | 5176 | 1039 | 4137 | 5280 | 1060 | 4220 | 847460 | 170055 | 677405 | 501506 | 100634 | 400872 | 614846 | 123377 | 491469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 31359 | 6293 | 25066 | 47040 | 9439 | 37601 | 10411565 | 2089224 | 8322341 | 3956580 | 793942 | 3162638 | 6330528 | 1270308 | 5060220 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 10704050 | 2147916 | 8556134 | 15753068 | 3161071 | 12591997 | 32612412 | 6544128 | 26068284 | 10704050 | 2147916 | 8556134 | 15753068 | 3161071 | 12591997 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | CCI | 2012 | Q1 | Q1 - 2012 | 1137016 | 228158 | 908858 | 866000 | 173775 | 692225 | 1046055 | 209906 | 836149 | 16923915 | 3396017 | 13527898 | 6129040 | 1229988 | 4899052 | 7802838 | 1565747 | 6237091 | 1770811 | 355337 | 1415474 | 946569 | 189942 | 756627 | 984432 | 197540 | 786892 | 1394639 | 279853 | 1114786 | 531686 | 106690 | 424996 | 786766 | 157875 | 628891 | 21600 | 4333 | 17267 | 8896 | 1785 | 7111 | 12616 | 2532 | 10084 | 847460 | 170055 | 677405 | 596126 | 119621 | 476505 | 690747 | 138608 | 552139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 35285 | 7080 | 28205 | 39211 | 7868 | 31343 | 10411565 | 2089224 | 8322341 | 5999836 | 1203950 | 4795886 | 8893093 | 1784522 | 7108571 | 27400 | 5498 | 21902 | 1300 | 261 | 1039 | 1300 | 261 | 1039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 15114738 | 3033092 | 12081646 | 20257058 | 4064859 | 16192199 | 32612412 | 6544128 | 26068284 | 15114738 | 3033092 | 12081646 | 20257058 | 4064859 | 16192199 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | CCI | 2012 | Q2 | Q2 - 2012 | 1137016 | 228158 | 908858 | 1024534 | 205587 | 818947 | 1046055 | 209905 | 836149 | 16923915 | 3396017 | 13527898 | 7542650 | 1513537 | 6029112 | 8962660 | 1798481 | 7164179 | 1770811 | 355337 | 1415474 | 1044302 | 209553 | 834749 | 1086074 | 217936 | 868139 | 1394639 | 279853 | 1114786 | 776016 | 155718 | 620298 | 1020347 | 204747 | 815600 | 21600 | 4333 | 17267 | 8896 | 1785 | 7111 | 8896 | 1785 | 7111 | 847460 | 170055 | 677405 | 640609 | 128547 | 512062 | 685091 | 137473 | 547618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 72304 | 14509 | 57795 | 78006 | 15653 | 62353 | 10411565 | 2089224 | 8322341 | 7558472 | 1516712 | 6041760 | 8893093 | 1784522 | 7108571 | 27400 | 5498 | 21902 | 1300 | 261 | 1039 | 1300 | 261 | 1039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 18669083 | 3746209 | 14922873 | 21781522 | 4370763 | 17410759 | 32612412 | 6544128 | 26068284 | 18669083 | 3746209 | 14922873 | 21781522 | 4370763 | 17410759 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | CCI | 2012 | Q3 | Q3 - 2012 | 1137016 | 228158 | 908858 | 1032377 | 207161 | 825216 | 1046055 | 209905 | 836150 | 16923915 | 3396017 | 13527898 | 9105123 | 1826841 | 7278282 | 12021375 | 2412255 | 9609120 | 1770811 | 355337 | 1415474 | 1115429 | 223826 | 891603 | 1416649 | 284270 | 1132379 | 1394639 | 279853 | 1114786 | 894521 | 179498 | 715023 | 1227282 | 246271 | 981011 | 21600 | 4333 | 17267 | 8896 | 1785 | 7111 | 17792 | 3570 | 14222 | 847460 | 170055 | 677405 | 678241 | 136098 | 542143 | 745765 | 149648 | 596117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 10411565 | 2089224 | 8322341 | 8619412 | 1729604 | 6889808 | 8893093 | 1784522 | 7108571 | 27400 | 5498 | 21902 | 9480 | 1902 | 7578 | 9480 | 1902 | 7578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 21541485 | 4322368 | 17219117 | 25455497 | 5107996 | 20347501 | 32612412 | 6544128 | 26068284 | 21541485 | 4322368 | 17219117 | 25455497 | 5107996 | 20347501 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | CCI | 2012 | Q4 | Q4 - 2012 | 1137016 | 228158 | 908858 | 1049083 | 210513 | 838570 | 1129981 | 226746 | 903235 | 16923915 | 3396017 | 13527898 | 10483590 | 2103765 | 8379825 | 13059720 | 2620613 | 10439107 | 1770811 | 355337 | 1415474 | 1200320 | 240861 | 959459 | 1656713 | 332442 | 1324271 | 1394639 | 279853 | 1114786 | 908081 | 182219 | 725862 | 1297327 | 260327 | 1037001 | 21600 | 4333 | 17267 | 9721 | 1951 | 7770 | 21600 | 4334 | 17266 | 847460 | 170055 | 677405 | 719030 | 144283 | 574747 | 834617 | 167477 | 667140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 10411565 | 2089224 | 8322341 | 9063825 | 1818782 | 7245044 | 10303746 | 2067589 | 8236157 | 27400 | 5498 | 21902 | 20830 | 4180 | 16650 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 23532486 | 4722207 | 18810280 | 28409110 | 5700679 | 22708432 | 32612412 | 6544128 | 26068284 | 23532486 | 4722207 | 18810280 | 28409110 | 5700679 | 22708432 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | CCI | 2013 | Q1 | Q1 - 2013 | 1137016 | 228158 | 908858 | 1078138 | 216343 | 861795 | 1137016 | 228158 | 908857 | 16923915 | 3396017 | 13527898 | 11252104 | 2258147 | 8993957 | 13259720 | 2660746 | 10598974 | 1770811 | 355337 | 1415474 | 1261502 | 253138 | 1008364 | 1770811 | 355338 | 1415473 | 1394639 | 279853 | 1114786 | 926490 | 185913 | 740577 | 1297327 | 260327 | 1037001 | 21600 | 4333 | 17267 | 9829 | 1972 | 7857 | 21600 | 4334 | 17266 | 847460 | 170055 | 677405 | 758284 | 152160 | 606124 | 847460 | 170055 | 677405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 10411565 | 2089224 | 8322341 | 9450628 | 1896399 | 7554229 | 10303746 | 2067589 | 8236157 | 27400 | 5498 | 21902 | 20830 | 4180 | 16650 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 24835811 | 4983905 | 19851906 | 28743086 | 5767698 | 22975388 | 32612412 | 6544128 | 26068284 | 24835811 | 4983905 | 19851906 | 28743086 | 5767698 | 22975388 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | CCI | 2013 | Q2 | Q2 - 2013 | 1137016 | 228158 | 908858 | 1079997 | 218202 | 861795 | 1137016 | 228158 | 908858 | 16923915 | 3396017 | 13527898 | 12838222 | 2574935 | 10263287 | 15902492 | 3191056 | 12711437 | 1770811 | 355337 | 1415474 | 1332587 | 267402 | 1065185 | 1529788 | 306973 | 1222815 | 1394639 | 279853 | 1114786 | 934711 | 187563 | 747148 | 1394639 | 279854 | 1114785 | 21600 | 4333 | 17267 | 9829 | 1972 | 7857 | 18069 | 3626 | 14443 | 847460 | 170055 | 677405 | 798541 | 160238 | 638303 | 798542 | 160238 | 638303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 10411565 | 2089224 | 8322341 | 9899917 | 1986555 | 7913362 | 10293886 | 2065610 | 8228276 | 27400 | 5498 | 21902 | 20830 | 4180 | 16650 | 25758 | 5169 | 20589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 26992640 | 5416700 | 21575940 | 31178196 | 6256337 | 24921859 | 32612412 | 6544128 | 26068284 | 26992640 | 5416700 | 21575940 | 31178196 | 6256337 | 24921859 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | CCI | 2013 | Q3 | Q3 - 2013 | 1137016 | 228158 | 908858 | 1080096 | 216736 | 863360 | 1137016 | 228158 | 908858 | 16923915 | 3396017 | 13527898 | 14091808 | 2827970 | 11263838 | 16923915 | 3396017 | 13527898 | 1770811 | 355337 | 1415474 | 1409928 | 282922 | 1127006 | 1770811 | 355337 | 1415474 | 1394639 | 279853 | 1114786 | 934711 | 187563 | 747148 | 1394639 | 279853 | 1114786 | 21600 | 4333 | 17267 | 9829 | 1972 | 7857 | 21600 | 4333 | 17267 | 847460 | 170055 | 677405 | 812383 | 163016 | 649367 | 847460 | 170055 | 677405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 10411565 | 2089224 | 8322341 | 10194585 | 2045684 | 8148901 | 10411565 | 2089224 | 8322341 | 27400 | 5498 | 21902 | 20830 | 4180 | 16650 | 27400 | 5498 | 21902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32612412 | 6544128 | 26068284 | 28632176 | 5745696 | 22886480 | 32612412 | 6544128 | 26068284 | 32612412 | 6544128 | 26068284 | 28632176 | 5745696 | 22886480 | 32612412 | 6544128 | 26068284 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc. | TRUE
NT10BIX5570128 | CCI | 2013 | Q4 | Q4 - 2013 | 1122630 | 225271 | 897359 | 1122630 | 225271 | 897359 | 1122630 | 225271 | 897359 | 15389489 | 3088369 | 12301120 | 15389489 | 3088369 | 12301120 | 15389489 | 3088369 | 12301120 | 1611677 | 323405 | 1288272 | 1611677 | 323405 | 1288272 | 1611677 | 323405 | 1288272 | 1042711 | 209234 | 833477 | 1042711 | 209234 | 833477 | 1042711 | 209234 | 833477 | 9281 | 1862 | 7419 | 9281 | 1862 | 7419 | 9281 | 1862 | 7419 | 845276 | 169616 | 675660 | 845276 | 169616 | 675660 | 845276 | 169616 | 675660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 78006 | 15653 | 62353 | 10563288 | 2119670 | 8443618 | 10563288 | 2119670 | 8443618 | 10563288 | 2119670 | 8443618 | 26463 | 5310 | 21153 | 26463 | 5310 | 21153 | 26463 | 5310 | 21153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30688821 | 6158390 | 24530431 | 30688821 | 6158390 | 24530431 | 30688821 | 6158390 | 24530431 | 30688821 | 6158390 | 24530431 | 30688821 | 6158390 | 24530431 | 30688821 | 6158390 | 24530431 | [REDACTED] | [REDACTED] | Troy Cablevision, Inc. | TRUE
NT10BIX5570129 | CCI | 2010 | Q4 | Q4 - 2010 | 2239010 | 0 | 2239010 | 0 | 0 | 0 | 208700 | 62610 | 146090 | 2973056 | 497171 | 2475885 | 0 | 0 | 0 | 0 | 0 | 0 | 35150 | 0 | 35150 | 0 | 0 | 0 | 5000 | 1500 | 3500 | 3219000 | 2500000 | 719000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 0 | 0 | 0 | 97000 | 29100 | 67900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 0 | 0 | 0 | 15000 | 4500 | 10500 | 9990570 | 2997171 | 6993399 | 0 | 0 | 0 | 325700 | 97710 | 227990 | 9990570 | 2997171 | 6993399 | 0 | 0 | 0 | 325700 | 97710 | 227990 | 0 | 0 | Rockbridge, County of | TRUE
NT10BIX5570129 | CCI | 2011 | Q1 | Q1 - 2011 | 2239010 | 0 | 2239010 | 0 | 0 | 0 | 75000 | 22500 | 52500 | 2973056 | 497171 | 2475885 | 0 | 0 | 0 | 60000 | 18000 | 42000 | 35150 | 0 | 35150 | 1291 | 387 | 904 | 30000 | 9000 | 21000 | 3219000 | 2500000 | 719000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 52008 | 15602 | 36406 | 252173 | 75652 | 176521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 13889 | 4167 | 9721 | 16574 | 4973 | 11601 | 9990570 | 2997171 | 6993399 | 67188 | 20156 | 47031 | 433747 | 130125 | 303622 | 9990570 | 2997171 | 6993399 | 67188 | 20156 | 47031 | 433747 | 130125 | 303622 | 0 | 0 | Rockbridge, County of | TRUE
NT10BIX5570129 | CCI | 2011 | Q2 | Q2 - 2011 | 2239010 | 0 | 2239010 | 0 | 0 | 0 | 200000 | 60000 | 140000 | 2973056 | 497171 | 2475885 | 0 | 0 | 0 | 75000 | 22500 | 52500 | 35150 | 0 | 35150 | 5679 | 1704 | 3975 | 30000 | 9000 | 21000 | 3219000 | 2500000 | 719000 | 0 | 0 | 0 | 50000 | 15000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 395679 | 118704 | 276975 | 550000 | 165000 | 385000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 17822 | 5346 | 12476 | 24820 | 7446 | 17374 | 9990570 | 2997171 | 6993399 | 419180 | 125754 | 293426 | 929820 | 278946 | 650874 | 9990570 | 2997171 | 6993399 | 419180 | 125754 | 293426 | 929820 | 278946 | 650874 | 0 | 0 | Rockbridge, County of | TRUE
NT10BIX5570129 | CCI | 2011 | Q3 | Q3 - 2011 | 2239010 | 0 | 2239010 | 0 | 0 | 0 | 500000 | 150000 | 350000 | 2973056 | 497171 | 2475885 | 0 | 0 | 0 | 60000 | 18000 | 42000 | 35150 | 0 | 35150 | 5679 | 1704 | 3975 | 30000 | 9000 | 21000 | 3219000 | 2500000 | 719000 | 220224 | 66067 | 154157 | 500000 | 150000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 500522 | 150157 | 350365 | 700000 | 210000 | 490000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 17822 | 5346 | 12476 | 24820 | 7446 | 17374 | 9990570 | 2997171 | 6993399 | 744247 | 223274 | 520973 | 1814820 | 544446 | 1270374 | 9990570 | 2997171 | 6993399 | 744247 | 223274 | 520973 | 1814820 | 544446 | 1270374 | 0 | 0 | Rockbridge, County of | TRUE
NT10BIX5570129 | CCI | 2011 | Q4 | Q4 - 2011 | 2239010 | 0 | 2239010 | 0 | 0 | 0 | 641816 | 0 | 641816 | 2973056 | 497171 | 2475885 | 37925 | 31378 | 6547 | 712925 | 213877 | 499048 | 35150 | 0 | 35150 | 13935 | 0 | 13935 | 30000 | 0 | 30000 | 3219000 | 2500000 | 719000 | 307928 | 298654 | 9274 | 1344000 | 843741 | 500259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 721831 | 0 | 721831 | 771831 | 0 | 771831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 18487 | 0 | 18487 | 24820 | 0 | 24820 | 9990570 | 2997171 | 6993399 | 1100106 | 330032 | 770074 | 3525392 | 1057618 | 2467774 | 9990570 | 2997171 | 6993399 | 1100106 | 330032 | 770074 | 3525392 | 1057618 | 2467774 | 0 | 0 | Rockbridge, County of | TRUE
NT10BIX5570129 | CCI | 2012 | Q1 | Q1 - 2012 | 2239010 | 0 | 2239010 | 0 | 0 | 0 | 641816 | 0 | 641816 | 2973056 | 497171 | 2475885 | 38515 | 6440 | 32075 | 712925 | 213877 | 499048 | 35150 | 0 | 35150 | 14728 | 0 | 14728 | 20000 | 0 | 20000 | 3219000 | 2500000 | 719000 | 643535 | 438689 | 204846 | 2949750 | 2290776 | 658974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 763111 | 0 | 763111 | 837149 | 0 | 837149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 23872 | 0 | 23872 | 28872 | 0 | 28872 | 9990570 | 2997171 | 6993399 | 1483761 | 445129 | 1038632 | 5195512 | 2504653 | 2690859 | 9990570 | 2997171 | 6993399 | 1483761 | 445129 | 1038632 | 5195512 | 2504653 | 2690859 | 0 | 0 | Rockbridge, County of | TRUE
NT10BIX5570129 | CCI | 2012 | Q2 | Q2 - 2012 | 2239010 | 0 | 2239010 | 368464 | 0 | 368464 | 1300000 | 0 | 1300000 | 2973056 | 497171 | 2475885 | 45747 | 7648 | 38099 | 700000 | 117040 | 582960 | 35150 | 0 | 35150 | 15777 | 0 | 15777 | 17000 | 0 | 17000 | 3219000 | 2500000 | 719000 | 1448825 | 796105 | 652720 | 3020000 | 2345332 | 674668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 776494 | 0 | 776494 | 850000 | 0 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 0 | 0 | 0 | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 23872 | 0 | 23872 | 45000 | 0 | 45000 | 9990570 | 2997171 | 6993399 | 2679179 | 803753 | 1875426 | 5957000 | 2462372 | 3494628 | 9990570 | 2997171 | 6993399 | 2679179 | 803753 | 1875426 | 5957000 | 2462372 | 3494628 | 0 | 0 | Rockbridge, County of | TRUE
NT10BIX5570129 | CCI | 2012 | Q3 | Q3 - 2012 | 2239010 | 0 | 2239010 | 1089044 | 326713 | 762331 | 1500000 | 450000 | 1050000 | 2973056 | 497171 | 2475885 | 615487 | 184646 | 430841 | 1200000 | 360000 | 840000 | 35150 | 0 | 35150 | 19051 | 5715 | 13336 | 21000 | 6300 | 14700 | 3219000 | 2500000 | 719000 | 2964857 | 889457 | 2075400 | 3100000 | 930000 | 2170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 847133 | 254140 | 592993 | 900000 | 270000 | 630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 4872 | 1462 | 3410 | 23000 | 6900 | 16100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 100802 | 30241 | 70561 | 210000 | 63000 | 147000 | 9990570 | 2997171 | 6993399 | 5641246 | 1692374 | 3948872 | 6954000 | 2086200 | 4867800 | 9990570 | 2997171 | 6993399 | 5641246 | 1692374 | 3948872 | 6954000 | 2086200 | 4867800 | 0 | 286 | Rockbridge, County of | TRUE
NT10BIX5570129 | CCI | 2012 | Q4 | Q4 - 2012 | 2239010 | 0 | 2239010 | 1202977 | 360893 | 842084 | 1600000 | 480000 | 1120000 | 2973056 | 497171 | 2475885 | 1372711 | 411813 | 960898 | 2000000 | 600000 | 1400000 | 35150 | 0 | 35150 | 20517 | 6155 | 14362 | 21500 | 6450 | 15050 | 3219000 | 2500000 | 719000 | 3092734 | 927821 | 2164913 | 3142734 | 942820 | 2199914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 877235 | 263171 | 614064 | 927000 | 278100 | 648900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 14616 | 4385 | 10231 | 34000 | 10200 | 23800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 138761 | 41628 | 97133 | 210000 | 63000 | 147000 | 9990570 | 2997171 | 6993399 | 6719551 | 2015866 | 4703685 | 7935234 | 2380570 | 5554664 | 9990570 | 2997171 | 6993399 | 6719551 | 2015866 | 4703685 | 7935234 | 2380570 | 5554664 | 0 | 744 | Rockbridge, County of | TRUE
NT10BIX5570129 | CCI | 2013 | Q1 | Q1 - 2013 | 2239010 | 0 | 2239010 | 1474050 | 442215 | 1031835 | 2000000 | 600000 | 1400000 | 2973056 | 497171 | 2475885 | 2096442 | 628933 | 1467509 | 2970000 | 891000 | 2079000 | 35150 | 0 | 35150 | 20806 | 6242 | 14564 | 25000 | 7500 | 17500 | 3219000 | 2500000 | 719000 | 3095820 | 928746 | 2167074 | 3146000 | 943800 | 2202200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 929386 | 278816 | 650570 | 1050000 | 315000 | 735000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 24360 | 7308 | 17052 | 60000 | 18000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 210779 | 63234 | 147545 | 270000 | 81000 | 189000 | 9990570 | 2997171 | 6993399 | 7851643 | 2355494 | 5496149 | 9521000 | 2856300 | 6664700 | 9990570 | 2997171 | 6993399 | 7851643 | 2355494 | 5496149 | 9521000 | 2856300 | 6664700 | 0 | 1382 | Rockbridge, County of | TRUE
NT10BIX5570129 | CCI | 2013 | Q2 | Q2 - 2013 | 2239010 | 0 | 2239010 | 1525054 | 457516 | 1067538 | 1569042 | 470713 | 1098329 | 2973056 | 497171 | 2475885 | 3061709 | 918513 | 2143196 | 3643024 | 1092907 | 2550117 | 35150 | 0 | 35150 | 21679 | 6504 | 15175 | 35150 | 10545 | 24605 | 3219000 | 2500000 | 719000 | 3117589 | 935277 | 2182312 | 3219000 | 965700 | 2253300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054718 | 0 | 1054718 | 996862 | 299059 | 697803 | 1089718 | 326915 | 762803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108316 | 0 | 108316 | 48720 | 14616 | 34104 | 73316 | 21995 | 51321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361320 | 0 | 361320 | 213215 | 63963 | 149252 | 361320 | 108396 | 252924 | 9990570 | 2997171 | 6993399 | 8984828 | 2695448 | 6289380 | 9990570 | 2997171 | 6993399 | 9990570 | 2997171 | 6993399 | 8984828 | 2695448 | 6289380 | 9990570 | 2997171 | 6993399 | 0 | 2019 | Rockbridge, County of | TRUE
NT10BIX5570129 | CCI | 2013 | Q3 | Q3 - 2013 | 1569042 | 470713 | 1098329 | 1569042 | 470713 | 1098329 | 1569042 | 470713 | 1098329 | 3731516 | 1119455 | 2612061 | 3731516 | 1119454 | 2612062 | 3731516 | 1119454 | 2612062 | 35292 | 11730 | 23562 | 24923 | 6622 | 17446 | 24923 | 6622 | 17446 | 3217789 | 965337 | 2252452 | 3217789 | 965337 | 2252452 | 3217789 | 965337 | 2252452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088379 | 326514 | 761865 | 1086854 | 326056 | 760797 | 1086854 | 326056 | 760797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74704 | 22411 | 52293 | 74704 | 22411 | 52293 | 74704 | 22411 | 52293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279030 | 86193 | 192837 | 287251 | 89803 | 197448 | 287251 | 89803 | 197448 | 9995752 | 3002353 | 6993399 | 9992079 | 3000396 | 6990827 | 9992079 | 3000396 | 6990827 | 9995752 | 3002353 | 6993399 | 9992079 | 3000396 | 6990827 | 9992079 | 3000396 | 6990827 | 0 | 5182 | Rockbridge, County of | TRUE
NT10BIX5570130 | CCI | 2010 | Q4 | Q4 - 2010 | 21306005 | 6668780 | 14637225 | 291170 | 164263 | 126907 | 1542349 | 497702 | 1044647 | 1371989 | 429433 | 942557 | 0 | 0 | 0 | 301837 | 94475 | 207362 | 1234225 | 386312 | 847913 | 193751 | 0 | 193751 | 302687 | 0 | 302687 | 1012000 | 316756 | 695244 | 0 | 0 | 0 | 354200 | 110865 | 243335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 18780 | 41220 | 0 | 0 | 0 | 60000 | 0 | 60000 | 10399126 | 3254926 | 7144199 | 886296 | 566960 | 319336 | 2069982 | 729706 | 1340276 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 22217 | 6954 | 15263 | 19190744 | 6006703 | 13184041 | 0 | 0 | 0 | 128367 | 0 | 128367 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 31195356 | 9764147 | 21431209 | 10162 | 0 | 10162 | 1575896 | 488207 | 1087689 | 86256980 | 26998436 | 59258544 | 1381379 | 731223 | 650156 | 6357535 | 1927909 | 4429626 | 86256980 | 26998436 | 59258544 | 1381379 | 731223 | 650156 | 6357535 | 1927909 | 4429626 | 0 | 0 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | CCI | 2011 | Q1 | Q1 - 2011 | 21306005 | 6668780 | 14637225 | 329613 | 194263 | 299613 | 4030000 | 1261390 | 2768610 | 1371990 | 429433 | 942557 | 0 | 0 | 0 | 301837 | 94475 | 207362 | 1234225 | 386312 | 847913 | 359194 | 6000 | 359194 | 502687 | 157341 | 345346 | 1012000 | 316756 | 695244 | 0 | 0 | 0 | 264000 | 82632 | 181368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 18780 | 41220 | 0 | 0 | 0 | 0 | 0 | 0 | 10399125 | 3254926 | 7144199 | 1823533 | 566960 | 1256573 | 2769033 | 866707 | 1902326 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 22217 | 6954 | 15263 | 19190744 | 6006703 | 13184041 | 0 | 0 | 0 | 2140000 | 669820 | 1470180 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 31195356 | 9764147 | 21431209 | 10737 | 0 | 10737 | 0 | 986511 | 2165281 | 86256980 | 26998436 | 59258544 | 2523077 | 767223 | 1926117 | 10029774 | 4125830 | 9055736 | 86256980 | 26998436 | 59258544 | 2523077 | 767223 | 1926117 | 10029774 | 4125830 | 9055736 | 0 | 0 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | CCI | 2011 | Q2 | Q2 - 2011 | 21306005 | 6668780 | 14637225 | 544646 | 205738 | 338908 | 4150900 | 1299232 | 2851668 | 1371990 | 429433 | 942557 | 0 | 0 | 0 | 322965 | 101088 | 221877 | 1234225 | 386312 | 847913 | 520764 | 7000 | 513764 | 544578 | 170453 | 374125 | 1012000 | 316756 | 695244 | 0 | 0 | 0 | 264000 | 82632 | 181368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 18780 | 41220 | 60000 | 0 | 60000 | 0 | 0 | 60000 | 10399125 | 3254926 | 7144199 | 2404797 | 566960 | 1837837 | 3156697 | 988046 | 2168651 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 23994 | 7510 | 16484 | 19190744 | 6006703 | 13184041 | 0 | 0 | 0 | 2204200 | 689915 | 1514285 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 31195356 | 9764147 | 21431209 | 15364 | 0 | 15364 | 3309381 | 1035836 | 2273545 | 86256980 | 26998436 | 59258544 | 3545571 | 779698 | 2765873 | 13976715 | 4374712 | 9662003 | 86256980 | 26998436 | 59258544 | 3545571 | 779698 | 2765873 | 13976715 | 4374712 | 9662003 | 0 | 0 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | CCI | 2011 | Q3 | Q3 - 2011 | 21306005 | 6668780 | 14637225 | 4994155 | 2306786 | 2687369 | 9472217 | 2936387 | 6535830 | 1371990 | 429433 | 942557 | 0 | 0 | 0 | 322965 | 101088 | 221877 | 1234225 | 386312 | 847913 | 622389 | 7000 | 615389 | 1039151 | 322137 | 717014 | 1012000 | 316756 | 695244 | 0 | 0 | 0 | 264000 | 82632 | 181368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 18780 | 41220 | 79835 | 0 | 79835 | 79835 | 18780 | 60755 | 10399125 | 3254926 | 7144199 | 3488353 | 566960 | 2921393 | 5804273 | 1799325 | 4004948 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 23994 | 7510 | 16484 | 19190744 | 6006703 | 13184041 | 0 | 0 | 0 | 2204200 | 689915 | 1514285 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 31195356 | 9764147 | 21431209 | 15932 | 0 | 15932 | 3309949 | 1035836 | 2274113 | 86256980 | 26998436 | 59258544 | 9200664 | 2880746 | 6319918 | 22520584 | 6993610 | 15526674 | 86256980 | 26998436 | 59258544 | 9200664 | 2880746 | 6319918 | 22520584 | 6993610 | 15526674 | 0 | 0 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | CCI | 2011 | Q4 | Q4 - 2011 | 22470612 | 6668780 | 15801832 | 2979111 | 365524 | 2613587 | 17642460 | 2690300 | 14952160 | 1371989 | 429433 | 942556 | 0 | 0 | 0 | 439364 | 66999 | 372365 | 1761710 | 386312 | 1375398 | 872079 | 0 | 872079 | 1597687 | 243631 | 1354056 | 349577 | 316756 | 32821 | 0 | 0 | 0 | 106000 | 16164 | 89836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 18780 | 81220 | 0 | 0 | 0 | 35948 | 5482 | 30466 | 10379021 | 3254926 | 7124095 | 4757362 | 567019 | 4190343 | 7285453 | 1110959 | 6174494 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 87873 | 13400 | 74473 | 19589925 | 6006703 | 13583222 | 846714 | 7000 | 839714 | 7589014 | 1157249 | 6431764 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 29746611 | 9764147 | 19982464 | 945040 | 15278 | 929762 | 5158378 | 786601 | 4371778 | 86256980 | 26998436 | 59258544 | 10400306 | 954821 | 9445485 | 39942177 | 6090785 | 33851392 | 86256980 | 26998436 | 59258544 | 10400306 | 954821 | 9445485 | 39942177 | 6090785 | 33851392 | 0 | 0 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | CCI | 2012 | Q1 | Q1 - 2012 | 22470612 | 6668780 | 15801832 | 2988430 | 365524 | 2622906 | 7060188 | 1590458 | 5469730 | 1371989 | 429433 | 942556 | 0 | 0 | 0 | 460547 | 27893 | 432654 | 1761710 | 386312 | 1375398 | 1038207 | 0 | 1038207 | 1097721 | 59514 | 1038207 | 349577 | 316756 | 32821 | 0 | 0 | 0 | 35333 | 29945 | 5388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 18780 | 81220 | 0 | 0 | 0 | 11982 | 1827 | 10155 | 10379021 | 3254926 | 7124095 | 5362620 | 567019 | 4795601 | 5760749 | 965148 | 4795601 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 31087 | 6263 | 24824 | 19589925 | 6006703 | 13583222 | 1262765 | 7000 | 1255765 | 2086908 | 655255 | 1431653 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 29746611 | 9764147 | 19982464 | 1361424 | 15278 | 1346146 | 3674151 | 439477 | 3234674 | 86256980 | 26998436 | 59258544 | 12013446 | 954821 | 11058625 | 20218666 | 3775780 | 16442886 | 86256980 | 26998436 | 59258544 | 12013446 | 954821 | 11058625 | 20218666 | 3775780 | 16442886 | 0 | 0 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | CCI | 2012 | Q2 | Q2 - 2012 | 22470612 | 6668780 | 15801832 | 3050372 | 365524 | 2684848 | 7122130 | 1590458 | 5531672 | 1371989 | 429433 | 942556 | 200000 | 0 | 200000 | 660547 | 27893 | 632654 | 1761710 | 386312 | 1375398 | 1375232 | 0 | 1375232 | 1434485 | 59253 | 1375232 | 349577 | 316756 | 32821 | 0 | 0 | 0 | 35333 | 29945 | 5388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 18780 | 81220 | 0 | 0 | 0 | 11982 | 1827 | 10155 | 10379021 | 3254926 | 7124095 | 5433088 | 567019 | 4866069 | 5831217 | 965148 | 4866069 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 31087 | 6263 | 24824 | 19589925 | 6006703 | 13583222 | 1262765 | 7000 | 1255765 | 2086908 | 655255 | 1431653 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 29746611 | 9764147 | 19982464 | 1361424 | 15278 | 1346146 | 3674151 | 439477 | 3234674 | 86256980 | 26998436 | 59258544 | 12682881 | 954821 | 11728060 | 20887840 | 3775519 | 17112321 | 86256980 | 26998436 | 59258544 | 12682881 | 954821 | 11728060 | 20887840 | 3775519 | 17112321 | 0 | 0 | Trillion Communications Corp. | TRUE
NT10BIX5570130 | CCI | 2012 | Q3 | Q3 - 2012 | 22470612 | 6668780 | 15801832 | 3050372 | 365524 | 2684848 | 3050372 | 365524 | 2684848 | 1371989 | 429433 | 942556 | 200000 | 0 | 200000 | 200000 | 0 | 200000 | 1761710 | 386312 | 1375398 | 1509876 | 0 | 1509876 | 1614443 | 0 | 1614443 | 349577 | 316756 | 32821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 18780 | 81220 | 0 | 0 | 0 | 0 | 0 | 0 | 10379021 | 3254926 | 7124095 | 5433088 | 567019 | 4866069 | 5433088 | 567019 | 4866069 | 444335 | 139077 | 305258 | 0 | 0 | 0 | 0 | 0 | 0 | 19589925 | 6006703 | 13583222 | 1262765 | 7000 | 1255765 | 1262765 | 7000 | 1255765 | 43200 | 13522 | 29678 | 0 | 0 | 0 | 0 | 0 | 0 | 29746611 | 9764147 | 19982464 | 1361424 | 15278 | 1346146 | 1361424 | 15278 | 1346146 | 86256980 | 26998436 | 59258544 | 12817525 | 954821 | 11862704 | 12922092 | 954821 | 11967271 | 86256980 | 26998436 | 59258544 | 12817525 | 954821 | 11862704 | 12922092 | 954821 | 11967271 | 0 | 0 | Trillion Communications Corp. | TRUE
NT10BIX5570131 | CCI | 2010 | Q4 | Q4 - 2010 | 3709590 | 741918 | 2967672 | 0 | 0 | 0 | 2448 | 490 | 1958 | 25805608 | 5161122 | 20644486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012000 | 202400 | 809600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 0 | 0 | 0 | 727283 | 145456 | 581827 | 1290280 | 258056 | 1032224 | 0 | 0 | 0 | 107560 | 21512 | 86048 | 950297 | 190059 | 760238 | 0 | 0 | 0 | 0 | 0 | 0 | 192000 | 38400 | 153600 | 0 | 0 | 0 | 0 | 0 | 0 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36031695 | 7206339 | 28825356 | 0 | 0 | 0 | 837291 | 167458 | 669833 | 36031695 | 7206339 | 28825356 | 0 | 0 | 0 | 837291 | 167458 | 669833 | 0 | 0 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | CCI | 2011 | Q1 | Q1 - 2011 | 3709590 | 741918 | 2967672 | 2448 | 490 | 1958 | 2448 | 490 | 1958 | 25805608 | 5161122 | 20644486 | 0 | 0 | 0 | 1599032 | 319806 | 1279226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012000 | 202400 | 809600 | 0 | 0 | 0 | 42385 | 8477 | 33908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 603420 | 120684 | 482736 | 1041331 | 208266 | 833065 | 1290280 | 258056 | 1032224 | 188119 | 37624 | 150495 | 753349 | 150670 | 602679 | 950297 | 190059 | 760238 | 0 | 0 | 0 | 130805 | 26161 | 104644 | 192000 | 38400 | 153600 | 0 | 0 | 0 | 0 | 0 | 0 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451 | 490 | 1961 | 2451 | 490 | 1961 | 36031695 | 7206339 | 28825356 | 796438 | 159288 | 637150 | 3571801 | 714360 | 2857441 | 36031695 | 7206339 | 28825356 | 796438 | 159288 | 637150 | 3571801 | 714360 | 2857441 | 0 | 0 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | CCI | 2011 | Q2 | Q2 - 2011 | 3709590 | 741918 | 2967672 | 3811 | 762 | 3049 | 3811 | 762 | 3049 | 25805608 | 5161122 | 20644486 | 792397 | 158480 | 633917 | 1599032 | 319806 | 1279226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012000 | 202400 | 809600 | 15725 | 3145 | 12580 | 42385 | 8477 | 33908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 882836 | 176567 | 706269 | 1041331 | 208266 | 833065 | 1290280 | 258056 | 1032224 | 70881 | 14176 | 56705 | 753349 | 150670 | 602679 | 950297 | 190059 | 760238 | 0 | 0 | 0 | 130805 | 26161 | 104644 | 192000 | 38400 | 153600 | 0 | 0 | 0 | 0 | 0 | 0 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451 | 490 | 1961 | 2451 | 490 | 1961 | 36031695 | 7206339 | 28825356 | 1768101 | 353620 | 1414481 | 3573164 | 714632 | 2858532 | 36031695 | 7206339 | 28825356 | 1768101 | 353620 | 1414481 | 3573164 | 714632 | 2858532 | 0 | 0 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | CCI | 2011 | Q3 | Q3 - 2011 | 3709590 | 741918 | 2967672 | 974670 | 194934 | 779736 | 1124670 | 224934 | 899736 | 25805608 | 5161122 | 20644486 | 1948066 | 389613 | 1558453 | 3698066 | 739613 | 2958453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012000 | 202400 | 809600 | 16225 | 3245 | 12980 | 42385 | 8477 | 33908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 1215205 | 243041 | 972164 | 1590205 | 318041 | 1272164 | 1290280 | 258056 | 1032224 | 83381 | 16676 | 66705 | 83381 | 16676 | 66705 | 950297 | 190059 | 760238 | 0 | 0 | 0 | 130805 | 26161 | 104644 | 192000 | 38400 | 153600 | 9357 | 1872 | 7485 | 9357 | 1871 | 7485 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451 | 490 | 1961 | 2451 | 490 | 1961 | 36031695 | 7206339 | 28825356 | 4249355 | 849871 | 3399484 | 6681320 | 1336263 | 5345056 | 36031695 | 7206339 | 28825356 | 4249355 | 849871 | 3399484 | 6681320 | 1336263 | 5345056 | 0 | 0 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | CCI | 2011 | Q4 | Q4 - 2011 | 3709590 | 741918 | 2967672 | 1007147 | 201429 | 805718 | 1261261 | 252252 | 1009009 | 25805608 | 5161122 | 20644486 | 4329112 | 865822 | 3463290 | 6451402 | 1290280 | 5161122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012000 | 202400 | 809600 | 21050 | 4210 | 16840 | 42385 | 8477 | 33908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 1374108 | 274823 | 1099285 | 1459948 | 291989 | 1167959 | 1290280 | 258056 | 1032224 | 83381 | 16676 | 66705 | 221764 | 44353 | 177411 | 950297 | 190059 | 760238 | 152678 | 30536 | 122142 | 166323 | 33265 | 133058 | 192000 | 38400 | 153600 | 15763 | 3152 | 12611 | 19200 | 3840 | 15360 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2841 | 568 | 2273 | 2841 | 568 | 2273 | 36031695 | 7206339 | 28825356 | 6986080 | 1397216 | 5588864 | 9625124 | 1925024 | 7700100 | 36031695 | 7206339 | 28825356 | 6986080 | 1397216 | 5588864 | 9625124 | 1925024 | 7700100 | 0 | 0 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | CCI | 2012 | Q1 | Q1 - 2012 | 3709590 | 741918 | 2967672 | 1012050 | 202410 | 809640 | 1261000 | 252200 | 1008800 | 25805608 | 5161122 | 20644486 | 6478956 | 1295792 | 5183164 | 8250500 | 1650100 | 6600400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012000 | 202400 | 809600 | 25950 | 5190 | 20760 | 43822 | 8764 | 35058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 1623834 | 324766 | 1299068 | 1772100 | 354420 | 1417680 | 1290280 | 258056 | 1032224 | 132875 | 26575 | 106300 | 205750 | 41150 | 164600 | 950297 | 190059 | 760238 | 159259 | 31852 | 127407 | 187150 | 37430 | 149720 | 192000 | 38400 | 153600 | 26053 | 5211 | 20842 | 37500 | 7500 | 30000 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2841 | 568 | 2273 | 2841 | 568 | 2273 | 36031695 | 7206339 | 28825356 | 9461818 | 1892364 | 7569454 | 11760663 | 2352132 | 9408531 | 36031695 | 7206339 | 28825356 | 9461818 | 1892364 | 7569454 | 11760663 | 2352132 | 9408531 | 0 | 5845 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | CCI | 2012 | Q2 | Q2 - 2012 | 3709590 | 741918 | 2967672 | 1215672 | 243134 | 972538 | 1602561 | 320512 | 1282049 | 25805608 | 5161122 | 20644486 | 8648849 | 1729770 | 6919079 | 10952640 | 2190527 | 8762113 | 0 | 0 | 0 | 8430 | 1686 | 6744 | 8430 | 1686 | 6744 | 1012000 | 202400 | 809600 | 35300 | 7060 | 28240 | 43822 | 8764 | 35058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 2054410 | 410882 | 1643528 | 2443306 | 488662 | 1954644 | 1290280 | 258056 | 1032224 | 132875 | 26575 | 106300 | 205750 | 41150 | 164600 | 950297 | 190059 | 760238 | 159259 | 31852 | 127407 | 218720 | 43744 | 174976 | 192000 | 38400 | 153600 | 26053 | 5211 | 20842 | 37500 | 7500 | 30000 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36031695 | 7206339 | 28825356 | 12280848 | 2456170 | 9824678 | 15512729 | 3102545 | 12410184 | 36031695 | 7206339 | 28825356 | 12280848 | 2456170 | 9824678 | 15512729 | 3102545 | 12410184 | 0 | 32730 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | CCI | 2012 | Q3 | Q3 - 2012 | 3709590 | 741918 | 2967672 | 1421087 | 284217 | 1136870 | 1668300 | 333650 | 1334650 | 25805608 | 5161122 | 20644486 | 12320187 | 2464037 | 9856150 | 15780508 | 3156112 | 12624396 | 0 | 0 | 0 | 8430 | 1686 | 6744 | 8430 | 1686 | 6744 | 1012000 | 202400 | 809600 | 35300 | 7060 | 28240 | 43822 | 8764 | 35058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 2497678 | 499536 | 1998142 | 3203000 | 640600 | 2562400 | 1290280 | 258056 | 1032224 | 163044 | 32609 | 130435 | 205750 | 41150 | 164600 | 950297 | 190059 | 760238 | 277519 | 55504 | 222015 | 311390 | 62278 | 249112 | 192000 | 38400 | 153600 | 26233 | 5247 | 20986 | 37500 | 7500 | 30000 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36031695 | 7206339 | 28825356 | 16749478 | 3349896 | 13399582 | 21258700 | 4251740 | 17006960 | 36031695 | 7206339 | 28825356 | 16749478 | 3349896 | 13399582 | 21258700 | 4251740 | 17006960 | 0 | 155652 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | CCI | 2012 | Q4 | Q4 - 2012 | 3709590 | 741918 | 2967672 | 1629668 | 325933 | 1303735 | 1904668 | 380935 | 1523733 | 25805608 | 5161122 | 20644486 | 15173419 | 3034684 | 12138735 | 18923420 | 3784684 | 15138736 | 0 | 0 | 0 | 9119 | 1824 | 7295 | 19119 | 3823 | 15296 | 1012000 | 202400 | 809600 | 37300 | 7460 | 29840 | 46800 | 9360 | 37440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 3042997 | 608599 | 2434398 | 3676752 | 735350 | 2941402 | 1290280 | 258056 | 1032224 | 163044 | 32609 | 130435 | 163043 | 32609 | 130434 | 950297 | 190059 | 760238 | 338110 | 67622 | 270488 | 379356 | 75871 | 303485 | 192000 | 38400 | 153600 | 26233 | 5247 | 20986 | 33633 | 6726 | 26907 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36031695 | 7206339 | 28825356 | 20419890 | 4083978 | 16335912 | 25146791 | 5029358 | 20117433 | 36031695 | 7206339 | 28825356 | 20419890 | 4083978 | 16335912 | 25146791 | 5029358 | 20117433 | 0 | 373013 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | CCI | 2013 | Q1 | Q1 - 2013 | 3709590 | 741918 | 2967672 | 1839204 | 367841 | 1471363 | 2575000 | 515000 | 2060000 | 25805608 | 5161122 | 20644486 | 18480957 | 3696190 | 14784767 | 23730000 | 4746000 | 18984000 | 0 | 0 | 0 | 9119 | 1824 | 7295 | 19119 | 3823 | 15296 | 1012000 | 202400 | 809600 | 58002 | 11600 | 46402 | 75300 | 15060 | 60240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039520 | 607904 | 2431616 | 3505465 | 701093 | 2804372 | 4005000 | 801000 | 3204000 | 1290280 | 258056 | 1032224 | 163044 | 32609 | 130435 | 163044 | 32609 | 130435 | 950297 | 190059 | 760238 | 378013 | 75603 | 302410 | 485300 | 97060 | 388240 | 192000 | 38400 | 153600 | 26233 | 5247 | 20986 | 37500 | 7500 | 30000 | 32400 | 6480 | 25920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36031695 | 7206339 | 28825356 | 24460037 | 4892007 | 19568030 | 31090263 | 6218052 | 24872211 | 36031695 | 7206339 | 28825356 | 24460037 | 4892007 | 19568030 | 31090263 | 6218052 | 24872211 | 0 | 645222 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | CCI | 2013 | Q2 | Q2 - 2013 | 2869590 | 573918 | 2295672 | 2838488 | 567697 | 2270791 | 2869590 | 573918 | 2295672 | 27237608 | 5447522 | 21790086 | 24172400 | 4834479 | 19337921 | 27237608 | 5447522 | 21790086 | 10000 | 2000 | 8000 | 9164 | 1834 | 7330 | 10000 | 2000 | 8000 | 77000 | 15400 | 61600 | 75455 | 15091 | 60364 | 77000 | 15400 | 61600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4171920 | 834384 | 3337536 | 3726193 | 745239 | 2980954 | 4171920 | 834384 | 3337536 | 840280 | 168056 | 672224 | 408608 | 81722 | 326886 | 840280 | 168056 | 672224 | 750297 | 150059 | 600238 | 456343 | 91268 | 365075 | 750297 | 150059 | 600238 | 75000 | 15000 | 60000 | 73233 | 14647 | 58586 | 75000 | 15000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36031695 | 7206339 | 28825356 | 31759884 | 6351977 | 25407907 | 36031695 | 7206339 | 28825356 | 36031695 | 7206339 | 28825356 | 31759884 | 6351977 | 25407907 | 36031695 | 7206339 | 28825356 | 0 | 1070533 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570131 | CCI | 2013 | Q3 | Q3 - 2013 | 2900636 | 580128 | 2320508 | 2906600 | 586091 | 2320508 | 2906600 | 586091 | 2320508 | 28069887 | 5613978 | 22455909 | 28072209 | 5616300 | 22455909 | 28072209 | 5616300 | 22455909 | 9164 | 1834 | 7330 | 9164 | 1834 | 7330 | 9164 | 1834 | 7330 | 84875 | 16975 | 67900 | 84875 | 16975 | 67900 | 84875 | 16975 | 67900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3687828 | 737564 | 2950264 | 3967124 | 1016861 | 2950264 | 3967124 | 1016861 | 2950264 | 618406 | 123681 | 494725 | 618406 | 123681 | 494725 | 618406 | 123681 | 494725 | 583142 | 116628 | 466514 | 583142 | 116628 | 466514 | 583142 | 116628 | 466514 | 77757 | 15551 | 62206 | 77757 | 15551 | 62206 | 77757 | 15551 | 62206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36031695 | 7206339 | 28825356 | 36319277 | 7493921 | 28825356 | 36319277 | 7493921 | 28825356 | 36031695 | 7206339 | 28825356 | 36319277 | 7493921 | 28825356 | 36319277 | 7493921 | 28825356 | 0 | 1564739 | Peoples Telephone Cooperative Inc. | TRUE
NT10BIX5570132 | CCI | 2010 | Q4 | Q4 - 2010 | 4519951 | 1355985 | 3163965 | 0 | 0 | 0 | 0 | 0 | 0 | 15690500 | 4707150 | 10983350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 67500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080000 | 924000 | 2156000 | 38445 | 11534 | 26911 | 326445 | 97934 | 228511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460815 | 38445 | 11534 | 26911 | 326445 | 97934 | 228511 | 23515451 | 7054635 | 16460815 | 38445 | 11534 | 26911 | 326445 | 97934 | 228511 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | CCI | 2011 | Q1 | Q1 - 2011 | 4519951 | 1355985 | 3163965 | 0 | 0 | 0 | 0 | 0 | 0 | 15690500 | 4707150 | 10983350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 67500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080000 | 924000 | 2156000 | 155879 | 46764 | 109115 | 444607 | 133382 | 311225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460815 | 155879 | 46764 | 109115 | 444607 | 133382 | 311225 | 23515451 | 7054635 | 16460815 | 155879 | 46764 | 109115 | 444607 | 133382 | 311225 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | CCI | 2011 | Q2 | Q2 - 2011 | 4519951 | 1355985 | 3163965 | 0 | 0 | 0 | 200000 | 60000 | 140000 | 15690500 | 4707150 | 10983350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 67500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080000 | 924000 | 2156000 | 478839 | 143652 | 335187 | 762368 | 228711 | 533657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460815 | 478839 | 143652 | 335187 | 962368 | 288711 | 673657 | 23515451 | 7054635 | 16460815 | 478839 | 143652 | 335187 | 962368 | 288711 | 673657 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | CCI | 2011 | Q3 | Q3 - 2011 | 4519951 | 1355985 | 3163965 | 0 | 0 | 0 | 643745 | 193123 | 450622 | 15690500 | 4707150 | 10983350 | 0 | 0 | 0 | 2459130 | 737739 | 1721391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 67500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080000 | 924000 | 2156000 | 581570 | 174471 | 407099 | 940352 | 282106 | 658246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460815 | 581570 | 174471 | 407099 | 4043227 | 1212968 | 2830259 | 23515451 | 7054635 | 16460815 | 581570 | 174471 | 407099 | 4043227 | 1212968 | 2830259 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | CCI | 2011 | Q4 | Q4 - 2011 | 4519951 | 1355985 | 3163965 | 479073 | 143722 | 335351 | 1659934 | 497980 | 1161954 | 15690500 | 4707150 | 10983350 | 263102 | 78931 | 184171 | 4247732 | 1274320 | 2973412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 67500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080000 | 924000 | 2156000 | 744136 | 223241 | 520895 | 1694000 | 508200 | 1185800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460815 | 1486311 | 445894 | 1040417 | 7601666 | 2280500 | 5321166 | 23515451 | 7054635 | 16460815 | 1486311 | 445894 | 1040417 | 7601666 | 2280500 | 5321166 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | CCI | 2012 | Q1 | Q1 - 2012 | 4519951 | 1355985 | 3163965 | 1997859 | 599358 | 1398501 | 3750000 | 1125000 | 2625000 | 15690500 | 4707150 | 10983350 | 2098223 | 629467 | 1468756 | 7500000 | 2250000 | 5250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 67500 | 157500 | 46867 | 14060 | 32807 | 195000 | 58500 | 136500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3080000 | 924000 | 2156000 | 1069013 | 320704 | 748309 | 1750000 | 525000 | 1225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460815 | 5211962 | 1563589 | 3648373 | 13195000 | 3958500 | 9236500 | 23515451 | 7054635 | 16460815 | 5211962 | 1563589 | 3648373 | 13195000 | 3958500 | 9236500 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | CCI | 2012 | Q2 | Q2 - 2012 | 4304863 | 1291459 | 3013404 | 2352600 | 705780 | 1646820 | 3442270 | 1032681 | 2409589 | 15424113 | 4627234 | 10796879 | 5309813 | 1592944 | 3716869 | 10723753 | 3217126 | 7506627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 807064 | 242119 | 564945 | 295618 | 88685 | 206933 | 807064 | 242119 | 564945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2979411 | 893823 | 2085588 | 1494236 | 448271 | 1045965 | 2459572 | 737872 | 1721700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460816 | 9452267 | 2835680 | 6616587 | 17432659 | 5229798 | 12202861 | 23515451 | 7054635 | 16460816 | 9452267 | 2835680 | 6616587 | 17432659 | 5229798 | 12202861 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | CCI | 2012 | Q3 | Q3 - 2012 | 4304863 | 1291459 | 3013404 | 3092270 | 927681 | 2164589 | 3817270 | 1145181 | 2672089 | 15424113 | 4627234 | 10796879 | 8896390 | 2668917 | 6227473 | 12146390 | 3643917 | 8502473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 807064 | 242119 | 564945 | 792675 | 237803 | 554873 | 807064 | 242119 | 564945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2979411 | 893823 | 2085588 | 2139588 | 641876 | 1497712 | 2589588 | 776876 | 1812712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460816 | 14920923 | 4476277 | 10444647 | 19360312 | 5808093 | 13552219 | 23515451 | 7054635 | 16460816 | 14920923 | 4476277 | 10444647 | 19360312 | 5808093 | 13552219 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | CCI | 2012 | Q4 | Q4 - 2012 | 4273040 | 1281912 | 2991128 | 3142319 | 942696 | 2199623 | 4059388 | 1217816 | 2841572 | 15424113 | 4627234 | 10796879 | 9906507 | 2971952 | 6934555 | 13418978 | 4025693 | 9393285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2979411 | 893823 | 2085588 | 2490617 | 747185 | 1743432 | 2830440 | 849132 | 1981308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460816 | 16378330 | 4913499 | 11464831 | 21147693 | 6344307 | 14803386 | 23515451 | 7054635 | 16460816 | 16378330 | 4913499 | 11464831 | 21147693 | 6344307 | 14803386 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | CCI | 2013 | Q1 | Q1 - 2013 | 4518939 | 1355682 | 3163257 | 3319560 | 995868 | 2323692 | 4518939 | 1355682 | 3163257 | 14485517 | 4345655 | 10139862 | 11549419 | 3464826 | 8084593 | 13761241 | 4128372 | 9632869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3672108 | 1101632 | 2570476 | 2768727 | 830618 | 1938109 | 3304897 | 991469 | 2313428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460816 | 18476593 | 5542978 | 12933615 | 22423964 | 6727189 | 15696775 | 23515451 | 7054635 | 16460816 | 18476593 | 5542978 | 12933615 | 22423964 | 6727189 | 15696775 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | CCI | 2013 | Q2 | Q2 - 2013 | 4518939 | 1355682 | 3163257 | 3991493 | 1197448 | 2794045 | 4518939 | 1355682 | 3163257 | 14485517 | 4345655 | 10139862 | 13775994 | 4132798 | 9643196 | 14485517 | 4345655 | 10139862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3672108 | 1101632 | 2570476 | 3562670 | 1068801 | 2493869 | 3672108 | 1101632 | 2570476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054635 | 16460816 | 22169044 | 6650713 | 15518331 | 23515451 | 7054635 | 16460816 | 23515451 | 7054635 | 16460816 | 22169044 | 6650713 | 15518331 | 23515451 | 7054635 | 16460816 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570132 | CCI | 2013 | Q3 | Q3 - 2013 | 4518939 | 1355682 | 3163257 | 4326826 | 1163569 | 3163257 | 4326826 | 1163569 | 3163257 | 14485517 | 4345656 | 10139861 | 14686116 | 4546255 | 10139861 | 14686116 | 4546255 | 10139861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 838887 | 251666 | 587221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3672108 | 1101632 | 2570476 | 3727743 | 1157267 | 2570476 | 3727743 | 1157267 | 2570476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23515451 | 7054636 | 16460815 | 23579572 | 7118757 | 16460815 | 23579572 | 7118757 | 16460815 | 23515451 | 7054636 | 16460815 | 23579572 | 7118757 | 16460815 | 23579572 | 7118757 | 16460815 | 0 | 0 | E.N.M.R. Telephone Cooperative | TRUE
NT10BIX5570133 | CCI | 2010 | Q3 | Q3 - 2010 | 5598140 | 1119628 | 4478512 | 0 | 0 | 0 | 558700 | 111740 | 446960 | 37772032 | 7554407 | 30217626 | 215145 | 43029 | 172116 | 491448 | 98291 | 393158 | 1030440 | 206088 | 824352 | 31813 | 6363 | 25450 | 115032 | 23006 | 92026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 64216 | 12843 | 51373 | 294167 | 58833 | 235333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 0 | 0 | 0 | 4907 | 981 | 3926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 311174 | 62235 | 248939 | 1464254 | 292851 | 1171403 | 48673735 | 9734747 | 38938988 | 311174 | 62235 | 248939 | 1464254 | 292851 | 1171403 | 0 | 0 | ION Newco Corp | TRUE
NT10BIX5570133 | CCI | 2010 | Q4 | Q4 - 2010 | 5598140 | 1119628 | 4478512 | 558700 | 111740 | 446960 | 558700 | 111740 | 446960 | 37772032 | 7554407 | 30217626 | 491448 | 98290 | 393158 | 2493611 | 498722 | 1994889 | 1030440 | 206088 | 824352 | 115032 | 23007 | 92026 | 198251 | 39650 | 158601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 294167 | 58833 | 235333 | 753481 | 150696 | 602785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 4907 | 981 | 3926 | 4907 | 981 | 3926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 1464254 | 292851 | 1171403 | 4008950 | 801789 | 3207161 | 48673735 | 9734747 | 38938988 | 1464254 | 292851 | 1171403 | 4008950 | 801789 | 3207161 | 0 | 0 | ION Newco Corp | TRUE
NT10BIX5570133 | CCI | 2011 | Q1 | Q1 - 2011 | 5598140 | 1119628 | 4478512 | 251784 | 50357 | 201427 | 1187300 | 237460 | 949840 | 37772032 | 7554407 | 30217626 | 1492401 | 298480 | 1193921 | 4833642 | 966728 | 3866913 | 1030440 | 206088 | 824352 | 177581 | 35516 | 142065 | 281470 | 56294 | 225176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 585004 | 117001 | 468003 | 909675 | 181935 | 727740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 248 | 50 | 198 | 86554 | 17311 | 69244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 2507018 | 501404 | 2005614 | 7298641 | 1459728 | 5838913 | 48673735 | 9734747 | 38938988 | 2507018 | 501404 | 2005614 | 7298641 | 1459728 | 5838913 | 0 | 0 | ION Newco Corp | TRUE
NT10BIX5570133 | CCI | 2011 | Q2 | Q2 - 2011 | 5598140 | 1119628 | 4478512 | 258621 | 51724 | 206897 | 1315100 | 263020 | 1052080 | 37772032 | 7554407 | 30217626 | 3116387 | 623278 | 2493110 | 7756073 | 1551215 | 6204858 | 1030440 | 206088 | 824352 | 258137 | 51627 | 206509 | 364689 | 72938 | 291751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 878355 | 175671 | 702684 | 1077210 | 215442 | 861768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 248 | 50 | 198 | 166900 | 33380 | 133520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 4511748 | 902350 | 3609398 | 10679972 | 2135995 | 8543977 | 48673735 | 9734747 | 38938988 | 4511748 | 902350 | 3609398 | 10679972 | 2135995 | 8543977 | 0 | 0 | ION Newco Corp | TRUE
NT10BIX5570133 | CCI | 2011 | Q3 | Q3 - 2011 | 5598140 | 1119628 | 4478512 | 381335 | 76267 | 305068 | 1454960 | 290992 | 1163968 | 37772032 | 7554407 | 30217626 | 6115183 | 1223036 | 4892147 | 11319659 | 2263932 | 9055727 | 1030440 | 206088 | 824352 | 329516 | 65903 | 263613 | 447908 | 89582 | 358326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 1330560 | 266112 | 1064448 | 1500000 | 300000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 248 | 50 | 198 | 285729 | 57146 | 228583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 8156842 | 1631368 | 6525474 | 15008256 | 3001652 | 12006604 | 48673735 | 9734747 | 38938988 | 8156842 | 1631368 | 6525474 | 15008256 | 3001652 | 12006604 | 0 | 0 | ION Newco Corp | TRUE
NT10BIX5570133 | CCI | 2011 | Q4 | Q4 - 2011 | 5598140 | 1119628 | 4478512 | 1977085 | 395417 | 1581668 | 2500000 | 500000 | 2000000 | 37772032 | 7554407 | 30217626 | 9334208 | 1866841 | 7467366 | 13757134 | 2751427 | 11005707 | 1030440 | 206088 | 824352 | 431028 | 86205 | 344822 | 531126 | 106225 | 424901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 1568728 | 313746 | 1254983 | 1700000 | 340000 | 1360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 366348 | 73270 | 293079 | 411225 | 82245 | 328980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 13677397 | 2735479 | 10941918 | 18899485 | 3779897 | 15119588 | 48673735 | 9734747 | 38938988 | 13677397 | 2735479 | 10941918 | 18899485 | 3779897 | 15119588 | 0 | 0 | ION Newco Corp | TRUE
NT10BIX5570133 | CCI | 2012 | Q1 | Q1 - 2012 | 5598140 | 1119628 | 4478512 | 2819230 | 563846 | 2255384 | 4620620 | 924124 | 3696496 | 37772032 | 7554407 | 30217626 | 13140533 | 2628107 | 10512426 | 18573659 | 3714732 | 14858927 | 1030440 | 206088 | 824352 | 484377 | 96875 | 387502 | 614345 | 122869 | 491476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 1915710 | 383142 | 1532568 | 2147342 | 429468 | 1717874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 456386 | 91277 | 365109 | 530425 | 106085 | 424340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 18816236 | 3763247 | 15052989 | 26486391 | 5297278 | 21189113 | 48673735 | 9734747 | 38938988 | 18816236 | 3763247 | 15052989 | 26486391 | 5297278 | 21189113 | 0 | 0 | ION Newco Corp | TRUE
NT10BIX5570133 | CCI | 2012 | Q2 | Q2 - 2012 | 5598140 | 1119628 | 4478512 | 4152719 | 830544 | 3322175 | 4251620 | 850324 | 3401296 | 37772032 | 7554407 | 30217626 | 16252550 | 3250510 | 13002040 | 22923701 | 4584740 | 18338961 | 1030440 | 206088 | 824352 | 548749 | 109750 | 438999 | 697565 | 139513 | 558052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 2216072 | 443214 | 1772858 | 2651934 | 530387 | 2121547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 932686 | 186537 | 746149 | 946626 | 189325 | 757301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 24102776 | 4820555 | 19282221 | 31471446 | 6294289 | 25177157 | 48673735 | 9734747 | 38938988 | 24102776 | 4820555 | 19282221 | 31471446 | 6294289 | 25177157 | 0 | 0 | ION Newco Corp | TRUE
NT10BIX5570133 | CCI | 2012 | Q3 | Q3 - 2012 | 5598140 | 1119628 | 4478512 | 7120560 | 1424112 | 5696448 | 7494680 | 1498936 | 5995744 | 37772032 | 7554407 | 30217626 | 20082680 | 4016536 | 16066144 | 23247659 | 4649532 | 18598127 | 1030440 | 206088 | 824352 | 659870 | 131974 | 527896 | 780784 | 156157 | 624627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116122 | 623224 | 2492897 | 2532516 | 506503 | 2026013 | 2859730 | 571946 | 2287784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157001 | 231400 | 925601 | 1745565 | 349113 | 1396452 | 1830626 | 366125 | 1464501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 32141191 | 6428238 | 25712953 | 36213479 | 7242696 | 28970783 | 48673735 | 9734747 | 38938988 | 32141191 | 6428238 | 25712953 | 36213479 | 7242696 | 28970783 | 0 | 0 | ION Newco Corp | TRUE
NT10BIX5570133 | CCI | 2012 | Q4 | Q4 - 2012 | 8746002 | 1749200 | 6996801 | 8093945 | 1618789 | 6475156 | 8353302 | 1670661 | 6682641 | 32512638 | 6502528 | 26010111 | 21252249 | 4250449 | 17001800 | 24612850 | 4922570 | 19690280 | 1023794 | 204759 | 819035 | 778074 | 155615 | 622459 | 870469 | 174094 | 696375 | 24093 | 4819 | 19274 | 28654 | 5731 | 22923 | 28654 | 5731 | 22923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3370766 | 674153 | 2696613 | 2853908 | 570782 | 2283126 | 3074017 | 614803 | 2459214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2996442 | 599288 | 2397154 | 2584734 | 516947 | 2067787 | 2888979 | 577796 | 2311183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 35591564 | 7118313 | 28473251 | 39828271 | 7965655 | 31862616 | 48673735 | 9734747 | 38938988 | 35591564 | 7118313 | 28473251 | 39828271 | 7965655 | 31862616 | 0 | 0 | ION Newco Corp | TRUE
NT10BIX5570133 | CCI | 2013 | Q1 | Q1 - 2013 | 8746002 | 1749200 | 6996801 | 8464485 | 1692897 | 6771588 | 8633395 | 1726679 | 6906716 | 32512638 | 6502528 | 26010111 | 26163620 | 5232724 | 20930896 | 29973031 | 5994606 | 23978425 | 1023794 | 204759 | 819035 | 910736 | 182147 | 728589 | 978571 | 195714 | 782857 | 24093 | 4819 | 19274 | 24093 | 4819 | 19274 | 24093 | 4819 | 19274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3370766 | 674153 | 2696613 | 3072536 | 614507 | 2458029 | 3251474 | 650294 | 2601180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2996442 | 599288 | 2397154 | 2758475 | 551695 | 2206780 | 2901255 | 580251 | 2321004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 41393945 | 8278789 | 33115156 | 45761819 | 9152363 | 36609456 | 48673735 | 9734747 | 38938988 | 41393945 | 8278789 | 33115156 | 45761819 | 9152363 | 36609456 | 0 | 0 | ION Newco Corp | TRUE
NT10BIX5570133 | CCI | 2013 | Q2 | Q2 - 2013 | 8746002 | 1749200 | 6996801 | 8561001 | 1712200 | 6848801 | 8746002 | 1749200 | 6996801 | 32512638 | 6502528 | 26010111 | 29588668 | 5917734 | 23670934 | 32512638 | 6502528 | 26010111 | 1023794 | 204759 | 819035 | 728794 | 145759 | 583035 | 908794 | 181759 | 727035 | 24093 | 4819 | 19274 | 24093 | 4819 | 19274 | 24093 | 4819 | 19274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3370766 | 674153 | 2696613 | 3196541 | 639308 | 2557233 | 3370766 | 674153 | 2696613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2996442 | 599288 | 2397154 | 2286269 | 457254 | 1829015 | 2996442 | 599288 | 2397154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 44385366 | 8877074 | 35508292 | 48558735 | 9711747 | 38846988 | 48673735 | 9734747 | 38938988 | 44385366 | 8877074 | 35508292 | 48558735 | 9711747 | 38846988 | 0 | 0 | ION Newco Corp | TRUE
NT10BIX5570133 | CCI | 2013 | Q3 | Q3 - 2013 | 8432785 | 1686557 | 6746228 | 9581179 | 2834951 | 6746228 | 9581179 | 2834951 | 6746228 | 32512638 | 6502527 | 26010111 | 31885720 | 5875609 | 26010111 | 31885719 | 5875608 | 26010111 | 1023794 | 204759 | 819035 | 1290178 | 471143 | 819035 | 1290178 | 471143 | 819035 | 24093 | 4819 | 19274 | 31154 | 11880 | 19274 | 31154 | 11880 | 19274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3370766 | 674153 | 2696613 | 4129468 | 1432855 | 2696613 | 4129468 | 1432855 | 2696613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3309659 | 661932 | 2647727 | 5027840 | 2380113 | 2647727 | 5027840 | 2380113 | 2647727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48673735 | 9734747 | 38938988 | 51945539 | 13006551 | 38938988 | 51945538 | 13006550 | 38938988 | 48673735 | 9734747 | 38938988 | 51945539 | 13006551 | 38938988 | 51945538 | 13006550 | 38938988 | 0 | 0 | ION Newco Corp | TRUE
NT10BIX5570135 | CCI | 2010 | Q4 | Q4 - 2010 | 29211582 | 8888681 | 20322901 | 0 | 0 | 0 | 3505390 | 955384 | 2550006 | 93402141 | 18671661 | 74730480 | 0 | 0 | 0 | 2802064 | 763694 | 2038370 | 12479100 | 7394000 | 5085100 | 468534 | 229900 | 238634 | 2373155 | 646796 | 1726359 | 1350000 | 0 | 1350000 | 0 | 0 | 0 | 225000 | 61323 | 163677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 92793 | 0 | 92793 | 2239049 | 610246 | 1628803 | 6109850 | 2869099 | 3240751 | 25277 | 0 | 25277 | 582635 | 158795 | 423840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 586604 | 229900 | 356704 | 11727293 | 3196238 | 8531055 | 158416521 | 43175940 | 115240581 | 586604 | 229900 | 356704 | 11727293 | 3196238 | 8531055 | 0 | 0 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | CCI | 2011 | Q1 | Q1 - 2011 | 29211582 | 8888681 | 20322901 | 0 | 0 | 0 | 3505390 | 955384 | 2550006 | 93402141 | 18671661 | 74730480 | 0 | 0 | 0 | 2802064 | 763694 | 2038370 | 12479100 | 7394000 | 5085100 | 778136 | 320980 | 457156 | 2373155 | 646796 | 1726359 | 1350000 | 0 | 1350000 | 0 | 0 | 0 | 225000 | 61323 | 163677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 157905 | 0 | 157905 | 2239049 | 610246 | 1628803 | 6109850 | 2869099 | 3240751 | 169531 | 0 | 169531 | 582635 | 158795 | 423840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 1105572 | 320980 | 784592 | 11727293 | 3196238 | 8531055 | 158416521 | 43175940 | 115240581 | 1105572 | 320980 | 784592 | 11727293 | 3196238 | 8531055 | 0 | 0 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | CCI | 2011 | Q2 | Q2 - 2011 | 29211582 | 8888681 | 20322901 | 1812078 | 1812078 | 0 | 6124156 | 4124156 | 2000000 | 93402141 | 18671661 | 74730480 | 1032787 | 1032787 | 0 | 4665575 | 2065574 | 2600000 | 12479100 | 7394000 | 5085100 | 1553924 | 561960 | 991964 | 4617848 | 1633920 | 2983928 | 1350000 | 0 | 1350000 | 0 | 0 | 0 | 225000 | 61323 | 163677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 298202 | 0 | 298202 | 1699404 | 480000 | 1219404 | 6109850 | 2869099 | 3240751 | 169531 | 0 | 169531 | 489062 | 0 | 489062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 4866522 | 3406825 | 1459697 | 17821045 | 8364973 | 9456071 | 158416521 | 43175940 | 115240581 | 4866522 | 3406825 | 1459697 | 17821045 | 8364973 | 9456071 | 0 | 0 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | CCI | 2011 | Q3 | Q3 - 2011 | 29211582 | 8888681 | 20322901 | 5763723 | 2279112 | 3484611 | 6758413 | 2566882 | 4191531 | 93402141 | 18671661 | 74730480 | 5510629 | 2627451 | 2883178 | 14885973 | 4089036 | 10796937 | 12479100 | 7394000 | 5085100 | 2920378 | 1201944 | 1718434 | 4241750 | 1814232 | 2427517 | 1350000 | 0 | 1350000 | 0 | 0 | 0 | 337500 | 0 | 337500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 1431855 | 0 | 1431855 | 2640552 | 0 | 2640552 | 6109850 | 2869099 | 3240751 | 812329 | 38225 | 774104 | 2983202 | 835297 | 2147905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 16438914 | 6146732 | 10292182 | 31847390 | 9305447 | 22541942 | 158416521 | 43175940 | 115240581 | 16438914 | 6146732 | 10292182 | 31847390 | 9305447 | 22541942 | 0 | 0 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | CCI | 2011 | Q4 | Q4 - 2011 | 29211582 | 8888681 | 20322901 | 5794572 | 2278318 | 3516254 | 6337552 | 2635209 | 3702343 | 93402141 | 18671661 | 74730480 | 11579661 | 3118029 | 8461632 | 22436345 | 6638089 | 15798256 | 12479100 | 7394000 | 5085100 | 4740495 | 1506773 | 3233722 | 4953956 | 1676904 | 3277052 | 1350000 | 0 | 1350000 | 411089 | 0 | 411089 | 880589 | 0 | 880589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 2728922 | 0 | 2728922 | 4597697 | 285061 | 4312636 | 6109850 | 2869099 | 3240751 | 2097414 | 38225 | 2059189 | 2437602 | 133478 | 2304124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 27352153 | 6941345 | 20410808 | 41643741 | 11368741 | 30275000 | 158416521 | 43175940 | 115240581 | 27352153 | 6941345 | 20410808 | 41643741 | 11368741 | 30275000 | 0 | 0 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | CCI | 2012 | Q1 | Q1 - 2012 | 29211582 | 8888681 | 20322901 | 4206430 | 1953252 | 2253178 | 11638946 | 4276135 | 7362811 | 93402141 | 18671661 | 74730480 | 25038578 | 6254951 | 18783627 | 48053404 | 11844779 | 36208625 | 12479100 | 7394000 | 5085100 | 4795487 | 2279328 | 2516159 | 5299273 | 2328029 | 2971244 | 1350000 | 0 | 1350000 | 411089 | 0 | 411089 | 411089 | 0 | 411089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 3129924 | 0 | 3129924 | 4717629 | 0 | 4717629 | 6109850 | 2869099 | 3240751 | 4276775 | 602662 | 3674113 | 5622500 | 1574300 | 4048200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 41858283 | 11090193 | 30768090 | 75742841 | 20023243 | 55719598 | 158416521 | 43175940 | 115240581 | 41858283 | 11090193 | 30768090 | 75742841 | 20023243 | 55719598 | 0 | 0 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | CCI | 2012 | Q2 | Q2 - 2012 | 29211582 | 8888681 | 20322901 | 4678794 | 2347814 | 2330980 | 14815235 | 5543353 | 9271882 | 93402141 | 18671661 | 74730480 | 50545456 | 11092420 | 39453035 | 73018602 | 16272508 | 56746093 | 12479100 | 7394000 | 5085100 | 5288361 | 2583471 | 2704891 | 5911160 | 2770713 | 3140447 | 1350000 | 0 | 1350000 | 411089 | 0 | 411089 | 874939 | 0 | 874939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 4562776 | 0 | 4562776 | 5577995 | 0 | 5577995 | 6109850 | 2869099 | 3240751 | 5373416 | 1126154 | 4247262 | 8350778 | 2092599 | 6258179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 70859892 | 17149859 | 53710033 | 108548709 | 26679173 | 81869535 | 158416521 | 43175940 | 115240581 | 70859892 | 17149859 | 53710033 | 108548709 | 26679173 | 81869535 | 0 | 0 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | CCI | 2012 | Q3 | Q3 - 2012 | 29211582 | 8888681 | 20322901 | 8136854 | 2157470 | 5979383 | 10695380 | 4262087 | 6433292 | 93402141 | 18671661 | 74730480 | 68603324 | 18064883 | 50538441 | 90052997 | 22471838 | 67581159 | 12479100 | 7394000 | 5085100 | 5891365 | 2788417 | 3102948 | 6255225 | 2937330 | 3317894 | 1350000 | 0 | 1350000 | 874939 | 0 | 874939 | 874939 | 0 | 874939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 5493694 | 0 | 5493694 | 6384968 | 0 | 6384968 | 6109850 | 2869099 | 3240751 | 6968391 | 1861537 | 5106854 | 7645188 | 2064683 | 5580505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 95968567 | 24872307 | 71096259 | 121908697 | 31735938 | 90172757 | 158416521 | 43175940 | 115240581 | 95968567 | 24872307 | 71096259 | 121908697 | 31735938 | 90172757 | 0 | 0 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | CCI | 2012 | Q4 | Q4 - 2012 | 29211582 | 8888681 | 20322901 | 9968741 | 3457705 | 6511036 | 15206802 | 4136249 | 11070553 | 93402141 | 18671661 | 74730480 | 83965737 | 22141818 | 61823919 | 93964986 | 27120905 | 66844081 | 12479100 | 7394000 | 5085100 | 6465196 | 3213737 | 3251459 | 6868273 | 3416727 | 3451546 | 1350000 | 0 | 1350000 | 935972 | 0 | 935972 | 1053965 | 0 | 1053965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 6290079 | 0 | 6290079 | 7372122 | 0 | 7372122 | 6109850 | 2869099 | 3240751 | 7685095 | 2086681 | 5598414 | 7814195 | 2142763 | 5671432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 115310820 | 30899941 | 84410879 | 132280343 | 36816644 | 95463699 | 158416521 | 43175940 | 115240581 | 115310820 | 30899941 | 84410879 | 132280343 | 36816644 | 95463699 | 0 | 0 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | CCI | 2013 | Q1 | Q1 - 2013 | 29211582 | 8888681 | 20322901 | 14099689 | 4569826 | 9529863 | 16434107 | 5721602 | 10712505 | 93402141 | 18671661 | 74730480 | 94550651 | 27604657 | 66945994 | 107477715 | 30043469 | 77434246 | 12479100 | 7394000 | 5085100 | 6754623 | 3407199 | 3347424 | 7156015 | 3642882 | 3513133 | 1350000 | 0 | 1350000 | 1257956 | 0 | 1257956 | 1257956 | 0 | 1257956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15550369 | 5039020 | 10511349 | 7297717 | 0 | 7297717 | 8126040 | 0 | 8126040 | 6109850 | 2869099 | 3240751 | 8261896 | 2412935 | 5848960 | 8336476 | 2457147 | 5879329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313479 | 313479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416521 | 43175940 | 115240581 | 132222532 | 37994617 | 94227914 | 148788309 | 41865100 | 106923209 | 158416521 | 43175940 | 115240581 | 132222532 | 37994617 | 94227914 | 148788309 | 41865100 | 106923209 | 0 | 0 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | CCI | 2013 | Q2 | Q2 - 2013 | 18619128 | 5862684 | 12756444 | 15208206 | 4950874 | 10257332 | 18619128 | 5862684 | 12756444 | 113689497 | 30971125 | 82718372 | 104922047 | 29026841 | 75895206 | 113689497 | 30971125 | 82718372 | 7479147 | 3811988 | 3667160 | 7015499 | 3578250 | 3437249 | 7429147 | 3798338 | 3630810 | 1350000 | 0 | 1350000 | 1257956 | 0 | 1257956 | 1350000 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8749198 | 157764 | 8591434 | 8114213 | 0 | 8114213 | 8749198 | 157764 | 8591434 | 8529550 | 2372379 | 6157170 | 8529550 | 2523068 | 6006482 | 8529550 | 2372379 | 6157170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416520 | 43175940 | 115240580 | 145047471 | 40079033 | 104968438 | 158366520 | 43162290 | 115204230 | 158416520 | 43175940 | 115240580 | 145047471 | 40079033 | 104968438 | 158366520 | 43162290 | 115204230 | 0 | 0 | Information Technology, Maryland Department of | TRUE
NT10BIX5570135 | CCI | 2013 | Q3 | Q3 - 2013 | 18291208 | 6020448 | 12270761 | 18291208 | 6020448 | 12270761 | 18291208 | 6020448 | 12270761 | 114175181 | 30971125 | 83204056 | 114175181 | 30971125 | 83204056 | 114175181 | 30971125 | 83204056 | 7479147 | 3811987 | 3667160 | 7479147 | 3811987 | 3667160 | 7479147 | 3811987 | 3667160 | 1350000 | 0 | 1350000 | 1350000 | 0 | 1350000 | 1350000 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8591434 | 0 | 8591434 | 8591434 | 0 | 8591434 | 8591434 | 0 | 8591434 | 8529550 | 2372380 | 6157170 | 8529550 | 2372380 | 6157170 | 8529550 | 2372380 | 6157170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158416520 | 43175940 | 115240581 | 158416520 | 43175940 | 115240581 | 158416520 | 43175940 | 115240581 | 158416520 | 43175940 | 115240581 | 158416520 | 43175940 | 115240581 | 158416520 | 43175940 | 115240581 | 0 | 0 | Information Technology, Maryland Department of | TRUE
NT10BIX5570136 | CCI | 2010 | Q4 | Q4 - 2010 | 19870336 | 500000 | 19370336 | 0 | 0 | 0 | 203000 | 0 | 203000 | 6570942 | 0 | 6570942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22800563 | 11301200 | 11499363 | 0 | 0 | 0 | 592800 | 442800 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395058 | 863058 | 532000 | 863058 | 863058 | 0 | 903058 | 863058 | 40000 | 251066 | 0 | 251066 | 0 | 0 | 0 | 180000 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 0 | 0 | 0 | 0 | 0 | 0 | 51939135 | 12664258 | 39274877 | 863058 | 863058 | 0 | 1878858 | 1305858 | 573000 | 51939135 | 12664258 | 39274877 | 863058 | 863058 | 0 | 1878858 | 1305858 | 573000 | 2762000 | 0 | GOVNET, INC. | TRUE
NT10BIX5570136 | CCI | 2011 | Q1 | Q1 - 2011 | 19825624 | 500000 | 19325624 | 97851 | 0 | 97851 | 1305149 | 0 | 1305149 | 6561810 | 0 | 6561810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21552560 | 11301200 | 10251360 | 0 | 0 | 0 | 5012800 | 1162800 | 3850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1972059 | 863058 | 1109002 | 653996 | 653996 | 0 | 733996 | 653996 | 80000 | 251066 | 0 | 251065 | 184111 | 0 | 184111 | 270000 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1776017 | 0 | 1776017 | 0 | 0 | 0 | 0 | 0 | 0 | 51939136 | 12664258 | 39274878 | 935958 | 653996 | 281962 | 7321945 | 1816796 | 5505149 | 51939136 | 12664258 | 39274878 | 935958 | 653996 | 281962 | 7321945 | 1816796 | 5505149 | 2762000 | 0 | GOVNET, INC. | TRUE
NT10BIX5570136 | CCI | 2011 | Q2 | Q2 - 2011 | 21655252 | 500000 | 21155252 | 172851 | 75000 | 97851 | 200000 | 75000 | 125000 | 6570942 | 0 | 6570942 | 0 | 0 | 0 | 0 | 0 | 0 | 1125000 | 0 | 1125000 | 0 | 0 | 0 | 375000 | 0 | 375000 | 19870647 | 11301200 | 8569447 | 4413898 | 799200 | 3614698 | 6122200 | 2122200 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395058 | 863058 | 532000 | 547452 | 547452 | 0 | 890202 | 590202 | 300000 | 271066 | 0 | 271066 | 217314 | 0 | 217314 | 290000 | 0 | 290000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 0 | 0 | 0 | 0 | 0 | 0 | 51939135 | 12664258 | 39274877 | 5351515 | 1421652 | 3929863 | 7877402 | 2787402 | 5090000 | 51939135 | 12664258 | 39274877 | 5351515 | 1421652 | 3929863 | 7877402 | 2787402 | 5090000 | 2762000 | 0 | GOVNET, INC. | TRUE
NT10BIX5570136 | CCI | 2011 | Q3 | Q3 - 2011 | 21655252 | 500000 | 21155252 | 1335035 | 33180 | 1301855 | 2115035 | 33180 | 2081855 | 6570942 | 0 | 6570942 | 0 | 0 | 0 | 100000 | 0 | 100000 | 1125000 | 0 | 1125000 | 440179 | 35000 | 405179 | 740179 | 35000 | 705179 | 19870647 | 11301200 | 8569447 | 12154506 | 8458450 | 3696056 | 14806456 | 10410400 | 4396056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1395058 | 863058 | 532000 | 717120 | 411509 | 305611 | 862120 | 456509 | 405611 | 271066 | 0 | 271066 | 287626 | 0 | 287626 | 296626 | 0 | 296626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 0 | 0 | 0 | 11000 | 0 | 11000 | 51939135 | 12664258 | 39274877 | 14934466 | 8938139 | 5996327 | 18931416 | 10935089 | 7996327 | 51939135 | 12664258 | 39274877 | 14934466 | 8938139 | 5996327 | 18931416 | 10935089 | 7996327 | 2762000 | 0 | GOVNET, INC. | TRUE
NT10BIX5570136 | CCI | 2011 | Q4 | Q4 - 2011 | 20007697 | 33180 | 19974517 | 2627667 | 33180 | 2594487 | 6877667 | 33180 | 6844487 | 6570942 | 3262000 | 3308942 | 0 | 0 | 0 | 350000 | 0 | 350000 | 2197000 | 35000 | 2162000 | 804434 | 35000 | 769435 | 1054435 | 35000 | 1019435 | 20023726 | 8562569 | 11461157 | 12565388 | 8562569 | 4002819 | 13365388 | 8562569 | 4802819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687259 | 771509 | 915750 | 896979 | 455759 | 441219 | 1241978 | 500759 | 741219 | 401341 | 0 | 401341 | 297682 | 0 | 297682 | 347682 | 0 | 347682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 0 | 0 | 0 | 0 | 0 | 0 | 51939135 | 12664258 | 39274877 | 17192150 | 9086508 | 8105642 | 23237150 | 9131508 | 14105642 | 51939135 | 12664258 | 39274877 | 17192150 | 9086508 | 8105642 | 23237150 | 9131508 | 14105642 | 2762000 | 0 | GOVNET, INC. | TRUE
NT10BIX5570136 | CCI | 2012 | Q1 | Q1 - 2012 | 20007698 | 33180 | 19974518 | 4558739 | 33180 | 4525559 | 7758739 | 33180 | 7725559 | 6570942 | 3262000 | 3308942 | 271312 | 0 | 271312 | 1109102 | 17790 | 1091312 | 2197000 | 35000 | 2162000 | 1052671 | 35000 | 1017671 | 1412671 | 35000 | 1377671 | 20023726 | 8562569 | 11461157 | 9210778 | 3436116 | 5774662 | 12407316 | 5382654 | 7024662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687259 | 771509 | 915750 | 1252275 | 503571 | 748704 | 1447275 | 548571 | 898704 | 401340 | 0 | 401340 | 343380 | 0 | 343380 | 363380 | 0 | 363380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 52382 | 0 | 52382 | 252382 | 0 | 252382 | 51939135 | 12664258 | 39274877 | 16741537 | 4007867 | 12733670 | 24750865 | 6017195 | 18733670 | 51939135 | 12664258 | 39274877 | 16741537 | 4007867 | 12733670 | 24750865 | 6017195 | 18733670 | 2762000 | 0 | GOVNET, INC. | TRUE
NT10BIX5570136 | CCI | 2012 | Q2 | Q2 - 2012 | 20007698 | 33180 | 19974518 | 5046848 | 33180 | 5013668 | 6606848 | 33180 | 6573668 | 6570942 | 3262000 | 3308942 | 512122 | 4250 | 507872 | 788402 | 30530 | 757872 | 2197000 | 35000 | 2162000 | 1192942 | 35000 | 1157942 | 1549127 | 35000 | 1514127 | 20023726 | 8562569 | 11461157 | 9096091 | 3554886 | 5541204 | 11736227 | 5495022 | 6241205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687259 | 771509 | 915750 | 1346879 | 532446 | 814433 | 1391879 | 547446 | 844432 | 401340 | 0 | 401340 | 349045 | 0 | 349045 | 403416 | 0 | 403416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 111424 | 0 | 111424 | 261424 | 0 | 261424 | 51939135 | 12664258 | 39274877 | 17655351 | 4159762 | 13495588 | 22737323 | 6141178 | 16596144 | 51939135 | 12664258 | 39274877 | 17655351 | 4159762 | 13495588 | 22737323 | 6141178 | 16596144 | 2762000 | 4250 | GOVNET, INC. | TRUE
NT10BIX5570136 | CCI | 2012 | Q3 | Q3 - 2012 | 20007698 | 33180 | 19974518 | 5052711 | 33180 | 5019531 | 7927924 | 33180 | 7894744 | 6570942 | 3262000 | 3308942 | 640600 | 4250 | 636350 | 1034901 | 44420 | 990481 | 2197000 | 35000 | 2162000 | 1333089 | 35000 | 1298089 | 1495397 | 35000 | 1460397 | 20023726 | 8562569 | 11461157 | 11133095 | 5451006 | 5682089 | 11823922 | 5522106 | 6301816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687259 | 771509 | 915750 | 1413513 | 580446 | 833067 | 1516501 | 631634 | 884867 | 401340 | 0 | 401340 | 353507 | 0 | 353507 | 403507 | 0 | 403507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 131562 | 0 | 131562 | 151969 | 0 | 151969 | 51939135 | 12664258 | 39274877 | 20058077 | 6103882 | 13954195 | 24354121 | 6266340 | 18087781 | 51939135 | 12664258 | 39274877 | 20058077 | 6103882 | 13954195 | 24354121 | 6266340 | 18087781 | 2762000 | 4250 | GOVNET, INC. | TRUE
NT10BIX5570136 | CCI | 2012 | Q4 | Q4 - 2012 | 20007698 | 33180 | 19974518 | 6427924 | 33180 | 6394744 | 7076408 | 33180 | 7043228 | 6570942 | 3262000 | 3308942 | 786157 | 4250 | 781907 | 1788921 | 85810 | 1703111 | 2197000 | 35000 | 2162000 | 1501045 | 35000 | 1466045 | 1601832 | 35000 | 1566832 | 20023726 | 8562569 | 11461157 | 11606816 | 5451006 | 6155810 | 12562383 | 5506306 | 7056077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687259 | 771509 | 915750 | 1512114 | 626571 | 885543 | 1593302 | 677759 | 915543 | 401340 | 0 | 401340 | 353167 | 0 | 353167 | 403167 | 0 | 403167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 156912 | 0 | 156912 | 230584 | 0 | 230584 | 51939135 | 12664258 | 39274877 | 22344135 | 6150007 | 16194128 | 25256597 | 6338055 | 18918542 | 51939135 | 12664258 | 39274877 | 22344135 | 6150007 | 16194128 | 25256597 | 6338055 | 18918542 | 2762000 | 44420 | GOVNET, INC. | TRUE
NT10BIX5570136 | CCI | 2013 | Q1 | Q1 - 2013 | 20007698 | 33180 | 19974518 | 6331440 | 33180 | 6298260 | 7331440 | 33180 | 7298260 | 6570942 | 3262000 | 3308942 | 774400 | 4250 | 770150 | 1062350 | 72200 | 990150 | 2197000 | 35000 | 2162000 | 1590351 | 0 | 1590351 | 2000351 | 0 | 2000351 | 20023726 | 8562569 | 11461157 | 11946630 | 5433840 | 6512790 | 12812770 | 5599980 | 7212790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687259 | 771509 | 915750 | 1451271 | 518696 | 932575 | 1522459 | 569884 | 952575 | 401340 | 0 | 401340 | 353507 | 0 | 353507 | 403507 | 0 | 403507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 165132 | 0 | 165132 | 265132 | 0 | 265132 | 51939135 | 12664258 | 39274877 | 22612731 | 5989966 | 16622765 | 25398009 | 6275244 | 19122765 | 51939135 | 12664258 | 39274877 | 22612731 | 5989966 | 16622765 | 25398009 | 6275244 | 19122765 | 2762000 | 58310 | GOVNET, INC. | TRUE
NT10BIX5570136 | CCI | 2013 | Q2 | Q2 - 2013 | 20007698 | 33180 | 19974518 | 6767135 | 33180 | 6733955 | 7711135 | 33180 | 7677955 | 6570942 | 3262000 | 3308942 | 831595 | 23930 | 807665 | 1040348 | 132683 | 907665 | 2197000 | 35000 | 2162000 | 2067276 | 0 | 2067276 | 2267276 | 0 | 2267276 | 20023726 | 8562569 | 11461157 | 12489270 | 5447175 | 7042095 | 13227570 | 5485475 | 7742095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687259 | 771509 | 915750 | 1508125 | 570259 | 937866 | 1553563 | 605697 | 947866 | 401340 | 0 | 401340 | 364703 | 0 | 364703 | 404703 | 0 | 404703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051170 | 0 | 1051170 | 191474 | 0 | 191474 | 197474 | 0 | 197474 | 51939135 | 12664258 | 39274877 | 24219578 | 6074544 | 18145034 | 26402069 | 6257035 | 20145034 | 51939135 | 12664258 | 39274877 | 24219578 | 6074544 | 18145034 | 26402069 | 6257035 | 20145034 | 2762000 | 23930 | GOVNET, INC. | TRUE
NT10BIX5570136 | CCI | 2013 | Q3 | Q3 - 2013 | 17059271 | 33180 | 17026091 | 6770680 | 33180 | 6737500 | 7070680 | 33180 | 7037500 | 4479813 | 821793 | 3658020 | 927577 | 4250 | 923327 | 1371616 | 148289 | 1223327 | 4854785 | 0 | 4854785 | 2625620 | 0 | 2625620 | 2925620 | 0 | 2925620 | 22287483 | 11076276 | 11211207 | 15303596 | 8075370 | 7228226 | 16576771 | 8348545 | 8228226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053091 | 733009 | 1320082 | 1477485 | 539509 | 937976 | 1712860 | 674884 | 1037976 | 604613 | 0 | 604613 | 403694 | 0 | 403694 | 453694 | 0 | 453694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222873 | 0 | 222873 | 197638 | 0 | 197638 | 200638 | 0 | 200638 | 51561929 | 12664258 | 38897671 | 27706290 | 8652309 | 19053981 | 30311879 | 9204898 | 21106981 | 51561929 | 12664258 | 38897671 | 27706290 | 8652309 | 19053981 | 30311879 | 9204898 | 21106981 | 821793 | 4250 | GOVNET, INC. | TRUE
NT10BIX5570136 | CCI | 2013 | Q4 | Q4 - 2013 | 17059271 | 33180 | 17026091 | 6775491 | 33180 | 6742311 | 7479912 | 37601 | 7442311 | 4479813 | 821793 | 3658020 | 1000083 | 59050 | 941033 | 1476452 | 155419 | 1321033 | 4854785 | 0 | 4854785 | 2964655 | 0 | 2964655 | 3318655 | 0 | 3318655 | 22287483 | 11076276 | 11211207 | 16036447 | 8552745 | 7483702 | 17766822 | 8783120 | 8983702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053091 | 733009 | 1320082 | 1569628 | 589947 | 979682 | 1755003 | 725321 | 1029682 | 604613 | 0 | 604613 | 409714 | 0 | 409714 | 419714 | 0 | 419714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222873 | 0 | 222873 | 205826 | 0 | 205826 | 211826 | 0 | 211826 | 51561929 | 12664258 | 38897671 | 28961844 | 9234922 | 19726923 | 32428384 | 9701461 | 22726923 | 51561929 | 12664258 | 38897671 | 28961844 | 9234922 | 19726923 | 32428384 | 9701461 | 22726923 | 821793 | 59050 | GOVNET, INC. | TRUE
NT10BIX5570138 | CCI | 2010 | Q4 | Q4 - 2010 | 1464565 | 451993 | 1012572 | 0 | 0 | 0 | 410078 | 126558 | 283520 | 12318000 | 3801573 | 8516427 | 0 | 0 | 0 | 3449040 | 1064440 | 2384600 | 1574266 | 485849 | 1088417 | 327608 | 101106 | 226502 | 362989 | 112025 | 250964 | 80000 | 24690 | 53310 | 0 | 0 | 0 | 22400 | 6913 | 15487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 0 | 0 | 0 | 494405 | 152583 | 341822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 23751 | 53208 | 3623 | 1118 | 2505 | 21549 | 6650 | 14899 | 17279523 | 5332795 | 11944728 | 331231 | 102224 | 229007 | 4760461 | 1469169 | 3291292 | 17279523 | 5332795 | 11944728 | 331231 | 102224 | 229007 | 4760461 | 1469169 | 3291292 | 0 | 0 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | CCI | 2011 | Q1 | Q1 - 2011 | 1464565 | 451993 | 1012572 | 210595 | 94843 | 115752 | 322304 | 98948 | 223356 | 12318000 | 3801573 | 8516427 | 0 | 0 | 0 | 2709960 | 826538 | 1883422 | 1574266 | 485859 | 1088417 | 381850 | 36994 | 344856 | 418843 | 48092 | 370751 | 80000 | 24690 | 53310 | 0 | 0 | 0 | 2350 | 725 | 1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 365075 | 163001 | 202074 | 463457 | 142281 | 321176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 23751 | 53208 | 0 | 0 | 0 | 10699 | 3274 | 7425 | 17279523 | 5332805 | 11944728 | 957520 | 294838 | 662682 | 3927613 | 1119858 | 2807755 | 17279523 | 5332805 | 11944728 | 957520 | 294838 | 662682 | 3927613 | 1119858 | 2807755 | 0 | 0 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | CCI | 2011 | Q2 | Q2 - 2011 | 1464565 | 451993 | 1012572 | 210595 | 94843 | 115752 | 1200000 | 360000 | 840000 | 12318000 | 3801573 | 8516427 | 0 | 0 | 0 | 250000 | 75000 | 175000 | 1574266 | 485849 | 1088417 | 630593 | 214644 | 415949 | 645782 | 193735 | 452047 | 80000 | 24690 | 55310 | 2775 | 805 | 1970 | 15000 | 4500 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1636124 | 458920 | 1177204 | 1700000 | 510000 | 1190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 23751 | 53208 | 0 | 0 | 0 | 0 | 0 | 0 | 17279523 | 5332795 | 11946728 | 2480087 | 769212 | 1710875 | 3810782 | 1143235 | 2667547 | 17279523 | 5332795 | 11946728 | 2480087 | 769212 | 1710875 | 3810782 | 1143235 | 2667547 | 0 | 0 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | CCI | 2011 | Q3 | Q3 - 2011 | 1464565 | 451993 | 1012572 | 211417 | 95665 | 115752 | 992847 | 307783 | 685064 | 12318000 | 3801573 | 8516427 | 331698 | 102181 | 229517 | 1503992 | 466238 | 1037754 | 1574266 | 485849 | 1088417 | 675722 | 233036 | 442686 | 720722 | 223424 | 497298 | 80000 | 24690 | 55310 | 2775 | 805 | 1970 | 40000 | 12400 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1848207 | 522545 | 1325662 | 1848207 | 522545 | 1325662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 23751 | 53208 | 0 | 0 | 0 | 0 | 0 | 0 | 17279523 | 5332795 | 11946728 | 3069819 | 954232 | 2115587 | 5105768 | 1532390 | 3573378 | 17279523 | 5332795 | 11946728 | 3069819 | 954232 | 2115587 | 5105768 | 1532390 | 3573378 | 0 | 0 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | CCI | 2011 | Q4 | Q4 - 2011 | 1464565 | 451993 | 1012572 | 210595 | 64934 | 145661 | 597819 | 184327 | 413492 | 12318000 | 3801573 | 8516427 | 1482127 | 456988 | 1025139 | 4967143 | 1531532 | 3435611 | 1574266 | 485849 | 1088417 | 710674 | 219124 | 491550 | 750626 | 231442 | 519184 | 80000 | 24690 | 55310 | 13493 | 4160 | 9333 | 40000 | 12333 | 27667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1834935 | 565770 | 1269165 | 1834935 | 565770 | 1269165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 23751 | 53208 | 0 | 0 | 0 | 0 | 0 | 0 | 17279523 | 5332795 | 11946728 | 4251824 | 1310976 | 2940848 | 8190523 | 2525404 | 5665119 | 17279523 | 5332795 | 11946728 | 4251824 | 1310976 | 2940848 | 8190523 | 2525404 | 5665119 | 0 | 0 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | CCI | 2012 | Q1 | Q1 - 2012 | 1464565 | 451993 | 1012572 | 470595 | 172843 | 297752 | 1318109 | 395433 | 922676 | 12318000 | 3801573 | 8516427 | 4384398 | 1317978 | 3066420 | 8253060 | 2475918 | 5777142 | 1574266 | 485849 | 1088417 | 770297 | 252734 | 517563 | 830300 | 272338 | 557962 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 40000 | 12333 | 27667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 0 | 76959 | 4182 | 0 | 4182 | 4182 | 0 | 4182 | 17279523 | 5309044 | 11970479 | 7507099 | 2291115 | 5215984 | 12297972 | 3695953 | 8602019 | 17279523 | 5309044 | 11970479 | 7507099 | 2291115 | 5215984 | 12297972 | 3695953 | 8602019 | 0 | 0 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | CCI | 2012 | Q2 | Q2 - 2012 | 1464565 | 451993 | 1012572 | 477789 | 175001 | 302788 | 525000 | 189000 | 336000 | 12318000 | 3801573 | 8516427 | 9079025 | 2726366 | 6352659 | 11979025 | 3597215 | 8381810 | 1574266 | 485849 | 1088417 | 827735 | 281424 | 546311 | 1177439 | 365006 | 812433 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 40000 | 12333 | 27667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 23751 | 53208 | 4182 | 0 | 4182 | 4182 | 0 | 4182 | 17279523 | 5332795 | 11946728 | 12266358 | 3730351 | 8536007 | 15577967 | 4703485 | 10874482 | 17279523 | 5332795 | 11946728 | 12266358 | 3730351 | 8536007 | 15577967 | 4703485 | 10874482 | 0 | 0 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | CCI | 2012 | Q3 | Q3 - 2012 | 1464565 | 451993 | 1012572 | 477789 | 175002 | 302787 | 600000 | 185160 | 414840 | 12317820 | 3801573 | 8516247 | 11425612 | 3430342 | 7995270 | 11648111 | 3594607 | 8053504 | 1574266 | 485849 | 1088417 | 989413 | 333217 | 656196 | 1125000 | 347175 | 777825 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 80000 | 24690 | 55310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 0 | 76959 | 11012 | 0 | 11012 | 11012 | 0 | 11012 | 17279343 | 5309044 | 11970299 | 14781453 | 4486121 | 10295332 | 15316444 | 4691563 | 10624881 | 17279343 | 5309044 | 11970299 | 14781453 | 4486121 | 10295332 | 15316444 | 4691563 | 10624881 | 0 | 0 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | CCI | 2012 | Q4 | Q4 - 2012 | 1464565 | 451993 | 1012572 | 477789 | 175001 | 302788 | 925000 | 285473 | 639527 | 12317820 | 3801573 | 8516247 | 11425612 | 3430342 | 7995270 | 11925000 | 3680339 | 8244661 | 1574266 | 485849 | 1088417 | 1017198 | 333217 | 683981 | 1275000 | 393490 | 881510 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 80000 | 24690 | 55310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 0 | 76959 | 11012 | 0 | 11012 | 11012 | 0 | 11012 | 17279343 | 5309044 | 11970299 | 14809238 | 4486120 | 10323118 | 16068333 | 4923923 | 11144410 | 17279343 | 5309044 | 11970299 | 14809238 | 4486120 | 10323118 | 16068333 | 4923923 | 11144410 | 0 | 0 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | CCI | 2013 | Q1 | Q1 - 2013 | 1464565 | 451993 | 1012572 | 477789 | 175001 | 302788 | 1000000 | 308600 | 691400 | 12317820 | 3801573 | 8516247 | 11725612 | 3730342 | 7995270 | 12000000 | 3816000 | 8184000 | 1574266 | 485849 | 1088417 | 1445569 | 467732 | 977837 | 1525000 | 470615 | 1054385 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 80000 | 24690 | 55310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 0 | 76959 | 11012 | 0 | 11012 | 11012 | 0 | 11012 | 17279343 | 5309044 | 11970299 | 15537609 | 4920635 | 10616974 | 16468333 | 5159836 | 11308497 | 17279343 | 5309044 | 11970299 | 15537609 | 4920635 | 10616974 | 16468333 | 5159836 | 11308497 | 0 | 0 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | CCI | 2013 | Q2 | Q2 - 2013 | 1464565 | 451993 | 1012572 | 477789 | 175001 | 302788 | 477789 | 175001 | 302788 | 12317820 | 3801573 | 8516247 | 11725612 | 3730342 | 7995270 | 13122705 | 4002425 | 9120280 | 1574266 | 485849 | 1088417 | 1484290 | 484835 | 999455 | 1783222 | 584058 | 1199164 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 25306 | 7629 | 17677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 0 | 76959 | 11012 | 0 | 11012 | 18000 | 0 | 18000 | 17279343 | 5309044 | 11970299 | 15576330 | 4937738 | 10638592 | 17279343 | 5309044 | 11970299 | 17279343 | 5309044 | 11970299 | 15576330 | 4937738 | 10638592 | 17279343 | 5309044 | 11970299 | 0 | 0 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | CCI | 2013 | Q3 | Q3 - 2013 | 1464565 | 451993 | 1012572 | 477789 | 175001 | 302788 | 477789 | 175001 | 302788 | 12317820 | 3801573 | 8516247 | 12352277 | 3692203 | 8660074 | 12834856 | 3806977 | 9027879 | 1574266 | 485849 | 1088417 | 1590630 | 519934 | 1070696 | 1590630 | 519934 | 1070696 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 25306 | 7629 | 17677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 0 | 76959 | 13426 | 0 | 13426 | 41674 | 0 | 41674 | 17279343 | 5309044 | 11970299 | 16311749 | 4934698 | 11377051 | 16822576 | 5049472 | 11773104 | 17279343 | 5309044 | 11970299 | 16311749 | 4934698 | 11377051 | 16822576 | 5049472 | 11773104 | 0 | 0 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570138 | CCI | 2013 | Q4 | Q4 - 2013 | 1464565 | 451993 | 1012572 | 477789 | 175001 | 302788 | 477789 | 175001 | 302788 | 12317820 | 3801573 | 8516247 | 12834856 | 3968952 | 8865904 | 12834856 | 3968952 | 8865904 | 1574266 | 485849 | 1088417 | 1590630 | 519934 | 1070696 | 1590630 | 519934 | 1070696 | 80000 | 24690 | 55310 | 25306 | 7629 | 17677 | 25306 | 7629 | 17677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1765733 | 544939 | 1220794 | 1852321 | 539931 | 1312390 | 1852321 | 539931 | 1312390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76959 | 0 | 76959 | 13426 | 0 | 13426 | 13426 | 0 | 13426 | 17279343 | 5309044 | 11970299 | 16794328 | 5211447 | 11582881 | 16794328 | 5211447 | 11582881 | 17279343 | 5309044 | 11970299 | 16794328 | 5211447 | 11582881 | 16794328 | 5211447 | 11582881 | 0 | 0 | Region 18 Education Svc Ctr. | TRUE
NT10BIX5570139 | CCI | 2010 | Q4 | Q4 - 2010 | 800000 | 160000 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 20427522 | 4085504 | 16342018 | 234766 | 46953 | 187813 | 617350 | 123470 | 493880 | 640161 | 128032 | 512129 | 153633 | 30727 | 122906 | 249663 | 49933 | 199730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8821039 | 1764208 | 7056831 | 1534014 | 306803 | 1227211 | 2205260 | 441052 | 1764208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 14000 | 56000 | 3600 | 720 | 2880 | 3600 | 720 | 2880 | 30758722 | 6151744 | 24606978 | 1926013 | 385203 | 1540810 | 3075873 | 615175 | 2460698 | 30758722 | 6151744 | 24606978 | 1926013 | 385203 | 1540810 | 3075873 | 615175 | 2460698 | 0 | 0 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | CCI | 2011 | Q1 | Q1 - 2011 | 800000 | 160000 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 20427522 | 4085504 | 16342018 | 454703 | 90941 | 363762 | 1113817 | 222763 | 891054 | 640161 | 128032 | 512129 | 291550 | 58310 | 233240 | 461550 | 92310 | 369240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8821039 | 1764208 | 7056831 | 3374666 | 674933 | 2699733 | 4574666 | 914933 | 3659733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 14000 | 56000 | 5800 | 1160 | 4640 | 7900 | 1580 | 6320 | 30758722 | 6151744 | 24606978 | 4126719 | 825344 | 3301375 | 6157933 | 1231586 | 4926347 | 30758722 | 6151744 | 24606978 | 4126719 | 825344 | 3301375 | 6157933 | 1231586 | 4926347 | 0 | 1716 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | CCI | 2011 | Q2 | Q2 - 2011 | 800000 | 160000 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 20427522 | 4085504 | 16342018 | 2269992 | 453998 | 1815994 | 5269992 | 1053998 | 4215993 | 640161 | 128032 | 512129 | 405820 | 81164 | 324656 | 555820 | 111164 | 444656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8821039 | 1764208 | 7056831 | 5730837 | 1146169 | 4584668 | 7580837 | 1516167 | 6064670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 14000 | 56000 | 7600 | 1520 | 6080 | 10400 | 2080 | 8320 | 30758722 | 6151744 | 24606978 | 8414249 | 1682851 | 6731398 | 13417049 | 2683409 | 10733639 | 30758722 | 6151744 | 24606978 | 8414249 | 1682851 | 6731398 | 13417049 | 2683409 | 10733639 | 0 | 3432 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | CCI | 2011 | Q3 | Q3 - 2011 | 800000 | 160000 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 20427522 | 4085504 | 16342018 | 5361601 | 1072320 | 4289281 | 7361601 | 1472320 | 5889281 | 640161 | 128032 | 512129 | 553534 | 110707 | 442827 | 765534 | 153107 | 612427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8821039 | 1764208 | 7056831 | 6526199 | 1305240 | 5220959 | 7276199 | 1455240 | 5820959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 14000 | 56000 | 9400 | 1880 | 7520 | 10400 | 2080 | 8320 | 30758722 | 6151744 | 24606978 | 12450734 | 2490147 | 9960587 | 15413734 | 3082747 | 12330987 | 30758722 | 6151744 | 24606978 | 12450734 | 2490147 | 9960587 | 15413734 | 3082747 | 12330987 | 0 | 0 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | CCI | 2011 | Q4 | Q4 - 2011 | 800000 | 160000 | 640000 | 0 | 0 | 0 | 800000 | 160000 | 640000 | 20427522 | 4085504 | 16342018 | 9222293 | 1844459 | 7377834 | 12222293 | 2444459 | 9777834 | 640161 | 128032 | 512129 | 893245 | 178649 | 714596 | 1168245 | 233649 | 934596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8821039 | 1764208 | 7056831 | 6972344 | 1394469 | 5577875 | 7472344 | 1494469 | 5977875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 14000 | 56000 | 8800 | 1760 | 7040 | 9800 | 1960 | 7840 | 30758722 | 6151744 | 24606978 | 17096682 | 3419337 | 13677345 | 21672682 | 4334537 | 17338145 | 30758722 | 6151744 | 24606978 | 17096682 | 3419337 | 13677345 | 21672682 | 4334537 | 17338145 | 0 | 0 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | CCI | 2012 | Q1 | Q1 - 2012 | 799970 | 159994 | 639976 | 0 | 0 | 0 | 799970 | 159994 | 639976 | 19341835 | 3868367 | 15473468 | 10811734 | 2162347 | 8649387 | 13011734 | 2602347 | 10409387 | 1923334 | 384667 | 1538667 | 1102181 | 220436 | 881745 | 1352181 | 270436 | 1081745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8673583 | 1734717 | 6938866 | 7802210 | 1560442 | 6241768 | 8302210 | 1660442 | 6641768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 4000 | 16000 | 8800 | 1760 | 7040 | 8800 | 1760 | 7040 | 30758722 | 6151745 | 24606977 | 19724925 | 3944985 | 15779940 | 23474895 | 4694979 | 18779916 | 30758722 | 6151745 | 24606977 | 19724925 | 3944985 | 15779940 | 23474895 | 4694979 | 18779916 | 0 | 0 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | CCI | 2012 | Q2 | Q2 - 2012 | 799970 | 159994 | 639976 | 799770 | 159954 | 639816 | 799770 | 159954 | 639816 | 19341835 | 3868367 | 15473468 | 14057427 | 2811485 | 11245941 | 15257427 | 3051485 | 12205942 | 1923334 | 384667 | 1538667 | 1375527 | 275106 | 1100422 | 1625528 | 325106 | 1300422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8673583 | 1734717 | 6938866 | 8224576 | 1644915 | 6579661 | 8424576 | 1684915 | 6739661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 4000 | 16000 | 9000 | 1800 | 7200 | 9000 | 1800 | 7200 | 30758722 | 6151745 | 24606977 | 24466300 | 4893260 | 19573040 | 26116301 | 5223260 | 20893041 | 30758722 | 6151745 | 24606977 | 24466300 | 4893260 | 19573040 | 26116301 | 5223260 | 20893041 | 0 | 0 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | CCI | 2012 | Q3 | Q3 - 2012 | 799970 | 159994 | 639976 | 799770 | 159954 | 639816 | 799770 | 159954 | 639816 | 19341835 | 3868367 | 15473468 | 15073977 | 3014795 | 12059181 | 15573638 | 3114728 | 12458910 | 1923334 | 384667 | 1538667 | 1526409 | 305282 | 1221127 | 1676409 | 335282 | 1341127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8673583 | 1734717 | 6938866 | 8334310 | 1666862 | 6667448 | 8409310 | 1681862 | 6727448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 4000 | 16000 | 9000 | 1800 | 7200 | 10000 | 2000 | 8000 | 30758722 | 6151745 | 24606977 | 25743466 | 5148693 | 20594772 | 26469127 | 5293826 | 21175301 | 30758722 | 6151745 | 24606977 | 25743466 | 5148693 | 20594772 | 26469127 | 5293826 | 21175301 | 240000 | 303384 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | CCI | 2012 | Q4 | Q4 - 2012 | 799970 | 159994 | 639976 | 799770 | 159954 | 639816 | 799770 | 159954 | 639816 | 19341835 | 3868367 | 15473468 | 15293389 | 3058678 | 12234711 | 15643389 | 3128678 | 12514711 | 1923334 | 384667 | 1538667 | 1621053 | 324211 | 1296842 | 1696053 | 339211 | 1356842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8673583 | 1734717 | 6938866 | 8428581 | 1685716 | 6742865 | 8453581 | 1690716 | 6762865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 4000 | 16000 | 9000 | 1800 | 7200 | 9000 | 1800 | 7200 | 30758722 | 6151745 | 24606977 | 26151793 | 5230359 | 20921434 | 26601793 | 5320359 | 21281434 | 30758722 | 6151745 | 24606977 | 26151793 | 5230359 | 20921434 | 26601793 | 5320359 | 21281434 | 590000 | 653421 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | CCI | 2013 | Q1 | Q1 - 2013 | 799970 | 159994 | 639976 | 799970 | 159994 | 639976 | 799970 | 159994 | 639976 | 19341835 | 3868367 | 15473468 | 16218767 | 3243753 | 12975014 | 18713767 | 3742753 | 14971014 | 1923334 | 384667 | 1538667 | 1695002 | 339000 | 1356002 | 1745002 | 349000 | 1396002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8673583 | 1734717 | 6938866 | 8434622 | 1686924 | 6747698 | 8444622 | 1688924 | 6755698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 4000 | 16000 | 8800 | 1760 | 7040 | 9800 | 1960 | 7840 | 30758722 | 6151745 | 24606977 | 27157161 | 5431431 | 21725730 | 29713161 | 5942631 | 23770530 | 30758722 | 6151745 | 24606977 | 27157161 | 5431431 | 21725730 | 29713161 | 5942631 | 23770530 | 949500 | 1120205 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | CCI | 2013 | Q2 | Q2 - 2013 | 799970 | 159994 | 639976 | 799970 | 159994 | 639976 | 799970 | 159994 | 639976 | 19341835 | 3868367 | 15473468 | 19108344 | 3821669 | 15286675 | 19341835 | 3868367 | 15473468 | 1923334 | 384667 | 1538667 | 1734446 | 346889 | 1387557 | 1923334 | 384667 | 1538667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8673583 | 1734717 | 6938866 | 8446349 | 1689270 | 6757079 | 8673583 | 1734717 | 6938866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 4000 | 16000 | 8800 | 1760 | 7040 | 20000 | 4000 | 16000 | 30758722 | 6151745 | 24606977 | 30097909 | 6019582 | 24078327 | 30758722 | 6151745 | 24606977 | 30758722 | 6151745 | 24606977 | 30097909 | 6019582 | 24078327 | 30758722 | 6151745 | 24606977 | 1309000 | 1502669 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570139 | CCI | 2013 | Q3 | Q3 - 2013 | 799970 | 159994 | 639976 | 799970 | 159994 | 639976 | 799970 | 159994 | 639976 | 19714604 | 3942921 | 15771683 | 19645904 | 3929181 | 15716723 | 19645904 | 3929181 | 15716723 | 1806438 | 361288 | 1445150 | 1845689 | 369138 | 1476551 | 1845689 | 369138 | 1476551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8426910 | 1685382 | 6741528 | 8446349 | 1689270 | 6757079 | 8446349 | 1689270 | 6757079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10800 | 2160 | 8640 | 10417 | 2083 | 8334 | 10417 | 2083 | 8334 | 30758722 | 6151745 | 24606977 | 30748329 | 6149666 | 24598663 | 30748329 | 6149666 | 24598663 | 30758722 | 6151745 | 24606977 | 30748329 | 6149666 | 24598663 | 30748329 | 6149666 | 24598663 | 1548667 | 1779040 | Maine Fiber Company, Inc. | TRUE
NT10BIX5570140 | CCI | 2010 | Q4 | Q4 - 2010 | 14663000 | 823200 | 13839800 | 0 | 0 | 0 | 4996204 | 0 | 4996204 | 25528000 | 7061446 | 18466554 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 0 | 0 | 0 | 7271204 | 608554 | 6662650 | 42466000 | 8493200 | 33972800 | 0 | 0 | 0 | 7271204 | 608554 | 6662650 | 0 | 0 | University of Hawaii Systems | TRUE
NT10BIX5570140 | CCI | 2011 | Q1 | Q1 - 2011 | 14663000 | 823200 | 13839800 | 2192010 | 0 | 2192010 | 14663000 | 823200 | 13839800 | 25528000 | 7061446 | 18466554 | 0 | 0 | 0 | 10028000 | 1308946 | 8719054 | 75000 | 0 | 75000 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 2192010 | 0 | 2192010 | 26966000 | 2740700 | 24225300 | 42466000 | 8493200 | 33972800 | 2192010 | 0 | 2192010 | 26966000 | 2740700 | 24225300 | 0 | 0 | University of Hawaii Systems | TRUE
NT10BIX5570140 | CCI | 2011 | Q2 | Q2 - 2011 | 14663000 | 823200 | 13839800 | 3881221 | 13853 | 3867368 | 6598350 | 1319670 | 5278680 | 25528000 | 7061446 | 18466554 | 0 | 0 | 0 | 5105600 | 1021120 | 4084480 | 75000 | 0 | 75000 | 0 | 0 | 0 | 110948 | 0 | 110948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 2000000 | 550554 | 1449446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 3881221 | 13853 | 3867368 | 13814898 | 2891344 | 10923554 | 42466000 | 8493200 | 33972800 | 3881221 | 13853 | 3867368 | 13814898 | 2891344 | 10923554 | 0 | 0 | University of Hawaii Systems | TRUE
NT10BIX5570140 | CCI | 2011 | Q3 | Q3 - 2011 | 14663000 | 823200 | 13839800 | 4537453 | 229767 | 4307686 | 13808000 | 660000 | 13148000 | 25528000 | 7061446 | 18466554 | 2600000 | 754000 | 1846000 | 5717000 | 1285000 | 4432000 | 75000 | 0 | 75000 | 110948 | 0 | 110948 | 110948 | 0 | 110948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 200000 | 58000 | 142000 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 7448401 | 1041767 | 6406634 | 21835948 | 2553554 | 19282394 | 42466000 | 8493200 | 33972800 | 7448401 | 1041767 | 6406634 | 21835948 | 2553554 | 19282394 | 0 | 0 | University of Hawaii Systems | TRUE
NT10BIX5570140 | CCI | 2011 | Q4 | Q4 - 2011 | 14663000 | 823200 | 13839800 | 6807032 | 549455 | 6257577 | 9925455 | 659455 | 9266000 | 25528000 | 7061446 | 18466554 | 2600000 | 754000 | 1846000 | 3726600 | 1080600 | 2646000 | 75000 | 0 | 75000 | 110978 | 0 | 110978 | 110978 | 0 | 110978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 602566 | 117107 | 485459 | 1204000 | 233000 | 971000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 10120576 | 1420562 | 8700014 | 14967033 | 1973055 | 12993978 | 42466000 | 8493200 | 33972800 | 10120576 | 1420562 | 8700014 | 14967033 | 1973055 | 12993978 | 0 | 0 | University of Hawaii Systems | TRUE
NT10BIX5570140 | CCI | 2012 | Q1 | Q1 - 2012 | 14663000 | 823200 | 13839800 | 10354813 | 671917 | 9682896 | 10531813 | 703917 | 9827896 | 25528000 | 7061446 | 18466554 | 3374715 | 919397 | 2455318 | 4610715 | 1337397 | 3273318 | 75000 | 0 | 75000 | 110978 | 0 | 110978 | 110978 | 0 | 110978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 758769 | 214516 | 544253 | 877769 | 254516 | 623253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 14599275 | 1805830 | 12793445 | 16131275 | 2295830 | 13835445 | 42466000 | 8493200 | 33972800 | 14599275 | 1805830 | 12793445 | 16131275 | 2295830 | 13835445 | 0 | 0 | University of Hawaii Systems | TRUE
NT10BIX5570140 | CCI | 2012 | Q2 | Q2 - 2012 | 14663000 | 823200 | 13839800 | 10388926 | 676432 | 9712494 | 10530500 | 686000 | 9844500 | 25528000 | 7061446 | 18466554 | 4674926 | 1350235 | 3324691 | 6492588 | 1758857 | 4733731 | 75000 | 0 | 75000 | 111008 | 0 | 111008 | 111008 | 0 | 111008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 862600 | 256089 | 606511 | 1037988 | 295517 | 742471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 16037460 | 2282756 | 13754704 | 18172084 | 2740374 | 15431710 | 42466000 | 8493200 | 33972800 | 16037460 | 2282756 | 13754704 | 18172084 | 2740374 | 15431710 | 0 | 0 | University of Hawaii Systems | TRUE
NT10BIX5570140 | CCI | 2012 | Q3 | Q3 - 2012 | 14663000 | 823200 | 13839800 | 10403428 | 676432 | 9726996 | 11749316 | 691400 | 11057916 | 25528000 | 7061446 | 18466554 | 4716263 | 1362223 | 3354040 | 8883868 | 2452328 | 6431540 | 75000 | 0 | 75000 | 111008 | 0 | 111008 | 111008 | 0 | 111008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 866587 | 257244 | 609343 | 1268726 | 362431 | 906295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 16097286 | 2295899 | 13801387 | 22012918 | 3506159 | 18506759 | 42466000 | 8493200 | 33972800 | 16097286 | 2295899 | 13801387 | 22012918 | 3506159 | 18506759 | 0 | 0 | University of Hawaii Systems | TRUE
NT10BIX5570140 | CCI | 2012 | Q4 | Q4 - 2012 | 14663000 | 823200 | 13839800 | 11515148 | 676432 | 10838716 | 12496148 | 681432 | 11814716 | 25528000 | 7061446 | 18466554 | 5151451 | 1474098 | 3677353 | 9097007 | 2618309 | 6478698 | 75000 | 0 | 75000 | 111008 | 0 | 111008 | 111008 | 0 | 111008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 908578 | 268038 | 640540 | 1289289 | 378444 | 910845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 17686185 | 2418568 | 15267617 | 22993452 | 3678185 | 19315267 | 42466000 | 8493200 | 33972800 | 17686185 | 2418568 | 15267617 | 22993452 | 3678185 | 19315267 | 0 | 0 | University of Hawaii Systems | TRUE
NT10BIX5570140 | CCI | 2013 | Q1 | Q1 - 2013 | 14663000 | 823200 | 13839800 | 11630050 | 775608 | 10854442 | 13170496 | 823200 | 12347296 | 25528000 | 7061446 | 18466554 | 8734403 | 2540520 | 6193883 | 13844235 | 4022371 | 9821864 | 75000 | 0 | 75000 | 111008 | 0 | 111008 | 111008 | 0 | 111008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 22675461 | 3924682 | 18750779 | 29325739 | 5454125 | 23871614 | 42466000 | 8493200 | 33972800 | 22675461 | 3924682 | 18750779 | 29325739 | 5454125 | 23871614 | 0 | 0 | University of Hawaii Systems | TRUE
NT10BIX5570140 | CCI | 2013 | Q2 | Q2 - 2013 | 14663000 | 823200 | 13839800 | 12538248 | 844281 | 11693967 | 14553000 | 854000 | 13699000 | 25528000 | 7061446 | 18466554 | 15226385 | 4389235 | 10837150 | 24267992 | 6763846 | 17504146 | 75000 | 0 | 75000 | 111008 | 0 | 111008 | 111008 | 0 | 111008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 30075641 | 5842070 | 24233571 | 41132000 | 8226400 | 32905600 | 42466000 | 8493200 | 33972800 | 30075641 | 5842070 | 24233571 | 41132000 | 8226400 | 32905600 | 0 | 0 | University of Hawaii Systems | TRUE
NT10BIX5570140 | CCI | 2013 | Q3 | Q3 - 2013 | 14663000 | 823200 | 13839800 | 13804444 | 849776 | 12954668 | 13967050 | 849776 | 13117274 | 25528000 | 7061446 | 18466554 | 24154901 | 6604559 | 17550342 | 24891388 | 6829559 | 18061829 | 75000 | 0 | 75000 | 111008 | 0 | 111008 | 111008 | 0 | 111008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 40270353 | 8062889 | 32207464 | 41169446 | 8287889 | 32881557 | 42466000 | 8493200 | 33972800 | 40270353 | 8062889 | 32207464 | 41169446 | 8287889 | 32881557 | 0 | 0 | University of Hawaii Systems | TRUE
NT10BIX5570140 | CCI | 2013 | Q4 | Q4 - 2013 | 14663000 | 823200 | 13839800 | 13891711 | 858221 | 13033490 | 14497800 | 864000 | 13633800 | 25528000 | 7061446 | 18466554 | 24866202 | 6753859 | 18112343 | 25095000 | 6908208 | 18186792 | 75000 | 0 | 75000 | 111008 | 0 | 111008 | 111008 | 0 | 111008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 2200000 | 608554 | 1591446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466000 | 8493200 | 33972800 | 41068921 | 8220634 | 32848287 | 41903808 | 8380762 | 33523046 | 42466000 | 8493200 | 33972800 | 41068921 | 8220634 | 32848287 | 41903808 | 8380762 | 33523046 | 0 | 0 | University of Hawaii Systems | TRUE
NT10BIX5570144 | CCI | 2010 | Q4 | Q4 - 2010 | 11386911 | 0 | 11386911 | 0 | 0 | 0 | 910953 | 0 | 910953 | 50277258 | 22461586 | 27815672 | 0 | 0 | 0 | 2011090 | 750208 | 1112626 | 3486487 | 0 | 3486487 | 151065 | 0 | 151065 | 324735 | 0 | 324735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1303920 | 0 | 1303920 | 0 | 0 | 0 | 0 | 0 | 0 | 1488758 | 0 | 1488758 | 0 | 0 | 0 | 1488758 | 0 | 1488758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67943334 | 22461586 | 45481748 | 151065 | 0 | 151065 | 4735536 | 750208 | 3837072 | 68530276 | 22461586 | 46068690 | 151065 | 0 | 151065 | 4735536 | 750208 | 3837072 | 0 | 0 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | CCI | 2011 | Q1 | Q1 - 2011 | 9778411 | 0 | 9778411 | 0 | 0 | 0 | 0 | 0 | 0 | 25911490 | 22416250 | 48327740 | 0 | 0 | 0 | 1054140 | 315000 | 1369140 | 3711487 | 0 | 3711487 | 480396 | 0 | 480396 | 803376 | 0 | 803376 | 4647688 | 0 | 4647688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223700 | 0 | 1223700 | 0 | 0 | 0 | 236293 | 0 | 236293 | 841250 | 0 | 841250 | 0 | 0 | 0 | 56249 | 0 | 56249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46114026 | 22416250 | 68530276 | 480396 | 0 | 480396 | 2150058 | 315000 | 2465058 | 46114026 | 22416250 | 68530276 | 480396 | 0 | 480396 | 2150058 | 315000 | 2465058 | 0 | 0 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | CCI | 2011 | Q2 | Q2 - 2011 | 9778411 | 3197540 | 6580871 | 0 | 0 | 0 | 1548533 | 309707 | 1238826 | 48327740 | 15810021 | 32517719 | 3204584 | 0 | 3204584 | 14945666 | 2989132 | 11956534 | 3711487 | 1213656 | 2497831 | 738242 | 30000 | 708242 | 1138243 | 227649 | 910594 | 4647688 | 1519794 | 3127894 | 0 | 0 | 0 | 41575 | 8315 | 33260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223700 | 400150 | 823550 | 286519 | 51556 | 234963 | 553823 | 110765 | 443058 | 841250 | 275089 | 566161 | 25000 | 0 | 25000 | 81249 | 16250 | 64999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 4254345 | 81556 | 4172789 | 18309089 | 3661818 | 14647271 | 68530276 | 22416250 | 46114026 | 4254345 | 81556 | 4172789 | 18309089 | 3661818 | 14647271 | 0 | 0 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | CCI | 2011 | Q3 | Q3 - 2011 | 9778411 | 3197540 | 6580871 | 0 | 0 | 0 | 265000 | 53000 | 212000 | 48327740 | 15810021 | 32517719 | 5747937 | 1293364 | 4454572 | 11875000 | 3801100 | 8073900 | 3711487 | 1213656 | 2497831 | 919568 | 183914 | 735655 | 1650000 | 330000 | 1320000 | 4647688 | 1519794 | 3127894 | 391095 | 78219 | 312876 | 1265000 | 253000 | 1012000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223700 | 400150 | 823550 | 311519 | 62304 | 249215 | 865000 | 173000 | 692000 | 841250 | 275089 | 566161 | 122200 | 24440 | 97760 | 343000 | 68600 | 274400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 7492319 | 1642241 | 5850078 | 16263000 | 4678700 | 11584300 | 68530276 | 22416250 | 46114026 | 7492319 | 1642241 | 5850078 | 16263000 | 4678700 | 11584300 | 0 | 0 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | CCI | 2011 | Q4 | Q4 - 2011 | 9778411 | 3197540 | 6580871 | 0 | 0 | 0 | 960000 | 0 | 960000 | 48327740 | 15810021 | 32517719 | 11641109 | 2607378 | 9033732 | 21171684 | 8341260 | 12830424 | 3711487 | 1213656 | 2497831 | 1100349 | 214297 | 886052 | 1454577 | 214297 | 1240279 | 4647688 | 1519794 | 3127894 | 603649 | 120730 | 482919 | 1132730 | 120730 | 1012000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223700 | 400150 | 823550 | 402371 | 80474 | 321897 | 502371 | 80474 | 421897 | 841250 | 275089 | 566161 | 134721 | 26944 | 107776 | 194721 | 26944 | 167776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 13882199 | 3049823 | 10832376 | 25416083 | 8783705 | 16632376 | 68530276 | 22416250 | 46114026 | 13882199 | 3049823 | 10832376 | 25416083 | 8783705 | 16632376 | 0 | 0 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | CCI | 2012 | Q1 | Q1 - 2012 | 9778411 | 3197540 | 6580871 | 883934 | 0 | 883934 | 2383934 | 0 | 883934 | 48327740 | 15810021 | 32517719 | 23318136 | 13186111 | 10132026 | 32038137 | 14706111 | 18832026 | 3711487 | 1213656 | 2497831 | 1576688 | 145496 | 1431192 | 2168188 | 145496 | 2022692 | 4647688 | 1519794 | 3127894 | 798816 | 30000 | 768816 | 978816 | 30000 | 948816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223700 | 400150 | 823550 | 411748 | 86367 | 325381 | 456748 | 86367 | 370381 | 841250 | 275089 | 566161 | 146721 | 0 | 146721 | 176721 | 0 | 176721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 27136043 | 13447974 | 13688070 | 38202544 | 14967974 | 23234570 | 68530276 | 22416250 | 46114026 | 27136043 | 13447974 | 13688070 | 38202544 | 14967974 | 23234570 | 0 | 0 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | CCI | 2012 | Q2 | Q2 - 2012 | 9778411 | 3197540 | 6580871 | 883934 | 0 | 883934 | 3383934 | 0 | 3383934 | 48327740 | 15810021 | 32517719 | 23941674 | 8549696 | 15391978 | 35113494 | 12593030 | 22520464 | 3711487 | 1213656 | 2497831 | 1924557 | 106138 | 1818419 | 2496557 | 106138 | 2390419 | 4647688 | 1519794 | 3127894 | 6483780 | 5743589 | 740191 | 6483780 | 5743589 | 740191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223700 | 400150 | 823550 | 417148 | 114950 | 302198 | 542148 | 114950 | 427198 | 841250 | 275089 | 566161 | 146721 | 0 | 146721 | 556235 | 0 | 556235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 33797814 | 14514373 | 19283441 | 48576148 | 18557707 | 30018441 | 68530276 | 22416250 | 46114026 | 33797814 | 14514373 | 19283441 | 48576148 | 18557707 | 30018441 | 0 | 0 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | CCI | 2012 | Q3 | Q3 - 2012 | 9778411 | 3197540 | 6580871 | 2951708 | 0 | 2951708 | 5250000 | 0 | 5250000 | 48327740 | 15810021 | 32517719 | 29026675 | 10538992 | 18487683 | 33500000 | 13182059 | 20317941 | 3711487 | 1213656 | 2497831 | 2359878 | 106138 | 2253740 | 2802877 | 106138 | 2696739 | 4647688 | 1519794 | 3127894 | 6972595 | 5743589 | 1229006 | 7100000 | 5743589 | 1356411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1223700 | 400150 | 823550 | 908934 | 114950 | 793984 | 1100000 | 114950 | 985050 | 841250 | 275089 | 566161 | 473735 | 0 | 473735 | 565000 | 0 | 565000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 42693525 | 16503669 | 26189856 | 50317877 | 19146736 | 31171141 | 68530276 | 22416250 | 46114026 | 42693525 | 16503669 | 26189856 | 50317877 | 19146736 | 31171141 | 0 | 0 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | CCI | 2012 | Q4 | Q4 - 2012 | 8811229 | 0 | 8811229 | 3605078 | 0 | 3605078 | 6005078 | 0 | 6005078 | 47274517 | 14887053 | 32387464 | 35814786 | 14104331 | 21710455 | 40316255 | 14210354 | 26105901 | 1977277 | 0 | 1977277 | 1076649 | 0 | 1076649 | 1414385 | 0 | 1414385 | 7533200 | 7308110 | 225090 | 5229597 | 5004507 | 225090 | 6579415 | 6354325 | 225090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159053 | 221087 | 1937966 | 1614974 | 221087 | 1393887 | 2022974 | 221087 | 1801887 | 775000 | 0 | 775000 | 507275 | 0 | 507275 | 607503 | 0 | 607503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 47848359 | 19329925 | 28518434 | 56945610 | 20785766 | 36159844 | 68530276 | 22416250 | 46114026 | 47848359 | 19329925 | 28518434 | 56945610 | 20785766 | 36159844 | 0 | 0 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | CCI | 2013 | Q1 | Q1 - 2013 | 8811229 | 0 | 8811229 | 4023078 | 0 | 4023078 | 6345000 | 0 | 6345000 | 47274517 | 14887053 | 32387464 | 38874694 | 14104331 | 24768893 | 44326470 | 14478490 | 29847980 | 1977277 | 0 | 1977277 | 1193746 | 0 | 1193746 | 1636746 | 0 | 1636746 | 7533200 | 7308110 | 225090 | 5560195 | 5004507 | 555688 | 6710000 | 6107485 | 602515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159053 | 221087 | 1937966 | 1790618 | 221087 | 1569531 | 2075000 | 221087 | 1853913 | 775000 | 0 | 775000 | 583865 | 0 | 583865 | 689000 | 0 | 689000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 52026196 | 19329925 | 32694801 | 61782216 | 20807062 | 40975154 | 68530276 | 22416250 | 46114026 | 52026196 | 19329925 | 32694801 | 61782216 | 20807062 | 40975154 | 0 | 0 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | CCI | 2013 | Q2 | Q2 - 2013 | 8811229 | 0 | 8811229 | 4786346 | 0 | 4786346 | 7645000 | 0 | 7645000 | 47274517 | 14887053 | 32387464 | 40458454 | 14104331 | 26354123 | 41253543 | 14140998 | 27112545 | 1977277 | 0 | 1977277 | 1307434 | 0 | 1307434 | 1583958 | 0 | 1583958 | 7533200 | 7308110 | 225090 | 6025618 | 5004507 | 1021111 | 7533200 | 5004507 | 2528693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159053 | 221087 | 1937966 | 2089751 | 221087 | 1868664 | 2159053 | 221087 | 1937966 | 775000 | 0 | 775000 | 659865 | 0 | 659865 | 775000 | 0 | 775000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 55327468 | 19329925 | 35997543 | 60949754 | 19366592 | 41583162 | 68530276 | 22416250 | 46114026 | 55327468 | 19329925 | 35997543 | 60949754 | 19366592 | 41583162 | 0 | 0 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | CCI | 2013 | Q3 | Q3 - 2013 | 8811229 | 0 | 8811229 | 6181083 | 0 | 6181083 | 8811229 | 0 | 8811229 | 47274517 | 14887053 | 32387464 | 45842775 | 14104331 | 31738444 | 47274517 | 17190656 | 30083861 | 1977277 | 0 | 1977277 | 1436773 | 0 | 1436773 | 1977277 | 0 | 1977277 | 7533200 | 7308110 | 225090 | 6210353 | 5004507 | 1205846 | 7533200 | 5004507 | 2528693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159053 | 221087 | 1937966 | 2155160 | 221087 | 1934073 | 2159053 | 221087 | 1937966 | 775000 | 0 | 775000 | 769065 | 0 | 769065 | 775000 | 0 | 775000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68530276 | 22416250 | 46114026 | 62595209 | 19329925 | 43265284 | 68530276 | 22416250 | 46114026 | 68530276 | 22416250 | 46114026 | 62595209 | 19329925 | 43265284 | 68530276 | 22416250 | 46114026 | 0 | 0 | Northern Illinois University, Inc. | TRUE
NT10BIX5570144 | CCI | 2013 | Q4 | Q4 - 2013 | 7697472 | 0 | 7697472 | 6820463 | 0 | 6820463 | 6820463 | 0 | 6820463 | 47585477 | 14514681 | 33070796 | 50485173 | 15500593 | 34984580 | 50485173 | 15500593 | 34984580 | 1485523 | 48750 | 1436773 | 1407350 | 0 | 1407350 | 1407350 | 0 | 1407350 | 6210353 | 5004507 | 1205846 | 5560353 | 5004507 | 555846 | 5560353 | 5004507 | 555846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2425411 | 491337 | 1934074 | 2111025 | 534303 | 1576722 | 2111025 | 534303 | 1576722 | 769065 | 0 | 769065 | 769065 | 0 | 769065 | 769065 | 0 | 769065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66173301 | 20059275 | 46114026 | 67153429 | 21039403 | 46114026 | 67153429 | 21039403 | 46114026 | 66173301 | 20059275 | 46114026 | 67153429 | 21039403 | 46114026 | 67153429 | 21039403 | 46114026 | 0 | 0 | Northern Illinois University, Inc. | TRUE
NT10BIX5570145 | CCI | 2010 | Q4 | Q4 - 2010 | 167229 | 51591 | 115638 | 0 | 0 | 0 | 51605 | 15921 | 35685 | 328560 | 101363 | 227197 | 0 | 0 | 0 | 101391 | 31280 | 70111 | 740184 | 228352 | 511832 | 0 | 0 | 0 | 228414 | 70467 | 157947 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 11782 | 3635 | 8147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 0 | 0 | 0 | 10800 | 3332 | 7469 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 9103 | 2808 | 6295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 0 | 0 | 0 | 186827 | 57637 | 129189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 0 | 0 | 0 | 33004 | 10182 | 22822 | 2051021 | 632755 | 1418266 | 0 | 0 | 0 | 632926 | 195262 | 437665 | 2051021 | 632755 | 1418266 | 0 | 0 | 0 | 632926 | 195262 | 437665 | 0 | 0 | Ute Indian Tribe | TRUE
NT10BIX5570145 | CCI | 2011 | Q1 | Q1 - 2011 | 167229 | 51591 | 115638 | 0 | 0 | 0 | 86328 | 21582 | 64746 | 328560 | 101363 | 227197 | 0 | 0 | 0 | 169611 | 42403 | 127208 | 740184 | 228352 | 511832 | 29060 | 7265 | 21795 | 382101 | 95525 | 286574 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 19709 | 4927 | 14782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 19294 | 4824 | 14470 | 18068 | 4517 | 13551 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 15229 | 3807 | 11421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 0 | 0 | 0 | 312531 | 78133 | 234398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 45000 | 11250 | 33750 | 55210 | 13803 | 41408 | 2051021 | 632755 | 1418266 | 93354 | 23339 | 70015 | 1058787 | 264697 | 794088 | 2051021 | 632755 | 1418266 | 93354 | 23339 | 70015 | 1058787 | 264697 | 794088 | 0 | 0 | Ute Indian Tribe | TRUE
NT10BIX5570145 | CCI | 2011 | Q2 | Q2 - 2011 | 167229 | 51591 | 115638 | 0 | 0 | 0 | 111167 | 27792 | 83376 | 328560 | 101363 | 227197 | 0 | 0 | 0 | 218414 | 54603 | 163810 | 740184 | 228352 | 511832 | 95720 | 23930 | 71790 | 492046 | 123011 | 369034 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 25381 | 6345 | 19035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 24194 | 6049 | 18146 | 24202 | 6049 | 18146 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 19610 | 4903 | 14708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 80288 | 20072 | 60216 | 402458 | 100615 | 301844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 49300 | 12325 | 36975 | 71096 | 17774 | 53322 | 2051021 | 632755 | 1418266 | 249502 | 62376 | 187127 | 1364374 | 341092 | 1023275 | 2051021 | 632755 | 1418266 | 249502 | 62376 | 187127 | 1364374 | 341092 | 1023275 | 0 | 0 | Ute Indian Tribe | TRUE
NT10BIX5570145 | CCI | 2011 | Q3 | Q3 - 2011 | 167229 | 51591 | 115638 | 105744 | 32622 | 73120 | 152974 | 47194 | 105780 | 328560 | 101363 | 227197 | 0 | 0 | 0 | 134727 | 41564 | 93163 | 740184 | 228352 | 511832 | 226912 | 70004 | 156908 | 303515 | 93637 | 209879 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 19709 | 6080 | 13629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 24194 | 7464 | 16730 | 26817 | 8273 | 18544 | 29500 | 9101 | 20399 | 12452 | 3842 | 8610 | 15228 | 4698 | 10530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 137153 | 42313 | 94841 | 146866 | 45309 | 101557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 100300 | 30943 | 69357 | 100300 | 30943 | 69357 | 2051021 | 632755 | 1418266 | 606755 | 187188 | 419566 | 900136 | 277698 | 622439 | 2051021 | 632755 | 1418266 | 606755 | 187188 | 419566 | 900136 | 277698 | 622439 | 0 | 0 | Ute Indian Tribe | TRUE
NT10BIX5570145 | CCI | 2011 | Q4 | Q4 - 2011 | 167229 | 51591 | 115638 | 105744 | 32623 | 73121 | 153000 | 47202 | 105798 | 328560 | 101363 | 227197 | 0 | 0 | 0 | 0 | 0 | 0 | 740184 | 228352 | 511832 | 373901 | 123831 | 250070 | 451640 | 139334 | 312306 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 12720 | 3924 | 8796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 24194 | 7464 | 16730 | 34194 | 10549 | 23645 | 29500 | 9101 | 20399 | 12453 | 3842 | 8611 | 22453 | 6927 | 15526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 335650 | 103551 | 232099 | 335650 | 103549 | 232099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 100300 | 30943 | 69357 | 100300 | 30943 | 69357 | 2051021 | 632755 | 1418266 | 952242 | 302254 | 649988 | 1109957 | 342428 | 767527 | 2051021 | 632755 | 1418266 | 952242 | 302254 | 649988 | 1109957 | 342428 | 767527 | 0 | 0 | Ute Indian Tribe | TRUE
NT10BIX5570145 | CCI | 2012 | Q1 | Q1 - 2012 | 167229 | 51591 | 115638 | 150563 | 46449 | 104113 | 162069 | 49999 | 112070 | 328560 | 101363 | 227197 | 0 | 0 | 0 | 251750 | 77667 | 174083 | 740184 | 228352 | 511832 | 471165 | 168305 | 302861 | 576146 | 177745 | 398401 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 29254 | 9025 | 20229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 24194 | 7464 | 16730 | 26817 | 8273 | 18544 | 29500 | 9101 | 20399 | 12453 | 3842 | 8611 | 22603 | 6973 | 15630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 335650 | 103551 | 232099 | 463885 | 143112 | 320773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 100300 | 30943 | 69357 | 100300 | 30943 | 69357 | 2051021 | 632755 | 1418266 | 1094325 | 360554 | 733771 | 1632824 | 503737 | 1129087 | 2051021 | 632755 | 1418266 | 1094325 | 360554 | 733771 | 1632824 | 503737 | 1129087 | 10800 | 10800 | Ute Indian Tribe | TRUE
NT10BIX5570145 | CCI | 2012 | Q2 | Q2 - 2012 | 167229 | 51591 | 115638 | 161904 | 49949 | 111955 | 167229 | 51591 | 115638 | 328560 | 101363 | 227197 | 205683 | 63455 | 142228 | 251750 | 77667 | 174083 | 740184 | 228352 | 511832 | 575308 | 177487 | 397821 | 677092 | 208887 | 468204 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 29254 | 9025 | 20229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 30656 | 9457 | 21199 | 35000 | 10798 | 24202 | 29500 | 9101 | 20399 | 16852 | 5198 | 11654 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 346071 | 106765 | 239306 | 402458 | 124161 | 278297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 100300 | 30943 | 69357 | 106950 | 32995 | 73955 | 2051021 | 632755 | 1418266 | 1436774 | 443254 | 993520 | 1699233 | 524225 | 1175007 | 2051021 | 632755 | 1418266 | 1436774 | 443254 | 993520 | 1699233 | 524225 | 1175007 | 21600 | 21600 | Ute Indian Tribe | TRUE
NT10BIX5570145 | CCI | 2012 | Q3 | Q3 - 2012 | 167229 | 51591 | 115638 | 161904 | 49949 | 111955 | 164404 | 50720 | 113684 | 328560 | 101363 | 227197 | 328415 | 99017 | 229398 | 328415 | 99017 | 229398 | 740184 | 228352 | 511832 | 669815 | 201949 | 467866 | 704815 | 212502 | 492313 | 38180 | 11779 | 26401 | 36173 | 10907 | 25266 | 37173 | 11208 | 25965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 30656 | 9457 | 21199 | 34156 | 10299 | 23857 | 29500 | 9101 | 20399 | 16852 | 5198 | 11654 | 22852 | 6889 | 15963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 554012 | 167035 | 386977 | 599012 | 180603 | 418409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 105300 | 31747 | 73553 | 106300 | 32049 | 74251 | 2051021 | 632755 | 1418266 | 1903127 | 575259 | 1327868 | 1997127 | 603287 | 1393840 | 2051021 | 632755 | 1418266 | 1903127 | 575259 | 1327868 | 1997127 | 603287 | 1393840 | 0 | 32400 | Ute Indian Tribe | TRUE
NT10BIX5570145 | CCI | 2012 | Q4 | Q4 - 2012 | 167229 | 51591 | 115638 | 164444 | 50732 | 113712 | 167229 | 51591 | 115638 | 328560 | 101363 | 227197 | 328415 | 101318 | 227097 | 328560 | 101363 | 227197 | 740184 | 228352 | 511832 | 731237 | 225592 | 505644 | 740184 | 228352 | 511832 | 38180 | 11779 | 26401 | 37922 | 11699 | 26223 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 30656 | 9457 | 21199 | 35000 | 10798 | 24202 | 29500 | 9101 | 20399 | 21480 | 6627 | 14854 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 598877 | 184758 | 414119 | 605418 | 186776 | 418642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 106841 | 32961 | 73879 | 106950 | 32995 | 73955 | 2051021 | 632755 | 1418266 | 2019872 | 623144 | 1396727 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2019872 | 623144 | 1396727 | 2051021 | 632755 | 1418266 | 0 | 32400 | Ute Indian Tribe | TRUE
NT10BIX5570145 | CCI | 2013 | Q1 | Q1 - 2013 | 167229 | 51591 | 115638 | 167229 | 51591 | 115638 | 167229 | 51591 | 115638 | 328560 | 101363 | 227197 | 328560 | 101363 | 227197 | 328560 | 101363 | 227197 | 740184 | 228352 | 511832 | 740184 | 228352 | 511832 | 740184 | 228352 | 511832 | 38180 | 11779 | 26401 | 38180 | 11779 | 26401 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 35000 | 10798 | 24202 | 35000 | 10798 | 24202 | 29500 | 9101 | 20399 | 29500 | 9101 | 20399 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 605418 | 186776 | 418642 | 605418 | 186776 | 418642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 106950 | 32995 | 73955 | 106950 | 32995 | 73955 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 0 | 32400 | Ute Indian Tribe | TRUE
NT10BIX5570145 | CCI | 2013 | Q2 | Q2 - 2013 | 167229 | 51591 | 115638 | 167229 | 51591 | 115638 | 167229 | 51591 | 115638 | 328560 | 101363 | 227197 | 328560 | 101363 | 227197 | 328560 | 101363 | 227197 | 740184 | 228352 | 511832 | 740184 | 228352 | 511832 | 740184 | 228352 | 511832 | 38180 | 11779 | 26401 | 38180 | 11779 | 26401 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 35000 | 10798 | 24202 | 35000 | 10798 | 24202 | 29500 | 9101 | 20399 | 29500 | 9101 | 20399 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 605418 | 186776 | 418642 | 605418 | 186776 | 418642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 106950 | 32995 | 73955 | 106950 | 32995 | 73955 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 0 | 32400 | Ute Indian Tribe | TRUE
NT10BIX5570145 | CCI | 2013 | Q3 | Q3 - 2013 | 167229 | 51591 | 115638 | 167229 | 51591 | 115638 | 167229 | 51591 | 115638 | 328560 | 101363 | 227197 | 328560 | 101363 | 227197 | 328560 | 101363 | 227197 | 740184 | 228352 | 511832 | 740184 | 228352 | 511832 | 740184 | 228352 | 511832 | 38180 | 11779 | 26401 | 38180 | 11779 | 26401 | 38180 | 11779 | 26401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 10798 | 24202 | 35000 | 10798 | 24202 | 35000 | 10798 | 24202 | 29500 | 9101 | 20399 | 29500 | 9101 | 20399 | 29500 | 9101 | 20399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605418 | 186776 | 418642 | 605418 | 186776 | 418642 | 605418 | 186776 | 418642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106950 | 32995 | 73955 | 106950 | 32995 | 73955 | 106950 | 32995 | 73955 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 2051021 | 632755 | 1418266 | 0 | 32400 | Ute Indian Tribe | TRUE
NT10BIX5570146 | CCI | 2010 | Q4 | Q4 - 2010 | 11245000 | 2450000 | 8795000 | 0 | 0 | 0 | 3953014 | 1185904 | 2767110 | 24114319 | 8800000 | 15314319 | 0 | 0 | 0 | 0 | 0 | 0 | 583281 | 0 | 583281 | 89049 | 26715 | 62334 | 157282 | 47185 | 110097 | 572400 | 0 | 572400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 155063 | 46519 | 108544 | 342992 | 102898 | 240094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 244112 | 73234 | 170878 | 4453288 | 1335987 | 3117301 | 38000000 | 11400000 | 26600000 | 244112 | 73234 | 170878 | 4453288 | 1335987 | 3117301 | 0 | 0 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | CCI | 2011 | Q1 | Q1 - 2011 | 11245000 | 2450000 | 8795000 | 0 | 0 | 0 | 4086014 | 1225804 | 2860210 | 24114319 | 8800000 | 15314319 | 35731 | 10719 | 25012 | 1562796 | 468839 | 1093957 | 583281 | 0 | 583281 | 88476 | 26543 | 61933 | 217032 | 65109 | 151922 | 572400 | 0 | 572400 | 8000 | 2400 | 5600 | 236850 | 71055 | 165795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 310499 | 93150 | 217349 | 451493 | 135448 | 316045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 0 | 0 | 0 | 219000 | 65700 | 153300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 442706 | 132812 | 309894 | 6773185 | 2031955 | 4741229 | 38000000 | 11400000 | 26600000 | 442706 | 132812 | 309894 | 6773185 | 2031955 | 4741229 | 0 | 0 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | CCI | 2011 | Q2 | Q2 - 2011 | 11245000 | 2450000 | 8795000 | 2788252 | 836476 | 1951776 | 7825313 | 2347594 | 5477719 | 24114319 | 8800000 | 15314319 | 128386 | 38516 | 89870 | 2814107 | 844232 | 1969875 | 583281 | 0 | 583281 | 166028 | 49808 | 116220 | 265157 | 79547 | 185610 | 572400 | 0 | 572400 | 132636 | 39791 | 92845 | 330600 | 99180 | 231420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 447483 | 134245 | 313238 | 559994 | 167998 | 391996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 57521 | 17256 | 40265 | 269250 | 80775 | 188475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 3720306 | 1116092 | 2604214 | 12064421 | 3619326 | 8445095 | 38000000 | 11400000 | 26600000 | 3720306 | 1116092 | 2604214 | 12064421 | 3619326 | 8445095 | 0 | 0 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | CCI | 2011 | Q3 | Q3 - 2011 | 11245000 | 2450000 | 8795000 | 3296650 | 988995 | 2307655 | 8229182 | 988995 | 7240187 | 24114319 | 8800000 | 15314319 | 3076419 | 922926 | 2153493 | 10689972 | 5422926 | 5267046 | 583281 | 0 | 583281 | 210338 | 63101 | 147237 | 310156 | 63101 | 247055 | 572400 | 0 | 572400 | 180012 | 54004 | 126009 | 330600 | 54004 | 276596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 603678 | 181104 | 422575 | 764996 | 181104 | 583892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 380254 | 114076 | 266178 | 403125 | 114076 | 289049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 7747351 | 2324206 | 5423147 | 20728031 | 6824206 | 13903825 | 38000000 | 11400000 | 26600000 | 7747351 | 2324206 | 5423147 | 20728031 | 6824206 | 13903825 | 0 | 0 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | CCI | 2011 | Q4 | Q4 - 2011 | 11245000 | 2450000 | 8795000 | 5842101 | 1018480 | 4823621 | 8619703 | 1018480 | 7601223 | 24114319 | 8800000 | 15314319 | 10517455 | 5520441 | 4997013 | 14751543 | 6710441 | 8041102 | 583281 | 0 | 583281 | 266279 | 64982 | 201296 | 303069 | 64982 | 238087 | 572400 | 0 | 572400 | 200092 | 55614 | 144477 | 220092 | 55614 | 164478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 766339 | 186503 | 579836 | 849870 | 186503 | 663367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 617798 | 117477 | 500321 | 636448 | 117477 | 518971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 18210064 | 6963497 | 11246564 | 25380725 | 8153497 | 17227228 | 38000000 | 11400000 | 26600000 | 18210064 | 6963497 | 11246564 | 25380725 | 8153497 | 17227228 | 0 | 0 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | CCI | 2012 | Q1 | Q1 - 2012 | 11245000 | 2450000 | 8795000 | 6717363 | 1018480 | 5698883 | 6717363 | 1018480 | 5698883 | 24114319 | 8800000 | 15314319 | 12476815 | 6491242 | 5985573 | 16982842 | 7044773 | 9938069 | 583281 | 0 | 583281 | 303584 | 64982 | 238602 | 400157 | 64982 | 335175 | 572400 | 0 | 572400 | 217152 | 55614 | 161538 | 429300 | 55614 | 373686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 901148 | 186503 | 714645 | 966998 | 186503 | 780495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 663746 | 117477 | 546269 | 663746 | 117477 | 546269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 21279808 | 7934298 | 13345510 | 26160406 | 8487829 | 17672577 | 38000000 | 11400000 | 26600000 | 21279808 | 7934298 | 13345510 | 26160406 | 8487829 | 17672577 | 0 | 0 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | CCI | 2012 | Q2 | Q2 - 2012 | 11245000 | 2450000 | 8795000 | 6778932 | 1018480 | 5760452 | 9191595 | 1018480 | 8173115 | 24114319 | 8800000 | 15314319 | 14007190 | 6491242 | 7515948 | 17501099 | 7330442 | 10170657 | 583281 | 0 | 583281 | 353606 | 64982 | 288624 | 388606 | 64982 | 323624 | 572400 | 0 | 572400 | 218038 | 55614 | 162424 | 218038 | 55614 | 162424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 955980 | 186503 | 769477 | 1076481 | 186503 | 889978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 796575 | 117477 | 679098 | 810415 | 117477 | 692938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 23110321 | 7934298 | 15176023 | 29186234 | 8773498 | 20412736 | 38000000 | 11400000 | 26600000 | 23110321 | 7934298 | 15176023 | 29186234 | 8773498 | 20412736 | 0 | 0 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | CCI | 2012 | Q3 | Q3 - 2012 | 11245000 | 2450000 | 8795000 | 9828734 | 1129226 | 8699508 | 9859200 | 1167804 | 8700197 | 24114319 | 8800000 | 15314319 | 17231761 | 7311989 | 9919772 | 20759085 | 8363596 | 12385689 | 583281 | 0 | 583281 | 395628 | 66508 | 329120 | 425628 | 68173 | 357454 | 572400 | 0 | 572400 | 218138 | 55618 | 162520 | 218138 | 56471 | 162666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 1010292 | 188475 | 821817 | 1040292 | 192546 | 847746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 810536 | 117984 | 692552 | 824376 | 121210 | 703167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 29495089 | 8869800 | 20625289 | 33126719 | 9969800 | 23156919 | 38000000 | 11400000 | 26600000 | 29495089 | 8869800 | 20625289 | 33126719 | 9969800 | 23156919 | 0 | 0 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | CCI | 2012 | Q4 | Q4 - 2012 | 11245000 | 2450000 | 8795000 | 9909266 | 1159111 | 8750155 | 10422493 | 1159111 | 9263382 | 24114319 | 8800000 | 15314319 | 20744955 | 8434752 | 12310203 | 23995998 | 9499752 | 14496246 | 583281 | 0 | 583281 | 440153 | 67835 | 372318 | 470153 | 67835 | 402318 | 572400 | 0 | 572400 | 218026 | 56276 | 161750 | 218026 | 56276 | 161750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 1058478 | 191667 | 866811 | 1088478 | 191667 | 896811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 787578 | 120359 | 667219 | 787578 | 120359 | 667219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 33158456 | 10030000 | 23128456 | 36982726 | 11095000 | 25887726 | 38000000 | 11400000 | 26600000 | 33158456 | 10030000 | 23128456 | 36982726 | 11095000 | 25887726 | 0 | 0 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | CCI | 2013 | Q1 | Q1 - 2013 | 11245000 | 2450000 | 8795000 | 10035848 | 1159111 | 8876737 | 10704714 | 1159111 | 9545603 | 24114319 | 8800000 | 15314319 | 22414740 | 8924752 | 13489988 | 24696051 | 9804752 | 14891299 | 583281 | 0 | 583281 | 440153 | 67835 | 372318 | 454976 | 67835 | 387141 | 572400 | 0 | 572400 | 218026 | 56276 | 161750 | 218026 | 56276 | 161750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 1084857 | 191667 | 893190 | 1114857 | 191667 | 923190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 811376 | 120359 | 691017 | 811376 | 120359 | 691017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 35005000 | 10520000 | 24485000 | 38000000 | 11400000 | 26600000 | 38000000 | 11400000 | 26600000 | 35005000 | 10520000 | 24485000 | 38000000 | 11400000 | 26600000 | 0 | 0 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | CCI | 2013 | Q2 | Q2 - 2013 | 11245000 | 2450000 | 8795000 | 10009050 | 1159111 | 8849939 | 10682716 | 1159111 | 9523605 | 24114319 | 8800000 | 15314319 | 24046659 | 9704752 | 14341907 | 24669210 | 9804752 | 14864458 | 583281 | 0 | 583281 | 488810 | 67835 | 420975 | 508810 | 67835 | 440975 | 572400 | 0 | 572400 | 218025 | 56276 | 161749 | 218026 | 56276 | 161750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 1100007 | 191667 | 908340 | 1110007 | 191667 | 918340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 811231 | 120359 | 690872 | 811231 | 120359 | 690872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 36673782 | 11300000 | 25373782 | 38000000 | 11400000 | 26600000 | 38000000 | 11400000 | 26600000 | 36673782 | 11300000 | 25373782 | 38000000 | 11400000 | 26600000 | 0 | 0 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570146 | CCI | 2013 | Q3 | Q3 - 2013 | 11245000 | 2450000 | 8795000 | 10455290 | 1177668 | 9277623 | 10455290 | 1177668 | 9277623 | 24114319 | 8800000 | 15314319 | 25605952 | 10570956 | 15034996 | 25605952 | 10570956 | 15034996 | 583281 | 0 | 583281 | 546275 | 104956 | 441319 | 546275 | 104956 | 441319 | 572400 | 0 | 572400 | 218026 | 48459 | 169566 | 218026 | 48459 | 169566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190000 | 0 | 1190000 | 1119757 | 167520 | 952237 | 1119757 | 167520 | 952237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 150000 | 145000 | 810700 | 86441 | 724259 | 810700 | 86441 | 724259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38000000 | 11400000 | 26600000 | 38756000 | 12156000 | 26600000 | 38756000 | 12156000 | 26600000 | 38000000 | 11400000 | 26600000 | 38756000 | 12156000 | 26600000 | 38756000 | 12156000 | 26600000 | 0 | 0 | SHO-ME Technologies, L.L.C. | TRUE
NT10BIX5570148 | CCI | 2010 | Q4 | Q4 - 2010 | 4316305 | 1299398 | 3016907 | 0 | 0 | 0 | 0 | 0 | 0 | 8189627 | 2465437 | 5724190 | 0 | 0 | 0 | 149976 | 45149 | 104827 | 6354845 | 1913088 | 4441757 | 0 | 0 | 0 | 68760 | 20700 | 48060 | 129600 | 39015 | 90585 | 0 | 0 | 0 | 48000 | 14450 | 33550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 15173 | 35227 | 0 | 0 | 0 | 5040 | 1517 | 3523 | 35200 | 10597 | 24603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662948 | 199577 | 463371 | 0 | 0 | 0 | 0 | 0 | 0 | 19738925 | 5942285 | 13796640 | 0 | 0 | 0 | 271776 | 81816 | 189960 | 19738925 | 5942285 | 13796640 | 0 | 0 | 0 | 271776 | 81816 | 189960 | 0 | 0 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | CCI | 2011 | Q1 | Q1 - 2011 | 4316305 | 1299398 | 3016907 | 150159 | 0 | 150159 | 500000 | 151235 | 348765 | 8189627 | 2465437 | 5724190 | 1080416 | 1080416 | 0 | 218800 | 65859 | 152941 | 6354845 | 1913088 | 4441757 | 39185 | 0 | 39185 | 1791872 | 1620624 | 171248 | 129600 | 39015 | 90585 | 0 | 0 | 0 | 50000 | 15050 | 34950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19469 | 0 | 19469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 15173 | 35227 | 0 | 0 | 0 | 12600 | 3793 | 8807 | 35200 | 10597 | 24603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662948 | 199577 | 463371 | 0 | 0 | 0 | 0 | 0 | 0 | 19738925 | 5942285 | 13796640 | 1289229 | 1080416 | 208813 | 2573272 | 1856561 | 716711 | 19738925 | 5942285 | 13796640 | 1289229 | 1080416 | 208813 | 2573272 | 1856561 | 716711 | 0 | 0 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | CCI | 2011 | Q2 | Q2 - 2011 | 4316305 | 0 | 4316305 | 1546888 | 0 | 1546888 | 2315500 | 0 | 2315500 | 8189627 | 0 | 8189627 | 88524 | 0 | 88524 | 2802814 | 0 | 2802814 | 6354845 | 5942285 | 412560 | 1261138 | 1080416 | 180722 | 4835523 | 4454801 | 380722 | 129600 | 0 | 129600 | 46317 | 0 | 46317 | 77760 | 0 | 77760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 0 | 50400 | 1225 | 0 | 1225 | 16128 | 0 | 16128 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662948 | 0 | 662948 | 0 | 0 | 0 | 662948 | 0 | 662948 | 19738925 | 5942285 | 13796640 | 2944092 | 1080416 | 1863676 | 10710673 | 4454801 | 6255872 | 19738925 | 5942285 | 13796640 | 2944092 | 1080416 | 1863676 | 10710673 | 4454801 | 6255872 | 0 | 0 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | CCI | 2011 | Q3 | Q3 - 2011 | 4316305 | 0 | 4316305 | 2324177 | 0 | 2324177 | 2325000 | 0 | 2325000 | 8189627 | 0 | 8189627 | 935600 | 0 | 935600 | 2802814 | 0 | 2802814 | 6354845 | 5942285 | 412560 | 4751379 | 4454801 | 296578 | 4951379 | 4454801 | 496578 | 129600 | 0 | 129600 | 172352 | 0 | 172352 | 260602 | 0 | 260602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 0 | 50400 | 1225 | 0 | 1225 | 16128 | 0 | 16128 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662948 | 0 | 662948 | 0 | 0 | 0 | 662948 | 0 | 662948 | 19738925 | 5942285 | 13796640 | 8184733 | 4454801 | 3729932 | 11018871 | 4454801 | 6564070 | 19738925 | 5942285 | 13796640 | 8184733 | 4454801 | 3729932 | 11018871 | 4454801 | 6564070 | 0 | 0 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | CCI | 2011 | Q4 | Q4 - 2011 | 3316305 | 0 | 3316305 | 2324177 | 0 | 2324177 | 2324177 | 0 | 2324177 | 14245272 | 5285285 | 8959987 | 6671267 | 4466701 | 2204566 | 8344973 | 4466701 | 3878272 | 928800 | 542000 | 386800 | 403387 | 100614 | 302773 | 539700 | 164927 | 374773 | 500000 | 115000 | 385000 | 197243 | 23648 | 173595 | 220243 | 38648 | 181595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 0 | 50400 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662948 | 0 | 662948 | 0 | 0 | 0 | 662948 | 0 | 662948 | 19738925 | 5942285 | 13796640 | 9647802 | 4590963 | 5056839 | 12143769 | 4670276 | 7473493 | 19738925 | 5942285 | 13796640 | 9647802 | 4590963 | 5056839 | 12143769 | 4670276 | 7473493 | 0 | 0 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | CCI | 2012 | Q1 | Q1 - 2012 | 3031253 | 0 | 3031253 | 2327822 | 0 | 2327822 | 2331722 | 0 | 2331722 | 14245272 | 5285285 | 8959987 | 8295747 | 4466701 | 3829046 | 10205696 | 4466701 | 5738995 | 928800 | 542000 | 386800 | 462945 | 158351 | 304594 | 574563 | 222664 | 351899 | 500000 | 115000 | 385000 | 221631 | 41178 | 180453 | 290000 | 53178 | 236822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 0 | 50400 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 0 | 0 | 0 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 11359873 | 4666230 | 6693643 | 14401709 | 4742543 | 9659166 | 19738925 | 5942285 | 13796640 | 11359873 | 4666230 | 6693643 | 14401709 | 4742543 | 9659166 | 0 | 0 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | CCI | 2012 | Q2 | Q2 - 2012 | 3031253 | 0 | 3031253 | 2363077 | 0 | 2363077 | 2455500 | 0 | 2455500 | 14245272 | 5285285 | 8959987 | 9635749 | 4466701 | 5169048 | 11105500 | 4466701 | 6638799 | 928800 | 542000 | 386800 | 531446 | 217665 | 313781 | 633877 | 281978 | 351899 | 500000 | 115000 | 385000 | 330340 | 51758 | 278582 | 400655 | 66758 | 333897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 0 | 50400 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 13860340 | 4736124 | 9124216 | 15595260 | 4815437 | 10779823 | 19738925 | 5942285 | 13796640 | 13860340 | 4736124 | 9124216 | 15595260 | 4815437 | 10779823 | 0 | 0 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | CCI | 2012 | Q3 | Q3 - 2012 | 3031253 | 0 | 3031253 | 2534594 | 0 | 2534594 | 2608094 | 0 | 2608094 | 14245272 | 5285285 | 8959987 | 11192663 | 4511201 | 6681462 | 11884500 | 4661201 | 7223299 | 928800 | 542000 | 386800 | 604457 | 272771 | 331686 | 689772 | 337086 | 352686 | 500000 | 115000 | 385000 | 405616 | 65239 | 340377 | 445616 | 80239 | 365377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 0 | 50400 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 15737058 | 4849211 | 10887847 | 16627710 | 5078526 | 11549184 | 19738925 | 5942285 | 13796640 | 15737058 | 4849211 | 10887847 | 16627710 | 5078526 | 11549184 | 0 | 0 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | CCI | 2012 | Q4 | Q4 - 2012 | 3031253 | 0 | 3031253 | 2607867 | 0 | 2607867 | 2637867 | 0 | 2637867 | 14245272 | 5285285 | 8959987 | 11846982 | 4692871 | 7154111 | 12281265 | 4692871 | 7588394 | 928800 | 542000 | 386800 | 693809 | 329641 | 364168 | 738809 | 374641 | 364168 | 500000 | 115000 | 385000 | 441941 | 75192 | 366749 | 461941 | 90192 | 371749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 | 0 | 50400 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 0 | 0 | 0 | 17100 | 0 | 17100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 16590327 | 5097704 | 11492623 | 17136710 | 5157704 | 11979006 | 19738925 | 5942285 | 13796640 | 16590327 | 5097704 | 11492623 | 17136710 | 5157704 | 11979006 | 0 | 0 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | CCI | 2013 | Q1 | Q1 - 2013 | 2781253 | 0 | 2781253 | 2643458 | 0 | 2643458 | 2768458 | 0 | 2768458 | 14443944 | 5285285 | 9158659 | 12416761 | 4850005 | 7566756 | 12721765 | 5155006 | 7566759 | 978800 | 542000 | 436800 | 787884 | 368199 | 419685 | 804999 | 368199 | 436800 | 500000 | 115000 | 385000 | 455615 | 79207 | 376408 | 464207 | 79207 | 385000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 0 | 0 | 0 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 17303446 | 5297411 | 12006035 | 17794357 | 5602412 | 12191945 | 19738925 | 5942285 | 13796640 | 17303446 | 5297411 | 12006035 | 17794357 | 5602412 | 12191945 | 0 | 0 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | CCI | 2013 | Q2 | Q2 - 2013 | 2613062 | 0 | 2613062 | 2613062 | 0 | 2613062 | 2613062 | 0 | 2613062 | 14612135 | 5285285 | 9326850 | 12652358 | 4905023 | 7747335 | 12952358 | 5155024 | 7797334 | 978800 | 542000 | 436800 | 810540 | 368199 | 442341 | 845540 | 368199 | 477341 | 500000 | 115000 | 385000 | 476760 | 79207 | 397553 | 478760 | 79207 | 399553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 4723 | 0 | 4723 | 4723 | 0 | 4723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 17557171 | 5352429 | 12204742 | 17894171 | 5602430 | 12291741 | 19738925 | 5942285 | 13796640 | 17557171 | 5352429 | 12204742 | 17894171 | 5602430 | 12291741 | 0 | 0 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | CCI | 2013 | Q3 | Q3 - 2013 | 2613062 | 0 | 2613062 | 2613599 | 0 | 2613599 | 2613599 | 0 | 2613599 | 14612135 | 5285285 | 9326850 | 13014033 | 5215892 | 7798141 | 13105000 | 5215892 | 7889108 | 978800 | 542000 | 436800 | 845552 | 403211 | 442341 | 902577 | 460236 | 442341 | 500000 | 115000 | 385000 | 479995 | 82442 | 397553 | 500000 | 102447 | 397553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 1278 | 0 | 1278 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 17954185 | 5701545 | 12252640 | 18156104 | 5778575 | 12377529 | 19738925 | 5942285 | 13796640 | 17954185 | 5701545 | 12252640 | 18156104 | 5778575 | 12377529 | 0 | 0 | Ronan Telephone Co. | TRUE
NT10BIX5570148 | CCI | 2013 | Q4 | Q4 - 2013 | 2613062 | 0 | 2613062 | 2613599 | 0 | 2613599 | 2613599 | 0 | 2613599 | 14612135 | 5285285 | 9326850 | 13135256 | 5227225 | 7908031 | 13664316 | 5285285 | 8379031 | 978800 | 542000 | 436800 | 857123 | 414782 | 442341 | 917123 | 474782 | 442341 | 500000 | 115000 | 385000 | 492017 | 94464 | 397553 | 500000 | 102447 | 397553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 51728 | 0 | 51728 | 35200 | 0 | 35200 | 3750 | 0 | 3750 | 35200 | 0 | 35200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 948000 | 0 | 948000 | 19738925 | 5942285 | 13796640 | 18101473 | 5736471 | 12365002 | 18729966 | 5862514 | 12867452 | 19738925 | 5942285 | 13796640 | 18101473 | 5736471 | 12365002 | 18729966 | 5862514 | 12867452 | 0 | 0 | Ronan Telephone Co. | TRUE
NT10BIX5570150 | CCI | 2010 | Q4 | Q4 - 2010 | 38619962 | 7441061 | 31178901 | 0 | 0 | 0 | 0 | 0 | 0 | 70971874 | 13914779 | 57057095 | 0 | 0 | 0 | 4200000 | 840000 | 3360000 | 650000 | 190803 | 459197 | 4118 | 0 | 4118 | 21500 | 4300 | 17200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 25872 | 25872 | 0 | 1195000 | 239000 | 956000 | 117318786 | 23463757 | 93855029 | 29990 | 25872 | 4118 | 5416500 | 1083300 | 4333200 | 117318786 | 23463757 | 93855029 | 29990 | 25872 | 4118 | 5416500 | 1083300 | 4333200 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | CCI | 2011 | Q1 | Q1 - 2011 | 38619962 | 7441061 | 31178901 | 0 | 0 | 0 | 12190000 | 2450000 | 9740000 | 70971874 | 13914779 | 57057095 | 5224750 | 3774750 | 1450000 | 14750000 | 3774750 | 10975250 | 650000 | 190803 | 459197 | 39753 | 0 | 39753 | 60000 | 12000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 67711 | 25872 | 41839 | 2250000 | 450000 | 1800000 | 117318786 | 23463757 | 93855029 | 5332214 | 3800622 | 1531592 | 29250000 | 6686750 | 22563250 | 117318786 | 23463757 | 93855029 | 5332214 | 3800622 | 1531592 | 29250000 | 6686750 | 22563250 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | CCI | 2011 | Q2 | Q2 - 2011 | 38619962 | 7441061 | 31178901 | 0 | 0 | 0 | 14550000 | 2900000 | 11650000 | 70971874 | 13914779 | 57057095 | 12877410 | 4599750 | 8277660 | 21125000 | 5500000 | 15625000 | 650000 | 190803 | 459197 | 47118 | 0 | 47118 | 67000 | 12000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 146343 | 36468 | 109875 | 1988750 | 423750 | 1565000 | 117318786 | 23463757 | 93855029 | 13070871 | 4636218 | 8434653 | 37730750 | 8835750 | 28895000 | 117318786 | 23463757 | 93855029 | 13070871 | 4636218 | 8434653 | 37730750 | 8835750 | 28895000 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | CCI | 2011 | Q3 | Q3 - 2011 | 38619962 | 7441061 | 31178901 | 5794718 | 0 | 5794718 | 16750000 | 4187500 | 12562500 | 70971874 | 13914779 | 57057095 | 21851754 | 7030713 | 14821041 | 30500000 | 9150000 | 21350000 | 650000 | 190803 | 459197 | 47118 | 0 | 47118 | 60000 | 12000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 296274 | 75732 | 220542 | 850000 | 170000 | 680000 | 117318786 | 23463757 | 93855029 | 27989864 | 7106445 | 20883419 | 48160000 | 13519500 | 34640500 | 117318786 | 23463757 | 93855029 | 27989864 | 7106445 | 20883419 | 48160000 | 13519500 | 34640500 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | CCI | 2011 | Q4 | Q4 - 2011 | 38619962 | 7441061 | 31178901 | 19742681 | 3065267 | 16677414 | 26000000 | 6350000 | 19650000 | 70971874 | 13914779 | 57057095 | 24714136 | 7426095 | 17288041 | 38000000 | 9250000 | 28750000 | 650000 | 190803 | 459197 | 49709 | 0 | 49709 | 62500 | 12500 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 414820 | 104838 | 309982 | 1500000 | 387500 | 1112500 | 117318786 | 23463757 | 93855029 | 44921346 | 10596200 | 34325146 | 65562500 | 16000000 | 49562500 | 117318786 | 23463757 | 93855029 | 44921346 | 10596200 | 34325146 | 65562500 | 16000000 | 49562500 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | CCI | 2012 | Q1 | Q1 - 2012 | 38619962 | 7441061 | 31178901 | 27024480 | 3066222 | 23958258 | 31200000 | 5600000 | 25600000 | 70971874 | 13914779 | 57057095 | 29907549 | 9597628 | 20309921 | 45800000 | 9960000 | 35840000 | 650000 | 190803 | 459197 | 50627 | 0 | 50627 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 846019 | 230000 | 616019 | 2000000 | 400000 | 1600000 | 117318786 | 23463757 | 93855029 | 57828675 | 12893850 | 44934825 | 79200000 | 16000000 | 63200000 | 117318786 | 23463757 | 93855029 | 57828675 | 12893850 | 44934825 | 79200000 | 16000000 | 63200000 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | CCI | 2012 | Q2 | Q2 - 2012 | 38619962 | 7441061 | 31178901 | 27580205 | 3085374 | 24494831 | 32850000 | 6570000 | 26280000 | 70971874 | 13914779 | 57057095 | 46166804 | 9597628 | 36569176 | 54250000 | 10850000 | 43400000 | 650000 | 190803 | 459197 | 56076 | 4544 | 51532 | 200000 | 40000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 1653137 | 349248 | 1303889 | 3250000 | 650000 | 2600000 | 117318786 | 23463757 | 93855029 | 75456222 | 13036794 | 62419428 | 90550000 | 18110000 | 72440000 | 117318786 | 23463757 | 93855029 | 75456222 | 13036794 | 62419428 | 90550000 | 18110000 | 72440000 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | CCI | 2012 | Q3 | Q3 - 2012 | 38619962 | 7441061 | 31178901 | 29136068 | 3469406 | 25666662 | 32250000 | 6450000 | 25800000 | 70971874 | 13914779 | 57057095 | 54766451 | 9597628 | 45168823 | 62750000 | 12550000 | 50200000 | 650000 | 190803 | 459197 | 59211 | 6191 | 53020 | 75000 | 15000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 2328106 | 412976 | 1915130 | 4500000 | 900000 | 3600000 | 117318786 | 23463757 | 93855029 | 86289836 | 13486201 | 72803635 | 99575000 | 19915000 | 79660000 | 117318786 | 23463757 | 93855029 | 86289836 | 13486201 | 72803635 | 99575000 | 19915000 | 79660000 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | CCI | 2012 | Q4 | Q4 - 2012 | 38619962 | 7441061 | 31178901 | 35085673 | 6477287 | 28608386 | 37500000 | 7000000 | 30500000 | 70971874 | 13914779 | 57057095 | 64113748 | 13810830 | 50302918 | 67500000 | 13900000 | 53600000 | 650000 | 190803 | 459197 | 62703 | 9684 | 53020 | 75000 | 15000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 2946550 | 451067 | 2495483 | 4500000 | 900000 | 3600000 | 117318786 | 23463757 | 93855029 | 102208674 | 20748868 | 81459807 | 109575000 | 21815000 | 87760000 | 117318786 | 23463757 | 93855029 | 102208674 | 20748868 | 81459807 | 109575000 | 21815000 | 87760000 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | CCI | 2013 | Q1 | Q1 - 2013 | 38619962 | 7441061 | 31178901 | 35549742 | 6554788 | 28994953 | 38619962 | 7441061 | 31178900 | 70971874 | 13914779 | 57057095 | 66911063 | 13914779 | 52996284 | 70971850 | 13914779 | 57057071 | 650000 | 190803 | 459197 | 62703 | 9684 | 53020 | 62703 | 9684 | 53020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7076950 | 1917114 | 5159836 | 3075915 | 472160 | 2603755 | 6580425 | 1908295 | 4672130 | 117318786 | 23463757 | 93855029 | 105599423 | 20951411 | 84648012 | 116234940 | 23273819 | 92961121 | 117318786 | 23463757 | 93855029 | 105599423 | 20951411 | 84648012 | 116234940 | 23273819 | 92961121 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | CCI | 2013 | Q2 | Q2 - 2013 | 39575806 | 7645380 | 31930426 | 38002667 | 7407719 | 30594948 | 39575806 | 7645380 | 31930426 | 71771874 | 14146779 | 57625095 | 70971850 | 13914779 | 57057071 | 71771874 | 14146779 | 57625095 | 65000 | 9684 | 55316 | 62703 | 9683 | 53020 | 65000 | 9684 | 55316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5906106 | 1661914 | 4244192 | 4148357 | 951762 | 3196595 | 5906106 | 1661914 | 4244192 | 117318786 | 23463757 | 93855029 | 113185577 | 22283943 | 90901634 | 117318786 | 23463757 | 93855029 | 117318786 | 23463757 | 93855029 | 113185577 | 22283943 | 90901634 | 117318786 | 23463757 | 93855029 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570150 | CCI | 2013 | Q3 | Q3 - 2013 | 39697535 | 7756764 | 31940771 | 39650921 | 7754517 | 31896404 | 39650921 | 7754517 | 31896404 | 71771874 | 14146779 | 57625095 | 71771752 | 14146779 | 57624973 | 71771752 | 14146779 | 57624973 | 65000 | 9684 | 55316 | 62704 | 9684 | 53020 | 62704 | 9684 | 53020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5784377 | 1550530 | 4233847 | 5684672 | 1531088 | 4153584 | 5684672 | 1531088 | 4153584 | 117318786 | 23463757 | 93855029 | 117170049 | 23442068 | 93727981 | 117170049 | 23442068 | 93727981 | 117318786 | 23463757 | 93855029 | 117170049 | 23442068 | 93727981 | 117170049 | 23442068 | 93727981 | 0 | 0 | Department of Administration Services Bureau of Enterprise Systems & Technology | TRUE
NT10BIX5570153 | CCI | 2010 | Q4 | Q4 - 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | CCI | 2011 | Q1 | Q1 - 2011 | 4484034 | 1834958 | 2649076 | 267500 | 86310 | 181190 | 297549 | 59510 | 238039 | 27531256 | 8441149 | 19090107 | 7027505 | 1394147 | 5633358 | 7721930 | 1544386 | 6177544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 7295005 | 1480457 | 5814548 | 8019479 | 1603896 | 6415583 | 32476991 | 10737808 | 21739183 | 7295005 | 1480457 | 5814548 | 8019479 | 1603896 | 6415583 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | CCI | 2011 | Q2 | Q2 - 2011 | 4484034 | 1834958 | 2649076 | 290442 | 86310 | 204132 | 2005163 | 501290 | 1503873 | 27531256 | 8441149 | 19090107 | 7644601 | 1523321 | 6121280 | 8222038 | 2055510 | 6166528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 7935043 | 1609631 | 6325412 | 10227201 | 2556800 | 7670401 | 32476991 | 10737808 | 21739183 | 7935043 | 1609631 | 6325412 | 10227201 | 2556800 | 7670401 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | CCI | 2011 | Q3 | Q3 - 2011 | 4484034 | 1834958 | 2649076 | 3015884 | 1278564 | 1737320 | 4249373 | 1578564 | 2670809 | 27531256 | 8441149 | 19090107 | 7784100 | 1727781 | 6056319 | 12347562 | 2227781 | 10119781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 10799984 | 3006345 | 7793639 | 16596935 | 3806345 | 12790590 | 32476991 | 10737808 | 21739183 | 10799984 | 3006345 | 7793639 | 16596935 | 3806345 | 12790590 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | CCI | 2011 | Q4 | Q4 - 2011 | 4484034 | 1834958 | 2649076 | 4427596 | 1771039 | 2656557 | 4484034 | 1793614 | 2690420 | 27531256 | 8441149 | 19090107 | 12251700 | 2964338 | 9287362 | 15095457 | 3764338 | 11331119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 16679296 | 4735377 | 11943919 | 19579491 | 5557952 | 14021539 | 32476991 | 10737808 | 21739183 | 16679296 | 4735377 | 11943919 | 19579491 | 5557952 | 14021539 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | CCI | 2012 | Q1 | Q1 - 2012 | 4484034 | 1834958 | 2649076 | 5496885 | 2213902 | 3282983 | 6248380 | 2482007 | 3766373 | 27531256 | 8441149 | 19090107 | 14023524 | 3205456 | 10818068 | 15380039 | 3845010 | 11535029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 19520409 | 5419358 | 14101051 | 21628419 | 6327017 | 15301402 | 32476991 | 10737808 | 21739183 | 19520409 | 5419358 | 14101051 | 21628419 | 6327017 | 15301402 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | CCI | 2012 | Q2 | Q2 - 2012 | 4484034 | 1834958 | 2649076 | 6385505 | 2479757 | 3905748 | 7018065 | 2807226 | 4210839 | 27531256 | 8441149 | 19090107 | 14460705 | 3424806 | 11035899 | 16527535 | 4131884 | 12395651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 20846210 | 5904563 | 14941647 | 23545600 | 6939110 | 16606490 | 32476991 | 10737808 | 21739183 | 20846210 | 5904563 | 14941647 | 23545600 | 6939110 | 16606490 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | CCI | 2012 | Q3 | Q3 - 2012 | 4484034 | 1834958 | 2649076 | 6438186 | 2508520 | 3929666 | 6624891 | 2508520 | 4116371 | 27531256 | 8441149 | 19090107 | 19828407 | 4696882 | 15131525 | 21374984 | 5343746 | 16031238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 26266593 | 7205402 | 19061191 | 27999875 | 7852266 | 20147609 | 32476991 | 10737808 | 21739183 | 26266593 | 7205402 | 19061191 | 27999875 | 7852266 | 20147609 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | CCI | 2012 | Q4 | Q4 - 2012 | 4484034 | 1834958 | 2649076 | 6615274 | 2559772 | 4055502 | 6746553 | 2697516 | 4049037 | 27531256 | 8441149 | 19090107 | 21024308 | 5431277 | 15593031 | 23245548 | 6643933 | 16601615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461701 | 461701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 27639582 | 7991049 | 19648533 | 29992101 | 9341449 | 20650652 | 32476991 | 10737808 | 21739183 | 27639582 | 7991049 | 19648533 | 29992101 | 9341449 | 20650652 | 0 | 0 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | CCI | 2013 | Q1 | Q1 - 2013 | 7102776 | 2484533 | 4618243 | 6658650 | 2648803 | 4009847 | 6672200 | 2655474 | 4016726 | 24046719 | 8072258 | 15974461 | 20362892 | 4971237 | 15391655 | 23669347 | 6455975 | 17213372 | 629796 | 78349 | 551447 | 512773 | 344818 | 167955 | 541773 | 373818 | 167955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583182 | 102669 | 480513 | 518072 | 313929 | 204143 | 560572 | 356429 | 204143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114518 | 0 | 114518 | 107250 | 18645 | 88605 | 107250 | 18645 | 88605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737809 | 21739182 | 28159637 | 8297432 | 19862205 | 31551142 | 9860341 | 21690801 | 32476991 | 10737809 | 21739182 | 28159637 | 8297432 | 19862205 | 31551142 | 9860341 | 21690801 | 0 | 604782 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | CCI | 2013 | Q2 | Q2 - 2013 | 7102776 | 2781489 | 4321287 | 6706546 | 2689820 | 4016726 | 7363860 | 3314150 | 4049710 | 24046719 | 7775301 | 16271418 | 21947577 | 5541546 | 16406031 | 23799961 | 6578615 | 17221346 | 629796 | 78349 | 551447 | 543334 | 375379 | 167955 | 586601 | 411222 | 175379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583182 | 102669 | 480513 | 556893 | 352750 | 204143 | 619319 | 415176 | 204143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114518 | 0 | 114518 | 107250 | 18645 | 88605 | 107250 | 18645 | 88605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 29861600 | 8978140 | 20883460 | 32476991 | 10737808 | 21739183 | 32476991 | 10737808 | 21739183 | 29861600 | 8978140 | 20883460 | 32476991 | 10737808 | 21739183 | 0 | 151639 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570153 | CCI | 2013 | Q3 | Q3 - 2013 | 7364740 | 3348014 | 4016726 | 7340847 | 3324121 | 4016726 | 7340847 | 3324121 | 4016726 | 23807396 | 6555996 | 17251400 | 23796004 | 6538845 | 17257159 | 23796004 | 6538845 | 17257159 | 583286 | 404977 | 178309 | 635417 | 472753 | 162664 | 635417 | 472753 | 162664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 614319 | 410176 | 204143 | 598798 | 383244 | 215554 | 598798 | 383244 | 215554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107250 | 18645 | 88605 | 105925 | 18845 | 87080 | 105925 | 18845 | 87080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32476991 | 10737808 | 21739183 | 32476991 | 10737808 | 21739183 | 32476991 | 10737808 | 21739183 | 32476991 | 10737808 | 21739183 | 32476991 | 10737808 | 21739183 | 32476991 | 10737808 | 21739183 | 0 | 1640788 | Ocean State Higher Education Economic Development Administrative Network | TRUE
NT10BIX5570156 | CCI | 2010 | Q4 | Q4 - 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 0 | 0 | 0 | 6944601 | 1777800 | 5166801 | 252000 | 0 | 252000 | 0 | 0 | 0 | 42000 | 0 | 0 | 24832866 | 11912238 | 12920628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 0 | 0 | 0 | 1838852 | 470750 | 1368102 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 0 | 0 | 0 | 8825453 | 2248550 | 6534903 | 135300777 | 34665587 | 100635190 | 0 | 0 | 0 | 8825453 | 2248550 | 6534903 | 0 | 0 | Centennial Board of Cooperative Educational Services | TRUE
NT10BIX5570156 | CCI | 2011 | Q1 | Q1 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 0 | 0 | 0 | 6944601 | 1777800 | 5166801 | 252000 | 0 | 252000 | 0 | 0 | 0 | 42000 | 0 | 0 | 24832866 | 11912238 | 12920628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 0 | 0 | 0 | 1838852 | 470750 | 1368102 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 0 | 0 | 0 | 8825453 | 2248550 | 6534903 | 135300777 | 34665587 | 100635190 | 0 | 0 | 0 | 8825453 | 2248550 | 6534903 | 0 | 0 | Centennial Board of Cooperative Educational Services | TRUE
NT10BIX5570157 | CCI | 2010 | Q4 | Q4 - 2010 | 9572649 | 800000 | 8772649 | 0 | 0 | 0 | 500000 | 0 | 500000 | 3793469 | 3180697 | 612772 | 0 | 0 | 0 | 0 | 0 | 0 | 333000 | 120000 | 213000 | 50018 | 2200 | 47818 | 76200 | 6200 | 70000 | 1582200 | 1537200 | 45000 | 128100 | 128100 | 0 | 256200 | 256200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 75000 | 63000 | 12000 | 2063882 | 253750 | 1810132 | 9485 | 9485 | 0 | 75000 | 25000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608869 | 0 | 608869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18029069 | 5891647 | 12137422 | 187603 | 139785 | 47818 | 982400 | 350400 | 632000 | 18029069 | 5891647 | 12137422 | 187603 | 139785 | 47818 | 982400 | 350400 | 632000 | 0 | 0 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | CCI | 2011 | Q1 | Q1 - 2011 | 9572649 | 800000 | 8772649 | 488759 | 0 | 488759 | 3000000 | 500000 | 2500000 | 3793469 | 3180697 | 612772 | 0 | 0 | 0 | 150000 | 150000 | 0 | 333000 | 120000 | 213000 | 70349 | 7405 | 62944 | 120000 | 17000 | 103000 | 1582200 | 1537200 | 45000 | 256200 | 256200 | 0 | 384300 | 384300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 75000 | 16937 | 0 | 16937 | 75000 | 0 | 75000 | 2063882 | 253750 | 1810132 | 56614 | 20614 | 36000 | 120000 | 40000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608869 | 0 | 608869 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18029069 | 5891647 | 12137422 | 888859 | 284219 | 604640 | 3899300 | 1091300 | 2808000 | 18029069 | 5891647 | 12137422 | 888859 | 284219 | 604640 | 3899300 | 1091300 | 2808000 | 0 | 0 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | CCI | 2011 | Q2 | Q2 - 2011 | 9572649 | 800000 | 8772649 | 685077 | 0 | 685077 | 3000000 | 600000 | 2400000 | 3793469 | 3180697 | 612772 | 0 | 0 | 0 | 200000 | 0 | 200000 | 333000 | 120000 | 213000 | 95108 | 17205 | 77903 | 130000 | 30000 | 100000 | 1582200 | 1537200 | 45000 | 275415 | 275415 | 0 | 375000 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 15000 | 0 | 15000 | 2063882 | 253750 | 1810132 | 98451 | 30739 | 67712 | 130000 | 45000 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608869 | 0 | 608869 | 0 | 0 | 0 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18029069 | 5891647 | 12137422 | 1154051 | 323359 | 830692 | 4050000 | 1050000 | 3000000 | 18029069 | 5891647 | 12137422 | 1154051 | 323359 | 830692 | 4050000 | 1050000 | 3000000 | 0 | 0 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | CCI | 2011 | Q3 | Q3 - 2011 | 9572649 | 800000 | 8772649 | 1810524 | 298244 | 1512280 | 2775000 | 675000 | 2100000 | 3793469 | 3180697 | 612772 | 0 | 0 | 0 | 0 | 0 | 0 | 333000 | 120000 | 213000 | 145502 | 28474 | 117028 | 210000 | 50000 | 160000 | 1582200 | 1537200 | 45000 | 435540 | 435540 | 0 | 525210 | 525210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 75000 | 0 | 75000 | 2063882 | 253750 | 1810132 | 2293322 | 589689 | 1703633 | 3400000 | 1000000 | 2400000 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 608869 | 0 | 608869 | 682 | 0 | 682 | 275000 | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334 | 0 | 334 | 334 | 0 | 334 | 18029069 | 5891647 | 12137422 | 4686004 | 1351947 | 3334057 | 7260644 | 2250210 | 5010434 | 18029069 | 5891647 | 12137422 | 4686004 | 1351947 | 3334057 | 7260644 | 2250210 | 5010434 | 0 | 0 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | CCI | 2011 | Q4 | Q4 - 2011 | 6345080 | 960000 | 5385080 | 2415588 | 636227 | 1779361 | 3400000 | 830000 | 2570000 | 2451391 | 1101550 | 1349841 | 0 | 0 | 0 | 250000 | 250000 | 0 | 303000 | 150000 | 153000 | 231889 | 39460 | 192429 | 260000 | 60000 | 200000 | 1121040 | 1076040 | 45000 | 673585 | 646905 | 26680 | 750000 | 720000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 3471927 | 867645 | 2604282 | 5100000 | 1100000 | 4000000 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 96002 | 0 | 96002 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334 | 0 | 334 | 334 | 0 | 334 | 16678762 | 4541340 | 12137422 | 6899125 | 2190237 | 4708888 | 9970134 | 2960000 | 7010134 | 16678762 | 4541340 | 12137422 | 6899125 | 2190237 | 4708888 | 9970134 | 2960000 | 7010134 | 0 | 0 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | CCI | 2012 | Q1 | Q1 - 2012 | 6345080 | 960000 | 5385080 | 4216949 | 886277 | 3330672 | 4800000 | 986277 | 3813723 | 2451391 | 1101550 | 1349841 | 1206 | 0 | 1206 | 1200000 | 300000 | 900000 | 303000 | 150000 | 153000 | 375410 | 51864 | 323546 | 405000 | 75000 | 330000 | 1121040 | 1076040 | 45000 | 629003 | 602070 | 26933 | 750000 | 710000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 3953391 | 881744 | 3071647 | 5053391 | 981744 | 4071647 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 135657 | 0 | 135657 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1239 | 0 | 1239 | 1239 | 0 | 1239 | 16678762 | 4541340 | 12137422 | 9322655 | 2421955 | 6900700 | 12419430 | 3053021 | 9366409 | 16678762 | 4541340 | 12137422 | 9322655 | 2421955 | 6900700 | 12419430 | 3053021 | 9366409 | 0 | 0 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | CCI | 2012 | Q2 | Q2 - 2012 | 6345080 | 960000 | 5385080 | 3388792 | 570801 | 2817991 | 3440000 | 590000 | 2850000 | 2451391 | 1101550 | 1349841 | 1206 | 0 | 1206 | 150000 | 0 | 150000 | 303000 | 150000 | 153000 | 210396 | 61986 | 148410 | 230000 | 70000 | 160000 | 1121040 | 1076040 | 45000 | 647351 | 608475 | 38876 | 766740 | 691740 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 5389948 | 1255127 | 4134821 | 5605000 | 1270000 | 4335000 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 189549 | 38037 | 151512 | 238037 | 38037 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2516 | 0 | 2516 | 3500 | 0 | 3500 | 16678762 | 4541340 | 12137422 | 9839558 | 2534426 | 7305132 | 10443077 | 2659777 | 7783300 | 16678762 | 4541340 | 12137422 | 9839558 | 2534426 | 7305132 | 10443077 | 2659777 | 7783300 | 0 | 0 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | CCI | 2012 | Q3 | Q3 - 2012 | 6345080 | 960000 | 5385080 | 3438596 | 570801 | 2867795 | 3471000 | 571000 | 2900000 | 2451391 | 1101550 | 1349841 | 126934 | 113273 | 13661 | 180000 | 150000 | 30000 | 303000 | 150000 | 153000 | 215535 | 67336 | 148199 | 230000 | 70000 | 160000 | 1121040 | 1076040 | 45000 | 730616 | 691740 | 38876 | 805005 | 775005 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 5605058 | 1257821 | 4347237 | 5640237 | 1270000 | 4370237 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 179906 | 38037 | 141869 | 208037 | 38037 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3320 | 0 | 3320 | 4125 | 0 | 4125 | 16678762 | 4541340 | 12137422 | 10309765 | 2739008 | 7570757 | 10548204 | 2874042 | 7674162 | 16678762 | 4541340 | 12137422 | 10309765 | 2739008 | 7570757 | 10548204 | 2874042 | 7674162 | 0 | 0 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | CCI | 2012 | Q4 | Q4 - 2012 | 6345080 | 960000 | 5385080 | 3442645 | 570801 | 2871844 | 3447645 | 570801 | 2876844 | 2451391 | 1101550 | 1349841 | 148774 | 113273 | 35501 | 180000 | 125000 | 55000 | 303000 | 150000 | 153000 | 224101 | 69202 | 154899 | 232000 | 73000 | 159000 | 1121040 | 1076040 | 45000 | 813881 | 775005 | 38876 | 898270 | 858270 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 5630946 | 1262687 | 4368259 | 5657000 | 1267000 | 4390000 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 182912 | 38037 | 144875 | 187037 | 38037 | 149000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4382 | 0 | 4382 | 5395 | 0 | 5395 | 16678762 | 4541340 | 12137422 | 10457441 | 2829005 | 7628436 | 10617147 | 2932108 | 7685039 | 16678762 | 4541340 | 12137422 | 10457441 | 2829005 | 7628436 | 10617147 | 2932108 | 7685039 | 0 | 0 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | CCI | 2013 | Q1 | Q1 - 2013 | 6345080 | 960000 | 5385080 | 3448357 | 570801 | 2877556 | 3463357 | 570801 | 2892556 | 2451391 | 1101550 | 1349841 | 158403 | 113273 | 45130 | 858403 | 233273 | 625130 | 303000 | 150000 | 153000 | 242130 | 75099 | 167031 | 268000 | 95000 | 173000 | 1121040 | 1076040 | 45000 | 919611 | 858270 | 61341 | 1002876 | 941535 | 61341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 5660851 | 1270458 | 4390393 | 5692985 | 1280458 | 4412527 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 195116 | 38037 | 157079 | 215116 | 38037 | 177079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5372 | 0 | 5372 | 5372 | 0 | 5372 | 16678762 | 4541340 | 12137422 | 10639640 | 2925938 | 7713702 | 11515909 | 3159104 | 8356805 | 16678762 | 4541340 | 12137422 | 10639640 | 2925938 | 7713702 | 11515909 | 3159104 | 8356805 | 0 | 0 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | CCI | 2013 | Q2 | Q2 - 2013 | 6345080 | 960000 | 5385080 | 3449397 | 570801 | 2878596 | 3519397 | 570801 | 2948596 | 2451391 | 1101550 | 1349841 | 158429 | 113273 | 45156 | 858403 | 233273 | 625130 | 303000 | 150000 | 153000 | 252308 | 79240 | 173068 | 267000 | 89000 | 178000 | 1121040 | 1076040 | 45000 | 1002876 | 941535 | 61341 | 1086800 | 1024800 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 5685128 | 1272436 | 4412692 | 5712234 | 1277000 | 4435234 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 196646 | 38037 | 158609 | 248037 | 38037 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6425 | 0 | 6425 | 7478 | 0 | 7478 | 16678762 | 4541340 | 12137422 | 10761009 | 3015322 | 7745687 | 11709149 | 3232911 | 8476238 | 16678762 | 4541340 | 12137422 | 10761009 | 3015322 | 7745687 | 11709149 | 3232911 | 8476238 | 0 | 0 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | CCI | 2013 | Q3 | Q3 - 2013 | 6345080 | 960000 | 5385080 | 3452645 | 570801 | 2881844 | 3552645 | 570801 | 2981844 | 2451391 | 1101550 | 1349841 | 890859 | 333002 | 557857 | 890859 | 333002 | 557857 | 303000 | 150000 | 153000 | 272626 | 84717 | 187909 | 309000 | 89000 | 220000 | 1121040 | 1076040 | 45000 | 1058386 | 997045 | 61341 | 1059045 | 997045 | 62000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944251 | 1253750 | 4690501 | 5709072 | 1273838 | 4435234 | 5735000 | 1275000 | 4460000 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 196646 | 38037 | 158609 | 247037 | 38037 | 209000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7488 | 0 | 7488 | 8572 | 0 | 8572 | 16678762 | 4541340 | 12137422 | 11597522 | 3297440 | 8300082 | 11811958 | 3302885 | 8509073 | 16678762 | 4541340 | 12137422 | 11597522 | 3297440 | 8300082 | 11811958 | 3302885 | 8509073 | 0 | 0 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570157 | CCI | 2013 | Q4 | Q4 - 2013 | 6345080 | 960000 | 5385080 | 3454638 | 570801 | 2883837 | 3504638 | 570801 | 2933837 | 2451391 | 1101550 | 1349841 | 890859 | 333002 | 557857 | 990859 | 393002 | 597857 | 303000 | 150000 | 153000 | 301600 | 87383 | 214217 | 321600 | 90383 | 231217 | 1121040 | 1076040 | 45000 | 1169406 | 1108065 | 61341 | 1252671 | 1191330 | 61341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 10500 | 9700 | 0 | 9700 | 9700 | 0 | 9700 | 5944521 | 1253750 | 4690501 | 5735489 | 1273838 | 4461651 | 5780708 | 1275838 | 4504870 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 100 | 503500 | 0 | 503500 | 223865 | 38037 | 185828 | 278865 | 38037 | 240828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8572 | 0 | 8572 | 8572 | 0 | 8572 | 16679032 | 4541340 | 12137422 | 11794229 | 3411126 | 8383103 | 12147713 | 3559391 | 8588322 | 16679032 | 4541340 | 12137422 | 11794229 | 3411126 | 8383103 | 12147713 | 3559391 | 8588322 | 0 | 0 | Adams County Communications Center, Inc. | TRUE
NT10BIX5570158 | CCI | 2010 | Q4 | Q4 - 2010 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 62968 | 62968 | 0 | 200000 | 200000 | 0 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 0 | 0 | 0 | 560000 | 60000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 62968 | 62968 | 0 | 760000 | 260000 | 500000 | 217894365 | 63254365 | 154640000 | 62968 | 62968 | 0 | 760000 | 260000 | 500000 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | CCI | 2011 | Q1 | Q1 - 2011 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 80029 | 80029 | 0 | 359555 | 359555 | 0 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 515778 | 0 | 515778 | 1499998 | 0 | 1499998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 595807 | 80029 | 515778 | 1859553 | 359555 | 1499998 | 217894365 | 63254365 | 154640000 | 595807 | 80029 | 515778 | 1859553 | 359555 | 1499998 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | CCI | 2011 | Q2 | Q2 - 2011 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 535480 | 535480 | 0 | 800000 | 800000 | 0 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 1095026 | 0 | 1095026 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 1630506 | 535480 | 1095026 | 2800000 | 800000 | 2000000 | 217894365 | 63254365 | 154640000 | 1630506 | 535480 | 1095026 | 2800000 | 800000 | 2000000 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | CCI | 2011 | Q3 | Q3 - 2011 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 796390 | 796390 | 0 | 1000000 | 1000000 | 0 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 1398132 | 0 | 1398132 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 2194522 | 796390 | 1398132 | 3000000 | 1000000 | 2000000 | 217894365 | 63254365 | 154640000 | 2194522 | 796390 | 1398132 | 3000000 | 1000000 | 2000000 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | CCI | 2011 | Q4 | Q4 - 2011 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 999240 | 999240 | 0 | 1200000 | 1200000 | 0 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 1398132 | 0 | 1398132 | 2100000 | 0 | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 2397372 | 999240 | 1398132 | 3300000 | 1200000 | 2100000 | 217894365 | 63254365 | 154640000 | 2397372 | 999240 | 1398132 | 3300000 | 1200000 | 2100000 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | CCI | 2012 | Q1 | Q1 - 2012 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 1289713 | 1289713 | 0 | 1400000 | 1400000 | 0 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 1398132 | 0 | 1398132 | 2607410 | 0 | 2607410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 2687845 | 1289713 | 1398132 | 4007410 | 1400000 | 2607410 | 217894365 | 63254365 | 154640000 | 2687845 | 1289713 | 1398132 | 4007410 | 1400000 | 2607410 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | CCI | 2012 | Q2 | Q2 - 2012 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 1448699 | 1448699 | 0 | 1600000 | 1600000 | 0 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 2362853 | 0 | 2362853 | 2600000 | 0 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 3811552 | 1448699 | 2362853 | 4200000 | 1600000 | 2600000 | 217894365 | 63254365 | 154640000 | 3811552 | 1448699 | 2362853 | 4200000 | 1600000 | 2600000 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | CCI | 2012 | Q3 | Q3 - 2012 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 2139282 | 1823166 | 316116 | 2318524 | 1972408 | 346116 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 2873560 | 0 | 2873560 | 3286120 | 0 | 3286120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 5012842 | 1823166 | 3189676 | 5604644 | 1972408 | 3632236 | 217894365 | 63254365 | 154640000 | 5012842 | 1823166 | 3189676 | 5604644 | 1972408 | 3632236 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | CCI | 2012 | Q4 | Q4 - 2012 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 2309308 | 1993192 | 316116 | 2500000 | 2100000 | 400000 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 2873560 | 0 | 2873560 | 2957353 | 0 | 2957353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 5182868 | 1993192 | 3189676 | 5457353 | 2100000 | 3357353 | 217894365 | 63254365 | 154640000 | 5182868 | 1993192 | 3189676 | 5457353 | 2100000 | 3357353 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | CCI | 2013 | Q1 | Q1 - 2013 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 2422126 | 2067680 | 354446 | 2728000 | 2147000 | 581000 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 2965717 | 0 | 2965717 | 3070000 | 0 | 3070000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 5387843 | 2067680 | 3320163 | 5798000 | 2147000 | 3651000 | 217894365 | 63254365 | 154640000 | 5387843 | 2067680 | 3320163 | 5798000 | 2147000 | 3651000 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | CCI | 2013 | Q2 | Q2 - 2013 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 2427323 | 1973913 | 453410 | 2724911 | 2122337 | 602574 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 3367072 | 349226 | 3017846 | 3849407 | 517226 | 3332181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 5794395 | 2323139 | 3471256 | 6574318 | 2639563 | 3934755 | 217894365 | 63254365 | 154640000 | 5794395 | 2323139 | 3471256 | 6574318 | 2639563 | 3934755 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | CCI | 2013 | Q3 | Q3 - 2013 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 3007264 | 2218273 | 788991 | 3238642 | 2350228 | 888414 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 4279573 | 538792 | 3740781 | 4598090 | 639894 | 3958196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 7286837 | 2757065 | 4529772 | 7836732 | 2990122 | 4846610 | 217894365 | 63254365 | 154640000 | 7286837 | 2757065 | 4529772 | 7836732 | 2990122 | 4846610 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT10BIX5570158 | CCI | 2013 | Q4 | Q4 - 2013 | 113368574 | 20394864 | 92973710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13297104 | 2685484 | 10611620 | 3230200 | 2415661 | 814539 | 3637821 | 2613049 | 1024772 | 73597901 | 37780781 | 35817120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16360786 | 1543236 | 14817550 | 4516486 | 641413 | 3875073 | 6504968 | 744034 | 5760934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270000 | 850000 | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 217894365 | 63254365 | 154640000 | 7746686 | 3057074 | 4689612 | 10142789 | 3357083 | 6785706 | 217894365 | 63254365 | 154640000 | 7746686 | 3057074 | 4689612 | 10142789 | 3357083 | 6785706 | 0 | 0 | Los Angeles Regional Interoperable Communications System Authority | TRUE
NT11BIX5570001 | CCI | 2010 | Q3 | Q3 - 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | CCI | 2010 | Q4 | Q4 - 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 0 | 0 | 0 | 6944601 | 1777800 | 5166801 | 252000 | 0 | 252000 | 0 | 0 | 0 | 42000 | 0 | 0 | 24832866 | 11912238 | 12920628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 0 | 0 | 0 | 1838852 | 470750 | 1368102 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 0 | 0 | 0 | 8825453 | 2248550 | 6534903 | 135300777 | 34665587 | 100635190 | 0 | 0 | 0 | 8825453 | 2248550 | 6534903 | 0 | 0 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | CCI | 2011 | Q1 | Q1 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 93228004 | 18066349 | 75161655 | 0 | 0 | 0 | 0 | 0 | 0 | 252000 | 0 | 252000 | 0 | 0 | 0 | 60000 | 0 | 60000 | 24832866 | 11912238 | 12920628 | 8918958 | 8918958 | 0 | 9452958 | 8918958 | 534000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 1396723 | 0 | 1396723 | 3808862 | 0 | 3808862 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 10315681 | 8918958 | 1396723 | 13421820 | 8918958 | 4502862 | 135300777 | 34665587 | 100635190 | 10315681 | 8918958 | 1396723 | 13421820 | 8918958 | 4502862 | 0 | 0 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | CCI | 2011 | Q2 | Q2 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | 252000 | 0 | 252000 | 74598 | 0 | 74598 | 104598 | 0 | 104598 | 24832866 | 11912238 | 12920628 | 8918958 | 8918958 | 0 | 8918958 | 8918958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 5001281 | 0 | 5001281 | 11029010 | 0 | 11029010 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 13994837 | 8918958 | 5075879 | 21052566 | 8918958 | 12133608 | 135300777 | 34665587 | 100635190 | 13994837 | 8918958 | 5075879 | 21052566 | 8918958 | 12133608 | 0 | 0 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | CCI | 2011 | Q3 | Q3 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 108159 | 25000 | 83159 | 6036096 | 1025000 | 5011096 | 252000 | 0 | 252000 | 103572 | 0 | 103572 | 128572 | 0 | 128572 | 24832866 | 11912238 | 12920628 | 14814619 | 8918958 | 5895661 | 18314619 | 8918958 | 9395661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 8057626 | 0 | 8057626 | 10104689 | 0 | 10104689 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 23083976 | 8943958 | 14140018 | 34583976 | 9943958 | 24640018 | 135300777 | 34665587 | 100635190 | 23083976 | 8943958 | 14140018 | 34583976 | 9943958 | 24640018 | 0 | 0 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | CCI | 2011 | Q4 | Q4 - 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 20325643 | 1025000 | 19300643 | 26961543 | 1025000 | 25936543 | 252000 | 0 | 252000 | 116302 | 0 | 116302 | 141302 | 0 | 141302 | 24832866 | 11912238 | 12920628 | 8918958 | 8918958 | 0 | 8918958 | 8918958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 6788073 | 0 | 6788073 | 8062073 | 0 | 8062073 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 36148976 | 9943958 | 26205018 | 44083876 | 9943958 | 34139918 | 135300777 | 34665587 | 100635190 | 36148976 | 9943958 | 26205018 | 44083876 | 9943958 | 34139918 | 0 | 0 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | CCI | 2012 | Q1 | Q1 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 26481103 | 1025000 | 25456103 | 40983011 | 3025000 | 37958011 | 252000 | 0 | 252000 | 201970 | 0 | 201970 | 226970 | 0 | 226970 | 24832866 | 11912238 | 12920628 | 8918958 | 8918958 | 0 | 11912238 | 11912238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 7920452 | 0 | 7920452 | 9301521 | 0 | 9301521 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 43522483 | 9943958 | 33578525 | 62423740 | 14937238 | 47486502 | 135300777 | 34665587 | 100635190 | 43522483 | 9943958 | 33578525 | 62423740 | 14937238 | 47486502 | 0 | 0 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | CCI | 2012 | Q2 | Q2 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 43431785 | 1025000 | 42406785 | 65188073 | 1025000 | 64163073 | 252000 | 0 | 252000 | 304119 | 0 | 304119 | 431042 | 0 | 431042 | 24832866 | 11912238 | 12920628 | 9780342 | 8918958 | 861384 | 9980342 | 8918958 | 1061384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 8689218 | 0 | 8689218 | 10332810 | 0 | 10332810 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 62205464 | 9943958 | 52261506 | 85932267 | 9943958 | 75988309 | 135300777 | 34665587 | 100635190 | 62205464 | 9943958 | 52261506 | 85932267 | 9943958 | 75988309 | 0 | 2657 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | CCI | 2012 | Q3 | Q3 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 54294716 | 1025000 | 53269716 | 69933492 | 1025000 | 68908492 | 252000 | 0 | 252000 | 434193 | 0 | 434193 | 535100 | 0 | 535100 | 24832866 | 11912238 | 12920628 | 9965308 | 8918958 | 1046350 | 10298170 | 8918958 | 1379212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 9654704 | 0 | 9654704 | 10421167 | 0 | 10421167 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 74348921 | 9943958 | 64404963 | 91187929 | 9943958 | 81243971 | 135300777 | 34665587 | 100635190 | 74348921 | 9943958 | 64404963 | 91187929 | 9943958 | 81243971 | 0 | 0 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | CCI | 2012 | Q4 | Q4 - 2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93228004 | 18066349 | 75161655 | 56912354 | 1025000 | 55887354 | 58212354 | 1025000 | 57187354 | 252000 | 0 | 252000 | 644980 | 0 | 644980 | 844980 | 0 | 844980 | 24832866 | 11912238 | 12920628 | 9965308 | 8918958 | 1046350 | 9965308 | 8918958 | 1046350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 9654704 | 0 | 9654704 | 9654704 | 0 | 9654704 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 77177346 | 9943958 | 67233388 | 78677346 | 9943958 | 68733388 | 135300777 | 34665587 | 100635190 | 77177346 | 9943958 | 67233388 | 78677346 | 9943958 | 68733388 | 0 | 0 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | CCI | 2013 | Q1 | Q1 - 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 12858509 | 0 | 12858509 | 93228004 | 18066349 | 75161655 | 57282940 | 1025000 | 56257940 | 55793021 | 0 | 55793021 | 252000 | 0 | 252000 | 886335 | 0 | 886335 | 8370304 | 0 | 8370304 | 24832866 | 11912238 | 12920628 | 9365308 | 8318958 | 1046350 | 34326473 | 31937974 | 2388499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16755059 | 4687000 | 12068059 | 9654704 | 0 | 9654704 | 14949507 | 600000 | 14349507 | 232848 | 0 | 232848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 77189287 | 9343958 | 67845329 | 126297814 | 32537974 | 93759840 | 135300777 | 34665587 | 100635190 | 77189287 | 9343958 | 67845329 | 126297814 | 32537974 | 93759840 | 0 | 0 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | CCI | 2013 | Q2 | Q2 - 2013 | 18646122 | 0 | 18646122 | 14451717 | 0 | 14451717 | 14453232 | 0 | 14453232 | 53279568 | 0 | 53279568 | 50624658 | 0 | 50624658 | 53484389 | 0 | 53484389 | 9230560 | 0 | 9230560 | 7987805 | 0 | 7987805 | 8365172 | 0 | 8365172 | 36811327 | 33615587 | 3195740 | 34123919 | 31596583 | 2527336 | 36143333 | 33615587 | 2527746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17333200 | 1050000 | 16283200 | 14652436 | 1050000 | 13602436 | 15157842 | 1050000 | 14107842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 121840535 | 32646583 | 89193952 | 127603968 | 34665587 | 92938381 | 135300777 | 34665587 | 100635190 | 121840535 | 32646583 | 89193952 | 127603968 | 34665587 | 92938381 | 0 | 0 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | CCI | 2013 | Q3 | Q3 - 2013 | 18646122 | 0 | 18646122 | 14453232 | 0 | 14453232 | 14895320 | 0 | 14895320 | 53279568 | 0 | 53279568 | 53481489 | 0 | 53481489 | 54715142 | 0 | 54715142 | 9230560 | 0 | 9230560 | 8382290 | 0 | 8382290 | 8606368 | 0 | 8606368 | 36811327 | 33615587 | 3195740 | 36143333 | 33615587 | 2527746 | 36143333 | 33615587 | 2527746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17333200 | 1050000 | 16283200 | 15138417 | 1050000 | 14088417 | 16173559 | 1050000 | 15123559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 127598761 | 34665587 | 92933174 | 130533722 | 34665587 | 95868135 | 135300777 | 34665587 | 100635190 | 127598761 | 34665587 | 92933174 | 130533722 | 34665587 | 95868135 | 0 | 0 | Eagle-Net Alliance | TRUE
NT11BIX5570001 | CCI | 2013 | Q4 | Q4 - 2013 | 18646122 | 0 | 18646122 | 14771083 | 0 | 14771083 | 14929635 | 0 | 14929635 | 53279568 | 0 | 53279568 | 54189469 | 0 | 54189469 | 54668941 | 0 | 54668941 | 9230560 | 0 | 9230560 | 8601886 | 0 | 8601886 | 8751886 | 0 | 8751886 | 36811327 | 33615587 | 3195740 | 36150255 | 33615587 | 2534668 | 36160255 | 33615587 | 2544668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17333200 | 1050000 | 16283200 | 16051430 | 1050000 | 15001430 | 16358582 | 1050000 | 15308582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135300777 | 34665587 | 100635190 | 129764123 | 34665587 | 95098536 | 130869299 | 34665587 | 96203712 | 135300777 | 34665587 | 100635190 | 129764123 | 34665587 | 95098536 | 130869299 | 34665587 | 96203712 | 0 | 0 | Eagle-Net Alliance | TRUE
NT12BIX5570001 | CCI | 2012 | Q1 | Q1 - 2012 | 1113000 | 222600 | 890400 | 1042468 | 208494 | 833974 | 1113000 | 222600 | 890400 | 25677347 | 8655469 | 17021878 | 8285937 | 1657187 | 6628751 | 17391410 | 6998282 | 10393127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291273 | 58255 | 233018 | 10080 | 2016 | 8064 | 281193 | 56239 | 224954 | 898478 | 179696 | 718782 | 790226 | 158045 | 632181 | 108252 | 21651 | 86601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294228 | 58846 | 235382 | 48232 | 9646 | 38586 | 245996 | 49200 | 196796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28274326 | 9174866 | 19099460 | 10176943 | 2035388 | 8141556 | 19139851 | 7347972 | 11791878 | 28274326 | 9174866 | 19099460 | 10176943 | 2035388 | 8141556 | 19139851 | 7347972 | 11791878 | 0 | 0 | Zayo Group, LLC | TRUE
NT12BIX5570001 | CCI | 2012 | Q2 | Q2 - 2012 | 1113000 | 222600 | 890400 | 1065027 | 213005 | 852022 | 1113000 | 222600 | 890400 | 25677347 | 8655469 | 17021878 | 12664058 | 2532812 | 10131246 | 17391410 | 6998282 | 10393127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291273 | 58255 | 233018 | 210288 | 42057 | 168231 | 281193 | 56239 | 224954 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294228 | 58846 | 235382 | 85843 | 17169 | 68674 | 245996 | 49200 | 196796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28274326 | 9174866 | 19099460 | 14923694 | 2984739 | 11938955 | 19930077 | 7506017 | 12424059 | 28274326 | 9174866 | 19099460 | 14923694 | 2984739 | 11938955 | 19930077 | 7506017 | 12424059 | 0 | 0 | Zayo Group, LLC | TRUE
NT12BIX5570001 | CCI | 2012 | Q3 | Q3 - 2012 | 1113000 | 222600 | 890400 | 1068427 | 213685 | 854742 | 1113000 | 222600 | 890400 | 25667347 | 8655469 | 17021878 | 15085438 | 3017088 | 12068350 | 25667347 | 8655469 | 17021878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291273 | 58255 | 233018 | 641684 | 128336 | 513348 | 641684 | 128336 | 513348 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294228 | 58846 | 235382 | 158535 | 31707 | 126828 | 294228 | 58846 | 235382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28264326 | 9174866 | 19099460 | 17852562 | 3570512 | 14282050 | 28614737 | 9244947 | 19379790 | 28264326 | 9174866 | 19099460 | 17852562 | 3570512 | 14282050 | 28614737 | 9244947 | 19379790 | 0 | 0 | Zayo Group, LLC | TRUE
NT12BIX5570001 | CCI | 2012 | Q4 | Q4 - 2012 | 1113000 | 222600 | 890400 | 1068427 | 213685 | 854742 | 1113000 | 222600 | 890400 | 25677347 | 8655469 | 17021878 | 16449918 | 3289984 | 13159934 | 25123093 | 8544618 | 16578475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291273 | 58255 | 233018 | 845527 | 169106 | 676422 | 845527 | 169106 | 676421 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294228 | 58846 | 235382 | 201975 | 40395 | 161580 | 294228 | 58846 | 235382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28274326 | 9174866 | 19099460 | 19464325 | 3892866 | 15571460 | 28274326 | 9174866 | 19099460 | 28274326 | 9174866 | 19099460 | 19464325 | 3892866 | 15571460 | 28274326 | 9174866 | 19099460 | 0 | 0 | Zayo Group, LLC | TRUE
NT12BIX5570001 | CCI | 2013 | Q1 | Q1 - 2013 | 1113000 | 222600 | 890400 | 1068427 | 213685 | 854742 | 1113000 | 222600 | 890400 | 24677347 | 8455469 | 16221878 | 17375089 | 3475018 | 13900071 | 21191793 | 7758359 | 13433434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1291273 | 258255 | 1033018 | 1116859 | 223372 | 893487 | 1291273 | 258255 | 1033018 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 898478 | 179696 | 718782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294228 | 58846 | 235382 | 216625 | 43325 | 173300 | 294228 | 58846 | 235382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28274326 | 9174866 | 19099460 | 20675478 | 4135096 | 16540382 | 24788772 | 8477756 | 16311016 | 28274326 | 9174866 | 19099460 | 20675478 | 4135096 | 16540382 | 24788772 | 8477756 | 16311016 | 0 | 0 | Zayo Group, LLC | TRUE
NT12BIX5570002 | CCI | 2012 | Q1 | Q1 - 2012 | 2647380 | 794214 | 1853166 | 179991 | 53997 | 125994 | 2467389 | 740217 | 1727172 | 15004615 | 4501385 | 10503230 | 4652353 | 1395706 | 3256647 | 10352262 | 3105679 | 7246583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 350669 | 105201 | 245468 | 253110 | 75933 | 177177 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18278375 | 5483513 | 12794862 | 5205614 | 1561684 | 3643930 | 13072761 | 3921829 | 9150932 | 18278375 | 5483513 | 12794862 | 5205614 | 1561684 | 3643930 | 13072761 | 3921829 | 9150932 | 0 | 0 | Zayo Group, LLC | TRUE
NT12BIX5570002 | CCI | 2012 | Q2 | Q2 - 2012 | 2647380 | 794214 | 1853166 | 179991 | 53997 | 125994 | 2467389 | 740217 | 1727172 | 15004615 | 4501385 | 10503230 | 7009336 | 2102801 | 4906535 | 10352262 | 3105679 | 7246583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 474040 | 142212 | 331828 | 474040 | 142212 | 331828 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18278375 | 5483513 | 12794862 | 7685968 | 2305790 | 5380178 | 13316292 | 3994888 | 9321404 | 18278375 | 5483513 | 12794862 | 7685968 | 2305790 | 5380178 | 13316292 | 3994888 | 9321404 | 0 | 0 | Zayo Group, LLC | TRUE
NT12BIX5570002 | CCI | 2012 | Q3 | Q3 - 2012 | 2647380 | 794214 | 1853166 | 185353 | 55606 | 129747 | 2647380 | 794214 | 1853166 | 15004615 | 4501385 | 10503230 | 8753680 | 2626104 | 6127576 | 15004615 | 4501385 | 10503230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 568527 | 170558 | 397969 | 603779 | 181134 | 422645 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18278375 | 5483513 | 12794862 | 9530161 | 2859048 | 6671113 | 18278375 | 5483513 | 12794862 | 18278375 | 5483513 | 12794862 | 9530161 | 2859048 | 6671113 | 18278375 | 5483513 | 12794862 | 0 | 0 | Zayo Group, LLC | TRUE
NT12BIX5570002 | CCI | 2012 | Q4 | Q4 - 2012 | 2647380 | 794214 | 1853166 | 192284 | 57685 | 134599 | 2647380 | 794214 | 1853166 | 15004615 | 4501385 | 10503230 | 10609055 | 3182717 | 7426338 | 14954989 | 4486498 | 10468491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 653405 | 196021 | 457384 | 653405 | 196021 | 457384 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18278375 | 5483513 | 12794862 | 11477345 | 3443203 | 8034142 | 18278375 | 5483513 | 12794862 | 18278375 | 5483513 | 12794862 | 11477345 | 3443203 | 8034142 | 18278375 | 5483513 | 12794862 | 0 | 0 | Zayo Group, LLC | TRUE
NT12BIX5570002 | CCI | 2013 | Q1 | Q1 - 2013 | 2647380 | 794214 | 1853166 | 233685 | 70105 | 163579 | 2647380 | 794214 | 1853166 | 15004615 | 4501385 | 10503230 | 10798742 | 3239622 | 7559119 | 13851615 | 4155484 | 9696131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603779 | 181134 | 422645 | 755956 | 226787 | 529169 | 755956 | 226787 | 529169 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 22601 | 6780 | 15821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18278375 | 5483513 | 12794862 | 11810984 | 3543294 | 8267688 | 17277552 | 5183265 | 12094287 | 18278375 | 5483513 | 12794862 | 11810984 | 3543294 | 8267688 | 17277552 | 5183265 | 12094287 | 0 | 0 | Zayo Group, LLC | TRUE
NT12BIX5570002 | CCI | 2013 | Q2 | Q2 - 2013 | 2647380 | 794214 | 1853166 | 354562 | 106369 | 248193 | 354562 | 106369 | 248193 | 15004615 | 4501385 | 10503230 | 14750659 | 4425198 | 10325461 | 14750659 | 4425198 | 10325461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626380 | 187914 | 438466 | 977778 | 293333 | 684445 | 977778 | 293333 | 684445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18278375 | 5483513 | 12794862 | 16082999 | 4824900 | 11258099 | 16082999 | 4824900 | 11258099 | 18278375 | 5483513 | 12794862 | 16082999 | 4824900 | 11258099 | 16082999 | 4824900 | 11258099 | 0 | 0 | Zayo Group, LLC | TRUE

## CCI_Annual_KeyIndicators_Actual
Award_Num | Year | MMile_AvgCost | MMile_AvgCost_Desc | LMileHous_AvgCost | LMileHous_AvgCost_Desc | LMileSubsc_AvgCost | LMileSubsc_AvgCost_Desc | MMile_MaxSpeed | MMile_MaxSpeed_Desc | LMile_MaxSpeed | LMile_MaxSpeed_Desc | MMile_AvgSpeed | MMile_AvgSpeed_Desc | LMile_AvgSpeed | LMile_AvgSpeed_Desc | SpeedIncrease_Desc | RetService_Desc | NetManagemnt_Desc | DiscontReason_Desc | TotalStrand_Num | AvgActStrand_Num | AvgLeaseStrand_Num | AvgDarkStrand_Num | BuildActStrand_Num | BuildLeaseStrand_Num | BuildDarkStrand_Num | WSaleCustList_Desc | SqFeet_Total_Num | SqFeet_Use_Num | SqFeet_Lease_Num | SqFeet_Availbl_Num | NetConnect_Desc | SubcontrConcern_Desc | BestPractice_Desc | Recipient | School_Total_Num | Library_Total_Num | CCollege_Total_Num | Universt_Total_Num | Healthcr_Total_Num | PublSafety_Total_Num | OtherGov_Total_Num | OtherGov_Improv_Num | OtherNonGov_Total_Num | PublHousng_Total_Num | TotalComInst_Num | InterAgreement_Name | PeerAgreemnt_Name | April 11, 2014 Cutoff Date
NT10BIX5570003 | 2010 | 28,285 | This number is slightly higher than our Baseline projection based on the limited construction completed for the project. As miles are added we anticipate this number to fall in line with our projections. | N/A | N/A | N/A | N/A | N/A | We currently do not advertise our enhanced broadband speeds associated with the project. Part of our marketing strategy in the coming year will be to incorporate the new speeds with our overall network promotion. | N/A | N/A | 47.5 Meg | With only two Anchor Institutions connected at this time, this number is skewed higher than normal due to one subscriber requesting an atypical speed. | N/A | N/A | Since SDN was not the provider of service to these institutions prior to this award, we are not able to provide the data requested. | N/A | (a.) Network management policies are currently being developed as part of the overall project design and implementation as we roll out the enhanced broadband infrastructure to our customers. (b.) No, we have not blocked or limited consumers to our network. | N/A | 12576 | 432 | 0 | 3024 | 1140 | 0 | 7980 | N/A | 0 | 0 | 0 | 0 | Interconnection can be accomplished at any meetpoint where SDN connects to other carriers throughout the network. Interconnection can be requested by contacting our sales staff at SDN Communications, 2910 West 10th Street, Sioux Falls, South Dakota 57104 or by visiting our website at: www.sdncommunications.com. | N/A | Maintain regularly scheduled contact with the Federal Program Officer and make sure they are aware of everything you are doing. | South Dakota Network, LLC | 247 | 4 | 0 | 24 | 66 | 30 |  | 139 | 2 | 0 | 512 | N/A None No | N/A | TRUE
NT10BIX5570003 | 2011 | 23,644 | Original Baseline projections were projected to be at $22,000 for the project. The average cost per mile using the Middle Cost to Build divided by the miles. This calculation is consistent with Baseline calculations. | N/A | N/A | N/A | N/A | N/A | We currently do not advertise our enhanced broadband speeds associated with the project. Part of our marketing strategy in the coming year will be to incorporate the new speeds with our overall network promotion. | N/A | N/A | 28 Mbps | This metric was calculated using the new facilities added during the 2011 year. | N/A | N/A | 44 Mbps increase as it was calculated using total bandwidth ordered minus previous, divided by total site count. | N/A | a.) Network Management Policies are in place and posted on the SDN Website, sdncommunications.com. b.) No | N/A | 16992 | 4410 | 0 | 11658 | 308 | 0 | 616 | N/A | 0 | 0 | 0 | 0 | Points of Presence (PoP's) are available and identified on the attached addendum. | N/A | N/A | South Dakota Network, LLC | 247 | 4 | 0 | 24 | 66 | 30 |  | 139 | 2 | 0 | 512 | 1). None 2). None 3). No | N/A | TRUE
NT10BIX5570003 | 2012 | $23,644 | Original Baseline projections were projected to be at $22,000 for the project. The average cost per mile using the Middle Cost to Build divided by the miles. This calculation is consistent with Baseline calculations. This metric was consistent with 2011 as the Middle Mile component was completed during that year. | N/A | N/A | N/A | N/A | N/A | We currently do not advertise our enhanced broadband speeds associated with the project. Part of our marketing strategy in the coming year will be to incorporate the new speeds with our overall network promotion. | N/A | N/A | 44Mbps. | This metric was calculated using the new facilities added during the 2012 year. | N/A | N/A | 44 Mbps increase as it was calculated using total bandwidth ordered minus previous, divided by total site count. | N/A | a.) Network Management Policies are in place and posted on the SDN Website, sdncommunications.com. b.) No | N/A | 17440 | 5096 | 0 | 12344 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Points of Presence (PoP's) are available and identified on the attached addendum. | N/A | N/A | South Dakota Network, LLC | 247 | 4 | 0 | 24 | 66 | 30 |  | 139 | 2 | 0 | 512 | 1.) None 2.) None 3.) No | N/A | TRUE
NT10BIX5570004 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Physical locations for collocation points have been determined, however the collocation facilities and specifications have not been finalized due to waiting on Environmental Assessment approval. | N/A | Environmental Assessments regulations and requirements vary with different agencies. We recommend that other BTOP projects fully research what is required prior to contracting with an Environmental firm. | North Georgia Network Cooperative, Inc. | 18 | 6 | 0 | 5 | 28 | 17 |  | 18 | 2 | 0 | 94 | N/A | N/A | TRUE
NT10BIX5570004 | 2011 | 13,690.00 | Southern Route construction is not yet complete. This cost for this build will be higher than the average cost shown. | N/A | As of 12/31/2011, no last mile connections have been made. | N/A | As of 12/31/2011, no last mile connections have been made. | 10 Gb | Meets Baseline | 100 Mb | Meets Baseline | 10 Gb | Meets Baseline | 15 Mb | Based on pre-market take rates the average speed will be 15Mb | N/A | N/A | N/A | N/A | 28190 | 0 | 0 | 24313 | 758 | 0 | 3119 | N/A | 0 | 0 | 0 | 0 | CPOP and SPOP construction will be completed in January of 2012 at that point collocation facilities will be offered. | N/A | N/A | North Georgia Network Cooperative, Inc. | 18 | 6 | 0 | 5 | 28 | 17 |  | 18 | 2 | 0 | 94 | N/A | N/A | TRUE
NT10BIX5570004 | 2012 | 16,856 | Meets Baseline | 662 | Meets Baseline | 7,918 | Meets Baseline | 10 Gb | Meets Baseline | 100 Mb | Meets Baseline | 10 Gb | Meets Baseline | 15 Mb | Based on market take rates the average speed will be 15-20Mb | NGN has compared information from CAIs. The average before the BTOP project was 3 Mb with no ability for expansion. Currently, our average current CAIs package is around 15 Mb. The BTOP program has given the CAIs the ability to increase this bandwidth to 1000Mb (1Gb) if interested. | Broadband Services. We deliver internet bits to premises. | Currently all of our data traffic is internet bits that do not require quality of service. We do not filter internet content or services. We currently sell internet packages. These packages define bandwidth rates controlled at the endpoint. | N/A | 54584 | 23499 | 896 | 30189 | 0 | 0 | 0 | N/A | 864 | 576 | 0 | 288 | CPOP and SPOP facilities can be offered as collocation facilities. | N/A | N/A | North Georgia Network Cooperative, Inc. | 18 | 6 | 0 | 5 | 28 | 17 |  | 18 | 2 | 0 | 94 | N/A | N/A | TRUE
NT10BIX5570009 | 2010 | 0 | None Noted | 0 | N/A | 0 | N/A | 10 Gbps | None Noted | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | a) CAI's can request their bandwidth limited but by default Merit does not limit the users access. b) Merit has not block access to any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | N/A | 73630 | 0 | 0 | 1080 | 17897 | 5221 | 49432 | N/A | 0 | 0 | 0 | 0 | Merit does not own collocation space for this build. Other network providers and CAI's can interconnect to Merit at splice points along the route. | N/A | Merit encourages all BTOP recipients to reach out to communities at all levels and get them involved in the process. Build relationships with all the permitting agencies; we would suggest informal meetings with them on a regular basis. Merit would encourage that inquiries with communities on existing infrastructure as well as talking with others in your industry about existing infrastructure given that the cost is about the same or less and the time savings will get you ahead of your project. | Merit Network Inc. | 67 | 68 | 16 | 35 | 58 | 45 |  | 87 | 57 | 0 | 433 | N/A | N/A | TRUE
NT10BIX5570009 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10 Gbps | No variance. | 0 | N/A | 0 | N/A | 0 | N/A | Broadband speeds have not increased since construction and deployment have not been completed. | Pricing plans have not been provided, since construction and deployment have not been completed. | Our project is not yet providing service. | N/A | 72821 | 0 | 0 | 6552 | 17715 | 5221 | 43333 | N/A | 0 | 0 | 0 | 0 | Other network providers and customers will have opportunities to connect to the recipient and subrecipient networks at leased facilities along the route, including, but not limited to: telecommunication huts; Central Offices; Community Anchor Institutions; and other leased facilities. No part of the project network was lit and operational during the reporting period; the locations, owners, and interconnection method data will be available in the 2012 reporting year. | N/A | Project success depends on collaboration and communication with the NTIA and the Grants Office via the Project's Federal Program Officer, Grants Officer, and their consulting teams. It is important to become intimately familiar with the Grant terms and conditions, and implement financial and administrative systems that allow for the monitoring of grant activities and documentation of the use of funds. Starting processes early makes a huge difference in the project time line. Initiating procurement processes, completing the Environmental Assessment, requesting Davis-Bacon Act wage rates for your project area, and having agreements in place with subrecipients and vendors, and working with permitting agencies as early as possible maximizes construction time. Planning is an essential component of a successful project, and BTOP recipients should have clearly defined baseline project plans, communication plans for subrecipients, contractors, vendors, and the community, plans for collecting progress data, risk mitigation and contingency plans, and plans for monitoring subrecipients. Community outreach helps get communities involved in the project, creates an open dialogue, and demonstrates that our organization and the NTIA are using Federal funds responsibly. Helping key stakeholders and organizations see the positive socioeconomic impact that broadband has will result in higher adoption rates and stronger, more vibrant communities. | Merit Network Inc. | 67 | 68 | 16 | 35 | 58 | 45 |  | 87 | 57 | 0 | 433 | 1. N/A 2. N/A 3. N/A (No requests for interconnection were made.) | 1. N/A 2. N/A 3. N/A (No requests for peering or transit were made.) | TRUE
NT10BIX5570009 | 2012 | 33461 | No significant variance. | 0 | N/A | 0 | N/A | 10 Gbps | No variance. | 0 | N/A | 10 Mbps | No variance. | 0 | N/A | The average increase is 10 Gbps. This was calculated by taking the average of the average speed connections to the communicaty anchor institutions receiving new or improved service. | Merit provides a managed fiber attachment service. Members pay a single annual fee based on the service level to which they subscribe. The fee comprises a local loop provisioned on fiber infrastructure and bandwidth from the backbone to the Member. | Merit Network employs standard best effort Internet delivery policy to ensure that any organization, institution or entity connected, directly or indirectly, to Merit's fiber backbone may exercise choice in lawful Internet content, web-based application and use of Merit or competitor service, including any device which is not harmful to the network. All of the preceding is subject to the needs of law enforcement. Merit Network does not favor any lawful Internet applications or content over others, and is committed to enabling competition among network providers, application and service providers, and content providers. | N/A | 81789 | 3863 | 74686 | 0 | 180 | 0 | 3060 | N/A | 0 | 0 | 0 | 0 | Other network providers and customers have opportunities to connect to the recipient and subrecipient networks along the route at telecommunications huts, central offices, community anchor institutions, and other facilities. | N/A | Project success depends on collaboration and communication with the NTIA and the Grants Office via the Project's Federal Program Officer, Grants Officer, and their consulting teams. It is important to become intimately familiar with the Grant terms and conditions, and implement financial and administrative systems that allow for the monitoring of grant activities and documentation of the use of funds. Starting processes early makes a huge difference in the project time line. Initiating procurement processes, completing the Environmental Assessment, requesting Davis-Bacon Act wage rates for your project area, and having agreements in place with subrecipients and vendors, and working with permitting agencies as early as possible maximizes construction time. Planning is an essential component of a successful project, and BTOP recipients should have clearly defined baseline project plans, communication plans for subrecipients, contractors, vendors, and the community, plans for collecting progress data, risk mitigation and contingency plans, and plans for monitoring subrecipients. Community outreach helps get communities involved in the project, creates an open dialogue, and demonstrates that our organization and the NTIA are using Federal funds responsibly. Helping key stakeholders and organizations see the positive socioeconomic impact that broadband has will result in higher adoption rates and stronger, more vibrant communities. | Merit Network Inc. | 67 | 68 | 16 | 35 | 58 | 45 |  | 87 | 57 | 0 | 433 | N/A | N/A | TRUE
NT10BIX5570009 | 2013 | 34734 | The variance, 2%, is not significant, but could be attributed to unanticipated expenses associated with the Environmental Assessment and higher than expected permitting costs. | 0 | N/A | 0 | N/A | 10 Gbps | No variance. | 0 | N/A | 10 Mbps | No variance. | 0 | N/A | The average increase is 10 Gbps. This was calculated by taking the average of the average speed connections to the communicaty anchor institutions receiving new or improved service. | Merit provides a managed fiber attachment service. Members pay a single annual fee based on the service level to which they subscribe. The fee comprises a local loop provisioned on fiber infrastructure and bandwidth from the backbone to the Member. | Merit Network employs standard best effort Internet delivery policy to ensure that any organization, institution or entity connected, directly or indirectly, to Merit's fiber backbone may exercise choice in lawful Internet content, web-based application and use of Merit or competitor service, including any device which is not harmful to the network. All of the preceding is subject to the needs of law enforcement. Merit Network does not favor any lawful Internet applications or content over others, and is committed to enabling competition among network providers, application and service providers, and content providers. | N/A | 81789 | 4043 | 74686 | 3060 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Other network providers and customers have opportunities to connect to the recipient and subrecipient networks along the route at telecommunications huts, central offices, community anchor institutions, and other facilities. | N/A | Project success depends on collaboration and communication with the NTIA and the Grants Office via the Project's Federal Program Officer, Grants Officer, and their consulting teams. It is important to become intimately familiar with the Grant terms and conditions, and implement financial and administrative systems that allow for the monitoring of grant activities and documentation of the use of funds. Starting processes early makes a huge difference in the project time line. Initiating procurement processes, completing the Environmental Assessment, requesting Davis-Bacon Act wage rates for your project area, and having agreements in place with subrecipients and vendors, and working with permitting agencies as early as possible maximizes construction time. Planning is an essential component of a successful project, and BTOP recipients should have clearly defined baseline project plans, communication plans for subrecipients, contractors, vendors, and the community, plans for collecting progress data, risk mitigation and contingency plans, and plans for monitoring subrecipients. Community outreach helps get communities involved in the project, creates an open dialogue, and demonstrates that our organization and the NTIA are using Federal funds responsibly. Helping key stakeholders and organizations see the positive socioeconomic impact that broadband has will result in higher adoption rates and stronger, more vibrant communities. | Merit Network Inc. | 67 | 68 | 16 | 35 | 58 | 45 |  | 87 | 57 | 0 | 433 | There were no interconnection agreements entered into during the annual reporting period, however one agreement was under negotiation. No requests were denied. | N/A | TRUE
NT10BIX5570011 | 2010 | $0 | No fiber yet deployed, although at end of quarter conduit placement had occurred. | N/A | N/A to our project. | N/A | N/A to our project. | N/A | No fiber yet deployed. | N/A | N/A to our project. | N/A | No fiber yet deployed | N/A | N/A to our project. | No CAI's were explicitly called out for direct service as a part of this project. As of 12/31/2010, no network components had been deployed as part of this project. | N/A | MCNC has Internet/Data Acceptable Use, Nondiscrimination, Interconnection, and Network Management Policies (see https://www.mcnc.org/about/policies.html for further details). MCNC does not impose any bandwidth limitations or access limitations to lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to it's existing infrastructure or on proposed BTOP infrastructure. | N/A | 46274 | 0 | 0 | 2642 | 0 | 0 | 43632 | N/A | 0 | 0 | 0 | 0 | Although we have not yet deployed, access to other network providers will be allowed at all hand holds deployed within the network and all carrier neutral facilities we end up colocating in. . | While our next tier contractors are not SDB, each are including a SDB component via their subcontractors. | Get your RFP's out as quickly as you can. With folks desperate for work and orders, you might end up with more favorable pricing. Continue to work with incumbents in your area as new opportunities for partnerships arise. Realize that every day will present a new challenge and opportunity, but to keep the big picture in focus. | MCNC | 1799 | 0 | 16 | 27 | 6 | 5 |  | 8 | 5 | 0 | 1866 | MCNC has a Definitive Agreement with FRC which provides for IRUs (exclusive, unrestricted and indefeasible right to use the fibers associated with the IRUs) - such IRU grant does not convey any legal title to any real or personal property, including the fibers, the cable or the network; however, the Grantee shall have the exclusive, unrestricted and indefeasible right to use the fibers associated with the IRU for any lawful purpose during the term applicable to such IRU. -FRC will be getting IRUs in New MCNC Fiber Segments -MCNC will be getting IRUs in Existing FRC Fiber Segments For ERC we have a Fiber Optics Exchange Agreement The agreement defines IRU as an indefeasible right to use a designated number of fiber strands within the other party's cable -ERC will be getting an exclusive and unrestricted IRU from MCNC -MCNC will be getting an exclusive and unrestricted IRU from ERC | N/A | TRUE
NT10BIX5570011 | 2011 | 61,704.50 | New miles built and fully deployed stand at 105. Total cost of engineering, construction, and relevant permits to light those segments that are in service is $6,478,973. We are less than what was forecasted in our baseline due to lower than expected construction costs. As we deploy more miles in the areas that were cheaper, this number will continue to drop. While we had forecasted more miles to be completed at this point, they are not yet operated (i.e. equipment deployed). Even were they deployed, the cost per mile would be lower as our expenses have turned out to be lower on those segments as well. | 0 | N/A to our project | 0 | N/A to our project | 10Gbps | 10Gbps is the maximum current speed realized on our network, however the equipment deployed has the ability to scale to 100G as user needs would dictate. | 0 | N/A to our project | 1.9Gbps | Four 10Gbps services have been provisioned on the MCNC portions of the network, and 17 50Mbps services have been provisioned on the FRC portions of the network. | 0 | N/A to our project | All of the community anchor institutions identified above received improved access to the NCREN backbone. They all currently have access to the North Carolina Research and Education network through third party providers. This access is enabled through regional points of presence that before the BTOP awarded infrastructure operated at a maximum sustained speed of 1Gbps. After the implementation of the BTOP network, all the POP's operated at a minimum of 10Gbps. Their ability to access internet based resources prior was limited to the capacity of this 1Gbps backbone, which was oversubscribed. | FRC has used 2 fiber pairs (4 fiber strands) in Asheville, NC to provide ethernet based services to Verizon Wireless at approximately 17 cell tower locations. FRC charges Verizon Wireless approximately $1,400 per month at each tower location. | The North Carolina Research and Education Network by policy does not limit/restrict access to the network. There is no prioritization of traffic placed on the backbone for IP based services. Lambda based circuits encompass their own payload, so by nature that traffic is prioritized within the circuit design. The only filtering policies on the IP backbone that are utilized relate to anti-spoofing related filters to protect our customers, and the IP based resources of the infrastructure itself. If a site is the target of or initiating a Denial of Service attack, from time to time network access will be limited to resolve those issues. We do have a service that our K-12 community users can procure related to content filtering to satisfy CIPA (Children Internet Protection Act) requirements. | N/A as no subscribers have dropped the service. | 46562 | 998 | 246 | 39942 | 616 | 0 | 4760 | We have signed agreements with ERC for use of 6 fibers over 40 miles of the infrastructure and with Haywood County Government for use of 6 fibers over 1 mile of the infrastructure yielding the 246 miles referenced above. | 0 | 0 | 0 | 0 | North Carolina Research and Education (NCREN) POP's for this project are facilitated out of existing space with providers that MCNC leases space from or at CAI facilities in the regions the network goes through, generally university or county government facilities. These facilities allow for other carriers/customers to interconnect to us at those locations. In addition, we also had the route designed and built to allow for interconnection at all hand holes that exist along the route and have the ability to have fiber splicing occur. | MCNC's efforts for socially and economically disadvantaged small (SDB) business involvement has resulted in MCNC's contractors subcontracting with seven SDB concerns: Indepth Utility Resources, LLC - WBE applied for T&B Drilling & Electric, LLC - MBE North Star International Group - MBE Coastline Cable Construction - WBE applied for Blackshear Corporation - MBE DKL & Associates - WBE Keller Environmental - WBE | Work through your permitting process as quickly as possible. Issues will undoubtedly surface that will take additional time. Do not allow your contractors that you award work to only focus on the easy elements of construction first without also addressing some of the difficult elements. We had a situation where they did all the easy stuff, let the remainder, and our prime contractor has had difficulty finding someone to complete the segment they were awarded. Award RFP's early. Implement stringent contracts for material delivery and construction delivery. Expect your legal bills to be more than you anticipated. Celebrate your successes and always look at the big picture. | MCNC | 1799 | 0 | 16 | 27 | 6 | 5 |  | 8 | 5 | 0 | 1866 | We have finalized two agreements with FRC and ERC related to fibers built with BTOP awards. These were agreements that were outlined in our project application and represent new access for both in these regions. No request for interconnection has been denied to any interested provider. | There have been no peering and/or transit related agreements negotiated as part of the new infrastructure. | TRUE
NT10BIX5570011 | 2012 | 64,615.28 | New miles built and deployed is 444. Total cost of engineering, construction, and relevant permits for this fiber is $28,689,184. We are less than what was forecasted in our baseline due to lower than expected construction costs. | 0 | N/A to our project | 0 | N/A to our project | 10Gbps | 10Gbps is the maximum current speed realized on our network for CAI connections, however the equipment deployed has the ability to scale to 100G as user needs would dictate. In addition we have deployed 100G core upgrades for the North Carolina Research and Education (NCREN) backbone as approved by NTIA this past year. | 0 | N/A to our project | 4.2Gbps | 12 10Gbps services have been provisioned on the MCNC portions of the network, and 17 50Mbps services have been provisioned on the FRC portions of the network. | 0 | N/A to our project | 1847 of the community anchor institutions identified above received improved access to the NCREN backbone. They all currently have access to the North Carolina Research and Education network through third party providers. This access is enabled through regional points of presence that before the BTOP awarded infrastructure operated at a maximum sustained speed of 1Gbps. After the implementation of the BTOP network, all the POP's operated at 10Gbps. Their ability to access internet based resources prior was limited to the capacity of this 1Gbps backbone, which was oversubscribed. 19 CAI's have now had direct fiber built to them as a result of the project with minimum connectivity of 1Gbps scalable to 100Gbps in the future now that fiber as been deployed. | FRC is providing point to point services for cell towers in the western portion of the network for Verizon wireless. They have not yet had demand for other wholesale lit services related to these areas. Their marketing strategy enables them to provide services from 50M-10Gbps as required by customers. Each opportunity has to be priced on a case by case basis to offset additional capital costs (additional lateral builds and equipment) that were not funded by the BTOP program specifically. For the existing services they're providing to Verizon wireless, they are charging $1400/mo for 50M backhaul services from their towers to other locations off the BTOP route. MCNC is not providing wholesale services to carriers per our mission. We are providing transport, lambda, and internet services on the network for CAI's in these regions. | The North Carolina Research and Education Network by policy does not limit/restrict access to the network. There is no prioritization of traffic placed on the backbone for IP based services. Lambda based circuits encompass their own payload, so by nature that traffic is prioritized within the circuit design. The only filtering policies on the IP backbone that are utilized relate to anti-spoofing related filters to protect our customers, and the IP based resources of the infrastructure itself. If a site is the target of or initiating a Denial of Service attack, from time to time network access will be limited to resolve those issues. We do have a content based filtering service that our K-12 community can subscribe to to meet CIPA (Children's Internet Protection Act) requirements that the districts may have, as well as firewall based service. MCNC does not limit access to any lawful content. | N/A - as no subscribers have dropped the service. | 49676 | 2564 | 366 | 46746 | 0 | 0 | 0 | We have signed agreements with ERC for use of 6 fibers over 40 miles of the infrastructure, Haywood County Government for use of 6 fibers over 1 mile of the infrastructure, Pangea for 6 fibers over 7.6 miles of the infrastructure, and Morris Broadband for 2 fibers over 37.2 miles of the infrastructure yielding the 366 miles referenced above. | 0 | 0 | 0 | 0 | North Carolina Research and Education (NCREN) POP's for this project are facilitated out of existing space with providers that MCNC leases space from or at CAI facilities in the regions the network goes through, generally university or county government facilities. These facilities allow for other carriers/customers to interconnect to us at those locations. In addition, hand holds along the route, placed at a minimum of 1 mile apart, allow for interconnect to other carriers or CAI's that would build fiber to those meet points. | MCNC's efforts for socially and economically disadvantaged small (SDB) business involvement has resulted in MCNC's contractors subcontracting with nine SDB concerns: Indepth Utility Resources, LLC - WBE T&B Drilling & Electric, LLC - MBE North Star International Group - MBE Coastline Cable Construction - WBE Blackshear Corporation - MBE DKL & Associates - WBE Keller Environmental - WBE Edwards Telecommunication, Inc VBE HK&L, LLC WBE applied for | Work through your permitting process as quickly as possible. Issues will undoubtedly surface that will take additional time. 1) Do not allow your contractors that you award work to only focus on the easy elements of construction first without also addressing some of the difficult elements. We had a situation where they did all the easy construction, left the remainder and our prime contractor had difficulty finding someone to complete the segment they were awarded. 2) Award RFP's early. 3) Implement stringent contracts for material delivery and construction delivery. 4) Expect your legal bills to be more than you anticipated. 5) Celebrate your successes and always look at the big picture. | MCNC | 1799 | 0 | 16 | 27 | 6 | 5 |  | 8 | 5 | 0 | 1866 | FRC finalized two agreements with Pangea and Morris Broadband related to fibers built with BTOP awards. MCNC executed agreements with FRC and ERC related to fibers in the project. There are an additional five agreements being considered and discussed that are various stages of completeness as of writing of this report. No request for interconnection has been denied to any interested provider. | There have been no peering and/or transit related agreements negotiated as part of the new infrastructure. | TRUE
NT10BIX5570011 | 2013 | 65,440.23 | New miles built and deployed is 444. Total cost of engineering, construction, and relevant permits for this fiber is $29,055,463. We are less than what was forecasted in our baseline due to lower than expected construction costs. | 0 | N/A to our project | 0 | N/A to our project | 100Gbps | 10Gbps is the maximum current speed realized on our network for CAI connections, however the equipment deployed has the ability to scale to 100G as user needs would dictate. In addition we have deployed 100G core upgrades for the North Carolina Research and Education (NCREN) backbone as approved by NTIA this past year. | 0 | N/A to our project | 5Gbps | This project focused on middle mile access and backbone services were the focus until directly connected CAI's were funded through savings. As a result of all work, thirty-six 10Gbps backbone services and 19 100M customer connections have been provisioned on the MCNC portions of the network and 17 100Mbps services have been provisioned on the FRC portions of the network. | 0 | N/A to our project | 1847 of the community anchor institutions identified above received improved access to the NCREN backbone. They all currently have access to the North Carolina Research and Education network through third party providers. This access is enabled through regional points of presence that before the BTOP awarded infrastructure operated at a maximum sustained speed of 1Gbps. After the implementation of the BTOP network, all the POP's operated at 10Gbps. Their ability to access internet based resources prior was limited to the capacity of this 1Gbps backbone, which was oversubscribed. 19 CAI's have now had direct fiber built to them as a result of the project with minimum connectivity of 100Mbps scalable to 100Gbps in the future now that fiber as been deployed. | FRC is providing point to point services for cell towers along the footprint of the network for Verizon wireless. They have not yet had demand for other wholesale lit services related to these areas. Their marketing strategy enables them to provide services from 50M-10Gbps as required by customers. Each opportunity has to be priced on a case by case basis to offset additional capital costs (additional lateral builds and equipment) that were not funded by the BTOP program specifically. For the existing services they're providing to Verizon wireless, they are charging $1400/mo for 50M backhaul services from their towers to other locations off the BTOP route. Earthlink has bought fibers along the footprint from MCNC and is providing lit services up to 100G to customers they serve. MCNC is not providing wholesale services to carriers per our mission. We are providing transport, lambda, and internet services on the network for CAI's in these regions. | The North Carolina Research and Education Network by policy does not limit/restrict access to the network. There is no prioritization of traffic placed on the backbone for IP based services. Lambda based circuits encompass their own payload, so by nature that traffic is prioritized within the circuit design. The only filtering policies on the IP backbone that are utilized relate to anti-spoofing related filters to protect our customers, and the IP based resources of the infrastructure itself. If a site is the target of or initiating a Denial of Service attack, from time to time network access will be limited to resolve those issues. We do have a content based filtering service that our K-12 community can subscribe to to meet CIPA (Children's Internet Protection Act) requirements that the districts may have, as well as firewall based service. MCNC does not limit access to any lawful content. | N/A - as no subscribers have dropped the service. | 49676 | 2610 | 5258 | 41808 | 0 | 0 | 0 | We have signed agreements with ERC for use of 6 fibers over 40 miles of the infrastructure, a separate agreement with ERC for the lease of 4 fibers over 31 miles of the infrastructure, Pangea for 6 fibers over 7.6 miles of the infrastructure, Morris Broadband for 2 fibers over 37.2 miles of the infrastructure, Earthlink for 2 fibers over 186 miles of the infrastructure, Broadplex for 1 fiber over 502 miles of the infrastructure, RST for 6 fibers over 472 miles of the infrastructure, and MOX networks for 12 fibers over 89 miles of the infrastructure yielding the 5258 miles referenced above. | 600 | 96 | 0 | 504 | North Carolina Research and Education (NCREN) POP's for this project are facilitated out of existing space with providers that MCNC leases space from or at CAI facilities in the regions the network goes through, generally university or county government facilities. These facilities allow for other carriers/customers to interconnect to us at those locations. In addition, hand holds along the route, placed at a minimum of 1 mile apart, allow for interconnect to other carriers or CAI's that would build fiber to those meet points. In addition we built three colocation facilities in this reporting period that were included as part of the project at the end of 2012 with a portion of the original project savings that yields the figures in the tables above. | MCNC's efforts for socially and economically disadvantaged small (SDB) business involvement has resulted in MCNC's contractors subcontracting with nine SDB concerns: Indepth Utility Resources, LLC - WBE T&B Drilling & Electric, LLC - MBE North Star International Group - MBE Coastline Cable Construction - WBE Blackshear Corporation - MBE DKL & Associates - WBE Keller Environmental - WBE Edwards Telecommunication, Inc VBE HK&L, LLC WBE applied for | Work through your permitting process as quickly as possible. Issues will undoubtedly surface that will take additional time. 1) Do not allow your contractors that you award work to only focus on the easy elements of construction first without also addressing some of the difficult elements. We had a situation where they did all the easy construction, left the remainder and our prime contractor had difficulty finding someone to complete the segment they were awarded. 2) Award RFP's early. 3) Implement stringent contracts for material delivery and construction delivery. 4) Expect your legal bills to be more than you anticipated. 5) Celebrate your successes and always look at the big picture. | MCNC | 1799 | 0 | 16 | 27 | 6 | 5 |  | 8 | 5 | 0 | 1866 | FRC has executed agreements with Pangea and Morris Broadband related to fibers built with BTOP awards. MCNC has executed agreements with FRC, Broadplex, RST Communications, Earthlink, MOX networks and ERC related to fibers in the project. There are an additional four agreements being considered and discussed that are at various stages of completeness as of writing of this report. No request for interconnection has been denied to any interested provider. | There have been no peering and/or transit related agreements negotiated as part of the new infrastructure. | TRUE
NT10BIX5570016 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | 10 MBPS - 100 MBPS - OPEN ACCESS | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | We provide an open-access network available to all members. We do not limit or block access of lawful content or applications for members. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We will provide 3 interconnection points on this project. These interconnection points are strategically placed to provide regeneration points, interconnection and access points and co-location points. | N/A | 1- Start the Environmental Assessment process as early as possible for long, linear projects. 2- Perform design work in advance to aid in preparation of EA and construction bidding. | Virginia Tech Foundation, Inc. | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 2 | N/A | N/A | TRUE
NT10BIX5570016 | 2011 | 17,778.74 | Average cost is less than Baseline due to both 1) lower-than-anticipated bid prices, and 2) being based on 82% complete (86 miles) | 0 | N/A | 0 | N/A | 10 Gbps | N/A | 0 | N/A | 100 mbps | N/A | 0 | N/A | 0 | MBC provides optical transport services, using both SONET/TDM, Wavelength and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STSs for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in Â¼ rack increments or 12 rack units) for members. Due to grant funds being used in the construction of the MBC backbone network, Dark fiber IRUs are no longer offered. . Fiber lease arrangements are considered on case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | We provide an open-access network available to all members. We do not limit or block access of lawful content or applications for members. | N/A | 14894 | 26 | 0 | 1846 | 436 | 0 | 12586 | N/A | 0 | 0 | 0 | 0 | Co-location point is with PemTel, located in Newport, VA. Two new interconnection points are built in New Castle, VA, and Bonsack, VA (Eastpark Business Park) | N/A | 1. Start the Environmental Assessment process as early as possible for long, linear projects 2. Perform design work in advance to aid in preparation of EA and construction bidding. | Virginia Tech Foundation, Inc. | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 2 | 1. Entered into 1 agreement (PemTel) 2. Negotiating 1 interconnection agreement (TDS) 3. Have not denied any requests for interconnection. | N/A | TRUE
NT10BIX5570016 | 2012 | 46115 | Average cost less than baseline due to lower than expected bid prices, and baseline estimate included all grant costs | 0 | N/A | 0 | N/A | 10 Gbps | 10 mbps - 100 mbps - Open Access | 0 | N/A | 105 mbps | 10 mbps - 100 mbps - Open Access | 0 | N/A | Broadband speed has not increased. | [REDACTED] | We provide an open-access network available to all customers. We do not limit or block access of lawful services or applications of our customers. | None | 15004 | 585 | 29 | 14146 | 3 | 0 | 241 | N/A | 480 | 240 | 15 | 225 | One (1) co-location point is with Pemtel, located in Newport, VA. Our lease space is 36 square feet. | N/A | 1) Start the environmental assessment process as early as possible for long, linear projects. 2) Do the SHPO assessment for both aerial and buried construction methods. 3) Perform design work in advance to aid in preparation of Environmental Assessment and construction bidding. | Virginia Tech Foundation, Inc. | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 2 | 1) Entered into four (4) agreements: Pemtel (1), Lumos (3) 2) Negotiating two (2) interconnection agreements (TDS, Citizens Telephone) 3) Have not denied any requests for interconnection | N/A | TRUE
NT10BIX5570016 | 2013 | 33695 | Average cost is less than baseline because of lower than expected bid prices and baseline estimate included in all grant costs. | 0 | N/A | 0 | N/A | 10Gbps | 10 mbps - 100 mbps - Open Access | 0 | N/A | 105 mbps | 10 mbps - 100 mbps - Open Access | 0 | N/A | Broadband speed was not increased. | MBC provides optical transport services, using SONET/TDM, Wavelength, and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STS's for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in 1/4 rack increments are 12 rack units) for members. Due to grant funds being used in the construction of the MBC backbone network, Dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on a case by case bysis. See attachment for pricing sheet. | We provide an open-access network available to all customers. We do not limit or block access of lawful services or applications of our customers. | None | 15004 | 585 | 29 | 14390 | 0 | 0 | 0 | Carilion - 28 Bonsack - 464 | 720 | 360 | 30 | 330 | One (1) co-location point is with Pemtel, located in Newport, VA. Our lease space is 36 square feet. | N/A | 1. Start the environment assessment process as early as possible for long, linear projects. 2. Do the SHPO assess for both aerial and buried construction methods. 3. Perform design work in advance to aid in preparation of Environment Assessment and construction bidding. | Virginia Tech Foundation, Inc. | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 2 | 1) Entered int five (5) agreements: Pemtel (1); Lumos (3); Citizens (1) 2) Negotiating two (2) interconnection agreements (TDS, Comcast) 3) Have note denied any requests for interconnection | N/A | TRUE
NT10BIX5570017 | 2010 | 0 | N/A at this point in the project | 0 | N/A | 0 | N/A | 0 | N/A at this point in the project | 0 | N/A | 0 | N/A at this point in the project | 0 | N/A | N/A | N/A, no services have been provided at this point in the project | N/A, no services have been provided at this point in the project | N/A, no services have been provided at this point in the project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A, there is no plan to lease dark fiber. | 0 | 0 | 0 | 0 | The Commonwealth of PA will provide a telecommunications pad and cabinet within the tower compound for both last mile providers and long distance carriers to interconnect with the middle mile broadband network at the 68 backbone locations. In most cases, the switching equipment will be located within our shelter, and we will run a fiber jumper between the shelter and the interconnect cabinet. We will not allow collocation within our shelters for security reasons. | N/A. No subcontracts or sub grants have been made. | With any construction project, there is the inherent risk of delays due to weather. It is prudent to plan for them ahead of time so that you can minimize the impact upon the project should the worst case happen, because chances are good that it will. Also, know that your Federal Program Officer (FPO) is there to ensure that your project is completed successfully and on time. Make sure you communicate with him or her along the way and document everything. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | 34 | 5 | 0 | 3 | 9 | 44 |  | 2 | 1 | 0 | 98 | N/A | N/A | TRUE
NT10BIX5570017 | 2011 | n/a | The miles that have been upgraded as part of this project are not considered to be "new" miles. | n/a | This is a middle mile project. | n/a | This is a middle mile project. | 0 | No speeds have been advertised to date, due to ongoing construction of the network; however, our baseline identified that we would offer our customers Ethernet virtual circuits at 10, 20 and 50 Mbps. | n/a | This is a middle mile project. | 0 | No services have been provided to date; however, our baseline estimates that the average broadband speed will be 20 Mbps. | n/a | This is a middle mile project. | N/A. No services have been provided to Community Anchor Institutions at this point. | N/A. No services have been provided at this point. | N/A. No services have been provided at this point due to the ongoing construction of the network; however, the network management policies that we plan to implement are as follows. Our standard features will include Layer 2 MPLS Ethernet ports and best effort routing with route protection in backbone connections. The base price shall include burst capability of up to 25% of contracted bandwidth at no cost if excess capacity is available. We anticipate that the agreement will include access to the tower site compound but not tower space or access to the Commonwealth's shelter. | N/A. No services have been provided at this point. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. There is no plan to lease dark fiber as part of this project. | 2700 | 2700 | 0 | 0 | The Commonwealth of Pennsylvania's switching equipment will be located within our shelters; however, we will run a fiber jumper between the shelter and an interconnect cabinet within the compound. We will not allow collocation within our shelters for security reasons. | N/A. The Commonwealth of Pennsylvania has not made any subcontracts or sub grants. | The best practice/lessons learned that we could share with other similar BTOP projects would be to ensure regular meetings of the project team to allow for discussion in depth of project happenings. Monthly, we bring our vendors and staff together for a group discussion. During these face to face meetings, we dissect each area of the project and discuss any accomplishments as well as potentials for delay. We are sure to address with our vendors any need for feedback between the parties and deadlines that are necessary to ensure continued progress. Additionally, we have found that having both GIS software as well as professionals trained to use it has proven to be invaluable for many aspects of the project. Our GIS folks have assisted with route change research as well as providing information necessary for the completion of our performance reports. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | 34 | 5 | 0 | 3 | 9 | 44 |  | 2 | 1 | 0 | 98 | N/A. No interconnection agreements have been signed to date; however, we are currently in negotiations with a last mile service provider as well as a community anchor institution with multiple locations in our project footprint. We have not denied any requests for service in 2011. | N/A. No peering or transit agreements have been signed to date. Additionally, we have not denied any requests for service in 2011. | TRUE
NT10BIX5570017 | 2012 | n/a | The miles that have been upgraded as part of this project are not considered to be "new" miles. | n/a | This is a middle mile project. | n/a | This is a middle mile project. | 0 | No speeds have been advertised to date; however, we have connected to two last mile service providers in order to test the network. The maximum speed that these customers are receiving as part of the test, is 10 Mbps. The "Maximum broadband speed advertised metric" noted in our baseline report was 50Mbps; however, as our project reached the stage of connecting customers to the network, we found that most of the project footprint was not necessarily in need of faster broadband, they instead were in need of reliable service at reasonable pricing. With that in mind, advertising faster speeds is not necessarily a driving force in generating demand. | n/a | This is a middle mile project. | 10 | While we are still negotiating an agreement with three last mile service providers, we have actually connected to two of them in order to test the network. The maximum speed that these customers are currently receiving is 10 Mbps. This "average speed provided" metric differs from our baseline report which noted that we would provide an average of 20 Mbps. This variance can be explained in that the customers we are in the process of negotiating contracts with to date, have requested less bandwidth than we had predicted when the baseline report was created. As additional customers are added to the network, the "average speed provided" is expected to change and more closely align with our baseline. | n/a | This is a middle mile project. | N/A. No services have been provided to Community Anchor Institutions at this point; however, we are in negotiations with multiple government facilities (state and local) as well as multiple public safety entities that we intend to connect in the 2013 calendar year. | N/A. No services have been provided at this point. | No services have been provided at this point due to the completion of switching equipment upgrades occurring in mid December of 2012; however, the network management policies that we plan to implement are as follows. Our standard features will include Layer 2 MPLS Ethernet ports and best effort routing with route protection in backbone connections. The base price shall include burst capability of up to 25% of contracted bandwidth at no cost if excess capacity is available. We anticipate that the agreements will also include access to the tower site compound but not tower space or access to the Commonwealth's shelter. We intend to have customers connect to the network through an elevated platform structure where their own secure cabinet can be placed and cabling be routed through existing conduit into our equipment shelter. | N/A. Only the testing of services has occurred to date as we continue to finalize agreements with our first two last mile service providers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. There is no plan to lease dark fiber as part of this project. | 2700 | 2700 | 0 | 0 | The Commonwealth of Pennsylvania's switching equipment will be located within our shelters; however, we will run a fiber jumper between the shelter and an interconnect cabinet within the compound. This interconnect cabinet will be mounted to an elevated platform where our last mile providers may add their own secure cabinet and connect to our network. The construction of the platforms is nearing completion as of the writing of this report; however, since they are not complete, they have not been included in the collocation information above. We will not allow collocation within our shelters for security reasons. | N/A. The Commonwealth of Pennsylvania has not made any subcontracts or sub grants. | The best practice/lessons learned that we could share with other similar BTOP projects would be to ensure regular meetings of the project team to allow for discussion in depth of project happenings. Monthly, we bring our vendors and staff together for a group discussion. During these face to face meetings, we dissect each area of the project and discuss any accomplishments as well as potentials for delay. We are sure to address with our vendors any need for feedback between the parties and deadlines that are necessary to ensure continued progress. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | 34 | 5 | 0 | 3 | 9 | 44 |  | 2 | 1 | 0 | 98 | N/A. No interconnection agreements have been signed to date; however, we are currently in negotiations with three last mile service providers as well as a few community anchor institutions each with multiple locations in our project footprint. We have not denied any requests for service in 2012. | N/A. No peering or transit agreements have been signed to date. Additionally, we have not denied any requests for service in 2012. | TRUE
NT10BIX5570017 | 2013 | N/A | The miles of network that have been upgraded as part of this project are not considered to be "new" miles. | N/A | This is a middle mile project. | N/A | This is a middle mile project. | 0 | No broadband speeds were advertised; however, the baseline report that was submitted at the start of this project noted that we would advertise speeds of 50 Mbps. As the project began the process of connecting customers to the network, it was realized that most customers in the northern tier were not interested in speeds over 10 Mbps. Reliable service at reasonable pricing was the driving factor in making connections for our project. | N/A | This is a middle mile project. | 10 | Most of the customers that have connected to the network are receiving speeds of 10 Mbps; however, we do have four Community Anchor Institutions receiving speeds of 40 Mbps. Our baseline report noted that we would provide an average of 20 Mbps; however, most of the customers that actually connected to the network were more interested in reliable service than they were in speeds over 10 Mbps. | N/A | This is a middle mile project. | The lowest speed increase is zero (same speed, just a more reliable connection) and the highest increase is 567% where a T1 line was replaced by a 10MB wireless connection. The CAI-wide average increase in broadband speed is 242%. This figure wad derived by subtracting new speed from old speed for each CAI yielding a delta percent; averaging all of these, then, provides the overall average of 242%. | N/A. No retail services have been provided as part of this project. Only wholesale services were sold in order to remain in compliance with the Pennsylvania Utility Commission's requirements. | Our standard features include Layer 2 MPLS Ethernet ports and best effort routing with route protection in backbone connections. The base price includes burst capability of up to 25% of contracted bandwidth at no cost if excess capacity is available. The agreements include access to the tower site compound but not tower space or access to the Commonwealth's shelter. Our customers connect to the network through an elevated platform structure where their own secure cabinet can be placed and cabling be routed through existing conduit into our equipment shelter. | N/A. No subscribers have dropped the services provided through this project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. No dark fiber was leased as part of this project. | 5436 | 2830 | 0 | 0 | The Commonwealth of Pennsylvania's switching equipment has been located within our shelters with a fiber jumper between the shelter and an interconnect cabinet within the compound. This interconnect cabinet has been mounted to an elevated platform where our last mile providers have added their own secure cabinet and connected to our network. We have not allowed collocation within our shelters for security reasons. | N/A. The Commonwealth of Pennsylvania has not made any subcontracts or sub grants. | The best practices/lessons learned that we could share with other similar BTOP projects would be to ensure regular meetings of the project team to allow for discussion in depth of project happenings. Monthly, we brought our vendors and staff together for a group discussion. During these face to face meetings, we dissected each area of the project and discussed any accomplishments as well as potentials for delay. We are sure to address with our vendors any need for feedback between the parties and deadlines that are necessary to ensure continued progress. | Executive Office of the Commonwealth of Pennsylvania (Office of Administration) | 34 | 5 | 0 | 3 | 9 | 44 |  | 2 | 1 | 0 | 98 | We have signed agreements with two last mile service providers within the northern tier of Pennsylvania. Through these providers, we were able to provide service to 47 Community Anchor Institutions (CAIs) requiring reliable, low cost high speed internet. Of these CAIs, two are receiving new service while the others are receiving improved services. The last mile service providers that we have connected to are KCNet of Lock Haven, Pennsylvania and North Central Pennsylvania Regional Planning and Development Commission of Ridgway, Pennsylvania. No requests for interconnection were denied. | N/A. No peering or transit agreements have been signed. Additionally, no requests for service were denied. | TRUE
NT10BIX5570018 | 2010 | 0 | We have yet to deploy services. However, total project expenditures to date were $27,061,970 for 3901 miles, for an average cost per new mile of $6,937.19 | 0 | N/A | 0 | N/A | 0 | We have yet to activate services. However, we plan to offer transit speeds up to 1Gbps to last mile providers. | 0 | N/A | 0 | Currently there are no interconnected networks utilizing the services. | 0 | N/A | As of 12/31/2010, we are still testing the PR-FL facilities and have not officially activated services. | The PRBI project does not provide retail services. PRBI provides middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | 7a. Network management policies regarding the new transit & peering services for service providers are still in development as we are still in testing and are finalizing the network architecture & design, which must be completed first. 7b. Critical Hub Networks generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: (a) forwarding of traffic explicitly tagged as "less than best effort" by the end-user, offering a priority of traffic forwarding that is less than best effort to support researchers that choose a lower class of service when they transfer large data sets which are insensitive to loss or latency. (b) MPLS traffic engineering is sometimes used to differentially route "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. (c) measures to address distribution of harmful viruses or spam, denial of service attacks, and other harmful activities following customer notification of violations of our Acceptable Usage Policy. | N/A | 15604 | 0 | 15604 | 0 | 0 | 0 | 0 | N/A | 8000 | 150 | 4602 | 1117 | N/A | Critical Hub Networks, Inc. is itself a Socially and Economically Disadvantaged Small Business (SBD) concern. In addition, funds have been expended to the following SDB's: Computer Paradise, Fire Control Corporation, JAS Corporation, International Hardware Inc. | - Maintain, regularly review all award documents including NOFA, CD450, SAC, Budget, BTOP Recipient Master Checklist of Activities. - Keep your Grant File up-to-date. - Regular logins to PAM & GOL. - Regular communication with NTIA & NOAA staff is essential to ensure that project stays on course and nobody has any surprises. And, if you have any doubts, always ask. - Ensure all SAC requirements, including BAA, Davis Bacon, are properly included in procurement documents such as PO's, RFP/RFQ, and any contractor agreements. - Start all required reporting early, and participate in drop-in calls to address questions. Often other recipients catch minor details that you may miss - its a great way to ensure that you are reporting correctly! - Designate a compliance officer who is dedicated to ensuring project compliance, budgeting, and maintenance of contemporaneous records. - Finding experienced, qualified staff can be a challenge. Hire early. Anticipate training requirements. | Critical Hub Networks, Inc | 1473 | 119 | 0 | 32 | 256 | 194 |  | 0 | 0 | 0 | 2074 | As of 12/31/2010, PRBI has not activated services. Five contracts have been signed with last mile providers. We anticipate activating services for some of these signed contracts in the next quarter. Some of the providers are in the process of constructing the middle mile to the PRBI interconnection point, which will delay the activation of services until that is completed. We are working with 12 potential interconnection clients. Due to competitive purposes, the names of the providers who have signed agreements will be released upon successful activation of interconnection. We have not denied any request for interconnection. | N/A | TRUE
NT10BIX5570018 | 2011 | 7705.21 | Total project expenditures as of 12/31/2011 were $30,058,030. Total miles completed as of 12/31/2011: 3901. Expenditures include costs for future mile deployment. | 0 | N/A | 0 | N/A | 1Gbps | We offer transit speed up to 1Gbps for last mile providres. | 0 | N/A | 258Mbps | As of 12/31/2011, there are 8 last mile providers interconnected. | 0 | N/A | The Puerto Rico Bridge Initiative project is a middle-mile project serving primarily last mile broadband providers. Projections for Community Anchor Institutions on our baseline were made based on data we received from broadband providers on how many each of their networks served. Critical Hub did not receive any funding for laterals or last mile connectivity to CAI's. In Q1 2012, interconnected providers will report on how many CAIs each of their networks serve and we will provide this data to the NTIA in our next quarterly reporting. Additionally, Critical Hub is working directly with the Dept of Education to provide local peering with 1,473 schools at their main facilities. Peering interconnection will be via a 1Gbps port. | The PRBI project does not provide retail services. PRBI provides middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | 7a. Critical Hub's network consists of, but is not limited to, channel banks, hubs, switches, routers, servers, Local Area Networks at the equipment locations, Wide Area Links connecting sites together consisting of the microwave & fiber optic equipment, and the network management tools provided by the equipment manufacturer. The specifics and details are available upon request and published at our webpage (www.criticalhub.com). 7b. Critical Hub Networks generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: (a) forwarding of traffic explicitly tagged as "less than best effort" by the end-user, offering a priority of traffic forwarding that is less than best effort to support researchers that choose a lower class of service when they transfer large data sets which are insensitive to loss or latency. (b) MPLS traffic engineering is sometimes used to differentially route "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. (c) measures to address distribution of harmful viruses or spam, denial of service attacks, and other harmful activities following customer notification of violations of our Acceptable Usage Policy. | N/A | 15604 | 0 | 15604 | 0 | 0 | 0 | 0 | N/A | 8000 | 150 | 4602 | 2131 | N/A | Critical Hub Networks, Inc. is itself a Socially and Economically Disadvantaged Small Business (SBD) concern. In addition, funds have been expended to the following SDB's: Computer Paradise, Fire Control Corporation, JAS Corporation, International Hardware, Than Inc. | - Maintain, regularly review all award documents including NOFA, CD450, SAC, Budget, BTOP Recipient Master Checklist of Activities. - Keep your Grant File up-to-date. - Regular logins to PAM & GOL. - Regular communication with NTIA & NOAA staff is essential to ensure that project stays on course and nobody has any surprises. And, if you have any doubts, always ask. - Ensure all SAC requirements, including BAA, Davis Bacon, are properly included in procurement documents such as PO's, RFP/ RFQ, and any contractor agreements. - Start all required reporting early, and participate in drop-in calls to address questions. Often other recipients catch minor details that you may miss - its a great way to ensure that you are reporting correctly! - Designate a compliance officer who is dedicated to ensuring project compliance, budgeting, and maintenance of contemporaneous records. - Finding experienced, qualified staff can be a challenge. Hire early. Anticipate training requirements. | Critical Hub Networks, Inc | 1473 | 119 | 0 | 32 | 256 | 194 |  | 0 | 0 | 0 | 2074 | As of 12/31/2011, PRBI has signed interconnection agreements with twelve (12) last mile service providers. Eight (8) of those agreements have already established interconnection. The other four (4) pending networks are in the process of constructing/preparing their last mile to the PRBI interconnection site or are pending the completion of the terrestrial middle-mile network spans to their desired interconnection point. We are continuing to negotiate with eight (8) last mile providers. Due to competitive purposes, the names of the providers who have signed agreements will be released upon successful activation of interconnection. We have not denied any request for interconnection. | N/A | TRUE
NT10BIX5570018 | 2012 | 6948.40 | Calculation based on costs associated with middle miles completed as of 12/31/2012: 4,096. | 0 | N/A | 0 | N/A | 10 Gbps | We offer middle mile transit and peering at up to 10Gbps for last mile providers | 0 | N/A | 836.78 Mbps | As of 12/31/2012, there were 14 last mile providers interconnected. | 0 | N/A | The Puerto Rico Bridge Initiative project is a middle-mile project serving primarily last mile broadband providers. Projections for Community Anchor Institutions on our baseline were made based on data we received from broadband providers on how many each of their networks served. Critical Hub did not receive any funding for laterals or last mile connectivity to CAI's. Critical Hub is working directly with the Dept of Education to provide local peering with 1,473 schools at their main facilities. Peering interconnection will be via a 1Gbps port. | The PRBI project does not provide retail services. PRBI provides middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | 7a. Critical Hub's network consists of, but is not limited to, channel banks, hubs, switches, routers, servers, Local Area Networks at the equipment locations, Wide Area Links connecting sites together consisting of the microwave & fiber optic equipment, and the network management tools provided by the equipment manufacturer. The specifics and details are available upon request and published at our webpage (www.criticalhub.com). 7b. Critical Hub Networks generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: (a) forwarding of traffic explicitly tagged as "less than best effort" by the end-user, offering a priority of traffic forwarding that is less than best effort to support researchers that choose a lower class of service when they transfer large data sets which are insensitive to loss or latency. (b) MPLS traffic engineering is sometimes used to differentially route "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. (c) measures to address distribution of harmful viruses or spam, denial of service attacks, and other harmful activities following customer notification of violations of our Acceptable Usage Policy. | N/A | 15604 | 15604 | 0 | 0 | 0 | 0 | 0 | N/A | 8000 | 1267 | 4620 | 2113 | N/A | Critical Hub Networks, Inc. is itself a Socially and Economically Disadvantaged Small Business (SBD) concern. In addition, funds have been expended to the following SDB's: Computer Paradise, EOA Telecom, Fire Control Corporation, JAS Corporation, International Hardware, JD Interiors, Sanchez Technical, TecnolAir, Teknical Telekom, VersaTech. | - Maintain, regularly review all award documents including NOFA, CD450, SAC, Budget, BTOP Recipient Master Checklist of Activities. - Keep your Grant File up-to-date. - Regular logins to PAM & GOL. - Regular communication with NTIA & NOAA staff is essential to ensure that project stays on course and nobody has any surprises. We prepare a memo for each call to summarize project status, ongoing challenges, other pending issues. - Ensure all SAC requirements, including BAA, Davis Bacon, Disbarment, etc are properly included in procurement documents such as PO's, RFP/RFQ, and any contractor agreements. - Start reporting preparations early, and participate in drop-in calls to address questions. Often other recipients catch minor details that you may miss - its a great way to ensure that you are reporting correctly! - Designate a compliance officer who is dedicated to ensuring project compliance, budgeting, and maintenance of contemporaneous records. - Finding experienced, qualified staff can be a challenge. Anticipate training requirements. | Critical Hub Networks, Inc | 1473 | 119 | 0 | 32 | 256 | 194 |  | 0 | 0 | 0 | 2074 | In 2012, PRBI has signed interconnection agreements with five (5) last mile service providers. We are continuing to negotiate interconnection agreements with seven (7) last mile providers. We have not denied any requests for interconnectivity. | N/A | TRUE
NT10BIX5570018 | 2013 | 7014.10 | Calculation based on costs associated with middle miles completed as of 9/30/2013: 4,119 | 0 | N/A | 0 | N/A | 10 Gbps | We offer middle mile transit and peering at up to 10Gbps for last mile providers | 0 | N/A | 1122.5 Mbps | As of 9/30/2013, there were 14 last mile providers interconnected. | 0 | N/A | The Puerto Rico Bridge Initiative project is a middle-mile project serving primarily last mile broadband providers. Projections for Community Anchor Institutions on our baseline were made based on data which we received from broadband providers on how many each of their networks served. Critical Hub did not receive any funding for last mile connectivity to CAI's. | The PRBI project does not provide retail services. PRBI provides middle-mile transit and peering services to broadband service providers. In addition, PRBI will also provide peering services to Critical Community Anchor Institutions and Government Agencies. | 7a. Critical Hub's network consists of, but is not limited to, channel banks, hubs, switches, routers, servers, Local Area Networks at the equipment locations, Wide Area Links connecting sites together consisting of the microwave & fiber optic equipment, and the network management tools provided by the equipment manufacturer. The specifics and details are available upon request and published at our webpage (www.criticalhub.com). 7b. Critical Hub Networks generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: (a) forwarding of traffic explicitly tagged as "less than best effort" by the end-user, offering a priority of traffic forwarding that is less than best effort to support researchers that choose a lower class of service when they transfer large data sets which are insensitive to loss or latency. (b) MPLS traffic engineering is sometimes used to differentially route "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. (c) measures to address distribution of harmful viruses or spam, denial of service attacks, and other harmful activities following customer notification of violations of our Acceptable Usage Policy. | N/A | 15692 | 15626 | 0 | 0 | 0 | 0 | 0 | N/A | 8000 | 1267 | 4620 | 2113 | N/A | Critical Hub Networks, Inc. is itself a Socially and Economically Disadvantaged Small Business (SBD) concern. In addition, funds have been expended to the following SDB's: Computer Paradise, EOA Telecom, Fire Control Corporation, JAS Corporation, International Hardware, JD Interiors, Sanchez Technical, TecnolAir, Teknical Telekom, VersaTech. | - Maintain, regularly review all award documents including NOFA, CD450, SAC, Budget, BTOP Recipient Master Checklist of Activities. - Keep your Grant File up-to-date. - Regular logins to PAM & GOL. - Regular communication with NTIA & NOAA staff is essential to ensure that project stays on course and nobody has any surprises. We prepare a memo for each call to summarize project status, ongoing challenges, other pending issues. - Ensure all SAC requirements, including BAA, Davis Bacon, Disbarment, etc are properly included in procurement documents such as PO's, RFP/RFQ, and any contractor agreements. - Start reporting preparations early, and participate in drop-in calls to address questions. Often other recipients catch minor details that you may miss - its a great way to ensure that you are reporting correctly! - Designate a compliance officer who is dedicated to ensuring project compliance, budgeting, and maintenance of contemporaneous records. - Finding experienced, qualified staff can be a challenge. Anticipate training requirements. | Critical Hub Networks, Inc | 1473 | 119 | 0 | 32 | 256 | 194 |  | 0 | 0 | 0 | 2074 | No new interconnection agreements were entered into for the period January 1, 2013 to September 30, 2013. In total, PRBI has entered into 17 interconnection agreements. We are currently negotiating interconnection with seven (7) last mile providers. We have not denied any requests for interconnectivity. | N/A | TRUE
NT10BIX5570019 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | 10 MBPS-100 MBPS - OPEN ACCESS | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | We provide an open-access network available to all members. We do not limit or block access of lawful content or applications for members. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We will provide four (4) interconnection points on this project. These interconnection points are strategically placed to provide regeneration points, interconnection and access points and co-location points. | N/A | 1- Start the Environmental Assessment (EA) process as early as possible for long, linear projects. 2- Perform design work in advance to aid in preparation of EA and construction bidding. | Mid-Atlantic Broadband Cooperative | 101 | 3 | 0 | 1 | 0 | 0 |  | 9 | 4 | 0 | 118 | N/A | N/A | TRUE
NT10BIX5570019 | 2011 | 21505 | Complete 338 miles or 80% of total miles | 0 | N/A | 0 | N/A | 0 | 10mbps - 100mbps - Open Access | 0 | N/A | 82 mpbs | 10mbps - 100mbps - Open Access | 0 | N/A | Most schools (CAIs) requested 100 mbps services | N/A | We provide an open-access network available to all members. We do not limit or block access of lawful content or applications for members. | None | 29413 | 200 | 0 | 2200 | 160 | 0 | 26853 | N/A | 0 | 0 | 0 | 0 | We provide four (4) interconnection points on this project. These interconnection points are strategically placed to provide regeneration points, interconnection and access points and co-location points. | N/A | 1. Start the Environmental Assessment (EA) process as early as possible for long, linear projects. 2. Perform design work in advance to aid in preparation of EA and construction bidding. | Mid-Atlantic Broadband Cooperative | 101 | 3 | 0 | 1 | 0 | 0 |  | 9 | 4 | 0 | 118 | 1. Entered into 18 interconnection agreements 2. Currently negotiating 2 interconnection agreements. 3. Have not denied any request for interconnection, peering or transit agreements. | N/A | TRUE
NT10BIX5570019 | 2012 | $31,374 | Average cost less than Baseline due to lower than expected bid prices and only 88% of construction is complete | 0 | N/A | 0 | N/A | 10 Gbps | 10 mpbs - 100 mbps - Open Access | 0 | N/A | 59 | 10 mpbs - 100 mbps - Open Access | 0 | N/A | Most schools (CAI's) request either 50 mbps or 100 mbps services. | [REDACTED] | We provide an open access network available to all customers. We do not limit or block access of lawful services or applications of our customers. | None | 28969 | 278 | 0 | 28111 | 137 | 0 | 443 | N/A | 1440 | 720 | 0 | 720 | N/A | N/A | 1) Start the environmental assessment process as early as possible for long, linear projects. 2) Do the SHPO assessment for both aerial and buried construction methods. 3) Perform design work in advance to aid in preparation of Environmental Assessment and construction bidding. | Mid-Atlantic Broadband Cooperative | 101 | 3 | 0 | 1 | 0 | 0 |  | 9 | 4 | 0 | 118 | 1) Entered into 49 agreements 2) Negotiating 1 agreement (Virginia State University) 3) Have not denied any requests for interconnection. | N/A | TRUE
NT10BIX5570019 | 2013 | 29430 | Average cost less than Baseline due to lower than expected bid prices and only 95% of construction budget was actually spent. | 0 | N/A | 0 | N/A | 10 Gbps | 10 mbps - 100 mbps - Open Access | 0 | N/A | 64 | 10 mbps - 100 mbps - Open Access | 0 | N/A | Most schools (CAIs) request either 50 mbps or 100 mbps services | [REDACTED] | We provide an open access network available to all customers. We do not limit or block access of lawful services or applications of our customers. | Buggs Island Telephone(BIT) contracted with MBC to backhaul four (4) cell sites being developed under their BTOP grant. Due to equipment issues, they decreased their footprint and discontinued service to four (4) sites in our footfprint. The percentage of subscribers who have dropped off is 6.7%. The "churn rate" is 6.7%. | 28206 | 396 | 0 | 27810 | 0 | 0 | 0 | N/A | 1440 | 720 | 45 | 675 | N/A | N/A | 1) Start the environmental assessment process as early as possible for long, linear projects. 2) Do the SHPO assessment for both aerial and buried construction methods. 3) Perform design work in advance to aid in preparation of Environmental Assessment and construction bidding. | Mid-Atlantic Broadband Cooperative | 101 | 3 | 0 | 1 | 0 | 0 |  | 9 | 4 | 0 | 118 | 1) Entered into sixty (60) agreements; Shentel (4), Kinex (7), Lumos (11), GCR (31), BIT (4), Telpage (2), Gamewood (1) 2) Negotiating eight (8) agreements 3) Have not denied any requests for interconnection | N/A | TRUE
NT10BIX5570023 | 2010 | 0 | Equipment procurement is underway; however, actual deployment has not started, and no portion of the network is available for service yet. Therefore, there is no cost per mile indicated for this report. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | 1 Gbps | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | 100 Mbps | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps, and we anticipate that most of our customers will fall into that level of service. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | Preliminary research indicates that current broadband speed available for community anchor institutions is less than 6 Mbps, according to survey respondents that were asked to identify their ISPâ€™s advertised speed. Actual speeds measured at individual workstations can be substantially less than advertised speeds. Therefore, we conservatively anticipate the average increase in broadband speed provided to be in the range of 5 Mbps to 95 Mbps, as 10 Mbps to 100 Mbps is the level of service range that we anticipate will be offered to most community anchor institutions. | Planned services include Standard and Premium wholesale, enterprise, and e-Rate/discounted government Ethernet access. Please see the attached preliminary pricing plan draft for the NFBA network. | Network management policies are in compliance with the nondiscrimination and interconnection obligations outlined in the NOFA. When completed, the project will provide open, ubiquitous, Middle Mile access to broadband Internet services for both private entities and public institutions in the underserved areas of northern Florida. We will display all non-discrimination practices in a prominent location on our web site and we will provide notice to customers of any changes to these policies. We are fully committed to offering wholesale access to the project facilities at reasonable rates and terms. We are also committed to binding private arbitration for any disputes concerning these interconnection obligations. Our network management practices and policies will adhere to the principles contained in the Federal Communications Commissionâ€™s Internet Policy Statement and not show favoritism to any lawful Internet applications and content over others. The NFBA network will not be a private closed network, but will instead be connected to the public Internet directly and provide open access to all Internet resources. We will offer interconnection where technically feasible without exceeding current or reasonably anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A. This project is a Middle Mile network that has not yet been deployed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We will not be providing access to dark fiber, as we do not have that access. | 292 | 292 | 292 | 292 | The availability of any additional co-location space is yet to be determined, as is its necessity. Upstream IRU design configuration is complete, IRU with Level 3 is in place to connect the core middle mile network to the first mile Internet backbone, and circuit delivery is on schedule. Interconnection for customers (last mile providers) will be accessed through switched IP/Ethernet multi-service access platforms located at each tower/wireless network link. | We have not issued any subcontracts or subgrants. | We improved our approach to network design, utilizing shorter links, more licensed towers, and lower cost ratios to yield greater reliability, greater capacity, and greater competition from more available manufacturersâ€”all within the original overall project budget. This approach requires more time for site assessments (for existing commercial towers and in-kind vertical assets) and follow-up engineering and network design, but it yields improved efficiency and shortens the overall deployment schedule. We are asking the Grants Office to review a draft template of our master tower license agreement in order to obtain verification that the contract language in the license agreement is in compliance with grant requirements. We are also in the process of determining Davis-Bacon wage rate decisions for equipment installation laborers, and to that end we submitted an Award Action Request to the Grants Office (for our NFBA project) that included a Request for Authorization of Additional Classification and Rate (SF 1444) for proposed classification titles. We are also conducting our own research on this matter in order to move forward with the development of the Equipment Installation and Pathing RFP in an effort to avoid any delay to the release of this RFP and to subsequent equipment installation activities. In addition, we are checking for previous/duplicate federal funding for targeted in-kind assets, per the Grants Officeâ€™s request. Discovery of previous or duplicate federal funding for in-kind assets may or may not impact planned project progress, depending on the interpretation of this particular requirement. We are seeking to utilize only a limited amount of space on any given in-kind asset to mount microwave antennas and equipment; we are not seeking to utilize any in-kind asset in its entirety. | North Florida Broadband Authority | 144 | 29 | 5 | 14 | 265 | 74 |  | 243 | 702 | 0 | 1476 | N/A. We are continuing to finalize products and pricing with pre-deployment service level agreements. We have continuing dialogue with carriers, resellers, and community anchor institutions, with the expectation of signing several after pricing and service level agreements are finalized. While we have not yet signed agreements with other providers as yet, the pricing and ability to describe the value proposition is imminent, and we anticipate the signing of several agreements this quarter and next. We have not denied any request for interconnection. | N/A. As noted above, we are developing products and pricing with pre-deployment service level agreements, and developing dialogue with carriers, re-sellers, and community anchor institutions, with the expectation of signing several after pricing and service level agreements are finalized. Also, the network design is committed to meeting the stringent quality of service and reliability standards set by the State of Florida for providing transport and direct internet access (as a last mile provider of last resort) to State agencies. Once deployed, the NFBA network will be qualified to serve State offices, community colleges, and their last mile network partners. | TRUE
NT10BIX5570023 | 2011 | 0 | Deployment is still underway due to the grant suspension and transfer to new General Contractors; therefore, no portion of the network is available for service yet, hence, there is no cost per mile indicated for this report. | 0 | n/a | 0 | n/a | 1 Gbps | Currently engaging a vendor to conduct a market analysis to analyze services and pricing in rural Florida to validate baseline service offerings. However, the Maximum of 1 Gbps will continue to be available as described in the baseline for those last mile providers connecting at point of presence locations. | 0 | This is a middle mile network. The connection to last mile customers will be made by last mile providers. | 100 Mbps | Currently engaging a vendor to conduct a market analysis to analyze services and pricing in rural Florida to validate baseline service offerings. Services of up to 1 Gbps service will be available for those last mile providers connecting at point of presence locations. | 0 | This is a middle mile network. The connection to last mile customers will be made by last mile providers. | N/A | N/A | N/A - policies under development | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 292 | 146 | 0 | 146 | The NFBA does have collocation space available for interconnection with our network. In addition, as a wireless network, we have 92 interconnection points with ground lease space available at each site for collocating within the NFBA footprint. | None at this time. | n/a | North Florida Broadband Authority | 144 | 29 | 5 | 14 | 265 | 74 |  | 243 | 702 | 0 | 1476 | The NFBA has been working on implementing a Corrective Action Plan and Transition Plan approved by the Grants Office following suspension of the Grant Award. NFBA is now completing a network evaluation and revised Project Plan to reflect its path forward following the completion of the transition to its new operating structure. In 1st quarter 2012, the NFBA will be conducting one or more community outreach events to inform key stakeholders regarding NFBA's activities, and is working to provide updated information regarding network routes and interconnection points. No request for interconnection has been denied. In addition, the NFBA has begun negotiation of two interconnection agreements with last mile providers. The NFBA, however, is currently in the process of updating its analysis of service offerings, pricing, and needs. These negotiations will proceed more rapidly following the completion of that analysis. | The NFBA has been working on implementing a Corrective Action Plan and Transition Plan approved by the Grants Office following suspension of the Grant Award. NFBA is now completing a network evaluation and revised Project Plan to reflect its path forward following the completion of the transition to its new operating structure. In 1st quarter 2012, NFBA will be conducting one or more community outreach events to inform key stakeholders regarding NFBA's activities and will provide updated information regarding network routes and interconnection points. Currently, the NFBA board has approved the Acceptable Use Policy, the Privacy Policy, and the main Service Level Agreement. Exhibits to articulate specifics to the providers to acquire space for peering and transit which will be negotiated on an as needed basis. service and costs would be negotiated at future time. Colocation space is available at the Level 3 facility to allow for anchor institutions and last mile | TRUE
NT10BIX5570023 | 2012 | $28,537 | Average cost per new mile is calculated as follows: Cumulative direct capital costs associated with the installation of middle mile transmission infrastructure (through the end of calendar year 2012), divided by the route miles that the middle mile transmission infrastructure traverses. Capital costs are derived from equipment, material, and associated labor costs for the deployment of middle mile transmission infrastructure, such as tower cabling, field-installed equipment cabinets and access platforms (switches), licensed wireless radios and antennas, leased vertical tower space, and donated in kind vertical tower space. Capital costs do not include network access (e.g., core routers, upstream / first mile circuit provisioning, and associated leased co-location space for upstream circuits), customer premise equipment, testing equipment, billing and operational support systems, and professional services. Average cost per new mile, through the end of calendar year 2012: $20,546,768 / 720 miles = $28,537 / mile Route miles are determined as total new miles, which for this project corresponds to total new wireless core network miles. Our baseline plan was based on our original network design. The total new middle mile network miles and average cost per mile indicated in this report reflect our updated network design, which was approved through an Award Action Request. | 0 | This project is a Middle Mile network. We will work with our Last Mile providers to assist with the collection of this data as it becomes available. | 0 | This project is a Middle Mile network. We will work with our Last Mile providers to assist with the collection of this data as it becomes available. | 1 Gbps | At out Point of Presence we will deliver up to 1 Gbps to Last Mile providers and/or Community Anchor Institutions. Available speed tiers are customizable, generally increasing in increments of 10 Mbps. | 0 | This project is a Middle Mile network. We will work with our Last Mile providers to assist with the collection of this data as it becomes available. | 100 Mbps | The NFBA will deliver up to 1 Gbps to Last Mile providers and/or Community Anchor Institutions at our Point of Presence. Available speed tiers will begin at 10 Mbps, increasing in increments of 10 Mbps and 100 Mbps. | 0 | This project is a Middle Mile network. We will work with our Last Mile providers to assist with the collection of this data as it becomes available. | Our partners at the Florida State University Information Institute conducted needs assessment, benchmarking, and onsite diagnostics at participating community anchor institutions in our network service area. Their research indicates that the current broadband speed available for the majority of community anchor institutions in our service area is 5 Mbps or less, according to survey respondents that were asked to identify their Internet Service Provider's advertised speed. Actual speeds measured at individual workstations can be substantially less than advertised speeds. Therefore, we estimate the average increase in broadband speed provided through our project to be in the range of 5 Mbps to 95 Mbps, as 10 Mbps to 100 Mbps is the level of service range that is typically offered to most community anchor institutions. | Planned services include wholesale, enterprise, and e-Rate / discounted government Internet access. Private households and businesses are served through our last mile provider partners. | Network management policies are in compliance with the nondiscrimination and interconnection obligations outlined in the Notice of Funds Availability. This project provides open, ubiquitous, Middle Mile access to broadband Internet services for both private entities (last mile service providers) and community anchor institutions in the underserved areas of northern Florida. Our non-discrimination policies are available to the public, and we will provide notice to our customers of any changes to these policies. We are fully committed to offering wholesale access at reasonable rates and terms. Our network management practices and policies adhere to the principles contained in the Federal Communications Commissionâ€™s Internet Policy Statement and do not show favoritism to any lawful Internet applications and content over others. The North Florida Broadband Authority network is not a private, closed network, but instead is connected to the public Internet directly and provides open access to all Internet resources. We will offer interconnection where technically feasible without exceeding current or reasonably anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A. This project is a Middle Mile network. Private households and businesses are served through our Last Mile provider partners. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. We will not be providing access to dark fiber, as we do not have that access. In reference to Question 9 above, this project is not constructing any fiber miles, so therefore all 7 fields in Question 9 are N/A, or not applicable. The formatting of this report does not permit us to enter letters (such as "N/A") in these fields, so we entered "0" instead. | 292 | 146 | 0 | 146 | The North Florida Broadband Authority has co-location space available for interconnection with our network. In addition, as a wireless network, we have 92 interconnection points with ground lease space available at each site for co-location within our core network footprint. Interconnection for customers (last mile providers) is available through switched multi-service access platforms located at each core network tower/wireless link. | N/A. We have not issued any subcontracts or subgrants. | Our in-house general management staff hosted a series of stakeholder workshops during this past calendar year to build relationships with the local broadband service providers in our service area. These events proved to be effective as we were able to present these local providers with the latest information regarding the status and direction of our network development. We also invited them to discuss their expectations for bandwidth and services in an open forum where they provided us with important feedback. We are continuing to plan workshops and seek other opportunities to build and leverage our relationships with the local broadband service providers in our service area. We also completed a comprehensive market and rate study to develop customer growth forecasts for our network services portfolio. This analysis supported our internal management strategies for product and service pricing, demand forecasting, capacity planning, network enhancements, capital and operational budgeting, long-term financial planning, and providing value-added services. | North Florida Broadband Authority | 144 | 29 | 5 | 14 | 265 | 74 |  | 243 | 702 | 0 | 1476 | We completed a market and rate study to develop customer growth forecasts for our network services portfolio and to provide current-state assessments and future-state recommendations for business planning and organizational activities. Through this analysis, we developed effective management strategies to plan, deliver, and manage our broadband services. In addition, following a transition period that resulted in significant improvements to our network engineering and deployment processes, our core middle mile network is now complete, fully operational, and available for customer access. We also successfully executed our network enhancement plan to ensure that network performance and capacity requirements are aligned with actual market conditions and forecasted customer demand. We have entered into 3 interconnection agreements for our organization to sell our wholesale services to last mile providers in our network service region. We are in negotiations for 1 interconnection agreement at this time to sell our wholesale services to another last mile provider. We have not denied any request for interconnection, as it is our policy to remain actively engaged in open customer acquisition. | Co-location space is available at our upstream (first mile) providers' facilities to allow for last mile Internet service providers and community anchor institutions to acquire space for peering and transit services, which will be negotiated on an as-needed basis. We currently have signed agreements in place for our organization to sell our wholesale services to 3 last mile providers in our network service region. We are in negotiations for 1 agreement at this time to sell our wholesale services to another last mile provider. We have not denied any request for peering and transit services, as it is our policy to remain actively engaged in open customer acquisition. | TRUE
NT10BIX5570023 | 2013 | $22,144.89 | Average cost per new mile is calculated as follows: Cumulative direct capital costs associated with the installation of middle mile transmission infrastructure (from project inception through the end of the 3rd quarter of calendar year 2013), divided by the route miles that the middle mile transmission infrastructure traverses. Average cost per new mile, through the end of 3rd Quarter 2013: $18,291,678.96 / 826 new miles = $22,144.89 / new mile New miles are represented by new wireless network miles determined by equipment installed at towers within a direct line of sight. Fiber leased from our upstream providers is not included in this calculation. Our baseline plan was based on our original network design. The total new middle mile network miles and average cost per mile indicated in this report reflect our updated network design, which was approved through an Award Action Request. | 0 | This project is a Middle Mile Network. As such, Last Mile customer provisioning costs are incurred by our Last Mile provider partner. | 0 | This project is a Middle Mile Network. As such, Last Mile customer provisioning costs are incurred by our Last Mile provider partner. | 1 Gbps | Our Points of Presence are designed to deliver up to 1 Gbps to Last Mile providers and/or Community Anchor Institutions. Available speed tiers are customizable and generally increase in increments of 10 Mbps. | 0 | This project is a Middle Mile Network, and our network is capable of delivering maximum broadband speeds of up to 1 Gbps to Community Anchor Institutions from our Points of Presence. Our Last Mile provider partner publishes their maximum advertised broadband speeds at their discretion. Please see the attached Excel spreadsheet â€œAnnual PPR CCI Addendumâ€ for more details regarding broadband speeds provided to Community Anchor Institutions. | 100 Mbps | Our network is designed to deliver up to 1 Gbps to Last Mile providers and/or Community Anchor Institutions at our Points of Presence. Available speed tiers begin at 10 Mbps and increase in increments of 10 Mbps and 100 Mbps. | 8 Mbps | This project is a Middle Mile Network. The average broadband speed listed here is based on information provided by our Last Mile provider partner and represents the average speed provided to residential, business, and Community Anchor Institution last mile customers that receive broadband service through our network. We will continue to work with our Last Mile partner to provide this information as it is made available to us. Please see the attached Excel spreadsheet â€œAnnual PPR CCI Addendumâ€ for more details regarding broadband speeds provided to Community Anchor Institutions. | According to research from our partners at the Florida State University Information Institute, broadband speeds previously available for the majority of community anchor institutions in our service area were 5 Mbps or less, according to survey respondents that were asked to identify their Internet Service Provider's advertised speed. Actual speeds measured at end-user client workstations can be substantially less than advertised speeds due to high demand for broadband capacity within the facility. We therefore estimate the average increase in broadband speed provided through the North Florida Broadband Authority network to be in the range of 5 Mbps to 95 Mbps, as 10 Mbps to 100 Mbps is the level of service range that is typically offered to most community anchor institutions. | This project is a Middle Mile network that provides wholesale high speed Internet access to Last Mile providers and Community Anchor Institutions (as a provider of last resort, in the event Last Mile provider services are not available to the Community Anchor Institution). Our services include wholesale, enterprise, and e-Rate / discounted government Internet access. Private households and businesses are served through our last mile provider partner. | Our network management policies are in compliance with the nondiscrimination and interconnection obligations outlined in the Notice of Funds Availability. Our network provides open, ubiquitous, Middle Mile access to broadband Internet services for both private entities (last mile service providers) and community anchor institutions in the underserved areas of northern Florida. Our non-discrimination policies are available to the public, and we will provide notice to our customers of any changes to these policies. We are fully committed to offering wholesale access at reasonable rates and terms. Our network management practices and policies adhere to the principles contained in the Federal Communications Commissionâ€™s Internet Policy Statement and do not show favoritism to any lawful Internet applications and content over others. The North Florida Broadband Authority network is not a private, closed network, but instead is connected to the public Internet directly and provides open access to all Internet resources. We offer interconnection opportunities where technically feasible without exceeding current or reasonably anticipated capacity limitations, with reasonable rates and terms negotiated with requesting parties. | N/A. This project is a Middle Mile network. Private households and businesses are served through our Last Mile provider partner. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. We do not provide access to dark fiber, as we do not have that access. In reference to Question 9 above, this project has not constructed any fiber miles, so therefore all 7 fields in Question 9 are N/A, or not applicable. The formatting of this report does not permit us to enter letters (such as "N/A") in these fields, so we entered "0" instead. | 438 | 438 | 0 | 438 | The North Florida Broadband Authority has co-location space available for interconnection with our network. In addition, as a wireless network, we have 95 interconnection points with ground lease space available at each site for co-location within our core network footprint. Interconnection for customers (Last Mile providers) is available through switched multi-service access platforms located at each core network tower site. | N/A. We have not issued any subcontracts or sub-grants to any socially and/or economically disadvantaged small businesses. | â€¢ We continued to organize workshops and outreach events for project stakeholders, community leaders, and Last Mile service providers. Our goals with these workshops are to provide stakeholders with current information regarding the status of our network development plans and to provide them with an open forum to discuss their expectations and concerns for bandwidth and services. This interaction gives us important feedback to include as an input for our market-based engineering processes. We expect that utilizing these types of outreach events and workshops would produce similar benefits for other BTOP projects. â€¢ During this past calendar year, we developed and launched of series of informational videos to create awareness for our network services. These videos include testimonials from some of our early adopter customers who describe how they are using high-speed broadband Internet service provided through our network to create their own success stories, which include building a profitable startup business (ahead of schedule) and improving the quality of online educational resources for the children who attend our rural community schools. Other similar BTOP projects might benefit from these types of informational or promotional videos by using them as supplemental media on their public-facing websites and social media pages. North Florida Broadband Authority informational videos can be viewed online at: www.youtube.com/user/NFBA1 â€¢ We continued to plan and coordinate in-kind site development with our Last Mile provider partner in a collaborative effort to provide broadband service to Community Anchor Institutions. We leveraged this Middle Mile / Last Mile partnership to reduce implementation time, cost, and risk, which helped to ensure faster "time to benefit" for everyone involved. â€¢ We continued to implement our network design enhancement plan this past calendar year, which included comprehensive independent reviews and assessments of our network's (then) current-state capabilities and future-state requirements to ensure that our network is able to meet current and anticipated customer demand for our high-speed Internet services and solutions. | North Florida Broadband Authority | 144 | 29 | 5 | 14 | 265 | 74 |  | 243 | 702 | 0 | 1476 | We entered into one interconnection agreement to sell our wholesale broadband services to a last mile provider in our network service region. We have not denied any request for interconnection, as it is our policy to remain actively engaged in open customer acquisition. | Co-location space is available at our upstream (First Mile) providers' facilities to allow Last Mile Internet service providers and Community Anchor Institutions to acquire space for peering and transit services, which is negotiated on an as-needed basis. We have not denied any request for peering and transit services, as it is our policy to remain actively engaged in open customer acquisition. | TRUE
NT10BIX5570024 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No network build out has been completed at this time. | The U of U /UEN will not be offering any retail services. | UEN uses industry standard network management processes with specific emphasis on maintaining a stable backbone. UEN does not currently limit or prioritize specific traffic on the network. All traffic flows freely and is available for any legitimate purpose defined by policy. No traffic filtering occurs on the network with the exception for sites serving minors where content filters limit access to adult-content systems and services. | The U of U/UEN BTOP project has not completed connectivity to any subscribers at this point in time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | The U of U/UEN network Points of Presence (PoP) are located in all institutions of higher education around the State of Utah. These sites serve as regional aggregation points for customers on the network and connect directly to the U of U/UEN backbone. Community Anchor Institutions (CAIs) will have a Telecommunications Partner customer hand off that serves as a interconnection point to the U of U/UEN network. | None at this time. | The U of U/UEN would recommend that all recipients carefully examine and build into their project time line and budget the necessary resources needed to complete the Environmental Assessment. This process should start immediately following grant award notification. Not fully understanding the resources required to complete this milestone drastically changed the overall U of U/UEN project completion schedule. Secondly, early discussion and clarification of all Special Award Conditions with sub-recipients during the application process is advised. A comprehensive understanding of their responsibilities should be started as early on in the grant process as is feasible. If possible, agreements delineating all responsibilities should be signed as early as possible in the post grant award period. Lastly, establishing a relationship with your grant Federal Program Officer (FPO) is vital to navigating any obstacles and keeping your project moving forward. Establishing a regular meeting schedule with your FPO to cover issues and provide progress updates will prove to be invaluable. | University of Utah, The | 106 | 20 | 0 | 0 | 23 | 149 |  | 0 | 0 | 0 | 298 | No network build out has been completed at this time. | No network build out has been completed at this time. | TRUE
NT10BIX5570024 | 2011 | 58,224 | There is a significant increase and variance from the Baseline Report because the calculation in that report included new network miles leased, whereas this Annual Performance Report includes only newly constructed miles. Additionally, the U of U/UEN has not been invoiced for thirty (30) of the ninety five (95) completed builds, so the budgeted amount was used for these sites when calculating this average. | 0 | N/A | 0 | N/A | 1000Mbps | This is the maximum circuit connection speed that is being offered by sub recipients. | 0 | N/A | 712Mbps | The U of U/UEN BTOP project is connecting CAIs with circuit speeds ranging from 2Mbps (one CAI) to a majority of CAIs, connecting at 100Mbps and 1000Mbps. These circuits speeds are committed rates with dedicated bandwidth. | 0 | N/A | The average increase in broadband speed for CAI customers as a result of the BTOP Utah Anchors project is seven hundred ten (710) Mbps or an average of four hundred sixty (460) percent. All of the CAIs that are part of the U of U/UEN BTOP Utah Anchors project were previously connected via T1s at a rate of 1.544 Mbps. The average connected speed for the ninety five (95) CAIs that are now completed as a part of this project, is seven hundred twelve (712) Mbps. To arrive at an average increase in broadband speed, we subtracted the previous average broadband speed (A) from the BTOP project average broadband speed (B) to arrive at the average increase in speed (C) and divided this by the previous average broadband speed to arrive at a percentage of increase. See the following: 712 -1.544 = 710.456 / 1.544 = 460%. | The U of U/UEN is not a retail service provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Partners who will provision critical fiber infrastructure to the CAI end sites. These Telecommunications Partners intend to make use of this infrastructure by offering telecommunication services to residential and business customers on a retail or commercial basis in these service areas. | UEN uses industry standard network management processes with specific emphasis on maintaining a stable backbone. UEN does not currently limit or prioritize specific traffic on the network. All traffic flows freely and is available for any legitimate purpose defined by policy. No traffic filtering occurs on the network with the exception for sites serving minors where content filters limit access to adult-content systems and services. | N/A | 2175 | 734 | 0 | 0 | 1441 | 0 | 0 | N/A | 600 | 50 | 0 | 550 | The U of U/UEN network Points of Presence (PoP) are located in institutions of public and higher education around the State of Utah. These sites serve as regional aggregation points for customers on the network and connect directly to the U of U/UEN backbone. Community Anchor Institutions (CAIs) will have a Telecommunications Partner customer hand off that serves as a interconnection point to the U of U/UEN network. | None at this time. | The U of U/UEN would recommend that all recipients carefully examine and build into their project time line and budget the necessary resources needed to complete the Environmental Assessment. This process should start immediately following grant award notification. Not fully understanding the resources required to complete this milestone, drastically changed the overall U of U/UEN project completion schedule. Secondly, early discussion and clarification of all Special Award Conditions with sub-recipients during the application process is advised. A comprehensive understanding of their responsibilities should be started as early on in the grant process as is feasible. If possible, agreements delineating all responsibilities should be signed as early as possible in the post grant award period. Lastly, establishing a relationship with your grant Federal Program Officer (FPO) is vital to navigating any obstacles and keeping your project moving forward. Establishing a regular meeting schedule with your FPO to cover issues and provide progress updates will prove to be invaluable. | University of Utah, The | 106 | 20 | 0 | 0 | 23 | 149 |  | 0 | 0 | 0 | 298 | The U of U/UEN has entered into four (4) interconnection agreements during this annual reporting period. The U of U/UEN in not currently negotiating any additional agreements nor have we denied any requests for interconnection. | N/A | TRUE
NT10BIX5570024 | 2012 | 95,765 | There is a significant increase and variance from the Baseline Report because the calculation in that report included new network miles leased, whereas this Annual Performance Report includes only newly constructed miles. | 0 | N/A | 0 | N/A | 1000Mbps | This is maximum circuit connection speed that is being offered by the sub-recipients. | 0 | N/A | 660Mbps | The U of U/UEN BTOP project is connecting CAIs with circuit speeds ranging from 2Mbps (one CAI) to a majority of CAIs connecting at 1000Mbps. These circuit speeds are committed rates with dedicated bandwidth. | 0 | N/A | The average broadband speed for CAI customers as a result of the BTOP Utah Anchors project is six hundred sixty (660) Mbps or an average increase of four hundred twenty six (426) percent. All of the CAIs that are part of the U of U/UEN BTOP Utah Anchors project were previously connected via T1s at a rate of 1.544 Mbps. The average connected speed for the one hundred thirty five (135) CAIs that are now completed as a part of this project, is six hundred sixty six (660) Mbps. To arrive at an average increase in broadband speed, we subtracted the previous average broadband speed for CAIs (B) from the BTOP project average broadband speed for CAIs (A) to arrive at the average increase in speed (I) and divided this by the previous average broadband speed (B) to arrive at a percentage of increase (P) . See the following: A - B = I/B = P (660 -1.544 = 658.456 / 1.544 = 426%). | The U of U/UEN is not a retail service provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Partners who will provision critical fiber infrastructure to the CAI end sites. These Telecommunications Partners intend to make use of this infrastructure by offering telecommunication services to residential and business customers on a retail or commercial basis in these service areas. | The U of U/UEN uses industry standard network management processes with specific emphasis on maintaining a stable backbone. The U of U/UEN does not currently limit or prioritize specific traffic on the network. All traffic flows freely and is available for any legitimate purpose defined by policy. No traffic filtering occurs on the network with the exception for sites serving minors where content filters limit access to adult-content systems and services. | N/A | 2339 | 998 | 0 | 0 | 1441 | 0 | 0 | N/A | 853 | 71 | 0 | 782 | The U of U/UEN network Points of Presence (PoP) are located in institutions of public and higher education around the State of Utah. These sites serve as regional aggregation points for customers on the network and connect directly to the U of U/UEN backbone. Community Anchor Institutions (CAIs) will have a Telecommunications Partner customer hand off that serves as a interconnection point to the U of U/UEN network. | None at this time. | The U of U/UEN would recommend that all recipients carefully examine and build into their project time line and budget the necessary resources needed to complete the Environmental Assessment. This process should start immediately following grant award notification. Not fully understanding the resources required to complete this milestone, drastically changed the overall U of U/UEN project completion schedule. Secondly, early discussion and clarification of all Special Award Conditions with sub-recipients during the application process is advised. A comprehensive understanding of their responsibilities should be started as early on in the grant process as is feasible. If possible, agreements delineating all responsibilities should be signed as early as possible in the post grant award period. Lastly, establishing a relationship with your grant Federal Program Officer (FPO) is vital to navigating any obstacles and keeping your project moving forward. Establishing a regular meeting schedule with your FPO to cover issues and provide progress updates will prove to be invaluable. | University of Utah, The | 106 | 20 | 0 | 0 | 23 | 149 |  | 0 | 0 | 0 | 298 | The U of U/UEN has not entered into any interconnection agreements during the annual reporting period. The U of U/UEN is not currently negotiating and additional agreements nor have we denied any requests for interconnection. | N/A | TRUE
NT10BIX5570024 | 2013 | 92,991 | There is an increase and variance from the Baseline Report because the calculation in that report included new network miles leased, whereas this Annual Performance Report includes only newly constructed miles. | 0 | N/A | 0 | N/A | 100000Mbps | This is the maximum circuit connection speed that is being offered by the sub-recipients. | 0 | N/A | 675Mbps | The U of U/UEN BTOP project is connecting CAIs with circuit speeds ranging from 2Mbps (one CAI) to a majority of CAIs connecting at 1000Mbps. These circuit speeds are committed rates with dedicated bandwidth. | 0 | N/A | The average broadband speed for CAI customers as a result of the BTOP Utah Anchors project is six hundred seventy-five (675) Mbps or an average increase of four hundred thirty six (436) percent. All of the CAIs that are part of the U of U/UEN BTOP Utah Anchors project were prevously connected via T1s at a rate of 1.544 Mbps. The average connected speed for the one hundred forty-two (142) CAIs that are now completed as a part of this project, is six hundred seventy five (675) Mbps. To arrive at an average increase in broadband speed, we subtracted the previous broadband speed for CAIs (B) from the BTOP project average broadband speed for CAIs (A) to arrive at the average increase in speed (I) and divided this by the previous average broadband speed (B) to arrive at a percentage of increase (P). See the following: A - B = I / B = P or (675 - 1.544 = 673.456 / 1.544 = 436%). | The U of U/UEN is not a retail service provider. Our BTOP project will deliver broadband connections to specific CAIs working with incumbent Telecommunications Partners who will provision critical fiber infrastructure to the CAI end sites. These Telecommunications Partners intend to make use of this infrastructure by offering telecommunications services to residential and business customers on a retail or commercial basis in these service areas. | The U of U/UEN uses industry standard network management processes with specific emphasis on maintaining a stable backbone. The U of U/UEN does not currently limit or prioritize specific traffic on the network. All traffic flows freely and is available for any legitimate purpose defined by policy. No traffic filtering occurs on the network with the exception of sites serving minors where content filters limit access to adult-content systems and services. | N/A | 2589 | 1073 | 0 | 0 | 0 | 0 | 0 | N/A | 963 | 855 | 27 | 108 | The U of U/UEN network Points of Presence (PoP) are located in institutions of public and higher education around the State of Utah. These sites serve as regional aggregation points for customers on the network and connect directly to the U of U/UEN backbone. Community Anchor Institutions (CAIs) will have a Telecommunications Partner customer hand off that serves as a interconnection point to the U of U/UEN network. | None at this time. | The U of U/UEN would recommend that all recipients carefully examine and build into their project time line and budget the necessary resources needed to complete the Environmental Assessment. This process should start immediately following grant award notification. Not fully understanding the resources required to complete this milestone drastically changed the overall U of U/UEN project completion schedule. Secondly, early discussion and clarification of all Special Award Conditions with sub-recipients during the application process is advised. A comprehensive understanding of their responsibilities should be started as early on in the grant process as is feasible. If possible, agreements delineating all responsibilities should be signed as early as possible in the post grant award period. Lastly, establishing a relationship with your grant Federal Program Officer (FPO) is vital to navigating any obstacles and keeping your project moving forward. Establishing a regular meeting schedule with your FPO to cover issues and provide progress updates will prove to be invaluable. | University of Utah, The | 106 | 20 | 0 | 0 | 23 | 149 |  | 0 | 0 | 0 | 298 | The U of U/UEN has not entered into any interconnection agreements during the annual reporting period. The U of U/UEN is not currently negotiating any additional agreements nor have we denied any requests for interconnection. | N/A | TRUE
NT10BIX5570025 | 2010 | $54,263.56 | N/A | N/A | N/A | N/A | N/A | 10Gbps | N/A | N/A | N/A | 1Gbps | N/A | N/A | N/A | Seventeen of the sites are connected via NxT1, or DS3, and four sites are connected via Gigabit ethernet connections. The average increase is approximately 2.5gigabits. This is based on the gig locations moving to 10gig connections, and all other sites moving to 1 gig connections. Specifically, 4 sites increase by 9 gig, seven sites increase from 45 meg to 1000 meg, and nine sites increase from 9 meg to 1000 meg. The average is 2.5 gigabit increase. | The Zayo Bandwidth Middle Mile Proposal leverages dark fiber, DWDM (Dense Wave Division Multiplexing), and SONET (Synchronous Optical Network) technologies to provide Point to Point Private Line, Ethernet, Wavelength, Dark Fiber and Dedicated Internet services to last mile providers and end users. High count single mode fiber is being deployed in rings and linear spurs off of Zayo Bandwidthâ€™s existing network infrastructure to maximize the reach of the proposal. DWDM and SONET technologies are being deployed over the fiber to enable 1.5M to 10G services from the newly reached communities to the Zayo network infrastructure and the internet. The proposal provides interconnect points for connectivity to last mile providers or end users in the various markets via strategically placed points along the fiber path. From each interconnection point, Zayo will be capable of delivering Ethernet, Private Line, Wavelength, Dark Fiber and Dedicated Internet Access services from 1.5Mbps to 10Gbps via industry standard interfaces. A last mile provider or end user can connect to Zayo Bandwidth at any interconnection point via 2 fiber or 4 fiber optical interfaces. A 2 fiber interface is provided for Ethernet, Wavelength, and Unprotected SONET services while a 4 Fiber interface is used to provide Protected SONET services. The interconnection will leverage industry standard SONET interfaces at OC3, OC12, OC48, or OC192 SONET rates for the various service types, or can leverage standard Gigabit or 10Gigabit Ethernet interfaces for Ethernet private line, Wavelength, and Dedicated Internet Access services. A last mile provider or end user can also request that Zayo Bandwidth extend from a standard interconnection point to their facility. In this case Zayo Bandwidth would construct new fiber from an interconnection point to the customers designated premise and deploy equipment at the premise as appropriate for the requested service type. This extension is provided on an Individual Case Basis (ICB) and is dependent on the distance and complexity of the build. | Zayo will provide a customer with the bandwidth subscribed to, e.g. DS3 (45meg), Fast Ethernet (100meg or fractions thereof), etc. Zayo does not limit a customerâ€™s bandwidth up to the subscribed level, but will â€œchokeâ€ the bandwidth once the level is met. Traffic prioritization is not needed, since Zayo is not providing an â€œMPLSâ€ type service. Customers may, at their discretion, elect to run VLANs, traffic shaping or prioritization within the confines of their subscribed to bandwidth. Zayoâ€™s standard Master Service Agreement carries language forbidding customers from using the service for any unlawful act. We do not block customer traffic from any site deemed legal and lawful, but clearly will comply with government sanctions against sites found to be harmful or illegal. Customer may attach any legal device to our service, and we have not prevented customers from doing this at any time. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zayo is in talks with Verizon Wireless and FiberTower for dark fiber in Southwestern Indiana. The number of miles are unknown. | 0 | 0 | 0 | 0 | Pending locations for COâ€™s and New Huts Frontier CO, 711 Popular, Terra Haute, Indiana AT&T CO, 61 North Jefferson, Bloomfield, Indiana Smithville CO, 302 North Walnut, Bloomington, Indiana or AT&T CO 301 Washington, Bloomington, Indiana New Hut 1204 East 6th street, Huntingburg, New Hut between Rockport and Reo AT&T CO, 134 N.W. 6th Street, Evansville, Indiana Frontier CO, 315 North Hart Street, Princeton, Indiana New hut between English and Milltown Level 3 CO, 848 south 8th Street, Louisville, Kentucky Frontier CO in Connersville, Indiana New Hut between Chester and Webster New Hut between North Manchester and Warsaw New Hut in Marriam, Indiana Level3 Hut, 911 Adams, Gary Indiana Us Signal Hut, 3904 Massachusetts Street, Gary, Indiana | 3. Zayo has issued 4 subcontracts under this work. 1 Went to TurnKey for our Environmental Assessment. Zayo then divided the Engineering into 3 sections in order to meet our time line and ensure that we had backup in case one firm began to fall behind. Two of these sections went to small businesses. 1 was another subcontract to TurnKey for Engineering. 1 went to RCG for Engineering. | N/A | Zayo Bandwidth, LLC | 1070 | 0 | 21 | 0 | 3271 | 423 |  | 2388 | 0 | 0 | 7173 | 0. Per our baseline, this will not happen until Q2 of this year. | N/A | TRUE
NT10BIX5570025 | 2011 | 67394 | This is slightly higher than our baseline, based on route changes and additional EA and Engineering work. | 0 | N/A | 0 | N/A | 10Gbps | This matches our baseline. | 0 | N/A | 1Gbps | This matches our baseline. | 0 | N/A | 1 Gbps based on customers that are currently unserved. | N/A This is a middle mile project. | Zayo's standard policies. Zayo has never blocked customers from accessing any lawful content, service, service provider or application. Zayo has never prevented any consumers from attaching any legal device to our network. | N/A This is a middle mile project. | 818 | 355 | 55 | 408 | 355 | 55 | 408 | 0 | 0 | 0 | 0 | 0 | Zayo will have collocation space, but we have not provided it yet. We are currently purchasing huts and ISP equipment. | Turnkey Network Solutions is a small business and did our EA work and some of our engineering. Gray and Pape is a small woman owned business and doing our Archeological work. JDH is a small business doing some of our engineering. (Engineering was divided up and bid out in segments because of the size of the project). Mitchell is a small business providing strand. Eustis Cable is a small woman owned business doing some construction for us. Baseline NXC is a small business doing some construction for us. White Mountain is a small veteran owned business doing splicing for us. | Zayo's biggest challenge has been dealing with pole providers and permitting agencies. We have had to tell them that we are willing to bypass them and go underground if we cannot reach agreement and agree to pricing. When we explain our deadline and our willingness to seek other solutions, we have found the pole providers and permitting agencies much easier to work with. | Zayo Bandwidth, LLC | 1070 | 0 | 21 | 0 | 3271 | 423 |  | 2388 | 0 | 0 | 7173 | 0 Currently entered into. Zayo is currently negotiating 30 agreements. Zayo has not denied any request. | 0 Currently entered into. Zayo is not currently negotiating any and Zayo has not denied any request. | TRUE
NT10BIX5570026 | 2010 | Unknown | Construction is just beginning, therefore the cost is unknown at this time. | n/a | Middle mile project | n/a | Middle mile project | Unknown | Service is not yet available | n/a | Middle mile project | Unknown | No service is available yet | n/a | Middle mile project | No service has been provided. | No service has been provided. | A. Policies are currently under development. B. No. | No service has been provided. | 81600 | 0 | 0 | 0 | 6800 | 0 | 74800 | KINBER is not currently providing dark fiber services. | 0 | 0 | 0 | 0 | KINBER plans to enter into member agreements to provide collocation space at service and access nodes along the network. Other network providers and/or customers will interconnect with KINBER's network by working with KINBER engineers who will, in turn, work with the member hosting the site. | None. | None at this time. | Keystone Initiative For Network Based Education and Research | 501 | 155 | 14 | 125 | 250 | 630 |  | 625 | 20 | 0 | 2320 | n/a | n/a | TRUE
NT10BIX5570026 | 2011 | Unknown | Construction is underway. No services are being provided at this time. | n/a | This is a middle mile project. | n/a | This is a middle mile project. | n/a | Construction is underway. No services are being provided at this time. | n/a | This is a middle mile project. | Unkknown | Construction is underway. No services are being provided at this time. | n/a | This is a middle mile project. | Construction is underway. No services are being provided at this time. | Construction is underway. No services are being provided at this time. | A. Policies are currently under development. B. No. | n/a | 77520 | 0 | 0 | 0 | 0 | 0 | 77520 | None at this time. | 0 | 0 | 0 | 0 | KINBER plans to enter into member agreements to provide collocation space at service and access nodes along the network. Other network providers and/or customers will interconnect to the network by working with KINBER engineers. No space has been contracted at this time. KINBER also plans to connect to other network providers at Alleghany Center Mall in Pittsburgh and 401 N. Broad Street in Philadelphia. | n/a | Communication and transparency are very important to get broad public buy-in. KINBER is planning a Network member day event that is being very well received by the community. Since many people have question about the project and its eventual impact in Pennsylvania; we have also launched a website with weekly updates on the progress of the network construction, maps and other data that is of interest to the public. | Keystone Initiative For Network Based Education and Research | 501 | 155 | 14 | 125 | 250 | 630 |  | 625 | 20 | 0 | 2320 | n/a | n/a | TRUE
NT10BIX5570026 | 2012 | $75,833 | Construction is still underway on the network, so this figure represents the total construction cost to date (approx. $109M) divided by miles to date of 1437. This figure is slightly higher than expected due the construction not being complete. | n/a | This is a middle mile project, not last mile. | n/a | This is a middle mile project, not last mile. | 10G | Speed is as described in baseline. | n/a | This is a middle mile project, not last mile. | 1G | Speed is as described in baseline. | n/a | This is a middle mile project, not last mile. | To date, four CAIs have received improved broadband access. Their speed increases vary from 10X (100Mbps to 1,000Mbps to 200X (50Mbps to 10,000Mbps). With an average increase of 60X. | Proposed FY2013 prices for on-net services to members : Dark Fiber $700 per strand mile 1G Ethernet Port $1650 10G Ethernet Port $5,000 100M Ethernet Port $2,000 1G Ethernet Point-to-point $5,000 10G Ethernet Point -to-point $15,000 10G Lambda point-to-point $15,000 Commodity Internet $3 per Mbps | No policies are in place at this time other than acceptable use policies. KINBER has never blocked or limited a consumer from accessing content or service. | 0 | 77424 | 2874 | 34488 | 31614 | 352 | 4224 | 3872 | KINBER is not a provider of wholesale fiber. KINBER has made 24 strands available to IRU. | 0 | 0 | 0 | 0 | KINBER does not own any facilities or co-location space. Instead, it has entered into agreements with the CAIs connected to the network. | n/a | We have found that strong partnerships and good communication have been the best tools to make this project a success. Keeping our program officer, local government, and the public updated on our project has been very helpful in dealing with any questions that have come up about what we are doing and how it can benefit the Commonwealth. Engaging the appropriate professionals (staff, legal counsel, auditors) and ensuring detailed documentation have also allowed us to be successful. | Keystone Initiative For Network Based Education and Research | 501 | 155 | 14 | 125 | 250 | 630 |  | 625 | 20 | 0 | 2320 | KINBER has entered into an interconnection agreement with Cogent, a commercial internet provider. We have not been approached by any other providers. | n/a | TRUE
NT10BIX5570026 | 2013 | $65,083 | This figure represents 1612 miles of 48 strands of fiber (77,376 strand miles) which is a decrease from the originally proposed 1696 miles. This decrease was a result of changing construction contractors, an expedited construction schedule and a route change due to potential overlap with another BTOP funded project, Zito Media in the Northwestern corner of Pennsylvania. Although the route changed, we did not lose any CAIs. | n/a | This is a middle mile project. | n/a | This is a middle mile project. | 10G | As described in the baseline. | n/a | This is a middle mile project. | 1G | As described in the baseline. | n/a | This is a middle mile project. | To date, 7 CAIS have received improved broadband access. Their speed increases vary from 10X (from 100Mbps to 1,000MBps) to 200X (50Mbps to 10,000MBps). | Current pricing to on-net members is below. Non-members pay an additional 10%. 1G Ethernet Port Connection $1,650 10G Ethernet Port Connection $5,000 Point to Point Services 100M Ethernet $2,000 1G Ethernet $5,000 10 Ethernet $15,000 10G Lambda $5,000 Commodity Internet $3.00 per Mbps Dark Fiber $700 per strand mile | No policies are in place at this time other than an acceptable use policy. KINBER is working on developing and adopting model policies for network management. KINBER has never blocked or limited a consumer from accessing content or service. | 0. We haven't experienced anyone dropping service. | 77376 | 3224 | 38688 | 35464 | 0 | 0 | 0 | KINBER is not a wholesale provider of fiber. KINBER has made 24 strands available through an IRU. | 0 | 0 | 0 | 0 | KINBER does not own any facilities or collocation space. Instead, we have entered into agreements for space with CAIs connected to the network. | n/a | Communication with all stakeholders has been the most important lesson learned. KINBER continues to work to build its brand awareness within Pennsylvania through marketing efforts, gatherings and outreach activities. We are learning not to concentrate on the technology but on the outcomes it can facilitate. Of course, excellent record keeping and transparency help to answer any questions raised and facilitate a positive audit experience. The importance of sustainability planning, especially for new organizations, cannot be overstated. | Keystone Initiative For Network Based Education and Research | 501 | 155 | 14 | 125 | 250 | 630 |  | 625 | 20 | 0 | 2320 | KINBER has entered into an interconnection agreement with Cogent, a commercial Internet provider. | KINBER has not entered into any peering or transit agreements. | TRUE
NT10BIX5570027 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR-Plateau does not and has not ever blocked our users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR-Plateau operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available to us. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to our customers, we have employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, however due to the increased demand for bandwidth; the DPI system will be brought back online in 2011 with the intention of prioritizing certain applications over others on our wireless access networks only. In managing our network through traffic prioritization, we intend to give a lower priority to peer to peer file sharing traffic and other traffic that does not noticeably impair our customer experience. Though a lower priority will be given to certain applicati | N/A | 8250 | 0 | 0 | 0 | 0 | 0 | 8250 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | E.N.M.R. Telephone Cooperative | 51 | 6 | 4 | 17 | 30 | 22 |  | 106 | 33 | 0 | 269 | ENMR-Plateau has 3 interconnection agreements in place prior to this reporting period. No new interconnection agreements have been entered into in this reporting period and no agreements are being negotiated at this time. ENMR-Plateau has not denied any requests for interconnection during this reporting period. | ENMR-Plateau is currently providing peering services to the University of New Mexico and in negotiations with New Mexico State University. ENMR-Plateau has not denied any requests for peering or transit during this reporting period. | TRUE
NT10BIX5570027 | 2011 | $82,773.87 | Positive variance. Total cost of construction divided by the number of fiber miles constructed as of 12/31/11. | 0 | N/A | 0 | N/A | 1Gb | The maximum broadband speed advertised by ENMR-Plateau is 1Gb. | 0 | N/A | 1Gb | As of the end of the reporting period the average broadband speed provided by ENMR-Plateau is 1Gb to the 23 Roswell Independent School District CAI locations. | 0 | N/A | As of 12/29/2011 ENMR-Plateau activated 23 CAI (schools k-12) locations providing 1Gb broadband service to each. 19 of the CAI locations were previously utilizing dual T-1 services comprising of broadband speeds of 3Mb to each location, four of the CAI locations were previously utilizing 1Gb broadband service from ENMR-Plateau. Therefore the average increase in broadband speed provided to the 23 CAI locations as a result of the project is 824Mb per location. | Long Haul Special Access services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access services which are typically Ethernet services from the local Interconnection point to the anchor institution. | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR-Plateau does not and has not ever blocked our users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR-Plateau operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available to us. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to our customers, we have employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, reinstated again in 2011 for approximately five months and then discontinued again around November of 2011. At this time ENMR-Plateau does not prioritize any network traffic and at no time will we block access to any lawful content, service, service provider, or application. | N/A | 8271 | 43 | 0 | 0 | 8228 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Interconnection with other network providers requires a physical fiber meet at one of Plateauâ€™s Points of Interconnection. The connecting entity would establish a fiber splice meet-point adjacent to Plateauâ€™s POI building. This fiber splice would connect the network providerâ€™s fiber to Plateauâ€™s single-mode fiber entering the building and terminating on Plateauâ€™s optical equipment. This enables optical level interconnection between the other network providerâ€™s optical equipment and Plateauâ€™s. Interconnections with customers of Plateauâ€™s services are established via direct last mile fiber connections terminating at the customer premise. | N/A | N/A | E.N.M.R. Telephone Cooperative | 51 | 6 | 4 | 17 | 30 | 22 |  | 106 | 33 | 0 | 269 | (1) ENMR-Plateau has entered into 3 new interconnection agreements this annual reporting period, (2) ENMR-Plateau is currently negotiating 1 new agreement, (3) ENMR-Plateau has not denied any requests for interconnection during this reporting period. | N/A | TRUE
NT10BIX5570027 | 2012 | $90,163.66 | Total cost of construction divided by the number of fiber miles constructed as of 12/31/12. Includes fiber cable, vaults, etc. and labor of outside plant construction contractor. | 0 | N/A | 0 | N/A | 1Gb | The maximum broadband speed advertised by ENMR Telephone Cooperative is 1Gb. | 0 | N/A | 557Mb | As of the end of the reporting period the average broadband speed provided by ENMR-Plateau and subrecipients is 557Mb to CAI locations. This average includes a 10Gb connection to UNM. | 0 | N/A | As of 12/31/12 ENMR-Plateau and Baca Valley Telephone have activated 60 CAI locations. The following is a breakdown of the number of anchor instutions for each speed tier: 1.5Mb (1), 3Mb (4), 5Mb (11), 8Mb (7), 10Mb (4), 20Mb (7), 40Mb (1), 100Mb (1), 1Gb (23), 10Gb (1). Out of the 60 CAI locations that ENMR and Baca Valley are providing services to, as of 12/31/12, we were able to determine the previous broadband speeds of 48 of those locations. We calculated an average current broadband speed of 486Mb and an average previous broadband speed of 67Mb, which results in an average increase in broadband speed of 419 per CAI location as a result of the BTOP award. | Long Haul Special Access services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access services which are typically Ethernet services from the local Interconnection point to the anchor institution. | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR Telephone Cooperative does not and has not ever blocked users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR Telephone Cooperative operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to its customers, ENMR Telephone Cooperative has employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, reinstated again in 2011 for approximately five months and then discontinued again around November of 2011. ENMR reinstated the use of DPI rate shaping to limit peer to peer traffic only on the wireless internet product MMDS on July 13, 2012. | N/A | 8271 | 8271 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Interconnection with other network providers requires a physical fiber meet at one of ENMR's Points of Interconnection. The connecting entity would establish a fiber splice meet-point adjacent to ENMR's POI building. This fiber splice would connect the network provider's fiber to ENMR's single-mode fiber entering the building and terminating on ENMR's optical equipment. This enables optical level interconnection between the other network provider's optical equipment and ENMR's. Interconnections with customers of ENMR's services are established via direct last mile fiber connections terminating at the customer premise. | N/A | N/A | E.N.M.R. Telephone Cooperative | 51 | 6 | 4 | 17 | 30 | 22 |  | 106 | 33 | 0 | 269 | (1) ENMR Telephone Cooperative has entered into 1 new interconnection agreements this annual reporting period with Conterra Ultra Broadband, (2) ENMR Telephone Cooperative is currently negotiating 1 new agreement, (3) ENMR Telephone Cooperative has not denied any requests for interconnection during this reporting period. | N/A | TRUE
NT10BIX5570027 | 2013 | $94,363.99 | Total cost of construction divided by the number of fiber miles constructed as of 1/31/13. Includes fiber cable, vaults, etc. and labor of outside plant construction contractor. Slightly higher than last reporting period due to final invoicing being paid in the interim. | 0 | N/A | 0 | N/A | 1Gb | The maximum speed advertised by ENMR Telephone Cooperative is 1Gb. | 0 | N/A | 557Mb | As of the end of the reporting period the average broadband speed provided by ENMR Telephone Cooperative and subrecipients is 557Mb to CAI locations. This average includes a 10Gb connection to UNM. | 0 | N/A | As of 1/31/13 ENMR Telephone Cooperative and Baca Valley Telephone Company have activated 60 CAI locations. The following is a breakdown of the number of anchor institutions for each speed tier: 1.5Mb (1), 3Mb (4), 5Mb (11), 8Mb (7), 10Mb (4), 20Mb (7), 40Mb (1), 100Mb (1), 1Gb (23), 10Gb (1). Out of the 60 CAI locations that ENMR and Baca Valley are providing service to, as of 1/31/13, we were able to determine the previous broadband speeds of 48 of those locations. We calculated an average current broadband speed of 486Mb and an average previous broadband speed of 67Mb, which results in an average increase in broadband speed of 419Mb per CAI location as a result of the BTOP award. | Long Haul Special Access services which are typically point to point Ethernet services from Interconnection Point to Interconnection Point; Local Access services which are typically Ethernet services from the local interconnection point to the anchor institution. | A. All Internet services provided over our BTOP project network will be best effort and no Internet traffic will be prioritized over any other Internet traffic. B. ENMR Telephone Cooperative does not and has not ever blocked users from accessing lawful content, service, service provider, or application, or prevented any consumer from attaching any legal devices to our network. ENMR Telephone Cooperative operates a wireless broadband technology that provides a limited amount of bandwidth within a given sector, based on the amount of licensed spectrum available. As a result, all of the bandwidth within this wireless sector is shared among a varying number of broadband subscribers on an oversubscription basis. In order to manage this finite amount of bandwidth and provide an acceptable level of service to its customers, ENMR Telephone Cooperative has employed a deep packet inspection (DPI) device to limit the amount that can be used for bandwidth intensive applications like peer to peer file sharing. The use of this DPI system was discontinued in 2007, reinstated again in 2011 for approximately five months and then discontinued again around November of 2011. ENMR reinstated the use of DPI rate shaping to limit peer to peer traffic only on the wireless internet product MMDS on July 13, 2012. | N/A | 8271 | 8271 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Interconnection with other network providers requires a physical fiber meet at one of ENMR's Points of Interconnection. The connecting entity would establish a fiber splice meet-point adjacent to ENMR's POI building. This fiber splice would connect the network provider's fiber to ENMR's single-mode fiber entering the building and terminating on ENMR's optical equipment. This enables optical level interconnection between the other network provider's optical equipment and ENMR's. Interconnections with customers of ENMR's services are established via direct last mile fiber connections terminating at the customer premise. | N/A | N/A | E.N.M.R. Telephone Cooperative | 51 | 6 | 4 | 17 | 30 | 22 |  | 106 | 33 | 0 | 269 | (1) ENMR Telephone Cooperative has entered into 3 new interconnection agreements this annual reporting period with Verizon Wireless, North Central NM Economic Development and Northern New Mexico Telecom, (2) ENMR Telephone Cooperative is currently negotiating no new agreements, (3) ENMR Telephone Cooperative has not denied any requests for interconnection during this reporting period | N/A | TRUE
NT10BIX5570028 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 406 | 0 | 3506 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Administration, Wisconsin Department of | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | N/A | N/A | TRUE
NT10BIX5570029 | 2010 | 0 | N/A - Delay in securing primary vendor contract because during the fourth quarter our vendor was in the process of undergoing an acquisition and that significantly affected their ability to negotiate or enter into new service contracts. | 0 | N/A, Middle Mile Project | 0 | N/A, Middle Mile Project | 0 | N/A - Delay in securing primary vendor contract because during the fourth quarter our vendor was in the process of undergoing an acquisition and that significantly affected their ability to negotiate or enter into new service contracts. | 0 | N/A, Middle Mile Project | 0 | N/A - Delay in securing primary vendor contract because during the fourth quarter our vendor was in the process of undergoing an acquisition and that significantly affected their ability to negotiate or enter into new service contracts. | 0 | N/A, Middle Mile Project | N/A | N/A, Middle Mile Project | N/A | N/A | 1120 | 0 | 0 | 0 | 1120 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | All points of interconnection between the proposed Middle Mile network are either at the indicated Community Anchor Institutions of by direct negotiation with interested Last Mile providers. | N/A | None at this time. | Education Networks of America, Inc. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | N/A | N/A | TRUE
NT10BIX5570029 | 2011 | 0 | Grant termination due to unforeseen changes in the end-user market within our PFSAs. | 0 | N/A, Middle Mile Project | 0 | N/A, Middle Mile Project | 0 | Grant termination due to unforeseen changes in the end-user market within our PFSAs. | 0 | N/A, Middle Mile Project | 0 | Grant termination due to unforeseen changes in the end-user market within our PFSAs. | 0 | N/A, Middle Mile Project | N/A | N/A. Middle Mile Project | N/A. Grant terminated. | N/A. Grant terminated. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A. Grant terminated. | N/A. Grant terminated. | N/A Grant terminated. | Education Networks of America, Inc. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | N/A | N/A | TRUE
NT10BIX5570030 | 2010 | 0 | Deployment is not complete for any parts of the network. | 0 | N/A | 0 | N/A | 1Gb | This is the maximum speed to be offered by the one last mile provider with which we have an agreement. (TBCNet) | 0 | N/A | 0 | Deployment is not complete for any parts of the network. | 0 | N/A | N/A Deployment is not complete for any parts of the network. | N/A Deployment is not complete for any parts of the network. | N/A Our project is middle mile. | N/A Deployment is not complete for any parts of the network. | 6240 | 0 | 0 | 0 | 520 | 0 | 5720 | N/A Deployment is not complete for any parts of the network. | 0 | 0 | 0 | 0 | Customers and/or network providers connect either at Community Anchor Institutions or hand hole locations along the route. | DeKalb Fiber Optic, LLC has awarded two supplier contracts to Women's Business Enterprises. Those are B and C Distribution dba R-BOC Representatives and KGP Telecommunications, Inc. | DeKalb County has been working collaboratively together with the Northern Illinois University (NIU) BTOP finding project by collaborating weekly on strategic interconnections between the networks and their methodology. NIU has regular correspondence with the IBOP-EC project to assure that the Illinois Century Network interconnection points as successfully executed for delivery of content to ICN constituents. The synergies between DeKalb County and the IBOP-EC are in process by regular e-mails, phone or in person meetings. DeKalb County has been working with the Partnership for Connected Illinois (PCI) on developing the necessary information and processes to meet their goals. DeKalb County plans to attend the seminars presented by PCI for the State of Illinois BTOP grantees to understand further the requirements of PCI. For future BTOP project applicants, we recommend keeping in regular communication with proposed Community Anchor Institutions during the application, due diligence, award, and environmental assessment periods. We are finding that entities previously interested in being a community anchor in our project have accessed other providers of high speed internet or constructed their own high speed infrastructure in the lag time between initial contact and actual build of the system. | De Kalb, County of (Inc.) | 38 | 13 | 1 | 4 | 8 | 7 |  | 24 | 1 | 1 | 97 | 1) None entered into. 2 )None are currently being negotiated. However, we expect to have interconnection agreements with Northern Illinois University and several school districts that have multiple schools on the system. 3) None denied. | 1) None entered into 2) None currently being negotiated. However, we may have peering agreements eventually with other BTOP projects and non-BTOP-funded projects in the northern Illinois area. 3) None denied. | TRUE
NT10BIX5570030 | 2011 | $90,077 | 4.09 miles in service @ total cost of $368,414. This is the same cost as we provided in our application and upon which the construction budget is based. | 0 | N/A | 0 | N/A | 10Gb | Available within networks, rings and dark fiber. | 0 | N/A | 683Mb | Two customers (three locations) active for which our project is not the ISP for eany. Project is providing transport only at 50Mb for one and other has two locations running at 1 Gb. 50+1000+1000= 2050/3= .683 Gb | 0 | N/A | For the three connections mentioned in Q1, two were using a wireless connection @ 20Mb and was increased to 1 Gb (increase of 980 Mb). The third connection was using a wireless connection @ 768 Kb and was increased to 50Mb (increase of 49.232Mb). 2 x 980Mb + 49.232Mb= 2,009.232 / 3 = average increase in speed of 669.744 Mb. | None | Network policies based on port speed system will use protocols PPB-TE and IEEE 802.1Q with IP for prioritizing network traffic. | None | 19034 | 8 | 5717 | 6525 | 1790 | 3203 | 1791 | DeKalb Fiber Optics. LLC is being provided, via IRU, 68 strands of fiber throughout the system for economic development purposes. Dekalb Fiber Optics has, in turn, has to-date subleased more than 45 strand miles for economic development including providing service to an underserved community wireless network previously providing service to approximately 35 residents via a 3Mbps connection. The new connection is running at 50 Mbps, more than a 16 fold increase in speed. | 0 | 0 | 0 | 0 | The project has access to collocation rack space in four telephone central offices and has a presence in the Northern Illinois University Network Operations Center and indirectly in the Northern Illinois University Central Office. In addition, interconnection also can be provided at any of more than 300 hand holes provided as a part of the project. | None by the recipient. Sub-Awards have been made by the contractor, DeKalb Fiber Optics, to two Women's Business Enterprises: 1) B and C Distribution dba R-BOC Representatives and KGP Telecommunications, Inc. | All duct used in the project contains multiple sub-ducts that allow additional cable to be installed in the future of needs dictate with minimal ground disturbance. | De Kalb, County of (Inc.) | 38 | 13 | 1 | 4 | 8 | 7 |  | 24 | 1 | 1 | 97 | 1. None entered into. 2. We are in discussions with four ISP's to provide service over the BTOP funded network 3. We have not denied any requests for interconnection. | 1. Entered into peering agreement with DNA Communications for collocation space in four telephone central offices. 2. Currently negotiating agreement with Northern Illinois University for peering location at Network Operation Center. Draft agreement is currently in University administrative review process. 3. We have not denied any requests for interconnection. | TRUE
NT10BIX5570030 | 2012 | $90,077 | 596,672 feet of new construction completed as of December 31, 2012 at cost of $10,179,247. This is the same cost provided in our application and upon which the construction was based. | 0 | N/A | 0 | N/A | 10Gb | Available within networks, rings and dark fiber. | 0 | N/A | 943Mb | Of 61 connections, 52 are lit. 47 are at 1 Gbps, 3 are at 50 Mbps and two are dark fiber. ([47*1000] + [3*50]) = 47,150/ 50 = 947 Mbps | 0 | N/A | The average speed increase for the lit connections is 916 Mbps. This was calculated by obtaining the pre-project broadband speeds for each Community Anchor Institution and subtracting that speed from the new connection speed. The results were totalled and averaged. New connections and dark fiber connections were omitted from the calculations. | None | Network policies based on port speed system will use protocols PPB-TE and IEEE 802.1Q with IP for prioritizing network traffic. | None | 18661 | 553 | 8592 | 9194 | 72 | 322 | 146 | DeKalb Fiber Optics, LLC is being provided, via IRU, 68 strands of fiber throughout the system for economic development purposes. This amounts to 8,624 of the strand miles built to-date. DFO has subleased 2 strands across the majority of the network to a carrier providing LTE upgrades in fiber-to-the-cell, resulting in expanded mobile broadband access. DFO has contracted with a number of financial institutions to utilize the leased fiber to provide upgraded connectivity. DFO and their providers are rolling out broadband service to agricultural businesses throughout the region at speeds in excess of 300 Mbps. | 0 | 0 | 0 | 0 | The project has access to collocation rack space in four telephone central offices and has a presence in Northern Illinois University Network Operations Center and indirectly at Northern Illinois University Central Telephone Office. In addition, interconnection can be provided at any of the 291 hand holes currently deployed. The project also has interconnection agreements with the Northwest Illinois BTOP project (iFiber) for two additional interconnection points, extending interconnection potential for the DATA project to network providers and/or customers at locations throughout the six northwest Illinois counties as well as the DeKalb County area. | None by the recipient. Sub-awards have been made by the Contractor, DeKalb Fiber Optics, to two Women's Business Enterprises: 1)B and C Distribution dba R-BOC Representatives and 2) KGP Communications, Inc. | The County engaged an independent engineer to verify all footages billed by the contractor for the project and to confirm the placement of all hand holes. The project used duct containing multiple sub-ducts, allowing for additional cable to be installed in the future if needed with minimal ground disturbance. | De Kalb, County of (Inc.) | 38 | 13 | 1 | 4 | 8 | 7 |  | 24 | 1 | 1 | 97 | 1. Five entered into during this reporting period, 2. Three are in current negotiations, 3. We have not denied any interconnection requests. | No peering agreements entered into during reporting period. Transit agreements: 1. Three entered into during this reporting period. 2. One in current negotiations 3. We have not denied any interconnection requests. | TRUE
NT10BIX5570030 | 2013 | $90,077 | 597,196 feet of new construction completed as of end of 2013 at a cost of $10,201,061. This is the same cost provided in our application and baseline report. | 0 | N/A | 0 | N/A | 10Gbps | Available within networks, rings and dark fiber. | 0 | N/A | 897Mbps | Of 78 total connections, 64 are lit, 3 are connected via dark fiber and 11 did not elect service as of this time. Of the 64 lit connections, 57 are at 1Gb, 1 is at 100 Mbps and 6 are at 50 Mbps. ([57*1000] + [6*50] + [1*100]/64=897Mbps. | 0 | N/A | The average speed increase for the lit connections is 843Mbps. This was calculated by obtaining the pre-project broadband speeds for each Community Anchor Institution and subtracting that speed from the new, post-project connection speed. The result was totaled and averaged. New connections and dark fiber connections were omitted from the calculations. | None | a)Network policies are based on port speed system with use protocols PPB-TE and IEEE 802 1Q with IP for prioritizing network traffic. The DeKalb County Network is a layer 2 designed network providing for Metro Ethernet connectivity. Three classes of priorities have been defined in the network based on off ELAN classes of traffic. The three levels of traffic are 1) E-911 Services, 2) ISP Services and 3) Cloud (intranet) Traffic. The highest level of priority is given to the E-911 services with the next level to ISP services and the lowest to the intranet cloud traffic. The system is open to all lawful content and types of traffic. b) We have not limited or blocked consumers from accessing any lawful content, service, service provider, or application or prevented any consumers from attaching any legal device to the network. | None | 18132 | 1574 | 8354 | 8204 | 0 | 0 | 0 | DeKalb Fiber Optics, LLC is being provided, via IRU, with 68 strands of fiber throughout the newly constructed network for economic development purposes. This amounts to 8,354 of the strand miles built by the project. This number is less than we reported last year. When we audited the entire build in preparing the 2013 annual report we discovered we erroneously counted fiber in pin point duct for service lateral as 144 fibers when, in fact, only 12 fibers were installed in pin point for the most part and none of the fibers in the pin point has been allocated to DeKalb Fiber Optic, LLC for economic development. This adjustment also lowered the Total Strand-mile metric as compared to last year. Of the 68 fibers allocated to DFO: - 2 strands has been subleased across the majority of the network to a carrier providing LTE upgrades in fiber-to-the-cell resulting in expanded mobile broadband access. - a number of financial institutions, especially in rural areas of the county, have leased fiber to provide increased connectivity to existing and new facilities. - broadband services to agricultural businesses throughout the region is being rolled out by DFO and its providers. Speeds are in excess of 300 Mbps. - broadband services to residential areas, especially in rural areas of the county, is being improved as DFO has provided increased connectivity to cable tv providers. | 0 | 0 | 0 | 0 | The project has access to collocation rack space in four telephone central offices and has a presence in Northern Illinois University Network Operations Center and at Northern Illinois University Central Telephone Office. In addition, interconnection can be provided at any of the 291 hand holes through which owed and leased fiber passes. The project also has interconnection agreements with the Northwest Illinois BTOP project (iFiber) for two additional interconnection points, extending interconnection potential for the DATA project to network providers and/or customers at locations throughout the six northwest Illinois counties as well as the DeKalb County area. | None by the recipient. Sub-awards have been made by the Contractor, DeKalb Fiber Optics, to two Women's Business Enterprises: 1)B and C Distribution dba R-BOC Representatives and 2) KGP Communications, Inc. | The County engaged an independent engineer to verify all footages billed by the contractor for the project and to confirm the placement of all hand holes. The project used duct containing multiple sub-ducts, allowing for additional cable to be installed in the future if needed with minimal ground disturbance. | De Kalb, County of (Inc.) | 38 | 13 | 1 | 4 | 8 | 7 |  | 24 | 1 | 1 | 97 | 1. Three entered into during 2013. 2. None are currently being negotiated 3. We have not denied any interconnection requests. | No peering agreements entered into during 2013. Transit Agreements: 1. One entered into during 2013. 2. None in current negotiations. 3. We have not denied any interconnection agreements. | TRUE
NT10BIX5570031 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 47088 | 0 | 37632 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | The most monumental lesson learned related to the WV BTOP grant is that of the Environmental Assessment process. Because of the scope, complexity, and geography of our project, this was a monumental task. Recommendation: Start this process early and have a â€œteamâ€ dedicated solely to this aspect of the overall environmental effort. Another lesson learned is that of planning teams. Shortly into the planning and engineering the magnitude of the effort surfaced. We were a bit slow to induce planning and engineer teams into the process. After we originated these teams and implemented their operation, the entire process gained momentum. Recommendation: Begin with all engineers, planners, and stakeholders involved. | Executive Office State of West Virginia | 718 | 176 | 17 | 19 | 392 | 863 |  | 1 | 20 | 0 | 2206 | (1) N/A (2) Interconnect -2 Peering - 0 Transit - 1 (3) N/A | N/A | TRUE
NT10BIX5570031 | 2011 | 50,000 | Baseline shows 17,000. This price has been on the rise since the Hurricane in Japan. The lack of sources to buy Fiber has driven the cost up as well. | N/A | N/A | N/A | N/A | 50 MEG | As noted in baseline | N/A | N/A | 10 MEG | As noted in baseline | N/A | N/A | Copper facilities have been at the heart of telecommunications for many years. Itâ€™s a testament to the ingenuity of telco engineers that its data capacity has been pushed to DSL2 speeds up to 45 Mbps on an average, but copper is rapidly reaching its maximum potential. But where copper stops, fiber starts. Fiber gives you a â€œtrue bandwidthâ€ connection. If you buy a 10Mbit/s EPL connection, for example, 10Mbit/s is exactly what youâ€™ll get, 24/7. It doesnâ€™t matter how far away from the exchange you are, or how busy the network becomes - youâ€™ll be getting a rock-steady 10Mbit/s in both directions. Based on upgrading data communication lines with fiber as part of our BTOP initiative, we can now achieve data speeds of 100 Megabit Ethernet, Gigabit Ethernet, OC3 (155 Mbps), OC12 (622 Mbps), and OC48 (2.5 Gbps) if required. | This WV BTOP grant does not provide any retail services. The fiber is placed at the Community Anchor Institute with termination points and interconnect points established for the customer to order services from multiple potential vendors. The BTOP fiber is classified as "dark fiber". It is up to the individual CAI location as to the service provider they wish to use, as well as the type of service they wish to order. | 7a. N/A 7b. N/A | The Project is under the initial activation phase customers are currently just beginning to sign up with carrier for enhanced Broadband service to date there has been no one removed from the new served areas. This in time may change but as of 12-31-11 this metric in not applicable. | 99585 | 0 | 0 | 20962 | 849603144 | 7862 | 39312 | We are currently negotiating one interconnect agreement with CityNet West Virginia LLC. Frontier is still awaiting the amount of fiber strands that CityNet wishes to utilize, but the total mileage of that agreement will 0.19 miles. | 0 | 0 | 0 | 0 | Frontier Communications does own collocation space. Potential providers can apply for collocation space at the respective Central Office as well connect directly into the BTOP fiber at the existing A to Z locations as defined in the Interconnection Agreement. | We have two subcontracts. One is with Frontier Communications, the other is with Lewis County Commission. | Key learnings for this project have come from the needs of public communication. When dealing with public entities such as K12 and others it has been determined that it is best to provide weekly status reports and long term schedules for fiber roll out. With the development of consistent weekly reporting much of the publics desire for status updates has been satisfied. Additional communication (Monthly Meetings) with CAI points of contact has been a best practice allowing all key questions to be addressed in a group forum and allow CAIs to feel connected to the project and lets them know they are a priority. | Executive Office State of West Virginia | 718 | 176 | 17 | 19 | 392 | 863 |  | 1 | 20 | 0 | 2206 | Frontier Communications is currently finalizing an interconnect agreement with CityNet West Virginia LLC for the Bridgeport Library location. The details of said "in progress" agreement are below. 2.0 BTOP Fiber Meet Point 2.1 All Charges are based on the following in accordance with the Technical Specifications Form: GPS COORDINATES A Location GPS Stop 39.2996 -80.2752 Z Location GPS Start 39.2989 -80.2731 PHYSICAL LOCATION Access to Fiber serving the Bridgeport Public Library 1200 Johnson Avenue, Bridgeport, WV in Harrison County ACCESS The Fiber will be made available at installed splice case at the A Location to Z Location Demarcation Point within the Bridgeport Public Library 2.2 Monthly Recurring Charges Access per Fiber Strand $5.27 Maintenance Cost per Fiber Strand $0.36 Total Fiber Strands Ordered CityNet LLC has yet to advise as to how many strand they wish to order. Frontier Communications has received one other request from the Weirton Area Port Authority. We are in the beginning stages of this request and to this point, it appears their request is in error. They have not requested access to specific BTOP fiber segments. In their initial inquiry, they requested a "co-location" presence within the Weirton Central Office for what they called "access to the BTOP network". This falls outside the guidelines of the BTOP interconnection agreement. We will be having a meeting with representatives from the WAPA, Frontier Carrier Services, Frontier Legal and Engineering to discuss and resolve the issue. At this point, it would appear we will be denying the request as it is written today. We anticipate additional connection points as the grant progresses.The Fiber will be made available at installed splice case at the A Location to Z Location Demarcation Point within the Bridgeport Public Library 2.2 Monthly Recurring Charges Access per Fiber Strand $5.27 Maintenance Cost per Fiber Strand $0.36 Total Fiber Strands Ordered CityNet LLC has yet to advise as to how many strand they wish to order. Frontier Communications has received one other request from the Weirton Area Port Authority. We are in the beginning stages of this request and to this point, it appears their request is in error. They have not requested access to specific BTOP fiber segments. In their initial inquiry, they requested a "co-location" presence within the Weirton Central Office for what they called "access to the BTOP network". This falls outside the guidelines of the BTOP interconnection agreement. We will be having a meeting with representatives from the WAPA, Frontier Carrier Services, Frontier Legal and Engineering to discuss and resolve the issue. At this point, it would appear we will be denying the request as it is written today. We anticipate additional connection points as the grant progresses. | N/A | TRUE
NT10BIX5570031 | 2012 | 47,500 | Although the baseline indicates a cost of $17,000 per mile, the actual cost is at $47,500 per mile. This is a decrease from $50,000 as noted on the 2011 Annual Report. We expect the cost to continue to decrease. However, the storms late in 2012, the environmental considerations, delay on fiber receipts, and other factors continue to cause the per mile cost to be above baseline. | N/A | N/A | N/A | N/A | 50 MEG | The 50 MEG maximum is in keeping with the baseline for the EOWV BTOP grant. | N/A | N/A | 10 MEG | The average speed at 10MEG is in keeping with the baseline for the EOWV BTOP grant. | N/A | N/A | Copper facilities have been at the heart of telecommunications for many years. Itâ€™s a testament to the ingenuity of telco engineers that its data capacity has been pushed to DSL2 speeds up to 45 Mbps on an average, but copper is rapidly reaching its maximum potential. But where copper stops, fiber starts. Fiber gives you a â€œtruer bandwidthâ€ connection. If you buy a 10Mbit/s EPL connection, for example, 10Mbit/s is exactly what youâ€™ll get, 24/7. It doesnâ€™t matter how far away from the exchange you are, or how busy the network becomes - youâ€™ll be getting a reliable approximate 10Mbit/s in both directions. Based on upgrading data communication lines with fiber as part of our BTOP initiative, we can now achieve data speeds of 100 Megabit Ethernet, Gigabit Ethernet, OC3 (155 Mbps), OC12 (622 Mbps), and OC48 (2.5 Gbps) if required. | This WV BTOP grant does not provide any retail services. The fiber is placed at the Community Anchor Institute with termination points and interconnect points established for the customer to order services from multiple potential vendors. The BTOP fiber is classified as "dark fiber". It is up to the individual CAI location as to the service provider they wish to use, as well as the type of service they wish to order. | 7a. N/A 7b. N/A | This project does not offer broadband services. | 91296 | 27388 | 0 | 63908 | 29160 | 0 | 68040 | We are currently negotiating one interconnect agreement with CityNet West Virginia LLC. Frontier is still awaiting the amount of fiber strands that CityNet wishes to utilize, but the total mileage of that agreement will 0.19 miles. | 0 | 0 | 0 | 0 | Frontier Communications does own collocation space. Potential providers can apply for collocation space at the respective Central Office as well connect directly into the BTOP fiber at the existing A to Z locations as defined in the Interconnection Agreement. | We have two subcontracts. One is with Frontier Communications, the other is with Lewis County Commission. | Key learnings for this project have come from the needs of public communication. When dealing with public entities such as K12 and others it has been determined that it is best to provide weekly status reports and long term schedules for fiber roll out. With the development of consistent weekly reporting much of the publics desire for status updates has been satisfied. Additional communication (Monthly Meetings) with CAI points of contact has been a best practice allowing all key questions to be addressed in a group forum and allow CAIs to feel connected to the project and lets them know they are a priority. In retrospect, it would be a positive for all similar grants to begin "outreach" programs at receipt of grant funding. After grant award, the "outreach" should be on-going. A proactive program would serve to minimize many misunderstandings associated with grant actions. We utilized a Point of Contact (POC) approach to disseminate information to the end user. It would have been better had we had more direct approach at the user level at intervals, but maintaining the overall POC approach. The magnitude of the grant, including total funding, differences of major efforts contained within the grant, and varying entities associated would have been better served had we utilized at all levels a single data-base. | Executive Office State of West Virginia | 718 | 176 | 17 | 19 | 392 | 863 |  | 1 | 20 | 0 | 2206 | Frontier Communications is currently finalizing an interconnect agreement with CityNet West Virginia LLC for the Bridgeport Library location. The details of said "in progress" agreement are below. 2.0 BTOP Fiber Meet Point 2.1 All Charges are based on the following in accordance with the Technical Specifications Form: GPS COORDINATES A Location GPS Stop 39.2996 -80.2752 Z Location GPS Start 39.2989 -80.2731 PHYSICAL LOCATION Access to Fiber serving the Bridgeport Public Library 1200 Johnson Avenue, Bridgeport, WV in Harrison County ACCESS The Fiber will be made available at installed splice case at the A Location to Z Location Demarcation Point within the Bridgeport Public Library 2.2 Monthly Recurring Charges Access per Fiber Strand $5.27 Maintenance Cost per Fiber Strand $0.36 Total Fiber Strands Ordered CityNet LLC has yet to advise as to how many strand they wish to order. Frontier Communications has received one other request from the Weirton Area Port Authority. We are in the beginning stages of this request and to this point, it appears their request is in error. They have not requested access to specific BTOP fiber segments. In their initial inquiry, they requested a "co-location" presence within the Weirton Central Office for what they called "access to the BTOP network". This falls outside the guidelines of the BTOP interconnection agreement. We will be having a meeting with representatives from the WAPA, Frontier Carrier Services, Frontier Legal and Engineering to discuss and resolve the issue. At this point, it would appear we will be denying the request as it is written today. We anticipate additional connection points as the grant progresses. | N/A | TRUE
NT10BIX5570031 | 2013 | $57,881/$62,338 | There are 2 calculations for cost per mile. If we remove all FBO and Legal/Audit fees, the cost for building 675 miles of fiber equated to $57,881 per mile. If we include those "non construction" components that include customer premise FBO work, along with Legal and Audit fees, the cost per mile equated to $62,338. Federal regulations dictating Davis-Bacon wages added $7.5 million to the overall cost. Below is a breakdown of our analysis. Restated Totals 1. Remove FBO, Audit & Legal BTOP Invoiced Cost $42,078,450 FBO $2,435,316 Audit & Legal $573,371 X - FBO & Audit $39,069,763 Miles 675 $/Mile $57,881.13 | N/A | N/A | N/A | N/A | 10Gig | The link connecting NRAO/WVU will be provisioned and capable of providing speeds up to 10 Gigabits per second to meet the demands of data transfer between those 2 facilities. | N/A | N/A | 100Meg | Frontier has provisioned and installed over 300 Metro-E circuits for BTOP CAIs since the inception of the BTOP program. The average rate of those circuits is approximately 100 Megabits per second. | N/A | N/A | Copper facilities have been at the heart of telecommunications for many years. Itâ€™s a testament to the ingenuity of telco engineers that its data capacity has been pushed to DSL2 speeds up to 45 Mbps on an average, but copper is rapidly reaching its maximum potential. But where copper stops, fiber starts. Fiber gives you a â€œtruer bandwidthâ€ connection. If you buy a 10Mbit/s EPL connection, for example, 10Mbit/s is exactly what youâ€™ll get, 24/7. It doesnâ€™t matter how far away from the exchange you are, or how busy the network becomes - youâ€™ll be getting a reliable approximate 10Mbit/s in both directions. Based on upgrading data communication lines with fiber as part of our BTOP initiative, we can now achieve data speeds of 100 Megabit Ethernet, Gigabit Ethernet, and even 10 Gigabit Ethernet if required. | This WV BTOP grant does not provide any retail services. The fiber is placed at the Community Anchor Institute with termination points and interconnect points established for the customer to order services from multiple potential vendors. The BTOP fiber is classified as "dark fiber". It is up to the individual CAI location as to the service provider they wish to use, as well as the type of service they wish to order. As stated above, over 300 CAIs have upgraded to MetroE services since the inception of this project. | 7A. There are no bandwidth limitations with this project. As for traffic priority, standard Class of Service (CoS) and Quality of Service (QoS) policies are applied. 7b. N/A | This project does not provide broadband services. However, as stated above, over 300 CAIs have upgraded to MetroE services since the inception of this project. | 95225 | 38090 | 0 | 57135 | 38090 | 0 | 57135 | Dark fiber is available to other carriers at wholesale rates. However, as stated above, there are currently no finalized, signed interconnection agreements. | 0 | 0 | 0 | 0 | Frontier Communications does own collocation space. Potential providers can apply for collocation space at the respective Central Office as well connect directly into the BTOP fiber at the existing A to Z locations as defined in the Interconnection Agreement. | We have two sub grants. One is with Frontier Communications, the other is with Lewis County Commission. | Best practices for this grant remain as stated last year, which is noted below. Key learnings for this project have come from the needs of public communication. When dealing with public entities such as K12 and others it has been determined that it is best to provide weekly status reports and long term schedules for fiber roll out. With the development of consistent weekly reporting much of the publics desire for status updates has been satisfied. Additional communication (Monthly Meetings) with CAI points of contact has been a best practice allowing all key questions to be addressed in a group forum and allow CAIs to feel connected to the project and lets them know they are a priority. In retrospect, it would be a positive for all similar grants to begin "outreach" programs at receipt of grant funding. After grant award, the "outreach" should be on-going. A proactive program would serve to minimize many misunderstandings associated with grant actions. We utilized a Point of Contact (POC) approach to disseminate information to the end user. It would have been better had we had more direct approach at the user level at intervals, but maintaining the overall POC approach. The magnitude of the grant, including total funding, differences of major efforts contained within the grant, and varying entities associated would have been better served had we utilized at all levels a single data-base. | Executive Office State of West Virginia | 718 | 176 | 17 | 19 | 392 | 863 |  | 1 | 20 | 0 | 2206 | Frontier has been contacted by seven carriers seeking information on BTOP facilities, and has entered into detailed negotiations with one carrier. However, there are currently no finalized, signed interconnection agreements. | N/A | TRUE
NT10BIX5570032 | 2010 | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | 0 | NA | No services are being provided yet, so it is not possible to calculate an average increase in speed. | No retail services are being provided at this time. LCOG will contract with retail service providers who will then offer services to the anchor institutions. When those arrangements are made, LCOG will report them. | 7a. No policies are yet in place. The plan is to not have any limitations except as they relate to increased price for greater service. these price structures will be evenly applied. 7b. The contracts that we will negotiate with service providers will have an express prohibition on limiting access. | Not Applicable | 398 | 185 | 295 | 295 | 0 | 3 | 110 | No leases have been made | 1040 | 100 | 0 | 940 | LCOG will be providing collocatoin space. | No subcontracts with socially or economically disadvantaged small businesses have been made thus far. | None at this time. | Lane Council of Government | 48 | 12 | 6 | 6 | 29 | 28 |  | 45 | 40 | 3 | 217 | N/A | N/A | TRUE
NT10BIX5570032 | 2011 | $159,597 | This number was reached by dividing the federal funds spent on engineering and construction by the number of customers connected as of December 31. It is misleading because a great deal has been spent to connect other customers, but these customers have not yet been brought on line. | NA | NA | NA | NA | 55Mbs | This is the speed offered in the promotional advertising for commercial operations by the provider who is currently connected to the most customers. There is no advertising for connections to anchor institutions, because individual arrangements are made. As additional segments become available, speeds will increase. The planned gigabit ethernet segment is not on line yet, so no advertising has been done for this segment. | NA | NA | 10Mbs | It is difficult to discuss an average speed with so few customers currently connected. Initial demand is always lower than what it grows to be within a short time. | NA | NA | Only a few sites have been connected so far. The average increase is approximately 10 Megabits per second, because prior to connection, the sites had no broadband connectivity, and the service provider is providing services at that level. | We are contracting with service providers to provide retail services. The one provider that we have contracted with that is offering services over the fiber constructed by the project thus far is Douglas Fast Net. Douglas Fast Net offers a range of services. The attached service plan describes and provides the prices for these services. The relevant prices for this project are attached. The fiber based services range from 1 to 100 plus megabits. | No services are provided yet, except through contracts with other service providers. By contract the service providers are required to offer services to all on a non-discriminatory open platform. 7b. The service providers are contractually required to provide non-discriminatory services. | No subscribers have dropped service. | 4114 | 0 | 1310 | 1762 | 0 | 521 | 521 | This question is confusing (as is question 9) It presents misleading figures. A number of the fibers that are currently dark will be used by the recipient, but this does not allow that to be reported. | 0 | 0 | 0 | 0 | No collocation space has yet been finished. When completed there will be approximately 200 square feet of collocation space available. Approximately 10 square feet of recipient's owned space will be used by the recipient, and an additional 4 square feet will be leased by recipient. The remaining approximately 190 square feet will be available for other users. | No contracts have been made to socially and economically disadvantaged small businesses. | None. | Lane Council of Government | 48 | 12 | 6 | 6 | 29 | 28 |  | 45 | 40 | 3 | 217 | We have not entered into any interconnection, peering or transit agreements yet. We are negotiating or will soon negotiate six (6) interconnection agreements and five (5) transit agreements. We do not expect to negotiate any peering agreements. We have not denied any requests and will not deny any requests. | We have not entered into any interconnection, peering or transit agreements yet. We are negotiating or will soon negotiate six (6) interconnection agreements and five (5) transit agreements. We do not expect to negotiate any peering agreements. We have not denied any requests and will not deny any requests. | TRUE
NT10BIX5570032 | 2012 | 16785 | This has increased slightly because the number of miles for the project has decreased slightly as we get better estimates of actual distance., | NA | NA | NA | NA | Gigabit | No change from baseline. | NA | NA | 10Meg | I believe that this is the same. This is a average using the projected mode. | NA | NA | The average increase is perhaps 70 Megabits/ second. This is calculated by considering the previous average speed, which was either zero (for most users) or poor DSL, and considering the speed most commonly purchased. | We are not providing retail services. We contract with several retail providers across a three county area. They have varying prices that they offer. | We have no network management policies in place. We have been able to provide more bandwidth than needed by the customers. No customers have been blocked from accessing any content. | NA | 500 | 107 | 393 | 0 | 107 | 0 | 0 | We are leasing as dark fiber all of the constructed strand miles, an estimated 107 miles. | 300 | 6 | 6 | 288 | NA | No sub grants have been made. No subcontracts have been made to SBD concerns. | A successful outreach program will overwhelm you with demand for services from potential customers who may not qualify for service but would still like to get service. | Lane Council of Government | 48 | 12 | 6 | 6 | 29 | 28 |  | 45 | 40 | 3 | 217 | One Agreement has been signed. We are negotiating four additional interconnection agreements. We expect to negotiate an additional five agreements in the next year or so. We have not denied any request for interconnection. | We have not negotiated any peering agreements yet. We hope to do so in the next year. | TRUE
NT10BIX5570032 | 2013 | $16,785 | This has increased slightly as the number of miles has become more accurately measured. | NA | NA | NA | NA | Gigabit | No change from baseline | NA | NA | 10 Meg | Same | NA | NA | The average increase is perhaps 70 Megabits/ second. This is calculated by considering the previous average speed, which was either zero (for most users) or poor DSL, and considering the speed most commonly purchased. | We are not providing retail services. We contract with several retail providers across a three county area. They have varying prices that they offer. | There are no network management policies allowed. Each provider signs an agreement that they will provide an open network, with equal service to all customers. Bandwidth uses are all tiered, and all users pay the same prices for use. | NA | 499 | 104 | 395 | 0 | 104 | 104 | 0 | Coast Com, 8 miles; Douglas Fast Net, 120 miles; Hunter Communications, 31 miles; City of Cottage Grove, 4 miles. Note this adds up to more than the active strand miles because some of the leased fibers are sub-leased. | 300 | 6 | 24 | 270 | NA | NA | None | Lane Council of Government | 48 | 12 | 6 | 6 | 29 | 28 |  | 45 | 40 | 3 | 217 | Five have been signed. | Two agreements have been signed. This was not projected in the baseline report. | TRUE
NT10BIX5570033 | 2010 | 0 | N/A. No variance from baseline. Project in Pre construction stage. | 0 | N/A. No variance from baseline. Project in Pre construction stage. | 0 | N/A. No variance from baseline. Project in Pre construction stage. | 0 | N/A. No variance from baseline. Project in Pre construction stage. | 0 | N/A. No variance from baseline. Project in Pre construction stage. | 0 | N/A. No variance from baseline. Project in Pre construction stage. | 0 | N/A. No variance from baseline. Project in Pre construction stage. | Not Applicable. Project is in Pre-Construction Stage. | Not Applicable. Project is in Pre-Construction Stage. | Not Applicable. Project is in Pre-Construction Stage. | Not Applicable. Project is in Pre-Construction Stage. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Applicable. Project is in Pre-Construction Stage. | 0 | 0 | 0 | 0 | Not Applicable. Project is in Pre-Construction Stage. | We have not made any subcontracts with entities with section 8a definition. Project is in pre-construction stage. | a) Lessons learned. Collection of information on regional public school broadband use. There was no centralized information in the region on what internet capabilities and how broadband was being used in the public school system. We developed a short survey and are conducting on site interviews to develop an information database on the state of the use of broadband in the region. We understand that this will do the following; 1) create a baseline for comparison when the project is implemented, 2) Pinpoint resources in the school system to foment the use of broadband resources, 3) Provide an overall inventory of how the public schools in the rural community are currently using the internet, 4) Create a contact sheet for which the people involved with Broadband in the school system in the region can connect with each other, 5) establish schools which can be highlighted as innovative school implementing broadband programs in an objective form b) The baseline report which we initially submitted was not prepared utilizing cash spent versus project total cash, as the project progress measurement method. The original baseline prepared was based on the planning of activities. A number of planning elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation take a lot preliminary work /time in addition to the time it takes to deliver, install and test the equipment. This effort does not require a big amount of cash disbursement, therefore t he progress made, measured with the cash disbursement method is not recognized. However we have recognized that our project plan needs to reflect the cash disbursement methodology and we will comply with the SAC goal of more than 70% completion of the project, as measured in money drawdownâ€™s , within the initial two year time span of the project and 100% completion in the three years of the project. The lesson learned here is to avoid assuming a methodology and to insure that you understand the requirement. | Iniciativa Tecnologica Centro Oriental (INTECO) | 180 | 10 | 25 | 12 | 26 | 10 |  | 40 | 14 | 13 | 330 | N/A. Project in Pre construction stage. | N/A. Project in Pre construction stage. | TRUE
NT10BIX5570033 | 2011 | 0 | N/A. Project in construction stage | 0 | N/A. Project in construction stage | 0 | N/A. Project in construction stage | 9 mbps | Project in construction stage | N/A | N/A. Middle mile project in construction stage | 5.6 mbps | Project in construction stage | N/A | N/A. Middle mile project in construction stage | Project network is in construction stage. | Not applicable. Project network is in construction stage. | Project network is in construction stage. | Not applicable. Project in construction stage. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is microwave tower based not fiber based. | 0 | 0 | 0 | 0 | Project is in construction stage | We have not made any subcontracts with entities with section 8a Small Business Act definition (SDB - Small Disadvantage Business). | a) Lessons learned. The INTECO project is a tower based microwave project, which needs to develop the towers in the network to be able to service the region and the CAIâ€™s. The network is designed with four loops or quadrants to provide redundancy and improve service levels to customers. To assure that we meet the 67% objective in the first two years, we have developed a strategy that prioritized the activities by focusing on completing two initial loops of the network. In these two quadrants the majority of the towers already exist (14 of the 16 existing towers in the network). We prioritized the preparation and construction in these two quadrants, will install equipment in these towers and complete the construction of the command center (NOC) in the first two years of the project. The initial two quadrants of the network have 14 existing towers, 3 new towers and the command center (CO). The site preparation for these 18 sites and all the equipment for all sites and the command center will be completed or ordered in 2011 which will assure substantial completion of expenditures for the project within the two year requirement. We will also be constructing in these two initial quadrants, three of the eight new towers in the network. We have construction permits for these three towers and completed the RFP process to award construction. By developing this quadrant strategy and prioritizing the site preparation and tower construction, INTECO has established the objective to activate the network and the operations in the these two areas in summer of 2012, ahead of the Grant schedule. We will initiate connection for CAIâ€™s in the third quarter of 2012 in the quadrants which are activated. We have completed interconnection agreements and a wholesale agreement with two providers in the 4th quarter of 2011, as we anticipate the network start-up. b) Lessons learned. Collection of information on regional public school broadband use. There was no centralized information in the region on what internet capabilities and how broadband was being used in the public school system. We developed a short survey and are conducting on site interviews to develop an information database on the state of the use of broadband in the region. We understand that this will do the following; (1) create a baseline for comparison when the project is implemented, (2) Pinpoint resources in the school system to foment the use of broadband resources, (3) Provide an overall inventory of how the public schools in the rural community are currently using the internet, (4) Create a contact sheet for which the people involved with Broadband in the school system in the region can connect with each other, and (5) establish schools which can be highlighted as innovative school implementing broadband programs in an objective form c) This type of project in Broadband infrastructure is driven by three major areas of investment that covers; Telecom Equipment, Construction of Towers & Sites and Site preparation for Towers. These three elements are over 85% of the total cost of the project. They are spent in certain peak periods of time as the equipment and sites are delivered, verified and accepted. The baseline report which we initially submitted did not consider this method. The original baseline was along the planning of activities, not cash flow paid to suppliers. In other words a lot of planning and preliminary work is needed to deliver the ability to install equipment and finish sites. Our project uses existing towers (which require preparation) and new towers being constructed. Elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation occur prior to payments to suppliers and draw downs. The method used for the original baseline analysis does not reflect the time and effort it took for the project management of a complex project as well as the timing of payment to key suppliers. We will comply with the SAC goal of more than 67% completion of the project, as measured in money drawdownâ€™s , within the initial two year time span of the project and 100% completion in the three years of the project. d) Major activities and tasks of INTECO project completed by December 2011; 1) Sites Surveys and Network Design verification and confirmation, the sites in the network were submitted to the EA process Did a RFP (request for proposal) to select entity to do Environmental Assessment (EA). Completed EA, submitted and (FONSI) received from NTIA. 2) In first two years INTECO has prepared five additional Requests for Proposal (RFP) processes, four RFPâ€™s were completed in 2011 (proposals received, evaluated and awarded, contracts established). RFP for construction of three towers will be completed in first quarter 2012. [a] RFP 1 - Construction Permits contract, submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency for the construction of eight new telecommunications towers to be used by the network in underserved areas. Approval received for four sites in 2011. Work continues on three additional sites which we expect to receive in 2012. [b] RFP 2 - Site prep and construction on exiting tower Sites, For preparation of existing tower sites, construction of pads, ice bridge, electrical connection. 10 of 16 sites were completed by December 2011. Structural analysis has been requested from all existing sites to latest code requirement; negotiation of improvements to existing towers has been completed and is in process. Example, one of our key vendors is Crown Castle which has 9 of the existing towers in the network and they have completed all structural analysis and we have negotiated updated terms. [c] RFP 3 - Telecommunications Equipment, For all telecommunication equipment, microwave backbone- point to point radios, Wi Max - point to multipoint radios, switches, cables, antennas, spares, installation and commissioning. RFP was evaluated, vendor selected and equipment was ordered. All equipment for this RFP to be received and installed in 15 sites by March 2012 with three more sites installed by June 2012. [d] RFP 4 - Central Office Equipment for Network, All central office gear, servers, routers, switches, firewall, security, network operations management, HVAC, UPS, ect. Proposals were evaluated and vendor selected, contract negotiations completed in 2011. All equipment to be installed in the first quarter of 2012. [e] RFP 5 â€“ Tower Construction for three new locations, Site preparation, construction and installation of foundation in three telecommunication towers in first two years. Published and meetings held in 2011, evaluation and vendor to selected in Jan 2012. The three towers are one 200 ft. self-sustaining tower, and two 150 ft. mono pods The three towers will be installed in the first two quarters of 2012. 3) The FCC frequencies for the projectâ€™s backbone have been secured. All the frequencies for the point to point microwave backbone, are reserved by the FCC in INTECOâ€™s name. All frequencies required in the Backbone in 6 and 11GHz and have completed the Client Approval Notification (CAN). 4) The 2.5 spectrum for Wi Max transmission is reserved by contract agreement 5) The lease agreements for sixteen existing towers will be completed by 1st quarter 2012; we have 13 signed, three in process. 6) The land- lease agreements for eight new tower sites will be completed by 1st quarter of 2012, we have 6 signed, two in process. 7) The Command Center (NOC) of the network and its data center will be completed by 1st quarter 2012. 8) Evaluation of personnel needed to adequately manage the project was completed and Engineering resources were added to the project. In 2011, we added, an engineer to do tower site construction inspections and a Network Engineering Manager. | Iniciativa Tecnologica Centro Oriental (INTECO) | 180 | 10 | 25 | 12 | 26 | 10 |  | 40 | 14 | 13 | 330 | We have completed an interconnection agreement with a key ISP supplier on the island and have a wholesale agreement completed with another supplier in order to provide Broadband Service connection. Although the network is in construction, we have a target of activating two major quadrants by late summer 2012, ahead of the grant schedule. We are establishing agreements beforehand in order to be able to provide service to key municipalities and CAI's once we active the BTOP network. | We agreed to acquire transit agreements in order to provide Broadband service which may include interconnection service. Although the network is in construction, we have a target of activating two major quadrants by late summer 2012, ahead of the grant schedule. We are establishing transit agreements beforehand in order to be able to provide service to key municipalities and CAI's once we active the BTOP network. We also want to have local peering on the island through an agreement with the other BTOP project on the island. We will have the benefits of local peering to all key CAI's from the begging of the project. | TRUE
NT10BIX5570033 | 2012 | 84,843 | This considers linear miles of a microwave network. | N/A | Same as baseline. | N/A | Same as baseline | 200 mbps | N/A | 9 mbps | N/A | 7.6 mbps | N/A | 5.6 mbps | N/A | 4 MBPS . Most institutions had a DLS Service and now will be provided by Broadband Service | Retail services to be provided is Internet connectivity, (DIA, Direct Internet Access). Point to Point and Point to Multipoint Mesh services will be provided. | Network Management Policies are being structured to comply with SLA (Service Level Agreement) standard to the Puerto Rico Market. Will be implemented at the end of Q1, 2013. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is microwave tower based not fiber based. | 2400 | 480 | 0 | 1920 | N/A | We have not made any subcontracts with entities with section 8a Small Business Act definition (SDB-Small Disadvantage Business). | a) Lessons learned. The INTECO project is a tower based microwave project, which needs to develop the towers in the network to be able to service the region and the CAIâ€™s. The network is designed with four loops or quadrants to provide redundancy and improve service levels to customers. To assure that we met the 67% objective in the first two years, we developed a strategy that prioritized the activities by focusing on completing two initial loops of the network. In these two quadrants the majority of the towers already existed (14 of the 16 existing towers in the network). We prioritized the preparation and construction in these two quadrants, will installed equipment in these towers and had complete the construction of the command center (NOC) in the first two years of the project. The initial two quadrants of the network have 14 existing towers, 3 new towers and the command center (CO). The site preparation for these 18 sites and all the equipment for all sites and the command center has been completed. This assured substantial completion of expenditures for the project within the two year requirement. We also constructed in these two initial quadrants, three of the eight new towers in the network. By developing the quadrant strategy and prioritizing the site preparation and tower construction, INTECO was able to achieve the objective of activating the network and the operations in the these two areas in August/September of 2012, ahead of the Grant schedule. We initiated connection for CAIâ€™s in the third quarter of 2012 in the quadrant which was activated. All at the NOC (Network Operation Center) equipment was installed and testing initiated in 2012. The network start-up was done in August/September of 2012. b) Lessons learned. Collection of information on regional public school broadband use. There was no centralized information in the region on what internet capabilities and how broadband was being used in the public school system. We developed a short survey and are conducting on site interviews to develop an information database on the state of the use of broadband in the region. We understand that this will do the following; (1) create a baseline for comparison when the project is implemented, (2) Pinpoint resources in the school system to foment the use of broadband resources, (3) Provide an overall inventory of how the public schools in the rural community are currently using the internet, (4) Create a contact sheet for which the people involved with Broadband in the school system in the region can connect with each other, and (5) establish schools which can be highlighted as innovative school implementing broadband programs in an objective form. As part of this survey we discovered the State Government Educational System has a procurement policy on a State-Wide basis, which eliminates regional possibility of participation. c) This type of project in Broadband Microwave infrastructure is driven by three major areas of investment that covers; Telecom Equipment, Construction of Towers & Sites and Site preparation for Towers. These three elements are over 85% of the total cost of the project. They are spent in certain peak periods of time as the equipment and sites are delivered, verified and accepted. The baseline report which we initially submitted did not consider this method. The original baseline was along the planning of activities, not cash flow paid to suppliers. In other words a lot of planning and preliminary work is needed to deliver the ability to install equipment and finish sites. Our project uses existing towers (which require preparation) and new towers being constructed. Elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation occur prior to payments to suppliers and draw downs. The method for the original baseline analysis did not reflect the time and effort it took for the project management of a complex project as well as the timing of payment to key suppliers. We have complied with the SAC goal of more than 67% completion of the project, as measured in money drawdownâ€™s , within the initial two year time span of the project and will achieve 100% completion of the project in three years. d) Major activities and tasks of INTECO project completed by December 2012; 1) Did sites surveys and network design verification, the sites in the network were submitted to the Environmental Assessment (EA) process . Completed EA, submitted and (FONSI) Finding of No Significant Impact received from NTIA. 2) INTECO managed six Requests for Proposal (RFP) processes. [a] RFP 1 - Construction Permits contract, submission of permits, included soil studies, terrain elevation and foundation design, to the responsible Puerto Rican permits agency for the construction of eight new telecommunications towers or roof-tops to be used by the network in underserved areas. All permit approvals for the sites were received by the end of 2012. [b] RFP 2 - Site preparation and equipment installation on sixteen existing tower Sites were completed by December 2012. [c] RFP 3 - Telecommunications Equipment, For all telecommunication equipment, microwave backbone- point to point radios, Wi Max - point to multipoint radios, switches, cables, antennas, spares, installation and commissioning. All equipment received and installed in 22 sites by December 2012. [d] RFP 4 - Central Office Equipment for Network, All central office gear, servers, routers, switches, firewall, security, network operations management, HVAC, UPS, etc. All equipment in central office were installed in 2012. [e] RFP 5/6 â€“ Tower Construction for four new locations, Site preparation, construction and installation of foundation of four telecommunication towers. 3) The FCC frequencies for the projectâ€™s backbone have been secured. All the frequencies for the point to point microwave backbone, are reserved by the FCC in INTECOâ€™s name. All frequencies required in the Backbone in 6 and 11GHz and have completed the Client Approval Notification (CAN). 4) The 2.5 frequencies for WiMax transmission is reserved by contract agreement 5) The lease agreements for sixteen existing tower sites and land-lease agreements for eight new tower/roof-top sites were completed in 2012. 6) The Command Center (NOC) of the network and its data center was completed in 2012. | Iniciativa Tecnologica Centro Oriental (INTECO) | 180 | 10 | 25 | 12 | 26 | 10 |  | 40 | 14 | 13 | 330 | We have two interconnection / transit agreements. Inteco has entered into an interconnection agreement with Critical Hub Networks and Ednet. We have not denied any request for interconnection. | Under the interconnection agreement with Critical Hub Networks, Inteco’s network is also peered with the Puerto Rico Bridge Initiative’s Internet Exchange Point (IXP) for local IP traffic exchange. | TRUE
NT10BIX5570033 | 2013 | 84,843 | This considers linear miles of a microwave network. | N/A | N/A. Project is classified as middle mile. | N/A | N/A. Project is classified as middle mile. | 300 mbps | N/A. | 9 mbps | N/A. | 7.6 mbps | N/A. | 5.6 mbps | N/A. | 4 mbps. Most institutions had a DLS Service ad now will provided by Broadband Service. | Retail services to be provided is internet connectivity. (DIA, Direct Internet Access). Point to Point and Point to Multipoint Mesh services will be provided. | Network Management Policies are being structured to comply with SLA (Service Level Agreement) standard to the Puerto Rico Market. They were implemented as of the end of the award date 07/31/2013. | 1 subscriber - 1% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is microwave tower based not fiber based. | 5800 | 1600 | 0 | 4200 | N/A. | We have not made any subcontracts with entities with section 8a Small Business Act definition (SDB-Small Disadvantage Business). | a) Lessons learned. The INTECO project is a tower based microwave project, which needs to develop the towers in the network to be able to service the region and the CAIâ€™s. The network is designed with four loops or quadrants to provide redundancy and improve service levels to customers. To assure that we met the 67% objective in the first two years, we developed a strategy that prioritized the activities by focusing on completing two initial loops of the network. In these two quadrants the majority of the towers already existed (14 of the 16 existing towers in the network). We prioritized the preparation and construction in these two quadrants, will installed equipment in these towers and had complete the construction of the command center (NOC) in the first two years of the project. The initial two quadrants of the network have 14 existing towers, 3 new towers and the command center (CO). The site preparation for these 18 sites and all the equipment for all sites and the command center has been completed. This assured substantial completion of expenditures for the project within the two year requirement. We also constructed in these two initial quadrants, three of the eight new towers in the network. By developing the quadrant strategy and prioritizing the site preparation and tower construction, INTECO was able to complete the project within time frame required. b) Lessons learned. Collection of information on regional public school broadband use There was no centralized information in the region on what internet capabilities and how broadband was being used in the public school system. We developed a short survey and are conducting on site interviews to develop an information database on the state of the use of broadband in the region. We understand that this will do the following; (1) create a baseline for comparison when the project is implemented, (2) Pinpoint resources in the school system to foment the use of broadband resources, (3) Provide an overall inventory of how the public schools in the rural community are currently using the internet, (4) Create a contact sheet for which the people involved with Broadband in the school system in the region can connect with each other, and (5) establish schools which can be highlighted as innovative school implementing broadband programs in an objective form. As part of this survey we discovered the State Government Educational System has a procurement policy on a State-Wide basis, which eliminates regional possibility of participation. c) This type of project in Broadband Microwave infrastructure is driven by three major areas of investment that covers; Telecom Equipment, Construction of Towers & Sites and Site preparation for Towers. These three elements are over 85% of the total cost of the project. They are spent in certain peak periods of time as the equipment and sites are delivered, verified and accepted. The baseline report which we initially submitted did not consider this method. The original baseline was along the planning of activities, not cash flow paid to suppliers. In other words a lot of planning and preliminary work is needed to deliver the ability to install equipment and finish sites. Our project uses existing towers (which require preparation) and new towers being constructed. Elements such as permits, design, contacting, proposal evaluation, negotiation, lead times for equipment, lead times for construction and installation occur prior to payments to suppliers and draw downs. The method for the original baseline analysis did not reflect the time and effort it took for the project management of a complex project as well as the timing of payment to key suppliers. Adjustents were made to complete the project on time. We have complied with the SAC goal of more than 67% completion of the project, as measured in money drawdownâ€™s , within the initial two year time span of the project and achieved 100% completion of the project on time. | Iniciativa Tecnologica Centro Oriental (INTECO) | 180 | 10 | 25 | 12 | 26 | 10 |  | 40 | 14 | 13 | 330 | We have two (2) interconnection/transit agreements. INTECO has entered into an interconnection agreement with Critical Hub Networks and Ednet. We have not denied any request for interconnection. | Under the interconnection agreement with Critical Hub Networks, INTECO's network is also peered with the Puerto Rico Bridge Initiative's Internet Exchange Point (IXP) for local IP traffic exchange. | TRUE
NT10BIX5570034 | 2010 | N/A | The network is not deployed at this time. | N/A | N/A | N/A | N/A | N/A | The network is not deployed at this time. | N/A | N/A | N/A | The network is not deployed at this time. | N/A | N/A | N/A | The network is still being deployed so services utilizing this network are not being provided at this time. DeltaCom is creating competitive middle mile pricing that enables connectivity for last mile provider networks. Additionally, DeltaCom will utilize last mile providers to enable direct DeltaCom services to public anchor institutions in select markets at a 20% discount below our list pricing for qualifying broadband services. | The network management policies for this specific project are being reviewed and will be ready prior to the launch of the network.DeltaCom adheres to the non-discrimination and interconnection requirements set forth in the NOFA. DeltaComâ€™s service connects to the public Internet and is not an entirely private or closed network. DeltaCom promotes the open and interconnected nature of the public Internet, and believes consumers are entitled to access the lawful Internet content of their choice. On our network, consumers are entitled to run applications and use services of their choice, subject to the needs of law enforcement. DeltaCom does not favor any Internet applications over any other Internet applications. Consumers are entitled to connect to our service via their choice of legal devices that do not harm the network. We believe consumers are entitled to competition among network providers, applications, service providers and content providers. DeltaCom employs generally accepted measures to provide acceptable service level to customers. DeltaCom utilizes fair negotiation of interconnection agreements with carriers for the exchange of traffic and has multiple interconnection agreements and contracts currently in place. DeltaCom has a collocation process by which carriers may ask for interconnection and where DeltaCom seeks interconnection within other carrierâ€™s network. DeltaCom has a standard process in place for physical interconnection in order to evaluate | N/A | 5668 | 0 | 0 | 3570 | 175 | 0 | 1923 | N/A | 0 | 0 | 0 | 0 | Carriers can interconnect with DeltaCom's network at ILEC central offices defined as interconnection points in DeltaCom's award application. | No subcontracts or sub grants have been made. | DeltaCom utilizes a bifurcated award implementation approach and has a Project Director for Compliance and a Project Director for Operations. Using this approach has created a check and balance system for activities related to the award. | DeltaCom, Inc. | 39 | 39 | 11 | 21 | 39 | 52 |  | 18 | 31 | 21 | 271 | N/A | N/A | TRUE
NT10BIX5570034 | 2011 | $3,911 | This number was calculated based on Construction funds expended and the number of miles deployed as of December 31, 2011. This number is different from the Baseline because it does not include the total funds required to complete the project. | N/A | N/A | N/A | N/A | 0 | Not applicable at this time. | N/A | N/A | 0 | Not applicable at this time. | N/A | N/A | Community anchor institutions are not connected to the network at this time. | Community anchor institutions are not connected to the network and services are not being provided at this time. DeltaCom will lease facilities from last mile providers to enable DeltaCom services to community anchor institutions in select markets. These community anchor institutions will receive a 20% discount below DeltaCom's list pricing for qualifying broadband services. Please see the attached document titled DeltaCom Retail Service Descriptions for more information on planed DeltaCom services. | DeltaCom's network management policies are available at http://www.earthlinkbusiness.com/about-us/legal/network-management-policy.xea . DeltaCom adheres to the non-discrimination and interconnection requirements set forth in the NOFA. DeltaComâ€™s service connects to the public Internet and is not an entirely private or closed network. DeltaCom promotes the open and interconnected nature of the public Internet, and believes consumers are entitled to access the lawful Internet content of their choice. On our network, consumers are entitled to run applications and use services of their choice, subject to the needs of law enforcement. DeltaCom does not favor any Internet applications over any other Internet applications. Consumers are entitled to connect to our service via their choice of legal devices that do not harm the network. We believe consumers are entitled to competition among network providers, applications, service providers and content providers. DeltaCom employs generally accepted measures to provide acceptable service level to customers. DeltaCom utilizes fair negotiation of interconnection agreements with carriers for the exchange of traffic and has multiple interconnection agreements and contracts currently in place. DeltaCom has a collocation process by which carriers may ask for interconnection and where DeltaCom seeks interconnection within other carrierâ€™s network. DeltaCom has a standard process in place for physical interconnection in order to | Not applicable at this time. | 5668 | 3731 | 0 | 1773 | 14 | 0 | 150 | Not applicable to this project. | 0 | 0 | 0 | 0 | Carriers can interconnect with DeltaCom's network at ILEC central offices located in Cleveland, Cookeville, Morristown, Oak Ridge and Sweetwater, Tennessee. | No subcontracts or sub grants have been made to socially and economically disadvantaged small business (SDB) concerns as defined by section 8(a) of the Small Business Act. | DeltaCom utilizes a bifurcated award implementation approach and has a Project Director for Compliance and a Project Director for Operations. Using this approach has created a check and balance system for activities related to the award. | DeltaCom, Inc. | 39 | 39 | 11 | 21 | 39 | 52 |  | 18 | 31 | 21 | 271 | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570034 | 2012 | $4029 | This number was calculated based on Construction funds expended and the number of miles deployed as of December 31, 2012. This number is different from the Baseline because it does not include the total funds required to complete the project. | N/A | N/A | N/A | N/A | OC-12, 100 Gig, 225 Mile | Service Offering: OC- 12 Distance Band or Point to Point: 225 Mile Distance Band Minimum Peak Load Network Bandwidth Capacity: 100 Gig | N/A | N/A | 8 Gig | This number is slightly higher than the baseline plan. | N/A | N/A | In order to respond to this question, DeltaCom surveyed the community anchor institution customers that connect to the BTOP funded network. One community anchor institution added a 50Mbps Ethernet connection for internet connectivity to their existing facilities. The other community anchor institution customer upgraded from a 4.5Mbps bonded circuit to a 10Mbps Ethernet connection. | DeltaCom leases facilities from last mile providers to enable DeltaCom services to community anchor institutions in select markets. These community anchor institutions will receive a 20% discount below DeltaCom's list pricing for qualifying broadband services. Please see the attached document titled DeltaCom Retail Service Descriptions for more information on planed DeltaCom services. Currently one customer is utilizing a 50Mbps Ethernet connection and another community anchor institution customer is utilizing a 10Mbps Ethernet connection. | DeltaCom's network management policies are available at http://www.earthlinkbusiness.com/about-us/legal/network-management-policy.xea . DeltaCom adheres to the non-discrimination and interconnection requirements set forth in the NOFA. DeltaComâ€™s service connects to the public Internet and is not an entirely private or closed network. DeltaCom promotes the open and interconnected nature of the public Internet, and believes consumers are entitled to access the lawful Internet content of their choice. On our network, consumers are entitled to run applications and use services of their choice, subject to the needs of law enforcement. DeltaCom does not favor any Internet applications over any other Internet applications. Consumers are entitled to connect to our service via their choice of legal devices that do not harm the network. We believe consumers are entitled to competition among network providers, applications, service providers and content providers. DeltaCom employs generally accepted measures to provide acceptable service level to customers. DeltaCom utilizes fair negotiation of interconnection agreements with carriers for the exchange of traffic and has multiple interconnection agreements and contracts currently in place. DeltaCom has a collocation process by which carriers may ask for interconnection and where DeltaCom seeks interconnection within other carrierâ€™s network. DeltaCom has a standard process in place for physical interconnection in order to | No customers have dropped the broadband service provided through this project. | 5668 | 3745 | 0 | 1923 | 0 | 0 | 0 | Not applicable to this project. | 0 | 0 | 0 | 0 | Carriers can interconnect with DeltaCom's network at ILEC central offices located in Cleveland, Cookeville, Morristown, Oak Ridge and Sweetwater, Tennessee. | No subcontracts or sub grants have been made to socially and economically disadvantaged small business (SDB) concerns as defined by section 8(a) of the Small Business Act. | DeltaCom utilizes a bifurcated award implementation approach and has a Project Director for Compliance and a Project Director for Operations. Using this approach has created a check and balance system for activities related to the award. | DeltaCom, Inc. | 39 | 39 | 11 | 21 | 39 | 52 |  | 18 | 31 | 21 | 271 | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570034 | 2013 | 3,659.83 | This number was calculated based on Construction funds expended and the number of miles deployed as of May 1, 2013. This number is different from the Baseline because it does not include the total funds required to complete the project. Additional decrease from the 2012 APPR is the result of a return of funs to ASAP for expenditures not covered by the grant. | N/A | N/A | N/A | N/A | OC-12, 100 Gig, 225 Mile | Service Offering: OC- 12 Distance Band or Point to Point: 225 Mile Distance Band Minimum Peak Load Network Bandwidth Capacity: 100 Gig | N/A | N/A | 8 Gig | This number is slightly higher than the baseline plan. | N/A | N/A | In order to respond to this question, DeltaCom surveyed the community anchor institution customers that connect to the BTOP funded network. One community anchor institution added a 50Mbps Ethernet connection for internet connectivity to their existing facilities. The other community anchor institution customer upgraded from a 4.5Mbps bonded circuit to a 10Mbps Ethernet connection. | DeltaCom leases facilities from last mile providers to enable DeltaCom services to community anchor institutions in select markets. These community anchor institutions will receive a 20% discount below DeltaCom's list pricing for qualifying broadband services. Please see the attached document titled DeltaCom Retail Service Descriptions for more information on planed DeltaCom services. Currently one customer is utilizing a 50Mbps Ethernet connection and another community anchor institution customer is utilizing a 10Mbps Ethernet connection. | DeltaCom's network management policies are available at http://www.earthlinkbusiness.com/about-us/legal/network-management-policy.xea . DeltaCom adheres to the non-discrimination and interconnection requirements set forth in the NOFA. DeltaComâ€™s service connects to the public Internet and is not an entirely private or closed network. DeltaCom promotes the open and interconnected nature of the public Internet, and believes consumers are entitled to access the lawful Internet content of their choice. On our network, consumers are entitled to run applications and use services of their choice, subject to the needs of law enforcement. DeltaCom does not favor any Internet applications over any other Internet applications. Consumers are entitled to connect to our service via their choice of legal devices that do not harm the network. We believe consumers are entitled to competition among network providers, applications, service providers and content providers. DeltaCom employs generally accepted measures to provide acceptable service level to customers. DeltaCom utilizes fair negotiation of interconnection agreements with carriers for the exchange of traffic and has multiple interconnection agreements and contracts currently in place. DeltaCom has a collocation process by which carriers may ask for interconnection and where DeltaCom seeks interconnection within other carrierâ€™s network. DeltaCom has a standard process in place for physical interconnection in order to | No customers have dropped the broadband service provided through this project. | 5668 | 3745 | 0 | 1923 | 0 | 0 | 0 | Not applicable to this project. | 0 | 0 | 0 | 0 | Carriers can interconnect with DeltaCom's network at ILEC central offices located in Cleveland, Cookeville, Morristown, Oak Ridge and Sweetwater, Tennessee. | No subcontracts or sub grants have been made to socially and economically disadvantaged small business (SDB) concerns as defined by section 8(a) of the Small Business Act. | DeltaCom utilizes a bifurcated award implementation approach and has a Project Director for Compliance and a Project Director for Operations. Using this approach has created a check and balance system for activities related to the award. | DeltaCom, Inc. | 39 | 39 | 11 | 21 | 39 | 52 |  | 18 | 31 | 21 | 271 | DeltaCom has not entered into any interconnection agreements at this time. DeltaCom is not currently negotiation any interconnection agreements at this time and DeltaCom has not denied any requests for interconnection on the BTOP funded network. | DeltaCom has entered into eight transit/transport interconnection agreement utilizing the BTOP funded network. These agreements include one agreement with Sunset Digital Communications, and one agreement with Morristown Utilities Commission, five agreements with Dukenet Communications, and one agreement with Twin Lakes Telephone Cooperative. DeltaCom has not denied any requests for peering or transit agreements. | TRUE
NT10BIX5570035 | 2010 | 0 | Network deployment not yet completed pending intercreditor agreement and Historic Preservation review completion. | 0 | Middle Mile only | 0 | Middle Mile only | 0 | Network deployment not yet completed pending intercreditor agreement and Historic Preservation review completion. | 0 | Middle Mile only | 0 | Network deployment not yet completed pending intercreditor agreement and Historic Preservation review completion. | 0 | Middle Mile only | Network deployment not yet completed pending NTIA approval of intercreditor agreement and Historic Preservation review completion. | Middle Mile network only. | Hardy Telecommunications does not limit bandwidth or prioritize traffic. Hardy has never limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | Network deployment not yet completed pending NTIA approval of intercreditor agreement and Historic Preservation review completion. | 13667 | 13113 | 0 | 554 | 12144 | 0 | 554 | Network deployment not yet completed pending NTIA approval of intercreditor agreement and Historic Preservation review completion. | 180 | 160 | 0 | 20 | Collocation space will be provided. Facilities deployment not yet started. | No subcontracts or sub grants to SDBs to date. | Communicate well and often with NTIA staff and project team. Keep detailed, contemporaneous project records. | Hardy Telecommunications, Inc. | 7 | 0 | 0 | 0 | 11 | 9 |  | 28 | 8 | 0 | 63 | No interconnection agreements. Network deployment not yet completed. | No peering and transit agreements. | TRUE
NT10BIX5570035 | 2011 | $19,217.18 | (44.8%) Variance is due to difference in basis of calculation of Baseline Plan indicator compared to APR-2011 guidance. Baseline indicator was calculated based on total project costs, including equipment, professional services, and operational support systems. APR-2011 indicator guidance is to base calculation on labor and materials costs only of new middle mile network deployed. | 0 | NA | 0 | NA | 0 | Basline Plan Indicator is 1-Gbps. Speed tiers associated with service plans for purchase have not yet been advertised -- deployment of backbone ring still in process. New construction of CAI laterals and drops not yet started. Delays due to section 106 review process requiring Phase 1 survey and archaeological shovel testing. Hardy has conducted marketing and outreach in newspaper stories, company website and company newsletter. The following is a link to Hardy's newsletter on the web with an article that can be downloaded. The newletter was published in November, 2011: http://hardynet.net/images/stories/PDfs/Hardy_November_2011_newsletter_WEB.pdf | 0 | Baseline Indicator "N/A" | 10 | Backbone ring partially complete at 12-31-2011. Spans between 8 nodes constructed as of 12-31-2011, with 10-Gbps capacity turned up between nodes. At this time dedicated ethernet transport can be offered between nodes at 10, 50 and 100 Mbps up to 1 Gbps. New construction of laterals and drops to CAIs not yet started. Network upgraded to local schools, school administration office, and three cellular towers. Seven schools sites each receiving 10-Mbps dedicated ethernet transport service. Cellular carriers considering replacement or system upgrades for upstream TDM equipment to take advantage of low-cost high capacity ethernet service. Deployment delays are due to section 106 review process requiring Phase 1 survey and archaeological shovel testing. | 0 | Baseline Indicator "N/A" | Pending backbone network completion, laterals and drops to anchor institutions, Hardy AnchorRing service is available for six schools, the school administration office, and three cellular towers. Prior to deployment, each school site received T1 transmission service at 1.544 Mbps second. Currently school sites are each receiving 10 Mbps transport service, for a capacity increase of approximately 548% over T1 service. Service is available to the schools up to 1 Gbps per site, an increase of approximately 66,221% over T1 service. Cellular carriers could obtain only T1 service to three tower sites. Two towers are served with two T1 lines each, or 3.088 Mbps per tower, and one tower is served one T1 line at 1.544 Mbps. Service up to 1 Gbps is now available to the towers, representing a capacity increase of approximately 33,061% or 66,221% depending upon number of T1 lines connected. | Hardy AnchorRing offers from 10 Mbps to 1 Gbps service to connected community anchor institutions. Six local schools and the school administration office currently purchase 10 Mbps service per site for a total of 70 Mbps, a capacity increase of approximately 548% over T1 service at an increase in cost of only 63.1%. On March 30, 2012 a price decrease will go into effect for the schools, which will lower the schools' total cost of service by an additional 22.8%. At that time, the schools will be receiving 548% more capacity at only a 26.3% increase in cost over T1 service. | Hardy Telecommunications does not limit or block consumers from accessing any lawful content, service, service provider or application, or prevent any consumers from attaching any legal devices to the network. Network management practices are posted on Hardyâ€™s website at: http://www.hardynet.com/images/stories/PDfs/HardyNet_Network_Management_Policies_Disclosure_11-11_Ver._2.pdf | No broadband services provided through this project have been dropped or discontinued. | 15383 | 122 | 0 | 1826 | 12997 | 0 | 438 | Hardy Telecommunications has not received requests for wholesale dark fiber during the performance period. | 0 | 0 | 0 | 0 | Not yet constructed. | No contracts have been awarded to socially and economically disadvantaged small business concerns within the performance period. Hardy Telecommunications encourages qualified local small businesses of all types, including small disadvantaged, women-owned, veteran-owned, and service disabled veteran-owned small businesses, to respond to requests for proposals for construction and installation services in order to create more jobs within the local area. Hardy instructs contractors to be proactive in subcontracting to such small businesses. | NTIA's web-based guidance sessions and drop-in calls have been very helpful to Hardy's project team members; Hardy encourages other BTOP recipients to take advantage of these sessions whenever possible. Networking with other BTOP recipients has been valuable to Hardy and its project team as a way to learn about progress of other projects, delays and suggestions for avoidance or mitigation, news of emerging risks, and suggestions to speed deployment, save time, and control costs. | Hardy Telecommunications, Inc. | 7 | 0 | 0 | 0 | 11 | 9 |  | 28 | 8 | 0 | 63 | Hardy Telecommunications did not receive requests for interconnection during the annual reporting period. | Hardy telecommunications did not receive requests for peering and transit agreements during the annual reporting period. | TRUE
NT10BIX5570035 | 2012 | 19734.95 | (43.3%) Variance is due to basis in calculation of Basedline Indicator compared to APR-2012. Baseline indicator calculated based on total project costs including equipment, professional services, and operational support systems. APR-2012 indicator based on labor and materials costs of new middle mile network deployed. | 0 | Middle Mile | 0 | Middle Mile | 10 Gbps | Baseline Plan Indicator = 1 Gbps. Speed Tiers offered to CAIs range include 5Mbps/2Mbps, 15Mbps/7Mbps, 25Mbps/10Mbps, and other increments up to 1 Gbps bidrectional service. Wholesale service is offered from 1Gbps to 10Gbps. | 0 | Middle Mile | 18 Mbps / 8 Mbps | Average broadband speed provided to CAIs 18 Mbps upstream /8 Mbps downstream | 0 | Middle Mile | Prior to BTOP deployment of broadband infrastructure many CAIs in Hardy County could not obtain affordable or reliable broadband service. The available connection speed for many CAIs was 1.544 Mbps upstream and downstream, or T1 transmission service. In addition the existing upstream network was not diverse or redundant, and frequent outages were experienced. Hardy AnchorRing service is now available at speeds up to 1 Gbps, and the network is diverse and redundant. 18 Mbps is the average downstream service speed now being provided, with 8 Mbps upstream. This represents an average increase in bandwidth of 16.5 Mbps downstream and 6.5 Mbps upstream, or an average increase of 1066% and 418% respectfully. Hardy began serving Hardy County Scho2ols and three cellular towers prior to award of BTOP funding, but was unable to provide for diversity and redundancy. These sites have now been connected to Hardy AnchorRing and can now obtain up to 1 Gbps of affordable and reliable service. | Hardy AnchorRing is a Middle Mile network. Hardy Telecommunications was also awarded a Broadband Initiatives Program loan/grant award from the Rural Utilities Service of the U.S. Department of Agriculture to deploy Hardy OneNet. Hardy OneNet. which began construction in 2011, is a Fiber-to-the-Premise Last Mile network serving underserved areas of Hardy County. Hardy OneNet leverages the BTOP Middle Mile Backbone Ring and upstream connection to the Global Internet to lower costs and speed deployment to homes and businesses, especially small businesses. | Hardy Telecommunications does not limit or block consumers from accessing any lawful content, service, service provider or application, or prevent any consumers from attaching any legal devices to the network. Network management practices are posted on Hardyâ€™s website at: http://www.hardynet.net/wp-content/uploads/2012/09/HardyNet_Network_Management_Policies_Disclosure_11-11_Ver._2.pdf | No subscribers have dropped Hardy AnchorRing service. | 14701 | 2821 | 0 | 11880 | 0 | 0 | 0 | No wholesale fiber leases at this time. | 0 | 0 | 0 | 0 | Customers may connect with Hardy AnchorRing at Hardy Telecommunications' central offices. | No contracts have been awarded to socially and economically disadvantaged small business concerns within the performance period. Hardy Telecommunications encourages qualified local small businesses of all types, including small disadvantaged, women-owned, veteran-owned, and service disabled veteran-owned small businesses to respond to requests for proposals for construction and installation services in order to create more jobs within the local area. Hardy instructs contractors to be proactive in subcontracting to small local businesses and hiring qualified local employees. | Early communication of issues or questions to the Federal Program Officer and Grants Management Officer is key. Hardy's Program and Grants Management Officers have been proactive and responsive in tracking down information and following up. NTIA's web-based guidance sessions and drop-in calls have been very helpful to Hardy's project team. Networking with other BTOP recipients at events hosted by NTIA and other public and nonprofit institutions has been valuable to Hardy and its project team as a way to learn about progress of other projects, delays and suggestions for avoidance or mitigation, news of emerging opportunities or risks, and potential opportunities for interconnection and collaboration. | Hardy Telecommunications, Inc. | 7 | 0 | 0 | 0 | 11 | 9 |  | 28 | 8 | 0 | 63 | No Interconnection requests received or denied. | No peering agreements requested to date. 155-Mbps wholesale transport service was requested and is being provided to a wholesale interexchange carrier for connection to the carrier's cellular customer site. Higher capacity can improved cellular coverage in the area. No additional transport agreements have been requested to date. | TRUE
NT10BIX5570036 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 50M-10Gbps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 1 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 1 interconnection agreement (3) N/A | N/A | TRUE
NT10BIX5570036 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 1 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570036 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570036 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 50Mb - 10Gbps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570037 | 2010 | $53132.00 | Phase I Fiber Bid $1,275,169.44 - 23.72 Conduit miles, 26.10 cable miles | 0 | N/A | 0 | N/A | 1 Gig | No Change | 0 | N/A | 500MB | No Change | 0 | N/A | Construction Started December 13, 2010 | Construction Started December 13, 2010 | Construction Started December 13, 2010 | Construction Started December 13, 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction Started December 13, 2010 | 0 | 0 | 0 | 0 | Construction Started December 13, 2010 | None at this time | During the Environmental Assessment, pre-qualify contractors and stake the routes. This process will speed the construction process. Created Twitter account @cccbu and as of December 2010 have 500+ users following the progress of our stimulus project. Created Facebook page Columbia County Community Broadband Utility to communicate project milestones and present pictures and videos pertaining to project. Utilizing RSS feeds and text updates to inform citizens about the status of our project. Created an article introducing our project and included it in our local Water Utility direct mail insert, which on average, reaches 44,000 households. Setup Website to communicate project milestones and vendors to register to receive project updates. Evaluate outside and inside plant materials (quality, cost, etc.) before issuing construction bids. Standardize and Include materials evaluated including the cost received from suppliers in the construction bids. This will lower your overall material cost including material management cost. | Columbia, County of | 36 | 3 | 1 | 1 | 4 | 35 |  | 65 | 4 | 1 | 150 | N/A | N/A | TRUE
NT10BIX5570037 | 2011 | 55,193 | Cost based on fiver awarded construction contracts. | 0 | N/A | 0 | N/A | 1 Gig | No Change | 0 | N/A | 500MB | No Change | 0 | N/A | Our current focus is on outside plant fiber construction. Once our construction is substantially completed and electronic equipment selected, we will focus on subscribers and connecting Community Anchor Institutions. | Our current focus is on outside plant fiber construction. Once our construction is substantially completed and electronic equipment selected, we will focus on subscribers and connecting Community Anchor Institutions. | Our current focus is on outside plant fiber construction. Once our construction is substantially completed and electronic equipment selected, we will focus on subscribers and connecting Community Anchor Institutions. | Our current focus is on outside plant fiber construction. Once our construction is substantially completed and electronic equipment selected, we will focus on subscribers and connecting Community Anchor Institutions. | 42836 | 0 | 0 | 0 | 0 | 0 | 42836 | Fiber plant under construction. | 2130 | 480 | 0 | 1650 | Network providers and/or customers can interconnect at any hand hole in our network build out. New 450 square foot point of presence building in Evans. Seven 240 square foot prefab concrete shelters at each tower location located in (Appling, Harlem, Grovetown, Evans, and Martinez). | None at this time | Due to rapid technology changes and warranty periods, recommend purchasing electronic equipment at the end of your project. | Columbia, County of | 36 | 3 | 1 | 1 | 4 | 35 |  | 65 | 4 | 1 | 150 | N/A | N/A | TRUE
NT10BIX5570037 | 2012 | 55,193 | Cost based on five awarded construction contracts. | 0 | N/A | 0 | N/A | 1 Gig | No Change | 0 | N/A | 500MB | No Change | 0 | N/A | CAI's Speeds ~ Upgraded Avg Old Avg New Avg Increase Speed Service Speed Speed <10Mb >=10Mb and <50Mb 12 .5Mb 10Mb 20 times 240 >=50Mb and <100Mb 6 1.5Mb 50Mb 33.33 times 200 >=100Mb and < 1Gb 7 5Mb ~ 100Mb 20 times 140 >=1Gb 41 10Mb ~ 1000Mb 100 times 4100 Total upgraded connections 66 70.909 4680/66 upgraded service Upgraded 66 CAI's with and an average increase of 71 times faster service | Price structure waiting approval of Board of Commissioners. | Columbia County will manage the network in accordance with the FCC's Internet Policy Statement (FCC 05-151, adopted August 5, 2005) and in compliance with any future Internet policy changes by the FCC. Currently Columbia County does not discriminate or favor any lawful Internet applications, content, or services where lawfully used. Columbia County will promote our customer's ability to freely access and disseminate lawful content in a manner that respects others' use of the network and that complies with the law. Columbia County follows standard best efforts for Internet delivery with respect to allocation of capacity without differentiation among applications, providers, or sources. Columbia county uses generally accepted technical measures to provide acceptable service levels to all customers, such as application-neutral bandwidth allocation, as well as measures to address service attacks, illegal content and other harmful activities to protect network integrity and reliability. | None at this time | 42294 | 4838 | 0 | 37456 | 0 | 0 | 0 | Once Board of Commissioners approve rate structure, Columbia County will be actively marketing the lease of fiber. | 2130 | 480 | 0 | 1650 | Network providers and/or customers can interconnect at any hand hole in our network build out. New 450 square foot point of presence building in Evans. Seven 240 square foot prefab concrete shelters at each tower location located in (Appling, Harlem, Grovetown, Evans, and Martinez). | None at this time | Due to rapid technology changes and warranty periods, recommend purchasing electronic equipment at the end of your project. | Columbia, County of | 36 | 3 | 1 | 1 | 4 | 35 |  | 65 | 4 | 1 | 150 | N/A | N/A | TRUE
NT10BIX5570037 | 2013 | 55,193 | Cost based on five awarded construction contracts. | 0 | N/A | 0 | N/A | 1Gig | No Change | 0 | N/A | 500Mb | No change | 0 | N/A | CAI's Speeds ~ Upgraded Avg Old Avg New Avg Increase Speed Service Speed Speed <10Mb >=10Mb and <50Mb 12 .5Mb 10Mb 20 times 240 >=50Mb and <100Mb 6 1.5Mb 50Mb 33.33 times 200 >=100Mb and < 1Gb 7 5Mb ~ 100Mb 20 times 140 >=1Gb 41 10Mb ~ 1000Mb 100 times 4100 Total upgraded connections 66 70.909 4680/66 upgraded service Upgraded 66 CAI's with and an average increase of 71 times faster service | Our plan is to connect CAIs and provide wholesale services. Rate plan attached. | Columbia County will manage the network in accordance with the FCC's Internet Policy Statement (FCC 05-151, adopted August 5, 2005) and in compliance with any future Internet policy changes by the FCC. Currently Columbia County does not discriminate or favor any lawful Internet applications, content, or services where lawfully used. Columbia County will promote our customer's ability to freely access and disseminate lawful content in a manner that respects others' use of the network and that complies with the law. Columbia County follows standard best efforts for Internet delivery with respect to allocation of capacity without differentiation among applications, providers, or sources. Columbia county uses generally accepted technical measures to provide acceptable service levels to all customers, such as application-neutral bandwidth allocation, as well as measures to address service attacks, illegal content and other harmful activities to protect network integrity and reliability. | None at this time | 42294 | 4838 | 0 | 37456 | 0 | 0 | 0 | Columbia County Board of Commissioners approved a rate plan on January 15,2013. Columbia County is actively marketing the lease of fiber. | 2130 | 480 | 0 | 1650 | Network providers and/or customers can interconnect at any hand hole in our network build out. New 450 square foot point of presence building in Evans. Seven 240 square foot prefab concrete shelters at each tower location located in (Appling, Harlem, Grovetown, Evans, and Martinez). | None at this time | Due to rapid technology changes and warranty periods, recommend purchasing electronic equipment at the end of your project. | Columbia, County of | 36 | 3 | 1 | 1 | 4 | 35 |  | 65 | 4 | 1 | 150 | N/A | N/A | TRUE
NT10BIX5570038 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 50M-10Gbps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 1 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreement (2) 2 interconnection agreements (3) N/A | N/A | TRUE
NT10BIX5570038 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 2 interconnection agreements (2) 1 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570038 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 2 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570038 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50Mb-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570039 | 2010 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 44000 | 0 | 0 | 0 | 9000 | 0 | 35000 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | The negotiation of all contracts associated with your project will take longer and cost more than you anticipate. Use a very competent law firm with multiple in house disciplines to provide aid in this regard. Where possible, include drafts of your anticipated contracts in RFPs for respondents to mark up with concerns and issues that can then be discussed in interviews. Meet with pole and conduit owners early and often and aggressively pursue all master agreements and organize with them to ensure the fastest possible response to license applications for pole attachments and conduit access, and the performance of make ready. Request that they look at your project outside the box of normal procedure so that innovative methods can be used to expedite the project. They will not alter long established procedures or ignore collective bargaining agreements, but will work with you to devise methods to move things more quickly. An example would be the use of a single detailed field survey acceptable to all parties for assessment of make ready needs. Contract for field survey, licensing and permitting, and engineering services early. Chose a competent company with experience within your region and a good reputation with utility companies. Start this activity as soon as possible as it can aid in all other contract development and decision-making about path. Select a very capable engineering company to prepare your Environmental Assessment as early as possible. Ensure they have in-house capability or a partnership relationship with a cultural and historical survey firm. | OpenCape Corporation | 127 | 58 | 3 | 24 | 70 | 258 |  | 65 | 65 | 0 | 670 | N/A | N/A | TRUE
NT10BIX5570039 | 2011 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 44000 | 0 | 0 | 0 | 9000 | 0 | 35000 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | The negotiation of all contracts associated with your project will take longer and cost more than you anticipate. Use a very competent law firm with multiple in house disciplines to provide aid in this regard. Where possible, include drafts of your anticipated contracts in RFPs for respondents to mark up with concerns and issues that can then be discussed in interviews. Meet with pole and conduit owners early and often and aggressively pursue all master agreements and organize with them to ensure the fastest possible response to license applications for pole attachments and conduit access, and the performance of make ready. Request that they look at your project outside the box of normal procedure so that innovative methods can be used to expedite the project. They will not alter long established procedures or ignore collective bargaining agreements, but will work with you to devise methods to move things more quickly. An example would be the use of a single detailed field survey acceptable to all parties for assessment of make ready needs. Contract for field survey, licensing and permitting, and engineering services early. Chose a competent company with experience within your region and a good reputation with utility companies. Start this activity as soon as possible as it can aid in all other contract development and decision-making about path. Select a very capable engineering company to prepare your Environmental Assessment as early as possible. Ensure they have in-house capability or a partnership relationship with a cultural and historical survey firm. | OpenCape Corporation | 127 | 58 | 3 | 24 | 70 | 258 |  | 65 | 65 | 0 | 670 | N/A | N/A | TRUE
NT10BIX5570039 | 2012 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A. Though CAIs are connected, services is not yet offered on the network. | N/A | N/A. Network management policies are under development. | N/A | 44000 | 0 | 0 | 0 | 9000 | 0 | 35000 | N/A | 0 | 0 | 0 | 0 | Owned colocation space is still under construction. Other providers/customers may interconnect with the network at 10 leased colocation or central office facilities, and one microwave location. Customers may also connect into the network with new fiber laterals at multiple points around the fiber network where splice points and slack loops are located. | N/A | Specificity in contracts is always desirable, but as time passes since initial contacts were signed projects mature and evolve. This is especially true when key personnel change from time to time. Conducting an annual review of all major contracts is important to refresh what the contracts actually say versus what day to day practice may be. Such a review must be done with the perspective of as if one is reading them for the first time. In conjunction with such a contract review, also note all of the future obligations of the company for such things as equipment list updates to tower owners or permitting jurisdictions, lease renewals, etc. Creating the ongoing operational action list is critical in a new company especially. With no history to follow, items in underlying rights that need to be updated on regular intervals won't be lost, especially in situations where key people with institutional memory are lost over time. | OpenCape Corporation | 127 | 58 | 3 | 24 | 70 | 258 |  | 65 | 65 | 0 | 670 | N/A | OpenCape effectively entered into one transit agreement during this reporting period by virtue of an IRU with OSHEAN, Inc. No other peering and transit agreements are being negotiated. | TRUE
NT10BIX5570039 | 2013 | $54,739 | Costs per mile are as expected in the baseline plan, and consistent with other BTOP projects in the state. | 0 | N/A, middle mile project | 0 | N/A, middle mile project | 1000 | Speeds up to 1 Gbps are available on the network | 0 | N/A, middle mile project | 200 | Average speed of network customers today is approximately 100 Mbps. Speeds of customers range from 10 Mbps to 2.5 Gbps. Average speeds depend on what customers need for their application and are not limited by the network. Once the Barnstable County RFP evaluation is completed, average speeds should increase considerably. | 0 | N/A | Average broadband speed increases at CAIs has been moderate to date. Most CAIs acquiring service on the network are replacing existing connectivity and making only moderate increases of around 20% in speed. The Barnstable County RFP process has delayed connecting more CAIs at the higher speeds of shared 1 Gbps service rings (a total of 14 Gbps on net capacity that will be reserved for 63 of the Cape CAIs) with 1 Gbps connectivity to the Internet. The connections will be shared across 14 service rings operating at 1 Gbps, shared 1 Gbps Internet, and shared 1 Gbps Internet2 connections. When service is provided through the proposal, all 63 CAIs will have a 1 Gbps connection to the network. | OpenCape only offers retail services in the collocation data center. Retail pricing is currently set at $750/rack/month, or $50/RU/month. Connectivity to the Internet is offered at $10/mbps/month. Power is charged at the rated power supply of the equipment installed. Pricing is under review based on a recent reconfiguration of the data center cooling system. | Network management practices consistent with FCC 10-201A1. As a general network practice, no bandwidth limitations are imposed on network users other than limiting traffic at the level contracted for by the end user. No traffic prioritization methods are in place. No lawful content is blocked on the network, nor access to any service, service provider, or application. Firewall services have been requested in the Barnstable County RFP and will be applied, including any content blocking, as desired by the end network user (for example, educational institutions). | No users have dropped service provided through this project. | 44000 | 9000 | 0 | 35000 | 9000 | 0 | 35000 | N/A. OpenCape does not wholesale dark fiber. | 2500 | 100 | 0 | 2400 | Network provider can interconnect with the network at any of the 12 points of presence maintained by OpenCape. Eight of these location are ILEC central office locations. One is a CLEC collocation facility. One is a private facility with limited interconnection facilities, but one carrier plans on interconnecting with the network at that point. The remaining facility is the OpenCape collocation center. Network providers or customers may also connect at any of the 11 microwave sites that are active in the network, provided they can obtain physical access rights from the facility owners. All sites are connected to the fiber optic network. Customers can connect at any convenient point in the network where splice points exist. Laterals would be run from these splice points to the customer location. There are slack loops and existing splice locations throughout the network to facilitate customer connections. | N/A | Local permitting cannot be started too early. An understanding of the local permitting processes is critical, but always takes longer than one expects. For ongoing operations, it is also important to maintain an updated financial model. As real costs are determined as compared to what was modeled years ago, the operational plan should continue to be updated to understand the financial aspects of the business post-grant. | OpenCape Corporation | 127 | 58 | 3 | 24 | 70 | 258 |  | 65 | 65 | 0 | 670 | No interconnection agreements were entered into by OpenCape during the period. CapeNet, the OpenCape network operator, has entered into one interconnection agreement during this period. On additional interconnection agreements are planned at this time. | OpenCape has not entered into any additional transit agreements during this annual reporting period, and maintains a single interconnection agreement. No other peering and transit agreements are being negotiated by OpenCape. Transit agreements may be negotiated and added by the OpenCape network operator, CapeNet. No interconnection requests have been denied to either CapeNet or OpenCape. | TRUE
NT10BIX5570040 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 50M-10Gbps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 1 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 1 interconnection agreement (3) N/A | N/A | TRUE
NT10BIX5570040 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570040 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570040 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570041 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 50M-10Gbps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 1 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) N/A (3) N/A | N/A | TRUE
NT10BIX5570041 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 2 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570041 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570041 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570042 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 50M-10Gbps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 1 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreement (2) N/A (3) N/A | N/A | TRUE
NT10BIX5570042 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 2 interconnection agreements (2) 1 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570042 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570042 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570043 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 50M-10Gbps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 1 | 0 | 0 | [Please note under 9, it's actually <1 mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreement (2) N/A (3) N/A | N/A | TRUE
NT10BIX5570043 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 1 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570043 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570043 | 2013 | 0 | N/A | 0 | N/A | 0 | N/A | 10Gps | N/A | 0 | N/A | 50M-10Gps | N/A | 0 | N/A | Level 3 EON project will provide options for speeds of 50Mbps to 10Gbps to the last mile provider. | N/A | For the Level 3 EON BTOP project, Level 3 commits that it will follow the Nondiscrimination and Interconnection Obligations of the NOFA. Specifically, Level 3 will continue to: (a) adhere to the principles contained in the FCCâ€™s Internet Policy Statement (FCC 05-151, adopted August 5, 2005). Level 3 follows these principles in its day-to-day operations; (b) Not favor any lawful Internet applications and content over others. As a transport provider and especially in the role of providing those services in the middle mile, Level 3 does not monitor content on its network and investigates all allegations of unlawful content; (c) connect to the public internet directly or indirectly, such that the project is not a private closed network. Level 3 operates a significant backbone network within the United States, and can provide connectivity to the global Internet to any customers requesting such connectivity; (d) offer interconnection where technically feasible on the networks constructed by BTOP funds without exceeding current or reasonable anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [Please note under 9, it's actually < 1mile.] N/A | 0 | 0 | 0 | 0 | Level 3 will construct single or diverse fiber entrance duct systems, cable, and customer access manhole. The customer access manhole will be placed on Level 3â€™s side of the property line. Customers will bring their own metro/regional fiber to the manhole at the Level 3 property line, for the purpose of interconnecting with Level 3â€™s middle mile services. | 1 - Byers Engineering | For recipients managing multiple awards, they may find it helpful to set up a standing, cross-functional core team within the organization to ensure consistency of implementation across all of the awards. | Level 3 EON, LLC | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | (1) 0 interconnection agreements (2) 0 interconnection agreement (3)N/A | N/A | TRUE
NT10BIX5570044 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | While we have not started delivering services yet, in our proposal and in all of our discussions with NTIA and the public we have said that we would have 10 Gbps Middle Mile connections available. | 0 | While we have not started delivering services yet, in our proposal and in all of our discussions with NTIA and the public we have said that we would have 1 Gbps Last Mile connections available. | 0 | N/A - While we have no data yet, we expect the vast majority of our Middle Mile customers to have 1 Gbps connections so this numbers should be slightly more than 1 Gbps. | 0 | N/A - While we have no data yet, we expect the vast majority of our Last Mile customers to have 100 Mbps connections, so this number should be slightly more than 100 Mbps. | N/A - We have not delivered any services yet. When we do, we believe it will be a substantial increase for each Anchor Institution. We will track before and after bandwidths for each Anchor Institution, and can report the average percentages of those increases. | UC2B has not provided any retail services yet. The proposed retail services are detailed on the attached PDF file. In short, we will offer a base local symmetric Intranet connection that is as fast as the equipment will go - either 100 Mbps or 1 Gbps. In addition to that there are 5 tiers of symmetric Internet connectivity that start at $19.99 a month for a 5 Mbps Internet connection with a 100 Mbps Intranet connection and range up to $85.99 a month for a 40 Mbps Internet Connection with a 1 Gbps Intranet connection. Depending on the competitive landscape, those Internet bandwidth tiers may be adjusted upwards at the same price levels before we actually roll out services to our first service areas in the fall of 2011. Our issues with securing rights-of-way will not impact our ability to deliver services to some areas in the fall of 2011. Retail services across all eleven Census Block Groups will not be available until 2012. | We plan to provide QOS for all services that need it - such as VoIP and IPTV, but beyond that, no other prioritization of any traffic based on content, source or destination. The only bandwidth limitations will be through the tiers of Internet bandwidth that a customer subscribes to. We have not delivered any traffic yet, and therefore could not have blocked any, but we have pledged to never block any lawful content. Our management policies are on-line at: www.uc2b.net. | N/A - No customers to churn yet. | 36259 | 0 | 0 | 0 | 8379 | 5464 | 22416 | We agreed to provide dark fiber IRU's to the organizations that provided our local matching funds. The value of those IRU's determined each organization's "contribution". No lease or IRU agreements have been signed yet, but the number of proposed strand miles for each organization is in the attached PDF file. | 0 | 0 | 0 | 0 | UC2B will make 1/4th of a standard 7-foot telco rack available to each IRU holder for co-location in each of our two core nodes, so that they can co-locate equipment that connects to their fiber strands on our seven rings. We will have in excess of 350 splice points on our rings throughout the community, and any provider/customer will be able to diversely connect to our core network architecture from any of those ring spice points. The rings eliminate the need for any large central co-location facility. | We have made no sub-awards at this time. We plan to make two sub awards - one to the City of Urbana and one to the City of Champaign that will cover the costs of the backbone rings and fiber-to-the-curb construction in their respective communities. Each city will hire the contractors that will be working in that city on the UC2B project. No direct subcontracts or grants to SDB's are anticipated, but we fully expect SDB's to participate as primary or sub contractors on our fiber construction. The two cities have agreed to adopt the University's goal of 15% Minority and Female Business Enterprise (MAFBE) participation on this construction. | Lesson # 1: It is never too early to understand all of your easement challenges. While more than 90% of our project is within the city boundaries of Urbana and Champaign, some of our proposed backbone fiber routes extend beyond those cities' limits. In those unincorporated areas, it is not uncommon for a property owner to own the right-of-way all the way to the center of the road. Often the same applies to the other side of the road. To legally install underground fiber in the right-of-way along that road requires an easement from one or the other property owners. Each of our participating cities has its own easement negotiation process and the Federal government has a required process that must be followed as well for federally funded projects. None of those processes are are designed to be completed within the short time periods that are required by the BTOP grants. Our engineering firm will be creating construction bid documents based on a contracted, "easement-free" design, that only builds on city-owned right-of-way. Then we will have several alternates in those bid documents that can be activated if we are able to negotiate the private easements. From the perspective of public safety and economic development, the full design that requires the private easements is a preferable design, but if the acquisition of easements can not be completed in the time available, we will be forced to build the less desirable design. Lesson # 2: Communicate early and often and then again. We have a diverse group of people working toward the same goals on this project. Given the differing backgrounds, levels of understanding, experience, time, etc, it's a challenge to maintain an open, relevant dialog. UC2B is comprised of a major research University, and two cities that formed the Urbana-Champaign Big Broadband (UC2B) intergovernmental consortium. The University and the cities appointed the members of the UC2B Policy Board to represent their interests on the project. The Policy Board members appointed the members of the UC2B Technical Committee to advise them on technical issues. At any one time it is fair to say that not every Policy Board member nor every Technical Committee member fully understands every detail of the project. These are volunteer positions and often the people appointed to fill them already had over-subscribed professional and personal lives before they became involved with UC2B. There need to be recurring regular communications with these committee members to keep them on the same page. This is further complicated by the fact that there are elected and appointed officials in both cities as well as University administrators who also want to be in the loop. This project would benefit from someone working full-time just to keep all of these stakeholders informed, because out of necessity this project is moving at the speed of light (no pun intended), while cities and universities are more accustomed to and more comfortable with a more considered pace. Keeping stakeholders informed is made more complicated by by the Illinois Open Meetings Act, which pretty much outlaws discussions between UC2B committee members outside of pubic meetings. If there is a silver bullet for communications, we have not found it yet. The staff managing the grant is typically so busy with the day-to-day activities and planning that must be done to remain on schedule that there is little time or energy left over to tell people what they are doing. We did not budget for a "communications officer", but if there ever is a BTOP2 opportunity, that would be money well spent for any project. We do have a marketing and outreach subcommittee and they are doing a good job of planning for communications with the community about the value of Big Broadband and why families and business should subscribe, but probably nothing short of hiring someone whose primary responsibility is to communicate to our administrative stakeholders for the next two years will provide the level of information within the time frames that are desired. In the meanwhile those of us managing the grant must tell our story early and often and not worry about repeating ourselves. | University of Illinois | 38 | 4 | 1 | 1 | 34 | 31 |  | 93 | 80 | 12 | 294 | N/A | N/A | TRUE
NT10BIX5570044 | 2011 | 0 | We have not yet completed any of our middle mile fiber rings or laterals. Construction was delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We will also not receive our first fiber shipment until the first quarter of 2012. | 0 | We have not yet passed any of our FTTP households with fiber. Construction was delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We will also not receive our first fiber shipment until the first quarter of 2012. While this is not a metric that NTIA tracks, we have passed 1,613 households with conduit, which is roughly one third of the total in our Fiber-to-the-Premise (FTTP) service areas. | 0 | We have not yet completed any of our FTTP installations. Construction was delayed by the length of time it took for the Environmental Assessment, the fiber engineering and completing the RFP process for our construction contractors. We underestimated all three in our baseline plan. We will also not receive our first fiber shipment until the first quarter of 2012. | 10 Gbps | We will be able to deliver 10 Gbps (or partial 10 Gbps on a 10 Gbps link) ringed connections to major Anchor Institutions or businesses if they so desire. | 1 Gbps | All of our last mile FTTP customers will have a 1 Gbps connection to our local UC2B Intranet. Their Internet connectivity will be sold in tiers, starting with a 20 Mbps symmetric Internet connection and going up from there. | 20 Mbps | We expect almost all of our middle mile Anchor Institution customers to have a 20 Mbps Internet connection. (1 Gbps to the local Intranet.) A few will have larger Internet connections, but not enough to impact the average. | 20 Mbps | We expect almost all of our last-mile FTTP customers to have 20 Mbps Internet connections. (1 Gbps to the local Intranet.) A few will have larger connections, but not enough to raise the average. | We have not begun services to Anchor Institutions yet, but when we do, the minimum Internet speed available from UC2B will be a 20 Mbps symmetric service. That will be typically 2-10 times faster than what they receive today via DSL or cable modem. | UC2B does not provide any retail services yet. They will start in the 2nd quarter of 2012. We have attached our planned suite of retail services, but please also know that we are in the midst of a review of our pricing models and there is a good chance that we may make some adjustments in the weeks to come. We do know for sure that we will offer the 20 Mbps symmetric service to FTTP residential customers for $19.99 a month. We are looking at perhaps breaking out non-profits and government entities as well as for profit businesses and having different rate scales for each. We are also seeking to monetize a ringed, high-availability service that our equipment will allow us to provide. The UC2B Policy Board has hired a municipal broadband consultant (with non-grant funds) for this final business plan and service offering review. The consultant's report is due on February 15th. We expect the Board to act quickly on the recommendations, and finalize the remaining service offerings. | We have yet to offer any service and therefore have not been in a position to block anything. However, we have no plans to limit bandwidth utilization beyond the Internet rate limiting that is built into the tiers of service. We may implement Quality of Service (QOS)on some or all VLANS, but that by itself will not discriminate against any single user or class of users. | N/A | 24963 | 0 | 0 | 0 | 6256 | 5706 | 13001 | UC2B has not executed any IRU agreements yet, but we have letters of intent for IRU's from the following: City of Champaign - 637 strand miles, City of Urbana - 496 strand miles, University of Illinois - 900 strand miles, Unit 4 Schools - 290 strand miles, District 116 Schools - 164 strand miles, Champaign County - 252 strand miles, C-U Mass Transit District - 453 strand miles, Champaign Telephone Company - 453 strand miles, State of Illinois/ICN - 764 strand miles, State of Illinois/IDOT - 453 strand miles. Recently we entered into discussions with the Illinois Rural Health Network for 584 strand miles. | 850 | 754 | 0 | 96 | UC2B will be leasing space from the University in two UIUC Nodes for its core network equipment and for a minimal amount of collocation space for the routers of our Dark Fiber customers. In order to have as redundant a system as possible, our Dark Fiber customers will need to locate a small router that can terminate the fiber coming from the 7 rings in each of the two core nodes. We have allocated a quarter of a 7-foot-tall, 23"-inch-wide rack for each IRU customer. Beyond that, UC2B is not offering any collocation space. Instead, we are including diverse fiber transport on any of our seven rings as part of our service provider packages. If an ISP can get fiber to any one of the 400+ manholes on our seven backbone rings that will contain splice cases, they can connect redundantly to the UC2B network core and distribute their services. Additionally, service providers will be able to connect to UC2B in three University telecommunications nodes, where many of them already have facilities today. AT&T has a presence in all three nodes. Windstream and Champaign Telephone have presences in two of the nodes. ICN, Comcast, Pavlov Media and Volo Broadband have a presence in one of the nodes. There is also a group of private firms that is looking at constructing a data center / carrier hotel that will have dual connections to several of the UC2B rings, which by definition gets them access to all seven. Our seven fiber rings were designed to be able to redundantly connect any location on one ring to any location on any ring. Our seven ring design reduces the need for co-location and decentralizes service provider hardware. | UC2B has only made two sub-awards, and both were made to local municipalities - the Cities of Urbana and Champaign. The City of Urbana hired a prime contractor for the fiber construction in its city limits, and their prime contractor engaged the services of four small disadvantaged Minority and Female Business Enterprises (MAFBE) as subcontractors. They are: Electrical Resource Management (MBE), Southern Belle Electric and HVAC (MBE), Tepper Electric Supply Co. (FBE) and Groundhog Utility Construction, Inc. (FBE). The City of Champaign's prime contractor for the fiber construction in Champaign hired two FBE subcontractors. They are: Prairie Restorations, Inc. and Gordon Electric Supply, Inc. | This will not apply to all projects, but sub-awarding the construction with will happen in Champaign to the City of Champaign and sub-awarding the construction that will happen in Urbana to the City of Urbana has proved to be an excellent decision. Because the contractors report directly to the Public Works departments of each city, there is great communication between each contractor and its employing city, and issues are resolved quickly. Whether a contractor agrees or disagrees with a decision made by a city does not really matter, because at the end of the day the city is paying the contractor, and therefore the cities are getting what they want in their rights-of-ways, installed the way they want it installed. Municipalities that do not provide municipal-owned utilities do not necessarily have in-house expertise with underground utility construction. While they see it from a permitting and inspection perspective all the time, they can lack expertise in planning and implementation. One of our early hires was a retired fiber construction manager with more than 20 years of experience supervising fiber and copper utility construction. His expertise in the planning and daily implementation has been worth every dollar we pay him. He has been a vital link between the fiber construction crews and the cities' Public Works departments. | University of Illinois | 38 | 4 | 1 | 1 | 34 | 31 |  | 93 | 80 | 12 | 294 | N/A We have no completed interconnection agreements at this time. UC2B has always intended to interconnect with local providers and has published rates for doing so in our BTOP application. We are currently reviewing those rates one last time before we seek interconnection agreements. | N/A We have no completed peering or transit agreements at this time. We have started discussions with the University of Illinois about peering with the University and their local caching services such as Akamai. We have started discussions about peering with the Illinois Century Network. We are strong proponents of local peering, and certainly have not denied any request to peer, nor do we anticipate ever denying a request to peer. Our core network design has always included local peering connections. UC2B will be purchasing Internet transit in Chicago. | TRUE
NT10BIX5570044 | 2012 | $59,690 | This is substantially less than the $135,808 in our baseline plan, but there are several months of contractors' invoices that have not hit NTIA's books yet. This average will go up as those are processed. | $1,744 | This is slightly less than the $1,750 in our baseline plan. When the outstanding invoices are processed, this too will rise. | $11,008 | This is substantially more than the $4,062 in our baseline plan. As we connect more customers n the Fiber-to-the-Premise areas, this average will decrease. This reflects the high cost of getting the infrastructure up and down every street. At this point we are at less than one third of our customer projections, so this number will be high. | 10 Gbps | We offer up to 10 Gbps ports on layer-two services. | 200 Mbps | Our fastest retail service is 200 Mbps. | N/A | We have no existing Middle-Mile customers. Even though we are connecting some Anchor Institutions to our Middle-Mile fiber, we are treating them like Last-Mile customers. | 22.5 Mbps | This is the weighted average of the bandwidths subscribed to by all of our Last-Mile customers. Our network delivers its advertised speeds. | While we do not have exact data, we know that most of our CAIs have converted to UC2B from either a T-1, DSL or cable-modem connection. The fastest of those can offer speeds as fast as the slowest UC2B fiber tier on downloads, but those technologies are far slower on uploads. UC2B's download speeds at our slowest bandwidth could range from "equivalent" to 13 times faster. UC2B's upload speeds at our slowest bandwidth would be 20-40 times faster than either T-1, DSL or cable modems. | UC2B customers can self-self to subscribe to Consumer or Commercial tiers of services. The Commercial tiers provide more IPv4 public IP addresses and have greater bandwidth tiers. All UC2B customers have unlimited bandwidth to the UC2B Intranet, but have tiers of connectivity to the Internet. The customer CPE can deliver close to 900 Mbps to the Intranet. Consumer Internet connectivity is sold in 20, 30 and 40 Mbps tiers. 82.5% of our Consumer customers have elected a 20 Mbps symmetric connection. 10.3% have elected a 30 Mbps symmetric connection. 7.2% have elected a 40 Mbps symmetric connection. We have three subscribers who have chosen our Commercial services, two have 20 Mbps and one has 100 Mbps. UC2B's retail pricing plans are attached. | The only rate limiting done by UC2B is to enforce the tiers of Internet connectivity that a customer has subscribed to. We have never blocked any customer's access to any content or service, not do we ever intend to. We have had to remove customers from the network for failing to comply in a timely fashion with lawful requests to remove copyrighted content from their computers and cease sharing it. | We have lost 24 installed retail customers thus far out of a total customer base of 811 . That would give us a churn rate thus far of just less than 3%. Typically they have either been unsatisfied with their installation experience or the limited technical support UC2B has been able to provide them for customer owned equipment. We will be rebidding our Fiber-to-the-Premise (FTTP) construction to address the unacceptable installation experiences. Our monthly service rates are quite low, and allow us to be able to make sure the network is working, but do not allow us to be able to make sure that every device owned by a customer will always work on a UC2B connection. We understand that is a need, but it is not one that we can currently fill. | 24963 | 8611 | 897 | 15455 | 0 | 0 | 0 | We have two IRU agreements with Big Broadband Services. They total 897 strand miles. We are in negotiations for more IRUs, but those IRUs were not complete at the end of 2012. | 850 | 754 | 48 | 48 | UC2B is leasing space from the University in two of its Nodes for its core network equipment and for a minimal amount of collocation space for the routers of our Dark Fiber customers. In order to have as redundant a system as possible, our Dark Fiber customers will need to locate a small router that can terminate the fiber coming from the 7 rings in each of the two core nodes. We have allocated a quarter of a 7-foot-tall, 23"-inch-wide rack for each IRU customer's router. Beyond that, UC2B is not offering any collocation space. Service providers will be able to connect to UC2B in three of the University's telecommunications nodes, where many of them already have facilities today. AT&T and Champaign Telephone Company have presences in all three nodes. Windstream, US Signal and Metro Communications have presences in two of the nodes. The Illinois Century Network, Comcast, Pavlov Media and Volo Broadband have a presence in one of the nodes. We are also providing diverse fiber transport on any of our seven rings for service providers without facilities in the UIUC Nodes. If an ISP can get fiber to any one of the 400+ manholes on our seven backbone rings that contain splice cases, they can connect redundantly to the UC2B network core and distribute their services. A local provider is planning to build a data center / carrier hotel in the spring that will have dual connections to four of the seven main UC2B rings, which by definition gets them access to all seven. Our seven fiber rings were designed to be able to redundantly connect any location on one ring to any location on any ring. Our cotangent seven ring design reduces the need for co-location in our facilities and decentralizes service provider hardware. | UC2B has made two sub-awards, and both were made to local municipalities - the Cities of Urbana and Champaign. Urbana hired a prime contractor for the phase one fiber construction (all fiber in rights-of-way) in its city limits, and their prime contractor engaged the services of four small disadvantaged Minority and Female Business Enterprises (MAFBE) as subcontractors. They are: Electrical Resource Management (MBE), Southern Belle Electric and HVAC (MBE), Tepper Electric Supply Co. (FBE) and Groundhog Utility Construction, Inc. (FBE). Champaign's prime contractor for the phase one fiber construction hired two FBE subcontractors. They are: Prairie Restorations, Inc. and Gordon Electric Supply, Inc. Through their sub-award, City of Champaign handled the contracting for all the phase two construction (fiber from the curbs to the buildings) and hired PowerUp an MBE firm as the prime contractor. PowerUp also engaged Southern Belle Electric and HVAC (MBE) as a sub-contractor. | This will not apply to all projects, but sub-awarding the right-of-way construction with will happen in Champaign to the City of Champaign and sub-awarding the construction that will happen in Urbana to the City of Urbana has proved to be an excellent decision. Because the contractors report directly to the Public Works departments of each city, there is great communication between each contractor and its employing city, and issues are resolved quickly. Whether a contractor agrees or disagrees with a decision made by a city does not really matter, because at the end of the day the city is paying the contractor, and therefore the cities are getting what they want in their rights-of-ways, installed the way they want it installed. Municipalities that do not provide municipal-owned utilities do not necessarily have in-house expertise with underground utility construction. While they see it from a permitting and inspection perspective all the time, they can lack expertise in planning and implementation. One of our early hires was a retired fiber construction manager with more than 20 years of experience supervising fiber and copper utility construction. His expertise in the planning and daily implementation has been worth every dollar we pay him. He has been a vital link between the fiber construction crews and the cities' Public Works departments. | University of Illinois | 38 | 4 | 1 | 1 | 34 | 31 |  | 93 | 80 | 12 | 294 | We have not yet entered into any interconnection agreements, because we have not yet officially accepted our ring fiber from our contractors. We have not denied any requests, but we have not acted on any either. Once the fiber has been fully tested and accepted, we will move forward with the two informal interconnection requests that we have received. | UC2B has one peering arrangement - with the University of Illinois, but it is not a formal agreement. As the University is one of the three members of the UC2B Intergovernmental Consortium, we have not gone through the process of creating a formal agreement. Our legal team's time is scarce and there have been more pressing contractual things for them to work on. We have no other peering arrangements pending. | TRUE
NT10BIX5570044 | 2013 | $107,253.84 | This is substantially less than the $135,808 in our baseline plan. We had originally specified larger fiber cables and a spare conduit on the rings. Those elements were changed to reduce costs. | $1,616.44 | This is slightly less than the $1,750 in our baseline plan. | $10,220.57 | This is substantially more than the $4,062 in our baseline plan. Due to issues with landlords and UC2B's lack of a TV service, our take rate was substantially less than our projections. The base cost of building the infrastructure in the FTTP areas was divided by less than half of our projected number of subscribers, which more than doubled the cost per subscriber. | 10 Gbps | We offer up to 10 Gbps ports on layer-two services. | 200 Mbps | Our fastest retail service is 200 Mbps. | N/A | We have no existing Middle-Mile customers. Even though we are connecting many Anchor Institutions to our Middle-Mile fiber, we are provisioning them with electronics and are providing services to them just them like our Last-Mile FTTP customers. | 22.45 Mbps | This is the weighted average of the bandwidths subscribed to by all of our Last-Mile customers. Our network delivers its advertised speeds, and all service levels provide symmetrical bandwidth. | While we do not have exact data, we know that most of our CAI's have converted to UC2B fiber from either a T-1, DSL or cable-modem connections. The fastest of those technologies can offer speeds as fast as the slowest UC2B fiber tier on downloads, but those technologies are far slower on uploads. UC2B's download speeds at our slowest bandwidth could range from "equivalent" to 13 times faster. UC2B's upload speeds at our slowest bandwidth would be 20-40 times faster than either T-1, DSL or cable modems. | UC2B customers can self-determine to subscribe to Consumer or Commercial tiers of services. The Commercial tiers provide access to more IPv4 public IP addresses, have greater bandwidth tiers and offer reverse DNS. All UC2B customers have unlimited bandwidth to the UC2B Intranet, but have tiers of connectivity to the Internet. The customer CPE can deliver close to 900 Mbps to the Intranet. Consumer Internet connectivity is sold in 20, 30 and 40 Mbps tiers. 87.2% of all customers have elected a 20 Mbps symmetric connection. 9.7% of all customers have elected a 30 Mbps symmetric connection. 1.5% of all customers have elected a 40 Mbps symmetric connection. Additionally we have 17 commercial customers that have subscribed to faster tiers. There are 12 at 60 Mbps symmetrical, 4 customers at 100 Mbps symmetrical and 1 customer at 200 Mbps symmetrical. UC2B's retail pricing plans are attached. | The only bandwidth limiting done by UC2B is to enforce the tier of Internet connectivity that a customer has subscribed to. We have never blocked any customer's access to any content or service, not do we ever intend to. We also do no traffic prioritization, be it based on source, content or recipient. We have not prevented any customer from attaching any legal device to the network. We have had to remove some customers from the network for failing to comply in a timely fashion with lawful requests to remove copyrighted content from their computers and cease sharing it | We have lost 64 installed retail customers thus far out of a total customer base of 1,389 . That would give us a churn rate thus far of 4.61%. The most common reason for dropping UC2B service has been when customers move. However in some instances we have been able to sell UC2B service to the new occupants of rental units that are connected to UC2B fiber. Other customers cancelling service have either been unsatisfied with their installation experience or with the limited technical support UC2B has been able to provide them for customer-owned equipment. Our monthly service rates are quite low, and allow us to be able to make sure the network is working, but they do not allow us to be able to make sure that every device owned by a customer will always work on a UC2B connection. We understand that is a need, but it is not one that we can currently fill. | 31005 | 5297 | 5277 | 20431 | 0 | 0 | 0 | UC2B wholesales dark fiber to six service providers and to five public entities. We have two IRU agreements with Big Broadband Services and recently amended one of those agreements adding strand miles. Their combined agreements now total 1,075.89 miles. We have an IRU agreement with the Central Illinois Regional Broadband Network for 69.93 strand miles. We have an IRU agreement with the State of Illinois Department of Central Management Services - Illinois Century Network (CMS/ICN) for 343.65 strand miles. We have an IRU agreement with PEG Bandwidth for 201.58 strand miles. We lease 19.39 strand miles of dark fiber on a short-term lease to Volo Broadband. We also lease 22.96 strand-miles of dark fiber on a short-term lease to Metro Communications. We also have or will soon have IRU agreements with the University of Illinois, the City of Champaign, the City of Urbana, the Champaign-Urbana Mass Transit District (MTD), and Champaign County totalling 3,293.53 strand miles. Those five public entities are not Internet Service Providers, but rather use the fiber for internal communications and distributing Internet among their various locations in our community. | 850 | 754 | 40 | 8 | UC2B is leasing space from the University in two of its Nodes for its core network equipment and for a minimal amount of collocation space for the routers of our dark fiber customers. In order to have as redundant a system as possible, our dark fiber customers need to locate a small router that can terminate the fiber coming from the 7 rings (and their subrings) in each of the two core nodes. We have allocated a quarter of a 7-foot-tall, 23"-inch-wide rack for each IRU customer's router. Beyond that, UC2B is not offering any collocation space. UC2B does also have fiber cross-connect panels in a third University node on two inter-nodal fiber cables to facilitate connections to the Illinois Century Network, the University itself, AT&T, Comcast, Windstream, Champaign Telephone Company, Metro Communications and Pavlov Media, who all have facilities in that node. Service providers will be able to connect to UC2B in those three University's telecommunications nodes, where many of them already have facilities today. The Illinois Century Network, AT&T and Champaign Telephone Company have presences in all three nodes. Windstream, US Signal, Peg Bandwidth and Metro Communications have (or will have) presences in two of the nodes. Comcast, and Volo Broadband have presences in one of the nodes. We are also providing diverse fiber transport on any of our seven rings for service providers without facilities in the UIUC Nodes. If an ISP can get fiber to any one of the 400+ manholes on our seven backbone rings that contain splice cases, they can lease dark UC2B fiber strands to connect redundantly to the UC2B network core and distribute their services. A local provider is planning to build a data center / carrier hotel in 2014 that will have diverse connections to four of the seven main UC2B rings, which by definition gets them access to all seven. Our seven fiber rings were designed to be able to redundantly connect any location on one ring to any location on any ring. Our cotangent seven ring design reduces the need for co-location in our facilities and decentralizes service provider hardware. A simplified diagram of the ring design, the inter-nodal cables and the three nodes is attached. | UC2B has made two sub-awards, and both were made to local municipalities - the Cities of Urbana and Champaign. Urbana hired a prime contractor for the phase one fiber construction (all fiber in rights-of-way) in its city limits, and their prime contractor engaged the services of four small disadvantaged Minority and Female Business Enterprises (MAFBE) as subcontractors. They were: Electrical Resource Management (MBE), Southern Belle Electric and HVAC (MBE), Tepper Electric Supply Co. (FBE) and Groundhog Utility Construction, Inc. (FBE). Champaign's prime contractor for the phase one fiber construction hired two FBE subcontractors. They are: Prairie Restorations, Inc. and Gordon Electric Supply, Inc. Through their sub-award, City of Champaign handled the contracting for all the phase two construction (fiber from the curbs to the buildings) and hired PowerUp an MBE firm as the prime contractor. PowerUp also engaged Southern Belle Electric and HVAC (MBE) as a sub-contractor. | This will not apply to all projects, but sub-awarding the right-of-way construction that happened in Champaign to the City of Champaign and sub-awarding the construction that happened in Urbana to the City of Urbana has proved to be an excellent decision. Because the contractors reported directly to the Public Works departments of each city, there was great communication between each contractor and its employing city, and issues were resolved quickly. Whether a contractor agrees or disagrees with a decision made by a city does not really matter, because at the end of the day the city is paying the contractor, and therefore the cities are getting what they want in their rights-of-ways, installed the way they want it installed. Municipalities that do not provide municipal-owned utilities do not necessarily have in-house expertise with underground utility construction. While they see it from a permitting and inspection perspective all the time, they can lack expertise in planning and implementation. One of our early hires was a retired fiber construction manager with more than 20 years of experience supervising fiber and copper utility construction. His expertise in the planning and daily implementation has been worth every dollar we pay him. He has been a vital link between the fiber construction crews and the cities' Public Works departments. | University of Illinois | 38 | 4 | 1 | 1 | 34 | 31 |  | 93 | 80 | 12 | 294 | In 2013, we signed agreements with and interconnected with four service providers - Champaign Telephone Company, Metro Communications, the Illinois Century Network (ICN)and the Central Illinois Regional Broadband Network (CIRBN). In early 2014, we also signed agreements with and interconnected with PEG Bandwidth and Volo Broadband, for a total of six interconnections with service providers as of this reporting. There are no other interconnection agreements currently being negotiated. UC2B has not denied any requests for interconnection. | UC2B has three peering arrangements, although they are not formal agreements. UC2B peers with the University of Illinois, the Illinois Century Network and Champaign Telephone Company. All three organizations lease dark fiber from UC2B and peer with UC2B's network core. UC2B supports local peering and encourages all local providers to peer with UC2B and its peering partners. UC2B is not providing transit for any other service providers, but UC2B purchases transit from Cogent in Chicago and from US Signal in Champaign. | TRUE
NT10BIX5570045 | 2010 | 0 | We received an Environmental Assessment (EA) Finding of No Significant Impact (FONSI) on 12/23/10 such that no construction occurred in 2010 | 0 | N/A | 0 | N/A | 0 | We received an Environmental Assessment (EA) Finding of No Significant Impact (FONSI) on 12/23/10 such that no construction occurred in 2010. We are offering dark fiber such that speed can be anything from 10Mb to 100Gbps. | 0 | N/A | 0 | We received an Environmental Assessment (EA) Finding of No Significant Impact (FONSI) on 12/23/10 such that no construction occurred in 2010 and our 1 wholesale contract has not begun using MUFN (BTOP-funded) facilities yet. | 0 | N/A | N/A - we received a FONSI on 12/23/10 such that we did not perform any construction in 2010 with BTOP funds. | N/A - MUFN is a middle-mile project and is not providing retail services directly to the public. Our pricing plan is attached for the wholesale services we are offering. | MUFN offers wireline services via fiber optic strands consistent w/ the NTIA BTOP NOFA non-discrimination & network interconnection obligations. MUFN supports network neutrality and will not limit, restrict, prioritize or otherwise hinder system usersâ€™ access to any lawful Internet content, applications or services of their choice except for reasonable system preservation purposes (e.g. security events). System users, at their full expense, will be permitted to connect their choice of hardware to dark fiber strands, provided such hardware does not adversely affect the use by and/or electronic or optronic equipment of other system users. General network management policies include: users must pay all initial and ongoing costs to connect to MUFN facilities; system users can request interconnect at MUFN system manholes, handholes, identified interconnection â€œwire serving or terminationâ€ locations and other splice points as determined by MUFN and designated in the course of negotiation; MUFN may route system user fiber through its facilities at MUFNâ€™s sole discretion, provided such routing does not materially impact system userâ€™s use of facilities; system users shall execute a separate agreement with reasonable terms and conditions for interconnection of MUFN facilities with a 3rd party facilities; MUFN, with 120 day notice and minimized disruption to system user, may at its sole option and full expense, substitute fiber on any fiber segment(s) or portions thereof wi | N/A | 6057 | 161 | 0 | 1578 | 240 | 1845 | 2473 | Mad City Broadband is currently our only wholesale customer. We have not leased any fiber strand-miles to them yet as we did not receive a FONSI until 12/23/10 and therefore did not build any fiber plant yet (and they have not looked to use our existing in-kind plant yet either). | 13858 | 13645 | 0 | 213 | MUFN does not have a collocation service offering. Rather, our plan is to permit entities to interconnect to existing and grant-funded fiber infrastructure at over 105 interconnect points (splice cases, patch panels within CAI facilities, Internet peering points). We have leased space at Network222 (an Internet peering point) where other commercial entities offer collocation space within the building (i.e. 5Nines data center, Fiore Company) and other network providers/customers can cross-connect to fiber infrastructure in our leased collocation space (many already do). Finally, individual MUFN consortium members are permitted to negotiate privately with other network providers and customers to offer collocation services within their facility as permitted by law and executive management/board of directors. | We have not made any subcontracts/sub grants to socially and economically disadvantaged small businesses. | 1. Perform engineering study for aerial fiber installations before hiring a contractor to furnish and install materials such that construction vendors will be able to bid jobs tighter than if engineering is not performed (buffer added). 2. Plot/use of GIS maps with portable shapefiles has been very helpful in order to overlay streets, other utilities, environmental assessment data (i.e. brownfields, wetlands, land use). 3. Sharing of information (i.e. RFPs/bids, problems) among affinity groups such as higher education and state education and research networks has been extremely useful. | University of Wisconsin System | 51 | 6 | 3 | 6 | 19 | 19 |  | 35 | 64 | 3 | 206 | MUFN has entered into 1 interconnection agreement during the reporting period. We are currently and actively negotiating 2 additional interconnection agreements. We have not denied any request for interconnection. | MUFN has entered into 3 peering agreements at the Network222 Internet peering point we identified in our original proposal to NTIA. We have not entered into any transit agreements. We are not currently negotiating any additional peering or transit agreements and have not denied any requests for peering and transit agreements during the reporting period. | TRUE
NT10BIX5570045 | 2011 | 150185 | MUFN new mileage construction is behind schedule due to delays in obtaining an EA FONSI. The result is completion of several miles of fiber installs JUST after the end of 4Q2011 (lower denominator) though many expenses (numerator) are reflected in our costs at end of 4Q2011. Also, we removed 12.6% of our full in-kind match in the numerator (3.25mi/25.75 miles of conduit match * $3,223,242) so we exclude from the numerator the portion of MUFN (phase 3) that has not been started yet. We are also excluding $91,124 in the numerator for admin/engineering expenses. ($4355377 / 29 miles) | 0 | N/A | 0 | N/A | 10Gbps | We are offering dark fiber. | 0 | N/A | 1Gbps | Currently, all subscribers are lit at 1Gbps. | 0 | N/A | N/A - MUFN is a dark fiber project middle mile project such that we are not providing specific broadband speeds to members. However, most CAIs connected via MUFN to the Internet are increasing their connectivity by at least 10 times (100Mb to 1Gbps) if not as much as 667 times (1.5Mb to 1Gbps). | N/A - MUFN is a middle-mile project and is not providing retail services directly to the public. Our pricing plan is attached for the wholesale services we are offering. | MUFN is providing dark fiber services. We support ubiquitous and pervasive network access that is open and affordable using open, standard protocols. MUFN supports network neutrality and will not limit, restrict, prioritize or otherwise hinder system usersâ€™ access to any lawful Internet content, applications or services of their choice except for reasonable system preservation purposes (e.g. security events). Rather, we offer services on a best effort basis with all services subject to the legal needs of law enforcement. MUFN has never limited or blocked consumers from accessing any lawful content, service, service provider or application or prevented any consumers from attaching any legal device to the network. | MUFN has not had any subscribers drop service though we have had a total of 5 CAIs (5.1%) request we not install fiber to their facility. All 5 were dropped due to planned office consolidation for budget reasons. | 6057 | 161 | 50 | 4228 | 93 | 450 | 1075 | MUFN has 2 wholesale customers (Mad City Broadband and WI Independent Network (WINs). Neither entity has leased any fiber yet as our fiber builds were completed late in 3Q2011 and predominantly in 4Q2011 due to delays in obtaining an EA FONSI. | 13858 | 13645 | 0 | 213 | MUFN does not have a collocation service offering. Rather, our plan is to permit entities to interconnect to existing and grant-funded fiber infrastructure at over 105 interconnect points (splice cases, patch panels within CAI facilities, Internet peering points). We have leased space at Network222 (an Internet peering point) where other commercial entities offer collocation space within the building (i.e. 5Nines data center, Fiore Company) and other network providers/customers can cross-connect to fiber infrastructure in our leased collocation space (many already do). Finally, individual MUFN consortium members are permitted to negotiate privately with other network providers and customers to offer collocation services within their facility as permitted by law and executive management/board of directors. | We have not made any subcontracts/sub grants to socially and economically disadvantaged small businesses. | 1. Perform engineering study for aerial fiber installations before hiring a contractor to furnish and install materials such that construction vendors will be able to bid jobs tighter than if engineering is not performed (buffer added). 2. Plot/use of GIS maps with portable shapefiles has been very helpful in order to overlay streets, other utilities, environmental assessment data (i.e. brownfields, wetlands, land use). 3. Sharing of information (i.e. RFPs/bids, problems) among affinity groups such as higher education and state education and research networks has been extremely useful. 4. Participating in groups performing similar BTOP CCI projects (e.g. Internet2 BTOPers) is helpful to discuss issues. 5. Attending NTIA BTOP events. 6. Meeting with area governmental traffic engineering groups to understand road construction plans and install conduit as part of those projects (when road is open) has been VERY helpful to reduce project costs and coordinate schedules. 7. Meeting with government leaders and the permitting offices of local jurisdictions has been helpful to ease permitting and right-of-way issues. | University of Wisconsin System | 51 | 6 | 3 | 6 | 19 | 19 |  | 35 | 64 | 3 | 206 | MUFN has entered into 1 new interconnection agreement during the reporting period. We are currently negotiating 7 additional interconnection agreements. We have not denied any request for interconnection. | We have entered into 3 peering agreements at the Network222 Internet peering point we identified in our original proposal to NTIA. We have not entered into any transit agreements. We are not currently negotiating any additional peering or transit agreements and have not denied any requests for peering and transit agreements during the reporting period. | TRUE
NT10BIX5570045 | 2012 | 115884 | We note our original baseline of $62,245 is not calculated correctly and includes (31.25) leased miles in denominator and excludes our in-kind contribution match. Recalculating this correctly, our original baseline should have been $152,811. Also, we received approval in Dec 2012 for a route change that adds 18.25 miles. This will bring down our average cost/mile in the next Annual PPR report. | 0 | N/A | 0 | N/A | 0 | We are offering dark fiber such that speeds can be anything from 10Mb to 100Gbps. Most CAIs and commercial groups are selecting 1Gbps with some at 10Gbps. | 0 | N/A | 0 | We are offering dark fiber such that speeds can be anything from 10Mb to 100Gbps. Most CAIs and commercial groups are selecting 1Gbps with some at 10Gbps. | 0 | N/A | N/A - MUFN is a dark fiber project middle mile project such that we are not providing specific broadband speeds to members. However, most CAIs connected via MUFN to the Internet are increasing their connectivity by at least 100 times (10Mb to 1Gbps) if not as much as 667 times (1.5Mb to 1Gbps). | N/A - MUFN is a middle-mile project and is not providing retail services directly to the public. Our pricing plan is attached for the wholesale services we are offering. | MUFN is providing dark fiber services. We support ubiquitous and pervasive network access that is open and affordable using open, standard protocols. MUFN supports network neutrality and will not limit, restrict, prioritize or otherwise hinder system usersâ€™ access to any lawful Internet content, applications or services of their choice except for reasonable system preservation purposes (e.g. security events). Rather, we offer services on a best effort basis with all services subject to the legal needs of law enforcement. MUFN has never limited or blocked consumers from accessing any lawful content, service, service provider or application or prevented any consumers from attaching any legal device to the network. | MUFN has not had any subscribers drop service though we have had a total of 5 CAIs (5.1%) request we not install fiber to their facility. All 5 were dropped due to planned office consolidation for budget reasons. | 10829 | 674 | 0 | 6952 | 256 | 173 | 2774 | MUFN has 2 wholesale customers (Mad City Broadband and WI Independent Network (WINs). Neither entity has leased any fiber yet as they are currently building laterals and other connections into the MUFN middle-mile infrastructure. | 13858 | 13645 | 0 | 213 | MUFN does not have a collocation service offering. Rather, our plan is to permit entities to interconnect to existing and grant-funded fiber infrastructure at over 105 interconnect points (splice cases, patch panels within CAI facilities, Internet peering points). We have leased space at Network222 (an Internet peering point) where other commercial entities offer collocation space within the building (i.e. 5Nines data center, Fiore Company) and other network providers/customers can cross-connect to fiber infrastructure in our leased collocation space (many already do). Finally, individual MUFN consortium members are permitted to negotiate privately with other network providers and customers to offer collocation services within their facility as permitted by law and executive management/board of directors. | We have not made any subcontracts/sub grants to socially and economically disadvantaged small businesses. | 1. Perform engineering study for aerial fiber installations before hiring a contractor to furnish and install materials such that construction vendors will be able to bid jobs tighter than if engineering is not performed (buffer added). 2. Plot/use of GIS maps with portable shapefiles has been very helpful in order to overlay streets, other utilities, environmental assessment data (i.e. brownfields, wetlands, land use). 3. Sharing of information (i.e. RFPs/bids, problems) among affinity groups such as higher education and state education and research networks has been extremely useful. 4. Participating in groups performing similar BTOP CCI projects (e.g. Internet2 BTOPers) is helpful to discuss issues. 5. Attending NTIA BTOP events. 6. Meeting with area governmental traffic engineering groups to understand road construction plans and install conduit as part of those projects (when road is open) has been VERY helpful to reduce project costs and coordinate schedules. 7. Meeting with government leaders and the permitting offices of local jurisdictions has been helpful to ease permitting and right-of-way issues. | University of Wisconsin System | 51 | 6 | 3 | 6 | 19 | 19 |  | 35 | 64 | 3 | 206 | MUFN has entered into 2 new interconnection agreement during the reporting period. We are currently negotiating 6 additional interconnection agreements. We have not denied any request for interconnection. | We have entered into 3 peering agreements at the Network222 Internet peering point we identified in our original proposal to NTIA. We have not entered into any transit agreements. We are not currently negotiating any additional peering or transit agreements and have not denied any requests for peering and transit agreements during the reporting period. | TRUE
NT10BIX5570045 | 2013 | 98302 | We note our original baseline of $62,245 is not calculated correctly and includes (31.25) leased miles in denominator and excludes our in-kind contribution match. Recalculating this correctly, our original baseline should have been $152,811. Also, we received approval in Dec 2012 for a route change that adds 18.25 miles of fiber installed in existing conduit. | 0 | N/A | 0 | N/A | 0 | We are offering dark fiber such that speeds can be anything from 10Mb to 100Gbps. Most CAIs and commercial groups are selecting 1Gbps with some at 10Gbps. | 0 | N/A | 0 | We are offering dark fiber such that speeds can be anything from 10Mb to 100Gbps. Most CAIs and commercial groups are selecting 1Gbps with some at 10Gbps or multiple wavelengths via dense wave division multiplexing (DWDM) | 0 | N/A | N/A - MUFN is a dark fiber project middle mile project such that we are not providing specific broadband speeds to members. However, most CAIs connected via MUFN to the Internet are increasing their connectivity by at least 100 times (10Mb to 1Gbps) if not as much as 667 times (1.5Mb to 1Gbps). | N/A - MUFN is a middle-mile project and is not providing retail services directly to the public. Our pricing plan is attached for the wholesale services we are offering. | MUFN is providing dark fiber services. We support ubiquitous and pervasive network access that is open and affordable using open, standard protocols. MUFN supports network neutrality and will not limit, restrict, prioritize or otherwise hinder system usersâ€™ access to any lawful Internet content, applications or services of their choice except for reasonable system preservation purposes (e.g. security events). Rather, we offer services on a best effort basis with all services subject to the legal needs of law enforcement. MUFN has never limited or blocked consumers from accessing any lawful content, service, service provider or application or prevented any consumers from attaching any legal device to the network. | MUFN has not had any subscribers drop service though we have had a total of 5 CAIs (5.1%) request we not install fiber to their facility. All 5 were dropped due to planned office consolidation for budget reasons. | 10829 | 124 | 1006 | 9699 | 0 | 0 | 0 | MUFN has 2 wholesale customers (Mad City Broadband and WI Independent Network (WINs). Neither entity has leased any fiber yet as they are currently building laterals and other connections into the MUFN middle-mile infrastructure. | 13858 | 13645 | 0 | 213 | MUFN does not have a collocation service offering. Rather, our plan is to permit entities to interconnect to existing and grant-funded fiber infrastructure at 100 interconnect points (splice cases, patch panels within CAI facilities, Internet peering points). We have leased space at Network222 (an Internet peering point) where other commercial entities offer collocation space within the building (i.e. 5Nines data center, Fiore Company) and other network providers/customers can cross-connect to fiber infrastructure in our leased collocation space (many already do). Finally, individual MUFN consortium members are permitted to negotiate privately with other network providers and customers to offer collocation services within their facility as permitted by law and executive management/board of directors. | We have not made any subcontracts/sub grants to socially and economically disadvantaged small businesses. | 1. Perform engineering study for aerial fiber installations before hiring a contractor to furnish and install materials such that construction vendors will be able to bid jobs tighter than if engineering is not performed (buffer added). 2. Plot/use of GIS maps with portable shapefiles has been very helpful in order to overlay streets, other utilities, environmental assessment data (i.e. brownfields, wetlands, land use). 3. Sharing of information (i.e. RFPs/bids, problems) among affinity groups such as higher education and state education and research networks has been extremely useful. 4. Participating in groups performing similar BTOP CCI projects (e.g. Internet2 BTOPers) is helpful to discuss issues. 5. Attending NTIA BTOP events. 6. Meeting with area governmental traffic engineering groups to understand road construction plans and install conduit as part of those projects (when road is open) has been VERY helpful to reduce project costs and coordinate schedules. 7. Meeting with government leaders and the permitting offices of local jurisdictions has been helpful to ease permitting and right-of-way issues. 8. Advertise permit meetings in the newspaper to increase awareness of project and reduce surprises to neighborhoods. | University of Wisconsin System | 51 | 6 | 3 | 6 | 19 | 19 |  | 35 | 64 | 3 | 206 | MUFN has entered into 2 new interconnection agreement during the reporting period. We are currently negotiating 7 additional interconnection agreements. We have not denied any request for interconnection. | We have entered into 3 peering agreements at the Network222 Internet peering point we identified in our original proposal to NTIA. We have not entered into any transit agreements. We are not currently negotiating any additional peering or transit agreements and have not denied any requests for peering and transit agreements during the reporting period. | TRUE
NT10BIX5570046 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | $40 per Mbps for 1000Mbps | 0 variance | 0 | N/A | $40 per Mbps for 100Mbps | 0 variance | 0 | N/A | N/A | N/A | N/A | N/A | 131040 | 0 | 0 | 0 | 0 | 0 | 131040 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | We've learned it has worked well selecting a firm that can perform both the environmental assessment as well as the construction design. There have been several case that having access to the immediate internal collaboration within the same firm has avoided environmental concerns that could be mitigated by construction techniques. | Louisiana Board of Regents | 253 | 49 | 15 | 0 | 273 | 237 |  | 37 | 385 | 0 | 1249 | N/A | N/A | TRUE
NT10BIX5570046 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | $40 /1000Mbps | 0 variance | 0 | N/A | $40 /100Mbps | 0 variance | 0 | N/A | N/A | N/A | N/A | N/A | 131040 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Louisiana Board of Regents | 253 | 49 | 15 | 0 | 273 | 237 |  | 37 | 385 | 0 | 1249 | N/A | N/A | TRUE
NT10BIX5570047 | 2010 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | (a.)-N/A (b.)-No | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | None at this point in the project. | None at this time. | Northwest Open Access Network | 55 | 59 | 6 | 4 | 61 | 17 |  | 54 | 21 | 1 | 278 | (1)-3 (2)-1 Interconnection agreement currently being negotiated. (3)- No, we have not denied requests for interconnection. | N/A | TRUE
NT10BIX5570047 | 2011 | $30,892 | Baseline-$78,747 - Completion of a Sub Participant Route in Northwest Washington is complete and In Service for calculation purposes but is not a good indicator for the true cost per mile calculation for the complete project. | N/A | N/A | N/A | N/A | 1 Gig | Meeting Baseline projections. | N/A | N/A | 100 Mbps | Meeting Baseline projections. This number was calculated using the average of the current subscribers. Speeds from 10 Meg to 1 Gig are being provided. | N/A | N/A | On average the increase in broadband speed was just over 10 Meg for the Community Anchor Institutions connected over the past year. Most AI's were utilizing traditional copper T1 services and are upgrading to ethernet services from NoaNet and it's participants with 10 Meg being the lowest speed product offered. | Noanet is a wholesale provider and not authorized to provide retail services. The services provided are to retail service providers with an array of services including Broadband Internet, Wave/Lambda, TDM, Ethernet, and Collocation. Pricing Plans are established by each individual provider and are attached as Confidential and Proprietary information. | a.) NoaNet does not apply any bandwidth shaping or network management-control mechanisms unless specifically requested by the customer. Interface limits of 100Meg or 1-Gig will apply as a hard cap on usage, depending on interface type used on customer connection. b.) NoaNet has not limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | N/A | 88416 | 720 | 0 | 0 | 87696 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A Northwest Open Access Network will be installing POP and BTOP funded Interconnection equipment in quarters 1 and 2 of 2012. This metric will appear in future reports based upon feedback received from NTIA. | N/A | None at this time in the project. | Northwest Open Access Network | 55 | 59 | 6 | 4 | 61 | 17 |  | 54 | 21 | 1 | 278 | 1. 6 Interconnection Agreements as Wholesale Providers with Capacity Provisioning Inc., Columbia County, Olmpus Net, Spectrum, Touchet Valley TV, and WCI. 2. 1 3. No, we have not denied requests for interconnection. | 4 Transit Agreements-NoaNet currently has transit agreements with four companies: NTT, Ti Net, Cogent, and Spectrum. 3 Peering Agreements with Google, Microsoft, and SIX. | TRUE
NT10BIX5570047 | 2012 | $68,836 | This is under the projected cost per mile estimate of $78,747. | N/A | N/A | N/A | N/A | 100 Gig | Exceeding Baseline projections. | N/A | N/A | 100 Mbps | Meeting Baseline projections. This number was calculated using the average of the current subscribers. Speeds from 10 Meg to 1 Gig are being provided. | N/A | N/A | On average the increase in broadband speed was just over 10 Meg for the Community Anchor Institutions connected over the past year. Most AI's were utilizing traditional copper T1 services and are upgrading to ethernet services from NoaNet and it's participants with 10 Meg being the lowest speed product offered. | Noanet is a wholesale provider and not authorized to provide retail services. The services provided are to retail service providers with an array of services including Broadband Internet, Wave/Lambda, TDM, Ethernet, and Collocation. Pricing Plans are established by each individual provider and are attached as Confidential and Proprietary information. | a.) NoaNet does not apply any bandwidth shaping or network management-control mechanisms unless specifically requested by the customer. Interface limits of 100Meg or 1-Gig will apply as a hard cap on usage, depending on interface type used on customer connection. b.) NoaNet has not limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | N/A | 75744 | 4500 | 0 | 67500 | 3744 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | POP and Interconnection locations via BTOP funded equipment are identified on the attached addendum to this report in various strategic areas as outlined and noted as City Pairs. Anyone wishing to inquire further may contact Northwest Open Access Network by visiting our website at noanet.net. | N/A | None at this time. | Northwest Open Access Network | 55 | 59 | 6 | 4 | 61 | 17 |  | 54 | 21 | 1 | 278 | 1.) None 2.) N/A 3.) N/A | 1.) One (1) Netflix CDN 2.) N/A 3.) N/A | TRUE
NT10BIX5570047 | 2013 | $73,719 | This is under the projected cost per mile estimate of $78,747. | N/A | N/A | N/A | N/A | 100 Gig | Exceeding Baseline Projections. | N/A | N/A | 100 Mbps | Meeting Baseline Projections. This number was calculated using the average of the current subscribers. Speeds from 10 Meg to 1 Gig are being provided. | N/A | N/A | On average the increase in broadband speed was just over 10 Meg for the Community Anchor Institutions connected over the past year. Most CAI's were utilizing traditional copper T1 Services and are being upgraded to ethernet services from NoaNet and it's sub-recipients with 10 Meg being the lowest speed product offered. | Noanet is a wholesale provider and not authorized to provide retail services. The services provided are to retail service providers with an array of services including Broadband Internet, Wave/Lambda, TDM, Ethernet, and Collocation. Pricing Plans are established by each individual provider and are attached as Confidential and Proprietary information. | a.) NoaNet does not apply any bandwidth shaping or network management-control mechanisms unless specifically requested by the customer. Interface limits of 100Meg or 1-Gig will apply as a hard cap on usage, depending on interface type used on customer connection. b.) NoaNet has not limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | N/A | 74880 | 74880 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | POP and Interconnection locations via BTOP funded equipment are identified on the attached addendum to this report in various strategic areas as outlined and noted as City Pairs. Anyone wishing to inquire may contact Northwest Open Access Network by visiting our website at noanet.net. | N/A | None at this time. | Northwest Open Access Network | 55 | 59 | 6 | 4 | 61 | 17 |  | 54 | 21 | 1 | 278 | 1.) None 2.) N/A 3.) N/A | 1.) One (1) - Fatbeam 2.) N/A 3.) N/A | TRUE
NT10BIX5570049 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A network not yet constructed | N/A network not yet constructed | N/A network not yet constructed | N/A network not yet constructed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A network not yet constructed | 0 | 0 | 0 | 0 | N/A network not yet constructed | N/A - no subgrants provided | Lessons learned include planning for environmental compliance early in the project as this task may take much longer than anticipated. | Nelson, County of | 4 | 1 | 0 | 0 | 2 | 5 |  | 9 | 2 | 0 | 23 | N/A no agreements entered into | N/A no agreements entered into | TRUE
NT10BIX5570049 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A, network not yet constructed | N/A, network not yet constructed | N/A, network not yet constructed | N/A, network not yet constructed | 4464 | 0 | 0 | 0 | 4464 | 0 | 0 | N/A, network not yet constructed | 0 | 0 | 0 | 0 | N/A, network not yet constructed | N/A, no sub grants provided in this project | Lessons learned include planning for environmental compliance early in the project. | Nelson, County of | 4 | 1 | 0 | 0 | 2 | 5 |  | 9 | 2 | 0 | 23 | N/A, no agreements entered into | N/A, no agreements entered into | TRUE
NT10BIX5570049 | 2012 | 57,442 | Variance due to increase in construction costs to deploy all fiber underground in conduit rather than primarily aerial as initially proposed. | 0 | N/A | 0 | N/A: The county is not providing services on the network. | 1 Gbps | No variance | 0 | N/A: The county is not providing services on the network. | 0 | N/A: The county is not providing services on the network and no private providers have begun offering services. Network testing confirms 1 Gbps capability. | 0 | N/A: The county is not offering services on the network. | Currently Nelson County is providing 10 Mbps Internet service to their facilities across the middle mile network. Previously each of those county facilities was capable of receiving only 1.5 Mbps T1 service. The remaining community anchor institutions are to be served by private providers at speeds desired up to 1 Gbps. | No retail services are provided. | The County has contracted with Blue Ridge InterNetworks for third party network operation services. Rates for transport have been established by the County and agreements used to govern contractual relationships and network use policies. Bandwidth is limited only by the capability of the electronics (currently 1 Gbps). No private providers are serving customers from the middle mile network currently. No limiting or blocking has occurred. | Not applicable. The County is not a service provider on this network. | 4464 | 0 | 0 | 0 | 4464 | 0 | 0 | No dark fiber has been leased although capacity is available if desired. | 392 | 84 | 36 | 272 | The County does provide collocation space for interconnection at the Lovingston network operating center. Additional interconnection points are at the Colleen, Afton, Avon, and Lovingston equipment shelters and network cabinets. Two providers are currently collocated in the Lovingston network operating center only. | No subgrants or subcontracts have been made by the recipient to SDB concerns. | All aspects of implementing the broadband network were new for Nelson County personnel. The most important lesson learned is that it is crucial for elected officials to be engaged in the project early and to be aware of all aspects of ongoing implementation for effective communication with constituents and timely approval of any resolutions or decisions to keep the project on schedule. | Nelson, County of | 4 | 1 | 0 | 0 | 2 | 5 |  | 9 | 2 | 0 | 23 | The County has entered into interconnection agreements with two providers to date, Lumos Networks and Blue Ridge InterNetworks. One additional interconnection agreement is currently being negotiated. No requests for interconnection have been denied. | No peering or transit agreements were proposed or completed. Interconnection agreements have been completed with Lumos Networks and Blue Ridge InterNetworks, and Lumos has completed interconnection of their facilities in the Lovingston network operating center. An initial 25 Mbps Internet circuit is available from Lumos for wholesale services to private providers who wish to use the middle mile network. | TRUE
NT10BIX5570049 | 2013 | 57,442 | Variance due to increase in construction costs to deploy all fiber underground in conduit rather than primarily aerial as initially proposed. | 0 | N/A | 0 | N/A: The County does not provide services on the network | 1 Gbps | No Variance | 0 | N/A: The County does not provide services on the network | 0 | N/A: The county is not providing services on the network and no private providers have begun offering services. Network testing confirms 1 Gbps capability. | 0 | N/A: The County does not provide services on the network | Currently Nelson County is providing 15 Mbps Internet service to their facilities across the middle mile network. Previously each of those county facilities was capable of receiving only 1.5 Mbps T1 service. The remaining community anchor institutions are to be served by private providers at speeds desired up to 1 Gbps. | No retail services are provided. | The County has contracted with Blue Ridge InterNetworks for third party network operation services. Rates for transport have been established by the County and agreements used to govern contractual relationships and network use policies. Bandwidth is limited only by the capability of the electronics (currently 1 Gbps). No private providers are serving customers from the middle mile network currently but last mile services planning by Blue Ridge InterNetworks is in progress. No limiting or blocking has occurred. | Not applicable. The County is not a service provider on this network. | 4464 | 0 | 0 | 0 | 4464 | 0 | 0 | No dark fiber has been leased although capacity is available if desired. | 392 | 84 | 36 | 272 | The County does provide collocation space for interconnection at the Lovingston network operating center. Additional interconnection points are at the Colleen, Afton, Avon, and Lovingston equipment shelters and network cabinets. Two providers are currently collocated in the Lovingston network operating center. | No subgrants or subcontracts have been made by the recipient to SDB concerns. | All aspects of implementing the broadband network were new for Nelson County personnel. The most important lesson learned is that it is crucial for elected officials to be engaged in the project early and to be aware of all aspects of ongoing implementation for effective communication with constituents and timely approval of any resolutions or decisions to keep the project on schedule. | Nelson, County of | 4 | 1 | 0 | 0 | 2 | 5 |  | 9 | 2 | 0 | 23 | At the end of the grant period, the County had completed interconnection with Blue Ridge InterNetworks. An initial agreement with provider Lumos had been negotiated and the connection completed, but the final agreement has not been executed. One additional interconnection agreement is currently being negotiated with Mid Atlantic Broadband. No requests for interconnection have been denied. | No peering or transit agreements were proposed or completed. Interconnection has been completed with Blue Ridge InterNetworks, and negotiations continue with Lumos. Lumos has completed interconnection of their facilities in the Lovingston network operating center and an initial 25 Mbps Internet circuit is available from Lumos for wholesale services to private providers who wish to use the middle mile network. | TRUE
NT10BIX5570050 | 2010 | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. No construction has occurred yet. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010.No construction has occurred yet. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. No construction has occurred yet. | 10Gbps | No variance from baseline. | 8Mbps | No variance from baseline. | 10Mbps | No variance from baseline. | 8Mbps | No variance from baseline. | A majority of the project area currently receives internet services with a maximum speed of .5-1Mbps. Zito's network will offer speeds from 6Mbps to 10,000Mbps depending on the service. The average increase based off a survey of service offerings in the project area would be 10Mbps to 1,000Mbps. | Zito's project is unique in that it offers both middle and last mile service offerings. Last mile service offerings include internet and voice services with internet speeds 6-8Mbps. Commercial service offerings include local point to point ethernet circuits with speeds between 1,000Mbps-10,000Mbps, internet service ad SIP trunks. The full list of services and pricing is attached to the report. | 7a) Zito will not apply restrictions to residential or commercial internet traffic. Zito will employ business practices or technical mechanisms for reasonable network management including application-neutral allocation of capacity, caching, differentiation among applications, providers and sources in order to limit usage and to manage illegal or harmful content and compliance with the needs of law enforcement. For residential and commercial traffic, at times, traffic will be restricted on certain ports to address issues with spam, worms, denial of service attacks and viruses to maintain reasonable customer service levels. Zito will offer managed services, such as telemedicine, public safety communications, and distance learning, which use private network connections for enhanced quality of service and adherence to HIPAA standards and other legal requirements. Reasonable congestion management tactics will be used based upon whether the traffic is time sensitive or non-time sensitive. Examples of time sensitive applications are voice (VoIP), Web Surfing, IM, tunneling & remote connectivity, streaming, and on-line games. Examples of non-time sensitive applications are file access, network storage, and software updates. Zito shall not use congestion management tactics to impair or degrade applications or services. 7b) Zito has not ever limited or blocked consumers from accessing any lawful content, service, service provider or application, or prevented any consumers from at | None. | 12300 | 0 | 0 | 0 | 0 | 0 | 0 | None. | 0 | 0 | 0 | 0 | Network construction has not started yet. Customers can interconnect to our network through fiber that will be built to their location. Network providers can interconnect with our network at the following hub sites: Denmark,OH; Rock Creek, OH; Thompson, OH; Roaming Shores, OH; West Farmington, OH; Warren, OH; Cortland, OH; Geneva, OH; Ashtabula, OH; Edgewood, OH; North Kingsville, OH; Conneaut, OH; Girard, PA; Fairview, PA; Erie, PA; Saegertown, PA; Meadville, PA. | Zito has hired one SDB to work on the project. Stell Environmental Enterprises, Inc. was chosen as our environmental engineering firm to aide us in drafting and submitting the environmental assessment. | Have scheduled meetings to discuss the grant project and its progression . In addition, be preemptive in any possible problems that could arise in the future by noting possible areas of concern. | Zito Media Communications II, LLC | 41 | 20 | 0 | 3 | 13 | 57 |  | 9 | 3 | 0 | 146 | N/A | N/A | TRUE
NT10BIX5570050 | 2011 | $9,268 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Construction started at the beginning of quarter 4 2011, but network is not currently active. | 0 | N/A | 0 | N/A | 1 Gbps | No variance from baseline. | 0 | No speeds are being advertised currently as construction has not commenced in last mile areas. | 0 | Average broadband speed is currently zero as network is not active. | 0 | Average broadband speed is currently zero as network is not active. | Broadband speeds have not increased as not CAIs are connected and the network is not currently lit for services. | Retail services are not currently be provided as network build during the reporting period is not lit for services. | 7a) Zito does not apply restrictions to residential or commercial internet traffic. Zito does employ business practices or technical mechanisms for reasonable network management including application-neutral allocation of capacity, caching, differentiation among applications, providers and sources in order to limit usage and to manage illegal or harmful content and compliance with the needs of law enforcement. For residential and commercial traffic, at times, traffic is restricted on certain ports to address issues with spam, worms, denial of service attacks and viruses to maintain reasonable customer service levels. Zito offers managed services, such as telemedicine, public safety communications, and distance learning, which use private network connections for enhanced quality of service and adherence to HIPAA standards and other legal requirements. Reasonable congestion management tactics is used based upon whether the traffic is time sensitive or non-time sensitive. Examples of time sensitive applications are voice (VoIP), Web Surfing, IM, tunneling & remote connectivity, streaming, and on-line games. Examples of non-time sensitive applications are file access, network storage, and software updates. Zito does not use congestion management tactics to impair or degrade applications or services. 7b) Zito has not ever limited or blocked consumers from accessing any lawful content, service, service provider or application, or prevented any consumers from attaching any le | None | 16066 | 0 | 160 | 2616 | 13290 | 0 | 0 | None | 0 | 0 | 0 | 0 | Customers can interconnect to our network through fiber that will be built to their location. Network providers can interconnect with our network at the following hub sites: Denmark,OH; Rock Creek, OH; Thompson, OH; Roaming Shores, OH; West Farmington, OH; Warren, OH; Cortland, OH; Geneva, OH; Ashtabula, OH; North Kingsville, OH; Conneaut, OH; Girard, PA; Fairview, PA; Erie, PA; Greenville, PA; Meadville, PA; Mercer, PA; Hermitage PA; Edinboro, PA. | Zito has hired one SDB to work on the project. Stell Environmental Enterprises, Inc. was chosen as our environmental engineering firm to aide us in drafting and submitting the environmental assessment. | Have scheduled meetings to discuss the grant project and its progression . In addition, be preemptive in any possible problems that could arise in the future by noting possible areas of concern. Weekly quality control checks by project manager ensure that project is progressing and work completed is accurate. Interface often with utilties to ensure make ready work progresses in a timely manner. We engaged with outside consultants to improve our accounting management and internal controls. | Zito Media Communications II, LLC | 41 | 20 | 0 | 3 | 13 | 57 |  | 9 | 3 | 0 | 146 | No agreements were entered into or denied in 2011. | No agreements were entered into or denied in 2011. | TRUE
NT10BIX5570050 | 2012 | $20,550 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Based off of miles constructed divided by amount of funds expended. | $17 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. Based off of the cost of overlashing fiber in the last mile areas divided by the number of households passed. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. The portion of the network in last mile areas is not yet active. For that reason there is no average cost per subscriber. | 1 Gbps | No variance from baseline. | 10 Mbps | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. 10 Mbps are currently being advertised in the Last Mile areas. | 10-100 Mbps | Average broadband speed in the areas that the network is active is 10-100 Mbps. The speed depends on the services used by the location. | 0 | Negative variance due to fact that we received the grant at the end of quarter one on March 26, 2010. No speeds are being advertised currently as construction and connectivity is not finished in last mile areas. | The average increase varies on the services provided to the anchor institutions. The average speed previous to our services varied from 1.5Mbps to 3Mbps with the Zito services these anchor institutions now receive at a minimum 10Mbps with a few receiving 100Mbps. The increase then is between 7Mbps to 97Mbps for the anchor institutions. | The retail services Zito Media Communications II, LLC offers are attached as an attachment. The majority of Zito's network is not currently active as construction and splicing are still being completed. The general services Zito offers include the following: local point to point ethernet circuits, internet service, SIP trunks (inbound/outbound), voice services, and dark fiber leases. | 7a) Zito does not apply restrictions to residential or commercial internet traffic. Zito does employ business practices or technical mechanisms for reasonable network management including application-neutral allocation of capacity, caching, differentiation among applications, providers and sources in order to limit usage and to manage illegal or harmful content and compliance with the needs of law enforcement. For residential and commercial traffic, at times, traffic is restricted on certain ports to address issues with spam, worms, denial of service attacks and viruses to maintain reasonable customer service levels. Zito offers managed services, such as telemedicine, public safety communications, and distance learning, which use private network connections for enhanced quality of service and adherence to HIPAA standards and other legal requirements. Reasonable congestion management tactics is used based upon whether the traffic is time sensitive or non-time sensitive. Examples of time sensitive applications are voice (VoIP), Web Surfing, IM, tunneling & remote connectivity, streaming, and on-line games. Examples of non-time sensitive applications are file access, network storage, and software updates. Zito does not use congestion management tactics to impair or degrade applications or services. 7b) Zito has not ever limited or blocked consumers from accessing any lawful content, service, service provider or application, or prevented any consumers from attaching any le | None | 16066 | 7850 | 168 | 7668 | 380 | 0 | 0 | None | 1080 | 36 | 36 | 1008 | Customers can interconnect to our network through fiber that will be built to their location. Network providers can interconnect with our network at the following hub sites: Denmark,OH; Rock Creek, OH; Thompson, OH; Roaming Shores, OH; West Farmington, OH; Warren, OH; Cortland, OH; Geneva, OH; Ashtabula, OH; North Kingsville, OH; Conneaut, OH; Girard, PA; Fairview, PA; Erie, PA; Greenville, PA; Meadville, PA; Mercer, PA; Hermitage PA; Edinboro, PA. Under the lease agreements with facilities other network providers and/or customers interconnect with our network at these locations not owned by us. | Zito has hired one SDB to work on the project. Stell Environmental Enterprises, Inc. was chosen as our environmental engineering firm to aide us in drafting and submitting the environmental assessment. | Have scheduled meetings to discuss the grant project and its progression . In addition, be preemptive in any possible problems that could arise in the future by noting possible areas of concern. Weekly quality control checks by project manager ensure that project is progressing and work completed is accurate. Interface often with utility companies to ensure make ready work progresses in a timely manner. We engaged with outside consultants to improve our accounting management and internal controls. | Zito Media Communications II, LLC | 41 | 20 | 0 | 3 | 13 | 57 |  | 9 | 3 | 0 | 146 | No agreements were entered into or denied in 2012. | No agreements were entered into or denied in 2012. | TRUE
NT10BIX5570051 | 2010 | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | n/a | 0 | Keep good notes and document. It is very important to read the CFR's and ask questions in advance. Get written clarification on all aspects of projects before moving forward. | First Step Internet, L.L.C. | 19 | 15 | 1 | 1 | 11 | 42 |  | 36 | 10 | 500 | 635 | n/a | n/a | TRUE
NT10BIX5570051 | 2011 | $3,748 | actual cost/mile is up $391/mile. cost/mile will fluctuate with the distances covered. We anticipate additional longer shots coming up which will lower the overall cost/mile. | $0 | n/a | $0 | n/a | 45megs | 45megs will be advertised, however actual available could be as high as 200megs depending on location and distance. | 0 | n/a | 150 | all paths are currently licensed between 100/megs and 400megs | 0 | n/a | 100 megs All Community Anchor Institutions are built with 100meg licensed capable radios. Each CAI will select their appropriate broadband speed based on their own needs and indicators. Speeds are available in 1meg increments. | First Step is providing direct Internet connections as well as L2VPN (Layer 2 Virtual Private Network) services across the network. Pricing is based on $100/meg/month. Discounts can be negotiated for larger purchases or for transit only service. | First Step does not currently block or restrict access to any lawful content. Bandwidth is controlled by PPPoE (Point to Point Protocol over Ethernet) and is set based on the service level purchased by the end user. Policies can be found at http://www.fsr.com/documents/policies/FSI_Network_Neutrality_Policy and http://www.fsr.com/first-step-internet-policies/ | No subscribers have dropped the service provided by the BTOP award. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 1600 | 100 | 0 | 1500 | 1,500 sq.ft is what is available in building space. The towers are also available for collocation of equipment. The amount available space would be dependent upon the requested usage, antenna size, weight, frequency, mounting height, etc. There is no method for determining the available space without knowing the exact specifications of each requested use. | no subcontracts or or sub grants. | First Step believes that you must work closely with all participants and engaged parties in the project. There must be an open communication standard so the progress of the project is as transparent as possible. | First Step Internet, L.L.C. | 19 | 15 | 1 | 1 | 11 | 42 |  | 36 | 10 | 500 | 635 | 1. n/a 2. 3 3. none denied | n/a - not defined in application | TRUE
NT10BIX5570051 | 2012 | $2,978.49 | cost/mile is down ~$378/mile. This is most due to cost savings in the construction of the network. First Step was able to build the network with fewer man hours than originally estimated. | 0 | n/a | 0 | n/a | 100megs | All CAI connections are built with 100meg minimum capacity. All middle mile paths are constructed with a minimum 200megs capacity and are software upgradable as necessary | 0 | n/a | 150 | all paths are currently licensed between 100/megs and 400 megs | 0 | n/a | 100 megs All Community Anchor Institutions are built with 100meg licensed capable radios. Each CAI will select their appropriate broadband speed based on their own needs and indicators. Speeds are available in 1meg increments. | First Step is providing direct Internet connections as well as L2VPN (Layer 2 Virtual Private Network) services across the network. Pricing is based on $100/meg/month. Discounts can be negotiated for larger purchases or for transit only service. | First Step does not currently block or restrict access to any lawful content. Bandwidth is controlled by PPPoE (Point to Point Protocol over Ethernet) and is set based on the service level purchased by the end user. Policies can be found at http://www.fsr.com/documents/policies/FSI_Network_Neutrality_Policy and http://www.fsr.com/first-step-internet-policies/ | No subscribers have dropped the service provided by the BTOP award. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 1600 | 100 | 0 | 1500 | 1,500 sq.ft is what is available in building space. The towers are also available for collocation of equipment. The amount available space would be dependent upon the requested usage, antenna size, weight, frequency, mounting height, etc. There is no method for determining the available space without knowing the exact specifications of each requested use. | no subcontracts or or sub grants. | First Step believes that you must work closely with all participants and engaged parties in the project. There must be an open communication standard so the progress of the project is as transparent as possible. As the project has continued and progressed it has become increasingly apparent and important to communicate directly and clearly with any other potential entities or project partners. This is especially true when dealing with other Federal agencies. The timelines for decisions are often very long and much different than one would expect when dealing with private enterprise. | First Step Internet, L.L.C. | 19 | 15 | 1 | 1 | 11 | 42 |  | 36 | 10 | 500 | 635 | 1. 0 2. 3 3. no requests have been denied. | n/a - not defined in application | TRUE
NT10BIX5570051 | 2013 | $3,596.79 | Cost/mile is up $618/mile from last year. This is due to the increased administrative costs associated with this years work being completed with few miles being constructed this season. | 0 | n/a | 0 | n/a | 100 | All CAI connections are built with 100meg minimum capacity. All middle mile paths are constructed with a minimum 200megs capacity and are software upgradable as necessary | 0 | n/a | 150 | All middle mile paths are currently licensed between 100 megs and 400 megs. | 0 | n/a | 100 megs All Community Anchor Institutions are built with 100meg licensed capable radios. Each CAI will select their appropriate broadband speed based on their own needs and indicators. Speeds are available in 1meg increments. The current average speed increase for the CAI clients is 4.75 megs. This represents the average increase in the amount of purchased bandwidth. Each CAI has a 100meg connection to the Internet. This number represents a ~98meg average increase in possible connection speeds. Please see the attachment (CAI Speed Comparison V2) for details. | First Step is providing direct Internet connections as well as L2VPN (Layer 2 Virtual Private Network) services across the network. Pricing is based on $100/meg/month. Discounts can be negotiated for larger purchases or for transit only service. First Step does not offer pre-defined â€œspeed tiersâ€. CAIâ€™s are able to order the exact bandwidth they believe they need for their individual usage and project. Speed packages currently provisioned are as follows: Current Speed Tier Matrix Speed Provisioned # of CAI's 800k/128k: 1 1.5/256: 1 2.0/500: 6 2/2: 1 3/3: 5 4/2: 1 5/5: 4 6/6: 7 7/7: 1 9/3: 1 10/10: 6 12/12: 2 20/20: 1 30/30: 6 Total 43 | First Step does not currently block or restrict access to any lawful content. Bandwidth is controlled by PPPoE (Point to Point Protocol over Ethernet) and is set based on the service level purchased by the end user. Policies can be found at http://www.fsr.com/documents/policies/FSI_Network_Neutrality_Policy and http://www.fsr.com/first-step-internet-policies/ | No subscribers have dropped the service provided by the BTOP award. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 1600 | 100 | 0 | 1500 | 1,500 sq.ft is what is available in building space. The towers are also available for collocation of equipment. The amount available space would be dependent upon the requested usage, antenna size, weight, frequency, mounting height, etc. There is no method for determining the available space without knowing the exact specifications of each requested use. | no subcontracts and/or sub grants | First Step believes that you must work closely with all participants and engaged parties in the project. There must be an open communication standard so the progress of the project is as transparent as possible. As the project has continued and progressed it has become increasingly apparent and important to communicate directly and clearly with any other potential entities or project partners. This is especially true when dealing with other Federal agencies. The timelines for decisions are often very long and much different than one would expect when dealing with private enterprise. | First Step Internet, L.L.C. | 19 | 15 | 1 | 1 | 11 | 42 |  | 36 | 10 | 500 | 635 | 1. 0 2. 3 3. no requests have been denied. | n/a - not defined in application | TRUE
NT10BIX5570053 | 2010 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 7a. IT&E utilizes various tools and techniques to manage its network. Such products include identifying spam and preventing its delivery to customer e-mail accounts, detecting malicious Internet traffic and preventing the distribution of viruses or other harmful code or content. IT&E employs no traffic shaping and implements no bandwidth limitations. 7b. No. IT&E provides its customers with full access to all the content, services, and applications that the Internet has to offer. In addition, IT&E does not block P2P traffic or applications like BitTorrent, Gnutella, or others as part of its current network congestion management technique. Furthermore, IT&E protects its customers from spam, phishing, and other unwanted or harmful online content and activities. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. | 448 | 200 | 4 | 244 | Please see answer to 11. | N/A | A. Management Practices 1. Modification of normal procurement practices to match Federal Regulations (FAR) for all ARRA-related procurements. 2. Strict accounting of time by cost centers using bi-weekly time sheets. 3. All documentation relating to grant activities stored in soft copy on server to insure audit trails are completely visible. 4. Competitive procurement vehicles (IFB, RFP) contain explicit statements of work, contract deliverable requirements lists (CDRLs), explicit statements of conditions under which procurement actions can be cancelled in best interest of IT&E and U.S. Government, and clear, understandable evaluation criteria to guide vendors in developing proposals. 5. Oversight of individual projects and project managers by management team experienced in Federal procurement practices and Federal grants management. 6. Separate accounting for ARRA funds; no mixing of ARRA funds with other company accounts to insure clear audit trails. 7. RFPs evaluated separately on technical and cost factors by teams; evaluators assign raw scores without knowledge of weighting factors; weighted scores computed by procurements administrator and grants management team to select short list of vendors in each step; selection of final contract awardees based on best value to IT&E and U.S. Government in accordance with FAR. 8. Procurement actions reviewed by in house General Counsel experienced in Federal Acquisition Regulations and Federal procurement practices. B. Adherence to Federal Rules and Regulations 1. Strict Adherence to Special Award Conditions and FAR. 2. Inclusion of appropriate FAR Clauses in all ARRA-funded procurements 3. All sole-source procurements backed by NTIA/DOC approved J&A (Justification and Authorization) per FAR 6.302.1 4. Level Playing Field for all vendors according to intent of Congress as directed in ARRA and implemented in FAR. 5. Pre-evaluation/pre-award vetting of all vendors per Federal suspension and debarment lookup on www.epls.gov. C. Community Outreach 1. Large signs following criteria spelled out in Special Award Conditions posted at major company locations. 2. Periodic press releases issued at major milestones in project completion. 3. Meetings with Government officials and community organizations with direct interest in the various projects. 4. Pictures of project-related activities collected and saved on server for use in community outreach activities. 5. Establishment of public web site to publicize ARRA-related activities and to advertise ARRA-related procurements. Established links to and from local Government ARRA web sites to insure wider public awareness. D. Examples 1. On our NOC project, we received a only single quote to a widely advertised and subscribed IFB that was three times the engineerâ€™s estimate. It was obvious from the prices listed that the quote was heavily padded with unjustifiable costs. We cancelled the procurement using â€œoutside the competitive rangeâ€ as the reason. We then devised a different, far more cost-effective strategy to complete the procurement action by breaking the activity into smaller, separately advertised procurements and substituting our own in-house labor force for some of the labor originally intended to be contracted out. 2. On our Prepaid Charging Platform Billing System project, our original RFP produced responses that were all above the engineerâ€™s estimate and the available budget by factors ranging from 3 to 10. Again we cancelled the procurement as being outside the competitive range, revised the RFP to make many of the original fixed requirements separately priced options, and re-advertised. Mostly the same vendors responded and even with the options included, all of the proposals were significantly lower in total cost, proving our suspicions that the original cost proposals were heavily padded with unjustifiable costs. We are in the final process of selecting the winning vendor and hope to make an award early in January after we visit existing customers of the short-listed vendors to gain insight on their experience. The purpose of these visits is to insure we select the vendor who will deliver the best total value to IT&E and the Government even if it is not the vendor with the lowest cost. | PTI Pacifica, Inc., dba: IT&E | 90 | 10 | 13 | 15 | 45 | 19 |  | 153 | 71 | 4 | 420 | N/A. | N/A. | TRUE
NT10BIX5570053 | 2011 | 16500.72 | Total project cost to date divided by the completed miles = $7,664,252/464.48=$16,500.72. | n/a | n/a | n/a | n/a | 10.0 Mbps | This is for Middle Mile. | n/a | n/a | 3.0 Mbps | This is for Middle Mile. | n/a | n/a | None. We are delivering average speeds between 1.43 Mbps to 3.035 Mbps. | None. | 7a. IT&E utilizes various tools and techniques to manage its network. Such products include identifying spam and preventing its delivery to customer e-mail accounts, detecting malicious Internet traffic and preventing the distribution of viruses or other harmful code or content. IT&E employs no traffic shaping and implements no bandwidth limitations. 7b. No. IT&E provides its customers with full access to all the content, services, and applications that the Internet has to offer. In addition, IT&E does not block P2P traffic or applications like BitTorrent, Gnutella, or others as part of its current network congestion management technique. Furthermore, IT&E protects its customers from spam, phishing, and other unwanted or harmful online content and activities. | None. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 448 | 200 | 4 | 244 | Other network providers and customers connect in our facilities; we do not connect in their facilities so we own no collocation space. We do make collocation space in our facilities available to other network providers. | n/a | Community Outreach: 1. Invite all Community Anchor Institutions to an initial (introductory) meeting to provide information on the Grant Award. Discuss how it would benefit the Community Anchor Institutions. IT&E did this on Guam in October 2011 and had 14 CAIs (IT Managers) that attended the meeting. After that initial meeting, a relationship had been established and IT&E continues to work with these anchors to see how we can support their broadband requirements. | PTI Pacifica, Inc., dba: IT&E | 90 | 10 | 13 | 15 | 45 | 19 |  | 153 | 71 | 4 | 420 | none | none | TRUE
NT10BIX5570053 | 2012 | 20149.75 | Total project cost to date divided by the completed miles = $10,165,145/504.48=$20,149.75. In 2011, Total project cost to date divided by the completed miles = $7,664,252/464.48=$16,500.72. | n/a | n/a | n/a | n/a | 10.0 Mbps | This is for middle mile. | n/a | n/a | 3.0 Mbps | This is for middle mile. | n/a | n/a | None. We are delivering average speeds between 1.43 Mbps to 3.035 Mbps. | none | 7a. IT&E utilizes various tools and techniques to manage its network. Such products include identifying spam and preventing its delivery to customer e-mail accounts, detecting malicious Internet traffic and preventing the distribution of viruses or other harmful code or content. IT&E employs no traffic shaping and implements no bandwidth limitations. 7b. No. IT&E provides its customers with full access to all the content, services, and applications that the Internet has to offer. In addition, IT&E does not block P2P traffic or applications like BitTorrent, Gnutella, or others as part of its current network congestion management technique. Furthermore, IT&E protects its customers from spam, phishing, and other unwanted or harmful online content and activities. | none | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 448 | 200 | 4 | 244 | Other network providers and customers connect in our facilities; we do not connect in their facilities so we own no collocation space. We do make collocation space in our facilities available to other network providers. | n/a | NONE. | PTI Pacifica, Inc., dba: IT&E | 90 | 10 | 13 | 15 | 45 | 19 |  | 153 | 71 | 4 | 420 | none | none | TRUE
NT10BIX5570053 | 2013 | $9,588.79 | $4,837,351/504.48=$9,588.79. | n/a | n/a | n/a | n/a | 10.0 Mbps | This is for Middle Mile | n/a | n/a | 3.0 Mbps | This is for middle mile. | n/a | n/a | None. We are delivering average speeds between 1.43 Mbps to 3.619 Mbps. | none. | 7a. IT&E utilizes various tools and techniques to manage its network. Such products include identifying spam and preventing its delivery to customer e-mail accounts, detecting malicious Internet traffic and preventing the distribution of viruses or other harmful code or content. IT&E employs no traffic shaping and implements no bandwidth limitations. 7b. No. IT&E provides its customers with full access to all the content, services, and applications that the Internet has to offer. In addition, IT&E does not block P2P traffic or applications like BitTorrent, Gnutella, or others as part of its current network congestion management technique. Furthermore, IT&E protects its customers from spam, phishing, and other unwanted or harmful online content and activities. | none. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a. | 448 | 200 | 4 | 244 | Other network providers and customers connect in our facilities; we do not connect in their facilities so we own no collocation space. We do make collocation space in our facilities available to other network providers. | n/a. | none. | PTI Pacifica, Inc., dba: IT&E | 90 | 10 | 13 | 15 | 45 | 19 |  | 153 | 71 | 4 | 420 | None. | none. | TRUE
NT10BIX5570054 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Page County Broadband Authority | 11 | 3 | 1 | 0 | 6 | 7 |  | 20 | 5 | 0 | 53 | N/A | N/A | TRUE
NT10BIX5570054 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A, network not yet constructed | N/A, network not yet constructed | N/A, network not yet constructed | N/A, network not yet constructed | 4464 | 0 | 0 | 0 | 3168 | 1296 | 0 | N/A, network not yet constructed | 0 | 0 | 0 | 0 | N/A, network not yet constructed | N/A, no sub grants provided in this project | It is important for BTOP recipients to begin work on the make-ready connections early in the design profits. In many cases, other utility providers may be unaware of their existing infrastructure (including utility poles) and this will cause delays in the project when negotiations and design work for make-ready and pole attachments must be complete. It is also important to have a strong and active management team that can quickly address problems/delays that may arise in a concise and timely manner. | Page County Broadband Authority | 11 | 3 | 1 | 0 | 6 | 7 |  | 20 | 5 | 0 | 53 | N/A, no agreements at this time | N/A | TRUE
NT10BIX5570054 | 2012 | 36035 | Variance due to change in costs as a result of a project modification in early 2012. The inter-community fiber was replaced with microwave transport between towers in each of the proposed funded service areas. | 0 | N/A | 0 | N/A | 1Gbps | At completion, the fiber middle mile network will provide 1 Gbps transport services to private providers. At completion, the microwave network will provide 1 Gbps transport between towers for interconnection to the fiber. | 0 | N/A | 0 | N/A: The PCBA will not provide retail services on the network. The network is nearing completion but no private providers are offering services at this time. | 0 | N/A | The network is currently under construction and no community anchor institutions are being served at this time. | No retail services will be provided by the PCBA. | The PCBA has contracted with Shentel for third party network operation services. Rates for transport have been established by the PCBA and agreements are currently under development to govern contractual relationships for network transport and network use policies. The network is still under construction at this time, and no private providers are serving customers from the middle mile network currently. | N/A | 972 | 486 | 486 | 0 | 0 | 0 | 0 | One (1) lease agreement has been signed with the Shenandoah Long Distance Telephone Company (Shentel) for dark fiber. No additional agreements for dark fiber will be signed. | 1494 | 747 | 0 | 747 | The PCBA does provide collocation space for interconnection at the Luray POP. Additional interconnection points are at the Rileyville Tower, Stanley Water Tank, Cub Run Tower, and Shenandoah Water Tank network cabinets. | No sub grants or subcontracts have been made by the recipient to SDB concerns. | It is important for BTOP recipients to begin work on the make-ready connections early in the design process. In many cases, other utility providers may be unaware of their existing infrastructure (including utility poles) and this will cause delays in the project when negotiations and design work for make-ready and pole attachments must be complete. It is also important to have a strong and active management team that can quickly address problems/delays that may arise in a concise and timely manner. | Page County Broadband Authority | 11 | 3 | 1 | 0 | 6 | 7 |  | 20 | 5 | 0 | 53 | One (1) lease agreement has been signed with the Shenandoah Long Distance Telephone Company (Shentel). The PCBA is not negotiating any interconnection, peering or transit agreements at this time. Now that construction is complete, efforts are underway to reach out to providers that have expressed interest and initiate contract proceedings. No requests for interconnection have been denied by the PCBA at this time. | N/A | TRUE
NT10BIX5570054 | 2013 | 36035 | No Variance. Project is complete. | 0 | N/A | 0 | N/A | 500mbs | No Variance. Project is complete. | 0 | N/A | 0 | N/A: The PCBA will not provide retail services on the network. The project is complete. | 0 | N/A | Improved broadband access for all community anchor institutions connected. Not customers have signed on to the network as of grant end date, February 28, 2013. | No retail services will be provided by the PCBA. | The PCBA has contracted with Shentel for third party network operation services. Rates for transport have been established by the PCBA and agreements are currently developed to govern contractual relationships for network transport and network use policies. | N/A | 972 | 486 | 486 | 0 | 0 | 0 | 0 | One (1) lease agreement has been signed with the Shenandoah Long Distance Telephone Company (Shentel) for dark fiber. No additional agreements for dark fiber will be signed. | 1494 | 747 | 0 | 747 | The PCBA does provide collocation space for interconnection at the Luray POP. Additional interconnection points are at the Rileyville Tower, Stanley Water Tank, Cub Run Tower, and Shenandoah Water Tank network cabinets. | No sub grants or subcontracts have been made by the recipient to SDB concerns. | It is important for BTOP recipients to begin work on the make-ready connections early in the design process. In many cases, other utility providers may be unaware of their existing infrastructure (including utility poles) and this will cause delays in the project when negotiations and design work for make-ready and pole attachments must be complete. It is also important to have a strong and active management team that can quickly address problems/delays that may arise in a concise and timely manner. | Page County Broadband Authority | 11 | 3 | 1 | 0 | 6 | 7 |  | 20 | 5 | 0 | 53 | One (1) lease agreement has been signed with the Shenandoah Long Distance Telephone Company (Shentel). The PCBA is not negotiating any interconnection, peering or transit agreements at this time. Now that construction is complete, efforts are underway to reach out to providers that have expressed interest and initiate contract proceedings. No requests for interconnection have been denied by the PCBA at this time. | N/A | TRUE
NT10BIX5570055 | 2010 | $25,963.00 | No Variance | $1,053.62 | No Variance | $327.39 | No Variance | 100 Mbps | NTUA can provide tiered service. Please refer to attachment A for details | 1.0 Mbps up to 3.0 Mpbs | NTUA can provide tiered service. Please refer to attachment A for details | N/A | NTUA can provide tiered service. Please refer to attachment A for details | .512 to 1.128 Mpbs | NTUA can provide tiered service. Please refer to attachment A for details | Given the absence of broadband capacity in and around the Navajo Nation, the average increase in broadband speed will be enormous. Most community anchor institutions only have access to T-1 lines which equates to 1.5 Mbps. The NTUA can offer up to 100Mbps or dark fibers capable of up to 10 Gbps. | Retail Services shall be provided by NTUA's sub-recipient Commnet Wireless LLC. For pricing plans, please refer to Attachment A. | Not Applicable | Not Applicable | 550 | 0 | 0 | 0 | 0 | 0 | 550 | N/A | 0 | 0 | 0 | 0 | The NTUA will provide collocation space at their proposed Data Center as well as collocation space at their telecommunications shelters throughout the Navajo Navajo. | Not Applicable | The most important practices/lessons learned are to adhere to the rules and procedures stipulated in the Grant. Following the rules and training our staff on grant procedures helped immensely in eliminating problems that might arise in the reporting process. Equally important is developing clear lines of communications between various departments. For example, the ROW department needs to communicate with the Engineering department, which needs to communicate with the IT department to obtain the information they require. Another lesson to keep in mind is to develop contingencies for all aspects of the job; always have a backup plan and plan everything ahead of time. In particular, allowing enough time for ordering equipment is imperative. Also, creating a detailed project plan is crucial to a successful project. | Navajo Tribal Utility Authority Company | 112 | 10 | 9 | 7 | 63 | 27 |  | 274 | 307 | 19 | 828 | The NTUA is currently in negotiations for interconnection agreements. | The NTUA is currently in negotiations for Peering and Transit Agreements. | TRUE
NT10BIX5570055 | 2011 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Current broadband speeds available on the Navajo Nation are limited to T-1 (1.5 Mb/s) lines provided by the incumbent telephone provider. Although NTUA is not providing any broadband services at this time, NTUA's system as a result of the BTOP grant will allow for up to 10 Gb/s of data transfer speeds. This is a tenfold increase of capacity available. | NTUA and sub-recipient partner, NTUA Wireless will provide a host of wholesale and retail services to various entities on the Navajo Nation. Services include dedicated fiber optic solutions, point to point connections for community anchor institutions, private network connections to enable virtual private networks (VPNs) for hospitals, public safety, transport services to a point of presence, and wireless services for small business and residences. NTUA anticipates completion of the Broadband Rate study by the first month of the following quarter at which time NTUA will provide pricing plans for all services provided. | In regards to network management policies, NTUA has committed to nondiscrimination, interconnection with other providers, and network openness, with respect to both the middle-mile and last-mile portions of this proposal. NTUA and NTUA Wireless will display any network management policies in a prominent location on the service providerâ€™s web page and provide notice to customers of changes in these policies as soon as the policies are developed. NTUA anticipates completion of network management policies and procedures during the following quarter. | N/A | 55372 | 0 | 652 | 17568 | 0 | 0 | 37152 | Although NTUA is currently not leasing any dark fibers, NTUA has agreements in place to provide dark fibers to the following entities: 1. Navajo Nation - NTUA has committed to offer up to 12 dark fibers to the Navajo Nation for a total of 6840 fiber strand miles. 2. Bureau of Reclamations (BoR) - NTUA has committed to provide 4 dark fibers to the BoR for a total of 2280 fiber strand miles. | 15000 | 0 | 0 | 15000 | N/A | N/A | Listed below are the best practices/lessons learned: 1. Order all materials early! Waiting to order materials such as fiber optic cable and hardware can be detrimental to construction progress in the later stages of the grants. 2. Anticipate any potential changes in the build-out that may require additional environmental assessment. 3. Have adequate processes in place with respect to accounting practices to allow for maximum transparencies. 4. Submit any applications for rights of way or permitting as soon as possible. 5. Follow the rules and guidelines as stated in the NOFA. 6. Utilize the staff at the NTIA to assist with any questions, issues or concerns that may arise. | Navajo Tribal Utility Authority Company | 112 | 10 | 9 | 7 | 63 | 27 |  | 274 | 307 | 19 | 828 | 1. NTUA has finalized the Tri-State indefeasible right of use (IRU) agreement to obtain dark fibers to a point of presence (POP) in Albuquerque, NM. 2. The total number of agreements NTUA is currently negotiating is one. NTUA is currently negotiating an interconnection agreement with CenturyLink to provide a back up route to Albuquerque, NM via Gallup, NM. 3. NTUA has not denied any request for interconnection. | N/A | TRUE
NT10BIX5570055 | 2012 | N/A | Average cost/speed per mile will be determined once construction is complete and the system is in service at which point any variance will be addressed. | N/A | Average cost/speed per mile will be determined once construction is complete and the system is in service at which point any variance will be addressed. | N/A | Average cost/speed per mile will be determined once construction is complete and the system is in service at which point any variance will be addressed. | N/A | The maximum broadband speed will be determined once construction is complete and the system is in service at which point any variance will be addressed. | N/A | The maximum broadband speed advertised will be determined once the Last Mile infrastructure has undergone the acceptance test procedures (ATP). | N/A | The average broadband speed will be determined once construction is complete and the system is in service at which point any variance will be addressed. | N/A | The average broadband speed advertised will be determined once the Last Mile infrastructure has undergone the acceptance test procedures (ATP). | Current broadband speeds available on the Navajo Nation are limited to T-1 (1.5 Mb/s) lines provided by the incumbent telephone provider. Although NTUA is not providing any broadband services at this time, NTUA's system as a result of the BTOP grant will allow for up to 10 Gb/s of data transfer speeds. This is a tenfold increase of capacity available. | NTUA and sub-recipient partner, NTUA Wireless will provide a host of wholesale and retail services to various entities on the Navajo Nation. Services include dedicated fiber optic solutions, point to point connections for community anchor institutions, private network connections to enable virtual private networks (VPNs) for hospitals, public safety, transport services to a point of presence, and wireless services for small business and residences. NTUA Wireless is in the process of completing their retail plan and shall publish the various pricing plans prior to the retail launch. | In regards to network management policies, NTUA has committed to nondiscrimination, interconnection with other providers, and network openness, with respect to both the middle-mile and last-mile portions of this proposal. NTUA and NTUA Wireless will display any network management policies in a prominent location on the service providerâ€™s web page and provide notice to customers of changes in these policies as soon as the policies are developed. NTUA has not prevented any consumers from attaching any legal device to the network. | N/A | 54220 | 0 | 652 | 50844 | 0 | 0 | 2724 | Although NTUA is currently not leasing any dark fibers, NTUA has agreements in place to provide dark fibers to the following entities: 1. Navajo Nation - NTUA has committed to offer up to 12 dark fibers to the Navajo Nation for a total of 6840 fiber strand miles. 2. Bureau of Reclamations (BoR) - NTUA has committed to provide 4 dark fibers to the BoR for a total of 2280 fiber strand miles. | 15000 | 3750 | 0 | 11250 | N/A | N/A | 1. Order all materials early! Waiting to order materials such as fiber optic cable and hardware can be detrimental to construction progress in the later stages of the grants. 2. Anticipate any potential changes in the build-out that may require additional environmental assessment. 3. Have adequate processes in place with respect to accounting practices to allow for maximum transparencies. 4. Submit any applications for rights of way or permitting as soon as possible. 5. Follow the rules and guidelines as stated in the NOFA. 6. Utilize the staff at the NTIA to assist with any questions, issues or concerns that may arise. | Navajo Tribal Utility Authority Company | 112 | 10 | 9 | 7 | 63 | 27 |  | 274 | 307 | 19 | 828 | 1. NTUA has finalized the Tri-State indefeasible right of use (IRU) agreement to obtain dark fibers to a point of presence (POP) in Albuquerque, NM. 2. The total number of agreements NTUA is currently negotiating is one. NTUA is currently negotiating an interconnection agreement with CenturyLink to provide a back up route to Albuquerque, NM via Gallup, NM. 3. NTUA has not denied any request for interconnection. | N/A | TRUE
NT10BIX5570055 | 2013 | $19,226 | There is a variance from the baseline plan. In the baseline, NTUA anticipated the average cost per new mile to be $25,963. The methodology to calculate the average cost per new mile is as follows: Average Cost per new mile = (total costs for (conduit, cables, towers, antennas/wireless transceivers, and the labor used to install this transmission infrastructure)) / (number of fiber miles + number of microwave miles) The calculation includes the original budget and overages. The calculation does not include the following: network access (e.g., core network routers), customer premise equipment (CPE), building/facility construction, make ready, test equipment, billing and operational support systems, and/or any additional professional services. | $494.69 | Variance is due to the methodology utilized to calculate costs. The current formula used includes costs for the following: distribution and remote terminals (e.g., DSLAM, B/GPON), conduit, cables, wireless transceivers, antennas and the labor used to install the transmission infrastructure. The formula excludes the following: any costs associated with CPE, CPE installation services, building/facility/tower construction, test equipment, billing and operational support systems and/or any additional professional services. Average cost per household = cumulative direct last mile capital costs / total entities passed. | $162.39 | Variance is due to the methodology utilized to calculate costs. The current formula used includes costs for the following: distribution and remote terminals (e.g., DSLAM, B/GPON), conduit, cables, wireless transceivers, antennas and the labor used to install the transmission infrastructure. The formula excludes the following: any costs associated with CPE, CPE installation services, building/facility/tower construction, test equipment, billing and operational support systems and/or any additional professional services. Average cost per household = cumulative direct last mile capital costs / total households available for subscription. | 10 Gb | No Variance | 3 Mb | Variance is due to NTUA Wireless (NTUAW) adding two additional pricing tiers. In the baseline, NTUAW offered two options: â€¢ $27.95: 765 Kb Download / 200 Kb Upload â€¢ $49.95: 2 Mb Download / 2 Mb Upload In addition to the plans offered above, NTUAW offers two additional plans: â€¢ $39.95: 1.5Mb Download / 765Kb Upload â€¢ $79.95: 3 Mb Download / 2 Mb Upload | 50 Mb | The average speed or rather average capacity provided by this network is in 50 Mbps Circuits. Wireless carriers, among others, have requested 50 Mb circuits for wireless and LTE backhaul. NTUA has the ability to offer circuits up to 10 Gbps in size. | 1.8 Mb | Variance is due to the additional plans offered. As of December 31, 2013, NTUAW has the following subscribers: Rate Plan $27.95 - (765 Kbps) 81 Subscribers $39.95 - (1.5 Mbps)140 Subscribers $49.95 - (2.0 Mbps)184 Subscribers $79.95 - (3.0 Mbps) 74 Subscribers Formula: The sum of the total number of subscribers multiplied by their respective speed divided by the total number of subscribers. | Current broadband speeds available on the Navajo Nation are limited to T-1 (1.5 Mb/s) lines provided by the incumbent telephone provider. Although NTUA is not providing any broadband services at this time, NTUA's system as a result of the BTOP grant will allow for up to 10 Gb/s of data transfer speeds. This is a tenfold increase of capacity available. | NTUA and sub-recipient partner, NTUA Wireless will provide a host of wholesale and retail services to various entities on the Navajo Nation. Services include dedicated fiber optic solutions, point to point connections for community anchor institutions, private network connections to enable virtual private networks (VPNs) for hospitals, public safety, transport services to a point of presence, and wireless services for small business and residences. NTUA Wireless has completed their retail plan and shall publish the various pricing plans prior to the retail launch. Refer to Attachment A & B for details | In regards to network management policies, NTUA and NTUA Wireless have committed to nondiscrimination, interconnection with other providers, and network openness, with respect to both the middle-mile and last-mile portions of the project. NTUA and NTUA Wireless will display any network management policies in a prominent location on the service providerâ€™s web page and provide notice to customers of changes in these policies as soon as the policies are updated and/or developed. Neither NTUA nor NTUA Wireless have prevented any consumers from attaching any legal device to the network. | N/A | 55372 | 2280 | 652 | 52440 | 0 | 0 | 0 | NTUA is a wholesale dark fiber provider and is currently in negotiations with the following entities to provide them dark fiber or Lambdas: 1. Tri-State Generation & Transmission 2. CenturyLink 3. Navajo Nation 4. Tuba City Hospital, Tuba City, AZ 5. Western Area Power Administration (WAPA) | 15000 | 3750 | 0 | 11250 | N/A | N/A | 1. Order all materials early! Waiting to order materials such as fiber optic cable and hardware can be detrimental to construction progress in the later stages of the grants. 2. Anticipate any potential changes in the build-out that may require additional environmental assessment. 3. Have adequate processes in place with respect to accounting practices to allow for maximum transparencies. 4. Submit any applications for rights of way or permitting as soon as possible. 5. Follow the rules and guidelines as stated in the NOFA. 6. Utilize the staff at the NTIA to assist with any questions, issues or concerns that may arise. | Navajo Tribal Utility Authority Company | 112 | 10 | 9 | 7 | 63 | 27 |  | 274 | 307 | 19 | 828 | N/A | N/A | TRUE
NT10BIX5570056 | 2010 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A. When constructed DBC's network will offer wholesale option to any provider. | 0 | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | N/A | N/A | TRUE
NT10BIX5570056 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. When constructed, DBC's network will offer wholesale options for any provider. | 0 | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | N/A | N/A | TRUE
NT10BIX5570056 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | N/A | N/A | TRUE
NT10BIX5570057 | 2010 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A. When constructed, DBC's network will offer wholesale option to any provider. | N/A | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
NT10BIX5570057 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | n/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | o | 0 | 0 | 0 | 0 | N/A.When constructed, DBC's network will offer wholesale options for any provider. | 0 | N/A. | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
NT10BIX5570057 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
NT10BIX5570058 | 2010 | 0 | N/A | 0 | The homes passed at this time are with inactive plant and are in the construction phase. | 0 | Subscribers passed at this time are with inactive plant and are in the construction phase. | 0 | N/A | 10Mbps | No Variance from Baseline | 0 | N/A | 6Mbps | No Variance from Baseline | N/A, Project does not yet offer broadband, therefore no increase can be determined. | Retail Services will not be determined until network is completed, tested, and running. | Grant Recipient does not have any management polices regarding bandwidth limitations or traffic prioritization at this time. Grant Recipient has never blocked consumers from accessing any lawful content, service, service provider, application, and has not prevented any consumers from attaching any legal devices to its network. | N/A, Project has not yet been completed. | 942 | 0 | 0 | 0 | 156 | 0 | 786 | N/A Grant Recipient is not currently wholesaling any fiber in the project area. System is under construction. | 0 | 0 | 0 | 0 | At this time no other network providers have expressed interest in collocation. Customers will interconnect with network at network nodes located throughout system. | N/A, there are no subcontract or sub grants under this grant. | Best practice to provide as much dark fiber as financially feasible. It is also best practice to provide adequate start-up and initial grant administration time in the baseline performance perimeters to permit delays in initial engineering, design and permit acquisition. | City of Williamstown | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 | 0 | 2 | 5 | Grant Recipient has not entered into or is currently negotiating any interconnection agreements. Grant Recipient has not had any and has not denied any request for interconnection agreements. | Grant Recipient has not entered into or is currently negotiating an peering or transit agreements. Grant Recipient has not had any and has not denieid any request for peering or transit agreements. | TRUE
NT10BIX5570058 | 2011 | N/A | N/A | $495.33 | We have not made all draw downs on the project, The distribution construction and equipment cost totals $337814.32 divided by 682 homes passed making the average cost per homes passed $495.33 | $5118.40 | We have not made all draw downs on the project. The distribution construction and equipment cost totals $337814.32 divided by 66 subscribers making the average cost per subscriber $5118.40 | N/A | N/A | 50 Mbps | We have increased both the basic and maximum speed offerings since project was started. | N/A | N/A | 11Mbps | Increase from baseline due to our increased in speed offerings. | 9 Mbps, All three had 1 Mbps and now are at 10 Mbps. | We offer 10, 15 and 50 Mbps broadband and a full video lineup. Refer to attachment entitled Rate Card. | Grant recipient does not have any management polices regarding bandwidth limitations or traffic prioritization at this time. Grant recipient has never blocked consumers from accessing any lawful content, service, service provider, application and has not prevented any consumers from attaching any legal devices to its network. | At present time we have not had any subscribers drop the service. | 942 | 156 | 0 | 786 | 0 | 0 | 0 | N/A Grant recipient is not currently wholesaling any fiber in the project area. | 0 | 0 | 0 | 0 | At this time no other network providers have expressed interest in collocation. Customers interconnect with network at network nodes located throughout system. | N/A There are no subcontract or sub grants under this grant. | Best practice is to build as much dark fiber as financially feasible, this would allow for future expansion into other under or undeveloped areas. | City of Williamstown | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 | 0 | 2 | 5 | Grant recipient has not entered into or is currently negotiating any interconnection agreements. Grant recipient has not had any and has not denied any request for interconnection agreements | Grant recipient has not entered into or is currently negotiating any peering or transit agreements. Grant recipient has not had any and has not denied any request for peering or transit agreements | TRUE
NT10BIX5570058 | 2012 | N/A | N/A | $ 874.04 | Total of construction and equipment cost $ 596,098.00 divided by 682 homes passed making the average cost per homes passed $ 874.04 | $ 6550.53 | Total of construction and equipment cost $ 596,098.00 divided by 91 subscribers making the average cost per subscriber $6550.53 | N/A | N/A | 50 Mbps | We have increased both the basic and maximum speed offerings since project was started. | N/A | N/A | 11 Mbps | Increase from baseline due to our increased in speed offerings. | 9 Mbps, all 5 had 1 Mbps and now are at 10 Mbps. | We offer 10, 15 and 50 Mbps broadband and a full video lineup. Refer to attachment entitled Rate Card. | Grant recipient does not have any management polices regarding bandwidth limitations or traffic prioritization at this time. Grant recipient has never blocked consumers from accessing any lawful content, service, service provider, application and has not prevented any consumers from attaching any legal devices to its network. | At present time we have not had any subscribers drop the service. | 942 | 156 | 0 | 786 | 0 | 0 | 0 | N/A Grant recipient is not currently wholesaling any fiber in the project area. | 0 | 0 | 0 | 0 | At this time no other network providers have expressed interest in collocation. Customers interconnect with network at network nodes located throughout system. | N/A There are no subcontract or sub grants under this grant. | Best practice is to build as much dark fiber as financially feasible, this would allow for future expansion into other under or undeveloped areas. | City of Williamstown | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 | 0 | 2 | 5 | Grant recipient has not entered into or is currently negotiating any interconnection agreements. Grant recipient has not had any and has not denied any request for interconnection agreements. | Grant recipient has not entered into or is currently negotiating any peering or transit agreements. Grant recipient has not had any and has not denied any request for peering or transit agreements. | TRUE
NT10BIX5570059 | 2010 | N/A | N/A | 0 | Nothing to report. | 0 | Nothing to report. | N/A | N/A | 0 | Nothing to report. | N/A | N/A | 0 | Nothing to report. | Nothing to report at this time in the project. | N/A | Policies addressing network management are in development for the expanded network. These policies will soon be implemented and will have at their core the equitability mandated by the Federal Communications Commission. The District has never limited access and only monitors packets in accordance with the provisions required of the Communications Assistance for Law Enforcement Act (CALEA). | N/A | 16309 | 0 | 0 | 0 | 2120 | 0 | 14189 | Nothing to report. | 0 | 0 | 0 | 0 | Providers can interconnect with our network at our single interconnection point at the US Bank building in Spokane. Interested parties may contact Pend Oreille Public Utility District #1 for further information, or visit our website at www.popud.com. | None at this time in the project. | None at this time. | Public Utility District of Pend Oreille County | 1 | 1 | 0 | 2 | 6 | 2 |  | 2 | 0 | 0 | 14 | Nothing to report. | N/A | TRUE
NT10BIX5570059 | 2011 | N/A | N/A | 4,239 | $9,902.26 was the Year 2 Baseline. This number is significantly below the Baseline projection primarily caused by aerial plant being the only thing constructed in 2011. With addition of buried construction in 2012, this number will rise significantly by end of year three of the project. | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Nothing to report as services have not been turned up as of 12-31-11. | Pend Oreille PUD dba Community Network Systems will be entertaining agreements with Local Service Providers for a variety of retail services all of which will be finalized in 2012. To date, no agreements have been signed and pricing is still being reviewed. | Policies addressing network management are in development for the expanded network. These policies will soon be implemented and will have at their core the equitability mandated by the Federal Communications Commission. The District has never limited access and only monitors packets in accordance with the provisions required of the Communications Assistance for Law Enforcement Act (CALEA). | N/A | 16309 | 0 | 0 | 0 | 0 | 0 | 16309 | Nothing to Report. | 0 | 0 | 0 | 0 | Providers can interconnect with our network at our single interconnection point in the US Bank building in Spokane, WA. Interested parties may contact Pend Oreille Public Utility District #1 for further information, or visit our website at www.popud.org. | None at this time in the project. | Clear and open communications with your Federal Program Officer allows for a smooth and cooperative relationship during the process. | Public Utility District of Pend Oreille County | 1 | 1 | 0 | 2 | 6 | 2 |  | 2 | 0 | 0 | 14 | N/A | N/A | TRUE
NT10BIX5570059 | 2012 | $37,139.79 | 460 miles of Backbone or Middle Mile construction at a cost of 17,084,303. | $3726.43 | Baseline projection was $5061.81, with the anticipation that this number will more than likely rise as the project nears completion. | 0 | N/A There are no subscribers for service as of 12-31-12. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not applicable as services have not been turned up as of 12-31-2012. | Pend Oreille PUD dba Community Network Systems has entered into agreements with Local Service Providers for a variety of retail services all of which will be finalized in 2013. To date, pricing is still being determined by each of the Service Providers and will be available once finalized. | Policies addressing network management are in development for the expanded network. These policies will soon be implemented and will have at their core the equitability mandated by the Federal Communications Commission. The District has never limited access and only monitors packets in accordance with the provisions required of the Communications Assistance for Law Enforcement Act (CALEA). | N/A | 31000 | 0 | 0 | 25368 | 5632 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Providers can interconnect with our network at several interconnection points or at the network hub in the US Bank building in Spokane, WA. Interested parties may contact the Pend Oreille Public Utility District #1 for further information, or visit our website at www.popud.org. | None at this time in the project. | Clear and open communication with your Federal Program Officer allows for a smooth and cooperative relationship during the award process. Commitment to share lessons learned with all unserved and underserved community leaders. Building the project with openness to all interested parties seeking to expand broadband services in rural environments. | Public Utility District of Pend Oreille County | 1 | 1 | 0 | 2 | 6 | 2 |  | 2 | 0 | 0 | 14 | N/A | N/A | TRUE
NT10BIX5570059 | 2013 | 36,566 | Baseline estimates were $51,821 per mile. The final metric shows significant decrease in cost per new mile. This was calculated by taking total construction cost ($21,429,121) and multiplying by the middle mile percentage of 86 % (504 Middle miles/585 total miles) equals $18,429,044 then dividing middle mile $ by the number of middle miles (504), $36,566. | 4,286 | Baseline was $5,061, again, this cost per household metric out-performed projections and original forecasts. This was calculated by taking total construction cost ($21,429,121) divided by households (5,000). | 22,846 | Baseline projections were $17,450. This metric was short or exceeding costs based on the project lagging progress as early as originally planned. Subscribers were only recently signed up and did not reach baseline projections. This was calculated by taking total construction cost ($21,429,121) dividing by 938 original application predicted subscriber connections. | 10 Gig | Exceeding Baseline projections. | 1 Gig | Exceeding Baseline projections. | 10 Gig | Exceeding Baseline projections. | 100 Meg | Meeting Baseline Projections. | We can now offer speeds up to 1 Gig and provide redundancy across the network. Calculations were made using the current speeds provided. | Pend Oreille PUD dba Community Network Systems has entered into agreements with Local Service Providers for a variety of retail services all of which were finalized in 2013. Pricing is attached as is currently determined. | Policies addressing network management have been developed for the expanded network. These policies have been implemented and will have at their core the equitability mandated by the Federal Communications Commission. The District has never limited access and only monitors packets in accordance with the provisions required of the Communications Assistance for Law Enforcement Act (CALEA). | Customers in our area are ecstatic to have High Speed Fiber Optic Broadband services in the area. Those leaving or discontinuing service are doing so only for reason of relocating to a different area or out of our service area. | 30112 | 30112 | 0 | 0 | 0 | 0 | 0 | Pend Oreille County PUD in it's core mission of providing open access network will typically not offer to it's wholesale customers dark fiber leases. | 0 | 0 | 0 | 0 | Providers can, and have interconnected with our network at interconnection points in Pend Oreille County. Interested parties may contact the Pend Oreille Public Utility District #1 for further information, or visit our website at www.popud.org. | None at the the conclusion of the project. | Accurate Cost Accounting methods and close supervision of Sub-Contractors are two things that come to mind as we complete the project. | Public Utility District of Pend Oreille County | 1 | 1 | 0 | 2 | 6 | 2 |  | 2 | 0 | 0 | 14 | 1.) N/A 2.) N/A 3.) N/A | 1.) One-NoaNet to Douglas County. 2.) N/A 3.) N/A | TRUE
NT10BIX5570060 | 2010 | N/A | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 3Mbps | N/A | N/A | N/A | 3Mbps | N/A | The areas addressed in the project are predominantly unserved. Pine will provide Community and Anchor Institutions broadband services with a downstream speed of 3 Mbps and and upstream speed of 512 Kbps. Since the customers didnâ€™t previously have service, the average increase in broadband speeds realized will be 100% of the aforementioned amounts. | The rates are provided below in lieu of an attachment. Three tiers of broadband services will be available: 1. 1Mbps / 256Kbps - $25.00/Month 2. 1.5Mbps / 384Kbps - $45/Month 3. 3Mbps / 512Kbps - $60/Month Voice services will be offered at the following rates: Local Service - $33.25/Month Long Distance - $0.10/Minute Long Distance Optional - $3.95/Month and $0.05/Minute | 7a) NONE 7b) NO | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Pine Telephone Company will offer interconnection where technologically feasible, for exchange traffic on reasonable rates and terms to be negotiated with requesting parties. It will also adhere to interconnection requirements with respect to those wishing to connect directly to the public Internet using the projectâ€™s broadband network. Limited amounts of collocation space in Pine Telephone Companyâ€™s offices will be available. Pine Telephone Company may also be able to interconnect with service providers at network nodes or the providerâ€™s premise if technologically feasible and the provider is willing to pay the associated costs of providing interconnection. | N/A | Due to the length of time and the work involved in getting the Environmental Assessment completed and approved, it is recommended that this portion of the BTOP project be given top priority as soon as an application has been approved. | Pine Telephone Company, Inc. | 6 | 0 | 0 | 0 | 0 | 16 |  | 0 | 0 | 0 | 22 | N/A | N/A | TRUE
NT10BIX5570060 | 2011 | $191,176.50 / mile | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 3Mbps | N/A | N/A | N/A | 3Mbps | N/A | The areas addressed in the project are predominantly unserved. Pine will provide Community and Anchor Institutions broadband services with a downstream speed of 3 Mbps and and upstream speed of 512 Kbps. Since the customers didnâ€™t previously have service, the average increase in broadband speeds realized will be 100% of the aforementioned amounts. | Three tiers of broadband services will be available: 1. 1Mbps / 256Kbps - $25.00/Month 2. 1.5Mbps / 384Kbps - $45/Month 3. 3Mbps / 512Kbps - $60/Month Voice services will be offered at the following rates: Local Service - $33.25/Month Long Distance - $0.10/Minute Long Distance Optional - $3.95/Month and $0.05/Minute | 7a) Pine Telephone Company network management policies are prominently located on our website at www.pinetelephone.com 7b) NO | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Pine Telephone Company (PTC) will offer interconnection where technologically feasible, for exchange traffic on reasonable rates and terms to be negotiated with requesting parties. It will also adhere to interconnection requirements with respect to those wishing to connect directly to the public Internet using the projectâ€™s broadband network. Limited amounts of collocation space in PTCâ€™s offices will be available. PTC may also be able to interconnect with service providers at network nodes or the providerâ€™s premise if technologically feasible and the provider is willing to pay the associated costs of providing interconnection. | N/A | N/A | Pine Telephone Company, Inc. | 6 | 0 | 0 | 0 | 0 | 16 |  | 0 | 0 | 0 | 22 | N/A | N/A | TRUE
NT10BIX5570060 | 2012 | $191,176.50 / mile | N/A | $1,414.50 / household | N/A | $3,382.87 / subscriber | N/A | N/A | Pine Telephone Company is not currently advertising a middle mile component. | 3Mbps | N/A | 219Mbps | Pine Telephone Company is the only entity utilizing the middle mile segment and the speed is 219Mbps. | 3Mbps | N/A | The areas addressed in the project are predominantly unserved. Pine will provide Community and Anchor Institutions broadband services with a downstream speed of 3 Mbps and and upstream speed of 512 Kbps. Since the customers didnâ€™t previously have service, the average increase in broadband speeds realized will be 100% of the aforementioned amounts. | Three tiers of broadband services will be available: 1. 1Mbps / 256Kbps - $25/Month 2. 1.5Mbps / 384Kbps - $45/Month 3. 3Mbps / 512Kbps - $60/Month Voice services will be offered at the following rates: Local Service - $33.25/Month Long Distance - $0.10/Minute Long Distance Optional - $3.95/Month and $0.05/Minute | 7a) Pine Telephone Company network management policies are prominently located on our website at www.pinetelephone.com 7b) No | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Pine Telephone Company (PTC) will offer interconnection where technologically feasible, for exchange traffic on reasonable rates and terms to be negotiated with requesting parties. It will also adhere to interconnection requirements with respect to those wishing to connect directly to the public Internet using the projectâ€™s broadband network. Limited amounts of collocation space in PTCâ€™s offices will be available. PTC may also be able to interconnect with service providers at network nodes or the providerâ€™s premise if technologically feasible and the provider is willing to pay the associated costs of providing interconnection. | N/A | N/A | Pine Telephone Company, Inc. | 6 | 0 | 0 | 0 | 0 | 16 |  | 0 | 0 | 0 | 22 | N/A | N/A | TRUE
NT10BIX5570060 | 2013 | $14,460.54 / mile | N/A | $1,099.99 / household | N/A | $11,722.60 / subscriber | As customers subscribe to the service the cost per subscriber will drop. The application proposed an incremental turn-up of sites as they became available, but some of the approval processes required the majority of the sites to be turned up at one time closer to the end of the project. | N/A | Pine Telephone Company is not currently advertising a middle mile component. | 3 Mbps | N/A | 219 Mbps | Pine Telephone Company is the only entity utilizing the middle mile segment and the speed is 219 Mbps. | 1.17 Mbps | Currently the range of speeds is from 1 Mbps to 3 Mbps. | The areas addressed in the project are predominantly unserved. Pine provides Community and Anchor Institutions broadband services with a downstream speed of 3 Mbps and an upstream speed of 512 Kbps. Since the customers didnâ€™t previously have service, the average increase in broadband speeds realized will be 100% of the aforementioned amounts. | Three tiers of broadband services are available: 1. 1Mbps / 256Kbps - $25/Month 2. 1.5Mbps / 384Kbps - $45/Month 3. 3Mbps / 512Kbps - $60/Month Voice services are offered at the following rates: Local Service - $33.25/Month Long Distance - $0.10/Minute Long Distance Optional - $3.95/Month and $0.05/Minute | 7a) Pine Telephone Company network management policies are prominently located on our website at www.pinetelephone.com 7b) No | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Pine Telephone Company (PTC) will offer interconnection where technologically feasible, for exchange traffic on reasonable rates and terms to be negotiated with requesting parties. It will also adhere to interconnection requirements with respect to those wishing to connect directly to the public Internet using the projectâ€™s broadband network. Limited amounts of collocation space in PTCâ€™s offices will be available. PTC may also be able to interconnect with service providers at network nodes or the providerâ€™s premise if technologically feasible and the provider is willing to pay the associated costs of providing interconnection. | N/A | N/A | Pine Telephone Company, Inc. | 6 | 0 | 0 | 0 | 0 | 16 |  | 0 | 0 | 0 | 22 | N/A | N/A | TRUE
NT10BIX5570062 | 2010 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. When constructed, DBC's network will offer wholesale options for any provider. | 0 | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
NT10BIX5570062 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A. When constructed, DBC's network will offer wholesale options for any provider. | 0 | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
NT10BIX5570062 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | DigitalBridge Communications Corp. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
NT10BIX5570065 | 2010 | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | 0 | No variance | The average community anchor institution in a currently unserved or underserved rural area will see an increase of a minimum of 1.5 Mbps. In areas that have one or more providers, critical anchor institutions will see their average available service offering increase to a maximum of 10 Mbps in areas where the minimum achievable speed currently is currently only 5 Mbps. The increase was calculated based on competitive analysis of areas where broadband services are offered and not offered. All broadband speeds are based on availability of services offered by this project compared to services currently available or not available to each community anchor institution. | See Word document attached titled '03) Q-19. Attachment A - Last Mile Offerings'. | Buggs Island Telephone Cooperative will utilize a Policy Server that will restrict users from receiving more bandwidth than their service profile allows. Buggs Island Telephone Cooperative does not restrict any lawful device from attaching to the network, nor does it block consumers from accessing any content. | N/A | 0 | 0 | 928 | 0 | 0 | 0 | 0 | N/A | 1000 | 800 | 0 | 200 | Buggs Island Telephone Cooperative does own collocation space. | N/A | It is important to procure all equipment, engineering and project management services as early in the process as possible. | Buggs Island Telephone Cooperative | 32 | 12 | 0 | 8 | 31 | 25 |  | 47 | 8 | 0 | 163 | Buggs Island Telephone has not entered into any interconnection agreements. | Buggs Island Telephone has not entered into any peering and transit agreements. | TRUE
NT10BIX5570065 | 2011 | 0 | BIT is a last mile provider. | 0 | BIT has begun build-out of the network, and as of 12/31/11 there was WiMax equipment on 10 of the 35 towers. Of the sites with WiMax equipment installed, several still did not have power and others had not yet been connected to backhaul. Therefore, the service was not commercially ready at 12/31/11. There is a variance from the baseline plan. This variance is due to the fact that BIT had to get an extension on the Environmental Assessment, and several of the originally selected towers were found to be inadequate for various reasons and BIT submitted a request to NTIA for approval to change these towers to alternate sites. The approval process for this change was very lengthy, which caused changes to be made to the build-out schedule and delays in tower negotiations. BIT has submitted updated project indicators to NTIA as part of their Performance Improvement Plan (PIP). The projections in the PIP did not show subscribers until after 12/31/11, which meets the cost indicator as reported here. | 0 | BIT has begun build-out of the network, and as of 12/31/11 there was WiMax equipment on 10 of the 35 towers. Of the sites with WiMax equipment installed, several still did not have power and others had not yet been connected to backhaul. Therefore, the service was not commercially ready at 12/31/11. There is a variance from the baseline plan. This variance is due to the fact that BIT had to get an extension on the Environmental Assessment, and several of the originally selected towers were found to be inadequate for various reasons and BIT submitted a request to NTIA for approval to change these towers to alternate sites. The approval process for this change was very lengthy, which caused changes to be made to the build-out schedule and delays in tower negotiations. BIT has submitted updated project indicators to NTIA as part of their Performance Improvement Plan (PIP). The projections in the PIP did not show subscribers until after 12/31/11, which meets the cost indicator as reported here. | 0 | BIT is a last mile provider. | 0 | BIT has begun build-out of the network, and as of 12/31/11 there was WiMax equipment on 10 of the 35 towers. Of the sites with WiMax equipment installed, several still did not have power and others had not yet been connected to backhaul. Therefore, the service was not commercially ready at 12/31/11. There is a variance from the baseline plan. This variance is due to the fact that BIT had to get an extension on the Environmental Assessment, and several of the originally selected towers were found to be inadequate for various reasons and BIT submitted a request to NTIA for approval to change these towers to alternate sites. The approval process for this change was very lengthy, which caused changes to be made to the build-out schedule and delays in tower negotiations. BIT has submitted updated project indicators to NTIA as part of their Performance Improvement Plan (PIP). The projections in the PIP did not show subscribers until after 12/31/11, which meets the cost indicator as reported here. | 0 | BIT is a last mile provider. | 0 | BIT has begun build-out of the network, and as of 12/31/11 there was WiMax equipment on 10 of the 35 towers. Of the sites with WiMax equipment installed, several still did not have power and others had not yet been connected to backhaul. Therefore, the service was not commercially ready at 12/31/11. There is a variance from the baseline plan. This variance is due to the fact that BIT had to get an extension on the Environmental Assessment, and several of the originally selected towers were found to be inadequate for various reasons and BIT submitted a request to NTIA for approval to change these towers to alternate sites. The approval process for this change was very lengthy, which caused changes to be made to the build-out schedule and delays in tower negotiations. BIT has submitted updated project indicators to NTIA as part of their Performance Improvement Plan (PIP). The projections in the PIP did not show subscribers until after 12/31/11, which meets the cost indicator as reported here. | Broadband speeds have not increased since construction has not been completed and service is not yet live. | Pricing plans have not been provided, since construction has not been completed and service is not yet live. | Buggs Island Telephone Cooperative will utilize a Policy Server that will restrict users from receiving more bandwidth than their service profile allows. Buggs Island Telephone Cooperative does not restrict any lawful device from attaching to the network, nor does it block consumers from accessing any content. BIT has not yet begun providing service. | Not applicable. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not applicable. | 0 | 0 | 0 | 0 | Buggs Island Telephone Cooperative's project is a wireless broadband project and no fiber cable is being constructed for this project. | Not applicable. | It is important to procure all equipment, engineering and project management services as early in the process as possible. Additionally, if applicable, submit your Department Of Labor Davis Bacon Wage Conformance Request as early as possible. Begin working on the Environmental Assessment immediately upon acceptance of the grant in order to avoid project delays. | Buggs Island Telephone Cooperative | 32 | 12 | 0 | 8 | 31 | 25 |  | 47 | 8 | 0 | 163 | Buggs Island Telephone Cooperative (BIT) has not entered into any agreements during this annual period. BIT is negotiating with two (2) wholesale providers, and has not denied any request for interconnection. | N/A | TRUE
NT10BIX5570065 | 2012 | 0 | BIT is a last mile provider. | 311.04 | From the current funds spent at the end of 2012, that figure was divided by the number of households passed, i.e. 19,333,697 / 62,159 = 311.04. | 0 | BIT currently has not commercially deployed the service. | 0 | n/a | 0 | BIT has not begun to commercially deploy the service so no advertising has been done. | 0 | n/a | 1.5 | This is the average speed received by the beta testers. No commercial subscribers at the end of 2012. | Broadband speeds have not increased since the service has not been commercially ready. | BIT has not yet begun offering broadband services commercially as of now. | Buggs Island Telephone Cooperative will utilize a Policy Server that will restrict users from receiving more bandwidth than their selected service package. VOIP services will have prioritization over all other traffic types. BIT has not yet begun offering commercially deployed services. | Of BIT's beta testers, 20 out of 100 have dropped the service even though the beta testers were not paying for the service due to the broadband service's inconsistencies and lack of reliability and quality, i.e. firmware problems causing CPE to constantly factory default. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Applicable | 0 | 0 | 0 | 0 | Buggs Island Telephone Cooperative is a wireless broadband project and no fiber cable is being constructed for this project. | Not Applicable | It is important to procure all equipment, engineering and project management services as early in the process as possible. Additionally, if applicable, submit your Department of Labor Davis Bacon Wage Conformance Request as early as possible. Most importantly, make sure your leadership is committed and dedicated to the project's success. | Buggs Island Telephone Cooperative | 32 | 12 | 0 | 8 | 31 | 25 |  | 47 | 8 | 0 | 163 | N/A | N/A | TRUE
NT10BIX5570065 | 2013 | 0 | BIT is a last mile provider. | $106.08 | BIT has projected to begin the LTE construction in Q2 of 2014 so currently there is no commercially deployed service, however, BIT has estimated that the average cost per household passed will be based on the remaining funding divided by the number of households passed. BIT has projected to have the potential to serve 35,345 households included in the 5 county serving area but can only pass 34,322. | $2,261.34 | BIT has projected to begin the LTE construction in Q2 of 2014 so currently there is no commercially deployed service, however, BIT has estimated that the average cost per subscriber will be based on the remaining funding divided by the number of subscribers predicted to be serviced by end of the project period. BIT has projected to have the potential to serve 35,345 households included in the 5 county serving. | 0 | N/A | 4 Mbps | As explained above, BIT has not begun to commercially deploy the service so no advertising has been done, however, BIT has anticipated the maximum speeds to be delivered to the end user to be 4 Mbps. | 0 | N/A | 1.5 Mbps | No commercial subscribers at the end of 2013, however, BIT has anticipated the average broadband speeds to be delivered to the end user to be 1.5 Mbps. | Broadband speeds have not increased since the service has not been commercially ready. Construction for the retrofit to LTE is projected to begin in Q2 of 2014. | BIT has not yet begun offering broadband services commercially as of now, however, BIT has developed a comprehensive offering of products and services at competitive prices. Included in the service offerings will be wireless high-speed broadband, voice, unlimited long distance, up to 10 calling features. The minimum broadband high-speed internet that will be available to the residents and businesses in the 5 county service area will be 1.5 Mbps of service. Generally, residential and business subscribers will have the option to upgrade to 3.0 or 4.0 Mbps of service for an additional monthly fee. BIT estimates that the monthly access rates to residential subscribers will be between $30 and $60 per month for internet service based on the selected package. Business rates will be between $40 and $90 per month based on the selected package. All subscribers will be charged a monthly $3.00 lease fee for the Customer Premise Equipment (CPE). See attachment that provides the specific pricing plans. | BIT will utilize a Policy Server that will restrict users from receiving more bandwidth than their selected service package. VOIP services will have prioritization over all other traffic types. BIT has not yet begun offering commercially deployed services. Construction for the retrofit to LTE is projected to begin in Q2 of 2014. | Of BIT's remaining WiMAX customers, 50 out of 100 have dropped the service, even though they are not paying for the service, due to the WiMAX broadband service's inconsistencies, lack of reliability and quality, i.e.. interference issues. BIT plans to retrofit the remaining customers with LTE, once the network has been deployed, as beta testers for the new service. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Other network providers can connect to BIT's network via a Virtual Private Network (VPN) using their current Internet Service Provider (ISP) for provisioning of subscriber services. Customers would connect to BIT's network using either a Customer Premise Equipment (CPE) or a User Equipment (UE) device that contains a SIM card. | N/A | It is important to thoroughly review all contracts and if possible, have amendments to the contracts that allow a means of termination if the products are not delivered as stated in the contract. Contract negotiations can lead to a tedious and lengthy process which can potentially delay your project milestones, so start the process as early as possible. Work closely with your vendors in order to have project milestones and the time line as precise as possible in order to meet the requirements you set forth in your BTOP application. Always make sure your quarterly and annual reports are filed on time. Delinquent reports affect your good standing and are unacceptable with the rules and regulations of your grant. Most importantly, make sure your leadership and staff is committed and dedicated to the project's success. An extreme amount of man hours go in to the successful implementation of your project, so be prepared. Have the essential staff dedicated for this purpose. | Buggs Island Telephone Cooperative | 32 | 12 | 0 | 8 | 31 | 25 |  | 47 | 8 | 0 | 163 | N/A | BIT's equipment vendor ordered circuits in 12/2013 through Level 3 and Mid-Atlantic Broadband in order to connect BIT to the hosted core (SuperCenter) in Texas. | TRUE
NT10BIX5570066 | 2010 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No formal policy since this a middle-mile project and we structure based on leases needs, however, we do prioritize commercial traffic over residential, and we prioritize voice traffic (VoIP) over other types. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | We will add 7 PoPs (connection points) as part of the middle-mile build out of the routes and customers will connect through these facilities. | N/A | Best advice we can give is to contact the agencies (especially US Forest Service and the US Fish and Wildlife Service) early, keep them in the loop, and communicate with them frequently. Aggressively push for responses, else in our experience, responses will be very slow or not received at all. Also, engage a qualified environmental assessment expert with a comprehensive background in all aspects associated with environmental studies. As we have learned in dealing with the environmental assessment process, the examples of previous reports referenced by NTIA as guidelines for a complete assessment did not address several environmental issues that were noted as deficiencies in the EA we submitted. This has caused us to scramble to get the needed information very late in the process when we had up-front time available, before EA submission, to get the information marked as deficient. We would hope that a qualified EA consultant would recognize missing areas even though not specifically listed in examples. | BVU Authority | 33 | 4 | 8 | 3 | 16 | 32 |  | 18 | 9 | 2 | 125 | N/A | N/A | TRUE
NT10BIX5570066 | 2011 | 70,034 | Cost a factor of higher than expected hard rock found during underground burial. To mitigate, some of the planned underground fiber was changed to aerial. No impact to Environmental Assessment since assessment discussed both options and study was based on most intrusive impact (i.e. buried fiber). Fiber being built on VDOT rights-of-way. | 0 | N/A | 0 | N/A | 10Gb | Consistent with plan. | 0 | N/A | 2Gb | N/A | 0 | N/A | N/A. Broadband speeds have not increased since project is middle mile and we are not providing direct connection to any CAI's as part of the project. | N/A. Only providing dark fiber services as part of middle mile project. | No services have yet begun over the constructed routes. We do not have a formal policy since this a middle-mile project and we structure services based on lease needs, however, we do prioritize commercial traffic over residential, and we prioritize voice traffic (VoIP) over other types. | N/A | 72051 | 0 | 0 | 34552 | 0 | 0 | 37499 | N/A. No customers as of end of reporting period. | 0 | 0 | 0 | 0 | We will add 5 PoPs (connection points) as part of the middle-mile build out of the routes and customers will connect through these facilities. | N/A | Best advice we can give is to contact the agencies (especially US Forest Service and the US Fish and Wildlife Service) early, keep them in the loop, and communicate with them frequently. Aggressively push for responses, else in our experience, responses will be very slow or not received at all. Also, engage a qualified environmental assessment expert with a comprehensive background in all aspects associated with environmental studies. As we have learned in dealing with the environmental assessment process, the examples of previous reports referenced by NTIA as guidelines for a complete assessment did not address several environmental issues that were noted as deficiencies in the EA we submitted. This has caused us to scramble to get the needed information very late in the process when we had up-front time available, before EA submission, to get the information marked as deficient. We would hope that a qualified EA consultant would recognize missing areas even though not specifically listed in examples. | BVU Authority | 33 | 4 | 8 | 3 | 16 | 32 |  | 18 | 9 | 2 | 125 | We do not have any interconnection agreements at this time. No last mile providers have contacted BVU requesting interconnection to-date. However, BVU has provided last mile interconnection to the first completed route for Hiltons, VA, themselves. | N/A | TRUE
NT10BIX5570066 | 2012 | 74,024 | Cost a factor of higher than expected hard rock found during underground burial. To mitigate, some of the planned underground fiber was changed to aerial. No impact to Environmental Assessment since assessment discussed both options and study was based on most intrusive impact (i.e. buried fiber). Fiber being built on VDOT rights-of-way. | 0 | N/A | 0 | N/A | 10 Gb | Consistent with plan. | 0 | N/A | 2 Gb | Consistent with plan. | 0 | N/A | N/A. Broadband speeds have not increased since project is middle mile and we are not providing direct connection to any CAI's as part of the project, unless approved by NTIA with any surplus funds. | N/A. Only providing dark fiber services as part of middle mile project. | We do not have a formal policy since this a middle-mile project and we structure services based on lease needs, however, we do prioritize commercial traffic over residential, and we prioritize voice traffic (VoIP) over other types. | N/A | 68332 | 1842 | 0 | 0 | 66302 | 0 | 188 | Virginia Department of Transportation (VDOT): 188 miles | 972 | 972 | 0 | 0 | It was expected that colocation space would be available. However, actual PoP structures purchased, due to cost, are compact and will not allow BVU to support full colocation, except for perhaps, some rack space. Other network providers would connect by running their fiber from their PoP into the BVU PoP for connection to our fiber panel/equipment. | N/A | Best advice we can give is to contact the agencies (especially US Forest Service and the US Fish and Wildlife Service) early, keep them in the loop, and communicate with them frequently. Aggressively push for responses, else in our experience, responses will be very slow or not received at all. Also, engage a qualified environmental assessment expert with a comprehensive background in all aspects associated with environmental studies. As we have learned in dealing with the environmental assessment process, the examples of previous reports referenced by NTIA as guidelines for a complete assessment did not address several environmental issues that were noted as deficiencies in the EA we submitted. This has caused us to scramble to get the needed information very late in the process when we had up-front time available, before EA submission, to get the information marked as deficient. We would hope that a qualified EA consultant would recognize missing areas even though not specifically listed in examples. Lastly, spend time researching how to correctly fill out the necessary reports. The instructions are somewhat vague. Attend webinars on how to interpret the instructions. | BVU Authority | 33 | 4 | 8 | 3 | 16 | 32 |  | 18 | 9 | 2 | 125 | We do not have any interconnection agreements at this time. No last mile providers have contacted BVU requesting interconnection to-date. However, BVU has provided last mile interconnection to Hiltons, VA, themselves. BVU plans to connect some other cities on the completed routes through other funding sources. | N/A | TRUE
NT10BIX5570066 | 2013 | 63,108 | Cost calculation only considers costs associated with new miles (not leased or upgraded miles) and include ONLY costs associated with conduit, cables, towers, antennas/wireless transceivers, and the labor used to install transmission infrastructure. Cost per mile higher than expected due to hard rock found during underground burial. To mitigate hard rock costs, some of the planned underground fiber was changed to aerial. No impact to Environmental Assessment since assessment discussed both options and study was based on most intrusive impact (i.e. buried fiber). Fiber being built on Virginia Department of Transportation's rights-of-way. | 0 | NA. Middle mile project. | 0 | NA. Middle mile project. | 10 Gbps | Consistent with plan. | 0 | NA. Middle mile project does not include providing last mile | 2 Gbps | Consistent with plan. | 0 | NA. Middle mile project does not include providing last mile | Broadband speeds have not increased since project is middle mile and we are not providing direct connection to any Community Anchor Institutions's as part of the project, however, increased speeds will be achieved when last mile provided. Many Community Anchor Institutions along routes are accessing network through Digital Subscriber Line (1.5 Megabits per second) and the new fiber network could offer, on average, 2 Gigabits per second, or an increase of over 1300%. | NA | We do not have a formal policy since this a middle-mile project and we structure services based on lease needs, however, we do prioritize commercial traffic over residential, and we prioritize voice traffic (Voice Over Internet Protocol) over other types. | NA | 67653 | 1842 | 188 | 65623 | 0 | 0 | 0 | Virginia Department of Transportation (VDOT): 188 strand-miles. | 1141 | 1057 | 0 | 84 | There is space for one rack, which consist of 44 vertical rack units, in each National Telecommunications and Information Administration / Broadband Technologies Opportunity Program funded PoP (Point-of-Presence) site. The floor space would equate to 14 square feet of area for the rack and access room around it. Facility Identifer/Name County Total Sq Ft Colocation Space Sq Ft Bland PoP Bland, VA 162.4 14.0 Broadford PoP Smyth, VA 162.4 14.0 Damascus PoP Washington, VA 162.4 14.0 Rosedale PoP Russell, VA 185.6 14.0 Valley PoP Washington, VA 162.4 14.0 Wytheville PoP Wythe, VA 306.0 14.0 Optionally, any provider could interconnect at BVU Authority's primary data center and utilize in place transport equipment to the PoP (Point-of-Presence) sites. The data center has a dedicated colocation center. | NA | Best advice we can give is to contact the agencies (especially US Forest Service and the US Fish and Wildlife Service) early, keep them in the loop, and communicate with them frequently. Aggressively push for responses, else in our experience, responses will be very slow or not received at all. Also, engage a qualified environmental assessment expert with a comprehensive background in all aspects associated with environmental studies. As we have learned in dealing with the environmental assessment process, the examples of previous reports referenced by Broadband Technology Opportunities Program as guidelines for a complete assessment did not address several environmental issues that were noted as deficiencies in the Environmental Assessment we submitted. This has caused us to scramble to get the needed information very late in the process when we had up-front time available, before EA submission, to get the information marked as deficient. We would hope that a qualified Environmental Assessment consultant would recognize missing areas even though not specifically listed in examples. Also, spend time researching how to correctly fill out the necessary reports. The instructions are somewhat vague. Attend webinars on how to interpret the instructions. Lastly, be flexible as the instructions for filling out reports changed quite often and different Broadband Technology Opportunities Program administrative departments did not always agree on what report is needed or what information is needed in report. We consistantly had to go back and amend report information. | BVU Authority | 33 | 4 | 8 | 3 | 16 | 32 |  | 18 | 9 | 2 | 125 | NA | NA | TRUE
NT10BIX5570067 | 2010 | $0.00 | Construction has not started, awaiting FONSI | n/a | Per our program application & baseline, we are targeting community anchor institutions. This is a middle mile project | n/a | Per our program application & baseline, we are targeting community anchor institutions. This is a middle mile project | n/a | Construction has not started, awaiting FONSI | n/a | Construction has not started, awaiting FONSI | n/a | Construction has not started, awaiting FONSI | n/a | Construction has not started, awaiting FONSI | N/A. Construction has not begun on our middle mile project, as we are awaiting receipt of our "FONSI". | N/A. Construction has not begun on our middle mile project, as we are awaiting receipt of our "FONSI". | 7a. OneCommunity rates limit customer traffic per their contracted committed information rate. On top of the CIR the customer has the ability to burst at 50% above their ordered bandwidth. An example of this is a customer contract has a CIR of 100Mbps the circuit would be provisioned for 150Mbps to allow them to burst. The exception to this rule is when TDM or SONET circuit are used to deliver last mile, for these levels circuits are delivered at DS-1, DS-3, OC-3, -OC-12, OC-48, and OC-192 speeds and cannot exceed the Committed information rate. OneCommunity uses MPLS traffic engineering to assure the customers always get the subscribed bandwidth. Traffic prioritization is based on the type of traffic that is sent to the network. OneCommunity breaks priorities into 4 sub categories, real time, Transactional, Video, and Best Effort. For Real-time, OneCommunity supports DSCP Expedited forwarding for real time traffic such as Video or voice this method has priority on the OneCommunity network. Transactional video is the next tier of QoS using DSCP Assured Forwarding 21 (AD21) for traffic such as Time Sensitive Data, Mission Critical applications, Low Bandwidth applications, Bursty data like Telnet and web applications. The third tier of Qos is Video using DSCP Assured forwarding 41 (AF41) tags for traffic such as general video and business critical applications such as SAP, Siebel, and Citrix. The fourth tier of QoS is Best effort, this has the lowest priority and is meant fo | N/A. This is a middle mile project, and construction has not yet started. | 160608 | 0 | 0 | 0 | 36518 | 3384 | 120706 | N/A - we do not currently wholesale and dark fiber. | 0 | 0 | 0 | 0 | OneCommunity will be upgrading five (5) existing core network locations and building out thirteen (13) new core locations in primarily commercially available collocation space, such as that offered by ATT, Verizon, First Energy, Conneaut Telephone, Horizon Telecom, and ComNet. Two of the new locations will be collocation/leased space from OARnet, our sub-recipient / partner in the project. All space is leased, with capacity available in the commercially available collocation spaces. | None at this time | We are just preparing for construction ramp up. | ONECOMMUNITY | 1402 | 94 | 39 | 14 | 197 | 74 |  | 36 | 29 | 0 | 1885 | (1) none were entered into / signed during the period or since project inception (2) as of 12/31/2010, none were under negotiation (3) as of 12/31/2010, OneCommunity has never denied an request for interconnection | (1) none were entered into / signed during the period or since project inception (2) as of 12/31/2010, none were under negotiation (3) as of 12/31/2010, OneCommunity has never denied an request for interconnection or peering | TRUE
NT10BIX5570067 | 2011 | 17,481 | based on ring segments that were completed and "lit" during the period (costs include direct and allocated costs for construction materials, labor). In my baseline, I estimated higher costs for initial miles, leveling off to our historic average as we got more miles completed and spread out the non-variable costs. The costs on which the 2011 Annual PR average is based is direct costs for completed miles only. The miles completed were the miles that could be easily â€œclearedâ€ â€“ e.g., they did not require much if any â€œmake readyâ€, and therefore experienced a below average cost. When these miles are combined with miles which will be built in 2012, we will see the overall average climb closer to our historic levels of $25k per mile. | 0 | Not Applicable | 0 | not applicable | 10 gigabits | per baseline | 0 | not applicable | 364 mbps | calculated as the weighted average of all new or improved CAI connections made during 2011. EX: 28 CAI's at 10 mbps each = 280 total mbps in equation. Sum of all mbps/total CAI's = avg bandwidth | 0 | not applicable | The average speed for all current CAI connections is 364 mbps, as calculated by the sum of all mbps available to all locations, divided by the number of locations. For example, 28 locations have a 10 mbps service, that would be 280 mpbs available and added into the numerator. At the other end of the spectrum we have 30 locations with 1 gigabit of service, or 1,000 mbps each, for a total of 30,000 mbps added into the numerator. Sum of all mbps available divided by number of locations resulted in the average of 364 mbps. | not applicable. | QUESTION 7a. OneCommunity rates limit customer traffic per their contracted committed information rate. On top of the CIR the customer has the ability to burst at 50% above their ordered bandwidth. An example of this is a customer contract has a CIR of 100Mbps the circuit would be provisioned for 150Mbps to allow them to burst. The exception to this rule is when TDM or SONET circuit are used to deliver last mile, for these levels circuits are delivered at DS-1, DS-3, OC-3, -OC-12, OC-48, and OC-192 speeds and cannot exceed the Committed information rate. OneCommunity uses MPLS traffic engineering to assure the customers always get the subscribed bandwidth. Traffic prioritization is based on the type of traffic that is sent to the network. OneCommunity breaks priorities into 4 sub categories, real time, Transactional, Video, and Best Effort. For Real-time, OneCommunity supports DSCP Expedited forwarding for real time traffic such as Video or voice this method has priority on the OneCommunity network. Transactional video is the next tier of QoS using DSCP Assured Forwarding 21 (AD21) for traffic such as Time Sensitive Data, Mission Critical applications, Low Bandwidth applications, Bursty data like Telnet and web applications. The third tier of Qos is Video using DSCP Assured forwarding 41 (AF41) tags for traffic such as general video and business critical applications such as SAP, Siebel, and Citrix. The fourth tier of QoS is Best effort, this has the lowest priority and is | Not applicable. | 150917 | 1249 | 484 | 3748 | 26532 | 4080 | 114824 | Windstream LLC - 2 IRU agreements (1 @ 50 miles, 4 fibers, 20 years; 1 @ 41 miles, 4 fibers, 20 years) ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years | 0 | 0 | 0 | 0 | OneCommunity leases space in established data centers, telco company central offices, and other collocation spaces. We interconnect to other carriers at these "hub site" locations following the prescribed procedures in each collocation facility. Please reference question #2 for a list of current and planned "hub sites". All sites are POPs with Internet gateways. | None at this time. | None at this time. FOR Question 15 - we are using census blocks from the 2000 census, in order to stay consistent with our application. | ONECOMMUNITY | 1402 | 94 | 39 | 14 | 197 | 74 |  | 36 | 29 | 0 | 1885 | A total of seventy one (71) interconnection, peering and/or transit agreements were either entered into or enhanced during the period as a result of establishing a new presence or upgrading existing hub sites. Six new hub site locations (see Excel addendum for Question #2) were established, seven existing hub site locations were upgraded. As of the end of the reporting period, no other interconnection, peering or transit agreements were under active negotiations. OneCommunity operates a completely open network and has never denied any request for interconnection. | Prior to the grant OneCommunity had - and maintains - 2 peering agreements (with Level 3 and Global Crossings, but they have since merged). Prior to the grant also OneCommunity had - and maintains - almost a dozen transit agreements with the major carriers and other parties in our northeast Ohio area. In addition, as part of the grant OneCommunity is negotiating 3 transit agreements with our partners in the Ohio Middle Mile Consortium (OMMC), with ComNet and Horizon Telephone and OARnet Ohio's Advanced Research network for higher ed institutions. | TRUE
NT10BIX5570067 | 2012 | 27471 | Based on the total costs per ring segment, divided by total fiber miles deployed. Total costs include: engineering/"EA" costs, pole owner engineering and make ready costs, construction labor, and materials. | 0 | not applicable | 0 | not applicable | 10 gigabits/sec | per baseline | 0 | not applicable | 343 | Calculated as the average of the speeds of all CAI's from inception to-date as of 12-31-2012 | 0 | not applicable | The average speed for all currently connected CAI's is 343 mbps (calculated as the average speed of circuits provided to CAI's where fiber was built into the building). The average speed is estimated to be 2 to 4 times greater, on average, across all locations with new or improved service. | Please see additional attachment for current MSA pricing on file with the State of Ohio. | QUESTION 7a. OneCommunity rates limit customer traffic per their contracted "committed information rate". On top of the CIR the customer has the ability to burst at 50% above their committed rate. An example of this is, a customer who has a contract at a CIR of 100Mbps the circuit would be provisioned for 150Mbps to allow them to burst. The exception to this rule is when TDM or SONET circuit are used to deliver last mile, for these levels circuits are delivered at DS-1, DS-3, OC-3, -OC-12, OC-48, and OC-192 speeds and cannot exceed the "committed information rate". OneCommunity uses MPLS traffic engineering to assure the customers always get the subscribed bandwidth. Traffic prioritization is based on the type of traffic that is sent to the network. OneCommunity breaks priorities into 4 sub categories, real time, Transactional, Video, and Best Effort. For Real-time, OneCommunity supports DSCP Expedited forwarding for real time traffic such as Video or voice this method has priority on the OneCommunity network. Transactional video is the next tier of QoS using DSCP Assured Forwarding 21 (AD21) for traffic such as Time Sensitive Data, Mission Critical applications, Low Bandwidth applications, Bursty data like Telnet and web applications. The third tier of Qos is Video using DSCP Assured forwarding 41 (AF41) tags for traffic such as general video and business critical applications such as SAP, Siebel, and Citrix. The fourth tier of QoS is Best effort, this has the lowest pri | Not Applicable. | 151827 | 26005 | 243 | 121710 | 1872 | 124 | 1872 | NEW: SIGNED - NOVA TELEPHONE - - 60 month term, 1Gigabit subscription (note this is a subscription) - WINDSTREAM - 2 IRU agreements (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years - United Private Networks - 20 year IRU, 2 strands, 6 miles PENDING - Cox Communications - dark fiber IRU (2 strands, 45 miles, 20 year term) | 0 | 0 | 0 | 0 | OneCommunity leases space in established data centers, telco company central offices, and other collocation spaces. We interconnect to other carriers at these "hub site" locations following the prescribed procedures in each collocation facility. Please reference question #2 for a list of current and planned "hub sites". All sites are POPs with Internet gateways. | None at this time. | FOR Question 15 - we are using census blocks from the 2000 census, in order to stay consistent with our application. | ONECOMMUNITY | 1402 | 94 | 39 | 14 | 197 | 74 |  | 36 | 29 | 0 | 1885 | We had or now have relationships with the following wholesale/last mile providers: Global Crossing, North Coast Wireless, Net X Internet, Mango Bay Internet, ACC, Time Warner Cable, Agile Networks, and Continental Broadband (formerly Expedient), and Time Warner Telecomm of Ohio. We have sold to all of these entities (and have purchased from some). NEW: SIGNED - NOVA TELEPHONE - - 60 month term, 1Gigabit subscription. - WINDSTREAM - 2 IRU agreements (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years - United Private Networks - 20 year IRU. - ALLTEL - signed services agreement with last mile provider PENDING - Cox Communications - dark fiber IRU (2 strands, 45 miles, 20 year term) | Prior to the grant OneCommunity had - and maintains - 2 peering agreements (with Level 3 and Global Crossings, but they have since merged). Prior to the grant also OneCommunity had - and maintains - almost a dozen transit agreements with the major carriers and other parties in our northeast Ohio area. In addition, as part of the grant OneCommunity is negotiating 3 transit agreements with our partners in the Ohio Middle Mile Consortium (OMMC), with ComNet and Horizon Telephone and OARnet Ohio's Advanced Research network for higher ed institutions. | TRUE
NT10BIX5570067 | 2013 | 27604.75 | Based on the total costs per ring segment, divided by total fiber miles deployed. Total costs include: engineering/"EA" costs, pole owner engineering and make ready costs, construction labor, and materials. | 0 | n/a | 0 | n/a | 10 Gbps | per baseline | 0 | n/a | 313 | calculated as the average of the speeds of all CAI's where new service was provided | 0 | not applicable | The average speed for all currently connected CAI's is 313 mbps (calculated as the average speed of circuits provided to CAI's where fiber was built into the building). The average speed is estimated to be 2 to 4 times greater, on average, across all locations with new or improved service. | Please see additional attachment for current MSA pricing on file with the State of Ohio. | QUESTION 7a. OneCommunity rates limit customer traffic per their contracted "committed information rate". On top of the CIR the customer has the ability to burst at 50% above their committed rate. An example of this is, a customer who has a contract at a CIR of 100Mbps the circuit would be provisioned for 150Mbps to allow them to burst. The exception to this rule is when TDM or SONET circuit are used to deliver last mile, for these levels circuits are delivered at DS-1, DS-3, OC-3, -OC-12, OC-48, and OC-192 speeds and cannot exceed the "committed information rate". OneCommunity uses MPLS traffic engineering to assure the customers always get the subscribed bandwidth. Traffic prioritization is based on the type of traffic that is sent to the network. OneCommunity breaks priorities into 4 sub categories, real time, Transactional, Video, and Best Effort. For Real-time, OneCommunity supports DSCP Expedited forwarding for real time traffic such as Video or voice this method has priority on the OneCommunity network. Transactional video is the next tier of QoS using DSCP Assured Forwarding 21 (AD21) for traffic such as Time Sensitive Data, Mission Critical applications, Low Bandwidth applications, Bursty data like Telnet and web applications. The third tier of Qos is Video using DSCP Assured forwarding 41 (AF41) tags for traffic such as general video and business critical applications such as SAP, Siebel, and Citrix. The fourth tier of QoS is Best effort, this has the lowest pri | Not applicable. | 160994 | 31118 | 1902 | 127974 | 0 | 0 | 0 | - NOVA TELEPHONE - - 60 month term, 1Gigabit subscription (note this is a subscription) - WINDSTREAM - 2 IRU agreements (1 @ 50 miles 4 fibers 20 years; 1 @41 miles for 4 fibers 20 years) - ZITO MEDIA - IRU for 8 dark fibers, 15 miles, 20 years - United Private Networks - 20 year IRU, 2 strands, 6 miles - Cox Communications - dark fiber IRU (2 strands, 45 miles, 20 year term) | 0 | 0 | 0 | 0 | OneCommunity leases space in established data centers, telco company central offices, and other collocation spaces. We interconnect to other carriers at these "hub site" locations following the prescribed procedures in each collocation facility. Please reference question #2's Addendum for a list of "hub sites". All sites are POPs with Internet gateways. | None. | None at this time. | ONECOMMUNITY | 1402 | 94 | 39 | 14 | 197 | 74 |  | 36 | 29 | 0 | 1885 | We had or now have relationships with the following wholesale/last mile providers: Global Crossing/Level 3 (existing/improved) North Coast Wireless (existing/improved) NetX Internet (new) Windstream KDL (existing/improved) Mango Bay Internet (new) Zito Media (existing/improved) ACC (new) Time Warner Cable (existing/improved) Agile Networks (new) Continental Broadband (existing/improved) Time Warner Telecom of Ohio (existing/improved) United Private Networks (new) Alltel Wireless (new) Cox Communications (new) Fidelity Access Networks (new) | Prior to the grant OneCommunity had - and maintains - 2 peering agreements (with Level 3 and Global Crossings, but they have since merged). Prior to the grant also OneCommunity had - and maintains - almost a dozen transit agreements with the major carriers and other parties in our northeast Ohio area. In addition, as part of the grant OneCommunity is negotiating 3 transit agreements with our partners in the Ohio Middle Mile Consortium (OMMC), with ComNet and Horizon Telephone and OARnet Ohio's Advanced Research network for higher ed institutions. | TRUE
NT10BIX5570068 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 7a. Existing network management policies will be used 7b. No | N/A | 58296 | 0 | 0 | 58296 | 0 | 0 | 0 | N/A | 3700 | 0 | 0 | 3700 | We own co location space | N/A | N/A | Valley Telephone Cooperative, Inc. | 12 | 2 | 5 | 22 | 27 | 3 |  | 10 | 84 | 0 | 165 | N/A | N/A | TRUE
NT10BIX5570068 | 2011 | 0 | Construction underway, but no cost information yet | 0 | Does not apply | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | [REDACTED] | [REDACTED] | N/A | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | N/A | 3700 | 0 | 0 | 3700 | We own the collocation space. | N/A | Obtain approval from NEPA to do engineering at the same time the Phase 1 Environmental Assessment is being performed. This can solve a lot of potential problems that may be encountered later, e.g., EA route is acceptable, but city will not allow permits to build the route along the proposed or approved EA route. | Valley Telephone Cooperative, Inc. | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | N/A | N/A | TRUE
NT10BIX5570068 | 2012 | $39,970 | Rio Grande City, Harlingen - Brownsville, Brownsville - Weslaco, Weslaco - Hidalgo, Brownsville - Hidalgo (express route) and six in-kind contribution routes (total of 370 miles) | 0 | N/A | 0 | N/A | 2.5 Gbps | Initial maximum wholesale offering will be equivalent to an OC48 (2.5 Gbps) with a future offering of an OC192 equivalent (10 Gbps) available in the future. | 0 | N/A | 622 Mbps | Out of the seven inital speed tiers offered, the OC12 (622 Mbps) is the average. | 0 | N/A | The dark fiber being provided to CAIs is not replacing an existing connection, so no increase calculation is possible. Also, since we are delivering dark fiber, actual bandwidth for the connection will be determined by each CAIs choice of network electronics. | We will be offering transport, Internet access, and/or collocation services. The transport service includes point-to-point (a.k.a.; A-to-Z) connectivity with a selection of bandwidth options. Internet access adds connectivity through our Internet gateway; and is also available in a selection of bandwidth options. (Speed and price tiers attached) | 7a) We will utilize our current management policies across this network. Bandwidth limitations are determined by contracted servce tiers and traffic prioritization is only done for quality of service (QoS) purposes. 7b) We do not block or censor our connections. | N/A | 50318 | 93 | 0 | 38952 | 5219 | 6054 | 0 | N/A | 4800 | 840 | 0 | 3960 | N/A (We own the collocation space.) | N/A | Obtain approval from NEPA to do engineering at the same time the Phase 1 Environmental Assessment is being performed. This can solve a lot of potential problems that may be encountered later, e.g., EA route is acceptable, but city will not allow permits to build the route along the proposed or approved EA route. | Valley Telephone Cooperative, Inc. | 12 | 2 | 5 | 22 | 27 | 3 |  | 10 | 84 | 0 | 165 | 1) Did not enter into any agreements during this reporting period. 2) We are currently negotiating two (2) interconnection agreements. 3) We have not denied any requests for interconnection. | 1) Did not enter into any agreements during this reporting period. 2) Negotiating dark fiber IRU participation agreements with five (5) entities. | TRUE
NT10BIX5570068 | 2013 | 64475 | Construction costs of $12,894,941 / 200 new miles constructed = $64,475 per mile. Baseline projections were for approximately $94,853 per mile. | 0 | N/A | 0 | N/A | 10 Gbps | As per baseline plan. | 0 | N/A | 0 | All participant CAIs have been connected. However, they have been provided with dark fiber drops, as per the baseline plan. As none of the participant CAIs have currently installed equipment to utilize the dark fiber at this time, we cannot calculate an average speed. | 0 | N/A | All of the current CAIs are dark fiber recipients that have not yet connected equipment to their fibers. It is, therefore, not possible to calculate a figure for increased bandwidth speed at this time. | We will be offering transport, Internet access, and/or collocation services. The transport service includes point-to-point (a.k.a.; A-to-Z) connectivity with a selection of bandwidth options. Internet access adds connectivity through our Internet gateway; and is also available in a selection of bandwidth options. (Speed and price tiers attached) | 7a) We will utilize our current management policies across this network. Bandwidth limitations are determined by contracted servce tiers and traffic prioritization is only done for quality of service (QoS) purposes. 7b) We do not block or censor our connections. | N/A | 50318 | 93 | 0 | 50225 | 0 | 0 | 0 | We do offer dark fiber access as a service, but currently do not have any commercial subscribers leasing this option. We have provided dark fiber to participant CAIs without a lease fee as a condition of the grant award. (So, technically, they are not being leased.) Those institutions are: South Texas College (20 fibers), University of Texas Pan American (20 fibers), Texas State Technical College (20 fibers), Texas Southmost College (10 fibers), University of Texas Brownsville (10 fibers), and University of Texas Health Science Center (20 fibers). All together, these entities account for 100 fiber strands throughout this network; or approximately 50% of all strand-miles deployed. | 4800 | 840 | 0 | 3960 | N/A (We own the collocation space.) | N/A | 1) Obtain approval from NEPA to perform engineering at the same time as the Phase 1 Environmental Assessment. This can solve a lot of potential problems that may be encountered later, e.g., EA route is acceptable, but city will not allow permits to build the route along the proposed or approved EA route. 2) The Federal Program Officers are an invaluable resource when trying to learn the, sometimes confusing, reporting requirements of federal grants. Engaging them early on when difficulties arise can same a lot of time. 3) Do not pass up the opportunity to attend the many webinars that are offered. Many times, the topic discussed presents solutions to problems that several recipients are experiencing. | Valley Telephone Cooperative, Inc. | 12 | 2 | 5 | 22 | 27 | 3 |  | 10 | 84 | 0 | 165 | 1) One (1) interconnection agreement was established during this reporting period. 2) We are currently negotiating one (1) interconnection agreement. 3) We have not declined any requests for interconnection. | 1) Five (5) transit agreements were established during this reporting period encompassing seven (7) entities. 2) We are in the process of hiring staff to market and negotiate new transit agreements on this network. | TRUE
NT10BIX5570069 | 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | 18928 | 9212 | 0 | 0 | 6846 | 0 | 2870 | N/A - No new BTOP network was physically deployed in calendar year 2010 | 0 | 0 | 0 | 0 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | The key to successfully moving forward the BTOP project was solid out front planning and initial focus on driving through all issues related to the Environmental Assessment process. The entire ICN plan was committed very early on to the Microsoft Project Planning format so all details large and small would receive adequate visibility with the entire project team. Without this type of format critical task and time line linkages would be difficult to identify and manage. The Environmental Assessment process required a great deal of communication and follow up with a myriad of entities. It is suggested that this communication occur early and project teams remain highly focused and subsequently follow up regarding any refinements or adjustments that may be needed to clear each particular agency. Don't hesitate to contact BTOP support staff for clarification and guidance throughout the process. This will help with formulating the required components of the EA draft. Meet regularly with a specific agenda not only with your BTOP team but with the Federal Program Management team as well. Clear communication combined with clear goals and time lines for detail management will keep a complex process steadily moving forward. There are not any "short cuts". Steady organized effort will deliver results. | Iowa Communications Network | 596 | 61 | 109 | 204 | 203 | 343 |  | 1185 | 117 | 0 | 2818 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | TRUE
NT10BIX5570069 | 2011 | 0 | No new miles have yet been constructed. Baseline shows total for end of project. | 0 | Baseline indicates N/A. | 0 | Baseline indicates N/A. | 1Gbps | No variation from baseline. | 1Gbps | No variation from baseline. | 34Mbps | No variation from baseline. | 34Mbps | No variation from baseline. | Broadband speeds are increased at the request of customers. For example, Community School District in Williamsburg, Iowa ordered an increase from 25Mb to 100Mb of Ethernet services in December 2011. Previous to the BTOP switch and DWDM deployment, the maximum capacity at the location was 45Mb of which 25Mb was the maximum Ethernet service they could get. Current maximum capacity now is 1Gbs which allowed them to order the additional 75Mb. | Ethernet Private Line Service - Symmetrical, 10Mbps $360 per month Ethernet Private Line Service - Symmetrical, 20Mbps: $500 per month Ethernet Private Line Service - Symmetrical, 50Mbps: $750 per month Ethernet Private Line Service - Symmetrical, 100Mbps: $900 per month Ethernet Private Line Service - Symmetrical, 1Gbps: $2,100 per month Premium Internet - Symmetrical, 10Mbps: $920 per month Premium Internet - Symmetrical, 20Mbps: $1,480 per month Premium Internet - Symmetrical, 500Mbps: $3,385 per month Premium Internet - Symmetrical, 100Mbps: $5,661 per month | The project has no non-capacity related bandwidth limitations. During normal operations, traffic is not prioritized. During declared emergencies and public safety events, traffic may be prioritized to public safety organizations as defined by law. The project includes no restrictions on any legal device. | N/A | 19009 | 6000 | 0 | 0 | 0 | 0 | 13009 | N/A ICN wholesales no dark fiber. | 0 | 0 | 0 | 0 | As a state agency, the ICN receives collocation space without charge from its authorized users. | Engineering services for the Sac and Fox Tribe portion of the BTOP grant were provided by TURTLE ISLAND COMMUNICATION, INC. 2513 94th Avenue North, Brooklyn Park, Minnesota 55444 | In order to facilitate the management of the many sites that require installs and then followed by migration of traffic to the new circuits for the BTOP project, the team decided to develop an application to plan and monitor the progress. This required extracting information from the ICNâ€™s Order Entry system, the Work Order system, Circuit Provisioning system, and Billing system. Currently, Engineering is using spreadsheets to assign and track work. This type of short-term solution is duplicating much of the information within existing systems while taking valuable time from the engineers, thus reducing productivity. The BTOP Information System will provide a universal view into the BTOP project as well as provide the opportunity for the ICN to easily develop dashboard views and specific reports/charts, once those needs are determined. There are several benefits for this new system. It will reduce and in most cases eliminate double entry of pertinent data while reducing the number of errors and the need for synching/normalizing the information. It will also permit ICN to pinpoint issues in the process either with individuals, segments within the process, or equipment so that they can be addressed immediately rather than waiting for the issue to become apparent through missed implementation steps and disparate data flows. Another plus with the system is simplifying the information gathering for the Federal reporting. The dashboard items developed, as well as the global view of projects, can be translated to any or all project(s) the ICN currently has or will have in the future. The primary cost savings will be in employee time saved and the ramifications in not completing the project on time, within the budget. Double entry, compiling data, and the validation of multiple spreadsheets can be eliminated. This will speed determination of status and thus resolution. | Iowa Communications Network | 596 | 61 | 109 | 204 | 203 | 343 |  | 1185 | 117 | 0 | 2818 | N/A Project does not include interconnection agreements. | N/A No new peering and/or transit agreements have been entered in to. | TRUE
NT10BIX5570069 | 2012 | 73,243 | Baseline says 89,358. Variance due to overestimation in baseline. | 4,737 | Baseline says NA. Includes 197 households passed. Variance due to overestimation error in baseline. | 4,737 | Baseline says 7,717. Includes 197 subscribers served. Variance due to overestimation in baseline. | 1Gbps | No variation from baseline. | 1Gbps | No variation from baseline. | 34Mbps | No variation from baseline. | 34Mbps | No variation from baseline. | Customers turned up as part of the BTOP program now have a minimum of 10 Mb each. This represents an average increase of 8.95 Mb per customer added. Based on total CAIs added, that represents an increase of 2.1 Gb of network to the community overall. Sites receiving new connectivity previously had in the 1.5 Mb-3Mb range prior to the BTOP program, now they can get up to 980 Mb per location. Sites receiving new edge routers were previously limited to 45 Mb, with an available segment for broadband of up to 25 Mb. Now, those sites can get slightly more than 980 Mb. Users at aggregation sites were previously limited to 25 Mb or 980 Mb connections and now have the capability of nearly 10 Gb of usable bandwidth. | Ethernet Private Line Service - Symmetrical, 10Mbps $360 per month Ethernet Private Line Service - Symmetrical, 20Mbps: $500 per month Ethernet Private Line Service - Symmetrical, 50Mbps: $750 per month Ethernet Private Line Service - Symmetrical, 100Mbps: $900 per month Ethernet Private Line Service - Symmetrical, 1Gbps: $2,100 per month Premium Internet - Symmetrical, 10Mbps: $920 per month Premium Internet - Symmetrical, 20Mbps: $1,480 per month Premium Internet - Symmetrical, 500Mbps: $3,385 per month Premium Internet - Symmetrical, 100Mbps: $5,661 per month | The project has no non-capacity related bandwidth limitations. During normal operations, traffic is not prioritized. During declared emergencies and public safety events, traffic may be prioritized to public safety organizations as defined by law. The project includes no restrictions on any legal device. | A total of 31 CAIs expected to receive service improvements or new service have been dropped from the project. This represents 9 percent of customers who have so far received new or improved service and 1.2 percent of those capable of receiving new service. Of the 31 who have have churned out, 16 were customer disconnections. Disconnects were based on budgeting issues. There were 12 sites in which the CAI closed or moved out of the service area. Three sites canceled service before it was installed, again, due to budgeting reasons. | 19009 | 17209 | 0 | 0 | 0 | 0 | 1800 | N/A ICN wholesales no dark fiber | 0 | 0 | 0 | 0 | As a state agency, the ICN receives collocation space without charge from its authorized users. | During 2011 and 2012, engineering services for the Sac and Fox Tribe portion of the BTOP grant were provided by TURTLE ISLAND COMMUNICATION, INC. 2513 94th Avenue North, Brooklyn Park, Minnesota 55444 | Recipients should make clear the scope and intent of all equipment changes and ensure they are allowable under the scope of the project and budget. When making changes that include 1) the purchase of 'bigger', more costly version of the equipment originally intended such as a higher capacity router or switch and 2) the purchase of additional equipment to handle the higher broadband demands of customers, be sure to submit AAR an obtain a clear response before proceeding. Even changes that are within budget and scope should be approved before project changes are made. | Iowa Communications Network | 596 | 61 | 109 | 204 | 203 | 343 |  | 1185 | 117 | 0 | 2818 | N/A Project does not include interconnection agreements. | N/A No new peering and/or transit agreements have been entered in to. | TRUE
NT10BIX5570069 | 2013 | 69,538 | Baseline says 89,358. Variance due to over-estimation in baseline. Costs calculated include only the fiber build from the ICN backbone to the Sac & Fox backbone and the fiber build costs from Decorah divided by the mileage from those builds. | 4,564 | Baseline says N/A. Includes 197 households passed. Variance due to over-estimation in the baseline. | 4,564 | Baseline says 7,717. Includes 197 subscribers served. Variance due to over-estimation in the baseline. | 1Gbps | No variation from baseline. | 1Gbps | No variation from baseline. | 78Mbps | Baseline was calculated using only the new IRU customers and did not factor in the increases from existing customers. This figures represents the average speed of all middle mile circuits being provided. | 44Mbps | Baseline was calculated using only the new IRU customers and did not factor in the increases from existing customers. This figures represents the average speed of all last mile circuits being provided. | Customers turn up as part of the BTOP program now now have a minimum of 10 Mb each. This represents an average increase of 8.95 Mb per customer added. Based on total CAIs added, that represents an increase of 2.1 Gb of network to the community overall. Sites receiving new connectivity previously had in the 1.5 Mb-3Mb range prior to the BTOP program, now they can get up to 980 Mb per location. Sites receiving new edge routers were previously limited to 45 Mb, with an available segment for broadband of up to 25 Mb. Now, those sites can get slightly more than 980 Mb. Users at aggregation sites were previously limited to 25 Mb or 980 Mb connections and now have the capability of nearly 10 Gb of usable bandwidth. | Ethernet Private Line Service - Symmetrical, 10Mbps $360 per month Ethernet Private Line Service - Symmetrical, 20Mbps: $500 per month Ethernet Private Line Service - Symmetrical, 50Mbps: $750 per month Ethernet Private Line Service - Symmetrical, 100Mbps: $900 per month Ethernet Private Line Service - Symmetrical, 1Gbps: $2,100 per month Premium Internet - Symmetrical, 10Mbps: $920 per month Premium Internet - Symmetrical, 20Mbps: $1,480 per month Premium Internet - Symmetrical, 500Mbps: $3,385 per month Premium Internet - Symmetrical, 100Mbps: $5,661 per month | The project has no non-capacity related bandwidth limitations. During normal operations, traffic is not prioritized. During declared emergencies and public safety events, traffic may be prioritized to public safety organizations as defined by law. The project includes no restrictions on any legal device. | The original grant included 3,080 CAIs expected to receive new or improved service. The final count was 2,818 CAIs receiving new or improved service. This represents a total change of 262 fewer CAIs or a 8.5% decrease. A total of 103 CAIs dropped service because it was no longer needed. A total of 32 CAIs were dropped because the customer location was closed. A total of 74 CAIs were dropped from the list because they did not meet the definition of CAI. A total of 49 CAI were dropped from the project due to overlap with another BTOP recipient. A total of 10 CAIs were removed due to an inability of the carrier to deliver network connectivity. A total of 3 CAIs were removed because they were duplicative. This represents 262 CAIs removed from the project for various reasons. A total of 9 CAIs were added via approved AARs bringing the grand total to 2,818. | 19009 | 17497 | 0 | 1512 | 0 | 0 | 0 | N/A ICN does not wholesale dark fiber. | 0 | 0 | 0 | 0 | As a state agency, the ICN receives collocation space without charge from its authorized users. | During 2011 and 2012, engineering services for the Sac and Fox Tribe portion of the BTOP grant were provided by TURTLE ISLAND COMMUNICATION, INC. 2513 94th Avenue North, Brooklyn Park, Minnesota 55444 | CAI lists should be carefully managed and trued up with NTIA on a quarterly basis to avoid process complications. AARs for CAI changes should be submitted at least quarterly. Recipients should closely monitor sub-recipients and ensure funds are not released until sub-recipient reporting and other obligations are met. | Iowa Communications Network | 596 | 61 | 109 | 204 | 203 | 343 |  | 1185 | 117 | 0 | 2818 | N/A Project does not include interconnection agreements. | N/A No new peering and/or transit agreements have been entered in to. | TRUE
NT10BIX5570070 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 157662 | 0 | 0 | 0 | 7852 | 615 | 149195 | N/A | 0 | 0 | 0 | 0 | MassBroadband 123 is currently negotiating to lease collocation space in the carrier-neutral hotel and Internet PoP at One Federal Street in Springfield, MA. In the Baseline Plan we projected that by Year 2, Quarter 1 MassBroadband 123 will complete fit out of our space at One Federal Street and will also have completed agreements for siting 22 Point of Interconnection nodes that will house interconnection equipment for third parties and last-mile providers. | N/A | POLE ATTACHMENT LICENSE APPLICATION PROCESSES The Massachusetts Technology Collaborative (â€œMTCâ€) and the Massachusetts Broadband Institute (â€œMBIâ€) have worked collaboratively with Verizon, Western Massachusetts Electric (â€œWMECOâ€), and National Grid (â€œGridâ€) to develop new processes for submitting pole attachment license applications that we believe will help speed up the initial phase of pole attachment licensing and greatly help the MassBroadband 123 fiber build. In Massachusetts, as in most states, an entity wishing to gain access to attach to an existing utility pole must first submit an application to the pole owners along with payment for pre-construction surveys to determine adequacy of the poles to handle the applicantâ€™s proposed attachment. In Massachusetts as most poles are owned jointly by the incumbent telephone and electric companies this requires submitting an application to two pole owners for most applications. In order to prepare the application, the applicant typically conducts a field survey to collect appropriate information on each pole that it wants to license. Upon receiving the application each pole owner also conducts a field survey of the poles included in the application so each owner can assess what make-ready work they believe is required to accommodate a new attachment and who they believe should be responsible for paying for that make-ready work. Sometimes the applicant will attend the pole owner field surveys to represent their own interests. The scheduling of so many field surveys is cumbersome, time consuming, and costly to all parties. The applicant receives a make-ready estimate from each owner only after all the surveys have been conducted and the parties have reconciled their results. Faced with the prospect of licensing 35,000 pole attachments MTC and MBI worked collaboratively with Verizon, WMECO, and Grid to execute Memorandums of Understanding that allow MTC to hire a single third party to collect the detailed data on each pole that all parties will rely upon as the basis of the application phase for determining pole adequacy and developing make-ready work estimates. The data being collected includes GPS locations of each pole, the height and type of all existing attachments measured utilizing photogrammetry, digital photographs and, if required, load screening and analysis. All parties will work off the same data set to discuss and reconcile make-ready requirements so the estimates can be prepared. MAKE-READY WORK In addition, to speed up make-ready work, MTC is currently negotiating with Grid to be able to hire and oversee a make-ready contractor to do all of their make-ready work. Where third party attachers will give MTC permission to do any of their transfers and moves we will attempt to obtain agreements that allow our Design-Builder to do the work just in advance of installing the cable to save time and achieve an economy of scale. | Massachusetts Technology Park | 232 | 143 | 8 | 4 | 56 | 378 |  | 324 | 64 | 24 | 1233 | N/A | N/A | TRUE
NT10BIX5570070 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 7a. We will offer tiered bandwidth service options for our transit agreements; the only bandwidth limitations are the 10 gigabyte hardware. Traffic prioritization is not applicable at this time. 7b. No | N/A | 143095 | 0 | 0 | 15840 | 23500 | 0 | 103755 | N/A | 0 | 0 | 0 | 0 | MassBroadband 123 has executed a lease for a co-location space in the carrier-neutral hotel and Internet Point of Presence at One Federal Street in Springfield, MA. We are currently negotiating agreements for 22 Points of Interconnection nodes that will house interconnection equipment for third parties and last-mile providers | N/A | N/A | Massachusetts Technology Park | 232 | 143 | 8 | 4 | 56 | 378 |  | 324 | 64 | 24 | 1233 | 1. N/A 2. MTC's Network Operator have four interconnection agreements being negotiated at this time: Crocker Communication, Cornerstone Telephone, CenturyLink, and Windstream 3. No requests for interconnection have been denied | 1. N/A 2. We have two transit agreements being negotiated at this time: Crocker Communication and CenturyLink 3. No requests for peering or transit have been denied | TRUE
NT10BIX5570070 | 2012 | 0 | We have 3 "lit" miles on the network, but it was for I91, which was an in-kind contribution to the network and is categorized as "existing upgraded" infrastructure, so it is not to be included as a "new mile" cost | 0 | N/A | 0 | N/A | $2500/month/1 Gbps | For Ethernet services, we offer up to 1 Gigabit Ethernet. For wavelength services, we offer 10 Gigabit wavelength | 0 | N/A | 100 Mbps | N/A | 0 | N/A | N/A | N/A | 7a. None at this time 7b. No | N/A | 83203 | 3 | 0 | 42500 | 17500 | 0 | 23200 | None at this time | 544 | 408 | 408 | 136 | MassBroadband 123 has has leased a co-location space in the Internet Point of Presence at One Federal Street in Springfield, MA and One Summer Street in Boston, MA. We are currently working on installing equipment and connecting 22 Points of Interconnection nodes that will house interconnection equipment in our racks for third parties and last-mile providers | N/A | Make-Ready The Massachusetts Technology Collaborative (â€œMTCâ€) and the Massachusetts Broadband Institute (â€œMBIâ€) work collaboratively, proactively, and aggressively with all utility pole owners and all third parties on the poles including cable providers, municipalities and private entities. Operations staffs from all companies are in regular communication on a weekly and often daily basis. Senior staffs from all companies meet bi-weekly. Company executives meet on an as-needed basis. MBI is also in regular communication with Government Relations staffs of the utility and cable companies. This strategy has built strong support for MassBroadband 123 at all levels of the companies involved in the successful outcome of the project. MBI holds a variety of weekly project management meetings to oversee the make-ready process including weekly meetings that bring together joint pole owners. Typically each owner or third party prefers to manage their own make-ready work and they are uncomfortable meeting with joint owners and licensees. MBI understood from the start that collaborative project management would be required to stay on top of make-ready work on over 30,000 utility poles. MBI collects work progress trackers from each company and loads them into one database so all parties involved in the make-ready work for a single pole can work together to clear roadblocks and can work together on the same MBI identified priorities. MBI will liaise among the various parties to mitigate problems, particularly in a situation where one company is road blocked by another. Whenever possible, MTC has executed agreements with municipalities, cable providers and other third parties to enable our builder to perform make-ready construction. If the pole owner knows that MTCâ€™s contractor is going to perform third party make-ready, they will release licenses before all the work is complete and allow MTC to perform the third party make-ready work in conjunction with installation of our cable. This requires very close communication among all parties, but saves time and also gives the contractor more flexibility in prioritizing where they work. Construction Regardless of how quickly licenses are issued, on a project of this size there are many issues that arise that can cause delays. MTC has worked closely with our builder to find ways to mitigate delays and compress the schedule where possible. Some of the practices that have helped MassBroadband 123 to make up time in the schedule include: â€¢ Beginning negotiations with utilities and railroads prior to final design completion â€¢ Installing messenger strand ahead of fiber when there are not enough contiguous miles of licenses to install fiber. MTC fiber is typically stored on 20,000 foot reels and can not be cut arbitrarily. Strand is stored on smaller reels and can be cut as needed. This helped keeps crews working during lulls in licensing so they could stay on the project and not have to demobilize and then remobilize again at a later time. â€¢ Partnering with a prime contractor with relationships and access to multiple vendors to assist with crew allocation â€¢ Whenever possible, rodding and roping underground segments early in the project to avoid "work-arounds" required late in the project â€¢ Utilizing directional boring instead of grass trenching can speed up environmental permitting and reduce restoration work â€¢ Starting community anchor institution (â€œCAIâ€) and point of interconnection (â€œPOIâ€) installation work prior to backbone fiber installation, so POIs and CAIs are ready to be connected by the time the fiber reaches them | Massachusetts Technology Park | 232 | 143 | 8 | 4 | 56 | 378 |  | 324 | 64 | 24 | 1233 | 1. 8. Axia Networks, USA; Massachusetts Information Technology Division (ITD), Crocker Communications, FTG Technologies, Center for Education Leadership (CELT), Access Plus, Community WISP, Inc., Streamline Networks 2. 20 3. No requests for Interconnection have been denied | 1. None at this time 2. None at this time 3. No requests for Interconnection have been denied | TRUE
NT10BIX5570070 | 2013 | $50,186.52 / mile | Based on the 950 route miles (of 954 expected final miles) completed as of Dec 31, 2013 and currently forecasted total cost of $47,677,193.78 | 0 | N/A | 0 | N/A | 1 Gbps | For Ethernet services, we offer up to 1 Gigabit Ethernet. For wavelength services, we offer 10 Gigabit wavelength | 0 | N/A | 125 Mbps | Provisioned speeds (excluding wavelength services) range from 5 Mbps to 1Gbps. The average speed is based on 31 active Ethernet and Broadband services. | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions (CAIs) is approximately 73 Mbps. This figure is based upon each CAI using the lowest value from the Planned Speed Tier range and assumes that CAIs classified as "New" are considered to have a broadband speed of 0 Mbps and CAIs classified as "Improved" are considered to currently have broadband service at one speed tier one lower than their Planned Speed Tier. Speed Tiers for this purpose are 1-19 Mbps, 20-49 Mbps, 50-99 Mbps, 100 - 999 Mbps, and 1Gbps+. | MassTech only provides wholesale service via the MassBroadband123 network and therefore has no retail service descriptions or pricing plans. | 7a. None at this time 7b. No | N/A | 143095 | 17422 | 8 | 125641 | 4 | 0 | 20 | None at this time | 5784 | 5784 | 0 | 0 | MassBroadband 123 has leased co-location space in 23 locations as noted in the Colocation Capacity Addendum. We have finalized the installation of equipment and connections to all Points of Interconnection nodes that will house interconnection equipment in our racks for third parties and last-mile providers. While MBI does make space available within our racks for qualified service providers to install equipment for interconnection purposes, the number of rack units available for colocation varies by site. The square footage listed above is the amount of space occupied by MassBroadband 123 and no floor space is available at any site for 3rd party use. | N/A | Make-Ready The Massachusetts Technology Collaborative (â€œMTCâ€) and the Massachusetts Broadband Institute (â€œMBIâ€) worked collaboratively, proactively, and aggressively with all utility pole owners and all third parties on the poles including cable providers, municipalities and private entities. Operations staffs from all companies were in regular communication on a weekly and often daily basis. Senior staffs from all companies met bi-weekly and company executives met on an as-needed basis. MBI was in regular communication with Government Relations staffs of the utility and cable companies. This strategy built strong support for MassBroadband 123 at all levels of the companies involved in the successful outcome of the project. MBI held a variety of weekly project management meetings to oversee the make-ready process including weekly meetings that brought together joint pole owners. Typically each owner or third party preferred to manage their own make-ready work and they were uncomfortable meeting with joint owners and licensees. MBI understood from the start that collaborative project management would be required to stay on top of make-ready work on over 30,000 utility poles. MBI collected work progress trackers from each company and loaded them into one database so all parties involved in the make-ready work for a single pole could work together to clear roadblocks and work together on the same MBI identified priorities. MBI liaised among the various parties to mitigate problems, particularly in a situation where one company was road blocked by another. Whenever possible, MTC executed agreements with municipalities, cable providers and other third parties to enable our builder to perform make-ready construction. If the pole owner knew that MTCâ€™s contractor was going to perform third party make-ready, they would release licenses before all the work was complete and allow MTC to perform the third party make-ready work in conjunction with installation of our cable. This required very close communication among all parties, but saved time and gave the contractor more flexibility in prioritizing where they work. Construction Regardless of how quickly licenses are issued, on a project of this size there are many issues that arise that can cause delays. MTC worked closely with our builder to find ways to mitigate delays and compress the schedule where possible. Some of the practices that have helped MassBroadband 123 to make up time in the schedule include: â€¢ Beginning negotiations with utilities and railroads prior to final design completion â€¢ Installing messenger strand ahead of fiber when there are not enough contiguous miles of licenses to install fiber. MTC fiber is typically stored on 20,000 foot reels and can not be cut arbitrarily. Strand is stored on smaller reels and can be cut as needed. This helped keeps crews working during lulls in licensing so they could stay on the project and not have to demobilize and then remobilize again at a later time. â€¢ Partnering with a prime contractor with relationships and access to multiple vendors to assist with crew allocation â€¢ Whenever possible, rodding and roping underground segments early in the project to avoid "work-arounds" required late in the project â€¢ Utilizing directional boring instead of grass trenching can speed up environmental permitting and reduce restoration work â€¢ Starting community anchor institution (â€œCAIâ€) and point of interconnection (â€œPOIâ€) installation work prior to backbone fiber installation, so POIs and CAIs are ready to be connected by the time the fiber reaches them | Massachusetts Technology Park | 232 | 143 | 8 | 4 | 56 | 378 |  | 324 | 64 | 24 | 1233 | 1. 7 2. 1 3. No requests for Interconnection have been denied | 1. None at this time 2. None at this time 3. No requests for Interconnection have been denied | TRUE
NT10BIX5570071 | 2010 | 67,055.90 | N/A | 0 | N/A | 0 | N/A | 10Gbps | N/A | 0 | N/A | 1Gbps | N/A | 0 | N/A | On average institution customers will see at least a 20x increase in available bandwidth. In a small sample of institutions visited, the current common broadband speeds ranged from T1 (1.544Mbps) to 10Mbps Cable Modem. The majority of institutions will have an access port with at least 100Mbps rate, most Academic Type locations will have a 1Gbps available bandwidth. Given our sample data's average bandwidth of about 5Mbps, we can expect on average a 20x increase to the 100Mbps service. | The Zayo Bandwidth Middle Mile Proposal leverages dark fiber, DWDM (Dense Wave Division Multiplexing), and SONET (Synchronous Optical Network) technologies to provide Point to Point Private Line, Ethernet, Wavelength, Dark Fiber and Dedicated Internet services to last mile providers and end users. High count single mode fiber is being deployed in rings and linear spurs off of Zayo Bandwidthâ€™s existing network infrastructure to maximize the reach of the proposal. DWDM and SONET technologies are being deployed over the fiber to enable 1.5M to 10G services from the newly reached communities to the Zayo network infrastructure and the internet. The proposal provides interconnect points for connectivity to last mile providers or end users in the various markets via strategically placed points along the fiber path. From each interconnection point, Zayo will be capable of delivering Ethernet, Private Line, Wavelength, Dark Fiber and Dedicated Internet Access services from 1.5Mbps to 10Gbps via industry standard interfaces. A last mile provider or end user can connect to Zayo Bandwidth at any interconnection point via 2 fiber or 4 fiber optical interfaces. A 2 fiber interface is provided for Ethernet, Wavelength, and Unprotected SONET services while a 4 Fiber interface is used to provide Protected SONET services. The interconnection will leverage industry standard SONET interfaces at OC3, OC12, OC48, or OC192 SONET rates for the various service types, or can leverage standard Gigabit or 10Gigabit Ethernet interfaces for Ethernet private line, Wavelength, and Dedicated Internet Access services. A last mile provider or end user can also request that Zayo Bandwidth extend from a standard interconnection point to their facility. In this case Zayo Bandwidth would construct new fiber from an interconnection point to the customers designated premise and deploy equipment at the premise as appropriate for the requested service type. This extension is provided on an Individual Case Basis (ICB) and is dependent on the distance and complexity of the build. | Zayo will provide a customer with the bandwidth subscribed to, e.g. DS3 (45meg), Fast Ethernet (100meg or fractions thereof), etc. Zayo does not limit a customerâ€™s bandwidth up to the subscribed level, but will â€œchokeâ€ the bandwidth once the level is met. Traffic prioritization is not needed, since Zayo is not providing an â€œMPLSâ€ type service. Customers may, at their discretion, elect to run VLANs, traffic shaping or prioritization within the confines of their subscribed to bandwidth. Zayoâ€™s standard Master Service Agreement carries language forbidding customers from using the service for any unlawful act. We do not block customer traffic from any site deemed legal and lawful, but clearly will comply with government sanctions against sites found to be harmful or illegal. Customer may attach any legal device to our service, and we have not prevented customers from doing this at any time. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Currently have IRU Agreement in place with Anoka County to provide 8 Dark Fibers upon completion of Fiber Construction @ a Rate $ $1.00 per month for 30 years. | 0 | 0 | 0 | 0 | All 145 Anchor Institutions are providing Zayo with Rack Space or Location for Zayo to place necessary Racks. Any new customers in the future it would be necessary to do the same. | 0. Zayo has only awarded one subcontract so far on this grant. That subcontract is for Environmental Assessment and Route Development. Zayo has an internal target of 12% to 15% SBD for this project and is working hard to meet this target. | N/A | Zayo Bandwidth, LLC | 4 | 12 | 3 | 1 | 2 | 56 |  | 0 | 67 | 0 | 145 | N/A, Per our baseline, this will not take place until Q2 of year 2. | N/A | TRUE
NT10BIX5570071 | 2011 | 0 | Zayo has not started building yet, because we are still doing engineering and permitting. | 0 | N/A | 0 | N/A | 10Gbps | This is in line with our baseline. | 0 | N/A | 1Gbps | This is in line with our baseline. | 0 | N/A | 10Gbps based on unserved areas. | N/A | Zayo's standard. Zayo had never limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to our network. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zayo is in the process of identifying our spaces and hut requirements. | Fiber Engineering and Design is a Small woman owned business doing the engineering work for this project. Mitchell Industries is a Small business providing us strand for this project. | Zayo's biggest challenge has been dealing with pole providers and permitting agencies. We have had to tell them that we are willing to bypass them and go underground if we cannot reach agreement and agree to pricing. When we explain our deadline and our willingness to seek other solutions, we have found the pole providers and permitting agencies much easier to work with. | Zayo Bandwidth, LLC | 4 | 12 | 3 | 1 | 2 | 56 |  | 0 | 67 | 0 | 145 | 0 Currently. 0 Negotiating. Zayo has not denied any request. We have not started building yet. | 0 Currently. 0 Negotiating. Zayo has not denied any request. We have not started building yet. | TRUE
NT10BIX5570072 | 2010 | 0 | The EA SAC has not yet been satisfied and that a FONSI has not yet been granted, so network construction has not yet commenced | 0 | The EA SAC has not yet been satisfied and that a FONSI has not yet been granted, so network construction has not yet commenced | 0 | The EA SAC has not yet been satisfied and that a FONSI has not yet been granted, so network construction has not yet commenced | 0 | The EA SAC has not yet been satisfied and that a FONSI has not yet been granted, so network construction has not yet commenced | 0 | The EA SAC has not yet been satisfied and that a FONSI has not yet been granted, so network construction has not yet commenced | 0 | The EA SAC has not yet been satisfied and that a FONSI has not yet been granted, so network construction has not yet commenced | 0 | The EA SAC has not yet been satisfied and that a FONSI has not yet been granted, so network construction has not yet commenced | Construction has not commenced as the Environmental Assessment Special Award Condition has not been satisfied and a FONSI has not been granted, so this indicator is not applicable at this time | Construction has not commenced as the Environmental Assessment Special Award Condition has not been satisfied and a FONSI has not been granted, so this indicator is not applicable at this time | 7a.. Com Net has network management polices in place for our project to address rate limiting, traffic prioritization and other policies related to the openess of our network. Com Net's network openess policy is available to the general public at www.gigepac.com. 7b. To our knowledge, Com Net has never intentionally blocked consumers from accessing any lawful content, service, service provider or application or prevented any consumer from attaching any legal device to the network. | Construction has not commenced as the Environmental Assessment Special Award Condition has not been satisfied and a FONSI has not been granted, so this indicator is not applicable at this time | 0 | 0 | 0 | 0 | 11798 | 13012 | 39467 | Construction has not commenced as the Environmental Assessment Special Award Condition has not been satisfied and a FONSI has not been granted, so this indicator is not applicable at this time | 0 | 0 | 0 | 0 | Construction has not commenced as the Environmental Assessment Special Award Condition has not been satisfied and a FONSI has not been granted, so this indicator is not applicable at this time | To date Com Net has not made any subcontracts or sub grants to socially and economically disadvantaged small business (SDB) concerns. | Com Net has noted the following best practices and lessons learned: 1) Upon notification of receipt of award, although you have thirty-days (30) to accept, Com Net strongly recommends making your preliminary decision within ten (10) days or less. If your preliminary decision is to proceed but you are waiting on clarification of requirements, Com Net would recommend that you conduct a compliance review of your procurement policy(s) and that you initiate your request for proposal for Environmental Assessment Consultant services unless you do not have such resources available in-house. Com Net still recommends that you wait until you receive clarification on key award requirements prior to final acceptance, it is just important to start your Environmental Assessment work as soon as possible if it is highly probable you will accept the award. 2) In conducting your Environmental Assessments, Com Net recommends you break your overall route into multiple segments for release of work. As work is completed on each segment, it should be reviewed with your Federal Program Officer for route modifications of significance from your application. This approach allows you to prioritize your build-out by segment based on interest and timing requirements for Environmental Assessment, permitting, special construction considerations and of interested Community Anchor Institutions when it comes time to implementation. 3) Do not under estimate the time and expense required for project administration during the six month Special Award Condition especially if you are a first-time grant recipient who may be relying on outside consultants as subject matter experts. There are multiple items that will need to be addressed in parallel following award acceptance, therefore, ensuring training and involvement by qualified individuals is critical to success. Com Net learned that the following items had to be addressed in parallel: Award Requirements Review for Acceptance, establishment of a compliance management program, review of procurement-employment and other policies for compliance, Environmental Assessment for qualified consultant services, establishment of sub-recipient management program, action items for satisfaction of special award conditions, accounting database-system set-up, financing, corporate governance resolutions-directives, reporting administration, community out-reach meetings, route reviews, agency consultations, environmental assessment field work, on-going communications with contacts from community out-reach efforts, attending BTOP orientation meeting and webinars, sub-recipient contract negotiations, other project partner contract negotiations, sub-recipient communications, partner communications, site acquisition efforts, Environmental Assessment draft report review for submission and other project management activities. | COM Net, Inc. | 705 | 165 | 12 | 16 | 279 | 322 |  | 488 | 504 | 377 | 2868 | (1) N/A (2) Com Net is working to finalize four (4) agreement for Points-of-Interconnect; two (2) with sub-recipients ZAYO and OARnet, and two (2) with One Community and Horizon Technologies as Ohio Middle Mile Consortium partners. Com Net is working on a total of ten (10) unique agreements for mid-span meet points of interconnect for meet point billed services with its Broadband Service Provider Partners. (3) Com Net has not denied any request for interconnect. | (1) NA (2) Com Net is not aware of any conditions in any agreements at this time that differentiate them as peering and transit agreements rather than as Points of Interconnect Agreements. (3) Com Net has not denied any request for interconnection | TRUE
NT10BIX5570072 | 2011 | $25,534.41 | A favorable variance versus budget of just under $7000 per mile due to the total miles completed being fewer than originally projected with a favorable mix of miles constructed using the direct plow versus boring method of construction. The new fiber route segments that were accepted as fully complete as of the end of 2011 involved highly rural portions of the build-out with minimal obstructions. The routes build therefore did not require the use of the more costly boring operation. | N/A | N/A | N/A | N/A | 10 Gbps | Baseline indicated 10 Gbps in Year 2 of the project. No Variance. | N/A | N/A | 249 Mbps | Com Net's baseline included a projection of 100 Mbps. Com Net's average is driven above the 100 Mbps average based on high bandwidth users by a few hospitals in the healthcare industry, OARnet's lit service usage and the diverse connectivity to Com Net Points-of-Presence through diverse backhaul routes to the Northwest Ohio Area Computer Service Cooperatives data center. | N/A | N/A | The average increase in broadband speed was by a factor of ~5.5. This is based on the actual increase in committed data rate on port connections for point-to-point and private virtual local area network services. All service provided to date are private network services of the subscribing Community Anchor Institution; therefore, actual bandwidth usage is not a monitored characteristic. In calculating this number, Com Net summed the data rate of all subscribing entities prior to implementation of the new or improved service and then post implementation. Com Net then divided the post implementation aggregate committed data rate by the pre-implementation committed data rate to establish broadband speed increase factor. | Com Net is offering three basic types of service at the present time. Ethernet Linear (ELINE) transport service for point-to-point connection, Ethernet Local Area Network (ELAN) transport service for point-to-multipoint through port connection to a customer private virtual Local (Metro) Area Network and a dual homed satellite facility to two hub locations (Primary and Disaster Recovery Site) as Ethernet Virtual Private Line (EVPL) circuits through multiservice user network interface ports. | At the present time Com Net maintains an open network policy as published on its web site at www.cniteam.com. Com Net does not practice any bandwidth limitation outside of port limiting that is based on customer's ordered capacity. Com Net does not currently prioritize traffic in any form. Com Net has never limited or blocked consumers from accessing lawful content, service, service provider, application or prevented any consumer from attaching any legal device to the network. | Com Net has not experienced any dropped subscriber for the GigEPAC to date. Com Net has lost prospective community anchor institutions to competitive broadband providers that were included in its initial projections. | 64277 | 28 | 14 | 4931 | 11770 | 13004 | 34530 | Ottoville Mutual Telephone Company, 8.5 route miles, 1 Fiber or 8.5 Fiber Miles for the purpose of providing service to Grover Hill Elementary as a K-12 Community Anchor Institution Benton Ridge Telephone Company, 5.85 Route Miles, 1 Fiber, 5.85 Fiber Miles for the purpose of serving Findlay High School as a K-12 Community Anchor Institution | 692 | 527 | 36 | 129 | None of the facilities specified above are owned. The square footage reported is based on (i) two sites where in-kind equipment along with DWDM network upgraded equipment is collocated in network centers/transmission sites of an interexchange carrier; (ii) in one site where in-kind equipment is located in carrier neutral space of the data center operator; (iii) in one site where in-kind equipment, along with DWDM network upgrade equipment, is located in carrier neutral space of the data center operator; (iv) in one site where in-kind equipment located in a legacy leased suite of Com Net; (v) in one site where in-kind equipment is located in rack space inside of Com Net's wholly owned subsidiary Independents Fiber Network; and (vi) in one site where upgraded DWDM equipment of Com Net occupies space at an incumbent Local Exchange Carrier Central Office. Other network providers can also connect to Com Net's federally funded backhaul network through mid span point-of-meet arrangements at one or more of the multiple non-environmentally controlled outdoor enclosures housing splice points located along the new construction routes. | Continental Resources - Women Owned | Com Net recommends involving the County Engineer's office early on in your Community Outreach efforts with County Commissioners and economic development agencies. It is important that the County Engineer's office understands that the BTOP award is a fixed budget award and that forced changes in the method of construction by the authority having jurisdiction can limit the fiber optic system's reach in that county as well as downstream counties in the system. | COM Net, Inc. | 705 | 165 | 12 | 16 | 279 | 322 |  | 488 | 504 | 377 | 2868 | Com Net has entered into eleven (11) agreements that it classifies as an interconnection, peering and/or transit arrangement. As of year-end 2011, Com Net had established mid-span point-of-meet, meet-point billed points of interconnection with Middle Point Home Telephone Company, Arthur Mutual Telephone Company, Northwest Net and its wholly owned subsidiary Independents Fiber Network. Com Net is currently in the process of negotiating 21 similar such agreements. Com Net had established mid-span point-of-meet interconnections with the Ottoville Mutual Telephone Company and Benton Ridge Telephone Company allowing them to secure an Indefeasible Right to Use (IRU) Dark Fiber (DF) for serving community anchor institutions through their local service point-of-presence. Com Net is currently in the process of negotiating agreements with 5 additional such agreements. The five entities are not unique from the 21 mentioned above. Com Net had established intrabuilding mid-span point-of-meet interconnections with Community Internet Service Provider (CISP) in its data center located at 3035 Moffat Street; Toledo, OH; and with OneCommunity and OARnet at DatacenterBZ located at 535 Scherers Court; Columbus, OH. Com Net is currently in the process of negotiating 2 additional such agreements that are unique from the 21 mentioned above. Com Net had established interbuilding mid span point-of-meet interconnections with Northwest Ohio Area Computer Services Cooperative (NOACSC) and Ohio Academic Resources Network (OARnet) through a splice case located outside of 1680 North Sugar Street; Lima, OH. Com Net has not started negotiations with another party on a similar agreement at the present time. Com Net had established an agreement with T2 Communications, a wholly owned subsidiary of Com Net, allowing each party to purchase facilities and services from the other. The original basis of the agreement was for T2 Communications, as a sub-recipient to sub-lease conduit space it could secure through a legacy Interconnect Agreement to Com Net. Com Net had established an agreement with Sycamore Telephone Company to Interconnect for the sale of transport service for connectivity to Com Net IP data and IP video services. This agreement was contingent on the completion of a joint build by Sycamore as the construction management company, the completion of certain route segments by Com Net between Lima, Ohio and a planned point-of-meet with the Sycamore Telephone Company north of Upper Sandusky, Ohio. Com Net has not denied any request for service and/or use of the facilities. Com Net has only expressed a potential for limited capabilities to deliver an Indefeasible Right to Use (IRU) dark fiber based on plans to serve Community Anchor Institutions (CAIs) in certain areas of the network. | None based on Com Net's interpetation. Com Net's legacy core IP routers that host BGP announcements/peers with Tier 1 carriers, Tier 2 Carriers, other regional IP network operators and with other autonomous system numbers of other providers were not made part of the GigEPAC project as inkind nor were they purchased with federal funds. The only network equipment made part of the project was MPLS Network Equipment strictly utilized in providing Layer 2 and Layer 3 Ethernet Transport Services. | TRUE
NT10BIX5570072 | 2012 | 28,525 | This price includes all outside plant construction firm charges, fiber-optic plant materials, private easement costs, authority having jurisdiction (AHJ) permit application costs, conduit costs, pole attachment application costs, pole make ready costs, Railroad (RR) crossing occupancy costs, RR liability insurance cost and RR flagman costs. | NA | NA | NA | NA | 10 Gbps | Baseline indicated 10 Gbps in Year 2 of the project. No Variance | NA | NA | 139 | CNI's most common service being sold is point-to-point Ethernet service, so this number is based on the average committed data rate being ordered. In 2011 CNI saw limited customer's subscribing for service but with several requesting connection speeds in excess of 100 Mbps. In 2012 CNI has seen more moderate capacity requirements from Community Anchor Institutions and wholesale customers. | NA | NA | The average increase in broadband speed was by a factor of ~4.0. This is based on the actual increase in committed data rate on port connections for point-to-point and private virtual local area network services. All service provided to date are private network services of the subscribing Community Anchor Institution; therefore, actual bandwidth usage is not a monitored characteristic. In calculating this number, Com Net summed the data rate of all subscribing entities prior to implementation of the new or improved service and then post implementation. Com Net then divided the post implementation aggregate committed data rate by the pre-implementation committed data rate to establish broadband speed increase factor. | CNIâ€™s offering of Ethernet Transport Services is focused on ELINE; ELAN, ETREE and dual-homed satellite to primary and disaster recovery hub site connectivity. CNI offers wholesale last mile connectivity with Internet Access Port and Bandwidth for the service providersâ€™ resale use. CNI, also, offers managed fiber-tail service, which is the management of a fiber-tail to a customer location or a mid-span meet-point interconnect or customer provided access facility through CNI's network operation center to deliver jointly provided lit services. The availability of GigE PLUS fiber facilities managed and operated by CNI is limited on two major segments at the present time. This is on the segment from Toledo-to-Lima and Lima-to-Dayton where CNI manages 48 of the 96 fiber and ZAYO Group manages the remaining 48 fiber. In the 48 fiber CNI is managing over these major metro segments, it has committed a majority of the fiber for serving Community Anchor Institutions, establishing Ethernet Network-to-Network mid-span meet-point interconnects and reserved additional fiber for quotes to wireless carrier sites that are in various states of award. On these two major segments, the use of the remaining dark fiber is reserved for satisfying the primary purpose of the grant, which is to serve Community Anchor Institutions and to bring broadband to unserved and underserved rural areas. The monthly lease of fiber facilities has not been offered to date. | At the present time Com Net maintains an open network policy as published on its web site at www.cniteam.com. Com Net does not practice any bandwidth limitation outside of port limiting that is based on customer's ordered capacity. Com Net does not currently prioritize traffic in any form. Com Net has never limited or blocked consumers from accessing lawful content, service, service provider, application or prevented any consumer from attaching any legal device to the network. | CNI has not experienced any dropped subscriber to date for the GigE Plus project. CNI is not tracking and reporting on dropped subscibers of its Broadband Service Partners. CNI has lost the opportunity to serve prospective community anchor institutions that were included in its initial projections to competitive broadband providers on price and service availability at the time of customer commitment. | 64396 | 761 | 287 | 29732 | 9026 | 3406 | 21184 | Ottoville Mutual Telephone Company, 8.5 route miles, 1 Fiber or 8.5 Fiber Miles for the purpose of providing service to a K-12 educational institution Benton Ridge Telephone Company, 5.85 Route Miles, 1 Fiber, 5.85 Fiber Miles for the purpose of serving a K-12 Community Anchor Institution, 1 Fiber for serving the a K-12 school district, 1 Fiber for serving a K-12 school district, 1 Fiber for serving a K-12 school district Wabash Mutual Telephone Company 2 Fiber for Serving a K-12 school district SAA bright.net 2 fiber for serving a K-12 school district Telephone Service Company 1 Fiber for serving the a K-12 school district and one fiber for delivering IP service to a K-12 school district. McClure Telephone Company 2 Fiber for customer access to Com Net Findlay Point-of-Presence for protected network connectivity as part of Network Interface connection Bascom Mutual Telephone Company 2 Fiber for establishing mid-span meet-point interconnect with the Sycamore Telephone Company. Sycamore Telephone Company 2 Fiber for establishing mid-span meet-point interconnect with the Bascom Mutual Telephone Company Northwest Net 2 Fiber for providing service to a K-12 school district. Northwest Net 1 Fiber for providing service to a commercial entity 2 fiber Toledo to Dayton route to be used by ZAYO for leasing to an undisclosed customer | 708 | 420 | 36 | 252 | The square footage reported is comprised of (i) one sites where in-kind equipment along with DWDM network upgraded equipment is placed in leased collocation space of an ISP; (ii) addition of a rack in 2012 at one site to house the Cyan chassis where in-kind equipment is located in carrier neutral space of the data center operator as reported in 2011; (iii) addition of a rack in 2012 at one site where in-kind MPLS Network equipment had to be separated from DWDM network upgrade equipment for cooling purpose, which is located in carrier neutral space of the data center operator as reported in 2011; (iv) three newly constructed 12x10 concrete hut enclosures in 2012; (v) in one site where upgraded DWDM equipment of CNI was installed in occupied space at an ISP's Point-of-Presence as part of a mid-span meet-point interconnect agreement whereby CNI will lease facilities as service are sold; (vi) in one site where upgraded DWDM equipment of CNI was installed in occupied space at an Cable TV provider's central network distribution office as part of a mid-span meet-point interconnect agreement whereby CNI will lease facilities as service are sold; and (vi)i in 24 sites where upgraded DWDM equipment of CNI was installed in occupied space at an incumbent Local Exchange Carrier Central Office as part of a mid-span meet-point interconnect agreement whereby CNI will lease facilities as services are sold. Other network providers can also connect to Com Net's federally funded backhaul network through mid span meet-point interconnect arrangements at one or more of the multiple non-environmentally controlled outdoor enclosures housing splice points located along the new construction routes. | Continental Resources - Women Owned | Although aerial plant may be lucrative from a construction cost standpoint, do not underestimate the application fees and make ready costs in aerial construction as well as time line impacts and on-going repair costs. A thorough inspection of pole facilities should be completed prior to making a final determination to go aerial versus underground from a cost and timing perspective. At the same time, when making the decision to go underground, one should pursue all resource information available on subsurface soil and rock conditions. The presence of quarries in or around the planned route is a good indication you may encounter obstructions during construction. It is also important to engage with the authorities having jurisdiction to establish a working relationship, especially if the authorities have encountered problems with workmanship associated with the placement of communication facilities in the past. You may encounter resistance to certain methods of construction that can only be overcome through relationship building and/or negotiation of special agreements to repair any disturbed underground facilities. | COM Net, Inc. | 705 | 165 | 12 | 16 | 279 | 322 |  | 488 | 504 | 377 | 2868 | In Com Net Incorporated's (CNI's) 2011 annual performance progress report it was noted that eleven (11) agreements classified as an interconnection, peering and/or transit arrangement were established. It was later determined that four (4) of these should not have been reported in OARnet and OneCommunity as sub-recipients, as well as Tier 2 Communications and Independents Fiber Network as wholly owned subsidiaries of CNI making the adjusted total agreements seven (7) for 2011. As of year-end 2012 CNI had established 34 agreements classified as interconnection, peering and/or transit arrangements. CNI had established mid-span meet-point (MSMP), meet-point billed points of interconnection as services are sold with Telephone Service Company; Bascom Mutual Telephone Company; Wabash Mutual Telephone Company; Sherwood Mutual Telephone Association; Vaughnsville Telephone Company; Farmers Mutual Telephone Company; Kalida Telephone Company; Glandorf Telephone Company; Defiance Holdings property Qualstar; SAA bright.net; New Knoxville Telephone Company; Buckland Telephone Company; Waldron Telephone Company; Ayersville Telephone Company; Fort Jennings Telephone Company; Ridgeville Telephone Company; Ogden Telephone Company; Sand Creek Telephone Company; McClure Telephone Company and Champaign Telephone Company. Com Net was in the process of negotiating one such additional agreement. CNI had established or upgraded Mid-Span Meet Point Network-to-Network Interconnection (NNI) agreement with carriers with the purchase and/or sale of transport services with Columbus Grove, a Fairpoint Communications property; AVETEC; Buckeye Telesystem and MediaCom as well as Bowling Green Municipal Utilities. Com Net was in the process of negotiating one such additional agreement. CNI had established intrabuilding mid-span point-of-meet interconnections with Level3 at its network center located at 1946 N. 13th Street, Toledo, OH; US Signal at 121 N. Erie Street through an intrabuilding cross connect at 1946 N. 13th Street, Toledo, OH to US Signal fiber facilities; XO Communications at 535/545 Scherers Court, Columbus, OH; and INDATEL Service at 305 E. Cermak Street, Chicago, IL through leased DWDM service from 535 Scherers Court to the INDATEL Services collocation cage. CNI had entered into agreement to provide new or improved transient transport for connectivity to CNI's regional transient IP network to WATCH Communications; Bascom Communications; Wabash Communications; and Securus Technologies. CNI sub-recipient ZAYO had reported it had entered into an agreement with one undisclosed customer to provide two dark fiber under an IRU. Com Net has not denied any request for service and/or use of the facilities. Com Net has only expressed a potential for limited capabilities to deliver an Indefeasible Right to Use (IRU) dark fiber as a fiber tail service under a managed service agreement based on jointly provided service plans to a Community Anchor Institutions (CAIs) in certain areas of the network. | CNI did not enter into any peering or transit agreement as part of the federally funded project. Com Net's legacy core IP routers that host BGP announcements/peers with Tier 1 carriers, Tier 2 Carriers, Content Delivery Networks, IP Exchanges, Ethernet Exchanges, other regional IP network operators and with other autonomous system numbers of other providers were not made part of the GigEPAC project as in-kind nor were they purchased with federal funds. The only network equipment made part of the project was MPLS Network Equipment strictly utilized in providing Layer 2 and Layer 3 Ethernet Transport Services. | TRUE
NT10BIX5570072 | 2013 | $43,416 | This price includes all outside plant construction firm charges, fiber-optic plant materials, private easement costs, authority having jurisdiction (AHJ) permit application costs, route surveying, conduit costs, pole attachment application costs, pole make ready costs, Railroad (RR) crossing occupancy costs, RR liability insurance cost and RR flagman costs, EA consultant fees for route changes and route inspection, as well as, allocation of for right-of-way, permits, construction progress reporting and construction contract management support. The original baseline new route mile construction cost was developed on a non-cumulative project year basis with 10% construction completed project year 1, 45% project year 2 and 45% project year 3 which works out to $43,467 composite. CNI firmly believes its composite cost would have been on or over the cumulative average cost per mile per new mile if construction to downtown Dayton would have been completed prior to the end of the project award. | NA | NA | NA | NA | 100Gbps | Baseline indicated 40Gbps in Year 3 of the project. CNI is promoting concatenated 10Gbps ports until such time it is economical to upgrade to a 100 Gbps port. CNI successfully completed a 100Gbps field test on its network with Cyan and JDSU to demonstrate the capability. | NA | NA | 298 Mbps | CNI's most common service being sold is point-to-point Ethernet service on a wholesale basis. This number is based on the average committed data rate being ordered. In 2011, CNI saw limited customer's subscribing for service but with several requesting connection speeds in excess of 100Mbps. In 2012, CNI saw more moderate capacity requirements from Community Anchor Institutions and wholesale customers. In 2013, CNI deployed CISCO 9K MPLS network equipment across its core network, running Sylvania-Lima-Worthington-Sylvania operating at 10Gbps for wholesaling Dedicated Internet Access to its Broadband Service Providers serving residential and business end users throughout west-central Ohio. At the end of 2013, CNI's network planning team was finalizing implementation documentation to upgrade this core to 2x10Gbps for an aggregate capacity of 20Gbps In 2013, CNI extended its 10Gbps service to Chicago via Lima and Worthington, which has led to several sales of 1Gbps point-to-point circuits. | NA | NA | The average increase in broadband speed was by a factor of ~4.0. This is based on the actual increase in committed data rate on port connections for point-to-point and private virtual local area network services. All services provided to date are private network services of the subscribing Community Anchor Institution; therefore, actual bandwidth usage is not a monitored characteristic. In calculating this number, Com Net summed the data rate of all subscribing entities prior to implementation of the new or improved service and then post implementation. Com Net then divided the post implementation aggregate committed data rate by the pre-implementation committed data rate to establish broadband speed increase factor. | CNIâ€™s offering of Ethernet Transport Services is focused on ELINE; ELAN, ETREE and dual-homed satellite to primary and disaster recovery hub site connectivity. CNI offers wholesale last mile connectivity with Internet Access Port and Bandwidth for the service providersâ€™ resale use. CNI, also, offers managed fiber-tail service, which is the management of a fiber-tail to a customer location or a mid-span meet-point interconnect or customer-provided access facility through CNI's network operation center to deliver jointly provided lit services. The availability of GigE PLUS fiber facilities managed and operated by CNI is limited on two major segments at the present time. This is on the segment from Toledo-to-Lima and Lima-to-Dayton where CNI manages 48 of the 96 fiber and ZAYO Group manages the remaining 48 fiber. In the 48 fiber CNI is managing over these major metro segments, it has committed a majority of the fiber for serving Community Anchor Institutions, establishing Ethernet Network-to-Network mid-span meet-point interconnects and reserving additional fiber for quotes to wireless carrier sites that are in various states of award. On these two major segments, the use of the remaining dark fiber is reserved for satisfying the primary purpose of the grant, which is to serve Community Anchor Institutions and to bring broadband to unserved and underserved rural areas. The monthly lease of fiber facilities has not been offered to date. | At the present time, Com Net maintains an open network policy as published on its web site at www.cniteam.com. Com Net does not practice any bandwidth limitation outside of port limiting that is based on customer's ordered capacity. Com Net does not currently prioritize traffic in any form. Com Net has never limited or blocked consumers from accessing lawful content, service, service provider, application or prevented any consumer from attaching any legal device to the network. | CNI has not experienced any dropped subscribers to date for the GigE Plus project. CNI is not tracking and reporting on dropped subscribers of its Broadband Service Partners. CNI has lost the opportunity to serve prospective community anchor institutions that were included in its initial projections to competitive broadband providers on price and service availability at the time of customer commitment. | 64339 | 3970 | 2858 | 56224 | 36 | 57 | 1194 | Ottoville Mutual Telephone Company, Benton Ridge Telephone Company, Qualstar, Wabash Mutual Telephone Company, New Knoxville Telephone Company, SAA bright.net, Telephone Service Company, McClure Telephone Company, Bascom Mutual Telephone Company, Sycamore Telephone Company, NorthwestNet, Champaign Telephone Company, NetGain, Ohio K-12 Information Technology Center(s) and undisclosed customer of ZAYO. The total number of fiber miles to be delivered on completion of the post award build totals 2,915 fiber strand miles with the majority delivered to the undisclosed customer of ZAYO. With the exception of the undisclosed customers of ZAYO, all recipients of dark fiber are also using the facilities as a dark fiber tail to deliver broadband services to subscribers which drives its demand for Com Net wholesale bandwidth service; to jointly deliver with Com Net lit services to a commercial or public organization; or to establish a mid-span meet point route for connecting the company's office to another broadband service provider or to a Com Net Point-of-Presence (PoP) for a City Pair on Com Net's GigE PLUS network. | 923 | 179 | 108 | 636 | ,,,The square footage reported for 2013 is comprised of (i) one site housing Cyan equipment in leased rack space from a local service provider; (ii) leased rack space of three 19" racks in a city municipality facility with two racks for housing CNI equipment and one rack for sub-recipient equipment; (iii) rack space occupancy in a city administration building for the placement of a Cyan Chassis and auxiliary equipment; (iv) rack space occupancy in a sub-station of an electrical cooperative for the placement of Cyan equipment and auxiliary equipment; (v) one newly constructed 12x26 concrete hut enclosure placed in 2013; (vi) occupancy of rack space for the placement of Cyan equipment at one independent exchange carriers office; (vii) occupancy of rack space for the placement of Cyan equipment in a leased suite of a wireless Internet Service Provider (WISP); (viii) occupancy of rack space for the placement of Cyan equipment at a K-12 Information Technology Center's office; (ix) lease of rack space in a suite at a non-profit organization's facility for the placement of Com Net and sub-recipient equipment with the ability to sub-lease rack space as room permits; (x) adjustment of previously reported 3 huts from 12x10 to 12x20 along with the placement of 1 rack at one site and 2 racks at 2 sites by sub-recipient ZAYO with only the incremental 120 square feet and new ZAYO leased space reported; and (xi) single rack collocation space at the Equinix datacenter at 350 E. Cermak Street in Chicago, IL where customers wishing to interconnect can make their own arrangements for space and cross connect facilities to a meet-me room or Com Net's rack space demarcation point as permitted by the landlord. Fiber facilities were, also, placed to non-federally funded existing facilities of ZAYO in Toledo, Ohio and Lima, Ohio. Installation of fiber entrance facilities to ZAYO collocation space at a Dayton datacenter and to a ZAYO network center in Columbus, Ohio were still outstanding at the end of the project award. Prior to the end of the project award, Com Net had, also, entered into agreement with NetGain and Disaster Recovery Services, along with their jointly held entity Mercury Networks, to interconnect through protected-diverse path facilities that will extend the reach of the GigE network with access equipment occupying space in landlord buildings in Bellefontaine, Marysville, Delaware and Westerville Ohio. Customer will be able to interconnect to the GigE PLUS network through these sites. Non-federally funded fiber facilities were extended and lit with 10Gbps capabilities to a datacenter operator at 1 Limestone St; Springfield, Ohio, as well as, in the process of being extended to the datacenter at Wright State University with an expected completion date of January 31, 2014. Other network providers can, also, connect to Com Net's federally funded backhaul network through mid span meet-point interconnect arrangements at one or more of the multiple non-environmentally controlled outdoor enclosures housing splice points located along the new construction routes. | Continental Resources - Women Owned Team Fishel - Women Business Enterprise | Although aerial plant may be lucrative from a construction cost standpoint, do not underestimate the application fees and make ready costs in aerial construction, as well as, time line impacts and on-going repair costs. A thorough inspection of pole facilities should be completed prior to making a final determination to go aerial versus underground from a cost and timing perspective. At the same time, when making the decision to go underground, one should pursue all resource information available on subsurface soil and rock conditions. The presence of quarries in or around the planned route is a good indication you may encounter obstructions during construction. It is, also, important to engage with the authorities having jurisdiction to establish a working relationship, especially if the authorities have encountered problems with workmanship associated with the placement of communication facilities in the past. You may encounter resistance to certain methods of construction that can only be overcome through relationship building and/or negotiation of special agreements to repair any disturbed underground facilities. | COM Net, Inc. | 705 | 165 | 12 | 16 | 279 | 322 |  | 488 | 504 | 377 | 2868 | In Com Net Incorporated's (CNI's) 2011 annual performance progress report, it was noted that eleven (11) agreements classified as interconnection, peering and/or transit arrangements were established. It was later determined that four (4) of these should not have been reported in OARnet and OneCommunity as sub-recipients, as well as, Tier 2 Communications and Independents Fiber Network as wholly owned subsidiaries of CNI making the adjusted total agreements seven (7) for 2011. As of year-end 2012, CNI had established 34 agreements classified as interconnection, peering and/or transit arrangements with sub-recipient ZAYO reporting it had entered into an agreement for dark fiber with one wholesale customer. In 2013, CNI entered into a agreement to interconnect with dark fiber facilities of AVETEC in order to light them and deliver services, with TDS to move and upgrade legacy lit service provided by Com Net's wholly owned subsidiary to the federally funded network, with a national 4G wireless provider to move and upgrade legacy lit service provided by Independents Fiber Network to the federally funded network, two other national 4G wireless providers to deliver lit cell site backhaul services, with Consolidated Electric Company to establish a network-to-network interface to provide wholesale transport services and with Piqua Municipal Electric Utility Service to provide bandwidth services and to manage excess fibers deployed for the utilities SCADA system in an open network environment for the benefit of the community. In addition, Com Net entered into an agreement with NetGain and Disaster Recovery Services, along with their jointly owned entity Mercury Networks, to deliver a 10Gbps wavelength service and backhaul network management service to establish protected, diverse-path network-to-network connectivity in a mutually beneficial manner. Com Net has not denied any request for service and/or use of the facilities. Com Net has only expressed a potential for limited capabilities to deliver Indefeasible Right to Use (IRU) dark fiber as a fiber tail service under a managed service agreement based on jointly provided service plans to Community Anchor Institutions (CAIs) in certain areas of the network. | CNI did not enter into any peering or transit agreement as part of the federally funded project. Com Net's legacy core IP routers that host BGP announcements/peers with Tier 1 carriers, Tier 2 Carriers, Content Delivery Networks, IP Exchanges, Ethernet Exchanges, other regional IP network operators and with other autonomous system numbers of other providers were not made part of the GigEPAC project as in-kind nor were they purchased with federal funds. The only network equipment made part of the project was MPLS Network Equipment strictly utilized in providing Layer 2 and Layer 3 Ethernet Transport Services for delivering IP Bandwidth CNI purchases on wholesale and resells with its transport to Broadband Service Providers for their resale. CNI, also, procured a Cyan chassis and deployed it at 350 East Cermak Street, Chicago, IL for the purpose of protected transport over leased 10Gbps wavelength service for connecting to and peering with the INDATEL Services Content Delivery Network (CDN). | TRUE
NT10BIX5570073 | 2010 | $0 | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | Not available at this time. | Not available at this time. | N/A - the network has not been implemented as of yet. However, we will adhere to the network management policies provided by BTOP. | N/A | 9576 | 0 | 0 | 0 | 1064 | 0 | 8512 | N/A - we will not be wholesaling dark fiber. | 0 | 0 | 0 | 0 | We will have five new interconnection points and four existing that out network providers may interconnect to our network. | 0 | We are using our normal project management processes to run this project. However, very soon after award, we placed RFPs for legal and EA consulting. We also worked on our RFPs for construction, materials and technology in parallel to EA process. Once we have final FONSI, we'll be ready to roll. | Bend Cable Communications, LLC | 3 | 1 | 1 | 0 | 2 | 2 |  | 2 | 4 | 0 | 15 | N/A | N/A | TRUE
NT10BIX5570073 | 2011 | $35,303 | Total project cost divided by total miles. Cost decreased as total miles increased as we didn't account for the GePON miles in the baseline. | NA | Middle and last mile business project | NA | Middle and last mile business project | 1GB | No variance from baseline plan | NA | Middle and last mile business project | 100Mbs | No variance from baseline plan | NA | Middle and last mile business project | Most of the CAIs have 1.5 Mpbs with DS-3 service or didn't exist at all as it is a brand new building. The hospitals have an existing dedicated 1Gbs route. With this project, these entities will be able to select from symmetrical 10 Mbps to 1Gbs. | NA | Will upload once we have customers online. | NA | 12874 | 0 | 0 | 0 | 12874 | 0 | 0 | NA - We will not wholesale dark fiber | 0 | 0 | 0 | 0 | NA | NA | NA | Bend Cable Communications, LLC | 3 | 1 | 1 | 0 | 2 | 2 |  | 2 | 4 | 0 | 15 | NA | NA | TRUE
NT10BIX5570073 | 2012 | 35,303 | Total project cost divided by total miles. Cost decreased as total miles increased as we didn't account for the Passive Optical Network (PON) | NA | Middle and last mile business project | NA | Middle and last mile business project | 1GB | No variance from baseline | 100 MB | Last mile business | 100MB | Middle mile | 25 | Last mile business | NA | MetroEthernet Direct Internet Access - 10MB - $414; 50 MB - $1,615; 100MB - $2,612 Metro Ethernet Point to Point - 50 MB - $675; 100 MB - $825; 1GB - $1,900 Community Anchor Institutions receive 25% discount if sign a five year contract PON - 4/1.5 - $54.95; 12/1.5 - $71.95; 25/25 - $91.00; 50/50 - $150; 100/100 - $249.00 | Network Management For Internet customers, BendBroadband has not deployed congestion or network management principles. There is no mechanism in place today to adjust a customerâ€™s experience based on the type of activities they are performing on the Internet. Shared bandwidth allocated to streaming video, flash video and peer to peer file sharing applications is managed to reduce network congestion during peak traffic times. BendBroadband does not block any lawful content, applications or services and does not discriminate in transmitting lawful network traffic. BendBroadband does not block or manage any specific protocols or protocol ports, except in cases of malware, spam and viruses to protect customers. Port blocks or preventive action may be used temporarily following notice to a customer who has violated the terms of service. Voice traffic may be prioritized to improve quality. BendBroadband does not otherwise target specific types of traffic based on technology, application or provider, modify protocol fields in ways not prescribed by the protocol standard, or otherwise inhibit or favor certain applications or classes of applications. BendBroadband does not engage in any â€œdeep packet inspectionâ€ or other inspection of content for non-diagnostic purposes, such as providing customers with specific advertising or recommendations based on use of the Internet. | Zero. | 12874 | 0 | 0 | 0 | 12874 | 0 | 0 | NA - We will not wholesale dark fiber | 0 | 0 | 0 | 0 | NA | NA | NA | Bend Cable Communications, LLC | 3 | 1 | 1 | 0 | 2 | 2 |  | 2 | 4 | 0 | 15 | NA | NA | TRUE
NT10BIX5570073 | 2013 | 35,812 | Total project cost divided by total miles. | NA | Middle and last mile business project | NA | Middle and last mile business project | 1GB | No variance from baseline | 100MB | Last mile business | 100MB | Middle Mile | 25MB | Last mile | The Community Anchor Institutions seem to be mostly in two buckets: ones that received new service - average 20MB; ones that increased their bandwidth - average 100MB. We also have one who increased to 1GB. | MetroEthernet Direct Internet Access - 10MB - $414; 50 MB - $1,615; 100MB - $2,612 Metro Ethernet Point to Point - 50 MB - $675; 100 MB - $825; 1GB - $1,900 Community Anchor Institutions receive 25% discount if sign a five year contract within the grant period PON - 4/1.5 - $54.95; 12/1.5 - $71.95; 25/25 - $91.00; 50/50 - $150; 100/100 - $249.00 | Network Management For Fiber Internet customers, BendBroadband has not deployed congestion or network management principles. There is no mechanism in place today to adjust a customerâ€™s experience based on the type of activities they are performing on the Internet. Shared bandwidth allocated to streaming video, flash video and peer to peer file sharing applications is managed to reduce network congestion during peak traffic times. BendBroadband does not block any lawful content, applications or services and does not discriminate in transmitting lawful network traffic. BendBroadband does not block or manage any specific protocols or protocol ports, except in cases of malware, spam and viruses to protect customers. Port blocks or preventive action may be used temporarily following notice to a customer who has violated the terms of service. Voice traffic may be prioritized to improve quality. BendBroadband does not otherwise target specific types of traffic based on technology, application or provider, modify protocol fields in ways not prescribed by the protocol standard, or otherwise inhibit or favor certain applications or classes of applications. BendBroadband does not engage in any â€œdeep packet inspectionâ€ or other inspection of content for non-diagnostic purposes, such as providing customers with specific advertising or recommendations based on the use of the Internet. | Zero | 12874 | 0 | 0 | 0 | 12874 | 0 | 0 | One - due to confidentiality provisions can not provide the name and number of miles | 0 | 0 | 0 | 0 | NA | NA | NA | Bend Cable Communications, LLC | 3 | 1 | 1 | 0 | 2 | 2 |  | 2 | 4 | 0 | 15 | NA | NA | TRUE
NT10BIX5570074 | 2010 | 0 | Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 0 | N/A | 0 | N/A | 0 | Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 0 | N/A | 0 | Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 0 | N/A | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 66680 | 56 | 0 | 280 | 12433 | 932 | 52979 | N/A Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 0 | 0 | 0 | 0 | Contact Network Inc. is in process of negotiating collocation space in Jackson, MS and negotiations will be finalized in January 2011. In addition to this collocation space, we will have communication huts in each county. Service providers or customers that wish to make their own last mile connection into the network will be able to interconnect with us at the hut. We will also assist providers and customers with their last mile connection. | N/A | No comment | Contact Network Inc. d/b/a InLine | 260 | 41 | 9 | 8 | 212 | 159 |  | 193 | 36 | 1 | 919 | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | N/A Construction not yet begun per our baseline schedule and required Environmental Assessment activities | TRUE
NT10BIX5570074 | 2011 | 46,612 | variance is due to higher fiber costs, higher than anticipated costs related to railroad crossing and aerial permits as well as up front expenditures that should level out ie: make ready costs for aerial, one time fees associated with permitting etc.) | 0 | N/A | 0 | N/A | 1000Mbps | No Variance | 0 | N/A | 970Mbps | Currently we have 32 subscribers receiving 1000Mbps and 1 subscriber receiving 10Mbps. | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions we are servicing is 968Mbps. This number was calculated based on the fact that all 33 of our current customers were receiving 1.5Mpbs before upgrading to our service. Thirty two of our current customers are receiving 1000Mbps and one is receiving 10Mbps. | Contact Network Inc will provide multiple service tiers across the network with access speeds ranging from 10 to 1000 MBps. Currently, the retail services offered include 10Mbps, 100Mbps and 1000Mbps Private Network Connectivity, 10Mbps and 100Mbps Fiber connection with internet access and a public safety only option for 100Mbps Fiber connection with separate VLAN's to other connected Anchor Institutions. | We monitor network utilization throughout our network, as well as traffic to other autonomous networks on the public Internet. We use these metrics to determine if additional network resources are needed to provide our customers with effective Internet access. These metrics are not utilized in any way to filter or manipulate network traffic, nor are they used to prioritize services to customers based on type of traffic. During times of extremely high network traffic, application-neutral techniques may be utilized to ensure minimum advertised speeds to all clients. With the exception of blocking content, or sources of content that are harmful to the operation our network, or where a client contracts with us for a service that limits access to dangerous or undesirable content, we do not discriminate or prioritize one source or type of content over any others. Furthermore, we support and adhere to the principles contained in the FCCâ€™s August 2005 Broadband Policy Statement" (more often called the agency's Internet Policy Statement). | No subscribers have dropped the broadband service provided through this project. | 66680 | 120 | 3877 | 6552 | 12313 | 22994 | 20824 | Currently we have one wholesale customer purchasing dark fiber, PEG Bandwidth. We are leasing 76.26 fiber miles or 3877 strand miles to PEG Bandwidth. | 1035 | 260 | 0 | 775 | In addition to the collocation space described in question eleven, Contact Network Inc. has designed our network in such a way that we will support additional splice points at either our Community Anchor Institutions (or other) end points, as well as in telecom hut facilities. | We do not have any subcontracts or subgrants. | No comment. | Contact Network Inc. d/b/a InLine | 260 | 41 | 9 | 8 | 212 | 159 |  | 193 | 36 | 1 | 919 | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | TRUE
NT10BIX5570074 | 2012 | 37308 | variance is due to higher fiber costs, higher than anticipated costs related to railroad crossing and aerial permits as well as up front expenditures that should level out ie: make ready costs for aerial, one time fees associated with permitting etc.) | 0 | N/A | 0 | N/A | 1000Mbps | No Variance | 0 | N/A | 948Mbps | Currently we have two subscribers receiving 100Mbps, one receiving 10Mbps , the rest are receiving 1000Mbps service. | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions we are servicing is 824Mbps. This number was calculated based on the fact that all 90 percent of our current customers were receiving 1.5Mpbs before upgrading to our service. | Contact Network Inc will provide multiple service tiers across the network with access speeds ranging from 10 to 1000 MBps. Currently, the retail services offered include 10Mbps, 100Mbps, 500Mbps and 1000Mbps Private Network Connectivity, 10Mbps and 100Mbps Fiber connection with internet access and a public safety only option for 100Mbps Fiber connection with separate VLAN's to other connected Anchor Institutions. | We monitor network utilization throughout our network, as well as traffic to other autonomous networks on the public Internet. We use these metrics to determine if additional network resources are needed to provide our customers with effective Internet access. These metrics are not utilized in any way to filter or manipulate network traffic, nor are they used to prioritize services to customers based on type of traffic. During times of extremely high network traffic, application-neutral techniques may be utilized to ensure minimum advertised speeds to all clients. With the exception of blocking content, or sources of content that are harmful to the operation our network, or where a client contracts with us for a service that limits access to dangerous or undesirable content, we do not discriminate or prioritize one source or type of content over any others. Furthermore, we support and adhere to the principles contained in the FCCâ€™s August 2005 Broadband Policy Statement" (more often called the agency's Internet Policy Statement). | No subscribers have dropped the broadband service provided through this project. | 64697 | 1137 | 26345 | 34651 | 69 | 101 | 2394 | Currently we have two wholesale customers purchasing dark fiber, PEG Bandwidth and Windstream. We are leasing 372 fiber miles or 25,830 strand miles to PEG Bandwidth and 50 fiber miles or 515 strand miles to Windstream. | 1035 | 260 | 11 | 764 | In addition to the collocation space described in question eleven, Contact Network Inc. has designed our network in such a way that we will support additional splice points at either our Community Anchor Institutions (or other) end points, as well as in telecom hut facilities. | We do not have any subcontracts or subgrants. | The most important lesson that we have learned is to plan as far ahead as possible. The focus of this being on permits for railroads, department of transportation and pole attachments. Some of these permits can take months to process and without proper planning, the project could become delayed for that time while waiting on approval. | Contact Network Inc. d/b/a InLine | 260 | 41 | 9 | 8 | 212 | 159 |  | 193 | 36 | 1 | 919 | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | TRUE
NT10BIX5570074 | 2013 | 37709 | variance is due to higher fiber costs, higher than anticipated costs related to railroad crossing and aerial permits | 0 | N/A | 0 | N/A | 1000Mbps | No Variance | 0 | N/A | 755Mbps | Currently we have four subscribers receiving 500Mbps; twenty six receiving 100Mbps, thirteen receiving 50Mbps; three receiving 20Mbps, seven receiving 10Mbps , the rest are receiving 1000Mbps service. | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions we are servicing is 378Mbps. This number was calculated based on the fact that all 95 percent of our current customers were receiving 1.5Mpbs before upgrading to our service. | Contact Network Inc will provide multiple service tiers across the network with access speeds ranging from 10 to 1000 MBps. Currently, the retail services offered include 10Mbps, 20Mpbs, 50Mbps 100Mbps, 500Mbps and 1000Mbps Private Network Connectivity, 10Mbps, 20Mbps, 50Mbps and 100Mbps Fiber connection with internet access and a public safety only option for 100Mbps Fiber connection with separate VLAN's to other connected Anchor Institutions. | We monitor network utilization throughout our network, as well as traffic to other autonomous networks on the public Internet. We use these metrics to determine if additional network resources are needed to provide our customers with effective Internet access. These metrics are not utilized in any way to filter or manipulate network traffic, nor are they used to prioritize services to customers based on type of traffic. During times of extremely high network traffic, application-neutral techniques may be utilized to ensure minimum advertised speeds to all clients. With the exception of blocking content, or sources of content that are harmful to the operation our network, or where a client contracts with us for a service that limits access to dangerous or undesirable content, we do not discriminate or prioritize one source or type of content over any others. Furthermore, we support and adhere to the principles contained in the FCCâ€™s August 2005 Broadband Policy Statement" (more often called the agency's Internet Policy Statement). | No subscribers have dropped the broadband service provided through this project. | 74062 | 4021 | 26446 | 43595 | 0 | 0 | 0 | Currently we have two wholesale customers purchasing dark fiber, PEG Bandwidth and Windstream. We are leasing 372 fiber miles or 25,931 strand miles to PEG Bandwidth and 50 fiber miles or 515 strand miles to Windstream. | 1035 | 260 | 11 | 764 | In addition to the collocation space described in question eleven, Contact Network Inc. has designed our network in such a way that we will support additional splice points at either our Community Anchor Institutions (or other) end points, as well as in telecom hut facilities. | We do not have any subcontracts or subgrants. | The most important lesson that we have learned is to plan as far ahead as possible. The focus of this being on franchise agreements and permits for railroads, department of transportation and pole attachments. Some of these permits can take months to process and without proper planning, the project could become delayed for that time while waiting on approval. | Contact Network Inc. d/b/a InLine | 260 | 41 | 9 | 8 | 212 | 159 |  | 193 | 36 | 1 | 919 | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | TRUE
NT10BIX5570075 | 2010 | 0 | The first fiber miles will be put in service during the forth quarter of the project; this annual report only includes the first two quarters of the project | 0 | NA | 0 | NA | 1000000000 | 10Gb/s sec | 0 | NA | 8000000000 | 8Gb/sec | 0 | NA | N/A | N/A | The Internet2 IP network (AS 11537) generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: â€¢ The forwarding of traffic explicitly tagged as "less than best effort" (aka Scavenger Service) by the end user. Internet2 offers less than best effort traffic forwarding to support researchers that choose a lower class of service for transferring large datasets which are insensitive to loss or latency. â€¢ MPLS traffic engineering is sometimes used to differentially route Internet2's "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. â€¢ Internet2 offers its network peers the option of using BGP community strings to signal to the Internet2 backbone that traffic destined for a particular prefix should be discarded at the earliest opportunity. This mechanism is provided so that Internet2 network peers are able to minimize the effects of an on-going network-based attack. In addition, network peers are provided with a range of traffic influencing BGP community values to control how their [the peer's] traffic is treated by the backbone. The Internet2 IP network is used exclusively for transit among regional networks and the public Internet (i.e., no users connect directly to the Internet2 IP network). The Internet2 IP network does not interfere with the transmission of content as long as the content is not harmful to | N/A | 32624 | 0 | 0 | 0 | 32624 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | All of the project's network interconnection facilities are either located in carrier-neutral collocation facilities such as those hosted by Equinix or within carried-owned facilities such as Level 3's. In all cases, the facility owner provides collocation and cross-connect services on a nondiscriminatory basis, within reasonable business and technical terms. | N/A | Seek clarification of any program requirements directly from your NTIA team. Ensure that you understand and comply with all recipient requirements, which includes ensuring that sub-recipients do the same. Ensure that your vendor/contractor agreements contain language to ensure they comply with any flow-through requirements of the program. Complete drafts of compliance reports ahead of schedule and seek their review by your NTIA team. Maintain a calendar of compliance deadlines. If you receive verbal advice from your NTIA team, acknowledge your understanding of such advice in writing to ensure your understanding is correct and that the information is documented. Perform on the stated goals of your project (i.e., don't lose sight of the goals). | University Corporation For Advanced Internet Development | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | For clarification, this project includes approximately 100+ pre-existing interconnection agreements. These are typically informal settlement-free peering agreements with commercial networks (e.g., Facebook, Google, etc.). | For clarification, this project includes the improvement of access for 20 pre-existing transit customers. | TRUE
NT10BIX5570075 | 2011 | 7105 | This number was calculated by using the Actual Total Cost from Project Inception through the End of the Current Reporting Period ($53,437,496) divided by the Number of Network Miles Leased (7,521). ($53,437,496 Ã· 7,521 = $7,105) | 0 | NA | 0 | NA | 1000000000 | 10Gb/sec | 0 | NA | 8000000000 | 8Gb/sec | 0 | NA | NA | NA | The Internet2 IP network (AS 11537) generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: â€¢ The forwarding of traffic explicitly tagged as "less than best effort" (aka Scavenger Service) by the end user. Internet2 offers less than best effort traffic forwarding to support researchers that choose a lower class of service for transferring large datasets which are insensitive to loss or latency. â€¢ MPLS traffic engineering is sometimes used to differentially route Internet2's "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. â€¢ Internet2 offers its network peers the option of using BGP community strings to signal to the Internet2 backbone that traffic destined for a particular prefix should be discarded at the earliest opportunity. This mechanism is provided so that Internet2 network peers are able to minimize the effects of an on-going network-based attack. In addition, network peers are provided with a range of traffic influencing BGP community values to control how their [the peer's] traffic is treated by the backbone. The Internet2 IP network is used exclusively for transit among regional networks and the public Internet (i.e., no users connect directly to the Internet2 IP network). The Internet2 IP network does not interfere with the transmission of content as long as the content is not harmful to | NA | 32624 | 7521 | 0 | 0 | 25103 | 0 | 0 | NA | 0 | 0 | 0 | 0 | All of the project's network interconnection facilities are either located in carrier-neutral collocation facilities such as those hosted by Equinix or within carried-owned facilities such as in Level 3. In all cases, the facility owner provides collocation and cross-connect services on a nondiscriminatory basis, within reasonable business and technical terms. | NA | Seek clarification of any program requirements directly from your NTIA team. Ensure that you understand and comply with all recipient requirements, which includes ensuring that sub-recipients do the same. Ensure that your vendor/contractor agreements contain language to ensure they comply with any flow-through requirements of the program. Complete drafts of compliance reports ahead of schedule and seek their review by your NTIA team. Maintain a calendar of compliance deadlines. If you receive verbal advice from your NTIA team, acknowledge your understanding of such advice in writing to ensure your understanding is correct and that the information is documented. Perform on the stated goals of your project (i.e., don't lose sight of the goals). | University Corporation For Advanced Internet Development | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | For clarification, this project includes approximately 100+ pre-existing interconnection agreements. These are typically informal settlement-free peering agreements with commercial networks (e.g., Facebook, Google, etc.). Internet2 maintains a number of informal settlement-free-interconnect agreements with content providers and small internet service providers. There are no formal agreements that have been arranged in the last annual reporting period, nor are there any agreements currently in negotiation. | For clarification, this project includes the improvement of access for 20 pre-existing transit customers. We have 2 Letters of Intent that may result in 2 additional connections by Year 3, Quarter 1. | TRUE
NT10BIX5570075 | 2012 | 0 | Internet2 leased all miles for this project. | 0 | NA | 0 | NA | 10000000000 | 100Gb/sec | 0 | NA | 8000000000 | 8Gb/sec | 0 | NA | NA | NA | The Internet2 IP network (AS 11537) generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: â€¢ The forwarding of traffic explicitly tagged as "less than best effort" (aka Scavenger Service) by the end user. Internet2 offers less than best effort traffic forwarding to support researchers that choose a lower class of service for transferring large datasets which are insensitive to loss or latency. â€¢ MPLS traffic engineering is sometimes used to differentially route Internet2's "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. â€¢ Internet2 offers its network peers the option of using BGP community strings to signal to the Internet2 backbone that traffic destined for a particular prefix should be discarded at the earliest opportunity. This mechanism is provided so that Internet2 network peers are able to minimize the effects of an on-going network-based attack. In addition, network peers are provided with a range of traffic influencing BGP community values to control how their [the peer's] traffic is treated by the backbone. The Internet2 IP network is used exclusively for transit among regional networks and the public Internet (i.e., no users connect directly to the Internet2 IP network). The Internet2 IP network does not interfere with the transmission of content as long as the content is not harmful to | NA | 36360 | 31434 | 0 | 0 | 31434 | 0 | 0 | NA | 0 | 0 | 0 | 0 | All of the project's network interconnection facilities are either located in carrier-neutral collocation facilities such as those hosted by Equinix or within carried-owned facilities such as in Level 3. In all cases, the facility owner provides collocation and cross-connect services on a nondiscriminatory basis, within reasonable business and technical terms. | NA | Seek clarification of any program requirements directly from your NTIA team. Ensure that you understand and comply with all recipient requirements, which includes ensuring that sub-recipients do the same. Ensure that your vendor/contractor agreements contain language to ensure they comply with any flow-through requirements of the program. Complete drafts of compliance reports ahead of schedule and seek their review by your NTIA team. Maintain a calendar of compliance deadlines. If you receive verbal advice from your NTIA team, acknowledge your understanding of such advice in writing to ensure your understanding is correct and that the information is documented. Perform on the stated goals of your project (i.e., don't lose sight of the goals). | University Corporation For Advanced Internet Development | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | For clarification, this project includes approximately 100+ pre-existing interconnection agreements. These are typically informal settlement-free peering agreements with commercial networks (e.g., Facebook, Google, etc.). Internet2 maintains a number of informal settlement-free-interconnect agreements with content providers and small internet service providers. There are no formal agreements that have been arranged in the last annual reporting period, nor are there any agreements currently in negotiation. | For clarification, this project includes the improvement of access for 20 pre-existing transit customers and new access for 2 new customers. | TRUE
NT10BIX5570075 | 2013 | 0 | Internet2 leased all miles for this project. | 0 | NA | 0 | NA | 100000000000 | 100GB/sec | 0 | NA | 8000000000 | NA | 0 | NA | NA | NA | The Internet2 IP network (AS 11537) generally provides best effort forwarding of all IP traffic. Exceptions to best effort forwarding are limited to the following: â€¢ The forwarding of traffic explicitly tagged as "less than best effort" (aka Scavenger Service) by the end user. Internet2 offers less than best effort traffic forwarding to support researchers that choose a lower class of service for transferring large datasets which are insensitive to loss or latency. â€¢ MPLS traffic engineering is sometimes used to differentially route Internet2's "managed high-speed service" traffic from commercial peering or commodity traffic for the purpose of load balancing traffic among backbone resources. â€¢ Internet2 offers its network peers the option of using BGP community strings to signal to the Internet2 backbone that traffic destined for a particular prefix should be discarded at the earliest opportunity. This mechanism is provided so that Internet2 network peers are able to minimize the effects of an on-going network-based attack. In addition, network peers are provided with a range of traffic influencing BGP community values to control how their [the peer's] traffic is treated by the backbone. The Internet2 IP network is used exclusively for transit among regional networks and the public Internet (i.e., no users connect directly to the Internet2 IP network). The Internet2 IP network does not interfere with the transmission of content as long as the content is not harmful to | NA | 36360 | 36360 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | All of the project's network interconnection facilities are either located in carrier-neutral collocation facilities such as those hosted by Equinix or within carried-owned facilities such as in Level 3. In all cases, the facility owner provides collocation and cross-connect services on a nondiscriminatory basis, within reasonable business and technical terms. | NA | Seek clarification of any program requirements directly from your NTIA team. Ensure that you understand and comply with all recipient requirements, which includes ensuring that sub-recipients do the same. Ensure that your vendor/contractor agreements contain language to ensure they comply with any flow-through requirements of the program. Complete drafts of compliance reports ahead of schedule and seek their review by your NTIA team. Maintain a calendar of compliance deadlines. If you receive verbal advice from your NTIA team, acknowledge your understanding of such advice in writing to ensure your understanding is correct and that the information is documented. Perform on the stated goals of your project (i.e., don't lose sight of the goals). | University Corporation For Advanced Internet Development | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | For clarification, this project includes approximately 100+ pre-existing interconnection agreements. These are typically informal settlement-free peering agreements with commercial networks (e.g., Facebook, Google, etc.). | For clarification, this project includes the improvement of access for 21 pre-existing transit customers and new access for 3 new customers. | TRUE
NT10BIX5570076 | 2010 | 0 | No facilities constructed to date. | 0 | Not Last Mile provider. | 0 | Not Last Mile provider. | 0 | No facilities constructed to date. | 0 | Not Last Mile provider. | 0 | No facilities constructed to date. | 0 | Not Last Mile provider. | N/A - No facilities constructed to date | N/A - No facilities constructed to date; all services planned are described in the Application Service Deck. | N/A - No facilities constructed to date | N/A - Not there yet | 111312 | 0 | 0 | 0 | 111312 | 0 | 0 | NA - No facilities constructed to date | 0 | 0 | 0 | 0 | Sovernet Fiber Corp is not constructing any collocation facilities. Providers and/or customers will interconnect at Fairpoint collocation facilities. | None | Our project is just getting started. At this time we do not have any best practices/lessons learned to share. As our project progresses, we will include. | Vermont Telecommunications Authority | 103 | 41 | 10 | 18 | 28 | 25 |  | 75 | 3 | 0 | 303 | N/A | N/A | TRUE
NT10BIX5570076 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10 Gbps | for data transport service | 0 | N/A | 0 | N/A | 0 | N/A | Network construction has not been completed; no CAI's have yet been connected or experienced an increase in broadband speed. | Retail services are not yet being provided since the network is still under construction. | Subrecipient has not begun to provide service. | Not applicable, as network is only middle mile. | 111312 | 0 | 0 | 0 | 111312 | 0 | 0 | N/A. | 0 | 0 | 0 | 0 | N/A. No collocation space is presently in service. | To our knowledge, no SDB has been subcontracted or received a subgrant under this award. | Entering contracts with multiple fiber vendors has alleviated concerns regarding ability to timely procure fiber. | Vermont Telecommunications Authority | 103 | 41 | 10 | 18 | 28 | 25 |  | 75 | 3 | 0 | 303 | N/A | N/A | TRUE
NT10BIX5570076 | 2012 | $33,200 | Figure is preliminary, as OSP construction contractors have not yet rendered final invoices for any of the primary bid packages. Includes make-ready charges. | 0 | N/A | 0 | N/A | 10 Gbps | for data transport service | 0 | N/A | GigE,100 Mbps CIR | N/A | 0 | N/A | 79 Mbps. Average increase in broadband speed is calculated as difference between contracted-for broadband connection speeds before and after connection to BTOP network. | Only Direct Internet Access service as of end of reporting period. | 7a.: SFC will not manage or limit the content of communications traffic transiting SFC's network, except to the extent necessary to maintain reliable service. SFCâ€™s network management practices does not involve preferential routing of traffic on the basis of content or provider. SFC utilizes neutral traffic routing, and will enable connections to other carriers and to the public Internet. 7b.: No. | Not applicable, as network is only middle mile. | 111312 | 53 | 0 | 54288 | 56971 | 0 | 0 | N/A. | 0 | 0 | 0 | 0 | In the attached addendum, SFC has identified the Points of Presence where any carrier collocated in that facility would have the ability interconnect with SFC. A typical carrier-to-carrier network interconnection would use a fiber cross-connect to create an NNI. | To our knowledge, no SDB has been subcontracted or received a subgrant under this award. | N/A | Vermont Telecommunications Authority | 103 | 41 | 10 | 18 | 28 | 25 |  | 75 | 3 | 0 | 303 | Duncan Cable Television Southern Vermont Broadband Cooperative Educational Networks of America | N/A | TRUE
NT10BIX5570076 | 2013 | $31,200 | Figure is preliminary, as OSP construction contractors have not yet invoiced SFC for all work that has been completed. The average cost for the Essex County build is $23,000 per mile | 0 | N/A | 0 | N/A | 10 Gbps | for transport service | 0 | N/A | 88 Mbps | N/A | 0 | N/A | 81 Mbps. We have incomplete data on the broadband speeds that were being purchased by CAI's prior to this project, but estimate the average was 7.5 Mbps. The average speed of service provided to CAI customers using the new network is 88 Mbps (symmetrical, and committed rate). Burst rates provided as WAN transport services can be substantially higher. This average is computed using the committed information rate of WAN transport services provided to each customer, or, for Internet-access-only services, the committed Internet bandwidth provided. | Retail services provided include: symmetrical Internet access starting at 10 Mbps, GigE WAN point-to-point or point-to-multipoint transport services with committed information rates starting at 100 Mbps and burstable rates up to 10 Gbps, combined transport and Internet delivered over the same connection. Prices vary on a case-by-case basis, as market and competitive conditions warrant. Attachment name: "VTA FiberConnect Rate Sheet.pdf" | 7a/b for the Essex dark fiber segment: VTA does not have any restrictive policies for dark fiber (it is open access) 7a.: SFC will not manage or limit the content of communications traffic transiting SFC's network, except to the extent necessary to maintain reliable service. SFC's network management practices do not involve preferential routing of traffic on the basis of content or provider. SFC utilizes neutral traffic routing, and will enable connections to other carriers and to the public Internet. 7b.: No. | No subscribers of broadband service provided through this project have dropped the service. | 117560 | 58780 | 2936 | 55556 | 288 | 0 | 0 | The VTA built 13 miles of fiber in Essex county. This segment is available to lease which connects to other dark fiber routes in the Northeast region of Vermont. The VTA expects this route to be utilized in a planned fiber route from Boston to Montreal by a service provider once the adjoining fiber routes are finished. | 852 | 828 | 4 | 20 | Sovernet is collocated in the incumbent central offices or PoPâ€™s listed in the APR addendum as â€œFacilitiesâ€. Other service providers can interconnect with Sovernetâ€™s network by collocating in those facilities as well and requesting permission from the owner of the facility for indirect cross-connects or direct cable connections between collocation bays. Interconnection points can be reached at the following locations: Brattleboro CO Brattleboro, Main St Wilmington CO Williamstown CO St. Johnsbury CO Hardwick CO Lebanon CO Stratton CO Manchester CO Rutland CO Middlebury CO Burlington CO Burlington POP Essex Junction CO Keene CO Manchester, Sundial Manchester CO Boston, 1 Summer For the Essex county dark fiber segment, access to use the fiber will be accommodated at any splice point along the route by contacting the VTA and entering into an IRU. | No SDB has been subcontracted or received a subgrant under this award. | N/A | Vermont Telecommunications Authority | 103 | 41 | 10 | 18 | 28 | 25 |  | 75 | 3 | 0 | 303 | Interconnect: 1) Three wholesale service agreements have been entered with broadband and communications service providers. Cloud Alliance Vanu Coverage Co. WaveComm 2) None. 3) No | Peering / Transit: 1) Peering or transit agreements have been entered with three service providers. Fairpoint Verizon Sidera 2) None. 3) No. | TRUE
NT10BIX5570077 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 10213 | 0 | 0 | 0 | 4428 | 0 | 5785 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Silver Star Telephone Company, INC. | 5 | 1 | 0 | 5 | 3 | 8 |  | 27 | 1 | 0 | 50 | N/A | N/A | TRUE
NT10BIX5570077 | 2011 | $106,656 | Variance is due to actual construction bid cost lower than original estimate | N/A | N/A | N/A | N/A | 1 Gbps | No variance | N/A | N/A | Mbps | N/A | N/A | N/A | N/A | N/A | 7a. Recipient currently maintains an open network policy and does not differentiate among applications that travel across its Internet network. Recipient employs reasonable network management policies to provide acceptable service levels to all customers and has measures in place to address service attacks, illegal content and other harmful activities to protect its network integrity and reliability. 7b. Recipient's policy is not to block access to any lawful content, service, service provider or application or to prevent a consumer from attaching any legal device to the network. | N/A | 10213 | 336 | 0 | 2100 | 4428 | 0 | 5785 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Silver Star Telephone Company, INC. | 5 | 1 | 0 | 5 | 3 | 8 |  | 27 | 1 | 0 | 50 | N/A | N/A | TRUE
NT10BIX5570077 | 2012 | 120,149 | Variance due to actual construction bid cost lower than original estimate; cost increased from prior year due to "in-town" higher costs of construction. | N/A | N/A | N/A | N/A | 10 Gbps | No variance | N/A | N/A | 10 Gbps | N/A | 100 Mbps | N/A | Recipient estimates speed increases ranging from 5 Mbps up to 100 Mbps. This estimate is based on information relayed by CAIs. A prime example is a CAI that experienced speeds of 56 Kbps to 512 Kbps, depending on location, and it is now running a 100 Mbps Vlan and is connected to the internet at 100 Mbps as a direct result of the BTOP Project. This type of bandwidth was simply unattainable prior the BTOP facilities construction because of the prohibitive cost to reach remote areas over difficult terrain. | Recipient's broadband offerings are varied and pricing depends on the type(s) of service(s) and location. Sample services and plan pricing include: 4Mb Down / 768Kb Up $49.95 6Mb Down / 768Kb Up $59.95 15Mb Down / 768Kb Up $94.95 20Mb Down / 5Mb Up $109.95 Upload Speed Upgrade 3Mb Up (Available on 6Mb, 10Mb & 15Mb) $10/mo. Higher upload speeds are available upon request. | 7a. Recipient currently maintains an open network policy and does not differentiate among applications that travel across its Internet network. Recipient employs reasonable network management policies to provide acceptable service levels to all customers and has measures in place to address service attacks, illegal content and other harmful activities to protect its network integrity and reliability. 7b. Recipient's policy is not to block access to any lawful content, service, service provider or application or to prevent a consumer from attaching any legal device to the network. | N/A | 10535 | 3069 | 0 | 7466 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Providers may interconnect to the network via project fiber meet points, and customers are connected at nearby handholes. Leased fibers, if any are patched through project points of facilities and Recipient's central office facilities. | N/A | Best practices include starting project activities immediately upon award notification, particularly with regard to environmental assessment tasks. Maintaining consistent internal communications is key to ensuring project stays on track and meets both the organization and agency goals. Maintaining external relations through open communications with contracts/vendors, community and project stakeholders, also an important element to project success. | Silver Star Telephone Company, INC. | 5 | 1 | 0 | 5 | 3 | 8 |  | 27 | 1 | 0 | 50 | N/A | N/A | TRUE
NT10BIX5570078 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 10537 | 0 | 0 | 0 | 6480 | 0 | 4057 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Silver Star Telephone Company, INC. | 4 | 0 | 0 | 0 | 4 | 1 |  | 27 | 5 | 0 | 41 | N/A | N/A | TRUE
NT10BIX5570078 | 2011 | $96,258 | No Variance | N/A | N/A | N/A | N/A | 1 Gbps | N/A | N/A | N/A | Mbps | N/A | N/A | N/A | Testing to occur and services anticipated to be available 1q012 | N/A | 7a. Recipient currently maintains an open network policy and does not differentiate among applications that travel across its Internet network. Recipient employs reasonable network management policies to provide acceptable service levels to all customers and has measures in place to address service attacks, illegal content and other harmful activities to protect its network integrity and reliability. 7b. Recipient's policy is not to block access to any lawful content, service, service provider or application or to prevent a consumer from attaching any legal device to the network. | N/A | 10537 | 0 | 0 | 0 | 6480 | 0 | 4057 | N/A | 528 | 384 | 0 | 144 | N/A | N/A | N/A | Silver Star Telephone Company, INC. | 4 | 0 | 0 | 0 | 4 | 1 |  | 27 | 5 | 0 | 41 | N/A | N/A | TRUE
NT10BIX5570078 | 2012 | 74,950 | Variance due to lower than estimated construction contractor bid | N/A | N/A | N/A | N/A | 10 Gbps | N/A | N/A | N/A | 10 Gpbs | N/A | 10 Mbps | N/A | Recipient estimates speed increases ranging from 5 Mbps up to 100 Mbps. This estimate is based on information relayed by CAIs. A prime example is a CAI that experienced speeds of 56 Kbps to 512 Kbps, depending on location, and it is now running a 100 Mbps Vlan and is connected to the internet at 100 Mbps as a direct result of the BTOP Project. This type of bandwidth was simply unattainable prior the BTOP facilities construction because of the prohibitive cost to reach remote areas over difficult terrain. | Sample services and plan pricing include: 4Mb Down / 768Kb Up $49.95 6Mb Down / 768Kb Up $59.95 15Mb Down / 768Kb Up $94.95 20Mb Down / 5Mb Up $109.95 Upload Speed Upgrade 3Mb Up (Available on 6Mb, 10Mb & 15Mb) $10/mo. Higher upload speeds are available upon request. | 7a. Recipient currently maintains an open network policy and does not differentiate among applications that travel across its Internet network. Recipient employs reasonable network management policies to provide acceptable service levels to all customers and has measures in place to address service attacks, illegal content and other harmful activities to protect its network integrity and reliability. 7b. Recipient's policy is not to block access to any lawful content, service, service provider or application or to prevent a consumer from attaching any legal device to the network. | N/A | 11584 | 6780 | 172 | 4632 | 0 | 0 | 0 | N/A | 528 | 384 | 0 | 144 | Providers may interconnect to the network via project fiber meet points, and customers are connected at nearby handholes. Leased fibers, if any are patched through project points of facilities and Recipient's central office facilities. | N/A | Best practices include starting project activities immediately upon award notification, particularly with regard to environmental assessment tasks. Maintaining consistent internal communications is key to ensuring project stays on track and meets both the organization and agency goals. Maintaining external relations through open communications with contracts/vendors, community and project stakeholders, also an important element to project success. | Silver Star Telephone Company, INC. | 4 | 0 | 0 | 0 | 4 | 1 |  | 27 | 5 | 0 | 41 | N/A | N/A | TRUE
NT10BIX5570078 | 2013 | 62710 | Variance due to lower than estimated construction contractor bid | N/A | N/A | N/A | N/A | 10 Gbps | N/A | N/A | N/A | 10 Gbps | N/A | 10 Mbps | N/A | Recipient estimates speed increases ranging from 5 Mbps up to 100 Mbps. This estimate is based on information relayed by CAIs. A prime example is a CAI that experienced speeds of 56 Kbps to 512 Kbps, depending on location, and it is now running a 100 Mbps Vlan and is connected to the internet at 100 Mbps as a direct result of the BTOP Project. This type of bandwidth was simply unattainable prior the BTOP facilities construction because of the prohibitive cost to reach remote areas over difficult terrain. | Sample services and plan pricing include: 4Mb Down / 768Kb Up $49.95 6Mb Down / 768Kb Up $59.95 15Mb Down / 768Kb Up $94.95 20Mb Down / 5Mb Up $109.95 Upload Speed Upgrade 3Mb Up (Available on 6Mb, 10Mb & 15Mb) $10/mo. Higher upload speeds are available upon request. | 7a. Recipient currently maintains an open network policy and does not differentiate among applications that travel across its Internet network. Recipient employs reasonable network management policies to provide acceptable service levels to all customers and has measures in place to address service attacks, illegal content and other harmful activities to protect its network integrity and reliability. 7b. Recipient's policy is not to block access to any lawful content, service, service provider or application or to prevent a consumer from attaching any legal device to the network. | N/A | 11584 | 6780 | 172 | 4632 | 0 | 0 | 0 | N/A | 528 | 384 | 0 | 144 | Providers may interconnect to the network via project fiber meet points, and customers are connected at nearby handholes. Leased fibers, if any, are patched through at project points of facilities and Recipient's central office facilities. | N/A | Best practices include starting project activities immediately upon award notification, particularly with regard to environmental assessment tasks. Maintaining consistent internal communications is key to ensuring project stays on track and meets both the organization and agency goals. Maintaining positive external relations through open communications with contracts/vendors, community and project stakeholders, also an important element to project success. | Silver Star Telephone Company, INC. | 4 | 0 | 0 | 0 | 4 | 1 |  | 27 | 5 | 0 | 41 | N/A | N/A | TRUE
NT10BIX5570079 | 2010 | 0 | Consistent with Baseline - No Construction Activity until FONSI received | 0 | N/A - no households or businesses served | 0 | Consistent with Baseline - No Construction Activity until FONSI received | 10 GBPS | Consistent with Baseline | 10 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | N/A. The project has not broken ground to begin construction yet. We anticipate benefits to both broadband speeds as well as reduced costs for those speed tiers. | The project is not providing any retail services. The project is only providing dark fiber only. Pricing for one pair of fibers will be about $250 per month for government and non profit anchor sites, and about $1,000 per month for commercial entities and enterprises. | A) - Network Management policies are still under development B) - No limiting or blocking of service | As the project is providing only dark fiber, not lit services, its typical network stakeholders will be CAIs and local communications companies, not "subscribers." Since the project has yet to start construction and has not yet connected any CAIs or interconnected with any communications companies, there have been no fiber connections to drop. | 0 | 0 | 0 | 0 | 23055 | 0 | 23055 | As the network has not yet been constructed, there are no current customers. | 750 | 6 | 0 | 18 | In addition to County collocation space, the network is being designed for future likely interconnection points with providers. There are over 20 facilities-based providers in the county. We are trying to meet and plan interconnection with them where feasible and where they desire it. Two definite collocation spaces will be in the data centers at the Clackamas Education Service District (approx. 4,000 sq/ft facility), and SandyNet (approx. 160 sq/ft facility), a retail service provider in the City of Sandy. | None at this time. | None at this time. | Clackamas, County of | 101 | 11 | 3 | 0 | 20 | 51 |  | 18 | 43 | 2 | 249 | (1) - No Agreement completed (2) - 7 Agreements currently in various levels of negotiation (3) - No requests have been denied | 1) No agreements have been completed. 2) 7 agreements are in various levels of negotiation; whether they include peering arrangements or not has yet to be determined. 3) No requests have been denied. | TRUE
NT10BIX5570079 | 2011 | 0 | N/A. There were no Middle Miles in service as of 12/31/2011, as described in the January 2012 APR Reporting Guidance document. | 0 | N/A. The project will not directly serve any households or businesses. | 0 | N/A. This was not reported in Baseline. This project only offers dark fiber so does not have subscribers. | 10 GBPS | Consistent with Baseline | 10 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | N/A - The project construction has concentrated on Middle Mile Backbone and pole make ready. Lateral connections will begin in Q1 of 2012. We anticipate benefits to both broadband speeds as well as reduced costs for those speed tiers. The project will track the historic connection speeds and costs to CAI sites for reporting purposes as they are connected to our project. Current pre-project options range from no connectivity, T1, DSL and some fiber connections, though speed is questionable because the fiber connections are typically shared among multiple CAI sites. | This project is not providing any retail services - dark fiber only. Pricing for one pair of fibers is $250 per month for governmental and Non-Profit anchor sites. Commercial rates are $1,000 per month per pair of ring fiber. | A) - Network Management policies are on the project web site. However, the project has no services so there are policies related to services or network traffic. B) - No, we have never blocked or limited users. The project only provides dark fiber so there are no services to block or limit. | N/A. This project does not have subscribers. | 33834 | 0 | 0 | 17428 | 1970 | 7382 | 7054 | None. Wholesale customers are awaiting the rings to be finished before leasing. | 350 | 50 | 0 | 300 | Clackamas County owns 2 interconnect facility locations (hubs). One is the Development Services Building (200 sq/ft) and the other is North Station (150 sq/ft). Both are now operational and available. There are two other primary facilities currently under development with providers. One is the Clackamas Educational Service District's data center (4,000 sq/ft) and the other is SandyNet's data center (160 sq/ft). In addition, the network is being designed for future likely interconnection points with providers. We are currently in negotiations with several local and regional providers which include collocation facilities, and the middle mile path was planned to be within one block of most central offices of local telecom providers. | None at this time | Not at this Time | Clackamas, County of | 101 | 11 | 3 | 0 | 20 | 51 |  | 18 | 43 | 2 | 249 | (1) - No Agreement Completed (2) - 9 Agreements with providers currently in negotiation under Non-Disclosure Agreements. 20+ Service Level Agreements under review with CAI sites for connection. (3) - No requests have been denied. | (1) - No agreements have been completed. (2) - 9 Agreements are in various levels of negotiation; whether they include peering arrangements or not has yet to be determined. (3) - No requests have been denied. | TRUE
NT10BIX5570079 | 2012 | $47,168 | Consistent with Baseline (it is 0.005% greater, or $269/route mile more, than baseline of $46,899). | N/A | N/A. The project will not directly serve any households or businesses. | N/A | N/A. This was not reported in Baseline. This project only offers dark fiber so does not have subscribers. | 10 GBPS | Consistent with Baseline | 10 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | The estimated average increase to CAIs is between 900mb-1Gig. Generally, schools and institutions of higher education were getting 100mb shared connections which were less than 100mb each. Generally, fire stations and county sites had T1s, which was 1.5mb, so the fiber resulted in almost full 1Gig increases. Typical basic off-the-shelf electronics provide a minimum of 1Gig service; some school districts are using 10Gig equipment. | N/A. This is a dark fiber project. No services are provided. | 7a. This is a dark fiber project and we will not be providing any services. We do not have any policies that limit bandwidth or traffic prioritization. 7b. No, and we have no way to limit or block customers. This is an open access, dark fiber project. The network is open to any service provider that wishes to connect. Once connected, the service provider can utilize the dark fiber network as needed to meet its needs. | N/A. This is a dark fiber project and we do not provide any lit services to the general public. Therefore, we have not had any subscribers drop our services. | 34088 | 223 | 133 | 33060 | 0 | 0 | 672 | No wholesaler signed on as of Dec 31, 2012 because the Middle Mile network has not been completed yet. | 350 | 50 | 0 | 300 | Clackamas County owns 2 interconnect facility locations (hubs) at the Development Services Building (DSB) (200 sq/ft), and North Station (150 sq/ft). Both are now operational and available. There are two other primary facilities with local providers. One is the Clackamas Educational Service District's data center (4,000 sq/ft) and the other is SandyNet's data center (160 sq/ft). In addition, the network is being designed for future likely interconnection points with local providers. We are currently in negotiations with several local and regional providers which include collocation facilities, and the middle mile path was planned to be within one block of most central offices of local telecom providers. | None at this time. | None at this time. | Clackamas, County of | 101 | 11 | 3 | 0 | 20 | 51 |  | 18 | 43 | 2 | 249 | 1) No agreements completed. 2) One public last mile provider is using the fiber (City of Sandy’s broadband utility (SandyNet), which is a partner in our grant). No Service Agreements yet with a private provider, but there are about 10 Non-Disclosure agreements currently in place. We are engaged in multiple, ongoing discussions with local and regional service providers. Based on those conversations, we do not expect the first signed agreement with a private provider until construction of both fiber rings are completed, which is projected to be in Q1 2013. 3) No requests have been denied. | N/A as we only offer dark fiber and not any lit service. | TRUE
NT10BIX5570079 | 2013 | $45,773 | Consistent with baseline ( it is a decrease of 2.4% from the baseline of $46,899) | N/A | N/A. The project will not directly serve any households or businesses. | N/A | N/A. This was not reported in Baseline. This project only offers dark fiber so does not have subscribers. | 10 GBPS | Consistent with Baseline | 10 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | 1 GBPS | Consistent with Baseline | The estimated average increase to CAIs is between 900mb-1Gig. Generally, schools and institutions of higher education were getting 100mb shared connections which were less than 100mb each. Generally, fire stations and county sites had T1s, which was 1.5mb, so the fiber resulted in almost full 1Gig increases. Typical basic off-the-shelf electronics provide a minimum of 1Gig service; some school districts are using 10Gig equipment. | N/A. This is a dark fiber project. No services are provided. | 7a. This is a dark fiber project and we will not be providing any services. We do not have any policies that limit bandwidth or traffic prioritization. 7b. No, and we have no way to limit or block customers. This is an open access, dark fiber project. The network is open to any service provider that wishes to connect. Once connected, the service provider can utilize the dark fiber network as needed to meet its needs. | N/A. This is a dark fiber project and we do not provide any lit services to the general public. Therefore, we have not had any subscribers drop our services. | 34205 | 273 | 2649 | 31283 | 0 | 0 | 0 | 1) Edge IT. We have a signed Service Level Agreement but no fiber has been wholesaled during the grant period. 2) Silver Star. We have a signed Service Level Agreement but no fiber has been wholesaled during the grant period. 3) Wave Broadband; 151.6 fiber miles leased. 4) Integra Telecom. We have a signed Service Level Agreement but no fiber has been wholesaled during the grant period. | 450 | 100 | 0 | 350 | Clackamas County owns 3 interconnect facility locations (hubs) at the Development Services Building (DSB) (200 sq/ft), North Station (150 sq/ft) and at Water Environmental Services (WES) (100sq/ft). All hubs are now operational and available. There are two other primary facilities with local providers. One is the Clackamas Educational Service District's data center (4,000 sq/ft) and the other is SandyNet's data center (160 sq/ft). In addition, the network is being designed for future likely interconnection points with local providers. We are currently in negotiations with several local and regional providers which include collocation facilities and the middle mile path is planned to be within one block of most central offices of local telecom providers. | None at this time. | None at this time. | Clackamas, County of | 101 | 11 | 3 | 0 | 20 | 51 |  | 18 | 43 | 2 | 249 | 1) One public last mile provider is using the fiber (City of Sandy’s broadband utility (SandyNet), which is a partner in our grant). We have 3 Service Level Agreements with Telecoms (Edge IT, Integra and Silver Star Telecom) but they are not utilizing any dark fiber before the end of the grant. Wave Broadband is a private last mile provider that is leasing fiber on the dark fiber network. 2) Clackamas County is currently in active negotiations with 5 other telecoms, all looking to connect and provide telecom services. 3) No requests have been denied. | N/A as we only offer dark fiber and not offer any lit service. | TRUE
NT10BIX5570080 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | OnWav has been working diligently to complete the Environmental Assessment to allow construction to begin. As a result, no service has yet been made available to community anchor institutions. | OnWav has been working diligently to complete the Environmental Assessment to allow construction to begin. As a result, no retail services have yet been made available. | OnWav has been working diligently to complete the Environmental Assessment to allow construction to begin. As a result, no retail services have yet been made available. However, at such time, OnWav will meet all Non-discrimination requirements. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - OnWav does not have any fiber components in its network. | 0 | 0 | 0 | 0 | OnWav currently leases space at the Freeze St. Tower which it already currently subleases some space to Solutions IT Consulting for collocation and Interconnection. More space is available for future Interconnection partners. | OnWav has not made any subcontracts or sub grants to small disadvantaged Businesses (SDB). | OnWav has a couple lessons learned that can be shared with other similar BTOP projects: - Delve into the details. Onwav's original deployment schedule needs to be amended as a result of the difficulties in solving an overlap issue with a BIP winner. OnWav approached the problem by initially mapping out the affected census blocks. This showed that descoping those blocks from OnWav's project would not have a meaningful impact, Final resolution is expected to be complete the first week of January. Resolving issues like these is best solved by examining the details. - Bring in experienced help. OnWav brought in outside help through an outside consulting firm to assist in project management, procurement and reporting for this project. That decision has allowed OnWav to continue maintaining its existing business while accelerating the deployment process. By taking advantage of the consultant's prior experience with BTOP requirements and network deployment, OnWav was able to augment its capabilities without increasing costs. | ONWAV INC. | 20 | 4 | 2 | 2 | 4 | 27 |  | 55 | 25 | 15 | 154 | - OnWav has spoken and is in negotiations with Celina Cable Company to provide them with backhaul, Internet, and Voice over Internet Protocol for their current customer base. - OnWav contacted Info-Ed regarding Onwav's ability to provide them with broadband access, backhaul, and Voice over Internet Protocol. | - OnWav is currently negotiating to replace its existing internet backhaul agreement. Currently there are two potential candidates: Deltacom and IRIS Networks. The new connection will provide more capacity and redundancy options. | TRUE
NT10BIX5570080 | 2011 | 0 | OnWav signed an IRU to acquire 190.44 miles of dark Middle Mile fiber for a total cost of $2,079,604.80. However, as this is all existing fiber so far, This section does not apply. | N/A | OnWav has not yet finished deployment of it's Last Mile wireless network. As a result, no homes are passed at this time. The initial households passed are expected to be turned up Q2 or Q3 2012 | N/A | OnWav has not yet finished deployment of it's Last Mile wireless network. As a result, there are no subscribers currently on the grant network. The initial households passed are expected to be turned up Q2 or Q3 2012. | 1 Gbps | OnWav anticipates being able to provide at least 1 Gbps. Once the network is closer to completion, OnWav expects to adjust this number upwards. | 10 Mbps / 2Mbps | OnWav has not yet finished deployment of it's Last Mile wireless network. OnWav anticipates being able to provide 10 Mbps / 2 Mbps. | N/A | OnWav has not yet finished deployment of it's Last Mile wireless network. As a result, OnWav does not yet have any customers on the Middle Mile Network. OnWav anticipates being able to provide at least 130 Mbps. | N/A | OnWav has not yet finished deployment of it's Last Mile wireless network. As a result, OnWav does not yet have any customers on the Last Mile Network. OnWav anticipates providing an average of 8 Mbps / 1.5 Mbps. | N/A. OnWav's network is still under construction and no sites have yet been turned up. As a result, no service has yet been made available to community anchor institutions. | N/A. OnWav's network is still under construction and no sites have yet been turned up. As a result, no retail services have yet been made available. However, at such time, OnWav will meet all Non-discrimination requirements. | N/A. Policies under development. OnWav's network is still under construction and no sites have yet been turned up. As a result, no retail services have yet been made available. However, at such time, OnWav will meet all Non-discrimination requirements. OnWav has an Acceptable Use Policy which is posted on its website. | N/A | 418 | 0 | 0 | 381 | 37 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | OnWav currently leases space at the Freeze St. Tower (with non-grant funds) which it already currently subleases some space to Solutions IT Consulting for collocation and Interconnection. More space is available for future Interconnection partners. | OnWav has not made any subcontracts or sub grants to small disadvantaged Businesses (SDB). | OnWav has a couple lessons learned that can be shared with other similar BTOP projects: - Plan plenty of time for your RFP processes. Invariably, you will find that there are additional technical questions which need to be answered based on the RFP responses received, and you want to ensure you are not short-changing yourself by providing yourself insufficient time to review the responses and ask for clarifications from bidders. - Partner with local organizations. OnWav's new relationship with the local telephone cooperative has allowed it access to acquire dark fiber for the backhaul between it's tower locations. This backhaul will provide higher capacity and reliability than the microwave backhaul solution OnWav would need to deploy without the cooperation of the telephone cooperative. | ONWAV INC. | 20 | 4 | 2 | 2 | 4 | 27 |  | 55 | 25 | 15 | 154 | OnWav is still in negotiation with wholesalers as well as last mile providers for interconnection, but has not yet completed any agreements. OnWav has not denied any requests for interconnection. | OnWav is still in negotiation with wholesalers as well as last mile providers for interconnection, but has not yet completed any agreements. OnWav has not denied any requests for interconnection. | TRUE
NT10BIX5570080 | 2012 | N/A | OnWav signed an IRU to acquire 190.44 miles of dark Middle Mile fiber for a total cost of $2,079,604.80. However, as this is all existing fiber so far, This section does not apply. | $188.04 | OnWav has not yet finished deployment of it's Last Mile wireless network. So far two markets have been deployed. The direct cost of deployment at these sites is $243,705. There are 1296 households in Jamestown and Allardt, for an average cost of $188.04 per household passed | N/A | OnWav has not yet finished deployment of it's Last Mile wireless network. So far two markets have been deployed. The direct cost of deployment at these sites is $243,705. OnWav does not yet have any households subscribers. As a result, this section does not apply. | 1 Gbps | OnWav is capable of offering service as high as 1Gbps. OnWav has not actively marketed this speed tier, but is available if approached. | 12 Mbps / 2Mbps | OnWav highest offered service tier is currently 12 Mbps download with 2 Mbps upload. | 460Mbps | OnWav currently measures approximately 460Mbps Down and 230 Mbps Up as an average speed on the middle mile portion of the network. However, there is not currently sufficient traffic on the network to guage this value with complete confidence. | 8 Mbps / 1 Mbps | Based on a combination of the average speed tier selected by customers and an average of the performance supplied by the network. | OnWav is currently offering CAIs free service as a backup to their existing service. As a result, while there has been no increase in broadband speed for these providers, the reliability and redudency of their service has significantly improved as they now have two sources of Internet access In the event of a failure of service to their primary access, | OnWav is currently only offering Internet services to CAI customers. In the future OnWav plans to offer backup VoIP lines to all customers as well. | Currently OnWav is only offering last mile customers speed tiers as backup service to their primary Internet service. As a result, OnWav is throttling customers to provide service within their relevant speed tier. Other than the aforementioned speed tier limitations, OnWav is not limiting or blocking customer from accessing any Lawful content, service, service provider or applications. Nor has OnWav prevented any consumers from attaching any legal device to the network. | No OnWav grant customers have dropped the broadband service provided through this project (0% churn). | 418 | 381 | 0 | 0 | 37 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | OnWav currently leases space at the Freeze St. Tower (with non-grant funds) which it already currently subleases some space to Solutions IT Consulting for collocation and Interconnection. More space is available for future Interconnection partners. | OnWav has not made any subcontracts or sub grants to small disadvantaged Businesses (SDB). | OnWav has a couple lessons learned that can be shared with other similar BTOP projects: - Construction projects can take a long time to pass various governmental regulatory requirements (FAA, FCC, etc.). But once construction starts it can move extremely quickly Towers can take 6 months of regulatory filings, and then be built in the matter of weeks. - Repeat and Reiterate your Environmental Special Award conditions to your internal teams, vendors and subcontractors on a regular basis, both verbally as well as in writing Individuals and teams who are not dealing with them on a regular basis can easily forget, or mis-remember details. Repetition helps ensure memory and compliance in the field. | ONWAV INC. | 20 | 4 | 2 | 2 | 4 | 27 |  | 55 | 25 | 15 | 154 | OnWav has signed two agreements with last mile wholesalers to provide wholesale service through them. No additional agreements are currently under negotiation. OnWav has not denied any requests for interconnection. | OnWav has signed two agreements with last mile wholesalers to provide wholesale service through them. No additional agreements are currently under negotiation. OnWav has not denied any requests for interconnection. | TRUE
NT10BIX5570080 | 2013 | $10920 | OnWav signed an IRU for 215.955 miles of Middle Mile fiber (2 strands) including both existing dark fiber and newly constructed fiber, for a total cost of $2,358,228.60. OnWav's cost per mile of fiber was $10,920 | $182.51 | The direct cost of deployment at all six last mile sites is $833,722. There are 4567 households in OnWav's Service Area, for an average cost of $182.51 per household passed | N/A | The direct cost of deployment at all six last mile sites is $833,722. OnWav does not have any households subscribers. As a result, this section does not apply. | 1 Gbps | OnWav is capable of offering service as high as 1Gbps. OnWav has not actively marketed this speed tier, but is available if approached. | 16 Mbps / 2 Mbps | OnWav highest offered service tier is currently 16 Mbps download with 2 Mbps upload. | 460 Mbps | OnWav currently measures approximately 460Mbps Down and 230 Mbps Up as an average speed on the middle mile portion of the network. However, because the CAIs current use the service primarily as backup, there is not currently sufficient traffic on the network to gauge this value with complete confidence. | 8 Mbps / 1 Mbps | Based on a combination of the average speed tier selected by customers and an average of the performance supplied by the network. | OnWav is currently offering CAIs free service as a backup to their existing service. As a result, while there has been no increase in broadband speed for these providers, the reliability and redudency of their service has significantly improved as they now have two sources of Internet access In the event of a failure of service to their primary access, | OnWav is currently only offering Internet services to CAI customers. In the future OnWav plans to offer backup VoIP lines to all customers as well. | Currently OnWav is only offering last mile customers speed tiers as backup service to their primary Internet service. As a result, OnWav is throttling customers to provide service within their relevant speed tier. Other than the aforementioned speed tier limitations, OnWav is not limiting or blocking customer from accessing any Lawful content, service, service provider or applications. Nor has OnWav prevented any consumers from attaching any legal device to the network. | Two of the locations OnWav had previously listed as served CAIs are no longer being listed as served CAIs by OnWav: One has since closed and was removed from our CAI list in a September 2013 CAI Change AAR. The other had some uncertainty of its current operational status as a valid CAI and in order to remain conservative it was also removed in the September 2013 AAR. As a result, we are not reporting them as subscribers. OnWavâ€™s final total subscribers are 154 CAIs (126 from Q2 2013, minus 2 dropped, plus 30 added Q3 2013) | 432 | 432 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | OnWav currently leases space at the Freeze St. Tower (with non-grant funds) which it already currently subleases some space to Solutions IT Consulting for collocation and Interconnection. More space is available for future Interconnection partners. OnWav also leases rackspace in Gainesboro from Twin Lakes Telephone Cooperative for its Core Network Equipment and Internet Access. | OnWav has not made any subcontracts or sub grants to small disadvantaged Businesses (SDB). | OnWav has a couple lessons learned that can be shared with other similar BTOP projects: - Make sure to schedule a meeting between your Operations teams and Accounting Department to ensure that expenses and invoices are being booked to the correct accounts. Many vendor invoices are not explicit on what they are for and it's important to ensure that equipment is being booked to the correct account so it can be depreciated at the correct rate. - Document everything as soon as possible after work is complete. The longer you wait the harder it is for those involved to remember the details of the project as it happened. | ONWAV INC. | 20 | 4 | 2 | 2 | 4 | 27 |  | 55 | 25 | 15 | 154 | OnWav has signed two agreements with last mile wholesalers to provide wholesale service through them. No additional agreements are currently under negotiation. OnWav has not denied any requests for interconnection. | OnWav has signed two agreements with last mile wholesalers to provide wholesale service through them. No additional agreements are currently under negotiation. OnWav has not denied any requests for interconnection. | TRUE
NT10BIX5570081 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No Community Anchors have been installed or upgraded during this reporting period, consistent with the Baseline Plan. | No retail services have been offered as of the end of this reporting period, consistent with the Baseline Plan. | DC-CAN will provide quality-of-service capabilities. As part of District of Columbia Government, neither OCTO nor DC-NET have ever blocked lawful content to any subscriber. For DC-CAN, OCTO and DC-Net have no intention of blocking lawful content for any reason, except as required by law. | No subscribers have dropped broadband service. | 33120 | 0 | 0 | 0 | 33120 | 0 | 0 | Not applicable, as no dark fiber has been, or will be, offered to wholesale subscribers. | 4000 | 4000 | 0 | 0 | District of Columbia's Office of the Chief Technology Officer (OCTO) currently has a telecommunications, fiber and broadband operation providing services to District of Columbia Government Agencies, operating under the "DC-Net" program name. DC-Net plans ten (10) collocation sites dedicated to DC-CAN use, estimated at approximately 400 square feet per site. Of these ten (10) sites, DC-Net currently operates and supports electronics at eight (8) of these sites; the other two sites are either under construction or are under lease negotiation currently. Once fully operational, seven (7) of the ten (10) DC-CAN sites will be owned by DC Government; the remaining three (3) will be leased. | No sub-contracts or sub-grants have been made as of the end of this reporting period. | As standard procedure, DC-Net reviews equipment specifications regularly, and ensures that it exploits more current technologies. DC-Net finds technology continues to evolve at a rapid pace, providing greater capabilities for the project, once project is deployed. DC-Net recommends periodically review its bill of materials and configuration, at community anchors and at mega-POP sites. | District of Columbia Government | 52 | 23 | 4 | 8 | 61 | 60 |  | 0 | 48 | 35 | 291 | N/A. No Inter-connection Agreements executed this period, consistent with accepted Baseline Plan. None are currently being negotiated, and no requests have been denied. | N/A. No Peering and Transit Agreements executed this period, consistent with accepted Baseline Plan. None are currently being negotiated, and no requests have been denied. | TRUE
NT10BIX5570081 | 2011 | 51166 | Through Dec 31, 2011, DC-CAN experience suggests a cost per fiber mile of approximately $51,166. Total costs for 45 miles of fiber are $2.3 million, with a resulting cost per fiber mile = $51,166. OCTO DC-Net has been able to procure equipment, materials and services at favorable rates when compared to the original budget. | 0 | DC-CAN is only a middle-mile project. | 0 | DC-CAN is only a middle-mile project. | 100000 | Maximum advertised speed is 100 Gbps (or 100,000 Mbps). This exceeds the maximum 40 Gbps speed offered in the baseline plan, as technology improvements by procurement date provided more powerful equipment, permitting DC-CAN to build this more powerful infrastructure. | 0 | DC-CAN is only a middle-mile project. | 10 | Average broadband speed provided is 10 Mbps. Consistent with baseline. | 0 | DC-CAN is only a middle-mile project. | Typical customers have seen their broadband speed improve to 10 Mbps, as a consequence of moving to DC-CAN service offerings. Most customers have upgraded to DC-CAN from T-1 service, or 1.54 Mbps. In addition to more than six-fold increase in broadband speeds, their monthly costs have declined. | As of December 31, 2011, no retail services have been offered. | DC-CAN limits bandwidth based on the bandwidth provisioned and requested by the customer. No, DC-Net (or DC-CAN have not limited or blocked consumers from accessing lawful content. | No subscribers have dropped broadband service. | 33206 | 7614 | 0 | 0 | 25592 | 0 | 0 | For DC-CAN, no dark fiber has been, or will be, offered to wholesale subscribers. | 1200 | 1200 | 0 | 0 | District of Columbia's Office of the Chief Technology Officer (OCTO) currently has a telecommunications, fiber and broadband operation providing services to District of Columbia Government Agencies, operating under the "DC-Net" program name. DC-Net plans fourteen (14) collocation sites dedicated to DC-CAN use, estimated at approximately 400 square feet per site. Of these fourteen (14) sites, DC-Net currently operates and supports electronics at eight (8) of these sites; the other sites are either under construction or are under lease negotiation currently. Once fully operational, ten (10) of the fourteen (14) DC-CAN sites will be owned by DC Government; the remaining four (4) will be leased. | DC-CAN has made no sub-grants or sub-contracts to any economically-disadvantaged small business concerns, as defined by Section 8(a) of the Small Business Act. DC-CAN does not intend to make any in the future. | As standard procedure, DC-Net reviews equipment specifications regularly, and ensures that it exploits more current technologies, as they are commercially available, and proved viable through testing. DC-Net finds technology continues to evolve at a rapid pace, providing greater capabilities for the project, once project is deployed. DC-Net recommends periodically review its bill of materials and configuration, at community anchors and at mega-POP sites. | District of Columbia Government | 52 | 23 | 4 | 8 | 61 | 60 |  | 0 | 48 | 35 | 291 | N/A | N/A | TRUE
NT10BIX5570081 | 2012 | 53000 | Through Dec 31, 2012, DC-CAN has spent $6.88 million in outside plant costs. With one hundred thirty (130) miles fiber installed, that results in a cost per mile of just under $53,000 per installed fiber mile. OCTO DC-Net has been able to procure equipment, materials and services at favorable rates when compared to the original budget. | 0 | DC-CAN is solely a middle-mile project. | 0 | DC-CAN is solely a middle-mile project. | 100000 | Maximum advertised speed is 100 Gbps (or 100,000 Mbps). This exceeds the maximum 40 Gbps speed offered in the baseline plan, as technology improvements by procurement date provided more powerful equipment, permitting DC-CAN to build this more powerful infrastructure. | 0 | DC-CAN is solely a middle-mile project. | 10 | Average broadband speed provided is 10 Mbps. Consistent with baseline. | 0 | DC-CAN is solely a middle-mile project. | Typical customers have seen their broadband speed improve to 10 Mbps or 50 Mbps, as a consequence of moving to DC-CAN service offerings. Most customers have upgraded to DC-CAN from T-1 service, 1.54 Mbps service, or digital subscriber line (DSL) service. In addition to more than six-fold increase in broadband speeds, their monthly costs have declined. | As of December 31, 2012, no retail services have been offered. None are planned. | DC-CAN limits bandwidth based on the bandwidth provisioned and requested by the customer. No, DC-Net (or DC-CAN have not limited or blocked consumers from accessing lawful content. | No subscribers have dropped DC-CAN broadband services. | 33206 | 16412 | 0 | 0 | 16794 | 0 | 0 | For DC-CAN, no dark fiber has been, or will be, offered to wholesale subscribers. | 3600 | 3600 | 0 | 0 | District of Columbia's Office of the Chief Technology Officer (OCTO) currently has a telecommunications, fiber and broadband operation providing services to District of Columbia Government Agencies, operating under the "DC-Net" program name. DC-Net plans fourteen approved (14) collocation sites dedicated to DC-CAN use, estimated at approximately 400 square feet per site. Of these fourteen (14) sites, DC-Net currently operates and supports electronics at nine (9) of these sites; the other sites are either under construction or are under lease negotiation currently. Once fully operational, ten (10) of the fourteen (14) DC-CAN sites will be owned by DC Government; the remaining four (4) will be leased. | DC-CAN has made no sub-grants or sub-contracts to any economically-disadvantaged small business concerns, as defined by Section 8(a) of the Small Business Act. DC-CAN does not intend to make any in the future. | As standard procedure, DC-Net reviews equipment specifications regularly, and ensures that it exploits more current technologies, as they are commercially available, and proved viable through testing. DC-Net finds technology continues to evolve at a rapid pace, providing greater capabilities for the project, once project is deployed. DC-Net recommends periodically review its bill of materials and configuration, at community anchors and at inter-connection sites. | District of Columbia Government | 52 | 23 | 4 | 8 | 61 | 60 |  | 0 | 48 | 35 | 291 | DC-CAN has executed one (1) inter-connection agreement with a local high-speed internet service provider. The partner entity, DC Access, is a notfor- profit organization based in the District of Columbia; the intent of the agreement is for DC Access to provide last mile services to individuals and corporations. DC-CAN is currently in negotiations with two high-speed internet providers to offer last-mile services directly to households and businesses. DC-CAN has denied no requests for inter-connection. | N/A | TRUE
NT10BIX5570081 | 2013 | 38,719.10 | Through Dec 31, 2013, the end of the grant closeout period, DC-CAN has spent $8,154,241.88 in outside plant costs. With approximately two hundred eleven (211) linear miles of fiber installed, that results in a cost per mile of $38,719 per installed fiber mile. | 0 | DC-CAN is solely a middle-mile project. | 0 | DC-CAN is solely a middle-mile project. | 100000 | Maximum advertised speed is 100 Gbps (or 100,000 Mbps). This exceeds the maximum 40 Gbps speed offered in the baseline plan, as technology improvements by procurement date provided more powerful equipment, permitting DC-CAN to build this more powerful infrastructure. | 0 | DC-CAN is solely a middle-mile project. | 10 | Average broadband speed provided is 10 Mbps. Consistent with baseline. | 0 | DC-CAN is solely a middle-mile project. | Typical customers have seen their broadband speed improve to 10 Mbps or 50 Mbps, as a consequence of moving to DC-CAN service offerings. Most customers have upgraded to DC-CAN from T-1 service, 1.54 Mbps service, or digital subscriber line (DSL) service. In addition to more than six-fold increase in broadband speeds, their monthly costs have declined. | As of the end of the grant closeout period, December 31, 2013, no retail services have been offered. None are planned. | DC-CAN limits bandwidth based on the bandwidth provisioned and requested by the customer. No, DC-Net have not limited or blocked consumers from accessing lawful content. | No subscribers have dropped DC-CAN broadband services. | 26459 | 26459 | 0 | 0 | 0 | 0 | 0 | For DC-CAN, no dark fiber has been, or will be, offered to wholesale subscribers. | 5400 | 5400 | 0 | 0 | District of Columbia's Office of the Chief Technology Officer (OCTO) currently has a telecommunications, fiber and broadband operation providing services to District of Columbia Government Agencies, operating under the "DC-Net" program name. DC-Net has installed fourteen approved (14) collocation sites dedicated to DC-CAN use, estimated at approximately 400 square feet per site. Of these fourteen (14) sites, seven (7) are owned by DC Government, and the final seven (7) are leased. | Throughout the grant period, DC-CAN made no sub-grants or sub-contracts to any economically-disadvantaged small business concerns, as defined by Section 8(a) of the Small Business Act. DC-CAN does not intend to make any in the future. | As standard procedure, DC-Net reviews equipment specifications regularly, and ensures that it exploits more current technologies, as they are commercially available, and proved viable through testing. DC-Net finds technology continues to evolve at a rapid pace, providing greater capabilities for the project, once project is deployed. DC-Net recommends periodically review its bill of materials and configuration, at community anchors and at inter-connection sites. | District of Columbia Government | 52 | 23 | 4 | 8 | 61 | 60 |  | 0 | 48 | 35 | 291 | DC-CAN has executed four (4) inter-connection agreement with local high-speed internet service providers. All four entities have presence within the District of Columbia; the intent is for all four to provide last-mile services to individuals and corporations. Through the entire grant period, DC-CAN has denied no requests for inter-connection. | N/A | TRUE
NT10BIX5570082 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | None this period | None this period | None this period | None this period | 0 | 0 | 0 | 0 | 0 | 74304 | 107616 | None this period | 0 | 0 | 0 | 0 | None this period | None this period | Open, clear, timely and consistent communication with NTIA FPO and other Federal contacts has led to streamlined addressing of issues that have surfaced during the first year of this project. Following clear PMBOK practices and regular (weekly and monthly) project management meetings with both prime recipients and sub-recipients allows for the entire project team to remain current with project activities and challenges as they surface. Recommend early public relations on BTOP projects. Would like to leverage other communications plans from other BTOP projects in the future. We have been meeting with other local projects to review challenges and leverage expertise. With the project having been awarded in July of this first year, there are a number of practices that are beginning to emerge as best and will likely appear in this area in subsequent Annual Reports. | University System of New Hampshire | 358 | 306 | 13 | 41 | 477 | 232 | 298 | 298 | 50 | 0 | 1775 | None this period | None this period | TRUE
NT10BIX5570082 | 2011 | 0 | 0 at this time due to current construction phase. | 0 | 0 at this time due to current construction phase. | 0 | 0 at this time due to current construction phase. | 10GB | No variance from plan. | 0 | 0 at this time due to current construction phase. | 1.3GB | No variance from plan. | 0 | 0 at this time due to current construction phase. | Average broadband speed is estimated to increase to 1.3 GB which is based on averaging their current speed factored with an estimated 20x increase in speed. | No retail services were provided in 2011. | 7a. We are utilizing BTOP optical network equipment to light fiber between the University of New Hampshire and Keene State College. The equipment is dividing a 10 GB wave into 1 GB VLANS. Bandwidth is being allocated for internet services, video conferencing, and disaster recovery. We use Quality of Service (QOS) for voice and video services. 7b. No consumers have been limited or blocked from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | N/A | 135936 | 0 | 0 | 17280 | 0 | 0 | 118656 | No leasing in 2011. | 0 | 0 | 0 | 0 | Colocation space is owned. | None | a. Communicate frequently with state and local officials frequently on the project status and benefits it can bring to the region. Focus on whatâ€™s important, economic, educational, and medical seem to be the hot buttons for our project. b. Work closely with the state regulatory groups. We meet quarterly to provide updates both positive and negative. In challenging situations we make every effort to work through the problems independently first before reaching out to the regulating authorities. They appreciate the efforts and if it does come time to actually meet over an issue we find them to be more receptive to our project. c. Weâ€™ve worked very hard on our relationships with the local utility companies. Making adjustments when necessary to accommodate their processes and communicating regularly helps to keep things moving and provides a level of visibility necessary for such a big project. | University System of New Hampshire | 358 | 306 | 13 | 41 | 477 | 232 | 298 | 298 | 50 | 0 | 1775 | 1. Interconnection agreements are in place with Keene State College and DSCI corporation. 2. We are currently working on interconnection agreements with Plymouth State College, Dartmouth College, NH Community College System, Granite State College, UNH Law in Concord, and Northern Community Investment Organization. 3. We have not denied requests for interconnection. | N/A | TRUE
NT10BIX5570082 | 2012 | 40,000 | Estimated at 40K due to fixed price contract with New Hampshire Optical Systems. Actual average is trending toward 53K per mile. Some sections of make-ready have cost over 250K per mile. | 0 | No households available for subscription in 2012 as network is under construction. Construction occurred later than baseline estimates due to delays in match funding and longer than expected make ready time frames. | 0 | No subscribers in 2012 as network is under construction. Construction occurred later than baseline estimates due to delays in match funding and longer than expected make ready time frames. | 10GB | No variance from plan. | 1GB | No variance from plan. | 1.3GB | No variance from plan. | 0 | 0 at this time due to current construction | Average broadband speed is estimated to increase by 9.5Gbps, approximately a 20x increase. Keene State College aggregate 400Mbps to 10Gbps, delta = 9.6 Gbps UNH aggregate 600Mbps to 10Gbps, delta = 9.4 Gbps | New Hampshire Optical Systems provides wholesale dark fiber for lease on a fiber mile basis. Pricing plan is attached. NH FastRoads will provide retail last mile services but is still under construction and pricing plans have not yet been established. | 7a. USNH is using BTOP Optical network equipment to light fiber between the University of New Hampshire and Keene State College. The equipment is dividing a 10GB wave into 1GB VLANs. Bandwidth is being allocated for Internet services, video conferencing, and disaster recovery. We use Quality of Service (QOS) for voice and video services. 7b. No consumers have been limited or blocked from accessing lawful content, service, service provider, or application or prevented any consumers from attaching any legal device to the network. | 0 | 185276 | 2659 | 19152 | 74503 | 7260 | 3456 | 78246 | USNH 9108 fiber miles Company A 1050 fiber miles Company B 1000 fiber miles Company C 50 fiber miles | 8 | 8 | 0 | 0 | These locations are collocation facilities for the USNH fiber leased from NHOS. There will be additional interconnect points as NHOS fiber is completed and becomes available for lease but this was not the case as of December 31, 2012. DSCI Corp (commercial co-lo facility), 1 Sundial (ISP/carrier hotel), Manchester, NH - UMAINE is leasing a rack at DSCI and UNH has an agreement with UMAINE to share use of that rack and has installed BTOP DWDM equipment in that rack. This site is currently utilized to provide the USNH interconnection between the University of New Hampshire data center and the Keene State College data center. ADDITIONAL RESPONSE TO Q11 - The remaining two sites below are owned by the University System of New Hampshire and are not available for commercial co-location use. BTOP DWDM equipment is installed in one rack (4 sq ft) at each facility: Keene State College Data Center, 229 Main St, Keene, NH University of New Hampshire Data Center, 1 Leavitt Lane, Durham, NH | None | Project recommends utilizing current and very conservative make-ready costs estimates and timelines because: Make-ready time frames have exceeded estimates. This is due to a combination of factors including some areas having more make-ready needed than originally expected (especially in urban areas, highway crossings and major route intersections). Other factors include the number of third party make-ready moves that need to occur and higher than expected costs to complete make-ready. The process to coordinate third party moves was more complex than expected and we have worked closely with the New Hampshire Public Utilities Commission and state and federal officials to work around obstacles that have arisen during construction. | University System of New Hampshire | 358 | 306 | 13 | 41 | 477 | 232 | 298 | 298 | 50 | 0 | 1775 | 1. NHOS has dark fiber IRU agreements with 4 entities. Three of the entities have requested confidentiality agreements. The fourth entity is the University of New Hampshire. 2. NH FastRoads has been in negotiations with three Internet service providers and is finalizing an agreement with a network service provider, but no agreements were signed in 2012. New Hampshire Optical Systems is currently negotiating agreements for use of dark fiber and is working to connect the NH BTOP Network with BTOP assets in Maine, Massachusetts, and Vermont. 3. No one has been denied requests for interconnection. | None | TRUE
NT10BIX5570082 | 2013 | $49,639 | Baseline was $33,663 The make-ready costs for aerial construction were much higher than anticipated. The Department of Transportation (DOT) portion of the project constructed 20 miles of fiber in conduit along Interstate 93 at a significantly higher cost than the aerial construction. Cost/MILE: NHOS $41,176 (592 miles: Route mileage was derived from GIS middle mile and lateral segment â€œas builtsâ€. Some overlap of middle mile and lateral miles exists due to the tracking mechanism within the GIS system. ) DOT averaged $299,968 per mile (20 miles). | $3,433 | Baseline was $1,770. The original baseline projection was calculated using only the two Last Mile communities, Enfield and Rindge. In reality, the entire NH FastRoads portion of this project is Last Mile. There are 1,266 households passed, 363 CAIs passed, and 254 businesses passed totalling 1,883 "households" passed. Cost for labor ($2,066,734), equipment ($2,150,902) and site preparation expenses ($2,247,067) total $6,464,703. This total cost of $6,464,703 divided by 1,883 last mile connections equals $3,433 per connection. Throughout this project we experienced Make Ready costs that exceeded the original budgeted amounts. These extra costs explain the difference between baseline and actual. Note - If you include the prorated average cost for 48 strands of the middle mile fiber utilized by NH FastRoads, the average cost per household passed jumps to $4,610. Theses costs are already included in the Average cost per new mile (Middle Mile) question. | $29,655 | Baseline was $8,681. At the end of 2013, 162 residents, 47 CAIs, and 9 businesses (218 total) subscribed to the NH FastRoads Last Mile network. Total cost ($6,464,703)/218=$29,655). Baseline estimates assumed subscribers would start taking service in January 2013. Due to construction delays, the network was not available to subscribers until the end of September 2013. Had the network been ready in January 2013 and, assuming the same subscription rate as Q4 2013, the average cost per subscriber could have been been much lower ($6,464,703/720 = $8,979). | 10Gbps | Baseline 10Gbps. No variance. | 1Gbps | Baseline was 100 Mbps. At the time the baseline was calculated, NH FastRoads assumed the maximum speeds would be 100 Mbps. The capabilities of the equipment ultimately purchased under the grant now allow an improved maximum of 1 Gbps. | 1.9Gbps | Baseline was 10Gbps The network has the capability of multiple 10Gbps connections, but is currently provisioned for an average of 1.9Gbps. | 20Mbps | Baseline was 100Mbps. The last mile calculations are based on NH FastRoads only. Current customers taking service have opted for an average of 20Mbps. Network construction delays reduced the number of subscribers that were able to be connected before grant closure. Since the contracts for the higher speeds typically taken by CAIs and businesses take longer to complete than requests for residential service, the higher speed connections were not realized in time for this calculation. | The CAI broadband speeds increased from a pre-grant average of 16 Mbps to the grant completion average of 104 Mbps resulting in an overall average increase of 88 Mbps. Dartmouth College, Keene State College, Plymouth State University, and the University of NH already had high bandwidth connections prior to the grant (400Mbps to 1.5 Gbps). These would have significantly skewed the data so they were not included in the above computed averages. These four institutions went from an average of 813 Mbps to an average of 8.625 Gbps. If included in the overall averages, the result would be a pre-grant average of 61 Mbps to the grant completion average of 584 Mbps resulting in an average increase of 523 Mbps. Many of the pre-grant speeds are estimates based on the best information we have available. It should also be noted that many of the pre-grant connections were asymmetrical and have been replaced with symmetrical connections. | NH FastRoads, the last-mile component, provides last mile retail services via resellers. The wholesale base prices per subscriber for these resellers noted in the FastRoads section of attached price list. USNH is leasing 12 strands of fiber from NHOS and is providing lit service to education CAIs at between 50Mbps and 10Gbps. The pricing is noted in the University System of New Hampshire section of the attached price list. | 7a. Each of the components of the project provide some type of bandwidth limitations and traffic prioritization corresponding to the client being served: USNH has provisioned its network into multiple 10 Gbps waves and multiple 1 Gbps VLANs. Bandwidth is being allocated for Internet services, video conferencing, and disaster recovery. USNH uses Quality of Service (QoS) for voice and video services. The NHSafeNet closed public safety microwave network prioritizes traffic with highest priority QoS for the NH Department of Safety and NH Public Television. Each of the stakeholders have defined peak information rates to ensure that there is no chance of oversubscribing. NH FastRoads prioritizes its traffic using priority bits on the network. VoIP and Point-to-Point or Point-to-Network Traffic have the highest priority, followed by business class traffic, leaving residential traffic as best effort. 7b. No entities have been limited or blocked from accessing lawful content, service, service provider, or application or prevented any consumers from attaching any legal device to the network. NH FastRoads Acceptable Use policies indicate use must be lawful. | No dropped subscribers or turnover. | 142664 | 15700 | 19713 | 107251 | 0 | 0 | 0 | [REDACTED] | 152 | 152 | 0 | 0 | The 750 miles of middle-mile fiber infrastructure is owned and operated by sub-awardee, New Hampshire Optical Systems, LLC (NHOS). Access to fiber strands in the NHOS cable infrastructure is available virtually anywhere along the middle-mile route via aerial or manhole splicing. The NHOS cable infrastructure has splice cases at a maximum of every 20,000 feet or closer. Service Providers can access this network at DSCI in Manchester, NH, and BayRing Communications in Portsmouth. The last mile component, NH FastRoads, is located in the Keene Technology Center collocation facility and NH FastRoads provides rack space to their own Service Providers at this location. NH FastRoads is also located in the Hanover, NH Community and Senior Center building. The agreement with the Town of Hanover is not exclusive, and on request, the Town would consider allowing other service providers access to the collocation space. NH FastRoads utilized BTOP funds to provide leasehold improvements to the Keene technology Center noted above. NH FastRoads also utilized BTOP funds to provide leasehold improvements at a HUB location in the ATA Construction, LLC building in Rindge, New Hampshire. (Note - this site is not an interconnection facility) | N/A | 1) Make-ready in New Hampshire is significantly more expensive and takes much longer than expected. We learned through this project that the pole attachment processes and regulations are not clearly defined which led to both delays and cost overruns. This process will discourage build out for economic development purposes. Recruiting a business to your region requires a nimbleness that the current process does not support. 2) Work closely with the state regulatory groups and provide updates, both positive and negative. In challenging situations, we made every effort to work through the problems independently first before reaching out to the regulating authorities. They appreciate the efforts and if it does come time to actually meet over an issue, we find them to be more receptive to our project. 3) Communicate frequently with state and local officials frequently on the project status and benefits that it can bring to the region. Focus on whatâ€™s important--economic, educational, and medical seem to be the hot buttons for our project. 4) Weâ€™ve worked very hard on our relationships with the local utility companies. Making adjustments, when necessary, to accommodate their processes and communicating regularly helps to keep things moving and provides a level of visibility necessary for such a big project. 5) Open access networks are a new concept. Attracting service providers into this environment has been a challenge. However, it is with open access that the region finally has real competition. This competitive environment is bringing down pricing and making big broadband affordable and plentiful. 6) Although welcome on the open access network, incumbent carriers have chosen to overbuild this network with DSL instead of delivering services over the open access network. 7) To support the smaller networks, companies providing network operations, outside plant construction, and provisioning services would be helpful to save costs with economies of scale. 8) From a grant management perspective, we discovered that baselines would have been more accurate if they had been set after engineering was completed. 9) Some of the data requested during closeout would have been more easily delivered if we had known up front what was going to be required. It would have been easier to extract some of the data if tracking systems were put in place at the beginning of the project to categorize some of the items. | University System of New Hampshire | 358 | 306 | 13 | 41 | 477 | 232 | 298 | 298 | 50 | 0 | 1775 | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570084 | 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A | No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - No new BTOP network was physically deployed in calendar year 2010 | 0 | 0 | 0 | 0 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010. The only contract in 2010 that was issued was for the Environmental Assessment. The recipient was not a SDB entity. | Ensure that you have the correct and most recently updated forms for reporting and submission. Be open about all the issues you are experiencing, especially regarding the EA as it was an intensive process. You will face many obstacles that seem insurmountable but seek BTOP counsel in an effort to obtain clarity and direction. | Iowa Health System | 0 | 0 | 15 | 0 | 1535 | 105 |  | 26 | 0 | 0 | 1681 | N/A - No new BTOP network was physically deployed in calendar year 2010 | N/A - No new BTOP network was physically deployed in calendar year 2010 | TRUE
NT10BIX5570084 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | Iowa Health System (IHS)/Broadband, Inc. (BBI) have not provided pricing plans since construction and deployment have not begun. | Broadband, Inc. has not begun providing service, however, the network management policy does not limit or prioritize traffic up to the agreed purchased service level. No limits are imposed for lawful access or use of the network. | N/A | 6522 | 6100 | 0 | 0 | 224 | 198 | 0 | N/A | 2400 | 1720 | 0 | 680 | Iowa Health System owns the collocation facilities. | N/A | One lesson learned earlier on in the project was how quickly technology changes and planning for implementation to those changes can be lengthy. The continuously changing broadband pricing landscape has created challenges as the price for capacity of broadband may change dramatically from the time a recipient identifies competitor data for service offerings until the time revenue can be generated from customers receiving the improved BTOP funded broadband services. The need to continuously update data and the business model as a result of the increasing demand and reduced pricing landscape of broadband is a necessity to becoming successful as a business vs. the implementation component of the funded BTOP project. | Iowa Health System | 0 | 0 | 15 | 0 | 1535 | 105 |  | 26 | 0 | 0 | 1681 | Broadband, Inc. (BBI) is a subrecipient and subsidiary of Iowa Health System. Currently BBI has not entered any interconnection agreements, BBI is in negotiations for a middle mile transit agreement with one customer, and BBI has not denied any request for interconnection. Broadband, Inc. is currently in discussions with 14 potential customers to start working towards negotiations for agreements with customers. | Broadband, Inc. (BBI) is a subrecipient and subsidiary of Iowa Health System. Currently BBI has not entered any peering and/or transit agreements, BBI is in negotiations for a middle mile transit agreement with one customer, and BBI has not denied any request for peering and/or transit agreements. Broadband, Inc. is currently in discussions with 14 potential customers to start working towards negotiations for agreements with customers.N/A | TRUE
NT10BIX5570084 | 2012 | $10,000 | Deep urban construction and limited amounts of construction builds have increased the cost to obtain construction vendors in Iowa. Cost was also driven up due to the waiting time to obtain an EA and vendors waiting upon approval to start the small construction activities in rural Iowa as well. | N/A | N/A | N/A | N/A | 10G | No variance from baseline plan | N/A | N//A | 100M | No variance from Baseline Plan | N/A | N/A | N/A | Iowa Health System (IHS)/Broadband, Inc. (BBI) is working through pricing plans for retail services but currently has not started offering. | Broadband, Inc. network management policy does not limit or prioritize traffic up to the agreed purchased service level. No limits are imposed for lawful access or use of the network. | N/A | 6522 | 6100 | 198 | 0 | 224 | 0 | 0 | N/A | 2400 | 1720 | 0 | 680 | Iowa Health System owns the collocation facilities. | N/A | One lesson learned earlier on in the project was how quickly technology changes and planning for implementation to those changes can be lengthy. The continuously changing broadband pricing landscape has created challenges as the price for capacity of broadband may change dramatically from the time a recipient identifies competitor data for service offerings until the time revenue can be generated from customers receiving the improved BTOP funded broadband services. The need to continuously update data and the business model as a result of the increasing demand and reduced pricing landscape of broadband is a necessity to becoming successful as a business vs. the implementation component of the funded BTOP project. Two years into the BTOP project, construction costs have increased as a result of limited construction activities to build in different locations throughout Iowa and the waiting time for EA approvals have been a challenge as a result of the project modification to eliminate wireless towers and construct broadband fiber. | Iowa Health System | 0 | 0 | 15 | 0 | 1535 | 105 |  | 26 | 0 | 0 | 1681 | Broadband, Inc. (BBI) is a subrecipient and subsidiary of Iowa Health System. Currently BBI has entered into 7 interconnection agreements with last mile provider customers and BBI has not denied any request for peering and/or transit agreements. | Broadband, Inc. (BBI) is a subrecipient and subsidiary of Iowa Health System. Currently BBI has not entered into any peering agreements. BBI currently has 9 middle mile transit agreements with customers. | TRUE
NT10BIX5570084 | 2013 | $10,000 | Deep urban and longer rural fiber construction builds boring through rock were a direct result of increased construction costs. Cost was also driven due to longer than expected winter season that condensed the construction schedule. | N/A | N/A | N/A | N/A | 10G | No Variance from Baseline Plan | N/A | N/A | 100M | No Variance from Baseline Plan | N/A | N/A | N/A | Wholesale Internet Access Service provides managed access to Internet via Broadband Inc. facilities designed for small to mid sized internet service providers. Pricing attached. | N/A | N/A | 6522 | 6522 | 198 | 0 | 224 | 0 | 0 | N/A | 2400 | 1720 | 0 | 680 | Iowa Health System owns the collocation facilities. | N/A | One lesson learned earlier on in the project was how quickly technology changes and planning for implementation to those changes can be lengthy. The continuously changing broadband pricing landscape has created challenges as the price for capacity of broadband may change dramatically from the time a recipient identifies competitor data for service offerings until the time revenue can be generated from customers receiving the improved BTOP funded broadband services. The need to continuously update data and the business model as a result of the increasing demand and reduced pricing landscape of broadband is a necessity to becoming successful as a business vs. the implementation component of the funded BTOP project. Construction costs have increased as a result of limited construction activities to build in different locations throughout Iowa and the waiting time for EA approvals have been a challenge as a result of the project modification to eliminate wireless towers and construct broadband fiber. Construction costs continue to be limiting in how much fiber can be built to customers to continue these connections. This continues to be the difficulty when signing rural customers. | Iowa Health System | 0 | 0 | 15 | 0 | 1535 | 105 |  | 26 | 0 | 0 | 1681 | Cedar Falls Utilities US Secure Hosting Center Bellevue Municipal Utilities Enseva Data Center Mahaska Communications Group Osage Municipal Utilities FiberComm InfoBunker Harlan Municipal Utilities VS Enterprises City of Denison Professional Computer City of Maquoketa City of Charles City BBI has not denied any request for peering or transit agreements. | Broadband, Inc. (BBI) is a subrecipient and subsidiary of Iowa Health System. Currently BBI has not entered into any peering agreements. BBI currently has 14 middle mile transit agreements with customers. | TRUE
NT10BIX5570085 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No increase in broadband speed provided to community anchor institutions has been achieved. We are still completing the Environmental Assessment and negotiating a resolution of the overlap with NTIA. | N/A | VTel posts our terms of service and network managment policies on our website where customers can access them. We do not prevent consumers any lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to the network. We are committed to the spirit of the NOFA. | N/A | 18504 | 0 | 0 | 0 | 18504 | 0 | 0 | N/A | 544 | 9 | 9 | 526 | Network providers and/or customers can interconnect with VTel at the interconnection points listed in our BTOP Application. These locations include primarily third party collocation facilities/Central Offices. | No subcontracts or sub grants have been made to socially and economically disadvantaged small businesses. | One of the lessons learned is that it is a critical first step to quickly start on the environmental assessment portion of the project. It is also important that the process be handled by someone or an organization that has had experience with similar environmental issue and has the ability to properly coordinate with local, state and federal governmental organizations. | Vermont Telephone Company, Inc. | 55 | 11 | 3 | 10 | 27 | 1 |  | 6 | 11 | 1 | 125 | 0 Interconnection agreements entered into. 0 Interconnection agreements being negotiated 0 Interconnection agreements denied | 1 Peering Relationship entered into. VTel entered into a peering relationship with Telx Peering exchange at 60 Hudson Street, New York, NY 0 Peering or Transit Agreements being negotiated. 0 Peering or Tranist Agreements denied. | TRUE
NT10BIX5570085 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No increase in broadband speed provided to community anchor institutions has been achieved. Construction will begin in the 1st quarter of 2012. | N/A | VTel posts our terms of service and network management policies on our website where customers can access them. We do not prevent customers any lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to the network. We are committed to the spirit of the NOFA. | N/A | 18504 | 0 | 0 | 0 | 18504 | 0 | 0 | N/A | 544 | 27 | 27 | 490 | Network providers and/or customers can interconnect with VTel at the interconnection points listed in our BTOP Application. These locations include primarily third party collocation facilities/Central Offices. | No subcontracts or sub grants have been made to socially and economically disadvantaged small businesses. We are entering into a construction contract with a socially and economically disadvantaged small business. | As a result of our BTOP site visit in October, we have learned that in order to remain compliant with the final award agreement, it was necessary to make a few changes. Although construction is not scheduled to begin until the first quarter of 2012, it was necessary to increase the rate in which we were reaching out to community anchors. By doing that, we quickly became aware that there might be changes to the list proposed originally, and determined through the overlap process, based on many different factors including economic conditions, market competition from other providers, changes in location due to tropical storm Irene, etc. VTel also needed to adopt and document procedures to adequately comply with the financial management guidelines for the BTOP project. Processes are in place to identify allowable costs, however the policies needed to be clearly outlined, to ensure that BTOP guidelines are being followed. The last performance improvement plan that was identified concerned identifying that all BTOP terms and conditions be included in any contracts entered into during the NTIA grant period. We have made corrections to all existing contracts, and any new contracts are being reviewed by VTel's attorneys to make sure that they include all the necessary terms and conditions required. Several CAI's listed on the attached "Annual PPR CCI Addendum" have been stricken at the request of NTIA. Our understanding is that another BTOP funded project has included these and despite Vtel having built fiber prior to BTOP, these CAI's remain in the other BTOP project's scope. While VTel will not expend any grant funds to overbuild the fiber we've already placed, VTel's grant is also upgrading our network's overall speed and capacity. These pre-existing customers will receive improved service from VTel if they choose to remain our customers. | Vermont Telephone Company, Inc. | 55 | 11 | 3 | 10 | 27 | 1 |  | 6 | 11 | 1 | 125 | 0 Interconnection agreements entered. 0 Interconnection agreements being negotiated. 0 Interconnection agreements denied. We have 6 existing agreements with broadband wholesale and last mile providers whose connection will be upgraded as a result of this | 7 Peering Relationship entered into. 0 Peering or Transit Agreements being negotiated. 0 Peering or Transit Agreements denied. | TRUE
NT10BIX5570085 | 2012 | EST $35,000 | This is an estimate based on engineering, make ready, and construction costs. | 0 | N/A | 0 | N/A | 100 gb | No variance from base line. | 0 | N/A | 75mg | No variance from base line. | 0 | N/A | Although there may be increases in broadband speed, the final increase will not be measurable until the full network has been upgraded. | N/A | VTel posts our terms of service and network management policies on our website where customers can access them. We do not prevent customers any lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to the network. We are committed to the spirit of the NOFA. | N/A | 18504 | 5965 | 0 | 0 | 12539 | 0 | 0 | N/A | 544 | 27 | 27 | 490 | Network providers and/or customers can interconnect with VTel at the interconnection points listed in our BTOP Application. These locations include primarily third party collocation facilities/Central Offices. | No subcontracts or sub grants have been made to socially and economically disadvantaged small businesses. We are entering into a construction contract with a socially and economically disadvantaged small business. | Management of the make ready process has proven to be the most difficult part of this project. Although the utility pole owners have guidelines for time frames in getting the work done, it is necessary to actively manage and track the process, in order for the construction deadlines to be met. | Vermont Telephone Company, Inc. | 55 | 11 | 3 | 10 | 27 | 1 |  | 6 | 11 | 1 | 125 | 0 Interconnection agreements entered. 0 Interconnection agreements being negotiated. 0 Interconnection agreements denied. We have 6 existing agreements with broadband wholesale and last mile providers whose connection will be upgraded as a result of this project once the core optical network is installed. These customers are shown in the quarterly indicators of the baseline. | 7 Peering Relationship entered into. 0 Peering or Transit Agreements being negotiated. 0 Peering or Transit Agreements denied. | TRUE
NT10BIX5570085 | 2013 | 88044 | Our baseline target of $82,975 per mile. We fully expect that we will be on or under our baseline target as our miles increase during the last construction phase. | 0 | n/a | 0 | n/a | 100Gb/s | We are happy to report that we have started offering speeds up to 100Gb/s, which is improved and faster access than in our baseline. | 0 | n/a | 72Mb/s | No variance from base line | 0 | n/a | We have reviewed the speeds that our CAI's contracted for before the BTOP project as well as the speeds contracted for now that the grant is underway. We took the average total speed prior and the average total speed subsequent and calculated the delta between the two to come up with a speed increase to be 420 Mbps. | Community Anchor institutions can avail themselves with one of our seven pricing options outlined on the attached CAI pricing sheet. We offer the following: #1 10Mbps of internet access bursting up to 25Mbps #2 25Mbps of internet access with bursting up to 50Mbps #3 50Mbps of internet access with bursting to 100Mbps. #4 100Mbps with bursting to GigE. #5 200Mbps with bursting up to GigE h #6 Dedicated GigE "spoke" back to any of the above #7 100Mbps of dedicated access with bursting to GigE to any of the above | VTel posts our terms of service and network management policies on our web site therefore any and all customers have access them. We do not prevent customers any lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to the network. We are committed to the spirit of the NOFA. | n/a | 18504 | 5965 | 0 | 0 | 12539 | 0 | 0 | n/a | 544 | 27 | 27 | 490 | Network providers and/or customers can interconnect with VTel at primarily third party collocation facilities/Central Offices. The Central Offices are: White River Junction CO, Chelsea Hut, Montpelier CO, Waterbury CO, Essex CO, Burlington CO, Burlington Telecom CO, New Haven Cabinet, Brandon Hut, Rutland CO, Waterbury CO, Stowe CO, Morrisville CO, Milton CO | Our Prime Construction Contractor is a SDB (Eustis Cable Enterprises) and we have contracted with them to build the entire network. | Management of the make ready process continues to be the most difficult part of this project. Although the utility pole owners have guidelines for time frames in getting the work done, it is necessary to actively manage and track the process in order for the construction deadlines to be met. Consistent scheduled meetings where all parties can see the work work that is being completed, and the work not yet done are key. These status meetings can be used to raised issues, and work through roadblocks to resolution to keep progress on track. | Vermont Telephone Company, Inc. | 55 | 11 | 3 | 10 | 27 | 1 |  | 6 | 11 | 1 | 125 | We have 6 pre-existing agreements with broadband wholesale and last mile providers whose connection will be upgraded (all were existing customers prior to our BTOP project) as a result of this project once the core optical network is installed. These customers are: Earthlink, Topsham Telephone, Burlington Telecom, Wavecomm, Great Awk (formerly Finowen and Light Tower (formerly Sidera). 6 Interconnection agreements entered. 0 Interconnection agreements being negotiated. 0 Interconnection agreements denied. | 1. Netflix 2. Google 3. Apple 4. ISPrime.com 5. FPL FiberNET LLC 6. BroadbandONE 7. Webair 8. Amazon 9. TelX 10. Free Software Foundation (GNU) 11. TowardEX 12. Studsvik Scandpower 13. OCCAID 14. RCN Cable 15. Akamai 15 New Peering Relationship entered into (all entered into subsequent to the project starting) 0 Peering or Transit Agreements being negotiated. 0 Peering or Transit Agreements denied. | TRUE
NT10BIX5570086 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | Network usage will not be limited to anything less than the purchased bandwidth; users on Enventisâ€™ network will have a choice of service levels. By default, Layer 1 TDM service is a guaranteed bandwidth service; Layer 2 and 3 services will be offered with a choice of five classes of service and user defined bandwidth profiles. Enventis will employ generally acceptable network management practices and its interconnection policies will be displayed on its web site. Enventis will provide its customers with notice of changes to these policies. To date, Enventis has not blocked customers from accessing lawful content or services unless in doing so, they would cause harm or degradation to the Enventis network. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Enventis will provide interconnections to the BTOP funded network through existing interconnection locations where Enventis is a current tenant. Interconnections with new customers will also be made at these existing locations. They include â€œcarrier hotelsâ€ such as the 511 building and TriTech buildings in Minneapolis as well as Qwest central office co-locations throughout the state. | N/A | Enventis has learned that it is very important to document everything and keep a central repository. We have started a Grants File to track all required documents and reporting along with anything that is project related. We continually update and organize that folder to make it easy to find required information. | Enventis Telecom, Inc. | 1 | 0 | 5 | 4 | 22 | 0 |  | 2 | 0 | 0 | 34 | N/A | Enventis is currently negotiating transit agreements with three separate wholesale customers. | TRUE
NT10BIX5570086 | 2011 | 53,972.95 | Due to location and conditions this was the most expensive part of the project. Remaining miles will be less bringing the overall average down. | 0 | N/A | 0 | N/A | 10Gig | N/A | 0 | N/A | 50mbps | We are providing 50mbps service to one CAI site at this time. | 0 | N/A | We are currently serving one community anchor institution. They were upgraded from a point to point T1 to 50Mbps Ethernet service. | Enventis has completed a build to a Mayo Clinic site and now provide improved access at this location. The site previously had a T1 of service and now enjoys 50Mbps. This project seeks to provide 100Mg to 10G lit capacity as well as leased dark fiber. We provide Individual Case Basis (ICB) pricing to potential customers that are based on speed and fiber proximity as we continue to reassess the broader retail market to determine competitive rates and standard pricing. | Network usage will not be limited to anything less than the purchased bandwidth; users on Enventisâ€™ network will have a choice of service levels. By default, Layer 1 TDM service is a guaranteed bandwidth service; Layer 2 and 3 services will be offered with a choice of five classes of service and user defined bandwidth profiles. Enventis will employ generally acceptable network management practices and its interconnection policies will be displayed on its web site. Enventis will provide its customers with notice of changes to these policies. To date, Enventis has not blocked customers from accessing lawful content or services unless in doing so, they would cause harm or degradation to the Enventis network. | N/A | 41721 | 0 | 0 | 15072 | 0 | 0 | 26649 | Enventis intends to wholesale dark fiber as part of this project and we are actively negotiating four Agreements with three customers. We have not yet signed these documents and as such are not currently leasing any dark fiber to customers. | 300 | 200 | 0 | 100 | In addition to the collocation space available at the two new Point of Presence sites, Enventis will provide interconnections to the BTOP funded network through existing interconnection locations where Enventis is a current tenant. Interconnections with new customers will also be made at these existing locations. They include carrier hotels such as the 511 Building and TriTech buildings in Minneapolis as well as Qwest central office collocations throughout the state. | N/A | Through the implementation of this federal project, Enventis has learned some valuable lessons that may benefit other federal recipients. These include: Federal projects require consistent and thorough documentation; it is easier to track progress and document open issues as they unfold versus revisiting the matter afterward and trying to recall important facts, decisions or dates. Census tracts and census blocks can vary significantly in geographic size; it may benefit a recipient to carefully review each before requesting one versus the other as it may unexpectedly narrow the proposed funded service area. Use the guidance and information that is available on the BTOP websites. Take advantage of conferences, drop in calls and webinars that are offered to stay up to date on processes. Make every effort to ensure that all employees who are part of the project are aware of requirements to stay in compliance. | Enventis Telecom, Inc. | 1 | 0 | 5 | 4 | 22 | 0 |  | 2 | 0 | 0 | 34 | Enventis has completed three interconnection agreements during the reporting period. Completion of one agreement provided Enventis access to a major carrier hotel in Minneapolis which is the preferred endpoint for three customers; the associated dark fiber agreements are currently in negotiation. Enventis also entered into two joint construction agreements with other BTOP recipients to collaborate on de minimus shared segments along the long haul route. Enventis adheres to a defined policy on Network Openness and Non-Discrimination and fully explores each interconnection request received. | Enventis is in active negotiations with three customers on four dark fiber agreements. Enventis adheres to a defined policy on Network Openness and Non-Discrimination and fully explores each request for new or improved service that is received. | TRUE
NT10BIX5570086 | 2012 | 39494.00 | This amount is currently below our estimated cost. | 0 | N/A | 0 | N/A | 10Gig | N/A | 0 | N/A | 92Mbps | We are providing 100Mbps service to 5 of the 6 CAI's that are receiving service. The other one is getting 50Mbps. | 0 | N/A | The average increase in broadband speed provided is 92Mbps. We have 6 customers currently receiving service, with one getting 50Mbps and 5 getting 100Mbps. | Enventis is now providing new or improved access to nine Community Anchor Institutions. This project seeks to provide 100Mg to 10G lit capacity as well as leased dark fiber. We provide Individual Case Basis (ICB) pricing to potential customers that is based on speed and fiber proximity as we continue to reassess the broader retail market to determine competitive rates and standard pricing. | Network usage will not be limited to anything less than the purchased bandwidth; users on Enventisâ€™ network will have a choice of service levels. By default, Layer 1 TDM service is a guaranteed bandwidth service; Layer 2 and 3 services will be offered with a choice of five classes of service and user defined bandwidth profiles. Enventis will employ generally acceptable network management practices and its interconnection policies will be displayed on its web site. Enventis will provide its customers with notice of changes to these policies. To date, Enventis has not blocked customers from accessing lawful content or services unless in doing so, they would cause harm or degradation to the Enventis network. | N/A | 41721 | 1554 | 652 | 35619 | 162 | 0 | 3734 | [REDACTED] | 240 | 170 | 35 | 35 | In addition to collocation space available at two Point of Presence sites along the BTOP-funded middles mile routes, Enventis will provide interconnections to the BTOP funded network through existing interconnection locations where Enventis is a current tenant. Interconnections with new customers will also be made at these existing locations. They include carrier hotels such as the 511 Building and TriTech buildings in Minneapolis as well as Qwest central office collocations throughout the state of Minnesota. | N/A | Through the implementation of this federal project, Enventis has learned valuable lessons that may benefit other federal recipients. These include: It is important to provide project updates and reminders on program requirements to all employees working on the project on a regular basis. Some employees are participating in a small part of the project but still must be familiar with all federal guidelines. Enventis has updated internal and contractor fact sheets on a quarterly basis to refresh project information and we continually remind the project team and participating employees on key directives including the need to verify Federal status in EPLS or SAM before engaging a new contractor or vendor. Take advantage of BTOP-sponsored conferences, drop in calls and webinars that are offered to stay up to date on program requirements. Continually review project policies for accuracy. Enventis developed a Program Income policy at the start of the project but it required an update once we had obtained Program Income and verified how it was tracked through our internal accounting process and systems. | Enventis Telecom, Inc. | 1 | 0 | 5 | 4 | 22 | 0 |  | 2 | 0 | 0 | 34 | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570086 | 2013 | 51309 | This is above our initial baseline due to decreased number of route miles. | 0 | N/A | 0 | N/A | 10Gig | N/A | 0 | N/A | 166Mbps | The average increase in broadband speed provided is 166Mbps. We have 20 CAI customers currently receiving service, with 2 customers receiving 1Gb service, 11 customers receiving 100Mbps, 2 customers receiving 50Mbps service, 1 customer receiving 45Mbps service, 1 customer receiving 40Mbps service, 1 customer receiving 20Mbps service, 1 customer receiving 10Mbps service and 1 customer receiving 5Mbps service. | 0 | N/A | The average increase in broadband speed provided is 166Mbps. We have 20 CAI customers currently receiving service, with 2 customers receiving 1Gb service, 11 customers receiving 100Mbps, 2 customers receiving 50Mbps service, 1 customer receiving 45Mbps service, 1 customer receiving 40Mbps service, 1 customer receiving 20Mbps service, 1 customer receiving 10Mbps service and 1 customer receiving 5Mbps service. | Enventis is now providing new or improved access to 34 Community Anchor Institutions. This project seeks to provide 100Mg to 10G lit capacity and leased dark fiber. We provide Individual Case Basis (ICB) pricing to potential customers that is based on speed and fiber proximity as we continue to reassess the broader retail market to determine competitive rates and standard pricing. | Network usage will not be limited to anything less than the purchased bandwidth; users on Enventisâ€™ network will have a choice of service levels. By default, Layer 1 TDM service is a guaranteed bandwidth service; Layer 2 and 3 services will be offered with a choice of five classes of service and user defined bandwidth profiles. Enventis will employ generally acceptable network management practices and its interconnection policies will be displayed on its web site. Enventis will provide its customers with notice of changes to these policies. To date, Enventis has not blocked customers from accessing lawful content or services unless in doing so, they would cause harm or degradation to the Enventis network. | N/A | 39267 | 3238 | 2112 | 33917 | 0 | 0 | 0 | Enventis is leasing 191 route miles of dark fiber to MND, 163 route miles to Zayo, and 157 route miles to the State of MN OET. | 240 | 170 | 70 | 0 | In addition to collocation space available at two Point of Presence sites along the BTOP-funded middles mile routes, Enventis will provide interconnections to the BTOP funded network through existing interconnection locations where Enventis is a current tenant. Interconnections with new customers will also be made at these existing locations. They include carrier hotels such as the 511 Building and TriTech buildings in Minneapolis as well as Qwest central office collocations throughout the state of Minnesota. | N/A | Through the implementation of this federal project, Enventis has learned valuable lessons that may benefit other federal recipients. These include: It is important to provide project updates and reminders on program requirements to all employees working on the project on a regular basis. Some employees are participating in a small part of the project but still must be familiar with all federal guidelines. Enventis has updated internal and contractor fact sheets on a quarterly basis to refresh project information and we continually remind the project team and participating employees on key directives including the need to verify Federal status in EPLS or SAM before engaging a new contractor or vendor. Take advantage of BTOP-sponsored conferences, drop in calls and webinars that are offered to stay up to date on program requirements. Utilize the wiki for references and resources. Continually review project policies for accuracy. Enventis developed a number of policies at the start of the project but some required updates as we moved through the project period. Keep internal records updated to ensure accurate reporting. Begin preparing reports and verifying internal information as soon as possible - do not wait to begin just before a deadline. If there are questions or you run into an issue, it is better to have more time to straighten it out. If you have a question for an NTIA or BAH representative, ask it right away. The unanticipated federal government shutdown prevented access to key resources at all federal agencies and BAH during the close out reporting period. | Enventis Telecom, Inc. | 1 | 0 | 5 | 4 | 22 | 0 |  | 2 | 0 | 0 | 34 | Enventis has secured multiple agreements with some providers and also secured agreements that document multiple services (services may be New or Improved Access) on one agreement. During the reporting period, Enventis completed 25 agreements with 11 providers including Verizon Wireless (4), WIN (1), MND (1), SDN (1), Qwest QCC (3), Verizon Business (2), State of MN OET (9), Cooperative Network Services (1), Cooperative Light & Power (1), XO (1), Compudyne (1). Enventis adheres to a Network Openness policy and fully explores each interconnection request received. | Enventis has secured dark fiber agreements with MND and the State of MN OET. Enventis adheres to a Network Openness and Non-Discrimination policy and fully explores each request for new or improved service that is received. | TRUE
NT10BIX5570087 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | 10 MBPS - 100 MBPS - OPEN ACCESS | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | We provide an open-access network available to all members. We do not limit or block access of lawful content or applications for members. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We will provide four (4) interconnection points on this project. These interconnection points are strategically placed to provide regeneration points, interconnection & access points and co-location points. | N/A | N/A | Mid-Atlantic Broadband Cooperative | 14 | 0 | 2 | 0 | 0 | 0 |  | 3 | 0 | 0 | 19 | N/A | N/A | TRUE
NT10BIX5570087 | 2011 | 0 | Not yet started construction | 0 | N/A | 0 | N/A | 0 | 10mbps-100mbps- Open Access | 0 | N/A | 0 | Not yet started construction | 0 | N/A | 0 | N/A | We provide an open-access network available to all members. We do not limit or block access of lawful content or applications for members. | N/A | 25024 | 0 | 0 | 0 | 340 | 0 | 24684 | 0 | 0 | 0 | 0 | 0 | We will provide four (4) interconnection points on this project. These interconnection points are strategically placed to provide regeneration points, interconnection & access points and co-location points. | N/A | N/A | Mid-Atlantic Broadband Cooperative | 14 | 0 | 2 | 0 | 0 | 0 |  | 3 | 0 | 0 | 19 | 1. None 2. None 3. We have not denied any requests. | N/A | TRUE
NT10BIX5570087 | 2012 | $33,861 | Average cost less than baseline due to lower than expected bid prices and only 84% of construction is complete. | 0 | N/A | 0 | N/A | 10 Gbps | 10 mbps- 100 mbps - Open Access | 0 | N/A | 57 mbps | 10 mbps- 100 mbps - Open Access | 0 | N/A | Broadband speed has not increased. Most CAI's request 50 mbps or 100 mbps. | [REDACTED] | We provide an open access network available to all customers. We do not limit or block access of lawful services or applications of our customers. | None | 24057 | 0 | 0 | 19348 | 192 | 0 | 4517 | N/A | 960 | 480 | 15 | 465 | N/A | N/A | 1) Start the Environmental Assessment process as early as possible for long, linear projects 2) Perform design work in advance to aid in preparation of EA and construction bidding. | Mid-Atlantic Broadband Cooperative | 14 | 0 | 2 | 0 | 0 | 0 |  | 3 | 0 | 0 | 19 | 1) Entered into one (1) agreement (County of Surry) 2) Negotiating seven (7) agreements with Cox, VDOT, Comcast, Town of Suffolk, BIT(2), Surry County Schools 3) Have not denied any requests for interconnection | N/A | TRUE
NT10BIX5570087 | 2013 | 24697 | Average cost less than baseline due to lower than expected bid prices and 87% of budgeted funds were actually spent. | 0 | N/A | 0 | N/A | 10 Gbps | 10mbps- 100mbps- Open Access | 0 | N/A | 40 mbps | 10mbps- 100mbps- Open Access | 0 | N/A | Broadband speed has not increased. Most CAIs request 10mbps, 50mbps or 100mbps. | [REDACTED] | We provide an open access network available to all customers. We do not limit or block access of lawful services or applications of our customers. | None | 23923 | 605 | 0 | 23318 | 0 | 0 | 0 | N/A | 960 | 480 | 15 | 465 | N/A | N/A | 1) Start the Environmental Assessment process as early as possible for long, linear projects. 2) Perform design work in advance to aid in preparation of EA and construction bidding. | Mid-Atlantic Broadband Cooperative | 14 | 0 | 2 | 0 | 0 | 0 |  | 3 | 0 | 0 | 19 | 1) Entered into five (5) agreements: (3)GCR, (2) Kinex 2) Negotiating four (4) agreements with Cox, VDOT, Comcast, Town of Suffolk 3) Have not denied any requests for interconnection | N/A | TRUE
NT10BIX5570088 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | LTE devices will be very expensive. Consider a transition or refresh plan to minimize costs. | Charlotte, City of | 0 | 0 | 0 | 0 | 0 | 27 |  | 0 | 0 | 0 | 27 | N/A | N/A | TRUE
NT10BIX5570088 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | None | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Charlotte, City of | 0 | 0 | 0 | 0 | 0 | 27 |  | 0 | 0 | 0 | 27 | N/A | N/A | TRUE
NT10BIX5570088 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | None | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Charlotte, City of | 0 | 0 | 0 | 0 | 0 | 27 |  | 0 | 0 | 0 | 27 | N/A | N/A | TRUE
NT10BIX5570088 | 2013 | 0 | N/A. Due to suspension middle mile has not been deployed. | 0 | N/A. This project is specific to public safety entities only. | 0 | N/A. Due to suspension last mile has not been deployed. | 0 | N/A. Due to suspension middle mile has not been deployed. | 0 | N/A. Due to suspension last mile has not been deployed. | 0 | N/A. Due to suspension middle mile has not been deployed. | 0 | N/A. Due to suspension last mile has not been deployed. | N/A | None | N/A. 7a. Due to suspension network has not been deployed. 7b. This project is specific to public safety only and is not providing commercial services. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | 1. Plan on Significant cost increase for Band 14 devices and maintenance. 2. Commercial costs structure for LTE 4G service have become very competitive. 3. Preserving network design in such a fluid tower space market. 4. Local zoning conditions can have a significant impact on schedule and site costs. 5. Balancing commitment to a design with tower modification expense. | Charlotte, City of | 0 | 0 | 0 | 0 | 0 | 27 |  | 0 | 0 | 0 | 27 | N/A | N/A | TRUE
NT10BIX5570089 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No increase in speed at this time. | No retail services are being provided by this project. | No network management policies have been developed at this time. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | No interconnection points have been finalized at this time. | No subcontracts have been awarded to SDB businesses at this time. | N/A | Motorola Solutions, Inc. | 0 | 0 | 0 | 0 | 0 | 150 |  | 0 | 0 | 0 | 150 | N/A | N/A | TRUE
NT10BIX5570089 | 2011 | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | Since no infrastructure has been deployed to date, no increase in broadband speed can be reported. | N/A | Since no infrastructure has been deployed to date, no network policies have been developed to date. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Since no infrastructure has been deployed to date, no collocation space can be reported. | No SDB subcontracts have been awarded. | Since deployment has not yet begun Motorola is not yet in a position to share best practices/lessons learned. | Motorola Solutions, Inc. | 0 | 0 | 0 | 0 | 0 | 150 |  | 0 | 0 | 0 | 150 | N/A | N/A | TRUE
NT10BIX5570089 | 2012 | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and other initial program delays. | 0 | N/A. | 0 | N/A. | 0 | N/A. | 0 | N/A. | 0 | N/A. | 0 | N/A. | Since no infrastructure has been deployed to date, no increase in broadband speed can be reported. | N/A | Since no infrastructure has been deployed to date, no increase in broadband speed can be reported. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Since no infrastructure has been deployed to date, no collocation space can be reported. | No SDB subcontracts have been awarded. | Motorola Solutions participated in a site visit with members of the First Responder Network Authority (First Net) board, JPA executives, NTIA, Sate of California representative, representative from the Mayor of San Francisco office, the Police Chief of City of San Francisco, director of EMA, and Motorola Solutions executives. During that meeting Motorola and the BAYRICS authority shared many lessons learned concerning contracting, BOOM agreements, SAU agreements, and vendors. | Motorola Solutions, Inc. | 0 | 0 | 0 | 0 | 0 | 150 |  | 0 | 0 | 0 | 150 | N/A | N/A | TRUE
NT10BIX5570089 | 2013 | 0 | The indicated variance from the baseline plan occurred as a result of delays in the finalization and readiness of sites and ultimate expiration of the BTOP grant. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | Since no infrastructure was deployed due to the expiration of the BTOP grant, no increase in broadband speed can be reported. | N/A | Since no infrastructure was deployed due to the expiration of the BTOP grant, no network policies can be reported. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Since no infrastructure was deployed due to the expiration of the BOP grant, no collocation space can be reported. | No SDB subcontracts were awarded. | Motorola Solutions continued to participate in meetings with members of the First Responder Network Authority (First Net) board, Joint Powers Authority (JPA executives, NTIA, State of California representatives, and Motorola Solutions executives. During those meetings, Motorola and the BAYRICS authority shared many lessons learned concerning contracting, Build Own Operate Maintain(BOOM) agreements, Site Access and Use (SAU) agreements, and vendors. | Motorola Solutions, Inc. | 0 | 0 | 0 | 0 | 0 | 150 |  | 0 | 0 | 0 | 150 | N/A | N/A | TRUE
NT10BIX5570090 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 7a. Only limitations are the service level the customer is contracted to pay for the service (SLA). 7b. No. | N/A | 408 | 0 | 0 | 0 | 408 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Network providers and customers are either connected in their space or they are connected to DCN's equipment in DCN's space within our facility. | None. | N/A | DCN, LLC | 17 | 2 | 0 | 1 | 55 | 12 |  | 27 | 10 | 0 | 124 | 1. 17 2. 0 3. N/A | N/A | TRUE
NT10BIX5570090 | 2011 | 44869 | So far we have been below our estimate by $14,000/mile. But not all of our costs from sub recipients have been incurred yet. This is a good indication that our budgets should not be exceeded. | 0 | N/A | 0 | N/A | 100 | Mbps | 0 | N/A | 5 | Mbps | 0 | N/A | 0 Mbps; no increase at this time since only one has been connected with no change to their purchased speed at this time. Service quality and consistency are greatly increased due to the change from copper to fiber and dedicated service. | N/A | 7a. Only limitations are the service levels the customer is contracted to pay for (SLA). 7b. No | N/A | 5632 | 3184 | 0 | 0 | 408 | 0 | 2040 | N/A | 0 | 0 | 0 | 0 | Customers are connected in the space they own and DCN meets them on a cable connection demarcation equipment basis at their site. Network service providers are connected at the cable level either in DCN's space or at the serve providers location and DCN owns the equipment in either case. | None. | Have to allow extra time to accommodate reporting requirements. | DCN, LLC | 17 | 2 | 0 | 1 | 55 | 12 |  | 27 | 10 | 0 | 124 | 1. 17 2. 0 3. N/A | N/A | TRUE
NT10BIX5570090 | 2012 | 43,049 | So far we have been below our estimate by $5,000 per mile. But not all of our costs have been incurred yet. | 0 | N/A | 0 | N/A | 100 Mbps | N/A | 0 | N/A | 7 Mbps | N/A | 0 | N/A | 4 Mbps on average. Subscribers were being by TI's and now have 5 mpbs service or higher. | No retail service provided. | 7a. Only limitations are the service levels the customer is contracted to pay for (SLA). 7b. No | N/A | 5725 | 3193 | 0 | 0 | 422 | 0 | 2110 | N/A | 0 | 0 | 0 | 0 | Customers are connected in the space they own and DCN meets them on a cable connection demarcation equipment basis at their site. Network service providers are connected at the cable level either in DCN's space or at the serve providers location and DCN owns the equipment in either case. | None. | Have to allow extra time to accommodate reporting requirements. | DCN, LLC | 17 | 2 | 0 | 1 | 55 | 12 |  | 27 | 10 | 0 | 124 | Number of signed agreements: 17 Number being negotiated: 0 Average term of the signed agreements: 7 | N/A | TRUE
NT10BIX5570090 | 2013 | 42064 | We are below our estimate by $6,000 per mile. Costs were lower than estimated. | 0 | N/A | 0 | N/A | 1000 Mbps | N/A | 0 | N/A | 13.6 | N/A | 0 | N/A | 10 Mbps on average. Subscribers were being served by TI's and now have 5 mbps service or higher. | no retail service provided. | 7a. Only limitations are the service levels the customer is contract to pay for (SLA) 7b. No | N/A | 5725 | 5725 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Customers are connected in the space they own and DCN meets them on a cable connection demarcation equipment basis at their site. Network service providers are connected at the cable level either in DCN's space or at the service provider's location and DCN owns the equipment in either case. | None. | Have to allow extra time to accommodate quarterly reporting requirements. | DCN, LLC | 17 | 2 | 0 | 1 | 55 | 12 |  | 27 | 10 | 0 | 124 | Number of signed agreements: 17 Number being negotiated: 0 Average term of the signed agreements: 7 Denied requests: 0 | N/A | TRUE
NT10BIX5570091 | 2010 | 0 | Deployment is not complete | 0 | NA | 0 | NA | 10GB | Planned maximum speed in line with baseline | 0 | NA | 1GB | Planned average speed in line with baseline | 0 | NA | NA | NA | NA, no network in place to date | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA, no network to date | NA | Bluebird decided to split the mapping/staking engineering between three engineering firms. This allows the firms to work on a smaller portion of the project decreasing the return time on the work requested. This also mitigates the risk of a single firm delaying the project. | Bluebird Media, L.L.C. | 44 | 15 | 14 | 14 | 30 | 4 |  | 34 | 21 | 0 | 176 | NA | NA | TRUE
NT10BIX5570091 | 2011 | 0 | N/A-no fiber in service to date. | N/A | N/A | N/A | N/A | 10GB | Planned maximum speed in line with baseline | N/A | N/A | 0 | No subscribers to date, therefore no average speed. | N/A | N/A | NA | NA | NA, no network in place to date. | NA | 107212 | 0 | 0 | 21197 | 2920 | 0 | 83095 | NA | 0 | 0 | 0 | 0 | NA, no collocation space built to date. | NA | Bluebird decided to split the outside plant construction into 7 segments. This allowed Bluebird to contract with four different construction companies to build the fiber routes mitigating the risk of a single company faltering. Bluebird also went directly to several equipment manufactures to request a bid on the equipment used for this BTOP project. This strategic decision has allowed Bluebird to obtain the lowest price for manufactured goods without paying a premium to a re-seller. | Bluebird Media, L.L.C. | 44 | 15 | 14 | 14 | 30 | 4 |  | 34 | 21 | 0 | 176 | N/A | N/A | TRUE
NT10BIX5570091 | 2012 | 0 | N/A-no portion of the network was fully deployed, complete, and in service. | N/A | N/A | N/A | N/A | 10GB | Planned maximum speed in line with baseline | N/A | N/A | 0 | No subscribers to date, therefore no average speed. | N/A | N/A | N/A-no lit services during this annual reporting period | N/A-no lit services during this annual reporting period | N/A-no lit services during this annual reporting period | N/A-no lit services during this annual reporting period | 105464 | 1174 | 0 | 91851 | 346 | 0 | 12093 | N/A | 4110 | 2055 | 0 | 2055 | N/A-own collocation space | N/A | Bluebird decided to split the outside plant construction into 7 segments. This allowed Bluebird to contract with four different construction companies to build the fiber routes mitigating the risk of a single company faltering. Bluebird also went directly to several equipment manufactures to request a bid on the equipment used for this BTOP project. This strategic decision has allowed Bluebird to obtain the lowest price for manufactured goods without paying a premium to a re-seller. | Bluebird Media, L.L.C. | 44 | 15 | 14 | 14 | 30 | 4 |  | 34 | 21 | 0 | 176 | Total number of interconnections entered into during this annual reporting period was 22; currently negotiating 5 interconnection agreements; no requests for interconnection has been denied. | N/A | TRUE
NT10BIX5570091 | 2013 | $55,170 | The average variance increase of $12,083 per mile was caused from engineering and construction costs being under estimated. | N/A | N/A | N/A | N/A | 10GB | Planned maximum speed in line with baseline | N/A | N/A | 140 Mb | The average variance decrease of 50 Mb was caused by less than estimated CAIs subscribing for 1GB of service. This decrease caused the average to fall below estimated. | N/A | N/A | The average increase in broadband speed provided to the CAI customers was 20 Mb. Bluebird calculated this increase by comparing the CAIs service speed prior to connecting to the grant network against the current speed while connected to the grant network. These figures were than averaged. | Dedicated Internet Access, Extended Local Area Network, Extended Wide Area Network, etc. Pricing plans are unique to each individual customer since Bluebird is a middle mile network and the majority of retail customers need outside plant to directly connect for services. | Bluebird's management policies consist of no traffic prioritization and the bandwidth limitations are capped at the bandwidth the customer subscribed. Bluebird has never limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | N/A- zero subscribers have dropped during this project once connect to the grant network. | 98097 | 2602 | 110 | 95385 | 0 | 0 | 0 | Bluebird would like to refrain from including the names of the broadband wholesales due to the names being proprietary. The agreements Bluebird has with these providers are proprietary and confidential. | 4470 | 2235 | 0 | 2235 | N/A-own collocation space | N/A | Bluebird learned that it is better to start sooner rather than later when filing federal liens with all the appropriate counties as each county has different formats, costs, and requirements. | Bluebird Media, L.L.C. | 44 | 15 | 14 | 14 | 30 | 4 |  | 34 | 21 | 0 | 176 | Total number of interconnections entered into during this annual reporting period was 2; currently negotiating 5 interconnection agreements; no requests for interconnection has been denied. | N/A | TRUE
NT10BIX5570093 | 2010 | 0 | N/A - Waiting on completion of EA to begin project | 0 | N/A - Waiting on completion of EA to begin project | 0 | N/A - Waiting on completion of EA to begin project | 0 | N/A - Waiting on completion of EA to begin project | 0 | N/A - Waiting on completion of EA to begin project | 0 | N/A - Waiting on completion of EA to begin project | 0 | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project | 0 | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | Citizens' Telephone Co-operative | 37 | 1 | 2 | 2 | 4 | 4 |  | 7 | 0 | 0 | 57 | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | TRUE
NT10BIX5570093 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | The one CAI that has been connected using BTOP funding had a symmetrical broadband connection of 1.5Mbps replaced by a symmetrical 1Gbps (1,000Mbps) broadband connection. This resulted in a 66566.67% increase in broadband speed (increase = (new amount - original amount)/original amount. In both cases this is a transport circuit only between the school and the central technology center for the school system. The internet connectivity is centralized and shared with all schools in the school system from the technology center. | No retail services have been provided by this project at this time. Delays with EA approval and in acquiring fiber have limited progress until January 2012. | a) No bandwidth limitations or traffic prioritization are being used. Our Network Management Policy, Acceptable Use Policy and policy regarding compliance with the Digital Millennium Copyright Act (DMCA) are all posted on our website under Terms & Conditions. http://citizens.coop/terms/ b) No | N/A | 38419 | 38419 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Citizens' Telephone Co-operative | 37 | 1 | 2 | 2 | 4 | 4 |  | 7 | 0 | 0 | 57 | N/A | N/A | TRUE
NT10BIX5570093 | 2012 | 33,455 | Average cost per new mile is less than the baseline amount of $52,791 due to the fact that construction is 96% complete, but we have only received and paid invoices for 65% of the project. This amount will come in line with the baseline once we start receiving and paying invoices for completed construction. | 0 | N/A | 0 | N/A | 1G | No Variance | 0 | N/A | 1G | The 5 Subscribers we are currently serving over BTOP-funded facilities are all using a 1G circuit. | 0 | N/A | The five CAI's that have been connected using BTOP funding had a symmetrical broadband connection of 1.5Mbps replaced by a symmetrical 1Gbps (1,000Mbps) broadband connection. This resulted in a 66566.67% increase in broadband speed (increase = (new amount - original amount)/original amount. In these cases this is a transport circuit only between the school and the central technology center for the school system. The internet connectivity is centralized and shared with all schools in the school system from the technology center. | See Attachment for services offered and pricing plan. | a) No bandwidth limitations or traffic prioritization are being used. Our Network Management Policy, Acceptable Use Policy and policy regarding compliance with the Digital Millennium Copyright Act (DMCA) are all posted on our website under Terms & Conditions. http://citizens.coop/terms/ b) No | N/A | 43039 | 43039 | 0 | 0 | 0 | 0 | 0 | N/A | 480 | 240 | 0 | 240 | N/A | N/A | N/A | Citizens' Telephone Co-operative | 37 | 1 | 2 | 2 | 4 | 4 |  | 7 | 0 | 0 | 57 | N/A | N/A | TRUE
NT10BIX5570093 | 2013 | 49,914 | Average cost per new mile is less than the baseline amount of $52,791 due to the fact that Citizens was able to complete the project and come in under budget. Construction was originally budgeted for $9,819,064 and the actual construction expense was $9,283,920. | 0 | N/A | 0 | N/A | 10G | No Variance | 0 | N/A | 1G | No Variance | 0 | No Variance | There are 17 CAI's that have been connected using BTOP funding that had a symmetrical broadband connection of 1.5Mbps replaced by a symmetrical 1Gbps (1,000Mbps) broadband connection. This resulted in a 66566.67% increase in broadband speed. There are 4 CAI's that have been connected using BTOP funding that had a symmetrical broadband connection of 10.0Mbps replaced by a symmetrical 1Gbps (1,000Mbps) broadband connection. This resulted in a 9900.00% increase in broadband speed. There are 2 CAI's that have been connected using BTOP funding that had a symmetrical broadband connection of 45.0Mbps replaced by a symmetrical 1Gbps (1,000Mbps) broadband connection. This resulted in a 2122.22% increase in broadband speed. There are 5 CAI's that have been connected using BTOP funding that had a symmetrical broadband connection of 100.0Mbps replaced by a symmetrical 1Gbps (1,000Mbps) broadband connection. This resulted in a 900.00% increase in broadband speed. There is 1 CAI that has been connected using BTOP funding that had a symmetrical broadband connection of 768.0Kbps (0.768Mbps) replaced by a symmetrical 3.0Mbps broadband connection. This resulted in a 290.63% increase in broadband speed. The increases in speeds above were calculated using the following formula: (increase = (new amount - original amount)/original amount. | See Attachment for services offered and pricing plan. | a) No bandwidth limitations or traffic prioritization are being used. Our Network Management Policy and policy regarding compliance with the Digital Millennium Copyright Act (DMCA) are all posted on our website under Terms and Conditions. http://citizens.coop/terms/ b) No | N/A | 41997 | 40743 | 0 | 1254 | 0 | 0 | 0 | Radford University - 93.40 Miles Virginia Department of Transportation - 200 | 480 | 240 | 0 | 240 | N/A | N/A | None at this time. | Citizens' Telephone Co-operative | 37 | 1 | 2 | 2 | 4 | 4 |  | 7 | 0 | 0 | 57 | No new Interconnection Agreements were entered into during this annual reporting period. We are continuing and extending the eight existing agreements we have with Bristol Virginia Utility (BVU), Mid Atlantic Broadband (MBC), Shentel, Cox Communications, Windstream, Lumos, Surry Telephone Membership Corporation, and Skyline Telephone Membership Corporation, that were in place before the NTIA Grant was awarded. No Interconnection Agreements are currently being negotiated. No Interconnection requests have been denied. | No new Peering and/or Transit Agreements were entered into during this annual reporting period, but we are continuing and extending the three existing agreements we have with Virginia Tech, Radford University, and New River Community College. No Peering and/or Transit Agreements are currently being negotiated. | TRUE
NT10BIX5570094 | 2010 | $0 | No new miles were constructed during 2010. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 Mbps | N/A | 1 Mbps | N/A | N/A | N/A | 7a. Network Management is within the scope of RFP 3639, which has been released. Traffic prioritization will be in accordance with the State's FCC waiver for use of 700 MHz PSST Spectrum. 7b. No | Service is not available at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Facilities have not been established at this time. Customers will connect via a mobile wireless device. | N/A | Once the addition of LTE equipment on the towers begins, we will be able to offer best practices to other BTOP recipients. | Executive Office of the State of Mississippi | 0 | 0 | 1 | 1 | 7 | 200 |  | 17 | 0 | 0 | 226 | N/A | N/A | TRUE
NT10BIX5570094 | 2011 | $3559.40 | 428 new miles completed in 2011 which included the installation of microwave backhaul equipment for 24 new network links in Phase 2C & 2D. Each set of microwave dishes costs $63,476 which equates to $3559.40 per mile. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | The upgraded microwave backhaul was in the initial stages of deployment and therefore was not utilized in 2011. | 0 | The upgraded microwave backhaul was in the initial stages of deployment and therefore was not utilized in 2011. | In 2011, we were in the initial stages of designing and deploying the components of the LTE network. We had not begun offering broadband services to community anchor institutions during 2011. | N/A | 7a. Network Management is within the scope of RFP 3639 which has been awarded to Motorola Solutions. Traffic prioritization will be in accordance with the State's FCC waiver for use of 700 MHz PSST Spectrum. 7b. No | Service is not available at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Facilities have not been established at this time. Customers will connect via a mobile wireless device. | N/A | N/A | Executive Office of the State of Mississippi | 0 | 0 | 1 | 1 | 7 | 200 |  | 17 | 0 | 0 | 226 | N/A | N/A | TRUE
NT10BIX5570094 | 2012 | $3559.40 | 428 new miles completed in 2011 which included the installation of microwave backhaul equipment for 24 new network links in Phase 2C & 2D. Each set of microwave dishes costs $63,476 which equates to $3559.40 per mile. Payment milestones related to microwave installation in Phase 3 have been achieved during 2012, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | In 2012, Mississippi was in the process of deploying the components of the LTE network. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. We continued to deploy the upgraded microwave backhaul, however it was not utilized in 2012. | 0 | In 2012, Mississippi was in the process of deploying the components of the LTE network. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. We continued to deploy the upgraded microwave backhaul however it was not utilized in 2012. | In 2012, Mississippi was in the process of deploying the components of the LTE network. On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Therefore, we have not begun offering broadband services to community anchor institutions during 2012. | N/A | 7a. Network Management is within the scope of RFP 3639 which has been awarded to Motorola Solutions. Traffic prioritization will be in accordance with the State's FCC waiver for use of 700 MHz PSST Spectrum. 7b. No | Service is not available at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Facilities have not been established at this time. Customers will connect via a mobile wireless device. | N/A | N/A | Executive Office of the State of Mississippi | 0 | 0 | 1 | 1 | 7 | 200 |  | 17 | 0 | 0 | 226 | N/A | N/A. | TRUE
NT10BIX5570095 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | Network Management will utilize 'best practices' for protection of the network. The six steps were outlined in our initial BTOP application and exceed the word limitation for this section. However, all of these capabilities are available from the appliances provided by all major providers of content filtering devices. Additionally, these capabilities are fully configured to ensure that the filtering and protection taking place is fully in compliance with the NOFA without compromising the ability of the network to provide the required services to its users. | N/A | 9800 | 0 | 0 | 0 | 1000 | 1200 | 7600 | N/A | 0 | 0 | 0 | 0 | Network providers and/or customers requesting interconnection have 3 options: 1)Secure collocation at one of our current collocation facilities or point of presence. 2)Meet at a splice point for mid-span meet. 3)Instruct/Request that we build to their premise. | N/A | One of our best practices has been the selection of East Alabama Regional Planning Commission for the development of our Environmental Assessment. We had several concerns expressed from other government agencies due to this selection, however having a local representative that is very familiar with the processes and, most importantly, the personnel responsible for services throughout our state has been a large benefit to reaching our goals for the EA. | JKM Consulting, Inc. | 20 | 7 | 4 | 3 | 10 | 6 |  | 3 | 17 | 6 | 76 | N/A | N/A | TRUE
NT10BIX5570095 | 2011 | 0 | Final invoices, including splicing, for the currently completed segments have not been received as of 12/31/2011. Insufficient data to calculate average cost per mile as of yet. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | Not provided because deployment has not yet begun. | Services are not yet being provided. | N/A | 9800 | 0 | 0 | 0 | 1000 | 1800 | 7600 | N/A | 0 | 0 | 0 | 0 | Interconnect to the network can occur at negotiated splice points, or with POP locations. All POP locations reside within data centers that are open to collocation or at carrier hotel type facilities. | Willie T. Gooden d/b/a Gooden Construction P.O. Box 3250 Anniston, Alabama 36202 | N/A | JKM Consulting, Inc. | 20 | 7 | 4 | 3 | 10 | 6 |  | 3 | 17 | 6 | 76 | N/A | N/A | TRUE
NT10BIX5570095 | 2012 | $29,266 | Changing standards/requirements from AL DOT (Department of Transportation) and the NESC (National Electric Safety Code) increased construction cost. | 0 | N/A | 0 | N/A | 1 Gbps | No variance from baseline | 50 Mbps | Changes in technology allowed an increase in offered speeds on wireless system | 100 Mbps | No variance from baseline | 0 | N/A | Average increase is 80 Mbps. Prior services ranged from 0 to 50 Mbps. CAI's subscribing to our receiving 100 Mbps service. | As of December, we were not serving retail customers that were not on the CAI (Community Anchor Institution) list. | Network Management Policies: Traffic for services with a purchased CIR (Committed Information Rate)feature are given higher priority to services that are sold at best effort, otherwise prioritization policies exist. Service providers are limited to oversubscription ratio of 4 to 1. No traffic has been blocked or limited to date. | We have not experienced any number of subscribers dropping services provided through this project. | 12500 | 1500 | 0 | 11000 | 0 | 0 | 0 | At this time, we do not have wholesale customers for dark fiber services. | 0 | 0 | 0 | 0 | We have established interconnection points at the equivalent of carrier hotels owned by third parties where multiple service providers collocate. Additional interconnection is made available at fiber splice points. | N/A | N/A | JKM Consulting, Inc. | 20 | 7 | 4 | 3 | 10 | 6 |  | 3 | 17 | 6 | 76 | Earthlink Interconnection Agreement completed on March 27, 2012. Slappey Telephone agreement completed May 2, 2012. AT&T interconnection agreement completed May 24, 2012. CenturyLink Interconnection Agreement completed December 6, 2012 Roanoke Telephone interconnection agreement under negotiations. SynchGlobal interconnection agreement under negotiations. | Transit agreements with both Cogent Communications and EarthLink completed, | TRUE
NT10BIX5570095 | 2013 | 39,187.79 | n/a | 0 | n/a | 0 | n/a | 1 gigabyte | n/a | 0 | n/a | 100 megabyte | n/s | 0 | n/a | Average increase is 80 Mbps. Prior services ranged from 0 to 50 Mbps. CAI's subscribing to our receiving 100 Mbps service. | At the retail level fiber services are; 100 mps Ethernet transport, virtual private lines, internet access and dark fiber. Wireless internet access is available in select locations. | Network Management Policies: Traffic for services with a purchased CIR (Committed Information Rate)feature are given higher priority to services that are sold at best effort, otherwise prioritization policies exist. Service providers are limited to oversubscription ratio of 4 to 1. No traffic has been blocked or limited to date. | We have not experienced any number of subscribers dropping services provided through this project. | 12500 | 320 | 52 | 12128 | 160 | 38 | 11218 | Jacksonville State University: 24 fiber miles: Calhoun County Administration: 14 fiber miles Slappey Telephone: 6 fiber miles SyncGlobal Telecom: 8 fiber miles | 0 | 0 | 0 | 0 | Other network providers and/or may interconnect at any of our 7 collocated POP's or at a mutually agreeable splice point on the network. We have established interconnection points at the equivalent of carrier hotels owned by third parties where multiple service providers collocate. | N/A | N/A | JKM Consulting, Inc. | 20 | 7 | 4 | 3 | 10 | 6 |  | 3 | 17 | 6 | 76 | Earthlink Interconnection Agreement completed on March 27, 2012. Slappey Telephone agreement completed May 2, 2012. AT&T interconnection agreement completed May 24, 2012. CenturyLink Interconnection Agreement completed December 6, 2012 SynchGlobal Telecommunications agreement completed March 1, 2013 Roanoke Telephone Company/TEC June 2013 | Internet Transit Traffic peering agreements with Cogent Communication and Hurricane Electric | TRUE
NT10BIX5570096 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | NONE | N/A | N/A | 1438323 | 0 | 0 | 0 | 1434723 | 1200 | 2400 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | None at this time | Virgin Islands Public Finance Authority | 70 | 7 | 2 | 8 | 19 | 42 |  | 127 | 19 | 22 | 316 | N/A | N/A | TRUE
NT10BIX5570096 | 2011 | 0 | N/A: Until the network build is completed and tested, the U.S. Virgin Islands Public Finance Authority (VIPFA)/Virgin Islands Next Generation (viNGN) team is unable to accurately calculate the average cost per new mile. The team has executed an Indefeasible Right of Use (IRU) agreement with Global Crossing/Level 3; has purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network and has purchased Carrier Ethernet equipment; however, the network build and equipment deployment have been delayed due to 1) restarting the projects during an implementation period that was shorter by nearly three weeks due to the stop work order that was not lifted until October 17, 2011, 2) resulting delays in procurement, construction and other project implementation activities, and 3) the simultaneous transition of the implementation of the VIPFA/viNGN's four BTOP projects to a new management team. The team plans to address these challenges by compressing construction schedules, implementing parallel construction activities; maintaining aggressive work schedules; and, hiring additional staff. | 0 | N/A | 0 | N/A | 10Gbps | N/A: Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available. | 0 | N/A | 0 | N/A; Until the network build is completed and tested, viNGN will not be able to accurately determine the speeds that will be available. | 0 | N/A | N/A | N/A | N/A | N/A | 31489 | 0 | 0 | 0 | 31489 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | In both the Miami NAP (Network Access Point) of Americas and the NYC 60 Hudson NAP, viNGN's collocation agreement contractually provides it with the ability to extend fiber cables from the collocation cage to the â€œmeet meâ€ rooms; the interconnection to other carriers is via â€œmid-spanâ€ fiber "meet me" physical connection arrangements that enable connectivity with more than sixty (60) different carriers and network providers. viNGN has a lease with Global Crossing/Level 3 at both the Miami and New York NAPs. The NAP in Miami has 750,000 sq ft.; viNGN will lease 6 sq ft. The NY NAP has 15,000 sq ft.; viNGN will lease 6 sq ft in this facility, as well. | N/A | None at this time | Virgin Islands Public Finance Authority | 70 | 7 | 2 | 8 | 19 | 42 |  | 127 | 19 | 22 | 316 | N/A | 1) viNGN has executed one Indefeasible Right of Use (IRU) agreement with Global Crossing/Level 3 for access to 10Gb of capacity through New York and Miami, providing a strong network with a diverse route and the ability to purchase bandwidth at prices that are significantly less than what is offered in the local market today. The IRU with Global Crossing / Level 3 is expected to offer 1) a 10Gb Clear Ethernet WAV, 2) a “one hop” to the core of the NAP of the Americas, 3) better connectivity than the city of Miami, 4) an internet peering point, and 5) a Carrier Ethernet network. 2) The team is still in negotiations with a second wholesale service provider, AT&T. 3) The team has not denied any request for interconnection, as its network is being built and tested. The project team is not able to finalize negotiations with last mile providers before finalizing an IRU agreement with AT&T, as the terms of the IRU agreements are key to the development of viNGN's schedule of products and pricing. As a result, viNGN has not signed any agreements with retail services providers; however, the team continues to engage the local community of anchor tenants and last mile providers in discussions. These conversations have been conducted on an individual basis, as well as under the aegis of the Broadband Coalition. Two additional Broadband Coalition meetings were held during October 2011, one on St. Thomas and the other on St. Croix. These meetings and conversations have resulted in the request for a business and technical conference to be held to further facilitate discussions and to achieve consensus on the optimal types of products and services to be offered by viNGN. The formulation of the Broadband Coalition and the technical conference are also designed to support a range of market research activities and to solicit direct feedback as viNGN formulates its range of products, prices, terms and conditions for the services and products to be offered. | TRUE
NT10BIX5570096 | 2012 | 0 | N/A: Until the network build is completed and tested, the U.S. Virgin Islands Public Finance Authority (VIPFA)/Virgin Islands Next Generation (viNGN) team is unable to accurately calculate the average cost per new mile. The team has executed an Indefeasible Right of Use (IRU) agreement with Global Crossing/Level 3 and a lease agreement with AT&T; has purchased all of the fiber required for its network; and, has purchased all of the required Carrier Ethernet equipment. | 0 | N/A | 0 | N/A | 10Gbps | N/A: Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available. The Broadband speeds that are expected to be available are from 1 Gbps to 10 Gbps. | 0 | N/A | 0 | N/A: Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available. | 0 | N/A | N/A; CAI connections are expected to begin during Quarter 2, CY 2013. | N/A; The VIPFA/viNGN team is building out a middle mile network; thus, retail services will not be provided. | N/A; 7a. Network management policies are being developed for viNGN's middle mile services 7b. The VIPFA/viNGN team is building out a middle mile network; thus, retail services will not be provided directly to retail consumers. | N/A; The VIPFA/viNGN team is building out a middle mile network; thus, retail subscriber services will not be provided. | 31489 | 0 | 0 | 0 | 31489 | 0 | 0 | N/A | 12 | 12 | 0 | 0 | In both the Miami NAP (Network Access Point) of Americas and the NYC 60 Hudson NAP, viNGN's collocation agreement contractually provides it with the ability to extend fiber cables from the collocation cage to the "meet me" rooms; the interconnection to other carriers is via "mid-span" fiber "meet me" physical connection arrangements that enable connectivity with more than sixty (60) different carriers and network providers. viNGN has a lease with Global Crossing/Level 3 at both the Miami and New York NAPs. The NAP in Miami has 750,000 sq ft.; viNGN leased 6 sq. ft. The New York NAP has 15,000 sq. ft.; viNGN leased 6 sq. ft. in this facility, as well. These areas that are leased are not collocation spaces. However, as the FAPs are completed, the square footage within them will be collocation spaces between viNGN and the ISPs (Internet Service Providers) and other service providers. viNGN may also lease additional space on St. Croix from Global Crossing/Level 3, in an effort to provide customers with an earlier service date, i.e. prior to the completion of its entire network build. | N/A | None at this time | Virgin Islands Public Finance Authority | 70 | 7 | 2 | 8 | 19 | 42 |  | 127 | 19 | 22 | 316 | N/A | 1) viNGN has executed one Indefeasible Right of Use (IRU) agreement with Global Crossing/Level 3 for access to 10Gb of capacity through New York and Miami, providing a strong network with a diverse route and the ability to purchase bandwidth at prices that are significantly less than what is offered in the local market today. The IRU with Global Crossing/Level 3 is providing 1) two 10Gb Clear Ethernet WAVE, 2) a "one hop" to the core of the NAP (Network Access Point) of the Americas and to New York City, 3) an internet peering point, and 4) a Carrier Ethernet Network. 2) The team has a lease agreement with AT&T for the SONET OC-48 to temporarily connect St. Thomas and St. Croix. 3) The team has not denied any request for interconnection, as its network is being built and tested. viNGN has not signed any agreements with retail services providers; however, the team continues to engage the local community of anchor tenants/ Community Anchor Institutions (CAIs) and last mile providers in discussions. These conversations have been conducted on an individual basis, as well as under the aegis of the Broadband Coalition. Three Broadband Coalition meetings were held during CY 2012, two of which were simulcast through video conference on St. Thomas and on St. Croix. One of the simulcasts was held at the University of the Virgin Islands (UVI), and the second simulcast was held at the U.S. Virgin Islands Emergency Management Agency (VITEMA), both of which are CAIs on VIPFA/viNGN's network. The Broadband Coalition meeting discussions included the following: -VIPFA/viNGN's Organization, Key Contacts and Working Relationship with Service Providers, ISPs, the local government and the Federal government; -CCI Build-out Plans and Schedule; -Equipment to be deployed at each CAI, the technical specifications and the schematics; -FAP Details (Locations and Layout); -Community Anchor Institutions (Connecting to the Network); and -viNGN's Future Business Plans. These meetings and conversations have resulted in the request for a business and technical conference to be held to further facilitate discussions and to achieve consensus on the optimal types of products and services to be offered by viNGN. The Broadband Coalition and the technical conference are also designed to support a range of market research activities and to solicit direct feedback as viNGN refines its range of products, prices, terms and conditions for the services and products to be offered. | TRUE
NT10BIX5570096 | 2013 | $116,156 | The actual "Average cost per mile (Middle Mile)", per NTIA's definition, is below the Baseline estimate of $157,294. | 0 | N/A | 0 | N/A | 10Gbps | The network is designed to offer broadband speeds that are up to 10 Gbps. | 0 | N/A | 0 | N/A: Until the network build is completed and tested and service is provided to a larger customer base, the VIPFA/viNGN team will not be able to accurately provide an average broadband speed provided. | 0 | N/A | Prior to the VIPFA/viNGN team's installation of its fiber optic network at the Althalie McFarlane Peterson Library, the library's network was operating at 2 Mbps to 5 Mbps. After VIPFA/viNGN installed its equipment and fiber and the library was connected to VIPFA/viNGN's 100% fiber optic, wholesale/middle mile network, the library's speed was recorded at between 20 Mbps to 50 Mbps, i.e. ten times (10X) the speeds previously experienced at the library. | N/A; The VIPFA/viNGN team is building out a 100% fiber optic, wholesale/middle mile network; thus, retail services are not being provided. | 7a. Network management policies are being developed. 7b. No | N/A; The VIPFA/viNGN team is building out a 100% fiber optic, wholesale/middle mile network. | 29602 | 21 | 6494 | 22515 | 572 | 0 | 0 | N/A | 2128 | 2128 | 0 | 0 | In both the Miami NAP (Network Access Point) of Americas and the NYC 60 Hudson NAP, viNGN's collocation agreement contractually provides it with the ability to extend fiber cables from the collocation cage to the "meet me" rooms; the interconnection to other carriers is via "mid-span" fiber "meet me" physical connection arrangements that enable connectivity with more than sixty (60) different carriers and network providers. viNGN has a lease with Global Crossing/Level 3 at both the Miami and New York NAPs. The NAP in Miami has 750,000 sq ft.; viNGN leased 6 sq. ft. The New York NAP has 15,000 sq. ft.; viNGN leased 6 sq. ft. in this facility, as well. These areas that are leased are not collocation spaces. However, as the FAPs are completed, the square footage within them will be collocation spaces between viNGN and the ISPs (Internet Service Providers) and other broadband service providers. | The entire U.S. Virgin Islands has been classified as a Historically Under-utilized Business Zone (HUBZone), as it is a 100% underserved or un-served, rural, insular territory, consisting of four inhabited islands with less than 110,000 residents in total, low per capita income levels and a higher than the national average unemployment rate. Thus, it is believed that most of the project's local vendors can be classified as SDBs; however, the information to verify the relevant data is not available at the time of the publication of this report. Further, it is believed that some of the project's non-local vendors can be classified as SDBs; however, additional resources would have to be identified and allocated for the data to be collected and verified. Additional funding is not currently available through VIPFA, viNGN or the Government of the U.S. Virgin Islands. In addition, the VIPFA/viNGN's procurement process allows for open and, at a minimum, limited competition, the latter in those cases when the purchases are defined as "Small Purchases" or in cases of emergency under Federal and local law, for which there have been none to date. Full and open competition solicitations are posted on www.vingn.com, the VIPFA's Office of Economic Opportunity (OEO) website, local newspapers, and local online media, with sufficient time for respondents to provide quotes, bids or proposals, in order to ensure that all potential vendors, including SDBs, are aware of all opportunities. | The key best practices and lessons learned by the VIPFA/viNGN team are the following: â€¢ Recipients must identify additional financial and human resources needed to meet the extensive reporting requirements under the BTOP projects and to most effectively and efficiently implement a major construction project, especially in environments with relatively low broadband speeds and reliability and very high prices and limited local government financial resources, like the U.S. Virgin Islands; and, â€¢ In order to have significant penetration in broadband adoption levels in communities which are significantly underserved and unserved, like the U.S. Virgin Islands, significant financial resources, well in excess of what is currently available under the VIPFA/viNGN's team's BTOP programs, must be allocated to marketing, public relations, promotions, community outreach, and awareness activities; Internet-based research support; training and other educational courses; and, other services to encourage broadband use and adoption and to have impact in an insular broadband market within the short term of the program. | Virgin Islands Public Finance Authority | 70 | 7 | 2 | 8 | 19 | 42 |  | 127 | 19 | 22 | 316 | Under its Indefeasible Right of Use (IRU) agreement with Global Crossing/Level 3, which was executed during CY 2011, the VIPFA/viNGN team activated connections through Level 3 in New York, Level 3 in Miami, FAP STX-02 (Frederiksted)/Lagoon and the U.S. Virgin Islands Department of Planning and Natural Resources' Althalie McFarlane Petersen Library in Frederiksted, St. Croix, the latter of which is a CAI and a Public Computer Center (PCC). The team has not denied any request for interconnection. | N/A | TRUE
NT10BIX5570097 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Department of Information Technology | 0 | 0 | 0 | 0 | 0 | 23 |  | 0 | 0 | 0 | 23 | N/A | N/A | TRUE
NT10BIX5570097 | 2011 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | Service to Community Anchor Institutions's (CAI) not yet offered. | N/A | N/A | Broadband speeds have not increased since construction/deployment has not begun | N/A | DoIT is currently doing its Broadband network planning, including network offerings, network control, etc. Modern network management capabilities are inherent in Aviat's Internet Protocol (IP) radio architecture. DoIT plans to implement a Network Operation Center capability as part of our Middle Mile Broadband system, but this capability is still in the planning stages and will be implemented as portions of the network are substantially completed. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 5760 | 4608 | 0 | 1152 | Connections to the State of New Mexico Middle Mile Network will be made at network Points Of Presence (POP) currently located at 28 of 59 sites being up-graded. Connections between Community Anchor Institution's and the POP sites will be provided by private Local Exchange Carrier's or possibly by other BTOP grantees providing Last Mile service in New Mexico. | N/A | N/A | Department of Information Technology | 0 | 0 | 0 | 0 | 0 | 23 |  | 0 | 0 | 0 | 23 | N/A | N/A | TRUE
NT10BIX5570097 | 2012 | 0 | NA | NA | NA | NA | NA | 0 | NA | NA | NA | NA | Service to Community Anchor Institutions's (CAI) not yet offered. | NA | NA | Broadband speeds have not increased since construction/deployment has not begun | NA | DoIT is currently doing its Broadband network planning, including network offerings, network control, etc. Modern network management capabilities are inherent in Aviat's Internet Protocol (IP) radio architecture. DoIT plans to implement a Network Operation Center capability as part of our Middle Mile Broadband system as part of the system implementation in early CY13. | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 5760 | 4608 | 0 | 1152 | Connections to the State of New Mexico Middle Mile Network will be made at network Points Of Presence (POP) currently located at 28 of 59 sites being up-graded. Connections between Community Anchor Institution's and the POP sites will be provided by private Local Exchange Carrier's or possibly by other BTOP grantees providing Last Mile service in New Mexico. | NA | NA | Department of Information Technology | 0 | 0 | 0 | 0 | 0 | 23 |  | 0 | 0 | 0 | 23 | NA | NA | TRUE
NT10BIX5570097 | 2013 | 0 | Cost analysis in process and has not yet been completed. | N/A | N/A | N/A | N/A | 0 | Until the system is up and operational, advertisement of broadband speed has not been established. | N/A | N/A | N/A | Service to Community Anchor Institutions (CAI) not yet offered. | N/A | N/A | Until the system is up and operational, broadband speed has not been established or advertised. | N/A | DoIT is currently doing its Broadband network planning, including network offerings, network control, etc. Modern network management capabilities are inherent in Aviat's Internet Protocol (IP) radio architecture. DoIT has implemented a Network Operation Center capability as part of our Middle Mile Broadband system as part of the system implementation. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 5760 | 4608 | 0 | 1152 | Connections to the State of New Mexico Middle Mile Network will be made at network Points Of Presence (POP) currently located at 28 of 59 sites being up-graded. Connections between Community Anchor Institution's and the POP sites will be provided by private Local Exchange Carrier's or possibly by other BTOP grantees providing Last Mile service in New Mexico. | N/A | N/A | Department of Information Technology | 0 | 0 | 0 | 0 | 0 | 23 |  | 0 | 0 | 0 | 23 | N/A | N/A | TRUE
NT10BIX5570098 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 245364 | 0 | 0 | 0 | 2120 | 2544 | 240700 | N/A | 0 | 0 | 0 | 0 | N/A | 1) Chambers Group - Subcontract (Vendor) 2) Praxis Associates, Inc. - Sub-grant (Subrecipient) | (1) Obtain detailed engineering measurements and construction methods early in the process as a basis for budgeting and environmental studies. (2) Develop strong GIS mapping capabilities early on as a basis for Environmental Assessment and project documentation, (3) Build budget and plan as detailed as possible so that the various information is consistently developed and used. It is also a key basis for accurate modifications as plans or budget changes occur. | California Broadband Cooperative, Inc. | 51 | 12 | 3 | 4 | 13 | 36 |  | 116 | 16 | 0 | 251 | N/A | N/A | TRUE
NT10BIX5570098 | 2011 | 0 | Construction not started | 0 | NA | 0 | NA | 0 | We have not begun advertising as construction not started | 0 | NA | 0 | Construction not started | 0 | NA | None, Construction not started | NA | 7a. None, Construction not started 7b. No, Construction not started | None, Construction not started | 245364 | 0 | 0 | 0 | 2120 | 2544 | 240700 | ZAYO Group, LLC. ZAYO Group has purchased 553 miles of wholesale middle mile dark fiber from us between Carson and Barstow. | 0 | 0 | 0 | 0 | We do not own collocation space but other network providers will be able to interconnect with our network at node sites, splice points, terminals and carrier central offices. | 1. Chambers Group - Subcontractor (Vendor) 2. Praxis Associates, Inc. - Sub-grant (Subrecipient) | Aggressively and continuously monitor primary environmental consultant using project staff or secondary consultant to ensure accurate and timely deliverable. | California Broadband Cooperative, Inc. | 51 | 12 | 3 | 4 | 13 | 36 |  | 116 | 16 | 0 | 251 | None | None | TRUE
NT10BIX5570098 | 2012 | 470,633.30 | The forecast of $229,097.78 was predicated on a higher completion of conduit and fiber placement by this time. These costs are based upon total dollars spent against the total miles of fiber placed. The dollars spent are heavily burdened with front end engineering, permitting, environmental, and materials acquisition costs. As the denominator increases with miles placed, these fixed costs will proportionately go down. | 0 | NA | 0 | NA | 10Gbps | Increase to 10Gbps from 2.5Gbps, due to unexpected demand and the fact that equipment hardware is cheaper to provision this level than to break services down to the 2.5Gbps. | 0 | NA | 0 | 10Mbps Variance - No anchors have yet to be connected. | 0 | NA | None - Construction started but no community anchor institutions connected | NA - This is a wholesale network | California Broadband Cooperative, Inc. (CBC) will solely manage the proposed funded network in accordance with the FCC's Internet Policy Statement (FCC 05-151, adopted August 5, 2005) and in compliance with any future Internet policy changes by the FCC. Currently CBC does not discriminate or favor any lawful Internet applications, content, or services where lawfully used, and these same practices will be continued for the proposed funded network. We promote our customer's ability to freely access and disseminate lawful content in a manner that respects others' use of the network and that complies with the law. While CBC does not engage in blocking customer access to illegal or legal Internet content, CBC supports industry practices for safeguarding children, intellectual property rights and our customers' privacy and security. CBC follows standard best efforts for Internet delivery with respect to allocation of capacity without differentiation among applications, providers, or sources. CBC uses generally accepted technical measures to provide acceptable service levels to all customers, such as application-neutral bandwidth allocation, as well as measures to address service attacks, illegal content and other harmful activities to protect network integrity and reliability. | None - Network presently under construction but no community anchor institutions connected. | 245364 | 0 | 0 | 47088 | 2120 | 2544 | 193612 | ZAYO Group, LLC ZAYO Group has purchased 553 miles of wholesale middle mile dark fiber between Carson and Barstow. | 1664 | 712 | 0 | 952 | NA - We own collocation space | N/A | 1) External stakeholder management and on-going interactions with Agencies is important factor. Local agencies, and elected officials expect a high degree of information. We were able to achieve this with a dynamic web site that kept the public informed of our progress. 2) Timeframes and complexity of environmental permits and approvals are exponentially related to the number of agencies involved. In many instances, at project start, many agencies are unfamiliar with longitudinal projects, especially fiber. Many of the paradigms they use in their work do not apply. 3) Flexible start dates should be included in construction contracts, as seasonality can have a great impact of future cost changes. 4) Strength in contract administration is a Key Success Factor. This includes a high level of field inspections, regulatory compliance, and thorough documentation. The use of databases and cloud computing is especially effective. | California Broadband Cooperative, Inc. | 51 | 12 | 3 | 4 | 13 | 36 |  | 116 | 16 | 0 | 251 | 1) Agreements Entered Into ZAYO Group, LLC. - Purchased wholesale middle mile dark fiber between Reno and Barstow. AT&T Nevada – Signed interconnection agreement for NV. Verizon California – Signed interconnection agreement for CA. Suddenlink - Signed agreement for dark fiber 2) Agreements Being Negotiated - 11 3) NA | 1) Agreements Entered Into ZAYO Group, LLC. - Purchased wholesale middle mile dark fiber between Reno and Barstow. Level 3 - Signed interconnection agreement for collocation and peering for Barstow and Reno. 2) Agreements Being Negotiated - 0 3) NA | TRUE
NT10BIX5570098 | 2013 | 181,498.07 | The forecast of $139,191.74 was predicated on a an overrun in budget due to higher environmental permitting costs and method of construction (i.e, change in CPUC Pole calculation formulas) There was approximately $25M in environmental costs. | 0 | NA | 0 | NA | 10Gbps | Increase to 10Gbps from 2.5Gbps, due to unexpected demand and the fact that equipment hardware is cheaper to provision this level than to break services down to the 2.5Gbps. | 0 | NA | 500Mbps | Increase from 10Mbps, due to the connection of only 6 customers through the end of 2013. These initial customers are significantly heavier users of bandwidth. As the remaining customers are hooked up we expect the average bandwidth speed to decrease toward the average bandwidth projected | 0 | NA | 48.5 MB increase. This is calculated based on the majority of customers were receiving T1 service and will now have 50MB delivered via a gigabit ethernet circuit allowing growth of up to 1000MB. | NA - This is a wholesale network | California Broadband Cooperative, Inc. (CBC) will solely manage the proposed funded network in accordance with the FCC's Internet Policy Statement (FCC 05-151, adopted August 5, 2005) and in compliance with any future Internet policy changes by the FCC. Currently CBC does not discriminate or favor any lawful Internet applications, content, or services where lawfully used, and these same practices will be continued for the proposed funded network. We promote our customer's ability to freely access and disseminate lawful content in a manner that respects others' use of the network and that complies with the law. While CBC does not engage in blocking customer access to illegal or legal Internet content, CBC supports industry practices for safeguarding children, intellectual property rights and our customers' privacy and security. CBC follows standard best efforts for Internet delivery with respect to allocation of capacity without differentiation among applications, providers, or sources. CBC uses generally accepted technical measures to provide acceptable service levels to all customers, such as application-neutral bandwidth allocation, as well as measures to address service attacks, illegal content and other harmful activities to protect network integrity and reliability. | None - Network presently under construction and only few community anchor institutions were connected in December | 245364 | 2248 | 0 | 243116 | 0 | 0 | 0 | ZAYO Group, LLC ZAYO Group has purchased 553 miles of wholesale middle mile dark fiber between Carson and Barstow. | 1664 | 712 | 0 | 952 | NA - We own collocation space | NA | 1) External stakeholder management and on-going interactions with Agencies is important factor. Local agencies, and elected officials expect a high degree of information. Use web sites and any available media opportunities. 2) Time frames and complexity of environmental permits and approvals are exponentially related to the number of agencies involved. In many instances, at project start, many agencies are unfamiliar with longitudinal projects, especially fiber. Many of the paradigms they use in their work do not apply. 3) Flexible start dates should be included in construction contracts, as seasonality can have a great impact of future cost changes. 4) Strength in contract administration is a Key Success Factor. This includes a high level of field inspections, regulatory compliance, and thorough documentation. The use of databases and cloud computing is especially effective. 5) Strong focus on agile budget management and cost control. 6) In additional to fundamental network construction capability, fiber optic projects have complex data communication elements that must be properly designed, implemented and managed. | California Broadband Cooperative, Inc. | 51 | 12 | 3 | 4 | 13 | 36 |  | 116 | 16 | 0 | 251 | 1) Agreements Entered Into Plumas Sierra - Signed internet and collocation agreement Lone Pine TV - Internet Access SchatNet - Internet Access and Transport 2) Agreements Being Negotiated - 3 3) Have we denied a request for interconnection and if so, why? No | 1) Agreements Entered Into - 0 2) Agreements Being Negotiated - 0 3) Have we denied a request for interconnection and if so, why? No | TRUE
NT10BIX5570099 | 2010 | $0 | N/A | $0 | N/A | $0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 7a. N/A 7b. No | N/A | 12961 | 0 | 0 | 0 | 1548 | 0 | 11413 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Bloomingdale Communications Inc | 13 | 9 | 0 | 0 | 0 | 1 |  | 10 | 0 | 0 | 33 | N/A | N/A | TRUE
NT10BIX5570099 | 2011 | $0 | N/A - Bloomingdale Communications, Inc. did not project to have construction completed by the end of Quarter 2 Year 2 (December 2011), however by the end of the project the estimated average cost per new mile for Middle Mile is expected to be around $40,511. | N/A | N/A | N/A | N/A | 0 | N/A - Bloomingdale Communications, Inc. did not project to have construction completed by the end of Quarter 2 Year 2 (December 2011), however by the end of the project the estimated maximum broadband speed advertised for Middle Mile is expected to be 20 Mbps. | 0 | N/A | 0 | N/A - Bloomingdale Communications, Inc. did not project to have construction completed by the end of Quarter 2 Year 2 (December 2011), however by the end of the project the estimated average broadband speed provided for Middle Mile is expected to be 10 Mbps. | 0 | N/A | N/A | N/A | 7a. N/A 7b. No | N/A | 12961 | 0 | 0 | 0 | 1548 | 0 | 11413 | NA | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Bloomingdale Communications Inc | 13 | 9 | 0 | 0 | 0 | 1 |  | 10 | 0 | 0 | 33 | N/A | N/A | TRUE
NT10BIX5570099 | 2012 | $33,500 | Due to construction re-bid, Bloomingdale Communications, Inc. has not completed construction by the end of December 2012. The construction is close to completion and will be fully complete within the 3 year project window. However, through December 31, 2012, Bloomingdale Communications has spent around $33,500 per new mile based on total budget. | N/A | N/A | N/A | N/A | N/A | Bloomingdale Communications, Inc. has not completed construction by the end of December 2012, therefore speeds have not been advertised at this point in the project. However by the end of the project the estimated maximum broadband speed advertised for Middle Mile is expected to be 100 Mbps. | N/A | N/A | N/A | Bloomingdale Communications, Inc. has not completed construction by the end of December 2012, therefore is not providing average broadband speeds yet. However, by the end of the project the estimated average broadband speed provided for Middle Mile is expected to be 20 Mbps. | N/A | N/A | N/A, Bloomingdale Communications, Inc. has not completed construction of the project yet, therefore the average increase in broadband speed provided to the community anchor institution customers is not applicable at this time. | N/A, Bloomingdale Communications, Inc. is not providing retail services by this project. | 7a. Bloomingdale has an Acceptable Use Policy (AUP) on its website (http://www.bloomingdalecom.net/forms.php) regarding network management practices, performance and commercial terms of service sufficient for consumers to make an informed choice regarding their use of such services. Bloomingdale will not unjustly or unreasonably prevent or interfere with competition among content, applications, service, or device providers. Following is a non-exclusive list of policies included within Bloomingdaleâ€™s AUP: Bloomingdale uses generally accepted technical measures to provide acceptable service levels to all customers, such as application-neutral bandwidth allocation, as well as measures to address service attacks, illegal content and other harmful activities to protect network integrity and reliability. Bloomingdale reserves the right to 1) immediately disconnect or modify Service if determined that use of Service is inconsistent with normal residential or business usage patterns or is in violation of the AUP; 2) protect its network from harm, which may impact legitimate data flows; 3) limit throughput or amount of data transferred, and to deny or discontinue service, without notice, to anyone it believes is using an unlimited data plan or feature in any manner prohibited by the AUP or whose usage adversely impacts network or service levels. Bloomingdale is under no obligation to monitor customer's usage, bandwidth, transmissions and/or content of Service however may do | N/A | 16043 | 0 | 0 | 0 | 1548 | 0 | 14495 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Bloomingdale Communications Inc | 13 | 9 | 0 | 0 | 0 | 1 |  | 10 | 0 | 0 | 33 | N/A | N/A | TRUE
NT10BIX5570099 | 2013 | $48,900 | Bloomingdale Communications, Inc (BCI) has completed the project and average cost per mile based on the total budget is around $48,900 per new mile. | N/A | N/A | N/A | N/A | 100 Mbps | BCI currently advertises up to 100 Mbps. | N/A | N/A | 40 Mbps | Based on the 32 Community Anchor Institutions (CAIs) BCI currently provides service to utilizing the new network, the average speed subscribed to is 40 Mbps. | N/A | N/A | Using straight average calculation, the average increase in broadband speed provided to the 32 CAIs that are taking the new service from BCI is about 30 Mbps. The average of the 32 CAIs previous speed was around 10 Mbps, however the new average speed since connected to the new network and subscribing to BCI service the average speed is now around 40 Mbps. | N/A, BCI is not providing retail services by this project. | 7a. Bloomingdale has an Acceptable Use Policy (AUP) on its website (http://www.bloomingdalecom.net/forms.php) regarding network management practices, performance and commercial terms of service sufficient for consumers to make an informed choice regarding their use of such services. Bloomingdale will not unjustly or unreasonably prevent or interfere with competition among content, applications, service, or device providers. Following is a non-exclusive list of policies included within Bloomingdaleâ€™s AUP: Bloomingdale uses generally accepted technical measures to provide acceptable service levels to all customers, such as application-neutral bandwidth allocation, as well as measures to address service attacks, illegal content and other harmful activities to protect network integrity and reliability. Bloomingdale reserves the right to 1) immediately disconnect or modify Service if determined that use of Service is inconsistent with normal residential or business usage patterns or is in violation of the AUP; 2) protect its network from harm, which may impact legitimate data flows; 3) limit throughput or amount of data transferred, and to deny or discontinue service, without notice, to anyone it believes is using an unlimited data plan or feature in any manner prohibited by the AUP or whose usage adversely impacts network or service levels. Bloomingdale is under no obligation to monitor customer's usage, bandwidth, transmissions and/or content of Service however may do | N/A, no BCI subscribers have dropped the new broadband service. | 14172 | 974 | 0 | 13198 | 0 | 0 | 0 | N/A | 480 | 392 | 0 | 88 | BCI connects to their customers network with an Overture Network Interface Device (NID) that resides at the customers location. This NID has the ability to connect either with a fiber or copper connector. The Overture NID connects back to the Cyan transport network via fiber. They Cyan transport then carries the customer traffic to whatever end point is required by the customer. If the customer is needing internet connectivity BCI has two ISPâ€™s that they connect with to provide that service. The interconnection to the ISPâ€™s is located in the Bloomingdale central office. | N/A | N/A | Bloomingdale Communications Inc | 13 | 9 | 0 | 0 | 0 | 1 |  | 10 | 0 | 0 | 33 | N/A | N/A | TRUE
NT10BIX5570100 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 106560 | 0 | 0 | 0 | 17760 | 5920 | 82880 | N/A | 6 | 6 | 0 | 0 | Fiber will be built between this network and other network provider's and customer's networks. Interconnect occurs at a fiber splice vault or fiber termination panel in a customer's building. | N/A | Working through the Environmental Assessment (EA) can be time consuming process. Because of this we have been working concurrently on other tasks that will allow us to be ready to start construction once we have received our Finding of No Significant Impact (FONSI). This has included working on obtaining Rights of Way from local municipalities, railroads, and the Illinois Department of Transportation. These all take time, so doing this at the same time as the EA is being done has been a good use of our time. We have also been going through the selection process of equipment vendors as well as going through the RFP process for selecting our General Contractor. All of these processes take time, so doing these at the same time as the EA is being done has been a good use of our time. | Delta Communications, L.L.C. | 125 | 27 | 9 | 1 | 73 | 28 |  | 37 | 0 | 0 | 300 | N/A | N/A | TRUE
NT10BIX5570100 | 2011 | $44,975.92 | End of Year 2011 is the end of our Q2 Year 2. Our baseline estimated cost per mile for Year 1 to be $56,657 and Year 2 to be $36,972. Our cost of $44,975.92 is in line with our baseline projections. | 0 | N/A | 0 | N/A | I Gig. | In line with baseline | 0 | N/A | 0 | N/A | 0 | N/A | As of the end of 2011 we have not begun to provide broadband service. | As of the end of 2011 we have not begun to provide broadband service. | As of the end of 2011 we have not begun to provide broadband service. | We have not begun providing service, so we have not had any subscribers drop the service. | 106560 | 328 | 0 | 0 | 17432 | 5920 | 82880 | N/A | 800 | 800 | 0 | 0 | Fiber will be built between this network and other network provider's and customer's networks. Interconnect occurs at a fiber splice vault or fiber termination panel in a customer's building. | N/A | Rights of Way and Permitting â€“ This will take longer than expected. To be able to make significant construction progress you must stay ahead of the permitting process. Allow for ample time for Railroad permits as well as certain highway and local permitting. We have been helped by using people that are experienced in dealing with these entities, but the process is still time consuming. You must plan for the time it will take and match that to your desired construction time lines. | Delta Communications, L.L.C. | 125 | 27 | 9 | 1 | 73 | 28 |  | 37 | 0 | 0 | 300 | N/A. We are in negotiations with 6 third party service providers. This process is going slower than expected. Most carriers want at least part of the network to be lit before they sign an agreement. | N/A | TRUE
NT10BIX5570100 | 2012 | 43,127 | Higher than baseline of 36,972 due to higher construction and permitting costs than anticipated. | NA | NA | NA | NA | 1 Gig | In line with baseline plan | NA | NA | 50 Mbps | Slightly lower than baseline of 76.76 for year two, but in line with baseline of 50.95 by the end of year 3. | NA | NA | The average increase in broadband speed has been approximately 38 Mbps. Most of the CAIs we serve had single or multiple T1's before the project. We estimate their prior broadband speeds to be 12 Mbps. Their average speed today is a little over 50Mbps. This gives an average increase of broadband speed of 38 Mbps or 216%. | Ethernet Services ranging in speeds of 10 Mbps to 1 Gbps and Internet Services. | 7a. We have no network management policies to limit bandwidth or prioritize traffic. 7b. We have not limited nor blocked consumers from accessing any legal content, service, service provider, nor application, nor prevented any consumers from attaching any legal device to the network. | No subscribers have dropped the broadband service provided through this project | 106560 | 5699 | 0 | 91069 | 0 | 0 | 9792 | NA | 800 | 800 | 0 | 0 | Fiber will be built between this network and other network provider's and customer's networks. Interconnect occurs at a fiber splice vault or fiber termination panel in a customer's building. | NA | Creating and marketing your brand can be a key factor in making your project sustainable. Clearwave utilizes our own sales and marketing team including business to business account executives. Company team members are avid in attending events of other businesses in the communities. Members have attended: Open houses, grand openings, ribbon cuttings, chamber luncheons and dinners, technology showcases, summits, seminars, and job fairs. Members also present at town hall meetings and other organizational meetings. These events are attended by decision makers and civic leaders. Attendees are given take-home packets full of informational materials including key facts, slideshow handouts, and contact information. Clearwave produces an informative newsletter every quarter, and has made a media presence with news releases, and paid advertising through radio, newspaper, and events. Clearwave also has a social media presence with Facebook, Twitter, and YouTube. | Delta Communications, L.L.C. | 125 | 27 | 9 | 1 | 73 | 28 |  | 37 | 0 | 0 | 300 | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570100 | 2013 | $45,903 | Higher than baseline of 36,972 due to higher construction costs than anticipated. | NA | NA | NA | NA | 1000 Mbps | In line with Baseline | NA | NA | 50.59 Mbps | Within 99% of baseline estimate of 50.95 Mbps. Subscribed speeds range between 10Mbps and 1000 Mbps. 57% of subscribers are getting less than 50 Mbps and 43% are getting 50 Mbps and higher. | NA | NA | The average increase in broadband speed has been approximately 38 Mbps. Most of the CAIs we serve had single or multiple T1's before the project. We estimate their prior broadband speeds to be 12 Mbps. Their average speed today is a little over 50Mbps. This gives an average increase of broadband speed of 38 Mbps or 216%. | Ethernet Services ranging in speeds of 10 Mbps to 1 Gbps and Internet Services. | 7a. We have no network management policies to limit bandwidth or prioritize traffic. 7b. We have not limited nor blocked consumers from accessing any legal content, service, service provider, nor application, nor prevented any consumers from attaching any legal device to the network. | None have dropped service. | 107318 | 9860 | 0 | 97458 | 0 | 0 | 0 | NA | 800 | 800 | 0 | 0 | Fiber will be built between this network and other network provider's and customer's network. Interconnect occurs at a fiber splice vault or fiber termination panel in a customer's building. | NA | Clearwave Communications has successfully completed the construction of 749 miles of fiber and has signed up 230 Community Anchor Institutions for service by the scheduled end date of our project. Lessons learned include a greater appreciation that in a project of this magnitude obstacles and challenges occur almost every week. Being a small company we were able to meet these challenges and make adjustments quickly. In order to react and adjust to these challenges in a timely manner your management structure needs to be lean and efficient. Another lesson learned is that costs of engineering and permitting are significant and can be much higher than expected. The amount of time and expense involved in completing the Environmental Analysis as well as the network design were higher than anticipated. Permitting costs are also a significant expense in being able to complete a project of this size. As an example we had over 80 different railroad permits in our project area. These can be time consuming and expensive and need to be considered when making budgets and time lines. Clearwave was fortunate to have an existing sales team that had a strong presence in most of our proposed service area. Because of this we were able to contract and provide service to 200 of the original 232 CAIs that we listed in our original application and serve 230 CAIs by the end of our project. Highlighted among these 230 CAIs, we were able to greatly improve the bandwidth connectivity at 105 K-12 Schools and 62 Medical facilities. These institutions will be able to benefit from the BTOP initiative for years to come, and our company is proud to have been a part of that initiative. To accomplish a project of this size in this short a period of time you need a management team that is committed to the goals you have. They must be willing to handle setbacks and challenges in a proactive way. You also need to have the ability to communicate and make decisions in an efficient manner. We were fortunate to already have that type of management team and structure in place before the project began. | Delta Communications, L.L.C. | 125 | 27 | 9 | 1 | 73 | 28 |  | 37 | 0 | 0 | 300 | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570101 | 2010 | 0 | No variance | NA | No variance | NA | No variance | 0 | No variance | NA | No variance | 0 | No variance | NA | No variance | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | 11832 | 0 | 0 | 0 | 1092 | 120 | 10620 | NA | 0 | 0 | 0 | 0 | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | - AVFN has learned that finalization of fiber routes, both primary and alternate routes, is a critical path item for commencement and completion of the environmental assessment process. EA consultants must have clear and documented fiber route maps in order to perform the necessary surveys. AVFN advises other applicants to begin the process of route finalization as early as possible. - AVFN has learned that resolving potential duplication of funding issues (AKA overlaps) is a time-consuming process. Other applicants often do not share the same urgency to resolve these issues, and are often unwilling or unable to share detailed street-level maps. AVFN advises other applicants to begin the process to resolve such overlaps as early as possible. - AVFN has learned that securing the eventual commitment of community anchor institutions is an ongoing, time-consuming process. While project planning and construction is underway, applicants must also be communicating consistently with potential CAIs to educate them on the services the network will offer, stay up to date on deadlines (e.g. eRate) faced by those CAIs, set the CAIs expectations on when service will be available, and educate CAIs on the importance of CAI commitment to the network. | Appalachian Valley Fiber Network | 23 | 9 | 3 | 87 | 24 | 16 |  | 4 | 0 | 0 | 166 | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | TRUE
NT10BIX5570101 | 2011 | 0 | N/A. Due to lack of fiber availability, AVFN has only been able to deploy conduit up to this point. | 0 | N/A. AVFN is a purely middle-mile project. | 0 | N/A. AVFN is a purely middle-mile project. | 0 | Due to lack of fiber availability, AVFN has only been able to deploy conduit up to this point. Therefore, no broadband speeds are currently being advertised. | 0 | N/A. AVFN is a purely middle-mile project. | 0 | Due to lack of fiber availability, AVFN has only been able to deploy conduit up to this point. Therefore, no broadband speeds are currently being provided. | 0 | N/A. AVFN is a purely middle-mile project. | N/A. Due to lack of fiber availability, AVFN has not begun to offer services over its network yet. | None. AVFN's business plan is to be purely a wholesale provider. Other retail service providers (affiliated and unaffiliated) will offer retail service over the AVFN network. | None are in place at this time, since fiber availability has prevented AVFN from being able to offer services over the network. AVFN does have a non discrimination and interconnect policy in place and it adheres strictly to the requirements and intent of the BTOP program. | N/A. Due to lack of fiber availability, AVFN has not begun to offer services over the network yet. | 34796 | 0 | 1148 | 0 | 1566 | 0 | 32082 | N/A. Due to lack of fiber availability, AVFN has not begun to offer services over the network yet. | 288 | 72 | 0 | 216 | N/A. AVFN does have collocation space. | None at this time. | Focus on procurement issues early (fiber availability). Set up robust procedures for testing, verification, proofing of constructed assets. Railroad crossings require very advance-notice and should be started early. | Appalachian Valley Fiber Network | 23 | 9 | 3 | 87 | 24 | 16 |  | 4 | 0 | 0 | 166 | Due to lack of fiber availability, AVFN has not begun to interconnect with other service providers yet. | Due to lack of fiber availability, AVFN has not begun to peer with other service providers yet. | TRUE
NT10BIX5570101 | 2012 | 48000 | Cumulative direct middle mile capital costs divided by total new miles. | 0 | N/A. AVFN is a purely middle-mile project. | 0 | N/A. AVFN is a purely middle-mile project. | 10Gbps | Maximum speed offered. | 0 | N/A. AVFN is a purely middle-mile project. | 20Mbps | Average speed of subscribers. | 0 | N/A. AVFN is a purely middle-mile project. | Since AVFN is a wholesale-only, middle mile provider, it does not have visibility into the speeds provisioned by retail customers before and after the AVFN network is introduced. | None. AVFN's business plan is to be purely a wholesale provider. Other retail service providers (affiliated and unaffiliated) will offer retail service over the AVFN network. | AVFN has no bandwidth caps, throttling, blocking of lawful content or other traffic prioritization schemes in place. AVFN supports the free and open nature of the Internet and embraces the FCC's policy on the "Four Freedoms." | None. | 34796 | 0 | 1148 | 0 | 1566 | 0 | 32082 | Parker FiberNet is AVFN's only wholesale customer at this point. AVFN does not have a measurement of the number of strand miles at this time. AVFN leases dark fiber to service providers, including Parker FiberNet, on a customer-connection basis, and these connections can vary in length. | 288 | 72 | 0 | 216 | N/A. AVFN does have collocation space. | None at this time. | Permitting processes can vary greatly from state to state. Do not assume timing is the same or even similar. Focus on procurement issues early (fiber availability). Set up robust procedures for testing, verification, proofing of constructed assets. Railroad crossings require very advance-notice and should be started early. | Appalachian Valley Fiber Network | 23 | 9 | 3 | 87 | 24 | 16 |  | 4 | 0 | 0 | 166 | In 2012, AVFN signed an interconnection agreement with Parker FiberNet. AVFN is currently negotiating three additional interconnect agreements. AVFN has not denied any request to interconnect. | AVNF has signed an agreement for colocation space at the 56 Marietta Telx facility in Atlanta. AVFN is currently coordinating with North Georgia Network (NGN) and Troy Cablevision to peer at the Telx facility. | TRUE
NT10BIX5570101 | 2013 | 52072 | Cumulative direct middle mile capital costs divided by total new miles | 0 | N/A. AVFN is a purely middle-mile project. | 0 | N/A. AVFN is a purely middle-mile project. | 10Gbps | Maximum speed offered | 0 | N/A. AVFN is a purely middle-mile project. | 20Mbps | Average speed of subscribers | 0 | N/A. AVFN is a purely middle-mile project. | Since AVFN is a wholesale-only, middle mile provider, it does not have visibility into the speeds provisioned by retail customers before and after the AVFN network is introduced. | None. AVFN's business plan is to be purely a wholesale provider. Other retail service providers (affiliated and unaffiliated) will offer retail service over the AVFN network. | AVFN has no bandwidth caps, throttling, blocking of lawful content or other traffic prioritization schemes in place. AVFN supports the free and open nature of the Internet and embraces the FCC's policy on the "Four Freedoms." | None. | 34796 | 0 | 1148 | 0 | 1566 | 0 | 32082 | Parker FiberNet is AVFN's only wholesale customer at this point. AVFN does not have a measurement of the number of strand miles at this time. AVFN leases dark fiber to service providers, including Parker FiberNet, on a customer-connection basis, and these connections can vary in length. | 288 | 72 | 0 | 216 | N/A. AVFN does have collocation space. | None at this time. | Permitting processes can vary greatly from state to state. Do not assume timing tis the same or even similar. Focus on procurement issues early (fiber availability). Set up robust procedures for testing, verification, and proofing of constructed assets. Railroad crossings require very advance-notice and should be started early. Overestimate the amount of time it takes to closeout on construction activities with subcontractors. | Appalachian Valley Fiber Network | 23 | 9 | 3 | 87 | 24 | 16 |  | 4 | 0 | 0 | 166 | In 2013, AVFN signed an interconnection agreement with Cartersville FiberCom and Calhoun Telecommunications (Calnet) of Calhoun. AVFN is not currently negotiating any additional interconnect agreements. AVFN has not denied any request to interconnect. | None for 2013 | TRUE
NT10BIX5570102 | 2010 | 0 | In this and all upcoming narratives, the following remains true: The Baseline Report collected a Year 1 figure, which UAMS understood to include the first 12 months of the project period. However, the 2010 Annual Report appears to collect information on progress on a calendar year basis (January 1 - December 31), rather than a 12-month basis (First month of Project Period to 12th month of Project Period). Since the UAMS BTOP grant was awarded in August 2010, the outcomes reported on this 2010 Annual Report only embody the first five months of the grant period, which was dedicated to Environmental Assessment development and planning activities. As such, the figures provided in the Baseline Report differ from those reported in this 2010 Annual Report for the reasons described. As verification, the reported figures in this report are on target with the progress UAMS expected by Month Five of the first year of the project period. | 0 | N/A | 0 | N/A | 0 | See explanation above. The Baseline Report figure and the figure reported here differ in terms of timing: Baseline reflects first 12 months of the project period; whereas the Annual Report reflects the first 5 months of the project. The reported outcome is accurate to anticipated progress by Month 5 of the project period. | 0 | N/A | 0 | See explanation above. The Baseline Report figure and the figure reported here differ in terms of timing: Baseline reflects first 12 months of the project period; whereas the Annual Report reflects the first 5 months of the project. The reported outcome is accurate to anticipated progress by Month 5 of the project period. | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | In this, the first five months of the Arkansas Healthcare, Higher Education, Public Safety, & Research Integrated Broadband Initiative, the University of Arkansas System has noted several best practices and lessons learned that may be helpful in other BTOP projects, Some of these comments may only be helpful for projects in the planning phases of their BTOP projects. At such a time when these comments are circulated, most BTOP projects will have progressed beyond such a stage. * Meet weekly with your Federal Program Officer (FPO) and collect non-pressing questions for your time with him or her. Contact your FPO directly for pressing questions. * For in-kind match items, begin filing Uniform Commercial Codes (UCCs) for the contributed items as soon as possible. Many items may be included on a single form. * Create a BTOP project website and launch promptly to route requests and news updates for your partners and visitors. * To organize numerous vendor contacts, create a distribution list for vendors to notify them when Request for Proposals and related requests are released in respect to your BTOP-funded project. * Designate a single person to act as primary contact to the FPO and other Federal officials to help streamline communication. | University of Arkansas System | 0 | 8 | 21 | 12 | 410 | 1 |  | 6 | 0 | 0 | 458 | N/A | N/A | TRUE
NT10BIX5570102 | 2011 | 0 | The network is still being built-out. Per instructions, the information is N/A until deployment for the network is complete and in service. | 0 | N/A | 0 | N/A | 10Gpbs | The ARE-ON backbone can support connection speeds up to 10Gbps. Current plans are for 1Gbps connections to all ARE-ONâ€™s CAIs. | 0 | N/A | 1Gbps | The ARE-ON backbone can support connection speeds up to 10Gbps. Current plans are for 1Gbps connection to all ARE-ONâ€™s CAIs. | 0 | N/A | The project's healthcare CAI were provided with new broadband, therefore their increase would be 100%. This consists of 307 sites with <10Mbps; 82 sites with >/= 10Mbps and <50Mbps; seven sites with >/= 100Mbps and <1000Mbps. The average broadband speed for the two-year colleges (12 of 22 respondents) is 21.4Mbps (minimum is 6Mbps, maximum is 56Mbps). The project is providing 1000Mbps (1Gbps) connections to each of the schools, for an average increase of 978.6Mbps. The individual schools can opt for any commodity Internet bandwidth up to the full 1000Mbps per their campus needs and budget. The increase was calculated as the current average broadband speed subtracted from the new connection speed of 1000Mbps. | N/A | The project currently does not have any portion of the expanded network completed or in service. However, the projectâ€™s network management policies are to provide commodity Internet services up to the amount of bandwidth contracted for by the CAI and rate limit based on that contracted bandwidth. However, connections to other ARE-ON members and to research networks, such as Internet2 and National LambdaRail, are not rate limited. No traffic prioritization is planned or occurring unless specifically requested by the CAI (such as to give video conferencing traffic a higher priority over that CAIâ€™s other traffic). ARE-ON does not block or filter content of any type to its members. ARE-ON has no policies or practice that restricts the connection of any legal device to its network. However, ARE-ONâ€™s members, which are institutions of higher education, define their own policies about content filtering for their users or what devices they will permit to connect to their respective campus networks. | N/A | 10240 | 0 | 0 | 0 | 0 | 4141 | 6099 | N/A | 200 | 196 | 0 | 4 | Network providers will interconnect with our network at meet points outside our collocation facilities and transition via our fiber into the collocation facility. Network providers can also interconnect at one of our member institutions where we maintain a presence. | N/A | Items to consider should include standardization of data, data management and face-to-face contact in the field with CAI. Structure a strong plan for inventory management and support. Block time for adequate reporting preparation and submission for both federal and internal needs. For fiber construction, use only contractors experienced in installing, splicing, and testing the type of fiber plant you are building, such as long-haul, metro, residential, etc. Be as specific as possible about every aspect of the construction, including setting minimum standards for testing and acceptance. In selecting the contractors, consider an interview or selection process that identifies specific skill levels needed for the type of fiber and writing specifications for such in the contract. Pay for and perform independent inspection by your engineering firm to ensure that construction meets all engineering design standards. For hut construction, be as detailed as possible on every aspect of their construction. Consider having your hut manufacturer install as much internal infrastructure as possible, including generators, racks, power, security, etc. at the factory. | University of Arkansas System | 0 | 8 | 21 | 12 | 410 | 1 |  | 6 | 0 | 0 | 458 | N/A | N/A | TRUE
NT10BIX5570102 | 2012 | 0 | The network is still being built-out. Per instructions, the information is N/A until deployment for the network is complete and in service. | 0 | N/A | 0 | N/A | 10Gbps | The Arkansas e-Link backbone can support connection speeds up to 10 Gbps. | 0 | N/A | 1Gbps | The Arkansas e-Link backbone can support connection speeds up to 10Gbps. Current plans are for 1Gbps connection to all Higher Ed CAIs. | 0 | N/A | The project's healthcare CAIs were provided with new broadband, therefore their increase would be 100%. This consists of 291 sites with <10Mbps; 77 sites with >/= 10 Mbps and <50 Mbps; five (5) sites with >/= 50 Mbps and <100 Mbps; and, 1 site with <1000 Mbps. At the end of the project, the average broadband speed for the two-year colleges (12 of 22 respondents) is 21.4Mbps (minimum is 6Mbps, maximum is 56Mbps). The project is providing 1000Mbps (1Gbps) connections to each of the schools receiving fiber connectivity, for an average increase of 978.6Mbps, and 100Mbps connections to each of the schools receiving broadband circuit connectivity, for an average increase of 78.6Mbps. The individual schools can opt for any commodity Internet bandwidth up to the full capacity of the connection per their campus needs and budget. The increase was calculated as the current average broadband speed subtracted from the new connection speed of 1000Mbps or 100Mbps. | N/A | Arkansas e-Link currently does not have any portion of the expanded network completed with the exception of Southern Arkansas University, Magnolia. The projectâ€™s network management policies are to provide commodity Internet services up to the amount of bandwidth contracted for by the CAI and rate limit based on that contracted bandwidth. However, connections to other ARE-ON members and to research networks, such as Internet2 and National LambdaRail, are not rate limited. No traffic prioritization is planned or occurring unless specifically requested by the CAI (such as to give video-conferencing traffic a higher priority over that CAIâ€™s other traffic). ARE-ON does not block or filter content of any type to its members. ARE-ON has no policies or practice that restricts the connection of any legal device to its network. However, ARE-ONâ€™s members, which are institutions of higher education, define their own policies about content filtering for their users or what devices they will permit to connect to their respective campus networks. | N/A | 11687 | 1574 | 0 | 9848 | 9 | 0 | 256 | N/A | 200 | 196 | 0 | 4 | Network providers will interconnect with the network at meet points outside our collocation facilities and transition via our fiber into the collocation facility. ARE-ON can provide a limited amount of space for collocation within the facilities. ARE-ON typically connects to its members (colleges and universities) via direct fiber into the customer's campus. Members can also interconnect at a member institutions where we maintain a presence. | N/A | UAS suggests these best practices/lessons learned: â€¢ Start the Environmental Assessment (EA) process as early as possible and monitor consultant for timely completion. â€¢ Develop and implement operational procedures. â€¢ To help stay focused, review project goals often with your team. â€¢ Identify and study institutional and regulatory requirements. â€¢ Develop a checks and balances system to ensure that sub-recipient is compliant with regulatory requirements. â€¢ Maintain effective communication with partners and vendors by keeping them informed and updated. â€¢ Develop strategy for inventory management. â€¢ Maintain schedule of compliance deadlines. â€¢ Define data that is needed from CAIs and develop comprehensive plan for acquiring and managing the data. â€¢ Keep a reference log of decisions made between recipient and NTIA program officer and/or other representatives of NTIA. â€¢ Allow sufficient time in the process to develop, release, evaluate, and award bids for RFPs, including order lead time to avoid delays during deployment. â€¢ When selecting contractors for fiber construction, consider an interview or selection process that identifies specific skill levels needed and include these written specifications in the contract. â€¢ Use only contractors experienced in installing, splicing, and testing the type of fiber plant you are building, such as long-haul, metro, residential, etc. â€¢ Contracts should include specifics about every aspect of the construction, including setting minimum standards for testing and acceptance. â€¢ Perform independent inspection by your engineering firm to ensure that construction meets all engineering design standards. â€¢ Be as detailed as possible on every aspect of hut construction. â€¢ Consider having the hut manufacturer install as much internal infrastructure as possible, including generators, racks, power, security, etc. at the factory. | University of Arkansas System | 0 | 8 | 21 | 12 | 410 | 1 |  | 6 | 0 | 0 | 458 | N/A | N/A | TRUE
NT10BIX5570102 | 2013 | $146,498 | This is calculated as the total allocated cost of construction of fiber and conduit, engineering, and splicing of all fiber laterals constructed in the project. | 0 | N/A | 0 | N/A | 10 Gb | The Arkansas e-Link backbone can support connection speeds up to 10 Gb. | 0 | N/A | 1 Gb | All ARE-ON fiber-connected CAIs have 1 Gb connections, and all ARE-ON circuit-connected CAIs have 100 Mb. | 0 | N/A | The project's healthcare CAIs were provided with improved broadband, therefore their increase would be 100%. This consists of: 296 sites with <10 Mb 80 sites with >/= 10 Mb and <50 Mb 8 sites with >/= 50 Mb and <100 Mb 21sites with >/=100 Mb and <1 Gb 9 sites with >/= 1 Gb The remaining 44 sites received BTOP-funded equipment but are using their own connectivity bringing our total to 458. The average broadband speed is 980 Mb. Typical broadband speeds for the community colleges was previously 6-20 Mb. All college CAIs received 1 Gb connections. The average was calculated by subtracting the high end of the two numbers. | N/A | 7a. The Arkansas e-Link portion of the network is a membership-only network, open only to defined and HIPAA compliant medical purposes. This is not a public, consumer-oriented network. The fiber projectâ€™s (ARE-ON) network management policies are to provide commodity Internet services up to the amount of bandwidth contracted for by the CAI and rate limit based on that contracted bandwidth. However, connections to other ARE-ON members and to research networks, such as Internet2 and National LambdaRail, are not rate limited. No traffic prioritization is planned or occurring unless specifically requested by the CAI (such as to give video-conferencing traffic a higher priority over that CAIâ€™s other traffic). ARE-ON does not block or filter content of any type to its members. 7b. Only standards-compliant devices will function on the e-Link network. The e-Link network is not a public, consumer-oriented network. ARE-ON has no policies or practice that restricts the connection of any legal device to its network. However, ARE-ONâ€™s members, which are institutions of higher education, define their own policies about content filtering for their users or what devices they will permit to connect to their respective campus networks. | N/A | 11820 | 1583 | 0 | 10237 | 0 | 0 | 0 | N/A | 8738 | 8310 | 114 | 314 | Network providers will interconnect with the network at meet points outside our collocation facilities and transition via our fiber into the collocation facility. Network providers can also interconnect at one of our member institutions where we maintain a presence. | N/A | UAS suggests these best practices/lessons learned: â€¢ Start the Environmental Assessment (EA) process as early as possible and monitor consultant for timely completion. â€¢ Develop and implement operational procedures. â€¢ To help stay focused, review project goals often with your team. â€¢ Identify and understand institutional and regulatory requirements. â€¢ Develop a checks and balances system to ensure that sub-recipient is compliant with regulatory requirements. â€¢ Maintain effective communication with partners and vendors. â€¢ Develop strategy for inventory management. â€¢ Maintain schedule of compliance deadlines. â€¢ Define data that is needed from CAIs and develop comprehensive plan for acquiring and managing the data. â€¢ Keep a reference log of decisions made between recipient and NTIA program officer and/or other representatives of NTIA. â€¢ Allow sufficient time in the process to develop, release, evaluate, and award bids for RFPs, including order lead time to avoid delays during deployment. â€¢ When selecting contractors for fiber construction, consider an interview or selection process that identifies specific skill levels needed and include these written specifications in the contract. â€¢ Use only contractors experienced in installing, splicing, and testing the type of fiber plant you are building, such as long-haul, metro, residential, etc. â€¢ Contracts should include specifics about every aspect of the construction, including setting minimum standards for testing and acceptance. â€¢ Perform independent inspection by your engineering firm to ensure that construction meets all engineering design standards. â€¢ Be as detailed as possible on every aspect of hut construction. â€¢ Consider having the hut manufacturer install as much internal infrastructure as possible, including generators, racks, power, security, etc. at the factory. â€¢ Ensure there are comprehensive contracts with all vendors that assure grant requirements are met and flexibility is included. | University of Arkansas System | 0 | 8 | 21 | 12 | 410 | 1 |  | 6 | 0 | 0 | 458 | N/A | N/A | TRUE
NT10BIX5570103 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No activity for year ending December 31, 2010. | No activity for year ending December 31, 2010. | No activity for year ending December 31, 2010. | No activity for year ending December 31, 2010. | 11658 | 0 | 0 | 0 | 896 | 906 | 9856 | No activity for year ending December 31, 2010. | 0 | 0 | 0 | 0 | No activity for year ending December 31, 2010. | No activity for year ending December 31, 2010. | Moving from proposal to actual award and implementation has caused the management team to review, refine and often modify preliminary program planning elements, desktop engineering assumptions, initial line item allocations and management practices. Estimates of those participating in the network, thus affecting the overall sustainability model, has been significantly enhanced now that the project is funded; requiring us to re-budget the capital resources needed to meet expected demand. The real lesson learned here is that once programs have a firm foundation, the leadership team must be flexible enough to meet new obligations and opportunities; all while ensuring compliance with BTOP policies. | Nevada Hospital Association | 134 | 58 | 2 | 6 | 37 | 73 |  | 0 | 5 | 0 | 315 | N/A | N/A | TRUE
NT10BIX5570103 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No Activity for year ending December 31, 2011. | No Activity for year ending December 31, 2011. | No Activity for year ending December 31, 2011. | No Activity for year ending December 31, 2011. | 63040 | 0 | 0 | 0 | 1219 | 4515 | 57306 | No Activity for year ending December 31, 2011. | 0 | 0 | 0 | 0 | No Activity for year ending December 31, 2011. | No Activity for year ending December 31, 2011. | Throughout the Environmental Assessment process, the management team has had to review, refine and modify aspects of the preliminary program planning elements; specifically addressing Tribal relation concerns and their impact upon network design. By including alternative routes within the EA as possible contingency plans, the network design was able to adapt as necessary. | Nevada Hospital Association | 134 | 58 | 2 | 6 | 37 | 73 |  | 0 | 5 | 0 | 315 | 1) 0 2) 2 3) 0 | N/A | TRUE
NT10BIX5570103 | 2012 | $37,897.83 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | 0 | N/A | 0 | N/A | 1G | Increased from 100 Mbps to 1G to meet market demand. | 1G | Increased from 100 Mbps to 1G to meet market demand. | N/A | We have not yet started providing services. Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | N/A | We have not yet started providing services. Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | We are not yet providing services to CAIs. Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | No activity for year ending December 31, 2012 | 7a. The Nondiscrimination and Network Management Policy and Interconnection Policy information are in place, available and published on the Subrecipient's Web site, the network operators of the project. A link to the policies are posted on the NHA Web site. 7b. We are not yet providing services to consumers therefore we have not limited or blocked consumers from accessing any lawful content, service, service provider, or application or prevented any consumers from attaching any legal device to the network. | No activity for year ending December 31, 2012. | 47756 | 0 | 0 | 13858 | 1088 | 0 | 32810 | No activity for year ending December 31, 2012. | 0 | 0 | 0 | 0 | No activity for year ending December 31, 2012. | No activity for year ending December 31, 2012. | NHA has encountered challenges during year two of the project construction and environmental assessment process. Continuous evaluation, pre-planning tasks and modification in the project planning elements; specifically in acquiring local permitting; agreements for rights-of-way and other land easements; utility pole agreements and make-ready work; and other deployment activities helps identify and address barriers quickly to ensure timely project progress. | Nevada Hospital Association | 134 | 58 | 2 | 6 | 37 | 73 |  | 0 | 5 | 0 | 315 | 1) 2 (SwitchNAP - Las Vegas - 200M IP and Zayo - Reno - 200M IP) 2) 0 3) 0 (We have not denied interconnection to anyone.) | 1) 2 (SwitchNAP - Las Vegas - BGP Peering and Zayo - Reno - BGP Peering) 2) 0 3) 0 (We have not denied interconnection to anyone.) | TRUE
NT10BIX5570103 | 2013 | 37897.83 | Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | 0 | N/A | 0 | N/a | 1G | Increased from 100 Mbps 1G to meet market demand. | 1G | Increased from 100 Mbps 1G to meet market demand. | N/A | We have not yet started providing services. Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | N/A | We have not yet started providing services. Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | We are not yet providing services to CAIs. Projected progress meaningfully altered due to delay in acquiring permits from utility providers related to fiber installation. Additionally, a delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | No activity for year ending December 31, 2013. | 7a. The Nondiscrimination and Network Management Policy and Interconnection Policy information are in place, available and published on the Subrecipient's Web site, the network operators of the project. A link to the policies is posted on the NHA Web site. 7b. We are not yet providing services to consumers therefore we have not limited or blocked consumers from accessing any lawful content, service, service provider, or application or prevented any consumers from attaching any legal device to the network. | No activity for year ending December 31, 2013. | 47756 | 0 | 0 | 13858 | 1088 | 0 | 32810 | No activity for the year ending December 31, 2013. | 0 | 0 | 0 | 0 | No activity for the year ending December 31, 2013. | No activity for the year ending December 31, 2013. | N/A | Nevada Hospital Association | 134 | 58 | 2 | 6 | 37 | 73 |  | 0 | 5 | 0 | 315 | N/A | N/A | TRUE
NT10BIX5570104 | 2010 | 0 | Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 0 | N/A | 0 | N/A | 0 | Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 0 | N/A | 0 | Construction not yet begun per our baseline schedule and required Environmental Assessment activities | 0 | N/A | N/A;Construction not yet begun per our baseline schedule and required Environmental Assessment activities | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities and services are not yet being offered | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities and services are not yet being offered | 38394 | 0 | 0 | 0 | 7082 | 704 | 30608 | N/A Construction not yet begun per our baseline schedule and required Environmental Assessment activities and services are not yet being offered | 0 | 0 | 0 | 0 | Contact Network Inc. is in process of negotiating collocation space in Jackson, MS and negotiations will be finalized in January 2011. In addition to this collocation space, we will have communication huts in each county. Service providers or customers that wish to make their own last mile connection into the network will be able to interconnect with us at the hut. We will also assist providers and customers with their last mile connection. | N/A | No comment | Contact Network Inc. d/b/a InLine | 163 | 22 | 7 | 20 | 80 | 78 |  | 139 | 23 | 2 | 534 | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | N/A; Construction not yet begun per our baseline schedule and required Environmental Assessment activities | TRUE
NT10BIX5570104 | 2011 | 38,521 | variance is due to higher fiber costs, higher than anticipated costs related to railroad crossing and aerial permits as well as up front expenditures that should level out (ie: make ready costs for aerial, one time fees associated with permitting etc.) | 0 | N/A | 0 | N/A | 1000Mbps | No variance from baseline | 0 | N/A | 980Mbps | Currently we have 46 subscribers receiving 1000Mpbs and one receiving 10Mbps | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions we are servicing is 968Mbps. This number was calculated based on the fact that all 47 of our current customers were receiving 1.5Mpbs before upgrading to our service. Forty six of our current customers are receiving 1000Mbps and one is receiving 10Mbps. | Contact Network Inc will provide multiple service tiers across the network with access speeds ranging from 10 to 1000 MBps. Currently, the retail services offered include 10Mbps, 100Mbps and 1000Mbps Private Network Connectivity, 10Mbps and 100Mbps Fiber connection with internet access and a public safety only option for 100Mbps Fiber connection with separate VLAN's to other connected Anchor Institutions. | We monitor network utilization throughout our network, as well as traffic to other autonomous networks on the public Internet. We use these metrics to determine if additional network resources are needed to provide our customers with effective Internet access. These metrics are not utilized in any way to filter or manipulate network traffic, nor are they used to prioritize services to customers based on type of traffic. During times of extremely high network traffic, application-neutral techniques may be utilized to ensure minimum advertised speeds to all clients. With the exception of blocking content, or sources of content that are harmful to the operation our network, or where a client contracts with us for a service that limits access to dangerous or undesirable content, we do not discriminate or prioritize one source or type of content over any others. Furthermore, we support and adhere to the principles contained in the FCCâ€™s August 2005 Broadband Policy Statement" (more often called the agency's Internet Policy Statement). | No subscribers have dropped the broadband service provided through this project. | 38602 | 286 | 0 | 9318 | 7082 | 704 | 30816 | As of December 31, 2011, Contact Network Inc. does not have any wholesale customers leasing dark fiber. | 1035 | 260 | 0 | 775 | In addition to the collocation space described in question eleven, Contact Network Inc. has designed our network in such a way that we will support additional splice points at either our Community Anchor Institutuion (or other) end points, as well as in telecom hut facilities. | We have no subcontracts or sub grants. | No comment | Contact Network Inc. d/b/a InLine | 163 | 22 | 7 | 20 | 80 | 78 |  | 139 | 23 | 2 | 534 | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | TRUE
NT10BIX5570104 | 2012 | 44669 | variance is due to higher fiber costs, higher than anticipated costs related to railroad crossing and aerial permits as well as up front expenditures that should level out (ie: make ready costs for aerial, one time fees associated with permitting etc.) | 0 | N/A | 0 | N/A | 1000Mbps | No variance from baseline | 0 | N/A | 838Mbps | Currently we have nine subscribers receiving 10Mpbs and the remainder are receiving 1000Mbps service. | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions we are servicing is 836Mbps. This number was calculated based on the fact that all 55 of our current customers were receiving 1.5Mpbs before upgrading to our service. Forty Six of our current customers are receiving 1000Mbps and the rest are receiving 10Mbps. | Contact Network Inc will provide multiple service tiers across the network with access speeds ranging from 10 to 1000 MBps. Currently, the retail services offered include 10Mbps, 100Mbps, 500Mbps and 1000Mbps Private Network Connectivity, 10Mbps and 100Mbps Fiber connection with internet access and a public safety only option for 100Mbps Fiber connection with separate VLAN's to other connected Anchor Institutions. | We monitor network utilization throughout our network, as well as traffic to other autonomous networks on the public Internet. We use these metrics to determine if additional network resources are needed to provide our customers with effective Internet access. These metrics are not utilized in any way to filter or manipulate network traffic, nor are they used to prioritize services to customers based on type of traffic. During times of extremely high network traffic, application-neutral techniques may be utilized to ensure minimum advertised speeds to all clients. With the exception of blocking content, or sources of content that are harmful to the operation our network, or where a client contracts with us for a service that limits access to dangerous or undesirable content, we do not discriminate or prioritize one source or type of content over any others. Furthermore, we support and adhere to the principles contained in the FCCâ€™s August 2005 Broadband Policy Statement" (more often called the agency's Internet Policy Statement). | No subscribers have dropped the broadband service provided through this project. | 31495 | 390 | 100 | 17672 | 746 | 0 | 12587 | We are leasing 25 miles of dark fiber or 100 strand miles to Windstream. | 1035 | 260 | 11 | 764 | In addition to the collocation space described in question eleven, Contact Network Inc. has designed our network in such a way that we will support additional splice points at either our Community Anchor Institutuion (or other) end points, as well as in telecom hut facilities. | We have no subcontracts or sub grants. | The most important lesson that we have learned is to plan as far ahead as possible. The focus of this being on permits for railroads, DOT and pole attachment. Some of these permits can take months to process and without proper planning, the project could become delayed for that time while waiting on approval. | Contact Network Inc. d/b/a InLine | 163 | 22 | 7 | 20 | 80 | 78 |  | 139 | 23 | 2 | 534 | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | TRUE
NT10BIX5570104 | 2013 | 47477 | variance is due to higher fiber costs, higher than anticipated costs related to railroad crossing and aerial permits | 0 | N/A | 0 | N/A | 1000Mbps | No variance from baseline | 0 | N/A | 909Mbps | Currently we have 5 subscribers receiving 10Mbps; 4 receiving 100Mbps and 85 receiving 1000Mbps | 0 | N/A | The average increase in broadband speed provided to the community anchor institutions we are servicing is 836Mbps. This number was calculated based on the fact that 84 of our current customers were receiving 10Mpbs, the remainder had 1.5Mbps before upgrading to our service. Eight five of our current customers are receiving 1000Mbps, four are receiving 100Mbps and the rest are receiving 10Mbps. | Contact Network Inc will provide multiple service tiers across the network with access speeds ranging from 10 to 1000 MBps. Currently, the retail services offered include 10Mbps, 100Mbps, 500Mbps and 1000Mbps Private Network Connectivity, 10Mbps and 100Mbps Fiber connection with internet access and a public safety only option for 100Mbps Fiber connection with separate VLAN's to other connected Anchor Institutions. | We monitor network utilization throughout our network, as well as traffic to other autonomous networks on the public Internet. We use these metrics to determine if additional network resources are needed to provide our customers with effective Internet access. These metrics are not utilized in any way to filter or manipulate network traffic, nor are they used to prioritize services to customers based on type of traffic. During times of extremely high network traffic, application-neutral techniques may be utilized to ensure minimum advertised speeds to all clients. With the exception of blocking content, or sources of content that are harmful to the operation our network, or where a client contracts with us for a service that limits access to dangerous or undesirable content, we do not discriminate or prioritize one source or type of content over any others. Furthermore, we support and adhere to the principles contained in the FCCâ€™s August 2005 Broadband Policy Statement" (more often called the agency's Internet Policy Statement). | No subscribers have dropped the broadband service provided through this project. | 31696 | 617 | 100 | 30223 | 0 | 0 | 756 | We are leasing 25 miles of dark fiber or 100 strand miles to Windstream. | 1035 | 260 | 11 | 764 | In addition to the collocation space described in question eleven, Contact Network Inc. has designed our network in such a way that we will support additional splice points at either our Community Anchor Institutuion (or other) end points, as well as in telecom hut facilities. | We have no subcontracts or sub grants. | The most important lesson that we have learned is to plan as far ahead as possible. The focus of this being on franchise agreements and permits for railroads, DOT and pole attachment. Some of these permits can take months to process and without proper planning, the project could become delayed for that time while waiting on approval. | Contact Network Inc. d/b/a InLine | 163 | 22 | 7 | 20 | 80 | 78 |  | 139 | 23 | 2 | 534 | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | Contact Network Inc. did not enter into any interconnection, peering and/or transit agreements during this annual reporting period nor are we negotiation any at this time. Contact Network Inc. has not received any requests for interconnection. | TRUE
NT10BIX5570105 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Treasury, New Jersey Department of | 0 | 0 | 5 | 3 | 1 | 73 |  | 2 | 1 | 0 | 85 | N/A | N/A | TRUE
NT10BIX5570105 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Treasury, New Jersey Department of | 0 | 0 | 5 | 3 | 1 | 73 |  | 2 | 1 | 0 | 85 | N/A | N/A | TRUE
NT10BIX5570105 | 2012 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | PLEASE NOTE: The data provided in response to questions 15 and 16 below are simply re-produced from the State's most recent Annual PPR, because they reflect the currently approved project, though that original project direction has been overtaken by events. Due to regulatory and budgetary issues stemming from the passage in February 2012 of the Middle Class Tax Relief and Job Creation Act (for example, NTIA's partial suspension of grant funds, the FCC's termination of the State's conditional permission to use the 700 MHz public safety broadband spectrum, and FirstNet's uncertainty whether it will permit the State to use such spectrum), the direction and budget of the State's project is in flux. The State has proposed a revised project to FirstNet; FirstNet has stated that it will respond to the State's proposal in February 2013. The State intends that, with FirstNet's guidance, it will then submit to NTIA a revised project budget, including revised data in response to questions 15 and 16 below. | Treasury, New Jersey Department of | 0 | 0 | 5 | 3 | 1 | 73 |  | 2 | 1 | 0 | 85 | N/A | N/A | TRUE
NT10BIX5570105 | 2013 | 0 | Based on the newly approved project scope, network miles will not apply to New Jersey moving forward. Because of the project focus on deployables , middle-mile calculations were removed from the project | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | The New Jersey BTOP team will purchase 37 deployable assets equipped with microwave and satellite backhaul, and end-user devices. The project calls for allocating 27 deployable assets (COWs and SOWs) for the three proof-of-concept networks, and 10 assets in ready standby which will be deployed as necessary throughout the State and Region. The deployables based networks will include LTE equipment, microwave, satellite, and appropriate Band Class 14 devices (Band Class 14 is the portion of radio spectrum that is licensed to FirstNet and designated for broadband services for the public safety community). The New Jersey BTOP team will procure User Equipment (UEs) â€“ specifically vehicular modems, dongles (USB wireless antenna devices), tablets and air cards â€“ that can be used with the LTE Band Class 14 services. Users of the deployable-based network will include State law enforcement, fire service, EMS and NJ Transit personnel. | N/A | We currently don't have any best practices/lessons learned to share with other BTOP projects. | Treasury, New Jersey Department of | 0 | 0 | 5 | 3 | 1 | 73 |  | 2 | 1 | 0 | 85 | N/A | N/A | TRUE
NT10BIX5570106 | 2010 | 0 | NA | 0 | NA | 0 | NA | 100 mbps | Same as baseline | 0 | NA | 60 | NA | 0 | NA | NA | NA | 7a. NA 7b NA | NA | 80 | 0 | 80 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | NA | Multitasking for the project is essential in order to get a headstart on as many issues as possible. There are always delays caused by the schedules of various parties, weather, and unanticipated circumstances. Proactive and persistent contact with government agencies is essential in keeping tasks moving forward. Having one individual to oversee and understanding all aspects of the project is beneficial for keeping the tasks on schedule. Integration of the tasks by team meetings helps the coordinator have a firm grasp of the tracking and understanding of the reporting requirements. | Pyramid Lake Paiute Tribe | 1 | 1 | 0 | 1 | 2 | 4 |  | 12 | 4 | 0 | 25 | NA | NA | TRUE
NT10BIX5570106 | 2011 | 0 | NA | 0 | NA | 0 | NA | 100 | Same as Baseline | 0 | NA | 0 | NA | 0 | NA | NA | NA | 7a. NA 7b. NA | NA | 6336 | 0 | 0 | 0 | 32 | 0 | 6304 | NA | 0 | 0 | 0 | 0 | Presently we do not own collocation space. The dark fiber (IRU) with Level-3 allows us to chose between providers in Reno, NV. We have the option of buying bandwidth from Charter Communications, Level-3, At&t and the California Broadband Coalition. The California Broadband Coalition is building a Network Operations Center next to Level-3s' building which will increase the number of providers available to us. | NA | NA | Pyramid Lake Paiute Tribe | 1 | 1 | 0 | 1 | 2 | 4 |  | 12 | 4 | 0 | 25 | NA | NA | TRUE
NT10BIX5570106 | 2012 | 93412 | The electronics have not been purchased yet and will increase this amount to get us back on track with the baseline data. | 0 | NA | 0 | NA | 100 Mbps | Same as Baseline | 0 | NA | 0 Mbps | This is the average speed we expect our customers to use. | 0 | NA | NA | NA | 7a. The service level agreements will dictate the the limitations on the bandwidth offered. 7b We will not block or limit any consumer from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | NA | 6336 | 0 | 0 | 3024 | 3312 | 0 | 0 | NA | 0 | 0 | 0 | 0 | Presently we do not own collocation space. The dark fiber (IRU) with Level-3 allows us to chose between providers in Reno, NV. We have the option of buying bandwidth from Charter Communications, Level-3, At&t and the California Broadband Coalition. The California Broadband Coalition is building a Network Operations Center next to Level-3s' building which will increase the number of providers available to us. | NA | Multitasking for the project is essential in order to get a headstart on as many issues as possible. There are always delays caused by the schedules of various parties, weather, and unanticipated circumstances. Proactive and persistent contact with government agencies is essential in keeping tasks moving forward. Having one individual to oversee and understanding all aspects of the project is beneficial for keeping the tasks on schedule. Integration of the tasks by team meetings helps the coordinator have a firm grasp of the tracking and understanding of the reporting requirements. | Pyramid Lake Paiute Tribe | 1 | 1 | 0 | 1 | 2 | 4 |  | 12 | 4 | 0 | 25 | NA | NA | TRUE
NT10BIX5570106 | 2013 | $99,941 | Baseline was 99,094. There was a slight increase due to site prep construction costs. | 0 | NA | 0 | NA | 100 MBPS | No variance | 100 MBPS | No Variance | 60 MBPS | No Variance | 0 | NA | Average increase is 58.5 mbps. Average speed (using bandwidth testing) is 60 mbps. The maximum current service capability of 100 mbps is shared among 25 CAIs A prior maximum of 1.5 mbps was shared among 21 CAIs. Therefore the average increase is 60 mbps - 1.5 mbps = 58.5 mbps. | Retail services will be 5 - 10 mbps shared service, >= 10 mbps dedicated service and 100 mbps shared service. Attachment has full description and pricing for proposed services. | Bandwidth limitations will be based upon level of service. We will not block retail or commercial customers from accessing any lawful content, service service provider, or application. We will not prevent consumers from attaching any legal device to the network | Two have decline service prior to being activated. The grade school was connected to another provider's fiber under a county wide E Rate program with which we were unable to bid for service. A juvenile treatment facility has declined service at this time, however they indicated that they may be interested in the near future. | 6336 | 3312 | 0 | 3024 | 0 | 0 | 0 | NA | 425 | 225 | 0 | 200 | NA | NA | Interaction with state and federal agencies with similar projects provides potential opportunities for interconnection. In addition, contact with state agencies involved with economic development provides information and contacts with potential business customers. | Pyramid Lake Paiute Tribe | 1 | 1 | 0 | 1 | 2 | 4 |  | 12 | 4 | 0 | 25 | NA | NA | TRUE
NT10BIX5570106 | 2014 | 99941 | Baseline was 99,094. There was a slight increase due to site prep construction consts. | 0 | NA | 0 | NA | 100 MBPS | No Variance | 100 MBPS | No Variance | 60 MBPS | No Variance | 0 | NA | Average increase is 58.5 mbps. Average speed (using bandwidth testing) is 60 mbps. The maximum current service capability of 100 mbps is shared among 25 CAIs. A prior maximum of 1.5 mbps was shared among 21 CAIs. Therefore the average increase is 60 mbps - 1.5 mbps = 58.5 mbps. | Retail services will be 1) 5-10 mbps shared service, 2) >= 10mbps dedicated service and 3) 100 mbps shared service. Attachment has full description and pricing for proposed services. | Bandwidth limitations will be based upon level of service. We will not block retail or commercial customers from accessing any lawful content, service provider, or application. We will not prevent customers from attaching any legal device to the network. | No one has dropped service during this reporting period. | 6336 | 3312 | 0 | 3024 | 0 | 0 | 0 | NA | 425 | 225 | 0 | 200 | NA | NA | Because of the short reporting period, there hasn't been much time for experiences to provide much insight. However there is one area that we are learning needs to be carefully thought out for sustainability. If the organization operating the network needs to rely on outside vendors for facility and equipment support, it is good to have more than one vendor knowledgeable on each area of the system. Good designs and individuals that understand the operations at even a high level, can be instrumental in assisting vendors with understanding the system for solving problems and extending capabilities. | Pyramid Lake Paiute Tribe | 1 | 1 | 0 | 1 | 2 | 4 |  | 12 | 4 | 0 | 25 | NA | NA | TRUE
NT10BIX5570107 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | Our connections are all anticipated to be at the gigabit or greater data rate. | No network is built at this time so these figures are not yet available. | We have not yet had to incorporate any network policy changes to date but we anticipate that our System Policy will need to change to reflect the non-discrimination provisions of the NTIA grant. We do not block or limit any bandwidth within our customers committed data rates. | None. | 4422 | 264 | 592 | 3566 | 4422 | 592 | 3566 | N/A | 0 | 0 | 0 | 0 | All of our collocation space is either in the carrier facilities of our network partners or in carrier hotel facilities where we rent space by the rack. | None have been made yet. We anticipate at least 5 subcontracts within the next quarter. | Never underestimate the complexity of an environmental assessment. | Texas A&M University | 18 | 13 | 2 | 1 | 32 | 31 |  | 18 | 7 | 1 | 123 | 0 | 0 | TRUE
NT10BIX5570107 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | Our connections are all anticipated to be at the gigabit or greater data rate. | None, this is a middle mile project. | 7a No policy changes at this time. 7b No for TAMU | N/A | 4847 | 17 | 16 | 392 | 265 | 772 | 3385 | N/A | 0 | 0 | 0 | 0 | Our network hubs are located within carrier co-location facilities, most of which have at least a dozen other carriers in the same facility. Our interconnects are typically done over fiber cross connects provided by the carrier that owns the facility. | We have identified 5 subcontract opportunities at this time. | Identify agencies and key personnel in the various counties and districts that have jurisdictional authority for the project areas that will have an impact on the construction of the project. Provide them with a high level Project overview and include them in the planning process (TxDOT, USACE, DOD, County, City, Railroad and utilities.) | Texas A&M University | 18 | 13 | 2 | 1 | 32 | 31 |  | 18 | 7 | 1 | 123 | N/A | N/A | TRUE
NT10BIX5570107 | 2012 | $48,267.00 | N/A | 0 | N/A | 0 | N/A | 10 Gigabit | N/A | 0 | N/A | 1 Gigabit | N/A | 0 | N/A | All connections anticipated to be at gigabit or greater data rate. | None. This is a middle mile project. | 7a. No policy changes at this time. 7b. No for TAMU | N/A | 4847 | 178 | 16 | 4605 | 4 | 0 | 44 | N/A | 0 | 0 | 0 | 0 | Our network hubs are located within carrier co-location facilities, most of which have at least a dozen other carriers in the same facility. Our interconnects are typically done over fiber cross connects provided by the carrier that owns the facility. We are currently in colocation sites in Goldthwaite, Stephenville, Temple, Commerce, Corpus Christi, San Antonio, Cleta, Tulia, Campbell, and Tyler, TX. | We have identified 5 subcontract opportunities at this time.None are SDB. | Identify agencies and key personnel in the various counties and districts that have jurisdictional authority for the project areas that will have an impact on the construction of the project. Early in the process, provide them with a high level Project overview and include them in the planning process (TxDOT, USACE, DOD, County, City, Railroad and utilities.) | Texas A&M University | 18 | 13 | 2 | 1 | 32 | 31 |  | 18 | 7 | 1 | 123 | None at this time | None at this time | TRUE
NT10BIX5570107 | 2013 | $59,267 | Includes: conduit, cables, towers, antennas/wireless transceivers, and the labor used to install this transmission infrastructure Does not include: network access (e.g., core network routers), customer premise equipment (CPE), building/facility construction, test equipment, billing and operational support systems, and/or any additional professional services | 0 | n/a | 0 | n/a | 10 Gigabit | n/a | 0 | n/a | 1 Gigabit | n/a | 0 | n/a | CAIâ€™s identified on this project are receiving new access rather than improved access . In that regard the least connection is anticipated to be a minimum data rate of 1 gigabit therefore there is no sound method for calculating an increase to their broadband speed. 1 gigabit is the minimum anticipated data rate that would be available for the CAIs | None. This is a middle mile project. | 7a. The Trans Texas Video Network manages the network. Bandwidth is determined on a customer by customer basis depending on their needs and the physical limitation of the data network equipment. 7b. No for TAMU | n/a | 4847 | 108 | 0 | 4739 | 0 | 0 | 0 | none at this time | 0 | 0 | 0 | 0 | Our network hubs are located within carrier co-location facilities, most of which have at least a dozen other carriers in the same facility. Our interconnects are typically done over fiber cross connects provided by the carrier that owns the facility. We are currently in collocation sites in Goldthwaite, Stephenville, Temple, Commerce, Corpus Christi, San Antonio, Cleta, Tulia, Campbell, Waller, Waco, Atlanta, Dallas, and Tyler, TX. | We have identified two subcontract opportunities at this time. None are SBD. | Identify agencies and key personnel in the various counties and districts that have jurisdictional authority for the project areas that will have an impact on the construction of the project. Early in the process, provide them with a high level project overview and include them in the planning process (TxDOT, USACE, DOD, County, City, Railroad and utilities.) | Texas A&M University | 18 | 13 | 2 | 1 | 32 | 31 |  | 18 | 7 | 1 | 123 | none at this time | none at this time | TRUE
NT10BIX5570108 | 2010 | 0 | No fiber deployment to date. | 0 | NA - Last Mile services are not included within the project. | 0 | NA - Last Mile services are not included within the project. | 0 | No fiber deployment to date. When complete the maximum speed will be 10 Gbps. | 0 | NA - Last Mile services are not included within the project. | 0 | No fiber deployment to date. When complete the speed tiers advertised will be the same as the actual speed provided. | 0 | NA - Last Mile services are not included within the project. | Since construction has yet to begin, there is no increase in broadband speeds to report at this time. | Since construction has yet to begin, there are no services currently being offered. Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet services. | The project fully embraces and will adhere to the NOFAâ€™s non-discrimination and network interconnection obligations including the FCCâ€™s Internet Policy Statement (FCC 05-151). As a current broadband service provider, Illinois Century Network (ICN), we have maintained acceptable use policies consistent with the nondiscrimination policies referenced in the NOFA. Customers are required to sign a participation agreement, which is posted on the ICN website at http://www.illinois.net/connect/default.htm. The agreement outlines responsibilities of the ICN and the customer and includes ICN's policies for acceptable use. The participation agreement will be modified to reflect the new service offerings resulting from the IBOP EC project. We do not interfere with the transmission of constituent data or prioritize content and will not monitor at the data level any fibers or Lambdas offered to providers without their written request. | None to date. | 168517 | 0 | 0 | 0 | 8519 | 3539 | 156460 | Since construction has yet to begin, there are no services currently being offered. | 0 | 0 | 0 | 0 | Collocation space is not yet established as construction activities have not started. | None to date. | The IBOP EC project is receiving strong support from all parties within the service area. As a current service provider, Central Management Services currently supports a number of customers in the area but is seeing a lot of interest and enthusiasm from potential new customers and stakeholders. We believe this positive response is a result of outreach efforts to share project information and engage the local communities in planning discussions. The project team is reaching out to the community on a local, regional and state level. At the local level, Field Staff are meeting with community anchors and stakeholders within individual towns and counties. At the regional level, Field Staff are working with local Economic Development Councils and University Cooperative Extension resources. At the state level, the project team is working with the state coordinating boards/agencies for education, libraries, museums, health care, emergency management, and public safety. As a result, consistent information regarding the benefits of the project is flowing to communities and stakeholders. The project team also sends a monthly update to all schools, libraries and universities as well as hundreds of other anchor institutions. The updates are posted on the project web site at www.illinois.net/IBOP.htm. The web site includes a link for interested parties to subscribe to future updates. The project team is also working closely with an advisory panel comprised of technical managers from various community anchor institutions throughout the state. This advisory panel is providing direct input into the development of network policies and service offerings. Members of the advisory panel are based on nominations collected annually from the general public and customers of Central Management Services' current broadband services. Nominations are reviewed and approved by a statutorily created policy committee (20 ILCS 3921) which guides Central Management Services on the operations of its broadband network. More information regarding the advisory committee and the policy committee are available at www.illinois.net. At the state level, the Illinois BTOP and BIP projects gathered to share information on their various projects and establish lines of communications. The level of cooperation among the BTOP Infrastructure projects is phenomenal and will result in all projects interconnected. | Central Management Services, Illinois Department of | 2837 | 187 | 34 | 151 | 32 | 32 |  | 349 | 89 | 0 | 3711 | Since construction has yet to begin, there are no interconnection, peering and/or transit agreements in place. However, we are in the discovery phase with several potential wholesale customers. | Since construction has yet to begin, there are no interconnection, peering and/or transit agreements in place. However, we are in the discovery phase with several potential wholesale customers. | TRUE
NT10BIX5570108 | 2011 | 0 | Construction activities started in November. No invoices were paid during this reporting period. | 0 | NA - Last mile services are not included in the project. | 0 | NA - Last mile services are not included in the project. | 0 | Since only a small portion of the network is operational, CMS is not offering services at this time. When complete the maximum speed will be 10 Gbps. | 0 | NA - Last mile services are not included in the project. | 0 | Since only a small portion of the network is operational, CMS is not offering services at this time. When complete the speed tiers advertised will be the same as the actual speed provided. | 0 | NA - Last mile services are not included in the project. | The new leased fiber lit in 2011 positions these CAIs to connect at speeds up to 1 gigabit. Since only a small portion of the network (80 of 2,000 miles is operational, the new service offerings are not available. Once fully deployed, these CAIs will realize a significant increase in broadband speeds as they move from 3-5 megabits to 50-100 megabits. | Since construction has yet to begin, there are no services currently being offered. Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet services. | The project fully embraces and will adhere to the NOFAâ€™s non-discrimination and network interconnection obligations including the FCCâ€™s Internet Policy Statement (FCC 05-151). As a current broadband service provider, Illinois Century Network (ICN), we have maintained acceptable use policies consistent with the nondiscrimination policies referenced in the NOFA. Customers are required to sign a participation agreement, which is posted on the ICN website at http://www.illinois.net/connect/default.htm. The agreement outlines responsibilities of the ICN and the customer and includes ICN's policies for acceptable use. The participation agreement will be modified to reflect the new service offerings resulting from the IBOP EC project. We do not interfere with the transmission of constituent data or prioritize content and will not monitor at the data level any fibers or Lambdas offered to providers without their written request. | None | 168518 | 320 | 0 | 0 | 8199 | 3539 | 156460 | Since only a small portion of the network is operational, no dark fiber has been leased. | 0 | 0 | 0 | 0 | CMS is not using grant funds to purchase or lease collocation capacity. Customers and providers can lease collocation space from CMS using existing collocation facilities and from select CAI facilities. | None | Our sub recipient, Illinois State University (ISU), has learned that it is imperative to appoint a single point of contact to work with CAIs. In the beginning, ISU had several staff members working with the same CAIs sometimes created confusion. The CAIs prefer working with one person even if it takes longer to respond to inquiries. CMS is using Share Point as the central repository for program and project management. The capabilities inherent to Share Point enhance the collaboration among the team members and streamline record keeping through automation. For example, CMS stores permit documents in Share Point and uses "view capabilities" to sort and analyze the data by construction package, status, and permitting authority. This feature allows team members to quickly sort and access the information in a view that meets their specific need. Another example of how CMS is using Share Point is managing vendor weekly certified payroll. Vendors send their weekly certified payroll documents to a specific email address that automatically files the email and its attachments in the appropriate Share Point folder. These easy to use features in Share Point are saving staff time generating and filing reports. | Central Management Services, Illinois Department of | 2837 | 187 | 34 | 151 | 32 | 32 |  | 349 | 89 | 0 | 3711 | 1) No interconnection agreements have been executed. 2) CMS is negotiating three interconnection agreements with other providers. 3) CMS has not denied any requests for interconnection. | 1) One transit agreement has been executed with the Illinois Rural HealthNet. 2) CMS and the sub recipient are in discussions with 11 entities regarding transit services. 3) CMS has not denied any requests for peering or transit services. | TRUE
NT10BIX5570108 | 2012 | $50,000 | The baseline forecasted costs at $61,674. Through competitive bidding, costs are running lower than anticipated. The average cost per new mile may increase as construction proceeds into more difficult areas (rock, utility congested areas, etc.). | 0 | NA - no last mile component. | 0 | NA - no last mile component. | 10 Gbps | Standard service offerings are 10 Mbps to 10 Gbps. The network can support faster speeds if required. | 0 | NA - no last mile component. | 10 Gbps | CMS provides symmetrical, dedicated broadband services. Customers are guaranteed to receive the subscribed speeds. | 0 | NA - no last mile component. | The leased fiber lit in 2011 positions these CAIs to connect at speeds up to 10 Gbps. The average increase in broadband speeds is 32 Mbps which is a 5- 7 times increase in previous speeds. | Since construction is ongoing, the availability of services is limited. Once fully operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet services. | The project fully embraces and will adhere to the NOFAâ€™s non-discrimination and network interconnection obligations including the FCCâ€™s Internet Policy Statement (FCC 05-151). As a current broadband service provider, Illinois Century Network (ICN), we have maintained acceptable use policies consistent with the nondiscrimination policies referenced in the NOFA. The acceptable use policy is posted on the website at www.illinois.net. We do not interfere with the transmission of constituent data or prioritize content and will not monitor at the data level any fibers or Lambdas offered to providers without their written request. | None | 167792 | 507 | 0 | 72785 | 3626 | 0 | 90874 | Since the network is under construction, no dark fiber has been leased. | 0 | 0 | 0 | 0 | CMS is not using grant funds to purchase or lease collocation capacity; however, ISU, the sub recipient will. CMS customers and providers can lease collocation space from CMS using existing collocation facilities and from select CAI facilities. ISU customers can lease collocation space at the BTOP funded facilities. The ISU collocation space is not operational at this point in the project. | Integrated Technology Providers Inc. | Having a single point of contact for potential customers is very helpful for continuity and customer confidence in the organization and process. Start working with railroads immediately in order to obtain permits. The process with the railroads can be lengthy and frustrating. Collect and validate the final as built diagrams for the new fiber and utilize a fiber management system. The fiber management system can assist in tracking fiber assignments for internal use and customer leases as well as generate accurate and detailed mapping information to be used for fiber locates and maintenance. Through the course of construction our vendors have discovered or hit unmarked utilities. We believe the problem is a result of poor network maps for the older infrastructure. | Central Management Services, Illinois Department of | 2837 | 187 | 34 | 151 | 32 | 32 |  | 349 | 89 | 0 | 3711 | 1) No new interconnection agreements were executed during this reporting. 2) CMS is not negotiating any new agreements. 3) CMS has not denied any requests for interconnection. CMS currently interconnects with more than a dozen service providers. These service providers are providing last mile connections for CAIs connected to the State's educational network. | 1) One transit agreement has been executed with the Illinois Rural HealthNet. 2) CMS is in contract negotiations with a wholesale provider and in discussions with an additional 9 providers. 3) CMS has not denied any requests for peering or transit services. | TRUE
NT10BIX5570108 | 2013 | $53,345 | The baseline forecasted costs at $61,674. Through competitive bidding, costs were lower than anticipated. | 0 | NA - no last mile component. | 0 | NA - no last mile component. | 10 Gbps | Standard service offerings are 10 Mbps to 10 Gbps. The network can support faster speeds if required. | 0 | NA - no last mile component. | 10 Gbps | CMS provides symmetrical, dedicated broadband services. Customers are guaranteed to receive the subscribed speeds. | 0 | NA - no last mile component. | The new fiber infrastructure positions these CAIs to connect at speeds up to 10 Gbps. Prior to completion of this project, most K-12 schools were connected at speeds of 1.5 to 20 Mbps and higher education sites were connected at speeds of 10 to 50 Mbps. As a result of this project, K-12 schools are now connected at speeds of 10 Mbps to 1 Gbps with more than half connected at speeds at 100+ Mbps which is an increase of more than 80 Mbps. The majority of higher education sites are now connected at speeds of 100+ Mbps which is an increase of more than 50 Mbps. | CMS provides wholesale services only. The sub recipient, Illinois State University, does provide the following retail services: 1) ISP Internet Services, 2) Subscriber Internet Services, 3) Intranet Services, and 4) Dark Fiber Leases. | The project fully embraces and will adhere to the NOFAâ€™s non-discrimination and network interconnection obligations including the FCCâ€™s Internet Policy Statement (FCC 05-151). As a current broadband service provider, Illinois Century Network (ICN), we have maintained acceptable use policies consistent with the nondiscrimination policies referenced in the NOFA. The acceptable use policy is posted on the website at www.illinois.net. We do not interfere with the transmission of constituent data or prioritize content and will not monitor at the data level any fibers or Lambdas offered to providers without their written request. | None | 149722 | 6141 | 2862 | 140719 | 0 | 0 | 0 | [REDACTED] | 1520 | 1166 | 0 | 354 | CMS is not using grant funds to purchase or lease collocation capacity; however, the sub recipient, Illinois State University, has used grant funds to lease collocation space. CMS customers and providers can lease collocation space from CMS using existing collocation facilities and from select CAI facilities. ISU customers can lease collocation space at the BTOP funded facilities. | Integrated Technology Providers Inc. | Having a single point of contact for potential customers is very helpful for continuity and customer confidence in the organization and process. Start working with railroads immediately in order to obtain permits. The process with the railroads can be lengthy and frustrating. Collect and validate the final as built diagrams for the new fiber and utilize a fiber management system. The fiber management system can assist in tracking fiber assignments for internal use and customer leases as well as generate accurate and detailed mapping information to be used for fiber locates and maintenance. Through the course of construction our vendors have discovered or hit unmarked utilities. We believe the problem is a result of poor network maps for the older infrastructure. | Central Management Services, Illinois Department of | 2837 | 187 | 34 | 151 | 32 | 32 |  | 349 | 89 | 0 | 3711 | 1) CMS currently interconnects with 20 service providers of which 3 were added in 2013. These service providers are providing last mile connections for CAIs connected to the State's educational network. 2) CMS is not negotiating any new agreements. 3) CMS | 1) CMS has 17 peering agreements of which 5 were added in 2013. CMS did not complete any new transit agreements in 2013. 2) CMS is negotiating 1 transit agreement. 3) CMS has not denied any requests for peering or transit services. | TRUE
NT10BIX5570109 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Carver, County of | 27 | 5 | 2 | 0 | 1 | 16 |  | 34 | 614 | 1 | 700 | N/A | N/A | TRUE
NT10BIX5570109 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | We have not yet begun to provide service. | N/A | N/A | 17880 | 0 | 0 | 0 | 0 | 8940 | 8940 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Carver, County of | 27 | 5 | 2 | 0 | 1 | 16 |  | 34 | 614 | 1 | 700 | N/A | N/A | TRUE
NT10BIX5570109 | 2012 | 45386 | N/A | 0 | N/A | 0 | N/A | 1GB | N/A | 0 | N/A | 10MB | N/A | 0 | N/A | N/A | We have not yet begun to provide service. | N/A | N/A | 17880 | 0 | 0 | 0 | 0 | 8940 | 8940 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Carver, County of | 27 | 5 | 2 | 0 | 1 | 16 |  | 34 | 614 | 1 | 700 | N/A | N/A | TRUE
NT10BIX5570109 | 2013 | 45386 | N/A | 0 | N/A | 0 | N/A | 1 GB | N/A | 0 | N/A | 10 MB | N/A | 0 | N/A | N/A | We are not providing retail service | N/A | N/A | 17880 | 8940 | 8940 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Carver, County of | 27 | 5 | 2 | 0 | 1 | 16 |  | 34 | 614 | 1 | 700 | N/A | N/A | TRUE
NT10BIX5570111 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A No | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | NoaNet will have leased collocation, these facilities will be designed for other carriers to have access either through pre-existing facilities within the collocation facility or through newly constructed interconnection facilities such as meet-me vaults and pig-tail fibers to a common and commercially available meet-me point. | N/A | None currently to be shared. | Northwest Open Access Network | 97 | 40 | 5 | 1 | 10 | 27 |  | 70 | 30 | 2 | 282 | One (1) interconnection agreement entered into during the annual reporting period. Currently negotiating one interconnection agreement. We have not denied any requests for interconnection during the annual reporting period. | N/A | TRUE
NT10BIX5570111 | 2011 | 0 | Since construction has not yet started on this project, calculations are not applicable. | 0 | Construction has not yet started. | 0 | Construction has not yet started. | 0 | Broadband speeds have not been advertised and will be available once construction has commenced and services turned up. | 0 | Broadband speeds have not been advertised and will be available once construction has commenced and services turned up. | 0 | Construction has not yet started so speeds are not available. | 0 | Construction has not yet started so speeds are not available. | There has not been any increase in Broadband speed since construction of the Network has not yet begun. | None at this time of the project life cycle. | N/A No | N/A | 47705 | 0 | 0 | 0 | 47705 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | NoaNet will have leased collocation, these facilities will be designed for other carriers to have access either through pre-existing facilities within the collocation facility or through newly constructed interconnection facilities such as meet-me vaults and pig-tail fibers to a common and commercially available meet-me point. | N/A | None currently to be shared as a result of this past year. | Northwest Open Access Network | 97 | 40 | 5 | 1 | 10 | 27 |  | 70 | 30 | 2 | 282 | 1). 7 agreements entered into in 2011. Capacity Provisioning, Columbia County, Olympus Net, Spectrum, and Touchet Valley, and WCI all were signed with Wholesale Agreements this past year. 2). 1 Interconnection agreement being negotiated 3). No, none denied. | N/A | TRUE
NT10BIX5570111 | 2012 | $134,506.89 | This cost was calculated using the Outside Plant expenditures and dividing by the actual miles built as of the end of 2012. With the most expensive portion of the Network Build being done in 2012, this number is not representative of the overall project when the project has been completed. | N/A | N/A | N/A | N/A | 100 Gig | With the improvement in technology since the application was submitted, Northwest Open Access Network has been able to advertise and provide 100 Gig service for those that are interested in securing. | N/A | N/A | 100 Meg | No Variance. | N/A | N/A | On average the increase in broadband speed was just over 10 Meg for the Community Anchor Institutions connected over the past annual reporting period. | NoaNet is a wholesale provider and not authorized to provide retail services. The services provided are to Retail Service Providers with array of services including Broadband Internet, Wave/Lambda, TDM, Ethernet, and Collocation. Pricing Plans are established by each individual provider and are attached as Confidential and Proprietary information. | N/A No | N/A | 51648 | 5 | 0 | 14683 | 36960 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | NoaNet will have leased collocation, these facilities will be designed for other carriers to have access either through pre-existing facilities within the collocation facility or through newly constructed interconnection facilities such as meet-me vaults and pig-tail fibers to a common and commercially available meet-me point. | N/A | None currently to be shared as a result of this past year. | Northwest Open Access Network | 97 | 40 | 5 | 1 | 10 | 27 |  | 70 | 30 | 2 | 282 | 1.) None 2.) N/A 3.) N/A | 1.) One (1) Netflix CDN 2.) N/A 3.)N/A | TRUE
NT10BIX5570111 | 2013 | 79,600 | This cost was calculated using the Outside Plant expenditures and dividing by the actual miles built as of the end of 2013. This number is down considerably from the 2012 report as the less expensive portion of the build was done in 2013. Baseline was $74,299, we found additional rock in areas making the build slightly more expensive. | N/A | N/A | N/A | N/A | 100 Gig | With the improvement in technology since the application was submitted, Northwest Open Access Network has been able to advertise and provide 100 Gig service for those that are interested in securing. | N/A | N/A | 100 Meg | No Variance. | N/A | N/A | On average the increase in broadband speed was just over 10 Meg for the Community Anchor Institutions connected over the past annual reporting period. | NoaNet is a wholesale provider and not authorized to provide retail services. The services provided are to Retail Service Providers with an array of services including Broadband Internet, Wave/Lamda, TDM, Ethernet, and Collocation. Pricing Plans are established by each individual provider and are attached as Confidential and Proprietary information. | N/A No | N/A | 45216 | 45216 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | NoaNet will have leased collocation, these facilities will be designed for other carriers to have access either through pre-existing facilities within the collocation facility or through newly constructed interconnection facilities such as meet-me vaults and pig-tail fibers to a common and commercially available meet-me points. | N/A | None currently to be shared as a result of this past year. | Northwest Open Access Network | 97 | 40 | 5 | 1 | 10 | 27 |  | 70 | 30 | 2 | 282 | 1.) None 2.) N/A 3.) N/A | 1.) One- Fatbeam 2.) N/A 3.) N/A | TRUE
NT10BIX5570112 | 2010 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 7a: All NebraskaLink customers have full access/ bandwidth to their purchased bandwidth / no traffic prioritization. 7b: NebraskaLink has not limited or blocked customers from accessing any lawful content, service, service provider or application, or prevented any consumers from attaching any legal device to the network. | N/A | 50976 | 809 | 0 | 0 | 5000 | 2500 | 42667 | N/A | 0 | 0 | 0 | 0 | Currently we are leasing collocation space from the following: Nebraska Central Telephone Company - 887 H St, Burwell, NE Four-U-Technology - 104 W Centre St, Hartington, NE Consolidated Long Distance - 234 S. Price St, Merna, NE 68856 | N/A | Communication is the best practice we can share thus far in our project - communication with your Grants Officer, Environmental Officers,etc. Don't be afraid to ask questions of your team - they are there to assist you and to work with you on all aspects of your award. | Nebraskalink, LLC | 25 | 3 | 7 | 1 | 34 | 8 |  | 19 | 4 | 0 | 101 | 1) 3 interconnection agreements have been signed 2) Currently working on 7 interconnection agreements 3) No requests for interconnection have been denied. | N/A | TRUE
NT10BIX5570112 | 2011 | 13485.60 | NebraskaLink is on target for the average cost per mile as compared to our baseline plan. | N/A | N/A | N/A | N/A | 10 Gbps | N/A | N/A | N/A | 115 mbps | NebraskaLink is on target with our baseline plan. | N/A | N/A | N/A | N/A | 7a: All NebraskaLink customers have full access/bandwidth to their purchased bandwidth / no traffic prioritization. 7b: NebraskaLink has not limited or blocked customers from accessing any lawful content, service, service provider or application, or prevented any consumers from attaching any legal device to the network. | N/A | 35086 | 15865 | 1415 | 0 | 17695 | 111 | 0 | N/A | 0 | 0 | 0 | 0 | Currently NebraskaLink leases collocation spaces from the following: Arlington Telephone: Arlington Blair Telephone: Blair Consolidated Long Distance: Merna, Brady, Maxwell, Maywood, Ravenna Clarks Telephone: Clarks Hamilton Long Distance: Grand Island, Aurora Nebraska Central Telephone Company: Burwell, Sargent, Ravenna Great Plains Communications: Snyder, Wynot, Broken Bow, Arnold, Columbus, Cotesfield, Archer, Grant, Imperial Northeast Nebraska Telephone Company: Clearwater, Bartlett | N/A | Communications with our Federal Program Officer and team is the best practice we can share. Secondly would be to take advantage of any and all advice and communications - via email, webinar training, drop in calls, etc - many times others have the same questions we have and it is truly advantageous to attend this meetings to increase knowledge of expectations and to see how others are meeting their objectives and any obstacles they may be encountering. | Nebraskalink, LLC | 25 | 3 | 7 | 1 | 34 | 8 |  | 19 | 4 | 0 | 101 | 1) 33 interconnection agreements have been signed 2) NebraskaLink is currently working on 4 new interconnection agreements 3) No requests for interconnection have been denied. | N/A | TRUE
NT10BIX5570112 | 2012 | 13449.50 | NebraskaLink is on target for this milestone | N/A | N/A | N/A | N/A | 10 Gbps | NebraskaLink is on target for this milestone | N/A | N/A | 150 Mbps | NebraskaLink is on track with this milestone | N/A | N/A | Prior to services offered to the CAI's by NebraskaLink, the CAI's were utilizing asymetrical DSL services provided by their carriers. NebraskaLink is now offering Ethernet services to the CAI's which gives them the ability for increased bandwidth to each CAI. The average speed provided is 89 Mbps. The average was arrived by taking the speed of each CAI taking our services and dividing by number of CAI's taking our service. We currently offer to our CAI's services ranging from 5 Mbps to 1 Gig of service. | Currently NebraskaLink offers full symmetrical Direct Internet Access and Layer 2 Ethernet Service to our retail customers. Pricing attached. | 7a: All NebraskaLink customers have full access to their purchased bandwidth / no traffic prioritization 7b: NebraskaLink has not limited or blocked customers from accessing any lawful content, service, service provider or application or prevented any consumers from attaching any legal device to the network. | N/A | 35086 | 31320 | 1415 | 0 | 2240 | 111 | 0 | N/A | 0 | 0 | 0 | 0 | Currently NebrakaLink leases collocation spaces from the following: Arlington Telephone: Arlington Blair Telephone : Blair Consolidated Long Distance: Merna, Brady, Maxwell, Maywood, Ravenna, Paxton Clarks Telephone: Clarks Hamilton Long Distance: Grand Island, Aurora Nebraska Central Telephone Company: Burwell, Sargent, Ravenna Great Plains Communications: Snyder, Wynot, Broken Bow, Arnold, Columbus, Cotesfield, Archer, Grant, Imperial, Crookston, Chadron, Trenton, Wood Lake Northeast Nebraska Telephone Company: Clearwater, Bartlett, Stuart Eastern Nebraska Telephone Company: Osmond Hartelco: Hartington | N/A | Communications with our Grants team is the best practice/ lesson that we can share. Take advantage of any and all training, webinars, calls with other recipients. | Nebraskalink, LLC | 25 | 3 | 7 | 1 | 34 | 8 |  | 19 | 4 | 0 | 101 | 1) 52 interconnection agreements have been signed 2) NebraskaLink is currently working on 3 new interconnection agreements 30 No requests have been denied. | N/A | TRUE
NT10BIX5570112 | 2013 | 24429 | NebraskaLink was over target on this milestone. Cost includes construction, materials, engineering and inspections costs. | N/A | N/A | N/A | N/A | 10 Gbps | NebraskaLink is on target for this milestone | N/A | N/A | 150 Mbps | NebraskaLink is on target with this milestone | N/A | N/A | Prior to services offered to the CAI's by NebraskaLink, the CAI's were utilizing asymetrical DSL services provided by their carriers. NebraskaLink is now offering Ethernet services to the CAI's which gives them the ability for increased bandwidth to each CAI. The average speed provided is 89 Mbps. The average was arrived by taking the speed of each CAI taking our services and dividing by number of CAI's taking our service. We currently offer to our CAI's services ranging from 5 Mbps to 1 Gig of service. | Currently NebraskaLink offers full symmetrical Direct Internet Access and Layer 2 Ethernet Service to our retail customers. Pricing attached. | 7a: All NebraskaLink customers have full access to their purchaesed bandwidth/ no traffic prioritization 7b: NebraskaLink has not limited or blocked customers from accessing any lawful content, service, service provider or applicaton or prevented any consumers from attaching any legal device to the network. | N/A | 48266 | 43050 | 1415 | 0 | 0 | 0 | 0 | No dark fiber | 0 | 0 | 0 | 0 | Currently NebrakaLink leases collocation spaces from the following: Arlington Telephone: Arlington Blair Telephone : Blair Consolidated Long Distance: Merna, Brady, Maxwell, Maywood, Ravenna, Paxton Clarks Telephone: Clarks Hamilton Long Distance: Grand Island, Aurora Nebraska Central Telephone Company: Burwell, Sargent, Ravenna Great Plains Communications: Snyder, Wynot, Broken Bow, Arnold, Columbus, Cotesfield, Archer, Grant, Imperial, Crookston, Chadron, Trenton, Wood Lake Northeast Nebraska Telephone Company: Clearwater, Bartlett, Stuart Eastern Nebraska Telephone Company: Osmond Hartelco: Hartington | N/A | Communications with our Grants team is the best practice we can share. | Nebraskalink, LLC | 25 | 3 | 7 | 1 | 34 | 8 |  | 19 | 4 | 0 | 101 | 1) 24 interconnection agreements have been signed 2) NebraskaLink is not currently working on any new interconnection agreements 3) No requests have been denied | N/A | TRUE
NT10BIX5570113 | 2010 | $62,277 | No Variance. | 0 | N/A | 0 | N/A | 1000 Meg | No variance. | 0 | N/A | 100 Meg | No variance. | 0 | N/A | No Community Anchor Institutions have yet been connected. | N/A | 7a. No services are yet being provided by this project. 7b. There are no plans to limit access to the network. | N/A | 64824 | 0 | 0 | 0 | 12060 | 28764 | 24000 | N/A | 0 | 0 | 0 | 0 | The Oklahoma Community Anchor Network (OCAN) project will build 15 Communication/Collocation facilities along the OCAN route. | N/A | None at this time. | Finance, Oklahoma Office of State | 475 | 52 | 12 | 27 | 89 | 387 |  | 112 | 31 | 0 | 1185 | N/A | N/A | TRUE
NT10BIX5570113 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | No Community Anchor Institutions (CAI) have yet been connected. The numbers listed above in number 4 include the 32 CAI's that will be directly connected to the Oklahoma Community Anchor Network (OCAN) plus 1,154 potential CAI's noted in the Baseline and the Key Metrics Dashboard that was submitted with the grant application. Each of the 32 directly connected CAI's will have a 1 Gig connection, when connected. The current average broadband speed at the CAI's is 44 Meg, thus the increase in broadband speed available will be 956 Meg. | N/A | 7a. No services are yet being provided by this project. 7b. There are no plans to limit access to the network. | N/A | 105864 | 0 | 0 | 0 | 19696 | 46974 | 39194 | N/A | 3520 | 1760 | 0 | 1760 | The Oklahoma Community Anchor Network (OCAN) project is constructing sixteen (16) Communication/Collocation facilities along the OCAN route. Each facility will have 220 square feet with 110 square feet used by recipient and 110 square feet available for other network providers and/or customers to interconnect with OCAN. | N/A | None at this time. | Finance, Oklahoma Office of State | 475 | 52 | 12 | 27 | 89 | 387 |  | 112 | 31 | 0 | 1185 | N/A | N/A | TRUE
NT10BIX5570113 | 2012 | $60,713 | Variance from Baseline Plan of $62,277. Actual average cost per mile on project has come in $2,064 lower than the Baseline. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | The average increase in broadband speed at the Community Anchor Institutions (CAI's) is 956 Meg. The current average speed is 44 Meg and the CAI's are being provided with 1000 Meg connections. The numbers listed in question 4 include the 32 CAI's directly connected by the OCAN fiber. There are 1,154 potential CAI's noted in the Baseline and the Key Metrics Dashboard that was submitted with the grant application. | N/A | 7a. No services are yet being provided by this project. 7b. There are no plans to limit access to the network. | N/A | 91382 | 2324 | 0 | 76002 | 0 | 0 | 13056 | N/A | 3520 | 1760 | 0 | 1760 | The Oklahoma Community Anchor Network (OCAN) project has constructed sixteen (16) Communication/Collocation facilities along the OCAN route. Each facility has 220 square feet with 110 square feet used by recipient and 110 square feet available for other network providers and/or customers to interconnect with OCAN. | N/A | None at this time. | Finance, Oklahoma Office of State | 475 | 52 | 12 | 27 | 89 | 387 |  | 112 | 31 | 0 | 1185 | N/A | N/A | TRUE
NT10BIX5570114 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 10 Gbps | None Noted | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | a) CAI's can request their bandwidth limited but by default Merit does not limit the users access. b) Merit has not block access to any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. | N/A | 147730 | 0 | 0 | 0 | 39279 | 12177 | 96274 | N/A | 0 | 0 | 0 | 0 | Although collocation space will be built in the future for this project, Merit does not currently own collocation space for this build. Other network providers and CAI's can interconnect to Merit at splice points along the route. | N/A | Merit encourages all BTOP recipients to reach out to communities at all levels and get them involved in the process. Build relationships with all the permitting agencies; we would suggest informal meetings with them on a regular basis. Merit would encourage that inquiries with communities on existing infrastructure as well as talking with others in your industry about existing infrastructure given that the cost is about the same or less and the time savings will get you ahead of your project. | Merit Network Inc. | 88 | 31 | 6 | 17 | 26 | 5 |  | 20 | 13 | 0 | 206 | N/A | N/A | TRUE
NT10BIX5570114 | 2011 | 0 | N/A | 0 | N/A | 0 | N/A | 10 Gbps | No variance. | 0 | N/A | 0 | N/A | 0 | N/A | Broadband speeds have not increased since construction and deployment have not been completed. | Pricing plans have not been provided, since construction and deployment have not been completed. | Our project is not yet providing service. | N/A | 153737 | 0 | 0 | 0 | 35713 | 10762 | 107262 | N/A | 0 | 0 | 0 | 0 | Other network providers and customers will have opportunities to connect to the recipient and subrecipient networks at leased facilities along the route, including, but not limited to: telecommunication huts; Central Offices; Community Anchor Institutions; and other leased facilities. No part of the project network was lit and operational during the reporting period; the locations, owners, and interconnection method data will be available in the 2012 reporting year. | N/A | Project success depends on collaboration and communication with the NTIA and the Grants Office via the Project's Federal Program Officer, Grants Officer, and their consulting teams. It is important to become intimately familiar with the Grant terms and conditions, and implement financial and administrative systems that allow for the monitoring of grant activities and documentation of the use of funds. Starting processes early makes a huge difference in the project time line. Initiating procurement processes, completing the Environmental Assessment, requesting Davis-Bacon Act wage rates for your project area, and having agreements in place with subrecipients and vendors, and working with permitting agencies as early as possible maximizes construction time. Planning is an essential component of a successful project, and BTOP recipients should have clearly defined baseline project plans, communication plans for subrecipients, contractors, vendors, and the community, plans for collecting progress data, risk mitigation and contingency plans, and plans for monitoring subrecipients. Community outreach helps get communities involved in the project, creates an open dialogue, and demonstrates that our organization and the NTIA are using Federal funds responsibly. Helping key stakeholders and organizations see the positive socioeconomic impact that broadband has will result in higher adoption rates and stronger, more vibrant communities. | Merit Network Inc. | 88 | 31 | 6 | 17 | 26 | 5 |  | 20 | 13 | 0 | 206 | 1. N/A 2. N/A 3. N/A (No requests for interconnection were made.) | 1. N/A 2. N/A 3. N/A (No requests for peering or transit were made.) | TRUE
NT10BIX5570114 | 2012 | 90988 | This number is higher than the baseline plan primarily because Merit Network, Inc. focused on installing the most difficult and labor-intensive sections of the network before the winter season. The cost per new mile should gradually align with the baseline cost as additional miles are completed, and Merit anticipates no variance at the project culmination. | 0 | N/A | 0 | N/A | 10 Gbps | No variance | 0 | N/A | 10 Mbps | No variance | 0 | N/A | The average increase is 10 Gbps. This was calculated by taking the average of the average speed connections to the communicaty anchor institutions receiving new or improved service. | Merit provides a managed fiber attachment service. Members pay a single annual fee based on the service level to which they subscribe. The fee comprises a local loop provisioned on fiber infrastructure and bandwidth from the backbone to the Member. | Merit Network employs standard best effort Internet delivery policy to ensure that any organization, institution or entity connected, directly or indirectly, to Merit's fiber backbone may exercise choice in lawful Internet content, web-based application and use of Merit or competitor service, including any device which is not harmful to the network. All of the preceding is subject to the needs of law enforcement. Merit Network does not favor any lawful Internet applications or content over others, and is committed to enabling competition among network providers, application and service providers, and content providers. | N/A | 153616 | 108 | 0 | 2844 | 4774 | 0 | 145890 | N/A | 0 | 0 | 0 | 0 | Other network providers and customers have opportunities to connect to the recipient and subrecipient networks along the route at telecommunications huts, central offices, community anchor institutions, and other facilities. | N/A | Project success depends on collaboration and communication with the NTIA and the Grants Office via the Project's Federal Program Officer, Grants Officer, and their consulting teams. It is important to become intimately familiar with the Grant terms and conditions, and implement financial and administrative systems that allow for the monitoring of grant activities and documentation of the use of funds. Starting processes early makes a huge difference in the project time line. Initiating procurement processes, completing the Environmental Assessment, requesting Davis-Bacon Act wage rates for your project area, and having agreements in place with subrecipients and vendors, and working with permitting agencies as early as possible maximizes construction time. Planning is an essential component of a successful project, and BTOP recipients should have clearly defined baseline project plans, communication plans for subrecipients, contractors, vendors, and the community, plans for collecting progress data, risk mitigation and contingency plans, and plans for monitoring subrecipients. Community outreach helps get communities involved in the project, creates an open dialogue, and demonstrates that our organization and the NTIA are using Federal funds responsibly. Helping key stakeholders and organizations see the positive socioeconomic impact that broadband has will result in higher adoption rates and stronger, more vibrant communities. | Merit Network Inc. | 88 | 31 | 6 | 17 | 26 | 5 |  | 20 | 13 | 0 | 206 | N/A | N/A | TRUE
NT10BIX5570114 | 2013 | 57331 | The cost per mile was significantly above the estimate in the baseline plan, primarily due to unanticipated costs associated with underground construction. Merit's construction crews encountered unforeseen stretches of solid rock in the Upper Peninsula; boring through rock is the mostly costly construction method, and the overall cost per mile increased as a result. | 0 | N/A | 0 | N/A | 10 Mbps | No variance | 0 | N/A | 10 Mbps | No variance | 0 | N/A | The average increase is 10 Gbps. This was calculated by taking the average of the average speed connections to the communicaty anchor institutions receiving new or improved service. | Merit provides a managed fiber attachment service. Members pay a single annual fee based on the service level to which they subscribe. The fee comprises a local loop provisioned on fiber infrastructure and bandwidth from the backbone to the Member. | Merit Network employs standard best effort Internet delivery policy to ensure that any organization, institution or entity connected, directly or indirectly, to Merit's fiber backbone may exercise choice in lawful Internet content, web-based application and use of Merit or competitor service, including any device which is not harmful to the network. All of the preceding is subject to the needs of law enforcement. Merit Network does not favor any lawful Internet applications or content over others, and is committed to enabling competition among network providers, application and service providers, and content providers. | N/A | 153741 | 38390 | 0 | 115170 | 45 | 0 | 135 | N/A | 0 | 0 | 0 | 0 | Other network providers and customers have opportunities to connect to the recipient and subrecipient networks along the route at telecommunications huts, central offices, community anchor institutions, and other facilities. | N/A | Project success depends on collaboration and communication with the NTIA and the Grants Office via the Project's Federal Program Officer, Grants Officer, and their consulting teams. It is important to become intimately familiar with the Grant terms and conditions, and implement financial and administrative systems that allow for the monitoring of grant activities and documentation of the use of funds. Starting processes early makes a huge difference in the project time line. Initiating procurement processes, completing the Environmental Assessment, requesting Davis-Bacon Act wage rates for your project area, and having agreements in place with subrecipients and vendors, and working with permitting agencies as early as possible maximizes construction time. Planning is an essential component of a successful project, and BTOP recipients should have clearly defined baseline project plans, communication plans for subrecipients, contractors, vendors, and the community, plans for collecting progress data, risk mitigation and contingency plans, and plans for monitoring subrecipients. Community outreach helps get communities involved in the project, creates an open dialogue, and demonstrates that our organization and the NTIA are using Federal funds responsibly. Helping key stakeholders and organizations see the positive socioeconomic impact that broadband has will result in higher adoption rates and stronger, more vibrant communities. | Merit Network Inc. | 88 | 31 | 6 | 17 | 26 | 5 |  | 20 | 13 | 0 | 206 | There were no interconnection agreements entered into during the annual reporting period, however, four agreements were under negotiation. No requests were denied. | There were no peering or transit agreements entered into during the annual reporting period, however one agreement was under negotiation. No requests were denied. | TRUE
NT10BIX5570115 | 2010 | 0 | Network build has not started. | 0 | Network build has not started. | 0 | Network build has not started. | 0 | Network build has not started. | 0 | Network build has not started. | 0 | Network build has not started. | 0 | Network build has not started. | na | na | There are no services being provided at this time. Network management policies are currently being developed with partners. | na | 0 | 0 | 0 | 0 | 0 | 0 | 0 | na | 0 | 0 | 0 | 0 | na | na | na | University of Wisconsin System | 32 | 5 | 10 | 11 | 26 | 20 |  | 50 | 16 | 2 | 172 | na | na | TRUE
NT10BIX5570115 | 2011 | $65,488 | Network build has just started with initial fiber being installed in late December. Current cost is for very small portion of overall network only (a higher portion of urban and rocky conditions were experienced) and should normalize as more installation takes place in the next year. | 0 | No last mile service areas yet installed. | 0 | No last mile service areas yet installed. | 40 Mb | Only WiMAX connections are available to date and are limited to Community Anchor Institutions. Maximum speed is 40 Mb and typical speed for WiMAX expected to be around 10 Mb. | 0 | No last mile service areas yet installed. | 10 Mb | Only WiMAX connections are available to date and are limited to Community Anchor Institutions. Typical speed for WiMAX is expected to be around 10 Mb. | 0 | No last mile service areas yet installed. | 10 Mb average improvement: The institutions connected to date are all considered "new" with a previous speed of zero. In all cases, the new broadband connections are accomplished via WiMAX with a typically expected speed of 10Mb. With no previous service, this represents an increase of 10Mb for each institution. | No retail services will be provided until network is available in last mile service areas. | Services provided by this project predominantly include simple, large bandwidth connectivity over fiber and using Ethernet equipment owned and operated by the connected institutions. Expected service rates will be limited only by the hardware capacity. All traffic will be allowed to each institution which has the right to filter, limit, or block as needed for that institution. No rate limits, content filtering, or connectivity restrictions will be applied by UW-Extension or other outside party. Network management policies in each community are under development. All policies will allow open access, interconnection and promote nondiscrimination. UW-Extension network management policies are available on our Web site:http://broadband.uwex.edu. | N/A | 67995 | 0 | 0 | 2499 | 11100 | 3400 | 50996 | N/A | 0 | 0 | 0 | 0 | We are building no new collocation space with grant funds. Existing facilities will be used for interconnection, typically utilizing existing racks in data centers located at technical college and university where other network providers and/or customers may install equipment. We do not anticipate the need for providing actual floor space for customer or provider owned racks. Additional interconnect at a basic fiber-splice level will be available in buried communications vaults throughout the network footprint. | 0 - none of our subcontractors are small businesses. | Order fiber optic cable immediately; lead times run from 2 months to 12 months. If installation is intended to be direct-bury method, consider installing conduit first, then returning later to install the fiber when the order arrives. Document all assumptions, calculation methods, and explanations for any reportable information - as much for your own future reference as to satisfy audit requirements. Consider hiring outside project management help. Where some community partners were having a hard time making progress, bringing in a dedicated person to focus on the project immediately resulted in forward progress. | University of Wisconsin System | 32 | 5 | 10 | 11 | 26 | 20 |  | 50 | 16 | 2 | 172 | 1. No interconnection agreements were signed this year. 2. Negotiations are currently underway with two providers. 3. No interconnection agreements have been denied. | No activity has occurred regarding peering and transit agreements this year. | TRUE
NT10BIX5570115 | 2012 | 58,711 | Average cost per new mile is slightly higher than $56,331 / mile Year 2 milestone target cost due to higher portion of rocky conditions than originally planned. | 0 | No last mile service areas yet installed. | 0 | No last mile service areas yet installed. | 40Gb | Hospitals are making use of 40Gb link on newly installed BCCB network. | 0 | No last mile service areas yet installed. | 2.65Gb | Most new connections are 1Gb. There are three connections running at 10Gb and one at 40Gb. Simple average calculated across all Community Anchor Institutions currently receiving service. | 0 | No last mile service areas yet installed. | Average increase in broadband speed for three upgraded connections is 953Mb - institutions previously had 20-100Mb connections, increased to 1Gb each. The net increase was calculated for each site and averaged together. Average increase in broadband speed for 37 new connections is 2.78Gb - institutions considered "new" (institutions never before served by sub recipient) are treated as having a previous speed of zero. The new connections are typically 1Gb, with three at 10Gb and one at 40Gb. The speed for each connection was averaged together. Overall average increase in broadband speed is 2.64Gb when net increase from all sites above is averaged together. | No retail services will be provided until network is available in last mile service areas. | Services provided by this project predominantly include simple, large bandwidth connectivity over fiber and using Ethernet equipment owned and operated by the connected institutions. Expected service rates will be limited only by the hardware capacity. All traffic will be allowed to each institution which has the right to filter, limit, or block as needed for that institution. No rate limits, content filtering, or connectivity restrictions will be applied by UW-Extension or other outside party. Network management policies in each community are under development. All policies will allow open access, interconnection and promote nondiscrimination. UW-Extension network management policies are available on our Web site:http://broadband.uwex.edu. | NA | 67995 | 571 | 0 | 36170 | 0 | 0 | 31254 | NA | 0 | 0 | 0 | 0 | We are building no new collocation space with grant funds. Existing facilities will be used for interconnection, typically utilizing existing racks in data centers located at technical college and university where other network providers and/or customers may install equipment. We do not anticipate the need for providing actual floor space for customer or provider owned racks. Additional interconnect at a basic fiber-splice level will be available in buried communications vaults throughout the network footprint. | 0 - none of our subcontractors are small businesses. | It is advisable to include environmental experts early and throughout all phases of project construction. If these experts are not available in-house, find qualified consultants to ensure compliance with all requirements. There are more agencies involved than might initially seem likely and the requirements are often more stringent for federally-funded projects than might otherwise be the case in privately-funded projects. It may take multiple experts to cover all requirements, such as those experienced in archeological, historical, wetlands and waterways, and threatened and endangered species. Another best practice and lesson learned is the value of our key partnerships. Our project was created through collaboration with many entities that had similar missions and clearly shared the goals of the endeavor. The partnership built off the strengths of each individual organization, bringing together the technical, construction experience and community engagement skill sets needed for completion. Given the scope and complexities inherent in this project, the partnership has proven to be invaluable. Our partners have been engaged, informed and remained steadfast in making the numerous adjustments required to complete the project successfully. | University of Wisconsin System | 32 | 5 | 10 | 11 | 26 | 20 |  | 50 | 16 | 2 | 172 | 1. No interconnection agreements were signed this year. 2. Negotiations are currently underway with two providers. 3. No interconnection agreements were denied this year. | No activity has occurred regarding peering and transit agreements this year. | TRUE
NT10BIX5570115 | 2013 | 50,220 | Average cost in Baseline Plan was 52,916. | 142 | Average cost in Baseline Plan was 167. | 31,232 | Average cost in Baseline Plan was 941. The Baseline Plan assumed 331 residential and 220 business subscribers over a two year growth period. However, actual services were limited to 14 residential subscribers since services did not become available until the last quarter of the project. | 40Gb | Baseline Plan was 10Gb. Actual connections for Community Anchor Institutions included one subscriber at 40Gb, 2 subscribers at 20Gb and 12 subscribers at 10Gb. New technology and demands exceeded expectations set three years prior. | 20Mb | Baseline Plan was 10,000 Mb. Of the 14 actual subscribers connected, eight of them are at 20 Mb. The variance is due to a new understanding of this category since initial application: the baseline value falsely included wholesale backbone circuit sizes. Those wholesale links are excluded in this calculation, leaving just business and residences in last mile service areas. | 1874Mb | The baseline plan was 513 Mb. Most new connections are 1Gb. The speeds range from 10 Mb to 40Gb. We calculated the average of all 172 Community Anchor Institutions currently receiving services. The variance is due to more users with high speed connections (10Gb, 20Gb and 40Gb) than initially anticipated. | 17Mb | Of the 14 actual subscribers connected, eight of them are at 20 Mb, three are at 15Mb and three are at 10Mb.The variance from baseline is due to a new understanding of this category since initial application: the baseline value incorrectly included wholesale backbone circuit sizes. Those wholesale links are excluded here, leaving just business and residences in last mile service areas. | The average broadband speed for 20 UPGRADED connections increased from 734Mb to 4,300 Mb - institutions previously had 20-2,000Mb connections that increased to 1,000 - 20,000Mb. The increase was calculated for each individual site and then averaged together. The average broadband speed for 152 NEW connections increased from 0 speed to 1.17Gb - institutions considered "new" are institutions never before served by sub recipient. The new connections are typically 1 or 2Gb, with five at 10Gb and one at 40Gb. The increase was calculated for each site and averaged together. | Our last mile service provider is offering High-Speed Internet access delivered via cable modem and fiber architecture to residential customers with speed range from 10-20Mb and price range of $36.95 - $56.95 per month. Business customers offerings include high -Speed Cable Modems with a low speed of 10Mb at $89.95 per month to highest Point-to-Point speed of 1,000 Mb for $2,450 per month. | Services provided by this project predominantly include simple, large bandwidth connectivity over fiber and using Ethernet equipment owned and operated by the connected institutions. Expected service rates will be limited only by hardware capacity. All traffic will be allowed to each institution which has the right to filter, limit, or block as needed for that institution. No rate limits, content filtering, or connectivity restrictions will be applied by UW-Extension or other outside party. All policies will allow open access, interconnection and promote nondiscrimination. UW-Extension network management policies are available on our Web site:http://broadband.uwex.edu. | NA | 54792 | 11002 | 0 | 43790 | 0 | 0 | 0 | As sub recipient, Packerland Broadband has access to dark fiber and will provide wholesale services to third party providers. Currently they are leasing 409 miles of fiber to one provider and 331 miles to another provider. | 0 | 0 | 0 | 0 | We are building no new collocation space with grant funds. Existing facilities will be used for interconnection, typically utilizing existing racks in data centers located at technical college and university where other network providers and/or customers may install equipment. We do not anticipate the need for providing actual floor space for customer or provider owned racks. Additional interconnect at a basic fiber-splice level will be available in buried communications vaults throughout the network footprint. | 0 - none of our subcontractors are small businesses. | It is advisable to include environmental experts early and throughout all phases of project construction. If these experts are not available in-house, find qualified consultants to ensure compliance with all requirements. There are more agencies involved than might initially seem likely and the requirements are often more stringent for federally-funded projects than might otherwise be the case in privately-funded projects. It may take multiple experts to cover all requirements, such as those experienced in archeological, historical, wetlands and waterways, and threatened and endangered species. Another best practice and lesson learned is the value of our key partnerships. Our project was created through collaboration with many entities that had similar missions and clearly shared the goals of the endeavor. The partnership built off the strengths of each individual organization, bringing together the technical, construction experience and community engagement skill sets needed for completion. Given the scope and complexities inherent in this project, the partnership has proven to be invaluable. Our partners have been engaged, informed and remained steadfast in making the numerous adjustments required to complete the project successfully. | University of Wisconsin System | 32 | 5 | 10 | 11 | 26 | 20 |  | 50 | 16 | 2 | 172 | 1. No interconnection agreements were signed this year. 2. No negotiations are currently underway. 3. No interconnection agreements were denied this year. | No activity has occurred regarding peering and transit agreements this year. | TRUE
NT10BIX5570116 | 2010 | 0 | No services are yet being provided. The project is still completing its Environmental Assessment. | 0 | N/A | 0 | N/A | 0 | No services are yet being provided. The project is still completing its Environmental Assessment. | 0 | N/A | 0 | No services are yet being provided. The project is still completing its Environmental Assessment. | 0 | N/A | During the reporting period, no community anchor institutions were connected or passed by this project. The project is still completing its Environmental Assessment. | During the reporting period, no retail services were provided. The project is still completing its Environmental Assessment. | During the reporting period, no network management policies were in place, as the Environmental Assessment is still in progress. No consumers were limited or blocked access to any lawful content, service, service provider or application, or prevented from attaching any legal devise to the network. This publicly owned network will be governed by a board composed of official representatives of five Pueblos, three Counties, one City and one inter-governmental organization, to whom the grant was awarded. This board is in formation. No services are being provided because the project is still completing its Environmental Assessment. These issues will be addressed upon formation of the board and in accordance with federal regulations. | N/A. No services have been provided to date. The project is still completing its Environmental Assessment. | 16217 | 0 | 0 | 0 | 16217 | 0 | 0 | No dark fiber services are yet being provided. The project is still completing its Environmental Assessment. | 0 | 0 | 0 | 0 | Once the Environmental Assessment is complete and network implementation begins, the project will own its collocation space and offer interconnect points with other network providers and customers. The project can also collocate with interconnect providers at their facilities, should that option be deemed appropriate, either by creating a passive interconnect point at a splice point within a manhole location, or by building REDI Net owned infrastructure into the interconnect providers' facilities and collocating REDI Net equipment there. | No subcontracts have yet been awarded to such entities. The project has two contracts in place, one for the Environmental Assessment and one for Engineering and Project Management. | This project includes five federal or state permitting agencies and five Indian tribes, in addition to the three counties and one city that make up the rest of the consortium. NTIA BTOP staff provided valuable assistance in working with the other federal partners, but it would have been a great advantage to have had a programmatic agreement at the federal level to insure all local and regional staff had the authority to accept the NTIA Environmental Assessment format and the direction to do so, with the understanding that all individual agency concerns would be addressed in the EA. That said, the selection of a highly qualified EA firm with strong local working relationships with these other federal partners helped to expedite the EA process. In addition, the selection of an engineering and management team with local knowledge was essential. Getting things done fast requires trust among disparate partners, especially in such an unusual partnership.. It also means there is a practical limitation on how much time one can spend building relationships and educating team members about the specific and often unique needs of some of the parties involved. Finally, when dealing with so many jurisdictions, it is essential to investigate fully the status of all easement agreements between the infrastructure owners and land owners. | North Central New Mexico Economic Development District | 30 | 4 | 0 | 4 | 12 | 17 |  | 24 | 19 | 0 | 110 | There were no interconnection agreements entered into during this reporting period, no agreements are under negotiation and no denials have been made for interconnection. The project is still completing its Environmental Assessment. | There were no peering and/or transit agreements entered into during this reporting period, no agreements are under negotiation and no denials have been made. The project is still completing its Environmental Assessment. | TRUE
NT10BIX5570116 | 2011 | $89964.88 | Cost per mile is higher than baseline because the majority of construction completed to date is underground construction, which has a higher per mile cost. As more aerial segments are built out, the cost per mile will decrease. | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 16217 | 0 | 0 | 0 | 16217 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | Once the construction is complete and network implementation begins, the project will own its collocation space and offer interconnect points with other network providers and customers. The project can also collocate with interconnect providers at their facilities, should that option be deemed appropriate, either by creating a passive interconnect point at a splice point within a manhole location, or by building REDI Net owned infrastructure into the interconnect providers' facilities and collocating REDI Net equipment there. | N/A | Verify all the route easements well in advance along with early coordination with the easement owners. Also ensure that all desired network and community anchor locations are identified and included in the Environmental Assessment. | North Central New Mexico Economic Development District | 30 | 4 | 0 | 4 | 12 | 17 |  | 24 | 19 | 0 | 110 | N/A | N/A | TRUE
NT10BIX5570116 | 2012 | 0 | N/A. Network was not "live" and no production quality, revenue generating services were provided in 2012. Only trial based services were offered, on a limited basis, for assisting with network testing. "Go-live" planned for Feb 2013. | 0 | N/A. | 0 | N/A. | 0 | N/A. Network was not "live" and no production quality, revenue generating services were provided in 2012. Only trial based services were offered, on a limited basis, for assisting with network testing. "Go-live" planned for Feb 2013. | 0 | N/A. | 0 | N/A. Network was not "live" and no production quality, revenue generating services were provided in 2012. Only trial based services were offered, on a limited basis, for assisting with network testing. "Go-live" planned for Feb 2013. | 0 | N/A. | On average, we find that CAIs that are currently utilizing a DSL or cable modem style service are moving to a fiber service on REDI Net below 10 Mbps. However, the performance of REDI Net fiber-based services is typically far superior to that of older DSL/cable modem services, even though the "advertised" speeds might be similar numbers. So, there may not be an increase when comparing the numbers of the advertised speeds, but there are significant performance improvements on REDI Net. CAI's that are on private line T-1 type services from the incumbent telephone companies are typically moving to 10 Mbps and 20 Mbps services from REDI Net. We also find that CAIs on higher tiers of service, such as 50 Mbps and 100 Mbps, are doubling their capacity over the current incumbent services, indicating a market gap that REDI Net has been able to address. | REDI Net provides wholesale services to last-mile providers and to qualifying CAIs. REDI Net does not provide retail consumer services. | REDI Net's Board of Directors has enacted a comprehensive Network Policy manual, addressing both CAI network services and wholesale services to last-mile providers. The service policies contain provisions for establishing the bandwidth rate pursuant to the tier of service being subscribed to. REDI Net does not prioritize traffic based on source/destination addressing nor application type. REDI Net forwards data packets at the speed provisioned under the service tier. REDI Net has not limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. REDI Net's network management policies have also adopted Open Access, Nondiscrimination and Interconnection provisions, consistent the the terms provided NTIA BTOP. | N/A. REDI Net has not experienced any churn. | 13858 | 13858 | 0 | 0 | 16401 | 0 | 0 | N/A. REDI Net does not currently offer wholesale access to dark fiber. | 484 | 436 | 0 | 48 | REDI Net Point-of-Presence (POP) facilities contain collocation space and offers interconnect points with other network providers and customers. REDI Net also collocate with interconnect providers at their facilities, should that option be deemed appropriate, either by creating a passive interconnect point at splice point within a manhole location, or by building our own infrastructure into the interconnect providers facilities and collocating our equipment there. REDI Net also considers establishing "meet-me-points" with last-mile providers at outside plant locations, such as vaults, cabinets, and splice cases. | n/a | Establish best practices for asset management early on to ensure development of operational and financial infrastructure is addressed adequately. In turn, a practical business model can be created and sustained. Given the complexity and multi-layered partnerships REDI Net has, critical attention is necessary towards provision and update of information to all stakeholders on regular basis. | North Central New Mexico Economic Development District | 30 | 4 | 0 | 4 | 12 | 17 |  | 24 | 19 | 0 | 110 | REDI Net signed one interconnect agreement, for providing REDI Net with upstream Internet bandwidth. REDI Net was under negotiation with 5 downstream last-mile providers, for providing them with wholesale Internet and point-to-point Ethernet transport. No requests were denied for interconnection. | There were no peering and/or transit agreements entered into during this reporting period, no agreements were under negotiation, and no denials were made. | TRUE
NT10BIX5570116 | 2013 | $56,393.67 | 136 new route miles built at a direct capital cost of $7,669,539.66, for the installation of the passive elements of the middle-mile transmission infrastructure. The 136 new route miles are comprised of 108 new linear fiber route miles (not actual fiber miles) and 28 new route miles of microwave transmission. | 0 | N/A | 0 | N/A | 100Mbps | 100Mbps is the maximum advertised speed pursuant to a standardized rate schedule. However, speeds up to 10Gbps are quoted on a case-by-case basis, depending on available infrastructure resources. | 0 | N/A | 37Mbps | 37Mbps is the average speed provided, based on actual service subscriptions. | 0 | N/A | On average, we find that CAIs that are currently utilizing a DSL or cable modem style service are moving to a fiber service on REDI Net below 10 Mbps. However, the performance of REDI Net fiber-based services is typically far superior to that of older DSL/cable modem services, even though the "advertised" speeds might be similar numbers. So, there may not be an increase when comparing the numbers of the advertised speeds, but there are significant performance improvements on REDI Net. CAI's that are on private line T-1 type services from the incumbent telephone companies are typically moving to 10 Mbps and 20 Mbps services from REDI Net. We also find that CAIs on higher tiers of service, such as 50 Mbps and 100 Mbps, are doubling to quadrupling their capacity over the current incumbent services, indicating a market gap that REDI Net has been able to address. Based on the before/after speeds for the CAIs connected under the trial/provisional service, the average increase was ~25 Mbps. | REDI Net provides wholesale services to Last-Mile Providers and to qualifying CAIs. REDI Net does not provide retail consumer services. REDI Net's CAI and Last-Mile Provider pricing plan is as follows: 1 Mbps, Ethernet & Internet Bundle, $80.00 MRC; 1 Mbps, Ethernet Only, $60.00 MRC 3 Mbps, Ethernet & Internet Bundle, $210.00 MRC; 3 Mbps, Ethernet Only, $157.50 MRC 5 Mbps, Ethernet & Internet Bundle, $300.00 MRC; 5 Mbps, Ethernet Only, $225.00 MRC 10 Mbps, Ethernet & Internet Bundle, $500.00 MRC; 5 Mbps, Ethernet Only, $375.00 MRC 15 Mbps, Ethernet & Internet Bundle, $675.00 MRC; 15 Mbps, Ethernet Only, $506.25 MRC 20 Mbps, Ethernet & Internet Bundle, $800.00 MRC; 20 Mbps, Ethernet Only, $600.00 MRC 35 Mbps, Ethernet & Internet Bundle, $1,050.00 MRC; 35 Mbps, Ethernet Only, $787.50 MRC 50 Mbps, Ethernet & Internet Bundle, $1,200.00 MRC; 50 Mbps, Ethernet Only, $900.00 MRC 75 Mbps, Ethernet & Internet Bundle, $1,575.00 MRC; 75 Mbps, Ethernet Only, $1,181.25 MRC 100 Mbps, Ethernet & Internet Bundle, $1,800.00 MRC; 100 Mbps, Ethernet Only, $1,350.00 MRC 1 Gbps, Ethernet & Internet Bundle, custom quote; 1 Gbps, Ethernet Only, custom quote Services above 100 Mbps are quoted on a case-by-case basis, pending engineering analysis, network resource availability, and subcommittee review. For last-mile service providers, REDI Net also offers co-location services, on a similar custom quote process. | REDI Net's Board of Directors has enacted a comprehensive Network Policy manual, addressing both CAI network services and wholesale services to last-mile providers. The service policies contain provisions for establishing the bandwidth rate pursuant to the tier of service being subscribed to. REDI Net does not prioritize traffic based on source/destination addressing nor application type. REDI Net forwards data packets at the speed provisioned under the service tier. REDI Net has not limited or blocked consumers from accessing any lawful content, service, service provider, or application, or prevented any consumers from attaching any legal device to the network. REDI Net's network management policies have also adopted Open Access, Nondiscrimination and Interconnection provisions, consistent the the terms provided NTIA BTOP. | N/A. REDI Net has not experienced any churn. | 16620 | 16620 | 0 | 0 | 0 | 0 | 0 | N/A. REDI Net does not currently offer wholesale access to dark fiber. | 242 | 224 | 0 | 18 | REDI Net installed two new Point-of-Presence (POP) facilities that contain collocation space. The Espanola POP is a 242 sq. ft. facility, with 224 sq. ft. being used by REDI Net and 18 sq. ft. of collocation space available (qty. 3 2'x3' cabinets). The Espanola POP serves as a POI, by establishing physical connection through either colocation at the POP, or at a midspan meet point, depending on service provider preferences. While the Santa Fe POP facility construction is complete, it is not currently capable of establishing interconnects with REDI Net until a 3rd party fiber build is finished to the POP, post-BTOP. Therefore, the square footage of the SF POP and available colocation space is not reported above in question 11. However, once the 3rd party fiber build is completed post-BTOP, the 242 sq. ft. facility will have 230 sq. ft. used by REDI Net and 12 sq. ft. of collocation space available (qty. 2 2'x3' cabinets).The third REDI Net POP is in Los Alamos, NM. This is a shared facility which is not REDI Net property, nor was it funded through the REDI Net grant. The facility is owned by Los Alamos County government. REDI Net's space in the shared communications room is limited and does not enable colocation. However, interconnections could be established with REDI Net if the 3rd party were able to create their own presence in the shared communications room, by gaining approval from the facility owner. Midspan meet points would be another interconnect option for the Los Alamos POP. The Espanola POP and Los Alamos POP are a completed REDI Net community pair, as reported in the final APR Addendum (spreadsheet). | not applicable | REDI Net as a joint public network requires continuing collaboration amongst the local and tribal governments. Towards this end, much of the design, build and development of the infrastructure require consensus on achieving mutual and common benefits and impact for a large geographic region with diverse cultural and environmental fabric. Active and ongoing engagement with public and private stakeholders were critical and key to completing the middle mile open access network to the extend that it functions and operates in a robust high performance manner. This parallels the innovations for better asset management practices that attempts to align with the changing needs of the respective communities in Northern New Mexico. As a result, opportunities to expand beyond the built coverage area in collaboration with other public and private entities have actualized. | North Central New Mexico Economic Development District | 30 | 4 | 0 | 4 | 12 | 17 |  | 24 | 19 | 0 | 110 | REDI Net signed SLAs with 3 downstream last-mile providers, Plateau Telecommunications, Los Alamos Network, and Cyber Mesa, for providing them with wholesale Internet and point-to-point Ethernet transport. No interconnection requests were denied for interconnection. | REDI Net has signed one IP transit agreement, with Plateau Telecommunications, for providing REDI Net with upstream Internet bandwidth. There were no peering and/or transit agreements entered into during this reporting period, no agreements were under negotiation, and no denials were made. | TRUE
NT10BIX5570117 | 2010 | 0 | na | na | na | na | na | na | na | na | na | na | na | na | na | NA Deployment has not yet started. | NA Retail services are not provided in this project. | Not completed during this reporting period. | NA Deployment has not yet started. | 69288 | 0 | 0 | 0 | 26500 | 28930 | 13858 | NA | 0 | 0 | 0 | 0 | No co-location space is currently active in this project. | NA | NA | Oconee County | 23 | 4 | 1 | 0 | 0 | 28 |  | 24 | 22 | 0 | 102 | na | na | TRUE
NT10BIX5570117 | 2011 | 36,237 | N/A | 0 | N/A | 0 | N/A | 10 GB | N/A | 1GB | N/A | 10mb | N/A | 0 | N/A | Most anchors will receive 1 GB connection. Currently most do not have a connection. | N/A | N/A | N/A | 2304 | 0 | 0 | 2304 | 0 | 0 | 0 | N/A | 1350 | 0 | 0 | 1350 | Oconee FOCUS will have collocation space available in future. At this moment, the team is in process of setting up the NOCs. | GeoVision, Technology Solutions, JET, and Network Controls | - Crossing rail roads at public or SC DOT right of way areas. Private crossings are expensive. - Constant communication between engineering, construction, blowing, and splicing crews is critical. - Continue to work with fiber manufacture on lead times. | Oconee County | 23 | 4 | 1 | 0 | 0 | 28 |  | 24 | 22 | 0 | 102 | N/A | N/A | TRUE
NT10BIX5570117 | 2012 | 36237 | na | 0 | na | 0 | na | 10GB | na | 1GB | na | 10mb | na | 0 | na | Most anchors will receive 1GB connection. Currently most do not have a connection. | na | na | na | 2304 | 0 | 0 | 2304 | 0 | 0 | 0 | County has entered into a dark fiber agreement with DukeNet for 143 fiber miles. | 1350 | 0 | 0 | 1350 | Project FOCUS will allow collocation at Seneca NOC. Future collocation sites at fire stations and other NOCs. | GeoVision, Technology Solutions, JET, and Network Controls | Quality verification, identification, and inspection of hand hole, depth, and anchor egress. GPS of fiber, hand hole, markers, and splice points. Results entered into fiber management software. | Oconee County | 23 | 4 | 1 | 0 | 0 | 28 |  | 24 | 22 | 0 | 102 | NA | NA | TRUE
NT10BIX5570117 | 2013 | 36237 | na | 0 | na | 0 | na | 10 GB | na | 1GB | na | 10mb | na | 0 | na | Most anchors will receive 1GB connection. Currently most do not have GB connection. | na | na | na | 36288 | 3629 | 0 | 32659 | 0 | 0 | 0 | County has entered into a dark fiber agreement with Dukenet for 143 fiber miles | 1350 | 400 | 0 | 950 | Project FOCUS will allow collocation at Seneca NOC. Future collocation sites at fire stations and other NOCs. | Geovision, JET, Network Controls, and Technology Solutions | 17 aggregation sites built to reduce costs of build out for last mile connections for ISPs. ISPs take advantage GPON connections closer to the businesses and residential areas which provides sustainability for the project and cost savings for customer. Utilizing Telvent software to manage and map both inside and outside fiber infrastructure. | Oconee County | 23 | 4 | 1 | 0 | 0 | 28 |  | 24 | 22 | 0 | 102 | na | na | TRUE
NT10BIX5570118 | 2010 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | WAN service to schools in Bienville, Claiborne, Lincoln, Winn, and Union Parishes have been upgraded via matching funds in anticipation of connection to the new fiber backbone. Schools in Bienville and Claiborne are being upgraded with very high speed licensed microwave services which effectively increased their prior speeds from 10 MBits to 300 MBits per WAN link. Schools in Lincoln have been upgraded via dedicated fiber providing one gigabit service to each site in the City of Ruston and 300 MBit licensed band microwave to outlying areas of the parish. Schools in Winn have been upgraded via dedicated fiber providing one gigabit service to each site in in the City of Winnfield with 300 MBit licensed band microwave to outlying areas of the parish. School sites in Lincoln and Winn had been operating at anywhere from 3 MBits to 10 MBits prior to the upgrades. Libraries in Claiborne Parish have been upgraded from 1.5 MBit ("T1") service to 20 MBit service delivered via fiber and licensed band backhauls. | N/A - Retail services are not provided at this time. | There are no bandwidth limitations or traffic prioritization policies in place for customers on this network. Network design is to provide each customer with full bandwidth without blocking or oversubscription. | N/A - No customer churn at this point. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - There is no wholesale dark fiber at this time. | 0 | 0 | 0 | 0 | Co-location planning is underway as part of the design and construction process. Co-location is projected to be available at the Huey P Long Hospital (Pineville - not a Nexus owned facility), and Nexus facilities in Dry Prong, Winnfield, Jonesboro, Ruston, and Vienna. Although construction design has not been finalized at this time, the co-location facilities are projected to be 288 to 384 square feet with approximately half the space available for co-location. | N/A - No contracts to date have been let to concerns as defined by section 8(a) of the Small Business Act. | At this point in the project, we are engaged in engineering design and environmental assessment services. For best practices, we learned the most impressive engineering firms may not be the best contractors for this type of project. In our case, we selected an excellent firm with impressive credentials which appeared to exceed our expectations. We were disappointed, however, when the firm withdrew as it was not willing to commit the resources to meet timelines and other commitments for the project. We also learned many professional engineers appear to not read an RFP, but instead reply with a standardized, vague, response and do not wish to commit to project fee caps or timelines as noted above. We learned our best engineer might be the smaller firm with a good organizational effort. The best practice therefore is to carefully prepare specifications in the engineering RFP and even more carefully evaluate proposals received. Environmental assessment response appear to be the item which will cause the greatest delays in any of the BTOP or BIP projects. In another project, we have already experienced six to eight month delays for environmental clearances which would normally be routine. the problem appears to be the environmental officers at all levels (local, State, Federal) are overwhelmed with project requests. The lesson learned is environmental clearance processing cannot be a passive request process, but must be pursued on a daily basis. | Nexus Systems, Inc. | 67 | 18 | 3 | 2 | 6 | 5 |  | 7 | 0 | 0 | 108 | N/A - Interconnection agreements for this project have not been completed at this time. | N/A - Peering and Transit Agreements for this project have not been completed at this time. | TRUE
NT10BIX5570118 | 2011 | 56000 | Cost based on budgeted cost of construction of 125 miles including all facilities and equipment. | 0 | N/A - Middle mile project | 0 | N/A - Middle mile project | 10G | Standard speeds will be from 10M to 10G | 0 | N/A - Middle mile project | 0 | Network not yet available due to construction in progress | 0 | N/A - Middle mile project | WAN service to schools in Bienville, Claiborne, Lincoln, Winn, and Union Parishes have been upgraded via matching funds in anticipation of connection to the new fiber backbone. Schools in Bienville and Claiborne are being upgraded with very high speed licensed microwave services which effectively increased their prior speeds from 10 MBits to 300 MBits per WAN link. Schools in Lincoln have been upgraded via dedicated fiber providing one gigabit service to each site in the City of Ruston and 300 MBit licensed band microwave to outlying areas of the parish. Schools in Winn have been upgraded via dedicated fiber providing one gigabit service to each site in in the City of Winnfield with 300 MBit licensed band microwave to outlying areas of the parish. School sites in Lincoln and Winn had been operating at anywhere from 3 MBits to 10 MBits prior to the upgrades. Libraries in Claiborne Parish have been upgraded from 1.5 MBit ("T1") service to 20 MBit service delivered via fiber and licensed band backhauls. | N/A - Retail services are not provided at this time. | There are no bandwidth limitations or traffic prioritization policies in place for customers on this network. Network design is to provide each customer with full bandwidth without blocking or oversubscription. | N/A - There has been no customer churn at this point. | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - There is no wholesale dark fiber at this point. | 1680 | 840 | 0 | 840 | Co-location planning is underway as part of the design and construction process. Co-location is projected to be available at the Huey P Long Hospital (Pineville - Nexus owned facility on grounds of the hospital), and Nexus facilities in Dry Prong, Winnfield, Jonesboro, Ruston, and Vienna. Co-location facilities are 120 square feet except for Vienna which is 1200 square feet. Approximately half the space available for co-location in each location. | N/A - No contracts to date have been let to concerns as defined by section 8(a) of the Small Business Act. | We followed the established USDA RUS format for engineering and contracting and found these contracts and standards protected all parties fairly. Early securing of fiber was essential to success in the project . We were very disappointed to discover the absolute power railroads have and how they can hold a project hostage for any amount of budget dollars the railroad deems appropriate. We learned to value and advantage of hiring an expert environmental engineer to keep the project on track with the complex requirements of the environmental review. Through our project engineer, we found the value of contracting with an experienced installation company as opposed to the first or lowest bidder. | Nexus Systems, Inc. | 67 | 18 | 3 | 2 | 6 | 5 |  | 7 | 0 | 0 | 108 | N/A - Interconnection agreements for this project have not been completed at this time due to construction in progress. | N/A Peering and transit agreements for this project have not been completed at this time due to construction in progress. | TRUE
NT10BIX5570118 | 2012 | 38035 | Cost based on actual cost of construction to date of 125 miles. | 0 | N/A - Middle mile project | 0 | N/A - Middle mile project | 10G | Standard speeds will be from 10M to 10G | 0 | N/A - Middle mile project | 500 | CAI sites connected at speeds from 100M to 1G. | 0 | N/A - Middle mile project | WAN service to schools in Bienville, Claiborne, Lincoln, Winn, and Union Parishes have been upgraded via matching funds in anticipation of connection to the new fiber backbone. Schools in Bienville and Claiborne are being upgraded with very high speed licensed microwave services which effectively increased their prior speeds from 10 MBits to 300 MBits per WAN link. Schools in Lincoln have been upgraded via dedicated fiber providing one gigabit service to each site in the City of Ruston and 300 MBit licensed band microwave to outlying areas of the parish. Schools in Winn have been upgraded via dedicated fiber providing one gigabit service to each site in in the City of Winnfield with 300 MBit licensed band microwave to outlying areas of the parish. School sites in Lincoln and Winn had been operating at anywhere from 3 MBits to 10 MBits prior to the upgrades. Libraries in Claiborne Parish have been upgraded from 1.5 MBit ("T1") service to 20 MBit service delivered via fiber and licensed band backhauls. | N/A - Retail services are not provided at this time. | There are no bandwidth limitations or traffic prioritization policies in place for customers on this network. Network design is to provide each customer with full bandwidth without blocking or oversubscription. | N/A - There has been no customer churn at this point. | 18000 | 3000 | 0 | 15000 | 20228 | 0 | 17228 | N/A - There is no wholesale dark fiber at this point. | 2480 | 1240 | 0 | 1240 | Co-location planning is underway as part of the design and construction process. Co-location is available available at Nexus facilities in Dry Prong, Winnfield, Jonesboro, and Vienna as well as the Nexus Venable POP. Co-location facilities are 120 square feet except for Vienna which is 1400 square feet and Venable at 360 square feet. Approximately half the space available for co-location in each location. | N/A - No contracts to date have been let to concerns as defined by section 8(a) of the Small Business Act. | We followed the established USDA RUS format for engineering and contracting and found these contracts and standards protected all parties fairly. Early securing of fiber was essential to success in the project . We learned to value and advantage of hiring an expert environmental engineer to keep the project on track with the complex requirements of the environmental review. Through our project engineer, we found the value of contracting with an experienced installation company as opposed to the first or lowest bidder. As we continue with the project through a project modification, we have learned the essential nature of tracking environmental and related regulatory concerns carefully. We have also found partners willing to enhance the project through cooperative endeavors. | Nexus Systems, Inc. | 67 | 18 | 3 | 2 | 6 | 5 |  | 7 | 0 | 0 | 108 | N/A - Interconnection agreements for this project have not been completed at this time due to construction in progress. | N/A Peering and transit agreements for this project have not been completed at this time due to construction in progress. | TRUE
NT10BIX5570119 | 2010 | n/a | No construction yet | n/a | Middle-mile project | n/a | Middle-mile project | n/a | No speeds advertised yet | n/a | Middle-mile project | n/a | No service provided yet | n/a | Middle-mile project | n/a; no connections yet | n/a; no services provided yet | n/a | n/a | 0 | 0 | 0 | 0 | 1960 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | n/a; no construction yet | We made no subcontracts or subgrants in the reporting period | n/a | Horizon Telecom, Inc. | 622 | 166 | 25 | 19 | 353 | 407 |  | 744 | 612 | 476 | 3424 | n/a | n/a | TRUE
NT10BIX5570119 | 2011 | 0 | Not yet available. The first work-orders have only just begun to close. There is not enough information to provide decisive data. | 0 | n/a | 0 | n/a | 10 Gbps | n/a | 0 | n/a | 16 Mbps | n/a | 0 | n/a | Average increase in speed was 8.5 Megabytes per second (Mbps). Most above had a T1 which is 1.5 Mbps and have chosen 10 Mbps. | Horizon is offering retail customers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). Pricing plan redacted. Pricing plans are only a starting point for negotiations and are not written in stone. | None. We are not limiting or blocking access to our network. | none | 257600 | 100 | 0 | 57500 | 60000 | 120000 | 20000 | none | 0 | 0 | 0 | 0 | When we complete our builds to Columbus and Cincinnati we will be in the same proximity as other major carriers. This will be an optical hand-off. | KGP Logistics - 1 sub-contract | n/a | Horizon Telecom, Inc. | 622 | 166 | 25 | 19 | 353 | 407 |  | 744 | 612 | 476 | 3424 | 1. Six (6) 2. One (1) 3. Zero (0) | n/a | TRUE
NT10BIX5570119 | 2012 | $46,876 | Initial statistics appear to be running slightly below the projected cost in our baseline (96.75% of $48,450). However we are seeing signs that the costs will come in much higher due to higher than average costly make-ready charges. | 0 | n/a | 0 | n/a | 10 Gbps | n/a | 0 | n/a | 16 Mbps | This is a direct result of slower build rate than expected. The environmental assessment requirements, make-ready and permitting delays put us behind our baseline of 20 Mbps in year 1 and 150 Mbps in year 2. These rates will increase as the build is finished and more customers are added. This rate is the result of thirty-two connections ranging from 5 Mbps to 1 Gbps, averaging 16 Mbps. | 0 | n/a | Average increase in broadband speed provided is 60 Mbps. Calculated by averaging speed prior to connection with Horizon (in most cases a T-1 or 1.5 Mbps, but ranging from 0 to 100 Mbps) which was 9 Mbps subtracted from average of current connection with Horizon (ranging from 5 Mbps to 1 Gbps) which was 69 Mbps, for a total of 60 Mbps. | Horizon is offering retail customers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). Pricing plan redacted. Pricing plans are only a starting point for negotiations and are not written in stone. | none | none | 257500 | 101355 | 0 | 520 | 155129 | 0 | 496 | Windstream - 250 miles | 0 | 0 | 0 | 0 | Connectlink, Inc - we connect at their physical location Country Connection (2) - we connect at their physical location JB-Nets, LLC - we connect at their physical location New ERA Broadband - we connect at their physical location Smart Networks - we connect at their physical location Southern Ohio Communication Services (SOCS) - we connect at their physical location | KGP Logistics - 1 sub-contract | none | Horizon Telecom, Inc. | 622 | 166 | 25 | 19 | 353 | 407 |  | 744 | 612 | 476 | 3424 | 1. Avolve; Connectlink, Inc; Country Connection (2); Firewire; GMN Wireless Broadband; Intelliwave; JB-Nets, LLC; New ERA Broadband; Rowe Wireless Networks; Smart Networks; Southern Ohio Communication Services (SOCS); Windstream. 2. Zero (0) 3. Zero (0) | n/a | TRUE
NT10BIX5570119 | 2013 | $64,516 | 133.2% of $48,450. This per mile rate does includes estimates for post construction make ready not yet invoiced. | 0 | n/a | 0 | n/a | 10 Gbps | n/a | 0 | n/a | 108 Mbps | Based on direct connections; subscribers have speeds ranging from 5 Mbps to 1 Gbps. | 0 | n/a | Average increase in broadband speed provided is 191 Mbps. Calculated by averaging speed prior to connection with Horizon (in most cases a T-1 or 1.5 Mbps, but ranging from 0 to 100 Mbps) which was 9 Mbps subtracted from average of current connection with Horizon (ranging from 5 Mbps to 1 Gbps) which was 200 Mbps for a total of 191 Mbps. | Horizon is offering retail customers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). Pricing plan redacted. Pricing plans are on a starting point for negotiations and are not written in stone. | 7a. None 7b. No | none | 256293 | 255273 | 0 | 1020 | 0 | 0 | 0 | Windstream - 250 miles Washington County Board of Commissioners - 2 miles | 4882 | 4882 | 0 | 0 | To date we have built to each provider's meet point. Connectlink, Inc - we connect at their physical location Country Connection (2) - we connect at their physical location Intelliwave - we connect at their physical location JB-Nets, LLC - we connect at their physical location New ERA Broadband (2) - we connect at their physical location Rowe Wireless Networks - we connect at their physical location Smart Networks - we connect at their physical location Southern Ohio Communication Services (SOCS) - we connect at their physical location | KGP Logistics - 1 sub-contract | none | Horizon Telecom, Inc. | 622 | 166 | 25 | 19 | 353 | 407 |  | 744 | 612 | 476 | 3424 | 1. Avolve; Connectlink, Inc; Country Connection (2); Firewire; GMN Wireless Broadband; Intelliwave; JB-Nets, LLC; New ERA Broadband; Rowe Wireless Networks; Smart Networks; Southern Ohio Communication Services (SOCS); Windstream. 2. Zero (0) 3. Zero (0) | n/a | TRUE
NT10BIX5570120 | 2010 | $0 | N/A | N/A | N/A | N/A | N/A | $0 | N/A | N/A | N/A | $0 | N/A | N/A | N/A | N/A | N/A | MCNC has Internet/Data Acceptable Use, Nondiscrimination, Interconnection, and Network Management Policies (see https://www.mcnc.org/about/policies.html for further details). MCNC does not impose any bandwidth limitations or access limitations to lawful content, service, service provider, or application or prevent any consumers from attaching any legal device to it's existing infrastructure or on proposed BTOP infrastructure. | N/A | 192922 | 0 | 0 | 112 | 0 | 0 | 192810 | N/A | 0 | 0 | 0 | 0 | We will be deploying network huts as we get in to construction after the FONSI has been received and interconnect can happen at that time in those locations, as well as all handholds with splice locations along the route. | N/A | N/A | MCNC | 57 | 52 | 45 | 7 | 2 | 11 |  | 0 | 1 | 0 | 175 | N/A | N/A | TRUE
NT10BIX5570120 | 2011 | 0 | While newly constructed miles have been installed in the ground, they are not in service at this point, and per guidance are not included in this report. | 0 | N/A to our project | 0 | N/A to our project | 0 | At this point we have not placed any segments in to service. Ultimately the initial offering will be 10Gpbs with capabilities up to 100Gbps. | 0 | N/A to our project | 0 | At this point we have not placed any segments in to service. Ultimately the initial offering will allow for 10Gbps average connectivity. | 0 | N/A to our project | While we have not yet completed any of the infrastructure, plans call for all CAI's to receive service at a minimum of 1Gpbs over the fiber enabled infrastructure. | There are no planned retail service offerings associated with this project as MCNC does not provide residential or service to business enterprises. | The North Carolina Research and Education Network by policy does not limit/restrict access to the network. There is no prioritization of traffic placed on the backbone for IP based services. Lambda based circuits encompass their own payload, so by nature that traffic is prioritized within the circuit design. The only filtering policies on the IP backbone that are utilized relate to anti-spoofing related filters to protect our customers, and the IP based resources of the infrastructure itself. If a site is the target of or initiating a Denial of Service attack, from time to time network access will be limited to resolve those issues. We do have a service that our K-12 community users can procure related to content filtering to satisfy CIPA (Children Internet Protection Act) requirements. | N/A | 189725 | 0 | 0 | 0 | 6372 | 0 | 183353 | No customers have been signed on as of this report. | 0 | 0 | 0 | 0 | MCNC will be deploying telecommunication huts as part of the project as we enter the next 6 months of the project. As of this report, several had been started from a site work perspective, but none had been finished. Where suitable existing space exists, MCNC will use a few select CAI's along the route to house the equipment that will operate the network. | MCNC's efforts for socially and economically disadvantaged small (SDB) business involvement has resulted in one prime contract and four subcontracts through our prime contractors with SDB concerns: SEPI Engineering and Construction, Inc - WBE CBW Communications Engineers - VBE Edwards Telecommunications, Inc. - VBE Minter Consulting - MBE Globenet Telecommunications, LLC - MBE | Work through your permitting process as quickly as possible. Issues will undoubtedly surface that will take additional time. Do not allow your contracts that you award work to only focus on the easy elements of construction first without also addressing some of the difficult elements. We had a situation where they did all the easy stuff, let the remainder, and our prime contractor has had difficulty finding someone to complete the segment they were awarded. Award RFP's early. Implement stringent contracts for material delivery and construction delivery. Expect your legal bills to be more than you anticipated. Celebrate your successes and always look at the big picture. | MCNC | 57 | 52 | 45 | 7 | 2 | 11 |  | 0 | 1 | 0 | 175 | No agreements have been signed to date. Our marketing partner is discussing opportunities with potential carriers and users of the network, but none have been signed to date. We are learning that carriers want to see the final product before making any commitments. No requests for discussion about potential agreements have been denied. | As the construction of the network is ongoing, with no full segments ready for operation, there are no peering and transit agreements yet in place. | TRUE
NT10BIX5570120 | 2012 | 54,349 | While newly constructed miles have been installed in the ground, they are not in service at this point, and per guidance are not included in this report. We are lower to baseline than forecasted because the miles counted toward this calculation are those miles that were cheaper to construct and operate at this point. More challenging and thus costly miles are built, but not yet considered completed and in service. | N/A | N/A to our project | N/A | N/A to our project | 10Gbps | We anticipate initially that most expected service offerings requested from our user base will be 1Gbps through 10Gbps. The system being deployed, however, has capability to scale to 100Gbps as required. | N/A | N/A to our project | 1Gbps | As it relates to services to the CAI's served, all are provisioned with 1Gbps capacity. Along the backbone routes of the network, which at this point we've deployed three such services, the average capacity for those is 10Gbps. | N/A | N/A to our project | The CAI's that we currently serve operate on limited capacity 100M interfaces at most. As we deployed, we are putting them on to burstable 1Gbps links that interface directly with a 10Gbps path. Therefore based on what we know, their immediate increase with the equipment deployed gives them 900Mbps more in capability day one. | There are no planned retail service offerings associated with this project as MCNC does not provide residential or service to business enterprises. The two carriers that have signed on for dark fiber access will provide this service, but to date we do not have visibility in to how they will price their offerings, although we do know that it will be scalable service as required from 10Mbps up to 10Gbps as users warrant. Both carriers are wholesale carriers. Discussions with 1-2 residential providers are ongoing. | The North Carolina Research and Education Network by policy does not limit/restrict access to the network. There is no prioritization of traffic placed on the backbone for IP based services. Lambda based circuits encompass their own payload, so by nature that traffic is prioritized within the circuit design. The only filtering policies on the IP backbone that are utilized relate to anti-spoofing related filters to protect our customers, and the IP based resources of the infrastructure itself. If a site is the target of or initiating a Denial of Service attack, from time to time network access will be limited to resolve those issues. We do have a service that our K-12 community users can procure related to content filtering to satisfy CIPA (Children Internet Protection Act) requirements. | N/A | 197412 | 2092 | 1481 | 65287 | 43632 | 0 | 84920 | MCNC has sold dark fibers to two wholesale carriers, Broadplex and Dukenet Communications. The Broadplex agreement is for 1279 strand miles and the Dukenet Communications agreement is for 202 strand miles. | 3600 | 224 | 0 | 3376 | MCNC has deployed telecommunication huts as part of the project as outlined above. MCNC will additionally use a few select CAI's along the route to house the equipment that will operate the network. In these particular facilities MCNC does not control the ability to allow other carriers or entities to colocate. Above and beyond that, hand hands that are placed no farther apart than a mile act as interconnect points for splicing capability to the backbone to fibers another provider or user would build to those locations. | MCNC's efforts for socially and economically disadvantaged small (SDB) business involvement has resulted in one prime contract and four subcontracts through our prime contractors with SDB concerns: SEPI Engineering and Construction, Inc - WBE CBW Communications Engineers - VBE Edwards Telecommunications, Inc. - VBE Minter Consulting - MBE Globenet Telecommunications, LLC - MBE Vertech International MBE MSM, Inc. MBE Dig-It MBE Coastline Cable Construction WBE HK&L, LLC WBE applied for Peachtree Telecommunications, Inc. WBE | Work through your permitting process as quickly as possible, especially those involving railroads. Issues will undoubtedly surface that will take additional time. Do not allow your contractors that you award work to to only focus on the easy elements of construction first without also addressing some of the difficult elements. Award RFP's early. Implement stringent contracts for material delivery and construction delivery. Expect your legal bills to be more than you anticipated. Celebrate your successes and always look at the big picture. | MCNC | 57 | 52 | 45 | 7 | 2 | 11 |  | 0 | 1 | 0 | 175 | To date we have entered in to two IRU agreements for dark fiber with wholesale and last mile carriers. The agreements were for one fiber across portions of the footprint totaling 1279 miles, and a second agreement for two fibers across 101 miles. We have not executed any other transit, peering, or interconnection agreements to date. Negotiations continue with eight additional providers for fibers in various portions of the constructed route. We have not denied any request for interconnection to the fiber routes. | N/A | TRUE
NT10BIX5570120 | 2013 | $63,759.66 | Total capital construction costs not including IRUs, equipment and software total $82,951,324 for 1,301 miles. We are slightly above baseline of $59,657.62 per mile due to costs of construction in the western portion of the network being higher than expected than in the budget. | NA | N/A to our project | NA | N/A to our project | 100Gbps | We anticipate initially that most expected service offerings requested from our user base will be 1Gbps through 10Gbps. The system being deployed, however, has capability to scale to 100Gbps as required. | NA | N/A to our project | 3.2Gbps | As it relates to services to the CAI's served, all are provisioned with 1Gbps capacity. Along the backbone routes of the network we provisioned thirty-eight 10Gbps backbone services. Additionally we have turned up MPLS based last mile services to the following speeds and tiers of services: 10M:6 20M:4 30M:1 50M:6 100M:52 150M:1 250M:30 275M:2 475M:1 500M:13 1G:11 2G:2 3G:1 | NA | N/A to our project | The CAI's that we currently serve operate on limited capacity 100M interfaces at most. As we deployed, we put them on to burstable 1Gbps links that interface directly with a 10Gbps path. Therefore based on what we know, their immediate increase with the equipment deployed gives them 900Mbps more in capability day one. | There are no planned retail service offerings associated with this project as MCNC does not provide residential or service to business enterprises. Several of the carriers that have signed on for dark fiber access will provide this service, but to date we do not have visibility in to how they will price their offerings. We do know that it will be scalable service as required from 10Mbps up to 100Gbps as users warrant. Additionally one of the carriers that has bought fiber on the whole footprint is a residential provider that in it's current operations provides 50x50M service for $59.95/month. | The North Carolina Research and Education Network by policy does not limit/restrict access to the network. There is no prioritization of traffic placed on the backbone for IP based services. Lambda based circuits encompass their own payload, so by nature that traffic is prioritized within the circuit design. The only filtering policies on the IP backbone that are utilized relate to anti-spoofing related filters to protect our customers, and the IP based resources of the infrastructure itself. If a site is the target of or initiating a Denial of Service attack, from time to time network access will be limited to resolve those issues. We do have a service that our K-12 community users can procure related to content filtering to satisfy CIPA (Children Internet Protection Act) requirements. | N/A | 197921 | 6256 | 11865 | 179800 | 0 | 0 | 0 | MCNC has sold dark fibers to MOX Networks (12 strands over 70 miles), RST Communications (6 strands over 1345 miles), Broadplex Communications (2 strands over 1349 miles), Dukenet Communications (2 strands over 101 miles), Conterra (2 strands over 15.5 miles), and Earthlink (2 strands over 12 miles) to account for the 11,865 strand miles noted above. | 3600 | 592 | 16 | 2992 | MCNC has deployed telecommunication huts as part of the project as outlined above. MCNC will additionally use a few select CAI's along the route to house the equipment that will operate the network. In these particular facilities MCNC does not control the ability to allow other carriers or entities to colocate. Above and beyond that, hand holes that are placed no farther apart than a mile act as interconnect points for splicing capability to the backbone to fibers another provider or user would build to those locations. | MCNC's efforts for socially and economically disadvantaged small (SDB) business involvement has resulted in one prime contract and four subcontracts through our prime contractors with SDB concerns: SEPI Engineering and Construction, Inc - WBE CBW Communications Engineers - VBE Edwards Telecommunications, Inc. - VBE Minter Consulting - MBE Globenet Telecommunications, LLC - MBE Vertech International MBE MSM, Inc. MBE Dig-It MBE Coastline Cable Construction WBE HK&L, LLC WBE applied for Peachtree Telecommunications, Inc. WBE | Work through your permitting process as quickly as possible, especially those involving railroads. Issues will undoubtedly surface that will take additional time. Do not allow your contractors that you award work to to only focus on the easy elements of construction first without also addressing some of the difficult elements. Award RFP's early. Implement stringent contracts for material delivery and construction delivery. Expect your legal bills to be more than you anticipated. Celebrate your successes and always look at the big picture. | MCNC | 57 | 52 | 45 | 7 | 2 | 11 |  | 0 | 1 | 0 | 175 | To date we have entered in to 6 IRU agreements for dark fiber with wholesale and last mile carriers. The agreements are with Broadplex, Dukenet Communications, RST Communications, Conterra, Earthlink, and MOX networks. We have not executed any other transit, peering, or interconnection agreements to date. Negotiations continue with 6 additional providers for fibers in various portions of the constructed route. We have not denied any request for interconnection to the fiber routes. | N/A | TRUE
NT10BIX5570122 | 2010 | 0 | Deployment has not started, and no portion of the network is available for service yet. Therefore, there is no cost per mile indicated for this report. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | 1 Gbps | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | 100 Mbps | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps, and we anticipate that most of our customers will fall into that level of service. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | Preliminary research indicates that current broadband speed available for community anchor institutions is less than 6 Mbps, according to survey respondents that were asked to identify their ISPâ€™s advertised speed. Actual speeds measured at individual workstations can be substantially less than advertised speeds. Therefore, we conservatively anticipate the average increase in broadband speed provided to be in the range of 5 Mbps to 95 Mbps, as 10 Mbps to 100 Mbps is the level of service range that we anticipate will be offered to most community anchor institutions. | Planned services include Standard and Premium wholesale, enterprise, and e-Rate/discounted government Ethernet access. Please see the attached preliminary pricing plan draft for the FRBA network. | Network management policies are in compliance with the nondiscrimination and interconnection obligations outlined in the NOFA. When completed, the project will provide open, ubiquitous, Middle Mile access to broadband Internet services for both private entities and public institutions in the underserved areas of northern Florida. We will display all non-discrimination practices in a prominent location on our web site and we will provide notice to customers of any changes to these policies. We are fully committed to offering wholesale access to the project facilities at reasonable rates and terms. We are also committed to binding private arbitration for any disputes concerning these interconnection obligations. Our network management practices and policies will adhere to the principles contained in the FCCâ€™s Internet Policy Statement and not show favoritism to any lawful Internet applications and content over others. The FRBA network will not be a private closed network, but will instead be connected to the public Internet directly and provide open access to all Internet resources. We will offer interconnection where technically feasible without exceeding current or reasonably anticipated capacity limitations on reasonable rates and terms to be negotiated with requesting parties. | N/A. This project is a Middle Mile network that has not yet been deployed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We will not be providing access to dark fiber, as we do not have that access. | 0 | 0 | 0 | 0 | Co-location facility square footage information is yet to be determined. Contract negotiations with Level 3 have commenced, and upstream engineering and provisioning are currently still in development. Interconnection for customers (last mile providers) will be accessed through switched Internet Protocol/Ethernet multi-service access platforms (MSAPs)located at each tower/wireless network link. | We have not issued any subcontracts or subgrants. | We improved our approach to network design, utilizing shorter links, more licensed towers, and lower cost ratios to yield greater reliability, greater capacity, and greater competition from more available manufacturersâ€”all within the original overall project budget. This approach requires more time for site assessments (for existing commercial towers and in-kind vertical assets) and follow-up engineering and network design, but it yields improved efficiency and shortens the overall deployment schedule. We have asked the Grants Office to review a draft template of our master tower license agreement in order to obtain verification that the contract language in the license agreement is in compliance with grant requirements. We are also in the process of determining Davis-Bacon wage rate decisions for equipment installation laborers, and to that end we submitted an Award Action Request to the Grants Office (for our NFBA project) that included a Request for Authorization of Additional Classification and Rate (SF 1444) for proposed classification titles. We are also conducting our own research on this matter in order to move forward with the development of the Equipment Installation and Pathing Request for Proposals (RFP) in an effort to avoid any delay to the release of this RFP and to subsequent equipment installation activities. In addition, we are checking for previous/duplicate federal funding for targeted in-kind assets, per the Grants Officeâ€™s request. Discovery of previous or duplicate federal funding for in-kind assets may or may not impact planned project progress, depending on the interpretation of this particular requirement. We are seeking to utilize only a limited amount of space on any given in-kind asset to mount microwave antennas and equipment; we are not seeking to utilize any in-kind asset in its entirety. | Florida Rural Broadband Alliance, LLC | 178 | 28 | 6 | 18 | 70 | 97 |  | 124 | 272 | 11 | 804 | N/A. We are developing products and pricing with pre-deployment service level agreements. We are also developing dialogue with carriers, re-sellers, and community anchor institutions, with the expectation of signing several after pricing and service level agreements are finalized. While we have not yet signed agreements with other providers as yet, the pricing and ability to describe the value proposition is imminent, and we anticipate the signing of several agreements over the next subsequent quarters. | N/A. As noted above, we are developing products and pricing with pre-deployment service level agreements, and developing dialogue with carriers, re-sellers, and community anchor institutions, with the expectation of signing several after pricing and service level agreements are finalized. Also, the network design is committed to meeting the stringent quality of service and reliability standards set by the State of Florida for providing transport and direct internet access (as a last mile provider of last resort) to State agencies. Once deployed, the FRBA network will be qualified to serve State offices, community colleges, and their last mile network partners. | TRUE
NT10BIX5570122 | 2011 | $19,042 | Average cost per mile based on initial 230 mile build of Hardee County. | $3771.76 | This project is a Middle Mile network. However, we will work with our Local Access providers to collect and report on this data as it becomes available. | $3771.76 | This project is a Middle Mile network. The cost per subscriber are based on anchor tenant connections. | 0 | Construction will begin in 2012 and it is anticipated that available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3 | 0 | Construction will begin in 2012 and it is anticipated that available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3 | 0 | Construction will begin in 2012 and it is anticipated that available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3 | 10 Mbps | This project is a Middle Mile network. Last mile services are being provided to selective anchors. The current average speed for anchor tenants is 10 Mbps. | The FRBA network is increasing broadband speeds by a multiple of 4 to 20 times previously available services throughout the region. CAIs are moving from DSL speeds of 1 Mbps to FRBA wireless speeds of 5 to 20 Mbps. Other CAIs are upgrading to 200 Mbps which is 20 times the available capacity they were able to receive prior to FRBA providing broadband in their serving area. Preliminary research indicates that current broadband speed available for community anchor institutions is less than 6 Mbps, according to survey respondents that were asked to identify their ISPâ€™s advertised speed. Actual average anchor tenant speeds have been less than 1.5 Mbps based on T1 or DSL connectivity. Actual speeds measured at individual workstations can be substantially less than advertised speeds. Current anchor connection speeds being provided by FRBA in Hardee county average 10 Mbps or better. Top speeds currently being provided peak at 20 Mbps. Therefore, we conservatively anticipate the average increase in broadband speed provided to be in the range of 10 Mbps with the capability of reaching 100 Mbps on average for high speed connections. | FRBA is a middle provider and as such will not be offering a broad based retail service except to anchor institutions and as carrier of last resort. However, in these scenarios, FRBA plans to offer wireless Ethernet and Internet based services. These services will be offered in bandwidth pricing tiers to accommodate the needs of the region. These services will be offered in multiples of 2, 5, 10, 15, 20, and up Mbps. Planned services include Standard and Premium wholesale, enterprise, and e-Rate/discounted government Ethernet access. Please see the attached preliminary pricing plan draft for the FRBA network. | Network management policies are in compliance with the nondiscrimination and interconnection obligations outlined in the NOFA. When completed, the project will provide open, ubiquitous, Middle Mile access to broadband Internet services for both private entities and public institutions in the underserved areas of northern and central Florida. FRBAs network management policies are in effect and active with the initial deployment of Hardee County. These policies will continue to be developed and scaled to meet the needs of the region as the FRBA network continuous to be deployed in other counties. We will display all non-discrimination practices in a prominent location on our web site and we will provide notice to customers of any changes to these policies. We are fully committed to offering wholesale access to the project facilities at reasonable rates and terms. We are also committed to binding private arbitration for any disputes concerning these interconnection obligations. Our network management practices and policies will adhere to the principles contained in the FCCâ€™s Internet Policy Statement and not show favoritism to any lawful Internet applications and content over others. The FRBA network will not be a private closed network, but will instead be connected to the public Internet directly and provide open access to all Internet resources. We will offer interconnection where technically feasible without exceeding current or reasonably anticipated capacity limi | No subscriber has dropped service during the early testing and pilot phase of the deployment in Hardee County. Based on the small sample size of 26 subscribers the churn rate is 0%. The FRBA network is still relatively new and an effective churn rate cannot be calculated at this time. | 1216 | 1216 | 0 | 0 | 0 | 0 | 0 | N/A | 144 | 144 | 0 | 0 | FRBA has negotiated space with Level 3 and Rapid Systems and has a collocated cabinet at each of the tower location sites. FRBA provides wireless network access so subscriber and wholesale service connections can be made at any one of the 4 fiber collocation data centers or at the tower sites through either wireless or physical Ethernet service connections to the cabinet. This enables FRBA to provide wholesale providers and anchor tenants a number of geographic options. Interconnection for customers (last mile providers) will be accessed through switched IP/Ethernet multi-service access platforms located at each tower/wireless network site. | FRBA has not issued any subcontracts or subgrant SDB firms. | FRBA has improved its approach to network design, utilizing shorter links, more licensed towers, and lower cost ratios to yield greater reliability and greater â€” all within the original project budget. This approach enabled FRBA to redesign its network to meet commercial carrier class service objectives and create more cost effective opportunities for wholesale services providers. FRBA in collaboration with its partners and vendors has developed and tested the next generation high capacity wireless backbone designs capable of multi-gigabit speeds and network access options from 10 Mbps to 1 Gbps. In addition FRBA has created and leveraged Level 3s BTOP grant investment that was essential to providing fiber access through the ILAs in rural central and northern Florida. This has proved to be essential to managing high capacity links and services to FRBAs wireless core. With the help of Rapid Systems, FRBA has developed an ISO standardized documentation framework for the project and plans to continue to develop ISO best practices as part of its operational deployment. These standards are being incorporated into FRBAs Operational Support and Back Office Systems to streamline operational and customer service management processes. This high degree of automation will help reduce the operational burden and cost that FRBA will incur as anchor tenants and wholesale partners begin to fully utilize the network. Some of FRBAs ISO documents include; â€¢ Quality Policy Manual â€¢ Document Control Manual/Record Retention Policy â€¢ Warehouse Policy/Procedures â€¢ Finance Policy/Procedures â€¢ Inventory Control/Asset Tagging â€¢ Dispatch/RMA Policies/Procedures â€¢ Interoperability and Benchmark Testing â€¢ Security and Disaster Plan/Hurrican/Fire â€¢ Fabrication and Work Practices FRBA also attended the BTOP Best Practices workshop and identified a number of awardees that have already developed best practices. Some of these best practices have contributed to the redesign and development of internal processes related to procurement, fraud prevention, and the development of RFPs for construction. In addition FRBA has been evaluating how other programs are managing compliance.. | Florida Rural Broadband Alliance, LLC | 178 | 28 | 6 | 18 | 70 | 97 |  | 124 | 272 | 11 | 804 | FRBA has interconnection agreements with four wholesale providers. • Rapid Systems has agreement with the Hardee County Broadband Project. • Rapid Systems has a wholesale agreement with Daystar for Last Mile Services within the FRBA project • Rapid Systems has a wholesale / Last Mile agreement with Knology for Voice over Internet Protocol services within the FRBA project and is currently deploying Hosted and Residential Voice over Internet Protocol • Rapid Systems has a wholesale/Last Mile agreements with TampaBayDSL No requests were denied in 2011. | FRBA has established a IRU and IP transit agreement with Level 3 for fiber and internet services. These services are being provided to FRBA anchor tenants and wholesale service providers using FRBAs network services. | TRUE
NT10BIX5570122 | 2012 | $11,776 | FRBA's average cost per new mile is calculated by dividing total capital costs for network construction (less certain equipment categories) by 1,201 total route miles in the project to arrive at an average cost per mile of $11,776. | 0 | FRBA is a middle-mile network only and does not provide any direct last-mile residential access. Last-mile providers will provide such services utilizing FRBAâ€™s middle-mile capacity for backhaul to reach markets within the service area. | 0 | FRBA is a middle-mile network only and subscriber connections will only be made to community anchors throughout the region (as well as last-mile providers). Costs associated with such infrastructure are not included in this section. | 200Mbps | FRBA is a middle-mile network capable of providing wholesale capacity in increments of 200Mbps. Gigabit speeds are available on the FRBA network on an individual case basis. | 200Mbps | FRBA is a middle-mile network but will provide last-mile services to community anchors. Anchors will be able to receive a maximum of 200Mbps, but additional capacity may be provisioned to increase that capacity to higher rates. | 200Mbps | FRBAâ€™s middle-mile wholesale access will provide transport and commodity Internet services between speeds of 5Mbps and 200Mbps. We anticipate the average middle-mile transport circuit at 20Mbps, based on the requirements of CAIs in the region and last-mile providers. Last-mile providers will require larger transport circuits for backhaul into local service areas. In addition, last-mile providers will require direct type 2 services to reach customers in these areas. | 10Mbps | Broadband connections to CAIs will range between 5Mbps and 150Mbps, with the average in the region being 10Mbps. These connections will provide broadband services to community anchors requiring both Internet and transport services in FRBAâ€™s service area. Currently, many anchors utilize DSL, T1 or T1xN services and FRBAâ€™s services will provide a significant increase in capacity over legacy copper infrastructure. | The FRBA network will provide significant increases in broadband speeds to community anchors throughout the region. Through our market research, we have found that many CAIs in the service area receive DSL, Cable and NxT1 local access services, in most cases limited to 6Mbps or less. FRBAâ€™s network will provide bandwidth from 5Mbps to 200Mbps to CAIs, utilizing both shared and dedicated products. On average, and through our outreach programs, we have recognized that many CAIs will upgrade existing services by 3-5 times the amount of bandwidth they currently receive. On average, a 6Mbp customer will double or triple their bandwidth on the FRBA network, for competitive rates using FRBAâ€™s redundant middle-mile infrastructure. In addition, CAIs will be able to interconnect their facilities utilizing FRBAâ€™s transport services, allowing them to provision site-to-site connectivity, previously only possible through high-cost, legacy private line circuits and unreliable Internet-based VPNs. | FRBA will offer retail services to CAIs throughout the region. These services include point-to-point/multi-point transport and Internet services to community anchors as identified in this APR and its attachments. FRBA has identified many CAIs in its region that require a combination of transport and Internet services. Transport services will provide site-to-site connectivity for many of the local government, public safety and healthcare customers in the region, enabling them to upgrade or replace their costly copper-based WAN services with higher speed wireless WAN services. FRBA will also participate in the E-Rate program for Schools and Libraries as administered by USAC and will be an eligible E-Rate provider for these organizations. For these critical education-based CAIs, FRBAâ€™s network will provide high-performance Internet and site-to-site transport interconnections between schools, libraries and related facilities, helping ensure students have access to critical online resources. Pricing for services is also included in the attached rate sheet for dedicated transport and Internet capacity (Please see FRBA Rate Sheet 1.0.pdf) | FRBAâ€™s network management practices and policies will adhere to the principles contained in the FCCâ€™s Internet Policy Statement and not show favoritism to any lawful Internet applications and content over others. The FRBA network will not be a private closed network, but will instead be connected to the public Internet directly and provide open access to all Internet resources. FRBA will offer at least two classes of services to its customers depending on their particular needs and budgetary constraints. FRBA will offer both dedicated and shared access to customers. Dedicated access will provide committed rate services for CAIs and last-mile providers that require guaranteed bandwidth. Shared services will provide best-effort services to customers that donâ€™t require stringent performance requirements, geared primarily for smaller CAIs, branch offices and small businesses. Pricing for shared services will be significantly lower than dedicated services as a result. | The FRBA network is currently under construction and does not have any subscribers | 1216 | 1216 | 1216 | 0 | 0 | 0 | 0 | FRBA does not wholesale dark fiber. | 300 | 300 | 0 | 0 | FRBA has negotiated and purchased colocation space in two Level3 data centers in Orlando, FL and Tallahassee, FL. Both data centers have neutral access to significant regional and national carriers, through which FRBA will develop interconnection agreements and NNIs. Data centers have available cage and cabinet space to provide colocation services to potential subtenants who require local presence for peering and interconnection. FRBA will maintain direct cross-connects to other carriers in these facilities. Additionally, each of FRBAâ€™s tower sites is equipped with colocation facilities for last-mile providers, local exchange carriers and other entities. Interconnection for customers (last mile providers) will be accessed through switched IP/Ethernet multi-service access platforms located at each tower/wireless network site. These sites will enable local last-mile networks interconnect with FRBA's middle-mile backhaul to deliver new bandwidth to local service areas. In doing so, FRBA's network will offer a significant amount of points of interconnection into underserved service areas that lack adequate backhaul. Many regions maintain legacy T1 and DS3 backhaul and few offer bandwidth beyond those transport technologies. FRBA will deliver new wireless backhaul to these service areas as an upgrade to existing legacy copper backhaul networks. | FRBA has not issued any subcontracts or subgrants to SDB firms. | No Comments at this time | Florida Rural Broadband Alliance, LLC | 178 | 28 | 6 | 18 | 70 | 97 |  | 124 | 272 | 11 | 804 | FRBA has not signed any interconnection agreements during the period in question. FRBA is actively identifying interconnection partners and will be establishing NNIs for wholesale and type 2 services in the region. These activities will coincide with completion and activation of the network to ensure that NNIs and interconnections can be made immediately, allowing the network to begin providing services as soon as it is commissioned. FRBA has begun this process early to ensure that we budget a 6-month window for negotiation of interconnection agreements, required network testing and certification and regulatory filings that may be required. | FRBA currently maintains IRU capacity with Level3 for backhaul connectivity between the wireless middle-mile core network and its two data centers in Tallahassee, FL and Orlando, FL. As the network nears completion, FRBA will identify commodity Internet, peering and interconnection partners to be integrated into the network. FRBA seeks tier 1 IP providers to ensure the highest quality Internet services available to its network. FRBA will also identify value-based Internet providers that can provide diversity to FRBA's network, blended IP transit and maintain competitive overall costs for FRBA's IP transit. | TRUE