NT10BIX5570084 | 2012 | Q1 | Q1 - 2012 | During this quarter, Iowa Health System (IHS)/Broadband, Inc. (BBI) released 2 Request For Proposals (RFP) to procure installation kits/materials and Routers, received proposals from bidders and selected the vendor upon board approval. IHS committed its match for the purchase of the routers. IHS obtained its FONSI in February and proceeded with finalizing the permits for the hut locations. By end of this quarter we received 3 permits (Ames, Ottumwa, and Waterloo), 2 permits (Mason City and Cedar Rapids) pending a licensed contractor, 2 permits (Iowa City and Marshalltown) pending payments submitted, and 2 permits (Davenport and Clinton) pending executed land leasing agreements. Additionally, the Engineering Start Up Support Services for the middle mile extensions continued to work review proposed middle mile extensions. One customer agreement was executed for transport services and connection was through a collocation, so no further Section 106 review was required under the Programmatic Agreement for the 1st Middle Mile Extension Customer. IHS continues to engage the customers on its prospect list, moving them into the pipeline for negotiations. The negotiations for the IRU are underway once the IHS received its FONSI, however was not finalized this quarter. Outside Plant (OSP) and Inside Plant (ISP) design for the 9 hut locations are in process and it has been identified that four hut laterals will be outside the proposed route that our EA covered for Iowa City, Waterloo, Marshalltown, and Davenport. During this quarter, IHS is gathering the required mapping and documentation to submit a route modification to NTIA. IHS/BBI submitted a budget modification to reallocate the unallowable purchase of spare equipment and first year support services. These line items were reallocated to include the anticipated legal expenses and additional Environmental Assessment work that may need to be completed under the Programmatic Agreement for the Middle Mile Extensions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | This variance from the baseline is due to the delay of receiving a FONSI. | IHS/BBI is currently finalizing the IRU negotiations and anticipates finalizing altogether during Q2 2012 (Apr-Jun) | This variance from the baseline is due to the delay in receiving a FONSI. | No variance from baseline report. | This variance from the baseline is due to the delay in receiving a FONSI. | No variance from the baseline report. | No variance from the baseline report. | This variance from the baseline is due to the delay in receiving a FONSI. | 1 | 5 | 20 | Cedar Falls Utilities | See attachment. | N/A | 0 | 0 | 0 | 0 | Cedar Falls Utilities did not receive new access this qtr. IHS/BBI anticipate that Cedar Falls Utilities will receive new access starting in Q2 2012. | No variance from baseline report. | No variance from baseline report. | No variance from baseline report. | 0 | 0 | 0 | 0 | No variance from baseline report. | No variance from baseline report. | No variance from baseline report. | No variance from baseline report. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings are anticipates during this qtr. | FALSE | N/A | IHS/BBI anticipates installing the 9 hut locations pending fiber lateral installation upon review of the reroute modification. IHS/BBI anticipate staging the equipment in the huts, finalizing the IRU with Long Lines, and executing customer agreements with at least 3 more customers. During the next quarter, there will not be any new subscribers served because the construction activities for the 9 huts and laterals will not begin until Q2 2012 (Apr-Jun)and the lateral construction is dependent on what the next steps will be for the reroute modifications. IHS/BBI does not anticipate providing any upgraded access to CAIs by end of next quarter, however, IHS/BBI still anticipates that 162 CAI subscribers will be connected and receiving improved access starting in Q4 2012 (Oct-Dec). IHS anticipates that it will exceed the 67% project completion by the end of Q2 2012 (Apr-Jun) and will be on track for 100% project completion by end of Q2 2013 (Apr-Jun). IHS/BBI anticipates that it will deploy 16 new network miles during Q3 2012 (Jul-Sept) and 0 new network miles during Q2 2012 (Apr-Jun). IHS/BBI anticipates that it will have 4 signed agreements by the end of Q2 (Apr-Jun). | Iowa Health System | IHS/BBI faces the challenge of finalizing the Middle Mile Extension routes that are dependent on finalizing the interconnection agreements with Last Mile Providers. | IHS/BBI will continue to face the challenge of reroute modifications that will need to be finalized prior to construction activities for the middle mile extensions. | TRUE
NT10BIX5570084 | 2012 | Q2 | Q2 - 2012 | During this quarter, Iowa Health System (IHS)/Broadband, Inc. (BBI) released 3 Requests For Proposals (RFP). One RFP for site prep construction, one RFP for lateral construction activities, and one RFP for the Ethernet Switches. Delivery coordination is underway for the generators and huts to be placed at each of the nine locations. IHS received proposals from bidders and selected vendors for the site and lateral construction. The Long Lines IRU was finalized and executed which will close the western ring. Outside Plant (OSP) and Inside Plant (ISP) design for the 9 hut locations has been completed and most of the permits have been obtained. IHS will complete all permitting for the 9 hut locations in the beginning of Q3 2012. Since OSP engineering has been completed it was identified that four hut laterals will be outside the proposed route that our EA covered for Iowa City, Waterloo, Marshalltown, and Davenport and a pole replacement will be necessary in the City of Ottumwa. The EHP Pre-Screening Checklist and supporting documentation for the five route modifications was submitted to NTIA for approval before submitting to the Iowa State Historic Preservation Office for final concurrence. All land lease agreements have been executed. During this quarter, BBI executed four capacity agreements totaling five capacity agreements with last mile providers to date. IHS continues to engage the customers on its prospect list, moving them into the sales pipeline for negotiations. | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | This variance from the baseline is due to the route modifications for the hut laterals due to unexpected circumstances. IHS anticipates completing the hut laterals by end of Q3 2012. | On target | This variance from the baseline of 357.5 miles is due to the route modifications for the hut laterals. IHS anticipates completing the hut laterals by end of Q3 2012 and will finalize the upgraded 357.5 miles in Q4 2013 once equipment is deployed and activated. | NA | This variance from the baseline is due to the route modifications for the hut laterals due to unexpected circumstances. IHS anticipates completing the hut laterals by end of Q3 2012. | NA | NA | This variance of 30 interconnection points from the baseline is due to the route modifications for the hut laterals. IHS anticipates completing the hut laterals by end of Q3 2012 and will upgrade 30 interconnection points by end of Q3 2012 | 5 | 3 | 20 | Cedar Falls Utilities US Secure Hosting Center Bellevue Municipal Utilities Mahaska Communications Group Osage Municipal Utilities | See Attachment | N/A | 1 | 0 | 0 | 0 | Variance from baseline due to the longer than expected negotiation time frames and dependency on IHS' ring bring ups that have been pushed back due to EA modifications. Cedar Falls Utilities started recieving new access this quarter and there were not any construction activities required to build fiber | No variance from baseline report. | No variance from baseline report. | No variance from baseline report. | 0 | 0 | 0 | 0 | Variance from baseline due to the longer than expected negotiation time frames and dependency on IHS' ring bring ups that have been pushed back due to EA modifications. | No variance from baseline report. | No variance from baseline report. | No variance from baseline report. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | No special offering are anticipated this qtr. | FALSE | NA | IHS anticipates completing the 8 of the 9 hut installations by the 1st week of August in Q3 2012 if the route modifications are approved. IHS anticipates obtaining approval for 3 middle mile extension routes and will begin to move forward with construction activities to ensure 3 middle mile extensions are completed by end of Q4 2012. IHS does not anticipate any new subscribers served until Q4 2012 due to the time frame it has taken to obtain EA approvals. IHS has exceeded the 67% project completion by the end of Q2 2012 and will be on track for 100% project completion by end of Q2 2013. IHS anticipates that it will deploy 16 new network miles during Q3 2012. IHS anticipates that it will have 3 more signed agreements by the end of Q3 2012. | Iowa Health System | IHS faces the challenges of the route modifications and the turnaround time for approval due to pole replacements and new city ordinances. IHS also faces the challenge of finalizing the Middle Mile Extension routes that are dependent on finalizing capacity agreements with Last Mile Providers. | IHS continues to face the challenge of reroute modifications that will need to be finalized prior to construction activities for the middle mile extensions. | TRUE
NT10BIX5570084 | 2012 | Q3 | Q3 - 2012 | During this quarter, Iowa Health System (IHS)/Broadband, Inc. (BBI) IHS received approval for the five route modifications that were submitted to NTIA for approval and construction crews were dispatched to the 9 locations to start the fiber lateral builds. IHS completed all permitting for the 9 hut locations in the beginning of this quarter. Fiber lateral builds were completed for Ames, Clinton, Davenport, Iowa City, Marshalltown, Mason City, Ottumwa, and Waterloo. The Cedar Rapids fiber lateral construction on part of the route was started at the end of this quarter and is projected to be completed by beginning of Q4 2012. The main ring will have 14 of the 21 sites ready for equipment deployment beginning Q4 2012 and all sites completed by end of Q4 2012 to fully activate the main ring this year. IHS/BBI submitted the 2nd route modification package (middle mile fiber extension builds to three last mile providers) to NTIA beginning of Q3 2012 and has been working with NTIA to finalize route approval before sending the Iowa SHPO for concurrence. Final route approval is projected for beginning of Q4 2012 to start construction activities. During this quarter, BBI executed five capacity agreements totaling twelve capacity agreements with last mile providers to date. IHS continues to engage the customers on its prospect list, moving them into the sales pipeline for negotiations. | 3 | 99 | 378 | 0 | 3 | 0 | 0 | 30 | This variance from the baseline is due to the route modifications for the hut laterals due to unexpected circumstances. IHS completed 8 hut laterals and anticipates finalizing the last in Q4 2012. 38.54 new network miles will be deployed by end of Q4 2012. | On Target | IHS anticipates completing the hut laterals by end of Q3 2012 and will upgrade 1168 miles in Q4 2012 once equipment is deployed and activated. Total 3088 existing network miles will be upgraded by end of Q2 2013. | N/A | IHS anticipates constructing 38.54 new miles be end of Q4 2012 | N/A | N/A | This variance of 30 interconnection points from the baseline is due to the route modifications for the hut laterals. IHS anticipates completing the hut laterals by end of Q3 2012 and will upgrade 30 interconnection points by end of Q3 2012 | 12 | 5 | 20 | Cedar Falls Utilities US Secure Hosting Center Bellevue Municipal Utilities Mahaska Communications Group Osage Municipal Utilities FiberComm InfoBunker Riverside Clinic Sunnybrook Clinic VS Enterprises Laurens Municipal TCA | See Attachment | N/A | 1 | 0 | 0 | 0 | Variance from baseline due to the longer than expected negotiation time frames and dependency on IHS' ring bring ups that have been pushed back due to EA modifications. Cedar Falls Utilities started recieving new access this quarter and there were not any construction activities required to build fiber | No variance from baseline report. | No variance from baseline report. | No variance from baseline report. | 0 | 0 | 0 | 0 | Variance from baseline due to the longer than expected negotiation time frames and dependency on IHS' ring bring ups that have been pushed back due to EA modifications. | No variance from baseline report. | No variance from baseline report. | No variance from baseline report. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offering are anticipated this qtr. | FALSE | N/A | IHS anticipates completing 9th lateral installation by in the beginning of Q4 2012 and completing 50% of the 3 Middle Mile Fiber Extension builds if the route modifications are approved at the beginning of Q4 2012. IHS anticipates obtaining approval for 3 middle mile extension routes and will begin to move forward with construction activities to ensure 3 middle mile extensions are completed by end of Q4 2012. IHS does not anticipate any new subscribers served until Q1 2013 due to the time frame it has taken to obtain EA approvals. IHS will have 80% of the overall project completed by the end of Q4 2012 and will be on track for 100% project completion by end of Q2 2013. IHS anticipates that it will deploy 38.54 new network miles during Q4 2012. IHS anticipates that it will have 4 more signed agreements by the end of Q4 2012. IHS anticipates 162 CAIs by end of Q1 2013 with the total 190 CAIs by end of Q2 2013 receiving improved services. | Iowa Health System | IHS faces the challenges of the route modifications and the turnaround time for approval due to pole replacements and new city ordinances. IHS also faces the challenge of finalizing the Middle Mile Extension routes that are dependent on finalizing capacity agreements with Last Mile Providers. | IHS continues to face the challenge of reroute modifications that will need to be finalized prior to construction activities for the middle mile extensions. | TRUE
NT10BIX5570084 | 2012 | Q4 | Q4 - 2012 | Phase 1 - All 9 deployed huts and fiber laterals to existing network are totally complete and operational. Phase 2 - Iowa Health System (IHS)/Broadband Inc. (BBI) deployed 21 of the 21 DWDM sites on the main ring and they became operational. IHS is preparing to deploy equipment on the North, South, West, and long haul routes to remain on track for Q1 2013 and final completion by end of Q2 2013. Phase 3 - IHS/BBI executed four capacity agreements totaling 16 capacity agreements with last mile providers to date. IHS has met its customer target of 16 and will continue to move these projects along to completion to meet the end of our project requirements. IHS/BBI also received approval for 3 middle mile extensions that were submitted to NTIA for approval and construction crews were deployed to the 3 locations to start the fiber extension builds. IHS/BBI is preparing to submit a 3rd route modification package to NTIA beginning of Q1 2013 for 4 additional routes. IHS/BBI will attend the Iowa Association Municipal Utilities conference in Q2 2013 and publish community highlights as we start connecting CAIs in Q1 2013 and last mile providers in rural areas providing lower cost services. | 38 | 99 | 1168 | 0 | 38 | 0 | 0 | 30 | This variance from the baseline is due to the route modifications for the hut laterals due to unexpected circumstances. IHS completed 9 hut laterals in Q4 2012 and deployed 35.54 new network miles altogether by end of Q4 2012. IHS anticipates completing 63.27 miles total by end of Q1 2013 and 112 by end of Q2 2013. | On target | IHS upgraded the network miles on the main ring and is on schedule to upgrade a total of 3088 existing network miles by end of Q2 2013 | N/A | IHS anticipates constructing 63.27 miles by end of Q1 2013 and the remaining miles by end of Q2 2013 once the routes are approved no later than beginning of Q2 2013 (April) to allow enough construction time. | N/A | N/A | The variance from the baseline was due to the route modifications and completing the ring bring ups. However, IHS is on schedule to complete the upgrade of all interconnection points the begining of Q2 2013. | 16 | 4 | 20 | Cedar Falls Utilities US Secure Hosting Center Bellevue Municipal Utilities Mahaska Communications Group Osage Municipal Utilities FiberComm InfoBunker Riverside Clinic Siouxland PACE Clinic Harlan Municipal Utilities VS Enterprises City of Denison Professional Computer Services (PCS) City of Maquoketa City of Charles City City of Algona | See attachment | N/A | 16 | 0 | 0 | 0 | Variance from baseline due to the longer than expected negotiation time frames and dependency on IHS' ring bring ups. Cedar Falls Utilities and Mahaska Communications have started receiving new access this quarter and there were not any construction activities required to build fiber. The remaining providers are signed and planned for connection in Q1 and Q2 2013 to start receiving new access. | No variance from baseline report | No variance from baseline report | No variance from baseline report | 0 | 0 | 0 | 0 | Variance from baseline report due to the dependency on IHS' ring bring ups. Projected to have all CAIs served in Q2 2013. | No variance from baseline report | No variance from baseline report | No variance from baseline report | 0 | 0 | 0 | 0 | 0 | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | 0 | 0 | 0 | 0 | 0 | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | No special offerings during Q4 2012. | FALSE | N/A | Phase 2 - Iowa Health System (IHS)/Broadband Inc. (BBI) will deploy equipment on the North, South, West, and long haul routes to remain on track for Q1 2013 and final completion by end of Q2 2013. Phase 3 - IHS/BBI projects to finalize middle mile fiber construction by end of Q1 2013 and receive approval by end of Q1 2013 to submit to the Iowa SHPO. Upon receiving approval from NTIA, IHS/BBI projects to start construction on the 4 fiber lateral builds starting Q2 2013. IHS/BBI will attend the Iowa Association Municipal Utilities conference in Q2 2013 and publish community highlights as we start connecting CAIs in Q1 2013 and last mile providers in rural areas providing lower cost services. IHS/BBI anticipates completing the 3 middle mile fiber extension builds beginning of Q2 2013. IHS anticipates four additional last mile providers served in Q1 2013 totaling 6 last mile providers and 10 add'l last mile providers by end of Q2 2013 totaling 16 total last mile providers. IHS/BBI anticipates completing 63.27 miles of fiber construction by end of Q1 2013, 16 middle mile providers, and starting the migration of 85 CAIs onto the newly upgraded fiber backbone by end of Q1 2013. | Iowa Health System | IHS faces the challenges resulting from route changes that will need to be submitted through the EA process/requirements. IHS has alleviated the challenge of finalizing the Middle Mile Extension routes since we have met our 16 customer signed milestone by end of Q4 2012. | The challenge remains obtaining NTIA approvals for EA route modifications due to the time it takes to sign customers to complete Phase 3 of our project, customer implementations. | TRUE
NT10BIX5570084 | 2013 | Q1 | Q1 - 2013 | Phase 1 - All 9 huts and fiber laterals to existing network are deployed and operational. Phase 2 - Iowa Health System (IHS)/Broadband Inc. (BBI) deployed 21 of the 21 DWDM sites on the main ring and they became operational. During this quarter, the North, South, and West rings are operational. The western long haul route remains on track to complete by end of Q2 2013. Phase 3 - IHS/BBI executed four capacity agreements totaling 16 capacity agreements with last mile providers to date. IHS has met its customer target of 16 and will continue to move these projects along to completion to meet the end of our project requirements. IHS/BBI also received approval for 3 middle mile extensions that were submitted to NTIA for approval and construction crews were deployed to the 3 locations to start the fiber extension builds. IHS/BBI submitted the 3rd route modification package to NTIA beginning of Q1 2013 to construct 3 additional routes. During this quarter, we received approval from NTIA to proceed forward with construction under our Programmatic Agreement. There will be one last route modification submittal in Q2 2013 to connect 2 customers that were signed at the end of Q1 to complete our target of 16 customers. In addition, due to weather IHS/BBI has been delayed approx. 4 months from completing any construction activities. At the end of Q1 2013, construction crews were still unable to start boring/burying fiber. This activity was projected to start back up in Q2 2013 but would delay the completion of the construction projects to July/August 2013 time frame. IHS/BBI will attend the Iowa Association Municipal Utilities conference in Q2 2013 and publish community highlights as we start connecting CAIs in Q1 2013 and last mile providers in rural areas providing lower cost services. | 38 | 89 | 1916 | 0 | 38 | 0 | 0 | 59 | This variance from the baseline is due to the route modifications for the hut laterals due to unexpected circumstances. IHS completed 9 hut laterals in Q4 2012 and deployed 35.54 new network miles altogether by end of Q4 2012. During the winter months, no additional network miles were deployed as a result of severe winter weather. IHS anticipates completing 63.27 miles total by end of Q2 2013 and 112 by end of Q3 2013. | Miles leased was less than originally planned due to a better leased route option. Differentiation from last report due to incorrect reporting of miles leased. | IHS upgraded the network miles on the main ring and is on schedule to upgrade a total of 3088 existing network miles by end of Q2 2013. | N/A | IHS anticipated constructing 63.27 miles by end of Q2 2013 and the remaining miles by end of Q3 2013. Construction activities were stopped due to weather through Q1 2013 and is not expected to start back up until middle of Q2 2013. | N/A | N/A | The variance from the baseline was due to the route modifications and completing the ring bring ups. The remaining interconnection points are on the western long haul route that are planned for completion by end of Q2 2013. | 16 | 6 | 20 | Cedar Falls Utilities US Secure Hosting Center Bellevue Municipal Utilities Mahaska Communications Group Osage Municipal Utilities FiberComm InfoBunker Riverside Clinic Siouxland PACE Clinic Harlan Municipal Utilities VS Enterprises City of Denison Professional Computer Services (PCS) City of Maquoketa City of Charles City Enseva | See Attachment. | N/A | 16 | 0 | 0 | 16 | Variance from baseline due to the longer than expected negotiation time frames and dependency on IHS' ring bring ups. The weather has remained a challenge as we were unable to start construction up during March and we have had heavy rain fall as well. The remaining providers are signed and planned for connection in Q2 and Q3 2013. Construction activities were delayed throughout Q1 2013 and will not start back up until middle of Q2 2013. This will cause the completion of customer connections to be pushed into Q3 2013. | No variance from baseline report | No variance from baseline report | 50Megs = 3 subscribers 100Megs=7 subscribers 500Megs=1 subscriber 1Gig=4 subscribers 2Gig=1 subscriber | 14 | 0 | 14 | 14 | Variance from baseline report due to the dependency on IHS' ring bring ups that were pushed out. | No variance from baseline report | Variance from baseline report due to the dependency on IHS' ring bring ups that were pushed out. | 10Megs=14 subscribers | 0 | 0 | 0 | 0 | 0 | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | 0 | 0 | 0 | 0 | 0 | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | No special offerings during Q1 2013. | FALSE | N/A | Phase 3 - IHS/BBI projects to start up the middle mile fiber construction in Q2 2013 for the 1st group of 3 routes. The construction activites have been on hold due to weather. IHS/BBI will plan on requesting an extension due to weather constraints and the inability to start the fiber construction during Q1. During this quarter, the migrations will continue and the remaining customer connections will be started. Completion is not projected until Q 3 which will require IHS/BBI to request this extension through end of August 2013. During Q2 2013, IHS/BBI plans to plans to deploy 10 miles dependent upon weather, provide upgraded capacity to 80 additional CAIs, and we'll have an add'l 3 last mile provider agreements in place. IHS/BBI plans to upgrade 1,172 miles by end of Q2 2013 completing 3088 miles of upgraded network. IHS/BBI plans will increase leased miles from 89 to 98 (9 miles of lease to connect Siouxland PACE and Riverside Clinics) and all miles leased will be finalized by end of Q2 2013. | Iowa Health System | IHS faces the challenges of weather due to excessive snow coverage and rain fall during the winter and early spring season. In return, the weather has caused construction activities to cease. | Weather would be seen as a variable that could impact/hinder progress to complete the customer fiber builds. | TRUE
NT10BIX5570084 | 2013 | Q2 | Q2 - 2013 | Phase 1 - All 9 huts and fiber laterals to existing network are deployed and operational. Phase 2 - Iowa Health System (IHS)/Broadband Inc. (BBI) deployed 21 of the 21 sites on the main ring and they became operational. Q1 2013, the North, South, and West rings were operational. During this quarter, 2Q 2013, there were a total of 69 community anchor institutions (CAI) receiving upgraded services by migrating onto the network. The western long haul route remains on track to complete by end of Q3 2013. Phase 3 - IHS/BBI executed four capacity agreements totaling 16 capacity agreements with last mile providers to date. IHS has met its customer target of 16 and will continue to move these projects along to completion to meet the end of our project requirements. IHS/ BBI also received approval for 3 middle mile extensions during Q1 2013 in which construction is fully underway with planned completion during Q3 2013. There was one last route modification submitted in Q2 2013 to connect 2 customers that were signed at the end of Q1 to complete our target of 16 customers. IHS/BBI received approval from NTIA to proceed with the 2 customers signed during Q2 2013. In addition, due to weather IHS/BBI has been delayed approx. 4 months from completing any construction activities. At the end of Q1 2013, construction crews were still unable to start boring/burying fiber. This activities started back up in Q2 2013 but will delay the completion of the construction projects to July/August 2013 time frame. IHS/BBI attended the Iowa Association Municipal Utilities conference in Q2 2013 and publish community highlights as we start connecting CAIs in Q1 2013 and last mile providers in rural areas providing lower cost services. | 63 | 98 | 3088 | 0 | 63 | 0 | 0 | 59 | This variance from the baseline is due to the route modifications for the hut laterals due to unexpected circumstances. IHS completed 9 hut laterals in Q4 2012 and deployed 35.54 new network miles altogether by end of Q4 2012. During the winter months, no additional network miles were deployed as a result of severe winter weather. IHS anticipates completing remaining miles of 112 by end of Q3 2013. | Miles leased was less than originally planned due to a better leased route option. Differentiation from last report due to incorrect reporting of miles leased and the addition of 2 customers. | Complete | N/A | Construction activities were stopped due to weather through Q1 2013 and activities started back up in Q2 2013. IHS anticipates completing remaining miles of 112 by end of Q3 2013. | N/A | N/A | The variance from the baseline was due to the route modifications and completing the ring bring ups. The remaining interconnection points are on the western long haul route that are planned for completion by end of Q2 2013. | 16 | 9 | 20 | Cedar Falls Utilities US Secure Hosting Center Bellevue Municipal Utilities Mahaska Communications Group Osage Municipal Utilities FiberComm InfoBunker Riverside Clinic Siouxland PACE Clinic Harlan Municipal Utilities VS Enterprises City of Denison Professional Computer Services (PCS) City of Maquoketa City of Charles City Enseva | See Attachment. | N/A | 16 | 0 | 0 | 5 | Variance from baseline due to the longer than expected negotiation time frames and dependency on IHS' ring bring ups. The weather remained a challenge as we were unable to start construction up during March and we have had heavy rain fall as well. The remaining providers were signed and planned for connection in Q2 and Q3 2013. Construction activities were delayed throughout Q1 2013 and started back up during the middle of Q2 2013. This has caused the completion of customer connections to be pushed into Q3 2013. | No variance from baseline report | No variance from baseline report | 50Megs = 3 subscribers 100Megs=7 subscribers 500Megs=1 subscriber 1Gig=4 subscribers 2Gig=1 subscriber | 78 | 0 | 78 | 1 | Variance from baseline report due to the dependency on IHS' ring bring ups that were pushed out. 14 CAIs migrated Q1 2013 and 64 CAIs migrated Q2 2013. | No variance from baseline report | Variance from baseline report due to the dependency on IHS' ring bring ups that were pushed out. | 100Megs=78 subscribers | 0 | 0 | 0 | 0 | 0 | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | 0 | 0 | 0 | 0 | 0 | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | No special offerings during Q2 2013. | FALSE | N/A | Phase 3 - IHS/BBI construction projects started up during the middle of Q2 2013 with the 1st group of 3 routes. The construction activities were on hold due to weather. During this quarter, the migrations will continue and the remaining customer connections will be completed. Completion is now on track for Q3 2013. IHS/BBI upgraded 1,172 miles by end of Q2 2013 completing 3088 miles of upgraded network. IHS/BBI increased leased miles from 89 to 98 (9 miles of lease to connect Siouxland PACE and Riverside Clinics) and all miles leased were finalized by end of Q2 2013. During Q3 2013, IHS/BBI plans to complete the migration of the 181 CAIs during, 112 new network miles, 16 wholesale agreements, 89 leased miles, and 3088 miles of upgraded network. BNc sales team has met with city leadership around Iowa with press releases scheduled for release in Q3 2013 demonstrating our achieved success in providing 16 CAIs with new access as a result of the BTOP. | Iowa Health System | IHS faces the challenges of weather due to excessive snow coverage and rain fall during the winter and early spring season. In return, the weather has caused construction activities to cease. | Weather would be seen as a variable that could impact/hinder progress to complete the customer fiber builds. | TRUE
NT10BIX5570084 | 2013 | Q3 | Q3 - 2013 | Phase 1 - All 9 huts and fiber laterals to existing network are deployed and operational. Phase 2 - Iowa Health System (IHS)/Broadband Inc. (BBI) deployed 21 of the 21 sites on the main ring and they became operational. Q1 2013, the North, South, and West rings were operational. The upgrade of the western long haul route was completed during Q3. 3088 miles of existing network have been upgraded, including upgrading 73 interconnection points. Phase 3 - IHS/BBI executed 14 capacity agreements with last mile providers to date and executed 2 capacity agreements with CAIs, Riverside Clinic and Siouxland PACE clinic. All fiber routes for the Maquoketa, Denison, and Charles City have been constructed during this quarter, completing all construction activities to connect new customers. Total CAIs migrated by end of Q3 total 181, of those 154 were originally planned CAIs and 27 were newly added CAIs that will benefit from their newly upgraded connectivity. 112 new network miles were deployed, 98 miles leased, and 3088 existing network miles were upgraded to include 73 interconnection point upgrades during this project. | 112 | 98 | 3088 | 0 | 112 | 0 | 0 | 73 | Complete | Complete | Complete | N/A | Complete | N/A | N/A | Complete | 14 | 12 | 20 | Cedar Falls Utilities US Secure Hosting Center Bellevue Municipal Utilities Enseva Data Center Mahaska Communications Group Osage Municipal Utilities FiberComm InfoBunker Harlan Municipal Utilities VS Enterprises City of Denison Professional Computer City of Maquoketa City of Charles City Riverside Clinic - removed from the list of broadband wholesalers or last mile providers. This clinic is under new Community Anchor Institutions. Siouxland PACE Clinic- removed from the list of broadband wholesalers or last mile providers. This clinic is under new Community Anchor Institutions. | See Attachment | N/A | 14 | 0 | 0 | 5 | Variance due to signing Siouxland PACE and Riverside clinics. We are providing them broadband connectivity and have removed them from the Broadband Wholesalers or Last Mile Providers and replaced them in the Community Anchor Instiution category. | N/A | N/A | 50Megs = 3 subscribers 100Megs=5 subscribers 500Megs=1 subscriber 1Gig=4 subscribers 2Gig=1 subscriber | 181 | 0 | 181 | 1 | Variance from baseline report of 190 due to clinics relocating or closing within the funding period. | No variance from baseline report | Variance from baseline report of 190 due to clinics relocating or closing within the funding period. | 100Megs=181 subscribers | 0 | 0 | 0 | 0 | 0 | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | 0 | 0 | 0 | 0 | 0 | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | No variance from baseline report | No special offerings during Q3 2013. | FALSE | N/A | Project closeout completion. | Iowa Health System | IHS did not face any challenges during the past quarter that would have impacted project completion. | N/A | TRUE
NT10BIX5570085 | 2010 | Q4 | Q4 - 2010 | We have completed a draft environmental assessment and are now responding to questions from the various entities involved. The overlap issue has essentially been resolved and we are now working with NTIA on how best to reallocate the capital displaced by the overlap resolution. Two of the vehicles proposed in our application have been purchased using recipient funds and are available for the project | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | Environmental clearance to proceed with contruction has not been granted to date. | No Variance | No Variance | No Variance | 0 | 0 | 0 | No agreements have been signed with any wholesale or last mile providers to date. | No wholesale services have yet been provided by this project. | We have not designated a third party to operate all or a portion of our network. | 0 | 0 | 0 | 0 | No Variance | No Variance | N/A | For Broadband Wholesalers and Last Mile Providers Transport and Internet bandwidth are sold on a per-Megabit basis. Capacity is available from 1Megabit/second to 10Gigabit/second. Higher speeds may also be available; however are provided on an individual case basis, where available. It is estimated that 80 percent of the Broadband Wholesalers and Last Mile Providers will take under 100Megabit/second of capacity. The remaining 20 percent are expected to use significantly higher rates, including 2.5Gigabit/second and 10Gigabit/second service. | 47 | 0 | 0 | 0 | VTBell has 47 existing customer that were listed under the proposed CAI's. Service is currently provided to these institutions and is not dependent on construction of new facilities. | No Variance | No Variance | Community Anchor Institutions may also buy capacity on a per-Megabit/second basis; however we expect most of them will take advantage of one of our two tier pricing models. The first is 25Megabit/second of Internet capacity, burstable to 1000Megabit/second, including offsite data storage. The second is 100Megabit/second of Internet capacity, burstable to 1000Megabit/second, including offsite data storage. Both of these packages also include savings on GigE "spoke" connections to nearby facilities, allowing a highspeed local area network. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | With all $1,400 and $2,500 packages we include off site data storage, access to Internet2 and access to a state wide WAN connection. | FALSE | N/A | We plan to have completed our environmental assessment . | Vermont Telephone Company, Inc. | We are currently working with our program officer to finalize the reallocation of funds displaced by the resolution of overlap with another award recipient. This process has been the biggest challenge to planned progress as it has, among other things, introduced uncertainty in the routes being constructed and the final design for the electronics, which have a direct impact on many pieces of our project milestones. Once this issue has been resolved we can move forward with implementation. With the funding of both VTBell and the State of Vermont's VTA/Sovernet application, an unexpected number of Vermont's several hundred school boards, schools, and other CAI institutions concluded that the VTBell and VTA/Sovernet were competitors. This caused both confusion and frustration for CAI's. Some interpreted these series of events to indicate there was no single integrated statewide network and therefore many have decided to "go their own way" signing long-term contracts with other fiber providers who have been connecting customers since the NTIA awards. These developments have caused CAI's to be reluctant to proceed with signing contracts while the uncertainties of overlap exists between the two funded projects. A quick resolution to the process of removing overlap and coming to a resolution on the redeployment of grant funds, displaced by overlap, will help VTBell regain the momentum needed to complete the overall project and meet the milestones listed above. | Two of the biggest challenges we anticipate, during the next quarter, that will have an impact on our planned progress are: 1. Coming to a resolution on the overlap and reallocation of funds displaced by the remove of routes. 2. Getting our environmental assessment updated to reflect the changes made in the overlap resolution process. | TRUE
NT10BIX5570085 | 2011 | Q1 | Q1 - 2011 | During this quarter we continued efforts to resolve and eliminate overlap between our project and two other NTIA-funded projects. These efforts were ongoing through the entire quarter; however at the time of submitting this report (quarter 2) we have completed this process and received approval on our Overlap Special Award Condition and our Reprogram/Rebudget request that was required as a result of the overlap resolution. | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 2 | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | We have established an interconnection point with two service providers. | 0 | 0 | 0 | We have 7 existing agreements with broadband wholesale and last mile providers who's connection will be upgraded as a result of this project. These customers are shown in the quarterly indicators of the baseline. With the change in the scope of the project no new wholesale and last mile providers have signed agreements as the construction of the project has not begun. | No new wholesale services have yet been provided by this project. | We have not designated a third party to operate all or a portion of our network. | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | For Broadband Wholesalers and Last Mile Providers, transport and Internet bandwidth are sold on a per-Megabit basis. Capacity is available from 1Mbps/Second to 10Gbps/Second. Higher speeds may also be available; however are provided on a individual case basis, where available. | 0 | 0 | 0 | 0 | VTBell has 47 existing customers that were listed under the proposed CAI's. These customers connections will be upgraded with the network funded by NTIA which is in process. | No Variance | No Variance | Community Anchor institutions may also buy capacity on a per-Megabit/second basis; however we expect most of them will take advantage of one of our two tier pricing models. The first is 25Megabit/second of Internet capacity, burstable to 1000Megabit/second, including off site data storage. The second is 100Megabit/second of Internet capacity, burstable to 1000Megabit/second. Both packages include offsite data storage and savings on GigE "spoke" connections to nearby facilities. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | With all $1,400 and $2,500 packages we include off site data storage, access to Internet2 and acess to a state wide WAN connection. | FALSE | N/A | During the next quarter we anticipate the completion of the revised environmental assessment with the issuance of a FONSI by the NTIA. We also will have issued and completed our request for proposal for engineering services and equipment procurement. During the next quarter we will also have received approval of our updated budget. We anticipate the overlap special award condition to be lifted. We also plan to have our 6 month budget approved. | Vermont Telephone Company, Inc. | During this quarter we worked with our Federal Program Officer to finalize the resolution of overlap and reallocation of funds. This process has continued to be the biggest challenge to the planned progress as it has introduced uncertainty in the routes being constructed, the final design of the network, and our progress towards satisfying our Special Award Conditions. At the time of submitting this report (during the next quarter) we have resolved the overlap and reallocation of funds issues and are now able to work to implement the project. The original baseline report indicates we are behind in several key milestones; however the reduction in size and scope of the project reduces the required time to completion significantly. We are currently working on a revised baseline and key milestones to more accurately measure our progress past this point. | The biggest challenges during the next quarter are getting final approval for our updated Environmental Assessment. With regard to the environmental assessment, any assistance the BTOP program can give to issuance of a timely FONSI would be of great benefit to the progress of the project. While the milestones in the original baseline would indicate that our project is behind the original baseline; however due to the reduction in project scope, which removed approximately 50% of the new miles to be constructed we do not see a significant risk to the completion of the project within the allotted time line | TRUE
NT10BIX5570085 | 2011 | Q2 | Q2 - 2011 | During this quarter we completed efforts to resolve and eliminate overlap between our project and two other NTIA-funded projects and have received approval on our Overlap Special Award Condition and our Reprogram/Rebudget request that was required as a result of the overlap resolution. During Q2 2011 the project also successfully submitted an updated EA and received a FONSI resulting in a release of funds. During this quarter we also released an RFP for the engineering and project management services which was completed and awarded to a firm. An RFP was also released for the DWDM optical equipment and will be completed in early Q3 2011. During the process of finalizing our project and reprogram and rebudget we received valuable support from the State of Vermont and the chief of Connect VT, Karen Marshall. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance from updated baseline. | No Variance from updated baseline. | No Variance from updated baseline. | No Variance from updated baseline. | No Variance from updated baseline. | No Variance from updated baseline. | No Variance from updated baseline. | No Variance from updated baseline. | 0 | 0 | 0 | We have 7 existing agreements with broadband wholesale and last mile providers whose connection will be upgraded as a result of this project once the core optical network is installed. These customers are shown in the quarterly indicators of the baseline. The connections to these wholesale and last mile providers are expected to be upgraded in the 4th quarter of this year. At that point they will be shown as receiving upgraded service. | No new wholesale services have yet been provided by this project. | We have not designated a third party to operate all or a portion of our network. | 0 | 0 | 0 | 0 | No variance with updated baseline | We have 7 existing agreements with broadband wholesale and last mile providers whose connection will be upgraded as a result of this project once the core optical network is installed. These customers are shown in the quarterly indicators of the baseline. The connections to these wholesale and last mile providers are expected to be upgraded in the 4th quarter of this year. At that point they will be shown as receiving upgraded service. | No variance with updated baseline | For Broadband Wholesalers and Last Mile Providers, transport and Internet bandwidth are sold on a per-Megabit basis. Capacity is available from 1Mbps/Second to 10Gbps/Second. Higher speeds may also be available; however are provided on a individual case basis, where available. | 0 | 0 | 0 | 0 | VTBell has 47 existing customers that were listed under the proposed CAI's. These customers connections will be upgraded with the network funded by NTIA which is in process. | No variance with updated baseline | No variance with updated baseline | Community Anchor institutions may also buy capacity on a per-Megabit/second basis; however we expect most of them will take advantage of one of our two tier pricing models. The first is 25Megabit/second of Internet capacity, burstable to 1000Megabit/second, including off site data storage. The second is 100Megabit/second of Internet capacity, burstable to 1000Megabit/second. Both packages include offsite data storage and savings on GigE "spoke" connections to nearby facilities. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | With all $1,400 and $2,500 packages we include off site data storage, access to Internet2 and acess to a state wide WAN connection. | FALSE | N/A | During the next quarter we plan to have selected a DWDM vendor. We will have begun the purchase and installation of the DWDM network to provide our 47 existing customers with upgraded services utilizing the NTIA Funds. | Vermont Telephone Company, Inc. | With the resolution of overlap and reallocation of funds resolved,we can now focus on working with our recently selected engineering firm to accelerate the process of network design, rights of way and construction permits and other approvals. The process of selecting a vendor and getting those resources for the project in place that has been one of the challenges faced during this quarter. The process of identifying overlap, removing it, and reprogram/rebudget of the project has put our project behind the original baseline; however due to the reduction in project scope, which removed approximately 50% of the new miles to be constructed we do not see a significant risk to the completion of the project within the allotted time line. In addition to the reductions in the project scope a substantial amount of the budget is allocated to electronics which will be deployed within the fall of 2011. This expenditure will get us close to the 67% completion required in year 2 of the project. | During the next quarter we will be aggressively working to get rights of way and construction permits and other approvals submitted. Any delay in obtaining these approvals will push out construction forecast in the coming quarters. | TRUE
NT10BIX5570085 | 2011 | Q3 | Q3 - 2011 | During this quarter the majority of of the project field engineering was completed. Signed a equipment and services contract with DWDM vendor. Submitted purchase order for DWDM equipment. Released RFP for construction services. Hired a Project Accountant to help with organization and tracking of VTel ARRA projects. Project status calls with BTOP staff every two weeks. Focused contact on k-12 school CAI's. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | N/A | N/A | No variance from baseline. | 7 | 0 | 0 | We have 7 existing agreements with broadband wholesale and last mile providers whose connection will be upgraded as a result of this project once the core optical network is installed. These customers are shown in the quarterly indicators of the baseline. The connections to these wholesale and last mile providers are expected to be upgraded in the 4th quarter of this year. At that point they will be shown as receiving upgraded service. | No new wholesale services have yet been provided by this project. | We have not designated a third party to operate all or a portion of our network. | 0 | 0 | 0 | 0 | No variance with baseline. | No variance with baseline. | No variance with baseline. | For Broadband Wholesalers and Last Mile Providers, transport and Internet bandwidth are sold on a per-Megabit basis. Capacity is available from 1Mbps/Second to 10Gbps/Second. Higher speeds may also be available; however are provided on a individual case basis, where available. | 0 | 0 | 0 | 0 | VTBell has 47 existing customers that were listed under the proposed CAI's. These customers connections will be upgraded with the network funded by NTIA which is in process. | No variance with baseline. | No variance with baseline. | Community Anchor institutions may also buy capacity on a per-Megabit/second basis; however we expect most of them will take advantage of one of our two tier pricing models. The first is 25Megabit/second of Internet capacity, burstable to 1000Megabit/second, including off site data storage. The second is 100Megabit/second of Internet capacity, burstable to 1000Megabit/second. Both packages include offsite data storage and savings on GigE "spoke" connections to nearby facilities. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | With all $1,400 and $2,500 packages we include off site data storage, access to Internet2 and acess to a state wide WAN connection. | FALSE | N/A | In the coming quarter we plan to deploy a significant portion of the core electronics for the network. This will enable the new fiber being built to be aggregated and receive high speed data, and backhaul to core interconnection locations. This is one of the major steps for us in providing service under the BTOP project. We also plan to begin submitting permit requests for pole attachments, make ready, and obtaining easements based on the engineering work that has been done to date. We do not expect any new network miles deployed or network miles leased in the next quarter. We expect that 47 existing customers will have improved service in the next quarter and 5 new customers will have service. 90% of permit applications are expected to be filed in the next quarter. | Vermont Telephone Company, Inc. | The largest impact to our project schedule was the occurrence of Hurricane/Tropical Storm Irene. The storm caused widespread damage to Vermont utility infrastructure and roads. Travel to many areas became difficult as areas of the state were inaccessible. Working with other utilities was slow because of their need to respond and restore their infrastructure. This has caused a slight delay in progress on engineering and permit/make-ready requests. At this time we do not feel that it will impact the completion schedule of the project, and will continue to forecast progress. 67% completion is still considered to occur in Q4 of year 2, and 100% in Q4 of year 3. | Weather conditions and multiple holidays during the next quarter are two items that could threaten to delay progress on engineering, and deployment of electronics to the field. We are working closely with our engineering contractor and DWDM vendor to be sure of availability of personnel and timely delivery of equipment. As with any quarter leading up to the fiber construction, obtaining permits and completing make ready are always a risk for introduction of delay in the project schedule. | TRUE
NT10BIX5570085 | 2011 | Q4 | Q4 - 2011 | During this quarter our outside engineers continued field engineering. They are very close to completion, and have been preparing the necessary pole applications and state permits that are needed for construction. We have made a final selection for construction vendor based on the results of last quarter's RFP. We have continued to update BTOP staff every two weeks. We are responding to the PIP's identified in our site visit. A concentrated effort has been made to reach all CAI's and numerous discussions and negotiations have taken place this quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | The DWDM equipment that will upgrade the existing network was installed in Q4â€™11 and is in the process of being cut-over. It is expected to be fully operational in Q1'12. | The DWDM equipment that will upgrade the existing network was installed in Q4â€™11 and is in the process of being cut-over. It is expected to be fully operational in Q1'12. | No variance from baseline. | N/A | N/A | The DWDM equipment that will upgrade the existing network was installed in Q4 2011 and is in the process of being cut-over. It is expected to be fully operational in Q1 2012. | 6 | 1 | 20 | We have 6 existing agreements with broadband wholesale and last mile providers whose connection will be upgraded as a result of this project once the core optical network is installed. These customers are shown in the quarterly indicators of the baseline. We expect to be on schedule in Q1 2012. | No new wholesale services have yet been provided by this project. | We have not designated a third party to operate all or a portion of our network. | 0 | 0 | 0 | 0 | No variance with baseline. | Providers receiving improved access has been delayed until the DWDM has been fully installed and operational. This is expected to be completed in Q1 2012. | No variance with baseline. | No variance with baseline. | 0 | 0 | 0 | 0 | VTBell has 47 existing customers that were listed under the proposed CAI's. These customers connections will be upgraded with the network funded by NTIA which is in process. This is expected to happen in Q1 2012. | Fiber construction will begin Q1 2012. We have had discussions with multiple schools who have submitted applications through the ERate process. We are prioritizing the routes to be constructed to coincide with the schools' funding years where possible. | Existing subscribers will receive improved once the DWDM is fully installed and operational. This is expected to be completed in Q1 2012. | Community Anchor institutions may also buy capacity on a per-Megabit/second basis; however we expect most of them will take advantage of one of our two tier pricing models. The first is 25Megabit/second of Internet capacity, burstable to 1000Megabit/second, including off site data storage. The second is 100Megabit/second of Internet capacity, burstable to 1000Megabit/second. Both packages include offsite data storage and savings on GigE "spoke" connections to nearby facilities. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | With all $1,400 and $2,500 packages we include off site data storage, transport to Internet2 and access to a state wide WAN connection. | FALSE | N/A | In the next quarter we expect to have installed 85% of the core electronics. We plan to complete submitting permit requests for pole attachments, make ready, and obtaining easements based on the engineering work already completed. We expect that all remaining engineering will be completed in the following quarter. We plan to contract with an experienced person to apply for all railroad permits. Construction is slated to begin and we intend to complete approximately 15 miles. We expect to be at 67% completion in Q1 2013, Grant Year 3 Q2. We expect to be at 100% completion in Q3 3013, Grant Year 3 Q4. | Vermont Telephone Company, Inc. | Although construction is not scheduled to begin until the first quarter of 2012, it was necessary to increase the rate in which we were reaching out to community anchors. By doing that, we quickly became aware that there might be changes to the list proposed originally, and determined through the overlap process, based on many different factors including economic conditions, market competition from other providers, changes in location due to tropical storm Irene, etc. We plan to file an Award Action Request to address the community anchors that are being replaced. VTel also needed to adopt and document procedures to adequately comply with the financial management guidelines for the BTOP project. Processes are in place to identify allowable costs, however the policies needed to be clearly outlined, to ensure that BTOP guidelines are being followed. The last performance improvement plan that was identified concerned identifying that all BTOP terms and conditions be included in any contracts entered into during the NTIA grant period. We have made corrections to all existing contracts, and any new contracts are being reviewed by VTel's attorneys to make sure that they include all the necessary terms and conditions required. | Construction is scheduled to begin in the next quarter. One issue that might impact the progress of meeting the goal of 15 miles is the ability of the various utility companies to respond quickly to our pole applications, and the timeliness of make ready work. We have had a fairly mild winter to date, but early spring storms could also affect the construction schedule. | TRUE
NT10BIX5570085 | 2012 | Q1 | Q1 - 2012 | During this quarter, engineering on the initial routes was completed, and any additional engineering will be for slight route changes. Construction has begun and a total of 9 miles were completed. Installation of the electronics continued this quarter. The majority of permit applications have been submitted, and we are now responding to numerous make ready payment requests. We continue to update the BTOP team on a biweekly basis and have submitted requests for some route removals, as well as route additions, as determined by our efforts to reach the CAI's in our project. | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | Construction equipment malfunctions caused a slight delay in construction for the 1st quarter. We have also submitted a large number of make ready payments; however the utility owners are within their allotted time to complete, and many of these are due to be completed in the 2nd quarter of this year. | No variance with baseline | The DWDM equipment that will upgrade the existing is still being installed. We expect to reach our baseline by the end of 2012. | The DWDM equipment that will upgrade the existing leased miles is still being installed. We expect to reach our baseline by the end of 2012. | This is six miles less than our baseline, due to pole make ready. We still expect to meet our baseline estimates for completion of the project. | N/A | N/A | The DWDM equipment that will be needed to add new or upgraded interconnection points is not yet operational. | 6 | 1 | 20 | We have 6 existing agreements with broadband wholesale and last mile providers whose connection will be upgraded as a result of this project once the core optical network is installed. These customers are shown in the quarterly indicators of the baseline. We expect to be on schedule by the end of 2012. | No new wholesale services have yet been provided by this project. | We have not designated a third party to operate all or a portion of our network. | 0 | 0 | 0 | 0 | No variance with baseline | The electronic equipment is not yet operational. We expect to meet the baseline by the end of 2012. | N/A | The electronic equipment is not yet operational. We expect to meet the baseline by the end of 2012. | 0 | 0 | 0 | 0 | VTBell has 47 existing customers that were listed under the proposed CAI's. These customers connections will be upgraded with the network funded by NTIA which is in process. This is expected to happen by the end of 2012. | We have had discussions with multiple schools who have submitted applications through the ERate process. We are prioritizing the routes to be constructed to coincide with the schools' funding years where possible. New access will be available to them by the end of 2012. | Existing subscribers will receive improved once the DWDM is fully installed and operational. This is expected to be completed by the end of 2012. | Community Anchor institutions may also buy capacity on a per-Megabit/second basis; however we expect most of them will take advantage of one of our two tier pricing models. The first is 25Megabit/second of Internet capacity, burstable to 1000Megabit/second, including off site data storage. The second is 100Megabit/second of Internet capacity, burstable to 1000Megabit/second. Both packages include offsite data storage and savings on GigE "spoke" connections to nearby facilities. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | With all $1,400 and $2,500 packages we include off site data storage, transport to Internet2 and access to state wide WAN connection. | FALSE | N/A | During the next quarter, we expect that many make ready requests will have been completed, and that construction will meet the baseline of 55 miles. We anticipate completing fiber deployment by the end of 2012. We expect that the core electronics will continue to be installed with completion by year end. We expect to be at 67% completion in Q1 2013. We expect to be at 100% completion in Q2 2013. We look to connect at least 3 schools in the next quarter, however they will not be able to received the improved access until the core electronics are operational. Additionally the 6 agreements with broadband wholesaler/last mile providers will receive the improved access at that same time. Although make ready completion is not within our control, we believe that it will be completed in time for our contractor to complete construction, meeting our baseline completion date. We also have found that make ready pricing, electronic pricing, and construction pricing is favorably below budget to date. | Vermont Telephone Company, Inc. | As we continue to reach out to CAI's in our project, we have found it necessary to make some route additions and deletions. Make ready responses have also indicated some areas where the costs might outweigh the need in a certain area. Each of these situations require additional research and discussion to determine the best way to proceed. Our team is meeting on a weekly basis to discuss the timing of make ready, and construction, as it coincides with the needs of our existing and new customers. The installation of the network electronics is not going as quickly as originally anticipated. On several parts of the network the new electronics are replacing older electronics, which are still proving service to live customers. This means we need to perform the transitions during scheduled maintenance windows in an attempt to cause as little disruption to existing customers as possible. | We may experience delays based on the ability of various utility companies ability to respond quickly to our make ready requests. We will monitor this closely and ask for additional support from local government officials if we see this starting to occur. | TRUE
NT10BIX5570085 | 2012 | Q2 | Q2 - 2012 | During this quarter construction continued and a total of 15 miles were completed. A routine weekly call with Fair Point was developed to assist in managing the make ready process. Members from VTel, Fair Point's Make Ready Coordinator, and the respective managers for each geographical area discuss progress for each segment and the priorities based on our construction plan. Significant progress on make ready in one of our largest planned segments occurred in this quarter, and construction is slated to be complete by the end of the third quarter for this segment (approximately 45 miles). We have continued to update the BTOP team on a biweekly basis and are preparing an action report request based on our projects needs utilizing their guidance. | 15 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | Utility pole owners were behind with our make ready requests during the beginning of this quarter. We have instituted bi-weekly calls with the major owner to expedite the process, and progress has been noted since the calls began. | No variance with baseline. | The DWDM equipment that will upgrade the existing network is still being installed. We expect to reach baseline by the end of 2012. | N/A | We have constructed 35 miles less than our baseline, mainly due to timing of make ready completion. We expect to meet baseline estimates by the 1st quarter of 2013. | N/A | N/A | The DWDM equipment that is needed to add new or upgraded interconnection points is not yet operational. | 6 | 1 | 20 | [REDACTED] | No new wholesale services have yet been provided by this project. | We have not designated a third party to operate all or a portion of our network. | 0 | 0 | 0 | 0 | The electronic equipment is not yet operational. We expect to meet the baseline by the end of 2012. | The electronic equipment is not yet operational. We expect to meet the baseline by the end of 2012. | N/A | The electronic equipment is not yet operational. We expect to meet the baseline by the end of 2012. | 0 | 0 | 0 | 0 | VTBell has 47 existing customers that were listed under the proposed CAI's. These customers connections will be upgraded with the network funded by NTIA which is in process. This is expected to happen by the end of 2012. | We have had discussions with multiple schools who have submitted applications through the ERate process. We are prioritizing the routes to be constructed to coincide with the schools' funding years where possible. New access will be available to them by the end of 2012. | Existing subscribers will receive improved once the DWDM is fully installed and operational. This is expected to be completed by the end of 2012. | Community Anchor institutions may also buy capacity on a per-Megabit/second basis; however we expect most of them will take advantage of one of our two tier pricing models. The first is 25Megabit/second of Internet capacity, burstable to 1000Megabit/second, including off site data storage. The second is 100Megabit/second of Internet capacity, burstable to 1000Megabit/second. Both packages include offsite data storage and savings on GigE "spoke" connections to nearby facilities. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | With all $1,400 and $2,500 packages we include off site data storage, transport to Internet2 and access to state wide WAN connection. | FALSE | N/A | During the next quarter, we expect that numerous make ready segments will be complete, allowing construction to increase to an estimate of 60-70 miles. We expect the the core electronics will continue to be installed, with completion by the end of 2012. We expect to have nine CAI's connected by the end of the quarter, and possibly one new agreement with a broadband wholesaler/ last mile provider Overall construction is expected to be 67% by the 4th quarter of 2012 and 100% by the second quarter of 2013. We are also working closely with VTA and Karen Marshall to help identify other underserved areas in Vermont that would ultimately aid in replacing CAI's that may have been removed to overlap. | Vermont Telephone Company, Inc. | As the project progresses, our team meets on a weekly basis to discuss issues related to CAI's, make ready responses, make ready deadlines, construction, and any other topics that are affecting the success of the project. We are compiling a request that will have additions, removals, and possible changes to the routes originally applied for. These changes will utilize the NTIA funding to reach the largest number of CAI's that are currently under served and would benefit from fiber construction. | We have experienced delays from various utility companies, however we have reached out to them and our local government officials to assist us with overcoming them. There has been significant progress which we expect to continue. Equipment deployment has experienced delays, however, progress is being made, and completion is still expected by the end of 2012. | TRUE
NT10BIX5570085 | 2012 | Q3 | Q3 - 2012 | During 3Q12 we turned up two major segments of our DWDM network, with testing. We constructed 21 miles of new fiber facilities, and connected 8 new CAI's. We also submitted a completed Award Action Request for potential route changes and additions, which is under review by NTIA staff. | 36 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | Utility pole owners have been behind with our make ready requests. Our outside engineering company has done a physical survey of the remaining poles, and is contacting the major owner to expedite the process. | No variance with baseline. | The DWDM equipment that is needed to upgrade existing network miles in not yet operational. | N/A | We have constructed 61 miles less than our baseline, mainly due to timing of make ready completion. We expect to meet baseline estimates by the 1st quarter of 2013. | N/A | N/A | The DWDM equipment that is needed to add new or upgraded interconnection points is not yet operational. | 6 | 1 | 20 | [REDACTED] | No new wholesale services have yet been provided by this project. | We have not designated a third party to operate all or a portion of our network. | 0 | 0 | 0 | 0 | The electronic equipment is not yet operational. | The electronic equipment is not yet operational. | N/A | The electronic equipment is not yet operational. | 8 | 8 | 0 | 0 | VTel has 47 existing customers that were listed under the proposed CAI's. These customers connections will be upgraded with the network funded by NTIA which is in process. | VTel has connected five schools, and 3 health care facilities. | Existing subscribers will receive improved once the DWDM is fully installed and operational. | Community Anchor institutions may also buy capacity on a per- Megabit/second basis; however we expect most of them will take advantage of one of our two tier pricing models. The first is 25Megabit/second of Internet capacity, burstable to 1000Megabit/ second, including off site data storage. The second is 100Megabit/second of Internet capacity, burstable to 1000Megabit/second. Both packages include offsite data storage and savings on GigE "spoke" connections to nearby facilities. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | With all $1,400 and $2,500 packages we include off site data storage, transport to Internet2 and access to state wide WAN connection. | FALSE | N/A | During the next quarter, we expect that numerous make ready segments will be complete, allowing construction to increase to an estimate of 60-70 miles. We expect the the core electronics will continue to be installed. We expect to have fifteen CAI's connected by the end of the quarter, and possibly one new agreement with a broadband wholesaler/ last mile provider Overall construction is expected to be 67% by the 4th quarter of 2012 and 100% by the second quarter of 2013. We have submitted a request to review additions and deletions to our CAI list, as well as modifications to the original planned routes. We expect that a determination on this request will be made in the 4th quarter 2012. | Vermont Telephone Company, Inc. | As the project progresses, our team meets on a weekly basis to discuss issues related to CAI's, make ready responses, make ready deadlines, construction, and any other topics that are affecting the success of the project. We are compiling a request that will have additions, removals, and possible changes to the routes originally applied for. These changes will utilize the NTIA funding to reach the largest number of CAI's that are currently under served and would benefit from fiber construction. | We have experienced delays from various utility companies, however we have reached out to them and our local government officials to assist us with overcoming them. There has been significant progress which we expect to continue. Equipment deployment has experienced delays, however, progress is being made. | TRUE
NT10BIX5570085 | 2012 | Q4 | Q4 - 2012 | During 4Q12, we turned up two additional major segments of our DWDM network, with testing. We constructed 10 miles of new fiber facilities. We experienced additional delays with make ready and contracted with a local inspector to assist us with resolution of any problems that were delaying the licensing of segments. Our Award Action Request was submitted officially late in the fourth quarter, based on suggestions and direction from NTIA. It has been advanced to the Environmental area for review. | 46 | 0 | 136 | 0 | 46 | 0 | 0 | 9 | Utility pole owners have been behind with our make ready requests. Our outside engineering company has done a physical survey of the remaining poles, and is contacting the major owner to expedite the process. We have also contracted with an inspector to assist in these communications. He is familiar with many of the organizations and the contacts necessary to speed up the process. | No variance with baseline. | The DWDM equipment that is needed to upgrade existing network miles in not yet operational. | N/A | We have constructed 80 miles less than our baseline, mainly due to timing of make ready completion. We still expect to be able to complete the original project by June of 2013. | N/A | N/A | The DWDM equipment that is needed to add new or upgraded interconnection points is not yet operational. | 6 | 1 | 20 | [REDACTED] | No new wholesale services have yet been provided by this project. | We have not designated a third party to operate all or a portion of our network. | 0 | 0 | 0 | 0 | The electronic equipment is not yet operational. | The electronic equipment is not yet operational. | N/A | The electronic equipment is not yet operational. | 11 | 11 | 0 | 0 | VTel has 47 existing customers that were listed under the proposed CAI's. These customers connections will be upgraded with the network funded by NTIA which is in process. | VTel has connected five schools, and 3 health care facilities. | Existing subscribers will receive improved once the DWDM is fully installed and operational. | Community Anchor institutions may also buy capacity on a per- Megabit/second basis; however we expect most of them will take advantage of one of our two tier pricing models. The first is 25Megabit/second of Internet capacity, burstable to 1000Megabit/ second, including off site data storage. The second is 100Megabit/second of Internet capacity, burstable to 1000Megabit/second. Both packages include offsite data storage and savings on GigE "spoke" connections to nearby facilities. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | With all $1,400 and $2,500 packages we include off site data storage, transport to Internet2 and access to state wide WAN connection. | FALSE | N/A | With additional people working to speed up the make ready process, additional mileage will become ready for construction in the first quarter of 2013. Additional equipment deployment and testing is also scheduled to occur in 1Q13. We await the approval of our submitted Action Award Request. We estimate that five additional CAI's will be connected in 1Q13. | Vermont Telephone Company, Inc. | Our team continues to hold weekly meetings to discuss make ready delays, construction progress, electronic installation progress, community anchor connections, and any other topics that need to be addressed for the timely completion of the project. Make ready delays have occurred on segments where a partial number of poles have been completed, due to availability of crews, difficulty in level of make ready. These partial segments needed to be addressed individually with the pole owners, so that attention, and completion could be accomplished. | We believe that the additional effort to get the make ready completed will help the construction progress, however if there were any significant delays on any segments, this could affect the projections for the first quarter. Equipment deployment and testing has had some delays due to technical issues. We believe that they have been resolved and any future deployment and testing will go smoothly. If this isn't the case, projections would not be accurate. | TRUE
NT10BIX5570085 | 2013 | Q1 | Q1 - 2013 | During 1Q13 we turned up six additional major segments of our DWDM network. We constructed almost 30 miles of new fiber. We placed three new Points of Presence. We continued working with NTIA staff on our Award Action Request that was submitted late in 4Q12. KPI's for the first quarter of 2013 were 2 CAI's connected and 21.4 miles of fiber deployed. | 76 | 0 | 241 | 0 | 76 | 0 | 0 | 13 | Some make ready and permits are still pending, but we have made significant progress in the last quarter. We are continuing to work closely with pole owners. | No variance with baseline | The DWDM equipment that is needed to upgrade existing network miles is not yet operational. | N/A | Some make ready and permits are still pending, but we have made significant progress in the last quarter. We are continuing to work closely with pole owners. | N/A | N/A | The DWDM equipment that is needed to add new or upgraded interconnection points is not yet operational. | 7 | 0 | 20 | [REDACTED] | No new wholesale service have been provided by this project at this point in time. | We have not designated a third party to operate any or all of our network. | 0 | 0 | 0 | 0 | The electronic equipment is not yet operational | The electronic equipment is not yet operational | N/A | The electronic equipment is not yet operational | 38 | 38 | 0 | 0 | N/A | N/A | N/A | Community Anchor institutions may also buy capacity on a per- Megabit/second basis; however we expect most of them will take advantage of one of our two tier pricing models. The first is 25Megabit/second of Internet capacity, burstable to 1000Megabit/ second, including off site data storage. The second is 100Megabit/second of Internet capacity, burstable to 1000Megabit/second. Both packages include offsite data stora | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | With all $1,400 and $2,500 packages we include off site data storage, transport to Internet2 and access to state wide WAN connection. | FALSE | N/A | Next quarter we plan to complete turn-up of all the major DWDM network segments, and make significant progress on the remaining fiber miles to be constructed in the project. Mileage in Q2 will be approximately 30 miles which will get us to 76% of the project. We expect to "connect" another 20 CAI's during the quarter which brings us to 50% of the total and we do not expect to sign any broadband wholesaler/last mile provider agreements before June 30, 2013. | Vermont Telephone Company, Inc. | Our team continues to hold weekly meetings to discuss make ready delays, construction progress, electronic installation progress, community anchor connections, and any other topics that need to be addressed for the timely completion of the project. Make ready delays have occurred on segments where a partial number of poles have been completed, due to availability of crews, difficulty in level of make ready. These partial segments needed to be addressed individually with the pole owners, so that attention, and completion could be accomplished. | Make ready and permit approvals continue to be our largest challenge. We will be submitting an extension request as these delays are hindering our ability to complete the project within the initial term. By the end of the 2nd quarter we will have spent 75% of the total project's budget. An extension request AAR was submitted. | TRUE
NT10BIX5570085 | 2013 | Q2 | Q2 - 2013 | During 2Q13 our AAR was approved which allowed us to further our coverage points and reach more 'underserved' Vermonters. We submitted an extension request to allow for winter weather and permitting roadblocks that were hindering our ability to deliver a completed project by June 30, 2013. Our project deadline is now August 2014. During the quarter we deployed 7.3 miles of fiber and connected 5 CAI's | 83 | 0 | 241 | 0 | 83 | 0 | 0 | 13 | Few make ready and permits are still pending, but we have made significant progress in the last quarter. We are continuing to work closely with pole owners and expect a large increase in 3Q13 | No variance with baseline | The DWDM equipment that is needed to upgrade existing network miles is not yet operational. | N/A | Few make ready and permits are still pending, but we have made significant progress in the last quarter. We are continuing to work closely with pole owners and expect a large increase in 3Q13 | N/A | N/A | The DWDM equipment that is needed to upgrade existing network miles is not yet operational. | 6 | 0 | 20 | [REDACTED] | No new wholesale service have been provided by this project at this point in time. | We have not designated a third party to operate any or all of our network. | 0 | 6 | 0 | 0 | The electronic equipment is not yet operational | We are in continual talks with others to obtain more contracts but nothing has come of our negotiations. | N/A | The electronic equipment is not yet operational | 43 | 43 | 0 | 0 | N/A | N/A | N/A | Community Anchor institutions may also buy capacity on a per- Megabit/second basis; however we expect most of them will take advantage of one of our two tier pricing models. The first is 25Megabit/second of Internet capacity, burstable to 1000Megabit/ second, including off site data storage. The second is 100Megabit/second of Internet capacity, burstable to 1000Megabit/second. Both packages include off-site data storage | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | With all $1,400 and $2,500 packages we include off site data storage, transport to Internet2 and access to state wide WAN connection. | FALSE | N/A | Next quarter we plan to turn-up of all the major DWDM network segments, and make significant progress on the remaining fiber miles to be constructed in the project. Mileage in Q3 will be approximately 20 miles which will get us to 90% of the project. We expect to "connect" another 15 CAI's during the quarter which brings us to 64% of the total and we do not expect to sign any broadband wholesaler/last mile provider agreements before September 30, 2013. | Vermont Telephone Company, Inc. | Our team continues to hold weekly meetings to discuss make ready delays, construction progress, electronic installation progress, community anchor connections, and any other topics that needs to be addressed. Due to the availability of crews we have experienced some make ready delays on segments where a partial number of poles have been completed. Partial segments needed to be addressed individually with the pole owners so that we could progress along toward completion. The third quarter will see significant make ready permits issued for the routes outlined in the AAR. | The granting of our AAR and the extension request will enable us to complete our project in the most meaningful manner for all previously underserved Vermonters. | TRUE
NT10BIX5570085 | 2013 | Q3 | Q3 - 2013 | During 2Q13 our AAR was approved which allowed us to further our coverage points and reach more 'underserved' Vermonters. We submitted an extension request to allow for winter weather and permitting roadblocks that were hindering our ability to deliver a completed project by June 30, 2013. Our project deadline is now August 2014. During the quarter we deployed 22.88 miles of fiber and connected 1 CAI | 106 | 0 | 241 | 0 | 106 | 0 | 0 | 13 | Few make ready and permits are still pending, but we have made significant progress in the last quarter. We saw a large increase in 3Q13 in the number of permits issued. | no variance with baseline | The DWDM equipment that is needed to upgrade | n/a | Few make ready and permits are still pending, but we have made significant progress in the last quarter. We saw a large increase in 3Q13 in the number of permits issued. | n/a | n/a | The DWDM equipment that is needed to upgrade existing network miles is not yet operational. | 6 | 0 | 20 | We have 6 existing agreements with broadband wholesale and last mile providers whose connection will be upgraded as a result of this project once the core optical network is installed. These customers are shown in the quarterly indicators of the baseline. We expect to be on schedule by the end of 2012. Wholesale and last mile providers include: Earthlink, Topsham Telephone, Burlington Telecom, Wavecomm, Great Awk (formerly Finowen), and Light Tower (formerly Sidera). | No new wholesale service have been provided by this project at this point in time. | We have not designated a third party to operate any or all of our network. | 0 | 6 | 0 | 0 | The electronic equipment is not yet operational | We are in continual talks with others to obtain more contracts but nothing has come of our negotiations. | N/A | The electronic equipment is not yet operational | 44 | 44 | 0 | 0 | n/a | n/a | n/a | Community Anchor institutions may also buy capacity on a per- Megabit/second basis; however we expect most of them will take advantage of one of our two tier pricing models. The first is 25Megabit/second of Internet capacity, burstable to 1000Megabit/ second, including off site data storage. The second is 100Megabit/second of Internet capacity, burstable to 1000Megabit/second. Both packages include off-site data storage | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | With all $1,400 and $2,500 packages we include off site data storage, transport to Internet2 and access to state wide WAN connection. | FALSE | n/a | Next quarter we plan to turn-up of all the major DWDM network segments, and make significant progress on the remaining fiber miles to be constructed in the project. Mileage in Q4 will be approximately 5 miles which will get us to 92% of the new miles for the project. We expect to "connect" another 15 CAI's during the quarter which brings us to 73% of the total and we do not expect to sign any broadband wholesaler/last mile provider agreements before March 31, 2014 | Vermont Telephone Company, Inc. | Our team continues to hold weekly meetings to discuss make ready delays, construction progress, electronic installation progress, community anchor connections, and any other topics that needs to be addressed. Due to the availability of crews we have experienced some make ready delays on segments where a partial number of poles have been completed. Partial segments needed to be addressed individually with the pole owners so that we could progress along toward completion. In the third quarter we did see make ready permits issued for most routes outlined in the AAR and we have a few more to go. | The granting of our AAR and the extension request will enable us to complete our project in the most meaningful manner for all previously underserved Vermonters. | TRUE
NT10BIX5570085 | 2013 | Q4 | Q4 - 2013 | During this quarter we were able to build a total of 6 miles. Going forward we will be reporting route miles as opposed to the design miles we used to report. We have completed 129 route miles and target is at 142.14 Our progress toward upgrading existing network miles lags behind new construction as we find ourselves with 241 of our 410 existing network miles completed (new optics installed for enhanced service) and 12 of our 38 existing leased miles upgraded. We have connected 109 of our projected 136 total CAI's for the project. Due to weather in the Northeast we halted construction during the last 6 weeks of the quarter and we focused on obtaining permits and ROW's to work toward an on-time completion in August of 2014 | 129 | 0 | 241 | 12 | 129 | 0 | 0 | 25 | 6 miles built bringing us to 129 route miles of our revised projection of 142.14 route miles- weather has slowed construction considerably on the final We will continue to report route miles from now on as opposed to the design miles we formerly reported. | We continue to negotiate for a North-Link IRU. The baseline for this indicator was zero and we added the new leased miles in AAR GOL#2407329 approved on 5/17/2013 | The DWDM equipment that is needed to upgrade existing network miles is not yet operational therefore the upgraded optics are not fully deployed. We expect to be at 100% of our baseline 410 miles by the end of 2Q 2014. All of these miles were pre-existing to the BTOP project. | Our baseline for this indicator is 38. We have upgraded 12 of the baseline 38 of the Fairpoint miles that we lease and once the weather breaks we expect to be at 100% by July 31, 2014. | 6 miles built bringing us to 129 of our projected route miles of 142.14 - weather has slowed construction considerably on the final 13 miles | n/a | n/a | We have been able to exceed our baseline of 3 interconnection points and expect this figure to increase by project end. | 6 | 1 | 20 | Wholesale and last mile providers that are receiving improved access number six (out of a baseline of 7) and they are: Earthlink, Topsham Telephone, Burlington Telecom, Wavecomm, Great Awk (formerly Finowen), and Light Tower (formerly Sidera). Each of these arrangements were pre-existing to the BTOP project. We continue to negotiate but have been unable to formalize any contracts for new service. Our baseline for arrangements receiving new access was 3 and we do not expect to reach this target as there appears to be little interest from wholesale or last mile providers - there just is no market in Vermont for this service. | Each agreement that we have with wholesale providers is highly individualized and heavily negotiated. We range in speeds of 30 Mbps to 2,000 Mbps and offer a myriad of options in between. We do not have a formalized pricing plan for this service as our experience has dictated that each agreement is based on many intricate and highly individualized elements. We welcome each opportunity to negotiate and do not discriminate in any way and feel that we try to meet each providers needs. We will not hit our target of 3 new contracts - Sovernet was a recipient of funding and as a result they do not need our services. Telco declared bankruptcy so we could not enter into an agreement with them. | We have not designated a third party to operate any or all of our network. | 0 | 6 | 0 | 6 | Our baseline for arrangements receiving new access was 3 and we do not expect to reach this target - two of the three expected providers will not be taking our service. Sovernet received funding on its own and Telco declared bankruptcy. | Our baseline for improved access is 7.We have reached agreements with 6 providers. A pre-existing provider is no longer under contract with us. | At this point in the project we do not expect to offer dark fiber. | As with our pricing structure for wholesalers we do not have a specific grid of available speed tiers. Our contracts are based on a per Mbps need for internet service and a transport need (if there is one) and we bundle the needs of the customer in to a per Mbps agreement. We treat for reporting purposes each agreement as a separate speed tier as no two agreements are alike and the range of speeds from 30 Mbps to 2,000 Mbps do not lend themselves to the creation of tiers. the contracts are for 30 Mbps, 100Mps, 200 Mbps, 1000 Mbps, 2000 Mbps and 1GigE | 109 | 62 | 47 | 7 | We have attached a spreadsheet that shows 90 new CAI's connected since 3Q13. On our 3Q13 submission we had not included a full list of connected CAI's and we are now bringing the list to the correct level. Our CAI count has increased dramatically from previous submissions as we had been counting "served" rather than "connected CAI's prior to this report. We have connected 109 of our targeted 136 CAI's. | Our baseline for new access was 61 and we find ourselves exceeding that target with 62 availing themselves of new service | Our baseline for this category was 47 and we are at that figure as of the date of this report. | We have 7 pricing options available and have attached a pricing sheet to our submission that describes the terms of each. We currently have the following number of CAI's served for each tier: #1 - 1 10 to 25 Mbps #2 - 9 25 to 50 Mbps #3 - 0 50 to 100 Mbps #4 - 3 100Mbps to GigE #5 - 0 300 Mbps to GigE #6 - 18 GigE Spoek to any 25+ Mbps Hub #7 - 3 100 Mbps to GigE dedicated access Spoke to 25+ Mbps Hub | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | With all $1,400 and $2,500 packages we include off site data storage, transport to Internet2 and access to state wide WAN connection. | FALSE | n/a | Next quarter we plan to turn-up of all the major DWDM network segments, and make significant progress on the remaining fiber miles to be constructed in the project. All acceptances have been signed. Mileage in Q1 will be slight due to weather. We do not expect to sign any broadband wholesaler/last mile provider agreements before March 31, 2014 nor do we expect to connect any additional CAI's | Vermont Telephone Company, Inc. | Our team continues to hold weekly meetings to discuss make ready delays, construction progress, electronic installation progress, community anchor connections, and any other topics that needs to be addressed. Due to the weather we have essentially halted construction in 4Q13. Partial segments needed to be addressed individually with the pole owners so that we could progress along toward completion. We have only 9 easements left to obtain to finalize a segment in the northern portion of the state. Our biggest hurdle at this point is to get make ready licenses in time to construct. | The granting of our AAR GOL#2482645 will enable us to complete our project in the most meaningful manner for all previously underserved Vermonters. | TRUE
NT10BIX5570086 | 2010 | Q4 | Q4 - 2010 | Quarterly Activities: Members of the project team attended the Broadband Technology Opportunities Program Recipient Post-Award Workshop in Herndon, Virginia; collaborated with other award recipients to analyze a potential overlap situation in Superior, Wisconsin and submitted report on ways to avoid duplication of services in that area; continued working with contractor to complete required Environmental Assessment and have submitted Cultural Resources literature reviews to the Wisconsin and Minnesota State Historic Preservation Offices, continued working with Departments of Natural Resources and have received approval from the United States Fish and Wildlife Service to proceed with the project as designed, continued working with affected federally-recognized tribes on potential disturbances as a result of this project; completed and submitted Environmental Assessment timeline to the Federal Program Officer for review; assessed potential project modification and discussed best way to mitigate changes with the Federal Program Officer; continued infrastructure analysis and implementation of modified/adjusted financial, sales, audit and contract processes to more closely align with federal program standards. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | N/A | N/A | No variance | 0 | 3 | 0 | N/A | Upon completion, this project will provide 100Mg to 10G lit capacity as well as leased dark fiber. Enventis is currently negotiating agreements and final pricing with three wholesale customers. We continue to reassess the broader retail market to determine competitive rates and standard pricing for potential retail customers. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Current design intends to provide from 100Mg to 10Gig of service to all service providers at all sites. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Current design intends to provide either dark fiber drop (either as a POP or POI) or 100Mg of service to all Community Anchor Institution sites. | 0 | 0 | 0 | 0 | 0 | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | 0 | 0 | 0 | 0 | 0 | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | N/A | FALSE | N/A | â€¢ Initiate permitting & obtain easements for new fiber construction between Twin Cities-Duluth, between Brainerd â€“ Moorhead, and for all laterals. â€¢ Complete Environmental Assessment â€¢ Continue route design â€¢ Initiate RFP for contractors to build routes and laterals â€¢ Initiate bill of materials to order Outside Plant equipment for Twin Cities-Duluth corridor and all laterals | Enventis Telecom, Inc. | N/A | We expect to have received a FONSI (Finding of No Significant Impact) by this quarter. If not, it may impact our progress by delaying the start of construction. If we require further follow up with the State Historic Preservation Office or with the tribal office, this may impact the start of construction. We do not expect either of these situations to arise. | TRUE
NT10BIX5570086 | 2011 | Q1 | Q1 - 2011 | Quarterly Activities: Enventis continued working to align internal processes with program requirements; began seeking out real estate along the route; contacted Round 1 Rural Utilities Service recipient on potential collaboration opportunities; researched all federally-funded network projects in network service area to determine if any overlap exists then initiated contact with each project lead and documented results; assessed potential joint trenching opportunity; received approval on a joint build proposal to address an overlap in Superior, WI; continued working with project partners to confirm sites still of interest; received Environmental Assessment Comment Matrix and continued working with contractor to complete and submit required response; working to complete all tribal consultations; received concurrence letter from Wisconsin State Historical Preservation Office; launched construction planning procedures including route and site assessments; applied for permits along planned construction route; began development of Request for Proposal forms for construction contractors; continued working with Departments of Natural Resources to address concerns related to protected species and wetlands. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | N/A | N/A | No Variance | 0 | 3 | 0 | N/A | Upon completion, this project will provide 100Mg to 10G lit capacity as well as leased dark fiber. Enventis is currently negotiating agreements and final pricing with three wholesale customers. We continue to reassess the broader retail market to determine competitive rates and standard pricing for potential retail customers. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Current design intends to provide from 100Mg to 10Gig of service to all service providers at all sites. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Current design intends to provide either dark fiber drop (either as a POP or POI) or 100Mg of service to all Community Anchor Institution sites. | 0 | 0 | 0 | 0 | 0 | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | 0 | 0 | 0 | 0 | 0 | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | N/A | FALSE | N/A | Finalize permitting & obtain easements for new fiber construction between Twin Cities-Duluth. Receive FONSI (Finding of No Significant Impact) from the Environmental Assessment. Complete and issue RFP for contractors to build routes and laterals. Review responses and award contracts for construction. Complete and issue RFP for equipment and materials, review responses and award contracts. Order equipment and materials for Twin Cities-Duluth corridor and all laterals. Begin construction on Twin Cities-Duluth corridor and laterals. Purchase land for Point of Presence buildings | Enventis Telecom, Inc. | N/A | N/A | TRUE
NT10BIX5570086 | 2011 | Q2 | Q2 - 2011 | Enventis continued working to align internal processes with program requirements; closed on real estate along the route; collaborated with Round 1 Rural Utilities Service recipient on potential joint opportunities; assessed potential joint trenching opportunity and options; continued working with project partners to confirm sites still of interest; completed Environmental Assessment Comment Matrix; completed tribal consultations; submitted final Environmental Assessment; Received FONSI; continued construction planning procedures including route and site assessments; applied for permits along planned construction route; awarded construction and materials contracts; placed first materials order; began development of Request for Proposal forms for equipment vendors and general contractors for site preparation; continued working with Departments of Natural Resources to address concerns related to protected species and wetlands; analyzed and developed community outreach strategy; completed grants management audit and implemented process revisions; completed draw down process and documentation; initiated and received first draw down of federal funds. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | We were unable to begin construction this quarter due to the delay in receiving our FONSI. We have it now and will work to catch up to plan. | n/a | n/a | No variance | 0 | 2 | 0 | N/A | Upon completion, this project will provide 100Mg to 10G lit capacity as well as leased dark fiber. Enventis is currently negotiating agreements and final pricing with two wholesale customers. We continue to reassess the broader retail market to determine competitive rates and standard pricing for potential retail customers. | N/A | 0 | 0 | 0 | 0 | Enventis is in active contract negotiations with our project partners for services on the Stimulus-funded network. These negotiations were delayed as our partners were hesitant to continue moving forward in the midst of the State of MN budget crisis and resulting shutdown. Additionally, they are still finalizing all options for CAI sites. It was mutually agreed that we would resume contract negotiations upon a resolution to the State of MN budget crisis as well as final selection of CAI sites. Negotiations have since resumed, and Enventis is working to complete both open contracts as soon as possible, but prior to year end. Enventis is actively pursuing other potential wholesale and last mile service providers to engage in negotiations for increased access resulting from the expanded network. | No variance | This variance is due to budget constraints related to the state budget crisis and expected state government shutdown. | Current design intends to provide from 100Mg to 10Gig of service to all service providers at all sites. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | Current design intends to provide either dark fiber drop (either as POP or POI) or 100Mg of service to all Community Anchor Institution sites. | 0 | 0 | 0 | 0 | 0 | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | 0 | 0 | 0 | 0 | 0 | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | We will not be offering last mile service to homes and businesses | N/A | FALSE | N/A | Receive & stage outside plant equipment for Twin Cities-Duluth fiber construction Refine inside and outside plant design & equipment requirements for new fiber construction: Brainerd â€“ Moorhead Initiate bill of materials to order Outside Plant equipment for Brainerd - Moorhead corridor Initiate outside plant construction for Twin Cities-Duluth fiber construction Initiate outside plant construction for laterals Initiate bill of materials & order transport equipment for Twin Cities-Duluth corridor Complete installation/ make ready of regen buildings for Twin-Cities-Duluth corridor Begin Customer Premise equipment installation for laterals Award contract for audit firm and initiate audit. The Groundbreaking Ceremony is scheduled for August 25, 2011 in Duluth, MN and we have invited a number of public and elected officials, media contacts, local business leaders, customers, and a representative from NTIA. Community-specific datasheets have been created for a number of new communities along our route. This information will be sent to local media contacts and community leaders with a letter introducing Enventis and the GMBC project and will arrive approximately 30 days in advance of construction crews beginning work in that area. | Enventis Telecom, Inc. | The State of Minnesota has been in a budget crisis and the budgets for two of our partners are directly related to the State budget. This has resulted in difficulty with getting CAI contracts signed. In anticipation of a State government shut down, some offices were making preparations for shutdown. This caused delays in permit processing. Permitting may be up to two months behind due to the State of MN shutdown. The State permit offices stopped accepting applications on June 18, 2011 in anticipation of the shutdown. We have the necessary permits required to begin the build but had originally planned to have all permits in place prior to starting construction. We expect to have the remaining permits in hand in advance of when the construction crew is ready to work in those areas. If these are further delayed, inclement weather could cause risk to completion of this yearâ€™s build, although we do not anticipate further delays. We do not expect these delays to affect the route build planned for next yearâ€™s construction. | The State of Minnesota government did shut down for nearly three weeks due to the budget crisis. Since the budgets for two of our partners are directly tied to the state budget, we anticipate continued difficulty and delays in getting signed contracts for the CAI's. We also anticipate continued delays in permit processing which may result in delays in obtaining permits, right of ways and the actual construction. Although we have experienced delays in beginning construction, we are confident that we will be able to meet the 67% milestone related to spending funds. The Brainerd to Moorhead route and lateral builds will likely not be complete by June 20, 2012, however we will have ordered and paid for the materials and equipment by that time. | TRUE
NT10BIX5570086 | 2011 | Q3 | Q3 - 2011 | Quarterly Activities: Enventis began construction and has completed 116 miles to date. This includes completing a bore under the St. Louis Bay between Superior, Wisconsin and Duluth, Minnesota and completing bores under the Nemadji and Black Rivers. Began blowing fiber into the ducts and have completed 175,000 feet to date. Awarded bids for audit work, optical equipment and site preparation work. Completed concrete work and building installation for two Point of Presence locations. Held a groundbreaking ceremony which was attended by local, State and Federal officials. Conducted first program audit. Initiated analysis for Environmental Assessment addendum. Prepared filings documenting federal interest in land in two counties. Collaborated with UW-Extension on joint build segment in Superior, WI; submitted sole source filing for joint build. Continued to work with project partners to narrow down Community Anchor Institutions (CAIs) of interest. Collaborated with Merit Network on joint build segment in Duluth, Minnesota and Superior, Wisconsin; working to finalize related contractual agreements. | 116 | 0 | 0 | 0 | 116 | 0 | 0 | 0 | N/A-ahead of projection | No variance | No variance | No variance | N/A-ahead of projection | N/A | N/A | No CAIs connected this quarter | 0 | 4 | 0 | N/A | Upon completion, this project will provide 100Mg to 10G lit capacity as well as leased dark fiber. We continue to reassess the broader retail market to determine competitive rates and standard pricing for potential retail customers. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | Enventis had been in active negotiations with several providers on dark fiber agreements. Updated NTIA guidance on the use of IRUs required a modification to the templates we had been using which extended the internal and customer review processes. We continue to work through the negotiation process with these entities using the updated contract templates. | Current design intends to provide from 100Mg to 10Gig of service to all service providers at all sites. | 0 | 0 | 0 | 0 | Enventis continues to work with our project partners, the State of Minnesota and Mayo Clinic, to identify CAIs that are still of interest to them. These partners had identified a number of sites for inclusion in the original application that Enventis verified before including in the baseline plan. Since the baseline was submitted, the State of MN has experienced severe budget cuts and Mayo Clinic has been reassessing their procurement policies, network priorities and site requirements. Enventis is working with each partner to revalidate the CAI detail in light of these changes and continues to seek out and qualify additional CAIs along the route. We have also reached out to a number of additional firms in the medical community to determine their needs and to assess if they match within the program requirements and could be used as alternative CAIs. | N/A | N/A | Current design intends to provide from 100Mg to 10Gig of service to all service providers at all sites. | 0 | 0 | 0 | 0 | 0 | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | 0 | 0 | 0 | 0 | 0 | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | N/A | FALSE | N/A | Complete installation/make ready the Point of Presence (POP) sites on our Twin Cities-Duluth route. Prepare Environmental Assessment addendum for submission. Receive and stage transport equipment for Twin Cities-Duluth corridor. Continue construction as long as weather permits (frost, ground freeze and snow will halt construction). We expect to have over 150 miles constructed by the end of next quarter. Complete bill of materials and order outside plant materials for the Brainerd route. Begin customer premise equipment installation for laterals. Attend Mid-course conference in Cleveland, Ohio. Submit first year audit. Complete Federal Program Officer (FPO) site review. Continue working with project partners to revalidate and contract CAI sites. Launch marketing campaign to seek out new CAIs near the long haul routes and build relationships with broadband wholesalers and last mile providers in the project area. | Enventis Telecom, Inc. | Due to the State of Minnesota shutdown there were delays in permits which resulted in a trickle down effect for delays.During this time all State agencies were unresponsive. While the official shutdown occurred on July 1, most agencies quit responding on June 18th. Our ability to exceed our build target was due to the number of segment miles impacted. We were fortunate that areas already permitted included many miles of the project, allowing us to move construction crews and work where we could. Once permit approvals were received we were able to go back and fill in the â€œgapsâ€. We continue working to catch up to planned milestones. | We started construction later than originally planned and experienced a number of delays in the permitting process, in part due to the State of Minnesota shut down. We plan to continue construction and work to meet milestones, but we may be hindered due to winter weather and frost. We do not expect these delays to affect the route build planned for next year's construction. An EA addendum is being prepared for the remaining route. Permits cannot be applied for until we are cleared for a construction path so we can submit our applications to the various permitting entities. We expect approval of the EA addendum in Year 2, Q3 with permits to follow shortly after that. All year 1 activity will have subsided as the winter sets in. In the mean time all electronics will start arriving and be invoiced which will increase spending during times of no construction spending. We expect to be at or exceed the 67% threshold by the end of 8 quarters. | TRUE
NT10BIX5570086 | 2011 | Q4 | Q4 - 2011 | Quarterly Activities: Enventis continued construction and has completed 157 miles to date. Began installation and turn up of optical equipment in three locations. Completed concrete work and building installation for two Point of Presence locations. Completed analysis for Environmental Assessment addendum. Collaborated with UW-Extension on joint build segment in Superior, WI; submitted sole source filing for joint build. Continued to work with project partners to narrow down CAIs of interest. Completed contractual agreements for joint build segments with UW-Extension and Merit Network in Duluth, Minnesota and Superior, Wisconsin. Completed conduit purchase agreement. Completed For-Profit Audit Requirement. Submitted two federal interest filings for land purchases. | 157 | 0 | 0 | 0 | 157 | 0 | 0 | 42 | This is just a few miles behind baseline. | N/A | N/A | N/A | This is just slightly behind baseline. | N/A | N/A | This number is ahead of our baseline due to definition. This represents the number of Point of Presence buildings as well as the number of handholes that have been placed on the route in anticipation of potential CAI's connection opportunities. | 0 | 4 | 0 | N/A | Upon completion, this project will provide 100Mg to 10G lit capacity as well as leased dark fiber. Wholesale pricing methodology is further explained on the attached. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | Enventis continues to negotiate four dark fiber agreements with three separate providers. | Current design intends to provide from 100Mg to 10Gig of services to all service providers at all sites. | 1 | 0 | 1 | 1 | Enventis continues to work with our project partners, the State of Minnesota and Mayo Clinic to re-prioritize their requested CAI sites in light of recent budget revisions. | N/A | We have increased the speed of a Mayo Clinic health care site from a PTP T1 to 50mbps ethernet service. | We are providing 50mbps service to one site. Current design intends to provide from 100Mg to 10Gig of services at all locations. | 0 | 0 | 0 | 0 | 0 | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | 0 | 0 | 0 | 0 | 0 | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | N/A | FALSE | N/A | We plan to submit Qwest augment orders for the Regen sites on our second long haul route. Initiate bill of materials, let and award RFPs for five different types of Customer Premise equipment, contract with selected vendors, and begin ordering Customer Premise equipment for route laterals. Begin Customer Premise equipment installation for laterals. Initiate any remaining permits & obtain easements for new fiber construction on our second long haul route. Initiate permitting & obtain easements for new fiber construction for all laterals. Submit and receive approval of EA addendum. Finalize route design. Refine inside and outside plant design & equipment requirements for new fiber construction on our second long haul route. Initiate outside plant construction for on our second long haul route. Continue negotiating four pending dark fiber agreements. | Enventis Telecom, Inc. | Enventis has encountered a number of challenges in achieving the milestones set on our baseline report particularly in securing contracts for CAI sites. Enventis has two key project partners, the State of Minnesota and Mayo Clinic, each of whom have undergone significant budget adjustments and/or internal re-organizations which have delayed their ability to readily commit to the CAIs identified in the initial application. Enventis continues to diligently pursue CAI commitments and have worked with our project partners to re-prioritize their requested CAI sites in light of recent budget revisions. We reach out to the partners on a weekly basis and continue to reiterate the cost savings and increased speeds made available by this unique program to encourage their participation. The challenge in securing CAIs has perpetuated difficulties in procuring and deploying customer premise equipment. | N/A | TRUE
NT10BIX5570086 | 2012 | Q1 | Q1 - 2012 | Quarterly Activities: Enventis awarded contracts to four distinct vendors for Customer Premise Equipment and one vendor for additional Cisco optical equipment. Two federal interest filings on easements were submitted. Enventis initiated permit, easement and Right of Way requests along the Riverton to Moorhead route and in St. Paul. Two bridge attachments were affixed and splicing continued along the Duluth to St. Paul route. An Environmental Assessment addendum was submitted and approved. The finalization of Community Anchor Institution sites continued. Internal procedures have been further developed and documented for program income, sales tracking, and time entry. A wage conformance request was submitted for verification of internal wages paid to technicians who will be installing equipment along the Stimulus routes. The public relations and community outreach strategy has been updated and additional personnel assigned to support increased marketing activity along the Riverton to Moorhead route. | 176 | 0 | 0 | 0 | 176 | 0 | 0 | 42 | No variance | N/A | N/A | N/A | No variance | N/A | N/A | This number is ahead of our baseline due to definition. This represents the number of Point of Presence buildings as well as the number of handholes that have been placed on the route in anticipation of potential CAI's connection opportunities. | 1 | 4 | 12 | [REDACTED] | Upon completion, this project will provide 100Mg to 10G lit capacity as well as leased dark fiber. We continue to reassess the broader retail market to determine competitive rates and standard pricing for potential retail customers. | N/A | 1 | 0 | 0 | 1 | This number is above baseline. | This number is below our baseline of 2. Enventis continues to pursue opportunities to provide improved access. | Enventis continues to negotiate four dark fiber agreements with three separate providers. | There is one subscriber at 10Gig; Enventis' current design intends to provide from 100Mg to 10Gig of services to all service providers at all sites. | 1 | 0 | 1 | 1 | Enventis continues to work with our project partners, the State of Minnesota and Mayo Clinic to re-prioritize their requested CAI sites in light of recent budget revisions. | Enventis continues to work with our project partners, the State of Minnesota and Mayo Clinic to re-prioritize their requested CAI sites in light of recent budget revisions. | We have increased the speed of a Mayo Clinic health care site from a PTP T1 to 50mbps ethernet service. | We are providing 50mbps service to one site. Current design intends to provide from 100Mg to 10Gig of services at all locations. | 0 | 0 | 0 | 0 | 0 | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | 0 | 0 | 0 | 0 | 0 | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | N/A | FALSE | N/A | â€¢ Complete outside plant fiber construction between Twin Cities-Duluth â€¢ Continue outside plant construction for Brainerd - Moorhead fiber construction â€¢ Initiate bill of materials & order transport equipment for Brainerd - Moorhead corridor â€¢ Expect to have deployed 287 total network miles by the end of next quarter. This is just slightly lower than baseline and is due to longer than anticipated permit completion and delays due to rainy weather. â€¢ Expect to connect at least one (1) CAI for a project partner; will increase sales and marketing efforts along the Duluth - St. Paul corridor in advance of construction completion as part of our normal course of business. â€¢ Expect to complete at least one (1) Agreement with a broadband wholesaler/last mile provider. | Enventis Telecom, Inc. | The main challenge we face is the delay in the timing of securing CAI's. Enventis continues to work with our project partners, the State of Minnesota and Mayo Clinic to re-prioritize their requested CAI sites in light of recent budget revisions. | Enventis is assessing a possible route change along the western middle mile route due to unforeseen permitting issues. The preliminary results of this assessment indicate a second EA addendum may be required. Completing additional EA analysis and working through the federal approval process of this amendment may impact project construction in that area. Enventis has initiated this assessment fairly early on in the process and will work to diligently to move through the analysis and review processes as efficiently as possible. | TRUE
NT10BIX5570086 | 2012 | Q2 | Q2 - 2012 | We have installed and turned up another CAI location. We conducted an extremely thorough project analysis and re-forecasted project milestones and associated budget categories. Enventis has awarded an RFP and contract for optronics equipment along the western route; we have also awarded an RFP for central office equipment and installation and are presently negotiating contract terms. We completed agreements with a telecom service provider for dark fiber and collocation services along the Duluth to Twin Cities route. | 224 | 0 | 0 | 0 | 224 | 0 | 0 | 61 | This is slightly behind baseline. Additional crews are being added and construction is being ramped up in an effort to reach the goal identified on the baseline report. | No variance | No variance | No variance | This is slightly behind baseline. Additional crews are being added and construction is being ramped up in an effort to reach the goal identified on the baseline report. | N/A | N/A | This number is ahead of our baseline due to definition. This represents the number of Point of Presence buildings as well as the number of handholes that have been placed on the route in anticipation of potential CAI connection opportunities. | 2 | 2 | 30 | [REDACTED] | Upon completion, this project will provide 100Mg to 10G lit capacity as well as leased dark fiber. We continue to assess the retail market to determine competitive rates and standard pricing for potential retail customers. | N/A | 2 | 0 | 1 | 1 | This is above baseline | This number is below our baseline. Enventis continues to pursue opportunities to provide improved access. | This number is slightly below baseline, however, we are in active negotiations with two wholesale providers to provide leased dark fiber. | Current design intends to provide from 1Gig to 10Gig of service to all service providers at all sites. | 13 | 12 | 1 | 1 | Enventis continues to work with our project partners, the State of Minnesota and Mayo Clinic to re-prioritize their requested CAI sites in light of recent budget revisions. | Enventis continues to work with our project partners, the State of Minnesota and Mayo Clinic to re-prioritize their requested CAI sites in light of recent budget revisions. | We have increased the speed of a Mayo Clinic health care site from a PTP T1 to 50mbps ethernet service. | Current design intends to provide from 100Mg to 10Gig of services at all locations. | 0 | 0 | 0 | 0 | 0 | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | 0 | 0 | 0 | 0 | 0 | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | We will not be offering last mile service to homes and businesses. | N/A | FALSE | N/A | â€¢ Complete test and turn up of new fiber construction between the Twin Cities - Duluth â€¢ Complete test and turn up of leased dark fiber services to a broadband wholesaler customer â€¢ Complete two leased dark fiber agreements that are presently being negotiated with broadband wholesaler/last mile provider customers. â€¢ Connect 12 additional CAIs â€¢ Complete installation/make ready of Central Office locations â€¢ Complete installation of transport network equipment including buildings and transport facilities for new fiber construction between Twin-Cities-Duluth â€¢ Continue customer premise equipment installation â€¢ Continue outside plant construction for all laterals â€¢ Continue outside plant construction for Brainerd - Moorhead middle mile fiber route using additional crews to help accelerate the pace. By the end of this quarter we expect to have deployed a total of 375 miles. | Enventis Telecom, Inc. | Enventis continues to face challenges in contracting for CAI sites. Our project partners are working through budget constraints and employee restructuring which has delayed their ability to commit to CAIs contractually. We are collaborating with our partners to provide competitive rates that will fit their reduced budgets and reaching out to new decision makers within these organizations to keep this project at the forefront of their initiatives. Concurrently, we are building to the CAI sites and placing handholes with the intent to connect lateral extensions directly into the building when we have the partners' contractual commitment and approval to build in. Enventis is challenged by an abbreviated construction season due to weather concerns (frost, ground freeze, snow, etc.) and have forecasted and scheduled anticipated lateral construction work to account for this. Enventis had submitted a route change request for a minor route deviation along our western route. BTOP has responded and we are working to complete the required reviews. This site is directly in the middle of our western route construction and failure to secure approvals from BTOP in a timely fashion could result in a delay to our construction schedule. Enventis is appreciative of the assistance provided by BTOP thus far and we are hopeful for a quick resolution to this request. | We are pending approval for a slight route change which requires SHPO consultation. A delay in this could result in a delay of completion of our western middle mile route. We continue to have difficulty in securing CAI contracts which has the potential to hinder equipment procurement and deployment and keep us below baseline in those areas. | TRUE
NT10BIX5570086 | 2012 | Q3 | Q3 - 2012 | Construction is continuing on our western route and is completed on the Duluth to Twin Cities route. Six CAIs have been installed. Submitted and received approval on a small route change. Completed the site visit with our FPO. Installed equipment to augment two collocations. Community outreach continues with letters and data sheets being sent to cities we are entering. We are working with regional economic development agencies to promote our network and the new segments constructed through the BTOP program. We continue reaching out to our project partners to finalize CAIs and are working to incorporate anticipated locations into our construction plan. | 185 | 0 | 0 | 0 | 185 | 0 | 0 | 67 | This varies from previous reports and baseline due to a change in how miles are reported. In addition to the miles reported, we have 134 miles of conduit placed. | No variance | No variance | No variance | This varies from previous reports and baseline due to a change in how miles are reported. In addition to the miles reported, we have 134 miles of conduit placed. | No variance | No variance | This number is slightly ahead of baseline. | 4 | 2 | 60 | [REDACTED] | Upon completion, this project will provide 100Mg to 10G lit capacity as well as leased dark fiber. We continue to assess the retail market to determine competitive rates and standard pricing for potential retail customers. | N/A | 3 | 2 | 1 | 1 | This is above baseline. | This number is below our baseline. Enventis continues to pursue opportunities to provide improved access. | This number is slightly below baseline, however, we are in active negotiations with two wholesale providers to provide leased dark fiber. | Enventis is providing dark fiber (1), collocation services (1), 10G wavelengths (1), 100M Ethernet (2) and 500M Ethernet (1) services. | 6 | 6 | 0 | 6 | There are an additional 12 sites where the Right of Way or property hand hole is built to within Â½ block of CAI location. This is lower than baseline due to the requirement to report only direct connect sites. The 12 sites with close hand holes are along the east route that have duct and fiber built to the hand hole. Enventis continues to work with our project partners to re-prioritize their requested CAI sites. | There are an additional 12 sites where the Right of Way or property hand hole is built to within Â½ block of CAI location. This is lower than baseline due to requirement to report only direct connect sites. The 12 sites with close hand holes are along the east route that have duct and fiber built to the hand hole. Enventis continues to work with our project partners to re-prioritize their requested CAI sites. | No optronics only sites have been upgraded yet. | Current design intends to provide from 100Mg to 10Gig of services at all locations. | 0 | 0 | 0 | 0 | 0 | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | 0 | 0 | 0 | 0 | 0 | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | N/A | FALSE | N/A | â€¢ Complete outside plant construction for Brainerd-Moorhead fiber route â€¢ Continue outside plant construction for all laterals â€¢ Continue customer premise equipment installation â€¢ Receive & stage transport equipment for Brainerd-Moorhead corridor â€¢ Deploy an additional 156 miles of fiber â€¢ Directly connect 10 cumulative CAIs â€¢ Complete 10 cumulative broadband wholesaler/last mile provider agreements | Enventis Telecom, Inc. | Enventis continues to face challenges in contracting for CAI sites. Our project partners are working through budget constraints and employee restructuring which has delayed their ability to commit to CAIs contractually. We are collaborating with our partners to provide competitive rates that will fit their reduced budgets and reaching out to new decision makers within these organizations to keep this project at the forefront of their initiatives. Concurrently, we are building to the CAI sites and placing handholes with the intent to connect lateral extensions directly into the building when we have the partners' contractual commitment and approval to build in. Enventis is challenged by an abbreviated construction season due to weather concerns (frost, ground freeze, snow, etc.) and have forecasted and scheduled anticipated lateral construction work to account for this. Enventis is appreciative of the assistance provided by BTOP thus far. | We continue to have difficulty securing CAI contracts. This has the potential to hinder equipment procurement and deployment and keep us below baseline in those areas. We continue to work with our partners and other potential CAIs. | TRUE
NT10BIX5570086 | 2012 | Q4 | Q4 - 2012 | Construction is completed on the western middle mile route. Three CAIs have been installed. Completed follow up activities related to the FPO Site Visit. Updated several project policies to more accurately describe processes related to Program Income, Procurement and Grants Management. We continue collaborating with project partners to finalize CAIs and are working to incorporate anticipated locations into the final construction period which will begin immediately upon spring thaw. | 384 | 0 | 0 | 0 | 384 | 0 | 0 | 124 | This is slightly behind baseline mainly due to the number of CAI's installed to date. | No variance | No variance | No variance | This is slightly behind baseline mainly due to the number of CAI's installed to date. | No variance | No variance | Slightly ahead of baseline | 11 | 2 | 23 | [REDACTED] | Upon completion, this project will provide 100Mg to 10G lit capacity as well as leased dark fiber. We continue to assess the retail market to determine competitive rates and standard pricing for potential retail customers. | N/A | 6 | 2 | 1 | 1 | This is above baseline. | This number is below our baseline. Enventis continues to pursue opportunities to provide improved access. | This number is slightly below baseline, however, Enventis is in active negotiations with two broadband wholesalers to provide dark fiber services. | Enventis is providing dark fiber (1), collocation services (1), 10G wavelengths (2), 100M Ethernet (5), 50M Ethernet (8) and 500M Ethernet (1) services. | 9 | 9 | 0 | 9 | There are an additional 31 sites where the Right of Way or property hand hole is built to within Â½ block of CAI location. This is lower than baseline due to the requirement to report only direct connect sites. The 31 sites with close hand holes are along the middle mile routes that have duct and fiber built to the hand hole. Enventis continues to work with our project partners to re-prioritize their requested CAI sites. | There are an additional 31 sites where the Right of Way or property hand hole is built to within Â½ block of CAI location. This is lower than baseline due to the requirement to report only direct connect sites. The 31 sites with close hand holes are along the middle mile routes that have duct and fiber built to the hand hole. Enventis continues to work with our project partners to re-prioritize their requested CAI sites. | No optronics only sites have been upgraded yet. | Current design intends to provide from 100Mg to 10Gig of services at all locations. | 0 | 0 | 0 | 0 | 0 | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | 0 | 0 | 0 | 0 | 0 | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | N/A | FALSE | N/A | â€¢ Complete testing and turn up of Brainerd-Moorhead middle mile fiber route â€¢ Due to weather constraints and inability to do construction in the winter we do not anticipate deploying any route miles this quarter. â€¢ Continue customer premise equipment installation â€¢ Directly connect 10 cumulative CAIs â€¢ Complete 13 cumulative broadband wholesaler/last mile provider agreements | Enventis Telecom, Inc. | Enventis continues to face challenges in contracting for CAI sites. We are collaborating with our partners to provide competitive rates that will fit their reduced budgets and reaching out to all decision makers within these organizations to keep this project at the forefront of their priorities. We have continued to include CAI sites in our construction plan and are placing handholes in these locations with the intent to connect lateral extensions directly into the building when we have received contractual commitments and approval to build in. Enventis is challenged by an abbreviated construction season due to weather concerns (frost, ground freeze, snow, etc.) and have forecasted and scheduled anticipated lateral construction work to account for this. | We continue to have difficulty securing CAI contracts. This has the potential to hinder equipment procurement and deployment and keep us below baseline in those areas. The planned acquisition of Community Anchor Institutions (CAI) has been slowed by delays in procurement from the State of Minnesotaâ€™s Office of Enterprise Technology (OET). Requests For Proposal (RFPs) are required by state law and were delayed in 2012 with the initial RFP being rescinded and later re-issued in the fall of 2012. Out of this RFP process Enventis was selected as a certified vendor for its Statewide Access & Backbone Network contract. Enventis received the first quote requests under this contract in late January and has received more since then. Enventis is hopeful that agreements will be awarded out of this process, including to CAI locations, beginning in late February and continuing into March, April, and May of 2013.We continue to work with our partners and other potential CAIs. | TRUE
NT10BIX5570086 | 2013 | Q1 | Q1 - 2013 | Completed construction, testing and turn up of middle mile route segment from Riverton to Moorhead. Signed a dark fiber and collocation agreement with a last mile service provider. Signed additional agreements with wholesale service providers. Two additional CAIs were turned up. Worked on designs and submitted permit applications in order to be prepared for construction immediately upon spring thaw. We continue collaborating with project partners to finalize CAIs. | 384 | 0 | 0 | 0 | 384 | 0 | 0 | 124 | This is slightly behind baseline mainly due to the number of CAIs installed to date. We were unable to do any construction this quarter due to weather constraints. | No variance | No variance | No variance | This is slightly behind baseline mainly due to the number of CAIs installed to date. | No variance | No variance | Slightly ahead of baseline | 21 | 1 | 19 | [REDACTED] | Upon completion, this project will provide 100Mg to 10G lit capacity as well as leased dark fiber. We continue to assess the retail market to determine competitive rates and standard pricing for potential retail customers. | N/A | 8 | 4 | 2 | 1 | This is above baseline | This is below baseline. We continue working with providers. | This meets the baseline plan. | Enventis is providing dark fiber (2), collocation services (2), DS3 (3), 1G wavelengths (4), 10G wavelengths (4), 10M Ethernet (1), 50M Ethernet (6), 100M Ethernet (5), 200M Ethernet (1), 250M Ethernet (2), and 500M Ethernet (1) services. Enventis has secured some agreements that document multiple services (services may be New or Improved Access) on one agreement and multiple agreements with the same provider. This accounts for the difference in reported subscribers/providers/agreements as noted in this section and question 5.b. | 11 | 11 | 0 | 11 | There are an additional 36 sites where the Right of Way or property line hand hole is built to within Â½ block of CAI location. This is lower than baseline due to the requirement to report only direct connect sites. The 36 sites have duct and fiber built to the hand hole. There are currently an additional 12 sites in 2Q13 to be built to the property line hand hole. Enventis continues to work with our project partners to re-prioritize their requested CAI sites. | There are an additional 36 sites where the Right of Way or property line hand hole is built to within Â½ block of CAI location. This is lower than baseline due to the requirement to report only direct connect sites. The 36 sites have duct and fiber built to the hand hole with the intent that we will directly connect into the site once we have obtained a signed contract and have approval to access private property and/or Right of Way. There are an additional 12 sites in 2Q13 to be built to the property line hand hole. Enventis continues to work with our project partners to re-prioritize their requested CAI sites. | No optronics only sites have been upgraded yet. | Current design intends to provide from 100Mg to 10Gig of services at all locations. | 0 | 0 | 0 | 0 | 0 | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | 0 | 0 | 0 | 0 | 0 | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | Enventis will not be offering last mile service to homes and businesses. | N/A | FALSE | N/A | We will continue construction on CAI laterals and continue turning up equipment. We will continue working with partners and other customers to get signed up for more services. We will begin addressing items for the close-out process. We plan to construct an additional 18 miles for CAI laterals. We plan to directly connect 16 cumulative CAIs. We plan to complete 23 cumulative broadband wholesaler/last mile provider agreements | Enventis Telecom, Inc. | Enventis continues to face challenges in contracting with CAI sites. We are collaborating with our partners to provide competitive rates that will fit their reduced budgets and reaching out to all decision makers within these organizations to keep this project at the forefront of their priorities. We have continued to include CAI sites in our construction plan and are placing handholes in these locations with the intent to connect lateral extensions directly into the building when we have received contractual committments and approval to build in. Enventis is challenged by an abbreviated construction season due to weather concerns, (frost, ground freeze, snow, etc.) and have forecasted and scheduled anticipated lateral construction work to account for this. | We continue to have difficulty securing CAI contracts. This has the potential to hinder equipment procurement and deployment and keep us below baseline in those areas. The planned acquisition of Community Anchor Institutions (CAI) has been slowed by delays in procurement from the State of Minnesota's Office of Enterprise Technology. Enventis has responded to request for quotes and are hopeful that agreements will be awarded, including CAI locations. We continue to work with our partners and other potential CAIs. | TRUE
NT10BIX5570086 | 2013 | Q2 | Q2 - 2013 | Completed construction to additional CAI sites. Signed additional agreements with wholesale service providers. Initiated project close out procedures. | 387 | 0 | 0 | 0 | 387 | 0 | 0 | 153 | This will vary from baseline due to route adjustments and CAI changes. | No variance | No variance | No variance | This will vary from baseline due to route adjustments and CAI changes. | No variance | No variance | This number is above baseline | 36 | 1 | 27 | [REDACTED] | Upon completion, this project will provide 100Mg to 10G lit capacity as well as leased dark fiber. We continue to assess the retail market to determine competitive rates and standard pricing for potential retail customers. | N/A | 11 | 5 | 3 | 1 | This is above baseline. | This is below baseline. We continue working with providers. | This is above baseline. | Enventis is providing dark fiber (8), collocation services (2), DS3 (3), 1G wavelengths (4), 10G wavelengths (5), 10M Ethernet (3), 50M Ethernet (5), 100M Ethernet (12), 200M Ethernet (1), 250M Ethernet (2) and 500M Ethernet (1) services. Enventis has secured some agreements that document multiple services (services may be New or Improved Access) on one agreement and multiple agreements with the same provider. This accounts for the difference in reported subscribers/providers/agreements as noted in this section and question 5.b. | 16 | 13 | 3 | 16 | There are an additional 40 sites where the Right of Way or property line hand hole is built to within Â½ block of CAI location. This is lower than baseline due to the requirement to report only direct connect sites. The 40 sites have duct and fiber built to the hand hole. | There are an additional 40 sites where the Right of Way or property line hand hole is built to within Â½ block of CAI location. This is lower than baseline due to the requirement to report only direct connect sites. The 40 sites have duct and fiber built to the hand hole. | This is above baseline | Current design intends to provide from 100Mg to 10Gig of services at all locations. | 0 | 0 | 0 | 0 | 0 | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | 0 | 0 | 0 | 0 | 0 | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | N/A | FALSE | N/A | Complete construction on all planned lateral builds for a total of 404 miles We will directly connect 32 cumulative CAI's We will continue to work with partners and other customers to get signed up for more services We will continue to address close-out process | Enventis Telecom, Inc. | Enventis continues to face challenges in contracting with CAI sites. We are collaborating with our partners to provide competitive rates that will fit their reduced budgets and reaching out to all decision makers within these organizations to keep this project at the forefront of their priorities. We have continued to include CAI sites in our construction plan and are placing handholes in these locations with the intent to connect lateral extensions directly into the building when we have received contractual committments and approval to build in. Enventis is challenged by an abbreviated construction season due to weather concerns, (frost, ground freeze, snow, etc.) and have forecasted and scheduled anticipated lateral construction work to account for this. | We plan to complete our project by the end of our award period. | TRUE
NT10BIX5570086 | 2013 | Q3 | Q3 - 2013 | Completed final construction on the remaining laterals builds and CAI's. Shifted project focus to close out activities. | 405 | 0 | 0 | 0 | 405 | 0 | 0 | 173 | This varies slightly from baseline due to route adjustments and CAI changes. | No variance | No variance | No variance | This varies slightly from baseline due to route adjustments and CAI changes. | No variance | No variance | This is above baseline | 36 | 0 | 27 | Enventis has secured multiple agreements with some providers. Additionally, we have secured some agreements that document multiple services (services may be New or Improved Access) on one agreement. To date, Enventis has completed 36 agreements with 15 providers including Verizon Wireless (9), AT&T (1), Zayo (2), WIN (2), Lakes PC (1), Sprint (1), MND (1), SDN (1), Qwest QCC (3), Verizon Business (2), State of MN OET (9), Cooperative Network Services (1), Cooperative Light & Power (1), XO (1), Compudyne (1). | This project provides 50Mg to 10G lit capacity as well as leased dark fiber and collocation services. | N/A | 11 | 5 | 3 | 1 | This is above baseline. | This is below baseline. | This is above baseline. | Enventis is providing dark fiber (8), collocation services (2), DS3 (3), 1G wavelengths (4), 10G wavelengths (5), 10M Ethernet (3), 50M Ethernet (5), 100M Ethernet (12), 200M Ethernet (1), 250M Ethernet (2) and 500M Ethernet (1) services. Enventis has secured some agreements that document multiple services (services may be New or Improved Access) on one agreement and multiple agreements with the same provider. This accounts for the difference in reported subscribers/providers/agreements as noted in this section and question 5.b. | 34 | 27 | 7 | 34 | There are an additional 40 sites where the Right of Way or property line hand hole is built to within Â½ block of CAI location. This is lower than baseline due to the requirement to report only direct connect sites. The 40 sites have duct and fiber built to the hand hole. | There are an additional 40 sites where the Right of Way or property line hand hole is built to within Â½ block of CAI location. This is lower than baseline due to the requirement to report only direct connect sites. The 40 sites have duct and fiber built to the hand hole. | This is above baseline | Current design intends to provide from 100Mg to 10Gig of services at all locations. | 0 | 0 | 0 | 0 | 0 | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | 0 | 0 | 0 | 0 | 0 | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | Enventis will not be offering last mile service to homes and businesses | N/A | FALSE | N/A | All project construction and close out tasks other than the final audit are complete. | Enventis Telecom, Inc. | Due to cost savings, most of the milestones were completed for less cost than originally expected. | N/A | TRUE
NT10BIX5570087 | 2010 | Q4 | Q4 - 2010 | Bids were received in response to the issuance of the Environmental Assessment RFP, and an environmental consulting firm was selected to perform the Environmental Assessment for 7280 An RFP was issued for the Engineering portion of the project and an engineering pre-bid meeting was conducted on October 25th. Five companies responded with bids to this RFP. All bids were rejected and a revised Engineering RFP was issued to the five bidders. The reissued RFP was to redress the field engineering rates and to allow for bids on three (3) bridge attachments that will be required under this project. As initial work on the EA began, a desk review and some preliminary consultations were conducted. A preliminary engineering design was completed in November to aid in the completion of the EA and in the reissue of the RFP. The draft EA was submitted to the NTIA on 12-31-10 to fulfill the Special Award Condition (SAC). In December, MBC attended a meeting in Newport News, VA with the Virginia Marine Resources Commission to review all of MBCâ€™s grant projects and to discuss requirements for joint permits. A permit application is being compiled and will be submitted to the US Army Corps of Engineers and the VMRC for permits to cross Virginia water resources. The proposed locations for the four (4) interconnection points have been determined and work is being done on surveys, permits, and zoning approvals for these sites. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10 MBPS - 100 MBPS - OPEN ACCESS | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 10 MBPS - 100 MBPS - OPEN ACCESS | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 MBPS - 100 MBPS - OPEN ACCESS | N/A | FALSE | N/A | â€¢ Select an Engineering firm to complete the field engineering and submit permits â€¢ Draft and have signed the Engineering Services contract â€¢ Submit the Final EA to the NTIA â€¢ Gain approval of Interconnection point permits (4) â€¢ Submit other required permits â€¢ Compile a list of perspective construction vendors â€¢ Prepare the Construction and Procurement RFP | Mid-Atlantic Broadband Cooperative | During preliminary engineering, it was discovered that there will be at least three (3) large bodies of water to cross via new bridge attachment designs. we re-bid the detailed engineering & permitting to obtain new bids based on this information. This pushed our design and permitting activities into Y1Q3. | â€¢ Weather could be a hindrance to engineering activities â€¢ Crossing of at least three waterways that will require detailed engineering of bridge attachments and approval by VDOT | TRUE
NT10BIX5570087 | 2011 | Q1 | Q1 - 2011 | Engineering firms were selected to design the Outside Plant facilities and their respective contracts have been approved and signed. Work in in progress on the design phase of the project. It is approximately 70% complete. MBC has made application to another utility company to lease part of their duct space across four bridges on this project. This will decrease the cost of the crossing substantially when compared to having to construct our own new conduit crossings and will expedite the EA process. We are in the process of preparing the Construction and Procurement RFPs for distribution to vendors next quarter. A preliminary consultation letter was sent to SHPO. The preliminary fiber cable requirements were sent to the cable manufacturer to aid in their scheduling of fiber manufacturing. Work continues on the final draft of the EA, submission of permits to the VMRC and USACE, and easement for the interconnection points. Most of the activity this quarter has been in Southampton County on this project. We do not anticipate having the EA before July 1, 2011. There have been several route changes and design changes that were unforeseen and will require EA changes. Although we submitted the draft EA, consultation with SHPO and other agencies will have to be revisited due to route changes. This may push the EA further into 2011, 3rd quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10 MBPS - 100 MBPS - OPEN ACCESS | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 10 MBPS - 100 MBPS - OPEN ACCESS | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 MBPS - 100 MBPS - OPEN ACCESS | N/A | FALSE | N/A | â€¢ Complete the design of work orders â€¢ Complete the field verification of the work orders â€¢ Issue the Construction and Procurement RFP â€¢ Award the Construction and Procurement contract(s) â€¢ Submit the final EA for approval â€¢ Submit the VMRC and USACE permit â€¢ Complete the site easements and begin site preparation â€¢ Begin the Outside Plant construction phase of this project â€¢ We also face delays because of route changes brought on by municipality requirements, revitalization projects along the route, and the moving of our meet point with a CAI, all of which require re-design efforts. Our cable supplier has recently moved delivery dates out to six months, which is a major obstacle. â€¢ Our mitigation plan is two- fold: Our plan is to perhaps award construction contracts to more than one vendor and to require significantly more construction crews per project segment to catch up. We have already obtained an alternate cable supplier that should be able to meet our cable ship dates requirements. MBC hopes to have the project back on track with the baseline plan in 2011, quarter 4. â€¢ MBC does have some concern about the completion date, but until we have the construction RFPs returned and evaluated, we will not make a decision as to a hard construction schedule or the number of contractors to award. Our plan is to perhaps award to more than one vendor and to require significantly more construction crews per project segment to catch up. | Mid-Atlantic Broadband Cooperative | During the design state, MBC discovered a revitalization project in Smithfield, VA. This will require execution of a lease for underground conduit through the area. Because of Sussex County requirements, the site for one interconnection point will have to be moved, resulting in delay in start of site work. COX Cable moved their "meet" point in Chesapeake, VA requiring re-design of a portion of the backbone. | â€¢ Make up time lost in re-bidding the engineering RFP to include bridge designs to get back on schedule as outlined on Baseline Report. â€¢ Delay in completing design changes will impact EA, permits and construction start dates. â€¢ MBC typically uses matching funds for the purchases of definable assets for the project. We have not gotten to the point of purchasing or constructing definable assets for this project yet. However, starting in 2011, quarter 2, MBC will begin catching up with the 20% matching amount and continue to maintain the 20% match throughout the project. | TRUE
NT10BIX5570087 | 2011 | Q2 | Q2 - 2011 | The engineering design work is 100% completed. The final route through Franklin, VA and Suffolk, VA were determined and approved by the respective cities. This had been a hold-up for the SHPO report, the EA and the VMRC/USACE permits. The SHPO review has been started and is approximately 70% complete. The cable requirements for this project were determined and ordered this quarter. A portion of the transport equipment was ordered and received this quarter. An Easement agreement and a co-location agreement with the town of Surry have been finalized this quarter. Three of the four hut site have been finalized and are in the process of being approved by the proper government entities. All VDOT permits have been prepared. Eighty percent of the pole permits and make ready requests have been prepared. The RFP for construction is being prepared and the final engineering prints are being Quality Controlled. No construction has started. Most of the project activity this quarter has been in Suffolk County. An inspector was hired for this project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from baseline | N/A | N/A | N/A | No variance from baseline | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10 mbps-100mbps- Open Access | 0 | 0 | 0 | 0 | 0 | 10 mbps-100mbps- Open Access | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-100mbps- Open Access | N/A | FALSE | N/A | â€¢ Complete the EA, SHPO consultation and receive the FONSI â€¢ Issue the Construction RFP â€¢ Evaluate bids and select construction vendor(s) â€¢ Order the Hand holes and marker posts â€¢ Start construction â€¢ Complete acquisition of hut sites â€¢ Submit the VMRC and USACE permits â€¢ Prepare bridge attachment work orders (6) and bid them â€¢ Complete utility agreements with the City of Franklin and the City of Suffolk â€¢ Complete lease agreements with another utility for duct space on bridges. | Mid-Atlantic Broadband Cooperative | The difficulty in gaining approval of routes through or around the City of Frankin and the City of Suffolk has caused significant delays in completing the design, completing the SHPO consultations and completing the EA. Since we have routes settled, we are pushing to complete the EA by Y2Q1. | Delivery date on fiber optic cable and delay in approval of EA could impact progress in the next quarter. | TRUE
NT10BIX5570087 | 2011 | Q3 | Q3 - 2011 | There has been a delay in completion of the final State Historic Preservation Office (SHPO) report, thus delaying the Environmental Assessment (EA). The initial report was insufficient and a new consultant has been retained to complete the consultation (80%). The Virginia Marine Resources Commission (VMRC)/U.S. Army Corps of Engineers (USACE) permits have been submitted for approval. We have received approximately 20% of the cable for this project. The majority of the transport equipment has been received this quarter. The remaining hut site was finalized this quarter. All Virginia Dept. of Transportation (VDOT) permits have been prepared. We attended a pre-construction coordinating meeting with VDOT to identify areas that may be in conflict with road construction. The remaining pole permits and makes ready requests have been prepared. The RFP for construction was issued, bids reviewed, and the work was awarded to two contractors. Bids were solicited for the hand holes and marker posts during this quarter. A pre-construction meeting with the awardees was held this quarter. Mid Atlantic Broadband Cooperative (MBC) met with the City of Smithfield to co-ordinate construction activities with their street improvement project. No construction has started pending receipt of the Findings of No Significant Impact (FONSI). Most of the project activity this quarter has been in Greensville County. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Unable to start construction until approval of EA | N/A | N/A | N/A | Unable to start construction until approval of EA | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10 mbps-10mbps; Open Access | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10 mbps-10mbps; Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-10mbps; Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-10mbps; Open Access | N/A | FALSE | N/A | â€¢ Complete the Environmental Assessment (EA), State Historic Preservation Office (SHPO) consultation and receive the Findings of No Significant Impact (FONSI) â€¢ Order the hand holes and marker posts â€¢ Start fiber construction â€¢ Gain approval of bridge designs from Virginia Dept. of Transportation (VDOT) and bid the work â€¢ Complete lease agreements with another utility for duct space on bridges. â€¢ Issue RFP and award contracts for the site work for the 4 interconnections hut sites â€¢ New network miles deployed 8 in Y2Q4 â€¢ No CAI subscribers served (CAIs connected) â€¢ No signed agreements with broadband wholesalers or last mile providers in Y2Q4 | Mid-Atlantic Broadband Cooperative | â€¢ Completion of utility agreement with the City of Franklin and the City of Suffolk â€¢ Receiving the fiber optic cable in a timely manner â€¢ Finalization of a hut site in Windsor being problematic â€¢ Completion of lease agreements with another utility for duct space on bridges â€¢ Completion of SHPO report for the EA (Consultant resigned) | â€¢ Receiving the fiber optic cable in a timely manner â€¢ Completion of lease agreements with another utility for duct space on bridges â€¢ Gaining approval of the State Historic Preservation Office (SHPO) report â€¢ Gaining approval of the EA â€¢ Starting fiber construction in December(weather impact) | TRUE
NT10BIX5570087 | 2011 | Q4 | Q4 - 2011 | The NTIA program officer conducted a field visit on this project on October 24-26, 2011. The SHPO report was approved November 8, 2011. The final draft of the Environmental Assessment was submitted to the NTIA for approval on December 9, 2011. We are awaiting its approval and the issuance of the FONSI. No construction work can begin until the approval is received. We spent $4.3 million on the project in this quarter. The majority of these expenditures were for huts, transport equipment and fiber optic cable. We have received 97% of the cable for this project. The remainder of the transport equipment has been received. Bids for the hand holes and marker posts were evaluated, vendors selected and orders placed during this quarter. We have received three shipments of marker posts and four shipments of hand holes. The RFP for the site work and placement of four huts for interconnection points was issued, with a return date of January 16, 2012. The leases for the use of conduit in Smithfield cannot be completed until the new inner duct is placed by the utility. The majority of the project activity this quarter has been in Isle of Wight County. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Unable to start construction until approval of EA(expected 1-12) | N/A | N/A | N//A | Unable to start construction until approval of EA (expected 1-12) | Unable to start construction until approval of EA (expected 1-12) | Unable to start construction until approval of EA (expected 1-12) | N/A | 1 | 0 | 24 | Town of Surry, VA - Co-location agreement to provide access and transport of internet services offered by the county. | [REDACTED] | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10 mbps-100mbps- Open Access | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10 mbps-100mbps- Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-100mbps- Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-100mbps- Open Access | N/A | FALSE | N/A | â€¢ Gain approval of the EA and receive the FONSI â€¢ Start fiber construction in January â€¢ Place at least 20 miles of fiber in this quarter â€¢ Gain approval of bridge designs from VDOT and bid the work â€¢ Complete lease agreements with another utility for duct space on bridges. â€¢ Award contracts for the site work for the 4 interconnections hut site | Mid-Atlantic Broadband Cooperative | â€¢ Completion of utility agreement with the City of Franklin and the City of Suffolk â€¢ Submission of SHPO report and the final draft of EA to NTIA â€¢ Finalization of a hut site in Windsor was problematic, but accomplished â€¢ Completion of lease agreements with another utility for duct space on bridges | â€¢ Completion of lease agreements with another utility for duct space on bridges â€¢ Starting fiber construction in January(weather impact) â€¢ Deploy 20 new network miles in Y2Q3 because of late start of construction â€¢ No CAI subscribers served (CAIs connected) â€¢ No signed agreements with broadband wholesalers or last mile providers in Y2Q3 | TRUE
NT10BIX5570087 | 2012 | Q1 | Q1 - 2012 | MBC has prepared a budget modification to request that the original budget be modified to redistribute existing budgeted funds to more accurately identify and track actual project expenditures. This request will be sent to the NTIA for approval in the 2nd quarter. The EA was approved and FONSI issued on January 6, 2012. Construction was started on this project on March 8, 2012 after VDOT permits were approved. The contract for the site work for the four interconnection sites on this project was awarded in January, 2012. Work has begun on the Franklin Node site. The RFP for the construction of the six bridge crossing identified on this project was distributed in March, 2012 to four prospective bidders. Replies are due back to MBC in April, 2012. No CAIâ€™s have been passed at this point of construction and no agreements with last mile providers have been signed. We have received 100% of the cable, OSP materials, and transport equipment for this project. All that remains to be ordered is the power equipment. The leases for the use of conduit in Smithfield cannot be completed until the new inner duct is placed by the utility. Make ready by other utilities is on-going. Permits are awaiting approval by the City of Chesapeake and the City of Suffolk. A sub-contractor for the Town of Smithfield is placing a conduit for our use in conjunction with the Townâ€™s revitalization project. We have placed 16 miles of fiber cable during this quarter for a total of 16 miles placed or 9 % of the total. We spent $412,070 this quarter, bringing the total spent to $5,698,472 or 45.5% of the total. The majority of the project activity this quarter has been in Southampton County. | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | Fiber construction started March 8,2012 | N/A | N/A | N/A | Constructed 16 miles in March 2012 | N/A | N/A | Site work began in March 2012 | 1 | 5 | 12 | Town of Surry,VA - co-location agreement to provide access and transport of internet services offered by the county or their agent. | MBC provides optical transport services, using both SONET/TDM, Wavelength and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STSs for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in Â¼ rack increments or 12 rack units) for members. Due to grant funds being used in the construction of the MBC backbone network, Dark fiber IRUs are no longer offered. . Fiber lease arrangements are considered on case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term | N/A | 0 | 0 | 0 | 0 | Cable has not been placed in service as of March 2012 | N/A | N/A | 10 mbps - 100 mbps - Open Access | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10 mbps - 100 mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps - 100 mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps - 100 mbps - Open Access | N/A | FALSE | N/A | â€¢ Place at least 40 miles of fiber in this quarter â€¢ Pass at least 5 CAIs â€¢ Gain final approval of bridge designs from VDOT â€¢ Complete lease agreements with another utility for duct space on bridges. â€¢ Select successful bridge crossing contractor and start construction on bridge crossings | Mid-Atlantic Broadband Cooperative | â€¢ Completion of utility agreement with the City of Chesapeake and the City of Suffolk â€¢ Completion of lease agreements with another utility for duct space on bridges â€¢ Coordinating cable construction along Highway 58 to avoid certain VDOT improvement projects | â€¢ Completion of lease agreements with another utility for duct space on bridges â€¢ Completion of utility agreement with the City of Chesapeake and the City of Suffolk â€¢ Co-ordinating cable construction along Hwy. 58 to avoid certain VDOT improvement projects â€¢ Signage and traffic control requirements limit construction time on controlled access highways and is an added expense | TRUE
NT10BIX5570087 | 2012 | Q2 | Q2 - 2012 | The budget modification requesting that the original budget be modified to redistribute existing budgeted funds to more accurately identify and track actual project expenditures has been approved. Fiber construction on this project has been brisk. We have completed the construction between Emporia and Franklin as well as the majority of the fiber construction between Windsor and Smithfield. Site work is continuing on the Franklin and Surry node sites. Wet weather has slowed progress somewhat. The signed easement was recently recorded for the Windsor site and we are currently waiting for the signed easement from the County School Board for the Smithfield site. Once received, we will begin site work on those. The contract for construction of the six bridge crossings identified on this project has been awarded and construction is to begin in the next quarter. Four CAIâ€™s have been passed so far in Isle of Wight County. They are Carrollton, Windsor, and Westside Elementary schools and Windsor High School. We have also been contacted on behalf of Community Electric Co-operative about a contract for service to one of their substations. Make ready by other utilities is on-going, although it will be slowed in the coming quarter by recent storms in central and eastern Virginia. The conduit has been placed in Smithfield thru the revitalization area and is now ready to occupy. We have placed 69 miles of fiber cable during this quarter for a total of 85 miles placed or 50% of the total. We spent $998,895 this quarter, bringing the total spent to $6,697,367 or 53.5% of the total. The majority of the project activity this quarter has been in Isle of Wight County. | 81 | 0 | 0 | 0 | 81 | 0 | 0 | 0 | Placed 65 miles of fiber in Y2Q4(2nd qtr of 2012) | N/A | N/A | N/A | Placed 65 miles of fiber to Y2Q3(2nd qtr of 2012) | N/A | N/A | N/A | 1 | 5 | 12 | Town of Surry, Va co-location agreement to provide access and transport services offered by the county or their agent. | MBC provides optical transport services, using both SONET/TDM, Wavelength and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STSs for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members. Due to grant funds being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on a case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 0 | 0 | 0 | 0 | Cable not placed in service as of June, 2012 | N/A | N/A | 10 mbps-100 mbps- Open Access | 4 | 0 | 0 | 0 | Passed but not connected | N/A | N/A | 10 mbps-100 mbps- Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-100 mbps- Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-100 mbps- Open Access | N/A | FALSE | N/A | â€¢ Place at least 50 miles of fiber in this quarter â€¢ Pass at least 5 CAIs â€¢ Completion of the six bridge crossings â€¢ Completion of the aerial make ready â€¢ Completion of four node sites | Mid-Atlantic Broadband Cooperative | â€¢ Completion of Easements for the Windsor and Smithfield nodes. â€¢ Completion of aerial make ready thorough out the project â€¢ Co-ordinating cable construction along Hwy. 58 to avoid certain VDOT improvement projects | â€¢ Completion of six bridge crossings in a timely manner â€¢ Completion of aerial make-ready due to storm related damages for other utilities â€¢ Completion of the site work and placing of the four node sites â€¢ Coordination of cable construction with VDOT along Hwy 460 | TRUE
NT10BIX5570087 | 2012 | Q3 | Q3 - 2012 | Fiber construction on this project has been on schedule. We have completed the construction between Emporia and Franklin; between Windsor and Smithfield. In addition, most of the construction between Surry and Smithfield is complete. The Franklin make ready was completed and the cable placed through the Town. The Franklin and Surry nodes have been set and the site work for Windsor is 50% complete. We continue to wait on the signed easement from the County School Board for the Smithfield site. Once received, we will begin the site work for Smithfield. Construction of two of the six bridge crossings identified on this project has been completed. Six additional CAIs were passed this quarter, bringing the total passed to ten. They are Smithfield High School, Smithfield Middle School, Surry County High School, Surry County Elementary School, Luther Porter Jackson Middle School (Surry County) and Carrsville Elementary School. We are negotiating at least five contracts for service to cell tower sites and to an electric cooperative. We have placed 39 miles of fiber cable during this quarter for a total of 120 miles placed or 71% of the total. We spent $1,313,363 this quarter, bringing the total spent to $8,010,730 or 63.9% of the total. The majority of the project activity this quarter has been in Surry County. | 130 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | Placed 49 miles in Y3Q3 (Y3Q1) | N/A | N/A | N/A | Placed 49 miles in Y3Q3(Y3Q1) | N/A | N/A | N/A | 1 | 7 | 12 | Town of Surry,VA; co-location agreement to provide access and transport services offered by the county or their agent. | MBC provides optical transport services, using both SONET/TDM, Wavelength and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STSs for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members. Due to grant funds being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on a case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 0 | 0 | 0 | 0 | Cable not placed in service as of September 30,2012 | N/A | N/A | 10mbps-100mbps - Open Access | 11 | 0 | 0 | 0 | Passed but not connected yet | N/A | N/A | 10mbps-100mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10mbps-100mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10mbps-100mbps - Open Access | N/A | FALSE | N/A | â€¢ Place at least 30 miles of fiber in this quarter â€¢ Pass at least 2 CAIs â€¢ Completion of the four remaining bridge crossings â€¢ Completion of the two remaining node sites â€¢ Completion of the City of Chesapeake and City of Suffolk agreements | Mid-Atlantic Broadband Cooperative | â€¢ Obtaining the easement for the Smithfield node. â€¢ Completing the aerial make ready in Franklin â€¢ Completing the cable construction through the Town of Surry â€¢ Obtaining permits and agreements from the City of Chesapeake and the City of Suffolk | â€¢ Completion of four bridge crossings in a timely manner â€¢ Obtaining the easement and completing construction of the Smithfield node â€¢ Completion of the City of Chesapeake and City of Suffolk agreements in a timely manner | TRUE
NT10BIX5570087 | 2012 | Q4 | Q4 - 2012 | Fiber construction on this project has been on or ahead of schedule until this quarter. We completed the construction between Emporia and Franklin, between Franklin and Windsor, between Windsor and Smithfield, and between Smithfield and Waverly, via Surry. Construction has been halted on the Smithfield to Chesapeake section and the Windsor to Suffolk section until Right-of-way agreements can be approved by the respective City Councils. The work on the Windsor nodes has been completed. We continue to wait on the signed easement from the County School Board for the Smithfield site. Once received, we will begin the site work for it. Construction of two of the six bridge crossings identified on this project has been completed. We continue to wait for VDOT and City of Suffolk approval of the remaining four. Five additional CAIs were passed this quarter, bringing the total passed to fifteen. They were Windsor Middle School, New Horizonâ€™s Alternative Center, Isle of Wight School board, Paul Camp Community College, and Surry County High school. We are continuing negotiation for at least five contracts for serve cell tower sites and an electric cooperative. We have placed 13 miles of fiber cable during this quarter for a total of 143 miles placed or 84% of the total. We spent $543,334.12 this quarter, bringing the total spent to $8,566,063.69 or 68.3% of the total. The majority of the project activity this quarter has been in Isle of Wight County. | 143 | 0 | 0 | 0 | 143 | 0 | 0 | 3 | Placed 13 miles in Y3Q4 (Y3Q2) | N/A | N/A | N/A | Placed 13 miles in Y3Q4 (Y3Q2) | N/A | N/A | Holding for easement approval | 1 | 7 | 12 | Town of Surry- Co-location agreement to provide access and transport offered by the county or their agent | MBC provides optical transport services, using both SONET/TDM, Wavelength and Ethernet Connections. Ethernet circuits are provisioned as Ethernet over SONET, and each circuit has dedicated STSs for transport delivery. Standard contract terms are 24 months. MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members. Due to grant funds being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on a case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 0 | 0 | 0 | 0 | Cable not placed in service as of December 31, 2012 | N/A | N/A | 10 mbps - 100 mbps - Open Access | 16 | 0 | 16 | 16 | Schools & other government institutions connected | N/A | Schools & other government institutions connected | 10 mbps - 100 mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps - 100 mbps - Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps - 100 mbps - Open Access | N/A | FALSE | N/A | â€¢ Place 20 miles of fiber cable â€¢ Pass at least 4 CAIs â€¢ Completion of the four remaining bridge crossings â€¢ Completion of the one remaining node site â€¢ Completion of the City of Chesapeake and City of Suffolk agreements | Mid-Atlantic Broadband Cooperative | â€¢ Obtaining the easement for the Smithfield node. â€¢ Obtaining permits and agreements from the City of Chesapeake and the City of Suffolk | â€¢ Completion of four bridge crossings in a timely manner â€¢ Obtaining the easement and completing construction of the Smithfield node â€¢ Completion of the City of Chesapeake and City of Suffolk agreements in a timely manner | TRUE
NT10BIX5570087 | 2013 | Q1 | Q1 - 2013 | MBC has completed all fiber cable construction up to the City of Suffolk and City of Chesapeake jurisdictional boundaries. The Franchise Agreement with the City of Chesapeake was approved on February 26, 2013 and the construction permits are under review. We intend to resume construction work in April, 2013. MBC met with the Chief Operating Officer of Old Dominion University this quarter to solicit support for our Franchise applications in Chesapeake and Suffolk. He agreed the University would support us in any way possible. The Franchise application and supporting documents have been prepared and the City of Suffolks City council will consider the application at their April 17, 2013 meeting. Our expectation is that it will be approved and we can begin construction immediately. After several months of delay by the Isle of Wight School Board, they approved the easement for the hut to be placed near Smithfield High school on March 14, 2013. The application for the building permit has been submitted and we should begin site work in mid-April, 2013. Upon completion, all four (4) hut sites will be ready for equipment installation. Two (2) additional CAIs were served this quarter, bringing the total served to eighteen. They were Hardy Elementary School and the Surry County Bus Garage. We are continuing negotiation on services several to cell tower sites and an electric cooperative. We have placed 1 mile of fiber cable during this quarter for a total of 144 miles placed or 85% of the total. We spent $456,283.82 this quarter, bringing the total spent to $9,012,365.51 or 71.9% of the total. The majority of the expenditures were for construction and retainage. The majority of the project activity this quarter has been in Isle of Wight County. | 144 | 0 | 0 | 0 | 144 | 0 | 0 | 3 | Placed one (1) mile in Y4Q1(Y3Q3) | N/A | N/A | N/A | Placed one (1) mile in Y4Q1(Y3Q3) | N/A | N/A | Work to start 4-15-13 on 4th site | 1 | 7 | 12 | Town of Surry; co-location agreement to provide access and transport offered by the county or their agent. | MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members Due to grant funds being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 1 | 0 | 0 | 0 | Cable not placed in service as of 3-31-13 | N/A | N/A | 10 mbps-100 mbps; Open access | 18 | 1 | 17 | 18 | Added Hardy Elementary (Isle of Wight School) and Surry County Bus Garage (other Gov't institute) | Other government Institution | Schools and other government institutions | 10 mbps-100 mbps; Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-100 mbps; Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-100 mbps; Open Access | N/A | FALSE | N/A | â€¢ Place remaining 28 miles of fiber cable to complete fiber construction on the project â€¢ Complete the equipment installation in the nodes â€¢ Complete the four remaining bridge crossings â€¢ Complete the one remaining hut site â€¢ Complete City of Suffolk Franchise agreement and begin construction â€¢ One additional CAI to be added this quarter | Mid-Atlantic Broadband Cooperative | â€¢ Obtaining the easement for the Smithfield node. â€¢ Obtaining permits and agreements from the City of Chesapeake and the City of Suffolk | â€¢ Completion of four bridge crossings in a timely manner â€¢ Completion of the remainder of the fiber construction by June 30, 2013. | TRUE
NT10BIX5570087 | 2013 | Q2 | Q2 - 2013 | MBC has completed all fiber cable construction in Chesapeake and 10 miles of 27 miles remain in Suffolk. All of the bridge crossings were completed this quarter and cable has been pulled in all but one. The Smithfield node has been set, along with the generator, and the cables have been spliced and tested. We are awaiting the placement of the power before the remaining equipment installation starts. One new circuit with a last mile provider was executed this quarter, bringing the total circuits to one (1) for this project. We have placed 17 miles of fiber cable during this quarter for a total of 161 miles placed or 95% of the total. We spent $520,229.05 this quarter, bringing the total spent to $9,532,594.56 or 76% of the total. The majority of the expenditures were for construction and retainage. The majority of the project activity this quarter has been in the City of Suffolk. | 161 | 0 | 0 | 0 | 161 | 0 | 0 | 4 | Placed 17 miles in Y4Q2(Y3Q4). To be completed by 8/31/13 | N/A | N/A | N/A | Placed 17 miles in Y4Q2(Y3Q4). To be completed by 8/31/13 | N/A | N/A | Completed in Y4Q2 | 1 | 7 | 12 | Town of Surry (1) | MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members Due to grant funds being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 1 | 0 | 0 | 0 | Town of Surry | N/A | N/A | 10 mbps-100 mbps- Open Access | 18 | 1 | 17 | 18 | No additions this quarter | Other government institutions | Schools & other government institutions | 10 mbps-100 mbps- Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-100 mbps- Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mbps-100 mbps- Open Access | N/A | FALSE | N/A | â€¢ Complete the remaining 10 miles of cable and the route modification work by July 31, 2013 â€¢ Complete the equipment installation by July 31, 2013 â€¢ Complete the payment of all outstanding invoices by August 31, 2013 â€¢ Complete all close-out activities and reports by the end of the 3rd quarter, 2013. | Mid-Atlantic Broadband Cooperative | â€¢ Construction progress has been slowed in Suffolk due to weather, utility conflicts, and make ready issues. â€¢ Site work and placing of the Smithfield node â€¢ Getting consultation replies from the Eastern Shawnee Tribe of Oklahoma so we can finish the route modification work. | â€¢ Complete the remaining 10 miles of cable by July 31, 2013 â€¢ Complete the equipment installation by July 31, 2013 â€¢ Complete the payment of all outstanding invoices by August 31, 2013 â€¢ Complete all close-out activities and reports by the end of the 3rd quarter, 2013 | TRUE
NT10BIX5570087 | 2013 | Q3 | Q3 - 2013 | MBC has completed all fiber cable construction on this project, having placed the final 13 miles this quarter. The equipment installations for all four nodes, as well as ODU, have been completed. The cables and equipment have all been tested and all network components completed. We have installed 3 new circuits this quarter, bringing the total circuits to 4 with one(1) co-location agreement. We have connected a total of 19 CAIs for this project. We have placed a total of 174 miles of cable on this project. The total spent (Federal and matching) after all invoices have been paid is $10,847,702 (87%). The majority of the expenditures this quarter were for construction and retainage. | 174 | 0 | 0 | 0 | 174 | 0 | 0 | 4 | Complete; Placed 13 miles in Y4Q3(Y4Q1) | N/A | N/A | N/A | Placed 13 miles in Y4Q3(Y4Q1) | N/A | N/A | Complete | 5 | 3 | 12 | Kinex (2); GCR (3) | MBC provides secured, carrier-class collocation space (in 1/4 rack increments or 12 rack units) for members Due to grant funds being used in the construction of the MBC backbone network, dark fiber IRUs are no longer offered. Fiber lease arrangements are considered on case by case basis. (Member pays annual fee for use of the dark fiber strands.) Five year minimum lease term. | N/A | 5 | 0 | 0 | 0 | Kinex (2); GCR (3) | N/A | N/A | 10 mbps-100 mbps- Open Access | 19 | 2 | 17 | 19 | One (1) addition this quarter | Other government institutions | Schools & other government institutions | 10 mbps-100mbps-Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mpbs-100 mbps- Open Access | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10 mpbs-100 mbps- Open Access | N/A | FALSE | N/A | â€¢ Completed | Mid-Atlantic Broadband Cooperative | â€¢ Construction progress was slowed in Suffolk due to weather, utility conflicts, and make ready issues. â€¢ Previously damaged duct on one bridge crossing â€¢ Getting consultation replies from the Eastern Shawnee Tribe of Oklahoma so we could finish the route modification work. | Completed | TRUE
NT10BIX5570088 | 2010 | Q4 | Q4 - 2010 | A stakeholder selection committee has been meeting and evaluating vendor proposals from an RFP to build, operate and maintain a new LTE broadband network. An additional RFP was submitted seeking a Technical Consultant to serve as a technical team advisor to Charlotte's BTOP project team. A selection committee was formed and is currently evaluating these proposals. An Environmental Assessment draft was completed by the selected Environmental Consulting firm and is currently under review by Charlotte's BTOP team. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Select & Award Technical Consultant Contract. Re-Structure Project Business Plan and Network approach/design Strategy. Re-Structure and issue RFP with new approach/design strategy. | Charlotte, City of | The vendor selection, technical consultant selection and remaining project is expected to be delayed due to several factors that may change the scope and restart of this project. Factors include: 1. The discovery in November that $4.077 million of Charlotte's grant match is not allowable via OMB circular A-87 section 37 2. SAC - FCC definition of a public safety user does not extend to secondary responders 3. SAC - FCC Order for Interoperability among other recipients create unpredictable costs and time to project 4. Device Cost - Learned from proposal submissions, cost of the LTE devices are significantly higher than projected 5. Continuance - Charlotte will need to re-think its business plan, system design, subscriber base, operation and maintainability for this network to be substantiable. Efforts are underway to resolve as priority. | Next quarter impacts are contingent to how and how quickly the following issues are addressed/resolved. Issues include: 1. The discovery in November that $4.077million of Charlotte's grant match is not allowable via OMB circular A-87 section 37 2. SAC - FCC definition of a public safety user does not extend to secondary responders 3. SAC - FCC Order for Interoperability among other recipients create unpredictable costs and time to project 4. Device Cost - Lessons learned from proposal submissions, cost of the LTE devices are significantly higher than projected. 5. Continuance - Charlotte will need to re-think its business plan, system design, subscriber base, operation and maintainability for this network to be substantiable. | TRUE
NT10BIX5570088 | 2011 | Q1 | Q1 - 2011 | On January 31st 2011, the City of Charlotte canceled the evaluation of its initial wireless broadband RFP responses. In exchange, Charlotte focused on a reevaluation and restructure of its BTOP project. This was in part due to the discovery that the majority of Charlotteâ€™s grant match was not consistent with the Office of Management and Budget matching guidelines, and the current RFP afforded little if no opportunity to explore more flexible alternatives as it had solicited a specific solution to design, construct and manage the network On February 28th 2011, the City filed a request for a waiver with NTIA for any remaining cost match it could not meet during the grant performance period. NTIA responded on March 21st 2011 that the request was NOT in the best interest at this time but the City should pursue alternatives options. On March 3 2011, another quarter milestone was reached when Charlotte completed their Technical Consultant evaluation selection process and awarded a Technical Consultant Contract to RCC. With RCCâ€™s assistance the City of Charlotte explored different network design strategies, project scope and business plan solutions. On April 4th 2011, the City of Charlotte reissued a new LTE Broadband RFP soliciting broader and more flexible approach. The new RFP invites providers to propose multiple solutions to design construct and manage a 700 MHz public safety LTE broadband network while contributing to the project in a way aligned with NTIAâ€™s policies. T | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Receive and Review new RFP Responses. Narrow vendor list to top 2 or 3. Request top vendor presentations. Provide a contracts for top vendors for their review and ask them to red-line any issues. Select Primary Vendor. | Charlotte, City of | Last quarter Charlotte reported challenges/issues with grant match, FCC issues with public safety definition and interoperability, LTE device cost, and business plan continuance. This quarter much effort was put towards mitigating these challenges: â€¢ Charlotte filed for a grant match waiver which was not accepted by the NTIA. This response allowed Charlotte to rule out specific preferred project approaches that were under considerations. â€¢ Charlotte took the lead in filing a Declaratory Judgment with the FCC regarding who could be a user on the network. â€¢ Charlotte also took the lead in establishing a 700BTOP Recipients group and document sharing website for interoperability coordination. Charlotte invited NTIA & PSST OAC Group to participate. â€¢ Charlotte plans to leverage devices acquired for DNC coming in Fall of 2012. â€¢ Charlotte issued a new Broadband RFP to address project challenges mentioned above. | Charlotte anticipates a push back from vendors to allow more time to respond to Charlotte's RFP. While plans are in place to make selection process more efficient, vendors need for more response time may likely cause Charlotte to miss all three milestones for next quarter. This will essentially put Charlotte behind their baseline by one quarter. As Charlotte reviews the new RFP responses, it is very likely Charlotte will need to issue a new budget and baseline plan for NTIA approval. | TRUE
NT10BIX5570088 | 2011 | Q2 | Q2 - 2011 | Since the City of Charlotte's original project funding match was found not compliant with the Broadband Technology Opportunity (BTOP) grant match requirements, Charlotte decided to redesigned and reissued a new and more open-ended Request for Proposal (RFP) which also asked bidders to assist in meeting Charlotteâ€™s grant match requirement. This new RFP was publicly re-issued on April 4th, 2011. The City also hired a legal consultant to assist in drafting a proposed broadband vendor contract and contract negotiations with hopes to streamline the evaluation and negotiation process. A proposed contract accompanied the BTOP RFP as an addendum and respondents were required to submit their proposed changes to the contract with their RFP responses. The City held a pre-proposal conference on April 20th and addressed questions and answers for prospective bidders throughout the proposal submission time frame. Charlotte received several requests to allow bidders more time to respond to the new proposal. Charlotte granted an additional month for bidders to respond to the RFP changing the deadline for submissions to June 6th, 2011 at which time Charlotte began the proposal evaluation process. On June 30th the evaluation team met and began the short list process. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance | N/A | N/A | N/A | N/A | No Variance | N/A | No Variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No Variance | No Variance | N/A | Network not operational at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Pending NTIAâ€™s approval of a significant project change that includes a new deployment strategy, and an overhaul in Charlotteâ€™s original BTOP project budget, Charlotteâ€™s goal would be to have a primary LTE vendor selected and contract negotiated by end of next quarter. Charlotte is hopeful that a new approved project strategy will allow for a more compressed and streamline implementation schedule by focusing on a solution that will minimize risks that may result in additional project delays. Charlotteâ€™s goal with this new approved project strategy and budget framework is to provide the ability to be back on tract with the original baseline plan by end of 2nd quarter year 2. This would include completing any necessary environmental assessment efforts, finalizing a network design and begin the manufacturing of network equipment for deployment. | Charlotte, City of | Because the City of Charlotte needed to reissue a new Request for Proposal (RFP) and extend the proposal submission time line by an additional month, Charlotte was not able to meet their three original baseline milestones for this quarter.(Award Contract, Project Kickoff, & System Design studies) Charlotteâ€™s current plan is to accomplish two of these milestones (Award Contract, & Project Kickoff) by the end of next quarter. Charlotte is hopeful that the extra diligence put forth in the redesign of a project solution with the awarded vendor will aid in getting the project back on track by year end. Charlotte plans to work closely with their BTOP Program Officer to help validate that new proposals will properly address Charlotte's match issues. | Charlotteâ€™s three main project challenges are funding match, network sub stainability, and the grant project time line. Charlotte anticipates that a vendor solution can be identified to resolve Charlotteâ€™s match challenge. Charlotte also anticipates working with the selected vendor to identify a fast track project approach/solution that will ultimately achieve the performance requirements of the grant. Charlotte however is still very concerned about investing in a network in which the ability to sustain the network is doubtful due to the use restriction in the FCC license for the spectrum. Until the use and user question is resolved, either by the FCC or through additional legislation, the implementation of the grant is an open question. Charlotte does plan to engage the BTOP program assistance in each of these three areas in this next quarter. | TRUE
NT10BIX5570088 | 2011 | Q3 | Q3 - 2011 | Towards the end of last quarter, Charlotte had received proposals from broadband vendors who were encouraged to submit proposals with multiple options to deliver/deploy their broadband solutions and provide solutions for Charlotte to meet its grant matching challenges. Upon the review of these submitted proposals during this quarter, Charlotte invited two vendors in for bid presentations. After these presentations were given, Charlotte requested both vendors to prepare best and final offers on two deployment strategies. One strategy, where Charlotte owned the entire network including the systems core components (Own Solution) and the other strategy where the Core would be owned, operated and hosted by the vendor (Hosted Solution). With assistance from Charlotteâ€™s Technical Advisor, a Broadband Business Plan was formulated which included an analysis of these offers and strategies. Also with assistance from NTIA, Charlotte completed its analysis of the vendorâ€™s proposed match solution strategies. Upon the completion of this analysis, Charlotte began contract negotiations with both vendors on the Hosted Solution strategy. Charlotte completed its negotiations process and recommended Alcatel-Lucent as the Wireless Broadband Deployment vendor to Charlotte City Council. The Council voted on September 26, 2011 to approve a contact with Alcatel-Lucent and an agreement was signed by both parties on September 28th . | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance | N/A | N/A | N/A | N/A | No Variance | N/A | No Variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No Variance | No Variance | N/A | Network not operational at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Charlotte will be submitting an Award Action Request for (new budget & route modification) next quarter. Additionally, now with a vendor contract signed, Charlotte intends to complete the following baseline milestones for next quarter; Project Kick Off, Design Studies, Finalize Network Design, and any Environmental Assessments and Studies required. | Charlotte, City of | Charlotte was able complete the Contract Award milestone as stated in last quarters report. However, Charlotte was unable to accomplish Project Kickoff, System Design Studies, Final Network Design and Begin Equipment Manufacturing as stated in the original Baseline. Charlotte appreciates the assistance received from NTIA in reviewing the vendor's match proposals and attending the vendors proposal presentations. The evaluation and due diligence needed to complete the procurement process required longer than expected/planned. This was realized through the complexity of the proposals and Charlotte's need to recognized a solution that can lead to a sustainable network solution. | The preliminary new design from Alcatel-Lucent indicates that 1 new tower is be required to be built. All other deployments are on existing Crown Castle or Charlotte owned towers. Technical assistance will be sought to assist/define what Environmental Assessments needs are required with this new deployment design. Aside from this one identified new tower, Charlotte is hopeful that the relatively small deployment on 38 existing towers under a hosted core solution will allow the completion of this project with the grant performance period. | TRUE
NT10BIX5570088 | 2011 | Q4 | Q4 - 2011 | In the fourth quarter of 2011, Charlotte kicked off their Implementation Project with the recently awarded implementation vendor, Alcatel-Lucent (ALU). Alcatel-Lucent's 4th quarter Implementation Activities included: â€¢ Completed an implementation Project Plan, a High Level Network Design Document including cellular site locations, design details for the Charlotte based Data Center and Design details of the EPC Network Core which will be hosted by ALU. â€¢ Ongoing activities include surveys of all the planned eNodeB sites, for antenna design, and microwave path design. approximately 75% complete. Charlotte's Grant Reporting Activities for the quarter include: â€¢ Submission of a revised budget plan to match the new ALU solution. â€¢ Submission of a revised Network Route Plan as designed by ALU. â€¢ Submission of a new environmental assessment project description report which lead to Charlotte obtaining a Categorical Exclusion for the environmental special award condition. Charlotteâ€™s program level activities and accomplishments for the quarter include: â€¢ Coordinated with many National and State entities to ensure then new system (CharMeck Connect) is designed and implemented according to Federal Communications Commission Orders. â€¢ Preparation of Charlotteâ€™s Interoperability showing for the FCC. â€¢ Began procurement activities to purchase new network compliant devices. * Please note: Charlotte actually completed much more on project milestones as indicated in the status above than indicated in the percent complete column in table 2 below. Charlotte received over $3 million in deliverable milestone invoices in mid December, but was not able to get these paid or draw down grant funds before the quarter ended. Therefore the table below does not accurately reflect the true progress made but only the financial activity encumbered as of December 31 2011. Charlotte also is working off a new program budget beginning this quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance | N/A | N/A | N/A | N/A | No Variance | N/A | No Variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No Variance | No Variance | N/A | Network not operational at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Charlotte's Implementation planned accomplishments for Q1 2012 include: • Alcatel-Lucent will continue with Low level design work and test plans. • There will be heavy emphasis on preparation for site work at the cell site locations to include site walks, leasing, structural mapping and analysis, physical design specifications and permitting that will be required for Phase 1 installation and integration activities. • Design Teams will complete specifications (path surveys and overall physical design of the Microwave/IP Backhaul network) and file for frequency licenses on behalf of the project. • In support of Phase 1 a Bill of Materials will be defined the networking equipment, systems ordered, manufactured and procured for staging activity and then delivered to Charlotte • Alcatel-Lucent will also perform interoperability testing with City selected vendors of user devices. Charlotte’s program level activities planned for completion Q1 2012 include: • InterOp Showing to FCC • PSST Spectrum Lease Execution Complete • State of NC CIO Confirmation of Coordination • Complete RFI for IPX Services and Provider Contracting Process • Networking and Interworking Low Level/Detailed Designs Finalized (includes PLMN ID and related matters & Core N/W and ePC LLD/DD Activities) • Device Provisioning Process Design • PSCR Testing w/Devices • Devices Testing Completed: IODT using ALU IODT Group • Phase 1 Policy Definitions and Applications Support Complete • Devices: Vendor Selections Finalized | Charlotte, City of | Charlotte did complete the following original baseline milestones, Project Kickoff, System Design Studies and Finalize a High Level Network Design. However, according to the original baseline milestones for this given period, Charlotte was unable to accomplish, Equipment Manufacturing, Obtain Site Permits for Tower work and begin Installation of microwave equipment. Charlotte appreciates the guidance provided by NTIA that lead to the acceptance of our budget modification, route modification and Categorical Exclusion filed in order to better align with our new project direction and vendor solution. | Program level activities involving FCC orders or possible delayed actions on FCC part. The following Infrastructure Budget Details reflect a NEW BUDGET. Budget modification approved in December 2011. | TRUE
NT10BIX5570088 | 2012 | Q1 | Q1 - 2012 | Project Accomplishments in the first quarter of 2012 for Charlotte and their deployment vendor Alcatel-Lucent include the following: â€¢ Microwave Path Studies and Microwave Design completed â€¢ Radio Frequency (RF) Design is nearly completed â€¢ Low level Inter-networking and System Network Design is completed â€¢ Microwave Equipment, RF Equipment and Radio Access Network (RAN) equipment was Ordered/Manufactured for Phase 1 (8 Center City Sites) â€¢ Successfully completed a Customer Witness Test of Phase 1 staging of Microwave Equipment â€¢ Began Shipping Phase 1 Equipment to Charlotte â€¢ Completed the following Site Preparation Activities for most all sites: site walks, tower application. tower leasing agreements, physical design specifications, structural mapping and analysis â€¢ Began Test Team Meetings for Designing Testing Processes and Optimization Plans â€¢ Reviewed Proposals for LTE Devices and a Device Procurement Contract is nearly complete â€¢ Inter-Operability Showing has been completed and is in Pre-Approval State â€¢ Completed 70% of Microwave Licensing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance | N/A | N/A | N/A | N/A | No Variance | N/A | No Variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No Variance | No Variance | N/A | Network not operational at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Charlotte was verbally informed by NTIA to anticipate changes coming in the BTOP grant management as it relates to types of authorized expenditures. However, until such information is received formally, Charlotte's will continue to comply with its approved Implementation plan. Anticipated accomplishments for Q2 2012 include: â€¢ Continue to progress towards network installation, integration and deployment with June 30 as target date for going to production with phase 1. â€¢ Charlotte Data Center Installation will begin April 9 â€¢ The completion of all site acquisitions and site preparation activities including permitting and getting all sites finalized, structural related items identified and plans to address in place by June 1. â€¢ Continuation of Equipment delivery to the Charlotte warehouse and facilitate inventory by City of Charlotte resources, prior to installation in the field, with ALU supporting the effort. â€¢ Begin Installation of M/W backhaul, Antennas and ground LTE based equipment by early May. â€¢ In-market testing, RF and Acceptance Testing, will start at the beginning of June. RF testing will be executed using ALU provided devices. â€¢ Test Teams will complete development of test plans to be executed in the RAN, Hosted Core, and in a full end-to-end capacity. â€¢ Dependant on device availability: o Device Management related development and Device Provisioning Process Design - motive work o will continue o Devices: Vendor Selections Finalized and Device Procurement for Phase 1 o Alcatel-Lucent will perform interoperability testing with City selected user devices. o Device testing in mid May timeframe in Naperville via on the air eNBâ€™s â€¢ Phase 2 equipment builds and procurement initiated in late June in preparation for phase 2 installation activities once phase 1 has completed. â€¢ Acceptance Test execution will require City provided devices and will occur throughout the month of June in parallel to RF testing. | Charlotte, City of | While Charlotte completed the following original baseline milestones, Finalize a Low-Level Network Design, Begin Equipment Manufacturing, and Begin Shipping Equipment, According to the original baseline milestones for this given period, Charlotte was not able to begin the Site Permitting and begin any Installation of Microwave Equipment. However Site permitting submissions will begin the first of April 2012. | The possible suspension by NTIA of the authority to purchase LTE specific equipment. The availability of DEVICES and UICCâ€™s for interoperability testing will be paramount. Device Management development and various aspects of test planning and subsequent test execution. Failure of the FCC to approve the Cityâ€™s Interoperability Showing. | TRUE
NT10BIX5570088 | 2012 | Q2 | Q2 - 2012 | One of Charlotteâ€™s main goals for second quarter 2012 was to complete all site acquisitions and site preparation activities and begin the deployment of phase 1 sites. These activities included the signing of all site leases, finalizing structural related items and obtain all permitting by June 1. However, early in the second quarter (April 3, 2012), Assistant Secretary Strickling requested the City not purchase any Long term Evolution (LTE) related equipment or services pending a decision by the First Responder Network Authority Board (FirstNet) on Charlotteâ€™s continued use of the 700 MHz spectrum. This was clarified and confirmed by the Grants Office in May with a formal notification that Charlotteâ€™s Grant would no longer fund any LTE related project activity. The verbal notice initially slowed Charlotteâ€™s progress in the early stages of the second quarter and the formal notification eventually stopped all these activities. Below is a status of activities before they came to a stop. â€¢ Received Phase 1 Equipment into Charlotte Warehouse and began staging equipment for phase 1 deployment â€¢ Completed the installation of the Charlotte Data Center including the connection to Alcatel-Lucentâ€™s Hosted core located in Naperville Illinois â€¢ Completed the electrical up fit work needed at the first phase 1 site (Charlotte-Mecklenburg Government Center) â€¢ Signed leasing agreements for 11 co-located tower sites â€¢ Submission of 17 sites in for permitting â€¢ Working on structural drawings and bids for 14 structural improvement sites â€¢ Completed around 90% of test plans for phase 1 system acceptance testing â€¢ Assisted device vendors for interoperability device testing â€¢ Charlotteâ€™s internal networking detail design was fully completed and partially implemented For the remainder of the quarter Charlotteâ€™s focused has been providing the Grants Office with necessary reporting and maintaining a working relationship with their vendors to define a possible go forward approach acceptable to all parties | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance | N/A | N/A | N/A | N/A | No Variance | N/A | No Variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No Variance | No Variance | N/A | Network not yet operational. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | At this time the City of Charlotte cannot predict any future project activities due to the current suspension issued by the Grant Office. The current suspension has stopped all of Charlotteâ€™s project activities as all activities for Charlotte are considered LTE related. Charlotteâ€™s focus in next quarter will be to maintaining an open relationship with their vendors and NTIA to define a possible go forward approach acceptable to all parties. If an acceptable approach cannot be discovered then Charlotte will be forced to terminate the project and begin closeout processes. | Charlotte, City of | The suspension of LTE related funding by the Grants Office is the only reason the planned activities for the past quarter were not achieved. | The suspension of LTE related funding by the Grants Office is the only reason the planned activities for the past quarter were not achieved. | TRUE
NT10BIX5570088 | 2012 | Q3 | Q3 - 2012 | Throughout the third quarter of 2012 the City of Charlotte's Broadband Technology Opportunities Program (BTOP) grant was in suspension. The suspension as ordered by the National Oceanic and Atmospheric Administration (NOAA) Grant Management Office ordered that no funding or LTE project deployment activities shall continue until the newly established FirstNet Board authorizes it to do so. As a result Charlotte performed the following non-deployment activities while under the suspension: â€¢ Performed Impact analysis on BTOP vendor contracts as a result of the suspension. â€¢ Performed project cost analysis as it relates to the suspension. â€¢ Maintained relationship with project vendors while seeking to minimize delay cost and research â€œgo forwardâ€ project options. â€¢ Analyzed â€œgo forwardâ€ project costs options. â€¢ Prepared drafts of â€œgo forwardâ€ agreements to support optional project approaches and include additional NTIA special award condition requirements. â€¢ Prepared a draft submission for the Federal Communications Commission (FCC) requesting Special Temporary Authority (STA) to operate under the Public Safety spectrum. â€¢ Performed an updated Public Safety user base inventory. â€¢ Worked with several wireless device vendors to obtain device pricing models to aid in determining a â€œgo forwardâ€ scenario. â€¢ Produced and analyzed â€œgo forwardâ€ Business Case models | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project under suspension | N/A | N/A | N/A | N/A | Project under suspension | N/A | No Variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project under suspension | Project under suspension | N/A | Network not yet operational. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Continue working with primary vendors and device vendors in determining financial viability and changing requirements to support a go forward plan. Other activities are not predictable due to current suspension by the Grants Office. | Charlotte, City of | Any guidance toward funding suspension cost. | Any guidance toward funding suspension cost. | TRUE
NT10BIX5570088 | 2012 | Q4 | Q4 - 2012 | The City of Charlotteâ€™s Broadband Technology Opportunities Program (BTOP) grant remained under suspension throughout the fourth quarter of 2012. The suspension requires that no Long Term Evolution (LTE) related activities or funding continue until the newly established FirstNet Board authorizes. As a result, the following is a list of non-deployment activities accomplished while under suspension: Performed financial cost analysis and business modeling as it relates to: â€¢ Project suspension â€¢ Project restart or â€œgo forwardâ€ â€¢ Procurement options for end user devices â€¢ Operational expenses (OPEX) â€¢ User subscriptions Maintain partnerships with current contracted vendors and N.C. State Representatives to: â€¢ Minimize project risks during suspension â€¢ Identify changes to scope of work in â€œgo forwardâ€ approaches â€¢ Solidify and continue to preserve the projectâ€™s network design â€¢ Identify funding gap resolutions as it relates to project extensions and changes to requirements â€¢ Strengthen relationships with N.C. State CIO and other offices. Presentation to members of the new FirstNet Board and the National Telecommunications and Information Administration (NTIA). Topics included: â€¢ Project Overview â€¢ Technical Aspects of Project â€¢ Lessons Learned â€¢ Path Forward | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project under suspension | N/A | N/A | N/A | N/A | Project under suspension | N/A | No Variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project under suspension | Project under suspension | N/A | Network not yet operational. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The anticipation of a "go forward" plan and agreements that will support both the project/award and funding requirements. | Charlotte, City of | None. | Guidance toward removing suspension and funding suspension cost. | TRUE
NT10BIX5570088 | 2013 | Q1 | Q1 - 2013 | The City of Charlotte remains under a partial grant suspension until such time the City and the First Responder Network Authority (FirstNet) can negotiate a Spectrum Management Lease Agreement. No deployment activities occurred during the first quarter of 2013. The following is a list of non-deployment activities that were accomplished: â€¢ Completed end user device surveys for analysis and requirements of end user devices. â€¢ Held device workshops where vendorâ€™s could share product roadmap and end users could share their needed requirements. â€¢ Continued partnership activities with current contracted vendors to refine a re-start or â€œgo-forwardâ€ approach. â€¢ Developed a "go-forward" task plan and risk plan related to negotiating a spectrum license agreement with FirstNet and restarting Charlotte's broadband grant project. â€¢ Opened negotiations with FirstNet to obtain a lease for use of the Public Safety Spectrum. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project under suspension | N/A | N/A | N/A | N/A | Project under suspension | N/A | Project under suspension | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project under suspension | Project under suspension | N/A | Network not yet operational. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Determination and definition of a "go forward" project approach and plan. | Charlotte, City of | None. | Guidance toward funding opportunities to assist with suspension and possible project extension costs. | TRUE
NT10BIX5570088 | 2013 | Q2 | Q2 - 2013 | The City of Charlotte remains under a partial grant suspension which restricts any LTE deployment activity until such time the City and the First Responder Network Authority (FirstNet) successfully negotiate a Spectrum Management Lease Agreement. Therefore, No deployment activities occurred during the 2nd quarter of 2013. The following is a list of non-deployment activities during the second quarter or 2013: â€¢ Continued the research and planning of end user devices including the sharing of effort with other BTOP recipients for a possible re-issuance of a cooperative purchasing RFP. â€¢ Continued the collaboration effort with other BTOP recipients on the general terms and conditions associated with obtaining 700MHz Spectrum Manager Lease Agreement with FirstNet. â€¢ Continued partnership activities with current contracted vendors to help track all expenses and cost savings for a restart or â€œgo-forwardâ€ approach. â€¢ Requested Grant be extended from July 2013 through September 2013 to complete agreement with FirstNet and define a sustainable "go forward" approach. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is under suspension | N/A | N/A | N/A | N/A | Project is under suspension | N/A | Project is under suspension | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project is under suspension | Project is under suspension | N/A | Network not yet operational | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Complete Spectrum Manager License agreement with FirstNet. Determine Path Forward. Request Grant Extension | Charlotte, City of | None. | Guidance with optional go forward paths being considered. | TRUE
NT10BIX5570088 | 2013 | Q3 | Q3 - 2013 | On August 13 2013, FirstNet, an independent authority within the National Telecommunications and Information Administration (NTIA), ended its negotiations with the City of Charlotte for a Spectrum Management Lease Agreement (SMLA). This agreement was required in order to lift a partial suspension on the Broadband Technology Opportunities Program (BTOP) grant funds and allow the City to continue deploying a 700 MHz public safety cellular network infrastructure. The decision to end negotiations was based on months of effort working with Charlotte to find a successful â€œgo forwardâ€ strategy to overcome deployment and sustainability challenges which came about during the 15 month suspension period. The remaining part of quarter, Charlotte has been consulting with NTIA and its partners on next steps related to the BTOP grant including: â€¢ August 15th Requested BTOP Grant extension to 12/31/2013 in order to restructure the BTOP grant efforts without an SMLA. â€¢ Request additional funds be available to cover expenses through 12/31/2013. â€¢ Began Termination agreements with original BTOP project partners. â€¢ Began efforts to restructure the grant. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is under suspension | N/A | N/A | N/A | N/A | Project is under suspension | N/A | Project is under suspension | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project is under suspension | Project is under suspension | N/A | Network not operational | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Complete efforts to restructure the grant and submit an Award Action Request containing all necessary documents for NTIA review and approval. Including: â€¢ A Modified Project Description and Plan â€¢ A Modified Budget â€¢ A Route Change â€¢ A Request to extend the grant performance period | Charlotte, City of | None. | Assistance from BTOP program manager in reviewing drafted grant restructure documentation for thoroughness and proper filing process. | TRUE
NT10BIX5570088 | 2013 | Q4 | Q4 - 2013 | During the fourth quarter of 2013, the City of Charlotte was engaged in two primary activities. 1. Termination of obligations associated with the original grant to deploy a Long Term Evolution (LTE) broadband infrastructure for public safety network. 2. Restructure the project activities in keeping with original grant purpose to improve Public Safety broadband infrastructure. As a result of these two activities the City of Charlotte: 1. Successfully ended agreements with the primary deployment vendor and several tower lease agreements against the original LTE project. 2. Successfully submitted a restructured "go forward" project plan for the balance of the grant funds which includes a. Repurpose of microwave equipment acquired from the original LTE project. b. Improve Charlotte's outdated & end-of-life Public Safety Network Infrastructure to support future broadband network capacity & speeds. c. Improve Charlotte's outdated & end-of-life Public Safety Vehicular Routers and End User Devices to make use of future broadband network capacity & speeds. 3. Obtained approval and an extension to the grant performance period to begin its restructured effort. 4. Obtained approval to lift the partial suspension placed upon Charlotte grant under the original deployment plan. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project was under suspension most of this period. | N/A | N/A | N/A | N/A | Project was under suspension most of this period. | N/A | Project was under suspension most of this period. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Project was under suspension most of this period. | Project was under suspension most of this period. | N/A | Network not operational | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | During the first quarter of 2014, the City of Charlotte plans to accomplish to following: 1. Complete an approved Route Modification plan and an approved Re-Budget for the approved restructured project. 2. Acquire necessary staffing to manage, architect, secure and plan deployment approach and detail efforts. 3. Define and Acquire and critical path network components consider as highest priority in the deployment approach 4. Evaluate RFQ responses from vendors fro the Dual Band routers. 5. Expect to closeout the original Alcatel-Lucent (ALU) contract. Therefore the payout for partially completed milestones will reflect significant cost in the milestones and budget narratives below. | Charlotte, City of | None. | 1. Reviewing Route Modification and Re-budget submission for assistance in approval. 2. Qualifications/testing and pricing for a dual band router that meets Charlotte and FirstNet's requirements will be a challenge. | TRUE
NT10BIX5570089 | 2010 | Q4 | Q4 - 2010 | Significant project accomplishments include: 1) Establishment of a local project office. 2) Continuation of site environmental assessment activities. 3) Completed RFP process for site assessment vendor subcontractor. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | Project baseline did not project any wholesale provider agreements during this quarter. | Project baseline did not project any wholesale provider agreements during this quarter. | No third party entities were designated to operate any part of this network. | 0 | 0 | 0 | 0 | Project baseline did not project any wholesale provider agreements during this quarter. | Project baseline did not project any wholesale provider agreements during this quarter. | N/A | Per project baseline, no tiers of service were offered in this quarter. | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for the quarter. | Per project baseline, no subscribers service were scheduled for the quarter. | Per project baseline, no subscribers service were scheduled for the quarter. | Per project baseline, no subscribers service were scheduled for the quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for the quarter. | Per project baseline, no subscribers service weres scheduled for the quarter. | Per project baseline, no subscribers service were scheduled for the quarter. | Per project baseline, no subscribers service were scheduled for the quarter. | Per project baseline, no subscribers service were scheduled for the quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for the quarter. | Per project baseline, no subscribers service were scheduled for the quarter. | Per project baseline, no subscribers service were scheduled for the quarter. | Per project baseline, no subscribers service were scheduled for the quarter. | Per project baseline, no subscribers service were scheduled for the quarter. | No special offerings were provided or anticipated to be provided during the quarter. | FALSE | N/A | Significant project accomplishments include: 1) Completion of 200+ site assessments. | Motorola Solutions, Inc. | N/A | The BayWEB grant project is currently challenged by the formation of and negotiations with the public partnersâ€™ Governance Organization with regards to the site readiness and forward-looking business arrangement. In addition, due to the number of sites required in the project and a few last minute changes by some of the participants, we are working hard to complete the National Historic Preservation requirements but are slightly behind schedule. | TRUE
NT10BIX5570089 | 2011 | Q1 | Q1 - 2011 | 200 preliminary site assessments completed. 271 prospective site locations were loaded into TCNS and Tribal notifications started to State and Federally recognized tribes within each county that is part of the project. Consulted with the California SHPO. Consulted with the Native American Heritage Commission on project. Performed consultations with interested State and Federal Tribes. Referred non-responsive Tribes to the FCC for government to government consultation. Continued desk reviews and determinations of sites excluded from Section 106 reviews per the National Programmatic Agreement for the Collocations of Wireless Antennas. Initiated Section 106 consultation work for those sites requiring review . Coverage design reviews held with two major cities and all participating counties to include LTE coverage and backhaul design. Presentations given to the BayWEB policy group regarding site assessments. Initiated contact with a potential wholesaler for the Public Access system. Hosted NTIA representatives for the first project monitoring visit. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | Although the Project Baseline report indicated that Motorola Solutions would have one wholesale provider agreement in place, Motorola has held meetings with wholesale providers but has not finalized an agreement at this time. | Not applicable as there are no agreements in place at this time. | No third parties were designated to operate any part of this network. | 0 | 0 | 0 | 0 | Project baseline did not project any wholesale provider agreements during this quarter. | Although the Project Baseline report indicated that Motorola Solutions would have one wholesale provider agreement in place, Motorola Solutions has held meetings with wholesale providers but has not finalized an agreement at this time. | N/A | Per project baseline, no tiers of service were offered in this quarter. | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | No special offerings were provided or anticipated to be provided during the quarter. | FALSE | N/A | Completion of Section 106 determinations and final report submittal for all identified sites. Commencement of site engineering activities including transmission engineering, structural analysis and microwave frequency coordination. Continue engineering efforts to finalize coverage requirements and backhaul design. Initiate meetings with potential fiber providers. Continue negotiations with potential Public Access wholesalers. Continue to support the formation of the Joint Power Authority (JPA) for the BayWEB system. | Motorola Solutions, Inc. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other initial program delays. These delays are primarily due to our public safety partners continuing efforts to create a JPA and finalize negotiation and signature of the BOOM agreement with Motorola. | The BayWEB grant project is currently challenged by the formation of and negotiations with the public partnersâ€™ Joint Powers Authority with regards to the site readiness and forward-looking business arrangement. In addition, due to the number of sites required in the project and a few last minute changes by some of the participants, we are working hard to complete the National Historic Preservation requirements and are on schedule to complete this requirement based upon the extension of the SAC #12. | TRUE
NT10BIX5570089 | 2011 | Q2 | Q2 - 2011 | Tribal notifications were completed to State and Federally recognized tribes within each county that is part of the project for the prospective site locations. 22 sites were referred to the California SHPO for 106 review and all required documentation was submitted. Completed consultations with the Native American Heritage Commission on project. Completed consultations with interested State and Federal Tribes. Completed desk reviews and determinations of sites excluded from Section 106 reviews per the National Programmatic Agreement for the Collocations of Wireless Antennas and received notification of lifting of the SAC #12. Continued coverage design reviews held with the two major cities and all participating counties to include LTE coverage and backhaul design. Continued contacts with a potential wholesalers and WISP's for the Public Access system. Continued negotiations with representatives of the still forming BayWEB JPA to finalize the BOOM system operations agreement. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | N/A | N/A | N/A | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | 0 | 0 | 0 | Although the Project Baseline report indicated that Motorola Solutions would have two wholesale provider agreement in place, Motorola has held meetings with wholesale providers but has not finalized an agreement at this time. | Not applicable as there are no agreements in place at this time. | No third parties were designated to operate any part of this network. | 0 | 0 | 0 | 0 | Project baseline did not project any wholesale provider agreements during this quarter. | Although the Project Baseline report indicated that Motorola Solutions would have two wholesale provider agreement in place, Motorola Solutions has held meetings with wholesale providers but has not finalized an agreement at this time. | N/A | Due to the fact that no agreements have been finalized with wholesale providers, no tiers of service were available for the previous quarter. | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | No special offerings were provided or anticipated to be provided during the quarter. | FALSE | N/A | Continuation of site engineering activities including transmission engineering, structural analysis and microwave frequency coordination/ interference analysis. Continue engineering efforts to finalize coverage requirements and backhaul design. Continue meetings with potential fiber providers. Continue negotiations with potential Public Access wholesalers. Continue to support the formation of the Joint Power Authority (JPA) for the BayWEB system. Continue negotiations to complete a BOOM operations agreement for the operation of the BayWEB system between Motorola Solutions and the BayWEB JPA. | Motorola Solutions, Inc. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization of an agreement for the use of the identified network site owners. These delays are primarily due to our public safety partners continuing efforts to create a JPA and finalize negotiation and signature of the BOOM agreement with Motorola. In addition, Motorola is currently in the process of bidding the LTE network equipment which has caused a delay in the timing of equipment ordering. | The BayWEB grant project continues to be challenged by the formation of and negotiations with the public partnersâ€™ Joint Powers Authority with regards to the site readiness and forward-looking business arrangement. | TRUE
NT10BIX5570089 | 2011 | Q3 | Q3 - 2011 | Continued site engineering activities including transmission engineering, structural analysis and microwave frequency coordination/ interference analysis. Continued engineering efforts to finalize coverage requirements and backhaul design with the representative of the BayWEB jurisdictions . Conducted meetings with potential fiber providers and potential Public Access wholesalers. Successfully supported the formation of the Joint Power Authority (JPA) for the BayWEB system. Continued negotiations to complete a Build, Own, Operate and Maintain (BOOM) agreement for the BayWEB system between Motorola Solutions and the BayWEB JPA. Held competition and selected vendor for the LTE core and eNodeB equipment. Held initial kick-off meeting with the successful vendor. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | N/A | N/A | N/A | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | 0 | 0 | 0 | Although the Project Baseline report indicated that Motorola Solutions would have three wholesale provider agreement in place, Motorola has held meetings with wholesale providers but has not finalized an agreement at this time. | Not applicable as there are no agreements in place at this time. | No third parties were designated to operate any part of this network. | 0 | 0 | 0 | 0 | Project baseline did not project any wholesale provider agreements during this quarter. | Although the Project Baseline report indicated that Motorola Solutions would have three wholesale provider agreement in place, Motorola Solutions has held meetings with wholesale providers but has not finalized an agreement at this time. | N/A | Due to the fact that no agreements have been finalized with wholesale providers, no tiers of service were available for this quarter. | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | Due to the fact that no agreements have been finalized with subscribers, no tiers of service were available for this quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | No special offerings were provided or anticipated to be provided during the quarter. | FALSE | N/A | Finalize the location of the BayWEB system core facility. Sign Site Use Agreements with all participating jurisdictions committing sites to the network. Support negotiations between the Joint Powers Authority (JPA) and potential backhaul providers. Complete negotiations for the BOOM agreement. Complete internal project audit by October 31st. Participate in scheduled NTIA Site Visit. Continue search for qualified wholesalers for the Public Access system. Enter into a contract with selected LTE equipment vendor. | Motorola Solutions, Inc. | The BayWEB project continues to be challenged with the public partnersâ€™ Joint Powers Authority capacity to affect the site readiness, backhaul commitment, resolution of open regulatory issues and completion of the business arrangement. | There is risk to completion of the listed project milestones within the next quarter due to the challenges of arriving at agreements related to site use, site readiness and operating agreements. | TRUE
NT10BIX5570089 | 2011 | Q4 | Q4 - 2011 | Finalized the location of the BayWEB system core facility. Signed Site Use Agreements with two participating jurisdictions committing sites to the network. Continued to support negotiations between the Joint Powers Authority (JPA) and potential back-haul providers. Completed negotiations for the BOOM agreement. Completed internal project audit by October 31st. Participated in scheduled NTIA Site Visit. Continued negotiations for entering into a contract with selected LTE equipment vendor. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreements with the owners. | N/A | N/A | N/A | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreements with the owners. | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreements with the owners. | 0 | 0 | 0 | Although the Project Baseline report indicated that Motorola Solutions would have four wholesale provider agreement in place, Motorola has held meetings with wholesale providers but has not finalized an agreement at this time. | Not applicable as there are no agreements in place at this time. | No third parties were designated to operate any part of this network. | 0 | 0 | 0 | 0 | Project baseline did not project any wholesale provider agreements during this quarter. | Although the Project Baseline report indicated that Motorola Solutions would have four wholesale provider agreement in place, Motorola Solutions has held meetings with wholesale providers but has not finalized an agreement at this time. | N/A | Due to the fact that no agreements have been finalized with wholesale providers, no tiers of service were available for this quarter. | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | Due to the fact that no agreements have been finalized with subscribers, no tiers of service were available for this quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | No special offerings were provided or anticipated to be provided during the quarter. | FALSE | N/A | Motorola intends to execute a BOOM agreement with the JPA by January. Motorola intends to execute Site Access and Use Agreements with all participating jurisdictions by February. Motorola intends to submit a revised Budget and associated AAR for Change of Scope by the end of the quarter. Continue site engineering, complete equipment design, sign equipment vendor contracts and prepare equipment orders. | Motorola Solutions, Inc. | The BayWEB project continues to be challenged with the public partnersâ€™ Joint Powers Authority capacity to affect the site readiness, back-haul commitment, resolution of open regulatory issues and completion of the business arrangement. | There is risk to completion of the listed project milestones within the next quarter due to the challenges of arriving at agreements related to site use, site readiness and operating agreements. | TRUE
NT10BIX5570089 | 2012 | Q1 | Q1 - 2012 | Executed a Build, Own, Operate and Maintain (BOOM) agreement with the BayRICS Authority (a.k.a. the JPA). Entered into Site Access & Use (SAU) agreements with a total of nine jurisdictions to secure long-term agreements for LTE sites. Walked sites in conjunction with the backhaul owner and contractors, to assess lateral fiber runs at each site. In coordination with our vendor, developed and began reviews of the LTE equipment lists. Participated in a site visit to the Harris County, TX LTE system. Attended the PSCR conference in Boulder, CO. Submitted to NTIA a Route Modification Request to address scope changes in the system design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of site use agreements with the owners. | N/A | N/A | N/A | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of site use agreements with the owners. | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of site use agreements with the owners. | 0 | 0 | 0 | Although the Project Baseline report indicated that Motorola Solutions would have four wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA during the quarter. | See 5b. | No third parties were designated to operate any part of this network. | 0 | 0 | 0 | 0 | Although the Project Baseline report indicated that Motorola Solutions would have one wholesale provider agreement in place for new access, Motorola Solutions has held meetings with wholesale providers but has not finalized an agreement at this time. | Although the Project Baseline report indicated that Motorola Solutions would have four wholesale provider agreements in place for improved access, Motorola Solutions has held meetings with wholesale providers but has not finalized an agreement at this time. | N/A | No speed tiers are available at this time. | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and the finalization of a site use agreement with the BayWEB JPA. | Due to the fact that no agreements have been finalized with subscribers, no tiers of service were available for this quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | No special offerings were provided or anticipated to be provided during the quarter. | FALSE | N/A | Enter into a contract with vendor for the LTE equipment and microwave equipment. Final Bills of Material for LTE equipment and for microwave equipment are expected to be completed during the upcoming period. Support negotiations between the Authority and the backhaul provider for use of fiber and sites. Advantage will be taken of the time to continue negotiation with site owners to increase the commitment of infrastructure to the network where possible. Site engineering and planning will continue in anticipation of being allowed to order equipment from vendors for installation. | Motorola Solutions, Inc. | During the past quarter, there were no significant additional issues that would have benefitted from technical assistance from the BTOP program. | There is risk to completion of the listed project milestones within the next quarter due to the challenges of arriving at agreements related to site use, site readiness and operating agreements, and to inefficiencies that likely will result from the anticipated partial suspension of the Grant as suggested by NTIA. | TRUE
NT10BIX5570089 | 2012 | Q2 | Q2 - 2012 | Continued to support negotiations between BayRICS JPA and potential backhaul providers. Continued site zoning and permitting process with local governing agencies. As part of the activities caused by NTIAâ€™s decision to partially suspend our grant and as directed by the NTIA, Motorola has taken steps to preserve the BayWEB projectâ€™s viability. The actions taken include cessation of tasks that are directly related to LTE equipment. All new activities planned to be undertaken during the partial suspension are intended to align with the nationwide public safety broadband network as it is currently described. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | N/A | N/A | N/A | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | 0 | 0 | 0 | Although the Project Baseline report indicated the Motorola Solutions would have six wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA during the first quarter of this year. | See 5b. | No third parties were designated to operate any part of this network. | 0 | 0 | 0 | 0 | Although the Project Baseline report indicated the Motorola Solutions would have one wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA during the first quarter of this year. | Although the Project Baseline report indicated the Motorola Solutions would have five wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA during the first quarter of this year. | N/A | No speed tiers are available at this time. | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | Due to the fact that no agreements have been finalized with subscribers, no tiers of service were available for this quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | No special offerings were provided or anticipated to be provided during the quarter. | FALSE | N/A | Receive zoning approval for many of the sites planned for use in the system. Support negotiations between the BayRICS Authority and the backhaul providers for use of fiber and sites. Prepare for the eventual improvements to be made to sites that are planned for use in the system. No LTE related equipment will be ordered due to the partial suspension on those activities. | Motorola Solutions, Inc. | The partial suspension of LTE related expenditures had a major impact on the program's progress during the past quarter. The impact of the partial suspension is expected to have an increased effect on the program as time continues due to the uncertainty that it creates. | All expected Site Access & Use agreements (SAU's) have been signed with the sites' owners and/or controllers, except for an agreement between the BayRICS Authority and BART. BART is expected to provide a significant portion of the central backhaul transport network and a portion of the LTE sites. Once an agreement is reached between those parties, Motorola Solutions will need to enter a SAU agreement with the Authority that covers the use of those facilities. Issues encountered during either negotiations could adversely impact the anticipated timeline for completion of related tasks. Additionally, the partial suspension of LTE related activities has created uncertainties that will need to be resolved for progress to be maintained at the expected rate. | TRUE
NT10BIX5570089 | 2012 | Q3 | Q3 - 2012 | Continued to support negotiations between BayRICS JPA and potential backhaul providers. Continued site zoning and permitting process with local governing agencies. As part of the activities caused by NTIAâ€™s decision to partially suspend our grant and as directed by the NTIA, Motorola has taken steps to preserve the BayWEB projectâ€™s viability. The actions taken include cessation of tasks that are directly related to LTE equipment. All new activities planned to be undertaken during the partial suspension are intended to align with the nationwide public safety broadband network as it is currently described. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | N/A | N/A | N/A | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | 0 | 0 | Although the Project Baseline report indicated the Motorola Solutions would have six wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | See 5b | No third parties were designated to operate any part of this network. | 0 | 0 | 0 | 0 | Although the Project Baseline report indicated the Motorola Solutions would have one wholesale provider agreement in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | Although the Project Baseline report indicated the Motorola Solutions would have five wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | N/A | No speed tiers are available at this time. | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | Due to the fact that no agreements have been finalized with subscribers, no tiers of service were available for this quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | 0 | 0 | 0 | 0 | 0 | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | Per project baseline, no subscribers service were scheduled for this quarter. | No special offerings were provided or anticipated to be provided during the quarter. | FALSE | N/A | Continue working toward zoning approval for the remaining the sites planned for use in the system. Support negotiations between the BayRICS Authority and the backhaul providers for use of fiber and sites. Prepare for the eventual improvements to be made to sites that are planned for use in the system. No LTE related equipment is anticipated to be ordered until the partial suspension on those activities has been lifted. | Motorola Solutions, Inc. | The partial suspension of LTE related expenditures has continued to have a major impact on the program's progress during the past quarter. The impact of the partial suspension is expected to have an increased effect on the program as time continues due to the uncertainty that it creates. Work has continued in support of achieving zoning approval for the sites that currently are planned to comprise the system, but all LTE-related activities have been suspended as directed by NTIA. | The agreement between the BayRICS Authority and BART is not complete. BART is expected to provide a significant portion of the central backhaul transport network and a portion of the LTE sites. Once an agreement is reached between those parties, Motorola Solutions will need to enter a SAU agreement with the Authority that covers the use of those facilities and perhaps facilities owned by others. Issues encountered during either negotiations could adversely impact the anticipated timeline for completion of related tasks. Additionally, the partial suspension of LTE related activities has created uncertainties that will need to be resolved for progress to be maintained at the expected rate. It is anticipated that the BOOM agreement between Motorola and the Authority will be impacted by FirstNet's operation plans as will the SAUs that currently exist between Motorola and the various site owners/controllers. These agreements will be subject to renegotiation after FirstNet discloses its detailed plan. | TRUE
NT10BIX5570089 | 2012 | Q4 | Q4 - 2012 | Motorola Solutions participated in a site visit with members of the First Responder Network Authority (FirstNet) board, BayRICS executives, NTIA, a State of California representative, a representative from the Office of the Mayor of San Francisco, the Police Chief of City of San Francisco, director of San Francisco's Emergency Management Authority, and Motorola Solutions executives. The site visit participants reviewed the program performance to date and a evaluation of the ultimate integration of the BAYWEB network into the Nationwide Public Safety Broadband Network (NPSBN). In addition, Motorola continues to support negotiations between the BayRICS Authority and potential backhaul providers. We continued efforts in support of site zoning and permitting process with local governing agencies. Motorola Solutions preserved the capacity to continue the project after the suspension is lifted. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | N/A | N/A | N/A | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | 0 | 0 | Although the Project Baseline report indicated the Motorola Solutions would have seven wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | See 5b | No third parties were designated to operate any part of this network. | 0 | 0 | 0 | 0 | Although the Project Baseline report indicated that Motorola Solutions would have two wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | Although the Project Baseline report indicated that Motorola Solutions would have five wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | N/A | No speed tiers are available at this time. | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | Due to the fact that no agreements have been finalized with subscribers, no tiers of service were available for this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings were provided or anticipated to be provided during the quarter. | FALSE | N/A. | We anticipate receiving guidance from FirstNet and the NTIA by middle of the upcoming quarter. Based on that guidance Motorola will pursue the necessary details with FirstNet and NTIA to allow continued progress on the project. The next quarter project indicators below anticipate progress towards that goal. We anticipate applying for a no-cost extension of this grant once the templates and instructions are available from NTIA. No LTE related equipment is anticipated to be ordered until the partial suspension on those activities has been lifted. | Motorola Solutions, Inc. | The extended partial suspension of LTE related expenditures has continued to have a major impact on the program's progress during the past quarter. | We await a favorable a decision from FirstNet and NTIA concerning BAYWEB. Many tasks necessary for the deployment of this system remain frozen as a result of the partial suspension along with the delayed approval of the Route Modification requested by Motorola Solutions. Guidance early in the upcoming quarter will enable Motorola to gain positive momentum on this project. | TRUE
NT10BIX5570089 | 2013 | Q1 | Q1 - 2013 | In coordination with other BTOP recipients and spectrum lessees, substantial progress was made in preparing documents and negotiation with FirstNet for the eventual Spectrum Management Lease Agreement (SMLA). MSI conducted follow up tasks for action items from last quarter's FirstNet/NTIA site visit to BayWEB. We conferred with our Program Officer and FirstNet to begin preparations to reinitiate the NTIA review of our Route Modification which has been tabled since the beginning of the partial suspension period. Limited work continued in support of FCC licensing for the microwave backhaul subsystem and in support of zoning approvals for some of the planned RAN sites. MSI participated in the BayRICS Authority's Technical Advisory Group reviews of technology and met with 4G Partners to provide an overview of site requirements. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | n/a | n/a | n/a | n/a | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | n/a | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | 0 | 0 | Although the Project Baseline report indicated the Motorola Solutions would have seven wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | See 5b. | No third parties were designated to operate any part of this network.. | 0 | 0 | 0 | 0 | Although the Project Baseline report indicated the Motorola Solutions would have two wholesale provider agreement in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | Although the Project Baseline report indicated the Motorola Solutions would have five wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | n/a | No speed tiers are available at this time. | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | Due to the fact that no agreements have been finalized with subscribers, no tiers of service were available for this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings were provided or anticipated to be provided during the quarter. | FALSE | N/A | We anticipate the satisfactory conclusion of the SMLA between FirstNet and spectrum lessees. We expect to complete and submit our BTOP Award Period Extension Request Letter and Template and anticipate a favorable decision in its approval. We plan on meeting the NTIA's requirements such that the review and evaluation of our submitted Route Modification can be continued and hope for its eventual approval. We plan a meeting with NTIA and our environmental contractor to define procedures and details that relate to a redefined environmental review and approval process. We expect to arrive at an agreement with FirstNet for "Key Learnings" to be derived from the early deployment of the BayWEB system. If the partial suspension is lifted during the upcoming period, we will resume work to result in the eventual placing of orders for LTE equipment and services. | Motorola Solutions, Inc. | Although FirstNet is working with recipients/spectrum lessees closely to fulfill all requirements to cause NTIA to rescind the partial suspension of all grants, the lifting of the suspension has not yet occurred. In the year that has passed since the partial suspension was invoked, reassignment of resources has resulted in a significant loss of momentum among local stakeholders insofar as continued efforts for the regulatory preparation of sites for inclusion in the network. | Although substantial progress in arriving at consensus among BTOP recipients and FirstNet on project-related topics was made during the past period, many tasks necessary for the deployment of this system remain frozen as a result of the partial suspension. We anticipate that this constructive relationship among all stakeholders will continue and that the lifting of the partial suspension lies not too far in the future. One factor that could significantly improve the early availability of "Key Learnings" to FirstNet would be to find a solution that effectively accommodates interim construction on sites as they become environmentally-approved, as opposed to awaiting approval for ALL sites prior to beginning work on any. We hope to explore alternatives with NTIA in seek of a solution. | TRUE
NT10BIX5570089 | 2013 | Q2 | Q2 - 2013 | In coordination with other BTOP recipients and spectrum lessees, substantial progress was made in preparing documents and negotiation with FirstNet for the eventual Spectrum Management Lease Agreement (SMLA). We arrived at an agreement with FirstNet for "Key Learnings" to be derived from the early deployment of the BayWEB system. MSI met with FirstNet and its consultants, along with representatives in San Bruno, CA, to discuss the business aspects of the project, MSI applied for a short term BTOP Award Period Extension through September 30, 2013. This was subsequently approved and countersigned by NTIA and Motorola. We worked closely with NTIA's environmental consultants in an effort to retain our BTOP and DOC Categorical Exclusions for our route modification. We provided a significant number of Site narratives and are awaiting review and comment from NTIA's representatives. Limited work continued in support of FCC licensing for the microwave backhaul subsystem and in support of zoning approvals for some of the planned RAN sites. MSI attended the PSCR conference in Westminster, CO for a technology update. MSI met with representatives from FirstNet and NTIA while in Colorado. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | N/A | N/A | N/A | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | 0 | 0 | Although the Project Baseline report indicated the Motorola Solutions would have seven wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | See 5b | No third parties were designated to operate any part of this network. | 0 | 0 | 0 | 0 | Although the Project Baseline report indicated the Motorola Solutions would have two wholesale provider agreement in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | Although the Project Baseline report indicated the Motorola Solutions would have five wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | N/A | No speed tiers are available at this time. | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | Due to the fact that no agreements have been finalized with subscribers, no tiers of service were available for this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | NA | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings were provided or anticipated to be provided during the quarter. | FALSE | N/A | We anticipate the satisfactory conclusion of the SMLA between FirstNet and spectrum lessees. We expect to complete and submit our long-term BTOP Award Period Extension Request Letter and Template and anticipate a favorable decision in its approval. We plan on meeting the NTIA's requirements such that the review and evaluation of our submitted Route Modification can be continued and hope for its eventual approval. We will continue to work with NTIA and our environmental contractor to finish the required narratives to confirm our categorical exclusion and conduct necessary work on Section 106 to complete SAC 12 by the end of the year. If the partial suspension is lifted during the upcoming period, we will resume work to result in the eventual placing of orders for LTE equipment and services. | Motorola Solutions, Inc. | Although FirstNet is working with recipients/spectrum lessees closely to fulfill all requirements to cause NTIA to rescind the partial suspension of all grants, the lifting of the suspension has not yet occurred. In the year that has passed since the partial suspension was invoked, reassignment of resources has resulted in a significant loss of momentum among local stakeholders insofar as continued efforts for the regulatory preparation of sites for inclusion in the network. | Although substantial progress in arriving at consensus among BTOP recipients and FirstNet on project-related topics was made during the past period, many tasks necessary for the deployment of this system remain frozen as a result of the partial suspension. We anticipate that this constructive relationship among all stakeholders will continue and that the lifting of the partial suspension lies not too far in the future. FirstNet has extended their estimation to complete the SMLA an additional 30 days. | TRUE
NT10BIX5570089 | 2013 | Q3 | Q3 - 2013 | In coordination with other BTOP recipients and spectrum lessees, substantial progress was made in preparing documents and negotiation with FirstNet for the eventual Spectrum Management Lease Agreement (SMLA). MSI met with consultants of FirstNet concerning about aspects of the project. MSI applied for and were granted a short term BTOP Award Period Extension through December 31, 2013. We worked closely with NTIA's environmental consultants in an effort to retain our BTOP and DOC categorical exclusions for our route modification. We provided all Site drafts narratives. Limited work continued in support of FCC licensing for the microwave backhaul subsystem and in support of zoning approvals for some of the planned RAN sites. We supported the NTIA submittal for tribal notification for Federal tribes. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | N/A | N/A | N/A | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. | 0 | 0 | 0 | Although the Project Baseline report indicated the Motorola Solutions would have seven wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | See 5b | No third parties were designated to operate any part of this network. | 0 | 0 | 0 | 0 | Although the Project Baseline report indicated the Motorola Solutions would have two wholesale provider agreement in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | Although the Project Baseline report indicated the Motorola Solutions would have five wholesale provider agreements in place, the unavailability of sites to accommodate the Public Access system has caused the latter to be removed from the design. This is a portion of the Route Modification request made to NTIA. | N/A | No speed tiers are available at this time. | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays in the finalization and readiness of sites and other program delays. The LTE equipment portion of this program is on partial suspension as is the case for other similar programs. | Due to the fact that no agreements have been finalized with subscribers, no tiers of service were available for this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings were provided or anticipated to be provided during the quarter. | FALSE | N/A | We anticipate the satisfactory conclusion of the SMLA between FirstNet and spectrum lessees. We expect to complete and submit our long-term BTOP Award Period Extension Request Letter and Template and anticipate a favorable decision in its approval. We plan on meeting the NTIA's requirements such that the review and evaluation of our submitted Route Modification can be continued and hope for its eventual approval. We will continue to work with NTIA and our environmental contractor to finish the required narratives to confirm our categorical exclusion and conduct necessary work on Section 106 to complete SAC 12 by the end of the year. If the partial suspension is lifted during the upcoming period, we will resume work to result in the eventual placing of orders for LTE equipment and services. | Motorola Solutions, Inc. | Although FirstNet is working with recipients/spectrum lessees closely to fulfill all requirements to cause NTIA to rescind the partial suspension of all grants, the lifting of the suspension has not yet occurred. In the 15 months that has passed since the partial suspension was invoked, reassignment of resources has resulted in a significant loss of momentum among local stakeholders insofar as continued efforts for the regulatory preparation of sites for inclusion in the network. | Although substantial progress in arriving at consensus among BTOP recipients and FirstNet on project-related topics was made during the past period, many tasks necessary for the deployment of this system remain frozen as a result of the partial suspension. Due to Government shutdown in October caused logistical issues on all tasks and processes. FirstNet has extended the negotiating period for the the SMLA until November 15, 2013 JPA and Motorola are working to meet that date. Receipt of the executed SMLA in this quarter is critical for the timely program completion. | TRUE
NT10BIX5570089 | 2013 | Q4 | Q4 - 2013 | Motorola completed and NTIA accepted our Route Modification. All work to support environmental reporting requirements was completed and prepared to be submitted. Negotiations continued with FirstNET and the BayRICS Joint Powers Authority (JPA) to reach agreement on a Spectrum Management Lease Agreement for the proposed system. Unfortunately, no agreement was able to be reached and Motorola submitted a termination for convenience of the Grant on December 30th 2013. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays due to the partial suspension and ultimate expiration of the grant. | N/A | N/A | N/A | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays due to the partial suspension and ultimate expiration of the grant. | N/A | The indicated variance from the baseline plan for the previous quarter occurred as a result of delays due to the partial suspension and ultimate expiration of the grant. | 0 | 0 | 0 | N/A | N/A | No third parties were designated to operate any part of this network. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No subscribers were connected. The partial suspension of the Grant and its subsequent expiration prevented the project from performing any implementation activities. | N/A. No subscribers were connected. The partial suspension of the Grant and its subsequent expiration prevented the project from performing any implementation activities. | N/A. No subscribers were connected. The partial suspension of the Grant and its subsequent expiration prevented the project from performing any implementation activities. | N/A. No subscribers were connected. The partial suspension of the Grant and its subsequent expiration prevented the project from performing any implementation activities. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings were provided or anticipated to be provided during the quarter. | FALSE | N/A | Motorola will work with the NTIA and Grants Office to complete all necessary reporting and audit requirements in order to close out the BTOP grant. | Motorola Solutions, Inc. | Negotiations continued with FirstNET and the BayRICS Joint Power Authority (JPA) to reach agreement on a Spectrum Management Lease Agreement (SMLA) for the proposed system. Unfortunately, no agreement was able to be reached and Motorola submitted a termination for convenience of the Grant on December 30th 2013. | Negotiations continued with FirstNET and the BayRICS Joint Powers Authority to reach agreement on a Spectrum Management Lease Agreement for the proposed system. Unfortunately, no agreement was able to be reached and Motorola submitted its Grant termination request December 30th 2013. Motorola will work with the NTIA and Grants Office to complete all necessary reporting and audit requirements in order to close out the BTOP grant. | TRUE
NT10BIX5570090 | 2010 | Q4 | Q4 - 2010 | Preliminary design is finished with the final routing for environmental assessment (EA). Design has started. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | On target | N/A | On target | N/A | On target | N/A | N/A | N/A | 17 | 0 | 8 | United Telephone Mutual Aide Corporation, Dakota Central Telecommunications Cooperative, Midstate Telephone Company, ND Information Technology Department, MLGC, ND Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, ICTC, Reservation Telephone Cooperative, SRT Communications, Consolidated Telecom, Red River Telephone, SDN Communications | No wholesale services will be provided. | N/A | 0 | 0 | 0 | 0 | On Schedule | On Schedule | N/A | On Schedule | 0 | 0 | 0 | 3 | On Schedule | On Schedule | On Schedule | No Varriations | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Finish environmental Assessment. Complete the design of the Bismarck and Mandan area and partner project which equals 50% of the project. Prepare to solicit pricing for cable placement, equipment and start equipment installation. | DCN, LLC | The project is moving forward and on schedule. | None at this time. | TRUE
NT10BIX5570090 | 2011 | Q1 | Q1 - 2011 | Preliminary design is finished with the final routing for environmental assessment (EA). 90% design complete for Bismarck and Mandan, ND sites. SRT sites designed and ready for bid. NCL sites designed and ready for bid. Final EA 90% complete, worked with Ft. Peck Tribe. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | On target, start development when EA is approved. | N/A | On target, start development when EA is approved. | N/A | On target, start development when EA is approved. | N/A | N/A | N/A | 0 | 0 | 8 | No wholesale providers. | No wholesale services will be provided. | DCN does not have a designated third party to operate the network. | 0 | 0 | 0 | 100 | On Schedule | On Schedule | N/A | On Schedule. Note Speeds are 5 mbps, 10 mbps, 20 mbps, 50 mbps and 100 mbps | 0 | 0 | 0 | 100 | On Schedule | On Schedule | On Schedule | On Schedule. Note Speeds are 5 mbps, 10 mbps, 20 mbps, 50 mbps and 100 mbps | 0 | 0 | 0 | 0 | 0 | No Varriations | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time no special offerings will be made. | FALSE | N/A | Finish environmental Assessment. Complete the design of the Bismarck and Mandan area and partner project which equals 60% of the project. Prepare to solicit pricing for cable placement, equipment and start equipment installation. | DCN, LLC | The project is moving forward and behind schedule with outside plant (cable) work due to extra work and delay in responding to TCNS comments. Preparing an ethnographic report for work outside previously disturbed areas for an entity in Montana. Reports are to be delivered week of May 2nd. This request will delay constructions a minimum of 30 days. Equipment procurement is not an issue as far as schedule since we need fiber cable to turn up at sites. (We have shifted this equipment schedule.) | Working with TCNS comments. Did not receive them from NTIA until February 23rd. Need to work with entity requesting ethnographic reports to satisfy his concerns. (Fort Peck Tribes, Curly Youpee, Poplar, MT.) Due to limited construction season in ND, we will shift schedule but will finish before deadline. | TRUE
NT10BIX5570090 | 2011 | Q2 | Q2 - 2011 | Preliminary design is finished with the final routing for environmental assessment (EA). 90% design complete for Bismarck and Mandan, ND sites. SRT Communications sites designed and ready for bid. Northwest Communications Cooperative sites designed and ready for bid. Final EA 100% complete, worked with Ft. Peck Tribe. | 0 | 0 | 0 | 1388 | 0 | 0 | 0 | 0 | Will start by end of July due to delay in EA. | N/A | will get started by end of July due to delay in EA | N/A | will get started by end of July due to delay in EA | N/A | N/A | N/A | 17 | 0 | 0 | Last Mile Providers: BEK Communications, United Telephone Mutual Aide Corporation, Dakota Central Telecommunications Cooperative, SDN Communications, Midstate Telephone Company, North Dakota Information Technology Department, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, Reservation Telephone Cooperative, SRT Communications, Consolidated Telecom Company, and Red River Telephone | No wholesale services will be provided. | DCN does not have a designated third party to operate the network. | 0 | 0 | 0 | 100 | On Schedule | On Schedule | N/A | On Schedule. Note Speeds are 5 mbps, 10 mbps, 20 mbps, 50 mbps and 100 mbps | 0 | 0 | 0 | 100 | On Schedule | On Schedule | On Schedule | On Schedule. Note Speeds are 5 mbps, 10 mbps, 20 mbps, 50 mbps and 100 mbps | 0 | 0 | 0 | 0 | 0 | No Varriations | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time no special offerings will be made. | FALSE | N/A | Award contracts for cable placement. Start construction in Bismarck and Mandan area and partner project which equals 60% of the project. | DCN, LLC | The project is moving forward and is behind schedule with outside plant (cable) work due to extra work and delay in responding to TCNS comments. DCN has received our FONSI. Equipment procurement is not an issue as far as schedule since we need fiber cable to turn up at sites. (We have shifted this equipment schedule.) We will try to make up some of the lost time to the EA, however the weather is still a factor. Fiber may be an issue be we have the majority on order to line up with construction. W have enought time in our schedule to make this up in 2012 by providing more construction resources. | Weather may be an issue due to the late construction start. We do not have many construction days left in 2011. Fiber availability may be an issue but we have orders in and should get enough to finish out Mandan, Bismarck, Grand Forks and subrecipient routes before freeze up. | TRUE
NT10BIX5570090 | 2011 | Q3 | Q3 - 2011 | 90% design complete for Bismarck and Mandan, ND sites. Construction is proceeding in Bismarck. SRT Communications sites have been awarded and construction has begun. Northwest Communications Cooperative sites designed and awarded, but waiting for construction to start. DCT sites awarded and construction begun. | 10 | 0 | 0 | 1388 | 10 | 0 | 0 | 0 | Due to delay in EA | N/A | Due to delay in EA | N/A | Due to delay in EA | N/A | N/A | N/A | 17 | 0 | 30 | Last Mile Providers: BEK Communications, United Telephone Mutual Aide Corporation, Dakota Central Telecommunications Cooperative, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, Reservation Telephone Cooperative, SRT Communications, Consolidated Telecom Company, Red River Telephone, West River Telecommunications, Dickey Rural, Idea One, and Midstate Communications. | Last Mile Providers: BEK Communications, United Telephone Mutual Aide Corporation, Dakota Central Telecommunications Cooperative, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, Reservation Telephone Cooperative, SRT Communications, Consolidated Telecom Company, Red River Telephone, West River Telecommunications, Dickey Rural, Idea One, and Midstate Communications. | DCN does not have a designated third party to operate the network. | 0 | 0 | 0 | 5 | N/A | N/A | N/A | On schedule. Note speeds are 5 mbps, 10 mbps, 20 mbps, 50 mbps and 100 mbps | 0 | 0 | 0 | 5 | Late start due to EA. Connections should start in Nov. 2011. | Late start due to EA | Late start due to EA | On schedule. Note speeds are 5 mbps, 10 mbps, 20 mbps, 50 mbps and 100 mbps | 0 | 0 | 0 | 0 | 0 | No varriations | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time no special offerings will be made. | FALSE | N/A | Started cable placement. Stared construction in Bismarck and Fargo area. SRT and DCT construction started. New network miles deployed is 20 total. New network miles leased is not applicable. Total CAI subscribers served is eight. Number of wholesale/ last mile providers is 17. | DCN, LLC | The project is moving forward and is behind schedule with outside plant (cable) work due to extra work and delay in responding to TCNS comments. DCN has received our FONSI. Equipment procurement is not an issue as far as schedule since we need fiber cable to turn up at sites. (We have shifted this equipment schedule.) We will try to make up some of the lost time to the EA, however the weather is still a factor. Fiber may be an issue be we have the majority for 2011. We have enough time in our schedule to make this up in 2012 by providing more construction resources. | Weather may be an issue due to the late construction start. We do not have many construction days left in 2011. We will shut down outside construction in November due to the weather. | TRUE
NT10BIX5570090 | 2011 | Q4 | Q4 - 2011 | 100% of the design is complete for Bismarck, Fargo, and Mandan, ND sites. Construction is still proceeding in Bismarck. SRT Communications sites have been awarded and construction has begun. Northwest Communications Cooperative sites designed and awarded, but waiting for construction to start in the spring. DCT sites were awarded and the construction is complete. | 48 | 0 | 0 | 1388 | 48 | 0 | 0 | 0 | Behind due to delay in Environmental Assessment. | N/A | N/A | N/A | Behind due to delay in Environmental Assessment. | N/A | N/A | N/A | 17 | 0 | 7 | Last Mile Providers: BEK Communications, United Telephone Mutual Aide Corporation, Dakota Central Telecommunications Cooperative, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, Reservation Telephone Cooperative, SRT Communications, Consolidated Telecom Company, Red River Telephone, West River Telecommunications, Dickey Rural, Idea One, and Midstate Communications. | Last Mile Providers: BEK Communications, United Telephone Mutual Aide Corporation, Dakota Central Telecommunications Cooperative, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, Reservation Telephone Cooperative, SRT Communications, Consolidated Telecom Company, Red River Telephone, West River Telecommunications, Dickey Rural, Idea One, and Midstate Communications. | DCN does not have a designated third party to operate the network. Sub recipients will own and maintain the fiber within their network and charge DCN for the circuits. DCN will own, operate and manage the entire electronics network for all CAI's. Sub recipients maintaining the their fiber are: BEK Communications, Dakota Central Telecommunications, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, SRT Communications, Consolidated Telecom Company, and Red River Telephone. | 0 | 0 | 0 | 5 | N/A | N/A | N/A | Speeds are 5 mbps, 10 mbps, 20 mbps, 50 mbps and 100 mbps. | 1 | 0 | 1 | 5 | Late start due to environmental assessment. Connections should started in November of 2011. 17 additional are being scheduled for cutover. | Late state due to environmental assessment. | Late state due to environmental assessment. | Speeds are 5 mbps, 10 mbps, 20 mbps, 50 mbps and 100 mbps. | 0 | 0 | 0 | 0 | 0 | No Variations. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time no special offerings will be made. | FALSE | N/A | Continue design in Fargo and Grand Forks, ND areas. Currently the total CAI subscribers served is eight, and DCN will continue to connect CAIs. Construction is mostly shut down for the winter, however, some construction in Bismarck/Mandan will continue but most will not start up during the first quarter of 2012. New network miles deployed: 52 New network miles leased: N/A Total CAI's served (connected):1 Signed agreement wholesalers: 17 | DCN, LLC | The project is moving forward and is currently behind schedule with outside plant (cable) work due to extra work and delay in responding to TCNS comments. We are diligently working to make up lost time and continuing to lay fiber. However, the winter weather will force us to stop construction. Access to fiber may be an issue, but we have the majority on order for 2012. We believe there is enough time in our schedule to make up delays from 2011 in 2012 by providing more construction resources. We will also be constructing in Mandan, Bismarck and Fargo simultaneously rather than sequentially like we originally planned on cable construction. Grand Forks will overlap with Fargo also. These two factors will bring us back on schedule this summer. | DCN is confident we will finish well ahead of the third year deadline, however reaching 67% completion will be a challenge for 2012. We are lining up resources and should have spent approximately 70% of funds by July 31, 2012. Miles deployed is estimated to be 44% of miles by July 31, 2012. This is due to the fact that the majority of construction dollars and work is in city limits and you cannot achieve 67% of mile with 70% of the dollars. Equipment, engineering and right-of-way will be at least 67% complete by July 31, 2012. By end of 2012 we expect to be 87% overall and 82% of miles deployed. | TRUE
NT10BIX5570090 | 2012 | Q1 | Q1 - 2012 | 100% of the design is complete for Bismarck, Fargo, and Mandan, ND sites. Construction is proceeding in Bismarck. SRT Communications sites have been awarded and construction is almost complete. Northwest Communications Cooperative sites designed and awarded, but waiting for construction to start in the spring. DCT sites were awarded and the construction is complete. | 52 | 0 | 0 | 1388 | 52 | 0 | 0 | 0 | On Schedule.(As revised) | N/A | N/A | N/A | On Schedule.(As revised) | N/A | N/A | N/A | 17 | 0 | 7 | Last Mile Providers: BEK Communications, United Telephone Mutual Aide Corporation, Dakota Central Telecommunications Cooperative, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, Reservation Telephone Cooperative, SRT Communications, Consolidated Telecom Company, Red River Telephone, West River Telecommunications, Dickey Rural, Idea One, and Midstate Communications. | Last Mile Providers: BEK Communications, United Telephone Mutual Aide Corporation, Dakota Central Telecommunications Cooperative, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, Reservation Telephone Cooperative, SRT Communications, Consolidated Telecom Company, Red River Telephone, West River Telecommunications, Dickey Rural, Idea One, and Midstate Communications. | DCN does not have a designated third party to operate the network. Sub recipients will own and maintain the fiber within their network and charge DCN for the circuits. DCN will own, operate and manage the entire electronics network for all CAI's. Sub recipients maintaining the their fiber are: BEK Communications, Dakota Central Telecommunications, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, SRT Communications, Consolidated Telecom Company, and Red River Telephone. | 0 | 0 | 0 | 5 | N/A | N/A | N/A | Speeds are 5 mbps, 10 mbps, 20 mbps, 50 mbps and 100 mbps | 12 | 0 | 12 | 5 | On schedule. | On schedule. | On schedule. | Speeds are 5 mbps, 10 mbps, 20 mbps, 50 mbps and 100 mbps | 0 | 0 | 0 | 0 | 0 | No variations. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time no special offerings will be made. | FALSE | N/A | Bid projects and start construction with Dakota Carrier Network (DCN) (Bismarck, Mandan and Fargo), BEK Communications, Red River Telephone, Northwest Communications Cooperative, and SRT Communications. The total CAI subscribers constructed is 22 and DCN will continue to connect CAIs. Sixteen projects will in construction. New network miles deployed: 80 New network miles leased: N/A | DCN, LLC | The project is moving forward and is on schedule with outside plant (cable) work due to extra work. We are diligently working to make up lost time and continuing to lay fiber. Access to fiber may be an issue, but we have the majority on order for 2012. We believe there is enough time in our schedule to make up delays from 2011 in 2012 by providing more construction resources. We will also be constructing in Mandan, Bismarck and Fargo simultaneously rather than sequentially like we originally planned on cable construction. Grand Forks will overlap with Fargo also. These two factors will keep us on schedule this summer. | DCN is confident we will finish well ahead of the third year deadline, however reaching 67% completion will be a challenge for 2012. We are lining up resources and should have spent approximately 70% of funds by July 31, 2012. Miles deployed is estimated to be 44% of miles by July 31, 2012. This is due to the fact that the majority of construction dollars and work is in city limits and you cannot achieve 67% of mile with 70% of the dollars. Equipment, engineering and right-of-way will be at least 67% complete by July 31, 2012. By end of 2012 we expect to be 87% overall and 82% of miles deployed. | TRUE
NT10BIX5570090 | 2012 | Q2 | Q2 - 2012 | 100% of the design is complete for Bismarck, Fargo, and Mandan, ND sites. Construction is proceeding in Bismarck. SRT Communications sites have been awarded and construction is almost complete. Northwest Communications Cooperative sites designed and awarded, but waiting for construction to start in the spring. DCT sites were awarded and the construction is complete. | 105 | 0 | 0 | 1388 | 105 | 0 | 0 | 0 | Ahead of schedule by 25 miles. | N/A | N/A | N/A | Ahead of schedule by 25 miles. | N/A | N/A | N/A | 17 | 0 | 7 | Last Mile Providers: BEK Communications, United Telephone Mutual Aide Corporation, Dakota Central Telecommunications Cooperative, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, Reservation Telephone Cooperative, SRT Communications, Consolidated Telecom Company, Red River Telephone, West River Telecommunications, Dickey Rural, Idea One, and Midstate Communications. | Next level internet interconnection from 5 MBPS to 10 GBPS. | DCN does not have a designated third party to operate the network. Sub recipients will own and maintain the fiber within their network and charge DCN for the circuits. DCN will own, operate and manage the entire electronics network for all CAI's. Sub recipients maintaining the their fiber are: BEK Communications, Dakota Central Telecommunications, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, SRT Communications, Consolidated Telecom Company, and Red River Telephone. | 0 | 0 | 0 | 5 | N/A | N/A | N/A | Speeds are 10 mbps-0 subscribers, 20 mbps-0 subscribers, 50 mbps-0 subscribers,100 mbps-0 subscribers, and I gbps-8,450 subscribers. Remaining subscribers have not hooked-up yet. | 34 | 0 | 34 | 5 | Ahead of schedule by 15 sites. | On schedule. | Ahead of schedule. | 5 mbps-5 subscribers, 10 mbps-1 subscriber, 20 mbps-3 subscribers, 50 mbps-0 subscribers, and 100 mbps-0 subscribers. Remaining anchor institutions have not hooked-up yet. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time no special offerings will be made. | FALSE | N/A | Finished bidding projects and continue construction with Dakota Carrier Network (DCN) (Bismarck, Mandan, Grand Forks and Fargo), BEK Communications, Red River Telephone, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, and North Dakota Telephone Company. The total CAI subscribers constructed is 104 and DCN will continue to connect CAIs. Ten projects will be under construction. New network miles deployed: 140 New network miles leased: N/A | DCN, LLC | The project is moving forward and is on schedule with outside plant (cable) work due to extra work. We are diligently working to make up lost time and continuing to lay fiber. Access to fiber may be an issue, but we have the majority on order for 2012. We believe there is enough time in our schedule to make up delays from 2011 in 2012 by providing more construction resources. We will also be constructing in Mandan, Bismarck and Fargo simultaneously rather than sequentially like we originally planned on cable construction. Grand Forks will overlap with Fargo also. These two factors will keep us on schedule this summer. Progress is ahead of schedule but bill from sub-recipients are lagging behind. | DCN is confident we will finish well ahead of the third year deadline. We have resources working and should have spent approximately 67% of funds by July 31, 2012. Miles deployed is estimated to be 54% of miles by July 31, 2012. This is due to the fact that the majority of construction dollars and work is in city limits and you cannot achieve 67% of the miles with 70% of the dollars. Equipment, engineering and right-of-way will be at least 85% complete by July 31, 2012. By end of 2012 we expect to be 87% overall and 82% of miles deployed. | TRUE
NT10BIX5570090 | 2012 | Q3 | Q3 - 2012 | 100% of the design is complete for Bismarck, Fargo, and Mandan, ND sites. Construction is proceeding in Bismarck. SRT Communications sites have been awarded and construction is almost complete. Northwest Communications Cooperative sites designed and awarded, but waiting for construction to start in the spring. DCT sites were awarded and the construction is complete. | 149 | 0 | 0 | 1388 | 149 | 0 | 0 | 0 | Ahead of schedule by 9 miles. | N/A | N/A | N/A | Ahead of schedule by 9 miles. | N/A | N/A | N/A | 17 | 0 | 7 | Last Mile Providers: BEK Communications, United Telephone Mutual Aide Corporation, Dakota Central Telecommunications Cooperative, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, Reservation Telephone Cooperative, SRT Communications, Consolidated Telecom Company, Red River Telephone, West River Telecommunications, Dickey Rural, Idea One, and Midstate Communications. | Next level internet interconnection from 5 MBPS to 10 GBPS. | DCN does not have a designated third party to operate the network. Sub recipients will own and maintain the fiber within their network and charge DCN for the circuits. DCN will own, operate and manage the entire electronics network for all CAI's. Sub recipients maintaining the their fiber are: BEK Communications, Dakota Central Telecommunications, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, SRT Communications, Consolidated Telecom Company, and Red River Telephone. | 0 | 0 | 0 | 5 | N/A | N/A | N/A | Speeds are 10 mbps-0 subscribers, 20 mbps-0 subscribers, 50 mbps-0 subscribers,100 mbps-0 subscribers, and I gbps-8,450 subscribers. Remaining subscribers have not hooked-up yet. | 55 | 24 | 31 | 5 | Behind schedule by 4 sites since we cannot count 6 towers | On schedule. | Behind schedule by 4 sites since we cannot count 6 towers | 5 mbps-20 subscribers, 10 mbps-1 subscriber, 20 mbps-3 subscribers, 50 mbps-0 subscribers, and 100 mbps-0 subscribers. Remaining anchor institutions have not hooked-up yet. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time no special offerings will be made. | FALSE | N/A | Finished bidding projects and continue construction with Dakota Carrier Network (DCN) (Mandan, Grand Forks and Fargo), Red River Telephone, Polar Communications Mutual Aid, Consolidated Telecom and North Dakota Telephone Company. The total CAI subscribers constructed is 104 and DCN will continue to connect CAIs. Seven projects will be under construction. New network miles deployed: 167 New network miles leased: N/A | DCN, LLC | The project is moving forward and is close to being on schedule with outside plant (cable) work. We are diligently working to make up lost time and continuing to lay fiber. We believe there is enough time in our schedule to make up the small delays from 2012 in 2013 by providing more construction resources. We will also be constructing in Mandan and Grand Forks simultaneously rather than sequentially like we originally planned on cable construction. These factors will keep us close to the schedule to the end of the year. Progress is close to schedule but bills from sub-recipients are lagging behind. | DCN is confident we will finish well ahead of the third year deadline. We have resources working and should have built 89% of the system. Miles deployed is estimated to be 82%. We will finish right-of-way and work on marketing. | TRUE
NT10BIX5570090 | 2012 | Q4 | Q4 - 2012 | 100% of the design is complete for almost all of projects. Construction continued in Bismarck, Fargo, and Mandan, ND sites. Construction is proceeding in Bismarck. NDTC, Polar, and Consolidated Telcom projects have started and almost finished Polar projects. | 167 | 0 | 0 | 1388 | 167 | 0 | 0 | 0 | On schedule. | N/A | N/A | N/A | On schedule. | N/A | N/A | N/A | 17 | 0 | 7 | Last Mile Providers: BEK Communications, United Telephone Mutual Aide Corporation, Dakota Central Telecommunications Cooperative, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, Reservation Telephone Cooperative, SRT Communications, Consolidated Telecom Company, Red River Telephone, West River Telecommunications, Dickey Rural, Idea One, and Midstate Communications. | Next level internet interconnection from 5 MBPS to 10 GBPS. | DCN does not have a designated third party to operate the network. Sub recipients will own and maintain the fiber within their network and charge DCN for the circuits. DCN will own, operate and manage the entire electronics network for all CAI's. Sub recipients maintaining the their fiber are: BEK Communications, Dakota Central Telecommunications, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, SRT Communications, Consolidated Telecom Company, and Red River Telephone. | 0 | 17 | 0 | 5 | N/A | Increased bandwidth capability beyond 1 Gbps. | N/A | Speeds are 10 mbps-0 subscribers, 20 mbps-0 subscribers, 50 mbps-0 subscribers,100 mbps-0 subscribers, and I Gbps-17 subscribers. Remaining subscribers have not hooked-up yet. | 68 | 29 | 39 | 5 | Behind schedule by 36 sites, 6 of which are towers. Results of marketing are not as high as we expected to this point. | Behind schedule by 36 sites, 6 of which are towers. Results of marketing are not as high as we expected to this point. | Behind schedule by 36 sites, 6 of which are towers. Results of marketing are not as high as we expected to this point. | 5 mbps-20 subscribers, 10 mbps-1 subscriber, 20 mbps-3 subscribers, 50 mbps-0 subscribers, and 100 mbps-0 subscribers. Remaining anchor institutions have not hooked-up yet. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 5 | N/A | One business is connected. | N/A | N/A | 5 mbps-20 subscribers, 10 mbps-1 subscriber, 20 mbps-3 subscribers, 50 mbps-0 subscribers, and 100 mbps-0 subscribers. Remaining anchor institutions have not hooked-up yet. | At this time no special offerings will be made. | FALSE | N/A | Finished bidding projects and continue construction with Dakota Carrier Network (DCN) (Mandan, Bismarck, Grand Forks and Fargo mostly drops), Polar Communications Mutual Aid, Consolidated Telecom and North Dakota Telephone Company. The total CAI subscribers constructed is 72 and DCN will continue to connect CAIs. Seven projects will be under construction, but with slow progress due to winter freeze. New network miles deployed: 170 New network miles leased: N/A | DCN, LLC | The project is moving forward and is close to being on schedule with outside plant (cable) work. We made up lost time on the backbone and are continuing to lay fiber. We believe there is enough time in our schedule to make up the small delays from 2012 in 2013 by providing more construction resources. We will also be constructing in Mandan, Bismarck, Fargo, Grand Forks NDTC, and Consolidated Telecom simultaneously rather than sequentially like we originally planned on mostly drop construction. These factors will keep us close to the schedule. Progress is close to schedule but bills from sub-recipients are lagging behind. | DCN is confident we will finish well ahead of the third year deadline. We have resources working and should have built 90% of the system. Miles deployed is estimated to be 81%. We will finish right-of-way and work on marketing. | TRUE
NT10BIX5570090 | 2013 | Q1 | Q1 - 2013 | 100% of the design is complete for almost all of projects. Construction continued in Bismarck, Fargo, and Mandan, ND sites. Construction is proceeding in Bismarck. NDTC, Polar, and Consolidated Telcom projects have started and almost finished Polar projects. | 167 | 0 | 0 | 1388 | 167 | 0 | 0 | 0 | On schedule. | N/A | N/A | N/A | On schedule. | N/A | N/A | N/A | 17 | 0 | 7 | Last Mile Providers: BEK Communications, United Telephone Mutual Aide Corporation, Dakota Central Telecommunications Cooperative, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, Reservation Telephone Cooperative, SRT Communications, Consolidated Telecom Company, Red River Telephone, West River Telecommunications, Dickey Rural, Idea One, and Midstate Communications. | Next level internet interconnection from 5 MBPS to 10 GBPS. | DCN does not have a designated third party to operate the network. Sub recipients will own and maintain the fiber within their network and charge DCN for the circuits. DCN will own, operate and manage the entire electronics network for all CAI's. Sub recipients maintaining the their fiber are: BEK Communications, Dakota Central Telecommunications, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, SRT Communications, Consolidated Telecom Company, and Red River Telephone. | 0 | 17 | 0 | 5 | N/A | Increased bandwidth capability beyond 1 Gbps. | N/A | Speeds are 10 mbps-0 subscribers, 20 mbps-0 subscribers, 50 mbps-0 subscribers,100 mbps-0 subscribers, and I Gbps-17 subscribers. Remaining subscribers have not hooked-up yet. | 68 | 29 | 39 | 5 | Behind schedule by 36 sites, 6 of which are towers. Results of marketing are not as high as we expected to this point. | Behind schedule by 36 sites, 6 of which are towers. Results of marketing are not as high as we expected to this point. | Behind schedule by 36 sites, 6 of which are towers. Results of marketing are not as high as we expected to this point. | 5 mbps-20 subscribers, 10 mbps-1 subscriber, 20 mbps-3 subscribers, 50 mbps-0 subscribers, and 100 mbps-0 subscribers. Remaining anchor institutions have not hooked-up yet. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 5 | N/A | One business is connected. | N/A | N/A | 5 mbps-20 subscribers, 10 mbps-1 subscriber, 20 mbps-3 subscribers, 50 mbps-0 subscribers, and 100 mbps-0 subscribers. Remaining anchor institutions have not hooked-up yet. | At this time no special offerings will be made. | FALSE | N/A | Finished bidding projects and continue construction with Dakota Carrier Network (DCN) (Mandan, Bismarck, Grand Forks and Fargo mostly drops), Polar Communications Mutual Aid, Consolidated Telecom and North Dakota Telephone Company. The total CAI subscribers constructed is 69 and DCN will continue to connect CAIs. Seven projects will be under construction, but with slow progress due to winter freeze. New network miles deployed: 170 New network miles leased: N/A | DCN, LLC | The project is moving forward and is close to being on schedule with outside plant (cable) work. We made up lost time on the backbone and are continuing to lay fiber. We believe there is enough time in our schedule to make up the small delays from 2012 in 2013 by providing more construction resources. We will also be constructing in Mandan, Bismarck, Fargo, Grand Forks NDTC, and Consolidated Telecom simultaneously rather than sequentially like we originally planned on mostly drop construction. These factors will keep us close to the schedule. Progress is close to schedule but bills from sub-recipients are lagging behind. | DCN is somewhat confident we will finish well ahead of the third year deadline, however, the late spring has delayed construction. We have resources working and should have built 96% of the system. Miles deployed is estimated to be 81%. We will finish the majority of the project in the next quarter. | TRUE
NT10BIX5570090 | 2013 | Q2 | Q2 - 2013 | 100% of the design is complete for almost all of projects. Construction continued in Bismarck, Fargo, and Mandan, ND sites. Construction is proceeding in Bismarck. NDTC, Polar, and Consolidated Telcom projects have started and almost finished Polar projects. | 179 | 0 | 0 | 1388 | 179 | 0 | 0 | 0 | 35 miles behind due to spring delays | N/A | N/A | N/A | 35 miles behind due to spring delays | N/A | N/A | N/A | 17 | 0 | 7 | Last Mile Providers: BEK Communications, United Telephone Mutual Aide Corporation, Dakota Central Telecommunications Cooperative, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, Reservation Telephone Cooperative, SRT Communications, Consolidated Telecom Company, Red River Telephone, West River Telecommunications, Dickey Rural, Idea One, and Midstate Communications. | Next level internet interconnection from 5 MBPS to 10 GBPS. | DCN does not have a designated third party to operate the network. Sub recipients will own and maintain the fiber within their network and charge DCN for the circuits. DCN will own, operate and manage the entire electronics network for all CAI's. Sub recipients maintaining the their fiber are: BEK Communications, Dakota Central Telecommunications, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, SRT Communications, Consolidated Telecom Company, and Red River Telephone. | 0 | 17 | 0 | 5 | N/A | Increased bandwidth capability beyond 1 Gbps. | N/A | Speeds are 10 mbps-0 subscribers, 20 mbps-0 subscribers, 50 mbps-0 subscribers,100 mbps-0 subscribers, and I Gbps-17 subscribers. Remaining subscribers have not hooked-up yet. | 106 | 54 | 52 | 5 | Behind schedule by 24 sites, 1 of which are towers. Results of marketing are not as high as we expected to this point. | Made up some ground. | Made up some ground. | 5 mbps-30 subscribers, 10 mbps-1 subscriber, 20 mbps-3 subscribers, 50 mbps-0 subscribers, and 100 mbps-0 subscribers. Remaining anchor institutions have not hooked-up yet. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 5 | N/A | One business is connected | N/A | N/A | 5 mbps-1 subscribers, 10 mbps-0 subscriber, 20 mbps-0 subscribers, 50 mbps-0 subscribers, and 100 mbps-0 subscribers. Remaining anchor institutions have not hooked-up yet. | At this time no special offerings will be made. | FALSE | N/A | Continue construction with Dakota Carrier Network (DCN) (Mandan, Bismarck, Grand Forks and Fargo mostly drops), Polar Communications Mutual Aid, and North Dakota Telephone Company. The total CAI subscribers constructed is 124 (this does not include 12 towers we went to) and DCN will continue to connect CAIs. Six projects will be under construction. New network miles deployed: 214 New network miles leased: N/A | DCN, LLC | The project is moving forward and is close to being on schedule with outside plant (cable) work. We made up some lost time on the backbone and are continuing to lay fiber. We believe there is enough time in our schedule to make up the small delays from 2012 in 2013 by providing more construction resources. We were constructing in Mandan, Bismarck, Fargo, Grand Forks, North Dakota Telephone Company, and Consolidated Telecom simultaneously rather than sequentially like we originally planned on mostly drop construction. These factors will keep us close to the schedule. Progress is close to schedule but bills from sub-recipients are lagging behind. With the recently approved extension we will have no issues finishing. | DCN is working diligently to be completed by the third year deadline. The late spring has delayed construction. We have resources working and will have built 100% of the system. Miles deployed is estimated to be 100%. We will finish the majority of the project in the next quarter. | TRUE
NT10BIX5570090 | 2013 | Q3 | Q3 - 2013 | Completed all required sites for 124 CIAs, 1 business and 10 towers. These sites may now have access to high speed data connections. DCN and it's sub-recipients also placed 210 miles of fiber for theses sites. DCN set up the medical network backbone on the network for any medical or healthcare facility to connect to each other and other entities. We connected several CAI's that will benefit from better quality service and higher bandwidth availability. | 210 | 0 | 0 | 1388 | 210 | 0 | 0 | 0 | Complete. 214 was estimated but when final sites were built we only needed to place 210. | N/A | N/A | N/A | Complete | N/A | N/A | N/A | 17 | 0 | 7 | Last Mile Providers: BEK Communications, United Telephone Mutual Aide Corporation, Dakota Central Telecommunications Cooperative, Midstate Telephone Company, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, Reservation Telephone Cooperative, SRT Communications, Consolidated Telecom Company, Red River Telephone, West River Telecommunications, Dickey Rural, Idea One, and Midstate Communications. | Next level internet interconnection from 5 MBPS to 10 GBPS. | DCN does not have a designated third party to operate the network. Sub recipients will own and maintain the fiber within their network and charge DCN for the circuits. DCN will own, operate and manage the entire electronics network for all CAI's. Sub recipients maintaining the their fiber are: BEK Communications, Dakota Central Telecommunications, Moore & Liberty/Griggs County Telephone, North Dakota Telephone Company, Northwest Communications Cooperative, Polar Communications Mutual Aid, Inter-Community Telephone Company, SRT Communications, Consolidated Telecom Company, and Red River Telephone. | 0 | 17 | 0 | 5 | N/A | Increased bandwidth capability beyond 1 Gbps. | N/A | Speeds are 10 mbps-0 subscribers, 20 mbps-0 subscribers, 50 mbps-0 subscribers,100 mbps-0 subscribers, and I Gbps-17 subscribers. | 124 | 68 | 56 | 5 | Does not include 10 towers | As of end of reporting period. | As of end of reporting period. | 5 mbps-38 subscribers, 10 mbps-14 subscriber, 20 mbps-13 subscribers, 50 mbps-6 subscribers, and 100 mbps-1 subscribers. Remaining anchor institutions just may not be subscribing to services yet. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 5 | N/A | One business is connected | N/A | N/A | 5 mbps-0 subscribers, 10 mbps-1 subscriber, 20 mbps-0 subscribers, 50 mbps-0 subscribers, and 100 mbps-0 subscribers. Remaining anchor institutions have not hooked-up yet. | At this time no special offerings will be made. | FALSE | N/A | We will close out all projects and prepare for final close out. | DCN, LLC | Work was completed as expected. | DCN will be working through the project close out phase. | TRUE
NT10BIX5570091 | 2010 | Q4 | Q4 - 2010 | During the second quarter of Bluebird Mediaâ€™s award period, Bluebird Media hired additional employees to engineer and design an ultra-high capacity middle-mile network throughout under-served and un-served northern rural Missouri. These employees included engineers and operational personnel with telecommunications backgrounds. Bluebird Media had federal expenditures during the second quarter of the award period. These expenditures included the salaries of employees related to the network and infrastructure design and up front mobilization payments for the engineering firms. Key milestones completed during the second quarter consisted of selecting engineering firms to survey the proposed infrastructure routes and selecting an environmental firm to complete an environmental assessment. Bluebird Media posted a request for proposal on our web site so any engineering/environmental firm could bid on the project. Bluebird Media worked throughout the quarter to ensure all fiber routes and towers were going to be constructed on Missouri Department of Transportation right of way and/or property. Bluebird Media contacted several potential CAIs making them aware of the future possibility of being directly connected to Bluebird's fiber. Bluebird Media also met with another BTOP recipient to discuss overlapping areas and proposed a joint route structure in the overlapping area. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No build to date | No build to date | No build to date | No build to date | No build to date | No build to date | No build to date | No build to date | 0 | 22 | 0 | NA | DIA, ELAN, EWAN etc. Pricing plans are being currently developed. | NA | 0 | 0 | 0 | 0 | No build to date | No build to date | No build to date | 50 MB - 1GB are the speed tiers that will be available. No subscribers since no build to date. | 0 | 0 | 0 | 0 | No build to date | No build to date | No build to date | 10MB-10GB are the speed tiers that are available. No subscribers since no build to date. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | No special offerings at this time. | FALSE | NA | Engineering firms will finish surveying the proposed infrastructure routes and the environmental engineering firm will complete an environmental assessment. Bluebird Media will then be issued a FONSI. Bluebird Media also plans to select a Fiber vendor and several construction companies to build the infrastructure using a RFQ posted on Bluebird's web site. Bluebird Media will also purchase construction materials and network equipment during the next quarter using the web site. CAIs will be contacted and be provided a Letter of Interest indicating that the CAI would be willing to direct connect to Bluebird's network. Bluebird Media is planning on devising a rate structure for all products offered during this quarter. Bluebird Media will also be working on an education campaign and conducting public presentations to inform and attract CAIs. Site Preparation will be delayed during the next quarter due to route changes relating to exclusive right-of-ways. Bluebird Media will work diligently to catch up on the site preparation once Bluebird knows the exact routes for the infrastructure. | Bluebird Media, L.L.C. | Potential delays and challenges Bluebird Media incurred included changing the routes of the fiber as more information came available during the design and surveying phase related to exclusive right-of-ways. Bluebird Media was also delayed in site preparation during the past quarter due to route changes relating to exclusive right-of-ways. These exclusive right-of-ways were unknown to Bluebird Media during the design phase of the grant application. Missouri Department of Transportation has given exclusive right-of-ways to another company along some Missouri major highways and river crossings. Therefore, Bluebird Media is working diligently to propose an altered route for their infrastructure to bypass the exclusive right-of-ways. | Potential delays and challenges Bluebird Media anticipates during the next quarter include obtaining approval of route changes due to exclusive right-of-ways unknown to Bluebird Media during the grant application period. | TRUE
NT10BIX5570091 | 2011 | Q1 | Q1 - 2011 | Engineering firms finished surveying the infrastructure routes and the environmental engineering firm gained progress on completing an environmental assessment. A environmental assessment draft was submit during this time. Bluebird Media selected a Fiber vendor through a competitive process and contracted for fiber delivery. Four construction companies were also selected to build the infrastructure using a competitive process. Bluebird Media held competitive bidding for purchase of construction materials and network equipment during this quarter completing selection of one vendor to provide shelters for the network while materials and electronics were still pending at the end of the quarter. Over 200 CAIs were contacted and many provided a Letter of Interest indicating that the CAI would be willing to direct connect to Bluebird's network. Bluebird Media identified and participated with key organizations to support Bluebirdâ€™s mission including USDA Field Agents, Chairs of state legislative telecommunication committees, University of Missouri- Missouri Health Policy, State of Missouri-Mo High Tech Meetings, Missouri Telecommunication Industry Association, MoreNet, and the Office of State Court Administrators. Bluebird initiated the development of a comprehensive portfolio for community presentations including collateral materials. Site Preparation was delayed during this quarter due to route changes relating to exclusive right-of-ways. During the early portion of the quarter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | None- no construction yet | None- no construction yet | N/A | N/A | None- no construction yet | N/A | N/A | None- no construction yet | 0 | 22 | 0 | NA | DIA, ELAN, EWAN etc. Pricing plans are being currently developeds are being currently developed. | NA | 0 | 0 | 0 | 0 | No build to date | No build to date | No build to date | 50 MB - 1GB are the speed tiers that will be available. No subscribers since no build to date. | 0 | 0 | 0 | 0 | No build to date | No build to date | No build to date | 10MB-10GB are the speed tiers that are available. No subscribers since no build to date. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | No special offerings at this time. | FALSE | NA | Bluebird's environmental engineering firm will complete an environmental assessment and will then be issued a FONSI. Bluebird also plans to select a electronics network equipment provider(s), OSS software program provider(s), and miscellaneous construction materials provider(s) through a competitive bidding process. Bluebird will complete contracts with the OSP/ISP vendors, OSS software vendor(s) and network construction companies that were selected during the prior and present quarter. Bluebird will also issue a RFP for construction management and site engineering and plans to complete contracts with these vendors during the quarter. Bluebird is planning on acquiring site locations for all communication shelters. Bluebird also plans to devise a rate structure for all products offered in the future. Bluebird will be working on finalizing an agreement with MODOT. Bluebird will work diligently to catch up on the site preparation once Bluebird knows the exact routes for the infrastructure, which is project to be finalized during this quarter. Lastly, Bluebird will complete a community outreach and identify stakeholders. This outreach will consist of brochures, collateral materials, press releases, and web site revisions. Bluebird plans to participate in the MO Broadband Now and Regional Technology Planning Group meetings across the PFSA. | Bluebird Media, L.L.C. | Potential delays and challenges Bluebird Media incurred included changing the routes of the fiber as more information came available during the design and surveying phase related to exclusive right-of-ways during Q4 2010. Bluebird Media was also delayed in site preparation during the past quarter due to route changes relating to exclusive right-of-ways. These exclusive right-of-ways were unknown to Bluebird Media during the design phase of the grant application. Missouri Department of Transportation has given exclusive right-of-ways to another company along some Missouri major highways and river crossings. Therefore, Bluebird Media during Q1-2011 worked diligently to propose an altered route for their infrastructure to bypass the exclusive right-of-ways. | Potential delays and challenges Bluebird Media anticipates during the next quarter include obtaining a FONSI in a timely manner. Delay of the Environment Assessment has been caused by approval of route changes due to exclusive right-of-ways unknown to Bluebird Media during the grant application period. This will challenge Bluebird Media to get the construction started immediately following a FONSI. | TRUE
NT10BIX5570091 | 2011 | Q2 | Q2 - 2011 | Bluebird Media's environmental engineering firm completed an environmental assessment and was issued a Finding of Non Significant Impact (FONSI) on the environment. Bluebird's engineering firms completed the route drawings and staking of the infrastructure routes during this quarter. Bluebird selected two electronics network equipment providers for Dense Wavelength Division Multiplexing (DWDM) and Multiprotocol Label Switching (MPLS) equipment, a construction supervisor and a site preparation consultant, and selected one miscellaneous construction materials provider through competitive bidding processes. Bluebird completed contracts with a miscellaneous construction materials and warehousing provider, four network construction companies, a construction supervisor, and a site preparation consultant. Bluebird finalized an agreement with the Missouri Department of Transportation (MODOT) regarding state rights of ways. Bluebird Media completed a study on the value of rural fiber indefeasible rights of use (IRU) and hired two new engineers during the past quarter. Bluebird Media took delivery of one-third of their projects fiber and confirmed the timing of the shipments of the remaining two-thirds of the fiber with Draka due to the fiber shortage across the industry. Bluebird revised their budget to reflect the approved routes changes and increased the amount of the budget that reflected to amount Bluebird was able to spend prior to obtaining a FONSI. Bluebird Media also proposed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | None- no construction yet | None- no construction yet | N/A | N/A | None- no construction yet | N/A | N/A | None- no construction yet | 0 | 22 | 0 | N/A | Dedicated Internet Access, Extended Local Area Network, Extended Wide Area Network, etc. Pricing plans are being currently developed.3 | N/A | 0 | 0 | 0 | 0 | No build to date | No build to date | No build to date | 50 MB - 1GB are the speed tiers that will be available. No subscribers since no build to date. | 0 | 0 | 0 | 0 | No build to date | No build to date | No build to date | 10MB-10GB are the speed tiers that are available. No subscribers since no build to date. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | No special offerings at this time. | FALSE | NA | Bluebird's environmental engineering firm will continue to monitor environmental assessment to comply with the Special Award Conditions while the engineering team completes the network design while the infrastructure is being built. Bluebird will finalize all agreements with state agencies to compete the necessary contracts for the state Rights of Way. Once completed, Bluebird will begin construction on the infrastructure routes and start site preparation for the node sites. Bluebird plans to have ground breaking ceremonies across the state once construction starts. Bluebird also plans to select an Operational Support System (OSS) software program provider(s), a fiber distribution panel vendor, and a auditing firm through a competitive bidding process. Bluebird will complete contracts with the OSS software vendor(s), the Fiber Distribution Panel vendor, DWDM/MPLS equipment vendors, a shelter vendor, and a certified auditor during the present quarter. Bluebird is planning on acquiring/finalizing all site locations for all communication shelters. Bluebird also plans to devise a rate structure for all products offered in the future. Bluebird will design and implement a Community Outreach Plan including education for community and elected officials, local leaders and media, including press events, fact sheets, Question & Answer handouts, power points and video. | Bluebird Media, L.L.C. | Bluebird Media faced the challenge of completing the environmental assessment during this past quarter and obtaining a Finding of Non Significant Impact (FONSI) on the environment. Due to the route changes being approved in March 2011, Bluebird Media had to work diligently to finish engineering and environmental studies along the new approved routes. Bluebird Media was delayed in site preparation too during the past quarter due to the route changes relating to exclusive right-of-ways. These exclusive right-of-ways were unknown to Bluebird Media during the design phase of the grant application. The delay in obtaining a FONSI has challenged Bluebird Media to start construction about two to three months behind schedule. Bluebird Media feels confident that the current plan in place with all four construction companies gives Bluebird time to fulfill the grant requirements timely. | Potential delays and challenges Bluebird Media anticipates during the next quarter include the flooding of the Missouri River. Spring rain combined with heavy release of water from dams, have caused the Missouri River to reach flood stage during Q2 2011. The U.S. Army Corps of Engineers think it will be late Q3 2011 before the river returns to its banks. This will challenge Bluebird Media to get the construction started immediately for the river bore immediately following the river receding below flood stage. | TRUE
NT10BIX5570091 | 2011 | Q3 | Q3 - 2011 | Bluebird started construction on 8-15-11 upon finalizing all agreements with state agencies for the use of state Rights of Way and after receiving several building permits. Four contractors selected through a competitive bidding process started on four different infrastructure segments across the state. As of 9-30-11, these contractors had deployed 62 new network miles of fiber. Bluebird completed Master Service Agreements with electronics network equipment providers for Dense Wavelength Division Multiplexing (DWDM) and Multiprotocol Label Switching (MPLS) equipment, Through a competitive bidding process, Bluebird posted a Request for Proposal on Bluebird's web site for Node Site Civil Construction. Bluebird selected an Operational Support Systems (OSS) software program providers, a fiber distribution panel vendor, and a auditing firm through a competitive bidding process. Bluebird completed contracts with the OSS software vendors, the Fiber Distribution Panel vendor, DWDM/MPLS equipment vendors, a shelter vendor, and a certified auditor during the present quarter. Bluebird was substantially complete with the Year one audit at quarter end and hired four new employees during the past quarter. Bluebird Media took delivery of half of their projects fiber during this quarter. Due to the fiber shortage across the industry, Bluebird also confirmed the timing of the shipments of the remaining 20% of the fiber. Bluebird Media also was approved of a proposed route change that woul | 62 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 25 miles behind revised baseline caused by 45 day delay in obtaining construction permits during the first part of Q3 2011 delaying construction startup. The plan is to catch up to the revised baseline during Q4 2011. The construction permits will all be available during Q4 2011 allowing the construction of the network build to continuously carry on without delays. | None-no miles leased to date which is in line with revised baseline. | NA | NA | 25 miles behind revised baseline caused by 45 day delay in obtaining construction permits during the first part of Q3 2011 delaying construction startup. | NA | NA | None-no new and/or upgraded interconnection points which is in line with revised baseline. RECIPIENT NAME:Bluebird Media, L.L.C. AWARD NUMBER: NT10BIX5570091 DATE: 11/23/2011 OMB CONTROL NUMBER: 0660-0037 EXPIRATION DATE: 12/31/2013 | 0 | 22 | 0 | Bluebird Media is currently behind the revised baseline due to not having any fiber turned up to date. Bluebird Media has wholesalers and last mile providers ready to sign agreements once certain segments of the fiber has been turned up. Bluebird Media plans to catch up to the revised baseline during Q1-2012. | Dedicated Internet Access, Extended Local Area Network, Extended Wide Area Network, etc. Pricing plans are being currently developedd Local Area Network, Extended Wide Area Network, etc. Pricing plans are being currently developed. | NA | 0 | 0 | 0 | 0 | No turned up fiber to date | No turned up fiber to date | No turned up fiber to date | 50 MB - 1GB are the speed tiers that will be available. No subscribers since no build to date. | 0 | 0 | 0 | 0 | No turned up fiber to date | No turned up fiber to date | No turned up fiber to date | 10MB-10GB are the speed tiers that are available. No subscribers since no build to date. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | No special offerings at this time. | FALSE | NA | Bluebird's environmental engineering firm will continue to monitor environmental assessment to comply with the Special Award Conditions while the engineering team completes the network design and while the infrastructure is being built. Bluebird will continue to apply for construction permits and railroad permits in a timely manner to ensure the construction companies are not waiting on permits. Bluebird plans to start site preparation for the node sites and plans to have ground breaking ceremonies across the state once fiber starts to be turned up. Bluebird plans to implement the OSS Software during the next quarter. Bluebird will complete contracts with a Node Site Civil Construction company and will start procuring the majority of the DWDM/MPLS equipment during the next quarter. Bluebird also plans to devise a rate structure for all products offered in the future. Bluebird will continue to design and implement a Community Outreach Plan including education for community and elected officials along fiber route. Local leaders and media will be notified of these press events. Bluebird Media plans on presenting at the Missouri Association of Counties Annual meeting and to participate in the Mid-Course Workshop for Broadband Awardees in Cleveland, OH. Bluebird Media plans to catch up to the revised baseline for new network miles deployed of 287 and new network miles leased of 114 during the next quarter. Bluebird Media plans to be behind the revised baseline for CAI subscribe | Bluebird Media, L.L.C. | Bluebird Media faced the challenge of completing a route change during the past quarter. The issued faced during the route change were minimal since the route change was going from a build route to a fiber IRU route. Since the change was for a fiber IRU route, there were not any environmental implications. Railroad Crossing permits have been challenging to obtain in a timely manner. Bluebird has devoted key employees to handle the railroad permitting process and do not feel like any technical assistance from the BTOP program is needed at this time. Bluebird Media feels confident that the current construction plan in place with all four construction companies gives Bluebird time to fulfill the grant requirements timely. | Potential delays and challenges Bluebird Media anticipates during the next quarter include the possibility of worse winter weather than expected. | TRUE
NT10BIX5570091 | 2011 | Q4 | Q4 - 2011 | Bluebird was given a clean audit opinion by an independent auditor for the first year of the grant period stating Bluebird was in conformity with accounting principles generally accepted in the United States of America and had the proper internal controls over compliance. Four contractors worked on several different infrastructure segments across the state. During this quarter, these contractors had deployed 156 new network miles of fiber. Bluebird completed a Master Service Agreement with a electronic network equipment provider for Dense Wavelength Division Multiplexing (DWDM) equipment. Through a competitive bidding process, Bluebird posted a Request for Proposal on Bluebird's web site for Node Site Civil Construction. Bluebird then completed a Master Service Agreement with a construction company to complete the Node Site Civil construction. Bluebird took delivery of the projects remaining outstanding fiber during this quarter. Bluebird also made progress payments for the 37 shelters that will be used at many of Bluebird's POP sites.Bluebird started construction at both of their internet Gateways in Kansas City and St. Louis. Bluebird continued a community outreach campaign that included; educating key general assembly members about Bluebird Media, sending out brochures and collateral materials to Community Anchor Institutions, and stayed involved with MO Broadband Now initiatives. Lastly, Bluebird Media presented at the Missouri Association of Counties Annual meeting and participated in the Mid-Course Workshop for Broadband Awardees in Cleveland, OH. | 218 | 0 | 0 | 0 | 218 | 0 | 0 | 0 | 69 miles behind revised baseline caused by one of the four contractors not completing their segments by the end of Q4 2011 as planned. The plan is to catch up to the revised baseline during Q2 2012 as this contractor has been replaced. The construction of the network build will continuously carry on without delays with the current construction companies in place. | 114 miles behind revised baseline due to delay in signing fiber IRU agreements with several parties. The plan is to catch up to the revised baseline during Q1-2012 once several fiber IRU agreements are finalized. | NA | NA | 69 miles behind revised baseline caused by one of the four contractors not completing their segments by the end of Q4 2011 as planned. The plan is to catch up to the revised baseline during Q2 2012 as this contractor has been replaced. The construction of the network build will continuously carry on without delays with the current construction companies in place. | NA | NA | 6 interconnection points behind revised baseline due to delay in construction of new network miles. This delay was caused by the 45 day delay in obtaining construction permits during the first part of Q3 2011 delaying construction startup. The plan is to catch up to the revised baseline during Q1-2012 once several network segments are completed. | 0 | 22 | 0 | Bluebird Media is currently behind the revised baseline due to not having any fiber turned up to date. Bluebird Media has wholesalers and last mile providers ready to sign agreements once certain segments of the fiber has been turned up. Bluebird Media plans to catch up to the revised baseline during Q1-2012. | Dedicated Internet Access, Extended Local Area Network, Extended Wide Area Network, etc. Pricing plans are being currently developed. | NA | 0 | 0 | 0 | 0 | No turned up fiber to date | No turned up fiber to date | No turned up fiber to date | 50 MB - 1GB are the speed tiers that will be available. No subscribers since no build to date. | 0 | 0 | 0 | 0 | No turned up fiber to date | No turned up fiber to date | No turned up fiber to date | 10MB-10GB are the speed tiers that are available. No subscribers since no build to date. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | No special offerings at this time. | FALSE | NA | Bluebird's environmental engineering firm will continue to monitor environmental assessment to comply with the Special Award Conditions while the infrastructure is being built. Bluebird will continue to apply for construction permits and railroad permits in a timely manner to ensure the construction companies are not waiting on permits. Bluebird plans to start site preparation for the node sites, construct shelters for POP sites, and plans to have ground breaking ceremonies across the state once fiber starts to be turned up. Bluebird will start procuring all of the DWDM equipment and complete procurement of the Multiprotocol Label Switching equipment during the next quarter. Bluebird plans to connect their first CAI to the network during the next quarter. Bluebird also plans to devise a rate structure for all products offered in the future. Bluebird will continue to design and implement a Community Outreach Plan including education for community and elected officials along fiber route. Local leaders and media will be notified of these press events. Bluebird Media plans to catch up to the revised baseline for new network miles deployed of 460 during this next quarter, but will remain behind schedule for new network miles leased of 0 during the next quarter. Bluebird Media plans to be behind the revised baseline for CAI subscribers served and for the number of signed agreements with broadband wholesalers or last mile providers. The plan is to catch up those two indicators during Q2-2012 once certain fiber routes have been turned up allowing Bluebird Media to connect CAIs and sign agreements with providers. Bluebird Media plans to be at the following infrastructure key indicators at the end of the next quarter: -New Network Miles Deployed = 460 -New Network Miles Leased = 0 -Total CAI Subscribers Served = 2 -Number of Signed Agreements with wholesalers/last mile providers = 2 | Bluebird Media, L.L.C. | Bluebird under estimated the amount of time needed to negotiate final equipment contracts with two major vendors. This has delayed procuring the equipment but will not delay rolling out the equipment across the network. Bluebird also had one of their construction contractors miss the scheduled deadline for all their segment completion dates. This contractor has been removed from the project and has been replaced with a company that is currently working on a different Bluebird segment. Bluebird believes the replacing contractor has the capability to take over this segment and get the constructions completed on schedule. | Potential delays and challenges Bluebird Media anticipates during the next quarter include the possibility of worse winter weather than expected. Bluebird Media also faces the challenge of working diligently to receive network equipment, then deploying this equipment to the shelters as they are constructed, and then start testing the network as the build of the segments are completed. | TRUE
NT10BIX5570091 | 2012 | Q1 | Q1 - 2012 | Four contractors and several sub-contractros worked on several different infrastructure segments across the northern 59 counties in Missouri. During this quarter, these contractors deployed 225 of new network miles of fiber. This was a substantial increase from the prior quarter of deploying 156 miles of fiber as one additional project was started while another contractor took over a lagging project. Bluebird looks to have new network miles increase during the next quarter as one additional project will begin. Bluebird completed a Master Service Agreement with a electronic network equipment provider for Dense Wavelength Division Multiplexing (DWDM) equipment in the prior quarter and had received one third of this equipment during this quarter. None of the equipment had been paid for during the quarter but had been received. Bluebird also received DWDM equipment to set up as a lab for testing and troubleshooting Bluebird's future network. Through a competitive bidding process, Bluebird posted two Request for Proposals on Bluebird's web site during the quarter. These were related to a bridge attachment across the Missouri River near Boonville and additional labor for installing equipment in the communication shelters. Two vendors were selected during this process and started working during the quarter. Node Site Civil Construction started during this quarter completing several sites while some sites are ongoing. Bluebird took delivery of several shelters during this quarter and completed the construction of three shelters. Bluebird continued construction at their internet Gateway in St. Louis and completed the construction a Gateway in Kansas City. Bluebird completed a route change with the NTIA changing a build route to a fiber IRU route. Bluebird continued to work on fiber IRU agreements with several companies. Bluebird continued Davis-Bacon wage compliance during the quarter and was working with the DOL for a few wage conformances. Bluebird also received a site visit from the Federal Program Officer during this quarter. Bluebird continued a community outreach campaign that included; educating key general assembly members about Bluebird Media, sending out brochures and collateral materials to Community Anchor Institutions, and staying involved with MO Broadband Now initiatives. | 443 | 0 | 0 | 0 | 443 | 0 | 0 | 0 | 17 miles behind revised baseline caused by one of the four contractors not completing their segments by the end of Q4 2011 as planned. The plan is to catch up to the revised baseline during Q2 2012 as this contractor has been replaced. The construction of the network build will continuously carry on without delays with the current construction companies in place. | NA | NA | 317 miles behind revised baseline due to delay in signing fiber IRU agreements with several parties. The plan is to catch up to the revised baseline during Q2-2012 once several fiber IRU agreements are finalized. | 17 miles behind revised baseline caused by one of the four contractors not completing their segments by the end of Q4 2011 as planned. The plan is to catch up to the revised baseline during Q2 2012 as this contractor has been replaced. The construction of the network build will continuously carry on without delays with the current construction companies in place. | NA | NA | 16 interconnection points behind revised baseline due to delay in construction of new network miles. This delay was caused by the 45 day delay in obtaining construction permits during the first part of Q3 2011 delaying construction startup. The plan is to catch up to the revised baseline during Q2-2012 once several network segments are completed. | 0 | 22 | 0 | Bluebird Media is currently behind the revised baseline due to not having any fiber turned up to date. Bluebird Media has wholesalers and last mile providers ready to sign agreements once certain segments of the fiber has been turned up. Bluebird Media plans to catch up to the revised baseline during Q2-2012 once fiber is turned up. | Dedicated Internet Access, Extended Local Area Network, Extended Wide Area Network, etc. Pricing plans are being currently developed. | NA | 0 | 0 | 0 | 0 | No turned up fiber to date, fiber being turned up during Q2-2012 will allow Bluebird to catch up to baseline by Q3-2012. | No turned up fiber to date, fiber being turned up during Q2-2012 will allow Bluebird to catch up to baseline by Q3-2012. | No turned up fiber to date, fiber being turned up during Q2-2012 will allow Bluebird to catch up to baseline by Q3-2012. | 50 MB - 1GB are the speed tiers that will be available. No subscribers since no turned up to date. | 0 | 0 | 0 | 0 | No turned up fiber to date, fiber being turned up during Q2-2012 will allow Bluebird to catch up to baseline by Q3-2012. | No turned up fiber to date, fiber being turned up during Q2-2012 will allow Bluebird to catch up to baseline by Q3-2012. | No turned up fiber to date, fiber being turned up during Q2-2012 will allow Bluebird to catch up to baseline by Q3-2012. | 10MB-10GB are the speed tiers that are available. No subscribers since no turned up to date. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | No special offerings at this time. | FALSE | NA | Bluebird's environmental engineering firm will continue to monitor environmental assessment to comply with the Special Award Conditions while the infrastructure is being built. Bluebird will continue to apply for construction permits and railroad permits in a timely manner to ensure the construction companies are not waiting on permits. Bluebird plans to continue site preparation for the node sites, continue constructing shelters for Node sites, and plans to have ground breaking ceremonies across the state once fiber starts to be turned up this quarter. Bluebird will procure the remaining DWDM equipment and complete procurement of the Multiprotocol Label Switching equipment during the next quarter. Bluebird plans to connect their first CAI to the network during the next quarter. Bluebird also plans to devise a rate structure for all products offered in the future. Bluebird will continue to design and implement a Community Outreach Plan including education for community and elected officials along fiber route. Local leaders and media will be notified of these press events. Bluebird will continue to monitor covered worked for Davis-Bacon wage compliance and conduct wage interview during the next quarter. Bluebird would suspect the DOL will provide a response to the wage conformances during the next quarter. Bluebird Media plans to catch up and surpass the revised baseline for new network miles deployed of 612 during this next quarter, and catch up to schedule for new network miles leased of 353 during the next quarter. Bluebird Media plans to be behind the revised baseline for CAI subscribers served and for the number of signed agreements with broadband wholesalers or last mile providers. The plan is to catch up those two indicators during Q3-2012 once certain fiber routes have been turned up allowing Bluebird Media to connect CAIs and sign agreements with providers. Bluebird Media plans to be at the following infrastructure key indicators at the end of the next quarter: -New Network Miles Deployed = 650 -New Network Miles Leased = 353 -Total CAI Subscribers Served = 3 -Number of Signed Agreements with wholesalers/last mile providers = 2 Lastly, Bluebird Media plans to attend the Creating Sustainable Broadband Solutions for Communities and Anchor Institutions conference in Washington D.C. from May 22 to 24, 2012. | Bluebird Media, L.L.C. | Bluebird under estimated the amount of time needed to receive and check in equipment. This has delayed procuring the equipment but will not delay rolling out the equipment across the network. Bluebird replaced one of the build segments with a contractor that has the capability to take over that segment and get the constructions completed on schedule after the prior contractor was not performing. This segment started to catch up during Q1 2012 and Bluebird suspects this segment will be caught up by the end of Q2 2011. Bluebird is also working on selecting an appraiser that can value the in-kind donation of rights-of-ways and parcel of lands provided by the State of Missouri. Bluebird faces a time crunch of getting the appraiser completed by June 30, 2012. Bluebird faced the issue of completing a route change during this quarter. The NTIA changed the format and process of route changes that added complexity and increase the time to complete the route change. | Bluebird Media faces the challenge of working diligently to receive network equipment, then deploying this equipment to the shelters as they are constructed, and then start testing the network as the build of the segments are completed. Bluebird Media also is negotiating pulling fiber along a bridge while using another partner's existing corridor. Bluebird would like to save time and money by using this existing corridor. | TRUE
NT10BIX5570091 | 2012 | Q2 | Q2 - 2012 | Three contractors and several subcontractors worked on several different infrastructure segments across the northern 59 counties in Missouri. During this quarter, these contractors deployed 265 of new network miles of fiber. This was a substantial increase from the prior quarter of deploying 225 miles of fiber as three additional projects were started during this quarter. Bluebird looks to have new network miles increase during the next quarter as several project will be completed. Bluebird received several shipments of Dense Wavelength Division Multiplexing (DWDM) network equipment during Q2 2012. Node Site Civil Construction continued during this quarter completing several sites while some sites are still ongoing. Bluebird took delivery of several shelters during this quarter and completed the construction of 16 shelters. Bluebird completed construction at their internet Gateway in St. Louis and turned up DWDM equipment, routers, and fiber network hardware at eight node locations. Bluebird continued to negotiate the terms on fiber IRU agreements with several companies during the quarter. Bluebird continued Davis-Bacon wage compliance and received two wage conformances from the DOL during the quarter. Through a competitive bidding process, Bluebird posted one Request for Proposal on Bluebird's web site during the quarter related to appraising rights-of-ways and parcels of land. One vendors was selected during this process and started working during the quarter on appraising the value of the in-kind donation of rights-of-ways and parcel of lands provided by the State of Missouri. Bluebird continued a community outreach campaign that included; educating key general assembly members about Bluebird Media, reaching out and visiting Community Anchor Institutions, and staying involved with MO Broadband Now initiatives. | 708 | 0 | 0 | 0 | 708 | 0 | 0 | 0 | 96 miles ahead of the baseline. The plan is to stay ahead of schedule for the remainder of the project. | NA | NA | 353 miles behind revised baseline due to delay in signing fiber IRU agreements with several parties. The plan is to catch up to the revised baseline during Q3-2012 once several fiber IRU agreements are finalized. | 96 miles ahead of the baseline. The plan is to stay ahead of schedule for the remainder of the project. | NA | NA | 18 interconnection points behind revised baseline due to delay in construction of new network miles. This delay was caused by the 45 day delay in obtaining construction permits during the first part of Q3 2011 delaying construction startup. The plan is to catch up to the revised baseline during Q3-2012 once several network segments are completed. | 0 | 22 | 0 | Bluebird Media is currently behind the revised baseline due to having a small amount of fiber turned up to date. Bluebird Media has wholesalers and last mile providers ready to sign agreements once certain segments of the fiber has been turned up. Bluebird Media plans to catch up to the revised baseline during Q3-2012 once fiber is turned up. | Dedicated Internet Access, Extended Local Area Network, Extended Wide Area Network, etc. Pricing plans are being currently developed. | NA | 0 | 0 | 0 | 0 | Small amount of turned up fiber to date, fiber being turned up during Q3-2012 will allow Bluebird to catch up to baseline by the end of Q3-2012. | Small amount of turned up fiber to date, fiber being turned up during Q3-2012 will allow Bluebird to catch up to baseline by the end of Q3-2012. | Small amount of turned up fiber to date, fiber being turned up during Q3-2012 will allow Bluebird to catch up to baseline by the end of Q3-2012. | 50 MB - 1GB are the speed tiers that will be available. No subscribers to date. | 0 | 0 | 0 | 0 | Small amount of turned up fiber to date, fiber being turned up during Q3-2012 will allow Bluebird to catch up to baseline by the end of Q3-2012. | Small amount of turned up fiber to date, fiber being turned up during Q3-2012 will allow Bluebird to catch up to baseline by the end of Q3-2012. | Small amount of turned up fiber to date, fiber being turned up during Q3-2012 will allow Bluebird to catch up to baseline by the end of Q3-2012. | 10MB-10GB are the speed tiers that are available. No subscribers to date. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | No special offerings at this time. | FALSE | NA | Bluebird's environmental engineering firm will continue to monitor environmental assessment to comply with the Special Award Conditions while the infrastructure is being built. Bluebird will continue to apply for construction permits and railroad permits in a timely manner to ensure the construction companies are not waiting on permits. Bluebird plans to continue site preparation for the node sites, continue constructing shelters for Node sites, and plans to have ground breaking ceremonies across the state once fiber starts to be turned up this quarter. Bluebird will procure the remaining DWDM equipment and complete procurement of the Multiprotocol Label Switching equipment during the next quarter. Bluebird plans to connect their first CAI to the network during the next quarter. Bluebird also plans to devise a rate structure for all products offered in the future. Bluebird will continue to design and implement a Community Outreach Plan including education for community and elected officials along fiber route. Local leaders and media will be notified of these press events. Bluebird will continue to monitor covered worked for Davis-Bacon wage compliance and conduct wage interview during the next quarter. Bluebird Media plans to continue to surpass the revised baseline for new network miles deployed of 753 during this next quarter, and catch up to schedule for new network miles leased of 422 during the next quarter. Bluebird Media plans to be behind the revised baseline for CAI subscribers served and for the number of signed agreements with broadband wholesalers or last mile providers. The plan is to catch up those two indicators during Q4-2012 once certain fiber routes have been turned up allowing Bluebird Media to connect CAIs and sign agreements with providers. Bluebird Media plans to be at the following infrastructure key indicators at the end of the next quarter: -New Network Miles Deployed = 850 -New Network Miles Leased = 422 -Total CAI Subscribers Served = 3 -Number of Signed Agreements with wholesalers/last mile providers = 4 Lastly, Bluebird Media plans to have a valuation completed by a certified appraiser by 7-31-12 valuing the in-kind donation of rights-of-way and parcels of land. | Bluebird Media, L.L.C. | Bluebird under estimated the amount of time needed to receive and check in electronic equipment. This has delayed procuring the equipment, but will not delay rolling out the equipment across the network as these orders were made in advance. Bluebird replaced one of the build segments with a contractor that has the capability to take over that segment and get the construction completed on schedule after the prior contractor was not performing. This segment was very close to getting caught up during Q2 2012 after Bluebird faced the challenge of getting a new contractor to pick up where the last contractor left off. | Bluebird Media faces the challenge of working diligently to receive network equipment, then deploying this equipment to the shelters as they are constructed, and then start testing the network as the build of the segments are completed. Bluebird Media also is negotiating pulling fiber along a bridge while using another partner's existing corridor. Bluebird would like to save time and money by using this existing corridor. Bluebird also faces the challenge of completing a valuation of the in-kind donation by 7.31.12. | TRUE
NT10BIX5570091 | 2012 | Q3 | Q3 - 2012 | Three contractors and several subcontractors worked on several different infrastructure segments across the northern 59 counties in Missouri. During this quarter, these contractors deployed 71 of new network miles of fiber. Bluebird looks to have new network miles increase during the next quarter as several project will be completed. Bluebird broke out their construction into 7 builds. Of those 7 builds, one is 100 percent complete, 5 are above 95% complete, and the remaining metro build is 75% complete. During the quarter Bluebird successfully completed a river bore across the Missouri River. Bluebird received a few shipments of Dense Wavelength Division Multiplexing (DWDM) and Multiprotocol Label Switching (MPLS) networking equipment during Q3 2012. Node Site Civil Construction continued during this quarter completing several sites while some sites are still ongoing. Bluebird took delivery of several shelters during this quarter and completed the construction of 6 shelters. Bluebird turned up DWDM equipment, routers, and fiber network hardware at nine node locations. Bluebird continued to negotiate the terms on fiber IRU agreements with a few companies during the quarter. Bluebird continued Davis-Bacon wage compliance during the quarter. Through a competitive bidding process, Bluebird hired an independent appraiser to appraise rights-of-ways and parcels of land during Q2 and Q3 2012. The appraised value of the in-kind donation of rights-of-ways and parcel of lands provided by the State of Missouri was recorded by Bluebird during Q3-2012. Bluebird continued a community outreach campaign that included; educating key general assembly members about Bluebird Media, reaching out and visiting Community Anchor Institutions, and staying involved with MO Broadband Now initiatives. | 779 | 0 | 0 | 137 | 779 | 0 | 0 | 40 | 26 miles ahead of the baseline. The plan is to stay ahead of schedule for the remainder of the project. | NA | NA | 285 miles behind revised baseline due to delay in signing fiber IRU agreements with a few parties. The plan is to catch up to the revised baseline during Q4-2012 once the remaining fiber IRU agreements are finalized. | 26 miles ahead of the baseline. The plan is to stay ahead of schedule for the remainder of the project. | NA | NA | No variance from baseline plan or subsequent written updates provided to the program officer. | 22 | 5 | 20 | Bluebird would like to refrain from including the names of the broadband wholesales due to the names being proprietary. The agreements Bluebird has with these providers are proprietary and confidential. | Dedicated Internet Access, Extended Local Area Network, Extended Wide Area Network, etc. Pricing plans are being currently developed. | NA | 7 | 15 | 0 | 22 | 5 subscribers ahead of the baseline. The plan is to stay ahead of subscribers for the remainder of the project. | 10 subscribers ahead of the baseline. The plan is to stay ahead of subscribers for the remainder of the project. | 1 Agreement has been signed which agrees to the revised baseline plan, but the schedule for the dark fiber to be turned up is Q1-2013 when the construction has been completed. | 50 MB - 1GB are the speed tiers that will be available. All of the broadband wholesalers or last mile providers subscriber for speed tiers between 50 MB -1 GB. | 0 | 0 | 0 | 0 | Small amount of turned up fiber to date, fiber being turned up during Q4-2012 will allow Bluebird to catch up to baseline by the end of Q4-2012. | Small amount of turned up fiber to date, fiber being turned up during Q4-2012 will allow Bluebird to catch up to baseline by the end of Q4-2012. | Small amount of turned up fiber to date, fiber being turned up during Q4-2012 will allow Bluebird to catch up to baseline by the end of Q4-2012. | 10MB-10GB are the speed tiers that are available. No subscribers to date. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | No special offerings at this time. | FALSE | NA | Bluebird's environmental engineering firm will continue to monitor environmental assessment to comply with the Special Award Conditions while the infrastructure is being built. Bluebird will continue to apply for construction permits and railroad permits in a timely manner to ensure the construction companies are not waiting on permits. Bluebird plans to continue site preparation for the node sites, continue constructing shelters for Node sites, and plans to have ground breaking ceremonies across the state once fiber starts to be turned up this quarter. Bluebird will procure the remaining DWDM equipment and complete procurement of the MPLS equipment during the next quarter. Bluebird plans to connect all of their CAIs to the network during the next quarter. Bluebird also plans to devise a rate structure for all products offered in the future. Bluebird will continue to design and implement a Community Outreach Plan including education for community and elected officials along fiber route. Local leaders and media will be notified of these press events. Bluebird will continue to monitor covered worked for Davis-Bacon wage compliance and conduct wage interview during the next quarter. Bluebird Media plans to continue to surpass the revised baseline for new network miles deployed of 894 during this next quarter, and catch up to schedule for new network miles leased of 563 during the next quarter. Bluebird Media plans to catch up to the revised baseline for CAI subscribers served. The plan is to catch to this indicator during Q4-2012 once certain fiber routes have been turned up allowing Bluebird Media to connect CAIs. Bluebird Media plans to be at the following infrastructure key indicators at the end of the next quarter: -New Network Miles Deployed = 900 -New Network Miles Leased = 575 -Total CAI Subscribers Served = 102 | Bluebird Media, L.L.C. | Bluebird faced the challenge of boring the Missouri River during Q3-2012. It became a much larger challenge when the contractor hit bed rock much sooner than expected. The time of the project went from days to weeks, but was completed during Q3-2012. | Bluebird Media faces the challenge of working diligently to receive network equipment, then deploying this equipment to the shelters as they are constructed, and then start testing the network as the build of the segments are completed. Bluebird faces the challenge of completing the last build segment in metro St. Louis. Permitting is tougher in a metro city and challenges the time it takes to get permits in place. | TRUE
NT10BIX5570091 | 2012 | Q4 | Q4 - 2012 | Three contractors and several subcontractors worked on several different infrastructure segments across the northern 59 counties in Missouri. During this quarter, these contractors deployed 14 new network miles of fiber and placed 29 miles of innerduct for new network miles of fiber to be added next quarter. Bluebird broke out their construction into 7 builds. Of those 7 builds, one is 100 percent complete, 5 are above 95% complete, and the remaining metro build is 25% complete. Bluebird received a few shipments of Dense Wavelength Division Multiplexing (DWDM) and Multiprotocol Label Switching (MPLS) networking equipment during Q4 2012. Node Site Civil Construction continued during this quarter completing several sites while some sites are still ongoing. Bluebird took delivery of several shelters during this quarter and completed the construction of seven shelters. Bluebird turned up DWDM equipment, routers, and fiber network hardware at seven node locations. Bluebird continued to negotiate the terms on fiber IRU agreements with a few companies during the quarter. Bluebird continued Davis-Bacon wage compliance during the quarter. Bluebird continued a community outreach campaign that included; educating key general assembly members about Bluebird Media, reaching out and visiting Community Anchor Institutions, and staying involved with MO Broadband Now initiatives. | 793 | 0 | 0 | 376 | 793 | 0 | 0 | 48 | 101 miles behind revised baseline. Delay caused by permits being slowly obtained in the St. Louis metro area. Total miles deployed does not count 29 miles of innerduct placed in the St. Louis metro area waiting for fiber to be place. | NA | NA | 187 miles behind revised baseline due to delay in signing fiber IRU agreements with a few parties. The plan is to catch up to the revised baseline during Q1-2013 once the remaining fiber IRU agreements are finalized. | 101 miles behind revised baseline. Delay caused by permits being slowly obtained in the St. Louis metro area. Total miles deployed does not count 29 miles of innerduct placed in the St. Louis metro area waiting for fiber to be place. | NA | NA | No variance from baseline plan or subsequent written updates provided to the program officer. | 22 | 5 | 20 | Bluebird would like to refrain from including the names of the broadband wholesales due to the names being proprietary. The agreements Bluebird has with these providers are proprietary and confidential. | Dedicated Internet Access, Extended Local Area Network, Extended Wide Area Network, etc. Pricing plans are being currently developed. | NA | 7 | 15 | 0 | 22 | 5 subscribers ahead of the baseline. The plan is to stay ahead of subscribers for the remainder of the project. | 8 subscribers ahead of the baseline. The plan is to stay ahead of subscribers for the remainder of the project. | 1 Agreement has been signed which agrees to the revised baseline plan, but the schedule for the dark fiber to be turned up is Q1-2013 when the construction has been completed. | 50 MB - 1GB are the speed tiers that will be available. All of the broadband wholesalers or last mile providers subscriber for speed tiers between 50 MB -1 GB. | 0 | 0 | 0 | 0 | Small amount of turned up fiber to date, fiber being turned up during Q1-2013 will allow Bluebird to catch up to baseline by the end of Q1-2013. | Small amount of turned up fiber to date, fiber being turned up during Q1-2013 will allow Bluebird to catch up to baseline by the end of Q1-2013. | Small amount of turned up fiber to date, fiber being turned up during Q1-2013 will allow Bluebird to catch up to baseline by the end of Q1-2013. | Small amount of turned up fiber to date, fiber being turned up during Q1-2013 will allow Bluebird to catch up to baseline by the end of Q1-2013. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | No special offerings at this time. | FALSE | NA | Bluebird's environmental engineering firm will continue to monitor environmental assessment to comply with the Special Award Conditions while the infrastructure is being built. Bluebird will continue to apply for construction permits and railroad permits in a timely manner to ensure the construction companies are not waiting on permits. Bluebird is planning on issuing a Request for Proposal for a bridge attachment near Washington, Missouri and having the attachment completed during the next quarter. Bluebird plans to continue site preparation for the node sites, continue constructing shelters for Node sites, and plans to have ground breaking ceremonies across the state once fiber starts to be turned up this quarter. Bluebird will procure the remaining DWDM equipment and complete procurement of the MPLS equipment during the next quarter. Bluebird plans to connect all of their CAIs to the network during the next quarter. Bluebird also plans to devise a rate structure for all products offered in the future. Bluebird will continue to design and implement a Community Outreach Plan including education for community and elected officials along fiber route. Local leaders and media will be notified of these press events. Bluebird will continue to monitor covered worked for Davis-Bacon wage compliance and conduct wage interview during the next quarter. Bluebird Media plans to obtain the revised baseline for new network miles deployed of 941 during this next quarter, and catch up to schedule for new network miles leased of 563 during the next quarter. Bluebird Media plans to catch up to the revised baseline for CAI subscribers served. The plan is to catch to this indicator during Q1-2013 once certain fiber routes have been turned up allowing Bluebird Media to connect CAIs. Bluebird Media plans to be at the following infrastructure key indicators at the end of the next quarter: -New Network Miles Deployed = 941 -New Network Miles Leased = 575 -Total CAI Subscribers Served = 102 | Bluebird Media, L.L.C. | Bluebird faced the challenge of deciding to bore or attach to a bridge to get across the Missouri River near Washington Missouri during Q1-2013. It became a much larger challenge when the Missouri Department of Transportation provided information on the future destruction of the bridge many years down the road. Bluebird plans to issue a competitive bid to attach to a bridge to cross the Missouri River during Q1-2013. | Bluebird Media faces the challenge of working diligently to receive network equipment, then deploying this equipment to the shelters as they are constructed, and then start testing the network as the build of the segments are completed. Bluebird faces the challenge of completing the last build segment in metro St. Louis. Permitting is tougher in a metro city and challenges the time it takes to get permits in place. | TRUE
NT10BIX5570091 | 2013 | Q1 | Q1 - 2013 | Two contractors and several subcontractors worked on several different infrastructure segments across the northern 59 counties in Missouri. During this quarter, these contractors deployed 37 new network miles of fiber. Bluebird broke out their construction into seven builds. Of those seven builds, six are 100 percent complete, with one segment remaining at 95% complete. Bluebird issued a Request for Proposal for a bridge attachment near Washington, Missouri, selected a contractor, and had the attachment completed during the quarter. Bluebird received a few shipments of Dense Wavelength Division Multiplexing (DWDM) and Multiprotocol Label Switching (MPLS) networking equipment during Q1 2013. Node Site Civil Construction continued during this quarter completing several sites while some sites are still ongoing. Bluebird took delivery of several shelters during this quarter and completed the construction of seven shelters. Bluebird turned up DWDM equipment, routers, and fiber network hardware at five node locations. Bluebird continued to negotiate the terms on fiber IRU agreements with a few companies during the quarter. Bluebird continued Davis-Bacon wage compliance during the quarter. Bluebird continued a community outreach campaign that included; educating key general assembly members about Bluebird Media, reaching out and visiting Community Anchor Institutions, and staying involved with MO Broadband Now initiatives. | 831 | 0 | 0 | 376 | 831 | 0 | 0 | 57 | 110 miles behind revised baseline. Delay caused by finalizing last few shelter locations. Total miles deployed does not count pipe attachment to a Missouri River bridge awaiting for fiber to be placed. | NA | NA | 187 miles behind revised baseline due to delay in signing fiber IRU agreements with a few parties. The plan is to catch up to the revised baseline during Q2-2013 once the remaining fiber IRU agreements are finalized. | 110 miles behind revised baseline. Delay caused by finalizing last few shelter locations. Total miles deployed does not count pipe attachment to a Missouri River bridge awaiting for fiber to be placed. | NA | NA | No variance from baseline plan or subsequent written updates provided to the program officer. | 24 | 5 | 20 | Bluebird would like to refrain from including the names of the broadband wholesales due to the names being proprietary. The agreements Bluebird has with these providers are proprietary and confidential. | Dedicated Internet Access, Extended Local Area Network, Extended Wide Area Network, etc. Pricing plans are being currently developed. | NA | 7 | 17 | 0 | 24 | 4 subscribers ahead of the baseline. The plan is to stay ahead of subscribers for the remainder of the project. | 9 subscribers ahead of the baseline. The plan is to stay ahead of subscribers for the remainder of the project. | 1 Agreement has been signed which is 1 less than the revised baseline plan. The schedule for the dark fiber to be turned up is Q2-2013 when the construction has been completed. | 50 MB - 1GB are the speed tiers that will be available. All of the broadband wholesalers or last mile providers subscriber for speed tiers between 50 MB -1 GB. | 0 | 0 | 0 | 0 | Small amount of turned up fiber to date, fiber being turned up during Q2-2013 will allow Bluebird to catch up to baseline by the end of Q2-2013. | Small amount of turned up fiber to date, fiber being turned up during Q1-2013 will allow Bluebird to catch up to baseline by the end of Q2-2013. | Small amount of turned up fiber to date, fiber being turned up during Q2-2013 will allow Bluebird to catch up to baseline by the end of Q2-2013. | Small amount of turned up fiber to date, fiber being turned up during Q2-2013 will allow Bluebird to catch up to baseline by the end of Q2-2013. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | No special offerings at this time. | FALSE | NA | Bluebird's environmental engineering firm will continue to monitor environmental assessment to comply with the Special Award Conditions while the infrastructure is being built and the CAIs are connected. Bluebird will continue to apply for construction permits and railroad permits in a timely manner to ensure the construction companies are not waiting on permits. Bluebird plans to continue site preparation for the node sites, continue constructing shelters for Node sites, and plans to have ground breaking ceremonies across the state once fiber starts to be turned up this quarter. Bluebird will procure the remaining DWDM equipment and complete procurement of the MPLS equipment during the next quarter. Bluebird plans to connect all of their CAIs to the network during the next quarter. Bluebird also plans to devise a rate structure for all products offered in the future. Bluebird will continue to design and implement a Community Outreach Plan including education for community and elected officials along fiber route. Local leaders and media will be notified of these press events. Bluebird will continue to monitor covered worked for Davis-Bacon wage compliance and conduct wage interview during the next quarter. Bluebird Media plans to obtain the revised baseline for new network miles deployed of 941 during this next quarter, and catch up to schedule for new network miles leased of 563 during the next quarter. Bluebird Media plans to catch up to the revised baseline for CAI subscribers served. The plan is to catch to this indicator during Q2-2013 once certain fiber routes have been turned up allowing Bluebird Media to connect CAIs. Bluebird Media plans to be at the following infrastructure key indicators at the end of the next quarter: -New Network Miles Deployed = 941 -New Network Miles Leased = 575 -Total CAI Subscribers Served = 102 | Bluebird Media, L.L.C. | Bluebird faced the challenge of finding a third party parcel of land to lease for the last node site. This site was selected near the end of the quarter, but Bluebird still faced getting all the documents in place to finalize a lease for this site. Bluebird also faced very wet weather during the month of March causing some of the final construction progress to be delayed. | None | TRUE
NT10BIX5570091 | 2013 | Q2 | Q2 - 2013 | One contractor worked on one infrastructure segment across the northern 59 counties in Missouri. During this quarter, this contractor deployed 2 new network miles of fiber while completing a bridge attachment. Bluebird broke out their construction into seven builds. Of those seven builds, all seven are 100 percent complete. Bluebird received a few shipments of Dense Wavelength Division Multiplexing (DWDM) and Multiprotocol Label Switching (MPLS) networking equipment during Q2 2013 for the remaining Community Anchor Institutions (CAI) . Bluebird was approved to connect to 76 CAIs while 46 of these CAIs had been connected during this quarter. Node Site Civil Construction continued during this quarter completing several sites while some sites are still ongoing. Bluebird took delivery of several shelters during this quarter and completed the construction of several shelters. Bluebird turned up DWDM equipment, routers, and fiber network hardware at several of these node locations. Bluebird continued to negotiate the terms on fiber IRU agreements with a few companies during the quarter. Bluebird continued Davis-Bacon wage compliance during the quarter. Bluebird continued a community outreach campaign that included; educating key general assembly members about Bluebird Media, reaching out and visiting CAIs, and staying involved with MO Broadband Now initiatives. | 833 | 0 | 0 | 376 | 833 | 0 | 0 | 57 | No variance from baseline plan or subsequent written updates provided to the program officer. | NA | NA | 187 miles behind revised baseline due to delay in signing fiber IRU agreements. The plan is to catch up to the subsequent written updates provided to the program officer during Q3-2013 once the remaining fiber IRU agreement is finalized. | No variance from baseline plan or subsequent written updates provided to the program officer. | NA | NA | No variance from baseline plan or subsequent written updates provided to the program officer. | 24 | 5 | 20 | Bluebird would like to refrain from including the names of the broadband wholesales due to the names being proprietary. The agreements Bluebird has with these providers are proprietary and confidential. | Dedicated Internet Access, Extended Local Area Network, Extended Wide Area Network, etc. Pricing plans are being currently developed.. | NA | 7 | 17 | 1 | 24 | 4 subscribers ahead of the baseline. The plan is to stay ahead of subscribers for the remainder of the project. | 9 subscribers ahead of the baseline. The plan is to stay ahead of subscribers for the remainder of the project. | 1 Agreement has been signed which is 1 less than the revised baseline plan. | 50 MB - 1GB are the speed tiers that will be available. All of the broadband wholesalers or last mile providers subscriber for speed tiers between 50 MB -1 GB. | 46 | 23 | 23 | 11 | Behind revised baseline by 56 CAIs. Several routes were finishing construction in late Q2-2013 and remaining 26 CAIs have been submitted for final approval. The plan is to connect all remaining CAIs by 7/31/2013. | Behind revised baseline by 79 CAIs. Several routes were finishing construction in late Q2-2013 and remaining 26 CAIs have been submitted for final approval. The plan is to connect all remaining CAIs by 7/31/2013 which will be mostly subscriber receiving new access. | Ahead revised baseline by 23 CAIs as the baseline plan did not include and subscribers receiving improved access. | Speed tiers available and the number of subscribers is as follows: 1.5 Meg 1; 5 Meg 6; 10 Meg 11; 20 Meg 7; 30 Meg 1; 50 Meg 9; 70 Meg 1; 100 Meg 4; 150 Meg 1; 250 Meg 3; 1000 Meg 2. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | No special offerings at this time. | FALSE | NA | Bluebird's environmental engineering firm will continue to monitor environmental assessment to comply with the Special Award Conditions while the CAIs are connected. Bluebird plans to continue constructing shelters for Node sites, and plans to have ground breaking ceremonies across the state once fiber starts to be turned up this quarter. Bluebird will procure the remaining DWDM equipment and complete procurement of the MPLS equipment during the next quarter. Bluebird plans to connect the remaining 56 CAIs to the network during the next quarter. Bluebird will continue to design and implement a Community Outreach Plan including education for community and elected officials along fiber routes. Local leaders and media will be notified of these press events. Bluebird will continue to monitor covered workers for Davis-Bacon wage compliance and conduct wage interviews during the next quarter. Bluebird Media plans to adjust the revised baseline for new network miles deployed below 941 during this next quarter to reflect the 833 actual built miles, and catch up to schedule for an adjusted new network miles leased of 485 during the next quarter. Bluebird Media plans to catch up to the revised baseline for CAI subscribers served. The plan is to catch to this indicator during Q3-2013 once certain fiber routes have been turned up allowing Bluebird Media to connect remaining CAIs. Bluebird Media plans to be at the following infrastructure key indicators at the end of the next quarter: -New Network Miles Deployed = 833 -New Network Miles Leased = 485 -Total CAI Subscribers Served = 102 | Bluebird Media, L.L.C. | Bluebird faced the challenge of signing a fiber IRU lease. Bluebird also faced getting several CAIs connected quickly once the CAIs were approved in April. | Bluebird plans on getting the remaining CAIs approved and adjusting the new network miles deployed and old network miles leased to reflect actual amounts. Bluebird will identify all close out documents during this period and utilize BTOP assistance to ensure all documents have been complete accurately and timely. | TRUE
NT10BIX5570091 | 2013 | Q3 | Q3 - 2013 | Bluebird received a few shipments of Dense Wavelength Division Multiplexing (DWDM) and Multiprotocol Label Switching (MPLS) networking equipment during July 2013 for the remaining Community Anchor Institutions (CAI). Bluebird was approved to connect to all 102 CAIs while 56 of these CAIs were connected during this month. Bluebird took delivery of 2 shelters during this quarter and completed the construction and site civil on several shelters. Bluebird turned up DWDM equipment, routers, and fiber network hardware at several of these node locations. Bluebird continued Davis-Bacon wage compliance during the month. Bluebird was approved to eliminate a few redundancy routes from the project in order to reduce costs. These routes being eliminated did not effect the number of communities Bluebird was approved to serve included in the baseline. Bluebird continued a community outreach campaign that included; educating key general assembly members about Bluebird Media, reaching out and visiting CAIs, and staying involved with MO Broadband Now initiatives. Prior to embarking on this BTOP project, Bluebird knew our customers had the need to join the statewide high-speed broadband networks. With the grant project now completely finished, we have made it possible, even in un-served and under-served rural areas, for our customers to obtain high speed broadband. During the project, Bluebird deployed a Network with the latest technology adding a 40-channel DWDM backbone and a 10GB MPLS network. A differentiating feature enabled by Bluebirdâ€™s BTOP project is a symmetrical network backbone, which is not generally available outside of metropolitan areas. Using the latest technology of optical fiber systems, Bluebirdâ€™s newly finished project supports scalable and symmetrical services in rural areas. Bluebird calculated the total impact of the BTOP Project reporting the following network metrics: -833 New Miles of Fiber -472 Existing Fiber Leased -98,097 Total Fiber Strand Miles Added -57 new/upgraded interconnection points -31 new shelters with 4,470 total square feet of collocation space added -5 new collocation points of presence including connection to two internet gateway buildings in Kansas City and Saint Louis Bluebird successfully connected 102 CAIs while averaging an increase in broadband speed provided of 20 Mb for those CAIs while keeping the customer cost comparable due to the grant. CAIs such as libraries, schools, colleges and universities, hospitals, medical providers, public safety entities, and government agencies will directly benefit from Bluebirdâ€™s symmetrical fiber route. They now can access an ultimate internet connection, faster than ever before. The following is a breakdown of the connected CAIs classification: 5-Community Colleges 4-Libraries 14-Medical and Healthcare Providers 2-Other Community Support Organizations 30-Other Governmental Facilities 10-Other Institutions of Higher Education 10-Public Safety Entities 27-Schools (K-12) As the project comes to a close, a total of $71.7 million was infused into the economy, over 715 full time equivalents had been reported quarterly, and un-served and under-served communities now have access or increased access to broadband technology. Bluebird states this has been a successful public-private partnership that will directly benefit rural and metro communities for years to come. We are happy to announce that Bluebirdâ€™s grant project has been completed on time and is bringing Missouriâ€™s internet connection to a whole new level. The completion of the project will broaden business potential for any company that seeks access to a true high-speed internet network in central and northern Missouri. | 833 | 0 | 0 | 472 | 833 | 0 | 0 | 57 | No variance from baseline plan or subsequent written updates provided to the program officer. | NA | NA | No variance from baseline plan or subsequent written updates provided to the program officer. | No variance from baseline plan or subsequent written updates provided to the program officer. | NA | NA | No variance from baseline plan or subsequent written updates provided to the program officer. | 25 | 5 | 20 | Bluebird would like to refrain from including the names of the broadband wholesales due to the names being proprietary. The agreements Bluebird has with these providers are proprietary and confidential. | Dedicated Internet Access, Extended Local Area Network, Extended Wide Area Network, etc. Pricing plans are unique to each individual customer. | NA | 7 | 17 | 1 | 24 | 4 subscribers ahead of the baseline. | 8 subscribers ahead of the baseline. | 1 Agreement has been signed which is 1 less than the revised baseline plan. | 50 MB - 1GB are the speed tiers that will be available. All of the broadband wholesalers or last mile providers subscriber for speed tiers between 50 MB -1 GB. | 102 | 73 | 29 | 5 | No variance from baseline plan or subsequent written updates provided to the program officer. | No variance from baseline plan or subsequent written updates provided to the program officer. | No variance from baseline plan or subsequent written updates provided to the program officer. | Speed tiers available and the number of subscribers is as follows: < 10 Meg 16; >= 10 Mb and < 50 Mb 50; >= 50 Mb and < 100 Mb 17; >=100 Mb and <1Gb 18; =>1 G 1. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | No special offerings at this time. | FALSE | NA | Bluebird will complete all appropriate close out documents and obtain an audit over the BTOP Grant. | Bluebird Media, L.L.C. | Bluebird faced getting several CAIs connected quickly once the CAIs were approved in mid July by July 31, 2013. | Bluebird will identify all close out documents during this period and utilize BTOP assistance to ensure all documents have been complete accurately and timely. | TRUE
NT10BIX5570093 | 2010 | Q4 | Q4 - 2010 | On December 10, 2010, Citizens sent out a Request For Proposal (RFP) for the engineering service contract for the NTIA/BTOP project. The proposals were due on December 28, 2010 at 4:00 p.m. EST. There were eleven (11) firms that responded with an RFP. Citizens begin reviewing the RFPâ€™s on December 29 and identified the 3 lowest bidders that met the qualification requirements. On December 30, 2010 Citizens called the low bidder to schedule a meeting with the firm to discuss the proposal and clarify questions and concerns. This meeting was scheduled for Monday, January 3, 2011 and complete contract negotiations by January 7, 2011. On December 14, 2010, Citizens completed contract negotiations with Earth Environmental and Civil, Inc. (EEC) from Rocky Mount, Virginia for engineering services to do the Joint Permit Application (JPA) with the Virginia Marine Resources Commission (VMRC), Department of Environmental Quality (DEQ), and Army Corp of Engineers. EEC began work on the JPA on December 15, 2010 and is coordinating with the Environmental Assessment team in the permit application process. Citizens met with and completed ride outs with the local Virginia Department of Transportation (VDOT) district offices. Overall, VDOT is in agreement with the scope of the project and foresee no issues at this time. There were three locations identified where VDOT plans future road improvements. One location is in the Town of Pearisburg where VDOT and the Town are scheduling im | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin projecf EA to begin project | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin projecf EA to begin project | N/A - Waiting on completion of EA to begin projecf EA to begin project | N/A - Waiting on completion of EA to begin project | 0 | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | 0 | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | 0 | 0 | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | 0 | 0 | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | N/A - Waiting on completion of EA to begin project | FALSE | N/A - Waiting on completion of EA to begin project | Citizens staff and the New River Valley Planning District Commission (NRVPDC) staff is scheduled to complete and submit the Environmental Assessment by February 1, 2011. The NRVPDC is the firm that Citizens contracted with to perform the BTOP requirements of the EA. The NRVPDC had contacted and received responses from most of the required agencies by the end of quarter 2. Environmental Earth and Civil, Inc. (EEC) is doing the engineering work for the Joint Permit Application to meet the requirements for steam and wetland crossings. EEC will be coordinating with the NRVPDC, NTIA, and BTOP officials in obtaining the JPA permitting requirements. Citizens will be contracting with Thompson & Litton, Inc. to assist the Citizens engineering staff in completing the field staking and network design by March 18, 2011. Thompson & Litton, Inc. will team with Citizens to prepare the construction contract and bid instructions and mail to the approved contractors list by March 31, 2011. Citizens engineering staff will submit for the required Virginia Department of Transportation (VDOT) permits, Norfolk & Southern railroad applications, Locality work permits, building permits, and joint use proposals by February 25, 2011. Citizens is currently negotiating will all these agencies and plans to have all permits, proposals, and agreements complete by March 31, 2011. Acquisition of property for the two proposed telecommunication huts is scheduled to be completed by March 31, 2011. Si | Citizens' Telephone Co-operative | Selection of the engineering firm became more difficult and more time consuming due to the number of respondents (11) and the wide range of cost proposals that were submitted. There were three firms that came in at less than one million dollars, five firms submitted proposals from one million to 1.4 million, and three firms that submitted proposals from 1.5 million to 2.1 million. The engineering firm is needed to assist Citizens staff in administering the construction contract, performing field staking and field engineering, and performing the construction and inspection service for the project. Citizens has been coordinating with the Virginia Cable Telecommunications Association, the Virginia Telecommunications Industry Association, other service providers, and Norfolk and Southern Railroad, and state legislators to have a better and more consistent process in place to do Railroad crossing. These negotiations have been going on for most of the 2010 calendar year with scheduled meetings in Richmond, Virginia and with conference calls between the parties. In late December, Norfolk and Southern Railroad agreed to work with Citizens and come up with a more consistent cost structure for the proposed 15 crossing in the project. In December, Citizens received notification form the Fish and Wildlife Service (FWS) that the Smooth Cone Flower has been identified in six locations within the project area. The FWS will provide more information in early January 2011 about the loca | Environmental Assessment. The pending issue with the Fish and Wildlife Service regarding the Smooth Cone Flower could delay the EA process. Citizens may need guidance and assistance from BTOP/NTIA project team with this issue if it can not be resolved without delaying the EA process. | TRUE
NT10BIX5570093 | 2011 | Q1 | Q1 - 2011 | The Environmental Assessment Draft was completed and submitted by Citizens and the New River Valley Planning District Commission (NRVPDC) in February. The NRVPDC has been actively corresponding with the FWS and other agencies to resolve questions and provide additional documentation when requested. Environmental Earth and Civil, Inc. completed the Joint Permit Application (JPA) for the stream and wetland crossings for the proposed fiber routes. This application was submitted to VMRC, DEQ, and the Army Corp in mid February. The field engineering and route staking is being done by Citizens and Thompson & Litton, Inc. Thompson & Litton started work on the project on January 21, 2011. Route staking and design is running slightly behind schedule and will be addressed further in the Milestone Categories under Network Design. Citizens completed ride outs and meetings with the Virginia Department of Transportation (VDOT) permit officials in early February. The performance bonds for the new counties have been obtained and are on file with VDOT. Citizens has also obtained the project performance bond that is required for the overall for the project permit. Citizens and VDOT have completed the amendments to the existing Memorandum of Understanding agreement and the agreement is currently processing through the signing stage. Once this document is finalized the project permit will be issued covering the total project. Railroad crossing permits with Norfolk Southern Railro | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project constructiof EA to begin project construction | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project constructiof EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | 0 | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | 0 | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | 0 | 0 | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | 0 | 0 | 0 | 0 | 0 | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | N/A - Waiting on completion of EA to begin project construction | FALSE | N/A - Waiting on completion of EA to begin project construction | All VDOT permits, locality work permits, rights of way agreements, and joint use arrangements will be completed by May 31, 2011. The construction contract(s) is scheduled to go out for bids on April 27, 2011 and the bids are due at 4:00 p.m. EST on May 12, 2011 at the Citizens Office in Floyd, VA. The contract(s) is scheduled to be evaluated and awarded by May 17, 2011. The selected contractor(s) will be promptly notified and Citizens will authorize the contractor to order supplies and materials and to make preparations to start construction. The construction start date is scheduled to be June 13, 2011. Site preparation and construction of the telecommunication huts will began by mid July. | Citizens' Telephone Co-operative | The bid process and selection of the contractor (s) could be more difficult due to bidding the project later in the construction season when fewer contractors may be available to submit bids. The availability of fewer contractors and the higher cost of fuel and construction materials could result in higher bids which could force a re-bidding of the project. This would delay the proposed construction start date and require adjusting the contract to try to attract lower bids without sacrificing the scope of the project design. As other BTOP, BIP, and normal telecommunications project gear up for construction the lead time on getting materials (especially fiber cable) could become longer which could delay construction start date or slow construction progress. Citizens is working with suppliers and giving advance notice of material requirements for the project to try to avoid lead time problems. Any further delays in getting final approval of the EA and JPA could affect the planned start on construction date. The BTOP program and program officer and staff have provided and guidance and feedback to Citizens in helping to keep the assessment process moving. | Further delays in the approval of the EA and JPA could affect the start date of beginning the construction process. Lead time on construction materials and supplies could delay the construction start date or slow the construction progress. | TRUE
NT10BIX5570093 | 2011 | Q2 | Q2 - 2011 | Correspondence continued through the 4th quarter with the various environmental agencies, NRVPDC, Citizens, and the NTIA Environmental Compliance Team on completing the Environmental Assessment (EA) for the 186 mile broadband project. Citizens received verbal notification on June 30, 2011 that the assessment had completed the final approval and that the FONSI would be issued in a few days. The only outstanding issue in the EA process is final response from two or three of the TPHOâ€™s. All of these agencies have been contacted by Citizens, NRVPDC, and NTIA. Citizens (CTC) and Thompson & Litton, Inc. (T&L) engineering staff completed field engineering design and staking on the proposed project routes on April 15, 2011. CTC and T&L decided to split the 186 mile project into 4 separate smaller construction contracts to help expedite the process and to attract a wider range of contractors. Three bid packages were sent out through the Citizens web site on April 27, 2011 for Contract I, II, and III. Contract IV will be sent out later in the fall. Bids were due on May 12, 2011 and six contractors submitted bids by the 4:00 pm deadline. CTC and T&L evaluated the bids and selected the low bidders on May 17, 2011. The winning bidders were notified by phone on May 17, 2011 of their successful bid. Notice of Award letters were sent to the winning contractors on May 27, 2011 which included authorization to the contractor to proceed with ordering fiber cable for the project. Th | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/1; issued on 6/30/11 | 0 | 0 | 0 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/1; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | 0 | 0 | 0 | 0 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | 0 | 0 | 0 | 0 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | 0 | 0 | 0 | 0 | 0 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | 0 | 0 | 0 | 0 | 0 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | N/A-Waiting on FONSI to begin construction; issued on 6/30/11 | FALSE | N/A | All locality work permits, rights of way agreements, and joint use arrangements will be completed by August 31, 2011. Citizens will research the fiber market and explore options to obtain fiber cable in order to start portions of the project sooner than waiting on the existing 25 â€“ 30 week fiber lead times advertised. Any new fiber options that are considered will meet current design specifications and strand count size. Citizens plans on starting Construction on Contract III with Lambertâ€™s Cable Splicing, LLC by July 25, 2011. This contract will include installation of the two telecommunication huts and installing fiber in the Town of Blacksburg and constructing fiber to schools in the Town of Blacksburg, Town of Christiansburg, and Montgomery County. Citizens plans to have approximately 3.5 miles of fiber construction complete on contract III by the end of the 1st quarter, year 2. Citizen will schedule start dates for contract I (Nichols Construction, LLC) and contract II (Lambertâ€™s Cable Splicing, LLC) as soon as ship dates for the fiber cable are known or fiber can be obtained from other sources. The anticipated start date for contract I & II is expected to be the first week of September, 2011. | Citizens' Telephone Co-operative | Working with the Towns and localities in obtaining work permits and agreements has been difficult and slow at times due to each locality having their own unique process and procedures. Some of the localities require public hearings or public notices to be scheduled for review of the agreements and then scheduled for approval by town councils or board of supervisors at their meeting which can mean waiting 1 â€“ 2 months depending on timing. The long lead time on obtaining fiber (25 â€“ 30 weeks) is making it difficult to schedule construction start dates with the contractors. The fiber manufacturers are unwilling to give ship dates for delivery at this time. The lead time for other materials is starting to extend also, which may add delays or slow progress along with the fiber situation. | Construction start dates are going to be impacted by the current long lead time in getting fiber optic cable and other materials. Fiber manufacturers are reluctant to give ship dates on fiber delivery which makes it very difficult to start any of the construction process. This puts Citizens, Thompson & Litton, Inc., and the Contractors in a difficult position because all the firms have organized and arranged their schedules and personnel to meet the previously anticipated milestone timelines. CTC and T&L will be reviewing all options to try to stay as close to the original milestone timelines as possible. There are options to do some of the construction process that can be done without having the fiber cable. Some of the work that can be done is directional boring, conduit/handhole placement, setting new poles, setting down guys and anchors, and hanging strand on aerial cable routes. | TRUE
NT10BIX5570093 | 2011 | Q3 | Q3 - 2011 | Citizens received official notification of the approved FONSI during the first week of July 2011. The Citizens staff and Thompson & Litton, Inc. awarded three Outside Plant Construction Contracts during the 5th quarter. The proposed 186 mile fiber project was divided into 4 separate construction contracts. Three of the construction contracts have been awarded as follows: Contract I Nichols Construction, LLC 102 miles 180 days Contract II Lambertâ€™s Cable Splicing Co, LLC 70 miles 130 days Contract III Lambertâ€™s Cable Splicing Co, LLC 11 miles 90 days Starting construction has been delayed due to the extended lead times that the fiber cable manufacturers are now experiencing. The contractors placed orders for the fiber optic cable needed for their individual contracts in early June 2011. The scheduled fiber delivery dates for the project are as follows: Shipment 1 Contract III November 10, 2011 Shipment 2 Contract I November 30, 2011 Shipment 3 Contract II December 22, 2011 Shipment 4 Contract II December 29, 2011 Citizens was successful in locating a small amount of 144 strand fiber that would allow Contract III construction to begin sooner than the scheduled fiber delivery dates. Lambertâ€™s Cable Splicing Co., LLC started construction on Contract III on July 27, 2011. As of September 30, 2011 approximately 5 miles of fiber optic cable had been installed and 45 days of the 90 day Contract. Service drop construction has been completed to 5 Mont | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | Citizens had anticipated approximately 37 miles complete by the end of quarter 5. Due to the unavailable fiber cable, construction on Contract I and Contract II has not begun. Construction work on Contract III is in progress. | No Variance | No Variance | No Variance | Citizens had anticipated having 37 miles of new fiber installed by the end of quarter 5. Due to the unavailable fiber cable, construction on Contract I and Contract II has not begun. Construction work on Contract III is in progress. | No Variance | No Variance | No Variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | N/A | FALSE | N/A | Citizens will complete the lease agreement with Pulaski County for the Pulaski telecommunication hut site and obtain the necessary building and work permits with the county by mid-November, 2011. Two right of way agreements will be complete by mid- November, 2011. Contract III Construction in the Town of Blacksburg should be complete by the 2nd week of December, 2011. Splicing and testing on Contract should be complete by the end of December, 2011. This will include service drops complete to 13 CAIâ€™s and service activated at three of those locations. Site preparation for the two telecommunication huts and installation of the two huts will be completed by the end of November, 2011. Commercial power and generator installation will begin by mid-November, 2011 and should be complete by the end of January, 2012. Contract I Nichols Construction, LLC will begin preliminary construction on Contract I the 2nd week of October, 2011. Installation of strand, setting guys, installing anchors, and make ready adjustments on the poles are portions of the aerial work that needs to be completed in advance of the actual installation of the aerial fiber cable. The contractor will start doing the directional bores along the underground portions of the project route. The directional bore crews are scheduled to begin the 2nd week of November, 2011. The fiber optic cable for Contract I is scheduled to be shipped on November 30, 2011. The contractor will start fiber construction by the | Citizens' Telephone Co-operative | Obtaining the various permits and agreements with the cities, towns, and counties that the proposed project spans through has been difficult and time consuming due to the unique procedures and process that each locality has. Some documents and agreements seem to get bogged down in the different stages of the process even though the request has been approved by the required boards, councils, committees, and government officials. The permit process that the Town of Blacksburg requires has made scheduling and keeping the work crews organized and moving ahead very difficult. The Blacksburg permit process often causes the crew to wait before they can proceed to the next work location because the next permit has not been approved yet. The long lead time for obtaining the fiber optic cable needed for the project has caused a 15 week delay in starting construction on Contract I and Contract II. The first shipment of fiber is not due to be delivered until November 10, 2011 which will add several weeks more to the delay. This is also causing the contractors to have to reschedule their crews and find fill in work for the crews until the contract work can start. | Construction start dates will continue to be impacted by the long lead time in getting the fiber optic cable and other materials for the project. The fiber optic cable is scheduled to start shipping near the end of quarter 6 which will push the construction process into the winter season. Aerial construction usually experiences a slow down in the winter months but can continue if the weather conditions are not too bad. Winter weather has a greater impact on the underground construction process. Snow, ice, and frozen ground can stop underground construction in the southwest area of Virginia for 4 to 10 weeks. The delay in obtaining fiber cable continues to put Citizens, Thompson & Litton, Inc., and the Contractors in a difficult position because all these firms have organized and arranged their schedules and personnel to meet the previously anticipated milestone timelines. Citizens and Thompson & Litton will continue to review all options to try to stay as close as possible to the original milestone timelines. | TRUE
NT10BIX5570093 | 2011 | Q4 | Q4 - 2011 | The proposed 186 mile fiber project was divided into 4 separate construction contracts. Three of the construction contracts have been awarded as follows: Contract I Nichols Construction, LLC 102 miles 180 days Contract II Lambertâ€™s Cable Splicing Co, LLC 70 miles 130 days Contract III Lambertâ€™s Cable Splicing Co, LLC 11 miles 90 days Due to the difficulty of obtaining the fiber optic cable needed to start construction on the overall project. Contract I and II saw limited activity during the 6th quarter. As reported in the previous PPR, Citizens was successful in obtaining enough fiber cable to proceed with construction on Contract III. Construction work on Contract III started in mid 5th quarter and continued through the 6th quarter. Fiber Construction Progress: Contract I: Preliminary construction activities began on October 12, 2011 with placement of aerial make ready and strand placement. 7 miles of strand had been placed be the end of the quarter. The contractor started a directional bore crew on November 28, 2011 and has completed 18 bores by the end of the quarter. The contractor received shipments of the fiber cable on December 1st and 2nd. The contractor plans to start construction on January 9, 2012 with two buried placement crews, one aerial crew, and two bore crews. Contract II: Preliminary construction activities began on December 14, 2011 with two directional bore crews. 7 bores had been completed by the end of the quarter. The contractor received fiber cable on December 30, 2011. The contractor plans to start fiber construction on January 9, 2012 with one buried crew, one aerial crew, and two bore crews. Contract III: Fiber construction continued throughout the 6th quarter in the Town of Blacksburg. Approximately 1 mile of fiber construction was remaining to be completed at the end of the 5th quarter. The contractor completed site work for the telecommunication huts at Christiansburg and Pulaski. The Christiansburg hut was set in place and had power turned on by December 31, 2011. The Pulaski hut is scheduled to be set the 2nd week in January 2012. Construction and splicing on Contract III is scheduled to be complete by January 13, 2012 and testing, cleanup, and final inventory completed by the end of January. Service drops had been installed to 7 CAIâ€™s by the end of the 6th quarter and 1 service had been turned on. Citizens completed negotiations for the Pulaski hut site with the County of Pulaski and the agreement was signed at the end of December 2011. | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | Citizens had anticipated approximately 71 miles complete by the end of quarter 6. Due to the unavailable fiber cable, construction on Contract I and Contract II will not start until January 9, 2012. Construction work on Contract III was near complete by the end of the quarter. | No Variance | No Variance | No Variance | Citizens had anticipated approximately 71 miles complete by the end of quarter 6. Due to the unavailable fiber cable, construction on Contract I and Contract II will not start until January 9, 2012. Construction work on Contract III was near complete by the end of the quarter. | No Variance | No Variance | No Variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | 1 | 0 | 1 | 1 | Subscriber was turned up ahead of schedule due to customer contract obligation which was not part of the original project plan. | No Variance | Subscriber was turned up ahead of schedule due to customer contract obligation which was not part of the original project plan. | 1 Gb - 1 Subscriber | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | FALSE | N/A | Citizens will have all right of way agreements in place by mid-February, 2012. Joint use make ready will be complete in Roanoke county by American Electric Power and Verizon by the end of February, 2012. Contract I Nichols Construction, LLC will officially start contract work on January 9, 2012. The contractor will start with two buried crews, one aerial crew, and two bore crews. The crews will start in the Town of Wytheville and Wythe County with the underground construction. The contractor plans on starting a third and fourth buried crew by February and anticipates having approximately 16 miles of fiber installed by the end of the 7th quarter. Contract II Lambert’s Cable Splicing Co., LLC will officially start contract work on January 9, 2012. The contactor plans to start with two bore crews and one aerial crew and start two buried crews by the third week of January. One buried crew, aerial crew, and one bore crew will begin working and installing fiber in the Town of Christiansburg and Montgomery County. The second buried crew and bore crew will begin work in Botetourt County. The contract plans to start a third buried crew around the first of March, 2012 and anticipates having approximately 15 miles of fiber installed by the end of the 7th quarter. Contract III Lambert’s Cable Splicing Co. LLC will complete fiber installation by January 13, 2012. Splicing, testing, and cleanup will be completed on Contract III by January 31, 2012. The Pulaski telecommunication hut will be installed by mid-January and site work complete by the end of January. | Citizens' Telephone Co-operative | Obtaining the various permits and agreements with the cities, towns, and counties that the proposed project spans through has been difficult and time consuming due to the unique procedures and process that each locality has. The permit process that the Town of Blacksburg requires made scheduling and keeping the work crews organized and moving ahead very difficult. The Blacksburg permit process often causes the crew to wait before they can proceed to the next work location because the next permit has not been approved yet. Joint use proposals and make ready work continues to be slow and difficult to get the pole owner and other utility attachments to complete their make ready work. The long lead time for obtaining the fiber optic cable needed for the project has caused Contract I and Contract II to be delayed until the first or second week in January 2012. The delay caused the contractors to have to reschedule their crews to other projects or find fill in work until the contract work could start. | Due to the delays in getting the fiber optic cable required to construct the fiber network project, Citizens, Thompson&Litton, and the contractors are exploring options on how to increase production and get the milestones in line with those projected in the original projections. Another factor that may impact the construction process in the 7th quarter is the winter season. Having to start construction in winter can slow progress. Normally underground construction is difficult due to wet, frozen, snow, and cold conditions. The original milestones had reflected and accounted for less construction progress for the winter months compared with much more progress being accounted for in the summer months which also have longer daylight working hours. The contractors are prepared to bring in additional crews if the winter weather conditions allow construction to continue which will help bring the milestones closer to the original projections. | TRUE
NT10BIX5570093 | 2012 | Q1 | Q1 - 2012 | The proposed 186 mile fiber project was divided into 4 separate construction contracts. Three of the construction contracts have been awarded as follows: Contract I Nichols Construction, LLC 102 miles 180 days Contract II Lambertâ€™s Cable Splicing Co, LLC 70 miles 130 days Contract III Lambertâ€™s Cable Splicing Co, LLC 11 miles 90 days Contract IV is scheduled to be released and bid by the end of May, 2012. Fiber Construction Progress: Contract I: Installation of the fiber optic cable started on January 10, 2012 in the Town of Wytheville and in Wythe County, VA. The contractor began with one aerial crew, one buried placement crew, and two directional bore crews. By mid February and as weather conditions improved the contractor started moving in additional crews to the project. By March there were one aerial crew, three buried placement crews, and three directional bore crews working in several areas of the project including Wythe and Pulaski Counties and in the Town of Wytheville, Town of Pulaski, Town of Dublin, and the City of Radford. By the end of the quarter the contractor had installed 4.6 miles of aerial and 13.9 miles of buried fiber optic cable. Contract II: Construction activities began on January 16, 2012 with two bore crews working in the Town of Christiansburg. On January 18, 2012 aerial construction began in the Town of Christiansburg, VA. By the first of February the contractor had one aerial crew, three buried placement crews, and three directional bore crews working on several areas of the project including Montgomery, Roanoke, and Botetourt Counties and the Town of Christiansburg. By the end of the quarter the contractor had installed 4.3 miles of aerial and 13.2 miles buried fiber optic cable. Contract III: Construction was completed by January 20, 2012. Splicing, testing, inventory, and final clean up were completed by the end of February 2012. Final inventory tabulation should be complete by mid April, 2012. The project consisted of installing 0.8 miles of aerial fiber and 8.1 miles of buried fiber cable. 1.4 miles of service drop had been installed to 11 CAI locations. Service had been activated at 1 of those locations. Site work and installation of the telecommunication hut at Christiansburg and the telecommunication hut at Pulaski has been completed including power and back up generators. The total project miles of fiber installed by the end of quarter 7 equals 46.3. | 46 | 0 | 0 | 0 | 46 | 0 | 0 | 1 | Citizens had anticipated approximately 89 miles complete by the end of quarter 7. Due to the unavailable fiber cable, construction on Contract I and Contract II did not start until January 9, 2012. Starting construction in the winter months and having to adjust construction schedules to meet requirements of the Virginia Department of Transportation due to VDOT road improvement projects and traffic situations have caused delays. | No Variance | No Variance | No Variance | Citizens had anticipated approximately 89 miles complete by the end of quarter 7. Due to the unavailable fiber cable, construction on Contract I and Contract II did not start until January 9, 2012. Starting construction in the winter months and having to adjust construction schedules to meet requirements of the Virginia Department of Transportation due to VDOT road improvement projects and traffic situations have caused delays. | No Variance | No Variance | Citizens had anticipated having 3 interconection points in place by the end of quarter 7. Due to construction delays caused by unavailable fiber cable, construction on Contract I and Contract II did not start until January 9, 2012. Starting construction in the winter months and having to adjust construction schedules to meet requirements of the Virginia Department of Transportation due to VDOT road improvement projects and traffic situations have caused delays. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | 1 | 0 | 1 | 1 | Citizens had anticipated 8 subs by the end of the quarter. Delays were due to existing school contracts and school schedule. | Citizens had anticipated 2 subs receiving new access by the end of the quarter. Delays were due to existing school contracts and school schedule. | Citizens had anticipated 6 subs receiving improved access by the end of the quarter. Delays were due to existing school contracts and school schedule. | 1 Gb - 1 Subscriber | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | N/A | FALSE | N/A | Citizens and Thompson & Litton will finalize the construction plan sheets and prepare bid documents for the fourth contract of the 186 mile project. The bid documents are scheduled to be sent out by the third week of May, 2012. Bids will be due and the contractor will be announced by the third week of June. Citizens will set a start date once the delivery date of the fiber cable for contract IV is identified. Contract I Nichols Construction LLC plans to continue with 4 â€“ 5 plow crews, 2 â€“ 3 bore crews and one aerial crew during the 8th quarter. With improving weather conditions and longer daylight hours, the contractor anticipates placing 30 â€“ 35 miles of fiber this quarter. By the end of the 8th quarter the contractor plans to have 53 total miles (51%) complete on the contract. Contact II Lambertâ€™s Cable Splicing Co., LLC will continue the construction process with 3 â€“ 4 plow crews, 2 -3 bore crews, and one aerial crew during the 8th quarter. With improving weather conditions and longer daylight hours the contractor anticipates placing 25 miles of fiber this quarter. By the end of the 8th quarter the contractor plans to have 42.5 total miles (60%) complete on the contract. This contract has two routes that require limited work hours and weekend work schedule due to Virginia Department of Transportation requirements. Community Anchor Institutions Service will be activated at 2 -3 additional CAI locations in the 8th quarter. These schedules are being coordinated with the Montgomery County School system so work can be done after the current school session ends. | Citizens' Telephone Co-operative | Starting the construction process in the winter months has impacted the amount of progress due to the weather conditions and the shorter working hours during this time of the year. The Virginia Department of Transportation has an ongoing construction project on Interstate 81 in Montgomery and Roanoke counties that is impacting Citizens construction along Route 11 in Montgomery. The Citizens contactor is not allowed to work in the right of way of Route 11 during times that the VDOT project is rerouting interstate traffic onto Route 11. This is forcing the contractor to adjust the schedule to work on this portion of the route on weekends only. The Virginia Department of Transportation is also enforcing strict working hours along route 8 in Montgomery County due to the traffic volume along that route. Aerial fiber installation has been impacted in several areas due the Joint Use Process and make ready issues with the other utility owners in the area. Lack of communication between the pole owners and existing attaching service providers is the main problem. There is also a lack of effort following the guidelines and procedures that are set forth in the Joint Use Agreements and standard industry practices. | Citizens, Thompson & Litton, and the contractors are continuing to explore options on how to increase production and bring the original projected milestones more in line. Having to adjust work schedules because of Virginia Department of Transportation construction on I-81 and because of the congested traffic on route 8 could impact overall production accomplishment for the quarter. There is also an environmental issue that has been identified in the New River Valley Commerce Park in Pulaski County that could delay construction in the park until September 1, 2012. Citizens and the NRVPDC has contacted FWIS and VDGIF to work through the issue. Citizens does not anticipate that this issue will have a significant impact on the project completion date. The construction process on Contract IV could be delayed by the lead times on obtaining fiber cable. Although lead times have improved from what they were a year ago, they are still running 20 â€“ 30 weeks out. | TRUE
NT10BIX5570093 | 2012 | Q2 | Q2 - 2012 | The proposed 186 mile fiber project was divided into 4 separate construction contracts. Three of the construction contracts have been awarded as follows: Contract I Nichols Construction, LLC 102 miles 180 days Contract II Lambertâ€™s Cable Splicing Co, LLC 70 miles 130 days Contract III Lambertâ€™s Cable Splicing Co, LLC 11 miles 90 days Contract IV is scheduled to be released and bid by the end of August, 2012. Fiber Construction Progress: Contract I: Installation of the aerial and buried fiber optic cable continued in Wythe, Pulaski, and Montgomery counties through the 8th quarter. Approximately 90% of the 32 miles of fiber planned to be installed in the Town of Wytheville and Wythe County has been completed. 35% of the 51 miles of fiber planned to be installed in the Town of Pulaski, the Town of Dublin, and Pulaski County has been completed. Preliminary aerial construction and directional bores are near complete in Montgomery County and the City of Radford. The contractor has had 3 â€“ 5 buried crews, 3 â€“ 4 bore crews and 1 â€“ 2 aerial crews working along the various routes during the quarter. Fiber splicing and testing began in Wythe County and the Town of Wytheville in early June and will begin in Pulaski County in early August. The contractor had installed 45 miles of aerial and buried fiber by the end of the quarter and had worked 107 days of the 180 day contract. Contract II: Installation of the aerial and buried fiber optic cable continued in Montgomery, Floyd, Roanoke, and Botetourt counties through the 8th quarter. 65% of the 32 miles of fiber planned for Montgomery County and the Town of Christiansburg has been completed. 13% of the planned 11.5 miles of fiber planned for Floyd County has been completed. 77% of the planned 22 miles of fiber has been completed in the City of Salem and Roanoke County. 100% of the 4.5 miles in Botetourt County was completed. The contractor has had 3 â€“ 5 buried crews, 4 â€“ 5 bore crews, and 1 â€“ 2 aerial crews working on the various routes during the quarter. Fiber splicing and testing began in mid May in Botetourt County and Roanoke County and will continue into Christiansburg by the middle of July. The Contractor had installed 43.7 miles of aerial and buried fiber by the end of the quarter and had completed 106 days of the 130 day contract. Contract III: Final inventory and inspection was completed in mid April, 2012. Final invoice was approved on June 4, 2012. Contract III consisted of a total of 8.5 miles of middle mile fiber installed. There were also 2.5 drop miles of fiber installed in Contract III. Total project miles completed by the end of quarter 8 equals 97.2 miles or 52% of the 186 miles proposed. The Land, Structures, and Right of Way budget line item is currently over budget. A 424 will be submitted before the next reporting period to adjust our budget, as we have another line item which will be coming in under budget. | 97 | 0 | 0 | 0 | 97 | 0 | 0 | 2 | Citizens had anticipated approximately 128 miles complete by the end of quarter 8. Due to the unavailable fiber cable, construction on Contract I and Contract II did not start until January 9, 2012. Having to adjust construction schedules to meet requirements of the Virginia Department of Transportation due to VDOT road improvement projects and traffic situations continues to slow construction progress on several routes. Delays in getting make ready completed are impacting completion of aerial construction in three locations. | No Variance | No Variance | No Variance | Citizens had anticipated approximately 128 miles complete by the end of quarter 8. Due to the unavailable fiber cable, construction on Contract I and Contract II did not start until January 9, 2012. Having to adjust construction schedules to meet requirements of the Virginia Department of Transportation due to VDOT road improvement projects and traffic situations continues to slow construction progress on several routes. Delays in getting make ready completed are impacting completion of aerial construction in three locations. | No Variance | No Variance | Citizens had anticipated having 4 interconnection points in place by the end of the 8th quarter. Delays in start of construction have resulted in portions of the fiber route needing to be built in order to establish the 2 remaining interconnect points. | 0 | 0 | 0 | None | N/A | N/A | 0 | 0 | 0 | 0 | Citizens had anticipated having 1 signed agreement with a wholesale provider. Delay in the final approval of the Environmental Assessment and the long lead time in obtaining fiber cable and other materials have impacted the timing of construction, thus impacting the ability to provide new access to wholesalers. | No Variance | No Variance | N/A | 7 | 0 | 7 | 1 | Citizens had anticipated 18 CAIâ€™s by the end of the 8th Qtr. Delays were due to existing school contracts and school schedule. | Citizens anticipated having 12 new subs by the end of the quarter. Delays were due to existing school contracts and incomplete construction in some locations | Citizens anticipated having 6 subs by the end of the quarter. | 1 Gb - 1 Subscriber | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | N/A | FALSE | N/A | Citizens and Thompson & Litton will finalize the construction plan sheets and prepare bid documents for the fourth contract of the 186 mile project. The bid documents are scheduled to be sent out by the middle of August, 2012. Bids will be due and the contractor will be announced by the end of August. Citizens ordered fiber at the end of July in order to avoid delaying construction start. Contract I Nichols Construction LLC plans to continue with 4 â€“ 5 plow crews, 2 â€“ 3 bore crews and one aerial crew during the 9th quarter. At the current pace and schedule the contractor should have a total of 87 miles of fiber installed by the end of quarter 9 which is 85% of the contract amount. The anticipated completion date for contract I is October 18, 2012. Contact II Lambertâ€™s Cable Splicing Co., LLC will continue the construction process with 3 â€“ 4 plow crews, 2 -3 bore crews, and one aerial crew during the 9th quarter. At the current pace and schedule the contractor should have 100% of the 71 miles complete on contract II by mid- September. Community Anchor Institutions Actual service activation at most of the proposed CAIâ€™s is still pending Montgomery County and Pulaski County school schedules. The School systems are currently in contract arrangements with other providers that will be phasing out during the remainder of the year. The service at each location will be activated as soon as these contract agreements end. The service drops are being installed as construction progresses past each location. Contract IV The final contract for the 186 mile NTIA/BTOP project is schedule to be bid and awarded by the first week of September, 2012. The scheduled start date of construction will be the second week of October, 2012 with a completion date of 45 days. Citizens has ordered the fiber for this contract in advance in order to avoid delays in beginning the construction. | Citizens' Telephone Co-operative | The Virginia Department of Transportation has an ongoing construction project on Interstate 81 in Montgomery and Roanoke counties that is impacting Citizens construction along Route 11 in Montgomery. The Citizens contactor is not allowed to work in the right of way of Route 11 during times that the VDOT project is rerouting interstate traffic onto Route 11. This is forcing the contractor to adjust the schedule to work on this portion of the route on weekends only. The Virginia Department of Transportation is also enforcing strict working hours along route 8 in Montgomery County due to the traffic volume along that route. Aerial fiber construction continues to be impacted by delays in getting the make ready completed by other utility owners in three areas of the project. The weather event that occurred on June 29, 2012 has affected both contractors. The Citizens contractors were obligated to provide storm restoration crews to different areas in the north eastern United States, leaving both contractors short of crews on the project. The storm also has affected the other utilities in the area which will further delay aerial make ready. | Adjusting work schedules and moving crews to accommodate the Virginia Department of Transportation (VDOT) construction project on I-81 could affect completion of the fiber installation along portions of route 11 in Montgomery County and Roanoke County. The VDOT working hours restriction on Route 8 in Montgomery County and Floyd County could also slow the process along that route. Delays in getting make ready completed on three aerial routes (one in the Town of Christiansburg and two in Roanoke County) could affect those sections from being completed in the next quarter. Citizens and Thompson & Litton will continue to monitor this situation closely and look for alternatives options if the delays continue. | TRUE
NT10BIX5570093 | 2012 | Q3 | Q3 - 2012 | The proposed 186 mile fiber project was divided into 4 separate construction contracts as follows: Contract I Nichols Construction, LLC 103 miles 180 days Contract II Lambertâ€™s Cable Splicing Co, LLC 71 miles 130 days Contract III Lambertâ€™s Cable Splicing Co, LLC 9 miles 90 days Contract IV Edwards Telecommunication, Inc. 24 miles 45 days Fiber Construction Progress: Contract I: Nichols Construction, LLC completed fiber construction in the Town of Wytheville and Wythe county early in the 9th quarter. The 144 strand fiber facility from the Wytheville Hut to the Town of Wytheville and the western beginning point of the project has been spliced and tested and is ready for service activation. The 240 strand fiber from the Wytheville Hut to Pulaski County has been spliced and is being tested. Construction and splicing was completed from the Wythe County line to the Pulaski Hut and the testing process was started in September on the section. Three construction crews were working in the Dublin and Fairlawn areas of Pulaski County and one crew was working in the City of Radford and Montgomery County at the end of the quarter. Service drops have been completed to 9 CAIâ€™s in Pulaski County and will be ready for service as soon as the connector routes are complete. The contractor plans to add another buried placement crew at the beginning of the 10th quarter working in Montgomery County. By the end of the quarter the contractor had installed a total of 68.5 miles (67%) of the proposed 103 miles and 162 days. Contract II: Lambertâ€™s Cable Splicing, LLC completed construction along route 11 from the Town of Christiansburg to the Roanoke County line by mid August. The contractor has completed the splicing along the segment and is currently testing the fiber and completing the clean up and inventory process. Fiber construction on route 11 from the Montgomery County line to the City of Salem and along I-81 to exit 150 in Botetourt County has been completed. Splicing has been completed along this segment and the fiber was being tested. Final clean up and inventory was started by mid-September and should be complete by mid-October. Fiber construction along route 8 in Montgomery County to Floyd County is complete except for a 1 mile section that is being held up by make ready due to road construction and a new high school being built. Fiber construction was stopped by mid September due the holdup. Splicing, testing, and cleanup began in early September and will proceed up to the incomplete section. Another .5 miles of aerial is held up was in the Falling Branch Industrial Park in Christiansburg because of make ready. By the end of the 9th quarter the contractor had placed 66.5 miles of fiber of the proposed 71 miles for the contract. Citizens granted Lambertâ€™s a 30 day extension of the contract days due to unexpected delays from the DOT and aerial make ready issues. Contract III: 8.9 miles installed. (complete) Contract IV: On August 21, 2012 a pre bid meeting was held at the Citizens Office to discuss detail of the final portion of the NTIA/BTOP project. Bids were received on September 11, 2012 and Notice of Award was issued on September 21, 2012. The contract is scheduled to be finalized in early October with a tentative construction start date of October 22, 2012. Total project miles completed by the end of quarter 9 equals 143.9 of the 186 miles proposed. The project is 77% complete at the end of the 9th quarter. | 144 | 0 | 0 | 0 | 144 | 0 | 0 | 3 | Citizens had anticipated approximately 166 miles complete by the end of quarter 9. Due to the unavailable fiber cable, construction on Contract I and Contract II did not start until January 9, 2012. Having to adjust construction schedules to meet requirements of the Virginia Department of Transportation due to VDOT road improvement projects and traffic situations continues to slow construction progress on several routes. Delays in getting make ready completed is impacting completion of aerial construction in two locations. | No Variance | No Variance | No Variance | Citizens had anticipated approximately 166 miles complete by the end of quarter 9. Due to the unavailable fiber cable, construction on Contract I and Contract II did not start until January 9, 2012. Having to adjust construction schedules to meet requirements of the Virginia Department of Transportation due to VDOT road improvement projects and traffic situations continues to slow construction progress on several routes. Delays in getting make ready completed is impacting completion of aerial construction in two locations. | No Variance | No Variance | Citizens had anticipated having 5 interconnection points in place by the end of the 9th Quarter. Delays in the start of construction have resulted in portions of the fiber route needing to be built in order to establish the 2 remaining interconnect points. | 0 | 0 | 0 | None | N/A | N/A | 0 | 0 | 0 | 0 | Citizens had anticipated having 1 signed agreement with a wholesale provider. Delay in the final approval of the Environmental Assessment and the long lead time in obtaining fiber cable and other materials have impacted the timing of construction, thus impacting the ability to provide new access to wholesalers. | No Variance | No Variance | N/A | 30 | 18 | 12 | 1 | Citizens had anticipated 38 CAI's by the end of the 9th Quarter. Delays were due to existing school contracts and incomplete construction in some locations. | Citizens anticipated having 32 new subs by the end of the quarter. Delays were due to existing school contracts and incomplete construction in some locations. | Citizens anticipated having 6 subs by the end of the quarter. | 1 Gb - 3 Subscribers | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | N/A | FALSE | N/A | Citizens and Thompson & Litton will finalize the administration of Contract IV by mid-October, 2012. Citizens will issue the Notice to Proceed shortly after or when the contract documents have been signed. The tentative construction start date is October 22, 2012. Contract I Nichols Construction LLC plans to continue with 4 â€“ 5 plow crews, 1 - 2 bore crews and one aerial crew during the 10th quarter. The previous anticipated completion date was October 18, 2012. Construction has recently been slowed because of large areas of rock that two crews have encountered in Pulaski County. The contractor is anticipating having to request an extension of time which will push the completion date out to approximately December 12, 2012. The contractor also plans to add 1 â€“ 2 crews if necessary to help stay course with the completion date. Contact II Lambertâ€™s Cable Splicing Co., LLC completed all the construction that can be completed before the end of the 9th quarter. There are two sections of aerial that are being held up due to make ready not being complete by two utility companies. The contractor will work on completing the splicing and testing of all the fiber that is in place by mid-October. Final clean up and inventory will be completed on all the work that has been done on the contract. Citizens will continue to try to get the make ready completed as soon as possible. The actual completion date will be pending the completion of the make ready. Contract IV The final contract for the 186 mile NTIA/BTOP project is schedule to start construction by October 22, 2012 with a 45 day completion time limit. Edwards Telecommunications, Inc. was awarded the contract. The contractor plans to start with one directional bore crew and one aerial crew the first week. Two underground placement crews will start approximately 2 weeks after or as soon as the bore crew is far enough ahead to not hold up the underground crew. Citizens ordered the fiber for contract IV. The fiber is now on site. Community Anchor Institutions Actual service activation at most of the proposed CAIâ€™s is still pending Montgomery County and Pulaski County school schedules. The School systems are currently in contract arrangements with other providers that will be phasing out during the remainder of the year. The service at each location will be activated as soon as these contract agreements end. The service drops had been installed at 30 CAI locations and the remaining will be completed in the 10th quarter. | Citizens' Telephone Co-operative | Throughout the 9th quarter The Virginia Department of Transportation had the ongoing construction project on Interstate 81 in Montgomery and Roanoke counties that is impacting Citizens construction along Route 11 in Montgomery. The Citizens contactor was not allowed to work in the right of way of Route 11 during times that the VDOT project is rerouting interstate traffic onto Route 11. This forced the contractor to adjust the schedule to work on this portion of the route on weekends only. The Virginia Department of Transportation also had strict working hours along route 8 in Montgomery County due to the traffic volume along that route. Contract II has two aerial sections that cannot be completed due to make ready not being complete. American Electric Power and Verizon are both running several months behind on these sections. The weather event that occurred on June 29, 2012 affected both contractors. The Citizens contractors were obligated to provide storm restoration crews to different areas in the north eastern USA, leaving both contractors short of crews on the project. The storm also has affected the other utilities in the area which has added further delay to aerial make ready. | Contract II may continue to be delayed because of aerial make ready that has not been completed. This will delay final testing and closeout of the contract until the two sections can be completed. Contract IV has one section of aerial make ready pending in the Town of Pearisburg. This make ready is being done by the same two utility companies that are holding up the process in Contract II. Citizens will continue to monitor this situation and try to push for this work to be completed. Construction on contract I and contract IV will run into mid to late fall which may result in some delay due to shorter day light hours to work in and more potential for winter weather. | TRUE
NT10BIX5570093 | 2012 | Q4 | Q4 - 2012 | Contract I: Nichols Construction, LLC completed fiber construction in the City of Radford and the county of Montgomery on December 21,2012. All fiber construction is complete in Pulaski Co. except for a 1-mile aerial section that has been delayed by difficulty in easement obtainment and aerial make ready that is required from Verizon. Splicing of fiber in these areas is in process and is complete except for one splice in Pulaski Co. and one location in Montgomery Co. These 2 splice locations are to be completed by January 11, 2013. Testing of the fiber for this contract is ongoing and is projected to be completed by January 15, 2013. Currently Nichols Construction has a crew performing final clean-up on all routes included in the contract. By the end of the quarter, Nichols had installed a total of 102 miles (99%) of the proposed 103 mile contract. Contract II: Lambertâ€™s Cable Splicing, LLC has completed construction of the 0.5 mile aerial fiber along the Falling Branch Industrial Park which had previously been held up by make ready work needed by Verizon. Construction along Route 8 in Montgomery Co. near the site of road construction and new high school is still being delayed by aerial make ready work needed by AEP and Verizon. No schedule has been established by these companies for completion of this work. Splicing of all fiber except for the incomplete section along Route 8 is complete. Testing of fiber to resolve attenuation issues along completed fiber routes and up to the incomplete section is in process and scheduled to be completed by January 15, 2013. By the end of the 10th quarter, Lambertâ€™s had placed 67 miles of the proposed 71 miles of fiber on this contract. Contract IV: Edwards Telecommunications, Inc. completed construction on the underground section of fiber along Route 100 from Dublin (Pulaski Co.) to Pearisburg (Giles Co.) on December 20, 2012. Splicing and testing of this section of fiber was completed on December 28,2012. Edwards will complete any final clean up on this section by January 15, 2013. The remaining section (5.2 miles) of construction is aerial cable located in the Town of Pearisburg that is being held up by make ready work that is needed by AEP and Verizon. No time schedule for completion of this work has been announced by these companies. By the end of the quarter, Edwards had completed construction on 18.8 miles (78%) of the proposed 24 miles of fiber for this contract. By the end of the 10th quarter, a total of 179.2 linear miles (96%) of the proposed 186 linear miles of NTIA/BTOP project had been completed. | 180 | 0 | 0 | 0 | 180 | 0 | 0 | 4 | Citizens had anticipated approximately 186 miles being complete by the end of quarter 10. Delays in getting make ready completed is impacting completion of the remaining aerial construction in three locations. | No Variance | No Variance | No Variance | Citizens had anticipated approximately 186 miles being complete by the end of quarter 10. Delays in getting make ready completed is impacting completion of the remaining aerial construction in three locations. | No Variance | No Variance | Citizens had anticipated having 8 interconnection points in place by the end of the 10th quarter. Delays in construction because incomplete aerial make ready work has resulted in portions of the fiber route needing to be built in order to establish the remaining interconnection points. | 0 | 0 | 0 | None | N/A | N/A | 0 | 0 | 0 | 0 | Citizens had anticipated having 1 signed agreement with a wholesale provider. Delay in the final approval of the Environmental Assessment and the long lead time in obtaining fiber cable and other materials have impacted the timing of construction, thus impacting the ability to provide new access to wholesalers. | No Variance | No Variance | No Variance | 36 | 24 | 12 | 1 | Citizens had anticipated 52 CAI's by the end of the 10th Quarter. Delays were due to existing school contracts and incomplete construction in some locations. Also, total number of CAI's being built to is now at 50. | Citizens anticipated having 46 new subs by the end of the quarter. Delays were due to existing school contracts and incomplete construction in some locations. | Citizens anticipated having 6 subs by the end of the quarter. | 1 Gb - 5 Subscribers | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | N/A | FALSE | N/A | Contract I Nichols Construction LLC will continue with the testing of fiber optic cable in all areas to resolve attenuation issues. This work will consist of the digging up of cable in problem areas to relieve tight radius bends in cable. Plans are to complete this testing by February 15, 2013. Construction of service drop to Radford University will be completed by February 15 as well. If make ready work on the 1-mile aerial section in Pulaski Co. is completed in February, it is anticipated that the remaining construction and all testing could be completed by the end of the 11th quarter. Contract II Lamberts Cable Splicing will continue with testing of fiber optic cable in problem areas to resolve attenuation issues as well. It is anticipated that all testing will be finished on all fiber optic cable where construction is complete by February 15, 2013. Construction on the aerial section along Route 8 in Montgomery Co. will be completed soon after make ready work is completed by AEP. Plans are to have all construction and testing completed on this contract by the end of the 11th quarter if make ready issues are resolved by mid-February. Contract IV At this time, Edwards Telecommunications is finished with all construction and testing of the 18.8 mile buried portion of the fiber optic cable on itâ€™s contract. They will complete all clean-up work in February, weather permitting. They will construct the 5.2 mile aerial section in the town of Pearisburg soon after make ready is completed by AEP and Verizon. Estimated time for completion of this contruction cannot be established since no completion dates have been announced by either company for the make ready work. Community Anchor Institutions Service activation at most of the CAIâ€™s in Montgomery and Pulaski County are still pending the completion of testing of the fiber optic cable in these areas. Activation of service at these locations should be ready by the 12th quarter. Service drops have been installed at 35 CAI locations and the remaining will be completed in the 11th quarter. | Citizens' Telephone Co-operative | During the 10th quarter, make ready issues in 3 areas have delayed the completion of construction for this project. On Contract I, there is approximately 1 mile of aerial in Pulaski Co. that cannot be built because of pending make ready work by Verizon. On Contract II, a .75 mile aerial section of construction is being delayed by needed make ready work by AEP. On Contract IV, a 5.2 mile portion of aerial construction in the town of Pearisburg in Giles Co. is being held up by pending make ready work needed by Verizon and AEP. This make ready work is currently being engineered by these companies and some have already been invoiced. However, no schedule has been announced by these companies as to when this work will be completed. Currently 2 winter storms have hit these areas and recovery work has taken precedence over this project. These areas make up all of the construction that is left on this project. | Contracts I,II, and IV have varying amounts of make ready issues that continue to delay construction and completion of those contracts. Contract I - 1 mile section in Pulaski County Contract II â€“ 0.5 mile section in Montgomery Co. Contract IV â€“ 5.2 mile section in Pearisburg (Giles Co.) All contractors are committed to finish this construction as soon as this make ready work is completed by Verizon and AEP. Unfortunately with no schedules having been set by these companies for this work and with storm recovery work increasing during the winter, projecting completion dates is difficult. | TRUE
NT10BIX5570093 | 2013 | Q1 | Q1 - 2013 | Contract I: Nichols Construction, LLC has completed all fiber construction on the contract except for a 1-mile aerial section in Pulaski County that has been delayed by difficulty in easement obtainment and aerial make ready that is required from Verizon. This make ready work is in progress and easements should be obtained by the end of the month. Splicing of fiber on all constructed areas is complete. Currently Nichols Construction has a crew performing testing on fiber and correcting attenuation issues in the fiber storage loops. This testing should be complete by April 30,2013. By the end of the quarter, Nichols had installed a total of 102 miles (99%) of the proposed 103 mile contract. Contract II: Lambertâ€™s Cable Splicing, LLC completed construction along Route 8 in Montgomery County in the Riner area, near the site of road construction and new high school that was delayed by aerial make ready work needed by AEP and Verizon. Splicing of the fiber along Route 8 was completed on April 9, 2013. Testing of fiber to resolve attenuation issues along the fiber routes has continued and should be completed by April 30,2013. By the end of the 11th quarter, Lambertâ€™s had placed 70.5 miles (99%) of the proposed 71 miles of fiber on this contract. Contract IV: Edwards Telecommunications, Inc. completed construction on the underground section of fiber along Route 100 from Dublin (Pulaski County) to Pearisburg (Giles County) on December 20, 2012. Splicing and testing of this section of fiber was completed on December 28,2012. Edwards has completed all final clean up on this section of the contract. The remaining section (5.2 miles) of construction is aerial cable located in the Town of Pearisburg that is being held up by make ready work that is needed by AEP and Verizon. No time schedule for completion of this work has been announced by these companies. By the end of the quarter, Edwards had completed construction on 18.8 miles (78%) of the proposed 24 miles of fiber for this contract. By the end of the 11th quarter, a total of 179.8 linear miles (97%) of the proposed 186 linear miles of NTIA/BTOP project had been completed. | 180 | 0 | 0 | 0 | 180 | 0 | 0 | 4 | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | Citizens had anticipated having 8 interconnection points in place by the end of the 11th quarter. Delays in construction because of incomplete aerial make ready work has resulted in portions of the fiber route needing to be built in order to establish the remaining interconnection points. Also, despite there only being 6.2 miles of construction left to complete, not all of the fiber has been tested and released to us, nor all of the equipment deployed thus making us unable to connect all 8 interconnection points as of March 31, 2013. | 0 | 2 | 0 | None | Pricing plan, along with wholesale services being provided, has been attached to PPR submission. | N/A | 0 | 0 | 0 | 0 | Citizens had anticipated having 1 signed agreement with a wholesale provider. Delay in the final approval of the Environmental Assessment and the long lead time in obtaining fiber cable and other materials have impacted the timing of construction, thus impacting the ability to provide new access to wholesalers. | No Variance | No Variance | No Variance | 47 | 28 | 19 | 1 | Citizens had anticipated 52 CAI's by the end of the 11th Quarter. Delays were due to existing school contracts and incomplete construction in some locations. Also, total number of CAI's being built to is now at 50. | Citizens anticipated having 46 new subs by the end of the quarter. Delays were due to existing school contracts and incomplete construction in some locations. | Citizens anticipated having 6 subs by the end of the quarter. | 1 GB - 5 Subscribers NOT YET ESTABLISHED - 42 CAI's | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | N/A | FALSE | N/A | Contract I Nichols Construction LLC will continue with the testing of fiber optic cable in all areas to resolve attenuation issues. This work will consist of digging up of cable in problem areas to relieve tight radius bends in cable and repair bad splices. Plans are to complete this testing by May 3, 2013. If make ready work on the 1-mile aerial section in Pulaski County is completed in early May, it is anticipated that this remaining construction and all testing associated with it could be completed by the end of May 2013. Contract II Lamberts Cable Splicing will continue with testing of fiber optic cable in problem areas to resolve attenuation issues as well. It is anticipated that all testing will be finished on all fiber optic cable by May 8th, 2013. Contract IV At this time, Edwards Telecommunications is finished with all construction and testing of the 18.8 mile buried portion of the fiber optic cable on itâ€™s contract. They will construct the 5.2 mile aerial section in the town of Pearisburg soon after make ready is completed by AEP and Verizon. Since some make ready has been done, it is anticipated that construction can be started by Edwards around the middle of May 2013 or shortly after with construction and testing complete by the middle of June 2013. Community Anchor Institutions Service activation at most of the CAIâ€™s in Montgomery and Pulaski County is still pending the completion of testing of the fiber optic cable in these areas. Activation of service at these locations should be ready by the 12th quarter. Service drops have been installed at 35 CAI locations. Only one location remains and it should be completed by mid-February. | Citizens' Telephone Co-operative | Contracts I and IV have varying amounts of make ready issues that continue to delay construction and completion of those contracts. * Contract I - 1 mile section in Pulaski County * Contract IV â€“ 5.2 mile section in Pearisburg (Giles County) Both contractors are committed to finish this construction as soon as this make ready work is completed by Verizon and AEP. At this time, the make ready work in these two locations is underway, but not complete. No definite schedule has been announced for the final completion of this work. The above mentioned areas make up all of the unfinished construction on this project. | N/A | TRUE
NT10BIX5570093 | 2013 | Q2 | Q2 - 2013 | Contract I: Nichols Construction, LLC has completed all fiber construction on the contract as of June 26, 2013. Splicing and testing of all fiber on this contract was completed on July 8, 2013 as well. By the end of the quarter, Nichols had installed a total of 103 miles (100%) of the proposed 103 mile contract. Contract II: Lambertâ€™s Cable Splicing, LLC has completed all construction on this project as of April 4th, 2013. All splicing and testing of the fiber on this contract was completed on May 15, 2013. By the end of the 12th quarter, Lambertâ€™s had placed 71 miles (100%) of the proposed 71 miles of fiber on this contract. Contract IV: Edwards Telecommunications, Inc. completed construction on the underground section of fiber along Route 100 from Dublin (Pulaski Co.) to Pearisburg (Giles Co.) on December 20, 2012. Splicing and testing of this section of fiber was completed on December 28,2012. Edwards has completed all final clean up on this section of the contract. The remaining section (5.2 miles) of construction is aerial cable located in the Town of Pearisburg and is currently under construction and is scheduled to be completed by July 15,2013. All splicing and testing of the fiber in this area will be completed by July 17,2013. By the end of the quarter, Edwards will have completed construction on 21.4 miles (89%) of the proposed 24 miles of fiber for this contract. By the end of the 12th quarter, a total of 183.4 linear miles (99%) of the proposed 186 linear miles of NTIA/BTOP project had been completed. | 183 | 0 | 0 | 0 | 183 | 0 | 0 | 7 | Citizens had anticipated approximately 186 miles complete by the end of quarter 12. Delays in getting make ready completed has impacted completion of the remaining aerial construction in one location (Pearisburg). | No Variance | No Variance | No Variance | Citizens had anticipated approximately 186 miles complete by the end of quarter 12. Delays in getting make ready completed has impacted completion of the remaining aerial construction in one location (Pearisburg). | No Variance | No Variance | Citizens had anticipated having 8 interconnection points in place by the end of the 12th quarter. Delays in construction due to incomplete aerial make ready work resulted in portions of the fiber route needing to be built in order to establish the remaining interconnect point. The construction to this remaining interconnect point was completed on July 15, 2013. | 0 | 2 | 0 | None | Pricing plan, along with wholesale services being provided, has been attached to PPR submission. | N/A | 0 | 0 | 0 | 0 | Citizens had anticipated having 1 signed agreement with a wholesale provider. Delay in the final approval of the Environmental Assessment and the long lead time in obtaining fiber cable and other materials have impacted the timing of construction, thus impacting the ability to provide new access to wholesalers | No Variance | No Variance | No Variance | 55 | 46 | 9 | 1 | No Variance | No Variance | No Variance | 1 GB - 5 Subscribers NOT YET ESTABLISHED - 50 | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | N/A | FALSE | N/A | Contract IV: As of June 30, 2013, Edwards Telecommunications Inc had 2.6 miles of construction remaining to complete. The remaining section (2.6 miles) of construction is aerial cable located in the Town of Pearisburg and is scheduled to be completed by July 15,2013. All splicing and testing of the fiber in this area was completed on July 17,2013. By the end of the quarter, Edwards will have completed construction on 24 miles (100%) of the proposed 24 miles of fiber for this contract. By July 31, 2013, a total of 186 linear miles (100%) of the proposed 186 linear miles of NTIA/BTOP project will have been completed, thus ending the project. As of July 31, 2013, Citizens will have two signed wholesale agreements. One with LIT Networks and one with Radford University. | Citizens' Telephone Co-operative | During the 12th quarter, make ready issues in 2 areas have delayed the completion of construction of this project. On Contract I, there was approximately 1 mile of aerial in Pulaski Co. that could not be built because of pending make ready work by Verizon. When that work was finally completed, Construction on this 1-mile section was completed on June 26, 2013. On Contract IV, a 5.2 mile portion of aerial construction in the town of Pearisburg in Giles Co. has been held up by pending make ready work needed by Verizon and AEP. This make-ready work was completed in mid-June. Construction began on the aerial section in Pearisburg on June 24, 2013 and was completed on July 15th, 2013. | None | TRUE
NT10BIX5570093 | 2013 | Q3 | Q3 - 2013 | Contract I: Nichols Construction, LLC completed all fiber construction on the contract on June 26, 2013. Splicing and testing of fiber on this contract was completed on July 8, 2013. By July 8th , Nichols had installed and tested a total of 103 miles (100%) of the proposed 103 mile contract. Contract IV: Edwards completed construction on the remaining 5.2 miles of aerial fiber in the Town of Pearisburg on July 15, 2013. Splicing and testing of the fiber in this area was completed on July 17,2013. By July 17, 2013, Edwards had completed construction on all 24 miles (100%) of the proposed 24 miles of fiber for this contract. By July 17, 2013, a total of 186 linear miles (100%) of the proposed 186 linear miles of the NTIA/BTOP project had been completed. Accomplishments: NRCC (New River Community College) With the completion of our BTOP project NRCC now has a 1Gbps (1,000Mbps) connection between its two campuses for less than what they were paying before for two T1s. The link between the two campuses has over 600 times the speed they had before. Pulaski County & Pulaski County Public Schools (PCPS) Pulaski County and PCPS both analyzed their telecommunication expenses and elected to put up $600,000 in matching funds for this project, knowing that the cost savings alone would result in an ROI (Return On Investment) of roughly 3 years. Even with this short ROI, they were able to dramatically increase their bandwidth. PCPS was able to upgrade connections between schools from 100Mbps to 1Gbps (1,000Mbps) and their centralized internet connection from 100Mbps to 200Mbps. The local government offices were able to upgrade their T1 (1.5Mbps) connections between offices to 1Gbps (1,000Mbps), while also increasing their centralized internet connection to 100Mbps. PCPS also gained low latency connectivity to school systems and higher education institutions (VT, RU, and NRCC) in the region that have connectivity and peering setup with Citizens. Montgomery County Public Schools (MCPS) MCPS saw a huge increase in bandwidth between schools by switching from MPLS. Over 50% of the schools in the county only had T1 service (1.5Mbps) and a few had 10Mbps service and one 100Mbps service (shared internet backbone for all schools). All the schools are now interconnected with 1Gbps circuits and are sharing a 200Mbps centralized internet connection. After the switch to the new fiber network the interconnections between schools on average have over 500 times the speed/bandwidth than they had previously. LTE service now available in region Lumos has purchased wholesale circuits to provide fiber connections to three LTE cell sites for large cellular companies in the New River Valley: Pearisburg, Newport, and Radford. NRV Airport The NRV Airport previously had DSL service of 768Kbps/256Kbps (upload/download) and they now have 3Mbps (3,000Kbps) symmetrical service with the option to purchase service up to 10Gbps (10,000Mbps). This upgrade to 3Mbps symmetrical internet service was a 206% increase in download speed and 1072% speed increase for upload. Citizens Cablevision, Inc. This project tied into another BTOP project that was built by the partnership of VTF (Virginia Tech Foundation) and MBC (Mid-Atlantic Broadband Corporation) whose project went through New Castle, VA. Cablevision has been looking for an economical way to get a fiber connection to the cable system in New Castle since acquiring the system in 2005/2006. Through our NRV-ROAN project interconnections with the VTF/MBC project in Blacksburg, Cablevision now has an economical way to get to New Castle. They are in the process of upgrading that system to improve the quality of its TV service and adding cable modem service in the near future. | 186 | 0 | 0 | 0 | 186 | 0 | 0 | 8 | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | No Variance | 1 | 2 | 40 | Lumos Networks | Pricing plan, along with wholesale services being provided, has been attached to PPR submission. | N/A | 1 | 0 | 0 | 1 | No Variance | No Variance | No Variance | 50M - 1 Subscriber | 57 | 48 | 9 | 2 | No Variance | No Variance | No Variance | 1GB - 28 Subscribers 3M - 1 Subscriber NOT YET ESTABLISHED - 28 | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 2 | 2 | 0 | 2 | No Variance | No Variance | No Variance | No Variance | 1GB - 1 Subscriber 3M - 1 Subscriber | N/A | FALSE | N/A | Project Complete. | Citizens' Telephone Co-operative | Up to June 15, 2013, make ready issues in 2 areas had delayed the completion of construction on this project. On Contract I, there was approximately 1 mile of aerial in Pulaski Co. that could not be built because of pending make ready work by Verizon. When that make-ready work was finally completed, construction on this 1-mile section was completed on June 26, 2013 and testing was completed on July 8th, 2013. On Contract IV, a 5.2 mile portion of aerial construction in the town of Pearisburg in Giles Co. was held up by pending make ready work needed by Verizon and AEP. This make-ready work was completed in mid-June. Construction was completed on the aerial section in Pearisburg on July 15, 2013 and testing of this section of fiber was completed on July 17th, 2013. | N/A | TRUE
NT10BIX5570094 | 2010 | Q4 | Q4 - 2010 | During Quarter 4 of 2010, the Mississippi Wireless Information Network (MSWIN) project staff has continued administrative preparations for the microwave upgrade expansion and the Long Term Evolution (LTE) addition. At the beginning of the quarter, the Broadband Technology Opportunities Program (BTOP) Request for Proposals (RFP) selection committee was announced. The committee is led by a member of the Wireless Communication Commission (WCC) and has public and private sector members. The RFP, which is for the implementation of the 700 MHz LTE Broadband core and radio access network equipment, was released December 16, 2010. A mandatory vendor proposal web conference took place January 11, 2011; and, final proposals are due March 3, 2011, at 3:00 p.m. The Executive Office of the State of Mississippi worked with the WCC, the University of Mississippi Medical Center (UMC), and the Mississippi Department of Information Technology Services (ITS) to complete the Baseline Report which projected and detailed MSWINâ€™s quarterly activities. Staff has continued to formulate plans to ensure financial sustainability for the MSWIN system. During Quarter 4, the WCC evaluated alternatives for upgrading the MSWIN microwave backhaul to accommodate broadband data traffic and presented these plans to our BTOP program officer. With the approval of the National Telecommunications and Information Administration (NTIA), the Commission, in its December 2010 meeting, approved a Change Order | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A3 | N/A | RFP 3639 for Broadband equipment and services has been issued. Network operation is an option in RFP 3639. | 0 | 0 | 0 | 0 | RFP 3639 for Broadband equipment and services has been issued. Proposals are due from Vendors on March 3, 2011. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | RFP 3639 for Broadband equipment and services has been issued. Proposals are due from Vendors on March 3, 2011. | N/A | N/A | 768 kbps downlink, 256 kbps uplink | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings are planned at this time. | FALSE | N/A | For the WCC, Microwave equipment has been ordered, and manufacturing should begin during next quarter. The State will commence microwave backhaul network detailed design activities with Motorola and Alcatel-Lucent during next quarter. Vendor Proposals to RFP 3639 for Broadband equipment and services are due March 3, 2011. For MED-COM, the following activities are planned for next quarter: 1. Purchase Microwave Link 2. Purchase PSAP integration system 3. Hire Personnel (non-grant funded positions) 4. Finalize purchase of communications equipment on existing state contract 5. Continue operational planning | Executive Office of the State of Mississippi | The uncertainty of the final technical and functional requirements for BTOP and FCC waiver recipients presented a challenge in the development of the State's RFP for Broadband implementation. Additionally, the BTOP build-out time line presents a challenge to the recipients' using 700 MHz LTE devices since equipment, particularly end user devices, are not yet available on the market. We know that NTIA/BTOP program managers are aware of this issue and are coordinating efforts with the FCC, NIST and ERIC in this arena. | The equipment for the microwave upgrade has been ordered and is in manufacture now. This equipment may not be completed, factory tested, and delivered until after next quarter's end. | TRUE
NT10BIX5570094 | 2011 | Q1 | Q1 - 2011 | The Executive Office of the State of Mississippi has worked with the Wireless Communication Commission (WCC) and the University of Mississippi Medical Center/Mississippi MED-COM to prepare for the Long Term Evolution (LTE) Mississippi Wireless Information Network's (MSWIN) vendor contract and initial purchases. Project staff has also worked with the Federal Program Officer to finalize modifications to the budget. During Q1 2011, the WCC's contractor conducted microwave path analyses on all of the MSWIN Phase 2 tower sites and began work on the Phase 3 sites. Furthermore, an additional 25 tower sites were approved during the quarter adding to the 76 towers that are currently operational on MSWIN. The microwave equipment for Phase 2 is now in manufacturing at Alcatel-Lucent. On March 3, 2011, the WCC received three proposals in response to our LTE Request for Proposals. Evaluation of the proposals is underway and is expected to be completed during second quarter 2011. The microwave change order has been approved, and we have obligated $17,151,980 for this portion of the project. For Mississippi MED-COM, initial purchase requisitions for initial procurements began to be processed. Additional requisitions were prepared for ambulance and hospital radio procurement, project management, and engineering services which received WCC board approval at the April 7, 2011, meeting. Medical Center legal teams are currently reviewing customer service agreements and contracts fro | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A change order to an existing contract was approved by the State's Contracting Agent this quarter and payment milestones have been negotiated. Microwave equipment has been ordered and is in manufacturing. | N/A | After discussions with our Program Manager, the State determined to allocate all BTOP funds specified for microwave backhaul to build new network miles instead of upgrading existing network backhaul. | N/A | N/A | A change order to an existing contract was approved by the State's Contracting Agent this quarter and payment milestones have been negotiated. Microwave equipment has been ordered and is in manufacturing. | N/A | N/A Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) A change order to an existing contract was approved by the State's Contracting Agent this quarter and payment milestones have been negotiated. Microwave equipment has been ordered and is in manufacturing. After discussions with our Program Manager, the State determined to allocate all BTOP funds specified for microwave backhaul to build new network miles instead of upgrading existing network backhaul. A change order to an existing contract was approved by the State's Contracting Agent this quarter and payment milestones have been negotiated. Microwave equipment has been ordered and is in manufacturings for any variance from the baseline plan or any other relevant information) A change order to an existing contract was approved by the State's Contracting Agent this quarter and payment milestones have been negotiated. Microwave equipment has been ordered and is in manufacturing. After discussions with our Program Manager, the State determined to allocate all BTOP funds specified for microwave backhaul to build new network miles instead of upgrading existing network backhaul. A change order to an existing contract was approved by the State's Contracting Agent this quarter and payment milestones have been negotiated. Microwave equipment has been ordered and is in manufacturing. | 0 | 0 | 0 | N/A | N/A | The State is currently reviewing proposals in response to our Broadband RFP. One option under the RFP is for the Vendor to provide Operations Services. Vendor selection has not occurred. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The State is currently evaluating proposals in response to our Broadband RFP. Proposals were received on March 3, 2011. Vendor selection is expected to occur in June 2011. Although the state is building out network infrastructure, implementation of eNode B equipment for end user access is not projected to begin until third quarter 2011. | The State is currently evaluating proposals in response to our Broadband RFP. Proposals were received on March 3, 2011. Vendor selection is expected to occur in June 2011. Although the state is building out network infrastructure, implementation of eNode B equipment for end user access is not projected to begin until third quarter 2011.N/A | N/A | Speeds will be a minimum of 256 kbps in the uplink and 700 kbps in the downlink. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No Special Offerings are anticipated at this time. | FALSE | N/A | The Detailed Design plan for the microwave equipment for the first 25 new sites has been approved and the equipment is in manufacturing. Factory testing of that equipment is scheduled for June 23, 2011. Construction of the State's MSWIN LMR tower sites pledged as cash match will commence in the next quarter. The State will continue paying lease payments on tower sites that will be used for the Broadband implementation. The State is currently evaluating proposals in response to our Broadband RFP. Proposals were received on March 3, 2011. Vendor selection is expected to occur in June 2011. Although the state is building out network infrastructure, implementation of eNode B equipment for end user access is not projected to begin until third quarter 2011. | Executive Office of the State of Mississippi | Microwave Change Order contracting and Procurement activities for LTE equipment are progressing slower than anticipated at time of the Baseline Budget creation. The continuing efforts by the Federal Communications Commission (FCC) and the Emergency Response Interoperability Center Technical Advisory Committee (ERIC) have impacted the State's ability to define the technical specifications in our procurement instructions. However, during Q1 2011, the WCC's contractor conducted microwave path analyses on all of the MSWIN Phase 2 tower sites and began work on the Phase 3 sites. Furthermore, an additional 25 tower sites were approved by FEMA during the quarter, adding to the 76 towers that are currently operational in MSWIN. The microwave equipment for Phase 2 is now in manufacturing at Alcatel-Lucent. On March 3, 2011, the WCC received three proposals in response to our LTE Request for Proposals. Evaluation of the proposals is underway and is expected to be completed during second quarter 2011. The microwave change order has been approved, and we have obligated $17,151,980 for this portion of the project. | The projected percentages in the table above are based on the completion of the RFP evaluation process in Q2 2011. However, contract negotiations could be impacted by the FCC and ERIC Committee's continuing efforts. | TRUE
NT10BIX5570094 | 2011 | Q2 | Q2 - 2011 | The Executive Office of the State of Mississippi has worked with the Wireless Communication Commission (WCC) and the University of Mississippi Medical Center/Mississippi MED-COM to prepare for the Long Term Evolution (LTE) Mississippi Wireless Information Network's (MSWIN) vendor contract and initial purchases. During Q2 2011, the WCC's contractor completed microwave path analyses on all of the MSWIN Phase 3 tower sites. The WCC continued the build-out of the MSWIN LMR system with the approval of 20 new tower sites. The factory acceptance testing of the microwave backhaul equipment for Phase 2 was conducted at Alcatel-Lucentâ€™s facility with shipment scheduled for the first week of July 2011. The evaluation of the three proposals in response to our LTE Broadband Request for Proposals was completed during second quarter 2011. The MS Department of Information Technology Services Board, the Stateâ€™s Information Technology contracting agent, approved the award of the LTE contract to Motorola Solutions, Inc. on June 23, 2011. Contract negotiations will commence in July with anticipated execution prior to September 1, 2011. For Mississippi MED-COM, initial purchase orders have been released for equipment outlined in the BTOP award totaling approximately three million dollars. These purchase orders were prepared for ambulance and hospital radio procurement, project management, and engineering services which received WCC board approval at the April 7, 2011, meeting. The | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Microwave equipment for the 28 MSWIN Phase 2 sites were manufactured and tested in Quarter 2, 2011. Microwave field path surveys were completed on the remaining MSWIN sites. Manufacturing for remaining sites is scheduled for Quarters 3 and 4 of 2011. Microwave installation is scheduled to begin in Quarter 3 2011. | N/A | After discussions with our Program Manager, the State determined to allocate all BTOP funds specified for microwave backhaul to build new network miles instead of upgrading existing network backhaul. | N/A | N/A | Microwave equipment for the 28 MSWIN Phase 2 sites were manufactured and tested in Quarter 2, 2011. Microwave field path surveys were completed on the remaining MSWIN sites. Manufacturing for remaining sites is scheduled for Quarters 3 and 4 of 2011. Microwave installation is scheduled to begin in Quarter 3 2011. | N/A | N/A | 0 | 0 | 0 | N/A | N/A | The State awarded a contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The State will own the Core and eNodeBs. Contract negotiations will include that Motorola provide a comprehensive operations program to manage and operate the Core and RAN network as well as provide network monitoring, maintenance and support and end user help desk services. The Motorola Project Director will be Bob Busch, (601) 420-4528. 10 Canebrake Boulevard, Suite 350, Flowood, MS 39232. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Although the state is building out network infrastructure, implementation of eNode B equipment for end user access is not projected to begin until third quarter 2011. | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Although the state is building out network infrastructure, implementation of eNode B equipment for end user access is not projected to begin until third quarter 2011. | N/A | Speeds will be a minimum of 256 kbps in the uplink and 700 kbps in the downlink. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings are anticipated at this time. | FALSE | N/A | Microwave equipment for the 28 MSWIN Phase 2 sites were manufactured and tested in Quarter 2, 2011. Microwave field path surveys were completed on the remaining MSWIN sites. Manufacturing for remaining sites is scheduled for Quarters 3 and 4 of 2011. Microwave installation is scheduled to begin in next Quarter (Quarter 3 2011). Construction of the State's MSWIN LMR tower sites pledged as cash match will commence in the next quarter. The State will continue paying lease payments on tower sites that will be used for the Broadband implementation. The evaluation of the three proposals in response to our LTE Broadband Request for Proposals was completed during second quarter 2011. The MS Department of Information Technology Services Board, the Stateâ€™s Information Technology contracting agent, approved the award of the LTE contract to Motorola Solutions, Inc. on June 23, 2011. Contract negotiations will commence next Quarter with anticipated execution prior to September 1, 2011. | Executive Office of the State of Mississippi | Manufacture and factory acceptance testing of the microwave backhaul equipment for MSWIN Phase 2 was not completed until the last week of the Quarter delaying the State's anticipated installation schedule. However, during Q2 2011, the WCC's contractor completed microwave path analyses on all of the MSWIN Phase 3 tower sites. The WCC continued the build-out of the MSWIN LMR system with the approval of 20 new tower sites. The factory acceptance testing of the microwave backhaul equipment for Phase 2 was conducted at Alcatel-Lucentâ€™s facility with shipment scheduled for the first week of July 2011. The evaluation of the three proposals in response to our LTE Broadband Request for Proposals was completed during second quarter 2011. The MS Department of Information Technology Services Board, the Stateâ€™s Information Technology contracting agent, approved the award of the LTE contract to Motorola Solutions, Inc. on June 23, 2011. Contract negotiations will commence in July with anticipated execution prior to September 1, 2011. | The percentages in the table above are based upon a preliminary LTE project implementation schedule. The State awarded the LTE Broadband project to Motorola Solutions, Inc. on June 23, 2011. Deliverables and payment milestones will be negotiated with Motorola Solutions, Inc. as part of the LTE Broadband contract. During the course of implementation, achievement of payment milestones could be impacted by actions of the FCC and/or ERIC Committees regarding specifications, standards or testing requirements. | TRUE
NT10BIX5570094 | 2011 | Q3 | Q3 - 2011 | The Executive Office of the State of Mississippi has worked with the Wireless Communication Commission (WCC) and the University of Mississippi Medical Center/Mississippi MED-COM to prepare for the Long Term Evolution (LTE) Mississippi Wireless Information Network's (MSWIN) vendor contract and initial purchases. Quarterly Activities: During Q3 2011, the WCCâ€™s contractor completed factory acceptance testing of the microwave backhaul equipment for the MSWIN Phase 2 sites. The microwave backhaul equipment for 24 phase two links was delivered to the sites which will provide 428 new network miles. Subsequent to the award of the LTE contract to Motorola Solutions, Inc. on June 23, 2011, the State team successfully negotiated a contract for the project with execution on August 11, 2011. The WCC Staff conducted a project kick-off meeting with the Motorola LTE Project team on September 8, 2011, and initial project tasks associated with design and equipment orders of the core and eNode B equipment are underway. Mississippi MED-COM has completed about 2.5 million dollars in purchases for end-user equipment that is in the process of being drawn down or is progressing through the state purchasing system. We have completed three regional information meetings regarding the use of the funds and getting suggestions from the Coastal Region, Southwest Mississippi Region and Meridian. The MED-COM team has begun the RFP preliminary work with Mississippi Information Technology Serv | 428 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | During Q3 2011, the WCCâ€™s contractor completed factory acceptance testing of the microwave backhaul equipment for the MSWIN Phase 2 sites. The microwave backhaul equipment for 24 phase two links was installed during the quarter totaling 428 new network miles. | N/A | After discussions with our Program Manager, the State determined to allocate all BTOP funds specified for microwave backhaul to build new network miles instead of upgrading existing network backhaul | N/A | N/A | During Q3 2011, the WCCâ€™s contractor completed factory acceptance testing of the microwave backhaul equipment for the MSWIN Phase 2 sites. The microwave backhaul equipment for 24 phase two links was installed during the quarter totaling 428 new network miles. | N/A | N/A | 0 | 0 | 0 | N/A | N/A | The State awarded a contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The State will own the Core and eNodeBs. Contract negotiations will include that Motorola provide a comprehensive operations program to manage and operate the Core and RAN network as well as provide network monitoring, maintenance and support and end user help desk services. The Motorola Project Director will be Bob Busch, (601) 420-4528. 10 Canebrake Boulevard, Suite 350, Flowood, MS 39232. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The eNodeB equipment for MSWIN sites in Phase 1 and Phase 2 is scheduled for installation beginning January 3, 2012 with Acceptance Testing to be completed by June 30, 2012, The Core will initially be installed in November 2011 at the Motorola Schaumburg, IL facility. After testing at the Motorola facility, the Core will be moved to the permanent Core location in Jackson by April 23, 2012. Subscriber loading will begin in second calendar quarter 2012. | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The eNodeB equipment for MSWIN sites in Phase 1 and Phase 2 is scheduled for installation beginning January 3, 2012 with Acceptance Testing to be completed by June 30, 2012, The Core will initially be installed in November 2011 at the Motorola Schaumburg, IL facility. After testing at the Motorola facility, the Core will be moved to the permanent Core location in Jackson by April 23, 2012. Subscriber loading will begin in second calendar quarter 2012. | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings are anticipated at this time. | FALSE | N/A | Factory Acceptance testing for the Phase 3 sites is scheduled for November 2, 2011 at Alcatel-Lucentâ€™s facility with shipment scheduled for the first week of December 2011. The remaining microwave links in Phase 2 will be installed during fourth quarter 2011. | Executive Office of the State of Mississippi | Timeline for installation of microwave dishes on MSWIN towers has been negatively impacted by the preparation and review of tower loading analysis for each tower. Each MSWIN site has excess loading capacity over what is required for the State's land mobile radio system. Microwave dish sizes increased with the Broadband design causing a review of the size, height and azimuth required at each site. MedCom's procurement processes some components scheduled for the quarter have taken longer than anticipated. | The percentages in the table above are based upon the Contract project implementation schedule. The CCI payment milestones have been revised and will be reflected in a BTOP budget modification. During the course of implementation, achievement of payment milestones could be impacted by actions of the FCC and/or ERIC Committees regarding specifications, standards or testing requirements. | TRUE
NT10BIX5570094 | 2011 | Q4 | Q4 - 2011 | The Executive Office of the State of Mississippi has worked with the Wireless Communication Commission (WCC) and the University of Mississippi Medical Center/Mississippi MED-COM to prepare for the Long Term Evolution (LTE) Mississippi Wireless Information Network's (MSWIN) vendor contract and initial purchases. WCC Quarterly Activities: During Q4 2011, the microwave backhaul equipment was installed for 24 MSWIN Phase 2 C & D links. The contractor completed factory acceptance testing for microwave backhaul equipment for all of the Phase 3 sites. The Detailed Design Review for the LTE system was conducted by Motorola on November 15, 2011, with the WCC staff and the Stateâ€™s QA vendor. Twelve sets of LTE antenna arrays were installed on MSWIN sites during the quarter. The equipment for the LTE Core was delivered to Motorolaâ€™s Schaumburg, IL facility where it will be initially staged and tested. The State received notification from Motorola that the eNodeB equipment for 50 sites had been shipped on December 24 from Ericsson with expected delivery to occur early January 2012. Mississippi MED-COM - Purchase requisitions submitted for: 1. Microwave link from MS MedCom to the Sillers Building 2. Network maintenance and security updates for existing equipment 3. Additional radio consoles and furniture 4. Public Safety Answering Point equipment. Email communications have been submitted to end-users for installation of radio equipment in ambulances and hospitals in south and central Mississippi. RFP development of Medical LTE data system application underway with ITS. | 428 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | The WCCâ€™s contractor completed installation of the microwave backhaul equipment for the MSWIN Phase 2 C & D sites. The contractor completed factory acceptance testing for microwave backhaul equipment for all of the Phase 3 sites. We expected to be further along with the construction of the Phase 3 towers which would have allowed us to begin installation of the microwave backhaul equipment. The estimated timeline for the completion of Phase 3 towers is third quarter 2012 at which we should have compeleted all new network miles. | N/A | After discussions with our Program Manager, the State determined to allocate all BTOP funds specified for microwave backhaul to build new network miles instead of upgrading existing network backhaul | N/A | N/A | The WCCâ€™s contractor completed installation of the microwave backhaul equipment for the MSWIN Phase 2 C & D sites. The contractor completed factory acceptance testing for microwave backhaul equipment for all of the Phase 3 sites. We expected to be further along with the construction of the Phase 3 towers which would have allowed us to begin installation of the microwave backhaul equipment. The estimated timeline for the completion of Phase 3 towers is third quarter 2012 at which time we should have completed all new wireless links. | N/A | N/A | 0 | 0 | 0 | N/A | N/A | The State awarded a contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The State will own the Core and eNodeBs. Contract negotiations will include that Motorola provide a comprehensive operations program to manage and operate the Core and RAN network as well as provide network monitoring, maintenance and support and end user help desk services. The Motorola Project Director will be Bob Busch, (601) 420-4528. 10 Canebrake Boulevard, Suite 350, Flowood, MS 39232. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The eNodeB equipment for MSWIN sites in Phase 1 and Phase 2 is scheduled for installation beginning January 3, 2012 with Acceptance Testing to be completed by June 30, 2012, The Core will initially be installed in November 2011 at the Motorola Schaumburg, IL facility. After testing at the Motorola facility, the Core will be moved to the permanent Core location in Jackson by April 23, 2012. Subscriber loading will begin in second calendar quarter 2012. | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The eNodeB equipment for MSWIN sites in Phase 1 and Phase 2 is scheduled for installation beginning January 3, 2012 with Acceptance Testing to be completed by June 30, 2012, The Core will initially be installed in November 2011 at the Motorola Schaumburg, IL facility. After testing at the Motorola facility, the Core will be moved to the permanent Core location in Jackson by April 23, 2012. Subscriber loading will begin in second calendar quarter 2012. | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings are anticipated at this time. | FALSE | N/A | The eNodeB equipment for 50 sites will be delivered in January 2012 with an additional 35 eNodeB's to be delivered in March 2012. The equipment for the LTE core will be initially staged and tested in Motorola's Schaumburg, IL facility and will be available for delivery to the ITS data center in mid-March. | Executive Office of the State of Mississippi | Timeline for installation of microwave dishes on MSWIN towers has been negatively impacted by the preparation and review of tower loading analysis for each tower. Each MSWIN site has excess loading capacity over what is required for the State's land mobile radio system. Microwave dish sizes increased with the Broadband design causing a review of the size, height and azimuth required at each site. MedCom's procurement processes for some components scheduled for the quarter have taken longer than anticipated. | The percentages in the table above are based upon the Contract project implementation schedule. The CCI payment milestones have been revised and will be reflected in a BTOP budget modification. During the course of implementation, achievement of payment milestones could be impacted by actions of the FCC and/or ERIC Committees regarding specifications, standards or testing requirements. | TRUE
NT10BIX5570094 | 2012 | Q1 | Q1 - 2012 | The Executive Office of the State of Mississippi has worked with the Wireless Communications Commission (WCC) and the University of Mississippi Medical Center/Mississippi MEDCOM to prepare for the Long Term Evolution (LTE) Mississippi Wireless Information Network's (MSWINs) vendor contract and initial purchases. WCC - During Q1 2012, the Detailed Design Review for the LTE system was approved by the WCC. 24 sets of LTE antenna arrays were installed on MSWIN sites during the quarter. The eNodeB equipment for 61 sites was delivered to the warehouse in Mississippi with eNodeB equipment being delivered directly to 48 sites. The eNodeB equipment for 31 sites was delivered to the shelter manufacturer in Georgia. They will arrive within the shelter upon a respective Phase 3 site being ready for receipt. The equipment for the LTE core was initially staged and tested in Motorola's Schaumburg, IL facility and was delivered to the ITS data center at the end of March. The State is currently in the process of installing the Core. The State's vendor began the construction of seven tower sites in North Mississippi that will be paid for by state bond funds and used as match. MEDCOM - MEDCOM finalized and published the RFP for the Medical LTE data system per ITS guidelines. A mandatory vendor conference was held on March 26, 2012. Construction began for the installation of the PSAP equipment and additional consoles and other equipment. | 428 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | The WCCâ€™s contractor completed installation of the microwave backhaul equipment for the MSWIN Phase 2 C & D sites in QTR 4, 2011. The contractor has completed factory acceptance testing for microwave backhaul equipment for all of the Phase 3 sites. We expected to be further along with the construction of the Phase 3 towers which would have allowed us to begin installation of the microwave backhaul equipment. The estimated timeline for the completion of Phase 3 towers is fourth quarter 2012 at which we should have completed all new network miles. | N/A | After discussions with our Program Manager, the State determined to allocate all BTOP funds specified for microwave backhaul to build new network miles instead of upgrading existing network backhaul | N/A | N/A | The WCCâ€™s contractor completed installation of the microwave backhaul equipment for the MSWIN Phase 2 C & D sites in QTR 4, 2011. The contractor has completed factory acceptance testing for microwave backhaul equipment for all of the Phase 3 sites. We expected to be further along with the construction of the Phase 3 towers which would have allowed us to begin installation of the microwave backhaul equipment. The estimated timeline for the completion of Phase 3 towers is fourth quarter 2012 at which we should have completed all new wireless links. | N/A | N/A | 0 | 0 | 0 | N/A | N/A | The State awarded a contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The State will own the Core and eNodeBs. Contract negotiations included that Motorola provide a comprehensive operations program to manage and operate the Core and RAN network as well as provide network monitoring, maintenance and support and end user help desk services. The Project Director for Motorola is Jesse Brenton, Jesse.Brenton@motorolasolutions.com, 901-569-5899. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The eNodeB equipment for MSWIN sites in Phase 1 and Phase 2 is scheduled for installation beginning QTR 2, 2012 with Acceptance Testing to be completed by QTR 3, 2012, The Core was initially installed in November 2011 at the Motorola Schaumburg, IL facility. After testing at the Motorola facility, the Core was moved to the permanent Core location in the State Data Center in March 2012. Subscriber loading will begin in QTR 4, 2012. | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The eNodeB equipment for MSWIN sites in Phase 1 and Phase 2 is scheduled for installation beginning QTR 2, 2012 with Acceptance Testing to be completed by QTR 3, 2012, The Core was initially installed in November 2011 at the Motorola Schaumburg, IL facility. After testing at the Motorola facility, the Core was moved to the permanent Core location in the State Data Center in March 2012. Subscriber loading will begin in QTR 4, 2012. | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings are anticipated at this time. | FALSE | N/A | WCC - The LTE Core will be installed at the State Data Center and the core is expected to be tested and fully operational during this quarter. The remainder of the 135 eNodeB's will be delivered to the warehouse in Mississippi and delivered directly to the LMR tower sites. 25 eNodeBs will be installed at tower sites in the central part of the State. 50 sets of LTE antenna arrays will be installed on MSWIN sites during the quarter. The construction of the Tower Sites in North Mississippi being used by match by the State will be complete. The microwave backhaul equipment will be installed for 40 MSWIN LTE network links. MEDCOM - As the site preparation construction nears completion, MEDCOM will move to the next phase of the project. This phase includes the installation of various components of the new infrastructure equipment (console furniture, PSAP system, PTP MSWIN connection). As installation is completed, the next phase will be testing and acceptance of the new hardware and software. Employee training has been scheduled following anticipated equipment acceptance. | Executive Office of the State of Mississippi | Timeline for installation of microwave dishes on MSWIN towers has been negatively impacted by the preparation and review of tower loading analysis for each tower. Each MSWIN site has excess loading capacity over what is required for the State's land mobile radio system. Microwave dish sizes increased with the Broadband design causing a review of the size, height and azimuth required at each site. The analysis and lease renegotiation has occurred and the State is in the process of updating the timeline. State is also seeking to add 60 additional sites to the LTE network which will increase the coverage area of the LTE system. MedCom's procurement processes for some components scheduled for the quarter have taken longer than anticipated. | The percentages in the table above are based upon the Contract project implementation schedule. The State is seeking to add 60 additional sites to the LTE network to increase the coverage area and MEDCOM is seeking a redistribution of funds from the "Ambulance Data Transmission" category to the "Medical Data Coordination System" category. These revisions will be reflected in a BTOP budget modification. During the course of implementation, achievement of payment milestones could be impacted by actions of the FCC and/or NTIA regarding specifications, standards or testing requirements. | TRUE
NT10BIX5570094 | 2012 | Q2 | Q2 - 2012 | The Executive Office of the State of Mississippi has worked with the Wireless Communications Commission (WCC) and the University of Mississippi Medical Center/Mississippi MEDCOM to prepare for the Long Term Evolution (LTE) Mississippi Wireless Information Network's (MSWINs) vendor contract and initial purchases. WCC - On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. As of this date, Mississippi has accepted receipt of and installed the LTE core at the State Data Center. All eNodeB equipment for the 135 MSWIN tower sites has been received by the State and has either been delivered to the site or the placed in the shelters for delivery to the site once construction has been completed. The installation of eNodeB equipment has been completed at 73 of the MSWIN tower sites. 69 sets of LTE antenna arrays have been installed on MSWIN sites. The installation of the microwave backhaul was completed for all Phase 2C & 2D sites. Mississippi also completed the construction and acceptance of all 9 match towers during this quarter. | 428 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | The WCCâ€™s contractor completed installation of the microwave backhaul equipment for the MSWIN Phase 2 C & D sites in QTR 4, 2011. The contractor has completed factory acceptance testing for microwave backhaul equipment for all of the Phase 3 sites. We expected to be further along with the construction of the Phase 3 towers which would have allowed us to begin installation of the microwave backhaul equipment. The estimated timeline for the completion of Phase 3 towers is fourth quarter 2012 at which we should have completed all new network miles. | N/A | After discussions with our Program Manager, the State determined to allocate all BTOP funds specified for microwave backhaul to build new network miles instead of upgrading existing network backhaul | N/A | N/A | The WCCâ€™s contractor completed installation of the microwave backhaul equipment for the MSWIN Phase 2 C & D sites in QTR 4, 2011. The contractor has completed factory acceptance testing for microwave backhaul equipment for all of the Phase 3 sites. We expected to be further along with the construction of the Phase 3 towers which would have allowed us to begin installation of the microwave backhaul equipment. The estimated timeline for the completion of Phase 3 towers is fourth quarter 2012 at which we should have completed all new wireless links. | N/A | N/A | 0 | 0 | 0 | N/A | N/A | The State awarded a contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The State will own the Core and eNodeBs. Contract negotiations included that Motorola provide a comprehensive operations program to manage and operate the Core and RAN network as well as provide network monitoring, maintenance and support and end user help desk services. The Project Director for Motorola is Jesse Brenton, Jesse.Brenton@motorolasolutions.com, 901-569-5899. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Subscriber loading would have begun in QTR 4, 2012 if the State had not received a partial suspension from NTIA for all LTE-related expenditures. | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Subscriber loading would have begun in QTR 4, 2012 if the State had not received a partial suspension from NTIA for all LTE-related expenditures. | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings are anticipated at this time. | FALSE | N/A | The State received a partial suspension from NTIA on May 11, 2012. The State was on target to meet the 67% completion timeline set forth by the BTOP requirements. At this time, the State has halted work on its LTE project for OVER 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading, lease costs to establish a redundant fiber connectivity between the CORE and the RAN, and costs associated with additional planning of sites to improve LTE coverage. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts. The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. The State anticipates the microwave backhaul equipment will be installed for 25 MSWIN LTE network links. | Executive Office of the State of Mississippi | The State received a partial suspension from NTIA on May 11, 2012. The State was on target to meet the 67% completion timeline set forth by the BTOP requirements. At this time, the State has halted work on its LTE project for OVER 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading, lease costs to establish a redundant fiber connectivity between the CORE and the RAN, and costs associated with additional planning of sites to improve LTE coverage. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts. | The State received a partial suspension from NTIA on May 11, 2012. The State was on target to meet the 67% completion timeline set forth by the BTOP requirements. At this time, the State has halted work on its LTE project for OVER 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading, lease costs to establish a redundant fiber connectivity between the CORE and the RAN, and costs associated with additional planning of sites to improve LTE coverage. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts. | TRUE
NT10BIX5570094 | 2012 | Q3 | Q3 - 2012 | WCC - On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. During Q3, 2012, payment milestones were met for the completion of installation services of the LTE Core in the State Data Center for work completed prior to May 11, 2011. Payment milestones were also met for microwave services for Phase 2C & 2D of the MSWIN Network. MedCom - The State of Mississippi received notification from the National Telecommunication and Information Administration that the Broadband Technology Opportunities Program has been partially suspended to evaluate Long Term Evolution spending in light of the formation of the First Responder Network Authority. In response to the above notification, RFP 3679 closure, response evaluation, vendor selection and contract negotiation has been delayed. Functionality testing continues for the Public Safety Answering System. Functionality testing continues for the Microwave connection between MedCom and the Sillers Building. Scheduling of land mobile radio installation continues. | 428 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | The WCCâ€™s contractor completed installation of the microwave backhaul equipment for the MSWIN Phase 2 C & D sites in QTR 4, 2011. The contractor has completed factory acceptance testing for microwave backhaul equipment for all of the Phase 3 sites. Additional milestones related to microwave installation in Phase 3 may have been achieved during this quarter, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. We also expected to be further along with the construction of the Phase 3 towers which would have allowed us to begin installation of the microwave backhaul equipment. The estimated timeline for the completion of Phase 3 towers is fourth quarter 2012 at which we should have completed all new network miles. | N/A | After discussions with our Program Manager, the State determined to allocate all BTOP funds specified for microwave backhaul to build new network miles instead of upgrading existing network backhaul | N/A | N/A | The WCCâ€™s contractor completed installation of the microwave backhaul equipment for the MSWIN Phase 2 C & D sites in QTR 4, 2011. The contractor has completed factory acceptance testing for microwave backhaul equipment for all of the Phase 3 sites. Additional milestones related to microwave installation in Phase 3 may have been achieved during this quarter, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. We also expected to be further along with the construction of the Phase 3 towers which would have allowed us to begin installation of the microwave backhaul equipment. The estimated timeline for the completion of Phase 3 towers is fourth quarter 2012 at which we should have completed all new wireless links. | N/A | N/A | 0 | 0 | 0 | N/A | N/A | The State awarded a contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The State will own the Core and eNodeBs. Contract negotiations included that Motorola provide a comprehensive operations program to manage and operate the Core and RAN network as well as provide network monitoring, maintenance and support and end user help desk services. The Project Director for Motorola is Jesse Brenton, Jesse.Brenton@motorolasolutions.com, 901-569-5899. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Subscriber loading would have begun in QTR 4, 2012 if the State had not received a partial suspension from NTIA for all LTE-related expenditures. | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Subscriber loading would have begun in QTR 4, 2012 if the State had not received a partial suspension from NTIA for all LTE-related expenditures. | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings are anticipated at this time. | FALSE | N/A | The State received a partial suspension from NTIA on May 11, 2012. At this time, the State has halted work on its LTE project for OVER 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts. The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. The State anticipates the microwave backhaul equipment will be installed for 20 MSWIN LTE network links. | Executive Office of the State of Mississippi | The State received a partial suspension from NTIA on May 11, 2012. At this time, the State has halted work on its LTE project for OVER 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts. | The State received a partial suspension from NTIA on May 11, 2012. At this time, the State has halted work on its LTE project for OVER 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts. | TRUE
NT10BIX5570094 | 2012 | Q4 | Q4 - 2012 | On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Payment milestones related to microwave installation in Phase 3 have been achieved during Q4, 2012, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. The Office of the Governor is continuing to work with First Net and NTIA toward a solution that allows Mississippi to move forward with the project. | 428 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Additional milestones related to microwave installation in Phase 3 have been achieved during this quarter, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. | N/A | After discussions with our Program Manager, the State determined to allocate all BTOP funds specified for microwave backhaul to build new network miles instead of upgrading existing network backhaul. | N/A | N/A | Additional milestones related to microwave installation in Phase 3 have been achieved during this quarter, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. | N/A | N/A | 0 | 0 | 0 | N/A | N/A | The State awarded a contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The State will own the Core and eNodeBs. Contract negotiations included that Motorola provide a comprehensive operations program to manage and operate the Core and RAN network as well as provide network monitoring, maintenance and support and end user help desk services. The Project Director for Motorola is Jesse Brenton, Jesse.Brenton@motorolasolutions.com, 901-569-5899. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Subscriber loading would have begun in QTR 4, 2012 if the State had not received a partial suspension from NTIA for all LTE-related expenditures. | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Subscriber loading would have begun in QTR 4, 2012 if the State had not received a partial suspension from NTIA for all LTE-related expenditures. | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings are anticipated at this time. | FALSE | N/A | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended ALL LTE-related expenditures. | Executive Office of the State of Mississippi | The State received a partial suspension from NTIA on May 11, 2012. At this time, the State has halted work on its LTE project for OVER 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts. | The State received a partial suspension from NTIA on May 11, 2012. At this time, the State has halted work on its LTE project for OVER 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts. | TRUE
NT10BIX5570094 | 2013 | Q1 | Q1 - 2013 | On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. WCC: All work related to the deployment of the LTE network has been suspended per NTIA. Payment milestones related to microwave installation in Phase 3 have been achieved during Q1, 2013, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. Medcom: RFP 3679 remains closed due to the partial suspension from NTIA for all LTE-related expenditures. Scheduling and installation of land mobile radio continues. | 428 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | Additional milestones related to microwave installation in Phase 3 have been achieved during this quarter, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. | N/A | After discussions with our Program Manager, the State determined to allocate all BTOP funds specified for microwave backhaul to build new network miles instead of upgrading existing network backhaul. | N/A | N/A | Additional milestones related to microwave installation in Phase 3 have been achieved during this quarter, however, these milestones have not been accepted by the WCC due to issues regarding the Davis Bacon Act. | N/A | N/A | 0 | 0 | 0 | N/A | N/A | The State awarded a contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The State will own the Core and eNodeBs. Contract negotiations included that Motorola provide a comprehensive operations program to manage and operate the Core and RAN network as well as provide network monitoring, maintenance and support and end user help desk services. The Project Director for Motorola is Jesse Brenton, Jesse.Brenton@motorolasolutions.com, 901-569-5899. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Subscriber loading would have begun in QTR 4, 2012 if the State had not received a partial suspension from NTIA for all LTE-related expenditures. | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Subscriber loading would have begun in QTR 4, 2012 if the State had not received a partial suspension from NTIA for all LTE-related expenditures. | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings are anticipated at this time. | FALSE | N/A | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended all LTE-related expenditures. | Executive Office of the State of Mississippi | The State received a partial suspension from NTIA on May 11, 2012. At this time, the State has halted work on its LTE project for over 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts. | The State received a partial suspension from NTIA on May 11, 2012. At this time, the State has halted work on its LTE project for over 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts. | TRUE
NT10BIX5570094 | 2013 | Q2 | Q2 - 2013 | WCC: On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Payment milestones for work accomplished prior to May 11, 2012, were processed. This includes payment for the installation of 20 LTE antenna arrays on MSWIN sites, the delivery of the LTE core to the ITS data center in MS, the installation of 20 new microwave links, the acceptance of the Detailed Design Plan for Phase 3 of the MSWIN system. MedCom: The State of Mississippi continues to negotiate with the First Responder Network Authority (FirstNet) for a contractual agreement which would allow the removal of the suspension for the Long Term Evolution project. RFP 3679 remains closed pending the outcome of the discussions between the State of Mississippi and the FirstNet board. Scheduling and installation of land mobile radio continues. | 784 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | We have installed 20 new microwave links. | N/A | After discussions with our Program Manager, the State determined to allocate all BTOP funds specified for microwave backhaul to build new network miles instead of upgrading existing network backhaul. | N/A | N/A | We have installed 20 new microwave links. | N/A | N/A | 0 | 0 | 0 | N/A | N/A | The State awarded a contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The State will own the Core and eNodeBs. Contract negotiations included that Motorola provide a comprehensive operations program to manage and operate the Core and RAN network as well as provide network monitoring, maintenance and support and end user help desk services. The Project Director for Motorola is Jesse Brenton, Jesse.Brenton@motorolasolutions.com, 901-569-5899. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Subscriber loading would have begun in QTR 4, 2012 if the State had not received a partial suspension from NTIA for all LTE-related expenditures. | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Subscriber loading would have begun in QTR 4, 2012 if the State had not received a partial suspension from NTIA for all LTE-related expenditures. | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings are anticipated at this time. | FALSE | N/A | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended all LTE-related expenditures. | Executive Office of the State of Mississippi | The State received a partial suspension from NTIA on May 11, 2012. At this time, the State has halted work on its LTE project for over 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts. | The State received a partial suspension from NTIA on May 11, 2012. At this time, the State has halted work on its LTE project for over 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts. | TRUE
NT10BIX5570094 | 2013 | Q3 | Q3 - 2013 | WCC: On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. Payment milestones for work accomplished prior to May 11, 2012, were processed. This includes payment for the installation of 29 new microwave links, microwave integration milestones for 43 sites and the acceptance of the microwave for Phase 3 of the MSWIN system. MedCom: The State of Mississippi continues to negotiate with the National Telecommunications and Information Administration (NTIA) and First Responder Network Authority (FirstNet) for an agreement which would allow the continuation of the Broadband Technology Opportunities Program. The State of Mississippi Congressional Delegation, Office of the Governor representatives, UMMC representatives, and Wireless Communication Commission representatives met with NTIA and FirstNet representatives September 17, 2013 in Washington, DC for further negotiations. RFP 3679 remains closed pending the outcome of the discussions between the State of Mississippi and the FirstNet board. MedCom continued with approved scheduling and installation of land mobile radios. No reimbursable milestones were achieved during this quarter therefore no reimbursement funds were drawn down. | 1344 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | We have installed 29 new microwave links. | N/A | After discussions with our Program Manager, the State determined to allocate all BTOP funds specified for microwave backhaul to build new network miles instead of upgrading existing network backhaul. | N/A | N/A | We have installed 29 new microwave links. | N/A | N/A | 0 | 0 | 0 | N/A | N/A | The State awarded a contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The State will own the Core and eNodeBs. Contract negotiations included that Motorola provide a comprehensive operations program to manage and operate the Core, RAN network, microwave backhaul as well as provide network monitoring, maintenance and support and end user help desk services. The Project Director for Motorola is Jesse Brenton, Jesse.Brenton@motorolasolutions.com, 901-569-5899. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Subscriber loading would have begun in QTR 4, 2012 if the State had not received a partial suspension from NTIA for all LTE-related expenditures. | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Subscriber loading would have begun in QTR 4, 2012 if the State had not received a partial suspension from NTIA for all LTE-related expenditures. | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings are anticipated at this time. | FALSE | N/A | The State does not anticipate any LTE accomplishments during this QTR other than the processing of invoices for work already accomplished, as NTIA has partially suspended all LTE-related expenditures. The State is currently in spectrum lease negotiations with FirstNet and expects a resolution will be reached during November 2013. The State is working on a BTOP Modification which will be filed with NTIA should the State be unable to reach a resolution with FirstNet. | Executive Office of the State of Mississippi | The State received a partial suspension from NTIA on May 11, 2012. At this time, the State has halted work on its LTE project for over 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts. | The State received a partial suspension from NTIA on May 11, 2012. At this time, the State has halted work on its LTE project for over 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts. | TRUE
NT10BIX5570094 | 2013 | Q4 | Q4 - 2013 | WCC: On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. No payment milestones for work accomplished prior to May 11, 2012, were processed. Mississippi filed a BTOP Modification with NTIA in December and requested additional time to work with FirstNet and develop a sustainable business model for the LTE Network & to be allowed to use BTOP funds to purchase multi-band devices for first responders which could be used on Band Class 14 at a later date. The BTOP Modification request was denied, without any request for clarification, and NTIA notified Mississippi that the Grant is considered terminated as of December 31, 2013. MedCom: The majority of the quarter included continued discussions between The State of Mississippi and the National Telecommunications and Information Administration (NTIA) whereby the State was requesting a modification to Broadband Technology Opportunities Program beyond December 31, 2013. On December 23, 2013 the Office of the Governor received a letter from the Department of Commerce denying the request for program modification. The letter also stated Mississippi should prepare for grant closeout on January 1, 2014. The Mississippi Department of Information Technology Services removed RFP 3679 from their website citing the length of the suspension and likely need for major RFP restructuring pending program modification approval. Scheduling and installation of land mobile radio continued until December 31, 2013. | 1344 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. No payment milestones for work accomplished prior to May 11, 2012, were processed. | N/A | After discussions with our Program Manager, the State determined to allocate all BTOP funds specified for microwave backhaul to build new network miles instead of upgrading existing network backhaul. | N/A | N/A | On May 11, 2012, Mississippi received a partial suspension from NTIA for all LTE-related expenditures. No payment milestones for work accomplished prior to May 11, 2012, were processed. | N/A | N/A | 0 | 0 | 0 | N/A | N/A | The State awarded a contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. The State will own the Core and eNodeBs. Contract negotiations included that Motorola provide a comprehensive operations program to manage and operate the Core, RAN network, microwave backhaul as well as provide network monitoring, maintenance and support and end user help desk services. The Project Director for Motorola is Jesse Brenton, Jesse.Brenton@motorolasolutions.com, 901-569-5899. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Subscriber loading would have begun in QTR 4, 2012 if the State had not received a partial suspension from NTIA for all LTE-related expenditures. | The State awarded the contract for the LTE equipment to Motorola Solutions, Inc. on June 23, 2011. Subscriber loading would have begun in QTR 4, 2012 if the State had not received a partial suspension from NTIA for all LTE-related expenditures. | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings are anticipated at this time. | FALSE | N/A | None. Mississippi filed a BTOP Modification with NTIA in December and requested additional time to work with FirstNet and develop a sustainable business model for the LTE Network & to be allowed to use BTOP funds to purchase multi-band devices for first responders which could be used on Band Class 14 at a later date. The BTOP Modification request was denied, without any request for clarification, and NTIA notified Mississippi that the Grant is considered terminated as of December 31, 2013. | Executive Office of the State of Mississippi | The State received a partial suspension from NTIA on May 11, 2012. At this time, the State has halted work on its LTE project for over 60 days and will likely incur costs associated with the re mobilization of crews necessary to restart the deployment of the LTE network. Additional state funds will also be expended for tower lease costs associated with the additional antenna loading. The State will also incur costs for LTE antennas hanging on MSWIN owned towers as well as leased towers, eNodeB equipment sitting in shelters, LTE antennas housed in warehouses, etc. Further, should the construction of the LTE network stop, the State will suffer additional financial losses associated with suspending Motorolaâ€™s contract. Because both the P25 and the LTE systems currently under construction are being provided by the same vendor, cost reductions were realized by avoiding a duplication of efforts | The State is currently reviewing contracts to determine the impact associated with termination of the BTOP Grant. Also, the State is reviewing cost information to determine the amount of federal funds needed to deconstruct the MS LTE Network. This includes a fully installed LTE Core in the State Data Center, 135 eNodeB's which have been installed at MSWIN sites across the state, as well as 69 LTE antenna arrays which have been installed on MSWIN tower sites. | TRUE
NT10BIX5570095 | 2010 | Q4 | Q4 - 2010 | Completed all consults and studies (excluding US Forestry) for EA. Completed 75% of OSP Engineering. Finalized collocation and interconnection documents and initiated meetings for distribution. Permits for state and county Right of Way were submitted this quarter and one permit approval was received. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 5 | 0 | N/A | Broadband Service providers may lease dark fiber, as available, on a non-discriminatory basis at a cost based rate to be negotiated with acceptance to binding arbitration. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Receipt of FONSI, therefore allowance to begin contract initiation and completion related to deployment-such as, construction materials and operations bid(s) announced and initiated, via signed contracts and materials ordered. IRU finalized with James Cable, LLC. Signed interconnection/collocation agreements on multiple sites. | JKM Consulting, Inc. | SHPO response was received favorably from Alabama SHPO, however project resource personnel were pulled to gather additional data from the state to satisfy NTIA officials. US Forestry Service was unable to meet to initiate the EA process until January 12, 2011. | Timing circumstances around FONSI receipt expected to push actual major expenditures into the following quarter due typical billing cycles. According to the response received from US Fish and Wildlife, our fiber optic construction crosses several bridges that could be potential roosting sites for the endangered gray bat (Myotis grisescens). Because we are unable to know the outcome of the required surveys (required April through October), this is a possible challenge to our project. | TRUE
NT10BIX5570095 | 2011 | Q1 | Q1 - 2011 | During 1st Quarter 2011, JKM Consulting, Inc. (JKM) has participated in various meetings for Project BEAR (Broadband for East Alabama Region). One significant meeting included the US Forestry Services to review the project and begin the application process for a portion of the route that traverses the National Forest. Additional meetings included: Alabama Supercomputer, Homeland Security of Alabama, Clay County stakeholders, Alabama Broadband Advisory Board meeting and various wireless vendors. During 1st Quarter, the Special Award Condition (SAC) with Appalachian Valley Fiber Network (AVFN) for a fiber overlap issue was completed and a memorandum of understanding between JKM and AVFN was executed. Also during this quarter, JKM continued negotiations toward partnership agreements with the three remaining partners. One collocation agreement was secured this quarter and several are reaching final approvals. JKM continues to pursue a Finding of No Significant Impact (FONSI) in order to begin purchasing equipment, fiber and begin construction. The fiber RFP was submitted during 1st quarter 2011 and the award letter was submitted to the vendor selected based upon the process defined in the JKM Procurement Policy. The pre-bid construction conference is scheduled for early April 2011. The RFP for construction will be released at this event. For Community Outreach, JKM has participated in Chamber events in the four counties that we represent with Project BEAR. We have met wit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Delay in receipt of FONSI has delayed construction. | Constructing an agreement with third party contributor that was compliant with the 501-c3 requirements of the contributor and the applicable FAR regulation has proved to be more time consuming than anticipated. Agreement in principal has been reached, by the attorney's, on the appropriate framework. Attorney's are now working on details. | N/A | N/A | Delay in receipt of FONSI has delayed construction. | Delay in receipt of FONSI has delayed construction. | N/A | Delay in receipt of FONSI has delayed constructiond construction. | 0 | 1 | 0 | N/A | Broadband service providers may lease dark fiber, as available, on a non-discriminatory basis at a cost based rate to be negotiated3 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1. Completion of FONSI 2. Finalize Construction Contract 3. Finalize Anniston Fiber Optics Inkind Contribution Contract 4. Release Optronics Request for Proposal | JKM Consulting, Inc. | Major challenge has been completion of the final EA and receipt of FONSI. BTOP team has continued to provide support through assistance with FCC challenges and meeting the additional changes with the Environmental Assessment. | Additional delays in receiving FONSI could translate into critical delays in construction. Delays in receiving Tribal responses for antennae collocation notice could delay EA completion and further FONSI delays. Because of the Japanese natural disasters, lead time tripled on fiber delivery and may increase further delays. | TRUE
NT10BIX5570095 | 2011 | Q2 | Q2 - 2011 | During this quarter, our greatest achievement was NTIA's acceptance of the final Environmental Assessment(EA) revisions and notification of the Finding of No Significant Impact(FONSI). During this quarter, our selected fiber vendor (Corning Fiber Systems) defaulted on their bid. This forced us to re-award to an alternative vendor at higher prices and longer delivery times.The Request for Proposal(RFP)for Construction, pre-bid meeting and Construction award were conducted this quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Finding of No Significant Impact (FONSI) was delayed beyond the projected time, decreasing the activities that could be undertaken. Also, the tsunami in Japan created a world wide fiber shortage and increased our delivery time line for fiber cable by ten weeks. | N/A | N/A | N/A | Finding of No Significant Impact (FONSI) was delayed beyond the projected time, decreasing the activities that could be undertaken. Also, the tsunami in Japan created a world wide fiber shortage and increased our delivery time line for fiber cable by ten weeks. | N/A | N/A | Finding of No Significant Impact (FONSI) has been delayed beyond the projected time, decreasing the activities that could be undertaken. | 0 | 1 | 0 | n/a | Broadband service providers may lease dark fiber, as available, on a non-discriminatory basis at a cost based rate to be negotiated with acceptance to binding arbitration | n/a | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | n/a | FALSE | n/a | 1-. Finalize Anniston Fiber Optics In-kind Contribution Contract 2. Release Optronics Request for Proposal 3. Begin fiber construction | JKM Consulting, Inc. | The Severe outbreak of multiple tornados throughout Alabama during April generated critical economic losses for two markets of Partner, James Cable LLC. This loss to our partner has effectively caused longer delays to partner and network agreements. Charter Communications has advised that they will be assuming operations of James Cable's Alabama plant. We have had initial favorable conversations with Charter concerning their participation in the project. Additional negotiations with Charter are required and will continue in third (3rd) quarter. | Fiber delivery is identified by the vendor. However, recent natural disasters have caused delays throughout the fiber manufacturing industry. We have this as a potential delay. | TRUE
NT10BIX5570095 | 2011 | Q3 | Q3 - 2011 | During this quarter, we had to replace our engineering firm, due to poor performance. During the week that we anticipated our fiber delivery, we were advised that the September date had been pushed until February. As a result, our focus shifted to looking for an alternative fiber supplier for the third time. James Cable, LLC advised that Charter Communications would be taking ownership of their Alabama properties; therefore we began seeking communication with Charter Communications. In an effort to add additional value to the project, we are seeking cash funding to replace a named partner who is unable to participate due to tax limitations. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fiber shortages and delays have caused significant delays in beginning construction. | Delays as a result in partner participation have delayed lease arrangements. | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 2 | 0 | N/A | Broadband service providers may lease dark fiber, as available, on a non-discriminatory basis at a cost based rate to be negotiated with acceptance to binding arbitration. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Construction contractors are moving equipment in and construction is set to begin in November with fiber delivery being promised mid-November. Optronics Request for Proposal (RFP) will be released with a finalized response and award during this quarter. Partner contribution(s) are expected to reach significant points for further planning. Alabama Power has decided to change their procedures and cost structure for broadband providers. It is anticipated that next quarter will produce our final agreement with Alabama Power (Tallapoosa River Electric Cooperative is complete). | JKM Consulting, Inc. | Delays with our partner, James Cable LLC occurred due to the severe tornado outbreak earlier this year, however we learned this quarter that they were in discussions with Charter Communications for an exchange on markets - Charter will now have James Cable, LLC's Alabama markets effective November 30th, 2011, upon closing. During this quarter, we have focused time on building the relationship with Charter in hopes for a smooth transition. | Fiber delivery is identified for mid-November, therefore we are mobilizing construction at the beginning of next quarter. This is our third order for fiber due to natural disasters earlier this year. We have fiber as a potential delay. We expect James Cable, LLC and Charter Communications to close on November 30, 2011. We anticipate delays for IRU and other fiber leases as this deal is finalized. Funding for Cash replacement of Anniston Fiber Optics, Inc. participation is expected to close in the upcoming quarter. | TRUE
NT10BIX5570095 | 2011 | Q4 | Q4 - 2011 | During this quarter, all fiber cable arrived and construction began. Eight (8) miles of fiber was completed this quarter, in addition to, several additional miles of preparatory work. An equity offering for $1,225,000 was completed to fulfill cash match requirements. Discussions with Charter Communications continued this quarter, as the purchase of Alabama properties from grant partner, James Cable, LLC was completed at the end of November. Requests for Proposal(s) (RFP) for optical equipment and Radio Frequency (RF) Engineering services were released during this fourth quarter. Electronics vendor selection has been narrowed, from RFP responses, to three vendors with selection due January 2012. | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | Previous reports detailed the delays with FONSI and tsunami issues for ordering fiber. The new fiber vender was 2 weeks late delivering the fiber. Preparatory construction began shortly before fiber delivery. | N/A | N/A | N/A | Previous reports detailed the delays with FONSI and tsunami issues, as mentioned above. Winter weather arrived along with the fiber, effecting the underground construction minimally. | N/A | N/A | N/A | 0 | 5 | 0 | None as of this date. | Broadband service providers may lease dark fiber, as available, on a non-discriminatory basis at a cost based rate to be negotiated with acceptance to binding arbitration. Broadband service providers may lease 10/100 mps circuits at $550 per month per leg where available on a month to month basis, term and volume discounts are open to negotiations. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | CLEC (Competitive Local Exchange Carrier) certification is a goal for 1st quarter 2012 with our state hearing set for January. This certification will provide long-term savings and a more favorable contract with Alabama Power. Also on target for 1st quarter is the completion of Jacksonville State University's (JSU) two campus connections and construction completion for northern Calhoun county. The optronics vendor selection will awarded with the order processed and initial installations commencing. Progress is expected with railroad and Department of Transportation (DOT) permits and construction initiated for southbound installation aerial and underground. | JKM Consulting, Inc. | Major challenges this past quarter resulted from delays in fiber and other construction materials delivered by suppliers. Permitting delays are occurring during review process with state DOT, this has been a challenge. Unexpected delays occurred in completing fund raising, however all funds received prior to fourth quarter end. | Charter Communications recent acquisition of partner, James Cable LLC has caused delays in progress for our project as we continue to develop relationships and introduce the value of the project. The business development may be a challenge to meet contract completions as we move forward, nevertheless, we believe in the benefits of the project. The permit from US Forestry Service was completed in June/July 2011, however we have been unable to obtain the actual permit to move forward with construction in our state right-of-way until provided. Several state road projects have developed and changes within their projects have reflected delays in providing permits on state highways. We anticipate moving forward, however note the possibility for challenges with final permits. Winter weather and rain are possible during the 1st quarter and this may present a challenge for the underground construction, however we do not anticipate any unforeseen long delays. | TRUE
NT10BIX5570095 | 2012 | Q1 | Q1 - 2012 | During 1st quarter 2012, a fifteen (15) year Indefeasible Right to Use (IRU) was executed, pending acceptance testing, for 26 miles of 96 fiber(s). Also during this quarter, an Interconnection Agreement with Earthlink/DeltaCom was executed. A total of thirty-six fiber route miles have been completed as of the end of 1st quarter. Total mileage (leased and built fiber) reflects approximately 1/3 of fiber miles to be built. | 34 | 0 | 0 | 0 | 34 | 0 | 0 | 2 | Previous reports detailed the delays with FONSI and tsunami issues for ordering fiber. The new fiber vender was 2 weeks late delivering the fiber. Preparatory construction began shortly before fiber deliver | Acceptance testing for new leased fibers uncovered some needed minor corrective actions. JKM is deferring acceptance of 26 miles of leased new network miles until the corrective actions are complete. | N/A | N/A | Previous reports detailed the delays with FONSI and tsunami issues for ordering fiber. The new fiber vender was 2 weeks late delivering the fiber. Preparatory construction began shortly before fiber deliver | N/A | N/A | N/A | 1 | 4 | 20 | Earthlink Interconnection Agreement completed on March 27, 2012. | N/A | N/A | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 10/100/1000 and Dark Fiber | 3 | 0 | 3 | 0 | N/A | N/A | N/A | both subscribers, Jacksonville State University and Calhoun County Commission are subscribing to dark fiber. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 34 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | During the 2nd quarter, JKM expects to complete fiber acceptance on the 26 route miles of 96 fiber in Anniston. JKM expects all state of Alabama Department of Transportation permits to be revised and accepted. JKM expects to have deployed a total of 70 miles of the new construction backbone fiber (for a total of 96 miles constructed and leased) and deploy the fiber based network equipment. RF engineering will be completed prior to May 1st and JKM expects to place orders for the Radio Frequency (RF) equipment for the last mile wireless coverage of the project. JKM projects having a total of 25 CAI's connected and signed agreements with 2 wholesale/last mile providers by the end of the quarter. | JKM Consulting, Inc. | N/A | N/A | TRUE
NT10BIX5570095 | 2012 | Q2 | Q2 - 2012 | JKM completed the project match contribution during 2nd quarter 2012. This significant accomplishment allows the project to move forward without concerns for meeting the matching grant funds. Construction reached the sixty (60) mile mark during this quarter and contracts were finalized on the lease of twenty-six (26) miles of fiber. All collocation agreements required for equipment placement were completed this quarter and all entrance requests for educational facilities, along with additional Community Anchor Institution facilities were completed during this quarter. During this quarter, JKM released the Request for Quote to equipment vendors for last mile equipment. The selection for the wireless equipment was made and orders placed with Double Radius, the selected vendor, during this quarter. | 60 | 26 | 0 | 0 | 60 | 0 | 0 | 3 | On track with PIP filed in first quarter | On track with PIP filed in first quarter | n/a | n/a | n/a | On track with PIP filed in first quarter | On track with PIP filed in first quarter | On track | 3 | 2 | 20 | Earthlink Interconnection Agreement completed on March 27, 2012. Slappey Telephone agreement completed May 2, 2012. AT&T interconnection agreement completed May 24, 2012 | Wholesales services: 1). Dark Fiber IRU are individual case basis. 2) Dark fiber lease: $250 per month plus $50 per fiber per route mile per month with term and volume discounts to be negotiated. 3). 100 mbs ethernet $550 per month per connection for three year contract. 4) GigE $1500 per month per connection, three year contract. | N/A | 3 | 0 | 2 | 1 | N/A | N/A | N/A | 10/100/1000 and Dark Fiber | 14 | 6 | 8 | 14 | N/A | N/A | N/A | 100 mps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 80 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Equipment arrival expected this quarter for the wireless last mile service; as well as the selection of the Civil Engineering and Construction following pre-bid meetings to be held this next quarter. JKM anticipates the revisions required, after permitting, by AL DOT, to be received, as well as route modifications- as approved by NTIA - to be received this quarter. Projections for third quarter performance 21 additional CAI"s connected, 22 additional new fiber miles, no additional wholesale agreements. | JKM Consulting, Inc. | Challenges faced during this quarter, as in previous quarters, relate to delays with the Alabama Department of Transportation (AL DOT). | One anticipated challenge involves the re-engineer of a lake crossing. This revision is required by the local Electric Cooperative due to National Electric Safety Code (NESC) revisions effective January 2012. | TRUE
NT10BIX5570095 | 2012 | Q3 | Q3 - 2012 | Selection of of wireless installation vender, site surveys completed, microwave link paths verified and finalized, wireless testing lab brought online. | 80 | 26 | 0 | 0 | 80 | 0 | 0 | 3 | On track with PIP filed in first quarter | On track with PIP filed in first quarter | N/A | N/A | N/A | N/A | N/A | On track with PIP filed in first quarter | 3 | 2 | 20 | Earthlink Interconnection Agreement completed on March 27, 2012. Slappey Telephone agreement completed May 2, 2012. AT&T interconnection agreement completed May 24, 2012. | Wholesales services: 1). Dark Fiber IRU are individual case basis. 2) Dark fiber lease: $250 per month plus $50 per fiber per route mile per month with term and volume discounts to be negotiated. 3). 100 mbs ethernet $550 per month per connection for three year contract on net. 4) GigE $1500 per month per connection, three year contract on net | N/A | 3 | 0 | 2 | 1 | N/A | N/A | N/A | 10/100/1000 and Dark Fiber | 14 | 6 | 8 | 14 | N/A | N/A | N/A | 100 mps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 130 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Anticpate completion of fiber backbone (30 additional miles of fiber deployment), connections of additional CAI's (15 new connections), installation of three wireless base stations and commencement of wireless network testing. Add two additional wholesale last mile providers for a total of 5. | JKM Consulting, Inc. | Bringing up the wireless network: testing and debugging, signing last mile provider to resell wireless network. Completion of fiber backbone, testing and cleanup | Outstanding CenturyLink makeready work for final portions of fiber backbone is an issue. | TRUE
NT10BIX5570095 | 2012 | Q4 | Q4 - 2012 | During this quarter, fiber construction entered into the final miles. Lateral builds continued into Community Anchor Institutions and towers for wireless broadband (last mile). Installation on wireless equipment commenced this quarter, along with additional testing for TVWS (TV Whitespace) technology. For Community Outreach, we installed a portal on our website for pre-registration and received over 50 registrations right away, ending the month near 100 for one census area. Discussions continue with TEC Communications for providing last miles services as a wholesale customer. This quarter ended with another last mile provider agreement with CenturyLink. | 105 | 26 | 0 | 0 | 105 | 0 | 0 | 5 | On track with PIP filed in first quarter | On track with PIP filed in first quarter | N/A | N/A | N/A | N/A | N/A | On track with PIP filed in first quarter | 4 | 2 | 20 | Earthlink Interconnection Agreement completed on March 27, 2012. Slappey Telephone agreement completed May 2, 2012. AT&T interconnection agreement completed May 24, 2012. CenturyLink Interconnection Agreement completed December 6, 2012 | Wholesales services: 1). Dark Fiber IRU are individual case basis. 2) Dark fiber lease: $250 per month plus $50 per fiber per route mile per month with term and volume discounts to be negotiated. 3). 100 mbs ethernet $550 per month per connection for three year contract on net. 4) GigE $1500 per month per connection, three year contract on net | N/A | 4 | 0 | 4 | 4 | N/A | N/A | N/A | 10/100/1000 | 20 | 8 | 12 | 15 | On track with PIP filed in first quarter | On track with PIP filed in first quarter | On track with PIP filed in first quarter | 100 MPS (15) 1000 MPS(0) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 160 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10/100/1000 mps | n/a | FALSE | n/a | Anticipated accomplishments for next quarter include: completion of the fiber backbone (final 3 miles of backbone construction) and fiber laterals to Community Anchor Institutions (approximately 3 miles of laterals connecting 8 additional CAI's). Next quarter will continue the installation, testing and service activation of the WiMax network for the last mile portion of the project. Anticipate having a total of 6 wholesaleer/last mile provider contracts signed by of of quarter. | JKM Consulting, Inc. | An ongoing challenge for us during this quarter relates to a lake crossing. We made several attempts with CenturyLink to gain access to their bridge conduit to cross the lake. A conduit agreement is in place, however our attempts are unsuccessful because CenturyLink feels the conduit is not accessible. Several attempts were made to reflect the available space in the conduit, to no avail. | Currently facing two main challenges in achieving our goals. We have a single lake crossing that has been complicated by changes in the National Electric Safety Code (NESC) and the US Army Core of Engineering regulations. These NESC changes have occurred since the original engineering was performed at the beginning of the project (multiple solutions are under investigations). The second challenge involves the IRU (Indefeasible Right to Use) from Southern Company Services for the fibers needed to implement a self-healing ring as opposed to offering a linear system for the project. | TRUE
NT10BIX5570095 | 2013 | Q1 | Q1 - 2013 | For this first quarter 2013, fiber construction has surpassed the 95% completion mark. Test sites for the last mile network portion have commenced in the two counties planned for wireless internet. Focus this quarter has been on the wireless internet construction, turn up and testing. An agreement with an additional last mile provider was completed this quarter with expectations of service interconnection during second quarter 2013 for a rural hospital facility. | 105 | 26 | 0 | 0 | 105 | 0 | 0 | 5 | Original estimate of mileage and route modification identify a target of 97 miles of new. Final engineering and actual total produce a new target of 110 miles of new fiber installed. | On track with PIP filed in first quarter | N/A | N/A | N/A | N/A | N/A | On track with PIP filed in first quarterN/A | 5 | 1 | 20 | Earthlink Interconnection Agreement completed on March 27, 2012. Slappey Telephone agreement completed May 2, 2012. AT&T interconnection agreement completed May 24, 2012. CenturyLink Interconnection Agreement completed December 6, 2012 SynchGlobal Telecommunications agreement completed March 1, 2013 | Wholesales services: 1). Dark Fiber IRU are individual case basis. 2) Dark fiber lease: $250 per month plus $50 per fiber per route mile per month with term and volume discounts to be negotiated. 3). 100 Mbps Ethernet $550 per month per connection for three year contract on-net. 4) GigE $1500 per month per connection, three year contract on-net | N/A | 2 | 1 | 2 | 1 | N/A | N/A | N/A | 10/100/1000 | 21 | 8 | 13 | 16 | On track with PIP filed in first quarter | On track with PIP filed in first quarter | On track with PIP filed in first quarter | 100 Mbps (16) 1000 Mbps (0) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 160 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 10/100/1000 mps | N/A | FALSE | N/A | Anticipated accomplishments for next quarter include: completion of the fiber backbone (final 3 miles of backbone construction) and fiber laterals to Community Anchor Institutions (approximately 3 miles of laterals connecting 20 additional CAI's). Next quarter will continue the installation, testing and service activation of the WiMax network for the last mile portion of the project. Anticipate having a total of 6 wholesaleer/last mile provider contracts signed by of of quarter. | JKM Consulting, Inc. | An ongoing challenge to us this quarter is to complete the wireless access network. Delays with the manufacturer of the wireless network equipment has placed a backlog on the customers pre-registered for service. Another challenge we continue to face revolves on completing an agreement with Southern Company for the two fibers need to close our ring for redundancy on the network. | One challenge involves the IRU (Indefeasible Right to Use) from Southern Company Services for the fibers needed to implement a self-healing ring as opposed to offering a linear system for the project. A second major challenge is receiving the required quantity of Customer Premise Equipment (CPE) for the Television White Space (TVWS) wireless technology portion of the last mile network. | TRUE
NT10BIX5570095 | 2013 | Q2 | Q2 - 2013 | Project BEAR (Broadband for East Alabama Region) reached 99 percent completion. Fiber construction continued this quarter to finalize installations at a number of Community Anchor Institutions (CAIs) with minimal installations remaining for 3rd quarter. A recent interconnection allowed a rural clinic to open on-time with the latest technology and connectivity to larger medical facilities in Georgia. | 110 | 26 | 0 | 0 | 110 | 4 | 0 | 16 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 6 | 0 | 20 | Earthlink Interconnection Agreement completed on March 27, 2012. Slappey Telephone agreement completed May 2, 2012. AT&T interconnection agreement completed May 24, 2012. CenturyLink Interconnection Agreement completed December 6, 2012 SynchGlobal Telecommunications agreement completed March 1, 2013 Roanoke Telephone Company/TEC June 2013 | Wholesales services: 1). Dark Fiber IRU are individual case basis. 2) Dark fiber lease: $250 per month plus $50 per fiber per route mile per month with term and volume discounts to be negotiated. 3). 100 Mbps Ethernet $550 per month per connection for three year contract on-net. 4) GigE $1500 per month per connection, three year contract on-net | n/a | 2 | 1 | 2 | 1 | n/a | n/a | n/a | 10/100/1000 | 38 | 10 | 28 | 3 | n/a | n/a | n/a | all receiving 100 mbps | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 160 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 10/100/1000 | n/a | FALSE | n/a | Third quarter (3Q2013) will bring a close to the project. Therefore, focus will be to complete the project and begin closeout of the grant. One unclear exception involves the deployment of residential services which have been impacted by our wireless vendor withdrawing from the market. We plan to complete the lease for an additional 15 miles of fiber to close our ring giving a project total of 115 miles. We plan to add 11 additional CAI's for a project total total of 49. We do not anticipate signing any additional wholesaler/last mile provider agreement end the project with 6 total. | JKM Consulting, Inc. | An ongoing challenge to us this quarter is to complete the wireless access network. Delays with the manufacturer of the wireless network equipment has placed a backlog on the customers pre-registered for service. Additionally we learned after the close of the quarter, the primary wireless vender is withdrawing from the market and will not deliver the agreed upon materials. Another challenge we continue to face revolves on completing an agreement with Southern Company for two fibers need to close our ring, providing redundancy for the transport network. | One challenge involves the IRU (Indefeasible Right to Use) from Southern Company Services for the fibers needed to implement a self-healing ring as opposed to offering a linear system for the project. A second major challenge is finding an alternate manufacturer or technology for Television White Space (TVWS) wireless technology portion of the last mile network. | TRUE
NT10BIX5570095 | 2013 | Q3 | Q3 - 2013 | Project BEAR (Broadband for East Alabama) has reached 100% completion after completing the final 11 Community Anchor Institutions (CAI's) for a total of 49 for the project and allowing growth opportunities to others in the counties represented by our BTOP project. This project allowed a rural clinic that was previously unable to participate in a statewide network to upgrade facilities and allow new services to the hospital with the bandwidth now available to them and their community in Clay County, Alabama. With changes in the healthcare system, we have seen a number of clinics being consumed by the local hospitals. This network allows our local hospitals to connect at reasonable rates to offer more efficient access to the clinics, while providing hospitals and clinics the bandwidth needed for Electronic Medical Records (EMR) compliance. This network was well received by a number of rural companies that simply could not get the bandwidth needed, such as a rural high tech laser company that would not have been accessible without the middle mile made available through the project. Many of the schools on our network are implementing tablets and Macbooks for student use and additional bandwidth is required. With fiber to these facilities, upgrades are prompt and less costly than previously experienced. Lastly, we enjoy the personal excitement that the last mile, although very limited, allowed for the underserved area of Pleasant Valley allowing customers to establish home-based businesses. This grant allowed a number of opportunities for east Alabama and we look forward to expanding the footprint. | 110 | 26 | 0 | 0 | 110 | 4 | 0 | 16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 6 | 0 | 20 | Earthlink Interconnection Agreement completed on March 27, 2012. Slappey Telephone agreement completed May 2, 2012. AT&T interconnection agreement completed May 24, 2012. CenturyLink Interconnection Agreement completed December 6, 2012 SynchGlobal Telecommunications agreement completed March 1, 2013 Roanoke Telephone Company/TEC June 2013 | See separate pricing plan file submitted. | N/A | 2 | 2 | 2 | 14 | N/A | N/A | N/A | Carrier Ethernet Service: 10mps(0)/20 mps(0)/50mps(0)/100mps(2)/250mps(0)/500mps(0)/1000(1) Fiber Based Internet Access: 10mps(1)/20 mps(0)/50mps(0)/100mps(0)/250mps(0)/500mps(0)/1000(0) : Dark fiber(2) | 49 | 10 | 39 | 14 | N/A | N/A | N/A | Carrier Ethernet Service: 10mps(0)/20 mps(0)/50mps(0)/100mps(29)/250mps(2)/500mps(1)/1000(0) Fiber Based Internet Access: 10mps(12)/20 mps(0)/50mps(0)/100mps(3 )/250mps(0)/500mps(0)/1000(0) : Dark fiber(2) | 3000 | 8 | 8 | 0 | 1 | Had to remove TVWS systems, theoratical households covered by 2.4 | The 2,4 Wifi systems have failed to perform as planned in our terrain and vegetation. The new TVWS technology performed better, but the manufacturer withdrew from the market and no replacement provider has received FCC certification as of yet. | 8 on 2.4: had to remove TVWS customers | N/A | 2meg up/8meg down(8) | 160 | 18 | 6 | 12 | 19 | N/A | N/A | N/A | N/A | Carrier Ethernet Service: 10mps(0)/20 mps(0)/50mps(0)/100mps(29)/250mps(0)/500mps(0)/1000(0) Fiber Based Internet Access: 10mps(4)/20 mps(0)/50mps(2)/100mps(2)/250mps(0)/500mps(0)/1000(0): Small Office/Home Office Wireless Internet: 8/2 Mbps (2), 5/5Mbps (0), 10/10Mbps (0), 20/20Mbps (2),50/5050Mbps (0): Dark fiber(0) | N/A | FALSE | N/A | Complete audit and close out grant | JKM Consulting, Inc. | Earlier this year, the manufacturer for the TVWS technology informed us that they were withdrawing fro the market and would no longer provide additional equipment to connect customers and requested we return the installed equipment that was improperly sold to us. Efforts continue with another provider, however we await their FCC Certification before further discussions. | N/A | TRUE
NT10BIX5570096 | 2010 | Q4 | Q4 - 2010 | The first internal draft of the Environmental Assessment was completed towards a major milestone of removing a Special Award Condition. The Engineering Consultant contract was awarded and the Facility Access Points were walked and verified with the Contractor. This resulted in the beginning of construction grade engineering drawings for the routes. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 2 | 40 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Once the FONSI is received, the building of the middle mile will commence. We anticipate issuing RFP for equipment and conducting sources sought process to identify Small Disadvantaged Businesses as vendors and contractors in building out the middle mile. The construction drawings should be complete and the construction of the network will be underway. Discussions with all IRU including the agreements with our local partner the Water and Power Authority are on target. Rights of way, construction permits and other approvals will also be underway and, to the extent possible, begin site preparation. | Virgin Islands Public Finance Authority | None at this time. | None at this time | TRUE
NT10BIX5570096 | 2011 | Q1 | Q1 - 2011 | The Final EA was submitted on March 28, 2011 with the expectations of a FONSI shortly. The surveys of the selected Fiber or Facility Access Point (FAP) sites have begun as well as the rodding and roping of the existing underground duct bank system to verify the condition of the in-kind assets from VIWAPA. Over 15 RFPs are drafted and ready to be posted for services and materials. We have also selected the IRU and collocation vendors for the mainland aggregation points for the network and are close to completing contract agreements. We have also placed an order for the conduit system excavation equipment that will substantially save on project costs. Field analysis of all entry points from the core network ring and the respective servicing FAP to the communications room of each CAI location have been completed. Existing underground conduit ducts received through our partner VIWAPA as in-kind assets are being rodded and roped to verify condition of ducts for fiber cable installation. Also, make ready analysis has begun on pole spaces in preparation for aerial fiber cable installation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from baseline plan. | No variance from baseline plan. | No variance from baseline plan. | No variance from baseline plan. | No variance from baseline plan. | N/A | N/A | No variance from baseline plan. | 0 | 2 | 40 | None Yet | None Yet. | N/A | 0 | 0 | 0 | 0 | No variance from baseline plan | No variance from baseline plan | N/A | No variance from baseline plan | 0 | 0 | 0 | 0 | No variance from baseline plan | No variance from baseline plan | No variance from baseline plan | No variance from baseline plan | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | We expect to receive our FONSI. Major construction can begin on several of our FAPs and of the underground conduit duct bank. Fiber cable will begin to be pulled through innerduct in existing conduit received as an in-kind contribution. Make-ready efforts are expected to begin in preparation for hanging of the aerial fiber cables. Once the construction of the local FAPs begin we also anticipate that we will make up the variance on the deployment of equipment very easily with the placement of network equipment in our own FAPs. | Virgin Islands Public Finance Authority | A major challenge faced this quarter was not getting the field engineering activities started as quickly as expected due to the late arrival of the field engineering team to the islands. Our engineering & consulting firm is currently engaged on several RUS projects on the mainland which were at various stages of completion. It took time for them to mobilize there manpower after our contract negotiations were completed and get them on island. Also, we did not receive feedback on our draft EA within the time expected (that is, March 18th when we finally got feedback vs. February 15th, which was our original expectation date.) as well as the efforts surrounding whether our needed a SHPO concurrence letter or not. These matters are all now resolved and the project is moving froward as expected. Finally, due to an SF270 amendment on this project, we were unable to make any draws from the federal grant funds - the project's indicator of overall progress. We fully anticipate that this will be resolved shortly and we will draw all eligible grant funds for payments we have made from our local matching monies. We estimate that the project is 2 months off schedule; however, our 67% target is not in jeopardy. | One challenge that may impact achieving planned progress against the project's milestone in this quarter is receiving the authorization to raise sufficient local cash match due to the Legislature's decision to move the BAN/Bond authorization bill to a sub-committee hearing before a final vote before the Committee on the Whole. This may delay the availability of additional local match funds to the middle of May 2011. Without these funds, we will not be able to enter into certain contracts for various construction phases of the project. However, the Governor plans to call a Special Session of the Legislature during the week of April 4, 2011 to expedite this vote and get us the authorization sooner to maintain the financing time schedule to receive the local match dollars before the end of April 2011. We are proceeding with the release of all RFPs and once we receive access to local funds the week of April 20th we do not anticipate any project delays. As we approach the hurricane season, unpredictability becomes a real factor in available days for construction. Fortunately for this project, the majority of the infrastructure (conduit system and poles) is already in place and only requires pulling through or attachment of the fiber cables. | TRUE
NT10BIX5570096 | 2011 | Q2 | Q2 - 2011 | Significant accomplishments for this period include finalizing vendor selection for major portions of the network construction and project implementation. These include the Carrier Ethernet Equipment vendor, UDT; the Operations System Support/Business Support System vendor, ETI; the underground materials (conduits, flowable fill, fiber, fiber splice enclosures) suppliers, WESCO and WallComm. Also, we concluded our negotiations with the Indefeasible Right of Use vendor Global Crossing and undersea cable supplier, Alcatel-Lucent. Also note that the routes associated with these negotiations are under review by the NTIA. Finally, over 90% of the of the permits have been received that will allow us to start major construction in the upcoming quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from baseline plan. | No variance from baseline plan. | No variance from baseline plan. | No variance from baseline plan. | No variance from baseline plan. | N/A | N/A | No variance from baseline plan. | 0 | 2 | 40 | None Yet. | None Yet. | N/A | 0 | 0 | 0 | 0 | No variance from baseline plan. | No variance from baseline plan. | No variance from baseline plan. | No variance from baseline plan. | 0 | 0 | 0 | 0 | No variance from baseline plan. | No variance from baseline plan. | No variance from baseline plan. | No variance from baseline plan. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | We anticipate completing the alpha testing our our major Carrier Ethernet Equipment and initial installation of this equipment at the aggregation points in Miami and New York. We also, anticipate completion of two super Fiber Access Points (FAPs) and the completion of the initial duct bank system from the Global Crossing cable landing station on St. Croix to the Super FAP on St. Croix. We also anticipate receiving final approval from the NTIA on the IRU route modification changes which will enable us to execute the 15-year IRU contract with Global Crossing. | Virgin Islands Public Finance Authority | The major challenge we faced during this quarter was not being able to obtain the approval from the NTIA on the IRU route change modifications . After the initial discussions of the route change in March of this year, formal definition and submission of a comprehensive Supplemental Information Request (SIR) was presented to NTIA in May and detailed discussions continue. The process requires extensive discussions and exchanges between the NTIA and the project team. These discussions and clarifications directly impact the achievement of significant milestones around the route and network build. Also, the grant award is a reimbursement grant for allowable costs. This also impacts our cash flow and ability to prepay or be proactive for critical acquisitions related to this project. These factors will continue to be challenging as we manage the project and seek to strike a balance between milestone achievement and payment for services. We are resolute in the success of this project, nonetheless, and believe that as we gain credible achievement on the project many of these restrictions placed on a new grantee will be removed. We are resolute in the success of this project, nonetheless, and believe that as we gain credible achievement on the project many of these restrictions placed on a new grantee will be removed. | Being on "reimbursement only" for allowable costs in negatively impacting our cash-flow and ability to prepay or or be proactive in any of our critical acquisitions related to this project. This will continue to cripple our ability to achieve major project milestones over the remainder of this project. | TRUE
NT10BIX5570096 | 2011 | Q3 | Q3 - 2011 | Substantially all of the permits, environmental clearances, and construction documents necessary for commencement of underground conduit construction and build out of the new fiber network have been received. Also, the vendor selected for the Carrier Ethernet (United Data Technologies, Inc. or UDT) has developed a test suite for the initial Alpha testing of the network's core gateway routers in a lab environment. Further, contract negotiations began with the vendor selected for Operations Support Systems/Business Support Systems (OSS/BSS). Due to the stop work order, these contract negotiations were put on hold. The project team is, however, prepared to resume final contract negotiations related to OSS/BSS and IRU negotiations with carriers, which were also suspended, once the stop work order has been lifted and the newly-expanded VIPFA/viNGN team has had the opportunity to review all of the business decisions made to date, technological requirements, approved budgets, implementation schedules and approved applications related to each of our BTOP grant awards. Moreover, construction documents were finalized for the two super Fiber Access Points (FAPS) which are planned for location in Frederiksted on St. Croix and on St. Thomas. RFPs were issued, and responses were received for the construction of these facilities. The evaluation of these bids has been suspended and will resume, once the stop work order is lifted and the newly-expanded viNGN team has had the opportunit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We have under performed against this baseline indicator mainly due to general delays in procurement processes related to construction activities and delays in issuing RFPs for services. These delays were cumulative and were further exacerbated by the effects of the stop work order. | No variance from the baseline plan | No variance from the baseline plan | N/A | We have under performed against this baseline indicator mainly due to general delays in procurement processes related to construction activities and delays in issuing RFPs for services. These delays were cumulative and were further exacerbated by the effects of the stop work order. | N/A | N/A | We have under performed against this baseline indicator mainly due to general delays in procurement processes related to construction activities and delays in issuing RFPs for services. These delays were cumulative and were further exacerbated by the effects of the stop work order. We have under performed against this baseline indicator mainly due to general delays in procurement processes related to construction activities and delays in issuing RFPs for services. These delays were cumulative and were further exacerbated by the effects of the stop work order. Construction documents have been finalized for the two super Fiber Access Points (FAPS), and RFPs have been issued and accepted for the construction of these facilities. Further, evaluation of these bids has been suspended and will resume, once remaining issues related to the CAP are addressed. Final design of the first ten regular FAPs has also been completed, and further design work has been suspended until the issues related to the CAP are addressedt this baseline indicator mainly due to general delays in procurement processes related to construction activities and delays in issuing RFPs for services. These delays were cumulative and were further exacerbated by the effects of the stop work order. We have under performed against this baseline indicator mainly due to general delays in procurement processes related to construction activities and delays in issuing RFPs for services. These delays were cumulative and were further exacerbated by the effects of the stop work order. Construction documents have been finalized for the two super Fiber Access Points (FAPS), and RFPs have been issued and accepted for the construction of these facilities. Further, evaluation of these bids has been suspended and will resume, once remaining issues related to the CAP are addressed. Final design of the first ten regular FAPs has also been completed, and further design work has been suspended until the issues related to the CAP are addressed. | 0 | 2 | 0 | At this time, we have no signed agreements with wholesale or retail services providers. Negotiations with our two anticipated broadband wholesalers (AT&T and Global Crossing/Level 3) were suspended during the stop work order. We anticipate that we can resume and conclude negotiations with the intent to fully execute agreements by the end of December 2011. Negotiations will resume immediately after the lifting of the stop work order, with a focus on finalizing the technical details, such as QOS (Quality of Service) delivery. The project team is not able to finalize negotiations with last mile providers before finalizing the IRU agreements with Global Crossing/Level 3 and AT&T, as the terms of these agreements are key to the development of our schedule of products and pricing. We have had discussions with anchor tenants and last mile ISP and broadband providers. These discussions have been conducted on an individual basis and under the aegis of the Broadband Coalition and have resulted in the request for a business and technical conference to be held to further facilitate discussions and to achieve consensus on the optimal types of products and services to be offered by viNGN. The formulation of the Broadband Coalition and the technical conference are also designed to support a range of market research activities and to solicit direct feedback as we formulate our range of products, prices, terms and conditions for the services and products to be offered. | The Comprehensive Community Infrastructure grant award funds will be utilized by viNGN to build out high speed, open access fiber optic network infrastructure which will provide Ethernet transport for service providers and anchor tenants territory-wide. The over arching goal of this segment of the viNGN BTOP implementation, which is reinforced by our enabling legislation, defines our business3 operations as a middle mile provider. The only service the viNGN team anticipates providing is wholesale broadband. The main goal of this build out is to provide reliable, affordable broadband services to ISPs and anchor tenants throughout the Territory. The viNGN management team believes that giving access to relatively inexpensive, reliable bandwidth to ISPs and other retail service providers will help to increase GDP (Gross Domestic Product) growth by giving commercial and residential consumers inexpensive, reliable broadband access. The infrastructure will be deployed to ISPs, other last mile providers and community anchor institutions (such as government departments and agencies, non-profit organizations, educational institutions, public safety entities, healthcare delivery providers, and other key community stakeholders), several of which are located in economically distressed areas. We are currently conducting market research to define our menu of service and product offerings; thus, we are unable to share pricing plans at this time. | Not Applicable | 0 | 0 | 0 | 0 | No variance from the baseline plan | No variance from the baseline plan | N/A | No variance from the baseline plan | 0 | 0 | 0 | 0 | No variance from the baseline plan | No variance from the baseline plan | No variance from the baseline plan | No variance from the baseline plan | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Any special offerings will be determined, based upon the results of market research on optimal pricing and the optimal range of services to be offered. | FALSE | Not Applicable | With the lifting of the stop work order, we are targeting the following significant accomplishments during Quarter 4, CY 2011: - The hiring of a full complement of staff to more effectively implement and monitor program activities; - Revisions to the implementation schedule and the related budget, based upon the U.S. Department of Commerce-approved route change and the delays which are the result of the stop work order; - Completion of the Alpha testing of core gateway routers by UDT; - Completion of the procurement of substantially all construction materials; - Finalization of a significant portion of IRU negotiations; - Substantial completion of the remaining design work associated with the relocation of a few FAPs and finalization of the beach manhole landing relocations; - Resumption of design work for the next phase of FAP rollout; and - Resumption of contract negotiations with the OSS/BSS vendor. | Virgin Islands Public Finance Authority | Overall challenges are generally directly related to slippage against the implementation schedules, specifically with respect to delays with procurement and construction activities. These delays and challenges were further magnified by the stop work order. | Most challenges or issues anticipated during Quarter 4, CY 2011 are related to legacy issues and the above-referenced delays in procurement and construction activities. The Project Team anticipates the following challenges and issues: - The need to fully execute existing contracts that are in various stages of negotiation, all of which were further delayed as a result of the stop work order; - Delays that are likely to result from the need to re-mobilize existing vendor teams; - Increased lead times related to the delivery of fiber; - Though only a few, negotiations needed with the private landowners for FAP Rights of Way (ROWs) and other related matters. In addition, the Project Team is awaiting official written documentation from the U.S. Department of Commerce, which specifies the approved route changes. | TRUE
NT10BIX5570096 | 2011 | Q4 | Q4 - 2011 | The U.S. Virgin Islands Public Finance Authority/Virgin Islands Next Generation Network (VIPFA/viNGN) team successfully met the requirement for submitting a Corrective Action Plan which was accepted, and a unilateral lifting of the stop work was issued on October 17, 2011, which permitted VIPFA/viNGN to resume work. During the remaining ten weeks of Quarter 4, Calendar (CY) 2011, the new management team mobilized and restarted the following implementation activities. The VIPFA/viNGN team hired a Vice President of Project and Program Administration to manage VIPFA/viNGNâ€™s territory-wide project management team and a St. Thomas-based Project Manager for the CCI project. These two new hires are managing projects in both districts until a St. Croix-based Project Manager for the CCI project is hired. The U.S. Virgin Islands team has executed an Indefeasible Right of Use (IRU) agreement with Global Crossing/Level 3 for access to 10Gb of capacity through New York and Miami, providing a strong network with a diverse route and the ability to purchase and offer bandwidth at prices that are significantly less than what is currently offered in the local market. viNGN's partnership with Global Crossing/Level 3 Communications ensures that the U.S. Virgin Islands (the Territory) will have world class Internet connectivity. Global Crossing/Level 3â€™s high capacity Internet Protocol (IP) network will connect the U.S. Virgin Islands to the most important business centers in the world. Its scalable and flexible network platform provides high speed internet connectivity which the VIPFA/viNGN team expects will support private sector and public sector efforts to drive economic growth; encourage service providers to offer more affordable, nationally competitive and reliable service offerings to customers throughout the Territory; expand access to educational opportunities for the Territory's under served populations; and, support local and national efforts in health and public safety. United Data Technologies, Inc. (UDT), the vendor selected to supply the Carrier Ethernet equipment, has completed the first stage of the initial alpha testing of viNGN network's core gateway routers in a lab environment, using electronic equipment purchased by viNGN. The U.S. Virgin Islands team also purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network; signed contracts for the construction of two Super FAPs (Facility Access Points), one each on St. Thomas and St. Croix; and, drafted a Request for Proposals (RFP) for the first of the St. Thomas and St. Croix regular FAPs. The team also re-engaged with the project engineering and the facility engineering/design contractors; conducted a review of the network and Outside Plant (OSP) plant design; completed the mapping of the existing U.S. Virgin Islands Water and Power Authority (WAPA) terrestrial conduit, which was critical to finalizing the engineering plan for the installation of the OSP; and, finalized its approach to performing the trenching needed for building the OSP. The team plans to conduct a competitive procurement for external vendors, through which awards can be made to two or more contractors to conduct simultaneous excavation, trenching and fiber pulling activities in each district. The new management team also began to review all of the business decisions made prior to its arrival, the technological requirements of the network to be built, the approved grant and local match budgets, the implementation schedules, the approved applications and the grant award agreements related to each of its four Broadband Technology Opportunities Program (BTOP) grant awards. | 0 | 3313 | 0 | 0 | 0 | 0 | 0 | 0 | Under performance against this baseline indicator is due to 1) restarting the projects during an implementation period that was shorter by nearly three weeks due to the stop work order that was not lifted until October 17, 2011, 2) resulting delays in procurement, construction and other project implementation activities, and 3) the simultaneous transition of the implementation of the VIPFA/viNGN's four BTOP projects to a new management team. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively consider ways to improve the coordination of construction activities to close the gap against the Baseline. Performance against the Baseline is expected to improve significantly during Quarter 2, CY 2012 and be in line with the Baseline by the end of Quarter 3, CY 2012. | With the signing of the Indefeasible Right of Use (IRU) agreement with Global Crossing/Level 3 for access to 10Gb of capacity through New York and Miami, VIPFA/viNGN is far outperforming the Baseline expectation of 1,600 new network miles to be leased and expects to continue to outperform this measure through at least Quarter 2, CY 2013. The IRU agreement with Global Crossing/Level 3 is providing a strong network with a diverse route and the ability to purchase and offer bandwidth at prices that are significantly less than what is currently offered in the local market. viNGN's partnership with Global Crossing/Level 3 Communications ensures that the U.S. Virgin Islands (the Territory) will have world class Internet connectivity. Global Crossing/Level 3â€™s high capacity Internet Protocol (IP) network will connect the U.S. Virgin Islands to the most important business centers in the world. Its scalable and flexible network platform provides high speed internet connectivity which the | Under performance against this baseline indicator is due to 1) restarting the projects during an implementation period that was shorter by nearly three weeks due to the stop work order that was not lifted until October 17, 2011, 2) resulting delays in procurement, construction and other project implementation activities, and 3) the simultaneous transition of the implementation of the VIPFA/viNGN's four BTOP projects to a new management team. The viNGN team will coordinate with contractors to work on accelerated schedules and actively consider ways to improve the coordination of construction activities to close the gap against the Baseline. Performance against the Baseline is expected to improve significantly during Quarter 2, CY 2012 and be in line with the Baseline by the end of Quarter 3, CY 2012. | N/A | Under performance against this baseline indicator is due to 1) restarting the projects during an implementation period that was shorter by nearly three weeks due to the stop work order that was not lifted until October 17, 2011, 2) resulting delays in procurement, construction and other project implementation activities, and 3) the simultaneous transition of the implementation of the VIPFA/viNGN's four BTOP projects to a new management team. The viNGN team will coordinate with contractors to work on accelerated schedules and actively consider ways to improve the coordination of construction activities to close the gap against the Baseline. Performance against the Baseline is expected to improve significantly during Quarter 2, CY 2012 and be in line with the Baseline by the end of Quarter 3, CY 2012. | N/A | N/A | Under performance against this baseline indicator is due to 1) restarting the projects during an implementation period that was shorter by nearly three weeks due to the stop work order that was not lifted until October 17, 2011, 2) resulting delays in procurement, construction and other project implementation activities, and 3) the simultaneous transition of the implementation of the VIPFA/viNGN's four BTOP projects to a new management team. The viNGN team will coordinate with contractors to work on accelerated schedules and actively consider ways to improve the coordination of construction activities to close the gap against the Baseline. Performance against the Baseline is expected to improve significantly during Quarter 2, CY 2012 and be in line with the Baseline by the end of Quarter 3, CY 2012. | 1 | 1 | 60 | The viNGN team has one signed agreement with a wholesale service provider, i.e. Global Crossing/Level 3. The team is still in negotiations with a second wholesale service provider, AT&T. The project team is not able to finalize negotiations with last mile providers before finalizing an IRU agreement with AT&T, as the terms of the IRU agreements are key to the development of viNGN's schedule of products and pricing. As a result, viNGN has not signed any agreements with retail services providers; however, the team continues to engage the local community of anchor tenants and last mile providers in discussions. These conversations have been conducted on an individual basis, as well as under the aegis of the Broadband Coalition. Two additional Broadband Coalition meetings were held during October 2011, one on St. Thomas and the other on St. Croix. These meetings and conversations have resulted in the request for a business and technical conference to be held to further facilitate discussions and to achieve consensus on the optimal types of products and services to be offered by viNGN. The formulation of the Broadband Coalition and the technical conference are also designed to support a range of market research activities and to solicit direct feedback as viNGN formulates its range of products, prices, terms and conditions for the services and products to be offered. Based on inquires received to date, viNGN expects to have more signed agreements by the end of Qtr. 3, CY 2012. | VIPFA/viNGN plans to build out a high speed, open access, fiber optic network infrastructure which will provide Ethernet transport for service providers and, by extension, to community anchor institutions / anchor tenants territory-wide. VIPFA/viNGN's goal is to serve as a middle mile provider, and the only service the viNGN team anticipates providing is wholesale broadband. This operational model is reinforced by viNGN's enabling legislation. The main goal of this build out is to provide reliable, affordable broadband services to ISPs and other service providers throughout the Territory. The viNGN management team believes that giving access to relatively inexpensive, reliable bandwidth to ISPs and other retail service providers will help to increase GDP (Gross Domestic Product) growth by, in turn, giving commercial and residential consumers inexpensive, reliable broadband access. The infrastructure will be deployed to ISPs, other last mile providers and community anchor institutions / anchor tenants (such as government departments and agencies, non-profit organizations, educational institutions, public safety entities, healthcare delivery providers, and other key community stakeholders), many of which are located in economically distressed areas. The team is currently testing its network and conducting market research to define its menu of service and product offerings; thus, its is unable to share pricing plans at this time. | NOT APPLICABLE | 0 | 0 | 0 | 0 | No variance from baseline | Under performance against this baseline indicator is due to 1) restarting the projects during an implementation period that was shorter by nearly three weeks due to the stop work order that was not lifted until October 17, 2011, 2) resulting delays in procurement, construction and other project implementation activities, and 3) the simultaneous transition of the implementation of the VIPFA/viNGN's four BTOP projects to a new management team. The viNGN team will coordinate with contractors to work on accelerated schedules and actively consider ways to improve the coordination of construction activities to close the gap against the Baseline. Performance against the Baseline is expected to improve significantly during Quarter 3, CY 2012 and be in line with the Baseline by the end of Quarter 4, CY 2012. | N/A | Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available; however, speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; Tier 3 and Tier 4 providers are expected to receive 5,000 Mbps. At this time, viNGN estimates that it will service two (2) providers at Tier 1, two (2) providers at Tier 2, two (2) providers at Tier 3 and one (1) provider at Tier 4. | 0 | 0 | 0 | 0 | Under performance against this baseline indicator is due to 1) restarting the projects during an implementation period that was shorter by nearly three weeks due to the stop work order that was not lifted until October 17, 2011, 2) resulting delays in procurement, construction and other project implementation activities, and 3) the simultaneous transition of the implementation of the VIPFA/viNGN's four BTOP projects to a new management team. The viNGN team will coordinate with contractors to work on accelerated schedules and actively consider ways to improve the coordination of construction activities to close the gap against the Baseline. Performance against the Baseline is expected to improve significantly during Quarter 3, CY 2012 and be in line with the Baseline by the end of Quarter 4, CY 2012. | Under performance against this baseline indicator is due to 1) restarting the projects during an implementation period that was shorter by nearly three weeks due to the stop work order that was not lifted until October 17, 2011, 2) resulting delays in procurement, construction and other project implementation activities, and 3) the simultaneous transition of the implementation of the VIPFA/viNGN's four BTOP projects to a new management team. The viNGN team will coordinate with contractors to work on accelerated schedules and actively consider ways to improve the coordination of construction activities to close the gap against the Baseline. Performance against the Baseline is expected to improve significantly during Quarter 3, CY 2012 and be in line with the Baseline by the end of Quarter 4, CY 2012. | No variance from baseline | Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available; however, speed tiers to CAIs are anticipated at two levels - Tier 1 are expected to receive 10Gbps; Tier 2 Institutions are expected to receive 1Gbps. At this time, viNGN estimates that it will service fourteen (14) CAIs at Tier 1 and the remainder at Tier 2. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Any special offerings will be determined, based upon the results of market research on optimal pricing and the optimal range of services to be offered. | FALSE | NOT APPLICABLE | The VIPFA/viNGN team plans to accomplish the following during Quarter 1, CY 2012: - Commence the construction of the Super FAPs (Facility Access Points) on St. Croix and St. Thomas, with a targeted for Quarter 2, CY 2012, and commence the construction of the initial group of regular FAPs on St. Thomas and St. Croix by the end of Quarter2, CY 2012; - Issue solicitations for excavation and trenching, fiber pulling, the purchase of additional fiber, and the purchase of additional electronics; - Purchase additional routers and aggregate switches from United Data Technologies (UDT); - Sign a contract with the vendor selected to provide technical services equipment, with the purchase of the equipment to occur within the next two quarters; - Revise the VIPFA/viNGN project implementation schedule and the related budget to reflect the U.S. Department of Commerceapproved route change; - Continue negotiations with the vendor selected to provide the Operational Support Systems and Business Support Systems (OSS/ BSS) Software; - Plans to hire a Project Manager, based on St. Croix, in order to most effectively implement and monitor program activities on St. Croix; - Expect to engage its project archaeological team, Maguire, in monitoring identified cultural resource sites which are located within viNGN's construction zones; - Complete the engineering design work for the relocation of the FAPs; - Continue to work to obtain the remaining building permits and right of way access necessary for the construction of the FAPs and the anchor tenant build out; - Complete the design work for the next phase of regular FAPs; and, - Continue negotiations with AT&T for an IRU. As VIPFA/viNGN begins its excavation, trenching and fiber pulling activities and continues with the SuperFAP and regular FAP construction through Quarter 2, CY 2012, the team will coordinate with contractors to work on accelerated schedules. Contractor oversight will include, at a minimum, weekly site visits and meetings with individual contractors and monthly meetings with all contractors who are working through VIPFA/viNGN's CCI project. Meeting discussion topics will include construction status against the implementation schedule, performance against the Baseline Milestones and Indicators, approaches to accelerate construction activities, impediments to accelerating progress in the construction schedule, and ways to improve the coordination of construction activities to close gaps against the Baseline targets. Given the stage of the network build, VIPFA/viNGN does not expect to deploy miles, connect/reconnect any CAIs or sign any broadband wholesaler/last-mile provider agreements by the end of Quarter 1, CY 2012; however, with the actions outlined above expected to be taken to speed up the build schedule, VIPFA/viNGN does expect to be in line with the Baseline targets by the end of Quarter 4, CY 2012 for 1) the number of miles planned for deployment, 2) the number of CAIs planned for reconnection, and 3) the number of broadband wholesaler/last-mile provider agreements planned to be signed. | Virgin Islands Public Finance Authority | The delays and other challenges faced by the VIPFA/viNGN team are related to slippage against the implementation schedule, driven largely by delays with procurement and construction activities and overall project implementation with a largely new management team. These delays and other challenges were further magnified by the stop work order. Under the former management team, the project suffered programmatic and compliance challenges which led to the issuance of a stop-work order and the requirement to submit a Corrective Action Plan (CAP) which was confirmed as acceptable and resulted in the unilateral lifting of the stop work order. Since the lifting of the stop work order on October 17, 2011, the new team has made significant progress towards assessing the current state of project implementation, including contract negotiations and procurement activities; understanding the technological requirements of the network to be built; re-engaging with key architectural and engineering contractors and key partners; restarting the build out/leasing of the network; conducting testing of its high-speed Carrier Ethernet network; gaining a more in depth understanding of its four BTOP programs, including the approved grant and local match budgets, the implementation schedules, the approved applications and the grant award agreements for each; and, training a full complement of new staff. With the start of excavation, trenching and fiber pulling activities and with the SuperFAP and F | The VIPFA/viNGN team must implement the remaining activities under a very compressed schedule. These activities include all aspects of the network build (to include excavation and trenching; fiber pulling activities; FAP construction; electronics purchase, installation and testing; and, network testing), along with finalization of product profiles and a focus on revenue generating activities. The team plans to address these challenges by working its contractors to compress construction schedules, working with contractors to implement parallel construction activities; working with contractors to maintain aggressive work schedules; and, hiring additional staff. The VIPFA/viNGN team will consult with the assigned BTOP program manager if technical assistance is needed. At this time, the team does not anticipate any technical difficulties that would require support from the BTOP program team members. | TRUE
NT10BIX5570096 | 2012 | Q1 | Q1 - 2012 | The Virgin Islands Public Finance Authority (VIPFA)/Virgin Islands Next Generation Network (viNGN)â€™s team continued to make progress with its network build-out. Construction of the two Super FAPs (Facility Access Points), one on St. Thomas and one on St. Croix, is well underway. These will be the first locations where the team can test and light the off-island internet connection points which are being facilitated via an Indefeasible Right of Use (IRU) and Collocation Agreements with Global Crossing/Level 3. VIPFA/viNGN also concluded a competitive procurement process to select contractors to construct six FAPs, three each on St. Thomas and St. Croix. The team obtained the building permits and is prepared to issue Notices to Proceed immediately after the construction contracts have been finalized. Construction is expected to begin by the end of Quarter 2, CY 2012. The team also received construction drawings for an additional twelve (12) FAPs and expects to issue a solicitation for the construction of these FAPS during May 2012. In addition, VIPFA/viNGN purchased 100% of the main network management equipment/switch gear needed for the fiber connections at each FAP, for more than two-thirds of the Community Anchor Institutions (CAIs), for turning on and lighting the network and for managing the network. This purchase includes the software needed to ensure that devices on the network can communicate with each other and to support the partitioning of data/setting up of individual accounts/provisioning. All of the equipment is CISCO-branded equipment. The viNGN management team continues to negotiate with AT&T to lease a SONET OC-48 connection between St. Thomas and St. Croix for up to two years to ensure broadband capacity between the two islands until viNGN is able to build out and/or otherwise obtain capacity along this segment of the approved network route. Further, along with its design engineers, the team continued to assess strategies for accelerating the network build and lighting some segments faster, without creating a cost-prohibitive environment. The strategies being considered include: 1) using pre-fabricated manholes, rather than constructing them; 2) contracting for seven day work weeks; 3) contracting for multiple work shifts; and 4) offering performance incentives for early, satisfactory completion. The team will continue to identify ways to improve productivity and to accelerate implementation. During Quarter 1, Calendar Year (CY) 2012, VIPFA/viNGN hired a Warehouse Manager to manage the St. Croix warehouse. The Warehouse Manager is supervised by the viNGN Director of Property and Procurement who, in turn, is supervised by the viNGN Chief Financial Officer and is responsible for inventory control, including receiving property, logging in property, planning the arrangement of property within the warehouse, identifying any special requirements for certain stock, maintaining property, securing property, maintaining records/administrative documents, maintaining automated storage and retrieval systems, controlling access to the warehouse, signing out assets and reporting on the status of property. Moreover, during Quarter 1, CY 2012, a Broadband Technology Opportunities Program (BTOP) team from National Telecommunications and Information Administration (NTIA) and National Oceanic and Atmospheric Administration (NOAA) conducted a routine site visit, including visits to the locations for the two SuperFAPs, the landing site for the Global Crossing/Level 3 connection on St. Croix and locations for the WAPA-owned conduit and utility poles for which access is being provided as local match. The visiting NTIA/NOAA team cited significant improvements in financial management, internal controls and compliance related to VIPFA/viNGNâ€™s management of its BTOP projects. | 0 | 3313 | 0 | 0 | 0 | 0 | 0 | 0 | The VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date. The team already purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network during the past quarter, and it is currently warehousing it on St. Thomas and St. Croix to ensure that it is immediately available for deployment. During Quarter 2, CY 2012 and Quarter 3, CY 2012, the team expects to complete the procurement for the remainder of its fiber needs. In addition, the team executed a fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami with Global Crossing/Level 3 during the past quarter, and with the expected execution of the lease agreement with AT&T for the SONET OC-48 to connect St. Thomas and St. Croix, the team expects to have additional new network miles to deploy during Quarter 2, CY 2012. Further, construction of the two SuperFAPs is well underway; construction of the remaining FAPs is expected to begin during Quarter 2, CY 2012; and, a large portion of the network management equipment has been procured and is being prepared for testing and staging for placement. Thus, under performance against this baseline indicator is largely due to the delays documented in Section 2 and Section 3 above in this report. Once the RFPs for the aerial fiber pulling and splicing, existing underground fiber pulling and splicing and trenching/excavation are issued during Quarter 2, CY 2012 and Quarter 3, CY 2012 and contracts signed soon after, significant progress is anticipated during the latter half of CY 2012. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. | VIPFA/viNGN team is currently over performing against the Baseline Indicator for the current quarter (i.e. Quarter 3 of Year 2 of the project) and, in fact, exceeds the Baseline Indicator targets that were set through Quarter 2 of Year 3 of the project due to the successful negotiation of a fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami with Global Crossing/Level 3 during the past quarter. With the expected execution of the lease agreement with AT&T for the SONET OC-48 to connect St. Thomas and St. Croix , the team expects to report additional new network miles under lease during Quarter 2, CY 2012. | Under performance against this baseline indicator is largely due to the delays documented in Section 2 and Section 3 above in this report. The VIPFA/viNGN team remains confident that existing network miles will be upgraded and its network will be built-out by June/July 2013, despite the delays it has experienced to date. The team already purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network during the past quarter, and it is currently warehousing it on St. Thomas and St. Croix to ensure that it is immediately available for deployment. During Quarter 2, CY 2012 and Quarter 3, CY 2012, the team expects to complete the procurement for the remainder of its fiber needs. In addition, the team executed a fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami with Global Crossing/Level 3 during the past quarter, and with the expected execution of the lease agreement with AT&T for the SONET OC-48 to connect St. Thomas and St. Croix, the team expects to have additional new network miles to deploy during Quarter 2, CY 2012. Further, construction of the two SuperFAPs is well underway; construction of the remaining FAPs is expected to begin during Quarter 2, CY 2012; and, a large portion of the network management equipment has been procured and is being prepared for testing and staging for placement. Once the RFPs for the aerial fiber pulling and splicing, existing underground fiber pulling and splicing and trenching/excavation are issued during Quarter 2, CY 2012 and Quarter 3, CY 2012 and contracts signed soon after, significant progress is anticipated during the latter half of CY 2012. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. | N/A | Under performance against this baseline indicator is largely due to the delays documented in Section 2 and Section 3 above in this report. The VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date. The team already purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network during the past quarter, and it is currently warehousing it on St. Thomas and St. Croix to ensure that it is immediately available for deployment. During Quarter 2, CY 2012 and Quarter 3, CY 2012, the team expects to complete the procurement for the remainder of its fiber needs. In addition, construction of the two SuperFAPs is well underway; construction of the remaining FAPs is expected to begin during Quarter 2, CY 2012; and, a large portion of the network management equipment has been procured and is being prepared for testing and staging for placement. Once the RFPs for the aerial fiber pulling and splicing, existing underground fiber pulling and splicing and trenching/excavation are issued during Quarter 2, CY 2012 and Quarter 3, CY 2012 and contracts signed soon after, significant progress is anticipated during the latter half of CY 2012. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. | N/A | N/A | Under performance against this baseline indicator is largely due to the delays documented in Section 2 and Section 3 above in this report. The VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date. Construction of the two SuperFAPs is well underway; construction of the remaining FAPs is expected to begin during Quarter 2, CY 2012; and, a large portion of the network management equipment has been procured and is being prepared for testing and staging for placement. In addition, the team already purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network during the past quarter, and it is currently warehousing it on St. Thomas and St. Croix to ensure that it is immediately available for deployment. During Quarter 2, CY 2012 and Quarter 3, CY 2012, the team expects to complete the procurement for the remainder of its fiber needs. Once the RFPs for the aerial fiber pulling and splicing, existing underground fiber pulling and splicing and trenching/excavation are issued during Quarter 2, CY 2012 and Quarter 3, CY 2012 and contracts signed soon after, significant progress is anticipated during the latter half of CY 2012. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. | 1 | 1 | 60 | The viNGN team has one signed agreement with a wholesale service provider, i.e. Global Crossing/Level 3. The team expects to execute a short-term lease agreement with a second wholesale service provider, AT&T, during Quarter 2, CY 2012. The team is not able to finalize negotiations with last mile providers before finalizing an IRU agreement with AT&T, as the terms of the IRU agreements are key to the development of viNGN's schedule of products and pricing. As a result, viNGN has not signed any agreements with retail services/last mile providers; however, the team continues to engage the local community of anchor tenants and last mile providers in discussions. These conversations have been conducted on an individual basis, as well as under the aegis of the Broadband Coalition. viNGN held a Broadband Coalition business and technical conference during January 2012 to further facilitate discussions to support viNGN's efforts to develop an optimal range of types of products and services to be offered by viNGN. Broadband Coalition meetings and technical conferences are designed to support a range of market research activities and to solicit direct feedback as viNGN formulates its range of products, prices, terms and conditions for the services and products to be offered. Based on discussions held to date with last mile providers, viNGN has received indications of interest to enter into agreements. | VIPFA/viNGN plans to build out a high speed, open access, fiber optic network infrastructure which will provide Ethernet transport for service providers and, by extension, to community anchor institutions / anchor tenants territory-wide. VIPFA/viNGN's goal is to serve as a middle mile provider, and the only service the viNGN team anticipates providing is wholesale broadband. This operational model is reinforced by viNGN's enabling legislation. The main goal of this build out is to provide reliable, affordable broadband services to ISPs and other service providers throughout the Territory. The viNGN management team believes that giving access to relatively inexpensive, reliable bandwidth to ISPs and other retail service providers will help to increase GDP (Gross Domestic Product) growth by, in turn, giving commercial and residential consumers inexpensive, reliable broadband access. The infrastructure will be deployed to ISPs, other last mile providers and community anchor institutions / anchor tenants (such as government departments and agencies, non-profit organizations, educational institutions, public safety entities, healthcare delivery providers, and other key community stakeholders), many of which are located in economically distressed areas. The team is currently testing its network and conducting market research to define its menu of service and product offerings; thus, it is unable to share pricing plans at this time. | NOT APPLICABLE | 0 | 0 | 0 | 0 | No variance from the Baseline Indicator target | Refer to the response to Section 5b above in this report. Under performance against this baseline indicator is due to the fact that we have not completed the build-out of the network segments that will enable us to provide improved access to providers; however, as the FAP construction is completed during the next three quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. Performance against the Baseline is expected to improve during Quarter 3, CY 2012 and be in line with the Baseline by the end of Quarter 4, CY 2012. | N/A | Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available; however, speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; Tier 3 and Tier 4 providers are expected to receive 5,000 Mbps. At this time, viNGN estimates that it will service two (2) providers at Tier 1, two (2) providers at Tier 2, two (2) providers at Tier 3 and one (1) provider at Tier 4. | 0 | 0 | 0 | 0 | Refer to the response to Section 5b above in this report. Under performance against this baseline indicator is due to the fact that we have not completed the build-out of the network segments that will enable us to provide improved access to providers; however, as the FAP construction is completed during the next three quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. Performance against the Baseline is expected to improve during Quarter 3, CY 2012 and be in line with the Baseline by the end of Quarter 4, CY 2012. | Refer to the response to Section 5b above in this report. Under performance against this baseline indicator is due to the fact that we have not completed the build-out of the network segments that will enable us to provide improved access to providers; however, as the FAP construction is completed during the next three quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. Performance against the Baseline is expected to improve during Quarter 3, CY 2012 and be in line with the Baseline by the end of Quarter 4, CY 2012. | Refer to the response to Section 5b above in this report. Under performance against this baseline indicator is due to the fact that we have not completed the build-out of the network segments that will enable us to provide improved access to providers; however, as the FAP construction is completed during the next three quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. Performance against the Baseline is expected to improve during Quarter 3, CY 2012 and be in line with the Baseline by the end of Quarter 4, CY 2012. | Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available; however, speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; Tier 3 and Tier 4 providers are expected to receive 5,000 Mbps. At this time, viNGN estimates that it will service two (2) providers at Tier 1, two (2) providers at Tier 2, two (2) providers at Tier 3 and one (1) provider at Tier 4. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Any special offerings will be determined, based upon the results of market research on optimal pricing and the optimal range of services to be offered. | FALSE | NOT APPLICABLE | The VIPFA/viNGN team plans to accomplish the following during Quarter 2, CY 2012: â€¢ Finalize the negotiations with AT&T for an IRU for the SONET OC-48 to connect St. Thomas and St. Croix and execute the related short-term, wholesale agreement which will result in an additional 46.6 miles (75 kilometers) for the network; â€¢ Issue an Invitation for Bid (IFB) and select a vendor to supply the remaining fiber needs; â€¢ Execute an agreement with the selected vendor to supply fiber and issue a Purchase Order for the remaining fiber; â€¢ Begin construction of the first six (6) regular FAPs; â€¢ Complete the design work for the next phase of regular FAPs; â€¢ Issue RFPs for the next phase of FAP construction; â€¢ Order additional network management equipment from UDT; â€¢ Continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012; Discussions will also include construction status against the implementation schedule and overall contract terms, approaches to accelerate construction activities and impediments to accelerating progress in the construction schedule; â€¢ Continue to assess the project implementation schedule and the network design to identify ways to speed up the build-out and â€œlighting upâ€ of the network and to reduce network construction, operational and maintenance costs; â€¢ Work with the BTOP program team and grants office, in efforts to finalize the revised project implementation schedule and the related budget to reflect the U.S. Department of Commerce-approved route change; â€¢ Complete the construction of the St. Thomas SuperFAP and place the network management equipment in it; â€¢ Engage the projectâ€™s archaeological team, Maguire, in monitoring identified cultural resource sites which are located within viNGN's construction zones on St. Croix; â€¢ Finalize and release solicitation(s) for excavation and trenching; â€¢ Finalize and release solicitation(s) for fiber pulling and splicing for existing underground conduit; â€¢ Finalize and release solicitation(s) for aerial fiber pulling and splicing; â€¢ Hire a Project Manager, based on St. Croix, in order to most effectively implement and monitor program activities on St. Croix; â€¢ Continue negotiations with the vendor selected to provide the Operational Support Systems and Business Support Systems (OSS/ BSS) Software; â€¢ Complete the engineering design work for the minimal relocation of a few FAPs and potentially a few beach manhole landings; â€¢ Continue to work to obtain the remaining building permits and rights of way access necessary for the construction of the FAPs and for the Community Anchor Institution (CAI)/anchor tenant build out; and, â€¢ Continue to build out the management and project implementation team. With the actions outlined above expected to be taken to speed up the build schedule, VIPFA/viNGN expects to be in line with the Baseline targets by the end of Quarter 1, CY 2013 for 1) the number of miles planned for deployment, 2) the number of CAIs planned for re-connection, and 3) the number of broadband wholesaler/last-mile provider agreements planned to be signed. Further, during Quarter 2, CY 2012, VIPFA/viNGN expects to lease an additional 46.6 miles (75 kilometers) through the IRU/wholesale agreement with AT&T; however, these miles are not expected to be "deployed" operationally until late CY 2012/CY 2013. Further, the first phase of CAIs are expected to be connected during late CY 2012/early CY 2013. | Virgin Islands Public Finance Authority | Though the VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date, the team will continue to work closely with the assigned BTOP program team members to identify ways to speed up the implementation. Discussions will include the experiences from other BTOP grantees who have experienced and/or are experiencing delays in implementation but have identified or developed ways to speed up their infrastructure build. Further, BTOP program team members and VIPFA/viNGN team members plan to coordinate a discussion/discussions with the National Telecommunication and Information Administration (NTIA)'s Director of Minority Telecom Development. VIPFA/viNGN continues to build its new management and project implementation team. The new team has made significant progress towards assessing the current state of project implementation, including contract negotiations and procurement activities; understanding the technological requirements of the network to be built; re-engaging with key architectural and engineering contractors and key partners; restarting the build out/leasing of the network; conducting testing of its high-speed Carrier Ethernet network and the requirement network management equipment; gaining a more in depth understanding of its four BTOP programs, including the approved grant and local match budgets, the implementation schedules, the approved applications and the grant award agreements for ea | Though the VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date, the team will continue to work closely with the assigned BTOP program team members to identify ways to speed up the implementation. Discussions will include the experiences from other BTOP grantees who have experienced and/or are experiencing delays in implementation but have identified or developed ways to speed up their infrastructure build. Further, BTOP program team members and VIPFA/viNGN team members plan to coordinate a discussion/discussions with the National Telecommunication and Information Administration (NTIA)'s Director of Minority Telecom Development. VIPFA/viNGN continues to build its new management and project implementation team. The new team has made significant progress towards assessing the current state of project implementation, including contract negotiations and procurement activities; understanding the technological requirements of the network to be built; re-engaging with key architectural and engineering contractors and key partners; restarting the build out/leasing of the network; conducting testing of its high-speed Carrier Ethernet network and the requirement network management equipment; gaining a more in depth understanding of its four BTOP programs, including the approved grant and local match budgets, the implementation schedules, the approved applications and the grant award agreements for ea | TRUE
NT10BIX5570096 | 2012 | Q2 | Q2 - 2012 | The Virgin Islands Public Finance Authority (VIPFA)/Virgin Islands Next Generation Network (viNGN) team continued to make progress with its network build out during Quarter 2, Calendar Year (CY) 2012. The final order for Fiber Optic Cable was placed during Quarter 2, CY 2012, and the Fiber Optic Cable is expected to be received during Quarter 3, CY 2012. The construction of the Super FAPs on both St. Thomas and St. Croix are nearing completion. Final details, such as adding permanent power, alarm systems, and landscape details, are in progress and will be completed during Quarter 3, CY 2012. Further, the construction of FAP STX-13 at the U.S. Virgin Islands Department of Public Works-Queens Crossing on St. Croix was started during Quarter 2, CY 2012 and was approximately 70% complete at the end of Quarter 2, CY 2012. Also, at quarter end, the viNGN team was working to finalize six (6) construction services contracts for the construction of six (6) additional FAPs. Construction of these FAPs is expected to start during Quarter 3, CY 2012. The team also expects to issue the remaining solicitations for the construction of the remaining FAPs during Quarter 3, CY 2012. The contract with Atlantic Engineering Group (AEG) was amended during the quarter, in order to include support services for the development of solicitations for services and equipment. During this time, AEG recommended several design changes which will shorten the construction schedule and reduce certain costs which will be reallocated to address other project needs. These changes include 1) reducing the number of Fiber Access Points (FAPs), 2) reducing the number of new conduits in new underground sections of the network and 3) reducing the size of new manholes. These changes do not entail route changes and will not impact the performance of the network. Also during the quarter, viNGN hired a President and Chief Executive Officer, a Vice President of CCI Project, a Project Manager for St. Croix, a Director of Property and Procurement and a Warehouse Manager for St. Thomas. Additionally, a Vice President of Sales and Marketing and a Marketing Coordinator were hired to manage broadband sales once the CCI network is complete and to support coordination of the Broadband Coalition which consists of the Community Anchor Institutions (CAIs), prospective customers for viNGN and other stakeholders. The President and Chief Executive Officer, the Director of Property and Procurement, the Vice President of Sales and Marketing and the Marketing Coordinator are not charged to the federal grant; these positions are funded by VIPFA/viNGN and play significant roles in ensuring that the CCI project and other Broadband Technology Opportunities Program (BTOP) projects are managed effectively and efficiently. Given the increase in staff, viNGN also secured office space in Christiansted on St. Croix. During the quarter, viNGN also received several proposals related to the solicitation for Construction Administration and Site Inspection Services. These proposals are being evaluated, and an award is expected to be made during Quarter 3, CY 2012. In addition, all Cisco equipment ordered through United Data Technologies (UDT) was received during Quarter 2, CY 2012. This is the main network management equipment/switch gear needed for the fiber connections at each FAP, for more than two-thirds of the Community Anchor Institutions (CAIs), for turning on and lighting the network and for managing the network. This purchase included the software needed to ensure that devices on the network can communicate with each other and to support the partitioning of data/setting up of individual accounts/provisioning. The Requests for Proposals (RFPs) for Trenching for St. Thomas and St. Croix were delayed and will be issued during early Quarter 3, CY 2012. The trenching work was divided into four (4) solicitations (two (2) solicitations for each of St. Croix and St. Thomas), in order to reduce the construction schedule for this work. Additionally, all RFPs for underground and aerial fiber installation and splicing are expected to be released during Quarter 3, CY 2012. | 0 | 3353 | 0 | 0 | 0 | 0 | 0 | 0 | The VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date. Under performance against this baseline indicator is largely due to the delays documented in Section 2 and Section 3 above in this report. The team purchased the remaining portion of the core backbone fiber (288 fiber strand count) and the other fiber optic cable required for its network during the past quarter and is currently warehousing it on St. Thomas and St. Croix to ensure that it is immediately available for deployment. In addition, construction of the two Super FAPs is near completion, and construction of the remaining FAPs is expected to begin during Quarter 3, CY 2012. Further, a large portion of the network management equipment has been procured and will be prepared for testing and staging for placement once the FAPs are completed. Significant progress is anticipated during the latter half of Quarter 3, CY 2012/early Quarter 4, CY 2012. The RFPs for the aerial fiber pulling and splicing, existing underground fiber pulling and splicing and trenching/excavation will be issued during Quarter 3, CY 2012. Templates for contracts have been developed; thus, contracts are expected to be signed soon after. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. | VIPFA/viNGN team is currently over performing against the Baseline Indicator for the current quarter (i.e. Quarter 4 of Year 2 of the project) and, in fact, exceeds the Baseline Indicator targets that were set through Quarter 2 of Year 3 of the project due to the successful negotiation of a fifteen (15) year Indefeasible Right of Use (IRU) and collocation agreements for New York City and Miami with Global Crossing/Level 3 during the past quarter. The lease agreement with AT&T for the SONET OC-48 to connect St. Thomas and St. Croix was executed during Quarter 2, CY 2012, and the team expects to report additional new network miles under lease during late Quarter 3, CY 2012/early Quarter 4, CY 2012. | Under performance against this Baseline Indicator is largely due to the delays documented in Section 2 and Section 3 above in this report. The VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date. The team already purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network during the past quarter, and it is currently warehousing it on St. Thomas and St. Croix to ensure that it is immediately available for deployment. During Quarter 3, CY 2012, the team expects to receive the remainder of its fiber needs. In addition, construction of the two Super FAPs is near completion, and construction of the remaining FAPs is expected to begin during Quarter 3, CY 2012. A large portion of the network management equipment has been procured and will be prepared for testing and staging for placement once the FAPs are completed. Significant progress is anticipated during the latter half of Quarter 3, CY 2012/early Quarter 4, CY 2012. The RFPs for the aerial fiber pulling and splicing, existing underground fiber pulling and splicing and trenching/excavation will be issued in Quarter 3, CY 2012. Templates for contracts have been developed; thus, contracts are expected to be signed soon after. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. | N/A | Under performance against this Baseline Indicator is largely due to the delays documented in Section 2 and Section 3 above in this report. The VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date. The team already purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network during the past quarter, and it is currently warehousing it on St. Thomas and St. Croix to ensure that it is immediately available for deployment. During Quarter 3, CY 2012, the team expects to receive the remainder of its fiber needs. In addition, construction of the two Super FAPs is near completion, and construction of the remaining FAPs is expected to begin during Quarter 3, CY 2012. A large portion of the network management equipment has been procured and will be prepared for testing and staging for placement once the FAPs are completed. Significant progress is anticipated during the latter half of Quarter 3, CY 2012/early Quarter 4, CY 2012. The RFPs for the aerial fiber pulling and splicing, existing underground fiber pulling and splicing and trenching/excavation will be issued in Quarter 3, CY 2012. Templates for contracts have been developed; thus, contracts are expected to be signed soon after. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. | N/A | N/A | Under performance against this Baseline Indicator is largely due to the delays documented in Section 2 and Section 3 above in this report. The VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date. The team already purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network during the past quarter, and it is currently warehousing it on St. Thomas and St. Croix to ensure that it is immediately available for deployment. During Quarter 3, CY 2012, the team expects to receive the remainder of its fiber needs. In addition, construction of the two Super FAPs is near completion, and construction of the remaining FAPs is expected to begin during Quarter 3, CY 2012. A large portion of the network management equipment has been procured and will be prepared for testing and staging for placement once the FAPs are completed. Significant progress is anticipated during the latter half of Quarter 3, CY 2012/early Quarter 4, CY 2012. The RFPs for the aerial fiber pulling and splicing, existing underground fiber pulling and splicing and trenching/excavation will be issued in Quarter 3, CY 2012. Templates for contracts have been developed; thus, contracts are expected to be signed soon after. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. | 2 | 0 | 60 | The viNGN team has two signed agreements with wholesale service providers, i.e. Global Crossing/Level 3 and AT&T. The lease agreement with AT&T for the SONET OC-48 was signed during Quarter 2, CY 2012. viNGN has not signed any agreements with retail service providers/last mile providers; however, the team continues to engage the local community of anchor tenants and last mile providers in discussions. These conversations have been conducted on an individual basis, as well as under the aegis of the Broadband Coalition. Broadband Coalition meetings and technical conferences are designed to support a range of market research activities and to solicit direct feedback as viNGN formulates its range of products, prices, terms and conditions for the services and products to be offered. Based on discussions held to date with last mile providers, viNGN has received indications of interest to enter into agreements. | VIPFA/viNGN plans to build out a high speed, open access, fiber optic network infrastructure which will provide Ethernet transport for service providers and, by extension, to Community Anchor Institutions / anchor tenants territory-wide. VIPFA/viNGN's goal is to serve as a Middle Mile provider, and the only service the viNGN team anticipates providing is wholesale broadband. This operational model is reinforced by viNGN's enabling legislation. The main goal of this build out is to provide reliable, affordable broadband services to ISPs and other service providers throughout the Territory. The viNGN management team believes that giving access to relatively inexpensive, reliable bandwidth to ISPs and other retail service providers will help to increase GDP (Gross Domestic Product) growth by, in turn, giving commercial and residential consumers inexpensive, reliable broadband access. The infrastructure will be deployed to ISPs, other last mile providers and Community Anchor Institutions / anchor tenants (such as government departments and agencies, non-profit organizations, educational institutions, public safety entities, healthcare delivery providers, and other key community stakeholders), many of which are located in economically distressed areas. The team is currently testing its network and conducting market research to define its menu of service and product offerings; thus, it is unable to share specific pricing plans at this time. | NOT APPLICABLE | 0 | 0 | 0 | 0 | No variance from the Baseline Indicator target | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that we have not completed the build-out of the network segments that will enable us to provide improved access to providers; however, as the FAP construction is completed during the remaining quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. Performance against the Baseline is expected to improve during Quarter 3, CY 2012 and be in line with the Baseline by the end of Quarter 4, CY 2012. | N/A | Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available; however, speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; Tier 3 and Tier 4 providers are expected to receive 5,000 Mbps. At this time, viNGN estimates that it will service two (2) providers at Tier 1, two (2) providers at Tier 2, two (2) providers at Tier 3 and one (1) provider at Tier 4. | 0 | 0 | 0 | 0 | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that we have not completed the build-out of the network segments that will enable us to provide improved access to providers; however, as the FAP construction is completed during the remaining quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. Performance against the Baseline is expected to improve during Quarter 3, CY 2012 and be in line with the Baseline by the end of Quarter 4, CY 2012. | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that we have not completed the build-out of the network segments that will enable us to provide improved access to providers; however, as the FAP construction is completed during the remaining quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. Performance against the Baseline is expected to improve during Quarter 3, CY 2012 and be in line with the Baseline by the end of Quarter 4, CY 2012. | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that we have not completed the build-out of the network segments that will enable us to provide improved access to providers; however, as the FAP construction is completed during the remaining quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. Performance against the Baseline is expected to improve during Quarter 3, CY 2012 and be in line with the Baseline by the end of Quarter 4, CY 2012. | Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available; however, speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; Tier 3 and Tier 4 providers are expected to receive 5,000 Mbps. At this time, viNGN estimates that it will service two (2) providers at Tier 1, two (2) providers at Tier 2, two (2) providers at Tier 3 and one (1) provider at Tier 4. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Any special offerings will be determined, based upon the results of market research on optimal pricing and the optimal range of services to be offered. | FALSE | NOT APPLICABLE | The VIPFA/viNGN team plans to accomplish the following during Quarter 3, CY 2012: â€¢ Issue all RFPs for Underground Trenching, Fiber Pulling and Splicing and for all Aerial Fiber Pulling and Splicing; â€¢ Complete the construction of the Super FAPs on St. Croix and on St. Thomas and install the network management equipment; â€¢ Complete the construction of the regular FAP on St. Croix; â€¢ Begin construction of an additional six (6) FAPs; â€¢ Release all remaining solicitations for FAP construction; â€¢ Issue solicitations for Generators, AC/DC Power and racking equipment and related installation work for all FAPs; â€¢ Continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012; Discussions will also include construction status against the implementation schedule and overall contract terms, approaches to accelerate construction activities and impediments to accelerating progress in the construction schedule; â€¢ Continue to assess the project implementation schedule and the network design to identify ways to speed up the build-out and â€œlighting upâ€ of the network and to reduce network construction, operational and maintenance costs; â€¢ Complete all archaeological surveys required for FAP relocations and additional archeological surveys for FAPs located near historical sites; â€¢ Select successful proposers/bidders, execute contracts and begin underground trenching, fiber pulling and splicing for existing underground conduit, and aerial fiber pulling and splicing; â€¢ Complete the engineering design work for the minimal relocation of a few FAPs; â€¢ Work with the BTOP program team and grants office, in efforts to finalize the revised project implementation schedule and the related budget to reflect the U.S. Department of Commerce-approved route change; Until the revised budget is approved, the team will report modest overspending against the Administrative and legal expenses budget line item, though that line item will not be exceeded under the revised budget and is exceeded by less than 10% of the budget line item; â€¢ Hire a new Project Manager, based on St. Thomas, in order to most effectively implement and monitor program activities on St. Thomas; and â€¢ Conduct a Broadband Coalition meetings with Community Anchor Institutions, prospective customers for viNGN and other stakeholders to discuss the status of the network build and to provide updates on the anticipated service offerings and pricing schedule. Based on the revised project schedule, VIPFA/viNGN expects to deploy the initial set of miles, connect the first group of CAIs and enter into the first agreement with last mile providers, likely for off-island Internet transit and possibly for CAI pass-through buys, all during late Quarter 4, CY 2012. | Virgin Islands Public Finance Authority | Though the VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date, the team will continue to work closely with the assigned BTOP program team members to identify ways to speed up the implementation. Discussions will include the experiences from other BTOP grantees that have experienced and/or experiencing delays in implementation but have identified or developed ways to speed up their infrastructure build. Further, BTOP program team members and VIPFA/viNGN team members plan to coordinate a discussion/discussions with the National Telecommunication and Information Administration (NTIA)'s Director of Minority Telecom Development. VIPFA/viNGN continues to build its new management and project implementation team. The new team has made significant progress towards assessing the current state of project implementation, including contract negotiations and procurement activities; understanding the technological requirements of the network to be built; re-engaging with key architectural and engineering contractors and key partners; restarting the build out/leasing of the network; conducting testing of its high-speed Carrier Ethernet network and the requirement network management equipment; gaining a more in depth understanding of its four BTOP programs, including the approved grant and local match budgets, the implementation schedules, the approved applications and the grant award agreements for each; a | Though the VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date, the team will continue to work closely with the assigned BTOP program team members to identify ways to speed up the implementation. Discussions will include the experiences from other BTOP grantees who have experienced and/or are experiencing delays in implementation but have identified or developed ways to speed up their infrastructure build. Further, BTOP program team members and VIPFA/viNGN team members plan to coordinate a discussion/discussions with the National Telecommunication and Information Administration (NTIA)'s Director of Minority Telecom Development. VIPFA/viNGN continues to build its new management and project implementation team. The new team has made significant progress towards assessing the current state of project implementation, including contract negotiations and procurement activities; understanding the technological requirements of the network to be built; re-engaging with key architectural and engineering contractors and key partners; restarting the build out/leasing of the network; conducting testing of its high-speed Carrier Ethernet network and the requirement network management equipment; gaining a more in depth understanding of its four BTOP programs, including the approved grant and local match budgets, the implementation schedules, the approved applications and the grant award agreements f | TRUE
NT10BIX5570096 | 2012 | Q3 | Q3 - 2012 | The Virgin Islands Public Finance Authority (VIPFA)/Virgin Islands Next Generation Network (viNGN) team continued to make progress with its network build out during Quarter 3, Calendar Year (CY) 2012. During Quarter 3, CY 2012, VIPFA/viNGN received the final order of fiber optic cables needed to complete the build out of its entire network. VIPFA/viNGN also received bids for aerial and underground hardware and installation services for the fiber optic cables for the entire network. The team expects to finalize contract negotiations and begin installation of these materials, including fiber pulling, during Quarter 4, CY 2012, especially through the existing conduit and on the existing poles for which we received rights to access through an agreement with the U.S. Virgin Islands Water and Power Authority (WAPA). The Requests for Proposals (RFPs) for all of the trenching required on St. Thomas and St. Croix were issued during Quarter 3, CY 2012. VIPFA/viNGN selected two contractors for trenching work, one on St. Croix and one on St. Thomas. These trenches will be the backbone for the fiber optic lines throughout a major portion of each island. The trenching work is divided into four segments (two on St. Thomas and two on St. Croix) and work will be carried out simultaneously, along with aerial installations, starting mid-Quarter 4, CY 2012. In addition to the fiber optic cables being placed on poles and underground through existing conduit, access to which was provided by the U.S. Virgin Islands Water and Power Authority, and through new conduit that is purchased under the grant, fiber will be pulled and spliced through underground traffic-rated vaults. VIPFA/viNGN issued an Invitation for Bids (IFB) for traffic-rated vaults during Quarter 3, CY 2012. The construction of three Fiber Access Points (FAPs) were completed as of September 30, 2012. Overall, the Super FAP on St. Croix was 98% complete, with only testing of the backup equipment remaining. The Super FAP was constructed in the town of Fredriksted, St. Croix and is the main FAP on that island. On St. Thomas, the Super FAP was 98% complete overall, pending electrical and telephone connections, backup equipment testing and security installation. This Super FAP is the main FAP on St. Thomas. The two Super FAPs will be the access points for the AT&T Sonnet OC-48 connection between St. Thomas and St. Croix. In addition, through the Super FAP in Fredriksted, St. Croix, viNGN will connect through Global Crossing/Level 3 to Miami, Florida and New York, New York. A second FAP on St. Croix was also 98% complete overall, as finishing work continues. It is located near the U.S. Virgin Islands Department of Public Works-Queens Crossing location on St. Croix. This FAP serves one of the largest clusters of Community Anchor Institutions (CAIs) and Public Computer Centers (PCCs). For example, the U.S. Virgin Islands Department of Public Works, the Girls Scouts, the U.S. Virgin Islands Department of Labor, the U.S. Virgin Islands Department of Education's Warehouse and the islands only Youth Rehabilitation Center (YRC). At the end of Quarter 3, CY 2012, the VIPFA/viNGN team worked to finalize contract negotiations for eleven (11) contracts for the construction of eleven (11) additional FAPs, four (4) on St. Thomas and seven (7) on St. Croix. Construction of these FAPs is expected to start during Quarter 4, CY 2012. VIPFA/viNGN also issued requests for proposals/bids for the construction of two additional FAPs; FAP racking and installations; FAP DC power/batteries and installations; FAP air conditioning (AC) and installations; FAP generators and installations; network operating software and systems (OSS/BSS); and, underground innerduct and fiber installations on St. Croix and St. Thomas. Proposals/bids were received for the FAP racking and installations; FAP DC power/batteries and installations; FAP AC equipment and installations; FAP generators and installations; and the OSS/BSS network operating software and systems. One contractor was selected for installing transfer switches and backup generators for the remaining FAPs to be constructed. Another contractor was selected for installing racks in the FAPs, including the Super FAPs on St. Thomas and St. Croix, for which construction was completed during Quarter 3, CY 2012. Further, during Quarter 3, CY 2012, VIPFA/viNGN hired a new Project Manager, based on St. Thomas, in order to most effectively implement and monitor program activities on St. Thomas. The team also hired a Controller, CCI for St. Croix and a Safety Coordinator. The Controller, CCI oversees management and coordination of all financial activities for the CCI project team and reports to viNGN's Chief Financial Officer (CFO). The Safety Coordinator reports to the Vice President (VP) of CCI and will ensure that safety meetings are held periodically and that all safety signs are installed prior to construction, including road signs, detour signs, etc. In addition, the Safety Coordinator ensures compliance against Occupational Safety and Health Act (OSHA) Rules and Regulations and conducts safety inspections of all workplace facilities and sites. This position is also in charge of evacuation plans and procedures for viNGN's offices. Moreover, during Quarter 3, CY 2012, a team from the National Telecommunications and Information Administration (NTIA) and the National Oceanic and Atmospheric Administration (NOAA) conducted a follow-up site visit to its February/March 2012 site visit. The visiting NTIA/NOAA team cited significant improvements in VIPFA/VINGN's management of its four broadband projects. | 0 | 3353 | 0 | 0 | 0 | 0 | 0 | 0 | The VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date. The team procured traffic rated vaults for installation during the trench work on both St. Thomas and St. Croix. In addition, VIPFA/viNGN purchased about 30,000 linear feet of PVC conduit for underground fiber optic installation. Some miscellaneous items purchased are couplings, spacers, adapters, cable racks and supports. VIPFA/viNGN also procured 51 reels (408,000 linear feet) of inner ducts for both islands. In addition, construction of the two Super FAPs is complete, and construction of the remaining FAPs is expected to begin during Quarter 4, CY 2012. Further, a large portion of the network management equipment has been procured and will be prepared for staging and testing for placement once the FAPs are completed. The RFPs for the aerial fiber pulling and splicing was issued during Quarter 3, CY 2012. Templates for contracts have been developed; thus, contracts are expected to be signed soon after. The VIPFA/viNGN team will coordinate with contractors to safely work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2013. | VIPFA/viNGN team is currently over performing against the Baseline Indicator for the current quarter and, in fact, exceeds the Baseline Indicator targets that were set through Quarter 3, CY 2012 of the project due to the successful negotiation of a fifteen (15) year Indefeasible Right of Use (IRU) and co-location agreements for New York City and Miami with Global Crossing/Level 3 during the past quarter. The lease agreement with AT&T for the SONET OC-48 to connect St. Thomas and St. Croix was executed during Quarter 2, CY 2012, and the team expects to report additional new network miles under lease during late Quarter 4, CY 2012/Quarter 1, CY 2013. No additional miles have been leased and currently the final work is being done to facilitate final connectivity and activation of SONET OC-48. | Existing backbone fiber remains the same as single-mode (long range backbone fiber). This fiber exist in viNGN warehouse on both islands, St. Thomas and St. Croix, for deployment for aerial for construction phase. This includes backbone fiber and distribution fiber ranges from 288 to 12 fiber strand count. All required fiber arrived in the 3rd quarter. | N/A | VIPFA/viNGN team issued RFPs for aerial construction for fiber optic lines installation on all four islands of the Virgin Islands. This includes 44.6 miles of aerial plant construction on St. Thomas, St. John and Water Island. As a result, there will be 235,426 ft. aerial placement of cables. In addition, VIPFA/viNGN will install 80,000 ft. of High Density Polyethylene (HDPE) into existing conduit and 260,000 ft. of fiber optic cable into newly placed underground conduit. This placement includes 105,000 ft. of fabric innnerduct inside of newly placed conduit. On the island of St. Croix, VIPFA/viNGN will install 36.6 miles of aerial plant. As a result, there will be 193,241 ft. aerial placement of cables. In addition, VIPFA/viNGN will install 130,000 ft. of High Density Polyethylene (HDPE) into existing conduit and 300,000 ft. of fiber optic cable into newly placed underground conduit. This placement includes 130,000 ft. of fabric innnerduct inside of newly placed conduit. | N/A | N/A | A large portion of the network management equipment has been procured and will be prepared for testing and staging for placement once the FAPs are completed. Significant progress is anticipated by the latter half of Quarter 4, CY 2012. Templates for contracts have been developed; thus, contracts are expected to be signed in the early half of Quarter 4, CY 2012. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012k management equipment has been procured and will be prepared for testing and staging for placement once the FAPs are completed. Significant progress is anticipated by the latter half of Quarter 4, CY 2012. Templates for contracts have been developed; thus, contracts are expected to be signed in the early half of Quarter 4, CY 2012. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. | 2 | 0 | 32 | VIPFA/viNGN has two wholesale service contracts, one for 15 years and the other for 1 year. As a result, the average term of signed agreements to date (in quarters) is 32. This figure is a correction to the average term reported of 60 in the last quarterly report. VIPFA/viNGN two agreements are with wholesale service providers, i.e. Global Crossing/Level 3 and AT&T. The lease agreement with AT&T for the SONET OC-48 was signed during Quarter 2, CY 2012. VIPFA/viNGN has not signed any agreements with retail service providers/last mile providers; however, the team continues to engage the local community of anchor tenants and last mile providers in discussions. These conversations have been conducted on an individual basis, as well as under the aegis of the Broadband Coalition. Broadband Coalition meetings and technical conferences are designed to support a range of market research activities and to solicit direct feedback as VIPFA/viNGN formulates its range of products, prices, terms and conditions for the services and products to be offered. Based on discussions held to date with last mile providers, viNGN has received indications of interest to enter into agreements. | VIPFA/viNGN plans to build out a high speed, open access, fiber optic network infrastructure which will provide Ethernet transport for service providers and, by extension, to Community Anchor Institutions / anchor tenants territory-wide. VIPFA/viNGN's goal is to serve as a Middle Mile provider, and the only service the viNGN team anticipates providing is wholesale broadband. This operational model is reinforced by viNGN's enabling legislation. The main goal of this build out is to provide reliable, affordable broadband services to ISPs and other service providers throughout the Territory. The viNGN management team believes that giving access to relatively inexpensive, reliable bandwidth to ISPs and other retail service providers will help to increase GDP (Gross Domestic Product) growth by, in turn, giving commercial and residential consumers inexpensive, reliable broadband access. The infrastructure will be deployed to ISPs, other last mile providers and Community Anchor Institutions / anchor tenants (such as government departments and agencies, non-profit organizations, educational institutions, public safety entities, healthcare delivery providers, and other key community stakeholders), many of which are located in economically distressed areas. The team is currently testing its network and conducting market research to define its menu of service and product offerings; thus, it is unable to share specific pricing plans at this time. No change is anticipated in this quarter | NOT APPLICABLE | 0 | 0 | 0 | 0 | No variance from the Baseline Indicator target | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that we have not completed the build-out of the network segments that will enable us to provide improved access to providers; however, as the FAP construction is completed during the remaining quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. Performance against the Baseline is expected to improve during Quarter 4, CY 2012 and be in line with the Baseline by the end of Quarter 1, CY 2013. | N/A | Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available; however, speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; Tier 3 and Tier 4 providers are expected to receive 5,000 Mbps. At this time, viNGN estimates that it will service two (2) providers at Tier 1, two (2) providers at Tier 2, two (2) providers at Tier 3 and one (1) provider at Tier 4. | 0 | 0 | 0 | 0 | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that we have not completed the build-out of the network segments that will enable us to provide improved access to providers; however, as the FAP construction is completed during the remaining quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. Performance against the Baseline is expected to improve during Quarter 4, CY 2012 and be in line with the Baseline by the end of Quarter 1, CY 2013. | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that we have not completed the build-out of the network segments that will enable us to provide improved access to providers; however, as the FAP construction is completed during the remaining quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. Performance against the Baseline is expected to improve during Quarter 4, CY 2012 and be in line with the Baseline by the end of Quarter 1, CY 2013. | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that we have not completed the build-out of the network segments that will enable us to provide improved access to providers; however, as the FAP construction is completed during the remaining quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012. Performance against the Baseline is expected to improve during Quarter 4, CY 2012 and be in line with the Baseline by the end of Quarter 1, CY 2013. | Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available; however, speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; Tier 3 and Tier 4 providers are expected to receive 5,000 Mbps. At this time, viNGN estimates that it will service two (2) providers at Tier 1, two (2) providers at Tier 2, two (2) providers at Tier 3 and one (1) provider at Tier 4. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Any special offerings will be determined, based upon the results of market research on optimal pricing and the optimal range of services to be offered. At this time, there is no special offering being proposed. | FALSE | NOT APPLICABLE | The VIPFA/viNGN team plans to accomplish the following during Quarter 4, CY 2012: â€¢ Release all remaining solicitations for FAP construction and begin construction on the additional FAPs â€¢ Continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2012; Discussions will also include construction status against the implementation schedule and overall contract terms, approaches to accelerate construction activities and impediments to accelerating progress in the construction schedule â€¢ Continue to assess the project implementation schedule and the network design to identify ways to speed up the build-out and â€œlighting upâ€ of the network and to reduce network construction, operational and maintenance costs â€¢ Complete all archaeological surveys required for FAP locations â€¢ Complete the engineering design work for the relocation of a few FAPs â€¢ During the next two quarters (Quarter 4, CY 2012 and Quarter 1, CY 2013), VIPFA/viNGN will work with the BTOP program team and the grants office to finalize the revised budget to reflect the U.S. Department of Commerce-approved route change; Until the revised budget is approved, the team will report modest overspending against the Administrative and legal expenses budget line item. â€¢ Hire a new Field Coordinator, based on St. Thomas, in order to most effectively implement and monitor program activities on St. Thomas, St. John and Water Island â€¢ Obtain the remaining permits needed to begin construction â€¢ Obtain the remaining environmental assessments â€¢ Participate in Broadband Coalition meetings with Community Anchor Institutions, future viNGN customers and other stakeholders to discuss the status of the network build and to provide updates on the anticipated service offerings and pricing schedule â€¢ Notify and enter into contracts with selected bidders for generators, AC/DC power and racking equipment and related installation work for all FAPs Based on the revised project schedule, VIPFA/viNGN expects to trench 6.2 miles on St. Thomas and 7.2 miles on St. Croix. In addition, VIPFA/viNGN plans to connect the first two CAIs in the downtown area as well as enter into the first agreement with at least one last mile provider, likely for off-island Internet transit and possibly for CAI pass-through buys, all during late Quarter 4, CY 2012 or Quarter 1, CY 2013. | Virgin Islands Public Finance Authority | Though the VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date, the team will continue to work closely with the assigned BTOP program team members to identify ways to speed up the implementation. Discussions will include the experiences from other BTOP grantees that have experienced and/or experiencing delays in implementation but have identified or developed ways to speed up their infrastructure build. Further, BTOP program team members and VIPFA/viNGN team members plan to coordinate a discussion/discussions with the National Telecommunication and Information Administration (NTIA)'s Director of Minority Telecom Development. VIPFA/viNGN continues to build its new management and project implementation team. The new team has made significant progress towards assessing the current state of project implementation, including contract negotiations and procurement activities; understanding the technological requirements of the network to be built; re-engaging with key architectural and engineering contractors and key partners; restarting the build out/leasing of the network; conducting testing of its high-speed Carrier Ethernet network and the requirement network management equipment; gaining a more in depth understanding of its four BTOP programs, including the approved grant and local match budgets, the implementation schedules, the approved applications and the grant award agreements for each; a | Though the VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date, the team will continue to work closely with the assigned BTOP program team members to identify ways to speed up the implementation. Discussions will include the experiences from other BTOP grantees who have experienced and/or are experiencing delays in implementation but have identified or developed ways to speed up their infrastructure build. Further, BTOP program team members and VIPFA/viNGN team members plan to coordinate a discussion/discussions with the National Telecommunication and Information Administration (NTIA)'s Director of Minority Telecom Development. VIPFA/viNGN continues to build its new management and project implementation team. The new team has made significant progress towards assessing the current state of project implementation, including contract negotiations and procurement activities; understanding the technological requirements of the network to be built; re-engaging with key architectural and engineering contractors and key partners; restarting the build out/leasing of the network; gaining a more in depth understanding of its four BTOP programs, including the approved grant and local match budgets, the implementation schedules, the approved applications and the grant award agreements for each; and, training a full complement of new staff. Personnel changes within the management team may slow down progr | TRUE
NT10BIX5570096 | 2012 | Q4 | Q4 - 2012 | The Virgin Islands Public Finance Authority (VIPFA)/Virgin Islands Next Generation Network (viNGN) team continued to make progress with its network build out during Quarter 4, Calendar Year (CY) 2012. During Quarter 4, CY 2012, VIPFA/viNGN began the trenching for fiber optic installation on St. Thomas and St. Croix. Work began simultaneously on both islands, starting November 12th. The trenching work is divided into four segments (two on St. Thomas and two on St. Croix). These trenches will be the backbone for the fiber optic lines throughout a major portion of each island. VIPFA/viNGN trenched approximately 7 miles during Quarter 4, CY 2012. Trenching was hampered by the holiday season, spanning from November through the end of the quarter. VIPFA/viNGN plans to complete the remaining 39 miles of trenching operations with four trenching teams operating simultaneously. VIPFA/viNGN also selected contractors for aerial and underground hardware supply and installation services for the fiber optic cables for the entire network. The team expects to finalize contract negotiations and begin installation of these materials, including fiber pulling, during Quarter 1, CY 2013, with the first phase being pulled through the existing conduit and on existing poles for which VIPFA/viNGN received rights to access through an agreement with the U.S. Virgin Islands Water and Power Authority (WAPA). VIPFA/viNGN plans to install 46.6 miles of aerial construction on St. Thomas and St. John combined and 36.6 miles on St. Croix. In addition to the fiber optic cables being placed on poles and underground through existing conduit, access to which was provided by WAPA, and through new conduit that was purchased under the grant, fiber will be pulled and spliced through underground traffic-rated vaults, rather than through large concrete bunker-styled manholes, in order to speed up the network build, to reduce costs and to reduce the environmental impact from placing them underground. VIPFA/viNGN selected a contractor to supply traffic-rated vaults during Quarter 4, CY 2012. The construction of three Fiber Access Points (FAPs) is complete. The Super FAP construction on St. Croix is 100% complete, with only testing of the backup equipment remaining. The Super FAP was constructed in the town of Frederiksted, St. Croix and is the main FAP on that island. which is near to the Global Crossing/Level 3 network operations center for the U.S. Virgin Islands. On St. Thomas, the Super FAP construction is 100% complete and is located at the U.S. Virgin Islands Emergency Management Agency (VITEMA)'s main operations center and administrative offices for the U.S. Virgin Islands and is also very near the airport. Electrical and telephone connections and security systems were also installed. This Super FAP is the main FAP on St. Thomas. The two Super FAPs will be the access points for the AT&T Sonnet OC-48 connection between St. Thomas and St. Croix. In addition, through the Super FAP in Frederiksted, St. Croix, viNGN will connect through Global Crossing/Level 3 to Miami, Florida and New York, New York. A second FAP construction on St. Croix is also 100%. It is located near the U.S. Virgin Islands Department of Public Works (DPW)-Queens Crossing location on St. Croix. This FAP serves one of the largest clusters of Community Anchor Institutions (CAIs) and Public Computer Centers (PCCs). For example, the U.S. Virgin Islands Department of Public Works, the Girls Scouts, the U.S. Virgin Islands Department of Labor, the U.S. Virgin Islands Department of Education's warehouse and the islands only Youth Rehabilitation Center (YRC) are located near the DPW-Queens Crossing FAP. VIPFA/viNGN also received proposals/bids for the construction of two additional FAPs; FAP DC power/batteries and installations; FAP air conditioning (AC) and installations; and, network operating software and systems (OSS/BSS). One contractor was selected for installing transfer switches and backup generators for the remaining FAPs to be constructed. Another contractor was selected for installing racks in the FAPs, including the Super FAPs on St. Thomas and St. Croix, for which construction was completed during Quarter 3, CY 2012. Further, during Quarter 4, CY 2012, VIPFA/viNGN hired a new Field Coordinator, based on St. Thomas, in order to aid in implementing and monitoring program activities on St. Thomas. | 0 | 3353 | 0 | 0 | 0 | 0 | 0 | 0 | The VIPFA/viNGN team remains confident that its network will be built-out by July 2013, despite the delays it has experienced to date. VIPFA/viNGN trenched approximately 7 miles during Quarter 4, CY 2012. VIPFA/viNGN expects to trench the remaining 39 miles of trenching operations with four trenching teams operating simultaneously. Traffic rated vaults are being constructed for installation during the trench work on both St. Thomas and St. Croix, in order to speed up the network build out, to reduce costs and to reduce the environmental impact of installing large, bunker-type concrete manholes. In addition, VIPFA/viNGN procured approximately 30,000 linear feet of PVC conduit for underground fiber optic installation. Some miscellaneous items procured include couplings, spacers, adapters, cable racks and supports. VIPFA/viNGN also procured 51 reels (408,000 linear feet) of inner duct for St. Thomas and St. Croix. In addition, the construction of three FAPs was completed by the end of Quarter 4, CY 2012, and construction of the remaining FAPs is expected to begin during Quarter 1, CY 2013. Further, a large portion of the network management equipment has been procured and will be prepared for staging and testing for placement once the FAPs are completed. The contracts for the aerial fiber pulling and splicing were issued during Quarter 4, CY 2012, with the contract for the St. Thomas/St. John portion of the network fully executed during Quarter 4, CY 2012. The contract for the St. Croix portion of the network is expected to be executed during early Quarter 1, CY 2013, and the aerial fiber installation on the three islands is scheduled to begin in March, CY 2013. The VIPFA/viNGN team will coordinate with contractors to safely work on accelerated schedules and actively identify and create ways to speed up the implementation of construction activities to close the gap against the Baseline during CY 2013. | VIPFA/viNGN team is currently over performing against the Baseline Indicator for Quarter 4, CY 2013, and in fact, exceeds the Baseline Indicator targets that were set through Quarter 4, CY 2012 of the project due to the successful negotiation of a fifteen (15) year Indefeasible Right of Use (IRU) and co-location agreements for New York City and Miami with Global Crossing/Level 3 during Quarter 4, CY 2011/early Quarter 1, CY 2012. The lease agreement with AT&T for the SONET OC-48 to connect St. Thomas and St. Croix was executed during Quarter 2, CY 2012. Preliminary work is being done to facilitate the final connection and activation of the SONET OC-48. No additional miles have been leased. | Existing backbone fiber remains the same as single-mode (long range backbone fiber). This fiber exists in viNGN's warehouse on both islands, St. Thomas and St. Croix, for deployment during aerial installations. This includes backbone fiber and distribution fiber which range from 288 to 12 fiber strand count. All fiber optic cable required to complete the network build out arrived by Quarter 3, CY 2012. IVIPFA/viNGN trenched approximately 7 miles during Quarter 4, CY 2012 and installed new conduit, in order to run new fiber optic cable. VIPFA/viNGN expects to trench the remaining 39 miles with four trenching teams operating simultaneously. | N/A | VIPFA/viNGN trenched approximately 7 miles during Quarter 4, CY 2012 and installed new conduit, in order to run new fiber optic cable. VIPFA/viNGN expects to trench the remaining 39 miles and install new conduit for new fiber installation with four trenching teams operating simultaneously. The VIPFA/viNGN team selected contractors for aerial construction for fiber optic line installation on St. Thomas, St. John, Water Island and St. Croix. This includes 44.6 miles of aerial plant construction on St. Thomas, St. John and Water Island combined. As a result, there will be 235,426 ft. of aerial placement of cables. In addition, VIPFA/viNGN will install 80,000 ft. of High Density Polyethylene (HDPE) into existing conduit and 260,000 ft. of fiber optic cable into newly-placed underground conduit. This placement includes 105,000 ft. of fabric innnerduct inside of newly-placed conduit. On the island of St. Croix, VIPFA/viNGN will install 36.6 miles of aerial plant. As a result, there will be 193,241 ft. of aerial placement of cables. In addition, VIPFA/viNGN will install 130,000 ft. of High Density Polyethylene (HDPE) into existing conduit and 300,000 ft. of fiber optic cable into newly-placed underground conduit. This placement includes 130,000 ft. of fabric innnerduct inside of newly-placed conduit. | N/A | N/A | The VIPFA/viNGN team remains confident that its network will be built-out by July 2013, despite the delays it has experienced to date. The team already purchased a significant portion of the core backbone fiber (288 fiber strand count) required for its network during Quarter 2, CY 2012, and it is currently warehousing it on St. Thomas and St. Croix to ensure that it is immediately available for deployment. During Quarter 3, CY 2012, the team received the remainder of its fiber needs. A large portion of the network management equipment has been procured and will be prepared for testing and staging for placement once the FAPs are completed. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2013. | 0 | 0 | 0 | VIPFA/viNGN has no wholesale service contracts, as a result there are no signed agreements to provide services to broadband wholesalers. In the interim, VIPFA/viNGN is purchasing wholesale service from Global Crossing/Level 3 and AT&T. The lease agreement with AT&T for the SONET OC-48 was signed during Quarter 2, CY 2012. VIPFA/viNGN has not signed any agreements with retail service providers/last mile providers; however, the team continues to engage the local community of anchor tenants and last mile providers in discussions. These conversations have been conducted on an individual basis, as well as under the aegis of the Broadband Coalition. Broadband Coalition meetings and technical conferences are designed to support a range of market research activities and to solicit direct feedback as VIPFA/viNGN formulates its range of products, prices, terms and conditions for the services and products to be offered. Based on discussions held to date with last mile providers, viNGN has received indications of interest to enter into agreements. | VIPFA/viNGN plans to build out a high speed, open access, fiber optic network infrastructure which will provide Ethernet transport for service providers and, by extension, to Community Anchor Institutions / anchor tenants territory-wide. VIPFA/viNGN's goal is to serve as a Middle Mile provider, and the only service the viNGN team anticipates providing is wholesale broadband. This operational model is reinforced by viNGN's enabling legislation. The main goal of this build out is to provide reliable, affordable broadband services to ISPs and other service providers throughout the Territory. The viNGN management team believes that giving access to relatively inexpensive, reliable bandwidth to ISPs and other retail service providers will help to increase GDP (Gross Domestic Product) growth by, in turn, giving commercial and residential consumers inexpensive, reliable broadband access. The infrastructure will be deployed to ISPs, other last mile providers and Community Anchor Institutions / anchor tenants (such as government departments and agencies, non-profit organizations, educational institutions, public safety entities, healthcare delivery providers, and other key community stakeholders), many of which are located in economically distressed areas. The team is currently testing its network and conducting market research to define its menu of service and product offerings; thus, it is unable to share specific pricing plans at this time. | NOT APPLICABLE | 0 | 0 | 0 | 0 | N/A | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that the VIPFA/viNGN team has not completed the build-out of the network segments that will enable viNGN to provide improved access to providers; however, as the FAP construction is completed during the remaining quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline. Performance against the Baseline is expected to improve during Quarter 1, CY 2013 and be in line with the Baseline by the end of Quarter 2, CY 2013. | N/A | Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available; however, speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; Tier 3 and Tier 4 providers are expected to receive 5,000 Mbps. At this time, viNGN estimates that it will service two (2) providers at Tier 1, two (2) providers at Tier 2, two (2) providers at Tier 3 and one (1) provider at Tier 4. | 0 | 0 | 0 | 0 | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that the VIPFA/viNGN team has not completed the build-out of the network segments that will enable viNGN to provide improved access to providers; however, as the FAP construction is completed during the remaining quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline. Performance against the Baseline is expected to improve during Quarter 1, CY 2013 and be in line with the Baseline by the end of Quarter 2, CY 2013. | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that the VIPFA/viNGN team has not completed the build-out of the network segments that will enable viNGN to provide improved access to providers; however, as the FAP construction is completed during the remaining quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline. Performance against the Baseline is expected to improve during Quarter 1, CY 2013 and be in line with the Baseline by the end of Quarter 2, CY 2013. | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that the VIPFA/viNGN team has not completed the build-out of the network segments that will enable viNGN to provide improved access to providers; however, as the FAP construction is completed during the remaining quarters, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline. Performance against the Baseline is expected to improve during Quarter 1, CY 2013 and be in line with the Baseline by the end of Quarter 2, CY 2013. | Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available; however, speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; Tier 3 and Tier 4 providers are expected to receive 5,000 Mbps. At this time, viNGN estimates that it will service two (2) providers at Tier 1, two (2) providers at Tier 2, two (2) providers at Tier 3 and one (1) provider at Tier 4. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Any special offerings will be determined, based upon the results of market research on optimal pricing and the optimal range of services to be offered. At this time, there is no special offering being proposed. | FALSE | NOT APPLICABLE | The VIPFA/viNGN team plans to accomplish the following during Quarter 1, CY 2013: â€¢ Estimate Miles Deployed for Quarter 1 CY, 2013 Activities 16.4 St. Thomas Underground Backbone 17.7 St. Croix Underground Backbone 12.2 St. Croix Aerial Fiber Installation 14.9 St. Thomas, St. John & Water Island Aerial Fiber Installation 14.8 St. Croix Lateral Drop Aerial 9.5 St. Croix Lateral Drop pulled through underground 0.2 Direct Bury Lateral Drop Underground St. Croix 15.8 St. Thomas, St. John & Water Island Lateral Drop Aerial 3.5 St. Thomas Lateral Drop pulled through underground 0.6 Direct Bury Lateral Drop Underground St. Thomas, St. John & Water Island 105.6 Total Deployed Miles VIPFA/viNGN trenched approximately 7 miles during Quarter 4, CY 2012, which was limited due to the impact of the holiday seasons during November 2012 and December 2012. VIPFA/viNGN expects to trench the remaining 39 miles with four trenching teams operating simultaneously, two on St. Thomas an two on St. Croix. In addition, VIPFA/viNGN plans to connect its first two CAIs and enter into the first agreement with a last mile provider, likely for off-island internet transit and possibly for CAI pass-through buys, all during late Quarter 1, CY 2013/early Quarter 2, CY 2013. â€¢ VIPFA/viNGN anticipates the installation of two CAIs by the end of Quarter 1, CY 2013. As noted in the Project Indicators (5b), this will be accomplished, using wholesale services purchased from Global Crossing/Level 3 and AT&T; â€¢ VIPFA/viNGN has no signed agreements to provide services to broadband wholesalers. VIPFA/viNGN is purchasing wholesale service from Global Crossing/Level 3 and AT&T. The lease agreement with AT&T for the SONET OC-48 was signed during Quarter 2, CY 2012. VIPFA/viNGN has also not signed any agreements with retail service providers/last mile providers; however, the team continues to engage the local community of anchor tenants and last mile providers in discussions. These conversations have been conducted on an individual basis, as well as under the aegis of the Broadband Coalition. Broadband Coalition meetings and technical conferences are designed to support a range of market research activities and to solicit direct feedback as VIPFA/viNGN formulates its range of products, prices, terms and conditions for the services and products to be offered. Based on discussions held to date with last mile providers, viNGN has received indications of interest to enter into agreements; â€¢ Release all remaining solicitations for FAP construction and begin construction on the additional FAPs; â€¢ Continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2013; Discussions will also include construction status against the implementation schedule and overall contract terms, approaches to accelerate construction activities and impediments to accelerating progress in the construction schedule; â€¢ Continue to assess the project implementation schedule and the network design to identify ways to speed up the build-out and â€œlighting upâ€ of the network; to reduce network construction and operational costs, including maintenance costs; â€¢ Put in place a contract for inspectors to monitor construction quality during the build-out process on all four islands (St. Thomas, St. Croix, St. John and Water Island); â€¢ Obtain any permits needed due to approved changes; â€¢ Obtain additional environmental assessments and archaeological studies, as needed; â€¢ Participate in Broadband Coalition meetings with Community Anchor Institutions, future viNGN customers and other stakeholders to discuss the status of the network build and to provide updates on the anticipated service offerings and pricing schedule; â€¢ Notify and enter into contract with the selected bidder for the supply of AC/DC power; and â€¢ Issue Letters of Award and Notices to Proceed to selected bidders to supply the generators, racking equipment and related installation work for all FAPs. | Virgin Islands Public Finance Authority | Though the VIPFA/viNGN team remains confident that its network will be built-out by June/July 2013, despite the delays it has experienced to date. The team will continue to work closely with the assigned BTOP program team members to identify ways to speed up the implementation. Discussions will include the experiences from other BTOP grantees that have experienced and/or are experiencing delays in implementation but have identified or developed ways to speed up the infrastructure build. Further, BTOP program team members and VIPFA/viNGN team members plan to coordinate a discussion/discussions with the National Telecommunication and Information Administration (NTIA)'s Director of Minority Telecom Development. VIPFA/viNGN continues to develop its new management and project implementation team. The new team has made significant progress towards assessing the current state of project implementation, including contract negotiations and procurement activities; understanding the technological requirements of the network to be built; re-engaging with key architectural and engineering contractors and key partners; restarting the build out/leasing of the network; conducting testing of its high-speed Carrier Ethernet network and the required network management equipment; coordinating with local government authorities and its key partner, the U.S. Virgin Islands Water and Power Authority (WAPA); gaining a more in depth understanding of its four BTOP programs, including the approved gr | Though the VIPFA/viNGN team remains confident that its network will be built-out by July 2013, despite the delays it has experienced to date, the team will continue to work closely with the assigned BTOP program and grant team members to identify ways to speed up the implementation. Discussions will include the experiences from other BTOP grantees who have experienced and/or are experiencing delays in implementation but have identified or developed ways to speed up the infrastructure build. Further, BTOP program team members and VIPFA/viNGN team members plan to coordinate a discussion/discussions with the National Telecommunication and Information Administration (NTIA)'s Director of Minority Telecom Development. VIPFA/viNGN continues to build its new management and project implementation team. The new team has made significant progress towards assessing the current state of project implementation, including contract negotiations and procurement activities; understanding the technological requirements of the network to be built; re-engaging with key architectural and engineering contractors and key partners; restarting the build out/leasing of the network; coordinating with local government departments and agencies and its key partner, the U.S. Virgin Islands Water and Power Authority (WAPA); gaining a more in depth understanding of its four BTOP programs, including the approved grant and local match budgets, the implementation schedules, the approved applications and the g | TRUE
NT10BIX5570096 | 2013 | Q1 | Q1 - 2013 | The Virgin Islands Public Finance Authority (VIPFA)/Virgin Islands Next Generation Network (viNGN) team continued to make progress with its network build out during Quarter 1, Calendar Year (CY) 2013. During Quarter 1, CY 2013, VIPFA/viNGN continued trenching operations in preparation for fiber optic cable installation on St. Thomas and St. Croix. As of March 31, 2013, VIPFA/viNGN trenched approximately 32 miles and plans to complete the remaining 12.5 miles of trenching operations, with four trenching teams operating simultaneously (two on St. Thomas and two on St. Croix). As of March 31, 2013, 80% of the trenching was completed on St. Thomas, and nearly 90% of the trenching was completed on St. Croix. Trenching activities began on November 12, 2012 and were divided into four segments (two on St. Thomas and two on St. Croix). These trenches will contain the main fiber/backbone fiber for the respective islands. During Quarter 1, CY 2013, VIPFA/viNGN finalized the contracts for lateral drops installations; the supply of lateral drop hardware; splicing material supply; aerial fiber installation services on St. Croix; fiber splicing, which includes fiber pulling and splicing through underground traffic-rated vaults for the entire network; and, the supply of traffic-rated vaults. Aerial and underground fiber installation commenced on both St. Croix and St. Thomas during Quarter 1, CY 2013. The team installed 6,900 ft. of aerial fiber and pulled 63,358 ft. of innerduct on St. Croix. On St. Thomas, aerial fiber hardware and innerduct were installed in preparation for aerial fiber installation. As of the end of CY 2012, the construction of three FAPs (Fiber Access Points) was completed. Construction of the two SuperFAPs, one on St. Thomas and one on St. Croix were completed and will be the access points for the AT&T Sonnet OC-48 connection between islands. The third FAP construction, which is a Type B FAP, was completed on St. Croix. It is located near the U.S. Virgin Islands Department of Public Works-Queens Crossing location on St. Croix. This FAP serves one of the largest clusters of Community Anchor Institutions (CAIs) and Public Computer Centers (PCCs). For example, the U.S. Virgin Islands Department of Public Works, the Girls Scouts, the U.S. Virgin Islands Department of Labor, the U.S. Virgin Islands Department of Education's Warehouse and the islands only Youth Rehabilitation Center (YRC). On St. Croix at Estate La Reine, a fourth FAP is under construction. The construction of this Type C FAP is nearly 90% complete as of March 31, 2013. VIPFA/viNGN received proposals during March 2013 for the construction of seven additional FAPs and selected a contractor. In addition, VIPFA/viNGN executed contracts for four additional FAPs with three contractors. Contracts for FAP DC power/batteries, FAP generators and FAP equipment and installations and the OSS/BSS system were also signed. Also, effective March 29, 2013, NTIA and NOAA approved a Budget Modification/Reallocation. The total approved budget, including the Federal Share and the Recipient Share, remained the same as the initial approved budget; however, costs were reallocated between budget line items, resulting in a $56,311 reduction in the total dollar amount of the match, which came out of the Architectural and Engineering Fees budget line item. On a percentage basis, the recorded match percentage (42.8%) of total expenditures exceeds the required match percentage of the total budget (33.3%) by nearly 10%. Further, during Quarter 1, CY 2013, a Tree Boa training was held for VIPFA/viNGN staff and its contractors who will install aerial fiber on the east end side of St. Thomas. The Tree Boa's only known habitat is on the eastern end of St. Thomas. | 0 | 3353 | 0 | 0 | 1 | 0 | 0 | 0 | As of March 31, 2013, VIPFA/viNGN trenched approximately 32 miles in total on St. Thomas and St. Croix. VIPFA/viNGN plans to complete the remaining 12.5 miles of trenching, with four trenching teams operating simultaneously. Some critical items received as a result of the procurement process are Maxcell fabric innerduct, aerial construction pole hardware and traffic rated vaults. As of the end of Quarter 4, CY 2012, the construction of three FAPs was completed. The two Super FAPs, one on St. Thomas and one on St. Croix, will be the access points for the AT&T Sonnet OC-48 connection between islands. The third FAP construction, a Type B FAP, was completed on St. Croix. At Estate La Reine on St. Croix, a fourth FAP is under construction. The construction of this Type C FAP is about 90% complete as of March 31, 2013. During Quarter 1, CY 2013, on Croix and on St. Thomas, aerial and underground fiber installation commenced during March, 2013. The VIPFA/viNGN team will coordinate with contractors to safely work on accelerated schedules and actively identify and create ways to speed up the implementation and to continue to coordinate construction activities to close the gap against the Baseline during CY 2013. | VIPFA/viNGN team executed a fifteen (15) year Indefeasible Right of Use (IRU) and co-location agreements for New York City and Miami with Global Crossing/Level 3 during CY 2011. In addition, the lease agreement with AT&T for the SONET OC-48 to connect St. Thomas and St. Croix was executed during Quarter 2, CY 2012. AT&T SONET OC-48 Link activation was initiated during Quarter 1, CY 2013. It takes 60 days to 90 days for activation; thus, the link is expected to be available for use during late Quarter 2, CY 2013 or early Quarter 3, CY 2013. With this addition, the team expects to report additional new network miles under lease during late Quarter 2, CY 2013 or early Quarter 3, CY 2013. | VIPFA/viNGN trenched approximately 32 miles as of March 31, 2013. VIPFA/viNGN plans to trench the remaining 12.5 miles during Quarter 2, CY 2013, with four trenching team operating simultaneously. The team also began to install new conduit and to pull innerduct, in order to run new fiber optic cable. | N/A | VIPFA/viNGN installed 6,900 ft. of aerial fiber and pulled 63,358 ft. of innerduct on St. Croix. On St. Thomas, aerial fiber hardware and innerduct were installed in preparation for aerial fiber installation. Also, VIPFA/viNGN trenched approximately 32 miles as of March 31, 2013. VIPFA/viNGN expects to trench the remaining 12.5 miles during Quarter 2, CY 2013. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during Quarter 2, CY 2013. | N/A | N/A | A large portion of the network management equipment has been procured and will be prepared for testing and staging for placement once the FAPs are completed. Solicitations for the remaining equipment will be issued during Quarter 2, CY 2013. During Quarter 1, CY 2013, a contractor was selected to construct another seven FAPs on St. Thomas. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during Quarter 2, CY 2013. | 2 | 0 | 32 | VIPFA/viNGN has two wholesale service contracts, one for 15 years with Global Crossing/Level 3 and the other for 1 year with AT&T, both providing leased fiber miles to viNGN. As a result, the average term of signed agreements to date (in quarters) is 32. VIPFA/viNGN has not signed any agreements with retail service providers/last mile providers; however, the team continues to engage the local community of anchor tenants and last mile providers in discussions. These conversations have been conducted on an individual basis, as well as under the aegis of the Broadband Coalition. Broadband Coalition meetings and technical conferences are designed to support a range of market research activities and to solicit direct feedback as VIPFA/viNGN formulates its range of products, prices, terms and conditions for the services and products to be offered. Based on discussions held to date with last mile providers, viNGN has received indications of interest to enter into agreements. | VIPFA/viNGN plans to build out a high speed, open access, fiber optic network infrastructure which will provide Ethernet transport for service providers and, by extension, to Community Anchor Institutions / anchor tenants territory-wide. VIPFA/viNGN's goal is to serve as a Middle Mile provider, offering wholesale broadband bandwidth. The main goal of this build out is to provide reliable, affordable broadband services to ISPs and other service providers throughout the Territory. The viNGN management team believes that giving access to relatively inexpensive, reliable bandwidth to ISPs and other retail service providers will help to increase GDP (Gross Domestic Product) growth by, in turn, giving commercial and residential consumers inexpensive, reliable broadband access. The infrastructure will be deployed to ISPs, other last mile providers and Community Anchor Institutions / anchor tenants (such as government departments and agencies, non-profit organizations, educational institutions, public safety entities, healthcare delivery providers, and other key community stakeholders), many of which are located in economically distressed areas. The team continues to test its network and conduct market research to define its menu of service and product offerings; thus, it is unable to share specific pricing plans at this time. | NOT APPLICABLE | 0 | 0 | 0 | 0 | No variance from the Baseline Indicator target | Refer to the response to Section 5b above in this report. Under performance against the Baseline Indicator is due to the fact that the build-out of the network segments that will enable VIPFA/viNGN to provide improved access to providers has not been completed. However, as the FAP construction is completed, the Community Anchor Institutions are connected and all backbone nodes equipment are installed, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline. Performance against the Baseline is expected to improve during Quarter 2, CY 2013. | N/A | Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available; however, speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; Tier 3 and Tier 4 providers are expected to receive 500 Mbps. At this time, viNGN estimates that it will service two (2) providers at Tier 1, two (2) providers at Tier 2, two (2) providers at Tier 3 and one (1) provider at Tier 4. | 0 | 0 | 0 | 0 | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that VIPFA/viNGN has not completed the build-out of the network segments that will enable viNGN to connect CAIs; however, as the network is completed, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will continue to seek ways to coordinate with contractors to work on accelerating the schedules and actively identifying and creating ways to speed up the project implementation. VIPFA/viNGN will also continue to coordinate the construction activities to close the project gap against the Baseline. Performance against the Baseline is expected to improve during Quarter 2, CY 2013. | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that VIPFA/viNGN has not completed the build-out of the network segments that will enable viNGN to connect CAIs; however, as the network is completed, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will continue to seek ways to coordinate with contractors to work on accelerating the schedules and actively identifying and creating ways to speed up the project implementation. VIPFA/viNGN will also continue to coordinate the construction activities to close the project gap against the Baseline. Performance against the Baseline is expected to improve during Quarter 2, CY 2013. | Refer to the response to Section 5b above in this report. Under performance against this Baseline Indicator is due to the fact that VIPFA/viNGN has not completed the build-out of the network segments that will enable viNGN to connect CAIs; however, as the network is completed, the team will be positioned to come in line with the Baseline Indicator targets. The VIPFA/viNGN team will continue to seek ways to coordinate with contractors to work on accelerating the schedules and actively identifying and creating ways to speed up the project implementation. VIPFA/viNGN will also continue to coordinate the construction activities to close the project gap against the Baseline. Performance against the Baseline is expected to improve during Quarter 2, CY 2013. | Until the network build is completed and tested, viNGN will not be able to accurately identify the speeds that will be available; however, speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; Tier 3 and Tier 4 providers are expected to receive 500 Mbps. At this time, viNGN estimates that it will service two (2) providers at Tier 1, two (2) providers at Tier 2, two (2) providers at Tier 3 and one (1) provider at Tier 4. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Any special offerings will be determined, based upon the results of market research on optimal pricing and the optimal range of services to be offered. At this time, there is no special offering being proposed. | FALSE | NOT APPLICABLE | The VIPFA/viNGN team plans to finalize the following during Quarter 2, CY 2013: â€¢ After trenching approximately 32 miles as of March 31, 2013, the team expects to trench the remaining 12.5 miles, with four trenching teams operating simultaneously, two on St. Thomas and two on St. Croix, during Quarter 2, CY 2013. â€¢ Estimate of Miles Deployed as of Quarter 2, CY 2013 Activities 16.4 St. Thomas Underground Backbone 17.7 St. Croix Underground Backbone 11.2 St. Croix Aerial Fiber Installation 14.9 St. Thomas, St. John & Water Island Aerial Fiber Installation 14.8 St. Croix Lateral Drop Aerial 9.5 St. Croix Lateral Drop pulled through underground 0.2 Direct Bury Lateral Drop Underground St. Croix 15.8 St. Thomas, St. John & Water Island Lateral Drop Aerial 3.5 St. Thomas Lateral Drop pulled through underground 0.6 Direct Bury Lateral Drop Underground St. Thomas, St. John & Water Island 104.6 Total Deployed Miles â€¢ Issue all remaining solicitations for FAP construction on St. Thomas and begin construction on the additional FAPs. â€¢ Notify selected bidders/proposers of awards made and enter into contracts with selected bidders/proposers for Fiber Management Software, additional FAP construction, and Network Operations Center Equipment. â€¢ Issue Notice(s) to Proceed to selected bidders/proposers for FAP construction on St. Thomas. â€¢ Issue solicitations for FAP construction on St. John. â€¢ Continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the implementation and to improve the coordination of construction activities to close the gap against the Baseline during CY 2013; Discussions will also include construction status against the implementation schedule and overall contract terms, approaches to accelerate construction activities and impediments to accelerating progress in the construction schedule. â€¢ Continue to assess the project implementation schedule and the network design to identify ways to speed up the build-out and â€œlighting upâ€ of the network and to reduce network construction, operational and maintenance costs. â€¢ Obtain any additional environmental assessments or archaeological studies that may be required. â€¢ Participate in Broadband Coalition meetings that may be scheduled with Community Anchor Institutions, future VIPFA/viNGN customers and other stakeholders to discuss the status of the network build and to provide updates on the anticipated service offerings and pricing schedule. The team expects to begin to connect CAIs during Quarter 3, CY 2013 and to enter into agreements with last mile providers after the network is built. | Virgin Islands Public Finance Authority | The VIPFA/viNGN team is working aggressively to complete the build out. The team will continue to work closely with the assigned BTOP program team members to identify ways to speed up the implementation. Discussions will include the experiences from other BTOP grantees that have experienced and/or experiencing delays in implementation but have identified or developed ways to speed up the infrastructure build. VIPFA/viNGN continues to develop its management and project implementation team. The new team has made significant progress towards assessing the current state of project implementation, including contract negotiations and procurement activities; understanding the technological requirements of the network to be built; re-engaging with key architectural and engineering contractors and key partners; restarting the build out/leasing of the network; conducting testing of its high-speed Carrier Ethernet network and the requirement network management equipment; gaining a more in depth understanding of its four BTOP programs, including the approved grant and local match budgets, the implementation schedules, the approved applications and the grant award agreements for each; and training a full complement of new staff. The team will continue to work towards overcoming delays experienced to date by coordinating with its contractors to work on accelerated schedules and to identify and create ways to speed up project activities. For example, VIPFA/viNGN bundled FAPs into one Req | The VIPFA/viNGN team will continue to work closely with the assigned BTOP program team members to identify ways to speed up the implementation. Discussions will include the experiences from other BTOP grantees who have experienced and/or are experiencing delays in implementation but have identified or developed ways to speed up the infrastructure build. Further, BTOP program team members and VIPFA/viNGN team members plan to coordinate a discussion/discussions with the National Telecommunication and Information Administration (NTIA)'s Director of Minority Telecom Development. VIPFA/viNGN continues to build its new management and project implementation team. The new team has made significant progress towards assessing the current state of project implementation, including contract negotiations and procurement activities; understanding the technological requirements of the network to be built; re-engaging with key architectural and engineering contractors and key partners; restarting the build out/leasing of the network; gaining a more in depth understanding of its four BTOP programs, including the approved grant and local match budgets, the implementation schedules, the approved applications and the grant award agreements for each; and, training a full complement of new staff. The team will need to hire and train additional personnel to operate the network. The VIPFA/viNGN team is overcoming the delays experienced to date by coordinating with its contractors to work on acce | TRUE
NT10BIX5570096 | 2013 | Q2 | Q2 - 2013 | The Virgin Islands Public Finance Authority (VIPFA)/Virgin Islands Next Generation Network (viNGN) team continued to make tremendous progress with its network build-out during Quarter 2, Calendar Year (CY) 2013. All backbone trenching operations (i.e. all four segments) were completed during Quarter 2, CY 2013 in preparation for underground backbone fiber optic cable installation on St. Thomas and St. Croix, a critical performance milestone. With the completion of trenching and continuing successful collaboration with the team's key partner, the U.S. Virgin Islands Water and Power Authority (WAPA), to ensure that utility poles are ready, another key milestone, VIPFA/viNGN began its underground backbone, aerial backbone, and later fiber installations which resulted in the following significant progress: On St. Croix: Aerial Backbone Fiber Installed = 20.0 miles Underground Backbone Fiber Installed = 27.9 miles Lateral Fiber Installed = 0.0 miles Total Fiber Installed on St. Croix during Quarter 2, CY 2013 = 47.9 miles On St. Thomas and on Water Islands: Aerial Backbone Fiber Installed = 14.4 miles Underground Backbone Fiber Installed = 6.7 miles Lateral Fiber Installed = 13.9 miles Total Fiber Installed on St. Thomas and Water Islands = 35.0 miles On St. John: Aerial Backbone Fiber Installed = 5.9 miles Underground Backbone Fiber Installed = 0.0 miles Lateral Fiber Installed = 0.0 miles Total Fiber Installed on St. John = 5.9 miles Cumulative Total Fiber Installed on St. Croix, St. Thomas, Water Island and St. John during Quarter 2, CY 2013: Aerial Backbone Fiber Installed = 40.3 miles Underground Backbone Fiber Installed = 34.6 miles Lateral Fiber Installed = 13.9 miles Cumulative Total Fiber Installed on All Islands = 88.8 miles Further, as of June 30, 2013, the construction of FAP (Fiber/Facility Access Point) STX-05 at Estate La Reine on St. Croix was approximately 90% complete. The brick and mortar construction was 95% complete, while the AC (Air Conditioning) units, racking equipment and DC Power installation were pending. Also, FAP STX-06, located near the John Woodson School, was approximately 85% complete, and FAP STX-12 in Cotton Valley was nearly 80% complete. At FAP STX-06 and FAP STX 12, the Cisco System routers, AC unit, and DC backup power are pending installation. An additional four FAPs were under construction on St. Croix as of June 30, 2013. On St. Thomas, the construction of four (4) FAPs began during Quarter 2, CY 2013, and contractors were selected for the construction of the remaining FAPs on St. Thomas. Construction of the remaining FAPs on St. Thomas by these contractors is expected to begin during Quarter 3, CY 2013. Contractors were also selected to begin construction of FAPs on St. John, starting in Quarter 3, CY 2013. In addition, during Quarter 2, CY 2013, VIPFA/viNGN hired two Network Technicians, one for the St. Thomas/St. John/Water Island District and one for the St. Croix District. The Network Technicians will perform â€œhands onâ€/day-to-day operational surveillance and network management tasks to ensure that the Gigabit Ethernet fiber optic network and its supporting systems and related services are operated/provided and maintained as cost effectively and efficiently as possible. As a result of the progress noted above, the VIPFA/viNGN team was successful in executing its first contract with a last mile provider/Internet Service Provider (ISP)/retail service provider during Quarter 2, CY 2013. The contract is with Orbitel, a new market entrant which expects to offer cable television and Internet service to the general population in the U.S. Virgin Islands. The team also held discussions and began negotiations with other last mile providers/Internet Service Providers (ISPs)/retail service providers during Quarter 2, CY 2013. Moreover, NTIA and NOAA conducted a follow-up Site Visit during April 2013 and provided positive feedback on the improvements in internal controls and the overall management and implementation of the CCI program by the new VIPFA/viNGN team. | 89 | 3353 | 0 | 0 | 89 | 0 | 0 | 0 | During Quarter 2, CY 2013, VIPFA/viNGN completed backbone trenching operations in preparation for underground backbone fiber optic cable installation on St. Thomas and St. Croix. With the completion of the trenching, a key milestone, a cumulative total of 88.8 miles of underground backbone, aerial backbone and later fiber installations across St. Croix, St. Thomas, Water Island and St. John were deployed during Quarter 2, CY 2013. All remaining new network miles (i.e. 184.4 miles) are expected to be deployed by December 31, 2013. | With the leasing of new network miles from Level 3 and AT&T, the VIPFA/viNGN has met its immediate plans for new leased miles. | The VIPFA/viNGN does not anticipate that it will upgrade network miles. All network miles are expected to be new installations of fiber or new leases of network miles. | N/A | During Quarter 2, CY 2013, VIPFA/viNGN completed backbone trenching operations in preparation for underground backbone fiber optic cable installation on St. Thomas and St. Croix. With the completion of the trenching, a key milestone, a cumulative total of 88.8 miles of underground backbone, aerial backbone and later fiber installations across St. Croix, St. Thomas, Water Island and St. John were deployed during Quarter 2, CY 2013. All remaining miles of new fiber (184.4) are expected to be deployed by December 31, 2013. | N/A | N/A | All interconnection points will be new. With the completion of the SuperFAPs during CY 2012, final testing and staging for placement of the routers and switches were completed during Quarter 2, CY 2013. With the staging and initial testing completed, the SuperFAP on St. Croix, along with the connection of one CAI, is expected to "come on line" during Quarter 3, CY 2013. As the construction of FAPs is completed, the routers and switches will be installed, final testing and activation will begin to bring the network fully on line. CAIs will be connected as FAPs are connected. | 3 | 3 | 32 | VIPFA/viNGN has two broadband wholesale service contracts, one for 15 years with Global Crossing/Level 3 and the other for 1 year with AT&T, both providing leased fiber miles to viNGN. As a result, the average term of signed agreements to date (in quarters) is 32. The VIPFA/viNGN team was successful in executing its first service contract with a last mile provider/Internet Service Provider (ISP)/retail service provider during Quarter 2, CY 2013. The contract is with Orbitel, a new market entrant which expects to offer cable television and Internet service to the general population in the U.S. Virgin Islands. | VIPFA/viNGN is building a high speed, open access, 100% fiber optic network which will provide inexpensive, high speed, reliable Ethernet transport to service providers and, by extension, to Community Anchor Institutions (such as government departments and agencies, non-profit organizations, educational institutions, public safety entities, healthcare delivery providers, and other key community stakeholders). VIPFA/viNGN's goal is to serve as a Middle Mile provider, primarily offering wholesale broadband bandwidth on-net (i.e. within the U.S.V.I.) and off-net (i.e. outside of the U.S.V.I.) through a variety of service offerings, starting with 100 Megabit, 1 Gigabit and 10 Gigabit bandwidth plans; Multiprotocol Label Switching (MPLS)/Virtual Private Network (VPN) service to the U.S.; and, Transport Aggregation services. The team continues to conduct market research to define its menu of service/product offerings and is not publicizing pricing plans at this time. | NOT APPLICABLE | 3 | 0 | 0 | 0 | Refer to the response to Questions 5a and 5b above. With the signing of 1 agreement with a last mile provider (Orbitel)and the signing of 2 agreements with broadband wholesalers to lease network miles (Level 3 and AT&T), the VIPFA/viNGN team has exceeded the Baseline Indicator target of 2. Though the network build-out is not complete, the VIPFA/viNGN team has agreements in place to allow it to connect its network through these service providers. | All agreements will result in the provisioning of new access. | N/A | Until the network build is completed and is fully tested, viNGN will not be able to accurately identify the speeds that will be available; however, speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; Tier 3 and Tier 4 providers are expected to receive up to 500 Mbps. | 0 | 0 | 0 | 0 | Under performance against this Baseline Indicator is due to the fact that VIPFA/viNGN has not completed the construction and connections of the FAPs and the build-out of other portions of the network that will enable viNGN to connect CAIs. As FAPs are connected and other portions of the network are built out, the team will be positioned to come in line with the Baseline Indicator targets. CAI connections are expected to begin during Quarter 3, CY 2013, and all FAP construction and connections are expected to be completed by December 31, 2013. | Under performance against this Baseline Indicator is due to the fact that VIPFA/viNGN has not completed the construction and connections of the FAPs and the build-out of other portions of the network that will enable viNGN to connect CAIs. As FAPs are connected and other portions of the network are built out, the team will be positioned to come in line with the Baseline Indicator targets. CAI connections are expected to begin during Quarter 3, CY 2013, and all FAP construction and connections are expected to be completed by December 31, 2013. | All subscribers will receive new access. | Until the network build is completed and is fully tested, viNGN will not be able to accurately identify the speeds that will be available; however, speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; Tier 3 and Tier 4 providers are expected to receive up to 500 Mbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time, there is no special offering being proposed. Any special offerings will be determined, based upon the results of market research on optimal pricing and the optimal range of services to be offered. | FALSE | NOT APPLICABLE | The VIPFA/viNGN team plans to finalize the following during Quarter 3, CY 2013: - Estimate of New Fiber Miles To-Be-Installed/Deployed during Quarter 3, CY 2013: Cumulative Total Fiber To-Be-Installed on St. Croix, St. Thomas, Water Island and St. John during Quarter 3, CY 2013: Aerial Backbone Fiber To-Be-Installed = 13.9 miles Underground Backbone Fiber To-Be-Installed = 18.8 miles Lateral Fiber To-Be-Installed = 62.6 miles Cumulative Total Fiber To-Be-Installed on All Islands = 95.3 miles - Estimate of CAIs To-Be-Connected during Quarter 3, CY 2013: On St. Croix = 66 CAIs On Thomas = 54 CAIs On St. John = 0 CAIs Cumulative Total Number of CAIs To-Be-Connected = 120 CAIs - Estimate of Broadband Wholesaler or Last Mile Provider Agreements To-Be-Signed during Quarter 3, CY 2013 = 2 The VIPFA/viNGN team also plans to finalize the following during Quarter 3, CY 2013: â€¢ Finalize and submit its official request to NTIA and NOAA for a no-cost project extension through December 31, 2013 and the related budget reallocations needed to carry out project activities during the extension period; â€¢ Continue the construction of FAPs (Fiber/Facility Access Points) and the installation of fiber patch panels, AC (Air Conditioning) units, racking equipment, and DC Power on St. Croix and St. Thomas; â€¢ After FAPs are built, install routers and switches to await the final connections to the aerial or underground fiber to bring the network on line; â€¢ Issue Notice(s) to Proceed to selected contractors for FAP construction on St. Thomas, St. Croix and St. John and begin construction of the additional FAPs; â€¢ Revise the procurement solicitations for the Fiber Management Software, Network Operations Center (NOC) Equipment and IP communications systems; â€¢ Continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the construction activities; â€¢ Continue to assess the project implementation schedule and the network design to identify ways to speed up the build-out and â€œlighting upâ€ of the network and to reduce network construction, operational and maintenance costs; and â€¢ Participate in Broadband Coalition meetings that may be scheduled with Community Anchor Institutions, future VIPFA/viNGN customers and other stakeholders to discuss the status of the network build and to provide updates on the anticipated service offerings and pricing schedule. | Virgin Islands Public Finance Authority | The new VIPFA/viNGN team has successfully increased the speed of implementation and will continue to work hard to further speed up the implementation. However, the team has experienced circumstances that have resulted in the need for a short extension beyond the original project implementation end date of July 31, 2013; thus, the team is working closely with NTIA and NOAA, in an effort to obtain a five (5) month extension through December 31, 2013. During the grant award extension period, the team will work to complete the construction of the remaining FAPs, to complete testing of the equipment in the FAPs, to connect the CAIs, to test the resulting network connections, to complete the installation of the Operating Support System/Business Support System (OSS/BSS) and to complete the testing of the OSS/BSS, using unspent grant funding. The VIPFA/viNGN team will continue to engage in active oversight of all project activities during the extension period. The VIPFA/viNGN team continues to coordinate with its contractors to work on accelerated schedules and to identify and create ways to speed up project activities. This includes any guidance that is received from BTOP program team members, based on the experiences from other BTOP grantees that have experienced and/or are experiencing delays in implementation but have identified or developed ways to speed up the infrastructure build. --------------------------------------------------------------------------------------------- | Refer to the response in Question #3 above, as it relates to challenges experienced during Quarter 2, CY 2013. Another challenge is that the next two quarters are in the height of the Atlantic Ocean's Hurricane Season, i.e. an active tropical storm season, during which heavy rain/flooding, wind, and lightning typically result in weather-related delays during the course of construction projects. The VIPFA/viNGN team will continue on its accelerated schedule during the good weather periods and ensure that it effectively coordinates with the NTIA/NOAA team, its contractors, and its staff during periods of inclement weather. The VIPFA/viNGN team has successfully overcome the delays experienced to date by closely coordinating with its partners at NTIA, NOAA and WAPA and with its contractors and by focusing its efforts on working on accelerated schedules and continuing to identify and create ways to speed up project activities in all areas of implementation. The team will need NTIA's and NOAA's ongoing support during this period of inclement weather through to the successful build-out of the network. | TRUE
NT10BIX5570096 | 2013 | Q3 | Q3 - 2013 | The Virgin Islands Public Finance Authority (VIPFA)/Virgin Islands Next Generation Network (viNGN) team continued to make progress with its network build-out during Quarter 3, Calendar Year (CY) 2013. With the completion of trenching and continuing successful collaboration with key stakeholders, the VIPFA/viNGN team achieved additional major milestones during Quarter 3, CY 2013. The following is a list of the VIPFA/viNGN's major achievements as of September 30, 2013: On St. Croix: Aerial Backbone Fiber Installed = 33.03 miles Underground Backbone Fiber Installed = 30.86 miles Lateral Fiber Installed = 50.18 miles Total Fiber Installed on St. Croix during Quarter 2, CY 2013 = 114.07 miles On St. Thomas, St. John and Water Island: Aerial Backbone Fiber Installed = 33.89 miles Underground Backbone Fiber Installed = 9.76 miles Lateral Fiber Installed = 89.24 miles Total Fiber Installed on St. Thomas and Water Islands = 132.89 miles Cumulative Total Fiber Installed on St. Croix, St. Thomas, Water Island and St. John during Quarter 3, CY 2013: Aerial Backbone Fiber Installed = 66.92 miles Underground Backbone Fiber Installed = 40.62 miles Lateral Fiber Installed = 139.42 miles Cumulative Total Fiber Installed on All Islands = 246.96 miles As of September 30, 2013, the construction of two Type C FAPs (Facility Access Points) on St. Croix (Estate La Reine FAP STX-05 and Woodson/VI Corporate Lands FAP STX-06) is 100% completed. Furthermore, construction of the Estate Diamond/The Boys' and Girls' Club FAP STX-03, the University of the Virgin Islands (UVI) FAP STX-04, and the Roebuck Industrial Park FAP STX-16 FAP is approximately 95% complete, and construction of the Cotton Valley FAP STX-12 is approximately 90% complete. Additionally, the construction of the La Grande Princess/U.S. Virgin Islands Department of Education FAP STX-07 is approximately 75% complete, the U.S. Virgin Islands Water and Power Authority (WAPA) Richmond FAP STX-17 is approximately 15% complete, and the Juan Luis Hospital FAP STX-15 is approximately 10% complete. Also, as of September 30, 2013, on St. Thomas and St. John, the construction of Cruz Bay FAP STJ-01 and of the Myrah Keating Medical Center FAP STJ-02 is 100% complete. The construction of the Roy Schneider Hospital FAP STT-12, Eudora Kean High School FAP STT-09 and Rt. 10 & 32/Nadir FAP STT-10 is approximately 95% complete, and the Fort Mylner FAP STT-11 and the U.S. Virgin Islands Department of Public Works (DPW) Nisky Center FAP STT-16 are approximately 65% complete. Finally, the University of the Virgin Islands (UVI) FAP STT-02 is approximately 55% complete, and the Havensight/West Indian Company Limited (WICO) FAP STT-13 and the Dorothea FAP STT-05 are approximately 10% complete. With the above-referenced FAPs under construction and the last contract for FAP construction signed (i.e. for Veteranâ€™s Drive FAP STT-14), all remaining FAP construction is still expected to be completed during Quarter 4, CY 2013. The VIPFA/viNGN team also connected its first Community Anchor Institution, the U.S. Virgin Islands Department of Planning and Natural Resources' (DPNR) Althalie McFarlane Petersen Library, in Frederiksted, St. Croix, which is also one of VIPFA/viNGN's BTOP-funded Public Computer Centers, a PCC. During Quarter 3, CY 2013, VIPFA/viNGN also hired a Network Engineer. The Network Engineer will support service provider network implementation and manage the Internet Protocol Platforms (IP), utilizing the Cisco core switches and routers. He will also work with the lead Network Manager of network operations and resolve network issues. As part of his duties when working with the Network Manager, he will develop, design and approve technologies to accommodate demands for growth and new services. This includes the creation of network test plans and the publication of reports for peer review. In some special cases, the Network Engineer will provide cost data to be used to create budgets for the implementation of designs and technologies. The end result to which he will monitor and control project expenditures, define problems encountered, prepare progress reports and provide recommended solutions to management. In addition, during Quarter 3, CY 2013, the VIPFA/viNGN team executed its second Master Services Agreement (MSA) with a local ISP, i.e. SMARTNET. SMARTNET is already offering Internet service to some of the Community Anchor Institutions and also plans to offer network monitoring, VPN (Virtual Private Network) solutions, MPLS (Multiprotocol Label Switching) Network Engineering, VOIP (Voice over Internet Protocol) phone systems and various other managed information technology services. Further, the VIPFA/viNGN team obtained the approval from NTIA and NOAA for a no-cost extension of its grant award agreement through December 31, 2013. | 247 | 3353 | 0 | 0 | 247 | 0 | 0 | 4 | As of September 30, 2013, a cumulative total of 246.96 miles of underground backbone, aerial backbone and lateral fiber was installed across St. Croix, St. Thomas, Water Island and St. John. The number of new network miles deployed during Quarter 3, CY 2013 was 158.16. | With the leasing of new network miles from Level 3 and AT&T, the VIPFA/viNGN has met its immediate plans for new leased miles. | The VIPFA/viNGN does not anticipate that it will upgrade network miles. All network miles are expected to be new installations of fiber or new leases of network miles. | N/A | As of September 30, 2013, a cumulative total of 246.96 miles of of underground backbone, aerial backbone and lateral fiber was installed across St. Croix, St. Thomas, Water Island and St. John. The number of new network miles deployed during Quarter 3, CY 2013 was 158.16. | N/A | N/A | All interconnection points are new and are considered from point to point. During Quarter 3, CY 2013, the VIPFA/viNGN team activated connections through Level 3 in New York, Level 3 in Miami, the SuperFAP STX-02 and DPNR's Althalie McFarlane Petersen Library in Frederiksted, St. Croix, the latter which is a CAI and PCC. | 4 | 4 | 18 | VIPFA/viNGN has two broadband wholesale service contracts, one for 15 years with Global Crossing/Level 3 and the other for 1 year with AT&T, both providing leased fiber miles to viNGN. In addition, VIPFA/viNGN has Master Services Agreements (MSAs) with two ISPs/last mile providers for 1 year each, with a renewal option. The MSAs are with Orbitel and SMARTNET. | VIPFA/viNGN is building a high speed, open access, 100% fiber optic network which will provide inexpensive, high speed, reliable Ethernet transport to service providers and, by extension, to Community Anchor Institutions (such as government departments and agencies, non-profit organizations, educational institutions, public safety entities, healthcare delivery providers, and other key community stakeholders). VIPFA/viNGN's goal is to serve as a Middle Mile provider, primarily offering wholesale broadband bandwidth on-net (i.e. within the U.S.V.I.) and off-net (i.e. outside of the U.S.V.I.) through a variety of service offerings, starting with 100 Megabit, 1 Gigabit and 10 Gigabit bandwidth plans; Multiprotocol Label Switching (MPLS)/Virtual Private Network (VPN) service to the U.S.; and, Transport Aggregation services. The team continues to conduct market research to refine its menu of service/product offerings and is not publishing pricing plans at this time. Please refer to the attached Strictly Confidential and Proprietary related information that is made available to NTIA and NOAA only, as required as a part of this report. The attached related information has been redacted from this report and shall not be made available to the public. | NOT APPLICABLE | 4 | 0 | 0 | 1 | Refer to the response to Questions 5a and 5b above. With the signing of two (2) agreements with last mile providers (i.e. Orbitel and SMARTNET) and the signing of 2 agreements with broadband wholesalers to lease network miles (Level 3 and AT&T), the VIPFA/viNGN team has exceeded the Baseline Indicator target of 2. Though the network build-out is not complete, the VIPFA/viNGN team has agreements in place to allow it to connect its network through these service providers. | All agreements will result in the provisioning of new access. | N/A | Speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; and, Tier 3 and Tier 4 providers are expected to receive up to 500 Mbps. As of September CY 2013, VIPFA/viNGN is providing Tier 2 level service to SMARTNET which is, in turn, servicing DPNR's Althalie McFarlane Petersen Library in Frederiksted, St. Croix, which is a BTOP-funded Community Anchor Institution and PCC. | 1 | 1 | 0 | 1 | Under performance against this Baseline Indicator is due to the fact that VIPFA/viNGN has not completed the construction and connections of the FAPs and the build-out of other portions of the network that will enable viNGN to connect CAIs. As FAPs are connected and other portions of the network are built out, the team will be positioned to come in line with the Baseline Indicator targets. During Quarter 3, CY 2013, the VIPFA/viNGN team connected its first Community Anchor Institution (i.e. DPNR's Althalie McFarlane Petersen Library) in Frederiksted, St. Croix, which is also a BTOP-funded PCC. | As the remaining FAP construction is completed, the equipment racks are installed in the FAPs, Community Anchor Institutions are connected and the remaining backbone node equipment is installed, the team will be positioned to come in line with the Baseline Indicator targets. As the construction of all other FAPs is completed, the routers and switches will be installed, and final testing and activation will bring the network fully on line. VIPFA/viNGN connected its first Community Anchor Institution (i.e. DPNR's Althalie McFarlane Petersen Library) in Frederiksted, St. Croix. | All subscribers will receive new access. As of September CY 2013, VIPFA/viNGN is providing Tier 2 level service to DPNR's Althalie McFarlane Petersen Library through its ISP, SMARTNET. It previously had a low level Tier 4 bandwidth capacity. | Speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; and, Tier 3 and Tier 4 providers are expected to receive up to 500 Mbps. As of September CY 2013, VIPFA/viNGN is providing Tier 2 level service to Althalie McFarlane Petersen Library through its ISP, SMARTNET. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time, there are no special offerings being proposed. Any special offerings will be determined, based upon the results of market research on optimal pricing and the optimal range of services to be offered. | FALSE | NOT APPLICABLE | The VIPFA/viNGN team plans to finalize the following during Quarter 4, CY 2013: - Estimate of New Fiber Miles To-Be-Installed/Deployed during Quarter 4, CY 2013: Cumulative Total Fiber To-Be-Installed on St. Croix, St. Thomas, Water Island and St. John during Quarter 4, CY 2013: 26 miles - Estimate of CAIs To-Be-Connected during Quarter 4, CY 2013: On St. Croix = 132 CAIs On Thomas = 149 CAIs On St. John = 33 CAIs On Water Island = 1 CAI Cumulative Total Number of CAIs To-Be-Connected = 315 CAIs - Estimate of Broadband Wholesaler or Last Mile Provider Agreements To-Be-Signed during Quarter 4, CY 2013 = 1 The VIPFA/viNGN team also plans to finalize the following during Quarter 4, CY 2013: â€¢ Continue the construction of FAPs (Fiber/Facility Access Points) and the installation of fiber patch panels, AC (Air Conditioning) units, racking equipment, and DC Power on St. Croix, St. Thomas and St. John; â€¢ After FAPs are built, install routers and switches to await the final connections to the aerial or underground fiber to bring the network on line; â€¢ Continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the construction activities; â€¢ Continue to assess the project implementation schedule and the network design to identify ways to speed up the build-out and â€œlighting upâ€ of the network and to reduce network construction, operational and maintenance costs; â€¢ Continue to coordinate with the construction contractors, NTIA and NOAA to determine whether a follow-on extension and/or other project modifications will be needed; â€¢ Continue to assess the budget to determine if a budget modification will be needed; â€¢ Continue with Close-Out activities; and â€¢ Participate in viNGN Business and Technology Committee meetings (formerly called Broadband Coalition meetings) that may be scheduled with Community Anchor Institutions, future VIPFA/viNGN customers and other stakeholders to discuss the status of the network build and to provide updates on the anticipated service offerings. | Virgin Islands Public Finance Authority | The VIPFA/viNGN team has successfully increased the speed of implementation and will continue to work hard to further speed up the implementation. However, the team determined that additional time was needed to complete the construction activities and to test the network. NTIA and NOAA has initially approved a no-cost grant award extension from July 31, 2013 to December 31, 2013. During the initial grant award extension period, the team is continuing its efforts to complete the construction of the remaining FAPs, to complete testing of the equipment in the FAPs, to connect the CAIs, to test the resulting network connections, to complete the installation of the Operating Support System/Business Support System (OSS/BSS) and to complete the testing of the OSS/BSS, using unspent grant funding. The VIPFA/viNGN team continued to engage in active oversight of all project activities during the initial extension period and to work closely with its contractors to determine whether a follow-on extension will be necessary. | Refer to the response in Question #3 above, as it relates to challenges experienced during Quarter 3, CY 2013. The team will need to continue to assess the project implementation schedule and coordinate with the construction contractors, NTIA and NOAA to determine whether a follow-on extension, budget modification and/or other project modifications will be needed. Quarter 4, CY 2013 remains within the Atlantic Ocean's Hurricane Season, i.e. an active tropical storm season, during which heavy rain/flooding, wind, and lightning typically result in weather-related delays during the course of construction projects. To date, the season has been mild. The VIPFA/viNGN team will continue on its accelerated schedule during the good weather periods and ensure that it effectively coordinates with the NTIA/NOAA team, its contractors, and its staff during periods of inclement weather. The VIPFA/viNGN team has successfully overcome the delays experienced to date by closely coordinating with its partners at NTIA, NOAA and WAPA and with its contractors and by focusing its efforts on working on accelerated schedules and continuing to identify and create ways to speed up project activities in all areas of implementation, e.g. by focusing on outside construction activities while the weather has remained good. The team will need NTIA's and NOAA's ongoing support during this period of inclement weather through the successful build-out of the network. Also, VIPFA/viNGN intends to maximize | TRUE
NT10BIX5570096 | 2013 | Q4 | Q4 - 2013 | The Virgin Islands Public Finance Authority (VIPFA)/Virgin Islands Next Generation Network (viNGN) team continued to make progress with its network build-out during Quarter 4, Calendar Year (CY) 2013. Through continuing successful coordination with its contractors and collaboration with key stakeholders, the VIPFA/viNGN team achieved the following major milestones as of December 31, 2013: On St. Croix: Aerial Backbone Fiber Installed = 40.13 miles Underground Backbone Fiber Installed = 60.52 miles Lateral Fiber Installed = 86.88 miles Total Fiber Installed on St. Croix = 187.53 miles On St. Thomas, St. John and on Water Islands: Aerial Backbone Fiber Installed = 50.50 miles Underground Backbone Fiber Installed = 37.55 miles Lateral Fiber Installed = 91.17 miles Total Fiber Installed on St. Thomas, St. John and Water Islands = 179.22 miles Cumulative Total Fiber Installed on St. Croix, St. Thomas, Water Island and St. John through Quarter 4, CY 2013: Aerial Backbone Fiber Installed = 90.63 miles Underground Backbone Fiber Installed = 98.07 miles Lateral Fiber Installed = 178.05 miles Cumulative Total Fiber Installed on All Islands = 366.75 miles During Quarter 4, CY 2013, despite significant delays due to very heavy rainfall, the VIPFA/viNGN team continued to make good progress with its FAP construction and lateral drop installations for its Community Anchor Institution (CAI) connections. On St. Thomas, construction was completed for seven FAPs (Facility Access Points) which were under construction. FAP STT-02 (University of the Virgin Islands), FAP STT-09 (Eudora Kean), FAP STT-10 (Rt. 10 & 32)/Nadir, FAP STT-11 (Fort Mylner), FAP STT-12 (Schneider Hospital), FAP STT-13 (Havensight)/WICO and FAP STT-16 (DPW Nisky) are 100% complete. Progress was also made with FAP STT-14 (Veteranâ€™s Drive) which is now 95% complete and FAP STT-05 (Dorothea) which is approximately 10% complete. On St. Croix, the team completed the construction of five FAPs. FAP STX-03 (Estate Diamond), FAP STX-04 (University of the Virgin Islands), FAP STX-07 (La Grande Princess), FAP STX-12 (Cotton Valley), and FAP STX-16 (Roebuck Industrial Park) are 100% complete. Further, FAP STX-17 (WAPA Richmond) is approximately 85% complete, and FAP STX-15 (Juan Luis Hospital) is approximately 55% complete. From inception through December 31, 2013, construction of 19 out of a total 22 FAPs has been completed, with construction of 9 FAPs completed on St. Croix, 8 FAPs completed on St. Thomas, and 2 FAPs completed on St. John. Racking and DC power has been installed in the 19 constructed FAPs, and networking equipment and generators are installed in the two SuperFAPs. The VIPFA/viNGN team also connected its second CAI which is the U.S. Virgin Islands Legislature building on St. Croix which is now ready to be activated by its selected broadband service provider which has already entered into a Master Services Agreement (MSA) with viNGN. viNGN connected its first CAI, the U.S. Virgin Islands Department of Planning and Natural Resources' (DPNR) Althalie McFarlane Petersen Library, in Frederiksted, St. Croix, which is also one of VIPFA/viNGN's BTOP-funded Public Computer Centers (PCC), during Quarter 3, CY 2013. The Petersen Library now has broadband capacity at up to 10 times the levels it experienced in the past. In addition, as of December 31, 2013, the VIPFA/viNGN team has entered into Master Services Agreement (MSA) with the following six (6) local broadband service providers: SMARTNET, Orbitel Access, ADM Wireless, Broadband VI, Surge Communications, and Fibernet, Inc., and discussions and negotiations continue with others. Moreover, during Quarter 4, CY 2013, VIPFA/viNGN hired a Vice President of Network Operations (Note: The title was changed to Chief Technology Officer during January 2014). The Chief Technology Officer/Vice President of Network Operations is responsible for managing the network operations centers, all other network operations assets, and network operations personnel. These responsibilities include the following: â€¢ Ensure 24/7/365 support for incident management and resolution; â€¢ Manage the budget for the network operations data center development, deployment, ongoing maintenance and service provisioning and expansion of the entire middle mile network; â€¢ Schedule and oversee all maintenance and repair activities and notify clients of shutdowns and other maintenance and repair activities; â€¢ Create and validate reports, regarding the current and future state of all network systems and supporting software to ensure efficient and reliable delivery of services; and, â€¢ Assist in developing and implementing strategies to expand and improve network operations. The team also participated in a viNGN-hosted Broadband Business and Technology/Broadband Coalition meeting to update the CAIs on the status of the build-out of VIPFA/viNGNâ€™s broadband network and the next steps for connecting them to the network. Further, the VIPFA/viNGN team obtained approval from NTIA and NOAA for a no-cost extension of its grant award agreement through June 30, 2014 to complete construction and testing, as the team determined that the work could not be completed in significantly less time than the 3 years that was proposed in the original grant application. | 367 | 3353 | 0 | 0 | 367 | 0 | 0 | 17 | As of December 31, 2013, a cumulative total of 366.75 miles of underground backbone, aerial backbone and lateral fiber was installed across St. Croix, St. Thomas, St. John and Water Island since the inception of the project. The number of new network miles deployed during Quarter 4, CY 2013 is 119.79. | With the leasing of new network miles from Global Crossing/Level 3 and AT&T, the VIPFA/viNGN team has met its immediate plans for new leased miles. | The VIPFA/viNGN team does not anticipate that it will upgrade network miles. All network miles are expected to be new installations of fiber or new leases of network miles. | N/A | As of December 31, 2013, a cumulative total of 366.75 miles of underground backbone, aerial backbone and lateral fiber was installed across St. Croix, St. Thomas, St. John and Water Island since the inception of the project. The number of new network miles deployed during Quarter 4, CY 2013 is 119.79. | N/A | N/A | All interconnection points are new and are considered from point to point. During Quarter 4, CY 2013, the VIPFA/viNGN team connected St. Patrick's School, the U.S. Virgin Islands Housing Finance Authority (VIHFA), the U.S. Virgin Islands Legislature building on St. Croix, Frederiksted Clinic (Ingebord Nesbit), Ludvig E. Harrigan Court Community Center, Claude O. Markoe Elementary School, the. U.S. Virgin Islands Department of Public Works Department (West), the Alexander Henderson Elementary School, the U.S. Virgin Islands Department of Planning & Natural Resources (DPNR), the Wilfredo Pedro Homes Community Center, the Walter I.M. Hodge Pavilion Community Center, the Boys' & Girls' Club (West), the U.S. Virgin Islands Department of Police Operations & Administration Substation, the Arthur A. Richards Junior High School, the U.S. Virgin Islands Superior Court, the Marley Additions Community Center, and the Frederiksted Fire Station, which are all CAIs on St. Croix. | 6 | 4 | 18 | VIPFA/viNGN has two broadband wholesale service contracts, one for 15 years with Global Crossing/Level 3 and the other for 1 year with AT&T, both providing leased fiber miles to viNGN. In addition, VIPFA/viNGN has Master Services Agreements (MSAs) with six (6) ISPs/last mile providers for 1 year each, with a renewal option. The MSAs are with SMARTNET, Orbitel Access, ADM Wireless, Broadband VI, Surge Communications, and Fibernet, Inc. | VIPFA/viNGN is building a high speed, open access, 100% fiber optic network which will provide inexpensive, high speed, reliable Ethernet transport and Internet connections to ISPs and other broadband service providers and, by extension, to Community Anchor Institutions (such as government departments and agencies, non-profit organizations, educational institutions, public safety entities, healthcare delivery providers, and other key community stakeholders). VIPFA/viNGN's goal is to serve as a Middle Mile provider, primarily offering wholesale broadband bandwidth on-net (i.e. within the U.S.V.I.) and off-net (i.e. outside of the U.S.V.I.) through a variety of service offerings, starting with 100 Megabit, 1 Gigabit and 10 Gigabit bandwidth plans; Multiprotocol Label Switching (MPLS)/Virtual Private Network (VPN) service to the U.S.; and, Transport Aggregation services. The team continues to conduct market research to refine its menu of service/product offerings and is not publishing pricing plans for the general public. Pricing plans are being negotiated with each service provider. Please refer to the attached Strictly Confidential and Proprietary related information that is made available to NTIA and NOAA only, as required as a part of this report. The attached related information has been redacted from this report and shall not be made available to the public. | NOT APPLICABLE | 6 | 0 | 0 | 2 | Refer to the response to Questions 5a and 5b above. With the signing of six (6) agreements with last mile providers (i.e. SMARTNET, Orbitel Access, ADM Wireless, Broadband VI, Surge Communications, and Fibernet, Inc.) and the signing of 2 agreements with broadband wholesalers to lease network miles (Level 3 and AT&T), the VIPFA/viNGN team has exceeded the Baseline Indicator target of 2. Though the network build-out is not complete, the VIPFA/viNGN team has agreements in place to allow it to connect its network and provide services to these service providers. | All agreements will result in the provisioning of new access. | N/A | Speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; and, Tier 3 and Tier 4 providers are expected to receive up to 500 Mbps. Since Quarter 3, CY 2013, VIPFA/viNGN is providing Tier 4 level service to SMARTNET which is, in turn, servicing DPNR's Althalie McFarlane Petersen Library in Frederiksted, St. Croix, which is a BTOP-funded CAI and Public Computer Center (PCC). Further, viNGN has entered into a Master Services Agreement with an ISP which expects to provide up to Tier 3 level service to the U.S. Virgin Islands Legislature building in Frederiksted, St. Croix. viNGN has connected and tested the connection, and the U.S. Virgin Islands Legislature has signed an agreement with an ISP who has an MSA with viNGN and is preparing to test and activate service. VIPFA/viNGN is providing each CAI with Cisco routers/switches with capacity up to 1 Gbps. As funding becomes available to them, each CAI is positioned to upgrade its other related equipment to be able to realize the full capacity of viNGN's network. | 2 | 2 | 0 | 2 | Under performance against this Baseline Indicator is due to the fact that VIPFA/viNGN has not completed the construction and connections of the FAPs and the build-out of other portions of the network that will enable viNGN to connect the remaining CAIs. As FAPs are connected and other portions of the network are built out, the team will be positioned to come in line with the Baseline Indicator target. viNGN connected its first CAI, the U.S. Virgin Islands Department of Planning and Natural Resources' (DPNR) Althalie McFarlane Petersen Library, in Frederiksted, St. Croix, which is also one of VIPFA/viNGN's BTOP-funded Public Computer Centers, during Quarter 3, CY 2013. The Petersen Library now has broadband capacity at up to 10 times the levels it experienced in the past. Prior to connecting to VIPFA/viNGN's network, it experienced a very low level Tier 4 bandwidth capacity (10 Mbps) and is now experiencing up to 100 Mbps. The VIPFA/viNGN team connected its second CAI, the U.S. Virgin Islands Legislature building on St. Croix, which is now ready to be tested and activated by its selected broadband service provider which has already entered into a Master Services Agreement (MSA) with viNGN. | viNGN connected its first CAI, the U.S. Virgin Islands Department of Planning and Natural Resources' (DPNR) Althalie McFarlane Petersen Library, in Frederiksted, St. Croix, which is also one of VIPFA/viNGN's BTOP-funded Public Computer Centers, during Quarter 3, CY 2013. The VIPFA/viNGN team connected its second CAI which is the U.S. Virgin Islands Legislature building on St. Croix which is now ready to be tested and activated by its selected broadband service provider which has already entered into a Master Services Agreement (MSA) with viNGN. As the remaining FAP construction is completed, the remaining equipment is installed in the FAPs, Community Anchor Institutions are connected, the remaining backbone node equipment is installed, and final testing and activation bring the network fully on line, the team will be positioned to come in line with the Baseline Indicator target. | All subscribers will receive new access. As of Quarter 4, CY 2013, VIPFA/viNGN is providing Tier 4 level service to DPNR's Althalie McFarlane Petersen Library through its ISP, SMARTNET. Prior to connecting to VIPFA/viNGN's network, it experienced a very low level Tier 4 bandwidth capacity (10 Mbps) and is now experiencing up to 100 Mbps. | Speed tiers to last mile providers and broadband wholesalers are anticipated at four levels - Tier 1 providers are expected to receive 10Gbps; Tier 2 providers are expected to receive 1Gbps; and, Tier 3 and Tier 4 providers are expected to receive up to 500 Mbps. Since Quarter 3, CY 2013, VIPFA/viNGN is providing Tier 4 level service to SMARTNET which is, in turn, servicing DPNR's Althalie McFarlane Petersen Library in Frederiksted, St. Croix, which is a BTOP-funded CAI and PCC. Further, viNGN has entered into a Master Services Agreement with an ISP which expects to provide up to Tier 3 level service to the U.S. Virgin Islands Legislature building in Frederiksted, St. Croix. viNGN has connected and tested the connection, and the U.S. Virgin Islands Legislature has signed an agreement with an ISP who has an MSA with viNGN and is preparing to test and activate service. VIPFA/viNGN is providing each CAI with Cisco routers/switches with capacity up to 1 Gbps. As funding becomes available to them, each CAI is positioned to upgrade its other related equipment to be able to realize the full capacity of viNGN's network. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | At this time, there is no special offering being proposed. Any special offerings will be determined, based upon the results of market research on optimal pricing and the optimal range of services to be offered. | FALSE | NOT APPLICABLE | The VIPFA/viNGN team plans to finalize the following during Quarter 1, CY 2014: - Estimate of New Fiber Miles To-Be-Installed/Deployed during Quarter 1, CY 2014: Cumulative Total Fiber To-Be-Installed on St. Croix, St. Thomas, Water Island and St. John during Quarter 1, CY 2014: 8 miles - Estimate of CAIs To-Be-Connected during Quarter 1, CY 2014: On St. Croix = 131 CAIs On Thomas = 149 CAIs On St. John = 33 CAIs On Water Island = 1 CAI Cumulative Total Number of CAIs To-Be-Connected = 314 CAIs - Estimate of Broadband Wholesaler or Last Mile Provider Agreements To-Be-Signed during Quarter 1, CY 2014 = 1 The VIPFA/viNGN team also plans to finalize the following during Quarter 1, CY 2014: â€¢ Continue the construction of the remaining FAPs (Fiber/Facility Access Points) and begin the installation of routers, switches and other equipment in the FAPS to await final connections to the aerial or underground fiber to bring the network on line; â€¢ Continue the installation of the remaining equipment in the already-constructed FAPS; â€¢ Continue the connections of CAIs and the testing of the connections; â€¢ Continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the construction activities; â€¢ Continue to assess the project implementation schedule and the network design to identify ways to speed up the build-out and â€œlighting upâ€ of the network and to reduce network construction, operational and maintenance costs; â€¢ Continue to assess the budget to determine if a budget modification will be needed; â€¢ Continue with Close-Out activities; â€¢ Participate in viNGN Broadband Business and Technology Committee meetings (formerly called Broadband Coalition meetings) that may be scheduled with Community Anchor Institutions, future VIPFA/viNGN customers and other stakeholders to discuss the status of the network build and to provide updates on the anticipated service offerings; and, â€¢ Continue to participate in U.S. Department of Commerce Broadband technology Opportunities Program-sponsored webinars. | Virgin Islands Public Finance Authority | The VIPFA/viNGN team has successfully increased the speed of implementation and will continue to work hard to complete the remainder of the network build-out and testing. During Quarter 4, CY 2013, the team determined that additional time was needed to complete the construction of the remaining FAPs, to connect CAIs, and to test the network. During late Quarter 3, CY 2013 and as the holiday season drew nearer, the VIPFA/viNGN team realized the importance of an extension to complete these critical activities, especially because the work could not be completed without the grant funding and could not be completed with significantly less time than what was proposed in the construction schedule that was submitted with the original grant application, i.e. a full 3 year construction and testing schedule, assuming no delays due to natural and/or man-made impediments. Construction and testing have been effectively and consistently underway for only 2 years. As a result, NTIA and NOAA approved a no-cost grant award extension from December 31, 2013 to June 30, 2014. During this grant award extension period, the team is continuing its efforts to complete the construction of the remaining FAPs, to complete testing of the equipment in the FAPs, to connect the CAIs, to test the resulting network connections, to complete the installation of the Operating Support System/Business Support System (OSS/BSS) and to complete the testing of the OSS/BSS, using unspent grant funding. The VIPFA/viNGN | The team will need to continue to coordinate with contractors to work on accelerated schedules and actively identify and create ways to speed up the construction activities, especially during periods of good weather; continue to assess the project implementation schedule and the network design to identify ways to speed up the build-out and â€œlighting upâ€ of the network and to reduce network construction, operational and maintenance costs; and, continue to assess the budget to determine if a budget modification will be needed. The VIPFA/viNGN team has successfully overcome the delays experienced to date by closely coordinating with its partners at NTIA, NOAA and WAPA and with its contractors and by focusing its efforts on working on accelerated schedules and continuing to identify and create ways to speed up project activities in all areas of implementation, e.g. by focusing on outside construction activities while the weather remains good. | TRUE
NT10BIX5570097 | 2010 | Q4 | Q4 - 2010 | October: completed draft budget amendment to submit to grant officer to acquire administrative budget; completed job descriptions for proposed grant staff. Received approval from State recovery office for draw of funds. November: Sponsored Public Safety/ Homeland Security Chief Jamie Barnett at a presentation to over 40 New Mexico public safety stakeholders. Attended federal grant training in D.C. Co-lead meetings of Operator Advisory Group. Submitted detail for revision of Environmental SAC. Secured leadership for environmental work to be performed on sites. December: attended Public Safety Research group conference in Boulder to obtain updates on Long Term Evolution development as part of LTE grant planning. Developing checklist for contractors who will bid to perform Environmentals. Reviewing existing site leases to ensure lessors are informed of work to be performed on radio site locations. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EAs have not been completed due to amendment of Special Award Condition on EA which now requires an Assessment rather than a consultation. No work on network can begin until environmental assessments are complete and approved. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Award of contracts to vendors to perform Environmental Assessments; Completion of 70% of the EA's. Contract negotiations with vendors to develop construction contracts. | Department of Information Technology | Obtaining approvals from State Recovery Office, determining grant budget amendment to accommodate administrative costs, such as grant staff, and keeping such change under 10%. Staff working on grant are all performing such work in addition to regularly assigned duties causing delays in some paperwork. Understanding all federal grant processes for administration of grant has been a challenge. The timing of State elections and subsequent outcome resulted in loss of key administrative grant staff (Secretary and PI) by the end of December; no appointments were made. Review of sites and subsequent discussions with radio staff resulted amendment of Environmental SAC, effective in December. Such change requires a request to NTIA to delay environmental report submission. DoIT will need help from BTOP to facilitate completion of EAs. EA coordinator will work with Grant officers and DoIT staff to move forward. | Identifying new DoIT management and PI; timely completion of EA and acceptance of final report; obtaining a Project Mgr for infrastructure work; confirming LTE sites; completing multiple contracts with infrastructure contractors selected via RFP. Weather conditions during winter months impact completion of EA's. | TRUE
NT10BIX5570097 | 2011 | Q1 | Q1 - 2011 | During the last quarter the Request for Proposal (RFP) for the construction of the Middle Mile Digital Micro Wave (DMW) sites was released, the proposals evaluated, and price agreements are being finalized. The Governor approved and certified the project and it has been posted on the State of NM website. The Baseline Project Plan was approved, along with the Budget Amendment and the Six Month Budget. The New Mexico Office of Recovery and Reinvestment (NMORR) approved the release of all funds for the project. Three term positions have been established and are in the Governorâ€™s office for approval. It is expected that these positions will be hired within the next four to six weeks. The Department of Information Technology Secretary has been designated as the Principal Investigator. The extension was approved for conducting the Environmental Assessments and submission of an Overlap Map. The required Overlap Map was submitted for review and approval prior to March 1, 2011. The State is waiting on the approval for the sole source request for contacting general counsel. Three contracts have been negotiated and signed for conducting the Environmental Assessments on the fifty-nine DMW sites. A fourth contract is in the signature process for conducting the assessments on the fourteen 700MHz Long Term Evolution sites. All site lease agreements are being reviewed for notification requirements and any restrictions that may apply. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No work on network can begin until environmental assessments are complete and approved. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time | FALSE | N/A | 90% completion of EA analysis activities and submission of the draft EA. Finalize Price Agreements for DMW construction, contract negotiations with vendors on the construction specifically related to the planning and design activities; Contract for a Radio Frequency Engineer to begin network design; Begin purchase process for equipment such as towers, generators, and shelters. | Department of Information Technology | Contracting process delayed the execution of the contracts to perform EA analysis activities. Developing the four EA contracts impacted the development of the Price Agreements and formal announcement of the award. New staff, a change in government administration, and a delay in the appointment of key government personnel further delayed activities. Completion of the feasibility study is included in one of the EA contracts, and while not completed during Q3, will be completed early in Q4. | Approval from the Governor's office to hire three term employees for the project. Extremely dry weather conditions creating fire hazards. | TRUE
NT10BIX5570097 | 2011 | Q2 | Q2 - 2011 | During the last quarter the Request For Proposal (RFP) for the construction of the Middle Mile Digital Microwave (DMW) sites was evaluated, and price agreements have been awarded. Three term positions were announced and interviews are being conducted. It is expected that these positions will be hired within the next four to six weeks. The site inspections have been completed and the Environmental Assessment will be finalized and submitted. (submitted on 07/13) The Overlap Maps were submitted. Additionally, maps have been forwarded based on request from various Tribal responses. The sole source request for contacting general counsel was approved and the contract finalized. Site lease agreements are still being reviewed for notification requirements and any restrictions that may apply. The project was presented to the State's Project Certification Committee for the Planning Phase and received approval for budget release of $7,175K. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New network miles will only apply to the 700MHz part of the project. This is NA on the DMW portion of the project | no variance | no variance | no variance | N/A | no variance | no variance | no variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | no variance | no variance | no variance | no variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time | FALSE | N/A | In the next quarter the FONSI should be received reflecting all applicable comments and responses to move forward. A contract will be awarded for a Radio Frequency Engineer to begin network design. Contracts will be awarded for project management for the five regions. | Department of Information Technology | 1)The development of the four Environmental Assessments contracts consumed the resource which impacted the finalization of the Price Agreement Awards. | 1) The state's process to hire three term employees for the project has been slow moving . 2) Extremely dry weather conditions created burned areas that are susceptible to flooding which could have an affect on completion due to an inability to access certain areas. | TRUE
NT10BIX5570097 | 2011 | Q3 | Q3 - 2011 | During the last quarter the Request For Proposal (RFP) for the construction of the Middle Mile Digital Microwave (DMW) sites was evaluated, and price agreements have been awarded. Three term positions were announced and interviews conducted. Two position were filled (PM and Finance), third position in process. EA site inspections completed and the EA is in final draft process. Detailed DMW program planning is underway. Contractor SOWs being formulated. Prepared draft professional services contract for 700 MHz LTE consulting support. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction contracts not yet awarded. Contracts to be awarded in Year 1 Quarter 2, with focus on completing links where no construction is required. | N/A | 700 MHz procurement in planning | N/A | N/A | Construction contracts not yet awarded, no wireless links yet activiated. | no variance | Construction contracts not yet awarded, no network elements yet installed. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Construction Contracts not yet awarded, no network elements yet installed. No subscribers yet connected. Anticipate first connections in Year 2 Quarter 3. | Construction Contracts not yet awarded, no network elements yet installed. No subscribers yet connected. Anticipate first connections in Year 2 Quarter 3. | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time | FALSE | N/A | 1) Condition FONSI 2) Construction contractor SOWs negotiated 3 DMW construction initiation -- site design, construction, activation 4) 700 MHz consultant contract initiated -- develop system procurement requirements | Department of Information Technology | None at this time. | 1) Biggest challenge likely New Mexico winter weather impact on site access and site surveys. 2) Negotiating site lease modifications necessary to obtain construction permits | TRUE
NT10BIX5570097 | 2011 | Q4 | Q4 - 2011 | 1. Digital Microwave (DMW) construction contracts initiated, site surveys 90% complete, path analyses 50% complete, civil construction drawings 5% complete, and Federal Communication Commission (FCC) Current Prior Coordination Notices (PCNs) 80% complete. 2. DMW hardware vendors selected and currently working with construction contractors supporting tower and shelter designs. Data required to issue hardware purchase orders 50% complete. 3. Significant DMW planning completed; baseline schedules prepared and logistics strategy developed. 4. Network architecture developed by Cisco and router selection made. Competitive router procurement initiated. 5. 700 MHz consulting contract in final negotiation. 6. Broadband Executive Steering Committee formed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | Construction has not commenced | N/A | N/A | Construction has not commenced | Construction has not commenced | Construction has not commenced | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Construction has not commenced | Construction has not commenced | Construction has not commenced | Construction has not commenced | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | DMW Project 1. In January 2012, will issue purchase orders to Sabre for towers, Modular Connections for shelters, NGH for battery/rectifiers, Aviat for radio kits, and (to-be-determined) for Cisco network. Department of Information Technology (DoIT) will have hardware delivered to secured State of New Mexico facilities in Santa Fe, NM, and construction contractors will requisition needed hardware items as required. 2. All microwave frequencies identified by ComSearch and PCNs prepared and submitted to the FCC. Aviat to begin manufacturing, testing, and shipping radio kits as soon as frequencies are cleared 3. Our two civil construction contractor have agreed to have construction (new tower and shelter) completed for at least 20 sites by July, 31, 2012. Civil designs (Professional Engineer Stamped Drawings) and cost estimates will be prepared to support this schedule 4. Radio kits available to be installed at site requiring no civil construction will be installed as soon as available from Aviat 5. A Community Anchor Institution Marketing staff member has joined the grant project team to begin developing our strategy for offering the broadband network as a state service; which includes the 700 MHz LTE sites. 1. Televate will begin assisting DoIT in developing our LTE system request-for-proposal (RFP). Televate will begin by leading a needs assessment; visioning session with our LTE Users Group in early February 2012. | Department of Information Technology | None at this time. | 1) Biggest challenge likely New Mexico winter weather impact on site access and site surveys. 2) Negotiating site lease modifications necessary to obtain construction permits | TRUE
NT10BIX5570097 | 2012 | Q1 | Q1 - 2012 | Middle Mile Project 1. Coordination with USFS and BLM a. All SF 299â€™s have been submitted with the certified drawing packages b. Met with all but one (BLM â€“ South Mesa). Currently scheduled in April. 2. POs issued to all hardware vendors authorizing manufacturing â€“ tower, shelters, batteries, radio kits, routers, and security systems totaling over $15.6M 3. 30% of hardware manufactured, accepted, invoiced, and paid totaling over $4.6M. Another $6M is in the process of being paid. The remaining amounts are expected to be completed/paid within the second quarter. 4. Contracts for the three primary vendors were amended to cover deployment, installation, and testing of all Radio Frequency (RF) systems 5. PCNs for all links have been approved. 6. Proposals for all civil construction received, negotiated, and contract modifications prepared. Over $8M in contract amendments are being processed (Currently waiting on approval from Department of Finance & Administration). 7. All radio equipment has been manufactured by Aviat and is ready for factory acceptance testing (FAT). All network routers delivered to Aviat for installation with radios and included in FAT. 8. Preparing contract for professional engineering services to independently inspect civil construction sites â€“ 8 inspections at each site. 9. Construction contractors (Aviat and TowerCom) performing detailed planning and preparations for beginning site construction in April 2012 â€“ arrangements with subs, equipment rental, ordering materials (cement, rebar, etc.). Started installing new battery backup systems in equipment only locations (Albuquerque State Police and Cedro Peak). 10. Contracts for Network Engineering Services is being negotiated. 11. Obtained work permits for all Department of Transportation sites. 12. Coordinated all procedures and inspections with the State of New Mexico Construction Industries Division. 13. Updating the Master Schedule for all equipment deliveries, construction, and implementation activities. 700 LTE Project 1. Formed Executive Steering Committee (ESC) and Technical Users Group (TUG). ESC â€œMeet and Greetâ€ in January 2012 and TUG â€œVisioning Sessionâ€ held in February 2012. 2. Televate contract signed January 2012. Draft deliverables â€“ Needs Assessment and System Specifications delivered in March 2012. 3. Began LTE RFP preparations in March 2012. However, preparations delayed due to advent of FirstNet Legislation and guidance from NTIA. Plans are to proceed with planning, site selection, and design. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | Construction has not commenced. Network miles will be 'upgraded' as the radio and network equipment is brought on-line over the next 6 to 8 months. | N/A | N/A | Construction has not commenced. 700 MHz LTE RFP for design is being drafted. | Construction has not commenced. DMW is replacing 24 towers. Towers are being delivered and current plans are to have all towers assembled by the end of Q2Y3. | Construction has not commenced. The interconnect points will be upgraded as part of the construction which is expected to be completed Q2Y3. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Based on last quarters identification of CA's, all CAI's are related to the LTE portion of the project. The Department, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project. | Based on last quarters identification of CA's, all CAI's are related to the LTE portion of the project. The Department, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project. | Based on last quarters identification of CA's, all CAI's are related to the LTE portion of the project. The Department, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project. | No speed tiers are currently available for any subscriber. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | DMW 1. Civil Construction will begin on at least thirteen sites. 2. FAT and Signal Quality Check (SITQ) testing will be completed on Radio Kits and the equipment shipped to Albuquerque staging facility for distribution to installation contractors. 3. Implementation of RF equipment will begin at the Equipment Only designated sites. 4. DoIT staff will do final acceptance and payments for remaining equipment. 5. Radio System Training for State and Contractor personnel will be conducted with Certification Test administered. 700MHz LTE 1. Establish State Price Agreements for 700MHz LTE equipment (Price Agreements only, NO Purchases) via an Invitation To Bid. 2. Will issue a Request For Proposal for 700MHz Professional Services with the expectation to establish a Statewide Price Agreement on a Deliverable (Task Order) basis. | Department of Information Technology | None at this time. | 1) Biggest challenge likely New Mexico summer weather impact on site access and site surveys. Current predictions are to have a second bad year of fires. USFS is already looking at the possibility of closing forest areas. 2) Equipment purchases for the 700MHz LTE system are delayed due to the status of FirstNet. | TRUE
NT10BIX5570097 | 2012 | Q2 | Q2 - 2012 | Middle Mile Project 1. Coordination with United States Forest Service (USFS) and Bureau of Land Management (BLM) a. All SF 299â€™s required have been submitted with the certified drawing packages; Approvals have been received for Sandia Crest, Gallinas, and LaMosca. b. Met with BLM (South Mesa & High Lonesome) in April. c. Coordinated with USFS and BLM on indemnification language to be used in lease documents 2. Received, accepted and paid for all towers, shelters, batteries, radio kits, routers, and security systems that had been ordered, totaling almost $15M. 3. Over $8M in contract amendments for civil construction were processed. 4. Executed a contract for professional engineering services to independently inspect civil construction sites â€“ 8 inspections at each site. 5. Construction contractors (Aviat and TowerCom) began construction at over 20 sites during the quarter. Two are nearing completion 6. Updating the Master Schedule for all equipment deliveries, construction, and implementation activities. 7. Radio System Training for State and Contractor personnel was conducted with Certification Test administered. 700 LTE Project 1. LTE portion was put into a suspended status. The Request for Proposal activities were put on hold due to the LTE suspension. The suspension letter was submitted to NTIA per requirements. | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | N\A | N\A | Network miles will be 'upgraded' as the radio and network equipment is brought on-line starting in September (Q3Y3) | N/A | N/A | The LTE portion of the project which deals with wireless links, is currently suspended. | Five towers have been completed and construction has commenced at a number of other sites. DMW is replacing 24 towers. Current plans are to have all towers assembled by the end of Q2Y3. | Construction has commenced at over 20 locations. The interconnect points will be upgraded as part of the construction which is expected to be completed Q2Y3. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N\A | N\A | N\A | N\A | 0 | 0 | 0 | 0 | Based on a previous quarters identification of Community Anchor Institutions (CAI's), all CAI's are related to the LTE portion of the project. The Department, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | Based on a previous quarters identification of CA's, all CAI's are related to the LTE portion of the project. The Department, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | Based on a previous quarters identification of CA's, all CAI's are related to the LTE portion of the project. The Department, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | No speed tiers are currently available for any subscriber. | 0 | 0 | 0 | 0 | 0 | N\A | N\A | N\A | N\A | N\A | 0 | 0 | 0 | 0 | 0 | N\A | N\A | N\A | N\A | N\A | N\A | FALSE | N\A | DMW 1. Civil Construction will begin on remaining construction sites. 2. Factory Acceptance Test (FAT) and Signal Quality Check (SITQ) testing will be completed on Radio Kits and the equipment shipped to Albuquerque staging facility for distribution to installation contractors. 3. Implementation of RF equipment will begin at the Equipment Only designated sites. 4. DoIT staff will do final acceptance and payments for remaining equipment. 5. A second round of Radio System Training for State and Contractor personnel will be conducted with Certification Test administered. 6. Training plan will be approved. 700MHz LTE. 1. Revamped budget amendment will be submitted. 2. Geographical areas for LTE will be considered. 3. LTE Build and Equipment purchase activities is suspended. | Department of Information Technology | None at this time. | 1) Biggest challenge likely New Mexico summer weather impact on site access and site surveys. Current predictions are to have a second bad year of fires. USFS has elevated the Fire Status to Level 2 and is still looking at the possibility of closing forest areas. 2) Equipment purchases for the 700MHz LTE system are suspended | TRUE
NT10BIX5570097 | 2012 | Q3 | Q3 - 2012 | Middle Mile Project 1. Coordination with United States Forest Service (USFS) and Bureau of Land Management (BLM). a. All SF 299â€™s required have been submitted with the certified drawing packages; Approvals have been received on all but High Lonesome, South Mesa, Coyote, and Eureka. b. Coordinated with USFS and BLM on indemnification language to be used in lease documents. 2. Construction has been started at 24 sites with several completed or nearly completed. 3. Submitted and received approval on a Budget Amendment. 4. Submitted a Route Modification Request adding 9 sites to the DMW list (equipment only). 5. Received antennas and waveguides in Albuquerque for distribution/installation. 6. Received all radio/router racks for the Metro, Southwest, and Southeast regions for distribution/installation. 7. Conducted Cisco Network training for five engineers on the DMW staff. 700 LTE Project 1. LTE portion is still on hold. | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | n/a | n/a | Network miles will be upgraded as the network and radio equipment is brought on-line. The majority will be implemented in the March/April time frame with the remaining upgraded by the end of Q4Y3. | n/a | n/a | The LTE portion of the project is currently suspended. | 11 new towers have been stacked. It is expected that 21 of the 24 towers will be completed in Q2Y3. The final towers will be delayed due to weather until Q4Y3. | Construction has commenced at 24 sites. The interconnect points will be upgraded as part of the construction which is expected to be competed Q4Y3. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Based on a previous quarters identification of Community Anchor Institutions (CAI's), all CAI's are related to the LTE portion of the project. The Department, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | Based on a previous quarters identification of Community Anchor Institutions (CAI's), all CAI's are related to the LTE portion of the project. The Department, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | Based on a previous quarters identification of Community Anchor Institutions (CAI's), all CAI's are related to the LTE portion of the project. The Department, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | No speed tiers are currently available for any subscriber. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | DMW 1. Leases with BLM for High Lonesome and South Mesa will be signed and permits issued. 2. Civil Construction will begin on 3 additional construction sites, the final two sites will begin as permitting and weather permits. 3. Factory Acceptance Test (FAT) and Signal Quality Check (SITQ) testing will be completed on Radio Kits and the equipment for the NE and NW regions will be shipped to Albuquerque staging facility for distribution to installation contractors. 4. Implementation of RF equipment will begin at the Equipment Only designated sites. 5. Equipment will be ordered for the sites added via the Route Modification Request (pending). 700MHz LTE. 1. LTE is suspended at this time | Department of Information Technology | None at this time. | 1) Biggest challenge likely is New Mexico winter weather impact on site access for installation and site surveys (if needed). We are still waiting on permits for two USFS sites (Coyote and Eureka). 2) Equipment purchases for the 700MHz LTE system are suspended. | TRUE
NT10BIX5570097 | 2012 | Q4 | Q4 - 2012 | DMW: The state has made significant progress on construction and implementation. Construction has been completed at 18 sites, 9 others are in progress with several nearing completion. Factory Acceptance was completed on all radio/network equipment Almost all radio/network equipment has been deployed for installation. Leases with Bureau of Land Management (BLM) for High Lonesome and South Mesa were completed and permits obtained. LTE: Met with the FirstNet board members for a presentation on 12/21/12. | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | n/a | n/a | Network miles will be upgraded as the network and radio equipment is brought on-line. The majority will be implemented in the March/April time frame with the remaining upgraded by the end of June CY2013.. | n\a | n\a | The LTE portion remains suspended. | 21 of 25 towers have been stacked. The final towers will be delayed due to weather until second quarter CY2013. | Construction has commenced at 27 sites. The interconnect points will be upgraded as part of the construction which is expected to be competed second quarter of CY2013. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Based on a previous quarters identification of Community Anchor Institutions (CAI's), all CAI's are related to the LTE portion of the project. DoIT, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | Based on a previous quarters identification of Community Anchor Institutions (CAI's), all CAI's are related to the LTE portion of the project. DoIT, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | Based on a previous quarters identification of Community Anchor Institutions (CAI's), all CAI's are related to the LTE portion of the project. DoIT, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | No speed tiers are currently available. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | DMW Civil construction will be completed at all but 2 sites. The final two sites will begin, weather permitting. All Antenna and radio kits will be installed at all but the 2 sites, with all but four links being brought up for testing. Equipment will be ordered for the approved Route Modification sites. Finalize leases with USFS (Santa Fe) for the remaining 2 sites. LTE Get direction from FirstNet via NTIA on how to proceed. | Department of Information Technology | The New Mexico Department of Information Technology (DoIT) continues to work with United States Forest Service (USFS) on special insurance that is being required with the new leases. Snow has stopped all activity at a number of sites in the Northern portion of the state. | 1) Biggest challenge likely is New Mexico winter weather impact on site access for installation. We are still waiting on permits for two USFS sites (Coyote and Eureka). 2) Equipment purchases for the 700MHz LTE system are suspended. | TRUE
NT10BIX5570097 | 2013 | Q1 | Q1 - 2013 | DMW: Continued major construction activities at 26 of the 29 sites. Began installation of antennas, waveguides, radios, and routers Brought up five links for "burn in" and testing totaling 126 miles Purchased additional equipment (antennas, waveguides, radios, and routers) for the new approved sites. LTE: Started the process of negotiating the Spectrum Lease Agreement with FirstNet Developed the base contract to perform a 700MHz Spectrum Analysis along the international border between New Mexico and Mexico. | 0 | 0 | 126 | 0 | 0 | 0 | 22 | 0 | NA | NA | Five links have been turned up for "burn in" and testing | NA | NA | DoIT is working with FirstNet on a Spectrum Lease Agreement. | 22 of 25 towers have been stacked. The final towers will be delayed until second quarter CY2013. | Construction has commenced at 27 sites. The interconnect points will be upgraded as part of the construction which is expected to be competed second quarter of CY2013. | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | na | 0 | 0 | 0 | 0 | Based on a previous quarters identification of Community Anchor Institutions (CAI's), all CAI's are related to the LTE portion of the project. DoIT, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | Based on a previous quarters identification of Community Anchor Institutions (CAI's), all CAI's are related to the LTE portion of the project. DoIT, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | Based on a previous quarters identification of Community Anchor Institutions (CAI's), all CAI's are related to the LTE portion of the project. DoIT, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | No speed tiers are currently available. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | DMW Complete all major construction at 27 of the 29 sites. Receive final permits/approvals for the remaining 2 sites and start construction activities. Bring up 44 of the 70 links for "burn in" and testing. LTE Complete the Spectrum Lease Agreement with FirstNet. Complete the 700MHz Spectrum Analysis along the international border between New Mexico and Mexico. Start developing MOUs with stakeholders in support of the 700MHz LTE border project. | Department of Information Technology | The New Mexico Department of Information Technology (DoIT) continues to work with United States Forest Service (USFS) on special insurance that is being required with the new leases. Snow has stopped all activity at a number of sites in the Northern portion of the state. | New Mexico is still experiencing a significant drought period with little snowfall last winter and low expectation of rain this summer. While major construction will be completed, we still need access into the National Forest for implementation activities. Depending on the weather conditions and dryness, closure of USFS/BLM areas can cause delays. | TRUE
NT10BIX5570097 | 2013 | Q2 | Q2 - 2013 | DMW: Finished major construction at 25 sites. Continued major construction activities at 2 of the 29 sites. Two sites are still pending start. Continued installation of antennas, waveguides, radios, and routers. Brought up 30 links for "burn in" and testing totaling over 900 miles. Received additional equipment (antennas, waveguides, radios, and routers) for the new approved sites. LTE: Continued the process of negotiating the Spectrum Lease Agreement with FirstNet. Completed a 700MHz Spectrum Analysis along the international border between New Mexico and Mexico. | 0 | 0 | 900 | 0 | 0 | 0 | 23 | 0 | NA | NA | 30 links have been turned up for "burn in" and testing. | NA | NA | DoIT is working with FirstNet on a Spectrum Lease Agreement. | 22 have been completed and 1 is near completion The final towers will be delayed until fourth quarter CY2013. | Construction has commenced at 27 sites. The interconnect points will be upgraded as part of the construction which is expected to be competed fourth quarter of CY2013. | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | Based on a previous quarters identification of Community Anchor Institutions (CAI's), all CAI's are related to the LTE portion of the project. DoIT, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | Based on a previous quarters identification of Community Anchor Institutions (CAI's), all CAI's are related to the LTE portion of the project. DoIT, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | Based on a previous quarters identification of Community Anchor Institutions (CAI's), all CAI's are related to the LTE portion of the project. DoIT, in conjunction with NTIA, re-evaluated and revised the CAIs identified. The current list of remaining CAIs are all related to the 700 MHz LTE part of the project which has been suspended. | No speed tiers are currently available. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | DMW Complete all major construction at 27 of the 29 sites. Receive final permits/approvals for the remaining 2 sites and start construction activities. Bring up 60 of the 70 links for "burn in" and testing. LTE Finalize negotiation with FirstNet and sign the Spectrum Lease Agreement. Start developing MOUs with stakeholders in support of the 700MHz LTE border project. Develop a MOU with Texas for Core sharing. Develop the 700MHz RFP. | Department of Information Technology | The New Mexico Department of Information Technology (DoIT) continues to work with United States Forest Service (USFS) on special insurance that is being required with the new leases. Fires and rain has stopped some activity at a number of sites in the Northern portion of the state. | New Mexico is still experiencing a significant drought period with little snowfall last winter and low expectation of rain this summer. While major construction will be completed, we still need access into the National Forest for implementation activities. Depending on the weather conditions and dryness, closure of USFS/BLM areas can cause delays. | TRUE
NT10BIX5570097 | 2013 | Q3 | Q3 - 2013 | DMW: Finished major construction at 26 sites, finalizing construction at 1 site.. Received permission to start at the last two sites from the USFS Santa Fe. However, construction is delayed due to weather. Continued installation of antennas, waveguides, radios, and routers at all remaining sites. Brought up 44 links for "burn in" and testing totaling almost 1300 miles. LTE: Signed the Spectrum Lease Agreement with FirstNet. Received a two year extension on the project, still waiting for final approval to lift the Funds Suspension. | 0 | 0 | 1300 | 0 | 0 | 0 | 23 | 0 | NA | NA | 44 links have been turned up for "burn in" and testing | NA | NA | DoIT has signed a Spectrum Lease Agreement with FirstNet. | 23 towers have been completed. the final towers will be delayed until Q2CY14. | Construction has commenced at 27 sites. The interconnect points will be upgraded as part of the construction which is expected to be competed fourth quarter of CY2013. | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | DMW Complete major construction at the 27th of the 29 sites. Bring up 56 of the 70 BTOP links for "burn in" and testing and upgrade the remaining 32 non-BTOP links for compatibility LTE Begin Design Continue to negotiate MOUs with the State of Texas and potential Federal partners | Department of Information Technology | The New Mexico Department of Information Technology (DoIT) has resolved the insurance issues with the United States Forest Service (Santa Fe). The USFS has given DoIT permission to build the Coyote and Eureka sites. However, the winter weather in the Northern portion of the state combined with risks associated with incomplete construction will delay the beginning of construction until March/April of CY2014. | Weather (cold/snow) at higher elevations in Norther New Mexico regions will prevent the start of construction at Coyote and Eureka. | TRUE
NT10BIX5570097 | 2013 | Q4 | Q4 - 2013 | DMW: Finished major construction at 27 sites. Construction is delayed at Eureka and Coyote until Spring, 2014 due to weather. Continued installation of antennas, waveguides, radios, and routers at all remaining sites. Brought up 46 links for "burn in" and testing totaling almost 1400 miles. Started transition from "old legacy network" to new BTOP network. LTE: Have made contact with Customs Border Protection (CBP). Meeting scheduled for February 24, 2014. Starting Request for Proposal (RFP) for 700 LTE Equipment, Professional Services, and Implementation. | 0 | 0 | 1400 | 0 | 0 | 0 | 23 | 0 | NA | NA | 46 links have been turned up for "Burn in" and testing. | NA | NA | DoIT has signed a Spectrum Lease Agreement with FirstNet. | 23 towers have been completed. The final towers will be delayed until Q2CY14. | Construction has completed at 27 sites. The interconnect points will be upgraded as part of the construction which is expected to be competed first quarter of CY2014. | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | DMW: Due to contract delays and weather, the Network transition from the "old legacy network" to the new BTOP network has been delayed. Once contracts are approved; DoIT will continue the upgrade and testing of the remaining 32 non-BTOP links for compatibility and testing of our BTOP Network Operations Center (NOC). No new miles are projected for the first quarter. No Community Anchor Institutions (CAIs) are to be connected for the first quarter. LTE: Work will begin on the 700 LTE Request for Proposal (RFP). Work will begin on the LTE design pending discussion outcome with CBP. DoIT will continue to negotiate Memorandum of Understanding (MOU) with the State of Texas and potential Federal partners. | Department of Information Technology | Due to scheduling conflicts, the meeting with Customs Border Protection (CBP) has been delayed until Monday, February 24, 2014 at 1400 hours in El Paso, Texas. | Weather (cold/snow) at higher elevations in Northern New Mexico regions will prevent the start of construction at Coyote and Eureka. Weather (cold/snow) at Cathey Peak in Southern New Mexico has hampered/delayed due to delay in tree cutting for microwave line of site to link to Caballo. | TRUE
NT10BIX5570098 | 2010 | Q4 | Q4 - 2010 | Grants Administration â€¢ Completed Special Award Condition 10, Baseline Project Plan â€¢ Revised and Completed Detailed Budget, 6-Month EA Budget, and Budget Narrative â€¢ Clarified status of Praxis Associates, Inc. as a sub-recipient â€¢ Attended the National Telecommunications and Information Administration Broadband Technology Opportunity Program Recipient Conference (Nov 9-12) â€¢ Conducted weekly status meetings with Federal Program Officer Network Planning and Engineering â€¢ Completed end to end route plans for EA and Rights-of-Way documentation â€¢ Completed node site identification â€¢ Identified and documented all Staging and Laydown Sites â€¢ Took detailed "Distance Measuring Instrument" measurements for 70% of route (high altitude and desert sections) â€¢ Completed Request For Proposal and awarded Digital Mapping contract with TetraTech. â€¢ Completed survey of 2/3 route to create digital base maps â€¢ Negotiated changes to the Caltrans Broadband Policy to accommodate special needs of Digital 395 â€¢ Negotiated route in State of Nevada with Nevada Department of Transportation and Counties Environmental Assessment â€¢ Awarded Contract for Environmental Assessment vendor â€¢ Completed Biological Investigation: Desktop and field surveys throughout entire route â€¢ Completed Cultural Investigation: conducted route-wide record searches; field cultural surveys in all but Indian Reservations, Bureau of Land Management, Department of Defense and United States Forest Se | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 3 | 0 | N/A | N/A3 | Inyo Networks, Inc. as a vendor for the California Broadband Cooperative will perform all day to day operating activities for the Digital 395 network after the initial network construction phase of the project is complete. These activities will include network management and operation, anchor institution service provisioning, customer care, billing and regulatory support. Inyo Networks Michael Ort - Chief Executive Officer 1101 Nimitz Avenue Vallejo, CA 94592-1014 Phone (510) 599-4062 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The third quarter (January 1, 2011-March 31, 2011) activities will concentrate on completing the Environmental Assessment and initiating Rights-of-Way efforts. In addition, pre-construction activities will focus on the development of working drawings for construction operations, securing permits, and creating bid specs for the Request For Proposals. Environmental Assessment A Draft Environmental Assessment will be submitted on time (January 31, 2011) for California Public Utility Commission and National Telecommunications and Information Administration review. Concurrently, environmental work will continue to be aggressively pursued with key state and federal agencies. Special attention will be given to sensitive cultural areas in Bureau of Land Management and United States Forest Service lands. Stakeholder work will be undertaken as required by local agencies. Network designs and construction methods will be modified, as needed to mitigate any identified project impacts. Network Design Having segmented the overall route into manageable sections, we will begin field drawings in key sections of the route to test our methodology with permitting agencies. In addition, we will complete our digital base maps for approximately 70% of the route and acquire available city and county maps for municipal network designs. Contracts will be secured with local telephone exchange companies to ascertain available conduit in communities. Project Overlap We conducted a series of | California Broadband Cooperative, Inc. | California Broadband encountered challenges with several federal agencies in obtaining cultural records for the Draft Environmental Assessment. Both the Bureau of Land Management and United States Forest Service indicated they were under statutory obligations regarding Section 106, requiring extensive field surveys, which appeared to be incongruent with Environmental Assessment requirements as expressed by National Telecommunications and Information Administration. As these issues were worked out, winter storms set in and much of the area in question was covered in snow. A mutual clarification of United States Forest Service and Bureau of Land Management agency roles would help move the project. | The project will continue to be challenged by agency Environmental requirements of Federal Lands. In addition to the extensive field survey work required under Section 106 by the Bureau of Land Management, we anticipate some intervention during the comment cycles by local stakeholders. Due to over 4,000 identified parcels along the route, we anticipate some challenges defining the specific location of the existing CalTrans rights-of-way. The land records are extremely old and do not lend themselves to efficient digital documentation. Accuracy and completeness is also a problem in the area. | TRUE
NT10BIX5570098 | 2011 | Q1 | Q1 - 2011 | Grants Administration â€¢ Submitted and obtained approval on 4-Month Budget â€¢ Worked with Nevada Hospital Association and other Grants to identify overlap â€¢ Conducted weekly meetings with National Telecommunications and Information Administration (NTIA) Federal Program Officer â€¢ Conducted status meetings with NTIA Administration on National Environmental Policy Act issues Network Planning and Engineering â€¢ Finalized route plans in Nevada with all agencies to acquire existing conduit â€¢ Developed tactical engineering plan â€¢ Based on Agency feedback, refined routes through Owens Valley â€¢ Created high-resolution base maps of 80% of route â€¢ Acquired engineering equipment for detailed engineering â€¢ Met with agencies to obtain design requirements Environmental Assessment â€¢ Completed and Submitted Draft EA â€¢ Conducted Scoping Meetings with Forest Service, Bureau of Land Management, and Fish and Wildlife â€¢ Coordinated Environmental Reviews with Dept. of Defense â€“ US Navy â€¢ Developed Desert Tortoise Fencing Solution with Fish and Wildlife â€¢ Developed alternative routes to avoid major permit issues â€¢ â€œInformalâ€ meetings with 3 of 6 Tribal Councils â€¢ Completed Section 107 Notifications (NTIA) â€¢ Actively supported Programmatic Agreement changes with agencies â€¢ Coordinated multiple meetings between CA agencies and counties â€¢ Scoping meeting conducted with Fish and Game â€¢ Conducted Phase 1 Environmental Assessment Project Management â€¢ D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance, Construction Not Started | NA | NA | No Variance, Construction Not Started | No Variance, Construction Not Started | NA | No Variance, Construction Not Started | No Variance, Construction Not Started | 0 | 12 | 0 | Presently we do not have any signed agreements. | Presently wholesale services are not being provided, construction not startede not being provided, construction not started. | Inyo Networks, Inc. as a vendor for the California Broadband Cooperative will perform all day to day operating activities for the Digital 395 network after the initial network construction phase of the project is complete. These activities will include network management and operation, anchor institution service provisioning, customer care, billing and regulatory support. Inyo Networks Michael Ort - Chief Executive Officer 1101 Nimitz Avenue Vallejo, CA 94592-1014 Phone (510) 599-4062 | 0 | 0 | 0 | 0 | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | 0 | 0 | 0 | 0 | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | Grants Administration - Develop budget for Months 10-14 - Validate Tax Exempt Status - Obtain Certificate of Public Convenience from State of Nevada for California Broadband - Complete the outfitting of project offices on entire route (Reno, Bishop, and Ridgecrest) Network Planning and Engineering - Complete final alignment, staging sites and node locations with full documentation - Clarify details needed by permitting agencies for working drawings - Create working drawings for first set of Design Blocks - Define detailed node requirements - Complete detailed design of Nodes and configurations - Define Anchor equipment room requirements - Initiate Anchor outreach efforts to ascertain hook up requirements - Complete Rights of Way requirements and documentation for Federal and State Agencies - Prepare Rights of Way documents for critical sections of route, including nodes Environmental Assessment - Complete second draft of Environmental Assessment - Complete and obtain support on Memorandum of Understanding and Programmatic Agreements for revised Section 106 requirements - Complete field studies in federal lands and land owned by Department of Water and Power - Issue revised Environmental Assessment for agency commentary Procurement - Complete detailed requirements for cable, nodes, and electronics - Initiate RFP process for materials purchases of major significance - Screen key vendor applicants for short list of qualified construction vendors - Validate procurement process | California Broadband Cooperative, Inc. | California Broadband encountered challenges with several federal agencies whose programmatic requirements exceeded those originally anticipated. Both the Bureau of Land Management and the United States Forest Service had stringent Section 106 requirements requiring extensive field surveys. While these issues have been worked out through inter-agency cooperation with the NTIA, there has been some delays in obtaining guidelines and access to their jurisdictions. In addition, extensive discussions have been required with Department of Fish and Wildlife to address Desert Tortoise habitat concerns. As a result, a complete Environmental Assessment was not filed and revisions are underway in the Third Quarter. The BTOP project office is fully aware of these issues and have been actively supporting their resolution, which appears imminent. | Environmental Assessment: Since the critical path of the entire project is agency cooperation in the environmental studies and getting their approval, our primary focus will be to tightly manage deliverables. Our project plan is to obtain FONSI and CEQA authorizations by October, necessitating good inter-agency cooperation. BTOP assistance in this is already in place. Network Design Potential challenges to network design is if agencies have unique or unanticipated design requirements in the permits or as a result of the environmental assessment. These matters can be resolved locally without BTOP involvement. Rights of Way We anticipate some challenges to intervals in obtaining rights of way from the City of Los Angeles and some private parties. We have addressed this by hiring Right of Way agents familiar with Department of Water and Power processes, will pursue interim licensing agreements that will not impeded construction timing (later following with Right of Way), and by escalating issue to political leadership in the City of Los Angeles (Mayor's office and City Council). There may be process delays on Native Lands with local tribes and the Bureau of Indian Affairs, due to local administrative challenges. While we have redoubled energy around these, we may need some assistance from BTOP, should the Bureau of Indian Affairs need guidance. | TRUE
NT10BIX5570098 | 2011 | Q2 | Q2 - 2011 | Grants Administration â€¢ Obtained IRS non-profit status letter â€¢ Obtained approval of Justification of Non-Competitive Bid for contractor insurance program â€¢ Worked with Nevada Hospital Association on Asset sharing â€¢ Conducted weekly meetings with National Telecommunications and Information Administration (NTIA) Federal Program Officer â€¢ Conducted status meetings with NTIA Administration on National Environmental Policy Act (NEPA) issues â€¢ Hosted Federal Program Officer for annual on-site visit Network Planning and Engineering â€¢ Negotiated conduit system access for section of route between Reno and Carson City â€¢ Finalized terms and conditions for Conduit system in Carson and Douglas Counties (NV) â€¢ Completed refinement of alignment through Owens Valley, China Lake and Highway 58 to meet Caltrans, State Lands Commission and Agency requirements â€¢ Initiated detailed working drawings and methodologies acceptable to permitting agencies. Completed 24 mile section prototype â€¢ Acquired fleet of engineering and administrative vehicles â€¢ Finalized basic node requirements for Request for Proposals and county permit agreements â€¢ Developed staffing plan and executed drafting and outside plant engineering acquisitions â€¢ Developed requirements for cable, conduit and contractor request for proposals Environmental Assessment â€¢ Obtained Survey Permits from all land management agencies â€¢ Completed all biological and cultural surveys for primary and alternative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance, Construction Not Started | NA | NA | No Variance, Construction Not Started | No Variance, Construction Not Started | NA | No Variance, Construction Not Started | No Variance, Construction Not Started | 0 | 13 | 0 | Presently we do not have any signed agreements. | Presently wholesale services are not being provided, construction not startede not being provided, construction not started. | Inyo Networks, Inc. as a vendor for the California Broadband Cooperative will perform all day to day operating activities for the Digital 395 network after the initial network construction phase of the project is complete. These activities will include network management and operation, anchor institution service provisioning, customer care, billing and regulatory support. Inyo Networks Michael Ort - Chief Executive Officer 1101 Nimitz Avenue Vallejo, CA 94592-1014 Phone (510) 599-4062 | 0 | 0 | 0 | 0 | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | 0 | 0 | 0 | 0 | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | 0 | 0 | 0 | 0 | 0 | No Variance, Construction Not Started | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | 3QTR11 will see the completion of the Environmental Assessment and the CEQA documentation, with approvals expected in October. In addition, RFPs will be issued and awarded for conduit, fiber cable, construction of main route, and node buildings. Approximately 70% of the entire project budget will be contracted. Logistics and monitoring systems will be put in place to oversee the project's construction phase. All project personnel will be trained on grant administration, safety, permit compliance, and technical details. An extensive job outreach effort will be designed and executed. | California Broadband Cooperative, Inc. | Environmental Assessment: Project had significant issues accessing federal lands for permits and getting agency cooperation on cultural studies. This issue was resolved by NTIA intervention in developing a Programmatic Agreement, Memorandum of Understanding and engaging participating agencies. Network Design Primary challenge in network was to establish a final alignment. This was accomplished by obtaining Orthophotographic maps from various sources, and conducting an on-the-ground survey of entire route and plotting for EA and baseline engineering design. There was no NTIA involvement in these matters. Rights of Way We encountered issues with the City of Los Angeles and some private parties. We escalated the matter to leadership at the City of Los Angeles and have begun seeing progress. We will obtain a Right of Entry and Permission to Construct for the 68 miles of their land, with processes beginning to become clarified. We have made significant progress with all tribal lands and have engaged the BIA. NTIA involvement with tribal organizations has been effective in getting their attention. Additional difficulties resolving conflicts between Department of Transportation requirements and environmental issues adjacent to roadways. | Environmental Assessment: Since the critical path of the entire project is agency cooperation in the environmental studies and getting their approval, our primary focus will be to tightly manage deliverables. Our project plan is to obtain FONSI and CEQA authorizations by October, necessitating good inter-agency cooperation. NTIA assistance in this is already in place assisting with Programmatic Agreements with Federal Agencies, SHPO and Tribal organizations. Network Design Department of Transportation agencies have set requirements contrary to environmental needs which are being resolved. These are being resolved locally with State Officials without NTIA involvement. Rights of Way Rights-of-Way through tribal allotments have been noted in the Nevada and Fort Independence reservation areas of the route. Fort Independence has been resolved with a work around and BIA involvement has been solicited in Nevada. Rights of way from the City of Los Angeles has been escalated to City Council members and agreements are in place with 2 private owners. | TRUE
NT10BIX5570098 | 2011 | Q3 | Q3 - 2011 | Grants Administration â€¢ Established Joint Construction Agreement Nevada Hospital â€¢ Hosted NTIA on two field visits to tribes and other agencies â€¢ Changed from Reimbursement to Advanced Payment drawdown method Legal and Regulatory â€¢ Drafted and Filed California Certificate of Public Convenience and Necessity â€¢ Completed Conduit Agreements with Douglas County and Zayo Group, LLC. Network Planning and Engineering â€¢ Finalize 152 miles backbone working drawings â€¢ Acquired digital photographic imagery for remaining 20% of route â€¢ Resolved Caltrans design issues and work print specs â€¢ Finalized Node locations, designs, and powering requirements â€¢ Validated all anchor locations and completed 50% of field site surveys â€¢ Completed engineering on Naval Air Weapons Station China Lake Environmental Assessment â€¢ Completed and Circulated Draft Environmental Assessment for Agency Comment â€¢ Completed Government-to-Government Consultations with Tribes â€¢ Completed Public Comment Cycle for California Environmental Quality Act â€¢ Submitted pre-construction notices to California carriers â€¢ Completed Biological Technical Report â€¢ Completed approval of Programmatic Agreement â€¢ Completed Storm Water Pollution Prevention Plan â€¢ Submitted Draft Biological Assessment to National Telecommunications and Information Administration for United Stated Fish and Wildlife Services review Project Management â€¢ Purchased and Created Customer Relationship Management System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction not started | NA | NA | No Variance, Construction Not Started | Construction not Started | NA | Construction not Started | No Variance, Construction Not Started | 1 | 12 | 80 | ZAYO Group, LLC. ZAYO Group has purchased wholesale middle mile dark fiber from us between Reno and Barstow. | Presently wholesale services are not being provided, construction not startee not being provided, construction not started | Inyo Networks is presently selected as contractor who will operate entire network upon completion and pending independent CBC Board approval. Michael Ort - Chief Executive Officer 1101 Nimitz Avenue Vallejo, CA 94592-1014 Phone (510) 599-4062 | 0 | 0 | 0 | 0 | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | 0 | 0 | 0 | 0 | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | Construction Not Started | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | Significant achievements for the next quarter will include the anticipated approval of the mitigated negative declaration by the California Public Utilities Commission and the Finding of No Significant Impact is expected to be issued by National Telecommunications and Information Administration. The California Certificate of Public Convenience and Necessity is expected to be issued for California Broadband Cooperative. License agreements are anticipated from federal, state and local land management agencies. Logistics for constructions operations will be implemented. Key material items will be staged and prime contractor awards will be announced. Since we do not expect to have environmental permits until December and construction will not start in Q4 2011, we will not have any new network miles deployed or leased and we will not have any Community Anchor Institutions connected. We expect to close on atleast one agreements with a last mile provider in Q4 2011. | California Broadband Cooperative, Inc. | We face continuing challenges from federal and state of California agencies in satisfying their constantly evolving environmentally related data requirements. | Our planned success is predicated on the issuance of the environmental permits, receiving rights of entry by Department of Water and Power (fee issues) and Department of Defense (right of entry and satisfying their environmental reporting requirements), and the resolution of Tribal Right of Way issues in Nevada. We also need to resolve the mitigation requirements of the Fish and Game and Fish and Wildlife services. Broadband Technology Opportunities Program staff is already engaged in all of these matters. | TRUE
NT10BIX5570098 | 2011 | Q4 | Q4 - 2011 | Grants Administration â€¢ Completed CBC annual financial audit â€¢ Initial Praxis sub-recipient audit completed complete â€¢ Held November Board Meeting with independent directors Legal and Regulatory â€¢ Received California Certificate of Public Convenience & Necessity â€¢ Completed negotiations and received approval on License Agreements with Mono and Inyo Counties â€¢ Completed negotiations on Zayo fiber agreement â€¢ Completed Pole & Conduit agreements with Verizon and ATT Network Planning and Engineering â€¢ Finalized 72 of 82 segment working drawings for backbone â€¢ Submitted all District 9 drawings for Encroachment permits â€¢ Completed site plans for all but one node site â€¢ Completed all fiber assignment plans Environmental Assessment â€¢ Received CA Environmental Quality Act approval â€¢ Finalized Programmatic Agreement & identified communication plan â€¢ Identified and mapped all cultural sites â€¢ Submitted Draft Biological Assessment for review â€¢ USFWS Reviewed draft Biological Assessment â€¢ Submitted permits for Army Corps of Engineers â€¢ Finalized Storm Water Pollution Prevention Plan, Spill Pollution Prevention Plan and Horizontal Direct Drilling plans â€¢ Submitted permits for Water, Air Quality and CA Fish and Game â€¢ Finalized Monitoring/Mitigation Plan and resolved protocol for Botanical treatments Project Management â€¢ Implemented Project Information and Control Center â€¢ Implemented three depot sites and received 80 trench miles of conduit / vaults Rights of Way â€¢ Finalized US Forest Service and Bureau of Land Management applications â€¢ Completed US Navy survey cadastral for China Lake and Hwy 178 â€¢ Successfully completed Allotment notification in Nevada â€¢ Completed all Tribal Council Meeting for jobs, right of way and services â€¢ Continued extensive negotiations with LA Department of Water & Power for right of way and Fees â€¢ Complete Department of Transportation Encroachment packages, â€¢ Identified and worked with Caltrans to resolve right of way on Hwy 58 Procurement â€¢ Awarded a $1.7MM contract for Node Buildings â€¢ Issued Request for Proposal and Awarded Sub-Recipient Monitoring Contract to ICF â€¢ Issued Request for Proposal for Environmental Monitoring services â€¢ Issued Request for Proposal for engineering services on distribution design â€¢ Received initial bids for fiber electronics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction not started | NA | NA | No Variance, Construction not started | Construction not started | NA | Construction not started | No Variance, Construction not started | 1 | 12 | 80 | ZAYO Group, LLC. ZAYO Group has purchased wholesale middle mile dark fiber from us between Reno and Barstow. | Presently wholesale services are not being provided, construction not started | Inyo Networks is presently selected as contractor who will operate entire network upon completion and pending independent CBC Board approval. Michael Ort - Chief Executive Officer 1101 Nimitz Avenue Vallejo, CA 94592-1014 Phone (510) 599-4062 | 0 | 0 | 0 | 0 | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | 0 | 0 | 0 | 0 | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | Construction Not Started | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | Grants Administration • Complete PIP and submit to NTIA Legal and Regulatory • Meet all California Public Utility Commission requirements for project implementation • Complete license agreement with LADWP • Complete license agreement with Kern County • Pass resolutions for All County License Agreements Network Planning and Engineering • Complete all backbone engineering segments, including cultural site data Complete Distribution Planning and strand allocation • Complete remaining field survey work for Distribution and backbone reroutes • Complete 60% of Distribution working drawings • Validate all anchor locations and completed site surveys • Complete design of Node interiors • Complete network architecture for electronics Environmental Assessment • Receive Finding of No Significant Impact (FONSI) • Finalize Mitigation, Monitoring and Reporting Plan • Finalize all Segment Reports for Environmental Sensitive Areas (Cultural sites) • Complete Biological Opinion with US Fish and Wildlife • Receive permits from Army Corps of Engineers, Water Quality Boards, and CA Fish and Game for water shed management • Receive approval on Storm Water Pollution Prevention Plan for CA and NV • Implement Mitigation and Monitoring Controls with selected vendor Project Management • All Depots actively receiving supplies • 175 miles of fiber cable to be shipped or received • Receive conduit, vaults and related supplies for 240 trench miles • Hire, train and deploy field inspectors • Complete Project Tracking database • Deploy ARRA signs on route Rights of Way • Issue USFS and BLM special use permits • Complete all permits for China Lake completed • Receive all BIA permits issued, Complete permission to use Allotment lands completed • Complete LADWP Agreement and Permission to Construct • California and Nevada DOT Encroachment Permits to be reviewed and granted • Purchase all Nevada private easements • Resolve rights of way issues on Hwy 58 Procurement • Award Mitigation and Monitoring Contract to Vendor • Award Contract for Electronics Vendors and issue purchase orders • Issue RFP and award for Splice Cases and Apparatus • Acquire Placing vehicles and equipment • Award contract for Node site preparation • Acquire node sites Network Construction • Site preparation underway in several locations on route • Execute pre-construction requirements for Monitoring and Mitigation Requirements • Begin underground conduit in 20 pre-cleared segments in the Programmatic Agreement. Key Indicators • New network miles deployed - 0 • New network miles leased - 0 • Total CAI subscribers served (CAIs connected) - 0 • Number of signed agreements with broadband wholesalers or last mile providers - 1 | California Broadband Cooperative, Inc. | Delays in obtaining permits from Federal agencies have delayed FONSI and subsequent progress in construction. Contractors are in place, materials have been in production and delivered; engineering products have met all agency standards and have been certified. BTOP staff has already been assisting in moving permitting processes forward. | Principle challenge for the quarter will be to abbreviate execution of revised Programmatic Agreement and review of Site Avoidance Plans. While labor, materials, and logistics will be in place, the primary scheduling challenges will be due to complete all permits and meet mitigation requirements along the route. BTOP support is in place for these issues. | TRUE
NT10BIX5570098 | 2012 | Q1 | Q1 - 2012 | Grants Administration â€¢ Submitted Quarterly and Annual Reports â€¢ Submitted Performance Improvement Plan â€¢ Prepared all California Public Utilities Commission Financial Documents for Matching Funds Disbursement â€¢ Initiated first meetings with vendor for Sub-Recipient Monitoring â€¢ Conducted Quarterly California Broadband Cooperative Board Meeting Legal and Regulatory â€¢ Established State Policy treating Proscriptive Easements to include Fiber Optic cable â€¢ Obtained Nevada 401 Water Quality Certification â€¢ Acquired Carson City, Douglas & Washoe County Waterway Permit â€¢ Acquired Waste Discharge ID for State Storm Water Permit in CA â€¢ Biological Opinion issued by United States Fish & Wildlife â€¢ Obtained San Bernardino County Flood Control District Permit â€¢ Finalized node building permit applications Network Planning and Engineering â€¢ Integrated Environmentally Sensitive Areas into Engineering Design â€¢ Engineered laterals for Ridgecrest, Mammoth, Bishop and Bridgeport â€¢ Node Site Engineering Complete â€¢ Node Powering and Equipment Designs Completed Environmental Assessment and Permits â€¢ Three additional signatories added to Programmatic Agreement â€¢ Completed Plant Protocol for Bureau of Land Management, United States Forest Service and California Department of Fish and Game â€¢ Segment Report Groups 0-2 circulated for review by agencies â€¢ Obtained Nevada 401 Water Quality Certification â€¢ Acquired Carson City, Douglas & Washoe County Waterway Permit â€¢ Acquired Waste Discharge ID for State Storm Water Permit in CA â€¢ Biological Opinion issued by United States Fish & Wildlife â€¢ Obtained San Bernardino County Flood Control District Permit â€¢ Obtained NV Dept of Environmental Protection Permit â€¢ Initiated Negotiations with CA Water Boards and Dept of Fish and Game â€¢ Permits issued by US Army Corps of Engineers â€¢ Decision Documents drafted for United States Forest Service and Bureau of Land Management â€¢ Final Environmental Assessment Draft submitted to National Telecommunications and Information Administration Project Management â€¢ Implemented Project Database â€¢ Release Pre-Construction Public Notices â€¢ Contractor Project Conference conducted â€¢ Finalized Methods & Procedures for Inspectors and Monitors â€¢ Logistics and resources identified and in place for materials deployment â€¢ Finalized Construction Project Schedule Rights of Way / Licenses â€¢ American Recovery and Reinvestment Act Sign Approval by NV Department of Transportation â€¢ Bureau of Indian Affairs: Notified, Surveyed, and obtained approval for NV allotments â€“ issued 600 letters â€¢ Bureau of Indian Affairs:: Submitted Legal definitions and surveys for CA tribal agreements â€¢ Sent Resolution packages to all 7 tribes; obtained for Bridgeport and Lone Pine â€¢ Encroachment Permits for NV Department of Transportation and Caltrans technical reviews complete. â€¢ LA Department of Water & Power: Obtained Grants Right-of-Entry â€¢ Acquired Encroachment Permits and Master Agreements for Mono, Inyo, San Bernardino and Kern Counties â€¢ Submitted Encroachment Permits with Douglas and Carson Counties (NV) â€¢ Acquired San Bernardino County Flood Control Encroachment Permit â€¢ Acquired Encroachment Permits for Cities of Barstow, Mammoth, â€¢ Private Permits or Right of Way acquired for Bently, Peri, and Mason Properties (complete) â€¢ Acquired all 4 Crossing Agreements â€¢ CA State Lands Commission Lease Agreement Fully Executed â€¢ NV State Lands Commission applied and expedited â€¢ Zayo Group Conduit Use Agreement Fully Executed Procurement â€¢ Contracts awarded for Underground Construction of Backbone â€¢ Node Request for Proposal Awarded â€¢ 165 trench miles of Conduit received â€¢ 104 Concrete vaults received â€¢ 117 miles of 432 fiber received â€¢ Request for Qualifications for electronics issued â€¢ Construction Vehicle Request for Proposal Issued and Awarded â€¢ Monitoring and Mitigation Contract Awarded (AECOM) â€¢ Sub-Recipient Monitoring Contract Awarded (IFC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Variance of 180 miles from Baseline plan, This is due to the extended time for getting the Findinding of No Significant Impact and other environmental clearance, therefore we cannot start construction | NA | NA | No Variance | Variance of 180 miles from Baseline plan, This is due to the extended time for getting the Finding of No Significant Impact and other environmental clearance, therefore we cannot start construction | NA | Variance 15, Construction not started | No Variance | 1 | 12 | 80 | ZAYO Group, LLC. ZAYO Group has purchased wholesale middle mile dark fiber from us between Reno and Barstow. | Presently wholesale services are not being provided, construction not started | Inyo Networks is presently selected as contractor who will operate entire network its upon completion. Michael Ort - Chief Executive Officer 1101 Nimitz Avenue Vallejo, CA 94592-1014 Phone (510) 599-4062 | 0 | 0 | 0 | 0 | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | No Variance, Construction Not Started | 0 | 0 | 0 | 0 | Variance 3, Construction Not Started | Variance 1, Construction Not Started | Variance 2, Construction Not Started | Construction Not Started | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | It is our expectation that the Finding of No Significant Impact, associated Cultural Programmatic Agreement Segment Reports and remaining outstanding permits will all be secured allowing for project construction to start. Underground conduit placement will start in three contractor bid segments, node site construction work will start and be completed. A distribution construction Request for Proposal will be awarded in addition to the Electronic Equipment award. All Anchor site pre-surveys will have been completed and a list of final anchors to be provisioned will have been finalized. We will not deploy any miles of fiber and will not connect any community anchor institutions. We plan on signing one broadband wholesaler/last mile provider agreement. | California Broadband Cooperative, Inc. | Persistent delays in obtaining permits from State and Federal agencies have delayed the Finding of No Significant Impact and approval of Programmatic Agreement Segments Reports. Underground contractor firms are being impacted by a continued delay in the project start date. Project readiness evaluations have tested our ability to start with little issues identified. BTOP staff has been working extensively with us and agencies to get permits approved. | Principle challenge for the quarter will be to close on the Finding of No Significant Impact and obtaining agreement with agencies on procedural issues relating to the Programmatic Agreement. Once construction begins, the coordination of all the environmental monitoring along the project in such a way that we comply and protect the public lands while meeting our delayed project schedule. | TRUE
NT10BIX5570098 | 2012 | Q2 | Q2 - 2012 | Legal and Regulatory â€¢ Acquired all city and county business licenses â€¢ Received Inter-Exchange Access Customer from National Exchange Carrier Association â€¢ Received Operating Company Number for both Nevada & California from Telcordia Network Planning and Engineering â€¢ Engineered 237 Community Anchor Institutions & signed 30 Access Agreements â€¢ Completed distribution engineering design Environmental Assessment â€¢ Received National Telecommunications and Information Agency Finding of No Significant Impact â€¢ Received both Forest Service Decision Notices & Findings of No Significant Impact â€¢ Finalized Master Cultural Resources Report â€¢ Segment Report Group 0 approved; submitted Groups 1 through 4 Rights of Way â€¢ Acquired Nevada Department of Energy & Power Right of Entry for Douglas County â€¢ Finalized Edwards Air Force Base Easement â€¢ Submitted China Lake Grant of Easement â€¢ Acquired Nevada and California Bureau of Land Management Right of Way Grants â€¢ Permission to Survey & Damage Waiver â€“Nevada Allotments â€¢ Acquired Zayo Conduit and Dark Fiber Use Agreement Permits â€¢ Granted United States Army Corps of Engineers 404 Permit â€¢ Granted Army Nationwide Permit â€¢ Received California Region Water Quality Control Board Section 401 Permit â€¢ Nevada State Lands Commission approved Carson River bore and State conduit usage Tribal â€¢ Tribal Allotment legal description and appraisals completed â€¢ Resolutions approved by the Benton, Fort Independence, Lone Pine and Bridgeport Tribes â€¢ Backbone Right of Way secured from 1 of 3 tribes â€¢ Developed Tribal Monitoring Plan â€¢ Conducted tribal monitor training Procurement â€¢ Received 392 miles of cable, 286 miles of conduit and 337 vaults â€¢ Awarded Electronics contract â€¢ Awarded Node site preparation contract Logistics â€¢ Depots fully operative and secured â€¢ Completed audits of all depot inventory Communication â€¢ California Public Utility Commission notifications mailed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Variance of 264 miles from Baseline plan. This is due to the extended time for getting the Programmatic Agreement approval; therefor we cannot start construction. | NA | NA | No variance. | Variance of 264 miles from Baseline plan. This is due to the extended time for getting the Programmatic Agreement approval; therefor we cannot start construction. | NA | Variance of 15; construction not started. We will be making a request to remove towers from the project | Variance of 8; construction not started. | 1 | 12 | 80 | ZAYO Group, LLC. ZAYO Group has purchased wholesale middle mile dark fiber from us between Reno and Barstow. | Presently wholesale services are not being provided, construction not started | Inyo Networks is presently selected as contractor who will operate entire network its upon completion. Michael Ort - Chief Executive Officer 1101 Nimitz Avenue Vallejo, CA 94592-1014 Phone (510) 599-4062 | 0 | 0 | 0 | 0 | Variance of 1; construction not started. | Variance of 1; construction not started. | No variance. | Construction not started | 0 | 0 | 0 | 0 | Variance of 46; construction not started. | Variance of 18; construction not started. | Variance of 28; construction not started. | Construction not started | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | N/A | FALSE | N/A | It is our expectation to have Programmatic Agreement Segment approval for Groups 1-7; allowing for remaining outstanding permits to be secured and for project construction to start. â€¢ Underground conduit placement will start in five contractor bid segments. â€¢ Node site construction work will start and be half completed. â€¢ The Distribution RFP will be awarded. â€¢ All Anchor agreements will be approved. â€¢ 58 miles of fiber will be deployed and will connect 0 number of community anchor institutions. â€¢ We plan on signing 0 wholesaler/last miles provider agreement. | California Broadband Cooperative, Inc. | Persistent delays in obtaining permits from State and Federal agencies have delayed the Finding of No Significant Impact and approval of Programmatic Agreement Segment Reports. Underground contractor firms are being impacted by a continued delay in the project start date. Project readiness evaluations have tested our ability to start with little issues identified except for snow in the higher elevations of the project. BTOP staff have been working extensively with us and agencies to get permits approved. | The principle challenge for the quarter will be securing the Programmatic Agreement, final permits, and tribal agreements. Beginning October 2012, early snowfall may impede construction in high altitudes in the Northern route in Mono and Douglas Counties. NTIA is aware of the Programmatic Agreement and Tribal issues and working with CBC on approvals. | TRUE
NT10BIX5570098 | 2012 | Q3 | Q3 - 2012 | Legal and Regulatory â€¢ Re-negotiated CalTrans District 8 Master Services Agreement â€¢ Signed conduit attachment agreement with Nevada Energy â€¢ Negotiated Rights of Way for the City of Ridgecrest â€¢ Signed interconnection agreements with Level 3 Communications Network Planning and Engineering â€¢ Submitted Underground Service Alert application â€¢ Engineering completed for all Community Anchor Institutions â€¢ Completed engineering for all distribution areas Environmental Assessment â€¢ Programmatic Agreement Segment Groups 0 to 4 approved â€¢ Master Cultural Resources Report Approved by NTIA and Signatories Rights of Way â€¢ Progressive CalTrans permits acquired concurrent with Programmatic Agreement Cultural Segment approvals â€¢ Obtained Douglas County Right of Way Agreement â€¢ Obtained Carson City Right of Way Agreement â€¢ Obtained Rights of Way from Seven Tribal Lands â€¢ Obtained Rights of Way from Naval Air Weapons Station, China Lake Permits â€¢ All permits received other than ongoing encroachment/building permits from Department of Transportation in Nevada and California â€¢ Humboldt Toyiabe National Forest, Inyo National Forest, Bureau of Land Management of Bishop, CalTrans District 8 and 9, San Bernardino Flood Control, City of Barstow, Mono County pre-construction meetings completed â€¢ Submitted permit applications for all nodes; obtained permits for seven nodes Tribal Monitoring â€¢ Tribal Monitoring Plan finalized and implemented â€¢ Eight Tribal Monitors hired as Contractors from the Washoe and Bridgeport Tribes â€¢ Began Tribal monitoring of Construction Operations in Mono County â€¢ Initiated over 400 allotment owners for Rights of Way through Washoe Allotment properties Procurement â€¢ Received all project backbone cable, 368 miles of conduit and 469 vaults â€¢ Receive 50% of node electronics from vendor Construction â€¢ Notice to Proceed issued to (3) sub-contractors for underground construction (Zayo, RBC and Westech) â€¢ Notice to Proceed issued to RADCO for Node Construction â€¢ Notice to Proceed issued to AECOM for construction monitoring â€¢ 44 trench-miles (9%) of the backbone 484 miles of conduit placed â€¢ American Recovery and Reinvestment Act signs are placed along route in approved Programmatic Agreement Segments â€¢ Zayo began placing and splicing fiber cable in segment N101, completing 10 miles â€¢ Node construction began in Reno, Carson, Coleville, and Bridgeport | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | (Variance of 368 miles) Programmatic Agreement approvals are impacting the construction schedule. | N/A | N/A | No variance | (Variance of 368) Programmatic Agreement approvals are impacting the construction schedule. The fiber installed is in existing conduit. | N/A | (Variance of 15) Programmatic Agreement approvals are impacting the construction schedule. We will be removing all new towers as the result of feedback from interested parties during the 30 day comment period of the Environmental Assessment Process (NEPA and CEQA) | (Variance of 18) Programmatic Agreement approvals are impacting the construction schedule. | 4 | 12 | 80 | ZAYO Group, LLC. - Purchased wholesale middle mile dark fiber between Reno and Barstow. Level 3 - Signed interconnection agreement for collocation and peering for Barstow and Reno. AT&T Nevada â€“ Signed interconnection agreement for NV. Verizon California â€“ Signed interconnection agreement for CA. | Presently wholesale services are not being provided. | Inyo Networks is presently selected as contractor who will operate entire network its upon completion. Michael Ort - Chief Executive Officer 1101 Nimitz Avenue Vallejo, CA 94592-1014 Phone (510) 599-4062 | 0 | 0 | 0 | 0 | Variance of 1; construction just started. | Variance of 2; construction just started. | Variance of 1; construction just started. | Construction just started | 0 | 0 | 0 | 0 | Variance of 128; construction just started. | Variance of 28; construction just started. | Variance of 100; construction just started. | Construction just started | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | N/A | FALSE | N/A | It is our expectation to have Programmatic Agreement Segment approval for Groups 5-8; allowing for remaining outstanding permits to be secured and for project construction to continue. â€¢ Underground conduit placement will continue in five contractor bid segments. â€¢ All but two node sites will be completed (the remaining are held up due to Section 106 schedule). â€¢ Distribution RFPs will be awarded. â€¢ All Anchor access agreements will be approved. â€¢ 160 miles of fiber will be deployed and will connect 10 community anchor institutions. â€¢ Two network spans (between nodes) will be connected and tested. â€¢ We anticipate signing one new broadband wholesaler/last mile provider agreement with Suddenlink consisting of 10G wave and dark fiber. This will produce $30,000 in monthly reoccurring and $500,000 in IRU's | California Broadband Cooperative, Inc. | The Programmatic Agreement continues to slowly drive the obtainment of encroachment permits and the underground construction schedule with winter weather and deep snow approaching rapidly. Once Group Segment 5 is released, underground construction will drive the schedule and fiber will be placed continuously. | The principle challenge for the fourth quarter will be finalizing studies for the Programmatic Agreements, finalizing tribal agreements, and obtaining permission for Route changes from the NTIA. Snowfall will impede construction and cable placement in high altitudes in the Northern route in Mono and Douglas Counties. NTIA is aware of the Programmatic Agreement and Tribal issues and working with CBC on approvals. | TRUE
NT10BIX5570098 | 2012 | Q4 | Q4 - 2012 | Environmental: â€¢ Programmatic Agreement Segment Group 5 approved and 4 out of 7 approved in Group Segment 6 â€¢ Tribal Monitors hired from Big Pine, Bishop, Benton, Lone Pine and Independence Tribes â€¢ Tribal monitoring requirements completed on 27 segments â€¢ Extensive monitoring of Desert Tortoise and Mojave Ground Squirrel habitat during construction Rights of Way â€¢ Implemented and completed Bureau of Indian Affairs process for Rights-of-Way approvals on Washoe Allotments and tribal lands held in trust â€¢ Rights of Way approved by all California Tribes â€¢ Ten Caltrans and two Nevada Department of Transportation segment permits acquired â€¢ Town of Mammoth Lake & Nevada State Lands Commission Permits acquired â€¢ Mono County License Agreement amended, licenses submitted for Inyo and Kern Counties â€¢ Rights of Way acquired for Southern California Edison, China Lake and Edwards Air Force Base Contract Administration: â€¢ Request for Proposal awarded for Distribution conduit â€¢ $.5.5 Millions in invoices processed for underground construction and environmental studies Engineering: â€¢ Reissued all engineering drawing to include Environmentally Sensitive Areas to meet programmatic agreement requirements â€¢ Completed fiber optic allocations plans for backbone, distribution and anchors â€¢ Produced working drawing for 50% of fiber cable plant Materials and Logistics: â€¢ Established new logistics center in Coso in preparation for shut down of Kramer Junction depot â€¢ Instituted monthly inventory of materials against project documentation and database Construction: â€¢ 163 miles or 34% of the backbone conduit installed â€¢ 109 miles of fiber cable installed of those, 99 miles are spliced and tested. â€¢ 13 segments completed â€¢ Construction started in Nevada â€¢ Conduit constructed on the China Lake Naval Base â€¢ Four American Recovery & Reinvestment Act signs installed on California route Five nodes sites completely constructed â€¢ Electronics received for backbone system | 109 | 0 | 0 | 0 | 109 | 0 | 0 | 0 | Variance of 391 miles from Baseline Plane due to permit delays | NA | NA | No Variance | Variance of 391miles from Baseline Plane due to permit delays | NA | Variance of 15 towers -We will be removing all new towers from project due to Stakeholder concerns during the Environmental Assessment | Variance of 36 due to no Anchor or Point of Interconnections completed. This work will begin in February. | 5 | 11 | 80 | ZAYO Group, LLC. - Purchased wholesale middle mile dark fiber between Reno and Barstow. Suddenlink - Signed agreement for dark fiber Level 3 - Signed Interconnection Agreement for collocation and peering for Barstow and Reno AT&T Nevada - Signed interconnection agreement for NV Verizon California - Signed interconnection agreement for California | Presently wholesale services are not being provided. | We were directed by the CBC Board of Directors to establish a greater degree of separation from Inyo Networks as a last mile service provider who could potentially be purchasing wholesale services from CBC. The board felt there could be potential perceived conflict of interest of having Inyo Network manage CBC operation and being a competitor for other last mile providers. As a result the sub recipient agreement has been revised with regards to the entity managing the CBC network therefore,Praxis Associates is presently designated as the vendor who will operate entire network its upon completion. Michael Ort - Chief Executive Officer 1101 Nimitz Avenue Vallejo, CA 94592-1014 Phone (510) 599-4062 | 3 | 0 | 2 | 0 | Ahead by 1 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Variance of 2 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Ahead by 1 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | No services are currently being offered. | 0 | 0 | 0 | 0 | Variance of 175 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Variance of 45 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Variance of 130 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | No services are currently being offered. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Active Ethernet, dark fiber, 10Gbps and wavelength. | FALSE | N/A | Environmental: â€¢ Complete remaining Programmatic Agreement â€¢ Complete tribal monitoring plan â€¢ Obtain permission from NTIA for reroute changes â€¢ Finalize CEQA approval for route changes Rights of Way: â€¢ Obtain final ROW Approval from BIA for Nevada Tribal lands â€¢ Finalize license agreements in the towns of Bishop, Ridgecrest and Mammoth â€¢ Finalize county Licenses/ROW in Mono, Inyo and Kern Counties â€¢ Complete remaining private ROW Contract Administration: â€¢ Realign major contract awards for Mono County â€¢ Complete final negotiations on electronics â€¢ Finalize contracts for all distribution and Anchor work â€¢ Submit CAI and POI change request AAR to NTIA Engineering â€¢ All engineering designs for anchors and POIâ€™s complete â€¢ Complete engineering designs for small communities Materials and Logistics: â€¢ Complete final purchases of distribution materials â€¢ Redeploy cable closer to work operations â€¢ Close Kramer Jct depot and deactivate Gardnerville depot Construction: â€¢ Construct and test conduit and cable from red mountain to Coso Jct, â€¢ Construct and test cable from Garnerville to Carson City â€¢ Complete construction of Bishop, Barstow and Ridgecrest nodes â€¢ Complete BB route conduit installation between Bishop and Lone Pine â€¢ Begin site prep for Olancha Node â€¢ Install and test electronics in available nodes â€¢ Complete and test conduit and cable installation from Bridgeport to June Lake â€¢ Complete distribution and anchor network in Ridgecrest. â€¢ We plan to deploy 225 miles of fiber â€¢ We plan to connect 25 anchors â€¢ We will have 3 broadband wholesaler/last mile provider agreements signed | California Broadband Cooperative, Inc. | Considerable delays in project due to extended period of Programmatic Agreement reviews and agency challenges to project schedule due to internal priorities. Fourth Quarter presented weather impacts on productivity due to high altitude construction during sub-zero weather resulting from late permits. The NTIA has been working with us on these issues and are aware of these challenges. | Permit delays and winter work will not be lifted until the March timeframe. This impacts the project both in the Southern portion (permits) and in the northern section (Mono County and Nevada, due to winter.). NTIA is already assisting in permits. Once these impediments are lifted, our contractors and work crews will operate at full capacity. | TRUE
NT10BIX5570098 | 2013 | Q1 | Q1 - 2013 | NTIA/Environmental: â€¢ Programmatic Agreement Segment Groups 7, 8, 9 and 10 approved by the NTIA except for segments M116, M120 and M122, approval of which was withheld which were not approved by the Inyo National Forest â€¢ Submitted Backbone and N109 Route changes to the NTIA â€¢ Resolved federal trespass issues with the Bureau of Land Management trespass issue â€¢ Negotiated changes in California Department of Fish and Game stream bed alteration Permit to include parallel construction. â€¢ Managed Sage Grouse & Goshawk restricted work areas successfully ROW, Permits/Agreements: â€¢ Amended backbone and distribution agreements with Mono, Inyo and Kern Counties â€¢ Acquired City of Reno Permit for N101 â€¢ Resolved 2 private ROW issues â€¢ Acquired Southern California Edison Penstock License Agreement â€¢ Acquired NDOT Permits for N106, N108, N109A, N107, N111, N112, and N113 â€¢ Acquired CalTrans Permits for S104B, I108, I109, I115, I116 M112 (bore under LA Department of Water and Power tunnel) â€¢ Acquired Douglas County Permits for N109B and N110 â€¢ Acquired Carson City permits for N105, N106 and N107 â€¢ Acquired Bureau of Indian Affairs approval for the Pinenut Allotments (N112 & N113) â€¢ Tribal Agreements â€¢ Acquired Grant of Easement for the Washoe Tribal lands: N109A â€“ Silverado Parcel and N111 â€“ Washoe Ranch Construction: â€¢ Placed additional 134 miles of backbone conduit or 23% for a cumulative total to 302 miles â€¢ Placed additional 88 miles of fiber cable or 15% for a cumulative total to 197 miles â€¢ Placed 181 barrel vaults â€¢ Completed 8 additional conduit segments â€¢ Completed site construction and placement of 2 additional node shelters â€¢ Completed City of Ridgecrest buried distribution conduit placement Contract Administration: â€¢ Awarded Distribution Contracts in the City of Ridgecrest, Mammoth and Bishop â€¢ Closed off contract for Mono County and re-awarded incomplete contract to new vendors. | 197 | 0 | 0 | 0 | 197 | 0 | 0 | 2 | Variance of 356 miles to target of 553 miles. The variance is due to limitations on conduit construction related to weather, environmental permits, and encroachment approvals from the Department of Transportation in Nevada and California. | NA | NA | Variance of 30 from target of 30 miles due to network design changes that eliminate the original need for 30 miles of fiber leasing. | Variance of 356 miles to target of 553 miles. The variance is due to limitations on conduit construction related to weather, environmental permits, and encroachment approvals from the Department of Transportation in Nevada and California. This network consists of all new fiber miles. | NA | Variance of 15 towers. We have removed all new towers planned due to stakeholders concerns during the Environmental Assessment | Variance of 66, since interconnections have been made at network end-point in Reno to Plumas Sierra and Level 3 | 5 | 11 | 80 | ZAYO Group, LLC. - Purchased wholesale middle mile dark fiber between Reno and Barstow. Suddenlink - Signed agreement for dark fiber Level 3 - Signed Interconnection Agreement for collocation and peering for Barstow and Reno AT&T Nevada - Signed interconnection agreement for NV Verizon California - Signed interconnection agreement for California | Presently wholesale services are not being provided. | Praxis Associates is presently designated as the vendor who will operate entire network its upon completion. This party is a sub-recipient of the BTOP award and will operate as a contractor when operating the network. Michael Ort - Chief Executive Officer 1101 Nimitz Avenue Vallejo, CA 94592-1014 Phone (510) 599-4062 | 3 | 0 | 2 | 0 | Ahead by 1 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Variance of 2 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Ahead by 1 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | No services are currently being offered. | 0 | 0 | 0 | 0 | Variance of 237 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Variance of 55 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Variance of 146 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | No services are currently being offered | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Active Ethernet, dark fiber, 10Gbps and wavelength. | FALSE | N/A | The project will complete all underground construction of the backbone network (except perhaps in several segments of the Inyo National Forest). All conduit and cabling will be completed in the major communities of Ridgecrest, Mammoth Lakes, and Bishop. Anchor and points of interconnections will be completed in these communities and at incidental locations along the backbone. All Nodes will be powered and will have electronics installed. Areas that will be the greatest challenge to complete are associated with approximately 30 route changes to anchors, portions of the distribution plan. We expect the remaining route changes to the backbone will be approved by the BTOP program over the next 30 days. We expect to have an additional 100 miles of fiber cable places, 75 anchors connected and 2 additional broadband wholesaler/last mile provider agreements signed | California Broadband Cooperative, Inc. | The principle challenges this project has is the resolution of environmental issues in the Inyo National Forest, changing requirements imposed by Federal and State agencies, and approval of route changes in the backbone and distribution plant. Restraints on this project continue to be administrative oversight by agencies and conflicting compliance obligations, and not technical or physical implementation. The BTOP program team is aware of these issues and has been very helpful in getting them resolved. | Challenges for the next quarter will be completion of Route Change approvals, resolving environmental concerns of the Inyo National Forest, and obtaining Rights-of-Way approvals from the Los Angeles Department of Water and Power, the Inyo National Forest and the Bureau of Land Management. Additional concerns involve cash flow issues resulting from the structure of the California Advanced Services Funds reimbursement model and turn around time related to matching funds. Budgetary uncertainty due to agency requirements and permit fees will present challenges in managing project cash flow. | TRUE
NT10BIX5570098 | 2013 | Q2 | Q2 - 2013 | Digital 395 Project Accomplishments â€“ 4/1/13 â€“ 6/30/13 Construction: â€¢ Placed an additional 119 miles of backbone conduit for a cumulative total of 421 miles â€¢ Placed an additional 152 vaults for a cumulative total of 333 vaults â€¢ Completed an additional 32 segments â€¢ Placed an additional 156 miles of backbone fiber cable for a cumulative total of 348 miles â€¢ Completed remaining nodes for a total of 11 â€¢ Placed approximately 16 miles of distribution conduit (Ridgecrest, Bishop & Lee Vining & Bridgeport Central) â€¢ Placed and spliced 6 miles of distribution cable â€¢ Provisioned all of or part of facilities for (48) CAIs â€¢ Installed electronics at five nodes â€¢ Established first interconnect with Plumas Sierra and Level 3 Communications Right of Way: â€¢ Acquired needed permits/riders from Cal Trans for highway crossings in Big Pine, Crowley, Bishop, Inyokern, Mammoth Lakes and Benton â€¢ Acquired distribution permits from Mono County for Lee Vining and Kern County for Inyokern â€¢ Acquired Grant of Easements from the Bishop and Bridgeport Tribes â€¢ Resolved Parallel Drainage issues with Nevada Department of Transportation â€¢ Bureau of Land Management approved six distribution and anchor routes Environmental â€¢ Obtained approvals from NTIA for route changes in N109, M116 (State Route 203) â€¢ Identified and addressed ESA breach in M115 â€¢ M116 cleared for Construction â€¢ Re-surveyed M120 and M122 due Inyo National Forest request â€¢ Conducted studies and obtained Bureau of Land Management Notice to Proceed for I101 & M123, signaling resolution to Wilderness Study Area incursion and resolution on endangered plant (Milk Vetch) â€¢ Submitted and obtained shortened bore distances for I-119 â€¢ Initiated discussions with California Department of Fish and Wildlife over Mitigation ratio reduction. â€¢ Began closure procedures on Desert Tortoise, Storm Water Pollution Prevention Plan â€¢ Conducted on-going discussions over environmental requirements with Inyo National Forest and Caltrans Administrative: â€¢ Filed for supplemental project funding from the California Public Utilities Commission â€¢ Filed for project extension with the NTIA â€¢ Became active members of USA Dig Alert for Southern and Northern California and Nevada â€¢ Secured Network Operating Center and Interconnect space at 200 South Virginia â€¢ Hosted NTIA and California Public Utilities Commission on site visit Logistics: â€¢ Gardnerville Supply Depot closed | 348 | 0 | 0 | 0 | 348 | 0 | 0 | 4 | Variance of 235 mile to target of 583 miles. While in the baseline plan we list 553, there are 30 miles of fiber no longer leased. The variance is due to late construction start due to Programmatic Agreement requirements and execution, delays in permit issuance and route changes. The latter consist of anchor routes and five changes required on the backbone. | NA | NA | Variance of 30 miles. We will not be leasing the 30 miles of fiber. The fiber is owned by California Broadband and placed in leased Zayo conduit. | Variance of 235 mile to target of 583 miles. While in the baseline plan we list 553, there are 30 miles of fiber no longer leased. The variance is due to late construction start due to Programmatic Agreement requirements and execution, delays in permit issuance and route changes. The latter consist of anchor routes and five changes required on the backbone. | NA | No towers constructed on project. While in the base plan, the towers were removed due to Environmental Assessment requirements. | Variance of 14 due to cable deployed to network end points in Reno and Barstow, Bridgeport and Lee Vining. Points of interconnect will expand next quarter as the result of distribution cable to be deployed. | 6 | 11 | 80 | ZAYO Group, LLC. - Purchased wholesale middle mile dark fiber between Reno and Barstow. Suddenlink - Signed agreement for dark fiber Level 3 - Signed Interconnection Agreement for collocation and peering for Barstow and Reno AT&T Nevada - Signed interconnection agreement for NV Verizon California - Signed interconnection agreement for California Plumas Sierra - Signed internet and collocation agreement | We have signed an agreement with Plumas Sierra (See attachment for details) | Inyo Networks is presently designated as the vendor who will operate entire network its upon completion. This party will serve as a contractor when operating the network. Michael Ort - Chief Executive Officer 1101 Nimitz Avenue Vallejo, CA 94592-1014 Phone (510) 599-4062 | 3 | 0 | 3 | 0 | Ahead by 1 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Variance of 2 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Ahead by 1 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | No services are currently being offered. | 36 | 36 | 0 | 36 | Variance of 201 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Variance of 24 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Variance of 177 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | There is currently no service operational however all subscribers will have up to 1GB Ethernet connection | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Active Ethernet, dark fiber, 10Gbps and wavelength. | FALSE | NA | Digital 395 Planned Project Accomplishments â€¢ Complete backbone route work (all conduit, cable placing and splicing) for Nevada Segments N111, N112, N113 and Mono County Segment M101 â€¢ Complete Environmentally Sensitive Area long bore in Segment I108 and commence required bore in Segment I119. â€¢ Complete cable placement in all northern route segments between Mammoth Lakes, California and Reno, Nevada. â€¢ Complete distribution conduit work in Boron and Inyokern, California. â€¢ Submit formal request for supplemental project funding from the California Public Utilities Commission â€¢ Commence completion of all anchor service trench work in Bishop, California â€¢ Complete all Bureau of Land Management mandated restoration work in Wilderness Study Area affected Segments I101 and M123 â€¢ Install electronics at remaining nodes, commence fiber span and integration testing from Mammoth Lakes, California to Reno, Nevada. â€¢ Acquire Grant of Easement for Bridgeport Tribal Office â€¢ Commence similar work for the Lone Pine Tribal Office â€¢ Obtain NTIA approval for Route Change in Carson City â€¢ Complete final field study for M122 as requested by NTIA and Inyo National Forest â€¢ Submit formal request for supplemental project funding from the California Public Utilities Commission â€¢ Start scaling down Digital 395 Project administrative staff â€¢ Complete closure of Coso Junction Material Depot â€¢ Returned empty Dura-line conduit and OFS fiber reels â€¢ We estimate an additional 91 miles of backbone conduit will be placed for a cumulative total of 512 miles and an additional 133 miles of backbone fiber cable to be placed for a cumulative total of 481 miles. â€¢ We estimate 141 CAIâ€™s will be connected for a cumulative total of 190 CAIâ€™s â€¢ We estimate 2 additional broadband wholesaler/last mile provider agreements will signed | California Broadband Cooperative, Inc. | The project has confronted a number of challenges that had slowed its initiation of construction. The biological and cultural sensitivity of the area, as well as the complexity of working with 47 agencies in these regards, led to a two year process to arrive at the authorization to proceed with construction. More recently, incidental delays relating to permits and the environment have slowed construction, which is almost completed along the 450 mile backbone. Shortly after our initial notice to proceed, another seven months were taken to obtain approvals for most of the route. One nine mile segment has yet to be approved as of the end of this quarter. Cold and snow hindered production in the alpine areas, shortly after the notices to proceed were issued, but once these impediments were resolved, construction has been extremely productive. The BTOP staff has been actively involved in helping to clear these barriers. In addition to procedural issues, the costs of the environmentally-related activities (studies, monitoring, and avoidance) have been substantial (25% of initial project costs), leading to an effort for additional state funding. This is underway and the NTIA has been helpful to the state in explaining the challenges to the project. The project has submitted an application for a time extension, which the BTOP staff could be helpful in approving. | We anticipate delays in applications and approvals for route changes relating to pole route conversions to underground (due to new California Pole Loading calculation guidelines), further information required by the Inyo National Forest, and the completion of construction in about half-dozen small communities and anchor connections. Continued support by the BTOP team in obtaining approvals from federal agencies relating to the Programmatic Agreement. Approval for our time extension would be a key support item. | TRUE
NT10BIX5570098 | 2013 | Q3 | Q3 - 2013 | Construction: â€¢ Placed an additional 80 miles of backbone conduit for a cumulative total of 501 miles. â€¢ Placed an additional 144 vaults for a cumulative total of 477 vaults. â€¢ Completed an additional 20 project segments. â€¢ Placed an additional 155 miles of backbone and distribution fiber cable for a cumulative total of 503 miles. â€¢ Completed 119 CAIs (155 total) and 28 POIs (32 total) service connections. â€¢ Completed installation of electronics at remaining six nodes, began integration and testing . â€¢ The Reno to Mammoth Lakes backbone was turned up, providing service connection to last mile service provider for testing . Right of Way: â€¢ Acquired needed permits from Cal Trans for 2 Inyo and 1 Kern County locations. Environmental â€¢ Finished restoration on Casa Diablo Road (BLM Wilderness Study Area) â€¢ Received clearance and started conduit work on the China Lake Naval Facility. â€¢ Re-surveyed 10 mile backbone segment for a second time in the Inyo National Forest to eliminate high cost long bores . â€¢ Continued discussions over environmental requirements with Inyo National Forest and Bishop Indian Tribe regarding segment long bore strategy. â€¢ Applied for route change into June Lake. â€¢ Received limited clearance to start work in the Inyo National Forest. â€¢ Identified and worked with agencies to conclude anchor site route changes. Administrative: â€¢ Granted project extension by the NTIA â€¢ Submitted application to the CPUC for $10.8 million of additional project funds and received all but three segments needing California Environmental Quality Act approvals. Environmental Quality Act approvals. â€¢ Generated 5 RFPs for incomplete construction segment work. Secured and awarded bids after California Broadband Cooperative Board approval. â€¢ Continued to scale back field and administrative staff. â€¢ Submitted and Approved proportionality Waiver from NTIA â€¢ Annual Audit initiated to satisfy our Special Award Condition Logistics: â€¢ Closed Coso Junction and Big Pine Depot; consolidating materials into Bishop storage areas â€¢ Recycled conduit and cable reels | 503 | 0 | 0 | 0 | 503 | 0 | 0 | 32 | Variance of 82 miles to target of 583 miles. The variance it due to the incompletion of backbone segment M122, side laterals and distribution conduit work which slowed down due to uncertain project funding. | NA | NA | Variance of 30 miles. We will not be leasing the 30 miles of fiber. The fiber is owned by California Broadband and placed in leased Zayo conduit. | Variance of 82 miles to target of 583 miles. The variance it due to the incompletion of backbone segment M122, side laterals and distribution conduit work which slowed down due to uncertain project funding. | NA | No towers constructed on project. While in the base plan, the towers were removed due to Environmental Assessment requirements. | Variance of 36 due to cable deployed to network end points in Reno and Barstow, Bridgeport and Lee Vining. Points of interconnect will expand next quarter as the result of distribution cable to be deployed | 8 | 9 | 80 | ZAYO Group, LLC. - Purchased wholesale middle mile dark fiber between Reno and Barstow. Suddenlink - Signed agreement for dark fiber Level 3 - Signed Interconnection Agreement for collocation and peering for Barstow and Reno AT&T Nevada - Signed interconnection agreement for NV Verizon California - Signed interconnection agreement for California Plumas Sierra - Signed internet and collocation agreement Lone Pine TV - Intenet Access SchatNet - Internet Access and Transport | We have signed an agreement with Plumas Sierra, Lone Pine TV and SchatNet (See Attached) | Inyo Networks is presently designated as the vendor who will operate entire network its upon completion. This party will serve as a contractor when operating the network. Michael Ort - Chief Executive Officer 1101 Nimitz Avenue Vallejo, CA 94592-1014 Phone (510) 599-4062 | 5 | 0 | 3 | 0 | Ahead by 3 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Variance of 2 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Ahead by 1 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | No services are currently being offered. | 155 | 155 | 0 | 0 | Variance of 82 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Variance of 82 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | Variance of 177 - Laterals and anchor connections not complete. End point interconnections have not completed. No operational bandwidth is in service. | There is currently no service operational however all subscribers will have up to 1GB Ethernet connection | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Active Ethernet, dark fiber, 10Gbps and wavelength. | FALSE | NA | Complete all the environmental approvals for the remaining route changes. Complete conduit construction for all laterals, the Benton, June Lake and Walker Communities, Conway Summit and the Pickles Meadows United States Marine Corp Base. We plan to finish placing, splicing and testing all of the remaining backbone fiber cable. We also intend to complete all remaining distribution cable placement, splicing and all remaining Anchor and Points of Interconnection connections. We plan to deploy 570 miles, connect 237 anchors and sign 2 additional broadband wholesaler/last mile provider agreements by the end of the quarter. | California Broadband Cooperative, Inc. | We continued to experience delays in acquiring environmental permits particularly with the Inyo National Forest Service. In addition funding issues became problematic restricting planned work on critical laterals and distribution conduit work. The NTIA has been working with us to complete and approve all remaining route changes. | We will, in fact, over spend the project by 10% as a result of the additional $9.9M funding provided by the California Public Utility Commission. This will allow us to finish construction work for June Lake, Walker, Benton and Johannesburg. Several additional sites including Round Valley, the Lone Pine Tribe extension and Poverty Hills Road work will be completed in the future using California Broadband Cooperative revenues. | TRUE
NT10BIX5570098 | 2013 | Q4 | Q4 - 2013 | Construction/Provisioning: â€¢ Placed an additional 43 miles of conduit for a total of 544 miles â€¢ Placed an additional 59 miles of fiber cable for a total of 562 miles â€¢ Placed an additional 191 vaults for a total of 668 vaults â€¢ Completed conduit construction in (3) additional backbone segments, most notably the long delayed final backbone segment through the Inyo National Forest (M122) â€¢ Splicing completed in 10 backbone segments allowing for complete network turn up â€¢ Completed distribution conduit construction, cable placing and splicing in (9) communities including China Lake Naval Air Weapons Station â€¢ Completed 46 CAIs (182 Total) & 12 POIs (44 Total) service connections â€¢ Electronics installed and configured at all remaining nodes â€¢ Circuit designs and provisioning completed or initiated at 60 anchors and POIâ€™s Right of Way: â€¢ Acquired Bureau of Indian Affairs approval to start construction of the Lone Pine Tribal extension â€¢ Acquired Bramlette private property Right of Way Agreement, the Bureau of Land Management and the Sierra Land Trust approval to commence construction work on M129 in Benton â€¢ Acquired City of Ridgecrest, town of Mammoth and Kern County permits for remaining distribution and anchor sites â€¢ Began closing out agency project construction permits Environmental â€¢ June lake backbone route change approved â€¢ Received full clearance to complete remaining work in M122 delayed by the Inyo National Forest â€¢ Continued to work with the NTIA to conclude Anchor site route changes Administrative: â€¢ Extensive focus on reviewing completed construction as-builts necessary for project closure â€¢ Delivered bi-Monthly Reports on project process to the California Public Utility Commission Staff â€¢ Continued to scale down administrative staff and field personnel Logistics: â€¢ Began process to liquidate un-needed equipment | 562 | 0 | 0 | 0 | 562 | 0 | 0 | 44 | Variance of 21 miles to target of 583. Again, we are realizing that the initial project objective was an engineering estimate not based on actual completed engineering designs which is proving to have been overstated. Actual cable placed to be trued of end of first quarter 2014. | NA | NA | Variance of 30 miles. We will not be leasing the 30 miles of fiber. The fiber is owned by California Broadband and placed in leased Zayo conduit. | Variance of 21 miles to target of 583. Again, we are realizing that the initial project objective was an engineering estimate not based on actual completed engineering designs which is proving to have been overstated. Actual cable placed to be trued of end of first quarter 2014. | NA | No towers constructed on project. While in the base plan, the towers were removed due to Environmental Assessment requirements. | Variance of 24 due to final end service point connections being completed. The remaining interconnection points will be completed in Q1 2014 | 8 | 12 | 80 | ZAYO Group, LLC. - Purchased wholesale middle mile dark fiber between Reno and Barstow. Suddenlink - Signed agreement for dark fiber Level 3 - Signed Interconnection Agreement for collocation and peering for Barstow and Reno AT&T Nevada - Signed interconnection agreement for NV Verizon California - Signed interconnection agreement for California Plumas Sierra - Signed internet and collocation agreement Lone Pine TV - Intenet Access SchatNet - Internet Access and Transport | We have signed an agreement with Plumas Sierra, Lone Pine TV and SchatNet (See Attached) | Inyo Networks is presently designated as the vendor who will operate entire network its upon completion. This party will serve as a contractor when operating the network. Michael Ort - Chief Executive Officer 1101 Nimitz Avenue Vallejo, CA 94592-1014 Phone (510) 599-4062 | 5 | 0 | 3 | 2 | Ahead by 3 - Installation of our backbone has created more competition in the region | Variance of 2 - Still in negotiation with last mile providers to improve access | Ahead by 1 - Installation of our backbone has created more competition in the region | 3 subscribers at 50MB 1 subscriber at 1GB, 1 subscriber at 500MB and 1 subscriber at 2GB | 182 | 182 | 0 | 1 | Variance of 55 - Laterals and anchor connections not complete. End point interconnections have not completed. | Variance of 55 - Laterals and anchor connections not complete. End point interconnections have not completed. | Last Quarter we reported 0 | 3 subscribers at 50MB and 1 subscriber at 1 GB | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Active Ethernet, dark fiber, 10Gbps and wavelength. | FALSE | NA | Complete all conduit, cable placing and splicing on the remaining network. Test and verify the physical connection from all anchors and POI's to the Nodes. Configure network electronics on backbone and nodes to assure ongoing network stability and redundancy. Turn up all services to customer specification. Close-out construction permits and open ongoing operational permits as required by agencies. Transition to operational mode and begin project close-out. We will add 4 miles of conduit for a total of 548, 26 miles of cable for a total of 588 and connect 70 anchors for a total of 271. We will sign 2 broadband wholesaler/last mile provider agreements with Frontier and Race Telecom | California Broadband Cooperative, Inc. | Fortunately with the additional funding provided by the California Public Utility Commission the California Broadband Cooperative was able to complete most of the originally planned project objectives. The only residual area needing prompt resolution by National Telecommunication Infrastructure Association is the approval of the remaining Community Anchor Institution re-route requests. Two months of delay were caused by additional permit requirements by the Eastern Sierra Land Trust in the area between Benton and the Benton Reservation on Highway 120 (Segment M129). | Unforeseen administrative complexities in the project close-out process including approvals or asset sales. Failure to achieve approval on route change. | TRUE
NT10BIX5570099 | 2010 | Q4 | Q4 - 2010 | In the second quarter of the award period (this quarter), Bloomingdale Communications, Inc. (BCI) continued with the Environmental Assessment (EA) preparation. This included evaluating proposed routes and submitting maps and letters to the appropriate agencies. In addition, BCI released an EA Request for Proposal (RFP) and received completed proposals back. These EA proposals will be coordinating with the archaeologist, Quality Services, Inc. In this quarter, BCI drove the proposed route and finalized route plans which did included some revisions to the proposed route for greater efficiency of the overall project. BCI also worked with Merit, Round 1 NTIA Awardee, in order to define the joint build approach for the two NTIA grants. BCI also began development of the sub-recipient contracts. BCI also began preparation of an RFP for engineering services related to this project. This is an important step since the outside plant detailed design cannot be performed until the engineering firm is selected. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A3 | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | In the third quarter of the award period, Bloomingdale Communications, Inc. (BCI) will hire a firm to complete the Environmental Assessment (EA) and will continue to work with the Michigan State Historical Preservation Office to meet the Section 106 requirements. BCI will update the maps with the revised route as well as submit the revised route to NTIA for approval. The archaeologist will receive updated copies of the revised maps of our project area and continue the Cultural Resources Record Search. BCI expects that the Cultural Resources Record and Assessment report will be delivered to NTIA in the third quarter. Once this has been completed, BCI will be able to submit their draft Environmental Assessment to NTIA during this quarter as well. BCI will also be submitting their street-level network map to NTIA. BCI also intends to release the Engineering RFP and hire an engineering firm so the Outside Plant staking can be completed as well as the Network Design. Staking is the process where the route is driven and specific, detailed drawings of the construction corridor are created. This is the detailed engineering phase of the project. Once the staking is completed this information will be transferred to an Outside Plant construction contract. The actual staking timeline may slip slightly depending upon snow cover and may possibly not be completed until the fourth quarter. The joint build process with Merit is expected to continue in the third quarter of the Award | Bloomingdale Communications Inc | N/A | The project is being delayed slightly due to the NTIA requirement to bid the engineering services hence the project design has been placed on hold temporarily until an engineering firm is selected. We expect to complete this step shortly and continue forward progress to bring the project back in line with our timeline. Winter weather, including heavier than normal snowfall, is also an anticipated challenge in the 1st quarter of 2011. | TRUE
NT10BIX5570099 | 2011 | Q1 | Q1 - 2011 | During this quarter, Quarter 1 of 2011, Bloomingdale Communications, Inc. awarded the Environmental Assessment through the Request for Proposal procurement process to ATC Associates Inc. ATC Associates, Inc. coordinated the Environmental Assessment process with the archeologist, Quality Services, Inc. The draft Environmental Assessment was submitted to National Telecommunications and Information Administration, which met the 6 month Special Award Condition requirement. National Telecommunications and Information Administration provided Bloomingdale Communications, Inc. with a list of follow-up items relating to the Environmental Assessment, which most of those items were incorporated into the Environmental Assessment during this quarter. Bloomingdale Communications, Inc. is now waiting for the Section 106 to be complete before submitting the final Environmental Assessment. In addition, during Q1 of 2011, Bloomingdale Communications, Inc. completed the Request for Proposals process for engineering services and selected Vantage Point Solutions as their engineering firm for the National Telecommunications and Information Administration stimulus project. With the Request for Proposals completed, Bloomingdale Communications, Inc. was able to begin moving along on the project. Due to unusually heavy snowfall in this quarter, the project was somewhat delayed, however, the detailed engineering staking was started on this project. The engineering staking is the process by wh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 0 new network miles deployed, therefore on target as projected in the baseline plan. | N/A | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 0 existing network miles upgraded, therefore on target as projected in the baseline plan. | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 0 existing network miles leased, therefore on target as projected in the baseline plan. | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 0 miles of fiber (aerial or underground), therefore on target as projected in the baseline plan. | N/A | N/A | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 0 new interconnection points, therefore on target as projected in the baseline pland period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 0 new interconnection points, therefore on target as projected in the baseline plan. | 0 | 0 | 0 | N/A | N/A | No designations. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 0 total subscribers served, therefore on target as projected in the baseline plan. | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 0 subscribers receiving new access, therefore on target as projected in the baseline plan. | For Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011), Bloomingdale Communications, Inc. initially projected 0 subscribers receiving improved access, therefore on target as projected in the baseline plan. | No speed tiers available as projected for Year 1 Quarter 3 of the award period which is this quarter (Quarter 1, 2011). | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings provided at this time in the project. | FALSE | Not applicable, no network management practice changes during this quarter (Quarter 1, 2011). | During the next quarter (Quarter 2, 2011), the detailed engineering of the route should be completed and the as-staked footages will be input into the 515 OSP contract. It is expected that this project will be nearly ready to go to bid by the end of Quarter 2, 2011. In addition, Bloomingdale Communications, Inc. expects that they will be able to submit their Final Environmental Assessment. Bloomingdale Communications, Inc. will continue working on sub-recipient contracts and draw down of grant funds during next quarter. The Overlap Special Award Condition should also be approved by National Telecommunications and Information Administration With the engineering firm in place for the project and warm weather coming next quarter, Bloomingdale Communications, Inc. expects to make significant progress in the project. | Bloomingdale Communications Inc | Nothing that is not covered above. | Please refer to the individual challenges listed in Section 2 above. Also, there may be longer than expected lead times for fiber and other materials due to increased demand and supply shortages. | TRUE
NT10BIX5570099 | 2011 | Q2 | Q2 - 2011 | During this quarter, Quarter 2 of 2011, the overlap Special Award Condition for Bloomingdale Communications, Inc. was approved by National Telecommunications and Information Administration, which resulted in the Special Award Condition being met and removed. Bloomingdale Communications, Inc. received the "No Effect Letter" from US Fish and Wildlife Service at the end of April 2011, which was the last requirement necessary to finalize the Environmental Assessment. At the end of May, Bloomingdale Communications, Inc. was notified by National Telecommunication and Information Administration that the Finding of No Significant Impact "FONSI" was issued, which allowed the project to move forward with construction plans. The coordination with Merit Networks on their Round 1 award also continued this quarter in regards to the joint build approach for the two National Telecommunications and Information Administration awards. Bloomingdale Communications, Inc. is still in the process of developing the sub-recipient contracts. The sub-recipient contract will be with Great Lakes Comnet, and Bloomingdale Communications, Inc. has also been talking with the City of South Haven as another possible sub-recipient. There have been many meetings with the City of South Haven during this quarter and the possibilities are being considered. Bloomingdale Communications, Inc. and its selected engineering firm, Vantage Point Solutions, met with all schools involved in the project with the exc | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 37 new network miles deployed. Due to Finding of No Significant Impacts not released until May 2011, construction could not begin any sooner. Bloomingdale Communications, Inc. anticipates making significant project progress next quarter as the fiber vendor has now been selected, however the fiber orders are currently running behind normal delivery as expected to take at least 5 months for delivery. | N/A | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 0 existing network miles upgraded, therefore on target as projected in the baseline plan. | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 0 existing network miles leased, therefore on target as projected in the baseline plan. | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 37 miles of fiber (aerial or underground). Due to Finding of No Significant Impacts not released until May 2011, construction could not begin any sooner. Bloomingdale Communications, Inc. anticipates making significant project progress next quarter as the fiber vendor has now been selected, however the fiber orders are currently running behind normal delivery as expected to take at least 5 months for delivery. | N/A | N/A | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 0 new interconnection points, therefore on target as projected in the baseline pland period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 0 new interconnection points, therefore on target as projected in the baseline plan. | 0 | 0 | 0 | N/A | N/A | No designations. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 0 total subscribers served, therefore on target as projected in the baseline plan. | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 0 subscribers receiving new access, therefore on target as projected in the baseline plan. | For Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011), Bloomingdale Communications, Inc. initially projected 0 subscribers receiving improved access, therefore on target as projected in the baseline plan. | No speed tiers available as projected for Year 1 Quarter 4 of the award period which is this quarter (Quarter 2 of 2011). | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings provided at this time in the project. | FALSE | Not applicable, no network management practice changes during this quarter (Quarter 2 of 2011). | During the next quarter (Quarter 3 of 2011), the fiber for the project will be ordered. Bloomingdale Communications, Inc. will also submit a Request for Proposal for Construction of the project and will select a Outside Plant contractor for completing the construction of this project. Bids are anticipated to open the first week of August 2011. Significant project progress is also anticipated for the overall project including network design, rights of way, construction permits and other approvals, site preparation, and equipment procurement. With the warm summer weather, Bloomingdale Communications, Inc. is making large strides to keep the project moving along. | Bloomingdale Communications Inc | Nothing that is not covered above. | Please refer to the individual challenges listed in Section 2 above. Also, there may be longer than expected lead times for fiber and other materials due to increased demand and supply shortages. | TRUE
NT10BIX5570099 | 2011 | Q3 | Q3 - 2011 | During this quarter, Quarter 3 of 2011, Bloomingdale Communications, Inc. worked on the Construction Request for Proposal (RFP). In the beginning of the quarter, Bloomingdale Communications, Inc. received bids for the construction portion of the project, however all bids received were above budget amounts which seemed to be due to the strict timing of the project. Therefore, Bloomingdale Communications, Inc. decided to reject all initial bids and re-open the RFP process for construction based on a less stringent timeline for the construction portion of the project. This was successful as the new bids received were more in line with the budget of the project, however the construction deadline was moved to October 2012 which will put the project a couple of months behind schedule, however the project overall will still be complete well within the 3 year grant window. Bloomingdale Communications, Inc. will make its official construction vendor selection in the first part of Quarter 4 of 2011. The coordination with Merit Networks on their Round 1 award also continued this quarter in regards to the joint build approach for the two National Telecommunications and Information Administration awards. This quarter there were meetings with Bloomingdale Communications, Inc. and the City of South Haven to continue discussions of the project. Bloomingdale Communications, Inc. is still in the process of developing the sub-recipient contracts. Bloomingdale Communications, Inc. worked on t | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 87 new network miles deployed. Due to Finding of No Significant Impacts not released until May 2011, construction could not begin any sooner. Bloomingdale Communications, Inc. anticipates making significant project progress in the coming quarters as the fiber has been ordered and will be delivered next quarter and the construction vendor will also be selected at the beginning of next quarter. However, due to the re-bid of construction the project completeness timeline will be pushed back from the baseline, but still completed within the 3 year grant window. | N/A | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 0 existing network miles upgraded, therefore on target as projected in the baseline plan. | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 0 existing network miles leased, therefore on target as projected in the baseline plan. | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 87 miles of fiber (aerial or underground). Due to Finding of No Significant Impacts not released until May 2011, construction could not begin any sooner. Bloomingdale Communications, Inc. anticipates making significant project progress in the coming quarters as the fiber has been ordered and will be delivered next quarter and the construction vendor will also be selected at the beginning of next quarter. However,due to the re-bid of construction the project completeness timeline will be pushed back from the baseline, but still completed within the 3 year grant window. | N/A | N/A | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 0 new interconnection points, therefore on target as projected in the baseline pland period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 0 new interconnection points, therefore on target as projected in the baseline plan. | 0 | 0 | 0 | N/A | N/A | No designations. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 0 total subscribers served, therefore on target as projected in the baseline plan. | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 0 subscribers receiving new access, therefore on target as projected in the baseline plan. | For Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011), Bloomingdale Communications, Inc. initially projected 0 subscribers receiving improved access, therefore on target as projected in the baseline plan. | No speed tiers available as projected for Year 2 Quarter 1 of the award period which is this quarter (Quarter 3 of 2011). | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings provided at this time in the project. | FALSE | Not applicable, no network management practice changes during this quarter (Quarter 3 of 2011). | During the next quarter (Quarter 4 of 2011), the fiber for the project will be delivered. Bloomingdale Communications, Inc. will also select an Outside Plant contractor for completing the construction of this project. Project progress is also anticipated for the overall project including network design, rights of way, construction permits and other approvals. However with the winter weather expected in the next couple of quarters, Bloomingdale Communications, Inc. is continuing to making large strides to keep the project moving along but may not show a lot of progress until Spring of 2012, however the overall project will be competed within the 3 year grant window. Updated projections for key indicators for next quarter (Quarter 4, 2011) are as follows: a. New network miles deployed = 0 b. New network miles leased = 0 c. Total CAI subscribers served (CAIs connected) = 0 d. Number of signed agreements with broadband wholesalers or last mile providers = 0 | Bloomingdale Communications Inc | Nothing that is not covered above. | Please refer to the individual challenges listed in Section 2 above. Also, there may be longer than expected lead times for fiber and other materials due to increased demand and supply shortages. | TRUE
NT10BIX5570099 | 2011 | Q4 | Q4 - 2011 | During this quarter, Quarter 4 of 2011, Bloomingdale Communications, Inc. selected Turnkey Network Solutions for the project through the Construction Request for Proposal (RFP). The coordination with Merit Networks on its Round 1 award also continued this quarter in regards to the joint build approach for the two National Telecommunications and Information Administration awards. Merit's contractor installed a total of 8,500 feet of conduit in the Bloomingdale joint build area this quarter. In addition, there were meetings with Bloomingdale Communications, Inc. and the City of South Haven to continue discussions of the project. Bloomingdale Communications, Inc. is still in the process of developing a sub-recipient contract with Great Lakes Comnet where Bloomingdale can construct and Great Lakes Comnet can lease certain project network facilities to connect Bloomingdaleâ€™s project from Hartford to Berrien Springs, Michigan. This will allow Bloomingdaleâ€™s middle mile Van Buren Independent School District data network to connect with regional school resources in Berrien Springs. Further, Great Lakes will lease additional fibers on other project routes, creating more efficiencies for both Bloomingdale and Great Lakes and providing greatly improved broadband services for the entire region. Bloomingdale Communications, Inc. worked on the Rights of Way and Construction permits for this project this quarter and has all of the county road, drain, and soil erosion permits ready. They are still working on the state highway and railroad permits, however there is plenty of time since construction will not start till spring of 2012. Turnkey is ready to start the Amtrak training and the CSX policy should be in soon. Bloomingdale Communications worked on related Davis Bacon items with Turnkey. Bloomingdale Communications, Inc. started taking delivery of the fiber optic cable this quarter. Bloomingdale Communications, Inc. received 24 out of the 26 reels ordered, therefore the majority of the order was delivered. The fiber optic cable is included in the construction portion of project budget. The single fiber vendor selected in 2nd Quarter of 2011 was Power & Telephone. Vantage Point Solutions, the selected engineering firm, also continued to work with Bloomingdale Communications, Inc. in regards to the project. The number of jobs created or retained in the 4th Quarter of 2011 was 0.52 full time equivalent. Bloomingdale Communications, Inc. drew down $277,025.41 in federal funds in the 4th quarter of 2011. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 131 new network miles deployed. Due to Finding of No Significant Impacts not released until May 2011, construction could not begin any sooner. Bloomingdale Communications, Inc. anticipates making significant project progress in the coming quarters as the majority of the fiber has been delivered and the construction vendor was selected. However, due to the re-bid of construction the project completeness timeline will be pushed back from the baseline, but still completed within the 3 year grant window. The Merit overlap was started this quarter and 8,500 feet of conduit was installed, which is about 1.6 miles. | N/A | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 15 existing network miles upgraded, however . | N/A - Baseline showed 1 mile of existing network miles leased for Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), however based on recent comments from NTIA this category should be zero and will remain zero throughout the project. | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 147 miles of fiber (aerial or underground). Due to Finding of No Significant Impacts not released until May 2011, construction could not begin any sooner. Bloomingdale Communications, Inc. anticipates making significant project progress in the coming quarters the majority of the fiber has been delivered and the construction vendor was selected. However,due to the re-bid of construction the project completeness timeline will be pushed back from the baseline, but still completed within the 3 year grant window. | N/A | N/A | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 0 new interconnection points, therefore on target as projected in the baseline plan. | 0 | 0 | 0 | N/A | N/A | No designations. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 0 total subscribers served, therefore on target as projected in the baseline plan. | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 0 subscribers receiving new access, therefore on target as projected in the baseline plan. | For Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011), Bloomingdale Communications, Inc. initially projected 0 subscribers receiving improved access, therefore on target as projected in the baseline plan. | No speed tiers available as projected for Year 2 Quarter 2 of the award period which is this quarter (Quarter 4 of 2011). | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings provided at this time in the project. | FALSE | Not applicable, no network management practice changes during this quarter (Quarter 4 of 2011). | During the next quarter (Quarter 1 of 2012), the final fiber for the project will be delivered. Project progress is also anticipated for the overall project including network design, rights of way, construction permits and other approvals. However with the winter weather expected in the next quarter, Bloomingdale Communications, Inc. is continuing to making large strides to keep the project moving along but may not show a lot of progress until Spring of 2012, however the overall project will be competed within the 3 year grant window. Updated projections for key indicators for next quarter (Quarter 1, 2012) are as follows: a. New network miles deployed = 10 b. New network miles leased = 0 c. Total CAI subscribers served (CAIs connected) = 0 d. Number of signed agreements with broadband wholesalers or last mile providers = 0 | Bloomingdale Communications Inc | Nothing that is not covered above. | Please refer to the individual challenges listed in Section 2 above. Also, there may be longer than expected lead times for materials due to increased demand and supply shortages. | TRUE
NT10BIX5570099 | 2012 | Q1 | Q1 - 2012 | During this quarter, Quarter 1 of 2012 (Year 2 Quarter 3), Bloomingdale Communications, Inc.'s selected contractor, Turnkey Network Solutions (Turnkey), began construction of the project. Turnkey had two bore crews that began in Lawrence. By the end of this quarter, four miles of conduit was completed which finished the town of Lawrence except for the railroad and began working between Lawrence and Hartford. The coordination with Merit Networks on its Round 1 award also continued this quarter in regards to the joint build approach for the two National Telecommunications and Information Administration awards. Merit's contractor installed a total of 5.5 miles of conduit in the Bloomingdale joint build area this quarter. Bloomingdale Communications, Inc. worked on the easements for the two huts and five cabinets. Some of the land owners have been difficult to reach due to family issues and extended winter vacations. In addition, there were meetings with Bloomingdale Communications, Inc. and the City of South Haven to continue discussions of the project. Payment was made for the engineering and make ready joint use of the city poles in February of this quarter. The lease agreement with the City of South Haven is still being worked on, but getting closer to finalizing. The co-lash agreement was signed in January with the South Haven schools allowing Bloomingdale Communications, Inc.'s to use some of their of existing poles. Attempts to contact the other service providers in the area were made regarding making poles ready for attachment in the City of South Haven. One provider did supply a list of items to be completed at the end of the project and the other provider has had changes in personnel, therefore very difficult to track this specific company contact down yet. Bloomingdale Comminications, Inc. will continue to work on getting the proper contact for this service provider. Bloomingdale Communications, Inc. is still in the process of developing a sub-recipient contract with Great Lakes Comnet where Bloomingdale can construct and Great Lakes Comnet can own certain project network facilities to connect Bloomingdaleâ€™s project from Hartford to Berrien Springs, Michigan. This will allow Bloomingdaleâ€™s middle mile Van Buren Independent School District data network to connect with regional school resources in Berrien Springs. Further, Great Lakes Comnet will own additional fibers on other project routes, creating more efficiencies for both Bloomingdale and Great Lakes and providing greatly improved broadband services for the entire region. Bloomingdale Communications, Inc. worked on the Rights of Way and Construction permits for this project this quarter and has all of the county road, state highway, drain, and soil erosion permits ready. Most of the railroad permits are complete as they are only still working on one railroad permit for which payment was sent at the end of the quarter. Turnkey is trained for Amtrak and the CSX policy was put in place. Bloomingdale Communications, Inc. awaited approval from the Department of Labor on Davis Bacon wage determination requests. By the end of the quarter, two of the four were confirmed. Bloomingdale Communications, Inc. took possession of the final two of the twenty-six reels of fiber optic cable. The fiber optic cable is included in the construction portion of project budget. Vantage Point Solutions, the selected engineering firm, continued to work with Bloomingdale Communications, Inc. regarding the project outside plant inspection services, network design, and overall project management. The number of jobs created or retained in the 1st Quarter of 2012 was 2.23 full time equivalent. Bloomingdale Communications, Inc. drew down $210,946.30 in federal funds in the 1st quarter of 2012. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 131 new network miles deployed. Due to Finding of No Significant Impacts not released until May 2011, construction could not begin any sooner. Bloomingdale Communications, Inc. anticipates making significant project progress in the coming quarters as the fiber has been delivered. However, due to the re-bid of construction the project completeness timeline was pushed back from the baseline, but still completed within the 3 year grant window. The construction vendor began construction this quarter with around 4 miles of conduit being completed. Also the Merit/Bloomingdale joint build continued this quarter and about 5.5 miles of conduit has been installed between Watervliet and South Haven. | Baseline showed "N/A" for new network miles leased for Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), however based on recent discussions with NTIA this category should be "1" by the end of the project due to the misinterpretation of "Existing network miles leased" notated below. | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 15 existing network miles upgraded, however due to the re-bid of construction the project completeness timeline was pushed back from the baseline, but still completed within the 3 year grant window. The construction vendor began construction this quarter with around 4 miles of conduit being completed. Also the Merit/Bloomingdale joint build continued this quarter and about 5.5 miles of conduit has been installed between Watervleit and South Haven. | N/A - Baseline showed 1 mile of existing network miles leased for Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), however based on recent comments from NTIA this category should be zero and will remain zero throughout the project as the "Existing network miles leased" refers to miles leased prior to the award period and no miles were leased prior to the award start date. | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 147 miles of fiber (aerial or underground). Due to the re-bid of construction the project completeness timeline was pushed back from the baseline, but still completed within the 3 year grant window. The construction vendor began construction this quarter with around 4 miles of conduit being completed. Also the Merit/Bloomingdale joint build continued this quarter and about 5.5 miles of conduit has been installed between Watervliet and South Haven. | N/A | N/A | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 0 new interconnection points, therefore on target as projected in the baseline plan. | 0 | 0 | 0 | N/A | N/A | No designations. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 31 total subscribers served. Due to the re-bid of construction the project completeness timeline was pushed back from the baseline, but still completed within the 3 year grant window. | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 31 subscribers receiving new access. Due to the re-bid of construction the project completeness timeline was pushed back from the baseline, but still completed within the 3 year grant window. | For Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012), Bloomingdale Communications, Inc. initially projected 0 subscribers receiving improved access, therefore on target as projected in the baseline plan. | No speed tiers available as projected for Year 2 Quarter 3 of the award period which is this quarter (Quarter 1 of 2012). | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings provided at this time in the project. | FALSE | Not applicable, no network management practice changes during this quarter (Quarter 1 of 2012). | During the next quarter (Quarter 2 of 2012), significant project progress is anticipated for the overall project. Construction is moving along as expected and with the upcoming Spring quarter the construction will continue to move forward as scheduled. The last railroad permit will be executed and the Hut and Electronic RFPs will be released. Bloomingdale Communications, Inc. is continuing to making large strides to keep the project moving along and the overall project will be competed within the 3 year grant window. Updated projections for key indicators for next quarter (Quarter 2, 2012) are as follows: a. New network miles deployed = 45 miles b. New network miles leased = 0 c. Total CAI subscribers served (CAIs connected) = 0 d. Number of signed agreements with broadband wholesalers or last mile providers = 0 | Bloomingdale Communications Inc | Nothing that is not covered above. | Please refer to the individual challenges listed in Section 2 above. Also, there may be longer than expected lead times for materials due to increased demand and supply shortages. | TRUE
NT10BIX5570099 | 2012 | Q2 | Q2 - 2012 | During this quarter, Quarter 2 of 2012 (Year 2 Quarter 4), Bloomingdale Communications, Inc.'s (BCI) selected contractor, Turnkey Network Solutions (Turnkey), made a lot of progress in the construction of the project. Turnkey had three crews working, one plow crew and two boring crews. By the end of this quarter, a total of 55 miles of duct had been installed, with 34 miles of fiber. The fiber has been placed in the Paw Paw to Watervliet segment as well as the Bloomingdale to Bangor segment. The joint build coordination with Merit Networks on its Round 1 award also continued this quarter. Merits contractor installed 2.54 miles of duct during this quarter which included 3 railroad crossings, 3 interstate crossings, and a river crossing. All of the underground duct for this joint build has been placed and the aerial strands are being started. Merit is still awaiting some permits to complete the aerial segment. The necessary permits and easements continued to be worked on this quarter and are in good shape for the continuation of the project. This quarter agreements were made for easements with the landowners that were difficult to reach previously, therefore only three easements are left to obtain for the cabinets. Also, there is only one railroad permit remaining and should be executed the first part of next quarter, however the last payment for these permits was made this quarter. Contact was made with the other service providers in the City of South Haven regarding the make ready of poles for the project. The parties agreed on the work to be performed, therefore this is moving along. The Request for Proposals (RFP) were released this quarter for the huts and electronics. This project includes two prefabricated huts for the locations of South Haven and Lawrence. Both huts necessary for the project were ordered this quarter, are currently under construction at Thermobond, and are scheduled to be delivered in the middle of August 2012. The electronics RFPs were released this quarter as well. The RFP for the DC power for the prefabricated huts was sent out in mid June and the vendor will be selected the first part of July. The transport electronics RFP was also released in June and BCI received responses from six vendors by June 19th, therefore the transport electronics will be selected after a technical session the first part of July and acceptance of the contract will be finalized by the end of July. The Department of Labor provided approval to BCI this quarter on the remaining two wage determinations. Therefore, all four determinations submitted have been confirmed. This quarter, BCI continued to work with Vantage Point Solutions, the selected engineering firm, regarding the project outside plant inspection services, network design, and overall project management. The network design is complete for the project until the final stages before deployment of the ring. BCI drew down $1,561,909 in federal funds in the 2nd quarter of 2012 and the number of jobs created or retained in this quarter due to this BCI project was 12.91 full time equivalent. This quarter, the project began coming together and moving along as planned with a lot of construction progress, RFPs for the necessary portions of the project, and overall network design. This quarter was very productive as expected and no delays are anticipated for final completion of the project within three years. This quarter, on June 5-6, 2012, NTIA conducted a site visit to Bloomingdale Communications, Inc. to observe and assess program performance as well as assess financial, asset and program management. NTIA Program Office staff met with key BCI personnel as well as a representative from sub-recipient, Great Lakes Comnet, to review documents, financial records and procedures. The site visit also included a tour of Bloomingdale Communications' facilities and project construction sites. | 34 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | As of the end of the second quarter 2012, BCI has blown 34 miles of fiber. This fiber will not be lit until the end of the project after all fiber is laid and electronics are installed, each segment is not turned up individually. At the end of last quarter, BCI projected to have about 45 miles of fiber blown, however only ended up with 34 miles. BCI did install 51 miles of conduit this quarter for a total of 55 miles. An additional 2.54 miles of duct was placed in the Merit joint build portion which completes the total of 8 miles of conduit, however fiber has not been blown through that section yet. Construction continues rapidly and the three year project will be completed well ahead of the award period end date. | N/A no change from report last quarter - Baseline showed "N/A" for new network miles leased for Year 2 Quarter 4 of the award period which is this quarter (Quarter 2 of 2012), however based on discussions with NTIA this category should be "1" by the end of the project due to the misinterpretation of "Existing network miles leased" notated below. | N/A no change from report last quarter - For this quarter, the baseline initially projected 15 existing network miles to be upgraded. With the re-bid of construction for budget purposes, the overall project was delayed, however will be completed well within the three year grant window. Construction is making great progress and will continue moving rapidly. | N/A - No miles were leased prior to the award start date | As of the end of the second quarter 2012, BCI has blown 34 miles of fiber through the 55 miles of conduit laid. Construction continues rapidly and the three year project will be completed well ahead of the award period end date. | N/A | N/A | BCI initially projected 13 interconnection points for the this projected by this time period, however as stated previously, the project was delayed from the initial timeline. | 0 | 0 | 0 | N/A | N/A | No designations. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | BCI initially projected 31 CAI total subscribers served by this quarter end, however as stated previously the project re-bid for budget constraints delayed the overall construction timeline. This projected will be completed well within the three year grant award window. | BCI initially projected 31 CAI total subscribers served by this quarter end, however as stated previously the project re-bid delayed the overall construction timeline. This projected will be completed well within the three year grant award window. | BCI initially projected 31 CAI total subscribers served by this quarter end, however as stated previously the project re-bid for budget constraints delayed the overall construction timeline. This projected will be completed well within the three year grant award window. | No speed tiers available yet until the project is complete, which will be well within the three year award window, however not on target with the initial projection due to construction re-bid process for budget constraints. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings provided at this time during the project. | FALSE | Not applicable, as no network management practices changed during this quarter. | Continuation of significant project progress is expected for next quarter, Quarter 3 of 2012. Construction will continue to move along rapidly. All easements should be obtained, equipment should be ordered as the vendor will be selected, huts should be delivered and installed, and the RFP for the core router should be released and the vendor should be selected. BCI will continue to make large strides in completing the project and the project will be complete within the three year grant window. Updated projections for key indicators for next quarter: a. New network mile deployed = 120 miles b. New network miles leased = 0 c. Total CAI subscribers served (connected) = 0 d. Number of signed agreements with broadband wholesalers or last mile providers = 0 | Bloomingdale Communications Inc | No issues or challenges other than what is covered above by individual category. | BCI does not anticipate any challenges or issues during the next quarter that may impact planned progress against the project milestones listed above other than what is listed in the individual categories above. The project will be completed well within the three year award period timeline. | TRUE
NT10BIX5570099 | 2012 | Q3 | Q3 - 2012 | During this quarter, Quarter 3 of 2012 (Year 3 Quarter 1), Bloomingdale Communications, Inc.'s (BCI) selected contractor, Turnkey Network Solutions (Turnkey), made a lot of progress in the construction of the project. By the end of this quarter, a total of 85.8 miles of fiber had been installed, with 80 miles of fiber underground and 5.8 aerial fiber. Fiber spliced was 54 miles. Also, of these totals include buried entrance fiber to 22 Community Anchor Institutions (CAIs) being installed this quarter. The joint build coordination with Merit Networks on its Round 1 award also continued this quarter and is close to completion. By the end of this quarter, Merit's contractor has installed a total of 38.63 aerial miles and 9.4 underground miles. Of these miles, fiber has been placed in 29.75 aerial miles and 8.46 underground miles. Splice locations completed was 10. The necessary permits and easements continued to be worked on this quarter and are in good shape for the continuation of the project. The final railroad permit was obtained this quarter. The Covert Public School Board approved the easement this quarter and will be signed next quarter. This project includes two prefabricated huts which are located in South Haven and Lawrence. The South Haven hut was delivered and installed this quarter and the concrete pad for Lawrence has been poured and the hut will be received soon. This quarter, BCI held a technical session in order to assist in determining the vendor based on the RFP responses. BCI selected Cyan for transport equipment and Cisco for core routing equipment. They Cyan transport equipment was ordered this quarter. DC power vendor for the huts was also selected during this quarter and will be Power & Tel. The environmental issues with the cabinets was resolved this quarter and the contract for the 5 cabinets was awarded to Power & Tel for Emerson cabinets. This quarter, BCI continued to work with Vantage Point Solutions, the selected engineering firm, regarding the project outside plant inspection services, network design, and overall project management. The network design is complete for the project until the final stages before deployment of the ring. This quarter BCI continued to work with NTIA regarding the action item list from the June 5-6, 2012 on site visit. Most action items have been resolved by the end of this quarter. BCI drew down $1,333,128 in federal funds in the 3rd quarter of 2012, which is a total of $2,895,037 since the project began. The number of jobs created or retained in this quarter due to this BCI project was 14.2 full time equivalent. This quarter, the project continued coming together and moving along as planned with a lot of construction progress, vendor selections, permits, easements, and overall network design. This quarter was very productive as expected and no delays are anticipated for final completion of the project within three years. | 124 | 0 | 0 | 0 | 124 | 0 | 0 | 0 | As of the end of the third quarter 2012, BCI has placed 80 miles of buried fiber and 5.8 miles of aerial fiber. The Merit joint build portion of the project has completed 8.46 underground fiber miles and 29.75 aerial fiber miles by the end of this quarter. This is a total of 124 project miles of fiber placed. The BCI fiber will not be lit until the end of the project after all fiber is laid and electronics are installed, each segment is not turned up individually. At the end of last quarter, BCI projected to have about 120 miles of fiber placed, therefore is just above the target projection at the end of this quarter. Splicing has also begun on the placed fiber. BCI has spliced 54 miles and the joint build portion has had 10 of the 23 locations spliced. Construction continues rapidly and the three year project will be completed well ahead of the award period end date. | N/A no change from report last quarter - Baseline showed "N/A" for new network miles leased for Year 3 Quarter 1 of the award period which is this quarter (Quarter 3 of 2012), however based on discussions with NTIA this category should be "1" by the end of the project due to the misinterpretation of "Existing network miles leased" notated below. | N/A no change from report last quarter - For this quarter, the baseline initially projected 15 existing network miles to be upgraded. With the re-bid of construction for budget purposes, the overall project was delayed, however will be completed well within the three year grant window. Construction is making great progress and will continue moving rapidly. | N/A - No miles were leased prior to the award start date. | As of the end of the third quarter 2012, BCI has placed 124 miles of fiber which includes the Merit joint build portion of the project. Construction continues rapidly and the three year project will be completed well ahead of the award period end date. | N/A | N/A | BCI initially projected 13 interconnection points for the this projected by this time period, however as stated previously, the project was delayed from the initial timeline however is moving along rapidly at this time. | 0 | 0 | 0 | N/A | N/A | No designations. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 22 | 22 | 0 | 11 | BCI initially projected in their baseline that 31 CAI total subscribers would be served by this quarter end, however as stated previously the project re-bid for budget constraints delayed the overall construction timeline. Construction is moving along rapidly now as fiber has been placed to 22 of the CAIs by the end of this quarter. This project will be completed well within the three year grant award window. | BCI initially projected in their baseline that 31 CAI total subscribers would be served by this quarter end, however as stated previously the project re-bid delayed the overall construction timeline. Construction is moving along rapidly now as fiber has been placed to 22 of the CAIs by the end of this quarter. This project will be completed well within the three year grant award window. | BCI initially projected in their baseline that 31 CAI total subscribers would be served by this quarter end, however as stated previously the project re-bid for budget constraints delayed the overall construction timeline. Construction is moving along rapidly now as fiber has been placed to 22 of the CAIs by the end of this quarter. This project will be completed well within the three year grant award window. | No speed tiers subscribed to yet until the project is complete, which will be well within the three year award window, however not on target with the initial projection due to construction re-bid process for budget constraints. Construction is moving along rapidly now and this project will be completed well within the three year grant award window. Speed tiers that will be available: 10 Mbps 20 Mbps 30 Mbps 40 Mbps 50 Mbps 100 Mbps 200 Mbps 300 Mbps 400 Mbps 500 Mbps 1000 Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings provided at this time during the project. | FALSE | Not applicable, as no network management practices changed during this quarter. | Continuation of significant project progress is expected for next quarter, Quarter 4 of 2012. The joint build portion with Merit should be completed and BCI construction will continue to move along rapidly. All easements should be obtained, transport equipment should be delivered and installed, the core routing equipment should be ordered and delivered as well as installed, the last hut delivered and installed along with the DC power installed to both huts, and the five cabinets will be delivered and installed. The start of installation and cut over of routing equipment as well as transport equipment should take place this quarter. Splicing should also be completed with testing of the network beginning. BCI will continue to make large strides in completing the project and the project will be complete within the three year grant window. Updated cumulative projections for key indicators for next quarter: a. New network mile deployed = 131 miles b. New network miles leased = 0 c. Total CAI subscribers served (connected) = 28 d. Number of signed agreements with broadband wholesalers or last mile providers = 0 | Bloomingdale Communications Inc | No issues or challenges other than what is covered above by individual category. Progress is moving along rapidly and really coming together as expected. | BCI does not anticipate any challenges or issues during the next quarter that may impact planned progress against the project milestones listed above other than what is listed in the individual categories above. The project will be completed well within the three year award period timeline. | TRUE
NT10BIX5570099 | 2012 | Q4 | Q4 - 2012 | During this quarter, Quarter 4 of 2012 (Year 3 Quarter 2), Bloomingdale Communications, Inc.'s (BCI) selected contractor, Turnkey Network Solutions (Turnkey), finished placing all fiber for the project. By the end of this quarter, an approximate total of 87.6 miles of fiber had been installed, with approximately 81.1 miles of fiber underground and 6.5 miles of aerial fiber. By the end of this quarter, all fiber had been spliced. These totals include buried entrance fiber to all Community Anchor Institutions (CAIs) being included in this project. Fiber testing was performed this quarter and three damaged sections of fiber were found, replaced, and re-spliced. All re-splicing and re-testing will be done early next quarter. The joint build coordination with Merit Networks (Merit) on its Round 1 award also continued this quarter and fiber and splicing was completed. By the end of this quarter, Merit's contractor has installed and placed fiber in a total of 40.02 aerial miles and 9.71 underground miles. All 23 splice locations were completed by the end of this quarter. Therefore all fiber has been placed and testing is underway. A Memorandum of Understanding was signed this quarter with Merit for them to build a lateral from BCI's backbone into Lake Michigan College, therefore this lateral and splicing was completed this quarter. The necessary permits and easements continued to be worked on this quarter and are complete. The Covert easement was received for the cabinet and pole attachment permits were received from American Electic Power (AEP) for the aerial fiber lateral to the Gobles Public Library. This project includes two prefabricated huts which are located in South Haven and Lawrence. The South Haven hut became 100% complete this quarter with commercial power service installed. The Lawrence hut and generator was delivered and installed this quarter. The utility company also installed gas and electric service to the Lawrence hut. The hook up and start up of the generator in Lawrence still remains as well as the installing of the DC equipment. The fiber equipment cabinets were ordered and delivered this quarter. The concrete pads were poured by Turnkey based on their awarded RFP this quarter. Therefore all five cabinets were received and placed this quarter. A contract for the new Cisco ASR 9010 core router was executed this quarter and the router was installed and placed into service. With the deployment of the new router, BCI has cut some subscribers over to this new router this quarter and will continue to cut more subscriber traffic. This quarter, BCI continued to work with Vantage Point Solutions, the selected engineering firm, regarding the project outside plant inspection services and overall project management. This quarter BCI continued to work with NTIA regarding the action item list from the June 5-6, 2012 on site visit. The action items were resolved. BCI did update line item budget category amounts, although the overall budget stayed the same the updated costs by classification are shown in the Infrastructure Budget Execution Details at the end of this report. BCI drew down $779,911 in federal funds in the 4th quarter of 2012, which is a total of $3,674,948 since the project began. The number of jobs created or retained in this quarter due to this BCI project was 6.14 full time equivalent. This quarter, the project continued coming together and moving along as planned with significant construction progress, vendor selections, permits finalized, easements finalized, and overall project progress. This quarter was very productive as expected and no delays are anticipated for final completion of the project within three years. | 137 | 0 | 0 | 0 | 137 | 0 | 0 | 0 | As of the end of the fourth quarter 2012, all fiber has been installed. BCI has placed approximately 81.1 miles of buried fiber and 6.5 miles of aerial fiber. The Merit joint build portion of the project has completed 9.71 underground fiber miles and 40.02 aerial fiber miles by the end of this quarter. This is a total of 137 project miles of fiber placed. The BCI fiber will not be lit until the end of the project after all fiber is laid and electronics are installed, each segment is not turned up individually. At the end of last quarter, BCI projected to have about 131 miles of fiber placed, therefore is just above the target projection at the end of this quarter. Splicing also was finalized on the placed fiber and testing began. Construction continues rapidly and the three year project will be completed well ahead of the award period end date as all new network miles have been completed. | N/A no change from report last quarter - Baseline showed "N/A" for new network miles leased for Year 3 Quarter 2 of the award period which is this quarter (Quarter 4 of 2012), however based on discussions with NTIA this category should be "1" by the end of the project due to the misinterpretation of "Existing network miles leased" notated below. This 1 mile will be leased once the network is lit. | N/A no change from report last quarter - For this quarter, the baseline initially projected 15 existing network miles to be upgraded. With the re-bid of construction for budget purposes, the overall project was delayed, however will be completed well within the three year grant window. Construction is making great progress and will continue moving rapidly. These 15 miles will be counted for once the network is lit. | N/A - No miles were leased prior to the award start date. | As of the end of the fourth quarter 2012, BCI has placed 137 miles of fiber which includes the Merit joint build portion of the project. Construction continues rapidly and the three year project will be completed well ahead of the award period end date. | N/A | N/A | BCI initially projected 13 interconnection points for this project by this time period, however as stated previously, the project was delayed from the initial timeline however is moving along rapidly at this time. These interconnection points will be accounted for once the network is lit. | 0 | 0 | 0 | N/A | N/A | No designations. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 29 | 29 | 0 | 11 | BCI initially projected in their baseline that 31 CAI total subscribers would be served by this quarter end, however as stated previously the project re-bid for budget constraints delayed the overall construction timeline. Construction is moving along rapidly now as fiber has been placed to 29 of the CAIs by the end of this quarter. This project will be completed well within the three year grant award window. | BCI initially projected in their baseline that 31 CAI total subscribers would be served by this quarter end, however as stated previously the project re-bid delayed the overall construction timeline. Construction is moving along rapidly now as fiber has been placed to 29 of the CAIs by the end of this quarter. This project will be completed well within the three year grant award window. | BCI initially projected in their baseline that 31 CAI total subscribers would be served by this quarter end, however as stated previously the project re-bid for budget constraints delayed the overall construction timeline. Construction is moving along rapidly now as fiber has been placed to 29 of the CAIs by the end of this quarter. This project will be completed well within the three year grant award window. There will be 4 CAI that will receive improved access once the equipment is installed. | No speed tiers subscribed to yet until the project is complete, which will be well within the three year award window, however not on target with the initial projection due to construction re-bid process for budget constraints. Construction is moving along rapidly now and this project will be completed well within the three year grant award window. Speed tiers that will be available: 10 Mbps 20 Mbps 30 Mbps 40 Mbps 50 Mbps 100 Mbps 200 Mbps 300 Mbps 400 Mbps 500 Mbps 1000 Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings provided at this time during the project. | FALSE | Not applicable, as no network management practices changed during this quarter. | Continuation of significant project progress is expected for next quarter, Quarter 1 of 2013. Turnkey will finish miscellaneous splicing and testing, then BCI will begin working on closing out the Outside Plant (OSP) contract. Thermobond will continue working on the generator hook up and start-up for the Lawrence Hut and Power Products Services will install the DC Power equipment. BCI will continue cutting over more subscribers to the new Cisco ASR 9010 router and this contract should also be closed out this next quarter. The Cyan CPE installation will be completed at the CAIs and the transport equipment will be installed. Training is trying to get scheduled next quarter for the Cyan equipment. Contract closeouts should take place and customers should begin to be turned up on to the new network. Next quarter, BCI will continue to make large strides in completing the project and the project will be complete within the three year grant window. Updated cumulative projections for key indicators for next quarter: a. New network miles leased = 1 b. Total CAI subscribers served (connected) = 33 c. Number of signed agreements with broadband wholesalers or last mile providers = 0 | Bloomingdale Communications Inc | No issues or challenges other than what is covered above by individual category. Progress is moving along rapidly and really coming together as expected. The project will be competed within the three year window. | BCI does not anticipate any challenges or issues during the next quarter that may impact planned progress against the project milestones listed above other than what is listed in the individual categories above. The project will be completed well within the three year award period timeline. | TRUE
NT10BIX5570099 | 2013 | Q1 | Q1 - 2013 | During this quarter, Quarter 1 of 2013 (Year 3 Quarter 3), Bloomingdale Communications, Inc.'s (BCI) continued to work with Vantage Point Solutions (Vantage Point), the selected engineering firm, regarding the project outside plant inspection services and overall project management. Vantage Point reviewed the re-testing of the three damaged sections of the fiber network and found an area of concern with splicing. The initial failed testing areas were addressed with BCI's selected contractor this quarter, Turnkey Network Solutions (Turnkey), and most locations were fixed by the end of the quarter by being re-spliced and re-tested. As they finish this work next quarter, BCI will work on closing the OSP contract. The Cyan CPE and transport equipment was installed this quarter and services are being scheduled to be cutover to this equipment. The inspection and acceptance testing by Cyan and Vantage Point went well as everything passed. Cyan training was also completed at the end of this quarter for the equipment. There was no change to the fiber miles installed by the end of the prior quarter as all fiber was placed in the previous quarter. An approximate total of 87.6 miles of fiber has been installed for this project, with approximately 81.1 miles of fiber underground and 6.5 miles of aerial fiber. These totals include buried entrance fiber to all Community Anchor Institutions (CAIs) being included in this project. The joint build coordination with Merit Networks (Merit) on its Round 1 award also continued this quarter. By the end of last quarter, Merit's contractor had installed and placed fiber in a total of 40.02 aerial miles and 9.71 underground miles. This project includes two prefabricated huts which are located in South Haven and Lawrence. The South Haven hut became 100% complete last quarter with commercial power service installed. The Lawrence hut and generator was delivered and installed last quarter. This quarter the gas line was ran to the generator and hooked up to the meter and the DC equipment was installed in the Lawrence hut. A request for proposal (RFP) was sent out this quarter for the driveways to be installed to the hut locations. BCI completed a RFP for a DC upgrade for their Bloomingdale Central Office this quarter. Emergency Power Corp. is working on getting the contract documents together. A RFP for the air conditioning unit was also prepared this quarter for the Bloomingdale Central Office. Two bids are being reviewed for this. The equipment was installed in the five fiber equipment cabinets this quarter. BCI has cut more subscribers over to the new Cisco ASR 9010 core router this quarter and will continue to cut more subscriber traffic. The closeout documentation on this was completed this quarter. BCI drew down $929,034 in federal funds in the 1st quarter of 2013, which is a total of $4,603,982 since the project began. The number of jobs created or retained in this quarter due to this BCI project was 1.86 full time equivalent. BCI and Merit Network held a joint press conference on February 22, 2013 in Berrien Springs, Michigan. BCI signed service agreements with 21 Community Anchor Institutions during the First Quarter of 2013. This quarter, the project continued coming together and moving along as planned with construction complete and equipment being deployed the overall project progress is moving along. This quarter was very productive as expected and no delays are anticipated for final completion of the project within three years. | 137 | 0 | 0 | 0 | 137 | 0 | 0 | 0 | As of the end of the fourth quarter 2012, all fiber had been installed. BCI had placed approximately 81.1 miles of buried fiber and 6.5 miles of aerial fiber. The Merit joint build portion of the project had completed 9.71 underground fiber miles and 40.02 aerial fiber miles by the end of last quarter. This is a total of 137 project miles of fiber placed. The BCI fiber will not be lit until the end of the project after all fiber is laid and electronics are installed, each segment is not turned up individually. All new network miles have been completed. | N/A no change from report last quarter - Baseline showed "N/A" for new network miles leased for Year 3 Quarter 3 of the award period which is this quarter (Quarter 1 of 2013), however based on discussions with NTIA this category should be "1" by the end of the project due to the misinterpretation of "Existing network miles leased" notated below. This 1 mile will be leased once the network is lit. | N/A no change from report last quarter - For this quarter, the baseline initially projected 15 existing network miles to be upgraded. With the re-bid of construction for budget purposes, the overall project was delayed, however will be completed well within the three year grant window. The project is making great progress and will continue moving rapidly. These 15 miles will be counted for once the network is lit. | N/A - No miles were leased prior to the award start date. | As of the end of the fourth quarter 2012, BCI had placed 137 miles of fiber which includes the Merit joint build portion of the project. Project progress continues rapidly and the three year project will be completed well ahead of the award period end date. | N/A | N/A | BCI initially projected 13 interconnection points for this project by this time period, however as stated previously, the project was delayed from the initial timeline. The project is moving along rapidly at this time. These interconnection points will be accounted for once the network is lit. | 0 | 0 | 0 | N/A | N/A | No designations. | 0 | 0 | 0 | 0 | None projected | None projected | None projected | None projected | 33 | 29 | 4 | 11 | All project CAIs have been connected by the end of this quarter (Quarter 1 2013). This project will be completed well within the three year grant award window. | All project CAIs have been connected by the end of this quarter (Quarter 1 2013). This project will be completed well within the three year grant award window. | Equipment was installed this quarter, therefore all project CAIs have been connected by the end of this quarter (Quarter 1 2013). This project will be completed well within the three year grant award window. | No speed tiers subscribed to yet until the project is complete, which will be well within the three year award window, however not on target with the initial projection due to construction re-bid process for budget constraints. The project is moving along rapidly now and will be completed within the three year grant award window. Speed tiers that will be available once the network is lit: 10 Mbps 20 Mbps 30 Mbps 40 Mbps 50 Mbps 100 Mbps 200 Mbps 300 Mbps 400 Mbps 500 Mbps 1000 Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings provided at this time during the project. | FALSE | Not applicable, as no network management practices changed during this quarter. | Continuation of significant project progress is expected for next quarter, Quarter 2 of 2013, as the project nears completion. Turnkey will finish splicing in South Haven and re-testing, then BCI will finalize working on closing out the Outside Plant (OSP) contract. BCI will continue cutting over more subscribers. Contract closeouts should continue to take place and customers should begin to be turned up on to the new network. Next quarter, BCI will continue to make large strides in completing the project and the project will be complete within the three year grant window. Updated cumulative projections for key indicators for next quarter: a. New network miles leased = 1 b. Number of signed agreements with broadband wholesalers or last mile providers = 0 | Bloomingdale Communications Inc | No issues or challenges other than what is covered above by individual category. Progress is moving along rapidly and really coming together as expected. The project will be competed within the three year window. | BCI does not anticipate any challenges or issues during the next quarter that may impact planned progress against the project milestones listed above other than what is listed in the individual categories above. The project will be completed well within the three year award period timeline. | TRUE
NT10BIX5570099 | 2013 | Q2 | Q2 - 2013 | During this quarter, Quarter 2 of 2013 (Year 3 Quarter 4), Bloomingdale Communications, Inc.'s (BCI) continued to work with Vantage Point Solutions (Vantage Point), the selected engineering firm, regarding the project outside plant inspection services and overall project management. The outside plant (OSP) contractor, Turnkey Network Solutions (Turnkey), finished splicing and testing the fiber optic cable. This accomplishment fulfilled the OSP contract with Turnkey, therefore Vantage Point worked with Turnkey and BCI to close out the contract this quarter. Provisioning has been completed for the Cyan CPE and transport equipment, therefore Community Anchor Institutions (CAIs) began to be cutover to the new network. At the end of this quarter, BCI had turned up 30 CAIs. This quarter, the contract with Cyan was amended to provide additional electronics so BCI and the sub-recipient, Great Lakes Comnet, will each be able to independently control the electronics in the shared fiber network. This equipment was ordered this quarter and will be installed next quarter. The budget was also revised this quarter to shift money between accounts for this amendment. There was no change to the fiber miles installed by the end of the prior quarter as all fiber was placed in the previous quarter. An approximate total of 87.6 miles of fiber has been installed for this project, with approximately 81.1 miles of fiber underground and 6.5 miles of aerial fiber. These totals include buried entrance fiber to all Community Anchor Institutions (CAIs) being included in this project. The joint build coordination with Merit Networks (Merit) on its Round 1 award also continued this quarter. By the end of last quarter, Merit's contractor had installed and placed fiber in a total of 40.02 aerial miles and 9.71 underground miles. This project includes two prefabricated huts which are located in South Haven and Lawrence. The Lawrence hut was completed this quarter and therefore both huts are now complete. The RFPs released last quarter for the hut driveways came back too expensive for asphalt, therefore BCI issued purchase orders for crushed asphalt. The two hut driveways will be completed next quarter. This quarter, BCI awarded contracts for purchase and installation of a new HVAC system and DC Power Equipment for the Bloomingdale Central Office in order to support the new electronics. BCI selected Emergency Power Corp. for the DC Power upgrade based on the RFP released last quarter. The equipment was ordered and will be received and installed next quarter as there was a delay with the powerboard. Hurst Mechanical was selected for the air conditioning unit based on the RFP released last quarter and they installed a new roof top HVAC unit this quarter. The batteries were also received and installed this quarter as well. BCI continued to cut more subscribers over to the new Cisco ASR 9010 core router this quarter. BCI signed service agreements with an additional 9 CAIs during this quarter, therefore bringing the total to 30 signed service agreements as of the quarter end. BCI drew down $424,978 in federal funds in the 2nd quarter of 2013, which is a total of $5,028,960 since the project began. The number of jobs created or retained in this quarter due to this BCI project was 0.69 full time equivalent. This quarter, the project continued coming together and moving along as planned with construction complete, equipment deployed, and CAIs connected the overall project progress is almost complete. As expected, this quarter was very productive and completion of the project is anticipated the project next quarter. | 137 | 1 | 15 | 0 | 137 | 0 | 0 | 13 | As of the end of the fourth quarter 2012, all fiber had been installed. BCI had placed approximately 81.1 miles of buried fiber and 6.5 miles of aerial fiber. The Merit joint build portion of the project had completed 9.71 underground fiber miles and 40.02 aerial fiber miles by the end of last quarter. This is a total of 137 project miles of fiber placed. All new network miles have been completed and the BCI fiber was lit this quarter. | This 1 mile became leased once the network was lit. | These 15 miles became leased once the network was lit. | N/A - No miles were leased prior to the award start date. | As of the end of the fourth quarter 2012, BCI had placed 137 miles of fiber which includes the Merit joint build portion of the project. | N/A | N/A | These interconnection points are accounted for now the network is lit. | 0 | 0 | 0 | N/A | N/A | No designations. | 0 | 0 | 0 | 0 | None projected | None projected | None projected | None projected | 33 | 29 | 4 | 11 | All project CAIs have been connected by the end of this quarter (Quarter 1 2013). This project will be completed well within the three year grant award window. | All project CAIs have been connected by the end of this quarter (Quarter 1 2013). This project will be completed well within the three year grant award window. | Equipment was installed this quarter, therefore all project CAIs have been connected by the end of this quarter (Quarter 1 2013). This project will be completed well within the three year grant award window. | Speed tiers available (11) and subscribers (30): 10 Mbps = 1 20 Mbps = 15 30 Mbps = 0 40 Mbps = 0 50 Mbps = 8 100 Mbps = 6 200 Mbps = 0 300 Mbps = 0 400 Mbps = 0 500 Mbps = 0 1000 Mbps = 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings provided at this time during the project. | FALSE | Not applicable, as no network management practices changed during this quarter. | Continuation of significant project progress is expected for next quarter, Quarter 3 of 2013, as the project will be completed. The amended Cyan contract equipment will be received, installed, and tested during the quarter. The DC Power upgrade will take place next quarter and the upgrade of software will be completed to support the new HVAC unit. The driveways will be completed for the two hut locations during the next quarter as well. Contract closeouts will continue to take place. BCI has made large strides in completing the project and has been turning up CAIs onto the new transport equipment. The project will be complete by the end of next quarter. | Bloomingdale Communications Inc | No issues or challenges other than what is covered above by individual category. Progress is moving along rapidly. The project will be competed next quarter. | We have encountered a delay in shipment of a powerboard that is part of the DC backup upgrade. This equipment is scheduled to ship and be installed prior to the end of July, however, having the equipment inspected and any necessary modifications to the installation may be a challenge. We also anticipate a challenge in having the HVAC system and the new Cyan equipment inspected and any corrections or modifications accomplished prior to the end of July. | TRUE
NT10BIX5570099 | 2013 | Q3 | Q3 - 2013 | During this quarter, Quarter 3 of 2013 (Year 4 Quarter 1), Bloomingdale Communications, Inc.'s (BCI) completed the broadband stimulus project. BCI's initial award end date was July 31, 2013, however this quarter a two month extension was granted due to the encountered delay in shipment of a powerboard which was part of the the DC backup upgrade. As noted last quarter, this equipment was scheduled to ship and be installed in July, however the equipment inspection and any necessary modifications could have been a timing challenge. The challenge of having the HVAC system and amended contract Cyan equipment inspected and modified was also a concern, therefore BCI filed for a two month award period extension which was granted this quarter. With the award period extension, the last day of the award period became September 30, 2013. With the provisioning being completed for the Cyan CPE and transport equipment, Community Anchor Institutions (CAIs) continued to be cutover to the new network. BCI has connected a total of 33 CAIs with this project and BCI has turned up 31 total CAIs. The amended Cyan contract for additional electronics equipment was received, installed, and tested during the quarter so BCI and the sub-recipient, Great Lakes Comnet, will each be able to independently control the electronics in the shared fiber network. All fiber was placed in the previous quarters. An approximate total of 87.6 miles of fiber has been installed for this project, with approximately 81.1 miles of fiber underground and 6.5 miles of aerial fiber. These totals include buried entrance fiber to all CAIs being included in this project. This project also included a joint build coordination with Merit Networks (Merit) on its Round 1 award also continued this quarter. Merit's contractor has installed and placed fiber in a total of 40.02 aerial miles and 9.71 underground miles. BCI did receive and reviewed the as built documentation from Merit for the joint build portion of the project this quarter. This project included two prefabricated huts which are located in South Haven and Lawrence. The hut driveways were completed for the two hut locations during this quarter. Last quarter, BCI awarded contracts for purchase and installation of a new HVAC system and DC Power Equipment for the Bloomingdale Central Office in order to support the new electronics to Emergency Power Corp. The equipment was received and installed this quarter. BCI signed service agreements with an 1 additional CAIs during this quarter, therefore bringing the total to 31 signed service agreements as of the quarter end. BCI drew down $322,891 in federal funds in the 3rd quarter of 2013, which is a total of $5,351,851 since the project began. The number of jobs created or retained in this quarter due to this BCI project was 1.11 full time equivalent. All remaining fiber and equipment testing was finalized this quarter and closeouts continued to take place. BCI has made large strides and has successfully completed the project and has been turning up CAIs onto the new transport equipment. As expected, this quarter was very productive and completion of the project took place. | 137 | 1 | 15 | 0 | 137 | 0 | 0 | 13 | As of the end of the fourth quarter 2012, all fiber had been installed. BCI had placed approximately 81.1 miles of buried fiber and 6.5 miles of aerial fiber. The Merit joint build portion of the project had completed 9.71 underground fiber miles and 40.02 aerial fiber miles by the end of last quarter. This is a total of 137 project miles of fiber placed. All new network miles have been completed and the BCI fiber has been lit. | This 1 mile became leased once the network was lit. | These 15 miles became leased once the network was lit. | N/A - No miles were leased prior to the award start date. | By the end of the fourth quarter 2012, BCI had placed 137 miles of fiber which includes the Merit joint build portion of the project which completed the project miles. | N/A | N/A | These interconnection points became accounted for once the network was lit. | 0 | 0 | 0 | N/A | N/A | No designations. | 0 | 0 | 0 | 0 | None projected | None projected | None projected | None projected | 33 | 29 | 4 | 11 | All project CAIs have been connected by the end of 1st Quarter 2013. | All project CAIs have been connected by the end of 1st Quarter 2013. | All project CAIs have been connected by the end of 1st Quarter 2013. | Speed tiers available (11) and subscribers (31): 10 Mbps = 1 20 Mbps = 16 30 Mbps = 0 40 Mbps = 0 50 Mbps = 8 100 Mbps = 6 200 Mbps = 0 300 Mbps = 0 400 Mbps = 0 500 Mbps = 0 1000 Mbps = 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No special offerings provided at this time during the project. | FALSE | Not applicable, as no network management practices changed during this quarter. | The project was completed this quarter and next quarter will be the close out period. Contracts will be closed out and paid in full as well as the close out deadlines being met. | Bloomingdale Communications Inc | No issues or challenges other than what is covered above by individual category. The project was competed this quarter as expected and BCI is entering into the close out period. | No issues or challenges other than what is covered above by individual category. The project was competed this quarter as expected and BCI is entering into the close out period next quarter. | TRUE
NT10BIX5570100 | 2010 | Q4 | Q4 - 2010 | â€¢ Environmental Assessment started. â€¢ Network Engineering started. â€¢ Pre-Engineering of Network Equipment Complete. â€¢ Land/Building purchase of Marion Datacenter complete. â€¢ Lease space agreements started for space at 900 Walnut St, (carrier hotel, internet gateway). â€¢ Application process started for collocation of remaining 10 central offices. â€¢ Outside plant Engineering Start (engineering includes application/request for access to rights-of-way on city property and state highways and railroad crossings). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | â€¢ Environmental Assessment complete. â€¢ Engineering/Design of Marion Datacenter complete. â€¢ Renovations of Marion Datacenter started. â€¢ In place duct purchase to St. Louis carrier hotel complete. Fiber pulled into duct. â€¢ Orders placed for network transport/access/route/switch and CPE equipment. â€¢ Network design complete. â€¢ Construction permit application process started. â€¢ Agreements regarding matching funds for the remainder of the project finalized. | Delta Communications, L.L.C. | Even though we are ahead of schedule on Environmental Assessment dealing with the various agencies in a timely manner has been a challenge. We are ahead of schedule regarding Rights of Way, however this is a time consuming area. Many of the city councils only meet once or twice a month and it will often take 2-4 meetings to get final approval. In some cases we are having to educate the decision makers about the value that the broadband infrastructure will bring to their area. | Working through Environmental Assessment and receiving our Finding of No Significant Impact (FONSI). Getting to all of the municipalities for Rights of Way Agreements, and continuing to educate certain municipalities about the value of the broadband infrastructure. Completing rights of way agreements with the Illinois Department of Transportation, in particular Controlled Access areas involving Interstate Highway Rights of Way. | TRUE
NT10BIX5570100 | 2011 | Q1 | Q1 - 2011 | Clearwave Communications has seen significant progress in the last quarter. Introductory letters were sent out in January and our sales team has met with each of our community anchor institutions. Seventy more anchors have been contracted this quarter, bringing our contracted anchor total to nearly 33% of our total project. Our network design has been completed, our routes have been selected and a substantial number or right-of-way agreements have been obtained. Construction contracts have been awarded, and our core network equipment has been purchased. Clearwave has chosen our strategic network solutions including transport solutions, routing solutions and access solutions. Our General Contractor has been selected. Our Environmental Assessment (EA) has been completed and we have received our Finding of No Significant Impact (FONSI). Initial construction has begun; Crews are on the routes boring, trenching and laying conduit. By the end of this quarter we had 3 miles of conduit buried. It is more economical to have substantial contiguous miles of conduit in place before blowing the fiber in. Because of this, fiber miles will lag behind conduit miles. We do, however anticipate beginning to blow in fiber during the next quarter. Seven new employees have been hired this quarter, and our General Contractor has contracted workers that are working on construction crews. We have built up a social media following as well, with nearly 200 likes on Facebook and 400 followers on T | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In line with baseline | In line with baseline | In line with baseline | In line with baseline | In line with baseline | N/A | N/A | In line with baseline Narrative (describe your reasons for any variance from the baseline plan or any other relevant informatione (describe your reasons for any variance from the baseline plan or any other relevant information) | 0 | 0 | 0 | None at this time. We have made contact with some third party service providers, but formal negotiations have not begun. | No agreements at this time. | Not applicable. | 0 | 0 | 0 | 0 | In line with baseline | In line with baseline | In line with baseline | N/A | 0 | 0 | 0 | 0 | In line with baseline | In line with baseline | In line with baseline | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time | FALSE | None made. | Clearwave will continue to make progress on construction, completing 120 miles of network. We will also complete the renovations on our Marion Datacenter. We will continue to make progress on obtaining rights of way and permitting to stay ahead of our construction efforts. Clearwave will have contracts signed with 80% of our Community Anchor Institutions. | Delta Communications, L.L.C. | We were able to obtain our FONSI and begin construction during this quarter, which has put us slightly ahead of schedule. The timing of invoices delayed some payments that we expected to make during this quarter. Because of this our match percentage appears to be below the 30% level. This should be back in line next quarter. Although we have had discussions with third party service providers, formal negotiations have not begun since our network will not be lit until the fourth quarter of this year. We do expect to have negotiations begun by the end of the next quarter. | There are several challenges that can impact our planned progress. Our part of the country has been experiencing quit a bit of flooding lately because of heavy rainfall. This prevents us from being able to plow or trench in certain areas. If the wet weather persists, it can negatively impact our construction schedule. We also need to continue the flow of rights of way and permitting from various entities, including local communities and the Illinois Department of Transportation. Any delays in this area would slow down our project's progress. | TRUE
NT10BIX5570100 | 2011 | Q2 | Q2 - 2011 | Construction began to ramp up this quarter as Clearwave ended up with 9 crews working by the end of the quarter. 115 miles of conduit has been buried and 30 miles of fiber has been installed. Our goal is to deploy 8-10 miles per week. Our sales and marketing teams continue to work with our anchor institutions and 141 (over 60%) of them have signed contracts with us. Clearwave participated in several local and regional economic development meetings to help promote the benefits of the project. We continue to build up our social media efforts as well, with over 450 likes on Facebook, close to 400 followers on Twitter, and our website www.clearwavebroadband.com bringing in an average of 70 visitors per week. | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baseline was 75. We have 115 miles of conduit and 30 miles of fiber deployed. In order to be more cost effective with our construction we are delaying the deployment of fiber until we have more continuous miles of conduit deployed. | N/A | N/A | N/A | N/A | N/A | N/A | Baseline was 3. Taken longer to get through the collocation application phase with Frontier and AT&T than we expected. Should be on track by next quarter. | 0 | 0 | 0 | None at this time. We are in discussions with 10 third party service providers, but formal negotiations have not begun. Expect to begin some formal negotiations, including responding to some RFPs by next quarter. | No agreements at this time. | Not applicable. | 0 | 0 | 0 | 0 | Baseline is 1. We are in discussions with 10 third party service providers, but formal negotiations have not begun. Expect to begin some formal negotiations, including responding to some RFPs by next quarter. | In line with baseline | n line with baseline | N/A | 0 | 0 | 0 | 0 | In line with baseline | In line with baseline | In line with baseline | In line with baseline | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | None made. | Clearwave expects to deploy 100-120 miles of conduit in the next quarter, giving us a total of 215-235 miles of conduit deployed. We should be close to 170 miles of fiber deployed and expect to have 8 new interconnection points. | Delta Communications, L.L.C. | The only area above that we were behind on our baseline was Equipment Deployment and it was discussed in the narrative above. We anticipate meeting our baseline projections on equipment deployment for next quarter by August 31. | Continued construction progress is dependent on our continued ability to obtain rights of ways and permits from Illinois Department of Transportation, Core of Engineers, railroads and local municipalities. We donâ€™t anticipate the delays in obtaining any of these permits to cause us to fall behind our baseline. | TRUE
NT10BIX5570100 | 2011 | Q3 | Q3 - 2011 | Clearwave continued to take advantage of the favorable weather and made significant progress in our construction. With as many as 15 crews working at different times during the quarter we ended up with 215 miles of conduit buried and 170 miles of fiber installed, including fiber into 8 of our interconnection points. Our sales and marketing teams continue to work with our anchor institutions and 183 (over 78%) of them have signed contracts with us. Clearwave continues to participate in local and regional economic development meetings to help promote the benefits of the project. Our social media efforts continue as well, with over 830 likes on Facebook, 468 followers on Twitter, and our website www.clearwavebroadband.com bringing in an average of 90 visitors per week. | 170 | 0 | 0 | 0 | 170 | 0 | 0 | 8 | Baseline was 168 - slightly ahead of baseline | NA | NA | NA | Baseline was 168 - slightly ahead of baseline | NA | NA | On baseline | 0 | 3 | 0 | No wholesale or last mile providers have signed agreements to date. It is difficult to get signed agreements until the network is live, which we should have by the end of the year. We are in negotiations and hope to have some signed agreements before the end of the year. | None at this point. | NA. | 0 | 0 | 0 | 0 | Baseline was 2. This process is going slower than expected. Most carriers want at least part of the network to be lit before they sign an agreement. | NA | NA | NA | 0 | 0 | 0 | 0 | On baseline | On baseline | On baseline | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | Clearwave expects to have a portion of the network lit by the end of next quarter and expect to meet or exceed exceed the following milestones: Network miles - 254 New interconnect points - 13 Community Anchor Institutions Served: 30 | Delta Communications, L.L.C. | During this quarter there were no challenges or issues that kept us from achieving our project milestones. Because of this we are on or ahead of our project milestones. | The biggest issue that we could face next quarter would be weather related. We have been fortunate over the last several months with weather that is very conducive for construction. We are entering a time of year that weather can become problematic. | TRUE
NT10BIX5570100 | 2011 | Q4 | Q4 - 2011 | Clearwave continued to take advantage of the favorable weather and made significant progress in our construction. With as many as 15 crews working at different times during the quarter we ended up with 350 miles of conduit buried and 260 miles of fiber installed, including fiber into 15 of our interconnection points. We now have continuity from the Carrier Hotel in St. Louis to our Data Center in Marion. Clearwave has already exceeded the 67% complete benchmark ahead of schedule, and if construction continues at the current pace it is possible that the project could be 100% complete by the end of first quarter 2013. 80% of Clearwaveâ€™s projected Community Anchor Institutions have contracted for service and 40 of them have fiber run and equipment installed at their premise. Clearwave continues to participate in local and regional economic development meetings to help promote the benefits of the project. Our social media efforts continue as well, with over 1000 likes on Facebook, and over 550 followers on Twitter. | 260 | 0 | 0 | 0 | 260 | 0 | 0 | 15 | Ahead of baseline which is 254 | N/A | N/A | N/A | Ahead of baseline which is 254 | N/A | N/A | Ahead of baseline which is 13. | 0 | 6 | 0 | None. This process is going slower than expected. Most carriers want at least part of the network to be lit before they sign an agreement. | None | N/A | 0 | 0 | 0 | 0 | N/A | Baseline was 1. This process is going slower than expected. Most carriers want at least part of the network to be lit before they sign an agreement. | N/A | N/A | 40 | 0 | 40 | 0 | 40 CAIs are connected, but are not yet receiving service. | N/A | 40 CAIs are connected, but are not yet receiving service. | 40 CAIs are connected, but are not yet receiving service. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None | FALSE | None | Clearwave expects to have CAIs receiving bandwidth and internet service by the end of next quarter. We also expect to meet or exceed exceed the following milestones: Network miles - 350 New interconnect points - 16 Community Anchor Institutions Served: 64 Last Mile Service Provider Contracts: 1 Clearwave has already exceeded the 67% complete benchmark ahead of schedule, and if construction continues at the current pace it is possible that the project could be 100% complete by the end of first quarter 2013. | Delta Communications, L.L.C. | We have managed to meet or exceed almost all of our baseline milestones. | Winter weather could present a challenge to our progress this next quarter. Other than that, we don't anticipate any other challenges that would impact our ability to remain ahead of schedule. | TRUE
NT10BIX5570100 | 2012 | Q1 | Q1 - 2012 | Clearwave continued to take advantage of the favorable weather and made significant progress in our construction. With as many as 15 crews working at different times during the quarter we ended up with 503 miles of conduit buried and 407 miles of fiber installed, including fiber into 15 of our interconnection points. Clearwave has already exceeded the 67% complete benchmark ahead of schedule, and if construction continues at the current pace it is possible that the project could be 100% complete by the end of first quarter 2013. Over 200 of Clearwaveâ€™s projected Community Anchor Institutions have contracted for service and 70 of them have fiber run and equipment installed at their premise. We will begin to light up service for these customers during the next quarter. Clearwave continues to participate in local and regional economic development meetings to help promote the benefits of the project. Our social media efforts continue as well, with over 1050 likes on Facebook, and over 600 followers on Twitter. | 407 | 0 | 0 | 0 | 407 | 0 | 0 | 15 | Ahead of Baseline of 350 | N/A | N/A | N/A | Ahead of Baseline of 350 | N/A | N/A | Baseline is 16. Slightly behind getting fiber pulled into central offices. | 1 | 8 | 20 | [REDACTED] | While our agreement has been signed, no services were provided during this quarter. Construction will need to be completed to the various cell sites before services can be delivered. Some will be completed by next quarter. | N/A | 0 | 1 | 0 | 0 | Baseline is 0 | Slightly behind baseline of 2. Most providers waiting until network is operational to finalize negotiations. | N/A | N/A | 63 | 0 | 63 | 0 | 63 CAIs are connected, but none are currently receiving service. | N/A | 63 CAIs are connected, but none are currently receiving service. | 63 CAIs are connected, but none are currently receiving service. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Clearwave will have CAIs receiving bandwidth and internet service by the end of next quarter. We also expect to meet or exceed exceed the following milestones: Network miles - 461 New interconnect points - 19 Community Anchor Institutions Served: 102 Last Mile Service Provider Contracts: 1 Clearwave has already exceeded the 67% complete benchmark ahead of schedule. If construction continues at the current pace it is possible that the project could be 100% complete by the end of first quarter 2013. | Delta Communications, L.L.C. | We have managed to meet or exceed almost all of our baseline milestones. | Wet weather in the spring could slow down construction progress. We do not anticipate any other challenges that would impact our ability to remain ahead of schedule. | TRUE
NT10BIX5570100 | 2012 | Q2 | Q2 - 2012 | Clearwave continued to stay ahead of our baseline construction schedule. We are up to 610 miles of conduit buried and 545 miles of fiber installed, including fiber into 18 of our interconnection points. 217 of Clearwaveâ€™s projected Community Anchor Institutions have contracted for service. 94 of them have fiber run and equipment installed at their premise and 64 are receiving service. Our social media efforts continue as well, with over 1096 likes on Facebook, and over 680 followers on Twitter. | 545 | 0 | 0 | 0 | 545 | 0 | 0 | 18 | Ahead of baseline of 461 | N/A | N/A | N/A | Ahead of baseline of 461 | N/A | N/A | Slightly behind baseline of 19 | 1 | 8 | 20 | [REDACTED] | While our agreement has been signed, no services were provided during this quarter. Construction will need to be completed to the various cell sites before services can be delivered. | N/A | 0 | 1 | 0 | 0 | Baseline is 0 | Slightly behind baseline of 2. Most providers waiting until network is operational to finalize negotiations. | N/A Was not a part of our business plan or baseline | N/A | 94 | 0 | 94 | 0 | Slightly behind baseline of 102. | N/A | Slightly behind baseline of 102. | Speeds ranging from 10 Mbps to 1 Gbps 10-49Mbps: 53 50-99Mbps: 19 100-499Mbps: 21 1Gbps+: 1 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None | FALSE | None | Clearwave will continue to stay ahead of schedule on construction. We will also continue to turn on service for more of 200+ CAIs that have contracted for service. We plan to meet or exceed the following milestones: Network miles - 538 New interconnect points - 23 Community Anchor Institutions Served - 135 | Delta Communications, L.L.C. | Clearwave continued to meet or exceed almost all of our baseline milestones. | We do not anticipate any other challenges that would impact our ability to remain ahead of schedule. However wet weather could delay progress from the planned progress listed above. Even with delays we would remain ahead of our baseline. Overall project is going over budget due to higher construction costs than anticipated. Due to confidence in the execution our business plan we have been able to secure additional private funding which will allow us to complete the project. Depending on weather conditions we may be able to complete construction by the end of the first quarter 2013. This would be two quarters ahead of schedule. | TRUE
NT10BIX5570100 | 2012 | Q3 | Q3 - 2012 | Clearwave continued to stay ahead of our baseline construction schedule. Our plan called for 740 miles of fiber to be completed by August of 2013. Through the end of September 2012 we are up to 665 miles of conduit buried and 630 miles of fiber installed, including fiber into 24 of our interconnection points. Clearwaveâ€™s plan called for 232 Community Anchor Institutions to be connected by August 2013. Through the end of September 2012 225 of our Community Anchor Institutions have been contracted for service. 120 of them have fiber run and equipment installed at their premise and 114 are receiving service. Our social media efforts continue as well, with 1098 likes on Facebook, and over 700 followers on Twitter. | 630 | 0 | 0 | 0 | 630 | 0 | 0 | 24 | Ahead of baseline of 538 | NA | NA | NA | Ahead of baseline of 538 | NA | NA | Ahead of baseline of 23 | 2 | 10 | 20 | [REDACTED] | Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | NA | 0 | 2 | 0 | 0 | In line with baseline | Slightly behind baseline of 3. We are negotiating another contract as of the time of this report, however it has not been executed. | NA | Only one of the two service providers contracted are live at this point. Speeds ranging from 50 Mbps to 1 Gbps 50-99Mbps: 0 100-499Mbps: 1 1Gbps+: 0 | 120 | 0 | 120 | 0 | Slightly behind baseline of 135 | NA | Slightly behind baseline of 135 | Speeds ranging from 10 Mbps to 1 Gbps 10-49Mbps: 70 50-99Mbps: 22 100-499Mbps: 27 1Gbps+: 1 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | No special offerings | FALSE | No changes | Clearwave will continue to push towards completing construction ahead of schedule. We will also continue to turn on service for more of 200+ CAIs that have contracted for service. We plan to meet or exceed the following milestones: Network miles - 675 New interconnect points - 27 Community Anchor Institutions Served - 170 | Delta Communications, L.L.C. | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570100 | 2012 | Q4 | Q4 - 2012 | Clearwave continued to stay ahead of our baseline construction schedule. Our plan called for 740 miles of fiber to be completed by August of 2013. Through the end of December 2012 we are up to 702 miles of conduit buried and 672 miles of fiber installed, including fiber into 27 of our interconnection points. Clearwaveâ€™s plan called for 232 Community Anchor Institutions to be connected by August 2013. Through the end of December 2012, 225 of our Community Anchor Institutions (CAIs) have been contracted for service. 143 of them have fiber run and equipment installed at their premise and 139 are receiving service. These CAIs are utilizing the increased bandwidth in many different ways. Examples include a community college expanding it's on-line classes and a Benton, IL school that is "flipping" their classrooms, implementing Bring Your Own Device. Clearwave is sharing some of our CAIs' success stories on our blog which can be found at http://clearwave.com/clearwave/index.cfm/blog/. Clearwaveâ€™s overall project has gone over budget due to higher construction costs than anticipated. We have completed over 90% of our construction and have spent 100% of our Federal money. Due to confidence in the execution our business plan we have been able to secure additional private funding which is allowing us to complete the project ahead of schedule. | 672 | 0 | 0 | 0 | 672 | 0 | 0 | 27 | Ahead of baseline of 630 | NA | NA | NA | Ahead of baseline of 630 | NA | NA | In line with baseline of 27 | 4 | 8 | 20 | [REDACTED] | Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | NA | 0 | 4 | 0 | 0 | In line with baseline | In line with baseline | NA Dark fiber not a part of project plan | Three of the four service providers contracted are live at this point. Speeds ranging from 50 Mbps to 1 Gbps 50-99Mbps: 1 100-499Mbps: 3 1Gbps+: 0 | 143 | 0 | 143 | 0 | Slightly behind baseline of 169 | In line with baseline | Slightly behind baseline of 169 | Speeds ranging from 10 Mbps to 1 Gbps 10-49Mbps: 84 50-99Mbps: 30 100-499Mbps: 28 1Gbps+: 1 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | None | FALSE | No changes. | Clearwave plans to have the project completed by the end of the next quarter. That would include: 740 miles of fiber 232 CAIs connected 5 Third Party Agreements signed | Delta Communications, L.L.C. | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570100 | 2013 | Q1 | Q1 - 2013 | Clearwave is nearing completion of our project ahead of our baseline construction schedule. Our plan called for 740 miles of fiber to be completed by August of 2013. Through the end of March 2013 we are up to 745 miles of conduit buried and 710 miles of fiber installed, including fiber into 28 of our interconnection points. Clearwaveâ€™s plan called for 232 Community Anchor Institutions to be connected by August 2013. Through the end of March 2013, 225 of our Community Anchor Institutions have been contracted for service. 171 of them have fiber run and equipment installed at their premise and are receiving service. Clearwaveâ€™s overall project has gone over budget due to higher engineering and construction costs than anticipated. We have completed over 95% of our construction and have spent 100% of our Federal money. Due to confidence in the execution our business plan we have been able to secure additional private funding which is allowing us to complete the project ahead of schedule. | 710 | 0 | 0 | 0 | 710 | 0 | 0 | 28 | Slightly behind baseline of 723. | NA | NA | NA | Slightly behind baseline of 723. | NA | NA | Slightly behind baseline of 31. | 5 | 9 | 20 | [REDACTED] | Clearwave currently offers the following wholesale services: Direct Internet Access (DIA) and Ethernet Transport. These are priced on an individual basis, based on variables including interconnection ability, cost of construction, Service Level Expectations, and length of term. | NA | 0 | 5 | 0 | 0 | In line with baseline | In line with baseline | NA. Dark fiber is not a part of the project plan. | Speeds ranging from 50 Mbps to 1 Gbps 50-99 Mbps: 1 100-499 Mbps: 3 500-1Gbps: 1 | 171 | 0 | 171 | 0 | Behind baseline of 198 | NA | Behind baseline of 198 | Speeds ranging from 10 Mbps to 1 Gbps 10-49 Mbps: 104 50-99 Mbps: 38 100-499 Mbps: 28 500-999 Mbps: 0 1 Gbps+: 1 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | None. | FALSE | None | Clearwave plans to have project completed by the end of the next quarter including: 740+ miles of fiber deployed 31 Interconnect Points 232 CAIs connected 5 Third Party Providers signed. | Delta Communications, L.L.C. | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570100 | 2013 | Q2 | Q2 - 2013 | Clearwave is nearing on time completion of our project which has a scheduled end date of July 31, 2013. Our Baseline Plan called for 740 miles of fiber to be completed by the end of the project. Through the end of June 2013 we are up to 751 miles of fiber installed, including fiber into 30 of our interconnection points. Clearwaveâ€™s Baseline Plan called for 232 Community Anchor Institutions to be connected by the end of the project. Through the end of June 2013, 185 of those identified in our application are connected with 14 to be completed in July. Clearwave has submitted a route modification request (AAR #2433865) that if approved would add an additional 34 CAIs that have been connected. Clearwaveâ€™s overall project has gone over budget due to higher engineering and construction costs than anticipated. Due to confidence in the execution our business plan we have been able to secure additional private funding which is allowing us to complete the project. | 751 | 0 | 0 | 0 | 751 | 0 | 0 | 30 | Higher than baseline of 740 | NA | NA | NA | Higher than baseline of 740 | NA | NA | In line with baseline as adjusted through AARs. | 5 | 9 | 20 | [REDACTED] | Clearwave currently offers the following wholesale services: Direct Internet Access (DIA) and Ethernet Transport. These are priced on an individual basis, based on variables including interconnection ability, cost of construction, Service Level Expectations, and length of term. | NA | 0 | 5 | 0 | 0 | In line with baseline | In line with baseline | NA. Dark fiber is not a part of the project plan | Speeds ranging from 50 Mbps to 1 Gbps 50-99 Mbps: 1 100-499 Mbps: 3 500-1Gbps: 1 | 185 | 0 | 185 | 0 | Behind baseline due to some CAIs opting out. Clearwave has submitted an AAR that if approved would add an additional 34 CAIs that have been connected. | NA | Behind baseline due to some CAIs opting out. Clearwave has submitted an AAR that if approved would add an additional 34 CAIs that have been connected. | Speeds ranging from 10 Mbps to 1 Gbps 10-49 Mbps: 104 50-99 Mbps: 38 100-499 Mbps: 28 500-999 Mbps: 0 1 Gbps+: 1 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | None. | FALSE | NA | Clearwave will finish connecting the remaining 14 CAIs in July. We expect one more mile of network to be completed bringing our total to 752. Clearwave has submitted a route modification request (AAR #2433865) that if approved next quarter would add an additional 34 CAIs that have been connected. All activities will be complete by the end of July which is the End Date for the project. Closeout activities will begin in August. | Delta Communications, L.L.C. | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570100 | 2013 | Q3 | Q3 - 2013 | Clearwave completed the project on July 31, 2013. We completed approximately one mile of fiber construction during July bringing our total fiber miles to 749. Our route modification request (AAR #2433865) was approved in July allowing us to add 34 Community Anchor Institutions (CAIs) bringing our project total to 230. Clearwave was fortunate to have an existing sales team that had a strong presence in most of our proposed service area which enabled us to serve 230 CAIs by the end of our project. Among these 230 CAIs, we were able to greatly improve the bandwidth connectivity at 105 K-12 Schools and 62 Medical facilities. These institutions will be able to benefit from the BTOP initiative for years to come, and our company is proud to have been a part of that initiative. One example is Benton Consolidated High School where Calculus became one of the first classes in southern Illinois to implement a â€œflipped classroomâ€. In a flipped classroom environment, the teacher records lectures for the students to watch outside of the classroom as their homework. This allows the time in the classroom to be actively spent problem solving and receiving guided one-on-one instruction, making certain the students are doing their work correctly and understanding the material, in turn ensuring better grades on quizzes and exams. â€œThe students watch videos as homework and class time is spent solving problems with their teacher,â€ the Curriculum/Technology Director said. â€œWe are very grateful to be part of this amazing project and see much potential on how student learning can be transformed.â€ The fiber optic implementation also encourages teachers and students to participate in a Bring Your Own Device (BYOD) program, and because instruction is increasingly digital, the introduction of digital devices in the classroom is essential. A second example is Southeastern Illinois College (SIC), a local community college in Harrisburg where broadband enables its online learning curriculum. According to the Chief Information Officer, â€œThe speed difference is incredible. We could not stream a simple YouTube instructional video prior to the upgrade that many users would just take for granted in their own home. Southeastern needed this additional capacity to remain an online leader for online programs in our area.â€ SIC is a recipient of a Title III Strengthening Institutions Grant. This grant is put in place to develop online programs and services for local students. SICâ€™s CIO said achieving these initiatives would be difficult without the opportunity of higher bandwidth. In addition to the new programs brought by the Grant, SIC is also building on its current online Nursing, Business, Criminal Justice, Biotechnology and Biofuels programs. Washington County Hospital in southern Illinois is a third example of the way BTOP impacted our community. Prior to BTOP, Washington County Hospital had been limited to a 75Mbps/5Mbps connection that was not capable of handling its needs any longer. â€œI had issues with the 5Mbps up in trying to push all of our diagnostic imaging studiesâ€ said their Chief Information Officer (CIO). â€œThe file sizes were so big, and it was just taking forever to move the informationâ€. â€œWe do our back-ups here in the hospital,â€ their CIO said. â€œThe 20Mbps/20Mbps we have from Clearwave, however, is going to be enough for us to start pushing our back-up offsite.â€ What might be Washington County Hospitalâ€™s biggest benefit of the fiber connection is the ability to now cut patient time in the emergency room. At prior 5Mbps up speeds, the images had to fully transmit to Springfield before the radiologists could begin reading them, which cost the hospital and the patientâ€™s precious time. â€œFor patients, their images are getting where they need to go much more quickly, so their time spent in the ER is substantially decreased,â€ the CIO said. â€œItâ€™s knocked 30-40 minutes out of ER time because weâ€™re able to send the images much quicker.â€ Turnaround time on the imaging reports had been a huge issue, but the Clearwave fiber has really made a difference with Washington County Hospital patients. | 749 | 0 | 0 | 0 | 749 | 0 | 0 | 30 | Slightly higher than baseline of 740 | NA | NA | NA | Slightly higher than baseline of 740 | NA | NA | In line with baseline as adjusted through AARs | 6 | 0 | 20 | [REDACTED] | Clearwave currently offers the following wholesale services: Direct Internet Access (DIA) and Ethernet Transport. These are priced on an individual basis, based on variables including interconnection ability, cost of construction, Service Level Expectations, and length of term. | NA | 0 | 6 | 0 | 5 | In line with baseline | Ahead of baseline of 5. | NA. Dark fiber is not a part of the project plan. | Speeds ranging from 50 Mbps to 1 Gbps 50-99 Mbps: 1 100-199: 4 200-499 Mbps: 0 500-1Gbps: 1 1Gbps+: 0 | 230 | 0 | 230 | 5 | Baseline was 232. | NA | Baseline was 232 | Speeds ranging from 10 Mbps to 1 Gbps 10-49 Mbps: 144 50-99 Mbps: 58 100-499 Mbps: 48 500-999 Mbps: 0 1 Gbps+: 2 This count represents the total circuits or services subscribed to. This count of 258 is higher than the number of subscribers because some subscribers have more than one circuit or service. An example would be a school that has a circuit for Internet connectivity through us and a point to point circuit for connectivity to the Illinoiis Century Network. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | None | FALSE | None | Although the BTOP project is complete there is still much work to be done in southern Illinois. Clearwave plans to add new last mile customers to the network, including more schools, hospitals, and libraries, and we plan to work with third party service providers to expand the impact of the middle mile network. Clearwave also intends to pursue other funding opportunities to expand the BTOP network into more rural communities that need broadband capability but where construction is cost prohibitive without government subsidies. One such opportunity is the rural trials proposed in the FCC IP Technology Transitions Report and Order and Further Notice of Proposed Rulemaking. Clearwave plans on submitting an Expression of Interest (EOI) to the FCC by the March 7th deadline. Clearwave is also following developments regarding ConnectEd and other such programs that will allow us to extend the benefits of broadband to areas in southern Illinois that remain underserved | Delta Communications, L.L.C. | The Environmental Group at NTIA did an excellent job in processing our AAR on a timely basis and because of that we were able to add additional CAIs to replace those that had to opt out for various reasons. The project is complete and ended up costing $55,002, 467 which is $9,607,447 over the initial estimate. In order to complete the project Clearwave provided $9,607,447 of additional matching funds, of which $2,556,898 is program income. | There is no next reporting quarter since our project is complete and this is our final PPR Report. | TRUE
NT10BIX5570101 | 2010 | Q4 | Q4 - 2010 | - Commencement of environmental assessment process. Completed initial alignment map, project descriptions and narrative, SHPO archival search and desktop reviews, wetland searches and development of endangered species lists. Commenced with consultation process with various agencies. - Refined and finalized fiber routes. Produced primary and alternate routes and mapping required for environmental assessment process. - Resolved various special awards conditions. - Hired consultants to assist with grant admin and compliance, environmental assessment and engineering. - Performed independent valuation of in-kind fiber assets. - Developed and implemented procurement policy. - Setup accounting system and other business systems and controls. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | N/A | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | FALSE | N/A | - Completion of environmental assessment research, consultations with all agencies and submission of draft EA. - Commencement of engineering surveying and right of way perfection. - Commencement of permitting applications for primary routes. - Development of draft requirements for material and labor RFQ/RFPs. | Appalachian Valley Fiber Network | N/A | A 3 weeks extension for our draft EA submission deadline has been requested. This is expected to result in a corresponding delay in completion of our network design/engineering efforts. We expect to make up the lost time on engineering and complete 100% as planned by the end of June 2011. | TRUE
NT10BIX5570101 | 2011 | Q1 | Q1 - 2011 | Submitted initial draft EA, conducted required consultations with Fish and Wildlife, SHPO and other agencies, prepared and submitted various permit, right of way and permit applications, commenced with initial design/engineering work, created public website for AVFN, resolved overlaps with other BIP/BTOP applicants. There is a difference in expenditures in the PPR and FFR of $1771 this is due to cash on hand as indicated in the FFR. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | N/A | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | None at this time. Construction has not commenced, pending completion of EA and issuance of FONSI. | FALSE | N/A | Key activities for next quarter are to complete EA, obtain FONSI, complete network design, issue RPFs for materials and labor, and obtain all necessary rights of way and permits. | Appalachian Valley Fiber Network | If we can complete the EA process and obtain our FONSI in the Apr-Jun 2011 quarter, we expect to be able to accelerate network design and equipment procurement efforts in the Jul-Sep quarter. | We will have to work hard to overcome delays in EA process. | TRUE
NT10BIX5570101 | 2011 | Q2 | Q2 - 2011 | Completed consultations with all EA parties. Submitted final EA. Completed RFQ process for fiber cabling and selected vendor. Issued RFQ for conduit and other materials. Prepared RFQs for construction labor and materials. Negotiated IRU lease with railroad for route to Chattanooga. Launched AVFN.net website. Completed all base mapping and walk/drive-out work to support engineering efforts. Obtained various franchise agreements with cities. Developed the initial package of engineering materials and began the permitting process with DOT and other parties. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The baseline report indicated that 19.82 new network miles would be deployed. Due to delays in the Environmental Assessment this was not accomplished as construction was delayed. It is AVFN's expectation that the environmental assessment will be complete in the next quarter and we will be back on schedule. | No variance | No variance | No variance | The baseline report projected this number at 79.82. this total is the total number miles contributed and newly constructed. Due to delay in the in kind match approval and environmental assessement, this was not acheived. However, it is AVFN's expectation that both will be approved in the next quarter. As result of the approval, we will back on schedule. | The baseline report projected this number at 181. this total is the total number contributed and newly constructed. Due to delay in the in kind match approval and environmental assessement, this was not acheived. However, it is AVFN's expectation that both will be approved in the next quarter. As result of the approval, we will back on schedule. | No variance | No variance | 0 | 0 | 0 | N/A | None at this time. Construction has not commenced, pending issuance of FONSI. | None at this time. Construction has not commenced, pending issuance of FONSI. | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | None at this time. Construction has not commenced, pending issuance of FONSI. | FALSE | N/A | Key activities for next quarter are to obtain our FONSI (EA has been submitted), complete our network design and engineering, contract for all fiber cabling, materials and labor, obtain all necessary rights of way and permits, and commence with our initial construction phases. | Appalachian Valley Fiber Network | We struggled this quarter to complete our EA and obtain our FONSI. This is now being resolved and we are awaiting our FONSI. Another issue that impacted us was not being able to obtain approval for our match/in-kind contribution. Both issues are on-track to be resolved next quarter. | Overcoming delays resulting from the EA. Getting to a point where we have recognized our in-kind contributions appropriately. Fiber availability in the marker is also constrained. Beginning to work with our new material and labor suppliers will require close monitoring and management. | TRUE
NT10BIX5570101 | 2011 | Q3 | Q3 - 2011 | Obtained EA. Executed agreements with selected construction vendors. Purchased conduit and other materials. Executed agreement with Regional Commission and completed marketing outreach plan. Obtained various franchise agreements with cities. Continued permitting process with DOT and other parties. Obtained "Other Common Carrier" or OCC status for the State of Georgia and Alabama. Constructed 38 miles of conduit. | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 280 | We estimated 40 miles in our baseline. We achieved 38 miles of CONDUIT construction (due to lack of fiber availability). Since we can only record miles deployed once fiber is deployed, we are required to record our progress as 0 miles. | No variance. | No variance. | No variance. | We estimated 100 miles in our baseline, however we interpreted this to mean the number of new miles deployed PLUS the number of new miles leased. We now understand that leased miles should not have been included in this category. We achieved 38 miles of new CONDUIT construction (due to lack of fiber availability), but were unable to county these miles since fiber has not been deployed. See above. | Not applicable. | Not applicable. | Exceeds baseline. No variance. | 0 | 1 | 0 | None at this time. | None at this time. Until we have fiber cabling, it is not possible to wholesale services over the network. | Not applicable. | 0 | 0 | 0 | 0 | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | 0 | 0 | 0 | 0 | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | None at this time. | FALSE | N/A | Continue to aggressively construct conduit. We expect to have 80 total/cumulative miles deployed at the end of the next quarter. Complete our IRU for fiber to Chattanooga with the railroad. Purchase additional electronics and other equipment. Continue executing on community outreach plan and engaging CAIs. Complete our engineering efforts. Continue permitting process for areas to be constructed. Negotiate wholesale service provider agreements. We project a cumulative 0 new network miles deployed by the end of Q4, which is due to the lack of fiber availability. We project a cumulative 250 new network miles leased, which results from the 60 miles already leased from Parker FiberNet and the 190 miles being leased from the Railroad (Atlanta - Chattanooga). We project a cumulative 0 total CAI subscribers served, which is due to the lack of fiber availability. We project a cumulative 1 signed agreements with broadband wholesalers or last mile providers. | Appalachian Valley Fiber Network | Fiber availability continues to be constrained. | Fiber availability. We continue to explore other avenues to minimize impact to the project. While cold weather doesn't impact our construction schedule much, we tend to get more rain in the winter months, and this does cause delays with underground construction. | TRUE
NT10BIX5570101 | 2011 | Q4 | Q4 - 2011 | Continued with aggressive conduit construction, despite lack of fiber availability; 71 miles deployed (cumulative). Executed IRU for 197 miles of fiber (Atlanta to Chattanooga) with railroad. Successfully completed NTIA site visit and required audits. Prepared, released and awarded several construction RFPs. Set up and administered systems for materials procurement, inventory control, warehousing, staging and other key backoffice functions. | 0 | 257 | 0 | 0 | 0 | 0 | 0 | 443 | We projected 60 miles in our original baseline. We achieved 71 miles of CONDUIT construction (due to lack of fiber availability). Since we can only record miles once fiber is deployed, we are required to record 0 miles this quarter. | No variance. Exceeding the goals from our original baseline. Includes 60 miles from PFN and 197 miles from Norfolk Southern IRU. | No variance. | No variance. | We estimated 120 miles in our baseline, however we interpreted this to mean the number of new miles deployed PLUS the number of new miles leased. We now understand that leased miles should not have been included in this category. We achieved 71 miles of new CONDUIT construction (due to lack of fiber availability), but were unable to county these miles since fiber has not been deployed. See above. | No variance. | No variance. | No variance. Exceeding the goals from our original baseline. | 0 | 1 | 0 | None at this time. No fiber deployed yet. | None at this time. No fiber cabling, no wholesale services. | Not applicable. | 0 | 0 | 0 | 0 | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | 0 | 0 | 0 | 0 | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | Until we have fiber cabling to install in the ducts that have been deployed, it is not possible to provide services over the network. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | None at this time. | FALSE | N/A. | Continue aggressive deployment of conduit. Receive our first orders of fiber cabling and begin the process of blowing/pulling it into existing conduit. | Appalachian Valley Fiber Network | Lack of fiber availability. BTOP program is already providing value for us in this area by sharing their insights and experiences from other projects. | There is some risk that vendors who have committed to deliver fiber cabling will fail to deliver, or will communicate further delays. | TRUE
NT10BIX5570101 | 2012 | Q1 | Q1 - 2012 | Began receiving fiber cabling and blowing into existing conduit. Re-engaged environmental consultants to perform archeological and cultural monitoring at construction sites, per FONSI and SAC. Continued aggressive construction of conduit. Completed final engineering for Georgia and commenced with Alabama. | 16 | 257 | 0 | 0 | 16 | 0 | 0 | 713 | We projected 88 miles in our original baseline. We achieved 125 miles of CONDUIT construction. We began receiving fiber cabling towards the end of this quarter and were able to blow in a total of 16 miles of this cable into the already-constructed conduit. | No variance. Exceeding goals from our original baseline. Includes 60 miles from PFN and 197 miles from Norfolk Southern IRU. | No variance. | No variance. | We estimated 188 miles in our baseline, however we interpreted this to mean the number of new miles deployed PLUS the number of new miles leased. We now understand that leased miles should not have been included in this category. | No variance. | No variance. | We estimated 256 in our original baseline. No variance. | 1 | 3 | 12 | Parker FiberNet | AVFN has an agreement with Parker FiberNet to provide wholesale dark fiber services, however, these services were not yet being provided as of the end of this (March) quarter. Pricing will be set on a per-end-customer (CAI) basis. | Not applicable. | 1 | 1 | 1 | 0 | No variance. | No variance. | No variance. | No lit/managed services are being provided until electronics are purchased and integrated. Only dark fiber at this time. | 0 | 0 | 0 | 0 | No variance. | No variance. | No variance. | No variance. | 0 | 0 | 0 | 0 | 0 | No applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | FALSE | Not applicable. | Substantial completion of Alabama engineering. Achievement of 2/3 complete milestone. Catch-up on blowing in of fiber cabling into existing conduit. Procurement of network electronics. We expect to have a cumulative total of 175 route miles (conduit AND fiber) deployed by the end of Q2 2012 (June 30). We expect to have a cumulative total of eight (8) CAIs connected by the end of the Q2 2012 (June 30). We expect to have a cumulative total of one (1) broadband wholesaler/last mile provider agreement in place by the end of Q2 2012 (June 30). | Appalachian Valley Fiber Network | We began receiving fiber cabling this quarter, and we had the challenge of getting caught up on blowing fiber in conduit that had been deployed. Continued delays in receiving railroad permits that have been submitted. More stringent permitting requirements for Alabama DOT. | We will be focused on meeting our 2/3 completion milestone in the next quarter. This will require getting all electronics procured from the ongoing RFP process, and getting all fiber blown into (caught up) with existing conduit. We also hope to substantially complete the remaining (Alabama) engineering. | TRUE
NT10BIX5570101 | 2012 | Q2 | Q2 - 2012 | We caught up substantially on the blowing in of fiber into our existing conduit. Combined with new conduit placement, this resulted in an increase of 134 miles of new fiber construction. | 150 | 257 | 0 | 0 | 150 | 0 | 0 | 874 | No variance. | No variance. Exceeding goals from our original baseline. Includes 60 miles from PFN and 197 miles from Norfolk Southern IRU. | No variance. | No variance. | We estimated 188 miles in our baseline, however we interpreted this to mean the number of new miles deployed PLUS the number of new miles leased. We now understand that leased miles should not have been included in this category. | No variance. | No variance. | No variance. | 1 | 3 | 12 | Parker FiberNet. | AVFN has an agreement with Parker FiberNet to provide wholesale dark fiber services. Pricing will be set on a per-end-customer (CAI) basis. | Not applicable. | 1 | 1 | 1 | 0 | No variance. | No variance. | No variance. | No lit/managed services are being provided until electronics are purchased and integrated. Only dark fiber at this time. | 13 | 13 | 0 | 1 | Our forecast was to have 8 CAIs by the end of this quarter. No variance. | All subscribers are new at this point. | N/A | Service are Ethernet, which supports speeds up to 10 Gbps. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Ethernet services. | FALSE | None. | Commencement of AL construction. Full installation and integration of network electronics. We expect to have 190 miles of fiber constructed by the end of the quarter. We expect to have 23 CAIs connected by the end of the quarter. We expect to have one (1) broadband wholesaler/last mile provider agreements in place by the end of the quarter. | Appalachian Valley Fiber Network | None. | None. | TRUE
NT10BIX5570101 | 2012 | Q3 | Q3 - 2012 | Completed engineering for AL. Submitted all required permits for AL to ALDOT. Full installation and integration of network electronics. Continued installation of conduit and fiber placement. | 192 | 257 | 0 | 0 | 192 | 0 | 0 | 912 | No variance. | No variance. Exceeding goals from our original baseline. Includes 60 miles from PFN and 197 miles from Norfolk Southern IRU. | No variance. | No variance. | We estimated 206 miles in our baseline, however we interpreted this to mean the number of new miles deployed PLUS the number of new miles leased. We now understand that leased miles should not have been included in this category. | No variance. | No variance. | No variance. | 1 | 3 | 12 | Parker FiberNet. | AVFN has an agreement with Parker FiberNet to provide wholesale dark fiber services. Pricing will be set on a per-end-customer (CAI) basis. | Not applicable. | 1 | 1 | 1 | 0 | No variance. | No variance. | No variance. | No lit/managed services are being provided until electronics are purchased, fully integrated and launched. Only dark fiber at this time. | 15 | 15 | 0 | 1 | No variance. | No variance. | All subscribers are new at this point. | Service are Ethernet, which supports speeds up to 10 Gbps. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Ethernet services. Internet access. | FALSE | None. | Receiving AL permits from DOT. Commencing with AL construction. We expect to have 215 miles of fiber constructed by the end of the quarter. We expect to have 21 CAIs connected by the end of the quarter. We expect to have one (1) broadband wholesaler/last mile provider agreements in place by the end of the quarter. | Appalachian Valley Fiber Network | Continued slow process for AL permitting approval. | None. | TRUE
NT10BIX5570101 | 2012 | Q4 | Q4 - 2012 | Revised and resubmitted permits for AL to ALDOT. Began activation of key anchor tenants. Continued fiber placement, splicing and wrap-up work for Georgia sections. | 205 | 257 | 0 | 0 | 205 | 0 | 0 | 974 | No variance. | No variance. Exceeding goals from our original baseline. Includes 60 miles from PFN and 197 miles from Norfolk Southern IRU. | No variance. | No variance. | We estimated 206 miles in our baseline. No variance. | No variance. | No variance. | No variance. | 1 | 3 | 12 | Parker FiberNet. | AVFN has an agreement with Parker FiberNet to provide wholesale dark fiber services. Pricing will be set on a per-end-customer (CAI) basis. | Not applicable. | 0 | 0 | 1 | 0 | No variance. | No variance. | No variance. | No lit/managed services are being provided at this time. Only dark fiber at this time. | 21 | 20 | 1 | 1 | No variance. | No variance. | All subscribers are new at this point. | Services are Ethernet, which supports speeds up to 10 Gbps. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Ethernet service. Internet access. | FALSE | None. | Finalize all permits for AL. Begin construction of the AL route. Wrap up remaining construction in GA, including all fiber blowing and splicing. Seek agreements with additional third party service providers. Continue supporting anchor institution connections. Our goal is to have an additional 15 miles of fiber deployed next quarter, cumulatively totalling 220 miles. Our goal is to have an additional 6 CAIs connected next quarter, cumulatively totalling 27 CAIs. Our goal is to have 1 additional broadband wholesaler/last mile provider agreement next quarter, cumulatively totalling 2 providers. | Appalachian Valley Fiber Network | Continued slow process for AL permitting approval. | The project timeline could be at risk if we don't secure the required AL permits and begin construction this quarter. We are making good progress, but it remains a risk. | TRUE
NT10BIX5570101 | 2013 | Q1 | Q1 - 2013 | Received permits for Alabama sections from ALDOT. Continued activation of key anchor tenants. Continued fiber placement, splicing and wrap-up work for Georgia sections. Negotiated interconnect agreement with third-party service provider. | 208 | 257 | 0 | 0 | 208 | 0 | 0 | 988 | No variance. | No variance. Exceeding goals from our original baseline. Includes 60 miles from PFN and 197 miles from Norfolk Southern IRU. | No variance. | No variance. | We estimated 222 miles in our baseline. Delayed start to Alabama construction is the reason for the variance. | No variance. | No variance. | No variance. | 2 | 2 | 12 | Parker FiberNet, Cartersville FiberCom | AVFN is now providing transport services for Cartersville FiberCom, with whom it is also interconnecting with at a co-location facility. Pricing is negotiated between AVFN and FiberCom on a per-end-customer (CAI) basis. | Not applicable. | 0 | 0 | 2 | 0 | No variance. | No variance. | No variance | Dark fiber at this time. Not applicable. | 25 | 24 | 1 | 1 | No variance. | No variance. | No variance. | Services are Ethernet, which supports speeds up to 10 Gbps. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Ethernet service. Internet access. | FALSE | Not applicable. | Substantial completion of Alabama construction. Wrap up remaining construction in GA, including all fiber blowing and splicing. Seek agreements with additional third party service providers. Continue supporting anchor institution connections. Our goal is to have an additional 30 miles of fiber deployed next quarter, cumulatively totalling 235 miles. Our goal is to have an additional 6 CAIs connected next quarter, cumulatively totalling 31 CAIs. Our goal is to have 1 additional broadband wholesaler/last mile provider agreement next quarter, cumulatively totalling 3 providers. | Appalachian Valley Fiber Network | ALDOT permitting required submission of applications and plans numerous time. Delayed start to Alabama construction. | Must complete route modification for seven CAIs connected that were not on original target list. | TRUE
NT10BIX5570101 | 2013 | Q2 | Q2 - 2013 | Commenced construction of Alabama portions of the network (completed about 6 route-miles of conduit and fiber placement). Continued activation of key anchor tenants. Continued fiber placement, splicing and wrap-up work for Georgia sections. | 235 | 257 | 0 | 0 | 235 | 0 | 0 | 1116 | No variance. | No variance. Exceeding goals from our original baseline. Includes 60 miles from PFN and 197 miles from Norfolk Southern IRU. | No variance. | No variance. | We estimated 242 miles in our baseline. Delayed start to Alabama construction is the reason for the variance. | No variance. | No variance. | No variance. | 2 | 2 | 12 | Parker FiberNet, Cartersville FiberCom | AVFN is now providing transport services for Cartersville FiberCom, with whom it is also interconnecting with at a co-location facility. Pricing is negotiated between AVFN and FiberCom on a per-end-customer (CAI) basis. | Not applicable. | 0 | 0 | 2 | 1 | No variance. | No variance. | No variance. | Services are Ethernet, which supports speeds up to 10 Gbps. | 130 | 129 | 1 | 1 | No variance. Exceeds baseline. | No variance. Exceeds baseline. | No variance. Exceeds baseline. | Services are Ethernet, which supports speeds up to 10 Gbps. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Ethernet service. Internet access. | FALSE | Not applicable. | Completion of Alabama construction. Completion of fiber placement, splicing and wrap-up work for Georgia sections. AVFN estimates that the end of next quarter we will have 256 miles of fiber deployed, 150 CAIs connected, and 3 wholesale/last mile service providers contracted. | Appalachian Valley Fiber Network | Delayed permitting and start of construction in Alabama was an issue, but has been resolved now. | No challenges expected. | TRUE
NT10BIX5570101 | 2013 | Q3 | Q3 - 2013 | Our original baseline goal was to construct 182 miles of fiber and lease 60 miles of fiber for a total of 242 miles. Following approved modifications during our project, and with no budget increase, we were actually able to construct 254 miles and lease 257 miles for a total of 511 miles -- 111% more than our baseline goal. The network connects 24 communities across nine counties in two states; Georgia and Alabama. We have established interconnection agreements with several municipal network providers in these communities, allowing them to expand the reach of the services they provide. The network also provides redundancy and diversity through connections to Internet hubs in Atlanta and Chattanooga. Our original baseline goal was to connect 80 CAIs. As a result of the increased miles and extensive outreach efforts, we were able to connect 145 CAIs -- 81% above our baseline goal. Schools, libraries, government facilities and healthcare organizations have been able to migrate from T-1 and other legacy services to 50-400 Mbps Internet connections and 1-10 Gbps Ethernet-class services. The network also passed 23 business and industrial parks, where third-party retail service providers have used our open-access, nondiscriminatory network to connect 15 manufacturers. More than 40 healthcare facilities, many in rural areas that did not previously have connectivity, have also been connected to a virtual "med-net" that enables high-speed, secure transfer of patient records and other clinical and financial data. Through budget efficiencies and approved project modifications, we were also able to light our entire core and middle mile network with state-of-the-art optical equipment -- which was not contemplated in our original plan. The federal share expenditures in two categories, Project Inspection and Miscellaneous, net amounts were reduced in Q3 due credits and/or refunds received during this period. | 254 | 257 | 0 | 0 | 254 | 0 | 0 | 1206 | Our original baseline goal was 261 miles. We were unable to complete the remaining seven miles of aerial construction in Calhoun County, AL. This was due to swap-outs of utility poles that were planned by Southern Company along a transmission corridor in the national forest. | No variance. Exceeding goals from our original baseline. Includes 60 miles from PFN and 197 miles from Norfolk Southern IRU. | No variance. | No variance. | Our original baseline goal was 261 miles. We were unable to complete the remaining seven miles of aerial construction in Calhoun County, AL. This was due to swap-outs of utility poles that were planned by Southern Company along a transmission corridor in the national forest. | No variance. | No variance. | No variance. | 3 | 2 | 12 | Parker FiberNet, Cartersville FiberCom, Calhoun Telecommunications (Calnet) | AVFN is now providing transport services for Cartersville FiberCom and Calnet, with whom it is also interconnecting with at co-location facilities. Pricing is negotiated between AVFN and FiberCom/Calnet on a per-end-customer (CAI) basis. | Not applicable. | 0 | 0 | 3 | 1 | No variance. | No variance. | No variance. | Services are Ethernet, which supports speeds up to 10 Gbps. | 145 | 144 | 1 | 1 | No variance. | No variance. | No variance. | Services are Ethernet, which supports speeds up to 10 Gbps. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Ethernet service. Internet access. | FALSE | Not applicable. | Our project is now complete. We will work during the next quarter to complete close-out activities. | Appalachian Valley Fiber Network | We were unable to complete the remaining seven (7) miles of aerial construction in Calhoun County, AL. This was due to swap-outs of utility poles that were planned by Southern Company along a transmission corridor in the national forest. | Not applicable. Project was completed this quarter. | TRUE
NT10BIX5570102 | 2010 | Q4 | Q4 - 2010 | This project will integrate isolated community anchor networks to expand the broadband capabilities and geographic reach of the Arkansas Telehealth Oversight & Management (ATOM) Networkâ€”a group of community anchor institutions with limited bandwidth and equipment that offer healthcare, higher education, public safety, and research servicesâ€”and the Arkansas Research & Education Optical Network (AREON), the stateâ€™s only public-owned fiber optic network currently serving four-year universities. This project will permit high-speed delivery and transmission of the following broadband benefits at the 474 â€œintegrated networkâ€ sites. In Project Quarter 2 of this project, the following activities were undertaken or accomplished to meet the mission described above: * Two qualified contractors were selected through Requests for Proposals (RFPs) to respectively design the leased and fiber networks. The network designs are now in their earliest stages of development. * An engineering firm was selected via a Request for Qualifications (RFQ) to perform an Environmental Assessment (EA) of leased and fiber routes. The engineering firm began route and prefab site planning in parallel with the EA. * Indefeasible Rights of Use (IRU) fiber routes were selected through an RFP process and are being employed to make the most efficient use of existing resources to expand the fiber network. * A construction management firm was selected through an RFQ process to act as the general contr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | --- | --- | N/A | The Baseline Report "existing network miles leased" represented IRU miles. The Baseline Report assumed IRUs would have been in place by the end of the fourth quarter of 2010, but those negotiations are still on-going at this time. We anticipate completing IRU agreements in the the first reporting of 2011. | --- | N/A | N/A | --- | 0 | 0 | 0 | N/A | N/A | UAMS has one subrecipient that will operate a portion of the BTOP-funded network: the Arkansas Research and Education Optical Network. This portion includes the publicly owned fiber network connecting the state's four-year universities and two-year colleges to high speed fiber optic services, including 33 total sites. ARE-ON is a state-supported entity. The subrecipient's contact information appears below: Arkansas Research and Education Optical Network (ARE-ON) Michael D. Abbiatti, Executive Director 155 S. Razorback Road Fayetteville, AR 72101 479-575-3901 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The Baseline Report assumed 8 "total subscribers served" would be active during the fourth quarter of 2010 as made possible through IRUs that were assumed to be placed by the end of the fourth quarter. However, as previous sections indicated, the IRUs were not purchased during the fourth quarter of 2010. These subscribers will be served once the IRUs are purchased. | --- | Please see explanation above in "total subscribers served." The "subscribers receiving improved access" were assumed to benefit from IRUs; however, these connections were not in place during the fourth quarter of 2010. These subscribers will be served once the IRUs are purchased. | Please see explanation above in "total subscribers served." The "subscribers receiving improved access" were assumed to benefit from IRUs; however, these connections were not in place during the fourth quarter of 2010. These subscribers will be served once the IRUs are purchased. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The first quarter of 2011 is anticipated to include several significant steps toward project completion. Most notably, the Environmental Assessment (EA) will be completed and submitted to the National Telecommunications and Information Administration (NTIA) for review and comment by the federal reviewers. While this process holds some unknown factors on the timing and rigidity of the review, UAMS anticipates obtaining a â€œFinding of No Significant Impact" (FONSI), which will enable the project to move forward to its implementation and deployment phases. While UAMS has been preparing for such a finding, many of its systems are on hold until the FONSI is declared. Once the project is approved to proceed, the grants team (consisting of Project Director, managers, coordinators, technologists, and other UAMS directors) will publish Requests for Proposals (RFPs) for the projectâ€™s leased circuits and telemedicine equipment. These RFPs will be released as soon as available, possibly during the first quarter of 2011; however selection of vendors is scheduled for the second quarter of 2011. As discussed earlier, Indefeasible Rights of Use (IRUs) have been bid out in the previous quarter and many will be selected in the first quarter of 2011. We have also identified the possibility that more IRUs will be added in future quarters as providers complete additional fiber construction, an act that will allow UAMS to maximize available resources and employ additional vendors to further | University of Arkansas System | The shifting of our timing in negotiating the IRUs caused the biggest deviation from our initial baseline. This deviation is contributed to complexities resident in the contract approval process in the State of Arkansas. The University of Arkansas System must follow State Purchasing regulations requiring specific timelines, then issue and evaluate appropriate Requests for Proposals. Following contractor selection, the proposed contract must be approved by the University of Arkansas Board of Trustees, then receive approval from the Legislative Council. The organizations at the center of each step meet independently, spread over a prolonged series of months resulting in meetings scheduled after the closing date of Q1. These regulatory steps caused a slight change in timing that should have no material impact on our overall project, as we anticipate completing IRU agreements next quarter. The BTOP program has provided very good technical assistance, and the UAMS project is progressing at an appropriate speed as we await the review and approval of the Environmental Assessment. | As highlighted above, the projected progress and degree of completion are primarily dependent on receiving a FONSI for the EA, thus receiving clearance from NTIA to move forward with project implementation. At present, UAMS estimates the EA will be commented upon, revised as needed, and approved by the end of February, allowing another month within the first quarter of 2011 to begin project implementation activities. If the EA process requires more time than estimated, there is a great potential the planned project progress will be delayed accordingly into subsequent quarters. | TRUE
NT10BIX5570102 | 2011 | Q1 | Q1 - 2011 | This project will integrate isolated community anchor networks to expand the broadband capabilities and geographic reach of the Arkansas Telehealth Oversight & Management (ATOM) Network-a group of community anchor institutions with limited bandwidth and equipment that offer healthcare, higher education, public safety, and research services-and the Arkansas Research & Education Optical Network (ARE-ON), the state's only public-owned fiber optic network currently serving four-year universities. In first quarter of 2011 (or the third project quarter), the following activities were undertaken or accomplished to meet the mission described above: â€¢ Seven project employees were hired: (1) Project Director, (4) Program Managers and (2) Project Specialists for a cumulative total of (12) FTE. â€¢ Drafted Request for Proposals (RFPs) for interactive video equipment with consideration given for state and grant requirements. â€¢ Began RFP drafting process (data collection, equipment specifications) for IAV Core equipment, Public Safety, eICU, Home Health. â€¢ Developed Memorandum of Agreements (MOAs) for network facility leases and equipment. â€¢ Began research and quantification of network facility leases in anticipation of the RFP. â€¢ Conducted field reviews for biological and cultural issues relating to the environmental assessment (EA). â€¢ Actively prepared a revised EA draft, Cultural Resources Survey Report for the State Historic Preservation Office (SHPO), and a Biological St | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | --- | --- | N/A | The Baseline Report â€œexisting network miles leasedâ€ represented IRU miles. The Baseline report assumed IRUs would have been in place by the end of the fourth quarter of 2010, but those negotiations are still ongoing at this time. We anticipate completing IRU agreements in the second reporting quarter of 2011. | -- | N/A | N/A | --- | 0 | 0 | 0 | N/A | N/A | UAMS has one sub-recipient that will operate a portion of the BTOP-funded network: the Arkansas Research and Education Optical Network. This portion includes the publicly owned fiber network connecting the stateâ€™s four-year universities and two-year colleges to high speed fiber optic services, including 33 total sites. ARE-ON is a state-supported entity. The sub-recipientâ€™s contact information appears below: Arkansas Research and Education Optical Network (ARE-ON) Michael D. Abbiatti, Executive Director 155 S. Razorback Road Fayetteville, AR 72101 479-575-3901 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The Baseline Report assumed 8 "total subscribers served" would be active during the first quarter of 2011 as made possible through IRUs that were assumed to in place by the end of the fourth quarter of 2010. However, as previous sections indicated, the IRUs are not purchased to date. These subscribers will be served once the IRUs are purchased. | --- | Please see explanation above in "total subscribers served." The "subscribers receiving improved access" were assumed to benefit from IRUs; however, these agreements are not in place to date. These subscribers will be served once the IRUs are purchased. | Please see explanation above in "total subscribers served." The "subscribers receiving improved access" were assumed to benefit from IRUs; however, these agreements are not in place to date. These subscribers will be served once the IRUs are purchased. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The second quarter of 2011 is anticipated to include several significant steps toward project completion. Most notably, the final Environmental Assessment (EA) will be completed and submitted to the National Telecommunications and Information Administration (NTIA) for review by the federal reviewers. While this process holds some unknown factors on the timing and rigidity of the review, UAMS anticipates obtaining a â€œFinding of No Significant Impactâ€ (FONSI) in the second quarter of 2011, which will enable the project to move forward to its implementation and deployment phases. While UAMS has been preparing for such a finding, many of its plans are on hold until the FONSI is declared. In this quarter, we anticipate over $4 million in IRU purchases, which will be possible when the conflict protest on the IRU process is resolved Additionally, the UAMS BTOP team (consisting of Project Director, managers, coordinators, technologists, and other UAMS directors) will publish a Requests for Proposals (RFP) for the projectâ€™s telemedicine equipment in the second quarter of 2011. This RFP will be released as soon as it is finalized. The RFP will invite bids for 30 days, and equipment vendors will be selected and awarded shortly thereafter. Overall, once the project receives a FONSI, the project will begin to reach its momentum and increase deployment activities as future quarters unfold. | University of Arkansas System | Two primary factors are causing the most notable deviation from our Baseline Report in this quarter: 1) IRU Negotiation and 2) FONSI Attainment. Negotiating the IRUs has resulted in a deviation contributed to complexities resident in the contract approval process in the State of Arkansas. The University of Arkansas System must follow State Purchasing regulations requiring specific timelines, then issue and evaluate appropriate Requests for Proposals. Following contractor selection, the proposed contract must be approved by the University of Arkansas Board of Trustees, then receive approval from the Legislative Council. The organizations at the center of each step meet independently, spread over a prolonged series of months resulting in meetings scheduled after the closing date of this quarter. These regulatory steps caused a change in timing that should have no material impact on our overall project, as we anticipate completing IRU agreements next quarter. A conflict protest on the IRU process, as explained above, has further contributed to this deviation. The EA has also caused a challenge, since review of the draft EA resulted in a number of requests for revision from the NTIA, SHPO, and USFWS. The nature of these requests pointed toward the need for greater specificity in the routes that required construction and their impact on biological and cultural resources. Finalization of these routes and careful review of their impacts required this first quarter of 2011 to comple | As highlighted above, the projected progress and degree of completion are largely dependent on receiving a FONSI, thus receiving clearance from NTIA to move forward with project implementation. At present, UAMS estimates the final EA will be submitted and approved prior to the end of the second quarter of 2011. If the EA process requires more time than estimated, there is a great potential the planned project progress will be delayed accordingly into subsequent quarters. | TRUE
NT10BIX5570102 | 2011 | Q2 | Q2 - 2011 | The University of Arkansas System project will integrate isolated community anchor networks to expand the broadband capabilities and geographic reach of the Arkansas Telehealth Oversight & Management (ATOM) Network-a group of community anchor institutions with limited bandwidth and equipment that offer healthcare, higher education, public safety, and research services-and the Arkansas Research & Education Optical Network (ARE-ON), the state's only public-owned fiber optic network currently serving four-year universities. This project will permit high-speed delivery and transmission of the following broadband benefits at the 474 "integrated network" sites. In Year 1 Quarter 4, the following activities were undertaken or accomplished to meet the mission described above: Overall Project â€¢Completed the Environmental Assessment (EA) and received a Finding of No Significant Impact (FONSI), which enables the project to begin its implementation phase in Year 2 Quarter 1. ATOM Network â€¢ Completed Phases I and II Network Design documents enabling the ATOM Network to begin project implementation. â€¢ Obtained concurrence letters from local universities approving placement of fiber huts on college campuses. â€¢ Released three Request for Proposals (RFP) to the University of Arkansas for Medical Sciences (UAMS) Procurement Office: 1) Interactive Video Equipment for Community Anchor institutions (CAIs) RFP, 2) Home Care Association Equipment RFP, 3), and Infrastructure Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | --- | --- | N/A | --- | --- | N/A | N/A | --- | 0 | 0 | 0 | N/A | N/A | UAMS has one sub-recipient that will operate a portion of the BTOP-funded network: the Arkansas Research and Education Optical Network. This portion includes the publicly owned fiber network connecting the stateâ€™s four-year universities and two-year colleges to high speed fiber optic services, including 33 total sites. ARE-ON is a state-supported entity. The sub-recipientâ€™s contact information appears below: Arkansas Research and Education Optical Network (ARE-ON) Michael D. Abbiatti, Executive Director 155 S. Razorback Road Fayetteville, AR 72101 479-575-3901 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | --- | --- | --- | --- | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Year 2 Quarter 1 is anticipated to include several significant steps toward project completion. Several University of Arkansas for Medical Sciences (UAMS) systems were on hold until declaration of the FONSI. Now that the National Telecommunications and Information Administration (NTIA) has formally issued a FONSI, the University of Arkansas System may proceed in moving forward to its implementation phase. The UAMS BTOP team (consisting of Project Director, Program Managers, coordinators, technologists and other UAMS directors) expects to have completed the process for finalizing contracts on interactive video (IAV) equipment, infrastructure equipment and Home Healthcare equipment in this quarter. This process includes opening and awarding bids followed by contract negotiation. This will enable a large portion of CAIs to receive telemedicine equipment that will prepare their sites for participation in the ATOM Network. Other significant steps toward equipment procurement will be undertaken such as posting of Requests for Proposals (RFP); receiving and opening bids for eICU equipment, leased facilities, and routers / aggregators; and awarding bid for public safety equipment. Further, the UAMS BTOP team anticipates placing the order for public access PCs. Improvements will be made in the tracking database allowing for ad hoc reporting. Outreach efforts include identification of a branding that will be easily recognized by the citizens of the state and participating communi | University of Arkansas System | The University of Arkansas System did face several challenges or issues in the final quarter of Year 1. The delay of the approval of the Environmental Assessment and subsequent issuance of FONSI did not occur until the final weeks of this past quarter, which resulted in delays in the purchase of home healthcare and public safety equipment and project-wide variances in the Baseline Report. The BTOP program did offer assistance in correcting these and other variations by offering the University of Arkansas System to submit a revised Baseline Report, which is referenced within this progress report. Another challenge, the aforementioned conflict protest progressed to legal action, which further impeded progress in IRU negotiations, although progress has been and is being made in these negotiations. | After issuance of the FONSI, the project has already begun to make significant progress. While every eventuality cannot be fully anticipated, the UAMS BTOP team will attempt to identify challenges or issues that may be encountered in Year 2 Quarter 1. Although timeline projections have been conservative, it is possible equipment delivery may delay anticipated deployment at ATOM Network CAI sites. Once equipment vendor contact negotiations are finalized, the UAMS BTOP team will utilize vendor delivery timeline commitments to refine the timeline as needed. Negotiations will continue regarding IRUs and hut construction. While progress is being monitored and managed, there are some unpredictable elements involved when negotiating terms with outside parties. A substantial portion of IRU funds are expected to be expended in Year 2 Quarter 1; however, the conflict protest that progressed to legal action could impede this progress. In addition, an easement is not available at one of the ARE-ON hut sites, which is currently being considered for land acquisition, long-term lease, or relocation should negotiations fail. Any significant issues involving IRUs and hut construction could cause shifts in timelines shared by UAMS and ARE-ON, both of which are aware of project dependencies and how to manage them accordingly to keep the project on track for timely completion. | TRUE
NT10BIX5570102 | 2011 | Q3 | Q3 - 2011 | The University of Arkansas System project will integrate isolated community anchor networks to expand the broadband capabilities and geographic reach of the Arkansas Telehealth Oversight & Management (ATOM) Network-a group of community anchor institutions with limited bandwidth and equipment that offer healthcare, higher education, public safety, and research services-and the Arkansas Research & Education Optical Network (ARE-ON), the state's only public-owned fiber optic network currently serving four-year universities. This project will permit high-speed delivery and transmission of the following broadband benefits at the 474 "integrated network" sites. In Year 2 Quarter 1, the following activities were undertaken or accomplished to meet the mission described above: Overall Project o The project gained substantial momentum in the implementation phase, which included the post of Requests for Proposals (RFPs), purchase of initial hardware, and acceleration of outreach efforts with Community Anchor Institutions (CAIs). Arkansas Telehealth Network (Arkansas Telehealth Oversight Management-ATOM) o Finalized contracts on interactive video (IAV) equipment. This process includes opening/awarding bids followed by contract negotiation. This enables a large portion of CAIs to receive telemedicine equipment that will prepare their sites for participation in the ATN Network. o Undertook significant steps toward equipment procurement, which included the preparation of Req | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | --- | --- | N/A | --- | The Baseline assumed this measure should include fiber laid in addition to conduit. Based on the revised criteria incorporating conduit miles, we show 10 miles of new fiber versus the 9 miles in the Baseline. | N/A | N/A | --- The Baseline assumed this measure should include fiber laid in addition to conduit. Based on the revised criteria incorporating conduit miles, we show 10 miles of new fiber versus the 9 miles in the Baselinee should include fiber laid in addition to c | 0 | 0 | 0 | N/A | N/A | UAMS has one sub-recipient that will operate a portion of the BTOP-funded network: the Arkansas Research and Education Optical Network. This portion includes the publicly owned fiber network connecting the stateâ€™s four-year universities and two-year colleges to high speed fiber optic services, including 33 total sites. ARE-ON is a state-supported entity. The sub-recipientâ€™s contact information appears below: Arkansas Research and Education Optical Network (ARE-ON) Michael D. Abbiatti, Executive Director 155 S. Razorback Road Fayetteville, AR 72101 479-575-3901 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | --- | --- | --- | --- | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Year 2 Quarter 2 is anticipated to include several significant steps toward project completion. The UAMS BTOP team (consisting of project director, program managers, project specialists, technologists and other UAMS directors) expects to complete deployment of 325 telehealth interactive video units, 284 public access PCs, and 81 Home Healthcare interactive video units during next quarter. The infrastructure management equipment contract facilitating 24/7 video network support is also expected to be finalized. Vendor(s) selection and contract negotiation for leased facilities broadband connectivity will be undertaken during the next quarter, which will impact 305 community anchor institutions (CAIs). Program managers will continue outreach activities to include visits to sites and ongoing coordination between vendors and CAIs for the installation of clinical and educational interactive video units and public access PCs. A dynamic re-design of the project web site is expected to improve stakeholder navigation and allow greater capabilities for the BTOP team to disseminate project progress quickly. ARE-ON, the program's sub-recipient, reports these project accomplishments are planned for completion during the next quarter: Fiber construction completion at: Pine Bluff, Little Rock West, and Morrilton Hut completion at Pine Bluff, Morrilton, Malvern, and Hope Start fiber construction at: Malvern, West Memphis, Hope, and Forrest City Start Hut construction at: West Memphis, For | University of Arkansas System | The unfortunate timing of the clinical and educational equipment interactive video invoicing and the ASAP scheduled down time precluded expenditure of funds for invoices during Year 2 Quarter 1. The legal action involving one of the unsuccessful IRU vendors and the University is still pending. We do not anticipate that the legal action will adversely affect any of the executed IRUs. Resolution of this conflict protest is anticipated by Year 2 Quarter 3. | Leased facilities agreements and negotiations are likely to spread into the next quarter. There are additional concerns about availability and receptivity of the installation sites due to CAI staff vacations during the November and December holiday season. Weather is unpredictable and icy road conditions during the last month of the next reporting quarter could create some issues in remote and mountainous areas of the deployment region. Although time-line projections have been conservative, it is possible equipment delivery may delay anticipated deployment at Arkansas Telehealth Network CAI sites. Now that equipment vendor contract negotiations are finalized, the UAMS BTOP team will utilize vendor delivery time-line commitments and site readiness to refine the time-line as needed. A portion of IRU funds are expected to be expended in Year 2 Quarter 2, however, it is projected that the final milestone payment for all IRUs will not be reached until Year 3 Quarter 2. The legal action involving one of the unsuccessful IRU vendors and the University is still pending but is expected to be resolved by Year 2 Quarter 3. We do not anticipate that the legal action will adversely affect any of the executed IRUs. Lastly, any significant issues involving IRUs and hut construction could cause shifts in time-lines shared by UAMS and ARE-ON, both of which are aware of project dependencies and how to manage them accordingly to keep the project on track for timely completion. | TRUE
NT10BIX5570102 | 2011 | Q4 | Q4 - 2011 | The University of Arkansas System project will integrate isolated community anchor networks to expand the broadband capabilities and geographic reach of the Arkansas Telehealth Network managed by Arkansas Telehealth Oversight & Management (ATOM) Network-a group of community anchor institutions with limited bandwidth and equipment that offer healthcare, higher education, public safety, and research services-and the Arkansas Research & Education Optical Network (ARE-ON), the state's only public-owned fiber optic network currently serving four-year universities. This project will permit high-speed delivery and transmission of the following broadband benefits at the 467 "integrated network" sites. (Note: The grant application indicated 474 sites, however, during our activities we identified seven sites that closed.) In Year 2 Quarter 2, the following activities were undertaken or accomplished to meet the mission described above: Overall Project o The project continued to gain substantial momentum in the implementation phase, which included finalizing contracts, bid awards, procurement for clinical assessment tools, procurement and delivery of wireless telehealth devices, installation of 261 interactive video (IAV) units and 161 Public Access PCs. The team's outreach efforts included launching of a re-designed web site to enhance efforts with Community Anchor Institutions (CAI). Arkansas Telehealth Network (Arkansas Telehealth Oversight Management-ATOM) â€¢ Awarded bid and finalized procurement for clinical assessment tools/peripherals. This process includes opening/awarding bids followed by procurement. Subsequently, an order was placed for over 500 peripherals for attachment to clinical IAV carts that will allow clinicians at CAI the ability to view and/or capture images that will aid in timely, accurate diagnoses. â€¢ Static images were placed on 290 public access PCs prior to deployment to CAI that identifies them as being a part of the BTOP funded Arkansas e-Link project and provides useful web links to citizens who may not be familiar with internet navigation. â€¢ Procurement of eICU sole source video items/furniture was completed and delivered to CAI. â€¢ Procurement and delivery of 68 wireless telehealth devices to the HomeCare Association was accomplished enabling them to distribute these devices to 13 home health agencies within the state serving Arkansas' home-bound population. â€¢ Awarded bids for leased facilities, connectivity devices/managed services for hubs, and MVP/Public Safety/MEMS impacting 305 community anchor institutions (CAI). Contracts for these awards are expected to be finalized next quarter. â€¢ Program managers completed visits to all corporate CAI sites, meeting executive level administrators, Information Technology (IT) and education staff at hospitals, community health centers, mental health clinics and libraries to retrieve signed Memorandums of Agreement (MOAs). By the end of the reporting quarter, 99 of 103 MOAs were processed. In addition to retrieval of MOAs, Program Managers conducted a baseline assessment of the CAIâ€™s knowledge, use, needs, perception/acceptance and vision of Telehealth that will be useful as the Arkansas e-Link team develops sustainability strategies. â€¢ Program managers disseminated site readiness assessments to IT contacts at each CAI in order to complete the final step in the deployment planning process, resulting in installation of 261 IAV units and 161 Public Access PCs. â€¢ A dynamic re-design of the project web site was launched that introduces the â€œArkansas e-Linkâ€ brand. This new web site (www.arkansaselink.com) is expected to improve stakeholder navigation and allow greater capabilities for the Arkansas e-Link team to quickly disseminate the BTOP project progress. Arkansas Research and Education Optical Network (ARE-ON) ARE-ON, the program's sub-recipient, reports these project accomplishments: IRUs: Contracted final route (Jonesboro to Pocahontas) bringing the total fiber miles contracted for to 690 miles. Fiber engineering is completed for 13 of the 17 routes. Construction is 99% complete for two routes, 66% complete for three routes and 33% complete for two routes. Construction: Lateral fiber - complete for Little Rock West project; complete for Pine Bluff and Morrilton projects except for final splicing; construction of conduit in progress in Little Rock (Center), Hope, Forrest City and Malvern. Huts: Hut installed in Morrilton; hut dirt work was completed for West Memphis, Forrest City, Harrison, Mountain Home, Melbourne, Newport, Malvern, Hope, Pine Bluff and Fayetteville; hut manufacturing was initiated for Pine Bluff, Hope, Harrison, Malvern and Forrest City The sum of these activities comprise the initial steps of the grant's implementation phase, allowing the University of Arkansas System to gather and disseminate the information and procure the resources necessary to effectively implement the proposed project. At the end of the three-year grant period, all 467 sites will function on an â€œintegrated networkâ€ fusing ATOM and ARE-ON sites, benefiting from the following BTOP deliverables: Substantial bandwidth upgrades Significant network expansion Interactive video equipment additions Public computer additions Fully available after grant funding ends, these deliverables will provide the tools needed to enable participation in activities that once were only limitedly available in Arkansas. | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | --- | --- | N/A | --- | The Baseline assumed this measure should include fiber laid in addition to conduit. Based on the revised criteria incorporating conduit miles, we show a cumulative 24 miles of new fiber this quarter alone exceeding the cumulative 18 miles in the Baseline resulting in a variance of 6 additional miles. | N/A | N/A | --- | 0 | 0 | 0 | N/A | N/A | UAMS has one sub-recipient that will operate a portion of the BTOP-funded network: the Arkansas Research and Education Optical Network. This portion includes the publicly owned fiber network connecting the stateâ€™s four-year universities and two-year colleges to high speed fiber optic services, including 33 total sites. ARE-ON is a state-supported entity. The sub-recipientâ€™s contact information appears below: Arkansas Research and Education Optical Network (ARE-ON) Michael D. Abbiatti, Executive Director 155 S. Razorback Road Fayetteville, AR 72101 479-575-3901 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | --- | --- | --- | --- | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Year 2 Quarter 3 is anticipated to include several significant steps toward project completion. The UAMS BTOP team (consisting of project director, program managers, project specialists, technologists and other UAMS directors) expects to complete deployment of approximately 123 public access PCs and 64 IAV units during next quarter. We also anticipate installation of managed services for hubs that will facilitate 24/7 video network support. Our grant application’s mission is to integrate and expand two existing networks. In the process of rolling out this grant, we have deployed equipment to sites that have existing connectivity (which has improved service at these sites). Full integration does not occur until later in the project. As a result, at this point in time we are projecting that by the end of the next quarter we will have a total project-to-date of 364 CAIs connected. Contracts are expected to be finalized for eICU, Public Safety, Hub connectivity/Managed services and CAIs Leased Facilities Broadband Connectivity. Once the Hub Connectivity Leased Facilities contracts are finalized, the project's momentum will pick up substantially. Program Managers will begin coordination of circuit installs or upgrades with CAI. We anticipate delivery and field installation of approximately 500 clinical assessment tools/peripherals that will allow clinicians at CAI the ability to view and/or capture images that will aid in timely, accurate diagnoses. Implementation of the infrastructure equipment, allowing for multi-point conference calls, managed directories, technical support, overall usage management and reporting is expected. eICU equipment software and associated video software contracts will be finalized, purchased and installed. Finally, individual video management devices will be attached to IAV equipment to facilitate mobility, cart management, management of multiple video units within a site at CAI. Program managers will continue outreach activities to include visits to sites and ongoing coordination between vendors and CAIs for the installation of public access PCs, IAV units, clinical assessment tools/peripherals, individual management devices and broadband leased facilities and fiber backbone connectivity. ARE-ON, the program's sub-recipient, providing fiber backbone for the network, reports these project accomplishments for completion during the next quarter: Completion of fiber construction at Pine Bluff, Morrilton, Hope, Forrest City, West Memphis, and Malvern Completion of hut at Pine Bluff, Malvern, Hope, Harrison, and Forrest City Estimated number of miles planned for deployment next quarter: Construction Miles: 33.41 Miles IRU Contracted Miles: 690.14 Miles Total Miles: 723.55 Miles ARE-ON does not plan to be a broadband wholesaler or provider for last-mile providers. This project is planned for middle mile deployment for integrating and expanding two existing networks (AREON and ATN/ATOM). | University of Arkansas System | The unfortunate timing of the infrastructure management equipment invoicing precluded expenditure of funds for invoices during Year 2 Quarter 2. The legal action involving one of the unsuccessful IRU vendors and the University is still pending. We do not anticipate that the legal action will adversely affect any of the executed IRUs. Resolution of this conflict protest is anticipated by Year 2 Quarter 3. | There are concerns about icy road conditions during the next reporting quarter which could create some issues in remote and mountainous areas of the deployment region. Although time-line projections have been conservative, it is possible equipment delivery and leased facility installations may delay anticipated deployment at Arkansas Telehealth Network CAI sites. A portion of IRU funds are expected to be expended in Year 2 Quarter 3, however, it is projected that the final milestone payment for all IRUs will not be reached until Year 3 Quarter 2. The legal action involving one of the unsuccessful IRU vendors and the University is still pending but is expected to be resolved by the next reporting quarter. We do not anticipate that the legal action will adversely affect any of the executed IRUs. Lastly, any significant issues involving IRUs and hut construction could cause shifts in time-lines shared by UAMS and ARE-ON, both of which are aware of project dependencies and how to manage them accordingly to keep the project on track for timely completion. | TRUE
NT10BIX5570102 | 2012 | Q1 | Q1 - 2012 | The University of Arkansas System project will integrate isolated community anchor networks to expand broadband capabilities & geographic reach of the Arkansas Telehealth Network (ATN) managed by Arkansas Telehealth Oversight & Management (ATOM) Network-a group of community anchor institutions with limited bandwidth & equipment that offer healthcare, higher education, public safety, & research services-and the Arkansas Research & Education Optical Network (ARE-ON), the state's only public-owned fiber optic network currently serving four-year universities. This project will permit high-speed delivery & transmission of the following broadband benefits at the 456 "integrated network" sites. (NOTE: The grant application indicated 474 sites, however, during our activities in Q4 2011 we identified seven (7) planned sites that closed. During our activities in Q1 2012, eleven (11) additional sites have closed or plan to be reassigned bringing the cumulative total of site closures to eighteen (18) and a total of planned sites to 456.) We plan to submit an AAR to address this matter. In Quarter 1 2012, the following activities were undertaken or accomplished to meet the mission described above: Overall Project The project reached significant milestones in the implementation phase which included finalizing contracts for leased broadband facilities. This accomplishment allowed the project to engage in aggressive coordination for deployment of leased broadband facilities and hub connectivity to healthcare Community Anchor Institutions (CAIs). At this stage, ARE-ON's (sub-recipient) lateral construction is still in progress. Contractors placed 9.73 miles of new conduit (overall total of 26.51 miles) and 27.78 cable miles of new fiber (overall total of 37.00 cable miles) in nine cities. One route in Little Rock having 4.3 cable miles of fiber placed is complete and carrying traffic. One IRU provider has delivered on both of its fiber routes. University of Arkansas for Medical Sciences (UAMS) reports these project accomplishments with regard to the telehealth network: â€¢ Received one colocation agreement allowing Arkansas e-Link to install & maintain networking, communications, computer & other equipment. â€¢ Finalized contracts for leased broadband facilities, eICU equipment, & connectivity devices/managed services for network hubs. â€¢ Completed procurement for 150 devices to aid in network management & interactive video (IAV) mobility at the CAI. â€¢ Began coordination for deployment of leased broadband facilities & hub connectivity to CAIs. â€¢ Continued installation of video infrastructure equipment that will provide 24/7 video network management. â€¢ Received 500+ Clinical Assessment Tools for attachment onto clinical IAV carts. â€¢ Program Managers met with staff at 64 CAIs to conduct site assessment interviews & discuss deployment of leased broadband facilities. â€¢ Program Managers coordinated installation of 63 interactive video units & 80 public access PCs to CAIs. â€¢ Outreach efforts included: - A web site enhancement of stories highlighting CAI IAV vision & usage. - Addition of a Google Earth map to the project web site with information about equipment & bandwidth each CAI is receiving. - Presentations on project overview & progress to four organizations. â€¢ Q4 2011 reported closure of seven (7) sites. Eleven (11) additional sites were identified in Q1 2012 as being closed or plan to be reassigned. To date there is a cumulative total of eighteen (18) closed sites (or sites that plan to be reassigned resulting in a total of 456 planned sites). ARE-ON (sub-recipient) reports these project accomplishments: â€¢ Continuation of fiber laterals construction to the college campuses. â€¢ Cable placement is approximately 100% complete pending final testing & acceptance in 6 cities. One route in Little Rock is completed & carrying traffic. â€¢ Work is in progress at Malvern, Harrison, & East Camden. â€¢ Three (3) new huts were placed bringing the total to four (4) leaving 12 additional huts to be placed. â€¢ Procurement of all optical equipment & routers. The sum of these activities comprise the continuing steps of the grant's implementation phase, allowing the University of Arkansas System to gather & disseminate information & procure the resources necessary to effectively implement the proposed project. At the end of the three-year grant period, all 456 planned sites will function on an "integrated network" fusing ATN & ARE-ON sites, benefiting from the following BTOP deliverables: Substantial bandwidth upgrades Significant network expansion Interactive video equipment additions Public computer additions | 4 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | The revised Baseline assumed there would be no new network miles deployed this quarter, however ARE-ON completed construction on 9.73 miles of conduit (overall total of 26.51 miles) and 27.78 cable miles of new fiber (overall total of 37.00 cable miles) in nine cities. One route of 4.29 cable miles in Little Rock was completed & is carrying traffic resulting in a positive variance of 4 miles. | The revised Baseline projected 633 new network miles leased (inclusive of 100, 20, 10 and 1.5 mbps circuits) would be completed. However, the state requirement of posting of RFPs for 30 days coupled with the length of time required for contract negotiation delayed this item resulting in a negative variance of 633 miles. By the end of Q2 2012, the number of new network miles leased should be in alignment with the revised Baseline. | N/A | --- | The revised Baseline assumed this measure should include fiber laid in addition to conduit. Based on the revised criteria incorporating conduit miles, we show a cumulative 28 miles of new fiber this quarter alone exceeding the cumulative 27 miles in the revised Baseline resulting in a variance of one additional mile. It is noted that a typo occurred on the Q4 2011 PPR. The total number of miles of new fiber indicated "34" and should have read "24". | N/A | N/A | --- | 0 | 0 | 0 | N/A | N/A | UAMS has one sub-recipient that will operate a portion of the BTOP-funded network: the Arkansas Research and Education Optical Network. This portion includes the publicly owned fiber network connecting the stateâ€™s four-year universities and two-year colleges to high speed fiber optic services, including 33 total sites. ARE-ON is a state-supported entity. The sub-recipientâ€™s contact information appears below: Arkansas Research and Education Optical Network (ARE-ON) Michael D. Abbiatti, Executive Director 155 S. Razorback Road Fayetteville, AR 72101 479-575-3901 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | The revised Baseline assumed that 43 subscribers would be served, however delay dependencies relative to issuance of FONSI, state requirements of posting of RFPs for 30 days, length of time required for vendor assessment, contract negotiations, etc., precluded our ability to reach this metric. By the end of Q2 2012 we anticipate having six (6) hubs interconnected and attached to ARE-ON's fiber backbone. Due to the delay of three (3) of our telehealth hubs we will temporarily locate these aggregation points in CAIs bringing the total number of hubs to nine (9). In addition, the awarded telecommunications vendors will provision all leased broadband healthcare facilities by Q2 2012. | The revised Baseline assumed that 43 subscribers would be served, however delay dependencies relative to issuance of FONSI, state requirements of posting of RFPs for 30 days, length of time required for vendor assessment, contract negotiations, etc., precluded our ability to reach this metric. By the end of Q2 2012 we anticipate having six (6) hubs interconnected and attached to ARE-ON's fiber backbone. Due to the delay of three (3) of our telehealth hubs we will temporarily locate these aggregation points in CAIs bringing the total number of hubs to nine (9). In addition, the awarded telecommunications vendors will provision all leased broadband healthcare facilities by Q2 2012. | The revised Baseline correctly assumed that 0 subscribers would received improved access. By the end of Q2 2012 we anticipate having six (6) hubs interconnected and attached to ARE-ON's fiber backbone. Due to the delay of three (3) of our telehealth hubs we will temporarily locate these aggregation points in CAIs bringing the total number of hubs to nine (9). In addition, the awarded telecommunications vendors will provision all leased broadband healthcare facilities by Q2 2012. | --- | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Quarter 2 2012 is anticipated to include significant steps toward project completion. The UAMS BTOP team (consisting of project director, program managers, project specialists, technologists and other UAMS directors) expects to: â€¢ Complete deployment (in place and operational) of telemedicine network connectivity. â€¢ Complete coordination, installation & testing of leased broadband facilities for CAIs. â€¢ Installation will be completed for: -Video infrastructure management system -150 devices to aid in interactive video management and interactive video (IAV) mobility at the CAI; - connectivity devices/managed services for hubs and leased broadband facilities; and, - e-ICU (electronic intensive care unit) equipment and associated software. â€¢ Deploy remaining 28 public access PCs. â€¢ Finalize Public Safety contract piloting remote medicine via wireless in two ambulances. â€¢ Troubleshoot technical questions from CAIs about connecting the e-Link network into their LAN. Develop processes for: - Internal notification (to CAIs) for when leased circuit facilities are tested and working. - Coordination of dialing plan changes for CAIs. â€¢ Program Managers will continue to visit sites and be available to field questions from CAIs about deployment process. ARE-ON, the program's sub-recipient, providing fiber backbone for the network, reports these project accomplishments for completion during the next quarter: â€¢ Completion of fiber construction â€¢ Placement of nine (9) telecommunication huts â€¢ Completion of optical networking and router/switch networking equipment procurement. â€¢ Deployment of the equipment will begin with staging (racking, stacking, powering, fibering, software installation, and general testing) at a central location. Installation will then occur at the appropriate hut or campus site as those sites become available and as IRU fibers serving the site are delivered. Estimated number of miles planned for deployment next quarter: Construction miles: 9.65 Miles IRU Contracted Miles: 690.14 Total Miles: 733.2 Miles ARE-ON does not plan to be a broadband wholesaler or provider for last-mile providers. This project is planned for middle mile deployment for integrating and expanding two existing networks (ARE-ON and ATN/ATOM). | University of Arkansas System | UAMS experienced challenges due to delays in receipt, installation and testing of video infrastructure management equipment as well as contract negotiations for eICU and Mobile Virtual Physician (MVP). There were issues with address changes and closings of CAIs. Also, additional (unexpected) reporting requirements re-directed resources from project management to project reporting. Our sub-recipient, ARE-ON faced two major challenges during this reporting quarter. Weather delays, especially due to heavy rain, has slowed some construction activities, including cable placement and hut sets. Contractors were able to absorb much of the delay by shifting activities around the state. Also, problems with manufacturing of the pre-fabricated huts were discovered requiring the manufacturer to do in-the-field remediation and some changes in procedures and documentation in the manufacturing process. The delays have not appreciably affected the overall schedule. It was believed the legal action involving one of the unsuccessful IRU vendors and the University would be resolved by the end of this reporting quarter. However, the litigation is still pending. On January 18, 2012 a hearing was held in the Miller County Circuit Court with respect to a Motion to Dismiss filed by Defendants. Among other grounds for dismissal, Defendants moved that the Complaint be dismissed due to improper venue under Ark. R. Civ. P. 12(b)(3). As a result of the hearing, Judge Griffin transferred the case to th | Challenges anticipated could include possible CAIs that move or close, particularly during deployment of leased broadband facilities. These shifts influence several changes to deployment plans. Due to the sheer number of CAIs receiving leased broadband facilities in Q2 2012, any delays by vendors could preclude our projections of CAIs connected via broadband. Our sub-recipient, ARE-ON, anticipates that weather-related delays could occur through the Spring. While these delays have been factored in to estimates, as the construction projects reach completion in various cities, contractors will have less opportunity to shift personnel around and keep them busy as delays occur in an area. | TRUE
NT10BIX5570102 | 2012 | Q2 | Q2 - 2012 | The University of Arkansas (U of A) System project will integrate isolated community anchor networks to expand broadband capabilities & geographic reach of the Arkansas Telehealth Network (ATN) managed by Arkansas Telehealth Oversight & Management (ATOM) Network-a group of community anchor institutions with limited bandwidth & equipment that offer healthcare, higher education, public safety, & research services-and the Arkansas Research & Education Optical Network (ARE-ON), the state's only public-owned fiber optic network currently serving four-year universities. This project will permit high-speed delivery & transmission at 456 "integrated network" sites. (NOTE: The grant application indicated 474 sites, however, during Q4 2011 we identified seven planned sites that closed. Eleven additional sites were identified in Q1 2012 that have closed or plan to be reassigned bringing the cumulative total of site closures to 18. An Award Action Request (AAR) was submitted 5/25/2012 to the Broadband Infrastructure program office to provide address changes for Community Anchor Institutions (CAIs) that have moved and corrections to addresses previously submitted. In Quarter 2 2012, the following activities were undertaken or accomplished to meet the mission described above: Overall Project The project achieved 71% substantial completion against the benchmark of 67%. Leased broadband facilities were deployed connecting 244 long-term operating leased circuits/facilities at the Telemedicine CAIs and hubs. Installation of 1.98 miles of new conduit & 9.95 miles of new fiber was accomplished. The completion status of fiber lateral construction is 97.17% conduit & 98.28% fiber. Seven new fiber huts were placed. University of Arkansas for Medical Sciences (UAMS) reports these project accomplishments with regard to the telehealth network: â€¢ Achieved 71% substantial completion against the benchmark of 67% â€¢ Completed deployment of BTOP Telemedicine network connectivity at end-user sites. â€¢ Installed aggregation for the hubs. â€¢ Deployed leased broadband facilities to Telemedicine CAIs resulting in connection of 244 long-term operating leased circuits/facilities. â€¢ Completed approximately 90% of the video infrastructure systems implementation. â€¢ Installed 338 (63%) clinical assessment tools (peripherals) that attach onto clinical interactive video (IAV) carts. â€¢ Installed 299 (63%) IAV management devices that allow for mobility at the CAIs. â€¢ Installed 28 public access PCs at CAIs. â€¢ Delivered electronic intensive care unit equipment & associated software to Baptist Health.These devices will be assigned by Baptist Health â€¢ Hosted Federal Program Officer site visit. â€¢ Started coordination efforts with ASR Analytics, LLC for project's social and economic impact study. Outreach efforts: â€¢ Presented project overview to Hospital Preparedness Program. â€¢ Presented project update to Office of Health Information Technology (OHIT). â€¢ Program Managers met with staff at 29 Telemedicine CAIs. â€¢ Presented project update & portfolios of estimated benefit from BTOP funds in their respective districts to State Senators/Representatives. ARE-ON (sub-recipient) reports these project accomplishments: â€¢ Initial deployment of optical ROADMs is complete in three sites, with preliminary cold staging & inventory of remaining optical equipment completed. â€¢ Procurement of all optical equipment & routers. â€¢ Four IRU providers met 43 of the total 62 milestones, with completion of 5 of the 17 overall fiber routes & approximately 484 of the total 715.89 miles of fiber completed. Note: Previous reports indicated 690.14 miles total of contracted fiber for the four IRUs. However, the route between two cities was re-engineered by our telecommunications vendor which lengthened the distance by 25.49 miles for a total of 715.89 miles. â€¢ Installation of core network routers is complete at two sites. â€¢ Fiber lateral construction is near completion (97.17% conduit & 98.28% fiber). â€¢ Seven (7) new fiber huts were placed (completing 11 of 16 huts). At the end of the three-year grant period, all 456 planned sites will function on an "integrated network" fusing ATN & ARE-ON sites, benefiting from the following BTOP deliverables: Substantial bandwidth upgrades Significant network expansion Interactive video equipment Public computer additions | 46 | 484 | 0 | 0 | 46 | 0 | 0 | 9 | The PIP revised Baseline (February 2012) assumed there would be a cumulative total of 40 new network miles deployed this quarter. However, we exceeded the projection resulting in a positive variance of 6 miles. | The PIP revised Baseline (February 2012) projected 456 new network miles leased thru Q2 2012. This is a positive variance of 28 miles leased. In addition, there was a total of 17,857 network miles of leased facilities (inclusive of 100,10 and 1.5 mbps circuits) for Telemedicine CAIs. | N/A | --- | The PIP revised Baseline (February 2012) assumed 40 miles of fiber would be installed. We show a cumulative 46 miles of new fiber at the end of this reporting quarter resulting in a positive variance of 6 miles. This calculation is based on the guidance given by NTIA that this is the length of conduit containing fiber. This number (46) includes approximately 7 miles of slack loops. Slack loops include slack fiber stored in handholes or manholes to accommodate fiber damage repairs. | N/A | N/A | The PIP revised Baseline (February 2012) projected 0 new and/or upgraded interconnection points would be completed. However, five (5) new interconnection points (new fiber huts) were placed and four (4) existing interconnection points were upgraded resulting in a +9 variance. | 0 | 0 | 0 | N/A | N/A | UAMS has one sub-recipient that will operate a portion of the BTOP-funded network: the Arkansas Research and Education Optical Network. This portion includes the publicly owned fiber network connecting the stateâ€™s four-year universities and two-year colleges to high speed fiber optic services, including 33 total sites. ARE-ON is a state-supported entity. The sub-recipientâ€™s contact information appears below: Arkansas Research and Education Optical Network (ARE-ON) Michael D. Abbiatti, Executive Director 155 S. Razorback Road Fayetteville, AR 72101 479-575-3901 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 244 | 0 | 244 | 0 | The revised Baseline assumed that 87 (cumulative) subscribers of Telemedicine CAIs would be served. We were able to accelerate our implementation which resulted in an excess of calculated variance (+157). | N/A | The revised Baseline assumed that 87 subscribers of Telemedicine CAIs would receive improved access. We were able to accelerate our implementation which resulted in an excess of calculated variance (+157). | The (actual) speed tiers and number of subscribers for each include the following: 100 mbpsâ€“5 subscribers; 10 mbpsâ€“72 subscribers; 1.5 mbpsâ€“167 subscribers. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | UAMS plans deployment of the majority (if not all) interactive video equipment to remaining 141 Telemedicine CAIs. Program managers will facilitate training to Emergency Directors and/or Clinic Managers on Telemedicine peripherals at 210 sites. By the end of Q3 2012, we anticipate that broadband at all Telemedicine CAIs will be connected and operational. ARE-ON, the program's sub-recipient, reports these project accomplishments are planned for completion during the next quarter: Fiber construction and installation of prefabricated telecommunication huts are expected to be 100% complete. Installation of optical and core network router equipment is expected to be at 50% completion during the next reporting quarter. ARE-ON's IRU providers have projected that 95% of the IRU milestones will be met, which represents approximately 80% of the overall completed fiber route miles. ARE-ON's engineers will initiate the major portion of equipment installation tasks, including staging and burn-in, racking & stacking, provisioning, and turn-up. We optimistically believe that we can complete about 50% of the equipment installation work by the end of the next reporting quarter. Estimated number of miles planned for deployment next quarter: Construction Miles: 0.94 Miles of Conduit, 2.03 Miles of Fiber IRU Contracted Miles: 696.78 of 715.89 Miles projected by providers for delivery Q3 2012 Total Miles: 743.83 Miles (47.05 Lateral Fiber Miles + 696.78 IRU Fiber Miles) ARE-ON does not plan to be a broadband wholesaler or provider for last mile providers. This project is planned for middle mile deployment for integrating and expanding two existing networks (ARE-ON and ATN/ATOM). | University of Arkansas System | The project achieved 71% substantial completion against the benchmark of 67%. To meet (exceed) this goal we focused our resources on Telemedicine telecommunications and equipment deployment. To meet substantial completion requirements, it was necessary for our team to intensely manage telecommunication vendors in the circuit installations at the Telemedicine CAIs. It was challenging to manage such a large scope against the amount of time given to accomplish this task. This quarter also included planning and hosting the Federal Program Officer (FPO) visit. Other challenges included delays in installation and testing of video infrastructure management equipment which we project will be operational by the end of the next reporting quarter. Contract negotiations continued for Mobile Virtual Physician (MVP) during Q2 2012 and are expected to be completed by the end of Q3 2012. The biggest challenges for our sub-recipient, ARE-ON, have been related to placement of the prefabricated telecommunication huts. Site preparation for hut placement at one site was delayed by approximately two months due to excessive underground water that eventually was traced to a broken water main at a nearby property. Other delays were due to hut manufacturing problems that continued to require in-the-field remediation. It is speculated that these errors are due to the manufacturer's workload in fulfilling a very large volume of orders from other customers for cellular network expansions and other fib | Challenges anticipated could include possible CAIs that move or close prior to or during deployment of leased broadband facilities. These shifts influence several changes to deployment plans. Any unforeseen delays by vendors could preclude our projections of CAIs connected via broadband. Our sub-recipient, ARE-ON, anticipates challenges in equipment deployment in the next quarter. Final phases will begin, including production of punch lists for each site and fiber route, remediation of any problems, completion of red-line drawings, certification of fiber by Arkansas OneCall, final splicing and testing of lateral to long-haul fiber, and production of as-built prints. Concurrently, ARE-ON's engineers will begin racking & stacking equipment, doing burn-in testing, configuring equipment, provisioning networks, and conducting a final inventory. The enormous amount of travel necessary to do both of these tasks may present challenges. We are working to negate this by doing more pre-staging of equipment and burn-in at the Fayetteville offices of ARE-ON. | TRUE
NT10BIX5570102 | 2012 | Q3 | Q3 - 2012 | The University of Arkansas (U of A) System project will integrate isolated community anchor networks to expand broadband capabilities & geographic reach of the Arkansas Telehealth Network (ATN) managed by Arkansas Telehealth Oversight & Management (ATOM) Network-a group of community anchor institutions with limited bandwidth & equipment that offer healthcare, higher education, public safety, & research services-and the Arkansas Research & Education Optical Network (ARE-ON), the state's only public-owned fiber optic network currently serving four-year universities. This project will permit high-speed delivery & transmission at 454 "integrated network" sites. (NOTE: The grant application indicated 474 sites, however, during Q4 2011 we identified seven (7) planned sites that closed. Eleven (11) additional sites were identified in Q1 2012 and two (2) additional sites were identified in Q3 2012 that have closed bringing the cumulative total of site closures to 20. An Award Action Request (AAR) was submitted 10/22/2012 to the Broadband Infrastructure program office to provide address changes for Community Anchor Institutions (CAIs) that have moved and corrections to addresses previously submitted. In Quarter 3 2012, the following activities were undertaken or accomplished to meet the mission described above: Overall Project July 11, 2012, a verbal temporary stop-work order was issued by the National Telecommunications and Information Administration (NTIA) and the National Oceanic and Atmospheric Administrative (NOAA). This was followed up with a written temporary stop-work order dated August 3, 2012. Activities were restricted to duties associated with the response of the Corrective Action Plan (CAP), security of grant-funded property to protect it against loss, damage, or theft, and management and administration of the grant. The UAS ceased disallowed activities in compliance with this work stoppage. In a letter dated September 10, 2012, the National Telecommunications and Information Administration (NTIA) and the National Oceanic and Atmospheric Administrative (NOAA) issued an amendment to lift the temporary stop-work order and also issued a partial temporary stop-work order - prohibiting project implementation and construction activities conducted by ARE-ON. University of Arkansas for Medical Sciences (UAMS) reports these project accomplishments with regard to the telehealth network: â€¢ Duties associated with the response to the Corrective Action Plan (CAP) and subsequent requests for additional information â€¢ Management and administration of the grant. â€¢ Began Phase II deployment of IAV equipment to 158 Telemedicine CAIs & migration to the network. â€¢ Continuance of MVP (Mobile Virtual Physician) contract for completion. â€¢ Quarterly report preparation ARE-ON, the program's sub-recipient, reports these project accomplishments: â€¢ Construction and installation was halted on July 11, 2012 with the exception of: - any work required for human safety such as covering or filling holes or ditches - security (changing locks and periodic site visits) - asset protection (ensuring HVAC and generators were working properly for sites in which equipment was already installed). â€¢ IRU providers continued to deliver on project milestones, completing at least 565 of 716 total miles (79.0%) by the end of the reporting quarter. This was allowed as validated by the FPO in a verbal conversation on August 27, 2012, and also in writing via an FPO e-mail dated September 18, 2012. | 46 | 484 | 0 | 0 | 46 | 0 | 0 | 9 | --- | --- | N/A | --- | --- | N/A | N/A | --- | 0 | 0 | 0 | N/A | N/A | UAMS has one sub-recipient that will operate a portion of the BTOP-funded network: the Arkansas Research and Education Optical Network. This portion includes the publicly owned fiber network connecting the stateâ€™s four-year universities and two-year colleges to high speed fiber optic services, including 33 total sites. ARE-ON is a state-supported entity. The sub-recipientâ€™s contact information appears below: Arkansas Research and Education Optical Network (ARE-ON) Michael D. Abbiatti, Executive Director 155 S. Razorback Road Fayetteville, AR 72101 479-575-3901 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 244 | 0 | 244 | 0 | --- | N/A | --- | --- | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The projections were calculated using the Revised PIP of October 2012. It is projected that 152 Telemedicine CAIs will be connected during the next quarter. Overall, the cumulative CAI project is: 33 Higher Education CAIs (to be connected by end of project) 13 Telemedicine CAIs (provided equipment only) 408 Telemedicine CAIs (provided equipment and connectivity) 20 Telemedicine CAIs that have closed during the grant period ----- 474 CAIs for the grant total ARE-ON, the program's sub-recipient, reports these project accomplishments are planned for completion during the next quarter: Previous projections were to complete fiber lateral construction and place the final huts during this past reporting quarter, but the temporary suspension at the beginning of the quarter has resulted in significant delay in all construction. Depending on when clearance to resume construction is given, ARE-ON's contractor and subcontractors will require time to ramp up activities while workers and supervisors are re-assigned to this project or new workers are hired. The prefab hut manufacturer will also have to re-insert fabrication of the remaining huts into its production schedule. The uncertainty of the schedule makes it difficult to estimate project accomplishments for the next quarter. Construction miles: Fiber lateral construction should be approximately 99% complete (46.75 of 47.05 miles). IRU contracted miles: 715.89 miles projected by providers for delivery Q4 2012 - 100% complete Total Miles: 762.94 miles (47.05 lateral fiber miles + 715.89 IRU fiber miles). Hut placement: Two additional (13 of 16 total) huts will be placed ARE-ON engineers plan to hot stage all equipment during the quarter with anticipated preliminary deployment of equipment to begin in the first quarter of calendar year 2013. ARE-ON does not plan to be a broadband wholesaler or provider for last mile providers. This project is planned for middle mile deployment for integrating and expanding two existing networks (ARE-ON and ATN/ATOM). | University of Arkansas System | Due to the temporary suspension, there have been numerous challenges to re-engaging the project and managing it to a successful completion. The project is now being managed as aggressively as possible with plans for acceleration in critical steps. The installation/testing of video infrastructure management equipment and deployment of interactive video units was delayed. In addition, contract negotiations for Mobile Virtual Physician (MVP) were ceased during Q3 2012. Our sub-recipient, ARE-ON, had halted its construction activities. The work stoppage resulted in subcontractors' work crews being diverted to other projects or laid off. As the suspension is lifted, ramping up requires re-engagement and reassignment of the work crews and replacing supervisors. Also, work will extend into the winter months where weather-related delays could possibly occur. The hut manufacturer will need to adjust its production schedule to accommodate the project's huts. | Challenges anticipated could include possible CAIs that move or close prior to or during deployment of leased broadband facilities. These shifts influence several changes to deployment plans. Any unforeseen delays by vendors could preclude our projections of CAIs connected via broadband. The stop-work order has delayed the telemedicine deployment approximately 2 months. Our sub-recipient, ARE-ON, reports the greatest challenge to the schedule is the delay resulting from the temporary suspension and the amount of time needed by the contractors to revamp their worker force, equipment, and supervisors to resume full construction. In addition, the suspension has pushed the schedule into the winter months during which we can anticipate weather delays and days when the ground is too wet to work. Since most of the construction is complete, it is less likely that contractors can simply move crews to subprojects in other parts of the state since there are fewer sites under construction. Finally, it is anticipated that some re-work will have to be done with site preparations due to deterioration of grounds around foundations from rain washout, etc. | TRUE
NT10BIX5570102 | 2012 | Q4 | Q4 - 2012 | The University of Arkansas System (UAS) project will integrate isolated community anchor networks to expand broadband capabilities and geographic reach of the Arkansas Telehealth Network (ATN) managed by Arkansas Telehealth Oversight & Management (ATOM) Network - a group of community anchor institutions (CAIs) with limited bandwidth & equipment that offers healthcare, higher education, public safety, & research services, and the Arkansas Research & Education Optical Network (ARE-ON), the state's only public-owned fiber optic network currently serving four-year universities. This project will permit high-speed delivery & transmission at 454 "integrated network" sites. (NOTE: The grant application indicated 474 sites, however, during Q4 2011 we identified seven (7) planned sites that closed. Eleven (11) additional sites were identified in Q1 2012 and two (2) additional sites were identified in Q3 2012 that have closed bringing the cumulative total of site closures to 20. In Quarter 4 2012, the following activities were undertaken or accomplished to meet the mission described above: Overall Project Installation and connections to CAIs were completed as planned. Also, FCC rural-funded leased circuit/facilities were enriched with BTOP funded telemedicine equipment and participation in the Arkansas e-Link network. Sub-recipient ARE-ON's construction and installation work was stopped on July 11, 2012, and engineering/construction efforts resumed after the ARE-ON suspension was lifted November 14, 2012. Actual fiber optic cable construction did not resume due to lack of work crews that were relocated to other jobs due to the suspension. University of Arkansas (UAS) reports these project accomplishments with regard to the telehealth network: â€¢ Completed installation of interactive video units (IAVs), Remote Executive Office devices (a network management tool), and clinical assessment tools at the medical and healthcare CAIs. â€¢ Managed installation, connection, and testing of circuits at the medical and healthcare CAIs. â€¢ Pursued resolution to outstanding installation issues at a limited number of CAIs. â€¢ Completed approximately 99% of the video infrastructure systems implementation. â€¢ Outreach activities included: - project overview to the UAMS Rural Health Fellows Roundtable - project update to the Advanced Communications and IT Joint Committee of the Arkansas Legislature - media events for regional outreach and public relations (television and newspapers) - meetings with staff at 25 CAIs by Program Managers â€¢ Signed the Public Safety project contract and began meetings with vendors to plan project launch. â€¢ Received approval from National Telecommunications and Information Administration (NTIA) for ARE-ONâ€™s second AAR route modification request. â€¢ Provided required documentation to NTIA that was needed to lift all suspensions related to the Corrective Action Plan (CAP). ARE-ON, the program's sub-recipient, reports these project accomplishments: â€¢ One Higher Education CAI, Southern Arkansas University at Magnolia, is now connected to the network and operational. â€¢ The totals being reported are the same as that of the previous quarter: 32.30 of approximately 33.24 miles of conduit placed, 46.36 of 47.05 miles of fiber placed. â€¢ Despite delays, IRU fiber providers completed the delivery of all 62 project milestones, completing 100% of the 716 total miles of fiber optic cable. Note: Previous reports indicated 690.14 miles total of contracted fiber for the four IRUs. However, the route between two cities was re-engineered by our telecommunications vendor which lengthened the distance by 25.49 miles for a total of 715.89 miles. â€¢ The overall project stands at 97.2% of the conduit and 98.3% of the fiber planned for this project completed. â€¢ Two (2) new fiber huts were placed in December (completing 13 of 16 huts). â€¢ Work to complete the punch lists on the first eleven huts was resumed. | 46 | 716 | 0 | 0 | 46 | 0 | 0 | 9 | --- | --- | N/A | --- | --- | N/A | N/A | The PIP revised Baseline (February 2012 and October 2012) projected 0 new and/or upgraded interconnection points would be completed. However, as reported Q2 2012, five (5) new interconnection points (new fiber huts) were placed and three (3) existing interconnection points were upgraded. Another interconnection point was added this reporting quarter bringing the cumulative total to 9 resulting in a +9 variance. | 0 | 0 | 0 | N/A | N/A | UAMS has one sub-recipient that will operate a portion of the BTOP-funded network: the Arkansas Research and Education Optical Network. This portion includes the publicly owned fiber network connecting the stateâ€™s four-year universities and two-year colleges to high speed fiber optic services, including 33 total sites. ARE-ON is a state-supported entity. The sub-recipientâ€™s contact information appears below: Arkansas Research and Education Optical Network (ARE-ON) Michael D. Abbiatti, Executive Director 155 S. Razorback Road Fayetteville, AR 72101 479-575-3901 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 374 | 0 | 374 | 0 | The revised Baseline assumed that 182 subscribers of Telemedicine and Higher Ed CAIs would receive improved access. We were able to accelerate our implementation which resulted in an excess of calculated variance (+192). It is noted that 244 Telemedicine & 1 Higher-Ed subscribers are BTOP-funded. The remaining 129 subscribers' circuits are FCC-funded (with access made possible by use of BTOP-funded telemedicine equipment). | --- | The revised Baseline assumed that 182 subscribers of Telemedicine and Higher Ed CAIs would receive improved access. We were able to accelerate our implementation which resulted in an excess of calculated variance (+192). | The (actual) speed tiers and number of subscribers for each include the following: 1Gbps - 1 subscriber; 100Mbps-5 subscribers; 10Mbps-77 subscribers; 1.5Mbps-291 subscribers | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The projections were calculated using the Revised PIP of October 2012. UAS Telehealth plans to resolve any outstanding installation issues at CAIs, continue education of community leaders and outreach to CAIs. Also, we will continue to finalize equipment acquisition/installation. Further, we plan to implement scheduling/reporting systems with CAIs as well as utilization reporting and scheduling of multi-conferences. We will continue to work toward completing development of operations for sustainability and working with CAIs to develop their own telemedicine applications. Until agreement is reached on approved funding of leased facilities, we can estimate no additional connections of CAIs - this includes the next quarter. If/when funding is approved, we will begin the process and complete a few additional CAIs. ARE-ON, the program's sub-recipient, reports these project accomplishments are planned for completion during the next quarter: Completion of fiber testing and remediation for all currently constructed fiber. However, final construction of fiber and placement of huts for the final three hut sites (Beebe, Fayetteville, and North Little Rock) are not anticipated until Q2 2013. Optical equipment hot staging will be completed, and deployment of that equipment will begin during the quarter. 100Mb leased circuits for three community colleges will be completed and activated by the end of the quarter. Backbone router deployment will continue, but will not be completed by the end of the quarter. Another 1.48 miles of fiber is projected for completion. ARE-ON does not plan to be a broadband wholesaler or provider for last mile providers. This project is planned for middle mile deployment for integrating and expanding two existing networks (ARE-ON and ATN/ATOM). Therefore, there will be 0 broadband wholesaler/last mile provider agreements. In summary: - 1.48 miles = Estimated number of miles planned for deployment next quarter. - 0 = Estimated number of additional CAIs planned to be connected by the end of the next quarter. - 0 = Estimated number of broadband wholesaler/last mile provider agreements planned through the end of next quarter. | University of Arkansas System | A small number of CAIs were identified that needed a variety of additional efforts toward closing resolution. There was some reduced productivity due to holidays and inclement weather. Once the work suspension was lifted, ARE-ON's primary challenge was to ramp up its engineering and construction activities. The four month suspension period resulted in all contractor and sub-contractor crews and supervisors being reassigned to other projects, some in other states. Fiber optic construction and testing crews could not be deployed to active status by the end of the quarter, but work will resume in January 2013. Manufacturing of huts had been suspended, and the manufacturer was able to complete two that were partially complete at the point of the suspension in July. Engineering on the remaining huts has resumed, and a manufacturing schedule has been established for the remaining three huts. Some work to repair deterioration at incomplete hut sites had to take place as a result of the suspension. | UAS Telehealth projects the following challenges: getting buy-in from CAIs that are new to telemedicine and assisting them with development of their own applications while finalizing the development of operations for sustainability. Our sub-recipient, ARE-ON, reports they will resume bringing huts online, install equipment, and begin bringing community colleges online. This will require substantial fine tuning of each hut's infrastructure. Weather-related delays are anticipated throughout the winter months. The engineering staff will also have to begin coordination and training for the networking staff at the community colleges to prepare them for the installation of their new connections. We are effectively six months behind schedule due to the work suspension, and although we have been verbally granted a two-month extension to the project, compressing the time lost into the time remaining to complete the project on time will be the greatest overall challenge. | TRUE
NT10BIX5570102 | 2013 | Q1 | Q1 - 2013 | The University of Arkansas System (UAS) project will integrate isolated community anchor networks to expand broadband capabilities and geographic reach of the Arkansas Telehealth Network (ATN) managed by Arkansas Telehealth Oversight & Management (ATOM) Network - a group of community anchor institutions (CAIs) with limited bandwidth & equipment that offers healthcare, higher education, public safety, & research services, and the Arkansas Research & Education Optical Network (ARE-ON), the state's only public-owned fiber optic network currently serving four-year universities. This project will permit high-speed delivery & transmission at 454 "integrated network" sites. (NOTE: The grant application indicated 474 sites, however, during Q4 2011 we identified seven (7) planned sites that closed. Eleven (11) additional sites were identified in Q1 2012 and two (2) additional sites were identified in Q3 2012 that have closed bringing the cumulative total of site closures to 20.) In Quarter 1 2013, the following activities were undertaken or accomplished to meet the mission described above: Overall Project Subsequent to the installation of leased circuits, interactive video units and associated devices, there was a significant focus on outreach to the CAIs during Q1 2013. In addition, Dr. Curtis Lowery, the UAS Principal Investigator, received the prestigious honor of an invitation by NTIA to serve on a panel at the Brookings Institute to highlight the Arkansas project. Sub-recipient ARE-ON completed fiber lateral construction on two projects (East Camden and Malvern) and started the final two projects (Beebe and North Little Rock). By the end of Q1 2013, approximately 33.25 of 33.29 miles of conduit and 46.71 of 47.28 miles of fiber were placed. NTIA gave guidance for budget modification and was ruled allowable. A re-budget resulting from the fiber backbone implementation did not exceed 10% variance and there was no change in scope of work. University of Arkansas (UAS) reports these project accomplishments with regard to the telehealth network: â€¢ Progress was made in finalizing outstanding installation issues at remaining five (5) CAIs. â€¢ Completed the video infrastructure system implementation. â€¢ Completed approximately 80% implementation of MVP/Public Safety project. â€¢ Outreach activities included: - project overview to five (5) hospital CAIs that included members of the Arkansas Legislature; - project update to the Advanced House Communications and IT Committee of the Arkansas Legislature; - overview and tour of the University of Arkansas for Medical Sciences (UAMS) Center for Distance Health to an Arkansas legislative group; - media events for regional outreach and public relations (television and newspapers); - meetings with approximately 225 staff at 23 CAIs by Program Managers; - UAS BTOP Principal Investigator served on a panel at Brookings Institute to highlight the Arkansas project. â€¢ Submitted three (3) Award Action Requests (AARs) to NTIA for approval which included address/name changes, CAI replacement (no construction), and route modification (required by the Arkansas Highway and Transportation Department). â€¢ Received approval from NTIA to proceed with up-front funding of leased facilities to complete 36 months. ARE-ON, the program's sub-recipient, reports these project accomplishments: â€¢ One new hut (Beebe) was placed; design was completed and manufacturing scheduled for the remaining two huts (North Little Rock and Fayetteville). â€¢ Engineering for upgrades (power, HVAC, generator) to an existing hut (Monticello) was completed. â€¢ Completed fiber lateral construction at East Camden and Malvern, with projects in Beebe and North Little Rock still in progress. â€¢ Significant progress was made to complete hut construction punch lists. â€¢ Work to complete the electrical wiring in the huts was begun in anticipation of equipment installation in Q2 2013. â€¢ Began rework of grounds at three (3) hut sites due to soggy soil conditions. â€¢ Installed equipment at CAI (Southern Arkansas University, Magnolia) and seven (7) UAS telehealth co-location hub sites. â€¢ Hot staging of all equipment is completed in preparation for installation of optical and router equipment at remaining sites (during Q2 2013). â€¢ Placed order for leased circuits for installation at three (3) community colleges; delivery is anticipated in Q2 2013. | 47 | 716 | 0 | 0 | 47 | 0 | 0 | 9 | It is estimated that there is only a fraction of a mile to reach completion. | --- | N/A | N/A | It is estimated that there is only a fraction of a mile to reach completion. | N/A | N/A | --- | 0 | 0 | 0 | N/A | N/A | UAMS has one sub-recipient that will operate a portion of the BTOP-funded network: the Arkansas Research and Education Optical Network. This portion includes the publicly owned fiber network connecting the stateâ€™s four-year universities and two-year colleges to high speed fiber optic services, including 33 total sites. ARE-ON is a state-supported entity. The sub-recipientâ€™s contact information appears below: Arkansas Research and Education Optical Network (ARE-ON) Michael D. Abbiatti, Executive Director 155 S. Razorback Road Fayetteville, AR 72101 479-575-3901 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 374 | 0 | 374 | 0 | The revised Baseline assumed that 228 subscribers of Telemedicine and Higher Ed CAIs would receive improved access. We were able to accelerate our implementation which resulted in an excess of calculated variance (+146). It is noted that 244 Telemedicine & 1 Higher-Ed subscribers are BTOP-funded. The remaining 129 subscribers' circuits are FCC-funded (with access made possible by use of BTOP-funded telemedicine equipment). | --- | The revised Baseline assumed that 228 subscribers of Telemedicine and Higher Ed CAIs would receive improved access. We were able to accelerate our implementation which resulted in an excess of calculated variance (+146). | The (actual) speed tiers and number of subscribers for each include the following: 1Gbps - 1 subscriber; 100Mbps-5 subscribers; 10Mbps-77 subscribers; 1.5Mbps-291 subscribers | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Co-location space and power is available at network fiber huts. | FALSE | N/A | These projections for Q2 2013 are calculated using the modified budget of March 2013. UAS Telehealth plans to: â€¢ Resolve the remaining installation issues (i.e., connecting existing non-BTOP funded equipment to the network) at three (3) CAIs â€¢ Continue outreach to CAIs. â€¢ Present seven (7) regional seminars targeting community/civic leaders, business leaders, educators, physicians and staff, hospital administrators and other healthcare providers. These seminars provide an overview of the BTOP project and its impact on health, education, research, public safety as well as economic impact for the region. â€¢ Complete implementation of scheduling/reporting systems with CAIs as well as utilization reporting and scheduling of multi- conferences. â€¢ Continue to work toward completing development of operations for sustainability and working with CAIs to develop their own telemedicine applications. â€¢ Subsequent to an agreement with NTIA on approved funding of leased facilities, we will finalize the contract extension. â€¢ We will deploy the remaining equipment intended for CAIs that have closed to other CAIs to enrich their network. ARE-ON, the program's sub-recipient, reports these project accomplishments are planned for completion during Q2 2013: â€¢ All fiber construction will be completed as the (estimated) last 0.56 miles of fiber is delivered. â€¢ The final two (2) of sixteen (16) fiber huts (North Little Rock and Fayetteville) are planned for completion. â€¢ Optical network and router equipment will be installed at all sites, and a majority of the fiber is expected to be lit. â€¢ 100Mb leased circuits for three (3) community colleges will be completed and activated. ARE-ON does not plan to be a broadband wholesaler or provider for last mile providers. This project is planned for middle mile deployment for integrating and expanding two existing networks (ARE-ON and ATN/ATOM). Therefore, there will be 0 broadband wholesaler/last mile provider agreements. In summary: - 0.56 miles = Estimated number of fiber miles planned for deployment next quarter. - 3 = Estimated number of Higher Ed CAIs planned to be connected by the end of the next quarter. - 0 = Estimated number of broadband wholesaler/last mile provider agreements planned through the end of next quarter. | University of Arkansas System | UAS has reduced the number of CAIs that require various additional efforts toward full installation of non-BTOP funded equipment to network. Work continues toward resolution. Our sub-recipient, ARE-ON reports that rainy weather during the winter months made completing hut sites difficult as crews had to wait for sites to drain and/or additional gravel was hauled in to counter soggy soil conditions. Each of the fourteen (14) hut sites were inspected. Punch lists were produced and worked to eliminate problems in manufacturing and faulty equipment. One hut site was impacted by a last minute city government decision to require a city franchise before rights-of-way could be used for fiber construction. | UAS Telehealth projects the following challenges: getting buy-in from CAIs that are new to telemedicine and assisting them with development of their own applications while finalizing the development of operations for sustainability; finalizing contract extensions with telecom providers for leased circuit facilities; and, completing the project with a staff reduction of 27%. Our sub-recipient, ARE-ON, reports that construction will wrap up during Q2 2013. There will be some challenges given a small engineering staff, a broad geographic territory, and a significant number of closing tasks. This includes detailed inspections and punch lists for huts and laterals along with equipment installation and turn-up. Every attempt will be made to leverage the available time provided by the extension. | TRUE
NT10BIX5570102 | 2013 | Q2 | Q2 - 2013 | The University of Arkansas System (UAS) project will integrate isolated community anchor networks to expand broadband capabilities and geographic reach of the Arkansas Telehealth Network (ATN) managed by Arkansas Telehealth Oversight & Management (ATOM) Network - a group of community anchor institutions (CAIs) with limited bandwidth & equipment that offers healthcare, higher education, public safety, & research services, and the Arkansas Research & Education Optical Network (ARE-ON), the state's only public-owned fiber optic network currently serving four-year universities. This project will permit high-speed delivery & transmission at 454 "integrated network" sites. NOTE: The grant application indicated 474 sites, however, we anticipate net closures of sites to be 20. In Quarter 2 2013, the following activities were undertaken or accomplished to meet the mission described above: Overall Project Outreach to CAIs and sustainability of this telehealth project continued to be the primary focus during Q2 2013. Seven (7) regional seminars were held targeting community/civic leaders, business leaders, educators, physicians and staff, hospital administrators and other healthcare providers. Construction of all conduit, fiber laterals and huts stands at 100% completed with the exception of working through final punch lists for the last two (2) hut sites (North Little Rock, Fayetteville). All IRU fiber (716 miles) has been delivered and tested, and of that fiber 584 miles has been lit, a portion of which is now in production. Optical equipment has been installed at 31 of 36 sites, and three (3) of the nine (9) Juniper backbone routers have been installed. 100Mbps MPLS circuits are operational at two (2) community colleges, and equipment for the UAMS e-Link network has been installed at all nine (9) hub sites and operational at six (6) sites. University of Arkansas (UAS) reports these project accomplishments with regard to the telehealth network: â€¢ Resolved installation issues at three (3) CAIs reducing outstanding issues to two (2) remaining sites. â€¢ Completed MVP/Public Safety project installation and assessment. â€¢ Outreach activities: Project overview presented at seven (7) regional seminars targeting community/civic leaders, business leaders, educators, physicians and staff, hospital administrators and other healthcare providers; Project Director presented, â€œBroadband in Rural Arkansasâ€, at 2013 Arkansas Rural Development Conference. â€¢ Continued media events for regional outreach and public relations (television and newspapers). Two (2) events included legislators joining via interactive video from the State Capitol and from CAI located in their district. â€¢ Continued to work toward completing development of operations for sustainability and working with CAIs to develop their own telemedicine applications. â€¢ Program managers met with approximately 447 staff at 90 community anchor institutions (CAIs). â€¢ Deployed remaining equipment intended for CAIs that have closed to other approved CAIs to enrich their network. â€¢ Piloted self-scheduling software and verified assigned video schedulers for each CAI. â€¢ Submitted an AAR to NTIA for approval of â€œno cost extensionâ€ to 9/30/2013. â€¢ Continued contract extension work with telecom companies. ARE-ON, the program's sub-recipient, reports these project accomplishments: â€¢ Placed final two (2) huts. â€¢ Completed approved fiber lateral build. â€¢ Completed hut punch lists for all but two huts. â€¢ Completed electrical wiring at huts. â€¢ Installed optical equipment at 31 of 36 sites. â€¢ Lit southern fiber path (Monticello to Hope) enabling it to carry production traffic. â€¢ Lit northern fiber path (Fayetteville to Jonesboro). â€¢ Installed two (2) community colleges (having leased circuits) enabling them to carry production traffic. â€¢ Began installation of new 10G e-Link waves. | 49 | 716 | 0 | 1488 | 49 | 0 | 0 | 23 | Upon review of numbers, it was found that the original (total) 47 miles omitted one of the routes from Malvern, which corrected to approximately 1.2 miles. It is emphasized that this was not a new route, but a factual inconsistency (the field in the calculation was "zero" when it should have been "1.2"). Hence, the correct number was 48.4 miles rather than 47.2 miles as originally estimated. Secondly, the projectâ€™s engineering firm reconciled field records collected during construction and counts for feet of fiber and conduit with units placed during construction. Reconciliation of these records resulted in the correction of +0.75 mile to the overall length. These circumstances resulted in a final route total of 49.32 miles resulting in a +2 mile variance. There were no route modifications resulting from these corrections. | --- | N/A | There was a factual inconsistency in previous PPRs. The total for this metric was (and is) 1,488. These fiber miles existed before BTOP and are being used as part of the network. | Upon review of numbers, it was found that the original (total) 47 miles omitted one of the routes from Malvern, which corrected to approximately 1.2 miles. It is emphasized that this was not a new route, but a factual inconsistency (the field in the calculation was "zero" when it should have been "1.2"). Hence, the correct number was 48.4 miles rather than 47.2 miles as originally estimated. Secondly, the projectâ€™s engineering firm reconciled field records collected during construction and counts for feet of fiber and conduit with units placed during construction. Reconciliation of these records resulted in the correction of +0.75 mile to the overall length. These circumstances resulted in a final route total of 49.32 miles resulting in a +2 mile variance. There were no route modifications resulting from these corrections. | N/A | N/A | --- | 0 | 0 | 0 | N/A | N/A | UAS has one sub-recipient that will operate a portion of the BTOP-funded network: the Arkansas Research and Education Optical Network. This portion includes the publicly owned fiber network connecting the state's four-year universities and two-year colleges to high speed fiber optic services, including 33 total sites. ARE-ON is a state-supported entity. The sub-recipient's contact information appears below: Arkansas Research and Education Optical Network (ARE-ON) David Merrifield, Executive Director 155 S. Razorback Road Fayetteville, AR 72101 479-575-5829 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 420 | 0 | 420 | 0 | The revised baseline assumed that 266 subscribers of Telemedicine and Higher Ed CAIs would receive improved access. We were able to accelerate our implementation which resulted in an excess of calculated variance (+154). It is noted that 244 Telemedicine and 3 Higher-Ed subscribers are BTOP-funded. 129 subscribers' circuits are FCC-funded (with access made possible by use of BTOP-funded telemedicine equipment). 44 sites are improved utilizing BTOP-funded equipment. | --- | The revised baseline assumed that 266 subscribers of Telemedicine and Higher Ed CAIs would receive improved access. We were able to accelerate our implementation which resulted in an excess of calculated variance (+154). | The (actual) speed tiers and number of subscribers for each include the following: 1Gbps-1 subscriber; 100Mbps-7 subscribers; 10Mbps-77 subscribers; 1.5Mbps-291 subscribers. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Co-location space and power is available at network fiber huts. | FALSE | N/A | These projections for Q3 2013 are calculated using the modified budget of March 2013. UAS Telehealth plans to: â€¢ Resolve outstanding installation issues at remaining two (2) CAIs. â€¢ Complete implementation of video-conference scheduling system for all CAIs. â€¢ Initiate interactive video utilization reporting to CAIs. â€¢ Finalize the contract extension with telecom providers. â€¢ Host interactive video town hall sessions with CAIs to encourage collaboration and utilization of telehealth resources. ARE-ON, the program's sub-recipient, reports these accomplishments are planned for completion during Q3 2013: â€¢ Complete backbone network, with all fiber routes lit and operational. â€¢ Provide network configuration workshop during which CAI technicians will directly configure their border routers and firewalls in preparation for the ARE-ON service. â€¢ Work with each community college to complete the final connection to the campus border router and cut over to the new service by the end of Q3 2013. ARE-ON does not plan to be a broadband wholesaler or provider for last mile providers. This project is planned for middle mile deployment for integrating and expanding two existing networks (ARE-ON and ATN/ATOM). Therefore, there will be 0 broadband wholesaler/last mile agreements. In summary: â€¢ 5 = Number of Telemedicine CAIs projected to be connected. â€¢ 29 = Number of Higher Ed CAIs projected to be connected. â€¢ 0 = Estimated number of broadband wholesaler/last mile provider agreements planned through the end of the next quarter. | University of Arkansas System | UAS is near completion on work at CAIs that require various additional efforts toward full installation of non-BTOP funded equipment to the network; and, finalizing leased circuit contract extensions pending budget approval from NTIA. Our sub-recipient, ARE-ON hired additional contractors to reduce the impact of the work stoppage ordered last year. However, it continued to be challenging to re-gain the momentum necessary for timely completion of project goals for Q2 2013. | UAS Telehealth projects the following challenges: CAIs adapting operations for telemedicine; implementing operations for sustainability; finalizing contract extensions with telecom providers for leased circuit facilities; and, completing the project with a staff reduction of 27%. The most significant challenge for our sub-recipient, ARE-ON is coordinating time with community college IT staff to get their network connected and migrated to the new service. Plans are to use a "workshop" approach that brings community college networking staff together into one facility to collectively train them to configure their border router and firewall. It is unknown how well this workshop will be attended, thereby creating necessity to travel to several community colleges to do the configuration for them. | TRUE
NT10BIX5570102 | 2013 | Q3 | Q3 - 2013 | The University of Arkansas System (UAS) project integrated two isolated existing networks (the Arkansas Telehealth Network (ATN) and the Arkansas Research and Education Optical Network (ARE-ON) to expand broadband capabilities and geographic reach for healthcare, higher education, public safety, & research. Arkansas e-Link was the name chosen to encompass the integration of both networks. This permitted broadband delivery and/or equipment at 458 "integrated network" community anchor institutions. Nationally, Arkansas ranks 46th in percentage of households with broadband access. At 15.6%, Arkansas has the 8th highest poverty rate in the United States. Nine of 13 major Arkansas cities have a poverty rate above the state average, demonstrating poverty in both urban and rural regions. By virtually every indicator, including economic growth, education, and health, Arkansas has one of the nationâ€™s most vulnerable populations. BTOP funding provided community services at 458 locations in all 75 Arkansas counties including broadband circuits, increased bandwidth and/or new equipment. This provides increased access to real-time clinical consultations with remote specialists, virtual research collaboration and distance & continuing education. A transport medium was provided for hospital disaster preparedness, trauma, new cardiac services, e-ICU, high risk OB, Arkansas SAVES (stroke program), and healthcare services in correctional institutions. Arkansasâ€™s publicly-supported community college students may now enroll in distance education courses at the stateâ€™s four-year universities. Fiber-grade Internet connections at public college or university campuses enable students to take online courses and join in research studies with fellow students and teachers across the state and world. In Quarter 3 2013, the following activities were accomplished: Outreach to CAIs and sustainability continued to be the project's primary focus. An overview and update was presented to the Public Health, Welfare and Labor Committee of the Arkansas Legislature in conjunction with the Federal Program Officer (FPO) visit. Broadband contract extensions with telecom providers were finalized. All conduit, fiber laterals and huts are completed. The remaining optical equipment and Juniper backbone routers are installed and in production. 100Mbps MPLS circuits are operational and in production at one 2-Year College (bringing the total to 3). Equipment for the redundant route between University of Arkansas for Medical Sciences (UAMS) and the University of Arkansas at Little Rock (UALR) was installed at 3 hub sites (bringing the total to 9 telemedicine hubs statewide). University of Arkansas (UAS) reports these project accomplishments with regard to the telehealth network: â€¢ Resolved installation issues at the last two CAIs. â€¢ Completed implementation of video-conference scheduling system. â€¢ Coordinated and hosted the FPO for the BTOP Best Practices Site Visit that included a project overview and status update, a project management review, CAI testimonials, tours of key AREON network facilities and selected CAIs, and discussion of grant close-out procedures. â€¢ Finalized contract extension with telecom providers. â€¢ Outreach activities: Provided testimony, BTOP overview and update to the Public Health, Welfare and Labor Committee of the Arkansas Legislature in conjunction with the site visit, allowing our FPO to testify. â€¢ Program managers met with approximately 444 staff at 37 community anchor institutions (CAIs). â€¢ Continued work toward completing development of operations for sustainability and working with CAIs to develop their own telemedicine applications. ARE-ON, the program's sub-recipient, reports these project accomplishments: â€¢ Placed final two huts into full production. â€¢ Completed all lateral fiber and hut construction. â€¢ Completed all optical network equipment installation and tuning. â€¢ Completed all backbone routers installation and turn-up. â€¢ All fiber routes now carrying production traffic. â€¢ Installed leased circuits at the remaining 2-year community college (bringing the total to 3). â€¢ Links to all community college networks are lit and backbone infrastructure in place. â€¢ Began final cut-over of fiber-connected community college LANs to ARE-ON network links. | 49 | 716 | 0 | 1488 | 49 | 0 | 0 | 23 | As reported Q2 2013, upon review of numbers, a factual inconsistency was found. The original (total) 47.2 miles was changed to 48.4 miles. In addition, the projectâ€™s engineering firm reconciled field records collected during construction and counts for feet of fiber and conduit with units placed during construction. Reconciliation of these records resulted in the correction of +0.75 mile to the overall length. Combined, these circumstances resulted in a final route total of 49.32 miles leaving a +2 mile variance. There were no route modifications resulting from the corrections. | --- | N/A | --- | Please see explanation above in "New network miles deployed". | N/A | N/A | --- | 0 | 0 | 0 | N/A | N/A | UAS has one sub-recipient that will operate a portion of the BTOP-funded network: the Arkansas Research and Education Optical Network. This portion includes the publicly owned fiber network connecting the state's four-year universities and two-year colleges to high speed fiber optic services, including 32 total sites. ARE-ON is a state-supported entity. The sub-recipient's contact information appears below: Arkansas Research and Education Optical Network (ARE-ON) David Merrifield, Executive Director 155 S. Razorback Road Fayetteville, AR 72101 479-575-5829 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 458 | 0 | 458 | 5 | The revised baseline assumed that 266 subscribers of Telemedicine and Higher Ed CAIs would receive improved access. We were able to accelerate our implementation which resulted in an excess of calculated variance (+192). Subscribers receiving improved access: 249 Telemedicine 133 Telemedicine* (FCC-funded) 32 Higher-Education 44 CAIs improved utilizing BTOP-funded equipment** - 35 Medical & Healthcare Providers - 8 Libraries - 1 Public Safety *Sites received BTOP-funded equipment; connected to network via FCC Pilot Program-funded broadband. **Sites received BTOP-funded equipment; connected through their parent organization's BTOP-funded broadband OR no connectivity funded. | --- | The revised baseline assumed that 266 subscribers of Telemedicine and Higher Ed CAIs would receive improved access. We were able to accelerate our implementation which resulted in an excess of calculated variance (+192). Subscribers receiving improved access: 249 Telemedicine 133 Telemedicine* (FCC-funded) 32 Higher-Education 44 CAIs improved utilizing BTOP-funded equipment** - 35 Medical & Healthcare Providers - 8 Libraries - 1 Public Safety *Sites received BTOP-funded equipment; connected to network via FCC Pilot Program-funded broadband. **Sites received BTOP-funded equipment; connected through their parent organization's BTOP-funded broadband OR no connectivity funded. | The (actual) speed tiers and number of subscribers for each: 1.5Mbps.. 296 10Mbps......80 100Mbps..... 8 1Gbps........21 10Gbps........9 TOTAL: 414 Note: Remaining 44 sites (35 Medical & Healthcare Providers, 8 Libraries, and 1 Public Safety) which brings our total to 458 sites, received BTOP-funded equipment but are using their own connectivity. Therefore, these sites are not included in the speed tier calculations. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Co-location space and power is available at network fiber huts. | FALSE | N/A | Now that the BTOP grant project is complete, there is evidence of its impact in several rural communities. Examples of expanded telehealth services being offered as a result of the grant include: cardiac care provided by cardiologists to rural areas, behavioral health consultations with inmates in city jails, and expansion of the e-ICU services to rural hospitals. There is increased interest in receiving required continuing education through distance learning for healthcare providers in rural locations and collaborations between colleges offering health curriculum and healthcare providers. In the uncertain climate of healthcare reimbursement, Arkansas BTOP grant recipients are looking for ways to become streamlined and collaborative in how business is conducted. Telehealth reimbursement continues to be an issue in Arkansas. To further this cause, an Arkansas State Senator who chairs the Legislative Committee on Public Health, Welfare, and Labor has drafted a bill and anticipates it will be introduced by the end of the year. This bill will begin a year-long Interim Study Proposal seeking legislative support of telehealth reimbursement. Many of the grant recipients will be interviewed as stakeholders before the committee. The success of this legislation could significantly impact the long-term viability of this program. UAMS successfully led the Arkansas Telehealth Network coalition in receiving a grant for the USAC Rural Healthcare Pilot Project. We have received approval from NTIA and FCC to migrate the Arkansas e-Link membership into the new FCC Healthcare Connect Fund program as a consortium. UAMS will lead this consortium. Approved entities may obtain 65% discounts for eligible expenses, thus benefiting current and future network participants, as well as positively impacting the future network growth. ARE-ON is a non-commercial state entity and therefore it is subject to legal restrictions on the customers it may serve and the manner in which it may serve them. Within the constraints of the law, ARE-ON will continue to seek new uses of its fiber network from state and non-commercial/non-profit entities such as: higher education institutions, public schools, public libraries, state, county, and local government, the Division of Agriculture of the University of Arkansas, and potentially a federal research laboratory located within the state. Finally, the broadband expansion has also provisioned more competitiveness among telecom companies. This has positioned telecommunications providers to extend services to Arkansas consumers in many rural areas. | University of Arkansas System | N/A | N/A | TRUE
NT10BIX5570103 | 2010 | Q4 | Q4 - 2010 | In the second quarter of the Nevada Broadband Telemedicine Initiative award period [4Q10], our organization completed the following: â€¢ Participated in Federal Program Officer Desk Review to provide a status report on each of the Special Award Conditions and project startup activities. â€¢ Established an organizational structure to manage and monitor the project. â€¢ Established financial accounting/auditing systems to manage project funds and federal grant expenditures. â€¢ Established grants file. â€¢ Prepared and submitted 6-month budget in accordance with Special Award Conditions. â€¢ Prepared and submitted Baseline Project Plan and Baseline Report to meet requirements of the Special Award Conditions. â€¢ Prepared and submitted Environmental Assessment Milestone Tracker. â€¢ Reviewed and updated existing procurement policies and company code of conduct for compliance with federal regulations. â€¢ A formal RFP was issued, and e-Care Nevada, Inc. selected, as a subrecipient to operate/manage project implementation. â€¢ Completed review of Award requirements and federal guidelines/compliance with subrecipient. â€¢ Established a subrecipient Monitoring System. â€¢ Reassessed project timeline and feasibility based on Special Award Conditions, specifically related to the Environmental Assessment. â€¢ Launched regular review meetings with project participants. â€¢ A formal RFP was issued and an EA firm tentatively selected to meet requirements of the Special Award Conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No activity this quarter. | No activity this quarter. | N/A | N/A | No activity this quarter. | No activity this quarter. | N/A | No activity this quarter. | 0 | 0 | 0 | No activity this quarter. | No activity this quarter.3 | During this project quarter, a formal RFP was issued and e-Care Nevada, Inc. was selected to manage, engineer, design, and operate the network. This entity would function as a subrecipient of the grant and be responsible for the following elements of project implementation: â€¢ Manage completion of an Environmental Assessment, and seek to secure the appropriate approvals resulting from such assessment. â€¢ Develop policies and procedures needed to secure all appropriate permits. â€¢ Provide Final Engineering and Design. â€¢ Develop a working budget to complete the Network design, engineering, operation, maintenance, and QoS standards needed to ensure sustainability. â€¢ Formulate Construction Management specifications. â€¢ Conduct Contractor evaluation and selection. â€¢ Complete Demand/Marketing Studies for Network growth and use; obtaining appropriate letters of interest and commitment from Member Hospitals, ancillary facilities, last mile service providers, and other related anchor institutions. â€¢ Review, and where necessary recalculate, the network budget. â€¢ Incorporate leased services into overall Network design and pursue agreements with dark fiber and wholesale rates for lit services. â€¢ Construction Oversight. â€¢ Management and Operation of the Network including management supervision, general operations, maintenance, network monitoring and control, customer service/sales and marketing. e-Care Contact Information: 900 South Pavilion Center Drive Las Vegas, | 0 | 0 | 0 | 0 | No activity this quarter. | No activity this quarter. | No activity this quarter. | No activity this quarter. | 0 | 0 | 0 | 0 | No activity this quarter. | No activity this quarter. | No activity this quarter. | No activity this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No activity this quarter. | FALSE | true | â€¢ Contact Federal and State agencies, specifically FWS, SHPO, and the Shoshone Paiute Tribe. â€¢ Prepare and submit draft EA by the February 1, 2011 date specified in Award SAC. â€¢ Execute formal contract with e-Care Nevada, Inc. as a subrecipient to operate/manage project implementation. â€¢ Participate in weekly progress conference calls with subrecipient, FPO, engineering, and construction to ensure progress on priority SAC's, specifically related to the EA. â€¢ Conduct meetings/conference calls with NHA Broadband Oversight Committee consisting of hospital representatives. â€¢Conduct a route feasibility analysis identifying appropriate routes and termination locations for the network. â€¢Continue discussions with Nevada System of Higher Education on proposed collaboration related to educational network infrastructure. â€¢ Increased participation and collaboration with other ARRA awardees to identify and address overlap issues. â€¢ Continue discussions with other ARRA awardees - Arizona Nevada Tower Corporation and Digital 395 to identify potential project overlap in network design. â€¢ Identify potential vendors for equipment and pre-qualifications in anticipation of FONSI approval. â€¢ Draft informational white paper on essential network elements for member facilities. â€¢ Draft community outreach plan for additional community anchor institutions. â€¢ Identify requirements for Outside Plant materials. â€¢ On site visits with individual member hospital facilities. â€¢ | Nevada Hospital Association | The most challenging aspect of this quarter was readjusting project timelines based on evolving requirements and the timing needed to secure approvals to proceed with the project. This included: â€¢ Clarifying and understanding differences between award period and physical receipt of Award Package. â€¢ Clarification from agencies related to EA response dates. â€¢ Under federal procurement policies, performed a formal RFP process to select a network operator/manager, thus consuming a portion of the award acceptance period. â€¢ Adjustments to project implementation plan to address Special Award Conditions, specifically the Environmental Assessment. Our organization successfully navigated these issues and will be submitting a draft EA by the February 1, 2011 deadline outlined in the Award SAC. | Potential delays and challenges next quarter may occur based on the outcomes of the draft EA. | TRUE
NT10BIX5570103 | 2011 | Q1 | Q1 - 2011 | In the third quarter of the Nevada Broadband Telemedicine Initiative award period [1Q11], our organization completed the following: ADMINISTRATIVE â€¢ Established organizational structure to manage and monitor the project. â€¢ Performed consolidated audit of the Nevada Hospital Association for year ending December 31, 2010; no federal findings. â€¢ Established financial accounting/auditing systems to manage project funds and federal grant expenditures. â€¢ Reviewed and updated existing procurement policies and company code of conduct for compliance with federal regulations. â€¢ A formal contract was executed with e-Care Nevada, Inc. to serve as subrecipient and operate/manage project implementation. â€¢ Established a subrecipient Monitoring System. â€¢ Conducted meetings/conference calls with NHA Broadband Oversight Committee consisting of hospital representatives. â€¢ Launched regular review meetings with project participants. â€¢ Conducted weekly progress conference calls with FPO to ensure progress on priority SAC's, specifically related to the EA and meeting the deadlines as defined in the EA Milestone Tracker. ENGINEERING â€¢ Preliminary route engineering design considerations provided for the draft EA. â€¢ Conducted route feasibility analysis identifying appropriate routes and termination locations for the network. â€¢ Initial research identifying existing broadband facilities that might be leased or purchased. â€¢ Discussions with NDOT related to right of way access | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Progress pending submission of proposed project route modifications affecting final FONSI approval. | Progress pending submission of proposed project route modifications affecting final FONSI approval. | N/A | N/A | Progress pending submission of proposed project route modifications affecting final FONSI approval. | No activity this quarter. No variance from Baseline Plan. | N/A | No activity this quarter. No variance from Baseline Plane from Baseline Plan. | 0 | 10 | 0 | No activity this quarter. | No activity this quarter. | During this project quarter, e-Care Nevada, Inc. was awarded the contract to coordinate engineering and design for the network. This entity functions as a subrecipient of the grant and is responsible for the following elements of project implementation: â€¢ Manage completion of an Environmental Assessment, and seek to secure the appropriate approvals resulting from such assessment. â€¢ Develop policies and procedures needed to secure appropriate permits. â€¢ Provide Final Engineering and Design. â€¢ Develop a working budget to complete the Network design, engineering, operation, maintenance, and QoS standards needed to ensure sustainability. â€¢ Formulate Construction Management specifications. â€¢ Conduct Contractor evaluation and selection. â€¢ Complete Demand/Marketing Studies for Network growth and use; obtaining appropriate letters of interest and commitment from Member Hospitals, ancillary facilities, last mile service providers, and other related anchor institutions. â€¢ Review, and where necessary, recalculate the network budget. â€¢ Incorporate leased or IRU facilities into overall Network design and pursue agreements with dark fiber and wholesale rates for lit services. â€¢ Construction Oversight. â€¢ Development of product and service definitions focused on initial set of services to be available at network launch, future tiered service offerings, and competitive market pricing review. e-Care Contact Information: 900 South Pavilion Center Drive, Suite 180 Las | 0 | 0 | 0 | 0 | No activity this quarter. No variance from Baseline Plan. | No activity this quarter. No variance from Baseline Plan. | Variance with Baseline Plan due to ongoing negotiations with dark fiber providers. | No activity this quarter. No variance from Baseline Plan. | 0 | 0 | 0 | 0 | No activity this quarter. No variance from Baseline Plan. | No activity this quarter. No variance from Baseline Plan. | No activity this quarter. No variance from Baseline Plan. | No activity this quarter. No variance from Baseline Plan. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No activity this quarter. | FALSE |  | ADMINISTRATIVE â€¢ Complete subrecipient monitoring for review of Grants Files, Award requirements, and federal guidelines/compliance. â€¢ Participate in weekly progress conference calls with subrecipient, FPO, engineering, and construction to ensure project progress. â€¢ Conduct meetings/conference calls with NHA Broadband Oversight Committee consisting of hospital representatives. â€¢ Continue review of project plans, agreements, and status with Federal Program Officer. ENGINEERING â€¢ Provide Final Engineering and Design. â€¢ Formulate Construction Management specifications. â€¢ Continue discussions with NSHE, NDOT, and DOIT on proposed collaboration on network infrastructure. â€¢ Identify potential vendors for equipment and pre-qualifications in anticipation of FONSI approval; conduct contractor evaluation and selection. â€¢ Work on permitting procedures with NDOT and BLM for select routes. â€¢ Incorporate leased services into overall Network design and finalize agreements with dark fiber providers as well as wholesale agreements for lit services. â€¢ Continue negotiations with NDOT related to potential Right of Way access and use of fiber facilities. â€¢ Prepare and submit project modifications related to network routes. â€¢ Secure commitments from dark fiber/last mile providers to secure excess capacity in areas where new fiber will be built. â€¢ Enter into MOU with each state agency detailing use of the state controlled infrastructure and the NHA Infrastructure. OUT | Nevada Hospital Association | In pursuing all dark fiber options, it was discovered that there were alternate routes offering potentially superior solutions to those initially submitted. By utilizing these routes it could enable a more robust network incorporating redundant ring architecture, thus increasing network reliability and sustainability. Review and approval challenges are being addressed by the Nevada Hospital Association. The Nevada Hospital Association encountered challenges in obtaining approvals, review, and comments from State and Federal Agencies related to the Environmental Assessment. The Bureau of Land Management indicated their review of the administrative EA would begin following a defined relationship between BLM and NTIA. An executed MOU between BLM and NTIA is acknowledged as critical to the EA review and approval process. The State Historic Preservation Office noted it would be premature to concur with the finding of no adverse effect until the BLM commented on the document. | Potential delays and challenges next quarter may occur based on comments and review of the draft EA as well as any proposed project route modification approvals. | TRUE
NT10BIX5570103 | 2011 | Q2 | Q2 - 2011 | In the fourth quarter of the Nevada Broadband Telemedicine Initiative award period [2Q11], our organization completed the following: ADMINISTRATIVE Conducted subrecipient monitoring site visit to review compliance documentation, grants file, internal control, policies and procedures. Conducted regular project status and review meetings with project participants to ensure project progress. Conducted call with Federal EA team to provide updates on Environmental Assessment consultations and progress against priority Special Award Conditions (SAC). Weekly conference calls with Federal Program Officer/NTIA to update project status and to ensure federal grant program compliance. Meetings/conference calls with Nevada Hospital Association (NHA) Broadband Oversight Committee consisting of hospital representatives. Contract negotiations to execute a Phase II agreement encompassing the construction phase of the project. Developed website content for the project. ENGINEERING Prepared revised network designs and supporting detailed route summaries for project modifications approval with NTIA. Development of detailed route evaluation, including specific construction types. Conducted route feasibility analysis identifying appropriate routes and termination locations. Contacted private/other rights of way owners to pursue alternatives to high cost, high environmental impact construction. Identified initial requirements and pricing for outside plant materials. Reviewed system design an | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Progress pending final approval of proposed project route modifications affecting final FONSI approval. | Progress pending final approval of proposed project route modifications affecting final FONSI approval. | N/A | N/A | Progress pending final approval of proposed project route modifications affecting final FONSI approval. | Progress pending final approval of proposed project route modifications affecting final FONSI approval. | N/A | Progress pending final approval of proposed project route modifications affecting final FONSI approvall of proposed project route modifications affecting final FONSI approval. | 0 | 10 | 0 | No activity this quarter. | No activity this quarter. | e-Care Nevada, Inc. was awarded the contract to coordinate engineering and design for the network. This entity functions as a subrecipient of the grant and is responsible for the following elements of project implementation: â€¢ Manage completion of an Environmental Assessment, and seek to secure the appropriate approvals resulting from such assessment. â€¢ Develop policies and procedures needed to secure appropriate permits. â€¢ Provide Final Engineering and Design. â€¢ Develop a working budget to complete the Network design, engineering, operation, maintenance, and QoS standards needed to ensure sustainability. â€¢ Formulate Construction Management specifications. â€¢ Conduct Contractor evaluation and selection. â€¢ Complete Demand/Marketing Studies for Network growth and use; obtaining appropriate letters of interest and commitment from Member Hospitals, ancillary facilities, last mile service providers, and other related anchor institutions. â€¢ Review, and where necessary, recalculate the network budget. â€¢ Incorporate leased or IRU facilities into overall Network design and pursue agreements with dark fiber and wholesale rates for lit services. â€¢ Construction Oversight. â€¢ Development of product and service definitions focused on initial set of services to be available at network launch, future tiered service offerings, and competitive market pricing review. e-Care Contact Information: 900 South Pavilion Center Drive, Suite 180 Las Vegas, NV 89144 http://www.e | 0 | 0 | 0 | 0 | No activity this quarter. No variance from Baseline Plan. | No activity this quarter. No variance from Baseline Plan. | Variance with Baseline Plan due to ongoing negotiations with dark fiber providers. | No activity this quarter. | 0 | 0 | 0 | 0 | Progress pending final approval of proposed project route modifications affecting final FONSI approval. | Progress pending final approval of proposed project route modifications affecting final FONSI approval. | Progress pending final approval of proposed project route modifications affecting final FONSI approval. | No activity this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No activity this quarter. | FALSE |  | ADMINISTRATIVE Execute formal contract for Phase II agreement encompassing the construction phase of the project. Seek and confirm NTIA approval for proposed project modifications. Complete subrecipient monitoring for review of Grants Files, Award requirements, and federal guidelines/compliance. Participate in regular calls with subrecipient, engineering, and construction to ensure project progress. Conduct meetings/conference calls with NHA Broadband Oversight Committee consisting of hospital representatives. Continue review of project plans, agreements, and status with Federal Program Officer. Continue calls with Federal EA team to ensure progress on priority SAC's, specifically related to the EA. ENGINEERING Finalize route design and initiate contacts with rights of way owners for access and use of existing facilities. Conduct in depth survey of hospital facilities' Outside Plant and Inside Plant. Issue formal RFQâ€™s for project equipment and materials. Execute agreements and initiate activation of Data Center(s). Engineer routes and determine placement of regeneration sites; execute agreements for use of conduit. Coordinate upgrades to routes to support lit services including design and construction of new regeneration sites; execute agreement for use of conduit along these routes. Execute agreements for fiber leases where applicable. Complete permitting for lateral construction in major build areas; issue RFQâ€™s and award contracts for construction of laterals. Begi | Nevada Hospital Association | In pursuing all dark fiber options, it was discovered that there were alternate routes offering potentially superior solutions to those initially submitted. By utilizing these routes it could enable a more robust network incorporating redundant ring architecture, thus increasing network reliability and sustainability. The challenges faced during this project quarter included the preparation of, and revisions to, the network map, project routes, financial exhibits, and supporting project plan seeking formal approval by NTIA for proposed route changes. The NTIA facilitated the review, providing key support for the proposed project modifications. The Nevada Hospital Association encountered challenges in obtaining approvals, review, and comments from State and Federal agencies related to the Environmental Assessment. The Bureau of Land Management indicated their review of the administrative EA would begin following a defined relationship between BLM and NTIA. An executed MOU between BLM and NTIA was executed this project quarter, thereby assisting in the EA review and approval process. | Challenges next quarter may include timeline of review for the final EA, approval of proposed project route modifications, as well as potential delays related to the execution of agreements pursuant to management changes at certain State agencies. | TRUE
NT10BIX5570103 | 2011 | Q3 | Q3 - 2011 | In the first quarter of the second year of the Nevada Broadband Telemedicine Initiative Award Period [3Q11], our organization completed the following: ADMINISTRATIVE â€¢ Weekly calls with FPO/NTIA to update project status and ensure federal grant program compliance. â€¢ Weekly calls with Federal EA team to provide updates on Environmental Assessment consultations and progress against priority Special Award Conditions (SAC). â€¢ Conducted regular project status and review meetings with project participants to ensure progress. â€¢ Meetings/calls with Nevada Hospital Association Broadband Oversight Committee and NHA Broadband Contract Subcommittee consisting of hospital representatives. â€¢ Contract negotiations to execute a Phase II agreement encompassing the construction phase of the project. ENGINEERING â€¢ Completed new route design utilizing fiber on existing facilities and termination locations for the network. â€¢ Continue negotiations on MOU with Nevada State agencies for route development and lit services. â€¢ Completed OSP engineering surveys, return to sites to conduct surveys and design for inside plant. â€¢ Continue development of agreements for pole attachments with multiple facility owners. â€¢ Engineering regenerator shelter sites and negotiating with property owners for space to create network access points. â€¢ Coordinating with Digital 395 on project overlap areas, terms of construction and access locations. â€¢ Hired additional project resources and mo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Progress pending final FONSI approval. | Progress pending final FONSI approval. | N/A | N/A | Progress pending final FONSI approval. | Progress pending final FONSI approval. | N/A | Progress pending final FONSI approval. | 0 | 10 | 0 | No activity this quarter. | No activity this quarter. | e-Care Nevada, Inc. was awarded the contract to coordinate engineering and design for the network. This entity functions as a subrecipient of the grant and is responsible for the following elements of project implementation: â€¢ Manage completion of an Environmental Assessment, and seek to secure the appropriate approvals resulting from such assessment. â€¢ Develop policies and procedures needed to secure appropriate permits. â€¢ Provide Final Engineering and Design. â€¢ Develop a working budget to complete the Network design, engineering, operation, maintenance, and QoS standards needed to ensure sustainability. â€¢ Formulate Construction Management specifications. â€¢ Conduct Contractor evaluation and selection. â€¢ Complete Demand/Marketing Studies for Network growth and use; obtain appropriate letters of interest and commitment from Member Hospitals, ancillary facilities, last mile service providers, and other related anchor institutions. â€¢ Review, and where necessary, recalculate the network budget. â€¢ Incorporate leased or IRU facilities into overall Network design and pursue agreements with dark fiber providers and wholesale rates for lit services. â€¢ Construction Oversight. â€¢ Development of product and service definitions focused on initial set of services to be available at network launch, future tiered service offerings, and competitive market pricing review. e-Care Contact Information: 900 South Pavilion Center Drive, Suite 180 Las Vegas, NV 89144 http: | 0 | 0 | 0 | 0 | Variance from Baseline Plan due to ongoing negotiations with providers. | No activity this quarter. No variance from Baseline Plan. | Variance from Baseline Plan due to ongoing negotiations with providers. | No activity this quarter. | 0 | 0 | 0 | 0 | Progress pending final FONSI approval. | Progress pending final FONSI approval. | Progress pending final FONSI approval. | No activity this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No activity this quarter. | FALSE |  | ADMINISTRATIVE â€¢ Conduct NTIA on-site visit with Federal Program Officer. â€¢ Execute formal contract for Phase II agreement encompassing the construction phase of the project. â€¢ Complete subrecipient monitoring for review of Grants Files, Award requirements, and federal guidelines/compliance. â€¢ Participate in regular calls with subrecipient, engineering and construction to ensure project progress. â€¢ Conduct meetings/conference calls with NHA Broadband Oversight Committee and Board of Directors consisting of hospital representatives. â€¢ Continue review of project plans, agreements and status with Federal Program Officer. â€¢ Continue calls with Federal EA team to ensure progress on priority SAC's, specifically related to the EA. ENGINEERING â€¢ Execute agreements and initiate activation of Data Center(s). â€¢ Select and negotiate agreement for collocation facilities. â€¢ Engineer routes and determine placement of regeneration sites; execute agreements for use of conduit. â€¢ Coordinate upgrades to routes to support lit services including design and construction of new regeneration sites; execute agreement for use of conduit along these routes. â€¢ Negotiate and award contracts for initial OSP materials, ISP materials and equipment, transmission equipment and standalone equipment shelters. â€¢ Execute agreements for fiber leases where applicable. â€¢ Complete permitting for lateral construction in major build areas; issue RFQâ€™s and award contracts for construction | Nevada Hospital Association | The Nevada Hospital Association encountered challenges in obtaining approvals, review and comments from State and Federal agencies related to the Environmental Assessment. Specifically, the timeline for review of the Biological Assessment by USFWS meaningfully altered anticipated project timeline. Separately, relations with tribal nations, namely the Walker River Paiute Tribe, have emerged as a priority issue. NHA is actively working to engage Native American governments and to better establish relations. | Challenges previously identified regarding the Biological Assessment review period from USFWS, approval of the final EA, as well as tribal relations with the Walker River Paiute Tribe, will persist through next project quarter. NHA fully anticipates full FONSI approval by the end of the project quarter, pending resolution on all of the issues mentioned above. NHA recognizes that any significant delay of FONSI approval beyond December/January could potentially and meaningfully impact broader project timelines. | TRUE
NT10BIX5570103 | 2011 | Q4 | Q4 - 2011 | In the second quarter of the second year of the Nevada Broadband Telemedicine Initiative Award Period [4Q11], our organization completed the following: ADMINISTRATIVE â€¢ Weekly calls with FPO/NTIA to update project status and ensure federal grant program compliance. â€¢ Weekly calls with Federal EA team to provide updates on Environmental Assessment consultations and progress against priority Special Award Conditions (SAC). â€¢ Conducted regular project status and review meetings with project participants to ensure progress. â€¢ Completed NTIA Site Visit Audit. â€¢ Continued contract negotiations to execute a Phase II agreement encompassing the construction phase of the project. ENGINEERING â€¢ Continued new route design utilizing fiber on existing facilities and termination locations for the network. â€¢ Continued MOU negotiations with Nevada State agencies for route development and lit services. â€¢ Continued OSP engineering surveys, return to sites to conduct surveys and design for inside plant. â€¢ Continued development of agreements for pole attachments with multiple facility owners. â€¢ Continued engineering of regenerator shelter sites and negotiation with property owners for space to create network access points. â€¢ Hired additional project resources, specifically regarding contract, ROW, and easement negotiations. â€¢ Continued researching necessary (franchise or other city/jurisdiction) requirements for each network build area. â€¢ Review of submissions for RFP's related to telecommunications equipment, as well as lateral and site building conduit and cable construction. OUTREACH/SUSTAINABILITY â€¢ Conducted meetings with Community Anchor Institutions in the funded service areas. â€¢ Held briefings with Governorâ€™s office and state Department of Health and Human Services. â€¢ Conducted meetings with hospitals to discuss service definitions, pricing and timeline for network connectivity. â€¢ Attended Community Outreach meetings to discuss project status updates and collaboration opportunities with incumbent service providers. â€¢ Attended Health Insight and Connect Nevada task force meetings. â€¢ Finalized marketing strategy for network capabilities and service offerings. FINANCE/GRANT COMPLIANCE/REPORTING â€¢ ARRA, FFR, and PPR Federal Reporting submitted for quarter ending September 30, 2011. â€¢ Development of proformas supporting sustainability and operating structure for the network. â€¢ NTIA approval of revised budget covering the extended EA/Business Planning Phase. â€¢ Attended BTOP drop in calls and webinars. â€¢ Executed Cost Reimbursement Agreement with state BLM office. â€¢ Submitted revised Baseline Report corresponding with project modifications. â€¢ Additional proposed route change summary submitted for NTIAâ€™s initial review. â€¢ Completed NTIA Site Visit Audit. â€¢ Ongoing correspondence with the Office of Inspector General regarding match-share audit of BTOP grant recipients. â€¢ Preparation underway for Program Specific Audit. ENVIRONMENTAL ASSESSMENT â€¢ Continued consultations with Federal and State agencies. â€¢ Received Biological Opinion from USFWS and complied with requirements contained therein. â€¢ Submission of final draft EA to NTIA for final FONSI approval. â€¢ Submission of final draft EA to BLM for 30 day public review. â€¢ Received "Resolution for Permission to Survey" from Walker River Paiute Tribe. â€¢ Received "Resolution of Support" from Timbisha Shoshone Tribe. â€¢ Received "Letter of Concurrence for No Adverse Affect" from the State Historic Preservation Office as required for Section 106 consultation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Progress pending final FONSI approval. | Progress pending final FONSI approval. | N/A | N/A | Progress pending final FONSI approval. | N/A | N/A | Progress pending final FONSI approval. | 0 | 2 | 0 | No activity this quarter. | No activity this quarter. | e-Care Nevada, Inc. was awarded the contract to coordinate engineering and design for the network. This entity functions as a subrecipient of the grant and is responsible for the following elements of project implementation: â€¢ Manage completion of an Environmental Assessment, and seek to secure the appropriate approvals resulting from such assessment. â€¢ Develop policies and procedures needed to secure appropriate permits. â€¢ Provide Final Engineering and Design. â€¢ Develop a working budget to complete the Network design, engineering, operation, maintenance, and QoS standards needed to ensure sustainability. â€¢ Formulate Construction Management specifications. â€¢ Conduct Contractor evaluation and selection. â€¢ Complete Demand/Marketing Studies for Network growth and use; obtain appropriate letters of interest and commitment from Member Hospitals, ancillary facilities, last mile service providers, and other related anchor institutions. â€¢ Review, and where necessary, recalculate the network budget. â€¢ Incorporate leased or IRU facilities into overall Network design and pursue agreements with dark fiber providers and wholesale rates for lit services. â€¢ Construction Oversight. â€¢ Development of product and service definitions focused on initial set of services to be available at network launch, future tiered service offerings, and competitive market pricing review. e-Care Contact Information: 900 South Pavilion Center Drive, Suite 180 Las Vegas, NV 89144 http://www.ecarenevada.com 702.405.7000 | 0 | 0 | 0 | 0 | Variance from Baseline Plan due to ongoing negotiations with providers. | No activity this quarter. No variance from Baseline Plan. | Variance from Baseline Plan due to ongoing negotiations with providers. | No activity this quarter. | 0 | 0 | 0 | 0 | Progress pending final FONSI approval. | Progress pending final FONSI approval. | Progress pending final FONSI approval. | No activity this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No activity this quarter. | FALSE |  | In the third quarter of the second year of the Nevada Broadband Telemedicine Initiative Award Period [1Q12], our organization plans to complete the following: ADMINISTRATIVE • Execute formal contract for Phase II agreement encompassing the construction phase of the project. • Complete subrecipient monitoring for review of Grants Files, Award requirements, and federal guidelines/compliance. • Participate in regular calls with subrecipient, engineering and construction to ensure project progress. • Conduct meetings/conference calls with NHA Broadband Oversight Committee and Board of Directors consisting of hospital representatives. • Continue review of project plans, agreements and status with Federal Program Officer. ENGINEERING • Execute agreements and initiate activation of Data Center(s). • Select and negotiate agreement for collocation facilities. • Engineer routes and determine placement of regeneration sites; execute agreements for use of conduit. • Coordinate upgrades to routes to support lit services including design and construction of new regeneration sites; execute agreement for use of conduit along these routes. • Negotiate and award contracts for initial OSP materials, ISP materials and equipment, transmission equipment and standalone equipment shelters. • Execute agreements for fiber leases where applicable. • Complete permitting for lateral construction in major build areas; issue RFQ’s and award contracts for construction of laterals. • Begin deployment of fiber laterals in major build areas. • Coordinate route development, engineering design and permitting and materials procurement for southern Nevada routes. • Pursuant to FONSI approval, initiate phased network construction. KEY PROJECT INDICATOR PROJECTIONS • New network miles deployed: 50 • New network miles leased: 713 • Total CAI subscribers served (CAIs connected): 9 • Number of signed agreements with broadband wholesalers or last mile providers: 2 OUTREACH/SUSTAINABILITY • Finalize service definitions inclusive of technical service descriptions. • Execute service contracts with NHA member hospital facilities for connectivity to the network. • Continue to work with Community Anchor Institutions in each service area to maximize participation. FINANCE/GRANT COMPLIANCE/REPORTING • Submit ARRA Report, Federal Financial Report, Yearly Progress Report, and Quarterly Performance Progress Report for quarter ending December 31, 2011 per Special Award Conditions. • Finalize Phase budgets including construction timelines incorporating engineering, O&M and QoS standards needed to ensure sustainability. • Determine and memorialize a long-term operating structure for the network. • Attend Grants Management Educational Conference. • Complete the Recipient A-133 Audit. • Complete the Subrecipient Program-Specific Audit, due 03/31/12. • Complete the Dept. of Commerce/OIG review of grant match share. ENVIRONMENTAL ASSESSMENT • Receive Finding of No Significant Impact (FONSI) from NTIA, complete NEPA process. • Receive Finding of No Significant Impact (FONSI) from BLM. | Nevada Hospital Association | The Nevada Hospital Association encountered challenges in obtaining approval of the Biological Assessment by USFWS, which meaningfully altered the anticipated project timeline. Additionally, negotiations with State agencies related to MOU and IRU agreements have emerged as a priority issue. NHA is actively working through these matters with the relevant agencies to meet substantial project completion requirements. | NHA does not expect any further significant challenges to project progress, as NTIA FONSI approval is anticipated for January 2012, allowing deployment of network construction and operability to commence. | TRUE
NT10BIX5570103 | 2012 | Q1 | Q1 - 2012 | In the third quarter of the second year of the Nevada Broadband Telemedicine Initiative (NBTI) Award Period [1Q12], our organization completed the following: ADMINISTRATIVE â€¢ Weekly calls with National Telecommunications and Information Administration (NTIA) Federal Program Officer to update project status and ensure federal grant program compliance. â€¢ Conducted regular project status and review meetings with project participants to ensure progress. â€¢ Continued contract negotiations to execute a Phase II agreement encompassing the construction phase of the project. ENGINEERING â€¢ Executed agreements related to activation of Data Center(s) and collocation facilities. â€¢ Contracts awarded for fiber and equipment delivery. â€¢ Continued new route design utilizing fiber on existing facilities and termination locations for the network. â€¢ Finalized Memorandum of Understanding (MOU) negotiations with Nevada State agencies for route development and lit services. â€¢ Continued development of Service Level Agreements for site specific locations. â€¢ Continued outside plant engineering survey design for inside plant. â€¢ Continued development of pole attachment and conduit agreements with multiple facility owners. â€¢ Continued engineering of regenerator shelter sites and negotiation with property owners for space to create network access points. â€¢ Continued application processes necessary (franchise or other city/jurisdiction) for each network build area. â€¢ Continued review of submissions for Requests for Proposal related to lateral and site building conduit and cable construction. â€¢ Executed Dark Fiber provider MOUs, Master Service Agreements (MSA) and Service Orders to ensure network connectivity. OUTREACH/SUSTAINABILITY â€¢ Conducted multiple meetings/conference calls with Nevada Hospital Association (NHA) Broadband Oversight Committee consisting of hospital representatives. â€¢ Conducted meeting with NHA Board of Directors and NHA Policy Development Committee consisting of hospital representatives. â€¢ Developed NBTI network press release for distribution upon project deployment. â€¢ Conducted meetings with Community Anchor Institutions in the funded service areas. â€¢ Conducted meetings with hospitals to discuss service definitions, pricing and timeline for network connectivity. â€¢ Attended Community Outreach meetings to discuss project status updates and collaboration opportunities with incumbent service providers and other Broadband Initiatives Program/Broadband Technology Opportunity Program (BTOP) awardees. â€¢ Attended Health Insight and Connect Nevada task force meetings. â€¢ Finalized marketing strategy for network capabilities and service offerings. â€¢ Finalized MSAs for distribution to member hospital facilities. FINANCE/GRANT COMPLIANCE/REPORTING â€¢ American Recovery and Reinvestment Act, Federal Financial Report, and Performance Progress Report (PPR) Federal Reporting submitted for quarter ending December 31, 2011. â€¢ Annual PPR for year ending December 31, 2011 submitted. â€¢ Development of proformas supporting sustainability and operating structure for the network. â€¢ Finalized requirements related to Department of Commerce (DOC) - Office of Inspector General (OIG) regarding match-share audit of BTOP grant recipients. â€¢ Completed Recipient A-133 Audit. â€¢ Subrecipient Program-Specific Audit in progress, and to be completed within the DOC/NTIA -authorized extension period (due 04/30/12). â€¢ Addressed NBTI-related information requests from the DOC - OIG as part of its grant match audit/review of NTIA. ENVIRONMENTAL ASSESSMENT â€¢ Continued consultations with Federal and State agencies. â€¢ Received final NTIA Finding of No Significant Impact (FONSI) approval. â€¢ Received final Bureau of Land Management FONSI approval. â€¢ Completed survey of Walker River Paiute Tribe land. â€¢ Ongoing preparation for easement related to Walker River Paiute Tribe. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | N/A | N/A | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | N/A | N/A | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | 0 | 3 | 0 | No activity this quarter. | No activity this quarter. | e-Care Nevada, Inc. was awarded the contract to coordinate engineering and design for the network. This entity functions as a subrecipient of the grant and is responsible for the following elements of project implementation: â€¢ Manage completion of an Environmental Assessment, and seek to secure the appropriate approvals resulting from such assessment. â€¢ Develop policies and procedures needed to secure appropriate permits. â€¢ Provide Final Engineering and Design. â€¢ Develop a working budget to complete the Network design, engineering, operation, maintenance, and Quality of Service standards needed to ensure sustainability. â€¢ Formulate Construction Management specifications. â€¢ Conduct Contractor evaluation and selection. â€¢ Complete Demand/Marketing Studies for Network growth and use; obtain appropriate letters of interest and commitment from Member Hospitals, ancillary facilities, last mile service providers, and other related anchor institutions. â€¢ Review, and where necessary, recalculate the network budget. â€¢ Incorporate leased or Indefeasible Right of Use facilities into overall Network design and pursue agreements with dark fiber providers and wholesale rates for lit services. â€¢ Construction Oversight. â€¢ Development of product and service definitions focused on initial set of services to be available at network launch, future tiered service offerings, and competitive market pricing review. e-Care Contact Information: 900 South Pavilion Center Drive, Suite 160 Las Vegas, NV 89144 http://www.ecarenevada.com 702.405.7000 | 0 | 0 | 0 | 0 | Variance from Baseline Plan due to ongoing negotiations with providers. | No activity this quarter. No variance from Baseline Plan. | Variance from Baseline Plan due to ongoing negotiations with providers. | No activity this quarter. | 0 | 0 | 0 | 0 | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | Progress pending execution of agreements, specifically with State Agencies, and fiber delivery in 2Q12. | No activity this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No activity this quarter. | FALSE |  | In the fourth quarter of the second year of the Nevada Broadband Telemedicine Initiative (NBTI) Award Period [2Q12], our organization plans to complete the following: ADMINISTRATIVE â€¢ Execute formal contract for Phase II agreement encompassing the construction phase of the project. â€¢ Complete subrecipient monitoring for review of Grants Files, Award requirements, and federal guidelines/compliance. â€¢ Participate in regular calls with subrecipient, engineering and construction to ensure project progress. â€¢ Conduct meetings/conference calls with Nevada Hospital Association (NHA) Broadband Oversight Committee consisting of hospital representatives. â€¢ Continue review of project plans, agreements and status with Federal Program Officer. ENGINEERING â€¢ Execute agreements and initiate activation of Data Center(s). â€¢ Select and negotiate agreement for collocation facilities. â€¢ Engineer routes and determine placement of regeneration sites; execute agreements for use of conduit. â€¢ Coordinate upgrades to routes to support lit services including design and construction of new regeneration sites; execute agreement for use of conduit along these routes. â€¢ Negotiate and award contracts for initial outside plant materials, inside plant materials and equipment, transmission equipment and standalone equipment shelters. â€¢ Execute agreements for fiber leases where applicable. â€¢ Complete permitting for lateral construction in major build areas; issue Requests for Quote and award contracts for construction of laterals. â€¢ Begin deployment of fiber laterals in major build areas. â€¢ Coordinate route development, engineering design and permitting and materials procurement for southern Nevada routes. â€¢ Submit Award Action Request detailing project route changes. KEY PROJECT INDICATOR PROJECTIONS â€¢ New network miles deployed: 0 â€¢ New network miles leased: 0 â€¢ Total Community Anchor Institution (CAI) subscribers served (CAIs connected): 0 â€¢ Number of signed agreements with broadband wholesalers or last mile providers: 0 OUTREACH/SUSTAINABILITY â€¢ Distribute Master Service Agreements for execution by NHA member hospitals. â€¢ Launch and distribution of NBTI newsletter. â€¢ Conduct meetings/conference calls with NHA Broadband Oversight Committee consisting of hospital representatives. â€¢ Conduct meeting with NHA Board of Directors and NHA Policy Development Committee consisting of hospital representatives. â€¢ Execute service contracts with NHA member hospital facilities for connectivity to the network. â€¢ Continue to work with CAIs in each service area to maximize participation. â€¢ Execute backhaul transport contracts with service providers in unserved and underserved areas. FINANCE/GRANT COMPLIANCE/REPORTING â€¢ Submit American Recovery and Reinvestment Act Report, Federal Financial Report, and Quarterly Performance Progress Report for quarter ending March 31, 2012 per Special Award Conditions. â€¢ Finalize Phase budgets including construction timelines incorporating engineering, Operations and Maintenance and Quality of Service standards needed to ensure sustainability. â€¢ Determine and memorialize a long-term operating structure for the network. â€¢ Attend Grants Management Educational Conference. â€¢ Subrecipient Program-Specific Audit in progress, and to be completed within the Department of Commerce/National Telecommunications and Information Administration - authorized extension period (due 04/30/12). ENVIRONMENTAL ASSESSMENT â€¢ Receive Right of Way authorization from Bureau of Land Management. â€¢ Receive Finding of No Significant Impact (FONSI) or Categorical Exclusion from Bureau of Reclamation. â€¢ Receive FONSI or Categorical Exclusion from U.S. Forest Service. â€¢ Receive easement from Army Corps of Engineers/Department of Defense. â€¢ Receive easements from pending federal agencies and Walker River Paiute Tribe. â€¢ Receive necessary resolutions from Timbisha Shoshone Tribal Council to begin California Bureau of Indian Affairs easement application process. | Nevada Hospital Association | The Nevada Hospital Association encountered challenges in executing final agreements with State agencies and other network partners in the time frame previously projected. Additionally, a delay in fiber cable delivery has meaningfully altered the anticipated project time line. Fiber delivery is expected to commence in 2Q12. NHA is actively working through these matters with the relevant agencies to meet substantial project completion time lines. Lighting of network circuits and fiber construction is expected to begin in 3Q12. | NHA does not expect any further significant challenges to project progress. | TRUE
NT10BIX5570103 | 2012 | Q2 | Q2 - 2012 | In the fourth quarter of the second year of the Nevada Broadband Telemedicine Initiative (NBTI) Award Period [2Q12], our organization completed the following: ADMINISTRATIVE â€¢ Weekly calls with National Telecommunications and Information Administration (NTIA) Federal Program Officer to update project status and ensure federal grant program compliance. â€¢ Conducted regular project status and review meetings with project participants to ensure progress. â€¢ Finalized and executed Phase II agreement encompassing the construction phase of the project. â€¢ Submission of quarterly reporting for local jurisdictions and state agencies related to licensing and taxation compliance. â€¢ Certificate of Public Convenience and Necessity (CPCN) granted by Public Utilities Commission of Nevada to Nevada Hospital Association (NHA). ENGINEERING â€¢ Ongoing equipment installation in Las Vegas and Reno Data Centers of fiber optic terminal and network management equipment. â€¢ Design, engineering, and tenant improvements are ongoing at 5 collocation facilities, necessary to facilitate installation of equipment. â€¢ Ongoing equipment delivery of core routers, firewalls, power conditioning equipment, servers, switches, and optical electronics. Approximately 50% received. â€¢ Continued new route design utilizing fiber on existing facilities and termination locations for the network. â€¢ Execution of Master Services Agreement (MSA) with State Agencies. â€¢ Continued development of Service Level Agreements (SLA) for site specific locations related to State Agencies. â€¢ Continued outside plant engineering surveys, return to sites to conduct surveys and design for inside plant. â€¢ Execution of pole attachment agreements with multiple facility owners. â€¢ Continued development of agreements for pole attachments and conduit leases with multiple facility owners. â€¢ Continued engineering of regenerator shelter sites and negotiation with property owners for space to create network access points. â€¢ Continued application processes necessary (franchise or other city/jurisdiction) requirements for each network build area. â€¢ Continued review of submissions for Request for Proposals (RFP) related to lateral and site building conduit and cable construction. â€¢ Executed Dark Fiber provider Memorandum of Understanding (MOU), MSA's and Service Orders to ensure network connectivity. OUTREACH/SUSTAINABILITY â€¢ Conducted multiple meetings/conference calls with NHA Broadband Oversight Committee consisting of hospital representatives. â€¢ Conducted meeting with NHA Board of Directors and NHA Policy Development Committee consisting of hospital representatives. â€¢ Finalization of NBTI network press release for distribution upon project deployment. â€¢ Conducted meetings with Community Anchor Institutions in the funded service areas. â€¢ Conducted meetings with hospitals to discuss service definitions, pricing and timeline for network connectivity. â€¢ RFP related to marketing agency services released. Evaluation of submissions ongoing. â€¢ Participation in NTIA / Schools, Health & Libraries Broadband Coalition Mid-Course Workshop. â€¢ Participation in Round Table Discussion forum with Governor's office. â€¢ Attended Community Outreach meetings to discuss project status updates and collaboration opportunities with incumbent service providers and other Broadband Initiatives Program / Broadband Technology Opportunity Program (BTOP) awardees. â€¢ Attended Health Insight and Connect Nevada task force meetings. â€¢ Circulation of MSA's to member hospital facilities. â€¢ Circulation of NBTI newsletter to member hospital facilities. FINANCE/GRANT COMPLIANCE/REPORTING â€¢ American Recovery and Reinvestment Act (ARRA), Federal Financial Report (FFR), and Performance Progress Report (PPR) Federal Reporting submitted for quarter ending March 31, 2012. â€¢ Subrecipient Monitoring Site Visit completed for review of Grants Files, Award requirements, and federal guidelines/compliance. â€¢ Participation in Grants Management Training workshop. â€¢ Recipient response to Office of Inspector General (OIG) Audit of Subrecipient Monitoring completed. â€¢ Attended BTOP drop in calls and webinars. â€¢ Subrecipient Program-Specific Audit completed. â€¢ Submission of necessary Award Action Requests related to project modifications and fiber swap agreements. ENVIRONMENTAL ASSESSMENT â€¢ Continued consultations with Federal and State agencies. â€¢ Ongoing preparation for Easement related to Walker River Paiute Tribe land. â€¢ Ongoing preparation for Easement related to Timbisha Shoshone Tribe. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Progress pending execution of agreements, specifically with utility providers, and fiber delivery in 3Q12. | Progress pending execution of agreements, specifically with utility providers, and fiber delivery in 3Q12. | N/A | N/A | Progress pending execution of agreements, specifically with utility providers, and fiber delivery in 3Q12. | N/A | N/A | Progress pending execution of agreements, specifically with utility providers, and fiber delivery in 3Q12. | 0 | 1 | 0 | No activity this quarter. | No activity this quarter. | e-Care Nevada, Inc. was awarded the contract to coordinate engineering and design for the network. This entity functions as a subrecipient of the grant and is responsible for the following elements of project implementation: â€¢ Manage completion of an Environmental Assessment, and seek to secure the appropriate approvals resulting from such assessment. â€¢ Develop policies and procedures needed to secure appropriate permits. â€¢ Provide Final Engineering and Design. â€¢ Develop a working budget to complete the Network design, engineering, operation, maintenance, and Quality of Service standards needed to ensure sustainability. â€¢ Formulate Construction Management specifications. â€¢ Conduct Contractor evaluation and selection. â€¢ Complete Demand/Marketing Studies for Network growth and use; obtain appropriate letters of interest and commitment from Member Hospitals, ancillary facilities, last mile service providers, and other related anchor institutions. â€¢ Review, and where necessary, recalculate the network budget. â€¢ Incorporate leased or Indefeasible Right of Use facilities into overall Network design and pursue agreements with dark fiber providers and wholesale rates for lit services. â€¢ Construction Oversight. â€¢ Development of product and service definitions focused on initial set of services to be available at network launch, future tiered service offerings, and competitive market pricing review. e-Care Contact Information: 900 South Pavilion Center Drive, Suite 160 Las Vegas, NV 89144 http://www.ecarenevada.com 702.405.7004 | 0 | 0 | 0 | 0 | Variance from Baseline Plan due to ongoing negotiations with providers. | Variance from Baseline Plan due to ongoing negotiations with providers. | Variance from Baseline Plan due to ongoing negotiations with providers. | No activity this quarter. | 0 | 0 | 0 | 0 | Progress pending execution of agreements, specifically with utility providers, and fiber delivery in 3Q12. | Progress pending execution of agreements, specifically with utility providers, and fiber delivery in 3Q12. | Progress pending execution of agreements, specifically with utility providers, and fiber delivery in 3Q12. | No activity this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | No activity this quarter. | FALSE |  | In the first quarter of the third year of the Nevada Broadband Telemedicine Initiative (NBTI) Award Period [3Q12], our organization plans to complete the following: ADMINISTRATIVE â€¢ Participate in regular calls with subrecipient, engineering and construction to ensure project progress. â€¢ Conduct meetings/conference calls with NHA Broadband Oversight Committee and Board of Directors consisting of hospital representatives. â€¢ Continue review of project plans, agreements and status with Federal Program Officer. ENGINEERING â€¢ Accept delivery of fiber optic cable necessary for project deployment. â€¢ Engineer routes and determine placement of regeneration sites; execute agreements for use of conduit and pole attachments. â€¢ Coordinate upgrades to routes to support lit services including design and construction of new regeneration sites; execute agreement for use of conduit along these routes. â€¢ Negotiate and award contracts for initial OSP materials, ISP materials and equipment, transmission equipment and standalone equipment shelters. â€¢ Execute agreements for fiber leases where applicable. â€¢ Complete permitting for lateral construction in major build areas; issue RFQâ€™s and award contracts for construction of laterals. â€¢ Begin deployment of fiber laterals in major build areas. â€¢ Coordinate route development, engineering design and permitting and materials procurement for southern Nevada routes. â€¢ Initiate phased network construction. KEY PROJECT INDICATOR PROJECTIONS â€¢ New network miles deployed: 48 â€¢ New network miles leased: 139 â€¢ Total CAI subscribers served (CAIs connected): 0 â€¢ Number of signed agreements with broadband wholesalers or last mile providers: 5 OUTREACH/SUSTAINABILITY â€¢ Issue press release upon network deployment. â€¢ Coordinate with media outlets to promote network deployment and community awareness of NBTI. â€¢ Continued development and distribution of NBTI newsletter (quarterly). â€¢ Conduct meetings / conference calls with Nevada Hospital Association (NHA) Broadband Oversight Committee consisting of hospital representatives. â€¢ Conduct meeting with NHA Board of Directors and NHA Policy Development Committee consisting of hospital representatives. â€¢ Execute service contracts with NHA member hospital facilities for connectivity to the network. â€¢ Continue to work with Community Anchor Institutions in each service area to maximize participation. â€¢ Execute backhaul transport contracts with service providers in unserved and underserved areas. â€¢ Continue participation in Broadband Taskforce and relevant State, Telecom, and Medical Industry meetings/events to promote the NBTI. FINANCE/GRANT COMPLIANCE/REPORTING â€¢ Submit American Recovery and Reinvestment Report, Federal Financial Report, and Quarterly Performance Progress Report for quarter ending June 30, 2012 per Special Award Conditions. â€¢ Receive approval of necessary Award Action Requests related to project modifications and fiber swap agreements. â€¢ Complete quarterly audit of subrecipient as prescribed by NHA. â€¢ Participate in Broadband Technology Opportunities Program webinars and drop-in calls. â€¢ Continue making drawdowns in compliance with grant specifications. ENVIRONMENTAL ASSESSMENT â€¢ Receive Right of Way authorization from Bureau of Land Management based on originally planned network routes. â€¢ Receive Right of Way authorization from Bureau of Reclamation based on originally planned network routes. â€¢ Receive FONSI or Categorical Exclusion from U.S. Forest Service based on originally planned network routes. â€¢ Receive Easements from pending federal agencies and Tribal entities based on originally planned network routes. â€¢ Receive additional Letter of Concurrence from U.S. Fish and Wildlife Service due to planned route modifications. â€¢ Receive additional Letter of Concurrence from State Historic Preservation Office due to planned route modifications. | Nevada Hospital Association | The Nevada Hospital Association encountered challenges in executing final agreements with State agencies and other network partners in the time frame previously projected. Additionally, a delay in fiber cable delivery has meaningfully altered the anticipated project time line. Fiber delivery is expected to commence in 3Q12. NHA is actively working through these matters with the relevant agencies to meet substantial project completion time lines. Lighting of network circuits and fiber construction is expected to begin in 3Q12. | In the first quarter of the third year of the NBTI (3Q12), it is anticipated that delays in execution of necessary agreements with utility companies may persist. However, it is fully expected that such delays will be resolved prior to 4Q12. | TRUE
NT10BIX5570103 | 2012 | Q3 | Q3 - 2012 | In the first quarter of the third year of the Nevada Broadband Telemedicine Initiative (NBTI) Award Period [3Q12], our organization completed the following: ADMINISTRATIVE â€¢ Weekly calls with National Telecommunications and Information Administration (NTIA) Federal Program Officer to update project status and ensure federal grant program compliance. â€¢ Conducted regular project status and review meetings with project participants to ensure progress. â€¢ Submission of quarterly reporting for local jurisdictions and state agencies related to licensing and taxation compliance. PROJECT DEPLOYMENT â€¢ Initiation of phased network construction and fiber deployment. â€¢ Equipment installed in the Las Vegas and Reno Data Centers. â€¢ Ongoing equipment installation in collocation facilities and member hospitals located at 200 S. Virginia in Reno, SNAP in Las Vegas and 1409 E. Lake Mead Blvd. in Las Vegas (North Vista Hospital). â€¢ Initiation of project testing on the Zayo IRU fibers and for equipment at 200 S. Virginia in Reno, SNAP in Las Vegas and 1409 E. Lake Mead Blvd. in Las Vegas (North Vista Hospital). ENGINEERING â€¢ Network Construction from Reno to Carson City has been initiated and is approximately 60% complete. â€¢ Alcatel Transport Equipment has been installed at the Data Centers at 200 S. Virginia in Reno and SNAP in Las Vegas. â€¢ Alcatel Transport Equipment has been installed at North Vista Hospital in Las Vegas. This represents one out of thirty-six member hospitals installed. â€¢ Silver Springs and Yerington POP sites are under construction. Silver Springs is 5% complete and Yerington is 70% complete. This represents two out of eight regenerator/shelter site locations. â€¢ Continued new route design utilizing fiber on existing facilities and termination locations for the network. â€¢ Continued development of Service Level Agreements (SLA) for site specific locations related to State Agencies. â€¢ Continued outside plant (OSP) engineering surveys, return to sites to conduct surveys and design for inside plant (ISP). â€¢ Execution of pole attachment and fiber swap agreements with multiple facility owners and utility providers. â€¢ Completed application processes necessary (franchise or other city/jurisdiction) requirements for each network build area. â€¢ Selection of subcontractors for lateral and site building conduit and cable construction work from Reno-to-Carson City, Carson City-to-Silver Springs, and the Carson City Metro Ring. Bid issued for Arden Substation-to-Pahrump and Pahrump-to-Valley Switch. â€¢ Ongoing delivery of fiber optic cable necessary for project deployment. â€¢ Executed Dark Fiber provider Master Service Agreements (MSA) and Service Orders to ensure network connectivity. â€¢ Received initial orders for OSP materials, ISP materials and equipment, transmission equipment and standalone equipment shelters. â€¢ Bids issued for laterals in major build areas. Permit approvals pending to begin work. OUTREACH/SUSTAINABILITY â€¢ Conducted multiple meetings/conference calls with Nevada Hospital Association (NHA) Broadband Oversight Committee consisting of hospital representatives. â€¢ Conducted meeting with NHA General Membership consisting of hospital representatives. â€¢ Conducted meetings with Community Anchor Institutions in the funded service areas. â€¢ Conducted meetings with hospitals to discuss service definitions, pricing and timeline for network connectivity. â€¢ Conducted meetings with the Yerington Paiute Tribe. â€¢ Attended Community Outreach meetings to discuss project status updates and collaboration opportunities with incumbent service providers and other Broadband Initiatives Program / Broadband Technology Opportunity Program (BTOP) awardees. â€¢ Attended Health Insight and Connect Nevada task force meetings. â€¢ Circulation of MSA's to member hospital facilities. â€¢ Circulation of NBTI newsletter to member hospital facilities. FINANCE/GRANT COMPLIANCE/REPORTING â€¢ American Recovery and Reinvestment Act (ARRA), Federal Financial Report (FFR), and Performance Progress Report (PPR) Federal Reporting submitted for quarter ending June 30, 2012. â€¢ Attended BTOP drop in calls and webinars. â€¢ Submission of necessary Award Action Requests related to project modifications and fiber swap agreements. â€¢ Completed quarterly audit of subrecipient as prescribed by NHA. ENVIRONMENTAL ASSESSMENT â€¢ Continued consultations with Federal and State agencies related to original network design. â€¢ Ongoing preparation for Easement related to Walker River Paiute Tribe land related to original network design. â€¢ Submitted Right-of-Way (ROW) application related to network deployment over Yerington Paiute Tribe land related to network route modifications. â€¢ Ongoing preparation for Easement related to Timbisha Shoshone Tribe related to original network design. â€¢ Received Finding of No Significant Impact (FONSI) from Bureau of Reclamation related to original network design. | 18 | 145 | 0 | 0 | 18 | 0 | 0 | 1 | Network deployment timeline altered due to modified fiber delivery schedule and delayed execution of utility provider agreements. | Network deployment timeline altered due to modified fiber delivery schedule and delayed execution of utility provider agreements. | N/A | N/A | Network deployment timeline altered due to modified fiber delivery schedule and delayed execution of utility provider agreements. | N/A | N/A | Network deployment timeline altered due to modified fiber delivery schedule and delayed execution of utility provider agreements. | 2 | 3 | 12 | Valley Electric Association Mason Valley QuickNet | Dedicated Internet Access Ethernet Transport *See pricing attachment | e-Care Nevada, Inc. was awarded the contract to coordinate engineering and design for the network. This entity functions as a subrecipient of the grant and is responsible for the following elements of project implementation: â€¢ Manage completion of an Environmental Assessment, and seek to secure the appropriate approvals resulting from such assessment. â€¢ Develop policies and procedures needed to secure appropriate permits. â€¢ Provide Final Engineering and Design. â€¢ Develop a working budget to complete the Network design, engineering, operation, maintenance, and Quality of Service standards needed to ensure sustainability. â€¢ Formulate Construction Management specifications. â€¢ Conduct Contractor evaluation and selection. â€¢ Complete Demand/Marketing Studies for Network growth and use; obtain appropriate letters of interest and commitment from Member Hospitals, ancillary facilities, last mile service providers, and other related anchor institutions. â€¢ Review, and where necessary, recalculate the network budget. â€¢ Incorporate leased or Indefeasible Right of Use facilities into overall Network design and pursue agreements with dark fiber providers and wholesale rates for lit services. â€¢ Construction Oversight. â€¢ Development of product and service definitions focused on initial set of services to be available at network launch, future tiered service offerings, and competitive market pricing review. e-Care Contact Information: 10100 W. Charleston Blvd. Suite 160 Las Vegas, NV 89135 | 0 | 0 | 0 | 0 | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | No activity this quarter. | 0 | 0 | 0 | 0 | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | No activity this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Data Center Point-to-Point Ethernet Private Line IRU | FALSE | N/A | In the second quarter of the third year of the Nevada Broadband Telemedicine Initiative (NBTI) Award Period [4Q12], our organization plans to complete the following: ADMINISTRATIVE â€¢ Participate in regular calls with subrecipient, engineering and construction to ensure project progress. â€¢ Conduct meetings/conference calls with Nevada Hospital Association (NHA) Broadband Oversight Committee and General Membership consisting of hospital representatives. â€¢ Continue review of project plans, agreements and status with Federal Program Officer. PROJECT DEPLOYMENT â€¢ Turn up of lit services at member hospitals and continued network testing. â€¢ Continuous network construction and fiber deployment. â€¢ Continuous installation of equipment in collocation facilities and member hospitals. â€¢ Continuous project testing with the Zayo IRU fibers in Reno and Las Vegas. Equipment testing will occur as MSAâ€™s are signed and equipment can be installed at hospitals. ENGINEERING â€¢ Complete delivery of 647 miles of fiber optic cable necessary for project deployment. â€¢ Finalization of routes as included in Award Action Request, currently under National Telecommunications and Information Administration (NTIA) review. â€¢ Coordinate upgrades to routes to support lit services including design and construction of new regeneration sites. â€¢ Complete permitting for lateral construction in major build areas; issue Request for Quotes (RFQ) and award contracts for construction of laterals. â€¢ Coordinate route development, engineering design and permitting and materials procurement for southern Nevada routes. KEY PROJECT INDICATOR PROJECTIONS â€¢ New network miles deployed: 81 â€¢ New network miles leased: 155 â€¢ Total CAI subscribers served (CAIs connected): 3 â€¢ Number of signed agreements with broadband wholesalers or last mile providers: 2 OUTREACH/SUSTAINABILITY â€¢ Coordinate with media outlets to promote network deployment and community awareness of NBTI. â€¢ Continued development and distribution of NBTI newsletter (quarterly). â€¢ Conduct meetings / conference calls with NHA Broadband Oversight Committee consisting of hospital representatives. â€¢ Conduct meeting with NHA Board of Directors and NHA Policy Development Committee consisting of hospital representatives. â€¢ Execute service contracts with NHA member hospital facilities for connectivity to the network. â€¢ Continue to work with Community Anchor Institutions in each service area to maximize participation. â€¢ Execute backhaul transport contracts with service providers in unserved and underserved areas. â€¢ Continue participation in Broadband Taskforce and relevant State, Telecom, and Medical Industry meetings/events to promote the NBTI. FINANCE/GRANT COMPLIANCE/REPORTING â€¢ Submit American Recovery and Reinvestment Report, Federal Financial Report, and Quarterly Performance Progress Report for quarter ending September 30, 2012 per Special Award Conditions. â€¢ Receive approval of necessary Award Action Requests related to project modifications and fiber swap agreements. â€¢ Participate in Broadband Technology Opportunities Program webinars and drop-in calls. â€¢ Continue making drawdowns in compliance with grant specifications. â€¢ Conduct Subrecipient Monitoring Site Visit for review of Grants Files, award requirements, and federal guidelines/compliance. â€¢ Complete Office of Environmental and Historic Preservation (EHP) review. ENVIRONMENTAL ASSESSMENT â€¢ Receive Right-of-Way (ROW) authorization from Bureau of Land Management related to original network design. â€¢ Receive ROW from U.S. Forest Service related to original network design. â€¢ Receive ROW from Bureau of Indian Affairs (BIA) for Yerington Paiute Tribe as related to network route design modifications. â€¢ Receive easement from BIA for Walker River Paiute Tribe as related to original network design. â€¢ Receive acceptance of Service Level Agreement from BIA for Timbisha Shoshone Tribe as related to original network design. â€¢ Receive additional Letter of Concurrence from U.S. Fish and Wildlife Service as related to network route design modifications. â€¢ Receive additional Letter of Concurrence from State Historic Preservation Office as related to network route design modifications. | Nevada Hospital Association | The Nevada Hospital Association (NHA) encountered challenges in executing final agreements with network partners in the timeframe previously projected. Additionally, a delay in fiber cable delivery meaningfully altered the anticipated project timeline. Fiber delivery is expected to be complete in 4Q12. NHA is actively working through this matters to ensure timely project progress. | In the second quarter of the third year of the NBTI (4Q12), no further delays are anticipated. | TRUE
NT10BIX5570103 | 2012 | Q4 | Q4 - 2012 | In the second quarter of the third year of the Nevada Broadband Telemedicine Initiative (NBTI) Award Period (4Q12), our organization completed the following: ADMINISTRATIVE â€¢ Weekly calls with National Telecommunications and Information Administration (NTIA) Federal Program Officer (FPO) to update project status and ensure federal grant program compliance. â€¢ Conducted regular project status and review meetings with project participants to ensure progress. â€¢ Submission of quarterly reporting for local jurisdiction and state agencies related to licensing and taxation compliance. â€¢ Conducted regular finance/budget vendor monitoring meeting. PROJECT DEPLOYMENT â€¢ 316,594 feet of cable placed between Reno - Carson City (158,118 Feet) and Carson City - Silver Springs (158,476 Feet) route segments. â€¢ Ongoing constructions in Carson City, Silver Springs and Yerington POP sites. ENGINEERING â€¢ Ongoing fiber installation. The network construction from Reno - Carson City and Carson City â€“ Silver Springs route segments are approximately 90% complete. â€¢ Ongoing construction in Carson City, Silver Springs and Yerington POP sites. The Civil Build for the Carson City POP is 90% complete, Silver Springs POP is 50% complete and Yerington POP is 100 % complete. The equipment installation will schedule to commence once the fiber optic cable installation is close to its completion for these locations. This represents three of out five POP sites on the network. There are 5 regenerator/shelter site locations where work is scheduled to start pending approval of the Bureau of Land Management (BLM) Right-of-Way (ROW) and approval of AAR #2 (Route Change Award Action Request). â€¢ Ongoing approval of permits from utility providers related to fiber installation. â€¢ Ongoing Outside Plant (OSP) engineering surveys on routes that requires to be re-designed due to issues with easements or lack of structural integrity of some pole lines. Design for Inside Plant (ISP) has been completed. â€¢ Franchise Agreement for City of North Las Vegas has been approved. â€¢ The selection of the subcontractor for aerial cable installation and splicing for all segments between Silver Springs to Las Vegas (SNAP) and from Arden to Amargosa Henderson has been completed. â€¢ Received orders for OSP and ISP materials and equipment required to meet the current construction schedule. â€¢ Bid issued for laterals in major build areas. Permit approvals pending to begin work. â€¢ Created Nevada Energy (NVE) Distribution Pole Permit Tracker and AT&T Permit Tracking Log. OUTREACH/SUSTAINABILITY â€¢ Continued to request execution of Master Service Agreements, Service Orders, and Letters of Commitment with grant-named hospitals. â€¢ Participated in Connect Nevada meetings in counties throughout the State promoting economic development impact from the network. â€¢ Continual review of pricing structure and service definitions for member hospitals and Community Anchor Institutions (CAIs). â€¢ Identified and pursuing significant Department of Defense opportunity at Creech Air Force Base in Indian Springs, NV. â€¢ Conducted meetings with CAIs in the funded service areas to pre-sell services and identify member hospital network needs and requirements. â€¢ Ongoing discussion regarding collaboration with HealtHIE Nevada and Department of Health and Human Services State HIE. â€¢ Continued research and analysis into other potential state, federal and private funding initiatives. â€¢ Conducted multiple meetings/conference calls with Nevada Hospital Association (NHA) Broadband Oversight Committee consisting of hospital representatives. â€¢ Attended Community Outreach meetings to discuss project status updates and collaboration opportunities with incumbent service providers and other Broadband Initiatives Program / Broadband Technology Opportunity Program (BTOP) awardees. â€¢ Circulation of MSA's to member hospital facilities. â€¢ Investigation of alternatives methods of serving I-80 corridor. FINANCE/GRANT COMPLIANCE/REPORTING â€¢ American Recovery and Reinvestment Act (ARRA), Federal Financial Report (FFR), and Performance Progress Report (PPR) Federal Reporting submitted for quarter ending September 30, 2012. â€¢ Attended BTOP drop in calls and webinars. â€¢ Conducted monthly financial/budget vendor monitoring meeting. ENVIRONMENTAL ASSESSMENT â€¢ Continuous consultation with Federal agencies. â€¢ Submission of response to NTIA EHP Review. â€¢ Received a completed survey and a revised appraisal related to Walker River Paiute Tribe (WRPT), preparation for easement is ongoing. â€¢ Received Service Line Agreement (SLA) and Concurrence Letter related to Timbisha Shoshone Tribe. â€¢ Received concurrence letter from U.S. Fish and Wildlife Service (USFWS) related to route modifications. â€¢ Received concurrence letter from State Historic Preservation Office related to route modifications. â€¢ Ongoing development of Yerington Paiute Tribe (YPT) Right-of-Way (ROW) application. | 42 | 145 | 0 | 0 | 42 | 0 | 0 | 1 | Network deployment time line altered due to progress pending approval of permits with utility providers. Additionally, the delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network deployment time line. | Network miles leased in 3Q12 = 145 miles. This represents the total miles to be leased during the entirety of the project. There are no other leased fibers that are planned for the grant network installation. | N/A | N/A | Network deployment time line altered due to progress pending approval of permits with utility providers. Additionally, the delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | N/A | N/A | Network deployment time line altered due to progress pending approval of permits with utility providers. Additionally, the delay on the approval of final agreements with federal agencies and Tribes related to ROW significantly affected the network project time line. | 1 | 4 | 12 | Mason Valley QuickNet | Dedicated Internet Access Ethernet Transport *See pricing attachment | â€¢ Manage completion of an Environmental Assessment, and seek to secure the appropriate approvals resulting from such assessment. â€¢ Develop policies and procedures needed to secure appropriate permits. â€¢ Provide Final Engineering and Design. â€¢ Develop a working budget to complete the Network design, engineering, operation, maintenance, and Quality of Service standards needed to ensure sustainability. â€¢ Formulate Construction Management specifications. â€¢ Conduct Contractor evaluation and selection. â€¢ Complete Demand/Marketing Studies for Network growth and use; obtain appropriate letters of interest and commitment from Member Hospitals, ancillary facilities, last mile service providers, and other related anchor institutions. â€¢ Review, and where necessary, recalculate the network budget. â€¢ Incorporate leased or Indefeasible Right of Use facilities into overall Network design and pursue agreements with dark fiber providers and wholesale rates for lit services. â€¢ Construction Oversight. â€¢ Development of product and service definitions focused on initial set of services to be available at network launch, future tiered service offerings, and competitive market pricing review. e-Care Contact Information: 10100 W. Charleston Blvd. Suite 160 Las Vegas, NV 89135 | 1 | 0 | 0 | 0 | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | No activity this quarter. | 0 | 0 | 0 | 0 | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | No activity this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Ethernet Transport Dedicated Internet Access (DIA) Point-to-Point Ethernet Private Line IRU | FALSE | N/A | In the third quarter of the third year of the Nevada Broadband Telemedicine Initiative (NBTI) Award Period 1Q13, our organization plans to complete the following: ADMINISTRATIVE â€¢ Continuous participation in regular calls with subrecipient, engineering and construction subcontractors to ensure project progress. â€¢ Conduct meeting/conference calls with Nevada Hospital Association (NHA) Broadband Oversight Committee and General Membership consisting of hospital representatives. â€¢ Continuous review of project plans, agreements and status with Federal Program Officer. PROJECT DEPLOYMENT â€¢ Continuous network construction and fiber installation. â€¢ Conduct bidding to select subcontractors for the remaining work in Carson City - Gardnerville and Goldfield - Lida Junction segments. â€¢ Completion of fiber installation in Reno â€“ Carson City â€“ Silver Springs route segments. ENGINEERING â€¢ Finalization of routes included in Award Action Requests, currently under NTIA review. â€¢ Coordinate upgrades to routes to support lit services including design and construction of new regeneration sites. â€¢ Complete permitting for lateral construction in major build areas; issue Request for Quotes (RFQ) and award contracts for construction laterals. â€¢ Coordinate route development, engineering design and permitting and materials procurement for southern Nevada routes. KEY PROJECT INDICATOR PROJECTIONS â€¢ New network miles deployed: Estimated 210 miles â€¢ New network miles leased: 0 â€¢ Total CAI subscribers served (CAIs connected): 0 â€¢ Number of signed agreements with broadband wholesalers or last mile providers:2 OUTREACH/SUSTAINABILTY â€¢ Continuous requests for executed Master Service Agreements, Service Orders, and Letters of Commitment from NHA member hospitals. â€¢ Continuous marketing to CAIs to maximize participation and set foundation for economic development. â€¢ Issue NBTI press release and rollout structured statewide marketing campaign. â€¢ Conduct meetings / conference calls with Nevada Hospital Association (NHA) Broadband Oversight Committee consisting of hospital representatives. â€¢ Execute backhaul transport and broadband service contracts with service providers in unserved and underserved areas. â€¢ Continuous participation in Broadband Taskforce and relevant State, Telecom, and Medical Industry meetings/events to promote the NBTI. FINANCE/GRANT COMPLIANCE/REPORTING â€¢ Submit American Recovery and Reinvestment Report, Federal Financial Report, and quarterly and annual Performance Progress Report for quarter ending December 30, 2012 per Special Award Conditions. â€¢ Receive approval of necessary Award Action Requests related to project modifications and fiber swap agreements. â€¢ Participate in Broadband Technology Opportunities Program webinars and drop-in calls. â€¢ Continue making drawdowns in compliance with grant specifications. â€¢ Conduct Subrecipient Monitoring Site Visit for review of Grants Files, award requirements, and federal guidelines/compliance. â€¢ Anticipating approval on NHA response to NTIA Environmental and Historic Preservation (EHP) review. â€¢ Continuous financial/budget vendor monitoring meeting. ENVIRONMENTAL ASSESSMENT â€¢ Anticipating approval of ROW authorization from U.S. Forest Service (USFS). â€¢ Anticipating NTIA approval on NHAâ€™s response to EHP Review. â€¢ Anticipating approval of easements for private land owners. â€¢ Anticipating approval of ROW authorization from Bureau of Land Management. â€¢ Anticipating approval of Easements/ROW from pending Tribal entities. | Nevada Hospital Association | The Nevada Hospital Association (NHA) encountered challenges in acquiring permits from utility providers related to fiber installation. Additionally, a delay on approval of final agreements with federal agencies and Tribes related to Right-of-Way significantly altered the project time line. NHA is actively working through these matters with the relevant agencies to meet substantial project completion time lines. | In the first quarter of the third year of the NBTI (1Q13), no further delays are anticipated. | TRUE
NT10BIX5570103 | 2013 | Q1 | Q1 - 2013 | In the third quarter of the third year of the Nevada Broadband Telemedicine Initiative (NBTI) Award Period (1Q13), our organization completed the following: ADMINISTRATIVE â€¢ Continuous consultation with the National Telecommunications and Information Administration (NTIA) Federal Program Officer (FPO) to update project status and ensure federal grant program compliance. â€¢ Conducted regular project status and review meetings with project participants to ensure progress. â€¢ Submission of quarterly reporting for local jurisdiction and state agencies related to licensing and taxation compliance. â€¢ Conducted regular finance/budget vendor monitoring meeting. PROJECT DEPLOYMENT â€¢ 349,488 feet of cable placed between Reno â€“ Carson City (165,354 Feet) and Carson City â€“ Silver Springs (184,134 Feet) route segments. â€¢ Civil construction is complete for the Carson City, Silver Springs and Yerington POP Sites. ENGINEERING â€¢ Ongoing collaboration between NHA and its Contractor on the Award Action Request (AAR) #4 to address numerous changes in routes and design identified since the project redesign described in AAR #2 approved in January 2013 and No Cost Extension. â€¢ Coordinate upgrades to routes to support lit services including design and construction of new regeneration sites. â€¢ Lateral designs completed for major construction in major build areas; Request for Quotes (RFQ) completed for Reno-Saint Mary, Reno-Renown and Las Vegas-St. Rose Dominican Hospitals-Siena Campus. Award of work pending completion of Master Service Agreements (MSAs) and Service Orders for these sites. All other laterals are designed and will have RFQs sent out once MSAs and Service Orders have been received. â€¢ Route development, engineering design, permitting and materials procurement for southern Nevada routes are completed except for the Mona Substation to Boulder City Hospital. Route selection in process for this remaining segment. â€¢ Ongoing fiber installation. The network construction from Reno to Carson City â€“ Silver Springs route segments are approximately 99% complete. â€¢ Civil Build in Carson City, Silver Springs and Yerington POP sites is 100% complete. The equipment installation has begun at all three locations and is scheduled to complete the end of April. This represents three out of five POP sites on the network. There are 5 regenerator/shelter site locations where work is scheduled to start pending approval of the Bureau of Land Management (BLM) Right-of-Way (ROW). â€¢ Ongoing approval of permits from utility providers related to fiber installation. â€¢ Ongoing Outside Plant (OSP) engineering surveys on routes that requires to be re-designed due to issues with easements or lack of structural integrity of some pole lines. Design for Inside Plant (ISP) has been completed. â€¢ Received orders for OSP and ISP materials and equipment required to meet the current construction schedule. â€¢ Selection of subcontractors for aerial cable installation and splicing for all segments between Silver Springs to Las Vegas (SNAP), from Arden to Amargosa, Henderson and the Carson City Metro Ring has been completed. Construction of the Carson City Metro Ring is scheduled to begin early April. â€¢ Ongoing update on the Nevada Energy Distribution Pole Permit Tracker and AT&T Permit Tracking Log. OUTREACH/SUSTAINABILITY â€¢ Continued to request execution of MSAs, Service Orders, and Letters of Commitment with grant-named hospitals. â€¢ Participated in Connect Nevada meetings in counties throughout the State promoting economic development impact from the network and presented status updates before the Nevada Broadband Task Force. â€¢ Continued review of pricing structure and service definitions for member hospitals and Community Anchor Institutions (CAIs). â€¢ Identified and pursuing significant Department of Defense opportunity at Creech Air Force Base in Indian Springs, NV. â€¢ Identified and pursuing significant wireless backhaul opportunities in Beatty and Pahrump. â€¢ Conducted meetings with CAIs in the funded service areas to pre-sell services and identify member hospital network needs and requirements. â€¢ Ongoing discussion regarding collaboration with HealtHIE Nevada and Department of Health and Human Services State HIE. â€¢ Continued research and analysis into other potential state, federal and private funding initiatives. â€¢ Conducted individual meetings/conference calls with members of the Nevada Hospital Association (NHA) Broadband Oversight Committee consisting of hospital representatives. â€¢ Conducted meeting with NHA Board of Directors and NHA Policy Development Committee consisting of hospital representatives. â€¢ Attended Community Outreach meetings to discuss project status updates and collaboration opportunities with incumbent service providers and other Broadband Initiatives Program / Broadband Technology Opportunity Program (BTOP) awardees. â€¢ Investigation of alternatives methods of serving I-80 corridor. FINANCE/GRANT COMPLIANCE/REPORTING â€¢ American Recovery and Reinvestment Act (ARRA), Federal Financial Report (FFR), Performance Progress Report (PPR) and Federal Reporting submitted for quarterly and annual report ending December 31, 2012. â€¢ Completed Recipient A-133 Audit. â€¢ Attended BTOP drop in calls and webinars. â€¢ Conducted monthly financial/budget vendor monitoring meeting. ENVIRONMENTAL ASSESSMENT â€¢ Continued consultation with Federal and State agencies. â€¢ Coordinated with relevant tribal entities and state/federal agencies to receive concurrence with previously submitted route change modifications. RIGHT OF WAY â€¢ Ongoing cooperation with relevant Tribal Governments to obtain easements and Right-of-Way (ROW) approvals. â€¢ Ongoing negotiations with Bureau of Land Management, US Forest Service, and Bureau of Reclamation for issuance of ROW Grant/Notice to Proceed. | 66 | 145 | 0 | 0 | 66 | 0 | 0 | 1 | Network deployment time line altered due to progress pending approval of permits with utility providers. Additionally, the delay on the approval of final agreements with federal agencies and Tribes related to ROW and easements significantly affected the network deployment time line. | The total network miles to be leased during the entirety of the project are 756 miles. This represents 145 IRU miles and 611 restricted lit service miles. | N/A | N/A | Network deployment time line altered due to progress pending approval of permits with utility providers. Additionally, the delay on the approval of final agreements with federal agencies and Tribes related to ROW and easements significantly affected the network project time line. | N/A | N/A | Network deployment time line altered due to progress pending approval of permits with utility providers. Additionally, the delay on the approval of final agreements with federal agencies and Tribes related to ROW and easements significantly affected the network project time line. | 1 | 4 | 12 | Mason Valley QuickNet | Dedicated Internet Access Ethernet Transport *See pricing attachment | â€¢ Manage completion of an Environmental Assessment, and seek to secure the appropriate approvals resulting from such assessment. â€¢ Develop policies and procedures needed to secure appropriate permits. â€¢ Provide Final Engineering and Design. â€¢ Develop a working budget to complete the Network design, engineering, operation, maintenance, and Quality of Service standards needed to ensure sustainability. â€¢ Formulate Construction Management specifications. â€¢ Conduct Contractor evaluation and selection. â€¢ Complete Demand/Marketing Studies for Network growth and use; obtain appropriate letters of interest and commitment from Member Hospitals, ancillary facilities, last mile service providers, and other related anchor institutions. â€¢ Review, and where necessary, recalculate the network budget. â€¢ Incorporate leased or Indefeasible Right of Use facilities into overall Network design and pursue agreements with dark fiber providers and wholesale rates for lit services. â€¢ Construction Oversight. â€¢ Development of product and service definitions focused on initial set of services to be available at network launch, future tiered service offerings, and competitive market pricing review. e-Care Contact Information: 10100 W. Charleston Blvd. Suite 160 Las Vegas, NV 89135 | 1 | 0 | 0 | 0 | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | No activity this quarter. | 0 | 0 | 0 | 0 | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | No activity this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | No activity this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N//A | N/A | Ethernet Transport Dedicated Internet Access (DIA) Point-to-Point Ethernet Private Line IRU | FALSE | N/A | In the fourth quarter of the third year of the Nevada Broadband Telemedicine Initiative (NBTI) Award Period 2Q13, our organization plans to complete the following: ADMINISTRATIVE â€¢ Continuous participation in regular calls with subrecipient, engineering and construction subcontractors to ensure project progress. â€¢ Conduct meeting/conference calls with Nevada Hospital Association (NHA) Broadband Oversight Committee and General Membership consisting of hospital representatives. â€¢ Continuous review of project plans, agreements and status with Federal Program Officer. PROJECT DEPLOYMENT â€¢ Continuous network construction and fiber installation. â€¢ Construction of the Carson City Metro Ring is scheduled to begin early April 2013. ENGINEERING â€¢ Ongoing fiber installation. â€¢ Approval of permits related to fiber installation. â€¢ Finalization of routes included in Award Action Requests to address numerous changes in routes and design identified since the project redesign described in AAR#2 approved in January 2013. â€¢ Start of construction for the Las Vegas to Pahrump and Yerington to Hawthorne segments. â€¢ Completion of equipment installation by end of April 2013 in Carson City, Silver Springs, and Yerington POP sites. This represents three out of five POP sites on the network. There are 5 regenerator/shelter site locations where work is scheduled to start pending approval of the Bureau of Land Management (BLM) Right-of-Way (ROW). â€¢ Continuous updating of the Nevada Energy Distribution Pole Permit Tracker and AT&T Permit Tracking Log. KEY PROJECT INDICATOR PROJECTIONS â€¢ New network miles deployed: Estimated 35.37 miles (Carsom City Metro Ring - 9.37 miles and 1/2 of Las Vegas to Pahrump - 26 miles) â€¢ New network miles leased: 0 â€¢ Total CAI subscribers served (CAIs connected): 0 â€¢ Number of signed agreements with broadband wholesalers or last mile providers:2 OUTREACH/SUSTAINABILTY â€¢ Continued to request execution of Master Service Agreements, Service Orders, and Letters of Commitment with grant-named hospitals. â€¢ Participated in Connect Nevada meetings in counties throughout the State promoting economic development impact from the network. â€¢ Continued review of pricing structure and service definitions for member hospitals and Community Anchor Institutions (CAIs). â€¢ Identified and pursuing significant Department of Defense opportunity at Creech Air Force Base in Indian Springs, NV. â€¢ Identified and pursuing significant wireless backhaul opportunities in Beatty and Pahrump. â€¢ Conducted meetings with CAIs in the funded service areas to pre-sell services and identify member hospital network needs and requirements. â€¢ Ongoing discussion regarding collaboration with HealtHIE Nevada and Department of Health and Human Services State HIE. â€¢ Continued research and analysis into other potential state, federal and private funding initiatives. â€¢ Conducted multiple meetings/conference calls with Nevada Hospital Association (NHA) Broadband Oversight Committee consisting of hospital representatives. â€¢ Attended Community Outreach meetings to discuss project status updates and collaboration opportunities with incumbent service providers and other Broadband Initiatives Program / Broadband Technology Opportunity Program (BTOP) awardees. â€¢ Investigation of alternatives methods of serving I-80 corridor. FINANCE/GRANT COMPLIANCE/REPORTING â€¢ Submit American Recovery and Reinvestment Report, Federal Financial Report, and quarterly and annual Performance Progress Report for quarter ending March 31, 2013 per Special Award Conditions. â€¢ Anticipating approval of necessary Award Action Request related to numerous changes in routes and design modifications identified since the project redesign described in AAR#2 approved in January 2013. â€¢ Participate in Broadband Technology Opportunities Program webinars and drop-in calls. â€¢ Conduct Subrecipient Monitoring Site Visit for review of Grants Files, award requirements, and federal guidelines/compliance. â€¢ Continuous financial/budget vendor monitoring meeting. ENVIRONMENTAL ASSESSMENT â€¢ Anticipating approval of ROW authorization from U.S. Forest Service (USFS). â€¢ Anticipating approval of easements for private land owners. â€¢ Anticipating identification and approval of the Bureau of Reclamation ROW. â€¢ Anticipating approval of Notice to Proceed authorization from Bureau of Land Management. â€¢ Anticipating approval of ROW from Walker River Paiute Tribe and final application submittal to Bureau of Indian Affairs. â€¢ Anticipating approval of Grant of Easement from BIA for Yerington Paiute Tribe. â€¢ Anticipating letter from U.S. Fish and Wildlife Service (USFWS) for AAR#4 by the end of April 2013. â€¢ Working with NTIA and State Historic Preservation Office for concurrence with Cultural Resources Report for AAR #4. | Nevada Hospital Association | The Nevada Hospital Association (NHA) encountered challenges in acquiring permits from utility providers related to fiber installation and numerous changes in routes and design (route modifications). Additionally, a delay on approval of final agreements with federal agencies and Tribes related to Right-of-Way and easements altered the project time line. NHA is actively working through these matters with the relevant agencies to meet substantial project completion time lines. | In the second quarter of the third year of the NBTI (2Q13), the potential challenge that NHA may encounter is acquiring easement from Tribes. NHA will continue consulting with BTOP Program Officer as issues arises. | TRUE
NT10BIX5570103 | 2013 | Q2 | Q2 - 2013 | In the fourth quarter of the third year of the Nevada Broadband Telemedicine Initiative (NBTI) Award Period (2Q13), our organization completed the following: ADMINISTRATIVE â€¢ Continuous consultation with the National Telecommunications and Information Administration (NTIA) Federal Program Officer (FPO) to update project status and ensure federal grant program compliance â€¢ Conducted regular project status and review meetings with project participants to ensure progress â€¢ Submission of quarterly reporting for local jurisdiction and state agencies related to licensing and taxation compliance â€¢ Worked with NTIA on a no cost extension â€¢Hired consultant to assist with Invitation to Negotiate â€¢Sought new investor/sub-recipient PROJECT DEPLOYMENT â€¢ 47,402 LF of cable placed in the Carson City Metro Ring â€¢ Civil construction is complete for the Carson City, Silver Springs and Yerington POP sites ENGINEERING â€¢ Ongoing collaboration between Nevada Hospital Association (NHA) and its Contractor on the Award Action Request (AAR) #4 to address numerous changes in routes and design identified since the project redesign described in AAR#2 approved in January 2013 â€¢ Route development, engineering design, permitting, and materials procurement for southern Nevada routes are completed except for the Mona substation to Boulder City Hospital. Valley Electric Association (VEA) review of the proposed design is on hold until grant funds are released â€¢ Route development, engineering design, permitting and materials procurement for northern Nevada routes are ongoing to resolve issues with make-ready with NV Energy. New engineering designs are on hold until grant funds are available. â€¢ Re-evaluation of current Community Anchor Institutions (CAIs) to identify new CAIs and replace CAIs that are no longer interested in acquiring services from the network â€¢ Many lateral designs are on hold pending a review of the CAIs â€¢ Ongoing fiber installation: The network construction from Reno to Carson City â€“ Silver Springs route segments are approximately 99.9% complete. The cable installation for the Carson City Ring is complete; only testing and acceptance of the fiber optic cable remains to complete these segments. â€¢ The ISP installation in Carson City, Silver Springs and Yerington POP sites is 80% complete. The completion of the equipment installation is waiting on additional material to arrive that is on hold until grant funds are available. This represents three out of five POP sites on the network â€¢ Ongoing approval of permits from utility providers related to fiber installation â€¢ Ongoing Outside Plant (OSP) engineering surveys on routes that require a re-design due to issues with easements or lack of structural integrity of pole lines. Design for Inside Plant (ISP) has been completed â€¢ Received orders for OSP and ISP materials and equipment required to meet the current construction schedule â€¢ Selection of subcontractors for aerial cable installation and splicing for all segments between Silver Springs to Las Vegas (SNAP), from Arden to Amargosa, Henderson and the Carson City Metro Ring has been completed. Construction of the network from Silver Springs to Yerington, Yerington to Hawthorne, Hawthorne to Mina, Mina to Tonopah and Tonopah to Goldfield is on hold pending pole license approval from NV Energy. Construction of the network from Lida Junction to Beatty, Beatty to Valley Switch, Valley Switch to Pahrump and Pahrump to SNAP is on hold pending pole license approve from VEA. â€¢Updated the NV Energy Distribution Pole Permit Tracker and AT&T Permit Tracking Log. The process to complete pole licenses is on hold pending design of new routes due to excessive make-ready costs submitted by NV Energy. Re-routes have been selected and the design process is on hold pending availability of grant funding. OUTREACH/SUSTAINABILITY â€¢Continuous review of pricing structure and service definitions for member hospitals and CAIs â€¢Identified and pursuing significant Department of Defense opportunities at Creech Air Force Base in Indian Springs, NV â€¢Identified and pursuing significant wireless backhaul opportunity covering all of I-80, US-50 and US-95 between Reno and Tonopah â€¢Conducted meetings with CAIs in the funded service areas to pre-sell services and identify member hospital network needs and requirements â€¢Ongoing discussion regarding collaboration with HealtHIE Nevada and Department of Health and Human Services State HIE â€¢Conducted meetings with the Nevada Department of Transportation, Nevada System of Higher Education and Nevada Information Technology Service Division â€¢Continued research and analysis into other potential state, federal and private funding initiatives â€¢Conducted multiple meetings/conference calls with members of the NHA Broadband Oversight Committee and NHA Membership consisting of hospital representatives â€¢Attended Community Outreach meetings to discuss project status updates and collaboration opportunities with incumbent service providers and other Broadband Initiatives Program / Broadband Technology Opportunity Program (BTOP) awardees â€¢Investigation of alternative methods of serving I-80 corridor FINANCE/GRANT COMPLIANCE/REPORTING â€¢ American Recovery and Reinvestment Act, Federal Financial Report, and Quarterly and Annual Performance Progress Report Federal Reporting submitted for period ending March 30, 2013 â€¢ Attended BTOP drop in calls and webinars ENVIRONMENTAL ASSESSMENT â€¢ Continuous consultation with federal and state agencies â€¢ Coordinated with relevant tribal entities and state/federal agencies to receive concurrence with previously submitted route change modifications â€¢ Received Notice to Proceed on Phase One of Three from BLM RIGHTS OF WAY â€¢ Ongoing cooperation with relevant Tribal Governments to obtain easements and Rights of Way (ROW) approvals â€¢ Ongoing negotiations with Bureau of Land Management, US Forest Service | 75 | 145 | 0 | 0 | 75 | 0 | 0 | 1 | Network deployment time line altered due to progress pending approval of permits with utility providers. Additionally, the delay on the approval of final agreements with Federal agencies and Tribal entities related to ROW and easements significantly affected the network project time line. | This represents the total miles to be leased during the entirety of the project. There are no other leased fibers that are planned for the grant network installation. | N/A | N/A | Network deployment time line altered due to progress pending approval of permits with utility providers. Additionally, the delay on the approval of final agreements with Federal agencies and Tribal entities related to ROW and easements significantly affected the network project time line. | N/A | N/A | Network deployment time line altered due to progress pending approval of permits with utility providers. Additionally, the delay on the approval of final agreements with Federal agencies and Tribal entities related to ROW and easements significantly affected the network project time line. | 1 | 0 | 12 | Mason Valley QuickNet | Dedicated Internet Access Ethernet Transport *See pricing attachment | â€¢ Manage completion of an Environmental Assessment, and seek to secure the appropriate approvals resulting from such assessment. â€¢ Develop policies and procedures needed to secure appropriate permits. â€¢ Provide final engineering and design. â€¢ Develop a working budget to complete the Network design, engineering, operation, maintenance, and Quality of Service standards needed to ensure sustainability. â€¢ Formulate Construction Management specifications. â€¢ Conduct Contractor evaluation and selection. â€¢ Complete Demand/Marketing Studies for Network growth and use; obtain appropriate letters of interest and commitment from Member Hospitals, ancillary facilities, last mile service providers, and other related anchor institutions. â€¢ Review, and where necessary, recalculate the network budget. â€¢ Incorporate leased or Indefeasible Right of Use facilities into overall Network design and pursue agreements with dark fiber providers and wholesale rates for lit services. â€¢ Construction Oversight. â€¢ Development of product and service definitions focused on initial set of services to be available at network launch, future tiered service offerings, and competitive market pricing review. e-Care Nevada Contact Information: 10855 West Dodge Road Suite 180 Omaha, NE 68154 | 1 | 0 | 0 | 0 | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | No activity this quarter. | 0 | 0 | 0 | 0 | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | No activity this quarter. | 0 | 0 | 0 | 0 | 0 | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | Variance from Baseline Plan due to ongoing network deployment. | No activity this quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Ethernet Transport Dedicated Internet Access (DIA) Point-to-Point Ethernet Private Line IRU | FALSE | N/A | In the first quarter of the fourth year of the Nevada Broadband Telemedicine Initiative (NBTI) Award Period 3Q13, our organization plans to complete the following: ADMINISTRATIVE â€¢ Finalize agreement with new subrecipient to provide additional funding to complete the project following release of Invitation to Negotiate. â€¢ Continuous coordination with subrecipient, engineering and construction subcontractors to ensure project progress. â€¢ Conduct meeting/conference calls with Nevada Hospital Association (NHA) Broadband Oversight Committee and NHA Membership consisting of hospital representatives. â€¢ Continuous review of project plans, agreements and status with Federal Program Officer. PROJECT DEPLOYMENT â€¢ The number of miles we plan to deploy next quarter is zero due to project funding delays. Anticipate deployment no sooner than October 2013. â€¢ No CAIs connected by the end of the next quarter due to project funding delays. â€¢ There are 5 regenerator/shelter site locations where work is scheduled to start pending approval of the Bureau of Land Management (BLM) Rights of Way (ROW). â€¢ Conduct bidding to select subcontractors for the fiber optic cable installation for the Carson City - Gardnerville and Goldfield - Lida Junction segments once grant funding is available. â€¢ Completion of fiber test and acceptance in Reno â€“ Carson City â€“ Silver Springs and Carson City Metro Ring route segments. ENGINEERING â€¢ Start of construction for the Las Vegas to Pahrump and Yerington to Hawthorne segments. OUTREACH/SUSTAINABILTY â€¢ Estimate the number of broadband wholesaler/last mile provider agreements we plan to sign through the end of next quarter is 0-2. â€¢ Continued requests for executed Service Orders from NHA member hospitals. â€¢ Continuous marketing to CAIs to maximize participation and set foundation for economic sustainability. â€¢ Participate in Connect Nevada meetings throughout the State promoting the network. â€¢ Continued review of pricing structure and service definitions. â€¢ Pursuing Department of Defense opportunities at Creech Air Force Base. â€¢ Pursuing wireless backhaul opportunities. â€¢ Continued meetings with State of Nevada agencies interested in use of the network. â€¢ Continued research and analysis into other potential state, federal, and private funding initiatives. â€¢ Conduct multiple meetings with NHA & NHA Broadband Oversight Committee. â€¢ Attend Community Outreach meetings. â€¢ Investigation of alternative methods of serving I-80 and US-50 corridors. FINANCE/GRANT COMPLIANCE/REPORTING â€¢ Submit American Recovery and Reinvestment Report, Federal Financial Report, and quarterly and annual Performance Progress Report for quarter ending June 30, 2013 per Special Award Conditions. â€¢ Anticipating approval of necessary Award Action Request (AAR) related to numerous changes in routes and design modifications identified since the project redesign described in AAR#2 approved in January 2013. â€¢ Participate in Broadband Technology Opportunities Program webinars and drop-in calls. â€¢ Conduct Subrecipient Monitoring Site Visit for review of grants files, award requirements, and federal guidelines/compliance. â€¢ Continuous financial/budget vendor monitoring meeting. ENVIRONMENTAL ASSESSMENT â€¢ Anticipating approval of ROW authorization from U.S. Forest Service for AAR#4. â€¢ Anticipating approval of easements for private land owners. â€¢ Anticipating identification and approval of the Bureau of Reclamation ROW for AAR#4. â€¢ Anticipating approval of Notice to Proceed authorization for Phases Two and Three from BLM. â€¢ Anticipating approval of ROW and Grant of Easement from Walker River Paiute Tribe and final application submittal to Bureau of Indian Affairs. â€¢ Working with National Telecommunications and Information Administration and the State Historic Preservation Office for concurrence with Cultural Resources Report for AAR#4. | Nevada Hospital Association | The Nevada Hospital Association encountered challenges in acquiring permits from utility providers related to fiber installation and numerous changes in routes and design (route modifications). Additionally, a delay on approval of final agreements with Federal agencies and Tribes related to Rights-of-Way and easements altered the project time line. NHA is actively working through these matters with the relevant agencies. | NHA is requesting a no-cost extension to September 30, 2014. This extension is necessitated by extended environmental reviews, delayed issuance of pole permits, delays in receiving Bureau of Land Management permits, remaining right-of-way access issues as well as the request by e-Care Nevada to withdraw as the subrecipient. | TRUE
NT10BIX5570103 | 2013 | Q3 | Q3 - 2013 | In the first quarter of the fourth year of the Nevada Broadband Telemedicine Initiative (NBTI) Award Period (3Q13), our organization completed the following: ADMINISTRATIVE â€¢ Submission to National Telecommunications and Information Administration (NTIA) and approval of a No-Cost Extension to continue the successful implementation of our Broadband Technology Opportunities Program (BTOP) award â€¢ Continuous consultation with the NTIA Federal Program Officer (FPO) and meeting with NTIA to update project status and ensure federal grant program compliance â€¢ Continuous consultation with vendor on Invitation to Negotiate â€¢ Worked with subrecipient on Letter of Intent to complete the project before September 30, 2014 â€¢ Conducted regular project status and review meetings with project participants to ensure progress â€¢ Submission of quarterly reporting for local jurisdiction and state agencies related to licensing and taxation compliance â€¢ Conducted regular finance/budget vendor monitoring meeting PROJECT DEPLOYMENT No deployment occurred this quarter ENGINEERING â€¢ Ongoing collaboration between the Nevada Hospital Association (NHA), subrecipient, and its vendor on the Award Action Request (AAR) #4 to address numerous changes in routes and design identified since the project redesign described in AAR#2 approved in January 2013 â€¢ Route development, engineering design, permitting, and materials procurement for all Nevada routes are on hold until revised Corrective Action Plan response is review and approved along with AAR4 â€¢ Re-evaluation of the current Community Anchor Institutions (CAI) list to identify new CAIs and replace CAIs that no longer interested in acquiring services from the network â€¢ The completion of the equipment installation is waiting on additional material to arrive which is on hold until grant funds are available â€¢ Ongoing approval of permits from utility providers related to fiber installation â€¢ Ongoing Outside Plant (OSP) engineering surveys on routes that require a re-design due to issues with easements or lack of structural integrity of pole lines. Design for Inside Plant (ISP) has been completed â€¢ Received orders for OSP and ISP materials and equipment required to meet the current construction schedule â€¢ Selection of subcontractors for aerial cable installation and splicing for all segments between Silver Springs to Las Vegas (SNAP), from Arden to Amargosa, Henderson and the Carson City Metro Ring has been completed. Construction of the network from Silver Springs to Yerington, Yerington to Hawthorne, Hawthorne to Mina, Mina to Tonopah and Tonopah to Goldfield is on hold pending pole license approval from NV Energy. Construction of the network from Lida Junction to Beatty, Beatty to Valley Switch, Valley Switch to Pahrump and Pahrump to SNAP is on hold pending pole license approve from Valley Electric Association. â€¢ The Nevada Energy Distribution Pole Permit Tracker and AT&T Permit Tracking Log are up to date. The process to complete pole licenses is on hold pending design of new routes due to excessive make-ready costs submitted by NV Energy. Re-routes have been selected and the design process is on hold pending availability of grant funding. OUTREACH/SUSTAINABILITY â€¢Continuous review of pricing structure and service definitions for member hospitals and CAIs â€¢Identified and pursuing significant Department of Defense opportunities at Creech Air Force Base in Indian Springs, NV â€¢Identified and pursuing significant wireless backhaul opportunity covering all of I-80, US-50 and US-95 between Reno and Tonopah â€¢Conducted meetings with CAIs in the funded service areas to pre-sell services and identify member hospital network needs and requirements â€¢ Ongoing discussion regarding collaboration with the HealtHIE Nevada and Department of Health and Human Services State HIE â€¢Continued research and analysis into other potential state, federal and private funding initiatives â€¢Conducted meeting/conference calls with members of the NHA Broadband Oversight Committee and NHA Membership consisting of hospital representatives â€¢Attended Community Outreach meetings to discuss project status updates and collaboration opportunities with incumbent service providers and other Broadband Initiatives Program / BTOP awardees â€¢Investigation of alternative methods of serving I-80 corridor FINANCE/GRANT COMPLIANCE/REPORTING â€¢ American Recovery and Reinvestment Act, Federal Financial Report, and Quarterly and Annual Performance Progress Report federal reporting submitted for period ending June 30, 2013 â€¢ Conducted various financial/budget monitoring meetings ENVIRONMENTAL ASSESSMENT â€¢ Continuous consultation with federal and state agencies â€¢ Coordinated with relevant tribal entities and state/federal agencies to receive concurrence with previously submitted route change modifications â€¢ Worked with BLM to complete Phase 2 and 3 for the Right of Way Grant RIGHT OF WAY (ROW) â€¢ Ongoing cooperation with relevant Tribal Governments to obtain easements and ROW approvals â€¢ Ongoing negotiations with Bureau of Land Management, Nevada State Lands, US Forest Service, and Bureau of Reclamation for issuance of ROW Grant/Notice to Proceed | 75 | 145 | 0 | 0 | 75 | 0 | 0 | 1 | Network deployment timeline altered due to progress pending approval of permits with utility providers as well as the delay on approval of final agreements with federal agencies and tribal entities related to ROW and easements | This represents the total miles to be leased during the entirety of the project. There are no other leased fibers that are planned for the grant network installation. | N/A | N/A | Network deployment timeline altered due to progress pending approval of permits with utility providers as well as the delay on approval of final agreements with federal agencies and tribal entities related to ROW and easements | N/A | N/A | Network deployment timeline altered due to progress pending approval of permits with utility providers as well as the delay on approval of final agreements with federal agencies and tribal entities related to ROW and easements | 1 | 0 | 12 | Mason Valley QuickNet | Dedicated Internet Access Ethernet Transport *See pricing attachment | â€¢ Manage completion of an Environmental Assessment, and seek to secure the appropriate approvals resulting from such assessment. â€¢ Develop policies and procedures needed to secure appropriate permits â€¢ Provide final engineering and design â€¢ Develop a working budget to complete the Network design, engineering, operation, maintenance, and Quality of Service standards needed to ensure sustainability â€¢ Formulate Construction Management specifications â€¢ Conduct Contractor evaluation and selection â€¢ Complete Demand/Marketing Studies for Network growth and use; obtain appropriate letters of interest and commitment from Member Hospitals, ancillary facilities, last mile service providers, and other related anchor institutions â€¢ Review, and where necessary, recalculate the network budget â€¢ Incorporate leased or Indefeasible Right of Use facilities into overall Network design and pursue agreements with dark fiber providers and wholesale rates for lit services â€¢ Construction Oversight â€¢ Development of product and service definitions focused on initial set of services to be available at network launch, future tiered service offerings, and competitive market pricing review e-Care Nevada Contact Information: 10855 West Dodge Road Suite 180 Omaha, NE 68154 | 1 | 0 | 0 | 0 | Variance From Baseline Plan due to ongoing network deployment. | Variance From Baseline Plan due to ongoing network deployment. | Variance From Baseline Plan due to ongoing network deployment. | No activity this quarter | 0 | 0 | 0 | 0 | Variance From Baseline Plan due to ongoing network deployment. | Variance From Baseline Plan due to ongoing network deployment. | Variance From Baseline Plan due to ongoing network deployment. | No activity this quarter | 0 | 0 | 0 | 0 | 0 | Variance From Baseline Plan due to ongoing network deployment. | Variance From Baseline Plan due to ongoing network deployment. | Variance From Baseline Plan due to ongoing network deployment. | Variance From Baseline Plan due to ongoing network deployment. | No activity this quarter | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Ethernet Transport Dedicated Internet Access (DIA) Point-to-Point Ethernet Private Line IRU | FALSE | N/A | In the first quarter of the fourth year of the Nevada Broadband Telemedicine Initiative (NBTI) Award Period 3Q13, our organization plans to complete the following: ADMINISTRATIVE â€¢ Continuous coordination with subrecipient, engineering and construction subcontractors to ensure project progress â€¢ Conduct meeting/conference calls with Nevada Hospital Association (NHA) Broadband Oversight Committee and NHA Membership consisting of hospital representatives â€¢ Continuous review of project plans, agreements and status with Federal Program Officer â€¢ Subrecipient plans to move office location to Reno area PROJECT DEPLOYMENT â€¢ The number of miles we plan to deploy next quarter is zero due to project funding delays. Anticipate deployment no sooner than January 2014 â€¢ No CAIs connected by the end of the next quarter due to project funding delays â€¢ Network construction, permit acquisition, and engineering will resume upon federal approval â€¢ There are 5 regenerator/shelter site locations where work is scheduled to start pending approval of the Bureau of Land Management (BLM) Right of Way (ROW) and upon federal approval â€¢ Conduct bidding to select subcontractors for the fiber optic cable installation for the Goldfield - Lida Junction segments once grant funding is available â€¢ Completion of fiber test and acceptance in Reno â€“ Carson City â€“ Silver Springs and Carson City Metro Ring route segments ENGINEERING â€¢ Complete pole licensing in preparation for the Las Vegas to Pahrump and Yerington to Hawthorne segment construction for the next quarter OUTREACH/SUSTAINABILTY â€¢ Estimate the number of broadband wholesaler/last mile provider agreements we plan to sign through the end of next quarter is 0-2 â€¢ Continued requests for executed Service Orders from NHA member hospitals â€¢ Continuous marketing to CAIs to maximize participation and set foundation for economic sustainability â€¢ Participate in Connect Nevada / Nevada Broadband Task Force meetings throughout the State promoting the network â€¢ Continued review of pricing structure and service definitions â€¢ Pursuing Department of Defense opportunities along US-50 â€¢ Pursuing backhaul opportunities â€¢ Ongoing discussion with HealtHIE Nevada and Department of Health and Human Services State HIE â€¢ Continued research and analysis into other potential state, federal, and private funding initiatives â€¢ Conduct multiple meetings with NHA & NHA Broadband Oversight Committee â€¢ Attend Community Outreach meetings â€¢ Investigation of alternative methods of serving I-80 and US-50 corridors FINANCE/GRANT COMPLIANCE/REPORTING â€¢ Submit American Recovery and Reinvestment Report, Federal Financial Report, and quarterly and annual Performance Progress Report for quarter ending September 30, 2013 per Special Award Conditions â€¢ Anticipating approval of necessary Award Action Request related to numerous changes in routes and design modifications identified since the project redesign described in AAR#2 approved in January 2013 â€¢ Once AAR#4 is approved all backup support and budget will be adjusted accordingly â€¢ Participate in Broadband Technology Opportunities Program webinars and drop-in calls â€¢ Conduct Subrecipient Monitoring Site Visit for review of Grants Files, award requirements, and federal guidelines/compliance â€¢ Continuous financial/budget vendor monitoring meeting â€¢ Conduct asset audit - ENVIRONMENTAL ASSESSMENT â€¢ Pursuing final approval of ROW authorization from U.S. Forest Service (USFS) for AAR#4 â€¢ Pursuing final approval of easements for private land owners â€¢ Anticipating identification and approval of the Bureau of Reclamation ROW for AAR#4 â€¢ Anticipating approval of Notice to Proceed authorization for Phase Three from Bureau of Land Management â€¢ Anticipating approval of ROW and Grant of Easement from Walker River Paiute Tribe and final application submittal to Bureau of Indian Affairs â€¢ Working with NTIA and SHPO for concurrence with Cultural Resources Report for AAR#4 | Nevada Hospital Association | The Nevada Hospital Association (NHA) encountered challenges in acquiring permits from utility providers related to fiber installation and numerous changes in routes and design (route modifications). Additionally, a delay on approval of final agreements with Federal agencies and tribes related to Rights of Way and easements altered the project timeline. NHA is actively working through these matters with the relevant agencies. NHA negotiated a Letter of Intent with its subrecipient, e-Care Nevada, to complete the project. Upon approval by the National Telecommunications and Information Administration (NTIA), construction of the network can resume with completion expected before September 2014. | In order to meet planned milestones, NHA will need approval by NTIA to resume construction of the network with completion expected before September 2014. | TRUE
NT10BIX5570103 | 2013 | Q4 | Q4 - 2013 | Network deployment * Established project metrics and benchmarks needed to move project forward * Completed NTIA required Network Operator Whitepaper * Completed detailed CAP Response including new budgets, routes, management team and CAI list * Worked on new Agreements/ new business relationship * Restructured project management team to become more efficient * Laid groundwork to move project forward with NV Energy * Conducted audit of federal asset inventory resulting in no finding variances Outreach * Continuous contact with CAIs and last mile providers to maintain interest in network participation and to keep CAIs aware of project status | 75 | 145 | 0 | 0 | 75 | 0 | 0 | 1 | Network deployment timeline altered due to progress pending approval of permits with utility providers as well as the delay on approval of final agreements with federal agencies and tribal entities related to ROW and easements | This represents the total miles to be leased during the entirety of the project. There are no other leased fibers that are planned for the grant network installation. | N/A | N/A | Network deployment timeline altered due to progress pending approval of permits with utility providers as well as the delay on approval of final agreements with federal agencies and tribal entities related to ROW and easements | N/A | N/A | Network deployment timeline altered due to progress pending approval of permits with utility providers as well as the delay on approval of final agreements with federal agencies and tribal entities related to ROW and easements | 1 | 0 | 12 | Mason Valley QuickNet | Dedicated Internet Access Ethernet Transport * See pricing attachment | â€¢ Manage completion of an Environmental Assessment, and seek to secure the appropriate approvals resulting from such assessment. â€¢ Develop policies and procedures needed to secure appropriate permits â€¢ Provide final engineering and design â€¢ Develop a working budget to complete the Network design, engineering, operation, maintenance, and Quality of Service standards needed to ensure sustainability â€¢ Formulate Construction Management specifications â€¢ Conduct Contractor evaluation and selection â€¢ Complete Demand/Marketing Studies for Network growth and use; obtain appropriate letters of interest and commitment from Member Hospitals, ancillary facilities, last mile service providers, and other related anchor institutions â€¢ Review, and where necessary, recalculate the network budget â€¢ Incorporate leased or Indefeasible Right of Use facilities into overall Network design and pursue agreements with dark fiber providers and wholesale rates for lit services â€¢ Construction Oversight â€¢ Development of product and service definitions focused on initial set of services to be available at network launch, future tiered service offerings, and competitive market pricing review e-Care Nevada Contact Information: 10855 West Dodge Road Suite 180 Omaha, NE 68154 | 1 | 0 | 0 | 0 | Variance From Baseline Plan due to ongoing network deployment | Variance From Baseline Plan due to ongoing network deployment | Variance From Baseline Plan due to ongoing network deployment | No activity this quarter | 0 | 0 | 0 | 0 | Variance From Baseline Plan due to ongoing network deployment | Variance From Baseline Plan due to ongoing network deployment | Variance From Baseline Plan due to ongoing network deployment | No activity this quarter | 0 | 0 | 0 | 0 | 0 | Variance From Baseline Plan due to ongoing network deployment | Variance From Baseline Plan due to ongoing network deployment | Variance From Baseline Plan due to ongoing network deployment | Variance From Baseline Plan due to ongoing network deployment | No activity this quarter | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Ethernet Transport Dedicated Internet Access (DIA) Point-to-Point Ethernet Private Line IRU | FALSE | N/A | Network Deployment * Execute new Network Management Agreement, Sub recipient Agreement, and six IRU Agreements between NHA and e-Care * Complete response to CAP questions and gain NTIA approval * Complete license application filings with NV Energy and Valley Electric Association * Begin Network construction of two network segments and one CAI lateral * Secure easements and licenses enabling constriction on Nevada State Lands property * Submit AAR#4 with a revised project budget * Submit AAR#5 for a Route Modification Request *Estimated number of miles to deploy next quarter- 0 *Estimated CAI's planned to be connected by next quarter-0 *Estimated number of broadband wholesaler/last mile provider agreements to be signed next quarter-0 Outreach * Continuous contact with CAIs and last-mile providers to maintain interest in network participation and to keep CAIs aware of project status * Participate in Community Outreach meetings to promote and maintain interest in the project * Complete interconnection design and pricing for Nevada Department of Correction locations in Lovelock, Ely and Indian Springs KPI targets through the end of the project *New network miles deployed- 544.2 *New network miles leased-0 *Existing network miles upgraded-608 *Existing network miles leased-144.88 | Nevada Hospital Association | CAP approval, negotiation of complete set of new management agreements between NHA and e-Care were issues that provided a challenge to achieving planned progress in the past quarter. | N/A | TRUE
NT10BIX5570104 | 2010 | Q4 | Q4 - 2010 | A detailed map of the fiber route including potential Community Anchor Instisution's for the project was developed. A firm was hired to assist with the Environmental Assessment. Received letter from the United States Fish and Wildlife service that our project would not likely adversely affect the surroundings. Negotiations for new collocation space in Jackson, MS also occurred. A Computer Aided Drafting department was created and three new employees were hired along with an outside construction project manager. Baseline reports were submitted and finalized. Vendor meetings were held to evaluate equipment, fiber management software etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance from baseline | No Variance from baseline | No Variance from baseline | No Variance from baseline | No Variance from baseline | N/A | N/A | No Variance from baseline | 0 | 2 | 0 | not applicable, construction not started | not applicable, construction not started | N/A | 0 | 0 | 0 | 0 | No Variance from baseline | No Variance from baseline | No Variance from baseline | No Variance from baseline | 0 | 0 | 0 | 0 | No Variance from baseline | No Variance from baseline | No Variance from baseline | No Variance from baseline | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Receipt of FONSI. Release and award of construction RFP(s). Beginning of construction. | Contact Network Inc. d/b/a InLine | The environmental assessment process has used resources that would have used to design network, obtain rights of ways and permits, as well as, issue requests for proposal's for procurement and construction. Reassignment of these resources to tackle issues within the environmental assessment has caused variance in the initial baseline figures. In addition, inconsistent instructions and/or changes/clarification on required forms for reporting has used internal resources that typically would be used to process rights of way, obtain permits etc. We need the ability to make decisions on our own or have National Telecommunications and Information Administration respond in a more timely fashion (i.e: Fiber Strand Miles in the Annual Progress Performance Reports). | If Finding Of No Significant Impact is not received further delays are expected in permitting, rights of way etc. Also, if changes are necessary and requested, delayed responses from National Telecommunications and Information Administration could also impact the planned progress above. | TRUE
NT10BIX5570104 | 2011 | Q1 | Q1 - 2011 | During this quarter, the Environmental Assessment was finalized and a draft submitted. Meetings were held with the Mississippi State Historic Preservation Officer to determine guidelines for construction in areas were archaeological sites exists. A plan was agreed upon and approval was sent to the National Telecommunication and Information Administration along with our final Environmental Assessment. In anticipation of receiving our Finding of No Significant Impact, we began riding all routes and submitting applications to attach to utility poles in the initial build counties. One administrative person was hired to process pole attachment agreements. Meetings were held with the Electric Power Associations involved and pole attachment agreements with the Electric Power Associations were negotiated. Construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Army Corp of Engineer and Railroad permitting also began during this quarter. Collocation space in Jackson, Mississippi was procured. The overlap special award condition was satisfied. Face to face meetings were held with potential Community Anchor Institutions. A total of seven district contracts were won which will connect forty seven Anchor Institutions by July 1, 2011. Three request for proposals were released during this quarter for: fiber and materials, huts and aerial/buria | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | N/A | N/A | No variance from baseline | 0 | 2 | 0 | N/A; currently we have no signed agreements | N/A; currently no wholesale services have yet to be provided. Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet; 100Mbps Private Network; 100Mbps Fiber Connection with Internet; 1000Mbps Private Networs have yet to be provided. Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet; 100Mbps Private Network; 100Mbps Fiber Connection with Internet; 1000Mbps Private Network | N/A | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline, we are currently in negotiation with a couple of providers but nothing has yet been signed. | No variance from baseline | 10Mbps/100Mbps/1000Mbps Private WAN; 10Mbps/100Mbps Fiber Connection with Internet | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | 10Mbps/100Mbps/1000Mbps Private WAN; 10Mbps/100Mbps Fiber Connection with Internet | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | During the next quarter we anticipate the receipt of our Environmental Assessment Finding of No Significant Impact. The fiber and materials RFP will be awarded and materials for construction will be purchased. Also, the construction RFP will be awarded. An RFP for equipment will be released, awarded and equipment will be purchased. Pole attachment agreements will be finalized. Pole attachment applications will be finalized. Railroad crossing permits will be secured. Army Corp of Engineers approval letters and/or permits will be received. Construction permits will be received. Contractors will begin construction on both aerial and burial components of our route. All forty-seven community anchor institutions for which contracts have been received will be connected during this quarter. | Contact Network Inc. d/b/a InLine | One of our competitors is creating doubt with our end userâ€™s regarding aerial fiber due to the recent tornados. Our customers are now requesting all fiber to be buried. The budget we submitted was based on an aerial/burial combination. | The tornados that came through our area on April 27, 2011 slowed the progress of our aerial pole attachment applications. The utility companies have pulled their crews to work on restoring services in the damaged areas instead of processing our new attachment requests. Likewise, the Mississippi River flooding is causing the same types of delays with both the utility companies and Rail Roads that are processing our Crossing Applications. | TRUE
NT10BIX5570104 | 2011 | Q2 | Q2 - 2011 | A response to the Environmental Assessment draft submitted in the prior quarter was received from the National Telecommunication and Information Administration along with a matrix of questions that needed to be addressed during this quarter. All questions were addressed and a final Environmental Assessment was sent. In mid April, we received the Finding of No Significant Impact from the National Telecommunication and Information Administration. All pole attachment applications were submitted to the various utility companies. Permits were submitted to and approved by the Mississippi Department of Transportation, Army Corp of Engineers, Railroad, and various city and county governments. The fiber and materials, huts and aerial/burial construction requests for proposals were awarded during this quarter. Purchases from these requests for proposals were made and construction began. A total of thirty seven Community Anchor Institutions were connected during this quarter. | 36 | 0 | 0 | 0 | 36 | 0 | 0 | 1 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | We are still negotiating the terms of the IRU and expect to have this finalized next quarter | No Variance from Baseline | No Variance from Baseline | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | 0 | 2 | 0 | Not applicable, currently we are still in negotiations and do not have any signed agreements in place. | N/A; currently no wholesale services have yet to be provided. Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 0 | 0 | 0 | 0 | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | No Variance from Baseline | 37 | 0 | 37 | 37 | We secured contracts with seven K-12 school districts which totaled forty seven Community Anchor Institutions. During this quarter we connected thirty-seven of the forty seven schools, which exceeds our baseline projections. | No Variance from Baseline | We secured contracts with seven K-12 school districts which totaled forty seven Community Anchor Institutions. During this quarter we connected thirty-seven of the forty seven schools, which exceeds our baseline projections. | Thirty Seven of the Community Anchor Institutions are receiving 1000Mpbs Private WAN Connections | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not Applicable | FALSE | Our network management practices have not changed. | Construction will continue to the ten anchor institutions that were not connected during last quarter. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. We will be issuing a request for proposals for hand holes. Additional fiber optic cable, markers etc. will be ordered. Franchise agreements will be negotiated in counties where our next build will take place and permits will be secured. Once permits/approvals are secured construction will continue. Our current IRU negotiations will also continue and be finalized during the next quarter. | Contact Network Inc. d/b/a InLine | We are still experiencing the same issues with one of our competitors creating doubt with our potential end users regarding aerial fiber due to the recent tornados. Our customers are continuing to request all buried fiber. | We are experience long lead times for delivery of our fiber optic cable. Also, the Electric Power Associations are overwhelmed due to the inclement weather and the volume of pole applications being filed. They cannot seem to produce the applications/approvals and complete any make ready needed in a timely fashion. We are also experiencing delays in aerial applications with the ILEC as well. | TRUE
NT10BIX5570104 | 2011 | Q3 | Q3 - 2011 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation, various City and County governments. A vault request for proposal was released and awarded. Additional fiber was ordered during this quarter. A total of 50 new miles of fiber was constructed and ten additional Community Anchor Institutions were connected. | 86 | 122 | 0 | 0 | 86 | 0 | 0 | 3 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline. | No variance from baseline. | No variance from baseline. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 0 | 2 | 0 | Not applicable, currently we are still in negotiations and do not have any signed agreements in place. | N/A; currently no wholesale services have yet to be provided. Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 47 | 0 | 47 | 47 | We secured contracts with seven K-12 school districts which totaled forty seven Community Anchor Institutions. During this quarter we finished connecting these forty seven schools, which exceeds our baseline projections. | No variance from baseline. | We secured contracts with seven K-12 school districts which totaled forty seven Community Anchor Institutions. During this quarter we finished connecting forty seven schools, which exceeds our baseline projections of twelve Community Anchor Institutions. | Forty-six of the Community Anchor Institutions are receiving 1000Mpbs Private WAN Connections; one is receiving a 10Mbps Private WAN Connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not Applicable | FALSE | Our network management practices have not changed. | We will continue to contact Community Anchor Institutions and present quotes/contracts for services. Discussions with our fiber vendors will continue to try to secure better lead times. Additional fiber optic cable, markers etc. will be ordered. Franchise agreements will be negotiated in counties where our next build will take place and permits will be secured. Once permits/approvals are secured construction will continue. Since we are ahead of schedule our primary focus during the next quarter will be on our grant in Central Mississippi. We do not plan connect any additional community anchor institutions nor deploy any additional network miles. The negotiations with broadband wholesales will also continue. No additional fiber is planned to be leased next quarter. | Contact Network Inc. d/b/a InLine | We are experiencing delays due to negotiations of Franchise Agreements with various cities and counties as well as with all the railroad crossing permits we submit. Also the cost of aerial build has dramatically increased - specifically the annual pole attachment fees and the one time make ready costs. The Electric Power Associations have changed the allocation space where communications are allowed to attach from 40 inches to 84 inches with is either causing us to have to pay for pole change outs or change the build to underground. Also, the K-12 schools are not freely allowing us to place the telecommunication huts for interconnection on their properties. | Long lead times for fiber delivery and hand holes are being received. | TRUE
NT10BIX5570104 | 2011 | Q4 | Q4 - 2011 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and county governments. A purchase order was issued for vaults against the request for proposals awarded last quarter. No new miles of fiber were constructed. Our focus was on securing permits and contracts this quarter. As of December 31, 2011 we have constructed 86 miles of new fiber, leased an additional 122 miles and are servicing a total of forty seven Community Anchor Institutions. | 86 | 122 | 0 | 0 | 86 | 0 | 0 | 3 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline. | No variance from baseline. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline. | No variance from baseline. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | 0 | 2 | 0 | Not applicable, currently we are still in negotiations and do not have any signed agreements in place. | N/A; currently no wholesale services have yet to be provided. Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 0 | 0 | 0 | 0 | No variance from baseline. | No variance from baseline. | No variance from baseline. | No variance from baseline. | 47 | 0 | 47 | 47 | During this quarter we did not connect any additional Community Anchor Institutions. | No variance from baseline. | During this quarter we did not connect any additional Community Anchor Institutions. | Forty-six of the Community Anchor Institutions are receiving 1000Mpbs Private WAN Connections; one is receiving a 10Mbps Private WAN Connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not Applicable | FALSE | Our network management practices have not changed. | We will continue to contact Community Anchor Institutions and present quotes/contracts for services. Request for proposals for wide area network services for K-12 schools are expected to be released this quarter. We will be submitting responses for these and anticipate securing several new contracts. Discussions with our fiber vendors will continue to try to secure better lead times. Additional fiber optic cable, markers etc. will be ordered. Franchise agreements will be negotiated in counties where our next build will take place and permits will be secured. Once permits/approvals are secured construction will continue. | Contact Network Inc. d/b/a InLine | We are experiencing delays due to negotiations of Franchise Agreements with various cities and counties as well as with all the railroad crossing permits we submit. Also the cost of aerial build has dramatically increased - specifically the annual pole attachment fees and the one time make ready costs. The Electric Power Associations have changed the allocation space where communications are allowed to attach from 40 inches to 84 inches with is either causing us to have to pay for pole change outs or change the build to underground. Also, the K-12 schools are not freely allowing us to place the telecommunication huts for interconnection on their properties. | Due to changes in route and hut locations more environmental studies will have to be conducted and approvals will have to be obtained. Mississippi Department of Transportation permits are becoming increasingly difficult to secure. As winter comes to an end and spring approaches, weather could also have an impact on our planned progress. | TRUE
NT10BIX5570104 | 2012 | Q1 | Q1 - 2012 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and county governments. Also, all route changes were finalized and sent the Mississippi State Historical Preservation Office for approval. No new miles of fiber were constructed. Our focus was on securing permits and contracts this quarter. As of March 31, 2012 we have constructed 86 miles of new fiber, leased an additional 122 miles and are servicing a total of forty seven Community Anchor Institutions. | 86 | 122 | 0 | 0 | 86 | 0 | 0 | 3 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline. | No variance from baseline. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | 1 | 1 | 80 | Windstream | Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 1 | 0 | 0 | 0 | We were able to secure one wholesale contract to provide new service, thus causing a variance from our baseline. | We were able to secure one wholesale contract to provide new service instead of improved service, thus causing a variance from our baseline. | No Variance from baseline. | 10Mbps Private Network-no subscribers; 10Mbps Fiber Connection with Internet Access-no subcribers; 100Mbps Private Network-no subscribers; 100Mbps Fiber Connection with Internet Access-no subscribers; 1000Mbps Private Network - 1 subscriber | 47 | 0 | 47 | 47 | During this quarter we did not connect any additional Community Anchor Institutions. | No variance from baseline. | During this quarter we did not connect any additional Community Anchor Institutions. | Forty-six of the Community Anchor Institutions are receiving 1000Mpbs Private WAN Connections; one is receiving a 10Mbps Private WAN Connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/ | N/A | Not Applicable | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction will continue. Route changes will be submitted to the grants office once approval from State and Local entities are approved. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Negotiations with our fiber vendors will continue to secure fiber deliveries also other resources for fiber will be researched. Franchise agreements will be continue to be negotiated in counties where our next builds will take place and permits will be secured. Once permits/approvals are secured construction will continue. We anticipate installation of 100 miles of new fiber and additional fiber to be leased. We also expect to connect 25 new CAIâ€™s. Negotiations will continue with wholesale broadband or last mile providers. | Contact Network Inc. d/b/a InLine | We are still experiencing delays due to negotiations of Franchise Agreements with various cities and counties as well as with all the railroad crossing permits and Mississippi Department of Transportation permits we submit. Also, the cost of aerial build has dramatically increased - specifically the annual pole attachment fees and the one time make ready costs. During this quarter, we were notified by Mississippi Power that they have contracted with an outside company to process the engineering for the pole attachment applications and that they would be passing this per pole costs on to us. Also, the Electric Power Associations have changed the allocation space where communications are allowed to attach from 40 inches to 84 inches with is either causing us to have to pay for pole change outs or change the build to underground. Also, we are still having issues with the K-12 schools are not freely allowing us to place the telecommunication huts for interconnection on their properties. While we have received small shipments of fiber, we still are in desperate need of more deliveries. | Mississippi Department of Transportation permits are becoming increasingly difficult to secure. As always in the south, weather could also have an impact on our planned progress. Fiber availability will continue to be an issue. | TRUE
NT10BIX5570104 | 2012 | Q2 | Q2 - 2012 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and county governments. Railroad permits were applied for and approved. Pole attachment permits were submitted and approved. A few deliveries of fiber were received. The route changes sent to the Mississippi State Historical Preservation Office were approved. Thirty three new miles of fiber were constructed bringing the total of miles built to one hundred and nineteen. Also, ten new anchor institutions were connected bring the total to fifty seven. | 119 | 122 | 0 | 0 | 119 | 0 | 0 | 8 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline | No variance from baseline | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | No variance from baseline. | 1 | 1 | 80 | Windstream | Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 1 | 0 | 0 | 0 | We were able to secure one wholesale contract to provide new service, thus causing a variance from our baseline. | We were able to secure one wholesale contract to provide new service instead of improved service, thus causing a variance from our baseline. | No variance from baseline. | 10Mbps Private Network-no subscribers; 10Mbps Fiber Connection with Internet Access-no subcribers; 100Mbps Private Network-no subscribers; 100Mbps Fiber Connection with Internet Access-no subscribers; 1000Mbps Private Network - 1 subscriber | 57 | 0 | 57 | 57 | We have contracts to connect another six community anchor institutions and are in the process of this construction, which would bring us closer to our baseline projection. | No variance from baseline. | We have contracts to connect another six community anchor institutions and are in the process of this construction, which would bring us closer to our baseline projection. | Fifty-six of the Community Anchor Institutions are receiving 1000Mpbs Private WAN Connections; one is receiving a 10Mbps Private WAN Connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not Applicable | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction will continue. Route changes will be submitted to the grants office, now that approvals from State and Local entities have been received. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Franchise agreements will continue to be negotiated in municipalities where our next builds will take place and permits will be secured. Once permits/approvals are secured construction will continue. We anticipate installation of 60 miles of new fiber and additional fiber to be leased. We also expect to connect four new Community Anchor Institutuions. Negotiations will continue with wholesale broadband or last mile providers. | Contact Network Inc. d/b/a InLine | We are still experiencing delays due to negotiations of Franchise Agreements with various cities and counties as well as with all the railroad crossing permits and Mississippi Department of Transportation permits we submit. Also, the cost of aerial build has dramatically increased - specifically the annual pole attachment fees and the one time make ready costs. Also, the Electric Power Associations have changed the allocation space where communications are allowed to attach from 40 inches to 84 inches with is either causing us to have to pay for pole change outs or change the build to underground. Also, we are still having issues with the K-12 schools are not freely allowing us to place the telecommunication huts for interconnection on their properties. | Mississippi Department of Transportation permits are becoming increasingly difficult to secure. As always in the south, weather could also have an impact on our planned progress. | TRUE
NT10BIX5570104 | 2012 | Q3 | Q3 - 2012 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Railroad and aerial permits were also submitted and approved. Forty three new miles of fiber were constructed bringing the total miles constructed to 162. A total of three new anchor institutions were connected bringing the total of anchors connected to Sixty. | 162 | 122 | 0 | 0 | 162 | 0 | 0 | 9 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline | No variance from baseline | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | No variance from baseline | 1 | 1 | 80 | Windstream | Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 1 | 0 | 0 | 0 | We were able to secure one wholesale contract to provide new service, thus causing a variance from our baseline. | We were able to secure one wholesale contract to provide new service instead of improved service, thus causing a variance from our baseline. | No variance from baseline. | 10Mbps Private Network-no subscribers; 10Mbps Fiber Connection with Internet Access-no subscribers; 100Mbps Private Network-no subscribers; 100Mbps Fiber Connection with Internet Access-no subscribers; 1000Mbps Private Network - 1 subscriber | 60 | 0 | 60 | 60 | We have contracts to connect another two community anchor institutions and are in the process of this construction, which would bring us closer to our baseline projection. | No variance from baseline. | We have contracts to connect another two community anchor institutions and are in the process of this construction, which would bring us closer to our baseline projection. | Fifty of the Community Anchor Institutions are receiving 1000Mpbs Private WAN Connections; ten are receiving a 10Mbps Private WAN Connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not Applicable | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction will continue. Route changes will be submitted to the grants office, now that approvals from State and Local entities have been received. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Franchise agreements will continue to be negotiated in municipalities where our next builds will take place and permits will be secured. Once permits/approvals are secured construction will continue. We anticipate installation of thirty two miles of new fiber and additional fiber to be leased. We also expect to connect four new Community Anchor Institutions. Negotiations will continue with wholesale broadband or last mile providers. | Contact Network Inc. d/b/a InLine | We are still experiencing delays due to negotiations of Franchise Agreements with various cities and counties as well as with all the railroad crossing permits and Mississippi Department of Transportation permits we submit. Also, the cost of aerial build has dramatically increased - specifically the annual pole attachment fees and the one time make ready costs. Also, the Electric Power Associations have changed the allocation space where communications are allowed to attach from 40 inches to 84 inches with is either causing us to have to pay for pole change outs or change the build to underground. Also, we are still having issues with the K-12 schools are not freely allowing us to place the telecommunication huts for interconnection on their properties. | Mississippi Department of Transportation permits are becoming increasingly difficult to secure. As always in the south, weather could also have an impact on our planned progress. | TRUE
NT10BIX5570104 | 2012 | Q4 | Q4 - 2012 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Railroad and aerial permits were also submitted and approved. Thirty three new miles of fiber were constructed bringing the total miles constructed to 195. No new anchor institutions were connected this quarter. Total anchors connected is Fifty Five. | 195 | 122 | 0 | 0 | 195 | 0 | 0 | 10 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline | No variance from baseline | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | No variance from baseline | 1 | 1 | 60 | Windstream | Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 500Mbps Private Network; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 1 | 0 | 0 | 0 | We were able to secure two wholesale contracts to provide new service, thus causing a variance from our baseline. | We were able to secure two wholesale contracts to provide new service, thus causing a variance from our baseline. | No variance from baseline | 10Mbps Private Network-no subscribers; 10Mbps Fiber Connection with Internet Access-one subscribers; 100Mbps Private Network-no subscribers; 100Mbps Fiber Connection with Internet Access-no subscribers; 1000Mbps Private Network - 1 subscriber | 55 | 0 | 55 | 55 | We have contracts to connect another eleven community anchor institutions and are in the process of this construction, which would bring us closer to our baseline projection. | No variance from baseline | We have contracts to connect another eleven community anchor institutions and are in the process of this construction, which would bring us closer to our baseline projection. | Forty six of the Community Anchor Institutions are receiving 1000Mpbs Private WAN Connections, ten with internet access; nine are receiving a 10Mbps Private WAN Connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not applicable | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction will continue. Route changes will be submitted to the grants office, now that approvals from State and Local entities have been received. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Franchise agreements will continue to be negotiated in municipalities where our next builds will take place and permits will be secured. Once permits/approvals are secured construction will continue. We anticipate installation of thirty five miles of new fiber and additional fiber to be leased. We also expect to connect eleven new Community Anchor Institutions. Negotiations will continue with wholesale broadband or last mile providers. | Contact Network Inc. d/b/a InLine | We are still experiencing delays due to negotiations of Franchise Agreements with various cities and counties as well as with all the railroad crossing permits, which are averaging six weeks to secure and Mississippi Department of Transportation permits we submit. Also, the cost of aerial build has dramatically increased - specifically the annual pole attachment fees and the one time make ready costs. Also, the Electric Power Associations have changed the allocation space where communications are allowed to attach from 40 inches to 84 inches with is either causing us to have to pay for pole change outs or change the build to underground. Also, we are still having issues with the K-12 schools are not freely allowing us to place the telecommunication huts for interconnection on their properties. | Mississippi Department of Transportation and Railroad crossing permits are becoming increasingly difficult to secure. As always in the south, weather could also have an impact on our planned progress. | TRUE
NT10BIX5570104 | 2013 | Q1 | Q1 - 2013 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Railroad and aerial permits were also submitted and approved. Thirty new miles of fiber were constructed bringing the total miles constructed to 225. Six new anchor institutions were connected this quarter. Total anchors connected is Sixty one. | 225 | 122 | 0 | 0 | 225 | 0 | 0 | 11 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | No variance from baseline | No variance from baseline | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | No variance from baseline | 1 | 1 | 60 | Windstream | Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 500Mbps Private Network; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 1 | 0 | 0 | 1 | We were able to secure one wholesale contracts to provide new service, thus causing a variance from our baseline. | We were able to secure one wholesale contracts to provide new service, thus causing a variance from our baseline. | No variance from baseline | 10Mbps Private Network-no subscribers; 10Mbps Fiber Connection with Internet Access-one subscribers; 100Mbps Private Network-no subscribers; 100Mbps Fiber Connection with Internet Access-no subscribers; 1000Mbps Private Network - 1 subscriber | 61 | 0 | 61 | 61 | We have contracts to connect another twenty one community anchor institutions and are in the process of this construction, which would bring us closer to our baseline projection. | No variance from baseline | We have contracts to connect another twenty one community anchor institutions and are in the process of this construction, which would bring us closer to our baseline projection. | Fifty two of the Community Anchor Institutions are receiving 1000Mpbs Private WAN Connections, ten with internet access; nine are receiving a 10Mbps Private WAN Connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not applicable | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction will continue. Route changes will be submitted to the grants office, now that approvals from State and Local entities have been received. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Franchise agreements will continue to be negotiated in municipalities where our next builds will take place and permits will be secured. Once permits/approvals are secured construction will continue. We anticipate installation of seventy eight miles of new fiber and additional fiber to be leased. We also expect to connect twenty five new Community Anchor Institutions. Negotiations will continue with wholesale broadband or last mile providers. | Contact Network Inc. d/b/a InLine | We are still experiencing delays due to negotiations of Franchise Agreements with various cities and counties as well as with all the railroad crossing permits, which are averaging six weeks to secure and Mississippi Department of Transportation permits we submit. Also, the cost of aerial build has dramatically increased - specifically the annual pole attachment fees and the one time make ready costs. Also, the Electric Power Associations have changed the allocation space where communications are allowed to attach from 40 inches to 84 inches with is either causing us to have to pay for pole change outs or change the build to underground. Also, we are still having issues with the K-12 schools are not freely allowing us to place the telecommunication huts for interconnection on their properties. | Mississippi Department of Transportation and Railroad crossing permits are becoming increasingly difficult to secure. As always in the south, weather could also have an impact on our planned progress. | TRUE
NT10BIX5570104 | 2013 | Q2 | Q2 - 2013 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Railroad and aerial permits were also submitted and approved. Sixty six new miles of fiber were constructed bringing the total miles constructed to 291. Thirteen new anchor institutions were connected this quarter. Total anchors connected is Seventy four. | 291 | 218 | 0 | 0 | 291 | 0 | 0 | 12 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | This number exceeds our baseline projection. | No variance from baseline | No variance from baseline | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | No variance from baseline | 1 | 1 | 60 | Windstream | Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 500Mbps Private Network; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 1 | 0 | 0 | 4 | We were able to secure one wholesale contracts to provide new service, thus causing a variance from our baseline | We were able to secure one wholesale contracts to provide new service, thus causing a variance from our baseline | No variance from base | 10Mbps = 0 Subscribers 100Mbps = 0 Subscribers 500Mpbs= 0 Subsribers 1000Mbps = 1 Subscriber | 74 | 0 | 74 | 5 | During this quarter we connected thirteen additional Community Anchor Institutions which varies from our baseline projections. | No variance from baseline. | During this quarter we connected sixty five additional Community Anchor Institutions which varies from our baseline projections. | 10Mbps = 9 Subscribers 50Mbps = 0 Subscribers 100Mbps = 0 Subscribers 500Mbps = 0 Subscribers 1000Mbps = 65 Subscribers | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not applicable | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction will continue. Route changes will be submitted to the grants office, now that approvals from State and Local entities have been received. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Once permits/approvals are secured construction will continue. We anticipate installation of sixty two miles of new fiber. We also expect to connect sixty new Community Anchor Institutions. Negotiations will continue with wholesale broadband or last mile providers. If negotiations are successful we will connect one additional wholesale provider. | Contact Network Inc. d/b/a InLine | We are still experiencing delays receiving permits from the Mississippi Department of Transportation permit. Also, we have experienced some construction delays due to wet weather. | As always in the south, weather could also have an impact on our planned progress. | TRUE
NT10BIX5570104 | 2013 | Q3 | Q3 - 2013 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Also during this quarter we submitted our final route modification. Nine new miles of fiber were constructed bringing the total miles constructed to 300. Six new anchor institutions were connected this quarter. Total anchors connected is Eighty. | 300 | 218 | 0 | 0 | 300 | 0 | 0 | 12 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | This number exceeds our baseline projection. | No variance from baseline | No variance from baseline | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | No variance from baseline | 1 | 1 | 60 | Windstream | Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 500Mbps Private Network; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network. | 1 | 0 | 0 | 4 | We were able to secure one wholesale contracts to provide new service, thus causing a variance from our baseline | We were able to secure one wholesale contracts to provide new service not improved access, thus causing a variance from our baseline | No variance from baseline | 10Mbps = 0 Subscribers 100Mbps = 0 Subscribers 500Mpbs= 0 Subsribers 1000Mbps = 1 Subscriber | 80 | 0 | 80 | 5 | During this quarter we connected six additional Community Anchor Institutions which varies from our baseline projections. | No variance from baseline. | During this quarter we connected six additional Community Anchor Institutions which varies from our baseline projections. | 10Mbps = 9 Subscribers 50Mbps = 0 Subscribers 100Mbps = 0 Subscribers 500Mbps = 0 Subscribers 1000Mbps = 71 Subscribers | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not applicable | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction will continue. We will begin to submit our UCC filings. Once we know if the pending route modification is approved the UCC filings will be finalized. During this quarter we will begin the final close out audit. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. Once permits/approvals are secured construction will continue. We anticipate installation of thirty two miles of new fiber. We also expect to connect fifty four new Community Anchor Institutions. Negotiations will continue with wholesale broadband or last mile providers. If negotiations are successful we will connect one additional wholesale provider. | Contact Network Inc. d/b/a InLine | We are still experiencing delays receiving permits from the Mississippi Department of Transportation permit. | As always in the south, weather could also have an impact on our planned progress. | TRUE
NT10BIX5570104 | 2013 | Q4 | Q4 - 2013 | During this quarter construction maps and detailed drawings were created and used to submit permits to various entities including the Mississippi Department of Transportation and various City and County governments. Also during this quarter our final route modification was approved which will allow us to build laterals to additional Community Anchor Institutions. Five new miles of fiber were constructed bringing the total miles constructed to 306. Fourteen new anchor institutions were connected this quarter. Total anchors connected is Ninety-four. | 306 | 218 | 0 | 0 | 306 | 0 | 0 | 12 | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | This number exceeds our baseline projection. | No variance from baseline | No variance from baseline | Due to actual contracts signed and the focus being to provide these Community Anchor Institutions service this number varies from our initial baseline projections. | N/A | N/A | No variance from baseline. | 1 | 1 | 60 | Windstream | Our wholesale service offerings will include: 10Mbps Private Network; 10Mbps Fiber Connection with Internet Access; 100Mbps Private Network; 100Mbps Fiber Connection with Internet Access; 500Mbps Private Network; 1000Mbps Private Network | Not Applicable; we do not have a third party operating any part of our network | 1 | 0 | 0 | 4 | We were able to secure one wholesale contracts to provide new service, thus causing a variance from our baseline | We were able to secure one wholesale contracts to provide new service not improved access, thus causing a variance from our baseline | No variance from baseline | 10Mbps = 0 Subscribers 100Mbps = 0 Subscribers 500Mpbs= 0 Subsribers 1000Mbps = 1 Subscriber | 94 | 0 | 94 | 5 | During this quarter we connected fourteen additional Community Anchor Institutions which varies from our baseline projections. | No variance from baseline. | During this quarter we connected fourteen additional Community Anchor Institutions which varies from our baseline projections. | 10Mbps = 5 Subscribers 50Mbps = 0 Subscribers 100Mbps = 4 Subscribers 500Mbps = 0 Subscribers 1000Mbps = 85 Subscribers | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Not applicable | FALSE | Our network management practices have not changed. | Permits will continue to be submitted and construction of laterals to CAI's will continue. We will begin to submit our UCC filings. During this quarter we will begin the final close out audit. Also, we will be continuing to contact Community Anchor Institutions and presenting quotes/contracts for services. We anticipate installation of fifteen miles of new fiber, bringing the total miles of new fiber construction to 321 miles. The last twenty miles will consist of laterals to connect the Anchor Institutions that have given us permission to install fiber to their buildings. In our last route modification we anticipated the total miles of new fiber build would be 332 miles; the eleven mile difference in this category is due to the fact that we only have permission from thirty-eight anchors to connect their facility. The additional thirty eight anchors we plan to connect next quarter will bring our total connected to 132. This will meet the connected Community Anchor Institutions in our original application. Negotiations will continue with wholesale broadband or last mile providers. If negotiations are successful we will connect one additional wholesale provider. | Contact Network Inc. d/b/a InLine | We are still experiencing delays receiving permits from the Mississippi Department of Transportation permit. | As always in the south, weather could also have an impact on our planned progress. | TRUE
NT10BIX5570105 | 2010 | Q4 | Q4 - 2010 | During the last quarter, the State of New Jersey has engaged The Louis Berger Group to conduct the Environmental Assessment. In addition, an RFP was drafted for the procurement of a vendor(s) to build out the funded network. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The State of New Jersey intends to release the RFP seeking qualified vendor(s) to build the network. In addition, the Environmental Assessment will be completed. | Treasury, New Jersey Department of | The requirement to complete an Environmental Assessment within six months of the award date is admirable. However, the timing makes it difficult to engage the necessary technical assistance to finalize the network design proposed in the application. As a result, an assessment cannot conducted with the confidence that the design will not be altered at a later date. | We may be at risk of having to re-conduct or append the Environmental Assessment after a vendor is engaged and the network design is finalized. | TRUE
NT10BIX5570105 | 2011 | Q1 | Q1 - 2011 | Draft Environmental Assessment was completed on 77 site and sent to the NTIA. An extension request was filed in order to allow for 40 additional sites to be added to the original list. A specialist was hired to manage the network build out. The RFP specification was reworked to change the design scope; which included the removal of 100 miles fiber back haul and additional tower sites. Removing the 100 miles of fiber will help to keep the project on track and completed on time. A search was initiated to hire an RF LTE engineer. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | None. No change from baseline | None. No change from baseline | None. No change from baseline | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | N/A | FALSE | N/A | Environmental assessments will be complete as of 4/30/2011. RFP will be released and responses received and under evaluation. We will hire a LTE RF engineer to support the RFP process and evaluate the responses. | Treasury, New Jersey Department of | The NJ Office of Information Technology had to re-scope the network conceptual design to remove 100 miles of back haul fiber. In order to do this we had to add 40 additional tower sites and have environmental assessments done on them. This approach was taken in order to meet our projects target completion date as well as provide comprehensive coverage in the UASI region. | We have stipulated that bidders must adhere to all current and future rules the FCC adopts for a nationwide interoperability. However, the timing of any new rules could extend the RFP process and time line. | TRUE
NT10BIX5570105 | 2011 | Q2 | Q2 - 2011 | Draft Environmental Assessment was completed on a total of 114 sites and sent to the NTIA. We are awaiting conditional approval for the EA. In addition was are awaiting approval for a programmatic agreement from the Historic Preservation Society. Requests for engineering as well as legal, policy, governance and regulatory personnel have been released to the marketplace and hiring will be completed in early July. The RFP has gone through final review and will be released in early July as well. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | None. No change from baseline. | None. No change from baseline. | None. No change from baseline. | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | N/A | FALSE | N/A | RFP will be released and evaluation complete by the end of the quarter. We will hire Microwave and LTE RF engineering resources to support the RFP process and evaluate the responses. In addition we will hire a Legal and Policy consultant to develop attachment agreements and local government communications plan. | Treasury, New Jersey Department of | The RFP release has been delayed Due to the changes made in the design scope. This approach was necessary in order to meet our environmental requirements. We completed the Environmental Assessments and expect conditional approval shortly. The RFP is being released in the beginning of July. | We have stipulated that bidders must adhere to all current and future rules the FCC adopts for a nationwide interoperability. However, the timing of any new rules could extend the RFP process and time line. | TRUE
NT10BIX5570105 | 2011 | Q3 | Q3 - 2011 | The State received a categorical exclusion for the Environmental impact assessment as well as a programmatic agreement from the Historic Preservation Society. The State also hired (3) RF/Microwave engineering consultants as well as a Policy consultant. The RFP was released on July 6th and responses are due back on October 25th. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | None. No change from baseline. | None. No change from baseline. | None. No change from baseline. | 0 | 0 | 0 | 0 | No change from baseline. | No change from baseline. | No change from baseline. | No change from baseline. | 0 | 0 | 0 | 0 | No change from baseline. | No change from baseline. | No change from baseline. | No change from baseline. | 0 | 0 | 0 | 0 | 0 | No change from baseline. | No change from baseline. | No change from baseline. | No change from baseline. | No change from baseline. | 0 | 0 | 0 | 0 | 0 | No change from baseline. | No change from baseline. | No change from baseline. | No change from baseline. | No change from baseline. | N/A | FALSE | N/A | By the next quarter the State expects to be in receipt of RFP responses, complete evaluations, negotiate terms with a selected vendor. The State will add an analyst resource to oversee document management and reporting functions. The selected vendor will have submitted a comprehensive, attainable project plan and adjoining time line that will meet grant mandated deadlines. In-kind match will be identified through a combination of State and/or vendor contributions. | Treasury, New Jersey Department of | A change in the original network design delayed the release of the RFP to the vendor community until July. The bid opening date was set for September 3rd, however, the State of NJ received more than 180 questions from the vendor community that required a response. In order to formulate thoughtful, thorough responses the bid opening date was revised to October 25th. | We have asked vendors, to the extent possible, to provide RFP responses that help the State meet its in-kind match requirement. OIT will consult with the NTIA in advance of making an award to ensure that the proposed vendor is suitable to the task and will meet the NTIA established guidelines or deadlines. | TRUE
NT10BIX5570105 | 2011 | Q4 | Q4 - 2011 | On November 15, 2011, the State received four proposals in response to the RFP. The Proposals are under review by the evaluation team. Reviews are expected to be complete by the middle of January. Immediately following the evaluations and vendor selection, the State will initiate contract negotiations. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | At this time no network miles have been deployed. The network design includes 361 miles of microwave backhaul. The State expects construction of the microwave links to begin by the end of the second quarter of 2012. | N/A | N/A | N/A | Fiber was in the originally approved design, but has been taken out. As such there is none deployed | The network design includes deployment of 77 eNodeB's. The State expects construction of the eNodeB's to begin at the same time as the microwave radios, by the end of the second quarter of 2012. At this time no eNodeB's have been deployed. | N/A | No change from baseline | 0 | 0 | 0 | None. No change from baseline | None. No change form baseline | The RFP requires that the contractor, build, operate and maintain the network. The contractor has not been selected yet. | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The State expects to select a vendor from those that responded to the RFP's Negotiations should be complete and a contract executed before the end of the quarter. Site visits will commence to confirm tower viability and identify any reradiation work necessary to accept Microwave and LTE equipment. | Treasury, New Jersey Department of | In order to give the vendor community enough time to respond to the RFP after answering their question, the state needed to extend the bid opening date 3 week from October 25th to November 15th. | The State is doing its best to accelerate the project due to the short overall time frame. | TRUE
NT10BIX5570105 | 2012 | Q1 | Q1 - 2012 | The State of New Jersey was unable to award a construction contract with the RFP released in 2011. In view of that, on 2/9/2012 the State submitted a request for a 2-year extension to the NTIA. On 2/22/2012, the 2012 Middle Class Tax Relief and Jobs Creation Act was passed creating the framework for construction a national public safety network. On 3/5/2012 the BTOP recipients were advised by the NTIA that there is a possibility that our lease to use the 700MHz PS spectrum may not be renewed which could jeopardize the grant. On 3/12/2012, NJ received a CAP letter from the NTIA requesting among other things, a plan to move forward and a plan for the match requirement. New Jersey is contemplating the best approach to move forward with the project that best serves the citizens of the State and remains consistent with the intentions of the Act. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | See narrative in section 3. | N/A | N/A | N/A | Fiber was in the originally approved design, but has been taken out. As such there is none deployed. | See narrative in section 3. | N/A | See narrative in section 3. | 0 | 0 | 0 | None. No change from baseline | None. No change from baseline | The state has not designated third party to operate their network. | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The activities described herein are contingent upon approval of the revised budget. During this quarter, the State expects to development a revised plan for budget dollars that will be consistent with the objectives of the Act and it national network vision. In addition, will begin outreach to state, local, and tribal government and public safety entities to solicit assets (tower, fiber etc.) to support initiative. We will begin a site acquisition initiative, and start developing an RFP for a commercial tower master services contract. | Treasury, New Jersey Department of | The State of New Jersey was unable to award a construction contract with the RFP released in 2011. In view of that, on 2/9/2012 the State submitted a request for a 2-year extension to the NTIA. Following that, the 2012 Middle Class Tax Relief and Jobs Creation Act was passed creating the framework for construction a national public safety network. On 3/5/2012 the BTOP recipients were advised by the NTIA that there is a possibility that our lease to use the 700MHz PS spectrum may not be renewed which could jeopardize the grant. On 3/12/2012, NJ received a CAP letter from the NTIA requesting among other things, a plan to move forward and a plan for the match requirement. New Jersey is contemplating the best approach to move forward with the project that best serves the citizens of the State and remains consistent with the intentions of the Act. | The State's project plan and progress will be materially affected by the status of the lease to use the 700 MHz spectrum. If the lease is not extended, NJ will not have spectrum access rights to operate an LTE network. We will work with the NTIA to determine an acceptable contingence plan. | TRUE
NT10BIX5570105 | 2012 | Q2 | Q2 - 2012 | On 4/27/2012 New Jersey submitted a comprehensive response to NTIA/NOAA's 3/12/12 CAP letter. The response included, among other things, a revised project plan, schedule, and $8M cash match commitment. On May 11, 2012 the State received a letter from NOAA suspending the LTE portion of the award. As a result of the suspension, the State was unable to proceed with the project plan outlined in our CAP response. The remainder of the qtr was devoted to developing a plan in response to the suspension notification. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | See narrative in section (3) | N/A | N/A | N/A | Fiber was in the originally approved design, but has been taken out. As such there is none deployed. | See Narrative in section (3) | N/A | See Narrative in section (3) | 0 | 0 | 0 | None. No change from baseline | None. No change from baseline | The state has not designated a third party to operate the network. | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | 0 | See Narrative in (Project Indicators section 1) | No change from baseline | See Narrative in (Project Indicators section 1) | No change from baseline | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The activities described herein are contingent upon approval of the revised budget, including matching funds. During this quarter, the State will work with NTIA to development a plan for budget dollars that will consist of low risk activities. The objective for the 3rd quarter is to start a statewide search for towers, buildings, fiber, microwave and backhaul assets that may be used to construct New Jersey's portion of the nationwide network. In addition, will begin outreach to state, local, and tribal government and public safety entities to solicit assets (tower, fiber etc.) to support initiative. Due to the changes required by the suspension of LTE the milestone and milestone indicators will not be in line with the baseline. | Treasury, New Jersey Department of | On 3/12/2012, NJ received a CAP letter from the NTIA requesting among other things, a plan to move forward and a plan for the match requirement. New Jersey developed and submitted a comprehensive detailed response and move forward plan on April 27, 2012. On May 11, 2012 NJ received a LTE suspension letter which has suspended any work involving the purchase and or installation of LTE equipment. The majority of the quarter was expended assessing the states option(s) which will make best use of the award funds for both NJ and FirstNet. | The State's ability to move forward in the 3rd quarter is contingent upon an agreement with NTIA on a revised project and spending, and matching funds plan that is limited to low risk activities. | TRUE
NT10BIX5570105 | 2012 | Q3 | Q3 - 2012 | In response to the NOAA partial suspension of grant funds, the State undertook to re-cast the project to avoid the potential delay of the partial suspension. The revised project would not actually deploy an LTE network; instead, it would prepare government-owned sites statewide to accept the future nationwide network. The State submitted a revised budget reflecting the re-cast project and is in the process of incorporating NTIA comments into those budget documents. Finally, the State took major steps toward bringing additional staff onto the project team, including selection of contractors and interviewing FTE candidates. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to deploy network miles per our project baseline. | N/A | N/A | N/A | Fiber was in the originally approved design, but has been taken out. As such there is none deployed. | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to complete new wireless links per our project baseline. | N/A | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to deploy new and/or upgraded interconnection points per our project baseline. | 0 | 0 | 0 | None. No change from baseline | None. No change from baseline | The state has not designated a third party to operate the network. | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | 0 | See Narrative in (Project Indicators section 1) | No change from baseline | See Narrative in (Project Indicators section 1) | No change from baseline | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | We hope to receive input from NTIA and solidify future direction and plan for the project. Additionally we anticipate to identify assets within the state and provide the necessary governance support and establish and streamline the grant management processes. | Treasury, New Jersey Department of | See answer to #1. Awaiting input from NTIA as described. | The State's ability to move forward in the 4th quarter is contingent upon an agreement with NTIA on a revised project and spending, and matching funds plan that is limited to low risk activities. | TRUE
NT10BIX5570105 | 2012 | Q4 | Q4 - 2012 | In light of stakeholder input, the State undertook a further revision of the project to include both the preparation of government-owned sites statewide to accept the future nationwide network as well as a small LTE pilot project in the Route 21 Paterson-Newark corridor. The State prepared and presented this revised plan to NTIA and FirstNet at a daylong meeting on December 14, 2012. That meeting, attended by BTOP staff and public safety stakeholders statewide, was for the explicit purpose of pursuing a dialogue between in which FirstNet (as the license holder), NTIA (as the grantor) and the State (as the grantee and project owner) would develop, agree upon, and pursue a project approach that meets the needs of the State and helps inform and forward the nationwide effort. The State also reviewed and analyzed the special award conditions proposed by NTIA staff proposed in connection with the grant and the FirstNet meeting. Finally, the State took major steps forward bringing on an BTOP Program Manager. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to deploy network miles per our project baseline. | N/A | N/A | N/A | Fiber was in the originally approved design, but has been taken out. As such there is none deployed. | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to complete new wireless links per our project baseline. | N/A | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to deploy new and/or upgraded interconnection points per our project baseline. | 0 | 0 | 0 | None. No change from baseline | None. No change from baseline | The state has not designated a third party to operate the network. | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | 0 | See Narrative in (Project Indicators section 1) | No change from baseline | See Narrative in (Project Indicators section 1) | No change from baseline | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The NJ BTOP team plans to submit our updated Project Plan including both the preparation of government-owned sites statewide to accept the future nationwide network as well as a small LTE pilot project in the Route 21 Paterson-Newark corridor. We will also submit a partially modified budget to align our resources to the project. The team also plans to begin site identification activities while creating a communications plan and a coverage design map. | Treasury, New Jersey Department of | See answer to #1. Awaiting input from FirstNet / NTIA related to our updated project plan. As it relates to Question1a in Activity Based Expenditures, the $53,975 previously reported in the Q3 2012 PPR was reallocated into Federal Funds expended in our Q4 2012 PPR. The State originally placed that amount in Matching Funds Expended prior to working with NOAA regarding their accrual reporting process. As it relates to Question 1l&n Actual Federal Funds, the $636,533 matches line g. Total Federal share in the Q4 2012 SF425 filing. This is in compliance with NOAA's accrual reporting process. | The State's is planning on moving forward doing the low risk activities mentioned above. | TRUE
NT10BIX5570105 | 2013 | Q1 | Q1 - 2013 | The project continued making progress. FirstNet released the first draft of the Memorandum of Agreement (MOA) to allow the state use of the spectrum. New Jersey, along with the other Broadband Technology Opportunity Program (BTOP) recipients, is in active negotiation on terms for the Memorandum of Agreement. Outreach activities that took place in February included briefings to the Public Safety Communications Advisory Council (PSCAC), the Public Safety Communications Commission and the Domestic Security Preparedness Task force. Project management activities included the definition of roles and responsibilities for the project, finalizing expected team structure and definition of stakeholder groups, and completion of the first draft of a Project Charter. A financial analyst joined the team and began in March and Site Identification resources were interviewed and selections made. The team also began work on the full budget modification and Project Plan to support the expected project extension. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to deploy network miles per our project baseline. | n/a | n/a | n/a | Fiber was in the originally approved design, but has been taken out. As such there is none deployed. | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to complete new wireless links per our project baseline. | n/a | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to deploy new and/or upgraded interconnection points per our project baseline. | 0 | 0 | 0 | None. No change from baseline | None. No change from baseline | The state has not designated a third party to operate the network. | 0 | 0 | 0 | 0 | No change from baseline | No change from baseline | No change from baseline | No change from baseline | 0 | 0 | 0 | 0 | See Narrative in (Project Indicators section 1) | No change from baseline | See Narrative in (Project Indicators section 1) | No change from baseline | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | New Jersey will continue negotiations on the Memorandum of Agreement with FirstNet. The NJ BTOP team plans to submit a Project Extension, allowing project activities through September 2015. The team will on-board site identification resources, who will begin site identification of government owned sites. If the revised project is approved, the team will also prepare for site assessment resources. The team will continue preparing the revised budget for full budget modification. The team will also work on finalizing the Project Charter and Communication plan, and work to finalize membership in the Broadband Working Group. | Treasury, New Jersey Department of | See answer to #1. Continued negotiations on the Memorandum of Agreement with FirstNet. As it relates to Question 1l&n Actual Federal Funds, the $873,169 matches line g. Total Federal share in the Q1 2013 SF425 filing. This is in compliance with NOAA's accrual reporting process. As it relates to Activity Based Expenditures: After an internal review, $63,724.34 was reallocated from the Administrative and Legal expenses cost classification to the Architectural and engineering fees cost classification. $933.64 was also reallocated from the Administrative and Legal expenses cost classification to the Miscellaneous cost classification. This includes the $227.11 charge that was removed, due to being an unallowable expense. | The State continues to negotiate the First Net Memorandum of Agreement for the spectrum lease. In preparation, the team will work on identifying the appropriate procurement processes and continue to review the budget to submit a full budget modification. | TRUE
NT10BIX5570105 | 2013 | Q2 | Q2 - 2013 | The NJ BTOP project team continues negotiations with FirstNet on a potential project â€œpivotâ€ as well as on the Memorandum of Agreement (MOA) to allow use of the spectrum. A Terms and Conditions proposal, with respect to the project pivot, has been put forth and is under review. Two site identification resources were brought on board in April to collect current data on tower resources; the resources have been making significant progress in identifying government owned assets. In addition, an initial coverage design for the Route 21 corridor was completed and a job description for site assessors compiled. A Memorandum of Understanding (MOU) was drafted and sent to New Jersey Transit regarding the cash match for the project; negotiations with New Jersey Transit continue. The project team has developed a logo and name "JerseyNet" and the project website is currently under development, with projected launch in July. The State received a mini-extension of the project until September 2013 and the project team also continues work on the full budget modification. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to deploy network miles per our project baseline. | n/a | n/a | n/a | Fiber was in the originally approved design, but has been removed. As such there is none deployed. | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to complete new wireless links per our project baseline. | n/a | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to deploy new and/or upgraded interconnection points per our project baseline. | 0 | 0 | 0 | None. No change from baseline. | None. No change from baseline. | The State has not designated a third party to operate the network. | 0 | 0 | 0 | 0 | No change from baseline. | No change from baseline. | No change from baseline. | No change from baseline. | 0 | 0 | 0 | 0 | See Narrative in Project Indicators section 1 | No change from baseline. | See Narrative in Project Indicators section 1 | No change from baseline. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | New Jersey will continue negotiations on the Memorandum of Understanding (MOU) and project strategy with FirstNet. The team will also continue to negotiate the Memorandum of Agreement (MOA) with New Jersey Transit for the projectâ€™s cash match. The team plans to finalize site identification activities of government owned sites, as well as continue to update the initial coverage design in the Route 21 corridor. The team will also work on finalizing the Project Charter and Communication plan, and work to finalize membership in the Broadband Working Group. Additionally, the team plans to launch the JerseyNet project website. The team will also continue to review the budget to submit for the full budget modification. | Treasury, New Jersey Department of | See response to question #1. Negotiations with FirstNet continue on the project direction and spectrum lease. As it relates to Question 1l&n Actual Federal Funds, the $1,076,579.29 matches line g. Total Federal share in the Q2 2013 SF425 filing. This is in compliance with NOAA's accrual reporting process. As it relates to Activity Based Expenditures: After an internal review, $63,724.34 was reallocated from the Administrative and Legal expenses cost classification to the Architectural and engineering fees cost classification. $933.64 was also reallocated from the Administrative and Legal expenses cost classification to the Miscellaneous cost classification. This includes the $227.11 charge that was removed, due to being an unallowable expense. As it relates to Activity Based Expenditures: After an internal review, $28,000 was reallocated from Land, structures, right-of-ways, appraisals, etc. to the Other Architectural and Engineering fees cost classification. | The State continues to negotiate the strategy and spectrum lease, which delays project activities. Additionally, New Jersey continues to negotiate the Memorandum of Agreement (MOA) with NJ Transit to secure matching funds. | TRUE
NT10BIX5570105 | 2013 | Q3 | Q3 - 2013 | The NJ BTOP project team continues negotiations with FirstNet on a potential project â€œpivotâ€ as well as on the Spectrum Management Lease Agreement (SMLA) to allow use of the spectrum. Site identification resources continued in July and August; site identification activities were completed in August. In addition, an initial coverage design for the Route 21 corridor began and a job description for site assessors compiled. A Memorandum of Understanding (MOU) was drafted and sent to New Jersey Transit regarding the cash match for the project; negotiations were completed and the MOU was executed in July. The addendum to the NJ Transit MOA, striking the language regarding credits, was executed in September. Initial match installment of $1.5 million was received in September, expending 27% in cash match allowing the project to come into match proportionality. The State filed for and received a short extension of the project until December 2013, as the project team continues to refine the project direction and prepare documentation for the full extension of the project until September 2015. The project team continued revisions to the project website and social media accounts. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to deploy network miles per our project baseline. | n/a | n/a | n/a | Fiber was in the originally approved design, but has been since removed. As such there is none deployed. | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to complete new wireless links per our project baseline. | n/a | With NJ's RFP not being fulfilled and the Department of Commerce issuing a partial suspension of the project, we have been unable to complete new wireless links per ourp roject baseline. | 0 | 0 | 0 | None. | None. | None. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | As a result of the changes engendered by the passage of the Middle Class Tax Relief Act and the creation of the FirstNet authority, New Jersey has revised the project to align with State and national (FirstNet) priorities. Once the State and FirstNet agrees on the spectrum lease, New Jersey will begin the process to serve subscribers. | As a result of the changes engendered by the passage of the Middle Class Tax Relief Act and the creation of the FirstNet authority, New Jersey has revised the project to align with State and national (FirstNet) priorities. Once the State and FirstNet agrees on the spectrum lease, New Jersey will begin the process to serve subscribers. | As a result of the changes engendered by the passage of the Middle Class Tax Relief Act and the creation of the FirstNet authority, New Jersey has revised the project to align with State and national (FirstNet) priorities. Once the State and FirstNet agrees on the spectrum lease, New Jersey will begin the process to serve subscribers. | As a result of the changes engendered by the passage of the Middle Class Tax Relief Act and the creation of the FirstNet authority, New Jersey has revised the project to align with State and national (FirstNet) priorities. Once the State and FirstNet agrees on the spectrum lease, New Jersey will begin the process to serve subscribers. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The project team plans to finalize the new project direction and submit supporting documents in anticipation of the project extension through September 2015. Additionally, the team anticipates completion of negotiations on the Spectrum Lease Management Agreement (SMLA) with FirstNet. The team anticipates working with Procurement to define procurement processes to procure equipment for the project. | Treasury, New Jersey Department of | None. | As a result of the changes engendered by the passage of the Middle Class Tax Relief Act and the creation of the FirstNet authority, New Jersey has revised the project to align with State and national (FirstNet) priorities. The State continues to negotiate the spectrum lease and define project strategy in concert with FirstNet and the National Telecommunications and Information Administration, which delays project activities. | TRUE
NT10BIX5570105 | 2013 | Q4 | Q4 - 2013 | In October, New Jersey received confirmation that FirstNet would reopen negotiations for a Spectrum Manager Lease Agreement (SMLA) with New Jersey, with intent to reach agreement by November 15th. FirstNet and New Jersey agreed on Key Learning Conditions and general language by November 15th. The BTOP project team continued to revise the Project Narrative, route modifications, environmental filings and other supporting project documentation focused on a deployables-based project and resubmitted to NTIA for review in late November. The project team conducted outreach with stakeholders in the Route 21 Corridor to allow the placement of Cells on Wheels (COWs) in police/fire and other suitable facilities. In December, New Jersey and FirstNet successfully reached agreement on the Spectrum Manager License Agreement and the FirstNet board approved the license in mid-December. The license allows New Jersey to utilize the 700 mhz public safety spectrum for their LTE based deployable project. In addition, NTIA approved the revised project scope and approved the extension of the New Jersey BTOP project through September 2015. Upon approval, the BTOP project team began consulting with the FirstNet technical staff to exchange information and finalize technical specifications. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Based on the newly approved project scope focused on deployable assets, network miles will not apply to New Jersey moving forward. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | None. | None. | None. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | As a result of the changes engendered by the passage of the Middle Class Tax Relief Act and the creation of the FirstNet authority, New Jersey has revised the project to align with State and national (FirstNet) priorities. As the State and FirstNet have agreed on the spectrum lease, New Jersey will begin to define the subscribers who will be served by the deployable implementation. | See narrative above. | See narrative above. | See narrative above. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The project team plans to continue to review technical specifications with FirstNet team to develop Statement of Work to procure vendors for equipment purchases and system integration services. Additionally, the project team will continue outreach with stakeholders in the Route 21 Corridor to allow the placement of Cells on Wheels (COWs) in police/fire and other suitable facilities. The project team will also begin the process to identify appropriate locations for Cells on Wheels in Camden and Atlantic City; an initial coverage design will be created for locations identified. | Treasury, New Jersey Department of | None. | The New Jersey project team anticipates submission of the budget modification next quarter; however, submission is largely dependent upon final vendor selection. The project team is developing several Statements of Work to be distributed next quarter to select vendors for the project; however, review by Procurement and FirstNet technical team may delay release of the Statements of Work by March 31st, 2014. | TRUE
NT10BIX5570106 | 2010 | Q4 | Q4 - 2010 | The Pyramid Lake Paiute Tribe has made significant progress on the NEPA draft. The US Fish and Wildlife Service has informed the tribe's Environmental Department which is preparing the draft that they will be signing off without any requirements. A late notice by the State Historical Preservation Office for the state of Nevada informed us that they will be requiring a Class 1 and Class 3 survey due to the scale of the project. We are in the process of hiring the credentialed Cultural Resource Specialist to perform these surveys. The Environmental Department has otherwise completed the draft NEPA report which will be submitted by the six month deadline. We have been informed by the NTIA that this will not necessitate an extension for the draft report. After meeting with NITA program officers and senior grant officers during the NTIA broadband conference, our selection of the prime contractor during the application phase will meet their approval for our procurement procedures. The process for the formal agreement with our telecom for the acquisition of the section of dark fiber from the reservation boundary into Reno, NV is progressing. We have made contact with the telecom representative and the tribal attorney will be working with another law firm with expertise in this area. We have completed the job description for the Project Manager position and the personnel committee has approved the new classification. The tribal council is waiting on a progress report with the dark | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 0 | NA | There are three wholesale services projected with this network infrastructure. The first one is a shared 100 mbps shared service. The second one is a dedicated 10 mbps service and associated voice and video services. The third one is a fiber circuit without network data, video or voice services being provideds projected with this network infrastructure. The first one is a shared 100 mbps shared service. The second one is a dedicated 10 mbps service and associated voice and video services. The third one is a fiber circuit without network data, video or voice services being provided. | NA | 0 | 0 | 0 | 1 | NA | NA | NA | 100 mbps with 1 projected provider | 0 | 0 | 0 | 2 | NA | NA | NA | 100 mbps shared speed tier with 26 projected subscribers 10 mbps dedicated speed tier with 3 subscribers | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 2 | NA | NA | NA | NA | 10 mbps dedicated, with 0 subscribers possible 100 mbps shared, with 3 subscribers projected | We will also make available dedicated fiber connections. There has been some interest from Great Basin Internet Services and the Nevada Department of Transportation,but nothing is firm on this. | FALSE | NA | During the next quarter, we plan on completing the dark fiber acquisition contract with our telecom. Our NEPA report, with required the State Historic Preservation Office report will be completed including it's approval by the Pyramid Lake Paiute Tribal Council. The contract with our prime contractor is also expected to be completed. The tribe's project manager will be hired and the project manager's office as well as the paperwork for assigning the designated staging area should be completed. We also intend to have the paperwork for the site acquisition for two nodes near completion. | Pyramid Lake Paiute Tribe | The acquisition of the tribe's IRU for the dark fiber to Reno involves the tribe's attorney, and progress seems to have been hampered with the holiday season and the attorney's schedule. The EA draft plan is on schedule, but the late notification by the SHPO for the survey requirement has us pushing to get the RFP out. We estimate to have the mapping for the cultural resource specialist and the material for the SHPO ready in the next quarter. | Because the dark fiber acquisition negotiations with our telecom involved a prior agreement with the telecom that laid the fiber, there may be some delays due to attorney involvement with the current holder of those fiber lines. However it is anticipated that if delayed, the impact on the overall project will be minimal. We are still expecting to be on schedule with this. | TRUE
NT10BIX5570106 | 2011 | Q1 | Q1 - 2011 | We completed the fiber route path maps for the Cultural Survey. The certified cultural survey specialist was hired and the survey began before the end of the quarter. Tribal monitors for the survey work were also hired. The attorneys for the tribe have made progress with the tribe's fiber contracts. The telecommunications company agreed to honor the prior commitment by the company that installed the fiber across tribal land to provide the two strands and possibly increase it to four for maintenance purposes. They've also agreed in principle to extend the original agreement so that we can meet the 20 year requirements for fiber contracts. This should increase the value of the tribe's inkind match once we have this contract finalized and appraised. We met with the Nevada Department of Transportation to review the portions of the route that are on highway right of way. Initial response is that portion of our route should get approval provided the proper detailed design requirements are followed in the application | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 0 | NA | There are three wholesale services projected with this network infrastructure. The first one is a shared 100 mbps service. The second one is a dedicated 10 mbps service and associated voice and video services. The third one is a fiber circuit without network data, video or voice service being provided. | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | We will also make available dedicated fiber connections. There has been some interest from a Reno based internet service provider and the Nevada Department of Transportation, but nothing is firm on this. | FALSE | NA | We anticipate the completion of the Environmental Assessment. The Preliminary Reports from the Cultural Survey and the State Historical Preservation Office should be completed. The US Fish and Wildlife signoff should also be completed. We also expect the attorneys will have completed the fiber lease agreement for the existing fiber route. We will be initiating the final network design and accompanying maps and hope to have that portion covering the fiber route near completion. The submittal process for permits with the Tribe and the Nevada Department of Transportation should be underway. The submission and approval of our six month budget modification should be approved and allow us to have a project manager on board before the completion of the next quarter. | Pyramid Lake Paiute Tribe | The cultural survey process required by state historical preservation office is extensive and covers 44 miles of tribal land. Because the fiber route involves an old railroad bed, we had some issues in convincing them that it doesn't qualify for the federal registry due to prior modified use. This would have required an environmental impact statement on that portion of the route and would have effectively required re-routing of the fiber due to the lengthy process and costs associated with that process. The tribe is requiring additional monitoring of this process for cultural discoveries to address potential impacts to the Native American Graves Protection and Repatriation Act. As a partial result of these additional costs and time delays, we have had to put the hiring of a project manager on hold until a modification of the six-month budget can be completed. Another difficulty we've encountered, is the lengthy process in formalizing the tribe's access to its fiber rights on existing cable into Reno. The attorneys have made significant process, but we've incurred delays because one of the attorneys always has prior commitments. In addition, the NTIA's requirements for these indefeasible rights of use are complicating the contract. | The first challenge is getting the attorneys to complete the dark fiber lease agreement. The second challenge is completing the Environmental Assessment and getting the FONSI on schedule. The cultural survey specialist has indicated they will be able to provide a summary report by the middle of the next reporting period. Being able to keep up with the baseline schedule on all the right of way and permit approvals will be challenging. The six month budget mod needs to be approved so we have to overcome the delay in hiring the project manager. The challenge will be in getting this position filled soon enough before the end of the quarter so that they can have a significant impact on the project's progress. The last challenge we have is in getting the contract with our network design company in soon enough so that we can have the detailed designs needed to move forward on the department of transportation and tribal right of way approvals. | TRUE
NT10BIX5570106 | 2011 | Q2 | Q2 - 2011 | The cultural survey specialist completed the field survey and submitted a preliminary report. The planned fiber route is viable from this report with no significant findings. The tribe's cultural committee was part of the field survey process, using a tribal monitor for observation. They are also satisfied with the proposed fiber route and will recommend this route in a report for the tribal council. The US Fish & Wildlife Service issued a letter of concurrence for the project. We are reviewing the construction requirements pertaining to that letter. The attorneys for the tribe have made significant progress with the tribe's fiber contracts. The telecommunications company agreed to increase the fiber exchange to four strands for maintenance purposes. They've also agreed to extend the original agreement so that we can meet the 20 year requirement for fiber contracts. This should increase the value of the tribe's in kind match once we have this contract finalized and appraised. A request for quote was sent out and we hired a firm to conduct an appraisal of the fiber agreement. The federal program officer and federal grants specialist came out for a site visit. Agendas and timelines were established to accelerate the completion of the environmental assessment and approval of the construction contract. The tribe's Realty Department has begun review of the easements and right of way agreements on the fiber route. They are also initiating the request for quotes so that we may p | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance from baseline | No Variance from baseline | No Variance from baseline | There have been delays in the contract negotiations for the tribe's dark fiber exchange. However, the request for quote to have an appraisal was done just before quarter's end, and the appraisal and contract for the fiber will be completed before the end of the next quarter | No Variance from baseline | No Variance from baseline | No Variance from baseline | No Variance from baseline Total Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) There have been delays in the contract negotiations for the tribe's dark fiber exchange. However, the request for quote to have an appraisal was done just before quarter's end, and the appraisal and contract for the fiber will be completed before the end of the next quartel Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) There have been delays in the contract negotiations for the tribe's dark fiber exchange. However, the request for quote to have an appraisal was done just before quarter's end, and the appraisal and contract for the fiber will be completed before the end of the next quarter | 0 | 0 | 0 | NA | There are three wholesale services projected with this network infrastructure. The first one is a shared 100 mbps service. The second one is a dedicated 10 mbps service and associated voice and video services. The third one is a fiber circuit without network data, video or voice service being provideds projected with this network infrastructure. The first one is a shared 100 mbps service. The second one is a dedicated 10 mbps service and associated voice and video services. The third one is a fiber circuit without network data, video or voice service being provided. | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | No Variance from baseline | No Variance from baseline | No Variance from baseline | No Variance from baseline | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | The primary accomplishment will be the completion and appraisal of the tribes IRU (indefeasible right to use) for it's dark fiber. The second primary accomplishment will be the completion of the construction contract. We anticipate significant procurement activity and the completion of the network outside plant design, and the near completion of the engineering designs for the Nevada State Department of Transportation. We also expect to have tribal clearance on all easements, right of ways, and appraisal of the tribes contribution of land for the project. Another significant accomplishment we expect to complete is the environmental assessment. | Pyramid Lake Paiute Tribe | The first challenge has been getting the environmental assessment completed. The preliminary report wasn't sufficient for the State Historical Preservation Office to issue a letter of concurrence. They cited section 106 of the Federal Historical Preservation Act requiring a complete inventory of sites that may have eligibility for the federal registry. This report is significant in size, and the completion date isn't expected until well into the next quarter. Also at issue is a late finding in the environmental assessment specifying construction shutdown for a four month period next spring due to bird migration. Because it wasn't specified in the US Fish & Wildlife's letter of concurrence, we are investigating this issue and its impact. Although the tribe's fiber right's negotiations have progressed, they weren't far enough along to complete the appraisal for our in-kind match. This situation did change at the end of the quarter, and this should be rectified. The contract with our contractor has not progressed satisfactorily and so our engineering designs are delayed, and this impacts our right of way approvals from the Nevada State Department of Transportation. The BTOP program stepped in during their site visit at the end of the current quarter and has provided significant help with us in creating aggressive time lines to accomplish these tasks. | There is still an issue with the environmental assessment regarding a construction blackout from March 31 through August 31 in 2012. With the help of BTOP, we are trying to mitigate this issue by providing for a biologist during construction, if occurring within this time frame. The reason it may become a problem is that it could impact construction costs and BTOP's two-thirds spending requirement by the end of the second year of the grant period. The timeline for completing the contract with our construction partner might prove a little aggressive. The reason is that there are tribal issues around sovereignty and TERO that must be implemented. There is also a requirement that this contract be approved by the Tribal Council, and they will require sufficient time for review. Our in kind match is temporarily stalled by legal issues regarding the failure of the fiber communications company, which provided the dark fiber in exchange for easements in consideration of traversing tribal lands with their fiber installation, and Nevada Department of Transportation to obtain proper documentation for the easement of their installation. The Bureau of Indian Affairs is requiring the proper recording of the easement includes a survey of the existing route. The appraisal was completed for the tribe's in kind match of the fiber indefeasible right to use and it is appraised at $2.7 million. The tribe is also in the process of posting request for quotes for the appraisal of the tribe's in kind | TRUE
NT10BIX5570106 | 2011 | Q3 | Q3 - 2011 | The environmental assessment has been completed and submitted. The cultural assessment has been completed and submitted. The IRU fiber is progressing and the contract is expected to be signed in the next quarter. The appraisal of the IRU fiber has been completed and is valued at 2.7 million dollars. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | We have fallen behind on the baseline due to delays in the Indefeasible Right to Use contract. We expect this to be caught up in the next quarter. | NA | NA | NA | NA | NA | NA | 0 | 0 | 0 | NA | There are three wholesale services projected with this network infrastructure. The first one is a shared 100 mbps shared service. The second one is a dedicated 10 mbps service and associated voice and video services. The third one is a fiber circuit without network data, video or voice services being provided. Pricing plans are contingent on the network recurring costs that will be negotiated over the next two quarters. | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | The FONSI will be issued. The Praxis contract and the IRU contract will be signed and submitted to council for approval. This will enable us to complete 40 leased network miles. The three node sites will be prepared for construction. The procurement process will start. The lay down yard will be constructed. Construction may start in the last month of next quarter contingent on the contracts being approved. Route engineering should be complete. A high level network design will be complete. Their will be a tangible plan to make up the in-kind shortfall. The monitoring plan will be complete. We may have up to six network miles deployed if we start construction by the middle of the next quarter as planed. We will not have any Community Anchor Institutions connected; but this is in line with the baseline data. We do not expect any signed agreements with broadband wholesalers or last mile providers at this time in accordance with our baseline data. | Pyramid Lake Paiute Tribe | The acquisition of the tribe's IRU for the dark fiber to Reno, and the Praxis contract, involves the tribe's attorney. Progress has been made and we expect the contracts to be complete in the beginning or the next quarter. | The contract with Level 3 for the IRU is being worked out with the attorneys. This may take a little longer than expected due to negotiations about the recurring costs. Once the Praxis contract is signed we will be able to start the procurement process. We may see delays in getting fiber due to availability from the manufacturers. The praxis contract and the IRU contract may slow down the time it will take to get back on track. | TRUE
NT10BIX5570106 | 2011 | Q4 | Q4 - 2011 | The FONSI has been issued. The contract with Praxis has been completed, approved by council, and is ready to be signed. Significant progress was made with Level Three and the IRU agreement. We are expecting to have a contract in the next quarter. The three node sites are ready for construction. Route engineering has been completed. The high level network design is complete. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Delays in the signing of the contract with Praxis has put us behind on this. We expect to have the contract signed in the next quarter. When the contract is signed it will take about 2-4 months to get caught up. | We have fallen behind on the baseline due to delays in the Indefeasible Right to Use contract with Level3. We are engaged and plan to have this caught up in the next quarter. | NA | NA | Delays in the signing of the contract with Praxis has put us behind on this. We expect to have the contract signed in the next quarter. When the contract is signed it will take about 2-4 months to get caught up. | NA | NA | NA | 0 | 0 | 0 | NA | There are three wholesale services projected with this network infrastructure. The first one is a shared 100 mbps shared service. The second one is a dedicated 10 mbps service and associated voice and video services. The third one is a fiber circuit without network data, video or voice services being provided. Pricing plans are contingent on the network recurring costs that will be negotiated over the next two quarters. | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | The Praxis contract and the IRU contract should be signed if a bond is acquired. If we need to apply for a waiver with the NTIA the contract will not be signed until the waiver is approved. This means that construction may not begin before the end of the next quarter unless the NTIA is able to expedite the waiver request. The procurement process will start as soon as the contract is signed. The lay down yard will be constructed. We will have a definitive construction project plan that will show when we will be back on track with the Base Line Data Sheets as soon as these issues are resolved. | Pyramid Lake Paiute Tribe | The tribe's IRU for the dark fiber to Reno is with the lawyers and the BIA. The BIA is reviewing the documentation at this time. Once the BIA gives their approval we will be able to complete the contract with Level Three. We were able to perform a site survey at Level Threes' POP in Reno. The information gathered will further assist Praxis and us in the network design. The Praxis contract will be signed as soon as the bonding issue is resolved. Progress has been made and we expect the contracts to be complete in the beginning or the next quarter. | The contract with Level 3 for the IRU is being worked out with the attorneys. Once the Praxis contract is signed we will be able to start the procurement process. The praxis contract is holding up the project and may need a waiver to get us back on track. | TRUE
NT10BIX5570106 | 2012 | Q1 | Q1 - 2012 | BIA is working out the details on the IRU agreement and we are expecting to have a contract in the next quarter. The appraisal of the three node sites has began. The route has been staked out and labeled. We have come together and worked out a base plan of the sustain ability. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Delays in the signing of the contract with Praxis has put us behind on this. We expect to have the contract signed in the next quarter. When the contract is signed it will take about 2-4 months to get caught up. | We have fallen behind on the baseline due to delays in the Indefeasible Right to Use contract with Level3. We are engaged and plan to have this caught up in the next quarter. | NA | NA | Delays in the signing of the contract with Praxis has put us behind on this. We expect to have the contract signed in the next quarter. When the contract is signed it will take about 2-4 months to get caught up. | NA | NA | NA | 0 | 0 | 0 | NA | There are three wholesale services projected with this network infrastructure. The first one is a shared 100 mbps shared service. The second one is a dedicated 10 mbps service and associated voice and video services. The third one is a fiber circuit without network data, video or voice services being provided. Pricing plans are contingent on the network recurring costs that will be negotiated over the next two quarters. | NA | 0 | 0 | 0 | 0 | Delays in signing the contract with Praxis have us behind on this. We are currently identifying providers in the area. | Delays in signing the contract with Praxis have us behind on this. We are currently identifying providers in the area. | Delays in signing the contract with Praxis have us behind on this. We are currently identifying providers in the area. | Delays in signing the contract with Praxis have us behind on this. We are currently identifying providers in the area. | 0 | 0 | 0 | 0 | Delays in signing the contract with Praxis have us behind on this. | Delays in signing the contract with Praxis have us behind on this. | Delays in signing the contract with Praxis have us behind on this. | Delays in signing the contract with Praxis have us behind on this. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | Delays in signing the contract with Praxis have us behind on this. | Delays in signing the contract with Praxis have us behind on this. | Delays in signing the contract with Praxis have us behind on this. | Delays in signing the contract with Praxis have us behind on this. | Delays in signing the contract with Praxis have us behind on this. | NA | FALSE | NA | The Praxis contract and the IRU contract should be signed. The procurement process will start. Construction will start and we will have a definitive construction project plan that will show when we will be back on track with the Base Line Data Sheets. A. Miles deployed = six B. CAI's connected in next quarter = Zero C. Agreements signed in next quarter = Zero | Pyramid Lake Paiute Tribe | The tribe's IRU for the dark fiber to Reno is with the lawyers and the BIA. The BIA is reviewing the documentation at this time. Once the BIA gives their approval we will be able to complete the contract with Level Three. The Praxis contract will be signed as soon as the bonding issue is resolved. Progress has been made and we expect the contracts to be complete in the next quarter. | The contract with Level 3 for the IRU is being worked out with the attorneys and BIA. Once the Praxis contract is signed we will be able to start the procurement process. | TRUE
NT10BIX5570106 | 2012 | Q2 | Q2 - 2012 | We were able to get the construction contract signed with the contractor. The IRU is completed and waiting for Council approval which will get us on track with our match matrix. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Once the Storm Water pollution prevention is approved by the EPA we will be able to begin construction. It will take 2-3 months to get back on track with the base line. | We have fallen behind on the baseline due to delays in the Indefeasible Right to Use / Dark Fiber contract. We will be presenting the contract to the Tribal Council in the beginning of the next quarter. | NA | NA | The construction will start as soon as the Storm Water Pollution Prevention Plan is approved by the Environmental Protection Agency. We expect it will take about 2-4 months to get caught up. | NA | NA | NA | 0 | 0 | 0 | NA | There are three wholesale services projected with this network infrastructure. The first one is a shared 100 mbps shared service. The second one is a dedicated 10 mbps service and associated voice and video services. The third one is a fiber circuit without network data, video or voice services being provided. Pricing plans are contingent on the network recurring costs that will be negotiated over the next two quarters. | NA | 0 | 0 | 0 | 0 | We are currently identifying providers in the area. | We are currently identifying providers in the area. | We are currently identifying providers in the area. | We are currently identifying providers in the area. | 0 | 0 | 0 | 0 | We expect to have the 29 CAI's hooked up in the next two quarters. | There are approximately 6 subscribers that do not have any access to the internet. | There are approximately 23 subscribers that will gain improved bandwidth compared to the T1's they are currently using. | We will be able to deliver 10 - 100 Mb/second to our subscribers. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 2 | 0 | 0 | 0 | 0 | There are two businesses that we are passing, the I 80 Smoke Shop and the Nixon convenience store. | NA | NA | NA | NA | NA | FALSE | NA | The IRU and Easement will be complete and we will begin construction in the coming quarter. By the end of the next quarter we will be close to being back on track with the baseline. The CAI's will begin to be connected in the quarter after the next. We dont expect to have any Broad Band agreements signed by the end of the next quarter. | Pyramid Lake Paiute Tribe | The tribe's IRU for the dark fiber to Reno is ready for council approval and will be heard by the Tribal Council in the beginning of the next quarter. The BIA is reviewing the easement documentation at this time. Once the BIA gives their approval of the easement we will be able to complete the contract. | We do not expect any issues or challenges during the next quarter. | TRUE
NT10BIX5570106 | 2012 | Q3 | Q3 - 2012 | Construction has started and we have deployed twenty six miles of inter duct and eleven miles of fiber. | 11 | 32 | 0 | 0 | 11 | 0 | 0 | 0 | We have deployed 11 miles of fiber and expect to get on track with the baseline data in the next quarter. | We have fallen behind on the baseline due to delays in the Indefeasible Right to Use / Dark Fiber contract. We will be presenting the contract to the Tribal Council in the beginning of the next quarter. | NA | NA | The delays in starting the construction have us behind but expect to be caught up with the base line data in the next two quarters. | NA | NA | NA | 0 | 0 | 0 | NA | There are three wholesale services projected with this network infrastructure. The first one is a shared 100 mbps shared service. The second one is a dedicated 10 mbps service and associated voice and video services. The third one is a fiber circuit without network data, video or voice services being provided. Pricing plans are contingent on the network recurring costs that will be negotiated over the next two quarters. | N/A | 0 | 0 | 0 | 0 | We are currently identifying providers in the area. | We are currently identifying providers in the area. | We are currently identifying providers in the area. | We are currently identifying providers in the area. | 0 | 0 | 0 | 0 | We expect to have the 29 CAI's hooked up in the next two quarters. | There are approximately 6 subscribers that do not have any access to the internet. | There are approximately 23 subscribers that will gain improved bandwidth compared to the T1's they are currently using. | We will be able to deliver 10 - 100 Mb/second to our subscribers. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 2 | 0 | 0 | 0 | 0 | There are two businesses that we are passing, the I 80 Smoke Shop and the Nixon convenience store. | NA | NA | NA | NA | NA | FALSE | NA | We are planning on having another 27 miles of substructure in the ground. We have had some challenges with the terrain that has slowed our progress and we do not expect to connect any CAIs' for another quarter. We do not plan to have any provider agreements signed in the next quarter. | Pyramid Lake Paiute Tribe | The tribe's IRU for the dark fiber to Reno has been approved by council and the BIA is reviewing the easement documentation at this time. Once the BIA gives their approval the easement and IRU will be complete. | We do not expect any issues or challenges during the next quarter. | TRUE
NT10BIX5570106 | 2012 | Q4 | Q4 - 2012 | We have a sustainability consultant that is working with us and we are exploring our options as to what types of businesses would be interested in connecting to our network. We had a site visit with our Federal Program Officer / NTIA that helped us continue our focus on completing the project. Construction has continued through the last quarter. We have deployed 28.45 miles of inner duct and 21.04 miles of fiber optic cable on the back bone portion of our network. | 21 | 33 | 0 | 0 | 21 | 0 | 0 | 0 | We have deployed 21 miles of fiber and expect to get on track with the baseline data in the next quarter. | We have fallen behind on the baseline due to delays in the easement agreement. We will be presenting the agreement to the Tribal Council in the beginning of the next quarter. The network miles as stated in the IRU is 33 Miles which is less than originally anticipated. | NA | NA | Construction started late causing us to be behind but we expect to be caught up in the next two quarters. | NA | NA | NA | 0 | 0 | 0 | NA | There are three wholesale services projected with this network infrastructure. The first one is a shared 100 mbps shared service. The second one is a dedicated 10 mbps service and associated voice and video services. The third one is a fiber circuit without network data, video or voice services being provided. Pricing plans are contingent on the network recurring costs that will be negotiated over the next two quarters. | NA | 0 | 0 | 0 | 0 | We are currently identifying providers in the area. | We are currently identifying providers in the area. | We are currently identifying providers in the area. | We are currently identifying providers in the area. | 0 | 0 | 0 | 0 | We expect to have the 29 CAIs' hooked up in the next two quarters. | There are approximately 6 subscribers that do not have any access to the Internet. | There are approximately 23 subscribers that will gain improved bandwidth compared to the T1's they are currently using. | We will be able to deliver 10-100Mbs to our subscribers. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 2 | 0 | 0 | 0 | 0 | There are two businesses that we are passing but are looking into the possibility of hooking them up as customers. | NA | NA | NA | NA | NA | FALSE | NA | In the next quarter we expect to have all of our back bone substructure in place which equals about 40 miles. We are expecting to have all of our back bone fiber in the ground by the end of the next quarter. We are planning on having our node buildings in place and have the electronics ordered and possibly installed by the end of the next quarter. The IRU should be completed by the end of the next quarter. We do not expect to hook up any CAIs in the next quarter. We do not plan on having any signed provider agreements in the next quarter. | Pyramid Lake Paiute Tribe | The Bureau of Indian Affairs has approved the easement documentation and is sending us support documentation to go into the easement packet for council approval. W are expecting to take it before council early in the next quarter. | We do not foresee any challenges or issues. | TRUE
NT10BIX5570106 | 2013 | Q1 | Q1 - 2013 | We have continued construction and are close to finishing the back bone installation. | 35 | 33 | 0 | 0 | 35 | 0 | 0 | 0 | We have placed 35 miles and expect to be on track with the baseline data in the next quarter. | We are scheduled to our IRU to council on May 3rd 2013. | NA | NA | We have placed 35 miles and expect to be on track with the baseline data in the next quarter. | NA | NA | NA | 0 | 0 | 0 | NA | There are three wholesale services projected with this network infrastructure. The first one is a shared 100 mbps shared service. The second one is a dedicated 10 mbps service and associated voice and video services. The third one is a fiber circuit without network data, video or voice services being provided. Pricing plans are contingent on the network recurring costs that will be negotiated over the next two quarters. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | We have the substructure to 23 of the 29 CAIs and expect to have the 29 CAIs spliced into the backbone in the next quarter. | There are approximately 6 subscribers that do not have any access to the Internet. | There are 23 subscribers that will gain improved bandwidth compared to the T1's they are currently using. | We will be able to deliver 10-100Mbs to our subscribers. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 2 | 0 | The two businesses reported as passed in the last quarter are now scheduled to be connected. | NA | NA | We have two government businesses that will receive improved access. | NA | NA | FALSE | NA | During the next quarter we expect to have the network back bone and laterals to be constructed; approximately 44 miles. We plan on having 27 CAI's and the 2 businesses connected by the end of the next quarter. We plan to have one broadband wholesaler provider agreement signed by the end of the next quarter. We are expecting the network electronics to be delivered and installed in the next quarter. | Pyramid Lake Paiute Tribe | We have had some challenges with the various types of rocky terrain. Our contractor has brought in the necessary equipment to overcome these challenges but progress has been slowed as a result. We are expecting to have all of the backbone completed in the next quarter and will be back on track with the baseline data. | We do not forecast any challenges or issues in the next quarter. | TRUE
NT10BIX5570106 | 2013 | Q2 | Q2 - 2013 | We have continued construction and are close to finishing the back bone installation. We experienced a slow down due to the absence of construction during the migratory bird season which is scheduled to end July 15. | 38 | 33 | 0 | 0 | 38 | 0 | 0 | 0 | We have placed 38 miles and expect to be on track with the baseline data in the next quarter. | The IRU is complete. | NA | NA | We have placed 38 miles and expect to be on track with the baseline data in the next quarter. | NA | NA | NA | 0 | 0 | 0 | NA | There are three wholesale services projected with this network infrastructure. The first one is a shared 100 mbps shared service. The second one is a dedicated 10 mbps service and associated voice and video services. The third one is a fiber circuit without network data, video or voice services being provided. Pricing plans are contingent on the network recurring costs. | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 2 | 0 | 2 | 2 | The two tribal businesses reported last quarter have been connected. | They are set to be turned up in the next quarter. | NA | The 2 connections are being served with a 56k modem and will be receiving 10Mb. | We are offering 10Mbps to each and they can scale as needed from there up to 100Mbps. | NA | FALSE | NA | The backbone of the network and all of the CAIs' will be up and running and the network will allow connections in Wadsworth Sutcliffe and Nixon, and Reno NV. | Pyramid Lake Paiute Tribe | The Migratory Bird season was our main setback this quarter. Progress along the 446 highway is still slow as the contractor is having trouble getting through the rock. | We do not for see any challenges or issues in the next quarter. | TRUE
NT10BIX5570106 | 2013 | Q3 | Q3 - 2013 | During this quarter all outside plant construction was completed. Restoration and reseeding of the trenching areas were underway and mostly completed. The connection with the network provider was also completed, and the fiber connections betwee the three towns and the POP in Reno were verified. Most of the CAIs were connected, and testing of the fiber connections was nearly completed. The data center server system was delivered and nearly all of the software was ordered. | 44 | 33 | 0 | 0 | 44 | 0 | 0 | 0 | The fiber backbone construction was completed | NA | NA | NA | The project's new fiber backbone construction miles are completed | NA | NA | NA | 0 | 0 | 0 | NA | There are 2 wholesale services projected with this network infrastructure. The first one is the "Reno Circuit. A fiber circuit without network data, video or voice services included. The second one is "Metro E Services" which is a dedicated 100 mbps service. These services and pricing are described in the attachment : PLPTPricingPlan . The other three services listed in the plan are retail services. | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 18 | 4 | 14 | 3 | Due to damage to two CAI buildings, the two CAIs are awaiting connections to new modular office buildings. The conduit is trenched up to where the buildings are being placed, but the equipment is not connected yet. The other 5 are undergoing troubleshooting for equipment and splicing issues, but are physically installed so they are not classified as connected yet. | No prior service for these subscribers | These subscribers had 768kb or better previous service. | All CAIs and businesses being connected are retail subscribers. There are three retail service levels. All subscribers will subscribe to shared 100 mbps tier service during the first year. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 2 | 0 | 2 | 2 | NA | No variance | NA | No variance | They will be subscribing to the 100 mbps shared service | NA | FALSE | NA | We plan on having seven more CAIs connected in this quarter. We plan on having the datacenter server, support software and the network running for all CAIs by the end of the next quarter. We do not anticipate having any wholesale/last mile provider agreements signed in the next quarter. | Pyramid Lake Paiute Tribe | The primary issues impacting the construction process were a two mile stretch of rock that became impossible for the contractor to penetrate to the depth of 36 inches. Approvals from the state to use a concrete slurry method for sealing the trench were finally obtained. In addition, the network provider was not able to deliver fiber splicing for connection to our leased fiber and the drop connection and the colocation facility in a timely manner. We were also waiting for approval for the consolidation of equipment pertaining to our datacenter and that delay impacted the purchasing and delivery of key equipment and software. | The primary challenge will be the network configuration of the VLANs and the deployment of the data center servers and software. Coordination among the tribe's vendors are needed for these complex tasks. However, we have already been developing the plan and configuration assignments with a schedule, so we do expect this to be completed before the end of the quarter. | TRUE
NT10BIX5570106 | 2013 | Q4 | Q4 - 2013 | This quarter we completed testing of the fiber connections to the CAIs. All except one were connected. This is because the setup of the modular building is not scheduled until January 2014. Installation of the data center system equpment and the rest of the networking equipment was completed and software installation and configuration of the network system are nearly done. | 44 | 33 | 0 | 0 | 44 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 0 | NA | There are 2 wholesale services projected with this network infrastructure. The first one is the "Reno Circuit. A fiber circuit without network data, video or voice services included. The second one is "Metro E Services" which is a dedicated 100 mbps service. These services and pricing are described in the attachment : PLPTPricingPlan . The other three services listed in the plan are retail services. | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 24 | 4 | 20 | 3 | One CAI has the replacement building ready to go in. This will be connected next quarter | No prior service for these subscribers | These subscribers had previous service less that 768kb | All CAIs and businesses being connected are retail subscribers. There are three retail service levels. All subscribers will subscribe to shared 100 mbps tier service during the first year. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 2 | 0 | 2 | 2 | NA | No variance | NA | No variance | They will be subscribing to the 100 mbps shared service | NA | FALSE | NA | We plan to have one more CAI connected and to have completed the project. | Pyramid Lake Paiute Tribe | The primary obstacle has been equipment failure at some CAIs and configuration errors. These issues involve two different contractors to resolve, so some coordination difficulties are expected. | The challenge will be completing all of the network and server configurations by the end of the grant. | TRUE
NT10BIX5570106 | 2014 | Q1 | Q1 - 2014 | We have completed all connections to the CAIs and we have also completed the purchasing and installation of all equipment. Because of the new network and datacenter, services to the CAIs are now being delivered at optimum levels. The network design has proven to be robust, and the equipment purchased is delivering efficiently as envisioned with the design requirements . Because of the quality and durability of this equipment, it should be reliable for many years to come. Power outages at various times have had no impact on the network system due to the redundant features built into the design. The ability to expand the capacity and maintain a high level of performance was built into the design, and this will enable the tribe to service the needs of the community for many years. Most importantly, the infrastructure will be easily capable of supporting a complete last mile build out as we move into the next phase of bringing home services to these rural communities. It is clear that only with the funding by BTOP for this middle mile project will the last mile phase be possible. Although still in the early phases of sustainability, the economic growth of this rural area will only be possible because of the capability of the fiber network to deliver advance technologies. | 44 | 33 | 0 | 0 | 44 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 0 | NA | There are 2 wholesale services projected with this network infrastructure. The first one is the "Reno Circuit. A fiber circuit without network data, video or voice services included. The second one is "Metro E Services" which is a dedicated 100 mbps service. These services and pricing are described in the attachment : PLPTPricingPlan . The other three services listed in the plan are retail services. There has been a modification to the tiered 10 mbps plan with reduced rates for incremental purchases up to 100 mbps. This is specified in the new pricing plan document that is being submitted. | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 25 | 4 | 21 | 3 | NA | No Prior Service for these subscribers | These subscribers had previous service less that 768kb | All CAIs and businesses being connected are retail subscribers. There are three retail service levels. All subscribers will subscribe to shared 100 mbps tier service during the first year. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 2 | 0 | 2 | 2 | NA | No Variance | NA | No variance | They will be subscribing to the 100 mbps shared service | NA | FALSE | NA | NA | Pyramid Lake Paiute Tribe | We had difficulty with some of the network configurations. We also had our last CAI on hold due to the construction of the building, but we were able to complete the installations before the end of the grant. | NA | TRUE
NT10BIX5570107 | 2010 | Q4 | Q4 - 2010 | This quarter's activities was focused on the Environmental Assessment (EA). We hired a consultant to assist with the final report and worked with the United States Corps of Engineers and State Historical Preservation Board. As of the writing of this report, it appears that the Texas Pipes project will meet the February deadline for final submission of the EA. Members of the Texas Pipes team made a presentation at a statewide network meeting. All of the internal coordination with System Counsel, Purchasing, Facilities Construction, and the Office of Sponsored Research necessary to facilitate the project was completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 5 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | During the next quarter, our goal is to complete the FONSI process. We are beginning the formal detailed engineering phase and anticipate completion during this quarter. Construction should begin on the College Station (Riverside Campus), Corpus Christi, San Antonio and Stephenville fiber builds. We also intend to order and install DWDM equipment on the Waco-to-Temple and Commerce-to-Dallas links using existing fiber optic cable. We extended a job offer to a managing engineer for this project, and she is going to start during this next quarter. We are currently working on five sub-recipient agreements, which should be approved in the next quarter. We also anticipate planning a fiber lighting event (public awareness) during the second quarter if we complete one of the segments. | Texas A&M University | During this quarter we experienced the unfortunate death of a key member of the Texas Pipes team. This has required us to retrain new team members, re-establish roles and change access to various information systems. This has caused delays with the submission of certain reports. Fortunately, NTIA and Booz Allen Hamilton staff were very supportive in terms of establishing new accounts when needed and in explaining procedures to new personnel that had previously been explained. | No challenges or issues anticipated at this time | TRUE
NT10BIX5570107 | 2011 | Q1 | Q1 - 2011 | During this quarter we completed and submitted the draft Environmental Assessment. Upon having received the issues matrix back from the NTIA, submitted requested modifications and resubmitted the EA. We anticipate FONSI in mid May. The TAMU team and the engineers visited San Antonio, Corpus Christi, Stephenville, Texarkana, and Killeen to complete the engineering sections of this project. Seventy two percent of the engineering is complete at this time and material is on order for the first phase of construction. A few of the permits have also been completed and submitted for approval. We received approval of the Sub-Recipient agreement from TAMU counsel and have the terms under negotiation with two of the sub-recipients. We also presented at a State Wide network meeting in February on the Texas Pipes project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We anticipated some completion at this time but were delayed due to a lack of FONSI. | No Variance | No Variance | No Variance | No Variance | N/A | N/A | No Variance | 0 | 6 | 0 | N/A | N/A | We anticipate that a portion of the network will be run by our sub-recipients but no agreements have been signed at this time. | 0 | 0 | 0 | 0 | No Variance | Subrecipient agreements have taken longer to prepare than anticipated. We anticipate being on schedule by Q3-2011. | No Variance | No Variance | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | None at this time | FALSE | N/A | During this next quarter we will receive the FONSI, and complete the fiber construction of the Riverside, San Antionio and a portion of the Corpus Christi networks. In addition we will order the DWDM equipment for the Waco and Commerce sites. We also intend to complete all engineering and will submit most of the permits. Permits will not be submitted for engineered projects until 120 days before anticipated construction to avoid permit expiration issues. | Texas A&M University | We received some guidance and useful information at a recent NTIA workshop in Washington D.C. regarding legal issues around telephone pole contact permits. | The only significant issues anticipated at this time are the completion and agreement of the sub-recipient agreements and permitting/licensing. . | TRUE
NT10BIX5570107 | 2011 | Q2 | Q2 - 2011 | During this quarter we completed and submitted the Final Environmental Assessment. Upon having received request for additional detail regarding environmental issues from previous matrix from the NTIA, submitted requested modifications and additional tribal responses resubmitted the EA. We received FONSI on 7 JUNE. The TAMU team and the engineers visited Corpus Christi, Kingsville, and Canyon to complete the engineering sections of this project. Eighty five percent of the engineering is complete at this time and material is on order for the first phase of construction. A few of the permits have also been completed and submitted and approved. Pole attachment agreements have been executed with four of the electric utility companies. Site construction has commenced on the Riverside segment. We received approval of the Sub-Recipient agreement from TAMU counsel and have the terms under negotiation with three of the sub-recipients. | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction commenced 06/15/2011after receipt of FONSI 06/07/2011 | No Variance | Behind schedule due to delays in receiving the FONSI. | No Variance | Behind schedule due to delays in receiving the FONSI. | N/A | N/A | Behind schedule due to delays in receiving the FONSI. | 0 | 6 | 0 | N/A | N/A | We anticipate that a portion of the network will be run by sub-recipients but no agreements have been signed at this time. | 0 | 0 | 0 | 0 | No Variance | Sub-recipient agreements have taken longer to prepare than anticipated. We anticipate being on schedule by Q3-2011. | No Variance | No Variance | 0 | 0 | 0 | 0 | Behind schedule due to delays in receiving the FONSI. | Behind schedule due to delays in receiving the FONSI. | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | None at this time | FALSE | N/A | With the receipt of the FONSI on 06/07/2011 we were able to begin construction on Riverside. We anticipate completion of construction on Riverside, San Antonio and portions of Corpus Christi networks and TAMU Central TX. We anticipate completing all engineering and TXDOT lease agreements for the remainder of the project sites. | Texas A&M University | 2a. Actual expenditures reported on final page do not accurately reflect the work completed. We anticipate invoices and payments for work completed in this quarter to be processed in the next quarter. 2d. Negotiating access to ROW with TxDOT utilizing their Lease Agreement process for non-Utility ROW access. 2e. Aerial construction in San Antonio pending receipt of Certificate of Insurance from Verizon's Carrier | N/A | TRUE
NT10BIX5570107 | 2011 | Q3 | Q3 - 2011 | During this quarter we completed fiber construction on the Riverside and San Antonio segments. Lease agreements document with TxDOT was finalized for use as template for future districts. All railroad Permit applications are in progress. Construction commenced late September on the Killeen segment. Efforts to complete the engineering were increased due to the supplier issues for manufacturer acquisition of materials required to fulfill our orders for Fiber optic cable well in advance of our immediate need. Approximately 90 percent of the engineering is completed. Progress is being made on the three sub recipient agreements. | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | Construction delays on the 2.54 mile San Antonio segment due to City Permitting issues. | N/A | Behind Schedule due to Permitting Delays, Construction delays and re engineering delays | N/A | Behind Schedule due to Permitting Delays, Construction delays and re engineering delays | N/A | N/A | N/A | 1 | 6 | 0 | N/A | N/A | We anticipate that a portion of the network will be run by sub-recipients with one agreement signed at this time. | 0 | 0 | 0 | 0 | No Variance. | Sub-Recipient agreements have taken longer than anticipated. | No Variance | No Variance | 4 | 3 | 1 | 2 | Permits and Lease agreements have taken longer than anticipated | Permits and Lease agreements have taken longer than anticipated | Permits and Lease agreements have taken longer than anticipated | 1 Gig and 10 Gig | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | None at this time | FALSE | N/A | We anticipate completion of construction on the Killeen and Kingsville segments and commencing site preparation for construction on Texarkana. We anticipate completion of all engineering and resolution of permitting with Railroad Utilities, TxDOT and local authorities having jurisdiction. We anticipate approximately 10.1 additional miles of fiber and/or conduit will be deployed and an additional three CAI's added (TAMU Central Nursing School, TAMU Central New Campus and TAMU Kingsville). | Texas A&M University | 2d Application for TxDOT Permits is taking longer than anticipated. 2e Road widening project requiring coordination and approval from City Engineering Office. 2f Additional pole attachments for Killeen as a result of design change from buried to aerial placement has caused delays 2g Availibility of Materials to manufacturers impacted by natural disasters in Japan and other logistics 2h Impacted by availibility of materials and based on miles deployed, construction delays due to permitting delays 2i Impacted by availibility of materials and based on miles deployed, Construction delays due to permitting delays and reengineering. 2j Testing is impacted by our delays in deployment. 2a-2k The completion percentages are based on project progress versus expenditures. This more accurately reflects the project status at this time. | 2d Allowing for unknowns with permitting on a district by district basis affects the ability to be 100% at this time 2e Allowing for unknowns with permitting on a district by district basis affects the ability to be 100%at this time 2f Allowing for unknowns with ermitting on a district by district basis affects the ability to be 100% at this time | TRUE
NT10BIX5570107 | 2011 | Q4 | Q4 - 2011 | Approval of TXDOT for Killeen permit allowed us to begin aerial construction of the TAMU Central project segment. The TAMU Kingsville project fiber construction , testing and turn up was completed with the addition of two CAI's. 13 of the 14 TxDOT Permits submitted and approved for Texarkana Project. | 13 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 8 mi. Riverside, 2.54 mi San Antonio,.6 mi Kingsville, 1 mi, Killeen (permit and construction delays created variance) | N/A | None at this time (permit and construction delays created variance) | N/A | 8 mi. Riverside, 2.54 mi San Antonio,.6 mi Kingsville, 1 mi, Killeen (permit and construction delays created variance) | N/A | N/A | None completed at this time (permit and construction delays created variance) | 2 | 5 | 8 | Peoples Telephone and Texas Lone Star Network | None at this time. | We anticipate that a portion of the network will be run by sub-recipients. | 0 | 0 | 0 | 0 | Sub-recipient sites not constructed due to permit delays | Sub-recipient agreements have taken longer than anticipated. | N/A | N/A | 8 | 8 | 0 | 2 | Permit delays | Permit procedures are unique to each TxDOT district in the state, also other permitting agencies have their own operational procedures and guidelines. City, County, Railroad and Utility pole attachments are dependent on a coordinated effort with other utilities in the area. Our approach with these various agencies is cooperative and proactive while making them aware of our project time line and our sense of urgency. | N/A | 1 Gig and 10 Gig | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | None at this time. | FALSE | N/A | Construction completion with fiber deployed at TAMU Central Campus at Killeen. TxDOT lease agreements executed for Texarkana, Prairie View and Corpus Christi project sites. Railroad permits executed for Corpus Christi and Comanche (Tarleton Project). We project that in the quarter ending March 2012 one new agreement will be executed, an additional 20 miles of fiber will be constructed and one new CAI will be connected. | Texas A&M University | 2a-The percent complete is based on current expenditures but the overall project completion is 20%. Expenditures are lagging progress because of invoice delays. The project progress is behind the baseline projections due to the lack of availability of materials to manufacturers and suppliers to our chosen vendors. This has been resolved in recent quarters but the delays impacted the overall project schedule. Additionally, the effort required for a non utility agency such as Texas A&M University, to obtain the required lease agreements for right of way access was underestimated and this continues to be the largest factor regarding scheduling the construction. We have established a plan of action that includes twice weekly follow-ups with the permitting agencies as well as pre-construction meetings at the agency locations. This will continue until all permitting requirements have been met. Budget Note: In the architectural and engineering fees budget category, $33,991 was incorrectly reported in the previous quarterly report. $33,045 is the actual/correct amount. The actuals from project inception through end of current reporting period matches with the drawdown and the FSR through the 4th quarter. 2c-Additional engineering required on Killeen site caused delayed TxDOT permitting and added permitting with the electric utility for additional make ready work before construction could proceed. 2d,e-The effort required for a University to obtain the required lease agreeme | None anticipated. | TRUE
NT10BIX5570107 | 2012 | Q1 | Q1 - 2012 | For the quarter ending March 31, 2012 we were able to complete the 7.85 miles of fiber in Killeen with placement, splicing, terminations and testing and connection of one CAI, the TAMU Central Texas New Campus connected March 2nd. The bore across the Galveston Ship channel was successfully completed mid-March, remainder of the construction planned for the 2nd quarter. Lease agreements were executed with TxDOT for the Texarkana project. Construction started in Texarkana early March and is currently under construction with approximately 8 miles of subduct placement complete at this time. Crews have begun work on the Prairie View segment with approximately 20% completed. The DWDM, radio gateways and routers were purchased this quarter. | 16 | 0 | 86 | 0 | 16 | 0 | 0 | 0 | Killeen 7.85, Texarkana 8.00, Galveston .47 = 16.32. We intend to catch up to the baseline project schedule by February 1, 2013. | n/a | After greater clarification on this indicator, we are in line with the baseline project schedule. (Existing network miles upgraded is the connection between Waco to Temple via TLSN and Commerce to Dallas. These are in operation with traffic running across network.) | n/a | Killeen 7.85, Texarkana 8.00, Galveston .47 = 16.32 | n/a | n/a | We intend to be in line with our baseline project schedule by February 1, 2013. We continue working through the following: permitting, right of way, sub recipient agreement process; equipment ordering/receipt process; and unanticipated delays caused by weather/environment | 3 | 4 | 8 | Peoples Telephone, Texas Lone Star Network, Totelcom | None at this time | We anticipate that a portion of the network will be run by the sub-recipients. | 0 | 0 | 0 | 0 | Delay due to finalization of permits. | Finalizing sub-recipient agreements has taken longer largely due to staffing changes within the entities with whom we are collaborating resulting in having to start the process over when paper trails and information haven't been handed down/passed on/shared appropriately. | n/a | n/a | 9 | 9 | 0 | 2 | The process for securing permits has taken longer than anticipated causing the present total to be lower than what we predicted for this time frame. | Permit procedures are unique to each TxDOT district within the state. Also other permitting agencies have their own operational procedures and guidelines. City, County, Railroad and Utility pole attachments are dependent on a corrdinated effort with other utilities in the area. Our approach with these various agencies is cooperative and proactive while making them aware of our project time line and our sense of urgency. | n/a | 1 Gig and 10 Gig | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | None at this time | FALSE | n/a | We project by for the next quarter (ending June 30, 2012) the following: 1) Execution of the remaining two TxDOT lease agreements for the Houston District and the Corpus Christi District. 2) Completion of the fiber placement for Galveston 1.14 miles, Laredo, .75 miles, Corpus Christi 3 miles resulting in 4 CAIâ€™s connected. 3) With Texarkana and Prairie View currently under construction we anticipate partial completion of fiber placement in Texarkana with approximately 25 miles and 3 CAIâ€™s connected and in Prairie View, 7 miles. 4) We expect to have construction starting in Comanche on April 20th and Stephenville as early as May 14. 5) We plan to host an outreach event in San Antonio, TX. 6) We plan to complete the procurement process for the generator. | Texas A&M University | BUDGET NOTE: The Infrastructure Budget Execution Details was incorrectly reported for the Administrative and Legal Expenses and the Architectural and Engineering Fees in the 4th quarter 2011 PPR. They were reversed. It has been corrected in this quarter's PPR. | We may be unable to complete the 2.7 miles in Waco during the 2nd Qtr 2012, as projected, due to the unanticipated Franchise Agreement that we have encountered. The matter currently resides with the City of Wacoâ€™s legal counsel. If we are unable to proceed in Waco this quarter we will focus our efforts in other project locations to gain additional fiber miles deployed. | TRUE
NT10BIX5570107 | 2012 | Q2 | Q2 - 2012 | For the quarter ending June 30, 2012 the remainder of work on the Galveston Ship channel bore was successfully completed final construction including placing and terminating the fiber. Construction in Texarkana continues with approximately 24 miles of subduct and aerial placement complete at this time. Also on the Texarkana project we were able to complete that fiber segment for the Atlanta ISD and connect three CAIs. The Prairie View segment is reporting 6.6 miles of construction complete. Mid May construction started on Comanche segment reporting 11.4 miles of construction completed of the Stephenville project with preliminary core boring at the Grant Building on the Tarleton campus in early June. The joint BTOP effort with the City of Corpus Christi and TAMU CC started in early May and 5 locations have been completed with 2.8 miles of fiber placed, including the BTOP fiber for the Education Service Center for Region 8 reporting them as connected CAI for the quarter. | 62 | 0 | 86 | 0 | 62 | 0 | 0 | 5 | We are aggressively following our revised construction plan to improve the number of miles deployed in order to be on track with the project plan. New construction mileage for this quarter includes Texarkana 23.51, Prairie View 6.65, Galveston 1.21, Corpus Christi 2.8, Laredo .42 and Stephenville 11.41. At the end of the quarter we had doubled the size of the team for Stephneville and we were installing at a faster pace. | n/a | Existing network miles upgraded is the connection between Waco and Temple via TLSN and Commerce to Dallas. These are in operation with traffic running across the network. | n/a | We are aggressively following our revised construction plan to improve the number of miles deployed in order to be on track with the project plan. New construction mileage for this quarter includes Texarkana 23.51, Prairie View 6.65, Galveston 1.21, Corpus Christi 2.8, Laredo .42 and Stephenville 11.41. At the end of the quarter we had doubled the size of the team for Stephneville and we were installing at a faster pace. | n/a | n/a | Five of the twenty interconnection points have been upgraded. They are Riverside Campus, Campbell POP (Commerce), Valley Telephone POP (Corpus Christi), Valley Telephone POP (San Antonio), TLSN POP (Temple). All will be completed by February of 2013. | 3 | 4 | 8 | Peoples Telephone, Texas Lonestar Network, and Totelcom | None at this time | Totelcom which is a sub-recipient will operate the Stephenville fiber. Mid Plains Telephone which is a sub recipient will operate the Canyon fiber. Contacts for these two subrecipients are: Jimmy Dennington of Totelcom (254-893-1000) and Rob Wilkinson of Mid Plains Telephone (806-866-9900). | 0 | 0 | 0 | 0 | There are several agreements pending but none in place due to construction delays. | There are several agreements pending but none in place due to construction delays. | There has only been one inquiry into dark fiber at this time. | n/a | 14 | 14 | 0 | 2 | CAI's connected this quarter include: Atlanta ISD (4 facilities)Atlanta, TX and Education Services Center Region 2, Corpus Christi, TX were added this quarter. We predicted 30 at this time on our baseline but are behind due to construction delays. All CAIs will be connected my April of 2013 | CAI's connected this quarter include: Atlanta ISD (4 facilities)Atlanta, TX and Education Services Center Region 2, Corpus Christi, TX were added this quarter. We predicted 30 at this time on our baseline but are behind due to construction delays. All CAIs will be connected my April of 2013 | n/a | 1 Gig and 10 Gig | 0 | 0 | 0 | 0 | 0 | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | 0 | 0 | 0 | 0 | 0 | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | None at this time. | FALSE | n/a | In summary, we plan to deploy an additional 40 miles, have an additional 10 CAIs connected, and the final four broadband wholesaler/last mile provider agreements should be executed by the end of the 3rd Qtr, 2012. Finalization for the deployment and construction schedule of the City portion of the Texarkana project segment with substantial completion of the remaining fiber and connection to the Level 3 POP South of Atlanta. Completion of the construction of the remaining Corpus Christi sites with close coordination among the subrecipients to provide splicing and termination of BTOP fiber to assure CAI connectivity as proposed. Completion of the Bore across US Highway 290 on the Prairie View Project. Resolution of Franchise and permitting with City of Waco should allow us to begin construction on the Waco project segment. Completion of construction between Stephenville to Desedmona. An invoice for $540,210 was expensed on the last day of June and could not make the draw down for this quarter. It will be reflected in next quarter. TotelCom matching for approximately $180,118 has been received but not reviewed for audit purposes. It will be reflected in next quarter. | Texas A&M University | We were notified by some of the utility companies that our projects may be impacted as a result of tornadoes and severe weather in their service areas not necessarily our project areas and that they would give priority to the restoration of services in affected areas. Their crews worked very diligently and lessened the impact to our project effort wherever possible. We are working with TxDOT to resolve an issue concerning the location of some underground drainage and traffic signal utilities which has currently stalled construction on the Prairie View Project segment. | TxDOT may factor into any unforeseen delays relative to weather as they have on previous occasions halted our construction when conditions in the rights of way were less than optimal. One of the major project sites has presented us with soil composition challenges, that being rock which lends itself to a slower construction pace and creates a higher level maintenance requirements for equipment such as rock saws. | TRUE
NT10BIX5570107 | 2012 | Q3 | Q3 - 2012 | This quarter we were able to finalize the remaining sub recipient agreements with the City of Corpus Christi, Midplains Rural Telephone with continuing efforts with the City of Waco and Texarkana Water Utilities. Meetings with all parties were favorable and progress continues. Thirteen additional miles of the Texarkana path have been constructed. We are currently negotiating access to the LEVEL 3 hut in Atlanta for the Texarkana project. We also added 4 more CAIâ€™s for the quarter. Remaining on the Prairie View project is termination at the Waller 2 Level 3 hut. Our subrecipient City of Corpus Christi continues to build out the three remaining Corpus Christi project sites. Construction is near completion in Stephenville for the northern route to Desdemona including the Tarleton State campus segment with 22 miles constructed. The final 11 miles of the southern segment of the Stephenville project in Comanche, the Comanche to Priddy segment was completed in August allowing us to place and terminate and test the fiber connectivity between the POP in Comanche and Priddy, and Newburg to Comanche. Construction of the remaining .33 miles of fiber was completed in Laredo for the Texas A&M International campus. | 123 | 0 | 86 | 0 | 123 | 0 | 0 | 7 | We are aggressively following our revised construction plan to improve the number of miles deployed in order to be on track with the project plan. New construction mileage for this quarter includes Texarkana 12.93, Prairie View .58, Corpus Christi 1.6 Laredo .33 and Stephenville 33.24. Please note the following corrections to our previously reported network miles deployed. It was a math error resulting from Q4 2011 miles not being carried over to the Q1 2012 report. The following reads accurately. Q4 2011 â€“ 13 Q1 2012 â€“ 29 (13 + 16) Q2 2012 â€“ 75 (29 + 46) | n/a | Existing network miles upgraded is the connection between Waco and Temple via TLSN and Commerce to Dallas. These are in operation with traffic running across the network. | n/a | We are aggressively following our revised construction plan to improve the number of miles deployed in order to be on track with the project plan. New construction mileage for this quarter includes Texarkana 12.93, Prairie View .58, Corpus Christi 1.6 Laredo .33 and Stephenville 33.24. Please note the following corrections to our previously reported network miles deployed. It was a math error resulting from Q4 2011 miles not being carried over to the Q1 2012 report. The following reads accurately. Q4 2011 â€“ 13 Q1 2012 â€“ 29 (13 + 16) Q2 2012 â€“ 75 (29 + 46) | n/a | n/a | Seven of the twenty interconnection points have been upgraded. They are Riverside Campus, Campbell POP (Commerce), Valley Telephone POP (Corpus Christi), Valley Telephone POP (San Antonio), TLSN POP (Temple) Totelcom POP in Comanche & Priddy, TX. All will be completed by February of 2013. | 4 | 1 | 8 | Peoples Telephone, Texas Lonestar Network, Totelcom, and Midplains Rural Telephone. | None at this time. | Totelcom which is a sub-recipient will operate the Stephenville fiber. Mid Plains Telephone which is a sub recipient will operate the Canyon fiber. Contacts for these two subrecipients are: Jimmy Dennington of Totelcom (254-893-1000) and Rob Wilkinson of Mid Plains Telephone (806-866-9900). | 0 | 4 | 0 | 0 | There are several agreements pending but none in place due to construction delays. | TLSN, Peoples, Totelcom, Mid Plains | There has only been one inquiry into dark fiber at this time. | n/a | 18 | 18 | 0 | 2 | CAI's connected this quarter include: Atlanta ISD (2 facilities) Queen City ISD(2 facilities) predicted more at this time on our baseline but are behind due to construction delays. All CAIs will be connected my April of 2013 | CAI's connected this quarter include: Atlanta ISD (2 facilities) Queen City ISD(2 facilities) predicted more at this time on our baseline but are behind due to construction delays. All CAIs will be connected my April of 2013 | n/a | 1 Gig and 10 Gig | 0 | 0 | 0 | 0 | 0 | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | 0 | 0 | 0 | 0 | 0 | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | None at this time. | FALSE | n/a | By the end of the next quarter 12/31/2012 we plan to have completed construction placement of fiber, splicing terminations and testing for all project sites excluding Waco. We propose to connect 15 of the remaining 20 CAIs by the end of the quarter. We anticipate all network equipment will be received and in the network testing and deployment phase, however that remains dependent on the coordinated efforts of different entities at each project site and interconnect site. Due to our fiscal year end 8/31/12 and the ASAP closed from 9/14/12-10/3/12, we were not able to draw down what we had anticipated in last quarter. | Texas A&M University | Negotiating third party agreements with Level 3 has taken longer than anticipated. | None anticipated at this time. | TRUE
NT10BIX5570107 | 2012 | Q4 | Q4 - 2012 | The Stephenville to Desdemona link has been terminated and tested. Connectivity to the BTOP fiber for Tarleton State University is being coordinated with TLSN (Texas Lone Star Network). Approximately 15 miles of fiber was placed and terminated between the Cleta and Gurley POP for the West Texas A&M Segment under the MidPlains Rural Telecom sub recipient agreement. The City of Corpus Christi finished the remainder of fiber construction with 1.14 miles placed, as in the sub recipient agreement . We focused on obtaining the necessary agreements with third parties like City of Waco, City of Texarkana as well as the agreements with third party vendors including Level 3, in order to finish the network connections for the project sites where the BTOP fiber has been placed. | 139 | 0 | 86 | 0 | 139 | 0 | 0 | 7 | We are aggressively following our revised construction plan to improve the number of miles deployed in order to be on track with the project plan. New construction mileage for this quarter includes West Texas A&M (Canyon) 15 miles, Corpus Christi 1.14. Q4 2011 â€“ 13 Q1 2012 â€“ 29 (13 + 16) Q2 2012 â€“ 75 (29 + 46) Q3 2012 --123.18 (75 + 48.68) Q4 2012 -- 139.32 (123.18 + 16.14) | n/a | Existing network miles upgraded is the connection between Waco and Temple via TLSN and Commerce to Dallas. These are in operation with traffic running across the network. | n/a | We are aggressively following our revised construction plan to improve the number of miles deployed in order to be on track with the project plan. New construction mileage for this quarter includes West Texas A&M (Canyon) 15 miles, Corpus Christi 1.14. Q4 2011 â€“ 13 Q1 2012 â€“ 29 (13 + 16) Q2 2012 â€“ 75 (29 + 46) Q3 2012 --123.18 (75 + 48.68) Q4 2012 -- 139.32 (123.18 + 16.14) | n/a | n/a | Seven of the twenty interconnection points have been upgraded. They are Riverside Campus, Campbell POP (Commerce), Valley Telephone POP (Corpus Christi), Valley Telephone POP (San Antonio), TLSN POP (Temple) Totelcom POP in Comanche & Priddy, TX. All will be completed by February of 2013. | 4 | 1 | 8 | We have signed Sub-recipient agreements with: Peoples Telephone, Texas Lonestar Network, Totelcom, and Midplains Rural Telephone. They in turn currently do or soon will offer services to others which presently include: (Totelcom) City of De Leon and its library and all offices are connected into this network. City of Gorman and Carbon, along with the Desdemona Fire Dept. Once Stephenville route is functional: A wireless ISP will be establishing a 100mb connection for its customerâ€™s use. It serves several state and county offices in Erath County. | Presently, we have not been provided the pricing plans by the sub recipients that are charged to their "customers". We are working to obtain this information. | Totelcom which is a sub-recipient will operate the Stephenville fiber. Mid Plains Telephone which is a sub recipient will operate the Canyon fiber. Contacts for these two subrecipients are: Jimmy Dennington of Totelcom (254-893-1000) and Rob Wilkinson of Mid Plains Telephone (806-866-9900). | 0 | 4 | 0 | 0 | There are several agreements pending but none in place due to construction delays. | TLSN, Peoples, Totelcom, Mid Plains | There has only been one inquiry into dark fiber at this time. | n/a | 18 | 18 | 0 | 2 | No CAI's connected this quarter. We predicted more at this time on our baseline but are behind due to construction delays. All CAIs will be connected my April of 2013. | No CAI's connected this quarter. We predicted more at this time on our baseline but are behind due to construction delays. All CAIs will be connected my April of 2013. | n/a | 1 Gig and 10 Gig | 0 | 0 | 0 | 0 | 0 | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | 0 | 0 | 0 | 0 | 0 | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | None at this time. | FALSE | n/a | By the end of the next quarter 03/31/2013, we plan to have the following completed for all project sites: placement of fiber, splicing terminations and testing. During the quarter, efforts will largely be focused on Texarkana, Waco, and West Texas A&M University in Canyon, TX. A total of 5.6 miles will be built out in these areas. We propose to connect the remaining 20 CAIs by the end of the quarter. We anticipate there will be 0 broadband wholesaler/last mile provider agreements signed. Although the billing process has improved greatly since project onset, there is still a slight delay in the billing process which ultimately impacts the budgetary figures we report specifically what we anticipate vs what is expended. Although, the work may have been completed, bills for the work may not have been received/paid. | Texas A&M University | Negotiating Agreements with the City of Waco and other third party agreements with Level 3 have taken longer than anticipated. Although the billing process has improved greatly since project onset, there is still a slight delay in the billing process which ultimately impacts the budgetary figures we report specifically what we anticipate vs what is expended. Although, the work may have been completed, bills for the work may not have been received. | None anticipated at this time. | TRUE
NT10BIX5570107 | 2013 | Q1 | Q1 - 2013 | All construction has been completed on the Prairie View project. Level 3 has completed their fiber terminations in the Waller 2 hut for network connectivity for Prairie View A&M University. The City of Texarkana Water Utilities has constructed a portion of the fiber in Texarkana, TX. Construction has been completed on the remainder of the West Texas A&M University campus in Canyon, TX. Network hardware was installed and circuits have been turned up in Stephenville for Tarleton State University. The project progress was further augmented by the addition of three CAIâ€™s (Community Anchor Institutions) this quarter. We are finalizing the franchise agreement with the City of Waco which will allow us to complete that segment of the project. | 147 | 0 | 86 | 0 | 147 | 0 | 0 | 7 | The number of actual miles of fiber placed exceeds the revised target of 145 because when work is engineered it is essentially a best guess; however, when work commences and actual placement occurs, miles can vary which is exactly what occurred. New construction mileage for this quarter includes West Texas A&M (Canyon) 7.09 (4.13; 2.96) miles, Texarkana (to Atlanta - a portion of the TWU work) .54. Q4 2011 â€“ 13 Q1 2012 â€“ 29 (13 + 16) Q2 2012 â€“ 75 (29 + 46) Q3 2012 --123.18 (75 + 48.68) Q4 2012 -- 139.32 (123.18 + 16.14) Q1 2013 --146.95 (139.32 + .7.09 + .54) | n/a | Existing network miles upgraded is the connection between Waco and Temple via TLSN and Commerce to Dallas. These are in operation with traffic running across the network. | n/a | The number of actual miles of fiber placed exceeds the revised target of 145 because when work is engineered it is essentially a best guess; however, when work commences and actual placement occurs, miles can vary which is exactly what occurred. We are aggressively following our revised construction plan to improve the number of miles deployed in order to be on track with the project plan. New construction mileage for this quarter includes West Texas A&M (Canyon) 7.09 (4.13; 2.96) miles, Texarkana (to Atlanta - a portion of the TWU work) .54. Q4 2011 â€“ 13 Q1 2012 â€“ 29 (13 + 16) Q2 2012 â€“ 75 (29 + 46) Q3 2012 --123.18 (75 + 48.68) Q4 2012 -- 139.32 (123.18 + 16.14) Q1 2013 --146.95 (139.32 + 7.09 + .54) | n/a | n/a | (7) of the twenty interconnection points have been upgraded. They are Riverside Campus, Campbell POP (Commerce), Valley Telephone POP (Corpus Christi), Valley Telephone POP (San Antonio), TLSN POP (Temple) Totelcom POP in Comanche & Priddy, TX. All will be completed by July 2013. | 4 | 1 | 8 | We have signed Sub-recipient agreements with: Peoples Telephone, Texas Lonestar Network, Totelcom, and Midplains Rural Telephone. They in turn currently do or soon will offer services to others which presently include: (Totelcom) City of De Leon and its library and all offices are connected into this network. City of Gorman and Carbon, along with the Desdemona Fire Dept. Once Stephenville route is functional: A wireless ISP will be establishing a 100mb connection for its customerâ€™s use. It serves several state and county offices in Erath County. | Presently, we have not been provided the pricing plans by the sub recipients that are charged to their "customers". We are working to obtain this information. | Totelcom which is a sub-recipient will operate the Stephenville fiber. Mid Plains Telephone which is a sub recipient will operate the Canyon fiber. Contacts for these two subrecipients are: Jimmy Dennington of Totelcom (254-893-1000) and Rob Wilkinson of Mid Plains Telephone (806-866-9900). | 0 | 4 | 0 | 0 | Several pending; none completely executed. | TLSN, Peoples, Totelcom, Mid Plains | There has only been one inquiry for dark fiber at this time. | n/a | 21 | 21 | 0 | 2 | Three CAI's connected this quarter. We predicted more at this time on our baseline but are behind due to construction delays and third party agreements. All CAIs will be connected by July 31 2013. The Project baseline indicated 32 CAIâ€™s. Due to Deletions and Additions as the project was engineered and developed the final number will be greater than 32. | Three CAI's connected this quarter. We predicted more at this time on our baseline but are behind due to construction delays and third party agreements. All CAIs will be connected by July 31 2013. The Project baseline indicated 32 CAIâ€™s. Due to Deletions and Additions as the project was engineered and developed the final number will be greater than 32. | n/a | 1 Gig and 10 Gig | 0 | 0 | 0 | 0 | 0 | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | 0 | 0 | 0 | 0 | 0 | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | None at this time. | FALSE | n/a | By June 30 2013 (Q2 2013) we plan to have all third party agreements executed with fiber construction completed in Waco as well as the remaining work completed in Texarkana. Additionally, we plan to have all fiber terminated, tested and operational, to the extent possible, by June 30 2013, contingent upon third parties ability to meet our objectives. During Q2 2013 we will place 2.17 miles of fiber in Waco and 1.7 miles in Texarkana, wrapping up all fiber placement for the project. Once fiber is placed, we will pursue completion of network build and network testing. We estimate one additional Broadband Wholesaler/Last Mile agreement will be signed by the end of Q2 2013. We estimate 15 additional CAIs will be connected by the end of Q2 2013. | Texas A&M University | Attempted negotiations with the City of Waco concerning the franchise agreement hindered our contractor pursuing construction; however, the final document with Waco has been agreed upon now and we await the fully executed copy from the City of Waco. | None anticipated at this time. | TRUE
NT10BIX5570107 | 2013 | Q2 | Q2 - 2013 | We completed fiber construction on the campus of West Texas A&M University Campus with splicing, terminating and testing complete at the end of June. Interlocal agreement with the Texarkana Water Utilities was finalized and they completed the fiber splicing for Texarkana project. The network equipment will be housed in their newly renovated data center. The City of Corpus Christi has connected the majority of their BTOP project sites. The network connection for the Prairie View Campus was completed this quarter with the coordination of Level 3 at the Waller location. The Waco project was permitted in late June. | 149 | 0 | 86 | 0 | 149 | 0 | 0 | 7 | The number of actual miles of fiber placed exceeds the revised target of 145 because when work is engineered it is essentially a best guess; however, when work commences and actual placement occurs, miles can vary which is exactly what occurred. New construction mileage for this quarter includes 1.7 additional miles for Texarkana. Q4 2011 â€“ 13 Q1 2012 â€“ 29 (13 + 16) Q2 2012 â€“ 75 (29 + 46) Q3 2012 --123.18 (75 + 48.68) Q4 2012 -- 139.32 (123.18 + 16.14) Q1 2013 --146.95 (139.32 + .7.09 + .54) Q2 2013 --148.65 (146.95 +1.7) | n/a | Existing network miles upgraded is the connection between Waco and Temple via TLSN and Commerce to Dallas. These are in operation with traffic running across the network. | n/a | The number of actual miles of fiber placed exceeds the revised target of 145 because when work is engineered it is essentially a best guess; however, when work commences and actual placement occurs, miles can vary which is exactly what occurred. New construction mileage for this quarter includes 1.7 additional miles for Texarkana. Q4 2011 â€“ 13 Q1 2012 â€“ 29 (13 + 16) Q2 2012 â€“ 75 (29 + 46) Q3 2012 --123.18 (75 + 48.68) Q4 2012 -- 139.32 (123.18 + 16.14) Q1 2013 --146.95 (139.32 + .7.09 + .54) Q2 2013 --148.65 (146.95 +1.7) | n/a | n/a | (7) of the twenty interconnection points have been upgraded. They are Riverside Campus, Campbell POP (Commerce), Valley Telephone POP (Corpus Christi), Valley Telephone POP (San Antonio), TLSN POP (Temple) Totelcom POP in Comanche & Priddy, TX. All will be completed by July 2013. | 8 | 0 | 24 | TLSN, Peoples, Totelcom, Mid Plains Our Town Internet Services Northland Cable TV Lone Star Network ISP division of Totelcom | [REDACTED] | Totelcom which is a sub-recipient will operate the Stephenville fiber. Mid Plains Telephone which is a sub recipient will operate the Canyon fiber. Contacts for these two subrecipients are: Jimmy Dennington of Totelcom (254-893-1000) and Rob Wilkinson of Mid Plains Telephone (806-866-9900). | 0 | 4 | 0 | 0 | n/a | TLSN, Peoples, Totelcom, Mid Plains | n/a | n/a | 32 | 32 | 0 | 2 | Eleven CAI's connected this quarter. We predicted more at this time on our baseline but are behind due to construction delays and third party agreements. The Project baseline indicated 32 CAIâ€™s. Due to Deletions and Additions as the project was engineered and developed the final number may be greater than 32. | Eleven CAI's connected this quarter. We predicted more at this time on our baseline but are behind due to construction delays and third party agreements. The Project baseline indicated 32 CAIâ€™s. Due to Deletions and Additions as the project was engineered and developed the final number may be greater than 32. | n/a | 31 CAI's running on 1 Gig 1 CAI running on 10 Gig | 0 | 0 | 0 | 0 | 0 | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | 0 | 0 | 0 | 0 | 0 | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | None at this time. | FALSE | n/a | We will deploy the remaining 2.17 miles of fiber in Q3 2013 .We plan to have all fiber construction completed with the start of the Waco Project in July 2013 with all fiber terminated, tested and operational, to the extent possible, by September 30 2013, contingent upon third parties ability to meet our objectives. We plan to have 32 CAIs connected by the end of Q3 2013. We estimate of the no additional broadband wholesaler/last mile provider agreements through the end of next quarter. We plan to use the remaining funds in each budget category for the outstanding invoices under the construction budget category. This will not e more than a 10% budget revision. | Texas A&M University | We experienced several weeks of delays in obtaining signatures from both parties (TAMU and City of Waco) for the agreements with the CIty of Waco. Additionally, there was some language in the agreement that needed modification due to the uniqueness of the agreement. Subsequently, the kick-off meeting and the start of construction was also delayed. We expect to meet all milestones for completion of the project on or before September 30, 2013. | We remain reliant on collaboration with other third parties and to the extent that they may not be able to schedule work in coordination with our remaining project could create delays, however none are anticipated that would prevent the project from meeting the completion date of September 30, 2013. | TRUE
NT10BIX5570107 | 2013 | Q3 | Q3 - 2013 | In summary, work for this quarter alone resulted in additional 2.17 miles constructed in Waco, Tx and CAI connections have been met as per the final project milestones. To capture the overall accomplishments of the project made possible by the federal Broadband Technology Opportunities Program along with matching funds, the project included building 151 miles of fiber throughout the State of Texas and connecting 44 Community Anchor Institutions (CAI), more than originally anticipated at project inception. The principle accomplishment of this project has been to extend broadband capacity to the universities within the Texas A&M University System. Many of these small institutions (referenced below) were suffering with low bandwidth connectivity until this project was completed. Today the broadband circuit brings an initial 1Gbps of bandwidth immediately to each campus, and the capacity of the fiber is limited only by optics replacement for many years to come. It has put all of our campuses on the information superhighway where they can serve students statewide, nationally, and internationally. Each CAI and the community within which it serves will benefit from this project by having the technological ability to provide additional (and advanced) learning/educational opportunities as well as enhanced levels of services. This project is and will continue to support all types of CAIs, not just education. Included at this point are local governments, public safety, K-12, and others. The project required extensive collaboration with numerous federal, state and local entities, as well as rural telephone companies. Additionally, the project involved the participation and support of many member institutions of The Texas A&M University System (Texas A&M University-Central Texas, Prairie View A&M University, Texas A&M University at Galveston, Texas A&M University-Texarkana, Texas A&M University-Commerce, West Texas A&M University, Texas A&M University-Kingsville, Texas A&M University-San Antonio, Texas A&M International University, Texas A&M University-Corpus Christi and Tarleton State University). Without these collaborations, successful completion of the project would not have been possible. We fully anticipate that these 151 miles will foster future network growth and connectivity throughout the state, accomplishing the long term vision of the 'Texas Pipes' (BTOP) project. | 151 | 0 | 86 | 0 | 151 | 0 | 0 | 18 | The number of actual miles of fiber placed exceeds the revised target of 145 because when work is engineered it is essentially a best guess; however, when work commences and actual placement occurs, miles can vary which is exactly what occurred. New construction mileage for this quarter includes 2.15 additional miles for Waco. Q4 2011 â€“ 13 Q1 2012 â€“ 29 (13 + 16) Q2 2012 â€“ 75 (29 + 46) Q3 2012 --123.18 (75 + 48.68) Q4 2012 -- 139.32 (123.18 + 16.14) Q1 2013 --146.95 (139.32 + .7.09 + .54) Q2 2013 --148.65 (146.95 +1.7) Q3 2013 --150.8 (148.65 + 2.17) | n/a | Existing network miles upgraded is the connection between Waco and Temple via TLSN and Commerce to Dallas. These are in operation with traffic running across the network. | n/a | The number of actual miles of fiber placed exceeds the revised target of 145 because when work is engineered it is essentially a best guess; however, when work commences and actual placement occurs, miles can vary which is exactly what occurred. New construction mileage for this quarter includes 2.15 additional miles for Waco. Q4 2011 â€“ 13 Q1 2012 â€“ 29 (13 + 16) Q2 2012 â€“ 75 (29 + 46) Q3 2012 --123.18 (75 + 48.68) Q4 2012 -- 139.32 (123.18 + 16.14) Q1 2013 --146.95 (139.32 + .7.09 + .54) Q2 2013 --148.65 (146.95 +1.7) Q3 2013 --150.8 (148.65 + 2.17) | n/a | n/a | The following interconnection points are new or upgraded -- Riverside Campus, Campbell POP (Commerce), Valley Telephone POP (Corpus Christi), Valley Telephone POP (San Antonio), TLSN POP (Temple) Totelcom POP in Comanche & Priddy, TX. Waco Level 3 POP, Waco TLSN POP, Gurly POP, Cleta POP, Goldthwaite POP, NTS facility Lubbock, Waller Level 3 POP,Houston Level 3 POP, City of Corpus Christi City Hall, City of Corpus Christi Fleet Facility, City of Corpus Christi Oso Water treatment facility | 8 | 0 | 24 | TLSN Peoples Totelcom Mid Plains Our Town Internet Services Northland Cable TV Lone Star Network ISP division of Totelcom | [REDACTED] | Totelcom which is a sub-recipient will operate the Stephenville fiber. Mid Plains Telephone which is a sub recipient will operate the Canyon fiber. Contacts for these two subrecipients are: Jimmy Dennington of Totelcom (254-893-1000) and Rob Wilkinson of Mid Plains Telephone (806-866-9900). | 0 | 8 | 0 | 0 | n/a | TLSN, Peoples Totelcom Mid Plains Our Town Internet Services Northland Cable TV Lone Star Network ISP division of Totelcom | n/a | n/a | 44 | 44 | 0 | 2 | The additional CAIs causing the variance were identified during the project implementation and were included within compliance and no variance from the approved Environmental assessment | The additional CAIs causing the variance were identified during the project implementation and were included within compliance and no variance from the approved Environmental assessment | n/a | 43 CAIs running 1 Gig 1 CAI running 10 Gig | 0 | 0 | 0 | 0 | 0 | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | 0 | 0 | 0 | 0 | 0 | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | No Variance as this is not a last mile project | None at this time | FALSE | n/a | The work on the project is complete. | Texas A&M University | Nothing to report. | The project is deemed complete. | TRUE
NT10BIX5570108 | 2010 | Q4 | Q4 - 2010 | The major focus this quarter has been on re-baseline the project timeline and completing the Environmental Assessment. The revised project timeline was submitted and approved establishing quarterly milestones over the next three years. The project procured the services of a professional engineering vendor for the Environmental Assessment and detailed network design. The project completed requisite notifications to the State Historical Preservation Office, US Fish and Wildlife, Army Core of Engineers, and Indian Tribes. The project team and engineering vendor have engaged the Illinois Department of Transportation to begin the permitting process. The project procured the services of a wireless consultant to assess the locations and specific needs for wireless towers as identified within the network design. A project manager and administrative assistant were also hired to support work activity of the sub-recipient. The project team hosted a number of informational meetings with the proposed direct connect Community Anchor Institutions and introduced a monthly project update distributed to more than 6,000 individuals representing Community Anchor Institutions as well as other interested parties. This monthly update is also posted on the project website at www.illinois.net/IBOP.htm. As project performance is measured on a cash-basis, performance remains 0 as the invoice/payment cycle lags services/equipment delivered by 30-60 days. We expect the payment cycle to begin in Janu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | No variance | No variance | No variance | 0 | 0 | 0 | Since construction has yet to begin, there are no signed provider agreements. The project team is in the discovery phase of discussions with several providers. | Since construction has yet to begin, there are no services currently being offered. Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 MB to 10 GB, and Internet services, there are no services currently being offered. Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 MB to 10 GB, and Internet services. | NA | 0 | 0 | 0 | 0 | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 MB to 10 GB, and Internet services. | 0 | 0 | 0 | 0 | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 MB to 10 GB, and Internet services. | 0 | 0 | 0 | 0 | 0 | NA - Last Mile services are not included within the project. | NA - Last Mile services are not included within the project. | NA - Last Mile services are not included within the project. | NA - Last Mile services are not included within the project. | NA - Last Mile services are not included within the project. | 0 | 0 | 0 | 0 | 0 | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 MB to 10 GB, and Internet services. | NA | FALSE | NA | During the next reporting period the project team plans to submit the Environment Assessment and receive a Finding of No Significant Impact (FONSI) clearing the way to begin construction activities. Once the FONSI is received, the project will begin splicing activities on leased fiber and begin preparations to move lab equipment to the field for this leased fiber. The project team plans to issue a Request for Proposals for construction contractors and outside plant materials. Other procurement activities include finalizing agreements for 40% of the leased fiber miles and purchasing miscellaneous testing tools, wireless bridges, and office equipment. The technical team will complete the lab testing of optical equipment and continue staff training on services, equipment and fiber. The project team will begin review of existing customer forms and agreements and identify revisions needed to support the new service offerings and customer base. The architectural and engineering vendor will continue to work on the detailed design, construction specifications, and requests for right-of-ways and easements. The construction specifications will be developed on a segment-by-segment basis to enable construction activities to begin on a rolling basis. The Sub Recipient will be working to secure final agreements with 40+ partners and begin collecting funds pledged for the local match. | Central Management Services, Illinois Department of | Work on the Environmental Assessment started later than anticipated due to delays in executing the contract with the professional engineering vendor. Project staff and the vendor worked diligently on pre-engagement planning to ensure a rapid start. As a result, the draft Environment Assessment is on track to be submitted prior to the deadline. | Given the size and scope of the project, receiving a FONSI by the end of the next quarter is critical to meeting the project's overall milestones. The greatest risk to securing the FONSI within the next quarter rests with obtaining approval from the State Historic Preservation Officer (SHPO). The SHPO has requested engagement of an archaeological consultant to perform a literature search of the proposed fiber route. This search has been completed and is under review by the SHPO. It is anticipated that the SHPO will request a cultural survey for portions of the planned fiber route. However, the SHPO has indicated a willingness to enter into a programmatic agreement to allow construction activities to begin on a restricted basis pending completion of the cultural survey. If the FONSI is delayed, the immediate impact will be limited to lighting an existing fiber route and preparation activities in network Points of Presence and collocation facilities. If the FONSI is delayed past June it will impact the start of construction activities which will impact the overall project deadline. Based on ongoing discussions with the SHPO the project team believes there is minimal risk of a delay beyond a few weeks. As always, timely procurements are essential to staying on task. A key procurement activity for next quarter is the release of bid requests for construction and outside plant materials (conduit and fiber optic cabling). | TRUE
NT10BIX5570108 | 2011 | Q1 | Q1 - 2011 | The IBOP EC project is tracking as expected at 4% completion as of March 31, 2011. Total project expenditures were $4.2 million which includes $2 million in federal funds. These federal funds supported 18.34 full time equivalent jobs. This quarter represented the first with actual expenditures and while the project reached its overall target, there was some variance within the specific project milestones. A detailed explanation for the variance is provided below. In general we are finding that as the project progresses we have more accurate information to forecast specific costs and the time needed to complete specific tasks. As expected, these variances are generally balancing across the project as reflected in the overall project milestone. One of the major milestones for the quarter was submission of the draft Environmental Assessment. The report was submitted in January while the project team continued to work with the State Historic Preservation Officer (SHPO). In March, the project received a letter of no effect from the SHPO completing all consultations with the required state and federal agencies. The project engineering vendor, Globetrotters Engineering Corporation (GEC), is on track to complete detailed design on 25% of the backbone and 25% of the lateral network miles by the end of Year 1 Quarter 4. In March the project team released a Request For Proposals (RFP) for the fiber materials and construction. Vendor proposals are due April 15. The project engin | 0 | 281 | 0 | 271 | 0 | 0 | 0 | 0 | No variance. | Target was 0. CMS was able to secure one large fiber lease ahead of schedule. A second lease for 26 miles has been secured but was not paid by March 31. | No variance. | Quarterly target was 0. Because the project is moving faster with other fiber leases, CMS tranferred existing leased fiber to the project ahead of schedule so that splicing between the new leased fiber and the existing leased fiber can begin as soon as the FONSI is received. The project team is anticipating lighting a major fiber route, Collinsville to Chicago, sooner than projected - possibly by the end of the calendar year. | No variance. | No variance. | No variance. | No variance. Target was 0. CMS was able to secure one large fiber lease ahead of schedule. A second lease for 26 miles has been secured but was not paid by March 31. Quarterly target was 0. Because the project is moving faster with other fiber leases, CMS tranferred existing leased fiber to the project ahead of schedule so that splicing between the new leased fiber and the existing leased fiber can begin as soon as the FONSI is received. The project team is anticipating lighting a major fiber route, Collinsville to Chicago, sooner than projected - possibly by the end of the calendar yearS was able to secure one large fiber lease ahead of schedule. A second lease for 26 miles has been secured but was not paid by March 31. Quarterly target was 0. Because the project is moving faster with other fiber leases, CMS tranferred existing leased fiber to the project ahead of schedule so that splicing between the new leased fiber and the existing leased fiber can begin as soon as the FONSI is received. The project team is anticipating lighting a major fiber route, Collinsville to Chicago, sooner than projected - possibly by the end of the calendar year. | 1 | 0 | 80 | CMS has executed an agreement with the Illinois Rural HealthNet for Ethernet and/or Lambda services. The project team continues to discuss options with several providers who have expressed an intent to purchases services once available; however, we are waiting to move to the contract negotiation stage until construction begins. | Since construction has yet to begin, there are no services currently being offered. Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speed of 10 Mbps to 10 Gbps, and Internet Services, there are no services currently being offered. Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speed of 10 Mbps to 10 Gbps, and Internet Services. | NA | 0 | 0 | 0 | 0 | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speed of 10 Mbps to 10 Gbps, and Internet Services. | 0 | 0 | 0 | 0 | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speed of 10 Mbps to 10 Gbps, and Internet Services. | 0 | 0 | 0 | 0 | 0 | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | 0 | 0 | 0 | 0 | 0 | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speed of 10 Mbps to 10 Gbps, and Internet Services. | NA | FALSE | NA | By the end of next quarter the project team is anticipating 8% overall project completion which will keep the project slightly ahead of schedule (original target was 6%). Specific activities for the next quarter include: Completing the Environmental Assessment and securing a FONSI. Beginning to splice 307 miles of new leased fiber (281 miles paid for plus the 26 miles contracted but not yet paid) with 271 miles of existing leased fiber (all backbone miles) and finalizing agreements for approximately 97 miles of new leased network miles (all lateral miles) for a total of approximately 404 new leased miles. Rebidding the fiber construction procurement (see #3 below for more details). Completing the detailed design and construction specifications for 25% of the backbone and 25% of the lateral network miles. Conducting archeological surveys required by State Historical Preservation Officer (SHPO). Securing permits for 10% of the backbone spans. Upgrading the environmentals and power at 50% of the Point of Presence (POP) sites in order to support the operational needs of the optical equipment. Completing the review and updates to the customer service agreement forms. Procuring equipment to support customer connections. Continuing to send monthly updates to community anchor institutions and other interested organizations. Continuing to present and exhibit at conferences and events targeting community anchor institutions. | Central Management Services, Illinois Department of | CMS experienced delays in securing the State Historic Preservation Officer's (SHPO) approval for the proposed construction. As a result, the project did not receive a FONSI in March as initially projected. SHPO approval was received March 11 and forwarded to NTIA. (CMS received a FONSI on April 22). The delay will not impact the project timeline as the critical path is construction for the new fiber which is not scheduled to begin until July. The purchase of fiber test equipment was not completed this quarter due to delays in the procurement process. The project team recognizes that the state's procurement process is likely to cause delays and is planning accordingly by starting the process earlier. March was the first time for the project to draw down federal funding. During the process we learned that a SF270 was needed prior to requesting money in the ASAP system. CMS was able to work with its Program Officer and Grants Specialist for a quick approval of the SF270 minimizing the delay in receiving the federal funds. | We have experienced a delay with the fiber construction RFP that may impact the June target for completion. The Request for Proposals (RFP) was issued in March with proposals due April 15. After completing the administrative review the decision was made to cancel the procurement, in part, because more than half of the vendor responses received were disqualified for administrative or procedural errors. It was determined to be in the best interests of the State to cancel the solicitation and issue a new solicitation that is substantially similar. We estimate this will cause a four week delay to beginning construction activities. This will cause the project to miss some near-term milestones with regards to construction; however, we are confident we will make up the time over a couple of quarters as the project baseline reflected a conservative schedule for construction progress. We are also moving ahead of schedule with the leased miles which will allow the network engineering staff to focus on turning up the new construction miles as they are built. The SHPO's letter of no effect identified areas that will need to be avoided and areas where a site survey will need to take place prior to construction. Globetrotters is working with the archeologist to reroute fiber to avoid identified areas of concern and conduct site surveys where needed to ensure the fiber placement within the right of way does not impact archeological concerns. Based on conversations between Globetrotters, SH | TRUE
NT10BIX5570108 | 2011 | Q2 | Q2 - 2011 | The IBOP EC project is 5% complete which is 1% behind the baseline target. Total project expenditures to date are $5 million which includes $2.7 in federal funds. These federal funds have supported 53.29 full time equivalent jobs. The project received a FONSI on April 22 clearing the way to begin construction activities. The FONSI included a requirement by the State Historic Preservation Officer (SHPO) to conduct archeological field surveys along about 2% of the new construction routes. During this quarter CMS has been working with the engineering firm to develop a scope of work and cost estimate for the surveys. Meanwhile CMS discovered that the Illinois Department of Transportation (IDOT) has conducted recent field surveys in the proposed construction areas. The IDOT Chief Archeologist has met with SHPO and all indications are that SHPO will remove the requirement for additional surveys. We are expecting written confirmation from SHPO shortly. The purchase of an additional 26 leased fiber miles was completed in April. This brings the total new leased miles to 307 and existing leased miles to 271. Work has begun to turn up the leased network miles. A small build to extend leased fiber into the Springfield network POP site was completed along with splicing activities to connect the fiber into a vendor leased In Line Amplification (ILA) hut. A second procurement solicitation was issued for a short fiber build to extend the leased fiber into the Collinsville POP. The opti | 0 | 307 | 0 | 271 | 0 | 0 | 0 | 95 | No variance. | Baseline target is 0. CMS was able to secure fiber leases ahead of schedule. | No variance | Baseline target is 0. Because the project is moving faster with other fiber leases, CMS transferred existing leased fiber to the project in Y1Q3 ahead of schedule. CMS is in the process of splicing the different fiber pieces together. The optical equipment to light a portion of the leased fiber has been ordered and received (the invoice was not paid by June 30 so it's not reflected in our spend). | No variance. | No variance. | No variance. | Baseline target is 0. These interconnection points are along leased fiber routesn points are along leased fiber routes. | 1 | 0 | 80 | Illinois Rural HealthNet The project team continues to discuss options with several providers who have expressed an intent to purchase services once available; however, we are waiting to move to the contract negotiation stage until construction begins. | Since construction has yet to begin, there are no services currently being offered. Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet Services, there are no services currently being offered. Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet Services. | NA | 0 | 0 | 0 | 0 | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet Services. | 0 | 0 | 0 | 0 | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet Services. | 0 | 0 | 0 | 0 | 0 | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | 0 | 0 | 0 | 0 | 0 | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Once operational, the network will offer the following services: Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet Services. | NA | FALSE | NA | Total cumulative spend estimated for next quarter is $9,408,282 which is 10% of the total budget. As the project enters the construction phase over the next two quarters we anticipate the rate of spend to increase significantly. Specific activities for next quarter include: Work with SHPO, IDOT and engineering firm to resolve the outstanding field survey requirements. Complete and submit Post Award Modification for changes to wireless tower locations and CAIs. Finish splicing work on the Springfield to Collinsville leased fiber, install the optical equipment and begin testing the link. Start construction activities on the first construction package which is a 91 mile route from Kankakee to Champaign and complete bid and vendor selection for the second package which is a 55 mile route from Kankakee to the southern edge of Cook County. CMS has asked the vendors to price a 3, 6 and 9 month construction schedule. The costs for the three options will determine which timeline we set for completion. We anticipate using the same or similar approach with the other construction packages. Complete detailed design and construction specifications for 50% of the total network miles. Secure permits for the first two construction packages. Continue site preparation at the existing Point of Presence (POP) sites which includes: purchasing and installing equipment racks and upgrading power. During this quarter we anticipate finalizing contract amendments with landlords to address the a | Central Management Services, Illinois Department of | As anticipated in the last report, the fiber construction solicitation was rebid due to administrative errors with the first round proposals. The second solicitation received the same level of interest (11 proposals) and resulted in the successful selection of 5 vendors. The 5 vendors will have the opportunity to bid on each construction package. The Site Preparation milestone is behind the baseline target. As described above, the activities that have been delayed are related to electrical upgrades and rack installations at POP sites. CMS has existing POP sites which are located in State facilities or leased from universities and/or community colleges. Several of the leased sites required contract amendments to address costs associated with the electrical updates. We are currently finalizing these amendments and anticipate having them executed by the end of the next quarter at which time the landlord will proceed with the electrical upgrades. The actual costs for the upgrades will most likely not be incurred until 2011Q4. Upgrades at one of the State facilities is taking longer than anticipated as it was determined we needed an assessment by and engineering professional to determine the overall electrical needs. CMS is working with the project engineering firm, Globetrotters, to conduct the assessment. Once complete, we will need to engage a separate vendor to perform the electrical work. CMS is finalizing a master contract with a vendor to perform all electrical work at POP | As the project enters into the construction phase we are hearing there could be a 12-14 week delay for fiber optic cabling. We are working with the construction vendors who are supplying the fiber cabling and the engineering firm on options to minimize delays. Some of these options include: adjusting the fiber specifications to utilize fiber in inventory, installing conduit initially and pulling fiber at a later date, or placing a bulk fiber order with 1 of the 5 construction vendors. CMS and Illinois State University (sub recipient) continue to work on finalizing the CAI list. Several sites on the original list have changed due to the CAI declining service, sites have relocated or it's been determined that it is more economical to connect individual school buildings indirectly through a school district wide area network. We are assessing what impact the new sites will have on the approved Environmental Assessment. In most cases, the new site is only a few blocks from an approved route. CMS is preparing a Post Award Modification to address the CAI changes. | TRUE
NT10BIX5570108 | 2011 | Q3 | Q3 - 2011 | Overall, the project is 9% complete. Total project expenditures are $8,689,032 which includes $2,359,290 in federal funds. These federal funds have supported a cumulative total of 83.88 full time equivalent jobs. During this quarter, CMS worked to address SHPO requirements for additional field surveys as articulated in our FONSI. SHPO has cleared 177 of 200 miles as a result of discussions with the Illinois Department of Transportation (IDOT) Chief Archeologist. A copy of this letter has been forwarded to NTIA via an Award Action Request. Field surveys have been completed on an additional 16 miles. The field surveys identified no archeological concerns. The report is being assembled and will be forwarded to SHPO. The restriction for the remaining 7 miles will be addressed via a Post Award Modification to reroute the fiber to avoid the remaining archeological concern. The 80 miles of leased fiber from Collinsville to Springfield was lit and is now operational ahead of schedule as we were able to finalize contracts quicker then anticipated. We are collecting quotes from our construction vendors to build the first CAI lateral off this segment. CMS has selected the vendor for the Kankakee to Champaign (91 miles) segment. The quote was within budget and in alignment with the overall project schedule. Permits have been filed for this segment and the next segment in queue. Over 95% of the route miles are along IDOT controlled access rights of ways. We are expecting to receive th | 0 | 307 | 0 | 271 | 0 | 0 | 0 | 95 | Baseline target is 0. | Baseline target is 0. CMS was able to secure fiber leases ahead of schedule. | No variance. | Baseline target is 0. Because the project is moving faster with other fiber leases, CMS transferred existing leased fiber to the project in Y1Q3 ahead of schedule. | Baseline target is 0. | No variance. | No variance. | Baseline target is 0. these interconnection points are along leased fiber routesn points are along leased fiber routes. | 1 | 0 | 80 | Illinois Rural HealthNet The project team continues to discuss options with several providers who have expressed an intent to purchase services once available; however, we are waiting to move to the contract negotiation stage until construction begins. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet Services. | NA | 0 | 0 | 0 | 0 | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since construction has yet to begin, there are no subscribers at this time. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet Services. | 0 | 0 | 0 | 0 | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet Services. | 0 | 0 | 0 | 0 | 0 | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | 0 | 0 | 0 | 0 | 0 | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet Services. | NA | FALSE | NA | The total cumulative spend estimated for next quarter is $12.5 million which is 13% of the total project spend. This projection is below the baseline target of 20%. The shortfall this quarter is directly attributable to the delay in completing the construction master contracts. We are working diligently to complete design and permitting necessary to begin sequential construction activities in Y2Q3. We anticipate construction to be underway on three segments and one lateral collectively covering approximately 180 miles. By the end of the quarter, detailed design and quote packages should be complete for all segments. We will continue to focus on securing permits for the remaining packages and coordinating construction activities with the vendors. CMS will continue to work on POP site upgrades where needed. We expect the engineering firm to complete it's analysis of the Chicago POP site and will develop a plan for the necessary modifications. Key Performance Indicators for next quarter include: New Network Miles Deployed - 0 (we are on track to begin reporting new network miles in Q7 as projected in the Baseline) New Network Miles Leased - 307 (no change as we are ahead of the 268 target listed in our Baseline) Total CAI subscribers served - 7 Signed Agreements with Wholesalers and/or Last Mile Providers - 1 (no change. We are on track with our Baseline projections which does not forecast signed agreements until Q10 when be will be in the final phase of turning up service | Central Management Services, Illinois Department of | After some delays with the construction procurement, CMS has selected its vendors and is in the process of signing contracts. While 5 vendors where originally selected for award, one vendor has been disqualified for failing to disclose information as required by the solicitation documents. This will have no impact on the project timeline. CMS will be using the newly operational fiber segment for production traffic for the current state and educational network. We are looking for guidance from NTIA on how to calculate the Program Income. As a governmental entity we are limited on the amount of profit that can be generated on our services. As such, our proposed rates are just slightly above operating costs. Since we are in the early stages of the project and only have partial routes operational, we are the only "customer" purchasing services. At this time, the operating costs exceed the revenue generated. Therefore, it's our position there is no Program Income to report. Our sub recipient, Illinois State University, projected spending $62,400 in the Project Inspection Fees budget line for easement related activities. While work was completed on 106 of 144 easements during this quarter, the invoice was not received in time to process payment by September 30. So far costs for the easement activities are tracking below projections. The sub recipient has also re-budgeted to track the work performed by legal counsel on easements under the Administrative and Legal budget category. | The greatest challenges at this point in the project will be securing permits and fiber in a timely manner. The majority of the construction is taking place along the Illinois Department of Transportation's (IDOT) controlled access rights of way (Interstate). CMS and IDOT staff are meeting on a regular basis to ensure that IDOT permits are received in accordance with the construction schedule. Using the controlled access rights of way will also result in a faster run rate for fiber installation as there are fewer road crossing and other obstructions. As for fiber delays, the construction vendors are planning accordingly by performing those activities that do not require fiber during the early stages of construction. The projected match proportionality is 80% federal and 20% local while the overall project target is 64% federal and 36% local. The approved project detailed budget identifies $31M of $34.4M local match applied to the Construction activities. Construction activities are just beginning in Q4 with expenditures anticipated to be reflected in the 2012Q1 report. The local match proportionality will increase as construction activities progress. | TRUE
NT10BIX5570108 | 2011 | Q4 | Q4 - 2011 | Overall the project is 12% complete. Total project expenditures are $11,441,431 which includes $9,034,421 in federal funds. These federal funds have supported a cumulative total of 110 full time equivalent jobs. During this quarter Central Management Services (CMS) submitted a Post Award Modification for minor route changes to address restrictions of the FONSI near the Cahokia Mounds area and planned road construction. The route changes do not change the planned anchors and communities to be served. CMS is in the process of receiving approvals from the appropriate state and federal agencies. Construction along the first network span started in November (90 mile span). As a result of the mild weather the contractor was able to install over 12,000 feet of conduit. Orders have been issued for two more network spans representing another 80 miles. CMS has selected vendors and is processing orders for four more spans representing 300 miles. Four vendors with multiple crews will be working simultaneously to install over 1,000 miles of new fiber over the next 6 to 9 months. Staff are working to secure permits for the new construction. CMS has filed permits for 6 of 12 network spans. The majority of the fiber will be installed along Illinois Department of Transportations's (IDOT) controlled access right of way so staff are working closely with IDOT to ensure timely approval. CMS continues to provide a monthly project update via email to community anchor institutions and interested organizations. The updates are also available on the Illinois Century Network website at http://www.illinois.net/IBOP/IBOP_EastCentral/Newsletters/ IBOP_EC_Monthly_Update.html. | 0 | 307 | 0 | 271 | 0 | 0 | 0 | 95 | Baseline target is 0. | Baseline target is 268. CMS was able to secure fiber leases ahead of schedule. | Baseline target is 0. | Baseline target is 221. CMS was able to light existing leased fiber ahead of schedule. | Baseline target is 0. | Baseline target is 0. | Baseline target is 0. | Baseline target is 37. CMS was able to light existing leased fiber ahead of schedule. | 1 | 0 | 80 | Illinois Rural HealthNet | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet Services. | NA | 0 | 0 | 0 | 0 | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet Services. | 7 | 0 | 7 | 4 | The new leased fiber lit in 2011 positions these CAIs to connect at speeds up to 100 megabits. Since only a small portion of the network (80 of 2,000 miles) is operational, the new service offerings are not available. Once fully deployed, these CAIs will realize a significant increase in broadband speeds as they move from 3-5 megabits to 50-100 megabits. | Since only a small portion of the network (80 of 2,000 miles) is operational, the new service offerings are not available. | Since only a small portion of the network (80 of 2,000 miles) is operational, the new service offerings are not available. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet Services. | 0 | 0 | 0 | 0 | 0 | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | NA - The project is a Comprehensive Community Infrastructure project with no last mile component. | 19767 | 0 | 0 | 0 | 4 | This represents the businesses near the leased fiber that is operational. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps, and Internet Services. | NA | FALSE | NA | The cumulative spend estimated for next quarter is $18 million which is 19% of the total project spend. The baseline projected a cumulative spend of $40 million or 42% of the total project. $20 of the $22 million shortfall is from the network build milestone. The Environmental Assessment delayed the start of construction by two quarters. We anticipate that by the end of the quarter we will have completed construction bidding, issued orders to contractors, and started construction on all 12 network spans. Construction for each network span is expected to last 6 to 9 months with construction substantially complete in Q4-2012. We anticipate that some construction activities will carry over into the first half of 2013 as we complete road/rail crossings postponed due to permit delays and minor route changes due to restrictions in the FONSI. To date, the construction contractors have provided fiber and conduit materials as part of their bid. Staff have been working with the engineering firm and the contractors to prepare a bulk fiber order to expedite delivery for the network spans not yet awarded to a contractor. The fiber order will be submitted by the end of the next quarter. We will continue to focus our attention on submitting permits for the remaining 6 network spans and securing the remaining permits. Staff are working closely with the Illinois Department of Transportation to complete the numerous permits that fall within their jurisdiction. CMS is also working to finalize additional fiber leases. Three lease agreements are in contract negotiations and we anticipate issuing bids for another four by the end of the quarter. Key Performance Indicators for next quarter include: New Network Miles Deployed - 15 miles of conduit New Network Miles Leased - 354 Total CAIs Connected - 7 Signed Agreements with Wholesalers and/or Last Mile Providers - 1 | Central Management Services, Illinois Department of | The greatest challenge right now is permitting. The engineering firm is working diligently to complete the remaining permit applications and respond quickly to modification requests from the permitting authorities. Many of the rail roads have indemnification language in their agreements that must be changed through negotiations as the State of Illinois cannot indemnify another entity. The contractors are moving forward with construction in the areas where permits have been secured and will complete the remaining areas at a later date. CMS is seeking NTIA's approval for a Post Award Modification. We would like to have approval before the end of the next quarter. This will allow the contractors to complete the route changes while they are still in the field working on the specific span. | Weather, permits and materials are the three factors that have the greatest potential to impact projections for next quarter. We anticipate that some construction activities will continue during the next quarter but recognize that progress will likely be slower in January and February. The engineering firm and staff are focusing closely on the permits knowing that we want most permits secured during the next quarter. To date construction contractors are purchasing fiber as they are selected to build a network span. CMS is in the process of placing a bulk fiber order to speed up delivery of materials for the construction that hasn't yet started. The projected match proportionality remains at 80% federal and 20% local while the overall project target is 64% federal and 36% local. The approved project detailed budget identifies $31M of $34.4M local match applied to the construction activities. Construction activities are just beginning in Q4 with expenditures anticipated to be reflected in the Q1-2012 report. The local match proportionality will increase as construction activities progress. CMS will submit a match proportionality waiver following submission of the quarterly and annual progress reports. | TRUE
NT10BIX5570108 | 2012 | Q1 | Q1 - 2012 | Overall the project is 20% complete. Total project expenditures are $19,103,284 which includes $12,919,898 in federal funds. These federal funds have supported a cumulative total of 157 full time equivalent jobs. Purchase orders have been issued for all 13 planned construction segments and construction has started on 5 routes. By quarter end, 70 miles of conduit and 4 miles of fiber have been installed. Between CMS and the construction vendors, all fiber has been ordered. The construction vendors are beginning to receive fiber from the early orders. Eighty percent of the permits have been received. CMS has filed for the remaining permits and are working with the permitting authority to resolve issues with indemnification language within the agreements. CMS submitted three route changes to address environmental restrictions, planned road construction and CAI changes. In January, the sub recipient, Illinois State University (ISU), hired an architectural and engineering firm to complete a structural assessment on locations targeted for wireless towers. ISU expects to release a bid in August for all wireless equipment and installation. In February, representatives from NTIA conducted a two day site visit. During the visit, NTIA representatives had the opportunity to visit construction activities associated with a lateral connection to a CAI, meet with the construction foreman, and talk with a high school that will be connected via fiber. As a follow-up, CMS submitted an updated CAI list and network mileage. CMS and the sub recipient have secured commitments from 368 of 380 CAIs. Work has begun on a video to track the construction progress and highlight the CAIs who will be benefiting from faster broadband speeds. The video will be posted on the project website and used in presentations and exhibits. CMS continues to provide a monthly project update via email to community anchor institutions and interested organizations. The updates are also available on the Illinois Century Network website at http://www.illinois.net/IBOP/IBOP_EastCentral/Newsletters/IBOP_EC_Monthly_Update.html. The local match at the end of the quarter is 32.4% while the overall project requirement is a 35.8% local match. The approved project detailed budget identifies $31M of $34.4M local match applied to the construction activities. Q1-2012 is the first quarter construction expenditures were reported. The local match proportionality will increase as construction activities progress. CMS has submitted a match proportionality waiver that projects CMS to achieve the target match in Q2-2012. | 4 | 307 | 0 | 271 | 4 | 0 | 0 | 95 | Baseline target is 114. In the revised project schedule provided to NTIA, CMS set a target of 24. During this quarter good progress was made on conduit installation (70 of 520 miles) while waiting for fiber deliveries. A small amount of fiber has been received from the early orders. The first delivery for the large fiber order is scheduled for April. | Baseline is 535. In the revised project schedule provided to NTIA, CMS set a target of 316. The overall number of leased project miles was reduced and the anticipated new build miles was increased. CMS has identified vendors for the remaining leases and is the the process of finalizing two contracts representing 35 miles and in negotiations with two additional vendors for 52 miles. | Baseline target is 0. In the revised project schedule provided to NTIA, CMS set a target of 0. | Baseline target is 441. In the revised project schedule provided to NTIA, CMS set a target of 271. The total existing leased miles has been recalculated to 297. 250 miles of existing, non-CMS, state fiber has been re-classified as new lease. | Baseline target is 1,088. The baseline number included leased and new build. Per NTIA instructions, only new construction miles are being reported here. | Baseline target is 0. The revised project schedule target is 0. | Baseline target is 0. The revised project schedule target is 0. | Baseline target is 61. The revised project schedule target is 95.The leased fiber includes more interconnection points then originally anticipated. | 1 | 0 | 80 | Illinois Rural HealthNet | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | NA | 0 | 0 | 0 | 0 | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | 7 | 0 | 7 | 0 | The new leased fiber lit in 2011 positions these CAIs to connect at speeds up to 100 Mbps. Since only a small portion of the network (80 of 2,000 miles) is operational, the new service offerings are not available. Once fully deployed, these CAIs will realize a significant increase in broadband speeds as they move from 3-5 Mbps to 50-100 Mbps. | Since only a small portion of the network (80 of 2,000 miles) is operational, there are no subscribers at this time. | Since only a small portion of the network (80 of 2,000 miles) is operational, there are no subscribers at this time. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | 0 | 0 | 0 | 0 | 0 | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | 19767 | 0 | 0 | 0 | 0 | This represents the businesses near the leased fiber that is operational. | Since only a small portion of the network (80 of 2,000 miles) is operational, there are no subscribers at this time. | Since only a small portion of the network (80 of 2,000 miles) is operational, there are no subscribers at this time. | Since only a small portion of the network (80 of 2,000 miles) is operational, there are no subscribers at this time. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | NA | FALSE | NA | The cumulative spend estimated for next quarter is $31,003,984 which is 32% of the total project spend. The baseline projected a cumulative spend of $65,597,477 or 68%. The revised project schedule submitted to NTIA has a target of $31,547,045 or 33%. The difference between the baseline and revised project schedule are due to unanticipated time for the Environmental Assessment, delays in securing construction contracts, and fiber delivery delays. With contracts and orders in place for construction, over 80% of the permits secured, and a schedule for fiber deliveries the revised targets are realistic and align with completing the project by the end of year 3. During the next quarter, construction will have started on all 13 planned segments. We anticipated securing most if not all of the permits and we will start to take delivery of fiber from the bulk fiber order. CMS is working with the existing construction vendors on specifications for inside plant work and expects to place orders by the end of the quarter. The sub recipient plans to issue a bid for inside plant and award a contract by the end of the quarter. The sub recipient's wireless A&E firm will continue their assessment of the tower location and will have bid documents prepared in mid August. Key Performance Indicators for next quarter include: New Network Miles Deployed - 90 New Network Miles Leased - 340 Total CAIs Connected - 8 Signed Agreements with Wholesalers and/or Last Mile Providers - 1 | Central Management Services, Illinois Department of | CMS has made progress securing permits (over 80% complete). There are a handful of permits still under negotiation in order to remove indemnification language. CMS has 3 Award Action Requests for route changes pending with NTIA. These changes are needed to address environmental restrictions, avoid planned road construction, and address CAI changes. | Delays with fiber delivery have the greatest potential to impact projections for next quarter. CMS has received the first shipment from the fiber bulk order on schedule and the vendor has provided dates and quantities for the remaining shipments. CMS is working closely with the four contractors to maximize productivity by focusing on conduit installations and direct the early fiber deliveries to those locations scheduled for direct bury. We are close to resolving issues with the indemnification language within remaining permits. However, if the negotiations linger the construction schedule could be affected. CMS would like approval of the three route change requests by the end of the quarter in order for the construction crews to complete the work while working in the area. | TRUE
NT10BIX5570108 | 2012 | Q2 | Q2 - 2012 | Overall the project is 32% complete. Total project expenditures are $30,672,180 which includes $16,821,995 in federal funds. These federal funds have supported a cumulative total of 260 full time equivalent jobs. The local match at the end of the quarter is 45%. The project will not meet the 2/3 completion by 24 months due to the slow start with construction. Now that construction has started, the contractors are making excellent progress and the project is on schedule to meet the July 31, 2013 deadline. Construction has started on all 12 planned construction segments. By quarter end, 300 miles of conduit (43%) and 75 miles of fiber (8%) have been installed. Approximately 30% of the fiber has been received and 90% of the permits secured. In order to continue construction progress while waiting for delivery of the remaining fiber, CMS added conduit to two network segments. Installing conduit now will allow the contractor to install fiber into the conduit significantly faster than the direct plow method, with minimal cost impact to the total segment. CMS had previously identified conduit as a solution for meeting the overall project deadlines in light of the long fiber delivery schedules. So far CMS is receiving fiber as scheduled. CMS has been working with the contractors on designs and quotes for the inside plant work and has begun to issue orders for work along the early backbone construction routes. The sub recipient is in the process of rebidding its inside plant work as the original bidder failed to meet the bid specifications. The sub recipient's architectural and engineering contractor is close to finalizing the structural analysis for the wireless towers. They plan to issue separate bid requests in August for installation and equipment. CMS finalized two more contracts for leased fiber which brings the total leased miles to 275 or 44% complete. CMS has accepted bids for three additional fiber leases which represent an additional 160 miles or 70%. CMS has responded to NTIA questions regarding the pending route change requests and is awaiting approval from the environmental review team. These changes are needed to avoid planned road construction, accommodate changes in community anchor institutions, and finish connections to leased fiber. CMS and the sub recipient have secured commitments from the targeted 376 CAIs (100%) that will be directly connected via fiber. Lateral connections and customer premise equipment installations are complete for 8 of the CAIs. One of the CAIs is using the BTOP funded infrastructure to receive improved service. An additional 1,100 CAIs are connected to the 80 miles of BTOP funded operational infrastructure thru non BTOP funded connections. As a result, these sites will see their broadband speeds more then double. The State's video production team is finishing edits on a video that showcases the project and the anchors that will benefit from the improved broadband. The video will be showcased on the project website and used at conferences and community informational meetings. CMS continues to provide a monthly project update via email to community anchor institutions and interested organizations. The updates are also available on the Illinois Century Network website at http://www.illinois.net/IBOP/IBOP_EastCentral/Newsletters/IBOP_EC_Monthly_Update.html. The sub recipient also has a monthly update available at http://cirbn.org. | 75 | 307 | 3 | 282 | 75 | 0 | 0 | 148 | Baseline target is 246. The revised project schedule provided to NTIA set a target of 250. During this quarter 300 miles of conduit was installed. The contractors are focusing on installing long segments of conduit first and will pull fiber at a later date. This approach allows the contractor to continue working around railroad and other crossings where permits and fiber deliveries are still pending. | Baseline target is 668. The revised project schedule provided to NTIA set a target of 316. CMS accepted bids for three additional fiber leases that total approximately 160 miles. This additional leased miles will not be reported until CMS completes the formal acceptance process and issues payment. | Baseline target is 0. The revised project schedule provided to NTIA set a target of 3. | Baseline target is 551. The revised project schedule provided to NTIA set a target of 288. The variance is due to actual mileage from the final route calculations. | Baseline target is 1,465. The revised project schedule provided to NTIA did not set a target for this indicator. The Baseline target was calculated incorrectly as the sum of the leased, new construction and existing upgraded miles which for this quarter equals 635. | Baseline target is 0. The revised project schedule provided to NTIA set a target of 0. | Baseline target is 2 The revised project schedule provided to NTIA set a target of 0. Only 1 new tower will be needed. The project will use 8 existing towers. | Baseline target is 68 The revised project schedule provided to NTIA set a target of 95. | 1 | 0 | 80 | Illinois Rural HealthNet | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | NA | 0 | 0 | 0 | 0 | Since only a small portion of the network is operational, there are no providers receiving new service at this time. | Since only a small portion of the network is operational, there are no providers receiving new service at this time. | Since only a small portion of the network is operational, there are no providers receiving new service at this time. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | 8 | 0 | 8 | 0 | The new leased fiber lit in 2011 positions these CAIs to connect at speeds up to 100 Mbps. Since only a small portion of the network (85 of 2,000 miles) is operational, the new service offerings are not available. Once fully deployed, these CAIs will realize a significant increase in broadband speeds as they move from 3-5 Mbps to 50-100 Mbps. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network (85 of 2,000 miles) is operational, the new service offerings are not available. Once fully deployed, these CAIs will realize a significant increase in broadband speeds as they move from 3-5 Mbps to 50-100 Mbps. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | 0 | 0 | 0 | 0 | 0 | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | 19767 | 0 | 0 | 0 | 0 | This represents the businesses near the leased fiber that is operational. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | NA | FALSE | NA | The cumulative spend estimated for next quarter is $44,941,186 which is 47% of the total project spend. The baseline projected a cumulative spend of $69,552,608 or 72%. The revised project schedule submitted to NTIA has a target of $52,755,517 or 55%. The difference between the revised project schedule and the PPR projection is approximately $7.8 million which is a result of costs coming in below budget for network design and rights of way and delays with construction, inside plant and final equipment purchases. During the next quarter we expect fiber installation for 2 of the 12 routes to be complete. Next quarter's spend for network build will be less then projected in the revised project schedule due to the late start on 3 routes and costs coming in less then budgeted. The construction completion dates are not affected by the late start as the projected time line included waiting time for fiber delivery. The fiber is being received as scheduled and we expect to have over 50% by the end of the quarter. Contractors will begin working on inside plant for the CMS CAIs. The sub recipient plans to finalize wireless tower and inside plant design and issue bids for the work and equipment. Staff will continue to work on securing the remaining permits. CMS will be working to finalize service agreement documents for new customers and services. CMS has been meeting with several wholesale providers interested in leasing fiber and/or services, a few of which have already begun extending their networks to the nearest CMS interconnection point. As the project enters its third year, we will be working to secure formal agreements with these interested parties. Key Performance Indicators for next quarter include: New Network Miles Deployed - 200 New Network Miles Leased - 275 Total CAIs Connected - 9 Signed Agreements with Wholesalers and/or Last Mile Providers - 1 | Central Management Services, Illinois Department of | CMS continues to work with railroads to secure the remaining permits. The contractual issues have been resolved with 13 of 15 railroads. The respective legal departments are negotiating agreements for the last two railroads. There are approximately 40 open railroad permits pending final approval of the engineering drawings by the railroad. As reported previously, long fiber delivery schedules continue to be a critical path. We are receiving fiber on schedule and are on track to complete the project by the end of year three. We added conduit to two routes which will shorten the time needed to install the fiber once received. CMS has a pending route change request that includes multiple changes required to avoid planned road construction, address CAI changes, and finish connections to leased fiber. We are requesting immediate approval for the Kankakee, Danville, Lincoln and City of Bloomington changes as the contractors are reaching the point where they cannot continue without approval. | CMS is requesting approval for the pending route change request as soon as possible. The most time sensitive portions of the request are the Kankakee, Danville, Lincoln and City of Bloomington changes as the contractors are reaching the point where they cannot continue without approval. Delays with fiber delivery and permits have the greatest potential to impact projections for next quarter. To date 30% of the fiber has been received and we anticipate we will have 50% by the end of the quarter. Ninety percent of the permits have been secured. We will continue to work closely with the contractors to make adjustments to the construction schedule to maximize productivity based on the the availability of fiber and permits. Some adjustments that have been made so far are the addition of conduit along two routes and redirecting crews to other routes where materials and/or permits are available. | TRUE
NT10BIX5570108 | 2012 | Q3 | Q3 - 2012 | Overall the project is 41% complete. Total project expenditures are $39,739,397 which includes $20,216,447 in federal funds. These federal funds have supported a cumulative total of 427 full time equivalent jobs. The local match at the end of the quarter is 49%. Construction is underway on all 12 planned construction segments. By quarter end, 556 miles of conduit (76%) and 296 miles of fiber (30%) have been installed. Construction on 2 routes is complete: Kankakee and Champaign (91 miles) and rural communities surrounding Bloomington (28 miles). Kankakee to Chicago and Northern Laterals were forecasted to be complete by the end of the quarter; however, due to two outstanding permits and route changes construction will continue through the end of the calendar year. Kankakee to Chicago has 14 miles of fiber left to install. This includes boring under 2 railroad crossings. The Northern Laterals has 8 miles of fiber to install. CMS has all the permits required for the Northern Laterals. Installation will be slow as the remaining work is street crossings to community colleges in the Chicago suburbs where there are many restrictions on when the work can be performed to minimize the impact on road traffic. Contractors started work on inside plant at the CMS CAI sites. The sub recipient is evaluating bids for inside plant and plans to start work next quarter. The sub recipient completed the structural assessment on locations targeted for wireless towers. A bid for installation of the wireless equipment was issued in September. The final award was issued after the cutoff date for the quarter. The total leased fiber miles is 557 of 630 (88%). CMS is in negotiations for the remaining lease agreements. CMS received approval for Route Change #2. Route Change #3 for additional backbone routes and laterals has been submitted. CMS is forecasting it will complete the original project scope under budget and has identified opportunities to expand fiber and CAI connections within the approved service area. CMS and the sub recipient have secured commitments from the targeted 376 CAIs (100%) that will be directly connected via fiber. No new lateral connections where completed this quarter. The total connections remains at eight of which one is already using the BTOP funded infrastructure to receive improved service. An additional 1,100 CAIs are connected to the 80 miles of BTOP funded operational infrastructure thru non BTOP funded connections. As a result, these sites will see their broadband speeds more then double. CMS has entered into a contract with the Illinois Rural HealthNet (IRHN) to provide middle mile connectivity for their healthcare network. IRHN is a recipient of an FCC rural healthcare pilot program grant which provides high speed broadband services to rural hospitals and clinics throughout Illinois. CMS is evaluating the options for engaging with a partner to market and sell fiber and broadband services to businesses and wholesale service providers. CMS anticipates issues a Request for Information in the first quarter of 2013 to collect input from potential partners. The State's video production team delivered the first version of the video that showcases the project and the anchors that will benefit from the improved broadband speeds. The video will be showcased on the project website and used at conferences and community informational meetings. CMS has provided feedback to the video team for final editing. CMS continues to provide a monthly project update via email to community anchor institutions and interested organizations. The updates are also available on the Illinois Century Network website at http://www.illinois.net/IBOP/IBOP_EastCentral/Newsletters/IBOP_EC_Monthly_Update.html. The sub recipient also has a monthly update available at http://cirbn.org. | 296 | 275 | 3 | 282 | 296 | 0 | 0 | 293 | Baseline target is 391. The revised project schedule provided to NTIA set a target of 645. In addition to the fiber, 556 miles of conduit has been installed. | Baseline target is 668. The revised project schedule provided to NTIA set a target of 382. Based on approved route changes the forecasted new leased miles is 415. CMS is working on the 3 remaining lease agreements. Two with other state/governmental entities and one with a private company. | Baseline target is 3. The revised project schedule provided to NTIA set a target of 3. | Baseline target is 551. The revised project schedule provided to NTIA set a target of 288. The variance is due to actual mileage from the final route calculations. | Baseline target is 1,613. The revised project schedule provided to NTIA did not set a target for this indicator. The Baseline target was calculated incorrectly as the sum of the leased, new construction and existing upgraded miles which for this quarter equals 856. | Baseline target is 3. The revised project schedule provided to NTIA set a target of 0. | Baseline target is 3. The revised project schedule provided to NTIA set a target of 0. | Baseline target is 161 The revised project schedule provided to NTIA set a target of 95. There will be more interconnection points then originally planned. | 1 | 0 | 80 | Illinois Rural HealthNet | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | NA | 0 | 0 | 0 | 0 | Since only a small portion of the network is operational, there are no providers receiving new service at this time. | Since only a small portion of the network is operational, there are no providers receiving new service at this time. | Since only a small portion of the network is operational, there are no providers receiving new service at this time. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | 8 | 0 | 0 | 0 | The new leased fiber lit in 2011 positions these CAIs to connect at speeds up to 100 Mbps. Since only a small portion of the network (85 of 2,000 miles) is operational, the new service offerings are not available. Once fully deployed, these CAIs will realize a significant increase in broadband speeds as they move from 3-5 Mbps to 50-100 Mbps. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network (85 of 2,000 miles) is operational, the new service offerings are not available. Once fully deployed, these CAIs will realize a significant increase in broadband speeds as they move from 3-5 Mbps to 50-100 Mbps. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | 0 | 0 | 0 | 0 | 0 | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | 19767 | 0 | 0 | 0 | 0 | This represents the businesses near the leased fiber that is operational. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | NA | FALSE | NA | The cumulative spend estimated for next quarter is $61.7M which is 64% of the total project spend. The baseline projected a cumulative spend of $77.8M or 81%. The revised project schedule submitted to NTIA has a target of $67.7 or 71%. The difference between the revised project schedule and the PPR projection is approximately $6 million which is a result of costs coming in below budget for construction and delays earlier this year starting construction, inside plant and final equipment purchases. During the next quarter we expect construction for 5 of the 12 routes (Routes 2, 3, 5, 12 and 13) to be completed while work will continue on the remaining 7 routes. CMS will have a 13th route as a result of a route change to Spoon River College. The majority of the route will be leased fiber. CMS will need to complete a 3.5 mile build. Network design associated with the recently approved route modifications is forecasted to be completed by the end of the quarter. Staff will continue working to secure the remaining permits for the original routes and the permits associated with the route modifications. Inside plant and customer premise equipment installation will continue. CMS anticipates 14 additional CAIs located along the lit fiber path to start receiving service this quarter. CMS anticipates finalizing the contract template for fiber leases and will begin negotiating agreements with several wholesale service providers. CMS has been meeting with these providers for the past year but holding off on negotiations until finalizing a standard agreement. The sub recipient plans to award the wireless tower equipment bid as well as the contract to construct or augment current structures where wireless equipment will be installed. Once the equipment bid is awarded, the sub recipient will work to complete the frequency coordination. The sub recipient will also continue to work with the FCC to complete the approval process for installation of the monopole in Chenoa. CMS will be hosting a serious of informational meetings throughout the state to provide updates on the BTOP project and discuss the new services and rates. Key Performance Indicators for next quarter include: New Network Miles Deployed - 445 New Network Miles Leased - 397 Total CAIs Connected - 13 Signed Agreements with Wholesalers and/or Last Mile Providers - 2 | Central Management Services, Illinois Department of | CMS is now receiving fiber ahead of schedule. CMS is making progress on securing the remaining railroad permits. There are 17 needed from 6 different railroads. CMS has negotiated agreements and fees with all but 1 railroad. The open permits with the other 5 railroads are waiting for the railroads' final review and approval of insurance and contractor documents. CMS has been in contact with the railroads on a weekly basis to move along the permits. There does not appear to be any issues with the open permits, rather the railroad cites limited resources available to process the permit requests. The pending railroad permits are affecting completion of the following routes: #1 Kankakee to Chicago and #5 Champaign to Effingham. Routes 1 and 5 were scheduled to be completed by the end of October 2012. The open permits will likely push back the completion dates to December 2012. Route 3 was also scheduled to be completed by October. Permits delayed construction, but all permits have been received and the contractor is scheduled to complete work by the end of December. Other routes with open permits are 6, 7 and 9. The contractors have other work to perform on these routes so the open permits are not having as great of an impact on the schedule. CMS has found some success expediting the railroad permit process by engaging the state railroad association. The association has a vested interest in ensuring that delays in obtaining railroad permits does not jeopardize the BTOP and s | The outstanding railroad permits have the potential to delay construction for Routes 1, 5, 6, 7 and 9. Considering the number of outstanding permits is down to 17, the ability to complete the project by the end of the grant period is not in jeopardy. At this point in the project, CMS anticipates the impact will be limited to delayed completion dates for Routes 1 and 5 which were scheduled to be completed by the end of October. The contractors have completed all the other work associated with these routes. The contractors have other work to perform on Routes 6, 7 and 9 so the open permits are not having as great of an impact on the schedule. CMS anticipates that the project will be completed under budget. An Award Action Request to add additional CAIs and routes using the remaining grant funds has been submitted. CMS is requesting programmatic and EHP approval by the end of the calendar year in order to complete the work prior to the grant deadline. CMS is also preparing a request to purchase 100G cards for the optical equipment to increase the capacity of the lit network. | TRUE
NT10BIX5570108 | 2012 | Q4 | Q4 - 2012 | Overall the project is 59% complete; total project expenditures are $57M, with $25M federal funds and $32M match funds. These federal funds have supported 91.93 full time equivalent jobs during the past quarter. The local match at the end of the quarter is 56%. CMS has spent 94% of its cash match. The local match percentage will decrease through the remainder of the project as those budget items marked for federal spend are incurred. By quarter end, 655 miles of conduit (94%) and 562 miles of fiber (56%) have been installed. Construction on two routes is complete: Kankakee to Champaign (91 miles) and the rural communities surrounding Bloomington (28 miles). Four additional routes are 99% complete: Champaign to Effingham (100), Bloomington to Champaign (109 miles), Northern Laterals (15 miles), and Kankakee to Chicago (55 miles). The contractors are making good progress on the remaining routes. Ninety-nine percent of the permits have been secured for the original route. Lateral fiber builds to three additional CAI sites where completed this quarter, increasing the total number of CAIs capable of receiving service to 13 of 376. An additional 1,100 CAIs are connected to the 80 miles of BTOP funded operational infrastructure thru non BTOP funded connections. As a result, these sites will see their broadband speeds more than double. Inside plant activities are underway at the anchor institutions. Most of the customer equipment has been purchased and staged at locations throughout the service area in preparation for installation. The sub recipient awarded the wireless tower/equipment construction contract as well as the bid for wireless equipment. Equipment is expected to arrive in January. The sub recipient completed the required environmental agency consultations for the construction of the wireless equipment monopole. CMS finalized a contract template for fiber lease agreements. CMS is finalizing a fiber lease agreement with one wholesale provider and has provided quotes for fiber and/or service to an additional nine providers. CMS has developed a Request For Information (RFI) to seek input on plans to engage a partner for the sales and marketing of fiber and services to wholesale and commercial providers. The RFI is scheduled to be released in early February and will be followed by a Request For Proposals in the summer. CMS held eight informational meetings to provide updates on the BTOP project. A copy of the presentation is available at www.illinois.net. CMS continues to provide a monthly project update via email to community anchor institutions and interested organizations. The updates are also available on the Illinois Century Network website at http://www.illinois.net/IBOP/IBOP_EastCentral/Newsletters/IBOP_EC_Monthly_Update.html. The sub recipient also has a monthly update available at http://cirbn.org. | 562 | 275 | 3 | 282 | 837 | 0 | 0 | 346 | Baseline target is 559. In addition to the fiber, 655 miles of conduit has been installed. | Baseline target is 668 which would be 100% of the originally anticipated leased miles. Based on approved route changes the forecasted new leased miles is 415. CMS is working on the 3 remaining lease agreements. Two with other state/governmental entities and one with a private company. | Baseline target is 3. | Baseline target is 551. The variance is due to a miscalculation in the Baseline. CMS submitted 297 as the corrected target to NTIA following the February 2012 site visit. 282 will be the final project amount for existing network miles leased. | Baseline target is 1,781. The Baseline target was calculated incorrectly as the sum of the leased, new construction and existing upgraded miles. | Baseline target is 7. The wireless towers are scheduled for completion in April 2013. | Baseline target is 3. The wireless towers are scheduled for completion in April 2013. | Baseline target is 320. There will be more interconnection points then originally planned due to miscalculations in the Baseline. | 1 | 13 | 80 | Illinois Rural HealthNet | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | NA | 1 | 0 | 0 | 1 | Illinois Rural HealthNet is receiving a portion of the contracted services. The full contracted services will not be available until the remainder of the network is complete. | Since only a small portion of the network is operational, there are no providers receiving new service at this time. | Since only a small portion of the network is operational, there are no providers receiving new service at this time. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | 13 | 0 | 13 | 7 | The leased fiber lit in 2011 positions these CAIs to connect at speeds up to 100 Mbps. Since only a small portion of the network (85 of 1,830 miles) is operational, the new service offerings are not available. Once fully deployed, these CAIs will realize a significant increase in broadband speeds as they move from 3-5 Mbps to 50-100 Mbps. | All 13 connected CAIs previously had some level of broadband connectivity. | 4 of the 13 subscribers are receiving lit service as of the end of the quarter. | The published pricing lists 7 speed tiers, however, CMS will sell services at any speed using the per megabit price listed for the immediately lower tier. Current subscribers: 50 Mbps (3 subscribers) 11 Mbps (1 subscriber) | 0 | 0 | 0 | 0 | 0 | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | 19767 | 0 | 0 | 0 | 0 | This represents the businesses near the leased fiber that is operational. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Since only a small portion of the network is operational, there are no subscribers at this time. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | NA | FALSE | NA | The cumulative spend estimated for next quarter is $70M which is 73% of the total project spend. The Baseline projected a cumulative spend of $92M or 96%. The difference between the Baseline and the PPR projection is approximately $22 million which is a result of costs coming in below budget for construction and delays early in the project starting construction, inside plant and final equipment purchases. CMS anticipates that the four 99% complete routes will remain at this status during the next quarter as the work remaining is tied to reroutes and requirements to work around pending road construction. Fiber installation between Paris to Olney (93 miles) and Effingham to Collinsville (102 miles) should be close to completion provided the contractors are able to schedule flaggers with the railroad. Fiber installation from Champaign to Springfield (103 miles) should also be close to completion by the end of the quarter. Inside plant and customer premise equipment installation will continue. CMS anticipates 5 additional CAIs located along the lit fiber path to start receiving service this quarter for a total of 18 of 376 CAIs connected. The sub recipient will be working with the wireless contractor to establish the schedule for equipment installation. Work should begin by the end of the quarter. Key Performance Indicators for next quarter include: New Network Miles Deployed - 800 New Network Miles Leased - 400 Total CAIs Connected - 18 Signed Agreements with Wholesalers and/or Last Mile Providers - 3 | Central Management Services, Illinois Department of | CMS has secured all but one railroad permit. CMS is forecasting to complete the project scope under budget and has a pending award action request to add additional routes and CAIs. If this request is not approved shortly, we will not have enough time to complete the additional work. Based on some very recent developments, we will need another route change for the original project scope. CMS originally planned to lease fiber along a 12 mile path; however, the leased fiber is no longer available. We have identified existing conduit along the majority of the route but may need to complete a four or five block build. We are working with the permitting entities, design engineers and construction vendor up front to ensure a viable route. We will submit a summary of the changes to NTIA as quickly as possible. | CMS anticipates that the project will be completed under budget. An Award Action Request to add additional CAIs and routes using the remaining grant funds has been submitted. If not approved in this quarter, it will be difficult to complete the work prior to the grant deadline. Based on some very recent developments, we will need approval for another route change for the original project scope. CMS originally planned to lease fiber along a 12 mile path; however, the leased fiber is no longer available. We have identified existing conduit along the majority of the route but may need to complete a four or five block build. We are working with the permitting entities, design engineers and construction vendor up front to ensure a viable route. We will submit the change request as quickly as possible. | TRUE
NT10BIX5570108 | 2013 | Q1 | Q1 - 2013 | Overall the project is 69% complete; total project expenditures are $66M, with $34M federal funds and $32M match funds. The federal funds supported 91.93 full-time equivalent jobs during the past quarter. The local match at the end of the quarter is 48%. CMS has spent 94% of its cash match. The local match percentage will continue to decrease through the remainder of the project as those budget items marked for federal spend are incurred. By quarter end, 696 miles of conduit (100%) and 895 miles of fiber (86%) have been installed. Construction on four routes is complete: P02: Kankakee to Champaign (91 miles) P04 Bloomington/Normal (67 miles) P05 Champaign to Effingham (100 miles) P12 rural communities surrounding Bloomington (28 miles). Six additional routes are 99% complete: P01 Kankakee to Chicago (55 miles) - complete except for a 10 mile re-route that was just approved. P03 Bloomington to Champaign (109 miles) - complete except for a 4 mile re-route that is approved and under construction. P06 Paris to Olney (93 miles) - on schedule to be finished within the next 30 days. P07 Effingham to Collinsville (102 miles) - complete except for a 4 mile lateral. P08 Champaign to Springfield (103 miles) - complete except for pulling fiber into the Springfield POP. P13 Northern Laterals (15 miles) - complete except for 3 short laterals. Status for the remaining two routes is: P09 Quincy to Springfield (79 miles) - boring under the Illinois River is complete, approximately 70% of the fiber is installed with approximately 2,400 feet of rock left to bore. P10 Quincy to Macomb (133 miles) - 52% complete. Lateral fiber builds to six additional CAI sites where completed this quarter, increasing the total number of CAIs capable of receiving service to 19 of 325. An additional 1,100 CAIs are connected to the 80 miles of BTOP funded operational infrastructure through non BTOP funded connections. As a result, these sites will see their broadband speeds more than double. The sub recipient's contractor has started construction at the wireless tower locations. The wireless equipment has been received and will be installed next quarter. This quarter CMS executed one agreement to sell/lease dark fiber and is in negotiations with several wholesale providers. As part of the sales and marketing strategy, CMS issued a Request For Information (RFI) to seek input on plans to engage a partner for the sales and marketing of fiber and services to wholesale providers. Responses were received from eight interested vendors. Information from the RFI responses will assist CMS in developing the Request For Proposals (RFP) that will be released midyear. CMS continues to provide a monthly project update via email to community anchor institutions and interested organizations. The updates are also available on the Illinois Century Network website at http://www.illinois.net/IBOP/IBOP_EastCentral/Newsletters/IBOP_EC_Monthly_Update.html. The sub recipient also has a monthly update available at http://cirbn.org. | 895 | 399 | 3 | 282 | 1294 | 0 | 0 | 412 | Revised target is 1,035. Fiber construction is behind due EA delays, delayed starts, and route changes. | Revised target is 459. CMS is working on the 2 remaining lease agreements with other state/governmental entities. | Revised target is 6. | Revised target is 282. | Revised target is 1,494. Fiber construction is behind due to EA delays, delayed starts, and route changes. | Baseline target is 7. Completion of the tower design and construction specifications were delayed. Construction has started and is forecasted to be completed next quarter. | Baseline target is 3. Completion of the tower design and construction specifications were delayed. Construction has started and is forecasted to be completed next quarter. | Baseline target is 320. There will be more interconnection points then originally planned due to miscalculations in the Baseline. | 2 | 12 | 80 | Illinois Rural HealthNet and PEG Bandwidth | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | NA | 1 | 0 | 1 | 1 | Illinois Rural HealthNet is receiving a portion of the contracted services. The full contracted services will not be available until the remainder of the network is complete. | Since only a small portion of the network is operational, there are no providers receiving new service at this time. | PEG Bandwidth has purchased dark fiber along a route still under construction. | CMS and ISU will sell Ethernet services at any speed between 10 Mbps and 10 Gbps including dark fiber and wave services. Current subscribers: 10 Gbps (1 subscriber) Dark Fiber (1 subscriber). | 19 | 0 | 19 | 19 | Since only a small portion of the network (322 of 1,900 miles) is operational, the new service offerings are available in a limited area only. Once fully deployed, these CAIs will realize a significant increase in broadband speeds as they move from a range of 3-5 Mbps to a range of 50-100 Mbps. | All 19 connected CAIs previously had some level of broadband connectivity. | 4 of the 19 subscribers are receiving lit service as of the end of the quarter. | CMS and ISU will sell Ethernet services at any speed between 10 Mbps and 10 Gbps including dark fiber and wave services. Current subscribers: 50 Mbps (3 subscribers) 11 Mbps (1 subscriber). The remaining 15 CAIs are not receiving service at this time and are undecided on the speed tier. | 0 | 0 | 0 | 0 | 0 | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | 164913 | 0 | 0 | 0 | 0 | This represents the businesses near the operational fiber. | CMS is selling wholesale services. ISU, the sub recipient will sell directly to businesses when their portion of the fiber is operational. | CMS is selling wholesale services. ISU, the sub recipient will sell directly to businesses when their portion of the fiber is operational. | CMS is selling wholesale services. ISU, the sub recipient will sell directly to businesses when their portion of the fiber is operational. | ISU will offer: dark fiber, Ethernet services ranging in speeds of 1 Mbps to 10 Gbps and Internet services. | NA | FALSE | NA | The cumulative spend estimated for next quarter is $77M which is 80% of the total project spend. The Baseline projected a cumulative spend of $96M or 100%. The difference between the Baseline and the PPR projection is approximately $19M which is a result of costs coming in below budget for construction and delays early in the project starting construction, inside plant and final equipment purchases. CMS has received approval to add additional routes/CAIs and will be working on those routes through the remainder of the project. CMS anticipates completing 99% of the activity associated with the project next quarter; however, invoices will continue to be received and paid in the following quarter. Fiber installations, fiber leases and wireless links will be complete except work associated with the two recently approved route changes and a lateral build to one community college that may require an additional route change. CMS will be requesting an extension to complete the recently approved Chicago reroute. By the end of next quarter, CMS anticipates 300 CAIs will be connected and capable of receiving services. Many K-12 CAIs will wait until July 1 to transition service in order to utilize E-rate funds to off-set the ongoing service costs. Key performance indicators for next quarter (cumulative): Total Miles - 1,764 of 1,782 New Network Miles Deployed - 1,020 of 1,035 New Leased Miles - 459 of 459 Upgraded Miles - 3 of 6 Existing Leased Miles - 282 of 282 Total CAIs Connected - 300 of 325 Signed Agreements with Wholesalers and Last Mile Providers - 5 | Central Management Services, Illinois Department of | CMS has received approval for two pending route changes. One change is associated with a 10 mile re-route from the south side of Chicago to downtown. CMS is working with the Illinois Department of Transportation, Chicago Transit Authority and City of Chicago to work through easement and permit issues. CMS plans to seek a no-cost extension through September 30, 2013 to complete this route change. The second approved route change is to connect additional CAIs with the remaining grant funds. | CMS plans to seek a no-cost extension through September 30, 2013 to complete the 10 mile route change for the path from the south side of Chicago to downtown and to continue work on the recently approved route/CAI expansions. | TRUE
NT10BIX5570108 | 2013 | Q2 | Q2 - 2013 | Overall the project is 80% complete; total project expenditures are $77M, with $44M federal funds and $33M match funds. The federal funds supported 124 full-time equivalent jobs during the past quarter. The local match at the end of the quarter is 43%. CMS has spent 94% of its cash match. The local match percentage will continue to decrease through the remainder of the project as those budget items marked for federal spend are incurred. At the end of the quarter, 1,026 of 1,035 (99%) miles of new construction fiber was complete. 438 of 459 (95%) of the new fiber leases were executed. One new wireless tower was complete. Approximately 57% of the network is operational with 223 of 325 (69%) of the CAIs connected. The sub recipient, Illinois State University, completed 7 miles of approved expansion miles. CMS is continuing to work on completing four short laterals and the last few miles associated with a backbone route. After the end of the quarter, CMS received an extension through September 30, 2013. Five additional whole sale agreements for dark fiber were executed. CMS is finalizing the Request For Proposals for the sales and marketing partner. CMS continues to provide a monthly project update via email to community anchor institutions and interested organizations. The updates are also available on the Illinois Century Network website at http://www.illinois.net/IBOP/IBOP_EastCentral/Newsletters/IBOP_EC_Monthly_Update.html. The sub recipient also has a monthly update available at http://cirbn.org. | 1026 | 438 | 3 | 282 | 1464 | 7 | 1 | 438 | Revised target is 1,035. The final number will come in a little above the target due to completing approved expansion routes. | Revised target is 459. CMS is working on the 2 remaining lease agreements with other governmental entities. | Revised target is 6. Work on the remaining 3 miles is complete. The asset will be transferred to the project books next quarter. | Revised target is 282. | Revised target is 1,494. 21 miles of new fiber and 2 leases remain outstanding. | Baseline target is 7. | Baseline target is 3. After an engineering analysis was completed on the tower locations it was determined that only 1 location required a new tower structure. Existing towers were used for the other locations. | Baseline target is 320. There will be more interconnection points then originally planned due to miscalculations in the Baseline. | 7 | 21 | 80 | Illinois Rural Healthnet, PEG Bandwidth (2 agreements), Illinois Rural Electric Cooperative, Kaneland School District, Illinois Eastern Community Colleges, Paris School District. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services. | NA | 1 | 0 | 6 | 1 | Illinois Rural HealthNet is receiving a portion of the contracted services. The full contracted services will not be available until the remainder of the network is complete. | All but one signed agreement is for dark fiber. | The providers have not taken possession of the contracted dark fiber. | CMS and ISU will sell Ethernet services at any speed between 10 Mbps and 10 Gbps including dark fiber and wave services. Current subscribers: 10 Gbps (1 subscriber) Dark Fiber (6 subscriber). | 223 | 0 | 223 | 223 | 223 of 325 CAIs are connected and capable of receiving services. | All 223 connected CAIs previously had some level of broadband connectivity. | 96 of the 223 subscribers are receiving lit service as of the end of the quarter. | CMS and ISU will sell Ethernet services at any speed between 10 Mbps and 10 Gbps including dark fiber and wave services. Current subscribers: 1-100 Mbps (23 subscribers) 101-200 Mbps(2 subscribers) 201-300 Mbps (5 subscribers) 301-400 Mbps (13 subscribers) 401-500 Mbps (12 subscribers) 501-600 Mbps (2 subscribers) 601-700 Mbps (0 subscribers) 701-800 Mbps (2 subscribers); >1 Gbps (37 subscribers). The remaining 127 CAIs are not receiving service at this time and are undecided on the speed tier. | 0 | 0 | 0 | 0 | 0 | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | 179172 | 32 | 0 | 32 | 32 | This represents the businesses near the operational fiber. | 16 of 32 connected businesses are receiving lit services as of the end of the quarter. | All 16 businesses receiving services previously had some level of broadband connectivity. | All 32 connected businesses are/will be receiving improved broadband services. | ISU will sell Ethernet services at any speed between 10 Mbps and 10 Gbps including dark fiber and wave services. Current subscribers: 1-100 Mbps (8 subscribers) 101-200 Mbps(3 subscribers) 201-300 Mbps (4 subscribers) 301-400 Mbps (0 subscribers) 401-500 Mbps (0 subscribers) 501-600 Mbps (0 subscribers) 601-700 Mbps (0 subscribers) 701-800 Mbps (0 subscribers); >1 Gbps (1 subscribers). The remaining 16 businesses are not receiving service at this time and are undecided on the speed tier. CMS does not intend to sell directory to businesses directly. Whenever possible, businesses will be served by a third party provider purchasing wholesale services from CMS. | NA | FALSE | NA | The cumulative spend estimated for next quarter is $92M which is 95% of the total project spend. The Baseline projected a cumulative spend of $96M or 100%. The difference between the Baseline and the PPR projection is approximately $4M which is a result of delays early in the project starting construction, inside plant and final equipment purchases. CMS anticipates construction activities to continue through September 30 with the final $4M in payments processed during the close out period. CMS has received an extension through September 30 to allow time to complete the remaining 21 miles of new construction plus approved expansion routes. Key performance indicators for next quarter (cumulative): Total Miles - 1,799 of 1,782 New Network Miles Deployed - 1,052 of 1,035 (includes 17 expansion miles) New Leased Miles - 459 of 459 Upgraded Miles - 6 of 6 Existing Leased Miles - 282 of 282 Total CAIs Connected - 340 of 325 (includes 15 expansion CAIs) Signed Agreements with Wholesalers and Last Mile Providers - 9 | Central Management Services, Illinois Department of | CMS is working on completing four laterals and the last few miles of a backbone route. The four laterals include: 1) 9 miles to McHenry College of which 6 of 9 miles is complete. The remaining 3 miles are on hold until the IL Dept. of Transportation acquires easements for property associated with an ongoing road expansion project. 2) Triton College - construction will begin in July on the 4 mile route. CMS requires 2 railroad permits before the work can be completed. 3) Morton College - construction will begin in July on the 1 mile route. 4) Danville Community College - CMS has submitted a route modification request for a 2 block portion of this lateral. Construction will start in July on the approved portion of the route. The remaining work on the backbone route is 11 miles in the City of Chicago. CMS will be pulling fiber in existing conduit for 10 of the 11 miles. The contractor will begin pulling fiber in July. | Construction for the McHenry lateral is on hold until the Illinois Department of Transportation acquires easements along the remaining 3 miles. If this work cannot be completed in the next quarter, CMS plans to work with the community college and community to complete the route post BTOP using other funds. CMS is working to obtain approval from seven tribes for expansion routes. Approval has been received from three of the seven tribes. We have received little to no response to the information and phone calls sent to the other four tribes. CMS has requested NTIA assistance in contacting the appropriate resources at the four tribes. | TRUE
NT10BIX5570108 | 2013 | Q3 | Q3 - 2013 | Overall the project is 86% complete; total project expenditures are $83M with $50M federal funds and $33M match funds. The federal funds supported 97 full-time equivalent jobs during the past quarter. The local match at the end of the quarter is 40%. CMS has spent 96% of its cash match. The local match percentage will continue to decrease through the remainder of the project as those budget items marked for federal spend are incurred. CMS received approval to extend the grant through December 31, 2013 which allows time to complete the Chicago construction. Originally, CMS planned to lease fiber to the Midwest Internet peering location in downtown Chicago; however, after the award the fiber was no longer available. CMS has added 11 miles of new construction to complete this route. CMS has received all permits required to complete the route and construction is underway. Fiber is installed along 10 of the 11 miles and conduit is nearly complete along the remaining 1 mile. CMS and its sub recipient Illinois State University (ISU) have added 17 miles of new construction and 17 CAI connections as a result of completing the original scope activity under budget. At the end of the quarter, 1,048 of 1,052 (99%) miles of new construction fiber were complete. 448 of 459 (98%) miles of the new fiber leases were executed. The seven wireless links are operational. Approximately 88% of the network is operational with 350 of 380 (92%) of the CAIs connected. CMS and ISU are negotiating more than a dozen additional wholesale agreements. This is in addition to the eight existing wholesale lease agreements. The CMS network is interconnected with more than 20 last mile service providers. CMS is finalizing the Request For Proposals for the sales and marketing partner. Central Illinois Regional Broadband Network (CIRBN) has been added as a sub recipient as contemplated in the original grant application. CIRBN was formed as a non-profit specifically to operate the portion of the network built by ISU in accordance with the grant rules and obligations. The network operations, rates, services, and customer agreements will remain the same. ISU will continue to be a board member of CIRBN. CMS continues to provide a monthly project update via e-mail to community anchor institutions and interested organizations. The updates are also available on the Illinois Century Network website at http://www.illinois.net/IBOP/IBOP_EastCentral/Newsletters/IBOP_EC_Monthly_Update.html. The sub recipient also has a monthly update available at http://cirbn.org. | 1048 | 448 | 6 | 282 | 1496 | 7 | 1 | 913 | Revised target is 1,052 with the expansion routes. | Revised target is 459. CMS is working to complete one remaining lease with a county government. | Revised target is 6. | Revised target is 282. | Revised target is 1,511. | Baseline target is 7. | Baseline target is 3. After an engineering analysis was completed on the tower locations it was determined that only 1 location required a new tower structure. Existing towers were used for the other locations. | Baseline target is 320. There are more interconnection points then originally planned due to miscalculations in the Baseline. | 8 | 16 | 80 | Illinois Rural Healthnet, PEG Bandwidth (2 agreements), Illinois Rural Electric Cooperative, Kaneland School District, Illinois Eastern Community Colleges, Paris School District, Metro Communications. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services | NA | 1 | 0 | 7 | 1 | Illinois Rural HealthNet is receiving a portion of the contracted services. The full contracted services will not be available until the remainder of the network is complete. | All but one signed agreement is for dark fiber. | 7 of 8 wholesale agreements are for dark fiber. The leased dark fiber has been turned over to 4 of 7 providers. | CMS and ISU will sell Ethernet services at any speed between 10 Mbps and 10 Gbps including dark fiber and wave services. Current subscribers: 10 Gbps (1 subscriber) Dark Fiber (7 subscribers). | 350 | 2 | 349 | 350 | 350 of 380 CAIs are connected and capable of receiving services. | 2 CAIs receiving service previously had no broadband connectivity. | 349 connected CAIs previously had some level of broadband connectivity. | CMS and ISU will sell Ethernet services at any speed between 10 Mbps and 10 Gbps including dark fiber and wave services. Current subscribers: 1-100 Mbps (149 subscribers) 101-200 Mbps(25 subscribers) 201-300 Mbps (21 subscribers) 301-400 Mbps (22 subscribers) 401-500 Mbps (13 subscribers) 501-600 Mbps (2 subscribers) 601-700 Mbps (4 subscribers) 701-800 Mbps (2 subscribers); 801-900 Mbps (8 subscribers); >1 Gbps (61 subscribers). The remaining 43 CAIs are not receiving service at this time and are undecided on the speed tier. | 0 | 0 | 0 | 0 | 0 | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | 208692 | 32 | 0 | 32 | 32 | This represents the businesses near the operational fiber. | All 32 connected businesses are receiving lit services as of the end of the quarter. | All 32 businesses previously had some level of broadband connectivity. | All 32 connected businesses are/will be receiving improved broadband services. | ISU will sell Ethernet services at any speed between 10 Mbps and 10 Gbps including dark fiber and wave services. Current subscribers: 1-100 Mbps (8 subscribers) 101-200 Mbps (2 subscribers) 201-300 Mbps (5 subscribers) 3; >1 Gbps (17 subscribers). CMS does not intend to sell directory to businesses directly. Whenever possible, businesses will be served by a third party provider purchasing wholesale services from CMS. | NA | FALSE | NA | CMS is on schedule to complete the project by the end of the next quarter. Forecasted spend is $96,329,030 of $96,382,028 (99%). The remaining funds are budgeted for eligible close out expenses. Activities during next quarter will focus on completing the construction in Chicago, completing a few remaining splices, executing the final fiber lease, and installing the upgraded equipment. CMS will also begin preparing for project close out. CMS anticipates the final key performance indicators to be: Total Miles - 1,799 New Miles - 1,052 New Leased Miles - 459 Upgraded Miles - 6 Existing Leased Miles - 282 CAIs Connected - 381 | Central Management Services, Illinois Department of | All permits have been secured and construction is underway. As previously reported, CMS will not be able to finish the lateral to McHenry College due to a planned road expansion project. CMS has completed 6 of 9 miles. The remaining 3 miles are on hold until the IL Dept. of Transportation acquires easements for property along the expansion. At this time, it does not appear that the easements will be secured before the grant deadline. CMS will complete the build at a future date when the easements are secured. | As previously reported, 3 of a 9 mile lateral build to McHenry Community College is on hold due to an Illinois Department of Transportation road widening project. CMS will complete the build with local funds once the easements for the expanded right-of-way are acquired. CMS contractor's have completed all possible work associated with the lateral including the inside plant work at the college. | TRUE
NT10BIX5570108 | 2013 | Q4 | Q4 - 2013 | Central Management Services (CMS) successfully completed construction and turn up for the planned fiber network and CAI connections. CMS completed installation and turn up of the approved upgraded 100G optical equipment. The final fiber network includes 1,052 of new construction fiber, 460 miles of new leased fiber, 6 miles of upgraded fiber, 282 miles of existing leased fiber and 3 wireless towers. The final number of CAIs connected and/or improved using BTOP funds is 3,711. That total includes 2,837 K12 schools, 187 public libraries, 32 healthcare facilities, 34 community colleges, 151 higher education sites, 89 other community support organizations, 32 public safety entities, and 349 government entities. CMS completed the project within budget with a final project cost of $95M. During the height of construction, 91 FTEs where dedicated to the project including professional engineers, construction foreman, equipment operators, fiber installers, and fiber splicers. The new network has resulted in significantly faster broadband speeds and lower operating costs. The speed of the Illinois Century Network (the CMS broadband network) backbone increased from 2.5 Gbps to 10 Gbps with portions of the backbone operating at 100 Gbps. At the same time, CMS is projecting a decrease in its annual operating expenses despite greater utilization and normal cost increases. On average, CAIs have seen a 500% increase in broadband speeds while the cost per Mbps has decreased by more than 80%. For example, Limestone Community High School in Bartonville IL has increased its broadband speeds from 13 Mbps to 50 Mbps while decreasing its monthly spend by $2,200. The bandwidth for Iroquois West High School in Gillman IL has increased from 3 Mbps to 50 Mbps at a cost increase of only $350 per month. As a result of the increased bandwidth, the school is piloting 1:1 devices in three grade levels with a plan to expand to all grade levels within three years. CMS and ISU have executed ten dark fiber agreements and are in negotiations with several additional providers. Service providers are leveraging the dark fiber to expand their service area and to access Internet peering points in Chicago IL. These service providers are expanding their service area to provide faster broadband speeds to more businesses and house holds. CMS' business strategy is to service CAIs directly and leverage our current and future service provider partners to reach the residential and business customers. Our wholesales services have been designed and priced to encourage service providers to utilize the fiber infrastructure to expand and improve their service offerings. We are working with several wholesale providers who are interested in interconnecting their vast multi-state infrastructure with the intent of reselling services to its service provider customer base. We have connected our fiber network to the neighboring BTOP funded networks such as UC2B, Delta Communications (Clearwave), DATA Network, and iFiber to provide seamless end to end connectivity for CAIs and service providers. The capital investment in the open access fiber infrastructure has ignited a wave of fiber investments from service providers, as competition for services increases the customer is benefiting from faster speeds and better pricing, and our schools, libraries, health care providers and other CAIs are expanding the use of technology and digital education within its daily operations. | 1052 | 460 | 6 | 282 | 1512 | 7 | 1 | 913 | None | None | None | None | None | None | Baseline target is 3. After an engineering analysis was completed on the tower locations it was determined that only 1 location required a new tower structure. Existing towers were used for the other locations. | Baseline target is 320. There are more interconnection points then originally planned due to miscalculations in the Baseline. | 10 | 17 | 80 | Illinois Rural Healthnet, PEG Bandwidth (3 agreements), Illinois Rural Electric Cooperative, Kaneland School District, Illinois Eastern Community Colleges, Paris School District, Metro Communications, Prairie Power. | Dark Fiber, Lambda/Wave Services, Ethernet Services ranging in speeds of 10 Mbps to 10 Gbps and Internet Services | NA | 1 | 0 | 9 | 10 | NA | NA | 9 of 10 wholesale agreements are for dark fiber. The leased dark fiber has been turned over to 5 of 9 providers. | CMS and ISU will sell Ethernet services at any speed between 10 Mbps and 10 Gbps including dark fiber and wave services. Current subscribers: 10 Gbps (1 subscriber) Dark Fiber (9 subscribers). | 3711 | 2 | 3709 | 3711 | 3,711 CAIs are connected and capable of receiving services. 385 CAIs were connected directly as a result of a new fiber build. 3,326 CAIs were connected as a result of building fiber to existing access points where the CAIs were already connected. These CAIs are benefiting from the faster speeds made possible by the BTOP project. | 2 CAIs receiving service previously had no broadband connectivity. | 3,709 connected CAIs previously had some level of broadband connectivity. | CMS and ISU will sell Ethernet services at any speed between 10 Mb and 10 Gb including dark fiber and wave services. Current subscribers: <10 Mb (142 subscribers) >=10 Mb and <50 Mb (1,312 subscribers) >=50 Mb and <100 Mb (607 subscribers) >=100 Mb and <1 Gb (928 subscribers) >=1 Gb (722 subscribers). | 0 | 0 | 0 | 0 | 0 | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | NA - The project is a CCI project with no last mile component. | 285410 | 32 | 0 | 32 | 32 | This represents the businesses near the operational fiber. | All 32 connected businesses are receiving lit services . | All 32 businesses previously had some level of broadband connectivity. | All 32 connected businesses are receiving improved broadband services. | ISU will sell Ethernet services at any speed between 10 Mbps and 10 Gbps including dark fiber and wave services. Current subscribers: 1-100 Mbps (8 subscribers) 101-200 Mbps (2 subscribers) 201-300 Mbps (5 subscribers) 3; >1 Gbps (17 subscribers). CMS does not intend to sell directory to businesses directly. Whenever possible, businesses will be served by a third party provider purchasing wholesale services from CMS. | NA | FALSE | NA | CMS will work with NTIA to submit all required close out documents. | Central Management Services, Illinois Department of | None. CMS has successfully completed the project. | NA | TRUE
NT10BIX5570109 | 2010 | Q4 | Q4 - 2010 | Thre primary efforts of the Carver County Open Fiber Initiative (CCOFI) project team related to our environmental assessment (EA) in which the County worked withy and received final conclusion communications from the various tribal entities with interest in our project; we finalized our meetings with all community anchor institutions (CAI's) relating to grant submitted laterals as well as gathering information on potential future optional add on laterals; the County reached out to various service providers such as telco's cable companies, wireless providers to discuss the project and potential interconnection opportunities; the County hired a consultant to complete an archaeological review of the project and received a final report that was submitted to MN SHPO for review. Other non environmental assessment project efforts focused on futhering our construction partner contract negotiations, hut permitting, the initial drafting of a community outreach packet for use by our CAI's, furthering the formation of our Broadband Initiatives Taskforce (BIT) which will act as a project communication and sounding board entity relating to the project, and creating a more robust and useful fiber public information website regarding our project; and unrelated to the funding of the ARRA project but critical to an interconnection point to the CCOFI fiber ring is the termination of the fiber connection between the Carver County and Scott County Gov't Centers.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The CCOFI project team anticipates the furthering or completion of the following components of the period in the 1st quarter of 2011; complete the environmental assessment and submit to NTIA; begin non hut construction permitting; complete contract negotiations with construction management vendor and finalize contract; complete construction bid document and issue construction bid; have first meeting of BIT group; send out CAI community outreach packets; publish new interactive fiber project map on public website. | Carver, County of | The project is on track as we have defined in our baseline. The most notable source of issue regarding the past quarter has related to the resources and time needed to complete and follow up on the variety of reports that are required in the project. The various reports have a considerable amount of redundancy and duplication and at times it can be difficult to know what is due, to whom and what information is being requested as you read through the at times somewhat vague questions in the report. | N/A | TRUE
NT10BIX5570109 | 2011 | Q1 | Q1 - 2011 | The primary efforts of the Carver County Open Fiber Initiative (CCOFI) project team were the work on our environmental assessment (EA) and construction bid for the project. In January the project team met the required deadline and submitted the first draft of our EA. At the end of February the County received a positive response regarding our submission, noting that only minor edits or additions were needed. The project team reviewed the response and began gathering additional information and making the needed corrections. Also in February the County received notice of the requirement to complete additional Tribal Consultations not originally requested in November, with one of the Tribes requiring the completion of an ethnographic report of the affected project area. The County began efforts to communicate with the additional Tribes and to create the ethnographic report. In parallel the County also worked on tightening the fiber route to reduce the amount of swag and continued our efforts on permitting for railway crossings and the required permits and contracts associated with the three fiber hut locations. The other primary effort during this quarter was the creation and issuing of the construction bid for the project, which is approximately 75% of the project budget. On February 17th the County issued the construction bid and held a vendor conference on February 25th with a repeat on March 9th followed by site visits to all base ring hub sites. Other project team | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A3 | N/A | 0 | 0 | 0 | 0 | We anticipated having one signed agreement during this quarter but contract negotiations were still underway. We anticipate having this provider signed by 3rd quarter 2011. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The CCOFI project team anticipates the furthering or completion of the following components of the project in the 2nd quarter of 2011; complete the environmental assessment and receive either a conditional or full FONSI; complete contract negotiations with construction management vendor and finalize contract; award construction bid and begin base ring construction; begin gathering information for the drafting of the equipment bid. | Carver, County of | N/A | Due to the EA not being completed in this quarter, the additional expenditures for engineering dollars were not yet realized, but with the completion of the EA, they will be realized in that quarter. | TRUE
NT10BIX5570109 | 2011 | Q2 | Q2 - 2011 | On June 13th the CCOFI received our Finding of No Significant Impact (FONSI) for our environmental assessment (EA). Also, during this quarter we updated our project route to properly place the fiber in the respective road rights of way and utility easements. To be vigilant regarding any potential environmental impacts, we have submitted EA addendums for four specific locations on the project route and we are awaiting final NTIA sign off on these changes. These addendums do not affect our original FONSI, nor do they hinder any preparation or start of construction outside of the four identified locations. On June 21st the Carver County Board approved the recommended construction vendors for the project from the construction bids received on April 5th. Carver County Open Fiber Initiative (CCOFI) staff performed an intensive review of bidders for the various bid components in an effort to meet our project objectives and provide our best recommendations on the lowest responsible bidders. The construction budget for the project is approximately $5.5 million of the overall project budget. The project awarded MP Nexlevel the bid for construction of the base fiber ring and laterals and awarded Power&Tel the bid for fiber cable and conduit. We did not award a bid for fiber splicing as those duties were rolled into our overall construction management functions. Staff began communicating with awarded vendors on planning, preparation and staging for the start of construction. CCOFI staf | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Our network miles deployed are at 0 miles, which is less than our originally stated 5 miles. This lower number was created by two factors, the first being the wait time in receiving our EA approval, which we received at the end of this quarter. The second being the availability of fiber, which affected our construction bid award process, which we also finalized at the end of this quarter. With our EA approved and orders for fiber and conduit placed and conduit shipping next quarter, we look to deploy the resources needed to regain our project timeline. | N/A | N/A | N/A | Our number of miles of new fiber are at 0 miles, which is less than our originally stated 5 miles. This lower number was created by two factors, the first being the wait time in receiving our EA approval, which we received at the end of this quarter. The second being the availability of fiber, which affected our construction bid award process, which we also finalized at the end of this quarter. With our EA approved and orders for fiber and conduit placed and conduit shipping next quarter and anticipated shipment of fiber in November, we look to deploy the resources needed to regain our project timeline in 2011. | N/A | N/A | No variance from baseline Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) Our number of miles of new fiber are at 0 miles, which is less than our originally stated 5 miles. This lower number was created by two factors, the first being the wait time in receiving our EA approval, which we received at the end of this quarter. The second being the availability of fiber, which affected our construction bid award process, which we also finalized at the end of this quarter. With our EA approved and orders for fiber and conduit placed and conduit shipping next quarter and anticipated shipment of fiber in November, we look to deploy the resources needed to regain our project timeline in 2011e (describe your reasons for any variance from the baseline plan or any other relevant information) Our number of miles of new fiber are at 0 miles, which is less than our originally stated 5 miles. This lower number was created by two factors, the first being the wait time in receiving our EA approval, which we received at the end of this quarter. The second being the availability of fiber, which affected our construction bid award process, which we also finalized at the end of this quarter. With our EA approved and orders for fiber and conduit placed and conduit shipping next quarter and anticipated shipment of fiber in November, we look to deploy the resources needed to regain our project timeline in 2011. | 0 | 0 | 0 | N/A | No variance from baseline | N/A | 0 | 0 | 0 | 0 | We noted in our 1st quarter 2011 report that we anticipate to have one signed agreement in place by 3rd quarter 2011. | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | N/A | FALSE | N/A | We look to complete all community anchor institution site visits and schedule a construction kick off event that will begin actual construction next quarter. | Carver, County of | N/A | Depending on maintaining the estimated shipping start date for our fiber order, we may not fully realize this expenditure until a later quarter, since the product is not billed until shipped. Also, our timeline anticipates a normal construction season, but if we have unseasonable weather, similar to what we have received this past winter and spring, both which have been record setting in regards to snow accumulation and then corresponding spring flooding, tied with record setting rainfall, it may impact our construction speed, which we would look to regain at the start of construction in spring of 2012. | TRUE
NT10BIX5570109 | 2011 | Q3 | Q3 - 2011 | We completed the key contracts and agreements needed that allowed us to begin construction of the project. The first contract in place was our construction contract with MP Nexlevel, our chosen construction vendor. Signing this contract allowed MP Nexlevel to begin staging materials and lining up human resources and also allowed us to work together to establish a construction kick off and the following construction scheduling. The second agreement was our purchase agreement with Power and Telephone, our chosen supplier for fiber optic cable and conduit. This agreement locked in our order at the factory for the high demand fiber optic cable and allowed us to begin receiving shipments of the dual duct conduit that the fiber will be installed within. Finally, we completed the mutually dependent contract for construction management services and associated project pre-engineering with Jaguar Communications along with the Indefeasible Right to Use (IRU), which establishes Jaguar Communications as our planned on initial private side anchor service provider in the project. To be vigilant regarding any potential environmental impacts, there were four specific locations on the project route where we updated our installation path. In making these changes we had to re-submit them to the Minnesota Historical Society State Historic Preservation Office (SHPO) and the US Fish and Wildlife Service for review. We then had to complete Environmental Assessment Addendums and submit to NTI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Our new network miles deployed is at 0, which is less than our originally stated 50. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, we will not be completing any new network miles until the end of the project, at which time we would promptly be at 100%. Instead, we are installing conduit and have installed approximately 40 miles as of September 30. | N/A | N/A | N/A | Our number of miles of new fiber is at 0, which is less than our originally stated 50. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, we will not be completing any new fiber miles until the end of the project, at which time we would promptly be at 100%. Instead, we are installing conduit and have installed approximately 40 miles as of September 30. | N/A | N/A | No variance from baseline Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) project, at which time we would promptly be at 100%. Instead, we are installing conduit and have installed approximately 40 miles as of September 30. Our number of miles of new fiber is at 0, which is less than our originally stated 50. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, we will not be completing any new fiber miles until the end of the project, at which time we would promptly be at 100%. Instead, we are installing conduit and have installed approximately 40 miles as of September 30e (describe your reasons for any variance from the baseline plan or any other relevant information) project, at which time we would promptly be at 100%. Instead, we are installing conduit and have installed approximately 40 miles as of September 30. Our number of miles of new fiber is at 0, which is less than our originally stated 50. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. Since we will not be lighting up our fiber in phases, but instead lighting up the project at the end of construction, we will not be completing any new fiber miles until the end of the project, at which time we would promptly be at 100%. Instead, we are installing conduit and have installed approximately 40 miles as of September 30. | 1 | 0 | 80 | Jaguar Communications | N/A | N/A | 1 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | N/A | FALSE | N/A | We will be continuing to work on our construction efforts, pushing as long into the months of November and December as the weather permits. We anticipate receiving our first shipments of fiber cable in December, which will allow us, weather permitting to begin blowing fiber into our already installed conduit. We will continue blowing in fiber until the amount of snow becomes problematic in accessing handholes. We do not anticipate deploying or leasing any new network miles nor do we anticipate servicing any CAI's or increasing the number of signed agreements with broadband wholesalers or last mile providers during this quarter. | Carver, County of | Based on fiber availability, we have adjusted our project construction plan. Fiber is not scheduled to begin shipping until approximately the first week of December, 2011, which in Minnesota, coincides with the typical construction shutdown for the season due to the cold and snowy weather. Based on not having fiber to install at time of conduit construction during this quarter, we will instead come back after our conduit construction is completed and once fiber begins arriving, and will blow the fiber into the already installed conduit. This changes the timing in which various portions of our project were scheduled to have fiber installed but does not change our overall project light up time, which is still on schedule to meet the June of 2013 timeline. | Depending on maintaining the estimated shipping start date for our fiber order, we may not fully realize this expenditure until a later quarter, since the product is not billed until shipped. Also, our timeline anticipates a normal construction season, but if we have unseasonable weather, similar to what we have received this past winter and spring, both which have been record setting in regards to snow accumulation and then corresponding spring flooding, tied with record setting rainfall, it may impact our construction speed, which we would look to regain at the start of construction in spring of 2012. | TRUE
NT10BIX5570109 | 2011 | Q4 | Q4 - 2011 | The Carver County Open Fiber Initiative consists of approximately 89 miles of base ring and 33 miles of laterals. The base ring is the backbone of the fiber project and runs a loop of fiber strands in a relative circle throughout the entire county, connecting every city in the county. The base ring also directly feeds all the laterals connected to it. Over the past quarter our primary efforts have focused on the plowing (rural) and boring (urban) construction to install the two communications conduits and associated activities related to this type of construction, which includes jurisdictional and entity communications, field engineering and permitting. There continues to be an industry wide shortage of fiber which is delaying our remaining shipments that were ordered in the third quarter of 2011. During this quarter we have received roughly 20% of the fiber needed to complete the base ring construction. Our fiber distributor has given us a staggered timeline for receiving the remaining shipments, which are scheduled to be delivered up through April of 2012. With this constraint we have adjusted our construction plan and are initially installing the two communications conduits that will hold the fiber cable, and once we receive our remaining fiber, we will come back and blow the fiber into the conduit. With this adjustment, we will still meet our overall construction schedule and budget, but we will be completing different components at different times than were originally planned. There are a number of jurisdictions that the County is communicating with regarding the variety of permits needed for the project including city, railroad, DNR, MN DOT, pipeline and even the County itself. The County is working quickly but deliberately to submit and gain approval of all the permits needed for the project so that construction can continue uninterrupted. We are doing field engineering for each segment of fiber construction prior to beginning construction on that segment. This approach allows us to use current information from the field to more appropriately identify the construction path where the fiber conduits are being installed, as well as allowing us to place hand holes in the best locations to accommodate current and anticipated connections into the fiber ring. At the end of December the County initiated the building penetrations phase of the project, which performs the work needed to physically bring the communications conduit from outside to inside the various buildings that will be directly connected to the fiber. This work will be completed at each Anchor Institution and will continue throughout the winter, until either snow accumulation or frost make this construction inappropriate. The ARRA Funding, along with the Countyâ€™s 20% matching funds, provides one time capital dollars which we are using to help build the CCOFI project. Once the project is complete, there will be ongoing costs associated with the fiber optic network, such as maintenance, equipment replacements and basic administrative costs. CCOFI staff have taken a proactive approach to our project sustainability and within months after receiving notice that the County was selected as a grant recipient back in 2010, staff put together a rough draft pro forma for the project. Even though construction is still between 12-18 months from completion, CCOFI staff are already refining the pro forma and working to establish the structure needed to maintain a long term sustainable fiber network. As of December 31st we have expended approximately $2.9 million dollars of our overall project budget of $7.5 million, with the majority for construction costs of which we have completed approximately 88 miles as of December 31. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Our new network miles deployed is at 0, which is less than our originally stated 80. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. | N/A | N/A | N/A | Our number of miles of new fiber is at 0, which is less than our originally stated 80. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. | N/A | N/A | No variance from baseline | 1 | 0 | 80 | Jaguar Communications | N/A | N/A | 1 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | N/A | FALSE | N/A | The next quarter runs through the Minnesota winter months of January to March, so many if not all construction and building penetration efforts will be shuttered due to frost, cold and snow accumulation. Construction will resume next spring, which is typically around May 1st, but Minnesota has weather restrictions on many roads for heavy construction equipment due to the frost and melt, which are typically lifted by the State of MN in June. So we will be resuming building penetrations or other project components that do not require heavy construction equipment in May and remainder of construction activities requiring heavy construction equipment, in June or when the road restrictions are lifted. Also, we will be using the winter months to gather data and begin the drafting of our equipment bid so that it can be released in April. Weather dependent, we anticipate the ability to blow in fiber during this quarter, which will allow us to install roughly 80 of our 89 miles of base ring fiber. We do not anticipate installing any fiber to our CAI's during this winter quarter. We also do not anticipate any additional signed agreements with broadband wholesalers or last mile providers. | Carver, County of | Based on fiber availability, we have adjusted our project construction plan. Our remaining fiber is not scheduled to begin shipping until the end of January 2012, with deliveries arriving up through April 2012. Based on not having fiber to install at the time of conduit construction during this quarter, we will instead come back after our conduit construction is completed and once fiber begins arriving, will blow the fiber into the already installed conduit. This changes the timing in which various portions of our project were scheduled to have fiber installed but does not change our overall project light up time, which is still on schedule to meet the June 2013 timeline. | We do not consider it an issue, but if fiber is delayed beyond the January through April delivery schedule that we have been provided from our fiber distributor, we will be pushing out the purchase of equipment to a more appropriate time so that we will be purchasing and installing the most appropriately current equipment. Secondly, if we were to get an unseasonable wet spring/summer where we have flooding or other severe weather, our construction plan would be modified to accommodate. | TRUE
NT10BIX5570109 | 2012 | Q1 | Q1 - 2012 | During this past quarter we have completed approximately 92 miles of the overall 132 miles of construction consisting of approximately 83 miles of our overall 89 miles of base ring construction and 9 miles of our overall 33 miles of lateral construction. All of these miles noted are conduit miles and we will begin installing fiber in the second quarter. As of this past quarter, the pressure of the fiber availability issue has eased considerably as we have received approximately 95% of the fiber needed for our 89 mile base ring. We are still awaiting the shipments of our 33 miles of smaller count lateral fiber, which is slated for delivery in the first to mid part of the second quarter of 2012. As of this past quarter we have submitted and received approval for approximately 80% of the permits needed to complete the construction of the project. Based on changing how we were originally going to construct the project due to the fiber availability issue, we are waiting to submit for specific permits that have a limited timeframe in which we are allowed to complete the permitted work. For these permits, we are waiting until a further date so as to not have to renew the permits because they would expire prior to us having an opportunity to complete. There are three fiber distribution huts that are identified in the project. During this past quarter, the County finalized discussions on the needed permits for the huts at all locations and began initial drafting of the bid proposal for their construction. With the unseasonably warm weather, construction was able to continue with building penetrations for sites that do not currently have an existing open interduct to allow for the two communications conduits to be run into a respective facility. As of this past quarter, approximately 50% of all locations in the project are ready for fiber conduit installs. Over the past quarter, CCOFI staff have spent a considerable amount of time discussing and beginning the design of the overall network and splicing plan, which is the equivalent of adding intersections, turn lanes and bridges to a stretch of currently open highway. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Our new network miles deployed is at 0, which is less than our originally stated 80. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We have 92 miles of conduit installed of our overall project miles of 132 and we will begin blowing fiber into this conduit starting next quarter. | N/A | N/A | N/A | Our number of miles of new fiber is at 0, which is less than our originally stated 80. Due to fiber availability, the manner in which we are constructing different phases of the project has changed. We have 92 miles of conduit installed of our overall project miles of 132 and we will begin blowing fiber into this conduit starting next quarter. | N/A | N/A | No variance from baseline | 1 | 0 | 80 | Jaguar Communications | N/A | N/A | 1 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | N/A | FALSE | N/A | We will be continuing our building penetration conduit installs. We will also be working on completing our splicing plan so that we can draft and release our equipment bid. With fiber having arrived we will begin pulling fiber into facilities. We anticipate completing the conduit install and pulling of fiber into that conduit for the miles that makes up our base ring. We do not anticipate any additional signed agreements with broadband wholesalers or last mile providers in this quarter. We do not anticipate connecting any CAI's in this quarter. | Carver, County of | Based on fiber availability, we have adjusted our project construction plan. Our remaining fiber was delivered at the end of this quarter. Based on the unpredictable fiber shipments we received throughout the quarter, we did not install fiber at the time of conduit construction. Instead, we plan to come back after our conduit construction is completed and begin blowing fiber into the already installed conduit. This changes the timing in which various portions of our project were scheduled to have fiber installed but does not change our overall project light up time, which is still on schedule to meet the June 2013 timeline. | We do not consider it an issue, but with the delay in fiber shipments, we will be pushing out the purchase of equipment to a more appropriate time so that we will be purchasing and installing the most appropriately current equipment. Secondly, if we were to get an unseasonable wet spring/summer where we have flooding or other severe weather, our construction plan would be modified to accommodate. | TRUE
NT10BIX5570109 | 2012 | Q2 | Q2 - 2012 | The project consists of approximately 89 miles of dual conduit base ring construction and 33 miles of lateral construction. As of the end June we have completed construction of our 89 mile base ring including the pulling of all fiber through the installed conduit. We have also completed approximately 28 miles of the 33 miles of lateral construction including the pulling of fiber through the installed conduit. With the base ring complete, we have begun what is called optical time-domain reflectometer ( OTDR) testing. This testing validates the speeds, loss and integrity of the fiber that has been installed. We are currently doing OTDR testing on various sections of our ring and once fiber huts are constructed and operational, OTDR testing will be run on fiber throughout the complete 89 mile ring to validate the integrity of the fiber installed. OTDR testing was included in our construction budget so it does not have a specific line item to report for budgetary progress. As of the end of June we have received all quantities of fiber that we originally ordered. Based on our design build engineering we are finding that we will be short on some small quantities of small count lateral fiber. We are working to finalize the shortage numbers so that this fiber can be ordered so that as the final lateral construction is completed, we have fiber to install. Based on initial conversations with fiber vendors for the footages we need, it looks that availability will not be a prominent factor. There are a number of jurisdictions that the County is communicating with regarding the variety of permits needed for the project including city, railroad, DNR, MN DOT, township, pipeline and even the County itself. Over the past quarter we have completed approximately 95% of the permitting that is needed for the project with the remaining being readied for submission once timing is appropriate for the respective area of construction. There are three fiber distribution huts that are identified in the project. The huts are located in Cologne, Victoria and Mayer. During this past quarter, the County has been working on hut design specifications and communicating with qualified contractors for hut construction. We have separate crews that work on building penetrations and the internal work needed for each of our identified project locations. As of the end of June we have completed over 50% of the building penetrations for the project. Almost 1/3 of the identified locations are school facilities and the project waited until the early summer break to begin work on these penetrations to avoid student and classroom disruption as much as possible. Over the past quarter staff have completed the initial splicing design for the project, working to best utilize this new fiber infrastructure to the advantage of the entities participating as well as for future growth and expansion. We are currently reaching out to anchor entities to discuss and validate our splicing designs. During these conversations we are also discussing growing and expanding the current fiber infrastructure in hopes that it will spawn collaborations and opportunities amongst participating entities and others within the County and Region. As of June 30th we have expended approximately $5.33 million dollars of our overall project budget of $7.5 million, with the majority for construction costs. | 117 | 0 | 0 | 0 | 117 | 0 | 0 | 407 | No variance from baseline | N/A | N/A | N/A | No variance from baseline | N/A | N/A | Prior to the beginning of construction, we increased our handhole count. As of the end of the quarter, we have completed construction and pulling of fiber into 407 of these handholes. | 1 | 0 | 80 | Jaguar Communications | N/A | N/A | 1 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 12 | 0 | 12 | 0 | We have completed our base ring construction so our 12 base ring sites have fiber pulled into them. | No variance from baseline | We have completed our base ring construction so our 12 base ring sites have fiber pulled into them. | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | N/A | FALSE | N/A | We look to complete our network design and splicing plan, which will us to move forward with the procurement process for equipment. We look to begin installing equipment in the next quarter as well as looking to start the construction of the three fiber huts in our project. We look to complete construction and be close to completion of pulling into fiber to the remaining anchor entities. For this quarter we anticipate connecting up approximately 75% of our anchor entity sites, which is 64 CAI's. | Carver, County of | In our final work on our network design we identified a shortage of fiber to complete the project. We are currently identifying final footages needed and contacting fiber vendors for availability so that an order can be placed. We are also working on final splicing designs for the project with our anchor entities, which have yielded numerous conversations for potential collaborations and cost saving opportunities that staff are working to best incorporate into the current splicing design. | We have not yet drafted our equipment bid and based on conversations with equipment vendors, we do not anticipate any issues with receiving the equipment we order, as that is one of our last large purchase components of the project. Also, if we were to get an unseasonably early winter starting in the third quarter it would push some construction into late 1st quarter of 2013. | TRUE
NT10BIX5570109 | 2012 | Q3 | Q3 - 2012 | As of the end of September, we have completed a number of components for our 89 mile base ring and approximately 33 miles of laterals. We have completed installation of the dual communications conduits and the pulling of fiber into these conduits. We have completed work on any building penetrations that were needed to allow us to pull fiber into each of our identified anchor entities. We have completed work on installing termination and/or rack equipment at our anchor entities and we are currently working on scheduling for the splicing and terminations of the fiber in these locations. We have begun work on the three fiber distribution huts in our project. We have completed the pouring of the concrete slab floors and are working on the walls and roofs as well as preparing both the interiors and exteriors for the installation of the required mechanicals. We have completed all splicing required for the 89 mile base ring, except for splicing that is specific to the fiber huts. We have completed all the OTDR testing that we are capable of performing without the fiber huts being complete. We currently have two diverse paths identified in our project that allow us to reach the 511 interconnect building in downtown Minneapolis. We are currently working on the contracts needed to establish these two routes. We are working on finalizing the method and documentation for the acquisition of our electronics for the project. We are reviewing opportunities to purchase equipment through existing contracts, through a bid process or combination of both. As part of the preparation for migrating to an operational status once the project construction is complete, County Staff have been working with anchor entities to finalize the agreements with how each anchor entity desires to use the fiber network. As of September 30th we have expended approximately $6.13 million dollars of our overall project budget of $7.5 million, with the majority for construction costs. | 132 | 0 | 0 | 0 | 132 | 0 | 0 | 407 | No variance from baseline | N/A | N/A | N/A | No variance from baseline | N/A | N/A | Prior to the beginning of construction, we increased our handhole count. As of the end of the quarter, we have completed construction and pulling of fiber into 407 of these handholes. | 1 | 0 | 80 | Jaguar Communications | N/A | N/A | 1 | 0 | 0 | 0 | No variance from baseline | Our providers with signed agreements receiving improved access is at 0, which is less than our originally stated 2. This lower number was created by existing providers waiting for our network to complete and prove it's reliability before furthering conversations to utilize it. | No variance from baseline | No variance from baseline | 86 | 0 | 86 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | N/A | FALSE | N/A | We look to complete our equipment bid, and thus our network design with our equipment bid, since we are bidding a design build equipment proposal. Once the bid is issued and a vendor is chosen, we look to begin equipment installations in this quarter. We also look that the three fiber huts will be completed and all inside work completed inside of them so that network testing can begin. | Carver, County of | In planning for our equipment needs and the design to operate the network, we are proceeding with a design build approach in our equipment bids, which is deferring our equipment purchases and installs until the next quarter. | We are preparing to issue our equipment bid and based on conversations with equipment vendors, we do not anticipate any issues with receiving the equipment we order, or costs as that is one of our last large purchase components of the project. | TRUE
NT10BIX5570109 | 2012 | Q4 | Q4 - 2012 | As of the end of December, we have relatively completed the construction of our 89 mile base ring and approximately 33 miles of laterals. We have completed installation of the dual communications conduits and the pulling of fiber into these conduits as well as the associated splicing on the fiber installed. Over the past several months we have been working on finishing up building penetrations, which allow us to pull fiber into each of our identified anchor entities, as well as installing any needed termination and/or rack equipment and performing the associated interior splicing and termination work. As of the end of December, this work is approximately 85% complete. There are three fiber distribution huts in our project, located in Cologne, Mayer and Victoria, which regenerate the fiber optic signal through the 89 mile fiber network. As of the end of December, we have completed outside structural work for each hut with some cosmetic exterior work remaining. We are also in the final stages of finishing the interior mechanical work, which includes electrical, rack mounting, cooling, etc. We are tentatively planning for our huts to be completed in March 2013. With the base ring construction complete, as of the end of December, we have also completed all the OTDR testing that we are capable of performing without the fiber huts being complete. Once fiber huts are completed we will be able to fully test all base ring fiber for the full 89 mile base ring distance. We currently have two diverse paths identified in our project that allow us to reach the 511 building in downtown Minneapolis, which is the critical internet provider interconnection hub for the region. These connections to the 511 are what will provide internet to our fiber network as well as allow for non internet connectivity outside of our network. The two paths, with their diversity in routes to the 511, allow our project to have both redundancy in routes out of our network and also redundancy in the networks we travel once we are out of our own network, as our data travels to and from 511. This quarter we worked on negotiations and the contracts needed to establish these two routes, in preparation for our project going live. As of the end of December we have received responses and are in the review process for the equipment RFP for the electronics needed to operate the network that was issued in November. This is the equipment (switches, optics, etc) that will be used in our hub sites for interconnecting and distributing our fiber network, along with equipment that will be located at each anchor entities for connecting their internal networks into the fiber network. We look to begin installation of equipment in February 2013 and continuing through May. As of December 31st, we have expended approximately $6.25 million of our overall project budget of $7.5 million, with the majority for construction costs. The project is 80% funded from a Federal ARRA Grant and 20% from Carver County through the use of general fund resources. | 122 | 0 | 0 | 0 | 122 | 0 | 0 | 407 | No variance from baseline | N/A | N/A | N/A | No variance from baseline | N/A | N/A | Prior to the beginning of construction, we increased our handhole count. As of the end of the quarter, we have completed construction and pulling of fiber into 407 of these handholes. | 1 | 0 | 80 | Jaguar Communications | N/A | N/A | 1 | 0 | 0 | 0 | No variance from baseline | Our providers with signed agreements receiving improved access is at 0, which is less than our originally stated 2. This lower number was created by existing providers waiting for our network to complete and prove it's reliability before furthering conversations to utilize it. | No variance from baseline | No variance from baseline | 75 | 0 | 75 | 0 | When we submitted the grant, we noted data centers as separate locations that shared the same facilities. We have 11 cities, so our CAI's were overstated by 11 data centers. | No variance from baseline | When we submitted the grant, we noted data centers as separate locations that shared the same facilities. We have 11 cities, so our CAI's were overstated by 11 data centers. | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | N/A | FALSE | N/A | We will be ordering our equipment next quarter and installations will begin once shipments begin arriving. We also look to complete our three required fiber huts and finally we look to complete one of our two connections to the 511 building, which is our carrier hotel. We plan to have all our project identified CAI's connected to the fiber, all of our identified route miles completed and our initial service provider connected to the project during this quarter. | Carver, County of | None | No challenges are anticipated. | TRUE
NT10BIX5570109 | 2013 | Q1 | Q1 - 2013 | We have made great progress over the past quarter. We have divided the entities in our project into two groups, the first being the schools and libraries, which is our initial focus, and second being the cities, county, townships and other remaining locations. As of the end of the quarter, all entities have the ability to utilize the dark fiber that is installed between their facilities. With our emphasis on the schools and libraries, we continue to be on schedule to go live with these entities in mid May. We are also on schedule to go live to our second group of entities by the end of May so they can begin connecting and testing throughout the month of June. All construction of the 89 mile base ring and 33 miles of laterals that are identified in our ARRA project are complete. We are awaiting the spring thaw to complete a handful of what are identified as additional laterals to the project, which are additional locations that entities have expressed desire to connect to the network. As of the end of the quarter, the large quantity of fiber switches and associated electronics that allow entities to connect to the fiber network as well as operate the network itself, were bid, awarded, ordered, received and are currently being configured and deployed. We are currently roughly 50% complete with our electronics deployment for the entire project. With our emphasis on the schools and library entities, 100% of the electronics have been deployed at these locations. There are three fiber distribution huts in our project, located in Cologne, Mayer and Victoria, which regenerate the fiber optic signal through the 89 mile fiber network. We have completed exterior construction on our Mayer and Cologne huts and we are approximately 95% complete with the exterior construction of our Victoria hut. The interior work needed to make the huts operational is complete and we are in the final stages of finishing non essential installations on the backup generators, racking and cooling systems. We will be establishing two diverse connections that connect our network to the 511 building, which is our carrier hotel. Our initial connection, which is connected to our network in Chanhassen, is complete and operational. We are currently in negotiations to establish our second connection, which we look to have in place by the end of summer. For redundancy, we will be receiving internet service from two ISPâ€™s. The County has completed the needed connections to our ISP and we are in the final days of completing the needed cross connect at the 511 building, allowing us to connect with our second ISP. For a network to function it needs DNS service and IPâ€™s so that it can properly communicate. The County desires to provide carrier neutral IPâ€s to our entities. To accommodate this desire, the County has been working with ARIN, the world body that distributes IP addresses to the internet, to secure our own block of carrier neutral IP addresses. We are nearing completion of this process and look to have completed all the requirements and technical configurations by mid May. As of March 31st, we have expended approximately $6.7 million of our overall project budget of $7.5 million, with the majority for construction costs. The project is 80% funded from a Federal ARRA Grant and 20% from Carver County through the use of general fund resources. | 122 | 0 | 0 | 0 | 122 | 0 | 0 | 407 | No variance from baseline | N/A | N/A | N/A | No variance from baseline | N/A | N/A | Prior to the beginning of construction, we increased our handhole count. As of the end of the quarter, we have completed construction and pulling of fiber into 407 of these handholes. | 1 | 0 | 80 | Jaguar Communications | N/A | N/A | 1 | 0 | 0 | 0 | No variance from baseline | Our provider signed agreements receiving improved access is at 0, which is less than our originally stated 6. This lower number is based on existing providers being reluctant to sign up for services on a currently unfinished and unproven network. We anticipate this to change once the network is live and has proven it's operational reliability. | No variance from baseline | No variance from baseline | 75 | 0 | 75 | 0 | When we submitted the grant, we noted data centers as separate locations that shared the same facilities. We have 11 cities, so our CAI's were overstated by 11 data centers. | No variance from baseline | When we submitted the grant, we noted data centers as separate locations that shared the same facilities. We have 11 cities, so our CAI's were overstated by 11 data centers. | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | N/A | FALSE | N/A | We plan on completing deployment of our remaining equipment. We plan on completing the configurations so that internet services can be provided on our network. We plan on making available the network so that our project entities can begin live cut over and begin to actively use the network. We plan on making our final expenditures for equipment as well as paying out our construction retainage, thus depleting the grants funds for our project. We plan on initiating the project close out process with our FPO. | Carver, County of | None | We do not anticipate any challenges at this time and plan on completing the project within our required deadline. Also, we will be utilizing the program income as an additive, so we will be expending program income on ARRA approved items. | TRUE
NT10BIX5570109 | 2013 | Q2 | Q2 - 2013 | Over the past quarter we have completed a number of critical steps that allow us to make the fiber network available and usable to our various entities in the manner that best meets their existing IT infrastructure desires. As such, the project continues to be on track for completion by our July 31st timeline. As we finish with the initial construction and equipment and electronics installations we are also establishing operations as we prepare to migrate from a construction to an operational status. As of the end of the quarter, we have a number of public entities that are either actively using or currently preparing their systems to use either internet services and/or dark fiber between their facilities from this new fiber infrastructure. As of this quarter we have the majority of the school districts, several cities, Carver County IT including the Carver County Library System, Ridgeview Medical and Crown College, which are using the fiber network in various capacities. Construction of our 89 mile base ring and 33 miles of laterals that are identified in our ARRA project are complete. Over the past quarter we substantially completed the thousands of required field splicing and terminations needed to establish the various entity specific fiber networks within our overall fiber network. Over the past quarter we substantially completed the installation of the equipment and electronics at our critical distribution points and entity facilities throughout the project. Along with these installations we have also substantially completed the significant amount of configuration work needed to establish the various entity specific fiber networks within our overall network. Part of this configuration work also included completing the work to interconnect with our two internet service providers at the 511 building and pass the internet services we are receiving from them into our network via our first connection point into our network located in Chanhassen. This configuration work also included establishing our desired carrier neutral IPâ€™s with ARIN and setting up our DNS. There are three fiber distribution huts in our project located in Cologne, Mayer and Victoria, which regenerate the fiber optic signal through the 89 mile fiber network. All work has been completed at these huts except for a basic utility move at one location and final landscape work at all locations that has been held up due to the unseasonably late and wet spring we have been having. All work will be completed at the huts by our required timeline. We will be establishing two diverse connections that connect our network to the 511 building in downtown Minneapolis, which is the critical internet interconnect hub for the region. These diverse connections are what will provide internet to our fiber network. As of this quarter, our initial diverse connection, which is connected to our network in Chanhassen, is complete and operational. We are continuing negotiations to establish our second connection. For redundancy, we will be receiving internet services from two separate internet service providers (ISPâ€™s). The County has completed the agreements with and has established connections to both of these providers. As of this quarter, we have expended approximately $6.9 million of our overall project budget of $7.5 million, with the majority for construction costs. The project is 80% funded from a Federal ARRA Grant and 20% from Carver County through the use of general fund resources. | 122 | 0 | 0 | 0 | 122 | 0 | 0 | 407 | No variance from baseline | N/A | N/A | N/A | No variance from baseline | N/A | N/A | Prior to the beginning of construction, we increased our handhole count. As of the end of the quarter, we have completed construction and pulling of fiber into 407 of these handholes. | 1 | 0 | 80 | Jaguar Communications | N/A | N/A | 1 | 0 | 0 | 0 | No variance from baseline | Our provider signed agreements receiving improved access is at 0, which is less than our originally stated 6. This lower number is based on existing providers being reluctant to sign up for services on a currently unfinished and unproven network. We anticipate this to change once the network is live and has proven it's operational reliability. | No variance from baseline | No variance from baseline | 75 | 0 | 75 | 0 | When we submitted the grant, we noted data centers as separate locations that shared the same facilities. We have 11 cities, so our CAI's were overstated by 11 data centers. | No variance from baseline | When we submitted the grant, we noted data centers as separate locations that shared the same facilities. We have 11 cities, so our CAI's were overstated by 11 data centers. | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | 0 | 0 | 0 | 0 | 0 | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | No variance from baseline | N/A | FALSE | N/A | We will finish the final equipment deployments and will be making payments to all vendors for construction retaininge, equipment and electronics and deployment services, which will draw down all grant funds. We do not anticipate any issues and plan to close out by our required July 31st project completion timeline. | Carver, County of | We do not anticipate any issues or challenges and will be closing out our project by the required July 31st timeline. | We do not anticipate any challenges at this time and plan on completing the project within our required deadline. Also, we will be utilizing the program income as an additive, so we will be expending program income on ARRA approved items. | TRUE
NT10BIX5570109 | 2013 | Q3 | Q3 - 2013 | Over the past quarter we have completed all project components and have expended and drawn down all funding and completed our project. Our network has been transitioned from a project to an ongoing operational status. | 122 | 0 | 0 | 0 | 122 | 0 | 0 | 407 | No variance from baseline | N/A | N/A | N/A | No variance from baseline | N/A | N/A | Prior to the beginning of construction, we increased our handhole count. As of the end of the quarter, we have completed construction and pulling of fiber into 407 of these handholes. | 1 | 0 | 80 | Jaguar Communications | N/A | N/A | 1 | 0 | 0 | 0 | No variance from baseline | N/A | N/A | N/A | 75 | 0 | 75 | 0 | No variance from baseline | N/A | No variance from baseline | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | N/A | Carver, County of | Based on the delays incurred from the governmental shutdown are working to complete all project closeout reporting. | N/A | TRUE
NT10BIX5570111 | 2010 | Q4 | Q4 - 2010 | Northwest Open Access Network (NoaNet) completed their Baseline Project and Six Month Budget during the 4th Quarter of 2010. Work continued on the Environmental Assessment (EA) in preparation for submission and anticipated receipt of Finding of No Significant Impact (FONSI). Project planning meetings and dialogue was held with Sub Participants of the project relative to their roles and responsibilities. NoaNet has developed a significant amount of progress towards establishing agreements with Sub Participants during this quarter. Network Design continued integrating with our first round award and other key elements of the project design. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 38 | 1 | 20 | The 38 signed agreements referred to above are comprised of 37 pre-existing wholesale customers of Northwest Open Access Network with existing agreements pre-dating the Broadband Technology Opportunities Program award and one (1) new agreement in this quarter. These contracts have non-disclosure provisions that prohibit public release of their specific names without prior written consent. The list of pre-existing customers has been previously provided to NTIA under separate cover as "Privileged and Confidential" sales-marketing information. | There are currently no wholesale services provided as this project has only recently been awarded and our Environmental Assessment has yet to be submitted. Once the Finding of No Significant Impact (FONSI) has been received,construction has started, and customers receive service, the Network will be tested and this list will be updated and data will be provided. | Sub Recipients: Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-738-3116 Kitsap Public Utility District, 1431 Finn Hill Road, PO Box 1989, Poulsbo, WA 98370 360-779-7656 Negotiations are currently in process with other parties on their operating models with no final determination being made as of this time. Additional third party operators may be added as we continue this process. See Attached Network Drawings. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time in the project. | FALSE | N/A | Northwest Open Access Network anticipates submission of our Environmental Assessment and subsequent Finding of No Significant Impact (FONSI) in the next quarter (1st Quarter of 2011). Preliminary network equipment procurement will begin with plans to award in the following quarter. Network design will continue with some preliminary permitting being completed. | Northwest Open Access Network | Northwest Open Access Network (NoaNet) initially experienced a delay in accepting their award due to some overlap with a Sub Participantâ€™s BTOP award. Since being awarded, NoaNet has worked diligently on the Environmental Assessment (EA) in anticipation of an on time completion. Though recently the NoaNet EA team was presented with new and refined information that is important to include in the EA. Therefore NoaNet requested an extension to allow the required additional mapping and Section 106 cultural analysis to be completed. It may have been possible to â€œforceâ€ a draft EA by the SAC due date of Feb 1, 2011, yet NoaNet strongly believes this extension will allow for thorough quality assurance/quality control of the EA and will mitigate the risk of further iterations due to missing, incomplete or conflicting data being presented. As explained in the request for extension NoaNet does not expect the extension to delay the overall project and therefore would appreciate any assistance on the approval of the extension. | The only issue that may develop would be a delay in receipt of the Finding of No Significant Impact (FONSI). We do not expect this to be an issue, but any delays in receipt could push the project out and cause us to accelerate construction later in the year. | TRUE
NT10BIX5570111 | 2011 | Q1 | Q1 - 2011 | The first quarter of 2011 primarily focused on completion and submittal of the Draft Environmental Assessment and subsequent comments sent by Federal reviewers. Now awaiting comments to the second draft with comments addressed. Work continues with the Grants Office on finalizing the detailed budget and network design. Project planning meetings were held with the sub recipients to work through the Participation Agreement comments, coordination of project details, designs and internal easement. Right of Way planning continues to evolve as we work through the construction planning phase. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance. | N/A | N/A | N/A | No variance. | No variance. | N/A | No variance. | 39 | 1 | 20 | The 39 signed agreements referred to above are comprised of the 37 original or pre-existing wholesale customers of Northwest Open Access Network with existing agreements pre-dating the Broadband Technology Opportunities Program award and two (2) new agreements from the previous two quarters. These contracts have non-disclosure provisions that prohibit public release of their specific names without prior written consent. The list of pre-existing customers was previously provided to NTIA under separate cover as "Privileged and Confidential" sales/marketing information. | There are currently no broadband wholesale services being provided as this project is currently awaiting receipt of Finding of No Significant Impact (FONSI) on the Environmental Assessment. Once customers are receiving service, the list of wholesale service offerings and prices will be updated and provided. | Sub Recipients: Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-738-3116 Kitsap Public Utility District, 1431 Finn Hill Road, PO Box 1989, Poulsbo, WA 98370 360-779-7656 Negotiations with other third parties are in process with no final determination at this time. Additional third party operators will likely be added as the project progresses. | 0 | 0 | 0 | 0 | No variance. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No variance. | No variance. | N/A | No variance. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time in the project. | FALSE | N/A | The primary focus and concentration will be receiving Environmental approval by way of the Finding of No Significant Impact (FONSI) this next quarter. Efforts will also be placed on the initiation of equipment procurement and request for proposals on material and labor during the quarter. Working with the Sub Recipients will continue to evolve and reach toward finalizing agreements. Staking, design and Right of Way acquisition will all take place as we plan for aggressive permitting activity in the second half of this year. | Northwest Open Access Network | Currently we are waiting for Environmental approval prior to ground disturbing activities taking place. Any assistance in expediting the approval process would be greatly appreciated. | None are anticipated; however, unidentified challenges and issues are always a concern. We have implemented additional resources to expedite the project and insure it is completed on time. | TRUE
NT10BIX5570111 | 2011 | Q2 | Q2 - 2011 | Northwest Open Access Network continued to work on the Environmental Process in anticipation of receipt of Finding of No Significant Impact (FONSI). Work with the Bureau of Land Management and the US Forest Service in a collaborative effort to gain approval for building of our Network on or near these Federal lands. Additionally, work continues on budgeting, inclusive of Sub Recipient projects, to ultimately draft agreements and finalize time lines for field staking, permitting, contractor and other vendor selection processes. A significant effort has been spent collecting data and visiting wireless sites in preparation of the Federal Communications Commission (FCC) application and execution per the Programmatic Agreement between the National Telecommunications and Information Administration (NTIA) and the FCC. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No Variance. | NA | NA | NA | No Variance. | No Variance. | NA | No Variance. | 43 | 1 | 20 | The 43 signed agreements referred to above are comprised of the 37 original or pre-existing wholesale customers with Northwest Open Access Network with existing agreements pre-dating the Broadband Technology Opportunities Program award and six (6) new agreements from the previous four quarters. These contracts have non-disclosure provisions that prohibit public release of their specific names without prior written consent. The list of pre-existing customers was previously provided to National Telecommunications and Information Administration (NTIA) under separate cover as "Privileged and Confidential" sales and marketing information. | There are currently no broadband wholesale services being provided as this project is currently awaiting receipt of finding of No Significant Impact (FONSI) on the Environmental Assessment. Once customers are receiving service, the list of wholesale service offerings and prices will be updated and provided. | Sub Recipients: Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-738-3116 Kitsap Public Utility District, 1431 Finn Hill Road, PO Box 1989, Poulsbo, WA 98370 360-779-7656 Negotiations with other third party providers are in process with no final determination at this time. Additional third party operators will likely be added as the project progresses. | 0 | 0 | 0 | 0 | No Variance. | NA | NA | NA | 0 | 0 | 0 | 0 | The number included on the Baseline projection was an error, as no miles of fiber were expected to be deployed at this time in the project. | The number included on the Baseline projection was an error, as no miles of fiber were expected to be deployed at this time in the project. | NA | N/A | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | None at this time in the project. | FALSE | NA | Most importantly, we are anticipating receipt of Finding of No Significant Impact from the Environmental Assessment. This will lead the way for continued progress in all metrics across all phases of the Project. Staking, Permitting and Right of Way acquisition are all being coordinated in support of an accelerated construction schedule. | Northwest Open Access Network | NoaNet is actively working with the Program Officer to enable FONSI to be issued late July to early August. NoaNet is also awaiting approval of the adjusted In Kind Assets. | None are anticipated, however, unidentified challenges and issues are always a concern. Additional resources will be implemented when needed to insure successful completion of the Project as required by the Broadband Technology Opportunities Program. | TRUE
NT10BIX5570111 | 2011 | Q3 | Q3 - 2011 | Northwest Open Access Network has worked diligently to complete and respond to questions related to the Environmental process, ultimately in anticipation of receiving Finding of No Significant Impact (FONSI) shortly. Non ground disturbing activities and any allowable planning functions pertaining to construction bidding, staking, permitting, and right of way acquisition have been taking place in order to proceed once FONSI is received. Sub recipient involvement continues to evolve as work towards agreements and finalizing details are close. In Kind asset approval was received and most of it has been attributed toward the project this quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | With the longer than anticipated Environmental Process, this metric has not met the original Baseline Projections. With the necessary approvals in hand and construction contracts awarded, this metric will start to make up ground. An aggressive Baseline forecast will not allow us to meet this metric until the final year of the project. | N/A | N/A | N/A | See 'New Network Miles Deployed' metric above. | Wireless links have not yet been incorporated into the project as construction has not yet started. The wireless links will be brought online incrementally with substantial completion by quarter three of 2012. | N/A | Interconnection related to new construction has not been made available as construction of the project has not been initiated. Interconnection will be made available when the balance of Anchor Institutions are brought up. Interconnection will be an ongoing process as the project develops and connectivity to Anchor Institutions is accomplished. Completion of this milestone will be met upon the final connections to the Network. | 44 | 1 | 20 | The 44 signed agreements referred to above are comprised of the 37 original or pre-existing wholesale customers with Northwest Open Access Network with existing agreements pre-dating the Broadband Technology Opportunities Program award and seven (7) new agreements from the previous five quarters. These contracts and all future agreements as standard verbiage have non-disclosure provisions that prohibit public release of their specific names without prior written consent. The list of pre-existing customers was previously provided to the National Telecommunications and Information Administration (NTIA) under separate cover as "Privileged and Confidential" sales and marketing information. | There are currently no broadband wholesale services being provided as this project is currently awaiting receipt of Finding of No Significant Impact (FONSI) on the Environmental Assessment. Once customers are receiving service, the list of wholesale offerings and prices will be updated and provided. | Sub Recipients: Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-783-3116 Kitsap Public Utility District, 1431 Finn Hill Road, PO Box 1989, Poulsbo, WA 98370 360-779-7656 Sawnet, c/o Sawtooth Technologies, 50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Kalispel Tribe of Indians, 22 Camas Flat Road, Cusick, WA 99180-0096 509-445-1664 Negotiations with other third party providers are in process with no final determination at this time. Additional third party operators will likely be added as the project progresses. | 0 | 0 | 0 | 0 | With the absence of having received Environmental Approval and ultimately construction being started, signed agreements have not been received for new access. Agreements and new providers will be brought online as we progress with the build, anticipating meeting this metric in the first half of year three. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Initial projections in the Baseline were aggressive and did not take into account a longer than anticipated environmental process. Anchor institutions will be caught up to Baseline with an expedited construction schedule during the final two quarters of the project. | See narrative above. | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time in the project. | FALSE | N/A | NoaNet intends to work aggressively towards initiating construction related activities that allow the project to commence beyond the non ground disturbing activity. All other project activity will focus around the metrics below, with an emphasis on achieving the baseline projections over the next several quarters. All available resources will be utilized to insure the project is completed in a timely manner. Projected metrics for the end of this quarter are noted below: New network miles deployed: 0 New network miles leased: N/A Total CAI subscribers served (CAI's connected): 0 Number of signed agreements with broadband wholesalers or last mile providers: 44 | Northwest Open Access Network | NoaNet is awaiting Finding of No Significant Impact (FONSI) and any assistance NTIA can provide would be greatly appreciated. | Any anticipated challenges have been addressed as we approach the winter season and potential unfavorable weather for construction related activities. No technical assistance is required at this time, however always appreciated as it is needed. | TRUE
NT10BIX5570111 | 2011 | Q4 | Q4 - 2011 | Northwest Open Access Network received approval for their Environmental Assessment via Finding of No Significant Impact (FONSI) in December. Staking, permitting and Right of Way acquisition continues as we anticipate the compressed construction schedule in 2012. Routes with permitting completed will commence with construction in early spring as weather allows. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | With the longer than anticipated Environmental Process, this metric has not met the original Baseline Projections. With the necessary approvals in hand and construction contracts awarded, this metric will start to make up ground. An aggressive Baseline forecast will not allow us to meet this metric until Quarter 4 of 2012. | N/A | N/A | N/A | See 'New Network Miles Deployed' metric above. | Wireless links have not yet been incorporated into the project as construction has not yet started. The wireless links will be brought online incrementally with substantial completion by quarter three of 2012. | N/A | Interconnection related to new construction has not been made available as construction of the project has not been initiated. Interconnection will be made available when the balance of Anchor Institutions are brought up. Interconnection will be an ongoing process as the project develops and connectivity to Anchor Institutions is accomplished. Completion of this milestone will be met upon final connections to the Network in the first quarter of 2013. | 43 | 1 | 20 | The 43 signed agreements referred to above are comprised of the 37 original or pre-existing wholesale customers with Northwest Open Access Network with existing agreements pre-dating the Broadband Technology Opportunities Program award and six (6) new agreements from the previous six quarters. These contracts and all future agreements as standard verbiage have non-disclosure provisions that prohibit public release of their specific names without prior written consent. The list of pre-existing customers was previously provided to the National Telecommunications and Information Administration (NTIA) under separate cover as "Privileged and Confidential" sales and marketing information. | There are currently no broadband wholesale services being provided as this project is currently awaiting the start of construction. Once customers are receiving service, the list of wholesale offerings and prices will be updated and provided. | Sub Recipients: Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-783-3116 Kitsap Public Utility District, 1431 Finn Hill Road, PO Box 1989, Poulsbo, WA 98370 360-779-7656 Sawnet, c/o Sawtooth Technologies, 50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Kalispel Tribe of Indians, 22 Camas Flat Road, Cusick, WA 99180-0096 509-445-1664 Negotiations with other third party providers are in process with no final determination at this time. Additional third party operators will likely be added as the project progresses. | 0 | 0 | 0 | 0 | With having only recently received Environmental Approval and ultimately construction being started, signed agreements have not been received for new access. Agreements and new providers will be brought online as we progress with the build, anticipating meeting this metric in the first half of year three. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Community Anchor Institutions will be brought online in conjunction with the Network Build, as an extended Environmental Approval and permitting has created a lag in start of construction. Current Baseline projections are anticipating meeting this metric in Quarter 3 of year three of the project. Based on overall delays, this metric be prolonged out to the final year of the project with final CAI's being connected during the final phase of the project. | N/A | N/A | 10-Meg (38 Subscribers) 100-Meg (170 Subscribers) 1-Gig (75 Subscribers) 10-Gig (0 Subscribers) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time in the project life cycle. | FALSE | N/A | Activities centered around construction will be primary focus as we into 2012. Preparing for construction bids on select routes as well as continued efforts on securing permits and Rights of Way for needed areas will remain a priority. NoaNet intends to once again focus on all activities related to construction and necessary functions to insure the metrics below are met. All available resources will be utilized to insure the project is completed in a timely manner. Bid packets will be completed for sections of the project scheduled for construction early in 2012. Projected Metrics for end of this quarter are noted below: New Network Miles Deployed: 25 New Network Miles Leased: N/A Total CAI Subscribers Served (CAI's Connected): 0 Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers: 47 | Northwest Open Access Network | None at this time in the project, however if needed, assistance is always appreciated. | The budgeted amount of $21,573 for line item e. Other Architectural and Engineering fees in the budget for Northwest Open Access Award NT10BIX5570111, was the summation of NoaNet and several Sub Recipients Right of Way projected costs. In the past quarters, accounting transactions were charged incorrectly to this sub category. We will be making adjustments to resolve this issue and will be reflected in the next reporting period. | TRUE
NT10BIX5570111 | 2012 | Q1 | Q1 - 2012 | The first quarter of 2012 was consumed with field staking, construction drawing and permit drawing development to enable public procurement of construction contractors. Cultural field survey and associate reports are being coordinated once final staking is complete and NoaNet approves the 'Staked' route. Additionally, each route under a potential modification is analyzed to assure that no new or significant environmental issues are created through the route modifications to assure timely processing with the BTOP program's route modification process. The required SEPA notices have been processed for all but one route that had specific requirement, yet will be advertised in the first week of May to support final permitting release. A significant amount of budget/schedule analysis is being resourced on NoaNet and sub-recipient projects to assure under budget and on time completion of these projects. There is a revision being made in the Infrastructure Budget Execution Details below in response to a concern with the 'Other Architectural and Engineering Fees' category over expended. NoaNet researched the issue and discovered $357,447 that had been inappropriately 'coded' to this budget line item by our accounting group and reallocated to the appropriate category within the budget. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | With a longer than anticipated Environmental process, this metric has not met the original aggressive projections that were established during the initial phase of planning. We are anticipating meeting this metric in the last quarter of the final year of the project year, Q2 2013. | N/A | N/A | N/A | See 'New network miles deployed' metric above. | Wireless links have not yet been incorporated into the project as construction has not yet started. The wireless links will be brought online incrementally with substantial completion by quarter three of 2012. | N/A | Interconnection related to new construction has not been made available as construction on the project has not been initiated. Interconnection will be made available when the balance of Anchor Institutions are brought up. Interconnection will be an ongoing process as the project develops and connectivity to Anchor Institutions is accomplished. Completion of this milestone will be met upon final connections to the Network in the first quarter of 2013. | 45 | 1 | 20 | The 45 signed agreements referred to above are comprised of the 37 original or pre-existing wholesale customers with Northwest Open Access Network with existing agreements pre-dating the Broadband Technology Opportunities Program award and eight (8) new agreements from the previous seven quarters. these contracts and all future agreements as standard verbiage have non-disclosure provisions that prohibit public release of their specific names without prior written consent. The list of pre-existing customers was previously provided to the National Telecommunications and Information Administration (NTIA) under separate cover as "Privileged and Confidential" sales and marketing information. | There are currently no broadband services being provided as this project is currently awaiting the start of construction. Once customers are receiving service, a list of wholesale offerings and prices will be updated and provided. | Sub Recipients: Black Rock Cable, Inc., 1512 Fairview St., Bellingham, WA 98229 360-783-3116 Kitsap Public Utility District, 1431 Finn Hill Road, PO Box 1989, Poulsbo, WA 98370 360-779-7656 Sawnet, c/o Sawtooth Technologies, 50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Kalispel Tribe of Indians, 22 Camas Flat Road, Cusick, WA 99180-0096 509-445-1664 Negotiations with other third party providers are in process with no final determination at this time. Additional third party operators will likely be added as the project progresses. | 0 | 0 | 0 | 0 | With having only recently initiated bids for construction contracts, signed agreements have not been received for new access. Agreements and new providers will be brought online as we progress with the build, anticipating meeting this metric in the first half of year three. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Community Anchor Institutions will be brought online in conjunction with the Network Build, as an extended Environmental Approval and permitting has created a lag in start of construction. Current Baseline projections are anticipating meeting this metric in Quarter 3 of year three of the project. Based on overall delays, this metric may be prolonged out to the final year of the project with final CAI's being connected during the final phase of the project. | Same as above. | N/A | 10- Meg Subscribers-38, 100-Meg Subscribers-170, 1-Gig Subscribers-75, and 10-Gig Subscribers-0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time of the project. | FALSE | N/A | Activities centered on permitting, Right of Way acquisition, and eventual construction of routes will be the primary focus for the second quarter of 2012 and beyond. All available resources will be utilized to insure the project meets the timeframe allotted by the BTOP Grant guidelines. All tasks and activities will be directed at the metrics surrounding this report and be concentrating on attaining those guidelines below: Projected Metrics for end of this quarter are noted below: New Network Miles Deployed: 33 New Network Miles Leased: N/A Total CAI Subscribers Served: 20 Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers: 46 | Northwest Open Access Network | None at this time in the project, although if needed, assistance is always appreciated. | None at this time of the project. | TRUE
NT10BIX5570111 | 2012 | Q2 | Q2 - 2012 | The second quarter of 2012 was consumed with field staking, construction drawing and permit drawing development to enable public procurement of construction contractors. Cultural field survey and associate reports are being coordinated once final staking is complete and NoaNet approves the 'Staked' route. Additionally, each route under a potential modification is analyzed to assure that no new or significant environmental issues are created through the route modifications to assure timely processing with the BTOP program's route modification process. A significant amount of budget/schedule analysis is being resourced on NoaNet and sub-recipient projects to assure under budget and on time completion of these projects. NoaNet's NE-1 project has been a primary focus to accomplish a fully permitted route by the end of June, we were fortunate to acquire all WSDOT permits to construct by mid-June. RPF's for the NE-1 project were also resourced with bid opening at the end of June, NoaNet awarded the 'lump sum' responses received on the project and moved to a pre-construction meeting with WSDOT and the contractor on the last week of June. Two projects started construction with an 'expedited' construction of approximately 2 miles of duct on our Route NW-2 and fiber pulls in conduits on NW-3. | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | With a longer than anticipated Environmental process, this metric has not met the original aggressive projections that were established during the initial phase of planning. We are anticipating meeting this metric in the last quarter of the final year of the project year, Q2 2013. | N/A | N/A | N/A | See 'New network miles deployed' narrative above. | Wireless links have not yet been incorporated into the project as construction has not yet started. The wireless links will be brought online incrementally with substantial completion by quarter one of 2013. | N/A | Interconnection related to new construction has not been made available as construction on the project has not been initiated. Interconnection will be made available when the balance of Anchor Institutions are brought up. Interconnection will be an ongoing process as the project develops and connectivity to Anchor Institutions is accomplished. Completion of this milestone will be met upon final connections to the Network in the first quarter of 2013. | 48 | 1 | 20 | The 48 signed agreements referred to above are comprised of the 37 original or pre-existing wholesale customers with Northwest Open Access Network with existing agreements pre-dating the Broadband Technology Opportunities Program award and twelve(12) new agreements from the previous eight quarters. These contracts and all future agreements as standard verbiage have non-disclosure provisions that prohibit public release of their specific names without prior written consent. The list of pre-existing customers was previously provided to the National Telecommunications and Information Administration (NTIA) under separate cover as "Privileged and Confidential" sales and marketing information. | There are currently no broadband services being provided as this project is currently awaiting the start of construction. Once customers are receiving service, a list of wholesale offerings and prices will be updated and provided. | Sub Recipients: Black Rock Cable Inc., 1512 Fairview St., Bellingham, WA 98229 360-783-3116 Kitsap Public Utility District, 1431 Finn Hill Road, PO Box 1989, Poulsbo, WA 98370 360-779-7656 Sawnet, c/o Sawtooth Technologies, 50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Kalispel Tribe of Indians, 22 Camas Flat Road, Cusick, WA 99180-0096 509-445-1664 Negotiations with other third party providers are in process with no final determination at this time. Additional third party operators will likely be added as the project progresses. | 0 | 0 | 0 | 0 | With having only recently initiated construction, signed agreements have not been received for new access. Agreements and new providers will be brought online as we progress with the build, anticipating meeting this metric in the first half of year three. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Community Anchor Institutions will be brought online in conjunction with the Network Build, as an extended Environmental Approval and permitting has created a lag in start of construction. Current Baseline projections are anticipating meeting this metric in Quarter 3 of year three of the project. Based on overall delays, this metric may be prolonged out to the final year of the project with final CAI's being connected during the final phase of the project. | See 'Total Subscribers served' narrative above. | N/A | 10 Meg Subscribers-38, 100 Meg Subscribers-170, 1 Gig Subscribers-75, and 10 Gig Subscribers-0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time in the project. | FALSE | N/A | Activities will continue to be focused around the permitting phase of the project, while additional bid packet information will be made available as additional routes slated for construction are phased in to the schedule. Equipment procurement will continue to take place as additional routes are built and necessary electronics are needed for completion. Projected Metrics for end of quarter are noted below: New Network Miles Deployed- 80 New Network Miles Leased-N/A Total CAI Subscribers Served-2 Number of Signed Agreements with Wholesalers or Last Mile Providers-49 | Northwest Open Access Network | None at this time. | None at this time in the project. | TRUE
NT10BIX5570111 | 2012 | Q3 | Q3 - 2012 | Construction activity continued at a rapid pace as route staking, permitting, and right of way acquisition all continue towards completion. The third quarter of 2012 focus continued on activity around the construction of some routes and permitting, final design, route modification and bid preparation for routes scheduled to begin construction this year. Permitting and Right of Way acquisition are a major focus for the remaining routes as any necessary adjustments will need to be finalized prior to bidding. Weather permitting, construction is anticipated to continue throughout the winter season to insure on time completion as outlined in the BTOP award. Sub recipient monitoring and engagement by NoaNet continues as their projects continue in various stages of progress. Weekly project meetings are taking place involving all members of the Team to insure members are aligned and apprised of all necessary information for completion of the project on budget and in a timely matter. | 60 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | With a longer than anticipated Environmental process, this metric has not met the original aggressive projections that were established during the initial phase of planning. We are anticipating meeting this metric in the last quarter of the final year of the project year, Q2 2013. | N/A | N/A | N/A | See 'New network miles deployed' narrative above. | Wireless links have not yet been incorporated into the project as construction has not yet started. The wireless links will be brought online incrementally with substantial completion by quarter one of 2013. The contract for all four have been awarded and are currently in process with completion anticipated in January 2013. | N/A | Interconnection related to new construction has not been made available as construction on the project has not been initiated. Interconnection will be made available when the balance of Anchor Institutions are brought up. Interconnection will be an ongoing process as the project develops and connectivity to Anchor Institutions is accomplished. Completion of this milestone will be met upon final connections to the Network in the first quarter of 2013. | 49 | 1 | 20 | The 49 signed agreements referred to above are comprised of the 37 original or pre-existing wholesale customers with Northwest Open Access Network with existing agreements pre-dating the Broadband Technology Opportunities Program award and 12(twelve) new agreements from the previous nine quarters. These contracts and all future agreements as standard verbiage have non-disclosure provisions that prohibit public release of their specific names without prior written consent. The list of pre-existing customers was previously provided to the National Telecommunications and Information Administration (NTIA) under separate cover as "Privileged and Confidential" sales and marketing information. | There are currently no Broadband Services being provided as this project has only recently begun construction. Once customers are turned up and receiving service, a list of Wholesale offerings and prices will be updated and provided. | Sub Recipients: Black Rock Cable Inc., 1512 Fairview St., Bellingham, WA 98229 360-779-7656 Kitsap Public Utility District, 1431 Finn Hill Road, PO Box 1989, Poulsbo, WA 98370 360-779-7656 Sawnet, c/o Sawtooth Technologies, 50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Kalispel Tribe of Indians, 22 Camas Flat Road, Cusick, WA 99180-0096 509-445-1664 Negotiations with other third party providers are in process with no final determination at this time. Additional third party operators will likely be added as the project progresses. | 0 | 0 | 0 | 0 | With having only recently initiated construction, signed agreements have not been received for new access. Agreements and new providers will be brought online as we progress with the build, anticipating meeting this metric in the first half of year three. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Community Anchor Institutions will be brought online in conjunction with the Network Build, as an extended Environmental Approval and permitting has created a lag in start of construction. Current Baseline projections are anticipating meeting this metric in Quarter 3 of year three of the project. Based on overall delays, this metric may be prolonged out to the final year of the project with final CAI's being connected during the final phase of the project. | See 'Total Subscribers served' narrative above. | N/A | 10 Meg Subscribers-38, 100 Meg Subscribers-170, 1 Gig Subscribers-75, and 10 Gig Subscribers-0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time of the project. | FALSE | N/A | Activities will continue to be focused around the construction phase of the project, while additional bid packet information will be made available as additional routes slated for construction are phased in to the schedule. Equipment procurement will continue to take place as additional routes are built and necessary electronics are needed for completion. Projected Metrics for end of quarter are noted below: New Network Miles to be Deployed- 170 New Network Miles Leased-N/A Total CAI Subscribers Served-5 Number of Signed Agreements with Wholesalers or Last Mile Providers-50 | Northwest Open Access Network | None at this time. | None at this time. | TRUE
NT10BIX5570111 | 2012 | Q4 | Q4 - 2012 | In the fourth quarter of 2012, focus continued on activity around the construction of the NE-1, NW-1A, NC-3 routes, and construction of the Microwave sites on NE-3. Activity also continued on permitting, final design, route modification and bid preparation for routes scheduled to begin construction in 2013. Permitting and Right of Way acquisition are a major focus for the remaining routes as any necessary adjustments will need to be finalized prior to bidding. Sub recipient monitoring and engagement by NoaNet continues as their projects continue in various stages of progress. Weekly project meetings are taking place involving all members of the Team to insure members are aligned and apprised of all necessary information for completion of the project on budget and in a timely manner. | 153 | 0 | 0 | 0 | 153 | 0 | 0 | 0 | With an elongated Environmental process, this metric has not met the original aggressive projections that were established during the initial phase of planning. This metric will meet projections during the final quarter of the project. Construction is being completed on the NE-1, NC-3, and NW-2 routes of the project. | N/A | N/A | N/A | See 'New network miles deployed' narrative above. | Wireless links are in the process of being built and incorporated into the project. | N/A | Interconnection related to new construction has not been made available as construction of routes has only recently started. Interconnection will be made available when the balance of Anchor Institutions are brought up. Interconnection will be an ongoing process as the project develops and connectivity to Anchor Institutions is accomplished. Completion of this metric will be met upon final connections to the Network in the second quarter of 2013. | 49 | 1 | 20 | The 49 signed agreements referred to above are comprised of the 37 original or pre-existing wholesale customers with Northwest Open Access with existing agreements pre-dating the Broadband Technology Opportunities Program award and 12 (twelve) new agreements from the previous ten quarters. These contracts and all future agreements as standard verbiage have non-disclosure provisions that prohibit public release of their specific names without prior written consent. The list of pre-existing customers was previously provided to National Telecommunications and Information Administration (NTIA) under separate cover as "Privileged and Confidential" sales and marketing information. | Northwest Open Access Network provides wholesale services to telecommunications companies, Internet providers, application service providers and cable companies throughout the State of Washington. Ethernet, Wave, IP and TDM Transport Services are among the services provided and available to interested parties. | Sub Recipients: Black Rock Cable Inc., 1512 Fairview St., Bellingham, WA 98229 360-738-3116 Kitsap Public Utility District, 1431 Finn Hill Road, PO Box 1989, Poulsbo, WA 98370 360-779-7656 Sawnet, c/o Sawtooth Technologies, 50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Kalispel Tribe of Indians, 22 Camas Flat Road, Cusick, WA 99180-0096 509-445-1664 Jefferson County Public Utility District #1, 230 Chimacum Rd., Port Hadlock, WA 360-385-5800 Stevens County Public Utility District #1, 3955 3rd Street, Loon Lake, WA 509-233-2534 Negotiations with other third party providers are in process with no final determination at this time. | 12 | 37 | 0 | 4 | Exceeding Baseline. | Exceeding Baseline. | N/A | 8-10 Meg, 25-100 Meg, 9-1 Gig, and 7-10 Gig | 9 | 9 | 0 | 9 | Community Anchor Institutions are being brought online in conjunction with the Network Build, as an extended Environmental Approval and permitting has created a lag in start of construction. Current Baseline projections are anticipating meeting this metric in Quarter 3 of 2013. Based on overall delays, this metric may be prolonged out to the final year of the project with final CAI's being connected during the final phase of the project. | See 'Total Subscribers served' narrative above. | N/A | 10 Meg Subscribers-9, 100 Meg Subscribers-0, 1 Gig Subscribers-0, and 10 Gig Subscribers-0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time of the project. | FALSE | N/A | Once again, construction of the Network is the primary focus going into the first and second quarters of 2013. In unison with construction activities, remaining routes will need preliminary work completed in preparation for bidding. Sub Participant projects will continue at different phases with the Network Build being the primary focus. Projected Metrics for end of quarter are noted below: New Network Miles to be Deployed- 193 New Network Miles Leased-N/A Total CAI Subscribers Served-14 Number of Signed Agreements with Wholesalers or Last Mile Providers-50 | Northwest Open Access Network | None at this time. | None at this time. | TRUE
NT10BIX5570111 | 2013 | Q1 | Q1 - 2013 | The first quarter of 2013, focus continued on activity around the completion or near completion of construction of the NE-1, Microwave Site on NE-3, and NW-1A. Preparation in regards to all necessary approvals to begin construction on NE-2, NE-2K, NE-1S, SC-6 and NW-2 took place with anticipation of starting construction in April 2013. Additional routes, SC-5, NW-3 and SC-2A, are nearing completion on pre-construction activities and are slated to begin construction in April and May 2013. Sub recipient monitoring and engagement by NoaNet continues as their projects continue in various stages of progress. Weekly project meetings are taking place involving all members of the Team to insure members are aligned and apprised of all necessary information for completion of the project on budget and in a timely and compliant manner. Metrics Achieved this Quarter: New Network Miles Deployed-19 New Network Miles Leased-N/A Total CAI Subscribers Served-25 Number of Signed Agreements with Wholesalers or Last Mile Proveders-0 | 172 | 0 | 0 | 0 | 172 | 2 | 0 | 18 | With an elongated Environmental process, this metric has not met the original aggressive projections that were established during the initial phase of planning. This metric will meet projections during the final quarter of the project. Construction is being completed on the NE-1 and NC-3 routes of the project with additional routes in various stages of production. | N/A | N/A | N/A | See 'New network miles deployed' | Wireless links on NE-3 and NW-1A routes are substantially complete at the end of this quarter. | N/A | Interconnection related to new construction has not been made available as construction of select routes are only recently nearing completion. Interconnection will be made available when the balance of Anchor Institutions are brought up. Interconnection will be an ongoing process as the project develops and connectivity to Anchor Institutions is accomplished. Completion of this metric will be met upon final connections to the Network in the third quarter of 2013. | 49 | 1 | 20 | The forty nine (49) signed agreements referred to above are comprised of the 37 original or pre-existing wholesale customers wtih Northwest Open Access with existing agreements pre-dating the Broadband Technologies Opportunity Program award and 12 (twelve) new agreements from the previous eleven quarters. These contracts and all future agreements as standard verbiage have non-disclosure provisions that prohibit public release of their specific names without prior written consent. The list of pre-existing customers was previously provided to National Telecommunications and Information Administration (NTIA) under separate cover as "Privileged and Confidential" sales and marketing information. | Northwest Open Access Network provides wholesale services to telecommunications companies, internet providers, application service providers and cable companies throughout the state of Washington. Ethernet, Wave, IP, and TDM Transport Services are among the services provided and available to interested parties. | Sub Recipients: Black Rock Cable Inc., 1512 Fairview St., Bellingham, WA 98229 360-738-3116 Kitsap Public Utility District, 1431 Finn Hill Road, PO Box 1989, Poulsbo, WA 98370 360-779-7656 Sawnet,c/o Sawtooth Technologies,50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Kalispel Tribe of Indians, 22 Camas Flat Road, Cusick, WA 99180-0096 509-445-1664 Jefferson County Public Utility District #1, 230 Chimacum Rd., Port Hadlock, WA 98339 360-385-5800 Stevens County Public Utility District #1, 3955 3rd Street, Loon Lake, WA 99148 509-233-2534 Negotiations with other third party providers may develop with no final determination made at this time. | 12 | 37 | 0 | 4 | Exceeding Baseline | Exceeding Baseline | N/A | 8-10 Meg, 25-100 Meg, 9-1 Gig, and 7-10 Gig | 34 | 33 | 1 | 4 | Community Anchor Institutions are being brought online in conjunction with the Network Build, as an extended Environmental Approval and permitting has created a lag in start of construction. Current Baseline projections are anticipating meeting this metric in Quarter 3 of 2013. Based on overall delays, this metric will be prolonged out to the final quarter of the project with final CAI's being connected during the final phase of the project. | See 'Total Subscribers Served' narrative above. | N/A | 34-10 Meg, 0-100 Meg, 0-1 Gig, and 0-10 Gig - This metric was previously listed as 9 which was the number of CAI's connected instead of the number of Speed Tiers available. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this stage of the project. | FALSE | N/A | Construction activity is anticipated to continue strong into this quarter with additional routes slated to begin construction, and others nearing completion. Permitting and rights of way acquisition will be substantially completed as equipment deployment and testing will occur in unison with the construction of routes. Projected Metrics for end of Quarter as noted below:(Cumulative) New Network Miles to be Deployed-428 Total New Network Miles Leased-N/A Total CAI Subscribers Served- 97 Number of Signed Agreements with Wholesale Providers or Last Mile Providers- 50 | Northwest Open Access Network | The challenges that NoaNet faced during Q1 2013 was completing and commencing construction due to weather conditions and restrictions. Q1 is a winter quarter and it is extremely difficult to construct fiber due to hazard conditions. Construction of fiber backbone and laterals require heavy road travel by large equipment on unsafe road conditions. Most permits restrict travel by large equipment on roads due to the potential road damage. In parallel with weather conditions, NoaNet and sub-recipients had permitting challenges that protracted the ability to retain construction contractors to commence construction. | Due to the delays in project start and challenges in Q1 2013 NoaNet and sub participants, yet most all BTOP II routes are now in construction and are vigorously building fiber backbone and laterals. However, due to the constricted program timeline it will be difficult to complete fiber construction, equipment installs and CAI connections within the Program timeline ending on July 31st, 2013. | TRUE
NT10BIX5570111 | 2013 | Q2 | Q2 - 2013 | The second quarter of 2013 focus is starting and substantially completing construction on most routes and connections to Community Anchor Institutions. For those routes that have not started construction they have completed procurement of construction contractors to begin work by the first of Q3 2013 and contracted completion by end of July, one quarter before the extended and revised end date.NoaNet submitted a route modification to the program for a small three mile change in NE-1 and is working closely with NTIA to gain approval and we expect no further route modifications. Project meetings are being held in a collaborative environment in which all team members involved in the planning, project management and oversight keep abreast of the project status. Sub recipient monitoring continues for those projects or portions of routes left to build or still in process. Weekly project meetings and sub-recipient meetings are being held to assure compliance, and monitor project budget and scope. Metrics Achieved this past Quarter: Miles Deployed-149 New Network Miles Leased-N/A CAI's Connected-16 Broadband Wholesale or Last Mile Providers-1 | 321 | 0 | 0 | 0 | 321 | 2 | 0 | 34 | With an elongated environmental process and re-budgeting prior to project start, this metric has not met the original aggressive projections that were established during the initial phase of planning. This metric will meet projections during the final quarter of the project. Construction is complete on the NE-1,NE-2, NE-3 and NC-3 routes of the project with additional routes in various stages of construction. | N/A | N/A | N/A | See 'New Network Miles Deployed' above. | Wireless links have been completed. | N/A | Interconnection related to new construction has not been made available as construction of select routes are only recently nearing completion. Interconnection will be made available when the balance of Anchor Institutions are brought up. Interconnection will be an ongoing process as the project develops and connectivity to Anchor Institutions is accomplished. Completion of this metric will be met upon final connections to the Network in the third quarter of 2013. | 50 | 0 | 20 | The fifty (50) signed agreements referred to above are comprised of the 37 original or pre-existing wholesale customers with Northwest Open Access with existing agreements pre-dating the Broadband Technologies Opportunity Program award and 13 (thirteen) new agreements from the previous twelve quarters. These contracts and all future agreements as standard verbiage have non-disclosure provisions that prohibit public release of their specific names without prior written consent. The list of pre-existing customers was previously provided to National Telecommunications and Information Administration (NTIA) under separate cover as "Privileged and Confidential" sales and marketing information. | Northwest Open Access Network provides wholesale services to telecommunications companies, internet providers, application service providers and cable companies throughout the state of Washington. Ethernet, Wave, IP, and TDM Transport Services are among the services provided and available to interested parties. | Sub Recipients: Black Rock Cable Inc., 1512 Fairview St., Bellingham, WA 98229 360-738-3116 Kitsap Public Utility District, 1431 Finn Hill Road, PO Box 1989, Poulsbo, WA 98370 360-779-7656 Sawnet,c/o Sawtooth Technologies,50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Kalispel Tribe of Indians, 22 Camas Flat Road, Cusick, WA 99180-0096 509-445-1664 Jefferson County Public Utility District #1, 230 Chimacum Rd., Port Hadlock, WA 98339 360-385-5800 Stevens County Public Utility District #1, 3955 3rd Street, Loon Lake, WA 99148 509-233-2534 Negotiations with other third party providers may develop with no final determination made at this time. | 13 | 37 | 0 | 4 | Exceeding Baseline. | Exceeding Baseline. | N/A | 9-10 Meg, 25-100 Meg, 9-1 Gig, and 7-10 Gig. | 50 | 49 | 1 | 4 | Community Anchor Institutions are being brought online in conjunction with the Network Build, as an extended Environmental Approval and permitting has created a lag in start of construction. Current Baseline projections are anticipating meeting this metric in Quarter 3 of 2013. Based on overall delays, this metric will be prolonged out to the final quarter of the project with final CAI's being connected during the final phase of the project. | See 'Total Subscribers Served' narrative above. | N/A | 45-10 Meg, 5-100 Meg, 0-1 Gig, and 0-10 Gig | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Construction is slated to wrap up in the third quarter of 2013 with additional anchor institutions being connected. Remaining equipment will be installed and tested as the Network build continues into this quarter. Closeout activities will continue as previously constructed routes are already in process and newly completed routes will commence. All Sub Recipient projects will be completed as well, with those routes already in the final stages. Metrics Achieved Next Quarter(Projected): Miles Deployed-163 New Network Miles Leased-N/A CAI's Connected-140 Broadband Wholesale or Last Mile Providers-1 | Northwest Open Access Network | Construction is moving along well with CAI's being connected. We anticipate challenges in completing all CAI connections in the prescribed timeframe even with the No Cost Extension in place. | Due to delays in project start and challenges in 2013 with NoaNet and sub participants, now most all BTOP 2 routes are in construction and are vigorously building fiber backbones and laterals. With the approval of the No Cost Extension received, additional CAI's will be connected and scheduled for construction. Challenges may be in getting all listed and planned CAI's connected prior to the end of September. | TRUE
NT10BIX5570111 | 2013 | Q3 | Q3 - 2013 | This past quarter was consumed with final construction activity and completing all required work prior to the award end date of September 30th. In addition, planning and work towards closeout activities took place with Sub Recipients. Metrics Achieved this past Quarter: Miles Deployed-150 New Network Miles Leased-N/A CAI's Connected-98 Broadband Wholesale or Last Mile Providers-0 See attachment regarding project narrative. | 471 | 0 | 0 | 0 | 471 | 2 | 0 | 40 | This is the final mileage metric for the project. This metric, as a result of route revisions and route segments not being constructed per previous requests, as well as Sub Recipient projects not being completed as originally planned, account for a vast majority of miles shortfall in this metric. | N/A | N/A | N/A | This is the final mileage metric for the project. See above. | All wireless links were completed for the project. | N/A | This is the final interconnection point metric for the project. | 50 | 0 | 20 | The fifty (50) signed agreements referred to above are comprised of the 37 original or pre-existing wholesale customers with Northwest Open Access with existing agreements pre-dating the Broadband Technologies Opportunity Program award and 13 (thirteen) new agreements from the previous twelve quarters. These contracts and all future agreements as standard verbiage have non-disclosure provisions that prohibit public release of their specific names without prior written consent. The list of pre-existing customers was previously provided to National Telecommunications and Information Administration (NTIA) under separate cover as "Privileged and Confidential" sales and marketing information. | Northwest Open Access Network provides wholesale services to telecommunications companies, internet providers, application service providers and cable companies throughout the state of Washington. Ethernet, Wave, IP, and TDM Transport Services are among the services provided and available to interested parties. | Sub Recipients: Black Rock Cable Inc., 1512 Fairview St., Bellingham, WA 98229 360-738-3116 Kitsap Public Utility District, 1431 Finn Hill Road, PO Box 1989, Poulsbo, WA 98370 360-779-7656 Sawnet,c/o Sawtooth Technologies,50 SE Cascade Ave., Stevenson, WA 98648 509-427-4865 Kalispel Tribe of Indians, 22 Camas Flat Road, Cusick, WA 99180-0096 509-445-1664 Jefferson County Public Utility District #1, 230 Chimacum Rd., Port Hadlock, WA 98339 360-385-5800 Stevens County Public Utility District #1, 3955 3rd Street, Loon Lake, WA 99148 509-233-2534 Public Utility District #1 of Benton County, 2721 West 10th Ave., Kennewick, WA 99336 509-582-2175 City of Port Angeles, 321 East 5th Street, PO Box 1150, Port Angeles, WA 98362 360-457-0411 | 13 | 37 | 0 | 4 | Exceeding Baseline. | Exceeding Baseline. | N/A | 9-10 Meg, 25-100 Meg, 9-1 Gig, and 7-10 Gig. | 151 | 150 | 1 | 4 | This metric fell short of baseline as change in scope and connections to CAI's originally planned were not completed due to rights of entry and service order delays. The variance of CAI's was trued up with this final report to be at 151 per an email from Chantel to NTIA on 12/20/2013. | This metric fell short of baseline as change in scope and connections to CAI's originally planned were not completed due to right s of entry and service order delays. | This metric fell short of baseline as change in scope and connections to CAI's originally planned were not completed due to right s of entry and service order delays. | 146-10 Meg, 5-100 Meg, 0-1 Gig, and 0-10 Gig. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Closeout activities will consume the next quarter with final reports, legal documents and filings, and other requirements being completed for submission. | Northwest Open Access Network | Community Anchor Institution connections were a challenge as it was difficult to obtain rights of entry or service orders for all of the targeted facilities. | With closeout activities being the only remaining tasks, we are confident the team will complete the project in a timely manner. | TRUE
NT10BIX5570112 | 2010 | Q4 | Q4 - 2010 | During 4th quarter 2010, NebraskaLink hired an Environmental Consultant to complete our EA survey. NebraskaLink also issued an RFP for Engineering / Network Design; reviewed all (5) vendor responses and awarded a contract for Network Engineering / Network Design. NebraskaLink signed agreements with ILEC's we will be leasing fiber from. | 0 | 809 | 0 | 0 | 809 | 0 | 0 | 13 | N/A | N/A | N/A | N/A | Leased fiber | N/A | N/A | N/A | 3 | 7 | 8 | Four U Technology Consolidated Telecom Nebraska Central Telephone Company These agreements were signed by both parties during the 4th quarter. | This schedule represents pricing for NebraskaLink member companies. Pricing is based on purchases at the indicated standard quantities and a two year service contract. There are no non-recurring charges or port charges for member companies. 50 Mbs $45.00/Mbs/Month 100 Mbs $40.00/Mbs/Month | N/A | 3 | 0 | 0 | 6 | Service was provided to these providers during 4th quarter. | N/A | N/A | 50 Mbps - 1 100 Mbps - 2 250 Mbps - 0 500 Mbps - 0 1000 Mbps - 0 10 Gpbs - 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | During the next quarter, NebraskaLink will be completing the environmental assessment and submitting to the grant agency and receiving FONSI. NebraskaLink will be working closely with the Engineering Consultant on Network Design and Contractor RFP's. | Nebraskalink, LLC | NebraskaLink is open to any advice that the BTOP team can offer on technical issues, reporting issues, performance, etc. We appreciate receiving emails, communications, etc on any changes / deadlines / training events, etc in regards to our project and award. | N/A | TRUE
NT10BIX5570112 | 2011 | Q1 | Q1 - 2011 | NebraskaLink has submitted their draft Environmental Assessment and are working on documentaton for completion of the final version for submission. NebraskaLink is working closely with our Engineering Consultant to stake (mapping only) Phase 1 of our project while waiting on award of our FONSI, and have assisted our consultant with construction RFP's and bid selection for our first rural and town projects. | 0 | 809 | 0 | 0 | 809 | 0 | 0 | 13 | We are on target with our baseline plan for this quarter in regards to deploying new network miles. | We are on target with our baseline plan for this quarter in regards to new network miles leased. | N/A | N/A | We are on target with our baseline plan for this quarter in regards to the number of new aerial or underground miles of fiber. | N/A | N/A | We are on target with our baseline plan for this quarter in regards to the number of new /or upgraded interconnection points. | 4 | 8 | 8 | Four U Technology - 4th qtr 2010 Consolidated Telecom - 4th qtr 2010 Nebraska Central Telephone Company - 4th qtr 2010 Hamilton Telecom - 1st qtr 2011 | This schedule represents pricing for NebraskaLink member companies. Pricing is based on purchases at the indicated standard quantities and a two year service contract. There are no non-recurring charges or port charges for member companies. 50 Mbs $45.00/Mbs/Month 100 Mbs $45.00/Mbs/Month | N/A | 4 | 0 | 0 | 7 | We are on target with our baseline plan in regards to the number of broadband wholesalers or last mile providers that we have signed agreements with for new access. | N/A | N/A | 50 Mbps - 1 100 Mbps - 2 150 Mbps - 1 250 Mbps 500 Mbps 1000 Mbps 10 Gpbs | 0 | 0 | 0 | 0 | We are on target with our baseline plan in regards to the nubmer of Community Anchor Institutions that we are currently servicing. | We are on target with our baseline plan in regards to the nubmer of Community Anchor Institutions that we are currently servicing. | N/A | We are not currently providing services to any Community Anchor Institutions. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | NebraskaLink is looking forward to the approval of their Environmental Assessment and the award of their FONSI. NebraskaLink is working with the NTIA and the Nebraska SHPO office for approval through the Advisory Council on a Programmatic Agreement. NebraskaLink will work closely with our Engineering Consultant on further network design and contractor RFP's / bids for continuing phases of our project. We are looking forward to breaking ground on phase 1 of our project. | Nebraskalink, LLC | The delays in our project milestones are a result of the timeframe in working through approval of our Environmental Assessment. NebrsakaLink is working closely with the NTIA and the Nebraska SHPO offices to complete and resolve all issues necessary to be awarded their FONSI. | The only challenge we anticipate in the next quarter is the delay in receiving our FONSI in order to get into full swing on our project: ground breaking, ordering equipment and securing land for hut and cabinet locations. We are hoping to have our FONSI by mid quarter in order to catch up to our project milestones. | TRUE
NT10BIX5570112 | 2011 | Q2 | Q2 - 2011 | NebraskaLink was awarded their FONSI during this quarter, allowing us to begin construction during the last three weeks of the quarter. NebraskaLink continues to work closely with our Engineering Consultant to finalize all mapping for our project. | 0 | 809 | 0 | 0 | 809 | 0 | 0 | 15 | We are behind on our anticipated new network miles deployed due to the delay in receiving our FONSI and the delay in delivery of our fiber cable. Our Contractor has been plowing and laying conduit - upon the receipt of our fiber that is starting to come in, we will be able to catch up on this milestone by blowing the fiber into the conduit that has been laid in the ground. | We are on target with our baseline plan for this quarter in regards to new network miles leased. | N/A | N/A | We are behind on our anticipated miles of new fiber deployed due to the delay in receiving our FONSI and weather delays once construction began. | N/A | N/A | NebraskaLink is currently on target with our baseline plan for this quarter in regards to the number of interconnection points. | 9 | 8 | 8 | Four U Technology Consolidated Telecom Nebraska Central Telephone Company Hamilton Telecom Northeast Nebraska Telephone Company Great Plains Communications American Broadband Windstream Frontier | Schedule represents pricing for NebraskaLink member companies. Pricing based on purchases at the indicated standard quantities and a two year service contract. There are non recurring charges or port charges for member companies. 50 Mbs $45.00/Mbs/Month 100 Mbs $45.00/Mbs/Month | N/A | 9 | 0 | 0 | 9 | NebraskaLink is ahead of projection from our baseline plan on our signed agreements with Broadband Wholesalers and last mile providers. | N/A | N/A | 10 Mbps - 1 20 Mbps - 1 50 Mbps 100 Mbps - 3 150 Mbps - 1 200 Mbps - 1 250 Mbps 500 Mbps - 1 1000 Mbps 10 Gpbs - 1 | 5 | 5 | 0 | 3 | We are behind on the number of CAI's from our baseline plan due to the delay in our construction start. | We are behind on the number of CAI's from our baseline plan due to the delay in our construction start. | N/A | 5 Mbps - 2 10 Mbps - 1 20 Mbps - 2 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | NebraskaLink plans to complete plowing / boring of an additional 90 miles of rural construction for ring 1 / phase 1 of our project, as well as roughly 6 miles of lateral town construction. | Nebraskalink, LLC | The delay in our project milestones were a result of the extended time period to receive the award of our FONSI. Dince the FONSI was awarded, we have experienced a significant delay in obtaining fiber for the first phase of our project due to the availability from the effects of the earthquake in Japan. Once construction began to lay conduit to house our fiber when delivered, our contractor was halted and requested to sandbag cities in our build areas due to river flooding in multiple areas of Nebraska. | Other than the possible delay for receiving ordered fiber, the only other anticipated challenges in the next quarter will be continued weather issues. Areas of Nebraska have been affected by flooding due to river overflows. | TRUE
NT10BIX5570112 | 2011 | Q3 | Q3 - 2011 | NebraskaLink began placing fiber in the ground at the beginning of the quarter and had simultaneous projects running for construction phases. NebraskaLink was able to complete the total build for one of our towns in our project plan, North Platte, during the later part of the quarter. | 89 | 1003 | 0 | 0 | 1092 | 0 | 0 | 27 | NebraskaLink is behind our target for miles deployed due to the delay in receiving our FONSI and the delay in receiving fiber from the manufacturer as scheduled. We did have 99 miles of conduit in the ground waiting for fiber to be blown in. | NebraskaLink is on target with our baseline plan for this quarter. | N/A | N/A | NebraskaLink is behind our target for miles deployed due to the delay in receiving our FONSI and the delay in receiving fiber from the manufacturer as scheduled. | N/A | N/A | NebraskaLink is ahead of schedule for new interconnection points. | 12 | 5 | 8 | Four U Technology Consolidated Telecom Nebraska Central Telephone Company Hamilton Telecommunications Northeast Nebraska Telephone Company Great Plains Communications American Broadband Windstream Frontier Clarks Telephone Company Three RIvers Telephone Company K&M Telephone Company | Currently NebraskaLink offers the following wholesale services: Direct Internet Access (DIA), Ethernet Transport, and Private Line/ TDM services. These are priced on an individual case basis, based on interconnection ability, local loop availability and distance for the circuit. | N/A | 12 | 0 | 0 | 10 | NebraskaLink is ahead of projection from our baseline plan on our signed agreements with Broadband Wholesalers and last mile providers. | N/A | N/A | 10 Mbps -2 20 Mbps - 2 50 Mbps - 1 100 Mbps - 3 150 Mbps - 1 200 Mbps - 1 250 Mbps - 500 Mbps - 1 1000 Mbps - 10 Gpbs - 1 | 26 | 26 | 0 | 12 | NebraskaLink is ahead of our project baseline for this quarter. | NebraskaLink is ahead of our project baseline for this quarter. | N/A | 5 Mbps -2 10 Mbps -6 20 Mbps -3 30 Mbps -3 50 Mbps - 100 Mbps - 2 150 Mbps - 200 Mbps - 250 Mbps - 500 Mbps - 1 1000 Mbps - 10 Gpbs - | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | During the next quarter, NebraskaLink expects to complete their first of three fiber optic rings of our project. NebraskaLink will comlete their builds in the cities of Kearney, O'Neill and Valentine and bury approximately 50 miles of fiber build in the south western area of the state of Nebraska. We are expecting to lease an additional 12 miles of fiber and deploy an additonal 90 miles of fiber - weather permitting. We anticipate the addition of at least 9 more CAI's on our routes. We are currently working on adding 4 signed agreements with last mile provider or broadband wholesalers. | Nebraskalink, LLC | The challenges that NebraskaLink faced during this past quarter were due to weather conditions and river flooding in our project construction areas. Another issue was the delay in receiving our previously ordered fiber due to availability from the manufacturers, after the effects of the earthquake last quarter. | NebraskaLink does not anticipate any challenges during the next quarter other than possible weather related issues with the onset of winter. | TRUE
NT10BIX5570112 | 2011 | Q4 | Q4 - 2011 | NebraskaLink has continued to build out our grant project through the 4th quarter of 2011. In the third quarter we had completed our builds to CAIâ€™s in the city of North Platte. In Q4, we completed a middle-mile build of 93.5 miles stretching from Gibbon to Brady. This section included 3 hut locations as well. After turning up this section the NebraskaLink ring 1 is now complete. This is an important milestone for NebraskaLink as this new ring is now the largest redundant fiber optic ring in Nebraska. Also in Q4 we completed a middle-mile build of 20 miles from North Platte to Sutherland. Other projects that are ongoing in Q4 include fiber laterals to CAIâ€™s in the towns of Oâ€™Neill, Valentine and Kearney as well as middle-mile builds from Imperial to Wauneta and Wauneta to Trenton. These projects will all be complete in Q1 of 2012. | 192 | 1415 | 0 | 0 | 1607 | 0 | 0 | 33 | NebraskaLink is slightly behind on this milestone. We are working closely with our Construction Contractor to align this with our baseline project plan for next quarter. | NebraskaLink is on target with our baseline for this quarter. | N/A | N/A | NebraskaLink is ahead of schedule on this milestone. | N/A | N/A | NebraskaLink is ahead of schedule for new interconnections points. | 15 | 4 | 8 | Four U Technology Consolidated Telecom Nebraska Central Telephone Company Hamilton Telecommunications Northeast Nebraska Telephone Company Great Plains Communications American Broadband Windstream Frontier Clarks Telephone Company Three Rivers Telephone Company K&M Telephone Company Hershey Telephone AT&T SDN Communications | Currently NebraskaLink offers the following wholesale services: Direct Internet Access (DIA), Ethernet Transport, and Private Line/TDM services. These are priced on an individual case basis, based on interconnection ability, local loop availability and distance for the circuit. | N/A | 15 | 0 | 0 | 10 | NebraskaLink is ahead of projection from our baseline plan on our signed agreements with Broadband Wholesales and last mile providers. | N/A | N/A | 10 Mbps: 3 20 Mbps: 2 50 Mbps: 1 100 Mbps: 4 150 Mbps: 1 200 Mbps: 1 250 Mbps: 500 Mbps: 1 1000 Mbps: 10 Gpbs: 1 DS3: 1 | 48 | 48 | 0 | 12 | NebraskaLink is ahead of our project baseline for this quarter. | NebraskaLink is ahead of our project baseline for this quarter. | N/A | 5 Mbps: 2 10 Mbps: 11 20 Mbps: 3 30 Mbps: 3 50 Mbps: 100 Mbps: 4 150 Mbps: 200 Mbps: 250 Mbps: 500 Mbps: 1 1000 Mbps: 10 Gpbs: NebraskaLink does not currently supply service to all CAI's - some have laterals built to their sites. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Heading into Q1 of 2012, NebraskaLink has 5 projects in process that will be complete before the end of the quarter. Those include the middle mile builds from Trenton to Wauneta (32 miles) and Wauneta to Imperial (19 miles). Along these routes we will be interconnecting with one new last mile provider. NebraskaLink will also be completing 3 city lateral builds, which include many CAIâ€™s. Valentine is a 4.8 mile build that will connect 14 CAIâ€™s. Oâ€™Neill is a 5.2 mile build that will connect 10 or more CAIâ€™s. Kearney is a 7.7 mile build that will connect 13 CAIâ€™s. In addition to these fiber builds, NebraskaLink will also be extending our network through leasing fiber and adding network nodes. NebraskaLink plans to build an additional 70 network miles, lease an additional 15-20 miles of network and connect / pass an additional 20+ CAI's. We will also sign agreements with at least an additional two broadband wholesalers or last mile providers. | Nebraskalink, LLC | The late spring/summer flooding in much of our project construction areas resulted in delays in NebraskaLink meeting their desired project milestones. | The only possible challenges facing NebraskaLink for the upcoming quarter would be weather during the winter season and if our fiber and /or pipe deliveries would be delayed not any reason. | TRUE
NT10BIX5570112 | 2012 | Q1 | Q1 - 2012 | NebraskaLink has continued to build out our grant project through the 1st quarter of 2012. NebraskaLink has completed 4 projects during the first quarter of 2012. Those include the middle mile builds from Trenton to Wauneta (32 miles) and Wauneta to Imperial (19) miles. NebraskaLink also completed 2 city lateral builds - Valentine which was a 4.8 mile build and O'Neill which was a 5.2 mile build. | 264 | 1415 | 0 | 0 | 1679 | 0 | 0 | 37 | NebraskaLink is close to project plan on this milestone. The winter season slightly delayed our ability to lay fiber. | NebraskaLInk is on target with our baseline for this milestone. | N/A | N/A | NebraskaLink is ahead of target with this project milestone. | N/A | N/A | NebraskaLink is ahead of target with this project milestone. | 21 | 4 | 8 | Four U Technology Consolidated Telecom Nebraska Central Telephone Company Hamilton Telecommunications Northeast Nebraska Telephone Company Great Plains Communications American Broadband Windstream Frontier Clarks Telephone Company Three Rivers Telephone Company K&M Telephone Company Hershey Telephone AT&T SDN Communicaitons Level 3 Benkelman Telephone Arapahoe Telephone Cox Business Allo Pinpoint | Currently NebraskaLink offers the following wholesale services: Direct Internet Access (DIA), Ethernet Transport and Private Line/ TDM Services. These are priced on an individual basis, based on interconnection ability, local loop availability and distance for the circuit. | N/A | 21 | 0 | 0 | 10 | NebraskaLink is ahead of projection from our baseline pan on our signed agreements with Broadband Wholesales and last mile providers. | N/A | N/A | 10 Mbps: 5 20 Mbps: 2 50 Mbps: 1 100 Mbps: 4 150 Mbps: 1 200 Mbps: 1 250 Mbps: 500 Mbps: 2 1000 Mbps: 10 Gbps: 3 DS3: 2 | 37 | 37 | 0 | 13 | NebraskaLink is currently providing service to 3 CAI's listed in their application, plus have passed an additional 34 CAI's listed in our application. NebraskaLink is currently behind the project baseline on this milestone. Many CAI's listed in our application are currently under contract with existing carriers - some (34) have allowed us to build laterals to their sites for potential future business. | NebraskaLink is currently behind the project baseline on this milestone. | N/A | 5 Mbps: 10 Mbps: 20 Mbps: 1 30 Mbps: 50 Mbps: 60 Mbps: 1 100 Mbps: 1 150 Mbps: 200 Mbps: 250 Mbps: 500 Mbps: 1000 Mbps: 10 Gpbs: NebraskaLink does not currently supply service to all CAI's - some have laterals built to their sites. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | In early Q2, 2012, NebraskaLink will complete the fiber build-out in Kearney which is a 7.7 mile build that will connect potentially 13 CAI's. We will also begin construction on our 240 mile middle-mile route from Sutherland to Sidney to Chadron. This project will be ongoing through Q2 and Q3. In addition to these fiber builds, NebraskaLink will also be extending our network through leasing fiber and adding network nodes. NebraskaLink plans to deploy an estimated 75 additional miles during 2nd quarter, connect an additional 4 CAI's and execute agreements with 3 additional broadband wholesaler/last mile providers. | Nebraskalink, LLC | Our late construction start due to spring/summer flooding in our project area delayed the start of our initial construction. This quarter our only delay was the inability to bore fiber during the winter season. | The only possible challenges facing NebraskaLink for the upcoming quarter (spring / start of summer season), would be weather related and if we experience any delays in receipt of our fiber and conduit deliveries. | TRUE
NT10BIX5570112 | 2012 | Q2 | Q2 - 2012 | In Q2, 2012, NebraskaLink completed the fiber build-out in Kearney which was a 7.7 mile build that connect s10 CAIâ€™s. We have also begun the construction on our 240 mile middle-mile network from Sutherland to Sidney to Chadron. This project will be ongoing through Q3 and Q4. At the end of Q2, NebraskaLink had 60% of the construction complete and 30% of the splicing complete on the 240 mile network expansion. As part of this construction we also added new interconnects to service providers along the construction path. With our focus being on the middle-mile during Q2, we did not add any new CAIâ€™s to our completed list. We did however turn up service to 7 more of our existing CAIâ€™s. | 380 | 1415 | 0 | 0 | 380 | 0 | 0 | 50 | NebraskaLink is ahead of our project plan on this milestone due to the favorable winter/ spring conditions for construction. | NebraskaLink is on target with this milestone. | N/A | N/A | NebraskaLink is ahead of our project plan on this milestone. | N/A | N/A | NebraskaLink is ahead of target with this project milestone. | 22 | 3 | 12 | Four U Technology Consolidated Telecom Nebraska Central Telephone Company Hamilton Telecommunications Northeast Nebraska Telephone Company Great Plains Communications American Broadband Windstream Frontier Clarks Telephone Company Three Rivers Telephone Company K&M Telephone Company Hershey Telephone AT&T SDN Communications Level 3 Benkelman Telephone Arapahoe Telephone Cox Business Allo Pinpoint Glenwood Telecommunications | NebraskaLink currently offers the following wholesale services: Direct Internet Access (DIA), Ethernet Transport and Private Line/ TDM Services. These are priced on an individual basis, based on interconnection ability, local loop availability and distance for the circuit. | N/A | 22 | 0 | 0 | 10 | NebraskaLink is ahead of our target baseline plan for signed agreements with Broadband Wholesalers and last mile providers. | N/A | N/A | 10 Mbps: 5 20 Mbps: 2 50 Mbps: 2 100 Mbps: 4 150 Mbps: 1 200 Mbps: 1 250 Mbps : 500 Mbps: 2 1000 Mbps 10 Gbps: 3 DS3: 2 | 37 | 37 | 0 | 15 | NebraskaLink is currently providing service to 10 CAI's listed in their application, plus have built laterals to an additional 27 CAI's listed in our application. NebraskaLink is currently behind the project baseline on this milestone. Many CAI's listed in our application are currently under contract with existing carriers - some have allowed us to build laterals to their sites for potential future business. | Laterals built to sites. | N/A | 5 Mbps: 10 Mbps: 20 Mbps: 3 30 Mbps: 50 Mbps: 60 Mbps: 1 75 Mbps: 1 100 Mbps: 4 150 Mbps: 200 Mbps: 250 Mbps: 300 Mbps: 1 500 Mbps: 1000 Mbps: 10 Gbps: NebraskaLink does not currently supply service to all CAI's - some have laterals built to their sites. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | In Q3, 2012, NebraskaLink expects to bring our 240 mile middle-mile network project from Sutherland to Sidney to Chadron up to 90% of completion. We will begin turn-up of our network equipment on these newly constructed spans as well and be able to turn up interconnects with service providers along this path. We will also begin our town lateral project in Sidney, Nebraska. Sidney has 11 planned CAIâ€™s. Lastly, with the completion of our middle-mile project from Sutherland to Paxton, we will be able to turn up our Southwest Nebraska ring. This will be the first fiber ring in that area of the State and will allow our interconnected service providers and CAIâ€™s to have access to fully protected paths from locations in Southwest Nebraska to locations on the East side of the state. NebraskaLink expects to have a total of 420 miles deployed by end of quarter, connect to an additional 2 Broadband Wholesaler/ last mile providers and connect one additional CAI during the quarter. | Nebraskalink, LLC | NebraskaLink has a very productive quarter due to the mild winter/ spring in our area. We were allowed to work non stop with our construction crews to catch up on our project in many aspects. | Currently NebraskaLink does not anticipate any delays for the upcoming quarter other than possible weather related issues and if we experience any delays in receipt of our fiber or conduit deliveries. No delays are anticipated at this time. | TRUE
NT10BIX5570112 | 2012 | Q3 | Q3 - 2012 | In Q3, 2012, NebraskaLink was able to bring our 240 mile middle-mile network project from Sutherland to Sidney to Chadron up to 90% of completion. We began to turn -up our network equipment on these newly constructed spans turned up interconnects with service providers along the path. We also began our town lateral project in Sidney, Nebraska. Sidney has 11 planned CAIâ€™s. Lastly, with the completion of our middle-mile project from Sutherland to Paxton, we were able to turn up our Southwest Nebraska ring. This is the first fiber ring in that area of the State and allows our interconnected service providers and CAIâ€™s to have access to fully protected paths from locations in Southwest Nebraska to locations on the East side of the state. | 420 | 1415 | 0 | 0 | 420 | 0 | 0 | 57 | NebraskaLink is ahead of our project plan for this milestone. | NebraskaLink is on target with this milestone. | N/A | N/A | NebraskaLink is ahead of our project plan for this milestone. | N/A | N/A | NebraskaLink is ahead of our project plan for this milestone. | 22 | 2 | 12 | Four U Technology Consolidated Telecom Nebraska Central Telephone Company Hamilton Telecommunications Northeast Nebraska Telephone Company Great Plains Communications American Broadband Windstream Frontier Clarks Telephone Company Three Rivers Telephone Company K&M Telephone Company Hershey Telephone AT&T SDN Communications Level 3 Benkelman Telephone Arapahoe Telephone Cox Business Allo Pinpoint Glenwood Telecommunications | NebraskaLink currently offers the following wholesale services: Direct Internet Access (DIA), Ethernet Transport and Private Line/ TDM Services. These are priced on an individual basis, based on interconnection ability, local loop availability and distance for the circuit. | N/A | 22 | 0 | 0 | 10 | NebraskaLink is ahead of our target baseline plan for signed agreements with Broadband Wholesales or last mile providers. | N/A | N/A | 10 Mbps: 5 20 Mbps: 2 50 Mbps: 2 100 Mbps: 4 150 Mbps: 1 200 Mbps: 1 250 Mbps : 500 Mbps: 2 1000 Mbps 10 Gbps: 3 DS3: 2 | 37 | 37 | 0 | 15 | NebraskaLink is currently providing service to 10 CAI's listed in their application, plus have built laterals to an additional 27 CAI's listed in our application. NebraskaLink is currently behind the project baseline on this milestone. Many CAI's listed in our application are currently under contract with existing carriers - some have allowed us to build laterals to their sites for potential future business. No additional CAI's were added this quarter due to focus on our longhaul project. | Laterals built to sites. | N/A | 5 Mbps: 10 Mbps: 20 Mbps: 3 30 Mbps: 50 Mbps: 60 Mbps: 1 75 Mbps: 1 100 Mbps: 4 150 Mbps: 200 Mbps: 250 Mbps: 300 Mbps: 1 500 Mbps: 1000 Mbps: 10 Gbps: NebraskaLink does not currently supply service to all CAI's - some have laterals built to their sites. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | In Q4, 2012, NebraskaLink will complete our 240 mile middle-mile network project from Sutherland to Sidney to Chadron. Upon completion we will also complete the turn-up of our network equipment and connect 2 more service providers to our network. All circuits on this new Northwest Nebraska Ring will be rebuilt as protected, which will provide better service and redundancy to businesses and residences in Western Nebraska. In Q4, 2012, we will also finish our town lateral project in Sidney, Nebraska. Sidney has 11 planned CAIâ€™s. Lastly, in Q4, 2012 we will begin the final planning and project bids for the last projects on our BTOP project list. NebraskaLink plans to deploy an additional 30 miles in the 4th quarter, connect and/or build laterals to 11 CAI's in Sidney and sign an additional five agreements with broadband wholesaler/last mile providers. | Nebraskalink, LLC | NebraskaLink had a very productive quarter. The only delays we experienced were when our construction crews were tasked with fighting wild fires close to our project areas. At one point, these fires were less than a mile from our project. | Currently the only challenge that may impact our project during the upcoming quarter would be the possible winter weather. We anticipate continuing with our construction for as long as the weather permits. | TRUE
NT10BIX5570112 | 2012 | Q4 | Q4 - 2012 | In Q4, 2012, NebraskaLink completed our 240 mile middle-mile network project from Sutherland to Sidney to Chadron. This allowed us to connect to two more service providers in that area. All circuits on this new Northwest Nebraska Ring are now rebuilt as protected, which provides better service and redundancy to businesses and residences in Western Nebraska. In Q4, 2012, we also finished our town lateral project in Sidney, Nebraska. Sidney has 11 CAIâ€™s. Lastly, in Q4, 2012 we began the final planning and project bids for the last projects on our BTOP project list. | 435 | 1427 | 0 | 0 | 435 | 0 | 0 | 62 | NebraskaLink is ahead of our project plan for this milestone. | NebraskaLink is on target with this milestone. | N/A | N/A | NebraskaLink is ahead of our project plan for this milestone. | N/A | N/A | NebraskaLink is ahead of our project plan for this milestone. | 24 | 2 | 12 | Four U Technology Consolidated Telecom Nebraska Central Telephone Company Hamilton Telecommunications Northeast Nebraska Telephone Company Great Plains Communications American Broadband Windstream Frontier Clarks Telephone Company Three Rivers Telephone Company K&M Telephone Company Hershey Telephone AT&T SDN Communications Level 3 Benkelman Telephone Arapahoe Telephone Cox Business Allo Pinpoint Glenwood Telecommunications Unite Private Networks USA Communications | NebraskaLink currently offers the following wholesale services: Direct Internet Access (DIA), Ethernet Transport and Private Line/ TDM Services. These are priced on an individual basis, based on interconnection ability, local loop availability and distance for the circuit. | N/A | 24 | 0 | 0 | 10 | NebraskaLink is ahead of our target baseline plan for signed agreements with Broadband Wholesales or last mile providers. | N/A | N/A | 10 Mbps: 5 20 Mbps: 2 50 Mbps: 2 100 Mbps: 4 150 Mbps: 1 200 Mbps: 1 250 Mbps : 500 Mbps: 3 1000 Mbps 1 10 Gbps: 3 DS3: 2 | 48 | 48 | 0 | 15 | NebraskaLink is currently providing service to 10 CAI's listed in their application, plus have built laterals to an additional 38 CAI's listed in our application. NebraskaLink is currently behind the project baseline on this milestone. Many CAI's listed in our application are currently under contract with existing carriers - some have allowed us to build laterals to their sites for potential future business. | Laterals built to sites | N/A | 5 Mbps: 10 Mbps: 20 Mbps: 3 30 Mbps: 50 Mbps: 60 Mbps: 1 75 Mbps: 1 100 Mbps: 4 150 Mbps: 200 Mbps: 250 Mbps: 300 Mbps: 1 500 Mbps: 1000 Mbps: 10 Gbps: NebraskaLink does not currently supply service to all CAI's - some have laterals built to their sites. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | In Q1, 2013, NebraskaLink will be planning / staking and bidding our final projects for the BTOP Grant. Due to Nebraska weather we will not likely have any build activities during this quarter. We will use the first quarter to get everything ready for the Q2 fiber builds. If our AAR's for changes/additions are approved, NebraskaLink expects to begin connections to an additional 31 CAI's, deploy an additional 25 miles of fiber in project towns and sign an additional two agreements with broadband and last mile providers. | Nebraskalink, LLC | NebraskaLink had a good quarter with our construction - weather was great for our crews. We are slightly behind on some milestones waiting a reply on Award Action Requests submitted to made modifications to some CAI's in our project towns as well as a requested addition to our route. | The only thing NebraskaLink is waiting on for this quarter is a response to our award action request so that we can begin construction on the requested change. Thus far, being the winter season, we have had favorable conditions to continue our builds. | TRUE
NT10BIX5570112 | 2013 | Q1 | Q1 - 2013 | In Q1, 2013, NebraskaLink planned and staked and our final projects for the BTOP Grant. Due to Nebraska weather we did not have any build activities during this quarter. We used the first quarter for planning out Q2 activities. | 435 | 1427 | 0 | 0 | 435 | 0 | 0 | 67 | NebraskaLink is behind on this milestone due to the winter season and waiting approval (since received) for pending CAI swaps. | NebraskaLink is on target with this milestone. | N/A | N/A | NebraskaLink is behind on this milestone due to the winter season and waiting approval (since received) for pending CAI swaps. | N/A | N/A | NebraskaLink is ahead of our project plan for this milestone | 24 | 1 | 12 | Four U Technology Consolidated Telecom Nebraska Central Telephone Company Hamilton Telecommunications Northeast Nebraska Telephone Company Great Plains Communications American Broadband Windstream Frontier Clarks Telephone Company Three Rivers Telephone Company K&M Telephone Company Hershey Telephone AT&T SDN Communications Level 3 Benkelman Telephone Arapahoe Telephone Cox Business Allo Pinpoint Glenwood Telecommunications Unite Private Networks USA Communications | NebraskaLink currently offers the following wholesale services: Direct Internet Access (DIA), Ethernet Transport and Private Line/ TDM Services. These are priced on an individual basis, based on interconnection ability, local loop availability and distance for the circuit. | N/A | 24 | 0 | 0 | 10 | NebraskaLink is ahead of our target baseline for signed agreements with Broadband Wholesales or last mile providers. | N/A | N/A | 10 Mbps: 5 20 Mbps: 2 50 Mbps: 2 100 Mbps: 4 150 Mbps: 1 200 Mbps: 1 250 Mbps : 500 Mbps: 3 1000 Mbps 1 10 Gbps: 3 DS3: 2 | 52 | 52 | 0 | 15 | NebraskaLink is currently providing service to 10 CAI's listed in their application, plus have built laterals to an additional 42 CAI's listed in our application. NebraskaLink is currently behind the project baseline on this milestone. Many CAI's listed in our application are currently under contract with existing carriers - some have allowed us to build laterals to their sites for potential future business. | Laterals built to sites | N/A | 5 Mbps: 10 Mbps: 20 Mbps: 3 30 Mbps: 50 Mbps: 60 Mbps: 1 75 Mbps: 1 100 Mbps: 4 150 Mbps: 200 Mbps: 250 Mbps: 300 Mbps: 1 500 Mbps: 1000 Mbps: 10 Gbps: NebraskaLink does not currently supply service to all CAI's - some have laterals built to their sites. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | In Q2, 2013, NebraskaLink will start and complete our Grand Island town project. Grand Island has 13 original CAIâ€™s and 11 new CAIâ€™s that were part of our project amendment. Grand Island work should be complete by 7/1/2013. We will also be building an additional 11 CAIâ€™s in North Platte. This project should also be completed by 7/1/2013. Lastly, we will be building an additional 9 CAIâ€™s in Kearney. This should be complete by 6/1/2013. Once these last three projects are finished, we will have completed our grant build-out requirements. | Nebraskalink, LLC | NebraskaLink's only delays this quarter were due to the winter season and NebraskaLink was waiting for approval on an Award Action Request to swap CAI's within some of our grant cities of our project due to changes in services being provided by alternate carriers since our grant was awarded. | The only issues that would impact our goals for this quarters project would be inclement weather in our project area. | TRUE
NT10BIX5570112 | 2013 | Q2 | Q2 - 2013 | In Q2, 2013, NebraskaLink started and completed our Grand Island town project. This allowed us to bring fiber to 23 CAIâ€™s in Grand Island. NebraskaLink also completed the builds to 12 additional CAIâ€™s in North Platte and 12 additional CAIâ€™s in Kearney. We were also able to bring fiber to 1 CAI in O'Neill and 1 CAI in Valentine. This completes our build out requirements for the NTIA BTOP Grant. | 461 | 1427 | 0 | 0 | 461 | 0 | 0 | 68 | NebraskaLink is on target with this milesone. | NebraskaLink is on target with this milestone. | N/A | N/A | NebraskaLink is on target with this milestone. | N/A | N/A | NebraskaLink is on target with this milestone | 24 | 1 | 12 | Four U Technology Consolidated Telecom Nebraska Central Telephone Company Hamilton Telecommunications Northeast Nebraska Telephone Company Great Plains Communications American Broadband Windstream Frontier Clarks Telephone Company Three Rivers Telephone Company K&M Telephone Company Hershey Telephone AT&T SDN Communications Level 3 Benkelman Telephone Arapahoe Telephone Cox Business Allo Pinpoint Glenwood Telecommunications Unite Private Networks USA Communications | NebraskaLink currently offers the following wholesale services: Direct Internet Access (DIA), Ethernet Transport and Private Line/ TDM Services. These are priced on an individual basis, based on interconnection ability, local loop availability and distance for the circuit. | N/A | 24 | 0 | 0 | 10 | NebraskaLink is ahead of our target baseline for signed agreements with Broadband Wholesales or last mile providers. | N/A | N/A | 10 Mbps: 5 20 Mbps: 2 50 Mbps: 2 100 Mbps: 4 150 Mbps: 1 200 Mbps: 1 250 Mbps : 500 Mbps: 3 1000 Mbps 1 10 Gbps: 3 DS3: 2 | 101 | 101 | 0 | 15 | NebraskaLink is currently providing service to 18 CAI's listed in their application, plus have built laterals to an additional 83 CAI's listed in our application. Many CAI's listed in our application are currently under contract with existing carriers - some have allowed us to build laterals to their sites for potential future business. | Laterals built to sites | N/A | 5 Mbps: 10 Mbps: 1 20 Mbps: 3 30 Mbps: 50 Mbps: 2 60 Mbps: 1 75 Mbps: 1 100 Mbps: 4 150 Mbps: 200 Mbps: 1 250 Mbps: 300 Mbps: 2 500 Mbps: 1 1000 Mbps: 2 10 Gbps: NebraskaLink does not currently supply service to all CAI's - some have laterals built to their sites | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | In Q3, 2013, NebraskaLink will be entering into the grant closeout stage. | Nebraskalink, LLC | NebraskaLink did not run into any challenges or issues during the 2nd quarter. Weather in our area was perfect to continue our construction. | NebraskaLink is not anticipating any issues in the upcoming quarter. NebraskaLink expects to work closely with our BTOP team on the close out period of our grant. | TRUE
NT10BIX5570112 | 2013 | Q3 | Q3 - 2013 | On 07/29/2010, NebraskaLink was awarded an NTIA / BTOP Stimulus grant. We began construction in 05/2011 and finished in 06/2013. We completed 461 miles of optical backbone fiber builds, which when combined with our 1427 miles of leased backbone fiber totaled 1888 mile fiber optic backbone. NebraskaLink equipped the backbone with a combination of 8 and 40 wave DWDM equipment. Along the newly created backbone, NebraskaLink interconnected with 24 Nebraska telephone and cable TV companies. This allowed us to expand our service foot-print to all other areas of Nebraska, including areas not reached by our backbone network. As part of our total miles, NebraskaLink completed 71 miles of aerial and underground construction within the cities of North Platte, Kearney, Oâ€™Neill, Valentine, Sidney and Grand Island allowing us to provide fiber optic services to 101 community anchor institutions. Benefits of the newly completed network include; â€¢ Interconnects with communications partners â€“ this helps us expand our footprint and provide end-to-end services to customers across the state â€¢ Large Ethernet capacity â€“ this allows us to sell large circuits to customers, which was not available in Nebraska prior to NebraskaLinkâ€™s backbone â€¢ Redundancy â€“ NebraskaLinkâ€™s network includes three main rings enabling us to protect circuits across the state. No other providers could provide a protected service prior to NebraskaLinkâ€™s backbone â€¢ Contracts with University system, State of Nebraska and Nebraska Schools â€“ NebraskaLink is able to offer high quality â€“ cost effective solutions that were not previously available. â€¢ Competition â€“ several communities along the NebraskaLink backbone were either unserved or underserved prior to the NebraskaLink network â€¢ Additional Jobs â€“ NebraskaLink has grown our staff to 14 employees since the beginning of the grant project â€“ our project has also contributed to the work forces of our contractors | 461 | 1427 | 0 | 0 | 461 | 0 | 0 | 68 | NebraskaLink completed this milestone on target | NebraskaLink completed this milestone on target | N/A | N/A | NebraskaLink completed this milestone on target | N/A | N/A | NebraskaLink is ahead of target on this milestone | 24 | 0 | 12 | Four U Technology Consolidated Telecom Nebraska Central Telephone Company Hamilton Telecommunications Northeast Nebraska Telephone Company Great Plains Communications American Broadband Windstream Frontier Clarks Telephone Company Three Rivers Telephone Company K&M Telephone Company Hershey Telephone AT&T SDN Communications Level 3 Benkelman Telephone Arapahoe Telephone Cox Business Allo Pinpoint Glenwood Telecommunications Unite Private Networks USA Communications | NebraskaLink currently offers the following wholesale services: Direct Internet Access (DIA), Ethernet Transport and Private Line/ TDM Services. These are priced on an individual basis, based on interconnection ability, local loop availability and distance for the circuit. Please see attachment. | N/A | 24 | 0 | 0 | 10 | NebraskaLink completed this milestone ahead of target | N/A | N/A | 10 Mbps: 5 20 Mbps: 2 50 Mbps: 2 100 Mbps: 4 150 Mbps: 1 200 Mbps: 1 250 Mbps : 500 Mbps: 3 1000 Mbps 1 10 Gbps: 3 DS3: 2 | 101 | 101 | 0 | 15 | NebraskaLink is currently providing service to 18 CAI's listed in their application, plus have built laterals to an additional 83 CAI's listed in our application. Many CAI's listed in our application are currently under contract with existing carriers - some have allowed us to build laterals to their sites for potential future business. | Laterals built to sites | N/A | 5 Mbps: 10 Mbps: 1 20 Mbps: 3 30 Mbps: 50 Mbps: 2 60 Mbps: 1 75 Mbps: 1 100 Mbps: 4 150 Mbps: 200 Mbps: 1 250 Mbps: 300 Mbps: 2 500 Mbps: 1 1000 Mbps: 2 10 Gbps: NebraskaLink does not currently supply service to all CAI's - some have laterals built to their sites | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | NebraskaLink's BTOP project is complete. | Nebraskalink, LLC | NebraskaLink did not encounter any issues. | NebraskaLink's BTOP project is complete. | TRUE
NT10BIX5570113 | 2010 | Q4 | Q4 - 2010 | During the quarter October 1, 2010 through December 31, 2010 the following activities occurred: 1) The Environmental Assessment project continued. The first set of Environmental Assessment documents was submitted for review in early October. Work continued on the final draft documents during November and December. These documents are scheduled to be submitted on February 1, 2011 for review. 2) Conference calls were held with the National Telecommunications and Information Administration (NTIA) during November and December to review the State's match. 3) The State prepared and submitted the Baseline Project Report. It was reviewed and approved by NTIA. 4) An update on the Oklahoma Community Anchor Network (OCAN) project was presented on November 18 to Community Anchor Institutions attending from across the State. 5) An update on the OCAN project was presented on December 9 to Librarians attending from across the State. 6) An update on the OCAN project was presented on December 15 to Broadband Providers attending from across the State. 7) A Request for Proposals was issued for engineering services for the OCAN project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | N/A | No variance from Baseline. | No variance from Baseline. | N/A | N/A | No variance from Baseline. | 0 | 0 | 0 | None at this time. | None at this time. | N/A | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | No variance from Baseline. | The speed tier available is planned to be 100MB. There is no variance from Baseline. | 0 | 0 | 0 | 0 | No variance from Baseline. | No variance from Baseline. | No variance from Baseline. | The speed tier available is planned to be 1GB. There is no variance from Baseline. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) Complete the Environmental Assessment and receive Finding Of No Significant Impact (FONSI). 2) Continue work on Network Design and reach 2% completion. 3) Continue work on acquiring Construction Permits and Other Approvals, including Railroad Permits, and reach 54% completion. 4) If the Environmental Assessment receives a Finding Of No Significant Impact, begin Network Build activities and reach 1% completion. | Finance, Oklahoma Office of State | There were no challenges or issues faced during the past quarter in achieving planned progress against the project milestones. The State is working with the National Telecommunications and Information Administration (NTIA) to define the State Match. | 1) Finishing and submitting the Environmental Assessment and receiving the Finding Of No Significant Impact (FONSI) from the National Telecommunications and Information Administration (NTIA). 2) Completion of definition and acceptance by NTIA of the State Match. | TRUE
NT10BIX5570113 | 2011 | Q1 | Q1 - 2011 | Significant accomplishments on the Oklahoma Community Anchor Network (OCAN) project during the quarter January 1, 2011 through March 31, 2011: 1) Environmental Assessment (EA) Final Draft documents submitted to the National Telecommunications and Information Administration (NTIA) February 1, 2011. 2) Additional documentation supporting the State of Oklahomaâ€™s Right-of-Way Match provided to NTIA. 3) The State received responses to Request for Proposals (RFPs) for engineering services to design the installation of the Oklahoma Community Anchor Network (OCAN) fiber optic cable over the entire route. The State completed reviews of the responses, and completed interviews of the engineering firms on March 10, 2011. 4) An evaluation of possible overlaps with other BIP and BTOP grantee projects was completed. The State reported to NTIA there is only one 8.1 mile overlap with one BIP Grantee project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | N/A | No variance from Baseline. | No variance from Baseline. | N/A | N/A | N/A | 0 | 0 | 0 | None at this time. | None at this time. | N/A | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | No variance from Baseline. | The speed tier available is planned to be 100MB. There is no variance from Baseline. | 0 | 0 | 0 | 0 | No variance from Baseline. | No variance from Baseline. | No variance from Baseline. | The speed tier available is planned to be 1GB. There is no variance from Baseline. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) Receive the Finding Of No Significant Impact (FONSI) on the Environmental Assessment. 2) Continue work on total network design. Negotiate contracts with engineering firms for the design of the installation of the Oklahoma Community Anchor Network (OCAN) fiber optic cable over the entire route. Goal is to reach the targeted 3% completion. 3) Continue Network Build activities. Release RFP for Joint Construction Partnerships and Indefeasible or Irrevocable Right of Use (IRU) Partnerships. Receive and evaluate responses and negotiate contracts with selected partners. 4) Release RFP for materials (fiber optic cable, conduit, etc.). Receive and evaluate responses and negotiate contracts with selected suppliers. 5) Commence acquiring needed construction permits, railroad permits and other approvals. | Finance, Oklahoma Office of State | Other than those covered in 2e and 2h above, there were no significant challenges faced during the past quarter that prevented achieving planned progress against project milestones. | All work completed to date on the Oklahoma Community Anchor Network (OCAN) project has been completed without expenditure of federal funds. Before the project can advance and expend federal funds it must: 1) Receive a Finding Of No Significant Impact (FONSI) from the National Telecommunications and Information Administration (NTIA) on the Environmental Assessment. 2) Successfully negotiate contracts with engineering firms for the design of the installation of the Oklahoma Community Anchor Network (OCAN) fiber optic cable over the entire route. 3) Select partners from responses to a Request For Proposal (RFP) and successfully negotiate contracts with the selected partners for Joint Construction or Indefeasible or Irrevocable Rights of Use (IRUâ€™s) for selected segments of the OCAN project. 4) Commence acquiring needed construction permits, railroad permits and other approvals. | TRUE
NT10BIX5570113 | 2011 | Q2 | Q2 - 2011 | Significant accomplishments on the Oklahoma Community Anchor Network (OCAN) project during the quarter April 1, 2011 through June 30, 2011: 1) The State received the Finding of No Significant Impact (FONSI) on its Environmental Assessment (EA). 2) Conference calls continued with the National Telecommunications and Information Administration (NTIA) to review the Oklahoma Community Anchor Network (OCAN) project status, the State's match, and possible overlaps with other Broadband Technology Opportunities Program (BTOP) or Broadband Initiatives Program (BIP) projects. 3) The NTIA Program Officer traveled to Oklahoma City and met with the OCAN project team on May 19, 2011 to review the project status and discuss the State's Match and possible overlaps with other BTOP or BIP projects. 4) The State submitted documentation to NTIA verifying the In-Kind Valuation and Cash Match and received confirmation the Match Special Award Condition (SAC) had been satisfied. 5) The State submitted documentation to NTIA on two possible overlaps with BIP projects, verifying there is no overlap with either project, and received confirmation the Overlap Special Award Condition (SAC) had been satisfied. 6) Negotiations were initiated with the Engineering firms selected from the Request for Proposal (RFP) process for the OCAN project design. 7) The State issued a RFP on May 20, 2011 to solicit and consider proposals from qualified offerors willing to enter into one or multiple agreements for publ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | N/A | No variance from Baseline | No variance from Baseline | N/A | N/A | N/A | 0 | 0 | 0 | None at this time. | None at this time.3 | N/A | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | No variance from Baseline. | The speed tier available is planned to be 100MB. There is no variance from Baseline. | 0 | 0 | 0 | 0 | No variance from Baseline. | No variance from Baseline. | No variance from Baseline. | The speed tier available is planned to be 1GB. There is no variance from Baseline. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) Continue work on total network design. Complete negotiations and sign contracts with selected engineering firms for the design of the installation of the Oklahoma Community Anchor Network (OCAN) fiber optic cable over the entire route. Goal is to reach the targeted 6% completion. 2) Continue Network Build activities. Evaluate responses to Request for Proposal (RFP) to solicit and consider proposals from qualified offerors willing to enter into one or multiple agreements for public-private initiative/partnership(s) or shared resources project(s) for the construction of fiber optic cables, conduit and ground boxes along the OCAN Broadband project construction routes. Conduct negotiations and sign contracts with selected partners. 3) Issue RFP(s) for materials (fiber optic cable, conduit, communications huts, etc.). Receive and evaluate responses and issue purchase orders to multiple selected suppliers. 4) Commence acquiring needed construction permits, railroad permits and other approvals. | Finance, Oklahoma Office of State | Other than those covered in 2e and 2h above, there were no significant challenges faced during the past quarter that prevented achieving planned progress against project milestones. | 1) Due to awaiting the Finding Of No Significant Impact (FONSI) from the National Telecommunications and Information Administration (NTIA) on the Environmental Assessment, all work completed to date on the Oklahoma Community Anchor Network (OCAN) project has been completed without expenditure of federal funds. 2) The State must complete negotiations and sign contracts with the engineering firms selected for the design of the installation of the Oklahoma Community Anchor Network (OCAN) fiber optic cable over the entire 1,005 mile route. 3) The State must select partners from the responses to the Request For Proposal (RFP) to solicit and consider proposals from qualified offerors willing to enter into one or multiple agreements for public-private initiative/partnership(s) or shared resources project(s) for the construction of fiber optic cables, conduit and ground boxes along the OCAN Broadband project construction routes, and must successfully negotiate and sign contracts with the selected partners. 4) The State must issue RFP(s) for materials (fiber optic cable, conduit, communications huts, etc.). Receive and evaluate responses and issue purchase orders to multiple selected suppliers. 5) The State must commence acquiring needed construction permits, railroad permits and other approvals. | TRUE
NT10BIX5570113 | 2011 | Q3 | Q3 - 2011 | Significant accomplishments on the Oklahoma Community Anchor Network (OCAN) project during the quarter July 1, 2011 through September 30, 2011: 1) The State completed negotiations and signed contracts with six Engineering firms for the detailed engineering design of the OCAN project. The engineering design project was divided into thirty-one sections spanning the OCAN project. Twenty sections have been completed and reviewed. 2) The State issued a Request for Proposal (RFP) for Communications Huts for the OCAN project. Bids were received and reviewed, and a recommendation made to award contracts to two bidders. NOTE: The bids for communications huts came in approximately $2.4 million higher than the estimate of $1,350,000 in the grant budget. This was primarily due to redesign to accommodate providers in the huts in order to increase utilization of the OCAN fiber. $2,490,620 has been transferred from the construction (i) category to the structures (b) category in the Infrastructure Budget Execution Details. The construction (i) category was reduced from $52,600,000 to $50,109,380 and the structures (b) category was increased from $5,872,500 to $8,363,120. 3) The State issued a RFP for Fiber Optic Cable for the OCAN project. The RFP was posted on September 28, 2011 with a close date of October 27, 2011. 4) The State completed evaluations of the proposals received from five bidders on the RFP for public-private initiative/partnership(s) or shared resources proje | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | N/A | No variance from Baseline. | No variance from Baseline. | N/A | N/A | No variance from Baseline. | 0 | 0 | 0 | None at this time. | None at this time. | N/A | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | No variance from Baseline. | The speed tier available is planned to be 100MB. There is no variance from Baseline. | 0 | 0 | 0 | 0 | No variance from Baseline. | No variance from Baseline. | No variance from Baseline. | The speed tier available is planned to be 1GB. There is no variance from Baseline. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) Complete the total network engineering design for construction and installation of the Oklahoma Community Anchor Network (OCAN) fiber optic cable over the entire route. 2) Complete review of Indefeasible Right of Use (IRU) Agreements submitted by one bidder for existing fiber optic strands that will allow the State to meet the purpose of the grant on certain segments of the OCAN project. Complete negotiations with this bidder and submit the IRU Agreements to NTIA for review. 3) Issue Request for Proposal (RFP) packages for construction of the OCAN project on remaining segments. 4) Evaluate responses to RFP for Fiber Optic Cable for the OCAN project and award bids. 5) Complete acquisition of needed construction permits, railroad permits and other approvals. 6) Issue RFP(s) for additional required materials (conduit, handholes, etc.). Receive and evaluate responses and award bids to multiple selected suppliers. 7) Evaluate responses to RFP packages for construction of the OCAN project and begin awarding bids. | Finance, Oklahoma Office of State | Other than those covered in 2e and 2h above, there were no significant challenges faced during the past quarter that prevented achieving planned progress against project milestones. | 1) The State must get the total network engineering design completed for construction and installation of the Oklahoma Community Anchor Network (OCAN) fiber optic cable over the entire route. 2) The State must complete review of Indefeasible Right of Use (IRU) Agreements submitted by one bidder for existing fiber optic strands that will allow the State to meet the purpose of the grant on certain segments of the OCAN project, and must complete negotiations with this bidder and submit the IRU Agreements to NTIA for review. 3) The State must issue Request for Proposal (RFP) packages for construction of the OCAN project on remaining segments. 4) The State must complete evaluations of responses to the RFP for Fiber Optic Cable for the OCAN project and award bids. 5) The State must complete acquisition of needed construction permits, railroad permits and other approvals. 6) The State must issue RFP(s) for additional required materials (conduit, handholes, etc.), and receive and evaluate responses and award bids. 7) The State must evaluate responses to RFP packages for construction of the OCAN project and begin awarding bids. | TRUE
NT10BIX5570113 | 2011 | Q4 | Q4 - 2011 | Significant accomplishments on the Oklahoma Community Anchor Network (OCAN) project during the quarter October 1, 2011 through December 31, 2011: 1) Conference calls continued with the National Telecommunications and Information Administration (NTIA) to review the Oklahoma Community Anchor Network (OCAN) project status. 2) Detailed engineering plans for the OCAN project were submitted for review. The engineering design project was divided into thirty-one (31) segments corresponding to the thirty-one construction segments spanning the OCAN project. The thirty-one segments were split between six (6) separate engineering firms to complete the detailed designs. Twenty-five of the detailed engineering plans have been reviewed and approved. One engineering firm is in process of finalizing the six remaining detailed engineering plans and will submit them in January, 2012. 3) Construction continued on the sixteen (16) new communications huts for the OCAN project. 4) The State completed evaluations of the bids for Fiber Optic Cable. Due to increased demand from communities and anchor institutions for strands of the OCAN Fiber Optic Cable, the State submitted an Award Action Request (AAR) to NTIA requesting to increase the number of strands over what was specified in the grant application: 48 strand fiber to 96 strand and 96 strand fiber to 144 strand. NTIA approved the AAR. 5) The State completed the Railroad Permitting process and has received permits from all but a few affected railroads for the OCAN project. 6) The State executed Memorandums of Understanding (MOUs) with Oklahoma communities the OCAN project is passing through. The MOUs grant the OCAN project access to right of way through the communities. 7) The State advertised for bids for construction of the OCAN project. There will be bid lettings in January, February and March, 2012. 8) The State was requested by NTIA to complete a Project Performance Improvement Plan. The State completed and submitted the Plan to NTIA on November 18, 2011. 9) The State submitted a Project Modification Request on October 31, 2011 to change the route of the OCAN fiber in six locations due to planned road construction. The State is completing the Environmental Assessments (EA) for the six locations and will submit an EA Addendum when those are completed. 10) The OCAN Project Plan was updated and submitted to the NTIA Program Officer. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Variance from Baseline. As noted in number 1, item 5, The State completed review of proposed Indefeasible Right of Use (IRU) Agreements for existing fiber optic strands that will allow the State to meet the purpose of the grant. The State submitted an Award Action Request (AAR) to the National Telecommunications and Information Administration (NTIA) requesting to execute three separate IRUs that will incorporate ten (10) of the thirty-one OCAN project segments, reducing the number of segments to be constructed from 31 to 21. The State is awaiting NTIA approval of this AAR. Also, as noted in number 1, item 8, the State advertised for bids for construction of the OCAN project. There will be bid lettings in January, February and March, 2012. The State is expediting this process with the goal of completing this milestone on schedule. | N/A | N/A | No variance from Baseline. | No variance from Baseline. | N/A | N/A | No variance from Baseline. | 0 | 0 | 0 | None at this time. | None at this time. | N/A | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | No variance from Baseline. | The speed tier available is planned to be 100MB. There is no variance from Baseline. | 0 | 0 | 0 | 0 | No variance from Baseline. | No variance from Baseline. | No variance from Baseline. | The speed tier available is planned to be 1GB. There is no variance from Baseline. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) Complete the six remaining network engineering design plans for construction and installation of the Oklahoma Community Anchor Network (OCAN) fiber optic cable. 2) Complete construction on the sixteen new communications huts for the OCAN project. 3) Issue purchase orders for all of the fiber optic cable required for the OCAN project. 4) Complete acquisition of the remaining needed railroad permits for the OCAN project. 5) Award the bids for construction of the OCAN project on segments not included in the proposed Indefeasible Right of Use (IRU) Agreements. 6) Issue Request for Proposal (RFP) for the network equipment needed for the OCAN project. Receive and evaluate responses and award bids to multiple selected suppliers. 7) Complete and submit an Environmental Assessment Addendum for the Project Modification Request to change the route of the OCAN fiber in six locations due to planned road construction. | Finance, Oklahoma Office of State | Other than those covered above there were no other significant challenges faced during the past quarter. | 1) The State must award all of the bids for construction of the Oklahoma Community Anchor Network (OCAN) project on all segments not included in the proposed Indefeasible Right of Use (IRU) Agreements. 2) The State must receive approval on the Environmental Assessment Addendum for the Project Modification Request to change the route of the OCAN fiber in six locations due to planned road construction. 3) The State must complete evaluations of responses to the RFP for network equipment and award the bids. | TRUE
NT10BIX5570113 | 2012 | Q1 | Q1 - 2012 | Significant accomplishments on the Oklahoma Community Anchor Network (OCAN) project during the quarter January 1, 2012 through March 31, 2012: 1) Conference calls continued with the National Telecommunications and Information Administration (NTIA) to review the Oklahoma Community Anchor Network (OCAN) project status. 2) Construction continued on the sixteen new Communications Huts for the OCAN project. Eight of the Communications Huts have been completed and installed. 3) Orders were placed for Fiber Optic Cable. Deliveries of all outside plant cable began in March and will be completed in May. Inside plant (plenum) cable is being delivered in the March through June time frame. 4) The State received approval from NTIA to execute two Indefeasible Right of Use (IRU) Agreements for existing fiber optic strands that will allow the State to meet the purpose of the grant. The State has executed the first IRU for 2 segments of the OCAN project covering 60 miles of the OCAN route and connecting one Community Anchor Institution (CAI). 5) The State received several more Railroad Permits and is awaiting the remaining few. 6) The State completed Memorandums of Understanding (MOUs) with Oklahoma communities the OCAN project is passing through. The MOUs grant the OCAN project access to right of way through the communities. 7) The State awarded 21 bids for construction of 21 segments of the OCAN project covering 748 miles of the OCAN route. 8) The State issued a Request for Proposal (RFP) for the network equipment required for the OCAN project. Responses were received and the evaluation of responses is underway. 9) The State received approval from NTIA for a Project Modification Request to make very minor route changes in seven locations along the OCAN route due to planned road construction. 10) The detailed OCAN Project Plan was updated and submitted to the NTIA Program Officer. | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | Variance from Baseline. As noted in number 1, item 7, the State awarded 21 bids for construction of 21 segments of the OCAN project covering 748 miles of the OCAN route. The State continues to expedite this process with the goal of completing this milestone on schedule. | Variance from Baseline. As noted in number 1, item 4, the State received approval from NTIA to execute two Indefeasible Right of Use (IRU) Agreements for existing fiber optic strands that will allow the State to meet the purpose of the grant. The State has executed the first IRU for 2 segments of the OCAN project covering 60 miles of the OCAN route and connecting one Community Anchor Institution (CAI). | N/A | No variance from Baseline. | No variance from Baseline. | N/A | N/A | No variance from Baseline. | 0 | 0 | 0 | None at this time. | None at this time. | N/A | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | No variance from Baseline. | The speed tier available is planned to be 100MB. There is no variance from Baseline. | 0 | 0 | 0 | 0 | No variance from Baseline. | No variance from Baseline. | No variance from Baseline. | The speed tier available is planned to be 1GB. There is no variance from Baseline. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) Complete construction and installation of the remaining eight Communications Huts for the OCAN project. 2) Complete acquisition of the remaining needed railroad permits for the OCAN project. 3) Execute IRUâ€™s for 8 more segments of the OCAN project covering 197 miles of the OCAN route and connecting 7 Community Anchor Institutions (CAI). 4) Receive remaining deliveries of fiber optic cable ordered for the OCAN project. 5) Complete construction of 645 conduit miles of the OCAN project route. 6) Complete pulling fiber optic cable in 11 miles of the constructed conduit and connect one CAI. 7) Complete evaluations of the responses to the RFP for the network equipment needed for the OCAN project and award bids to multiple selected suppliers. 8) Complete one agreement with a broadband wholesaler/last mile provider for the lease of strands of fiber optic cable from the OCAN project. | Finance, Oklahoma Office of State | Other than those covered above there were no other significant challenges faced during this quarter. | 1) The State must complete construction and installation of the remaining Communications Huts for the OCAN project. 2) The State must receive remaining deliveries of fiber optic cable ordered for the OCAN project. 3) The State must execute the remaining Indefeasible Right of Use (IRU) Agreements. 4) The State must complete evaluations of responses to the RFP for network equipment, award the bids and begin receiving the equipment. 5) The State must keep construction and other milestones of the OCAN project on schedule to meet the overall 67 percent project completion milestone by the end of year two of the project. | TRUE
NT10BIX5570113 | 2012 | Q2 | Q2 - 2012 | Significant accomplishments on the Oklahoma Community Anchor Network (OCAN) project during the quarter April 1, 2012 through June 30, 2012: 1) Conference calls continued with the National Telecommunications and Information Administration (NTIA) to review the Oklahoma Community Anchor Network (OCAN) project status. 2) A Site Visit by the NTIA Federal Program Officer was completed during the first week of June. 3) Construction was completed on the sixteen new communications huts for the OCAN project. 4) Deliveries of all inside plant and outside plant fiber optic cable were completed. 5) Evaluations of the responses to the RFP for network equipment were completed and all network equipment was ordered. 6) The State received approval from NTIA to execute one additional Indefeasible Right of Use (IRU) Agreement for 47 miles of existing fiber optic cable infrastructure that will allow the State to meet the purpose of the grant. 7) The State received several additional Railroad Permits and is awaiting several. 8) The State completed all remaining Memorandums of Understanding (MOUs) with Oklahoma communities the OCAN project is passing through. The MOUs grant the OCAN project access to right of way through the communities. 9) Construction was begun on 12 of 21 segments of the OCAN project with 497 miles of conduit construction completed and 157 miles of fiber optic cable pulled. 10) The detailed OCAN Project Plan was updated and submitted to the NTIA Federal Program Officer. | 157 | 60 | 0 | 0 | 157 | 0 | 0 | 0 | Variance from Baseline. As noted in number 1, item 9, the State has 497 miles of conduit construction completed, 157 miles with fiber pulled. The State continues to expedite this process with the goal of completing this milestone on schedule. | Variance from Baseline. As noted in 2h above, the State has executed one IRU for 60 miles of existing infrastructure on the OCAN route and connecting one Community Anchor Institution (CAI) as noted in number 9 below. | N/A | No variance from Baseline. | Variance from Baseline. As noted above the State has completed construction of 157 miles of the OCAN route with new underground fiber. | N/A | N/A | No variance from Baseline. | 0 | 0 | 0 | None at this time. | None at this time. | N/A | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | No variance from Baseline. | The speed tier available is planned to be 100MB. There is no variance from Baseline. | 1 | 0 | 1 | 1 | Variance from Baseline target of 6. As noted in number 9 below, 1 Community Anchor Institution (CAI) has been connected. | Variance from Baseline target of 3. No CAI's receiving new access have yet been connected. | Variance from Baseline target of 3. As noted in number 9 below, 1 CAI receiving improved access has been connected. | No variance from Baseline - the speed tier available is 1GB. One Community Anchor Institution, as noted in number 9 below, has been connected. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) Complete conduit construction on all segments of the OCAN project. 2) Complete pulling all fiber optic cable on all segments of the OCAN project. 3) Execute IRUâ€™s for 8 more segments of the OCAN project covering 197 miles of the OCAN route and connecting 7 Community Anchor Institutions (CAI). 4) Begin installing network Routers, Switches, DWDM, etc. equipment in the OCAN project Huts and Community Anchor Institutions (CAIâ€™s). 5) Review and update the OCAN Project Sustainability Plan and document the OCAN Pricing Plans. 6) Begin negotiating agreements with providers requesting access to the OCAN fiber. 7) Complete connection of fiber optic cable to an additional 20 CAI's, 7 through IRU's as noted above. | Finance, Oklahoma Office of State | Other than those covered above there were no other significant challenges faced during this quarter. | 1) The State must complete the conduit construction and pulling all fiber optic cable on all segments of the OCAN project. 2) The State must begin installing network Routers, Switches, DWDM, etc. equipment in the OCAN project Huts and Community Anchor Institutions (CAIâ€™s). 3) The State must execute the remaining Indefeasible Right of Use (IRU) Agreements. 4) The State must begin lighting segments of the OCAN fiber and providing improved services to CAI subscribers. | TRUE
NT10BIX5570113 | 2012 | Q3 | Q3 - 2012 | Significant accomplishments on the Oklahoma Community Anchor Network (OCAN) project during the quarter July 1, 2012 through September 30, 2012: 1) Conference calls continued with the National Telecommunications and Information Administration (NTIA) to review the Oklahoma Community Anchor Network (OCAN) project status. 2) The detailed OCAN Project Plan was updated and submitted to the NTIA Federal Program Officer. 3) The OCAN project met the year two milestone of 67 percent completion with 70.84 percent of Federal funds expended by July 31, 2012. 4) The State received all remaining Railroad Permits. 5) A majority of the new network equipment was delivered. 6) The State executed one additional Indefeasible Right of Use (IRU) Agreement for 47 miles of existing fiber optic cable infrastructure that will allow the State to meet the purpose of the grant. 7) Construction continued on the 12 project segments begun last quarter and commenced on the remaining 9 segments with 713 miles of conduit construction completed and 471 miles of fiber optic cable pulled. 8) Eighteen of the 32 Community Anchor Institutions (CAIs) included in the OCAN project were connected to OCAN fiber. Four of the CAIs are being provided with new access and fourteen are being provided with improved access. | 471 | 257 | 0 | 0 | 471 | 0 | 0 | 18 | Variance from Baseline. As noted in number 1, item 7, the State has 713 miles of conduit construction completed, 471 miles with fiber pulled. The State is a bit ahead of Baseline on this milestone. | Variance from Baseline. As noted in 2h above, the State has executed three IRU Agreements for a total of 257 miles of existing infrastructure on the OCAN route. | N/A | No variance from Baseline. | Variance from Baseline. As noted above the State has completed construction of 471 miles of the OCAN route with new underground fiber. | N/A | N/A | Variance from Baseline. The project has connected fiber optic cable to 18 Community Anchor Institutions (CAI's). | 0 | 0 | 0 | None at this time. | None at this time. | N/A. | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | No variance from Baseline. | The speed tier available is planned to be 100MB. There is no variance from Baseline. | 18 | 4 | 14 | 2 | Variance from Baseline target of 12. 18 Community Anchor Institutions (CAI's) have been connected. | Variance from Baseline target of 6. 4 CAI's receiving new access have been connected. | Variance from Baseline target of 6. 14 CAI's receiving improved access have been connected. | No variance from Baseline - the backbone will be 10GB with two speed tiers available to customers, 100MBPS and 1GB. The 32 CAIs included in the grant will be provided 1GB service. Additional customers (CAIs, last mile providers, etc.) may select either 100MBPS or 1GB service. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) Complete conduit construction on the remaining 35 miles of uncompleted segments of the OCAN project. 2) Complete pulling all fiber optic cable on the remaining 277 miles of uncompleted segments of the OCAN project. 3) Complete connecting the remaining fourteen of 32 Community Anchor Institutions (CAIs) included in the grant. Each of these CAIs will be receiving improved access. 4) Continue installing the new network Routers, Switches, DWDM, etc. equipment in the OCAN project Huts and CAIs. 5) Begin lighting segments of the OCAN fiber and providing either new or improved Broadband services to CAI subscribers. 6) Review and update the OCAN Project Sustainability Plan and document the OCAN Pricing Plans. 7) Continue holding meetings with providers requesting access to the OCAN fiber. There are no plans to execute agreements until after the OCAN project is completed during Q1 2013. | Finance, Oklahoma Office of State | Other than those covered above there were no other significant challenges faced during this quarter. | 1) The State must remain on schedule to complete the conduit construction and pulling of all fiber optic cable on all uncompleted segments of the OCAN project. 2) The State must remain on schedule with the installation of network Routers, Switches, DWDM, etc. equipment in the OCAN project Huts and Community Anchor Institutions (CAIâ€™s). 3) The State must remain on schedule lighting segments of the OCAN fiber and providing new or improved services to CAI subscribers. | TRUE
NT10BIX5570113 | 2012 | Q4 | Q4 - 2012 | 1) Conference calls continued with the National Telecommunications and Information Administration (NTIA) to review the Oklahoma Community Anchor Network (OCAN) project status. 2) The detailed OCAN Project Plan was updated and submitted to the NTIA Federal Program Officer. 3) The majority of new network equipment was installed. 4) 6 more Community Anchor Institutions (CAIâ€™s) were connected with fiber optic cable, receiving improved access, for a total of 24 connected CAIâ€™s. 5) Construction continued on all 21 project segments with completion of 9 segments, 870 total miles of conduit construction completed and 700 total miles of fiber optic cable pulled. ***Overall increase in conduit and fiber installation resulted from the following: The initial projection of conduit and fiber was based on general start and end points. When figuring IRU mileage into the network it is key to note that the executed IRU mileage is 294 miles whereas our original OCAN route was 269 miles, so there is a 25 mile difference that should not be subtracted from new network miles deployed, because these miles are outside of (in addition to) the IRU mileage. As construction progressed, variables came into play that were not accounted for in the baseline generalization. For instance, the estimated mileage did not account for all cases where terrain caused alignment changes, spurs to connect CAIâ€™s, and right-of-ways shaping placement of conduit. In addition, some locations such as colleges have two lines of conduit installed for fiber going to and from the college, doubling the conduit and fiber used to connect these anchors. Any alterations made to the route were approved by the environmental assessments. | 700 | 294 | 0 | 432 | 700 | 0 | 0 | 40 | Variance from Baseline. The delay in construction completion on 4 segments resulted in fiber-pull delays this quarter. The problems have been resolved and the remaining segments will be completed by the end of January 2013. | Variance from Baseline. The State has executed three IRU Agreements for a total of 294 miles of existing infrastructure on the OCAN route. | N/A | Variance from Baseline. 432 miles of the existing OCAN network are leased and have been booked as match. | Variance from Baseline. As noted above, the State has completed construction of 700 miles of the OCAN route with new underground fiber. | N/A | N/A | Variance from Baseline target of 24. The project has connected fiber optic cable to 24 Community Anchor Institutions (CAI's) and 16 communication huts. | 0 | 0 | 0 | None at this time. | None at this time. | N/A | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | No variance from Baseline. | The speed tier available is planned to be 100MB. There is no variance from Baseline. | 24 | 4 | 20 | 2 | Variance from Baseline target of 18. 24 Community Anchor Institutions (CAI's) have been connected. | Variance from Baseline target of 9. 4 CAI's receiving new access have been connected. Since the original application, weâ€™ve determined that some of the planned CAIs should be considered improved rather than new. We plan to complete all CAI connections, 4 with new access and 28 with improved access, by the end of Q1 2013. | Variance from Baseline target of 9. 20 CAI's receiving improved access have been connected. Since the original application, weâ€™ve determined that some of the planned CAIs should be considered improved rather than new. We plan to complete all CAI connections, 4 with new access and 28 with improved access, by the end of Q1 2013. | No variance from Baseline - the backbone will be 10GB with two speed tiers available to customers, 100 MBPS and 1 GB. The 32 CAI's included in the grant will be provided 1GB service. Additional customers (CAI's, last mile providers, etc.) may select either 100 MBPS or 1GB service. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) Complete conduit construction on the remaining uncompleted segments of the OCAN project. 2) Complete pulling all fiber optic cable on the remaining uncompleted segments of the OCAN project. 3) Complete connecting the remaining eight of 32 Community Anchor Institutions (CAIs) included in the grant. Each of these CAIs will be receiving improved access. 4) Continue installing the new network Routers, Switches, DWDM, etc. equipment in the OCAN project Huts and CAIs. 5) Continue lighting segments of the OCAN fiber and providing either new or improved Broadband services to CAI subscribers. 6) Review and update the OCAN Project Sustainability Plan and document the OCAN Pricing Plans. 7) Continue holding meetings with providers requesting access to the OCAN fiber. There are no plans to execute agreements until after the OCAN project is completed during Q1 2013. | Finance, Oklahoma Office of State | Other than those covered above there were no significant challenges faced during this quarter. | The State must remain on schedule with the installation of network generators, Routers, Switches, DWDM, etc. equipment in the OCAN project Huts and Community Anchor Institutions (CAI's). | TRUE
NT10BIX5570113 | 2013 | Q1 | Q1 - 2013 | 1) Conference calls continued with the National Telecommunications and Information Administration (NTIA) to review the Oklahoma Community Anchor Network (OCAN) project status. 2) The OCAN project expended 82.4 percent of Federal funds by March 31, 2013. 3) Construction was completed on all 21 project segments with 827 miles of conduit construction and fiber optic cable. These numbers were trued-up during an internal report review of our sub-recipient. 4) OCAN joined with 1,010 miles of existing State fiber during the quarter being reported. 5) OCAN pursued approval from NTIA to purchase additional optical equipment and ground vaults to utilize remaining BTOP grant funds. 6) An internal report review of our sub-recipient resulted in changes to budget values based on supporting documentation; adjusted Architectural and Engineering Fees match (Infrastructure Budget line D) to reflect expenditures rather than reporting contract amounts $3,768,343 rather than $4,817,836; adjusted Project Inspection Fees match (Infrastructure Budget line F) to reflect actuals and eliminate duplicate recording of funds (within Engineering) $2,833,445 rather than $3,356,541. | 827 | 294 | 0 | 1010 | 827 | 0 | 0 | 40 | Variance from Baseline. As noted in number 1, item 3, 827 miles of conduit construction and fiber optic cable have completed all 21 project segments. The State continues to expedite remaining critical milestones of the project. | Variance from Baseline. The State has executed three IRU Agreements for a total of 294 miles of existing infrastructure on the OCAN route. | N/A | Variance from Baseline. The total 1100 miles of existing State fiber was not joined with OCAN due to issues with Oklahoma Turnpike Authority fibers from Muskogee to Webbers Falls (approx. 90 miles); we anticipate the issues to be resolved before the end of 2013-Q2. | Variance from Baseline. As noted above, the State has completed construction of 827 miles of the OCAN route with new underground fiber. | N/A | N/A | Variance from Baseline target of 36. The project has connected fiber optic cable to 24 Community Anchor Institutions (CAI's) and 16 communication huts. | 0 | 0 | 0 | None at this time. | None at this time. | N/A | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | No variance from Baseline. | The speed tier available is planned to be 100MB. There is no variance from Baseline. | 24 | 4 | 20 | 2 | No variance from Baseline. 24 Community Anchor Institutions (CAI's) have been connected. | Variance from Baseline target of 12. 4 CAI's receiving new access have been connected. Since the original application, weâ€™ve determined that some of the planned CAIs should be considered improved rather than new. We plan to complete all CAI connections, 4 with new access and 28 with improved access, by the end of Q2 2013. | Variance from Baseline target of 12. 20 CAI's receiving improved access have been connected. Since the original application, weâ€™ve determined that some of the planned CAIs should be considered improved rather than new. We plan to complete all CAI connections, 4 with new access and 28 with improved access, by the end of Q2 2013. | No variance from Baseline - the backbone will be 10GB with two speed tiers available to customers, 100 MBPS and 1 GB. The 32 CAI's included in the grant will be provided 1GB service. Additional customers (CAI's, last mile providers, etc.) may select either 100 MBPS or 1GB service. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) Complete connecting the remaining eight of 32 Community Anchor Institutions (CAIs) included in the grant. Each of these CAIs will be receiving improved access. 2) Continue installing the new network Routers, Switches, DWDM, etc. equipment in the OCAN project Huts and CAIs; continue network testing. 3) Review and update the OCAN Project Sustainability Plan and document the OCAN Pricing Plans. 4) Continue holding meetings with providers requesting access to the OCAN fiber. There are no plans to execute agreements until after the OCAN project is completed. 5) Installation of additional access points along the route to provide greater opportunity to connect last-mile providers and CAIâ€™s. *Side Note: Adjustments made to Anticipated Engineering and Inspection Match values in Infrastructure Budget page of PPR, because these values will be lower than previously anticipated. | Finance, Oklahoma Office of State | Other than those covered above there were no significant challenges faced during this quarter. | The State must remain on schedule with the installation of additional ground vaults, network generators, Routers, Switches, DWDM, etc. equipment in the OCAN project Huts and Community Anchor Institutions (CAI's). | TRUE
NT10BIX5570113 | 2013 | Q2 | Q2 - 2013 | Significant accomplishments on the Oklahoma Community Anchor Network (OCAN) project during the quarter April 1, 2013 through June 30, 2013: 1) Conference calls continued with the National Telecommunications and Information Administration (NTIA) to review the Oklahoma Community Anchor Network (OCAN) project status. 2) The OCAN project expended 83.57 percent of Federal funds by June 30, 2013. 3) 47 of the additional 140 distribution points approved for construction by NTIA were completed by end of 2013-Q2, and the remaining 93 access points are on schedule for completion by grant end. | 827 | 294 | 0 | 1010 | 827 | 0 | 0 | 47 | Variance from Baseline. 827 miles of conduit construction and fiber optic cable have completed all 21 project segments. | Variance from Baseline. The State has executed three IRU Agreements for a total of 294 miles of existing infrastructure on the OCAN route. | N/A | Variance from Baseline. The total 1100 miles of existing State fiber was not joined with OCAN due to issues with Oklahoma Turnpike Authority fibers from Muskogee to Webbers Falls (approx. 90 miles); issues were resolved and remaining 90 miles of fiber leased July 26th (2013-Q3). | Variance from Baseline. As noted above, the State has completed construction of 827 miles of the OCAN route with new underground fiber. | N/A | N/A | No variance from Baseline; however, the project has connected fiber optic cable to 31 CAI's including an additional CAI, Gordon Cooper Technology Center, that was not included in original Baseline projection, and 16 communication huts. Fiber remains to be connected to Choctaw Hospital and Southeastern OSU CAI's pending IRU closure for a projected total of 49 new and/or upgraded interconnection points by grant end. | 0 | 0 | 0 | None at this time. | None at this time. | N/A | 0 | 0 | 0 | 0 | No variance from Baseline. | N/A | No variance from Baseline. | The speed tier available is planned to be 100MB. There is no variance from Baseline. | 31 | 4 | 27 | 2 | Variance from Baseline target of 32. 31 Community Anchor Institutions (CAI's) have been connected including Gordon Cooper Technology Center, which was not included in the original Baseline projection. The remaining 2 CAI's are pending IRU closure and completion is anticipated by grant end. | Variance from Baseline target of 16. 4 CAI's receiving new access have been connected. Since the original application, weâ€™ve determined that some of the planned CAIs should be considered improved rather than new. We plan to complete all 33 CAI connections, 4 with new access and 29 with improved access, by the end of the grant. | Variance from Baseline target of 16. 27 CAI's receiving improved access have been connected. Since the original application, weâ€™ve determined that some of the planned CAIs should be considered improved rather than new. We plan to complete all 33 CAI connections, 4 with new access and 29 with improved access, by the end of the grant. | No variance from Baseline - the backbone will be 10GB with two speed tiers available to customers, 100 MBPS and 1 GB. The 32 CAI's included in the grant will be provided 1GB service. Additional customers (CAI's, last mile providers, etc.) may select either 100 MBPS or 1GB service. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | 1) Complete connecting the remaining 2 of 33 Community Anchor Institutions (CAIs) included in the grant. Both of these CAIs will be receiving improved access. 2) Continue installing the new network Routers, Switches, DWDM, etc. equipment in the OCAN project Huts and CAIs; continue network testing. 3) Review and update the OCAN Project Sustainability Plan and document the OCAN Pricing Plans. 4) Continue holding meetings with providers requesting access to the OCAN fiber. There are no plans to execute agreements until after the OCAN project is completed. 5) Complete installation of remaining 93 additional access points along the route to provide greater opportunity to connect last-mile providers and CAIâ€™s. 6) Adjusted Anticipated Actuals for next quarter as shown on the Infrastructure Budget Execution Details page: Decrease Federal item B, Land/Huts, costs lower than initial projection; Decrease Match & Increase Federal item D, Engineering, for NTIA approved reimbursement to ODOT; Decrease Match item F, Inspections, costs lower than initial projection; Decrease Federal item I, Construction, costs lower than initial projection; Increase Federal item J, Equipment, for additional access points and network equipment approved by NTIA; Decrease Match & Increase Federal item K, Miscellaneous, for NTIA approved internal engineering salaries to ODOT. *NOTE that ODOT's TOTAL obligated Match $5,328,245 (Engineering $1,493,438 + Inspections $3,834,807) remains the same though the anticipated Match values for these categories next quarter have changed (Engineering $2,328,245 + Inspections $3,000,000). | Finance, Oklahoma Office of State | Other than those covered above there were no significant challenges faced during this quarter. | The State must remain on schedule with the installation of additional ground vaults, network generators, Routers, Switches, DWDM, etc. equipment in the OCAN project Huts and Community Anchor Institutions (CAI's). | TRUE
NT10BIX5570113 | 2013 | Q3 | Q3 - 2013 | PROJECT OVERALL ACCOMPLISHMENTS & KEY BENEFITS: 1) The OCAN project has the ability to form partnerships with telecommunication companies that wish to participate in this endeavor to expand broadband to Oklahomaâ€™s rural areas. 2) Allows access to basic services in the most remote areas of the state and bring an estimated 863 new jobs to Oklahoma. 3) In addition to the 32 Community Anchor Institutions that will be connected to the network in the initial construction, projections reflect that 10 new anchors will be added every year, resulting in a total of 84 connected institutions by year 8. 4) 827 miles of new fiber construction completed the total 2,221 mile OCAN route reaching 35 counties, 17 tribal jurisdictions and impacting 89% of Oklahoma's population. 5) The OCAN project expended 97.58 percent of Federal funds by grant closeout end. | 827 | 294 | 0 | 1100 | 827 | 0 | 0 | 47 | Variance from Baseline. 827 miles of conduit construction and fiber optic cable have completed all 21 project segments. | Variance from Baseline. The State has executed three IRU Agreements for a total of 294 miles of existing infrastructure on the OCAN route. | N/A | No variance from Baseline. | Variance from Baseline. As noted above, the State has completed construction of 827 miles of the OCAN route with new underground fiber. | N/A | N/A | No variance from Baseline; however, the project has connected fiber optic cable to 31 CAI's including an additional CAI, Gordon Cooper Technology Center, that was not included in original Baseline projection, and 16 communication huts. | 2 | 4 | 80 | Pioneer Telephone BCI/VYVE Broadband | Please see attached "Q3-2013_PPR_Item 5c_OCAN Pricing Plans" | N/A | 0 | 0 | 2 | 0 | N/A | N/A | Pioneer Telephone and BCI/VYVE Broadband are receiving new access to dark fiber. | The speed tier available is 100MB. | 31 | 4 | 27 | 2 | Variance from Baseline target of 32. 31 Community Anchor Institutions (CAI's) have been connected including Gordon Cooper Technology Center, which was not included in the original Baseline projection. The remaining 2 CAI's are pending IRU closure and completion is anticipated by grant closeout. | Variance from Baseline target of 16. 4 CAI's receiving new access have been connected. Since the original application, weâ€™ve determined that some of the planned CAIs should be considered improved rather than new. We plan to complete all 33 CAI connections, 4 with new access and 29 with improved access, by grant closeout. | Variance from Baseline target of 16. 27 CAI's receiving improved access have been connected. Since the original application, weâ€™ve determined that some of the planned CAIs should be considered improved rather than new. We plan to complete all 33 CAI connections, 4 with new access and 29 with improved access, by grant closeout. | No variance from Baseline - the backbone will be 10GB with two speed tiers available to customers, 100 MBPS and 1 GB. The 32 CAI's included in the grant will be provided 1GB service. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Project complete. | Finance, Oklahoma Office of State | Per the previous submitted AAR for closeout extension, Oklahoma Department of Transportation (ODOT), sub-recipient of the BTOP grant who administered construction for the project, estimated their closeout process to last six months to a year. ODOTâ€™s internal audit process of the twenty-one OCAN construction projects required sixty to ninety days for completion. As each of the twenty-one grant construction projects complete ODOTâ€™S internal audit and closeout, ODOT submits invoices for reimbursement from the grant. | Project complete. | TRUE
NT10BIX5570114 | 2010 | Q4 | Q4 - 2010 | Merit has selected two engineering firms to complete the task of our Network Design. Merits Requests for Proposals (RFP's) was posted on our web site and available to the public. Merit also sent out e-mail notifications to known vendors and organizations. Merit reviewed all RFP's and interviewed several candidates before make its selection. These firms have completed the pre-engineering of the route and are in the process of starting the final engineering. The Environmental Assessment has been moving along as planned and state correspondence has been sent to the multiple agencies as well as permits. Although not all the responses have come back, Merit has received many letters from various organizations at different stages of the process. Merit has been working with several organizations to avoid duplication with other project builds. UW Extension and Eventis are examples of projects Merit is working with to coordinate our builds to reduce costs, accelerate the construction and unltimately utilize the network for our communities. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | None Noted | None Noted | None Noted | None Noted | None Noted | None Noted | None Noted | None Noted | 0 | 0 | 0 | N/A | N/A | It is anticipated that 7 sub-recipients will be participating in this "condo" build. Each sub-recipient will own strands in the build depending on the segment/location of the build. The 7 sub-recipients anticipated to participate are as follows: LYNX Network Group, LLC: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 Ownership: Northeastern Corridor and Middle Corridor KEPS Technologies, Inc. (D.B.A. - ACD.net): Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 Ownership: All Corridors Boardman River Communications, LLC (BRC): Gary John, 1801 Boardman Rd., SW, PO Box 17, , South Boardman, MI, 49680, Phone: 231-369-2500, 231-492-5594 Ownership: Northern Corridor CCI Systems, Inc: Joe Esbrook, 105 Kent Street, Iron Mountain, MI, 48901, Phone: 906-776-2866 Ownership: Northeastern Corridor and Middle Corridor Great Lakes Comnet, Inc (GLC): John Summerset,1515 Turf Lane, Suite 100, East Lansing, MI, 48823, Phone: 517-664-1600 x117 Ownership: All Corridors Peninsula Fiber Network, LLC (PFN): David McCartney, 108 W. Superior, Munising, MI, 49862, Phone: 906-226-2010 Ownership: Northern Corridor Zayo Bandwidth: Essam El-beik, 400 Centennial Parkway, Suite 200, Louisville, CO 80027, Phone: 972-741-5882 Ownership: Middle Corridor | 0 | 0 | 0 | 0 | None Noted | None Noted | None Noted | None Noted | 0 | 0 | 0 | 0 | None Noted | None Noted | None Noted | None Noted | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The most largest accomplishment Merit will have established by the end of next quarter is draft submission of the environmental assessment. Merit will also have completed some of the field engineering as well as started the procurement procedures for equipment, fiber, materials and construction. Considering field engineering will start permitting will start and preparation for construction will get underway. Merit also anticipates the negotiation for the hut sites to be initiated as well as negotiations for the IRU for the Mackinaw Bridge to resume and the purchase of fiber from St. Ignace to Saute St. Marie. Construction will start if the FONSI is awarded before March and the permits are complete. Although construction is unlikely this quarter Merit feels the process will be streamlined enough to build the fiber at a rapid pace if we are able to complete those two big hurdles. | Merit Network Inc. | The primary issue we have had in the Environmental process is getting clearance from state agencies. In the State of Michigan there have been two individuals out of three that have retired from the SHPO offices therefore the agency does not have the capacity to respond to all the inquiries it has been presented in a timely manner. The other challenge we face is the weather conditions across the State of Michigan, Wisconsin, and Minnesota. These conditions make it difficult to perform many duties in the field. | Some challenges we forsee facing is a lack of resources given the vast amount of work in the State. Given that this industry is growing rapidly via the ARRA grants the capacity of engineers, construction companies, suppliers is being restricted. This may make it difficult to secure these important materials and services without paying a higher amounts and having longer lead times than anticipated. Due to Merit's "high" profile project we have not had these issues but we may be seeing the impact in the next quarter or future quarters to come. Permitting will continue to be our number one obstacle consider work will take place in multiple states given that we are unfamiliar with their practices and procedures. Merit has consulted with firms that are familiar with the process and they will be able to assist us in that process. By assisting us in the process this will help us mitigate these permitting issues. Although Merit will be able to catch up on the amount of work this quarter Merit will not be able to procure all the services that it has initially anticipated given the restriction of funds via the Environmental Assessment SAC. We feel Merit will be able to mitigate this issue in future quarters by catching up given that many if not all agreements will be in place. | TRUE
NT10BIX5570114 | 2011 | Q1 | Q1 - 2011 | Merit has submitted the Environmental Assessment and received comments from the NTIA. We are negotiating IRU purchases with the owners of the the Mackinaw Bridge and St. Ignace to Sault Ste. Marie infrastructure. Field engineering has started in the Upper Peninsula, Wisconsin, and Minnesota, and over 100 miles of engineering is complete. Preliminary engineering in the lower peninsula of Michigan is complete. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | N/A | N/A | The projection for interconnection points was dependent upon acquiring leased fiber. Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | 0 | 7 | 0 | None at this time. | No wholesale services are currently being provided. | We anticipate 7 subrecipients will participate in this "condo" build. Each subrecipient will own strands in the build depending on the segment/location of the build. LYNX Network Group, LLC: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 Ownership: Northeastern Corridor and Middle Corridor KEPS Technologies, Inc. (D.B.A. - ACD.net): Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 Ownership: All Corridors Boardman River Communications, LLC (BRC): Gary John, 1801 Boardman Rd., SW, PO Box 17, South Boardman, MI, 49680, Phone: 231-369-2500, 231-492-5594 Ownership: Northern Corridor CCI Systems, Inc: Joe Esbrook, 105 Kent Street, Iron Mountain, MI, 48901, Phone: 906-776-2866 Ownership: Northeastern Corridor and Middle Corridor Great Lakes Comnet, Inc (GLC): John Summerset,1515 Turf Lane, Suite 100, East Lansing, MI, 48823, Phone: 517-664-1600 x117 Ownership: All Corridors Peninsula Fiber Network, LLC (PFN): David McCartney, 108 W. Superior, Munising, MI, 49862, Phone: 906-226-2010 Ownership: Northern Corridor Zayo Bandwidth: Essam El-beik, 400 Centennial Parkway, Suite 200, Louisville, CO 80027, Phone: 972-741-5882 Ownership: Middle Corridor | 0 | 0 | 0 | 0 | The projection for agreements for this quarter was dependent upon acquiring leased fiber. Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | The projection for agreements for this quarter was dependent upon acquiring leased fiber. Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | No variance. | Merit will provide transport services to ISPs at speeds from 10 Mbps to 10 Gbps, including the option to lease dark fiber. We estimate that all providers will connect at a minimum of 1 Gbps. | 0 | 0 | 0 | 0 | No variance. | No variance. | No variance. | No variance. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Responses to the Environmental Assessment comments will be resubmitted with all finished state correspondence, and we hope to receive the Finding of No Significant Impact (FONSI). Construction RFP will be posted early next quarter. Sole source justifications will be submitted to use Round I equipment, fiber and materials vendors for the Round II Project. Construction in certain areas of the Upper Peninsula will start and IRU purchases will be made. Hut site construction will be begin. Field engineering in the Lower Peninsula will begin. | Merit Network Inc. | We have reinitiated correspondence with certain state agencies to allow more flexibility to switch between aerial and underground construction methods throughout Michigan. This was necessary due to slow response from pole owners as well as the extensive time constraints resulting from make-ready work. | Our primary concern is receiving the FONSI and the approval to use a sole source justification in our procurement strategy. The BTOP staff have attended several conference calls and have supported us as we continue to work through environmental issues, but currently our entire project is being held up primarily by our difficulty in obtaining clearances in Wisconsin. The most helpful assistance that the BTOP Program could possibly offer would be revisiting the idea of taking a segmented approach to the EA. If Merit were allowed to proceed with construction in Michigan, significant construction progress could be made while we continue to work with state agencies and tribes in Wisconsin and Minnesota. Given the workload of Round I and Round II grants constraints on resources may slow process. Merit has developed key relationships with its vendors and contractors as well as developing contracts that promote performance and timeliness. | TRUE
NT10BIX5570114 | 2011 | Q2 | Q2 - 2011 | Network fielding is about 90% complete. Over 120 right-of-way permits have been sent to municipalities across the state, and about 50% have been returned. Merit is working through an agreement with Enventis to co-build across the St. Louis Bay. Merit is working with Northeast Service Cooperative to get from the St. Louis Bay to multiple locations in the Duluth, MN area. Merit received all the clearances necessary to submit a final Environmental Assessment. Merit has received a majority of its Davis-Bacon Act wage determinations from the Department of Labor but is awaiting several counties in Wisconsin and Minnesota. Posted a position for Project manager and Environmental Assessor. Merit's revised budget has been approved. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance. | No variance. | No variance. | We are in negotiation with for the proposed leases. | We are in negotiation with for the proposed leases. | N/A | N/A | No variance. | 0 | 0 | 0 | None at this time. | No wholesale services are currently being provided. | We anticipate 7 subrecipients will participate in this "condo" build. Each subrecipient will own strands in the build depending on the segment/location of the build. LYNX Network Group, LLC: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 Ownership: Northeastern Corridor and Middle Corridor KEPS Technologies, Inc. (D.B.A. - ACD.net): Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 Ownership: All Corridors Boardman River Communications, LLC (BRC): Gary John, 1801 Boardman Rd., SW, PO Box 17, South Boardman, MI, 49680, Phone: 231-369-2500, 231-492-5594 Ownership: Northern Corridor CCI Systems, Inc: Joe Esbrook, 105 Kent Street, Iron Mountain, MI, 48901, Phone: 906-776-2866 Ownership: Northeastern Corridor and Middle Corridor Great Lakes Comnet, Inc (GLC): John Summerset,1515 Turf Lane, Suite 100, East Lansing, MI, 48823, Phone: 517-664-1600 x117 Ownership: All Corridors Peninsula Fiber Network, LLC (PFN): David McCartney, 108 W. Superior, Munising, MI, 49862, Phone: 906-226-2010 Ownership: Northern Corridor | 0 | 0 | 0 | 0 | The projection for agreements for this quarter was dependent upon acquiring leased fiber. Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | The projection for agreements for this quarter was dependent upon acquiring leased fiber. Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | No variance. | Merit will provide transport services to service providers at speeds from 10 Mbps to 10 Gbps, including the option to lease dark fiber. We estimate that all providers will connect at a minimum of 1 Gbps. | 0 | 0 | 0 | 0 | No variance. | No variance. | No variance. | No variance. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | The Finding of No Significant Impact will be received and the Enviromental Special Award Condition will be satisfied. About 1000 permits will be submitted by the end of the quarter and many will be completed. Hut sites will be procured and a Request for Proposals will be issued for Hut Construction. Merit will begin aerial and underground construction. If Merit's sole source requests are approved, materials and fiber will be procured, and a Request for Proposals will be issued for switch/router equipment. | Merit Network Inc. | We struggled for several months to work through communication difficulties with Federally recognized tribes, but we were able to develop a plan and we are currently working out a maintenance agreement. Weather conditions in the Upper Peninsula and Northern Lower Peninsula have made it difficult to complete full engineering and therefore it has taken multiple trips to verify information. To obtain clearance in Wisconsin, Merit was required to do shovel testing at hut site locations during the time of the year when the ground was not frozen. Weather has been the biggest challenge at this point but is clearing up and engineering is progressing quickly. Completion of the engineering and completion of the Finding of No Significant Impact has hindered our ability to complete permits. Michigan Department of Transportation permit submission has been delayed due to Finding of No Significant Impact approval; the Michigan Department of Transportation relies on the Finding of No Significant Impact to expedite the permit through the environmental review on their end therefore, will only process the permits once the Finding of No Significant Impact is in place. | Our progress is largely dependent on receiving the Finding of No Significant Impact; the sooner we are able to begin construction, the more progress we will make in the next quarter. Certain materials have been in short supply and long lead times are anticipated; however, when compliance requirements allow, we will place bulk orders for fiber and materials for the entire network build and set up a facility for storage to ensure all necessary supplies are on hand. | TRUE
NT10BIX5570114 | 2011 | Q3 | Q3 - 2011 | All known permits for Round 2 have been submitted. Merit made the decision to conduct more underground construction using Michigan Department of Transportation right-of-way roads for Round 2. We have completed 95% of the engineering needed for the Upper Peninsula portion of the project and submitted 60% of the Michigan Department of Transportation permits necessary. Merit has released and closed the RFP for hut construction in the Upper Peninsula and have purchased approximately 90% of the fiber and 80% of all other materials such as conduit. We have selected the construction contractors for Round 2, worked on our waterway crossing with Enventis, completed our Mackinaw Bridge Authority agreement, undergone our A-133 Audit and an NTIA site visit, and completed work on our Davis Bacon Act wage determinations. The sole source Award Action Request for conduit was approved. Merit secured a warehouse facility for improved logistics. Merit hired a Project Manager and an Environmental Compliance Manager. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Delays in some of our milestone categories has resulted in a delay in lighting fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | No variance. | No variance. | We are in negotiations for the proposed leases. | We are in negotiations for the proposed leases. | N/A | N/A | Delays in some of our milestone categories has resulted in a delay in lighting fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | 0 | 0 | 0 | None at this time. | No wholesale services are currently being provided. | We anticipate 7 subrecipients will participate in this "condo" build. Each subrecipient will own strands in the build depending on the segment/location of the build. LYNX Network Group, LLC: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 Ownership: Northeastern Corridor and Middle Corridor KEPS Technologies, Inc. (D.B.A. - ACD.net): Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 Ownership: All Corridors Boardman River Communications, LLC (BRC): Gary John, 1801 Boardman Rd., SW, PO Box 17, South Boardman, MI, 49680, Phone: 231-369-2500, 231-492-5594 Ownership: Northern Corridor CCI Systems, Inc: Joe Esbrook, 105 Kent Street, Iron Mountain, MI, 48901, Phone: 906-776-2866 Ownership: Northeastern Corridor and Middle Corridor Great Lakes Comnet, Inc (GLC): John Summerset,1515 Turf Lane, Suite 100, East Lansing, MI, 48823, Phone: 517-664-1600 x117 Ownership: All Corridors Peninsula Fiber Network, LLC (PFN): David McCartney, 108 W. Superior, Munising, MI, 49862, Phone: 906-226-2010 Ownership: Northern Corridor | 0 | 0 | 0 | 0 | The projection for agreements for this quarter was dependent upon acquiring leased fiber. Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | The projection for agreements for this quarter was dependent upon acquiring leased fiber. Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | No variance. | The projection for agreements for this quarter was dependent upon acquiring leased fiber. Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | 0 | 0 | 0 | 0 | Delays in some of our milestone categories has resulted in a delay in lighting fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | Delays in some of our milestone categories has resulted in a delay in lighting fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | Delays in some of our milestone categories has resulted in a delay in lighting fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | Delays in some of our milestone categories has resulted in a delay in lighting fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | We anticipate wrapping up main line engineering and beginning construction. We will select vendors for hut construction, and begin to procure optical equipment. Our Finding of No Significant Impact was received approximately two quarters later than we had projected, so many of our key indicators are also two quarters behind, including new network miles deployed (updated projection: 0), network miles leased (updated projection: 54), and new interconnection points (updated projection: 4). We anticipate having 6 of the 7 projected agreements with broadband wholesalers in place by the end of the next quarter. | Merit Network Inc. | Completion of the engineering and the receipt of the Finding of No Significant Impacts has allowed us to submit permit applications with the Michigan Department of Transportation so we are just starting to receive approved Right of Way permits for Round 2. Engineering is progressing quickly due to improved weather conditions in both the Lower and Upper Peninsulas, which has allowed us to complete the route however delays in receiving environmental permit approval has hindered our ability to begin construction. | Completion of the engineering and the receipt of the Finding of No Significant Impacts has allowed us to submit permit applications with the Michigan Department of Transportation so we are just starting to receive approved Right of Way permits for Round 2. We have also applied and received the majority of the Metro Act permits but still see significant work ahead to ensure all small municipalities are represented with an applicable permit. Since the field engineering has been completed, we are waiting to receive the appropriate drawings and prints from our engineering firm so as to apply for necessary permits. However, delays with attaining our environmental permits have hindered our ability to start construction in many places. | TRUE
NT10BIX5570114 | 2011 | Q4 | Q4 - 2011 | An agreement with BTOP recipient Enventis was negotiated and signed, and the Duluth conduit installation was completed. Merit continues to work with Allband, a BIP recipient with overlapping segments in Northeast Michigan; a construction agreement was signed. Merit worked with the Bad River Tribe, located in northern Wisconsin, to develop a maintenance agreement, which was signed and approved by the tribe council. The survey required by the Bureau of Indian Affairs in the Bad River reservation area was completed. Merit submitted an AAR request for our new Network Operations Director to replace our former Network Operations Director, who was listed as a key person on Meritâ€™s grant application. Merit completed our A-133 audit, which revealed no instances of noncompliance; there were no Federal Program findings. Construction vendors were interviewed, and finalists were selected. Our Central Office RFP and Hut RFP both closed, responses were evaluated, and the finalists were interviewed, and the selections were made. Our project manager met with a large utility that was non-responsive to permit applications, and was able to obtain approvals for outstanding permit requests. Merit completed the Key Project Indicator (KPI) report requested by the NTIA. Five of six Round 2 contracts were signed by subrecipients. Construction began in the Upper Peninsula in Houghton County. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Delays in some of our milestone categories has resulted in a delay in lighting fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | No variance. | No variance. | No variance. | Delays in some of our milestone categories has resulted in a delay in lighting fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | N/A | N/A | N/A | 5 | 0 | 80 | LYNX Network Group, LLC KEPS Technologies, Inc. (D.B.A. - ACD.net) Boardman River Communications, LLC (BRC) CCI Systems, Inc Peninsula Fiber Network, LLC (PFN) | No wholesale services are currently being provided. | We anticipate subrecipients will participate in this "condo" build. Each subrecipient will own strands in the build depending on the segment/location of the build. LYNX Network Group, LLC: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 Ownership: Northeastern Corridor and Middle Corridor KEPS Technologies, Inc. (D.B.A. - ACD.net): Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 Ownership: All Corridors Boardman River Communications, LLC (BRC): Gary John, 1801 Boardman Rd., SW, PO Box 17, South Boardman, MI, 49680, Phone: 231-369-2500, 231-492-5594 Ownership: Northern Corridor CCI Systems, Inc: Joe Esbrook, 105 Kent Street, Iron Mountain, MI, 48901, Phone: 906-776-2866 Ownership: Northeastern Corridor and Middle Corridor Peninsula Fiber Network, LLC (PFN): David McCartney, 108 W. Superior, Munising, MI, 49862, Phone: 906-226-2010 Ownership: Northern Corridor | 0 | 0 | 0 | 0 | The projection for agreements for this quarter was dependent upon acquiring leased fiber. Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | The projection for agreements for this quarter was dependent upon acquiring leased fiber. Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | No variance | The projection for agreements for this quarter was dependent upon acquiring leased fiber. Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | 0 | 0 | 0 | 0 | Delays in some of our milestone categories has resulted in a delay in lighting fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | Delays in some of our milestone categories has resulted in a delay in lighting fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | Delays in some of our milestone categories has resulted in a delay in lighting fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | Delays in some of our milestone categories has resulted in a delay in lighting fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Merit anticipates construction moving into full swing. We will select vendors for hut construction, continue to procure optical equipment, and begin to procure switches and routers. Our Finding of No Significant Impact was received approximately two quarters later than we had projected, so many of our key indicators are also two quarters behind. We anticipate making up this difference by the second quarter of 2012, but our projections for next quarter are as follows: - 7 new network miles deployed - 56 network miles leased - 1 community anchor institution subscriber served - 6 agreements with broadband wholesalers and/or last mile providers | Merit Network Inc. | We have not experienced any challenges or issues leading to delays unique to this quarter. The length of time it has taken to get our Finding of No Significant Impact and get environmental permits continues to impact the project, but we do anticipate making up for lost time during the second and third quarters in 2012. | We do not project encountering any challenges or issues leading to delays unique to this quarter, with the exception of possible weather delays. The length of time it has taken to get our Finding of No Significant Impact and get environmental permits continues to impact the project, but we do anticipate making up for lost time during the second and third quarters in 2012. | TRUE
NT10BIX5570114 | 2012 | Q1 | Q1 - 2012 | The joint conduit installation for Enventis Telecom (a BTOP recipient) and Merit Network in Duluth, MN was completed and accepted. Construction crews worked in the Northeastern, Middle, and Upper Peninsula regions of the Project. Merit reached a maintenance agreement with the Bad River Tribe regarding the REACH-3MCII project passing through Tribal lands. Capital Communications was selected through Merit's RFP process to complete Central Office work for the project. Merit purchased 41 miles of infrastructure from St. Ignance to Sault Ste. Marie. All 6 Subrecipient Agreements have been signed for the REACH-3MCII award. All fiber has been ordered for the project. Merit has received permits from the Michigan Department of Environmental Quality (MDEQ) for Kalkaska, Missaukee, Wexford, Osceola, and Lake counties. Merit received its Huron National Forest Permit for Alcona, Iosco, Ogemaw, Oscoda, and Crawford counties. Merit has also received several wetland permits. | 11 | 0 | 65 | 0 | 76 | 0 | 0 | 0 | Delays in some of our milestone categories has resulted in a delay in installing fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | No variance. | Merit purchased existing fiber along the planned route. | No variance. | Delays in some of our milestone categories has resulted in a delay in installing fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | N/A | N/A | N/A | 6 | 0 | 80 | LYNX Network Group, LLC KEPS Technologies, Inc. (D.B.A. - ACD.net) Boardman River Communications, LLC (BRC) CCI Systems, Inc Peninsula Fiber Network, LLC (PFN) Great Lakes Comnet | No wholesale services are currently being provided. | We anticipate subrecipients will participate in this "condo" build. Each subrecipient will own strands in the build depending on the segment/location of the build. LYNX Network Group, LLC: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 Ownership: Northeastern Corridor and Middle Corridor KEPS Technologies, Inc. (D.B.A. - ACD.net): Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 Ownership: All Corridors Boardman River Communications, LLC (BRC): Gary John, 1801 Boardman Rd., SW, PO Box 17, South Boardman, MI, 49680, Phone: 231-369-2500, 231-492-5594 Ownership: Northern Corridor CCI Systems, Inc: Joe Esbrook, 105 Kent Street, Iron Mountain, MI, 48901, Phone: 906-776-2866 Ownership: Northeastern Corridor and Middle Corridor Peninsula Fiber Network, LLC (PFN): David McCartney, 108 W. Superior, Munising, MI, 49862, Phone: 906-226-2010 Ownership: Northern Corridor Great Lakes Comnet: Bill Goodfellow, 1515 Turf Lane, Suite 100, East Lansing, MI 48823, Phone:517-664-1600 Ownership:North Eastern, Middle, and North Corridor | 0 | 0 | 0 | 0 | The projection for agreements for this quarter was dependent upon acquiring leased fiber. Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | The projection for agreements for this quarter was dependent upon acquiring leased fiber. Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | No variance | The projection for agreements for this quarter was dependent upon acquiring leased fiber. Negotiations for leased fiber are taking longer than anticipated; we are currently having productive conversations, and anticipate being on schedule by next quarter. | 1 | 0 | 1 | 0 | Although there was one subrecipient connected to the BTOP-funded network in Q1 2012, broadband service was not being provided during that quarter. | Delays in some of our milestone categories has resulted in a delay in lighting fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | Delays in some of our milestone categories has resulted in a delay in lighting fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | Although the subrecipient is connected to the BTOP-funded network, broadband service was not being provided this quarter. Merit anticipates delivering 1 Gbps service during the second quarter of 2012. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Merit anticipates the number of construction crews working and the number of segments where construction is underway to increase. Merit will obtain remaining easements for hut placements, and finalize the hut contract. Merit looks to obtaining all remaining wetlands and forest use permits. Merit looks to obtain outstanding right of way permits from the Bad River Tribe. - Estimated number of miles planned for deployment during the next quarter: 15 - Estimated number of CAIs planned or connection during the next quarter: 3 - Number of agreements with broadband wholesaler/last mile providers: 7 | Merit Network Inc. | The length of time it has taken to get the Finding of No Significant Impact and get permits continues to impact the project, but Merit does anticipate making up time during the second and third quarters in 2012. Merit is still working to obtain pole permits and complete make ready prior to construction. Construction was slowed January-March due to weather in northern Michigan, but Merit anticipates an increase in the amount of construction performed during the summer months. Merit is working to obtaining the remaining Right of Way permits from the Bad River Indian Tribe, by making frequent visits with the tribe and working closely with the BIA. | We do not project encountering any challenges or issues leading to delays unique to this quarter, with the exception of possible weather delays. The length of time it has taken to get our Finding of No Significant Impact and get environmental permits continues to impact the project, but we do anticipate gaining ground during the second and third quarters in 2012 and beyond. | TRUE
NT10BIX5570114 | 2012 | Q2 | Q2 - 2012 | Merit has finalized all remaining easements for the project, including all hut easements. Ground preparation is underway at the hut sites. Merit has installed fiber in the Enventis build area under the St. Louis Bay in Duluth, MN as part of a joint build with Enventis, a BTOP recipient. Merit received their Ottawa National Forest and Hiawatha National Forest Permits. Merit also received all Department of Environmental Quality (DEQ) permits. Property appraisals were conducted for easements at the Bad River Tribe site. Merit connected Round 1 fiber (another BTOP-funded project) to Round 2 fiber at the Mackinaw Bridge. Merit completed procurement for Huts and selected a contractor to place the huts at their final destination. Merit connected Forest Park Schools (Community Anchor Institution) and began servicing them in May 2012. Merit has begun prep work for additional Community Anchor Institution sites. Merit has completed route planning engineering work for the project. Merit formed an environmental inspection team to review/finalize documentation and inspect sites pre/post construction to ensure environmental compliance during the build. | 78 | 0 | 77 | 0 | 78 | 0 | 0 | 0 | Delays in some of our milestone categories has resulted in a delay in installing fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | No Variance | Merit purchased existing fiber along the planned route. | No Variance | Delays in some of our milestone categories has resulted in a delay in installing fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | N/A | N/A | N/A | 6 | 0 | 80 | LYNX Network Group, LLC KEPS Technologies, Inc. (D.B.A. - ACD.net) -(Signed contract as of June 30, 2012, will drop off project in following quarter) Boardman River Communications, LLC (BRC) CCI Systems, Inc Peninsula Fiber Network, LLC (PFN) Great Lakes Comnet | No wholesale services are currently being provided. | We anticipate subrecipients will participate in this "condo" build. Each subrecipient will own strands in the build depending on the segment/location of the build. LYNX Network Group, LLC: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 Ownership: Northeastern Corridor and Middle Corridor KEPS Technologies, Inc. (D.B.A. - ACD.net): Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 Ownership: All Corridors ( ACD has a signed contract with Merit at the time this quarter ended. They will be dropping off the project next quarter) Boardman River Communications, LLC (BRC): Gary John, 1801 Boardman Rd., SW, PO Box 17, South Boardman, MI, 49680, Phone: 231-369-2500, 231-492-5594 Ownership: Northern Corridor CCI Systems, Inc: Joe Esbrook, 105 Kent Street, Iron Mountain, MI, 48901, Phone: 906-776-2866 Ownership: Northeastern Corridor and Middle Corridor Peninsula Fiber Network, LLC (PFN): David McCartney, 108 W. Superior, Munising, MI, 49862, Phone: 906-226-2010 Ownership: Northern Corridor Great Lakes Comnet: Bill Goodfellow, 1515 Turf Lane, Suite 100, East Lansing, MI 48823, Phone:517-664-1600 Ownership:North Eastern, Middle, and North Corridor | 0 | 0 | 0 | 0 | The projection for agreements for this quarter was dependent upon acquiring leased fiber; agreements are in place, but no access is being provided at this time. Merit anticipates coming in line with our baseline over the next two quarters. | The projection for agreements for this quarter was dependent upon acquiring leased fiber; agreements are in place, but no access is being provided at this time. Merit anticipates coming in line with our baseline over the next two quarters. | No variance | The projection for agreements for this quarter was dependent upon acquiring leased fiber; agreements are in place, but no access is being provided at this time. Merit anticipates coming in line with our baseline over the next two quarters. | 1 | 0 | 1 | 1 | Delays in some of our milestone categories has resulted in a delay in installing fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | Delays in some of our milestone categories has resulted in a delay in installing fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | Delays in some of our milestone categories has resulted in a delay in installing fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | Delays in some of our milestone categories has resulted in a delay in installing fiber; however, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Merit anticipates obtaining remaining environmental and wetlands permits at the Bad River Tribe site as well as easements along the route with the Tribe. Merit anticipates having telecom huts placed in Escanaba, Powers, and Iron Mountain. Merit is hoping to have a significant amount of new infrastructure installed along the Upper Peninsula. Merit anticipates completing and lighting fiber from Oscoda to Harrisville as well as Gaylord to Mackinaw City. Merit plans to have all CAI permits submitted by the end of the quarter as well as all sites in some phase of construction (excluding the sites pending NTIA approval for changes). Merit will focus on overall construction and environmental compliance over the next quarter. - Network miles expected to be deployed next quarter: 250 - Merit anticipates connecting 20 CAI sites during the next quarter assuming the backbone fiber is in place for the sites to be connected to. - Agreements in place with Broadband/Last mile providers: Merit currently has six agreements in place, and anticipates one additional. -ACD.net will be dropping off of the project during Q3 2012 and will be reflected as removed in the subsequent reports. | Merit Network Inc. | The length of time it has taken to get the Finding of No Significant Impact and get permits continues to impact the project, but Merit has increased the pace of construction to make up time during the second and third quarters in 2012. Merit anticipates having a large portion of infrastructure completed before the weather changes later this year. Merit is still working to obtain pole permits and complete make ready prior to construction. Merit is working to obtaining the remaining Right of Way permits and easements from the Bad River Indian Tribe, by making frequent visits with the tribe and working closely with the BIA. Merit is working to obtain outstanding Wisconsin environmental permits so work can be completed on this portion of the project. | Merit will be working to resolve outstanding environmental permits in Wisconsin but this should not result in significant delays to this quarter. Merit does not project encountering any other significant challenges leading to delays in the coming quarter. the length of time it has taken to get our Finding of No Significant Impact and get environmental permits continues to impact hte project, but we do anticipate to continue making up ground in the third quarter of 2012 and beyond. | TRUE
NT10BIX5570114 | 2012 | Q3 | Q3 - 2012 | Merit has received all outstanding forestry and Michigan Department of Environmental Quality permits for this project. Merit is making continued progress with construction, averaging 35-40 miles of completed infrastructure construction per week. Fiber will be blown through once the infrastructure is completed. Merit submitted an Award Action Request to remove some Community Anchor Institutions and replace with more committed Community Anchor Institution sites. The request was approved. Merit has all easements approved for hut location sites for the project. | 209 | 0 | 77 | 0 | 209 | 0 | 0 | 0 | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. Strand miles completed through Q3 2012: 39 Miles (includes purchased infrastructure) Conduit miles completed through Q3 2012: 654 Miles (includes purchased infrastructure) | No Variance | Merit purchased existing fiber along the planned route. | No Variance | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | N/A | N/A | N/A | 6 | 0 | 80 | LYNX Network Group, LLC KEPS Technologies, Inc. (D.B.A. - ACD.net) -(Signed contract as of June 30, 2012, will drop off project in following quarter) Boardman River Communications, LLC (BRC) CCI Systems, Inc Peninsula Fiber Network, LLC (PFN) Great Lakes Comnet | No wholesale services are currently being provided. | We anticipate sub recipients will participate in this "condo" build. Each sub recipient will own strands in the build depending on the segment/location of the build. LYNX Network Group, LLC: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 Ownership: Northeastern Corridor and Middle Corridor KEPS Technologies, Inc. (D.B.A. - ACD.net): Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 Ownership: All Corridors ( ACD has a signed contract with Merit at the time this quarter ended. They will be dropping off the project next quarter) Boardman River Communications, LLC (BRC): Gary John, 1801 Boardman Rd., SW, PO Box 17, South Boardman, MI, 49680, Phone: 231-369-2500, 231-492-5594 Ownership: Northern Corridor CCI Systems, Inc: Joe Esbrook, 105 Kent Street, Iron Mountain, MI, 48901, Phone: 906-776-2866 Ownership: Northeastern Corridor and Middle Corridor Peninsula Fiber Network, LLC (PFN): David McCartney, 108 W. Superior, Munising, MI, 49862, Phone: 906-226-2010 Ownership: Northern Corridor Great Lakes Comnet: Bill Goodfellow, 1515 Turf Lane, Suite 100, East Lansing, MI 48823, Phone:517-664-1600 Ownership:North Eastern, Middle, and North Corridor | 0 | 0 | 0 | 0 | The projection for agreements for this quarter was dependent upon acquiring leased fiber. At this time agreements are in place, but no access is being granted. Merit anticipates aligning with our Baseline in the following quarters. | The projection for agreements for this quarter was dependent upon acquiring leased fiber. At this time agreements are in place, but no access is being granted. Merit anticipates aligning with our Baseline in the following quarters. | No Variance | The projection for agreements for this quarter was dependent upon acquiring leased fiber. At this time agreements are in place, but no access is being granted. Merit anticipates aligning with our Baseline in the following quarters. | 4 | 0 | 4 | 1 | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | 1 CAI is served at 1 Gbps; the remaining CAIs did not subscribe to service during the reporting quarter. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE |  | Merit will continue with construction at an aggressive pace before winter weather sets in and slows or halts progress. Merit expects to complete equipment procurement during the following quarter. In addition, Merit will have at least one (1) fiber hut placed in Escanaba, Michigan and hopes to place additional huts in the fourth quarter. Merit anticipates being able to connect additional Community Anchor Institution sites once main line construction is completed in the area, including fifteen (15) Community Anchor Institution sites during the fourth quarter of 2012 with five (5) of those receiving service during that time period. Additional estimated miles to deploy for Q4 2012 Strand: 15 Conduit: 115 Total Miles with Fiber: 150 Merit does not anticipate signing any broadband/wholesaler last mile agreements during the reporting quarter. | Merit Network Inc. | During the second and third quarters of 2012 Merit has accelerated the pace of construction to make up for delays caused by permits and the Finding of No Significant Impact. Merit anticipates having a large increase in the pace of construction. Management of the large quantity of field construction crews has been challenging. Merit conducts weekly status meetings to gather updates regarding: the progress of the crews, to plan for the coming weeks, and to identify and resolve any build obstructions. Merit is still working to receive all approvals and clearances in Wisconsin before construction can begin. Merit is working with the appropriate parties to expedite the process so construction will not be further delayed. | Merit will continue to work on resolution of approval issues in Wisconsin but this should not result in significant delays to this quarter. The weather will begin to be a factor as winter gets closer. Merit will be working to get as much infrastructure and construction completed before the weather impacts the build. Merit does not expect to encounter any other significant delay challenges in the coming quarter. The length of time it took to get the Finding of No Significant Impact and environmental permits continues to impact the projectâ€™s schedule; however, we anticipate making up this time in the fourth quarter of 2012 and beyond. | TRUE
NT10BIX5570114 | 2012 | Q4 | Q4 - 2012 | Merit has accelerated the pace of construction, which is in full swing to ensure as much build as possible is completed before weather prohibits further efforts. Merit began splicing in some areas where fiber installation was completed. Over 90% of our right of way and utility permits have been submitted and approved, and Merit made great progress working with Native American Tribes in Wisconsin. | 336 | 0 | 77 | 0 | 336 | 0 | 0 | 0 | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. Strand miles completed through Q4 2012: 53 Miles (includes purchased infrastructure) Conduit miles completed through Q4 2012: 769 Miles (includes purchased infrastructure) | No variance | Merit purchased existing fiber along the planned route. | No variance | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | N/A | N/A | N/A | 6 | 0 | 80 | LYNX Network Group, LLC KEPS Technologies, Inc. (D.B.A. - ACD.net) -(Signed contract as of June 30, 2012, will drop off project) Boardman River Communications, LLC (BRC) CCI Systems, Inc Peninsula Fiber Network, LLC (PFN) Great Lakes Comnet | No wholesale services are currently being provided. | We anticipate sub recipients will participate in this "condo" build. Each sub recipient will own strands in the build depending on the segment/location of the build. LYNX Network Group, LLC: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 Ownership: Northeastern Corridor and Middle Corridor KEPS Technologies, Inc. (D.B.A. - ACD.net): Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 Ownership: All Corridors ( ACD has a signed contract with Merit at the time this quarter ended. They will be dropping off the project next quarter) Boardman River Communications, LLC (BRC): Gary John, 1801 Boardman Rd., SW, PO Box 17, South Boardman, MI, 49680, Phone: 231-369-2500, 231-492-5594 Ownership: Northern Corridor CCI Systems, Inc: Joe Esbrook, 105 Kent Street, Iron Mountain, MI, 48901, Phone: 906-776-2866 Ownership: Northeastern Corridor and Middle Corridor Peninsula Fiber Network, LLC (PFN): David McCartney, 108 W. Superior, Munising, MI, 49862, Phone: 906-226-2010 Ownership: Northern Corridor Great Lakes Comnet: Bill Goodfellow, 1515 Turf Lane, Suite 100, East Lansing, MI 48823, Phone:517-664-1600 Ownership:North Eastern, Middle, and North Corridor | 0 | 0 | 6 | 0 | N/A | N/A | Merit is providing dark fiber to wholesale providers who will in turn offer last mile services | Speed tiers that are available will be dependant on what the equipment of the wholesale providers are using. | 72 | 14 | 58 | 1 | Many CAI sites have been completed but are awaiting the backbone fiber to pass by, or have been completed and connected but will not receive service until following quarters. | Will be recieving new access due to the REACH-3MCII project. | All CAI sites that have been connected will be receiving improved access thanks to the REACH-3MCII project. | All 72 are receiving a 1GB connection | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Merit will continue construction at an aggressive pace over Q1 of 2013 to install as much infrastructure as possible. Merit expects to complete equipment procurement in the coming quarter. In addition, Merit will have additional huts placed along the REACH-3MCII route. Merit anticipates being able to connect additional Community Anchor Institution sites once main line construction is completed in the area. Miles deployed in the next quarter-150 miles of infrastructure with 50 miles of fiber placed CAI's connected in the next quarter-5 *Miles deployed will determined by the weather the construction crews encounter in the next quarter | Merit Network Inc. | During previous quarters of 2012, Merit has accelerated the pace of construction to make up for delays caused by permits and the Finding of No Significant Impact. Merit anticipates continuing construction at a rapid pace. Management of the large quantity of field construction crews has been challenging. Merit conducts weekly status meetings to gather updates regarding: the progress of the crews, to plan for the coming weeks, and to identify and resolve any build obstructions. Merit is working with the appropriate parties to expedite the process so construction will not be further delayed. | Merit will be working to get as much infrastructure and construction completed during the next quarter. Merit does not expect to encounter any other significant delay challenges in the coming quarter assuming weather cooperates and does not limit construction. The length of time it took to get the Finding of No Significant Impact and environmental permits continues to impact the projectâ€™s schedule; however, we anticipate making up this time in the remaining quarters. | TRUE
NT10BIX5570114 | 2013 | Q1 | Q1 - 2013 | Merit completed construction from Gaylord, MI to Mackinaw, MI. Construction was also completed from Norway, MI to Iron Mountain, MI. Merit continues to work on the transition of Boardman River to ATI Networks, Inc. Merit also began work on a route change in the St. Ignace area. A significant accomplishment was connecting the Upper and Lower Peninsulas of Michigan via fiber across the Mackinac Bridge. | 497 | 0 | 77 | 0 | 497 | 0 | 0 | 0 | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. Strand miles completed through Q1 2013: 79 Miles (includes purchased infrastructure) Conduit miles completed through Q1 2013: 833 Miles (includes purchased infrastructure) | No Variance | Merit purchased existing fiber along the planned route. | No variance | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | N/A | N/A | N/A | 6 | 0 | 80 | LYNX Network Group, LLC KEPS Technologies, Inc. (D.B.A. - ACD.net) -(Signed contract as of June 30, 2012, will drop off project) Boardman River Communications, LLC (BRC) CCI Systems, Inc Peninsula Fiber Network, LLC (PFN) Great Lakes Comnet | No wholesale services are currently being provided. | Each sub recipient will own strands in the build depending on the segment/location of the build. LYNX Network Group, LLC: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 Ownership: Northeastern Corridor and Middle Corridor KEPS Technologies, Inc. (D.B.A. - ACD.net): Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 Ownership: All Corridors ( ACD had a signed contract with Merit. They will be dropping off the project) Boardman River Communications, LLC (BRC): Gary John, 1801 Boardman Rd., SW, PO Box 17, South Boardman, MI, 49680, Phone: 231-369-2500, 231-492-5594 Ownership: Northern Corridor CCI Systems, Inc: Joe Esbrook, 105 Kent Street, Iron Mountain, MI, 48901, Phone: 906-776-2866 Ownership: Northeastern Corridor and Middle Corridor Peninsula Fiber Network, LLC (PFN): David McCartney, 108 W. Superior, Munising, MI, 49862, Phone: 906-226-2010 Ownership: Northern Corridor Great Lakes Comnet: Bill Goodfellow, 1515 Turf Lane, Suite 100, East Lansing, MI 48823, Phone:517-664-1600 Ownership:North Eastern, Middle, and North Corridor | 0 | 0 | 6 | 0 | N/A | N/A | Merit is providing dark fiber to wholesale providers who will in turn offer last mile services | There are no Merit-defined speed tiers available to the current subscribers because they are all project subrecipients who will be creating their own speed tiers based on the equipment they independently install to light their fiber strands. | 91 | 33 | 58 | 1 | CAI sites that are connected with BTOP funded infrastructure. | Will be receiving new access due to the REACH-3MCII project. | All CAI sites that have been connected will be receiving improved access thanks to the REACH-3MCII project. | All 91 are receiving a 1GB connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Merit anticipates increasing construction activity in all segments in the upper and lower peninsula and get as much infrastructure and fiber installed as possible. Merit will look to obtain final approval of construction in the Bad River Tribe and begin construction in that area. However, project progress is still subject to weather constraints. Miles deployed in the next quarter - 50 CAI's connected in the next quarter - 5 Number of broadband wholesaler/last mile provider agreements you plan to sign through the end of next quarter -0 *Miles deployed will determined by the weather the construction crews encounter in the next quarter | Merit Network Inc. | Weather has been the biggest challenge facing the project over the last quarter. The northern lower peninsula and the upper peninsula have received large amounts of snow which has greatly slowed construction on the network build. | Merit will be working towards completing the infrastructure build in the coming quarter. Merit is targeting to have construction resumed in full force by May 1st. Weather has had a significant impact on construction in 2013 as heavy snow has limited construction. The upper peninsula still has significant snowfall on the ground and that will dictate when construction will resume. Merit has targeted May 1 as a date to resume work in all areas to stay on the construction schedule. Merit will also be working to obtain finial approval of construction in the Bad River Tribe. Merit will be working carefully around environmental sensitive areas in Wisconsin which can impact the construction time line. Merit will also be working to obtain final permits from pole owners along the route and the time that it takes to complete this could impact the construction schedule. | TRUE
NT10BIX5570114 | 2013 | Q2 | Q2 - 2013 | Construction on network infrastructure continued at a rapid pace once the winter weather cleared. Merit began construction in the Bad River Tribe area where the network infrastructure will be passing through. Merit, along with its contractors, placed all huts on their respective sites. Merit has completed work across many Central Office locations and worked to connect community anchor sites to the main fiber line. | 707 | 0 | 64 | 0 | 707 | 0 | 0 | 0 | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. Strand miles completed through Q2 2013: 103 Miles (includes purchased infrastructure) Conduit miles completed through Q2 2013: 1093 Miles (includes purchased infrastructure) | No Variance | Merit purchased existing fiber along the planned route. | No variance | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | N/A | N/A | N/A | 6 | 0 | 80 | LYNX Network Group, LLC KEPS Technologies, Inc. (D.B.A. - ACD.net) -(Signed contract as of June 30, 2012, will drop off project) Boardman River Communications, LLC (BRC) CCI Systems, Inc Peninsula Fiber Network, LLC (PFN) Great Lakes Comnet | No wholesale services are currently being provided. | Each sub recipient will own strands in the build depending on the segment/location of the build. LYNX Network Group, LLC: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 Ownership: Northeastern Corridor and Middle Corridor KEPS Technologies, Inc. (D.B.A. - ACD.net): Kevin Schoen, 1800 N Grand River Ave Lansing, MI 48906, Phone: 877.422.3638 Ownership: All Corridors ( ACD had a signed contract with Merit. They will be dropping off the project) Boardman River Communications, LLC (BRC): Gary John, 1801 Boardman Rd., SW, PO Box 17, South Boardman, MI, 49680, Phone: 231-369-2500, 231-492-5594 Ownership: Northern Corridor CCI Systems, Inc: Joe Esbrook, 105 Kent Street, Iron Mountain, MI, 48901, Phone: 906-776-2866 Ownership: Northeastern Corridor and Middle Corridor Peninsula Fiber Network, LLC (PFN): David McCartney, 108 W. Superior, Munising, MI, 49862, Phone: 906-226-2010 Ownership: Northern Corridor Great Lakes Comnet: Bill Goodfellow, 1515 Turf Lane, Suite 100, East Lansing, MI 48823, Phone:517-664-1600 Ownership:North Eastern, Middle, and North Corridor | 0 | 0 | 6 | 0 | N/A | N/A | Merit is providing dark fiber to wholesale providers who will in turn offer last mile services | There are no Merit-defined speed tiers available to the current subscribers because they are all project subrecipients who will be creating their own speed tiers based on the equipment they independently install to light their fiber strands. | 106 | 48 | 58 | 1 | CAI sites that are connected with BTOP funded infrastructure. | Will be receiving new access due to the REACH-3MCII project. | All CAI sites that have been connected will be receiving improved access thanks to the REACH-3MCII project. | All 106 are receiving a 1GB connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | In the next quarter, Merit anticipates completing lower peninsula construction as well as upper peninsula fiber. Merit will be looking to begin testing fiber in the lower peninsula and if possible, the upper peninsula. Merit will start any warranty work that is needed to repair issues that are discovered while testing. Merit will be looking to light any remaining anchors who have not been fully connected to the network. Merit plans to apply for a no cost extension to extend the performance period of the award to ensure the completion of the project. Merit is not currently planning a budget modification for the REACH-3MCII project. Estimated number of miles to be deployed during the quarter: 250 Estimated number of CAI's to be connected during the quarter:15 Estimated number of Broadband wholesaler/last mile provider agreements to be signed during the quarter: 0 | Merit Network Inc. | Weather slowed construction progress earlier in the quarter as snow continued to accumulate. Merit contractors also encountered many areas of hard, underground rock which slowed construction. As a result, contractors have had to dispatch workers and equipment to different areas, stretching resources which lead to a slower pace for construction than expected. Merit has also ran into some difficulties with aerial permits in hard rock areas, but Merit is working with the appropriate parties to resolve any permitting issues. | Rock Bore construction could continue to be an issue over the remaining areas of construction, but Merit will work with the contractors to generate a strategy to reduce construction time line impact. Merit will be working with municipalities and any other parties that are still needed to issue permits for the construction to take place. Merit will be working with the contractors to make sure construction work is completed in Green Bay as easily as possible. | TRUE
NT10BIX5570114 | 2013 | Q3 | Q3 - 2013 | Merit received a no cost extension to complete the REACH-3MCII project. Merit is nearly complete with all remaining infrastructure construction, with an estimated 99.7% of infrastructure completed. All lower peninsula fiber infrastructure was completed. Merit has lit all fiber within Michigan. Construction was completed in the Bad River Tribe area of the project, including completed restoration and clean up work. Merit has all Huts placed, activated, and lit. | 1235 | 0 | 64 | 0 | 1235 | 0 | 0 | 0 | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. Strand miles completed through Q3 2013: 116 Miles (includes purchased infrastructure) Conduit miles completed through Q3 2013: 1119 Miles (includes purchased infrastructure) | No Variance | Merit purchased existing fiber along the planned route. | No variance | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, once construction is fully underway we anticipate closing the gap between our Baseline Report and the reported totals. | N/A | N/A | N/A | 5 | 0 | 80 | LYNX Network Group, LLC Boardman River Communications, LLC (BRC) CCI Systems, Inc Peninsula Fiber Network, LLC (PFN) Great Lakes Comnet KEPS Technologies, Inc. (D.B.A. - ACD.net) - Has officially dropped off of the project. Their portion of the network will be taken over by Merit, Peninsula Fiber Network, and Great Lakes Comnet | No wholesale services are currently being provided. | Each sub recipient will own strands in the build depending on the segment/location of the build. LYNX Network Group, LLC: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 Ownership: Northeastern Corridor and Middle Corridor Boardman River Communications, LLC (BRC): Gary John, 1801 Boardman Rd., SW, PO Box 17, South Boardman, MI, 49680, Phone: 231-369-2500, 231-492-5594 Ownership: Northern Corridor CCI Systems, Inc: Joe Esbrook, 105 Kent Street, Iron Mountain, MI, 48901, Phone: 906-776-2866 Ownership: Northeastern Corridor and Middle Corridor Peninsula Fiber Network, LLC (PFN): David McCartney, 108 W. Superior, Munising, MI, 49862, Phone: 906-226-2010 Ownership: Northern Corridor Great Lakes Comnet: Bill Goodfellow, 1515 Turf Lane, Suite 100, East Lansing, MI 48823, Phone:517-664-1600 Ownership:North Eastern, Middle, and North Corridor | 0 | 0 | 5 | 0 | N/A | N/A | Merit is providing dark fiber to wholesale providers who will in turn offer last mile services. KEPS Technologies (ACD.net) has dropped off of the project. Their portion of the project will be taken over by Merit, Peninsula Fiber Network, and Great Lakes Comnet. | There are no Merit-defined speed tiers available to the current subscribers because they are all project subrecipients who will be creating their own speed tiers based on the equipment they independently install to light their fiber strands. | 133 | 75 | 58 | 1 | CAI sites that are connected with BTOP funded infrastructure. | Will be receiving new access due to the REACH-3MCII project. | All CAI sites that have been connected will be receiving improved access thanks to the REACH-3MCII project. | All 133 are receiving a 1GB connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Merit anticipates completing remaining construction on the project. Merit also anticipates being able to continue working on testing throughout the network. Merit will look to begin warranty work on any areas of the new infrastructure that will require repair. Merit will look to light any remaining community anchor sites. Merit will be receiving As-Built drawings for the infrastructure and will begin preparing for closeout once complete. Estimated number of miles to be deployed during the quarter: 2 Estimated number of CAI's to be connected during the quarter:11 Estimated number of Broadband wholesaler/last mile provider agreements to be signed during the quarter: 0 | Merit Network Inc. | Merit has encountered obstacles during the construction process in prior quarters where Merit contractors encountered many areas of hard, underground rock which slowed construction. As a result, contractors have had to dispatch workers and equipment to different areas, stretching resources which lead to a slower pace for construction than expected. Merit has also ran into some difficulties with aerial permits in hard rock areas, but Merit worked with with the appropriate parties to resolve any permitting issues. Merit encountered an issue when the I-43 bridge had shifted in the mud which disrupted Merit's fiber location along the bridge. Merit worked with the appropriate parties to minimize impact on the project. | Weather could impact project testing over the next quarter as winter weather nears. Merit could face challenges in completing the As-Built drawings but anticpates working through any issues that may occur. Getting fiber testing and accepted could be a challenge as well but Merit should be able to work through any issues with the appropriate parties. | TRUE
NT10BIX5570114 | 2013 | Q4 | Q4 - 2013 | Bad River Tribe work is complete,including restoration, and has been connected to the network. Merit has completed almost all infrastructure, with only a few miles remaining. All Telecom huts are energized and testing is taking place. Merit has continued restoration and testing across the network as weather permits. | 1236 | 0 | 64 | 0 | 1236 | 0 | 0 | 0 | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, construction is near complete | No Variance | Merit purchased existing fiber along the planned route. | No variance | Delays in some of our milestone categories have resulted in holdups in fiber installation. However, construction is near complete | N/A | N/A | N/A | 5 | 0 | 80 | LYNX Network Group, LLC Boardman River Communications, LLC (BRC) CCI Systems, Inc Peninsula Fiber Network, LLC (PFN) Great Lakes Comnet | No wholesale services are currently being provided. | Each sub recipient will own strands in the build depending on the segment/location of the build. LYNX Network Group, LLC: Chris Barber, PO Box 237 Kalamazoo, MI 49004, Phone: 877.585.5969 Ownership: Northeastern Corridor and Middle Corridor Boardman River Communications, LLC (BRC): Gary John, 1801 Boardman Rd., SW, PO Box 17, South Boardman, MI, 49680, Phone: 231-369-2500, 231-492-5594 Ownership: Northern Corridor CCI Systems, Inc: Joe Esbrook, 105 Kent Street, Iron Mountain, MI, 48901, Phone: 906-776-2866 Ownership: Northeastern Corridor and Middle Corridor Peninsula Fiber Network, LLC (PFN): David McCartney, 108 W. Superior, Munising, MI, 49862, Phone: 906-226-2010 Ownership: Northern Corridor Great Lakes Comnet: Bill Goodfellow, 1515 Turf Lane, Suite 100, East Lansing, MI 48823, Phone:517-664-1600 Ownership:North Eastern, Middle, and North Corridor | 0 | 0 | 5 | 0 | N/A | N/A | Merit is providing dark fiber to wholesale providers who will in turn offer last mile services. | There are no Merit-defined speed tiers available to the current subscribers because they are all project subrecipients who will be creating their own speed tiers based on the equipment they independently install to light their fiber strands. | 136 | 76 | 60 | 1 | CAI sites that are connected with BTOP funded infrastructure. | Will be receiving new access due to the REACH-3MCII project. | All CAI sites that have been connected will be receiving improved access thanks to the REACH-3MCII project. | All 134 are receiving a 1GB connection. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Merit anticipates completing remaining construction on the project. Merit also anticipates being able to continue working on testing throughout the network. Merit will look to begin warranty work on any areas of the new infrastructure that will require repair. Merit will look to light any remaining community anchor sites. Merit will be receiving As-Built drawings for the infrastructure and will begin preparing for closeout once complete. Estimated number of miles to be deployed during the quarter: 1 Estimated number of CAIs to be connected during the quarter:12 Estimated number of Broadband wholesaler/last mile provider agreements to be signed during the quarter: 0 | Merit Network Inc. | Weather has delayed the completion of the infrastructure build. Merit anticipates being able to complete the construction near the end of 2014 Q1 or early Q2 when the weather clears. Merit encountered an issue when the I-43 bridge had shifted in the mud which disrupted Merit's fiber location along the bridge. Merit worked with the appropriate parties to re-route the fiber and minimize the impact on the project. | Weather could impact completing construction and testing of the network. Merit will be working with appropriate parties to complete and receive As-Built drawings. Merit also plans to submit a rebudget request to ensure that all expenses are properly aligned against 424C and project milestone categories. | TRUE
NT10BIX5570115 | 2010 | Q4 | Q4 - 2010 | This quarter was largely occupied with our environmental assessment. We had several meetings with various state and federal departments responsible for environmental impact and regulations, all with good results. We also held open house meetings in each of our four demonstrations communities to solicit any environmental concerns; no concerns were raised in any of those meetings. This quarter we worked on submissions to National Telecommunications and Information Administration with our baseline reports and 6 month budget. We also submitted a proposal for addressing overlap among three different Broadband Technologies Opportunities Program grants in the Superior area per a request from our Program Officer. Permitting and engineering has started for the long haul fiber routes. The wireless project in Chippewa Valley has also completed it's spectrum analysis to study coverage and ensure no conflicts with neighboring signals. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Network build has not started. | na | Network build has not started. | na | Network build has not started. | Network build has not started. | Network build has not started. | Network build has not started. | 0 | 3 | 0 | na | na | na | 0 | 0 | 0 | 0 | Network build has not started. | Network build has not started. | Network build has not started. | Network build has not started. | 0 | 0 | 0 | 0 | Network build has not started. | Network build has not started. | Network build has not started. | Network build has not started. | 0 | 0 | 0 | 0 | 0 | Network build has not started. | Network build has not started. | Network build has not started. | Network build has not started. | Network build has not started. | 0 | 0 | 0 | 0 | 0 | Network build has not started. | Network build has not started. | Network build has not started. | Network build has not started. | Network build has not started. | No special offerings have been provided. | FALSE | na | Next quarter we expect to begin drawing funds. Our final baseline will be submitted and we expect to have all Special Award Conditions met, including any potential overlap situations with other BTOP or BIP projects. The environmental assessment will be submitted to National Telecommunications and Information Administration and, assuming a Finding of No Significant Impact, we will be able to begin buying equipment and hiring additional people to assist with the project. The Chippewa Valley wireless project will proceed with tower site zoning and geotechnical preparations and also conduct a procurement for the WiMAX equipment. If the weather does not cause delays, we also hope to begin fiber installation by the end of this quarter (pending National Telecommunications and Information Adminitration report of Finding Of No Significant Impact.) | University of Wisconsin System | na | na | TRUE
NT10BIX5570115 | 2011 | Q1 | Q1 - 2011 | During this quarter several significant activities have taken place to assist us in completing the Building Community Capacity through Broadband initiative in a timely fashion. The environmental assessment was completed and submitted to the National Telecommunications and Information Administration on January 27, 2011. The firm of Short Elliott Hendrickson Inc. led the environmental assessment process and during the quarter helped us continue providing information in each of the demonstration communities: Wausau, Platteville, Superior and the Chippewa Valley Region. In addition, the firm contacted all of the necessary parties to inform them of our effort and ensure compliance, and we had meetings with Wisconsin departments of Natural Resources and Transportation. Statewide and local demonstration community partners continued monthly strategic planning meetings during the quarter. The meetings helped everyone remain focused on project goals, grant deadlines, and collectively create processes for communications and data collection to jumpstart community efforts. Individual demonstration communities were also active within their communities during this quarter. Communities reviewed routes for the environmental assessment and continued planning sessions to identify issues and strategies to deal with those issues. Our private partner and sub-recipient, CCI Systems continued conversations with third party providers. We also executed the sub-contract with CCI Systems for the p | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Network build has not started- pending Finding of No Significant Impact. | na | Network build has not started- pending Finding of No Significant Impact. | na | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) Network build has not started- pending Finding of No Significant Impact. Network build has not started- pending Finding of No Significant Impact. Network build has not started- pending Finding of No Significant Impact. Network build has not started- pending Finding of No Significant Impact. Network build has not started- pending Finding of No Significant Impact. Network build has not started- pending Finding of No Significant Impacts for any variance from the baseline plan or any other relevant information) Network build has not started- pending Finding of No Significant Impact. Network build has not started- pending Finding of No Significant Impact. Network build has not started- pending Finding of No Significant Impact. Network build has not started- pending Finding of No Significant Impact. Network build has not started- pending Finding of No Significant Impact. Network build has not started- pending Finding of No Significant Impact. | 0 | 3 | 0 | na | na | na | 0 | 0 | 0 | 0 | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | 0 | 0 | 0 | 0 | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | 0 | 0 | 0 | 0 | 0 | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | 0 | 0 | 0 | 0 | 0 | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | Network build has not started- pending Finding of No Significant Impact. | No special offerings have been provided. | FALSE | na | At this time we are still waiting for the environmental assessment Finding of No Significant Impact before we can start our project in full. The delay in the Finding of No Significant Impact currently has our project behind schedule by five weeks. Once we get the Finding of No Significant Impact and can proceed with the project, we expect to assign additional construction crews to get us back on schedule. Availability of such crews has been confirmed. We expect to have a significant start on installation of the long haul fiber and begin installation in all four communities. The wireless services pilot for public safety and education institutions will also begin in this quarter. Procurement and hiring processes are already underway and should be concluded in this quarter with vendor selection, contracts and job offers. Some of these costs were contained in the 6 month budget, such as the first order of fiber optic cable, but most will wait until the Finding of No Significant Impact is in hand. Permitting and engineering work has been proceeding as planned and should continue through the quarter so that fiber installation may begin as soon as possible after the Finding of No Significant Impact is delivered. | University of Wisconsin System | Our biggest hurdle is clearly the delay in the Finding of No Significant Impact as the programmatic agreement is being finalized between the Wisconsin State Historic Preservation Officer, the National Telecommunications and Information Administration, the University of Wisconsin Extension and the Ho Chunk Nation. Despite the dedicated efforts of many, this continues to be a slow process that threatens to put us significantly behind schedule. | We have also learned that lead times for fiber have lengthened considerably due to worldwide delays caused by the earthquake in Japan. To mitigate potential delays in fiber delivery, we have decided to install conduit throughout the entire project. Conduit installation may begin immediately and we can then pull in the fiber at a later date when it becomes available, including winter months when new installation would otherwise be halted. | TRUE
NT10BIX5570115 | 2011 | Q2 | Q2 - 2011 | During this quarter several significant activities have taken place to assist us in completing the Building Community Capacity through Broadband initiative in a timely fashion. Permitting and architectural design has continued throughout the quarter. Permits for two counties and approximately 50 miles of state roads have been received to date. Construction has begun between Wausau and Summit Lake. The Finding of No Significant Impact required to address environmental assessment was received end of May. Immediately after receipt, materials were ordered and construction began during the quarter. At the end of the reporting quarter additional project manager positions were hired in the Chippewa Valley and Superior communities. Network build started in June of 2011 on the long haul fiber path. Materials procurement, notably fiber and conduit, was completed and awarded to a Wisconsin based company. This contract has fixed prices and delivery schedule to support our build timeline and budget. In this quarter, the Chippewa Valley community network build contract was awarded, with installation scheduled to begin in July, 2011. The procurement for the Superior community network was finalized this quarter with award expected in August and installation to be completed by December, 2011. Tower builds in the Chippewa Valley community started this quarter with the first tower at the Chippewa County Courthouse. Much of our community outreach is conducted through a separate Sustain | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | na | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | na | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. Network build started last week in June - delay was pending receipt of Finding of No Significant Impactk in June - delay was pending receipt of Finding of No Significant Impact. Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | 0 | 4 | 0 | na | na | na | 0 | 0 | 0 | 0 | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | 0 | 0 | 0 | 0 | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | 0 | 0 | 0 | 0 | 0 | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | 0 | 0 | 0 | 0 | 0 | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | Network build started last week in June - delay was pending receipt of Finding of No Significant Impact. | No special offerings have been provided. | FALSE | na | In the July - September, 2011 quarter we expect to be substantially underway on the long haul conduit installation, starting in the Northeast portion of the project at Summit Lake and moving toward Wausau. Construction will also begin on the long haul between Wausau and Eau Claire. Delivery of the fiber optic cable is expected near the end of the quarter and pulling that cable into the conduit may begin immediately. Progress within the four communities for this quarter will likely include the following: Chippewa Valley will start conduit installation in the Eau Claire city area with fiber added as it becomes available; Superior issued a construction bid and expects to award a winner in August with initial phases of installation starting shortly afterwards; Wausau will release a construction bid with expected awards within the quarter. Platteville will start their procurement process for construction to start early 2012. The tower construction at the Chippewa County courthouse location will be completed this quarter. A bid for the remaining eleven towers in Chippewa Valley will be prepared and released. The first electronics orders for the long haul and some of the communities is also expected in this quarter. | University of Wisconsin System | The lead times for fiber delivery vary considerably. To mitigate these delays, we are installing conduit throughout the entire project. While conduit installation has started, the fiber will be installed at a later date when it becomes available, including winter months when new installation would otherwise be halted. A provision was introduced in the State budget that proposed disallowing University of Wisconsin-Extension from receiving funds from National Telecommunications and Information Administration for the Building Community Capacity through Broadband effort. Statewide and community partners mobilized, resulting in a compromise that allowed the two grants received from National Telecommunications and Information Administration to continue. | Nationwide delivery delays for fiber continue, therefore our plan to initially install conduit only, followed by fiber when it becomes available will also continue. Some evidence of price increases for both conduit and fiber has also been observed, but the material prices for the vast majority of our project have already been locked in as a result of a procurements awarded last quarter. While our overall time line has been somewhat condensed due to previously discussed delays, we are confident of completion within designated project time frame. There is no need for further assistance from the National Telecommunications and Information Administration at this time. | TRUE
NT10BIX5570115 | 2011 | Q3 | Q3 - 2011 | During this quarter several significant activities have taken place to assist us in completing the Building Community Capacity through Broadband initiative in a timely fashion. Permitting and architectural design has continued throughout the quarter. Construction on the long haul has begun in the areas between Wausau and Summit Lake, Wausau to Stevens Point, Stevens Point to Eau Claire, Eau Claire to Superior, and Platteville to Madison. Construction within the Chippewa Valley and Superior community area networks started this quarter. A total of 158 miles of conduit has been installed with fiber to be installed next quarter when it is delivered. One tower was built in the Chippewa Valley. Permits and engineering will stay ahead of construction and will not delay the project. Approximately $2 million in equipment orders were placed. The revised network build schedule indicates we are still on target to meet construction completion by the end of the grant period. Recruitment for a project manager position in the Wausau community area network is still underway. Wausau community procurement activities are still pending for construction to begin next quarter. Platteville community procurement activities are still pending for construction to begin next year. The remaining towers to be constructed in Chippewa Valley will be contracted with a bid to be released in the next quarter. Build is complete through one of the two identified environmentally sensitive areas with no | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery is also subject to manufacturing delays. We are currently installing conduit only in anticipation of quicker fiber install once fiber delivery begins late next quarter. | na | See explanation for new miles deployed above. | na | See explanation for new miles deployed above. | See explanation for new miles deployed above. | Delayed receipt of Finding of No Significant Impact delayed procurement action. We anticipate completion of procurement process and build of remaining towers to be completed by December 2012. | See explanation for new miles deployed aboved above. | 0 | 2 | 0 | na | na | na | 0 | 0 | 0 | 0 | Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery is also subject to manufacturing delays. We are currently installing conduit only in anticipation of quicker fiber install once fiber delivery begins late next quarter. | See above | See above | See above | 0 | 0 | 0 | 0 | Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery is also subject to manufacturing delays. We are currently installing conduit only in anticipation of quicker fiber install once fiber delivery begins next quarter. | See above | See above | See above | 0 | 0 | 0 | 0 | 0 | Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery is also subject to manufacturing delays. We are currently installing conduit only in anticipation of quicker fiber install once fiber delivery begins late next quarter. | See above | See above | See above | See above | 0 | 0 | 0 | 0 | 0 | Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery is also subject to manufacturing delays. We are currently installing conduit only in anticipation of quicker fiber install once fiber delivery begins late next quarter. | See above | See above | See above | See above | No special offerings have been provided. | FALSE |  | In the October to December 2011 quarter we anticipate continuing the installation of conduit in each of the communities and the connections between the communities. For the Chippewa Valley community we anticipate completing fiber installation, equipment installation and testing to connect 12 community anchor institutions. We plan to start fiber installation near the Wausau and Platteville communities. As long haul equipment is received, we will begin installation with testing to occur late in the quarter. Procurement activities for this quarter include bid release and contract awards for 11 towers in Chippewa Falls and network build in Wausau and Platteville for construction to begin early 2012. The first wireless services will go live in Chippewa Valley this quarter. Projected indicators for this quarter: New network miles: 15-20 miles. Total Community Anchor Institution Subscribers connected: 10-15. Signed agreements for broadband providers or last mile providers: 1. | University of Wisconsin System | The above build is installation of conduit only. We expect initial fiber delivery late next quarter. We will continue conduit installation until frost stops installation and then continue with fiber installation as needed through the winter months. | Our biggest concern in this quarter is the possibility of an early freeze that would halt conduit and direct-bury fiber installation earlier than planned. | TRUE
NT10BIX5570115 | 2011 | Q4 | Q4 - 2011 | During this quarter several significant activities have taken place to assist us in completing the Building Community Capacity through Broadband initiative in a timely fashion. Throughout the project 265 miles of conduit have been installed. Permitting and architectural design has continued throughout the quarter. Construction on the long haul continued in the areas between Wausau and Summit Lake, Wausau to Stevens Point, Stevens Point to Eau Claire, Eau Claire to Superior, and Platteville to Madison. The first shipment of fiber arrived at the end of the quarter. Installation of long haul equipment has begun. Construction within the Chippewa Valley continued this quarter. For the Chippewa Valley, 35 miles of new fiber have been installed to date. Fiber splicing electronics installation and testing should start soon. In Chippewa Valley one tower has been constructed to date. The remaining eleven towers will be constructed in 2012 through a bid process currently under development. Initial WiMAX pilot installation activity is underway, connecting our first group of community anchor institutions. Wausau and Platteville community procurement activities are in progress. Expectations are that procurement will be finalized next quarter with construction to be completed in 2012. We are still on target to meet construction completion by the end of the grant period. Much of our community outreach is conducted through a separate Sustainable Broadband Adoption grant. Notable highlights include continuing to conduct webinars focusing on rural communities and e-commerce. A series of six video case studies were released to the general public as part of our community outreach. A total of 16.17 jobs were created this quarter. Most of the jobs were crews for network construction. | 35 | 0 | 0 | 0 | 35 | 0 | 1 | 0 | Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery is also subject to manufacturing delays. We are currently installing conduit only in anticipation of fiber install once fiber delivery begins this winter. | NA | See explanation for new miles deployed above. | NA | See explanation for new miles deployed above. | See explanation for new miles deployed above. | Delayed receipt of Finding of No Significant Impact delayed procurement action. We anticipate completion of procurement process and build of remaining towers to be completed by December 2012. | See explanation for new miles deployed above. | 0 | 2 | 0 | NA | NA | The following subrecipients will be operating a portion of the network as indicated below: Packerland Broadband, (800) 236-8434 in Iron Mountain MI, for long haul, wholesale and last mile providers, WiscNet, (608) 265- 6761 in Madison WI, for the long haul connections, CESA 10, (715) 723-0341 in Chippewa Falls, for the Community Area Network in the Chippewa Valley, Northcentral Technical College, (715) 675-3331 in Wausau, for the Wausau Community Area Network, University of Wisconsin-Platteville, (608) 342-1491 in Platteville, for the Platteville Community Area Network, and University of Wisconsin-Superior, (715) 394-8101 in Superior, for the Superior Community Area Network. | 0 | 0 | 0 | 0 | Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery is also subject to manufacturing delays. We are currently installing conduit only in anticipation of fiber install once fiber delivery begins this winter. | See above. | See above. | See above. | 5 | 5 | 0 | 10 | Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery is also subject to manufacturing delays. We are currently installing conduit only in anticipation of fiber install once fiber delivery begins this winter. | See above. | See above. | Speed tiers include 5 subscribers at 10 Mb. | 0 | 0 | 0 | 0 | 0 | Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery is also subject to manufacturing delays. We are currently installing conduit only in anticipation of fiber install once fiber delivery begins this winter. | See above. | See above. | See above. | See above. | 0 | 0 | 0 | 0 | 0 | Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery is also subject to manufacturing delays. We are currently installing conduit only in anticipation of fiber install once fiber delivery begins this winter. | See above. | See above. | See above. | See above. | No special offerings have been provided. | FALSE | A copy of our network management policies can be found on our Web site at http://broadband.uwex.edu | Construction on the long haul as well as the Chippewa Valley community will continue. Focus will be on fiber installation into already installed conduit, splicing, and equipment ordering and installation. Conduit installation in Superior is complete. Fiber installation will occur summer of 2012 depending on fiber delivery and scheduling a contractor installation crew. The Wausau and Platteville community procurements for fiber installation will be finalized with contracts awarded and fiber orders placed as soon as possible. Procurement documents will be released for construction of remaining eleven towers in the Chippewa Valley. Key project indicators for this quarter (cumulative): New network miles: 150 Total Community Anchor Institutions: 35 Signed agreements for broadband or last mile providers: 1 | University of Wisconsin System | Although we had initial concerns about fiber shortages, fiber delivery took place as planned. We focused on conduit installation until frost stopped installation. Another focus was final remaining procurement activities in Wausau and Platteville. External pressure from telecommunication companies continued during the quarter resulting in numerous communications but no delays to the project. | Our biggest concern in this quarter is the possibility of delays in spring thaw and the resultant delays in conduit and direct-bury fiber installation. We will also monitor fiber delivery schedules and procurement activities in Wausau and Platteville to mitigate impact of delays. | TRUE
NT10BIX5570115 | 2012 | Q1 | Q1 - 2012 | During this quarter several significant activities have taken place to assist us in completing the Building Community Capacity through Broadband initiative in a timely fashion. Permitting and architectural design has continued throughout the quarter. As anticipated, little construction took place with less than a quarter mile of conduit laid during this quarter. Instead, concentration was placed on strengthening our procedures to ensure proper permitting to comply with all environmental requirements going forward. To date, 226 miles (50%) of conduit and 3 miles of fiber have been installed in the areas between Wausau and Summit Lake, Wausau to Stevens Point, Stevens Point to Eau Claire, Eau Claire to Superior, and Platteville to Madison. Fiber shipments have been occurring as scheduled throughout the quarter. Installation of long haul electronic equipment has begun. For the Chippewa Valley, a total of 32 miles of conduit only and an additional 35 miles of fiber has been installed to date. Fiber splicing, electronics installation and testing has begun with three additional Community Anchor Institutions connected this quarter. In Chippewa Valley one tower has been constructed to date. The remaining eleven towers will be constructed in 2012 through a bid process currently under development. For the Wausau and Platteville communities, construction vendors have been selected and engineering is underway. Expectations are that construction will be completed in 2012. Superior has seen no activity this quarter. We are still on target to meet construction completion by the end of the grant period. Much of our community outreach is conducted through a separate Sustainable Broadband Adoption grant. Notable highlights include continuing to conduct webinars focusing on rural communities and e-commerce. A series of six video case studies were released to the general public as part of our community outreach. No jobs were created this quarter. | 38 | 0 | 0 | 0 | 38 | 35 | 1 | 0 | Baseline has 310 miles. Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery also had manufacturing delays. Installation of fiber should begin in earnest starting in April 2012 with actual expenditures occurring shortly afterwards. | NA | See explanation for new miles deployed above. | NA | See explanation for new miles deployed above. | Baseline has 70 links. See explanation for new miles deployed above. | Baseline has 6 towers. Delayed receipt of Finding of No Significant Impact delayed procurement action. We anticipate completion of procurement process and build of remaining towers to be completed by December 2012. | See explanation for new miles deployed above. | 1 | 2 | 12 | We have a signed agreement with Packerland Broadband as subrecipient. | As subrecipient, Packerland Broadband will receive access to dark fiber. Packerland Broadband will provide wholesale services to third party providers. Pricing plans for those services are not yet available. | The following subrecipients will be operating a portion of the network as indicated below: Packerland Broadband, (800) 236-8434 in Iron Mountain MI, for long haul, wholesale and last mile providers, WiscNet, (608) 265- 6761 in Madison WI, for the long haul connections, Chippewa Valley Inter-Networking Consortium, (715) 723-0341, for the Chippewa Valley area, Northcentral Technical College, (715) 675-3331 in Wausau, for the Wausau Community Area Network, Platteville Community Area Network, (608) 342-1491, for the Platteville area, and University of Wisconsin-Superior, (715) 394-8101 in Superior, for the Superior Community Area Network. | 0 | 0 | 1 | 0 | Baseline has 1 provider. Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery also had manufacturing delays. Installation of fiber should begin in earnest starting in April 2012 with actual expenditures occurring shortly afterwards. | See explanation above. | Baseline has 5 providers. See explanation above. | See explanation above. | 8 | 6 | 2 | 1000 | Baseline has 96 institutions. Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery also had manufacturing delays. Installation of fiber should begin in earnest starting in April 2012 with actual expenditures occurring shortly afterwards. | See explanation above. | See explanation above. | Speed tiers include 5 subscribers at 10 Mb and 3 subscribers at 1 Gb. | 0 | 0 | 0 | 0 | 0 | Baseline is 3,098 entities passed - all in last mile service areas. Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery also had manufacturing delays. Installation of fiber should begin in earnest starting in April 2012 with actual expenditures occurring shortly afterwards. | See explanation above. | See explanation above. | See explanation above. | See explanation above. | 0 | 0 | 0 | 0 | 0 | Baseline is 550 entities passed - all in last mile service areas. Delayed receipt of Finding of No Significant Impact delayed the start of network build. Fiber delivery also had manufacturing delays. Installation of fiber should begin in earnest starting in April 2012 with actual expenditures occurring shortly afterwards. | See explanation above. | See explanation above. | See explanation above. | See explanation above. | No special offerings have been provided. | FALSE | A copy of our network management policies can be found on our Web site at http:/broadband.uwex.edu. | For the April - June 2012 quarter, construction of the network will continue in earnest. The long haul and Chippewa Valley will have installation of fiber optic cable, splicing and installation of electronic equipment. Chippewa Valley will continue connecting Community Anchor Institutions and obtain permitting for tower construction. For Platteville and Wausau communities, focus will be on completing the engineering and design phase of construction as well as all required permitting. We anticipate fiber installation in Superior will begin late in the quarter. Key project performance indicators for this quarter (cumulative): New network miles installed: 165 Total Community Anchor Institutions connected: 35 Signed agreements for broadband or last mile providers: 2 | University of Wisconsin System | Progress on procurements and construction for the remaining towers, Wausau community network, and Platteville community network is behind schedule. The final procurement activities in Wausau and Platteville communities have occurred so construction should be underway next quarter. The procurement activities for the remaining eleven towers in Chippewa Valley are being finalized so construction should be underway next quarter. Given the large scale of construction, we have been working closely with multiple areas of the Wisconsin Department of Natural Resources to ensure compliance with all environmental requirements. This effort has been time-consuming for all parties. As stated earlier, we anticipate adding additional construction crews to ensure completion of fiber installation by the end of 2012. | The primary challenge that may impact planned progress this quarter will be obtaining all necessary permits to keep construction crews fully engaged. We are working closely with all required permitting agencies to expedite processing and approval. Approvals for route changes will be needed during this quarter to address right-of-way issues and rocky conditions in portions of the project. Approval of these changes will allow us to remain within budget and on schedule. Additional impact includes one more community anchor institution and one more point of interconnect. | TRUE
NT10BIX5570115 | 2012 | Q2 | Q2 - 2012 | During this quarter several significant activities have taken place to assist us in completing the Building Community Capacity through Broadband initiative in a timely fashion. Permitting and architectural design has continued throughout the quarter. Construction has resumed throughout the State. During the quarter we had delays in construction in selected areas pending receipt of various permits. To date, 61 miles of fiber have been installed in the areas between Wausau and Summit Lake, Wausau to Stevens Point, Stevens Point to Eau Claire, Eau Claire to Superior, and Platteville to Madison. We have received 95% of our fiber shipment. Remaining shipment is due next quarter. For the Chippewa Valley, a total of 51 miles of fiber has been installed to date. Fiber splicing, electronics installation and testing continue with 18 Community Anchor Institutions connected thus far. In Chippewa Valley one tower has been constructed at this time. The remaining eleven towers will be constructed in 2012 with the procurement process currently underway. For the Platteville community, construction contracts have been executed and engineering has been completed. Construction just started at the end of the June. Expectations are that construction will be completed in 2012. For the Wausau community, construction contracts have been executed and engineering is underway. Expectations are that construction will be completed in 2012. For the Superior community, no activities occurred this quarter. Conduit installation was completed in 2011 and fiber installation is scheduled for next quarter. We are still on target to meet construction completion by the end of the grant period. Much of our community outreach is conducted through a separate Sustainable Broadband Adoption grant. Notable highlights include discussions to develop a sustainability plan for the network after the grant ends. No jobs were created this quarter. | 112 | 0 | 0 | 0 | 112 | 35 | 1 | 0 | Baseline has 417 miles. Delayed receipt of Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting further delayed construction. | NA | See explanation for new miles deployed above. | NA | See explanation for new miles deployed above. | Baseline has 80 links. See explanation for new miles deployed above. | Baseline has 6 towers. Delayed receipt of Finding of No Significant Impact delayed procurement action. We anticipate completion of procurement process and build of remaining towers to be completed by December 2012. | See explanation for new miles deployed above. | 1 | 2 | 12 | We have a signed agreement with Packerland Broadband as subrecipient. | As subrecipient, Packerland Broadband will receive access to dark fiber. Packerland Broadband will provide wholesale services to third party providers. Specific pricing plans for those services are not yet available. | The following subrecipients will be operating a portion of the network as indicated below: Packerland Broadband, (800) 236-8434 in Iron Mountain MI, for long haul, wholesale and last mile providers, WiscNet, (608) 265- 6761 in Madison WI, for the long haul connections, Chippewa Valley Inter-Networking Consortium, (715) 723-0341, for the Chippewa Valley area, Northcentral Technical College, (715) 675-3331 in Wausau, for the Wausau Community Area Network, Platteville Community Area Network, (608) 342-1491, for the Platteville area, and University of Wisconsin-Superior, (715) 394-8101 in Superior, for the Superior Community Area Network. | 0 | 0 | 1 | 0 | Baseline has 1 provider. Delayed receipt of Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting further delayed construction. | See explanation above. | Baseline has 7 providers. See explanation above. | See explanation above. | 18 | 15 | 3 | 1000 | Baseline has 110 providers. Delayed receipt of Finding of No Significant Impact delayed the start of network build. The extensive review for environmental permitting further delayed construction. | See explanation above. | See explanation above. | All subscribers are at 1 Gb | 0 | 0 | 0 | 0 | 0 | Baseline has 3,098 entities passed - all in last mile service areas. Delayed receipt of Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting further delayed construction. | See explanation above. | See explanation above. | See explanation above. | See explanation above. | 0 | 0 | 0 | 0 | 0 | Baseline has 550 entities passed - all in last mile service areas. Delayed receipt of Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting further delayed construction. | See explanation above. | See explanation above. | See explanation above. | See explanation above. | No special offerings have been provided. | FALSE | A copy of our network management policies can be found on our Web site at http:/broadband.uwex.edu. | For the July - September 2012 quarter, construction of the network will continue, pending negotiations with NTIA and U.S. Fish and Wildlife Service regarding the Karner Blue Butterfly. In the long haul and Chippewa Valley community, installation of fiber optic cable, splicing and installation of electronic equipment will continue. Chippewa Valley will continue connecting Community Anchor Institutions and obtain permits for tower construction. The Platteville community will continue building and should complete fiber installation in 2012. The Wausau communities will focus on completing the engineering and design phase of construction, obtaining required permits and beginning construction of the network with expected completion of fiber installation in 2012. We anticipate fiber installation in Superior will occur late in the third quarter. Key project performance indicators for this quarter (cumulative): New network miles installed: 175 Total Community Anchor Institutions connected: 38 Signed agreements for broadband or last mile providers: 2 | University of Wisconsin System | Progress for procurement of the remaining eleven towers continued through this quarter. Local zoning permissions have been a challenge for two of the eleven remaining towers, thereby delaying procurement for tower construction. Tower construction should begin next quarter. Given the large scale of construction, we continued to work closely with multiple areas of the Wisconsin Department of Natural Resources to ensure compliance with all environmental requirements. The final permit was issued July 3, 2012. | Following the completion of negotiations with NTIA and U.S. Fish and Wildlife Service regarding the Karner Blue Butterfly, our biggest challenge will be to resume construction with enough crews to complete planned fiber installation before construction cannot take place due to winter weather. The schedule now shows about one third of construction will need to take place in 2013. Starting this quarter, we plan to have extra crews working on the project to ensure completion within the grant period. With extra crews, we should be able to complete construction on time barring an unusually long winter. The issues will continue to be the availability of construction crews and obtaining the necessary permissions in a timely manner. Zoning challenges for towers in Chippewa Valley community will likely continue this quarter. | TRUE
NT10BIX5570115 | 2012 | Q3 | Q3 - 2012 | During this quarter several significant activities have taken place to assist us in completing the Building Community Capacity through Broadband initiative in a timely fashion. Construction has resumed throughout the State except for Eau Claire and Clark counties. During the quarter we had delays in construction in selected areas pending resolution of environmental issues. For the overall project, a total of 175 fiber miles have been installed to date. Detail follows. To date, 84 miles of fiber have been installed in the areas between Wausau and Summit Lake, Wausau to Stevens Point, Stevens Point to Eau Claire, Eau Claire to Superior, and Platteville to Madison. For the Chippewa Valley, a total of 88 miles of fiber has been installed to date. Fiber splicing, electronics installation and testing continue with 28 Community Anchor Institutions connected thus far. In Chippewa Valley one tower has been constructed at this time. Construction contracts have been executed for three towers with construction to start in the next quarter. Procurement steps are in final stages for the remaining eight towers with construction to start next quarter but not finish until next construction year. For Platteville, a total of 3 miles of fiber has been installed to date. For Wausau, construction is just underway. For Superior, no activities occurred this quarter. Expectations are that all construction for these three communities will be completed in 2012. We are still on target to meet construction completion by the end of the grant period. Much of our community outreach is conducted through a separate Sustainable Broadband Adoption grant. Notable highlights include continuing discussions to develop a sustainability plan for the network after the grant ends and continuation of outreach and educational programming throughout the summer and into fall. No new jobs were created this quarter. | 175 | 0 | 0 | 0 | 175 | 35 | 1 | 0 | Baseline plan has 492. Delayed receipt of Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting has continued to delay construction. | NA | See explanation for new miles deployed above. | NA | See explanation for new miles deployed above. | Baseline has 90 links. See explanation for new miles deployed above. | Baseline has 12 towers. Delayed receipt of Finding of No Significant Impact delayed procurement action. We anticipate completion of procurement process and build of remaining towers to be completed by December 2012 | See explanation for new miles deployed above. | 1 | 3 | 12 | We have a signed agreement with Packerland Broadband as subrecipient. | As subrecipient, Packerland Broadband will receive access to dark fiber. Packerland Broadband will provide wholesale services to third party provider. Specific pricing plans for those services are not yet available. | The following subrecipients will be operating a portion of the network as indicated below: Packerland Broadband, (800) 236-8434 in Iron Mountain MI, for long haul, wholesale and last mile providers, WiscNet, (608) 265- 6761 in Madison WI, for the long haul connections as the Research and Education operator for the University of Wisconsin System, Chippewa Valley Inter-Networking Consortium, (715) 723-0341, for the Chippewa Valley area, Northcentral Technical College, (715) 675-3331 in Wausau, for the Wausau Community Area Network, Platteville Community Area Network, (608) 342-1491, for the Platteville area, and University of Wisconsin-Superior, (715) 394-8101 in Superior, for the Superior Community Area Network. | 0 | 0 | 1 | 0 | Baseline plan has 1. Delayed receipt of Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting further delayed construction. | See explanation above. | Baseline has 9 providers. See explanation above. | See explanation above. | 28 | 25 | 3 | 1000 | Baseline plan has 164. Delayed receipt of Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting further delayed construction. | See explanation above. | See explanation above. | One subscriber is at 10 Gb, the other 27 subscribers are at 1Gb | 0 | 0 | 0 | 0 | 0 | Baseline plan has 3,098 entities passed - all in last mile service areas. Delayed receipt of Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting further delayed construction. | See explanation above. | See explanation above. | See explanation above. | See explanation above. | 0 | 0 | 0 | 0 | 0 | Baseline plan has 550 entities passed - all in last mile service areas. Delayed receipt of Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting further delayed construction. | See explanation above. | See explanation above. | See explanation above. | See explanation above. | No special offerings have been provided. | FALSE | A copy of our network management policies can be found on our website at http:/broadband.uwex.edu. | For the October - December 2012 quarter, construction of the network will continue, pending negotiations with NTIA and U. S. Fish and Wildlife Service regarding the Karner Blue Butterfly. Construction activities include installation of fiber optic cable, splicing and installation of electronic equipment. All communities will connect Community Anchor Institutions. For Chippewa Valley, construction of the remaining eleven towers will begin. Construction activities are now running at full speed and will continue to do so until the ground freezes with the approaching winter. The first long haul spans are expected to come online in this quarter. Wholesale pricing plans will also be finalized at this time to support sales to third party providers. Organized through the Sustainable Broadband Adoption grant, a summit is being organized to bring broadband stakeholders of Wisconsin together to gain from lessons learned in the past two years and explore possible collaborations going forward. As part of this event, meetings will also be held for all subrecipients to discuss project completion, upcoming close-out activities, and ongoing sustainability beyond the grant period. Key project performance indicators for this quarter (cumulative): New network miles installed: 375 Total Community Anchor Institutions connected: 50 Signed agreement for broadband or last mile providers: 3 | University of Wisconsin System | The procurement process for the remaining eleven towers continued through their final stages during this quarter. Local zoning permissions continue to be a challenge for one of the remaining towers, thereby delaying procurement for tower construction. Tower construction is expected to still occur this year. Environmental protection efforts and restrictions continued this quarter. Construction activities did not occur in some areas due to seasonal habitation by protected species. The time line for many of these restrictions ends in October allowing construction to be completed in the fourth quarter. | Pending the completion of negotiations with NTIA and U. S. Fish and Wildlife Service regarding the Karner Blue Butterfly, construction will resume in the remaining areas of the project including Eau Claire County where the majority of towers and community anchor institutions are located. Winter weather typically ends the Wisconsin construction season in early December. Fiber installation and splicing will continue all winter where conduit has been installed, but ground breaking construction activities will cease once the ground freezes. In recent months work crew availability has not been a problem, but an early winter could significantly impact the amount of work done this quarter. UWEX has several route changes pending approval by NTIA which will delay completion of three long haul spans as well as connections to two community anchor institutions and one tower in the Chippewa Valley area. If approval is granted early in the fourth quarter, construction should still be possible before the end of the year. Otherwise these connections will not be completed until spring of 2013. | TRUE
NT10BIX5570115 | 2012 | Q4 | Q4 - 2012 | During this quarter several significant activities have taken place to assist us in completing the Building Community Capacity through Broadband initiative in a timely fashion. Construction has resumed throughout the State. During the quarter we had delays in construction in selected areas pending approval of route changes and resolution of environmental issues. For the overall project, a total of 388 fiber miles have been installed to date. Detail follows. To date, 263 miles of fiber have been installed in the areas between Summit Lake to Wausau, Wausau to Stevens Point, Stevens Point to Eau Claire, Eau Claire to Superior, and Platteville to Madison. For the Chippewa Valley, a total of 118 miles of fiber has been installed to date. Fiber splicing, electronics installation and testing continue with 40 Community Anchor Institutions connected thus far. In Chippewa Valley, tower installation has occurred for four of the 15 sites planned for the community. Procurement steps are in final stages for the remaining towers with installation to be completed next spring. For Platteville, a total of 4 miles of fiber has been installed to date. For Wausau, construction continued this quarter with fiber installation and network testing to occur next quarter. For Superior, all 3 miles of fiber has been installed. Expectations are that all remaining construction for these three communities will be completed next spring. We are still on target to complete the project by the end of the grant period. Much of our community outreach is conducted through a separate Sustainable Broadband Adoption grant. Notable highlights include continuing discussions to develop a sustainability plan for the network after the grant ends and continuation of outreach and educational programming this quarter. A total of 1.15 jobs were created this quarter. | 388 | 0 | 0 | 0 | 388 | 56 | 1 | 0 | Baseline plan has 584. Delayed receipt of the Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting also delayed construction. | NA | See explanation for new miles deployed above. | NA | See explanation for new miles deployed above. | Baseline has 101 links. See explanation for new miles deployed above. | Baseline has 12 new towers. See explanation for new miles deployed above. Three towers are almost complete. Construction contracts were being finalized for the remaining towers. | See explanation for new miles deployed above. | 1 | 3 | 12 | We have a signed agreement with Packerland Broadband as sub recipient. | As sub recipient, Packerland Broadband will receive access to dark fiber. Packerland Broadband will provide wholesale services to third party provider. Specific pricing plans for those services are not yet available. | The following subrecipients will be operating a portion of the network as indicated below: Packerland Broadband, (800) 236-8434 in Iron Mountain MI, for long haul, wholesale and last mile providers, WiscNet, (608) 265- 6761 in Madison WI, for the long haul connections as the Research and Education operator for the University of Wisconsin System, Chippewa Valley Inter-Networking Consortium, (715) 723-0341, for the Chippewa Valley area, Northcentral Technical College, (715) 675-3331 in Wausau, for the Wausau Community Area Network, Platteville Community Area Network, (608) 342-1491, for the Platteville area, and University of Wisconsin-Superior, (715) 394-8101 in Superior, for the Superior Community Area Network. | 0 | 0 | 1 | 0 | Baseline plan has 1. Delayed receipt of the Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting also delayed construction. | NA | Baseline plan has 11. See explanation above. | See explanation above. | 40 | 37 | 3 | 1000 | Baseline plan has 1. Delayed receipt of the Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting also delayed construction. | See explanation above. | See explanation above. | 1000 Mb (1Gb) is the most common connection speed. One subscriber is at 40 Gb, 3 subscribers are at 10 Gb, the other 36 subscribers are at 1 Gb. | 0 | 0 | 0 | 0 | 0 | Baseline plan has 3,098 entities passed. Delayed receipt of the Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting also delayed construction. | See explanation above. | See explanation above. | See explanation above. | See explanation above. | 0 | 0 | 0 | 0 | 0 | Baseline plan has 550 entities passed. Delayed receipt of the Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting also delayed construction. | See explanation above. | See explanation above. | See explanation above. | See explanation above. | No special offerings have been provided. | FALSE | A copy of our network management policies can be found on our website at http:/broadband.uwex.edu. | With the exception of some fiber pulling, fiber network construction will be halted until spring thaw allows construction to continue. Tower construction will continue on nine new towers currently in progress as will equipment installation at four collocation sites. Construction of the last new tower will begin after the spring thaw. All communities will be working on connecting their Community Anchor Institutions. Key activities this quarter include negotiating contracts for ongoing fiber maintenance (notably locates and repairs) and refining network operating budgets. Key project performance indicators for this quarter (cumulative): New network miles installed: 422 Total Community Anchor Institutions connected:65 Signed agreement for broadband or last mile providers: 2 | University of Wisconsin System | Tower construction for three more towers is almost complete. Local zoning issues remain for just one of the 15 tower sites. The final outstanding environmental issues were resolved early in the quarter. Construction continued in earnest through the end of the quarter with the mild winter start. A river crossing near Wausau was originally intended to be an underwater bore, but dense rock was encountered when the bore was attempted. Alternate plans were considered and an attachment to the adjacent bridge was selected as the preferred alternative. NTIA was instrumental in getting the change in installation method approved quickly. Final approval from Wisconsin Department of Transportation is expected soon and installation should be completed in Q1, 2013, thereby providing a path sought by third party providers. | There is some danger of a prolonged winter that will not allow construction to resume until after the end of the quarter, which will compress the schedule through the rest of the project but should not threaten the overall ability to finish the project on time. A specific challenge has emerged in the long haul portion of the project where considerable rock has been found. Changes to installation techniques may be required to avoid a budget shortfall. Detailed analysis of terrain in question is being conducted at this time and we expect to submit any needed change requests to our BTOP program officer shortly. | TRUE
NT10BIX5570115 | 2013 | Q1 | Q1 - 2013 | During this quarter several significant activities have taken place to assist us in completing the Building Community Capacity through Broadband initiative in a timely fashion. Ground disturbing construction halted for the winter season. During the quarter we were able to continue fiber splicing and complete indoor connections as well as tower erection. For the overall project, a total of 482 fiber miles have been installed to date. Detail follows. In the areas between Summit Lake to Wausau, Wausau to Stevens Point, Stevens Point to Eau Claire, Eau Claire to Superior, and Platteville to Madison a total of 355 miles of fiber have been installed. For the Chippewa Valley, a total of 120 miles of fiber has been installed to date. Fiber splicing, electronics installation and testing continue with 41 Community Anchor Institutions connected thus far. In Chippewa Valley, tower erection has been completed for four of the 15 sites planned for the region. Construction has begun for the remaining towers with installation to be completed next quarter. In Platteville, a total of 4 miles of fiber has been installed to date. In Wausau, construction halted due to winter. For Superior, all 3 miles of fiber has been installed. Expectations are that all remaining construction for these three communities will be completed next quarter. We are still on target to complete the project by the end of the grant period. Much of our community outreach is conducted through a separate Sustainable Broadband Adoption grant. Notable highlights include continuation of outreach and educational programming this quarter. A total of 2.15 jobs were created this quarter. | 482 | 0 | 0 | 0 | 482 | 86 | 4 | 0 | Baseline plan has 584. Delayed receipt of the finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting also delayed construction. | NA | See explanation for new miles deployed above. | NA | See explanation for new miles deployed above. | Baseline has 101 links. See explanation for new miles deployed above. | Baseline has 12 new towers. Construction is underway for six remaining new towers. The final two new towers are expected to change to collocation attachments, currently awaiting final NTIA approval. See explanation for new miles deployed above. | See explanation for new miles deployed above. | 2 | 2 | 8 | We have a signed agreement with Packerland Broadband as sub-recipient. A second agreement has been reached for wholesale services between Packerland Broadband and the Wisconsin Independent Network (WIN). | As sub recipient, Packerland Broadband will receive access to dark fiber. Packerland Broadband will provide wholesale services to third party providers. For the new agreement, a 1Gb circuit is being leased for $1,372 per month. | The following subrecipients will be operating a portion of the network as indicated below: Packerland Broadband, (800) 236-8434 in Iron Mountain MI, for long haul, wholesale and last mile providers, WiscNet, (608) 265- 6761 in Madison WI, for the long haul connections as the Research and Education operator for the University of Wisconsin System, Chippewa Valley Inter-Networking Consortium, (715) 723-0341, for the Chippewa Valley area, Wausau Community Area Network, (715) 675-3331, for the Wausau area, Platteville Community Area Network, (608) 342-1491, for the Platteville area, and Superior Community Area Network, (715) 394-8101 for the Superior area. | 1 | 0 | 1 | 0 | Baseline plan has 2. Delayed receipt of the finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting also delayed construction. | NA | Baseline plan has 12. See explanation above. | See explanation above. | 41 | 38 | 3 | 1000 | Baseline plan has 181. Delayed receipt of the finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting also delayed construction. | See explanation above. | See explanation above. | 1000 Mb (1Gb) is the most common connection speed. One subscriber is at 40 Gb, 4 subscribers are at 10Gb and the other 36 subscribers are at 1 Gb. | 0 | 0 | 0 | 0 | 0 | Baseline plan has 3098. Delayed receipt of the finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting also delayed construction. | See explanation above. | See explanation above. | See explanation above. | See explanation above. | 0 | 0 | 0 | 0 | 0 | Baseline plan has 550. Delayed receipt of the finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting also delayed construction. | See explanation above. | See explanation above. | See explanation above. | See explanation above. | No special offerings have been provided. | FALSE | A copy of our network management policies can be found on our website at http:/broadband.uwex.edu. | Fiber network construction will resume for all remaining locations as soon as spring thaw allows construction to continue. All fiber optic cable installation is expected to be completed this quarter. Tower construction will be completed on all new towers currently in progress. Equipment installation at all 15 new tower and collocation sites is also expected to be competed this quarter. All communities will be working on connecting their Community Anchor Institutions. Superior, Platteville, and Wausau communities should have all institutions connected by the end of the quarter. Key project performance indicators for this quarter (cumulative): New network miles installed: 585 Total Community Anchor Institutions connected:140 Signed agreement for broadband or last mile providers: 4 | University of Wisconsin System | Tower erection continues at various locations. Installation of equipment at new tower sites and collocated sites is occurring as planned, despite the late winter. Fiber construction/installation remains on hold due to winter weather. A late winter has delayed re-start of construction originally scheduled to resume in mid-March. Delays with permitting for the Lake Wausau crossing utilizing a bridge attachment have delayed pending sales to third party providers. The point of contention was in the detailed engineering design but those issues seem to be settled now. This construction should be complete in Quarter 2, 2013 | Continued winter weather in the northern part of the state is delaying fiber installation in the Chippewa Valley community and for the long haul segment near Superior. At this time, we expect there should still be time and resources available to complete construction as planned. Three key permits are still outstanding, however we don't anticipate any issues in obtaining the remaining permits. We understand that all underlying concerns have been addressed and we are simply waiting for the paperwork to be completed. A request for a change in the final tower site in New Auburn from new construction to collocation has been submitted and is awaiting NTIA approval. | TRUE
NT10BIX5570115 | 2013 | Q2 | Q2 - 2013 | During this quarter several significant activities have taken place to assist us in completing the Building Community Capacity through Broadband initiative in a timely fashion. Ground disturbing construction halted for the winter season but continued into this quarter with a late spring thaw and heavy rains. During the quarter we were able to continue fiber splicing and complete indoor connections as well as tower erection. For the overall project, a total of 520 fiber miles have been installed and 104 Community Anchor Institutions connected to date. Detail follows. In the areas between Summit Lake to Wausau, Wausau to Stevens Point, Stevens Point to Eau Claire, Eau Claire to Superior, and Platteville to Madison a total of 369 miles of fiber have been installed and 3 Community Anchor Institutions connected. For the Chippewa Valley, a total of 131 miles of fiber has been installed to date. Fiber splicing, electronics installation and testing continue with 62 Community Anchor Institutions connected thus far. In Chippewa Valley, tower erection has been completed for nine of the 15 sites planned for the region. Construction and equipment installation is almost completed for the other 6 sites. In Platteville, all 8 miles of fiber has been installed and all 23 Community Anchor Institutions connected. In Wausau, 8 miles of fiber has been installed and 11 Community Anchor Institutions connected. The remaining work in Wausau will be completed next quarter. For Superior, all 4 miles of fiber has been installed and 5 Community Anchor Institutions connected. The remaining Superior connections will occur next quarter. All remaining work for the project will be completed in the third quarter. Marketing and outreach efforts are now taking place through the newly created Center for Community Technology Solutions within the University of Wisconsin - Extension. The efforts include county listening sessions occurring in eight counties and multiple presentations made to participants interested in broadband. No new jobs were created this quarter. | 520 | 0 | 44 | 0 | 520 | 101 | 8 | 142 | Baseline plan has 588. Delayed receipt of the Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting delayed construction. The more recent prolonged winter and late spring thaw with heavy rains further delayed construction. | NA | Activity is complete. | NA | See explanation for new miles deployed above. | Baseline has 101 links. | Baseline has 12 new towers. Construction is almost complete for two towers. The remaining two towers changed to co-location attachment sites. See explanation for new miles deployed above. | Activity is complete. | 3 | 2 | 24 | We have signed agreement with Packerland Broadband as sub-recipient. A second agreement has been reached for wholesale services between Packerland Broadband and the Wisconsin Independent Network (WIN). Packerland Broadband has a new agreement with WiscNet to provide last mile services to Community Anchor Institutions. | As sub recipient, Packerland Broadband will receive access to dark fiber. Packerland Broadband will provide wholesale services to third party providers. For the first agreement, a 1Gb circuit is being leased for $1,372 per month. As sub recipient, the WiscNet lease agreement provides access to 28 fiber strands to serve community anchor institutions for estimated cost of network maintenance at $2,479 per month. | The following sub-recipients will be operating a portion of the network as indicated below: Packerland Broadband, (800) 236-8434 in Iron Mountain MI, for long haul, wholesale and last mile providers, WiscNet, (608) 265- 6761 in Madison WI, for the long haul connections as the Research and Education operator for the University of Wisconsin System and the operator for connections to community area networks, Chippewa Valley Inter-Networking Consortium, (715) 723-0341, for the Chippewa Valley area, Wausau Community Area Network, (715) 675-3331, for the Wausau area, Platteville Community Area Network, (608) 342-1491, for the Platteville area, and Superior Community Area Network, (715) 394-8101 for the Superior area. | 1 | 0 | 1 | 2 | Baseline plan has 2. Delayed receipt of the Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting delayed construction. The more recent prolonged winter and late spring thaw with heavy rains further delayed construction. All delays resulted in delays in sales of services. | NA | Baseline plan has 14. See explanation above. | One provider has a 1 Gb connection and the other just has dark fiber at this time. | 104 | 88 | 16 | 5 | Baseline plan has 182. Delayed receipt of the Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting delayed construction. The more recent prolonged winter and late spring thaw with heavy rains further delayed construction. All delays resulted in delays in sales of services. | See explanation above. | See explanation above. | 1000 Mb (1Gb) is the most common connection speed. One subscriber is at 40 Gb, 2 subscribers are at 20 Gb, 9 subscribers are at 10Gb, 10 subscribers are at 2 Gb and the other 82 subscribers are at 1 Gb. | 0 | 0 | 0 | 0 | 0 | Baseline plan has 3098. Delayed receipt of the Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting delayed construction. The more recent prolonged winter and late spring thaw with heavy rains further delayed construction. All delays resulted in delays in sales of services. | See explanation above. | See explanation above. | See explanation above. | See explanation above. | 0 | 0 | 0 | 0 | 0 | Baseline plan has 550. Delayed receipt of the Finding of No Significant Impact delayed the start of network build. The extensive review required for environmental permitting delayed construction. The more recent prolonged winter and late spring thaw with heavy rains further delayed construction. All delays resulted in delays in sales of services. | See explanation above. | See explanation above. | See explanation above. | See explanation above. | No special offerings have been provided. | FALSE | A copy of our network management policies can be found on our website at http:/broadband.uwex.edu. | For the final phase of the project, the remaining 63 miles of fiber will be installed, network testing will occur, and the remaining 81 community anchor institutions will be connected. All 15 tower sites, 10 new sites and five co-location attachment sites, in Chippewa Valley will be operational. With completion of the network, we also expect sales in last mile service areas to start. Key project performance indicators for this quarter (cumulative): New network miles installed: 583 Total Community Anchor Institutions connected: 185 Signed agreement for broadband or last mile providers: 3 | University of Wisconsin System | The late winter and spring thaw as well as heavy rains delayed the restart of construction until May. This delay meant a delay for fiber construction activities and connecting many community anchor institutions. All community anchor institutions will be connected next quarter. Migratory birds started nesting on the bridge over the Wisconsin River in Wausau which means we have to delay final construction of that segment until late next quarter. | There are no challenges to report. | TRUE
NT10BIX5570115 | 2013 | Q3 | Q3 - 2013 | During this quarter several significant activities have taken place to complete the Building Community Capacity through Broadband initiative by the end of the extension period. Ground disturbing construction continued throughout the quarter. Final splicing, equipment installations and testing as well as final connections to Community Anchor Institutions occurred this quarter. The last tower sites finished connections. For the overall project, a total of 591 fiber miles have been installed and 172 Community Anchor Institutions connected. Detail follows. In the areas between Summit Lake to Wausau, Wausau to Stevens Point, Stevens Point to Eau Claire, Eau Claire to Superior, and Platteville to Madison a total of 409 miles of fiber have been installed and 4 Community Anchor Institutions connected. For the Chippewa Valley, a total of 162 miles of fiber has been installed. Fiber splicing, electronics installation and testing is complete with 119 Community Anchor Institutions connected. In Chippewa Valley, tower erection has been completed for ten sites planned for the region. Equipment installation is complete for another 5 sites. A total of 15 tower site are active in the region. In Platteville, all 8 miles of fiber has been installed and 23 Community Anchor Institutions connected. In Wausau, 8 miles of fiber has been installed and 19 Community Anchor Institutions connected. For Superior, all 4 miles of fiber has been installed and 7 Community Anchor Institutions connected. No new jobs were created this quarter. | 591 | 0 | 44 | 0 | 591 | 101 | 10 | 142 | Activity is complete. We exceeded the baseline plan of 588. | NA | Activity is complete. | NA | Activity is complete. We exceeded the baseline plan of 588. | Activity is complete. Baseline has 101 links. | Activity is complete. Baseline has 12 new towers. The remaining two towers changed to co-location sites. | Activity is complete. Baseline has 142. | 3 | 0 | 24 | We have a signed agreement with Packerland Broadband as sub-recipient. A second agreement has been reached for wholesale services between Packerland Broadband and the Wisconsin Independent Network (WIN). Packerland Broadband has a new agreement with WiscNet to provide last mile services to Community Anchor Institutions. | As sub recipient, Packerland Broadband will receive access to dark fiber. Packerland Broadband will provide wholesale services to third party providers. For their first agreement, a 1Gb circuit is being leased for $1,372 per month. Two amendments to this agreement were executed this quarter. They are for 1Gb each with lease amounts of $1,874.96 and $1,250.00 per month. Packerland Broadband's second agreement provides access to 28 fiber strands to serve community anchor institutions for estimated cost of network maintenance at $2,479 per month. | The following sub-recipients will be operating a portion of the network as indicated below: Packerland Broadband, (800) 236-8434 in Iron Mountain MI, for long haul, wholesale and last mile providers, WiscNet, (608) 265- 6761 in Madison WI, for the long haul connections as the Research and Education operator and the operator for connections to community area networks, Chippewa Valley Inter-Networking Consortium, (715) 723-0341, for the Chippewa Valley area, Wausau Community Area Network, (715) 675-3331, for the Wausau area, Platteville Community Area Network, (608) 342-1491, for the Platteville area, and Superior Community Area Network, (715) 394-8101 for the Superior area. | 1 | 0 | 2 | 2 | Baseline plan has 2. | NA | Baseline plan has 14. Wholesale services just recently became available for sale due to construction delays. We expect growth to continue in the future. | One provider has a 1Gb connection and the other just has dark fiber at this time. | 172 | 152 | 20 | 6 | Baseline plan has 182. Difference is primarily due to towers that were included in baseline CAI count but omitted here as un-manned locations. | Baseline plan has 156. | Baseline plan has 26. | 1000 Mb (1Gb) is the most common connection speed. One subscriber is at 40 Gb, 2 subscribers are at 20 Gb, 12 subscribers are at 10Gb, 10 subscribers are at 2 Gb and 121 subscribers are at 1 Gb. 26 subscribers are at 10Mb. | 3098 | 14 | 6 | 8 | 3 | Baseline plan has 3098. | Baseline plan has 331. Services just recently became available, much later than originally anticipated . We expect continued growth. | See explanation above. | See explanation above. | 6 customers are receiving 20 Mb service, 3 are receiving 15 Mb service and 3 are receiving 10Mb service | 550 | 0 | 0 | 0 | 0 | Baseline plan has 550. | Baseline plan has 220. Services just recently became available. We expect growth next quarter. | See explanation above. | See explanation above. | See explanation above. | No special offerings have been provided. | FALSE | A copy of our network management policies can be found on our website at http:/broadband.uwex.edu. | Project is complete, there are no activities to report. | University of Wisconsin System | Construction over the Wisconsin River bridge in Wausau occurred in late August after the migratory bird nesting period ended. In September, the Wisconsin Department of Transportation required a minor route change that caused a small delay in construction. However, construction was completed this quarter. | There are no challenges to report. | TRUE
NT10BIX5570116 | 2010 | Q4 | Q4 - 2010 | On October 5, a kickoff meeting was held with over 90 people representing all project partners. The REDI Net team presented a description of the award and grant requirements, and the next steps for the project: obtaining the services of contractors, creating the REDI Net governance structure, initiating public outreach, securing all permits and permissions, and beginning construction of the system. Contracts for the Environmental Assessment, Final Design and Engineering, and Project Management were awarded on November 4, following a competitive procurement process. The REDI Net team attended the NTIA BTOP Workshop in Washington, DC, where it held several face to face meetings with federal partners and other programs in the region. Individuals representing North Central New Mexico Economic Development District, Rio Arriba County and the environmental and engineering contractors took advantage of the sessions and spent considerable time with federal officials regarding the Environmental Assessment. Following the BTOP Conference, work began immediately on the final route and draft environmental assessment. Research, survey work and agency consultation for the draft environmental assessment were substantially complete by the end of the quarter and progress was reviewed with NTIA staff. Much of the initial Design and Engineering work involved partnering with the environmental assessment team to insure the final route met all environmental requirements. Design and Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | n/a | No services are yet being provided. The project is still completing its Environmental Assessment. The project is still completing its Environmental Assessment. | No agreement has yet been signed. The project is still completing its Environmental Assessment. | 0 | 0 | 0 | 0 | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | 0 | 0 | 0 | 0 | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | 0 | 0 | 0 | 0 | 0 | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | 0 | 0 | 0 | 0 | 0 | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | No services are yet being provided. The project is still completing its Environmental Assessment. | FALSE | No services are yet being provided. The project is still completing its Environmental Assessment. | The RFP's for construction team, materials suppliers and equipment venders will be advertised the week of February 7, with a contract execution anticipated by the last week of April. Advance procurement of materials will take place in mid-February. This will enable the project to catch up to all milestones in the baseline report and to proceed to the following activities, as listed in the baseline. â€¢ Hold one or more public meetings on REDI Net â€¢ Complete 100% Environmental Assessment â€¢ Complete 30%, 60%, and 90% of milestones of Final Engineering Design â€¢ Select contractor and negotiate contract â€¢ Procure OSP materials and network equipment â€¢ Completion of rights-of-way and construction permits â€¢ Site prep for primary POP, renovations for secondary POP | North Central New Mexico Economic Development District | The Environmental Assessment proved challenging and considerable assistance from the BTOP program was provided and proved very useful. The intense effort required to insure that all the interconnections and routes were completely accurate for the EA by mid-December meant that other engineering activities were delayed. Delays in gaining approval for the six month budget hindered progress, in that contractors and NCNMEDD needed assurance that expenditures would be reimbursed and needed approval to draw down federal funds in order to meet the six month spending level. This has been resolved, but it did delay expenditures and some activities. | The team anticipates some challenges. Discussions scheduled in January indicate that more work may be needed to satisfy Bureau of Indian Affairs and some tribal concerns about what documents are needed to secure permits and what role the Bureau actually has in the issuing of rights of way. In addition, ongoing discussion between the local electric cooperative and some tribal partners may affect the easement underlying the fiber to be laid by this project. The project may request additional assistance from BTOP on these issues. These issues have been discussed with the FPO. While not unanticipated, the development of the Broadband Governing Board will be challenging. The current network design was limited by the available funds and the limitations imposed by the environmental assessment deadline. It will be important for the Board to initiate priorities for network expansion to accommodate the requests for connections that have come in since the finalization of the route to meet the EA deadline. While this is not expected to impact the project milestones, Finally, this quarter the team will submit AAR's to a) add four Pueblos to the sub-recipients on the grant; b) address the issue posed by the in-kind and project income portion of the match (the timing of which may affect project cash flow); c) acknowledge the submission of the EA; and d) address non-overlap issues. Assistance will be requested of the BTOP team to insure these activities are successfully accomplish | TRUE
NT10BIX5570116 | 2011 | Q1 | Q1 - 2011 | The Environmental Assessment was completed in Quarter 3. The draft EA was submitted on January 27, 2011. We received comments back from the agency on March 2, 2011 and submitted our revisions to the EA on March 28, 2011. Authorization to release the revised EA to relevant agencies and tribes was issued on April 8. 60% of aerial engineering design, 45% of underground design, and premise designs for 107 community anchor institutions were completed in the first quarter. A competitive request for proposal process for REDI Net Construction Services and Materials Procurement was announced on February 7, 2011. A mandatory pre-bid conference was held on February 22, 2011, and was attended by 55 individuals from prospective bidding companies. The RFP process closed on March 7, 2011, when all proposals were opened and screened. Eight complete and responsive proposals were submitted and are currently under review by a technical evaluation team. Further due-diligence is underway on a shortlist of 3 proposals. A public education meeting was held for REDI Net in Espanola, New Mexico on March 30, 2011 to inform the public about project status, routes and institutions to be connected. The project team provided samples of fiber optic cable, informational handouts and displayed a project map. The REDI Net governance board held its first two meetings in Quarter 3. On March 2, the group reviewed the overall project and project status. On April 5, the group reviewed the business model and | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | n/a | No services are being provided to date, and construction on the project will not begin until a FONSI is receivedd to date, and construction on the project will not begin until a FONSI is received. | The agreement with the third party operator has not yet been signed. No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | 0 | 0 | 0 | 0 | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | 0 | 0 | 0 | 0 | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | 0 | 0 | 0 | 0 | 0 | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | 0 | 0 | 0 | 0 | 0 | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | No services are being provided to date, and construction on the project will not begin until a FONSI is issued. | FALSE |  | The following activities are listed in the baseline report for the next quarter: *Complete 100% of engineering design, with all rights-of-way and construction permits secured *Complete construction of Phase I core, interconnect and primary POP. Begin construction of Phase I fiber laterals, and connections for 94 CAIs. Network will be approximately 36% complete. *Negotiate terms with interconnect provider and provision service. *Enter into contracts for network management and outside plant operation and maintenance. We anticipate completing 100% engineering design and securing all permits and rights-of-way in Quarter 4. A 90% engineering review meeting is currently scheduled for April 29, 2011. Permits and rights-of-way are currently 75% complete and should be fully executed in Quarter 4. We anticipate entering into contracts for construction services, materials procurement, network management and outside plant operation and maintenance in Quarter 4, as planned. We have been planning for the lineman training program which will be implemented by Northern New Mexico College, and should have curriculum developed and a projected date for the training by the end of Quarter 4. The project manager has been meeting with our anticipated interconnect provider, and will finalize terms with this entity in Quarter 4. Construction activities are now projected to begin in June 2011, due to delays with the Environmental Assessment/FONSI and project funding. This means that network construct | North Central New Mexico Economic Development District | Issues identified in the Quarter 2 report played a large role in the variances in Quarter 3. BTOP assistance was requested and received in Quarter 2 relevant to the Environmental Assessment, approval of the six-month budget, and approval in federal fund expenditures. This assistance was helpful, but these issues caused project delays and variances from the baseline which have carried over into Quarter 3. | Project construction is delayed until June 2011, instead of April 2011. This means that substantially less of the network will be constructed by the end of Quarter 4 than indicated in the baseline. Because the project anticipates a 12-month construction period, we believe that delays to date can be accommodated within the BTOP requirements. The FPO and BTOP team have been notified of this change, and are working closely with us on this issue. | TRUE
NT10BIX5570116 | 2011 | Q2 | Q2 - 2011 | A Finding of No Significant Impact (FONSI) for this project was issued on June 20, 2011. Make-ready activities began that same day and construction activities commenced on June 27, 2011. Network design and construction/materials procurement activities are now 100% complete. The REDI Net Board continues to meet monthly. During this quarter, we developed and adopted a Service Level Agreement (SLA) for community anchor institutions. We also held a successful meeting with last-mile provider partners in preparation for negotiating SLAs with them in the next quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | While network construction began at the very end of Q4, no fiber has been placed yet. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 2 | 0 | N/A | No services are being provided to date, as construction began on 6/27/11. The Policy Committee of the REDI Net Board is currently reviewing two wholesale pricing schedules and developing a last-mile provider Service Level Agreement. A successful meeting with potential last mile providers was held on June 7, 2011, with five potential providers in attendance. | The agreement with the third party operator has not yet been signed. No services are being provided to date, as construction began on 6/27/11. | 0 | 0 | 0 | 0 | No services are being provided to date, as construction began on 6/27/11. | No services are being provided to date, as construction began on 6/27/11. | No services are being provided to date, as construction began on 6/27/11. | No services are being provided to date, as construction began on 6/27/11. | 0 | 0 | 0 | 0 | No services are being provided to date, as construction began on 6/27/11. | No services are being provided to date, as construction began on 6/27/11. | No services are being provided to date, as construction began on 6/27/11. | No services are being provided to date, as construction began on 6/27/11. | 0 | 0 | 0 | 0 | 0 | No services are being provided to date, as construction began on 6/27/11. | No services are being provided to date, as construction began on 6/27/11. | No services are being provided to date, as construction began on 6/27/11. | No services are being provided to date, as construction began on 6/27/11. | No services are being provided to date, as construction began on 6/27/11. | 0 | 0 | 0 | 0 | 0 | No services are being provided to date, as construction began on 6/27/11. | No services are being provided to date, as construction began on 6/27/11. | No services are being provided to date, as construction began on 6/27/11. | No services are being provided to date, as construction began on 6/27/11. | Business customers will be served by last-mile providers. | No services are being provided to date, as construction began on 6/27/11. | FALSE | N/A | Construction activities are approximately one quarter behind schedule due to delays with the FONSI. As a result, we anticipate completion of the following construction activities in Quarter 1 of Year 2: *100% Site Preparation for POPs *36% Network Construction In addition, the following contracts and agreements will be developed: *Contract for network management *Contract for operation and maintenance of outside plant infrastructure *Service Level Agreements with last mile providers *Contract/s with interconnect providers | North Central New Mexico Economic Development District | Overall, construction and construction-related activities are approximately one quarter behind schedule due to delays in issuance of the FONSI. Construction began three days before the end of this quarter, therefore minimal construction expenditures were made. | In late June 2011, the Las Conchas fire broke out within Los Alamos County, Santa Clara Pueblo, and adjacent portions of Rio Arriba County. The fire is the largest in New Mexico's history and could potentially delay some aspects of permitting and construction. We do not know at this date if there will be delays or what the delays will be, as the fire has yet to be contained. | TRUE
NT10BIX5570116 | 2011 | Q3 | Q3 - 2011 | - Ramp up of construction activities from 1% to 27%. - Rights-of-way, construction permits, site preparation and equipment procurement are all near 100% complete. The project overcame delays in fiber procurement with no effect on the project. - Held public ground breaking event and one additional community outreach event for REDI Net, and issued an RFQ to develop a web portal for better community engagement. - REDI Net Board and committees continue to meet monthly. In Q3 2011, the policy committee developed an SLA for last-mile providers which is currently being negotiated with five last-mile partners. The committee also developed draft bylaws and network management policies scheduled for adoption in Q4 2011. - Began negotiations with upstream interconnect providers and network operations provider Kit Carson Electric and Telecom in preparation for signing agreements and contracts. | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2.27 miles of aerial fiber deployed | N/A | Tie ins with the existing/upgrade fiber plant will occur in Q1 2012 | N/A | 2.27 miles of aerial fiber deployed | N/A | N/A | Interconnect points will be established in the upcoming reporting period | 0 | 5 | 0 | N/A. | Please see attachment for proposed wholesale pricing schedule which we expect to be approved by the REDI Net Board of Directors by the end of Q4 2011. The REDI Net Board is also adopting policies which allow it to consider requests for Aggregated Internet Bandwidth provided that these requests do not negatively impact current bandwidth commitments to community anchor institutions and other last-mile providers, and do not or will not in the next five years cause REDI Net to exceed its oversubscription rate. CoLocation services are also being developed. | REDI Net is in the process of negotiating a three-year Network Management Agreement with Kit Carson Electric Cooperative and Telecom, as described in the original BTOP grant application. Kit Carson Telecom will provide network management for 100% of the REDI Net network. Kit Carson Telecom is not a sub-recipient, contractor or subcontractor under the BTOP grant, but is providing network management free of charge to REDI Net for its first three years of operation. Address: 201 Cruz Alta Road, Suite B, Taos NM, 87571. | 0 | 0 | 0 | 0 | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | 0 | 0 | 0 | 0 | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | 0 | 0 | 0 | 0 | 0 | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | 0 | 0 | 0 | 0 | 0 | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | REDI Net will provide the following service offerings: For community anchor institutions: Bundled Internet/Ethernet Access, Ethernet Transport. For last-mile service providers: Per Subscriber Bandwidth, Aggregated Internet Bandwidth, CoLocation. | FALSE | N/A | - Construction Activities: 29 new network miles will be deployed, POP buildings will be set on the foundations in Espanola and Santa Fe, along with wiring, rack installation, HVAC, and back-up generator. The existing POP facility in Los Alamos will also be retrofitted for operations. The core fibers will be placed in the Espanola POP. - Route Changes: We expect to submit an EA Addendum for additional laterals in Q4 2011. - Policy Activities: The REDI Net Board plans to adopt bylaws and network management policies in Q4 2011. - Contracts and Agreements: Contracts for upstream interconnect bandwidth and network operations management will be drafted in Q4 2011. We are negotiating but do not expect to have signed agreements with broadband wholesalers or last mile providers by the end of Q4 2011. -We do not anticipate providing service to CAI subscribers by the end of Q4 2011. No network miles will be leased in this project. | North Central New Mexico Economic Development District | - Pole Attachment Applications took longer to process than anticipated, - Make-Ready expenses are requiring significant negotiations and monitoring to stay within budget. - FONSI delays have most construction activities about 3 months behind schedule, but ramping up quickly. - Supply issues on fiber cable took significant time and effort to resolve, with impact to the project mitigated. - Communications links with NOC (Kit Carson Electric) and upstream bandwidth providers have been delayed to due the slower construction schedules of partner projects (Round 2 Kit Carson Electric BIP grant/loan and Plateau Communications BTOP grant). | In addition to the issues listed for #3 Performance Indicators for Q3 2011, we have experienced significant delays on route change requests. Based on recent guidance from NTIA, we are revising our route change requests and will likely be directed to complete an EA Addendum. We do not expect the EA Addendum to impact our ability to meet NTIA construction deadlines, however, as we are scheduled to complete network build by summer 2012. New laterals and CAI connections included in the EA Addendum will have to be completed within this time frame, as well, or crews will no longer be mobilized for construction. | TRUE
NT10BIX5570116 | 2011 | Q4 | Q4 - 2011 | - Construction activities increasing from 27% to 51%. - Increase of new fiber deployed from 2.27 to 30.57 miles complete. Previous PPR forecasted 29 additional miles. - POP buildings set on the foundations in Espanola and Santa Fe, along with wiring, rack installation, HVAC, and back-up generator. - Pole replacement cost sharing agreements resolved with electric utilities. - Route changes/route alternatives ifor key project segments defined for EA Addendum. - Rights-of-way, construction permits, site preparation and equipment procurement are all near 100% complete. The project overcame delays in fiber procurement with no effect on the project. - REDI Net Board, Executive Committees, and Subcommittees formalized, with scheduled monthly meetings. In Q4 2011, the Board adopted SLAs for last-mile providers (currently being negotiated with five last-mile partners), wholesale pricing models, network policy documents, and bylaws. - Issued RFB for upstream interconnect bandwidth. | 31 | 0 | 5 | 0 | 31 | 0 | 0 | 0 | Behind baseline due to make-ready delays (see 3 above). | N/A | 5.33 miles of existing fiber | N/A | Behind baseline due to make-ready delays (see 3 above). | N/A | N/A | Interconnect points will be established closer to lighting network | 0 | 5 | 0 | N/A | Previously attached wholesale pricing schedule was approved by the REDI Net Board in Q4 2011. The REDI Net Board is also adopting policies which allow it to consider requests for Aggregated Internet Bandwidth provided that these requests do not negatively impact current bandwidth commitments to community anchor institutions and other last-mile providers, and do not or will not in the next five years cause REDI Net to exceed its oversubscription rate. CoLocation services are also being developed. | REDI Net is in the process of negotiating a three-year Network Management Agreement with Kit Carson Electric Cooperative and Telecom, as described in the original BTOP grant application. Kit Carson Telecom will provide network management for 100% of the REDI Net network. Kit Carson Telecom is not a sub-recipient, contractor or subcontractor under the BTOP grant, but is providing network management free of charge to REDI Net for its first three years of operation. Address: 201 Cruz Alta Road, Suite B, Taos NM, 87571. | 0 | 0 | 0 | 0 | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | 0 | 0 | 0 | 0 | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | 0 | 0 | 0 | 0 | 0 | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | 0 | 0 | 0 | 0 | 0 | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | REDI Net will provide the following service offerings: For community anchor institutions: Bundled Internet/Ethernet Access, Ethernet Transport. For last-mile service providers: Per Subscriber Bandwidth, Aggregated Internet Bandwidth, CoLocation. | FALSE | N/A | - Construction Activities: 20 new network miles will be deployed and significant ramp-up in pole replacements will occur now that cost sharing agreements have been reached with the utilities. Will complete major backbone segment between Santa Fe and Espanola. - Route Changes: We expect to submit an EA Addendum for additional laterals and Los Alamos County backbone route alternatives in upcoming reporting period. - Contracts and Agreements: REDI Net anticipates awarding contract/s for interconnect bandwidth and signing a network operations agreement with Kit Carson Telecom. Some of the agreements with last mile providers may be finalized by the end of Q1 2012. - We do not anticipate providing service to CAI subscribers by the end of Q1 2012, as our NOC communications link may not be active by that date due to slower deployment of the Kit Carson BIP project. No network miles will be leased in this project. | North Central New Mexico Economic Development District | - Pole replacement expenses required significant negotiations with electrical utilities to stay within budget. Aerial construction activities were temporarily halted until a cost sharing agreement was finalized in late December 2011. - FONSI delays placed most construction activities about 3 months behind, but the schedule is ramping up. - Route changes and alternatives for key network segments required significant time and effort to identify for the EA Addendum. - Communications links with NOC (Kit Carson Electric) and upstream bandwidth providers have been delayed to due the slower construction schedules of partner projects (Round 2 Kit Carson Electric BIP grant/loan and Plateau Communications BTOP grant). | In the current reporting period, the project experienced delays in make-ready, which will take time to catch up on in the upcoming reporting period. As stated previously in this PPR, in late December 2011 agreements were reached with the utilities on cost-sharing agreements which will not add extra cost to the project, however there is ramp-up work needed on make-ready activities before aerial fiber placement can resume. The forecast for Q1 2012 assumes no unforeseen challenges arise. Make-ready activities will be monitored closely, with weekly status meetings planned with the utilities to ensure an efficient rollout. Other challenges in the current reporting period that may impact the upcoming quarter are route changes/route alternatives. Based on guidance from NTIA, we will be submitting an EA Addendum. This work is already underway with our EA consultants. The timing of the EA Addendum (including agency consultations and BTOP processing) is critical to maintain overall project delivery and meet construction deadlines, as we are scheduled to complete network build by fall 2012. New laterals, backbone alternatives, and CAI connections included in the EA Addendum will have to be authorized within 3-5 months, or crews will no longer be mobilized. | TRUE
NT10BIX5570116 | 2012 | Q1 | Q1 - 2012 | -Construction activities increased to 54% complete. Significant progress was made on the underground portion of network construction, which is now 75% complete. Aerial construction is proceeding more slowly at 22% complete due to ongoing replacement of 400 poles. -Increase in new fiber deployed from 30.57 miles to 49 miles. -Preparing POP facilities for network activation, including fiber testing/termination, generator installation, and utility connections. -Procurement for utility locating services secured through competitive process. REDI Net also selected an upstream Internet provider through a competitive proposal process and is in final contract negotiations. | 49 | 0 | 5 | 0 | 49 | 0 | 0 | 0 | Behind baseline due to make-ready delays (see 3 above). | N/A | 5.33 miles of existing fiber | N/A | Behind baseline due to make-ready delays (see 3 above). | N/A | N/A | Interconnect points will be established closer to network activation | 0 | 4 | 0 | N/A | Previously attached wholesale pricing schedule was modified by the REDI Net Board in the current reporting period, to remain competitive with market conditions. The REDI Net Board is also adopting policies which allow it to consider requests for Aggregated Internet Bandwidth provided that these requests do not negatively impact current bandwidth commitments to community anchor institutions and other last-mile providers, and do not or will not in the next five years cause REDI Net to exceed its oversubscription rate. CoLocation services are also being developed. | REDI Net is in the process of negotiating a three-year Network Management Agreement with Kit Carson Electric Cooperative and Telecom, as described in the original BTOP grant application. Kit Carson Telecom will provide network management for 100% of the REDI Net network. Kit Carson Telecom is not a sub-recipient, contractor or subcontractor under the BTOP grant, but is providing network management free of charge to REDI Net for its first three years of operation. Address: 201 Cruz Alta Road, Suite B, Taos NM, 87571. | 0 | 0 | 0 | 0 | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | 0 | 0 | 0 | 0 | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | 0 | 0 | 0 | 0 | 0 | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | 0 | 0 | 0 | 0 | 0 | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | REDI Net will provide the following service offerings: For community anchor institutions: Bundled Internet/Ethernet Access, Ethernet Transport. For last-mile service providers: Per Subscriber Bandwidth, Aggregated Internet Bandwidth, Ethernet Transport, CoLocation. | FALSE | N/A | - Construction Activities: 30 new network miles will be deployed and significant ramp-up in pole replacements will occur with the addition of new crews. Will complete major backbone segment between Espanola and Velarde as well as routes within Los Alamos/White Rock. - Route Changes: We will submit an EA Addendum for additional CAIs/laterals and route changes to connect Los Alamos County in upcoming reporting period. - Contracts and Agreements: In the upcoming reporting period, REDI Net will finalize an interconnect bandwidth agreement, a network operations agreement with Kit Carson Telecom, and an operation and maintenance agreement with Jemez Mountains Electric Cooperative. - REDI Net will continue network readiness, including fiber testing, POP preparation, core router installation, and burning in portions of the network, in an effort to launch services in limited markets in Q3 2012. Connections to CAIs will not be activated until Q3 2012, although in-building installation is ongoing. Therefore, no CAIs will be connected in Q2 2012. | North Central New Mexico Economic Development District | There are two primary challenges being faced: 1. Make-Ready: Significant progress has been made with the electric co-op that represents the majority of our pole attachments, but continuous oversight and management is required to keep pole replacements on schedule. REDI Net and the co-op brought on additional crews in Q1 2012 to ramp up construction. 2. EA Addendum: The EA checklist and EA addendum include additional CAIs and corresponding laterals, as well changes to the original route to connect Los Alamos County. While the CAI/lateral work has been complete for some time, additional due diligence has been required on the route changes for Los Alamos County. This has resulted in delays with submitting the checklist and addendum. However, consultation with the relevant agencies has already occurred and should expedite the process once the documents are submitted. | In the upcoming reporting period, we expect the pole replacement and make-ready activities to require continued, close oversight. This will be one of our main areas of focus. The other activity that could impact overall project delivery is the EA Addendum. In May of the upcoming reporting period, REDI Net will submit the EA Addendum checklist and subsequent EA addendum. Approval of the EA addendum is important from a construction scheduling standpoint, so that we have the appropriate personnel available to complete the work and avoid demobilization/remobilization expenses. | TRUE
NT10BIX5570116 | 2012 | Q2 | Q2 - 2012 | - Construction activities: 38 new network miles deployed during the current reporting period, ahead of the 30 miles forecasted in the previous PPR. - Network readiness: conducted network testing, completion of primary POP, CAI and POP equipment installation, all in a effort to prepare for project Q1 Y3 network activation. - Site prep work completed - Equipment procurement completed - Route Changes: EA Checklist submitted for additional CAI laterals and backbone alternatives to Los Alamos County. - Contracts and Agreements: REDI Net finalized an interconnect bandwidth agreement through a public bid process with an upstream interconnect provider. Network operations agreement and outside plant maintenance agreement in final negotiations. | 87 | 0 | 5 | 0 | 87 | 0 | 0 | 1 | Catching up to, but still behind baseline, due to initial EA and make-ready delays. | NA | 5.33 miles of existing fiber | NA | Catching up to, but still behind baseline, due to initial EA and make-ready delays. | NA | NA | 1 interconnect point established with upstream Internet gateway provider. | 0 | 4 | 0 | N/A | Wholesale pricing schedule provided in Q1 2012. The REDI Net Board and Finance Committee are continuously evaluating new wholesale offerings and related policy considerations, for services such as Aggregated Internet Bandwidth, CoLocation, and potential dark fiber strategies. The Board will ensure these requests do not negatively impact current bandwidth commitments to community anchor institutions and other last-mile providers, and do not or will not in the next five years cause REDI Net to exceed its oversubscription rate or fiber asset management. | REDI Net is in the process of negotiating a three-year Network Management Agreement with Kit Carson Electric Cooperative and Telecom, as described in the original BTOP grant application. Kit Carson Telecom will provide network management for 100% of REDI Net. Kit Carson Telecom is not a sub-recipient, contractor or subcontractor under the BTOP grant, but is providing network management at no charge to REDI Net for its first 3 years of operation. Address: 201 Cruz Alta Road, Suite B, Taos NM, 87571. | 0 | 0 | 0 | 0 | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | 0 | 0 | 0 | 0 | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | 0 | 0 | 0 | 0 | 0 | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | 0 | 0 | 0 | 0 | 0 | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | REDI Net will provide the following service offerings: For community anchor institutions: Bundled Internet/Ethernet Access, Ethernet Transport. For last-mile service providers: Per Subscriber Bandwidth, Aggregated Internet Bandwidth, Ethernet Transport, CoLocation. | FALSE | N/A | - Construction Activities: 20 new network miles will be deployed, with further production dependent upon route changes approved through the EA Addendum process. Other work includes network testing, POP setup, and equipment installation. - Route Changes: REDI Net anticipates receiving approval of its EA Addendum/proposed route changes in the August 2012 and is working in parallel on securing the necessary permits and NEPA compliance measures. - Contracts and Agreements: REDI Net intends to finalize network management, operations and maintenance, and 4 last-mile provider agreements. - Services: REDI Net plans to launch broadband services in late September/early October 2012. 3 CAIs will be connected and receiving service by the end of Q3 2012. All other CAIs not dependent on route changes will be connected in early October. The 4 last-mile providers discussed above will be connected in early October. | North Central New Mexico Economic Development District | The primary challenges being faced to complete the project are the approval of proposed route changes and make-ready activities. The route changes include additional connections for CAIs within the PFSA and realignment of the backbone due to unforeseen ROW and access issues. We continue to focus our construction crews on areas that are authorized to build, i.e. "Phase I construction", which has not slowed down productivity to date (76% complete of Phase I), but approval of the route changes will be required for project completion. Regarding make-ready, significant progress has been made with the electric co-op that represents the majority of our pole attachments, but continuous oversight and management is required to keep that effort on schedule. | In the upcoming reporting period, we expect to complete Phase I construction activities and commence Phase II (route changes)- provided that the REDI Net EA Addendum is approved by BTOP. Prompt approval of the EA Addendum is important from a construction scheduling standpoint, so that we still have the appropriate personnel available to complete the work and avoid demobilization/remobilization expenses. Also in the upcoming reporting period, we intend to begin offering wholesale broadband services to CAIs and last-mile providers, provided that the associated agreements are finalized. As we transition from primarily a construction project into live network operations, we foresee our main focus shifting to day-to-day operational matters and challenges that may arise. | TRUE
NT10BIX5570116 | 2012 | Q3 | Q3 - 2012 | - Construction activities: 12 new network miles deployed during the current reporting period. 20 new network miles were forecasted. Variance related to delays with EA Addendum approval, which resulted in demobilization/remobilization of the construction crews. - Network readiness: Launched "trial" services, as a pre-production network burn-in, to stabilize the network operating environment and to enable a limited number of CAIs to receive bandwidth services needed. The secondary POP was activated in Los Alamos, NM as well. Significant coordination held with the NOC, reviewing technical and billing details, in an effort to prepare the NOC for "go-live." - Contracts and Agreements: Network operations agreement executed. Outside plant maintenance agreement in final negotiations. Last-mile provider Service Level Agreements being negotiated. Pole attachment agreement being negotiated with US Dept. of Energy. | 99 | 0 | 5 | 0 | 99 | 0 | 0 | 1 | Catching up with original baseline but still behind due to EA, EA Addendum, and make-ready delays. | N/A | 5.33 miles of existing fiber | N/A | Catching up with original baseline but still behind due still behind due to EA, EA Addendum, and make-ready delays. | N/A | N/A | 1 interconnect point established with upstream Internet gateway provider. | 0 | 4 | 0 | N/A | Wholesale pricing schedule provided in Q1 2012. The REDI Net Board and Finance Committee are continuously evaluating new wholesale offerings and related policy considerations, for services such as Aggregated Internet Bandwidth, CoLocation, and potential dark fiber strategies. The Board will ensure these requests do not negatively impact current bandwidth commitments to community anchor institutions and other last-mile providers, and do not or will not in the next five years cause REDI Net to exceed its oversubscription rate or fiber asset management. REDI Net is currently providing network services on a "trial" basis to a limited number of CAIs, in an effort to stabilize the network operating environment and offer CAIs bandwidth needed. | REDI Net has signed a three-year Network Management Agreement with Kit Carson Electric Cooperative and Telecom, as described in the original BTOP grant application. Kit Carson Telecom will provide network management for 100% of REDI Net. Kit Carson Telecom is not a sub-recipient, contractor or subcontractor under the BTOP grant, but is providing network management at no charge to REDI Net for its first 3 years of operation. Address: 201 Cruz Alta Road, Suite B, Taos NM, 87571. | 0 | 0 | 0 | 0 | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | 27 | 27 | 0 | 4 | Services are being provided on a limited, "trial" basis as part of the network stabilization and "burn-in" period. | Services are being provided on a limited, "trial" basis as part of the network stabilization and "burn-in" period. | N/A | Services are being provided on a limited, "trial" basis as part of the network stabilization and "burn-in" period. Speeds being offered are 5 Mbps to 100 Mbps. 5 Mbps = 20 CAI 20 Mbps = 3 CAI 50 Mbps = 2 CAI 100 Mbps = 2 CAI | 0 | 0 | 0 | 0 | 0 | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | 0 | 0 | 0 | 0 | 0 | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | REDI Net will provide the following service offerings: For community anchor institutions: Bundled Internet/Ethernet Access, Ethernet Transport. For last-mile service providers: Per Subscriber Bandwidth, Aggregated Internet Bandwidth, Ethernet Transport, CoLocation. | FALSE | N/A | - Construction Activities: 30 new network miles will be deployed, with final production dependent upon pole replacements. Other work includes network testing, secondary POP setup, and remaining CAI equipment installation. - Contracts and Agreements: REDI Net intends to finalize operations and maintenance agreement and 4 last-mile provider agreements. - Services: REDI Net plans to "go-live" with production broadband services in November 2012. 44 additional CAIs will be activated. 2 last-mile providers should also be connected. | North Central New Mexico Economic Development District | The primary challenges faced during the past quarter were related to delays with receiving approval of the EA Addendum. This resulted in having to demobilize the aerial fiber construction crew due to lack of work, thus impacting project delivery. The project also experienced disruptions due to work flow issues on pole replacements; however, progress has been made with the respective electric co-op and continuous oversight is being provided to keep that effort moving forward. | In the upcoming reporting period, we expect to complete building the majority of the route changes as we near project completion - provided that pole replacement activities continue as scheduled with the electric utility. Prompt approval of the construction easement / pole attachment agreement with the US Dept of Energy, along with a microwave installation permit from Los Alamos will also be required to meet our quarterly objectives. In the upcoming reporting period, we intend to "go-live" with broadband services to CAIs and last-mile providers, provided that the associated Service Level Agreements (SLAs) are finalized. | TRUE
NT10BIX5570116 | 2012 | Q4 | Q4 - 2012 | - Construction activities: 20 new network miles deployed during the reporting period. 30 new network miles were forecasted. Variance relating to delays with US Dept of Energy (DOE) agreement and pole replacements. This resulted in demobilization of the aerial crews. - Network readiness: Expanded "trial" services, as a pre-production network burn-in, to a total of 37 locations. Finalized NOC setup, including technical, billing and operational procedures. Network "go-live" planned for Feb 2013. - Contracts and Agreements: Pursing outside plant maintenance agreement via State of NM approved contract. Last-mile provider Service Level Agreements (SLAs) under negotiation. Initial CAI SLAs signed with more under review. US DOE pole attachment agreement negotiated and prepared for signature. Santa Fe POP utility easement finalized and recorded at Santa Fe County. | 119 | 0 | 5 | 0 | 119 | 0 | 0 | 1 | Catching up with original baseline, due still behind due to EA, EA Addendum, and pole replacement delays | N/A | 5.33 miles of existing fiber | N/A | Catching up with original baseline, due still behind due to EA, EA Addendum, and pole replacement delays | N/A | N/A | 1 interconnect point established with upstream Internet provider | 0 | 6 | 0 | N/A | Updated wholesale pricing is being provided as part of this report. The REDI Net Board and Finance Committee are continuously evaluating new wholesale offerings and related policy considerations, for services such as Aggregated Internet Bandwidth, CoLocation, and potential dark fiber strategies. The Board will ensure these requests do not negatively impact current bandwidth commitments to community anchor institutions and other last-mile providers, and do not or will not in the next five years cause REDI Net to exceed its oversubscription rate or fiber asset management. REDI Net is currently providing network services on a "trial" basis to a limited number of CAIs, in an effort to stabilize the network operating environment and offer CAIs bandwidth needed. | REDI Net has signed a three-year Network Management Agreement with Kit Carson Electric Cooperative and Telecom, as described in the original BTOP grant application. Kit Carson Telecom will provide network management for 100% of REDI Net. Kit Carson Telecom is not a sub-recipient, contractor or subcontractor under the BTOP grant, but is providing network management at no charge to REDI Net for its first 3 years of operation. Address: 201 Cruz Alta Road, Suite B, Taos NM, 87571. | 0 | 0 | 0 | 0 | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | No services are being provided to date. | 37 | 37 | 0 | 5 | Services are being provided on a limited, "trial" basis as part of the network stabilization and "burn-in" period. | Services are being provided on a limited, "trial" basis as part of the network stabilization and "burn-in" period. | N/A | Services are being provided on a limited, "trial" basis as part of the network stabilization and "burn-in" period. Speeds being offered are 5 Mbps to 100 Mbps. 5 Mbps = 25 CAI 10 Mbps = 1 CAI 20 Mbps = 5 CAI 50 Mbps = 3 CAI 100 Mbps = 3 CAI | 0 | 0 | 0 | 0 | 0 | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | Residential services will be provided by last-mile providers. | 0 | 0 | 0 | 0 | 0 | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | Business services will be provided by last-mile providers. | REDI Net will provide the following service offerings: For community anchor institutions: Bundled Internet/Ethernet Access, Ethernet Transport. For last-mile service providers: Per Subscriber Bandwidth, Aggregated Internet Bandwidth, Ethernet Transport, CoLocation. | FALSE | N/A | - Construction Activities: estimated miles for next quarter--20 new network miles planned for deployment, with final production dependent upon remobilization date for aerial construction crew. Other work includes network testing and the remaining CAI activation. - estimated number of wholesaler/last mile provider agreements to be signed--2 agreements --Contracts and Agreements: REDI Net intends to finalize the US DOE pole attachment agreement and O & M agreements. - estimated number of CAIs to be connected for next quarter--Services: REDI Net plans to "go-live" with production broadband services February 2013, with service available to ~100 CAIs. | North Central New Mexico Economic Development District | The primary challenges faced during the past quarter were related to an electric cooperative needing to re-conductor a power line and replacing the associated poles, prior to REDI Net installing its fiber optic cable. In addition, a lengthy negotiation with the US Dept of Energy, for attaching fiber cable to their utility poles (associated with an approved route change), also impeded on construction progress. These two events were the primary causes for needing to demobilize our aerial fiber construction crews. Although we experienced workflow disruptions this past quarter, due to the pole replacements delays and pole attachment negotiations, we were able to complete 20 new miles of fiber construction and currently stand at 119 of the 142 new miles completed. | In the upcoming reporting period, we expect to finalize construction of the majority of the route changes as we near project completion - provided that pole replacement activities continue as scheduled with the electric utility. The US Dept of Energy pole attachment agreement will also need to be executed to meet our quarterly objectives. In the upcoming reporting period, we intend to "go-live" with production quality wholesale broadband services to CAIs and last-mile providers, provided that the associated SLAs are finalized. | TRUE
NT10BIX5570116 | 2013 | Q1 | Q1 - 2013 | - Construction activities: ~10 new network miles deployed during the reporting period. 20 new network miles were forecasted. Variance relating to delays with US Dept of Energy (DOE) agreement and pole replacements. Aerial crews remobilized 2/19/13. - Network operations: Network "went live" on 2/1/2013, as previously forecasted, for completed portions of the network. 35 CAIs currently under billing. Others under SLA negotiation and/or trial services. - Contracts and Agreements: US DOE pole attachment agreement signed. Outside Plant Maintenance agreement being finalized, utilizing State of NM approved contract. This is a separate agreement from the previously negotiated Network Operations Center agreement previously execututed with Kit Carson Electric Cooperative and Telecom, referenced in response to question 5d. Last-mile provider and CAI Service Level Agreements (SLAs) signed, with others under negotiation. | 133 | 0 | 5 | 0 | 133 | 2 | 0 | 2 | 132.5 new miles completed. Catching up with original baseline, although still behind due to EA, EA Addendum, and make-ready | N/A | 5.33 miles of existing fiber upgraded | N/A | 132.5 new miles completed. Catching up with original baseline, although still behind due to EA, EA Addendum, and make-ready | 2 new microwave backbone connections were built, 1 of which is currently operational. Reflective of approved route change. | N/A. The 2 microwave links attach to existing structures. | 2 POIs operational as of the reporting period, with 1 IP transit interconnect established. | 1 | 2 | 4 | REDI Net has a signed SLA with Plateau Telecommunications. | The REDI Net Board and Finance Committee are continuously evaluating new wholesale offerings and related policy considerations, for services such as additional tiers of Ethernet transport, Internet access, and co-location. The Board will ensure these requests do not negatively impact current bandwidth commitments to CAIs and other last-mile providers, and would not in the next five years cause REDI Net to exceed its oversubscription rate or fiber asset management strategy. REDI Net is currently billing for network services in production, via SLAs, and supported by the 24x7 NOC. See attached service tiers and pricing. REDI Net is also offering "trial" services to a limited number of CAIs, to aid in stabilizing the network operating environment and establishing baseline performance data. | REDI Net has signed a three-year Network Management Agreement with Kit Carson Electric Cooperative and Telecom, as described in the original BTOP grant application. Kit Carson Telecom will provide network management for 100% of REDI Net. Kit Carson Telecom is not a sub-recipient, contractor or subcontractor under the BTOP grant, but is providing network management at no charge to REDI Net for its first 3 years of operation. Address: 201 Cruz Alta Road, Suite B, Taos NM, 87571. The main Point of Contact for REDI Net NOC services is Terie Hannay, SVP - Planning and Integration, 616-293-5880, terie@pulsebroadband.net | 1 | 0 | 0 | 1 | REDI Net signed an SLA with Plateau Telecommunications, a last-mile "E-Rate" provider. The baseline had projected 6 signed agreements. The variance is primarily associated with the number of additional agreements currently under negotiation, consolidation amongst local service providers in the market, and service provider organizational restructuring. | N/A | N/A | Standard services are offered between 1 Mbps to 100 Mbps and the number of subscribers per service tier are indicated below. 1 Mbps = 0 subscribers 3 Mbps = 0 subscribers 5 Mbps = 4 subscribers 10 Mbps = 0 subscribers 15 Mbps = 0 subscribers 20 Mbps = 2 subscribers 35 Mbps = 0 subscribers 50 Mbps = 3 subscribers 75 Mbps = 0 subscribers 100 Mbps = 1 subscriber During the reporting period, REDI Net provided multiple speed tiers to a single last-mile provider (Plateau Telecommunications), based on destination address of where the service was delivered. | 97 | 97 | 0 | 97 | A cumulative total of 97 CAIs are connected as of the reporting period, with network access available. Of which, 35 CAIs are currently being billed for services and supported by the 24x7 NOC. The variance is reflective of other CAIs that are under a "provisional" trial period, to aid in network testing and establishing performance baseline data, and CAIs that are still negotiating SLAs. Furthermore, setbacks on the construction schedule, associated with the extended EA process, EA addendum, and other "make-ready" issues also impacted CAI service availability. The original baseline projected 127 CAIs connected at project end and the current forecast at completion is 119. The delta is reflective of the approved route changes, removing some locations that were classified as "businesses" (rather than CAI) and other government sites that were deemed recreational and ineligable for grant funding. | See above. 97 CAIs have access to service from REDI Net. | N/A | Standard services are offered between 1 Mbps to 100 Mbps. Of the 97 CAIs connected, 35 are currently subscribing to paid-for "production" services, as itemized below: 1 Mbps = 8 CAIs 3 Mbps = 0 CAIs 5 Mbps = 16 CAIs 10 Mbps = 1 CAIs 15 Mbps = 0 CAIs 20 Mbps = 4 CAIs 35 Mbps = 0 CAIs 50 Mbps = 4 CAIs 75 Mbps = 0 CAIs 100 Mbps = 2 CAIs 62 CAIs are not subscribing to services at this point, with no speed tier negotiated. The shift in subscriptions per service tier, compared with previous reporting periods, is reflective of CAI requests when moving from "trial" to "production" services. There was no loss of CAIs from the previous reporting period, only a change in reporting. Previous reports reflected the CAI "trial" participants, whereas the current report reflects CAIs actually paying for subscriptions to "production" services. | 17304 | 0 | 0 | 0 | 0 | Estimate based on 90% of infrastructure build-out complete. Although, REDI Net is not a last-mile provider. | N/A | N/A | N/A | N/A | 1199 | 0 | 0 | 0 | 0 | Estimate based on 90% of infrastructure build-out complete. Although, REDI Net is not a last-mile provider. | N/A | N/A | N/A | N/A | REDI Net will provide the following service offerings: For community anchor institutions: Bundled Internet/Ethernet Access, Ethernet Transport. For last-mile service providers: Per Subscriber Bandwidth, Aggregated Internet Bandwidth, Ethernet Transport, Co-location. | FALSE | N/A | During the upcoming quarter, REDI Net's forecast is to complete construction activities for network build-out, including 10 new miles of fiber plant and connections to the remaining 22 CAIs. This will include connecting our second microwave link to Los Alamos County, to the REDI Net backbone, as well as completing a short fiber backbone segment to the community of Embudo/Rinconada. Those two activities, in particular, require coordination with the local electric co-op and their completion of make-ready activities. Testing will continue on new network segments as well as service activation for CAIs/LMPs with signed SLAs. 2 POPs will be operational at the end of the upcoming reporting period: Espanola POP and Los Alamos POP, which also serve as the POIs. REDI Net estimates that 2 LMPs with signed SLAs will be connected to the POIs during the upcoming reporting period (Plateau Telecommunications and Los Alamos Network). Near the end of the upcoming reporting period, project close-out steps will commence. | North Central New Mexico Economic Development District | The primary challenges faced this quarter were similar to the previous reporting period, relating to a lengthy negotiation with the US Dept of Energy, for attaching fiber cable to their utility poles (associated with an approved route change). However, that negotiation completed successfully during the current reporting period and construction began on that route. Also, the main electric cooperative that REDI Net works with for pole attachment selected its contractor for re-conductoring a power line and replacing the associated poles - a prerequisite for REDI Net installing its fiber optic cable. Pre-construction activities for that route are schedule for mid-April 2013, with work to commence shortly thereafter. These two events were the primary causes for needing to demobilize/remobilize our aerial fiber construction crews. Although we experienced the respective workflow disruptions this quarter, we were able to complete 10 new miles of fiber construction and currently stand at 132.5 miles completed, of the 142.6 new miles to be built. ~93% of the total new mileage. The original baseline assumed ~149 new miles to be built. The difference is associated with the approved route changes. | In the upcoming quarter we anticipate the US Department of Energy route to be completed with all pole attachments in place. Progress with the electric utility has occurred this quarter and should be on track for completion of fiber pole attachments along remaining routes next quarter. Will continue to work with community anchor institutions and service providers to complete negotiations for service level agreements | TRUE
NT10BIX5570116 | 2013 | Q2 | Q2 - 2013 | - Construction activities: ~6.5 new network miles deployed during the reporting period. 10 new network miles were forecasted. Variance due to pending make-ready activities with electric co-op. In total, 108 of the 115 CAIs are currently connected to REDI Net. The total number of forecasted CAIs has been lowered to 115, as 4 sites were deemed not to be CAIs (although funding eligible). Other significant accomplishments include completing the fiber cable installation to the second microwave site, which serves as a redundant backbone connection between the REDI Net POPs in Espanola and Los Alamos. - Network operations: Of the 108 CAIs connected, 39 are currently being billed for production services. 3 LMPs are also receiving service from REDI Net (Cyber Mesa, Los Alamos Network, and Plateau Telecommunications). Other CAIs and LMPs under SLA negotiation and/or trial services. Coordinating router upgrade with NOC for performance enhancements and dynamic load balancing on backbone circuits. Refining operational procedures and service profiles. - Contracts and Agreements: REDI Net executed 1 Last Mile Service Provider Agreement during this period. | 137 | 0 | 5 | 0 | 137 | 2 | 0 | 4 | 137.3 new miles completed. Catching up with original baseline, although still behind due to EA, EA Addendum, and make-ready | N/A | 5.33 miles of existing fiber upgraded | N/A | 137.3 new miles completed. Catching up with original baseline, although still behind due to EA, EA Addendum, and make-ready | 2 new microwave backbone connections were built, pursuant to approved route changes. | N/A. The 2 microwave links attach to existing structures. | 4 POIs operational as of the reporting period, which includes 1 IP transit interconnect. 1 LMP (Cyber Mesa) is served from the Espanola POP, 2 LMPs (Los Alamos Network & Plateau Telecommunications) are served from the Los Alamos POP, and 1 IP transit interconnect (Plateau Telecommunications) is provisioned at the Espanola POP. | 3 | 2 | 4 | REDI Net has signed SLAs with Plateau Telecommunications, Los Alamos Network, and Cyber Mesa. | The REDI Net Board and Finance Committee are continuously evaluating new wholesale offerings and related policy considerations, for services such as additional tiers of Ethernet transport, Internet access, and co-location. The Board will ensure these requests do not negatively impact current bandwidth commitments to CAIs and other last-mile providers, and would not in the next five years cause REDI Net to exceed its oversubscription rate or fiber asset management strategy. REDI Net is currently billing for network services in production, via SLAs, and supported by the 24x7 NOC. See attached service tiers and pricing. REDI Net is also offering "trial" services to a limited number of CAIs, to aid in stabilizing the network operating environment and establishing baseline performance data. | REDI Net has signed a three-year Network Management Agreement with Kit Carson Electric Cooperative and Telecom, as described in the original BTOP grant application. Kit Carson Telecom will provide network management for 100% of REDI Net. Kit Carson Telecom is not a sub-recipient, contractor or subcontractor under the BTOP grant, but is providing network management at no charge to REDI Net for its first 3 years of operation. Address: 201 Cruz Alta Road, Suite B, Taos NM, 87571. The main Point of Contact for REDI Net NOC services is Terie Hannay, SVP - Planning and Integration, 616-293-5880, terie@pulsebroadband.net | 3 | 0 | 0 | 3 | REDI Net signed SLAs with Plateau Telecommunications, Cyber Mesa, and Los Alamos Network. Both Cyber Mesa and Plateau Telecommunications serve as last-mile "E-Rate" providers to public school districts. The baseline had projected 6 signed agreements. The variance is primarily associated with the number of additional agreements currently under negotiation, consolidation amongst local service providers in the market, and service provider organizational restructuring. | N/A | N/A | Standard services are offered between 1 Mbps to 100 Mbps and the number of subscribers per service tier are indicated below. 1 Mbps = 0 subscribers 3 Mbps = 0 subscribers 5 Mbps = 4 subscribers 10 Mbps = 0 subscribers 15 Mbps = 0 subscribers 20 Mbps = 4 subscribers 35 Mbps = 0 subscribers 50 Mbps = 5 subscribers 75 Mbps = 0 subscribers 100 Mbps = 2 subscriber During the reporting period, REDI Net provided multiple speed tiers to the 3 last-mile providers indicated above, based on destination address of where the service was delivered. | 108 | 108 | 0 | 108 | A cumulative total of 108 CAIs are connected as of the reporting period, with network access available. Of which, 39 CAIs are currently being billed for services and supported by the 24x7 NOC. The difference of 69 CAIs is reflective of those that are under a "provisional" trial period, to aid in network testing and establishing performance baseline data, and CAIs that are still negotiating SLAs. The original baseline projected 127 CAIs connected at project end and the current forecast is for 115. The 1Q12 PPR reported 97 CAIs connected at that point and forecasted 119 CAIs at project end. The variances in the forecasts are associated with approved route changes, removing some locations that were re-classified as "businesses" (rather than CAIs), and removing other government sites deemed recreational and ineligible for grant funding. Also, Q9 in this PPR reports 16 additional CAIs connected. Adding the 14 new CAIs to the 97 reported in the previous period, minus 3 that were mistakenly reported in duplicate, equals 108 currently connected. | See above. 108 CAIs have access to service from REDI Net. | N/A | Standard services are offered between 1 Mbps to 100 Mbps. Of the 108 CAIs connected, 39 are currently subscribing to paid-for "production" services, as itemized below: 1 Mbps = 9 CAIs 3 Mbps = 1 CAIs 5 Mbps = 16 CAIs 10 Mbps = 1 CAIs 15 Mbps = 0 CAIs 20 Mbps = 6 CAIs 35 Mbps = 0 CAIs 50 Mbps = 4 CAIs 75 Mbps = 0 CAIs 100 Mbps = 2 CAIs 70 CAIs are not subscribing to services at this point, with no speed tier negotiated. | 18458 | 0 | 0 | 0 | 0 | Estimate based on 96% of infrastructure build-out complete. Although, REDI Net is not a last-mile provider. | N/A | N/A | N/A | N/A | 1279 | 0 | 0 | 0 | 0 | Estimate based on 96% of infrastructure build-out complete. Although, REDI Net is not a last-mile provider. | N/A | N/A | N/A | N/A | REDI Net will provide the following service offerings: For community anchor institutions: Bundled Internet/Ethernet Access, Ethernet Transport. For last-mile service providers: Per Subscriber Bandwidth, Aggregated Internet Bandwidth, Ethernet Transport, Co-location. | FALSE | N/A | During the upcoming reporting period, REDI Net plans to complete the project grant requirements. Planned work activities include, but not limited to, reviewing construction as-built drawings, drafting Federal security interest forms as part of transferring the network assets to the jurisdictional partners, and submitting State of NM UCC filings. Particular focus will be on efforts relating to the transition from construction into network/business operations. This includes optimization of network operations policies and procedures, continued negotiation of LMP/CAI SLAs, expansion with existing LMPs/CAIs, community outreach, business development, and increasing education/awareness of REDI Net. In the next quarter, REDI Net forecasts to build ~.25 miles of new fiber cable, connect an additional 3 CAIs, and execute 1 new broadband wholesaler/last mile provider agreements. | North Central New Mexico Economic Development District | The primary challenge faced this quarter was similar to the previous reporting period, relating to a lengthy make-ready process with an electric co-op to complete pole replacements along a backbone route that feeds a REDI Net microwave site and 2 CAIs. However, those make-ready activities were completed successfully during the reporting period, which enabled REDI Net to complete its fiber installation and splicing along that route. Although we experienced the respective workflow disruptions this quarter, we were able to complete ~6.5 new miles of fiber construction and currently stand at 137.3 miles of the ~142.6 new miles to be built. ~96% of the total new mileage. The original baseline assumed ~149 new miles to be built. The difference is associated with the approved route changes. | While migrating into grant closeout activities, approval of Federal security interest and/or State of NM UCC filings will involve significant coordination with jurisdictional partners and processing via outside agencies which REDI Net has no direct control over. This makes forecasting the completion of the forms challenging to project with a high degree of accuracy. REDI Net has requested grant extension until 9/30/2013 to accommodate completing these final construction activities | TRUE
NT10BIX5570116 | 2013 | Q3 | Q3 - 2013 | Overall project status: This quarter signifies the completion of the REDI Net NTIA BTOP grant period, but just the beginning of a long-term investment in community infrastructure development. From the onset, REDI Net's goals and ambitions were to enable affordable, "open access" to ultra high-speed broadband services in the North Central region of New Mexico. The rural REDI Net communities were at economic, educational, and medical disadvantages from being unserved or underserved, as urbanized areas continued to progress with technological advancements. REDI Net is pleased to report that it has accomplished a great deal during the grant period, by investing in rural, community-owned broadband infrastructure, that is already being utilized for delivering tele-medicine services, distance learning applications, and critical communications for emergency first-responders, in collaboration with 4 local governments (Santa Fe County, Los Alamos County, Rio Arriba County, and the City of Espanola), 4 sovereign tribal nations (Tesuque Pueblo, Pojoaque Pueblo, Santa Clara Pueblo, and Ohkay Owingeh), and several private sector service provider partners. The following are examples of current REDI Net uses and public benefits: REDI Net is currently providing affordable, high-speed access over its community open-fiber network to the public schools in Los Alamos County and Espanola, NM. REDI Net is delivering local network (i.e. VPN) and Internet services for the schools as speeds from 5Mbps to 100Mbps, which are used for enabling e-curriculum, student research, video remote classroom, VoIP phone conferences, and public safety connections to local law enforcement for emergency communications - all while lowering cost and improving reliability of telecommunication services. Previously, the public schools were customarily served by T1, bonded T1, DS3, or wireless connections. The County governments of Los Alamos and Rio Arriba, NM, and the City of Espanola, NM are utilizing REDI Net for 50-100Mbps Internet services, in concert with local VPN connections at speeds starting at 1Mbps. The bandwidth enables the Counties and City to provide government services such as wireless public access at municipal complexes, recording and broadcast of Council meetings, Internet access for public housing and community centers, and critical communication links to police and fire first-responders. The REDI Net fiber optic infrastructure accomplishes this by providing higher performing, more affordable services than the DSL, T1, bonded T1, and DS3 lines that it replaced. The Pueblo's of Tesuque, Santa Clara, and Ohkay Owingeh are utilizing REDI Net for a variety of network services, such as high-speed Internet access and local VPN connections to their schools, libraries, day-care, community and wellness centers, medical and public safety institutions. The REDI Net infrastructure enables the delivery of curriculum and system updates in a matter of minutes, that previously would have taken several hours over the legacy networks. Libraries are able to video conference with remote resources. Medical offices are able to communicate in real-time with physicians at adjunct facilities. Police and fire departments now have the network capacity needed to establish high-speed, reliable communication with first-responders, providing real-time access to criminal databases, and delivering field information to aid office safety. The main REDI Net Internet feeds to the Pueblos are provisioned at 20Mbps and the local Ethernet VPN connections are from 1Mbps to 5Mbps, replacing the previous DSL, T1, or bonded T1 services. REDI Net currently provides high speed network services to two higher education institutions (University of New Mexico - Los Alamos and New Mexico State University - Alcalde) and one research organization (New Mexico Consortium). UNM-LA utilizes 50 Mbps of Internet access for student access, e-curriculum, and remote connectivity to their main campus. NMSU-Alcalde utilizes REDI Net in a similar capacity, albeit at 3Mbps. The NM Consortium leverages REDI Net's high-speed Internet access to network with their research partners for collaboration on various science initiatives, as well as a 1Gbps Ethernet VPN connection to their main data center at the Los Alamos Research Park for modeling and computing. REDI Net delivered the critical communication infrastructure that otherwise would not have been available. Medical Associates of Northern NM and the El Centro Family Health Services network of rural healthcare clinics also subscribe to Internet access from REDI Net, with the initial use is mainly for improvements in transferring medial records and imaging. REDI Net also serves 3 last-mile providers (Plateau Telecommunications, Cyber Mesa, and Los Alamos Network) with affordable, wholesale bandwidth, helping to change their business models and markets served. While the above highlights only a few of the initial benefits REDI Net has brought to these rural communities, the long-term potential has barely been tapped. However, with the forethought that went into the infrastructure development, the result is a flexible, scalable network architecture to foster the development of future applications as technology continues to advance and bandwidth demands rise. Final network production as of the end of the reporting period is as follows: - Route miles: 136 new route miles were built (comprised of 108 linear miles of new fiber optic cable and 28 miles of microwave transmission) and 5 linear miles of existing fiber cable were upgraded, for a total of 141 network miles. - CAI Connections: 110 CAIs were connected to REDI Net at project end. - POIs: 2 Points-of-Interconnect were built by the end of the grant period. - Network Operations: Of the 110 CAIs connected, 51 are currently being billed for production services. 3 LMPs are also receiving service from REDI Net (Cyber Mesa, Los Alamos Network, and Plateau Telecommunications). | 136 | 0 | 5 | 0 | 108 | 2 | 0 | 2 | 136 new network miles were deployed. This is comprised of 108 linear miles of new fiber optic cable and 28 miles of new microwave transmission. The new fiber construction is reported in linear network miles, not actual fiber route mileage. Previous forecasts utilized actual fiber mileage, which included cable slack, storage, splicing, and building premise. Changing the reporting methodology to linear network miles has caused a reduction in total miles deployed. The original baseline forecasted 149 new network miles, which was also projected on actual fiber cabling, not linear mileage. That is a primary cause in the delta between 136 new network miles deployed and the original baseline, along with replacing a fiber backbone segment with microwave transmission, other approved route changes,and 2 network laterals that were not completed due to circumstances outside of REDI Net's control. The original baseline also forecasted upgrading 5 miles of fiber cable, which was completed. The 136 new network miles, combined with the 5 miles of existing fiber cable that was upgraded, results in a total network of 141 miles. | N/A | 5 miles of existing fiber upgraded, in-line with original baseline. | N/A | 108 new network miles of fiber were deployed. This is linear network miles, not actual fiber route mileage. Previous forecasts utilized actual fiber mileage, which included cable slack, storage, splicing, and building premise. Changing the reporting methodology to linear network miles has caused a reduction in total miles deployed. The original baseline forecasted 149 new network miles, which was also projected on actual fiber cabling, not linear mileage. That is the main cause in the delta between 108 new network miles deployed and the original baseline, along with 2 network laterals that were not completed and the previously approved route changes. | 2 new microwave backbone connections were built, pursuant to approved route changes, for a total of 28 route miles of microwave transmission. One microwave link (14.5 miles) is established between the Barranca Mesa Water Tower in Los Alamos, NM and the Quintana Elementary School in Espanola, NM. The other microwave link (13.5 miles) is established between the North Mesa Water Tower in Los Alamos, NM and the Pojoaque Pueblo Industrial Park. | N/A. The 2 microwave links attach to existing structures. | 2 POIs were completed as of the end of the grant period: Espanola POP and Los Alamos POP. The original baseline forecasted 127 POIs, but that included 123 CAIs in the count - so that actual forecast was 4 facilities-based POIs. The 2 POIs that were not completed during the reporting period are pending 3rd party networks to complete their fiber builds to the POIs, but this is anticipated being finished post-BTOP. 1 of the POIs is the Santa Fe POP, and while the facility construction was completed during the grant period, the 3rd party fiber build to the facility is still pending. The other POI is a mid-span meet point, also awaiting a 3rd party fiber build to be completed to it. | 3 | 0 | 4 | REDI Net has signed SLAs with Plateau Telecommunications, Los Alamos Network, and CyberMesa. The original baseline assumed 7 signed agreements by grant end date. The delta is associated with current market dynamics, industry consolidation, and pending SLAs | REDI Net wholesale services for CAIs and LMPs, as of the grant end date, are as follows: 1 Mbps, Ethernet & Internet Bundle, $80.00 MRC; 1 Mbps, Ethernet Only, $60.00 MRC 3 Mbps, Ethernet & Internet Bundle, $210.00 MRC; 3 Mbps, Ethernet Only, $157.50 MRC 5 Mbps, Ethernet & Internet Bundle, $300.00 MRC; 5 Mbps, Ethernet Only, $225.00 MRC 10 Mbps, Ethernet & Internet Bundle, $500.00 MRC; 5 Mbps, Ethernet Only, $375.00 MRC 15 Mbps, Ethernet & Internet Bundle, $675.00 MRC; 15 Mbps, Ethernet Only, $506.25 MRC 20 Mbps, Ethernet & Internet Bundle, $800.00 MRC; 20 Mbps, Ethernet Only, $600.00 MRC 35 Mbps, Ethernet & Internet Bundle, $1,050.00 MRC; 35 Mbps, Ethernet Only, $787.50 MRC 50 Mbps, Ethernet & Internet Bundle, $1,200.00 MRC; 50 Mbps, Ethernet Only, $900.00 MRC 75 Mbps, Ethernet & Internet Bundle, $1,575.00 MRC; 75 Mbps, Ethernet Only, $1,181.25 MRC 100 Mbps, Ethernet & Internet Bundle, $1,800.00 MRC; 100 Mbps, Ethernet Only, $1,350.00 MRC 1 Gbps, Ethernet & Internet Bundle, custom quote; 1 Gbps, Ethernet Only, custom quote Services above 100 Mbps are quoted on a case-by-case basis, pending engineering analysis, network resource availability, and subcommittee review. For last-mile service providers, REDI Net also offers co-location services, on a similar custom quote process. | REDI Net has signed a three-year Network Management Agreement with Kit Carson Electric Cooperative and Telecom, as described in the original BTOP grant application. Kit Carson Telecom will provide network management for 100% of REDI Net. Kit Carson Telecom is not a sub-recipient, contractor or subcontractor under the BTOP grant, but is providing network management at no charge to REDI Net for its first 3 years of operation. Address: 201 Cruz Alta Road, Suite B, Taos NM, 87571. The main Point of Contact for REDI Net NOC services is Terie Hannay, SVP - Planning and Integration, 616-293-5880, terie@pulsebroadband.net. Two Operations & Maintenance (O&M) agreements were signed for emergence response services. One of the O&M agreements is with Integrated Technologies Corporation (ITC), for supporting the outside fiber plant and customer premise electronics. ITC serves as a contractor to REDI Net in this capacity. Address: 2732 Vassar Place, NE Suite E, Albuquerque, NM 87107. The main Point of Contact at ITC is Bob Kinney, Vice President, 505-883-4113, btkinney@itc4u.com. The other O&M agreement was signed with Advanced Communications & Electronics, for supporting the microwave system. Advanced Communications & Electronics serves as a contractor to REDI Net in this capacity. Address: 2417 Baylor Dr. SE, Albuquerque, NM 87106. The main POC at Advanced Communications & Electronics is Patrick Mosca, Director of Services, 505-244-3321 x118, pmosca@advtwoway.com. | 3 | 0 | 0 | 11 | REDI Net signed SLAs with Plateau Telecommunications, Cyber Mesa, and Los Alamos Network. Both Cyber Mesa and Plateau Telecommunications serve as last-mile "E-Rate" providers to public school districts. The baseline had projected 6 signed SLAs. The variance is primarily associated with the number of pending agreements, consolidation amongst local service providers in the market, and service provider organizational restructuring. | N/A | N/A | Standard services are offered between 1 Mbps to 100 Mbps and the number of subscribers per service tier are indicated below. 1 Mbps = 0 subscribers 3 Mbps = 0 subscribers 5 Mbps = 4 subscribers 10 Mbps = 0 subscribers 15 Mbps = 0 subscribers 20 Mbps = 4 subscribers 35 Mbps = 0 subscribers 50 Mbps = 5 subscribers 75 Mbps = 0 subscribers 100 Mbps = 2 subscriber 1 Gbps = 0 subscribers During the reporting period, REDI Net provided multiple speed tiers to the 3 last-mile providers indicated above, based on destination address of where the service was delivered. Services >100 Mbps are quoted on a case-by-case basis, pending engineering analysis, network resource availability, and subcommittee review. Previous reporting periods had reflected the number of wholesalers in the "Total" column, but this has now been changed, per BTOP guidance, to reflect the number of tiers. | 110 | 110 | 0 | 11 | A cumulative total of 110 CAIs were connected as of the grant end date with network access available. 51 CAIs are currently being billed for services and supported by the 24x7 NOC and the other 59 CAIs would be activated pending signed SLAs. The original baseline projected 123 CAIs connected at project end. The delta between 123 CAIs forecasted and 110 completed is 13 CAIs. The 13 CAIs not completed are associated with approved route changes, removing some locations that were re-classified as "businesses" (rather than CAIs), removing other government sites deemed recreational and ineligible for grant funding, and being unable to complete 2 fiber laterals due to make-ready and permitting delays outside of REDI Net's control. As the result of the permitting and make-ready delays mentioned above, 5 CAIs were not connected, along with 8 sites that were reclassified as businesses, rather than CAIs, and other sites deemed recreational and ineligible for grant funding. Reference the 2013 Annual Performance Report for a complete list of 110 CAIs connected. | See above. 110 CAIs have access to service from REDI Net. | N/A | Standard services are offered between 1 Mbps to 100 Mbps. Of the 110 CAIs connected, 51 are currently subscribing to paid-for "production" services, as itemized below: 1 Mbps = 12 CAIs 3 Mbps = 3 CAIs 5 Mbps = 16 CAIs 10 Mbps = 2 CAIs 15 Mbps = 0 CAIs 20 Mbps = 8 CAIs 35 Mbps = 0 CAIs 50 Mbps = 6 CAIs 75 Mbps = 0 CAIs 100 Mbps = 3 CAIs 1Gbps = 1 CAI 59 CAIs are not subscribing to services at this point, with no speed tier negotiated. Previous reporting periods had reflected the number of CAIs in the "Total" column, but this has now been changed, per BTOP guidance, to reflect the number of speed tiers. | 0 | 0 | 0 | 0 | 0 | N/A. In previous reporting periods, REDI Net provided estimates on number of residences/households passed, based on fiber routes completed. However, since REDI Net is a middle-mile network and not a last-mile provider, BTOP has advised to remove these estimates from the PPR. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A. In previous reporting periods, REDI Net provided estimates on number of businesses passed, based on fiber routes completed. However, since REDI Net is a middle-mile network and not a last-mile provider, BTOP has advised to remove these estimates from the PPR. | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Project award end date was 9/30/13. For the upcoming quarter, REDI Net has SLAs under negotiation with 3 additional Last-Mile Providers, to further extend affordable access to residential and business subscribers in the service area, and perhaps into new service areas as well. REDI Net is also in discussions with surrounding Counties and Tribal areas on infrastructure partnerships to extend REDI Net's reach into rural areas with needs for "open-access" to affordable, high-speed network connectivity for their communities. In addition, REDI Net is working with the State of New Mexico legislature on capital outlay requests, which could be utilized for completing planned and designed fiber routes that were not able to be completed during the grant period, aid in the expansion of REDI Net into unserved/underserved areas, and/or to add further capacity/redundancy to the system. REDI Net also intends to work with project partners on developing content to assist with the education of REDI Net and its capabilities, and further broadband adoption in the communities. We continue to work with the state departments and policy makers to address opportunities related to telehealth, tele-medicine, distance learning/education and economic development. | North Central New Mexico Economic Development District | The primary challenges faced were similar to previous reporting periods, relating to lengthy make-ready procedures with an electric co-op and associated permitting, outside of REDI Net's control. Those delays resulted in 2 network laterals (totalling 5 miles) not being able to be completed during the grant period and 5 CAIs not being connected. One lateral was to extend 4 miles of infrastructure in the San Pedro and La Mesilla areas of Rio Arriba County, where 3 CAIs were to be connected: San Pedro Health Clinic / Community Center, San Pedro Fire Station and the La Mesilla Fire Station. The other lateral would have completed build out to the community of Embudo in Rio Arriba County, to serve the Embudo Medical Clinic and Dixon/Rinconada Fire Station. REDI Net is still committed to completing those network laterals and CAI connections as part of its infrastructure reinvestment strategy, subject to funding availability. | Project award end date was 9/30/13. | TRUE
NT10BIX5570117 | 2010 | Q4 | Q4 - 2010 | Approximately 70 miles of South Carolina Department of Transportation permitting has been completed. We attended the BTOP conference in November. We did an official kick-off ceremony to introduce the project to the public. Prepared Environmental Assessment to be submitted in January. Met with the National Forestry personnel regarding the Environmental Assessment .Worked on Request for Proposals for the installation of fiber and the request for bid on fiber. Contract will be awarded for installation of fiber in the next quarter. Negotiating Direct Internet Access with multiple vendors. Readiness review of tri-city network operation centers. Set up separate bank account for broadband purposes. A new team member will be hired beginning next quarter. We are compiling information for other Request for Proposals that will be start in the coming months. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 1 | 0 | none at this time | N/A | N/A | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | na | FALSE | na | We plan to have our Environmental Assessment application submitted and waiting on Finding of no significant impact. We should have the permits completed for the entire network. When we are approved for our FONSI, we plan to start installing fiber. We plan to have the Request for Proposals completed for the fiber vendor, inside and outside plant manager and a vendor for some of the equipment. | Oconee County | na | At this time we do not for see any issues or challenges. | TRUE
NT10BIX5570117 | 2011 | Q1 | Q1 - 2011 | We awarded the contract for the fiber to OFS. We awarded the contract for the fiber installation to Southern Pipeline Utility. We submitted our first draft of the Environmental Assessment to the NTIA. Responded to all the tribal requests concerning the Environmental Assessment. Worked with the National Forestry Service to obtain permitting through National Forestry land. Negotiated Direct Internet Access (DIA) with vendors. Worked on the Request for Proposal (RFP) for equipment. Met with the Senate subcommittee concerning bill H3508 that was passed in the House and sent to the Senate. Met with AT&T concerning the bill. Tried to work out sections of the bill the County does not agree with. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In our baseline we showed 25 new network miles deployed by the end of the quarter. We are behind due to issues with the bill H3508 and how it could impact our project. We are also behind due to fiber installation contractor being unable to obtain performance bond. We hope to be on target by the end of the second quarter of 2011. | na | na | na | In our baseline we showed 25 new network miles deployed by the end of the quarter. We are behind due to issues with the bill H3508 and how it could impact our project. We are also behind due to fiber installation contractor being unable to obtain performance bond. We hope to be on target by the end of the second quarter of 2011. | na | na | na | 0 | 3 | 0 | At this time we do not have any signed agreements. The providers are waiting for us to begin the installation process before signing any agreements. | na | na | 0 | 0 | 0 | 0 | In our baseline we showed 1 provider with a signed agreement receiving access. We are behind due to issues with the bill H3508 and how it could impact our project. We are also behind due to fiber installation contractor being unable to obtain performance bond. We hope to be on target by the end of the second quarter of 2011. | na | In our baseline we showed 1 provider with a signed agreement receiving access. We are behind due to issues with the bill H3508 and how it could impact our project. We are also behind due to fiber installation contractor being unable to obtain performance bond. We hope to be on target by the end of the second quarter of 2011 | na | 0 | 0 | 0 | 0 | In our baseline we showed 8 subscribers being served. We are behind due to issues with the bill H3508 and how it could impact our project. We are also behind due to fiber installation contractor being unable to obtain performance bond. We hope to be on target by the end of the second quarter of 2011 | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | na | FALSE | na | We hope to have our FONSI and begin installation of fiber. We will be sending our a Request for Proposal (RFP) for some of the equipment. We plan in awarding the inside and outside managers. Should have +/- 95% of the permitting of route complete. Plan on having the permit from the National Forestry Service. | Oconee County | We have spent a lot of time dealing with the bill H3508 and AT&T. It has taken a lot of time dealing with the legal language and trying to find a resolution to our concerns with the bill. | The demand for fiber has risen due to the disaster in Japan. There are other applicants that are ready to install the fiber and are ordering the fiber for their projects. The bill H3508 will still an issue in the next quarter. No resolution has been found as of the end of this quarter. | TRUE
NT10BIX5570117 | 2011 | Q2 | Q2 - 2011 | During this quarter we released a revised Request for Proposal for the fiber installation. FOCUS employees attended Department of Labor Seminar. Attended meetings with potential Internet Service Providers. Met with the Judiciary subcommittee over concerns with the bill the was passed in the House and sent to the Judiciary Subcommittee. In June we received our FONSI (Finding of No Significant Impact). The FOCUS team worked on Request for Proposal for outside and inside plant manager. Composed bid for Engineering and Permitting. Reconstructed maps for phase I of project. During this quarter we completed out first draw down. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We are behind schedule due to the fiber installation RFP being released again. We hope to be on target at the end of the third quarter of 2011. | na | na | na | We are behind schedule due to the fiber installation RFP being released again. We hope to be on target at the end of the third quarter of 2011. | na | na | na | 0 | 3 | 0 | na | na | na | 0 | 0 | 0 | 0 | We are behind schedule due to the fiber installation RFP being released again. We hope to be on target at the end of the third quarter of 2011. | na | We are behind schedule due to the fiber installation RFP being released again. We hope to be on target at the end of the third quarter of 2011. | na | 0 | 0 | 0 | 0 | We are behind schedule due to the fiber installation RFP being released again. We hope to be on target at the end of the third quarter of 2011. | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | na | FALSE | na | We plan to have our fiber order on schedule for delivery. Without a fiber installation vendor we were unable to purchase equipment/supplies. A vendor will be selected next quarter for the fiber installation. We will also select a vendor for the engineering/permitting in the next quarter. We also plan on awarding the inside and outside plant managers. With the selections of a fiber installation vendor and an engineering/permitting vendor being accomplished we believe we will be able to get back on track. We will be working closely with the engineering/permitting contractor and hope to have most if not all of the permitting completed by the end of next quarter. The selected vendor for the fiber installation has a start date of late August. At that point we will be able to start construction of the network. Steps we are taking to catch up on our milestones are as follows: 1)Fiber installation contract, for the first 95 miles, to be signed on August 8th with construction to begin by last week of August. 2)Engineering/Permitting contract to be signed on August 8th with the work to being August 9th. 3)All electronics to be purchased by the end of the 4th quarter. 4)Two of the three network control centers will be up and running by the end of the 4th quarter. | Oconee County | Our percentages of completion are off schedule based upon the decision to release the RFP(request for Proposal) for the fiber installation again. The FOCUS team revised the RFP and broke the project up in to segments. The team had to rework the maps to show the segments that would be installed during the first phase. During this quarter we also spent a lot of time dealing with the bill that was passed in the House and sent to the Judiciary subcommittee. | At this time we are in queue for our fiber delivery. We anticipate that the fiber will be ready for delivery but will put the project behind schedule if it is not delivered on time. | TRUE
NT10BIX5570117 | 2011 | Q3 | Q3 - 2011 | Oconee County has been very busy this quarter. We released the Request for Proposal (RFP) for the fiber installation. It was awarded to Network Controls of Greer, SC. At the end of the third quarter Network Controls and subcontractor, JET Commercial of Seneca, SC had installed ~157,000 feet (30 miles) of conduit. During this quarter we had ~30 miles of fiber delivered. A variety a fiber counts were delivered. Oconee County released another RFP for the Engineering and Permitting. It was awarded to GeoVision of Sylva, NC. At the end of the third quarter GeoVision had engineered 156 miles. Oconee County released a RFP for the Systems Operator and we also released a Request for Bid for the optical switching equipment. The team met with the National Forestry Service. We walked the route to see if a endangered flower called the Smooth Cone Flower would be disturbed by the installation of the network. We worked with the National Forestry Service to insure the flower would not be disturbed. Our permit was approved and were waiting for it to be mailed. On September 26th and 27th the broadband team met with the Federal Program Officers assigned to our grant. The site visit was informative. We reviewed a lot of information and took them to see the conduit being installed for phase I. Submitted three railroad crossing permits to Norfolk Southern. Have been in close contact with them to insure we get correctness to obtain the permits. Oconee County has chosen all three locations for our | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. Fiber has been an issue but we hope to have large shipments in the beginning of 2012. | na | na | na | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. Fiber has been an issue but we hope to have large shipments in the beginning of 2012. | na | na | na | 0 | 3 | 0 | na | na | na | 0 | 0 | 0 | 0 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. Fiber has been an issue but we hope to have large shipments in the beginning of 2012. | na | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. Fiber has been an issue but we hope to have large shipments in the beginning of 2012. | na | 0 | 0 | 0 | 0 | We are behind schedule still due to the fact we had to release the RFP again in the 2nd quarter. Fiber has been an issue but we hope to have large shipments in the beginning of 2012. | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | na | FALSE | na | Phase I should be around 85% complete. We plan to have most of the equipment ordered and shipped. We hope to have 2 agreements signed with wholesalers or last mile providers and being executed by the end of this quarter. We will release and hopefully award construction contracts for Phase 2 and will be working on the Request for Proposal for phase 3. We hope to have the Seneca network operation center up and running by the end of the next quarter. By the end of the next quarter there should be 75-80 network miles deployed. We hope to have a few public sessions to explain Broadband and address questions that are being submitted on our FOCUS website. We will have 5-7CAI's connected and served by the end of the next quarter. | Oconee County | This is a big project for Oconee County. The locators for all the utility companies have been overwhelmed with the amount of locates that are associated with the project. Fiber could still be a challenge for Oconee County. We hope to have large shipments being shipped the first quarter of 2012. | Weather could be an issue with winter around the bend. Rock can always slow the project down a little. Fiber may continue to be an issue but hopefully will be resolved by first quarter of 2012. | TRUE
NT10BIX5570117 | 2011 | Q4 | Q4 - 2011 | The fourth quarter has showed significant change in Oconee County. We have installed/buried ~ 80 miles of conduit. We have installed 128 hand holes. The crews ran in to an issue with rock during this phase. We have installed ~ 10 miles of fiber. The crews had tested a few machines to determine best machine for installation. We have approximately 12-14 crews on any given day throughout the County working on installation, tie ins, blowing of fiber, etc. The County received the permit package for the National Forestry Land. The permit will be reviewed and should be issued in the 1st quarter of 2012. The County worked with Norfolk Southern Railroad on the railroad permits. The broadband team have submitted 5 more railroad permits for approval. We should have all approved permits for the during 1st quarter of 2012. Two more reels of the 288 fiber were delivered in December. In the 3rd quarter of 2011 we released a couple of Request for Proposals. The Request for Proposals were awarded during the 4th quarter. The County awarded the contracts for System Operator and a contract for Tellabs network equipment. The Systems Operator was awarded to Technology Solutions of Seneca, SC. The network equipment contract was awarded to AFL of Duncan, SC. Some of the broadband team members attended the NTIA and OneCommunity conference in Cleveland, Ohio. The team met with awardees to discuss progress and issues with our respective projects. Oconee County shared best practices with several awardees around public relations, construction, and electronics. Oconee County set up a follow up meeting with Columbia County, GA. Like Oconee County they are an awardee of a BTOP grant. We spent two days with Columbia County. We shared a lot of great information with that team!! The team has been working with school district and other anchor institutions determining egress into the buildings. We have met with school district a few times to determine their needs for the schools. Egress drawings have been done for many of the CAI's that are to be connected in phase I of the project. We have bi-weekly meetings with our contractors and subcontractors to discuss progress, next steps, delays, etc. We purchased a fusion splicer and other miscellaneous equipment needed for installation. We are still a little behind, but feel confident a lot of progress will be made in the 1st quarter of 2012. | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | We are behind schedule. This will be an ongoing problem since we had to re-release the RFP during the 2nd quarter of 2011. The crews have accomplished a lot in the 4th quarter. We hope to continue great progress and meet our goals in the quarters to come. | na | na | na | We are behind schedule. This will be an ongoing problem since we had to re-release the RFP during the 2nd quarter of 2011. The crews have accomplished a lot in the 4th quarter. We hope to continue great progress and meet our goals in the quarters to come. | na | na | na | 0 | 3 | 0 | na | na | na | 0 | 0 | 0 | 0 | With the project being behind we do not have any signed last mile provider. We have been in the process of reviewing contracts and negotiating but no signed ones to date. | na | With the project being behind we do not have any signed last mile provider. We have been in the process of reviewing contracts and negotiating but no signed ones to date. | na | 0 | 0 | 0 | 0 | With the project being behind we do not have any signed last mile provider. We have been in the process of reviewing contracts and negotiating but no signed ones to date. | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | 0 | 0 | 0 | 0 | 0 | na | na | na | na | na | na | FALSE | na | The County plans to have Phase I completed and lit. We plan to have fiber connected to approximately 40-50% of our Community Anchors Institutions. We should be receiving 3 large shipments in the next quarter. Our network operation centers should be operating as such in the next quarter. The request for proposal for Phase II and III should be released in the next quarter. Most of the right of way and permits should be complete by the end of the next quarter. | Oconee County | Weather has been somewhat of an issue for the crews. The County had approximately 14 inches of rain in the 4th quarter. With significant amounts of rain it can stall forward progress that can be made. Rail road permits have been an issue for us. The process is a little more in depth than the County expected. The team has been working diligently with the rail road to help us with this process. The County started reviewing the House Bill that was to be reintroduced in January. A lot of progress was made in the 4th quarter. We have been behind for awhile but are working very hard to catch up to our base line plan. | The team will be focusing on the bill that has passed in the House and now is in Senate Subcommittee. Weather will continue to be a problem due to rain/snow. Rock maybe an issue in the phases to come as it was in phase I. | TRUE
NT10BIX5570117 | 2012 | Q1 | Q1 - 2012 | Approximately 114 miles of conduit and approximately 70 miles of fiber installed and spliced. Two of the three NOCs (Network Operations Center) has equipment, power, cooling, and fiber termination. Direct Internet Access (DIA) has been secured for the Community Anchor Institutes. A Contract is in the works for cellular back haul. The Request For Proposal (RFP) for the 2nd phase of the installation process was released this quarter. The RFP will be awarded in the next quarter activities. Project schedule for phase II and III has been complete. Approximately 10% of the anchor institutes have fiber installed and awaiting NOC setup completion to go live. We are in the process of adding the electronics to those anchors. We have 95% of our Right Of Ways (ROW) drawings complete and turned into the South Carolina Department of Transportation (SCDOT) for permitting. All required permits for entire FOCUS project will be turned into SCDOT in the 2nd quarter. We received two critical railroad permits from Norfolk Southern, who has been a great help to us regarding our permitting process. The broadband team has made several trips to Columbia, SC this quarter to attend hearings regarding the H3508 bill. At the end of last quarter the bill had been moved from Judiciary Committee to the full Senate. The bill has been put on a contested calendar but will be addressed some time during the 2nd quarter of 2012. We received 3 shipments of fiber optical cable this quarter. In the 2nd quarter all required fiber optical cable for the entire project will be delivered. The broadband team met with a local groups during this quarter to discuss broadband and how it helps the community as part of our outreach plan. | 114 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | We are very close to our baseline target. Right of way issues has slightly delayed network miles. | NA | NA | NA | We are very close to our baseline target. Right of way issues has slightly delayed new miles of fiber being installed. | NA | NA | Right of way issues has slightly delayed new new/upgraded interconnection points being operating. | 0 | 4 | 0 | Oconee County is negotiating with 4 wholesale/last mile providers. No agreements signed. | This is still under review by Oconee County and will require approval by County Council. Pricing structure in process. | Oconee County has secured a contractor through Request for Proposal (RFP). Technology Solution was awarded to install, configure, and operate network through construction. Technology Solution will connect, provision, maintain, and monitor network through construction. | 0 | 0 | 0 | 0 | County is discussing connection to 4 providers | N/A | Contract in hands of legal for review | N/A | 0 | 0 | 0 | 0 | Network Operation Centers are in process of being completed. Once completed, CAIs will begin to be connected/serviced | Network Operation Centers are in process of being completed. Once completed, CAIs will begin to be connected/serviced | Network Operation Centers are in process of being completed. Once completed, CAIs will begin to be connected/serviced | N/A | 0 | 0 | 0 | 0 | 0 | Project FOCUS is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential & businesses | Project FOCUS is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential & businesses | Project FOCUS is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential & businesses | Project FOCUS is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential & businesses | Project FOCUS is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential & businesses | 0 | 0 | 0 | 0 | 0 | Project FOCUS is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential & businesses | Project FOCUS is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential & businesses | Project FOCUS is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential & businesses | Project FOCUS is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential & businesses | Project FOCUS is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential & businesses | Oconee FOCUS will provide connectivity to rural locations by allowing ISPs (Internet Service Providers) to purchase transport on the network. | FALSE | N/A | - Connection and service to Community Anchor Institutes. - 2 of 3 Network Operation Centers setup and operating. - 2nd Phase of construction underway - Obtain all permits necessary to complete project - Construct approximately 20-25 miles of conduit and 15-20 miles of fiber - Our plan is to have approximately 90 community anchor institutes connected by the end of the quarter - We plan to have 2 broadband/wholesaler agreements signed by the end of the quarter | Oconee County | The house bill H3508 has been a challenge for the project this quarter. If enacted, H.3508 will be a job killer and a threat to South Carolinaâ€™s economic development, educational opportunity, and quality of life. Given Americaâ€™s compelling need to deploy robust broadband infrastructure everywhere as rapidly as possible, this bill will prevent communities from helping themselves. A broadband infrastructure will help provide service to unserved and underserved areas where private-sector are unable or unwilling to meet local needs. Locates for utilities have been an ongoing problem. The team is still working closely to prevent any cuts and/or damage to all utilities. | If the Senate approves bill H3508, the broadband team will need to revise our business model. | TRUE
NT10BIX5570117 | 2012 | Q2 | Q2 - 2012 | Approximately 150 miles of conduit and approximately 130 miles of fiber has been installed and spliced. The request for proposal (RFP) for the installation of the second phase was awarded to Network Controls of Greer, SC. The County received the last railroad permits that were submitted to Norfolk Southern. During this quarter we also received the final shipment of fiber. A few quarters ago the County purchased fiber management software from Telvent. The broadband team had a week long training session with Telvent representatives to learn how to operate and utilize equipment. All three NOCs (network operation center) have power, equipment, cooling, and fiber termination. All three NOCs should be completely setup and operating in the next quarter. The team has been working diligently to get the NOCs communicating. The team did a lot of pre-planning for the arrival of Tellabs and Cisco for setup, configuration, and lighting of the NOCs, school district and fire departments. Approximately 75 community anchor institutions have fiber connected. Equipment is being installed to prepare for the lighting of the fiber. The team met with emergency services and agencies to inform how the fiber will help with rescue efforts and why the team chose the fire departments as aggregation points. The team attended the broadband conference in Arlington, VA. The team met with other awardees and have been in contact with them since the conference. The team divided and attended different sessions to accumulate as much data and knowledge as possible. Oconee County awarded a contract for the core routers to Internetwork Engineering out of Cincinatti, OH. The equipment was ordered and should arrive in next quarter. During this quarter Fiber Characterization was completed. Fiber characterization is an in depth integrity test of the fiber which has been already deployed within the backbone ring prior to the connection of the electronics portion of the network. This testing allows us to find any errors which may be inherent to the fiber due to a manufactures defect or externally created during the installation/construction phase of deployment. This testing allows us to determine, isolate and fix any issues with the fiber prior to turning up the electronics phase of the project. This way if there is an issue once we turn up the electronics we should be able to automatically rule out fiber issues and concentrate on the electronics or design of the network. The fight over the House bill 3508 came to an end during the quarter. The time line of bill is as follows: Introduced in the House on January 27, 2011 Introduced in the Senate on February 22, 2011 Last Amended on June 7, 2012 Passed by the General Assembly on June 27, 2012 Governor's Action: June 29, 2012, Signed The broadband team is diligently working on a revised business model since the bill has passed. The team has spent and will continue to spend numerous hours focusing on the effects of this bill. | 130 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | Very close to baseline. A few issues with fiber put the team a few miles short of target. | na | na | na | Very close to baseline. A few issues with fiber put the team a few miles short of target. | na | na | With all of our delays network build has been delayed. Hope to be closer to our base line milestone next quarter. | 0 | 4 | 0 | Oconee County is negotiating with 4 wholesale/last mile providers. No agreements have been signed. | This is still under review by Oconee County and will require approval by County Council. Pricing structure being processed. | Oconee County secured a contractor through the RFP (request for proposal) process. Technology Solutions was awarded to install, configure, and operate network through construction. Technology Solutions will connect, provision, maintain, and monitor network through construction. | 0 | 0 | 0 | 0 | County is discussing connection to 4 providers at this time. | na | Contract still in legal review. | na | 0 | 0 | 0 | 0 | Network Operation Centers are in the process of being completed. Once completed, CAIs will begin to be connected and served. | Network Operation Centers are in the process of being completed. Once completed, CAIs will begin to be connected and served. | Network Operation Centers are in the process of being completed. Once completed, CAIs will begin to be connected and served. | na | 0 | 0 | 0 | 0 | 0 | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential and businesses. | 0 | 0 | 0 | 0 | 0 | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. These ISPs will connect residential and businesses. | Oconee FOCUS project will provide connectivity to rural locations by allowing ISPs (Internet Service Providers) to purchase transport on the network. | FALSE | na | The team plans to have all NOCs set up and ready to service CAIs. We hope to release pricing to ISPs. Plan to have contracts/agreements signed and providing ISPs with the information they need to start selling service. The contractor plans to have most of phase II complete by the end of next quarter. The teams hopes to deploy ~200 miles next quarter. We should have ~ 30 community anchor institutions connected by the end of the quarter. | Oconee County | The crews installing conduit hit a section of rock this quarter. The crew got through the rock but it did slow progress down significantly. The crew installing the fiber had a few issues with the fiber but have resolved those issues. Installing fiber has resumed and making forward progress. The House bill has always been a challenge. During this quarter the bill did pass in the Senate. The team has been in contact with different officials concerning the effects the bill will have on project. We are also working on a revised business model. | The House bill H-3508 may take up some of the teams time next quarter. The team will be shifting gears to comply with all goals set forth with the grant and bill that has been passed. Equipment deployment could be delayed if back orders become an issue. | TRUE
NT10BIX5570117 | 2012 | Q3 | Q3 - 2012 | Approximately 180 miles of conduit and approximately 160 miles of fiber has been installed and spliced. All three of our NOCs (network operation centers) are set up and functioning. During this quarter, Tellabs spent several weeks at the County setting up and configuring equipment. We had several training sessions to familiarize ourselves with all components of the network. Tellabs will be providing training on specific pieces of equipment in the next quarter. Approximately 80 community anchor institutions have fiber and/or equipment installed. The County is waiting on a few pieces of equipment to be able to light the fiber and provide connectivity to the anchors. Installation on National Forestry Land began this quarter. The team met with National Forestry personnel to talk about progress and any areas of concern. The team will meet with the National Forestry personnel periodically to give updates about progress. The team attended the Fiber to the Home conference this quarter. The team met with vendors and other agencies that have been awarded money for broadband implementation. Attended classes for Economic Development through broadband, job creation, and general sessions where a broad range of questions were asked. Good trip for planning the future of the broadband build-out. Met with Oconee County Industrial group to discuss broadband opportunities for the County. OFS provided a fiber splicing training class for the team. Learned about the fiber the County is using for the project and how the fiber is spliced using a fusion splicer. Very interesting class!!! Attended the award close out and the Davis Bacon webinars. | 160 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | na | na | na | na | Very close to our goal. Should be at baseline next quarter. | na | na | With all of our delays, network build has been delayed. Hope to be closer to our base line next quarter. | 0 | 5 | 0 | Oconee County is negotiating with 5 wholesale/last mile providers. No agreements have been signed. | This is still under review by Oconee County and will require approval by County Council. Pricing structure being processed. | Upon completion of project, Oconee will select an operator for the system. This operator maybe public private or contractor. | 0 | 0 | 0 | 0 | The County is discussing connection to 5 providers at this time. | na | Contract still in review in end of quarter. | na | 56 | 0 | 56 | 0 | The team is waiting on a few pieces of equipment before we can serve anchors. Should have all equipment installed and anchors lit by next quarter. | The team is waiting on a few pieces of equipment before we can serve anchors. Should have all equipment installed and anchors lit by next quarter. | The team is waiting on a few pieces of equipment before we can serve anchors. Should have all equipment installed and anchors lit by next quarter. | The team is waiting on a few pieces of equipment before we can serve anchors. Should have all equipment installed and anchors lit by next quarter. | 0 | 0 | 0 | 0 | 0 | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. The ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. The ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. The ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. The ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. The ISPs will connect residential and businesses. | 0 | 0 | 0 | 0 | 0 | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. The ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. The ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. The ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. The ISPs will connect residential and businesses. | The FOCUS project is a middle-mile project that will provide connectivity & service to ISPs in Oconee County. The ISPs will connect residential and businesses. | Oconee FOCUS project will provide connectivity to rural locations by allowing ISPs (internet service providers) to purchase transport on the network. | FALSE | na | Hope to have first dark fiber contract signed. Hope to have at least one last mile contract signed. We have been working with last mile providers and hope to have pricing distributed to all ISPs that we have been in contact with. The team hopes to have ~ 220 miles of conduit and fiber installed by the end of the quarter. We plan to have 80-90 community anchor institutions connected by the end of next quarter. | Oconee County | Rock seems to be an issue for the team each quarter. It continues to slow progress of installation but we seem to learn from earlier issues. We started installation on National Forestry Land. The team is making sure to preserve all the natural surroundings in the Forestry Land. | Weather could be an issue as winter rolls in. Rock could always become an issue. | TRUE
NT10BIX5570117 | 2012 | Q4 | Q4 - 2012 | As the quarter ended, approximately 235 miles of conduit and approximately 190 miles of fiber were installed. The Broadband Team attended 3 weeks of beneficial on-site training with Tellabs instructors and engineers which included hands-on training with the specific equipment used for the network. The team has worked closely with the Economic Development Center to help attract economic growth in Oconee County. The team met with Forestry land personnel and successfully installed conduit through National Forestry Land. Rock continues to cause problems for conduit and fiber installation. Four wavelengths were built out for County and data traffic. Redundant fiber rings were constructed and also lit during the fourth quarter. | 190 | 0 | 0 | 0 | 190 | 0 | 0 | 0 | Weather has created problems for conduit and fiber installation. Should hit baseline goal next quarter. | na | na | na | Weather has created problems for fiber installation. Should hit baseline goal next quarter. | na | na | Should be at baseline goal first quarter of 2013. | 1 | 4 | 20 | Dukenet | Oconee County is completing analysis on dark and lit fiber. Oconee County has hired a consultant to assist with pricing. | Upon completion of project, Oconee will select an operator for the system. This operator maybe public or private. | 1 | 0 | 1 | 10 | The County is discussing connection to 4 providers at this time. | na | Still discussing other contracts. | Connection speeds from 10MB to 10GB will be offered. | 60 | 17 | 43 | 2 | After receiving some of the equipment needed for connection, the team added a few more anchors since last PPR. We hope to have many more connected by next quarter. | After receiving some of the equipment needed for connection, the team added a few more anchors since last PPR. We hope to have many more connected by next quarter. | After receiving some of the equipment needed for connection, the team added a few more anchors since last PPR. We hope to have many more connected by next quarter. | 1GB connection to each location | 0 | 0 | 0 | 0 | 0 | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | 0 | 0 | 0 | 0 | 0 | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | Oconee FOCUS will provide connectivity to rural locations by allowing ISPs to purchase transport on the network. | FALSE | na | We hope to have all installation of conduit and fiber completed in this next quarter. We also hope to have more contracts signed in the next quarter. We plan to install ~16 miles of conduit and fiber in the next quarter. We hope to have 95% of anchors connected by the end of next quarter also. We would to have at least 2 of the 4 wholesaler/last miles providers we are currently working with at this time. | Oconee County | Weather has been a problem during this quarter. Rock continues to slow progress. | Hope to have all areas except testing completed. | TRUE
NT10BIX5570117 | 2013 | Q1 | Q1 - 2013 | As of first quarter end we have approximately 243 miles of conduit installed and approximately 220 miles of fiber. Tellabs spent approximately 2 weeks to help with network operation centers and configuration on equipment. Phase III of the fiber installation was awarded to Network Controls of Greer, SC. The team met with Dukenet to discuss another route. Met with a few ISPs (internet service providers) to discuss interest in network and providing services to Oconee County. Our program officers paid us a visit this quarter. We spent the day discussing progress and what was to come. We also visited locations where conduit and fiber were being installed. One of out team members attended the SEATOA (Southeast Associations of Telecommunications Officers & Advisors) conference. The team member spoke about our project and challenges that the team faced throughout the project. On the technical side the County and ISP lambdas were brought online this quarter. Our core routers are online broadcasting BGP (Border Gateway Protocol). The team began setting up network aggregation sites at the fire departments. The team has completed configuration of the Gigabit Passive Optical Networking (GPON) for commercial and residential use. | 220 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | Rock has slowed progress. Continue to be very close to our baseline goal. | na | na | na | Rock has slowed progress. Continue to be very close to our baseline goal. | na | na | Should meet our baseline goal and the end of the 2nd quarter of 2013. | 1 | 5 | 20 | Dukenet | Oconee County is completing analysis on dark and lit fiber. Oconee County has hired a consultant to assist with pricing. | Upon completion of project, Oconee will select an operator for the system. This operator may be public or private. | 0 | 0 | 1 | 10 | The County is discussing connection to 5 providers at this time | na | Still discussing other contracts | Connection speeds from 10MB to 10GB will be offered | 63 | 17 | 46 | 2 | The County is in the process of connecting anchors to the network. Should have all anchors completed by the end of next quarter. | The County is in the process of connecting anchors to the network. Should have all anchors completed by the end of next quarter. | The County is in the process of connecting anchors to the network. Should have all anchors completed by the end of next quarter. | 1 GB connection to each location. | 0 | 0 | 0 | 0 | 0 | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | 0 | 0 | 0 | 0 | 0 | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | Oconee FOCUS will provide connectivity to rural locations by allowing ISPs | FALSE | na | The broadband team plans to have all conduit and fiber installed by the end of next quarter. We hope to have all anchors connected and operating through the broadband network. | Oconee County | Rock, rock, rock...continues to be an issue for this project. | We do not foresee any major issues next quarter. | TRUE
NT10BIX5570117 | 2013 | Q2 | Q2 - 2013 | Approximately 244 miles of conduit and 242 miles of fiber had been installed at the end of the second quarter. The team is in the process of route inspections with the South Carolina Department of Transportation. The team is checking the routes for cleanup and general inspections of conduit and fiber installation. This quarter the team participated in at least six webinars. The team met with a wireless internet service provider. The team also met with a consultant to help create and review sustainability model. The school district is utilizing 1 GB school to school connection which can be expanded to 10 GB when the school district is ready. Fiber was terminated at six fire departments. We also have two fiber cuts this quarter. It was a great test for the redundancy and outside plant emergency plan. | 242 | 0 | 0 | 0 | 242 | 0 | 0 | 10 | Rock slow down completion. Will be complete by end 3rd quarter. | na | na | na | Rock slow down completion. Will be complete by end 3rd quarter. | na | na | Should meet baseline goal at the end of 3rd quarter. | 1 | 5 | 20 | Dukenet | Oconee County is completing an analysis on dark and lit fiber. Oconee County has hired a consultant to assist with pricing. | Upon completion of this project, Oconee County will select an operator for the system. This operator may be public or private. | 0 | 0 | 1 | 0 | The County is discussing connection with 5 different providers at this time. | na | Should have at least one other contract by the end of the 3rd quarter. | Connection speeds from 10MB to 10GB will be offered | 70 | 23 | 47 | 70 | The County will have all anchors completed by end of next quarter. | The County will have all anchors completed by end of next quarter. | The County will have all anchors completed by end of next quarter. | 1 GB connection to each location. | 0 | 0 | 0 | 0 | 0 | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | 0 | 0 | 0 | 0 | 0 | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | Oconee FOCUS will provide connectivity to rural locations by allowing ISPs. | FALSE | na | Completion of project!!! We plan on having at least 245 miles installed by the end of the quarter. We plan to have all equipment installed in all of the 126 community anchor institutes. We would love to have another wholesaler/last mile provider agreement in the works by the end of the next quarter. | Oconee County | Rock continued to slow the process down as usual. | na | TRUE
NT10BIX5570117 | 2013 | Q3 | Q3 - 2013 | All construction is complete with approximately 252 miles of fiber and conduit. South Carolina Department of Transportation provided final inspection and punch list. The team continues to work with consulting agency on pricing. Outside Plant maintenance contract was sent out for RFP and awarded to Geovision. Geovision will provide fiber maintenance, locates, and new build. NDAs signed with 4 ISPs. The team has provided 1GB connection to the schools in Oconee County. With this accomplishment the school district was able to complete online testing. The schools have the optics to upgrade to 10 GB between each school. An emergency management network has been setup by connecting operation centers, E911, emergency shelters,and rescue location for command center vehicles. Connectivity has been provided to cell towers to provide early adoption of 4G/LTE deployment. | 252 | 0 | 0 | 0 | 252 | 0 | 0 | 10 | NA | N/A | N/A | N/A | N/A | N/A | N/A | na | 1 | 7 | 20 | Dukenet | Oconee County is completing an analysis on dark and lit fiber. Oconee County has hired a consultant to assist with pricing. | Upon completion of this project, Oconee County will select an operator for the system. This operator may be public or private. | 0 | 0 | 1 | 10 | The County is discussing connection with 7 different providers at this time. | N/A | Still finalizing deal | Connection speeds from 10MB to 10GB will be offered | 102 | 25 | 77 | 1 | NA | Replacing DSL at some of CAIs | Replacing DSL at some of CAIs | 1 GB connection to each location | 0 | 0 | 0 | 0 | 0 | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | 0 | 0 | 0 | 0 | 0 | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | The FOCUS project is a middle mile project that will provide connectivity and service to ISPs. The ISPs will connect residential and businesses. | Oconee FOCUS will provide connectivity to rural locations by allowing ISPs. | FALSE | N/A | Sales!!!! | Oconee County | Team transitioning from project construction and grant management to operation and customer support. | N/A | TRUE
NT10BIX5570118 | 2010 | Q4 | Q4 - 2010 | The project engineering bid process was completed and the awarded engineering firm, BBCom, began environmental and design work for the route. The accomplishment was significant since the initial awarded engineering firm withdrew after because of the strict implementation timelines imposed under the RFP. BBCOM accepted the conditions of the timeline and are proceeding ahead of projected schedules. The engineers confirmed the initial submitted design and budget estimates as being a valid design with proper budget allocations for the project. The engineers also researched and confirmed possible alternative construction plans which, if implemented, will improve the overall capacity of the installed network without changing the overall scope of the project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | 0 | 0 | 0 | We have no signed agreements at this stage of the project. | We have not established wholesale agreements or related pricing plans at this point in the project. | N/A - There is no planned third party to operate the network. | 0 | 0 | 0 | 0 | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | 0 | 0 | 0 | 0 | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | 0 | 0 | 0 | 0 | 0 | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | 0 | 0 | 0 | 0 | 0 | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | We do not have any special offerings at this time. | FALSE | Network management practices have not changed during the last quarter. | Engineering is planned to have design and bid packages completed with construction bidding to begin by the end of the next quarter. The environmental assessment draft submission is projected to be completed. Concurrent with the construction bids, purchase and/or acquisition of colocation buildings and equipment is planned. | Nexus Systems, Inc. | As noted above, our initial awarded engineering firm withdrew as they were concerned with the strict timelines. As this occurred during the holiday period, switching to a new firm delayed progress. The current engineers are making excellent progress with the design of the routes and preparation of the bid packages. We are, however, very concerned about the environmental assessments as we see the various parties from whom we need approvals are not responding in a timely manner. We designed the project route to utilize existing highway right of ways where there should be minimal environmental question, but we are concerned the environmental review may be the single point of delay in construction and implementation of the project. Any assistance BTOP can provide to expedite this process will be helpful. | As noted for the current quarter activities, the environmental assessment is a primary challenge. Agencies involved in the approval process are currently backlogged many months in responses to environmental approval requests. Obtaining necessary environmental assessments may delay construction. Other issues involve the Louisiana Spring weather which may impede construction with rain. At this time, we do not anticipate other significant challenges. | TRUE
NT10BIX5570118 | 2011 | Q1 | Q1 - 2011 | Project engineering and environmental assessment have been completed at the end of the quarter with the draft environmental assessment submitted for BTOP review on 04/14/2011. The engineers and Nexus reviewed an alternate route for services from Jonesboro to Weston utilizing fiber in lieu of microwave and concluded this change could be implemented within the project scope and budget to provide better long range services to the community. For the fiber route, staking has been completed and co-location/repeater sites confirmed. The engineering firm is currently reviewing potential bidder qualifications. Interviews with fiber and other materials suppliers have begun to secure materials in advance of contractor bid packages. Elements necessary for the bid package have been assembled with bids due for release within 30 days after approval of the environmental assessment. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | Project is still in engineering and environmental assessment | 0 | 0 | 0 | We have no signed agreements at this stage of the project. | We have not established wholesale agreements or related pricing plans at this point in the project. | N/A - There is no planned third party to operate the network. | 0 | 0 | 0 | 0 | Project is still in engineering and environmental assessment. | Project is still in engineering and environmental assessment. | Project is still in engineering and environmental assessment. | Project is still in engineering and environmental assessment. | 0 | 0 | 0 | 0 | Project is still in engineering and environmental assessment. | Project is still in engineering and environmental assessment. | Project is still in engineering and environmental assessment. | Project is still in engineering and environmental assessment. | 0 | 0 | 0 | 0 | 0 | Project is still in engineering and environmental assessment. | Project is still in engineering and environmental assessment. | Project is still in engineering and environmental assessment. | Project is still in engineering and environmental assessment. | Project is still in engineering and environmental assessment. | 0 | 0 | 0 | 0 | 0 | Project is still in engineering and environmental assessment. | Project is still in engineering and environmental assessment. | Project is still in engineering and environmental assessment. | Project is still in engineering and environmental assessment. | Project is still in engineering and environmental assessment. | We do not have any special offerings at this time. | FALSE | Network management practices have not changed during this quarter. | Construction bids are projected to be let May 15 with projected awards June 15 with construction to begin by end of quarter. Additional materials and equipment contracts are projected to be let by end of quarter. Establishment of pre-fab co-location huts and services will begin during the quarter with projected completion during the next (Summer) quarter. Budget projections for next quarter reflect projected payments for materials and equipment from federal funds as well as cash and in-kind contributions from Nexus Systems. | Nexus Systems, Inc. | Challenges related to the environmental assessment, but aggressive schedules from our environmental consultant along with outstanding assistance from BTOP personnel have completed the draft assessment to help get the project back to a acceptable schedule. Additional challenges related to highway right of way permits due to existing construction on some portions of the route along with some protected surface segments which required slight changes in the route. The Louisiana Department of Highways (DOT) offered assistance to mitigate the issues. In the original budget submitted, the plan was for a "design build" project whereby the awarded contractor performed much of the environmental and engineering design as part of the construction bid submitted. The construction segment reflected these costs. The engineering budget provided only for CAD and drawings. To provide the most competitive construction bids, Nexus separated all engineering and therefore the engineering category is over budget. The additional monies required will be moved from the construction budget. The change will not negatively impact the construction funding required to complete the project. Nexus Systems provided for 26% matching funding in the project in both cash and in-kind match. All in-kind match and a significant portion of the cash match will be reflected in the Q2 Progress Report which will provide match in excess of the proportion of expenditures to date. | Possible challenges relate to the procurement of fiber materials as we see the lead times for these products becoming longer. Permits for the railway crossings are pending as of the end of the quarter. Procedure for rail permits in the past has been for the rail company to only issue permit to the awarded contractor due to insurance requirements placed on the contractor. After the end of the quarter, we successfully negotiated a change in the procedure to issue permits directly to Nexus Systems and permits will therefore not impede the construction process. | TRUE
NT10BIX5570118 | 2011 | Q2 | Q2 - 2011 | Project engineering and environmental assessment have been completed and the environmental assessment was approved. The approval included project modifications to improve service to selected communities in the route. Construction bids were let and contracts awarded for all underground fiber installation. Bids received were within budget allocations even after consideration of the project modifications. Installation is to begin in July with mandated completion in January 2012. Purchase orders for fiber cable and transmission equipment have been issued with fiber delivery to begin in September, 2011. The project is on schedule to be completed in first quarter 2012. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Environmental assessment received May, 2011; construction to begin July 2011. Network not available at end of quarter. | Environmental assessment received May, 2011; construction to begin July 2011. Network not available at end of quarter. | Environmental assessment received May, 2011; construction to begin July 2011. Network not available at end of quarter. | Environmental assessment received May, 2011; construction to begin July 2011. Network not available at end of quarter. | Environmental assessment received May, 2011; construction to begin July 2011. Network not available at end of quarter. Construction is proceeding at the rate of approximately one mile per working day, or six miles per working week. The construction schedule projects we will have between 45 and 50 miles of fiber construction completed by the end of quarter September 30, 2011. | Environmental assessment received May, 2011; construction to begin July 2011. Network not available at end of quarter. | Environmental assessment received May, 2011; construction to begin July 2011. Network not available at end of quarter. | Environmental assessment received May, 2011; construction to begin July 2011. Network not available at end of quarter. | 0 | 0 | 0 | We have no signed agreements at this stage of the project. Nexus is expecting to begin active prospecting for wholesale providers in the October 2011 timeframe. Nexus has been receiving informal inquiries from various potential providers, but providers are reluctant to commit until there are sections of the route ready for occupancy. | We have not established wholesale agreements or related pricing plans at this point in the project. | N/A - There is no planned third party to operate the network. | 0 | 0 | 0 | 0 | Network not available for subscribers at end of quarter due to environmental and construction delays. | Network not available for subscribers at end of quarter due to environmental and construction delays. | Network not available for subscribers at end of quarter due to environmental and construction delays. | Network not available for subscribers at end of quarter due to environmental and construction delays. | 0 | 0 | 0 | 0 | Network not available for subscribers at end of quarter due to environmental and construction delays. The fiber construction to date has targeted the northern section of the route including Jonesboro, Quitman, Ruston and Vienna. We anticipate connection of a number of school, medical, library and related Critical Anchor Institution (CAI) sites to the fiber backbone by September 30, 2011. We have identified approximately 20 sites which we believe can be connected to the backbone during this time period. | Network not available for subscribers at end of quarter due to environmental and construction delays. | Network not available for subscribers at end of quarter due to environmental and construction delays.. | Network not available for subscribers at end of quarter due to environmental and construction delays. | 0 | 0 | 0 | 0 | 0 | Network not available for subscribers at end of quarter due to environmental and construction delays. | Network not available for subscribers at end of quarter due to environmental and construction delays. | Network not available for subscribers at end of quarter due to environmental and construction delays. | Network not available for subscribers at end of quarter due to environmental and construction delays. | Network not available for subscribers at end of quarter due to environmental and construction delays. | 0 | 0 | 0 | 0 | 0 | Network not available for subscribers at end of quarter due to environmental and construction delays. | Network not available for subscribers at end of quarter due to environmental and construction delays. | Network not available for subscribers at end of quarter due to environmental and construction delays. | Network not available for subscribers at end of quarter due to environmental and construction delays. | Network not available for subscribers at end of quarter due to environmental and construction delays. | We do not have any special offerings at this time. | FALSE | Network management practices have not changed during this quarter. | Construction contracts have been awarded with significant construction to be accomplished during the next quarter. Construction will have heavy focus on the northern portion of the route (Jonesboro, Weston, Ruston, Grambling, Vienna) to allow Nexus to begin service to a number of Critical Anchor Institutions. Co-location facility in Vienna has been purchased and will be fitted during next quarter. Additinoal co-location site land servitudes will be completed during the next quarter as well as securing and placing co-location huts for Jonesboro, Winnfield, Dry Prong, and Pineville in conjunction with construction schedule. Fiber transmission equipment is on order with acquisition and testing to begin during the next quarter. | Nexus Systems, Inc. | Challenges related to the environmental assessment, but aggressive schedules from our environmental consultant along with outstanding assistance from BTOP personnel have secured the approved assessment during May 2011. One railroad has demanded $250,000 in crossing fees for this project (in addition to the customary permit fee and safety fees); these fees are being protested at this time. | Construction is underway with multiple contractor and subcontractor crews assigned to segments of the project. The challenges for the next two quarters will be coordination of the construction process and for equipment deployment and testing. A favorable fiber delivery schedule has been obtained but must be monitored closely as all fiber manufacturers are running at peak production. Since construction is during July - September, weather is not anticipated to be a significant factor. No other significant challenges are anticipated. | TRUE
NT10BIX5570118 | 2011 | Q3 | Q3 - 2011 | Significant construction has been accomplished with approximately one third of all conduit laid. Most of the construction during the quarter has been the slower and more difficult directional boring in the northern sector of the route. The initial delivery of fiber has been received as well as fiber transmission equipment and testing equipment. Co-location units have been secured and are awaiting delivery as the schedule requires. The project is on schedule for completion in first quarter 2012. | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Deployment of 41 miles of conduit build has been completed at this time. Railroad crossings are pending at 3 sites with fiber installation to complete new network build. | N/A - No leasing is projected in the plan. | N/A - No existing network mileage is projected in the plan. | N/A - No existing network mileage is projected in the plan. | Deployment of 41 miles of conduit build has been completed at this time. Railroad crossings are pending at 3 sites with fiber installation to complete new network build. | Wireless links scheduled for upgrade in next quarter. | N/A - No new towers projected in this plan | Interconnection points scheduled for first quarter 2012 | 0 | 0 | 0 | We have no signed agreements at this stage of the project. Nexus is expecting to begin active prospecting for wholesale providers in third quarter 2011 as sections of the route become available. | Wholesale agreements or related pricing plans have not been established at this point in the project. | N/A - There is no planned third party to operate the network. | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. Construction is currently targeting parishes of Lincoln and Jackson to link school, medical, library, and governmental sites to the backbone. Fiber installation in completed conduit has not been completed due to railroad permits pending, but will be completed in 4th Quarter 2011. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | 0 | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | 0 | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | N/A - No special offerings are planned at this time. | FALSE | N/A - Network management practices have not changed during the quarter. | Significant construction with high conduit installation mileage is projected for the next quarter. During the current quarter, the construction emphasis targeted directional boring requirements. The next quarter will target primarily rural plowing with much faster deployment of conduit. New network miles deployed are projected to be 100 miles of the 120 miles total project. Deployment of co-location buildings and fiber transmission equipment is projected to be completed during this quarter. Connections to over 35 Critical Anchor Institutions are projected to be accomplished during the period. Signed wholesale agreements with other providers will be pursued in Quarter 1, 2012 with the availability of lighted fiber on the network. | Nexus Systems, Inc. | The only significant challenge has been our attempt to clarify the exorbitant fees demanded by the Kansas City Southern railroad for bore permits. We are working to resolve this issue without delaying the progress of the project. | The only pending item is negotiation of permits from Kansas City Southern railroad. This item is not expected to impact progress of the project schedule for the next quarter. Fiber deliveries have been on schedule. If fiber delivery should be delayed, this issue could impact the overall schedule. No other significant challenges are anticipated. | TRUE
NT10BIX5570118 | 2011 | Q4 | Q4 - 2011 | Construction has been completed for approximately 85% of the route. All significant construction obstacles such as railroads, waterway and city street construction have been completed. Foundations for 50% of co-location buildings have been completed with all to be completed and placed in the first quarter 2012. All fiber material is on site and fiber is being installed with approximately 40% installed at end of quarter. Fiber transmission equipment is on site and in test to be installed with co-location buildings. The project is on schedule for construction completion in first quarter 2012. | 56 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | Construction of 109 miles of conduit build completed at this time with 56 miles of fiber placement in the conduit. | N/A - No leasing is projected in the plan | N/A - No existing network mileage is projected in the plan | N/A - No existing network mileage is projected in the plan | Installation of 56 miles of fiber in the 109 miles of conduit placed has been completed | Wireless links scheduled for upgrade in 2012 | N/A - No new towers projected in the plan | Interconnection points scheduled for first quarter 2012 | 0 | 0 | 0 | We have no signed agreements at this point in the project. Initial inquiries with possible providers have shown interest, but providers wish to see all construction in place prior to signing agreements. | Wholesale agreements or related pricing plans have not been established at this point in the project. | N/A - There is no planned third party to operate the network. | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. Railroad permit delays caused fiber installation to be extended until first quarter 2012. In first quarter 2012, anchor institutions in Lincoln, Jackson, and Winn Parishes are projected to be connected as fiber placement is completed. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | 0 | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | 0 | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | N/A - No special offerings are planned at this time. | FALSE | N/A - Network management practices have not changed during the quarter. | Conduit placement and fiber placement will be completed for the primary route. Additional work will be for connections to anchor institutions and beginning ties to other wholesale and last mile providers. Placement of co-location buildings and related fiber transmission and switching equipment is projected to be completed. Wholesale agreement marketing will be pursued coincident with the completion of the lighted fiber. | Nexus Systems, Inc. | There have been no significant external challenges except for weather which has delayed some construction. The construction contractor and engineers have adjusted production schedules and the project construction is still on tract for first quarter 2012 significant completion. | The budget category "1D" is now projecting an increase from the original budget of $216,000 to $1,000,000 through the next quarter. This increase is due to outsourcing all engineering and required environmental reviews needed to complete the project and substantial permit requirements. The cost increases will be offset by lower than anticipated construction cost and equipment cost reductions. | TRUE
NT10BIX5570118 | 2012 | Q1 | Q1 - 2012 | Construction of conduit and fiber has been completed for about 95% of the route. The remaining fiber construction item is the termination point in Pineville which is being redesignated as a lateral and should be completed in the next quarter. Foundations for co-location buildings have been completed and buildings placed. Renovations of the point of presence site in Vienna are 90% completed with completion next quarter. Fiber terminations and testing in three co-location sites are completed with two remaining. Fiber transmission equipment is in test with deployment available upon completion of fiber terminations at Vienna and Pineville. Major procurements for equipment have been completed with the exception of routing switches for which competitive models are being tested next quarter. Nexus has been contacted by (4) major providers requesting information for broadband agreements with timelines for implementation. These potential partners have also provided significant assistance with suggestions for promoting co-locations and terminations into telecommunications central offices. These suggestions have prompted some changes in the network configurations in order to improved the network to accommodate needs of these stakeholders. Multiple critical anchor institution sites are being prepared for Summer conversion to the new network as this period will provide a less obtrusive conversion for schools, public offices, and similar sites. | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | Construction of 120 miles of conduit build completed at this time with 120 miles of fiber placement in the conduit. Terminations and testing underway at this time. | N/A - No leasing is currently in the project | N/A - No existing network mileage is projected in the plan | N/A - No existing network mileage is projected in the plan | Construction of 120 miles of conduit build completed at this time with 120 miles of fiber placement in the conduit. Terminations and testing underway at this time. | Wireless links scheduled for upgrade in Summer 2012 | N/A - No new towers projected in the plan | Interconnection points scheduled for Summer 2012 | 0 | 0 | 0 | We not no signed agreements at this point in the project. We have initial contact with three providers for whom we are providing network maps and seeking negotiations at this time. | Wholesale agreements or related pricing plans have not been established at this point in the project. | N/A - There is no planned third party to operate the network. | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress | Network not available for subscribers due to construction in progress | Network not available for subscribers due to construction in progress | Network not available for subscribers due to construction in progress | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. Anchor institutions in Lincoln, Jackson, and Winn Parishes are being moved to the network, but have not been completed as of end of quarter. | Network not available for subscribers due to construction in progress | Network not available for subscribers due to construction in progress | Network not available for subscribers due to construction in progress | 0 | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress | Network not available for subscribers due to construction in progress | Network not available for subscribers due to construction in progress | Network not available for subscribers due to construction in progress | Network not available for subscribers due to construction in progress | 0 | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress | Network not available for subscribers due to construction in progress | Network not available for subscribers due to construction in progress | Network not available for subscribers due to construction in progress | Network not available for subscribers due to construction in progress | N/A - No special offerings are planned at this time. | FALSE | N/A - Network management practices have not changed during the quarter. | Completion of co-location buildings and lighting of fiber is planned for the second quarter. This will include completion of co-location facilities, power systems, and backups, and installation of fiber transmission and routing equipment equipment. Installation of a Taqua T7000 series switch is expected to be completed in the next quarter in order to provide greater connectivity to last mile providers. Nexus has negotiated a cooperative endeavor agreement with the Louisiana State Department of Transportation (DOT) to incorporate approximately additional mileage of existing DOT dark fiber into the project which will allow fiber to certain critical anchor institutions institutions in lieu of original planned microwave extensions. A project modification for this purpose is being submitted this quarter with expectation of change orders for the end of the quarter or first of next quarter. The modification will essentially double the planned fiber mileage but remain within the original budget. The project modification will also include a request to change the point of presence termination at Pineville to the AT&T central office at Alexandria in order to allow greater connectivity for Nexus and broadband providers. The additional mileage is not expected to be completed during the next quarter (June 2012), but will be completed withing the following quarter (October 2012). Ongoing work will be to connect critical anchor institutions and negotiating with wholesale and last mile providers. Nexus has been contacted by multiple providers seeking services with providers seeking agreements after fiber is lighted. We expect to complete agreements with some at least 3 providers during the Summer period. Field work for connecting critical anchor institutions has been completed for many sites with Summer conversion slated for a number of educational and governmental sites. A significant number of the critical anchor sites are expected to be completed during the Summer overlapping into the third quarter. We expect to complete installations for at least 40 CAI sites during the next quarter. | Nexus Systems, Inc. | The project is on schedule for initial fiber construction. Fiber placement is complete with splice points completed except for the end points North (Vienna) and South (Huey P Long Hospital). Fiber termination South was delayed due to changing the location to be a lateral as opposed to a terminating point of presence. Initial design called for a co-location building to be constructed/installed at the site. Due to the State Board of Regents BTOP being cancelled, the hospital site will now be an anchor institution and not a point of presence. The installation is now being changed to terminate directly in the hospital as opposed to additional constructions. There is no change in environmental assessment, but minor delay in completion at this site. Construction/renovation at the North (Vienna) site was to be completed by end of quarter, but ran into the second quarter due to breakout of the construction into multiple contracts to achieve better pricing. No other significant external challenges are delaying the project. | The primary challenge will be the planned project modification and related environmental assessment required. A budget revision reflecting reclassification of engineering expenses and additional switch equipment will be submitted. Assistance from the BTOP team in determining required assessments may be needed. | TRUE
NT10BIX5570118 | 2012 | Q2 | Q2 - 2012 | Fiber construction for the original route is essentially complete with the exception of changes in a pending program modification. Co-location buildings have been placed with battery and generator installations. Power permits and work orders have been issued for these sites. Fiber transmission equipment and router/switch equipment has been delivered and extensive network configuration and testing has been completed. Nexus Systems and the Department of Transportation have initiated a partnership to provide much better interconnection points and services to critical anchor institutions in the North end of the project with the addition of 120 miles of DOT dark fiber. This program modification along with a re-designation of the interconnection point at the South end of the project have been submitted to the Program Office for review. Multiple critical anchor institutions are being fiber-connected to the backbone route at this time including schools, public safety and hospital sites. Additional negotiations are underway with multiple providers for wholesale agreements. | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | Construction of the original 120 miles is completed with testing underway at this time. Additional construction is anticipated in the pending requested program modification. | N/A - No leasing is currently in the project. Note the pending program modification will incorporate approximately 120 miles of DOT dark fiber in a cooperative endeavor arrangement to increase the total fiber deployment. | N/A - No existing network mileage is projected in the plan. | N/A - No existing network mileage is projected in the plan. | Original construction in the Piney Woods project. | Two wireless links are planned for next quarter. Three wireless links were planned in the original design, but one will be eliminated with the pending project modification. | N/A - No new towers projected in the plan. | Multiple additional interconnection points will be added with the pending project modification. | 0 | 0 | 0 | We do not have any signed agreements at this point in the project. We have initial contact with five providers for whom we are providing network maps and seeking negotiations at this time. | Wholesale agreements and related pricing plans have not been established at this point. | N/A - There is no planned third party to operate the network. | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | 35 | 14 | 21 | 3 | Network not available for subscribers due to construction in progress. Anchor institutions in Lincoln, Jackson, Winn, and Grant parishes have been connected or upgraded in segments of the network. | Libraries in Lincoln, Bienville, Winn received new service | Schools in Lincoln, Jackson, Winn received upgraded service. | Libraries received 20 Mbps, Schools received 100 Mbps and 1000 Mbps service. | 0 | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | 0 | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | N/A - No special offerings are planned at this time. | FALSE | N/A - Network management practices have not changed during the quarter. | Completion of all segments or the original fiber build necessary to pass light on the network from Pineville to Vienna is planned for the next quarter. This will include completion of the physical layer elements of fiber testing and equipment placement, but also network elements of fiber transmission equipment and network routing design and testing. Installation of the Taqua T7000 series switch has been accomplished and initial service to last mile customers is expected to begin. Nexus has negotiated a cooperative endeavor agreement with the Louisiana State Department of Transportation (DOT) to incorporate approximately 120 miles of existing DOT dark fiber into the project which will allow fiber to certain critical anchor institutions institutions in lieu of original planned microwave extensions. A project modification for this purpose has been submitted with expectation of change orders during the next quarter. The modification will essentially double the planned fiber mileage but remain within the original budget. The project modification will also include a request to change the point of presence termination at Pineville to the AT&T central office at Alexandria in order to allow greater connectivity for Nexus and broadband providers. Engineering and environmental review is underway and expected to be completed during the next quarter. The additional mileage is not expected to be completed during the next quarter (September 2012), but is expected to be completed within the following quarter (December 2012) pending environmental review. Ongoing work will be to connect critical anchor institutions and negotiating with wholesale and last mile providers. Nexus has been contacted by multiple providers seeking services with providers seeking agreements after fiber is lighted. At his time, we are estimating there will be zero wholesale/last mile providers connected as of end of Quarter 3, 2012. Field work for connecting critical anchor institutions has been completed for many sites with late-Summer conversion slated for a number of educational and governmental sites. As of end of Quarter 2, 2012, 39 CAI sites have been connected or upgraded with an additional 35 slated for connection in Quarter 3, 2012. These critical anchor sites are expected to be completed during the Summer overlapping into the third quarter. | Nexus Systems, Inc. | Fiber placement is complete with splice points completed except for the end points North (Vienna) and South (Huey P Long Hospital). The only significant challenges for construction during the quarter have been longer than anticipated power utility permits. For the overall project, the challenge has been to implement better interconnection facilities at the North and South ends of the project. The original design included interconnection points to the Board of Regents ("LONI") network at the North and South ends of the Piney Woods construction build. Due to the State Board of Regents BTOP grant being cancelled, the North and South ends will not be afforded the interconnections assumed in the original design. The State Department of Transportation (DOT) has worked closely with Nexus Systems to assist the project. A program modification request has been submitted to implement changes at the North and South ends of the project to provide viable interconnection paths. Assistance from BTOP for speedy review of the requested program modification would be helpful. | The pending project modification will require an environmental review primarily for crossing the Red River in Alexandria. Nexus is going forward with engineering and environmental consulting but any assistance from BTOP to identify requirements would be helpful. The construction in the proposed changes for the North will not be significant but construction at the Red River in the South end will require coordination with the Core of Engineers and the Rapides Parish Levy Board. | TRUE
NT10BIX5570118 | 2012 | Q3 | Q3 - 2012 | Fiber construction for the original route is essentially complete with the exception of changes in a pending program modification. Power and air conditioning for repeater sites in Vienna, Jonesboro, Winnfield, and Dry Prong is installed. Renovations to the Vienna site have been completed allowing for 1600 feet of co-location space. The southern interconnect point is still pending with Project Modification under review. BTI fiber transmission equipment has been installed and the initial 40 Gbps backbone is now operating from Vienna (north) to Dry Prong (south). Extensions out to Community Anchor Institutions from the primary fiber routes are underway with new or upgraded connections to the CAI sites. A program modification along with a re-designation of the interconnection point at the South end of the project have been submitted to the Program Office for review. Permits and engineering for this modification have been largely completed with construction pending environmental clearance. Additional negotiations are underway with multiple providers for wholesale agreements. | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | Construction of the original 120 miles is completed with testing completed. Additional construction is anticipated in the pending requested program modification. | N/A - No leasing is currently in the project. Note the pending program modification will incorporate approximately 120 miles of DOT dark fiber in a cooperative endeavor arrangement to increase the total fiber deployment. | N/A - No existing network mileage is projected in the plan. | N/A - No existing network mileage is projected in the plan. | Original construction in the Piney Woods project. | Two wireless links are planned for next quarter. Three wireless links were planned in the original design, but one will be eliminated with the pending project modification. | N/A - No new towers projected in the plan. | Multiple additional interconnection points will be added with the pending project modification. | 0 | 0 | 0 | We do not have any signed agreements at this point in the project. We have initial contact with five providers for whom we are providing network maps and seeking negotiations at this time. | Wholesale agreements and related pricing plans have not been established at this point. | N/A - There is no planned third party to operate the network. | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | 61 | 23 | 38 | 6 | Network not available for all subscribers due to construction in progress. Anchor institutions in Lincoln, Jackson, Winn, and Grant parishes have been connected or upgraded in segments of the network. | Hospitals in Jackson, Union, and Claiborne received new service. Sheriff in Jackson and Winn Recieved new service and library in Bienville received new service. Libraries in Lincoln, Bienville, Winn received new service. | Schools in Lincoln, Jackson and Winn received upgraded service. | Libraries, Hospitals and Sheriff received 20+ Mbps, Schools received 100 Mbps and 1000 Mbps service. | 0 | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | 0 | 0 | 0 | 0 | 0 | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | Network not available for subscribers due to construction in progress. | N/A - No special offerings are planned at this time. | FALSE | N/A - Network management practices have not changed during the quarter. | Work is to projected to begin on the proposed project modification with fiber to be installed at key points along I20. If permits are finalized, drilling under the river at Pineville/Alexandria will be accomplished. Additional BTI fiber transmission hardware will be ordered for delivery and testing. Microwave links to Farmerville and Athens/Homer is expected to be completed. The pending project modification will also include a request to change the point of presence termination at Pineville to the AT&T central office at Alexandria and add a point of presence at the AT&T Monroe CO and AT&T Shreveport CO in order to allow greater connectivity for Nexus and broadband providers. Ongoing work will be to connect critical anchor institutions and negotiating with wholesale and last mile providers. Nexus has been contacted by multiple providers seeking services with providers seeking agreements after fiber is lighted. At his time, there are no wholesale/last mile providers signed and connected as of end of Quarter 3, 2012. Field work for connecting critical anchor institutions has been completed for many sites with late-Summer conversion completed for a number of educational and governmental sites. As of end of Quarter 3, 2012, 61 CAI sites have been connected or upgraded with an additional 35 slated for connection in Quarter 4, 2012. The remaining critical anchor sites are expected to be completed during the Spring. | Nexus Systems, Inc. | Fiber placement is complete with splice points completed except for the end points North (Vienna) and South (Huey P Long Hospital). The only significant challenges for construction during the quarter have been longer than anticipated power utility permits and the required environmental review for the proposed program modification. For the overall project, the challenge has been to implement better interconnection facilities at the North and South ends of the project. The original design included interconnection points to the Board of Regents ("LONI") network at the North and South ends of the Piney Woods construction build. Due to the State Board of Regents BTOP grant being cancelled, the North and South ends will not be afforded the interconnections assumed in the original design. The State Department of Transportation (DOT) has worked closely with Nexus Systems to assist the project. A program modification request has been submitted to implement changes at the North and South ends of the project to provide viable interconnection paths. Assistance from BTOP for speedy review of the requested program modification would be helpful. | The pending project modification will require an environmental review primarily for crossing the Red River in Alexandria. Nexus is going forward with engineering and environmental consulting but any assistance from BTOP to identify requirements would be helpful. The construction in the proposed changes for the North will not be significant but construction at the Red River in the South end will require coordination with the Core of Engineers and the Rapides Parish Levy Board. The pressing challenge at this time is approval of the environmental review for the project modification. | TRUE
NT10BIX5570118 | 2012 | Q4 | Q4 - 2012 | Fiber construction for the original route is essentially complete with the exception of changes in a pending program modification. Power and air conditioning for repeater sites in Vienna, Jonesboro, Winnfield, and Dry Prong is installed. Renovations to the Vienna site have been completed allowing for 1400 feet of co-location space. The southern interconnect point is still pending with Project Modification under review. BTI fiber transmission equipment has been installed and the initial 40 Gbps backbone is now operating from Vienna (north) to Dry Prong (south). Extensions out to Community Anchor Institutions from the primary fiber routes are underway with new or upgraded connections to the CAI sites. A program modification along with a re-designation of the interconnection point at the South end of the project have been submitted to the Program Office for review. Permits and engineering for this modification have been largely completed with construction pending environmental clearance. Additional negotiations are underway with multiple providers for wholesale agreements. | 120 | 0 | 0 | 0 | 120 | 2 | 0 | 5 | Construction of the original 120 miles is completed with testing completed. Additional construction is anticipated in the pending requested program modification. | N/A - No leasing is currently in the project. Note the pending program modification will incorporate approximately 120 miles of DOT dark fiber in a cooperative endeavor arrangement to increase the total fiber deployment. | N/A - No existing network mileage is projected in the plan. | N/A - No existing network mileage is projected in the plan. | Original construction in the Piney Woods project. | Three wireless links were planned in the original design, but one will be eliminated with the pending project modification. | N/A - No new towers projected in the plan. | Multiple additional interconnection points will be added with the pending project modification. | 0 | 0 | 0 | We do not have any signed agreements at this point in the project. We have initial contact with five providers for whom we are providing network maps and seeking negotiations at this time. | Wholesale agreements and related pricing plans have not been established at this point. | N/A - There is no planned third party to operate the network | 0 | 0 | 0 | 0 | Negotiations underway with providers at this time. | Negotiations underway with providers at this time. | Negotiations underway with providers at this time. | Negotiations underway with providers at this time. | 77 | 39 | 38 | 6 | Network not available for all subscribers due to construction in progress. Anchor institutions in Lincoln, Jackson, Winn, and Grant parishes have been connected or upgraded in segments of the network. | Hospitals in Jackson, Union, and Claiborne received new service. Sheriff in Jackson and Winn Recieved new service and library in Bienville received new service. Libraries in Lincoln, Bienville, Winn received new service | Sheriff in Union, Library in Claiborne and Jackson, Hospital in Homer, Schools in Bienville, Claiborne, Jackson, Lincoln, Winn, and Union Parishes received improved access. | Libraries, Hospitals and Sheriff received 20+ Mbps, Schools received 100 Mbps and 1000 Mbps service. | 0 | 0 | 0 | 0 | 0 | Middle mile project construction in progress. | Middle mile project construction in progress. | Middle mile project construction in progress. | Middle mile project construction in progress. | Middle mile project construction in progress. | 0 | 0 | 0 | 0 | 0 | Middle mile project construction in progress. | Middle mile project construction in progress. | Middle mile project construction in progress. | Middle mile project construction in progress. | Middle mile project construction in progress. | N/A - No special offerings are planned at this time. | FALSE | N/A - Network management practices have not changed during the quarter. | The next quarter project accomplishments mirror the expectations of the Quarter 4, 2012 as the pending project modification has not been released for implementation at this point. Work is to projected to begin on the proposed project modification with fiber to be installed at key points along I20. If permits are finalized, drilling under the river at Pineville/Alexandria will be accomplished. We are projecting 10 miles additional fiber to be lighted during the next quarter for a total of 130 miles. The remaining fiber will be completed and lighted during Quarter 2, 2013. Additional BTI fiber transmission hardware will be ordered for delivery and testing. The pending project modification will also include a request to change the point of presence termination at Pineville to the AT&T central office at Alexandria and add a point of presence at the AT&T Monroe CO and AT&T Shreveport CO in order to allow greater connectivity for Nexus and broadband providers. Ongoing work will be to connect critical anchor institutions and negotiating with wholesale and last mile providers. Nexus has been contacted by multiple providers seeking services with providers seeking agreements after fiber is lighted. At his time, there are no wholesale/last mile providers signed and connected as of end of Quarter 4, 2012. We are expecting to have 5 wholesale agreements in place during the next quarter. Field work for connecting critical anchor institutions has been completed for many sites with late-Summer conversion completed for a number of educational and governmental sites. As of end of Quarter 4, 2012, 77 CAI sites have been connected or upgraded with an additional schools, hospitals, and public safety slated for connection in Quarter 1, 2013. We are projecting 87 total CAI sites to be connected through Quarter 1, 2013. The remaining critical anchor sites are expected to be completed during Quarter 2, 2013. | Nexus Systems, Inc. | Fiber placement is complete with splice points completed except for the end points North (Vienna) and South (Huey P Long Hospital). The only significant challenges for construction during the quarter have been longer than anticipated power utility permits and the required environmental review for the proposed program modification. For the overall project, the challenge has been to implementbetter interconnection facilities at the North and South ends of the project. The original design included interconnection points to the Board of Regents ("LONI") network at the North and South ends of the Piney Woods construction build. Due to the State Board of Regents BTOP grant being cancelled, the North and South ends will not be afforded the interconnections assumed in the original design. The State Department of Transportation (DOT) has worked closely with Nexus Systems to assist the project. A program modification request has been submitted to implement changes at the North and South ends of the project to provide viable interconnection paths. Assistance from BTOP for speedy review of the requested program modification would be helpful. | The pending project modification will require an environmental review primarily for crossing the Red River in Alexandria. Nexus is going forward with engineering and environmental consulting but any assistance from BTOP to identify requirements would be helpful. The construction in the proposed changes for the North will not be significant but construction at the Red River in the South end will require coordination with the Core of Engineers and the Rapides Parish Levy Board. The pressing challenge at this time is approval of the environmental review for the project modification. | TRUE
NT10BIX5570118 | 2013 | Q1 | Q1 - 2013 | Engineering, permits, and related technical requirements for the program modification were completed during the quarter pending approval of the environmental review of the project addition. Materials were secured for the addition of approximately 15 miles of fiber additions in the modification including boring under the Red River, incorporation of an additional 105 miles of Department of Transportation fiber along I20, extension into central telephone switch offices in Monroe, Alexandria, Shreveport, and extension to 10 breakout points along the new I20 addition. Additional fiber mileage deployed during the quarter was approximately 3 miles of laterals to CAI sites. Additional mileage for the I20 and Red River expansion was delayed pending approval of project modification. The original plan provided for 198 miles with 120 miles projected to be new fiber and 78 miles of microwave upgrades to four cities (Farmerville, Athens, Homer, Arcadia) from the Vienna north end point. The project modification provided for an additional 105 miles of Department of Transportation fiber upgrades and 15 miles of new fiber to be incorporated in the plan , but would also eliminate the 22 mile microwave extension to Arcadia. Microwave extension upgrades of 56 miles from the original plan from Vienna to Farmerville, Athens, and Homer have been completed. The Arcadia extension will be served with the new I20 fiber addition. Negotiations with wholesale providers and third party providers to Critical Anchor Institutions were expanded during the period. Fiber laterals to CAI sites were also initiated or completed during the period. | 120 | 0 | 56 | 0 | 120 | 3 | 0 | 5 | Construction of the original 120 miles is completed with testing completed. | N/A - No leasing is currently in the project. The pending program modification will incorporate approximately 120 miles of DOT dark fiber in a cooperative endeavor arrangement to increase the total fiber deployment. Total network miles will increase to 296 miles with 120 miles of new fiber construction and 120 miles of fiber in the DOT cooperative arrangement along with 56 miles of microwave extensions. | Microwave extension upgrades to Farmerville, Athens, and Homer total of 56 miles were completed during the period. The original plan of 78 miles of microwave upgrades was reduced to 56 miles as the extension to Arcadia was removed with the new I20 addition. The Arcadia route will be connected on the new I20 fiber. | N/A - No existing network mileage is projected in the plan. | Original construction in the Piney Woods project | Two wireless links to Farmerville, Athens, and Homer deployed for a total of 56 miles of microwave path. | N/A No new towers projected in the plan. | Multiple additional interconnection points will be added with the pending program modification. | 0 | 0 | 0 | There are no Master Sales Agreements with providers at close of period. We are in negotiations with multiple wholesalers at end of period and have signed orders/agreements with three after close of period. | Wholesale agreements and related pricing plans have not been completed as of the end of the period. | N/A - There is no planned third party of operate the network. | 0 | 0 | 0 | 0 | Negotiations with providers not completed at end of period | Negotiations with providers not completed at end of period | Negotiations with providers not completed at end of period | Negotiations with providers not completed at end of period | 78 | 39 | 39 | 6 | Anchor institutions in Lincoln, Jackson, Winn, and Grant parishes have been connected or upgraded in segments of the network. Major third party wholesale provider for additional CAI connections in Grant Parish has requested interconnection and will be serving additional CAI sites during second quarter. | Hospitals in Jackson, Union, and Claiborne received new service, Sheriff in Jackson and Winn received new service as well as libraries in Bienville, Lincoln, and Winn. | Sheriff in Union, Library in Claiborne, Jackson, Winn, hospital in Claiborne, schools in Bienville, Claiborne, Jackson, Lincoln, Winn, and Union Parishes all received improved access. | Libraries, Hospitals, and Sheriff received, 20+ Mbps, Schools received 100 Mbps and 1000 Mbps. | 0 | 0 | 0 | 0 | 0 | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | 0 | 0 | 0 | 0 | 0 | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - No special offerings are planned at this time. | FALSE | N/A - Network management practices have not changed during the quarter. | We have received approval of the program modification for extending the project south into Alexandria and east-west from Monroe to Shreveport. Total project will then be 120 miles of new fiber in the original project, 105 miles of upgraded fiber along I20, 15 miles of new fiber in the project modification, and 56 miles of upgraded microwave links for a total impact of 296 miles. The additional fiber projected to be deployed during the quarter will be 105 miles of upgrades for the DOT fiber and 15 miles of new fiber. The construction and equipment deployment for these additions will be completed during the second quarter. As of filing this report, the construction in Pineville/Alexandria, including boring the Red River, is essentially completed with fiber being installed. The upgrades and extensions along I20 are approximately 50% completed with fiber being lighted as each segment is brought online. Additional BTI fiber and related battery/power equipment will be delivered by mid-quarter with testing by end of quarter. Master sales agreements will be in place with several providers which will also extend services to remaining Critical Anchor Institutions. Projection is for 6 Master Sales Agreements to be in place for next quarter. Additional CAI sites will be added with Department of Transportation interconnections along I20 with the total CAI sites to be connected projected at 100 for next quarter. The overall goal will be to have to project ready for closeout on schedule in Quarter 3. | Nexus Systems, Inc. | As noted in the prior period report, cancellation of the original Board of Regents ("LONI") project caused this project connectivity problems for egress from the network. Incorporation of the program modification to extend the project into Alexandria with connectivity into the Alexandria, Monroe, and Shreveport AT&T central offices has provided relief, but with the delay from the engineering and environmental review and related construction planning. The primary delay encountered this period related to the railroad permit required for Arcadia and permits from Windstream for break/tie into the existing dark fiber along I20. Each of these items has been resolved. The very quick NTIA review and approval of the program modification to correct the egress issues provided Nexus with the opportunity to correct a deficiency with an overall improvement in the service provided by the project. | The project timeline is within three months of completion with major construction builds still underway. Our contractors and suppliers have provided excellent service and we expect there to be no significant challenges during the next quarter to bring the project to completion on construction and network deployment. We are still working diligently with other wholesale providers to initiate master sales agreements/interconnection agreements and will have progress in this area. The challenge will be securing agreements with national providers. One provider (Verizon) has already informed us they will not entertain any service agreement with a BTOP recipient for dark fiber, but only will consider for lighted service by that vendor. We are receiving favorable feedback from local/regional providers. The only other challenge may be to completed co-location rights with AT&T sites in Monroe, Shreveport, and Alexandria by end of quarter due to the lengthy process with this vendor. Note in the attached Budget Execution Details we project some remaining budget at end of quarter as the challenge will be to close out all funds by end of quarter. | TRUE
NT10BIX5570118 | 2013 | Q2 | Q2 - 2013 | Boring of the Red River and extension to the zero manhole for AT&T Central Office service in Alexandria was completed. Fiber to the zero manhole for this site and Monroe has completed all requirements for co-location at these sites and equipment installation is scheduled for first of next quarter. The approved project modification construction ties in for seven sites were completed along the I20 route as well as installation of repeater and power equipment in these sites. This construction allowed for about 80 of the additional 120 miles to be completed. Testing of all aspects of the fiber and microwave build to date has been accomplished with no deficiencies. Fiber laterals to CAI sites were also initiated or completed during the period. Negotiations with wholesale providers and third party providers to Critical Anchor Institutions were expanded during the period. | 120 | 0 | 136 | 0 | 120 | 3 | 0 | 5 | Construction of the original 120 miles is completed with testing completed. | N/A - No leasing is currently in the project. | Microwave extension upgrades to Farmerville, Athens, and Homer total of 56 miles were completed during Quarter 1, 2013. The original plan of 78 miles of microwave upgrades was reduced to 56 miles as the extension to Arcadia was removed with the new I20 addition. The Arcadia route will be connected on the new I20 fiber. The new I20 fiber will add 120 miles for existing miles upgraded bringing the total of miles upgraded to 176 miles. As of the end of the current quarter, approximately 80 miles of the I20 upgrade had been completed and tested wtih the remaining 40 miles and three sites to be completed during the next quarter. | N/A - No existing network mileage is projected in the plan | Original construction in the Piney Woods project | Two wireless links to Farmerville, Athens, and Homer deployed for a total of 56 miles of microwave path. | N/A No new towers projected in the plan. | Interconnection points at Nexus, Vienna, Jonesboro, Winnfield, Dry Prong from the original plan have been completed. Interconnection sites for the project modification including Wells Road, Arcadia and Bossier have been completed. Three sites in the new project modification have not yet been completed due to delays in splicing from Windstream/AT&T. | 2 | 2 | 20 | Agreements for service with Network USA and Skyrider Wireless have been obtained. Network USA will be serving cellular providers along the Highway 167 fiber route. Network USA will be serving school customers through the Nexus Monroe POP. | Wholesale agreements track the current AT&T MetroE pricing plan at 70% of the AT&T published pricing as proposed in the original grant application. | N/A - There is no planned third party of operate the network. | 2 | 0 | 0 | 2 | Network USA (cellular) and Skyrider Wireless (Internet) are connected through the network. | Negotiations with providers not completed at end of period | Negotiations with providers not completed at end of period | (1) subscriber each at speed tier of 100 Mbps and 150 Mbps | 79 | 40 | 39 | 6 | Anchor institutions in Lincoln, Jackson, Winn, and Grant parishes have been connected or upgraded in segments of the network. Major third party wholesale provider for additional CAI connections in Grant Parish has requested interconnection but has not finalized agreement as of the end of the quarter. | Hospitals in Jackson, Union, and Claiborne received new service, Sheriff in Jackson and Winn received new service as well as libraries in Bienville, Lincoln, and Winn. | Sheriff in Union, Library in Claiborne, Jackson, Winn, hospital in Claiborne and Pineville, schools in Bienville, Claiborne, Jackson, Lincoln, Winn, and Union Parishes all received improved access. | Libraries, Hospitals, and Sheriff received, 100+ Mbps, Schools received 100 Mbps and 1000 Mbps. Subscriber count of 31 at 100+ Mbps Tier and count of 47 at 1000+ Mbps Tier for total of 78 CAI subscribers. One subscriber is currently being installed and there is no speed tier set on this one site. | 0 | 0 | 0 | 0 | 0 | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | 0 | 0 | 0 | 0 | 0 | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - No special offerings are planned at this time | FALSE | N/A - Network management practices have not changed during the quarter. | The project has been extended until September 2013 and the next quarter will close the project. We have received approval of the program modification for extending the project south into Alexandria and east-west from Monroe to Shreveport. Total project will then be 120 miles of new fiber in the original project, 105 miles of upgraded fiber along I20, 15 miles of new fiber in the project modification, and 56 miles of upgraded microwave links for a total impact of 296 miles. The additional fiber projected to be deployed during the quarter will be linking in approximately 40 miles of upgrades for the DOT fiber. The construction and equipment deployment for these additions will be completed during the third quarter. Construction in Pineville/Alexandria, including boring the Red River, is completed with fiber installed to the zero manhole at the AT&T CO. Clearance for entry into the AT&T CO for Alexandria and Monroe has been obtained with equipment installation during the third quarter. The upgrades and extensions along I20 require spices at three additonal points and installation of repeater equipment (already in hand) during the next quarter. Master sales agreements will be in place with several providers which will also extend services to remaining Critical Anchor Institutions. Projection is for 6 Master Sales Agreements to be in place for next quarter. Additional CAI sites will be added with Department of Transportation interconnections along I20 with the total CAI sites to be connected projected at 110 for next quarter. The overall goal will be to have to project ready for closeout on schedule in Quarter 3. | Nexus Systems, Inc. | The primary delay encountered this period related to the permits from Windstream for break/tie into the existing dark fiber along I20. We reported last quarter (March 2013) that the Windstream permits had been resolved. Even after permits were issued, however, it took Windstream almost 90 days to provision a fiber tech to make the break/ties along I20. As of the end of the quarter.Each of these items has been resolved. The very quick NTIA review and approval of the program modification to correct the egress issues provided Nexus with the opportunity to correct a deficiency with an overall improvement in the service provided by the project. | The project timeline is within three months of completion with minor construction ties underway. The remaining items are spice ties at three sites along I20 and installation/testing of the related equipment at the repeater/colo sites. Nexus has received schedule AT&T central office install dates of the first week in August for Monroe and Alexandria sites with Shreveport pending. We are still working diligently with other wholesale providers to initiate master sales agreements/interconnection agreements and will have progress in this area. The challenge continues to be be securing agreements with national providers. We are receiving favorable feedback from local/regional providers. Remaining CAI sites are on schedule to be completed with one third party network provider accounting for about half of all remaining sites to be served. Budget monies for almost all remaining budget have been committed and Nexus will be committing additional monies to complete the project for any budget overruns. | TRUE
NT10BIX5570118 | 2013 | Q3 | Q3 - 2013 | What are the achievements obtained through the Louisiana Piney Hills Parishes Broadband Infrastructure Project? The accomplishments of things even greater than imagined possible when this project was begun are a true blessing for Louisiana. During the last quarter, extension of the fiber from the Red River into the Alexandria AT&T Central Office was completed with the Nexus equipment installation in the CO. Fiber extension into the Monroe AT&T Central Office was completed. The approved project modification construction tie-in for remaining sites was completed along the I20 route, as well as installation of repeater and power equipment at these sites. This construction accounted for approximately 40 miles of the additional 120 miles that were completed through the project. Testing of all aspects of the fiber and microwave build to date were accomplished with no deficiencies. Fiber laterals to Community Anchor Institution sites were also initiated or completed during the period. Negotiations with wholesale providers and third party providers to Community Anchor Institutions continued during the period. The overall project has been an outstanding example of effective public/private partnerships with NTIA, Nexus, State government and local agencies benefiting from this investment. The original footprint from Vienna to Pineville was effectively doubled within the same budget. It provided an east/west fiber path connecting seven new communities in addition to the original new north/south corridor. New communities served include Shreveport, Bossier City, Haughton, Minden, Filmore, Arcadia, Choudrant, and West Monroe, as well as intersecting the original Highway 167 BTOP route at Ruston. Plans are already underway, with other partners, to expand the fiber footprint an additional 100 plus miles through laterals and a ring construction. Engineering is already underway to extend the I20 fiber north to Cotton Valley, Springhill, Homer, Haynesville, and Farmerville; south from Shreveport to Stonewall, Mansfield, and Logansport; and south from Monroe to Columbia. Nexus is currently working with other service providers on plans to extend the original Highway 167 route to the communities of Pollock, Georgetown, Jena, Jonesville, Harrisonburg, Ferriday, and Vidalia. The initial investment was the seed needed to grow a fiber forest in North Louisiana. Nexus is very appreciative of the opportunity to have a role in building this fiber network in Louisiana. Nexus sincerely appreciates the excellent guidance and support provided by their assigned project field officer, Mr. Scott Woods. Benefits to stakeholders are abundantly evident. Community anchor sites are receiving GBPS service for the same or less cost than they were previously paying for copper or microwave connections. In the majority of cases, service was not available at all. This project has made reliable transport services available. Schools, in particular, are now able to meet the PARCCS testing bandwidth requirements. Providing higher standards for Internet services through the installation of the fiber has allowed increased local loop connections and has provided the infrastructure required for installation of new 10 GBPS Internet links on the backbone. Cellular carriers are currently contracting with Nexus to use the fiber backbone to bring enhanced data services to underserved rural areas of Louisiana. Future plans as described above include expanding the fiber backbones with laterals of 20-30 miles off the backbones and creating fiber rings with different segments. Nexus, as well as other contracted carrier clients, have already received requests for major implementations of VOIP services and Internet access services for up to 10 GBPS for business clients. A primary objective of BTOP was to bring top quality broadband Internet service to rural areas that would not be given an opportunity for broadband service without the support of BTOP funding and to serve as a springboard for even greater expansion into underserved rural areas. NTIA and Nexus Systems have surpassed the goal identified in the Louisiana Piney Hills Parishes Broadband Infrastructure Project. Through the willingness of NTIA to support a vision of what could be, a great portion of demographically isolated and economically challenged Louisiana has been blessed with the opportunity to enter the technology rich world that exists today. Thank you! | 120 | 0 | 176 | 0 | 120 | 3 | 0 | 12 | Construction of the original 120 miles is completed with testing completed. | N/A - No leasing is currently in the project. | Microwave extension upgrades to Farmerville, Athens, and Homer total of 56 miles were completed during Quarter 1, 2013. The original plan of 78 miles of microwave upgrades was reduced to 56 miles as the extension to Arcadia was removed with the new I20 addition. The Arcadia route will be connected on the new I20 fiber. The new I20 fiber will add 120 miles for existing miles upgraded bringing the total of miles upgraded to 176 miles. As of the end of the current quarter, the 120 miles of the I20 upgrade had been completed and tested. | N/A - No existing network mileage is projected in the plan | Original construction in the Piney Woods project | Three wireless links to Farmerville, Athens, and Homer deployed for a total of 56 miles of microwave path. | N/A No new towers projected in the plan. | Interconnection points at Nexus, Vienna, Jonesboro, Winnfield, Dry Prong from the original plan have been completed. Seven interconnection sites for the project modification including Monroe, Wells Road, Ruston, Arcadia, Minden, Filmore and Bossier have been completed. | 2 | 2 | 20 | Agreements for service with Network USA and Skyrider Wireless have been obtained. Network USA will be serving cellular providers along the Highway 167 fiber route. Network USA will be serving school customers through the Nexus Monroe POP. | Wholesale agreements track the current AT&T MetroE pricing plan at 70% of the AT&T published pricing as proposed in the original grant application. Pricing has decreased since the original project plan submission to reflect competitive markets. Please see the two attachments for Middle Mile and Last Mile customer pricing. | N/A - There is no planned third party of operate the network. | 2 | 0 | 0 | 2 | Network USA (cellular) and Skyrider Wireless (Internet) are connected through the network. | No providers receiving improved access | No providers receiving dark fiber | (1) subscriber each at speed tier of 100 Mbps and 150 Mbps | 108 | 41 | 67 | 6 | Anchor institutions in Lincoln, Jackson, Winn, and Grant parishes have been connected or upgraded in segments of the network. Major third party wholesale provider for additional CAI connections in Grant Parish has requested interconnection and fiber access has been extended to serve these sites. New anchor institutions for Department of Transportation along I20 corridor have been connected as part of the approved project modification. The list of CAI sites of 110 was modified by the addition of 7 sites added through the Department of Transportation addition, but reduced by 9 sites that did not elect to have a connection. Of the 9 sites not connected, 7 were service ready and may be connected at a later date as existing contracts expire. | Hospitals in Jackson, Union, and Claiborne received new service, Sheriff in Jackson and Winn received new service as well as libraries in Bienville, Lincoln, and Winn. | Sheriff in Union, Library in Claiborne, Jackson, Winn, hospital in Claiborne and Pineville, schools in Bienville, Claiborne, Jackson, Lincoln, Winn, Union and Grant Parishes all received improved access. University and Technical college sites and Department of Transportation offices (along I20 corridor) recieved improved service. | Libraries, Hospitals, and Sheriff received, 100+ Mbps, Schools received 100 Mbps and 1000 Mbps. Subscriber count of 54 at 100+ Mbps Tier and count of 54 at 1000+ Mbps Tier for total of 108 CAI subscribers. | 0 | 0 | 0 | 0 | 0 | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | 0 | 0 | 0 | 0 | 0 | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - Middle mile project. | N/A - No special offerings are planned at this time | FALSE | N/A - Network management practices have not changed during the quarter. | Project closeout is planned for next quarter. Nexus will extend services through new AT&T central office interconnections in Alexandria, Monroe, and Shreveport as well as continuing to provide new laterals services from the project backbone. | Nexus Systems, Inc. | Additional delays were encountered with scheduling for Windstream/AT&TT installations on I20, but were able to be mitigated. No other significant delays were encountered. | None - Project complete | TRUE
NT10BIX5570119 | 2010 | Q4 | Q4 - 2010 | In the project's second quarter, we laid the ground to begin project construction in spring 2011. This work includes completing route engineering and beginning site acquisition; substantial completion of the required environmental assessment; and preparing requests for proposals for fiber and materials and project construction. We completed the draft of an agreement with our subrecipient, OARnet. We completed our baseline project plan with key milestones and deliverables and a budget for the first six months of the project, both of which were accepted. This allowed us to begin drawing project funds. Three members of the team attended the Broadband Technology Opportunities Program workshop sponsored by the National Telecommunications and Information Administration in November. We have conducted regular monitoring meetings with the subrecipient, the environmental assesssment team, our Federal Program Officer and key project team members. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No construction allowed until FONSI issued | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | No fiber constructed yet | No fiber constructed yet | No plans regarding dark fiber | No fiber constructed yet | 0 | 0 | 0 | 0 | No fiber constructed yet | No fiber constructed yet | No fiber constructed yet | No fiber constructed yet | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | Completion of the draft environmental assessment; securing construction permits and other approvals; select equipment vendors and construction contractors; begin network construction | Horizon Telecom, Inc. | Key challenges in the past quarter included the required environmental assessment, particularly communications with the Ohio Historic Preservation Office; completing requests for proposals for construction while trying to select appropriate job classifications and wage determinations in compliance with the Davis-Bacon Act; and getting route maps and other pertinent information from BIP recipients to satisfy the Special Award Condition regarding overlap with other federally funded broadband projects. | Beginning of construction is dependent on issuance of a FONSI from our environmental assessment; a delay in receiving the FONSI will result in a delay in network construction. | TRUE
NT10BIX5570119 | 2011 | Q1 | Q1 - 2011 | Draft environmental assessment completed and submitted to NTIA; progress in reaching a programmatic agreement with Ohio Historic Preservation Office on procedures for historic and cultural properties during construction; completion of RFPs for fiber materials and electronics; issued RFPs for construction, IT hardware and plant records. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction continues to be delayed by environmental assessment, particularly with the Ohio Historic Preservation Office. | n/a | n/a | n/a | No construction due to continued delay in obtaining FONSI. | No construction due to continued delay in obtaining FONSI. | n/a | No construction due to continued delay in obtaining FONSI. | 0 | 0 | 0 | None. No construction. | Horizon will offer wholesalers and last-mile provider speed tiers of 5 MBps to 10GBps. | n/a | 0 | 0 | 0 | 0 | No fiber constructed yet | No fiber constructed yet | No fiber constructed yet | No fiber constructed yet | 0 | 0 | 0 | 0 | No fiber constructed yet | No fiber constructed yet | No fiber constructed yet | No fiber constructed yet | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | Contracts for network construction will be completed in this quarter; pending issuance of a FONSI on the environmental assessment, we expect to begin construction late in the quarter. Large orders of fiber materials and electronics equipment will be placed and warehoused. We will hold training for construction contractors on compliance with federal reporting requirements and with the stipulations in the programmatic agreement with NTIA and the Ohio Historic Preservation Office regarding cultural and historic resources. | Horizon Telecom, Inc. | Key challenges in the past quarter included the required environmental assessment, particularly communications with the Ohio Historic Preservation Office; selecting vendors from among the plethora of applicants; and getting information from BIP recipients to satisfy the Special Award Condition regarding overlap with other federally funded broadband projects. | Beginning of construction is dependent on issuance of a FONSI from our environmental assessment; a delay in receiving the FONSI will result in a continued delay in network construction. Collection of Davis-Bacon certified weekly payroll and other compliance data from construction contractors may be time-consuming at first. | TRUE
NT10BIX5570119 | 2011 | Q2 | Q2 - 2011 | Special Award Conditions for overlap and environmental assessment were lifted. Established a procedure for ongoing cultural and historical impact reviews in accordance with our agreement with the Ohio Historic Preservation Office. Vendors for construction, IT hardware and plant records were selected, bringing the RFP process to an end. The first shipment of fiber was delivered and the first order for electronics was placed. Created a vendor handbook outlining all company and government procedures, including reporting requirements; this is a living document that will be updated as needed. Conducted a training session for construction contractors on compliance, reporting and environmental awareness. Construction began in June; by the end of the reporting period, 30 miles of fiber had been strung. Created and convened Fiber Routing Advisory Committees in all 34 project counties; efforts are being made to accommodate the request for rerouting from one county. Internal discussions about services and marketing were initiated. | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction began late in the reporting period. | n/a | n/a | n/a | Construction began late in the reporting period. | Construction began late in reporting period. | n/a | Construction began late in the reporting period. | 5 | 0 | 9 | Intelliwave, Country Connections, Southern Ohio Communication Services, New Era Broadband, Hocking Internet | Horizon is offering wholesalers and last-mile provider speed tiers of 5 MBps to 10GBps. | n/a | 5 | 0 | 0 | 0 | With 5 signed agreements we are over one year ahead of projections. We have no new agreements in the queue at this time | Less than 1% of network constructed. | Less than 1% of network constructed. | Horizon will offer wholesalers and last-mile provider speed tiers of 5 MBps to 10GBps. | 0 | 0 | 0 | 0 | Less than 1% of network constructed. | Less than 1% of network constructed. | Less than 1% of network constructed. | Less than 1% of network constructed. Horizon will offer point-to-point and multipoint services between 5Mbps and 10Gbps; dedicated Internet access is 1Mbps-1Gbps standard, 2.5-40Gbps optional. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | We are currently projecting hanging fiber at a rate of 15+ miles per week. However we are still in ramp up mode and expect that number to improve. We expect to have equipment in place at 18 of 34 POP sites. We will begin to connect CAIs. We are active in a number of the Chambers of Commerce in the counties where we will be providing service. We are hosting 'lunch and learns' through the Chambers to explain the network and capabilities. We are providing speakers to the Chambers and service clubs. We will be placing targeted billboards and doing direct mail to those businesses on or close to the network route. | Horizon Telecom, Inc. | Key challenges in this quarter were the final acceptance of our environmental assessment, particularly communications with the Ohio Historic Preservation Office. With the issuance of our FONSI, construction began and the project has truly gotten underway. We have accelerated our build schedule and should catch and pass the baseline projections by EOQ4 2011 from a network perspective. | The most significant challenge we anticipate is making up for construction delays due to the environmental assessment process. Incumbent carriers--even though they may have inferior networks or less attractive pricing--have been able to use the time to move aggressively to sign up CAIs with long-term contracts, making the CAO network more difficult to sustain financially. In many cases, the rates are not especially attractive, but the carriers have been able to lock CAIs into long-term contracts. This delays our ability to sign up a particular CAI. Fortunately, many of our CAIs are represented in the consortium and have not been as easily led astray. Our main strategy to combat this problem is to be aggressive in our sales and marketing efforts, to pursue a greater volume of sales and to expand our focus to other types of institutions and facilities. | TRUE
NT10BIX5570119 | 2011 | Q3 | Q3 - 2011 | We completed our first BTOP audit. We broke ground for the first Point-of-Presence (PoP) in Muskingham County (Zanesville) Ohio. Construction continues in various areas of the state. With three different construction vendors each with multiple crews, we are making progress toward our accelerated build rate. We continue to negotiate/finalize our sub-recipient agreement with The Ohio Academic Resources Network (OARnet). In addition to signed agreements with five wireless internet service providers, community outreach has been educating businesses the different counties on our plans, timing and capabilities. | 135 | 0 | 0 | 0 | 135 | 0 | 0 | 9 | Variance is a result of delayed FONSI and slightly slower ramp-up than was expected. With our accelerated build schedule we should catch and pass baseline projections during the next six months. | n/a | n/a | n/a | Variance is a result of delayed FONSI and slightly slower ramp-up than was expected. With our accelerated build schedule we should catch and pass baseline projections during the next six months. | n/s | n/a | Near baseline. | 5 | 2 | 9 | Intelliwave, Country Connections, Southern Ohio Communications Services, New ERA Broadband, Hocking Internet | Horizon is offering wholesalers and last-mile providers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). Pricing plan redacted. | None. | 0 | 0 | 0 | 0 | Variance due to delay in FONSI. Our largest hurdle was the unknown duration of the FONSI process. We could not give them any idea of when we would arrive. | Variance due to delay in FONSI. Our largest hurdle was the unknown duration of the FONSI process. We could not give them any idea of when we would arrive. | n/a | n/a | 0 | 0 | 0 | 0 | Variance due to delay in FONSI. Our largest hurdle was the unknown duration of the FONSI process. We could not give them any idea of when we would arrive. Customers were unable and unwilling to sign contracts with a firm order commitment. Customers who were under contracts that were expiring could not risk not having service available renewed their existing agreements. | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | Variance due to delay in FONSI. Our largest hurdle was the unknown duration of the FONSI process. We could not give them any idea of when we would arrive. Customers were unable and unwilling to sign contracts with a firm order commitment. Customers who were under contracts that were expiring could not risk not having service available renewed their existing agreements. | Variance due to delay in FONSI. Our largest hurdle was the unknown duration of the FONSI process. We could not give them any idea of when we would arrive. Customers were unable and unwilling to sign contracts with a firm order commitment. Customers who were under contracts that were expiring could not risk not having service available renewed their existing agreements. | n/a | n/a | n/a | n/a | FALSE | n/a | With our planned accelerated build, the backbone will show significant progress in the 4th quarter. We are taking steps to increase our build rate to meet our projections. These steps include pushing more routes through our programmatic agreement to be cleared for construction and allow more crews to be working at the same time. Community Outreach programs will continue. PoP site ground-breakings will ramp-up in construction and subsequent equipment deployment this quarter. For the next quarter: we expect to build 200 new miles in this quarter; we do not expect any new network mile leases; we expect to have a couple (less than five) CAIs connected; we expect to have six signed agreements with last mile providers. | Horizon Telecom, Inc. | We struggled with permitting this quarter. One of the Ohio Department of Transportation's districts has not been as cooperative as the other districts. They have more reaching requirements than the other districts. We have held a meeting with district personnel and are hopeful the permitting in this area will speed up. We do not have any experience with them to know if this will really be the case. We continue to work through the environmental assessment process in our programmatic agreement. We did lose twenty-five Community Anchor Institutions (CAIs) (with one company) primarily due to the delay in receiving our FONSI. We feel the delay in construction from the FONSI is approximately five months. This seems extreme to us since virtually our entire project is aerial. The lost CAIs had a hard conversion date for which they needed fiber and could not wait. This conversion was required for transition to electronic records. the date was September, 2011. Replacement of these CAIs is an everyday objective. We have a opportunity which, should it come to fruition, has over 80 sites that would qualify as CAIs. | Our biggest challenge is expected to be the weather. As we are aerial frozen ground will have little if any impact. Rain and snow provide a factor of unknown impact. | TRUE
NT10BIX5570119 | 2011 | Q4 | Q4 - 2011 | Four Points of presence (POPs) have been constructed, installed, and tested. Four more have had electronics installed. Three hundred miles of backbone has been hung. 52 of 592 Community Anchor Institutions (CAIs), for nine percent of CAIs, are under contract. The vast majority of those are K-12 schools. Ten of those were signed during the reporting period. Horizon has signed a contract for a large number of points of interconnection. Based on current expenditure rates Horizon expects to reach the 67% point during the second quarter of 2012 and should reach the 100% point during the second quarter 2013. | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 16 | Horizon continues to ramp up construction. With multiple contractors who each have multiple crews, Horizon's run rate will continue to improve. Horizon is behind baseline projections because of the delays caused by the Environmental Assessment. This was not part of the project plan submitted with the application. | n/a | n/a | n/a | Horizon continues to ramp up construction. With multiple contractors who each have multiple crews, Horizon's run rate will continue to improve. | n/a | n/a | Near baseline. | 6 | 1 | 9 | Intelliwave, Country Connections, Southern Ohio Communications Services, New ERA Broadband, Hocking Internet, JB Nets | Horizon is offering wholesalers and last-mile providers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). Pricing plan redacted. | None. | 2 | 4 | 0 | 6 | Finally showing significant progress in build rates is building confidence in our ability to serve these carriers. | Finally showing significant progress in build rates is building confidence in our ability to serve these carriers. | n/a | Most ISPs have chosen 100 Mbps. | 10 | 9 | 1 | 10 | Customers are feeling more confident in our ability to serve them in a reasonable amount of time. K-12 schools are cyclical and most of these are those involved in the first wave. Horizon is behind baseline projections because of the delays caused by the Environmental Assessment. This was not part of the project plan submitted with the application. | These are a result of new builds. | This is a result of equipment upgrade. | Most schools (K-12) are choosing the 10 Mbps level. Two CAIs have chosen 100 Mbps. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | Unable to determine this information at this point in time. | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | We plan to complete the backbone by the end of the first quarter. Support systems will be put in place to assist in mapping and reporting. Horizon have goals in place to obtain approximately fifty new contracts by the end of the quarter. We will also identify and determine best suited replacement Community Anchor Institutions (CAIs) for the approximately 125 already determined to need replacements. | Horizon Telecom, Inc. | Permitting continues to be a struggle. Horizon is struggling with another utility provider to negotiate use of their poles. After following a certain procedure for years with the previous and current owner, they have decided we are in violation and have stopped all requests for make-ready. We will be attempting to re-route our fiber as much as possible. Identifying and subsequently gathering support for Community Anchor Institutions (CAIs) who need replaced. We have identified over 125 CAIs who need a replacement designated. | Horizon has concerns regarding its ability to overcome differences with other utility provider. We are developing alternatives to using their poles. This may cause not only delays but also increased costs. | TRUE
NT10BIX5570119 | 2012 | Q1 | Q1 - 2012 | Our significant accomplishments this quarter were the increase of Points of Presence (POPs) accepted from four to eighteen. 477 miles of backbone has been completed thus far and along with fifteen miles of distribution fiber. 99 of 592 Community Anchor Institutions (CAIs), for almost seventeen percent, are under contract with fourteen of those receiving service. Permitting, while a struggle most of the quarter, made huge progress with the signing of an agreement late in the quarter with the a large utility provider who was blocking our progress. | 492 | 0 | 0 | 0 | 492 | 0 | 0 | 18 | Horizon is behind baseline projections due to delays caused by the Environmental Assessment, as it was not part of the project plan submitted with the application. Permitting struggles have also slowed our build rate. An agreement reached late in the quarter with the utility causing us the most headaches will allow construction to move forward in those areas. | n/a | n/a | n/a | With the agreement reached late in the quarter with a utility for connectivity to their poles will allow construction crews to be more active and cover more miles. | n/a | n/a | We do not consider these to exist until we have audited all equipment and tested it. While we appear to be behind our baseline of 22, many more are in various stages of deployment. | 6 | 1 | 12 | Country Connections, Hocking Internet, Intelliwave, JB Nets, New ERA Broadband, Southern Ohio Communications Services | Horizon is offering wholesalers and last-mile providers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). | None. | 2 | 4 | 0 | 6 | none | none | none | Most Internet Service Providers (ISPs) have chosen the 100 Mbps level. | 14 | 10 | 4 | 14 | While schools are willing to sign contracts in advance of the network being built or complete, most other Community Anchor Institutions are not. Horizon is behind baseline projections because of the delays caused by the Environmental Assessment. This was not part of the project plan submitted with the application. | Horizon is behind baseline projections because of the delays caused by the Environmental Assessment. This was not part of the project plan submitted with the application. | Horizon is behind baseline projections because of the delays caused by the Environmental Assessment. This was not part of the project plan submitted with the application. | Eleven of the above have chosen the 10 Mbps level. One has chosen the 50 Mbps level and two have chosen the 100 Mbps level. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none | FALSE | n/a | Horizon expects to have a high percentage of the Points of Presence (POPs) finished or in the final stages by the end of the coming quarter with the remaining completing in the following six months. We expect to have twelve percent of our Community Anchor Institutions (CAIs) connected by the end of the quarter with twenty-five percent under contract. While we do expect to sign agreements with other wholesalers some time in the remainder of the year, we do not expect to sign them during this quarter. | Horizon Telecom, Inc. | Railroad permits are a struggle. Some companies ignore our requests completely while others move at a snail's pace. The big problem here is when an adjustment is needed, it starts their whole process over again. We are down to only one company not responding but that does not relieve the pace issue. With over 150 CAIs needing replacement, we have submitted an AAR with replacements. The first batch of replacements are for duplicate addresses (for example: two doctor's offices in the same building) and some no longer exist (for example: school consolidation, building closed). | Horizon has concerns with the relationship with the Railroads and their permitting processes. Railroad permitting time-frames range from a couple of days to over one year. Minor changes can start the clock over. | TRUE
NT10BIX5570119 | 2012 | Q2 | Q2 - 2012 | All points-of-presence (POPs) have been installed and are waiting on the fiber to reach them. We had built 600 miles of the fiber network at the end of the quarter, this is primarily backbone with a small amount of distribution fiber. 110 of Community Anchor Institutions (CAIs) are under contract. Fourteen of those are connected and receiving service. | 600 | 0 | 0 | 0 | 600 | 0 | 0 | 19 | Horizon lags baseline projections for a couple of reasons. The first being the delays caused by the Environmental Assessment, as it was not part of the project plan submitted with the application. This delay amounted to virtually ten months. Permitting and make-ready issues have caused a serious slow-down in our build rate. | n/a | n/a | n/a | Horizon lags baseline projections for a couple of reasons. The first being the delays caused by the Environmental Assessment, as it was not part of the project plan submitted with the application. This delay amounted to virtually ten months. Permitting and make-ready issues have caused a serious slow-down in our build rate. | n/a | n/a | While we appear to be behind our baseline of 29, all equipment has been installed and some awaits fiber. | 8 | 0 | 12 | Country Connections, Hocking Internet, Intelliwave, JB Nets, New ERA Broadband, Southern Ohio Communications Services, Rowe Wireless Networks, GMN Wireless Broadband | Horizon is offering wholesalers and last-mile providers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). | none | 2 | 4 | 0 | 6 | none | none | none | We have speed tiers available from 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). We have two at 10 Mbps; one at 20 Mbps; two at 50 Mbps and one at 100 Mbps. | 14 | 10 | 4 | 14 | Many Community Anchor Institutions (CAIs) hesitate to commit to a contract without the network being available in their area. Horizon lags baseline projections for a couple of reasons. The first being the delays caused by the Environmental Assessment, as it was not part of the project plan submitted with the application. This delay amounted to virtually ten months. Permitting and make-ready issues have caused a serious slow-down in our build rate. | none | none | We have speed tiers available from 5 Megabytes per second (Mbps) to 1 Gigabyte per second (Gbps) for CAIs. Eleven have chosen 10 Mbps tier; one has 50 Mbps tier and two have 100 Mbps tier. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none | FALSE | none | Horizon expects to build approximately 200 miles of backbone and another 100 miles of distribution fiber in the next quarter. We will continue to work with an expeditor on our problems with make-ready and permitting. We expect to have the two new wireless internet service providers (WISPs) online. | Horizon Telecom, Inc. | The project's progress faced delays this past quarter from issues surrounding make-ready and permitting. We have seen some progress with railroads, however crossing permits continue to take an inordinate amount of time. Make-ready consumes a lot of time and dollars. While we had overcome a large hurdle in the previous quarter with make-ready, more issues have arisen which continue to delay our build, including other utility providers and railroad permits. We continue to work on these issues from all foreseeable directions. Project coordination meetings were held with Ohio Department of Transportation (ODOT), Incumbent Local Exchange Carriers (ILECs)(local telephone companies), other utility providers, County and Municipal officials (like engineers or commissioners) in the counties included in the build-out of the network. | Horizon expects to continue to fight the battle against time on make-ready and permitting. | TRUE
NT10BIX5570119 | 2012 | Q3 | Q3 - 2012 | At the end of the third quarter of 2012, Horizon has built 708 miles of the fiber route. Over twenty percent of our Community Anchor Institutions (CAIs) are under contract. Twenty-six Community Anchor Institutions are online, receiving service. We have twelve contracts with Wireless Internet Service Providers (WISPs) with six of those online. Horizon successfully met the two-thirds milestone during the quarter. We have seen some success with our project coordination meetings, held with Ohio Department of Transportation (ODOT), Incumbent Local Exchange Carriers (ILECs)(local telephone companies), other utility providers, County and Municipal officials (like engineers or commissioners) in the counties included in the build-out of the network. Variance in budget categories from previous report due to spreadsheet issue (a column shifted). With resolution some numbers within the categories decline. These corrections also caused somewhat minor adjustments in milestone categories. | 708 | 0 | 0 | 0 | 708 | 0 | 0 | 23 | Slower than expected build rate this quarter due primarily to make-ready and permitting issues in addition to loss of crews to storm repair caused by Hurricane Isaac. | n/a | n/a | n/a | Slower than expected build rate this quarter due primarily to make-ready and permitting issues in addition to loss of crews to storm repair caused by Hurricane Isaac. | n/a | n/a | All equipment is installed in all Points-of-Presence (PoPs). They cannot be turned up until the backbone reaches them from one direction or another. | 12 | 0 | 12 | Avolve; Connectlink Inc; County Connection (2); Firewire; GMN Wireless Broadband; Intelliwave; JB-Nets LLC; New ERA Broadband; Rowe Wireless Networks; Smart Networks; SOCS. | Horizon is offering wholesalers and last-mile providers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). | none | 2 | 4 | 0 | 6 | none | none | none | We have speed tiers available from 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). We have one at 10 Mbps; one at 20 Mbps; three at 100 Mbps; and one at 150 Mbps. | 26 | 14 | 12 | 26 | Most Community Anchor Institutions (CAIs) are hesitant to sign a contract when the fiber has not reached them yet. As the network is build and CAIs can see the progress, more will be comfortable signing a contract. | none | none | We have speed tiers available from 5 Megabytes per second (Mbps) to 1 Gigabyte per second (Gbps) for CAIs. Seven have chosen 100 Mbps; one at 50 Mbps; two at 30 Mbps; one at 20 Mbps; fourteen at 10 Mbps; one at 5 Mbps. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none | FALSE | none | Horizon expects to have 900 miles of fiber built by the end of the quarter. We will continue to meet with all parties necessary to ensure make-ready and permitting continues to progress. A handful of Community Anchor Institutions (CAIs) will be connected this quarter. There are no additional broadband wholesaler/last mile provider/wireless internet service provider (WISP) agreements in the supply line, though we have had a lot of success in this area. | Horizon Telecom, Inc. | Our progress continues to be hampered by permitting and make-ready. Project coordination meetings continue with Ohio Department of Transportation (ODOT), Incumbent Local Exchange Carriers (ILECs)(local telephone companies), other utility providers, County and Municipal officials (like engineers or commissioners) in the counties included in the build-out of the network to help move make-ready and permitting process to move along. Power make-ready was impacted by Hurricane Isaac and the loss of those crews to deploy to the affected region. | Permitting and make-ready are most likely to cause delay. We could see the loss of power make-ready crews again, to assist in the clean-up of Hurricane Sandy. | TRUE
NT10BIX5570119 | 2012 | Q4 | Q4 - 2012 | At the end of the fourth quarter of 2012: Construction: Horizon has built over 900 miles of the fiber network. This quarter had twice the build rate of the previous quarter. We see this as a major positive. We continue to meet with all parties necessary to ensure make-ready and permitting continues to progress. Almost all railroad permits have been received - this was a huge barrier in previous quarters. Relationships continue to be fostered in an effort to smooth make-ready and permitting processes with all associated parties. Community Anchor Institutions (CAIs): Six new Community Anchor Institutions came online for a total of thirty-two. 118 of the Community Anchor Institutions are under contract. Wireless Internet Service Providers (WISPs): We have twelve contracts with WISPs with seven of those online. Points-of-Presence (POPs): Three additional POPs came online as fiber arrived for a total of twenty-six. Community Involvement: Horizon sponsored a number of events in it service area: The St. Clairsville Holiday on the Hilltop Christmas Parade in Belmont County. The Logan Santa Parade in Hocking County. Numerous Lunch and Learns with area business professionals discussing the benefits of utilizing a fiber optic network. Horizon also attended trade shows sponsored by area chambers of commerce. Horizon conducted a three-month campaign directed at businesses, schools, health facilities located along the network. | 900 | 0 | 0 | 0 | 900 | 0 | 0 | 26 | Build rates were in line with expectations this quarter. Most make-ready crews returned from outages caused by inclement weather in other parts of the country to work on our project and have made progress. | n/a | n/a | n/a | Build rates were in line with expectations this quarter. Most make-ready crews returned from outages caused by inclement weather in other parts of the country to work on our project and have made progress. | n/a | n/a | Equipment has been installed in all Points-of-Presence (POPs). This category is only slightly behind baseline of 29 and is only awaiting backbone connectivity. | 12 | 0 | 16 | Avolve; Connectlink, Inc; Country Connection (2); Firewire; GMN Wireless Broadband; Intelliwave; JB-Nets, LLC; New ERA Broadband; Rowe Wireless Networks; Smart Networks; Southern Ohio Communication Services (SOCS). | Horizon is offering wholesalers and last-mile providers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). Pricing Plan redacted. | none | 3 | 4 | 0 | 7 | none | none | none | We have speed tiers available from 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). We have two at 10 Mbps; one at 20 Mbps; three at 100 Mbps and one at 150 Mbps. | 32 | 14 | 18 | 32 | Community Anchor Institutions (CAIs) are behind baseline due to delay in backbone fiber reaching Points-of-Presence (POPs) to make connections. | none | none | We have speed tiers available from 5 Megabytes per second (Mbps) to 1 Gigabyte per second (Gbps) for CAIs. One has chosen 1 Gbps; nine have chosen 100 Mbps; one at 50 Mbps; two at 30 Mbps; two at 20 Mbps; sixteen at 10 Mbps; one at 5 Mbps. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none | FALSE | n/a | Horizon expects to have 1200 miles of fiber built by the end of the first quarter of 2013. We will continue to meet with all parties necessary to ensure make-ready and permitting continues to progress and find ways to improve the processes. Depending on the build rate success we could have another ten to fifteen Community Anchor Institutions (CAIs) connected this quarter. There are no additional broadband wholesaler/last mile provider/wireless internet service provider (WISP) agreements in the supply line, though we have had a lot of success in this area. | Horizon Telecom, Inc. | The biggest challenge Horizon faces is the delay caused by permitting and make-ready. With no governing authority, utilities, municipalities, counties, railroads, state and other local agencies work in an autonomous manner with no regard for the urgency of our requests or deadlines of our project. Even across the same organization, the permitting process can differ greatly. With our project extending across thirty-four counties, we find requirements much more stringent in one district than from another one. This does not allow for efficient or automated processes. One municipality wanted for us to provide them with detailed maps of how we would use their conduit system before we could use it. They did not have any decent maps of their own system. If we did not provide them we could not go through their city. With a handful of budget overruns, Horizon will need to put in additional funds. These areas are currently being audited. | Make-ready and permitting dictate our speed. They are very much out of our control. Horizon is working diligently to manage these issues to ensure no unnecessary delays occur. | TRUE
NT10BIX5570119 | 2013 | Q1 | Q1 - 2013 | Community Anchor Institutions (CAIs): Twenty-nine new Community Anchor Institutions came online for a total of sixty-one. Our 2012 APR report listed 16 Mbps as the average broadband speed provided which is well under our baseline. We indicated this was a direct result of the slower build rate. At the end of quarter 1 of 2013, Horizon has almost doubled the number of CAIs and the average broadband speed provided is now 97 Mbps. Points-of-Presence (POPs): Three additional POPs came online as fiber arrived for a total of twenty-nine. Wireless Internet Service Providers (WISPs): We have twelve contracts with WISPs with eight of those online. Community Involvement: Horizon presented construction update at the Connect Ohio Technology Summit in Columbus. We had booths at Chamber of Commerce functions in Jefferson, Washington and Jackson Counties plus an OME-RESA conference in Cambridge. We met with potential customers and CAI representatives at Chamber of Commerce luncheons/dinners/business showcases in Hocking, Tuscarawas, Columbiana, Pike, Gallia, Clermont, Athens and Jackson Counties over the course of the quarter. Construction: We have built over 1100 miles of the fiber network. Make-Ready continues to be a challenge on many fronts. Speed, cost and lack of response are the largest barriers we face at this point. | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 29 | Horizon has built over 1100 miles of backbone and distribution. | n/a | n/a | n/a | Horizon has built over 1100 miles of backbone and distribution. | n/a | n/a | Equipment has been installed in all Points-of-Presence (POPs). This category is only slightly behind baseline of 32 and is only awaiting backbone connectivity. | 12 | 0 | 16 | Avolve; Connectlink, Inc; Country Connection (2); Firewire; GMN Wireless Broadband; Intelliwave; JB-Nets, LLC; New ERA Broadband; Rowe Wireless Networks; Smart Networks; Southern Ohio Communication Services (SOCS). | Horizon is offering wholesalers and last-mile providers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). Pricing Plan redacted. | none | 7 | 5 | 0 | 12 | Total baseline for Last Mile Providers was 5. We have a positive variance of 7 with our 12 signed contracts. Four have yet to receive access due to lagging construction. | none | none | We have speed tiers available from 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). We have one at 10 Mbps; two at 20 Mbps; one at 100 Mbps; two at 150 Mbps; one at 200 Mbps and one at 500 Mbps. There are four agreements dependent on fiber currently under construction. They are contracted to receive the following: one at 30 Mbps; one at 50 Mbps and two at 100 Mbps. | 64 | 34 | 30 | 64 | Community Anchor Institutions (CAIs) connections are picking up pace as backbone segments are completed and Points-of-Presence (POPs) are brought online. | Baseline for this category was 148. These numbers are currently being revised due to a multitude of factors. | Baseline for this category was 444. These numbers are currently being revised due to a multitude of factors. | We have speed tiers available from <10 Mbps to â‰¥ 1 Gbps. We have eight in the < 10 Mbps tier; thirty-eight in the â‰¥ 10 Mbps and < 50 Mbps; one in the â‰¥ 50 Mbps and < 100 Mbps; thirteen in the â‰¥ 100 Mbps and < 1 Gbps; and four in the â‰¥ 1 Gbps. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none | FALSE | n/a | Horizon expects to bring three more POPs online this quarter. We plan to have 1250 miles built by the end of the quarter. Expect to serve 20 additional CAIs this quarter. We are not expecting to sign any additional wholesaler/last mile providers over the next quarter. | Horizon Telecom, Inc. | Challenges this quarter were led by the high costs of make-ready. Consistent with instruction early in project, percentage complete is based on the current budget filed with NTIA. We are projecting costs to be higher in various areas. | High costs and delays caused by make-ready. | TRUE
NT10BIX5570119 | 2013 | Q2 | Q2 - 2013 | Horizon met with NTIA and NOAA officials in Washington DC in May to review strategies to accomplish project scope. Horizon presented a proposal and NTIA agreed with a plan to move forward. Horizon is working its way through this plan and will be submitting Award Action Requests (AARs) for Community Anchor Institutions (CAIs), distribution route modifications for CAIs and a new budget to include cost overruns. An extension request from 7/31/2013 to 12/31/2013 was requested and approved. This was necessary for final make-ready (MR), permitting and easements to be resolved. This will also allow Horizon to complete more miles of backbone and distribution and connect additional CAIs. Points of Presence (POPs) - Four additional POPs came online as fiber reached them for a total of thirty-three. Community Anchor Institutions (CAIs) - Sixteen new CAIs were connected for a total of eighty. Community Involvement - Over the course of the quarter Horizon attended numerous Chamber of Commerce Business After Hours events. Also attend the Port Authority Meeting in Wintersville and Connect Ohio Technology Meeting in Byesville. Participated in networking events in Guernsey, Jefferson, Tuscarawas and Washington Counties. We attended and staffed an information booth on the Connecting Appalachia Project during the Ohio Association of School Business Official Trade Show in Columbus. We attend the monthly meetings of the Connect Ohio - Connect Appalachia Broadband Initiative team as a member, as well as quarterly meetings for OMEGA and EODA. Average broadband speed is over 106 Mbps - this is up from 97 Mbps at the end of last quarter and 16 Mbps at the end of 2012. Construction - 1100 miles of backbone and distribution have been built. Cost per mile has been much higher than anticipated due primarily to make-ready. Wireless Internet Service Providers (WISPs) - We have thirteen contracts with WISPs with eight of those online. | 1100 | 0 | 0 | 0 | 1100 | 0 | 0 | 33 | High costs and A/P slowed construction during this quarter. The backbone and distribution are currently projected to be 1140 miles. | n/a | n/a | n/a | High costs and A/P slowed construction during this quarter. The backbone and distribution are currently projected to be 1140 miles. | n/a | n/a | Equipment has been installed in all Points-of-Presence (POPs). This category is sightly behind baseline of 36. | 17 | 1 | 21 | Avolve; Connectlink, Inc; Country Connection (2); Firewire; GMN Wireless Broadband; Intelliwave; JB-Nets, LLC; New ERA Broadband (2); Rowe Wireless Networks; Smart Networks; Southern Ohio Communication Services (SOCS); Sprint; Verizon (2); Windstream. | Horizon is offering wholesalers and last-mile providers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). Pricing Plan redacted. | none | 16 | 0 | 1 | 16 | Total baseline for Wholesalers or Last Mile Providers was 7. We have a positive variance of 9 with our 16 signed contracts. Four have yet to receive access due to lagging construction. We have three wholesale agreements, each in various stages of completion. | none | We have one dark fiber agreement in the process of being accepted. | We have speed tiers available from 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). 1 = 10 Mbps 1 = 20 Mbps 4 = 50 Mbps 1 = 100 Mbps 3 = 150 Mbps 1 = 200 Mbps 1 = 500 Mbps There are four agreements dependent on fiber currently under construction. They are contracted to receive the following: one at 10 Mbps; one at 30 Mbps; and two at 100 Mbps. | 80 | 75 | 5 | 80 | Community Anchor Institutions (CAIs) connections are connected and brought online as backbone segments are completed and Points-of-Presence (POPs) are brought online. Horizon passes and is ready to serve an additional 145 CAIs which are within 250' of either backbone or distribution laterals. | Baseline for this category was 148. Unlike many projects of its size, this project did not have the benefit of a direct relationship with the CAIs it intended to serve. Meaning the CAIs had no obligation to take our service. Our financial models had underlying assumptions including penetration rates of increasing percentages. Year one being the first year with a network up and running was projected to be only 55-60 CAIs total between new and improved. | Baseline for this category was 444. Our financial models had underlying assumptions including penetration rates of increasing percentages. Year one being the first year with a network up and running was projected to be only 55-60 CAIs total between new and improved. This number decreased to five because of adjustments in our definition of new versus improved. Horizon has many additional customers who have benefited (improved access) from the electronics provided by these funds. | We have speed tiers available from <10 Mbps to â‰¥ 1 Gbps. 7 = < 10 Mbps tier; 36 = â‰¥ 10 Mbps and < 50 Mbps 1 = â‰¥ 50 Mbps and < 100 Mbps 27 = â‰¥ 100 Mbps and < 1 Gbps 5 = â‰¥ 1 Gbps. 4 = = not a customer | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none | FALSE | n/a | Three AARs will be filed. Construction should be virtually complete by the end of the next quarter. Our CAI count will increase by approximately ten over the next quarter. The approval of the CAI Award Action Request (AAR) will give a better visual of the positive impact of the CAO-MMC project on the region. | Horizon Telecom, Inc. | Our challenges continue to be the high cost of make-ready. This has had a huge negative impact on the cost and pace of the entire project. Equipment overages are driven primarily by six additional POPs (over what was in model and budget) necessary to complete the network. Some of the additional costs are engineering in nature, as some segments required intermediate equipment to regenerate the signal on long routes. Other additional cost has been required in order to add additional wavelengths necessary for transporting higher than anticipated bandwidth because of greater demand. CAI connection numbers appear worse than they are as compared to targets. Our financial models had underlying assumptions including penetration rates of increasing percentages (year 1 = 10%, year 2 = 20%, etc up to 50% at the end of year 5, then holding constant). Year one being the first year with a network up and running was projected to be only 55-60 CAIs total between new and improved. Additionally the delays caused by make-ready, permit and easement issues have delayed our ability to reach some CAIs forcing them to take alternative action such as signing agreements with another provider. | Costs will continue to be our largest barrier. | TRUE
NT10BIX5570119 | 2013 | Q3 | Q3 - 2013 | Horizon has 260 Community Anchor Institutions (CAIs) at the end of the third quarter of 2013. 98 are new builds/access with 92 customers receiving access on new fiber and six CAIs connected to new fiber but not subscribed as a customer. Baseline for this data point is 148. Most recent approved key performance indicators (KPIs) indicated there would be 95 in this category at the end of the project. 162 are improved with eight of these as customers. Horizon has direct connections (subscriptions ranging from 10 Mbps to 100 Mbps) to 4 Information Technology Centers and 2 medical system networks that enable an additional 154 elementary, middle, high schools, some government facilities and some health system satellite offices to receive faster speeds, reliability and availability. Most recent approved KPIs indicated there would be 105 in this category at completion of project. Community Involvement: We continue to attend the monthly meetings of the Connect Ohio - Connect Appalachia Broadband Initiative team as a member, as well as quarterly meetings for OMEGA and EODA. We also continue to attend and participate in Chamber events and Port Authority meetings in numerous counties. Horizon updated economic development committees, county commissioners, city councils, mayors, state and federal legislators on the progress of the project. We also continue with branding and marketing advertising fliers in the counties of Athens, Belmont, Guernsey, Hocking, Muskingum and Washington. NTIA approved a no-cost extension through 12/31/2013. Construction: 1,245 network miles is 1,022.5 miles of backbone and 222.5 miles of distribution. Overall the network will be 1,262.5 miles. Backbone: Originally expected to be 1,097 miles at time of application and baseline and most recent approved KPIs expected this to be 952 miles by the end of the project, backbone is currently slated to be 1,035 miles at term. Distribution: Originally expected to be 863 miles at time of application and baseline and most recent approved KPIs expected this to be just under 200 miles, distribution is currently slated to be 227.5 at the end of the project. The optimized backbone reduced the number of distribution miles necessary. Points-of Presence (POPs): We have thirty-four POPs online. Our baseline had thirty-six for this point in our project. Wholesalers and Last Mile Providers: Total baseline for Wholesalers or Last Mile Providers was 5. We have a positive variance of 12 with our 17 signed contracts. Wireless Internet Service Providers (WISPs): We have thirteen contracts with WISPs with ten of those online. Three WISPs have yet to receive access due to lagging construction. Wholesale agreements: We have three signed wholesale agreements (approximately 200 towers) at various stages of being fulfilled. We have one dark fiber agreement. | 1245 | 0 | 0 | 0 | 1245 | 0 | 0 | 34 | 1,245 network miles is 1,022.5 miles of backbone and 222.5 miles of distribution. Overall the network will be 1,262.5 miles. Backbone: Originally expected to be 1,097 miles at time of application and baseline and most recent approved KPIs expected this to be 952 miles by the end of the project, backbone is currently slated to be 1,035 miles at term. Distribution: Originally expected to be 863 miles at time of application and baseline and most recent approved KPIs expected this to be just under 200 miles, distribution is currently slated to be 227.5 at the end of the project. The optimized backbone reduced the number of distribution miles necessary. | The strategy to use leased fiber to mitigate or bypass a difficult make-ready, easement situation has not come to fruition. | n/a | n/a | 1,245 network miles is 1,022.5 miles of backbone and 222.5 miles of distribution. Overall the network will be 1,262.5 miles. Backbone: Originally expected to be 1,097 miles at time of application and baseline and most recent approved KPIs expected this to be 952 miles by the end of the project, backbone is currently slated to be 1,035 miles at term. Distribution: Originally expected to be 863 miles at time of application and baseline and most recent approved KPIs expected this to be just under 200 miles, distribution is currently slated to be 227.5 at the end of the project. The optimized backbone reduced the number of distribution miles necessary. | n/a | n/a | Equipment has been installed in all Points-of-Presence (POPs). | 17 | 1 | 21 | Avolve; Connectlink, Inc; Country Connection (2); Firewire; GMN Wireless Broadband; Intelliwave; JB-Nets, LLC; New ERA Broadband (2); Rowe Wireless Networks; Smart Networks; Southern Ohio Communication Services (SOCS); Sprint; Verizon (2); Windstream. | Horizon is offering wholesalers and last-mile providers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). Pricing Plan redacted. | none | 17 | 0 | 1 | 7 | Total baseline for Wholesalers or Last Mile Providers was 5. We have a positive variance of 12 with our 17 signed contracts. Three WISPs have yet to receive access due to lagging construction. We have three signed wholesale agreements (approximately 200 towers) in various stages of being fulfilled. | none | One dark fiber agreement is in the process of being implemented - we have delivered the dark fiber and provided test results and now await acceptance by the customer. | We have speed tiers available from 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). 2 = 10 Mbps 1 = 20 Mbps 4 = 50 Mbps 1 = 100 Mbps 3 = 150 Mbps 1 = 200 Mbps 1 = 500 Mbps There are three agreements dependent on fiber currently under construction. They are contracted to receive the following: one at 30 Mbps; and two at 100 Mbps. | 260 | 98 | 162 | 11 | Horizon is in the process of submitting an AAR requesting the addition of approximately 384 qualifying CAIs not originally included in our application. These are customers benefiting from the fiber network. This number is not expected to change. There are three CAIs who could move from the improved category to the new category. | 98 is 92 customers receiving access on new fiber and six CAIs connected to new fiber but not subscribed as a customer. Baseline for this data point is 148. Most recent approved KPIs indicated there would be 95 in this category at the end of the project. | Eight of these are customers. Horizon has direct connections (subscriptions ranging from 10 Mbps to 100 Mbps) to 4 Information Technology Centers and 2 medical system networks that enable an additional 154 elementary, middle, high schools, some government facilities and some health system satellite offices to receive faster speeds, reliability and availability. Most recent approved KPIs indicated there would be 105 in this category at completion of project. | We have speed tiers available from <10 Mbps to â‰¥ 1 Gbps. Mbps = CAIs 5 = 13 10 = 102 20 = 31 30 = 6 40 = 3 50 = 12 100 = 82 200 = 2 250 = 2 500 = 2 1000 = 5 | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none | FALSE | n/a | Construction: 17.5 miles will be built this quarter as we wrap up network construction. 12.5 of these miles are backbone and 5 are distribution. Most, if not all, of these will be in areas where previous issues (make-ready, easement, permit, etc) blocked completion. This quarter will be spent on resolving those issues. Budget: The new budget will be resubmitted as per instructions from NTIA. CAI Distribution Route Change AAR will be resubmitted with additions per instructions. | Horizon Telecom, Inc. | Horizon still faces challenges with the final permits and easements needed to complete the final backbone segments. | Challenges will be the final permits and easements needed to complete the backbone segments around Columbus. | TRUE
NT10BIX5570119 | 2013 | Q4 | Q4 - 2013 | Horizon has 256 Community Anchor Institutions (CAIs) at the end of the of 2013. 95 are new builds/access with 89 customers receiving access on new fiber and six CAIs connected to new fiber but not subscribed as a customer. Baseline for this data point is 148. Most recent approved key performance indicators (KPIs) indicated there would be 95 in this category at the end of the project. 161 are improved with eight of these as customers. Horizon has direct connections (subscriptions ranging from 10 Mbps to 100 Mbps) to 4 Information Technology Centers and 2 medical system networks that enable an additional 153 elementary, middle, high schools, some government facilities and some health system satellite offices to receive faster speeds, reliability and availability. Most recent approved KPIs indicated there would be 105 in this category at completion of project. NTIA approved a no-cost extension through 6/30/2014. Construction: Construction is complete with the exception of some testing. 1,265 network miles is 1,035 miles of backbone and 230 miles of distribution. Overall the network will be 1,265 miles. Backbone: Originally expected to be 1,097 miles at time of application and baseline and most recent approved KPIs expected this to be 952 miles by the end of the project, backbone is currently slated to be 1,035 miles at term. Distribution: Originally expected to be 863 miles at time of application and baseline and most recent approved KPIs expected this to be just under 200 miles, distribution is currently slated to be 230 at the end of the project. The optimized backbone reduced the number of distribution miles necessary. Points-of Presence (POPs): We have thirty-four POPs online. Our baseline had thirty-six for this point in our project. Wholesalers and Last Mile Providers: Total baseline for Wholesalers or Last Mile Providers was 5. We have a positive variance of 13 with our 18 signed contracts. Wireless Internet Service Providers (WISPs): We have thirteen contracts with WISPs with ten of those online. Three WISPs have yet to receive access due to lagging construction. Wholesale agreements: We have three signed wholesale agreements (approximately 200 towers) at various stages of being fulfilled. We have two dark fiber agreements. | 1265 | 0 | 0 | 0 | 1265 | 0 | 0 | 34 | Construction is complete with the exception of some testing. 1,265 network miles is 1,035 miles of backbone and 230 miles of distribution. Overall the network will be 1,265 miles. Backbone: Originally expected to be 1,097 miles at time of application and baseline and most recent approved KPIs expected this to be 952 miles by the end of the project, backbone is currently slated to be 1,035 miles at term. Distribution: Originally expected to be 863 miles at time of application and baseline and most recent approved KPIs expected this to be just under 200 miles, distribution is currently slated to be 230 at the end of the project. The optimized backbone reduced the number of distribution miles necessary. | n/a | n/a | n/a | Construction is complete with the exception of some testing. 1,265 network miles is 1,035 miles of backbone and 230 miles of distribution. Overall the network will be 1,265 miles. Backbone: Originally expected to be 1,097 miles at time of application and baseline and most recent approved KPIs expected this to be 952 miles by the end of the project, backbone is currently slated to be 1,035 miles at term. Distribution: Originally expected to be 863 miles at time of application and baseline and most recent approved KPIs expected this to be just under 200 miles, distribution is currently slated to be 230 at the end of the project. The optimized backbone reduced the number of distribution miles necessary. | n/a | n/a | Equipment has been installed in all Points-of-Presence (POPs). | 18 | 0 | 21 | Avolve; Connectlink, Inc; Country Connection (2); Firewire; GMN Wireless Broadband; Intelliwave; JB-Nets, LLC; New ERA Broadband (2); Rowe Wireless Networks; Smart Networks; Southern Ohio Communication Services (SOCS); Sprint; Verizon (3); Windstream. | Horizon is offering wholesalers and last-mile providers speed tiers of 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). Pricing Plan redacted. | none | 18 | 0 | 2 | 7 | Total baseline for Wholesalers or Last Mile Providers was 5. We have a positive variance of 13 with our 18 signed contracts. Three WISPs have yet to receive access due to lagging construction. We have three signed wholesale agreements (approximately 200 towers) in various stages of being fulfilled. We have two dark fiber agreements. | none | none | We have speed tiers available from 5 Megabytes per second (Mbps) to 10 Gigabytes per second (Gbps). 2 = 10 Mbps 1 = 20 Mbps 4 = 50 Mbps 1 = 100 Mbps 3 = 150 Mbps 1 = 200 Mbps 1 = 500 Mbps There are three agreements awaiting final connection. They are contracted to receive the following: one at 30 Mbps; and two at 100 Mbps. There are two agreements for dark fiber - no tier assigned. | 256 | 95 | 161 | 10 | Horizon is in the process of submitting an AAR requesting the addition of approximately 490 qualifying CAIs not originally included in our application. These are customers benefiting from the fiber network. This number is not expected to change. There are three CAIs who could move from the improved category to the new category. | 95 is 89 customers receiving access on new fiber and six CAIs connected to new fiber but not subscribed as a customer. Baseline for this data point is 148. Most recent approved KPIs indicated there would be 95 in this category at the end of the project. | Eight of these are customers. Horizon has direct connections (subscriptions ranging from 10 Mbps to 100 Mbps) to 4 Information Technology Centers and 2 medical system networks that enable an additional 153 elementary, middle, high schools, some government facilities and some health system satellite offices to receive faster speeds, reliability and availability. Most recent approved KPIs indicated there would be 105 in this category at completion of project. | We have speed tiers available from <10 Mbps to â‰¥ 1 Gbps. Mbps = CAIs 5 = 20 10 = 82 20 = 32 30 = 5 40 = 8 100 = 87 200 = 3 250 = 3 500 = 3 1000 = 13 | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none | FALSE | n/a | Construction is complete. Final segment testing is nearly complete. AARs to be completed: - Budget - Route Change Laterals - CAI | Horizon Telecom, Inc. | Horizon has experienced challenges in completing grant modification Award Action Requests (AARs) to modify network mileage and Community Anchor Institution (CAI) targets. | Horizon is experiencing challenges in completing grant modification Award Action Requests (AARs) to modify network mileage and Community Anchor Institution (CAI) targets. | TRUE
NT10BIX5570120 | 2010 | Q4 | Q4 - 2010 | Activities of the quarter focused primarily on engineering and environmental assessment work. A contract was awarded to a firm to oversee the design and EA work for the entire route. Legal documents were shared between MCNC and those companies providing IRUâ€™s for the project. Easement donation paperwork from community colleges along the route commenced. All work by the EA firm was tracking toward completion by February of the EA draft for NTIA. RFPâ€™s for mapping and materials were released and closed during the quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A to our project | N/A to our project | N/A to our project | N/A to our project | N/A to our project | 0 | 0 | 0 | 0 | 0 | N/A to our project | N/A to our project | N/A to our project | N/A to our project | N/A to our project | N/A | FALSE | N/A | We expect to submit our draft EA to the NTIA by 2/1/2011. We expect to have awarded a contract for materials related to the project. To get a jump on construction, we expect to release and close a construction RFP during the quarter to identify firms to perform the physical work in the field. Lastly we expect to have most IRU arrangements, for fibers we plan to acquire as part of the contract, in a state ready to execute when a FONSI is received. | MCNC | No unexpected issues or challenges were experienced this quarter toward completion of the project. | Timely receipt of a FONSI, before quarter close,will be critical to the project staying within the timeline and will be extremely valuable in terms of construction efforts, as we expect to be ready to select and/or contract with (or be close to contracting with) a materials vendor by the end of the quarter. | TRUE
NT10BIX5570120 | 2011 | Q1 | Q1 - 2011 | Activities for the quarter were limited to work on environmental and engineering elements of the project. The activities of the MCNC portions of the project as well as ERC's who is a sub-recipient were tightly coupled due to EA and engineering work being tied together to complete the EA draft for the entire project. Our project team met a critical milestone with the submission of the draft environmental assessment to the NTIA on 2/1/2011. Comments from NTIA were returned the middle of March and at the end of the quarter those questions were being addressed. Engineering efforts on the project began with the entire route having base mapping performed and initial field engineering efforts commencing. By the end of the quarter the first permitting activities had begun with the NC Department of Transportation and various controlling railroads along the route. A fair amount of time has been spent working through overlap issues with other federally funded projects within the state, with the bulk of that work with USDA RUS award winners. During the quarter we awarded a contract to Commscope for materials related to the project that will start to be ordered at which point the environmental assessment results in a FONSI. In addition we opened and closed an RFP for construction of the conduit/fiber. At the end of the quarter selection of those vendors to perform this function were being evaluated. Lastly, discussion of all planned IRU's commenced with those providers that woul | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ERC had anticipated deploying a small amount of fiber to one of it's CAI's in the third quarter had the FONSI been received but this did not happen. The variance to budget is insignificant in quantity. | na | na | na | The provided baseline miles were anticipated to be miles completed by ERC early in the process had we finalized the EA and received FONSI. Given this hasnâ€™t occurred construction couldnâ€™t start. The variance will be overcome as FONSI is obtained. | Not applicable to our project | Not applicable to our project | na | 1 | 4 | 80 | French Broad Electric Membership regarding a proposed IRU for fibers in their footprint. | Services offered on this network will range from dark fiber sales/leases to 10Gbps provisioned lambdas, with all available speeds between available. See attachedk will range from dark fiber sales/leases to 10Gbps provisioned lambdas, with all available speeds between available. See attached. | Not applicable at this time. We anticipate potentially releasing an RFP in the next quarter for identifying a firm to assist in this process. | 0 | 0 | 0 | 0 | Discussions are ongoing with many interested entities regarding potential access to fibers, but none are imminent. Forecasts here were wrong in that they may have included the planned IRU's of fiber purchases in error. | Discussions are ongoing with many interested entities regarding potential access to fibers, but none are imminent. | na | na | 0 | 0 | 0 | 0 | No construction activities have commenced. | No construction activities have commenced. | No construction activities have commenced. | No construction activities have commenced. | 0 | 0 | 0 | 0 | 0 | Not applicable to our project | Not applicable to our project | Not applicable to our project | Not applicable to our project | Not applicable to our project | 0 | 0 | 0 | 0 | 0 | No construction activities have commenced. | No construction activities have commenced. | No construction activities have commenced. | No construction activities have commenced. | No construction activities have commenced. | We are able to provide lambda based point to point based circuits between the NCREN POP's enabled by the new infrastructure. | FALSE | na | We hope to achieve a FONSI in the next quarter. We hope to have greater than 90% of the route engineered/designed. If FONSI is obtained in May, we believe we can begin construction activities in June in advance of quarter ending. We hope to have greater than 50% right of way's applied for and 25% of construction permits achieved. We anticipate planning a ground breaking activity for July. We hope to execute on two of the IRU agreements we had outlined at project application (Zayo and Blue Ridge Electric) during the quarter securing rights to 107 miles of the project. | MCNC | The size of the project is significant. Performing the EA on the entire footprint of the project and not being able to separate the laterals for the CAI connections from the middle mile to get started made completion of the EA draft a challenge. We are concerned with timeliness of receiving the FONSI in the fourth quarter. We feel if the laterals could have been separated from the trunk aspects of our project, work could begin quicker. Even given this, we still believe completion will not be a concern. The overlap issues have been problematic, especially given that the USDA RUS award winners do not have the same set of special award considerations to live up to, and so thus do not necessarily share the same motivation we do to close the issues out. We continue to aggressively work these issues. | Timely receipt of a FONSI. Final guidance from NTIA on how to structure sale/lease/swap of fiber to finalize the subrecipient IRU's of fiber from ERC to MCNC will be crucial. Cooperation from NC DOT on design of route and granting of ROW encroachments is crucial. We are consulting with them on planned traffic improvement plans that could potentially require some reroutes to avoid areas where road widening projects are slated to begin, and we will be learning of these activities over the next 3-6 months. Final execution of the planned IRU's is critical at the front end so as to make sure all planned acquisitions are completed without issue. Beyond that, our engineering firm is performing superbly, and with contracts ready to be signed with contractors and materials contract signed as well, if we have a FONSI in hand in a timely fashion and encroachments from DOT, there is no reason we can't begin construction activities by end of June at the latest. Until solved, the overlap issues with other federal projects, particularly USDA RUS, will be a drag on the project and take a large allocation of time to solve relative to the overall project. | TRUE
NT10BIX5570120 | 2011 | Q2 | Q2 - 2011 | Activities of the quarter focused on wrapping up the environmental and engineering efforts of the project. On June 23 MCNC received the FONSI for the project, clearing the way for construction efforts to begin. Formal engineering for the routes of the project continues with prime routes nearing 100% completion. During the quarter MCNC awarded construction contracts to three prime contractors for the project. Negotiations continued during the quarter on contracts related to Indefeasible Rights to Use that were outlined in the original project plan. At end of quarter none had been signed, but two were involved in significant legal editing. Permitting efforts have commenced, but it is very early in the approval process. We expect construction efforts to begin by the end of the July quarter and execution of a number of IRUâ€™s to be complete by end of the quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We originally forecasted FONSI late April and didn't receive until June 23. This put us slightly behind schedule. We would expect to offset within the next two reporting quarters due to having our construction firms beginning work at an expedited pace. We have communicated to them that once we are at full construction capacity, we need to be deploying between 90-100 miles per month between the three prime contractors and the segments we plan to release for construction. | We originally forecasted FONSI late April and didn't receive until June 23. This put us slightly behind schedule. We would expect to offset within the next two reporting quarters. We are confident we will have all planned IRU's completed by the end of the third quarter because we placed a priority on this with the companies and our legal counsel. At the end of the 2nd quarter we were in round 2 of iterations between our legal counsel and the companies we plan to IRU with. Generally we resolve these issues in 3-4 iterations. | N/A | N/A | We originally forecasted FONSI late April and didn't receive until June 23. This put us slightly behind schedule. We would expect to offset within the next two reporting quarters due to having our construction firms beginning work at an expedited pace. We have communicated to them that once we are at full construction capacity, we need to be deploying between 90-100 miles per month between the three prime contractors and the segments we plan to release for construction. | N/A | N/A | We originally forecasted FONSI late April and didn't receive until June 23. This put us slightly behind schedule. We would expect to offset within the next two reporting quarters due to having our construction firms beginning work at an expedited pace. We have communicated to them that once we are at full construction capacity, we need to be deploying between 90-100 miles per month between the three prime contractors and the segments we plan to release for construction. | 0 | 0 | 0 | At the end of the quarter, we had no signed agreements. We had, however, released a marketing partner RFP to determine a potential wholesale carrier to operate on the enabled infrastructure and actively market the fiber. | None available at this time. | Not applicable at this time. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | We expect to begin construction on a larger scale during the quarter. We expect to release and close an RFP for equipment to be deployed on the network. We expect to award a contract for marketing services and fiber to commercial entities on the network that we released and closed during the current quarter. We anticipate all formal engineering to mostly complete except for any potential reroutes that may be required due to permitting issues. As part of this, we would expect to begin receiving an abundance of all required construction permits. Lastly we will be holding a virtual statewide ground breaking on 8/12 to celebrate the project. | MCNC | The permitting process has proven to be slow because of the size of the project and the fact that it is statewide. We've had this feedback directly from NC DOT. We are working through the process and expect to make up variances that we have in the next quarter. Coordination with the CAI's that will get direct fiber has been a challenge. We had one proposed IRU provider change terms related to our planned acquisition that has forced us to consider a direct build now that we have presented to NTIA. We also have found a few locations on our route that we believe NC DOT will not let us construct on due to controlled access issues, that will require mandatory reroutes. We expect to get closure on these in August and will present findings to NTIA at that time. None put the project at risk, but will require us to move to secondary roads in the same proposed areas in some cases. We did not receive our FONSI as quickly as we might have hoped. This was due to issues related to our subrecipient performing in our EA corridor that have previously been documented through our performance improvement plan. | We believe we will continue to churn through the permit process but hope to make great headway in that regard. By end of next quarter we expect to have applied for most if not all construction permits related to rights of way. We are hearing some concerns from our materials vendor about timeliness on delivery of materials if we don't forecast our needs well in advance. We believe our approach to the project, which involves our materials contractor represented at all our weekly status calls, will mitigate those issues. With knowledge of our round 1 build and things to expect during construction, we are prepared to handle these better, but due to the amount of construction that will happen, realize the potential for these is broader. These include interactions with the permitting entities when we get in the field, municipalities as we move through their areas, and landowners concerned with how their property adjacent to right of ways is impacted. While we don't believe that these are challenges, we have realized a couple of opportunities to IRU fibers from incumbent providers for last mile portions of our network to CAI's, and expect to bring these to NTIA for consideration during the quarter. Continued timely engagement from our NTIA team on issues we can't handle will be paramount given the size of our project. Oversight of the ERC as a subrecipient due to some of the complexities of their project will continue to be a challenge. To mitigate this we are bringing in | TRUE
NT10BIX5570120 | 2011 | Q3 | Q3 - 2011 | Construction began this quarter on the first priority route leaving Charlotte, and at end of the quarter we had 67 miles of conduit placed, and pulled in the first seven miles of fiber. We continue to finalize the engineering of the route and working with the appropriate permitting agencies for ROW/easement access. During the quarter we closed an RFP to identify a marketing partner for commercial aspects of the build, and selected ECC Technologies who will be based out of Wake Forest for the project. In addition, we released and closed an RFP to determine an equipment vendor for the project, and released an RFP to determine a contractor to do the specialized bridge attachments required to complete the project. Negotiations continued during the quarter on contracts related to Indefeasible Rights to Use that were outlined in the original project plan, and for those identified after the project commenced with incumbent providers for existing/available fiber. At the end of the quarter we had completed acquisition of 26 miles of fiber from Zayo, and were nearing completion on IRU's with Blue Ridge Electric Membership Corporation and Skyline Telephone Membership Corporation. We continued to work with community colleges and universities around the state to finalize easements for land to locate telecommunication huts along the route. Lastly, we held a statewide virtual ground breaking in August attended by many members of the North Carolina Congressional Delegate as well as m | 7 | 26 | 60 | 0 | 7 | 0 | 0 | 141 | Only 7 miles of fiber deployed. 60 additional miles of conduit without fiber has been deployed. Slower start to construction is the reason for the lower rate, but we expect to recover within 1-2 quarters. We project to be at 67% completion for fiber by end of July 2012 and 100% complete by end of March 2013. | Completed the Zayo fiber acquisition. Formal agreements with BREMCO were close, but not signed off on. Expect to recover from this by next reporting quarter when as many as 4 of the remaining IRU's may finalize that we are expecting. We project to be at 67% completion for fiber leased by June of 2012 and 100% completion for fiber leased by December of 2012. | 60 miles of existing fiber (40 from existing owned Level3 route, 20 from BTOP1 project) are slated to be placed in to service. | NA | We are behind to our planned forecast. Primarily this is due to a slower start to construction which equates to a slower deployment of fiber in the built conduit. We have 7 miles of fiber placed and over 60 miles of conduit. We should recover from this discrepancy within 2 quarters. We project to be at 67% completion for fiber by end of July 2012 and 100% complete by end of March 2013. | NA | NA | The delay in starting construction means we haven't hit this forecast. But with further acquisitions of IRU's and more construction in the next quarter, we should be back on schedule. We expect to be at 67% completion for fiber by end of July 2012 and 100% complete by end of March 2013n means we haven't hit this forecast. But with further acquisitions of IRU's and more construction in the next quarter, we should be back on schedule. We expect to be at 67% completion for fiber by end of July 2012 and 100% complete by end of March 2013. | 0 | 0 | 0 | At the end of the quarter, we had no signed agreements. We have, however, selected a marketing partner to actively promote the fiber. Prospects from this company look extremely promising. While we had forecasted 3 agreement at this juncture, the delay in start to construction as well as finalizing the marketing partner contributed to us being behind. We would anticipate as segments are finished being built that over the next 3-4 quarters we will realize having signed agreements as this marketing firm begins their work. | None available at this time. We anticipate a carrier to gain access in the route in the future, who will offer a fully array of telecom services. To our CAI consituents, we will be offering IP service up to 10Gbps, lambda (circuit) services, as well as dark fiber as requestede anticipate a carrier to gain access in the route in the future, who will offer a fully array of telecom services. To our CAI consituents, we will be offering IP service up to 10Gbps, lambda (circuit) services, as well as dark fiber as requested. | Not applicable at this time. | 0 | 0 | 0 | 0 | No variance to baseline | No variance to baseline | No variance to baseline | No variance to baseline. | 0 | 0 | 0 | 0 | Our projection on this was too fast and our build out of the middle mile not far enough along to allow for support of this yet. We will be 3-4 quarters away from realizing this target. | Our projection on this was too fast and our build out of the middle mile not far enough along to allow for support of this yet. We will be 3-4 quarters away from realizing this target. | NA | We will be providing dark fiber, IP services up to 10Gbps, and lambda (circuit) based services. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | We expect to begin construction on a larger scale during the quarter. We released and closed an RFP for equipment to be deployed on the network, and will be going through proof of concept labs with the finalists. We anticipate starting the highly specialized bridge construction involved over 15 miles of the project. We anticipate all engineering efforts to be mostly complete, as well as securing of many of the remaining permits required for construction. We also intend to close around 3-4 IRU agreements for miles associated with the project. By the end of the quarter we anticipate total deployment of 250 miles of conduit, 100 miles of fiber placed within that conduit, and finalization of IRU's representing 200 miles of leased fiber. We anticipate new fiber to potentially 10-12 CAI's within the period. We do not anticipate closing any new agreements for sales/leases of dark fiber. | MCNC | The permitting process continues to be a work in progress, specifically with the NC Department of Transportation. We have also been requested by the NC Department of Natural Resources to apply for a Coastal Area Management Act Permit for 20 coastal counties because of the broad scope of the project, which is not something we were expecting to have to do based on guidance on their internet web site. While the process is expected to take about 4 months in total, because that construction is slated toward the end of our project, we don't believe this to be a concern. Coordination with the CAI's that will get direct fiber has been a challenge also, but we are gaining more traction with this and have roughly 1/2 of the sites completed now. We have encountered a few situations where our originally proposed route could not be continued due to a variety of issues including controlled access right of way, water crossings, and NC Forest Service permitting issues. This forced us to look at alternatives that we have presented to NTIA for consideration. None of these place the project at risk but add time delay to the execution of the project as we have to cycle through an EA amendment process. Timely review by NTIA of these changes and the EA amendments associated with them will help us stay on track as we work around those areas that lack final approval. | Finalization of all permits is a major goal for the next quarter. Although some areas will not have construction start on them for 9-12 months, it is important to get these wrapped up so as not to have to continue to spend resource on them. While we have not requested permission on a larger number of route adjustments, timely review and consideration of them by NTIA will be important to help us keep on track due to having to wait until formal acceptance by NTIA to order materials, equipment, and to begin construction. Given past history with NTIA on quick turnaround of these, we don't view this as a major challenge. Fiber delivery is somewhat troubling. While our contract with Commscope is very aggressive and they have done a good job of committing a certain schedule of delivery to us, should they have any hiccup in their supply chain of glass to their cable manufacturing plant, we could fall behind. Based on their manufacturing commitment of 125,000 feet of fiber per week, and the number of miles we have to deploy, they will be manufacturing our cable for the next year. Any disruption in that will push our installation schedule out. However, we are not extremely worried about this due to our contract as noted before. Lastly, with the onset of winter, weather in certain areas of the state could be problematic and any days lost to rain/snow/ice will add time to the end of the project. | TRUE
NT10BIX5570120 | 2011 | Q4 | Q4 - 2011 | Construction continued this quarter on the first priority segment from Charlotte to Wilmington in the project, as well as beginning construction in the northeast portion of the state. At the end of the quarter we had built 365 miles of conduit, representing approximately 27% of the planned construction efforts. In addition we finalized several IRU's during the quarter bringing our total at the end of the quarter 223 miles in the project. Final engineering efforts continue to finalize the construction plans and any required easements. NTIA formally approved a switch from an IRU to a build over a 57 miles stretch of network between Monroe and Huntersville. In addition, we began construction on placement of fiber along 15 miles of bridges in northeast North Carolina that will connect the Outer Banks back to the mainland. | 38 | 163 | 60 | 0 | 38 | 0 | 0 | 38 | This represents the number of miles of fiber actually placed. We would be able to account for more were it not for areas where we had to do reroutes to avoid future road projects that had to be taken to NTIA for consideration. We have constructed 367 miles of conduit, far ahead of the 169 miles projected. A slower start to construction by both MCNC and ERC is the primary driver for lower number to baseline. We expect to recover from this by the end of the year 2 reporting period. | Formal agreements with Zayo, BREMCO, Skyline, Pangea, and Greenlight were completed. These represented planned IRU acquisitions from the original proposal, as well as some approved during project by NTIA. We are ahead of baseline for this metric. | 60 miles of existing fiber are secured and ready to be lit when complementary fiber is completed in the project. 40 are from an existing route with Level3 owned by MCNC, and 20 from BTOP1 routes that are complete and will be used to tie the two networks together. | NA | We are below baseline of 264. Baseline contained acquired (Indefeasible Right to Use) miles in the calculation and thus all miles associated with the project. We will be below baseline going forward as the numbers reported will be actual construction numbers only. | NA | NA | We keep this number conservative to correspond with actual constructed miles deployed. During the implementation of the construction of conduit, hand holds average about 1 per mile, We will overcome this deficit in the next 1-2 reporting quarters. | 0 | 0 | 0 | There are no signed agreements as of yet, but there are many discussions occurring between our marketing partner ECC Technologies with carriers about access to the round 2 route. Due to planned completion dates of specific routes, as well as ongoing discussions by our marketing firm with folks interested in those routes, it is hard to accurately forecast when final agreements could be in place. However, given our current schedule and discussions to date, we anticipate being back on schedule to baseline by Q2Y3. | None available at this time. We anticipate a carrier to gain access in the route in the future, who will offer a fully array of telecom services. To our CAI consituents, we will be offering IP service up to 10Gbps, lambda (circuit) services, as well as dark fiber as requested. | Not applicable at this time. | 0 | 0 | 0 | 0 | We forecasted agreements too soon in our baseline based on completion cycle of the build. While it's hard to forecast when any agreements will be signed, we are encouraged by discussions our marketing firm is having with potential carriers. Due to planned completion dates of specific routes, as well as ongoing discussions by our marketing firm with folks interested in those routes, we anticipate being back on schedule to baseline by Q1Y3. | We forecasted agreements too soon in our baseline based on completion cycle of the build. While it's hard to forecast when any agreements will be signed, we are encouraged by discussions our marketing firm is having with potential carriers. Due to planned completion dates of specific routes, as well as ongoing discussions by our marketing firm with folks interested in those routes, we anticipate being back on schedule to baseline by Q1Y3. | We forecasted agreements too soon in our baseline based on completion cycle of the build. While it's hard to forecast when any agreements will be signed, we are encouraged by discussions our marketing firm is having with potential carriers. Due to planned completion dates of specific routes, as well as ongoing discussions by our marketing firm with folks interested in those routes, we anticipate being back on schedule to baseline by Q1Y3. | NA | 12 | 12 | 0 | 1 | We are right on baseline as we have finalized IRU's with providers for these locations (schools, libraries, and community colleges). | We are right on baseline as we have finalized IRU's with providers for these locations (schools, libraries, and community colleges). | NA | Service will be provisioned to these 12 locations at 1Gbps. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Our network, once deployed, will enable service offerings of 1Gbps to 100Gbps as required. The optronics we expect to deploy will have tremendous growth capability based on the road maps presented to us by the vendor finalists for equipment. | FALSE | NA | We anticipate finalizing our equipment vendor and begin ordering of equipment. We expect to fully complete all construction activities between Charlotte and Wilmington and make significant progress on Raleigh to Hamlet. We expect to push further in to the north east and north central portions of the state, as well as complete bridge attachment to approximately 15 miles of bridges in the northeast part of the state, as well as the first 6-8 hut deployments completed. Our goal is for 600 miles of fiber conduit to be placed that are part of the project. | MCNC | Permitting remains a challenge as we work with the railroads and DOT on the quantity of permits required. The process of having to work through reroutes with the NTIA while a necessary requirement, does create gaps in final designs that have to be approved before full builds can be completed. This slows deployment of fiber in some cases as reels have to be held out where the gaps occur. Timely review of the reroute requests will be helpful to staying on schedule. Winter weather is upon us and will likely slow us down in some regions, but our contractors are committed to working through it. The volume of materials we are ordering from our material vendor creates several "just in time" arrival of key components like conduit to the field, but thus far, we have not had any issues. | Timely review by the EA team on the required reroutes is of utmost importance. Beyond that, we feel our project is now in full construction mode and timely delivery of materials by our contractors will be critical. Thus far we have not been impacted by fiber delays and have a commitment from our vendor for manufacture of 125k feet per week of fiber, and 135k feet per week of conduit. The continuation of this just in time delivery will be vital to our project finishing this year from a construction point of view. Weather during the winter and spring months could slow us down, but would likely be offset by a typically dry summer. | TRUE
NT10BIX5570120 | 2012 | Q1 | Q1 - 2012 | Construction continued this quarter on the first priority segment from Charlotte to Wilmington in the project, as well as beginning full construction efforts in the northeast, north central, and central portions of the network. At the end of the quarter we had built 659 miles of conduit, representing approximately 49% of the overall planned construction efforts for conduit, and deployed 321 miles of fiber within that conduit. In addition we have now finalized Indefeasible Right to Use (IRU) contracts in the project totaling 272 miles. Permitting efforts with North Carolina Department of Transportation (NC DOT) and the railroads continued during the quarter on non priority segments and were nearly finished by end of the quarter. Construction on the bridges for approximately 15 miles in northeast North Carolina completed during the quarter. In addition, we selected a vendor, Cisco systems, for supplying all electronics that will operate the network when completed. | 321 | 272 | 60 | 0 | 321 | 0 | 0 | 839 | This represents the number of miles of fiber actually placed, which is below the baseline of 439 miles forecasted. We have constructed 659 miles of conduit, and because of this we are not concerned about being behind at this point. Where we had a gap in the conduit due to finalizing a permit, or incomplete construction, we opted not to deploy the fiber to make sure it was all locatable and in effect safeguarded. A slower start to construction by both MCNC and ERC is the primary driver for lower number to baseline. We expect to fully recover from this by the end of third quarter of 2012. | We are ahead of baseline on this metric. Formal agreements with Zayo, BREMCO, Skyline, Pangea, ERC and Greenlight have been completed to account for these totals. These represented planned IRU acquisitions from the original proposal, as well as some approved during project by NTIA. | 60 miles of existing fiber are secured and ready to be lit when complementary fiber is completed in the project. This fiber will be used to tie the BTOP2 construction together to the existing North Carolina Research and Education network. | N/A | We are below baseline of 561. Baseline contained acquired indefeasible right to use miles as well, in error, and thus we will be below baseline for this and all future reports. | N/A | N/A | Ahead of baseline due to number attributable to IRU's and the builds. Interconnect points occur at a minimum of roughly every one mile. | 0 | 3 | 0 | There are no signed agreements at this time; however, there are many discussions occurring between our marketing partner ECC Technologies and various carriers about access to the round 2 route. Feedback we are receiving is that as some regions of the network complete interest will pick up. We expect to be able to report some closed deals by end of Q2Y3. | None available at this time. We anticipate a carrier to gain access in the route in the future, who will offer a full array of telecom services. To our CAI constituents, we will be offering IP service up to 10Gbps, lambda (circuit) services, as well as dark fiber under lease and or IRU as requested. | Not applicable at this time. | 0 | 0 | 0 | 0 | We forecasted agreements too soon in our baseline based on completion cycle of the build. While it's hard to forecast when any agreements will be signed, we are encouraged by discussions our marketing firm is having with potential carriers. Due to planned completion dates of specific routes, as well as ongoing discussions by our marketing firm with folks interested in those routes, we anticipate being back on schedule to baseline by Q1Y3. | We forecasted agreements too soon in our baseline based on completion cycle of the build. While it's hard to forecast when any agreements will be signed, we are encouraged by discussions our marketing firm is having with potential carriers. Due to planned completion dates of specific routes, as well as ongoing discussions by our marketing firm with folks interested in those routes, we anticipate being back on schedule to baseline by Q1Y3. | We forecasted agreements too soon in our baseline based on completion cycle of the build. While it's hard to forecast when any agreements will be signed, we are encouraged by discussions our marketing firm is having with potential carriers. Due to planned completion dates of specific routes, as well as ongoing discussions by our marketing firm with folks interested in those routes, we anticipate being back on schedule to baseline by Q1Y3. | At the end of the quarter there were no broadband wholesale agreements established. MCNC will not be directly serving wholesale customers, but rather others that we expect to buy the fiber will be. | 30 | 30 | 0 | 1 | We are ahead of baseline due to being able to do the lateral construction work to these sites that were off the BTOP1 footprint while closing out that project. | We are ahead of baseline due to being able to do the lateral construction work to these sites that were off the BTOP1 footprint while closing out that project. | No CAI's were forecasted to have improved access, only new. | Service will be provisioned to these locations at 1Gbps. As needed and/or requested by the users, the capability can grow to 10Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Our network, once fully deployed, will enable service offerings of 1Gbps to 100Gbps as required. The optronics we expect to deploy will have tremendous growth capability based on the road maps presented to us by the vendor finalists for equipment. | FALSE | N/A | We anticipate finalizing our equipment vendor contract and beginning the process of ordering equipment. We expect to fully complete all construction activities between Charlotte and Wilmington and make significant progress on Raleigh to Hamlet. We expect to push further in to the north east and north central portions of the state, as well as complete bridge attachment to approximately 15 miles of bridges in the northeast part of the state, as well as the first 6-8 hut deployments completed. For the June 2012 reporting quarter, our expectation is for aggregate totals of at least 600 miles of fiber conduit to be placed, 400 miles of fiber deployed within that conduit, 290 miles of leased fiber, and 40 CAI's with fiber deployed to their facilities. At this point, we are unable to forecast that we will have any signed agreements with broadband wholesalers or last mile providers. | MCNC | Challenges in this quarter primarily centered around completing the permitting efforts as much as possible and managing the the three prime construction contractors across three distinct geographic regions, each with different characteristics. We have been able to stay ahead of delays in materials due to the aggressive contract we had with Commscope which has proven valuable as we have now received about 50% of all the fiber ordered for the project and have a commitment from them for all to arrive before end of the calendar year, 8 months before the project would have to finalize. Finalizing the contract for equipment procurement proved more challenging than one would reasonably expect and wasn't completed by the end of the March quarter as planned. | We feel our project is now in full construction mode and timely delivery of materials by our material vendor will continue to be critical to staying on pace. Thus far we have not been impacted by fiber delays and have a commitment from our vendor for manufacture of 125k feet per week of fiber, and 135k feet per week of conduit. Both of these commitments are essentially just in time commitments because they are not building too much material in advance of it being requested by our construction firms due to the volume of storage that would be required. The continuation of this just in time delivery will be vital to our project finishing this year from a construction point of view. Weather will continue to be a focal point for us as something that could slow us down. Keeping our contractors motivated to work at the pace we are requiring of them will be crucial as well as we are pushing each prime contractor to deploy nearly one mile a day on conduit placement during this middle portion of the build. | TRUE
NT10BIX5570120 | 2012 | Q2 | Q2 - 2012 | Construction efforts this quarter remained brisk and was the focal point for efforts within the project. At the end of the quarter in aggregate we had built 840 miles of conduit, representing approximately 63% of the designed plant to be built, and deployed 540 miles of fiber within that conduit. We have now also completed the acquisition of 303 miles of fiber. By the end of the quarter, all relevant permitting had been completed for the most part, with the exception of final execution on a US Forest Service permit to build in Graham County, and a few isolated railroads. We anticipate all of these closing next quarter. During the quarter we began placing orders on much of the equipment that will operate the new network, and toward the end of the quarter had begun receiving that equipment to stage for future deployment. By the end of the quarter we had placed telecommunication huts on 15 of the locations that had been identified within the project and were beginning final acceptance of those in anticipation of fiber being built up to them. | 540 | 303 | 60 | 0 | 540 | 0 | 0 | 1243 | This represents the number of miles of fiber actually placed, which is below the baseline of 780 miles forecasted. We have constructed 840 miles of conduit, and because of this we are not concerned about being behind at this point. A slower start to construction by both MCNC and ERC is the primary driver for lower number to baseline. We expect to fully recover from this by the end of fourth quarter of 2012. | We are ahead of baseline on this metric. Formal agreements with Zayo, BREMCO, Skyline, Pangea, ERC, Country Cable, French Broad Electric Membership Corporation and Greenlight have been completed to account for these totals. These represent planned IRU acquisitions from the original proposal, as well as some approved during project by NTIA. | 60 miles of existing fiber are secured and ready to be lit when complementary fiber is completed in the project. This fiber will be used to tie the BTOP2 construction together to the existing North Carolina Research and Education network. | N/A | We are below baseline of 993. Baseline contained acquired indefeasible right to use miles as well, in error, and thus we will be below baseline for this and all future reports. | N/A | N/A | Ahead of baseline due to number attributable to IRU's and the builds. Interconnect points occur at a minimum of roughly every one mile along the new construction. | 0 | 3 | 0 | There are no signed agreements at this time; however, there are many discussions occurring between our marketing partner ECC Technologies and various carriers about access to the round 2 route. Feedback we are receiving is that as some regions of the network complete interest will pick up. We expect to be able to report some closed deals by end of Q2Y3. | None available at this time. We anticipate a carrier to gain access in the route in the future, who will offer a full array of telecom services. To our CAI constituents, we will be offering IP service up to 10Gbps, lambda (circuit) services, as well as dark fiber under lease and or IRU as requested. | Not applicable at this time. | 0 | 0 | 0 | 0 | We forecasted agreements too soon in our baseline based on completion cycle of the build. While it's hard to forecast when any agreements will be signed, we are encouraged by discussions our marketing firm is having with potential carriers. Due to planned completion dates of specific routes, as well as ongoing discussions by our marketing firm with folks interested in those routes, we anticipate being back on schedule to baseline by Q1Y3. | We forecasted agreements too soon in our baseline based on completion cycle of the build. While it's hard to forecast when any agreements will be signed, we are encouraged by discussions our marketing firm is having with potential carriers. Due to planned completion dates of specific routes, as well as ongoing discussions by our marketing firm with folks interested in those routes, we anticipate being back on schedule to baseline by Q1Y3. | We forecasted agreements too soon in our baseline based on completion cycle of the build. While it's hard to forecast when any agreements will be signed, we are encouraged by discussions our marketing firm is having with potential carriers. Due to planned completion dates of specific routes, as well as ongoing discussions by our marketing firm with folks interested in those routes, we anticipate being back on schedule to baseline by Q1Y3. | We forecasted agreements too soon in our baseline based on completion cycle of the build. While it's hard to forecast when any agreements will be signed, we are encouraged by discussions our marketing firm is having with potential carriers. Due to planned completion dates of specific routes, as well as ongoing discussions by our marketing firm with folks interested in those routes, we anticipate being back on schedule to baseline by Q1Y3. | 52 | 52 | 0 | 1 | We are significantly ahead of baseline on this based on number of CAI's we have now built fiber to. At this point we have not turned service on to them due to timing of deployment in the core or their ability to sign a contract at this time, but the fiber has been deployed. | We are significantly ahead of baseline on this based on number of CAI's we have now built fiber to. At this point we have not turned service on to them due to timing of deployment in the core or their ability to sign a contract at this time, but the fiber has been deployed. | In error we forecasted in our baseline for improved service to CAI's. Given that the CAI's outlined in our proposal included all new builds for new services, these estimates in the baseline were wrong. This metric will be 0 for all future reports, and due to the continued forecasting error, a variance to baseline in all future reports. | Service will be provisioned to these locations at 1Gbps. As needed and/or requested by the users, the capability can grow to 10Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Our network, once fully deployed, will enable service offerings of 1Gbps to 100Gbps as required. The optronics we will deploy will have tremendous growth capability based on the road maps presented to us by the vendor of the equipment. Our willingness and ability to lease dark fiber to CAI's between their respective institutions in a confined geography we are hearing will be received well. | FALSE | N/A | We plan to continue full speed construction efforts and likely will complete a minimum of another 200 miles of conduit construction and 400 miles of fiber placement. Installation efforts of equipment will start on those backbone and CAI segments that will have had construction completed to them. We anticipate being at or ahead of baseline of 75 CAI's with new fiber. We are hopeful that we may close one fiber agreement with a carrier. At this point we will be looking to simply make major strides in final execution of all the construction related to the project leading in to the last quarter of the calendar year. | MCNC | Challenges during the quarter remain centered around ensuring that all material for the construction efforts reach the field in a timely fashion. In addition we are now starting to get in to the more challenging parts of the build, geography wise, and construction in those areas has proven to be slower as anticipated. We are still on pace to complete the project, however, and have no concerns about this based on when we began the construction effort and couldn't be more pleased with where we are. | At this time we do not foresee any challenges beyond keeping the crews focused and managing the build. We anticipate making a big push in to the fall on construction so as to be done by first quarter of calendar 2013. There are certain regions of the build where we need to make strong efforts on construction in advance of the winter months, primarily the northwestern portions of the state, and those efforts will become demanding. Beyond that, continued timely delivery of our materials by our outside plant vendor to our construction crews is the most important thing facing us. | TRUE
NT10BIX5570120 | 2012 | Q3 | Q3 - 2012 | Construction progress continued to be on pace with our expectations. At the end of the quarter we are able to call 1435 miles complete through conduit construction or IRU, representing approximately 84% of the project. Within the conduit installed of 1076 miles, we had placed 721 miles of fiber. We began deploying more equipment related to the backbone elements of the project and had some segments actually "lit", but not yet in a position to provide service as they are not tied back to the core network elements as of the end of the quarter. We anticipate that by end of the December 2012 reporting quarter we will have placed in to service the first several segments related to the project. We signed two agreements for IRU's related the fiber with Dukenet Communications and Broadplex. Ordering of most equipment has now completed as it relates to the backbone segments, and as CAI's are scheduled to come on line, the Customer Premise Equipment (CPE) required to make those connections is being ordered and deployed. Must more of this activity will occur in the upcoming 1-2 quarters. | 721 | 344 | 60 | 0 | 721 | 0 | 0 | 1458 | This represents the number of miles of fiber actually placed, which is below the baseline of 955 miles forecasted. We have constructed 1076 miles of conduit, which takes much more time than installation of the fiber, and because of this we are not concerned about being behind at this point. A slower start to construction by both MCNC and ERC is the primary driver for lower number to baseline. We expect to fully recover from this by the end of fourth quarter of 2012 or first quarter of 2013. | We are ahead of baseline on this metric. Formal agreements with Zayo, BREMCO, Skyline, Pangea, ERC, Country Cable, French Broad Electric Membership Corporation and Greenlight have been completed to account for these totals. These represent planned IRU acquisitions from the original proposal, as well as some approved during project by NTIA. The number is ahead of the number established for the entire project in baseline due to project changes approved for IRU's during the project by NTIA. | 60 miles of existing fiber are secured and ready to be lit when complementary fiber is completed in the project. This fiber will be used to tie the BTOP2 construction together to the existing North Carolina Research and Education network. | N/A | We are below baseline of 1205. Baseline contained acquired indefeasible right to use miles as well, in error, and thus we will be below baseline for this and all future reports. | N/A | N/A | Ahead of baseline of 1416 due to number attributable to IRU's and the builds. Interconnect points occur at a minimum of roughly every one mile along the new construction. | 2 | 3 | 80 | During the quarter we executed on an four fibers on an IRU of approximately 100 miles of new fiber with Dukenet as well as an IRU with Broadplex on 1 fiber over the entire footprint of the new build when complete, approximately 1435 miles. We're slightly behind to base line due to the timing of the completion of the routes, potential carriers timing to have capital funds, and negotiations taking longer than anticipated. | None available at this time from the newly signed contracts. We anticipate the carriers to offer a full array of telecom services. To our CAI constituents, we will be offering IP service up to 10Gbps, lambda (circuit) services, as well as dark fiber under lease and or IRU as requested. | During the quarter we signed a contract with Dukenet Communications out of Charlotte, NC to provide locate and maintenance services on the fiber when it is completed as a contractor. This contract signed represented a 9 month process to select a vendor to perform this critical task. They have also acquired a portion of the route to begin operations on and are continuing discussions on other parts to acquire and operate for commercial purposes. | 2 | 0 | 2 | 0 | We forecasted agreements too soon in our baseline based on completion cycle of the build. While at baseline, some other potential agreements have not signed due to timing related to completion of the routes and availability of capital resources on the part of the provider acquiring routes. | We forecasted agreements too soon in our baseline based on completion cycle of the build. While it's hard to forecast when any agreements will be signed, we are encouraged by discussions our marketing firm is having with potential carriers. Due to planned completion dates of specific routes, as well as ongoing discussions by our marketing firm with folks interested in those routes, we anticipate being back on schedule to baseline by Q1Y3. | We forecasted agreements too soon in our baseline based on completion cycle of the build. While at baseline, some other potential agreements have not signed due to timing related to completion of the routes and availability of capital resources on the part of the provider acquiring routes. | We forecasted agreements too soon in our baseline based on completion cycle of the build. While it's hard to forecast when any agreements will be signed, we are encouraged by discussions our marketing firm is having with potential carriers. Due to planned completion dates of specific routes, as well as ongoing discussions by our marketing firm with folks interested in those routes, we anticipate being back on schedule to baseline by Q1Y3. | 92 | 92 | 0 | 1 | We are ahead of baseline on this based on number of CAI's we have now built fiber to. At this point we have not turned service on to all of them due to timing of deployment in the core or their ability to sign a contract at this time, but the fiber has been deployed | We are ahead of baseline on this based on number of CAI's we have now built fiber to. At this point we have not turned service on to all of them due to timing of deployment in the core or their ability to sign a contract at this time, but the fiber has been deployed | In error we forecasted in our baseline for improved service to CAI's. Given that the CAI's outlined in our proposal included all new builds for new services, these estimates in the baseline were wrong. This metric will be 0 for all future reports, and due to the continued forecasting error, a variance to baseline in all future reports. | Service will be provisioned to these locations at 1Gbps. As needed and/or requested by the users, the capability can grow to 10Gbps. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Our network, once fully deployed, will enable service offerings of 1Gbps to 100Gbps as required. The optronics we will deploy will have tremendous growth capability based on the road maps presented to us by the vendor of the equipment. Our willingness and ability to lease dark fiber to CAI's between their respective institutions in a confined geography we are hearing will be received well. | TRUE | We have now implemented our mapping software package which allows us to more easily work with data related to the actual placement of the fiber route. This will enable us to understand how/where to meet other locations for build in the future and help with management of the actual route. | Assuming that there is not a great amount of bad weather, at the end of the next quarter we anticipate being within 100 miles of completion of the project for all conduit placement. Relative to fiber placement, we anticipate being with 250 miles of completion. Significant effort as it relates to turning on segments with equipment will begin to occur, but that effort will continue in to the reporting quarters of 2013. As it relates to CAI's we anticipate being approximately at baseline of 125. In addition we believe we could have as many as 4 agreements in total executed with providers along the completed fiber route. | MCNC | Challenges related to the schedule of materials has now largely abated. At this point, the challenges relate to keeping the contractors motivated more than 2 years in to the project. Because we have tight contracts signed with them, we are not concerned with them not completing the work, but it does require a lot of ongoing discussion with them as it relates to scheduling and project management. They are prone to complete easier portions of the build in advance of the more difficult aspects, and that is something that has to be monitored very closely. At this point, there is nothing more that the NTIA can do to help us we are in full deployment mode as we have been most of the last year. | Winter weather beginning to set in could have an impact on efforts in the north central portions of the network. 60 miles of construction remains in that mountainous area and if we have a lot of rain or snow, efforts will be slowed down. Beyond that, continuing to line up human capital for deployments with our internal staff and scheduling with the CAI's for installation will be a challenge, but not one that cannot be overcome. | TRUE
NT10BIX5570120 | 2012 | Q4 | Q4 - 2012 | Construction progress continued to be on pace with our expectations. At the end of the quarter we are able to call 1606 miles complete through conduit construction, IRU acquisition or existing MCNC controlled miles, representing approximately 94% of the project miles. Within the conduit installed we have placed 1010 miles of fiber. More equipment related to backbone segments had been deployed with the first working segments of the network between Charlotte and Whiteville, Raleigh and Henderson, and Sanford and Hamlet becoming active. As of this quarter fiber had been deployed to a total of 132 locations. No other IRU or leases were executed, but there were currently eight additional opportunities that are in various stages of discussion. | 1010 | 336 | 60 | 0 | 1010 | 0 | 0 | 1779 | This represents the number of miles of fiber actually placed, which is below the baseline of 1148 miles forecasted. We have constructed 1210 miles of conduit, which takes much more time than installation of the fiber, and because of this we are not concerned about being behind at this point on this metric. A slower start to construction by both MCNC and ERC is the primary driver for lower number to baseline. We expect to recover from this by the end of the first quarter of calendar 2013. | We are ahead of baseline on this metric, and always will be, due to IRU executions approved during the project instead of builds. Formal agreements with Zayo (26.5 miles), BREMCO (136 miles), Skyline (16 miles), Pangea (9 miles), ERC (42.5 miles), Country Cable (11 miles), French Broad Electric Membership Corporation (13 miles), Balsamwest (65 miles), Morris Broadband (9 miles) and Greenlight (8 miles) have been completed to account for these totals and represent all IRU's that will be completed. Note that this number is lower than the 344 reported in the previous quarter due to a double counting in error of one of the executed IRU's. The 336 represented here is the final number of network miles planned for lease in the project. | 60 miles of existing fiber are secured and ready to be lit when complementary fiber adjacent to them is completed in the project. This fiber will be used to tie the BTOP2 construction together to the existing North Carolina Research and Education network in operation today. | N/A | We are below baseline of 1503. Baseline contained acquired indefeasible right to use miles as well, in error, and thus we will be below baseline for this and all future reports. | N/A | N/A | Slightly ahead of baseline of 1765 due to number attributable to access points located on the IRU's executed and the builds completed to date. Interconnect points occur at a minimum of roughly every one mile along the new construction, more frequently within the metro areas. | 2 | 8 | 80 | No new agreements have been signed but there are 8 agreements being negotiated that have strong potential. We're slightly behind to base line due to the timing of the completion of the routes, potential carriers availability to have capital funds for purchases, and negotiations taking longer than anticipated. We are confident, however, that within the next two reporting quarters we will have other agreements finalized. Signed agreements to date are with Broadplex Communications and Dukenet Communications. | None available at this time from the newly signed contracts. We anticipate the carriers to offer a full array of telecom services. To our CAI constituents, we will be offering IP service up to 10Gbps, lambda (point to point circuit) services, as well as dark fiber under lease and or IRU as requested. | Dukenet Communications out of Charlotte, NC is providing locate and maintenance services on the fiber as it is completed by the contractors. They are not a sub recipient, but as reported in the last quarter have acquired fibers in a portion of the route and discussions for them to acquire in other areas continues. Contacts: Dukenet Communications Tony Cockerham, COO 704-382-5247 400 S. Tryon Street, Charlotte, NC 28202 MCNC Tommy Jacobson, COO 919-248-1178 3021 E. Cornwallis Road, Research Triangle Park, NC 27709 | 2 | 0 | 2 | 0 | We forecasted agreements too soon in our baseline based on completion cycle of the build. While meeting the projection forecasted in the baseline, some other potential agreements have not signed due to timing related to completion of the routes and availability of capital resources on the part of the provider acquiring routes. | No variance to baseline. | While meeting the projection forecasted in the baseline, some other potential agreements have not signed due to timing related to completion of the routes and availability of capital resources on the part of the provider acquiring routes. | We forecasted agreements too soon in our baseline based on completion cycle of the build. While it's hard to forecast when any agreements will be signed, we are encouraged by discussions our marketing firm is having with potential carriers. The carriers that we are speaking to, however, have a wide array of offerings in their current networks that we anticipate would be made available where they would buy fiber from us. | 132 | 132 | 0 | 7 | We are ahead of baseline on this based on number of CAI's we have now built fiber to. At this point we have not turned service on to all of them due to timing of deployment in the core or their ability to sign a contract at this time but fiber construction is complete. | We are ahead of baseline on this based on number of CAI's we have now built fiber to. At this point we have not turned service on to all of them due to timing of deployment in the core or their ability to sign a contract at this time but fiber construction is complete. | In error we forecasted in our baseline for improved service to CAI's. Given that the CAI's outlined in our proposal included all new builds for new services, these estimates in the baseline were wrong. This metric will be 0 for all future reports, and due to the continued forecasting error, a variance to baseline in all future reports. | Service will be provisioned to the CAI's at 1Gbps with varying contracted speeds up to 1Gbps. Currently the quantity at each tier based on deployment is: 10M:0 20M:2 50M:1 100M:11 250M:10 500M:8 1G:4 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Our network, once fully deployed, will enable service offerings of 1Gbps to 100Gbps as required. The optronics we will deploy will have tremendous growth capability based on the road maps presented to us by the vendor of the equipment. Our willingness and ability to lease dark fiber to CAI's between their respective institutions in a confined geography we are hearing will be received well. | FALSE | N/A | We believe by the end of the March 2013 reporting quarter we will be nearing completion of the build elements of the project. Relative to fiber placement, we anticipate being with 50 miles of completion and all conduit will be placed outside of the 14 mile segment in the Graham county area in the western part of the state which isn't planned for start until the end of February or first of March. Significant effort as it relates to turning on segments with equipment will occur in this quarter. As it relates to CAI's we anticipate being approximately at baseline of 179. In addition we believe we could have as many as 4 agreements in total executed with providers along the completed fiber route. | MCNC | Challenges now relate to a rainy start to the winter season in December as well as the expected holiday break for contractors slowing us down a bit in our construction efforts. Scheduling for site access at the CAI's is time consuming and doesn't always work well within schedules for the site and our project plan. This is a minor issue, but one that does take quite a bit of coordination. At this point we still do not have concerns about completing the project on time however as the pace of construction is slightly ahead of pace. | Our primary concerns in the project at this juncture relate to the winter weather in the areas left for construction. A snowy, wet winter will cause delays in one of the remaining regions of the project. Scheduling of equipment deployment is proving to be a challenge, but we intend to secure more part time staff resources as required to help in this effort. At this point, the focus is pushing through to completion of the project as much as we can in the March 2013 reporting quarter. | TRUE
NT10BIX5570120 | 2013 | Q1 | Q1 - 2013 | During the quarter, we closed in on finishing all construction efforts. At the end of the quarter we have completed a total of 1596 miles of fiber within the project through a combination of new build, IRU acquisition, or existing upgraded miles, representing approximately 94% of the project miles. Of the 1596 miles, 1200 miles represent new construction, 336 miles represent newly executed IRU's, and 60 miles represent upgraded miles. Deployment of backbone equipment continued between the Rocky Mount and Elizabeth City corridor, Raleigh and Henderson corridor, as well as the Henderson to Rockingham County corridor. During this quarter we deployed fiber by an additional 43 CAI's bringing our total for the project to 175. An additional 190 miles of new fiber was placed during the quarter, bringing the total to 1200 miles during the project. There are approximately 100 miles of new fiber left to be deployed. An additional IRU agreement was executed during the quarter for fibers on all newly constructed routes, bringing the total to three agreements executed on portions of the route. Conversations are ongoing with an additional seven companies regarding access to fibers. | 1200 | 336 | 60 | 0 | 1200 | 0 | 0 | 1964 | This represents the number of miles of fiber actually placed, which is below the baseline of 1340 miles forecasted. We have constructed 1337 miles of conduit which is right at baseline and which takes much more time than installation of the fiber. Because of this we are not concerned about being behind at this point on this metric and will finish fiber deployment no later than June. A slower start to construction by both MCNC and ERC and a rainy winter season is the primary driver for lower number to baseline. | We are ahead of baseline on this metric, and always will be, due to IRU executions approved during the project instead of builds. Formal agreements with Zayo (26.5 miles), BREMCO (136 miles), Skyline (16 miles), Pangea (9 miles), ERC (42.5 miles), Country Cable (11 miles), French Broad Electric Membership Corporation (13 miles), Balsamwest (65 miles), Morris Broadband (9 miles) and Greenlight (8 miles) have been completed to account for these totals and represent all IRU's that will be completed. | 60 miles of existing fiber are secured and ready to be lit when complementary fiber adjacent to them is completed in the project. This fiber will be used to tie the BTOP2 construction together to the existing North Carolina Research and Education network in operation today. | NA | We are below baseline of 1503. Baseline contained acquired indefeasible right to use miles as well, in error, and thus we will be below baseline for this and all future reports. | NA | NA | Slightly lower to baseline of 1990 as the baseline was set against the whole project being done at this time. | 4 | 7 | 63 | During the quarter we signed an agreement with RST Communications out of Shelby,NC for an Indefeasible Right to Use for fibers along the entire footprint of the project. ERC signed a lit service agreement with Lightleap, a wireless residential provider, during the quarter for 15M of service. Negotiations continued with 7 other carriers and enterprises for dark fiber as well as interest in the route remains high. We're slightly behind to base line due to the timing of the completion of the routes, potential carriers availability to have capital funds for purchases, and negotiations taking longer than anticipated. Additional signed agreements with Broadplex Communications and Dukenet Communications are in place as communicated in prior reports. | None available at this time from the newly signed contracts. We anticipate the carriers to offer a full array of telecom services. To our CAI constituents, we will be offering IP service up to 10Gbps, lambda (point to point circuit) services, as well as dark fiber under lease and or IRU as requested. | Dukenet Communications out of Charlotte, NC is providing locate and maintenance services on the fiber as it is completed by the contractors. They are not a sub recipient, but as reported in the last quarter have acquired fibers in a portion of the route and discussions for them to acquire in other areas continues. Contacts: Dukenet Communications Tony Cockerham, COO 704-382-5247 400 S. Tryon Street, Charlotte, NC 28202 MCNC Tommy Jacobson, COO 919-248-1178 3021 E. Cornwallis Road, Research Triangle Park, NC 27709 | 1 | 0 | 3 | 1 | In addition to the dark fiber agreements noted above, our subrecipient ERC signed a lit service agreement with Lightleap, who is a residential wireless provider, for service in the northwestern part of the state. | No variance to baseline | We are ahead of baseline of 2 on this metric. | The existing lit service ERC has provided noted above is for 15M of access. We anticipate RST beginning to provide 50M service to residential regions within the next 6-9 months as they start developing their business plan along certain portions of the route where they have obtained fibers. All carriers, based on the equipment they intend to deploy that they've revealed to us, will be in a position to provide service levels from 10M up to 10G. | 175 | 175 | 0 | 7 | We are slightly below baseline on this based on number of CAI's we have now built fiber to due to full completion of the construction efforts. | We are ahead of baseline on this based on number of CAI's we have now built fiber to. At this point we have not turned service on to all of them due to timing of deployment in the core or their ability to sign a contract at this time but fiber construction is complete. | In error we forecasted in our baseline for improved service to CAI's. Given that the CAI's outlined in our proposal included all new builds for new services, these estimates in the baseline were wrong. This metric will be 0 for all future reports, and due to the continued forecasting error, a variance to baseline in all future reports. | Service will be provisioned to the CAI's at 1Gbps with varying contracted speeds up to 1Gbps. Currently the quantity at each tier based on deployment is: 10M:1 20M:1 50M:2 100M:14 250M:10 500M:8 1G:6 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | Our network, once fully deployed, will enable service offerings of 1Gbps to 100Gbps as required. The optronics we will deploy will have tremendous growth capability based on the road maps presented to us by the vendor of the equipment. Our willingness and ability to lease dark fiber to CAI's between their respective institutions in a confined geography we are hearing will be received well. | FALSE | NA | We anticipate completing the project within the next quarter. While there could be some installations that carry over in to July for equipment of CPE at some locations, we expect those to be very few. We anticipate deploying the final 100 miles of fiber in the new construction, having fiber deployed by a total of 175 CAI's, and having signed a total of 6 new provider agreements for access (lit services or dark fiber). | MCNC | A winter that saw more rain than anticipated in the north central area of the state slowed construction an aggregate of approximately four weeks. With the wet rainy weather, time had to be given for areas to dry out to resume construction, and this caused delays that were beyond what we allowed for. As we have entered spring, this has given way to more ideal conditions and construction has picked up. At this point, the only remaining miles of conduit to be constructed to allow fiber placement are in the Graham County area for which NTIA is currently considering a waiver request from MCNC to grant use of fibers in this area to the controlling entity of an easement required for construction. Quick approval of this from NTIA in April will allow us to close out construction efforts in that area by end of May. | The biggest pending item is approval by NTIA to execute an agreement with Brookfield Hydorelectric that will allow us to grant them use of fibers over a short stretch in our Graham County build in exchange for an easement. We have provided all required information that we're aware of at this point to NTIA for consideration. | TRUE
NT10BIX5570120 | 2013 | Q2 | Q2 - 2013 | At the end of the quarter, we were nearly finished with all construction efforts. We have completed a total of 1690 miles of fiber within the project through a combination of new build, IRU acquisition, or existing upgraded miles, representing approximately 99% of the project miles. Of the 1690 miles, 1294 miles represents new construction, 336 miles represent newly executed IRU's, and 60 miles represent upgraded miles. Deployment of backbone equipment was completed on the fiber segments of Sparta to Henderson, Henderson to Elizabeth City, and the Outer Banks region. These deployments meant that all backbone related equipment ordered for the project was finished. An additional 94 miles of new fiber was placed during the quarter, bringing the total to 1294 miles during the project. There are approximately 7 more miles of new fiber left to be deployed. None of the newly deployed miles had any planned CAI's that they passed, leaving our total at 175 for the project. One IRU agreement was executed during the quarter for fibers on a small portion of the route with Conterra Communications, bringing the total to five agreements executed on portions of the route. Conversations are ongoing with an additional six companies regarding access to fibers | 1294 | 336 | 60 | 0 | 1294 | 0 | 0 | 2028 | This represents the number of miles of fiber actually placed due to new construction. We are below the baseline of 1340 established at the start of the project due to miles being moved to execution of IRU's as documented to NTIA and subsequently approved by NTIA as opposed to new construction. | We are ahead of baseline on this metric, and always will be, due to IRU executions approved during the project instead of builds. Formal agreements with Zayo (26.5 miles), BREMCO (136 miles), Skyline (16 miles), Pangea (9 miles), ERC (42.5 miles), Country Cable (11 miles), French Broad Electric Membership Corporation (13 miles), Balsamwest (65 miles), Morris Broadband (9 miles) and Greenlight (8 miles) have been completed to account for these totals and represent all IRU's that will be completed. | We are below the baseline projection of 106 here due to counting in error the miles associated with the ERC IRU acquisition noted above in this category during baseline. The actual miles turned out to be 42.5 as noted above, and were secured with an IRU during the project and were not existing to MCNC at the time baseline was created. | N/A | We are below baseline of 1694. Baseline contained acquired indefeasible right to use miles as well, in error, and thus we will be below baseline for this and all future reports. | N/A | N/A | Slightly higher to baseline due to approved reroutes during the project. | 5 | 6 | 63 | Signed agreements completed to date are as follows: 1. Broadplex (dark fiber) 2. Dukenet Communications (dark fiber) 3. RST Communications (dark fiber) 4. Lightleap (lit service) via ERC subrecipient 5. Conterra (dark fiber) | None available at this time from the newly signed contracts. We anticipate the carriers to offer a full array of telecom services. To our CAI constituents, we will be offering IP service up to 10Gbps, 10Gbps lambda (point to point circuit) services, as well as dark fiber under lease and or IRU as requested. | Dukenet Communications out of Charlotte, NC is providing locate and maintenance services on the fiber as it is completed by the contractors. They are not a sub recipient, but as reported in the last quarter have acquired fibers in a portion of the route and discussions for them to acquire in other areas continues. Contacts: Dukenet Communications Tony Cockerham, COO 704-382-5247 400 S. Tryon Street, Charlotte, NC 28202 MCNC Tommy Jacobson, COO 919-248-1178 3021 E. Cornwallis Road, Research Triangle Park, NC 27709 | 1 | 0 | 4 | 1 | In our baseline we in error put new fiber purchases in this section. Thus our baseline was too aggressive as our market has always been for dark fiber as MCNC is not a wholesale carrier to other communication companies. | No variance to baseline | We are ahead of baseline of 2 on this metric. | The existing lit service noted above is for 15M of access. We anticipate RST beginning to provide 50M service to residential regions within the next 6-9 months as they start developing their business plan along certain portions of the route where they have obtained fibers. All carriers, based on the equipment they intend to deploy that they've revealed to us, will be in a position to provide service levels from 10M up to 10G. | 175 | 175 | 0 | 7 | Our baseline was wrong in that it contained projections for services subscribed, and not locations served. For example we felt like some CAI's would subscribe to both internet and transport services. These were in our forecasts. Our number of 175 here represents those locations for which fiber was approved for construction to. | Our baseline was wrong due to our interpretation of what improved versus new service meant, and a combination of the two was used in development of our baseline. As a result of the approved construction plan, the number of 175 shown now represents those locations for which fiber was built to. | In error we forecasted in our baseline for improved service to CAI's. Given that the CAI's outlined in our proposal included all new builds for new services, these estimates in the baseline were wrong. This metric will be 0 for all future reports, and due to the continued forecasting error, a variance to baseline in all future reports. | Service will be provisioned to the CAI's at 1Gbps with varying contracted speeds up to 1Gbps. Currently the quantity at each tier based on deployment is: 10M:3 20M:2 30M:1 50M:4 100M:22 150M:1 250M:16 275M:2 500M:9 1G:9 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | Our network enables service offerings of 1Gbps to 100Gbps as required. The optronics deployed have tremendous growth capability based on the road maps presented to us by the vendor of the equipment. Our willingness and ability to lease dark fiber to CAI's between their respective institutions in a confined geography we are hearing will be received well. | FALSE | N/A | We anticipate completing the project by end of July. At this point there are no challenges anticipated that would keep that from happening. During the next quarter, MCNC will finish all remaining construction efforts, deploying the final seven miles of fiber associated with this project, which will bring total miles constructed to 1301. There will be no additional CAIs to report during the next quarter. This total will remain at 175. MCNC is currently communicating with six additional broadband wholesaler/last mile providers regarding fiber access. While we would hope that all agreements would be signed, given the complexity and individuality of each agreement and the legal processes involved, it could take more than three months to get signed agreements from some of these. | MCNC | There were no unexpected challenges experienced during the quarter to keep us in line to completing the project by the required end of July 2013 deadline. | Nothing anticipated that will keep us from completing the project. | TRUE
NT10BIX5570120 | 2013 | Q3 | Q3 - 2013 | At the end of the quarter, we had completed all efforts on the project. We have completed a total of 1697 miles of fiber within the project through a combination of new build, IRU acquisition, or existing upgraded miles. Of the 1697 miles, 1301 miles are new construction, 336 miles are newly executed IRU's, and 60 miles are upgraded miles. Deployment of backbone and CPE equipment was completed during the quarter. Total CAI's with newly placed fiber totaled 175 for the project. The project is now complete as awarded and adjusted during the project life. | 1301 | 336 | 60 | 0 | 1301 | 0 | 0 | 2035 | This represents the number of miles of fiber actually placed due to new construction. We are below the baseline of 1340 established at the start of the project due to miles being moved to execution of IRU's as documented to NTIA and subsequently approved by NTIA as opposed to new construction. | We are ahead of baseline on this metric, and always will be, due to IRU executions approved during the project instead of builds. Formal agreements with Zayo (26.5 miles), BREMCO (136 miles), Skyline (16 miles), Pangea (9 miles), ERC (42.5 miles), Country Cable (11 miles), French Broad Electric Membership Corporation (13 miles), Balsamwest (65 miles), Morris Broadband (9 miles) and Greenlight (8 miles) have been completed to account for these totals and represent all IRU's that will be completed. | We are below the baseline projection of 106 here due to counting in error the miles associated with the ERC IRU acquisition noted above in this category during baseline. The actual miles turned out to be 42.5 as noted above, and were secured with an IRU during the project and were not existing to MCNC at the time baseline was created | N/A | We are below baseline of 1694. Baseline contained acquired indefeasible right to use miles as well, in error, and thus we would always be below baseline. | N/A | N/A | Slightly higher to baseline due to approved reroutes during the project creating new points with new constructed routes. | 7 | 5 | 63 | Signed agreements completed to date are as follows: 1. Broadplex (dark fiber) 2. Dukenet Communications (dark fiber) 3. RST Communications (dark fiber) 4. Lightleap (lit service) via ERC subrecipient 5. Conterra (dark fiber) 6. Earthlink (dark fiber) 7. MOX Networks (dark fiber) | None available at this time from the newly signed contracts. We anticipate the carriers to offer a full array of telecom services. To our CAI constituents, we will be offering IP and MPLS based transport services up to 10Gbps, 10Gbps lambda (point to point circuit) services, as well as dark fiber under lease and or IRU as requested. | Dukenet Communications out of Charlotte, NC is providing locate and maintenance services on the fiber as it is completed by the contractors. They are not a sub recipient, but as reported in the last quarter have acquired fibers in a portion of the route and discussions for them to acquire in other areas continues. Contacts: Dukenet Communications Tony Cockerham, COO 704-382-5247 400 S. Tryon Street, Charlotte, NC 28202 MCNC Tommy Jacobson, COO 919-248-1178 3021 E. Cornwallis Road, Research Triangle Park, NC 27709 | 1 | 0 | 6 | 1 | In our baseline we in error put new fiber purchases in this section. Thus our baseline of 5 was too aggressive as our market has always been for dark fiber as MCNC is not a wholesale carrier to other communication companies. | No variance to baseline | We are ahead of our baseline of 2 signed dark fiber agreements. | The existing lit service noted above is for 15M of access. We anticipate RST beginning to provide 50M service to residential regions within the next 6-9 months as they start developing their business plan along certain portions of the route where they have obtained fibers. All carriers, based on the equipment they intend to deploy that they've revealed to us, will be in a position to provide service levels from 10M up to 10G. | 175 | 175 | 0 | 13 | Our baseline was wrong in that it contained projections for services subscribed, and not locations served. For example we felt like some CAI's would subscribe to both internet and transport services. These were in our forecasts. Our number of 175 here represents those locations for which fiber was approved for construction to. | Our baseline was wrong due to our interpretation of what improved versus new service meant, and a combination of the two was used in development of our baseline. As a result of the approved construction plan, the number of 175 shown now represents those locations for which fiber was built to. | In error we forecasted in our baseline for improved service to CAI's. Given that the CAI's outlined in our proposal included all new builds for new services, these estimates in the baseline were wrong. This metric will be 0 for all future reports, and due to the continued forecasting error, a variance to baseline in all future reports. | Service will be provisioned to the CAI's at 1Gbps with varying contracted speeds up to 1Gbps. Currently the quantity at each tier based on deployment is: 10M:6 20M:4 30M:1 50M:6 100M:52 150M:1 250M:30 275M:2 475M:1 500M:13 1G:11 2G:2 3G:1 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N.A | N/A | N/A | Our network enables service offerings of 1Gbps to 100Gbps as required. The optronics deployed have tremendous growth capability based on the road maps presented to us by the vendor of the equipment. Our willingness and ability to lease dark fiber to CAI's between their respective institutions in a confined geography we are hearing will be received well. | FALSE | N/A | N/A as the project is complete. | MCNC | There were no unexpected challenges experienced during the quarter that kept us from completing the project by the required deadline. | N/A as the project is complete. | TRUE
NT10BIX5570122 | 2010 | Q4 | Q4 - 2010 | 1. Project engineering teams have been procured and are under contract. 2. Accounting, Disbursement, and Reporting processes have been established. 3. Compliance contractor has been procured and is under contract. 4. Interim business plan has been completed. 5. Grant file has been established. 6. Preliminary drawdown plan has been established (for Q1, 2011). 7. Master Project Plan development has commenced and continues to be updated on an ongoing basis. 8. Network design is 30% complete, with preliminary link engineering underway. 9. Established and implemented procedures for core site evaluations. 10. Development of best-value criteria for tower sites has commenced. 11. Site audits and assessment of existing vertical assets have started for the two service areas. 12. Assessment of Point of Presence locations for the two service areas has started. 13. Indefeasible Right of Use contract negotiations with Level 3 for upstream access have commenced. 14. Development of Community Outreach plan/Public Relations strategy has commenced. 15. Validation of in-kind contributions has commenced. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | On target for this reporting period. | On target for this reporting period. IRU negotiations with Level 3 for upstream access have commenced. | N/A. Upgrading of network facilities performed by the upstream partner. | N/A. Leased IRU capacity does not differentiate between new or existing network facilities. We assume most or all of the fiber is existing and the equipment is new. | On target for this reporting period. | On target for this reporting period. | N/A. We are not building any towers. | On target for this reporting period. | 0 | 0 | 0 | None yet. We are developing products and pricing with pre-deployment service level agreements. We are also developing dialogue with carriers, re-sellers and anchor institutions, with the expectation of signing several after pricing and service level agreements are finalized. While we have not yet signed agreements with other providers as yet, the pricing and ability to describe the value proposition is imminent, and we anticipate the signing of several agreements over the next subsequent quarters. | Internet and Transport Services. Services will be offered in standard, premium (protected), and enterprise packages. We will offer term and volume discounts as well. A list of services matrix is being developed under a rate/services study for the development of our initial pricing and services model. A preliminary draft copy of our Proposed Service Offerings Pricing matrix is attached. | As deployment of the project nears completion, the Authority will advertise in an open and competitive procurement for contract operations services. These services will be performed under the management of Government Services Group, the General Manager of the Authority. | 0 | 0 | 0 | 0 | Unless it is a new provider, or just entering the market, we will assume that all providers are receiving improved access. | We are in discussion with several providers. Agreements are pending finalization of product and service plans, which are in development. | We will not be providing access to dark fiber, as we do not have that access. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1Gbps will be available, but we conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | 0 | 0 | 0 | Our plan outlines the potential to provide service (indirectly, through last mile providers that have purchased wholesale access through our network) to 196 anchor institutions by project closeout. The network will also be available as a direct access provider of â€œlast resortâ€ for community anchor institutions. | We will work with our Local Access providers to provide us with this information. | We will assume that if service is provided through our network, that all subscribers that have some kind of service will be receiving improved service. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1Gbps will be available, but we conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | We will work with our Local Access providers to collect and report on this data. | We will work with our Local Access providers to collect and report on this data. | We will work with our Local Access providers to collect and report on this data. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1Gbps will be available, but we conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | We will work with our Local Access providers to collect and report on this data. | We will work with our Local Access providers to collect and report on this data. | We will work with our Local Access providers to collect and report on this data. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1Gbps will be available, but we conservatively estimated that we will only add customers at that level of service beyond year 3. | No special offerings at this time. Rate and services study to evaluate future additional services/needs/offerings is underway. Internal analysis is also underway. We are in the process of securing very substantial capacity to allow third party providers to provide a wide array of services across our network. The full range of offerings will be determined by the marketplace, but the network has been designed to efficiently accommodate all types of traffic. | FALSE | N/A | 1. Procure Auditing services and execute contract. 2. Complete development of offered services and rate analysis. 3. Complete commercial tower license agreement drafts. 4. Complete In-Kind assets license agreement drafts. 5. Obtain E-rate registration Service Provider Identification Number (SPIN). 6. Begin Internet Protocol address planning. 7. Update engineering performance standards. Continue development of best-value criteria for tower sites. 8. Evaluate network design in reference to structural needs of towers, license rates, and cost of structural make-ready. 9. Continue upstream Indefeasible Right of Use development. Complete assessment of Point of Presence locations. 10. Develop network and data center equipment RFP's. 11. Develop and implement safety policies and procedures. 12. Community outreach meetings are planned for next quarter. | Florida Rural Broadband Alliance, LLC | We will ask the Grants Office to review a draft template of our master tower lease agreement in order to obtain verification that the contract language in the license agreement is in compliance with grant requirements. | We will ask the Grants Office to review a draft template of our master tower license agreement in order to obtain verification that the contract language in the license agreement is in compliance with grant requirements. We are also in the process of determining Davis-Bacon wage rate decisions for equipment installation laborers, and to that end we submitted an Award Action Request to the Grants Office (for the NFBA project) that included a Request for Authorization of Additional Classification and Rate (SF 1444) for proposed classification titles. We are also conducting our own research on this matter in order to move forward with the development of the Equipment Installation and Pathing RFP in an effort to avoid any delay to the release of this RFP and to subsequent equipment installation activities. In addition, we are checking for previous/duplicate federal funding for targeted in-kind assets, per the Grants Officeâ€™s request. Discovery of previous or duplicate federal funding for in-kind assets may or may not impact planned project progress, depending on the interpretation of this particular requirement. We are seeking to utilize only a limited amount of space on any given in-kind asset to mount microwave antennas and equipment; we are not seeking to utilize any in-kind asset in its entirety. | TRUE
NT10BIX5570122 | 2011 | Q1 | Q1 - 2011 | 1. Indefeasible Right of Use business terms and service level agreement terms were finalized this past quarter. 2. Upstream provisioning and engineering have commenced, and proposed Point-of-Presence sites are being evaluated for upstream vertical connectivity in the South Central and Northwest network regions. 3. A service agreement with the American Registry for Internet Numbers was executed for Internet Protocol Version 4 numbers and bandwidth. 4. Preliminary system design templates are complete for the South Central and Northwest network regions. 5. Initial site audit packages have been submitted for selected tower sites in the South Central and Northwest network regions. 6. Pre-structural pathing analysis and preliminary link engineering have been submitted for South Central network region. 7. Preliminary network engineering for datacenter infrastructure has been submitted for the South Central network region. 8. Scopes of work have been developed for remaining pre-deployment engineering tasks, including packet-switching design and architecture for Open Systems Interconnection model network layers and elements. 9. Commercial tower master license agreement business terms and conditions have been finalized. 10. In-kind vertical asset master license agreement business terms and conditions have also been finalized. The project is behind our Baseline Plan projections for this past quarter for the reasons noted in Section 1, Items #2 and #3 below. The Engineer elected to see | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | On target for this reporting period. | On target for this reporting period. | N/A. Upgrade of network facilities performed by our upstream partner. | N/A | On target for this reporting period. | On target for this reporting period. | N/A | On target for this reporting period. | 0 | 0 | 0 | None yet. We are developing our initial service catalog as products, pricing, and pre-deployment service level agreements continue to be finalized and business support system requirements continue to be defined. We have ongoing dialogue with carriers, re-sellers, and community anchor institutions, with the expectation of signing several after pricing and service level agreements are finalized. | Internet and transport services. Services will be offered in standard, premium (protected), and enterprise packages. We will offer term and volume discounts as well. A draft copy of our Wholesale Standard Ethernet Access Pricing matrix is attached. Services will be offered in standard, premium (protected), and enterprise packages. We will offer term and volume discounts as well. A draft copy of our Wholesale Standard Ethernet Access Pricing matrix is attached. | As project deployment nears completion, the Florida Rural Broadband Alliance (FRBA) will advertise in an open and competitive procurement for contract operations services. These services will be performed under the management of Government Services Group, the General Manager for FRBA. | 0 | 0 | 0 | 0 | Unless it is a new provider, or just entering the market, we will assume that all providers are receiving improved access. | We are in discussion with several providers. Agreements are pending finalization of product and service plans. | We will not be providing access to dark fiber, as we do not have that access. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | 0 | 0 | 0 | Our plan outlines service to 196 anchor institutions by project closeout. | N/A | We will assume that if service is provided through our network, that all subscribers that have some type of service will receive improved service. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | No special offerings at this time. Service catalog products and pricing are being developed along with business support system requirements. We are in the process of securing very substantial capacity to allow third party providers to provide a wide array of services across our network. The full range of offerings will be determined by the marketplace, but the network has been designed to efficiently accommodate all types of traffic. | FALSE | N/A | 1. Indefeasible Right of Use agreement for upstream capacity finalized and executed. 2. Upstream provisioning and engineering developed further, with proposed Point-of-Presence and datacenter locations identified for upstream vertical connectivity in both the South Central and the Northwest network regions. 3. Pre-structural pathing analysis and link engineering complete for the Northwest network region. 4. Preliminary network engineering for datacenter infrastructure complete for the Northwest network region. 5. Continued analysis of the preliminary network design to identify alternative tower sites and to reduce long network links. 6. Execute engineering work authorization for pre-deployment network design and architecture for Open Systems Interconnection model network layers and elements. 7. Develop performance specifications for equipment cabinets, multi-service access platforms (switches), datacenter equipment, tower transmission cables and attachment hardware, and licensed microwave radios and antennas. 8. Preliminary site acquisition activities, such as the determination of permitting requirements and the engagement of local electrical utility companies, are planned to begin next quarter for both the South Central and the Northwest network regions. | Florida Rural Broadband Alliance, LLC | The following is a summary explanation of the reasons for the variance between Baseline Plan projections and milestone completion percentages experienced this past quarter: In previous Performance Progress Reports, milestone completion percentages were based on pending expenditures as determined by work completed instead of actual budget expenditure. Our intent with this approach was to reflect project progress more accurately, in consideration of the time required to review, approve, and process vendor payment requests. Most of our vendor payment requests are based upon defined deliverables, and payment is not processed until a completed deliverable is received, reviewed, and approved. The payment approval process also requires signatures from the General Manager, the Compliance Office, and the Florida Rural Broadband Alliance's Authorized Organizational Representative. With actual budget expenditure as a progress indicator, work performed over the course of a deliverable's life cycle would not count toward project progress until all tasks associated with the deliverable were complete, all deliverable documents were subsequently reviewed and approved, and then upon approval, payment for the deliverable was processed. However, per the Additional Guidance instructions, from this point forward we will report milestone completion percentages based on budget expenditures, incorporating both Federal funds and non-Federal share in-kind contributions where applicable in the | Please see Section 1, Item #3 for further details regarding the reasons for variance from the Baseline Plan and our plans for catching up to the Baseline Plan, as we anticipate these issues to carry forward into the next quarter. We are in the process of resubmitting Davis-Bacon wage determination requests as an Award Action Request in Grants Online for Tower Technician and Radio Frequency Technician job classifications in all counties in both the Northwest and South Central core network regions, with one county listed per SF-1444 form per the Grant Office's instructions. | TRUE
NT10BIX5570122 | 2011 | Q2 | Q2 - 2011 | Florida Rural Broadband Alliance, LLC (â€œFRBAâ€) recently restructured the administration of its Limited Liability Company to allow for more hands on management of the grant administration, more visibility into the day-to-day activities and streamlined decision making regarding the grant implementation. This restructuring allows for the Members of FRBA to take a more active role in the daily management and oversight of its business and the grant-funded project. FRBA also terminated its relationship with Government Services Group as the General Manager of the program; again to provide better visibility into the grant management activities and implementation. In light of the reorganization of the Limited Liability Company and the termination of the General Manager, the Authority of Record for the grant administration has changed from Government Services Group to the grant owner, FRBA. We engaged with Gigabit Squared to provide due diligence of the program management to date and to develop a restructuring plan for the project. The due diligence process included active collaboration between the FRBA, Rapid Systems, CityNet, Gigabit Squared and In-Kind Match contributors. The restructuring plan allows for dramatic project/program acceleration: â€¢ Anticipated network build completion to substantially complete within 12 months (August 2012) â€¢ 1st Ring in South-Central Network â€˜Go-Liveâ€™ during Q2/Q3 2011 (as opposed to month 36 under Baseline Plan) â€¢ Community Ancho | 197 | 505 | 0 | 0 | 0 | 22 | 0 | 3 | Completion of Hardee County on June 1, 2011 brought on 197 miles of middle mile wireless access. | Level 3 fiber back haul. | N/A | N/A | N/A | Completion of Hardee County on June 1, 2011 brought on 197 miles of middle mile wireless access. | Completion of Hardee County on June 1, 2011 brought on 197 miles of middle mile wireless access. | Level 3 Colocation sites are in development and will become active next quarter. | 3 | 2 | 20 | â€¢ Rapid Systems has agreement with the Hardee County Broadband Project. â€¢ Rapid Systems has a wholesale agreement with Daystar for Last Mile Services within the FRBA project â€¢ Rapid Systems has a wholesale / Last Mile agreement with Knology for Voice over Internet Protocol services within the FRBA project and is currently deploying Hosted and Residential Voice over Internet Protocol | FRBA will provide Ethernet Wireless Transport and internet wholesale services as the Middle Mile Network. Additionally, FRBA will provide services to Community Anchor Institutions. Rapid Systems is providing Broadband Service to anchor facilities using WiMAX and other Licensed and unlicensed products. Rapid Systems has also recently completed integration and testing with Knology for Voice over Internet Protocol service. We currently are testing one community anchor on hosted Voice over Internet Protocol platform and 10 residential customers. Rapid Systems and Knology are currently working on call plans to Mexico to assist the migrant population with enhanced communications. | FRBA has designated two partners that are designated as sub recipients: 1) Rapid Systems will operate the South-Central Regional Network as a sub recipient. www.rapidsys.com a. 1211 N Westshore Blvd Tampa, FL 33607 813-232-4887 UPDATE Subscriber and Residential to include the 1400 other connections now being served by Rapid Systems b. Area Served â€“ Floridaâ€™s Heartland Counties Served â€“ Hardee, Desoto, Highlands, Okeechobee, Glades, and Hendry. Also, the community of Immokalee 2) CityNet will operate the North Western Regional Network as a sub recipient of the grant. a. CityNet LLC/Xiocom 17740 Ashley Drive, Suite 109 Panama City Beach, FL 32413 Telephone: (850)785-1969 b. Area Served â€“ Opportunity Florida Counties Served â€“ Holmes, Washington, Jackson, Gadsden, Calhoun, Liberty, Gulf, Franklin | 0 | 3 | 0 | 1 | Unless it is a new provider, or just entering the market, we will assume that all providers are receiving improved access. | We are in discussion with several providers. Agreements are pending finalization of product and service plans. | We will not be providing access to dark fiber, as we do not have that access. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 33 | 0 | 33 | 0 | Our plan outlines service to 196 anchor institutions by project closeout. | N/A | We will assume that if service is provided through our network, that all subscribers that have some type of service will receive improved service. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | Rapid Systems agreement is to provide a discount on services into Hardee County for three years. We are also in the process of securing very substantial capacity to allow third party providers to provide a wide array of services across our network. The full range of offerings will be determined by the marketplace, but the network has been designed to efficiently accommodate all types of traffic. | FALSE |  | The first tasks associated with the restructuring of the grant administration will be a re-look and refresh of the project budget, plan and schedule, working closely with NTIA PMO for an anticipated budget/design and baseline plan/timeline deviations. We will recast the project timeline based upon a 12-month design/build strategy, leveraging parallel development paths where possible and feasible. The accelerated schedule will allow for accelerated customer acquisition, and we will incorporate marketing activities and customer outreach to coincide with the accelerated network construction. We will identify, hire and contract with an experience locally-based Project Manager to manage the local relationships and contracts with the Community Anchor Institutions. We will begin construction on the North Western Region of the network and will continue construction activities on the South-Central Regionâ€™s network. To provide the documentation required to value and validate the assets provided as an in-kind contribution, a detailed appraisal of the assets will be conducted, including a list of all in-kind assets, valuation methodology and appraisal of said assets. Negotiate and execute asset transfer or capital lease for all assets, remembering that term of contract may exceed grant term. Objective 1: Business Model Fundamentals: Investigation of the core products, revenue streams, operational model and â€˜go-to-marketâ€™ strategy that will form the basis of a formal busine | Florida Rural Broadband Alliance, LLC | As mention previously the Prime Recipient FRBA elected to restructure the administration operations and controls to provide a streamlined administrative and program office, program transparency and assign accountability to the appropriate parties. The restructured administrative process is intended to accelerate the completion of the design process and initiation of the purchasing and construction phases of the project. The original submission defined the two major design/build/operating firms as partners when in the proper context they are sub recipients and the major contributors of the match associated with the project. The FRBA program staff will work with the PMO office and submit the appropriate Award Action Requests to appropriately reflect the intended relationship of the partners. The primary challenge for this project is simply to accelerate the construction activities to meet the milestones and key indicators of the Baseline Plan. We have the right team in place to meet these milestones and do not foresee any additional assistance from NTIA/BTOP. We do anticipate a series of Award Action Requests that will be submitted based upon potential changes resulting from the restructuring of the grant administration. FRBA will work closely with NTIA PMO to determine the actions and sequencing of the Award Action Requests that may be required to reflect the design, budget and schedule acceleration. | We will be submitting a Award Action Requests for a change in Authorized Organizational Representatives (AORs), revised schedule and budget. We appreciate the NTIAs PMOs efforts in addressing this matters. | TRUE
NT10BIX5570122 | 2011 | Q3 | Q3 - 2011 | The Florida Rural Broadband Alliance (FRBA) team submitted and has been executing on a 30-60-90 day transition plan to restructure the FRBA governance, project and deployment plans. During this period, FRBA: â€¢ Formalized the new roles and responsibilities of the organization â€¢ Committed to a Letter of Intent (LOI) with Rapid Systems to complete a subrecipient agreement for engineering and deployment support for the FRBA broadband network both in the South Central and in the Northern service areas of FRBA â€¢ Revised the project plan and budget â€¢ Solidified the match and submitted updated reconciliation report â€¢ Began development of a revised business and sustainability plan â€¢ Completed the engineering and equipment specifications for the FRBA broadband network â€¢ Continued to move the project forward in parallel with restructuring the organizational approach and schedule for deployment of the FRBA network FRBA has been making great strides and in fact actually accelerated a number of activities by creating a parallel process and more transparency within the project. As a result the team has completed the restructuring of the organizational administration, project budget, scheduled and aligned the projects and resources to move the project back to its original baseline over the next two quarters. In addition the project team recognized several opportunities to accelerate the deployment and have developed a project structure and measures that will help FRBA substa | 230 | 505 | 0 | 0 | 0 | 0 | 0 | 4 | The completion of Hardee County and extension of services into adjacent communities has resulted in deployment of 230 miles of wireless network. | The Level 3 fiber infrastructure connecting FRBA North and South to the Level 3 upstream network has been deployed and activated. | N/A | N/A | N/A | No new wireless links have been added this quarter. | Hardee County is complete and operation and services have been extended into Desoto and adjacent counties. | Hardee County is complete and operation and services have been extended into Desoto and adjacent counties. One of four Level 3 Points-of-Presence was activated that connects the FRBA/Hardee County to the Level 3 backbone. This is the first of four major nodal connections that will bring much needed upstream access to the rural communities of Floridan and services have been extended into Desoto and adjacent counties. One of four Level 3 Points-of-Presence was activated that connects the FRBA/Hardee County to the Level 3 backbone. This is the first of four major nodal connections that will bring much needed upstream access to the rural communities of Florida. | 3 | 2 | 20 | â€¢ Rapid Systems has agreement with the Hardee County Broadband Project. â€¢ Rapid Systems has a wholesale agreement with Daystar for Last Mile Services within the FRBA project â€¢ Rapid Systems has a wholesale / Last Mile agreement with Knology for Voice over Internet Protocol services within the FRBA project and is currently deploying Hosted and Residential Voice over Internet Protocol | FRBA will provide Ethernet Wireless Transport and internet wholesale services as the Middle Mile Network. Additionally, FRBA will provide services to Community Anchor Institutions. Rapid Systems is providing Broadband Service to anchor facilities using WiMAX and other Licensed and unlicensed products. Rapid Systems has also recently completed integration and testing with Knology for Voice over Internet Protocol service. We currently are testing one community anchor on hosted Voice over Internet Protocol platform and 10 residential customers. Rapid Systems and Knology are currently working on call plans to Mexico to assist the migrant population with enhanced communicationss Transport and internet wholesale services as the Middle Mile Network. Additionally, FRBA will provide services to Community Anchor Institutions. Rapid Systems is providing Broadband Service to anchor facilities using WiMAX and other Licensed and unlicensed products. Rapid Systems has also recently completed integration and testing with Knology for Voice over Internet Protocol service. We currently are testing one community anchor on hosted Voice over Internet Protocol platform and 10 residential customers. Rapid Systems and Knology are currently working on call plans to Mexico to assist the migrant population with enhanced communications. | FRBA has consolidated its efforts for an integrate operation management strategy that will support both the FRBA North and South Central networks. FRBA has designated a single subrecipient to engineer, test and turn-up the network. The subrecipient, Rapid Systems, has also been designated as the middle mile operator. 1) Rapid Systems will operate the FRBA Networks as a subrecipient. www.rapidsys.com a. 1211 N Westshore Blvd Tampa, FL 33607 813-232-4887 b. Area Served â€“ Floridaâ€™s Heartland Counties Served â€“ Hardee, Desoto, Highlands, Okeechobee, Glades, and Hendry. Also, the community of Immokalee c. Area Served â€“ Opportunity Florida Counties Served â€“ Holmes, Washington, Jackson, Gadsden, Calhoun, Liberty, Gulf, Franklin | 0 | 3 | 0 | 1 | Unless it is a new provider, or just entering the market, we will assume that all providers are receiving improved access. | We are in discussion with several providers. Agreements are pending finalization of product and service plans. | We will not be providing access to dark fiber, as we do not have that access. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 26 | 0 | 26 | 0 | Our plan outlines service to 196 anchor institutions by project closeout. In the last report we submitted 33 CAI's, seven of these were duplications that have been corrected in this report. The 26 CAIs being served include the following: Hardee County IT Hardee County Sheriff's Office Hardee County EDA Hardee County IDA Hardee County Chamber of Commerce Wauchula Municipal Airport Main Street Wauchula USF Polytechnic City of Wauchula Police Dept. City of Wauchula City of Wauchula Annex Hardee County Fire and Rescue Wauchula Bowling Green Fire and Rescue City of Bowling Green City of Bowling Green Police Department Town of Zolfo Springs Hardee County Drug Task Force Hardee County Court House PRECo Parnell Hardee County Parks and Recreation(Hardee Lakes) Desoto County Road and Bridge Desoto County Animal Control Desoto County Fire and Rescue Station Two Desoto County EOC 100â€™ PRECo Pine Level PRECo Lily | N/A | We will assume that if service is provided through our network, that all subscribers that have some type of service will receive improved service. | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | Available speed tiers will begin at 10 Mbps, in increments of 10 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | Rapid Systems agreement is to provide a discount on services into Hardee County for three years. We are also in the process of securing very substantial capacity to allow third party providers to provide a wide array of services across our network. The full range of offerings will be determined by the marketplace, but the network has been designed to efficiently accommodate all types of traffic. | TRUE | FRBA has consolidated its Northern and South Central network operations under a single agreement with Rapid Systems. This consolidation actually simplifies the network management and integration of services across the FRBA network. In addition it leverages the best practices already implemented in Hardee County and streamlines the need to develop separate business operations practices for the Northern portion of FRBA's network. | The project team continues to evaluate conditions that have the potential of impacting the network schedule. At this time the team does not foresee any significant roadblocks that would greatly impact the schedule. The project team has built enough slack into the project so that slight slippages will not impact the substantial completion of the FRBA network. Once the tower agreements/licenses are finalized, the work can be staged and adjusted to different locations where work is ready to begin. Rapid Systems has developed a flexible â€œforward lookingâ€ project approach that scales and assigns resources based on available tasking. The work teams are managed on a weekly and daily basis so that work can be planned out to maximize work streams as well as resource utilization. This approach will enable FRBA to continue to manage contingencies that arise from time to time while focusing on making continuous progress. FRBA will be implementing its operational support systems and back office systems during the 4th quarter of 2011. This software implementation will include the customer care, work order management, network asset management, and network monitoring and support services necessary to run the FRBA network operations. During this period FRBA will also be implementing is customer service support and billing systems. Business Services and Partner Agreements â€¢ Complete FRBA Sub-recipient agreement â€¢ Prepare and bid out selective construction request for quotes â€¢ Pro | Florida Rural Broadband Alliance, LLC | The FRBA team submitted and has been executing on a 30-60-90 day transition plan to restructure the FRBA governance, project and deployment plans. FRBA has been making great strides and in fact actually accelerated a number of activities by creating a parallel process and more transparency within the project. As a result the team has completed the restructuring of the organizational administration, project budget, schedule and aligned the projects and resources move the project back to its original baseline by the end of the 4th quarter of 2011. In addition the project team recognized several opportunities to accelerate the deployment and have developed a project structure and measures that will help FRBA substantially complete the project by the end of the summer in 2012. With the support of the NTIA Program Office, FRBA has been able to continue to make progress during the restructuring of the program. This has helped the FRBA team stay on task and keep momentum, ensuring that FRBA will be able to complete the project as was originally proposed. FRBA substantially completed all of the tasks in the 30/60/90 day plan and the project is making excellent progress. From a quarterly and cumulative spend standpoint; the project will be back on track and on schedule at the end of next quarter. Equipment procurement will be completed and purchase orders issued within the next quarter. FRBA anticipates equipment delivery by the end of this year. At the same time, we are negotiati | We will be submitting an Award Action Request for a change in Subrecipient Status. We appreciate the NTIA Program Office's efforts in addressing these matters. | TRUE
NT10BIX5570122 | 2011 | Q4 | Q4 - 2011 | The Florida Rural Broadband Alliance (FRBA) has made great progress during the 4th quarter of 2012. The completion of the Request for bids and selection of equipment vendors has resulted in orders being placed and equipment being received preparing FRBA to begin construction/installation of the radios during the 1st quarter of 2012. In addition a Request for proposals was released for construction and deployment related services and 10 proposals have been received and are under evaluation. Operational Support/Back Office Systems are being deployed gearing up for operations and new operational processes are being developed and put into place getting ready to go fully operational by the end of the 1st quarter of 2012.. Outreach efforts are being accelerated to make wholesale providers and anchor tenants aware of the network. Over 70 anchors are either active or pending connections. FRBA also has 4 active wholesale partners and 8 pending wholesale partners are in further discussions on network deployment in their service areas. Programmatic Adjustments and Revisions â€¢ Completed Organizational changes â€¢ Resolved Overlap Issues â€¢ Submitted Award Action Request for revised budget, system design and match Business Services, Outreach and Marketing â€¢ Attended Broadband Technology Opportunities Program (BTOP) Recipient Conference in October â€¢ Conducted Site Visit with BTOP Program Office â€¢ Completed initial business plan and design review â€¢ Completed initial pricing model review â€¢ Completed project deployment plan, tracker and site management maps â€¢ FRBA has finalized locations for the North and South warehouses and is in the final stages of preparing the warehouses to be ready for the equipment. â€¢ Finalizing subrecipient agreement â€¢ Continued meetings with county commissioners, anchors and started development of carrier relations. â€¢ FRBA started Facebook project daily and real-time status update functionality, as well as community team building â€¢ Updated purchasing policies and redrafted fraud prevention/detection policy â€¢ Updated FRBA Website â€¢ Saltmarsh completed the annual financial audit Network Engineering â€¢ Completed site development walk-outs â€¢ Completed design re-evaluation â€¢ Completed project deployment plan, tracker and site management maps â€¢ Started FRBA North and South utility application investigation â€¢ Completed North and South Path Calculations â€¢ Completed Internet address schemas and tracking system â€¢ Completed standardization and process documentation for radios â€¢ The entire Level 3 upstream network has been deployed and activated. â€¢ Completed The City of ONA Point of Presence Connectivity to FRBA â€¢ 1st design of cabinet architecture and drawings were produced and approved. 1st sample will arrive 2nd week of January to the project office for approval so the production run can begin. Network Procurement â€¢ Developed and released equipment requests for bids. â€¢ Conducted evaluations and awarded contracts to: o Calix, Ceragon, KPG Logistics, ProSys, Power & Telephone Supply, Eupen and ConnectIt o Procured Back Office software including Symantec, Solarwinds, and SugarCRM o Procured Asset Tags from Metal Craft â€¢ FRBA placed initial orders for Microwave Radios, cabinets, switching, datacenter gear and software applications/ operating systems. â€¢ Test equipment has been ordered and should be arriving last week of January. â€¢ Developed Request for Proposals (RFP) for construction and deployment services and received 10 proposals that are under review. Site Permits & Tower Readiness â€¢ Finalized tower locations and updated deployment tracker location addresses. â€¢ Developed in-kind agreements for north and south counties â€¢ Executing Master Agreements with Crown Castle and American Tower. o All engineering, cut sheets, azimuths, dish sizes defined as part of the design and documented for tower owners. o Finalizing individual tower contracts and first 17 sites with Crown Castle. â€¢ Met with in-kind asset owners and developing in-kind agreements for towers that will be approved by municipal and county officials. â€¢ Started FCC Private Coordination Notification (PCN) process Network Deployment Test and Turn-Up â€¢ Completed testing of Pilot Operating Support Systems (OSS)/Business Support Systems (BSS) and started FRBA's implementation of the OSS/BSS. Testing virtual servers and began implementation of Sugar CRM, Solarwinds and integration of Fishbowl and Quickbooks software. â€¢ FRBAâ€™s First customer orders have been received and looking for test and turn up in early February. â€¢ Initiated Sebringâ€™s Airport initiative for broadband expansion | 278 | 1201 | 0 | 0 | 0 | 0 | 0 | 26 | The completion of Hardee County and extension of services into adjacent communities and wireless backhaul to Level 3 and Cogent has resulted in deployment of 278 miles of wireless backbone network. | The Level 3 fiber infrastructure connecting FRBA North and South to the Level 3 upstream network has been deployed and activated. | N/A | N/A | N/A | No new wireless links have been added this quarter. | Hardee County is complete and operation and services have been extended into Desoto and adjacent Counties. | The completion of Hardee County network provides 22 tower interconnection points. One of four Level 3 Points-of-Presence were activated that connects the FRBA/Hardee County to the Level 3 backbone. This is the first of four major nodal connections that will bring much needed upstream access to the rural communities of Florida. | 4 | 8 | 20 | â€¢ Rapid Systems has agreement with the Hardee County Broadband Project. â€¢ Rapid Systems has a wholesale agreement with Daystar for Last Mile Services within the FRBA project â€¢ Rapid Systems has a wholesale / Last Mile agreement with Knology for Voice over Internet Protocol services within the FRBA project and is currently deploying Hosted and Residential Voice over Internet Protocol â€¢ Rapid Systems has a wholesale/Last Mile agreements with TampaBayDSL | FRBA will provide Ethernet Wireless Transport and internet wholesale services as the Middle Mile Network. Additionally, FRBA will provide services to Community Anchor Institutions. Rapid Systems is providing Broadband Service to anchor facilities using WiMAX and other Licensed and unlicensed products. | FRBA has consolidated its efforts for an integrated operation management strategy that will support both the FRBA North and South Central networks. FRBA has designated a single subrecipient to engineer, test and turn-up the network. The subrecipient, Rapid Systems, has also been designated as the middle mile operator. 1) Rapid Systems will operate the FRBA Networks as a subrecipient. www.rapidsys.com a. 1211 N Westshore Blvd Tampa, FL 33607 813-232-4887 b. Area Served â€“ Floridaâ€™s Heartland Counties Served â€“ Hardee, Desoto, Highlands, Okeechobee, Glades, and Hendry. Also, the community of Immokalee c. Area Served â€“ Opportunity Florida Counties Served â€“ Holmes, Washington, Jackson, Gadsden, Calhoun, Liberty, Gulf, Franklin | 0 | 4 | 0 | 1 | Unless it is a new provider, or just entering the market, we will assume that all providers are receiving improved access. | We are in discussion with several providers. Agreements are pending finalization of product and service plans. | We will not be providing access to dark fiber, as we do not have that access. | Bandwidth is described as upstream/downstream for individual speed tiers. Available speed tiers will begin at 5/5 Mbps, in increments of 5 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 35 | 0 | 35 | 35 | Our plan outlines service to 196 anchor institutions by project closeout. | N/A | The majority of the anchor tenants at a minimum had dial-up services, DSL or T1s. As a result they upgrade their services by connecting to the FRBA network. | Bandwidth is described as upstream/downstream for individual speed tiers. (Download/Upload) 1) 3/512 Mbps- 5 Anchor Tenants 2) 5/5 Mbps- 1 Anchor Tenant 3) 10/2 Mbps- 22 Anchor Tenants 4) 10/5 Mbps- 2 Anchor Tenant 5) 20/5 Mbps- 5 Anchor Tenants | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | N/A | Rapid Systems agreement is to provide a discount on services into Hardee County for three years. We are also in the process of securing very substantial capacity to allow third party providers to provide a wide array of services across our network. The full range of offerings will be determined by the marketplace, but the network has been designed to efficiently accommodate all types of traffic. | FALSE | FRBA management policies will be made publicly available through the http://www.weconnectflorida.com website in 2012. | The project team continues to evaluate conditions that have the potential of impacting the network schedule. At this time the team does not foresee any significant roadblocks that would greatly impact the schedule. The project team has built enough slack into the project so that slight slippages will not impact the substantial completion of the FRBA network. Once the tower agreements/licenses are finalized, the work can be staged and adjusted to different locations where work is ready begin. Rapid Systems has developed a flexible “forward looking” project approach that scales and assigns resources based on available tasking. The work teams are managed on a weekly and daily basis so that work can be planned out to maximize work streams as well as resource utilization. This approach will enable FRBA to continue to manage contingencies that arise from time to time while focusing on making continuous progress. FRBA implemented its operational support systems and back office systems during the 4th quarter of 2011 and will be testing and certifying these systems during the 1st quarter of 2012. These systems include the customer care, work order management, network asset management, and network monitoring and support services necessary to run the FRBA network operations. During this period FRBA will also be implementing is customer service support and billing systems. Planned execution for the 1st Quarter of 2012 includes: Business Services and Partner Agreements • Complete FRBA Sub-recipient agreement • Complete FRBA Operating Agreement • Award Construction Contract Services • Initiate asset management systems and asset tagging Complete Site Engineering Documents (including any civil engineering required) • Begin and complete site preparation and civil work on first 27 towers • Begin installation, test and turn up of first 18 towers FRBA North and South Tower Agreements & Site Permitting • Complete FRBA commercial tower leases • Complete In-Kind tower agreements • Finalize FRBA North and South utility applications • Finalize FRBA North and South FCC filings Initiate and begin Construction of Network Roll-out Plan • Stage and kit equipment for deployment • Pick-up and move equipment to installation sites • Receive internal FRBA and network build partner approvals for roll-out plan • Assign third party project and construction management responsibilities for oversight, quality assurance, compliance and reporting • Provide authorization for network build partners to proceed with construction • Begin and complete site preparation and civil work on first 27 towers • Begin installation, test and turn up of first 18 towers • Physical cabinet and suite build-out for Tampa/Orlando Data Centers • Install data center equipment, test and turn up level 3 network services • Install and provision anchor tenant connections as network services become available. Network Deployment Updates: • New network miles deployed, approximately 270 new wireless miles will be deployed over the 1st quarter of 2012. • New network miles leased, No new miles this quarter. • New towers: approximately 18 new towers will be placed in service. • Total CAI subscribers served (CAIs connected)38, 32 pending connections, with 10-15 complete by the end of the 1st quarter 2012. • Number of signed agreements with broadband wholesalers or last mile providers", Several county, utility partner wholesale agreements are in the developmental stages with the possibility of 1 or 2 additional agreements that could be executed during the 1st quarter of 2012. | Florida Rural Broadband Alliance, LLC | FRBA has been making great strides and in fact actually accelerated a number of activities by creating a parallel process and more transparency within the project. As a result the team has completed the restructuring of the organizational administration, project budget, schedule and aligned the projects and resources. Request for Bids on equipment have been received, contracted and equipment has been ordered. A Request for Proposals for Construction and deployment services was issued and proposals have been received and are under evaluation. Construction is expected to begin in February 2012. The subrecipient agreement with Rapid Systems is still underway and continues to make progress. However, this process has taken longer than anticipated and now overlaps with the need to initiate the development an operating agreement. These efforts are being accelerated and will not have any impact on current construction efforts. It is anticipated that these agreements will be completed by the middle of the first quarter of 2012. FRBA is currently finalizing the contracts for the in-kind tower assets and contracting with the tower companies for leases on existing towers that will be used in the design. This process has taken longer than originally anticipated because of the number of independent tower owners that contributed their assets for use and the need to follow their legal process for executing the contract agreements. However, FRBA has been making great progress and is on tr | FRBA does not anticipate any major challenges that will hold up progress the next quarter. The in-kind agreement process is under way and appears to be on track. FRBA has all the key agreements it needs for this quarter to continue construction according to schedule. The RFPs for construction are under final evaluation for selection and should be complete in January. Construction should begin in earnest February 2012. Equipment and materials have been ordered and are arriving as anticipated and FRBA is not aware of any potential delays at this time. The warehouses have been leased and equipment is being received and asset tagged. FRBA continues to work towards the completion of the subrecipient and operating agreements. These efforts will not delay construction but need to be finalized before additional towers are brought into operation. This would effect operations activities during the second quarter of 2012 if not completed. | TRUE
NT10BIX5570122 | 2012 | Q1 | Q1 - 2012 | The Florida Rural Broadband Alliance (FRBA) has made great progress during the 1st quarter of 2012. The completion of the Request for bids and selection of equipment vendors has resulted in most of the equipment being received preparing FRBA to begin construction/installation of the radios during the 2nd quarter and 2nd half of 2012. FRBA is still waiting on cabinets and steel for tower deployment and expects to be in full construction during the 2nd quarter. In addition a Request for Proposals was released for construction and deployment related services and 10 proposals were received and evaluated. FRBA awarded contracts to G4S and Rapid Systems for construction. G4S has submitted an updated construction schedule and FRBA has released purchase orders for 47 site walks, engineering packages and drawings. The site walks have been completed and engineering and the drawings are underway. Rapid Systems began staging the Operational Support/Back Office Systems and a purchase order for the first data center equipment deployment was released. Outreach efforts are being accelerated to make wholesale providers and anchor tenants aware of the network. Over 70 anchors are either active or pending connections. FRBA also has 4 active wholesale partners and 8 pending wholesale partners are in further discussions on network deployment in their service areas. Programmatic Adjustments and Revisions â€¢ Award Action Request for Design Changes, Budget and Schedule were approved â€¢ After much deliberation Rapid Systems and FRBA decided to terminate the negotiations for the proposed subrecipient arrangement. Rapid Systems elected to provide a response to the construction RFP and will be treated as a contractor. Business Services, Outreach and Marketing â€¢ Executed Construction contracts with G4S and Rapid Systems â€¢ Revised project deployment plan, tracker and site management maps have been developed to coordinate construction and align construction with FRBA outreach and anchor tenant contracts â€¢ FRBA finalized locations for the North warehouse â€¢ FRBA is reviewing changes for the South warehouse location â€¢ FRBA has received equipment for the North and South construction. â€¢ Continued meetings with county commissioners, anchors and started development of carrier relations. Network Engineering â€¢ Completed design re-evaluation â€¢ Completed site development walk-outs for 47 sites â€¢ Completed project deployment plan, tracker and site management maps â€¢ Started FRBA North and South utility applications Network Procurement â€¢ Executed Construction contracts with G4S and Rapid Systems Site Permits & Tower Readiness â€¢ Finalized tower locations and updated deployment tracker location addresses. â€¢ Developed in-kind agreements for north and south counties â€¢ Have executed 19 in-kind agreements with 46 pending final review and approval by owners. â€¢ Met with in-kind asset owners and developing in-kind agreements for remaining towers that will be approved by municipal and county officials. â€¢ Have received approvals and signed agreements back from Highlands County and Chipley. Desoto County has approved and should have executed agreements the 2nd quarter of 2012. â€¢ With 30% approved tower site engineering will begin and the majority of the in-kind towers should be complete by the 3rd quarter. â€¢ Executed Master Agreements with Crown Castle and American Tower. â€¢ Finalized individual tower contracts and first 17 sites with Crown Castle. â€¢ Received structural feedback from Crown Castle and American Tower, a number of towers failed their structural review and have been re-engineered and scheduled for structural modifications. â€¢ Started FCC Private Coordination Notification (PCN) process Network Deployment Test and Turn-Up â€¢ Installed three new tower links and the network link from Hardee County to the City of Sebring â€¢ Connected new CAIs including the Sebring Regional Airport initiative for broadband expansion | 282 | 1201 | 0 | 0 | 0 | 3 | 0 | 28 | The completion of Hardee County and extension of services into adjacent communities and wireless backhaul to Level 3 and Cogent has resulted in deployment of 282 miles of wireless backbone and Community Anchor Institutional network. | The Level 3 fiber infrastructure connecting FRBA North and South to the Level 3 upstream network has been deployed and activated. | N/A | N/A | N/A | The Highland County Sebring Regional Airport was activated in February. | N/A | The completion of Hardee County network provides 22 tower interconnection points. One of four Level 3 Points-of-Presence were activated that connects the FRBA/Hardee County to the Level 3 backbone. This is the first of four major nodal connections that will bring much needed upstream access to the rural communities of Florida. Two towers extending off of the Hardee network were added to connect the Sebring Regional Airport. | 4 | 8 | 20 | â€¢ Rapid Systems has agreement with the Hardee County Broadband Project. â€¢ Rapid Systems has a wholesale agreement with Daystar for Last Mile Services within the FRBA project â€¢ Rapid Systems has a wholesale / Last Mile agreement with Knology for Voice over Internet Protocol services within the FRBA project and is currently deploying Hosted and Residential Voice over Internet Protocol â€¢ Rapid Systems has a wholesale/Last Mile agreements with TampaBayDSL The initial agreements for wholesale services were developed under Rapid Systems as a Sub Recipient. As a result of restructuring the sub recipient arrangement FRBA will transition these wholesale agreements to the FRBA organization. These agreements will be reauthorized and executed by the FRBA management team. | FRBA will provide Ethernet Wireless Transport and internet wholesale services as the Middle Mile Network. Additionally, FRBA will provide services to Community Anchor Institutions. Rapid Systems is providing Broadband Service to anchor facilities using WiMAX and other Licensed and unlicensed products. Retail Wholesale Service Pricing Tiers in Attached in Wholesale Services Exhibit | FRBA has split its efforts for an operation management strategy between FRBA North and South Central networks. FRBA has contracted with Rapid Systems to engineer, test and turn-up the network. FRBA is in the process of negotiating with Rapid Systems, to become the interim FRBA middle mile operator. 1) Rapid Systems will operate the FRBA Networks as a contractor. www.rapidsys.com a. 1211 N Westshore Blvd Tampa, FL 33607 813-232-4887 b. Area Served â€“ Floridaâ€™s Heartland Counties Served â€“ Hardee, Desoto, Highlands, Okeechobee, Glades, and Hendry. Also, the community of Immokalee c. Area Served â€“ Opportunity Florida Counties Served â€“ Holmes, Washington, Jackson, Gadsden, Calhoun, Liberty, Gulf, Franklin | 0 | 4 | 0 | 1 | Unless it is a new provider, or just entering the market, we will assume that all providers are receiving improved access. | We are in discussion with several providers. Agreements are pending finalization of product and service plans. | We will not be providing access to dark fiber, as we do not have that access. | Bandwidth is described as upstream/downstream for individual speed tiers. Available speed tiers will begin at 5/5 Mbps, in increments of 5 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 34 | 0 | 34 | 34 | Our plan outlines service to 196 anchor institutions by project closeout. Some early turnover and consolidation have occurred bring the actual number to 34. | N/A | The majority of the anchor tenants at a minimum had dial-up services, DSL or T1s. As a result they upgrade their services by connecting to the FRBA network. | Bandwidth is described as upstream/downstream for individual speed tiers. (Download/Upload) 1) 3/512 Mbps- 6 Anchor Tenants 2) 5/5 Mbps- 1 Anchor Tenant 3) 10/2 Mbps- 20 Anchor Tenants 4) 10/5 Mbps- 3 Anchor Tenant 5) 20/5 Mbps- 4 Anchor Tenants | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | N/A | Rapid Systems agreement is to provide a discount on services into Hardee County for three years. We are also in the process of securing very substantial capacity to allow third party providers to provide a wide array of services across our network. The full range of offerings will be determined by the marketplace, but the network has been designed to efficiently accommodate all types of traffic. | FALSE | N/A | The project team continues to evaluate conditions that have the potential of impacting the network schedule. At this time the team does not foresee any significant roadblocks that would greatly impact the schedule. The project team has built enough slack into the project so that slight slippages will not impact the substantial completion of the FRBA network. Some structural modifications of towers have started and one tower has fallen out of the design due to structural issues. Re-engineering has resolved the network topology change. Over half of the towers are under license enabling the scheduling of 20-tower radio-antenna installation in the 2nd quarter. Once the remaining tower agreements/licenses are finalized, the work can be staged and adjusted to different locations where the balance of work is ready to begin. G4S and Rapid Systems have developed a flexible â€œforward lookingâ€ project approach that scales and assigns resources based on available tasking. The work teams are managed on a weekly and daily basis so that work can be planned out to maximize work streams as well as resource utilization. This approach will enable FRBA to continue to manage contingencies that arise from time to time while focusing on making continuous progress. FRBA implemented its operational support systems and back office systems during the 4th quarter of 2011 and began testing, configuring and modifying the back office processes. It is anticipated the full back office deployment will be completed and installed in the data centers during the 2nd quarter of 2012. These systems include the customer care, work order management, network asset management, and network monitoring and support services necessary to run the FRBA network operations. During this period FRBA will also be implementing its customer service support and billing systems. Planned execution for the 2nd Quarter of 2012 includes: Business Services and Partner Agreements â€¢ Complete FRBA Interim Operating Agreements â€¢ Execute partner and channel agreements with wholesale and retail service partners â€¢ Develop a strategy for alternative service partner arrangements for the addition of value added services that meet the needs of the Community Anchor Institutions and generate additional earned income Complete Site Engineering Documents (including any civil engineering required) â€¢ Begin and complete site preparation and civil work on first 47 towers â€¢ Begin radio-antenna installation, test and turn up of first 20 towers FRBA North and South Tower Agreements & Site Permitting â€¢ Complete In-Kind tower agreements â€¢ Manage structural modifications and redesign issues due to changes in site configurations â€¢ Finalize FRBA North and South utility applications â€¢ Finalize FRBA North and South FCC filings Initiate and begin Construction of Network Roll-out Plan â€¢ Stage, kit and ship equipment for deployment â€¢ Begin and complete civil work on first 20 towers â€¢ Begin radio-antenna installation, test and turn up of first 20 towers â€¢ Physical cabinet and suite build-out for Orlando Data Center â€¢ Install data center equipment, test and turn up level 3 network services â€¢ Install and provision anchor tenant connections as network services become available. Network Deployment Updates: â€¢ New network miles deployed, approximately 200 new wireless miles will be deployed over the 2nd quarter of 2012. â€¢ New network miles leased, No new miles this quarter. â€¢ New towers: no new towers will be placed in service. â€¢ Total CAI subscribers served (CAIs connected) 38, 32 pending connections, with 5 to 10 complete by the end of the 2nd quarter 2012. â€¢ Number of signed agreements with broadband wholesalers or last mile providers", Several county, utility partner wholesale agreements are in the developmental stages with the possibility of 1 or 2 additional agreements that could be executed during the 1st quarter of 2012. | Florida Rural Broadband Alliance, LLC | FRBA has been making great strides and in fact actually accelerated a number of activities by creating a parallel process and more transparency within the project. As a result the team has completed the restructuring of the organizational administration, project budget, schedule and aligned the projects and resources. The subrecipient Agreement with Rapid Systems has been taken off the table in favor of a construction contract with G4S and Rapid Systems. FRBA is continuing to finalize the contracts for the in-kind tower assets and contracting with the tower companies for leases on existing towers that will be used in the design. This process has taken longer than originally anticipated because of the number of independent tower owners that contributed their assets for use and the need to follow their legal process for executing the contract agreements. However, FRBA has been making great progress and is on track to complete enough tower agreements in key areas so construction will not be impacted by the delays. FRBA has initiated the construction contracts and started the construction process. Over half of the towers have executed leases and some towers have failed inspection and require structural modifications. FRBA has received some of the estimates and has begun to approve structural modifications. To keep on track with the schedule, FRBA will need to complete all the in-kind leases by the end of July. From a quarterly and cumulative spend standpoint; the project | FRBA does not anticipate any major challenges that will hold up progress the next quarter. The in-kind agreement process is under way and appears to be on track. FRBA has all the key agreements it needs for this quarter to continue construction according to schedule. Construction should begin in earnest the 2nd quarter and be in full swing the 2nd half of 2012. Equipment and materials with the exception of cabinets and some steel have been delivered. FRBA does not anticipate any additional delays at this time. The warehouse in the North has been leased and equipment is being received and asset tagged. FRBA South is anticipating a move of the South warehouse to a new location. FRBA has experienced some tower failures, requiring structural modifications. This process has begun. Out of 47 towers one tower completely failed and required minor network redesign. FRBA anticipates that additional tower modifications will be required. At this time all the structural modifications appear to have no impact on the project deployment schedule. FRBA anticipates requesting an Award Action Request (AAR) during the 3rd quarter of 2012. FRBA continues to work towards the completion of an interim operating agreement. These efforts will not delay construction but need to be finalized before additional towers are brought into operation. This would affect operations activities during the 2nd half of 2012 if not completed. This report reflects the revised budget based on breaking out the constru | TRUE
NT10BIX5570122 | 2012 | Q2 | Q2 - 2012 | The Florida Rural Broadband Alliance (FRBA) has executed the commercial leases with American Tower, Crown Castle and SBA completed over 47 site walks. In addition FRBA has executed 18 in-kind tower leases and recently completed the engineering packages for the initial deployment. The engineering packages have been received along with the permit packages. G4S was hired as the Project Manager to include coordination of all vendors and subcontractors related to design and deployment of the FRBA network. FRBA transitioned from a subrecipient to a vendor.arrangement. The initial delay in receiving the engineering and permit packages has delayed the initial construction start which is now scheduled for August. G4S is in the process of adjusting the master tracker schedule to accommodate the shift in construction and been coordinating the subcontractors to accommodate an accelerated schedule. G4S is in the process of facilitating the redesign of the data centers to accommodate a shift from Tampa to Orlando as the main data center and evaluating new In-Line Amplification (ILA) inter-connections in the North and South to accommodate the additional bandwidth needs of FRBAs wholesale and channel resellers. FRBA also requested for proposals to several consultant groups to develop a long-range sustainability plan. The objective of the sustainability plan is to build on the work that was done by the Florida State University (USF) in evaluating the Community Anchor Institutions (CAIs). The projections and analysis will be used to optimize the service deployment and maximize earned income from building wholesale/retail relationships and connecting the CAIs. Outreach efforts are being accelerated to make wholesale providers and anchor tenants aware of the network. FRBA has begun active discussions with wholesale and resale partners and are in further discussions on network deployment in their service areas. Programmatic Adjustments and Revisions â€¢ Opportunity Floridaâ€™s executive director retired and has been replaced by Jim Brooks who has taken over as its owner representative for FRBA. â€¢ Thompson, Walker & Associates, LLC has taken over for the accounting and fiscal management of the FRBA Middle Mile Project. â€¢ FRBA has relocated its south warehouse and operations under the control of FRBA with support from G4S. Business Services, Outreach and Marketing â€¢ Revised project deployment plan, tracker and site management maps have been developed to coordinate construction and align construction with FRBA outreach and anchor tenant contracts â€¢ Developed discussions with local Electrical Co-ops and wholesale/channel partners requiring some reconsideration of the interconnections and capacity arrangements with Level 3. Network Engineering â€¢ Completed project deployment plan, tracker and site management maps â€¢ Started FRBA North and South utility applications â€¢ Started FCC Private Coordination Notification (PCN) process Site Permits & Tower Readiness â€¢ Updating tower locations base on specific site structural failures â€¢ Finalized tower locations and updated deployment tracker location addresses. â€¢ Finalizing remaining in kind tower locations and approval by owners. â€¢ With over 50% approved tower site engineering will begin and the majority of the in-kind towers should be complete by the 3rd quarter. â€¢ Executed Master Agreements with Crown Castle, American Tower and SBA. â€¢ FRBA is currently working with the tower owners to re-engineer and implement structural modifications. | 282 | 1201 | 0 | 0 | 0 | 3 | 2 | 28 | The completion of Hardee County and extension of services into adjacent communities and wireless back haul to Level 3 has resulted in deployment of 282 miles of wireless backbone and Community Anchor Institutional network. | The Level 3 fiber infrastructure connecting FRBA North and South to the Level 3 upstream network has been deployed. | N/A | N/A | N/A | N/A | N/A | The completion of Hardee County network provides 22 tower interconnection points. One of four Level 3 Points-of-Presence were activated that connects the FRBA/Hardee County to the Level 3 backbone. This is the first of four major nodal connections that will bring much needed upstream access to the rural communities of Florida. | 1 | 4 | 20 | The initial agreements with wholesale and retail partners were established through the subrecipient arrangement and are in transition.. The transition away from the subrecipient agreement the changed the status of the existing agreements. FRBA is in the process of re-establishing these commitment and developing new ones during the second half of 2012. | FRBA will provide Ethernet Wireless Transport and internet wholesale services as the Middle Mile Network. Additionally, FRBA will provide services to Community Anchor Institutions. FRBA will be providing Broadband Service to anchor facilities using WiMAX and other Licensed and unlicensed products. The pricing plan will be provided under separate cover. | FRBA is in the process of evaluating 3rd party options for the operations and management of the FRBA network. It is anticipated that FRBA will have its operating agreements in place prior to activating the network for services during the 2nd half of 2012. | 1 | 1 | 0 | 1 | Unless it is a new provider, or just entering the market, we will assume that all providers are receiving improved access. | We are in discussion with several providers. Agreements are pending finalization of product and service plans. | We will not be providing access to dark fiber, as we do not have that access. | Bandwidth is described as upstream/downstream for individual speed tiers. Available speed tiers will begin at 5/5 Mbps, in increments of 5 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 34 | 0 | 34 | 34 | Our plan outlines service to 196 anchor institutions by project closeout. | N/A | The majority of the anchor tenants at a minimum had dial-up services, DSL or T1s. As a result they upgrade their services by connecting to the FRBA network. | Bandwidth is described as upstream/downstream for individual speed tiers. (Download/Upload) 1) 3/512 Mbps- 6 Anchor Tenants 2) 5/5 Mbps- 1 Anchor Tenant 3) 10/2 Mbps- 20 Anchor Tenants 4) 10/5 Mbps- 3 Anchor Tenant 5) 20/5 Mbps- 4 Anchor Tenants | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | N/A | We are also in the process of securing very substantial capacity to allow third party providers to provide a wide array of services across our network. The full range of offerings will be determined by the marketplace, but the network has been designed to efficiently accommodate all types of traffic. | TRUE | With the retirement of Richard Marcum, Jim Brook, Executive Director for Opportunity Florida has taken over the FRBA co-manager position in the North. In addition Thompson, Walker & Associates, LLC, Certified Public Accountants have taken over the accounting and fiscal management functions for the FRBA project. | The project team continues to evaluate conditions that have the potential of impacting the network schedule. At this time the team does not foresee any significant roadblocks that would greatly impact the schedule. The project team has built enough slack into the project so that slight slippages will not impact the substantial completion of the FRBA network. Some structural modifications of towers have started and several tower has fallen out of the design due to structural issues. Re-engineering has resolved the network topology change. Over half of the towers are under license enabling the scheduling of over 47-tower radio-antenna installation in the 3rd quarter. Once the remaining tower agreements/licenses are finalized, the work can be staged and adjusted to different locations where the balance of work is ready to begin. G4S has developed a flexible â€œforward lookingâ€ project approach that scales and assigns resources based on available tasking. The work teams are managed on a weekly and daily basis so that work can be planned out to maximize work streams as well as resource utilization. This approach will enable FRBA to continue to manage contingencies that arise from time to time while focusing on making continuous progress. FRBA implemented its interim operational support systems and back office systems during the 4th quarter of 2011 and began testing, configuring and modifying the back office processes. FRBA will be transferring the back office and system support services from the lab to the Orlando Data Center during the 3rd quarter of 2012. It is anticipated the full back office deployment will be completed and installed in the data centers during the 3rd quarter of 2012. These systems include the customer care, work order management, network asset management, and network monitoring and support services necessary to run the FRBA network operations. During this period FRBA will also be implementing its customer service support and billing systems. Planned execution for the 3rd Quarter of 2012 includes: â€¢ Complete the business sustainability plan â€¢ Execute new partner and channel agreements with wholesale and retail service partners â€¢ Develop a strategy for alternative service partner arrangements for the addition of value added services that meet the needs of the Community Anchor Institutions and generate additional earned income Complete Site Engineering Documents (including any civil engineering required) â€¢ Begin and complete site preparation and civil work on first 47 towers â€¢ Begin radio-antenna installation, test and turn up FRBA North and South Tower Agreements & Site Permitting â€¢ Complete In-Kind tower agreements â€¢ Manage structural modifications and redesign issues due to changes in site configurations â€¢ Finalize FRBA North and South utility applications â€¢ Finalize FRBA North and South FCC filings Initiate and begin Construction of Network Roll-out Plan â€¢ Stage, kit and ship equipment for deployment â€¢ Begin and complete civil work on first 20 towers â€¢ Begin radio-antenna installation, test and turn up of first 20 towers â€¢ Physical cabinet and suite build-out for Orlando Data Center â€¢ Install data center equipment, test and turn up level 3 network services â€¢ Install and provision anchor tenant connections as network services become available. Network Deployment Updates: â€¢ new network miles deployed, approximately 200 new wireless miles will be deployed over the 3rd quarter of 2012. â€¢ New network miles leased, No new miles this quarter. â€¢ New towers: no new towers will be placed in service. â€¢ Number of signed agreements with broadband wholesalers or last mile providers", Several county, utility partner wholesale agreements are in the developmental stages with the possibility of 1 or 2 additional agreements that could be executed during the 4th quarter of 2012. â€¢ No new CAIs this quarter until towers and data center services are activated and certified. | Florida Rural Broadband Alliance, LLC | As a result of some organizational and administrative changes in regards to the subrecipient to vendor arrangements the contractor has slowed progress until negotiations could be completed. G4S has stepped into the project management role and worked to resolve the contract issues. This resulted in delays related to the receipt of the engineering and permit packages. FRBA has worked to accelerate the development of the engineering and permit packages. The project team continues to evaluate conditions that have the potential of impacting the network schedule. At this time the team does not foresee any significant roadblocks that would greatly impact the schedule. FRBA is taking a forward looking program management approach which helps assign tasking in parallel where we see potential timing challenges in the future. Much of the work is just in time, but there are lead times for agreements, licensing and legal issues that need resolution earlier in order not to affect workflow. The FRBA project teams have created a great deal of flexibility and can now be assigned to different regions based on available permits/licenses. This forward-looking approach reduces potential slack periods and increases team efficiency. The construction RFP included a request for additional project, construction and site management. FRBA intends to add additional resources in the North and South to maintain schedule commitments. FRBA will add construction and installation crews to accelerate its effo | FRBA has all the key agreements it needs for this quarter to continue construction according to schedule. Construction should begin in earnest the 2nd half of 2012. Equipment and materials with the exception of cabinets and some steel have been delivered. FRBA has evaluated engineering issues highlighted by NFBA and is in the process of evaluating their impact on budget and schedule. FRBA does not anticipate any additional delays at this time. FRBA has experienced some tower failures, requiring structural modifications. This process has required FRBA to evaluate other tower options. Out of 47 towers two towers completely failed and required minor network redesign. FRBA anticipates that additional tower modifications will be required outside of the initial deployment. At this time all the structural modifications appear to have no impact on the project deployment schedule. FRBA anticipates requesting an Award Action Request (AAR) during the 3rd quarter of 2012 regarding the redesign as a result of structural failures. FRBA continues to work towards the identifying an interim operating partner. These efforts will not delay construction but need to be finalized before additional towers are brought into operation. This would affect operations activities during the 2nd half of 2012 if not completed. Changes to the Infrastructure Budget Related to in-Kind Distribution: 1) The majority of the In-Kind in Miscellaneous and Equipment has been redistributed to category b. Land Stru | TRUE
NT10BIX5570122 | 2012 | Q3 | Q3 - 2012 | FRBA contracted with Magellan Advisors to conduct a demand market assessment and develop a sustainability plan. The plan was delivered and FRBA/G4S have been evaluating the design and schedule based on the results of the initial demand assessment. These adjustments will be reflected in a new project rollout schedule and in a revised engineering plan that will be submitted as an Award Action Request (AAR). Florida Rural Broadband Alliance (FRBA) has executed commercial leases with American Tower, Crown Castle and SBA completed over 47 commercial site walks. In addition FRBA has executed over 30 in-kind tower leases and recently completed the engineering packages for the initial deployment. The engineering packages have been received along with the permit packages. G4S has stepped into the engineering and PCN processing role and has been working with the FCC to finalize the radio frequency licensing. The FCC is asking for some review and modifications to the PCN requests requiring some link re-engineering across the FRBA network. The process continues to move forward and will require some radio substitutions. FRBA has retained Telezoo, Inc. to serve as FRBA's engineering representative and Inspired Technologies of North Florida to facilitate staging of the tower cabinets and to build out the data centers. Inspired Technologies facilitated the transition of North Florida Broadband Authority's network deployment and was familiar with the FRBA design issues. During the last quarter Inspired has staged, and configured a majority of the cabinets. In addition, Inspired has evaluated the air conditioning options and tested an alternative cooling strategy that requires smaller air conditioning units and minor modifications to the cabinet doors. This new configuration will be ready for deployment the third quarter of 2012. Inspired Technologies also installed and configured the Orlando Data Center. The FRBA network head end has been initialized and interconnected to Internet services in collaboration with the North Florida Broadband Authority. G4S has adjusted the project deployment schedule to accommodate the re-engineering required for the PCNs and the cabinet modifications. The new schedule shows construction accelerating during the last quarter of 2012 and moving into the first quarter of 2013. This will move the majority of the active network services into the first quarter of 2013. FRBA is accelerating its efforts to find, contract and collaboration with potential wholesale and retail partners. In addition FRBA is evaluating alternative operating partners and investment partners to facilitate the on-going channel development, engineering, field services and operations of the network. These efforts include modifying the budget and matching considerations in compliance with the original FRBA grant request. FRBA expects to provide its NTIA Program Officer with a final Award Action Request for the budget and match during the fourth quarter of 2012. Outreach efforts are being accelerated to make wholesale providers and anchor tenants aware of the network. FRBA has begun active discussions with wholesale and resale partners and are in further discussions on network deployment in their service areas. Programmatic Adjustments and Revisions â€¢ Magellan Market Demand Study has been reviewed and used to adjust the deployment schedule relative to the regions demand â€¢ G4S has taken over the engineering and FCC PCN licensing process â€¢ Inspired Technologies has taken over the data center engineering and equipment/cabinet staging Business Services, Outreach and Marketing â€¢ Revised project deployment plan, tracker and site management maps have been developed to coordinate construction and align construction with the Market Demand Study and Sustainability Plan â€¢ FRBA continues discussions with local Electrical Co-ops and wholesale/channel partners requiring some reconsideration of the interconnections and capacity arrangements within the FRBA network and Level 3. Network Engineering â€¢ Completed re-engineering of the equipment and cabinets â€¢ Making cooling modifications to the network â€¢ Re-engineering links based on FCC requests â€¢ Managing FCC Prior Coordination Notification (PCN) process and impact on FRBA network design Site Permits & Tower Readiness â€¢ FRBA is currently working with the tower owners to re-engineer and implement structural modifications. | 0 | 1201 | 0 | 0 | 0 | 0 | 0 | 0 | With the restructuring of the subrecipient and in-kind partner agreements, FRBA is re-evaluating the build miles based on new partnerships and anticipates reporting significant progress during the last quarter. This number is expected to change with the acceptance of the engineering and project plan AARs. | The Level 3 fiber infrastructure connecting FRBA North and South to the Level 3 upstream network has been deployed. | N/A | N/A | N/A | N/A | N/A | None at this time. | 0 | 0 | 0 | The initial agreements with wholesale and retail partners were established through the subrecipient arrangement which has been cancelled. The transition away from the subrecipient agreement also changed the status of the existing agreements. FRBA is in the process of re-establishing these commitments and developing new ones during the last quarter of 2012. | FRBA will provide Ethernet Wireless Transport and internet wholesale services as the Middle Mile Network. Additionally, FRBA will provide services to Community Anchor Institutions. FRBA will be providing Broadband Service to anchor facilities using WiMAX and other Licensed and unlicensed wireless products. The pricing plan will be provided under separate cover. | FRBA is in the process of evaluating 3rd party options for the operations and management of the FRBA network. It is anticipated that FRBA will have its operating agreements in place prior to activating the network for services in 2013. | 0 | 0 | 0 | 0 | Unless it is a new provider, or just entering the market, we will assume that all providers are receiving improved access. | We are in discussion with several providers. Agreements are pending finalization of product and service plans. | We will not be providing access to dark fiber, as we do not have that access. | Bandwidth is described as upstream/downstream for individual speed tiers. Available speed tiers will begin at 5/5 Mbps, in increments of 5 Mbps to 100 Mbps. Service to 1 Gbps will be available, but we have conservatively estimated that we will only add customers at that level of service beyond year 3. | 0 | 0 | 0 | 0 | Our plan outlines service to 196 anchor institutions by project closeout. | N/A | The majority of the anchor tenants at a minimum had dial-up services, DSL or T1s. As a result they upgrade their services by connecting to the FRBA network. | Bandwidth is described as upstream/downstream for individual speed tiers. (Download/Upload) | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | n/a | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | When completed, the FRBA network will allow last mile providers the ability to cover the entire geography of the service area. | N/A | N/A | N/A | N/a | FRBA is also in the process of securing very substantial capacity to allow third party providers to provide a wide array of services across our network. The full range of offerings will be determined by the marketplace, but the network has been designed to efficiently accommodate all types of traffic. The restructuring of the subrecipient agreement under FRBA has changed the relationship and the status of existing agreements. These changes will be reflected over the next quarter. | FALSE | N/A | The project team continues to evaluate conditions that have the potential of impacting the network schedule. Many of the core engineering, configuration and licensing issues continue to be worked through and resolved. Re-engineering, design changes are expected to take place in parallel with construction activities. Most of the ongoing engineering will affect radio frequency engineering, and may cause some sites to fall out of the design or radios to be replaced due to a change in the radio frequency being used. This is normal in many designs. However, because of the tight time lines related to the grant, FRBA may have to trade or acquire additional radios and antennas. G4S has been working with vendors and partners to facilitate the exchange of radios to accommodate the quick turn around. This is not expected to affect the overall project schedule but will affect some sites/links within the network. The project team has built enough slack into the project so that the current slippages will not impact the substantial completion of the FRBA network. Some structural modifications of towers are continuing and the final engineering plan will be resolved of the next quarter. FRBA expects to submit a final Award Action Request for the FRBA engineering plan this quarter. Over half of the towers are under license enabling the scheduling of over 47-tower radio-antenna installations in the 4th quarter. Once the remaining tower agreements/licenses are being finalized, work can be staged and adjusted to different locations where the balance of work is ready to begin. G4S has developed a flexible â€œforward lookingâ€ project approach that scales and assigns resources based on available tasking. Work teams are managed on a weekly and daily basis so that work can be planned out to maximize work streams as well as resource utilization. Additional construction teams can be added as PCNS and permits are received. This approach will enable FRBA to continue to manage contingencies that arise from time to time while focusing on making continuous progress. FRBA implemented its interim operational support systems and back office systems during the 4th quarter of 2011 and began testing, configuring and modifying the back office processes. FRBA will be transferring the back office and system support services to the Orlando Data Center. FRBA anticipates the full back office deployment will be completed and installed in the data centers during the last quarter of 2012. These systems include the customer care, work order management, network asset management, and network monitoring and support services necessary to run FRBA network operations. During this period FRBA will also be implementing its customer service support and billing systems. Planned execution for the 4th Quarter of 2012 includes: â€¢ Implementation of a outreach and sales strategy in conjunction with the market demand study completed by Magellan â€¢ Execute new partner and channel agreements with wholesale and retail service partners â€¢ Develop a strategy for alternative service partner arrangements for the addition of value added services that meet the needs of the Community Anchor Institutions and generate additional earned income Complete Engineering and Network Redesign Efforts â€¢ Follow-up on PCN process, re-engineer Radio Frequency/Radio Design â€¢ Finalize site preparation and materials requirements â€¢ Begin radio-antenna installation, test and turn up FRBA North and South Tower Agreements & Site Permitting â€¢ Complete In-Kind tower agreements â€¢ Manage structural modifications and redesign issues due to changes in site configurations â€¢ Finalize FRBA North and South utility applications â€¢ Finalize FRBA North and South FCC filings Network Deployment Updates: â€¢ New network miles deployed, approximately 200 new wireless miles will be in progress of deployment over the 4th quarter of 2012. â€¢ New network miles leased, No new miles this quarter. â€¢ New towers: no new towers will be placed in service. â€¢ Number of signed agreements with broadband wholesalers or last mile providers: Several county, utility partner wholesale agreements are in the developmental stages with the possibility of 1 or 2 additional agreements that could be executed during the 4th quarter of 2012. â€¢ No new CAIs this quarter until towers and data center services are activated and certified. | Florida Rural Broadband Alliance, LLC | FRBA has faced several challenges this quarter. As a result of a contract dispute FRBA has replaced its engineering firm with more support from G4S and hired Inspired Technologies who worked with the North Florida Broadband Authority. Even though both contractors were already familiar with the project it became clear that some re-engineering and configuration was required. Both teams worked diligently during the third quarter to resolve these issues. The three key issues that FRBA faced related to the RF Design and FCC PCN request process, the engineering and configuration of the core data centers and Level 3 services, and finally the equipment cabinet configuration and cooling. Even though great progress has been made during the third quarter it still impacted the team's ability to maintain the original construction plan. G4S has developed a new deployment schedule that reflects a slight shift moving much of the build into the end of the forth quarter and into the first quarter. In addition, the change in vendor relationship also affected the design and partnership with Hardee County affecting the engineering design in the South and the match requirements for the project. FRBA has been working to resolve these issues or provide an alternative solution that provides the necessary match and long-term sustainable engineering and operations support for the project. NTIA sent FRBA a performance improvement plan letter requesting that FRBA provide a plan for resolving the ma | FRBA will submit a plan in response to NTIAs Performance Improvement Plan letter. This will require FRBA to align its strategies with potential parties that can provide the appropriate match and support the long-term sustainability of the program. Changes to the Infrastructure Budget Related to in-Kind Distribution: 1) The majority of the In-Kind in Miscellaneous and Equipment has been redistributed to category b. Land Structures, rights-of-way, appraisals, etc. This more accurately reflects the actual assets that have been contributed to the project. This change will be reflected in a revised budget. The shift was prompted by a shift in subrecipient and in-kind match. The change resulted in a difference in match recognition. This is a one-time change and the supplemental budget changes will be submitted to the NTIA PMO office with an award action request. FRBA continues to work toward identifying an interim operating partner and resolving deficiencies in the match. These efforts will not delay construction but need to be finalized before additional NTIA funding is made available. This would affect operations activities during the 1st half of 2013 if not completed. FRBA will finalize its engineering plan, budget, match, and deployment schedule. In parallel FRBA will continue to manage the deployment of the network in accordance with the primary plan and make modifications as required. As a result of the actions FRBA will develop a series of Award Action Requests: 1) â | TRUE
NT10BIX5570122 | 2012 | Q4 | Q4 - 2012 | NOTE: The following report reflects the 2nd quarter change of construction manager and engineering resource, the 3rd quarter reassessment of tasks required to complete, identification of resources required, contractual effort to employ the resources and finally in the 4th quarter full engagement of the resources to the tasks. a. RE-ENGINEERED NETWORK DESIGN: A full network redesign utilizing all prior data possible to build a network that is technically feasible to deploy, aligned to customer demand and provides an easier architecture to operationally maintain was conducted. A new design was conducted with demographic, monetary return and timing in consideration. The project team believes this was the best approach given the project constraints and that the risks can be managed. b. PROJECT RESOURCE ALIGNMENT: Project resources from FRBA, G4S, Inspired Technologies, Magellan and Telezoo were able to define roles and responsibilities in the deployment process, which will further be refined and improved in quarter 1 as construction activities ramp-up. The alignment of these resources will improve the efficiency and reduce the overall deployment cycle time moving forward. 3. The network design is optimized to provide service at a lower cost by eliminating sites that were not needed and also that did not have a positive net present value ("NPV") based on the forecasted customer demand. The prior design clustered backbone sites in a close proximity that were not required - removal of these sites saved significant amount on construction costs and simplified network operations moving forward. The new design also removed sites where there was not a positive NPV based on forecasted customer demand. 4. Inspired Technologies has completed staging and configuring the microwave equipment and IP ("Internet Protocol") switches in the cabinets at the two FRBA warehouses. This work will further reduce the overall deployment cycle time since this work will now not need to be done in the field. 5. The construction process is being run in parallel with the remaining pre-construction tasks. | 29 | 1201 | 0 | 0 | 0 | 1 | 0 | 0 | FRL016-FRL009 was completed in quarter 4 with full connectivity back to the Orlando data center. 2 additional sites are at 95% completion and are waiting on pathing and final release of the punch-down list. | N/A | N/A | N/A | N/A | FRL016-FRL009 was completed in quarter 4 with full connectivity back to the Orlando data center. | N/A | N/A | 0 | 1 | 8 | FRBA has not signed any agreements with wholesale or last mile providers during this reporting period. | The FRBA network provides transport, commodity Internet and co-location services to wholesale providers in the region. FRBA's services will allow wholesale providers (LEC's, CLEC's, Broadband Access and Wireless Access) to receive new type 2 middle-mile services across the service area with bandwidths between 5Mbp and 200Mbp. FRBA's wholesale will connect wholesale providers between multiple on-net points within the network or between points within the network and interconnecting data centers located in Orlando, FL and Tallahassee, FL. Data centers provide neutral access with interconnecting carriers utilizing Ethernet-based NNIs (network-to-network interconnections). FRBA also provides commodity Internet access at its data centers for wholesale providers who require transport + IP connections. FRBA also provides dedicated colocation at the Orlando data center for wholesalers needing local presence in this facility. The wholesale pricing plan for dedicated services is attached to this PPR. | FRBA has not yet designated a third party to operate its network. FRBA is in the process of procuring a network operator who will manage all network operations for the organization. Procurement will be completed in advance of network commissioning and activation to ensure a smooth hand-over and transition phase. The network operator will be tasked with the following primary responsibilities: -network management and monitoring -field services -provisioning and activations -installations and terminations -billing management -customer service -upgrades and expansions | 0 | 0 | 0 | 0 | FRBA is currently in discussions with several wholesalers for purchase of capacity on the FRBA network. | FRBA is currently in discussions with several wholesalers for purchase of capacity on the FRBA network. | FRBA does not provide dark fiber services. | Speed tiers will begin at 5Mbp and scale to 200Mbp and greater in special cases. FRBA will have the capability to provide gigabit speeds on an individual case basis. | 34 | 0 | 34 | 0 | FRBA is actively ramping up its CAI outreach program to ensure it maximizes uptake in the first year of operations. In addition, FRBA is actively participating in the E-Rate Schools and Libraries program to identify school districts, community colleges and libraries that will be significant users of FRBA's broadband services. | FRBA is actively ramping up its CAI outreach program to ensure it maximizes uptake in the first year of operations. In addition, FRBA is actively participating in the E-Rate Schools and Libraries program to identify school districts, community colleges and libraries that will be significant users of FRBA's broadband services. | FRBA is actively ramping up its CAI outreach program to ensure it maximizes uptake in the first year of operations. In addition, FRBA is actively participating in the E-Rate Schools and Libraries program to identify school districts, community colleges and libraries that will be significant users of FRBA's broadband services. | Speed tiers will begin at 5Mbp and scale to 200Mbp and greater in special cases. FRBA will have the capability to provide gigabit speeds on an individual case basis. | 0 | 0 | 0 | 0 | 0 | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | 0 | 0 | 0 | 0 | 0 | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | FRBA will have built-in capabilities to provide on-net services between community anchors throughout the region. This will allow for collaboration and interconnection between separate CAI organizations that need to share data between one another. FRBA will also have the capabilities to offer colocation and data center space to CAIs requiring secure data backup facilities. CAIs will have layer 2 access to such facilities across the FRBA network, enabling them to maintain direct on-net connectivity to their data, rather than having to provision separate physical circuits or Internet-based VPNs ("virtual private networks") for access to their data. | FALSE | Not applicable. | The primary objectives in quarter 1 are as follows: 1. Complete construction on 85% of link miles that currently have executed leases and do not require lease amendments - this will enable FRBA to meet quarter 1 milestone objectives. 1.a. Remaining pre-construction is being conducted to "stay ahead" of construction and running parallel. 1.b. 2nd quarter is to be used to complete construction and complete items in pre-construction of 1st quarter. 2. Complete data center build-outs that will enable FRBA to put customers in service. This will require Level3 to deliver incremental services in a timely manner and a temporary agreement can be executed with NFBA to purchase wholesale Internet service while FRBA coordinates a RFP for a longer term solution. 3. Establish direct service to at least one beta CAI customer. 4. Continue outreach efforts to secure significant CAI contracts for implementation in quarter 2 and quarter 3. The E-Rate window for schools and libraries is open during quarter 1 and 2 and FRBA will respond to all available E-Rate bids/quotes to secure school and library contracts beginning July 1, 2013. FRBA is also ramping up efforts for outreach to CAIs outside of the schools and libraries, targeting primarily city and county government in the region for services. 5. Continue to identify and negotiate with last-mile providers and other wholesalers in the region. In preparation for network activation, FRBA will actively be recruiting last-mile providers who will be able to provide end-user services throughout the region and interconnect at key POIs in the FRBA service areas and data centers. 6. Budget Relaignment. FRBA is also working through a comprehensive budget realignment project that will be completed during quarter 1 2013 and reported in the next PPR. The budget realignment will incorporate changes in the project budget with documentation of the changes, along with the matching requirement changes, once approved by the NTIA. The match documentation was submitted in mid-December and we are anticipating final approval from the NTIA. 7. FRBA is in the process of procuring a network operator who will manage all network operations for the organization. Procurement will be completed in advance of network commissioning and activation to ensure a smooth hand-over and transition phase. The network operator will be tasked with the following primary responsibilities: -network management and monitoring -field services -provisioning and activations -installations and terminations -billing management -customer service -upgrades and expansions o 1st Quarter 2013 PROJECTED MILES: â€¢ Projected Construction Complete Link Miles: 77 miles â€¢ FRL016-FRL009 = 9 miles â€¢ FRL014-FRL015 = 13 miles â€¢ FRL017-FRL018 = 7 miles â€¢ FRL018-FRL004 = 4 miles â€¢ FRL054-FRL020 = 6 miles â€¢ FRL054-FRL012 = 7 miles â€¢ FRH012-FRH020 = 15 miles â€¢ FRH014-FRH015 = 5 miles â€¢ FRH023-FRH026 = 11 miles â€¢ Projected Sites % Construction Completed: 52% Civil Completed + Some Portion of L&A Completed) â€¢ FRL016 = 67% (Civil + 1 of 2 Links Equipment Installed) â€¢ FRL009 = 100% (Civil + 2 of 2 Links Equipment Installed) â€¢ FRL059 = 95% Civil + 2 of 2 Links Equipment Installed except OCBs) â€¢ FRL011 = 67% (Civil + 1 of 2 Links Equipment Installed) â€¢ FRL015 = 67% (Civil + 1 of 2 Links Equipment Installed) â€¢ FRL014 = 67% (Civil + 1 of 2 Links Equipment Installed) â€¢ FRL012 = 67% (Civil + 1 of 2 Links Equipment Installed) â€¢ FRL020 = 67% (Civil + 1 of 2 Links Equipment Installed) â€¢ FRL017 = 100% (Civil + 2 of 2 Links Equipment Installed) â€¢ FRL018 = 100% (Civil + 2 of 2 Links Equipment Installed) â€¢ FRL004 = 67% (Civil + 1 of 2 Links Equipment Installed) â€¢ FRL019 = 33% (Civil Installed) â€¢ FRL054 = 100% (Civil + 2 of 2 Links Equipment Installed) â€¢ FRL024 = 33% (Civil Installed) â€¢ FRL021 = 33% (Civil Installed) â€¢ FRL013 = 100% (Civil + 2 of 2 Links Equipment Installed) â€¢ FRH014 = 67% (Civil + 1 of 2 Links Equipment Installed) â€¢ FRH015 = 67% (Civil + 1 of 2 Links Equipment Installed) â€¢ FRH012 = 67% (Civil + 1 of 2 Links Equipment Installed) â€¢ FRH020 = 67% (Civil + 1 of 2 Links Equipment Installed) â€¢ FRH026 = 67% (Civil + 1 of 2 Links Equipment Installed) â€¢ FRH023 = 100% (Civil + 2 of 2 Links Equipment Installed) â€¢ FRH001 = 33% (Civil Installed) â€¢ FRH004 = 33% (Civil Installed) â€¢ FRH051 = 33% (Civil Installed) â€¢ FRH035 = 50% (Civil + 2 of 3 Links Equipment Installed) â€¢ FRH043 = 33% (Civil Installed) â€¢ FRH047B = 33% (Civil Installed) â€¢ FRH058 = 33% (Civil Installed) â€¢ FRH049 = 33% (Civil Installed) â€¢ FRH011 = 33% (Civil Installed) o 1st Quarter 2013 PROJECTED CAIs: 0 o 1st Quarter 2013 PROJECTED LAST-MILE/WHOLESALE PROVIDERS: 0, but planning direct connections via license-free microwave to most CAIs o PROJECTED LEASE COMPLETIONS: 87% (59 of 68 sites) o PROJECTED STRUCTURAL COMPLETIONS: 75% (51 of 68 sites) o PROJECTED PERMIT COMPLETIONS: 51% (35 of 68 sites) | Florida Rural Broadband Alliance, LLC | FRBA continued to face several challenges this quarter primarily from the transition of its previous engineering firm to G4S and Inspired Technologies. Once the resources were identified and contracts were established to engage the resources, a significant portion of the quarter was spent generating full deliverable design and engineering that would enable the pre-construction tasks to truly begin. | Meeting the milestones listed above assume that 15% of the link miles that have executed leases and do not require lease amendments or can not be built due to the following risks: - G4S controlled construction schedule slips - Electrical permits can not be secured due to KGP cabinets not yet having NEMA certification - Failed site structurals - Existing equipment can support FCC assigned frequencies in PCNs - A temporary agreement can be reached with NFBA to purchase wholesale Internet connectivity to Level(3) while FRBA initiates a RFP for a longer term solution - Common construction delays; predatory birds, acts of nature... Proactive steps are being taken to minimize the impact of each of these identified risks including: - adding more detailed project management tracking and daily project calls - changing designs to meet available FCC frequencies where viable - Additional resources for construction | TRUE
NT10BIX5570122 | 2013 | Q1 | Q1 - 2013 | a) SITE CONSTRUCTION COMPLETE: The South network moved from <10% to 62% Construction Complete status and the North network moved from <5% to 32% Construction Complete status in 1Q2013. b) COMMERCIAL TOWER CONSTRUCTION: Construction was been materially completed at all commercial sites that did not require lease amendments in 1Q2013. Lease amendments were filed in 1Q2013 with executed agreements expected in May 2013, thus enabling construction to resume at these sites. c) DATA CENTER BUILDOUTS: Construction at the Orlando data center is materially completed. Construction at the Tallahassee data center was on hold until late in 1Q2013 due to a legal matter that prevented IRU re-configuration negotiations to begin; the legal matter was resolved in March and negotiations to re-configure the IRU capacity were initiated. d) QUALITY ASSURANCE/SITE ACCEPTANCE: Quality Assurance testing has been completed at 31% of sites in 1Q2013; the General Contractor is in process of correcting open punch-list items so sites can be formally accepted in 2Q2013. e) NETWORK OPERATOR: An Invitation To Negotiate (ITN) was released for a Network Operator in 1Q2013, resulting in multiple respondents. Negotiations with respondents will continue in 2Q2013, with selection of a Network Operator projected in 3Q2013. f) CUSTOMER OUTREACH: In discussions with 3 potential customers, which may initially start as "beta" customers. | 75 | 1201 | 0 | 0 | 0 | 9 | 0 | 0 | The following links are Construction Complete: FRH023-026, FRH014-015, FRL016-009, FRL014-015, FRL012-013, FRL012-054, FRL054-020, FRL017-018, FRL018-004. | Level3 IRU miles | N/A | N/A | N/A | The following links are Construction Complete: FRH023-026, FRH014-015, FRL016-009, FRL014-015, FRL012-013, FRL012-054, FRL054-020, FRL017-018, FRL018-004. | N/A | N/A | 0 | 1 | 8 | FRBA has not signed any agreements with wholesale or last mile providers during this reporting period. | The FRBA network provides transport, commodity Internet and co-location services to wholesale providers in the region. FRBA's services will allow wholesale providers (LEC's, CLEC's, Broadband Access and Wireless Access) to receive new type 2 middle-mile services across the service area with bandwidths between 5Mbp and 200Mbp. FRBA's wholesale will connect wholesale providers between multiple on-net points within the network or between points within the network and interconnecting data centers located in Orlando, FL and Tallahassee, FL. Data centers provide neutral access with interconnecting carriers utilizing Ethernet-based NNIs (network-to-network interconnections). FRBA also provides commodity Internet access at its data centers for wholesale providers who require transport + IP connections. FRBA also provides dedicated colocation at the Orlando data center for wholesalers needing local presence in this facility. The wholesale pricing plan for dedicated services is attached to this PPR. | FRBA has not yet designated a third party to operate its network. FRBA has released an Invitation to Negotiate ("ITN") that seeks to identify a investing partner that will manage all network and business operations. FRBA is currently in the process of evaluating two potential investing partners as part of this process. Procurement will be completed in advance of network commissioning and activation to ensure a smooth hand-over and transition phase. The investing partner will be tasked with the following primary responsibilities: -business management -sales and marketing -funding, current and future -legal and regulatory -network management and monitoring -field services -provisioning and activations -installations and terminations -billing management -customer service -upgrades and expansions | 0 | 0 | 0 | 0 | FRBA is currently in discussions with several wholesalers for purchase of capacity on the FRBA network. | FRBA is currently in discussions with several wholesalers for purchase of capacity on the FRBA network. | FRBA does not provide dark fiber services. | Speed tiers will begin at 5Mbp and scale to 200Mbp and greater in special cases. FRBA will have the capability to provide gigabit speeds on an individual case basis. | 0 | 0 | 0 | 0 | Previous reports identified 34 CAIs served by the project. These 34 CAIs were served through the Hardee County network which is no longer considered part of the project. As a result of this change, we are reporting an adjustment from 34 CAIs to 0 CAIs. Additional CAIs have been identified to be served through FRBA, as reported in the 2012 APR Template, making up the loss of the 34 CAIs. | 34 CAIs were served through the Hardee County network which is no longer considered part of the project. As a result of this change, we are reporting an adjustment from 34 CAIs to 0 CAIs. Additional CAIs have been identified to be served through FRBA, as reported in the 2012 APR Template, making up the loss of the 34 CAIs. | 34 CAIs were served through the Hardee County network which is no longer considered part of the project. As a result of this change, we are reporting an adjustment from 34 CAIs to 0 CAIs. Additional CAIs have been identified to be served through FRBA, as reported in the 2012 APR Template, making up the loss of the 34 CAIs. | 34 CAIs were served through the Hardee County network which is no longer considered part of the project. As a result of this change, we are reporting an adjustment from 34 CAIs to 0 CAIs. Additional CAIs have been identified to be served through FRBA, as reported in the 2012 APR Template, making up the loss of the 34 CAIs. Speed tiers will begin at 5Mbp and scale to 200Mbp and greater in special cases. FRBA will have the capability to provide gigabit speeds on an individual case basis. | 0 | 0 | 0 | 0 | 0 | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | 0 | 0 | 0 | 0 | 0 | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | FRBA will have built-in capabilities to provide on-net services between community anchors throughout the region. This will allow for collaboration and interconnection between separate CAI organizations that need to share data between one another. FRBA will also have the capabilities to offer colocation and data center space to CAIs requiring secure data backup facilities. CAIs will have layer 2 access to such facilities across the FRBA network, enabling them to maintain direct on-net connectivity to their data, rather than having to provision separate physical circuits or Internet-based VPNs ("virtual private networks") for access to their data. | FALSE | N/A | a) SITE CONSTRUCTION COMPLETE: The South network should move from 62% to ~90% Construction Complete status and the North network should move from 32% to ~80% Construction Complete status in 2Q2013. b) COMMERCIAL TOWER CONSTRUCTION: Lease amendments at commercial sites are expected to be received no later than May 31, 2013 and new/revised permits secured by the end of 2Q2013, thus enabling construction to resume in 3Q2013. c) DATA CENTER BUILDOUTS: In 2Q2013 FRBA will: (1) secure agreement to re-configure IRU capacity, OR (2) purchase incremental services from IRU vendor to enable construction of data centers to be completed in 3Q2013. d) QUALITY ASSURANCE/SITE ACCEPTANCE: Quality Assurance testing is projected to be completed at 57% of sites in 2Q2013 (this is aligned to planned project schedule). FRBA and General Contractor have agreed that there are aligned interests in punch-list items being corrected in a more timely manner moving forward. e) NETWORK OPERATOR: Negotiations and due diligence efforts with respondents will continue throughout 2Q2013 per the schedule published in the Intent to Negotiate, with an awarded contract for a Network Operator projected in 3Q2013. f) CUSTOMER OUTREACH: Establish direct service to at least 2 beta customers. Outreach to required and non-required CAI's will begin. Limited campaigns will occur with the intent to secure required CAI's as presented in the grant. Possible outreach activities could begin with influence from the selected Network Operator as part of the solicited role from the Network Operator encompasses Marketing and Outreach. Continue to work with last-mile providers, primarily wireless INTERNET providers, in the region to establish service needs and timing coinciding with construction completion. g) NUMBER OF MILES DEPLOYED: By the end of 2Q2013 there will be approximately 170 network miles deployed. There are sites completed that are not attributing to these miles (deployed) because the upstream/downstream site has not yet been completed; Completion of those sites will exponentially increase the realized deployed miles in 3Q2013. h) NUMBER OF CIA'S CONNECTED: By the end of 2Q2013, there should be one CAI connected, pending the customer's tower passes a required structural analysis. i) NUMBER OF BROADBAND WHOLESALE/LAST MILE PROVIDER AGREEMENTS SIGNED: One broadband wholesale/last mile provider agreement is under negotiation now, but the execution of this agreement may not occur until July. | Florida Rural Broadband Alliance, LLC | There were two core challenges that affected progress in 1Q2013: a) OVERALL SITE CONSTRUCTION SCHEDULE: The sub-contractor hired by the projects General Contractor to do construction on sites in the North, left the project in 1Q2013. The General Contractor has brought in a new sub-contractor to do this work starting in April. Two risks exist with this transition: (1) new permits are required in the new sub-contractors name, and (2) a "cleanse" of sites partially completed by the first sub-contractor that now must be finished with the second sub-contractor is required. The General Contractor is also working to bring on a second sub-subcontractor to make-up time lost associated with this transition and accelerate the current project deployment schedule. b) DATA CENTER BUILDOUTS: The build-outs of the Orlando and Tallahassee data centers can not be completed without negotiating the re-configuration of the IRU capacity. These negotiations were on-hold for most of 1Q2013 due to legal matters, but were resolved in March. The risk associated with negotiation of the re-configuration of the IRU capacity is that the IRU vendor will not entertain such negotiations, which would require FRBA to purchase incremental services from this vendor instead of re-configuring existing IRU capacity. Until this is resolved, FRBA is able to offer limited service to CAIs. | a) OVERALL SITE CONSTRUCTION SCHEDULE: The ability to meet the projected deployment schedule in 2Q2013 is dependent on: (1) the successful transition of sub-contractor work in the North, and (2) lease amendments being executed in May. As of this date, we see risk in the General Contractor managing the transition of work to the new sub-contractor, which could jeopardize the 2Q13 deployment schedule. FRBA will continue to work with the General Contractor to mitigate these risks on the project. | TRUE
NT10BIX5570122 | 2013 | Q2 | Q2 - 2013 | a) SITE CONSTRUCTION COMPLETE: The South network moved from 43% to 64% Construction Complete status and the North network moved from 32% to 41% Construction Complete status in 2Q2013. b) COMMERCIAL TOWER CONSTRUCTION: Construction has been materially completed at all commercial sites that did not require lease amendments in 2Q2013. Lease amendments continued to be filed in 2Q2013 with executed agreements continually being received, thus enabling construction to resume at these sites. c) DATA CENTER BUILDOUTS: Construction at the Orlando data center is materially complete. Construction at the Tallahassee data center is on hold until mid to late 3Q2013 pending IRU re-configuration negotiations to begin; negotiations to re-configure the IRU capacity were initiated but continued negotiations have delayed a final verdict on the IRU modification. d) QUALITY ASSURANCE/SITE ACCEPTANCE: Quality Assurance testing has been completed at 52% of sites in 2Q2013; the General Contractor is in process of correcting open punch-list items so sites can be formally accepted in 3Q2013. e) NETWORK OPERATOR: An Invitation To Negotiate (ITN) was released for a Network Operator in 1Q2013, resulting in multiple respondents. Selection of the Network Operator and a signed Letter of Intent occurred during 2Q2013. Final stages of due diligence are being performed; with a definitive agreement targeted in early 3Q2013. f) CUSTOMER OUTREACH: FRBA is in discussions with potential customers, which may initially start as "beta" customers. FRBA is also negotiating rates and service locations with the first Last Mile provider. g) BUDGET REALIGNMENT: FRBA has also submitted a budget realignment which realigns the costs more accurately to the project. Percentage completes in this PPR may be somewhat skewed because percentages are based on the original project budget, which has since changed, as documented in the budget realignment. FRBA has submitted the budget realignment to the NTIA for approval | 169 | 1201 | 0 | 0 | 0 | 17 | 0 | 0 | The following links are Construction Complete: FRH035 - FRH001, FRH001 - FRH051, FRH051 - FRH004, FRH004 - FRH012, FRH023 - FRH026, FRH051 - FRH057, FRH015 - FRH021, FRL016 - FRL009, FRL009 - FRL059, FRL059 - FRL011, FRL015 - FRL014, FRL013 - FRL012, FRL012 - FRL054, FRL054 - FRL020, FRL024 - FRL019, FRL017 - FRL018, FRL018 - FRL004 | Level3 IRU miles | N/A | N/A | N/A | The following links are Construction Complete: FRH035 - FRH001, FRH001 - FRH051, FRH051 - FRH004, FRH004 - FRH012, FRH023 - FRH026, FRH051 - FRH057, FRH015 - FRH021, FRL016 - FRL009, FRL009 - FRL059, FRL059 - FRL011, FRL015 - FRL014, FRL013 - FRL012, FRL012 - FRL054, FRL054 - FRL020, FRL024 - FRL019, FRL017 - FRL018, FRL018 - FRL004 | N/A | N/A | 0 | 2 | 0 | FRBA has not signed any agreements with wholesale or last mile providers during this reporting period. FRB is currently negotiating two agreement with last mile/wholesale providers in the region. | The FRBA network provides transport, commodity Internet and co-location services to wholesale providers in the region. FRBA's services will allow wholesale providers (LEC's, CLEC's, Broadband Access and Wireless Access) to receive new type 2 middle-mile services across the service area with bandwidths between 5Mbp and 200Mbp. FRBA's wholesale will connect wholesale providers between multiple on-net points within the network or between points within the network and interconnecting data centers located in Orlando, FL and Tallahassee, FL. Data centers provide neutral access with interconnecting carriers utilizing Ethernet-based NNIs (network-to-network interconnections). FRBA also provides commodity Internet access at its data centers for wholesale providers who require transport + IP connections. FRBA also provides dedicated colocation at the Orlando data center for wholesalers needing local presence in this facility. The wholesale pricing plan for dedicated services is attached to this PPR. | FRBA has not yet designated a third party to operate its network. FRBA has released an Invitation to Negotiate ("ITN") that seeks to identify a investing partner that will manage all network and business operations. FRBA is currently in due diligence with the selected investing partner with the intent of solidifying a definitive agreement with the partner as soon as possible. It is FRBA's intent to complete this definitive agreement prior to completion of the network and in advance of network commissioning and activation to ensure a smooth hand-over and transition phase. The investing partner will be tasked with the following primary responsibilities: -business management -sales and marketing -funding, current and future -legal and regulatory -network management and monitoring -field services -provisioning and activations -installations and terminations -billing management -customer service -upgrades and expansions | 0 | 0 | 0 | 0 | FRBA is currently in discussions with several wholesalers for purchase of capacity on the FRBA network. | FRBA is currently in discussions with several wholesalers for purchase of capacity on the FRBA network. | FRBA does not provide dark fiber services. | Speed tiers will begin at 5Mbp and scale to 200Mbp and greater in special cases. FRBA will have the capability to provide gigabit speeds on an individual case basis. | 0 | 0 | 0 | 0 | Previous reports identified 34 CAIs served by the project. These 34 CAIs were served through the Hardee County network which is no longer considered part of the project. As a result of this change, we are reporting an adjustment from 34 CAIs to 0 CAIs. Additional CAIs have been identified to be served through FRBA, as reported in the 2012 APR Template, making up the loss of the 34 CAIs. | 34 CAIs were served through the Hardee County network which is no longer considered part of the project. As a result of this change, we are reporting an adjustment from 34 CAIs to 0 CAIs. Additional CAIs have been identified to be served through FRBA, as reported in the 2012 APR Template, making up the loss of the 34 CAIs. | 34 CAIs were served through the Hardee County network which is no longer considered part of the project. As a result of this change, we are reporting an adjustment from 34 CAIs to 0 CAIs. Additional CAIs have been identified to be served through FRBA, as reported in the 2012 APR Template, making up the loss of the 34 CAIs. | 34 CAIs were served through the Hardee County network which is no longer considered part of the project. As a result of this change, we are reporting an adjustment from 34 CAIs to 0 CAIs. Additional CAIs have been identified to be served through FRBA, as reported in the 2012 APR Template, making up the loss of the 34 CAIs. Speed tiers will begin at 5Mbp and scale to 200Mbp and greater in special cases. FRBA will have the capability to provide gigabit speeds on an individual case basis. | 0 | 0 | 0 | 0 | 0 | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | 0 | 0 | 0 | 0 | 0 | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | FRBA will have built-in capabilities to provide on-net services between community anchors throughout the region. This will allow for collaboration and interconnection between separate CAI organizations that need to share data between one another. FRBA will also have the capabilities to offer colocation and data center space to CAIs requiring secure data backup facilities. CAIs will have layer 2 access to such facilities across the FRBA network, enabling them to maintain direct on-net connectivity to their data, rather than having to provision separate physical circuits or Internet-based VPNs ("virtual private networks") for access to their data. | FALSE | N/A | a) SITE CONSTRUCTION COMPLETE: The South network should move from 64% to ~90% Construction Complete status and the North network should move from 41% to ~85% Construction Complete status in 3Q2013. Approximately 440 miles of network will be completed based on an average link distance of 11 miles. b) COMMERCIAL TOWER CONSTRUCTION: Lease amendments at commercial sites have all been received with exception of (4) and new/revised permits secured by the mid 3Q2013, thus enabling construction to substantially complete by end of 3Q2013. c) DATA CENTER BUILDOUTS: In 3Q2013 FRBA will either: (1) secure agreement to re-configure IRU capacity, OR (2) purchase incremental services from IRU vendor to enable construction of data centers to be completed in 3Q2013. d) QUALITY ASSURANCE/SITE ACCEPTANCE: Quality Assurance testing is projected to be completed at ~85-90% of sites in 3Q2013 (this is aligned to planned project schedule). FRBA and General Contractor have agreed that there are aligned interests in punch-list items being corrected in a more timely manner moving forward. e) NETWORK OPERATOR: Negotiations and due diligence efforts with operator will continue into 3Q2013 per the schedule published in the Intent to Negotiate, with a definitive agreement to be reached early in 3Q2013. f) CUSTOMER OUTREACH: Establish direct service to at least 2 CAIs in Q3 2013 as beta customers. Outreach to required and non-required CAI's will begin. Limited campaigns will occur with the intent to secure required CAI's as presented in the grant. Possible outreach activities could begin with influence from the selected Network Operator as part of the solicited role from the Network Operator encompasses Marketing and Outreach. Continue to work with last-mile providers, primarily wireless Internet providers, in the region to establish service needs and timing coinciding with construction completion. g) Wholesale Agreements: FRBA is currently negotiating one last-mile provider agreement and anticipates to have this completed in Q3 of 2013. In addition, through FRBA's network operator/partner agreement with Affiniti, additional last-mile providers will be identified through their channels to provide broadband into the FRBA service area. | Florida Rural Broadband Alliance, LLC | There were two core challenges that affected progress in 2Q2013: a) OVERALL SITE CONSTRUCTION SCHEDULE: The General Contractor has brought in additional sub-contractors to do this work in 2Q2013. Two risks exist with this transition: (1) new permits are required in the new sub-contractors name, and (2) a "cleanse" of sites partially completed by the first sub-contractor that now must be finished with the second sub-contractor is required. As of this date, the transition of this work is going well. b) DATA CENTER BUILDOUTS: The build-outs of the Orlando and Tallahassee data centers can not be completed without negotiating the re-configuration of the IRU capacity. The risk associated with the re-configuration of the IRU capacity is that the IRU vendor will not entertain such negotiations, which would require FRBA to purchase incremental services from this vendor instead of re-configuring existing IRU capacity. Until this is resolved, FRBA is able to offer limited service to CAIs. c) CERAGON OCB DELIVERY: As lease amendments are completed, PCN's are being filed and then Ceragon OCB's can be ordered in support of the PCN frequency specifications. The lead time for Ceragon OCB's can be upto 8 weeks. FRBA is working with Ceragon to determine what steps can be taken to reduce these delivery intervals. | a) OVERALL SITE CONSTRUCTION SCHEDULE: Project deployment is estimated to continue its positive trend through to substantial completion in 3Q2013. With the exception of 3 outstanding leases, the potential to substantially complete the network build in 3Q2013 exists. The exception sites may carry forward to the very beginning of 4Q2013. Fortunately, these exception sites are spur locations that are not specifically impacting to the overall core network design. With the anticipated on-boarding of the operator occurring during 3Q2013, we will experience a transition process toward the end of 3Q2013 that may trickle into 4Q2013. Although the transition should start prior to the first commercial customers coming on-board, and delays to that transition represents potential customer facing challenges, we are being proactive in our approach on network operations to reduce, if not eliminate, any noticeable impact to potential customers. | TRUE
NT10BIX5570122 | 2013 | Q3 | Q3 - 2013 | a) SITE CONSTRUCTION COMPLETE: The South network moved from 64% to 96% Construction Complete status and the North network moved from 41% to 95% Construction Complete status in 3Q2013. b) COMMERCIAL TOWER CONSTRUCTION: Construction has been materially completed at all commercial sites that did not require lease amendments in 3Q2013. The last tower lease in the network is being finalized with the State of Florida Law Enforcement Network managed by Harris Corp. Construction for the last remaining sites have been scheduled and are proceeding with permitting. c) DATA CENTER BUILDOUTS: Construction at the Orlando and Tallahassee data centers is materially complete. Both Data-centers have been configured and engineered to accept and process core traffic destined for on-net facilities or the Public Internet. The Wireless millimeter wave link from FRH-022 to the Level 3 Tallahassee Data-center is being scheduled for final installation now that Core site construction has been completed. This link will provide an additional (1Gb) link for core network offloading in the FRBA North network. d) QUALITY ASSURANCE/SITE ACCEPTANCE: Quality Assurance testing has been completed at 85% of sites in 3Q2013; the General Contractor is in process of correcting open punch-list items so sites can be formally accepted in 4Q2013. e) NETWORK OPERATOR: An Invitation To Negotiate (ITN) was released for a Network Operator in 1Q2013, resulting in multiple respondents. Selection of the Network Operator and a signed Letter of Intent occurred during 2Q2013. Final stages of due diligence are being performed; with a definitive agreement targeted in early 4Q2013. f) CUSTOMER OUTREACH: FRBA is in discussions with potential customers, which may initially start as "beta" customers. FRBA's network operator has begun a joint customer outreach effort with FRBA. Customer proposals are being generated currently and service expectations are being defined. FRBA is continuing discussions with last-mile providers in the region to purchase wholesale capacity into the region to serve local markets. g) BUDGET REALIGNMENT: FRBA has also submitted a budget realignment which realigns the costs more accurately to the project. FRBA has submitted the budget realignment to NTIA which has received approval. h) PROGRAM INCOME: After cost of service review, FRBA has determined that it did not actually earn program income as reported in previous project performance quarters since the cost of service is greater that the income derived. | 601 | 1201 | 0 | 0 | 0 | 58 | 0 | 0 | The following links are Construction Complete: FRH063 - FRH016, FRH016 - FRH008, FRH016 - FRH059B FRH035 - FRH001, FRH001 - FRH05, FRH051 - FRH004 FRH004 - FRH012, FRH012 - FRH020, FRH020 - FRH059B FRH059B - FRH032, FRH032 - FRH022, FRH035 - FRH043 FRH001 - FRH047B, FRH047B - FRH006, FRH047B - FRH062 FRH046 - FRH006, FRH006 - FRH042, FRH042 - FRH040 FRH040 - FRH009B, FRH011 - FRH009B, FRH009B - FRH005B, FRH005B - FRH049, FRH049 - FRH058 FRH058 - FRH033, FRH033 - FRH023, FRH023 - FRH026 FRH026 - FRH041, FRH041 - FRH018, FRH018 - FRH051 FRH051 - FRH057, FRH057 - FRH057ILA, FRH051 - FRH039 FRH039 - FRH024, FRH024 - FRH019, FRH019 - FRH002 FRH019 - FRH014, FRH014 - FRH015, FRH015 - FRH021 FRH021 - FRH027, FRH027 - FRH036, FRH036 - FRH022 FRL016ILA - FRL016, FRL016 - FRL009, FRL009 - FRL059 FRL059 - FRL011, FRL011 - FRL023, FRL023 - FRL008 FRL023 - FRL024, FRL024 - FRL005, FRL005 - FRL063 FRL063 - FRL016, FRL063 - FRL064, FRL063 - FRL022 FRL022 - FRL015, FRL015 - FRL014, FRL014 - FRL013 FRL013 - FRL012, FRL012 - FRL054, FRL054 - FRL020 FRL020 - FRL006, FRL006 - FRL021, FRL021 - FRL005 FRL024 - FRL019, FRL017 - FRL018, FRL018 - FRL004 FRL004 - FRL052, FRL052 - FRL019 | Level 3 IRU Miles | N/A | N/A | N/A | The following links are Construction Complete: FRH063 - FRH016, FRH016 - FRH008, FRH016 - FRH059B FRH035 - FRH001, FRH001 - FRH05, FRH051 - FRH004 FRH004 - FRH012, FRH012 - FRH020, FRH020 - FRH059B FRH059B - FRH032, FRH032 - FRH022, FRH035 - FRH043 FRH001 - FRH047B, FRH047B - FRH006, FRH047B - FRH062 FRH046 - FRH006, FRH006 - FRH042, FRH042 - FRH040 FRH040 - FRH009B, FRH011 - FRH009B, FRH009B - FRH005B, FRH005B - FRH049, FRH049 - FRH058 FRH058 - FRH033, FRH033 - FRH023, FRH023 - FRH026 FRH026 - FRH041, FRH041 - FRH018, FRH018 - FRH051 FRH051 - FRH057, FRH057 - FRH057ILA, FRH051 - FRH039 FRH039 - FRH024, FRH024 - FRH019, FRH019 - FRH002 FRH019 - FRH014, FRH014 - FRH015, FRH015 - FRH021 FRH021 - FRH027, FRH027 - FRH036, FRH036 - FRH022 FRL016ILA - FRL016, FRL016 - FRL009, FRL009 - FRL059 FRL059 - FRL011, FRL011 - FRL023, FRL023 - FRL008 FRL023 - FRL024, FRL024 - FRL005, FRL005 - FRL063 FRL063 - FRL016, FRL063 - FRL064, FRL063 - FRL022 FRL022 - FRL015, FRL015 - FRL014, FRL014 - FRL013 FRL013 - FRL012, FRL012 - FRL054, FRL054 - FRL020 FRL020 - FRL006, FRL006 - FRL021, FRL021 - FRL005 FRL024 - FRL019, FRL017 - FRL018, FRL018 - FRL004 FRL004 - FRL052, FRL052 - FRL019 | N/A | N/A | 0 | 0 | 0 | FRBA has not signed any agreements with wholesale or last mile providers during this reporting period. FRBA is currently finalizing its definitive agreement with its Network Operator which has experience in both self performing last mile installations and brings existing last mile strategic partnerships in which FRBA anticipates will be able to utilize this middle-mile network. | The FRBA network provides transport, commodity Internet and co-location services to wholesale providers in the region. FRBA's services will allow wholesale providers (LEC's, CLEC's, Broadband Access and Wireless Access) to receive new type 2 middle-mile services across the service area with bandwidths between 5Mbp and 200Mbp. FRBA's wholesale will connect wholesale providers between multiple on-net points within the network or between points within the network and interconnecting data centers located in Orlando, FL and Tallahassee, FL. Data centers provide neutral access with interconnecting carriers utilizing Ethernet-based NNIs (network-to-network interconnections). FRBA also provides commodity Internet access at its data centers for wholesale providers who require transport + IP connections. FRBA also provides dedicated colocation at the Orlando data center for wholesalers needing local presence in this facility. The wholesale pricing plan for dedicated services is attached to this PPR. | FRBA has selected Affiniti, Inc to be the operator of the entire network. The definitive agreement is estimated to be completed during the month of November 2013. Contact information for Affiniti, Inc follows: Bob Roland, Chief Operating Officer, Affiniti, bobr@stingcom.com | 0 | 0 | 0 | 0 | FRBA is currently in discussions with several wholesalers for purchase of capacity on the FRBA network. | FRBA is currently in discussions with several wholesalers for purchase of capacity on the FRBA network. | FRBA does not provide dark fiber services. | Speed tiers will begin at 5Mbp and scale to 200Mbp and greater in special cases. FRBA will have the capability to provide gigabit speeds on an individual case basis. | 0 | 0 | 0 | 0 | Previous reports identified 34 CAIs served by the project. These 34 CAIs were served through the Hardee County network which is no longer considered part of the project. As a result of this change, we are reporting an adjustment from 34 CAIs to 0 CAIs. Additional CAIs have been identified to be served through FRBA, as reported in the 2012 APR Template, making up the loss of the 34 CAIs. | Previous reports identified 34 CAIs served by the project. These 34 CAIs were served through the Hardee County network which is no longer considered part of the project. As a result of this change, we are reporting an adjustment from 34 CAIs to 0 CAIs. Additional CAIs have been identified to be served through FRBA, as reported in the 2012 APR Template, making up the loss of the 34 CAIs. | Previous reports identified 34 CAIs served by the project. These 34 CAIs were served through the Hardee County network which is no longer considered part of the project. As a result of this change, we are reporting an adjustment from 34 CAIs to 0 CAIs. Additional CAIs have been identified to be served through FRBA, as reported in the 2012 APR Template, making up the loss of the 34 CAIs. | Previous reports identified 34 CAIs served by the project. These 34 CAIs were served through the Hardee County network which is no longer considered part of the project. As a result of this change, we are reporting an adjustment from 34 CAIs to 0 CAIs. Additional CAIs have been identified to be served through FRBA, as reported in the 2012 APR Template, making up the loss of the 34 CAIs. Speed tiers will begin at 5Mbp and scale to 200Mbp and greater in special cases. FRBA will have the capability to provide gigabit speeds on an individual case basis. | 0 | 0 | 0 | 0 | 0 | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | 0 | 0 | 0 | 0 | 0 | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | FRBA will have built-in capabilities to provide on-net services between community anchors throughout the region. This will allow for collaboration and interconnection between separate CAI organizations that need to share data between one another. FRBA will also have the capabilities to offer colocation and data center space to CAIs requiring secure data backup facilities. CAIs will have layer 2 access to such facilities across the FRBA network, enabling them to maintain direct on-net connectivity to their data, rather than having to provision separate physical circuits or Internet-based VPNs ("virtual private networks") for access to their data. | FALSE | N/A | a) SITE CONSTRUCTION COMPLETE: The South network should move from 96% to 100% Construction Complete status and the North network should move from 95% to 100% Construction Complete status in 4Q2013. Approximately 139 miles of network will be completed early in 4Q2013. b) COMMERCIAL TOWER CONSTRUCTION: Lease/Lease Amendments at commercial sites have all been received and all sites are scheduled for construction completion in 4Q2013. c) DATA CENTER BUILDOUTS: Data Center Buildout has been materially complete. In the Tallahassee Level 3 Data Center, an additional wireless 1GB link will be provided directly from FRH-022 to the Data Center. The link will be completed early in 4Q2013 and will constitute the completion of the Data Center buildouts. FRBA and the Network Operator will continue to pursue IRU Modifications with Level 3 in attempt to reconfigure space, power, and fiber allocations to better fit the needs of the entire network. This modification request does not hinder the capability for FRBA to provide service to end customers. d) QUALITY ASSURANCE/SITE ACCEPTANCE: Quality Assurance testing is projected to be completed at 100% of sites in 4Q2013. e) NETWORK OPERATOR: Negotiations of definitive agreement with operator will continue into 4Q2013. f) CUSTOMER OUTREACH: Establish direct service to as many CAI's as possible through unified outreach of FRBA and Network Operator. Outreach to required and non-required CAI's has begun. Limited campaigns will occur with the intent to secure required CAI's as presented in the grant. Continue to identify last-mile providers, primarily wireless Internet providers, in the region to establish service needs and timing coinciding with construction completion. FRBA expects to have made connection to at least 15 CAIs by the end of the next quarter, installed as the network is completed. g) Wholesale Agreements: Through FRBA's network operator/partner agreement with Affiniti, additional last-mile providers will be identified through their channels to provide broadband into the FRBA service area. FRBA anticipates at least 1 contract with a broadband wholesaler/last mile provider by the end of the next quarter. | Florida Rural Broadband Alliance, LLC | a) OVERALL SITE CONSTRUCTION SCHEDULE: Project deployment is estimated to continue its positive trend through to completion in 4Q2013. Some delayed leases caused a couple of sites to push into 4Q2013, but those lease delays have been rectified. Fortunately, these exception sites are spur locations that are not specifically impacting to the overall core network design. With the anticipated on-boarding of the operator occurring during 4Q2013, we will experience a transition process during the quarter. Site construction will be substantially complete early in 4Q2013 and the network projects majority of the network to be serviceable to customers in November 2013. | Through the extension of the the BTOP Grant, FRBA expects to complete all applicable project milestones 2a-2k. | TRUE
NT10BIX5570122 | 2013 | Q4 | Q4 - 2013 | a) SITE CONSTRUCTION COMPLETE: The South network remained at 96% Construction Complete status and the North network moved from 95% to 97% Construction Complete status in 4Q2013. b) COMMERCIAL TOWER CONSTRUCTION: Construction has been materially completed at all sites that did not require lease execution or amendments in 4Q2013. The last tower lease in the network is being finalized with the State of Florida Law Enforcement Network managed by Harris Corp. Construction for the last remaining sites are tentatively being scheduled or pending waiting on approved Route Modification from the NTIA. c) DATA CENTER BUILDOUTS: Construction at the Orlando and Tallahassee data centers is materially complete. Both Data-centers have been configured and engineered to accept and process core traffic destined for on-net facilities or the Public Internet. The Wireless millimeter wave link from FRH-022 to the Level 3 Tallahassee Data-center is being scheduled for final installation now that Core site construction has been completed. This link will provide an additional (1Gb) link for core network offloading in the FRBA North network. At the conclusion of 4Q2013 all millimeter wave equipment has been procured and we only await an Notice to Proceed(NTP) from Level 3. d) QUALITY ASSURANCE/SITE ACCEPTANCE: Quality Assurance testing has been completed at 96% of sites in 4Q2013; Punch-list items have been repaired for QA Completed sites and subsequently have been accepted per FRBA acceptance standards. e) NETWORK OPERATOR: An Invitation To Negotiate (ITN) was released for a Network Operator in 1Q2013, resulting in multiple respondents. Selection of the Network Operator and a signed Letter of Intent occurred during 2Q2013. Final stages of due diligence are being performed; with a definitive agreement targeted in early 1Q2014. It should be noted that a Definitive Agreement seems eminent and only minor details are being finalized for agreement approval and execution. f) CUSTOMER OUTREACH: FRBA is in discussions with potential customers, which may initially start as "beta" customers. FRBA's network operator has begun a joint customer outreach effort with FRBA. Customer proposals are being generated currently and service expectations are being defined. FRBA is continuing discussions with last-mile providers in the region to purchase wholesale capacity into the region to serve local markets. g) BUDGET REALIGNMENT: FRBA has also submitted a budget realignment which realigns the costs more accurately to the project. FRBA has submitted the budget realignment to NTIA which has received approval. | 617 | 1201 | 0 | 0 | 0 | 60 | 0 | 0 | The following links are Construction Complete: FRH022 - FRH022ILA, FRH063 - FRH016, FRH016 - FRH008 FRH016 - FRH020, FRH035 - FRH001, FRH001 - FRH051 FRH051 - FRH004, FRH004 - FRH012, FRH012 - FRH020 FRH020 - FRH059B, FRH059B - FRH032, FRH032 - FRH022 FRH035 - FRH043, FRH001 - FRH047B, FRH047B - FRH006 FRH046 - FRH006, FRH006 - FRH042, FRH042 - FRH040 FRH040 - FRH009B, FRH011 - FRH009B, FRH009B - FRH005B, FRH005B - FRH049, FRH049 - FRH058 FRH058 - FRH033, FRH033 - FRH023, FRH023 - FRH026 FRH026 - FRH041, FRH041 - FRH018, FRH018 - FRH051 FRH051 - FRH057, FRH057 - FRH057ILA, FRH051 - FRH039, FRH024 - FRH019, FRH019 - FRH002, FRH019 - FRH014 FRH014 - FRH015, FRH015 - FRH021, FRH021 - FRH027 FRH027 - FRH036, FRH036 - FRH022, FRL016ILA - FRL016 FRL016 - FRL009, FRL009 - FRL059, FRL059 - FRL011 FRL011 - FRL023, FRL023 - FRL008, FRL023 - FRL024 FRL024 - FRL005, FRL022 - FRL015, FRL015 - FRL014, FRL014 - FRL013, FRL013 - FRL012, FRL012 - FRL054, FRL054 - FRL020, FRL020 - FRL006, FRL006 - FRL021, FRL021 - FRL005, FRL024 - FRL019, FRL017 - FRL018, FRL018 - FRL004, FRL004 - FRL052, FRL052 - FRL019 | Level 3 IRU Miles | N/A | N/A | N/A | The following links are Construction Complete: FRH022 - FRH022ILA, FRH063 - FRH016, FRH016 - FRH008 FRH016 - FRH020, FRH035 - FRH001, FRH001 - FRH051 FRH051 - FRH004, FRH004 - FRH012, FRH012 - FRH020, FRH032 - FRH022 FRH035 - FRH043, FRH001 - FRH047B, FRH047B - FRH006 FRH046 - FRH006, FRH006 - FRH042, FRH042 - FRH040 FRH040 - FRH009B, FRH011 - FRH009B, FRH009B - FRH005B, FRH005B - FRH049, FRH049 - FRH058 FRH058 - FRH033, FRH033 - FRH023, FRH023 - FRH026 FRH026 - FRH041, FRH041 - FRH018, FRH018 - FRH051 FRH051 - FRH057, FRH057 - FRH057ILA, FRH051 - FRH039, FRH024 - FRH019, FRH019 - FRH002 FRH002 - FRH013, FRH013 - FRH053B, FRH019 - FRH014 FRH014 - FRH015, FRH015 - FRH021, FRH021 - FRH027 FRH027 - FRH036, FRH036 - FRH022, FRL016ILA - FRL016 FRL016 - FRL009, FRL009 - FRL059, FRL059 - FRL011 FRL011 - FRL023, FRL023 - FRL008, FRL023 - FRL024 FRL024 - FRL005, FRL022 - FRL015 FRL015 - FRL014, FRL014 - FRL013, FRL013 - FRL012 FRL012 - FRL054, FRL054 - FRL020, FRL020 - FRL006 FRL006 - FRL021, FRL021 - FRL005, FRL024 - FRL019 FRL017 - FRL018, FRL018 - FRL004, FRL004 - FRL052 FRL052 - FRL019 | N/A | N/A | 0 | 0 | 0 | FRBA has not signed any agreements with wholesale or last mile providers during this reporting period. FRBA is currently finalizing its definitive agreement with its Network Operator which has experience in both self performing last mile installations and brings existing last mile strategic partnerships in which FRBA anticipates will be able to utilize this middle-mile network. | The FRBA network provides transport, commodity Internet and co-location services to wholesale providers in the region. FRBA's services will allow wholesale providers (LEC's, CLEC's, Broadband Access and Wireless Access) to receive new type 2 middle-mile services across the service area with bandwidths between 5Mbp and 200Mbp. FRBA's wholesale will connect wholesale providers between multiple on-net points within the network or between points within the network and interconnecting data centers located in Orlando, FL and Tallahassee, FL. Data centers provide neutral access with interconnecting carriers utilizing Ethernet-based NNIs (network-to-network interconnections). FRBA also provides commodity Internet access at its data centers for wholesale providers who require transport + IP connections. FRBA also provides dedicated colocation at the Orlando data center for wholesalers needing local presence in this facility. | FRBA has selected Affiniti, Inc to be the operator of the entire network. The definitive agreement is estimated to be completed during the month of January 2014. Contact information for Affiniti, Inc follows: Bob Roland, Chief Operating Officer, Affiniti, bobr@stingcom.com | 0 | 0 | 0 | 0 | FRBA is currently in discussions with several wholesalers for purchase of capacity on the FRBA network. | FRBA is currently in discussions with several wholesalers for purchase of capacity on the FRBA network. | FRBA does not provide dark fiber services. | Speed tiers will begin at 5Mbp and scale to 200Mbp and greater in special cases. FRBA will have the capability to provide gigabit speeds on an individual case basis. | 3 | 0 | 3 | 3 | Previous reports identified 34 CAIs served by the project. These 34 CAIs were served through the Hardee County network which is no longer considered part of the project. As a result of this change, we are reporting an adjustment from 34 CAIs to 0 CAIs. Additional CAIs have been identified to be served through FRBA, as reported in the 2012 APR Template, making up the loss of the 34 CAIs. 3 CAI have been added as of the end 4Q2013. | N/A | N/A | Each subscriber is capable of receiving 10-50Mbs. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | Not applicable. FRBA is a middle-mile network only. Last-mile providers will access last-mile service areas through FRBA's middle-mile network. | FRBA will have built-in capabilities to provide on-net services between community anchors throughout the region. This will allow for collaboration and interconnection between separate CAI organizations that need to share data between one another. FRBA will also have the capabilities to offer colocation and data center space to CAIs requiring secure data backup facilities. CAIs will have layer 2 access to such facilities across the FRBA network, enabling them to maintain direct on-net connectivity to their data, rather than having to provision separate physical circuits or Internet-based VPNs ("virtual private networks") for access to their data. | FALSE | N/A | a) SITE CONSTRUCTION COMPLETE: The South network should move from 96% to 100% Construction Complete status and the North network should move from 97% to 100% Construction Complete status in 1Q2014. Approximately 96 miles of network will be completed early in 1Q2014. b) COMMERCIAL TOWER CONSTRUCTION: Lease/Lease Amendments at commercial sites have all been received and all sites are scheduled for construction completion in 1Q2014. c) DATA CENTER BUILDOUTS: Data Center Buildout has been materially complete. In the Tallahassee Level 3 Data Center, an additional wireless 1GB link will be provided directly from FRH-022 to the Data Center. The link will be completed early in 1Q2014 and will constitute the completion of the Data Center buildouts. FRBA and the Network Operator will continue to pursue IRU Modifications with Level 3 in attempt to reconfigure space, power, and fiber allocations to better fit the needs of the entire network. This modification request does not hinder the capability for FRBA to provide service to end customers. d) QUALITY ASSURANCE/SITE ACCEPTANCE: Quality Assurance testing is projected to be completed at 100% of sites in 1Q2014. e) NETWORK OPERATOR: Negotiations of definitive agreement with operator will continue into 1Q2014. f) CUSTOMER OUTREACH: Establish direct service to as many CAI's as possible through unified outreach of FRBA and Network Operator. Outreach to required and non-required CAI's has begun. Limited campaigns will occur with the intent to secure required CAI's as presented in the grant. Continue to identify last-mile providers, primarily wireless Internet providers, in the region to establish service needs and timing coinciding with construction completion. FRBA expects to have made connection to at least 30 CAIs by the end of the next quarter, installed as beta customers as the network is completed. g) Wholesale Agreements: Through FRBA's network operator/partner agreement with Affiniti, additional last-mile providers will be identified through their channels to provide broadband into the FRBA service area. FRBA anticipates at least 1 contract with a broadband wholesaler/last mile provider by the end of the next quarter. | Florida Rural Broadband Alliance, LLC | a) OVERALL SITE CONSTRUCTION SCHEDULE: Project deployment continued its positive trend through 4Q2013. The project made huge strides in link alignments, testing and integration. Punch-list construction items were repaired and a majority of sites were accepted per project standards. A no cost grant extension was submitted and approved during the quarter. Additionally, design changes occurred due to structural and elevation issues with two specific towers. Subsequently, a network route modification was submitted and FRBA is awaiting final approval. | Through the extension of the the BTOP Grant, FRBA expects to complete all applicable project milestones 2a-2k. | TRUE
NT10BIX5570123 | 2010 | Q4 | Q4 - 2010 | Confirmed the specific locations on the ground for the towers; GPS points taken for tower site and access road locations; and have written up legal Option and Lease agreements between the two Privately owned sites and the Nez Perce Tribe; and between the City of Culdesac and the Nez Perce Tribe. The City of Culdesac agreements have been accepted and signed; negotiations continue with private landowners. Formalized a collocation template to be used between the Nez Perce Tribe and project partners: Inland Cellular and First Step Internet. Approval for use of Trust property sites process has been initiated through the Nez Perce Land Commission. Network engineering underway to identify specific wireless pathway equipment requirements and tower capacity. Environmental Analysis field work for biological resource assessment underway; Section 106 consultation process also underway. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | In line with Baseline; project planning phase | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | In line with Baseline; project planning phase | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | In line with Baseline; project planning phase | N/A | N/A | N/A | N/A | Libraries have requested the Nez Perce Tribe Information Systems network obtain FCC SPIN for E-rate provider offering. Investigations are underway regarding the FCC SPIN process. | FALSE | N/A | Tower sites are all in higher elevation areas of the Reservation, which is subjected to harsh winter conditions, so winter months will be used for administrative preparation. The expectation is to: complete private landowners' tower site lease agreements; Initiate the County level planning & zoning permit process for two sites (Peck site is within Nez Perce County; and Greer Grade site is within Clearwater County) and the City of Culdesac planning & zoning process for the tower within city limits; Completion of the Tribal approval of Trust property tower sites by Tribal Executive Committee Resolution; and, Completion of the environmental analysis. | Nez Perce Tribe | Section 106; assistance from NTIA staff has been a huge help in getting the consultation process and communication moving forward. | Cultural, Historic and Native American resource site surveys are expected during the next quarter; set backs are not expected that would impede project progress. | TRUE
NT10BIX5570123 | 2011 | Q1 | Q1 - 2011 | Environmental Assessment completed and submitted to NTIA. This effort included negotiation facilitation of a Programmatic Agreement in regards to Section 106 Consultation; due to winter weather site reviews were unable to be completed, the Programmatic Agreement outlined the process for consultation and project implementation. Network design work completed and microwave equipment specifications identified. Federal Aviation Administration Tower Construction applications submitted; Determination of no impact to aeronautic safety received on six of the seven proposed tower sites. Site land lease agreements in place for the three non tribal tower construction sites; Tribal Executive Committee Resolution approved for use of tribal units for tower locations. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 411 | 136 | 0 | 0 | 0 | The number of residential units in Lapwai - Sweetwater area that can be served on the existing Nez Perce Tribe Information Systems network | The Nez Perce Tribe Information Systems existing wireless network has 136 subscribers in Lapwai, Idaho area. | NA | NA | NA | 25 | 0 | 0 | 0 | 0 | In the Baseline we projected deployment of the network equipment on existing towers that has not yet occurred. Early in the next quarter network equipment will be procured to get the project back on track with the Baseline. | NA | NA | NA | NA | NA | FALSE | NA | Complete County Planning & Zoning permits for the non tribal land sites. Facilitate utility Service Line Agreements between utility providers and the Bureau of Indian Affairs. Develop Request for Bids on existing tower equipment; site preparation work and power utility service. | Nez Perce Tribe | Finalizing the Environmental Assessment was helped along by NTIA staff but was more time consuming than the project team anticipated, which set the project as a whole back. In addition, the power utility service line agreement process with Bureau of Indian Affairs was identified late in the process, which has been initiated during this reporting quarter and is expected to be completed during the next quarter. | No real issues anticipated; we expect local Planning & Zoning Conditional Use permitting for the three non tribal land tower sites to go along smoothly; as well as utility corridor right of ways and service line agreements with Bureau of Indian Affairs for the development on Tribal Units. | TRUE
NT10BIX5570123 | 2011 | Q2 | Q2 - 2011 | This quarter yielded several major accomplishments: The Cultural/Historic/Native American resource surveys were completed and a clearance report was provided by the Tribal Historic Preservation Office. With clearance to move ahead project staff issued Request for bids on the wireless network equipment and road construction/reconstruction. Bids were awarded for the wireless network equipment and FCC license coordination is underway. Recommendation for bid award for road construction/reconstruction has been made to the Tribal Executive Committee process and is expected early in the next quarter. Federal Aviation Administration issued all tower sites a Determination of no impact to aviation following an aeronautical study for the final tower; TU 17 tower (250' tall) and has required lighting and marking as part of the determination. All local planning & zoning conditional user permits have been issued for tower construction on the non tribal lands (Culdesac, Beard, Peck) and building permits are being secured. Utility Service Line Agreement applications from power companies submitted to Bureau of Indian Affairs for approval. Approval received on sites: TU 17 and 99-101; and, waiting Utility company submittal for approval on sites TU 60 and TU 71. The site development challenges for TU 71 have grown in complexity; after the power utility engineer brought the construction foreman out on site, it was determined the power delivery route identified was not doable. The NPT pr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | The Baseline projection was for 2 links to be installed by this quarter; the equipment for one link is ready to be installed by our tower partner for collocation. Wet spring weather has slowed the pace of field work. The project is expected to use the arrival of summer weather to get back on track during the next quarter. | The project staff ran a month behind due to Planning & Zoning meeting schedule, whihc set back construction of the PEck tower. The P&Z proccess has been completed and tower construction will be initiated in the next quarter, getting back on track with the Baseline. | The Baseline projection was for 2 links to be installed by this quarter; the equipment for one link is ready to be installed by our tower partner for collocation. Wet spring weather has slowed the pace of field work. The project is expected to use the arrival of summer weather to get back on track during the next quarter. The project staff ran a month behind due to Planning & Zoning meeting schedule, whihc set back construction of the PEck tower. The P&Z proccess has been completed and tower construction will be initiated in the next quarter, getting back on track with the Baseline. Being behind in network deployment has set back the rate of new/upgraded interconnection points. The project expects to be back on track during the next two quartersr 2 links to be installed by this quarter; the equipment for one link is ready to be installed by our tower partner for collocation. Wet spring weather has slowed the pace of field work. The project is expected to use the arrival of summer weather to get back on track during the next quarter. The project staff ran a month behind due to Planning & Zoning meeting schedule, whihc set back construction of the PEck tower. The P&Z proccess has been completed and tower construction will be initiated in the next quarter, getting back on track with the Baseline. Being behind in network deployment has set back the rate of new/upgraded interconnection points. The project expects to be back on track during the next two quarters. | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | Discussions thought to begin during the previous quarter have yet to materialize. | NA | NA | NA | 2 | 0 | 2 | 3 | Building the existing network the Nez Perce Tribe Information Systems was successful in connecting two CAI's | NA | Prairie River Library District - Lapwai branch; Clearwater County | 3Mbps; 10 Mbps - 1 subscriber; 20 Mbps - 1 subscriber | 411 | 230 | 0 | 230 | 3 | Total residential units in Lapwai-Sweetwater area that could be served on the Nez Perce Tribe Information Systems (NPT-IS)network | Active subscribes as of Qtr end | NA; lack of affordable service is driving subscribers to the NPT-IS network | Residential subscribes have grown faster than projected in Baseline | 3 Mbps; 10 Mbps; 20+ Mbps | 25 | 0 | 0 | 0 | 3 | Businesses in the Lapwai-Sweetwater census area that could be served by the NPT-IS network | The project has not yet developed an outreach/marketing plan to attract business subscribers | NA | NA | 3 Mbps; 10 Mbps; 20+ Mbps | NA | FALSE |  | Site access roadway construction completed; power lines extensions run to each tower site; tower erection contract award/implementation; and wireless network equipment installation and path connections be begin serving more areas across the Reservation. | Nez Perce Tribe | Cold, wet spring conditions kept field workers off sites mid way through the quarter; until the project staff had clearance from Cultural Resources site development work and was held off. Upon receipt of Cultural clearance the project staff issued a Request for Bids on site roadway access. The process for contractual negotiations and approval require additional time, which has set the site development behind the Baseline report. The recommendation for contract award has been forwarded to the Nez Perce Tribe Executive Committee for action early next quarter, weather permitting all site/road development work will be back on track through this next quarter. With the exception of TU 60 and 71, the utility service line agreements are in place and power development will be initiated in the next quarter. This will get the project back on track with Baseline projections related to site preparation. The wireless network equipment order has been placed; currently the project staff are working through the Federal Communications Commission pathway licensing process, a hold up has occurred in getting existing tower site licensing information from project partners. | TU 71 and service to the easternmost community of the Reservation has been an ongoing challenge. During this Qtr the power utility company field engineer indicated power delivery to TU 71 would not be possible within the project budget. Development staff have been diligently working to identify an alternative site that meets the intent of the project scope. When an alternative location is identified (expected mid next quarter) a project modification will be required. Due to the challenges in the eastern side of the Reservation network, the western network loop will take priority; sites are development ready and all agreements are in place for power, the access roadways will be constructed/improved, and a tower construction contract will be awarded during the next quarter. Contract coordination/compliance with Tribal Employment Rights Ordinance office staff will be part of the process the project works through as infrastructure developments begin to get underway. The Nez Perce Tribe has been working to resolve the difference in Indirect Rate allowance ; the fund expenditure to date has been recalculated based on the NOFA guidelines and presented herein under the Budget for Admin/Legal. Following the acceptance of the new Indirect Rate the awarded project funds will be reallocated based on a revision of indirect rate calculation that will be aligned with the NOFA guidelines. | TRUE
NT10BIX5570123 | 2011 | Q3 | Q3 - 2011 | Utility Service Line Agreements all filed and recorded with Bureau of Indian Affairs (TU 17, 60, 99-101); Site lease agreement finalized with City of Culdesac, Beard Enterprises and Garner Farms for the three non tribal sites. Site development activities began: contract for access roadways completed for TU 99-101, 60, Peck and Beard sites. Tower construction company contract awarded and site development work underway: foundation work complete TU 17, 60, 99-101; and Beard tower site excavation got underway. Under an existing contract for Culdesac and Peck tower foundations completed. Wireless network equipment procurement underway and radio configuration underway for the network links. Wireless equipment installation complete on existing tower, Stoney Point with last mile service delivery connections made. Site visit with BTOP program officer completed. Investigation underway for a project modification to get around issues identified at TU 71 tower site. Working on project modification request; Section 106 and US Fish & Wildlife consultation. | 9 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | The wireless link BioControl - Stoney Pt is on line the quarter. | NA | NA | NA | NA | Stoney Pt - BioControl link is up | Five of seven foundations are complete. | NA | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 3 | NA | NA | NA | 3 Mbps; 10 Mbps- 1 subscriber; 20 Mbps - 1 subscriber | 230 | 1 | 0 | 1 | 3 | Total residents in Lapwai-Sweetwater area | Number of current subscribers | The NPT-IS network offers affordable connectivity | Total residential subscribers on the existing network infrastructure | 3 Mbps; 10 Mbps; 20+ Mbps | 1 | 0 | 0 | 0 | 3 | Total businesses in Census block covered by Stoney Pt | No outreach/marketing to business community | NA | NA | 3 Mbps; 10 Mbps; 20+ Mbps | NA | FALSE | Site visit resulted in the identification of changes needed and efforts to correct the identified issues will take place during the next Qtr. | Tower erection will be started early in Qtr and is expected to be complete for TU 99-101, TU 17, TU 60, Culdesac, Peck and Beard sites. Network equipment installation on existing towers will be initiated and is expected to be complete on Hubbard, Mason Butte and Teaken sites. This deployment will result in the addition of 33 miles to the network. Middle mile connectivity is expected to reach Ahsahka/western Orofino, Peck and Culdesac during the next quarter; last mile access points will follow. Last mile access to Culdesac and Peck will enable libraries in each community and the City of Culdesac to be connected; adding three (3) CAI's. There are no anticipated interconnection agreements with broadband wholesalers or last mile providers during this time. TU 64 request for project modification will be complete and NEPA review undertaken. | Nez Perce Tribe | The problems delivering power to TU 71; costs far exceed the budget available, will require project modification request which is underway and will take technical support from program officer. Working through the requirements and NEPA revision will be the focus of technical support required. An alternative site has been identified and an easement agreement with the adjacent landowner has been reached for ingress/egress to TU 64. To keep the project on track the weather is going to be a significant factor this fall/winter. Through Q3- 2011 the work season has been friendly - dry warm conditions have not hindered construction activities and the project has gotten back on track; however fall rains and winter snow could hinder activities. | Weather could become a limiting factor for project accomplishments as winter approaches. Technical support as we work through the modification and NEPA analysis to consider TU 64 as a replacement for TU 71. | TRUE
NT10BIX5570123 | 2011 | Q4 | Q4 - 2011 | All access roadway construction complete; and, tower site work, tower stacking and communication building placement complete at TU 17, 60, 99-101, Beard; and tower stacking complete at Culdesac and Peck sites. Electric utility connection complete at TU 17, 99-101, 60, Beard. Contract awarded for communication building placement and electrical service for Culdesac and Peck sites. Wireless equipment procurement underway, radio configuration underway and installation contract awarded for middle mile late December 2011; work to begin early 2012. Project modification to get around issues identified at TU 71 tower site: consultation with US Fish & Wildlife Service and Section 106 consultation complete where determinations of no effect were documented by each entity; Environmental Analysis Addendum submitted for approval; project modification request submitted. Negotiations for equipment collocation at all non Tribal tower sites competed. | 9 | 0 | 0 | 0 | 0 | 1 | 6 | 2 | The wireless link BioControl - Stoney Pt is on line the quarter. | NA | NA | NA | NA | Stoney Pt - BioControl link is up | TU 17, 60, 99-101, Beard, Culdesac, Peck | To date points of interconnection include Vets Building (Lapwai Tribal Headquarters) to XO Communications and BioControl to ID Regional Optic Network (Teaken Butte); each of these connections enable the NPT Network access to the internet. The project is behind projected Baseline because weather conditions set back construction of the network. As each new tower site comes on line we will get closer to baseline. The project expects to have the middle mile interconnection points completed during the next quarter. | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | 3 Mbps; 10 Mbps; 20+ Mbps | 2 | 0 | 2 | 3 | During Q2 2011 two community anchors were connected | Tower construction delays have held new connections back; we expect to be making connections in upcoming quarters | Tower construction delays have held improved access connections back; we expect to be making connections in upcoming quarters | 3 Mbps; 10 Mbps; 20+ Mbps | 60 | 2 | 0 | 2 | 3 | Total residences in census block 9901-01 is 230; however the tower line of sight coverage is approximately 25% of the area; we are planning to test a 900 MHz access point to increase coverage beyond direct line of sight. | NA | NA | From Dial up to broadband wireless | 3 Mbps; 10 Mbps; 20+ Mbps | 0 | 0 | 0 | 0 | 3 | No known businesses in service area | NA | NA | NA | 3 Mbps; 10 Mbps; 20+ Mbps | NA | TRUE | Billing system now tracks subscribers by tower served from; this enables separation of existing (pre BTOP) network and new (BTOP) subscribers and program income generation. | Completion of Culdesac and Peck tower site work; communications building placement, electrical connection are needed. Installation of all middle mile wireless equipment for the towers constructed will be completed during Q2 2012. Pending approval, the modification to construct a tower on TU 64 in place of TU 71 will be contracted and construction activities are expected to be underway in Q2 2012. Midway through Q2 2012 the last mile access equipment installation will be initiated by Nez Perce Tribe Information System staff; network testing will be initiated and subscriber connections begun. It is expected that during the next quarter the project 95 additional miles of the network will be brought on line; the middle mile loop should be completed. Both the Culdesac and Peck tower sites are expected to have last mile access points on line by the end of Q 1 2012, enabling connection of three CIAs (Culdesac City, Library, Peck Library). There have been no discussion with Broadband wholesalers or last mile providers; and, no agreements are expected in the next quarter. | Nez Perce Tribe | The project stumbling blocks should be mostly passed over; winter weather is still a factor as we move into wireless equipment installation and antenna alignment. Guidance on development of a marketing efforts will be sought as the Tribe moves forward from construction to implementation. The project team continues to work through issues brought forward in CAP review; all identified issues are expected to be addressed very early in 2012. | Weather could become a limiting factor for project accomplishments as winter storms can be unpredictable this time of year. Expect the NEPA EA Addendum decision early next quarter; enabling project modification will be a positive impact to project implementation. Technical assistance will be valuable as we proceed with developing a marketing plan as the network comes on line. | TRUE
NT10BIX5570123 | 2012 | Q1 | Q1 - 2012 | Modification to Environmental Assessment approved to replace TU 71 with TU 64. To date, six of the seven sites with new tower construction has been completed; and the middle mile wireless network equipment installation has been completed. There were issues with routing but the NPT Information Systems IT staff worked with manufacturer and resolved them. Last mile access issues arose, due to challenging topography across the Reservation; the single sector antenna ranges were limiting line of sight service offering. The NPT Information Systems IT staff worked with product manufactures to identify a solution; the antennae have different angle of service delivery, the solution identified in areas with the deepest topographical ranges (700 + ft from tower to subscriber) is to stack sector antennae (16 Db & 19 Db units) to improve area of coverage; and, in areas with lesser topographical ranges to stack sector antenna with an omni antenna. The additional radio/antenna have been ordered. To date last mile access points have been installed at the Stoney Point, Culdesac and Peck tower sites. The contract for tower construction at TU 64 has been awarded. | 116 | 0 | 0 | 0 | 0 | 11 | 6 | 2 | Remaining pathway links include: TU 60 - Nuxoll (5.57 miles); Nuxoll - KIYE (3.18 miles); KIYE - TU 64 (2.36 miles); a total of 11.11 new miles will be deployed Q2. These were on hold for EA modification, which is now approved. The contract to implement has been awarded and weather is holding construction start back. | NA | NA | NA | NA | The modification of project towers affected the middle mile; the modification approval enables construction to move ahead to complete the network links by end Q2 2012 | The final tower has completed EA review; a contract is awarded; weather is affecting the start of work, it will be started early Q2 2012 | Tribal headquarters to XO Communications; BioControl to Teaken for Idaho Regional Optic Network interconnection | 0 | 0 | 0 | NA | NA | NA | 0 | 0 | 0 | 3 | NA | NA | NA | 3 Mbps; 10 Mbps; 20 + Mbps | 2 | 0 | 2 | 3 | During Q2 2011 two CAI's were connected | Access service will be started in Q2 2012 | Access service will be started in Q2 2012 | 3 Mbps; 10 Mbps; 20 + Mbps | 604 | 2 | 0 | 2 | 3 | Last mile access established within census blocks 9901-01, 9901-03, 9901-02 and 9702-01 | Due to antenna coverage limitations in topographically challenging areas we have had to develop a solution; equipment is on order and we expect installation to offer baseline anticipated coverage during the next quarter. | NA | Site survey request list is being maintained by tower site, to date there are 14 requests in Culdesac area, and 16 requests in Peck area. Site surveys are underway in Culdesac and will begin in Peck once the equipment has been upgraded (stacking LM access pts) on tower | 3 Mbps; 10 Mbps; 20 + Mbps | 31 | 0 | 0 | 0 | 3 | Last mile access established within census blocks 9901-01, 9901-03, 9901-02 and 9702-01 | Marketing plan is being developed | Marketing plan is being developed | Marketing plan is being developed | 3 Mbps; 10 Mbps; 20 + Mbps | NA | TRUE | The technician crew doing to tower work have been more engaged in network coverage problem discussions and involved in proactive solution brainstorming. | Construction at TU 64 site is expected to be completed in Q2 2012(depending on weather). With construction of TU 64 the installation of the middle mile network is expected to also be completed by the end of Q2 2012. Remaining pathway links include: TU 60 - Nuxoll (5.57 miles); Nuxoll - KIYE (3.18 miles); KIYE - TU 64 (2.36 miles); a total of 11.11 new miles will be deployed Q2. Last mile access point installation and testing is expected to be complete in Q2 2012 for four of the eleven last mile access towers. A contract will be advertised in Q2 to install the remaining seven last mile sites. NPT Information Systems field crews are conducting site surveys and doing subscriber installations during the next quarter and throughout the remaining project period. The project will have two additional CAI's connected in Q2. The development of service marketing materials will be a project leader focus for the upcoming quarter. There are no current wholesaler or last mile providers requesting agreements in Q1 and none are expected in Q2. | Nez Perce Tribe | Guidance regarding development of marketing materials would be welcomed as we begin deployment and implementation. | Assistance and guidance in developing a marketing strategy as we deploy and begin service offerings. COMMENT: The program income will be used in Q2 2012 | TRUE
NT10BIX5570123 | 2012 | Q2 | Q2 - 2012 | The TU 64 tower construction contract was awarded and construction began and was completed in this quarter (access roadway, site excavation, foundation, tower delivery and construction). Middle mile equipment installation was completed during the quarter; and, all links are working except the KIYE-TU 64, which is under investigation. A contract to install last mile equipment on nine towers was advertised and awarded during the quarter. With the exception of the last mile at KIYE all last mile equipment has been installed and connection tested. New subscribers were connected to TU 17 tower during the Quarter. As of Q2 2012 last mile service is begin delivered on three (Stoney Pt, Culdesac and TU 17) of the eleven last mile towers identified for service delivery. Two new CAI's were connected during this quarter: Culdesac Library and the City of Culdesac. No broadband wholesale/last mile agreements were initiated during this reporting quarter. Program income totalling $809.50 has been expended to cover the costs of utility service to towers during the quarter. | 125 | 0 | 0 | 0 | 0 | 15 | 7 | 2 | Completed all links; however the KIYE-TU 64 link (2.36 miles) equipment is in place but there is a problem that is being troubleshot, when the KIYE-TU64 link is connected to the router we loose the KIYE link connecting to the rest of the network. | NA | NA | NA | NA | The KIYE-TU64 link is not operational and is not included in this report, all other links are operational. | All tower construction now complete | The project interconnection points to the internet include:Tribal headquarters to XO Communications; BioControl to Teaken for connection to Idaho Regional Optic Network. In the baseline the projected number of interconnection points included the connection of each tower site onto the network. Given the method used for baseline the project has interconnection at 13 sites (BioControl, Teaken, Stoney Pt, TU 17, TU 99-101, Culdesac, Peck, Hubbard, Beard, TU 60, Nuxoll, KIYE, Mason Butte). | 0 | 0 | 0 | None; the baseline projected an agreement with a local last mile provider start-up who has chosen to not pursue an internet service provider business at this time on the Reservation. | NA | NA | 0 | 0 | 0 | 3 | NA | NA | NA | 3, 10, 20+ Mbps | 4 | 0 | 4 | 3 | The following connections have been made through the end of Q2 2012: Lapwai library (20 Mbps), Clearwater County (15 Mbps), City of Culdesac (3 Mbps) and Culdesac Library (6 Mbps). The build out has been much slower than projected in the baseline; however NPT technical field staff are focused on last mile installation now and are poised to work towards baseline goals during the next quarter. | NA | Each of the subscribers are receiving a more affordable service | 3, 6, 10+ Mbps | 725 | 24 | 0 | 24 | 3 | Last mile service established within 2010 Census Tracts 160699400 (BioControl, Culdesac, Stoney Pt, TU 17). residences passed: Culdesac 411, TU 17 254, Stoney Pt 60 | For this Quarter BTOP new subscribers include: Culdesac 16 new; TU 17 6 new; cumulatively the Tribes network (non BTOP + BTOP) is serving 240 subscriber accounts, all accounts are subscribed at 3 Mbps. The overall Tribal network is currently serving ten less subscribers than baseline projection. | No subscribers are first time internet subscribers | More affordable service | 3, 6, 10+ Mbps | 44 | 0 | 0 | 0 | 3 | Last mile service established within 2010 Census Tracts 160699400 (BioControl, Culdesac, Stoney Pt, TU 17). Entities passed: BioControl 23; Culdesac 18, Stoney Pt 2, TU 17 1 | None to date, baseline projection was for twenty; the marketing plan work we will focus on should help gain business subscribers. | NA | NA | 3, 6, 10+ Mbps | NA | FALSE | NA | With the replacement IT technician on board the project expects to solve the middle mile KIYE-TU 64 problem (middle mile path of 2.36 miles); and complete the testing for last mile access points. NPT technical staff will continue subscriber installation to reach targets for the project. The Tribe is working on negotiating possible collocation with City of Moscow for an additional interconnection point to the ID Regional Optic Network. There were no wholesale or last mile providers requesting agreements in Q2 and it is anticipated there will be no requests in Q3 due to the limited amount of providers in this remote region. During Q3 2012 the project will have connection to an additional five (5) CAI's. Program staff are working on a marketing plan and strategies beyond word of mouth and brochures to attract subscribers. | Nez Perce Tribe | The resignation of a support IT technician in the middle of Q2 set the project back related to configuration and testing; however a replacement has been selected and will begin early Q3, which should get the network deployment and testing complete by the end of Q3. | The middle mile configuration problem we have between KIYE and TU 64 will be a priority for the replacement IT technician to troubleshoot and resolve. Project leader will be focussed on marketing strategy/plan and implementation to reach out to a wider range of potential subscribers. Field staff technicians will be focussed on CAI, residential and business subscriber site surveys and connection. | TRUE
NT10BIX5570123 | 2012 | Q3 | Q3 - 2012 | Construction of the final new tower site (TU 64) was completed in Q3 2012; power was delivered to the site and middle mile equipment installation was completed. There were configuration issues between KIYE & TU 64; and the cabling at KIYE required replacement with a higher shielded cable to reduce interference from the local radio station antenna. These issues were resolved in the quarter and Last Mile service was brought on line at six new sites (99-101, Mason Butte, Peck, Hubbard, TU 60, Beard) during the quarter. A total of nine of the eleven LM sites are now on line and site surveys are underway. Two new CAI's were brought on line during Q3 2012: Peck Library, Sunnyside Rural Fire Dept; and access has been offered to Culdesac-Lapwai Quick Response Unit and Big Canyon Rural Fire District, however they are not choosing to connect. We have confirmed network access to the Peck school and are awaiting school district approval to connect that facility. Staffing was increased again at the Nez Perce Wireless program; two additional technicians were brought on to assist with site surveys and connections. To date, the project has generated five new career path permanent job opportunities. | 152 | 0 | 0 | 0 | 0 | 16 | 7 | 16 | All middle mile network links are complete. | N/A | N/A | N/A | N/A | All project links have been completed. | Completed | In the Baseline the projected number of interconnection points was listed including each tower site as an interconnection point to the internet. Given this method of identifying interconnection points the project would have completed 16 interconnection points (Lapwai - XO Communications; Teaken - IRON; and the wireless network sites: Biocontrol, Stony Pt, Teaken, Beard, TU 60, Nuxoll, KIYE, TU 64, Mason Butte, TU 17, TU 99-101, Culdesac, Peck & Hubbard). | 0 | 0 | 0 | None, the ISP we expected to sign up in Baseline has gone out of business. During the Quarter, one provider, QRO of Idaho, has requested 50 Mb connection, we provided a price quote and have not heard back. | None | None | 0 | 0 | 0 | 3 | N/A | N/A | N/A | 3, 10, 20+ Mbps | 6 | 1 | 5 | 4 | Through Q3 2012 the following CAI connections have been established: Libraries - Lapwai (20 Mb), Culdesac (6 Mb), Peck (6 Mb); Government - Clearwater County (15 Mb), City of Culdesac (3 Mb), Sunnyside Rural Fire (3 Mb) | Sunnyside RFD had no previous internet connection | All others had previous internet but chose NPT Wireless for better connectivity (Peck was on Satellite), or a more affordable service. | 3 Mbps 2 subscribers (City Culdesac, Sunnyside RFD) 6 Mbps 2 subscribers (Culdesac & Peck Libraries) 9 Mbps 0 subscribers 10+ Mbps 2 subscribers (Lapwai Library & Clearwater County) | 2337 | 302 | 13 | 289 | 3 | Last mile service deployed across the Reservation in targeted communities | Cumulatively the NPT Wireless network is serving 302 residential subscribers, which is 38 less than established in baseline. | Subscribers in the Stony Pt , Mason Butte and TU 60 viewshed have received new access. | Subscribers across much of the Reservation have had access to the internet but are now receiving improved (higher speed, less cost) access. | 3 Mbps 244 subscribers 6 Mbps 50 subscribers 9 Mbps 8 subscribers | 273 | 0 | 0 | 0 | 4 | A marketing plan with detailed actions is working its way through the Tribes approval process. Marketing efforts are expected to be underway early in Q4 2012 | No business subscribers | No business subscribers | No business subscribers | 3 Mbps 0 subscribers 6 Mbps 0 subscribers 9 Mbps 0 subscribers 10+ Mbps 0 subscribers | N/A | TRUE | We have assigned crews of two technicians for site survey & installation specific areas within the Reservation. This way one crew is not doing site survey and another going to do an installation. This has streamlined out technical crews travel and made for a more positive customer relationship leading to a more positive experience. | During Q4 2012 the project will deploy equipment to enable mobile access in the Hwy 95 corridor, vastly improving public safety and enabling voice-data service to county, tribal and state police as well as the public travelers along this route. Project staff are working to deploy neighborhood solution sites (4 additional sites). In Q4 2012 we expect to have Culdesac, Shannadoah and Dumbo Flats installed for an additional 12.97 miles. The project staff will continue to work with CAI's across the Reservation to get them connected to the network as well as working to fill in the service area gaps, which are a result of the limitations of line of sight technology in our topographically challenging region. We expect to connect 4 additional CAI's in Q4 2012. We do not expect to have any wholesale/last mile provider agreements completed in Q4 2012. Increasing awareness of the NPT Wireless network through outreach and marketing efforts, such as direct mailings, media advertisements and flyer distribution in targeted markets. The expected outcome is more subscribers connected. | Nez Perce Tribe | The project is closing in on completion. The challenges we are dealing with are linked directly to the limits of last mile technology and the need for line of sight. Where possible we are working with existing infrastructure to add last mile access points to help fill in gaps in service areas. Our project partner, Inland Cellular will be adding the voice/data mobility coverage during the next Quarter in the Culdesac-Winchester area and in the Greer - Kamiah areas during Q1 of 2013. This component of the project will bring on line the public safety CAI's (State, County, Tribal police) connectivity. | Winter is approaching so weather will become a factor for field work; however, the impact should be minimal as work now is focused primarily on business/residential interconnection. The project is on track to be complete with match obligation met in Q1 2013. | TRUE
NT10BIX5570123 | 2012 | Q4 | Q4 - 2012 | Construction of the project was completed in Q4 of 2012. Broadband connectivity is now available in the communities of Lapwai, Sweetwater, Myrtle, Arrow Junction, Culdesac, Reubens, Peck, Ahsahka, Riverside-Orofino, Fraser, Kamiah, Network Technicians are working across the Reservation to connect subscribers. As the technicians find areas where coverage is not available due to topographic features blocking line of sight connection project development staff are working with perspective partners to develop middle mile neighborhood solutions. The neighborhood solutions are short hops of middle mile using existing buildings (primarily rooftops) to establish a last mile connection point that fills in the service area gaps. During Q4 three such partnerships were established: Downtown Culdesac had significant blockage of signal by evergreen and deciduous trees; the local hotel/apartment complex was identified as a desirable location and the landowners were willing to allow a rooftop dish mount and equipment cabinet that enabled the network to serve residents and businesses along the Main street corridor. At Shenandoah, above Kamiah and at Webb, southwest of Lapwai, a group of community members requested we consider coverage in their rural/remote corner of the Reservation; Signal coverage from existing last mile sites was blocked by a tree covered ridge-line. In each location a willing homeowner allowed rooftop space for a dish mount and equipment to enable last mile delivery to the surrounding community. At the KYE site, the last mile service continues to be interrupted by FM radio broadcast. Network Technicians are working on a variety of shielding solutions; ferrite beads for the cable and shielded antenna shields for the antenna themselves. In addition, development staff are working on options for a possible relocation to a rooftop in Kamiah to resolve the last mile delivery with a neighborhood solution. Mobile service was brought on line in Culdesac-Winchester corridor, expanding service to four (4) public safety CAI's (ID State Police, Tribal Police, Nez Perce and Lewis County Sheriff). A service agreement to serve Peck Elementary, Clearwater County Marine Sheriff and Ambulance Service was established; equipment procurement and the FCC 4.9 gHz licensing process are underway. Budget Construction expenditures discrepancies between Q3 andQ4 reports result from a detailed, item by item review of the project expenses by Project Mgmt staff and Finance staff accountant. In the review we found a $ 36,625 error, where BTOP had been charged for a non BTOP related expense. This error has been corrected but has resulted in an overall reduction in overall Construction line item expense documentation. | 155 | 0 | 0 | 0 | 0 | 16 | 7 | 16 | Completed primary middle mile network (152 miles); added 3.34 miles with deployment of two neighborhood solution sites (Culdesac & Dumbo Flats). | NA | NA | NA | NA | Complete | Complete | Complete | 1 | 0 | 20 | Washington RSA #8 Limited Partnership, dba Inland Cellular (5 year with option for additional 5 year term) | 3 Mbps of dedicated Network bandwidth to support mobile voice and data service delivery in Culdesac-Winchester area. | NA | 1 | 0 | 0 | 3 | Washington RSA #8 Limited Partnership, dba Inland cellular agreement for network bandwidth to facilitate cellular coverage expansion. | NA | NA | 3 Mbps - 1 10 Mbps - None 20 Mbps - None | 9 | 4 | 5 | 4 | To date, Fixed broadband service delivered to: Lapwai Library(20 Mbps), Clearwater County (15 Mbps), Culdesac Library (6 Mbps), City of Culdesac (3 Mbps), Peck Library (6 Mbps), Sunnyside RFD (3 Mbps), City of Reubens (3 Mbps); NW Indian College (connected but not receiving service; Big Canyon RFD (connected but not receiving service) | Mobile access is new in the Culdesac-Winchester corridor providing a boost to public safety along a treacherous section of the only N-S route (ID 95); and Sunnyside RFD had no previous access to broadband | The projects connection to Libraries, City and County governments has provided more desirable service (more affordable, reliable and higher speed) | 3 Mbps - City of Culdesac, City of Reubens, Sunnyside RFD 6 Mbps - Culdesac & Peck Libraries 9 Mbps - None 10+ Mbps - Lapwai Library (20 M), Clearwater County (15M) | 3610 | 372 | 55 | 317 | 3 | We have met the overall Baseline objective fro Residences passed. Tower coverage: BioControl 411; Culdesac 349; TU 17 (94); Stoney Pt (60); Peck (250); Hubbard (853); Beard (25); TU 60 (409); KIYE (350); TU 64 (203); Mason Butte 606. | Baseline projection was 460, so we are off 77 (2%). On average the field crew scheduling board has thirty (30) per week, and with travel time across the Reservation crews can connect three (3) per day. So, effectively we are just keeping up with demand with two field crews. | Baseline projection was 100. By partnering with and serving libraries we are facilitating brodband adoption on our rural communities which long term will lead to more first time subscribers. | Baseline projections was 20, which we have exceeded. | 3 Mbps - 283 subscribers 6 Mbps - 73 subscribers 9 Mbps - 16 subscribers | 286 | 1 | 0 | 1 | 4 | Tower coverage: Biocontrol (23); Culdesac (18); Peck (13); Hubbard (94); Mason Butte (39); TU 17 (2); TU 60 (5); KIYE (93); TU 64 (5). Marketing plan implementation should increase business subscriptions. | Baseline projection was 20. Project staff are prepared to conduct specific business targeted marketing efforts through print media as well as awareness campaigns through Chambers of Commerce and Economic Development groups. | Baseline projection was 0. | Baseline projection was 20; a targeted marketing effort to make the business community aware of the service offered should boost subscriptions. | 3 Mbps - 0 6 Mbps - 1 9 Mbps -0 10+ Mbps - 0 | We are working on a referral awards program for existing subscribers who recruit new subscribers. We expect to hae a system in place by end of Q1 2013. | TRUE | Field crew management and work order documentation have been in constant states of flux as we strive to develop an efficient system for field crew deployment; the Reservation distances to travel are slowing down productivity. We have developed a regionalized approach to field work so crews are not passing each other along the roadways or doing too much backtracking. | To date,construction of the backbone network is complete and final testing expected to be complete early in the quarter the emphasis of field technicians is connecting subscribers and identifying service gap areas. The network technicians will complete installation and testing of the Shenandoah (rural Kamiah) and Clearwater Transfer (to connect Clearwater Co Ambulance) neighborhood solutions to fill in identified service area gaps. Project development staff role will switch from construction related efforts to administrative as the close out process is initiated. Q1 2013 middle mile deployment will be (to Peck School 1.71 m, Clwtr County Ambulance, Marine Sheriff & Annex 7.04 m) 8.75 miles. This expansion will result in adding four (4) additional CAI's (Ambulance, Marine Sheriff, Emergency Mgmt, County Extension, and enable connectivity to Lewis Clark State College Outreach Center). There are no wholesale or last mile provider agreements anticipated in the upcoming quarter. | Nez Perce Tribe | The lack of affordable non-line of sight last mile delivery options in broadband technology has set the project back as we discovered the challenging topography posed more service connection interference than originally anticipated. We investigated Cambium Networks non line of sight equipment but end user costs were prohibitive ($ 1,000+). We are interested in network with firms doing R&D in the lower spectrum and perhaps serve as a field testing ground for non-line of sight technologies being developed. | Program income is being used monthly to cover utility service costs at each individual/unique tower site and to support neighborhood solution equipment procurement enabling service delivery. In addition, Program income will be used early in Q1 2013 to purchase necessary equipment to upgrade the current 200 Mbps back-haul link connection to the ID Regional Optic Network to a 1 Gbps connection. This upgrade will support the network bandwidth demand peaks. | TRUE
NT10BIX5570123 | 2013 | Q1 | Q1 - 2013 | During Q1, 2013 Nez Perce Tribe implemented two middle mile hops to resolve lack of coverage in neighborhoods targeted in the project: Shenandoah, a rural housing area north of Kamiah; and, into Clearwater County, enabling connectivity of the County Ambulance and to the Sheriff's marine patrol headquarters facility. These middle mile hops were accomplished by placing network equipment on the rooftops of existing buildings. The Webb neighborhood solution is still in development as a suitable location is under investigation. In Kamiah, the project continues to struggle with a solution to FM radio interference on the KIYE tower. Ferrite beads have been procured and will be installed early Q2; the use of ferrite should reduce interference along the shielded cat 5 cable currently in place. Developing a solution at KIYE will enable last mile Internet service delivery from the final project tower. Project staff have been working on a possible private rooftop location that would replace some of the KIYE access point antenna; the site will be presented at City Planning & Zoning for a Conditional Use Permit early Q2. If approved, this site will be deployed as soon as possible to enable residents, businesses and public sector entities access to the Tribes network. Program income earned has been utilized to support electrical utility service at BTOP tower sites, to cover the costs of a Q 2 print media campaign, to upgrade wireless links and deploy neighborhood solution equipment. As of the end of Q1 2013 total program income earned $ 46,193.27; expended to date $ 36,117.64; net balance of $ 10,075.63. | 169 | 0 | 0 | 0 | 0 | 19 | 7 | 16 | Completed primary network 152 miles; added 3.34 miles previously; during Q1 2013 added two middle mile hops to Shenandoah neighborhood (9.9 mi) and Clearwater transfer station (4.75 mi) | NA | NA | NA | NA | Primary network: 15; Neighborhood solution links: 4 | Complete | Complete | 1 | 0 | 20 | Washington RSA #8 limited Partnership,dba Inland Cellular (5 year with option for additional 5 years) | 3 Mbps dedicated bandwidth to support mobile voice and data service delivery in Culdesac-Winchester area. | NA | 1 | 0 | 0 | 3 | Inland Cellular agreement to facilitate expansion of mobile service within the project area. | NA | NA | 3Mbps -1 10 Mbps -0 20 Mbps -0 | 11 | 6 | 5 | 4 | To date, Fixed broadband service delivered to: Lapwai Library(20 Mbps), Clearwater County Courthouse (15 Mbps), Ambulance (15 Mbps),Marine Sheriff (15 Mbps), Culdesac Library (6 Mbps), City of Culdesac (3 Mbps), Peck Library (6 Mbps), Sunnyside RFD (3 Mbps), City of Reubens (3 Mbps); NW Indian College (connected but not receiving service; Big Canyon RFD (connected but not receiving service) | Peck Library, Big Canyon RFD, Sunnyside RFD, City of Reubens, Clearwater Co Ambulance and Marine Sheriff facilities had no previous access to broadband | The projects connection to Libraries (Lapwai, Culdesac), City (Culdesac), Clearwater Co Courthouse and NW Indian College has provided more desirable service (more affordable, reliable and higher speed) | 3 Mbps - City of Culdesac, City of Reubens, Sunnyside RFD 6 Mbps - Culdesac & Peck Libraries 9 Mbps - None 10+ Mbps - Lapwai Library (20 M), Clearwater County faclities (15M) | 3610 | 611 | 144 | 467 | 3 | The baseline projection has been met | The baseline projection of 460 has been met | The baseline projection of 100 has been met | The baseline projection has been met | 3 Mbps: 415 6 Mbps: 171 9 Mbps: 25 | 407 | 8 | 0 | 8 | 4 | The project has enabled connection to businesses by tower site as follows: BioControl (23) Culdesac (18), Peck (13), Hubbard (247), Mason Butte/TU 17 (13), KIYE/TU 64 (93). The baseline projection has been met. | Baseline projection of 65 has not been met; during Q1 marketing efforts were expanded to include print media coverage. In addition the regional economic development district has included all provider options in a recent newsletter focused on manufacturers. It is expected during Q2 that with expanded marketing and outreach to the business community subscriber numbers will increase. | Marketing efforts to the business community in previously unserved areas will be taking a more one on one approach during Q2 2013. Project staff will do more outreach through local Chambers, business associations and through the US Postal Service direct mail program to target businesses in previously unserved areas. | Business subscribers are clustered in the Lapwai area, we anticipate growth in areas across the Reservation as the business community becomes more aware of the service options available. | 3 Mbps: 4 6 Mbps: 3 9 Mbps: 1 10+ Mbps 0 | None at this time | TRUE | We returned to a centralized reservation system for customer scheduling. The field technician crews (3) have specific territories : Local Lapwai/Orchards; Prairie and River communities. The River crew has been relocated to an upriver office location, which has reduced drive times and improved efficiencies. | Complete the ferrite bead installation at KIYE and pursue corrective actions to enable last mile service from this site. Complete connection to Clearwater County Extension and Lewis Clark State College Outreach Center. The Glenwood-Caribel RFD opted to not connect to the network; Culdesac QRU is connected but not activated service; and the Orofino Rural Fire Dept opted to not connect the facility to the network. In Q 2 no new network miles will be deployed; and the upgrade of backbone to ID Regional Optic Network will be completed. No new wholesale or last mile provider agreementss are anticipated in the near future. Expand marketing to the business community in previously unserved areas. Continue to identify neighborhood solution sites to fill in the gaps of service across the Reservation due to topographic features blocking line of sight. | Nez Perce Tribe | At the KIYE site the facility has been constructed but Internet connectivity is significantly interrupted by the Tribes noncommercial FM radio station equipment, also on the KIYE tower. Ferrite beads have been delivered and are scheduled for installation early Q2. If the placement of ferrite along the Cat 5 shielded cable does not resolve the interference issue project staff have been working to identify an alternative site for network equipment. Two sites have been identified: City of Kamiah Water tank, this site will reach approximatively 40% of the City of Kamiah; and a private residence rooftop, this site will cover 90% of the community. Each solution will require a City Planning & Zoning Conditional Use Permit. Connection at to the Clearwater County Annex (Emergency Mgmt & County Extension office location, and the Lewis Clark State College Outreach Center has been delayed but is to be complete in Q2 2013. | None, we are well on our way to project completion. | TRUE
NT10BIX5570123 | 2013 | Q2 | Q2 - 2013 | During Q2 2013 the Nez Perce Tribe completed construction and deployment of the proposed broadband network. The KIYE site solution was reached with addition of ferrite beads to shielded cabling to reduce the interference from the Tribes local noncommercial FM radio transmission. In the quarter, two additional neighborhood solutions were deployed to fill in service gaps due to the topography across the Reservation. These sties added 5 miles to the middle mile network. There were five (5) new CAI's connected in the Quarter (Clearwater Transfer Station, USFWS-Dworshak National Fish Hatchery, ID Fish & Game Clearwater Hatchery, Univ of ID Extension, Lewis Clark State College -Outreach). The project has been completed with a balance of funds 1% ($ 19,395.99) remaining. Program income has been earned and spent to support electrical utility service to each new tower site; to develop marketing materials; to provide equipment for the neighborhood solutions sites; and to upgrade (200 to 600 Mbps) the back haul links (TU 17 - City Moscow) accessing the ID Regional Optic Network backbone to the Internet. To date Program Income earned is $58,884.00, spent $ 41,719.91, balance $ 17,164.09. | 175 | 0 | 41 | 0 | 0 | 21 | 7 | 16 | 152 Primary network miles; added Culdesac (0.4 m), Dumbo Flat (2.9 m), Shenandoah (9.9 m), Clearwater Trsf (4.75 m), Neville (2 m), Ahsahka (3 m) | NA | TU 17 - W Twin (34.3 m), W Twin - Moscow (6.7 m) paid for with Program Income funds; the upgrade allowed the network to expand backbone connection to Internet via ID Regional Optic Network to 764 Mbps | NA | NA | Primary network 15; Neighborhoods 6 | Complete | Complete | 1 | 0 | 20 | Washington RSA #8 Limited Partnership, dba Inland Cellular ( 5 year term with Option for 2nd term) | 3 Mbps dedicated bandwidth to support mobile voice/data service delivery in Culdesac-Winchester area | NA | 1 | 0 | 0 | 3 | Inland Cellular - Amgt facilitates expanded mobile service | NA | NA | 3 Mbps - 1 10 Mbps -0 20 Mbps -0 | 17 | 10 | 7 | 4 | To date, Fixed broadband service delivered to: Lapwai Library(20 Mbps), Clearwater County Courthouse (15 Mbps), Ambulance (15 Mbps),Marine Sheriff (15 Mbps), Annex (15 Mbps), County Transfer Stn (15 Mbps), Culdesac Library (6 Mbps), City of Culdesac (3 Mbps), Peck Library (6 Mbps), Sunnyside RFD (3 Mbps), City of Reubens (3 Mbps), Univ of ID Extension (15 Mbps), LCSC- Orofino Outreach (15 Mbps), USFWS - Dworshak NFH (6 Mbps), ID F&G - Clearwater Hatchery (6 Mbps); and NW Indian College (connected but not receiving service; Big Canyon RFD (connected but not receiving service). The Culdesac QRU and Woodland -Caribel RFD declined to be connected. | Peck Library, Big Canyon RFD, Sunnyside RFD, City of Reubens, Clearwater Co Ambulance, Annex, Marine Sheriff and Transfer Station facilities; UI Extension, LCSC Outreach had no previous access to broadband | Nez Perce Tribe network provides more desirable service (more affordable, reliable and higher speed) | 3 Mbps - City of Culdesac, City of Reubens, Sunnyside RFD 6 Mbps - Culdesac & Peck Libraries, USFWS, ID F&G 9 Mbps - None 10+ Mbps - Lapwai Library (20 M), Clearwater County facilities (15M) | 3610 | 693 | 150 | 543 | 3 | The baseline projection has been met. | The baseline projection of 463 has been exceeded. | Subscribers on the following towers were unserved:Stoney Pt, Peck, Hubbard, Beard, TU 17, 99-101, 60, Mason | Subscribers on the following towers were underserved:BioControl, Culdesac, Dumbo, TU 64, KIYE, Clwtr Transfer | 3 Mbps - 474 6 Mbps - 184 9 Mbps - 31 | 407 | 12 | 2 | 10 | 3 | The project has enabled connection to businesses by tower site as follows: BioControl (23) Culdesac (18), Peck (13), Hubbard (247), Mason Butte/TU 17 (13), KIYE/TU 64 (93). The baseline projection has been met. | Baseline of 75 has not been met. Marketing efforts continue to target the business community. A recent USDA-Rural Business Opportunity Grant was submitted to hold business broadband adoption workshops across the region in conjunction with the Small Business Development Center and Workforce Development Center with a goal of increasing use of broadband by regional businesses. | The baseline report had 0. The project will continue to market targeting the business community. | Baseline of 75 has not been met. Marketing efforts continue to target the business community. | 3 Mbps - 6 6 Mbps - 5 9 Mbps - 1 | None | FALSE | NA | NA | Nez Perce Tribe | NA | NA | TRUE
NT10BIX5570123 | 2013 | Q3 | Q3 - 2013 | The project completed by the Nez Perce Tribe deployed 175 miles of wireless broadband middle mile infrastructure across the Reservation. The middle mile network is a wireless 200 Mbps which enables last mile service delivery in the communities of Culdesac, Peck, Ahsahka, Orofino-Riverside, Fraser, Kamiah and in rural unincorporated areas. The project passed 3,610 residences, 407 businesses and 18 Community Anchor Institutions (Libraries, Cities, County facilities, Federal facilities and educational institutions). Benefits to the CAI's include providing access to broadband where it was not previously possible, enabling connection of multiple facilities for interoperability and in some instances more affordable access. In addition to constructing the network, the Nez Perce Tribe Dept of Technology Services has added seven full time employees. The project has been completed on time and within budget. Program income has been earned and spent to support electrical utility service to each new tower site; to develop marketing materials; to provide equipment for the neighborhood solutions sites; and to upgrade (200 to 600 Mbps) the back haul links (TU 17 - City Moscow) accessing the ID Regional Optic Network backbone to the Internet. To date Program Income earned is $58,884.00, spent $ 41,719.91, balance $ 17,164.09. | 175 | 0 | 41 | 0 | 0 | 21 | 7 | 16 | 152 Primary network miles; added Culdesac (0.4 m), Dumbo Flat (2.9 m), Shenandoah (9.9 m), Clearwater Trsf (4.75 m), Neville (2 m), Ahsahka (3 m) | NA | TU 17 - W Twin (34.3 m), W Twin - Moscow (6.7 m) paid for with Program Income funds; the upgrade allowed the network to expand backbone connection to Internet via ID Regional Optic Network to 764 Mbps | NA | NA | 15 in Primary network; 6 Neighborhood solutions | Complete | Complete | 2 | 0 | 20 | Washington RSA #8 Limited Partnership, dba Inland Cellular, LLC: Culdesac is 5 year term with Option for 1 additional term; Beard is 5 years term with Option for 3 additional terms | 3 Mbps dedicated bandwidth to support mobile voice/data service delivery in Culdesac-Winchester (Hwy 95) and Fraser/Greer (Hwy 12 & 11)areas | NA | 2 | 0 | 0 | 3 | Inland Cellular - Amgt facilitates expanded mobile service at two sites : Culdesac and Beard | NA | NA | 3 Mbps - 2 10 Mbps -0 20 Mbps -0 | 18 | 11 | 7 | 4 | Fixed broadband service delivered to: Lapwai Library(20 Mbps), Clearwater County Courthouse (15 Mbps), Ambulance (15 Mbps),Marine Sheriff (15 Mbps), Annex (15 Mbps), County Transfer Stn (15 Mbps), County Motorcade Shop (6 Mbps),Culdesac Library (6 Mbps), City of Culdesac (3 Mbps), Peck Library (6 Mbps), Sunnyside RFD (3 Mbps), City of Reubens (3 Mbps), Univ of ID Extension (15 Mbps), LCSC- Orofino Outreach (15 Mbps), USFWS - Dworshak NFH (6 Mbps), ID F&G - Clearwater Hatchery (6 Mbps); and NW Indian College (connected but not receiving service; Big Canyon RFD (connected but not receiving service). The Culdesac QRU and Woodland -Caribel RFD declined to be connected. | Peck Library, Big Canyon RFD, Sunnyside RFD, City of Reubens, Clearwater Co Ambulance, Annex, Marine Sheriff and Transfer Station facilities; UI Extension, LCSC Outreach had no previous access to broadband | Nez Perce Tribe network provides more desirable service (more affordable, reliable and higher speed) | 3 Mbps - City of Culdesac, City of Reubens, Sunnyside RFD 6 Mbps - Culdesac & Peck Libraries, USFWS, ID F&G, Clearwater Motorcade shop 9 Mbps - None 10+ Mbps - Lapwai Library (20 M), Clearwater County facilities (15M) | 3610 | 693 | 150 | 543 | 3 | Baseline projection met | Baseline exceeded | Subscribers on the following towers were unserved:Stoney Pt, Peck, Hubbard, Beard, TU 17, 99-101, 60, Mason | Subscribers on the following towers were underserved:BioControl, Culdesac, Dumbo, TU 64, KIYE, Clwtr Transfer | 3 Mbps - 474 6 Mbps - 184 9 Mbps - 31 | 407 | 13 | 2 | 11 | 3 | The project has enabled connection to businesses by tower site as follows: BioControl (23) Culdesac (18), Peck (13), Hubbard (247), Mason Butte/TU 17 (13), KIYE/TU 64 (93). The baseline projection has been met. | Baseline of 75 has not been met. Marketing efforts continue to target the business community. A recent USDA-Rural Business Opportunity Grant was submitted to hold business broadband adoption workshops across the region in conjunction with the Small Business Development Center and Workforce Development Center with a goal of increasing use of broadband by regional businesses. | Baseline exceeded | Baseline not met, marketing efforts will continue | 3 Mbps - 6 6 Mbps - 5 9 Mbps - 2 | NA | FALSE | NA | NA | Nez Perce Tribe | NA | NA | TRUE
NT10BIX5570125 | 2010 | Q4 | Q4 - 2010 | For this quarter, the environmental work is the primary focus. In addition we pursued and filed our applications to become a Competitive Local Exchange Carrier (CLEC). This status will allow for Interconnection Agreements with existing carriers to further augment the broadband available through this grant project. Detailed project milestone for this quarter include the following: California Local Exchange Carrier applications filed in California and Nevada, Maps prepared for scoping packets, Finalized scoping packets to state agencies and tribal entities, Follow up with all agencies occurred, Documented summary of comments, California Public Utilities Commission coordination of Environmental Assessment documents, Conducted Class 1 Cultural Literature Search, Initiated/ongoing coordination with state and federal agencies, Conduct Habitat Assessment Survey, Conducted any Class III Cultural Field surveys as applicable, Data gathering of resources present, Draft Environmental Assessment work, Continued to work closely with California Governorâ€™s Office, Completed resource field studies and reports, Railroad and California Transportation overhead crossing surveyed for clearance, Final route determined and mapped, Global Positioning System (GPS) key route locations, Overhead Pole Engineering Field work, Design of trench/boring of Hwy 395 underground portion, Professional Engineer review of Underground engineering design, Explored any available conduit and joint use possibi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | We project that we will continue work on the draft environmental assessment with both the federal and state agencies involved. In addition we are working on finalizing our engineering and drawings for the fiber build, and continuing with permit acquisition. We plan to begin work reviewing and fine tuning our wholesale marketing plan and to begin flushing out our business model and business strategies. Meeting with the Critical Anchor Institutions to discuss specifics on construction will be done in this quarter as well. Detailed project milestone for this quarter include the following: Continue preparation of Draft Environmental Assessment and Initial Study (IS), as applicable, Develop Mitigation Monitoring Report Plan (MMRP) for affected resources, Continue consultation with Tribes, State Historic Preservation Offices, United State Forest &Wildlife Service, California & Nevada state agencies, and local permitting authorities, as applicable, Submit Draft Environmental Assessment (DEA), Address any comments from circulation of DEA/IS, Re-circulate DEA/IS, Publish Final Environmental Assessment, Address Environmental Assessment comments, Underground drawings, Competitive Local Exchange Carrier filing completed, Aerial drawings, Continue GPS key route locations (weather permitting), Conduit and joint use agreement negotiation, Private easements found applicable will be pursued, Construction permit acquisition continues, Equipment Request For Proposal's continue, Project | Plumas Sierra Rural Electric Cooperative | n/a | n/a | TRUE
NT10BIX5570125 | 2011 | Q1 | Q1 - 2011 | For this quarter continuing the environmental work was the primary focus. PST has acquired their Competitive Local Exchange Carrier (CLEC) status in NV, and anticipates the California CLEC status to follow next quarter. Detailed project milestones for this quarter include the following: Prepared and filed Draft Environmental Assessment, Began development of Mitigation Report Plan for affected resources, Continued consultation with Tribes, State Historic Preservation Offices, United States Fish & Wildlife Services, California & Nevada state agencies, and local permitting authorities, Began response to comments received on Draft Environmental Assessment, underground drawing work continued, Nevada Competitive Local Exchange Carrier status acquired, California Competitive Local Exchange Carrier application filed and in process, continued Global Positioning System (GPS) of key route locations as weather allowed, Began conduit and joint use agreements with another carrier, continued permit acquisition, and ongoing project administration. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not yet constructed | None | n/a | n/a | Not yet constructed | n/a | n/a | None, not yet constructed | 0 | 0 | 0 | None. | Not yet constructed. | None. | 0 | 0 | 0 | 0 | None, not yet constructed. | None | None | None | 0 | 0 | 0 | 0 | None, not yet constructed. | None | None | None | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | None, not yet constructed | None | None | None | None | To be determined. | FALSE | n/a | We project that we will continue work on the draft environmental assessment with both National Environmental Policy Act (NEPA) and California Environmental Quality Act (CEQA) work concluding at the end of the quarter. Class III Cultural Field Survey work being conducted. In addition we are working towards finalizing the design and engineering work for both the underground and aerial portions of our network. Continued work with Critical Anchor Institutions related to connectivity to our fiber network grant project. Detailed project milestones for this quarter include the following: Negotiations of interconnection and joint use agreement work continues, work on the Mitigation Monitoring Report Plan (MMRP) to ensure it is current and that independent contractors have in order to commence activities upon construction kick-off, coordinate and continue work with the California Public Utilities Commission as it relates to the CEQA, concluding Global Positioning System (GPS) work of the key route locations, acquire private easements if applicable, equipment/materials Request For Proposals (RFP's), aerial drawings, permit acquisition, and project administration. | Plumas Sierra Rural Electric Cooperative | None. | None, at this time | TRUE
NT10BIX5570125 | 2011 | Q2 | Q2 - 2011 | In this quarter continuing the projects environmental work continued to be of primary focus. Both the California CEQA and CLEC was acquired with the NEPA FONSI expected to follow early in next quarter. Detailed project milestones for this quarter are as follows: Continued Environmental Assessment work, Conducted Class 3 Intensive Pedestrian Survey, Continued consultations with tribes, State Historic Preservation Offices, California & Nevada state agencies and local permitting authorities, Developing Mitigation Monitoring Reporting Plan, Worked with California Public Utilities Commission (CPUC), Approval of California Competitive Local Exchange Carrier status and California Environmental Quality Act (CEQA) approval, Began request for proposal (RFP) on limited materials, private easements being pursued,construction permit acquisition continued, interconnection and joint use agreement work continued, Underground and Overhead Engineering work continued,Concluded Global Positioning System(GPS) of key route locations, received a Proportionality Waiver allowing time lapse between PSREC's in-kind match and California grant funds, worked with our federal program officer on refining the non-federal matching portion of the project budget, expanded the Project Funded Service Area to add the Nevada portion of the project to match what was approved in the grant application, revised the Environmental Assessment budget to allow for limited equipment and materials procurement, ongoing proj | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not yet constructed | None | n/a | n/a | Not yet constructed | n/a | n/a | None, not yet constructed | 0 | 0 | 0 | None. | Not yet constructed | None. | 0 | 0 | 0 | 0 | None, not yet constructed | None | None | None | 0 | 0 | 0 | 0 | None, not yet constructed | None | None | None | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | None, not yet constructed | None | None | None | None | To be determined. | FALSE | n/a | We anticipate acquiring our NEPA FONSI this quarter and hope to begin construction following. Multiple facets of the project will begin during this time frame which will include site preparation, material procurement, and construction. Detailed project milestones for the quarter may include the following: Ensure contractors are supplied with the Mitigation Monitoring Reporting Plan (MMRP) and checklist, node and regeneration sites prepped and structure construction, construction permit acquisition continues, material procurement occurring, construction of underground and aerial starting later portion of quarter, network testing as applicable on sections built, ongoing project administration. | Plumas Sierra Rural Electric Cooperative | The environmental process is on track, but required considerable effort and manhours during this current quarter. The emphasis will shift in the early weeks of the next quarter to network design and construction permits. Further technical assistance is not anticipated from the BTOP program. | Fiber cable procurement and delivery dates are being explored with vendors. It is our understanding that many manufacturers are producing maximum amounts they can but with increased demand of fiber currently their lead times are getting pushed out. We will keep the NTIA advised as we acquire further data on this issue and discuss potential impacts with our FPO if any surface. | TRUE
NT10BIX5570125 | 2011 | Q3 | Q3 - 2011 | Continued Environmental work including Mitigation Monitoring Reporting Plan, Prepared Draft Final Environmental Assessment,Continued Request for Proposal's on limited materials, Construction permit acquisition continued, Joint use agreement work continued, Overhead Engineering work and Underground Engineering work continued, Mapping continued,Prepared Performance Improvement Plan (PIP) as requested by NTIA, NTIA site visit completed, Began advertising Grant Controller Position, Started Stormwater Pollution Prevention Plan (SWPPP), Ongoing project Administration. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not yet constructed | None | n/a | n/a | Not yet constructed | n/a | n/a | None, not yet constructed | 0 | 0 | 0 | None | Not yet constructed | None | 0 | 0 | 0 | 0 | None, not yet constructed | None | None | None | 0 | 0 | 0 | 0 | None, not yet constructed | None | None | None | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | None, not yet constructed | None | None | None | None | To be determined. | FALSE | n/a | We anticipate acquiring our NEPA FONSI this quarter. Multiple facets of the project will begin during this time frame which will include continued permit acquisition, engineering work, joint use agreements, interconnection agreements, material procurement. Hiring of a Grant Controller to occur in this quarter. We anticipate 0 network miles will be deployed, 0 new network miles leased, 0 CAI subscribers served or connected, and 0 last mile or broadband wholesale agreements signed, as network construction will likely not commence in Q4 due to material procurement timing. | Plumas Sierra Rural Electric Cooperative | Delay in acquiring the FONSI has had a trickle down affect in other areas as forecasted in the baseline. We anticipate FONSI being acquired in the fourth quarter of 2011. | None. | TRUE
NT10BIX5570125 | 2011 | Q4 | Q4 - 2011 | We acquired our NEPA Finding of No Significant Impact which will allow us to begin construction in 2012. We continued permit acquisition, engineering work, joint use agreements, material procurement, hired a grant controller, mapping, material request for proposals, legal consultation and work, bond acquisition, environmental work, on going project management. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not yet constructed. | None | n/a | n/a | not yet constructed. | n/a | n/a | None, not yet constructed | 0 | 0 | 0 | None at this time. | Not yet constructed. | None. | 0 | 0 | 0 | 0 | None, not yet constructed. | None | None | None | 0 | 0 | 0 | 0 | None, not yet constructed | None | None | None | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | None, not yet constructed. | None | None | None | None | To be determined. | FALSE | n/a | We will be continuing our rights of way work, acquiring construction permits, equipment procurement, equipment RFP work, legal work, budget realignment work, joint use application work, and constructing as feasible with material deliveries and weather, as well as ongoing project management. Forecasted Project Indicators for the quarter are as follows: New network miles deployed 27, New Network Miles Leased 0, Total CAI subscribers served (CAI's connected) 0, Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers 0 | Plumas Sierra Rural Electric Cooperative | None. | None. | TRUE
NT10BIX5570125 | 2012 | Q1 | Q1 - 2012 | Environmental work related to pending AAR that makes minor changes to the fiber network route out of Reno, NV and includes purchasing of existing conduit eliminating the need for underground work in this area, Continued Request for Proposal's for node site preparation, electronics, and pole mounted splice enclosures, Materials procurement, Construction permit acquisition continued, Joint use agreement & interconnection agreement work, joint use pole calculations, Overhead Engineering work, Underground Engineering work, Mapping, Hired an outside plant engineer, Fiber testing, Surveying of third party existing conduit infrastructure, Ongoing project Administration, Began Aerial & Underground construction, Traffic control plan development, completed a Performance Improvement Plan. | 50 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | We built an additional 23 miles over the previous project indicators projection. Due to the mild winter in our region we were able to construct more than originally anticipated. | n/a | n/a | n/a; with approval of AAR No. 2270354 which included a reno route change and thereby eliminated any leasing of network miles to be a part of our project. | We built an additional 23 miles over the previous project indicators projection. Due to the mild winter in our region we were able to construct more than originally anticipated. | n/a | n/a | None. | 0 | 0 | 0 | None. | None as of yet. | None. | 0 | 0 | 0 | 0 | None | None | None | None | 0 | 0 | 0 | 0 | None | None | None | None | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | To be determined. | FALSE | N/A | Construction of Aerial and Underground continues, Node ground preparation occurring, continued material procurement (related to Operation software, electronics, construction), fiber testing, vault placement, rights of way work and permitting as related to approved route change, traffic control, legal work, continued interconnection and joint use application work, budget realignment, ongoing project management. Forecasted Project Indicators for the quarter are as follows: New Network Miles Deployed: 83.5, New Network Miles Leased: 0, Total CAI Subscribers Served (CAIS connected): 0, Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers: 0 | Plumas Sierra Rural Electric Cooperative | None. | None. | TRUE
NT10BIX5570125 | 2012 | Q2 | Q2 - 2012 | Significant deployment of Fiber Cable (92 miles this quarter), Delivery and placement of all Node buildings, Completed conduit purchase, Fiber Testing, Materials procurement, Construction permit acquisition continued, Joint use agreement & interconnection agreement work, joint use pole calculations, Overhead Engineering work, Underground Engineering work, Mapping, Fiber Placing, Fiber Testing, Fiber Splicing, Cabinet & Vault installation, Traffic control, Ongoing project management. | 142 | 0 | 0 | 0 | 142 | 0 | 0 | 0 | We built an additional 58.5 miles over the previous project indicators projection. Due to improved construction schedules and improved efficiency we were able to construct more than originally anticipated. | n/a | n/a | n/a | We built an additional 58.5 miles over the previous project indicators projection. Due to improved construction schedules and improved efficiency we were able to construct more than originally anticipated. | n/a | n/a | None | 0 | 0 | 0 | None. | None as of yet. | None. | 0 | 0 | 0 | 0 | None. | None. | None. | None. | 0 | 0 | 0 | 0 | We donâ€™t think we will be connecting any CAIâ€™s by 09/30/12; however, we should have at least 15 of our CAIs connected by the next quarter ending 12/31/1. | None. | None. | None. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | To be determined. | FALSE | N/A | Construction of Aerial and Underground continues, Node ground preparation occurring, continued material procurement (related to Operation software and electronics, fiber testing, vault placement, rights of way work and permitting as related to approved route change, traffic control, legal work, continued interconnection and joint use application work, budget realignment, ongoing project management. Forecasted Project Indicators for the quarter are as follows: New Network Miles Deployed: 197, New Network Miles Leased: 0, Total CAI Subscribers Served (CAIS connected): 0, Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers: 0 | Plumas Sierra Rural Electric Cooperative | None. | None | TRUE
NT10BIX5570125 | 2012 | Q3 | Q3 - 2012 | Significant deployment of Fiber Cable (181 miles to date) from Beckworth to Quincy, in Reno, and along the Sprint rout. Ongoing preparation of all Node buildings in Portola, Quincy, and Susanville., Fiber splicing and testing has begun along the entire backbone of the system, Materials procurement has continued with current purchases being made mostly for hardware and materials used for Node construction. Construction permit acquisition continued in Reno, Quincy, and Portola. Joint use agreement & interconnection agreement work has been ongoing in Reno, Quincy, Portola and Susanville, Joint use pole calculations are being prepared for the distribution through Susanville, Overhead Engineering continues in Susanville, Portola, and Quincy, Underground Engineering continues in Reno and Quincy. Mapping has been ongoing over the entire backbone. Cabinet & Vault installation has been ongoing along the entire backbone where needed. Traffic control has been performed in Reno, along the Sprint route, and from Hallelejuha Junction to the outskirts of Quincy. Ongoing project management continues. | 181 | 0 | 0 | 0 | 181 | 0 | 0 | 0 | We were under our previous project indicators projection by 16 miles. Delays were caused by Joint Use complications, and increased pole engineering requirements in and around the City of Susanville. There were also permitting issues in the City of Reno. | n/a | n/a | n/a | We were under our previous project indicators projection by 16 miles. Delays were caused by Joint Use complications, and increased pole engineering requirements in and around the City of Susanville. There were also permitting issues in the City of Reno. | n/a | n/a | n/a | 0 | 0 | 0 | None. | None as of yet. | None. | 0 | 0 | 0 | 0 | None. | None. | None. | None. | 0 | 0 | 0 | 0 | We should have 8 of our CAIs connected by 12/31/12. | None. | None | None. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | To be determined. | FALSE | n/a | Construction of Aerial and Underground will continue in Reno, from Leavitt to Susanville, and the distribution ares of Loyalton, Susanville, Portola, and Quincy. There will be minimal material procurement for the aforementioned areas as most hardware needed has already been purchased. There will be procurement and installation of electronics and operating software in all of the Nodes - Quincy, Susanville, and the main Node in Portola. Fiber splicing and testing will occur along the entire backbone. Vault and box placement will be occurring in Reno, Portola, and Quincy. Traffic control will be needed in Reno and Quincy, Ongoing legal work will be needed as it relates to interconnection agreements. Joint use application work will be performed for construction in Susanville. The budget realignment should be finished. Ongoing project management will continue. Forecasted Project Indicators for the quarter are as follows: New Network Miles Deployed: 200, New Network Miles Leased: 0, Total CAI Subscribers Served (CAIS connected): 8, Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers: 0 | Plumas Sierra Rural Electric Cooperative | None. | None. | TRUE
NT10BIX5570125 | 2012 | Q4 | Q4 - 2012 | Completed construction and preparation of all Node buildings in Portola, Quincy, and Susanville. The majority or our electronics were purchased and installed in same Nodes. Fiber splicing and testing continues along the entire backbone of the system, Materials procurement has dropped off with completion of Node buildings. Construction permit acquisition continued in Reno, Quincy, and Portola. Joint use agreement & interconnection agreement work has been ongoing in Reno, Quincy, Portola and Susanville, Joint use pole calculations were completed in Susanville. Overhead Engineering continues in Portola, and Quincy, Underground Engineering continues in Reno and Quincy. Mapping has been ongoing over the entire backbone. Cabinet & Vault installation has been ongoing along the entire backbone where needed. Traffic control was performed in Reno. Ongoing project management continues. | 182 | 0 | 0 | 0 | 182 | 0 | 0 | 0 | We were under our previous project indicators projection by 18 miles. Delays were caused by Joint Use complications, and increased pole engineering requirements in and around the City of Susanville. There were also permitting delays in the City of Reno. | n/a | n/a | n/a | We were under our previous project indicators projection by 18 miles. Delays were caused by Joint Use complications, and increased pole engineering requirements in and around the City of Susanville. There were also permitting delays in the City of Reno. | n/a | n/a | n/a | 0 | 2 | 40 | None | None as of yet. | None | 0 | 0 | 0 | 0 | None | None | None | None | 0 | 0 | 0 | 0 | We should have 4 of CAIs connected by 03/31/12. Our previous project indicators anticipated that we would have 8 CAIs connected by 12/31/12. This did not occur due to construction delays in Susanville (documented in section 3). | None | None | None | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | To be determined. | FALSE | n/a | Construction of Aerial and Underground will continue in Reno, from Leavitt to Susanville, and the distribution ares of Loyalton, Susanville, Portola, and Quincy. There will be minimal material procurement for the aforementioned areas as most hardware needed has already been purchased. There will be installation of electronics and operating software in all of the Nodes - Quincy, Susanville, and the main Node in Portola. Fiber splicing and testing will occur along the entire backbone. Vault and box placement will be occurring in Reno, Portola, and Quincy. Traffic control will be needed in Reno and Quincy, Ongoing legal work will be needed as it relates to interconnection agreements. Joint use application work will be performed for construction in Quincy. The budget realignment should be finished. Ongoing project management will continue. Forecasted Project Indicators for the quarter are as follows: New Network Miles Deployed: 200, New Network Miles Leased: 0, Total CAI Subscribers Served (CAIS connected): 4, Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers: 2 | Plumas Sierra Rural Electric Cooperative | Construction in Susanville was delayed due to a significant number of poles failing to pass the increased safety requirements of the CPUC (California Public Utilities Commission). The CPUC increased the Safety Factor from 2.1 to 4.0 with General Order 95. There are approximately 135 poles that do not meet the new safety standard. To replace these poles will cost an additional $2.1 million. We are exploring alternative solutions. Our FPO has been consulted regularly with this development. | None. | TRUE
NT10BIX5570125 | 2013 | Q1 | Q1 - 2013 | Fiber splicing and testing continues along the entire backbone of the system. Construction permit acquisition continued in Reno, Quincy, and Portola. Joint use agreement & interconnection agreement work has been ongoing in Reno, Quincy, and Portola. Mapping has been ongoing over the entire backbone. Cabinet & Vault installation has been ongoing along the entire backbone where needed. Traffic control was performed in Reno. Ongoing project management continues. Electronic equipment has been installed with more to follow. Testing has begun on all electric equipment. | 183 | 0 | 0 | 0 | 183 | 0 | 0 | 0 | We were under our previous project indicators projection by 17 miles. Delays were caused by Joint Use complications, and increased pole engineering requirements in and around the City of Susanville. There were also permitting delays in the City of Reno. | n/a | n/a | n/a | We were under our previous project indicators projection by 17 miles. Delays were caused by Joint Use complications, and increased pole engineering requirements in and around the City of Susanville. There were also permitting delays in the City of Reno. | n/a | n/a | n/a | 1 | 3 | 80 | Confidential | Transport | None | 0 | 0 | 0 | 0 | None | None | None | None | 0 | 0 | 0 | 0 | We should have 12 CAIs connected by 06/30/13. Our previous project indicators anticipated that we would have 4 CAIs connected by 03/31/13. This did not occur due to construction delays in Susanville (documented in section 3). | None | None | None | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | To be determined | FALSE | n/a | Construction of Aerial and Underground will be complete in Reno, complete from Leavitt to Susanville. Construction will continue in the distribution ares of Susanville, Portola, and Quincy. There will be minimal material procurement for the aforementioned areas as most hardware needed has already been purchased. There will be installation and testing of electronics and operating software in all of the Nodes - Quincy, Susanville, and the main Node in Portola. Fiber splicing and testing will occur along the entire backbone. Vault and box placement will be occurring in Portola and Quincy. Traffic control will be needed in Quincy and Portola, Ongoing legal work will be needed as it relates to interconnection agreements. Joint use application work will be performed for construction in Quincy. The budget realignment should be finished. Ongoing project management will continue. Forecasted Project Indicators for the quarter are as follows: New Network Miles Deployed: 200, New Network Miles Leased: 0, Total CAI Subscribers Served (CAIS connected): 12, Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers: 3 | Plumas Sierra Rural Electric Cooperative | Construction in Susanville continues to be delayed due to a significant number of poles failing to pass the increased safety requirements of the CPUC (California Public Utilities Commission). The CPUC increased the Safety Factor from 2.1 to 4.0 with General Order 95. There are approximately 135 poles that do not meet the new safety standard. To replace these poles will cost an additional $2.1 million. We are exploring alternative solutions. Our FPO has been consulted regularly with this development. | We have had major delays with our deployment in Susanville. We anticipate making an appropriate route change to ensure we are able to serve those areas and CAI's that are required by the ARRA grant. This will be a lengthy process and will require an AAR (Awards Action Request) and the facilitation of our FPO. The budget realignment has been a larger than anticipated project. Due to the ongoing route changes experienced during this project, the budget realignment has likewise undergone several changes in direction that have required the appropriate recalculation of expenditures. The high degree of accountability required with the use of public funds has necessitated that this process be very thorough which has required the appropriate amount accompanying time. | TRUE
NT10BIX5570125 | 2013 | Q2 | Q2 - 2013 | Construction of Aerial and Underground was completed in Reno. Lease of Dark Fiber Distribution Fiber was completed in Susanville. Fiber was lit from Reno to Susanville. Fiber splicing and testing continues along the entire backbone of the system. Construction permit acquisition continued in Quincy, and Portola. Joint use agreement & interconnection agreement work has been ongoing Quincy and Portola. Mapping has been ongoing over the entire backbone. Cabinet & Vault installation has been ongoing along the entire backbone where needed. Traffic control was performed in Reno, Portola, and Quincy. Ongoing project management continues. Electronic equipment has been installed and tested with more to follow. Testing has begun on all electric equipment. | 183 | 9 | 0 | 0 | 183 | 0 | 0 | 0 | We were under our previous project indicators projection by 17 miles. Delays were caused by Joint Use complications in Quncy and Portola, and terrain difficulties in Quincy. We revised our total "New Miles" estimate downwards to 189.26 due to the lease of dark fiber in the distribution area in Susanville | We are over our previous project indicators by 9.23 miles. We did not anticipate leasing dark fiber in Susanville by the end of the 1st Qtr of 2013, so it was never included as an estimate. | N/A | N/A | We were under our previous project indicators projection by 8 miles. Delays were caused by Joint Use complications in Quncy and Portola, and terrain difficulties in Quincy. We revised our total "New Miles" estimate downwards to 189.26 due to the lease of dark fiber in the distribution area in Susanville | N/A | N/A | N/A | 1 | 3 | 80 | Zito Media | Transport | None | 1 | 0 | 0 | 10 | Baseline had predicted 4 by this quarter. Negotiations continue with 2 providers. There are presently no negatiations with a 4th provider, although the possibility of signing a 4th provider has not been ruled out. | none | none | 1 @ 600 Mg. | 2 | 0 | 0 | 10 | High Desert State Prison, California Correctional Center | none | none | These CAI's have been connected, but are not currently subscribed to our network. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | To be Determined | FALSE | N/A | Construction of Aerial and Underground will be complete in the distribution ares of Susanville, Portola, and Quincy. Completion of installation and testing of electronics and operating software in all of the Nodes. Fiber splicing and testing will be completed along the entire backbone. All construction will be be completed in Portola and Quincy. Ongoing legal work will be needed as it relates to interconnection agreements. Ongoing project management will continue. Forecasted Project Indicators for the quarter are as follows: New Network Miles Deployed: 189, New Network Miles Leased: 9, Total CAI Subscribers Served (CAIS connected): 17, Number of Signed Agreements with Broadband Wholesalers or Last Mile Providers: 3 | Plumas Sierra Rural Electric Cooperative | We had major delays with our deployment in Susanville which required us to request a route change to ensure that we will be able to serve those areas and CAI's that are required by the ARRA grant. This was a lengthy process and required an AAR (Awards Action Request) and the appropriate help from our FPO. Additionally, we have experienced delays in Quincy due mostly to rocky soil hindering our boring progress. T | We have had major delays with our network build in Quincy, mostly due to rocky soil hindering our boring efforts. There is a possibility that these delays will require us to ask for a "no cost" extension of the project. This will require the facilitation of our FPO. | TRUE
NT10BIX5570125 | 2013 | Q3 | Q3 - 2013 | Construction of Aerial and Underground was completed in Reno. Lease of Dark Fiber Distribution Fiber was completed in Susanville. Fiber was lit from Reno to Susanville. Construction permit acquisition occurred in Quincy, and Portola. Joint use agreement & interconnection agreement work occurred in Quincy and Portola. Mapping occurred over the entire backbone. Cabinet & Vault installation occurred along the entire backbone where needed. Traffic control was performed in Reno, Portola, and Quincy. Ongoing Project management occurred. Electronic equipment has been installed. | 189 | 9 | 0 | 0 | 189 | 0 | 0 | 0 | On target with previous previous Project Indicators. | On target with previous previous Project Indicators. | N/A | N/A | On target with previous previous Project Indicators. | N/A | N/A | N/A | 2 | 5 | 50 | Zito Media, Verizon | Transport and Access. | NONE | 2 | 0 | 0 | 10 | Baseline had predicted 4 by this quarter. Negotiations continue with 3 more providers, which if signed would make 5. | None | None | 1 @ 600 Mg. 1 @ 1 Gg, 300 Mg, and 200Mg | 17 | 0 | 17 | 6 | Sierra Army Depot, Feather River College, Plumas District Hospital, City of Portola, City of Loyalton, Eastern Plumas Health Care, California Correctional Center, High Desert State Prison, Lassen Community College, Plumas COE, Loyalton HS, Herlong HS, Portola HS, Quincy HS, Loyalton Elementary, Herlong Indian Rancheria, Lassen COE | None | All subscribers will receive improved access. As of September 30, 2013 there are only two Community Anchor Institutions that are receiving service. | 20Mg - 0, 25Mg - 1, 30Mg - 0, 40Mg - 0, 50Mg - 0, 100Mg - 1 | 19000 | 0 | 0 | 0 | 0 | Demographic Estimate | N/A | N/A | N/A | N/A | 2500 | 0 | 0 | 0 | 0 | Demographic Estimate | N/A | N/A | N/A | N/A | To be Determined | FALSE | N/A | Over the next quarter we will complete the Grant close-out process. We will submit our UCC-1 Filings to Plumas, Sierra, and Lassen Counties. We will complete the final audit. | Plumas Sierra Rural Electric Cooperative | We had major delays with our network build in Quincy, mostly due to rocky soil hindering our boring efforts. These delays required us to request a "no cost" extension to the project through September 30, 2013. This request was granted. All construction was completed by September 30, 2013. | We are in the close-out phase of the grant. This will occur over the last three months of the year. We anticipate that there is an average chance (50/50) that there will be some delays due to the holiday season. If there are delays we will file an AAR requesting a close-out extension. | TRUE
NT10BIX5570126 | 2010 | Q4 | Q4 - 2010 | Hired a CEO to lead CVIN (Central Valley Independent Network) in building and operating the project. Finalized the agreement with our partner and sub-recipient Corporation for Education Network Initiatives in California (CENIC). Our Environmental Assessment (EA) draft is substantially complete. Our goal is to submit the draft several days earlier than the deadline of February 1, 2011. We processed our first federal funds request to pay for expenses associated with our 6 Month EA Procurement Budget. Anchor Institution site visits and city/county leadership meetings are complete. This involved site visits and meetings with all 63 anchor institutions to determine cabinet locations, building entry points, and plans for route diversity where appropriate. We met with road authorities in each county and each city our project construction effects to identify the best route through each community to minimize disruption of roadways. Each authority has expressed a willingness to work together to simplify the right-of-way process. We also met with leadership in all 18 counties and many communities to determine how our project could best meet their economic development needs. These meetings have allowed us to create a good working relationship with those effected by our project. The information gathered will aid in the detailed engineering process, minimize route changes that could effect environmental assessment and streamline right-of-way procurement processes. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 36 | 0 | N/A construction has not yet begun | N/A construction has not yet begun | Once project is complete, the services provided to anchor institutions will be managed by our partner, Corporation for Education Network Initiatives in California (CENIC) who is a sub-recipient. We (CVIN) will manage all commercial services to third party providers, business and residential customers. CENIC's Chief Technology Officer, David Reese, is their operations contact for the project (dave@cenic.org, 714-220-3444). | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | We will submit EA draft earlier than February 1, 2011 deadline. We will also substantially complete California environment assessment process (CEQA). We will issue RFP for detailed engineering design on middle mile portion of project and award engineering contract. We will issue RFP for detailed engineering design on wireless last mile portion of project, award engineering contract and commence detailed engineering. We will identify specific wireless equipment site locations, acquire necessary spectrum licensing and conduct field evaluation of wireless equipment vendors. | CVIN, LLC | N/A | Consultation with Fish and Wildlife Service will be a significant factor in making progress toward completion of the Environmental Assessment. Continued assistance from NTIA in this matter would be helpful. | TRUE
NT10BIX5570126 | 2011 | Q1 | Q1 - 2011 | The Environmental Assessment (EA) draft was submitted to the National Telecommunications and Information Administration (NTIA) on January 18, 2011 well ahead of schedule. Biological and cultural field surveys were initiated for the project in multiple counties. Habitat mapping work was largely completed by the environmental team. California Environmental Quality Act (CEQA) coordination and planning between the project environmental consultants and the California Public Utilities Commission (CPUC) staff increased. The Engineering Design contract was competitively bid out. 18 engineering firms attended a Pre-bid Conference held by Central Valley Independent Network (CVIN) on February 16, 2011, 6 formal engineering bids were received by March 18, 2011 and the contract was awarded on March 30, 2011. CVIN launched a Student Internship Program with several California Universities to recruit advanced students of Engineering and Construction Management that will serve to monitor and record all construction compliance activities by construction contractors. Some of these internships could very well evolve into permanent positions. CVIN has filled several key grant funded staff positions including Construction Manager, Grant Administrator and Outside Plant Manager as well as three additional key administrative staff positions. Efforts have continued regarding wireless spectrum analysis and acquisition in anticipation of construction of the fixed wireless broadband portion of th | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not yet begun | N/A | Not yet begun | Not yet begun | Not yet begun | Not yet begun | Not yet begun | Not yet begun | 0 | 36 | 0 | N/A as construction has not yet begun. | N/A as construction has not yet begunt begun. | Once the project is complete, the services provided to Anchor Institutions will be managed by our partner, the Corporation for Education Network Initiatives in California (CENIC) who is a sub-recipient. We (CVIN) will manage all commercial services to third party providers, business and residential customers. CENIC's Chief Technology Officer, David Reese, is their operations contact for the project (dave@cenic.org, 714-220-3444). | 0 | 0 | 0 | 0 | Not yet begun | Not yet begun | Not yet begun | Not yet begun | 0 | 0 | 0 | 0 | Not yet begun | Not yet begun | Not yet begun | Not yet begun | 0 | 0 | 0 | 0 | 0 | Not yet begun | Not yet begun | Not yet begun | N/A | Not yet begun | 0 | 0 | 0 | 0 | 0 | Not yet begun | Not yet begun | Not yet begun | N/A | Not yet begun | N/A | FALSE | N/A | California Environmental Quality Act (CEQA) and National Environmental Policy Act (NEPA) requirements are expected to be completed. All of the Network Design and Engineering Plans are expected to be completed. We will begin preparing and submitting applications for Right of Way, construction permits, and other approvals. We will issue Purchase Orders for construction materials and electronics that have long lead times in preparation for construction. We will prepare the Request For Proposal (RFP) to competitively bid out construction contracts and will also conduct a Pre-bid Conference to encourage competitive contractor bids for the project. Detailed engineering for the fixed wireless broadband portion of the project will be complete. | CVIN, LLC | Environmental work is still progressing and until both the California Environmental Quality Act (CEQA) and National Environmental Policy Act (NEPA) requirements are completed, the project construction cannot commence. All the environmental work is scheduled to be completed by the summer of 2011. The official Federal and State adoptions/approvals will fall between late Q2-2011 and early Q3-2011. Project construction will commence immediately following these environmental clearances. | Commencement of construction activities still hinges on completion and acceptance of environmental assessment activities. Continued assistance with tribal, cultural, biological and Army Corps of Engineers issues is appreciated. | TRUE
NT10BIX5570126 | 2011 | Q2 | Q2 - 2011 | The Revised Draft Environmental Assessment (EA) was submitted to the National Telecommunications and Information Administration (NTIA) on June 30, 2011 for commenting. All biological and habitat studies, maps and surveys were submitted to the United States Department of Fish and Wildlife (USFWS) on June 29, 2011. NTIA also prepared a letter to USFWS requesting concurrence that the project may affect, but is not likely to adversely affect Federally-listed species. The Engineering Design work commenced for all segments of the CVIN Project alignment. Permit applications commenced for all multi-jurisdictional approvals and encroachment permits. CVIN conducted a Pre-bid Conference for Pre-qualified Construction Contractors presented by CVIN on June 28, 2011. CVIN has prepared and is ready to commence the first several segment construction bid packages for competitive bidding. CVIN is preparing to finalize the Student Internship Program with several California Universities to recruit advanced students of Engineering and Construction Management that will serve to monitor and record all construction compliance activities of the construction contractors. Some of these internships could very well evolve into permanent positions. CVIN has retained several key grant funded staff positions including Construction Manager, Grant Administrator and Outside Plant Manager as well as three additional key administrative staff positions. CVIN has hired 1 new full-time position for Const | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The FONSI has not been issued by NTIA, as a result no deployment or construction can commence. | N/A | Not yet begun | Not yet begun | Not yet begun | Not yet begun | Not yet begun | Not yet begun Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) The FONSI has not been issued by NTIA, as a result no deployment or construction can commencee your reasons for any variance from the baseline plan or any other relevant information) The FONSI has not been issued by NTIA, as a result no deployment or construction can commence. | 0 | 36 | 0 | N/A as construction has not yet begun. | N/A as construction has not yet begunt begun. | Once the project is complete, the services provided to Anchor Institutions will be managed by our partner, the Corporation for Education Network Initiatives in California (CENIC) who is a sub-recipient. We (CVIN) will manage all commercial services to third party providers, business and residential customers. CENIC's Chief Technology Officer, David Reese, is their operations contact for the project (dave@cenic.org, 714-220-3444). | 0 | 0 | 0 | 0 | Not yet begun | Not yet begun | Not yet begun | Not yet begun | 0 | 0 | 0 | 0 | Not yet begun | Not yet begun | N/A | Not yet begun | 0 | 0 | 0 | 0 | 0 | Not yet begun | Not yet begun | Not yet begun | N/A | Not yet begun | 0 | 0 | 0 | 0 | 0 | Not yet begun | Not yet begun | Not yet begun | N/A | Not yet begun | N/A | FALSE | N/A | NTIA comments are expected back to CVIN in July of 2011 for incorporation into the final EA document. In addition, the Bureau of Land Management (BLM) will submit EA comments to the NTIA in July of 2011. The National Environmental Policy Act (NEPA) requirements are expected to be completed. CVIN will complete the California Environmental Quality Act (CEQA) requirements for the project as the California Public Utilities Commission (CPUC) considers the adoption of the CVIN Project's proposed environmental study and findings of a Negative Declaration on July 14, 2011. Construction contractors will be procured and under contract with CVIN. Materials will be procured and received by CVIN. Many of the Permits required for construction will be completed and approved by jurisdictions. Construction and inspection monitoring will commence for several segments for the CVIN Project. Additional CVIN staff will be hired to help manage construction activities. | CVIN, LLC | CVIN has completed all the environmental assessments. The CEQA adoption was delayed by the California Public Utilities Commission and is now expected for July 14, 2011 adoption. The NEPA requirements are not completed therefore project construction cannot commence. The remaining NEPA requirements include: the Final EA submission to NTIA by the end of July 2011; Letters of Concurrence from USFWS and SHPO. CVIN has been waiting for the letters of concurrence for almost 2 months from SHPO and over a month from USFWS. The letters of concurrence have been significantly delayed and it has been difficult to receive communications from these agencies. The Final EA preparation is currently incorporating final comments from the NTIA and BLM and will be submitted to NTIA any day. Once the letters of concurrence are submitted to NTIA and a FONSI is completed, project construction will commence immediately as CVIN is already preparing bid packages for construction. | Commencement of construction activities still hinges on NEPA completion and acceptance of environmental assessment activities. Continued assistance with tribal, cultural, biological, USFWS, SHPO, BLM and Army Corps of Engineers issues is appreciated. | TRUE
NT10BIX5570126 | 2011 | Q3 | Q3 - 2011 | Environmental assessment (EA) processes continued through this quarter. The California Environmental Quality Act (CEQA) study was completed and adopted as a Negative Declaration by the California Public Utilities Commission (CPUC) on July 14, 2011. The National Environmental Policy Act (NEPA) final EA study was submitted to National Telecommunications and Information Administration (NTIA) for review. Federal agency concurrence and initial notification of a Finding of No Significant Impact (FONSI) was received on September 30, 2011. CVIN has hired additional key staff members including a CAD Specialist, Construction Accountant, and Network Manager in anticipation of beginning project construction early in quarter four of 2011. CVIN is also preparing to hire Network Specialists and Construction Inspectors. Detailed project engineering is completed. The project has been broken down into 30 construction segments. The first segment was bid out to construction contractors on August 30, 2011 and final competitive bids were received on September 27, 2011. Several additional segments have been bid out and are awaiting bid submittals from construction contractors. Additional pre-bid conferences have been conducted to qualify new construction contractors to participate in upcoming construction bids. Initial orders for conduit and fiber optic cable have been placed and are staged for immediate delivery. All grant fund expenditures this quarter are included in our approved 10-month Exten | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction could not commence since the FONSI was not issued until September 30, 2011. | N/A | Construction could not commence since the FONSI was not issued until September 30, 2011. | Construction could not commence since the FONSI was not issued until September 30, 2011. | Construction could not commence since the FONSI was not issued until September 30, 2011. | No change from the baseline. | No change from the baseline. | Construction could not commence since the FONSI was not issued until September 30, 2011e since the FONSI was not issued until September 30, 2011. | 0 | 36 | 0 | N/A as construction has not yet begun. | N/A as construction has not yet begunt begun. | Once the project is complete, the services provided to Anchor Institutions will be managed by our partner, the Corporation for Education Network Initiatives in California (CENIC) who is a sub-recipient. We (CVIN) will manage all commercial services to third party providers, business and residential customers. CENIC's Chief Technology Officer, David Reese, is their operations contact for the project (dave@cenic.org, 714-220-3444). | 0 | 0 | 0 | 0 | No change from the baseline. | Construction could not commence since the FONSI was not issued until September 30, 2011. | No change from the baseline. | Construction could not commence since the FONSI was not issued until September 30, 2011. | 0 | 0 | 0 | 0 | Construction could not commence since the FONSI was not issued until September 30, 2011. | Construction could not commence since the FONSI was not issued until September 30, 2011. | N/A | Construction could not commence since the FONSI was not issued until September 30, 2011. | 0 | 0 | 0 | 0 | 0 | No change from the baseline. | No change from the baseline. | No change from the baseline. | N/A | No change from the baseline. | 0 | 0 | 0 | 0 | 0 | No change from the baseline. | No change from the baseline. | No change from the baseline. | N/A | No change from the baseline. | N/A | FALSE | N/A | CVIN anticipates the delivery of additional materials and the commencement of construction. In addition, CVIN anticipates conducting the first public ground-breaking ceremony to include various public and community officials. CVIN anticipates contracting biological and cultural resource specialist to monitor construction activities for compliance to both CEQA and NEPA Plans. In addition, CVIN anticipates hiring Construction Inspectors to monitor construction contractor activities. CVIN anticipates completing various permitting agreements and additional construction segment contracts to progressively advance construction. We intend to have at least 100 miles of new network deployed and 185 miles of upgraded network, but won't have any leased network miles yet. We will have two signed agreements with last mile providers but won't be in a position to connect any CAI's yet. There have been some slight adjustments in Budget Classifications which will remain under 10% of the total budget. We will work with our Grants Officer to address any budget updates that need to be reflected on next quarter's PPR. | CVIN, LLC | One of the greatest challenges for CVIN which delayed the Final Environmental Assessment (EA) submission to the NTIA to complete NEPA and obtain the FONSI was the delay in receiving the final concurrence letter from the USFWS. The NTIA officials assisted CVIN by outreaching to USFWS to receive the final letter of concurrence on September 14, 2011. This allowed CVIN environmental consultants to finalize the EA for NTIA. CVIN commends the exceptional effort and support provided by NTIA to assist CVIN on reaching a major milestone. CVIN has submitted a number of construction permit applications with various jurisdictions for review and is working with their professional staff to meet conditions for approvals. | Construction will commence this quarter. The expectation of significant progress will hinge on effective biological and cultural monitoring as well as cooperation from rights of way and permitting authorities. | TRUE
NT10BIX5570126 | 2011 | Q4 | Q4 - 2011 | Permitting processes continued through this quarter and construction began in December. CVIN has hired an additional key staff member as Inventory Manager. CVIN also retained the services of a construction inspection firm and environmental monitoring firms. These firms work closely with CVIN staff and construction contractors to insure compliance with all aspects of grant project construction. The project has been broken down into 30 segments. Twenty-two (22) segments have been bid, eighteen (18) segments have been awarded, and six (6) segments have started construction. So far, 25 miles of conduit has been installed. All conduit and fiber optic cable has been ordered. To date, we have received 200 miles of conduit and 100 miles of fiber optic cable. An official ground breaking ceremony was held on December 9, 2011 in Fresno, CA at California State University Fresno. The event was well attended by CVIN staff, project stakeholders, as well as various other local government officials. Speakers included CVIN CEO David Nelson, CENIC CEO Jim Dolgonas, NTIA BTOP Program Director Tony Wilhelm, California Governors Office Director of Economic Development Joel Ayala, and CSUF President John Welty. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Slightly behind construction schedule due to delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No fiber has been installed. | N/A | Slightly behind construction schedule due to delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No fiber has been installed. | Slightly behind construction schedule due to delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No fiber has been installed. | Slightly behind construction schedule due to delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No fiber has been installed. | No change from baseline. | Behind schedule on construction due to delays in acquiring FONSI and construction permits. | Behind schedule on construction due to delays in acquiring FONSI and construction permits. | 2 | 34 | 16 | Sebastian Corp (DBA: Audeamus) Sierra Tel Internet | Internet access bandwidth at 500 Mbps to 1 Gbps (see attached pricing plans). | Once the project is complete, the services provided to Anchor Institutions will be managed by our partner, the Corporation for Education Network Initiatives in California (CENIC) who is a sub-recipient. We (CVIN) will manage all commercial services to third party providers, business and residential customers. CENIC's Chief Technology Officer, David Reese, is their operations contact for the project (dave@cenic.org, 714-220-3444). | 0 | 2 | 0 | 2 | Behind schedule on construction due to delays in acquiring FONSI and construction permits. | Behind schedule on construction due to delays in acquiring FONSI and construction permits. | No change from the baseline. | We have two wholesalers, one at 500Mbps and one at 2Gbps | 0 | 0 | 0 | 0 | Behind schedule on construction due to delays in acquiring FONSI and construction permits. | Behind schedule on construction due to delays in acquiring FONSI and construction permits. | Behind schedule on construction due to delays in acquiring FONSI and construction permits. | Behind schedule on construction due to delays in acquiring FONSI and construction permits. | 0 | 0 | 0 | 0 | 0 | Slightly behind construction schedule due to delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | No change from the baseline. | No change from the baseline. | No change from the baseline. | No change from the baseline. | 0 | 0 | 0 | 0 | 0 | Slightly behind construction schedule due to delays in acquiring FONSI and construction permits. Construction is focused on placement of underground conduit. No middle mile fiber or last mile wireless has been installed. | No change from the baseline. | No change from the baseline. | No change from the baseline. | No change from the baseline. | N/A | FALSE | N/A | Rights-of-way, permits and other approvals should be complete. CVIN anticipates that all construction segments will be awarded and significant progress will be made on construction of underground facilities. Equipment procurement will be ramped up and up to 50% of the equipment should be on hand. With construction focused on building underground facilities, new network (fiber) miles deployed will remain at zero. Calaveras Overblow and Jackson Aerial segments will be complete so we'll have 27 miles of new network leased. We will have two CAI's connected with the Jackson Aerial segment complete. Signed wholesaler agreements will remain at two. | CVIN, LLC | Experienced delays in acquiring necessary construction permits. Mainly due to lengthy review time lines from the permitting authorities. | We anticipate delays in fiber optic cable deliveries from manufacturer. We are currently in negotiations with the fiber manufacturer to shorten up the delivery schedule. In the mean time we are concentrating on underground construction. Once fiber is delivered, we plan to employ our own installation and splicing crews which should shorten the fiber installation time and also reduce costs. | TRUE
NT10BIX5570126 | 2012 | Q1 | Q1 - 2012 | Underground construction continued through this quarter. Permitting processes also continued and are nearing completion. CVIN has hired additional key staff members as Outside Plant Technician, two (2) Construction Management Assistants, Construction Coordinator, Network Technician, and two (2) Outside Plant Inspectors. Besides retaining the services of a construction inspection firm and environmental monitoring firms which work closely with CVIN staff and construction contractors to insure compliance with all aspects of grant project construction, CVIN also hired in-house inspectors. The project has been broken down into 30 segments and construction is in full force. Twenty-five (25) segments have been bid, twenty-three (23) segments have been awarded, and twelve (12) segments are under construction. So far, 200 miles of conduit has been installed. All conduit has been received and 300 miles of fiber optic cable has been received. Fiber optic cable installation will be done by in-house staff and the installation equipment has been received. The first shipment of fiber optic network equipment has been received and additional orders will arrive in the next few months. | 27 | 0 | 0 | 0 | 27 | 0 | 0 | 1 | Construction efforts have been focused on placement of underground conduit. 200 miles of underground conduit has been placed. This 27 miles of fiber was placed in leased conduit sections of our project (overblow). | N/A | Construction efforts have been focused on placement of underground conduit. Fiber optic cable installation will begin next quarter. | Construction efforts have been focused on placement of underground conduit. Fiber optic cable installation will begin next quarter. | Construction efforts have been focused on placement of underground conduit. This 27 miles of fiber was placed in leased conduit sections of our project (overblow). | Wireless equipment trials will be conducted next quarter. Deployment will begin in Q3-2012. | Wireless equipment trials will be conducted next quarter. Deployment will begin in Q3-2012. | Construction efforts have been focused on placement of underground conduit. Fiber optic cable installation will begin next quarter which will allow for establishment of interconnection points. | 2 | 34 | 16 | Sebastian Corp (DBA: Audeamus) Sierra Tel Internet | Internet access bandwidth at 500 Mbps to 1 Gbps (see attached pricing plans). | Once the project is complete, the services provided to Anchor Institutions will be managed by our partner, the Corporation for Education Network Initiatives in California (CENIC) who is a sub-recipient. We (CVIN) will manage all commercial services to third party providers, business and residential customers. CENIC's Chief Technology Officer, David Reese, is their operations contact for the project (dave@cenic.org, 714-220-3444). | 0 | 2 | 0 | 2 | Behind schedule due to construction delays. | Behind schedule due to construction delays. | No change from the baseline. | We have two wholesalers, one at 500Mbps and one at 2Gbps. | 0 | 0 | 0 | 0 | Behind schedule due to construction delays. | Behind schedule due to construction delays. | Behind schedule due to construction delays. | Behind schedule due to construction delays. | 0 | 0 | 0 | 0 | 0 | Behind schedule due to construction delays. | Behind schedule due to construction delays. | Behind schedule due to construction delays. | No change from the baseline. | Behind schedule due to construction delays. | 0 | 0 | 0 | 0 | 0 | Behind schedule due to construction delays. | Behind schedule due to construction delays. | Behind schedule due to construction delays. | No change from the baseline. | Behind schedule due to construction delays. | N/A | FALSE | N/A | Underground conduit construction will continue full force. We anticipate that all permitting except California Department of Transportation (Caltrans) will be complete. Additional engineering firms will continue to focus on Caltrans permitting processes. We should received all fiber optic cable materials and fiber optic cable installation will commence. We will use our own forces for fiber installation, splicing and testing which will save time and money. Additional orders of fiber optic network equipment will be received. Last mile wireless equipment trials will be conducted. We anticipate 339 miles of fiber, 5 Community Anchor Institutions, and 4 wholesale providers by end of next quarter. | CVIN, LLC | The California Department of Transportation (Caltrans) permitting process has been difficult to handle. Initial indications by Caltrans that accommodations would be made for government grant awardees has not materialized. Caltrans is handling the three districts involved in our project area individually rather than collectively, applying separate requirements for each district. CVIN has hired an additional engineering firm with Caltrans permitting experience for each district to monitor progress and to push the process along. | It is anticipated that it will continue to be a struggle to work through the Caltrans permitting process. | TRUE
NT10BIX5570126 | 2012 | Q2 | Q2 - 2012 | Underground construction continued through this quarter. Permitting processes also continued and are nearing completion. Installation of fiber optic cable began. CVIN has hired three (3) additional Outside Plant Technicians for fiber optic cable installation. CVIN also hired an RF Engineer to manage construction of the wireless last mile portion of the project. Construction inspection and environmental monitoring firms continue to work closely with CVIN staff and construction contractors to insure compliance with all aspects of grant project construction. The project has been broken down into 30 segments and construction is in full force. Twenty-seven (27) segments have been bid and awarded, and eighteen(18) segments are under construction. So far, 365 miles of conduit and 42 miles of fiber optic cable have been installed. All conduit and fiber optic cable has been received. Three (3) vendors participated in a wireless equipment trial to compare the capabilities of their WiMax products. Additional orders of fiber optic network equipment, anchor institution switches and routers, and network management equipment have been received. Bids are currently out on equipment cabinets and huts and backup power systems. NTIA conducted the second annual site visit on June 19-20, 2012. Our Federal Program Officer and Grants Coordinator were on site to review our project in detail. On the second day they were able to visit several locations where they observed construction crews performing various underground construction tasks. | 42 | 0 | 0 | 0 | 42 | 0 | 0 | 1 | Construction efforts have been focused on placement of underground conduit. 365 miles of underground conduit has been placed. Fiber installation in the underground conduit began this quarter. Besides 27 miles of fiber placed in leased conduit, 15 miles of fiber was placed in new underground conduit. | N/A | Construction efforts have been focused on placement of underground conduit and new fiber optic cable. Upgrade of existing and leased areas will be starting later this year. | Construction efforts have been focused on placement of underground conduit and new fiber optic cable. Upgrade of existing and leased areas will be starting later this year. | Fiber installation in the underground conduit began this quarter. Besides 27 miles of fiber placed in leased conduit, 15 miles of fiber was placed in new underground conduit. | Wireless equipment trials occurred this quarter. Deployment will begin next quarter. | N/A | Construction efforts have been focused on placement of underground conduit and fiber optic cable installation. Outdoor cabinets and huts will begin to be deployed in the next few months which will allow establishment of more interconnection points. | 2 | 34 | 16 | Sebastian Corp (DBA: Audeamus) Sierra Tel Internet | Internet access bandwidth at 500 Mbps to 1 Gbps (see attached pricing plans). | Once the project is complete, the services provided to Anchor Institutions will be managed by our partner, the Corporation for Education Network Initiatives in CAlifornia (CENIC) who is a sub-recipient. We (CVIN) will manage all commercial services to third party providers, business and residential customers. CENIC's Chief Technology Officer, David Reese, is their operations contact for the project (dave@cenic.org, 714-220-3444). | 0 | 2 | 0 | 2 | Behind schedule due to construction delays. | Behind schedule due to construction delays. | Behind schedule due to construction delays. | We have two wholesalers, one at 500 Mbps and one at 2Gbps. | 0 | 0 | 0 | 0 | Behind schedule due to construction delays. | Behind schedule due to construction delays. | Behind schedule due to construction delays. | Behind schedule due to construction delays. | 0 | 0 | 0 | 0 | 0 | Behind schedule due to construction delays. | Behind schedule due to construction delays. | Behind schedule due to construction delays. | No change from the baseline. | Behind schedule due to construction delays. | 0 | 0 | 0 | 0 | 0 | Behind schedule due to construction delays. | Behind schedule due to construction delays. | Behind schedule due to construction delays. | No change from the baseline. | Behind schedule due to construction delays. | N/A | FALSE | N/A | Underground conduit construction will continue full force with several segments being completed. All permitting and right-of-way processes should be complete. Fiber optic cable installation efforts will result in significant progress. Procurement of fiber optic network equipment, power equipment, outdoor cabinets & huts, etc. will be near complete. Wireless equipment deployment will begin. We anticipate 275 miles of fiber placed, 6 Community Anchor Institutions connected, and 4 wholesale providers by end of next quarter. | CVIN, LLC | The California Department of Transportation (Caltrans) permitting process was the only lingering problem area. The measures CVIN implemented last quarter have been effective and Caltrans permitting should be completed next quarter. | Caltrans permitting should be complete. No other issues are anticipated at this time. | TRUE
NT10BIX5570126 | 2012 | Q3 | Q3 - 2012 | Underground construction and fiber optic cable installation continued through this quarter. Permitting processes also continued and are coming to a close. CVIN has hired another three (3) additional Outside Plant Technicians for fiber optic cable installation. CVIN also hired an Outside Plant Office Assistant, another Construction Manager and another Network Technician. Construction inspection and environmental monitoring firms continue to work closely with CVIN staff and construction contractors to insure compliance with all aspects of grant project construction. The project has been broken down into 30 segments and construction is in full force. Twenty-seven (27) segments have been bid and awarded, and twenty-three (23) segments are under construction. So far, 472 miles of conduit and 105 miles of fiber optic cable have been installed. Existing tower locations have been specifically identified for the wireless last mile portion of the project and the wireless network design has been completed. An RFP was issued for the wireless equipment and responses are currently being evaluated. All anchor institution switches and routers and network management equipment have been received. The final shipments of fiber optic network equipment are expected early in the 4th quarter. Bids have been awarded and orders placed for equipment cabinets and huts and backup power systems. | 105 | 0 | 0 | 0 | 105 | 0 | 0 | 1 | Construction efforts have been focused on placement of underground conduit. 472 miles of underground conduit has been placed. Fiber installation in the underground conduit continued this quarter. Besides 27 miles of fiber placed in leased conduit, 78 miles of fiber was placed in new underground conduit. | N/A | Construction efforts have been focused on placement of underground conduit and new fiber optic cable. Upgrade of existing and leased areas will be starting later this year. | Construction efforts have been focused on placement of underground conduit and new fiber optic cable. Upgrade of existing and leased areas will be starting later this year. | Fiber installation in the underground conduit continued this quarter. Besides 27 miles of fiber placed in leased conduit, 78 miles of fiber was placed in new underground conduit. | An RFP was issued for the wireless equipment and responses are currently being evaluated. Deployment will begin next quarter. | N/A | Construction efforts have been focused on placement of underground conduit and fiber optic cable installation. Outdoor cabinets and huts will begin to be deployed in the next few months which will allow establishment of more interconnection points. | 2 | 34 | 16 | Sebastian Corp (DBA: Audeamus) Sierra Tel Internet | Internet access bandwidth at 500 Mbps to 1 Gbps (see attached pricing plans). | Once the project is complete, the services provided to Anchor Institutions will be managed by our partner, the Corporation for Education Network Initiatives in CAlifornia (CENIC) who is a sub-recipient. We (CVIN) will manage all commercial services to third party providers, business and residential customers. CENIC's Chief Technology Officer, David Reese, is their operations contact for the project (dave@cenic.org, 714-220-3444). | 0 | 2 | 0 | 2 | Behind schedule due to construction delays. | Behind schedule due to construction delays. | Behind schedule due to construction delays. | We have two wholesalers, one at 500 Mbps and one at 2 Gbps. | 0 | 0 | 0 | 0 | Behind schedule due to construction delays. | Behind schedule due to construction delays. | Behind schedule due to construction delays. | Behind schedule due to construction delays. | 0 | 0 | 0 | 0 | 0 | Behind schedule due to construction delays. | Behind schedule due to construction delays. | Behind schedule due to construction delays. | No change from the baseline. | Behind schedule due to construction delays. | 0 | 0 | 0 | 0 | 0 | Behind schedule due to construction delays. | Behind schedule due to construction delays. | Behind schedule due to construction delays. | No change from the baseline. | Behind schedule due to construction delays. | N/A | FALSE | N/A | Underground conduit construction will continue full force with several segments being completed. The few remaining permitting and right-of-way processes should be complete. Fiber optic cable installation efforts will continue, resulting in significant progress. Procurement of fiber optic network equipment, power equipment, outdoor cabinets & huts, etc. will be complete. Site prep and installation of outdoor cabinets and huts will begin. We have determined that there are inadequacies of the proposed 3.65 MHz WiMAX wireless equipment in achieving the data throughput necessary to provide the customer with quality service and no real path forward from equipment manufacturers to upgrade to LTE. As a result, we will be re-evaluating the feasibility of deploying 3.65 MHz WiMAX for the wireless last mile portion of our project. We anticipate 265 miles of fiber placed, 6 Community Anchor Institutions connected, and 4 wholesale providers by end of next quarter. | CVIN, LLC | CVIN was successful in implementing measures to eliminate permitting delays and has nearly completed acquiring all permits. This has allowed significant progress in construction. | No other issues are anticipated at this time. | TRUE
NT10BIX5570126 | 2012 | Q4 | Q4 - 2012 | Underground construction and fiber optic cable installation continued through this quarter. Equipment hut and cabinet installation and fiber optic network equipment deployment began this quarter. Permitting processes are complete. CVIN has hired four (4) additional Outside Plant Technicians and an additional Outside Plant Supervisor for fiber optic cable installation. Construction inspection and environmental monitoring firms continue to work closely with CVIN staff and construction contractors to insure compliance with all aspects of grant project construction. The project has been broken down into 30 segments and construction is in full force. Twenty-seven (27) segments have been bid and awarded, and twenty-four (24) segments are under construction. So far, 524 miles of conduit and 191 miles of fiber optic cable have been installed. All fiber optic network equipment, network management equipment, and anchor institution switches and routers have been received. Deployment of the fiber optic network equipment has begun. All equipment cabinets and backup power systems have been received. Two (2) equipment huts have been received and installed. | 191 | 0 | 226 | 0 | 191 | 0 | 0 | 2 | Construction efforts continue to be focused on placement of underground conduit, new fiber optic cable and upgrade of existing network. 524 miles of underground conduit has been placed. 27 miles of new fiber has been placed in existing conduit and 164 miles of fiber has been placed in new underground conduit. | N/A | Nearly 50% of the existing network to be upgraded is complete. | Construction efforts continue to be focused on placement of underground conduit, new fiber optic cable and upgrade of existing network. Leased network areas will be implemented early in 2013. | Fiber installation in the underground conduit continued this quarter. 27 miles of new fiber has been placed in existing conduit and 164 miles of fiber has been placed in new underground conduit. | Feasibility of deploying 3.65MHz WiMAX is being re-evaluated. | N/A | An additional interconnection point was established at the Dinuba Hut. The remaining interconnection points will be established early in 2013. | 2 | 34 | 16 | Sebastian (DBA: Audeamus) Sierra Tel Internet | Internet access bandwidth at 500 Mbps to 2.5 Gbps (see attached pricing plans). | Once the project is complete, the services provided to Anchor Institutions will be managed by our partner, the Corporation for Eduction Network Initiatives in California (CENIC) who is a sub-recipient. We (CVIN) will manage all commercial services to third party providers, business and residential customers. CENIC's Chief Technology Officer, David Reese, is their operations contact for the project (dave@cenic.org, 714-220-3444). | 0 | 2 | 0 | 2 | Behind schedule due to initial construction delays. | Behind schedule due to initial construction delays. | Behind schedule due to initial construction delays. | We have two wholesale providers, one at 500Mbps and one at 2.5Gbps. | 2 | 1 | 1 | 2 | Behind schedule due to initial construction delays. | Behind schedule due to initial construction delays. | Behind schedule due to initial construction delays. | We have two speed tiers, either 1Gbps or 10Gbps for Community Anchor Institutions. These two anchors will both receive 1Gbps connections. | 0 | 0 | 0 | 0 | 0 | Feasibility of deploying 3.65MHz WiMAX is being evaluated. | Feasibility of deploying 3.65MHz WiMAX is being evaluated. | Feasibility of deploying 3.65MHz WiMAX is being evaluated. | No change from the baseline. | Feasibility of deploying 3.65MHz WiMAX is being evaluated. | 0 | 0 | 0 | 0 | 0 | Feasibility of deploying 3.65MHz WiMAX is being evaluated. | Feasibility of deploying 3.65MHz WiMAX is being evaluated. | Feasibility of deploying 3.65MHz WiMAX is being evaluated. | No change from the baseline. | Feasibility of deploying 3.65MHz WiMAX is being evaluated. | N/A | FALSE | N/A | Underground conduit construction will continue with the majority of segments being completed. Fiber optic cable installation efforts will continue. Significant progress will be made on installation of outdoor cabinets and huts, fiber optic network equipment, and power equipment. We anticipate 366 miles of fiber placed, 6 Community Anchor Institutions connected, and 4 wholesale providers by end of next quarter. | CVIN, LLC | We determined that there are inadequacies in the proposed 3.65MHz WiMAX wireless equipment in achieving the data throughput necessary to provide the customer with quality service and no real path forward from equipment manufacturers to upgrade to LTE. As a result, we are re-evaluating the feasibility of deploying 3.65MHz WiMAX for the wireless last mile portion of our project. | No other issues are anticipated at this time. | TRUE
NT10BIX5570126 | 2013 | Q1 | Q1 - 2013 | Underground construction, fiber optic cable installation, equipment hut/cabinet installation and fiber optic network equipment deployment continued through this quarter. Permitting processes are complete. CVIN has hired an additional Construction Coordinator to assist with managing construction efforts in northern segments. Construction inspection and environmental monitoring firms continue to work closely with CVIN staff and construction contractors to insure compliance with all aspects of grant project construction. The project has been broken down into 30 segments and construction is in full force. Twenty-seven (27) segments have been bid and awarded, and twenty-five (25) segments are under construction. So far, 582 miles of conduit and 323 miles of fiber optic cable have been installed. All fiber optic network equipment, network management equipment, and anchor institution switches and routers have been received. All of the fiber optic network equipment has been pre-tested and much of it has been installed and turned up. All equipment cabinets and backup power systems have been received. Three (3) equipment huts have been received and installed. | 323 | 0 | 226 | 0 | 323 | 0 | 0 | 2 | Construction efforts are focused on placement of underground conduit and fiber optic cable. 582 miles of underground conduit has been placed. 27 miles of new fiber in existing conduit and 296 miles in new underground conduit. | N/A | The remaining existing network to be upgraded will complete in the next few months. | Construction efforts continue to be focused on placement of new underground conduit and new fiber optic cable. Leased network areas will be implemented in the next few months. | Fiber installation continued this quarter. 27 miles of new fiber in existing conduit and 296 miles in new underground conduit. | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | N/A | Additional interconnections points will be established in the next few months. | 2 | 34 | 16 | Sebastian (DBA: Audeamus) Sierra Tel Internet | Internet access bandwidth at 500 Mbps to 2.5 Gbps (see attached pricing plans). | Once the project is complete, the services provided to Anchor Institutions will be managed by our partner, the Corporation for Education Network Initiatives in California (CENIC) who is a sub-recipient. We (CVIN) will manage all commercial services to third party providers, business and residential customers. CENIC's Chief Technology Officer, David Reese, is their operations contact for the project (dave@cenic.org, 714-220-3444). | 0 | 2 | 0 | 2 | Behind schedule due to initial construction delays which has delayed turn-up of the network. We have quoted services to many more than are currently being negotiated. Some are waiting for current contracts with other providers to term out before moving to our network. We are confident that we will reach the projected target within a short timeframe. | Behind schedule due to initial construction delays which has delayed turn-up of the network. We have quoted services to many more than are currently being negotiated. Some are waiting for current contracts with other providers to term out before moving to our network. We are confident that we will reach the projected target within a short timeframe. | Behind schedule due to initial construction delays. | Two wholesale providers, one at 500Mbps and one at 2.5Gbps. | 17 | 8 | 9 | 2 | Behind schedule due to initial construction delays. | Behind schedule due to initial construction delays. | Behind schedule due to initial construction delays. | Two speed tiers, either 1Gbps or 10Gbps. 15 anchors will receive 1Gbps and 2 will receive 10Gbps. | 0 | 0 | 0 | 0 | 0 | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | 0 | 0 | 0 | 0 | 0 | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | N/A | FALSE | N/A | Underground conduit construction, fiber installation, installation of cabinet and huts, and installation of network equipment will be near completion. Remaining tasks will be turn up of remaining network equipment and connection and turn up of remaining anchor institutions. We anticipate 600 miles of fiber placed, 40 Community Anchor Institutions connected, and 4 wholesale providers by end of next quarter. | CVIN, LLC | We have determined that it is not feasible nor prudent to deploy the proposed 3.65MHz WiMAX last mile due to limitations discovered during field trials. | No other issues are anticipated at this time. | TRUE
NT10BIX5570126 | 2013 | Q2 | Q2 - 2013 | Underground construction, fiber optic cable installation, equipment hut/cabinet installation and fiber optic network equipment deployment continued through this quarter. Permitting processes are complete. Construction inspection and environmental monitoring firms continue to work closely with CVIN staff and construction contractors to insure compliance with all aspects of grant project construction. The project has been broken down into 30 segments and construction is in full force. All thirty (30) segments have been bid and awarded, and twenty-nine (29) segments are under construction. So far, 656 miles of conduit and 434 miles of fiber optic cable have been installed. All fiber optic network equipment, network management equipment, and anchor institution switches and routers have been received. All fiber optic network equipment has been pre-tested and much of it has been installed and turned up. All equipment cabinets and backup power systems have been received. Fourteen (14) of the seventeen (17) equipment cabinets have been installed. All five (5) equipment huts have been received and installed. | 434 | 0 | 332 | 0 | 434 | 0 | 0 | 12 | Construction efforts are focused on placement of underground conduit and fiber optic cable. 656 miles of underground conduit has been placed. 27 miles of new fiber in existing conduit and 407 miles in new underground conduit. | N/A | The remaining existing network to be upgraded will complete in the next few months. | Construction efforts are focused on placement of underground conduit and new fiber optic cable. 36 miles of leased fiber will be implemented during the network turn-up processes in the October/November time frame. | Fiber installation continued this quarter. 27 miles of new fiber in existing conduit and 407 miles in new underground conduit. | Not feasible nor prudent to deploy proposed 3.65MHz Wimax. | N/A | The remaining interconnection points will be established in the next few months. | 3 | 33 | 16 | Sebastian (DBA: Audeamus) Sierra Tel Internet Ponderosa Telephone | Internet access bandwidth at 500Mbps to 3Gbps (see attached pricing plans). | Once the project is complete, the services provided to Anchor Institutions will be managed by our partner, the Corporation for Education Network Initiatives in California (CENIC) who is a sub-recipient. We (CVIN) will manage all commercial services to third party providers, business and residential customers. CENIC's Chief Technology Officer, David Reese, is their operations contact for the project (dave@cenic.org, 714-220-3444). | 0 | 3 | 0 | 2 | Behind schedule due to initial construction delays which has delayed turn-up of the network. We have quoted services to many more than are currently being negotiated. Some are waiting for current contracts with other providers to term out before moving to our network. We are confident that we will reach the projected target within a short timeframe. | Behind schedule due to initial construction delays which has delayed turn-up of the network. We have quoted services to many more than are currently being negotiated. Some are waiting for current contracts with other providers to term out before moving to our network. We are confident that we will reach the projected target within a short timeframe. | Behind schedule due to initial construction delays. | Three wholesale providers, two at 500Mbps and one at 3Gbps | 28 | 14 | 14 | 2 | Behind schedule due to initial construction delays. | Behind schedule due to initial construction delays. | Behind schedule due to initial construction delays. | Two speed tiers, either 1Gbps or 10Gbps. 25 anchors will receive 1Gbps and 3 will receive 10Gbps. | 0 | 0 | 0 | 0 | 0 | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | 0 | 0 | 0 | 0 | 0 | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | Not feasible nor prudent to deploy proposed 3.65MHz Wimax | N/A | FALSE | N/A | Underground conduit construction, cabinet construction, fiber installation and splicing are expected to be complete. Significant progress is expected in fiber testing and network equipment installation. We anticipate 848 miles of fiber placed, 45 Community Anchor Institutions connected, and 4 wholesale providers by end of next quarter. We also plan to apply for a no cost extension to extend the period of performance of our award. | CVIN, LLC | Construction challenges due to rocky terrain in northern mountainous segments. | None | TRUE
NT10BIX5570126 | 2013 | Q3 | Q3 - 2013 | Underground construction, fiber optic cable installation, equipment hut/cabinet installation and fiber optic network equipment deployment continued through this quarter. Permitting processes are complete. CVIN hired an additional Network Technician to assist in network equipment installation and two additional Outside Plant Technicians to assist in fiber optic cable installation. Construction inspection and environmental monitoring firms continue to work closely with CVIN staff and construction contractors to insure compliance with all aspects of grant project construction. The project has been broken down into 30 segments and construction is in full force. All thirty (30) segments have been bid and awarded, and all thirty (30) segments are under construction. So far, 705 miles of conduit and 504 miles of fiber optic cable have been installed. All fiber optic network equipment, network management equipment, and anchor institution switches and routers have been received. All fiber optic network equipment has been pre-tested and most of it has been installed and turned up. All equipment cabinets and backup power systems have been received. All seventeen (17) equipment cabinets and all five (5) equipment huts have been installed. CVIN was granted an extension through December 31, 2013. | 504 | 0 | 443 | 0 | 504 | 0 | 0 | 20 | Construction efforts efforts are focused on placement of underground conduit and fiber optic cable. 705 miles of underground conduit have been placed. 27 miles of new fiber in existing conduit and 477 miles in new underground conduit. | N/A | There is only one more 44 mile section of existing network to be upgraded. | Construction efforts are focused on placement of underground conduit and new fiber optic cable. 36 miles of leased fiber will be implemented during the network turn-up processes in the November time frame. | Fiber installation continued this quarter. 27 miles of new fiber in existing conduit and 477 miles in new underground conduit. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | N/A | The remaining interconnection points will be established in the next quarter. | 4 | 32 | 16 | Sebastian (DBA: Audeamus) Sierra Tel Internet Ponderosa Telephone Optic Access | Internet access bandwidth at 500Mbps to 10Gbps (see attached pricing plans). | Once the project is complete, the services provided to Anchor Institutions will be managed by our partner, the Corporation for Education Network Initiatives in California (CENIC) who is a sub-recipient. We (CVIN) will manage all commercial services to third party providers, business and residential customers. CENIC's Chief Technology Officer, David Reese, is their operations contact for the project (dave@cenic.org, 714-220-3444). | 1 | 3 | 0 | 3 | Behind schedule due to initial construction delays which has delayed turn-up of the network. We have quoted services to many more than are currently being negotiated. Some are waiting for current contracts with other providers to term out before moving to our network. We are confident that we will reach the projected target within a short time frame. | Behind schedule due to initial construction delays which has delayed turn-up of the network. We have quoted services to many more than are currently being negotiated. Some are waiting for current contracts with other providers to term out before moving to our network. We are confident that we will reach the projected target within a short time frame. | Behind schedule due to initial construction delays. | Four wholesale providers, two at 500Mbps, one at 3Gbps and one at 10Gbps. | 40 | 22 | 18 | 2 | Behind schedule due to initial construction delays. | Behind schedule due to initial construction delays. | Behind schedule due to initial construction delays. | Two speed tiers, either 1Gbps or 10Gbps. 36 anchors receiving 1Gbps and 4 receiving 10Gbps. | 0 | 0 | 0 | 0 | 0 | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | 0 | 0 | 0 | 0 | 0 | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | N/A | FALSE | N/A | Underground conduit construction, fiber installation and splicing, network equipment installation and testing are expected to be completed. We anticipate 848 miles of fiber placed, 63 Community Anchor Institutions connected, and 8 Wholesale providers. Our no cost extension to extend the period of performance of our award was approved. | CVIN, LLC | Construction challenges due to rocky terrain in northern mountainous segments. | Construction challenges due to rocky terrain in northern mountainous segments. | TRUE
NT10BIX5570126 | 2013 | Q4 | Q4 - 2013 | Underground construction, fiber optic cable installation, and fiber optic network equipment deployment continued through this quarter. Equipment hut/cabinet installation is complete. Permitting processes are complete. CVIN hired an additional Network Technician to assist in network equipment installation and an additional Outside Plant Technician to assist in fiber optic cable installation. Construction inspection and environmental monitoring firms continue to work closely with CVIN staff and construction contractors to insure compliance with all aspects of grant project construction. Underground conduit construction is nearing completion. So far, 720 miles of conduit and 574 miles of fiber optic cable have been installed. All fiber optic network equipment, network management equipment, and anchor institution switches and routers have been received. 95% of the fiber optic network equipment has been deployed. All equipment cabinets and backup power systems have been received. All seventeen (17) equipment cabinets and all five (5) equipment huts have been received and installed. CVIN was granted an extension through May 31, 2014. | 574 | 0 | 487 | 0 | 574 | 0 | 0 | 32 | Construction efforts are focused on placement of underground conduit and fiber optic cable. 720 miles of underground conduit have been placed. 40 miles of new fiber in existing conduit and 534 miles in new underground conduit. | N/A | All of the planned network miles to be upgraded is complete. | Construction efforts are focused on placement of underground conduit and new fiber optic cable. 36 miles of leased fiber will be implemented during the network turn-up processes in the April 2014 time frame. | Fiber installation continued this quarter. 40 miles of new fiber in existing conduit and 534 miles in new underground conduit. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | N/A | The remaining interconnection points will be established in the next quarter. Only two are remaining. | 7 | 29 | 16 | Sebastian (DBA: Audeamus) Sierra Tel Internet Ponderosa Telephone Optic Access CalTel Internet Kings COE ISP Kings COE (dark fiber) | Internet access bandwidth at 100Mbps to 10Gbps (see attached pricing plans). | Once the project is complete, the services provided to Anchor Institutions will be managed by our partner, the Corporation for Education Network Initiatives in California (CENIC) who is a sub-recipient. We (CVIN) will manage all commercial services to third party providers, business and residential customers. CENIC's Chief Technology Officer, David Reese, is their operations contact for the project (dave@cenic.org, 714-220-3444). | 2 | 4 | 1 | 5 | Behind schedule due to initial construction delays which has delayed turn-up of the network. We have quoted services to many more than are currently being negotiated. Some are waiting for current contracts with other providers to term out before moving to our network. We are confident that we will reach the projected target within a short time frame. | Behind schedule due to initial construction delays which has delayed turn-up of the network. We have quoted services to many more than are currently being negotiated. Some are waiting for current contracts with other providers to term out before moving to our network. We are confident that we will reach the projected target within a short time frame. | Behind schedule due to initial construction delays. | Six wholesale providers, one at 100Mbps, two at 500Mbps, one at 1Gbps, one at 3Gbps and one at 10Gbps. | 41 | 22 | 19 | 2 | Behind schedule due to initial construction delays. | Behind schedule due to initial construction delays. | Behind schedule due to initial construction delays. | Two speed tiers, either 1Gbps or 10Gbps. 36 anchors receiving 1Gbps and 5 receiving 10Gbps. | 0 | 0 | 0 | 0 | 0 | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | 0 | 0 | 0 | 0 | 0 | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | Not feasible nor prudent to deploy proposed 3.65MHz WiMax. | N/A | FALSE | N/A | Underground conduit construction, fiber installation and splicing, network equipment installation and testing are expected to be completed. We anticipate 848 miles of fiber placed, 63 Community Anchor Institutions connected, and 8 Wholesale providers. Our no cost extension to extend the period of performance of our award to May 31, 2014 was approved. | CVIN, LLC | Construction challenges due to rocky terrain in northern mountainous segments. | Construction challenges due to rocky terrain in northern mountainous segments. | TRUE
NT10BIX5570127 | 2010 | Q4 | Q4 - 2010 | Finalized the project baseline on December 13th. Secured project engineering services and completed the intitial field review of routes and interconnection points needed for the environmental assessment. Started the detailed review of engineering and permitting requirements in Centerville and Murray. Environmental consulting engineers started work on the environmental assessment with draft completion scheduled as planned by February. Planning activities began for procurement of materials, contractors, personnel, and equipment. The project OSP construction services RFP was released in December. Completed setup of accounting and verification system for the project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zero at this time | N/A | N/A | N/A | Zero at this time | N/A | N/A | Zero at this time | 0 | 0 | 0 | N/A | Available when services are connected. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero at this time | Zero at this time | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Significant project accomplishments for Q1-2011 include: Completion of the Environmental Assessment. Completion of the Detailed Network Design, Right of way aquisition, and Construction permits and other approvals in Centerville and Murray. Procurement activities related to securing contracts for equipment, construction services, personnel, and materials will be underway with the materials and services secured that are required to begin construction in Q2-2011. | Utopia | Matching funds were scheduled to be available during YR1-Q2 (Q4-2010). UTOPIA experienced delays in obtaining the necessary matching funds during this quarter. Network design, ROW, and permitting work was not issued as planned for Midvale and Orem pending confirmation of available matching funds. It is anticipated these funds will be available during YR1-Q4 (Q2-2011). UTOPIA applied for a waiver of the proportional draw down requirement so the work can be issued now and the milestone baselines will be recovered in Q2-2011. | These plans anticipate timely approval of the waiver of proportional draw down requirement currently submitted to NTIA. Vendors for equipment will be secured in Q1-2011, but the costs associated with the intitial purchases will not be incurred until Q2-2011. The original milestone baseline for equipment procurement will recovered during Q2-2011. | TRUE
NT10BIX5570127 | 2011 | Q1 | Q1 - 2011 | Finalized the environmental assessment and received Finding of No Significant Impact. Created 4 full time equivalent jobs. Completed the engineering and permitting requirements in Centerville and Murray and started engineering and permitting in Midvale, Orem, Layton, and West Valley. Planning activities continued for procurement of materials, contractors, personnel, and equipment. Construction Contractor, Materials, and Equipment vendors were secured and orders placed for construction start in April. The percent complete for Network Design, Rights of Way, and Construction permits/approvals is currently below projection of 29% complete. Additional resources have been dedicated to these milestones. Equipment procurement is currently below projected. Awards were made during this Quarter and the significant equipment costs will be incurred in Q2-2011. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zero at this time. New network miles will be deployed in Q2-2011 | N/A | N/A | N/A | Zero at this time. New network miles will be deployed in Q2-2011 | N/A | N/A | Zero at this time. Work on New network interconnection points will begin in Q2-2011. | 0 | 0 | 0 | N/A | Available when services are connected. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Zero at this time. Connections to Community Anchor Institutions will begin in Q2-2011 | Zero at this time. New connections to Community Anchor Institutions will begin in Q2-2011 | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Construction begins in Centerville, Murray, Midvale, and Orem and approximately 8 miles of fiber cable will be installed. Job creation is anticipated to exceed 30 full time equivalent jobs. 37 Community Anchor Institutions will be connected with significantly improved broadband services. | Utopia | UTOPIA received a waiver of the proportional draw down requirement so the work is now well underway and the milestone baselines will be recovered in Q3-2011. | We are currently facing challenges with the time frames involved and approvals required to finalize easements and rights of way for the equipment shelters necessary to house the equipment. These pre-fabricated shelters cannot be ordered until we obtain these approvals to ensure site compatibility. Currently we plan to place 6 shelters by the end of Q2-2011. It is likely actual expenditures for the shelters will be delayed until the next quarter pending the final approval time frames by the various municipal agencies. This could directly affect progress of multiple milestones dependent on these buildings during this quarter, however, additional resources are now being deployed to limit these delays to this quarter only. Additional rights of way engineering resources will assist in finalizing these approvals, and if delays are experienced, ensure recovery of the original baseline by end of Q3-2011. Fiber Optic cable in this country is becoming increasingly difficult to obtain within reasonable time frames. This is due to significantly increased demand resulting from earthquake caused plant shutdowns in Japan. Lead times are increasing every day. Larger orders are placed, but there may be significant delays in being able to obtain all the necessary cable for the project. All options are being considered, but very little can be done at this time to ensure future milestones will not be impacted. | TRUE
NT10BIX5570127 | 2011 | Q2 | Q2 - 2011 | Twenty-one Community Anchor Institutions are now connected using BTOP funds. These connections consist of 13 public safety entities, 1 school (k-12), 1 institution of higher education, 1 community support organization, 4 other government facilities, and 1 medical facility. Eleven Miles of Fiber have been Installed collectively in the cities of Centerville and Murray. Network Design is complete in Centerville, Murray, and 50% of Orem. Construction activities are well underway with four times as many full time equivalent jobs created during quarter two (20.83) than in quarter one (4.21). Some delays have been experienced in obtaining fiber optic cable, rights of way, and permits, but these delays will not currently affect completion of the project as planned. | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | No Variance. | N/A | N/A | N/A | No Variance | N/A | N/A | Zero at this time. Work on New network interconnection points will be completed in Q3-2011. | 0 | 0 | 0 | No agreements with providers resulting from the investment of BTOP funds at this time. The original baseline indicated 16 broadband wholesale agreements signed and actually represented existing wholesale providers on the UTOPIA network with agreements instead of new agreements with wholesale providers from the investment of BTOP funds. It is not anticipated that additional wholesale providers with new agreements will need to be added to the network from the investment of BTOP funds, but existing providers will be utilized. | Twenty-five wholesale data packages are available to service providers. Please see attachment. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 21 | 21 | 0 | 25 | Fewer agreements were secured than anticipated do to challenges in finalizing terms. Additional resources have been secured in recent weeks and we anticipate recovering the baseline during the next quarter. | Fewer agreements were secured than anticipated do to challenges in finalizing terms. Additional resources have been secured in recent weeks and we anticipate recovering the baseline during the next quarter. | N/A | There are 25 speed tiers currently available to community anchor institutions through existing service providers. See attachment indicating the number of subscribers for each. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | UTOPIA will provide new broadband connections to approximately 70 additional community anchor institutions throughout West Valley, Layton, Murray, Centerville, Midvale, and Orem. UTOPIA will Construct an additional 20 miles of fiber in parts of Midvale, Centerville, West Valley, and Orem. We are working with local leaders using joint community outreach efforts to target business districts in these areas who will use the network to bolster economically distressed areas. Engineering will be completed in 80% of Orem and 30% of West Valley. We will deploy and test 6 points of interconnection in Centerville. Procurement activities will include the purchase of network equipment, test equipment, construction materials, fiber optic cable, and construction management and inspection equipment. | Utopia | Some delays have been experienced in obtaining community anchor institution agreements, acquisition of rights of way, and procurement of fiber optic cable and network equipment. These delays will not impact overall milestone completion. Alternate supplier sources and rights of way locations are in development to avoid delays in subsequent quarters. Contract negotiations with community anchor institutions are improving through strategic partnerships with our service providers. | Challenges will continue to be in securing the necessary right of way to place points of interconnect and finalize community anchor institution connection agreements. Fiber cable availability for larger counts due to increased demand and natural disasters abroad could also be an issue. UTOPIA continues to make adjustments to the initial project deployment locations and time frames to mitigate the impacts from these challenges and issues. The project will continue to make significant progress. We anticipate catching up to our baseline projections by end of Q4-2011. | TRUE
NT10BIX5570127 | 2011 | Q3 | Q3 - 2011 | Fifty-four Community Anchor Institutions are now connected using BTOP funds. These connections consist of public safety entities, schools (k-12), Institutions of higher education, community colleges, community support organizations, government facilities, and medical facility. Eighteen miles of Fiber have been installed collectively in the cities of Centerville, Orem, Midvale, and Murray. Network Design is complete in Centerville, Murray, 20% of Midvale, 10% West Valley, and 80% of Orem. Construction activities are well underway with 17.35 full-time equivalent jobs created during the quarter. Some delays are being experienced in obtaining fiber optic cable, rights of way and permits, and obtaining commitments from planned anchor institutions, but these delays will not currently affect final completion of the project as planned. | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 5 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q1-2012 | N/A | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q1-2012 | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect in Midvale, West Valley, Layton, and Orem. The network design and detailed route engineering is dependent on securing these sites in order for work to begin. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q1-2012 | 0 | 0 | 0 | No agreements with providers resulting from the investment of BTOP funds at this time. The original baseline indicated 16 broadband wholesale agreements signed and actually represented existing wholesale providers on the UTOPIA network with agreements instead of new agreements with wholesale providers from the investment of BTOP funds. it is not anticipated that additional wholesale providers with new agreements will need to be added to the network from the investment of BTOP funds, but existing providers will be utilized. | Twenty-five wholesale data packages are available to service providers. Please see attachment. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 54 | 54 | 0 | 25 | Fewer agreements were secured than anticipated due to challenges in finalizing terms and an unexpected reduction in resources. Additional resources will be secured in the next few weeks and we anticipate recovering the baseline during the two quarters. | Fewer agreements were secured than anticipated due to challenges in finalizing terms and an unexpected reduction in resources. Additional resources will be secured in the next few weeks and we anticipate recovering the baseline during the two quarters. | N/A | There are 25 speed tiers currently available to community anchor institutions through existing service providers. See attachment indicating the number of subscribers for each. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | UTOPIA will provide new broadband connections to approximately 50 additional community anchor institutions throughout West Valley, Layton, Murray, Centerville, Midvale, and Orem. UTOPIA will Construct an additional 25 miles of fiber in parts of Midvale, Centerville, West Valley, and Orem. We are working with local leaders using joint community outreach efforts to target business districts in these areas who will use the network to bolster economically distressed areas. Engineering will be completed in 90% of Orem, 30% of West Valley, 40% of Midvale, and 35% of Layton. We will deploy and test an addtional 6 points of interconnection. Procurement activities will include the purchase of network equipment, test equipment, construction materials, fiber optic cable, and construction management and inspection equipment. | Utopia | Some delays have been experienced in obtaining community anchor institution agreements, acquisition of rights of way and procurement of fiber optic cable and network equipment. These delays will not impact overall completion. Alternative supplier sources and rights of way locations are in development to avoid delays in subsequent quarters. Contract negotiations with community anchor institutions are improving through strategic partnerships with our service providers. | Challenges will continue to be in securing the necessary right of way to place points of interconnect and finalize community anchor institution connection agreements. Fiber cable availability for larger counts due to increased demand and natural disasters abroad is also an issue. UTOPIA continues to make adjustments to the initial project deployment locations and time frames to mitigate the impacts from these challenges and issues. The project will continue to make significant progress. We anticipate catching up to our baseline projections by end of Q1-2012. | TRUE
NT10BIX5570127 | 2011 | Q4 | Q4 - 2011 | Thirty eight Community Anchor Institutions and Thirty remote facilities for Community Anchor Institutions are now connected using BTOP funds. These connections consist of public safety entities, schools (k-12), Institutions of higher education, community colleges, community support organizations, government facilities, and medical facility. Twenty-Five miles of fiber have been installed collectively in the cities of Centerville, Orem, Midvale, West Valley and Murray. Network Design is complete in Centerville, Murray, 40% of Midvale, 15% West Valley, 40% of Layton, and 80% of Orem. Construction activities are well underway with 27.49 full-time equivalent jobs created during the quarter. Some delays are being experienced in obtaining rights of way and permits, and obtaining commitments from planned anchor institutions, but these delays will not currently affect final completion of the project as planned in Q4_2012. | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 7 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect, procure fiber optic cable,and construction delays. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q2-2012 | N/A | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect, procure fiber optic cable,and construction delays. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q2-2012 | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect and construction delays. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q2-2012 | 13 | 2 | 0 | Thirteen agreements with providers have improved access to subscribers resulting from the investment of BTOP funds. | [REDACTED] | N/A | 0 | 13 | 0 | 29 | N/A | Thirteen existing service providers are receiving improved access to subscribers because of BTOP funds | N/A | [REDACTED] | 38 | 9 | 29 | 28 | Fewer agreements were secured than anticipated due to challenges in finalizing terms and an unexpected reduction in resources. Additional resources are now secured and we anticipate recovering the baseline during the next two quarters. | Receiving new services through UTOPIA or UTOPIA Service Providers | Receiving improved services through UTOPIA or UTOPIA Service Providers | There are 28 speed tiers currently available to community anchor institutions. See attachment indicating the number of subscribers for each. | 10 | 0 | 0 | 0 | 1 | Passed using the middle mile lateral cable to an anchor. | N/A | N/A | N/A | There are 1 speed tier currently available to residential service providers which they re-sale to residential households. See attachment indicating the number of subscribers for each. | 5 | 0 | 0 | 0 | 15 | Passed using the middle mile lateral cable to an anchor institution. | N/A | N/A | N/A | There are 15 speed tiers currently available to businesses through existing service providers. See attachment indicating the number of subscribers for each. | N/A | FALSE | N/A | UTOPIA will provide new broadband connections to approximately 30 additional community anchor institutions throughout West Valley, Layton, Murray, Centerville, Midvale, and Orem. We will construct an additional 47 miles of fiber in parts of Midvale, West Valley, Layton, and Orem. We are working with local leaders using joint community outreach efforts to target business districts in these areas who will use the network to bolster economically distressed areas. Engineering will be completed in 90% of Orem, 30% of West Valley, 50% of Midvale, and 80% of Layton. We will deploy and test an additional 18 points of interconnection. Procurement activities will include the purchase of network equipment, test equipment, construction materials, fiber optic cable, and construction management and inspection equipment. | Utopia | Some delays have been experienced in obtaining community anchor institution agreements, acquisition of rights of way, procurement of fiber optic cable, construction, and network equipment procurement. These delays will not impact overall completion. Alternative supplier sources and rights of way locations have been secured to avoid delays in subsequent quarters. Contract negotiations with community anchor institutions are improving through strategic partnerships with our service providers. | Challenges will continue to be in securing the necessary rights of way and easements to place points of interconnect and finalize the project detailed route engineering. UTOPIA continues to make adjustments to the initial project deployment locations and time frames to mitigate the impacts from these challenges and issues. The project will continue to make significant progress. We anticipate catching up to our baseline projections by end of Q2-2012. | TRUE
NT10BIX5570127 | 2012 | Q1 | Q1 - 2012 | Thirty-eight Community Anchor Institutions and thirty-four remote facilities for Community Anchor Institutions are now connected using BTOP funds. These connections consist of public safety entities, schools (k-12), Institutions of higher education, community colleges, community support organizations, government facilities, and medical facility. Thirty six miles of fiber have been installed collectively in the cities of Centerville, Orem, Midvale, West Valley and Murray. Network Design is complete in Centerville, Murray, 40% of Midvale, 50% West Valley, 95% of Layton, and 80% of Orem. Construction activities are well underway with 76.94 full-time equivalent jobs created during the quarter. Some delays are being experienced in obtaining rights of way and permits, and obtaining commitments from planned anchor institutions, but these delays will not currently affect final completion of the project during the award period. | 36 | 0 | 0 | 0 | 36 | 0 | 0 | 12 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect and winter construction moratoriums on right of way crossings.These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q3-2012 | N/A | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect and winter construction moratoriums on right of way crossings. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q3-2012 | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect and winter construction moratoriums on right of way crossings. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q3-2012 | 13 | 2 | 0 | Thirteen agreements with providers have improved access to subscribers resulting from the investment of BTOP funds. InfoWest, 1Wire, Utah Broadband, Brigham.net, Fibernet, Voonami, Spectrum, XMission, Integra Telecom, PaeTec, Telesphere, Veracity, and SumoFiber. | 29 wholesale data packages are available to service providers and other government entities. Please see attachment. | N/A | 0 | 13 | 0 | 29 | N/A | Thirteen existing service providers are receiving improved access to subscribers because of BTOP funds | N/A | See the attached service offerings. | 38 | 9 | 29 | 28 | Fewer agreements were secured than anticipated due to challenges in finalizing terms. Additional resources are now secured and we anticipate recovering the baseline during the next two quarters | Receiving new services through UTOPIA or UTOPIA Service Providers | Receiving improved services through UTOPIA or UTOPIA Service Providers | There are 28 speed tiers currently available to community anchor institutions. See attachment indicating the number of subscribers for each. | 10 | 0 | 0 | 0 | 1 | Passed using the middle mile lateral cable to an anchor. | N/A | N/A | N/A | There is 1 speed tier currently available to residential service providers which they re-sale to residential households. See attachment indicating the number of subscribers for each. | 5 | 0 | 0 | 0 | 15 | Passed using the middle mile lateral cable to an anchor institution. | N/A | N/A | N/A | There are 15 speed tiers currently available to businesses through existing service providers. See attachment indicating the number of subscribers for each. | N/A | FALSE | N/A | UTOPIA will provide new broadband connections to approximately 50 additional community anchor institutions throughout West Valley, Layton, Murray, Centerville, Midvale, and Orem. We will construct an additional 60 miles of fiber in parts of Midvale, West Valley, Layton, and Orem. We are working with local leaders using joint community outreach efforts to target business districts in these areas who will use the network to bolster economically distressed areas. It is anticipated that two or three last mile providers will be added during this Quarter. Engineering will be substantially complete this Quarter. We will deploy and test an additional 20 points of interconnection. Procurement activities will include the purchase of network equipment and construction materials. | Utopia | Some delays have been experienced in obtaining community anchor institution agreements and acquisition of rights of way and winter construction moratoriums on right of way crossings. These delays will not impact overall completion during the award period. Alternative owners of rights of way locations have been secured to avoid delays in subsequent quarters. Contract negotiations with community anchor institutions are improving through strategic partnerships with our service providers. | UTOPIA continues to make adjustments to the initial project deployment locations and time frames to mitigate the impacts from these challenges and issues. The project will continue to make significant progress. We anticipate catching up to our baseline projections by end of Q3-2012. | TRUE
NT10BIX5570127 | 2012 | Q2 | Q2 - 2012 | 48 Community Anchor Institutions and 43 remote facilities for Community Anchor Institutions are now connected using BTOP funds. These connections consist of public safety entities, schools (k-12), Institutions of higher education, community colleges, community support organizations, government facilities, and medical facilities. Forty-six miles of fiber have been installed collectively in the cities of Centerville, Orem, Layton, Midvale, West Valley and Murray. Network Design is complete in Centerville, Layton, and Murray. Construction activities are well underway with 52.28 full-time equivalent jobs created during the quarter. Some delays are being experienced in obtaining rights of way and permits, and obtaining commitments from planned anchor institutions, but these delays will not currently affect final completion of the project during the award period. | 46 | 0 | 0 | 0 | 46 | 0 | 0 | 15 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q4-2012 | N/A | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q4-2012 | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q4-2012 | 15 | 2 | 0 | There are now 15 agreements with providers who have improved access to subscribers resulting from the investment of BTOP funds. InfoWest, 1Wire, Utah Broadband, Brigham.net, Fibernet, Voonami, Spectrum, XMission, Integra Telecom, Windstream, Telesphere, Veracity, TADA, Skywire and SumoFiber. We added TADA and Skywire during Q2-2012 | 29 wholesale data packages are available to service providers and other government entities. Please see attachment for the total connected to each product and in the second tab the specific products utilized by the additional community anchor institutions. | N/A | 0 | 15 | 0 | 29 | N/A | Fifteen existing service providers are receiving improved access to subscribers because of BTOP funds | N/A | See the attached service offerings. | 48 | 20 | 28 | 28 | Fewer agreements were secured than anticipated due to challenges in finalizing terms. Additional resources are now secured and we anticipate recovering the baseline during the next two quarters | Subscribers receiving new services through UTOPIA or UTOPIA Service Providers. | Subscribers receiving improved services through UTOPIA or UTOPIA Service Providers. The previous report incorrectly indicated 29 receiving improved access. The subscribers in error are now reported as receiving new access. There were 38 CAI's cumulatively reported in the previous Quarter and 48 cumulatively reported in this Quarter. | There are 28 speed tiers currently available to community anchor institutions. See attachment indicating the number of subscribers for each. | 10 | 0 | 0 | 0 | 1 | Passed using the middle mile lateral cable to an anchor. | N/A | N/A | N/A | There is 1 speed tier currently available to residential service providers which they re-sale to residential households. See attachment indicating the number of subscribers for each. | 5 | 0 | 0 | 0 | 15 | Passed using the middle mile lateral cable to an anchor institution. | N/A | N/A | N/A | There are 15 speed tiers currently available to businesses through existing service providers. See attachment indicating the number of subscribers for each. | N/A | FALSE | N/A | UTOPIA will provide new broadband connections to approximately 40 additional community anchor institutions throughout West Valley, Layton, Murray, Centerville, Midvale, and Orem. We will construct an additional 50 miles of fiber in parts of Midvale, West Valley, Layton, and Orem. We are working with local leaders using joint community outreach efforts to target business districts in these areas who will use the network to bolster economically distressed areas. We will deploy and test an additional 29 points of interconnection. Procurement activities will include the purchase of network equipment and construction materials. | Utopia | Some delays have been experienced in obtaining community anchor institution agreements and acquisition of rights of way. These delays will not impact overall completion during the award period. Alternative owners of rights of way locations have been secured to avoid delays in the following quarter. Contract negotiations with community anchor institutions are improving through strategic partnerships with our service providers. | UTOPIA continues to make adjustments to the initial project deployment locations and time frames to mitigate the impacts from these challenges and issues. The project will continue to make significant progress. We anticipate project completion by end of Q1-2013. | TRUE
NT10BIX5570127 | 2012 | Q3 | Q3 - 2012 | 58 Community Anchor Institutions and 47 remote facilities for Community Anchor Institutions are now connected using BTOP funds. These connections consist of public safety entities, schools (k-12), Institutions of higher education, community colleges, community support organizations, government facilities, and medical facilities. Ninety-two miles of fiber have been installed collectively in the cities of Centerville, Orem, Layton, Midvale, West Valley and Murray. Network Design is complete in Centerville, Layton, and Murray. Construction activities are well underway with 50.67 full-time equivalent jobs created during the quarter. Some delays are being experienced in obtaining rights of way and permits, and obtaining commitments from planned anchor institutions, but these delays will not currently affect final completion of the project during the award period. | 92 | 0 | 0 | 0 | 92 | 0 | 0 | 32 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q1-2013 | N/A | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q1-2013 | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q1-2013 | 15 | 0 | 0 | There are 15 agreements with providers who have improved access to subscribers resulting from the investment of BTOP funds. InfoWest, 1Wire, Utah Broadband, Brigham.net, Fibernet, Voonami, Spectrum, XMission, Integra Telecom, Windstream, Telesphere, Veracity, TADA, Skywire and SumoFiber. | 29 wholesale data packages are available to service providers and other government entities. Please see attachment for the total connected to each product and in the second tab the specific products utilized by the additional community anchor institutions. | N/A | 0 | 15 | 0 | 29 | N/A | Fifteen existing service providers are receiving improved access to subscribers because of BTOP funds | N/A | See the attached service offerings. | 58 | 21 | 37 | 29 | Fewer agreements were secured than anticipated due to challenges in finalizing terms. Additional resources are now secured and we anticipate recovering the baseline during the next two quarters | Subscribers receiving new services through UTOPIA or UTOPIA Service Providers. | Subscribers receiving improved services through UTOPIA or UTOPIA Service Providers. | There are 29 speed tiers currently available to community anchor institutions. See attachment indicating the number of subscribers for each. | 10 | 0 | 0 | 0 | 1 | Passed using the middle mile lateral cable to an anchor. | N/A | N/A | N/A | There is 1 speed tier currently available to residential service providers which they re-sale to residential households. | 5 | 0 | 0 | 0 | 15 | Passed using the middle mile lateral cable to an anchor institution | N/A | N/A | N/A | There are 15 speed tiers currently available to businesses through existing service providers. | N/A | FALSE | N/A | UTOPIA will provide new broadband connections to approximately 60 additional community anchor institutions throughout West Valley, Layton, Murray, Centerville, Midvale, and Orem. We will construct an additional 53 miles of fiber in parts of Midvale, West Valley, Layton, and Orem. We are working with local leaders using joint community outreach efforts to target business districts in these areas who will use the network to bolster economically distressed areas. We will deploy and test an additional 14 points of interconnection. Procurement activities will include the purchase of network equipment and construction materials. | Utopia | Some delays have been experienced in obtaining community anchor institution agreements and acquisition of rights of way. These delays will not impact overall completion during the award period. Alternative owners of rights of way locations have been secured to avoid delays in the following quarter. Contract negotiations with community anchor institutions are improving through strategic partnerships with our service providers. | UTOPIA continues to make adjustments to the initial project deployment locations and time frames to mitigate the impacts from these challenges and issues. The project will continue to make significant progress. We anticipate project completion by end of Q2-2013. | TRUE
NT10BIX5570127 | 2012 | Q4 | Q4 - 2012 | 68 Community Anchor Institutions and 58 remote facilities for Community Anchor Institutions are now connected using BTOP funds. These connections consist of public safety entities, schools (k-12), Institutions of higher education, community colleges, community support organizations, government facilities, and medical facilities. One hundred and forty-one miles of fiber have been installed collectively in the cities of Centerville, Orem, Layton, Midvale, West Valley and Murray. Network Design is complete in Centerville, Layton, Murray and Orem. Construction activities are well underway with 69.08 full-time equivalent jobs created during the quarter. Some delays are being experienced in obtaining rights of way and permits, and obtaining commitments from planned anchor institutions, but these delays will not currently affect final completion of the project during the award period. | 141 | 0 | 0 | 0 | 141 | 0 | 0 | 42 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q1-2013 | N/A | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q1-2013 | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q2-2013 | 15 | 0 | 0 | There are 15 agreements with providers who have improved access to subscribers resulting from the investment of BTOP funds. InfoWest, 1Wire, Utah Broadband, Brigham.net, Fibernet, Voonami, Spectrum, XMission, Integra Telecom, Windstream, Telesphere, Veracity, TADA, Skywire and SumoFiber. | 29 wholesale data packages are available to service providers and other government entities. Please see attachment for the total connected to each product and in the second tab the specific products utilized by the additional community anchor institutions. | N/A | 0 | 15 | 0 | 29 | N/A | Fifteen existing service providers are receiving improved access to subscribers because of BTOP funds | N/A | See the attached service offerings. | 68 | 21 | 47 | 29 | Fewer agreements were secured than anticipated due to challenges in finalizing terms. Additional resources are now secured and we anticipate recovering the baseline during the next two quarters. During this Quarter we only added 6 new anchors. During Q2-2012 we reported 10 new anchors and added 14 new anchors. This will be the variance as why there is only 6 new CIA added to this report. | Subscribers receiving new services through UTOPIA or UTOPIA Service Providers. | Subscribers receiving improved services through UTOPIA or UTOPIA Service Providers. | There are 29 speed tiers currently available to community anchor institutions. See attachment indicating the number of subscribers for each. | 10 | 0 | 0 | 0 | 1 | Passed using the middle mile lateral cable to an anchor. | N/A | N/A | N/A | There is 1 speed tier currently available to residential service providers which they re-sale to residential households. | 5 | 0 | 0 | 0 | 15 | Passed using the middle mile lateral cable to an anchor institution | N/A | N/A | N/A | There are 15 speed tiers currently available to businesses through existing service providers. | N/A | FALSE | N/A | UTOPIA will provide new broadband connections to approximately 110 total community anchor institutions throughout West Valley, Layton, Murray, Centerville, Midvale, and Orem. We will have constructed approximately 210 miles of fiber in parts of Midvale, West Valley, Layton, and Orem. We are working with local leaders using joint community outreach efforts to target business districts in these areas who will use the network to bolster economically distressed areas. We will deploy and test an additional 6 points of interconnection. Procurement activities will include the purchase of network equipment and construction materials. | Utopia | Some delays have been experienced in obtaining community anchor institution agreements and acquisition of rights of way. These delays will not impact overall completion during the award period. Alternative owners of rights of way locations have been secured to avoid delays in the following quarter. Contract negotiations with community anchor institutions are improving through strategic partnerships with our service providers. | UTOPIA continues to make adjustments to the initial project deployment locations and time frames to mitigate the impacts from these challenges and issues. The project will continue to make significant progress. We anticipate project completion by end of Q2-2013. | TRUE
NT10BIX5570127 | 2013 | Q1 | Q1 - 2013 | 75 Community Anchor Institutions and 89 remote facilities for Community Anchor Institutions are now connected using BTOP funds. These connections consist of public safety entities, schools (k-12), Institutions of higher education, community colleges, community support organizations, government facilities, and medical facilities. One hundred and sixty-seven miles of fiber have been installed collectively in the cities of Centerville, Orem, Layton, Midvale, West Valley and Murray. Network Design has been completed for the project. Construction activities are well underway with 43.42 full-time equivalent jobs created during the quarter. Some delays are being experienced in obtaining commitments from planned anchor institutions. | 167 | 0 | 0 | 0 | 167 | 0 | 0 | 45 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q2-2013 | N/A | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q2-2013 | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. These delays are not expected to significantly impact project completion. The baseline is expected to be recovered by the end of Q2-2013 | 16 | 0 | 0 | There are 16 agreements with providers who have improved access to subscribers resulting from the investment of BTOP funds. InfoWest, 1Wire, Utah Broadband, Brigham.net, Fibernet, Voonami, Spectrum, XMission, Integra Telecom, Windstream, Telesphere, Veracity, TADA, Skywire, SumoFiber and Senawave. | 29 wholesale data packages are available to service providers and other government entities. Please see attachment for the total connected to each product and in the second tab the specific products utilized by the additional community anchor institutions. | N/A | 0 | 16 | 0 | 29 | N/A | Sixteen existing service providers are receiving improved access to subscribers because of BTOP funds | N/A | See attached service offerings | 75 | 22 | 59 | 29 | Fewer agreements were secured than anticipated due to challenges in finalizing terms. Additional resources are now secured and we anticipate recovering the baseline during the next two quarters. | Subscribers receiving new services through UTOPIA or UTOPIA Service Providers. | Subscribers receiving improved services through UTOPIA or UTOPIA Service Providers. | There are 29 speed tiers currently available to community anchor institutions. See attachment indicating the number of subscribers for each. | 10 | 0 | 0 | 0 | 1 | Passed using the middle mile lateral cable to an anchor. | N/A | N/A | N/A | There is 1 speed tier currently available to residential service providers which they re-sale to residential households. | 5 | 0 | 0 | 0 | 15 | Passed using the middle mile lateral cable to an anchor institution | N/A | N/A | N/A | There are 15 speed tiers currently available to businesses through existing service providers. | N/A | FALSE | N/A | UTOPIA will provide new broadband connections to approximately 160 total community anchor institutions throughout West Valley, Layton, Murray, Centerville, Midvale, and Orem. We will have constructed approximately 260 miles of fiber in parts of Midvale, West Valley, Layton, and Orem. We are working with local leaders using joint community outreach efforts to target business districts in these areas who will use the network to bolster economically distressed areas. We will deploy and test an additional 18 points of interconnection. Procurement activities will include the purchase of network equipment and construction materials. | Utopia | Some delays have been experienced in obtaining community anchor institution agreements. Alternative owners of rights of way locations have been secured to avoid delays in the following quarter. Contract negotiations with community anchor institutions are improving through strategic partnerships with our service providers. | UTOPIA continues to make adjustments to the initial project deployment locations and time frames to mitigate the impacts from these challenges and issues. The project will continue to make significant progress. We anticipate project completion by end of Q2-2013. | TRUE
NT10BIX5570127 | 2013 | Q2 | Q2 - 2013 | 116 Community Anchor Institutions and 129 remote facilities for Community Anchor Institutions are now connected using BTOP funds. These connections consist of public safety entities, schools (k-12), Institutions of higher education, community colleges, community support organizations, government facilities, and medical facilities. Two hundred and seventeen miles of fiber have been installed collectively in the cities of Centerville, Orem, Layton, Midvale, West Valley and Murray. Network Design has been completed for the project. Construction activities are well underway with 26.94 full-time equivalent jobs created during the quarter. | 142 | 0 | 0 | 0 | 142 | 0 | 0 | 58 | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. Based on discussion with NTIA we were currently reporting sheath footage and now we are reporting path or route footage. Total miles anticipated for the project will be 162 miles. These delays are not expected to significantly impact project completion. Project will be completed by September 30, 2013 | N/A | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. Based on discussion with NTIA we were currently reporting sheath footage and now we are reporting path or route footage. Total miles anticipated for the project will be 162 miles. These delays are not expected to significantly impact project completion. Project will be completed by September 30, 2013 | N/A | N/A | Milestone baseline variance continued due to longer than expected time frames to secure rights of way and easements for many points of interconnect. These delays are not expected to significantly impact project completion. Project will be completed by September 30, 2013 | 19 | 0 | 0 | There are 19 agreements with providers who have improved access to subscribers resulting from the investment of BTOP funds. InfoWest, 1Wire, Utah Broadband, Brigham.net, Fibernet, Voonami, Spectrum, XMission, Integra Telecom, Windstream, Telesphere, Veracity, TADA, Skywire, SumoFiber, Senawave, Webwave, Centracom and Beehive Broadband. | 29 wholesale data packages are available to service providers and other government entities. Please see attachment for the total connected to each product and in the second tab the specific products utilized by the additional community anchor institutions. | N/A | 0 | 19 | 0 | 29 | N/A | Nineteen existing service providers are receiving improved access to subscribers because of BTOP funds | N/A | See attached service offerings | 116 | 40 | 76 | 29 | Fewer agreements were secured than anticipated due to challenges in finalizing terms. Projects anchors will be completed by September 30, 2013 | Subscribers receiving new services through UTOPIA or UTOPIA Service Providers. | Subscribers receiving improved services through UTOPIA or UTOPIA Service Providers. | There are 29 speed tiers currently available to community anchor institutions. See attachment indicating the number of subscribers for each. | 10 | 0 | 0 | 0 | 1 | Passed using the middle mile lateral cable to an anchor. | N/A | N/A | N/A | There is 1 speed tier currently available to residential service providers which they re-sale to residential households. | 5 | 0 | 0 | 0 | 15 | Passed using the middle mile lateral cable to an anchor institution | N/A | N/A | N/A | There are 15 speed tiers currently available to businesses through existing service providers. | N/A | FALSE | N/A | UTOPIA will provide new broadband connections to approximately 150 total community anchor institutions throughout West Valley, Layton, Murray, Centerville, Midvale, and Orem. We will have constructed approximately 262 miles of fiber in parts of Midvale, West Valley, Layton, and Orem. We are working with local leaders using joint community outreach efforts to target business districts in these areas who will use the network to bolster economically distressed areas. We will deploy and test an additional 3 points of interconnection. Procurement activities will include the purchase of network equipment and construction materials. | Utopia | N/A | UTOPIA continues to make adjustments to the initial project deployment locations and time frames to mitigate the impacts from these challenges and issues. The project will be completed by September 30th, 2013. | TRUE
NT10BIX5570127 | 2013 | Q3 | Q3 - 2013 | 158 Community Anchor Institutions and 129 remote facilities for Community Anchor Institutions are now connected using BTOP funds. These connections consist of public safety entities, schools (k-12), Institutions of higher education, community colleges, community support organizations, government facilities, and medical facilities. Two hundred and sixty four miles of fiber have been installed collectively in the cities of Centerville, Orem, Layton, Midvale, West Valley and Murray. The network design, construction, testing and installations have been completed for the project. | 149 | 0 | 0 | 0 | 142 | 0 | 0 | 62 | Project has been completed. The variance between engineered footage and completed footage is due to the use of existing city and state conduit and aerial support strand in some of the project areas. | N/A | N/A | N/A | Project has been completed. The variance between engineered footage and completed footage is due to the use of existing city and state conduit and aerial support strand in some of the project areas. | N/A | N/A | Project has been completed. All community Anchor Institutions are served with Interconnection Points | 19 | 0 | 0 | There are 19 agreements with providers who have improved access to subscribers resulting from the investment of BTOP funds. InfoWest, 1Wire, Utah Broadband, Brigham.net, Fibernet, Voonami, Spectrum, XMission, Integra Telecom, Windstream, Telesphere, Veracity, TADA, Skywire, SumoFiber, Senawave, Webwave, Centracom and Beehive Broadband. | 9 wholesale data packages are available to service providers and other government entities. Please see attachment for the total connected to each product and in the second tab the specific products utilized by the additional community anchor institutions. | N/A | 0 | 19 | 0 | 29 | N/A | Nineteen existing service providers are receiving improved access to subscribers because of BTOP funds | N/A | See attached service offerings | 158 | 39 | 119 | 29 | Project CAI's have been completed | Subscribers receiving new services through UTOPIA or UTOPIA Service Providers. | Subscribers receiving improved services through UTOPIA or UTOPIA Service Providers. | There are 29 speed tiers currently available to community anchor institutions. See attachment indicating the number of subscribers for each. | 10 | 0 | 0 | 0 | 1 | Passed using the middle mile lateral cable to an anchor. | N/A | N/A | N/A | There is 1 speed tier currently available to residential service providers which they re-sale to residential households. | 5 | 0 | 0 | 0 | 15 | Passed using the middle mile lateral cable to an anchor institution | N/A | N/A | N/A | There are 15 speed tiers currently available to businesses through existing service providers. | N/A | FALSE | N/A | We will continue to finish and complete the closeout of the project. | Utopia | N/A | N/A | TRUE
NT10BIX5570128 | 2010 | Q4 | Q4 - 2010 | Listed below are the project accomplishments completed during the quarter ending 12/31/10: -Team members submitted and received approval for the 6 Month Expenditure Plan. -Team members submitted the first draft of the Environmental Assessment to NTIA. -Procurement Team members released a RFP for Project Mapping, awarded the contract and began the mapping process. -Completed land survey for three proposed hub sites. -Procurement Team members released a RFP for Construction and Headend Materials. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | No signed agreements | N/A | There will be no third party operators of our network. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The SmartBand Project Plans on completing the following task during the next quarter: -release a RFP for Construction Services and award the contract for construction services. -approval of final specifications and design. -approval of final project plans. -Environmental Review Complete (NEPA Compliance, and Finding of No Significant Impact). -Complete Project Mapping. -Complete Hub Site Acquisition. -Complete enough permitting to allow construction to begin and allow permitting crews to stay ahead of the construction crews. -Release RFP for Equipment. -Initiate construction of Enterprise Hub Site 1, SAEC Fiber Zone 1, Anchor Institutions Fiber Zone 1, Business Customers Fiber Zone 1 and Core Fiber Zone 1. -Initiate upgrade of Troy Headend and Hub Site. | Troy Cablevision, Inc. | No challenges or issues noted. | As with any construction project, weather is always a factor. Due to our project be in the south, we do not anticipated cold weather to be a problem, but if temperatures are close to freezing underground construction will be slowed or stopped. Rain however could cause significant delays in construction during the next quarter. | TRUE
NT10BIX5570128 | 2011 | Q1 | Q1 - 2011 | Listed below are the SmartBand Project accomplishments completed during the quarter ending 03/31/2011: - Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to track financial milestones. - Procurement Team Members have begun receiving signed contracts for the Construction and Headend Materials Request For Proposal (RFP) that was awarded in First Quarter 2011. Troy Cablevision, Inc. (Troy Cable) has ordered materials and has engineered plans for three of approximately thirty-five project segments. - Procurement Team Members released an RFP for Construction Services and have awarded the contract. Construction is set to begin in Second Quarter 2011. - Procurement Team Members released an RFP for an Emergency Alert System (EAS) and have awarded the contract. Equipment and materials have been ordered and received. - The Environmental Assessment has been completed and approved by National Telecommunications and Information Administration. - Engineering Consultants have been hired and are currently in the process of designing and mapping the Project. - Approximately 90% of the map field work has been completed and 65% of the AutoCAD (Mapping) work has been completed. - Mapping and Permitting Team Members continue to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 1 of the Build Out Plan. - Troy Cable has closed a loan for its Cash Match funding. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | No signed agreements. | N/A | There will be no third party operators of our network. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The SmartBand Project proposes to complete the following tasks during the quarter which will end June 30, 2011: - Troy Cable will launch numerous Request for Proposals during the Second Quarter 2011 for Equipment and Machinery as it pertains to the SmartBand Project to include the following: Cable Modem Termination System (CMTS); Splicing Trailers; Bucket Trucks; Van/Installer Trucks; OTDR and Fusion Splicer Equipment; Telecom Shelters; RF Passive Combining/Management; EDFA, 1550 Transmitters, and WDM Filters and Assemblies; DC Power Plant Upgrade; DWDM Network; Active Ethernet ONT and SFP; - Project Team Members will continue to monitor progress to total Project using % complete construction reports along with budget to actual reports to track financial milestones. - Team Members will execute a Construction Services Agreement with the Vendor awarded the Construction Services of Phase 1 of the Build Out Plan. - Construction is scheduled to begin on three of approximately thirty-five project segments in April 2011, with two additional project segments scheduled to begin between May and June. | Troy Cablevision, Inc. | No challenges or issues noted. | Challenges related to Project milestones include delays from weather and slow responses from pole owners related to permitting request. | TRUE
NT10BIX5570128 | 2011 | Q2 | Q2 - 2011 | Listed below are the SmartBand Project accomplishments completed during the quarter ending June 30, 2011: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. - Procurement Team Members have continued receiving signed contracts for numerous Requests for Proposals that were awarded during the end of First Quarter and Second Quarter 2011. -Troy Cablevision, Inc. (Troy Cable) has continued to order and receive materials from the awarded Vendors for Construction and Head end Materials for seven of approximately fifty project segments. -Engineering Consultants have mapped approximately fifty project segments. -Construction has begun, with the awarded Contractor for Construction Services, on Phase 1 of the Build Out Plan which encompasses three of five counties: Pike, Dale, and Coffee, as outlined in the Southeast Alabama SmartBand Project Plan. -Troy Cable has completed 57.32 fiber miles of the total 595 mile Project which represents 9.63% construction completion through Second Quarter 2011. -Procurement Team Members released numerous Requests for Proposals during April, May and, June for Equipment, including: Telecom Shelters; OTDR and Fusion Splicing Equipment; Cable Modem Termination System (CMTS); Splicing Trailers; RF Passive Combining/Management; Return Path Receiver; Provisioning; Generators and Batteries for DC Power System; Switches and Routers; Tools; GX2 Chassis; EDFA; 1 | 57 | 0 | 0 | 0 | 57 | 0 | 0 | 6 | Due to lead times on materials the Project did not get as many miles as projected after receiving the FONSI. Troy Cable has added one additional Underground crew and three additional construction employees to existing Aerial Crew. The awarded Construction Contractor has also added one additional Aerial crew to their construction crew. A total of 5 Aerial Crews and 2 Underground Crews are currently working on the Project to catch Troy Cable up to the Projections. Contractor is looking at adding an additional Underground crew in August. | N/A | N/A | N/A | Due to lead times on materials the Project did not get as many miles as projected after receiving the FONSI. Troy Cable has added one additional Underground crew and three additional construction employees to existing Aerial Crew. The awarded Construction Contractor has also added one additional Aerial crew to their construction crew. A total of 5 Aerial Crews and 2 Underground Crews are currently working on the Project to catch Troy Cable up to the Projections. Contractor is looking at adding an additional Underground crew in August. | N/A | N/A | Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) catch Troy Cable up to the Projections. Contractor is looking at adding an additional Underground crew in August. Due to lead times on materials the Project did not get as many miles as projected after receiving the FONSI. Troy Cable has added one additional Underground crew and three additional construction employees to existing Aerial Crew. The awarded Construction Contractor has also added one additional Aerial crew to their construction crew. A total of 5 Aerial Crews and 2 Underground Crews are currently working on the Project to catch Troy Cable up to the Projections. Contractor is looking at adding an additional Underground crew in August. Although all upgrades are not complete at each Hub Site interconnection points are accessible at the Troy Headend and the following Points of Presence (POP): Ozark, Elba, Brantley, Luverne, and Daleville. Prefabricated Hub Sites have been delivered to Enterprise # 2 and Midland City and the other Hub Site in Enterprise has been secured but none of those sites have been brought on line. As of July 1, 2011, Information Transport Solutions, Inc. (ITS) has installed equipment at the Troy Headend to provide last mile services to the Ozark City School System. Also on July 1, 2011 SmartBand connected New Brockton City Schools to the SmartBand network. SmartBand is currently delivering the New Brockton traffic back to Alabama Connecting Classrooms via previously non-federal funded inter-connections to Troy University. Traffic is then delivered via AT&T back to Montgomerys for any variance from the baseline plan or any other relevant information) catch Troy Cable up to the Projections. Contractor is looking at adding an additional Underground crew in August. Due to lead times on materials the Project did not get as many miles as projected after receiving the FONSI. Troy Cable has added one additional Underground crew and three additional construction employees to existing Aerial Crew. The awarded Construction Contractor has also added one additional Aerial crew to their construction crew. A total of 5 Aerial Crews and 2 Underground Crews are currently working on the Project to catch Troy Cable up to the Projections. Contractor is looking at adding an additional Underground crew in August. Although all upgrades are not complete at each Hub Site interconnection points are accessible at the Troy Headend and the following Points of Presence (POP): Ozark, Elba, Brantley, Luverne, and Daleville. Prefabricated Hub Sites have been delivered to Enterprise # 2 and Midland City and the other Hub Site in Enterprise has been secured but none of those sites have been brought on line. As of July 1, 2011, Information Transport Solutions, Inc. (ITS) has installed equipment at the Troy Headend to provide last mile services to the Ozark City School System. Also on July 1, 2011 SmartBand connected New Brockton City Schools to the SmartBand network. SmartBand is currently delivering the New Brockton traffic back to Alabama Connecting Classrooms via previously non-federal funded inter-connections to Troy University. Traffic is then delivered via AT&T back to Montgomery. | 0 | 2 | 0 | In process - Information Transport Solutions, Inc. Computer Sciences Corporation - Alabama Connecting Classrooms, Educators and Students Statewide (ACCESS) | In process - Transport and bandwidth to local schools3 | There will be no third party operators of our network. | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | 0 | 0 | 0 | 0 | Due to Environmental Assessment Process delay SmartBand was not able to meet Baseline Projections. As of July 1, 2011 SmartBand connected the first two anchors and is working diligently to catch back up with projections. | Due to Environmental Assessment Process delay SmartBand was not able to meet Baseline Projections. As of July 1, 2011 SmartBand connected the first two anchors and is working diligently to catch back up with projections. | Due to Environmental Assessment Process delay SmartBand was not able to meet Baseline Projections. As of July 1, 2011 SmartBand connected the first two anchors and is working diligently to catch back up with projections. | Due to Environmental Assessment Process delay SmartBand was not able to meet Baseline Projections. As of July 1, 2011 SmartBand connected the first two anchors and is working diligently to catch back up with projections. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The SmartBand Project Team proposes to complete the following tasks during the Third Quarter 2011: -Troy Cable will launch numerous Requests for Proposals during the Third Quarter 2011 for Equipment and Machinery as it pertains to the SmartBand Project to include the following: DC Power Systems; VOD System; Operations Support System / Business Support Systems (OSS/BSS); Van / Installer Trucks; GPON System; Switches; Routers; and DWDM Network. -Project Team Members will continue to monitor progress to total Project using % complete construction reports along with budget to actual reports to measure financial milestones. -Troy Cable has connected one (1) Community Anchor Institution via a Last Mile service provider & connected the school to Alabama Connecting Classrooms, Educators and Students Statewide (ACCESS) which installed equipment in Troy Head end. -Troy Cable intends to connect five (5) other Community Anchor Institutions during Third Quarter 2011. -Troy Cable will continue construction with a projection of 152 fiber miles being completed of the total 595 mile Project which represents 25.5% construction completion through Third Quarter 2011. | Troy Cablevision, Inc. | No challenges or issues noted. | There is the potential for problems in receiving fiber for the Project due to extended lead times from Vendor. Troy Cable was notified by Vendor that delivery times would be extended from three weeks to six to eight weeks. Troy Cable is making every effort to order materials six weeks before anticipated start date to ensure timely arrival of materials before construction is scheduled to begin. If the Project runs out of fiber Troy Cable will continue to put up strand and install conduit in anticipation of receiving fiber. | TRUE
NT10BIX5570128 | 2011 | Q3 | Q3 - 2011 | Listed below are the SmartBand Project accomplishments completed during the quarter ending September 30, 2011: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -Approximately 96% of map field work and 87% of the AutoCAD (mapping) work has been completed. The SmartBand Project is approximately 25% complete of the post construction (As-Built) or final mapping. -The Mapping and Permitting Team Members continue to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. - Procurement Team Members have continued receiving signed contracts for numerous Request for Proposals that were awarded during the end of the Second Quarter 2011. -Troy Cable has continued to order and receive materials from the awarded Vendors for Construction and Head End Materials for nineteen (19) of approximately fifty (50) job segments. -Construction has continued with the awarded Contractor for Construction Services. Construction has continued on Phase 1 of the Build Out Plan and includes three of five counties, Pike, Dale & Coffee, as outlined in the Southeast Alabama SmartBand Project Plan. -Although last quarter Troy Cable projected an aggressive goal of 152 fiber miles constructed through the end of the Third Quarter, Troy Cable has completed 177.57 fiber miles of the total 595 mile Project. Troy Cable ha | 177 | 0 | 0 | 0 | 177 | 0 | 0 | 6 | Due to lead times on materials the Project did not get as many miles as projected after receiving the FONSI. Troy Cable has added one additional Underground crew and three additional construction employees to existing Aerial Crew. The awarded Construction Contractor has also added one additional Aerial crew to their construction crew. A total of five (5) Aerial Crews and two (2) Underground Crews are currently working on the Project to catch Troy Cable up to the Projections. The Contractor added one (1) additional Underground crew in August. Troy Cable has constructed 177.57 fiber miles of the total 595 mile Project and has placed 2.43 miles of empty pipe and 2.98 miles of bare strand and has deployed 177.57 new network miles. | N/A | N/A | N/A | Troy Cable has constructed 177.57 fiber miles of the total 595 mile Project and has placed 2.43 miles of empty pipe and 2.98 miles of bare strand. Of the 177.57 fiber miles constructed 177.57 miles consist of new fiber. | N/A | N/A | Although all upgrades are not complete at each Hub Site interconnection points are accessible at the Troy Headend and the following Points of Presence (POP): Ozark, Elba, Brantley, Luverne, and Daleville. Prefabricated Hub Sites have been delivered to Enterprise # 2 and Midland City and the other Hub Site in Enterprise has been secured , both Enterprise sites were brought on-line in October 2011. As of July 1, 2011, Information Transport Solutions, Inc. (ITS) has installed equipment at the Troy Headend to provide Last Mile services to the Ozark City School System. Also on July 1, 2011 SmartBand connected New Brockton City Schools to the SmartBand network. SmartBand is currently delivering the New Brockton traffic back to Alabama Connecting Classrooms via previously non-federal funded inter-connections to Troy University. Traffic is then delivered via AT&T back to Montgomerye at each Hub Site interconnection points are accessible at the Troy Headend and the following Points of Presence (POP): Ozark, Elba, Brantley, Luverne, and Daleville. Prefabricated Hub Sites have been delivered to Enterprise # 2 and Midland City and the other Hub Site in Enterprise has been secured , both Enterprise sites were brought on-line in October 2011. As of July 1, 2011, Information Transport Solutions, Inc. (ITS) has installed equipment at the Troy Headend to provide Last Mile services to the Ozark City School System. Also on July 1, 2011 SmartBand connected New Brockton City Schools to the SmartBand network. SmartBand is currently delivering the New Brockton traffic back to Alabama Connecting Classrooms via previously non-federal funded inter-connections to Troy University. Traffic is then delivered via AT&T back to Montgomery. | 2 | 2 | 36 | Information Transport Solutions, Inc. (ITS) Computer Sciences Corporation (CSC) - Alabama Connecting Classrooms, Educators and Students Statewide (ACCESS) | Computer Sciences Corporation (CSC) - 10 Mbps Transport for $700 a month. Information Transport Solutions, Inc. (ITS) - Fiber connections to Ozark School Systems, rack space in Troy Headend and Ozark Hub and internet bandwidth. Revenue for this connection is $5,325 per month. This pricing structure was determined by ITS's state required bid for E-rate services. Traffic is then delivered to Troy University through non-BTOP funded connection. Traffic is transported from Troy University to Montgomery via AT&T) - 10 Mbps Transport for $700 a month. Information Transport Solutions, Inc. (ITS) - Fiber connections to Ozark School Systems, rack space in Troy Headend and Ozark Hub and internet bandwidth. Revenue for this connection is $5,325 per month. This pricing structure was determined by ITS's state required bid for E-rate services. Traffic is then delivered to Troy University through non-BTOP funded connection. Traffic is transported from Troy University to Montgomery via AT&T. | There will be no third party operators of our network. | 2 | 0 | 0 | 2 | No Variance. | No Variance. | No Variance. | 10Mbps = 1 subscriber 100 Mbps = 1 subscriber | 28 | 28 | 0 | 28 | In the Third Quarter SmartBand has connected to twenty-eight (28) Community Anchor Institutions and is diligently working to catch back up with projections. | In the Third Quarter SmartBand has connected to twenty-eight (28) Community Anchor Institutions and is diligently working to catch back up with projections. Twenty-eight (28) Community Anchor Institutions are receiving new access. | N/A | 1 Mbps - 1 Gbps are available. The Community Anchor Institutions took the following: 1 Mbps = 11 subscribers 10 Mbps = 3 subscribers 50 Mbps = 3 subscribers 100 Mbps = 8 subscribers 3 subscribers are taking no service or video or voice only. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The SmartBand Project Team proposes to complete the following tasks during the Fourth Quarter 2011: -Troy Cable will award and contract various Request for Proposals during the Fourth Quarter for additional Equipment and order additional equipment and materials for Request for Proposals that were released in late September 2011, including: GPON and Access Equipment; DWDM Network; Installer Truck(s); Switches; VOD System; and Routers. New Request for Proposals scheduled to be released in Fourth Quarter 2011 include Headend Upgrade for Fiber Management. -Project Team will continue to monitor progress to total Project using % complete construction reports along with budget to actual reports to measure financial milestones. -Although Troy Cable projected an aggressive goal of 152 fiber miles constructed through the end of the Third Quarter, the Construction Team has completed 177.57 fiber miles of the total 595 mile Project. Troy Cable has also placed 2.43 miles of empty pipe and 2.98 miles of bare strand pending the arrival of additional materials needed for completion. During the Fourth Quarter, Troy Cable will continue construction with a projection of 270 fiber miles being completed of the total 595 mile Project which represents 45.38% construction completion through Fourth Quarter 2011. Troy Cable also anticipates the completion of the following: both Enterprise Hubs are scheduled to be brought on-line, Overlap build with Trillion Communications (other BTOP recipien | Troy Cablevision, Inc. | During this Quarter, Troy Cable has experienced extended delivery times for fiber for the Project. In the Second Quarter, Troy Cable was notified by Vendor that delivery times would be extended from three weeks to six to eight weeks. Troy Cable has made every effort to order materials at least six weeks before anticipated start date to ensure timely arrival of materials before construction is scheduled to begin. To ensure that the Project construction continues to run on schedule Troy Cable has ordered enough fiber to construct and complete 278.5 fiber miles. If the Project runs out of fiber Troy Cable will continue to put up strand and install conduit in anticipation of receiving fiber. State Highway DOT permit changes are creating delays in approval of ongoing permits. Anticipating no relief other than loading the system early to meet requirements. Pole applications for make ready with APCO continue to take extended periods of time for approval, APCO has secured additional engineering resources to work through the problem. Troy Cable anticipates by Second Quarter 2012 that we should see some relief. | There is the potential for problems in receiving fiber for the Project due to extended lead times from Vendor. During the previous quarter, Troy Cable had experienced extended delivery times for fiber for the Project due to an announcement by the awarded fiber Vendor that delivery times would be extended from three weeks to six to eight weeks. Troy Cable has and will continue to make every effort to order materials at least six weeks before anticipated start date to ensure timely arrival of materials before construction is scheduled to begin. To ensure that the Project construction continues to run on schedule Troy Cable has ordered enough fiber to construct and complete 278.5 fiber miles. If the Project runs out of fiber Troy Cable will continue to put up strand and install conduit in anticipation of receiving fiber. State Highway DOT permit changes are creating delays in approval of ongoing permits. Anticipating no relief other than loading the system early to meet requirements. Pole applications for make ready with APCO continue to take extended periods of time for approval, APCO has secured additional engineering resources to work through the problem. Troy Cable anticipates by Second Quarter 2012 that we should see some relief. | TRUE
NT10BIX5570128 | 2011 | Q4 | Q4 - 2011 | Listed below are the SmartBand Project accomplishments completed during the quarter ending December 31, 2011: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -Approximately 97% of map field work and 89% of the AutoCAD (mapping) work has been completed. The SmartBand Project is approximately 30% complete of the post construction (As-Built) or final mapping. -The Mapping and Permitting Team Members continue to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. -Approximately fifty-two (52) job segments have been engineered and mapped by our Engineering Consultants. -Procurement Team Members have continued receiving signed contracts from Vendors for Request for Proposals awarded during the Fourth Quarter 2011. -Troy Cable has continued to order and receive materials from the awarded Vendors for Construction and Headend Materials for thirty (30) of the approximately fifty-two (52) job segments. -Construction has continued with the awarded Contractor for Construction Services. Construction has continued on Phase 1 of the Build Out Plan and includes five of six counties: Pike, Dale, Crenshaw, Houston, and Coffee, as outlined in the Southeast Alabama SmartBand Project Plan. -Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on twenty-eight (28) of the fifty-two (52) job segments. The construction crews consist of three (3) Underground crews and four (4) Aerial crews. The addition of the Underground and Aerial crews reflects the progress Troy Cable is making to catch-up to the Baseline Budget Reporting for fiber miles constructed. -Last quarter, Troy Cable projected an aggressive goal of 270 fiber miles through the end of the Fourth Quarter. Troy Cable has completed 273.21 fiber miles of the total 595 mile Project. Troy Cable has also placed 1.12 miles of empty pipe and 20.09 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 95.64 fiber miles were constructed during the Fourth Quarter. The total fiber miles constructed represents 45.92% completion of the overall fiber construction. -Troy Cable launched Request for Proposal during the Fourth Quarter for Equipment relevant to the Headend Upgrade for Fiber Distribution System. -The Team has awarded contracts and has begun ordering and receiving equipment for Request for Proposals released during previous quarters. Troy Cable has ordered and begun receiving equipment including: Business Support Systems (â€œOSS/BSSâ€); DC Power System; VOD System; DWDM Network; Installer Vans; Bucket Trucks; Routers; Switches; and GPON and Access Equipment. -Troy Cable has connected and turned-up five (5) Community Anchor Institutions during the Fourth Quarter. Troy Cable has connected and turned-up twelve (12) Businesses during the Fourth Quarter. - The following new Hub Sites have been brought on line as of December 31, 2011: Enterprise #1 (South) and Enterprise #2 (North). Both sites will have the DWDM Network installed next quarter. Next quarter, the following existing Hub Sites will be connected to the DWDM Network: Troy; Brundidge; Ozark; Daleville; and Elba. The following existing Hub Sites are currently online but are receiving improvements and will be connected to the DWDM Network by Third Quarter 2012: Brantley and Luverne. -Troy Cable has constructed 25.47 fiber miles of the Overlap Build. The current construction will be spliced and tested during the First Quarter 2012. The Overlap Build has 2 miles of construction pending for Department of Transportation and APCO Permits. | 273 | 0 | 0 | 0 | 273 | 0 | 0 | 8 | Due to extended delivery lead times on materials the Project did not construct as many miles as projected after receiving the FONSI. Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on twenty-eight (28) of the fifty-two (52) job segments. The construction crews consist of three (3) Underground crews and four (4) Aerial crews. The addition of the Underground and Aerial crews reflects the progress Troy Cable is making to catch-up to the Baseline Budget Reporting for fiber miles constructed. Troy Cable has completed 273.21 fiber miles of the total 595 mile Project. Troy Cable has also placed 1.12 miles of empty pipe and 20.09 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 95.64 fiber miles were constructed during the Fourth Quarter 2011. The total fiber miles constructed represents 45.92% completion of the overall fiber construction. | N/A | N/A | N/A | Troy Cable has completed 273.21 fiber miles of the total 595 mile Project. Troy Cable has also placed 1.12 miles of empty pipe and 20.09 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 95.64 fiber miles were constructed during the Fourth Quarter 2011. The total fiber miles constructed represents 45.92% completion of the overall fiber construction and consists of 273.21 miles of new fiber. | N/A | N/A | [REDACTED] | 4 | 1 | 36 | [REDACTED] | [REDACTED] | There will be no third party operators of our network. | 4 | 0 | 0 | 4 | No variance from the Baseline | No variance from the Baseline. | No variance from the Baseline | 20 Mbps = 1 subscriber(s) 100 Mbps = 2 subscriber(s) 450 Mbps = 1 subscriber(s) | 25 | 25 | 0 | 25 | SmartBand has connected to twenty-five (25) Community Anchor Institutions and is aggressively working to catch up to Baseline Projections. | SmartBand has connected to twenty-five (25) Community Anchor Institutions and is aggressively working to catch up to Baseline Projections. Twenty-five (25) Community Anchor Institutions are receiving new access. | Not applicable. | 1 Mbps â€“ 1 Gbps are available. The Community Anchor Institutions took the following: 1 Mbps = 9 subscribers 10 Mbps = 4 subscribers 50 Mbps = 2 subscribers 100 Mbps = 6 subscribers 4 subscribers are taking no services or video or voice only. | 0 | 0 | 0 | 0 | 0 | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | 137 | 12 | 4 | 8 | 12 | SmartBand has passed One Hundred Thirty-seven (137) Businesses as a result of the Southeast Alabama SmartBand Project. | SmartBand has connected to twelve (12) Businesses as a result of the Southeast Alabama SmartBand Project. | SmartBand has connected to twelve (12) Businesses as a result of the Southeast Alabama SmartBand Project. Four (4) Businesses are receiving new access. | SmartBand has connected to twelve (12) Businesses as a result of the Southeast Alabama SmartBand Project. Eight (8) Businesses are receiving improved access. | 1 Mbps â€“ 1 Gbps are available. The Community Anchor Institutions took the following: 1 Mbps = 0 subscribers 5 Mbps = 3 subscribers 10 Mbps = 6 subscribers 15 Mbps = 2 subscribers 45 Mbps = 1 subscribers 100 Mbps = 0 subscribers | N/A | FALSE | N/A | Listed below are the SmartBand Project accomplishments planned during the quarter ending March 31, 2012: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. - Troy Cable will launch a Request for Proposal during the First Quarter 2012 for Equipment relevant to the Firewall. The Team has awarded contracts and has continued ordering and receiving equipment for Request for Proposals released during previous quarters. Troy Cable has ordered and begun receiving equipment including: Business Support Systems (“OSS/BSS”); DC Power System; VOD System; DWDM Network; Installer Vans; Bucket Trucks; Routers; Switches; and GPON and Access Equipment. The Billing Support Systems (“OSS/BSS”) is scheduled to go on line March 1, 2012. -Last quarter, Troy Cable projected an aggressive goal of 270 fiber miles through the end of the Fourth Quarter. Troy Cable has completed 273.21 fiber miles of the total 595 mile Project. Troy Cable has also placed 1.12 miles of empty pipe and 20.09 miles of bare strand pending the arrival of additional materials needed for completion. During the First Quarter 2012, Troy Cable will continue construction with a projection of 375 fiber miles being completed of the total 595 mile Project which represents 63.02% construction completion through First Quarter 2012. -Troy Cable plans to add one (1) additional Broadband wholesaler or Last Mile provider during the First Quarter 2012. -Troy Cable also anticipates connecting to an additional twenty (20) Community Anchor Institutions during the First Quarter 2012. -Troy Cable anticipates the completion of fiber connections to Dothan wholesale Internet Service Providers with service turn up during the First Quarter 2012. - Phase 1 of the DWDM Network installation will be complete by the end of First Quarter 2012. - Phase 2 of construction will start during First Quarter 2012. | Troy Cablevision, Inc. | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570128 | 2012 | Q1 | Q1 - 2012 | Listed below are the SmartBand Project accomplishments completed during the quarter ending March 31, 2012: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -Approximately 97% of map field work and 90% of the AutoCAD (mapping) work has been completed. The SmartBand Project is approximately 32% complete of the post construction (As-Built) or final mapping. -The Mapping and Permitting Team Members continue to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. -Approximately fifty-four (54) job segments have been engineered and mapped by our Engineering Consultants. -Procurement Team Members have continued receiving signed contracts from Vendors for Request for Proposals awarded during the Fourth Quarter 2011 and First Quarter 2012. -Troy Cable has continued to order and receive materials from the awarded Vendors for Construction and Headend Materials for forty-nine (49) of the approximately fifty-four (54) job segments. -Construction has continued with the awarded Contractor for Construction Services. Construction has begun on Phase 2 of the Build Out Plan and covers all six counties as outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Pike, Dale, Crenshaw, Coffee and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. -Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on thirty-four (34) of the fifty-four (54) job segments. The construction crews consist of five (5) Underground crews, four (4) Aerial crews, four (4) Fiber Splicers, and three (3) Construction Inspectors. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. -Last quarter, Troy Cable projected an aggressive goal of 375 fiber miles through the end of the First Quarter. Troy Cable has completed 383.04 fiber miles of the total 595 mile Project. Troy Cable has also placed 4.50 miles of empty pipe and 5.32 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 109.83 fiber miles were constructed during the First Quarter. The total fiber miles constructed represents 64.38% completion of the overall fiber construction. -The Team has awarded contracts and continues to order and receive materials from the awarded Vendors for additional equipment and materials for Request for Proposals released during previous quarters like: DWDM Network; Switches; Routers; Access Gear ("ADTRAN"); Provisioning; Light Meters; Bucket Trucks; and Access Controllers. Troy Cable has ordered and begun installing equipment for the Headend Upgrade for Fiber Distribution System. The Engineering Team has deployed the following network equipment: Billing Support System ("OSS/BSS"); DWDM Network Equipment; Routers; Switches; and Access Gear. The Billing Support System went live on line March 4, 2012. -Troy Cable has connected and turned-up thirty-three (33) Community Anchor Institutions during the First Quarter. Troy Cable has connected and turned-up twenty-four (24) Businesses through the First Quarter. -The following Hub Sites and co-location facilities have been brought on line as of March 31, 2012: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; and Troy. Next quarter, the following existing Hub Sites and co-location facilities will be connected to the DWDM Network: Luverne; Ozark; Brundidge; and Montgomery. The following existing Hub Sites are currently online but are receiving improvements and will be connected to the DWDM Network by Third Quarter 2012: Brantley and Midland City. -The Engineering Team has brought on-line a temporary ring to meet co-location requirements in Houston County. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas and has begun negotiating three (3) Interconnection Agreements. -Troy Cable has constructed approximately 28 fiber miles of the Overlap Build. | 383 | 0 | 0 | 0 | 383 | 0 | 0 | 12 | Due to extended delivery lead times on materials the Project did not construct as many miles as projected after receiving the FONSI. Construction has continued with the awarded Contractor for Construction Services. Construction has begun on Phase 2 of the Build Out Plan and covers all six counties as outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Pike, Dale, Crenshaw, Coffee and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on thirty-four (34) of the fifty-four (54) job segments. The construction crews consist of five (5) Underground crews, four (4) Aerial crews, four (4) Fiber Splicers, and three (3) Construction Inspectors. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. Troy Cable has completed 383.04 fiber miles of the total 595 mile Project. Troy Cable has also placed 4.50 miles of empty pipe and 5.32 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 109.83 fiber miles were constructed during the First Quarter. The total fiber miles constructed represents 64.38% completion of the overall fiber construction. | Not Applicable | Not Applicable | Not Applicable | Troy Cable has completed 383.04 fiber miles of the total 595 mile Project. Troy Cable has also placed 4.50 miles of empty pipe and 5.32 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 109.83 fiber miles were constructed during the First Quarter. The total fiber miles constructed represents 64.38% completion of the overall fiber construction and consists of 383.04 miles of new fiber. | Not Applicable | Not Applicable | [REDACTED] | 6 | 4 | 12 | [REDACTED] | [REDACTED] | There will be no Third Party Operators of our Network. | 6 | 0 | 1 | 6 | No variance from the Baseline. | No variance from the Baseline. | No variance from the Baseline. | 20 Mbps = 1 subscriber(s) 100 Mbps = 2 subscriber(s) 450 Mbps = 1 subscriber(s) The other 2 Providers w/ signed agreements are only currently Providing Wholesale Services to the Project. | 33 | 33 | 0 | 33 | SmartBand has connected to thirty-three (33) Community Anchor Institutions and is aggressively working to catch up to Baseline Projections. | SmartBand has connected to thirty-three (33) Community Anchor Institutions and is aggressively working to catch up to Baseline Projections. Thirty-three (33) Community Anchor Institutions are receiving new access. | SmartBand has connected to thirty-three (33) Community Anchor Institutions and is aggressively working to catch up to Baseline Projections. | 1 Mbps â€“ 1 Gbps are available. The Community Anchor Institutions took the following: 1 Mbps = 14 subscribers 5 Mbps = 0 subscribers 10 Mbps = 4 subscribers 15 Mbps = 0 subscribers 20 Mbps = 1 subscribers 45 Mbps = 0 subscribers 50 Mbps = 3 subscribers 100 Mbps = 8 subscribers 3 subscribers are taking no services or video or voice only. | 0 | 0 | 0 | 0 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 148 | 24 | 16 | 8 | 24 | SmartBand has passed One hundred forty-eight (148) Businesses as a result of the Southeast Alabama SmartBand Project. | SmartBand has connected to twenty-four (24) Businesses as a result of the Southeast Alabama SmartBand Project. | SmartBand has connected to twenty-four (24) Businesses as a result of the Southeast Alabama SmartBand Project. Sixteen (16) Businesses are receiving new access. | SmartBand has connected to twenty-four (24) Businesses as a result of the Southeast Alabama SmartBand Project. Eight (8) Businesses are receiving improved service. | 1 Mbps â€“ 1 Gbps are available. The Businesses took the following: 1 Mbps = 2 subscribers 5 Mbps = 0 subscribers 10 Mbps = 12 subscribers 15 Mbps = 3 subscribers 20 Mbps = 0 subscribers 45 Mbps = 1 subscribers 50 Mbps = 0 subscribers 100 Mbps = 0 subscribers 6 subscribers are taking no services or video or voice only. | N/A | FALSE | N/A | Listed below are the SmartBand Project accomplishments planned during the quarter ending June 30, 2012: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. - Troy Cable will launch a Request for Proposal during the Second Quarter 2012 for Equipment relevant to the Firewall. The Team has awarded contracts and will continue to order and receive equipment for Request for Proposals released during previous quarters, like: VOD System; DWDM Network; Routers; Switches; GPON Equipment; Access Gear ("ADTRAN"); Provisioning; Light Meters; and Access Controllers. Troy Cable has ordered and begun receiving equipment including: Business Support Systems (â€œOSS/BSSâ€); DC Power System; VOD System; DWDM Network; Installer Vans; Bucket Trucks; Routers; Switches; and GPON and Access Equipment. The Billing Support Systems (â€œOSS/BSSâ€) is went live on line March 4, 2012. -Last quarter, Troy Cable projected an aggressive goal of 375 fiber miles through the end of the First Quarter. Troy Cable has completed 383.04 fiber miles of the total 595 mile Project. Troy Cable has also placed 4.50 miles of empty pipe and 5.32 miles of bare strand pending the arrival of additional materials needed for completion. During the Second Quarter 2012, Troy Cable will continue construction with a projection of 475 fiber miles being completed of the total 595 mile Project which represents 79.83% construction completion through Second Quarter 2012. -Troy Cable plans to add one (1) additional Broadband wholesaler or Last Mile provider during the Second Quarter 2012. -Troy Cable also anticipates connecting to an additional ten (10) Community Anchor Institutions during the Second Quarter 2012. -Phase 2 of the DWDM Network Installation will be complete by the end of the Second Quarter 2012. | Troy Cablevision, Inc. | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570128 | 2012 | Q2 | Q2 - 2012 | Listed below are the SmartBand Project accomplishments completed during the quarter ending June 30, 2012: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -Approximately 98% of map field work and 91% of the AutoCAD (mapping) work has been completed. The SmartBand Project is approximately 37% complete of the post construction (As-Built) or final mapping. -The Mapping and Permitting Team Members continue to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. -Approximately fifty-five (55) job segments have been engineered and mapped by our Engineering Consultants. -Procurement Team Members have continued receiving signed contracts from Vendors for Request for Proposals awarded during the previous quarters. -Troy Cable has continued to order and receive materials from the awarded Vendors for Construction and Headend Materials for forty-nine (49) of the approximate fifty-five (55) job segments. -Construction has continued with the awarded Contractor for Construction Services. Construction has begun on Phase 2 of the Build Out Plan and covers all six counties as outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Pike, Dale, Crenshaw, Coffee and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. -Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on forty-seven (47) of the fifty-five (55) job segments. The construction crews consist of seven (7) Underground crews, six (6) Aerial crews, five (5) Fiber Splicers, and three (3) Construction Inspectors. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. -Last quarter, Troy Cable projected an aggressive goal of 475 fiber miles through the end of the Second Quarter. Troy Cable has completed 477.79 fiber miles of the total 595 mile Project. Troy Cable has also placed 26.44 miles of empty pipe and 15.52 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 94.75 fiber miles were constructed during the Second Quarter. The total fiber miles constructed represents 80.30% completion of the overall fiber construction. Troy Cable has activated 336.73 miles of fiber as of June 30,2012. - The Engineering Team has implemented software & equipment to support the Business Support System & is currently operating the system. The Team is continuing to order & receive materials from the awarded Vendors for additional Equipment & materials for Request for Proposals that were released in prior Quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. -Troy Cable has connected and turned-up forty-nine (49) Community Anchor Institutions throught the Second Quarter. Troy Cable has connected and turned-up forty-one (41) Businesses through the Second Quarter. -The following existing Hub Sites and colocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements and will be connected to the DWDM Network by Third Quarter 2012. - The Team has brought online a temporary ring to meet colocation requirements in Houston and Montgomery Counties. Co-location equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed co-location with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on five (5) Interconnection Agreements. -Troy Cable has constructed approximately 28 fiber miles of the Overlap Build. | 478 | 0 | 0 | 0 | 478 | 0 | 0 | 14 | Due to extended delivery lead times on materials the Project did not construct as many miles as projected after receiving the FONSI. Construction has continued with the awarded Contractor for Construction Services. Construction has begun on Phase 2 of the Build Out Plan and covers all six counties as outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Pike, Dale, Crenshaw, Coffee and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on forty-seven (47) of the fifty-five (55) job segments. The construction crews consist of seven (7) Underground crews, six (6) Aerial crews, five (5) Fiber Splicers, and three (3) Construction Inspectors. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. Troy Cable has completed 477.79 fiber miles of the total 595 mile Project. Troy Cable has also placed 26.44 miles of empty pipe and 15.52 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 94.75 fiber miles were constructed during the Second Quarter. The total fiber miles constructed represents 80.30% completion of the overall fiber construction. | Not Applicable. | Not Applicable. | Not Applicable. | Troy Cable has completed 477.79 fiber miles of the total 595 mile Project. Troy Cable has also placed 26.44 miles of empty pipe and 15.52 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 94.75 fiber miles were constructed during the Second Quarter. The total fiber miles constructed represents 80.30% completion of the overall fiber construction. | Not Applicable. | Not Applicable. | [REDACTED] | 10 | 5 | 12 | [REDACTED] | [REDACTED] | There will be no Third Party Operators of our Network. | 10 | 0 | 1 | 10 | No variance from Baseline. | No variance from Baseline. | No variance from Baseline. | 10 Mbps = 1 subscribers 20 Mbps = 1 subscriber(s) 100 Mbps = 2 subscriber(s) 450 Mbps = 1 subscriber(s) The other 5 Providers with signed agreements are only currently Providing Wholesale Services to the Project. | 49 | 49 | 0 | 49 | SmartBand has connected to forty-nine (49) Community Anchor Institutions and is aggressively working to catch up to Baseline Projections. | SmartBand has connected to forty-nine (49) Community Anchor Institutions and is aggressively working to catch up to Baseline Projections. Forty-nine (49) Community Anchor Institutions are receiving new access. | SmartBand has connected to forty-nine (49) Community Anchor Institutions and is aggressively working to catch up to Baseline Projections. | 1 Mbps to 1 Gbps are available. The Community Anchor Institutions took the following: 1 Mbps = 19 subscribers 5 Mbps = 0 subscribers 10 Mbps = 10 subscribers 15 Mbps = 1 subscribers 20 Mbps = 1 subscribers 45 Mbps = 0 subscribers 50 Mbps = 4 subscribers 100 Mbps = 8 subscribers 6 subscribers are taking no services or video or voice only. | 0 | 0 | 0 | 0 | 0 | Not Applicable. | Not Applicable. | Not Applicable. | Not Applicable. | Not Applicable. | 179 | 41 | 33 | 8 | 41 | SmartBand has passed one hundred seventy-nine (179) Businesses as a result of the Southeast Alabama SmartBand Project. | SmartBand has connected to forty-one (41) Businesses as a result of the Southeast Alabama SmartBand Project. | SmartBand has connected to forty-one (41) Businesses as a result of the Southeast Alabama SmartBand Project. Thirty-three (33) Businesses are receiving new access. | SmartBand has connected to forty-one (41) Businesses as a result of the Southeast Alabama SmartBand Project. Eight (8) Businesses are receiving improved access. | 1 Mbps to 1 Gbps are available. The Businesses took the following: 1 Mbps = 4 subscribers 5 Mbps = 0 subscribers 10 Mbps = 22 subscribers 15 Mbps = 4 subscribers 20 Mbps = 3 subscribers 45 Mbps = 1 subscribers 50 Mbps = 0 subscribers 100 Mbps = 0 subscribers 7 subscribers are taking no services or video or voice only. | Not Applicable. | FALSE | Not Applicable. | Listed below are the SmartBand Project accomplishments completed during the quarter ending September 30, 2012: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -Procurement Team Members will continue receiving signed contracts from Vendors for Request for Proposals awarded during the previous quarters. -Troy Cable will continue to order and receive materials from the awarded Vendors for Construction and Headend Materials for approximate fifty-five (55) job segments. -Construction will continue on Phase 2 of the Build Out Plan which covers all six counties as outlined in the Southeast Alabama SmartBand Project. Counties where construction is taking place includes: Pike, Dale, Crenshaw, Coffee and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. -Troy Cable has hired additional crews to aide in the construction of the fiber route. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. -Troy Cable projects an aggressive goal of 545 fiber miles constructed through the end of the Third Quarter. The total fiber miles constructed represents 91.60% completion of the overall fiber construction. - The Engineering Team will continue to order & receive materials from the awarded Vendors for additional Equipment & materials for Request for Proposals that were released in prior Quarters. -Troy Cable anticipates connecting to an additional twelve (12) Community Anchor Institutions during the Third Quarter. -Troy Cable is in negotiations on five (5) Interconnection Agreements and plans to add five (5) additional Broadband Wholesale or Last Mile Providers during the Third Quarter. -The Brantley Hub Site will be connected to the DWDM Network by the close of the Third Quarter 2012. | Troy Cablevision, Inc. | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570128 | 2012 | Q3 | Q3 - 2012 | Listed below are the SmartBand Project accomplishments completed during the quarter ending September 30, 2012: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -Approximately 98% of map field work and 92% of the AutoCAD (mapping) work has been completed. The SmartBand Project is approximately 45% complete of the post construction (As-Built) or final mapping. -The Mapping and Permitting Team Members continue to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. -Approximately fifty-six (56) job segments have been engineered and mapped by our Engineering Consultants. -Procurement Team Members have continued receiving signed contracts from Vendors for Request for Proposals awarded during the previous quarters. -Troy Cable has continued to order and receive materials from the awarded Vendors for Construction and Headend Materials for fifty-two (52) of the approximate fifty-six (56) job segments. -Construction has continued with the awarded Contractor for Construction Services. Construction has begun on Phase 2 of the Build Out Plan and covers all six counties as outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Pike, Dale, Crenshaw, Coffee and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. -Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on forty-nine (49) of the fifty-six (56) job segments. The construction crews consist of five (5) Underground crews, four (4) Aerial crews, four (4) Fiber Splicers, and three (3) Construction Inspectors. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. -Last quarter, Troy Cable projected an aggressive goal of 545 fiber miles through the end of the Third Quarter. Troy Cable has completed 566.73 fiber miles of the total 595 mile Project. Troy Cable has also placed 24.21 miles of empty pipe and 4.02 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 88.94 fiber miles were constructed during the Third Quarter. Troy Cable has activated 511.12 fiber miles as of September 30, 2012. - Troy Cable has released and awarded bids on Request for Proposals for Intelligent Policy Management and Firewall. - The Engineering Team continues to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior Quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. -Troy Cable has connected and turned-up fifty-two (52) Community Anchor Institutions through the Third Quarter. Troy Cable has connected and turned-up fifty-eight (58) Businesses through the Third Quarter. -The following existing Hub Sites and colocation facilities were connected to the DWDM Network: Dothan; Atlanta; Dallas; Daleville; Enterprise #1 (South); Enterprise #2 (North); Elba; Troy; Luverne; Ozark; Brundidge; Midland City; and Montgomery. The Brantley Hub Site is currently online but is receiving improvements and will be connected to the DWDM Network by Fourth Quarter 2012. - The Team has brought online a temporary ring to meet colocation requirements in Houston and Montgomery Counties. Colocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed colocation with a Carrier Neutral Hotel in Atlanta & Dallas. Troy Cable is in negotiations on three (3) Interconnection Agreements. -Troy Cable has constructed approximately 28 fiber miles of the Overlap Build. | 567 | 0 | 0 | 0 | 567 | 0 | 0 | 14 | Construction has continued with the awarded Contractor for Construction Services. Construction has begun on Phase 2 of the Build Out Plan and covers all six counties as outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Pike, Dale, Crenshaw, Coffee and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on forty-nine (49) of the fifty-six (56) job segments. The construction crews consist of five (5) Underground crews, four (4) Aerial crews, four (4) Fiber Splicers, and three (3) Construction Inspectors. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. Troy Cable has completed 566.73 fiber miles of the total 595 mile Project. Troy Cable has also placed 24.21 miles of empty pipe and 4.02 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 88.94 fiber miles were constructed during the Third Quarter. | Not Applicable. | Not Applicable. | Not Applicable. | Troy Cable has completed 566.73 fiber miles of the total 595 mile Project. Troy Cable has also placed 24.21 miles of empty pipe and 4.02 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported total, 88.94 fiber miles were constructed during the Third Quarter. | Not Applicable. | Not Applicable. | [REDACTED] | 11 | 3 | 12 | [REDACTED] | [REDACTED] | There will be no Third Party Operators of our Network. | 11 | 0 | 1 | 11 | No variance from Baseline. | No variance from Baseline. | No variance from Baseline. | 10 Mbps = 1 subscribers 20 Mbps = 1 subscriber(s) 100 Mbps = 2 subscriber(s) 450 Mbps = 1 subscriber(s) The other 7 Providers with signed agreements are only currently providing Wholesale Services to the Project. | 52 | 52 | 0 | 52 | SmartBand has connected to fifty-two (52) Community Anchor Institutions and is aggressively working to catch up to Baseline Projections. | SmartBand has connected to fifty-two (52) Community Anchor Institutions and is aggressively working to catch up to Baseline Projections. Fifty-two (52) Community Anchor Institutions are receiving new access. | SmartBand has connected to fifty-two (52) Community Anchor Institutions and is aggressively working to catch up to Baseline Projections. | 1 Mbps to 1 Gbps are available. The Community Anchor Institutions took the following: 1 Mbps = 19 subscribers 5 Mbps = 0 subscribers 10 Mbps = 12 subscribers 15 Mbps = 1 subscribers 20 Mbps = 1 subscribers 45 Mbps = 0 subscribers 50 Mbps = 4 subscribers 100 Mbps = 8 subscribers 7 subscribers are taking no services or video or voice only. | 0 | 0 | 0 | 0 | 0 | Not Applicable. | Not Applicable. | Not Applicable. | Not Applicable. | Not Applicable. | 202 | 58 | 50 | 8 | 58 | SmartBand has passed two hundred two (202) Businesses as a result of the Southeast Alabama SmartBand Project. | SmartBand has connected to fifty-eight (58) Businesses as a result of the Southeast Alabama SmartBand Project. | SmartBand has connected to fifty-eight (58) Businesses as a result of the Southeast Alabama SmartBand Project. Fifty (50) Businesses are receiving new access. | SmartBand has connected to fifty-eight (58) Businesses as a result of the Southeast Alabama SmartBand Project. Eight (8) Businesses are receiving improved access. | 1 Mbps to 1 Gbps are available. The Businesses took the following: 1 Mbps = 8 subscribers 5 Mbps = 0 subscribers 10 Mbps = 26 subscribers 15 Mbps = 4 subscribers 20 Mbps = 3 subscribers 45 Mbps = 1 subscribers 50 Mbps = 5 subscribers 100 Mbps = 0 subscribers 11 subscribers are taking no services or video or voice only. | Not Applicable. | FALSE | Not Applicable. | Listed below are the SmartBand Project accomplishments to be completed during the quarter ending December 31, 2012: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -Procurement Team Members will continue receiving signed contracts from Vendors for Request for Proposals awarded during the previous quarters. -Troy Cable will continue to order and receive materials from the awarded Vendors for Construction and Headend Materials for approximately fifty-six (56) job segments. -Construction will continue on Phase 2 of the Build Out Plan which covers all six counties as outlined in the Southeast Alabama SmartBand Project. Counties where construction is taking place includes: Pike, Dale, Crenshaw, Coffee and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. -Troy Cable has hired additional crews to aide in the construction of the fiber route. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. -Troy Cable projects an aggressive goal of 627 fiber miles constructed through the end of the Fourth Quarter. - The Engineering Team will continue to order & receive materials from the awarded Vendors for additional Equipment & materials for Request for Proposals that were released in prior Quarters. -Troy Cable anticipates connecting to an additional fifteen (15) Community Anchor Institutions during the Fourth Quarter. -Troy Cable is in negotiations on three (3) Interconnection Agreements and plans to add three (3) additional Broadband Wholesale or Last Mile Providers during the Fourth Quarter. -The Brantley Hub Site will be connected to the DWDM Network by the close of the Fourth Quarter 2012. | Troy Cablevision, Inc. | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570128 | 2012 | Q4 | Q4 - 2012 | [REDACTED] | 635 | 0 | 0 | 0 | 635 | 0 | 0 | 14 | Construction has continued with the awarded Contractor for Construction Services on Phase 2 of the Build Out Plan to included forty-nine (49) job segments and covers all counties outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Coffee, Crenshaw, Dale, Pike and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on the forty-nine (49) of the approximate fifty-six (56) job segments. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. The Construction Crew consists of nine Underground crews, three Aerial crews, ten Fiber Splicers, and two Inspectors. Troy Cable has completed 635.96 fiber miles, to include 424.38 route miles of new construction. Troy Cable has also placed 10.95 miles of empty pipe and 3.91 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 635.96 fiber miles, 69.23 fiber miles were constructed during the Fourth Quarter. Troy Cable has activated 382.08 fiber miles as of December 31, 2012. | Not Applicable | Not Applicable | Not Applicable | Troy Cable has completed 635.96 fiber miles, to include 424.38 route miles of new construction. Troy Cable has also placed 10.95 miles of empty pipe and 3.91 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 635.96 fiber miles, 69.23 fiber miles were constructed during the Fourth Quarter. Troy Cable has activated 382.08 fiber miles as of December 31, 2012. | Not Applicable | Not Applicable | [REDACTED] | 8 | 1 | 12 | [REDACTED] | [REDACTED] | There will be no Third Party Operators of our Network. | 8 | 0 | 1 | 8 | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | 51 | 51 | 0 | 51 | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | 0 | 0 | 0 | 0 | 0 | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | 852 | 151 | 117 | 34 | 151 | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | FALSE | Not Applicable | Listed below are the SmartBand Project projected accomplishments during the quarter ending March 31, 2013: -Team Members will continuously work to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -The Mapping and Permitting Team Members will continue requesting the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. -Troy Cable will continue to order & receive materials from the awarded Vendors for Construction and Headend Materials for all job segments. -Construction will continue with the awarded Contractor for Construction Services on Phase 2 of the Build Out Plan which covers all counties outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Coffee, Crenshaw, Dale, Pike and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. -Troy Cable has hired additional crews to aide in the construction of the fiber route. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. The Construction Crew consists of nine Underground crews, three Aerial crews, ten Fiber Splicers, and two Inspectors. -Troy Cable projects an aggressive goal of 45 fiber miles constructed through the end of the First Quarter 2013. -The Team will continue to order & receive materials from the awarded Vendors for Construction & Headend Materials. -The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. -Troy Cable is in negotiations on one (1) Interconnection Agreement and plans to add one (1) additional Broadband Wholesale or Last Mile Provider during the First Quarter 2012. -Troy Cable anticipates connecting to an additional fifty-five (55) Community Anchor Institutions during the First Quarter 2012. | Troy Cablevision, Inc. | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570128 | 2013 | Q1 | Q1 - 2013 | Listed below are the SmartBand Project accomplishments completed during the quarter ending March 31, 2013: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -Approximately 99% of map field work and 96% of the AutoCAD (mapping) work has been completed. -The Mapping and Permitting Team Members continue to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. -Approximately fifty-six (56) job segments have been engineered and mapped by our Engineering Consultants. -Procurement Team Members have continued receiving signed contracts from Vendors for Request for Proposals awarded during previous quarters. -Troy Cable has continued to order & receive materials from the awarded Vendors for Construction and Headend Materials for fifty-six (56) of the approximately fifty-six (56) job segments. -Construction has continued with the awarded Contractor for Construction Services on Phase 2 of the Build Out Plan to included fifty-five (55) job segments and covers all counties outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Coffee, Crenshaw, Dale, Pike and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. -Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on fifty-five (55) of the approximate fifty-six (56) job segments. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. The Construction Crew consists of nine Underground crews, three Aerial crews, eight Fiber Splicers, and two Inspectors. -Troy Cable has completed 700.51 fiber miles, to include 458.85 route miles of new construction. Troy Cable has also placed 9.23 miles of empty pipe and .22 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported miles, 34.47 new route miles were constructed during the First Quarter. Troy Cable has activated 388.95 route miles as of March 31, 2013. -The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. Troy Cable released the following RFP's during the First Quarter: IPTV and OTT Video Distribution System; and Digital Monitoring Test & Measurement System. -The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Troy Cable completed activation of the entire ring during the First Quarter 2013. Collocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. -Troy Cable has connected and turned-up ninety-four (94) Community Anchor Institutions. Troy Cable has connected and turned-up two hundred forty-seven (247) Businesses. | 458 | 0 | 0 | 0 | 458 | 0 | 0 | 14 | Construction has continued with the awarded Contractor for Construction Services on Phase 2 of the Build Out Plan to included fifty-five (55) job segments and covers all counties outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Coffee, Crenshaw, Dale, Pike and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on the fifty-five (55) of the approximate fifty-six (56) job segments. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. The Construction Crew consists of nine Underground crews, three Aerial crews, eight Fiber Splicers, and two Inspectors. Troy Cable has completed 700.51 fiber miles, to include 458.85 route miles of new construction. Troy Cable has also placed 9.23 miles of empty pipe and .22 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 700.51 fiber miles, 34.47 fiber miles were constructed during the First Quarter. Troy Cable has activated 388.95 route miles as of March 31, 2013. | Not Applicable | Not Applicable | Not Applicable | Troy Cable has completed 700.51 fiber miles, to include 458.85 route miles of new construction. Troy Cable has also placed 9.23 miles of empty pipe and .22 miles of bare strand pending the arrival of additional materials needed for completion. Of the reported 700.51 fiber miles, 34.47 fiber miles were constructed during the First Quarter. Troy Cable has activated 388.95 route miles as of March 31, 2013. | Not Applicable | Not Applicable | [REDACTED] | 8 | 2 | 12 | [REDACTED] | [REDACTED] | There will be no Third Party Operators of our Network. | 8 | 0 | 1 | 8 | No variance from Baseline. | No variance from Baseline. | No variance from Baseline. | 10 Mbps = 1 subscribers 20 Mbps = 1 subscriber(s) 100 Mbps = 3 subscriber(s) 900 Mbps = 1 subscriber(s) 10 G = 1 subscriber(s) No other Providers with signed agreements are only currently providing Wholesale Services to the Project. | 94 | 94 | 0 | 94 | Troy Cable has connected ninety-four (94) Community Anchor Institutions and is aggressively working to catch up to the Baseline Projections. | Troy Cable has connected ninety-four (94) Community Anchor Institutions and is aggressively working to catch up to the Baseline Projections. Ninety-four (94) Community Anchor Institutions are receiving new access. | Troy Cable has connected ninety-four (94) Community Anchor Institutions and is aggressively working to catch up to the Baseline Projections. | 1 Mbps to 1 Gbps are available. The Community Anchor Institutions took the following: 1 Mbps = 26 subscribers 5 Mbps = 0 subscribers 10 Mbps = 5 subscribers 15 Mbps = 3 subscribers 20 Mbps = 11 subscribers 45 Mbps = 0 subscribers 50 Mbps = 4 subscribers 100 Mbps = 8 subscribers 37 subscribers are taking no services or video or voice only. | 0 | 0 | 0 | 0 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1266 | 247 | 200 | 47 | 247 | SmartBand has passed one thousand two hundred sixty-six (1,266) Businesses as a result of the Southeast Alabama SmartBand Project. | Troy Cable has connected two hundred forty-seven (247) Businesses as a result of the Southeast Alabama SmartBand Project. | Troy Cable has connected two hundred forty-seven (247) Businesses as a result of the Southeast Alabama SmartBand Project. Two hundred (200) Businesses are receiving new access. | Troy Cable has connected two hundred forty-seven (247) Businesses as a result of the Southeast Alabama SmartBand Project. Forty-seven (47) Businesses are receiving improved access. | 1 Mbps to 1 Gbps are available. The Businesses took the following: 1 Mbps = 34 subscribers 5 Mbps = 0 subscribers 10 Mbps = 86 subscribers 15 Mbps = 26 subscribers 20 Mbps = 38 subscribers 45 Mbps = 1 subscribers 50 Mbps = 10 subscribers 100 Mbps = 16 subscribers 160 Mbps = 1 subscribers 35 subscribers are taking no services or video or voice only. | Not Applicable | FALSE | Not Applicable | Listed below are the SmartBand Project accomplishments completed during the quarter ending June 30, 2013: -Team Members will continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -Approximately 100% of map field work and 99% of the AutoCAD (mapping) work has been completed. -The Mapping and Permitting Team Members will continuously work to request the necessary permits and submit required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. -Approximately fifty-six (56) job segments have been engineered and mapped by our Engineering Consultants. -Procurement Team Members have continued receiving signed contracts from Vendors for Request for Proposals awarded during previous quarters. -Troy Cable will continue to order & receive materials from the awarded Vendors for Construction and Headend Materials for the approximately fifty-six (56) job segments. -Construction will continue with the awarded Contractor for Construction Services on Phase 2 of the Build Out Plan to included fifty-six (56) job segments and covers all counties outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Coffee, Crenshaw, Dale, Pike and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. -Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on approximately fifty-six (56) job segments. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. The Construction Crew consists of nine Underground crews, three Aerial crews, eight Fiber Splicers, and two Inspectors. -Troy Cable projects a goal of 17 route miles constructed through the end of the Second Quarter 2013. -The Engineering Team will continue to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. -The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Troy Cable completed activation of the entire ring during the First Quarter 2013. Collocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. -Troy Cable has connected and turned-up ninety-four (94) Community Anchor Institutions. Troy Cable has connected and turned-up two hundred forty-seven (247) Businesses. Troy Cable anticipates connecting to an additional forty-one (41) CAI's. | Troy Cablevision, Inc. | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570128 | 2013 | Q2 | Q2 - 2013 | Listed below are the SmartBand Project accomplishments completed during the quarter ending June 30, 2013: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -Approximately 99% of map field work and 96% of the AutoCAD (mapping) work has been completed. -The Mapping and Permitting Team Members continue to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. -Approximately fifty-eight (58) job segments have been engineered and mapped by our Engineering Consultants. -Procurement Team Members have continued receiving signed contracts from Vendors for Request for Proposals awarded during previous quarters. -Construction has continued with the awarded Contractor for Construction Services on Phase 2 of the Build Out Plan to included fifty-eight (58) job segments and covers all counties outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Coffee, Crenshaw, Dale, Pike and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. -Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on fifty-six (56) of the approximate fifty-eight (58) job segments. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. The Construction Crew consists of seven Underground crews, two Aerial crews, eight Fiber Splicers, and two Inspectors. -Troy Cable has completed 474.02 route miles of new construction. Troy Cable has activated 474.02 route miles as of June 30, 2013. -The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. -The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. -Troy Cable has connected and turned-up one hundred thirty-nine (139) Community Anchor Institutions. Troy Cable has connected and turned-up three hundred fifty-seven (357) Businesses. | 474 | 0 | 0 | 0 | 474 | 0 | 0 | 14 | Construction has continued with the awarded Contractor for Construction Services on Phase 2 of the Build Out Plan to included fifty-eight (58) job segments and covers all counties outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Coffee, Crenshaw, Dale, Pike and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on the fifty-six (56) of the approximate fifty-eight (58) job segments. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. The Construction Crew consists of seven Underground crews, two Aerial crews, eight Fiber Splicers, and two Inspectors. Troy Cable has completed 474.02 route miles of new construction. Troy Cable has activated 474.02 route miles as of June 30, 2013. | Not Applicable | Not Applicable | Not Applicable | Troy Cable has completed 474.02 route miles of new construction. Troy Cable has activated 474.02 route miles as of June 30, 2013. | Not Applicable | Not Applicable | [REDACTED] | 8 | 3 | 12 | [REDACTED] | [REDACTED] | There will be no Third Party Operators of our Network. | 8 | 0 | 1 | 8 | No variance from Baseline. | No variance from Baseline. | No variance from Baseline. Trillion Communications | 10 Mbps = 2 subscribers 20 Mbps = 1 subscriber(s) 100 Mbps = 3 subscriber(s) 900 Mbps = 1 subscriber(s) 10 G = 1 subscriber(s) No other Providers with signed agreements are only currently providing Wholesale Services to the Project. | 139 | 139 | 0 | 139 | Troy Cable has connected one hundred thirty-nine (139)Community Anchor Institutions and is aggressively working to catch up to the Baseline Projections. | Troy Cable has connected one hundred thirty-nine (139) Community Anchor Institutions and is aggressively working to catch up to the Baseline Projections. One hundred thirty-nine (139) Community Anchor Institutions are receiving new access. | Troy Cable has connected one hundred thirty-nine (139) Community Anchor Institutions and is aggressively working to catch up to the Baseline Projections. | 1 Mbps to 1 Gbps are available. The Community Anchor Institutions took the following: 1 Mbps = 26 subscribers 5 Mbps = 0 subscribers 10 Mbps = 17 subscribers 15 Mbps = 3 subscribers 20 Mbps = 11 subscribers 45 Mbps = 0 subscribers 50 Mbps = 4 subscribers 100 Mbps = 8 subscribers 70 subscribers are taking no services or video or voice only. | 0 | 0 | 0 | 0 | 0 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1447 | 357 | 252 | 105 | 357 | SmartBand has passed one thousand four hundred forty-seven(1,447) Businesses as a result of the Southeast Alabama SmartBand Project. | Troy Cable has connected three hundred fifty-seven (357) Businesses as a result of the Southeast Alabama SmartBand Project. | Troy Cable has connected three hundred fifty-seven (357) Businesses as a result of the Southeast Alabama SmartBand Project. Two hundred fifty-two (252) Businesses are receiving new access. | Troy Cable has connected two hundred forty-seven (247) Businesses as a result of the Southeast Alabama SmartBand Project. One hundred five (105) Businesses are receiving improved access. | 1 Mbps to 1 Gbps are available. The Businesses took the following: 1 Mbps = 44 subscribers 5 Mbps = 16 subscribers 10 Mbps = 130 subscribers 15 Mbps = 34 subscribers 20 Mbps = 42 subscribers 45 Mbps = 1 subscribers 50 Mbps = 10 subscribers 100 Mbps = 20 subscribers 160 Mbps = 1 subscribers 59 subscribers are taking no services or video or voice only. | Not Applicable | FALSE | Not Applicable | Listed below are the SmartBand Project accomplishments completed during the quarter ending September 30, 2013: -Team Members will continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -Approximately 100% of map field work and 99% of the AutoCAD (mapping) work has been completed. -The Mapping and Permitting Team Members will continuously work to request the necessary permits and submit required permitting documentation to pole owners for areas included in Phase 2 of the Build Out Plan. -Approximately fifty-eight (58) job segments have been engineered and mapped by our Engineering Consultants. -Procurement Team Members have continued receiving signed contracts from Vendors for Request for Proposals awarded during previous quarters. -Troy Cable will continue to order & receive materials from the awarded Vendors for Construction and Headend Materials for the approximately fifty-eight (58) job segments. -Construction will continue with the awarded Contractor for Construction Services on Phase 2 of the Build Out Plan to included fifty-eight (58) job segments and covers all counties outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Coffee, Crenshaw, Dale, Pike and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. -Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on approximately fifty-six (56) of the fifty-eight (58) job segments. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Fiber Miles Constructed. The Construction Crew consists of seven Underground crews, two Aerial crews, eight Fiber Splicers, and two Inspectors. -Troy Cable projects a goal of 1.50 route miles constructed through the end of the Third Quarter 2013. -The Engineering Team will continue to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. -The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. -Troy Cable has connected and turned-up one hundred thirty-nine (139) Community Anchor Institutions. Troy Cable has connected and turned-up three hundred fifty-seven (357) Businesses. Troy Cable anticipates connecting to an additional eight (8) CAI's. | Troy Cablevision, Inc. | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570128 | 2013 | Q3 | Q3 - 2013 | Listed below are the SmartBand Project accomplishments completed during the quarter ending September 30, 2013: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. -Approximately 97% of map field work and 95% of the AutoCAD (mapping) work has been completed. -The Mapping and Permitting Team Members continue to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 3 of the Build Out Plan. -Approximately eighty (80) job segments have been engineered and mapped by our Engineering Consultants. -Procurement Team Members have continued receiving signed contracts from Vendors for Request for Proposals awarded during previous quarters. -Construction has continued with the awarded Contractor for Construction Services on Phase 3 of the Build Out Plan to included approximately eighty (80) job segments and covers all counties outlined in the Southeast Alabama SmartBand Project. Counties where construction has continued include: Coffee, Crenshaw, Dale, Pike and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. -Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on approximately eighty (80) job segments. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Route Miles Constructed. The Construction Crew consists of six Underground crews, two Aerial crews, eight Fiber Splicers, and two Inspectors. -Troy Cable has completed 501.00 route miles of new construction. Troy Cable has activated 501.00 route miles as of September 30, 2013. -The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. -The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. -Troy Cable has connected and turned-up one hundred forty-six (146) Community Anchor Institutions. Troy Cable has connected and turned-up four hundred (400) Businesses. | 501 | 0 | 0 | 0 | 501 | 0 | 0 | 14 | Construction has continued with the awarded Contractor for Construction Services on Phase 3 of the Build Out Plan to included eighty (80) job segments and covers all counties outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Coffee, Crenshaw, Dale, Pike and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on approximately eighty (80) job segments. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Route Miles Constructed. The Construction Crew consists of six Underground crews, two Aerial crews, eight Fiber Splicers, and two Inspectors. Troy Cable has completed 501.00 route miles of new construction. Troy Cable has activated 501.00 route miles as of September 30, 2013. | Not Applicable. | Not Applicable. | Not Applicable. | Troy Cable has completed 501.00 route miles of new construction. Troy Cable has activated 501.00 route miles as of September 30, 2013. | Not Applicable. | Not Applicable. | [REDACTED] | 9 | 3 | 12 | [REDACTED] | [REDACTED] | There will be no Third Party Operators of our Network. | 8 | 0 | 1 | 11 | No variance from the Baseline. | No variance from the Baseline. | No variance from the Baseline. Trillion Communications. | 10 Mbps = 2 subscriber(s) 20 Mbps = 1 subscriber(s) 100 Mbps = 3 subscriber(s) 900 Mbps = 1 subscriber(s) 2.5G = 2 subscriber(s) 10G = 2 subscriber(s) No other Providers with signed agreements, are only currently providing Wholesale Services to the Project. Troy Cable is providing multi-tier service for some providers. This service type causes the value difference between this section and the number reported under the section above names "Broadband Wholesalers or Last Mile Providers" - "Providers with signed agreements receiving new access". Troy Cable currently has nine (9) signed agreements with eleven (11) various subscriber tiers. | 146 | 146 | 0 | 146 | Troy Cable has connected one hundred forty-six (146)Community Anchor Institutions and is aggressively working to catch up to the Baseline Projections. | Troy Cable has connected one hundred forty-six (146) Community Anchor Institutions and is aggressively working to catch up to the Baseline Projections. One hundred forty-six (146) Community Anchor Institutions are receiving new access. | Troy Cable has connected one hundred forty-six (146) Community Anchor Institutions and is aggressively working to catch up to the Baseline Projections. | 1 Mbps to 1 Gbps are available. The Community Anchor Institutions took the following: 1 Mbps = 26 subscribers 5 Mbps = 0 subscribers 10 Mbps = 17 subscribers 15 Mbps = 7 subscribers 20 Mbps = 13 subscribers 45 Mbps = 0 subscribers 50 Mbps = 4 subscribers 100 Mbps = 8 subscribers 71 subscribers are taking no services or video or voice only. | 0 | 0 | 0 | 0 | 0 | Not applicable. | Not applicable. | Not applicable. | Not applicable. | Not applicable. | 1551 | 400 | 278 | 122 | 400 | SmartBand has passed one thousand five hundred fifty-one(1,551) Businesses as a result of the Southeast Alabama SmartBand Project. | Troy Cable has connected four hundred (400) Businesses as a result of the Southeast Alabama SmartBand Project. | Troy Cable has connected four hundred (400) Businesses as a result of the Southeast Alabama SmartBand Project. Two hundred seventy-eight (278) Businesses are receiving new access. | Troy Cable has connected four hundred (400) Businesses as a result of the Southeast Alabama SmartBand Project. One hundred twenty-two (122) Businesses are receiving improved access. | 1 Mbps to 1 Gbps are available. The Businesses took the following: 1 Mbps = 44 subscribers 5 Mbps = 16 subscribers 10 Mbps = 153 subscribers 15 Mbps = 39 subscribers 20 Mbps = 42 subscribers 45 Mbps = 1 subscribers 50 Mbps = 10 subscribers 100 Mbps = 20 subscribers 160 Mbps = 1 subscribers 74 subscribers are taking no services or video or voice only. | Not applicable. | FALSE | Not applicable. | Listed below are the SmartBand Project accomplishments completed during the quarter ending December 30, 2013: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 55.79 route miles. -Approximately 100% of map field work and 100% of the AutoCAD (mapping) work has been completed. -The Mapping and Permitting Team Members continue to request the necessary permits and have submitted required permitting documentation to pole owners for areas included in Phase 3 of the Build Out Plan. -Approximately eighty (80) job segments have been engineered and mapped by our Engineering Consultants. -Procurement Team Members have continued receiving signed contracts from Vendors for Request for Proposals awarded during previous quarters. -Construction has continued with the awarded Contractor for Construction Services on Phase 3 of the Build Out Plan to included approximately eighty (80) job segments and covers all counties outlined in the Southeast Alabama SmartBand Project. Counties where construction has continued include: Coffee, Crenshaw, Dale, Pike and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. -Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on approximately eighty (80) job segments. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Route Miles Constructed. The Construction Crew consists of six Underground crews, two Aerial crews, eight Fiber Splicers, and two Inspectors. -Troy Cable will complete all construction related activities with approximately 30.31 route miles constructed during Third Quarter 2013. -The Engineering Team is continuing to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable will have all network equipment deployed. -The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. -Troy Cable connected and turned-up one hundred forty-six (146) Community Anchor Institutions. Troy Cable has connected and turned-up four hundred (400) Businesses. Troy Cable anticipates connecting to an additional fifty-two (52) CAI's. | Troy Cablevision, Inc. | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570128 | 2013 | Q4 | Q4 - 2013 | Listed below are the SmartBand Project accomplishments completed during the quarter ending December 31, 2013: -Team Members are continuously working to monitor progress of the total Project by tracking budget to actual to measure financial milestones. -Troy Cable applied and received a No-cost Extension to the Grant. The SmartBand Team also submitted and received a Route Modification to the existing Project with the addition of approximately 54.17 route miles. -All map field work and AutoCAD (mapping) work has been completed. -The Mapping and Permitting Team Members continued to request the necessary permits for areas included in Phase 3 of the Build Out Plan. Troy Cable is still awaiting Railroad Permitting for a .57 mile stretch along a route included in the Route Modification to be completed with non-federal funds due to the ending funds of availability. -Approximately eighty (80) job segments have been engineered and mapped by our Engineering Consultants. -Construction continued with the awarded Contractor for Construction Services on Phase 3 of the Build Out Plan to included approximately seventy-five (75) job segments and covers all counties outlined in the Southeast Alabama SmartBand Project. Counties where construction has continued include: Coffee, Crenshaw, Dale, Pike and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. -Troy Cable has hired additional crews to aide in the construction of the fiber route which included the construction on approximately eighty (80) job segments. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Route Miles Constructed. The Construction Crew consists of two Underground crews, two Aerial crews, nine Fiber Splicers, and two Inspectors. -Troy Cable has completed 529.12 route miles of new construction. Troy Cable has activated 529.12 route miles as of December 31, 2013. -The Engineering Team has continued to order & receive materials from the awarded Vendors for additional equipment & materials for Request for Proposals that were released in prior quarters. Troy Cable has deployed the following Network Equipment: DWDM Network; Routers; Switches; and Access Gear. -The Team has brought on-line a ring to meet collocation requirements in Houston and Montgomery Counties. Collocation equipment has been installed in both Houston and Montgomery Counties. Troy Cable has completed collocation with a Carrier Neutral Hotel in Atlanta & Dallas. -Troy Cable has connected and turned-up one hundred ninety-eight (198) Community Anchor Institutions. Troy Cable has connected and turned-up four hundred eighty-one (481) Businesses. | 529 | 0 | 0 | 0 | 529 | 0 | 0 | 14 | Construction has continued with the awarded Contractor for Construction Services on Phase 3 of the Build Out Plan to included seventy-five (75) job segments and covers all counties outlined in the Southeast Alabama SmartBand Project. Counties where construction has begun include: Coffee, Crenshaw, Dale, Pike and key internet points of presence or "on-ramps" to global Internet in Montgomery and Houston Counties. Troy Cable has hired additional crews to aide in the construction of the fiber route which includes the construction on approximately eighty (80) job segments. The addition of the construction related personnel reflects the progress Troy Cable is making to meet or exceed the requirements outlined in the Baseline Budget for Route Miles Constructed. The Construction Crew consists of six Underground crews, two Aerial crews, eight Fiber Splicers, and two Inspectors. Troy Cable has completed 529.12 route miles of new construction. Troy Cable has activated 529.12 route miles as of December 31, 2013. | Not Applicable. | Not Applicable. | Not Applicable. | Troy Cable has completed 529.12 route miles of new construction. Troy Cable has activated 529.12 route miles as of December 31, 2013. | Not Applicable. | Not Applicable. | [REDACTED] | 12 | 1 | 12 | [REDACTED] | [REDACTED] | There will be no Third Party Operators of our Network. | 11 | 0 | 1 | 13 | No variance from the Baseline. | No variance from Baseline. | No variance from Baseline. Trillion Communications. | 10 Mbps = 2 subscriber(s) 20 Mbps = 1 subscriber(s) 100 Mbps = 4 subscriber(s) 900 Mbps = 1 subscriber(s) 2.5G = 2 subscriber(s) 3G = 1 subscriber(s) 10G = 2 subscriber(s) No other Providers with signed agreements, are only currently providing Wholesale Services to the Project. Troy Cable is providing multi-tier service for some providers. This service type causes the value difference between this section and the number reported under the section above names "Broadband Wholesalers or Last Mile Providers" - "Providers with signed agreements receiving new access". Troy Cable currently has twelve (12) signed agreements with thirteen (13) various subscriber tiers. | 198 | 198 | 0 | 198 | Troy Cable has connected one hundred ninety-eight (198)Community Anchor Institutions. | Troy Cable has connected one hundred ninety-eight (198) Community Anchor Institutions. One hundred ninety-eight (198) Community Anchor Institutions are receiving new access. | Not Applicable. | 1 Mbps to 10 Gbps are available. The Community Anchor Institutions took the following: 1 Mbps = 26 subscribers 4 Mbps = 1 subscribers 10 Mbps = 18 subscribers 15 Mbps = 23 subscribers 20 Mbps = 13 subscribers 45 Mbps = 0 subscribers 50 Mbps = 4 subscribers 100 Mbps = 8 subscribers 105 subscribers are taking no services or video or voice only. | 0 | 0 | 0 | 0 | 0 | Not Applicable. | Not Applicable. | Not Applicable. | Not Applicable. | Not Applicable. | 1653 | 481 | 358 | 123 | 481 | SmartBand has passed one thousand six hundred fifty-three(1,653) Businesses as a result of the Southeast Alabama SmartBand Project. | Troy Cable has connected four hundred eighty-one (481) Businesses as a result of the Southeast Alabama SmartBand Project. | Troy Cable has connected four hundred eighty-one (481) Businesses as a result of the Southeast Alabama SmartBand Project. Three hundred fifty-eight (358) Businesses are receiving new access. | Troy Cable has connected four hundred eighty-one (481) Businesses as a result of the Southeast Alabama SmartBand Project. One hundred twenty-three (123) Businesses are receiving improved access. | 1 Mbps to 10 Gbps are available. The Businesses took the following: 1 Mbps = 44 subscribers 4 Mbps = 1 subscribers 5 Mbps = 16 subscribers 10 Mbps = 191 subscribers 15 Mbps = 42 subscribers 20 Mbps = 61 subscribers 35 Mbps = 1 subscribers 45 Mbps = 1 subscribers 50 Mbps = 10 subscribers 100 Mbps = 20 subscribers 160 Mbps = 1 subscribers 1 Gbps = 1 subscribers 92 subscribers are taking no services or video or voice only. | Not Applicable. | FALSE | Not Applicable | Listed below are the SmartBand Project accomplishments completed during the quarter ending March 31, 2013: -Troy Cable will work to complete all closeout activities. | Troy Cablevision, Inc. | [REDACTED] | [REDACTED] | TRUE
NT10BIX5570129 | 2010 | Q4 | Q4 - 2010 | During this quarter, the recipient attended the November 8-10, BTOP workshop. The environmental assessment process was continued. Engaged professional services to facilitate compliance with regulatory requirements, compile required documentation and analysis, submit draft environmental assessment by January 31, 2011 and apply NTIA comments and submit Final Environmental Assessment as required with all services complying with requirements set forth in the Environmental Assessment Guidance for BTOP Award Recipients. Contract for project management/route engineering, was awarded and signed. Efforts were started to update business and financial planning, and to start detailed network design and engineering. This included GIS mapping of community anchor tenants, fiber layout for middle mile and DSL expansion, design of network, pole survey work, engineering drawings and initiation of permitting application, including correspondence with VDOT. A Request for Proposals was issued for design build of the co-location data center. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | In Q3 (January 1 through March 31) , the draft Environmental Assessment will be submitted by January 31. Proposals for design build of the data center will be received, evaluated, and a contract will be awarded by mid-February. Route engineering and permitting will continue. Equipment procurement will begin with request for proposal for cabinets issued in March. Network Architecture will be completed. | Rockbridge, County of | N/A | N/A | TRUE
NT10BIX5570129 | 2011 | Q1 | Q1 - 2011 | The project activities have focused heavily on project management, route engineering, and environmental assessment work. Project management accomplishments have included route and network design, compliance and reporting documentation, Public and Rockbridge Area Network Authority (RANA) board meetings and work sessions, preliminary route assessment, comprehensive mapping, development of interested vendor list, in-progress drafting of legal agreements for cabinet site lease, service provider agreements, and Memorandum of understanding (MOU) between Washington and Lee University and Virginia Global Communication Systems. Design-Build proposals for the data collocation center were received. Upon further review, RANA decided to re-bid the work, following the design-bid-build process. The RANA project website was developed. Engineering has begun survey work on routes, including evaluating alternative routes, aerial conditions, and bridge/stream crossings. The draft environmental assessment was submitted. The environmental assessment has been returned with comment matrix and efforts were made to address those comments and continued work on compliance issues with State Historic Preservation Office, U.S.Fish and Wildlife Service, and Virginia Department of Historic Resources. During this quarter, several routes were modified and an official route modification request was submitted to National Telecommunications and Information Administration for review. The main reroute will bring f | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | For project Q4 (April 1 through June 30), the revised environmental assessment will be submitted for final review. Proposals for the rebid Design-Bid-Build data center will be received and evaluated. The engineering firm will create initial bill of material. Pending FONSI issuance for the Environmental Assessment, construction of cabinet pads and cabinet procurement may begin. | Rockbridge, County of | N/A | N/A | TRUE
NT10BIX5570129 | 2011 | Q2 | Q2 - 2011 | Project has not entered the construction period; therefore, the project activities have focused heavily on project management, route engineering, and environmental assessment work. Project management duties have included route and network design, compliance and reporting documentation, Rockbridge Area Network Authority (RANA) board meetings, development of an Operations guide, and the continued development of an interested vendor list. A GIS-based fiber-management tracking tool was built and became operational. A Request for Proposals (RFP) for the data center design/bid was issued and a contract awarded to Hoch Associates. Hoch held a program design session with project stakeholders and began design work of the site plan and building layout. Site surveying on the data center was completed. Survey work on fiber routes, including evaluating alternative routes, aerial pole conditions, and bridge/stream crossings has been completed. Route engineering continues. The environmental assessment (EA) work has continued in preparation for final submittal. An archaeological firm has reviewed the project as part of the EA requirements. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | N/A | N/A | N/A | No variance | N/A | N/A | No variance | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | No variance | No variance | N/A | N/A | 0 | 0 | 0 | 0 | No variance | No variance | No variance | N/A | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | N/A | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | N/A | N/A | FALSE | N/A | For the next quarter, 2011 Q3 (July 1 through September 30), the environmental assessment will be submitted. The design center site plan and schematic design will be finalized. Work on bid documents will begin and required permits will be submitted. Route engineering will be complete. In order to mitigate large fiber equipment lead times, a portion of fiber equipment will be ordered. Work on DSL sites will begin. | Rockbridge, County of | N/A | N/A | TRUE
NT10BIX5570129 | 2011 | Q3 | Q3 - 2011 | Most of the project activities have continued to focus heavily on project management, route engineering, and environmental assessment work. Project management duties have included route and network design, compliance and reporting documentation, Rockbridge Area Network Authority (RANA) board meetings, development of an Operations guide, and the continued development of an interested vendor list. A Memoranda of Understanding (MOU) between Washington and Lee University and Rockbridge County was signed. Geo-technical work on the Data Center has begun. Survey work on fiber routes, including evaluating alternative routes, aerial pole conditions, and bridge/stream crossings has been completed. Route engineering has also been completed. The environmental assessment (EA) has been submitted and approved. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | N/A | N/A | N/A | No variance | N/A | N/A | No variance | 0 | 0 | 0 | In 2011 Q3 we met with VGCS and MGW, two local service providers, who indicated keen interest in offering services on the network. We also prepared an information handout for Service Providers, and developed a draft service provider contract. We had discussions with Zayo, a major national wholesaler of Internet access, and Zayo has been provided with more information on the network. In our experience on past projects, service providers will rarely make a written commitment or sign a formal contract until a construction contract for the network has been signed. Accordingly, we plan to aggressively begin marketing the network to service providers in 2012, Q1. Based on the high levels of interest that have been expressed so far, we anticipate no difficulty having providers offering services on Day one of network operations. We further note that VGCS is a formal partner in the project, and they have consistently indicated they intend to be a Day One provider. | N/A | N/A | 0 | 0 | 0 | 0 | No variance | No variance | N/A | N/A | 0 | 0 | 0 | 0 | No variance | No variance | No variance | N/A | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | N/A | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | N/A | N/A | FALSE | N/A | For the next quarter, 2011 Q4 (October 1 through December 31), a portion of the fiber equipment will be ordered. Fiber bids will be received and fiber work will be close to starting. DSL cabinet and equipment ordering will begin as well as the contractor selection process will be started. Data Center construction will begin. There will be 0 new network miles deployed, 0 new network miles leased, 0 total CAI subscribers served, and 0 signed agreements with broadband wholesalers or last mile providers in 2011 Q4. 2011 Q4 completed milestones will include a signed contract for Data Center construction and the start of Data Center construction, issuance of the fiber construction RFP, issuance of the fiber and duct purchase orders, issuance of the RFP for DSL cabinet site construction, issuance of purchase orders for all of the DSL and fiber cabinets, and issuance of purchase orders for all DSL-related equipment purchases (DSLAMS, UPSes, batteries, patch panels, and misc. hardware). The contract for the fiber and DSL cabinet site construction should also be signed. | Rockbridge, County of | One of the challenges that we have overcome is the submission and approval of our Environmental Assessment, which did create a delay which is now past. This has delayed the gathering of needed construction permits and contractor selections. The length of the EA approval process also delayed the Rights of Way gathering because the final route had not been approved in the Environmental Assessment to get the necessary Rights of Way, thus the Environmental Assessment delay delayed any site prep from beginning. Collecting those Rights of Way is now underway. | Data Center bids have been received and there are some minor changes that need to be made to the specifications to keep that portion of the project in budget. Adjustments will NOT affect the size of the facility nor will it affect RANAâ€™s ability to market the facility; no essential systems will have be eliminated. Changes under review will not affect the scheduled completion in 2012 Q2. The contract for construction should be signed in December 2011. We have identified the necessary easements for the Cabinet the fiber construction. Because of the number of easements required, we have hired a person that is performing the title searches required to verify the easements that are needed. While the easement research is going on, the county and the RANA board are holding meetings to gather easement signatures. For landowners that do not attend a group meeting or agree to sign at a group meeting, we will go and talk to them one-on-one to get an easement signed. The majority of the fiber routes do not need easements, so any delays that come in gathering the easements will NOT delay fiber construction. We are also going through the final review of the fiber construction RFP, a legal review of it by the County Attorney is also underway. We will get final approval from the Board of Supervisors and have the fiber construction RFP advertised by the first week of December. The RFQ (Request For Quotation) for the purchase of fiber and conduit is also under final review as well as lega | TRUE
NT10BIX5570129 | 2011 | Q4 | Q4 - 2011 | Most of the project activities have continued to focus heavily on project management, geo-technical work on the Data Center, contract negotiations for the construction of the Data Center, and the writing of Invitation for Bids on the Fiber and DSL Network construction work. Project management duties have included route and network design, compliance and reporting documentation, Rockbridge Area Network Authority (RANA) board meetings, continued development of an Operations guide, and the continued development of an interested provider list. A Memoranda of Understanding (MOU) between Virginia Global Communications Systems and Rockbridge County was signed. Rockbridge County has received the needed permits for Railroad crossings and Stream crossings. The Data Center construction company has been selected and a contract has been signed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be 8 new network miles deployed by the end of Q4, 2011. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. | N/A | N/A | N/A | The Baseline plan indicated that there would be 8 miles of fiber deployed by the end of Q4, 2011. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. | N/A | N/A | The Baseline plan indicated that there would be 2 new interconnection points deployed by the end of Q4, 2011. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. | 0 | 0 | 0 | In 2011 Q3 we met with VGCS and MGW, two local service providers, who indicated keen interest in offering services on the network. We also prepared an informational handout for Service Providers, and developed a draft service provider contract which is currently undergoing legal review. We had discussions with Zayo, a major national wholesaler of Internet access, and Zayo has been provided with more information on the network. In our experience on past projects, service providers will rarely make a written commitment to sign a formal contract until a construction contract for the network has been signed. We expect the construction contract for the network to be signed during 2012, Q1. Accordingly, we plan to aggressively begin marketing the network to service providers in 2012, Q1. Based on high levels of interest that have been expressed so far, we anticipate no difficulty having providers offering services on Day One of network operations. We further note that VGCS is a formal partner in the project, and they have consistently indicated they intend to be a Day One provider. The Baseline plan indicated that we would have 2 signed agreements with 10 more agreements being negotiated. The negative variance is due to the delay in the submission and approval of the environmental assessment and the delay in legal review of the fiber network construction bid documents. Most providers do not want to sign agreements until the network is under construction. | N/A | N/A | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be 2 signed agreements by the end of Q4, 2011. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. We expect to begin getting signed agreements during Q1, 2012. | No variance | N/A | N/A | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be 18 total CAI's served by the end of Q4, 2011. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. We expect to begin serving CAI's in Lexington during Q3, 2012. | The Baseline plan indicated that there would be 18 CAI's served by the end of Q4, 2011. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. We expect to begin serving CAI's in Lexington during Q3, 2012. | No variance | N/A | 0 | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be 160 residents/households passed by the end of Q4, 2011. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. | The Baseline plan indicated that we would be serving 56 residents/households by the end of Q4, 2011. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. | No variance | No variance | N/A | 0 | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be 30 businesses passed by the end of Q4, 2011. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. | The Baseline plan indicated that we would be serving 12 businesses by the end of Q4, 2011. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. | No variance | No variance | N/A | N/A | FALSE | N/A | For the next quarter, 2012 Q1 (January 1 through March 31), a portion of the fiber and conduit will be ordered. Fiber construction and cabinet construction bids will be received and a contractor will be selected. We are expecting to receive a portion of the conduit and to have a signed contract with both the fiber network construction contractor and the cabinet construction contractor. The cabinet procurement bids will also be received during the next quarter and we are expecting to place an order for the cabinets and have them on hand for when the cabinet construction starts in late 2012 Q1 or early 2012 Q2. There will be 0 new network miles deployed, 0 new network miles leased, 0 total CAI subscribers served, and 1 signed agreement with broadband wholesalers or last mile providers in 2012 Q1. 2012 Q1 completed milestones will include the start of the Data Center construction, selection of a fiber network construction contractor, selection of a cabinet construction contractor, issuance of the fiber and conduit purchase orders, and issuance of the DSL and fiber cabinet purchase orders. We anticipate the project will be 67% complete during Q4, 2012 and 100% complete during Q2, 2013. | Rockbridge, County of | The contract negotiations for the data center construction held up the data center contract being signed and delayed the start of construction. Construction was scheduled to begin during this quarter but with the delay due to the contract it is now scheduled to begin early next quarter. This will not affect the scheduled completion in 2012 Q2. The data center construction contract has now been signed. We have identified the necessary easements for the cabinet and fiber network construction and are actively pursuing getting those easements from the land owners. 70% of the fiber routes do not need easements, so any delays that come in gathering the easements will NOT delay the start of the fiber network construction. The fiber network and cabinet construction bids were published during this quarter and we expect to make the awards during 2012 Q1. | The Data Center construction contract has been signed. Data Center construction is scheduled to begin during 2012 Q1 and is scheduled for completion in 2012 Q2. The necessary easements for the cabinet and fiber network construction projects have been identified. We are actively pursuing getting those signed. The County is planning to go and talk to landowners one-on-one to get the easements signed. 70% of the fiber routes do not need easements, so any delays that come in gathering the easements will NOT delay the start of the fiber network construction. The responses to the cabinet procurement, fiber procurement, conduit procurement, fiber network construction, and cabinet construction are due back during January and we are anticipating making an award on all five during 2012 Q1. We are expecting to issue purchase orders for the cabinets, and portions of the fiber and conduit this quarter. We are also anticipating to have signed contracts for both the fiber network construction and the cabinet construction with work beginning late 2012 Q1 or early 2012 Q2. | TRUE
NT10BIX5570129 | 2012 | Q1 | Q1 - 2012 | Most of the projects activities have focused heavily on project management, Data Center construction, evaluation of the Invitation for Bids on the Fiber Network and Cabinet construction work. The three procurement bids that were out, Fiber, Conduit, and Cabinets, were awarded and the Cabinets have been delivered as well as approximately 20% of the Conduit. Project management duties have included network design, compliance and reporting documentation as well as being on site for the BTOP site visit, Rockbridge Area Network Authority (RANA) board meetings, continued development of an operations guide, and the continued development of an interested vendor list. The ground breaking ceremony for the Data Center was February 6, 2012, construction is now underway. Contracts for the Fiber Network and Cabinet construction are being prepared and reviewed by the County Attorney to be sent to the contractors to be signed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be 20 new network miles deployed by the end of 2012 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that has delayed the start of construction. We are anticipating to have the construction contract signed during 2012 Q2 and for construction to begin. | N/A | N/A | N/A | The Baseline plan indicated that there would be 20 new network miles deployed by the end of 2012 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that has delayed the start of construction. We are anticipating to have the construction contract signed during 2012 Q2 and for construction to begin. | N/A | N/A | The Baseline plan indicated that there would be 2 new interconnection points deployed by the end of 2012 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that has delayed the start of construction. We are anticipating to have the construction contract signed during 2012 Q2 and for construction to begint there would be 2 new interconnection points deployed by the end of 2012 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that has delayed the start of construction. We are anticipating to have the construction contract signed during 2012 Q2 and for construction to begin. | 0 | 2 | 0 | In 2011 Q3 and Q4 we met with Virginia Global Communication Systems (VGCS) and MGW Communications, two local service providers, who indicated keen interest in offering services on the network. We also prepared an informational handout for service providers and developed a draft service provider contract, which is currently undergoing legal review. We have had discussions with Zayo, a major national wholesaler of Internet access, and Zayo has been provided with more information on the network. Service providers will rarely make a written commitment to sign a formal contract until a construction contract for the network has been signed. The signing of the construction contract has been delayed due to legal review but we are anticipating to have signed contracts and for construction to begin next quarter, 2012 Q2. We plan to aggressively begin marketing the network to service providers in 2012 Q2. Based on high levels of interest that have been expressed thus far, we anticipate no difficulty having providers offering services on Day One of network operations. We further note that VGCS is a formal partner in the project and they have consistently indicated they intend to be a Day One provider. The Baseline plan indicated that we would have 2 signed agreements with 9 more agreements being negotiated. The negative variance is due to the delay in the submission and approval of the environmental assessment and the delay in legal review of the fiber network construction bid documents. | N/A | RANA (Rockbridge Area Network Authority) will be operating the entire network. RANA has signed agreements with the County of Rockbridge for network handoff once construction and the grant period are complete. | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be 2 signed agreements by the end of 2012 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and contract. We expect to begin getting signed agreements during 2012 Q2 and for construction to begin during 2012 Q2 as well. | N/A | N/A | No variance | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be 53 total CAIs served by the end of 2012 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in legal review of the network construction bid documents and the contract. We expect for construction to begin during 2012 Q2 and to begin serving CAIs in Lexington during 2012 Q3. | The Baseline plan indicated that there would be 53 new CAIs served by the end of 2012 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. We expect for construction to begin during 2012 Q2 and to begin serving CAIs in Lexington during 2012 Q3. | N/A | No variance | 0 | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be a total of 480 residents/households passed by the end of 2012 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. We expect to have the network construction contract signed and for construction to begin during 2012 Q2. | The Baseline plan indicated that we would be serving a total of 184 residents/households by the end of 2012 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. We expect to have the network construction contract signed and for construction to begin during 2012 Q2. | The Baseline plan indicated that there would be 184 new subscribers served by the end of 2012 Q1. Negative variance is due to the delay in the submission and approval of the environmental assessment as well as the delay in the legal review of the network construction bid documents and the contract. We expect for construction to begin during 2012 Q2 and to begin serving subscribers in Lexington during 2012 Q4. | N/A | No variance | 0 | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be a total of 90 businesses passed by the end of 2012 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. We expect to have the network construction contract signed and for construction to begin during 2012 Q2. | The Baseline plan indicated that there would be a total of 36 business subscribers served by the end of 2012 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. We expect to have the network construction contract signed and for construction to begin during 2012 Q2. | The Baseline plan indicated that there would be 36 new business subscribers served by the end of 2012 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. We expect to have the network construction contract signed and for construction to begin during 2012 Q2. | N/A | No variance | N/A | FALSE | N/A | For the next quarter, 2012 Q2 (April 1 through June 30), the cabinets and the rest of the conduit will be delivered. Fiber construction and cabinet construction will begin. The data center construction will be substantially, approximately 95%, completed. We are expecting to have the DSL cabinet and fiber network construction contracts signed and for construction to start during the next quarter, 2012 Q2. There will be 10 new network miles deployed, 0 new network miles leased, 0 total CAI subscribers served, and 2 signed agreements with broadband wholesalers or last mile providers in 2012 Q2. 2012 Q2 completed milestones will include the substantial completion of the Data Center construction, signed contracts for both the cabinet construction and the fiber network construction, and for both the cabinet construction and the fiber network construction to have started. We anticipate the project will be 67% complete during 2012 Q4 and 100% complete during 2013 Q2. | Rockbridge, County of | The contract negotiations for the data center construction held up the data center contract from being signed and delayed the start of construction. Data center construction has now begun and is scheduled to be completed during 2012 Q2. The award has been made for the procurement of the materials needed for the Fiber and DSL cabinet construction and the contracts for the fiber network and cabinet construction are undergoing legal preparation and review. The contracts are anticipated to be signed next quarter and construction is scheduled to begin during the next quarter as well. We have had some difficulty in getting some of the easements that are needed but have found that people's objections come from the fact that they do not understand the project. Once the project and the easement is explained to them, most landowners are happy to sign the easements. Also during 2012 Q1, we submitted a route change request, the route change has been approved by NTIA and the NOAA Grants Office. | The Data Center construction has begun and is scheduled for substantial completion during 2012 Q2. The necessary easements for the cabinet and fiber network construction projects have been identified and we are actively pursuing getting those signed. The County is talking with landowners one-on-one and we have a local engineering firm that has been actively pursuing those easements as well. We have made substantial progress. 70% of the fiber routes do not need easements, so any delays that come in gathering the easements will NOT delay the start of the fiber network construction. The three procurement bids (cabinets, conduit, and fiber) have been awarded with deliveries scheduled for next quarter. The award for the cabinet and fiber network construction bids has been made and the contracts are currently undergoing legal preparation and review. We are anticipating having both construction contracts signed and for construction to start next quarter, 2012 Q2. | TRUE
NT10BIX5570129 | 2012 | Q2 | Q2 - 2012 | The project's activities during this quarter have been Data Center construction, project management, Cabinet site construction, Fiber Network construction, and reporting. We have signed contracts for both the Fiber Network construction and the Cabinet construction and the contractors have begun work. All of the cabinets and conduit have been delivered. Project management duties have included compliance and reporting documentation, Rockbridge Area Network Authority (RANA) board meetings, continued development of an operations guide for both the network and the data center, work on getting construction contracts signed and construction started. | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | The baseline plan indicated that there would be 40 new network miles deployed by the end of 2012 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that delayed the start of construction. The contract has now been signed and construction has begun. Other delays have been the Rockbridge County-City of Lexington agreement being signed and getting VDOT permits. The Rockbridge County-City of Lexington agreement has been signed and we are expecting to get the VDOT permits early 2012 Q3. | N/A | N/A | N/A | The baseline plan indicated that there would be 40 new network miles deployed by the end of 2012 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that delayed the start of construction. The contract has now been signed and construction has begun. Other delays have been the Rockbridge County-City of Lexington agreement being signed and getting VDOT permits. The Rockbridge County-City of Lexington agreement has been signed and we are expecting to get the VDOT permits early 2012 Q3. | N/A | N/A | The baseline plan indicated that there would be 2 new interconnection points deployed by the end of 2012 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that delayed the start of construction. Construction began during this quarter, 2012 Q3. | 0 | 3 | 0 | In 2011 Q3 and Q4 we met with Virginia Global Communication Systems (VGCS) and MGW Communications, two local service providers, who indicated keen interest in offering services on the network. We also prepared an informational handout for service providers and developed a draft service provider contract, which is currently undergoing legal review. We have had discussions with Zayo, a major national wholesaler of Internet access, and Zayo has been provided with more information on the network. Shentel has also expressed interest in being on the network. Service providers will rarely make a written commitment to sign a formal contract until a construction contract for the network has been signed. The signing of the construction contract was delayed due to legal review but we now have signed contracts. We plan to aggressively begin marketing the network to service providers in 2012 Q3. Based on high levels of interest that have been expressed thus far, we anticipate no difficulty having providers offering services on Day One of network operations. We further note that VGCS is a formal partner in the project and they have consistently indicated they intend to be a Day One provider. The Baseline plan indicated that we would have 3 signed agreements with 9 more agreements being negotiated. The negative variance is due to the delay in the submission and approval of the environmental assessment and the delay in legal review of the fiber network construction bid documents. | N/A | RANA (Rockbridge Area Network Authority) will be operating the entire network. RANA has signed agreements with the County of Rockbridge for network handoff once construction and the grant period are complete. | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be 3 signed agreements by the end of 2012 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and contract. Construction began during this quarter, 2012 Q2. | N/A | N/A | No variance | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be 79 total CAIs served by the end of 2012 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in legal review of the network construction bid documents and the contract. Construction began during 2012 Q2 and we expect to begin serving CAIs in Lexington during 2012 Q3. | The Baseline plan indicated that there would be 79 total CAIs served by the end of 2012 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in legal review of the network construction bid documents and the contract. Construction began during 2012 Q2 and we expect to begin serving CAIs in Lexington during 2012 Q3. | N/A | No variance | 0 | 0 | 0 | 0 | 0 | The baseline plan indicated that there would be a total of 750 residents/households passed by the end of 2012 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction has started. | The baseline plan indicated that we would be serving a total of 292 residents/households by the end of 2012 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction has started. | The baseline plan indicated that there would be a total of 292 new subscribers served by the end of 2012 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction has started. We expected to begin serving subscribers in Lexington during 2012 Q4. | N/A | No variance | 0 | 0 | 0 | 0 | 0 | The baseline plan indicated that there would be a total of 135 businesses passed by the end of 2012 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and we expect to begin passing businesses during 2012 Q3. | The baseline plan indicated that there would be a total of 61 subscribers served by the end of 2012 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and we expect to begin serving subscribers during 2012 Q4. | The baseline plan indicated that there would be a total of 61 subscribers served by the end of 2012 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and we expect to begin serving subscribers during 2012 Q4. | N/A | No variance | N/A | FALSE | N/A | For the next quarter, 2012 Q3 (July 1 through September 30), the fiber is expected to be delivered. Data Center construction will be complete and the Data Center will be operational. We expect the fiber contractor to have made substantial progress once the VDOT permits come in and now that the Rockbridge County-City of Lexington agreement has been signed. The cabinet construction will be continuing and we expect substantial progress to be made on the cabinets as well. We anticipate the project will be 67% complete during 2012 Q4 and 100 % complete during 2013 Q2. We are anticipating to have 15 miles deployed, we plan to have 0 CAIs connected, and we are planning to have 3 service provider agreements by the end of 2012 Q3. | Rockbridge, County of | The contract negotiations for the data center construction held up the data center contract from being signed and delayed the start of construction. Data center construction is underway and is scheduled for completion early in 2012 Q3. The Fiber and DSL construction contracts have been signed and construction has begun on both. Fiber construction was held up because of getting the Rockbridge County-City of Lexington agreement signed, but that has just been signed and construction throughout the City can now begin. The VDOT permits have also been delayed in getting processed but we are expecting to have those early 2012 Q3. We have had some difficulty in getting some of the easements that are needed but have found that people's objections come from the fact that they do not understand the project. Once the project and the easement is explained to them, most landowners are happy to sign the easements. | The Data Center construction is scheduled for completion during 2012 Q3. The necessary easements for the cabinet and fiber network construction projects have been identified and we will continue to actively pursue getting those signed. The County will continue talking with landowners one-on-one and we have a local engineering firm that will continue actively pursuing those easements as well. We have made substantial progress. 70% of the fiber routes do not need easements, so any delays that come in gathering the easements will NOT delay the start of the fiber network construction. We are anticipating the delivery of all of the fiber during next quarter, 2012 Q3. The VDOT permits are expected next quarter, 2012 Q3, so the fiber contractor should begin making substantial progress on the fiber routes. | TRUE
NT10BIX5570129 | 2012 | Q3 | Q3 - 2012 | The project's activities during this quarter have been finishing up the Data Center construction and punch lists, project management, cabinet site construction, fiber network construction, and reporting. The fiber contractor is make substantial progress on the construction of the network. The city of Lexington conduit is completed and they are working on areas throughout the County. All fiber has been delivered. Project management duties have included compliance and reporting documentation, Rockbridge Area Network Authority (RANA) board meetings, continued development of interested service provider lists and making contact with prospective service providers, and managing the construction of both the cabinets and the fiber network. | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | The baseline plan indicated that there would be 60 new network miles deployed by the end of 2012 Q3. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that delayed the start of construction. There was also a delay in getting the VDOT permits for construction to begin. Construction is now underway and construction inside the City of Lexington is complete. We expect the construction in the County to begin to move at a faster pace because it is easier than in the City. | N/A | N/A | N/A | The baseline plan indicated that there would be 60 new network miles deployed by the end of 2012 Q3. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that delayed the start of construction. There was also a delay in getting the VDOT permits for construction to begin. Construction is now underway and construction inside the City of Lexington is complete. We expect the construction in the County to begin to move at a faster pace because it is easier than in the City. | N/A | N/A | The baseline plan indicated that there would be 2 new interconnection points deployed by the end of 2012 Q3. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that delayed the start of construction. Construction began last quarter, 2012 Q2. | 0 | 5 | 0 | In 2011 Q3 and Q4 we met with Virginia Global Communication Systems (VGCS) and MGW Communications, two local service providers, who indicated keen interest in offering services on the network. We also prepared an informational handout for service providers and developed a draft service provider contract, which is currently undergoing legal review. We have had discussions with Zayo, a major national wholesaler of Internet access, and Zayo has been provided with more information on the network. Shentel has also expressed interest in being on the network. Service providers will rarely make a written commitment to sign a formal contract until a construction contract for the network has been signed. The signing of the construction contract was delayed due to legal review but we now have signed contracts. We plan to aggressively begin marketing the network to service providers in 2012 Q4. Based on high levels of interest that have been expressed thus far, we anticipate no difficulty having providers offering services on Day One of network operations. We further note that VGCS is a formal partner in the project and they have consistently indicated they intend to be a Day One provider. The Baseline plan indicated that we would have 5 signed agreements with 9 more agreements being negotiated. The negative variance is due to the delay in the submission and approval of the environmental assessment and the delay in legal review of the fiber network construction bid documents. | N/A | RANA (Rockbridge Area Network Authority) will be operating the entire network. RANA has signed agreements with the County of Rockbridge for network handoff once construction and the grant period are complete. | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be 5 signed agreements by the end of 2012 Q3. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and contract. Construction began during last quarter, 2012 Q2. | N/A | N/A | No variance | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be 105 total CAIs served by the end of 2012 Q3. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in legal review of the network construction bid documents and the contract. Construction began during 2012 Q2 and we expect to begin serving CAIs in Lexington during 2012 Q4. | The Baseline plan indicated that there would be 105 total CAIs served by the end of 2012 Q3. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in legal review of the network construction bid documents and the contract. Construction began during 2012 Q2 and we expect to begin serving CAIs in Lexington during 2012 Q4. | N/A | No variance | 400 | 0 | 0 | 0 | 0 | The baseline plan indicated that there would be a total of 1000 residents/households passed by the end of 2012 Q3. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction has started. | The baseline plan indicated that we would be serving a total of 392 residents/households by the end of 2012 Q3. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction has started. | The baseline plan indicated that there would be a total of 392 new subscribers served by the end of 2012 Q3. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction has started. We expected to begin serving subscribers in Lexington during 2012 Q4. | N/A | No variance | 50 | 0 | 0 | 0 | 0 | The baseline plan indicated that there would be a total of 180 businesses passed by the end of 2012 Q3. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and work has begun. | The baseline plan indicated that there would be a total of 81 subscribers served by the end of 2012 Q3. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and we expect to begin serving subscribers during 2012 Q4. | The baseline plan indicated that there would be a total of 81 subscribers served by the end of 2012 Q3. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and we expect to begin serving subscribers during 2012 Q4. | N/A | No variance | N/A | FALSE | N/A | For the next quarter, 2012 Q4 (October 1 through December 31), fiber construction is expected to continue. Data Center construction and punch lists will be complete and W&L will begin placing equipment inside the Data Center. We expect the fiber contractor to continue to make substantial progress on construction throughout the County. The cabinet construction will be continuing and we expect substantial progress to be made on the cabinets as well. We anticipate the project will be 67% complete during 2012 Q4 and 100% complete during 2013 Q2. We are anticipating to have 25 miles deployed, we plan to have 10 CAIs connected, and we are planning to have 3 service provider agreements by the end of 2012 Q4. | Rockbridge, County of | The fiber contractor is making substantial progress with construction. The issues faced this quarter have continued to be easements and getting them from landowners. We are working to resolve the issues on the routes and are planning to have them all resolved by the end of the next quarter, 2012 Q4. | The Data Center construction is scheduled for final completion and acceptance during 2012 Q4. The necessary easements for the cabinet and fiber network construction projects have been identified and we will continue to actively pursue getting those signed. CenturyLink has a new process that allows us to place our DSL cabinets inside of their existing easements, this has greatly reduced the number of easements needed for cabinet construction. We expect to hear back from CenturyLink on the requirements for placing our DSL cabinets during the next quarter, 2012 Q4. The County has made substantial progress along the fiber routes with landowners and getting the needed easements and the County will continue talking with landowners one-on-one and we have a local engineering firm that will continue actively pursuing the remaining easements as well. One of the routes from Buena Vista to Mountain View Elementary will be removed pending approval and will greatly reduce the number of needed easements. We are expecting to get all of the remaining easements before the end of the next quarter, 2012 Q4 and do not foresee any further issues with the remaining landowners. VDOT permits have been granted and construction is underway throughout the County. | TRUE
NT10BIX5570129 | 2012 | Q4 | Q4 - 2012 | The project's activities during this quarter have continued to be project management, cabinet site construction, fiber network construction, ordering fiber and DSL equipment, and reporting. The fiber contractor is making substantial progress on the construction of the network. Project management duties have included compliance and reporting documentation, Rockbridge Area Network Authority (RANA) board meetings, making contact with interested service providers, managing the delivery and inventorying of the DSL and fiber equipment, and managing the construction of both the cabinets and the fiber network. There has been 30 new network miles deployed and 1 signed service provider agreement. | 30 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | The baseline plan indicated that there would be 80 new network miles deployed by the end of 2012 Q4. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that delayed the start of construction. There was also a delay in getting the VDOT permits for construction to begin. Construction is now underway and the construction contractor is making substantial progress. | N/A | N/A | N/A | The baseline plan indicated that there would be 80 new network miles deployed by the end of 2012 Q4. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that delayed the start of construction. There was also a delay in getting the VDOT permits for construction to begin. Construction is now underway and the construction contractor is making substantial progress. | N/A | N/A | The baseline plan indicated that there would be 2 new interconnection points deployed by the end of 2012 Q4. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that delayed the start of construction. Construction began in 2012 Q2. | 1 | 4 | 8 | We have a signed agreement with Rockbridge Global Village (RGV) and Shentel has committed to sign an agreement, we are still working with them to finalize an agreements. We have also been talking with Zayo, CenturyLink, and MGW Communications about becoming service providers on the network. | N/A | RANA (Rockbridge Area Network Authority) will be operating the entire network. RANA has signed agreements with the County of Rockbridge for network handoff once construction and the grant period are complete. The current contact person for RANA information is RANA Secretary Dan Grim, 150 S. Main St., Lexington, VA 540-464-9656. | 1 | 0 | 0 | 0 | The Baseline plan indicated that there would be 6 signed agreements by the end of 2012 Q4. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and contract. Construction began during 2012 Q2. | N/A | N/A | No variance | 0 | 0 | 0 | 0 | The Baseline plan indicated that there would be 137 total CAIs served by the end of 2012 Q4. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in legal review of the network construction bid documents and the contract. Construction began during 2012 Q2 and we expect to begin serving CAIs in Lexington during 2013 Q1. | The Baseline plan indicated that there would be 137 total CAIs served by the end of 2012 Q4. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in legal review of the network construction bid documents and the contract. Construction began during 2012 Q2 and we expect to begin serving CAIs in Lexington during 2013 Q1. | N/A | No variance | 700 | 0 | 0 | 0 | 0 | The baseline plan indicated that there would be a total of 1220 residents/households passed by the end of 2012 Q4. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction is making substantial progress. | The baseline plan indicated that we would be serving a total of 480 residents/households by the end of 2012 Q4. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction is making substantial progress. | The baseline plan indicated that we would be serving a total of 480 residents/households by the end of 2012 Q4. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction is making substantial progress. | N/A | No variance | 150 | 0 | 0 | 0 | 0 | The baseline plan indicated that there would be a total of 219 businesses passed by the end of 2012 Q4. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and the contractor is making substantial progress. | The baseline plan indicated that there would be a total of 99 businesses passed by the end of 2012 Q4. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and the contractor is making substantial progress. | The baseline plan indicated that there would be a total of 99 businesses passed by the end of 2012 Q4. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and the contractor is making substantial progress. | N/A | No variance | N/A | FALSE | N/A | For the next quarter, 2013 Q1 (January 1 through March 31), fiber construction is expected to continue. Cabinet site construction is also expected to continue. Both contractors are making substantial progress on construction and we expect that to continue. We are expecting to begin to light up portions of the network as fiber is installed inside the conduit. The fiber equipment vendors are expected to install and configure the core and edge network equipment to begin to serve customers. We anticipate the project will be 80% complete during 2013 Q1 and 100% complete during 2013 Q2. We are anticipating to have 60 miles of backbone and drop connections installed, we plan to have 10 CAIs connected, and we are planning to have 2 service provider agreements by the end of 2013 Q1. | Rockbridge, County of | The fiber contractor is making substantial progress with construction. There have been issues with obtaining the easements needed for construction but easements have all been received along Forge Road during this quarter. To be able to secure the needed easements along Forge Road, the sides of the road had to be switched in some locations as well as switch from underground to aerial and vice versa. There were easement issues along Route J from Buena Vista to Mountain View Elementary. We will be submitting a route change request to remove this route from construction and to adjust Route C construction for easement locations. | CenturyLink is expected to start working on the connections into their cabinets for the DSL connections and we are expecting to begin being able to build the remaining cabinet sites on the CenturyLink easements during the next quarter. Construction will continue to progress throughout the County as all VDOT permits have been received and the contractor is making substantial progress in installing the conduit and fiber. We expect the fiber equipment vendors to install and configure the core and edge network equipment and we expect to begin being able to light up portions of the network as the fiber is installed. | TRUE
NT10BIX5570129 | 2013 | Q1 | Q1 - 2013 | The project's activities during this quarter have continued to be project management, cabinet site construction, fiber network construction, installing and testing fiber and DSL equipment, and reporting. The fiber contractor is making substantial progress on the construction of the network. Project management duties have included compliance and reporting documentation, Rockbridge Area Network Authority (RANA) board meetings, making contact with interested service providers, managing the delivery and inventorying of the DSL and fiber equipment, and managing the construction of both the cabinets and the fiber network. There has been 17 new backbone network miles deployed, bringing the total miles to 47 installed out of 63 total backbone miles. We have 1 new signed service provider agreement for a total of 1 signed service provider agreement. The project connected 10 CAIs during Q1 2013 bringing the total CAIs installed to 21. The project completed 10 DSL cabinets during Q1 2013 for a total of 23 DSL cabinets completed throughout the County. | 47 | 0 | 0 | 0 | 47 | 0 | 0 | 1 | The baseline plan indicated that there would be 100 new network miles deployed by the end of 2013 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that delayed the start of construction. Also, we have submitted a couple route change requests that have reduced the total number of network miles than is shown in the baseline plan. | N/A | N/A | N/A | The baseline plan indicated that there would be 100 new network miles deployed by the end of 2013 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that delayed the start of construction. Also, we have submitted a couple route change requests that have reduced the total number of network miles than is shown in the baseline plan. | N/A | N/A | The baseline plan indicated that there would be 2 new interconnection points deployed by the end of 2013 Q1. The 1 interconnection point that is now complete is the Data Center with fiber equipment installed and the core network equipment operating. We expect to have the 2nd interconnection point connected to the network during 2013 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that delayed the start of construction. Construction began in 2012 Q2. | 1 | 5 | 8 | We have a signed agreement with Rockbridge Global Village (RGV) and Shentel has committed to sign an agreement, we are still working with them to finalize the agreement. We have also been talking with Zayo, Blue Ridge Internet Works, CenturyLink, and MGW Communications about becoming service providers on the network. | N/A | RANA (Rockbridge Area Network Authority) will be operating the entire network. RANA has signed agreements with the County of Rockbridge for network handoff once construction and the grant period are complete. The current contact person for RANA information is RANA Project Lead Scott Robertson, 150 S. Main St., Lexington, VA 703-286-7415. | 1 | 0 | 0 | 0 | The Baseline plan indicated that there would be 8 signed agreements by the end of 2013 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and contract. Construction began during 2012 Q2. | N/A | N/A | No variance | 21 | 21 | 0 | 0 | The Baseline plan indicated that there would be 164 total CAIs served by the end of 2013 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in legal review of the network construction bid documents and the contract. We are expecting to be able to begin lighting up the CAIs in Lexington during 2013 Q2. Fiber has been installed in the completed CAIs. | The Baseline plan indicated that there would be 164 total CAIs served by the end of 2013 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in legal review of the network construction bid documents and the contract. We are expecting to be able to begin lighting up the CAIs in Lexington during 2013 Q2. | N/A | No variance | 1200 | 0 | 0 | 0 | 0 | The baseline plan indicated that there would be a total of 1420 residents/households passed by the end of 2013 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction is making substantial progress. | The baseline plan indicated that we would be serving a total of 560 residents/households by the end of 2013 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction is making substantial progress. | The baseline plan indicated that we would be serving a total of 560 residents/households by the end of 2013 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction is making substantial progress. | N/A | No variance | 225 | 0 | 0 | 0 | 0 | The baseline plan indicated that there would be a total of 260 businesses passed by the end of 2013 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and the contractor is making substantial progress. | The baseline plan indicated that there would be a total of 117 businesses served by the end of 2013 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and the contractor is making substantial progress on backbone construction. Also another reason for delay has been the extensive approval process by the Environmental Assessment team on the requested business connection locations. Once we have final approval on the business connections, construction will begin. | The baseline plan indicated that there would be a total of 117 businesses served by the end of 2013 Q1. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and the contractor is making substantial progress on backbone construction. Also another reason for delay has been the extensive approval process by the Environmental Assessment team on the requested business connection locations. Once we have final approval on the business connections, construction will begin. | N/A | No variance | N/A | FALSE | N/A | For the next quarter, 2013 Q2 (April 1 through June 30), fiber construction is expected to continue and near completion. Cabinet site construction is also expected to continue and near completion. Both contractors are making substantial progress on construction and we expect that to continue. Once we receive final approval for the route change request for business connections, that construction work is expected to begin. We are expecting to be able to light up portions of the network as the initial testing of the fiber equipment is completed. We anticipate the project will be 95% complete during 2013 Q2 and 100% complete during 2013 Q3. We are anticipating to have 90 miles if backbone and drop connections installed, we plan to have 35 CAIs connected, and we are expecting to have 2 service provider agreements by the end of 2013 Q2. We are projecting to have the remaining 6 DSL cabinet sites completed and ready for DSL equipment. | Rockbridge, County of | The fiber contractor is continuing to make substantial progress on the backbone construction. We have all of the easement issues cleared up along Forge Road and the route change that was submitted has been approved so the contractor is beginning to finish up the construction along Forge Road. Other issues have been with CenturyLink and getting them to complete their make ready but they have now begun their work that is needed and they are approximately halfway completed. This is allowing our contractor to begin doing aerial cable installation. We submitted a route change request to NTIA for approval of our business drops throughout the two cities and the county. This work was approved in our original submission we just didn't have the exact location for each drop at that time. We are currently waiting approval and once that is granted the contractor can begin construction of the connections. | CenturyLink is making progress on the make ready work that is needed for our contractor to install the aerial portions of the network. CenturyLink is also working on getting the DSL cabinet connections installed allowing the DSL cabinets to begin being online and offer services. We are currently waiting on the approval from NTIA/BTOP for the business connections. Once we have approval for the business connections construction will begin. We are expecting to be able to light up portions of the network as fiber equipment initial testing is completed. | TRUE
NT10BIX5570129 | 2013 | Q2 | Q2 - 2013 | The project's activities during this quarter have continued to be project management, cabinet site construction, fiber network construction, installing and testing fiber and DSL equipment, and reporting. The fiber contractor is continuing to make substantial progress on the construction of the network. Project management duties have included compliance and reporting documentation, Rockbridge Area Network Authority (RANA) board meetings, getting service providers configured and tested on the network, managing the delivery and inventorying of the DSL and fiber equipment, and managing the construction of both the cabinets and the fiber network. There have been 13 new backbone network miles deployed, bringing the total miles to 60 installed out of 63 total backbone miles. We have 1 new signed service provider agreement for a total of 2 signed service provider agreements. The project connected 24 CAIs during Q2 2013 bringing the total CAIs installed to 45 out of 53 total CAIs. The project completed 4 DSL cabinets during Q2 2013 for a total of 27 DSL cabinets completed throughout the County. | 60 | 0 | 0 | 0 | 60 | 0 | 0 | 2 | The baseline plan indicated that there would be 134 new network miles deployed by the end of 2013 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that delayed the start of construction. Also, we have submitted a couple route change requests that have reduced the total number of network miles than is shown in the baseline plan. The current total network backbone miles is 63 and there are a total of 7 miles of business and CAI connections making a project total of 70 miles. | N/A | N/A | N/A | The baseline plan indicated that there would be 134 new network miles deployed by the end of 2013 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as delay in the legal review of the network construction bid documents. There has also been a delay in the legal preparation and review of the fiber network construction contract and that delayed the start of construction. Also, we have submitted a couple route change requests that have reduced the total number of network miles than is shown in the baseline plan. The current total network backbone miles is 63 and there are a total of 7 miles of business and CAI connections making a project total of 70 miles. | N/A | N/A | No variance | 2 | 4 | 8 | We have signed agreements with Rockbridge Global Village (RGV) and Blue Ridge Internet Works (BRI). Shentel has committed to sign an agreement but we are still working with them to finalize the agreement. We have also been talking with Zayo, CenturyLink, and MGW Communications about becoming service providers on the network. | N/A | RANA (Rockbridge Area Network Authority) will be operating the entire network. RANA has signed agreements with the County of Rockbridge for network handoff once construction and the grant period are complete. The current contact person for RANA information is RANA Project Lead Scott Robertson, 150 S. Main St., Lexington, VA 703-286-7415. | 2 | 0 | 0 | 0 | The Baseline plan indicated that there would be 9 signed agreements by the end of 2013 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and contract. Construction began during 2012 Q2. | N/A | N/A | No variance | 45 | 45 | 0 | 100 | The Baseline plan indicated that there would be 177 total CAIs served by the end of 2013 Q2. There was a total of 24 installed in 2013 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in legal review of the network construction bid documents and the contract. Also, as part of the grant there is only a total of 53 CAIs to be served and that was not reflected in the Baseline plan. The Baseline plan originally included both the CAIs and business connections instead of only the CAIs. We are expecting to continue lighting up the CAIs in Lexington during 2013 Q3. Fiber has been installed in the completed CAIs. | The Baseline plan indicated that there would be 177 total CAIs served by the end of 2013 Q2. There was a total of 24 installed in 2013 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in legal review of the network construction bid documents and the contract. Also, as part of the grant there is only a total of 53 CAIs to be served and that was not reflected in the Baseline plan. The Baseline plan originally included both the CAIs and business connections instead of only the CAIs. We are expecting to continue lighting up the CAIs in Lexington during 2013 Q3. Fiber has been installed in the completed CAIs. | N/A | The network services will be provided by independent service providers and the current services that will be available range in speeds depending on the need of the end user. We expect for the 100Mbps speed tier shown in the total to be the most common among CAIs and large businesses. The maximum speed at this point is 1Gbps symmetric service. | 1450 | 0 | 0 | 0 | 0 | The baseline plan indicated that there would be a total of 1600 residents/households passed by the end of 2013 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction is making substantial progress. | The baseline plan indicated that we would be serving a total of 632 residents/households by the end of 2013 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction is making substantial progress. Residential connections are not a part of the project and so there will be no residential customers connected to the network during the grant period. | The baseline plan indicated that we would be serving a total of 632 residents/households by the end of 2013 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The network construction contract has been signed and construction is making substantial progress. Residential connections are not a part of the project and so there will be no residential customers connected to the network during the grant period. | N/A | No variance | 275 | 0 | 0 | 0 | 0 | The baseline plan indicated that there would be a total of 300 businesses passed by the end of 2013 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and the contractor is making substantial progress and is almost finished with construction. | The baseline plan indicated that there would be a total of 135 businesses served by the end of 2013 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and the contractor is making substantial progress on backbone construction and is almost finished. Also another reason for delay has been the extensive approval process by the Environmental Assessment team on the requested business connection locations. We received final approval from the EA team and construction will begin during 2013 Q3. There is a total of 84 approved business drops and that will be completed during 2013 Q3. | The baseline plan indicated that there would be a total of 135 businesses served by the end of 2013 Q2. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and the contract. The construction contract has been signed and the contractor is making substantial progress on backbone construction and is almost finished. Also another reason for delay has been the extensive approval process by the Environmental Assessment team on the requested business connection locations. We received final approval from the EA team and construction will begin during 2013 Q3. There is a total of 84 approved business drops and that will be completed during 2013 Q3. | N/A | No variance | N/A | FALSE | N/A | For the next quarter, 2013 Q3 (July 1 through September 30), fiber construction and business drop construction are expected to be completed. Cabinet site construction is also expected to be completed. We are expecting to have the network up and running and to be provided services to customers throughout Rockbridge County. We are expecting to have all 63 backbone network miles completed and all 7 lateral miles at the end of 2013 Q3 out of 63 total backbone miles and 7 total lateral miles. We are expecting to have all 53 CAIs complete out of 53 total, all 84 business drops complete out of 84 total, 2 service provider agreements signed, and all 28 DSL cabinets installed out of 28 total. We anticipate the project will be 100% complete during 2013 Q2. | Rockbridge, County of | The fiber contractor is continuing to make substantial progress on the backbone construction. We have most of the easement issues cleared up along Forge Road and the route change that was submitted has been approved and the contractor is now complete with that work. Other issues have been with CenturyLink and getting them to complete their make ready but they are now complete with all of their make ready. This is allowing our contractor to complete sections of aerial installation. The route change request for business drops throughout the region have been approved and the contractor has begun completing those connections. | We are anticipating all construction to be completed in 2013 Q3 and for the network to up and running and offering services to anyone with a connection to the network. | TRUE
NT10BIX5570129 | 2013 | Q3 | Q3 - 2013 | The Lexington School System is already using the RANA network. The Buena Vista Public School system is evaluating eRate proposals by RANA providers that will greatly increase the bandwidth available for teaching, testing, and research at their four schools, and eliminate a point-to-point wireless network created locally to overcome local Telco limitations. The Rockbridge County School system is also evaluating eRate proposals by RANA providers. Their current eRate program costs about $10,000 per month. The enhanced working environment at the County Administration offices with new 50/10 fiber connection allows the bandwidth to make the move to cloud resources such as Office365 and the new cloud based county website. The Regional E911 Dispatch Center and County Sheriffâ€™s office are now connected by a fiber based WAN, providing for both faster data transfer and disaster recovery/continuity of the enhanced 911 services. Of all of the available commercial and industrial properties advertised on the County Economic Development website four were targeted as grant-funded business drops, and only one will not be accessible by RANA fiber. Over the past 8 months, the historic Natural Bridge of Virginia, including hotel and conference center, has been marketed for sale. This historic, national icon and county namesake is the cornerstone of regional tourism. When prospective buyers expressed interest, one of their first questions was always, â€œdoes the hotel and conference center have access to a fiber network?â€ Fortunately, and via sound strategic planning, the RANA network passed directly in front of the hotel and received a grant-funded business drop, which was a key factor in enabling a successful outcome via a unique public/private partnership project. Natural Bridge Hotel has now upgraded to two separate fiber strands, one for their internal systems and the other for high speed guest access. Whatâ€™s more, they have paid for an additional 1,250 ft. fiber connection to the Natural Bridge Caverns offices. Natural Bridge of Virginia has been sold to the Virginia Conservation Legacy Fund (VCLF), a nonprofit organization that, among several goals, seeks to conserve an appropriate portion of Virginia's natural resources for public access and enjoyment. Part of the agreement is that VCLF will eventually deed the Natural Bridge and surrounding properties to become a Virginia State Park. From a business standpoint we should point to the savings reported by Sayre, Inc. who has enjoyed monthly savings with their fiber connectivity at Natural Bridge Station. Sayre Enterprises is an embroidery and embellishment manufacturing company with production and distribution facilities located in Buena Vista, Virginia. They recently bought the old Natural Bridge High School building in Natural Bridge Station, Virginia to become a business incubator as well as become Sayre Inc. corporate offices. The business incubator known as Stonebridge, has turned the former High School into a multidimensional venue with office space as well as entertainment, athletic, recreational, and educational facilities available for clients. They have new RANA fiber in use at both Buena Vista and Natural Bridge Station locations with multiple strands in use at Natural Bridge Station. Whiteâ€™s Travel Center in Raphine, a grant-funded business drop, that we expect to yield greater economic activity in the immediate area. Fiber availability has enhanced the marketing and development of more properties adjacent to Whiteâ€™s with new businesses such as a doctorâ€™s office and new logistics company settling in. In downtown Buena Vista the project has allowed Mariner Media to purchase greater bandwidth to support their publishing business. We can also identify the savings Southern Virginia University received from the development of RANA, saving several thousand dollars a month due to increased competition. | 70 | 0 | 0 | 0 | 70 | 0 | 0 | 2 | The baseline plan indicated that there would be 134 new network miles deployed by the end of 2013 Q3. Negative variance is due to the fact that we have submitted a couple route change requests that have reduced the total number of network miles then is shown in the baseline plan. The route change requests were submitted to reduce the amount of total network miles because of landowner easement issues and also because with the added routes, we would not have been able to remain on budget. The current total network backbone miles is 63 and there are a total of 7 miles of business and CAI connections making a project total of 70 miles. | N/A | N/A | N/A | The baseline plan indicated that there would be 134 new network miles deployed by the end of 2013 Q3. Negative variance is due to the fact that we have submitted a couple route change requests that have reduced the total number of network miles then is shown in the baseline plan. The route change requests were submitted to reduce the amount of total network miles because of landowner easement issues and also because with the added routes, we would not have been able to remain on budget. The current total network backbone miles is 63 and there are a total of 7 miles of business and CAI connections making a project total of 70 miles. | N/A | N/A | No variance | 2 | 4 | 8 | RANA has signed agreements with Rockbridge Global Village (RGV) and Blue Ridge Internet Works (BRI). Shentel has committed to sign an agreement but we are still working with them to finalize the agreement. We have also been talking with Zayo, CenturyLink, and MGW Communications about becoming service providers on the network. | The network authority will provide both dark fiber and transport at $50.00 per month, per strand, per mile. | RANA (Rockbridge Area Network Authority) will be operating the entire network. RANA has signed agreements with the County of Rockbridge for network handoff now that construction and the grant period are complete. The current contact person for RANA information is RANA Project Lead Scott Robertson, 150 S. Main St., Lexington, VA 703-286-7415. | 2 | 0 | 0 | 0 | The Baseline plan indicated that there would be 9 signed agreements by the end of 2013 Q3. Negative variance is due to the delay in getting the environmental assessment submitted and approved as well as the delay in the legal review of the network construction bid documents and contract. Construction is now complete and RANA is actively pursuing service providers to offer services on the network. | N/A | N/A | No variance | 52 | 52 | 0 | 100 | The Baseline plan indicated that there would be 177 total CAIs served by the end of 2013 Q3. There was a total of 8 installed in 2013 Q3. Negative variance is because as part of the grant there is only a total of 52 CAIs to be served and that was not reflected in the Baseline plan. The Baseline plan originally included both the CAIs and business connections instead of only the CAIs. Fiber has been installed in the completed CAIs. | The Baseline plan indicated that there would be 177 total CAIs served by the end of 2013 Q3. There was a total of 8 installed in 2013 Q3. Negative variance is because as part of the grant there is only a total of 52 CAIs to be served and that was not reflected in the Baseline plan. The Baseline plan originally included both the CAIs and business connections instead of only the CAIs. Fiber has been installed in the completed CAIs. | N/A | The network services will be provided by independent service providers and the current services that will be available range in speeds depending on the need of the end user. We expect for the 100Mbps speed tier shown in the total to be the most common among CAIs and large businesses. The maximum speed at this point is 1Gbps symmetric service. | 1600 | 0 | 0 | 0 | 0 | No variance | The baseline plan indicated that we would be serving a total of 632 residents/households by the end of 2013 Q3. Negative variance is because Residential connections are not a part of the project and so there will be no residential customers connected to the network during the grant period. | The baseline plan indicated that we would be serving a total of 632 residents/households by the end of 2013 Q3. Negative variance is because Residential connections are not a part of the project and so there will be no residential customers connected to the network during the grant period. | N/A | No variance | 300 | 84 | 84 | 0 | 0 | No variance | The baseline plan indicated that there would be a total of 135 businesses served by the end of 2013 Q3. Negative variance is because there is a total of 84 approved business drops. All construction on the 84 drops was completed during 2013 Q3. | The baseline plan indicated that there would be a total of 135 businesses served by the end of 2013 Q3. Negative variance is because there is a total of 84 approved business drops. All construction on the 84 drops was completed during 2013 Q3. | N/A | No variance | N/A | FALSE | N/A | For the next quarter, 2013 Q4 (October 1 through December 31), the project will be in the closeout stage. We will be working towards completing all of the necessary reports and submission of the reports before their deadlines. | Rockbridge, County of | One of the issues we had during this quarter was getting permission to install the DSL cabinets within the CenturyLink space. We received that permission for all but 2 of the cabinet sites and have completed the construction at 27 of the DSL sites out of the original 29 planned DSL sites. The backbone construction was completed as scheduled as well as the cabinet construction and the drop construction. We had a very tight time line for drop construction because of the delay in the approval of the Environmental Review but the construction was finished before the September 30th project deadline. | We are not anticipating any challenges or issues during the closeout period. | TRUE
NT10BIX5570130 | 2010 | Q4 | Q4 - 2010 | - Extensive collaboration with EA Firm and various environmental agencies that provide ultimate approvals based on Assessments. - Legal support finalized Non-Disclosure Agreements and execution between recipient and/or sub-recipient and 2 telecommunication companies. A third one is under review - Final version of Agreements for fiber optic services reviewed by our legal support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Awaiting completion of Environmental Assessment | Awaiting completion of Environmental Assessment | Awaiting completion of Environmental Assessment | Awaiting completion of Environmental Assessment | Awaiting completion of Environmental Assessment | Awaiting completion of Environmental Assessment | Awaiting completion of Environmental Assessment | Awaiting completion of Environmental Assessment | 1 | 5 | 20 | Current Letter of Intent Agreements: MediaCom, Frontier Communications, Triniti Communications, Pinebelt Communications, and Troy Cablevision. | The proposed network will aggregate and deliver the services of each interconnected last mile service provider to each of their subscriber. The service providers themselves will charge their end-user customers for services rendered. Each service provider will pay a Toll Fee which equates to 23%-44% of the retail service they charge each end-user per month per service. This fee will be reported as program income in accordance with the terms and conditions of the award and federal guidelines. | A2D, Inc. is the sub-recipient and operator of the South Central Alabama Broadband Cooperative District Network. A2D's corporate office is located at 3800 Camp Creek Parkway, Bldg 1400, Suite 132, Atlanta, GA 30331. A2D will operate and manage the entire network on behalf of the Municipal Broadband Authority, as well as ensure that the network meets the required performance standards of each interconnected Wholesale Middle Mile and Last Mile service provider. | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | NONE | FALSE | NONE | a) Receive official Environmental Assessment approval from the NTIA; b) Officially break ground in Hayneville, AL as part of Phase I Deployment; c) Acquire the necessary access permits for City, County, State, Utility, Private and Railroad Right of Way Access; d) Acquire the necessary AL DOT Permits for State Highway and Bridge Access Permits | Trillion Communications Corp. | Trillion worked extensively and met with the executive leadership of Troy Cable Vision to discuss the overlapping of both projects within Crenshaw County, Alabama. A Memorandum of Understanding was signed on 1/24/2011 and both companies agreed, in principle, to take the necessary steps to eliminate the overlap. This MOU ensures s a win-win opportunity for both entities where the community will truly benefit from receiving the broadband-based connectivity they will need both today and tomorrow. Each company worked diligently, both singularly and collectively, to ensure the funds provided by the federal grant are appropriately utilized and allowable. Troy Cablevision's Southeast Alabama SmartBand Project and Trillion's South Central Alabama Broadband Commission (SCABC) Project provide for and embraces an open access, non-discriminatory network in contiguous counties. Our MOU stipulates which company will manage the construction of the overlapping network, as well as assessing the factors that support the determination for cost sharing. | Continued uncertainty in the regulatory environment in regards to project compliance with either (i) the Federal Communications Commissionâ€™s (â€œFCCâ€) Internet Policy Statement principles which were made temporarily enforceable for certain broadband providers, or (ii) the rules, including network management practices, adopted by the FCC in its December 23, 2010, REPORT AND ORDER (GN Docket No. 09-191,WC Docket No. 07-52) In the Matter of Preserving the Open Internet Broadband Industry Practices. | TRUE
NT10BIX5570130 | 2011 | Q1 | Q1 - 2011 | The Trillion Team completed the following objectives: Completed Phase I Permit Drawings for Middle Mile Network deployment with Lowndes and Dallas County, formed the Broadband Municipal Authority, began testing Phase I Transport and Access Systems, and completed 75% of the required documentation to ensure the project receives its FONSI within May of 2011. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Awaiting for FONSI after completion of environmental assessment. | Awaiting for FONSI after completion of environmental assessment. | Awaiting for FONSI after completion of environmental assessment. | Awaiting for FONSI after completion of environmental assessment. | Awaiting for FONSI after completion of environmental assessment. | Awaiting for FONSI after completion of environmental assessment. | Awaiting for FONSI after completion of environmental assessment. | Awaiting for FONSI after completion of environmental assessment. | 0 | 3 | 20 | Pending agreements are with Level 3 Communications, Windstream Communications and Kentucky Datalink. Note of Correction: Pine Belt Communications currently has not executed a Letter of Intent with the Trillion Team although a formal NDA is currently in place previously reported as an entity who signed agreements. | The â€˜networkâ€™ will aggregate and deliver the services of each interconnected commercial service providers (carrier, wholesale, last mile, community-based) to each of their end-users (subscribers) connected. Each service provider charges and bills each end-user customers (subscribers) for services rendered over the network. Each service provider pays to the network a monthly per service fee (Toll Fee) which equates to 23%-44% of the monthly retail services charged each end-user (subscriber). Network services are as listed: Dark Fiber Lease(protected/unprotected), High-Capacity Data Transport (Dedicated/Point2Point), Wireless Backhaul, and Last Mile Toll Services. | A2D, Inc has been designated as the Operator of the Network. A2D is also a sub-recipient. A2D will manage the day-to-day operations of the proposed network on behalf of the municipal broadband authority by providing the required personnel, field equipment and vehicles, and network support and provisioning systems required to meet the Service Level Agreements of each service provider that competes to deliver services across the network. This includes but is not limited to managing the network's Transport, Access and Wireless-based systems, Outside Plant infrastructure, terminals, as well as co-location facilities. | 0 | 0 | 0 | 0 | Negotiations still underway | Negotiations still underway | Negotiations still underway | Wholesale Carrier Access (FTTP): The current bandwidth matrix available is 1mbps; 500mbps; 1 GigE; 10 GigE. The delivery speed per provider will be determined by the demand generated by the Sales effort by each service provider. Wholesale Dark Transport: Dark Fiber Lease- 2 Strand/mile + Maintenance/ 1,3,5 Year IRU; Fiber swap. | 0 | 0 | 0 | 0 | Awaiting FONSI; No construction has begun. | Awaiting FONSI; No construction has begun. | Awaiting FONSI; No construction has begun. | Internet: The speeds that will be available will be 10mbps-500mbps;up 1 GigE. The delivery speed per Anchor institution will be determined by the size and need per site. Intranet: 100mbps-1GigE on-net connectivity to public "connected" facilities on the network. $100+/facility/month. | 0 | 0 | 0 | 0 | 0 | Awaiting FONSI; No construction has begun. | Awaiting FONSI; No construction has begun. | Awaiting FONSI; No construction has begun. | Awaiting FONSI; No construction has begun. | The speed available at home will range between 1mbps - 100 mbps; actual speeds provided based on the services orders from Commercial Service Providers initiated by Home owners. Intranet: 1mbps-100mbps on-net connectivity to public "connected" facilities on the network subsidized by Nonprofit or State agencies. $2-10/end-user/month. | 0 | 0 | 0 | 0 | 0 | Awaiting FONSI; No construction has begun. | Awaiting FONSI; No construction has begun. | Awaiting FONSI; No construction has begun. | Awaiting FONSI; No construction has begun. | The speed available at businesses will be between 1mbps- 1 GigE; Actual need will be based on services orders from the Commercial Service Providers initiated by Businesses (end-user). | None | FALSE | None | The objective of the next quarter is as follows: 1. Secure FONSI to begin construction within May 2011. 2. Install approximately 113 Miles of Middle Mile Outside Plant Infrastructure within Lowndes and Dallas County. 3. Begin construction of last mile access connections to 3200 households within the NTIA approved census block groups of the City of Selma and the City of Haynevill. 4. Complete Drawings and Secure Permits for construction activities in Macon County and Escambia County. 5. Begin beta testing of network services within Lowndes and Dallas County. | Trillion Communications Corp. | The Trillion Team had a delay in receiving the FONSI due to more information required for premise connections, bridge attachments and tower connections. The Trillion Team also had a delay in systems testing due to the winter storms that slowed delivery of critical network equipment and components. Finally, the Trillion Team was delayed in producing the required permit drawings for Phase I construction due to the non-availability of adequate digital as-build drawings which required extensive field survey and GIS/based validation. Although these challenges cause several adjustments in our time line, technical assistance from BTOP was only required in addressing some of the concerns with our Environmental Assessment Reviewers. | The Trillion Team is preparing to receive all of the required concurrency letters required by the Environmental Assessment. If the FONSI is not received by May 15, 2011, delays in construction could be incurred due to material and equipment shortages resulting from increased competition from other applicants and reduction in component systems from Asian markets affected by the Tsunami. The noted potential delays can be mitigated by increasing simultaneous installation crews. We have discussed potential material delays with our vendors and have built our schedule around their current updated supply capabilities. | TRUE
NT10BIX5570130 | 2011 | Q2 | Q2 - 2011 | The following significant accomplishments were realized this quarter: a) The SCABC Authority continues to enroll/sign-up additional municipalities; b) Developed an independent System Performance Validation plan; c) SCABC signed lease for space in the Hayneville Plaza Building; d) A2D Sub-Recipient Agreement Signed. e) Submitted construction permit drawings to Alabama Department of Transportation f) First project construction management office opened and staffed in Hayneville, Al | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 0 | 3 | 20 | Pending- Level 3 Communications, Windstream Communications(KDL) Note of Correction: Pine Belt Communications currently has not executed a Letter of Intent. A formal NDA is currently in place. | The â€˜networkâ€™ will aggregate and deliver the services of each interconnected commercial service providers (carrier, wholesale, last mile, community-based) to each of their end-users (subscribers) connected. Each service provider charges and bills each end-user customer (subscribers) for services rendered over the network. Each service provider pays to access the network a monthly per service fee (Toll Fee) which equates to 23% - 44% of the monthly retail services charged each end-user (subscriber). This fee will be reported as program income in accordance with the terms and conditions of the grant award and federal guidelines. Network services are as follows: Dark Fiber Lease(protected/unprotected), High-Capacity Data Transport (Dedicated/Point2Point), Wireless Backhaul, and Last Mile Toll Services. | Antwon Alsobrook, president & CEO 3800 Camp Creek Parkway Bldg 1400, Ste 132 Atlanta, GA 30331 Phone: (678) 999-2525 Fax: (678) 623-5116 Web Site: www.a2dinc.com E-mail: a2dinfo@a2dinc.com A2D, Inc has been designated as the Operator of the Network. A2D is also a sub-recipient. A2D will manage the day-to-day operations of the proposed network on behalf of the municipal broadband authority by providing the required personnel, field equipment and vehicles, and network support and provisioning systems required to meet the Service Level Agreements of each service provider that competes to deliver services across the network. This includes but not limited to managing the network's Transport, Access and Wireless-based systems, Outside Plant infrastructure, terminals, as well as co-location facilities. | 0 | 0 | 0 | 0 | What we have encountered is that most providers will want to perform their own validation of the network before executing a comprehensive MSA and SLA given the uniqueness of our design and model. We do however, expect Level 3 and Magnolia Belle to execute MSA's prior to network lighting. In the interim we have executed 8 LOI's and 2 stronger LOC's | What we have encountered is that most providers will want to perform their own validation of the network before executing a comprehensive MSA and SLA given the uniqueness of our design and model. We do however, expect Level 3 and Magnolia Belle to execute MSA's prior to network lighting. In the interim we have executed 8 LOI's and 2 stronger LOC's | What we have encountered is that most providers will want to perform their own validation of the network before executing a comprehensive MSA and SLA given the uniqueness of our design and model. We do however, expect Level 3 and Magnolia Belle to execute MSA's prior to network lighting. In the interim we have executed 8 LOI's and 2 stronger LOC's | What we have encountered is that most providers will want to perform their own validation of the network before executing a comprehensive MSA and SLA given the uniqueness of our design and model. We do however, expect Level 3 and Magnolia Belle to execute MSA's prior to network lighting. In the interim we have executed 8 LOI's and 2 stronger LOC's | 0 | 0 | 0 | 0 | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 0 | 0 | 0 | 0 | 0 | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | 0 | 0 | 0 | 0 | 0 | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. | Private LAN (On-Net) Backhaul and Inter-Jurisdictional Access Services for Public Safety & First Responders | FALSE | None | a) 32%- Project Notification will be in process of Phase 2- Macon County; b) Extensive dialogue/collaboration with city and municipal entities will occur to ensure timely issuance of road/highway permits; c) Groundbreaking event(s) to be planned/scheduled; d) Initiate a Financial Assessment and Program Specific Audit; e) Construction-related Material and equipment will be ordered. | Trillion Communications Corp. | The extended lead time on the availability of the fiber material will impact the actual testing and lighting of long fiber runs. However, we will mitigate this delay by deploying and installing the fiber conduit prior to receipt of the fiber cables. | a) Permitting delays b) Access to fiber cable; c) Ramp up with contractors d) working out full logistics to effect placement of the fiber; e) Full adoption by last mile stakeholders. | TRUE
NT10BIX5570130 | 2011 | Q3 | Q3 - 2011 | The following significant accomplishments were realized this quarter: a. Submitted Construction Permit drawings to the Alabama Department of Transportation (ALDOT); b. First Project construction management office opened and staffed in Hayneville, AL; c. Signed and executed Phase I loan commitment Letter; d. Developed Ground-breaking event with support and input from multiple municipalities and anchor institutions; e. Booked $2M+ in in-kind match from key vendors; f. Worked on real estate valuations for municipal and anchor partner in-kind match; g. Received conduit and other infrastructure material in preparation for Phase 1 construction; h. Agreement with Troy Cable was executed & resolved the "Overlap Special Award Condition" (SAC); i. Notification#3:Trillion Team held a County-wide Construction Informational Community event in the Town of Hayneville, Lowndes County, AL; j. Notification #4:Trillion Team held a 3 county stakeholder session in Montgomery, Alabama. This event provided an open platform for stakeholders to address new questions from constituents; k. Published project update letter in print and website for stakeholders, including PCI. www.ecommunityalabama.org. l. In the process of completing program specific audit for the period 8/1/2010 through 7/31/2011. m. Pursuit of loan for matching funds n. Receipt of materials/equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The delay in proceeding with construction stemmed from the effect of the Finding Of No Significant Impact (FONSI) delay. However, we have revised our construction plan to segregate installation efforts into 3 core sectors: backbone, distribution and premise connections. With that, we plan to deploy contractors in various sectors simultaneously to achieve our timeline requirements. | The delay in proceeding with construction stemmed from the effect of the Finding Of No Significant Impact (FONSI) delay. However, we have revised our construction plan to segregate installation efforts into 3 core sectors: backbone, distribution and premise connections. With that, we plan to deploy contractors in various sectors simultaneously to achieve our timeline requirements. | The delay in proceeding with construction stemmed from the effect of the Finding Of No Significant Impact (FONSI) delay. However, we have revised our construction plan to segregate installation efforts into 3 core sectors: backbone, distribution and premise connections. With that, we plan to deploy contractors in various sectors simultaneously to achieve our timeline requirements. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. We will accelerate discussions with fiber-based owners to facilitate the process. | The delay in proceeding with construction stemmed from the effect of the Finding Of No Significant Impact (FONSI) delay. However, we have revised our construction plan to segregate installation efforts into 3 core sectors: backbone, distribution and premise connections. With that, we plan to deploy contractors in various sectors simultaneously to achieve our timeline requirements. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. This is not a critical component of the project at the moment. | The delay in proceeding with construction stemmed from the effect of the FONSI delay. This is not a critical component of the project at the moment. | We conducted the site survey of our key interconnect location at Level 3 and began the associated equipment provisioning. | 0 | 5 | 0 | Master Service Agreement are under review with Magnolia Belle (last mile service provider) and eCom Direct Wireless (last mile service provider). Services Agreements remain pending with Level 3 and Windstream, as Services Providers for the network. | The â€˜networkâ€™ will aggregate and deliver the services of each interconnected commercial service providers (carrier, wholesale, last mile, community-based) to each of their end-users (subscribers) connected. Each service provider charges and bills each end-user customer (subscribers) for services rendered over the network. Each service provider pays to access the network a monthly per service fee (Toll Fee) which equates to 23% - 44% of the monthly retail services charged each end-user (subscriber). This fee will be reported as Program Income in accordance with the terms and conditions of the grant award and federal guidelines. Network services are as follows: Dark Fiber Lease(protected/unprotected), High-Capacity Data Transport (Dedicated/Point2Point), Wireless Backhaul, and Last Mile Toll Services. | A2D, Inc has been designated as the Operator of the Network. A2D is also a sub-recipient. A2D will manage the day-to-day operations of the proposed network on behalf of the municipal broadband authority by providing the required personnel, field equipment and vehicles, and network support and provisioning systems required to meet the Service Level Agreements of each service provider that competes to deliver services across the network. This includes but not limited to managing the network's Transport, Access and Wireless-based systems, Outside Plant infrastructure, terminals, as well as Co-location facilities. Contact: A2D Inc (sub recipient) 3800 Camp Creek Parkway Atlanta, GA 30331 Phone: (678) 999-2525 Fax: (678) 523-5116 Contact: Tony Shackelford E-mail: (tony@a2dinc.com) | 0 | 0 | 0 | 0 | Continuing aggressive discussions with Service Providers to solidify agreements. | Continuing aggressive discussions with Service Providers to solidify agreements. | Continuing aggressive discussions with Service Providers to solidify agreements. | Project provides Dark Fiber IRU's for Public Safety, Emergency Management Agency (EMA), and Municipalities. Lit Services:(Wholesale Transport Bandwidth up to 10G. Wholesale Carriers Services Providers will provide new tiers and plans as serving areas are available. | 0 | 0 | 0 | 0 | Encountered a delay in construction as a result of the FONSI delay. We plan to deploy additional contractors in various sectors simultaneously to achieve our timeline requirements. | Encountered a delay in construction as a result of the FONSI delay. We plan to deploy additional contractors in various sectors simultaneously to achieve our timeline requirements. | Encountered a delay in construction as a result of the FONSI delay. We plan to deploy additional contractors in various sectors simultaneously to achieve our timeline requirements. | Project provides Dark Fiber IRU's for Public Safety, EMA, and Municipalities. Lit Services:(Wholesale Transport Bandwidth up to 10G. Also, Commercial Services Provider will provide new tiers and plans as serving areas are available. | 0 | 0 | 0 | 0 | 0 | Encountered a delay in construction as a result of the FONSI delay. We plan to deploy additional contractors in various sectors simultaneously to achieve our timeline requirements. | Encountered a delay in construction as a result of the FONSI delay. We plan to deploy additional contractors in various sectors simultaneously to achieve our timeline requirements. | Encountered a delay in construction as a result of the FONSI delay. We plan to deploy additional contractors in various sectors simultaneously to achieve our timeline requirements. | Encountered a delay in construction as a result of the FONSI delay. We plan to deploy additional contractors in various sectors simultaneously to achieve our timeline requirements. | Commercial Services Provider will provide new tiers and plans as serving areas are available. | 0 | 0 | 0 | 0 | 0 | Encountered a delay in construction as a result of the FONSI delay. We plan to deploy additional contractors in various sectors simultaneously to achieve our timeline requirements. | Encountered a delay in construction as a result of the FONSI delay. We plan to deploy additional contractors in various sectors simultaneously to achieve our timeline requirements. | Encountered a delay in construction as a result of the FONSI delay. We plan to deploy additional contractors in various sectors simultaneously to achieve our timeline requirements. | Encountered a delay in construction as a result of the FONSI delay. We plan to deploy additional contractors in various sectors simultaneously to achieve our timeline requirements. | Commercial Services Provider will provide new tiers and plans as serving areas are available. | Private Local Area Network (LAN) (On-Net) Backhaul and Inter Jurisdictional Access Services for Public Safety & First Responders | FALSE | None | Construction will begin; Cash Match will be secured; Community Anchor Institutions connected: 7; Complete the Program Audit; Increase membership of South Central Broadband Commission (SCABC); Complete 85% Phase 1 Notification; Complete the Asset Transfer Documentation; Complete Real Estate Valuations; New network miles deployed: 25; New network miles leased: 0; Total CAI subscribers served/connected: 7; Number of signed agreements with providers: 2; Plan to attend the BTOP Workshop in Cleveland, Oct 5 - 7, 2011 Upcoming ground-breaking ceremony and commencement of construction | Trillion Communications Corp. | We have had to adjust our strategy for route data collection given the number of infrastructure projects commencing and the affected resource capability of the local locating services. The South Central Broadband Commission (SCABC) continues to meet with potential Municipalities and Counties, relative to their membership in the Authority. | Project Adoption challenges: a. Poarch Band of Creek Indians: Tribal Consultant has been engaged to facilitate the project relationship to assure all efforts meet the requirements of the Poarch Creek Indian Nation: Construction, Tribal Relations, Governance, Compliance, Public Participation and Adoption. b. SCABC Broadband Authority+A2D efforts to secure municipal resolutions as membership within the broadband authority. Currently four (4) of the eight (8) Counties have joined the broadband authority. c. Local Telecom service provider adoption has progressed. With the physical construction underway, adoption should occur more quickly. | TRUE
NT10BIX5570130 | 2011 | Q4 | Q4 - 2011 | a. Received Loan Commitment Letter from 2nd Lender for balance of Cash Match Funds; b. Started construction of Backbone route; c. Increased construction management team in Alabama, engineering design and network engineering team in Atlanta and mobile field project engineering/inspection team in order to meet the construction activities that would ramp up significantly in the first calendar Quarter in 2012; d. Engineers successfully tested and configured the required backbone and transport cores that would be installed in the Level 3 Co-Location facility outside of Marion Junction, AL; e. secured heavy construction equipment to serve 3 additional crews and placed additional orders to accommodate 3 more crews; f. Reviewed SCABC - CCI Asset Transfer Plan and discussed SCABC's membership, organizational structure, and compliance laws and regulations; g. Reviewed terms of the County of Dallas, Alabama and Charter Communications Cable Franchise Agreement for compliance with federal, state and/or grant legal requirements; h. Trillion's program specific audit for FYE 7/31/11 was completed and submitted to OIG. | 29 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 10 Miles of backbone conduit has been installed to date. | N/A | N/A | N/A | 29 Miles of fiber (90% aerial) has been installed by Troy Cable as part of our Overlap Agreement. | N/A | N/A | N/A | 0 | 1 | 0 | No new providers to report at this time. | No new services to be reported at this time. | A2D Inc (Sub Recipient) Attn: Network Operations Phone: (678) 999-2525 Fax: (678) 523-5116 Network engineering & design, operations & maintenance, sales and marketing, service provider management, datacenter collocation, and data storage | 0 | 0 | 0 | 0 | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | 0 | 0 | 0 | 0 | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | 0 | 0 | 0 | 0 | 0 | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | 0 | 0 | 0 | 0 | 0 | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | To be served in subsequent quarters | Dark fiber lease for Public Safety, Emergency Responders, and Department of Homeland Security | FALSE | N/A | Phase 1 Middle Mile (network backbone) route complete. Phase 1-1st Last mile connectivity 50% - Town of Hayneville (250) Phase 1-2nd Last mile connectivity 10%- City of Selma (270) Phase 1- 10+ CAI's connected Phase 2 Middle Mile (network backbone)Permits Received. Phase 2 Pre-construction (backbone) in process Phase 3 Backbone GPS location completed. Network Inside Plant Equipment Deployed to NOC. Notification: Phase 2 Pre-construction complete Notification: Phase 2 Last mile Notification 30% complete- City of Tuskegee New network miles deployed: 237 miles New network miles leased: 194 miles Number of signed agreements with broadband wholesalers- 2 | Trillion Communications Corp. | The driving challenges/issues from this quarter were around acquiring construction permits on a timely basis. Details are provided above. | Closing on our Cash Match loan will determine how fast we can ramp up construction operations and catch up to baseline. | TRUE
NT10BIX5570130 | 2012 | Q1 | Q1 - 2012 | a. Installed 15 miles of fiber conduit b. Submitted for permit 80 miles of state right of way installation c. Received 3 additional railroad permits and permit for boring under Alabama River from US Army Core of Engineers e. Premise Pre-Installation Notification Program: Phase 1 Last Mile City 1- Hayneville, Alabama- report summary provided. f. National Telecommunications and Information Administration (NTIA) and National Oceanic and Atmospheric Administration (NOAA) performed a site visit to Trillion's home office and the Project's construction sites on March 12, 2012 through March 15, 2012. A detailed project inventory asset listing was provided and validation was performed by NTIA and NOAA. | 29 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | Work was delayed due to the suspension of the Project's funding. Fifteen miles of additional fiber conduit were installed prior to the suspension. Therefore, a total of 25 miles of conduit have been installed. An Action Plan developed to accelerate construction, once the suspension has been lifted. | Work was delayed due to the suspension of the Project's funding. Action Plan developed to accelerate construction, once the suspension has been lifted. | N/A | N/A | Work was delayed due to the suspension of the Project's funding. Twenty-nine (29) miles of fiber (90% aerial) has been installed by Troy Cable as part of our Joint Build Agreement. Action Plan developed to accelerate construction, once the suspension has been lifted. | Work was delayed due to the suspension of the Project's funding. Action Plan developed to accelerate construction, once the suspension has been lifted. | Work was delayed due to the suspension of the Project's funding. Action Plan developed to accelerate construction, once the suspension has been lifted. | Work was delayed due to the suspension of the Project's funding. Action Plan developed to accelerate construction, once the suspension has been lifted. | 0 | 1 | 0 | No new providers to report at this time. | No new services to be reported at this time. | South Central Alabama Broadband Commission (SCABC) - Sub Recipient Attention: Chairman Charlie King (SCABC Board Chairman) Phone: (334-412-9096) Network sales and marketing, service provider management. | 0 | 0 | 0 | 0 | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | 0 | 0 | 0 | 0 | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | 0 | 0 | 0 | 0 | 0 | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | 0 | 0 | 0 | 0 | 0 | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | Regional Tele-Health Network Program to provide a private network for approved healthcare providers participating in conjunction with the State of Alabama Tele-Health Initiative. | FALSE | N/A | a) The SCABC has confirmed that Grain Management to provide the Cash Match. The Terms/Conditions will be finalized by May 30th. b) Sub-Recipient status currently held by A2D, Inc. is being revised. The characteristics of this company changed, thus requiring the change from Sub-Recipient to Contractor. c) The project will centralize and control all construction activities via one General Contractor (GC), utilizing subcontractors to complete a simultaneous build out. Trillion will oversee all construction activity. d) Publish Procurement Document to assist in the selection of the General Contractor. e) The Minority Business Development Agency (MBDA) will play a significant role in supporting the Project Management activities. f) A Project "Accelerated Construction Plan" will be implemented to ensure the project meets ARRA Completion Date. g) Number of Miles to be Deployed by Next Quarter = 0. This is due primarily to the suspension of the federal funds. We do not expect to begin construction until NTIA/NOAA lifts the suspension. Expectations are that this will occur in the June time frame. Therefore , construction will re-start as soon as official authorization is received to go forward. h) Number of Community Anchor Institutions (CAIs) planned to connect = 0 (Rationale same as "g" above) i) Number of broadband wholesaler/last mile provider agreements you plan to sign (Rationale same as "g" above) | Trillion Communications Corp. | The Trillion Comprehensive Community Infrastructure (CCI) Project's funding remains in "suspension status". A letter was forwarded to Trillion from the Director of National Oceanographic and Atmospheric Administration (NOAA) advising the company of the suspended federal funds. Trillion responded with its Corrective Action Plan (CAP) which provided details, schedules and proactive measures to ensure timely completion of the project. An Action Plan has been developed and will be initiated to accelerate the overall construction effort. The goals and objectives include the following challenges: Finalized Cash Match plans, Organizational Structure, Construction Viability and Accountability. Each of these has been communicated and shared with NTIA. Additionally, Trillion has begun a collaborative effort with the Minority Business Development Agency (MBDA) to ensure the action plans and proposals meet the expectations of NTIA. The MBDA and its National Director are providing direct support, MBDA Funded Center resources, guidance and counsel to Trillion in an effort to complete the CAP requirements and to implement an effective action plan for the project. The director has also initiated dialogue with potential investor groups that were interested in providing non-federal matching funds for the project. By executing the proposed solutions, and through the support of the MBDA, we will be able to successfully complete the project within the time frame stipulated in the Grantâ€™s Specia | a) Davis-Bacon Act Wage Determinations are being finalized for several planned Heavy Construction Labor Employee positions. The wage rates proposed must adhere to the appropriate wages, as defined by the Department of Labor for each county. b) The Cash Match component with Grain Management must be finalized in May to ensure ARRA deliverables are met. c) Finalize restructuring the Project's Core Team, as defined by the Corrective Action Plan. d) Complete the agreement with the MBDA Funded Center to finalize the Project Manager position. e) Implement & monitor security and protection measures for the Material and Equipment currently staged in Hayneville, during the suspension period. f) Finalize Memorandum of Understanding between Trillion and South Central Alabama Broadband Commission. This document will reflect roles, responsibilities and assignments for SCABC. g) Develop a comprehensive Notification and Stakeholder manual. | TRUE
NT10BIX5570130 | 2012 | Q2 | Q2 - 2012 | a. Submitted June 2012 CAP Response to NOAA/NTIA. b. Transferred Grant-funded construction equipment and material to secure facility in Hope Hull Alabama. c. Hired Washington DC-based to assist in developing Corrective Action Plan and preparing comprehensive responses to NOAA's May 22 letter. d. Terminated Sub-Recipient, from the project. e. Issued General Contractor RFP for the project's Design/Build activity. Held Pre-Bid Construction conference with potential GCs. | 29 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | Work was stopped due to the suspension of the Project. Fifteen miles of additional fiber conduit were installed prior to the suspension. Therefore, a total of 25 miles of conduit have been installed. An Action Plan, a revised detailed budget forecast and a detailed budget narrative on how Trillion intends to complete the networkâ€™s deployment with the balance of the remaining Federal Grant is being finalized. | Work was stopped due to the suspension of the Project. An Action Plan was developed to accelerate the construction, once the suspension has been lifted. | N/A | N/A | Work was stopped due to the suspension of the Project. Twenty-nine (29) miles of fiber (90% aerial) have been installed by Troy Cable as part of our Joint Build Agreement. An Action Plan was developed to accelerate the construction, once the suspension has been lifted. | Work was stopped due to the suspension of the Project. An Action Plan was developed to accelerate the construction, once the suspension has been lifted. | Work was stopped due to the suspension of the Project. An Action Plan was developed to accelerate the construction, once the suspension has been lifted. | Work was stopped due to the suspension of the Project. An Action Plan was developed to accelerate the construction, once the suspension has been lifted. | 0 | 1 | 0 | No new providers to report at this time. | No new services to be reported at this time. | South Central Alabama Broadband Commission (SCABC) - Sub Recipient Attention: Chairman Charlie King (SCABC Board Chairman) Phone: (334-412-9096) Network sales and marketing, service provider management. | 0 | 0 | 0 | 0 | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | 0 | 0 | 0 | 0 | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | 0 | 0 | 0 | 0 | 0 | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | 0 | 0 | 0 | 0 | 0 | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | To be served in subsequent quarters after Suspension lifted | The SCABC network will be an open access platform. Its wholesale customers will use this network to deliver services to retail customers, including CAIs, businesses, and residential users. In addition, SCABC will provide nonrevenue-generating â€œOn-Netâ€ services, akin to a â€œCommunity Intranet,â€ that will provide local information and content to those end users who are connected to the network but who choose not to subscribe to broadband Internet access or other retail commercial services. Trillion and, prior to its departure, its Sub-Recipient, have had extensive discussions with potential wholesale customers, including Level 3 Communications, Internet2, Knology, Time Warner Telecom, Magnolia Belle, Troy Cablevision, and Baldwin County, as well as a possible collaboration with American Tower. These efforts were summarized in Trillionâ€™s March 9, 2012 (pp. 19-22) response to NOAA's February 8, 2012 letter. | FALSE | N/A | a) Trillion will issue a Request for Proposal to selected General Contractors that will be responsible for the Design/Build. The project will centralize and control all construction activities via one General Contractor (GC). Trillion will oversee all construction activity. b) Once the RFP process is completed and the General Contractor (GC) selected, Trillion will enter into an Master Service Agreement and Notice To Proceed agreement with a design-build contractor. Trillion will submit a copy of the bid response, as well as a revised project plan, organizational chart, and copies of key personnel of the selected GC(s) with the next scheduled CAP Response. c) Trillion directed its contractors to immediately to stop all work under the Grant Award, by letter dated February 9, 2012. One contractor completed its blueprint for transferring ownership of the network to SCABC at the conclusion of the Grant Award period of performance, in addition to certain other tasks within its agreed Statement of Work. d) Publish Procurement Document to assist in the selection of the General Contractor. e) Because the market for services is constantly evolving, Trillion will undertake a comprehensive review of its business plan, pro forma financial projections, demand forecasting, rate study, and go-to-market strategy for services using the SCABC network. f) A Project "Accelerated Construction Plan" will be implemented to ensure the project meets ARRA Completion Date. g) Trillion will collaborate with its consulting firm and its subcontractors to review, update, and validate its Marketing assumptions to expand and refine its business strategy, rate study, and go-to-market plans to ensure sustainability of the network. Trillionâ€™s revised business model will be based on the intent that SCABC will provide wholesale connectivity to retail providers of broadband Internet access and related services, which in turn will serve Community Anchor Institutes, businesses, and residential customers within the network footprint. h) Begin the project's Design/Build phase. i) Number of Community Anchor Institutions planned to connect = 0. (Rationale same as "g" above) j) Number of broadband wholesaler/last mile provider agreements you plan to sign = 0. (Rationale same as "g" above) | Trillion Communications Corp. | The Trillion Comprehensive Community Infrastructure (CCI) Project's funding remained in "suspension status". A letter was forwarded to Trillion from the Director of National Oceanographic and Atmospheric Administration (NOAA) advising the company of the suspended federal funds. Trillion responded with its Corrective Action Plan (CAP) on June 5, 2012 which provided details, schedules and proactive measures to ensure timely completion of the project. Trillion discussed the results of its efforts in its response to NOAA's May 22 Letter, as well as provided more detail in response to specific issues slated for discussion in its planned July 5 and July 13, 2012 responses. An immediate action taken by Trillion was the company retained the services of a Washington-based consulting firm to assist it with developing a Corrective Action Plan and preparing comprehensive responses to NOAA's May 22 letter. The new firm has a wealth of federal grant compliance, telecommunications and technology, and business planning expertise, including specific experience with BTOP award recipients, and Trillion has already benefitted greatly from their involvement and insight. An Action Plan has been developed and will be initiated to accelerate the overall construction effort. The goals and objectives include the following challenges: Finalizing the Cash Match/In-Kind plans, developing a feasible SCABC Organizational Structure, Construction Scheduling, Viability and Accountability. Each of these has be | a) Because Trillion recently terminated its relationship with two formerly central members of its project team, Trillionâ€™s go-forward plan to execute the Grant Award is currently being revised. Trillion will be assuming many of the project management responsibilities formerly discharged by its Sub-Recipient. In addition, with the departure of another key contractor, Trillion will rely on alternative resources, to the extent required, for the technical assistance that firm was to provide. b) Davis-Bacon Act Wage Determinations are being finalized for several planned Heavy Construction Labor Employee positions. The wage rates proposed will adhere to the appropriate wages, as defined by the Department of Labor for each county. c) The Non-Federal Match component must be finalized to ensure Grant deliverables are met. d) Finalize restructuring the Project's Core Team, as defined by the Corrective Action Plan. e) Implement an action to continually monitor the security and implement protection measures for the Material and Equipment currently staged in Hope Hull. These measures will remain in place during and after the suspension period. f) Revise the Sub-Recipient Agreement between Trillion and South Central Alabama Broadband Commission. This document will reflect roles, responsibilities and assignments for SCABC. g) Develop a comprehensive Notification and Stakeholder manual. h) Finalize the revised realigned budget, the detailed project plan and the organization charts | TRUE
NT10BIX5570130 | 2012 | Q3 | Q3 - 2012 | a. Submitted two July 2012 CAP Responses to NOAA/NTIA. | 29 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | Work was stopped due to the suspension and termination of the Project. Fifteen miles of additional fiber conduit were installed prior to the suspension. Therefore, a total of 25 miles of conduit have been installed. An Action Plan, a revised detailed budget forecast and a detailed budget narrative on how Trillion intended to complete the networkâ€™s deployment with the balance of the remaining Federal Grant was finalized. | Work was stopped due to the suspension and termination of the Project. An Action Plan was developed to accelerate the construction, once the suspension has been lifted. | N/A | N/A | Work was stopped due to the suspension and termination of the Project. Twenty-nine (29) miles of fiber (90% aerial) have been installed by Troy Cable as part of our Joint Build Agreement. An Action Plan was developed to accelerate the construction. | Work was stopped due to the suspension and termination of the Project. Prior to the termination notice, an Action Plan was developed to accelerate the construction, once the suspension has been lifted. | Work was stopped due to the suspension and termination of the Project. Prior to the termination notice, an Action Plan was developed to accelerate the construction, once the suspension has been lifted. | Work was stopped due to the suspension Prior to the termination notice, an of the Project. An Action Plan was developed to accelerate the construction, once the suspension has been lifted. | 0 | 1 | 0 | N/A. The project has been terminated. No new providers will be reported. | N/A. The project has been terminated. No new services will be reported. | N/A. The project has been terminated. | 0 | 0 | 0 | 0 | The Project has been terminated. No further activities planned. | The Project has been terminated. No further activities planned. | The Project has been terminated. No further activities planned. | The Project has been terminated. No further activities planned. | 0 | 0 | 0 | 0 | The Project has been terminated. No further activities planned. | The Project has been terminated. No further activities planned. | The Project has been terminated. No further activities planned. | The Project has been terminated. No further activities planned. | 0 | 0 | 0 | 0 | 0 | The Project has been terminated. No further activities planned. | The Project has been terminated. No further activities planned. | The Project has been terminated. No further activities planned. | The Project has been terminated. No further activities planned. | The Project has been terminated. No further activities planned. | 0 | 0 | 0 | 0 | 0 | The Project has been terminated. No further activities planned. | The Project has been terminated. No further activities planned. | The Project has been terminated. No further activities planned. | The Project has been terminated. No further activities planned. | The Project has been terminated. No further activities planned. | All work has stopped due to the suspension and termination of the Project. | FALSE | N/A | All work has ceased due to the termination of the Project. The project closeout process will begin during the next quarter. | Trillion Communications Corp. | Trillion responded with its Corrective Action Plan (CAP) on July 5, 2012 and July 13, 2012 which provided details, schedules and proactive measures to ensure timely completion of the project. An Action Plan had been developed to accelerate the overall construction effort. The goals and objectives include the following challenges: Finalizing the Cash Match/In-Kind plans, developing a feasible SCABC Organizational Structure, Construction Scheduling, Viability and Accountability. Each of these had been communicated and shared with NTIA. Additionally, Trillion began collaborating with the Minority Business Development Agency (MBDA) to ensure the action plans and proposals meet the expectations of NTIA. The MBDA and its National Director provided direct support, MBDA Funded Center resources, guidance and counsel to Trillion in an effort to complete the CAP requirements and to implement an effective action plan for the project. The purposeful intent behind the collaboration was to successfully complete the project within the time frame stipulated in the Grantâ€™s Special Awards Conditions (SAC) document. | The Project has been terminated and all work has stopped. Trillion will initiate the Project Closeout during the next quarter. | TRUE
NT10BIX5570131 | 2010 | Q4 | Q4 - 2010 | The outside plant design was finalized for Phase 1. The draft Environmental Assessment was discussed with NTIA and will be submitted during first quarter, 2011. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | We have no signed agreements with any wholesale or last mile providers. | We are currently developing wholesale products and pricing. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We may provide 10 Meg, 100 Meg, 1 GigE, and 10 GigE wholesale internet access for last mile providers. We may also provide network configuration and management. | FALSE | N/A | We will continue to seek approval of our environmental assessment. We plan to identify our equipment vendor, our Phase I outside plant contractor, and sign a contract with a fiber supplier. We also plan to work significantly on our land acquisition. | Peoples Telephone Cooperative Inc. | A delay was encountered while our lender and NTIA worked out their agreements. | We are currently working with Texas state agencies identified by our federal program officer to improve cost effectiveness of construction on state rights-of-way. | TRUE
NT10BIX5570131 | 2011 | Q1 | Q1 - 2011 | Our environmental assessment was completed and the FONSI was issued. The special award condition was satisfied and a new special award condition was issued for environmental compliance. The outside plant design developed last quarter was used to develop detailed construction plans and specifications. Plans and specifications were sent to bid. A construction firm was selected and construction will begin next quarter. An equipment vendor was selected and some of the project equipment will be delivered second quarter of 2011. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | We have no signed agreements with any wholesale or last mile providers. | Our wholesale pricing is as follows: 10 GigE, $15,000/month; 1 GigE, $6,000/month; 500 Meg, $4,000/month; 100 Meg, $2,250/month. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We are planning to provide 10 Meg, 100 Meg, 1 GigE, and 10 GigE wholesale internet access for last mile providers. We may also provide network configuration and management. | FALSE | N/A | During second quarter, 2011, we will receive our first shipment of equipment, install it, and begin the testing phase of this equipment. We plan to complete permits for construction and begin Phase IA construction. | Peoples Telephone Cooperative Inc. | Federal approval of our environmental assessment was delayed. | We continue to work with Texas state agencies identified by our federal program officer to improve cost effectiveness of construction on state rights-of-way. We are also working through environmental issues identified by our environmental assessment, in addition to construction delays caused by the delay in the environmental assessment FONSI. | TRUE
NT10BIX5570131 | 2011 | Q2 | Q2 - 2011 | We continued construction of Phase IA, nearing the halfway point with approx. 20 miles of duct in the ground. Plans & specifications were developed and a bid was negotiated with the incumbent contractor Gulf Shores for Phase IB. Part of the transmission equipment arrived, consisting of 4 Cisco ASR 9000s and enough access equipment to test them in a lab environment. Testing was completed and the equipment was accepted. A building site was located and acquired in Wills Point. The NTIA site visit was conducted in June. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The non-availability of fiber optic cable has ceased our network deployment activities. When cable is delivered late in the 4th quarter, 2011, these indicators should reflect deployment. | The non-availability of fiber optic cable has ceased our network deployment activities. When cable is delivered late in the 4th quarter, 2011, these indicators should reflect deployment. | The non-availability of fiber optic cable has ceased our network deployment activities. When cable is delivered late in the 4th quarter, 2011, these indicators should reflect deployment. | The non-availability of fiber optic cable has ceased our network deployment activities. When cable is delivered late in the 4th quarter, 2011, these indicators should reflect deployment. | The non-availability of fiber optic cable has ceased our network deployment activities. When cable is delivered late in the 4th quarter, 2011, these indicators should reflect deployment. | The non-availability of fiber optic cable has ceased our network deployment activities. When cable is delivered late in the 4th quarter, 2011, these indicators should reflect deployment. | The non-availability of fiber optic cable has ceased our network deployment activities. When cable is delivered late in the 4th quarter, 2011, these indicators should reflect deployment. | The non-availability of fiber optic cable has ceased our network deployment activities. When cable is delivered late in the 4th quarter, 2011, these indicators should reflect deployment. | 0 | 3 | 0 | We have no signed agreements with any wholesale or last mile providers. | Our wholesale pricing is as follows: 10 GigE, $15,000/month; 1 GigE, $6,000/month; 500 Meg, $4,000/month; 100 Meg, $2,250/month | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We are planning to provide 10 Meg, 100 Meg, 1 GigE and 10 GigE wholesale internet access for last mile providers. We may also provide network configuration and management. | FALSE | N/A | Revise fiber specifications and make a partial order to develop a second source for the fiber. Complete construction of Phase IA, with the exception of installing the fiber into the duct. Start Phase IB construction. Develop plans & specifications for Phase IC and negotiate pricing with the existing contractor, Gulf Shores. Deploy backbone equipment with the DWDM equipment and test the transport network. Place a building in Wills Point. | Peoples Telephone Cooperative Inc. | Federal approval of our environmental assessment was delayed. Fiber optic cable is in short supply and delivery dates have been delayed by more than 6 months. We have several route changes necessary due to the environmental assessment and identified cost savings over the original routes. | We continue to work with Texas state agencies identified by our federal program officer to improve cost effectiveness of construction on state rights-of-way. We are also working through environmental issues identified by our environmental assessment, in addition to construction delays caused by the delay in the environmental assessment FONSI. Fiber optic cable delivery has been delayed by more than 6 months. Without fiber, we cannot properly plan & schedule service to CAIs. This affects all aspects of implementation, as well as anticipated expense planning. | TRUE
NT10BIX5570131 | 2011 | Q3 | Q3 - 2011 | Phase 1A was completed with the exception of the fiber. Phase 1B and 1C have been contracted and begun. Between the 3 projects, 70 miles of 172 total miles have been constructed to the point of fiber placement and splicing. Phase 2A has been designed and contract let out. DWDM equipment is installed and in test. ASR 9000 backbone is installed, tested and 4 area schools have had their existing service upgraded. We succeeded in developing a second and third source for fiber procurement. | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 18.58 miles of fiber were delivered and installed. Additional fiber is scheduled to arrive 4th quarter. | 18.58 miles of fiber were delivered and installed. Additional fiber is scheduled to arrive 4th quarter. | 18.58 miles of fiber were delivered and installed. Additional fiber is scheduled to arrive 4th quarter. | 18.58 miles of fiber were delivered and installed. Additional fiber is scheduled to arrive 4th quarter. | 18.58 miles of fiber were delivered and installed. Additional fiber is scheduled to arrive 4th quarter. | 18.58 miles of fiber were delivered and installed. Additional fiber is scheduled to arrive 4th quarter. | 18.58 miles of fiber were delivered and installed. Additional fiber is scheduled to arrive 4th quarter. | 18.58 miles of fiber were delivered and installed. Additional fiber is scheduled to arrive 4th quarter. | 0 | 3 | 0 | We have no signed agreements with any wholesale or last mile providers. | Our wholesale pricing is as follows: 10 GigE, $15,000/month; 1 GigE, $6,000/month; 500 Meg, $4,000/month; 100 Meg, $2,250/month. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We are planning to provide 10 Meg, 100 Meg, 1 GigE and 10 GigE wholesale internet access for last mile providers. We may also provide network configuration and management. | FALSE | N/A | We expect a second fiber supplier to deliver 100 miles of fiber which will allow us to begin adding CAIs and customers to the fiber. Phase 1A will be complete with significant progress on Phase 1B and 1C. DWDM testing should be complete and circuits live from Dallas to Tyler and Longview. Additional CAIs will be connected. | Peoples Telephone Cooperative Inc. | Approval of the environmental assessment is still pending, delaying Phase 1B as we seek approval for some minor route changes as well. Lack of fiber has delayed getting service to customers and planned revenue generation is non-existent as a result. | We continue to work with Texas state agencies to improve cost effectiveness of construction on state rights-of-way. We plan to adjust our cash flow model to determine what adjustments may be necessary to the schedule in order to maintain the financial viability of this project. | TRUE
NT10BIX5570131 | 2011 | Q4 | Q4 - 2011 | We completed most of the construction in Phase 1 of 3, through rural areas from Quitman through Mineola, Grand Saline, Edgewood and to Wills Point. This resulted in a total of 41 miles in service. Duct was installed in 80% of the route from Mineola through Lindale, Van, Canton, and to Wills Point. Contruction began on duct from Wills Point to I-30. We also began construction on Phase 2 of 3 phases. | 41 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | Fiber was delivered mid-December and installation has begun. Fiber delivery delay caused variance. | Fiber was delivered mid-December and installation has begun. Fiber delivery delay caused variance. | Fiber was delivered mid-December and installation has begun. Fiber delivery delay caused variance. | Fiber was delivered mid-December and installation has begun. Fiber delivery delay caused variance. | Fiber was delivered mid-December and installation has begun. Fiber delivery delay caused variance. | Fiber was delivered mid-December and installation has begun. Fiber delivery delay caused variance. | Fiber was delivered mid-December and installation has begun. Fiber delivery delay caused variance. | Fiber was delivered mid-December and installation has begun. Fiber delivery delay caused variance. | 1 | 5 | 12 | The Cyber Shop in Grand Saline, Texas. | WiFi internet services will be provided to rural areas surrounding Grand Saline, Texas. We are charging The Cyber Shop $2,595.00 per month for 100 Meg. | None. | 1 | 0 | 0 | 1 | We have one customer receiving a speed of 100 Megs. The variance in subscriber counts is due to the environmental assessment taking longer than expected and fiber procurement delays. With fiber now being installed, we expect to begin serving additional subscribers next quarter. | The variance in subscriber counts is due to the environmental assessment taking longer than expected and fiber procurement delays. With fiber now being installed, we expect to begin serving additional subscribers next quarter. | The variance in subscriber counts is due to the environmental assessment taking longer than expected and fiber procurement delays. With fiber now being installed, we expect to begin serving additional subscribers next quarter. | We have one customer receiving a speed of 100 Megs. The variance in subscriber counts is due to the environmental assessment taking longer than expected and fiber procurement delays. With fiber now being installed, we expect to begin serving additional subscribers next quarter. | 0 | 0 | 4 | 4 | The variance in CAI counts is due to the environmental assessment taking longer than expected and fiber procurement delays. With fiber now being installed, we expect to begin serving additional subscribers next quarter. | The variance in CAI counts is due to the environmental assessment taking longer than expected and fiber procurement delays. With fiber now being installed, we expect to begin serving additional subscribers next quarter. | The variance in CAI counts is due to the environmental assessment taking longer than expected and fiber procurement delays. With fiber now being installed, we expect to begin serving additional subscribers next quarter. | All 4 CAIs are receiving 100 Megs. The variance in CAI counts is due to the environmental assessment taking longer than expected and fiber procurement delays. With fiber now being installed, we expect to begin serving additional subscribers next quarter. | 0 | 0 | 0 | 0 | 0 | No variance. | No variance. | No variance. | No variance. | No variance. | 0 | 0 | 0 | 0 | 0 | No variance. | No variance. | No variance. | No variance. | No variance. | None. | FALSE | N/A | We expect to procure a contract and begin to serve a large number of schools via the Region 8 Service Center. We have also contacted many schools and other community institutions along our routes who are very receptive to obtaining new or improved access via our fiber. We have several contracts pending including an electric cooperative and an end user who we expect to turn up in the first quarter, 2012. Additional contracts are expected with connection dates in the second quarter, 2012. By the end of the first quarter, 2012, we expect to have a total of 103 miles in service and 5 connections, including 2 CAIs. | Peoples Telephone Cooperative Inc. | Environmental approval of route changes was finally received as well as enough fiber to begin "lighting up" the facilities. Planned revenue is still non-existent and straining resources. The variance in subscriber counts (question #5) is due to the environmental assessment taking longer than expected and the delay in fiber procurement. | We have contacted many schools along our routes who are very receptive to obtaining new or improved access via our fiber, but they are under contract with other providers via the Universal Service ERate program and cannot commit to take our service until their current contract period is complete. | TRUE
NT10BIX5570131 | 2012 | Q1 | Q1 - 2012 | Last quarter we completed most of the construction of rural areas from Quitman through Mineola, Grand Saline, Edgewood, and to Wills Point. This quarter we completed the Mineola, Lindale, Van, Canton to Wills Point loop. Construction has begun on the Wills Point to Quinlan to Greenville leg. The completed construction in this quarter has permitted us to obtain signed agreements with 5 Community Anchor Institutions whom we expect to connect by the end of June. We have two sales-people working full-time to contact and connect anchor institutions. We have had many town-hall type presentations, as well as one-on-one meetings with economic development units, city managers, elected officials, representatives from educational institutions, and business-people from all walks of life. We also hope to be accepted into the lifeline broadband pilot project and are collaborating with other interested parties to make this project successful. | 102 | 0 | 0 | 0 | 102 | 0 | 0 | 0 | 102 miles placed and deployed. Approximately 77 miles are currently under construction. Fiber delivery delay caused variance. Now that we can procure fiber, and assuming we have good weather the rest of the year, we expect to be close to target by first quarter, 2013. | No variance. | No variance. | No variance. | 102 miles placed and deployed. Approximately 77 miles are currently under construction. Fiber delivery delay caused variance. Now that we can procure fiber, and assuming we have good weather the rest of the year, we expect to be close to target by first quarter, 2013. | No variance. | No variance. | No variance. | 6 | 2 | 12 | The last mile providers with whom we have signed agreements are: The Cyber Shop, ETEX Telephone, Cumby Telephone, Franklin County Wireless, ConNEXTions Telcom, and Peoples Communication, Inc. Of these six providers, three are receiving service in the first quarter, 2012, as shown below. | We are providing 100 Meg to 1000 Meg services to 6 providers. They are using them to provide WiFi internet services, to provide DSL services to their existing customers, or to access a second connection point for their network to provide redundancy. | None. | 2 | 1 | 0 | 7 | We anticipated more providers would be receiving new access by this point in the project, however, the majority of the providers with whom we are negotiating are requesting improved access. | No variance. | No variance. | 1 customer is receiving 20 megs. 1 customer is receiving 100 megs. 1 customer is receiving 1 Gig. The other tiers are 10 megs, 50 megs, 500 megs, and 10 gig. | 4 | 0 | 4 | 7 | The variance in CAI counts is due to the environmental assessment taking longer than expected and fiber procurement delays. With fiber now being installed, we expect to begin serving additional subscribers in the third quarter when their ERATE contracts change over to our company. | The variance in CAI counts is due to the environmental assessment taking longer than expected and fiber procurement delays. With fiber now being installed, we expect to begin serving additional subscribers in the third quarter when their ERATE contracts change over to our company. | The variance in CAI counts is due to the environmental assessment taking longer than expected and fiber procurement delays. With fiber now being installed, we expect to begin serving additional subscribers next quarter. We have 5 additional signed agreements, but we will not be able to serve these schools until 3rd quarter when their ERATE contracts end. | All 4 CAIs are receiving 100 Megs. We are also offering 10 megs, 20 megs, 50 megs, 500 megs, 1 gig and 10 gig tiers. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None. | FALSE | N/A | Next quarter we expect to be near completion on the Wills Point, Quinlan, and Greenville leg. We also expect to have a good deal of the design completed for the second phase of our project. We should have several more Community Anchor Institutions and last mile providers with signed agreements. We have 77 miles of cable currently under construction and expect to have that completed next quarter. We are also seeking approval to be involved in the lifeline broadband pilot project and are collaborating with several diverse entities to bring this to fruition. | Peoples Telephone Cooperative Inc. | Environmental approval of route changes was finally received as well as enough fiber to begin "lighting up" the facilities. Planned revenue is still under-budget and continues to strain resources. Now that we have program income and we will begin billing several educational community anchor institutions effective July 1, 2012, we expect the revenue strain to ease a bit during the second quarter. Fiber optic cable has also become more available so we are working to catch up construction and fiber installation. If we experience good weather conditions the rest of this year, we should be close to target by first quarter, 2013. | We have contacted many schools along our routes who are very receptive to obtaining new or improved access via our fiber, but they are under contract with other providers via the Universal Service ERate program and cannot commit to take our service until their current contract period is complete. Seven have signed agreements with us but will not begin receiving service from us until third quarter, 2012. Many more that we contract with over the next 3 quarters will be delayed until third quarter, 2013, for this very reason. There are 2 last mile providers with signed agreements that will receive service during the second quarter, 2012 and 1 that will be served in the third quarter, Trillion Partners. Trillion will, in turn, improve service to 51 schools in the third quarter with a possibility of more in the future (see http://www.trillion.net/customers/case_6.html.) | TRUE
NT10BIX5570131 | 2012 | Q2 | Q2 - 2012 | To date, we completed the southern sections of the project. This quarter we completed segments through the rural territory from Wills Point to Greenville and Mount Vernon to Mount Pleasant. The construction has allowed us to directly connect 9 community anchor institutions who will receive service July 1. We have two sales-people working full-time to contact and connect anchor institutions. We have had many town-hall type presentations, as well as one-on-one meetings with economic development units, city managers, elected officials, representatives from educational institutions, and business-people from all walks of life. We also hope to be accepted into the lifeline broadband pilot project and are collaborating with other interested parties to make this project successful. | 154 | 0 | 0 | 0 | 154 | 0 | 0 | 0 | 154 miles placed and deployed. Approximately 75 miles are currently under construction. Fiber delivery delay caused variance as well as delay of environmental assessment approvals. We expect to be close to target by second quarter, 2013. | No variance. | No variance. | No variance. | 154 miles placed and deployed. Approximately 75 miles are currently under construction. Fiber delivery delay caused variance as well as delay of environmental assessment approvals. We expect to be close to target by first quarter, 2013. | No variance. | No variance. | No variance. | 10 | 5 | 12 | The last mile providers with whom we have signed agreements are: The Cyber Shop, ETEX Telephone, Cumby Telephone, Franklin County Wireless/Mt Vernon Optic Herald, ConNEXTions Telcom, Peoples Communication, Inc., Trillion Partners, Down-to-Earth Broadband, CoStreet/Verizon, and Skynet. | We are providing 30 Megs to 4 Gig services to 10 providers. They are using them to provide WiFi internet services, to provide DSL services to their existing customers, or to access a second connection point for their network to provide redundancy. | None. | 2 | 4 | 0 | 8 | We projected that we would have 4 last mile providers receiving new access but most have been improved access rather than new access. | We projected we would have 1 last mile provider receiving improved access and have surpassed our projection. | No variance. | 1 customer is receiving both a 10 meg and a 20 meg circuit, 2 customers are receiving 100 megs, 2 customers are receiving 1 gig, and 1 customer is receiving 4 gigs. The other tiers are 50 megs, 500 megs, and 10 gigs. | 4 | 0 | 4 | 8 | The variance in CAI counts is due to the environmental assessment taking longer than expected and fiber procurement delays. We have several CAIs being served effective 7/1/2012 when their ERATE funding begins. | The variance in CAI counts is due to the environmental assessment taking longer than expected and fiber procurement delays. We have several CAIs being served effective 7/1/2012 when their ERATE funding begins. | The variance in CAI counts is due to the environmental assessment taking longer than expected and fiber procurement delays. We have several CAIs being served effective 7/1/2012 when their ERATE funding begins. | 3 CAIs are receiving 100 megs, 1 CAI is receiving 70 megs. We are also offering 10 megs, 20 megs, 50 megs, 500 megs, 1 gig, and 10 gig tiers. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Next quarter we expect to complete another 91.5 miles, including a run from Mt Pleasant to Paris with construction underway to Roxton and Bonham. Design work on the last phase should be complete with plans to start at both ends simultaneously in order to complete the project on time if there are no additional delays due to environmental assessment approvals. We have several community anchor institutions scheduled to go live July 1, and one wireless network serving over 50 schools and approximately 51,000 students going live at the same time. In all, we have 4 last mile provider contracts (with 6 more currently in negotiations) and 10 community anchor contracts we expect to be signed by the end of the quarter. We plan to connect 9 community anchor institutions during the third quarter of 2012. | Peoples Telephone Cooperative Inc. | Planned revenue is still under-budget and continues to strain resources. Now that we have program income and we will begin billing several educational community anchor institutions effective July 1, 2012, we expect the revenue strain to ease a bit during the third quarter. Fiber optic cable has also become more available so we are working to catch up construction and fiber installation. If we experience good weather conditions the rest of this year, and environmental assessments are approved in a timely manner, we should be close to target by second quarter, 2013. Additional route changes have again necessitated environmental assessments and the associated delay. | Additional route modifications have again necessitated environment assessments and the associated delays in approval have proven to be a challenge to our project. We have also experienced delays gaining easements or franchises in several cities which has delayed our progress, although not significantly so far. | TRUE
NT10BIX5570131 | 2012 | Q3 | Q3 - 2012 | To date, we completed the southern, eastern, and portions of the northern sections of the project. This quarter we completed segments into Mount Pleasant, Paris, and to the headquarters of Region 8 Educational Service Center which connects to 50 schools. The construction has allowed us to directly connect 8 community anchor institutions and numerous sites for 10 last mile providers. We continue to have one-on-one meetings with economic development units, city managers, elected officials, representatives from educational institutions, and business-people from all walks of life. We also hope to be accepted into the lifeline broadband pilot project and are collaborating with other interested parties to make this project successful. | 232 | 0 | 0 | 0 | 232 | 0 | 0 | 0 | 232 miles placed and deployed. Approximately 57 miles are currently under construction. Fiber delivery delay caused variance as well as delay of environmental assessment approvals. We expect to be close to target by second quarter, 2013. | No variance. | No variance. | No variance. | 232 miles placed and deployed. Approximately 57 miles are currently under construction. Fiber delivery delay caused variance as well as delay of environmental assessment approvals. We expect to be close to target by second quarter, 2013. | No variance. | No variance. | No variance. | 13 | 2 | 12 | The last mile providers with whom we have signed agreements are: The Cyber Shop, ETEX Telephone, Cumby Telephone, Franklin County Wireless/Mt Vernon Optic Herald, ConNEXTions Telcom, Peoples Communication, Inc., Trillion Partners, Down-to-Earth Broadband, CoStreet/Verizon, Skynet, Starnet, Peoples Wireless, and Northeast Texas Broadband. | We are providing 10 Megs to 4 Gig services to 10 providers. They are using them to provide WiFi internet services, to provide DSL services to their existing customers, or to access a second connection point for their network to provide redundancy. | None. | 5 | 5 | 0 | 8 | We projected that we would have 5 last mile providers receiving new access and we have surpassed our projection. | We projected we would have 1 last mile provider receiving improved access and have surpassed our projection. | We projected we would have 1 last mile provider receiving access to dark fiber, but all providers have requested new or improved access instead. | 1 customer is receiving a 10 meg circuit, 1 customer is receiving a 20 meg circuit, 2 customers are receiving 100 megs, 1 customer is receiving multiple 100 meg and 200 meg circuits, 1 customer is receiving 2 500 meg circuits, 3 customers are receiving 1 gig, and 1 customer is receiving 4 gigs. The other tiers are 50 megs and 10 gigs. | 12 | 0 | 12 | 8 | The variance in CAI counts is due to the environmental assessments taking longer than expected and fiber procurement delays. | The variance in CAI counts is due to the environmental assessments taking longer than expected and fiber procurement delays. | The variance in CAI counts is due to the environmental assessments taking longer than expected and fiber procurement delays. | 8 CAIs are receiving 100 megs, 1 CAI is receiving 70 megs, 1 CAI is receiving 50 megs, 1 CAI is receiving 20 megs, 1 CAI is receiving 10 megs. We are also offering 500 megs, 1 gig, and 10 gig tiers. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Next quarter we expect to complete another 91.5 miles, including a run from Mt Pleasant to Paris with construction underway to Roxton and Bonham. Design work on the last phase should be complete with plans to start at both ends simultaneously in order to complete the project on time if there are no additional delays due to environmental assessment approvals. We have several last mile providers and one community anchor institution scheduled to go live October 1. In all, we have 2 last mile provider contracts and 7 community anchor contracts we expect to be signed by the end of the quarter. We plan to connect 4 community anchor institutions during the fourth quarter of 2012. | Peoples Telephone Cooperative Inc. | Additional route modifications have again necessitated environment assessments and the associated delays in approval have proven to be a challenge to our project. We have also experienced delays gaining easements or franchises in several cities which has delayed our progress, although not significantly so far. Approval of the current series of environmental assessments is the only thing that could delay the timely completion of this project. | Additional route modifications have again necessitated environment assessments and the associated delays in approval have proven to be a challenge to our project. We have also experienced delays gaining easements or franchises in several cities which has delayed our progress, although not significantly so far. Approval of the current series of environmental assessments is the only thing that could delay the timely completion of this project. | TRUE
NT10BIX5570131 | 2012 | Q4 | Q4 - 2012 | Phase 1 is closed out. Completion of Phase 2 should be accomplished in the first quarter of 2013. The third and final phase is under construction. Completion is dependent on timely approval of the environmental assessment recently filed. We continue to have one-on-one meetings with economic development units, city managers, elected officials, representatives from educational institutions, and business-people from all walks of life. | 321 | 0 | 0 | 0 | 321 | 0 | 0 | 0 | 321 miles have been placed and deployed. Fiber delivery delay caused variance as well as delay of environmental assessment approvals. We expect to be close to target by second quarter, 2013. | No variance. | No variance. | No variance. | 321 miles have been placed and deployed. Fiber delivery delay caused variance as well as delay of environmental assessment approvals. We expect to be close to target by second quarter, 2013. | No variance. | No variance. | No variance. | 15 | 1 | 12 | The last mile providers with whom we have signed agreements are: The Cyber Shop, ETEX Telephone, Cumby Telephone, Franklin County Wireless/Mt Vernon Optic Herald, ConNEXTions Telcom, Peoples Communication, Inc., Trillion Partners, Down-to-Earth Broadband, CoStreet/Verizon, Skynet, Starnet, Peoples Wireless, Northeast Texas Broadband, CPI Scott McGriff, and LTE Coop. All agreements are for services sold by Peoples Telephone, not for those purchased. Of the 15 signed agreements, 12 providers are receiving service as of 12/31/2012. | We are providing 10 Megs to 4 Gig services to 10 providers. They are using them to provide WiFi internet services, to provide DSL services to their existing customers, or to access a second connection point for their network to provide redundancy. | None. | 6 | 6 | 0 | 9 | We projected that we would have 5 last mile providers receiving new access and we have surpassed our projection. | We projected that we would have 1 last mile providers receiving improved access and we have surpassed our projection. | We projected we would have 1 last mile provider receiving access to dark fiber, but all providers have requested new or improved access instead. | 1 customer is receiving a 10 meg circuit, 1 customer is receiving a 20 meg circuit, 1 customer is receiving a 25 Meg circuit, 3 customers are receiving 100 megs, 1 customer is receiving multiple 100 meg and 200 meg circuits, 1 customer is receiving multiple 500 meg and 1 Gig circuits, 3 customers are receiving 1 gig, and 1 customer is receiving 4 gigs. The other tiers are 50 megs and 10 gigs. | 14 | 0 | 14 | 8 | The variance in CAI counts is due to the environmental assessments taking longer than expected and fiber procurement delays. | The variance in CAI counts is due to the environmental assessments taking longer than expected and fiber procurement delays. | The variance in CAI counts is due to the environmental assessments taking longer than expected and fiber procurement delays. | 8 CAIs are receiving 100 megs, 1 CAI is receiving 70 megs, 1 CAI is receiving 50 megs, 1 CAI is receiving 20 megs, 1 CAI is receiving 10 megs. We are also offering 500 megs, 1 gig, and 10 gig tiers. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Next quarter we expect to complete a great deal of Phases 3A and 3B, and officially close-out Phase 2, a total of approximately 103 miles. We have several more tower sites and five CAIs scheduled to connect this quarter. We expect to sign one more wholesale/last mile provider next quarter. | Peoples Telephone Cooperative Inc. | Additional route modifications have again necessitated environment assessments and the associated delays in approval have proven to be a challenge to our project. We have also experienced delays gaining easements or franchises in several cities which has delayed our progress. Approval of the current series of environmental assessments is the only thing that could delay the timely completion of this project. | Additional route modifications have again necessitated environmental assessments and the associated delays in approval have proven to be a challenge to our project. We have also experienced delays gaining easements or franchises in several cities which has delayed our progress. Approval of the current series of environmental assessments is the only thing that could delay the timely completion of this project. | TRUE
NT10BIX5570131 | 2013 | Q1 | Q1 - 2013 | Phase 1 is closed out. Phase 2 is complete but not closed out. The third and final phase is under construction. Completion is dependent on timely approval of the final environmental assessment that will be filed during the second quarter, 2013. We continue to have one-on-one meetings with economic development units, city managers, elected officials, representatives from educational institutions, and business-people from all walks of life. | 428 | 0 | 0 | 0 | 428 | 0 | 0 | 0 | 428 miles have been placed and deployed. Fiber delivery delay caused variance as well as delay of environmental assessment approvals. We anticipate filing for an extension and completing the project by the end of third quarter, 2013. | No variance. | No variance. | No variance. | 428 miles have been placed and deployed. Fiber delivery delay caused variance as well as delay of environmental assessment approvals. | No variance. | No variance. | No variance. | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | We are providing 10 Megs to 4 Gig services to 10 providers. They are using them to provide WiFi internet services, to provide DSL services to their existing customers, or to access a second connection point for their network to provide redundancy. | None. | 10 | 5 | 0 | 9 | We projected that we would have 6 last mile providers receiving new access and we have surpassed our projection. | We projected that we would have 1 last mile providers receiving improved access and we have surpassed our projection. | We projected we would have 1 last mile provider receiving access to dark fiber, but all providers have requested new or improved access instead. | 1 customer is receiving a 10 meg circuit, 1 customer is receiving a 20 meg circuit, 1 customer is receiving a 25 meg circuit, 2 customer are receiving 30 meg circuits, 3 customers are receiving 100 megs, 1 customer is receiving multiple 100 meg and 200 meg circuits, 1 customer is receiving multiple 500 meg and 1 Gig circuits, 4 customers are receiving 1 gig, and 1 customer is receiving 4 gigs. The other tiers are 50 megs and 10 gigs. | 16 | 1 | 15 | 8 | The variance in CAI counts is due to the environmental assessments taking longer than expected and fiber procurement delays. | The variance in CAI counts is due to the environmental assessments taking longer than expected and fiber procurement delays. | The variance in CAI counts is due to the environmental assessments taking longer than expected and fiber procurement delays. | 1 CAI is receiving 250 megs, 10 CAIs are receiving 100 megs, 1 CAI is receiving 50 megs, 2 CAIs are receiving 20 megs, 2 CAIs are receiving 10 megs. We are also offering 500 megs, 1 gig, and 10 gig tiers. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Next quarter we expect to complete a great deal of Phases 3A and 3B, and officially close-out Phase 2. We plan to construct a total of 142 miles. We expect to sign one more wholesale/last mile provider and connect 7 more CAIs next quarter. | Peoples Telephone Cooperative Inc. | Additional route modifications have again necessitated environmental assessments and the associated delays in approval have proven to be a challenge to our project. We have also experienced delays gaining easements or franchises in several cities which has delayed our progress. Approval of the final environmental assessment being submitted during the second quarter of 2013 could significantly delay the timely completion of this project beyond third quarter, 2013. | Additional route modifications will be requested in April and the associated delays in past approvals have proven to be a challenge to our project. We have also experienced delays gaining easements or franchises in several cities which has delayed our progress. Delayed approval of the second quarter, 2013 route modification could delay the timely completion of this project. Community Anchor Institution information will be updated for second quarter, 2013 PPR to show fiber to demarcation rather than CAIs that have been billed. | TRUE
NT10BIX5570131 | 2013 | Q2 | Q2 - 2013 | Phase 1 is closed out. Phase 2 is closed out. The third and final phase is under construction and should be completed by the end of third quarter. We continue to have one-on-one meetings with economic development units, city managers, elected officials, representatives from educational institutions, and business-people from all walks of life. We added 141 CAIs during 2nd quarter and we have 32 more scheduled during 3rd quarter to reach our revised goal of 189 CAIs. We have constructed 97 new miles during 2nd quarter which has brought us within 13 miles of reaching our revised goal of 538. We plan to sign and connect one more last mile provider during 3rd quarter, doubling our original goal of 8. | 525 | 0 | 0 | 0 | 525 | 0 | 0 | 0 | 525 new miles have been constructed. Fiber delivery delay caused variance as well as delay of environmental assessment approvals. We anticipate completing the project by the end of third quarter, 2013. | No variance. | No variance. | No variance. | 525 new miles have been constructed. Fiber delivery delay caused variance as well as delay of environmental assessment approvals. | No variance. | No variance. | No variance. | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | We are providing 10 Meg to 4 Gig services to 14 providers, as one provider disconnected their service during the 2nd quarter 2013. They are using them to provide WiFi internet services, to provide DSL/Broadband services to their existing customers, or to access a second connection point for their network to provide redundancy. | None. | 9 | 5 | 0 | 9 | We projected that we would have 7 last mile providers receiving new access and we have surpassed our projection. One provider disconnected their service during 2nd quarter 2013 so we are providing service to one less provider than we were 1st quarter. | We projected that we would have 1 last mile providers receiving improved access and we have surpassed our projection. | We projected we would have 1 last mile provider receiving access to dark fiber, but all providers have requested new or improved access instead. | 1 customer is receiving a 25 meg circuit, 2 customer are receiving 30 meg circuits, 4 customers are receiving 100 megs, 1 customer is receiving multiple 100 meg and 200 meg circuits, 1 customer is receiving multiple 500 meg and 1 Gig circuits, 4 customers are receiving 1 gig, and 1 customer is receiving 4 gigs. The other tiers are 10 megs, 20 megs, 50 megs and 10 gigs. | 157 | 142 | 15 | 8 | The variance in CAI counts is due to the environmental assessments taking longer than expected and fiber procurement delays. | The variance in CAI counts is due to the environmental assessments taking longer than expected and fiber procurement delays. | The variance in CAI counts is due to the environmental assessments taking longer than expected and fiber procurement delays. | 1 CAI is receiving 250 megs, 11 CAIs are receiving 100 megs, 2 CAI is receiving 50 megs, 2 CAIs are receiving 20 megs, 3 CAIs are receiving 10 megs. We are also offering 500 megs, 1 gig, and 10 gig tiers. The remaining CAIs are built to demarcation point but are not being served at this time. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Next quarter we expect to complete the remainder of Phases 3A and 3B. We plan to construct a total of 13 miles. We expect to connect 32 more CAIs next quarter. We plan to sign and connect one more last mile provider during 3rd quarter 2013. With these figures we will reach our revised goals and double the number of last mile providers we anticipated connecting. | Peoples Telephone Cooperative Inc. | Additional route modifications have again necessitated environmental assessments and the associated delays in approval have proven to be a challenge to our project. We have also experienced delays gaining easements or franchises in several cities which has delayed our progress. | Additional route modifications were requested in April and the associated approval was received late July which proved to be a challenge to our project. We have also experienced delays gaining easements or franchises in several cities which has delayed our progress. Delayed approval of the second quarter, 2013 route modification delayed the timely completion of this project. Community Anchor Institution information has been updated for second quarter, 2013 PPR to show fiber to demarcation rather than CAIs that have been billed. | TRUE
NT10BIX5570131 | 2013 | Q3 | Q3 - 2013 | All phases were constructed and closed out as of the third quarter of 2013. We continue to have one-on-one meetings with economic development units, city managers, elected officials, representatives from educational institutions, and business-people from all walks of life. We added connections to 10 Community Anchor Institutions during 3rd quarter. We constructed 601 miles of fiber during this project, bringing greatly needed broadband connectivity to many East Texas communities. Overall, we have added broadband to or increased the broadband speeds of 51 communities and increased the number of broadband providers in our area to encourage competition. Building to last mile providers also increased access to and current speeds of countless other communities as we also provide access to lower cost bandwidth for these carriers. We built fiber to downtown Canton, Texas, to provide much needed high speed broadband to First Monday Trades Day which draws thousands of people nationwide one weekend a month and provides a lifeline of tax revenue to the community as a whole. A total of 24 jobs were created to build and sustain this project. Our future plans include developing the area's medical network to allow telemedicine in rural areas that desperately need it. | 601 | 30 | 0 | 0 | 601 | 0 | 0 | 0 | 601 new miles have been constructed. Fiber delivery delay and delay of environmental assessment approvals caused variance from baseline projections. The extension request and all prior PPRs based mileage on duct miles placed from Form 521 weekly progress reports submitted by field construction personnel. The weekly reports are not necessarily absolute and are not final unit tabulations. The total reflected on this PPR shows definitive final spliced & lit mileage including EA approved laterals and drops derived from actual "as constructed" unit tabulations. Additional construction was also possible due to favorable weather conditions during the 3rd quarter months. | A neighboring rural telephone company had capacity along some of our proposed routes. We surmised it was more feasible and a better use of BTOP funds to lease capacity along these routes rather than overbuild existing routes. The other telephone company was amenable to a lease arrangement and readily agreed to lease fiber optic cable along our proposed routes. No ground disturbance ensued. | No variance. | No variance. | 601 new miles have been constructed. Fiber delivery delay and delay of environmental assessment approvals caused variance from baseline projections. The extension request and all prior PPRs based mileage on duct miles placed from Form 521 weekly progress reports submitted by field construction personnel. The weekly reports are not necessarily absolute and are not final unit tabulations. The total reflected on this PPR shows definitive final spliced & lit mileage including EA approved laterals and drops derived from actual "as constructed" unit tabulations. Additional construction was also possible due to favorable weather conditions during the 3rd quarter months. | No variance. | No variance. | No variance. | [REDACTED] | [REDACTED] | [REDACTED] | [REDACTED] | We are providing 10 Meg to 4 Gig services to 14 providers, as one provider disconnected their service during the 2nd quarter 2013. They are using them to provide WiFi internet services, to provide DSL/Broadband services to their existing customers, or to access a second connection point for their network to provide redundancy. | None. | 9 | 5 | 0 | 9 | We projected that we would have 7 last mile providers receiving new access and we have surpassed our projection. One provider disconnected their service during 2nd quarter 2013 so we are providing service to one less provider than we were 1st quarter. | We projected that we would have 1 last mile providers receiving improved access and we have surpassed our projection. | We projected we would have 1 last mile provider receiving access to dark fiber, but all providers have requested new or improved access instead. | 1 customer is receiving a 25 meg circuit, 2 customer are receiving 30 meg circuits, 4 customers are receiving 100 megs, 1 customer is receiving multiple 100 meg and 200 meg circuits, 1 customer is receiving multiple 500 meg and 1 Gig circuits, 4 customers are receiving 1 gig, and 1 customer is receiving 4 gigs. The other tiers are 10 megs, 20 megs, 50 megs and 10 gigs. | 209 | 96 | 113 | 8 | We originally projected we would have 226 CAIs receiving access but revised our projection to 189 with our first extension request and the subsequent AARs adding and deleting CAIs. The variance in CAI counts from the baseline is due to the environmental assessments taking longer than expected and fiber procurement delays. The variance in CAI counts served was caused by substantial delays gaining easements or franchises in several cities which greatly delayed our progress. One city in particular had 7 CAIs along our proposed route and refused to allow us access to their right-of-way. We made arrangements with a wireless broadband last mile provider to build fiber to their tower to serve the CAIs but we could not serve them directly with fiber optic cable. CAIs are being served through last mile providers receiving access through our fiber, thus, they cannot be listed as served and it impacts our CAI count. We have been diligent about finding and approaching more CAIs than we originally identified, thus the addition of 20 above our revised projection making our final CAI count 209. All additional CAIs were in EA-approved areas. | We originally projected we would have 191 CAIs receiving new access but revised our projection to 155. The variance in CAI counts is due to delays gaining easements or franchises in several cities which has delayed our progress. | We originally projected we would have 35 CAIs receiving improved access but revised our projection to 34. The variance in CAI counts is due to delays gaining easements or franchises in several cities which has delayed our progress. | 1 CAI is receiving 250 megs, 17 CAIs are receiving 100 megs, 2 CAI is receiving 50 megs, 4 CAIs are receiving 20 megs, 10 CAIs are receiving 10 megs. We are also offering 500 megs, 1 gig, and 10 gig tiers. The remaining CAIs are built to demarcation point but are not being served at this time. | 0 | 0 | 0 | 0 | 0 | No variance. | No variance. | No variance. | No variance. | No variance. | 0 | 0 | 0 | 0 | 0 | No variance. | No variance. | No variance. | No variance. | No variance. | N/A | FALSE | N/A | The award has ended and all activities moving forward will be completed outside of the BTOP project. We plan to connect any community anchor institutions and last mile provider sites that have been built to but not connected. We also plan to continue reaching out to communities where access has been hindered by local governmental entities, by way of agreements with those local entities or through last mile providers. | Peoples Telephone Cooperative Inc. | Additional route modifications have again necessitated environmental assessments and the associated delays in approval have proven to be a challenge to our project. We have also experienced delays gaining easements or franchises in several cities which has delayed our progress and greatly impacted the number of CAIs we expected to connect directly to our fiber network. | We are also still encountering local governments that are hindering access to anchor institutions within their localities. We continue to reach out to these entities and are working to overcome these obstacles. | TRUE
NT10BIX5570132 | 2010 | Q4 | Q4 - 2010 | Environmental work and the network design are proceeding on schedule. The draft environmental assessment was submitted to NTIA's environmental division on January 17th. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnect point; Local Access Services which are typically Ethernet services from the local Interconnect point to the anchor institution, Dedicated Internet Access services and Long Distance Access services. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | DS1 - 0, DS3 - 0, OC12 - 0, 100Mb - 0, 1Gb - 0, 2.5Gb - 0, 10Gb - 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10Mb - 0, 15Mb - 0, 20Mb - 0, 30Mb - 0, 40Mb - 0, 50Mb - 0, 100Mb - 0, 1Gb - 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Completion of the environmental assessment and issuance of the FONSI by NTIA. Finalize network design and staking. Begin preparation of an RFP for the outside plant portion of the project. Begin the process of obtaining rights of way and construction permits for locations construction will take place. | E.N.M.R. Telephone Cooperative | Nothing to report. | Based on the progress of our Round 1 project we have some concern about the amount of time it will take to complete the environmental requirements. ENMR-Plateau's environmental consultants did submit the draft EA before the deadline, however what concerns us is the time taken by all the agencies that are involved to come to an agreement on the findings and provide approvals to proceed. | TRUE
NT10BIX5570132 | 2011 | Q1 | Q1 - 2011 | Completed draft Environmental Assessment and submitted to NTIA. Continued work on network design and staking, rights of way and construction permits. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution; Dedicated Internet Access services and Long Distance Access services. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | DS1 - 0, DS3 - 0, OC12 - 0, 100Mb - 0, 1GB - 0, 2.5Gb - 0, 10Gb - 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10Mb - 0, 15Mb - 0, 20Mb - 0, 30Mb - 0, 40Mb - 0, 50Mb - 0, 100Mb - 0, 1Gb - 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Completion of Environmental Assessment and issuance of the FONSI. Begin contract negotiations for equipment procurement and preparing outside plant construction RFP's. Finalize network design and continue work on rights of way and construction permits. | E.N.M.R. Telephone Cooperative | Completion of the Environmental Assessment is taking longer than expected, however we hope to have the FONSI issued by the end of April. We are waiting for the environmental requirements to be complete prior to purchasing any equipment and finalizing the RFP for outside plant construction. | Procurement of equipment and outside plant construction has been pushed back. We do not anticipate spending any funds by 6/30 on either equipment or construction due to the amount of time needed for contract negotiations, planning, and invoicing that must take place after the issuance of the FONSI. We anticipate getting back on schedule once the FONSI has been issued and we are able to begin procuring equipment and outside plant construction. | TRUE
NT10BIX5570132 | 2011 | Q2 | Q2 - 2011 | Environmental assessment completed and FONSI issued by NTIA. Network design finalized and outside plant construction RFP being completed and expected to be sent out to bid early next quarter. Finalizing contract negotiations with equipment vendors and preparing for procurement. Continuing work on rights of way, construction permits and franchise agreements. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution; Dedicated Internet Access services and Long Distance Access services. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | DS1 - 0, DS3 - 0, OC12 - 0, 100Mb - 0, 1GB - 0, 2.5Gb - 0, 10Gb - 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10Mb - 0, 15Mb - 0, 20Mb - 0, 30Mb - 0, 40Mb - 0, 50Mb - 0, 100Mb - 0, 1Gb - 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Begin outside plant construction, equipment procurement and deployment. | E.N.M.R. Telephone Cooperative | The project schedule has been pushed back based on the amount of time experienced in completing the environmental requirements that allow us to proceed with construction. Now that the FONSI has been issued we are moving forward with outside plant construction bids and expect to have vendor selection and construction started by the fourth quarter of this year. Additionally equipment procurement and deployment expected to begin next quarter. ENMR-Plateau will be working to catch up to projected milestones reflected in the Baseline Report related to Equipment Procurement and Deployment and Network Build. We've placed equipment procurement and deployment on hold until the bid responses for outside plant construction are obtained. We are concerned with potential issues related to fiber optic cabling availability and what effects it may have on both our project budget and schedule. Once that is determined, and if no issues are found, we will be able to move forward with procuring the equipment and having it installed at a very quick rate. We are confident in this due to the results we've seen in our Round 1 project and how quickly the vendor is able to deliver and install the equipment related to that project. Once bids have been received for outside plant construction and a contractor has been awarded we plan to evaluate any potential issues with the availability of fiber optic cabling. If no issues exist we will review the contractors proposed construction schedule to determine t | Procurement of equipment and outside plant construction was pushed back due to the amount of time needed to complete the environmental requirements and receive the FONSI. Now that the environmental requirements have been met we have been finalizing contract negotiations with vendors and will begin equipment procurement in the last part of this quarter. Also bid packages have been sent out to a number of outside plant contractors requesting bids on our Round 2 project. Responses are due on 8/12. We expect to have the responses evaluated and the contract awarded by the end of August with construction beginning approximately 30 to 45 days after that. Since we are billed by the contractor in arrears we would not be invoiced until October or November for work completed in September, which is why no dollars have been reflected as spent for "Network Build" in this next quarter. At this point we are waiting for the responses from the outside plant contractors to determine the availability of fiber optic cable and what kind of impact that may have on our schedule. Once we have that information we will be able to formulate a plan to increase our efforts to catch up to the projected milestones reflected in the Baseline Report. Additionally the budget for "Land, Structures, Rights-of-Way, Appraisals, etc." includes $255,000 for the construction of buildings. No costs were budgeted for the acquisition of rights-of-way in the original application,so we are assuming those costs out of pocke | TRUE
NT10BIX5570132 | 2011 | Q3 | Q3 - 2011 | Outside plant construction contractor selected. Construction began on October 10th. Procurement of DWDM equipment under way and installation to begin in November. Proceeding with rights of way, permitting, and site acquisition. Engineers completing design and specifications for new central office buildings; expect to submit RFP's to buildings contractors in Quarter 4. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Construction and equipment deployment have not started. | Construction and equipment deployment have not started. | Construction and equipment deployment have not started. | Construction and equipment deployment have not started. | Construction and equipment deployment have not started. | N/A | N/A | Construction and equipment deployment have not started. | 0 | 0 | 0 | N/A | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution; Dedicated Internet Access services and Long Distance Access services. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10Mb - 0, 15Mb - 0, 20Mb - 0, 30Mb - 0, 40Mb - 0, 50Mb - 0, 100Mb - 0, 1Gb - 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Continue outside plant construction, procurement of network equipment and begin installation. Select vendor for central office building construction. Continue rights of way and permit acquisition; no impact to schedule expected. Planning to place 30 miles of conduit and 5 miles of fiber. No new network miles are expected to be leased next quarter. No CAI subscribers are expected to be served next quarter; the construction and equipment deployment in the services areas will have to be completed prior to being able to serve anchors. No new signed agreements with broadband wholesalers or last mile providers are expected next quarter. | E.N.M.R. Telephone Cooperative | The project schedule was pushed back due to the amount of time needed to complete the environmental requirements and receive the FONSI from NTIA. Now that the environmental requirements are complete construction and equipment procurement and implementation has begun. Based on the speed and efficiency that the outside plant construction contractor and the equipment installers have displayed in our Round I project, we are confident that we will be able to catch up to projected milestones in subsequent quarters and meet the targets of 66% complete by the end of year 2 and 100% complete by the end of year 3. | The project schedule has been pushed back based on the amount of time experienced in completing the environmental requirements that allow us to proceed with construction. Now that the FONSI has been issued and the outside plant construction contractor has been selected we have begun construction in the fourth quarter of this year. Additionally, as of October the equipment procurement and deployment has begun. ENMR-Plateau will be working diligently to catch up to projected milestones reflected in the Baseline Report related to Equipment Procurement and Deployment and Network Build. We are concerned with potential issues related to fiber optic cabling availability and what effects it may have on both our project budget and schedule; however this concern should be addressed around March or April when the fiber is expected to be delivered. We are confident in the speed and efficiency of both the outside plant construction contractor along with the equipment installers based on the progress that has been reflected in our round I project. We believe that increased efforts on the part of the contractors will allow us to catch up to milestone projections. We are optimistic that we will be able to catch up to the projected milestones reflected in the Baseline Report in subsequent quarters. | TRUE
NT10BIX5570132 | 2011 | Q4 | Q4 - 2011 | Construction of outside plant facilities began. Equipment procurement and installation began. Acquisition of rights of way, permitting and central office building sites proceeding. RFP's for building contractors sent out for bid; expect to select contractor in Q1 2012. | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | Construction is ramping up and proceeding quickly. We anticipate catching up to baseline estimates in subsequent quarters. | No new network leases have been implemented at this point. | No existing network miles have been upgraded at this point. | N/A | New network miles deployed plus new network miles leased. | N/A | N/A | Additional interconnection points will be activated in subsequent quarters as equipment is deployed and activated in other loations. We anticipate catching up to baseline estimates in subsequent quarters. | 0 | 0 | 0 | N/A | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution; Dedicated Internet Access services and Long Distance Access services. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10Mb - 0, 15Mb - 0, 20Mb - 0, 30Mb - 0, 40Mb - 0, 50Mb - 0, 100Mb - 0, 1Gb - 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Continue outside plant construction, procurement of network equipment and installation. Begin construction on CO building locations. Continue rights of way and permit acquisition; no impact to project schedule. No new network miles are expected to be leased. No CAI subscribers are expected to be served next quarter; the construction and equipment deployment in the service areas will have to be completed prior to being able to serve anchors. No new signed agreements with broadband wholesalers or last mile providers are expected next quarter. | E.N.M.R. Telephone Cooperative | The project schedule was pushed back due to the amount of time needed to complete the environmental requirements and receive the FONSI from NTIA. Now that the environmental requirements are complete, construction and equipment procurement and implementation have begun. Based on the speed and efficiency that the outside plant construction contractor and the equipment installers have displayed in our Round I project, we are optimistic that we will be able to catch up to projected milestones in subsequent quarters and meet the target of 67% completion by the end of Year 2 and 100% completion by the end of Year 3. | The project schedule has been pushed back based on the amount of time experienced in completing the environmental requirements that allow us to proceed with construction. Now that the FONSI has been issued and the outside plant construction contractor has been selected we have begun construction on October 10th of 2011. Additionally, as of October the equipment procurement and deployment has begun. ENMR-Plateau will be working diligently to catch up to projected milestones reflected in the baseline report related to equipment procurement and deployment and network build. We are still somewhat concerned about potential issues related to fiber optic cabling availability and what effects it may have on both our project budget and schedule; however this concern should be addressed in the March/April time frame when the fiber is expected to be delivered. We are confident in the speed and efficiency of both the outside plant construction contractor along with the equipment installers based on the progress that has been reflected in our Round I project. We believe that increased efforts on the part of the contractors will allow us to catch up to milestone projections included in our baseline report. We are optimistic that we will be able to catch up to the projected milestones reflected in the baseline report in subsequent quarters. | TRUE
NT10BIX5570132 | 2012 | Q1 | Q1 - 2012 | Outside plant construction, procurement and installation continues. CO buildings have been ordered and are expected to be installed next quarter. | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | Currently conduit is being placed until fiber is received. Once fiber is received the contractor will place it within the conduit, which will allow us to report more new network miles deployed. | No new network leases have been implemented at this point. | No existing network miles have been upgraded at this point. | N/A | New network miles deployed plus new network miles leased. | N/A | N/A | Additional interconnection points will be activated in subsequent quarters as equipment is deployed and activated in other locations. We anticipate catching up to baseline estimates in subsequent quarters. | 0 | 0 | 0 | N/A | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution; Dedicated Internet Access and Long Distance Access services. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Continue outside plant construction, procurement of network equipment and installation. Complete construction of CO building locations. Finalize rights of way and permit acquisition; no impact to project schedule. No new network miles are expected to be leased. No CAI subscribers are expected to be served next quarter; the construction and equipment deployment in the service areas will have to be completed prior to being able to serve anchors. No new signed agreements with broadband wholesalers or last mile providers are expected next quarter. Estimating to construct 47 miles of duct and pull 22.75 miles of fiber next quarter. | E.N.M.R. Telephone Cooperative | The project schedule was pushed back due to the amount of time needed to complete the environmental requirements and receive the FONSI from NTIA. Now that the environmental requirements are complete, construction and equipment procurement and deployment have begun. Based on the speed and efficiency that the outside plant construction contractor and the equipment installers have displayed in our Round I project, we are optimistic that we will be able to catch up to projected milestones in subsequent quarters and meet the target of 67% completion by the end of Year 2 and 100% completion by the end of Year 3. | The project schedule has been pushed back based on the amount of time experienced in completing the environmental requirements that allow us to proceed with construction. Now that the FONSI has been issued and the outside plant construction contractor has been selected we have begun construction on October 10th of 2011. Additionally, as of October the equipment procurement and deployment has begun. ENMR-Plateau will be working diligently to catch up to projected milestones reflected in the baseline report related to equipment procurement and deployment and network build. We are still somewhat concerned about potential issues related to fiber optic cabling availability and what effects it may have on both our project budget and schedule; however this concern should be addressed in the Q2 2012 time frame when the fiber is expected to be delivered. We are confident in the speed and efficiency of both the outside plant construction contractor along with the equipment installers based on the progress that has been reflected in our Round I project. We believe that increased efforts on the part of the contractors will allow us to catch up to milestone projections included in our baseline report. We are optimistic that we will be able to catch up to the projected milestones reflected in the baseline report in subsequent quarters. | TRUE
NT10BIX5570132 | 2012 | Q2 | Q2 - 2012 | Outside plant fiber construction, equipment procurement and installation continues. Central office buildings and auxiliary equipment construction has been completed and awaiting final inspection and approval. Conducting community outreach and contacting anchor institutions. | 29 | 0 | 0 | 0 | 29 | 0 | 0 | 1 | Fiber is being placed as it is received. | No new network leases have been implemented. | No existing network miles have been upgraded at this point. | N/A | New network miles deployed plus new network miles leased. | N/A | N/A | Additional interconnection points will be activated in subsequent quarters as fiber construction is completed and equipment is deployed and activated in other locations. Several locations have been installed, but are waiting for fiber construction before they are ready to turn up and carry traffic. We anticipate catching up to baseline estimates in subsequent quarters. | 0 | 0 | 0 | N/A | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution; Dedicated Internet Access and Long Distance Access services. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Continue outside plant construction, procurement of network equipment and installation. Finalize rights of way and permit acquisition; no impact to project schedule. ENMR expects to construct an additional 15 miles of underground conduit and pull 50 miles of fiber optic cable in the next quarter. No new network miles are expected to be leased. No CAI subscribers are expected to be served next quarter; the construction and equipment deployment in the service areas will have to be completed prior to being able to serve anchors. No new signed agreements with broadband wholesalers or last mile providers are expected next quarter. | E.N.M.R. Telephone Cooperative | The project schedule was pushed back due to the amount of time needed to complete the environmental requirements and receive the FONSI from NTIA. Now that the environmental requirements are complete, construction and equipment procurement and deployment have begun. Based on the speed and efficiency that the outside plant construction contractor and the equipment installers have displayed in our Round I project, we are optimistic that we will be able to catch up to projected milestones in subsequent quarters and 100% completion by the end of Year 3. | The project schedule has been pushed back based on the amount of time experienced in completing the environmental requirements that allow us to proceed with construction. Now that the FONSI has been issued and the outside plant construction contractor has been selected we have begun construction on October 10th of 2011. Additionally, as of October the equipment procurement and deployment has begun. ENMR-Plateau will be working diligently to catch up to projected milestones reflected in the baseline report related to equipment procurement and deployment and network build. We have experienced issues related to fiber optic cabling availability and its effects on our project schedule. The majority of the fiber optic cable has been received and is in the process of being installed by the contractor. We are confident in the speed and efficiency of both the outside plant construction contractor along with the equipment installers based on the progress that has been reflected in our Round I project. We believe that increased efforts on the part of the contractors will allow us to catch up to milestone projections included in our baseline report. We are optimistic that we will be able to catch up to the projected milestones reflected in the baseline report in subsequent quarters. | TRUE
NT10BIX5570132 | 2012 | Q3 | Q3 - 2012 | Outside plant fiber construction, equipment procurement and installation continues. Central office buildings and auxiliary equipment construction has been completed, inspected and approved. Continuing community outreach efforts and contacting anchor institutions. | 81 | 0 | 0 | 0 | 81 | 0 | 0 | 5 | As of the end of the quarter the outside plant construction contractor has buried approximately 140 miles of underground duct, placed 81 miles fiber optic cabling and conducted 2,200 splices. The fiber miles that have been reported are less than the underground duct miles due to experiencing a long wait for the fiber optic cable, which was finally received from the manufacturer around the June/July time frame. Based on the efficiency of the outside plant construction contractor we expect to catch up to baseline estimates for new network miles deployed in subsequent quarters. | No new network miles have been implemented. | No new network miles have been upgraded at this point. | N/A | New network miles deployed plus new network miles leased. | N/A | N/A | Additional interconnection points will be activated in subsequent quarters as fiber construction is completed and equipment is deployed and activated in other locations. Several locations have been installed but are waiting for fiber construction before they are ready to be turned up and carry traffic. We anticipate catching up to baseline estimates in subsequent quarters. | 1 | 1 | 4 | Conterra Ultra Broadband, LLC | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution; Dedicated Internet Access and Long Distance Access service. | N/A | 1 | 0 | 0 | 1 | There is 1 provider currently receiving new access from ENMR-Plateau's core middle mile network. | N/A | N/A | 100Mb - 0, 1Gb - 0, 2.5Gb - 0, 10Gb - 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 10Mb - 0, 20Mb - 0, 50Mb - 0, 100Mb - 0, 500Mb - 0, 1Gb - 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Continue outside plant construction, procurement of network equipment and installation. ENMR expects to construct an additional 22 miles of underground conduit and place an additional 34.5 miles of fiber optic cable in the next quarter. No new network miles are expected to be leased. No CAI subscribers are expected to be served next quarter; the construction and equipment deployment in the service areas will have to be completed prior to being able to serve anchors. No new signed agreements with broadband wholesalers or last mile providers are expected next quarter. | E.N.M.R. Telephone Cooperative | The project schedule was pushed back due to the amount of time needed to complete the environmental requirements and receive the FONSI from NTIA. Now that the environmental requirements are complete, construction and equipment procurement and deployment have begun. Based on the speed and efficiency that the outside plant construction contractor and the equipment installers have displayed in our Round I project, we are optimistic that we will be able to catch up to projected milestones in subsequent quarters and 100% completion by the end of Year 3. | The project schedule has been pushed back based on the amount of time experienced in completing the environmental requirements that allow us to proceed with construction. Now that the FONSI has been issued and the outside plant construction contractor has been selected we have begun construction as of October 10, 2011. Additionally, as of October the equipment procurement and deployment has begun. ENMR-Plateau will be working diligently to catch up to projected milestones reflected in the baseline report related to equipment procurement and deployment and network build. We have experience issues related to fiber optic cabling availability and its effects on our project schedule. The majority of the fiber optic cable has been received and is in the process of being installed by the contractor. We are confident in the speed and efficiency of both the outside plant construction contractor along with the equipment installers based on the progress that has been reflected in our Round I project. We believe that increased efforts on the part of the contractors will allow us to catch up to milestone projections included in our baseline report. We are optimistic that we will be able to catch up to projected milestones reflected in the baseline report in subsequent quarters. | TRUE
NT10BIX5570132 | 2012 | Q4 | Q4 - 2012 | Outside plant fiber construction, equipment procurement and installation continues. Central office buildings and auxiliary equipment construction has been completed. Continuing community outreach efforts and contacting anchor institutions. | 143 | 97 | 23 | 0 | 240 | 0 | 0 | 17 | As of the end of the quarter the outside plant construction contractor has buried approximately 148 miles of underground duct and placed 143 miles of fiber optic cabling. | As of the end of the quarter ENMR has leased approximately 97 new network miles. | As of the end of the quarter ENMR has upgraded approximately 23 existing network miles. | N/A | N/A | N/A | N/A | As of the end of the quarter ENMR has added and/or upgraded 17 interconnection points. | 1 | 1 | 4 | Conterra Ultra Broadband | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution; Dedicated Internet Access and Long Distance Access services. | N/A | 1 | 0 | 0 | 1 | There is 1 provider currently receiving new access from ENMR's core middle mile network. | N/A | N/A | 50Mb - 1, 100Mb - 0, 1Gb - 0, 2.5Gb - 0, 10Gb - 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Continue outside plant construction, procurement of network equipment and installation. ENMR expects to construct an additional 8 miles of underground conduit and place an additional 10 miles of fiber optic cable in the next quarter. No new network miles are expected to be leased. No CAI subscribers are expected to be served next quarter; the construction and equipment deployment in the service areas will have to be completed prior to being able to serve anchors. ENMR expects to sign 1 new agreement with broadband wholesalers or last mile providers next quarter. | E.N.M.R. Telephone Cooperative | The project schedule was pushed back due to the amount of time needed to complete the environmental requirements and receive the FONSI from NTIA. Now that the environmental requirements are complete, construction and equipment procurement and deployment have begun. Based on the speed and efficiency that the outside plant construction contractor and the equipment installers have displayed in our Round I project, we are optimistic that we will be able to catch up to projected milestones in subsequent quarters and 100% completion by the end of Year 3. | From the beginning of the project the schedule had been pushed back based on the amount of time experienced in completing the environmental requirements that allowed ENMR to proceed with construction. The FONSI was issued and outside plant construction began on October 10, 2011 along with equipment procurement and deployment. ENMR has been working diligently in catching up to projected milestones reflected in the baseline report. ENMR had experienced issues related to fiber optic cabling availability, which also had some effects to the project schedule. ENMR is confident in the speed and efficiency of both the outside plant construction contractor and the equipment installers based on the progress that was reflected in ENMR's Round I project. ENMR is anticipating the completion of the project by the end of the grant award period of July 31, 2013. | TRUE
NT10BIX5570132 | 2013 | Q1 | Q1 - 2013 | Outside plant fiber construction, equipment procurement and installation continues. Central office buildings and auxiliary equipment construction has been completed. Continuing community outreach efforts and contacting anchor institutions. ENMR expects to be fully complete by the end of the award date of July 31, 2013. | 155 | 97 | 33 | 0 | 252 | 0 | 0 | 20 | As of the end of the quarter the outside plant construction contractor has placed approximately 155 miles of fiber optic cabling. | No variance. | As of the end of the quarter ENMR has upgraded approximately 33 existing network miles. | N/A | This represents new network miles deployed plus new network miles leased. | N/A | N/A | As of the end of the quarter ENMR has added and/or upgraded 20 interconnection points. | 2 | 0 | 4 | Conterra Ultra Broadband, Verizon Wireless | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution; Dedicated Internet Access and Long Distance Access services. | N/A | 2 | 0 | 0 | 2 | There are 2 providers currently receiving new access from ENMR's core middle mile network. | N/A | N/A | 50Mb - 1, 100Mb - 0, 1Gb - 1, 2.5Gb - 0, 10Gb - 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Continue outside plant construction, procurement of network equipment and installation. ENMR does not expect any new agreements with broadband wholesalers or last mile providers next quarter. ENMR is expecting to complete construction on 194 new network miles, lease a total of 97 new network miles, upgrade 63 exiting network miles and connect a total of 373 CAI locations by the project end date of 7/31/13. | E.N.M.R. Telephone Cooperative | The project schedule was pushed back due to the amount of time needed to complete the environmental requirements and receive the FONSI from NTIA. Now that the environmental requirements are complete, construction and equipment procurement and deployment have begun. Based on the speed and efficiency that the outside plant construction contractor and the equipment installers have displayed in our Round I project, we are optimistic that we will e able to catch up to projected milestones in subsequent quarters and 100% completion by the end of Year 3. | From the beginning of the project the schedule had been pushed back based on the amount of time experienced in completing the environmental requirements that allowed ENMR to proceed with construction. The FONSI was issued and outside plant construction began on October 10, 2011 along with equipment procurement and deployment. ENMR has been working diligently in catching up to projected milestones reflected in the baseline report. ENMR had experienced issues related to fiber optic cabling availability, which also had some effect to the project schedule. ENMR is confident in the speed and efficiency of both the outside plant construction contractor and the equipment installers based on the progress that was reflected in ENMR's Round I project. ENMR is anticipating the completion of the project by the end of the grant award period of July 31, 2013. | TRUE
NT10BIX5570132 | 2013 | Q2 | Q2 - 2013 | Outside plant fiber construction is complete. Continuing community outreach efforts and contacting anchor institutions. ENMR expects to construct a total of 185 new network miles, lease 97 new network miles and upgrade 49 existing network miles at completion of this project. ENMR intends to be fully complete by the award end date of July 31, 2013. | 185 | 97 | 49 | 0 | 282 | 0 | 0 | 20 | As a result of the approval of Modification #1 (AAR2283204) and Modification #3 (AAR2416112) new network miles were projected to total 191. Based on actual new network miles deployed of 185 there is a variance of 6 new network miles which is as a result of projected (staked) versus actual construction. | No variance. | As a result of the approval of Modification #1 (AAR2283204) which included the removal of 3 of ENMR's existing service areas from the Round II BTOP project the existing network miles upgraded estimates were affected. The 49 miles listed represents the actual fiber miles constructed for the remaining ENMR service areas that were included in the application. | N/A | Is comprised of new network miles deployed and new network miles leased. | N/A | N/A | No variance. | 4 | 0 | 12 | Conterra Ultra Broadband, Verizon Wireless, North Central NM Economic Development, Northern New Mexico Telecom, Inc. | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institution; Dedicated Internet Access and Long Distance Access services. | N/A | 4 | 0 | 0 | 4 | There are 4 providers currently receiving new access from ENMR's core middle mile network. | N/A | N/A | 50Mb - 1, 100Mb - 1, 500Mb - 1, 1Gb - 1, 2.5Gb - 0, 10Gb - 0 | 369 | 151 | 218 | 369 | Of the 402 Community Anchor Institutions located along the approved fiber routes ENMR Telephone Cooperative was able to directly connect a total of 369. | Of the directly connected CAI's a total of 151 are receiving new access to ENMR Telephone Cooperative's Round II BTOP funded network. | Of the directly connected CAI's a total of 218 are receiving improved access to ENMR Telephone Cooperative's Round II BTOP funded network. | 5Mb - 0, 10Mb - 0, 15Mb - 0, 20Mb - 0, 30Mb - 0, 40Mb - 0, 50Mb - 0, 100Mb - 0, 1Gb - 0, undetermined - 370. As of the end of the quarter ENMR Telephone Cooperative is not providing service to any CAI locations. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Completion of BTOP award. ENMR anticipates that the entire budget for the BTOP grant will be used, with no funds remaining after closeout. | E.N.M.R. Telephone Cooperative | No challenges or issues during this past quarter. ENMR Telephone Cooperative expects to be fully complete by the award end date of July 31, 2013. | No challenges or issues anticipated for next quarter. | TRUE
NT10BIX5570132 | 2013 | Q3 | Q3 - 2013 | Completion of award by end date of July 31, 2013. E.N.M.R. Telephone Cooperative completed construction of 185 new fiber network miles, connected 369 Community Anchor Institutions (151 new access and 218 improved access), and negotiated 4 new service agreements with broadband wholesalers/last mile providers. | 185 | 97 | 49 | 0 | 282 | 0 | 0 | 20 | As a result of the approval of Modification #1 (AAR2283204) and Modification #3 (AAR2416112) new network miles were projected to total 191. Based on actual new network miles deployed of 185 there is a variance of 6 new network miles which is as a result of projected (staked) versus actual construction. | No variance. | As a result of the approval of Modification #1 (AAR2283204) which included the removal of 3 of ENMR's existing service areas from the Round II BTOP project the existing network miles upgraded estimates were affected. The 49 miles listed represents the actual fiber miles constructed for the remaining ENMR service areas that were included in the application. | N/A | This amount is comprised of the sum of new network miles deployed and new network miles leased. | N/A | N/A | No variance. | 4 | 0 | 12 | Conterra Ultra Broadband, Verizon Wireless, North Central NM Economic Development, Northern New Mexico Telecom, Inc. | Long Haul Special Access Services which are typically point to point Ethernet services from Interconnection point to Interconnection point; Local Access Services which are typically Ethernet services from the local Interconnection point to the anchor institutions; Dedicated Internet Access and Long Distance Access services. | N/A | 4 | 0 | 0 | 4 | There are 4 providers currently receiving new access from ENMR's core middle mile network. | N/A | N/A | 50Mb - 1, 100Mb - 1, 500Mb - 1, 1Gb - 1, 2.5Gb - 0, 10Gb - 0 | 369 | 151 | 218 | 369 | Of the 402 Community Anchor Institutions located along the approved fiber routes ENMR Telephone Cooperative was able to directly connect a total of 369. | Of the directly connected CAI's a total of 151 are receiving new access to ENMR Telephone Cooperative's Round II BTOP funded network. | Of the directly connected CAI's a total of 218 are receiving improved access to ENMR Telephone Cooperative's Round II BTOP funded network. | 5Mb - 0, 10Mb - 0, 15Mb - 0, 20Mb - 0, 30Mb - 0, 40Mb - 0, 50Mb - 0, 100Mb - 0, 1Gb - 0, undetermined - 369. As of the end of the quarter ENMR Telephone Cooperative is not providing service to any CAI locations. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | None; project complete. | E.N.M.R. Telephone Cooperative | None. | None. | TRUE
NT10BIX5570133 | 2010 | Q3 | Q3 - 2010 | There have been two main focuses for the third quarter for ION: First has been to work diligently on wrapping up the Environmental Assessment process. The EA has been a monumental task with the project encompassing three states and the jurisdiction of many entities that needed to sign off on the construction of the project. All of these entities have signed off in Q3 and just minor adjustments to the EA remained going into Q4. We now expect that early in Q4 the EA will be approved and the FONSI issued. The second focus was completing the entity transfer, which completed as of 8/31/2010 transitioning the grant from ION HoldCo to ION NewCo. ION continues to gear up to start construction on its first two projects, Project 2 and 4b. This gearing up has included continued work on RFQ/RFP for the construction of the projects, making ongoing applications with the necessary agencies to move forward, meeting with vendors and prospective contractors. Additionally there have been continuous meetings with anchor institutions, communication with politicians and community outreach through IONâ€™s newsletter. The primary focus for the Development Authority of the North Country for Q32010, as it relates to the American Recovery and Reinvestment Act grant, was to engineer segment 6 of the project. The quarter saw many successes relative to that initiative. All GIS data for segment 6 has been captured and rendered. A quality assurance verification of the GIS data was also completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | With the completion of the Environmental Assessment we will move toward this milestone quickly. | N/A | N/A | N/A | With the completion of the Environmental Assessment we will move toward this milestone quickly. | N/A | N/A | With the completion of the Environmental Assessment we will move toward this milestone quickly. | 0 | 5 | 0 | N/A | DS-3, OC-3, OC-12, OC-48, 10Mb to 500Mb Ethernet services, GigE (1000Mb), 2.5Gb wave and 10Gb wave; provided as linear (point to point) and/or route protected circuits. (see attachment) | N/A | 0 | 0 | 0 | 0 | no variance | no variance | NA - we do not offer/provide this service | 20Mbps=0, 50Mbps=0, 100Mbps=0, 250Mbps=0, 500Mbps=0, 1Gbps=0, 2.5Gbps=0, 10Gbps=0, DS-3=0, OC-3=0, OC-12=0, OC-48=0 | 0 | 0 | 0 | 0 | no variance | no variance | no variance | 20Mbps=0, 50Mbps=0, 100Mbps=0, 250Mbps=0, 500Mbps=0, 1Gbps=0, 2.5Gbps=0, 10Gbps=0, DS-3=0, OC-3=0, OC-12=0, OC-48=0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The priority for ION with this funding will be to seek out and work with governmental, educational, and healthcare entities that need service or that can offer services to support the vision of the American Reinvestment and Recovery Act. ION is working in close collaboration with Southern Tier West, Southern Tier Central, Southern Tier East, and other development agencies where job creation is central to their mission. ION will address the needs of public safety agencies and has met with agencies to address the need for reliable, affordable and secure capacity to meet the needs of these entities. ION may provide collocation and cross connection services to 3rd party providers requiring such services. ION may provide direct Internet backbone access to anchor institutions or 3rd party service providers to resell to their customers. | FALSE | N/A | ION is planning to receive final NEPA/EA approval in the near term, while awaiting this; ION will complete staking and network design, make further progress on rights of way and construction permits, complete review of network equipment and begin procurement. During the next quarter and after EA approval ION will begin construction on three of the 10 proposed segments of the awarded project. More work will be done involving the creation of contracts with 3rd party service providers and anchor institution in preparation of network utilization. Job creation will continue during the next quarter. With the entity change and the new timeline set for the project with that change, ION will not only be able to meet its milestone timeline it will quickly be ahead of the depicted progress on the original timeline. | ION Newco Corp | ION Holdco decided early on in the grant process that for business reasons it needed to do an entity change. ION began this process in February 2010 and due to this grant truly being in its infancy stages, the processes needed to maneuver through this change were just not in place. This caused many false starts in getting through and finalizing an entity change. The entity change took until 8/31/2010 so that continued to hold us up in some regards to moving forward. Additionally, our EA has been challenging in that the project incorporates builds in 3 states. This was an ongoing focus in Q3 with many revisions being submitted to meet all requirements including recently established ones. While all of this certainly has not been easy, ION personnel has been diligent in trying to move this grant forward and thus none of these have caused a delay in the start of construction of the network. We expect to have a FONSI issued in Q4 and hope to still begin construction this year, though this will be tough with the season coming to a close. | 2.7. The entity change was approved as of August 31 20010. This has required additional work in recreating all of the necessary steps for the new entity. This includes registration in ASAP and registering in all governing Websites. We will need to act very quickly and have strong technical assistance to move through these processes quickly and efficiently so it does not affect our time line. As mentioned above, this process has slowed the transfer of grant money, but we have made strides in working through this process and hope this will no longer be an issue. Another potential issue is the availability of quality cable constructors, as this is late in the build season and many of the firms have their crews in the field working already. We believe we will be able to overcome this obstacle. | TRUE
NT10BIX5570133 | 2010 | Q4 | Q4 - 2010 | Our first priority has been to work diligently on wrapping up the Environmental Assessment process (EA). The EA has been a monumental task with the project encompassing three states and the jurisdiction of many entities that needed to sign off on the construction of the project. Due to the unanticipated delays in the EA process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. As an attempt to mitigate the issue we increased the resources toward completing the staking of the first few projects in our timetable. That effort also allows us to initiate the necessary make ready work with pole owners. The staking and make ready must be completed before construction can begin. By accelerating those steps we hope to be able to take full advantage of the next spring build period. We have continued work on RFQ/RFP (Request for Qualifications/Request for Proposal) for the construction and equipment for the projects, making ongoing applications with the necessary agencies to move forward, meeting with vendors and prospective contractors. Additionally there have been continuous meetings with anchor institutions, communication with politicians and community outreach through IONâ€™s newsletter. The primary focus for the Development Authority of the North Country for Q42010, as it relates to the American Recovery and Reinvestment Act grant, was to finalize the engineering and begin construction preparation for Proje | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Zero variance | Zero variance | Zero variance | Zero variance | Zero variance | N/A | N/A | Zero variance | 0 | 0 | 0 | N/A | N/A3 | N/A | 0 | 0 | 0 | 0 | Zero variance | Zero variance | Zero variance | Zero variance | 0 | 0 | 0 | 0 | Zero variance | Zero variance | Zero variance | Zero variance | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The priority for ION with this funding will be to seek out and work with governmental, educational, and healthcare entities that need service or that can offer services to support the vision of the American Reinvestment and Recovery Act. ION is working in close collaboration with Southern Tier West, Southern Tier Central, Southern Tier East, and other development agencies where job creation is central to their mission. ION will address the needs of public safety agencies and has met with agencies to address the need for reliable, affordable and secure capacity to meet the needs of these entities. ION may provide collocation and cross connection services to 3rd party providers requiring such services. ION may provide direct Internet backbone access to anchor institutions or 3rd party service providers to resell to their customers. | FALSE | N/A | ION is planning to receive final NEPA/EA approval in the 1Q2011. While awaiting this, ION will complete staking and network design, make further progress on rights of way and construction permits, complete review of network equipment and begin procurement. During the next quarter and after EA approval ION will begin construction on three of the 10 proposed segments of the awarded project. More work will be done involving the creation of contracts with 3rd party service providers and anchor institution in preparation of network utilization. | ION Newco Corp | The major issue we faced during the quarter was to satisfy all of the various federal and state agencies involved in our Environmental Assessment requirements. | None identified. | TRUE
NT10BIX5570133 | 2011 | Q1 | Q1 - 2011 | The major issue we faced during the quarter was to satisfy all of the various federal and state agencies involved in our Environmental Assessment requirements. ION Newco Corp. (ION) received its Findings of No Significant Impact (FONSI) for the Environmental work for the project. ION completed its wetland delineation for the Army Corp of Engineer for its projects 1 & 2 and has continued to get permits for the necessary work. ION increased the resources to continue to complete staking on the rest of the projects in our timetable. This continues to allow ION to initiate the necessary make ready work with pole owners. Which will also allow ION to complete the project on time and within the 3 year timeline. ION continues to work on each project according to our timeline, initiating RFQ/RFP (Request for Qualifications/Request for Proposals) for the construction and equipment for each project in a timely manner. ION continues to meet and market the availability of the network to prospective towns, anchor institutions, last mile providers, and government agencies in anticipation of the availability of the network. ION has had an overwhelming positive response to its marketing efforts with Community Anchor Institutions. The primary focus of our sub-recipient, the Development Authority of the North Country for the first quarter 2011, as it relates to the American Recovery and Reinvestment Act grant, was to begin construction of Segment 6. The milestones relative to that initiat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baseline = 41; According to the provisions of the Grant, we have been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0; No variance. | Baseline = 0; No variance. | Baseline = 33; According to the provisions of the Grant, we have been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 74; According to the provisions of the Grant, we have been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | N/A | N/A | Baseline = 5; According to the provisions of the Grant, we have been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time tablee provisions of the Grant, we have been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 1 | 10 | 12 | Paetec | 100 Megabit circuit | IONâ€™s partner, in the application and a sub recipient in the grant, is DANC. DANC is the Development Authority for the North Country based in Watertown, NY which operates a solid waste management facility, water and wastewater facilities, an open access telecom network, and administers several business and housing loan programs. Contact person for this organization is Dave Wolf, General Manager, Telecommunications (315)-785-2593 DANC is responsible to construct and operate approximately 40% of the total Grant project. | 0 | 1 | 0 | 1 | Baseline = 0 | Baseline = 0; Even though no fiber routes have been completed to date, electronics purchased with BTOP funds have been installed that facilitate the improved access for this provider. | Baseline = 0 | 100 Megabit circuit | 0 | 0 | 1 | 0 | Baseline = 0 | Baseline = 0 | Baseline = 0; The improved access provided to Paetec (see above) in turn provides improved access to the CAI. | 100 Megabits | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The priority for ION with this funding will be to seek out and work with governmental, educational, and healthcare entities that need service or that can offer services to support the vision of the American Reinvestment and Recovery Act. ION is working in close collaboration with Southern Tier West, Southern Tier Central, Southern Tier East, and other development agencies where job creation is central to their mission. ION will address the needs of public safety agencies and has met with agencies to address the need for reliable, affordable and secure capacity to meet the needs of these entities. ION may provide collocation and cross connection services to 3rd party providers requiring such services. ION may provide direct Internet backbone access to anchor institutions or 3rd party service providers to resell to their customers. | FALSE | N/A | ION has received the Finding of No Significant Impact (FONSI) in 1Q2011. ION has concentrated on getting the projects ready for the physical construction phase of the project. RFPâ€™s and RFQâ€™s will continue to go out and be awarded to companies involved in this quarter. Pole attachment agreements and permits will continue to be focused on so construction can proceed accordingly. ION will continue to work on completing the network design and final plans for the remaining projects. This will include permitting, staking, and ordering fiber. ION will continue to work with all the federal and state agencies on revisiting the EA work as necessary. The 2Q2011 will see physical construction on the DANC portion of the project will begin construction of fiber network in April 2011 and ION intends to begin construction of its first projects (project 2 and 4b) in May of 2011. The only unresolved issue is the Department of Transportation (DOT) surcharge on ROW use. We have also been working through an issue related to procuring the necessary fiber cable on a timely basis since the Corning fiber supply has now been committed to the needs created by the Japan tsunami disaster. We are awaiting a Corning Cable response and have contacted another vendor, Optical Fiber Systems (OFS) to determine if they could be a viable alternative to Corning. | ION Newco Corp | We continues to work diligently through an issue that has recently come to our attention and which if not resolved could potentially hold up and/or cause a great financial burden for ION. ION intends to spend $49M in New York state for broadband expansion mostly via the placement of fiber in the public right of way. ION is being told now that New York State Department of Transportation (NYSDOT) is requiring that it sign a Use and Occupancy (U&O) agreement and pay a fee for the use of that pubic Right of Way (ROW). ION has previously installed fiber in the public right away via NYSDOT permits under Empire State Independent Network LLC which certifications and tariffs are now owned by ION HoldCo LLC. The construction of the original network by ION was completed without the need of a NYSDOT U&O agreement and the associated lease payments, but now the NYSDOT is insisting that we sign one. We have being trying to work through this issue through the Governorâ€™s office, our attorney, and NYSTAR (New York State Foundation for Science, Technology and Innovation ). We were told that there is a practice of not requiring a U&O agreement with the associated rent/lease payments for C Corporations or Transportation Corporations such as telephone companies like Frontier, Verizon or Windstream. We have pointed out to NYSDOT that ION has been certified by the New York State Public Service Commission (NYSPSC) as a telephone company and as a utility we currently operate under the contr | As stated above, we are now ready to start physical construction of the network. Prior to beginning actual construction, we must have the reels of fiber ordered and delivered. We are now being informed by our fiber cable vendor that they are experiencing delays in their manufacturing process, and delays in shipping fiber cable due to the earthquakes and tsunami in Japan. At this time we are unable to determine the effect this issue will have on our progress. We will continue to seek additional resources for the procurement of the necessary fiber, which will include going back to the other bidders in the RFP process. If necessary we will rebuild and adjust our timeline to continue on schedule. | TRUE
NT10BIX5570133 | 2011 | Q2 | Q2 - 2011 | During the second quarter, ION completed the following significant project accomplishments: Increased labor resources dedicated towards completion of staking on the remaining projects. This allows ION to initiate the necessary make ready work with pole owners and to complete the project on time and within the three year timeline. ION continues to work on each project according to the timetable, initiating RFQ/RFP (Request for Qualifications/Request for Proposals) for the construction and equipment for each project in a timely manner. ION continues to meet and market the future network availability to prospective towns, anchor institutions, last mile providers, and government agencies. ION has had a positive response to its marketing efforts with Community Anchor Institutions (CAI). ION submitted and received approval of an Award Action Request (AAR) to utilize an Indefeasible Right of Use (IRU) for a portion of project 4a (Crown Point, NY to Burlington, VT). The result will shorten the scheduled time to complete the project, and will reduce the cost of the program. The first deliveries of fiber optic cable have been received. Laydown yards at three strategic sites in the state have been established for secure storage of the fiber prior to deployment. The placement of support strand was started in the second quarter for Project 4b (Whitehall, NY to Rutland VT). During the second quarter, the subrecipient of the Grant, Development Authority of the North Country (DANC) | 65 | 0 | 0 | 0 | 65 | 0 | 0 | 1 | Baseline = 96; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0; No variance. | Baseline = 0; No variance. | Baseline = 66; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. The normal sequence of activities for projects such as ours is to enter into lease arrangements near the completion of any newly constructed portions of a build. With new construction delayed, lease contracts have also been delayed. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in | Baseline = 161; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | N/A | N/A | Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. Baseline = 66; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. The normal sequence of activities for projects such as ours is to enter into lease arrangements near the completion of any newly constructed portions of a build. With new construction delayed, lease contracts have also been delayed. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. Baseline = 161; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. Baseline = 5; According to the provisions of the Grant, we were been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. RECIPIENT NAME:ION Newco Corp AWARD NUMBER: NT10BIX5570133 DATE: 08/17/2011 OMB CONTROL NUMBER: 0660-0037 EXPIRATION DATE: 12/31/2013 | 1 | 10 | 12 | Paetec | 150 Megabit circuit | IONâ€™s partner, in the application and a sub recipient in the grant, is the Development Authority for the North Country (DANC) based in Watertown, NY which operates a solid waste management facility, water and wastewater facilities, an open access telecom network, and administers several business and housing loan programs. Contact person for this organization is Dave Wolf, General Manager, Telecommunications (315)-785-2593 DANC is responsible to construct and operate approximately 40% of the total Grant project. | 0 | 1 | 0 | 1 | Baseline = 0 | Baseline = 3; Even though no fiber routes have been completed to date to connect to this broadband wholesaler, electronics purchased with BTOP funds have been installed that facilitate the improved access for this provider. Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0 | 150 Megabit circuit | 1 | 0 | 1 | 1 | Baseline = 3; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0; Service being provided to CAI above Baseline amount. | Baseline = 3; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 150 Megabits | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The priority for ION with this funding will be to seek out and work with governmental, educational, and healthcare entities that need service or that can offer services to support the vision of the American Reinvestment and Recovery Act. ION is working in close collaboration with Southern Tier West, Southern Tier Central, Southern Tier East, and other development agencies where job creation is central to their mission. ION will address the needs of public safety agencies and has met with agencies to address the need for reliable, affordable and secure capacity to meet the needs of these entities. ION may provide collocation and cross connection services to 3rd party providers requiring such services. ION may provide direct Internet backbone access to anchor institutions or 3rd party service providers to resell to their customers. | FALSE | N/A | ION will concentrate on getting the remaining projects ready for the physical construction phase of the project. RFPâ€™s and RFQâ€™s will continue to be reviewed and awarded to vendors and contractors. ION will continue to work on completing the network design and final plans for the remaining projects. This will include permitting, staking, and ordering fiber. Pole attachment agreements and permits will continue to be focused on so construction can proceed accordingly. ION will continue to work with all the federal and state agencies on monitoring the Environmental Assessment requirements as necessary. In 3Q11 DANC anticipates completing the fiber build and the test and turn-up of the fiber cable for segment 6. DANC also anticipates installing the equipment required to make segment 6 fully operational. For the segment 10 build we anticipate issuing an RFP and awarding a contract for three separate items; i) the fiber cable, ii) underground construction services, and iii) aerial construction services. DANC also anticipates completing all permitting and commencing the underground construction. Completion of the make ready survey and the commencement of the make-ready work for the aerial construction will also occur in 3Q2011. | ION Newco Corp | During the second quarter ION faced the following challenges and issues: 1. Early in the quarter ION continued to face an issue reported on in the first quarter; New York State Department of Transportation (NYSDOT) requiring a Use and Occupancy (U&O) agreement and payment of a fee for the use of the public Right of Way (ROW). The issue was resolved to IONâ€™s benefit. 2. ION was challenged by the suggestion that part of the project build overlapped with the proposed build of another federally funded project in the state of Vermont. The issue was resolved with a finding that the overlap would be a very insignificant portion of the projects. 3. During the quarter ION continued to experience long delays by Verizon in performing necessary make ready alterations to Verizon poles. We are continuing to meet with Verizon representatives to urge them to meet agreed upon work timetables. 4. ION is beginning to receive notices from its fiber optic cable provider, Corning, that future delivery dates are being extended. The stated reason is both global production and demand pressures resulting from the disasters in Japan. Delays in the receipt of fiber could impact unfavorably on meeting the three-year timetable for completion of the grant build. ION is working closely with Corning and other providers to gain earlier deliveries. | As stated above, we have begun physical construction of the network. Prior to performing actual construction, we must have the reels of fiber ordered and delivered. We are now being informed by our fiber cable vendor that they are experiencing delays in their manufacturing process, and delays in shipping fiber cable due to the earthquakes and tsunami in Japan. At this time we are unable to determine the effect this issue will have on our progress. We will continue to seek additional resources for the procurement of the necessary fiber, which will include going back to the other bidders in the RFP process. | TRUE
NT10BIX5570133 | 2011 | Q3 | Q3 - 2011 | During the third quarter, ION completed the following significant project accomplishments: ION has increased labor resources dedicated towards completion of staking on the remaining projects. This allows ION to initiate the necessarymake ready work with pole owners and to complete the project on time and within the three year timeline. ION continues to work on each project according to the timetable, initiating RFQ/RFP (Request for Qualifications/Request for Proposals) for the construction and equipment for each project in a timely manner. ION continues to meet and market the future network availability to prospective towns, anchor institutions, last mile providers, and government agencies. ION has had a positive response to its marketing efforts with Community Anchor Institutions (CAI). The delivery of fiber optic cable continues. Laydown yards at three strategic sites in the state have been established for secure storage of the fiber prior to deployment. The placement of support strand continues for Project 4b (Whitehall, NY to Rutland VT). An Award Action Request was submitted to add an additional subrecipient to participate in the construction of Project 4a (Crown Point New York to Burlington Vermont.) ION has chosen ADVA Optical as their vendor for DWDM electronics. Purchase orders have been placed. ION has released Request for Proposals (RFP) for Ethernet electronics. The primary accomplishments for the Development Authority of the North Country for 3Q2011: A | 90 | 5 | 0 | 0 | 90 | 0 | 0 | 2 | Baseline = 152; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0; Variance is immaterial. | Baseline = 0; No variance. | Baseline = 67; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. The normal sequence of activities for projects such as ours is to enter into lease arrangements near the completion of any newly constructed portions of a build. With new construction delayed, lease contracts have also been delayed. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in orde | Baseline = 219; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | N/A | N/A | Total Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) Baseline = 6; According to the provisions of the Grant, we were been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time tabler reasons for any variance from the baseline plan or any other relevant information) Baseline = 6; According to the provisions of the Grant, we were been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 1 | 10 | 12 | Paetec | 150 Megabit circuit | IONâ€™s partner, in the application and a sub recipient in the grant, is the Development Authority for the North Country (DANC) based in Watertown, NY which operates a solid waste management facility, water and wastewater facilities, an open access telecom network, and administers several business and housing loan programs. Contact person for this organization is Dave Wolf, General Manager, Telecommunications (315)-785-2593 DANC is responsible to construct and operate approximately 40% of the total Grant project. | 0 | 1 | 0 | 1 | Baseline = 0 | Baseline = 3; Even though no fiber routes have been completed to date to connect to this broadband wholesaler, electronics purchased with BTOP funds have been installed that facilitate the improved access for this provider. Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0 | 150 Megabit circuit | 1 | 0 | 1 | 1 | Baseline = 3; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0; Service being provided to CAI above Baseline amount | Baseline = 3; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 150 Megabits | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The priority for ION with this funding will be to seek out and work with governmental, educational, and healthcare entities that need service or that can offer services to support the vision of the American Reinvestment and Recovery Act. ION is working in close collaboration with Southern Tier West, Southern Tier Central, Southern Tier East, and other development agencies where job creation is central to their mission. ION will address the needs of public safety agencies and has met with agencies to address the need for reliable, affordable and secure capacity to meet the needs of these entities. ION may provide collocation and cross connection services to 3rd party providers requiring such services. ION may provide direct Internet backbone access to anchor institutions or 3rd party service providers to resell to their customers. | FALSE | N/A | ION will concentrate on getting the remaining projects ready for the physical construction phase of the project. RFPâ€™s and RFQâ€™s will continue to be reviewed and awarded to vendors and contractors. ION will continue to work on completing the network design and final plans for the remaining projects. This will include permitting, staking, and ordering fiber. Pole attachment agreements and permits will continue to be focused on so construction can proceed accordingly. ION will continue to work with all the federal and state agencies on monitoring the Environmental Assessment requirements as necessary. ION will select a vendor to supply Ethernet electronics. ION expects to host an event at one or more of the project sites to showcase the progress of the BTOP build. DANC anticipates completing the equipment install test and turn-up of segment 6. For the segment 10 build they anticipate completing all underground construction, completing the make ready surveys, and beginning the make-ready work. We also anticipate awarding the fiber cable bid. DANC expects for segment 8 to award the fiber cable bid and to begin the make-ready survey process. They also expect to have several access and license agreements in place for the Central offices. For combined ION and DANC, for the fourth quarter: Projected new network miles deployed - 75 Projected new network miles leased - 0 Projected total CAI subscribers served (CAIs connected) - 2 Projected number of signed agreements with | ION Newco Corp | During the third quarter ION faced the following challenges and issues: 1. ION was challenged by the suggestion that part of the project build overlapped with the proposed build of another federally funded project in the northern portion of New York state. A solution to the problem has been submitted to our program officer and is being reviewed. It is anticipate that the issue is not significant. 2. During the quarter ION continued to experience long delays by Verizon in performing necessary make ready alterations to Verizon poles. In many instances the agreed upon date for work to be completed has passed with no work being started. We are continuing to meet with Verizon representatives to urge them to meet agreed upon work timetables. We are also exploring legal paths to a solution. 3. ION is receiving notices from its fiber optic cable provider, Corning, and other potential providers that setting firm future delivery dates is problematic. The stated reason is both global production and demand pressures resulting from the disasters in Japan. Delays in the receipt of fiber could impact unfavorably on meeting the three-year timetable for completion of the grant build. ION is working closely with Corning and other providers to gain firm delivery dates. During the third quarter Development Authority of the North Country (DANC) faced the following challenges and issues: Although DANC bid the fiber cable for segment 10, none of the respondents that can provide cable that | As stated above, we have begun physical construction of the network. Prior to performing actual construction, we must both complete Make Ready work and have the reels of fiber ordered and delivered. We are now being informed by our fiber cable vendor that they are experiencing delays in their manufacturing process, and delays in shipping fiber cable due to the earthquakes and tsunami in Japan. We anticipate that Verizon will continue to miss the deadlines for completing Make Ready work. At this time we are unable to determine the effect this issue will have on our progress. We will continue to seek additional resources for the procurement | TRUE
NT10BIX5570133 | 2011 | Q4 | Q4 - 2011 | ION has physically started construction on projects 1, 2, 4b, and 9, including the placement of support strand and fiber cable for these projects. ION has increased labor resources dedicated towards completion of the staking on the remaining projects. This allows ION to initiate the necessary make ready work with pole owners in a timely manner. This also corresponds with our proposed timeline and will enable ION to complete all the projects on time and within the three year timeline. The delivery of fiber optic cable continues. ION continues to work on each project according to its proposed timetable, initiating RFQ/RFP (Request for Qualifications/Request for Proposals) for the construction and equipment for each project consecutively and concurrently. ION has released Request for Proposals (RFP) for Ethernet electronics. At the close of the fourth quarter the bids are being evaluated. ION has continued its aggressive marketing strategy, marketing the future network availability to prospective towns, anchor institutions, last mile providers, and government agencies. During this quarter ION has started to receive electronic components for the Dense Wavelength Division Multiplexing (DWDM) portion of projects. This equipment brings ION one step closer to lighting up its network and providing services to new CAIâ€™s and rural towns along their route. During this quarter, the ION financial team worked to complete an Audit on the federal grant funds awarded from the BTOP program. The audit was successfully completed and submitted. No findings were reported and the Audit was accepted by the NTIA. Also during this quarter, Vermont-based Sovernet Fiber Corp (â€œSovernetâ€) was added to the ION project as a subrecipient for project 4a in Vermont. The original project and its corresponding approved budget include a fiber route (known as Project 4A) from Crown Point, NY to Burlington, VT, which consists of both new fiber build and leased fiber. The northern-most segment of Project 4A is a dual-path ring within greater Burlington that will pass 12 carrier points of presence and over 80 potential CAIâ€™s. The primary accomplishments for the Development Authority of the North Country for the quarter were to complete the underground construction on the backbone network for segment 10 and to install, test and turn-up the SONET network on segment 6. Accomplishments relative to segment 6 include: â€¢ DWDM equipment for segment 6 was installed tested and turned up. â€¢ SONET network for segment 6 was installed, tested and activated. Accomplishments relative to segment 10 include: Make Ready surveys were completed for 95% of the route. â€¢ Completed the underground construction on the backbone portion of the network. This encompassed 12 miles of a combination of duct-proofing and innerduct placement, direct buried via cable plow, and a significant amount of directional drilling to avoid wetland areas. â€¢ Ordered fiber cable for segment 10. Still no ship date but order is in queue. â€¢ Installed conduit into the Cranberry Lake Central Office. â€¢ Agreements sent and waiting for approval for the Tupper Lake, Lake Placid, Saranac lake and Elizabethtown Central Offices. Accomplishments relative to segment 8 include: â€¢ Make ready survey process has begun and is 5% complete â€¢ Fiber optic cable has been ordered for the entire segment â€¢ Submitted a fiber exchange request to NTIA â€¢ Received signed Access and license agreement for the Malone Central Office. Built out the CO premise network to pre-position for long-haul connectivity when complete. | 200 | 5 | 0 | 0 | 200 | 0 | 0 | 3 | Baseline = 279; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0; Variance is immaterial. | Baseline = 0; No variance. | Baseline = 69; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. The normal sequence of activities for projects such as ours is to enter into lease arrangements near the completion of any newly constructed portions of a build. With new construction delayed, lease contracts have also been delayed. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in orde | Baseline = 348; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | N/A | N/A | Baseline = 10; According to the provisions of the Grant, we were been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 1 | 13 | 12 | Paetec | 150 Megabit circuit | IONâ€™s partner, in the application and a sub recipient in the grant, is the Development Authority for the North Country (DANC) based in Watertown, NY which operates a solid waste management facility, water and wastewater facilities, an open access telecom network, and administers several business and housing loan programs. Contact person for this organization is Dave Wolf, General Manager, Telecommunications (315)-785-2593 DANC is responsible to construct and operate approximately 40% of the total Grant project. Sovernet Fiber Corp has been approved as a sub recipient to build and operate the portion of the network in the Burlington VT area. | 0 | 1 | 0 | 1 | Baseline = 0 | Baseline = 13; Even though no fiber routes have been completed to date to connect to this broadband wholesaler, electronics purchased with BTOP funds have been installed that facilitate the improved access for this provider. Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0 | 150 Mgbs circuit | 4 | 0 | 4 | 4 | Baseline = 62; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0 | Baseline = 62; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next quarter. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 100 Mbps available to all subscribers. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The priority for ION with this funding will be to seek out and work with governmental, educational, and healthcare entities that need service or that can offer services to support the vision of the American Reinvestment and Recovery Act. ION is working in close collaboration with Southern Tier West, Southern Tier Central, Southern Tier East, and other development agencies where job creation is central to their mission. ION will address the needs of public safety agencies and has met with agencies to address the need for reliable, affordable and secure capacity to meet the needs of these entities. ION may provide collocation and cross connection services to 3rd party providers requiring such services. ION may provide direct Internet backbone access to anchor institutions or 3rd party service providers to resell to their customers. | FALSE | Network management practices have not changed. Policy statement can be found at www.i-o-n.com. | ION will concentrate on getting the remaining projects ready for the physical construction phase of the project. RFP’s and RFQ’s will continue to be reviewed and awarded to vendors and contractors. ION will continue to work on completing the network design and final plans for the remaining projects. This will include permitting, staking, and ordering fiber. Pole attachment agreements and permits will continue to be focused on so construction can proceed according to ION’s proposed timeline. ION will continue to work with all the federal and multi-state agencies on monitoring the Environmental Assessment requirements as necessary. ION continues to have an open dialogue with these entities to ensure compliance at all junctures of the project. There have been no significant impacts and all SAC’s have been complied with. ION will select a vendor to supply Ethernet electronics, moving ION closer to lighting up and providing services on the network. ION expects to host an event at one or more of the project sites to showcase the progress of the BTOP build. This will be highlighted in the ION marketing newsletter and many CAI’s, politicians and BTOP administrators will be invited to the event. In 1Q12 DANC anticipates obtaining agreements for all planned central offices in segments 8 and 10. We also anticipate activating Ethernet services in segment 6. For our segment 10 build we anticipate completing all make ready surveys, and beginning the makeready work. We also anticipate bidding of the aerial construction and electronics for this segment. For segment 8 we expect to complete approximately 50% of the make ready surveys and to begin the make ready construction. ION and DANC will continue to pursue the execution of service agreements now under negotiation, and to seek communication with the remaining Anchor institutions. We expect many of the agreements under negotiation to be executed next quarter. Sovernet will continue steps preliminary to actual build of the network, including letting bids for fiber, construction and equipment. We project the number of new network miles deployed will reach 295 miles, and we expect as many as ten CAI's receiving service. | ION Newco Corp | During the fourth quarter ION faced the following challenges and issues: 1. ION was notified that it appeared part of the project build overlapped with the proposed build of another federally funded project in the northern portion of New York State. A solution to the problem was submitted to our program officer and at the close of the fourth quarter is still being reviewed. It is anticipated that the issue is resolved and that an amicable agreement has been made that ensures there is no duplication of federal funds or duplication of services in the depicted area. 2. During the fourth quarter ION continued to experience delays by a specific pole owner in performing necessary make ready alterations needed on their poles. Unfortunately, in many instances the agreed upon date for work to be completed passed with no work being started. ION representatives continue to meet with the pole owner's representatives to urge them to work within the agreed upon work timetables. During the fourth quarter the severity of this issue has decreased. 3. Also during this quarter, delivery of fiber timetables was an issue. ION continues to be in communication with its major fiber optic cable provider regarding firming up delivery dates for its upcoming project needs. Likewise, DANC has ordered all fiber cable for segments 8 and 10, but does not have firm ship dates. At this time we have verbal dates but until we have final commitments we are unsure of the impact this will have. The stated rea | As stated above, we continue with the physical construction of the network in a timetable agreeable to our overall goal of completing the overall project within 3 years. Prior to performing actual construction, we must complete Make Ready work which we rely heavily on a specific pole owner to do as they are the owner of record on a lot of the poles the ION network needs to attach to. We anticipate that the specific pole owner may continue to miss the deadlines for completing Make Ready work. At this time we are unable to determine the effect this issue will have on our progress, but we continue to monitor this issue and work on it with the necessary representatives and through legal counsel. To perform construction, ION also needs to have the reels of fiber ordered and delivered on time. We are now being informed by our fiber cable vendor that they are experiencing delays in their manufacturing process, and delays in shipping fiber cable due to the earthquakes and tsunami in Japan. ION continues to monitor this situation and work on finding an additional provider for fiber needs just in case, so that this risk will not negatively impact the completion of the overall project in a timely manner. | TRUE
NT10BIX5570133 | 2012 | Q1 | Q1 - 2012 | ION has continued construction on projects 1, 2, 4b, and 9, including make ready work, and the placement of support strand and fiber cable for these projects. ION has ordered and has begun to receive fiber optic cable for all of the remaining projects. ION continues to work on each project according to its proposed timetable, initiating RFQ/RFP (Request for Qualifications/Request for Proposals) for the construction and equipment for each remaining project. Request for Proposals (RFP) for Ethernet electronics bids have been evaluated and a vendor was selected. ION has continued its aggressive marketing strategy, marketing the future network availability to prospective towns, anchor institutions, last mile providers, and government agencies. The primary accomplishments for the Development Authority of the North Country for 1Q2012 were to secure additional equipment locations, finalize route engineering, continue the make ready process, and to install additional Community Anchor Institutions (CAIâ€™s). Accomplishments relative to segment 6 include: â€¢ Upgraded the power at one central Office to allow for new equipment â€¢ Installed and turned up a new CAI. Accomplishments relative to segment 8 include: â€¢ Make ready survey process has increased from 5% to now 95% complete â€¢ Received 50% of the fiber cable â€¢ Received signed Letter of Intent for collocation in Plattsburgh â€¢ Project engineering is 95% complete Accomplishments relative to segment 10 include: â€¢ Bid submitted for the remaining construction â€¢ Make ready surveys are complete â€¢ Make ready work is 80% complete â€¢ Received 50% of the fiber cable â€¢ Installed conduit into the Tupper Lake and Lake Placid Central Office â€¢ Finalized agreements for the Lake Placid, Tupper Lake and Elizabethtown Central Office â€¢ Received all permits necessary for the aerial construction of segment 10. Subrecipient Sovernet Fiber Cable has completed strand mapping for the build in Burlington, VT. Make Ready ride-outs have been started, and approximately 1,000 poles have been surveyed. Central Office applications have been completed and submitted. Central Office conduit surveys are underway. | 262 | 5 | 0 | 50 | 262 | 0 | 0 | 3 | Baseline = 385; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0; Variance is immaterial. | Baseline = 0; No variance. | Baseline = 69; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. The normal sequence of activities for projects such as ours is to enter into lease arrangements near the completion of any newly constructed portions of a build. With new construction delayed, lease contracts have also been delayed. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber ro | Baseline = 454; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | N/A | N/A | Baseline = 17; According to the provisions of the Grant, we were been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 2 | 3 | 12 | Paetec, ION Holdco LLC | 150 Mbps circuits | IONâ€™s partner, in the application and a sub recipient in the grant, is the Development Authority for the North Country (DANC) based in Watertown, NY which operates a solid waste management facility, water and wastewater facilities, an open access telecom network, and administers several business and housing loan programs. Contact person for this organization is Dave Wolf, General Manager, Telecommunications (315)-785-2593. DANC is responsible to construct and operate approximately 40% of the total Grant project. Sovernet Fiber Corp has been approved as a sub recipient to build and operate the portion of the network in the Burlington VT area. | 1 | 1 | 0 | 1 | Baseline = 0; Variance is immaterial. | Baseline = 20; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0 | 150 Mbps circuit | 5 | 0 | 5 | 5 | Baseline = 65; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0 | Baseline = 65; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 100 Mbps available to all subscribers | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The priority for ION with this funding will be to seek out and work with governmental, educational, and healthcare entities that need service or that can offer services to support the vision of the American Reinvestment and Recovery Act. ION is working in close collaboration with Southern Tier West, Southern Tier Central, Southern Tier East, and other development agencies where job creation is central to their mission. ION will address the needs of public safety agencies and has met with agencies to address the need for reliable, affordable and secure capacity to meet the needs of these entities. ION may provide collocation and cross connection services to 3rd party providers requiring such services. ION may provide direct Internet backbone access to anchor institutions or 3rd party service providers to resell to their customers. | FALSE | Network policies statements can be found on both the ION and DANC websites. | ION will concentrate on getting the remaining projects ready for the physical construction phase of the project. RFPâ€™s and RFQâ€™s will continue to be reviewed and awarded to vendors and contractors. ION will continue to work on completing the network design and the final plans for the remaining projects. This will include permitting, staking, and obtaining fiber. Pole attachment agreements and permits will continue to be focused on so construction can proceed according to IONâ€™s proposed timeline. ION will continue to work with all the federal and multi-state agencies on monitoring the Environmental Assessment requirements as necessary. ION continues to have an open dialogue with these entities to ensure compliance at all junctures of the project. There have been no significant impacts and all SACâ€™s have been complied with. ION and DANC will continue to pursue the execution of service agreements now under negotiation, and to seek communication with the remaining Anchor institutions. We expect many of the agreements under negotiation to be executed next quarter. Sovernet will continue the preliminary steps necessary to actually physically construct the network, including soliciting bids for fiber, construction and equipment. By the end of the quarter we project the number of new network miles deployed will reach 345 miles, and we expect as many as nine CAI's will be receiving service on the networks constructed by ION and the two sub-recipients. For DANC, significant accomplishments planned for 2Q2012 includes completing 50% of the segment 10 construction, completing the build-out of 4 new Central Offices, and adding 7 CAIâ€™s. In addition, DANC plans to bid, award, and begin construction for segment 8 and complete 10% of that project. Sub-recipient Sovernet Fiber Cable plans to initiate Make Ready, and complete staking and right of way work on the Burlington VT project. For all ION and sub-recipient projects we expect during Q2 to deploy an additional 145 miles of fiber, serve an additional 5 CAI's and 2 last mile providers. | ION Newco Corp | During the first quarter ION faced the following challenges and issues: 1. ION was notified that it appeared part of DANC's project build overlapped with the proposed build of another federally funded project in the northern portion of New York State. A solution to the problem was submitted to our program officer and at the close of the first quarter is still being reviewed. It is anticipated that the issue is resolved and that an amicable agreement has been made that ensures there is no duplication of federal funds or duplication of services in the depicted area. 2. During the first quarter ION continued to experience delays by a specific pole owner in performing necessary make ready alterations needed on their poles. Unfortunately, in many instances the agreed upon date for work to be completed passed with little or no work being started. ION representatives continue to communicate with the pole owner's representatives to urge them to work within the agreed upon work timetables. During the first quarter the severity of this issue has decreased. During the make ready process for a DANC project we found 77 transmission poles that require replacement. We are working closely with the pole owner on this issue. At the present time we do not anticipate this causing any significant delays. | As stated above, we continue with physical construction of the network on a timetable agreeable to our overall goal of completing the overall project within three years. Prior to performing actual construction, we must complete Make Ready work. We rely heavily on a specific pole owner as they are the owner of record on many of the poles to which the ION network needs to attach. We anticipate that the specific pole owner may continue to miss the deadlines for completing Make Ready work. At this time we are unable to determine the effect this issue will have on our progress, but we continue to monitor this issue and work on it with the necessary representatives. | TRUE
NT10BIX5570133 | 2012 | Q2 | Q2 - 2012 | ION has continued construction on projects 1, 2, 4b, and 9, including make ready work; and the placement of support strand and fiber cable for these projects. Engineering, staking, permitting and negotiation of lease terms have been conducted for projects 3, 5, and 7. ION has received fiber optic cable for all of the remaining projects. ION continues to work on each project according to its proposed timetable, initiating RFQ/RFP (Request for Qualifications/Request for Proposals) for the construction and equipment for each remaining project. ION has continued its aggressive marketing strategy, marketing the future network availability to prospective towns, anchor institutions, last mile providers, and government agencies. Subrecipient Sovernet Fiber Cable has continued strand mapping for the build in Burlington, VT. Sovernet has worked with Vermont SHPO on the final route for project 4B, in the next quarter it is expected that a letter in agreement with the final route for the 4B build will be sent to ION, meeting the Special Award Conditions requirement for open dialogue with environmental agencies. Make Ready work is continuing to be done with ride-outs has begun and poles being surveyed. Central Office applications have been completed and submitted. Central Office conduit surveys are underway. Development Authority of the North Country accomplishments for the quarter were to begin to install several equipment locations, begin construction of segment 10, and to install additional Community Anchor Institutions (CAI). Accomplishments relative to segment 6 include: â€¢ Installed the 10 Gigabit per second Ethernet equipment in our Central Offices â€¢ Installed and turned up 4 new CAI. Accomplishments relative to segment 8 include: â€¢ Make ready survey process is complete â€¢ Received 100% of the fiber cable â€¢ Began construction of our 2 new and one upgraded Central Offices â€¢ Submitted an AAR to purchase an IRU of 6 strands over 9 miles for diversity on Plattsburgh. â€¢ Bid for construction sent and awarded. Construction to begin 3Q2012. Accomplishments relative to segment 10 include: â€¢ Bid awarded for the remaining construction â€¢ Construction began in June and over 20 miles of cable is installed. â€¢ Received 100% of the fiber cable â€¢ Began construction on 6 Central Offices Network wide accomplishments: â€¢ Bid and awarded the SONET equipment for all sites. â€¢ Bid the Ethernet equipment for all sites. â€¢ Bid and awarded contract for build out of all new Central Offices. â€¢ Commenced build-out of all new Central Offices. | 346 | 5 | 0 | 50 | 346 | 0 | 0 | 3 | Baseline = 625; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0; Variance is immaterial. | Baseline = 0; No variance. | Baseline = 75; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. The normal sequence of activities for projects such as ours is to enter into lease arrangements near the completion of any newly constructed portions of a build. With new construction delayed, lease contracts have also been delayed. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber ro | Baseline = 700; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | N/A | N/A | Baseline = 25; According to the provisions of the Grant, we were been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 11 | 12 | 12 | Ft Drum SUNY IT Griffiss NY Power Auth Claxton Hepburn Health center South Lewis Health Center Massena Hiospital Dialysis Center Beaver River Health Center Apogee FLTG INOC | 150 Mbps circuits 10 Mbps circuits 2.5 Gbps circuits | IONâ€™s partner, in the application and a sub recipient in the grant, is the Development Authority for the North Country (DANC) based in Watertown, NY which operates a solid waste management facility, water and wastewater facilities, an open access telecom network, and administers several business and housing loan programs. Contact person for this organization is Dave Wolf, General Manager, Telecommunications (315)-785-2593. DANC is responsible to construct and operate approximately 40% of the total Grant project. Sovernet Fiber Corp has been approved as a sub recipient to build and operate the portion of the network in the Burlington VT area. | 3 | 1 | 0 | 4 | Baseline = 0; Variance is immaterial. | Baseline = 26; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0 | 1 at 2.5 Gbps circuit 1 at 10 Mbps circuit 2 at 150 Mbps circuit | 9 | 1 | 8 | 9 | Baseline = 69; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0 Variance immaterial. | Baseline = 69; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 9 at 150 Mbps circuit | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The priority for ION with this funding will be to seek out and work with governmental, educational, and healthcare entities that need service or that can offer services to support the vision of the American Reinvestment and Recovery Act. ION is working in close collaboration with Southern Tier West, Southern Tier Central, Southern Tier East, and other development agencies where job creation is central to their mission. ION will address the needs of public safety agencies and has met with agencies to address the need for reliable, affordable and secure capacity to meet the needs of these entities. ION may provide collocation and cross connection services to 3rd party providers requiring such services. ION may provide direct Internet backbone access to anchor institutions or 3rd party service providers to resell to their customers. | FALSE | Network policies statements can be found on both the ION and DANC websites. | ION will concentrate on getting the remaining projects ready for the physical construction phase of the project. This will include continuing to work on completing the network design and the final plans for the remaining projects. This stage entails permitting, staking, and obtaining fiber. Pole attachment agreements and permits will continue to be focused on so construction can proceed according to IONâ€™s proposed timeline. RFPâ€™s and RFQâ€™s will continue to be reviewed and awarded to vendors and contractors according to the grant guidelines. ION will continue to work with all the federal and multi-state agencies on monitoring the Environmental Assessment requirements as necessary. ION continues to have an open dialogue with these entities to ensure compliance at all junctures of the project as required as part of our SAC. There have been no significant environmental impacts and all SACâ€™s have been complied with. ION and DANC will continue to pursue the execution of service agreements currently under negotiation, and seek communication with the remaining Anchor institutions. We expect many of the agreements under negotiation will be executed in the next quarter. By the end of the quarter we project the number of new network miles deployed will reach 646 miles, and we expect as many as twenty CAI's will be receiving service on the networks constructed by ION and the two sub-recipients. Sub-recipient Sovernet plans to initiate make ready work and complete staking and the right of way work on the Burlington VT project, project 4B Additionally, Sovernet will continue the preliminary steps necessary to physically construct the network, including soliciting bids for fiber, construction and equipment. Sovernet expects to gain approval from Vermont SHPO for the proposed final route for project 4B. For all ION and sub-recipient projects we expect during Q3 to deploy an additional 300 miles of fiber, serve an additional 11 CAI's and 2 last mile providers. For DANC, significant accomplishments planned for 3Q2012 includes completing the majority of segment 10 construction, completing the build-out of 4 new Central Offices, and adding 6 CAIâ€™s. In addition, we plan to bid, construct approximately 25% of segment 8. | ION Newco Corp | During the second quarter ION faced the following challenges and issues: 1. ION was notified that it appeared part of DANC's project build overlapped with the proposed build of another federally funded project in the northern portion of New York State. A solution to the problem was submitted to our program officer and was approved. 2. During the second quarter ION continued to experience delays, caused by a specific pole owner by not performing necessary make ready alterations needed on their poles. Unfortunately, in many instances the agreed upon date for work to be completed passed with little or no make ready work being started. ION representatives have continued to communicate with the pole owner's representatives and use other means available, to urge the pole owner to work within the agreed upon work timetables. During the second quarter the severity of this issue has decreased. 3. During the make ready process DANC found 77 utility owned transmission poles that require replacement. We are working closely with the utility on this issue. If this issue is not resolved we will request temporary attachments to these poles. | ION plans to continue with physical construction of the network on a timetable that substantiates our goal of completing the overall project within the three year term of the grant. Prior to performing actual construction, we must complete make ready work. To complete this work we must rely heavily on a specific pole owner as they are the owner of record on many of the poles that the ION network needs to attach on. Based on IONâ€™s previous interaction with this pole owner, we anticipate that the pole owner may very well continue to miss the deadlines for completing make ready work. At this time we are unable to determine the effect this issue will have on our progress, but we continue to monitor this issue very closely and work on it with the necessary representatives. | TRUE
NT10BIX5570133 | 2012 | Q3 | Q3 - 2012 | ION has continued construction on projects 1, 2, 4b, and 9, including make ready work; and the placement of support strand and fiber cable for these projects. Engineering, staking, permitting and negotiation of lease terms have been conducted for projects 3, 5, and 7. Fiber construction contractors have been selected for projects 3 and 7. ION continues to work on each project according to its proposed timetable, initiating RFQ/RFP (Request for Qualifications/Request for Proposals) for the construction and equipment for each remaining project. ION has continued its aggressive marketing strategy, marketing the future network availability to prospective towns, anchor institutions, last mile providers, and government agencies. Development Authority of the North Country accomplishments for the quarter include completing a significant portion of our largest build, segment 10. Accomplishments relative to segment 10 include installing approximately 90% of the fiber cable, completing 2 central office build outs, beginning the upgrade of 2 existing central offices, and commencing construction and installation of 3 new Central Office/interconnection point locations. In addition, we have installed fiber at 5 additional Community Anchor Institutions. The Development Authority also planned to begin work for segment 8 and we have started construction for segment 8. In addition, 3 new Central Office build-outs have been completed and the work to install electronics has begun. More general accomplishments include the receipt of all SONET/Optical transport equipment, the bid award and receipt of all Ethernet equipment, the bid, and award of optical transceiver equipment, and we have begun the installation of all electronics. | 555 | 20 | 0 | 50 | 555 | 0 | 0 | 6 | Baseline = 777; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget by the end of the Grant period. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0; Variance is immaterial. | Baseline = 0; No variance. | Baseline = 82; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. The normal sequence of activities for projects such as ours is to enter into lease arrangements near the completion of any newly constructed portions of a build. With new construction delayed, lease contracts have also been delayed. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber ro | Baseline = 700; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | N/A | N/A | Baseline = 25; According to the provisions of the Grant, we were been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 8 | 8 | 12 | FT Drum (Windstream) ION Holdco SLIC Networks Sovernet Level3 Windstream Sprint Action | 150 Mbps circuits 10 Mbps circuits 2.5 Gbps circuits | IONâ€™s partner, in the application and a sub recipient in the grant, is the Development Authority for the North Country (DANC) based in Watertown, NY which operates a solid waste management facility, water and wastewater facilities, an open access telecom network, and administers several business and housing loan programs. Contact person for this organization is Dave Wolf, General Manager, Telecommunications (315)-785-2593. DANC is responsible to construct and operate approximately 40% of the total Grant project. Sovernet Fiber Corp has been approved as a sub recipient to build and operate the portion of the network in the Burlington VT area. | 3 | 2 | 0 | 4 | Baseline = 0; Variance is immaterial. | Baseline = 37; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0; No variance | 1 at 2.5 Gbps circuit 2 at 10 Mbps circuit 2 at 150 Mbps circuit | 13 | 1 | 12 | 12 | Baseline = 117; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline by the end of our Grant period. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | Baseline = 0 Variance immaterial. | Baseline = 117; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline by the end of our Grant period. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 12 at 150 Mbps circuit | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The priority for ION with this funding will be to seek out and work with governmental, educational, and healthcare entities that need service or that can offer services to support the vision of the American Reinvestment and Recovery Act. ION is working in close collaboration with Southern Tier West, Southern Tier Central, Southern Tier East, and other development agencies where job creation is central to their mission. ION will address the needs of public safety agencies and has met with agencies to address the need for reliable, affordable and secure capacity to meet the needs of these entities. ION may provide collocation and cross connection services to 3rd party providers requiring such services. ION may provide direct Internet backbone access to anchor institutions or 3rd party service providers to resell to their customers. | FALSE | Network policies statements can be found on both the ION and DANC websites. | For 4Q2012 we expect to deploy 172 additional route miles of fiber, serve an additional 38 Anchor Institutions and 4 additional Last Mile Providers. | ION Newco Corp | During the third quarter ION continued to experience delays, caused by a specific pole owner by not performing necessary make ready alterations needed on their poles. Unfortunately, in many instances the agreed upon date for work to be completed passed with little or no make ready work being started. ION representatives have continued to communicate with the pole owner's representatives and use other means available, to urge the pole owner to work within the agreed upon work timetables. We still have some small portions of segment 8 where make-ready work has not been completed by the pole owners and occupiers. We have requested temporary attachment rights in these locations. | ION plans to continue with physical construction of the network on a timetable that substantiates our goal of completing the overall project within the three year term of the grant. Prior to performing actual construction, we must complete make ready work. To complete this work we must rely heavily on a specific pole owner as they are the owner of record on many of the poles that the ION network needs to attach on. Based on IONâ€™s previous interaction with this pole owner, we anticipate that the pole owner may very well continue to miss the deadlines for completing make ready work. At this time we are unable to determine the effect this issue will have on our progress, but we continue to monitor this issue very closely and work on it with the necessary representatives. | TRUE
NT10BIX5570133 | 2012 | Q4 | Q4 - 2012 | 81% of middle mile has been deployed across all projects, with 1 new Community Anchor Institutions added on the ION network and Development Authority of the North Country (DANC) has installed fiber at 23 additional Community Anchor Institutions. DANCâ€™s segment 10 is lit and operational. Accomplishments relative to segment 10 include completing 2 central office build outs and upgrading 2 existing central offices. 85% of segment 8 is complete. In addition, 2 new Central Office build-outs have been completed and the electronics are installed and activated on segment 8. DANC still has one existing Central Office to upgrade and segment 8 will be fully operational by 1Q 2013. Sovernet continues to make progress on their Burlington Vermont build with expectations of being totally complete by summer. ION has continued construction on projects 1, 2, 3, 4b, 7 and 9, including make ready work; and the placement of fiber and electronics for these projects. ION is negotiating with 6 last mile providers and wholesalers in this quarter to provide services on the ION network to end users. Information has been gathered for the necessary Award Action Requests for IRU lease agreements on projects 1, 3, 5, and 7. An alternate route segment was also needed on Project 1 due to an unforeseen circumstance; that route has been identified and staked. This route also has the potential for ION to IRU a piece of fiber that will close the ring. Work has been done on that potential agreement. ION continues to work with its partners and develop each project according to its proposed timetable, initiating RFQ/RFP (Request for Qualifications/Request for Proposals) for the construction and equipment for each remaining project. ION has continued its aggressive marketing strategy, marketing the future network availability to prospective towns, anchor institutions, last mile providers, and government agencies. | 617 | 45 | 0 | 57 | 617 | 0 | 0 | 14 | Baseline = 1,036; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget by the end of the Grant period. | Baseline = 0; Variance is immaterial. | Baseline = 0; No variance. | Baseline = 88; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. The normal sequence of activities for projects such as ours is to enter into lease arrangements near the completion of any newly constructed portions of a build. With new construction delayed, lease contracts have also been delayed. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber ro | Baseline = 1,124; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | N/A | N/A | Baseline = 41; According to the provisions of the Grant, we were been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 14 | 9 | 48 | FT Drum (Windstream) ION Holdco SLIC Networks Sovernet Level3 Sprint Action Westelcom Windstream/Paetec (3) AT&T Verizon Wireless TVC Communications Finger Lakes Technology Group Apogee | 150 Mbps circuits 10 Mbps circuits 2.5 Gbps circuits | IONâ€™s partner, in the application and a sub recipient in the grant, is the Development Authority for the North Country (DANC) based in Watertown, NY which operates a solid waste management facility, water and wastewater facilities, an open access telecom network, and administers several business and housing loan programs. Contact person for this organization is Dave Wolf, General Manager, Telecommunications (315)-785-2593. DANC is responsible to construct and operate approximately 40% of the total Grant project. Sovernet Fiber Corp has been approved as a sub recipient to build and operate the portion of the network in the Burlington VT area. | 4 | 3 | 0 | 3 | Baseline = 0; Variance is immaterial. | Baseline = 37; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline by the end of the Grant period. | Baseline = 0; No variance | 1 at 2.5 Gbps circuit 4 at 10 Mbps circuit 2 at 150 Mbps circuit | 35 | 0 | 35 | 1 | Baseline = 125; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline by the end of our Grant period. | Baseline = 0. | Baseline = 125; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to c3atch up to our baseline by the end of our Grant period. | All at 150 Mbps circuit | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The priority for ION with this funding will be to seek out and work with governmental, educational, and healthcare entities that need service or that can offer services to support the vision of the American Reinvestment and Recovery Act. ION is working in close collaboration with Southern Tier West, Southern Tier Central, Southern Tier East, and other development agencies where job creation is central to their mission. ION will address the needs of public safety agencies and has met with agencies to address the need for reliable, affordable and secure capacity to meet the needs of these entities. ION may provide collocation and cross connection services to 3rd party providers requiring such services. ION may provide direct Internet backbone access to anchor institutions or 3rd party service providers to resell to their customers. | FALSE | Network policies statements can be found on both the ION and DANC websites. | Submission of 6 AARâ€™s will happen in 1Q2013, this will help support a shortened operational time frame for the identified segments, including 1,3,5,7. After approval of these IRU leases, ION will be able to quickly move towards lighting up services many of its projected CAIâ€™s. This will also allow the redundancy and capacity increases for last mile providers as well as existing CAIâ€™s. For 1Q2013 we expect to complete all remaining Central Office work in the 6 Central Offices we are constructing and the 2 we are upgrading. We also anticipate connecting 10 additional CAIâ€™s to the network. DANC will upgrade the final existing Central Office on segment 8 and then this segment will be fully operational in 1Q 2013. Make ready work will be complete and construction contractors will begin work on the Burlington segment for subrecipient Sovernet. Cummulative number of miles of fiber we plan to deploy by the end of the first quarter: 722 miles Cummulative number of broadband wholesalers and last mile providers agreements we plan to have signed by the end of the first quarter: 20 | ION Newco Corp | During the fourth quarter unfortunately ION continued to experience delays due to make ready obligations not being met by a specific pole owner. Though the requirement is that the owner make necessary alterations on their poles, deadlines and agreed upon completion dates continue to go unmet. In most cases little or no make ready work has been started under these obligations and agreements. ION representatives have continued to communicate with the pole owner's representatives and use every means available, to urge the pole owner to work within the agreed upon work timetables. | ION and its partners, DANC and Sovernet plan to continue with physical construction of the network on a timetable that substantiates our goal of completing the overall project within the three year term obligation of the grant. Our biggest challenge continues to lie in the intention of a specific pole owner to meet their make ready obligations, as prior to performing any actual construction, we must have all make ready work complete. Though we continue to identify this as a challenge or concern, it has improved lately as ION has been working on an alternate plan to help alleviate the potential for this turning into a significant risk for the projects. This plan includes making temporary attachments, on poles that we are waiting for make ready work to be completed on, and by hiring alternate contractors to complete make ready work according to the original make ready agreements. Based on IONâ€™s previous interactions with this pole owner and ongoing delays, we anticipate that the pole owner may very well continue to miss the deadlines for completing make ready work. At this time we are unable to determine the full effect this issue will have on our progress, but we continue to monitor this issue very closely and work on it with the necessary representatives. | TRUE
NT10BIX5570133 | 2013 | Q1 | Q1 - 2013 | 92% of middle mile has been deployed across all projects, with new Community Anchor Institutions added on the ION network and Development Authority of the North Country (DANC) being added quickly. Development Authority of the North Country (DANC) has installed fiber at 5 additional Community Anchor Institutions for a total of 37. DANC has also completed 80% of the alarm installation and commenced implementation of the network management platform we are using to manage the network. DANCâ€™s segment 8 is primarily complete and is lit and operational. The final central office has been complete and we are now working across segment 8. Accomplishments relative to segment 10 include completing all central office builds. Sovernet continues to make progress on their Burlington Vermont build with expectations of being totally complete by July. ION continues construction on projects 1, 2, 3, 4b, 7 and 9, including make ready work; and the placement of fiber and electronics for these projects. ION is negotiating with last mile providers and wholesalers in this quarter to provide services on the ION network to end users. ION has submitted the necessary Award Action Requests for IRU lease agreements on projects 1, 3, 5a. ION has continued its aggressive marketing strategy, marketing the future network availability to prospective towns, anchor institutions, last mile providers, and government agencies. | 845 | 0 | 0 | 156 | 845 | 0 | 0 | 17 | Baseline = 1,220; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget by the end of the Grant period. | Baseline = 0; Variance is immaterial. | Baseline = 0; No variance. | Baseline = 167; Variance is immaterial. | Baseline = 1,387; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | N/A | N/A | Baseline = 53; According to the provisions of the Grant, we were been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 22 | 32 | 8 | Windstream/Paetec (3 agreements) AT&T Verizon Wireless (2 agreementss) TechValleyCommunications Sprint ACTION Sovernet Level3 Finger Lakes Technology Group Apogee Windstream/Paetec (2 add'l agreements) Sovernet/NYC L3 Jamestown Apogee/Ithaca ION Westelcom SLIC Windstream (Ft Drum) | 150 Mbps circuits 10 Mbps circuits 2.5 Gbps circuits | IONâ€™s partner, in the application and a sub recipient in the grant, is the Development Authority for the North Country (DANC) based in Watertown, NY which operates a solid waste management facility, water and wastewater facilities, an open access telecom network, and administers several business and housing loan programs. Contact person for this organization is Dave Wolf, General Manager, Telecommunications (315)-785-2593. DANC is responsible to construct and operate approximately 40% of the total Grant project. Sovernet Fiber Corp has been approved as a sub recipient to build and operate the portion of the network in the Burlington VT area. | 6 | 16 | 0 | 3 | Baseline = 0; Variance is immaterial. | Baseline = 43; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline by the end of the Grant period. | Baseline = 0; No variance | 1 at 2.5 Gbps circuit 19 at 10 Mbps circuit 2 at 150 Mbps circuit | 42 | 0 | 42 | 1 | Baseline = 125; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline by the end of our Grant period. | Baseline = 0. | Baseline = 125; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to c3atch up to our baseline by the end of our Grant period. | Average circuit is 300meg | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The priority for ION with this funding will be to seek out and work with governmental, educational, and healthcare entities that need service or that can offer services to support the vision of the American Reinvestment and Recovery Act. ION is working in close collaboration with Southern Tier West, Southern Tier Central, Southern Tier East, and other development agencies where job creation is central to their mission. ION will address the needs of public safety agencies and has met with agencies to address the need for reliable, affordable and secure capacity to meet the needs of these entities. ION may provide collocation and cross connection services to 3rd party providers requiring such services. ION may provide direct Internet backbone access to anchor institutions or 3rd party service providers to resell to their customers. | FALSE | Network policies statements can be found on both the ION and DANC websites. | Submission of AARâ€™s will continue to happen in 2Q2013, this will help support a much needed shortened operational time frame for the identified segments, including 2,5b,7,9. After approval of these IRU leases, ION will be able to quickly move towards lighting up services to many of its projected CAIâ€™s, which will help lessen the impact of the continued make-ready delays ION experienced. This will also allow the redundancy and capacity increases needed for last mile providers as well as existing CAIâ€™s. For 2Q2013 we expect to continue to add CAIâ€™s to the network, signing additional IRU agreements, and turning up network that is already in place. For 2Q2013 DANC expects to complete the remaining Central Office work in the Elizabethtown and Potsdam Central Offices. We also anticipate connecting 38 additional CAIâ€™s to the network. DANC will finish any miscellaneous clean-up work on all construction. The majority of the new network management platform will be installed and tested. Sovernet will continue to make progress on the Burlington Vermont segment with an expected completion date for that segment of late 2nd quarter 2013or beginning of the 3rd quarter 2013. After exceeding our expectations for miles deployed in the first quarter, ION, DANC, and Sovernet will continue to work towards the total number of network miles for the overall proposed project(s). ION will continue to add to the number of broadband wholesalers and last mile providerâ€™s agreements. Cummulative number of miles of fiber we plan to deploy by the end of the second quarter: 950 miles Cummulative number of broadband wholesalers and last mile providers agreements we plan to have signed by the end of the second quarter: 23 Cummulative number of CAI agreements we plan to have signed by the end of the second quarter: 84 | ION Newco Corp | During the first quarter, ION continued to experience some delays due to make ready obligations not being met by a specific pole owner. Though the requirement is that the owner make necessary alterations on their poles, deadlines and agreed upon completion dates continue to go unmet. In most cases little make ready work has been started under these obligations and agreements. ION representatives have continued to communicate with the pole owner's representatives and use every means available, to urge the pole owner to work within the agreed upon work timetables. There will be some impact to the project timetables due to the continued make ready delays. Though, there will be no risk that the project will not be completed. | ION and its partners, DANC and Sovernet plan to continue with physical construction of the network on a timetable that meets our goal of completing the overall project within the three year term obligation of the grant. Our biggest challenge continues to lie in the intention of a specific pole owner to meet their make ready obligations, as prior to performing any actual construction, we must have all make ready work complete. Although we continue to identify this as a challenge or concern, it has improved lately as ION has been working on an alternate plan to help alleviate the potential for this turning into a significant risk for the projects. The plan includes making temporary attachments on poles that we are waiting for make ready work to be completed on and by hiring alternate contractors to complete make ready work according to the original make ready agreements. Based on IONâ€™s previous interactions with this pole owner and ongoing delays, we anticipate that the pole owner may very well continue to miss the deadlines for completing make ready work. At this time we are unable to determine the full effect this issue will have on our progress, but we continue to monitor very closely and work on it with the necessary representatives. We feel at this time that there will be some impact to the project timetables due to the continued make ready delays, although, there will be little risk that the project cannot be completed. | TRUE
NT10BIX5570133 | 2013 | Q2 | Q2 - 2013 | 95% of middle mile has been deployed across all projects, with new Community Anchor Institutions added on the ION network and Development Authority of the North Country (DANC) being added quickly. Development Authority of the North Country (DANC) has installed fiber at 4 additional Community Anchor Institutions for a total of 41. In addition, we have commenced building to 40 additional CAIâ€™s and will have those completed next month. Additional 2Q2013 accomplishments includes completing the construction and equipment install at 3 of the final 4 new central offices. The final Central Office build is nearly complete and all equipment is already installed. DANC also completed and awarded three bids for CAI builds in 2Q2013. Upon completion of those fiber construction projects we will have met our CAI goal. Sovernet continues to make progress on their Burlington Vermont build with expectations of being totally complete by July. ION continues construction on projects 1, 2, 3, 7 and 9, including make ready work; and the placement of fiber and electronics for these projects. ION is negotiating with last mile providers and wholesalers in this quarter to provide services on the ION network to end users. ION has submitted the necessary Award Action Requests for IRU lease agreements on projects 2,7,9 and 5b. ION has continued its aggressive marketing strategy, marketing the future network availability to prospective towns, anchor institutions, last mile providers, and government agencies. | 939 | 0 | 0 | 274 | 939 | 0 | 0 | 23 | Baseline = 1,308; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget by the end of the Grant period. | Baseline = 0; No variance. | Baseline = 0; No variance. | Baseline = 246; Variance is immaterial. | Baseline = 1,554; According to the provisions of the Grant, we were prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | N/A | N/A | Baseline = 57; According to the provisions of the Grant, we were been prohibited from beginning the physical construction of the fiber network until we completed our Environmental Assessment (EA) process and were issued a Finding of No Significant Impact (FONSI). Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our budget during the next one or two quarters. Two additional contractors have been employed to accelerate the staking of fiber routes in order that we can begin actual fiber construction as early as possible in order to catch up to our planned time table. | 26 | 4 | 8 | Windstream/Paetec (3 agreements) AT&T Verizon Wireless TVC Sprint ACTION Sovernet Level3 FLTG Apogee Windstream/Paetec (2 add'l agreement) Sovernet/NYC L3 Jamestown Apogee/Ithaca Northland SLIC Verizon Wireless (Addl site) ION Westelcom SLIC Windstream Verizon Wireless TechValley Communications | 150 Mbps circuits 10 Mbps circuits 2.5 Gbps circuits | IONâ€™s partner, in the application and a sub recipient in the grant, is the Development Authority for the North Country (DANC) based in Watertown, NY which operates a solid waste management facility, water and wastewater facilities, an open access telecom network, and administers several business and housing loan programs. Contact person for this organization is Dave Wolf, General Manager, Telecommunications (315)-785-2593. DANC is responsible to construct and operate approximately 40% of the total Grant project. Sovernet Fiber Corp has been approved as a sub recipient to build and operate the portion of the network in the Burlington VT area. | 6 | 20 | 0 | 3 | Baseline = 0; Variance is immaterial. | Baseline = 55; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline by the end of the Grant period. | Baseline = 0; No variance | 1 at 2.5 Gbps circuit 19 at 10 Mbps circuit 2 at 150 Mbps circuit | 55 | 0 | 55 | 1 | Baseline = 125; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to catch up to our baseline by the end of our Grant period. | Baseline = 0. | Baseline = 125; Due to major complexities and unanticipated delays in the Environmental Assessment process, and our need to concentrate manpower resources in that process we were not able to begin actual construction as we had originally planned in the summer and fall months of 2010. We do not expect these delays to affect the overall timetable for our projects and we expect to c3atch up to our baseline by the end of our Grant period. | Average circuit is 300meg | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The priority for ION with this funding will be to seek out and work with governmental, educational, and healthcare entities that need service or that can offer services to support the vision of the American Reinvestment and Recovery Act. ION is working in close collaboration with Southern Tier West, Southern Tier Central, Southern Tier East, and other development agencies where job creation is central to their mission. ION will address the needs of public safety agencies and has met with agencies to address the need for reliable, affordable and secure capacity to meet the needs of these entities. ION may provide collocation and cross connection services to 3rd party providers requiring such services. ION may provide direct Internet backbone access to anchor institutions or 3rd party service providers to resell to their customers. | FALSE | Network policies statements can be found on both the ION and DANC websites. | For 3Q2013 we expect to continue to connect and add CAIâ€™s to the network, signing additional IRU agreements, and turning up network that is already in place. The last remaining IRU's contracts will be executed. For 3Q2013 DANC expects to complete the remaining CAI builds and to complete construction of the final Central Office. DANC will finish any miscellaneous clean-up work on all construction. The network management platform will be installed and tested. Sovernet will continue to make progress on the Burlington Vermont segment with an expected completion date for that segment of the beginning of the 3rd quarter 2013. After meeting our expectations for miles deployed in the second quarter, ION, DANC, and Sovernet will continue to work towards the total number of network miles for the overall proposed project(s). ION will continue to add to the number of broadband wholesalers and last mile providerâ€™s agreements. Cumulative number of miles of fiber we plan to deploy by the end of the third quarter: 944 miles Cumulative number of broadband wholesalers and last mile providers agreements we plan to have signed by the end of the third quarter: 26 Cumulative number of CAI agreements we plan to have connected by the end of the third quarter: 130 | ION Newco Corp | During the second quarter, ION continued to experience some delays due to make ready obligations not being met by a specific pole owner. Though the requirement is that the owner make necessary alterations on their poles, deadlines and agreed upon completion dates continue to go unmet. In most cases little make ready work has been started under these obligations and agreements. ION representatives have continued to communicate with the pole owner's representatives and use every means available, to urge the pole owner to work within the agreed upon work timetables. There will be some impact to the project timetables due to the continued make ready delays. Though, there will be no risk that the project will not be completed. | ION and its partners, DANC and Sovernet plan to continue with physical construction of the network on a timetable that meets our goal of completing the overall project within the three year term obligation of the grant. Our biggest challenge continues to lie in the intention of a specific pole owner to meet their make ready obligations, as prior to performing any actual construction, we must have all make ready work complete. Although we continue to identify this as a challenge or concern, it has improved lately as ION has been working on an alternate plan to help alleviate the potential for this turning into a significant risk for the projects. The plan includes making temporary attachments on poles that we are waiting for make ready work to be completed on and by hiring alternate contractors to complete make ready work according to the original make ready agreements. Based on IONâ€™s previous interactions with this pole owner and ongoing delays, we anticipate that the pole owner may very well continue to miss the deadlines for completing make ready work. At this time we are unable to determine the full effect this issue will have on our progress, but we continue to monitor very closely and work on it with the necessary representatives. We feel at this time that there will be some impact to the project timetables due to the continued make ready delays, although, there will be little risk that the project cannot be completed. | TRUE
NT10BIX5570133 | 2013 | Q3 | Q3 - 2013 | In 3Q2013 ION, Sovernet and the Development Authority of the North Country (DANC) focused primarily on completing all builds to Community Anchor Institutions, finalizing the Central Office build outs, and installing all network management and monitoring equipment. 100% of middle mile has been deployed across all projects. DANC has installed fiber at the final 46 Community Anchor Institutions for a total of 87 CAIâ€™s with new fiber. Additional 3Q2013 accomplishments includes completing the construction and equipment install at the final new central office. We also installed enhanced network monitoring equipment at 8 of the recently completed equipment locations. ION is negotiating with last mile providers and wholesalers in this quarter to provide services on the ION network to end users. ION has submitted the necessary Award Action Requests for IRU lease agreements on projects 2,7,9 and 5b. ION has continued its aggressive marketing strategy, marketing the future network availability to prospective towns, anchor institutions, last mile providers, and government agencies. | 944 | 0 | 0 | 378 | 944 | 0 | 0 | 45 | Baseline = 1,308: Original plans had a higher estimate of miles to be built, with fewer leased. Ultimately fewer miles built, with more leased as long-term IRU's. | Baseline = 0; No variance. | Baseline = 0; No variance. | Baseline = 246: Original plans had a higher estimate of miles to be built, with fewer leased. Ultimately fewer miles built, with more leased as long-term IRU's. | Baseline = 1,554: Original plans had a higher estimate of miles to be built, with fewer leased. Ultimately fewer miles built, with more leased as long-term IRU's. | N/A | N/A | Baseline = 57: | 39 | 3 | 12 | ION Holdco LLC Westelcom SLIC Windstream Verizon Wireless location 1 TechValley PEG Bandwidth Level 3 Windstream/Paetec AT&T Wireless location 1 AT&T Wireless location 2 AT&T Wireless location 3 AT&T Wireless location 4 AT&T Wireless location 5 AT&T Wireless location 6 AT&T Wireless location 7 AT&T Wireless location 8 AT&T Wireless location 9 AT&T Wireless location 10 Level 3 (Jamestown to NYC) Finger Lakes Technology Group - VZW cell tower at Alfred U. Empire Tel - NASA Finger Lakes Technology Group - CCC Wakefield Champlain Valley Telephone - AT&T Sovernet Verizon Wireless - Vernon Relo tower AT&T Wireless (location 11) NYS - Cooperstown Windstream/Paetec (4th site) Windstream/Paetec (5th site) Tech Valley Communications Sprint ACTION Level3 Apogee Apogee/Ithaca Northland SLIC Verizon Wireless (2nd Site) | 150 Mbps circuits 10 Mbps circuits 2.5 Gbps circuits | IONâ€™s partner, in the application and a sub recipient in the grant, is the Development Authority for the North Country (DANC) based in Watertown, NY which operates a solid waste management facility, water and wastewater facilities, an open access telecom network, and administers several business and housing loan programs. Contact person for this organization is Dave Wolf, General Manager, Telecommunications (315)-785-2593. DANC is responsible to construct and operate approximately 40% of the total Grant project. Sovernet Fiber Corp has been approved as a sub recipient to build and operate the portion of the network in the Burlington VT area. | 7 | 32 | 0 | 3 | Baseline = 0; Variance is immaterial. | Baseline = 55; Major reason for actual below baseline due providers waiting for current service contracts to expire. | Baseline = 0; No variance | 1 at 2.5 Gbps circuit 29 at 10 Mbps circuit 2 at 150 Mbps circuit | 128 | 0 | 128 | 8 | Baseline = 125; Variance immaterial | Baseline = 0; No variance | Baseline = 125; No variance | 9 at 1 gbps 25 at 10 mbps 19 at 100 mbps 1 at 10 gbps 9 at 200 mbps 5 at 300 mbps 9 at 50 mbps 4 at 500 mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | The priority for ION with this funding will be to seek out and work with governmental, educational, and healthcare entities that need service or that can offer services to support the vision of the American Reinvestment and Recovery Act. ION is working in close collaboration with Southern Tier West, Southern Tier Central, Southern Tier East, and other development agencies where job creation is central to their mission. ION will address the needs of public safety agencies and has met with agencies to address the need for reliable, affordable and secure capacity to meet the needs of these entities. ION may provide collocation and cross connection services to 3rd party providers requiring such services. ION may provide direct Internet backbone access to anchor institutions or 3rd party service providers to resell to their customers. | FALSE | Network policies statements can be found on both the ION and DANC websites. | ION and subrecipients have completed all work and do not expect any additional work in 4Q2013. All entities plan to accomplish all closeout activites. | ION Newco Corp | During the third quarter, ION continued to experience some delays due to make ready obligations not being met by a specific pole owner. Though the requirement is that the owner make necessary alterations on their poles, deadlines and agreed upon completion dates continue to go unmet. In most cases little make ready work has been started under these obligations and agreements. ION representatives have continued to communicate with the pole owner's representatives and use every means available, to urge the pole owner to work within the agreed upon work timetables. There will be some impact to the project timetables due to the continued make ready delays. Though, there will be no risk that the project will not be completed. | No challenges or issues anticipated. | TRUE
NT10BIX5570135 | 2010 | Q4 | Q4 - 2010 | Significant planning, design, and project management efforts were made along several parallel tracks, including performing a project-wide environmental assessment (EA), establishing project management offices, initiating key project procurement processes, and performing detailed physical fiber optic plant design. The key priority this quarter was to drive the Environmental Assessment to meet the March 1, 2011 deadline to submit our draft assessment. This involved selecting Columbia Telecommunications Corporation as the EA consulting firm, initiating the engineering work required to provide route detail and maps required by the various environmental agencies, and making initial contact with those agencies, such as: Maryland Department of the Environment (MDE), Department of Natural Resources (DNR), US Fish and Wildlife (USFWS), US Army Corps of Engineers (AMCE), and Maryland Historical Trust (MHT). Consultations with all agencies, except MDE and AMCE , were initiated within this reporting period. Work began in reaching out to state, county, and municipal right of way (ROW) owners to inform them of the project and solicit any special requirements they may have for construction permitting. Work began in negotiating pole attachment agreements with various utility pole owners where aerial construction is planned, and assessing the condition of poles on the planned routes. Utilities include Pepco Power, Choptank Electric, SMECO, Hagerstown City Light, Allegany Power, Verizon, B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | None were planned for this reporting quarteg quarter | 0 | 1 | 0 | None were planned for this reporting quarterg quarter. | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | All Right-of-way owners will have been met and introduced to the OMBN project, such as State Highway Administration (SHA) and various departments of public works and utility pole owners. The Environmental Assessment Draft will be submitted by March 1st deadline. Procurement solicitations will be publicly released for inventory and material distribution logistics, fiber construction materials, and detailed engineering services, including the development of permit applicatins. Also, we expect to have an awarded contract and an order placed for an initial allotment of certain fiber construction materials. | Information Technology, Maryland Department of | Nothing further to cover than what is described above. | Securing pole attachment agreement's in a timely fashion to commence with the Aerial Engineering. Ensuring the various permitting agencies have the bandwidth to process our volume of permit applications. | TRUE
NT10BIX5570135 | 2011 | Q1 | Q1 - 2011 | The following are the main accomplishments this reporting period along with some major key milestones: The submission of the program-wide Environment Assessment draft before the March 1, 2011 deadline. This major milestone will lead to the eventual receipt of the Finding of No Significant Impact (FONSI) which allows the program to begin construction. Letters of concurrence and consultation were obtained from the required environmental agencies, such as Maryland Department of the Environment (MDE), Department of Natural Resources (DNR), US Fish and Wildlife (USFWS), Army Corps of Engineers (USACE), and Maryland Historical Trust. Additionally, follow up meetings with the MDE and USACE were held to define and refine how the program will submit permit applications in a manner that will not overwhelm the permitting agencies, while ensuring we meet their requirements. Additionally, the Memorandum of Understanding (MOU) with of the Sub-Recipient; Howard County representing the Inter-County Broadband Network (ICBN) was concluded. Also work has begun in reaching out to the state, county, and municipal right of way (ROW) owners to inform them of the project scope and solicit any special requirements they may have for construction permitting. All utility companies have been contacted where Aerial Construction is planned, this includes Pepco Power, Choptank Electric, SMECO, Hagerstown City Light, Allegany Power, Verizon, BG&E, and Delmarva Power. Agreements with some utility com | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | None were planned for this reporting quarter | N/A | N/A | N/A | None were planned for this reporting quarter | N/A | N/A | None were planned for this reporting quarter | 0 | 3 | 0 | None were planned for this reporting quarter. | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | Baseline indicated 2, we are still in the process of negotiating | N/A | 0 | 0 | 0 | 0 | None were planned this reporting quarter | None were planned this reporting quarter | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | RFP-Fiber: Award(s) made and contract ratified. RFP-Logistics: The Proposals have been received and are being reviewed. Contract to be awarded next quarter. RFP-Construction: The Proposals have been received and are being reviewed. Multiple contracts will be awarded. Outside Plant Engineering: An RFP will be finalized, publicly issued, and multiple contracts awarded. MOU: 1) Signed Memorandum Of Understanding (MOU) with Maryland Depart of IT and the Maryland Broadband Cooperative (MdBC) 2) Signed Memorandum Of Understanding (MOU) between sub recipient Howard county (ICBN) and its 9 participating jurisdictions 3) Signed IRU between DoIT and MdBC Permitting: Begin submitting permits State Highway Administration (SHA) , county departments of public works, along with US Army Corps of Engineers (USACE) and Maryland Department of Environment (MDE) to jointly make approvals in the single permit application for all of OMBN thus allowing a continual build out of the One Maryland Broadband Network project with minimal delays in permitting process. FONSI: Final award of the FONSI (Finding Of No significant Impact) which allows the program to begin construction. Utility Companies: Signed agreements with most if not all utility companies for aerial pole attachments where aerial construction is planned, this may include Pepco Power, Choptank Electric, Hagerstown City Light, Allegany Power, Verizon, BG&E, and Delmarva Power. Fiber Procurement: The initial procurement of | Information Technology, Maryland Department of | For other BTOP projects, particularly those involving multiple government recipients and sub recipients over a large geographic area, we offer the following best practices: 1) Reach out early to permitting authorities to creating awareness of the scale, scope and timing of project. Solicit permitting authority needs, and coordinate application submission logistics. This includes Right of Way owners, utility pole owners, and utility locators. 2) Closely coordinate with your Federal Program Officer on all challenges. 3) Reach out to the vendor community via a vendor fair to ensure open and competitive procurement, as well as to efficiently disseminate relevant information regarding Program requirements, limitations, and opportunities 4) Meet with all stakeholders early to establish recurring touch points to leverage their support with permitting regulatory issues, and ensure a proper understanding of financial requirements and eligible uses of Federal funds. 5) Centralize accounting and reporting functions among multiple sub recipients to the greatest degree possible, thereby leveraging economies of scale for expert resources required and minimizing the risk of errors. | The following issues may cause some challenges, 1)Fiber Delivery: Japanâ€™s natural disaster could impact the fiber optic cable supply chain and may cause delivery delays. 2)Pole Agreements: Delays in obtaining signed pole attachment agreements among numerous program participants and multiple utility companies requires complex legal negotiations that could delay engineering and permitting in some participating jurisdictions. 3)Permitting: Staging and submitting permitting application in a way that will not overwhelm the staffs of applicable permitting authorities and delay issuance the permits will continue to present challenges in some cases where the magnitude of this project will require beyond normal workloads for some permitting agencies. | TRUE
NT10BIX5570135 | 2011 | Q2 | Q2 - 2011 | The following are the main accomplishments this reporting period: We received the environmental Finding of No Significant Impact (FONSI) from the NTIA based upon our completed Environmental Assessment detailing the consultations and findings of multiple environmental and cultural regulatory agencies, such as Maryland Department of the Environment (MDE), Department of Natural Resources (DNR), US Fish and Wildlife (USFWS), Army Corps of Engineers (AMCE), and Maryland Historical Trust (MHT). The Memorandum of Understanding (MOU) between the Maryland Department of Information Technology and the Maryland Broadband Cooperative has been fully executed. Also, the MOU between Sub-Recipient Howard County and the nine other participating jurisdictions of the Inter-County Broadband Network (ICBN) was completed and is being circulated for signatures. We expect this MOU to be ratified by all parties within the next quarter. A simultaneous process of submitting permit applications to the State, county and municipal right-of-way owners has begun. This will make the approval process faster, allowing the continual build out of the OMBN project with minimal delays in the permitting processes. During this quarter, detailed engineering work and local permit applications have been submitted, and many acquired, throughout the State. Detailed engineering work is completed for a total of approximately 250 miles of routes (out of 1300), which are permitted or are permit-ready. We are fully en | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 39 miles were planned, please refer to project indictor #3 above. | N/A | N/A | N/A | 39 miles were planned, please refer to project indictor #3 above. | N/A | N/A | 12 interconnection point were planned, insufficient fiber miles to begin connection, however we do anticipate interconnection within the next reporting quarter, insufficient fiber miles to begin connection, however we do anticipate interconnection within the next reporting quarter. | 0 | 1 | 0 | Two were projected for this reporting quarter, one was signed during this reporting quarter. We do however anticipate signing a second broadband wholesaler or last mile provider within the next reporting quarter. The anticipated number of signed broadband provider for the next quarter is a cumulative number of two. | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | At least one formal agreement is being negotiated with discussions occurring with several other potential lessees. Additionally, cooperative construction is occurring with at least one commercial carrier reducing costs for certain routes for both parties. | N/A | 3 | 3 | 0 | 0 | 1GB speed are now available for each anchor institution i.e.Gamer Fire Dept.(Public Safety), Sykesville Police Dept. (Public Safety), & Sykesville Town Hall (Government Facility) | 1GB speed are now available for each anchor institution i.e.Gamer Fire Dept.(Public Safety), Sykesville Police Dept. (Public Safety), & Sykesville Town Hall (Government Facility) | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | We expect to be able to report the following accomplishments for next quarter: Engineering: â€¢ Significant progress on field and CAD engineering by the next reporting quarter, this will enable an rapid increase in permit application submission. Permitting : â€¢ Rights of Way (ROW) permitting: Begin receiving permits from the State Highway Administration (SHA) and multiple county Departments of Public Works. â€¢ Environmental: Begin receiving permits from the US Army Corps of Engineers (USACE)USACE and Maryland Department of Environment (MDE) for phases of the single permit application for all of OMBN. â€¢ Rail Road Crossing: Begin receiving executed licensing agreements and permits from rail road companies â€¢ Utility Companies: Obtain signed pole attachment agreements with all utility companies that are currently under negotiation for aerial pole attachments where aerial construction is planned. These processes will allow a continual build out of the One Maryland Broadband Network project with minimal delays in permitting process. Fiber Procurement: â€¢ The continued procurement of fiber and related materials from the various suppliers program wide. Equipment Procurement: â€¢ The Initial equipment purchases, we are in the initial stages for purchasing the OMBN network electronic equipment with over $1.6M in equipment purchases made already with additional purchases to be made within the next reporting quarters. Construction: â€¢ Construction has begun in Ba | Information Technology, Maryland Department of | Competitive procurements are an important part of our Program strategy, but one that poses significant challenges for our timeline. Many of the key procurements necessary to enable large-scale construction efforts were still being finalized this quarter, though we anticipate these procurements will overall reduce risk to enable the Program to complete on-time. While initially time consuming, these procurements will allow for multiple awards to be made to qualified contractors that will be deployed simultaneously throughout the State. Additionally, a large number of centralized permitting and licensing efforts that involve significant upfront planning, negotiations, and coordination have delayed the initialization of large scale construction efforts, but that will further reduce risk by facilitating cooperative, streamlined processes with permitting authorities and utility pole owners that might otherwise be overwhelmed by the load presented by this Program. For example, we have engaged and have made significant progress with permitting through the Maryland Department of the Environment (MDE), the Maryland State Highway Administration (SHA), numerous railroads, and all relevant utility pole owners. Moreover, it should be noted that partial progress has been made on many more miles of construction than captured in the reporting for the respective Key Milestones above, which cannot yet be reported as completed miles of fiber construction due to certain challenges. Fo | The following issues may cause some challenges, 1)Fiber Delivery: Japanâ€™s natural disaster could impact the fiber optic cable supply chain and may cause additional delivery delays. Currently delivery lead time is 20 weeks, with a backlog of orders that could push the lead time to 34 weeks or more. 2)Pole Agreements: Delays in obtaining signed pole attachment agreements among numerous program participants and multiple utility companies requires complex legal negotiations that could delay engineering and permitting in some participating jurisdictions. 3)Permitting: Potential delays from Maryland Department of Engineering (MDE) & US Army Corps of Engineers (USACE) due to required wetland delineations needed to identify routes requiring permitting.. | TRUE
NT10BIX5570135 | 2011 | Q3 | Q3 - 2011 | This quarter saw significant progress in engineering across most of the state and the start of the construction ramp-up. Engineering is well in progress. Of the 1294 miles planned, POs have been issued for 859 miles to commence work. As of this point, 447 miles have already been submitted for permits to various agencies and utilities. Utility pole attachment agreements for aerial construction have been executed with the majority of utility pole owners, including; Baltimore Gas and Electric (BGE), Verizon, Alleghany Power, Delmarva Power, and Choptank Electric. Permits are being issued by the State Highway Administration, as well as many County Departments of Public Works for work in their right-of-ways. Additionally, a program wide permit application was submitted to the Maryland Department of Environment and US Army Corps of Engineers for all required crossing of tidal wetlands, and is under review. Materials logistics are now in place to support the ramp up of construction. Additionally, securing a sufficient supply of fiber has been a priority since the earthquake in Japan disrupted the fiber supply chain. Up to 501 miles of fiber, valued at $1,682,301 have been delivered during this reporting quarter. Additional awards have been made for construction related materials valued at $2,285,098 to be delivered during our next reporting quarter (Q4). The program has established two local centralized warehouses and has since setup and established the materials logistics | 15 | 0 | 0 | 0 | 15 | 0 | 0 | 3 | Planned was 116. Construction will continue ramping up in multiple counties. Contracts have been awarded to 21 construction companies and as work is tasked, construction will increase significantly in 2012. We expect to be in construction in all 24 jurisdictions in 2012. Currently we have installed over 59 miles of conduit. This number is not captured in the reporting for this milestone, which we do not report until fiber is pulled and spliced into the newly constructed conduit. | N/A | N/A | N/A | Planned was 116. Construction has begun ramping up in multiple counties. Currently we have installed over 59 miles of conduit. All pole owner applications have been signed and approved allowing for aerial permitting to commence. This will allow us to begin reporting aerial miles constructed during the next reporting quarters. | N/A | N/A | Total Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) 13 interconnection points were planned. Three connections were made on fiber from a resource share agreement between the state and the MdBC. At this point we do not yet have sufficient fiber miles built to begin other connectionsr reasons for any variance from the baseline plan or any other relevant information) 13 interconnection points were planned. Three connections were made on fiber from a resource share agreement between the state and the MdBC. At this point we do not yet have sufficient fiber miles built to begin other connections. | 0 | 2 | 0 | None were signed this reporting quarter, we do however anticipate signing with broadband wholesalers or last mile providers within the next reporting quarters. | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | Planned was 2. At least two formal agreements are being negotiated. | N/A | 7 | 7 | 0 | 0 | Planned was 111 CAI's. Construction has begun ramping up in multiple counties. The total subscribers served will increase exponentially as construction continues to ramp up. We have sufficient materials on hand to support rapid ramp up. 1GB speeds are now available for the community anchor institutions such as Public Safety & Government Facilities. | Planned was 111 CAI's. Construction has begun ramping up in multiple counties. The total subscribers served will increase exponentially as construction continues to ramp up. We have sufficient materials on hand to support rapid ramp up. 1GB speeds are now available for the community anchor institutions such as Public Safety & Government Facilities. | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | We expect to be able to report the following accomplishments for next quarter: Engineering: â€¢ Anticipating significant amount of engineering to be completed during the next reporting quarter. This will enable an exponential increase in permit application submission and approvals. Permitting : â€¢ Rights of Way (ROW) permitting: Continue receiving permits from the State Highway Administration (SHA) and multiple county Departments of Public Works. This will be an ongoing process throughout the construction phase. â€¢ Environmental: Begin receiving permits from the US Army Corps of Engineers (USACE) and Maryland Department of Environment (MDE). Detailed engineering work identified lower cost routing and other necessary routing changes. Environmental consultation should be completed this quarter with the Maryland Historical Trust (MHT), US Fish & Wildlife (USFW) and the Department Natural Resources (DNR). This is expected to be completed and submitted to the NTIA in November. â€¢ Rail Road Crossings: Continue receiving executed licensing agreements and permits from rail road companies. Currently have executed agreement with CSX. We are currently engaged with; Amtrak, Maryland Transit Authority, Norfolk Southern Corp., Maryland & Delaware Rail Road, Maryland Midland Rail Ways, and Bay Coast Rail Road to obtain licensing agreements. â€¢ Utility Companies: Obtained signed pole attachment agreements from ALL utility companies. These processes will allow a continual buil | Information Technology, Maryland Department of | Although we have made significant progress with permitting through the Maryland Department of the Environment (MDE), clarifications of regulatory requirements have required multiple meetings. We are however working towards a shared understanding through continued dialog to avoid additional delays. Detailed engineering work identified lower cost routing and other necessary routing changes. Environmental consultations are in process with the Maryland Historical Trust (MHT), US Fish & Wildlife (USFW) and the Department Natural Resources (DNR). This is expected to be completed and submitted to the NTIA in November. Maryland State Highway Administration (SHA) permitting on limited access freeways has also been a challenge in some jurisdictions, primarily surrounding negotiations for resource sharing agreements. Meanwhile, most permit applications continue to be processed in a timely manner with few issues. Discussions continue with SHA, the Governor's office, and the affected jurisdictions to ensure we that we come to an agreement. Another challenge identified this quarter is the time consuming nature of obtaining agreements for railroad crossings. Our network requires 80 crossings of 9 separate railroad companies throughout the state, each generally requiring an encroachment agreement and coordination with railroad personnel during construction. The process of coordinating with the various entities has proven to be more involved and time intensive than anticipated. The | The following issues may cause some challenges, 1) Fiber Delivery: Although our current supplier, OFS, is meeting its delivery commitments at this time, we consider the overall state of the market to be a risk. Currently delivery lead times are 20 weeks or more for new orders outside of existing commitments. 2) Pole Agreements: All pole attachment agreements required are executed, however the utility pole make-ready construction process and time-line is an ongoing risk and challenge. In many cases, the time-lines are several months for completion of make-ready work once engineering is completed. More significantly, pole owners are reluctant to make time-line commitments, in part due to potential weather-related delays that can drastically impact their construction resources for extended periods (i.e. Hurricane Irene) 2a) Pole Make Ready Cost: Additional challenges with pole make-ready are the requirement to replace/ renew utility poles. This may occur in certain jurisdictions due to regulatory load specifications and requirements. Should pole replacement become a requirement the financial undertaking could be in the range of $30K - $40K per pole. If pole replacement becomes excessive we would be forced to mitigate this risk by changing our methods from Aerial to Underground construction. This would stress our budget. 3) Permitting: As the pace of engineering and construction increases, potential delays may occur due to the limited resources available to perform wetlan | TRUE
NT10BIX5570135 | 2011 | Q4 | Q4 - 2011 | This quarter the Program saw significant progress across most of the state, and on many fronts. Construction awards continue to gain momentum and are scheduled to continue to ramp up as additional awards are made during the Q1 & Q2 reporting periods in 2012. Of the 1294 miles of engineering planned program-wide, purchase orders have been issued for 1133.8 miles, or 86% of the total. Required permit applications have been submitted to the various agencies and utility companies for 764.7 miles, or 58% of the total project, and have been approved or are being processed. Additionally, permit applications for all anticipated Tidal Wetlands crossings were submitted to the Maryland Department of Environment and US Army Corps of Engineers, and are expected to be approved in Q1 2012. Aerial attachment applications continue to be submitted throughout the One Maryland Broadband Network (OMBN). Utility pole make-ready construction work is underway by the utilities, and several pole attachment licenses were issued allowing aerial construction to begin. The utility companies include: Baltimore Gas and Electric (BGE), Verizon, Alleghany Power, Delmarva Power, PEPCO, Hagerstown Light, Berlin Electric, Antietam Cable, and Choptank Electric. We have received $3,162,844 of fiber, which is 29% of the total contract award valued at $10,819,850. Construction has begun in Anne Arundel County, Baltimore County, Baltimore City, Carroll County, Charles County, Harford County, Howard County, Montgomery County, and Prince George's County. An agreement to purchase communications shelters for the MdBC was executed on November, and the first order was placed on December 20, 2011. We anticipate receiving the first order in Q1, with remaining deliveries in Q2 and Q3 2012. To date, 199 miles of underground conduit have been installed, and 87 miles of fiber have been installed, representing 10% of our total mileage requirements. Additionally, 10 Community Anchor Institutions (CAIs) sites have been connected out of 1,006 CAIs, representing 1% of CAIs connected. Finally, we have expended 17.23% of the total budget funds to date. | 87 | 0 | 112 | 0 | 87 | 0 | 0 | 3 | Planned was 285. Construction will continue ramping up in multiple counties. Contracts have been awarded to 22 construction companies and as work is being tasked, construction is increasing exponentially. Note: last quarter we were at 1% complete. We expect to be in construction in all 24 counties in June 2012. Currently we have installed over 199 miles of conduit. This number is not captured in the reporting for this milestone, which we do not report until fiber is pulled and spliced into the newly constructed conduit. | N/A | This mileage represents the MdBC in kind fiber contribution to the project. | N/A | Planned was 285. Construction will continue ramping up in multiple counties. Contracts have been awarded to 22 construction companies and as work is being tasked, construction is increasing exponentially. Note: last quarter we were at 1% complete. We expect to be in construction in all 24 counties in June 2012. Currently we have installed over 199 miles of conduit. This number is not captured in the reporting for this milestone, which we do not report until fiber is pulled and spliced into the newly constructed conduit. | N/A | N/A | 16 interconnection points were planned. Three connections were made on fiber from a resource share agreement between the state and the MdBC. At this point we do not yet have sufficient fiber miles built to begin other connections. | 8 | 12 | 24 | [REDACTED] | N/A | N/A | 0 | 8 | 0 | 0 | N/A | Currently signed 8 agreements with wholesalers receiving improved access. | Planned was 2. At least twelve formal agreements are being negotiated. | N/A | 10 | 10 | 0 | 10 | Planned was 161 CAI's. Construction has begun ramping up in multiple counties. The total subscribers served will increase exponentially as construction continues to ramp up. We have sufficient materials on hand to support rapid ramp up. 1GB speeds are now available for the community anchor institutions such as Public Safety & Government Facilities. | Planned was 161 CAI's. Construction has begun ramping up in multiple counties. The total subscribers served will increase exponentially as construction continues to ramp up. We have sufficient materials on hand to support rapid ramp up. 1GB speeds are now available for the community anchor institutions such as Public Safety & Government Facilities. | N/A | 9- CAIs at 1GB 1- CAI at 100Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Please describe significant project accomplishments planned for completion during the next quarter (600 words or less). 28 miles of backbone ring construction, splicing and testing will be completed, which will complete the core ring. A modification request for community anchor institutions will be provided to NTIA for approval. Modifications are due to facility closures, relocations, and new requests for connectivity. For all approved modifications and additions, engineering will be completed by 2-20-2012, rights of way acquired, and clearances obtained from West Virginia State Historic Preservation office for ground-disturbing construction. Pending approvals from NTIA and WV-SHPO, construction of community anchor institution laterals will commence. Orders for network access equipment, facilities equipment, and customer premises equipment to be placed in first quarter. Community anchor institutions requesting service will be turned up as laterals and drops are placed. Requests for service by broadband wholesalers or last mile providers are not expected in Q1-2012. | Information Technology, Maryland Department of | One major challenge identified this quarter; the time consuming nature of obtaining agreements for railroad crossings. Our network requires 89 crossings of 10 separate railroad companies throughout the state, each generally requiring an encroachment agreement and coordination with railroad personnel during construction. The process of coordinating with the various entities has proven to be more involved and time intensive than anticipated. The need for separate encroachment agreements with each jurisdiction could create unforeseen legal challenges impacting the schedule. However, we have mitigated some of the risk by the centralizing the engineering and permitting for all railroad crossings. Another big challenge is obtaining make ready estimates from the utilities in a timely manner. We have weekly meetings with the utility companies to keep track of this process. | The following issues may cause some challenges, A major challenge identified is the time consuming nature of obtaining agreements for railroad crossings. Our network requires 89 crossings of 10 separate railroad companies throughout the state, each generally requiring an encroachment agreement and coordination with railroad personnel during construction. The process of coordinating with the various entities has proven to be more involved and time intensive than anticipated. The need for separate encroachment agreements with each jurisdiction could create unforeseen legal challenges impacting the time line. However, we have mitigated some of the risk by the centralizing the engineering and permitting for al railroad crossing. Another big challenge is obtaining make ready estimates from the utilities in a timely manner. We have weekly meetings with the utility companies to keep track of this process. | TRUE
NT10BIX5570135 | 2012 | Q1 | Q1 - 2012 | The project focus is shifting from engineering to construction. Nearly 97% of the route, or 1330 miles have been awarded to engineering vendors, and of that total, 1071 miles or 78% of the route have been fully engineered and submitted to permitting agencies. Permits have already been received for over 603 of the route miles or 44% of the route total. Aerial attachment agreements are signed with all utility pole owners and attachment applications are being submitted. The utility companies include; Baltimore Gas and Electric (BGE), Verizon, Alleghany Power, Delmarva Power, PEPCO, Hagerstown Light, Berlin Electric, Antietam Cable, and Choptank Electric. Make ready work has begun on 110 miles of the 400 aerial fiber route miles. Of that total, 25 miles have been completed and installed with fiber. Materials procurements continue with $3,457,072 of fiber received, or 32% of the total contract award valued at $10,819,850. Additionally, over $4,617,519 of Network Equipment and Communications huts have been received. Construction has begun in 18 counties and 1 city in the state of Maryland; Anne Arundel Co, Annapolis Co, Baltimore Co, Baltimore City, Calvert Co, Carroll Co, Caroline Co, Cecil Co, Charles Co, Fredrick Co, Harford Co, Howard Co, Kent Co, Montgomery Co, Prince George's Co, Queen Anne's Co, Saint Maryâ€™s Co, Talbot Co, Wicomico Co, & Worcester Co, as well as Baltimore City. To date, of the total 1373 planned miles, 384 miles of conduit have been installed or 39% of the total underground path. Of that total, 171 miles of fiber have been installed. Additionally, 25 miles of aerial fiber have been installed yielding a combined total of 196 miles or 14% of total route mileage. Additionally, 11 Community Anchor Institutions (CAIs) sites have been connected out of 1006 CAIs. | 196 | 0 | 254 | 0 | 196 | 0 | 0 | 4 | Planned was 362. Construction will continue ramping up in multiple counties. Contracts have been awarded to 22 construction companies and as work is being tasked, construction is increasing exponentially. Note: We more than doubled our total from last quarter. We expect to be in construction through out the entire state of Maryland in June 2012. Currently we have installed over 384 miles of conduit and begun 110 miles of aerial make ready work. These numbers are not captured in the reporting for this milestone, which we do not report until fiber is pulled and spliced into the newly constructed conduit. | N/A | This mileage represents the MdBC in kind fiber contribution to the project. | N/A | Planned was 362. Construction will continue ramping up in multiple counties. Contracts have been awarded to 22 construction companies and as work is being tasked, construction is increasing exponentially. Note: We more than doubled our total from last quarter. We expect to be in construction through out the entire state of Maryland in June 2012. Currently we have installed over 384 miles of conduit and begun 110 miles of aerial make ready work. These numbers are not captured in the reporting for this milestone, which we do not report until fiber is pulled and spliced into the newly constructed conduit. | N/A | N/A | 23 interconnection points were planned. Four connections were made on fiber from a resource share agreement between the state and the MdBC. At this point we do not yet have sufficient fiber miles built to begin other connections. | 8 | 12 | 24 | MdBC is our wholesale provider and have signed agreements with various last mile providers. The latest listing was provided on the Q4-2011 PPR. | N/A | N/A | 0 | 8 | 0 | 0 | N/A | Currently signed 8 agreements with wholesalers receiving improved access. | Planned was 2. At least twelve formal agreements are being negotiated. | N/A | 11 | 11 | 0 | 11 | Planned was 191 CAI's. Construction has begun ramping up in 18 counties. The total subscribers served will increase exponentially as construction continues to ramp up. We have sufficient materials on hand to support rapid ramp up. 1GB speeds are now available for the community anchor institutions such as Public Safety & Government Facilities. | Planned was 191 CAI's. Construction has begun ramping up in 18 counties. The total subscribers served will increase exponentially as construction continues to ramp up. We have sufficient materials on hand to support rapid ramp up. 1GB speeds are now available for the community anchor institutions such as Public Safety & Government Facilities. | N/A | 10- CAIs at 1GB 1- CAI at 100Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Our engineering efforts have passed their peak and are nearing completion, while construction continues a rapid ramp up. The following are our indicators for the next reporting quarter. Engineering: â€¢ Engineering is nearly completed and coming to closure for the outside-plant. The logical network engineering is in process. Permitting : â€¢ Rights of Way (ROW) permitting: At least 95% of the underground permits will have been received from State Highway Administration (SHA), county, and municipal authorities. We expect to receive at least 50% of our aerial attachment permits. â€¢ Aerial Utility permitting: Continue submitting aerial permit applications for the various utility companies. The utility companies include; Baltimore Gas and Electric (BGE), Verizon, Potomac Edison, Delmarva Power, PEPCO, Hagerstown Light, Berlin Electric, and Choptank Electric. â€¢ Environmental: We've been receiving permits from the US Army Corps of Engineers (USACE) and Maryland Department of Environment (MDE) for tidal and non-tidal wetlands crossings. This will be an ongoing process throughout the construction phase. We have begun construction across several permitted environmental resource areas. â€¢ Rail Road Crossings: We have been executing licensing agreements and receiving permits from the railroad companies. We expect to have executed agreements with CSX, Maryland & Delaware Rail Road, Maryland Midland Rail Ways, Bay Coast Rail Road. We are currently in the process of executing licensing agreements with the remaining Rail Road companies; Amtrak, George's Creek, and Metropolitan Transit Authority (MTA), Washington Metropolitan Transit Authority (WMTA). Fiber Procurement: â€¢ We expect continued receipt of fiber and related materials at our centralized warehouse locations in sufficient quantities to prevent construction delays. Equipment Procurement: â€¢ Continue the procurement of the OMBN equipment, with over $10M in equipment purchases to be made within the next reporting quarter. Construction: â€¢ With construction in the 18 counties and city already started, we anticipate starting in 5 other counties during the next quarter; Allegany Co, Dorchester Co, Garrett Co, Somerset Co, & Washingtion Co. This will bring our active construction to all of Maryland's 23 counties and Baltimore City by the next reporting quarter. Key project Indicators: a. New network miles deployed= 494 b. New network miles leased= 0 c. Total CAI subscribers served (CAIs connected)= 218 d. Number of signed agreements with broadband wholesalers or last mile providers= 9 | Information Technology, Maryland Department of | 1) One of our main challenges for this reporting quarter was obtaining make ready estimates from the utility companies in a timely manner. Ride-out scheduling challenges have occurred for various utility companies as their resources have limited capacity. We have weekly meetings with the utility companies to aggressively manage this process. In some cases our mitigation has been to convert aerial miles to underground construction. 2) A second challenge is the finalization of easements and permits to place Communication Huts in some locations i.e. Annapolis, La Plata and Aberdeen. | The following issues may cause some challenges, 1) Our main concern for the next reporting quarter is obtaining make ready estimates from the utilities companies in a timely manner. Ride-out scheduling challenges may occur for various utility companies as their resources have limited capacity. We have weekly meetings with the utility companies to aggressively manage this process. In some cases our mitigation will be to convert aerial miles to underground construction. 2) A second potential challenge is the ability of locating companies to keep up with the volume of locate tickets from Miss Utility. 3) A third potential challenge is the finalization of easements and permits to place Communication Huts in some locations i.e. Annapolis, La Plata and Aberdeen. | TRUE
NT10BIX5570135 | 2012 | Q2 | Q2 - 2012 | The project has fully transitioned to construction in every county in the state of Maryland. Of the planned 1411 route miles, 98% or 1381 miles have been awarded to engineering vendors. Of that total, 1254 miles or 89% of the route total have been fully engineered and submitted to permitting agencies. Permits have already been received for over 975 route miles or 69% of the route total. Aerial attachment agreements are executed with the 9 different utility pole owners throughout the state. Make ready work has begun on 184 miles of the 331 mile planned aerial route. Of that total, 65 miles have been completed and installed with fiber. Material procurement continues with $4,668,439 of fiber received, or 43% of the total contract award valued at $10,819,850. In addition to the $4,678,794 reported as spent for equipment during 2012 Q2, we placed orders in Q2 (but not included in a drawdown request yet) a total of $7,948,791.43 in network electronics that we expect will be invoiced and included in Q3 reporting. Much of this equipment has already been received. Of the total 1080 planned underground miles, 670 miles of conduit have been installed or 62% of the total underground mileage. Of that total, 291 miles of fiber have been installed, representing 27% of our total underground mileage. Finally, 40 Community Anchor Institutions (CAIs) sites have been connected out of 1006 CAIs. Of the 23 Counties and 1 City, Construction has been completed for Talbot County and all it's 3 CAIs are connected. Construction is in full swing in the remaining 21 counties and 1 City: Allegany Co, Anne Arundel Co, Baltimore Co, Baltimore City, Calvert Co, Caroline Co, Carroll Co, Cecil Co, Fredrick Co, Dorchester Co, Garrett Co, Harford Co, Howard Co, Kent Co, Montgomery Co, Prince George's Co, Queen Anneâ€™s Co, Saint Maryâ€™s Co, Somerset Co, Washington Co, Wicomico Co, and Worcester Co. | 356 | 0 | 254 | 0 | 356 | 0 | 0 | 6 | Planned was 414. Now that construction is currently ongoing in all counties, we anticipate meeting our goals during the next reporting quarter. We have installed over 670 miles of conduit and begun 184 miles of aerial make ready work. These numbers are not captured in our reports since we do not report them until fiber is pulled and spliced. | N/A | This mileage represents the MdBC in kind fiber contribution to the project. | N/A | Planned was 414. Now that construction is currently ongoing in all counties, we anticipate meeting our goals during the next reporting quarter. We have installed over 670 miles of conduit and begun 184 miles of aerial make ready work. These numbers are not captured in our reports since we do not report them until fiber is pulled and spliced. | N/A | N/A | 29 interconnection point were planned. The buildout has not yet reached most of the planned interconnection points. | 9 | 15 | 24 | MdBC is our wholesale provider and signed agreements have been signed with the following last mile providers: ISPs (6 circuits): Utilities (2 circuits): Cooperatives (1 circuit): | N/A | N/A | 0 | 9 | 0 | 0 | N/A | Currently we have signed 9 agreements with wholesalers receiving improved access. | Planned was 3. At least 1 agreement is being negotiated. | N/A | 40 | 40 | 0 | 2 | Planned was 262. Now that construction is actively ongoing in all 24 counties, the number of subscribers served will increase during the next reporting quarters. 1GB of high-speed internet access is available to the current subscribers being served. | Planned was 262. Now that construction is actively ongoing in all 24 counties, the number of subscribers served will increase during the next reporting quarters. 1GB of high-speed internet access is available to the current subscribers being served. | N/A | 39- CAIs at 1GB 1-CAI at 100 Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The project has fully transitioned to the construction phase in every county in the state of Maryland. The following are our projected indicators for the next reporting quarter. Engineering: â€¢ Outside-Plant engineering is coming to a closure. The next phase is the logical network engineering which continues to ramp up. Permitting : â€¢ Rights of Way (ROW) permitting: At least 76% of the underground and aerial permits will have been received from State Highway Administration (SHA), county, and municipal authorities. â€¢ Aerial Utility permitting: We continue to submit aerial permit applications to the various utility companies and anticipate receiving pole attachment liscenses throughout the next reporting period. The utility companies include; Baltimore Gas and Electric (BGE), Verizon, Potomac Edison, Delmarva Power, PEPCO, Hagerstown Light, Berlin Electric, and Choptank Electric. We expect to cut make ready checks to the utilities for 80% of our aerial route. â€¢ Environmental: We've been receiving permits from the US Army Corps of Engineers (USACE) and Maryland Department of Environment (MDE) for tidal and non-tidal wetlands crossings. This will be an ongoing process throughout the construction phase. We have begun construction across several permitted environmental resource areas. â€¢ Rail Road Crossings: We have executed licensing agreements with all railroad companies; CSX, Maryland & Delaware Rail Road, Maryland Midland Rail Ways, Bay Coast Rail Road, Amtrak, George's Creek, and Metropolitan Transit Authority (MTA), Norfolk Southern Corporation. We are currently receiving and anticipate to continue to receive the encroachment agreements with the various Maryland Operating Rail Systems owners, allowing us to construct across their various railroad crossing locations throughout the State of Maryland. Total Apps. Submitted Received Completed Amtrak 7 6 6 1 Bay Coast 2 2 2 2 CSX 39 36 26 15 George's Creek 4 4 4 4 Norfolk Southern 1 0 0 0 Maryland Delaware 2 2 2 2 Maryland Midland 4 4 4 3 MTA 8 7 6 0 TOTALS 67 61 50 27 Fiber Procurement: â€¢ Fiber procurement is winding down and the final deliveries are scheduled throughout the next couple of reporting periods. We expect continued receipt of fiber and related materials at our centralized warehouse locations in sufficient quantities to prevent construction delays. Equipment Procurement: â€¢ Continue the procurement of the OMBN equipment, with over $11M in cumulative equipment purchases will be made within the next reporting quarter. Construction Completion: â€¢ Construction will be completed for Talbot and Charles County. â€¢ Construction is in full swing in the remaining 22 counties and 1 City: Allegany Co, Anne Arundel Co, Baltimore Co, Baltimore City, Calvert Co, Caroline Co, Carroll Co, Cecil Co, Frederick Co, Dorchester Co, Garrett Co, Harford Co, Howard Co, Kent Co, Montgomery Co, Prince George's Co, Queen Anneâ€™s Co, Saint Maryâ€™s Co, Somerset Co, Washington Co, Wicomico Co, and Worcester Co. Key project Indicators: a. New network miles deployed= 711 b. New network miles leased= 0 c. Total CAI subscribers served (CAIs connected)= 378 d. Number of signed agreements with broadband wholesalers or last mile providers= 9 | Information Technology, Maryland Department of | 1) One of our main challenges for this reporting quarter was obtaining make ready estimates from the utility companies in a timely manner. With the recent storms (El Derecho) the priority of the utility companies is geared towards restoring power and replacing damaged or broken utility poles. We have weekly meetings with the utility companies to aggressively manage the make ready process. 2) A second challenge is the finalization of easements and permits to place Communication Huts in some locations i.e. Annapolis, La Plata and Aberdeen. | The following issues may cause some challenges, 1) With the recent storms (El Derecho) and major power outage, the priority of the utility companies is geared towards restoring power and replacing damaged or broken utility poles. This may lead to limited resources allocated to the OMBN project pole make ready needs. We have weekly conference calls with the utility companies to aggressively manage the make ready process. 2) Receiving approvals for our second round of scope and environmental change requests before our construction progress is impacted. | TRUE
NT10BIX5570135 | 2012 | Q3 | Q3 - 2012 | The project is in construction in every county in the state of Maryland. Of the planned 1368 route miles, 99%, or 1360, miles have been awarded to engineering vendors. Of that total, 1322 miles, or 97% of the route total, have been fully engineered and submitted to permitting agencies. Permits have been received for over 1060 route miles or 77% of the route total. Aerial attachment agreements have been executed with the 9 utility pole owners throughout the state. Make ready work has begun on 260 miles of the 314 mile planned aerial route. Of that total, 89 miles have been completed and installed with fiber. Of the total 1054 planned underground miles, 828 miles of conduit have been installed or 79% of the total underground mileage. Of that total, 629 miles of fiber have been installed, representing 60% of our total underground mileage. Construction has been completed for: -Talbot County and the 3 CAIs are connected -Charles County and the 8 CAIs are connected Construction is in full swing in the remaining 22 counties and 1 City: Allegany Co, Anne Arundel Co, Baltimore Co, Baltimore City, Calvert Co, Caroline Co, Carroll Co, Cecil Co, Fredrick Co, Dorchester Co, Garrett Co, Harford Co, Howard Co, Kent Co, Montgomery Co, Prince George's Co, Queen Anneâ€™s Co, Saint Maryâ€™s Co, Somerset Co, Washington Co, Wicomico Co, and Worcester Co. Overall, 718 miles of fiber has been deployed out of the planned 1368 route miles, or 52% of the total. Additionally 128 Community Anchor Institutions (CAIs) sites have been connected out of 1006 CAIs (cumulative). | 718 | 0 | 254 | 0 | 718 | 0 | 0 | 21 | Planned was 569. We have installed over 828 miles of conduit and begun 260 miles of aerial make ready work. These numbers are not captured in our reports since we do not report them until fiber is pulled and spliced. | N/A | This mileage represents the MdBC in kind fiber contribution to the project. | N/A | Planned was 569. We have installed over 828 miles of conduit and begun 260 miles of aerial make ready work. These numbers are not captured in our reports since we do not report them until fiber is pulled and spliced. | N/A | N/A | 31 interconnection points were planned. The build-out has not yet reached most of the planned interconnection points. | 10 | 33 | 24 | Agreements have been signed with the following last mile providers: ISPs (6 circuits): AboveNet (3 circuits), Atlantic Broadband, Bay Country Communications, FiberLight Utilities (2 circuits): Easton Utilities (2 circuits) Cooperatives (1 circuit): Eastern Shore of Virginia Broadband (1 circuit) Broadstripe (Agreement for dark fiber signed with Anne Arundel County to provide last mile services to approximately 600 unserved residences) | N/A | N/A | 0 | 10 | 0 | 0 | N/A | Currently we have signed 10 agreements with wholesalers receiving improved access | Planned was 3. At least 1 agreement is being negotiated. | N/A | 128 | 128 | 0 | 128 | Planned was 443. Now that construction is actively ongoing in all 24 counties, the number of subscribers served will increase during the next reporting quarters. 1GB of high-speed internet access is available to the current subscribers being served. | Planned was 443. Now that construction is actively ongoing in all 24 counties, the number of subscribers served will increase during the next reporting quarters. 1GB of high-speed internet access is available to the current subscribers being served. | N/A | 127- CAIs at 1GB 1-CAI at 100 Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The project will transition from fiber deployment to connecting CAIs. The following are our projected indicators for the next reporting quarter. Engineering: â€¢ Outside-Plant engineering will come to a closure. The engineering effort will focus on the logical network design and implementation, which continues to ramp up. Permitting : â€¢ Rights of Way (ROW) permitting: At least 95% of the underground and aerial permits will have been received from State Highway Administration (SHA), county, and municipal authorities. â€¢ Aerial Utility permitting: 95 % of aerial make ready payments will have been made to the utility companies. We will have received over 200 miles of pole attachment licenses and anticipate to continue to receive pole attachment licenses throughout the next reporting period. The utility companies include; Baltimore Gas and Electric (BGE), Verizon, Potomac Edison, Delmarva Power, PEPCO, Hagerstown Light, Berlin Electric, and Choptank Electric. â€¢ Environmental: We've been receiving permits from the US Army Corps of Engineers (USACE) and Maryland Department of Environment (MDE) for tidal and non-tidal wetlands crossings. All tidal crossing permitting is completed. Non-tidal wetland permitting will continue throughout the construction phase. We have begun construction across several permitted environmental resource areas. â€¢ Rail Road Crossings: We have executed licensing agreements with all railroad companies; CSX, Maryland & Delaware Rail Road, Maryland Midland Rail Ways, Bay Coast Rail Road, Amtrak, George's Creek, and Metropolitan Transit Authority (MTA), Norfolk Southern Corporation. We will continue to receive the encroachment agreements with the various Maryland Operating Rail Systems owners. Total Crossings Submitted Received Completed Amtrak 6 6 6 6 Bay Coast 2 2 2 2 CSX 38 37 36 25 George's Creek 4 4 4 4 Norfolk Southern 2 2 2 1 Maryland Delaware 2 2 2 2 Maryland Midland 4 4 4 4 MTA 8 8 8 7 TOTALS 66 65 64 51 Fiber Procurement: â€¢ Fiber procurement is winding down and the final deliveries are scheduled throughout the next couple of reporting periods. We expect continued receipt of fiber and related materials at our centralized warehouse locations in sufficient quantities to maintain the construction schedule. Equipment Procurement: â€¢ Continue the procurement of the OMBN equipment, with over $10M in cumulative equipment purchases will be made within the next reporting quarter. Construction Completion: â€¢ Construction will have been completed for Talbot, Charles, Calvert, Dorchester, Harford Counties. â€¢ Construction is in full swing in the remaining 19 counties and 1 City: Allegany Co, Anne Arundel Co, Baltimore Co, Baltimore City, Caroline Co, Carroll Co, Cecil Co, Frederick Co, Garrett Co, Howard Co, Kent Co, Montgomery Co, Prince George's Co, Queen Anneâ€™s Co, Saint Maryâ€™s Co, Somerset Co, Washington Co, Wicomico Co, and Worcester Co. Key project Indicators: a. New network miles deployed= 900 b. New network miles leased= 0 c. Total CAI subscribers served (CAIs connected)= 450 d. Number of signed agreements with broadband wholesalers or last mile providers= 12 | Information Technology, Maryland Department of | The past quarter saw tremendous progress in fiber placement in newly constructed underground conduit, as well as a rapid increase in the rate of CAI connections. There are no major challenges impeding overall conduit placement and fiber construction, and we expect to be able to continue at recent rates of production. However, there are certain location-specific challenges that are being managed actively: 1. Permits and easements for private and municipal crossings â€“ while still within anticipated time frames, the processes requiring legal review among the participant jurisdictions and either private land owners or municipal permitting authorities continue to represent the longer lead-time items over which the project team has less direct control. The vast majority of agreements required for gas pipeline crossings, railroad crossings, and municipal permitting have been executed, with few outstanding agreements remaining. 2. Utility pole make-ready engineering and construction costs â€“ unexpectedly high costs for make-ready construction required for utility pole attachments continue to drive designs towards underground construction, creating minor delays associated with revising engineering plans and validating costs assessed by utility pole owners. We believe the full extent of these challenge areas have been identified and are being actively addressed. | The next quarter will likely see challenges in the following three areas: 1. Weather-related delays â€“ the impact of the impending Hurricane Sandy is not yet known, but expected to be severe. Widespread damage to aerial infrastructure will pull utility crews off of the project make ready work and be redirected to storms repairs. During the July El Derecho storm, Utility crews were unavailable to the project for 3 weeks. This storm is expected to be worse. Additionally, heavy snow is expected in Garrett County, Western Maryland, which will halt all operations until it melts. 2. Permits and easements for private and municipal crossings â€“ the processes requiring legal review among the participant jurisdictions and either private land owners or municipal permitting authorities continue to represent the longer lead-time items over which the project team has less direct control. 3. Utility pole make-ready construction â€“ while now representing a relatively small portion of the project, we anticipate there will be challenges coordinating with the utility pole make-ready work in a manner that avoids interruptions in aerial fiber construction. This work must be completed prior to aerial fiber construction by the utility pole owners, rather than our own contractors, and as such represents an area of risk that can be impacted by labor disputes, weather emergencies, and other extenuating factors outside our direct control. | TRUE
NT10BIX5570135 | 2012 | Q4 | Q4 - 2012 | The project is in full construction mode in every county in the state of Maryland. Of the planned 1360 route miles, 100% of the miles have been awarded, engineered, and submitted to permitting agencies. Permits have been received for over 1185 route miles or 87% of the route total. Aerial attachment agreements have been executed with the 9 utility pole owners throughout the state. Make ready work has begun on 305 miles of the 318 mile planned aerial route. Of that total, 177 miles have been completed and installed with fiber. Of the total 1042 planned underground miles, 897 miles of conduit have been installed or 86% of the total underground mileage. Of that total, 822 miles of fiber have been installed, representing 79% of our total underground mileage. Construction has been completed in 4 counties: Caroline Co, Calvert Co, Charles Co., and Talbot Co. Construction is in full swing in the remaining 19 counties and 1 City: Anne Arundel Co, Allegany Co, Baltimore Co, Baltimore City, Carroll Co, Cecil Co, Fredrick Co, Dorchester Co, Garrett Co, Harford Co, Howard Co, Kent Co, Montgomery Co, Prince George's Co, Queen Anneâ€™s Co, Saint Maryâ€™s Co, Somerset Co, Washington Co, Wicomico Co, and Worcester Co. Overall, 999 miles of fiber have been deployed out of the planned 1360 route miles, or 73% of the total. Additionally 289 Community Anchor Institutions (CAIs) sites have been connected out of 1006 CAIs (cumulative). | 999 | 0 | 254 | 0 | 999 | 0 | 0 | 21 | Planned was 815. | N/A | This mileage represents the MdBC & DoIT in kind fiber contribution to the project. | N/A | Planned was 815. | N/A | N/A | 37 interconnection points were planned. The build-out has not yet reached most of the planned interconnection points. | 11 | 42 | 24 | Agreements have been signed with the following last mile providers: ISPs (6 circuits): AboveNet (3 circuits), Atlantic Broadband, Bay Country Communications, FiberLight Utilities (2 circuits): Easton Utilities (2 circuits) Cooperatives (2 circuit): Eastern Shore of Virginia Broadband (2 circuit) Broadstripe (1 circuits): Agreement for dark fiber signed with Anne Arundel County to provide last mile services to approximately 600 unserved residences | N/A | N/A | 0 | 10 | 1 | 11 | N/A | Currently we have signed 10 agreements with wholesalers receiving improved access | Planned was 4. At least 1 agreement is being negotiated. | We can offer services between 10Mgps and 40Gbps, of the 11 signed agreement(s) the speed tiers are as follows: 9= 1G 2= 10G | 289 | 289 | 0 | 289 | Planned was 594. Now that construction is actively ongoing in all 24 counties, the number of subscribers served will increase during the next reporting quarters. | Planned was 594. Now that construction is actively ongoing in all 24 jurisdictions, the number of subscribers served will increase during the next reporting quarters. | N/A | 288- CAIs at 1GB 1-CAI at 100 Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The following are our projected indicators for the next reporting quarter. â€¢ Aerial Utility permitting: 100% of aerial make ready payments will have been made to the utility companies. We expect to receive all pole attachment licenses during the next reporting quarter. The utility companies include; Baltimore Gas and Electric (BGE), Verizon, Potomac Edison, Delmarva Power, PEPCO, Hagerstown Light, Berlin Electric, and Choptank Electric. â€¢ Environmental: We've been receiving permits from the US Army Corps of Engineers (USACE) and Maryland Department of Environment (MDE) for tidal and non-tidal wetlands crossings. All tidal crossing permitting is completed. Non-tidal wetland permitting will continue throughout the construction phase. â€¢ Rail Road Crossings: We have executed licensing agreements with all railroad companies; CSX, Maryland & Delaware Rail Road, Maryland Midland Rail Ways, Bay Coast Rail Road, Amtrak, George's Creek, and Metropolitan Transit Authority (MTA), Norfolk Southern Corporation. We will continue to receive the encroachment agreements with the various Maryland Operating Rail Systems owners. We expect to have executed 57 of 60 total required railroad agreements by the end of the next quarter, as shown in the table below: Total Crossings Submitted Received Completed Amtrak 6 6 6 6 Bay Coast 2 2 2 2 CSX 32 32 32 29 George's Creek 5 5 5 5 Norfolk Southern 1 1 1 1 Maryland Delaware 2 2 2 2 Maryland Midland 4 4 4 4 MTA 8 8 8 8 TOTALS 60 60 60 57 Fiber Procurement: â€¢ Fiber procurement will be completed in Q1-2013. Construction will be completed in 7 counties: Caroline Co, Calvert Co, Charles Co., Harford Co., Somerset Co.,Talbot Co. Wicomico Co. Construction will continue in the remaining 16 counties and 1 City: Anne Arundel Co, Allegany Co, Baltimore Co, Baltimore City, Carroll Co, Cecil Co, Fredrick Co, Dorchester Co, Garrett Co, Howard Co, Kent Co, Montgomery Co, Prince George's Co, Queen Anneâ€™s Co, Saint Maryâ€™s Co, Washington Co, and Worcester Co. Key project Indicators: a. New network miles deployed= 1,200 b. New network miles leased= 0 c. Total CAI subscribers served (CAIs connected)= 600 d. Number of signed agreements with broadband wholesalers or last mile providers= 12 | Information Technology, Maryland Department of | The past quarter saw tremendous progress in fiber installation, both aerial & underground, as well as a rapid increase in the rate of CAI connections. However, we faced and overcame challenges in the following areas: 1. Weather-related delays: The impact of Hurricane Sandy resulted in a three week delay in our construction production as widespread damage to aerial infrastructure, both locally and regionally, pulled utility crews off of the project make ready work and were redirected for storm repairs. Additionally, heavy snow in Western Maryland halted all operations for 2 weeks. However we have recovered the schedule since the overall winter weather pattern has been favorable, allowing us to continue construction at a time when we anticipated a lull in construction due to winter. 2. Holiday season delays: Road lane closures for state and municipal construction were significantly limited during the holidays. However, we were ahead of schedule in obtaining agreements for gas pipeline crossings, railroad crossings, and municipal permits, mitigating holiday delays. | 1. Weather-related delays - Severe winter weather will significantly slow down progress for extended periods of time. Additionally, snow and ice storms can cause damage to existing infrastructure, requiring utility make ready construction resources to be diverted to making utility infrastructure repairs. 2. Utility pole make-ready construction â€“ while now representing a relatively small portion of the project, we anticipate there may be ongoing challenges with utility pole owners completing make-ready work on schedule. This make-ready work must be completed prior to aerial fiber construction. The make ready work is performed by the utility rather than our own contractors. We are concerned about potential labor strikes. 3. Final amendments to the Environmental Assessment â€“ As the construction begins to ramp down and certain design decisions finalized, we anticipate the need for a minor amendment to the Programâ€™s Environmental Assessment to cover any remaining changes. Timely responses from the various environmental authorities that will be consulted, as well as a timely approval by the NTIA will be necessary to minimize any delays to this final phase of construction. 4. Hut Installation - We have experienced significant difficulties in obtaining an acceptable easements from private and public sector partners. We are going to conclude easement discussions with the Counties in February. If we obtain positive results, we will have the fourteenth hut installed | TRUE
NT10BIX5570135 | 2013 | Q1 | Q1 - 2013 | With a couple of quarters remaining in the project the following are this quarter indicators. 100% of the planned route miles have been awarded, engineered, and submitted to permitting agencies. Aerial attachment agreements have been executed with the 9 utility pole owners throughout the state. Make ready work has been completed on 311 miles of the planned aerial route. Of that total, 253 miles have been completed and installed with fiber. Additionally 933 miles of conduit have been installed or 90% of the total underground mileage. Of that total, 895 miles of fiber have been installed, representing 86% of our total underground mileage. Of the 23 counties, construction has been completed in 6 counties: Caroline Co, Calvert Co, Charles Co., Queen Anneâ€™s Co, Somerset Co, and Talbot Co. Construction is in full swing in the remaining 17 counties and 1 City: Anne Arundel Co, Allegany Co, Baltimore Co, Baltimore City, Carroll Co, Cecil Co, Fredrick Co, Dorchester Co, Garrett Co, Harford Co, Howard Co, Kent Co, Montgomery Co, Prince George's Co, Saint Maryâ€™s Co, Washington Co, Wicomico Co, and Worcester Co. Overall, 1148 miles of fiber have been deployed, or 84% of the total. Additionally 692 Community Anchor Institutions (CAIs) sites or 65% have been connected (cumulative). Also, the NTIA and NOAA conducted their annual site visit with the One Maryland Broadband Network (OMBN) Recipient; Department of Information Technology (DoIT), and its Sub-recipients; Inter-County Broadband Network (ICBN), Maryland Broadband Cooperative (MdBC) and Frederick County, which took place from March 12-14, 2013 to discuss, review and ensure the program was complying with the terms and conditions of the grant award. The fundamental topics reviewed were: Organizational review, Construction Progress, Financial Management, Grant Management and Compliance, Davis Bacon, and Sales and Marketing processes. The OMBN team was able to successfully demonstrate scope, cost, grant compliance, procurement, and risk management throughout the program. The OMBN team also took the NTIA and NOAA to visit Queen Anneâ€™s County. A round table was held with the County CIO, Public School CIO, Department of Emergency Services and State of Maryland Deputy CIO. The county stakeholders demonstrated how the BTOP project brought them together to pool resources in a way they had not previously. The upgrade to the county infrastructure went from a shared wireless 20 Mbs connection to dedicated 1 Gbs links and a 10 Gbs backbone. NTIAâ€™s continued support and guidance throughout the project provides a road map to help us succeed by offing the various Webinars, BTOP new updates, and the continued involvement of our Federal Project Officer (FPO) and team. | 1148 | 0 | 254 | 0 | 1148 | 0 | 0 | 50 | Planned was 958. | N/A | This mileage represents the MdBC & DoIT in kind fiber contribution to the project. | N/A | Planned was 958. | N/A | N/A | Planned was 48 | 11 | 42 | 24 | Agreements have been signed with the following last mile providers: ISPs (6 circuits): AboveNet (3 circuits), Atlantic Broadband, Bay Country Communications, FiberLight Utilities (2 circuits): Easton Utilities (2 circuits) Cooperatives (2 circuit): Eastern Shore of Virginia Broadband (2 circuit) Broadstripe (1 circuits): Agreement for dark fiber signed with Anne Arundel County to provide last mile services to approximately 600 unserved residences | N/A | N/A | 0 | 10 | 1 | 11 | N/A | Currently we have signed 10 agreements with wholesalers receiving improved access. At least 42 agreement are being negotiated with broadband wholesalers or last mile providers. | Planned was 4. Currently we have signed 1 agreement with wholesalers receiving dark fiber. At least 1 agreement is being negotiated. | We can offer services between 10Mgps and 40Gbps, of the 11 signed agreement(s) the speed tiers are as follows: 9= 1G 2= 10G | 692 | 692 | 0 | 2 | Planned was 724. We expect to be on target next quarter. | Planned was 724. We expect to be on target next quarter. | N/A | 691- CAIs at 1GB 1- CAI at 100 Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The following are our projected indicators for the next reporting quarter. â€¢ Aerial Utility permitting: 100% of aerial make ready payments will have been made to the utility companies. We expect to receive the remaining pole attachment licenses during the next reporting quarter from the utility companies which includes; Baltimore Gas and Electric (BGE), Verizon, Potomac Edison, Delmarva Power, PEPCO, Hagerstown Light, Berlin Electric, and Choptank Electric. â€¢ Environmental: We've been receiving permits from the US Army Corps of Engineers (USACE) and Maryland Department of Environment (MDE) for tidal and non-tidal wetlands crossings. We expect to receive all tidal and wetland permits in the next quarter. â€¢ Rail Road Crossings: We have executed licensing agreements with all railroad companies; CSX, Maryland & Delaware Rail Road, Maryland Midland Rail Ways, Bay Coast Rail Road, Amtrak, George's Creek, and Metropolitan Transit Authority (MTA), Norfolk Southern Corporation. We will continue to receive the encroachment agreements with the various Maryland Operating Rail Systems owners. We expect to have executed 57 of 58 total required railroad agreements by the end of the next quarter, as shown in the table below: Total Crossings Submitted Received Completed Amtrak 6 6 6 6 Bay Coast 2 2 2 2 CSX 31 31 31 29 George's Creek 5 5 5 5 Norfolk Southern 1 1 1 1 Maryland Delaware 2 2 2 2 Maryland Midland 4 4 4 4 MTA 7 7 7 8 TOTALS 58 58 58 57 Fiber Procurement: â€¢ Fiber procurement will be completed in Q2-2013. Construction will be completed in 19 of the 23 counties and 1 City: Allegany Co, Baltimore City, Caroline Co, Carroll Co, Calvert Co, Charles Co, Dorchester Co, Garrett Co, Harford Co, Howard Co, Kent Co, Prince George's Co, Queen Anneâ€™s Co, Saint Maryâ€™s Co, Somerset Co, Talbot Co, Washington Co, Wicomico Co, Worcester Co. Construction will continue in the remaining 5 counties: Anne Arundel Co, Baltimore Co, Cecil Co, Fredrick Co, and Montgomery Co, Key project Indicators: a. New network miles deployed= 113 b. New network miles leased= 0 c. Total CAI subscribers served (CAIs connected)= 247 d. Number of signed agreements with broadband wholesalers or last mile providers= 5 | Information Technology, Maryland Department of | As the fiber construction nears completion, we saw tremendous progress in in the rate of CAI connections. Our key challenges were: 1. Utility pole make-ready construction (Delmarva Power & Light) â€“ We experienced some challenges with a utility pole owner which held up the release of the licenses to attach to their poles, which affected the completion of make-ready work as scheduled for the Eastern Shore region. While discussions between the utility owners and the state proceeded, our contractors were on stand by and available once the licenses were released, and as a result we were able to recover some of this delayed time and complete the required pole attachments. 2. Hut Installation - We experienced some difficulties in obtaining acceptable easements for 2 locations. With continued negotiations, a compromise was reached with the property owner resulting in the release of the required easement and installation of 1 Hut. | 1. Final approvals to the Environmental Assessment Round 3: We anticipate the approvals for the minor amendment / changes requested on the Programâ€™s Environmental Assessment package submitted to be finalized. We have consulted, acquired and submitted all approvals from the various environmental authorities to the NTIA. A timely approval by the NTIA is necessary to minimize any delays to this final phase of construction. | TRUE
NT10BIX5570135 | 2013 | Q2 | Q2 - 2013 | The project is entering the final project quarter. Of the planned 1339 route miles, 100% of the miles have been awarded, engineered, and permitted by various permitting agencies. Aerial attachment agreements have been executed with 9 different utility pole owners throughout the state. Make ready work has been completed on 314 miles of the 318 mile planned aerial route. Of that total, 307 miles have been completed and installed with fiber, representing 97% of the total planned aerial miles. Of the total 1022 planned underground miles, 986 miles of conduit have been installed or 96% of the total underground mileage. Of that total, 971 miles of fiber have been installed, representing 95% of our total underground mileage. Overall, 1278 miles of fiber have been deployed out of the planned 1339 route miles, or 95% of the total. Additionally 907 Community Anchor Institutions (CAIs) sites or 83% have been connected out of 1087 CAIs (cumulative). Of the 23 state counties, construction has been completed in 5: Caroline Co, Calvert Co, Charles Co., Howard Co, and Garrett Co. Construction is over 95% complete in the remaining 18 counties and 1 City: Anne Arundel Co, Allegany Co, Baltimore Co, Baltimore City, Carroll Co, Cecil Co, Fredrick Co, Dorchester Co, Harford Co, Kent Co, Montgomery Co, Prince George's Co, Queen Anneâ€™s Co, Saint Maryâ€™s Co, Talbot Co, Washington Co, Wicomico Co, and Worcester Co. | 1278 | 0 | 254 | 0 | 1278 | 0 | 0 | 50 | Planned was 1294 | N/A | This mileage represents the MdBC & DoIT in kind fiber contribution to the project. | N/A | Planned was 1294 | N/A | N/A | Planned was 59 | 12 | 56 | 24 | Agreements have been signed with the following last mile providers: ISPs (6 circuits): AboveNet (3 circuits), Atlantic Broadband, Bay Country Communications, FiberLight Utilities (2 circuits): Easton Utilities (2 circuits) Cooperatives (3 circuits): Eastern Shore of Virginia Broadband (3 circuit) Broadstripe (1 circuit): Agreement for dark fiber signed with Anne Arundel County to provide last mile services to approximately 600 unserved residences | N/A | N/A | 0 | 11 | 1 | 12 | N/A | Currently we have signed 11 agreements with wholesalers receiving improved access. At least 56 agreement are being negotiated with broadband wholesalers or last mile providers. | Planned was 4. Currently we have signed 1 agreement with wholesalers receiving dark fiber. At least 1 agreement is being negotiated. | We can offer services between 10Mgps and 40Gbps, of the 12 signed agreement(s) the speed tiers are as follows: 10= 1G 2= 10G | 907 | 907 | 0 | 2 | Planned was 1006. We expect to be on target next quarter. | Planned was 1006. We expect to be on target next quarter. | N/A | 906- CAIs at 1GB 1- CAI at 100 Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | The following are our projected indicators for the next and final reporting quarter. â€¢ Aerial Utility permitting: 100% of aerial make ready payments will have been made to the utility companies which includes; Baltimore Gas and Electric (BGE), Verizon, Potomac Edison, Delmarva Power, PEPCO, Hagerstown Light, Berlin Electric, and Choptank Electric. â€¢ Environmental: We will have received all required permits from the US Army Corps of Engineers (USACE) and Maryland Department of Environment (MDE) for tidal and non-tidal wetlands crossings (100%). â€¢ Rail Road Crossings: We will have executed licensing agreements with all railroad companies; CSX, Maryland & Delaware Rail Road, Maryland Midland Rail Ways, Bay Coast Rail Road, Amtrak, George's Creek, and Metropolitan Transit Authority (MTA), Norfolk Southern Corporation (100%). We expect to have all required railroad agreements executed by the end of the next quarter(100%), as shown in the table below: Total Crossings Submitted Received Completed Amtrak 6 6 6 6 Bay Coast 2 2 2 2 CSX 30 30 30 30 George's Creek 5 5 5 5 Norfolk Southern 1 1 1 1 Maryland Delaware 2 2 2 2 Maryland Midland 4 4 4 4 MTA 7 7 7 7 TOTALS 57 57 57 57 Fiber Procurement: â€¢ 100%, Procurement of all required fiber will have been completed. 100% of construction will be completed in all 23 counties and 1 City: Allegany Co, Anne Arundel Co, Baltimore City, Baltimore Co, Caroline Co, Carroll Co, Calvert Co, Cecil Co, Charles Co, Dorchester Co, Fredrick Co, Garrett Co, Harford Co, Howard Co, Kent Co, Montgomery Co, Prince George's Co, Queen Anneâ€™s Co, Saint Maryâ€™s Co, Somerset Co, Talbot Co, Washington Co, Wicomico Co, Worcester Co. Key project Indicators: a. New network miles deployed= 1339 b. New network miles leased= 0 c. Total CAI subscribers served (CAIs connected)= 1087 d. Number of signed agreement with broadband wholesalers or last mile providers= 11 | Information Technology, Maryland Department of | As the fiber construction nears completion, we saw tremendous progress in in the rate of CAI connections. Construction tasks related to final site connectivity and activation, such as fiber termination, fiber splicing, and equipment connectivity were and will continue to represent the bulk of our efforts through the end of the grant project. Our key challenge was maintaining momentum in the face of delays due to necessary EA change requests. Progress towards certain network connectivity tasks associated with the most recent Environmental Assessment Amendment were delayed while change request documentation was prepared and approvals received. We mitigated resulting delays to some degree by deploying splicing crews to locations where both backbone and laterals were already completed and previously approved. Due to the geographic dispersion of the required changes, it was impossible to completely contain the delays to discrete areas, and as a result, some delays were caused to construction progress for previously approved project scope. Consequently, construction work will continue into the last month of the grant award period. | We will commence out close procedures on September 1st. | TRUE
NT10BIX5570135 | 2013 | Q3 | Q3 - 2013 | All OMBN construction was concluded as of 8/31/13 and we are currently in our close-out project phase. The One Maryland Broadband Network (OMBN) project has built 1,324 miles of new fiber-optic cabling relative to its original baseline commitment of 1,294 miles, or 102% of goal. Building this infrastructure required permitting and construction of 57 railroad crossings from 8 different railway organizations, 21 tidal crossings, dozens of wetland crossings, 310 miles of aerial attachments across 8 different utilities, as well as permitting from many Right of Way owners, including; the State Highway Administration, 24 Counties and many Municipalities. The OMBN project has enabled access to broadband for 1,068 community anchor institutions (CAIs) or 106% of the original 1006 CAI goal. The success of this project will foster economic development, improved public safety interoperability and extend and interconnect existing networks; State (networkMaryland), multiple County networks, and the Maryland Broadband Cooperative. | 1324 | 0 | 254 | 0 | 1324 | 0 | 0 | 49 | Planned was 1294 | N/A | This mileage represents the MdBC & DoIT in kind fiber contribution to the project. | N/A | Planned was 1294 | N/A | N/A | Planned was 59. We had previously reported 50 but we had a duplicate in our count. | 12 | 56 | 24 | Agreements have been signed with the following last mile providers: ISPs (6 circuits): AboveNet (3 circuits), Atlantic Broadband, Bay Country Communications, FiberLight Utilities (2 circuits): Easton Utilities (2 circuits) Cooperatives (3 circuits): Eastern Shore of Virginia Broadband (3 circuit) Broadstripe (1 circuit): Agreement for dark fiber signed with Anne Arundel County to provide last mile services to approximately 600 unserved residences | N/A | N/A | 0 | 11 | 1 | 12 | N/A | We have11 agreements with wholesalers receiving improved access. At least 55 agreements are being negotiated with broadband wholesalers or last mile providers. | Planned was 4. Currently we have signed 1 agreement with wholesalers receiving dark fiber. | We can offer services between 10Mgps and 40Gbps, of the 12 signed agreement(s) the speed tiers are as follows: 10= 1G 2= 10G | 1068 | 1068 | 0 | 2 | Planned was 1006. | Planned was 1006. | N/A | 1067- CAIs at 1GB 1- CAI at 100 Mbps | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | OMBN Closeout The OMBN program has successfully completed the planned network of CAIâ€™s that were planned for the project. The total number of CAIs completed is 1068 with a total of miles done across the entire project being 1324. During the closeout process, the UCC-1â€™s were processed for all of the counties and entities involved in the project. All inventory and excess was accounted for on the various SF 428 forms and filed accordingly. Lastly, the prime recipient and the 3 subs are in the process of having single audits to be done that will be uploaded in the PAM system when they are respectively completed. | Information Technology, Maryland Department of | No additional challenges, final close-out process. | Final project close-out report. | TRUE
NT10BIX5570136 | 2010 | Q4 | Q4 - 2010 | Released first RFP for Environmental assessment; hired professional consultants in November 2010. Prepared and submitted 6-Month Expenditure plan for approval; expected first draw down in Q1 2011. Prepared and submitted 'Baseline Report' by 11/15/10; no major anticipated deviation expected. Working on Rights of Way and secured a meeting with Regional USFS to discuss project. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Still in Environmental Assessment | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 0 | 2 | 0 | No signed agreements to date. | Ds1, Ds3, Ethernet transport, and VIOP - pricing still being determined until after wholesale agreement with carrier is completed. | No third party operation of the network will occur. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | VOIP, Cloud computing, TelePresence, and a secure interoperable public safety channel for all 15 County government Emergency Services throughout the State of Arizona, that will also include connectivity to all Emergency Operation Centers (EOCs). | FALSE | n/a | Q3 of the project will be Jan - March 2011. DRAFT EA will be delivered to NTIA for review prior to Mar 01, 2011. A professional grant management firm will be in place to assist financial activity, and strict adherence to reporting and procurement standards. Release of several RFPs for site prep, concrete, construction, tower materials, shelters, and radio equipment is anticipated. IRU Lease for Community Interconnection Points at rural schools & libraries will be distributed (part of matching funds). Statewide outreach to stakeholders to continue. Anticipate meetings with neighboring tribal entities who received BTOP/BIP funds for possible collaboration. | GOVNET, INC. | GovNET's major challenge anticipated is with obtaining new federal rights of way in a timely manner. Our project was budgeted, and approved, on being able to build several new tower locations on existing, designated federal communication sites. Our core is built on public safety and providing federal security standards to our customers. USFS & BLM general policy is to push collocation. Unfortunately, our customers (County Emergency Dispatch Centers, State of Arizona, Dept of Emergency Management, AZ National Guard, Dept of Transportation, Dept of Corrections, and other government agencies) require secure remote physical & network facilities. Without obtaining new secure tower sites, these government customers may be lost, along with technical advances for their missions & large cost savings to taxpayers. | The most critical issue that will impact planned progress is issuance of federal Rights of Way, or communication site leases, from the United States Forest Service or Bureau of Land Management. Applications have been made, but unknown time frame of approval. These sites are the network Backbone, which need to be in place prior to providing service to CAIs. | TRUE
NT10BIX5570136 | 2011 | Q1 | Q1 - 2011 | Activities this quarter were focused on creating a Construction Program Plan, submitting the draft Environmental Assessment, outreach to communities, submitting the Overlap SAC, and continuing to pursue rights of ways and permits. Numerous milestones were accomplished, including the hiring of key staff and consultants. GovNET staff met with stakeholders throughout the State of Arizona, including the Navajo Tribal Utility (neighboring BTOP grantee), Northern Arizona Council of Governments, Department of Emergency Management, County School associations and Public Safety entities to coordinate and do outreach for the project. Activities are now focused on creating & releasing RFPs, obtaining lease agreements from the Community Anchor Institutions, and continued finalization of the Environmental Assessment. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance from baseline plan. | n/a | n/a | n/a | n/a | No variance from baseline plan. | No variance from baseline plan. | No variance from baseline plan. | 0 | 2 | 0 | No agreements with wholesalers have been signed, but two are in process. | The project is expected to provide the following wholesale services: Ds1, Ds3, Ethernet Transport and VOIP. Pricing for services has not yet been finalized but will be competitive with current market rates. | No third-party operators will be used on this project. | 0 | 0 | 0 | 0 | n/a | No variance from baseline plan. | n/a | 10 Mbps = 45 subscribers; 45 Mbps = 10 subscribers | 0 | 0 | 0 | 0 | No variance from baseline plan. | n/a | No variance from baseline plan. | 5 Mbps = 231 subscribers; 10 Mbps = 40 subscribers; ; 45 Mbps = 10 subscribers | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | No variance from baseline plan. | No variance from baseline plan. | n/a | No variance from baseline plan. | 10 Mbps = 4 subscribers; These are national cellular carriers in multiple markets in AZ. | VOIP, Cloud Computing, TelePresence, secure interoperable public safety channel for all 15 County Government Emergency Services, including connectivity to all Emergency Service Centers. | FALSE | n/a | In the next quarter, the Environmental Assessment will be resubmitted to NTIA for final review and approval. With a comprehensive Construction Project Plan in place, we expect to make significant strides in the purchase of equipment and hardware including, concrete, tower materials, shelters and radio equipment. Contracts will be awarded for site surveys and staking for towers. Architectural engineering and construction diagrams will be completed. 20% percent of IRU Leases for Community Interconnection Points are expected to be secured. GovNET staff will continue statewide outreach to stakeholders, including Arizona Association of County School Superintendents, Arizona Department of Administration, Arizona Department of Justice, the Department of Homeland Security, the U.S. Forest Service, BLM, Navajo Tribal Utility (neighboring BTOP grantee), Northern Arizona Council of Governments, and the Department of Emergency Management. GovNET will hire additional staff, including a Community Outreach Director and two Lead Construction Managers. We expect to purchase and move into our Network Operations Center (NOC). Activities are now focused on securing further rights of way, obtaining additional lease agreements from the Community Anchor Institutions, coordinating with Tribes and releasing RFPs for equipment and hardware in anticipation of beginning construction in June 2011. | GOVNET, INC. | The biggest challenge has been completing the Environmental Assessment in a timely manner. Construction cannot begin until the Environmental Assessment is approved and a FONSI issued. An issue we did not foresee is the difficulty in obtaining timely rights of way and use of tower locations on public lands managed by the U.S. Forest Service and BLM. We have requested and received technical assistance from the BTOP grant manager to address these challenges. | We are making good progress and do not anticipate any significant barriers to achieving the milestones of our Baseline Plan. The two issues with potential to impact the project are 1.) delayed approval of the Environmental Assessment and issuance of FONSI and 2.) siting facilities on public land. Construction on the project cannot move forward until the FONSI is approved. Gaining all the necessary approval from the U.S. Forest Service and BLM for tower sites has been very difficult, as their preference is co-location. GovNET customers, including the Department of Corrections, the Department of Homeland Security, and other government agencies require secure, remote physical and network facilities. If secure, structurally-sound tower sites are not obtained, then we may lose some government customers. Since construction has been delayed until the EA is approved, we have made adjustments to the construction schedule. Construction was originally scheduled to begin in April 2011, and now will not begin until June 2011 at the earliest. | TRUE
NT10BIX5570136 | 2011 | Q2 | Q2 - 2011 | Activities this quarter were focused on finalizing the technology requirements for the network, responding to comments on the Environmental Assessment, contracting and performing due diligence on Network Operations Center, submitting a re-budget Award Action Request, meeting with tribal entities, and requesting an extension for the pre-FONSI budget. In May, GovNET submitted a Performance Improvement Plan and in June, GovNET purchased a Network Operations Center (NOC). The NOC includes a warehouse area for equipment assembly needs prior to deployment. GovNET has moved its offices into the Network Operations Center. GovNET is in the process of responding to comments on the Overlap SAC map. Numerous milestones were accomplished, including hiring of key staff and releasing several RFPs. GovNET staff continued to meet with stakeholders throughout Arizona, including: Gila River Indian Community, Navajo Tribal Utility Authority, Northern Arizona Council of Governments, Western Arizona Council of Governments, AZ Dept. of Emergency Management, County school associations and public safety entities to coordinate and do outreach for the project. GovNET staff also met with Arizona Congressional Representatives in Washington, D.C. to explain the project and its potential impact to constituents. Activities are still very focused on securing rights of way, obtaining lease agreements from the Community Anchor Institutions (CAIs) and coordinating with Tribes throughout the state. The fol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Behind baseline plan due to delays in getting FONSI. | No variance from the baseline plan. | n/a | n/a | n/a n/a | No variance from the baseline plan. | Behind baseline plan due to delays in getting FONSI. | Behind baseline plan due to delays in getting FONSIs in getting FONSI. | 0 | 2 | 0 | No agreements with wholesalers have been signed, but two are in process and preliminary discussions have occurred for another. | The project is expected to provide the following wholesale services: Ds1, Ds3, Ethernet Transport and VOIP. Pricing for services has not been determined but will be competitive with current market rates.3 | No third-party operators will be used on this project. | 0 | 0 | 0 | 0 | No variance from baseline plan. | Behind baseline plan due to delays in getting FONSI. | n/a | 10 Mbps = 45 subscribers; 45 Mbps = 10 subscribers | 0 | 0 | 0 | 0 | Behind baseline plan due to delays in getting FONSI. | n/a | Behind baseline plan due to delays in getting FONSI. | 5 Mbps = 231 subscribers; 10 Mbps = 40 subscribers; ; 45 Mbps = 10 subscribers | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | Behind baseline plan due to delays in getting FONSI. | Behind baseline plan due to delays in getting FONSI. | n/a | Behind baseline plan due to delays in getting FONSI. | 10 Mbps = 4 subscribers; These are national cellular carriers in multiple markets in AZ. | VoIP, cloud computing, distance learning, video conferencing, secure interoperable public safety channel for all 15 County Government Emergency Services, including connectivity to all Emergency Operations Centers. | FALSE | n/a | In the next quarter, the Environmental Assessment will be sent to other federal agencies for comment, and to NTIA for final review and approval. We expect to release additional RFPs for equipment and hardware including, concrete, tower materials, shelters and radio equipment. Additional leases for Community Interconnection Points at CAIs are expected to be secured. GovNET staff will continue statewide outreach to stakeholders, including Arizona Association of County School Superintendents, Arizona Department of Administration, Arizona Department of Justice, the Department of Homeland Security, the U.S. Forest Service, BLM, Navajo Tribal Utility (neighboring BTOP grantee), Northern & Western Arizona Council of Governments, and the Department of Emergency Management. We expect to hire a Community Outreach Director and a Lead Construction Manager. We expect to begin modification of the Network Operations Center (NOC). Activities are now focused on securing further rights of way, obtaining additional lease agreements from the Community Anchor Institutions, finalizing technology requirements, and releasing RFPs for equipment and hardware in anticipation of construction beginning in Fall 2011. | GOVNET, INC. | The biggest challenges have been centered around 1.) completing the Environmental Assessment with the 321 total network sites, 2.)the multi-agency land ownership/management involvement, and 3.) multiple tribal consultations required in Arizona. Construction cannot begin until the Environmental Assessment is approved by all agencies involved. Each agency has different NEPA concerns and it is taking time to work through these. GovNET requested and received technical assistance from the BTOP grant manager to address these challenges. GovNET postponed hiring a Community Outreach Director and Lead Construction Manager due to delays in receiving the FONSI. | We are making good progress toward achieving the milestones of our Baseline Plan. The issue with the greatest impact on the project progress has been the delayed approval of the Environmental Assessment/ FONSI. Construction on the project cannot move forward until the FONSI is approved. Since construction has been delayed until the EA is approved, we have made adjustments to the construction schedule. Construction was originally scheduled to begin in April 2011, and will not begin until, at the earliest, September 2011. Looking forward, GovNET will be adapting the construction schedule around uncontrollable seasonal challenges with weather and mountain site variables. | TRUE
NT10BIX5570136 | 2011 | Q3 | Q3 - 2011 | Delay of the FONSI determination has led GovNET to remain very focused on working with Federal agencies in the project area to review the Environmental Assessment, which was resubmitted to the NTIA in September 2011. GovNET is still waiting on its FONSI determination, which will allow construction activities to begin. Other activities performed by GovNET this quarter included finalizing the technology requirements for the network, securing rights of way, obtaining lease agreements from community anchor Institutions, coordinating with Tribes, and responding to comments on the Overlap SAC map. Numerous site surveys were completed and tower sites were mapped. Several pre-construction site visits at community anchor institutions were completed. Several appraisals required for match documentation, including appraisals for the six backbone tower sites, were completed. Appraisals of all other tower sites are expected to be completed by the end of the next quarter. Also this quarter, the Arizona Land Department provided three new backbone site leases. GovNET staff continued to meet with stakeholders throughout Arizona, including the Bureau of Indian Affairs, Grand Canyon/National Park staff, the University of Arizona, county school associations and public safety entities to coordinate and do outreach for the project. GovNET also gave multiple webinars to community anchor institutions, specifically the libraries throughout the state. On August 30-Sept 2, 2011, GovNET staff attend | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Behind baseline plan due to delays in getting FONSI. In 2012, multiple tower construction crews will be utilized to make up for lost time. GovNET expects to be back in sync with its Baseline Plan by the end of Y2 Q4. | n/a | n/a | n/a | n/a | Behind baseline plan due to delays in getting FONSI. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | Behind baseline plan due to delays in getting FONSI. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | Narrative (describe your reasons for any variance from the baseline plan or any other relevant information) Behind baseline plan due to delays in getting FONSI. In 2012, multiple tower construction crews will be utilized to make up for lost time. GovNET expects to be back in sync with its Baseline Plan by the end of Y2 Q4. Behind baseline plan due to delays in getting FONSI. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. Behind baseline plan due to delays in getting FONSI. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. Behind baseline plan due to delays in getting FONSI. Expect to be back in sync with Baseline Plan by the end of Y2 Q4s for any variance from the baseline plan or any other relevant information) Behind baseline plan due to delays in getting FONSI. In 2012, multiple tower construction crews will be utilized to make up for lost time. GovNET expects to be back in sync with its Baseline Plan by the end of Y2 Q4. Behind baseline plan due to delays in getting FONSI. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. Behind baseline plan due to delays in getting FONSI. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. Behind baseline plan due to delays in getting FONSI. Expect to be back in sync with Baseline Plan by the end of Y2 Q4. | 0 | 2 | 0 | No agreements with wholesalers have been signed, but two are in process and preliminary discussions have occurred for another. | The project is expected to provide the following wholesale services: Ds1, Ds3, Ethernet Transport and VOIP. Pricing for services has not been determined but will be competitive with current market ratese the following wholesale services: Ds1, Ds3, Ethernet Transport and VOIP. Pricing for services has not been determined but will be competitive with current market rates. | No third-party operators will be used on this project. | 0 | 0 | 0 | 0 | No variance from baseline plan. | Behind baseline plan due to delays in getting FONSI. In 2012, multiple tower construction crews will be utilized to make up for lost time. Expect to be back in sync with its Baseline Plan by the end of Y2 Q4. | n/a | 10 Mbps = 45 subscribers; 45 Mbps = 10 subscribers | 0 | 0 | 0 | 0 | Behind baseline plan due to delays in getting FONSI. In 2012, multiple tower construction crews will be utilized to make up for lost time. Expect to be back in sync with its Baseline Plan by the end of Y2 Q4. | n/a | Behind baseline plan due to delays in getting FONSI. In 2012, multiple tower construction crews will be utilized to make up for lost time. Expect to be back in sync with its Baseline Plan by the end of Y2 Q4. | Anticipated: 5 Mbps = 231 subscribers; 10 Mbps = 40 subscribers; 45 Mbps = 10 subscribers | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 10 Mbps = 4 subscribers; These are national cellular carriers in multiple markets in AZ. | 0 | 0 | 0 | 0 | 0 | Behind baseline plan due to delays in getting FONSI. In 2012, multiple tower construction crews will be utilized to make up for lost time. Expect to be back in sync with its Baseline Plan by the end of Y2 Q4. | Behind baseline plan due to delays in getting FONSI. In 2012, multiple tower construction crews will be utilized to make up for lost time. Expect to be back in sync with its Baseline Plan by the end of Y2 Q4. | n/a | Behind baseline plan due to delays in getting FONSI. In 2012, multiple tower construction crews will be utilized to make up for lost time. Expect to be back in sync with its Baseline Plan by the end of Y2 Q4. | 10 Mbps = 4 subscribers; These are national cellular carriers in multiple markets in AZ. | VoIP, cloud computing, distance learning, video conferencing, secure interoperable public safety channel for all 15 County Government Emergency Services, including connectivity to all Emergency Operations Centers. | FALSE | n/a | GovNET expects to receive a FONSI determination and begin construction immediately as allowed. An Implementation Manager and a Construction Manager and Construction/Project Management Team will be hired. A remodel of the Network Operations Center, which serves and the monitoring and control center for the project, will begin and continue throughout the next quarter. GovNET staff plan to attend the Library Association's annual conference to further explain the project and communicate the benefits. Next quarter, we expect to make progress on the following key indicators: â€¢ New network miles deployed = 0 â€¢ New network miles leased = 0 â€¢ Total CAI subscribers served (CAIs connected) = 0 â€¢ Number of signed agreements with broadband wholesalers or last mile providers = 1 GovNET must receive the FONSI in order to begin construction. These key indicators are linked to construction. For this reason, we do not expect to catch up to the Baseline Plan until Y2 Q4. | GOVNET, INC. | The biggest challenges have been centered around 1.) completing the Environmental Assessment with the 321 total network sites, 2.)the multi-agency land ownership/management involvement, 3.) multiple tribal consultations required in Arizona, and 4.) adjusting the construction schedule around weather. Without the FONSI, which we are still waiting on, it is challenging to finalize the construction schedule that is based around seasonal weather issues.. | GovNET is making good progress toward achieving the milestones of the Baseline Plan. The issue with the greatest impact on the project's progress has been the delayed approval of the Environmental Assessment and the FONSI determination. Construction on the project cannot move forward until the FONSI is issued. Construction was originally scheduled to begin in April 2011, but has now been delayed to at least November 2011. Looking forward, GovNET anticipates further need to adjust the construction schedule during fall and winter months due to weather and mountain site issues. | TRUE
NT10BIX5570136 | 2011 | Q4 | Q4 - 2011 | Activities this quarter were focused on finalizing the technology requirements for the network, working with NTIA to finalize the Environmental Assessment, and coordinating pre-construction activities. GovNET received its FONSI on November 21, 2011, and is not required to do any additional mitigation. GovNET, NTIA and Arizona SHPO signed a Programmatic Agreement on September 14, 2011, defining NTIA's responsibility for releasing funds and authorizing construction; identifying Section 106 review responsibilities for FCC, USDA-FS, BLM and NPS; and establishing reporting requirements and outlining administrative protocols. GovNET is subject to Section 106 review in accordance to the Programmatic Agreement on all proposed tower sites or collocation sites prior to construction. Per the Programmatic Agreement, GovNET will send quarterly updates to all parties starting in January 2012. Receiving the FONSI set into motion pre-construction activities, which included: geotechnical work and soil surveys at construction sites, mapping tower sites, ordering radios and antennas, releasing additional RFPs for equipment, and completing appraisals required for match documentation. GovNET hired a Construction Manager and a Senior Project Manager. They will oversee the physical construction of the project, manage all contractors, manage â€œstackingâ€ the towers and equipment installation, and other construction management activities. Other milestones for this reporting period included completing the first program audit and securing additional library and school leases for node sites. GovNET also submitted a Budget Amendment, which was approved by the Grant Manager on Dec. 19, 2011. The milestone completion percentages reported in this report are based on the budget approved in that amendment. During the reporting period, GovNET staff attended many conferences, including the BTOP Conference in Cleveland, October 5 â€“ 7, 2011, and the Arizona Library Association Conference, November 28 â€“ 30, 2011. In order to coordinate leases and conduct outreach for the project, GovNET staff met with numerous stakeholders throughout the State of Arizona, including the Arizona Governorâ€™s Office of Education Innovation, the State Education Council, the University of Arizona, county school associations, local school boards and public safety entities. GovNETâ€™s Community Outreach Specialist has been coordinating with the Governorâ€™s Office and other statewide partners to plan an official ribbon-cutting for the network. The following RFPs were released during this reporting period: 1. The RFP for microwave gensets was released November 14, 2011, and the contract is expected to be award during Q1 2012. 2. The RFP for microwave air conditioners was released December 5, 2011, and the contract is expected to be award during during Q1 2012. 3. The RFP for microwave rectifier, racks and batteries was released December 14, 2011, and the contract is expected to be award during during Q1 2012. Two contracts for access and long haul radios systems were signed during this reporting period. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be in sync with its Baseline Plan by the end of Q3 2012. | No variance from Baseline Plan. | n/a | n/a | No variance from Baseline Plan. | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be in sync with its Baseline Plan by the end of Q3 2012. | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be in sync with its Baseline Plan by the end of Q3 2012. | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be in sync with its Baseline Plan by the end of Q3 2012. | 0 | 2 | 0 | No agreements with wholesalers have been signed, but two are in process and preliminary discussions have occurred for another. | The project is expected to provide the following wholesale services: Ds1, Ds3, Ethernet Transport and VOIP. Pricing for services has not been determined but will be competitive with current market rates. | No third-party operators will be used on this project. | 0 | 0 | 0 | 0 | No variance from Baseline Plan. | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be in sync with its Baseline Plan by the end of Q3 2012. | n/a | 10 Mbps = 45 providers; 45 Mpbs (DS3) = 10 providers | 0 | 0 | 0 | 0 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be in sync with its Baseline Plan by the end of Q3 2012. | n/a | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be in sync with its Baseline Plan by the end of Q3 2012. | 5 Mbps = 231 subscribers; 10 Mpbs = 40 subscribers; 45 Mbps =10 subscribers | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be in sync with its Baseline Plan by the end of Q3 2012. | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be in sync with its Baseline Plan by the end of Q3 2012. | n/a | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI during this reporting period and expects to be in sync with its Baseline Plan by the end of Q3 2012. | 10 Mpbs (equivalent to 7 T1s) = 4 subscribers; These are Nat'l Cellular Carriers in multiple markets in AZ. | VoIP, cloud computing, distance learning, video conferencing, secure interoperable public safety channel for all 15 County Government Emergency Services, including connectivity to all Emergency Operations Centers. | FALSE | n/a | Next quarter, we plan to: - finalize the construction schedule, - complete construction RFPs, - begin construction of three hub site foundations, - begin tower erection at one backbone site, - conduct the project's official ribbon cutting, scheduled for February 7, 2012. Next quarter, we expect to make progress on the following key indicators: â€¢ New network miles deployed = 100 â€¢ Total CAI subscribers served (CAIs connected) = 5 â€¢ Number of signed agreements with broadband wholesalers or last mile providers = 0 | GOVNET, INC. | The biggest challenges have been centered around 1.) completing the Environmental Assessment, 2.) the multi-agency land ownership/management involvement, 3.) multiple tribal consultations required in Arizona, and 4.) adjusting the construction schedule around weather. Now that the FONSI has been issued, the construction schedule can be finalized. | GovNET is making good progress toward achieving the milestones of the Baseline Plan. The issue with the greatest impact on the project's progress was the delayed approval of the Environmental Assessment. Now that the FONSI has been issued, GovNET can finalize the construction schedule and procure equipment to build the network. Construction was originally scheduled to begin in April 2011, but has now been delayed to February 2012. GovNET anticipates further need to adjust the construction schedule during fall and winter months due to weather and mountain site issues. | TRUE
NT10BIX5570136 | 2012 | Q1 | Q1 - 2012 | During this quarter, project activity included the following: finalized the construction schedule, organized and executed the official ribbon-cutting ceremony in February with the Arizona Governor and top agency officials, initiated construction of the network, scheduled and completed geotechnical work and soil surveys at construction sites and mapped tower sites. Construction commenced on five towers and five co-location backbone sites. Antennas, radios and towers were ordered and the following RFQs and RFPs for equipment and construction were released: â€¢ RFQ for Network Operations Center Remodel â€¢ RFP for Rectifiers, Batteries and Racks â€¢ RFP for Microwave Tower Foundations â€¢ RFP for Microwave Tower Stacking, Antenna Hanging and Wave Guide Installation Major milestones completed this quarter include: â€¢ Hired two construction project managers â€¢ Submitted Match Matrix â€¢ Submitted one Route Modification â€¢ Submitted three reimbursement requests â€¢ Submitted the Program Improvement Plan â€¢ Submitted quarterly progress report and annual progress report â€¢ Secured additional Community Anchor Institution leases for node sites GovNET staff met with numerous stakeholders throughout Arizona, including the Governorâ€™s Office of Education Innovation, the State Education Council, Northern Arizona University, county school associations, local school boards and public safety entities. The purpose of these meetings was to coordinate leases and conduct outreach for the project. Yuma County Board of Supervisors passed a Resolution in support of the project, and GovNET now has the support of all 15 counties in Arizona. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be in sync with its Baseline Plan by the end of Q3 2012. | No variance from Baseline Plan. | n/a | n/a | No variance from Baseline Plan. | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be in sync with its Baseline Plan by the end of Q3 2012. | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be in sync with its Baseline Plan by the end of Q3 2012. Three new sites in process; two done. | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be in sync with its Baseline Plan by the end of Q3 2012. Five sites in process. | 0 | 2 | 0 | No agreements with wholesalers have been signed, but two are in process and preliminary discussions have occurred for another. | The project is expected to provide the following wholesale services: Ds1, Ds3, Ethernet Transport and VOIP. Pricing for services has not been determined but will be competitive with current market rates. | No third-party operators will be used on this project. | 0 | 0 | 0 | 0 | No variance from Baseline Plan. | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be in sync with its Baseline Plan by the end of Q3 2012. | n/a | 10 Mbps = 45 providers; 45 Mpbs (DS3) = 10 providers | 0 | 0 | 0 | 0 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be in sync with its Baseline Plan by the end of Q3 2012. | n/a | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be in sync with its Baseline Plan by the end of Q3 2012. | 5 Mbps = 231 subscribers; 10 Mpbs = 40 subscribers; 45 Mbps =10 subscribers | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be in sync with its Baseline Plan by the end of Q3 2012. | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be in sync with its Baseline Plan by the end of Q3 2012. | n/a | Behind baseline plan due to delay in EA approval, which restricted construction. GovNET received its FONSI in Q4 2011 and expects to be in sync with its Baseline Plan by the end of Q3 2012. | 10 Mpbs (equivalent to 7 T1s) = 4 subscribers; These are Nat'l Cellular Carriers in multiple markets in AZ. | VoIP, cloud computing, distance learning, video conferencing, secure interoperable public safety channel for all 15 County Government Emergency Services, including connectivity to all Emergency Operations Centers. | FALSE | n/a | Next quarter, we expect to make progress on the following key indicators: â€¢ New network miles deployed = 200 â€¢ Total CAI subscribers installed (CAIs connected) = 25 â€¢ New towers built = 5 â€¢ Number of signed agreements with broadband wholesalers or last mile providers = 0 | GOVNET, INC. | We are experiencing some challenges around contractor selection, as bids are coming in higher than anticipated. We have had to request some necessary route changes. We would benefit from a streamlined approach to route changes, as it is a 'win-win' situation for both the grantee and the BTOP program. Our overall match value decreased due to an appraisal error. As a result, the percent completion of many milestones was also decreased. | We are making good progress toward achieving the milestones of the Baseline Plan. The issue with the greatest impact on the project's progress was the delayed approval of the Environmental Assessment. The FONSI was issued in Q4 2011, allowing us to develop the construction schedule and begin to procure equipment to build the network. Construction is underway, but we anticipate further need to adjust the construction schedule during fall and winter months due to weather and mountain site issues. An additional challenge is the inflation of construction costs and awaiting approval of some necessary project site and route changes. | TRUE
NT10BIX5570136 | 2012 | Q2 | Q2 - 2012 | During this quarter, significant construction and outreach project activity occurred including the following: attendance at numerous meetings with stakeholders, including Santa Cruz, Cochise, Yavapai, Yuma, and Pima County officials; the cities of Tusayan, Flagstaff, Prescott Valley and Mesa; BLM and USFS; and multiple school board presentations. The purpose of these meetings was to explain the benefits of the project to additional staff and discuss ways GovNET could further assist these stakeholders. Overall, responses were very positive, additional collaborative relationships developed, and new service locations requested. The project is moving from informational to adoption statewide. Multiple E-Rate/USAC approvals for network services were achieved and GovNET is scheduling service turn-on dates for one entire County School Consortium. GovNET participated in a statewide panel on education technology in schools. GovNET staff also attended a national BTOP Conference in Washington, D.C., May 22-24 and had meetings with NTIA officials. Additional progress on site leases with federal agencies and local governments was made for both backbone and node locations. GovNET also worked on additional match documents requested by NTIA. Multiple construction crews were employed and equipment ordered for implementation of the build-out plan in the northern part of Arizona. Tower construction activities in SE Arizona continued at the following locations: - Dragoon (antenna installation) - Mule (antenna installation) - Willcox new tower construction - Klondyke (antenna installation) - Kelvin (antenna installation) - Phoenix One (antenna installation) The following RFQs and RFPs for equipment and construction were released: - The RFP for Network Infrastructure was released and responses were received at the end of April. The Network Operations Center remodel began in early April at 7835 E. McClain Drive in Scottsdale, Arizona. The project received a partial stop work order for Mingus Mountain that was suggested out of environmental compliance. Less than 6 months after FONSI, all work on the project was halted May 22, 2012, per verbal instruction by NTIA after a GovNET-requested meeting in Washington DC regarding NEPA procedure with GovNET's attorney and environmental consultant. After a productive meeting, NTIA officials met separately with GovNET staff and provided verbal suspension notice. The only construction activities that occurred after May 22 were associated with securing sites. A written suspension letter was received June 1, 2012. Program officials made a site visit June 12-13, 2012. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 450 miles were on track for this quarter, only awaiting scheduled radio install. Behind baseline projections due to delay of FONSI and a suspension of the project by NTIA in June 2012. | n/a | n/a | n/a | n/a | 12 Backbone links & 62 CAI links were on track for this quarter. Behind baseline projections due to delay of FONSI in Q4 2011 restricting construction, and a suspension of the project by NTIA in June 2012. | 3 new towers were on track for this quarter. Behind baseline projections due to delay of FONSI in Q4 2011 restricting construction, and suspension of the project by NTIA. | 74 interconnects were on track for this quarter. Behind baseline projections due to delay of FONSI in Q4 2011 restricting construction, and a suspension of the project by NTIA in June 2012. | 2 | 3 | 0 | Two separate site access agreements with wholesale internet provider, Cogent Communications, have been signed for GovNET to resell internet to desperate CAIs and awaiting last mile providers. Three last mile provider agreements are in process. By the end of the project, nine agreements with wholesalers & last mile providers are expected to be signed. | The project is expected to provide the following wholesale services: Ds1, Ds3, Ethernet Transport and VOIP. Pricing for services has not been determined but will be competitive with current market rates. | No third-party operators will be used on this project. | 0 | 0 | 0 | 0 | No variance from Baseline Plan. | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and a review of the project by NTIA in May 2012. | n/a | 10 Mbps = 45 providers; 45 Mpbs (DS3) = 10 providers | 0 | 0 | 0 | 0 | 62 CAIs installed were on track for this quarter. Behind baseline projections due to delay of FONSI in Q4 2011 restricting construction, and a review of the project by NTIA in May 2012. | n/a | 62 CAIs installed were on track for this quarter. Behind baseline projections due to delay of FONSI in Q4 2011 restricting construction, and a review of the project by NTIA in May 2012. | 5 Mbps = 231 subscribers; 10 Mpbs = 40 subscribers; 45 Mbps =10 subscribers | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and a review of the project by NTIA in May 2012. | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and a review of the project by NTIA in May 2012. | n/a | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and a review of the project by NTIA in May 2012. | 10 Mpbs (equivalent to 7 T1s) = 4 subscribers; These are Nat'l Cellular Carriers in multiple markets in AZ. | VoIP, cloud computing, distance learning, video conferencing, secure interoperable public safety channel for all 15 County Government Emergency Services, including connectivity to all Emergency Operations Centers. Vendors have described this network design as the most sophisticated microwave network in the country. | FALSE | n/a | Next quarter (July - Sept.), we expect to make progress on the following key indicators: â€¢ New network miles deployed = 450; â€¢ Total CAI subscribers installed (CAIs connected) = 62 â€¢ New towers built = 4; â€¢ New wireless links = 74; â€¢ Number of signed agreements with broadband wholesalers or last mile providers = 1 additional A partial start work order could be provided by the NTIA in early September, after receipt of all additional requested documentation from GovNET, that would allow for the completion of all or substantial portions network elements planned as noted above. These milestones could have been completed last quarter (April - June) had the project work not been halted mid-quarter. | GOVNET, INC. | The project encountered some programmatic delays with regard to a necessary site addition (Arivaca) and a request for direction to swap out end locations (CAIs) in the project who had not signed leases with those who have signed leases and are "exempt" from Section 106 review, but need environmental/Section 106 approval by BTOP prior to proceeding. These in-kind leases, once approved, will assist in securing our matching funds. The project was verbally halted on May 22, 2012, per instruction by NTIA, and all construction activity was stopped as directed. A letter was received June 1, 2012, notifying GovNET an NTIA site visit was to occur. Major construction only occurred during the first 7 weeks of the quarter, or just over 50% of the time period, so milestones achieved & network activation was hampered. Once the suspension is lifted and project work is allowed, the match and program income issues will be resolved in short order. Unlike fiber projects that must progress in a linear succession, this wireless network can be turned up very quickly by constructing multiple sites at one time and achieving rapid multi-directional connectivity when deployed simultaneously (i.e. multiplied route miles) . | This past quarter, we were making exponential progress toward achieving the milestones of the Baseline Plan. The issues with the greatest impact on the project's progress was the 16 month delay for FONSI holding up project construction until issued and NTIA's decision to halt the project for review in May 2012, only 6 months later. Next quarter, BTOP program assistance is requested for rapid review/response of required route modifications/EHP checklists, as some of the affected sites are in a "ring" topology affect other "non-changed" sites, and delays may have an impact on those sites as well. The work stoppage may have affected vendor relations. | TRUE
NT10BIX5570136 | 2012 | Q3 | Q3 - 2012 | During this quarter, GovNET has been busy compiling responses to the CAP letter of July 19, 2012, and answering follow up questions from NTIA and NOAA. No project work has been allowed. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 450 miles were on track Q2 2012, only awaiting scheduled radio install. Behind baseline due to issue of FONSI in November 2011 and project suspension in May 2012 by NTIA. | n/a | n/a | n/a | n/a | 12 Backbone links & 62 CAI links were on track for this quarter. Behind baseline projections due to issue of FONSI November 22, 2011 restricting construction, and a suspension of the project by NTIA in May 2012. | 3 new towers were on track for Q2 2012 Behind baseline projections due to issue of FONSI in Q4 2011 restricting construction, and suspension of the project by NTIA. | 74 interconnects were on track for Q2 2012. Behind baseline projections due to issue of FONSI in Q4 2011 restricting construction, and a suspension of the project by NTIA. | 2 | 3 | 0 | Two separate site access agreements with wholesale internet provider, Cogent Communications, have been signed for GovNET to resell internet to desperate CAIs and awaiting last mile providers. Three last mile provider agreements are in process. By the end of the project, nine agreements with wholesalers & last mile providers are expected to be signed. | The project is expected to provide the following wholesale services: Ds1, Ds3, Ethernet Transport and VOIP. Final pricing for services has not been determined but will be competitive with current market rates. | No third-party operators will be used on this project. | 0 | 0 | 0 | 0 | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and project suspension by NTIA in May 2012. | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and project suspension by NTIA in May 2012. | n/a | 10 Mbps = 45 providers; 45 Mpbs (DS3) = 10 providers | 0 | 0 | 0 | 0 | 62 CAIs installed were on track for Q2 2012. Behind baseline projections due to delay of FONSI issue in Q4 2011 restricting construction, and a project suspension by NTIA in May 2012. | n/a | 62 CAIs installed were on track for Q2 2012. Behind baseline projections due to delay of FONSI issue in Q4 2011 restricting construction, and a project suspension by NTIA in May 2012. | Updated Estimated Subscriber needs: 10 Mbps = 231 subscribers; 50 Mbps = 40 subscribers; 100 Mbps =10 subscribers | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and project suspension by NTIA in May 2012. | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and project suspension by NTIA in May 2012. | n/a | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and project suspension by NTIA in May 2012. | 10 Mbps (equivalent to 7 T1s) = 4 subscribers; These are Nat'l Cellular Carriers in multiple markets in AZ. | VoIP, cloud computing, distance learning, video conferencing, secure interoperable public safety channel for all 15 County Government Emergency Services, including connectivity to all Emergency Operations Centers. Vendors have described this network design as the most sophisticated microwave network in the country. | FALSE | n/a | If the project is restarted by mid-November, we expect to make quick progress on the following key indicators: â€¢ New network miles deployed = 450; â€¢ Total CAI subscribers installed (CAIs connected) = 62 â€¢ New towers built = 4; â€¢ New wireless links = 74; â€¢ Number of signed agreements with broadband wholesalers or last mile providers = 1 additional A partial start work order could be provided by the NTIA in early November, as the additional requested documentation has been received from GovNET, which would allow for the completion of all or substantial portions network elements planned as noted above. These milestones could have been completed Q2-2012 (April - June) had the project work not been halted in May 2012. | GOVNET, INC. | GovNET faced many challenges this past quarter but stayed firm in its commitment to the project and local stakeholders. | This next quarter, GovNET is hopeful that project work may be resumed to benefit the deserving Arizonans in schools, hospitals, and public safety without high-speed broadband capabilities. | TRUE
NT10BIX5570136 | 2012 | Q4 | Q4 - 2012 | GovNET continued to respond to further NTIA/NOAA requests for information based on GovNET CAP Response submitted September 4, 2012. No project work was allowed. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 450 miles were on track Q2 2012, only awaiting scheduled radio install. Behind baseline due to issue of FONSI in November 2011 and project suspension in May 2012 by NTIA. | n/a | n/a | n/a | n/a | 12 Backbone links & 62 CAI links were on track for Q2 2012. Behind baseline projections due to issue of FONSI November 22, 2011 restricting construction, and a suspension of the project by NTIA in May 2012. | 3 new towers were on track for Q2 2012 Behind baseline projections due to issue of FONSI in Q4 2011 restricting construction, and suspension of the project by NTIA. | 74 interconnects were on track for Q2 2012. Behind baseline projections due to issue of FONSI in Q4 2011 restricting construction, and a suspension of the project by NTIA. | 2 | 3 | 0 | Two separate site access agreements with wholesale internet provider, Cogent Communications, have been signed for GovNET to resell internet to desperate CAIs and awaiting last mile providers. Three last mile provider agreements were in process. | The project is expected to provide the following wholesale services: Ds1, Ds3, Ethernet Transport and VOIP. Final pricing for services has not been determined but will be competitive with current market rates. | No third-party operators will be used on this project. | 0 | 0 | 0 | 0 | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and project suspension by NTIA in May 2012. | n/a | n/a | n/a | 0 | 0 | 0 | 0 | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and project suspension by NTIA in May 2012. | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | VoIP, cloud computing, distance learning, video conferencing, secure interoperable public safety channel for all 15 County Government Emergency Services, including connectivity to all Emergency Operations Centers. Vendors have described this network design as the most sophisticated microwave network in the country. | FALSE | n/a | GovNET is hopeful to re-engage in project work and network construction to finish the project for the deserving citizens of Arizona. | GOVNET, INC. | n/a | n/a | TRUE
NT10BIX5570136 | 2013 | Q1 | Q1 - 2013 | GovNET continued to respond to further NTIA/NOAA requests for information based on GovNET CAP Response submitted September 4, 2012. No project work was allowed. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 450 miles were on track Q2 2012, only awaiting scheduled radio install. Behind baseline due to issue of FONSI in November 2011 and project suspension in May 2012 by NTIA. | n/a | n/a | n/a | n/a | 12 Backbone links & 62 CAI links were on track for Q2 2012. Behind baseline projections due to issue of FONSI November 22, 2011 restricting construction, and a suspension of the project by NTIA in May 2012. | 3 new towers were on track for Q2 2012 Behind baseline projections due to issue of FONSI in Q4 2011 restricting construction, and suspension of the project by NTIA. | 74 interconnects were on track for Q2 2012. Behind baseline projections due to issue of FONSI in Q4 2011 restricting construction, and a suspension of the project by NTIA. | 0 | 3 | 0 | No agreements were allowed to be signed during suspension period. | The project is expected to provide the following wholesale services: Ds1, Ds3, Ethernet Transport and VOIP. Final pricing for services has not been determined but will be competitive with current market rates. | No third-party operators will be used on this project. | 0 | 0 | 0 | 0 | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and project suspension by NTIA in May 2012. | n/a | n/a | n/a | 0 | 0 | 0 | 0 | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and project suspension by NTIA in May 2012. | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | VoIP, cloud computing, distance learning, video conferencing, secure interoperable public safety channel for all 15 County Government Emergency Services, including connectivity to all Emergency Operations Centers. Vendors have described this network design as the most sophisticated microwave network in the country. | FALSE | n/a | GovNET is hopeful to re-engage in project work and network construction to finish the project for the deserving citizens of Arizona. Due to pending route changes and/or modifications awaiting approval, we do not anticipate being able to turn up CAIs or add route miles by end of June 2013. We plan to re-initiate discussions with last mile providers and start community outreach. | GOVNET, INC. | n/a | The unknown length of time to process a necessary route change impacts progress greatly. Once authorized to commence, GovNET is planning releasing an RFP for construction management, so until that vendor is in place, progress may be initially delayed but made up for in efficiency and multiple crews. | TRUE
NT10BIX5570136 | 2013 | Q2 | Q2 - 2013 | GovNET received a letter from NTIA/NOAA providing a partial suspension lift on April 30, 2013. GovNET completed the requested information. Additional vendor payments were processed. NTIA/NOAA made a site visit at the end of June. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 450 miles were on track Q2 2012, only awaiting scheduled radio install. Behind baseline due to issue of FONSI in November 2011 and project suspension in May 2012 by NTIA. | N/A | N/A | N/A | N/A | N/A | 3 new towers were on track for Q2 2012 Behind baseline projections due to issue of FONSI in Q4 2011 restricting construction, and suspension of the project by NTIA. | 74 interconnects were on track for Q2 2012. Behind baseline projections due to issue of FONSI in Q4 2011 restricting construction, and a suspension of the project by NTIA. | 0 | 3 | 0 | No agreements were allowed to be signed during suspension period. | The project is expected to provide the following wholesale services: Ds1, Ds3, Ethernet Transport and VOIP. Final pricing for services has not been determined but will be competitive with current market rates. | No third-party operators will be used on this project. | 0 | 0 | 0 | 0 | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and project suspension by NTIA in May 2012. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and project suspension by NTIA in May 2012. | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | VoIP, cloud computing, distance learning, video conferencing, secure interoperable public safety channel for all 15 County Government Emergency Services, including connectivity to all Emergency Operations Centers. Vendors have described this network design as the most sophisticated microwave network in the country. | FALSE | N/A | GovNET is hopeful to fully re-engage in project work and network construction to finish the project for the deserving citizens of Arizona. Pending the timing for full suspension release, pre-construction planning and network deployment activities will re-initiate, including discussions with last mile providers, community anchor institutions, and community outreach. Construction will proceed on sites with environmental approvals. Depending on when a release is provided, we estimate we may be able to deploy 300 miles, connect 2 CAIs, and sign 1 last mile provider agreement. | GOVNET, INC. | N/A | The unknown length of time to process a necessary route change impacts progress greatly. Once authorized to commence, GovNET is planning releasing an RFP for construction management, so until that vendor is in place, progress may be initially delayed but made up for in efficiency and multiple crews. | TRUE
NT10BIX5570136 | 2013 | Q3 | Q3 - 2013 | In July 2013, GovNET built a new tower site to serve the rural border community of Arivaca. During this quarter, GovNET received a one year grant project time extension to September 30, 2014. During the month September 2013, a formal letter from NTIA/NOAA was received pronouncing a full project release and additional hiring commenced to ramp company personnel back up to execute project. | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | Project miles will be added in Q4 due to a restart of construction activity. | N/A | N/A | N/A | N/A | N/A | GovNET was able to construct a new tower at Arivaca | Addition of Arivaca; all sites are interconnection points. | 0 | 3 | 0 | No agreements were allowed to be signed until project restart approval. Three agreements are in negotiation. | The project is expected to provide the following wholesale services: Ds1, Ds3, Ethernet Transport and VOIP. Final pricing for services has not been determined but will be competitive with current market rates. | No third-party operators will be used on this project. | 0 | 0 | 0 | 0 | Project is now able to restarted and negotiations can recommence with providers. | Project is now able to restarted and negotiations can recommence with providers. | N/A | 1 Mbps to 1 Gbps is available based on subscriber needs | 0 | 0 | 0 | 0 | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and project suspension by NTIA in May 2012 | N/A | Behind baseline due to delay of FONSI in Q4 2011 restricting construction, and project suspension by NTIA in May 2012 | 1 Mbps to 1 Gbps is available based on subscriber needs | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | VoIP, cloud computing, distance learning, video conferencing, secure interoperable public safety channel for all 15 County Government Emergency Services, including connectivity to all Emergency Operations Centers. Vendors have described this network design as the most sophisticated microwave network in the country. | FALSE |  | GovNET is looking forward to fully re-engaging in project work and network construction to finish the project for the deserving citizens of Arizona. Pre-construction planning, increased staffing, contractor positions, RFP / RFQ releases have commenced and network deployment activities are beginning again with anticipated heavy increase in the next quarter. Heavy emphasis will be placed on discussions with last mile providers, community anchor institutions, and community outreach. We estimate to deploy 150 network miles, connect 1 CAI, and 1 wholesaler/last mile agreement next quarter. A new General Manager has been hired. | GOVNET, INC. | As the project resumes, the task of completing necessary right-of-ways and receiving requested route change approvals will gauge how fast the network can be built. Since all activity was on hold, some new variables may come into play that were not known prior. | GovNET will be getting a Construction Management company up to speed, who will be secured via RFP release scheduled for this quarter. Snow may play into build timing. Many other RFPs willl be issued to allow for deployment the following quarter. | TRUE
NT10BIX5570136 | 2013 | Q4 | Q4 - 2013 | For the quarter October - December 2013, significant project movement was taking place: â€¢ Hired a General Manager/Grant Manager â€¢ Let RFQs for Architectural & Engineering (A&E) Services and Supplemental Personnel. Awarded Supplemental Personnel staffing contracts to two firms. Provided Notice of Awards to three A&E firms. â€¢ Let RFPs for Master Construction Services; Generators; Network Equipment Infrastructure; Rectifiers, Batteries and Cabinets â€¢ Completed search for Senior Construction Manager to manage build of network â€¢ Submitted and gained approval for Batch 3 Environmental Assessment Package â€¢ Completed initial submission of the Batch 2 Environmental Assessment Package â€¢ Re-initiated community outreach by letting stakeholders know the project was back up and had received an extension. | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 161 miles (which 142 miles are network backbone) have been deployed to a CAI on a test mode | N/A | N/A | N/A | N/A | N/A | Awaiting Construction Services RFP selection and award to progress new builds | all sites are interconnection points. | 0 | 2 | 0 | Two agreements are in negotiation. | The project is expected to provide the following wholesale services. Ds1, Ds3, Ethernet Transport and VOIP. Final pricing for services has not been determined but will be competitive with current market rates. | No third party operators will be used on this project. | 0 | 0 | 0 | 0 | Now project is restarted, negotiations are recommencing with providers. | Now project is restarted, negotiations are recommencing with providers. | N/A | 1 Mbps to 1 Gbps is available based on subscribers needs. | 0 | 0 | 0 | 0 | Re-engaging network construction activity to be able to deploy directly to CAIs. One remote CAI in test mode. | N/A | One remote CAI was up in test mode - 250 Mbps available | 1 Mbps to 1 Gbps is available based on subscriber needs | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | VoIP, Cloud computing, distance learning, video conferencing, secure interoperable public safety channel for all 15 County Government Emergency Services, including connectivity to all Emergency Operations Centers. Vendors have described this network design as the most sophisticated microwave network in the country. | FALSE | n/a | GovNET is fully re-engaging in project work, RFP/RFQ releases and the award of related contracts, as well as network construction deployment activities. Heavy emphasis will be placed on construction planning, completion of partially built sites, network deployment, equipment purchases, scheduling installation of community anchor institutions, community outreach and last mile provider discussions. A Construction Services RFP will be awarded and mobilization will occur. Materials and equipment will begin to be ordered and received for deployment. Network miles deployed are anticipated to be over 200 miles, along with 1-5 CAIs connected (depending on NTIA EA approval of Batch 2). Once the network is live, additional last mile provider interest is anticipated. | GOVNET, INC. | As the project resumes, several key challenges have already been faced, and will continue through the project extension period. Operationally, the task of re-initiating efforts toward completing necessary right-of-ways on federal lands which had been stopped due to suspension is a challenge under the grant time frame. Additionally, receiving requested route change approvals from the NTIA will gauge how fast the network can be built. The challenge of re-engaging stakeholders on the go-forward plan takes time to revive momentum. Since all project activity was on hold for over 16 months, some new variables may come into play that were not known prior. | The project suspension impacted site environmental clearance and lease negotiations/agreements. Completing all site "clearance" activity, including Section 106 documentation requirements on federal communication sites prior to site build, continues to be a major challenge. The geographical dispersions of approved sites increases the complexity of construction management, along with species mitigation windows and the weather being other key challenges affecting many sites throughout the state. | TRUE
NT10BIX5570138 | 2010 | Q4 | Q4 - 2010 | Environmental consultant has been hired and has contacted government representative to understand expectations. Routes have been identified and verified. Network Design is completed in several areas and progressing in others. Desktop surveys for endangered species are in progress. Proceeding with the Section 106 replies. Received an assessment of "No Effect" from NPS regarding proposed construction near Fort Davis Historic Site. Compiled list of all historic sites anywhere near project areas. Obtained GIS Maps of project areas and began pre-staking and staking activities. Working with Davis Mtn. State Park administration on permits to place fiber cable on AEP pole lines crossing Park Lands. Baseline Report has been submitted and accepted. Continuing work with FPO to provide continuous project updates. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no variance | na | na | na | no variance | no variance | no variance | no variance | 0 | 5 | 0 | We are currently negotiating contracts with: Hill Country Telephone; Wes-Tex Telecommunications; Dell City Communications; Polka Lambro Fiber; Big Bend Telephone. | NA | NA | 0 | 0 | 0 | 0 | no variance from baseline | no variance from baseline | no variance from baseline | na | 206 | 0 | 0 | 1 | no variance from baseline | NA | NA | Upto 1 Gbs. No variance from baseline | 40069 | 206 | 0 | 206 | 1 | no variance from baseline | no variance from baseline | no variance from baseline | no variance from baseline | Upto 1 Gbs. No variance from baseline | 8030 | 0 | 0 | 0 | 1 | no variance from baseline | NA | NA | NA | Upto 1 Gbs. No variance from baseline | NA | FALSE | NA | In Q3 we intend to receive our FONSI and have the SAC lifted on our project. We will complete 5 contracts. Finalize all permitting and ROW issues, complete field staking and generate construction plans, begin ordering of materials and equipment, begin construction. | Region 18 Education Svc Ctr. | This project is on track and moving forward. We anticipate submitting our EA on time and have confidence that our SAC will be satisfied and FONSI granted for us to meet our Q3 commitments. | Our project is on track and moving forward. We anticipate submission of EA on time and have confidence that our SAC will be satified and FONSI granted for us to meet our Q3 commitments. | TRUE
NT10BIX5570138 | 2011 | Q1 | Q1 - 2011 | Region 18 completed and submitted their draft EA on time February 28th. Draft returned to Region 18 with questions on March 31st. Currently working to answer questions with intended re-submission by April 14th. Significant progress has been made with the contracts between Region 18 and the 5 telephone companies that will perform the construction of the project. Contracts are currently being reviewed by the Region 18 legal department. All necessary 1444 forms have been submitted. Most have been approved. Six required minor administrative changes which will be completed and re-submitted for review by April 15th. Region 18 has been working with the NTIA and compliance administrators to ensure that there will not be any project overlap with another BTOP award. The process is going well. Region 18 received a new FPO. The change has had a positive impact for us in that our communications and response time with NTIA is greatly improved. Region 18 has (with approval from NTIA) removed a duplicate route to the McDonald Observatory. There will not be a negative impact to the project and the removal of the line will prevent any potential impact to an endangered species (Mexican Spotted Owl) and will mitigate potential budget overruns due to the rugged terrain that would cause damage to the equipment to be used causing the equipment to be scrapped after the project. The Observatory will still be connected via an existing ROW. No other CAI's are impacted by this change. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.7 mile variance. FONSI has not been issued, construction cannot begin. Expect to make-up shortfall in Q2 2011. | NA | NA | NA | 32.7 mile variance. FONSI has not been issued, construction cannot begin. Expect to make-up shortfall in Q2 2011. | No variance | No variance | -2 variance. Construction has not begun. | 0 | 5 | 0 | We are currently negotiating contracts with: Dell City Communications; Hill Country Telephone; Wes-Tex Telecommunications; Poka Lambro Fiber; Big Bend Telephone. The delay in finalizing the contracts rests within the legal department at Region 18 and potential budget cuts which may affect certain locations. | NA | NA | 0 | 0 | 0 | 0 | no variance | no variance | NA | NA | 0 | 0 | 0 | 0 | no variance | no variance | no variance | Up to 1 Gbs. | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | No variance | No varaince | No variance | No variance | NA | NA | FALSE | NA | During Q2 2011 (Q4 Year 1 BTOP) Region 18 will receive their EA FONSI thereby lifting the SAC. All contracts will be completed with the 5 telephone companies and construction will begin. | Region 18 Education Svc Ctr. | The EA process is a challenge. We are hopeful that our response will meet the needs of the NTIA and we will receive our FONSI by the end of April. The route to the McDonald Observatory presented a challenge, however with the support of our FPO a resolution has been agreed to and the problem resolved. Due to budget issues within the Texas School System the review and approval of the contracts with our Telephone companies has been slowed significantly. We are working to address this and intend to have resolved and the contracts completed prior to a FONSI being issued. | Meeting these targets will be difficult if the EA is not approved and FONSI granted very early in the quarter. The Region 18 ESC BTOP project is still on track. We have successfully identified potential project issues (McDonald Observatory) and presented solutions to keep the project on track and on budget. We have continued to report and communicate with NTIA as required. Region 18 ESC is looking forward to receiving the FONSI and to begin construction. Continued clear communication and support from our FPO and NTIA will help to keep the project on track. | TRUE
NT10BIX5570138 | 2011 | Q2 | Q2 - 2011 | Region 18 finalized submission of revised EA and received notification of FONSI in June 2011. Several SAC's were attached to the FONSI. Region 18 is taking action to address the SAC's. A packet of information sheets complete with photographs is being compiled to address the biological SAC's and to protect endangered species and their habitats. Google Earth maps are being distributed to protect the historical sites. All of this data will be forwarded to all construction companies. All contracts have been completed between Region 18 and the 5 telephone companies. The largest contract (representing 67% of construction) has been signed. The others should be signed by the end of July 2011. Several additional 1444 forms have been submitted and we are awaiting their approval. Documentation has been provided to FPO confirming that there is not an overlap of routes between the Region 18 BTOP grant and any other recipient. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -47.96 FONSI not received until mid-June. Companies are ordering equipment and planning to begin construction at the end of Q3 2011. Current construction schedules indicate the project to be back on track by the end of Q1 2012. This is Q3 of Project year 2. | NA | NA | NA | -47.96 See explanation above. | no variance | no variance | -4 See explanation above | 1 | 4 | 40 | Dell City Telephone, contract signed, represents 67% of project construction. Big Bend Telephone, contract waiting Big Bend signatures. Poka Lambro, WesTex Coop, and Hill Country Telephone are all performing final reviews of contracts. Completed signed contracts are expected by the end of July 2011. | NA | NA | 0 | 0 | 0 | 0 | No Variance | No Variance | NA | NA | 0 | 0 | 0 | 0 | No Variance | No Variance | No variance | No Variance | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | No Variance | No Variance | No Variance | No Variance | No Variance | NA | FALSE | NA | We anticipate that all 5 contracts will be signed with our telephone companies. All equipment should be ordered by the end of the quarter and much received. There are some fiber delivery delays, we are working to minimize the impact this could have on the project. Construction will begin in the next quarter but significant project progress will most likely not be recognized until Q4 of 2011. | Region 18 Education Svc Ctr. | FONSI not issued until the final weeks of the quarter. We immediately began the process of notifying our contracted companies. The process to begin construction is well under way at this time. As stated in our previous quarterly update, our time line for the quarter was at risk if the FONSI was not issued early in the quarter. We are still confident and have communication from our Telephone Companies performing the work that the project can still be completed on time and meet the 2/3 completion in 2 years hurdle. The SAC's attached to the FONSI were broad in scope and not project specific. This created an additional delay of 4 weeks and a cost over $10,000 to compile the necessary information and create a comprehensive packet of information to distribute to the construction companies hired to perform the work. | At this time we are excited to begin our construction and do not see any barriers to the process. The only potential cause for concern at this point is the potential for delays due to the availability of fiber. We are expecting 67% of our needed fiber to be delivered in October and the remaining amount needed is currently being ordered. | TRUE
NT10BIX5570138 | 2011 | Q3 | Q3 - 2011 | Region 18 completed the information packet that addresses all SAC's attached to our FONSI. This packet of information has been distributed to all of our telephone company partners and instructions have been given to provide a copy of the packet to all construction crews. Contracts have been signed with three additional telco's bringing our total signed contracts to 4. The one contract outstanding, Hill Country Telephone is now with Region 18 ESC legal department for final review. The outstanding issue concerning the University of Texas land that will be crossed during construction has been resolved. We will be able to construct as outlined in our EA and will not have to pay a right-of-way fee to the University. We are very pleased with the outcome. We are working with our telco's as they near the start of construction to provide all appropriate Davis Bacon guidance and are requesting to receive the certified weekly time sheets for our review. We are looking forward to construction starting the first of October. We have begun to develop our community outreach plan. We are preparing for and anticipating our Site Visit scheduled for October 24 - 26th in Midland Texas. Equipment and fiber are on order and deliveries are expected beginning the first week of October. These items are being purchased by each telco and not by Region 18. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -76.3 variance to baseline. Construction begins October 1st with multiple consecutive crews working. Equipment and fiber have been received and crews are ready to go. We anticipate Poka Lambro (2.0 miles); Wes Tex (1.33 miles) to complete their construction this coming quarter. Big Bend plans to complete 12.7 miles and Dell City miles | NA | NA | NA | -76.3 (see explanation above) | -1 (see explanation above) | -2 (see explanation above) | -6 (see explanation above) | 4 | 1 | 40 | Dell City Telephone; Big Bend Telephone; Wes Tex Telephone Cooperative; Poka Lambro Telephone. | NA | NA | 0 | 0 | 0 | 0 | No variance | No variance | NA | NA | 0 | 0 | 0 | 0 | no variance | no variance | no variance | no variance | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | NA | FALSE | NA | We anticipate that our fifth and final contract will be signed. Project construction will begin and miles of fiber will be constructed and service to our first CAI's will occur. Our site visit with our FPO is scheduled for this quarter. We have received confirmation that fiber deliveries have occurred. We will begin to close the variance gap and hope to be on track to our baseline by the end of Q1 2012. Number of Network mile deployed - WesTex (1.33 miles) and Poka Lambro (2.9 miles). WesTex will connect 6 CAI's in Big Spring and Poka Lambro will connect 1 CAI in Midland and 1 CAI in Andrews. Construction will begin with Big Bend on November 3 and Dell City will begin construction on November 1st. No miles are projected for these two contracts for Q4. Hill Country will not begin construction in this quarter. | Region 18 Education Svc Ctr. | At present we feel we have addressed the issues that have delayed the start of our construction. The EA, FONSI and SAC's have all been addressed. The open issue of taking fiber over University land has been rectified at no cost. Our telephone company partners have secured both equipment and fiber and are beginning construction October 1st. We remain confident that we will meet the 2/3 completion time line as well as a final completion by the end of year three. | We are excited to begin construction and do not anticipate any issues. The contracts have been signed, crews are ready to begin and fiber and equipment have been delivered. | TRUE
NT10BIX5570138 | 2011 | Q4 | Q4 - 2011 | This quarter we have begun construction on several routes of our project. Fiber and equipment have been received and are in place. Our 5th and final contract with Hill Country Telephone has been completed and signed. We are excited to enter this phase of our project and are not anticipating any issues. We have been receiving weekly Davis Bacon time sheets from all construction crews and reviewing them for accuracy. We have completed our Pole Attachment agreements as well as completed our agreement with Union Pacific Railroad and secured the necessary insurance. We also had our site visit in October of 2011. Two items that resulted from this meeting were the request by our FPO to add wireless miles to our total project miles. This has been done. We have added a total of 48.05 aerial miles. We will report wireless miles as completed when the links are installed and service is active. The second item is a clarification, in our grant we list "towers" to be constructed, we need to revise this term to accurately represent what will be installed, in two cases a small addition will be made to an existing structure and in two locations a 50' monopole will be built. An addendum with this information will be posted to GOL as requested. There are some variations in our financial reporting between line items. There is not a variation overall. In order to better represent the BTOP charges amounts were moved as follows: approx. $2500 for pole attachments was moved from Land to Construction. $13272 was moved from Architecture and Engineering to Land for Texas General Land Use. $822 was moved from Equipment to Construction. The budget overrun on line D of Budget Execution details is due to the cost of the Environmental Assessment which was not originally budgeted for. As the overage amount was less than 5% no addendum was requested through GOL. | 28 | 0 | 0 | 0 | 28 | 0 | 0 | 1 | -70 mile variance to baseline. We will narrow our gap in Q2 of 2012 and anticipate closing the gap by Q3 of 2012. | No variance | No variance | No variance | -70 mile variance to baseline. We will narrow our gap in Q2 of 2012 and anticipate closing the gap by Q3 of 2012. | -2 variance to baseline. One of the wireless links is anticipated to be connected in the next quarter and the second link is planned for completion in quarter 3 of 2012. | -2 variance to baseline. In clarification Region 18 will not be constructing cell towers. We will be adding wireless links to existing structures and in two cases adding a 50' monopole. | For clarification, our definition of interconnection points has been modified since the baseline submission. A peering point where 2 providers connect to each other will occur 4 times in the Region 18 project. At this time one of these locations has had upgraded equipment added by Dell City Telephone. We do not anticipate that any of the other 3 peering points in our project will require additional equipment. | 5 | 0 | 0 | We have signed agreements with the following companies: Dell City Telephone, Big Bend Telephone, Poka Lambro Telephone, Wes-Tex Telephone, and Hill Country Telephone Company. | NA | NA | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | 8 | 0 | 8 | 100 | NA | NA | Andrews ISD and Midland DPS Big Spring - Chief of Police, Chamber of commerce. Howard County - Library, Judge, Law Enforcement Center, 118th District Court | (100 mbps)(50mbps)(20mbps) | 0 | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | No variance | NA | FALSE | NA | Our Q1 2012 activities include, Dell City (our largest contractor) plans to complete an additional 40 miles of fiber construction. They plan to complete the route to Toyah TX (a total of 15 miles) and to continue the routes in Pecos TX. Through these routes we plan to connect 6 additional CAI's including the Pecos Barstow Toyah ISD and the Reeves County Hospital and Library. Big Bend will begin the buried and aerial fiber routes from High Frontier to Fort Davis, this route will not be complete until Q4 2012. Big Bend is also working on the route to Valentine ISD scheduled to be completed in Q2 2012. They will also continue the routes to Marfa ISD and Crane ISD. Big Bend plans to complete the wireless link to Marathon ISD this quarter as well. We anticipate Hill Country Telephone to begin construction late in Q1 2012. We are estimating a total of 60 additional miles completed this quarter and up to 15 additional CAI's being connected. We have completed our contracts and are not anticipating any additional wholesale or last mile agreements. | Region 18 Education Svc Ctr. | We have not encountered any obstacles that are preventing us from moving forward. We are anticipating closing our gap to baseline by the end of Q3 2012. | We do not anticipate any challenges. Equipment and fiber are on hand and construction crews are at work. | TRUE
NT10BIX5570138 | 2012 | Q1 | Q1 - 2012 | This quarter we have continued construction and are making excellent progress and have thankfully not had any setbacks. Two of the five telephone companies have finished construction and the 8 CAI's are up and running. The remaining three companies are all at work. Dell City has made great progress and has completed 48% of their route miles and they expect to connect at least 13 CAI's in the next quarter. Big Bend has completed a total of 12 miles as of the end of Q1 2012 and they are also progressing well. Big Bend expects to have the Fort Davis elementary and high school connected in the next quarter. This will be a full quarter ahead of schedule for them. Hill Country has begun construction and has not reported any routes completed at this point. Davis Bacon reporting continues and this quarter we reported over 10,000 hours worked in construction alone. We have also begun to focus on our Community Outreach program and are excited that through two press releases made by one of our Telco's (Dell City) we have had more than 5 calls from local business and a local judge. We will continue to work together with all our telco's and promote the opportunities now available (or soon to be) in so many communities. | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 1 | -46 mile variance to baseline. We are working to close this gap (we were at -70 miles last quarter) and expect to be on track to baseline by the end of Q3 2012. | No variance | No variance | No variance | -46 mile variance to baseline. We are working to close this gap (we were at -70 miles last quarter) and expect to be on track to baseline by the end of Q3 2012. | -2 variance to baseline. One of the links will be completed in Q2 2012 and the second will be completed to the Observatory in Q1 2013. | -2 variance to baseline. In clarification Region 18 will not be constructing cell towers. We will be adding wireless links to existing structures. We expect the Loving County Courthouse to be completed in Q2 2012 and the Observatory in Q1 2013. | For clarification, our definition of interconnection points has been modified since the baseline submission. A peering point where two providers connect to each other will occur 4 times in the Region 18 project. At this time one of these locations has had upgraded equipment added by Dell City Telephone. We do not anticipate that any of the other 3 peering points in our project will require additional equipment. | 5 | 0 | 40 | We have signed agreements with the following companies: Dell City Telephone, Big Bend Telephone, Poka Lambro Telephone, WesTex Telephone, and Hill Country Telephone Company. | NA | NA | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | 8 | 0 | 8 | 100 | Andrews ISD; Midland DPS; Big Spring Chief of Police; Howard County Library; Howard County Judge (Big Spring); County Law Enforcement Center (Big Spring); Chamber of Commerce (Big Spring); Howard County 118th District Court (Big Spring). | NA | see total subscribers served for locations | (100 Mbps) (50 Mbps) (20 Mbps) | 0 | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | NA | NA | FALSE | NA | Planned Q2 2012 activities include: 13 CAI locations to be connected by Dell City Telephone. An additional 30 miles of fiber construction for Dell City as well. We expect the routes to Wink ISD and to Pecos to be completed this quarter. Hill Country Telephone has begun their 21 miles of construction and we expect to see several miles completed this quarter. Big Bend Telephone will complete the route to Fort Davis Elementary and Fort Davis High School. Big Bend should also complete the route to Valentine ISD. Big Bend is also working to complete the route to Marfa ISD. We show that we will have completed 67% of the overall construction on our project by the end of the next quarter yet we will expend approximately 71% of our funds. The difference is due to the fact that materials and equipment have been purchased and construction completed yet CAI connections will not yet be complete and as such will not be complete by the end of the quarter. We will also solidify our Community Outreach plan and attend the BTOP conference in Washington DC. | Region 18 Education Svc Ctr. | We have not encountered any obstacles that are slowing down our construction progress. We anticipate a busy and productive quarter with continued closing of our gap to baseline. | We do not anticipate any challenges. Equipment and fiber are on hand and crews are working. | TRUE
NT10BIX5570138 | 2012 | Q2 | Q2 - 2012 | Q2 2012 was a very productive quarter. We have spent an additional 30% of our grant funds and constructed an additional 73 miles of fiber which represents over 28% of our total miles this quarter alone, we had anticipated an additional 30 miles of fiber would be completed this quarter. We have added two additional ISD's to our connected CAI's and completed an additional interconnection (peering point). As noted last quarter two of our five telephone companies have completed their projects, WesTex and Poka Lambro. Dell City Telephone has completed 87% of the fiber installation contracted and Big Bend telephone has completed 21% of their fiber installation, they have completed the planned routes to Fort Davis and Fort Stockton. Dell City did not complete connection of the 13 CAI's as planned but has begun the splicing process and the plan is to make the connections now in Q3 2012. Hill Country Telephone continued construction this quarter and complete two of its four routes and connected two new CAI's. We expect several additional CAI's to be connected in Q3 2012 as we are aware that construction of the fiber is complete and splicing is taking place in July. Additionally we attended the recent BTOP conference in Washington DC. Davis Bacon reporting continues, this quarter we are reporting 16.49 contractor jobs created, in total the Region 18 ESC BTOP grant is responsible for the creation of 20.54 jobs this quarter. We are continuing with our Community Outreach and have begun to develop a complete program to get the word out which will be coordinated with our telephone companies as service becomes available. | 153 | 0 | 0 | 0 | 153 | 0 | 0 | 2 | No variance to baseline (WesTex completed 1.33 miles; Poka Lambro completed 2.90 miles; Hill Country two routes completed 17.5 miles; Big Bend 13.35 miles completed; Dell City Telephone 117.79 miles completed total 152.87 miles). | No variance to baseline | No variance to baseline | No variance to baseline | No variance to baseline (WesTex completed 1.33 miles; Poka Lambro completed 2.90 miles; Hill Country two routes completed 17.5 miles; Big Bend 13.35 miles completed; Dell City Telephone 117.79 miles completed total 152.87 miles). | -2 variance to baseline. One link will be completed in July 2012 and the second will be completed to the Observatory in Q1 2013. | -2 variance to baseline. In clarification, Region 18 will not be constructing cell towers. We will be adding wireless links to existing structures. Loving County Courthouse will be connected in July 2012 and the Observatory in Q1 2013. | For clarification, our definition of interconnection points has been modified since the baseline submission. A peering point where two providers connect to each other will occur 4 times in the Region 18 project. At this time one of these locations has had upgraded equipment added by Dell City Telephone. WesTex Midland connection was completed Q4 2011; Big Bend Midland Connection was completed Q2 2012; Dell City Pecos and TLSN McCamey will be completed in (July) Q3 2012. | 5 | 0 | 40 | We have signed agreements with the following companies: Dell City Telephone; Big Bend Telephone; Poka Lambro Telephone; WesTex Telephone; Hill Country Telephone. | NA | NA | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | 10 | 0 | 10 | 100 | Andrews ISD; Midland DPS; Big Spring Chief of Police; Howard County Library; Howard County Judge (Big Spring); County Law Enforcement Center (Big Spring); Howard County 118th District Court (Big Spring); Grand Falls- Royalty ISD (new this quarter); Imperial, Buena Vista ISD (new this quarter). | NA | Andrews ISD; Midland DPS; Big Spring Chief of Police; Howard County Library; Howard County Judge (Big Spring); County Law Enforcement Center (Big Spring); Howard County 118th District Court (Big Spring); Grand Falls-Royalty ISD (new this quarter); Imperial, Buena Vista ISD (new this quarter). | (100 MBps) (50 Mbps) (20 Mbps) | 0 | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | NA | NA | FALSE | NA | Planned Q2 2012 activities and accomplishments include: Dell City will complete the route to Wink ISD, currently 3.22 of the 10.0 mile route is completed. Dell City to connect at least 13 CAI's and possibly up to 21 new CAI connections. Hill Country Telephone is waiting for lines to be moved by Verizon and AT&T prior to continuing their two remaining routes. Hill Country Telephone plans to begin construction on their two remaining routes to Big Lake and Rankin. Big Bend Telephone plans to complete a 30 mile wireless link to connect the Marathon ISD. Big Bend will complete the CAI connections to Fort Davis ISD; Fort Stockton; Valentine and Marfa as the construction of these routes has been completed. | Region 18 Education Svc Ctr. | We have not encountered any obstacles that are slowing down our construction progress. We anticipate construction to continue now ahead of schedule and to close the gap with our CAI connections this coming quarter. | We do not anticipate any issues to slow our progress at this point in our project. | TRUE
NT10BIX5570138 | 2012 | Q3 | Q3 - 2012 | This quarter, Dell City our largest contracted telephone company completed 135 total construction miles. Fiber has now been installed so that 39 CAI's along this route can be offered service. The fiber has been taken to the drop point at the 6 ISD's (Schools) and we are working to connect to the equipment in building to supply service. We anticipate all six remaining ISD's on this route to be connected by year end. Hill Country Telephone also completed construction of 21.49 miles as planned. Two of the CAI's on this route were connected last quarter and the remaining two now have service available and will be connected to the service by the end of the year. This brings four of five contracted companies to completion with their fiber construction for a total of 174.07 miles completed (80% of total project miles). We have spent 85.6% of program funds. Our project created 15.21 jobs this quarter. We will move our focus to Community Outreach and connecting as many CAI locations as possible. | 174 | 0 | 0 | 0 | 174 | 1 | 1 | 4 | +10 miles to baseline. WesTex completed 1.33 miles; Poka Lambro completed 2.90 miles; Hill Country Telephone 21.49 miles; Dell City Telephone 135 miles; Big Bend Telephone 13.35 miles completed | NA | NA | NA | +10 miles to baseline. WesTex completed 1.33 miles; Poka Lambro completed 2.90 miles; Hill Country Telephone 21.49 miles; Dell City Telephone 135 miles; Big Bend Telephone 13.35 miles completed | -1 variance to baseline. The final link is to the McDonald Observatory. This route will actually be a combination of buried fiber and aeriel fiber. We have reported incorrectly when saying wireless. It is actually aeriel fiber. | The wireless link in Mentone for the Loving County Courthouse has been established. The second and third have not yet been completed. We plan for their completion in Q1 2013. | For clarification our definition of interconnection points has been modified since the baseline submission. A peering point where two providers connect to each other will occur 4 times in the Region 18 project. At this time one of these locations has upgraded equipment added by Dell City Telephone. WesTex Midland connection was completed Q4 2011; Big Bend Midland connection was completed in Q2 of 2012; Dell City Pecos and TLSN McCamey were completed in Q3 of 2012. | 5 | 0 | 40 | We have signed agreements with the following companies: Dell City Telephone; Big Bend Telephone; Poka Lambro Telephone; WesTex Telephone; Hill Country Telephone. | NA | NA | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | 12 | 0 | 12 | 100 | Andrews ISD; Midland DPS; Big Spring Chief of Police; Howard County Library; Howard County Judge (Big Spring); County Law Enforcement Center (Big Spring); Howard County 118th District Court (Big Spring); Big Spring Chamber of Commerce; Grand Falls-Royalty ISD; Buena Vista ISD; Pecos ISD (new this quarter); Culberson County ISD (new this quarter) | NA | Andrews ISD; Midland DPS; Big Spring Chief of Police; Howard County Library; Howard County Judge (Big Spring); County Law Enforcement Center (Big Spring); Howard County 118th District Court (Big Spring); Big Spring Chamber of Commerce; Grand Falls-Royalty ISD; Buena Vista ISD; Pecos ISD (new this quarter); Culberson County ISD (new this quarter) | (100 Mbps) (50 Mbps) (20 Mbps) | 0 | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | NA | NA | FALSE | NA | For Q4 2012 we plan to connect a minimum of 6 additional CAI locations: Dell City Telephone will connect the remaining ISD locations in Balmorhea; Wink; Kermit and Monahans. HCTC will begin providing service to Rankin ISD and Big Lake ISD. We will continue to contact other potential CAI locations along the completed routes to let them know that service is available. We will work with our telephone companies on this process. Four of five telephone companies have completed all miles to be constructed. We do not plan to sign any additional broadband wholesaler or last mile agreements. Big Bend should complete a total of 22.66 miles by the end of this quarter. | Region 18 Education Svc Ctr. | Nothing as of September 30. | None anticipated. | TRUE
NT10BIX5570138 | 2012 | Q4 | Q4 - 2012 | This quarter we have begun providing service to the two remaining CAI locations to be connected by Hill Country Telephone. These locations are: Buena Vista ISD in Imperial, TX and Rankin ISD in Rankin, TX. Region 18 ESC is working with Hill Country on the Community Outreach portion of the project now that the fiber is in place and service is available. We hope to be able to begin service to some or all of the additional 12 CAI opportunities on these routes in the near future. Dell City Telephone is now providing service to six ISD locations and seven additional CAI locations (one of these is new to the project) for a total of 13 CAI's connected with service this quarter. We are actively pursuing the remaining CAI's on these routes and anticipate a strong response. Dell City Telephone has been very proactive with their pricing to help several public housing locations with afford ability We have completed 174.07 project miles, (80%) of total project miles. We have spent 86% of program funds. Our project created 6.8 jobs this quarter. | 174 | 0 | 0 | 0 | 174 | 1 | 1 | 4 | -11.3 miles to baseline. Construction stopped due to route change requests. | NA | NA | NA | -11.3 miles to baseline. Construction stopped due to route change requests. | -2 to baseline. The wireless link in Mentone is up and running. The two remaining links are in Marathon and Fort Stockton and have not been connected yet due to the need to stop construction on the Big Bend Telephone routes. | -3 to baseline. One tower in Mentone has been errected. The second tower for Mentone was not needed as we were able to connect to an existing tower on the courthouse. The other towers are on the Big Bend routes and have not been constructed. | For clarification our definition of interconnection points has been modified since the baseline submission. A peering point where two providers connect to each other will occur 4 times in the Region 18 CST project. At this time one of these locations has upgraded equipment added by Dell City Telephone. The WesTex Midland connection was completed Q4 2011; Big Bend Midland connection was completed in Q2 of 2012; Dell City Pecos and TLSN McCamey were completed in Q3 2012. | 5 | 0 | 40 | We have signed agreements with the following companies: Dell City Telephone; Big Bend Telephone; Poka Lambro Telephone; WesTex Telephone; Hill Country Telephone. | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 25 | 0 | 25 | 100 | Andrews ISD;Midland DPS; Big Spring Chief of Police; Howard County Library; Howard County Judge (Big Spring); County Law Enforcement Center (Big Spring); Howard County 118th District Court (Big Spring); Big Spring Chamber of Commerce; Grand Falls-Royalty ISD; Buena Vista ISD; Reagan County ISD (new); Rankin ISD (new); Kermit ISD (new); Wink-Loving ISD (new); Monahans-Wickett-Pyote ISD (new); Ward County Judge (new); Monahans, Ward County Sheriff (new); Balmorhea ISD (new); Pecos-Barstow-Toyah ISD; Pecos Research and Testing Center (new); Pecos - Mayor (new); Pecos Chief of Police (new); Pyote Mayor and City Hall (new); Culberson County- Allamoore ISD; Monahans EMS Ward County (new) | NA | Andrews ISD;Midland DPS; Big Spring Chief of Police; Howard County Library; Howard County Judge (Big Spring); County Law Enforcement Center (Big Spring); Howard County 118th District Court (Big Spring); Big Spring Chamber of Commerce; Grand Falls-Royalty ISD; Buena Vista ISD; Pecos ISD; Culberson County ISD; Reagan County ISD (new); Rankin ISD (new); Kermit ISD (new); Wink-Loving ISD (new); Monahans-Wickett-Pyote ISD (new); Ward County Judge (new); Monahans, Ward County Sheriff (new); Balmorhea ISD (new); Pecos-Barstow-Toyah ISD (new); Pecos Research and Testing Center (new); Pecos - Mayor (new); Pecos Chief of Police (new); Pyote Mayor and City Hall (new); Culberson County- Allamoore ISD (new); Monahans EMS Ward County (new) | (100 Mbps) (50 Mbps) (20 Mbps) | 0 | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | In the next quarter we plan to connect at least 10 additional CAI's and potentially 20+. The ability to connect the 20+ will depend upon our ability to receive approval for the route changes to the Big Bend Telephone routes. We are continuing community outreach programs and will have a joint press release with Dell City Telephone in the first quarter to highlight our project. We will file federal security interest paperwork this quarter as required. Spending will also depend upon our ability to resume construction. We will not sign any additional broadband wholesaler agreements. If route changes are approved we expect to report construction of an additional 9.31 miles of fiber and the addition of two wireless links, one in Marathon and one in Fort Stockton. | Region 18 Education Svc Ctr. | This quarter we have encountered the need to submit 6 route change requests for Big Bend Telephone routes. The routes in question were changed due to the fact that there were existing utilities along the planned routes and we were unable to obtain the permits for construction. The new routes are in existing ROW's and in previously disturbed areas. The route change requests have been submitted and are in the process of being reviewed. We have been working closely with our FPO and NTIA to provide the necessary information. We also have an additional route change request to submit for Big Bend on the route to Fort Davis but must wait to do this until we are back in compliance with the previous route changes. The route changes will not have a negative impact on the project budget or on the number of CAI locations we can connect to. There will be a reduction of 11 route miles. If the route changes are approved in a timely manner there will not be a negative impact on the project. However, to complete the remaining routes will require 4-5 months of construction. A delay in the approval will impact our ability to complete all the routes of our project prior to the end of the award period. | We are hopeful that the route change requests that we have submitted will be approved and construction allowed to resume on all remaining routes. This is our only issue at this time and the only item preventing our progress. | TRUE
NT10BIX5570138 | 2013 | Q1 | Q1 - 2013 | In this quarter Region 18 ESC Connect Southwest Texas was granted approval on our requested route changes. This allowed us to complete construction on 6 routes and connect an additional 6 CAI locations. This represents the completion of an additional 3.79 route miles. We have also been able to progress to 50% completion on a 30 mile wireless route(these miles will be reported when route is completed). We have submitted a final route change request for the route to McDonald Observatory. Final maps for this route change request were submitted in early April. We currently have 7 additional CAI locations pending that were listed as possible connections through Dell City Telephone. These have been approached through our community outreach and we hope to connect within the next two quarters (prior to project completion). Regarding total project miles: Original mile total from baseline is 218. At our site visit in Q4 2011 we were directed to add 41.05 wireless miles to our project total. This brought total project miles to 259.05. Based upon the approved route changes we will reduce total project miles by 11.09 miles. This will make our new total project miles (buried and aerial fiber and wireless) 247.96. We have completed a total of 177.86 miles to date. Our project miles are now 72% complete. (Project miles % complete was incorrectly reported at 80% in Q4 2012). We have spent a total of 90% of program funds to dated and created 4.05 full time jobs this quarter. | 178 | 0 | 0 | 0 | 178 | 1 | 1 | 4 | -29 miles to baseline. This is due to the work stoppage during the route change requests. We intend to bridge this gap this quarter. | NA | NA | NA | -29 miles to baseline. This is due to the work stoppage during the route change requests. We intend to bridge this gap this quarter. | -2 to baseline. The wireless link in Mentone is up and running. The two remaining links are in Marathon and Fort Stockton and have not been connected yet due to the need to stop construction on the Big Bend Telephone routes. | -3 to baseline. One tower in Mentone has been errected. The second tower for Mentone was not needed as we were able to connect to an existing tower on the courthouse. The other towers are on the Big Bend routes and have not been constructed. | For clarification our definition of interconnection points has been modified since the baseline submission. A peering point where two providers connect to each other will occur 4 times in the Region 18 CST project. At this time one of these locations has upgraded equipment added by Dell City Telephone. The WesTex Midland connection was completed Q4 2011; Big Bend Midland connection was completed in Q2 of 2012; Dell City Pecos and TLSN McCamey were completed in Q3 2012. | 5 | 0 | 40 | We have signed agreements with the following companies: Dell City Telephone; Big Bend Telephone; Poka Lambro Telephone; WesTex Telephone; Hill Country Telephone. | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 31 | 0 | 31 | 100 | Andrews ISD;Midland DPS; Big Spring Chief of Police; Howard County Library; Howard County Judge (Big Spring); County Law Enforcement Center (Big Spring); Howard County 118th District Court (Big Spring); Big Spring Chamber of Commerce; Grand Falls-Royalty ISD; Buena Vista ISD; Reagan County ISD; Rankin ISD; Kermit ISD; Wink-Loving ISD; Monahans-Wickett-Pyote ISD; Ward County Judge; Monahans, Ward County Sheriff; Balmorhea ISD; Pecos-Barstow-Toyah ISD; Pecos Research and Testing Center; Pecos - Mayor; Pecos Chief of Police; Pyote Mayor and City Hall; Culberson County- Allamoore ISD; Monahans EMS Ward County; Iraan-Sheffield ISD (New); Fort Davis ISD (New); Valentine ISD (New); Marfa ISD (New); Fort Stockton ISD (New); McCamey ISD (New). | NA | Andrews ISD;Midland DPS; Big Spring Chief of Police; Howard County Library; Howard County Judge (Big Spring); County Law Enforcement Center (Big Spring); Howard County 118th District Court (Big Spring); Big Spring Chamber of Commerce; Grand Falls-Royalty ISD; Buena Vista ISD; Reagan County ISD; Rankin ISD; Kermit ISD; Wink-Loving ISD; Monahans-Wickett-Pyote ISD; Ward County Judge; Monahans, Ward County Sheriff; Balmorhea ISD; Pecos-Barstow-Toyah ISD; Pecos Research and Testing Center; Pecos - Mayor; Pecos Chief of Police; Pyote Mayor and City Hall; Culberson County- Allamoore ISD; Monahans EMS Ward County; Iraan-Sheffield ISD (New); Fort Davis ISD (New); Valentine ISD (New); Marfa ISD (New); Fort Stockton ISD (New); McCamey ISD (New). | (100 Mbps) (50 Mbps) (20 Mbps) | 0 | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | NA | NA | FALSE | NA | During the next quarter we will continue to work on the final routes of our project. These include the wireless link to Marathon which was 50% complete at the end of Q1 and the route to Crane which has not yet begun. We anticipate adding 30 aerial miles and 10 miles of fiber during the second quarter of 2013. This will bring our total route miles to 218 miles. We are waiting for route change approval for the McDonald Observatory. We will continue with community outreach and will look to have service to 6 additional CAI locations for Dell Telephone. They are located in Pecos, Van Horne, and Wink. We also intend to purchase equipment for our project. | Region 18 Education Svc Ctr. | The greatest challenge faced by the Region 18 team this quarter was the delay due to the route change requests. We are pleased to have received approval to move forward this quarter on the changes submitted in October. We also submitted one additional (and final) route change request this quarter and are hopeful for a speedy review. | Our one remaining challenge is the final route change request outstanding for the McDonald Observatory connection. Construction for this route will take 2 -4 months and without approval we will be challenged to complete our project on time. | TRUE
NT10BIX5570138 | 2013 | Q2 | Q2 - 2013 | This quarter our final route change request was approved and construction on our final route to the McDonald Observatory is scheduled to begin July 10, 2013. This route is estimated to take 60 days to complete. Based upon this we will be submitting a request to extend our project for an additional 30 days. If approved our project end date would change from August 31 to September 30. This request will be submitted in July 2013. The Wireless route to Marathon was completed this quarter and the route to Crane is 80% complete with planned completion in early July. We completed 55.8 miles this quarter. This puts our project 7.3% ahead of baseline miles and on track with our revised miles. Our total project miles completed to date are 233.66. This represents 94.2% of our total project miles completed. This quarter we connected 31 additional CAI locations. To date we have spent 90% of project funds. No broadband wholesaler/last mile agreements were signed this quarter. Our plan was 5 agreements and these have all been completed. | 234 | 0 | 0 | 0 | 234 | 3 | 1 | 4 | 7.3% ahead of baseline. This is due to the addition of wireless miles not included in the baseline projections but added to our total miles after our site visit. As reported in Q1 2013 our new target miles are 247.96. We are 94% complete as related to our new target miles. The remaining miles will be completed in our final project quarter. | NA | NA | NA | 7.3% ahead of baseline. This is due to the addition of wireless miles not included in the baseline projections but added to our total miles after our site visit. As reported in Q1 2013 our new target miles are 247.96. We are 94% complete as related to our new target miles. The remaining miles will be completed in our final project quarter. | No variance | -3 to baseline. One tower in Mentone has been constructed. The second tower for Mentone was not needed as we were able to connect to an existing tower on the courthouse. The other towers are on the Big Bend routes. Big bend was able to use existing towers to install the wireless equipment. | For clarification our definition of interconnection points has been modified since the baseline submission. A peering point where two providers connect to each other will occur 4 times in the Region18 ESC project. At this time one of these locations has upgraded equipment added by Dell City Telephone. The WesTex Midland connection was completed Q4 2011; Big Bend Midland connection was completed in Q2 2012; Dell City Pecos and TLSN McCamey were completed in Q3 2012. | 5 | 0 | 40 | We have agreements with the following companies: Dell City Telephone; Big Bend Telephone; Poka Lambro Telephone; WesTex Telephone; Hill Country Telephone. | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 62 | 0 | 62 | 100 | Additional CAI locations to be reported upon completion of the final two project routes. CAI locations currently connected are: (Dell City) Kermit ISD; Winkler County Library; Kermit Fire Chief; Winkler County Judge; Public Housing Authority in Kermit; Kermit Chief of Police; Kermit Sheriff; Pecos-Barstow-Toyah ISD; Reeves County Library; Reeves County Hospital; Pecos Research and Testing Center; Pecos DPS; Mayor of Pecos; Reeves County Judge; Pecos Public Housing Authority; Pecos Chief of Police; Pecos Sheriff; Mayor of Pyote; Culberson County-Allamoore ISD; Van Horne City County Library; Van Horne DPS; Culberson County Judge; Mayor of Van Horne; Van Horne Sheriff; Wink-Loving ISD; Wink Fire Chief; Wink Mayor; Wink Public Housing Authority; Winkler County Barn; Wink Volunteer Fire Department; Monahans-Wickett-PeyoteISD; Mayor Monahans; Ward County Judge; Monahans Public Housing Authority; Monahans Sheriff; Balmorhea ISD; Balmorhea Mayor; Balmorhea Public Housing Authority; Toyah City Hall; Loving County Judge; Mentone Sheriff, Ward County EMS Monahans. (Big Bend) Iraa-Sheffield ISD; Fort Davis ISD; Valentine ISD; MarathonISD; Marfa ISD; Fort Stockton DPS; Fort Stockton ISD; McCamey ISD. (Hill Country) Reagan County ISD; Buena Vista ISD; Grandfalls-Royalty ISD; Rankin ISD. (Poka Lambro) Andrews ISD; Midland DPS. (WesTex) Howard County Library; Howard County Court House; Big Spring Chief of Police; Big Spring District Court; Big Spring Chamber of Commerce; Big Spring CountyLaw Enforcement Center. | NA | Additional CAI locations to be reported upon completion of the final two project routes. CAI locations currently connected are: (Dell City) Kermit ISD; Winkler County Library; Kermit Fire Chief; Winkler County Judge; Public Housing Authority in Kermit; Kermit Chief of Police; Kermit Sheriff; Pecos-Barstow-Toyah ISD; Reeves County Library; Reeves County Hospital; Pecos Research and Testing Center; Pecos DPS; Mayor of Pecos; Reeves County Judge; Pecos Public Housing Authority; Pecos Chief of Police; Pecos Sheriff; Mayor of Pyote; Culberson County-Allamoore ISD; Van Horne City County Library; Van Horne DPS; Culberson County Judge; Mayor of Van Horne; Van Horne Sheriff; Wink-Loving ISD; Wink Fire Chief; Wink Mayor; Wink Public Housing Authority; Winkler County Barn; Wink Volunteer Fire Department; Monahans-Wickett-PeyoteISD; Mayor Monahans; Ward County Judge; Monahans Public Housing Authority; Monahans Sheriff; Balmorhea ISD; Balmorhea Mayor; Balmorhea Public Housing Authority; Toyah City Hall; Loving County Judge; Mentone Sheriff, Ward County EMS Monahans. (Big Bend) Iraa-Sheffield ISD; Fort Davis ISD; Valentine ISD; MarathonISD; Marfa ISD; Fort Stockton DPS; Fort Stockton ISD; McCamey ISD. (Hill Country) Reagan County ISD; Buena Vista ISD; Grandfalls-Royalty ISD; Rankin ISD. (Poka Lambro) Andrews ISD; Midland DPS. (WesTex) Howard County Library; Howard County Court House;Big Spring Chief of Police; Big Spring District Court; Big Spring Chamber of Commerce; Big Spring CountyLaw Enforcement Center. | (100 Mbps) (50 Mbps) (20 Mbps) | 0 | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | In the next quarter we plan to complete our final two routes and a total of 14 additional miles. We plan to report 2 additional CAI locations. Crane and the McDonald Observatory routes will be completed. Our approved project completion date is August 31, 2013. Due to the delay caused by the route change requests and the additional environmental review we will be requesting and additional 30 days to complete our project. The one route to Crane was 80% complete at the end of quarter 2 and has a planned completion date of 7/31/2013. The final route to McDonald Observatory will begin in early July and has an estimated 60 day completion. The project will be complete by September 30, 2013. We are not negotiating or pursuing any additional broadband wholesaler/last mile agreements and do not intend to add any through the next quarter. | Region 18 Education Svc Ctr. | This past quarter our biggest challenge was the route change request and the need for additional environmental review that slowed down the approval process. As stated above the approval has been granted and the project is continuing. Our FPO and team were very helpful with this process and we are looking forward to completing the final routes in our project. | We do not anticipate any challenges at this time. We are confident that if our extension request is approved we will complete our project by September 30, 2013. | TRUE
NT10BIX5570138 | 2013 | Q3 | Q3 - 2013 | This quarter the route to Crane ISD was completed. An extension request for an additional 30 days was approved moving our project end date from August 31 to September 30. The request was made so that we can complete the route to the McDonald Observatory. During the extension month a development outside the control of Region 18 and outside the control of our contractor Big Bend Telephone required us to request an additional extension to December 31, 2013. The McDonald Observatory Route is being constructed in very rugged terrain - up the side of a mountain. The local utility company has begun to replace existing poles along this route that Region 18 needs to connect aeriel fiber to. Some of these spans are greater than 1000 ft. Once the poles are replaced additional BTOP route construction will take approximately 3 weeks. We completed 7.9 miles this month for the Crane route. Total project miles completed to date are 241.56. This represents 95.9% of total project miles. WE are behind plan the 10.34 aeriel miles to the Observatory. We connected one CAI - Crane. To date we have spent 96% of project funds and are outstanding the final construction invoice for the McDonald Observatory Route. We will connect one final CAI. No broadband wholesaler or last mile agreements were signed this quarter. Our plan was 5 agreements and these have been completed. | 242 | 0 | 0 | 0 | 242 | 3 | 1 | 4 | We are 95.9% complete. Total miles will be approximately 252 upon completion of the aeriel fiber install for McDonald Observatory. | no variance | NA | NA | We are 95.9% complete. Total miles will be approximately 252 upon completion of the aeriel fiber install for McDonald Observatory. | No variance | -3 to baseline. One tower in Mentone has been constructed. The second tower for Mentone was not needed as we were able to connect to an existing tower on the courthouse. The other towers are on Big Bend routes. Big Bend was able to use existing towers to install the wireless equipment. | For clarification our definition of interconnection points has been modified since the baseline submission. A peering point where two providers connect to each other will occur 4 times in the Region 18 ESC project. At this time one of these locations has upgraded equipment added by Dell City Telephone. The WesTex Midland connection was completed in Q4 2011. Big Bend Midland connection was completed in Q2 2012; Dell City Pecos and TLSN-McCamey were completed in Q3 2012. | 5 | 0 | 40 | We have signed agreements with the following companies: Dell City Telephone; Big Bend Telephone; WesTex Telephone; Poka Lambro and Hill Country Telephone. | NA | NA | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 62 | 0 | 62 | 100 | Additional CAI locations to be reported upon completion of the final two project routes. CAI locations currently connected are: (Dell City) Kermit ISD; Winkler County Library; Kermit Fire Chief; Winkler County Judge; Public Housing Authority in Kermit; Kermit Chief of Police; Kermit Sheriff; Pecos-Barstow-Toyah ISD; Reeves County Library; Reeves County Hospital; Pecos Research and Testing Center; Pecos DPS; Mayor of Pecos; Reeves County Judge; Pecos Public Housing Authority; Pecos Chief of Police; Pecos Sheriff; Mayor of Pyote; Culberson County-Allamoore ISD; Van Horne City County Library; Van Horne DPS; Culberson County Judge; Mayor of Van Horne; Van Horne Sheriff; Wink-Loving ISD; Wink Fire Chief; Wink Mayor; Wink Public Housing Authority; Winkler County Barn; Wink Volunteer Fire Department; Monahans-Wickett-PeyoteISD; Mayor Monahans; Ward County Judge; Monahans Public Housing Authority; Monahans Sheriff; Balmorhea ISD; Balmorhea Mayor; Balmorhea Public Housing Authority; Toyah City Hall; Loving County Judge; Mentone Sheriff, Ward County EMS Monahans. (Big Bend) Iraa-Sheffield ISD; Fort Davis ISD; Valentine ISD; MarathonISD; Marfa ISD; Fort Stockton DPS; Fort Stockton ISD; McCamey ISD. (Hill Country) Reagan County ISD; Buena Vista ISD; Grandfalls-Royalty ISD; Rankin ISD. (Poka Lambro) Andrews ISD; Midland DPS. (WesTex) Howard County Library; Howard County Court House; Big Spring Chief of Police; Big Spring District Court; Big Spring Chamber of Commerce; Big Spring CountyLaw Enforcement Center; Crane ISD | NA | Additional CAI locations to be reported upon completion of the final two project routes. CAI locations currently connected are: (Dell City) Kermit ISD; Winkler County Library; Kermit Fire Chief; Winkler County Judge; Public Housing Authority in Kermit; Kermit Chief of Police; Kermit Sheriff; Pecos-Barstow-Toyah ISD; Reeves County Library; Reeves County Hospital; Pecos Research and Testing Center; Pecos DPS; Mayor of Pecos; Reeves County Judge; Pecos Public Housing Authority; Pecos Chief of Police; Pecos Sheriff; Mayor of Pyote; Culberson County-Allamoore ISD; Van Horne City County Library; Van Horne DPS; Culberson County Judge; Mayor of Van Horne; Van Horne Sheriff; Wink-Loving ISD; Wink Fire Chief; Wink Mayor; Wink Public Housing Authority; Winkler County Barn; Wink Volunteer Fire Department; Monahans-Wickett-PeyoteISD; Mayor Monahans; Ward County Judge; Monahans Public Housing Authority; Monahans Sheriff; Balmorhea ISD; Balmorhea Mayor; Balmorhea Public Housing Authority; Toyah City Hall; Loving County Judge; Mentone Sheriff, Ward County EMS Monahans. (Big Bend) Iraa-Sheffield ISD; Fort Davis ISD; Valentine ISD; MarathonISD; Marfa ISD; Fort Stockton DPS; Fort Stockton ISD; McCamey ISD. (Hill Country) Reagan County ISD; Buena Vista ISD; Grandfalls-Royalty ISD; Rankin ISD. (Poka Lambro) Andrews ISD; Midland DPS. (WesTex) Howard County Library; Howard County Court House; Big Spring Chief of Police; Big Spring District Court; Big Spring Chamber of Commerce; Big Spring CountyLaw Enforcement Center; Crane ISD | All ISD locations (28) are receiving 100mg, all other locations are receiving between 10mg and 100mg of service (34). | 0 | 0 | 0 | 0 | 0 | No variance | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | In the next quarter we plan to complete our final route to the McDonald Observatory and to complete our BTOP project! We will complete a total of 252 project miles and add one additional CAI location. The project will reach completion by December 31, 2013. We are not negotiating or pursuing any additional broadband wholesaler last mile agreements and do not intend to. | Region 18 Education Svc Ctr. | This past quarter our biggest challenge was the difficulty with the power company on our final route. Their choice to change the poles during our construction project forced us to stop work at a critical time and delaying our ability to complete the route. | We do not anticipate any additional challenges at this time. | TRUE
NT10BIX5570138 | 2013 | Q4 | Q4 - 2013 | In this quarter Region 18 ESC completed the final route of the project. The final route to the McDonald Observatory was completed in early December and service is now connected. Final project mile totals are: Poka Lambro 2.9 miles completed; WesTex 1.33 miles completed; Hill Country Telephone 21.49 miles completed; Dell City Telephone 121 miles of fiber plus 14 miles of wireless for a total of 135 miles completed; Big Bend Telephone 49.37 miles of fiber plus 33.60 miles of wireless air miles. Project miles final total is 243.69 miles. Our total project miles are 8.21 miles less than our revised plan due to approved route changes. We are actually 25.69 miles greater than our baseline plan of 218 miles. Total number of routes and CAI connections were not impacted by the number of miles. We have spent a total of $11,582,881 in federal funds. (note that currently our draw down amount is less by $205,830.40. This amount will be drawn down in January of 2014). We spent 96.7% of our allocated Federal Funds. Our final project is 3.3% under budget. As a result of the 244 miles of fiber and 63 CAI locations connected directly with grant funds, this project has encouraged additional fiber installation and upgrades by the local telecommunication companies. We have introduced competition in broadband and telephone service where there was previously only one provider with lower speed and less reliable service offered. Wireless providers are expanding LTE coverage in more rural areas because the increased fiber infrastructure is allowing wireless towers to be upgraded to handle higher bandwidth applications. All public schools in Region 18 now have at least 100 Mbps of Internet service with the ability to upgrade to 1 Gbps, aligning with the National Broadband Plan. As a direct result, the schools in our area are rapidly adopting one-to-one initiatives where every student in high school is issued a computer or tablet device for instruction. This is accelerating the digital literacy of the students in our area. | 244 | 0 | 0 | 0 | 244 | 3 | 1 | 4 | Our final miles are 8 miles less than revised forecast due to approved route changes for Big Bend. The lower miles did not have an impact on our ability to complete all approved routes and connect all planned CAI locations. We are 11.7% ahead of baseline miles. | No variance | No variance | NA | Our final miles are 8 miles less than forecast due to approved route changes for Big Bend. The lower miles did not have an impact on our ability to complete all approved routes and connect all planned CAI locations. | No variance | -3 to baseline. One tower in Mentone has been constructed. The second tower for Mentone was not needed as we were able to connect to an existing tower on the courthouse. The other towers are on Big Bend routes and Big Bend was able to use existing towers to install the wireless equipment. | For clarification our definition of interconnection points has been modified since the baseline submission. A peering point where two providers connect to each other will occur 4 times in the Region 18 ESC project. At this time one of these locations has upgraded equipment added by Dell City Telephone. The Wes Tex Midland connection was completed in Q4 2011. Big Bend Midland connection was completed in Q2 2012; Dell City Pecos and TLSN-McCamey were completed in Q3 2012. | 5 | 0 | 40 | We have signed agreements with the following companies: Dell City Telephone; Big Bend Telephone; WesTex Telephone; Poka Lambro and Hill Country Telephone. | NA | NA | 5 | 0 | 0 | 0 | The companies with signed agreements are now receiving access to Region 18's network. | NA | NA | NA | 63 | 0 | 63 | 100 | CAI locations currently connected are: (Dell City) Kermit ISD; Winkler County Library; Kermit Fire Chief; Winkler County Judge; Public Housing Authority in Kermit; Kermit Chief of Police; Kermit Sheriff; Pecos-Barstow-Toyah ISD; Reeves County Library; Reeves County Hospital; Pecos Research and Testing Center; Pecos DPS; Mayor of Pecos; Reeves County Judge; Pecos Public Housing Authority; Pecos Chief of Police; Pecos Sheriff; Mayor of Pyote; Culberson County-Allamoore ISD; Van Horne City County Library; Van Horne DPS; Culberson County Judge; Mayor of Van Horne; Van Horne Sheriff; Wink-Loving ISD; Wink Fire Chief; Wink Mayor; Wink Public Housing Authority; Winkler County Barn; Wink Volunteer Fire Department; Monahans-Wickett-PeyoteISD; Mayor Monahans; Ward County Judge; Monahans Public Housing Authority; Monahans Sheriff; Balmorhea ISD; Balmorhea Mayor; Balmorhea Public Housing Authority; Toyah City Hall; Loving County Judge; Mentone Sheriff, Ward County EMS Monahans. (Big Bend) Iraa-Sheffield ISD; Fort Davis ISD; Valentine ISD; MarathonISD; Marfa ISD; Fort Stockton DPS; Fort Stockton ISD; McCamey ISD. (Hill Country) Reagan County ISD; Buena Vista ISD; Grandfalls-Royalty ISD; Rankin ISD. (Poka Lambro) Andrews ISD; Midland DPS. (WesTex) Howard County Library; Howard County Court House; Big Spring Chief of Police; Big Spring District Court; Big Spring Chamber of Commerce; Big Spring CountyLaw Enforcement Center; Crane ISD; McDonald Observatory. | NA | CAI locations currently connected are: (Dell City) Kermit ISD; Winkler County Library; Kermit Fire Chief; Winkler County Judge; Public Housing Authority in Kermit; Kermit Chief of Police; Kermit Sheriff; Pecos-Barstow-Toyah ISD; Reeves County Library; Reeves County Hospital; Pecos Research and Testing Center; Pecos DPS; Mayor of Pecos; Reeves County Judge; Pecos Public Housing Authority; Pecos Chief of Police; Pecos Sheriff; Mayor of Pyote; Culberson County-Allamoore ISD; Van Horne City County Library; Van Horne DPS; Culberson County Judge; Mayor of Van Horne; Van Horne Sheriff; Wink-Loving ISD; Wink Fire Chief; Wink Mayor; Wink Public Housing Authority; Winkler County Barn; Wink Volunteer Fire Department; Monahans-Wickett-PeyoteISD; Mayor Monahans; Ward County Judge; Monahans Public Housing Authority; Monahans Sheriff; Balmorhea ISD; Balmorhea Mayor; Balmorhea Public Housing Authority; Toyah City Hall; Loving County Judge; Mentone Sheriff, Ward County EMS Monahans. (Big Bend) Iraa-Sheffield ISD; Fort Davis ISD; Valentine ISD; MarathonISD; Marfa ISD; Fort Stockton DPS; Fort Stockton ISD; McCamey ISD. (Hill Country) Reagan County ISD; Buena Vista ISD; Grandfalls-Royalty ISD; Rankin ISD. (Poka Lambro) Andrews ISD; Midland DPS. (WesTex) Howard County Library; Howard County Court House; Big Spring Chief of Police; Big Spring District Court; Big Spring Chamber of Commerce; Big Spring CountyLaw Enforcement Center; Crane ISD; McDonald Observatory. | All ISD locations (28) are receiving 100 mg, all other are receiving between 10 mg and 100 mg of service (35). | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | FALSE | NA | We will plan to draw down the final $205,830.40 of federal funds and begin our project closeout requirements. We are not negotiating or pursuing any additional broadband wholesaler last mile agreements and do not intend to. | Region 18 Education Svc Ctr. | The Region 18 ESC project is now 100% complete. All planned routes and CAI locations are connected. | No challenges expected. | TRUE
NT10BIX5570139 | 2010 | Q4 | Q4 - 2010 | - Completed construction on the first 6 miles. - Completed 90% of the attachment agreements with progress achieved toward completion on the remaining agreement. - Finalized construction vendor. - Submitted over 97% of attachment applications (440 of 450 applications submitted); 80% of pole owner make-ready surveys complete; 3% licenses received. - 6% of make-ready has been completed by pole owners. - Completed over half of necessary bridge engineering/permit applications. - Completed 90% of pole gap engineering. | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 9 | Waiting on make-ready for additional miles | No variance; no leases planned - dark fiber | No variance; none planned | No variance; none planned | Waiting on make-ready for additional miles | None planned | None planned | Better than expected service provider take-rate/private investment | 4 | 4 | 80 | - GWI, Axiom Technologies, Pioneer Broadband, University of Maine System | - Dark fiber, prices are listed on the MFC website at www.mainefiberco.com | - N/A; this is a dark fiber network. | 4 | 4 | 4 | 0 | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups | Dark fiber only; speed will vary depending on last mile provider equipment. | 9 | 0 | 9 | 0 | Increased demand for healthcare information technologies (HIT) and education | No variance | Increased demand for HIT and education | Dark fiber only; speed will vary depending on last mile provider equipment. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data | N/A | N/A | N/A | Dark fiber only; speed will vary depending on last mile provider equipment. | - Dark fiber network. | FALSE | No variance | - Depending on the speed of make-ready completion, we anticipate completing 20 miles of fiber deployment with a significant portion of these miles also completing construction. - We anticipate executing the remaining attachment agreement; submitting the final make-ready applications to the pole owners; continued completion of the pole owners' make-ready surveys; and continuing to manage the pole licensing process. - Continue bridge engineering and permitting. - Continue to engineer service provider use of the network, and negotiate agreements. | Maine Fiber Company, Inc. | - Third-party make-ready completion continues to be slow impacting our construction schedule. We are working daily with the pole owners to complete make-ready in an effective and consistent manner. We are receiving cooperation from the pole owners. - We are making adequate and expected progress against baseline milestones. Slow make-ready completion hasn't fully impacted our construction schedule, but we are watching it. The pole owners will have to accelerate make-ready completion dates to make the project schedule. | - Make-ready completion by pole owners is our biggest challenge and may impact the construction schedule. | TRUE
NT10BIX5570139 | 2011 | Q1 | Q1 - 2011 | - Completed construction on 20 miles in this quarter bringing the total to 26 miles to date. - Completed 100% of the attachment agreements. Submitted 100% of the attachment applications for the network backbone (539 applications); over 30% of third-party make-ready is completed and we've received 30% of all licenses from the pole owners. - Finalized procurement of archeological vendor; prepared RFP for pole gap contractor - Continued review of Community Anchor Institutions' applications and began attachment applications for the first-round of approved Community Anchor Institutions | 26 | 0 | 0 | 0 | 26 | 0 | 0 | 16 | Completed construction on 1 additional mile over baseline due to early make-ready completion. | No variance; no leases planned - dark fiber | No variance; none planned | No variance; none planned | Completed construction on 1 additional mile over baseline due to early make-ready completion. | None planned | None planned | Better than expected service provider take-rate/private investment. The positive rate of make-ready completion demonstrated early project success to the community and generated increased interest and additional commitments to interconnect with the dark fiber network. | 4 | 7 | 80 | - Not applicable this quarter | - Dark fiber prices are listed on the MFC website at www.mainefiberco.com | - N/A; this is a dark fiber network. | 4 | 0 | 4 | 0 | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups | N/A | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups | Dark fiber only; speed with vary depending on last mile provider equipment. | 10 | 1 | 9 | 0 | Increased demand for healthcare information technologies (HIT) and education | Increased demand for HIT | Increased demand for HIT and education | Dark fiber only; speed will vary depending on last mile provider | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data | N/A | N/A | N/A | Dark fiber only; speed will vary depending on last mile provider | - Dark fiber network. | FALSE | - No variance | - We anticipate continued completion of the pole owners' make-ready surveys as well as additional make-ready completion. We continue to manage the pole licensing process. - Depending on the speed of make-ready completion, we anticipate 49 miles of fiber deployment with a significant portion of these miles also completing construction. - Continue bridge engineering and permitting. - Procurement finalization of the pole gap contractor. - Continue to approve CAI's and deploy fiber for approved CAI's depending on the speed of make-ready completion. - Continue to engineer service provider use of the network and negotiate agreements. | Maine Fiber Company, Inc. | - Third-party make-ready communication was enhanced this quarter through face-to-face meetings, weekly conference calls and daily communication with MFC's project team and the pole owners. The project team gave the pole owners clear and consistent direction on which areas had make-ready priorities. This specific direction allowed the pole owners to tackle make-ready in an efficient manner and resulted in increased cooperation from the pole owners and more efficient make-ready completion. Third-party make-ready continues to make steady progress against baseline milestones, and the pole owners will need to continue this pace of third-party make-ready to make the project schedule. | - Make-ready completion by pole owners is our biggest challenge and may impact the construction schedule; however, continued cooperation from and communication with the pole owners is moving the process along and there hasn't been any negative impact to the construction schedule to date. - The project's contracted fiber vendor is telling MFC that lead times are longer than anticipated due to a worldwide fiber shortage brought on, in part, by the Japanese earthquake and tsunami. According to the vendor, fiber was already in high demand worldwide due to the many BTOP projects in the U.S. along with other large-scale projects around the world. The earthquake and tsunami in Japan damaged a fiber production plant causing it to shutdown completely. Per the vendor, as the major fiber carriers around the world have contracts with multiple fiber production companies, demand has increased again. The project vendor is telling us that it may not be able to deliver the project's fiber as originally planned. At this time, all parties are working together to find the best solution; however, if the fiber isn't delivered on time, it would negatively impact the project schedule. | TRUE
NT10BIX5570139 | 2011 | Q2 | Q2 - 2011 | - We completed construction on an additional 53 miles bringing the total mileage of fiber construction to 79 miles; 4 miles ahead of the project's target baseline. We are on track to achieve our next level of construction mileage for the end of the third quarter. - We achieved just over 46% make-ready completion and have received the same amount in licenses from the pole owners. - We also achieved approval from the Maine State Historical Preservation Office on the archeological footprint for the new pole gaps on the project and are authorized to proceed with installing our new poles. - We awarded the installation and supplying of new poles to the winning vendor; currently completing contract negotiations. - We are on track with make-ready applications for the approved Community Anchor Institutions and are in pre-construction on some of these laterals. We continue to review and approve additional CAI's as they apply to participate on the project. - We received licenses from pole/conduit owners to lease conduit over several bridge crossings. | 79 | 0 | 0 | 0 | 79 | 0 | 0 | 17 | Completed construction on 4 additional miles over the baseline due to early make-ready completion. | No variance; no leases planned - dark fiber | No variance; none planned | No variance; none planned | Completed construction on 4 additional miles over the baseline due to early make-ready completion. | None planned | None planned | Better than expected service provider take-rate/private investment. The positive rate of make-ready completion continues to demonstrate project success to the community and the project is tracking ahead of the baseline. | 6 | 9 | 80 | - Not applicable this quarter | - Dark fiber, prices are listed on the MFC website at www.mainefiberco.com | - N/A; this is a dark fiber network. | 6 | 0 | 6 | 0 | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups | N/A; the baseline showed target numbers for agreements with improved access, but current NTIA guidelines indicate that our agreements reflect new access and are being tracked as such. | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups | Dark fiber only; speed will vary depending on last mile provider equipment. | 13 | 3 | 10 | 0 | Increased demand for healthcare information technologies (HIT) and education | Increased demand for HIT and rural community services | Increased demand for HIT and rural community services | Dark fiber only; speed will vary depending on last mile provider equipment. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data | N/A | N/A | N/A | Dark fiber only; speed will vary depending on last mile provider equipment. | - Dark fiber network. | FALSE | - No variance | - We anticipate continued successful coordination with the third-party pole owners to maintain the fast pace of make-ready completion and receiving additional attachment licenses. - If the fast pace of make-ready completion continues, we anticipate completing an additional 75 miles of fiber deployment with the majority of these miles completing construction keeping the project on track with its baseline estimates. - Continue bridge engineering and permitting. - Finalizing contract negotiations with the new pole installer/vendor and beginning installation of the new poles in the pole gaps. - Continue receiving make-ready completion on the approved CAI laterals as well as approving new CAI applications. - Continue to engineer service provider use of the network and to negotiate agreements. | Maine Fiber Company, Inc. | - Third-party make-ready communication continued successfully among MFC's project team and the pole owners. Third-party make-ready progress is currently in advance of baseline milestones. - MFC received challenging news this quarter from its fiber vendor when the vendor required MFC to limit its monthly orders to a rationed amount of fiber glass production. This rationing could have negatively impacted the project by delaying the ability to move into construction due to unavailable fiber. MFC's project team worked very hard to collaborate with the fiber vendor to reduce negative impacts to the schedule and secured committed delivery dates by agreeing to purchase the fiber in advance. The project team received technical assistance from the BTOP program on the drop-in call regarding fiber procurement and the worldwide shortage that occurred within this quarter; as well as assistance from its FPO during the biweekly conference calls. | - The current pace of make-ready completion by the third-party pole owners needs to continue to obtain the baseline requirements for next quarter. We anticipate this pace continuing. - The project's fiber vendor needs to continue making timely fiber deliveries to make the current schedule. We anticipate the fiber vendor making these deliveries. | TRUE
NT10BIX5570139 | 2011 | Q3 | Q3 - 2011 | - This quarter we anticipated a significant amount of make-ready completion which allowed for better than anticipated construction completion. - The summer months allowed for longer working days and the pole owners utilized their time well in coordination with project's communication regarding make-ready priorities. We achieved 65% make-ready completion and have received the same amount in licenses from the pole owners. In addition, the project and its construction contractor responded quickly and productively to this better than anticipated make-ready completion and achieved more miles of constructed fiber. The project is currently 100 miles ahead of its baseline schedule and anticipates remaining ahead of the baseline. - The new pole vendor has completed the majority of the new pole installation on the project and is on track to complete this scope next quarter on schedule. - We started preparation to cross three bridges through leased conduit this quarter and are tracking to complete these crossings early next quarter. - The project's fiber vendor was able to meet the majority of its fiber delivery dates ensuring no negative impact to the project schedule. | 250 | 0 | 0 | 0 | 250 | 0 | 0 | 25 | Better than anticipated make-ready completion and better than anticipated construction completion allowed the project to pull ahead of its baseline by 100 miles. | No variance; no leases planned - dark fiber. | No variance; none planned. | No variance; none planned. | Completed construction on 100 miles over the baseline. | None planned. | None planned. | Better than expected service provider take-rate/private investment. The positive rate of make-ready completion continues to demonstrate project success to the community and the project is tracking ahead of the baseline. | 6 | 9 | 80 | - Not applicable this quarter. | - Dark fiber; prices are listed on the MFC website at www.mainefiberco.com | - N/A; this is a dark fiber network. | 6 | 0 | 6 | 0 | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups. | N/A; the baseline showed target numbers for agreements with improved access, but current NTIA guidelines indicate that our agreements reflect new access and are being tracked as such. | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups. | Dark fiber only; speed will vary depending on last mile provider equipment. | 22 | 22 | 0 | 0 | The baseline lists 20 CAI's for this quarter, but we have 22 due to increased demand for education and municipalities. Please note that last quarter's PPR listed 13 CAI's completed, but the actual number was 12. We had an increase of 10 CAI's this quarter, all with new access to broadband through the Three Ring Binder. | The baseline lists 0 CAI's with new access for this quarter, but we have 22 as all of these CAI's have new access to broadband through the Three Ring Binder. | The baseline lists 20 CAI's with improved access for this quarter, but we have zero with improved access as all of the CAI's are receiving new access to broadband through the Three Ring Binder. | Dark fiber only; speed will vary depending on last mile provider equipment. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data. | N/A | N/A | N/A | Dark fiber only; speed will vary depending on last mile provider equipment. | - Dark fiber network. | FALSE | - No variance. | - We anticipate continued successful coordination with third-party pole owners to maintain the fast pace of make-ready completion and receiving additional attachment licenses. - If the fast-pace of make-ready completion continues, we anticipate completing an additional 250 miles of fiber deployment keeping the project in advance of its baseline estimates. - We anticipate crossing three bridges and continue bridge engineering and permitting. - We anticipate completing the new pole installation. - We anticipate limited construction on CAI's and continued make-ready applications on CAI's for submittal to pole owners. - Continue to engineer service provider use of the network and to negotiate agreements. | Maine Fiber Company, Inc. | - Third-party make-ready communication continued successfully among the project's team and the pole owners. Third-party make-ready remains in advance of baseline milestones. - The project management team worked closely with its fiber vendor to ensure that the fiber production rationing imposed suddenly on the project last quarter did not have a negative affect to the project's schedule. This collaboration ensured that fiber was delivered to the project in a timely manner and in conjunction with the anticipated construction schedule. The construction schedule pulled in advance of baseline milestones. The BTOP program's drop-in calls focusing on the shortage of fiber in the global market and its subsequent consequences across the BTOP programs was very helpful in understanding the nature of the fiber shortage; its large-scale impact; and various ideas for achieving success within this challenge. | - The current pace of make-ready completion by the third-party pole owners needs to continue to achieve the projected construction completion mileages. The shorter days may slow productivity, but we donâ€™t anticipate any negative impact to the anticipated construction completion mileage. - The projectâ€™s fiber vendor needs to continue making timely fiber deliveries to make the current schedule. We anticipate the fiber vendor making these deliveries through the end of this quarter and into early 2012. We are currently waiting for the fiber vendor to deliver its commitment capabilities from February 2012 and beyond. - Infrastructure Budget Execution Details: To increase the vitality and sustainability of the Three Ring Binder (3RB) project we have purchased software from Telvent. This software will allow the Maine Fiber Company to significantly improve the management of the network and to lease fiber more efficiently in the market place. The cost of the software will cause an overage in the Administrative and Legal section of the itemized budget as indicated in our forecast on line (a) of the Infrastructure Budget Execution Details section of the September 2011 PPR. We are confident that the project overall will remain ahead of schedule and remain under budget through completion. | TRUE
NT10BIX5570139 | 2011 | Q4 | Q4 - 2011 | - This quarter 82% of make-ready completion was accomplished. This faster than anticipated pace of make-ready continued to generate accelerated construction completion. - We constructed and tested over 500 miles of fiber optics on the network. This mileage exceeded our baseline projections by 250 miles. We anticipate gaining additional mileage during the next quarter as long as make-ready completion continues at its current pace. - The new pole vendor completed installation of the new poles this quarter. - We successfully crossed three bridges during this quarter. We are in preparation to cross another three bridges possibly as early as next quarter. - We released an RFP for an equipment procurement for the University of Maine system to use on the network. | 530 | 0 | 0 | 0 | 530 | 0 | 0 | 31 | Better than anticipated make-ready completion and better than anticipated construction completion allowed the project to pull ahead of its baseline by 250 miles. | No variance; no leases planned - dark fiber. | No variance; none planned. | No variance; none planned. | Completed construction on 250 miles over the baseline. | None planned. | None planned. | Better than expected service provider take-rate/private investment. The positive rate of make-ready completion continues to demonstrate project success to the community and the project is tracking ahead of the baseline. | 6 | 9 | 80 | - Not applicable this quarter. | - Dark fiber; prices are listed on the MFC website at www.mainefiberco.com | - N/A; this is a dark fiber network. | 6 | 0 | 6 | 0 | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups. | N/A; the baseline showed target numbers for agreements with improved access, but current NTIA guidelines indicate that our agreements reflect new access and are being tracked as such. | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups. | Dark fiber only; speed will vary depending on last mile provider equipment. | 25 | 25 | 0 | 0 | The baseline projects that 30 CAI's will be connected by the end of this quarter. We were able to construct the fiber for 30 CAI's, but we're only able to physically connect 25 to the network by the end of the quarter as the contractors focused on building the required portion of the network backbone first. In addition, make-ready completion for some of these CAI's took longer than anticipated. We anticipate connecting the remaining 6 CAI's to the network early next quarter as well as making our baseline projections for the next quarter. | The baseline lists 0 CAI's with new access this quarter, but we connected a cumulative total of 25 CAI's with new access. | All of the CAI's connected have received new access. | Dark fiber only; speed will vary depending on last mile provider equipment. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data. | N/A | N/A | N/A | Dark fiber only; speed will vary depending on last mile provider equipment. | - Dark fiber network. | FALSE | - No variance. | - We anticipate continued successful coordination with third-party pole owners to maintain the fast pace of make-ready completion and receiving additional attachment licenses. - If the fast-pace of make-ready completion continues, we anticipate completing an additional 150 miles of fiber deployment keeping the project in advance of its baseline estimates. - We anticipate awarding directional boring and conduit installation on one of the project's bridges and beginning construction on this scope of work. We anticipate installing fiber within leased conduit on one additional bridge. - We will continue to engineer service provider use of the network and to negotiate agreements. - We anticipate awarding an equipment procurement for optical equipment to the University of Maine system to use on the network. - We anticipate continued CAI make-ready and construction completion. - Projected Key Indicators: * New network miles deployed: We anticipate completing an additional 150 miles of fiber deployment by the end of the next quarter. * New network miles leased: We anticipate leasing a total of 100 miles by the end of next quarter. * Total CAI's connected: We anticipate having a cumulative total of 44 CAI's connected to the network by the end of next quarter. * Number of signed agreements with ISP's: We anticipate having a total of seven agreements with ISP's by the end of next quarter. | Maine Fiber Company, Inc. | - Third-party make-ready communication continues successfully among the project's team and the pole owners. Third-party make-ready remains in advance of baseline milestones. - The project management team continues to work closely with its fiber vendor to ensure that the fiber production rationing imposed suddenly on the project earlier in the year did not have a negative affect to the project's schedule. This collaboration ensures that fiber is delivered to the project in a timely manner and in conjunction with the anticipated construction schedule. The construction schedule pulled in advance of baseline milestones. The BTOP program's drop-in calls focusing on the shortage of fiber in the global market and its subsequent consequences across the BTOP programs was very helpful in understanding the nature of the fiber shortage; its large-scale impact; and various ideas for achieving success within this challenge. - Shorter days due to the northern, winter months did impact construction production rates, but the contractor successfully completed 500 miles of constructed and tested fiber even with the shorter days. - The hurricane in the fall did reduce availability of make-ready crews as many pole owners sent crews out of state to assist with recovery. However, the impact to the project was limited to certain pole owners and make-ready completion continued to increase. | - The current pace of make-ready completion by the third-party pole owners needs to continue to achieve the projected construction completion mileages. The possibility of heavy snow may slow productivity, but we donâ€™t anticipate any significant impact to the anticipated construction completion mileage. - The projectâ€™s fiber vendor needs to continue making timely fiber deliveries to make the current schedule. We anticipate the fiber vendor making these deliveries in 2012. | TRUE
NT10BIX5570139 | 2012 | Q1 | Q1 - 2012 | - This quarter 95% of make-ready was completed. This continues our trending of faster than anticipated make-ready completion and is accelerating construction completion. - We constructed over 650 miles to date. This mileage exceeds our targeted projection for this quarter by 400 miles. We anticipate continuing at this accelerated pace next quarter. - We are in the process of crossing another three bridges and will complete these crossings next quarter. - We successfully obtained equipment for the University of Maine to use on the network. - We have connected 32 CAI's to the network to date. | 653 | 0 | 0 | 0 | 653 | 0 | 0 | 72 | Better than anticipated make-ready completion and better than anticipated construction completion allowed the project to pull ahead of its baseline projections by 403 miles. | No variance; no leases planned - dark fiber. | No variance; none planned. | No variance; none planned. | Completed construction on 403 miles over the baseline to date. | None planned. | None planned. | Better than anticipated customer interest in connecting to the network. | 9 | 9 | 80 | - GWI, Axiom Technologies, Pioneer Broadband, University of Maine System, Cornerstone, Town of Scarborough, OTT, Oxford and Mid-Coast | - Dark fiber; prices are listed on the MFC website at www.mainefiberco.com. | - N/A; this is a dark fiber network. | 9 | 0 | 9 | 0 | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups. | N/A; the baseline showed target numbers for agreements with improved access, but current NTIA guidelines indicate that our agreements reflect new access and are being tracked as such. | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups. | Dark fiber only; speed will vary depending on last mile provider equipment. | 32 | 32 | 0 | 0 | The baseline projects that 40 CAI's will be connected by the end of this quarter. We have constructed 43 CAI's to date, but have only connected 32 CAI's to the network by quarter end. The variance is due to coordination requirements with the CAI's that take additional time to schedule. The remaining CAI's will be connected to the network early next quarter. Note that last quarter's PPR total CAI number included non-publicly funded CAI's connected to the network. This quarter's total CAI count includes only grant-funded CAI's. | The baseline lists 0 CAI's with new access this quarter, but we connected a cumulative total of 32 CAI's with new access. | All of the CAI's connected have received new access. | Dark fiber only; speed will vary depending on last mile provider equipment. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data. | N/A | N/A | N/A | Dark fiber only; speed will vary depending on last mile provider equipment. | - Dark fiber network. | FALSE | - No variance. | - We anticipate continued successful completion with third-party pole owners to maintain the fast pace of make-ready completion and receiving additional attachment licenses. - We anticipate completing construction of the remaining miles of the 1,100 mile backbone which is 750 miles ahead of our baseline projections. - We anticipate completing construction on the three remaining bridges. | Maine Fiber Company, Inc. | - Third-party make-ready communication remains challenging, particularly in two segments. However, daily communication and coordination is moving this make-ready forward and isn't impacting our baseline projections. - The project management team remains in close communication with its fiber vendor to ensure timely delivery. This collaboration ensures that the rationing imposed on the project has limited impact to the project schedule. - The winter weather in the northernmost part of the state did slow down productivity rates, but has not impacted the overall construction schedule. | - The remaining make-ready is quite complicated in some areas and we need to maintain the same level of communication and coordination to assist the pole owners to complete this work. - We are working very closely with our contractor to continue this assertive push toward construction completion including working multiple segments at one time. - The project's fiber vendor needs to continue making timely fiber deliveries to make the current schedule. We anticipate the fiber vendor making these deliveries through this upcoming quarter. - We anticipate connecting an additional 16 CAI's by the end of next quarter. - We are negotiating an additional 9 leases for broadband wholesale. We anticipate that 2 leases will sign by June 30, 2012. | TRUE
NT10BIX5570139 | 2012 | Q2 | Q2 - 2012 | - This quarter 99% of make-ready was completed. All make-ready for the backbone route was completed. - We completed construction of the 1,056 mile backbone route, which is 706 miles ahead of baseline projections. - All remaining bridge crossings were completed. - We have connected 49 CAI's to the network to date. | 1071 | 0 | 0 | 0 | 1071 | 0 | 0 | 93 | Better than anticipated make-ready completion and better than anticipated construction completion allowed the project to pull ahead of its baseline projections by 721 miles. | No variance; no leases planned - dark fiber. | No variance; none planned. | No variance; none planned. | Completed construction on 721 miles over the baseline to date. | None planned | None planned | Better than anticipated customer interest in connecting to the network. | 10 | 7 | 80 | - GWI, Axiom Technologies, Pioneer Broadband, University of Maine System, Cornerstone, Town of Scarborough, OTT, Oxford, Mid-Coast, and Seg-Tel | - Dark fiber; prices are listed on the MFC website at www.mainefiberco.com. | - N/A; this is a dark fiber network. | 10 | 0 | 10 | 0 | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups. | N/A; the baseline showed target numbers for agreements with improved access, but current NTIA guidelines indicate that our agreements reflect new access and are being tracked as such. | Better than expected service provider take-rate; results of earlier efforts of carrier outreach resulted in faster than expected sign-ups. | Dark fiber only; speed will vary depending on last mile provider equipment. | 49 | 49 | 0 | 0 | The baseline projects that 50 CAI's will be connected by the end of this quarter. The variance is due to coordination requirements with the CAI's that take additional time to schedule and delays between completion of construction and network testing acceptance. The remaining CAI's will be connected to the network and tested early next quarter. Note that last year's PPR total CAI number included non-publicly funded CAI's connected to the network. This quarter's total CAI count includes only grant-funded CAI's. | The baseline lists 0 CAI's with new access this quarter, but we connected a cumulative total of 49 CAI's with new access. | All of the CAI's connected have received new access. | Dark fiber only; speed will vary depending on last mile provider equipment. | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data. | N/A | N/A | N/A | Dark fiber only; speed will vary depending on last mile provider equipment. | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data. | N/A | N/A | N/A | Dark fiber only; speed will vary depending on last mile provider equipment. | - Dark fiber network. | FALSE | -No variance | - We anticipate 100% completion of network testing by the middle of the next quarter. - We anticipate completing an additional 70 miles of construction by the end of next quarter - We anticipate completing construction on 47 CAI's, which is 36 ahead of baseline projections. - We anticipate signing 4 additional Last Mile/Wholesale agreements by the end of the quarter. - We anticipate completion of the remaining sections connecting the network to New Hampshire and New Brunswick. | Maine Fiber Company, Inc. | - Unavoidable issues with the bridge crossings required the project management team to work very closely with conduit owners and construction crews to push through the final segments. - Testing of remaining segments revealed minor issues that had to be resolved with a round of correctives in the field, requiring close work and planning with the construction contractor. | - The remaining make-ready is quite complicated in some areas and we need to maintain the same level of communication and coordination to assist the pole owners to complete this work. - The project's fiber vendor needs to continue making timely fiber deliveries to make the current schedule. We anticipate the fiber vendor making these deliveries through this upcoming quarter. | TRUE
NT10BIX5570139 | 2012 | Q3 | Q3 - 2012 | Past progress and achievements to get us ahead of schedule and Baseline projections continue to allow for favorable reporting. Steady progress continued this quarter. -All testing of the 1,056 mile backbone was completed, as were all necessary correctives. -Construction on the approved route extension (Biddeford to Dover) was completed, and only testing remains. -An additional 39 CAI's were connected, for a total of 88 out of 100 approved CAIs now complete. -Increased focus on regeneration shelters including placement and leasing of first shelter in Sherman, ME complete. | 1143 | 0 | 0 | 0 | 1143 | 0 | 0 | 144 | Progress on CAIs and the approved extension resulted in additional mileage above the 1,100 mile baseline projection for the project. | No variance; no leases planned - dark fiber. | No variance; none planned. | No variance; none planned. | Completed 643 miles over the baseline projection for Q3 2012. | No variance; none planned. | No variance; none planned. | Continued Success with Customer Sign-ups and Connections | 14 | 6 | 80 | - GWI, Axiom Technologies, Pioneer Broadband, University of Maine System, Cornerstone, Town of Scarborough, OTT, Oxford, segTEL, Southern Maine Community College, Town of Greenwood, BayRing, unnamed party (under NDA) and TDS Telecom. Mid-Coast, a CLEC previously reported as a signed agreement has merged with another client. As the Agreement has been assigned, we are counting the 2 previous agreements as 1 moving forward. | - Dark fiber; prices are listed on the MFC website at www.mainefiberco.com. | - N/A; this is a dark fiber network. | 14 | 0 | 14 | 0 | Success from focused leasing/sales efforts allows us to continue to outperform Baseline projections. | N/A; the baseline showed target numbers for agreements with improved access, but current NTIA guidelines indicate that our agreements reflect new access and are being tracked as such. | All access is dark fiber. | Dark fiber only; speed will vary depending on last mile provider equipment. | 88 | 88 | 0 | 0 | Previous construction progress ahead of schedule allowed for focus on CAI construction this quarter. We are now ahead of Baseline projections. | The baseline lists 0 CAI's with new access this quarter, but we connected a cumulative total of 88 CAI's with new access. | All of the CAI's connected have received new access. | Dark fiber only; speed will vary depending on last mile provider equipment. | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data. | N/A | N/A | N/A | Dark fiber only; speed will vary depending on last mile provider equipment. | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data. | N/A | N/A | N/A | Dark fiber only; speed will vary depending on last mile provider equipment. | - Dark fiber network. | FALSE |  | The focus of the efforts will be on completing the remaining CAIs to get us to 100 complete by the end of Q4 2012, as well as finishing any testing that remains outstanding, such as the Extension route. In addition, an increase in efforts on the regeneration shelters will occur this quarter with a focus on procurement activities including various RFPs. There is also be a continued efforts on leasing/sales and customer interconnection. Other key metrics include: -Deployment of 7 additional miles bringing to total deployed to 1,150 (which is also the total for the project inclusive of the backbone, the Biddeford extension, and the CAIs). -An additional 12 CAI's connected, for a total of 100 out of 100 approved CAIs completed. -2 additional broadband wholesaler/last mile provider agreements being executed bringing the total to 16. | Maine Fiber Company, Inc. | No issues or challenges to report. | There are no issues or challenges that should impact testing and CAI completion over the course of the quarter. With regards to the increased focus on regeneration shelter construction, winter weather could begin to be a factor. | TRUE
NT10BIX5570139 | 2012 | Q4 | Q4 - 2012 | Past, ahead of schedule, progress continues to keep us ahead of Baseline projections and allow for favorable reporting. Steady progress continued this quarter. -All work on the backbone has been completed. -Testing of the approved route extension (Biddeford to Dover) was completed. -An additional 8 CAI's were connected, for a total of 96 out of 100 approved CAIs now complete. -RFPs complete and site preparation work on regeneration shelters significantly underway. | 1148 | 0 | 0 | 0 | 1148 | 0 | 0 | 225 | Progress on CAIs and completion of the approved extension resulted in additional mileage above the 1,100 mile baseline projection for the project. | No variance; no leases planned - dark fiber. | No variance; none planned. | No variance; none planned. | 498 miles over the baseline projection for Q4 2012. See note with 'New network miles deployed' above | No variance; none planned. | No variance; none planned. | Significant focus on customer sales and connection to the network | 16 | 8 | 80 | GWI, Axiom Technologies, Pioneer Broadband, University of Maine System, Cornerstone, Town of Scarborough, OTT, Oxford, segTEL, Southern Maine Community College, Town of Greenwood, BayRing, TDS Telecom, Unity Telephone and two unnamed parties (under NDA). | Dark fiber; prices are listed on the MFC website at www.mainefiberco.com. | N/A; this is a dark fiber network. | 0 | 0 | 16 | 0 | All access is dark fiber. | N/A; the baseline showed target numbers for agreements with improved access, but current NTIA guidelines indicate that our agreements reflect new access and are being tracked as such. | All access is dark fiber. | Dark fiber only; speed will vary depending on last mile provider equipment. | 96 | 96 | 0 | 0 | Previous construction progress allowed for focus on CAI construction this quarter. We are now ahead of Baseline projections. | The baseline lists 0 CAI's with new access this quarter, but we connected a cumulative total of 96 CAI's with new access. | All of the CAI's connected have received new access. | Dark fiber only; speed will vary depending on last mile provider equipment. | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data. | N/A | N/A | N/A | Dark fiber only; speed will vary depending on last mile provider equipment. | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data. | N/A | N/A | N/A | Dark fiber only; speed will vary depending on last mile provider equipment. | Dark fiber network. | FALSE |  | The focus for Q1 2013 will be to complete and test the 4 remaining CAIs to get us to 100 complete by the end of the quarter. In addition, we will continue with site preparation for the regeneration shelters with a goal of placing 3 completed structures by the end of the quarter. We will also also be a continued efforts on leasing/sales and customer interconnection. Other key metrics include: -Deployment of 1 additional mile (represents the 4 additional CAIs) bringing to total deployed to 1,149. -An additional 4 CAI's connected, for a total of 100 out of 100 approved CAIs completed. -2 additional broadband wholesaler/last mile provider agreements being executed bringing the total to 18. | Maine Fiber Company, Inc. | Tight scheduling in December with our subcontractor caused us to delay that last 4 CAI connections we had projected to finish in Q4 2012. All other aspects of the project remain on track or ahead of schedule. | There are no issues or challenges that should impact the completion of the 4 additional CAIs this quarter. Winter weather and aggressive internal time lines could impact the rate of construction of the regeneration shelters, however, risk of any overall impact is not a concern. | TRUE
NT10BIX5570139 | 2013 | Q1 | Q1 - 2013 | Ahead of Baseline progress continued in Q1 2013 and allows for favorable reporting. Steady progress on the few remaining items continued this quarter. -An additional 4 CAI's were connected, with all 100 of 100 approved CAIs now complete. -All RFPs are complete for the regeneration shelters. There was significant progress on site preparation work and 5 additional shelters were landed at their locations during Q1. -All work on the backbone remains completed. -All testing of the backbone, approved route extension and CAIs is now complete. -An IRU AAR for the use of Grant savings on other route/capacity was submitted and approved in Q1. NOTE: On the Budget Details Chart below, the amount shown for line K-Misc (Total, Match & Fed) was reduced in Q1 2013 from pervious quarters by $200 ($40 match & $160 fed) due to a reclassification of cost from line K-Misc to line J â€“ Equipment, which is where it was supposed to be recorded originally. | 1149 | 0 | 0 | 0 | 1149 | 0 | 0 | 234 | Progress on CAIs and completion of the approved extension resulted in additional mileage above the 1,100 mile baseline projection for the project | No variance; none planned | No variance; none planned | No variance this quarter, however the approved IRU AAR will cause this number to increase in the coming quarter. The total mileage leased under the IRUs will be 61. | 399 miles over the baseline projection for Q1 2013. See note with 'New network miles deployed' above | No variance; none planned | No variance; none planned | Significant focus on customer sales and connection to the network have increased number of interconnections | 17 | 6 | 80 | [REDACTED] | Dark fiber; prices are listed on the MFC website at www.mainefiberco.com. | N/A; this is a dark fiber network. | 0 | 0 | 17 | 0 | All access is dark fiber | N/A; the baseline showed target numbers for agreements with improved access, but current NTIA guidelines indicate that our agreements reflect new access and are being tracked as such | All access is dark fiber | Dark fiber only; speed will vary depending on last mile provider equipment | 100 | 100 | 0 | 0 | All approved CAIs are now complete | The baseline lists 0 CAI's with new access this quarter, but we connected a cumulative total of 100 CAI's with new access. | All of the CAI's connected have received new access | Dark fiber only; speed will vary depending on last mile provider equipment | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data | n/a | n/a | n/a | Dark fiber only; speed will vary depending on last mile provider equipment | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data | n/a | n/a | n/a | Dark fiber only; speed will vary depending on last mile provider equipment | Dark fiber network. | FALSE | n/a | Completion of the regeneration shelters will occur in Q2 2013. In addition, we plan to finalize the IRU deals that were approved in Q1 2013. Most other items have been completed to date. | Maine Fiber Company, Inc. | There were no significant challenges or issues that occurred in Q1 that caused any material impacts to planned progress. | Legal and compliance review for the IRUs will need to be completed by the applicable parties before the Agreements are signed and the deals are complete. Legal review and negotiation often take longer than anticipated and may cause delays during Q2. There is very little chance anything will delay the completion of the regeneration shelters during Q2. | TRUE
NT10BIX5570139 | 2013 | Q2 | Q2 - 2013 | Ahead of Baseline progress continued in Q2 2013 and allows for favorable reporting this quarter. Steady progress on the few remaining items continued this quarter. -All 7 regeneration shelters are substantially complete -Both approved IRU Agreements were executed -One additional customer Agreement was signed for a total of 18 to date In addition; -All 100 of 100 approved CAIs remain complete. -All work on the backbone remains completed. -All testing of the backbone, approved route extension and CAIs remains complete. | 1149 | 0 | 0 | 61 | 1149 | 0 | 0 | 251 | Progress on CAIs and completion of the approved extension resulted in additional mileage above the 1,100 mile baseline projection for the project | No variance; none planned | No variance; none planned | Both approved IRU Agreements were executed in Q2 2013 | See note with 'New network miles deployed' above | No variance; none planned | No variance; none planned | Significant focus on customer sales and connection to the network have increased number of interconnections | 18 | 7 | 80 | [REDACTED] | Dark fiber; prices are listed on the MFC website at www.mainefiberco.com. | N/A; this is a dark fiber network. | 0 | 0 | 18 | 0 | N/A; this is a dark fiber network. | N/A; the baseline showed target numbers for agreements with improved access, but current NTIA guidelines indicate that our agreements reflect new access and are being tracked as such | All access is dark fiber | Dark fiber only; speed will vary depending on last mile provider equipment | 100 | 100 | 0 | 0 | All approved CAIs are now complete | The baseline lists 0 CAI's with new access this quarter, but we connected a cumulative total of 100 CAI's with new access. | All of the CAI's connected have received new access | Dark fiber only; speed will vary depending on last mile provider equipment | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data | n/a | n/a | n/a | Dark fiber only; speed will vary depending on last mile provider equipment | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data | n/a | n/a | n/a | Dark fiber only; speed will vary depending on last mile provider equipment | Dark Fiber Netowrk | FALSE | n/a | We have submitted an AAR to amend our 424c to adjust and move money between line items. This was approved in early July. We have one last AAR under review for use of budget savings on an additional IRU Agreement. Completion of any remaining punch list items, receipt of final pole attachment billings for the project and a focus on preparing for closeout activities will also occur in Q3 2013. | Maine Fiber Company, Inc. | There were no significant challenges or issues that occurred in Q2 that caused any material impacts to planned progress. | There are no significant challenges or issues that should cause any material impacts to planned progress for Q3. If the additional IRU AAR is approved, we have a letter of intent signed, and the Agreement should be quick to execute. All other items are low risk. | TRUE
NT10BIX5570139 | 2013 | Q3 | Q3 - 2013 | The Award End Date for MFC occurred on August 31, 2013. During the 3-year project period, MFC was able to exceed the original goals and objectives of the project including: -MFC constructed 1,149 new network miles. This was 149 miles more than projected in the Baseline report and included mileage to extend the network from Biddeford, ME to South Berwick, NH with budget savings. This network extension helps enables out of state providers to enter Maine and provide services. It also allows in-state providers easier and more affordable access to other BTOP projects. -MFC was able to substantially complete the 3RB backbone build by June 30, 2012, well ahead of schedule. -MFCâ€™s average cost per new mile was $23,048 vs. the $28,867 projected in the Baseline report. This was due, in part, to competitive pricing from RFPs for subcontractors and materials as well as favorable Make Ready costs due to rigorous oversight and good working relationships with pole owners. -MFC purchased an IRU of strands of fiber (3 additional New Network Miles Leased from the Baseline report). This IRU provides fiber access into 37 Central Offices in Maine. By purchasing an IRU on these miles MFC was able to forgo overbuilding existing fiber. -MFC was able to purchase an IRU for strands of fiber (59 additional New Network Miles Leased from the Baseline report) from the NH/MA border into Boston with budget savings. With Boston being the closest internet point of presence to Maine, and the least expensive place to buy internet backhaul in New England, this IRU provides customers with a dark fiber option for internet connectivity to Boston from Maine and will allow new service providers with an easy, scalable and affordable way to bring their services into Maine with seamless access to the 3RB network and all of the rural communities it connects. -MFC connected 100 CAIs as part of the project (the exact number called for in the project Baseline report) and MFC completed these connections 2 Quarters ahead of schedule. The CAIs are comprised of 39 Schools (K-12), 6 Libraries, 5 Medial and Healthcare Providers, 5 Public Safety Entities, 10 Community Colleges, 10 Other Institutions of Higher Education, 5 Other Community Support Organizations, and 20 Other Government Facilities. -MFC has signed dark fiber lease agreements with 19 network users, 6 more than expected in the Baseline report. These customers include educational institutions, municipalities, ILECs, CLECs, wireless backhaul providers and others. -MFC constructed seven 10â€™x20â€™ regeneration shelters around the state of Maine helping to provide service providers with high quality, easy points of access to the 3RB network for their optronic equipment. These shelters are also available on an open access/non-discriminatory basis. In addition to signal regeneration, they provide additional locations to interconnect with the network and head-end last mile and wireless distribution networks. -MFC has provided 271 interconnection points to date on the 3RB, greatly exceeding the Baseline projection of 70. These points include 7 MFC owned regeneration facilities, 39 Central Offices in Maine, and over 200 connection points aerially at utility poles around the state of Maine. In addition, at an average distance of roughly every 2,100â€™ (and rarely exceeding 2,500â€™), MFC has roughly 2,400 splice/slack locations for future interconnections around the state when customer demand dictates. In summary, the network is being well used and is sustainable. Telecom carriers around Maine are using MFCâ€™s BTOP funded middle-mile fiber to get into rural communities, and build last mile fiber and DSL to the home and to businesses. | 1149 | 62 | 0 | 0 | 1149 | 0 | 0 | 271 | Completion of CAIs and of the approved extension resulted in additional mileage above the 1,100 mile baseline projection for the project | Execution of an approved Amendment to an IRU Agreement executed in Q2 added 1 mile in Q3 | No variance; none planned | No variance; none planned. However, 61 was reported in Q2 which should have been classified as "New network miles leased" | See note with 'New network miles deployed' above | No variance; none planned | No variance; none planned | Focus on customer sales and connection to the network have increased actual number of interconnections above baseline | 19 | 5 | 80 | [REDACTED] | Dark fiber; prices are listed on the MFC website at www.mainefiberco.com. | N/A; this is a dark fiber network. | 0 | 0 | 19 | 0 | N/A; this is a dark fiber network. | N/A; the baseline showed target numbers for agreements with improved access, but current NTIA guidelines indicate that our agreements reflect new access and are being tracked as such | All access is dark fiber | Dark fiber only; speed will vary depending on last mile provider equipment | 100 | 100 | 0 | 0 | All approved CAIs are now complete | The baseline lists 0 CAI's with new access this quarter, but we connected a cumulative total of 100 CAI's with new access. | All of the CAI's connected have received new access | Dark fiber only; speed will vary depending on last mile provider equipment | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data | n/a | n/a | n/a | Dark fiber only; speed will vary depending on last mile provider equipment | 0 | 0 | 0 | 0 | 0 | MFC is not collecting this data | n/a | n/a | n/a | Dark fiber only; speed will vary depending on last mile provider equipment | Dark Fiber Netowrk | FALSE | n/a | The project focus in will be to finalize Grant Closeout and focus on the final A-133 audit. | Maine Fiber Company, Inc. | There were no significant challenges or issues that occurred in Q3 that caused any material impacts to planned progress. | There are no significant challenges or issues that should cause any material impacts to planned progress for Q4. | TRUE
NT10BIX5570140 | 2010 | Q4 | Q4 - 2010 | Most milestones for Year 1 Q2 were reached. Much progress has been made on completing the complex network design and in completing the Environmental Assessment (EA) in order for construction to begin. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | per baseline | n/a | per baseline | n/a | per baseline | n/a | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | per baseline. | per baseline | per baseline | per baseline | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | Plans for the next quarter include the completion of the EA which would allow the project to begin construction on the fiber buildout, purchase of equipment and the start of installation and deployment of equipment at sites that require no ground disturbance. Site preparation will be completed with complete documentation of all sites. | University of Hawaii Systems | Due to the administrative leave during the holidays, the University system was shutdown and that contributed to the delays in ordering equipment for the project. We expect to continue to work on catching up to the baseline over the next quarter or two, including completion of the EA, equipment procurement and deployment and network building and testing.. | The completion of the EA is the key factor in adhering to the baseline schedule. Without the accepted EA and FONSI, fiber buildout cannot occur and the project will be delayed. We fully expect the EA to be completed and the FONSI issued on time. | TRUE
NT10BIX5570140 | 2011 | Q1 | Q1 - 2011 | The Network Design, Site Preparation and Equipment Procurement milestones have all been met during this quarter. Documentation of all sites was completed. The Environmental Assessment (EA) projected to be completed this quarter has still not been approved so this has caused delays in meeting the other milestones related to the network build, deployment, and testing as well as delaying completion of the overall project. Since no construction work can be contracted before EA approval, the projected Federal and matching expenditures for these construction-related milestones have also been delayed. In anticipation of receiving a Finding of No Significant Impact (FONSI) soon, we are preparing draft agreements with vendors to construct fiber connections, hoping these agreements can be finalized soon after the FONSI is received so that the project's progress will soon match the Baseline projections. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | As the FONSI has not yet been issued, the construction of the network has not begun and no new network miles have been deployed. | n/a | As the FONSI has not yet been issued, no construction can occur and the network cannot be upgraded. Equipment purchases are still being received and sites cannot be upgraded until components have been received and inventoried. | n/a | As the FONSI has not yet been issued, the construction of the network has not begun and no new network miles have been deployed. | n/a | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | No CAIs have been provided upgraded access yet. This is lower than the baseline number as fiber to new sites has not been constructed since the FONSI has not yet been issued and the baseline includes CAIs that already have access. | This is lower than the baseline number as fiber to new sites have not been constructed due to the FONSI that has not yet been issued. | This is lower than the baseline number as fiber to new sites have not been constructed due to the FONSI that has not yet been issued. | per baseline | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | na/ | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | We anticipate receiving a Finding of No Significant Impact (FONSI), which will allow construction to proceed. Additionally, we project deployment of equipment to sites which will involve no ground disturbance. Depending on when during the quarter the FONSI is issued, the vendor agreements for network build should be fully executed and actual construction may also be able to begin during the next quarter, bringing us closer to meeting the Baseline projections. Once construction begins, we expect to have access to matching funds which we included in the milestones calculations and job creation figures can then be reported. | University of Hawaii Systems | Not all milestones projected on the baseline for Year 1 Quarter 3 were reached. Much of this delay is due to the delay in equipment delivery as well as the EA requirement. The equipment as budged in the 6 month budget has been purchased and the project is awaiting the delivery of the equipment. Many of the parts have been received, but significant portions are still in transit. Completed delivery is expected by the end of April 2011, at which point Equipment deployment can begin and the project can start to catch up on the progress. Around the same time, the project expects the FONSI to be issued by the completion of the EA. Currently the EA is being reviewed and the project is working with the reviewer to respond to the comments in a timely manner. | The completion of the EA is the key factor in adhering to the baseline schedule. Without the accepted EA and FONSI, fiber buildout cannot occur and the project will be delayed. We fully expect the EA to be completed and the FONSI during the next quarter. | TRUE
NT10BIX5570140 | 2011 | Q2 | Q2 - 2011 | The Environmental Assessment was completed and a Finding of no Significant Impact (FONSI) was issued at the end of this quarter. The first round of equipment has been completely received and deployment is in process at sites. Some sites that have existing fiber connectivity have been upgraded with new network equipment and the fiber links were upgraded or prepared to support the addition of other sites along the path. Two CAI's (High Schools) were brought online during this quarter. These sites had existing fiber that was unlit. Their network capacity was increased from 6Mbps to 1Gbps. A major agreement with Wavecom Solutions to design and construct 10G wavelength connections from UH Manoa to Moloka'i and Lana'i was fully executed during this quarter and negotiations were nearly completed with Oceanic Time Warner. | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | Since the FONSI was received at the end of the quarter, construction has not started. | n/a | Estimated mileage. This represents the approximate miles that have been upgraded to 10Gbps or have been added to the network (fiber was already run to the site, but not lit) and connected at 1Gbps. This is below the baseline as the equipment deployment and staffing delays have delayed the upgrades of sites. | n/a | FONSI was received at the end of the Quarter. Construction has not started. | n/a | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 13 | 2 | 11 | 2 | 13 CAIs have been given upgraded access or new access. The number is below the baseline as no new construction has been done due to the delay in receiving the FONSI. | 2 CAIs have been given new access. This was done by existing fiber that was previously run into the sites but not yet activated.The number is below the baseline as no new construction has been done due to the delay in receiving the FONSI. | 11 CAIs have had their access speeds upgraded and/or new equipment installed to increase their capacity. The number is below the baseline as the deployment of new equipment to the sites was delayed by equipment delivery and installation delays. | There are two speed tiers - 10Gbps and 1Gbps. 2 sites have received upgraded circuits at 10Gbps, All other sites (90) are at 1Gbps, including the two sites that received new access. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none | FALSE | n/a | We expect that the contract with Oceanic will be fully executed so construction can commence next quarter. Site upgrades to Community Anchor Institutions that are already on the network and site installations to CAIs that already have fiber but are not on the network will continue as they have during this past quarter. Equipment deployment will continue throughout the state. Once construction begins, we will begin to expend matching funds more actively. In addition, job creation figures should increase. We expect that a number of sites will have their construction completed by the end of the next quarter. | University of Hawaii Systems | The delay in receiving the FONSI has delayed all construction-related milestones such as network build, deployment, and network testing and overall project completion by at least a quarter and thus most baseline milestones have been missed. Equipment on the initial order was slightly delayed in delivery due to manufacturing issues but was completely received during this quarter. This has delayed the deployment of the equipment at the sites. Staff changes at a partner institution, Department of Education (DOE), have also delayed the project slightly. The University is working with the DOE to bring their current team up to speed on the project and the timeline. | Construction delays and equipment deployment delays caused by delayed issuance of the FONSI are causing the project to miss the baseline milestones. We expect to catch up to the baseline by the end of Year 2. The project is looking at ways to streamline equipment deployment among the project partners to increase efficiencies and speed the equipment deployment to sites. Additionally, we are working with Oceanic to streamline the construction and deployment plan. | TRUE
NT10BIX5570140 | 2011 | Q3 | Q3 - 2011 | Construction contract with Oceanic Time Warner Cable has been fully executed and construction activities have begun. Engineering and joint pole applications for CAI locations are being done and submitted. We expect to average approximately 24 joint pole applications per month. As joint pole applications are approved for sites, fiber construction will commence for approved sites. The first two interisland 10G wavelengths to Molokai and Lanai were completed this quarter. A CAI on Molokai received upgraded access on the new interisland 10G circuit. Four CAIs that had existing fiber was brought online and a number of sites received upgraded access. Equipment deployment to sites continue, as does activation of sites that already have fiber installed. Distance learning equipment has been fully deployed and is in full production at University of Hawaii sites. | 3 | 0 | 159 | 0 | 3 | 0 | 0 | 0 | Construction just started this quarter after receipt of the FONSI at the end of last quarter so completion total is much lower than the Baseline. Two new backbone miles and a total of 1 mile of lateral fiber have been activated. | n/a | 159 miles of backbone fiber have been upgraded with new capacity. This is less than the Baseline as equipment deployment and staffing delays have delayed site upgrades. | n/a | Total of 3 new miles (including backbone and lateral) have been activated. This is far less than the Baseline since construction just started this quarter but is expected to significantly increase in the following quarters. | n/a | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 23 | 6 | 17 | 2 | A total of 23 CAIs have been given upgraded access or new access to date. That is well below the Baseline since construction was just recently started due to the late receipt of the FONSI. | 4 CAIs were given new access this quarter for a total of 6. This is less than the Baseline since construction was just recently started due to the late receipt of the FONSI. | 6 CAIs were given improved access this quarter for a total of 17. This is less than the Baseline because deployment of new equipment to the sites was delayed by equipment delivery and installation delays. | There are two speed tiers - 10Gbps and 1Gbps. 2 sites have received upgraded circuits at 10Gbps, All other sites (90) are at 1Gbps, including the two sites that received new access. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none | FALSE | n/a | Activation of the 10Gbps interisland circuit to Lanai should be completed in the next quarter. Other interisland links should also be activated during the next quarter. Oceanic expects to be able to start pulling fiber to the CAIs starting in the next quarter and the corresponding sites will be added to the fiber network. We also expect to complete the procurement of the remaining equipment (DWDM, UPS and CPE) and begin installation of the equipment on the neighbor islands. Project should see significant progress in completion percentages over the next quarter with a corresponding increase in matching funds as construction progresses. Projected Forecasts New Network Miles: 48 New backbone and lateral miles Total CAIs connected: 51 CAIs Improved, 38 CAIs New Access | University of Hawaii Systems | The Oceanic Time Warner construction contract for fiber connections to six Hawaiian islands was fully executed this quarter and the process of fiber deployment has finally begun. Equipment deployment is moving slowly at the DOE and HSPLS sites due to staffing and other projects in progress. UH sites however have been completely upgraded and almost all sites are finished. UH staff will be assisting the DOE and HSPLS staff install equipment and prepare the sites for fiber installs. The DOE and HSPLS have also committed to concentrate on the BTOP project going forward. | The EA and FONSI delay is still impacting the progress of the project. We are working towards catching up with the baseline as much as possible. We will continue to look for ways to steamline equipment deployment among the project partners such as the Libraries and Oceanic and increase efficiencies to speed up deployment to the sites. We expect that additional assistance we are giving to the Libraries to install their equipment will help us to meet the milestone in future quarters. | TRUE
NT10BIX5570140 | 2011 | Q4 | Q4 - 2011 | Construction for the project is in full swing. Engineering and joint pole applications are proceeding on four islands. Fiber has been pulled to 18 sites, but those sites, due to the location in the network topology have not yet been activated with improved services. Work on lighting those sites will continue the next quarter. An interisland circuit from the Big Island to Oahu was activated at the end of the quarter, as well as the the activation of a key hub site on the Big Island. Additional sites that already had existing fiber were activated and other sites within the network were upgraded. Equipment deployment has increased significantly. | 13 | 0 | 253 | 0 | 13 | 0 | 0 | 0 | Additional miles were built to 18 sites, but are not counted as they have not been activated due to network engineering limitations. The amount of new miles are lower than the baseline due to the delays in the start of construction. The number of miles will continue to be below baseline for the next few quarters as the project catches up. | n/a | 94 miles of fiber were upgraded this quarter - bringing the total to 253 miles. This is significant progress, although still under the baseline amount due to the previous quarter delays in construction. | n/a | 10 new miles were activated bringing to the total to 13 miles. Additional miles were built to 18 sites, but are not counted as they have not been activated. This is far less than the baseline since construction only recently began in earnest due to the previous quarters' delays and unexpected factors (Hawaiian Tel strike, APEC, holiday blackouts). | n/a | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 38 | 14 | 24 | 2 | 15 CAIs were given new or improved access this quarter. This is well below the baseline due to the delays from the previous quarters from the late receipt of the FONSI. | 8 CAIs were given new access this quarter for a total of 14. This is less than the Baseline due to the delayed start in construction due to the late receipt of the FONSI. | 7 CAIs were given improved access this quarter for a total of 24. This is less than the baseline as deployment of new equipment was delayed by equipment delivery and construction delays over the holidays. | There are two speed tiers - 10Gbps and 1Gbps. 2 of the new sites are at 10Gbps and 3 improved sites are at 10Gbps. All other sites including the 6 new and 4 improved are at 1Gbps (total of 102 sites). | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | none | FALSE | n/a | All interisland circuits should be completed and activated during the next quarter. Significant progress is expected in fiber builds and site activations. Regrooming efforts on Oahu are expected to get started next quarter and sites across the existing network will be upgraded. Projected Forecasts New Network Miles: 60 New backbone and lateral miles Total CAIs connected: 20 CAIs improved, 40 CAIs New Access | University of Hawaii Systems | Coordination issues with the DOE, HSPLS, UH and Oceanic Time Warner Cable and its contractors for site surveys initially delayed the joint pole application progress. This has been resolved and routine conference calls between all the parties have significantly improved coordination and communication and have sped up the construction process. This has resulted in more apps being submitted on a monthly basis. At the end of December 12 apps were approved, which will be built during the next quarter.The number of approved apps did not track projections this past quarter and the project network miles and CAIs connected and upgraded was significantly lower due to factors such as the Hawaiian Tel strike in November, the network maintenance freeze during the APEC Conference on Oahu in November, an Oceanic Time Warner Cable blackout for fiber trunk work due to a City & County of Honolulu prohibition on road closures between Thanksgiving and New Year. These external factors are cleared as of the next quarter (1Q2012), and the road closure prohibition will be factored into end-of-2012 planning. That said, work over the last quarter with the DOE and HSPLS has proved to be successful as the deployment rate has increased and is starting to track closer to the baseline. No assistance from the BTOP program is requested or required at this time. | Previous quarters' delays continue to impact the reported progress of the project. As construction progresses, the project will track closer to the projected baseline. Project completion percentages include fully completed sites as well as sites that have just fiber installed, but are not connected to the network yet. Approved pole-use applications for fiber builds are coming in batches (12 in the last week of December) and Oceanic is now building out mileage as quickly as they can once approvals are received. Fiber builds are expected to increase, but network build rates will not necessarily track the fiber builds. Oceanic builds out fiber as the approved pole-use applications are approved - but these new sites cannot necessarily be connected to the network until key intermediate sites have also been built and activated. This sometimes results in sites that have fiber built but connectivity cannot be activitated until intermediate sites are connected and activated in a future quarter. This will be reflected in the overall project completion percentage, but not the network build nor CAI list. Equipment deployment will continue on all islands. Work over the last quarter with the DOE and HSPLS has proved to be successful as the deployment rate has increased and is starting to track closer to the baseline. No assistance from the BTOP program is requested or required at this time. | TRUE
NT10BIX5570140 | 2012 | Q1 | Q1 - 2012 | Construction continues for the project. Engineering and joint pole applications are proceeding and have been tracking expected turn around times. 79 joint pole applications have been submitted and 55 have been approved by the end of this quarter. Fiber has been pulled to 27 new sites. Those sites have not yet been connected to the optical network due to the layout of the network topology. All interisland circuits have been completed and are in service. Additional sites that had existing fiber have been activated. The Ke Ala 'Ike BTOP CCI project was funded solely for network implementation so does not include project-specific community outreach efforts. These outreach efforts are included in a separate companion BTOP PCC project, Access for All, which is placing well over 600 new public computers in over 60 of our Ke Ala 'Ike sites (community college and public libraries) on 6 islands. 24 jobs were created as part of Oceanic's construction activities this quarter. Major expenditures were $3.3M for network equipment, UPSes and DWDM equipment. | 13 | 0 | 284 | 0 | 13 | 0 | 0 | 0 | Additional miles were built to 27 sites but are not counted as they have not yet been activated. No change from last quarter for lateral miles as all sites installed are on the backbone and do not have any lateral miles. The number of miles will remain below the baseline for the next few quarters as the project catches up from earlier delays in construction startup. | n/a | 31 miles of backbone fiber were upgraded this quarter for a total of 284 miles upgraded. This number is still below baseline due to previous quarters' construction delays. | n/a | Additional miles were built to 27 sites but are not counted as they have not yet been activated. This is below the baseline due to the previous quarters' delays. | n/a | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 49 | 18 | 31 | 2 | 11 CAIs were given new or improved access this quarter. This is well below the baseline due to delays from the previous quarters from the late receipt of the FONSI. Project timelines have been adversely affected by the additional time it took to process the FONSI approvals. Project participants have been working on improving production rates over the last quarter. Based on projected build rates, the project is estimating that it should reach baseline numbers towards the later quarters of Year 3 | 4 CAIs were given new access this quarter for a cumulative total of 18. This is less than the baseline due to the delayed start of construction as well as the network topology limitations.Project timelines have been adversely affected by the additional time it took to process the FONSI approvals. Project participants have been working on improving production rates over the last quarter. Based on projected build rates, the project is estimating that it should reach baseline numbers towards the later quarters of Year 3 | 7 CAIs were given improved access this quarter for a cumulative total of 31. This is less than the baseline due to the delayed start of construction as well as the limitations of the network topology. Project timelines have been adversely affected by the additional time it took to process the FONSI approvals. Project participants have been working on improving production rates over the last quarter. Based on projected build rates, the project is estimating that it should reach baseline numbers towards the later quarters of Year 3 | There are two speed tiers - 10Gbps and 1Gbps. 1 of the new sites are at 10Gbps and 2 improved sites are at 10Gbps. All others were at 1Gbps. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | Newly built sites are scheduled to be added to the network so that optical paths can be built. We should be able to add a significant number of new sites to the network. Projected Forecasts: New Network Miles: 62 New backbone and lateral miles Total CAIs Connected: 15 CAIs improved, 32 CAIs new access | University of Hawaii Systems | Previous quarter's coordination issues between all parties have been worked out and the weekly construction calls are occurring. These communications paths have streamlined the process of surveys, approvals and actual construction so that multiple sites are able to be built in a week. During this quarter 27 sites were built. At the end this quarter the DOE staff member who was in charge of the network deployment side of the BTOP project left and his roles and responsibilities have been assigned to others within the DOE. While the project does not expect significant delays due to this personnel change, there may be short term impacts. No assistance from the BTOP program is requested or required at this time. | Previous quarters' delays continue to impact the reported progress of the project. As construction progresses, the project will track closer to the projected baseline. Project completion percentages include fully completed sites as well as sites that have just fiber installed, but are not connected to the network yet. Approved pole use applications are coming in at a steady rate. Construction is averaging 4 - 5 sites per week for Oahu. Construction will start on the neighbor islands this quarter. Network activations should increase as the key hub sites around the ring are built and spliced in. Equipment deployment continues on all islands. Regular coordination and planning meetings with DOE, HSPLS, UH and Oceanic has proven to be successful over the last two quarters and will continue to occur to streamline the construction and site activation across the network. No assistance from the BTOP program is requested or required at this time. | TRUE
NT10BIX5570140 | 2012 | Q2 | Q2 - 2012 | Construction and site activation continues for the project. Engineering and joint pole applications are proceeding and have been tracking expected turn around times. 112 joint pole applications have been submitted and 80 have been approved by the end of this quarter. Fiber has been pulled to a total of 50 new sites. Most of those sites have not yet been connected to the optical network due to the layout of the network topology and the pending completion of the splicing, termination and testing. All interisland circuits have been completed and are in service. Additional sites that had existing fiber have been activated. Upgrades to sites that are already on the network have started and are progressing around the network. | 57 | 0 | 437 | 0 | 57 | 0 | 0 | 0 | Some of the miles that were built to the 50 new sites were not counted in this category as they have not yet been activated on the network. 42 new backbone miles on Oahu were lit, along with 2 miles of lateral fiber. The number of miles will remain below the baseline as construction catches up from earlier delays in the start of construction. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is just slightly behind these revised projections due to delays at the end of june in fiber terminations. | n/a | 153 miles of backbone fiber were upgraded this quarter for a total of 437 upgraded backbone miles. This number is still below Baseline due to previous quarters' construction delays. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is just slightly behind these revised projections due to delays at the end of june in fiber terminations. | n/a | Aside from the 42 new backbone miles on Oahu, additional lateral miles were built for the 50 new sites but will not be counted until those sites are activated on the network. This is below the Baseline due to the previous quarters' delays. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is just slightly behind these revised projections due to delays at the end of june in fiber terminations. | n/a | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 74 | 28 | 46 | 2 | A total of 25 CAIs were given new access or upgraded access this quarter. This number is below the baseline due to delays in completing the splices and terminations at the sites, continuing effects of the late receipt of FONSI. Based on projected build rates, the project is estimated to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is just slightly behind these revised projections due to delays at the end of june in fiber terminations. | 10 CAIs were given new access this quarter. This is less than the baseline due to the delayed start of construction as well as network topology limitations. Project participants have been working on improving production rates over the last quarter. Based on projected build rates, the project is estimating that it should reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is just slightly behind these revised projections due to delays at the end of june in fiber terminations. | 15 CAIs were given upgraded access this quarter. This is less than the baseline due to the delayed start of construction as well as network topology limitations. Project participants have been working on improving production rates over the last quarter. Based on projected build rates, the project is estimating that it should reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is just slightly behind these revised projections due to delays at the end of june in fiber terminations. | There are two speed tiers - 10Gbps and 1Gbps. 1 of the new sites are at 10Gbps and 2 improved sites are at 10Gbps. All others were at 1Gbps. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | Newly built sites will be added to the networks as the network topology and fiber splicing allows. Projected Forecasts New Network Miles: 120 New backbone and lateral miles Total CAIs connected: 12 CAIs improved, 70 CAIs new access | University of Hawaii Systems | Coordination among all the parties continues to improve as the weekly construction calls have been very helpful in communicating schedules and concerns and streamlining the construction process. The result is an increase, to a total of 50 sites built this quarter. DOE, UH and HSPLS staff continue to work through the activation of sites onto the network where possible. No assistance from the BTOP project is requested or required at this time. | Previous quarters' delays continue to impact the reported progress of the project. Construction progress has been significant in terms of sites completed due to the improved coordination that has occurred over the past quarters. Maintaining the build rate and activation rate in the next quarters will require continued coordination between all project partners. The project continues to look at ways to streamline the builds and deployments. The upcoming quarter may experience a slight downturn in activations as school starts. The project will be concentrating work on sites and paths that minimize the impact to the production network to continue the deployment pace and keep the projected schedule. A requested network freeze on the INET by the State due to the upcoming primary elections in August may also impact the activations; however, the project is doing its best to continue the progress of the project by working around the State's wavelength and concentrating on paths that do not carry any State traffic. No technical assistance from the BTOP project is requested or required at this time. | TRUE
NT10BIX5570140 | 2012 | Q3 | Q3 - 2012 | Construction and site activation continues across the state for the project. Fiber has been pulled to a total of 54 new sites. Most of these sites have not yet been connected to the network due to the layout of the network topology and the pending completion of the splicing, termination and testing. As these tasks are completed the sites are added to the network. All interisland circuits have been completed and are in service. Upgrades to sites that are already on the network are continuing. | 101 | 0 | 481 | 0 | 101 | 0 | 0 | 0 | Some of the miles that were built to the new sites were not counted in this category as they have not yet been activated on the network. A total of 24 new backbone miles were lit on Oahu, along with 20 miles of lateral fiber across the entire state for a total of 44 new network miles. The number of miles will remain below the baseline as construction catches up from the earlier delays in the start of construction. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. By this revised schedule, the project is just slightly behind, due to delays at the end of June in fiber terminations and the resulting site activations. | n/a | 44 miles of backbone fiber were upgraded this quarter for a cumulative total of 481 miles. This number is still below the baseline due to previous quarters' construction delays. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. By this revised schedule, the project is just slightly behind, due to delays at the end of June in fiber terminations and site activation. | n/a | A total of 101 new network miles of fiber have been deployed to date, a total of 76 miles of new backbone and 25 miles of new lateral. This number is below the baseline due to previous quarters' delays. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. By this revised schedule, the project is just slightly behind, due to delays at the end of June in fiber terminations and site activation. | n/a | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 101 | 52 | 49 | 2 | A total of 27 CAIs were given new access or upgraded access this quarter. This number is below the baseline due to delays in completing the splices and terminations at the sites, continuing effects of the late receipt of FONSI. Based on projected build rates, the project is estimated to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is behind those revised projections due to delays at the end of June in fiber terminations and resulting site activations. | 24 CAIs were given new access this quarter. This is less than the baseline due to the delayed start of construction and network topology limitations. Project participants have been working on improving production rates over the last quarter. Based on projected build rates, the project is estimated to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is behind those revised projections due to delays at the end of June in fiber terminations. | 3 CAIs were upgraded this quarter. This is less than the baseline due to the delayed start of construction and network topology limitations. Project participants have been working on improving production rates over the last quarter. Based on projected build rates, the project is estimated to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is behind those revised projections due to delays at the end of June in fiber terminations. | There are two speed tiers - 10Gbps and 1Gbps. 1 of the new sites are at 10Gbps and 2 improved sites are at 10Gbps. All others were at 1Gbps. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | Newly built sites will be added to the network as the the network topology and fiber splicing allows. Projected Forecasts 60 new Fiber builds 40 new CAI activations Planned for approximately 115 Miles of new backbone; 70 miles of new lateral for total of 185 miles of new fiber. | University of Hawaii Systems | Construction is progressing on schedule. Coordination meetings between all parties has paid off by streamlining the process and approvals and identifying issues that may arise. DOE, HSPLS and UH staff continue to work through the activation of sites onto the network where possible. There have been some delays in splicing built sites into the INET due to scheduling conflicts with Oceanic, however the project is confident that Oceanic will catch up in the coming months. Oceanic has committed to completing their work by the end of May of 2013. Additionally, some miscommunication with Oceanic has resulted in the low site activation numbers - specifically the Oceanic engineering was waiting for large strings of sites to be completed on the outside plant before giving the project the go ahead to begin work. This resulted in delays in activating sites. No assistance from the BTOP project is requested at this time. | Previous quarters' delays continue to impact the reported progress of the project. Construction progress has been significant in terms of sites completed due to the improved coordination that has occurred over the past quarters. Maintaining the build rate and activation rate in the next quarters will require continued coordination among all project partners. The project continues to look at ways to streamline the builds and deployments. Construction build rates have been meeting the target and the project expects the current rate to continue through next quarter. The upcoming quarter may experience a slight downturn in activations due to the Christmas holiday. State and City regulations prevent Oceanic from working on the streets so they are planning to work where they can to abide by those restrictions. Additionally the University is required to take administrative leave days during the last two weeks of the year and staff cannot work during that time. The project will work through these restrictions to the best of its abilities. A requested network freeze on the INET by the State due to the upcoming general elections in November may also impact the activations; however, the project is doing its best to continue the progress of the project by working around the State's wavelength and concentrating on paths that do not carry any State traffic. Additionally, the project has negotiated with the State to reduce the one month freeze to one week. The project realizes that it | TRUE
NT10BIX5570140 | 2012 | Q4 | Q4 - 2012 | The project has continued to make progress to complete the fiber build and activate the CAIs across the island. Of interest this quarter is that all fiber construction on the island of Kauai was completed in the two weeks after Thanksgiving. This included the inside plant termination of the fiber. Oceanic will be planning on cutting all the Kauai sites into the Kauai INET during the first quarter of 2013. Fiber builds are on target and the ability for Oceanic to get 65 sites built this quarter is quite an achievement considering the holidays, UH administrative leave and various blackout periods that the project had to endure. Site activations however were down, again due to the same challenges. | 125 | 0 | 521 | 0 | 125 | 0 | 0 | 0 | Some of the miles that were built to the sites were not counted in this category as they have not yet been activated on the network. A total of 22 new lateral miles were built and 2 miles of new backbone fiber were built during this quarter. The number of miles will remain below the baseline as construction catches up from the earlier delays in the start of construction. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. By this revised schedule, the project is just slightly behind, due to delays at the end of June in fiber terminations and the resulting site activations. | n/a | 40 miles of backbone fiber were upgraded this quarter for a cumulative total of 521 miles. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. By this revised schedule, the project is just slightly behind, due to delays at the end of June in fiber terminations and site activation. | n/a | A total of 125 new network miles of fiber have been deployed to date. This number is below the baseline due to previous quarters' delays. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. By this revised schedule, the project is just slightly behind, due to delays at the end of June in fiber terminations and site activation. | n/a | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 138 | 89 | 49 | 2 | A total of 37 CAIs were given new or upgraded access this quarter. This number is below the baseline due to delays in completing the splices and terminations at the sites, continuing effects of the late receipt of FONSI. Based on projected build rates, the project is estimated to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is behind those revised projections due to delays at the end of June in fiber terminations and resulting site activations. | 37 CAIs were given new access this quarter. Based on projected build rates, the project is estimated to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is behind those revised projections due to delays at the end of June in fiber terminations. | No CAIs were given upgraded access this quarter. Project participants have been working on improving production rates over the last quarter. Based on projected build rates, the project is estimated to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is behind those revised projections due to delays at the end of June in fiber terminations. | There are two speed tiers - 10Gbps and 1Gbps. 1 of the new sites are at 10Gbps and 2 improved sites are at 10Gbps. All others were at 1Gbps. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | The project plans to complete the island of Molokai with its 6 CAIs before the end of the next quarter, as well as the island of Kauai and its 18 CAIs. Big Island sites who have been built will start to be cut into the existing INET rings and be installed and activated. Project Forecasts 50 new Fiber builds 50 new CAI activations Planned for approximately 120 miles of new backbone, 40 miles of lateral for a total of 160 miles of new fiber. | University of Hawaii Systems | The 4th quarter, like previous quarters, proved challenging as many holidays, staff administrative time off, vacations and corporate and local government blackout periods reduced the number of available days for activities to occur. Oceanic has committed to completing their work by the end of May 2013 and is on schedule to complete that task. We were still able to complete a substantial number of sites even with the challenges that we faced during this quarter. Additionally Oceanic was still able to build many sites this quarter even with the delays encountered. Additionally, the Oceanic Director of Outside Plant Engineering and Construction passed away suddenly this quarter. Lance Uno was a key player in the project on the Oceanic side. Although the project will continue on as there is enough momentum, there was some delays incurred as the Oceanic staff had to pick up where he had left off. No assistance from the BTOP project is requested at this time. | Fiber construction continues to be on track to complete by the start of summer and the activations will continue as Oceanic splices the sites into the INET ring. We expect to complete two more islands by the end of next quarter - Kauai and Molokai, which have a total of 24 CAIs. We also expect that some sites on the Big Island will start to come online as construction continues to progress. We are working with Oceanic to see how we can expedite the activation of sites around the island. The pace of the activations are steady and we hope to increase the rate going forward to meet our planned projections. No technical assistance from the BTOP project is requested or required at this time. | TRUE
NT10BIX5570140 | 2013 | Q1 | Q1 - 2013 | The project team continues to make substantial progress on the fiber build and site activations. 28 sites were built this quarter and 62 were activated on the network. Of interest this quarter, the project team was able to completely finish the island of Molokai, bringing the total number of islands completed to 3 out of the 6 islands. Site activations were started on the Big Island and Kauai. A large number of sites on Oahu were also completed as well. There are approximately 60 sites left to build. All other sites are built, but the project is waiting on Oceanic for outside plant splicing. Oceanic continues to work on splicing the newly built sites into the ring at a pace that will ensure completion by may. | 204 | 0 | 578 | 0 | 204 | 0 | 0 | 0 | Some of the miles that were built to the sites were not counted in this category as they have not yet been activated on the network. A total of 42 new lateral miles were built and 37 miles of new backbone fiber were built during this quarter. The number of miles will remain below the baseline as construction catches up from the earlier delays in the start of construction. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. By this revised schedule, the project is just slightly behind, due to delays at the end of June in fiber terminations and the resulting site activations. | n/a | 57 miles of backbone fiber were upgraded this quarter for a cumulative total of 578 miles. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. By this revised schedule, the project is just slightly behind, due to delays at the end of June in fiber terminations and site activation. | n/a | A total of 204 new network miles of fiber have been deployed to date. This number is below the baseline due to previous quarters' delays. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. By this revised schedule, the project is just slightly behind, due to delays at the end of June in fiber terminations and site activation. | n/a | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 200 | 144 | 56 | 2 | A total of 62 CAIs were given new or upgraded access this quarter. This number is below the baseline due to delays in completing the splices and terminations at the sites, continuing effects of the late receipt of FONSI. Based on projected build rates, the project is estimated to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is behind those revised projections due to delays at the end of June in fiber terminations and resulting site activations. | 55 CAIs were given new access this quarter. Based on projected build rates, the project is estimated to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is behind those revised projections due to delays at the end of June in fiber terminations. | 7 CAIs were given upgraded access this quarter. Project participants have been working on improving production rates over the last quarter. Based on projected build rates, the project is estimated to reach baseline numbers towards the later quarters of Year 3. The project will be tracking the Progress Project table that was submitted in June 2012 going forward. This is a revised schedule and the project is behind those revised projections due to delays at the end of June in fiber terminations. | There are two speed tiers - 10Gbps and 1Gbps. All sites were 1Gbps. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | By the end of next quarter, all construction is scheduled to be completed on all islands. The project team expects to fully complete the entire island of Kauai, the last two schools on Maui, and the majority of the sites on Oahu and the Big Island. Projected Forecast 60 new Fiber builds 80 new CAI activations Planned for approximately 60 miles of new backbone, 50 miles of lateral fiber for a total of 110 miles of new fiber. Project is on track for 380 CAIs, 770 miles of upgraded fiber. New miles will be slightly reduced to about 410 miles. 44 miles of fiber cannot be built to Hana and these sites will instead be served by upgraded microwave links. | University of Hawaii Systems | Construction has slowed down from the previous quarters as the more challenging sites are left on Oahu. Neighbor island builds are still progressing as planned and are scheduled to be completed by May. The project team is waiting for Oceanic to complete the outside plant splicing in many locations so these sites can be activated on the network. Oceanic is making steady progress in completing the splicing. The project team will continue to work with Oceanic to get the sites released on a timely basis. The project had planned to complete the island of Kauai this quarter, however there were some delays in the outside plant splicing on Kauai that pushed the date out to the following quarter. The project was able to make up for the lack of Kauai site activations by activating a large number of sites on Oahu. No assistance from the BTOP project is requested at this time. | Fiber construction is scheduled to be completed by the end of next quarter and activations will continue. The project team is planning to have almost all sites activated on the network by the end of next quarter. Oceanic construction and fiber splicing is scheduled to be completed by the end of the next quarter in order to allow us enough time to complete the installation and activation of the sites. Should there be unforeseen delays, this will delay the ability for us to complete the installation and activation. If that occurs, the project team will increase the rate of installs to ensure that the project is completed on time. No Technical assistance from the BTOP project is requested or required at this time. | TRUE
NT10BIX5570140 | 2013 | Q2 | Q2 - 2013 | The project has made significant progress this past quarter and is now back on schedule tracking the baseline numbers. 146 sites were given new or improved access this quarter. The island of Kauai was completely finished and Maui was completed except for three sites on the East side of the island. | 300 | 0 | 755 | 0 | 300 | 0 | 0 | 0 | Some of the miles that were built to the sites are not counted in this category as they have not yet been terminated within the site although the fiber is physically run. A total of 88 miles of lateral fiber were built and 8 miles of new fiber. We are slightly behind the baseline numbers - this can be attributed to the inability for the project to build fiber to Hana and Haleakala due to easement issues with certain landowners. The project has instead utilized alternate means of connectivity. The revised new network miles deployed will be 409 miles. | n/a | 177 miles of backbone fiber were upgraded this quarter for a cumulative total of 755 miles. This number is slightly below the baseline number and can be attributed to the late start of construction. | n/a | A total of 300 new network miles of fiber have been deployed to date. This number is lower than baseline as we were not able to build the Hana and Haleakala runs. | n/a | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 344 | 275 | 69 | 2 | A total of 144 CAIs were given new or upgraded access this quarter. The number of CAIs given new access was slightly below baseline - there are a number of sites that are still being constructed next quarter. The lower than baseline number can be attributed to the late start of construction. | 131 CAIs were given new access this quarter. The number of CAIs given new access was slightly below baseline - there are a number of sites that are still being constructed next quarter. The lower than baseline number can be attributed to the late start of construction. | 13 CAIs were given improved access this quarter. The number of CAIs given new access was slightly below baseline - there are a number of sites that are still being constructed next quarter. The lower than baseline number can be attributed to the late start of construction. | There are two speed tiers - 10Gbps and 1Gbps. All sites were 1Gbps. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | The project expects to complete all possible builds by next quarter. The project is requesting a 6 month no cost extension to complete the sites that could not be built in time due to circumstances out of its control (military approvals, DOE infrastructure improvements, pole replacements, etc). There are approximately 19 sites that are part of the no cost extension - although some may still be completed before the end of the grant. The project expects to complete the remaining 25 sites by the end of next quarter for a total of 369 sites. The project also expects to enter into IRU agreements with HawaiianTel to obtain 10Gbps or greater capacity to two sites that we were unable to build fiber to. Projected New Miles: 89 Projected Upgraded Miles: 15 | University of Hawaii Systems | The project has made significant progress during the last quarter. It has been challenging in terms of logistics and coordination among all INET partners, end of school, registration periods and Oceanic. The project team has made excellent progress considering the coordination required to get sites connected. Construction has slowed down as the challenging sites are left to build. Neighbor island builds are almost done as well. The project team had hoped to make significant progress on the Big Island sites this quarter but due to logistics and equipment, it was decided to push most of the Big Island sites to the next quarter. The project teams do not believe this will cause any significant delays. Fiber builds to Hana and Haleakala were unable to be built. Easement issues with landowners were unable to be resolved due to various reasons. The project has instead backhauled traffic from Hana across the existing University microwave network - but fiber has been placed to the Hana School and Library. For the fiber run to Haleakala, the project has instead requested for leased circuits from HawaiianTel. The project has built fiber to the Puu Nia Niau microwave station for the University, which is half way up the mountain to Haleakala. This will provide additional fiber connectivity to the microwave radios there, which serve the Hana site. No assistance from the BTOP project is requested at this time. | The project will have completed all construction sites and network builds with the exception of the approximately 19 sites by the end of August 2013. The project requests the assistance of the BTOP team in approving the requested 6 month extension. The sites impacted by the extension were delayed in being built due to a variety of challenges - including pole replacement, congested or lack of infrastructure on campus infrastructure, delayed approvals by the Military and HawaiianTel. If the 6 month extension is granted, the project and its partners are confident that these challenges will be overcome as all are resolvable with more time to complete the tasks at hand. | TRUE
NT10BIX5570140 | 2013 | Q3 | Q3 - 2013 | The project has completed all sites except those that were identified in the approved no-cost 6 month extension. 96% of the original sites were completed by end the of the original grant, 8/31/2013. Two CAIs were connected via leased circuits from HawaiianTel as the Oceanic Time Warner Cable fiber could not reach these sites due to easements or other limitations. The grant is now in the no-cost extension period. | 394 | 0 | 759 | 0 | 394 | 1 | 0 | 0 | A total of 85 new miles and 9 lateral miles of fiber were built for a total 94 new miles this quarter. The revised new network miles deployed will be 409 miles as stated on the previous quarter's PPR due to the inability for the project to build fiber to Hana and Haleakala. | n/a | 4 miles of backbone fiber were upgraded this quarter for a cumulative total of 759 miles. The remaining 11 miles will be upgraded when the sites on the no cost extension are completed. | n/a | A total of 394 new network miles of fiber have been built to date. This number is lower than baseline as the project was unable to build the Hana and Haleakala runs. | One Wireless line between Waimalu Elementary and Pearlridge Elementary was installed due to the inability to get fiber into the Pearlridge Elementary campus. | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 374 | 301 | 73 | 2 | A total of 30 CAIs were given new or upgraded access this quarter. The number of CAIs is less than baseline as the project was not able to complete 14 CAIs. Those 14 are in the no cost extension that the project was granted. | 26 CAIs were given new access this quarter for a total of 301 CAIs with new access. The remaining 14 sites are in the no cost extension that the project was granted. | 4 CAIs were given improved access this quarter. This matches the baseline of 73 sites that would have received improved access. | There are two speed tiers - 10Gbps and 1Gbps. 24 are 10Gbps and the remaining 350 are at 1Gbps. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | The project has completed over 96% of the sites on the build list. It is quite an achievement considering that the project only had two full years to build due to the delay in obtaining the Environmental Assessment. Of the 14 sites left to build, the project is confident that it will complete most if not all of these sites during the 6 month no cost extension that was granted. The project is projecting that 11 CAI's will be completed over the next quarter. New Lateral Miles: 6 Miles | University of Hawaii Systems | The project completed 96% of the fiber builds that were originally planned at the start of the grant. The project team and its contractors were able to complete all but 14 sites of the original 381. Those 14 sites will be completed during the 6 month no cost extension that was granted to the project. No assistance from the BTOP project is requested at this time. | The project has completed over 96% of the sites that were originally planned for. The remaining 4% (14 total sites) will be completed during the 6 month no cost extension that was granted. The project team has come up with a project plan that estimated the builds over the next 6 months. At this time we are expecting that about 10 of the sites will be completed by the end of the next quarter. There are a number that require a single pole replacement that may extend into the next quarter - or possibly beyond that. Should the site not be able to be completed by the end of the no cost extension ending on February 28, 2014, the DOE will ensure that funds are available for the completion of the work. No assistance from the BTOP program is requested at this time. | TRUE
NT10BIX5570140 | 2013 | Q4 | Q4 - 2013 | Project is operating in the approved no-cost extension. During this quarter, 7 of the 23 sites that were identified on the Project Completion Schedule of August 2013 as "at risk" were completed for a total of 379 sites completed. A final feasibility review conducted during this quarter identified 9 sites that could not be completed by the end of the extension period but we were able to arrange to complete those using DOE and UH funding after the BTOP grant ends. A total of 11 new network miles were built this quarter, along with 6 miles of upgraded backbone. To date the project has built 405 miles of new fiber and upgraded 765 miles of fiber. The project discovered that 6 sites were incorrectly identified as completed (they were part of the extension list). There were 4 sites that were not included as completed (UH Hilo Farm, Kawaikini PCS, Liliha Library, Hilo DOE Annex). Thus, the number of sites completed last quarter should have been 372. | 405 | 0 | 765 | 0 | 405 | 1 | 0 | 0 | A total of 11 miles of lateral fiber were built this quarter. The remaining 4 lateral miles will be built when the last 5 sites are completed. | n/a | 6 miles of backbone fiber were upgraded this quarter for a cumulative total of 765 miles. The remaining 5 miles will be upgraded when the last 5 sites are completed. | n/a | A total of 405 new networks miles of fiber have been built to date. This number is lower than the baseline as the project was unable to build the Hana and Haleakala runs. The project is tracking for a total of 409 new miles. | One wireless link between Waimalu and Pearlridge Elementary is currently installed. | n/a | n/a | 0 | 0 | 0 | n/a | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 379 | 306 | 73 | 2 | A total of 7 CAIs were given new or upgraded access this quarter. In reviewing our documentation, the project discovered that 6 sites were incorrectly identified as completed (they were part of the extension list). There were 4 sites that were not included as completed (UH Hilo Farm, Kawaikini PCS, Liliha Library, Hilo DOE Annex). Thus, the number of sites completed last quarter should have been 372. | 7 CAIs were given new access this quarter for a total of 306 CAIs with new access. The remaining 5 sites will be completed prior to the end of the extension period. | All CAIs who were previously installed have received improved access. | There are two speed tiers - 10Gbps and 1Gbps. 24 are 10Gbps and the remaining 355 are at 1Gbps. | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a | FALSE | n/a | In January and February the project expects to complete the fiber build to the last 5 CAIs on the extension list for a total of 384 CAIs and 100% construction completion. New Lateral Miles : 4 Miles Upgraded Miles: 5 Miles | University of Hawaii Systems | The project discovered that 6 sites previously identified as completed in last quarter's PPR were incorrectly included and 4 sites were completed but not listed on last quarter's PPR. The numbers for this quarter's PPR have been adjusted and specific corrections indicated in the narrative. The project team identified 4 sites listed in the extension request that would not be able to be completed during the extension period. These sites require more site work either within the site or additional time from Hawaiian Tel or HECO for outside plant fiber installation. The DOE will pick up the remaining cost to get fiber to these sites. Additionally, the 5 other sites that were previously identified as possible but unlikey will not be able done prior to the extension period end date. The DOE and UH will pick up the remaining costs to get fiber to these sites after the grant. An updated site list was submitted for these 9 sites. No technical assistance from the BTOP program is needed at this time. | The next quarter will be the last quarter of the project as the extension period ends on February 28. The project expects to complete 5 additional sites before the end of February so this will require regular follow up with the subcontractors and our other partners to make sure that we keep on schedule. Although we will attempt to record all remaining expenditures in the next quarter, it is likely that a few will remain to be paid during the closeout period. No assistance from the BTOP program is required at this time. | TRUE
NT10BIX5570144 | 2010 | Q4 | Q4 - 2010 | 12/31/2010 - The Northern Illinois University IBOP team has been working on or completed the following: ï· Developing a methodology for project management with partners. ï· Developing a scope of work for sub-recipients to assist with management of non-technical project tasks. ï· Interviewed and selected an engineering firm for environmental assessment. ï· Completed and submitted final shape files for EA to the engineering firm. ï· Initiated environmental assessment. Completed analysis of historic places on CAI list. Retained an archeological consultant for review of routes. Completed analysis of threatened and endangered species. Tasks in progress include the submission of the analysis of threatened and endangered species to USFWS. Continue work on the draft EA report and schedule meeting with Illinois Department of Transportation. Complete ride-out of all planned routes. ï· Performing program and financial due diligence ï· Identify fiber optic contractors for three of nine counties. ï· Developed draft RFQ documents to identify fiber optic contractors to install the cable in the remaining six counties. ï· Finalized project CAIs through meetings with key contacts. ï· Initiated hiring process for engineers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no variance | no variance | no variance | no variance | no variance | no variance | no variance | no variance | 0 | 0 | 0 | not applicable | not applicable | not applicable | 0 | 0 | 0 | 0 | no variance | no variance | no variance | no variance | 0 | 0 | 0 | 0 | no variance | no variance | no variance | no variance | 0 | 0 | 0 | 0 | 0 | no variance | no variance | no variance | no variance | no variance | 0 | 0 | 0 | 0 | 0 | no variance | no variance | no variance | no variance | no variance | not applicable | FALSE | not applicable | For the quarter ended 3/31/2011 our planned accomplishments include: - completion of the environmental assessment and FONSI - execution of contracts with sub recipients - creation of new not-for-profit to coordinate construction through a single point/entity - completion of draft agreements for all cash and in-kind contributors - execution of 25% of those cash and in-kind match agreements. - secure State of Illinois cash match - DCEO grant received in January 2011 - initiation of construction contracts - installation of 25 miles of fiber - connection of 4 CAIs - completion of two signification IRU contracts - hiring of two engineers for project implementation | Northern Illinois University, Inc. | #1 The approval process for adding a new sub recipient to manage construction could impact our progress. We are working with BTOP to facilitate this change. #2 Pending procurement decisions from other BTOP awardees may impact progress on our project. #3 NIU received notification of award on 9/14/2010. However, NTIA determined the first quarter ended 9/30/2010, just two weeks later. NIU's baseline project plan is based on full quarters and therefore does not align with NTIA quarters because of the short two week quarter. If the initial project cannot be changed to 12/31/2010, then NIU will modify its baseline to accommodate the 9/30/2010 two week quarter. Despite the short initial period, we anticipate reaching the overall project target during the grant period. #4 A cultural review will be required on 13% of the project area which may be delayed due to the winter conditions. If a partial FONZI can be issued on the 87% of the region, then it is unlikely to affect construction timelines. If a partial FONZI for the 87% of the area not impacted by the cultural review cannot be issued, then NIU will consider multiple contractors to expedite construction. | #1 NIU received notification of award on 9/14/2010. However, NTIA determined the first quarter ended 9/30/2010, just two weeks later. NIU's baseline project plan is based on full quarters and therefore does not align with NTIA quarters because of the short two week quarter. If the initial project cannot be changed to 12/31/2010, then NIU will modify its baseline to accommodate the 9/30/2010 two week quarter. #2 A cultural review will be required on 13% of the project area which may be delayed due to the winter conditions. If a partial FONZI can be issued on the 87% of the region, then it is unlikely to affect construction timelines. If a partial FONZI for the 87% of the area not impacted by the cultural review cannot be issued, then NIU will consider multiple contractors to expedite construction. | TRUE
NT10BIX5570144 | 2011 | Q1 | Q1 - 2011 | The Broadband Technology Opportunities program is intended to accelerate broadband deployment in unserved and underserved areas, supporting strategic institutions that are likely to create jobs or provide significant public benefits. The Northern Illinois University IBOP team has been working on or completed the following: ï· Completed the analysis of threatened and endangered species for USFWS and ride-out of all planned routes ï· Provided EA information to 6 THPOs who requested project information beyond that provided in the Tower Construction Notification System. Two tribes have not responded; the other four responded concurring with the determination of no effect. ï· Completed an archeological desk top review and a conditional determination of no effect was issued by SHPO. ï· Completed and submitted the Environmental Assessment to NTIA in February. ï· Began review and response to NTIA comments on EA. ï· Received a letter of no objection to the construction of the project under the provisions of Nationwide Permit Number 12 from the Rock Island District of the Army Corps of Engineers. ï· Began archeological field work of 13% of the project region subject to review. ï· Received approval from NTIA/NOAA to add iFiber as a sub recipient to the grant. ï· Established iFiber as a not for profit to manage construction of the project. ï· Developed and released a Request for Qualifications for contractors to build the network. Completed a Contractors Conference and recei | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Based on the shortened first quarter issue noted in 3 above, there is no variance from the baseline plan for the project at six months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Over the next quarter contractors/engineers will be selected and then they can begin deploying network miles. | no variance | no variance | no variance | no variance | no variance | no variance | no variance Over the next quarter contractors/engineers will be selected and then they can begin deploying network milesr contractors/engineers will be selected and then they can begin deploying network miles. | 0 | 4 | 0 | not applicable | not applicable | not applicable | 0 | 0 | 0 | 0 | no variance | Based on the shortened first quarter issue noted above, there is no variance from the baseline plan for the project at six months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Over the next quarter contractors/engineers will be selected and then they can begin deploying network miles. | Based on the shortened first quarter issue noted above, there is no variance from the baseline plan for the project at six months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Over the next quarter contractors/engineers will be selected and then they can begin deploying network miles. | no variance | 0 | 0 | 0 | 0 | no variance | Based on the shortened first quarter issue noted above, there is no variance from the baseline plan for the project at six months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Service Agreements are in progress. | no variance | Based on the shortened first quarter issue noted above, there is no variance from the baseline plan for the project at six months and two weeks from initiation. We anticipate recovering progress lost due to this issue within the next two quarters. Service Agreements are in progress. | 0 | 0 | 0 | 0 | 0 | not applicable | not applicable | not applicable | not applicable | not applicable | 0 | 0 | 0 | 0 | 0 | not applicable | not applicable | not applicable | not applicable | not applicable | not applicable | FALSE | not applicable | - Completion of cultural review - Completion of a partial or completed FONSI. - Completion of a methodology for project management with construction contractors. - Completion of a master service agreement and begin execution of CAI agreements. - Execution of 45% of cash and in-kind match agreements - Initiation of construction contracts - Installation of 25 miles of fiber - Connection to 32 CAIs - Completion of two significant IRU contracts | Northern Illinois University, Inc. | #1 The approval process for adding a new sub recipient to manage construction could impact our progress. We are working with BTOP to facilitate this change. iFiber has been approved by NTIA and added as a new sub recipient. Procurement is in progress and will be issuing contracts early in the next quarter. #2 We are still waiting on two tribal approvals for the release of the FONSI. We anticipate receiving approvals in the next quarter. #3 In response to the EA conditions, we are working on a cultural review of 13% of the project area for the FONSI. Due to the winter conditions, the cultural review was delayed. We anticipate completion of the cultural review during the next quarter. #4 [Shortened First Quarter] The first official project quarter ended 9/30/2010, two weeks after notice of award on 9/14/2010. Therefore progress does not align with original baseline data which was based on full project quarters. According to full project quarters, there is no variance from the baseline plan for the project at six months and two weeks from initiation. We anticipate recovering progress lost due to the shortened first quarter within the next two quarters. Despite the short initial period, we anticipate reaching the overall project target during the grant period. #5 Because the progress is based on federal draw down of funds, there will be more activities than federal dollars spent during the report period. The overall project will be at 67% complete in Q8 6/30/2012. We | We anticipate challenges with permitting and acquisition of rights of way which could delay construction initiation. We are working on those areas that can be addressed and/or initiated in advance. There will be more activities than federal dollars drawn down during the report period due to the lag in expenditures and payments. The overall project will be at 67% complete in Q8 6/30/2012. | TRUE
NT10BIX5570144 | 2011 | Q2 | Q2 - 2011 | ï· Received NTIA approval on 5/9/2011 and the projects qualified Finding of No Significant Impact (FONSI) signed by Wayne Ritchie, the Chief Administrative Officer, Office of Telecommunications and Applications. ï· Secured the services of Baxter & Woodman to begin the permitting process in advance of contractor selection. ï· Initiated the permitting process with IDOT, various railroads, municipalities, and counties. ï· Initiated permitting with IDOT, railroads, and multiple counties, municipalities, and other permitting agencies. ï· Selected and executed an agreement with a construction contractor for four of the nine counties in the project region. We anticipate finalizing the second contractor for the remaining five counties by mid July 2011. ï· Initiated discussions with 6 ISP providers and partners. ï· Developed a wireless RFQ for release in July 2011. ï· Conducted over 25 Outreach Meetings with County/Municipalities across all 9 Counties to build awareness, address questions/concerns, and confirm interest ï· Finalized CAI pricing strategy for iFiber Transport services ï· Approved CAI Service Agreement for CAI review and signatures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Variance of 144 miles is due in part to the delayed FONSI and Shortened First Quarter issue noted in 5. below. According to full project quarters, there is less variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost within the next three quarters. Construction will begin in mid July with the first contractor and the second contractor will begin in mid August. Contracts were executed with 2 contractor during the quarter which will facilitate rapid deployment and network build going forward. | Variance of 234 miles is due in part to the Shortened First Quarter issue noted in 5. below. According to full project quarters, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost within the next three quarters. Lease negotiations are in progress. We expect to have some portions of the leased miles executed during the next quarter. | no variance | no variance | Variance of 371 miles is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there is less variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost within the next three quarters. Construction will begin in mid July with the first contractor and the second contractor will begin in mid August. Contracts were executed with 2 contractor during the quarter which will facilitate rapid deployment and network build going forward. | Variance of 2 wireless links is due in part to the Shortened First Quarter issue noted in 5. below. According to full project quarters, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost within the next three quarters. A RFQ for wireless construction and installation will be released in Aug. We anticipate having a contractor for wireless secured by the end of the next quarter. | no variance | no variance | 0 | 4 | 0 | Agreements are in progress, no signed agreements at this time. | Wholesale services are being developed. | Illinois Fiber Resources Group NFP (iFiber) - sub recipient will operate the entire network. Contact: John Lewis, Chairman (815) 753-0936 jlewis@niu.edu | 0 | 0 | 0 | 0 | no variance | Variance of 6 agreements is due in part to the Shortened First Quarter issue noted in 5. below. According to full project quarters, there is less variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost within the next three quarters. Negotiations are in progress with 6-8 providers which should result in wholesale agreements during the next quarter. | Variance of 6 agreements is due in part to the Shortened First Quarter issue noted in 5. below. According to full project quarters, there is less variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost within the next three quarters. Negotiations are in progress with 6-8 providers which should result in wholesale agreements during the next quarter. | Tiers will be available during the next quarter once agreements are negotiated. | 0 | 0 | 0 | 0 | Variance of 30 subscribers is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there is less variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost within the next three quarters. Construction began in mid July and the second contractor will begin in mid August. Contracts were executed with 2 contractor during the quarter which will facilitate rapid deployment and network build going forward. | Variance of 1 subscriber is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there is no variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost within the next three quarters. Construction began in mid July and the second contractor will begin in mid August. Contracts were executed with 2 contractor during the quarter which will facilitate rapid deployment and network build going forward. | Variance of 30 subscribers is due in part to the delayed FONSI and Shortened First Quarter issue noted above. According to full project quarters, there is less variance from the baseline plan for the project at nine months and two weeks from initiation. We anticipate recovering progress lost within the next three quarters. Construction began in mid July and the second contractor will begin in mid August. Contracts were executed with 2 contractor during the quarter which will facilitate rapid deployment and network build going forward. | 1 Gbps for 461 CAIs and 100 Mbps for 72 CAIs | 0 | 0 | 0 | 0 | 0 | not applicable | not applicable | not applicable | not applicable | not applicable | 0 | 0 | 0 | 0 | 0 | not applicable | not applicable | not applicable | not applicable | not applicable | not applicable | FALSE | not applicable | - PirTano Construction will break ground in Lee County Illinois during the week of July 18, 2011. - We anticipate finalizing a construction contract with the second contractor in mid July 2011 with construction in their region to begin in early August. This contractor has partnered with another finalist in the RFP process which will provide additional crews in the field. - We anticipate executing dozens of CAI agreements during the next quarter in conjunction with construction plans. Letters of Intent are being received in advance of the agreements to facilitate planning, design and execution. - Permitting will continue and will get ahead of construction over the next three months ensuring continuous flow of progress. Permits for major routes including IDOT and many county routes will be completed. - We are in negotiations with several ISP providers and anticipate executing agreements with those providers in the next quarter. - We anticipate signing IRUs with organization for dark fiber back haul. - RFQs and RFPs will be released during the next quarter for wireless installation and equipment. - Engineering and design for CAI building entrances will begin in July. | Northern Illinois University, Inc. | 1) Incumbent providers have increased target marketing aggressiveness to sign up BTOP project CAIs in advance of our efforts. This has resulted in CAIs signing long term contracts with other providers in the past few months. This recent activity from incumbent providers may inhibit our ability to sign up anchor institutions. We have initiated extensive outreach campaigns to provide an update on the project and anticipated build plans. 2) A portion of the project region may require greater than anticipated depths for duct and fiber installation. Our team and engineering firm are working with the affected county to resolve the issue. 3) The project's environmental assessment was submitted to NTIA on 2/7/2011. The FONSI was received on 5/8/2011. This three month period delayed construction start and will have an impact on progress in the next few quarters. Despite the delay in clearance to begin construction, we anticipate overcoming progress lost within the next three quarters and reaching the overall project target during the grant period. 4) Because the progress reported in this report is based on federal draw down of funds, there will be more activities than federal dollars spent during the report period. The overall project will be at 67% complete in Q8 6/30/2012. We are working with sub recipients and contractors to ensure timely receipt of invoices for expenditures on the project. 5) [Shortened First Quarter] The first official project quarter ended 9/30/2010, | We anticipate challenges with permitting and acquisition of rights of way which could delay construction progress in certain areas. We are working on those areas that can be addressed and/or initiated in advance. Weather related issues could cause delays in construction. CAI approval process of the service agreements could cause delays in completing building entrances and lighting of anchor institutions. In the interim, we are collecting Letters of Intent from CAIs. Meeting match estimates from proposal could be challenging given NTIAs redefinition of eligible match. We are waiting for clarification from NTIA on the eligibility and proper valuation of certain items of match that are currently listed in our budget. The impact of this ruling may reduce our match by $3-$4 million. There will be more activities than federal dollars drawn down during the report period due to the lag in expenditures and payments. The overall project will be at 67% complete in Q8 6/30/2012. Match proportionality - With clarification on our 20% state matching funds, NIU will proportionally draw those funds during the next quarter. A portion of the additional match is under review pending NTIAs ruling on match valuation. Additionally, NTIAs decision requiring that certain match partners be specified as sub recipients has resulted in loss of at least one match contributor and may impact others. NIU will not be able to reach true match proportionality until valuation rules are clarified. Furth | TRUE
NT10BIX5570144 | 2011 | Q3 | Q3 - 2011 | ARRA 9/30/2011 Project Description/Activities - The Broadband Technology Opportunities program is intended to accelerate broadband deployment in unserved and underserved areas, supporting strategic institutions that are likely to create jobs or provide significant public benefits. The Northern Illinois University IBOP team has been working on or completed the following: ï· Construction contracts for entire iFiber network footprint executed ï· Completed final engineering design for 40% of theconstructed route. ï· Received permits for 18% of the constructed route. ï· Completed duct installation for 12% of the new construction portion of the project totaling 65 miles. ï· Fiber optic material will be received in early October to both construction contractors. ï· Met with 50% of CAIs and have secured letters of intent to participate from 30% ï· Completed 5 CAI â€œlast mileâ€ lateral terminations for connectivity ï· Received final match contribution agreements from 31% of contributors ï· Initiated Wireless RFQ and received 7 responses. Interviewed 3 finalists and anticipate executing an agreement with one during the next quarter. ï· On-going negotiations with iFiber Partners to provide ISP/Content/Cloud services over iFiber transport network; anticipate tentative agreements in place by EOY2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. Construction will begin in mid July with the first contractor and the second contractor will begin in mid August. Contracts were executed with 2 contractor during the quarter which will facilitate rapid deployment and network build going forward. | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. Lease negotiations are in progress with 12 broadband wholesalers and last mile providers. Several of these agreements are in their final stages. We expect to have many portions of the leased miles finalized during the next quarter. We have identified additional resources to assist in solidifying agreements for leased miles which will impact progress during the next quarter. | no variance | no variance | Variance is due in part to permitting, the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. Construction will begin in mid July with the first contractor and the second contractor will begin in mid August. Contracts were executed with 2 contractor during the quarter which will facilitate rapid deployment and network build going forward. | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. We are in the final stages of the selection process for a Wireless contractor and anticipate issuing a contract during the next quarter. | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. We are in the final stages of the selection process for a Wireless contractor and anticipate issuing a contract during the next quarter. | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. We are in the final stages of the selection process for a Wireless contractor and anticipate issuing a contract during the next quarter. | 0 | 8 | 0 | Negotiations are in progress, no signed agreements at this time. | Wholesale services are being developed. | Illinois Fiber Resources Group NFP (iFiber) - sub recipient will operate the entire network. Contact: John Lewis, Chairman (815) 753-0936 jlewis@niu.edu | 0 | 0 | 0 | 0 | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. Negotiations are in progress with 10-12 providers which should result in wholesale agreements during the next quarter. | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next two quarters. Negotiations are in progress with 6-8 providers which should result in wholesale agreements during the next quarter. | Tiers will be available during the next quarter once agreements are negotiated. | 0 | 0 | 0 | 0 | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next three quarters. We have met with 50% of CAIs and have secured letters of intent to participate from 30%. During the quarter, we completed 5 CAI â€œlast mileâ€ lateral terminations for connectivity and anticipate a significant increase during the next quarter with 2 contractors deployed on the project. | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next three quarters. We have met with 50% of CAIs and have secured letters of intent to participate from 30%. During the quarter, we completed 5 CAI â€œlast mileâ€ lateral terminations for connectivity and anticipate a significant increase during the next quarter with 2 contractors deployed on the project. | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at twelve months and two weeks from initiation. We anticipate aligning to baseline within the next three quarters. We have met with 50% of CAIs and have secured letters of intent to participate from 30%. During the quarter, we completed 5 CAI â€œlast mileâ€ lateral terminations for connectivity and anticipate a significant increase during the next quarter with 2 contractors deployed on the project. | 1 Gbps for 461 CAIs and 100 Mbps for 72 CAIs | 0 | 0 | 0 | 0 | 0 | not applicable | not applicable | not applicable | not applicable | not applicable | 0 | 0 | 0 | 0 | 0 | not applicable | not applicable | not applicable | not applicable | not applicable | not applicable | FALSE | not applicable | We are actively negotiating with 12 leased and last mile providers and anticipate finalizing partner agreements with wholesale and last mile providers in addition to IRUs for portions of the network. Several of these agreements are in their final stages. We will have selected and executed an agreement with a Wireless Contractor and Equipment vendor for CAI gear. We will have received responses and evaluated vendors for Locate and Maintenance and Construction Inspection responding to the RFP/RFQs. Additionally, we will be releasing the Equipment RFPs for core and backbone. Contractors will begin blowing fiber in October and we anticipate a minimum of 40 new network miles deployed during the next quarter. While we have several leased miles under negotiation and in the final stages of execution, the holiday season may delay full execution of those agreements. Therefore, we anticipate no new network miles leased during the next quarter but will have substantial leased miles executed during Q1 2012. We will have a minimum of 3 CAI subscribers connected during the next quarter and 90% of all CAIs contacted. While we are in negotiations with 12 broadband wholesalers and last mile providers, we anticipate fully executed agreements will be received in Q1 2012. | Northern Illinois University, Inc. | 1) Incumbent providers have increased target marketing aggressiveness to sign up BTOP project CAIs in advance of our efforts. This has resulted in CAIs signing long term contracts with other providers in the past few months. This recent activity from incumbent providers may inhibit our ability to sign up anchor institutions. We have initiated extensive outreach campaigns to provide an update on the project and anticipated build plans. As of 9/30/2011, we have received letters of intent from 30% of our CAIs. 2) A portion of the project region may require greater than anticipated depths for duct and fiber installation. Our team and engineering firm are working with the affected county to resolve the issue. 3) FONSI. The project's environmental assessment was submitted to NTIA on 2/7/2011. The FONSI was received on 5/8/2011. This three month period delayed construction start and will have an impact on progress in the next few quarters. Despite the delay in clearance to begin construction, we anticipate overcoming progress lost within the next three quarters and reaching the overall project target during the grant period. 4) Expenditures. Because the progress reported in this report is based on federal draw down of funds, there will be more activities than federal dollars spent during the report period. The overall project will be at 67% complete in Q8 6/30/2012. We are working with sub recipients and contractors to ensure timely receipt of invoices for expenditures on t | Weather. Midwest weather could delay construction depending on snow levels and frost lines. Permitting. Nearly 75% of total permitting for the project is with a single agency who had limited resources available for permitting causing significant slow down in turnaround time given this project and other numerous projects in the region. Turnaround time for permits has increased significantly. The permitting agency plans to deploy additional resources in the next quarter. In the meantime, the construction companies have held back on additional crew deployment until sufficient permitting existed which has delayed the overall project schedule. We anticipate permitting to speed up in the next quarter allowing for maximum crews to be deployed on the project. Private Property Easements. There are hundreds of private properties which may require easements through rights of way along County and Townships routes. We are currently conducting title search to verify property status. In parraellel to thte title seearch we are developing a tactical outreach plan for obtaining easements. This could impose delays in construction along county and township routes along with costs associated with obtaining easements. | TRUE
NT10BIX5570144 | 2011 | Q4 | Q4 - 2011 | The Broadband Technology Opportunities program is intended to accelerate broadband deployment in unserved and underserved areas, supporting strategic institutions that are likely to create jobs or provide significant public benefits. The Northern Illinois University team has been working on or completed the following: ï· Completed final engineering design for 84% of the planned route. ï· Received permits for 34% of the planned route. ï· Completed duct installation for 30% of the new construction portion of the project totaling 187 miles. ï· Completed fiber installation for 5% of the new construction portion of the project totaling 29 miles ï· Met with 80% of CAIs and have secured letters of intent to participate from 41% ï· Completed 6 CAI laterals for connectivity ï· Selected wireless construction contractor, contract in progress. ï· Selected CAI equipment vendor, contract in progress. ï· Selected Construction Inspection contractor, contract in progress ï· Selected locate and maintenance contractor, contract in progress ï· On-going negotiations with potential iFiber Partners to provide ISP/Content/Cloud services to anchor institutions over the iFiber transport network; anticipate some agreements in place by end of Q12012. ï· Hired business development staff dedicated to securing agreements with private sector partners to supply bandwidth services and developing the private sector portion of the network ï· Hired Network Engineer to start 1/3/2012 | 29 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. At 12/31/2011, 84% of the fiber optic portion of the network is designed and 34% permitted. over 187 miles of conduit have been installed and 29 miles of fiber blown. Lateral terminations for 6 CAIs have been completed with many more in progress. We have selected both a wireless contractor and CAI equipment vendor and will be executing final contract in January along with initial purchases. We are confident the project will reach its 67% completion milestone. | Variance is due in part to the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. The planned lease routes are in progress and we anticipate execution of a significant portion in the next quarter. Lease agreements with IDOT and ISTHA for 66 miles along I-90 and I-88 are nearing completion. Other lease agreements are in progress. | no variance | no variance | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. At 12/31/2011, 84% of the network is designed and 34% permitted. over 187 miles of conduit have been installed and 29 miles of fiber blown. Lateral terminations for 6 CAIs have been completed with many more in progress. We have selected both a wireless contractor and CAI equipment vendor and will be executing final contract in January along with initial purchases. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. A wireless contractor has been selected and the final contract is in progress. We have secured CAI participation for 6 initial wireless links and anticipate initiation of those links during the next quarter. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. A wireless contractor has been selected and the final contract is in progress. We have secured CAI participation for 6 initial wireless links and anticipate initiation of those links during the next quarter. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. Fiber installation began during the quarter. We anticipate splicing and interconnections to begin during the next quarter. | 0 | 22 | 0 | Negotiations are in progress, no signed agreements at this time. We anticipate receiving a minimum of 2 executed agreements in late Q1 2012 or early Q2 2012. | Wholesale services are being developed. | Illinois Fiber Resources Group NFP (iFiber) - sub recipient will operate the entire network. Contact: John Lewis, Chairman (815) 753-0936 jlewis@niu.edu | 0 | 0 | 0 | 0 | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. We have secured a dedicated resource during the quarter for wholesale and last mile provider negotiations to expedite this process. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. We have secured a dedicated resource during the quarter for wholesale and last mile provider negotiations to expedite this process. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. We have secured a dedicated resource during the quarter for wholesale and last mile provider negotiations to expedite this process. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Tiers will be available once agreements are finalized. | 6 | 0 | 6 | 2 | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. We have met with 80% of CAIs and have secured letters of intent to participate from 41%. During the quarter, we completed 6 CAI lateral terminations for connectivity and anticipate a significant increase during the next two quarter with 2 contractors deployed on the project. | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. We have met with 80% of CAIs and have secured letters of intent to participate from 41%. During the quarter, we completed 6 CAI lateral terminations for connectivity and anticipate a significant increase during the next two quarter with 2 contractors deployed on the project. | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at fifteen months and two weeks from initiation. We have met with 80% of CAIs and have secured letters of intent to participate from 41%. During the quarter, we completed 6 CAI lateral terminations for connectivity and anticipate a significant increase during the next two quarter with 2 contractors deployed on the project. | 1 Gbps for 461 CAIs and 100 Mbps for 72 CAIs | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | We are actively negotiating with 22 leased and last mile providers and anticipate finalizing partner agreements with wholesale and last mile providers in addition to IRUs for portions of the network. Several of these agreements are in their final stages. We will have selected and executed agreements for a wireless contractor, equipment vendor for CAI gear, construction inspection, locate and maintenance contractor. We will have received responses and evaluated vendors for core equipment who respond to the planned RFP. Contractors began blowing fiber in October and we anticipate a minimum of 40 new network miles deployed during the next quarter. We have several leased miles under negotiation and in the final stages of execution. We will have a minimum of 20 CAI subscribers connected during the next quarter and 90% of all CAIs contacted. While we are in negotiations with 22 broadband wholesalers and last mile providers, we anticipate several fully executed agreements will be received in late Q1 2012 or early Q2 2012. | Northern Illinois University, Inc. | 1) Incumbent providers have increased target marketing aggressiveness to sign up BTOP project CAIs in advance of our efforts. This has resulted in CAIs signing long term contracts with other providers in the past few months. This recent activity from incumbent providers may inhibit our ability to sign up anchor institutions. We have initiated extensive outreach campaigns to provide an update on the project and anticipated build plans. As of 12/31/2011, we have received letters of intent from 41% of our CAIs. 2) A portion of the project region may require greater than anticipated depths for duct and fiber installation. Our team and engineering firm are working with the affected county to resolve the issue. 3) FONSI. The project's environmental assessment was submitted to NTIA on 2/7/2011. The FONSI was received on 5/8/2011. This three month period delayed construction start and will have an impact on progress in the next few quarters. Despite the delay in clearance to begin construction, we anticipate overcoming progress lost within the next three quarters and reaching the overall project target during the grant period. 4) Expenditures. Because the progress reported in this report is based on federal draw down of funds, there will be more activities than federal dollars spent during the report period. The overall project will have drawn 67% of federal expenditures by the project milestone, Q9 8/31/2012. We are working with sub recipients and contractors to ensure time | Weather. Midwest weather could delay construction depending on snow levels and frost lines. However, both contractors were still plowing in late December and anticipated plowing well into January 2012. | TRUE
NT10BIX5570144 | 2012 | Q1 | Q1 - 2012 | The Broadband Technology Opportunities Program (BTOP) is intended to accelerate broadband deployment in unserved and underserved areas, supporting strategic institutions that are likely to create jobs or provide significant public benefits. The Northern Illinois University BTOP team has been working on or completed the following: ï· To date, we have completed final engineering design for 87% of the fiber route representing 533 miles of 616 miles, 18.5 miles of which were completed during this reporting quarter. ï· To date, we have received permits for 61% of the fiber route representing 373 miles of 616 miles, 166 miles of which were received during this reporting quarter. ï· To date, we have completed duct installation for 50% of the new fiber portion of the project totaling 305 miles of 616 miles, 118 miles of which were completed during this reporting quarter. ï· To date, we have completed fiber installation for 17% of the new fiber portion of the project totaling 102 miles of 616 miles, 73 miles of which were completed during this reporting quarter. ï· To date, we have met with 95% of CAIs and secured commitments from 71%, 30% of which were completed during this reporting quarter. ï· To date, we have completed lateral building entrances with conduit installation for 45 CAI buildings and fiber installation to 25 CAI buildings, 19 of which were completed during this reporting quarter. ï· This quarter we finalized an agreement with a wireless construction contractor. The technical design is complete for 5 wireless segments. The contractor is proceeding with the implementation/construction phase. An additional 7 wireless segments are under design/review by the contractor. ï· This quarter the initial order of CAI equipment has been received. ï· This quarter we finalized an agreement with a Construction Inspection contractor who initiated inspections in early March. ï· This quarter we finalized an agreement with a locate and maintenance contractor. ï· This quarter we Initiated the RFP for core network equipment. Seven RFPs were received, three finalists were interviewed. We anticipate final selection of a vendor by the end of April. | 102 | 157 | 0 | 0 | 102 | 0 | 0 | 0 | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. At 3/31/2012, 87% of the fiber optic portion of the network is designed and 61% permitted. Over 305 miles of conduit have been installed and 102 miles of fiber blown. Lateral terminations for 25 CAIs have been completed with 27 more in progress. We have selected both a wireless contractor and CAI equipment vendor. CAI equipment has been purchased and core equipment is in the final stages of vendor selection. The project is on track to reach its 67% completion milestone. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. Leased miles were secured for a majority of the planned routes. The final segment of leased miles will be executed early in the next quarter. | no variance | no variance | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. At 3/31/2012, 87% of the fiber optic portion of the network is designed and 61% permitted. Over 305 miles of conduit have been installed and 102 miles of fiber blown. Lateral terminations for 25 CAIs have been completed with dozens more in progress. We have selected both a wireless contractor and CAI equipment vendor and have initiated the initial 5 wireless links and CAI equipment. The project is on track to reach its 67% completion milestone. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. 5 wireless links have been designed and another 7 will be in progress during Q2 2012. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. 5 wireless links have been designed and another 7 will be in progress during Q2 2012. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. Most interconnection points have been identified and agreements are in process for many. We anticipate solidifying all interconnection points during the next two quarters. | 0 | 22 | 0 | Negotiations are in progress, we have no signed agreements at this time but several are in the final stages. We anticipate receiving a minimum of 2 executed agreements in early Q2 2012. | Wholesale services are being developed and a plan completed by Q4 2012. | Illinois Fiber Resources Group NFP (iFiber) - sub recipient will operate the entire network. Contact: John Lewis, Chairman (815) 753-0936 jlewis@niu.edu | 0 | 0 | 0 | 0 | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. We secured a dedicated resource during the prior quarter for wholesale and last mile provider negotiations to expedite this process. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. We secured a dedicated resource during the prior quarter for wholesale and last mile provider negotiations to expedite this process. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. We secured a dedicated resource during the prior quarter for wholesale and last mile provider negotiations to expedite this process. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Tiers will be available once agreements are finalized. | 26 | 0 | 26 | 2 | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. We have met with 95% of CAIs and have secured letters of intent to participate from 71%. During the quarter, we completed 25 CAI lateral terminations for connectivity and anticipate a significant increase during the next two quarters with 2 contractors deployed on the project. | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. We have met with 95% of CAIs and have secured letters of intent to participate from 71%. During the quarter, we completed 25 CAI lateral terminations for connectivity and anticipate a significant increase during the next two quarters with 2 contractors deployed on the project. | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan for the project at eighteen months and two weeks from initiation. We have met with 95% of CAIs and have secured letters of intent to participate from 71%. During the quarter, we completed 25 CAI lateral terminations for connectivity and anticipate a significant increase during the next two quarters with 2 contractors deployed on the project. | 1 Gbps for 461 CAIs and 100 Mbps for 72 CAIs | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | We are actively negotiating with 22 leased and last mile providers and anticipate finalizing partner agreements with wholesale and last mile providers in addition to IRUs for portions of the network. Several of these agreements are in their final stages. We have received commitments from CAIs for the first 5 wireless links and identified the next 7. During the next quarter wireless equipment and installation will begin for the first 5 links and design/engineering will be completed for the next 7 links. We are in the final stages of evaluating core network equipment and vendors. We anticipate selection of the vendor during the next quarter and initiating the first purchase of equipment. Contractors have blown 102 files of fiber into the 305 miles of conduit through the end of this quarter. By the end of the next quarter we anticipate completing 420 miles of new conduit installation and 325 miles of new fiber blown. We will have a minimum of 50 CAI subscribers connected during the next quarter and 90% of all CAIs committed. While we are in negotiations with 22 broadband wholesalers and last mile providers, we anticipate at least two fully executed agreements will be received in Q2 2012. | Northern Illinois University, Inc. | 1) Incumbent providers have increased target marketing aggressiveness to sign up BTOP project CAIs in advance of our efforts. This has resulted in CAIs signing long term contracts with other providers in the past few months. This recent activity from incumbent providers may inhibit our ability to sign up anchor institutions. We have initiated extensive outreach campaigns to provide an update on the project and anticipated build plans. As of 3/31/2012, we have received letters of intent from 71% of our CAIs. 2) A portion of the project region may require greater than anticipated depths for duct and fiber installation. Our team and engineering firm are working with the affected county to resolve the issue. 3) FONSI. The project's environmental assessment was submitted to NTIA on 2/7/2011. The FONSI was received on 5/8/2011. This three month period delayed construction start and will have an impact on progress in the next few quarters. Despite the delay in clearance to begin construction, we anticipate overcoming progress lost within the next two quarters and reaching the overall project target during the grant period. 4) Expenditures. Because the progress reported in this report is based on federal draw down of funds, there will be more activities than federal dollars spent during the report period. The overall project will have drawn 67% of federal expenditures by the project milestone at 8/31/2012. We are working with sub recipients and contractors to ensure timely r | If permitting continues to be slow through the primary permitting agency, it could delay construction in portions of the network. However, we anticipate having enough miles for significant progress during the next quarter. Fiber Availability. We are beginning to experience delays in fiber deliveries. While we continue to have sufficient fiber on hand to meet construction timelines, this issue will be monitored closely as we move into the busier spring/summer seasons. | TRUE
NT10BIX5570144 | 2012 | Q2 | Q2 - 2012 | The Broadband Technology Opportunities Program (BTOP) is intended to accelerate broadband deployment in unserved and underserved areas, supporting strategic institutions that are likely to create jobs or provide significant public benefits. The Northern Illinois University BTOP team has been working on or completed the following: ï· Completed final engineering design for 94% of the planned route representing 582 miles. ï· Received permits for 77% of the planned route representing 478 miles. ï· Completed duct installation for 70% of the new construction portion of the project totaling 432 miles. ï· Completed fiber installation for 47% of the new construction portion of the project totaling 292 miles. ï· Met with 95% of CAIs and secured commitments from 72%. ï· Completed lateral building entrances with conduit installation for 105 CAI buildings; fiber installation to 90 CAI buildings. ï· Completed the technical design for 5 wireless segments. The contractor is currently working on technical design for 7 additional segments. ï· Selected a vendor for core network equipment and initiated the contract. ï· On-going negotiations with iFiber Partners to provide ISP/Content/Cloud services over iFiber transport network; anticipate agreements in place by Q3 2012. | 292 | 203 | 0 | 0 | 292 | 0 | 0 | 0 | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. At 6/30/2012, 94% of the network is designed and 77% permitted. Over 432 miles of conduit have been installed and 292 miles of fiber blown. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Leased miles were secured for a majority of the planned routes. The final segment of leased miles will be executed early in the next quarter. | no variance | no variance | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. At 6/30/2012, 94% of the network is designed and 77% permitted. Over 432 miles of conduit have been installed and 292 miles of fiber blown. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Five wireless links have been designed and easement agreements for towers are in progress. Another 7 are being designed and easement agreements will begin in Q3 2012. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Tower easement agreements are in progress and most will be executed during Q3 2012. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Most interconnection points have been identified and agreements are in process for many. We anticipate solidifying all interconnection points during the next two quarters. | 0 | 8 | 0 | Negotiations are in progress, we have no signed agreements at this time but several are in the final stages. We anticipate receiving a minimum of 4 executed agreements in Q3 2012. | Wholesale services are being developed and a plan completed by Q4 2012. | Illinois Fiber Resources Group NFP (iFiber) - sub recipient will operate the entire network. Contact: John Lewis, Chairman (815) 753-0936 jlewis@niu.edu | 0 | 0 | 0 | 0 | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. We secured a dedicated resource during the prior quarter for wholesale and last mile provider negotiations to expedite this process. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. We secured a dedicated resource during the prior quarter for wholesale and last mile provider negotiations to expedite this process. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Variance is due in part to permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. We secured a dedicated resource during the prior quarter for wholesale and last mile provider negotiations to expedite this process. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Tiers will be available once agreements are finalized. | 90 | 0 | 90 | 2 | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. We have met with 95% of CAIs and have secured letters of intent to participate from 72%. During the quarter, we completed 64 CAI lateral terminations for connectivity and anticipate a significant increase during the next two quarters with 2 contractors deployed on the project. | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. We have met with 95% of CAIs and have secured letters of intent to participate from 72%. During the quarter, we completed 64 CAI lateral terminations for connectivity and anticipate a significant increase during the next two quarters with 2 contractors deployed on the project. | Variance is due in part to the delayed FONSI and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. We have met with 95% of CAIs and have secured letters of intent to participate from 72%. During the quarter, we completed 64 CAI lateral terminations for connectivity and anticipate a significant increase during the next two quarters with 2 contractors deployed on the project. | 1 Gbps for 461 CAIs and 100 Mbps for 72 CAIs | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | We are actively negotiating with 22 leased and last mile providers and anticipate finalizing partner agreements with wholesale and last mile providers in addition to IRUs for portions of the network. Several of these agreements are in their final stages. We have received commitments from CAIs for the first 5 wireless links and identified the next 7. During the next quarter wireless equipment and installation will begin for the first 5 links and design/engineering will be completed for the next 7 links. We are in the final stages of evaluating core network equipment and vendors. We anticipate selection of the vendor during the next quarter and initiating the first purchase of equipment. Contractors have blown 292 files of fiber into 432 miles of conduit through the end of this quarter. By the end of the next quarter we anticipate completing 530 miles of new conduit installation and 450 miles of new fiber blown. We will have a minimum of 180 CAI subscribers connected during the next quarter and 98% of all CAIs committed. While we are in negotiations with 22 broadband wholesalers and last mile providers, we anticipate at least four fully executed agreements will be received in Q3 2012. | Northern Illinois University, Inc. | 1) Incumbent providers have increased target marketing aggressiveness to sign up BTOP project CAIs in advance of our efforts. This has resulted in CAIs signing long term contracts with other providers in the past few months. This recent activity from incumbent providers may inhibit our ability to sign up anchor institutions. We have initiated extensive outreach campaigns to provide an update on the project and anticipated build plans. As of 6/30/2012, we have received letters of intent from 72% of our CAIs. 2) A portion of the project region may require greater than anticipated depths for duct and fiber installation. We have submitted a route modification request to address this portion of the project. 3) FONSI. The project's environmental assessment was submitted to NTIA on 2/7/2011. The FONSI was received on 5/8/2011. This three month period delayed construction start and will have an impact on progress in the next few quarters. Despite the delay in clearance to begin construction, we anticipate overcoming progress lost within the next two quarters and reaching the overall project target during the grant period. 4) Expenditures. Because the progress reported in this report is based on federal draw down of funds, there will be more activities than federal dollars spent during the report period. The overall project will have drawn 67% of federal expenditures by the project milestone at 8/31/2012. We are working with subrecipients and contractors to ensure timely rec | Fiber Availability. We are beginning to experience delays in fiber deliveries. While we continue to have sufficient fiber on hand to meet construction time lines, this issue will be monitored closely as we move into the busier spring/summer seasons. | TRUE
NT10BIX5570144 | 2012 | Q3 | Q3 - 2012 | The Broadband Technology Opportunities Program (BTOP) is intended to accelerate broadband deployment in unserved and underserved areas, supporting strategic institutions that are likely to create jobs or provide significant public benefits. The Northern Illinois University BTOP team has been working on or completed the following: ï· Completed final engineering design for 98% of the planned route representing over 600 miles. ï· Received permits for 86% of the planned route representing 540 miles. ï· Completed duct installation for 76% of the new construction portion of the project totaling 480 miles. ï· Completed fiber installation for 58% of the new construction portion of the project totaling 365 miles. ï· Met with 98% of CAIs and secured commitments from 72%. ï· Completed lateral building entrances and fiber installation to 138 CAI locations. ï· Completed the technical design for 5 wireless segments, 2 of which are currently being installed. ï· Received core network equipment, training and implementation is in progress. ï· On-going negotiations with iFiber Partners to provide ISP/Content/Cloud services over iFiber transport network; anticipate agreements in place by Q4 2012. | 365 | 203 | 0 | 0 | 365 | 0 | 0 | 0 | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. At 9/30/2012, 98% of the network is designed and 86% permitted. Over 480 miles of conduit have been installed and 365 miles of fiber blown. Fiber and wireless route modifications submitted to NTIA in June 2012 are pending approval. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Leased miles were secured for a majority of the planned routes. The final segment of leased miles will be executed in the next two quarters. | no variance | no variance | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. At 9/30/2012, 98% of the network is designed and 86% permitted. Over 480 miles of conduit have been installed and 365 miles of fiber blown. Fiber and wireless route modifications submitted to NTIA in June 2012 are pending approval. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Five wireless links have been designed and easement agreements for towers are in progress. Another 7 are being designed and easement agreements in progress. Most wireless locations were revised from the original EA and were submitted to NTIA in June 2012. NTIA route modification approval is still pending. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Tower easement agreements are in progress and most will be executed during 2012. Most wireless locations were revised from the original EA and were submitted to NTIA in June 2012. NTIA route modification approval is still pending. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Most interconnection points have been identified and agreements are in process for many. We anticipate solidifying all interconnection points during the next two quarters. | 0 | 22 | 0 | Negotiations are in progress and several are in the final stages. We anticipate receiving a minimum of 4 executed agreements in Q4 2012. | Wholesale services are being developed and a plan completed by Q4 2012. | Illinois Fiber Resources Group NFP (iFiber) - sub recipient will operate the entire network. Contact: John Lewis, Chairman (815) 753-0936 jlewis@niu.edu | 0 | 0 | 0 | 0 | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Tiers will be available once agreements are finalized. | 138 | 0 | 138 | 2 | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. The project team has met with 98% of CAIs and has secured letters of intent to participate from 72%. During the quarter, the project connected 138 CAIs. Pending route modifications submitted in June 2012 are stalling completion of 72 fiber and 14 wireless CAI locations. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. The project team has met with 98% of CAIs and has secured letters of intent to participate from 72%. During the quarter, the project connected 138 CAIs. Pending route modifications submitted in June 2012 are stalling completion of 72 fiber and 14 wireless CAI locations. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. The project team has met with 98% of CAIs and has secured letters of intent to participate from 72%. During the quarter, the project connected 138 CAIs. Pending route modifications submitted in June 2012 are stalling completion of 72 fiber and 14 wireless CAI locations. | 1 Gbps for 461 CAIs and 100 Mbps for 72 CAIs | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Contractors have blown 365 miles of fiber into 480 miles of conduit through the end of this quarter. By the end of the next quarter we anticipate completing all available miles of new conduit installation and new fiber blown. We estimate deploying an additional 36 miles of conduit during Q4 2012 and 140 miles of fiber. We will have a minimum of 180 CAI subscribers connected during the next quarter and 100% of all CAIs committed. While we are in negotiations with 22 broadband wholesalers and last mile providers, we anticipate at least four fully executed agreements will be received in Q4 2012. Approval of June 2012 route modifications by early Q4 2012 may not significantly impact construction schedules. However, the upcoming winter weather could stall the start of pending route modifications until Q1 2013. We have received commitments from CAIs for the first 5 wireless links and identified the next 7. During the next quarter wireless equipment and installation will begin for links not pending route modification approvals. We have purchased CAI and core network equipment and are in the process of programming. Installation will begin in Q4 2012. We are actively negotiating with 22 leased and last mile providers and anticipate finalizing partner agreements with wholesale and last mile providers in addition to IRUs for portions of the network. Several of these agreements are in their final stages. | Northern Illinois University, Inc. | 1) Incumbent providers have increased target marketing aggressiveness to sign up BTOP project CAIs in advance of our efforts. This has resulted in CAIs signing long term contracts with other providers in the past few months. This recent activity from incumbent providers may inhibit our ability to sign up anchor institutions. We have initiated extensive outreach campaigns to provide an update on the project and anticipated build plans. As of 9/30/2012, we have received letters of intent from 72% of our CAIs. 2) A portion of the project region may require greater than anticipated depths for duct and fiber installation. We have submitted a route modification request to address this portion of the project. We are also working with the County to redesign the original route as an alternative to the route modification. 3) FONSI. The project's environmental assessment was submitted to NTIA on 2/7/2011. The FONSI was received on 5/8/2011. This three month period delayed construction start and will have an impact on progress in the next few quarters. Despite the delay in clearance to begin construction, we anticipate overcoming progress lost within the next two quarters and reaching the overall project target during the grant period. 4) Expenditures. Because the progress reported in this report is based on federal draw down of funds, there will be more activities than federal dollars spent during the report period. We are working with subrecipients and contractors to ensure ti | Route modifications submitted in June 2012 are still pending NTIA approval. These pending route modifications have had a significant impact on actual construction progress. If approved in early Q4 2012, the construction schedule will not be significantly impacted. If route modification approval is delayed well into Q4 2012, winter weather will stall the start of these final segments into Q1 2013. | TRUE
NT10BIX5570144 | 2012 | Q4 | Q4 - 2012 | The Broadband Technology Opportunities program (BTOP) is intended to accelerate broadband deployment in unserved and underserved areas, supporting strategic institutions that are likely to create jobs or provide significant public benefits. The Northern Illinois University BTOP team has been working on or completed the following: ï· Completed final engineering design for 99% of the planned route representing over 600 miles ï· Received permits for 94% of the planned route representing over 580 miles ï· Completed duct installation for 87% of the new construction portion of the project totaling 537 miles ï· Completed fiber installation for 77% of the new construction portion of the project totaling 473 miles ï· Secured commitments from 80% of CAIs ï· Completed lateral building entrances and fiber installation connecting 173 CAIs ï· The technical design is complete for 8 wireless segments, 2 of which are currently being installed ï· Core/Distribution sites have been selected and plans for deployment are in progress. | 473 | 203 | 0 | 0 | 473 | 0 | 0 | 0 | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. At 12/31/2012, 99% of the network is designed and 94% permitted. Over 537 miles of conduit have been installed and 473 miles of fiber blown. Lateral terminations connecting 173 CAIs have been completed. CAI and core equipment has been purchased and planning for installation initiated. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Leased miles were secured for a majority of the planned routes. The final segment of leased miles will be executed in the next two quarters. | no variance | no variance | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. At 12/31/2012, 99% of the network is designed and 94% permitted. Over 537 miles of conduit have been installed and 473 miles of fiber blown. Lateral terminations connecting 173 CAIs have been completed. CAI and core equipment has been purchased and planning for installation initiated. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Five wireless links have been designed and easement agreements for towers are in progress. Another 7 are being designed and easement agreements in progress. Most wireless locations were revised from the original EA and are still going through the route modification process. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Tower easement agreements are in progress and most were executed during 2012. Most wireless locations were revised from the original EA and are still going through the route modification process. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Most interconnection points have been identified and agreements are in process for many. We anticipate solidifying all interconnection points during the next two quarters. | 0 | 22 | 0 | Negotiations are in progress and several are in the final stages. We anticipate receiving a minimum of 5 executed agreements in Q1 2013. | Wholesale services are being developed and a plan completed by Q1 2013. | Illinois Fiber Resources Group NFP (iFiber) - sub recipient will operate the entire network. Contact: John Lewis, Chairman (815) 753-0936 jlewis@niu.edu | 0 | 0 | 0 | 0 | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Tiers will be available once agreements are finalized. | 173 | 0 | 173 | 2 | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. To date, the project has connected 173 CAIs. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. To date, the project has connected 173 CAIs. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. To date, the project has connected 173 CAIs. | 1 Gbps for 461 CAIs and 100 Mbps for 72 CAIs | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Contractors have blown 473 miles of fiber into 537 miles of conduit through the end of this quarter. By the end of the next quarter we anticipate completing all available miles of new conduit installation and new fiber blown. We estimate deploying an additional 20 miles of conduit and fiber during Q1 2013. Approximately 33 miles of intra municipal route changes are pending NTIA review/approval. An additional 12 miles of fiber route modifications submitted in June 2012 are pending NTIA review/approval. Over 150 CAI locations are pending NTIA route modification review and approval. NTIA approval on these route modifications in early Q1 2013 may not significantly impact construction schedules. However, winter weather could stall the start of pending route modifications until late Q1 2013. If route modifications are approved during the quarter, we anticipate connecting 125 CAI locations. We are actively negotiating with 22 leased and last mile providers and anticipate finalizing partner agreements with wholesale and last mile providers in addition to IRUs for portions of the network. We anticipate having 4 executed agreements in place by the end of next quarter. | Northern Illinois University, Inc. | 1) Incumbent providers have increased target marketing aggressiveness to sign up BTOP project CAIs in advance of our efforts. This has resulted in CAIs signing long term contracts with other providers in the past few months. This recent activity from incumbent providers may inhibit our ability to sign up anchor institutions. We have initiated extensive outreach campaigns to provide an update on the project and anticipated build plans. 2) A portion of the project region may require greater than anticipated depths for duct and fiber installation. We submitted a route modification request to address this portion of the project in June 2012 which was still pending approval in September at which time we proceeded with the original route to maintain construction schedules, despite the greater than anticipated depths. 3) FONSI. The project's environmental assessment was submitted to NTIA on 2/7/2011. The FONSI was received on 5/8/2011. This three month period delayed construction start and will have an impact on progress in the next few quarters. Despite the delay in clearance to begin construction, we anticipate overcoming progress lost within the next two quarters and reaching the overall project target during the grant period. 4) Expenditures. Because the progress reported in this report is based on federal draw down of funds, there will be more activities than federal dollars spent during the report period. We are working with subrecipients and contractors to ensure t | Route modifications submitted in June 2012 are still pending NTIA approval. These pending route modifications have had an impact on actual construction progress. If approved in early Q1 2013, the construction schedule will not be significantly impacted. NTIA approval required for intra-municipal routes is delaying completion of an additional 33 miles and impacts lateral construction for over 150 CAI locations. If approved in early Q1 2013, the construction schedule will not be significantly impacted. | TRUE
NT10BIX5570144 | 2013 | Q1 | Q1 - 2013 | The Broadband Technology Opportunities program (BTOP) is intended to accelerate broadband deployment in unserved and underserved areas, supporting strategic institutions that are likely to create jobs or provide significant public benefits. The Northern Illinois University BTOP team has been working on or completed the following: ï· Completed final engineering design for 100% of the planned route representing 612 miles ï· Received permits for 97% of the planned route representing 594 miles ï· Completed duct installation for 90% of the new construction portion of the project totaling 546 miles ï· Completed fiber installation for 85% of the new construction portion of the project totaling 516 miles ï· Secured commitments from 85% of CAIs, outreach efforts continue to finalized commitments from all CAIs ï· Completed lateral building entrances and fiber installation connecting 184 CAIs ï· The technical design is complete for 8 wireless segments, 2 of which are currently being installed ï· Core/Distribution sites have been selected and plans for deployment are in progress ï· Network testing continues as segments are completed ï· Negotiations are in progress with 22 last mile providers and several are in the final stages of completion | 516 | 203 | 0 | 0 | 516 | 0 | 0 | 0 | Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 3/31/2013, over 546 miles of conduit have been installed and 516 miles of fiber blown. Lateral terminations connecting 184 CAIs have been completed. The remaining portion of work will be completed once route modifications have been approved. | Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. Leased miles were secured for a majority of the planned routes. The final segment of leased miles will be executed in the next two quarters. | no variance | no variance | Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. At 3/31/2013, over 546 miles of conduit have been installed and 516 miles of fiber blown. Lateral terminations connecting 184 CAIs have been completed. The remaining portion of work will be completed once route modifications have been approved. | Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. Five wireless links have been designed and easement agreements for towers are in progress. Another 7 are being designed and easement agreements in progress. Most wireless locations were revised from the original EA. Modifications were submitted to NTIA in June 2012 but are still pending resubmission to NTIA. | Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. Tower easement agreements are in progress and most were executed during 2012. Most wireless locations were revised from the original EA. Modifications were submitted to NTIA in June 2012 but are still pending resubmission to NTIA. | Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. According to full project quarters, there is less variance from the baseline plan. Most interconnection points have been identified and agreements are in place for most. Most if not all of the core network and portions of the distribution network will be lit Q2 2013 pending completion of routes currently waiting for NTIA route modification approval. | 0 | 22 | 0 | Negotiations are in progress and several are in the final stages. We anticipate receiving a minimum of 5 executed agreements in Q2 2013. | Wholesale services are being developed and a plan completed by Q2 2013. | Illinois Fiber Resources Group NFP (iFiber) - sub recipient will operate the entire network. Contact: John Lewis, Chairman (815) 753-0936 jlewis@niu.edu | 0 | 0 | 0 | 0 | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. Negotiations are in progress with 22 broadband wholesalers and/or last mile providers. There is significant increase in interest from wholesalers and last mile providers. | There is no information to report for subscriber services in Q1 2013. | 184 | 0 | 184 | 2 | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. | Variance is due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. According to full project quarters, there is less variance from the baseline plan. | 1 Gbps for 461 CAIs and 100 Mbps for 72 CAIs | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | Contractors have blown 516 miles of fiber into 546 miles of conduit through the end of this quarter. By the end of the next quarter we anticipate completing all available miles of new conduit installation and new fiber blown. Approximately 33 miles of intra municipal route changes are pending NTIA review/approval. An additional 12 miles of fiber route modifications submitted in June 2012 are pending NTIA review/approval. Over 150 CAI locations are pending NTIA route modification review and approval. NTIA approval on these route modifications in early Q2 2013 may not significantly impact construction schedules. If route modifications are approved during the quarter, we anticipate connecting 125 CAI locations. We are actively negotiating with 22 leased and last mile providers and anticipate finalizing partner agreements with wholesale and last mile providers in addition to IRUs for portions of the network. We anticipate having 5 executed agreements in place during the next quarter, two of which will be signed in April 2013. | Northern Illinois University, Inc. | 1) Incumbent providers have increased target marketing aggressiveness to sign up BTOP project CAIs in advance of our efforts. This has resulted in CAIs signing long term contracts with other providers in the past few months. This recent activity from incumbent providers may inhibit our ability to sign up anchor institutions. We have initiated extensive outreach campaigns to provide an update on the project and anticipated build plans. 2) A portion of the project region requires greater than anticipated depths for duct and fiber installation. We submitted a route modification request to address this portion of the project in June 2012 which was still pending approval in September at which time we proceeded with the original route to maintain construction schedules, despite the greater than anticipated depths. 3) FONSI. The project's environmental assessment was submitted to NTIA on 2/7/2011. The FONSI was received on 5/8/2011. This three month period delayed construction start and will have an impact on progress. 4) Expenditures. Because the progress reported in this report is based on federal draw down of funds, there will be more activities than federal dollars spent during the report period. We are working with subrecipients and contractors to ensure timely receipt of invoices for expenditures on the project. Additionally, the original baseline report was developed based on project progress not just expenditures. Actual expenditures can lag project progress by as | Route modifications submitted in June 2012 are still pending NTIA approval. These pending route modifications have had an impact on actual construction progress. If approved in early Q2 2013, the construction schedule may not be significantly impacted. NTIA approval required for intra-municipal routes is delaying completion of an additional 33 miles and impacts lateral construction for over 150 CAI locations. If approved in early Q2 2013, the construction schedule may not be significantly impacted. | TRUE
NT10BIX5570144 | 2013 | Q2 | Q2 - 2013 | The Broadband Technology Opportunities program (BTOP) is intended to accelerate broadband deployment in unserved and underserved areas, supporting strategic institutions that are likely to create jobs or provide significant public benefits. The Northern Illinois University BTOP team has been working on or completed the following: ï· Completed final engineering design for 100% of the planned route representing 602 miles ï· Received permits for 99% of the planned route representing 594 miles ï· Completed duct installation for 94% of the new construction portion of the project totaling 564 miles ï· Completed fiber installation for 86% of the new construction portion of the project totaling 520 miles ï· Secured commitments from 86% of an expected 463 CAIs ï· Completed lateral building entrances and fiber installation connecting 55% of the CAIs totaling 255 locations. ï· 4 of 5 core network connections were completed. 14 of 28 distribution locations were completed. The final core and most of the distribution locations will be completed during Q3 2013. ï· Completed 1 wireless link representing 8 of 38 wireless miles. A second link is spending final equipment testing. Three towers are under construction now with completions expected during next quarter. Equipment installation and testing will follow. ï· Secured 11 last-mile/wholesale provider agreements during the quarter with several more planned during the next quarter. We are currently planning and implementing provider access into the network. ï· Outreach activities include securing ISP selections from CAIs and coordinating equipment installation and lighting. | 528 | 203 | 0 | 0 | 528 | 1 | 1 | 0 | Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. Cumulatively, 520 fiber and 8 wireless miles have been completed. NTIA approval of all remaining route modifications was received during the quarter which will enable the project move forward and complete the remaining miles. Only 4 additional miles of fiber were blown during the quarter due to construction pending route modifications which left gaps in the network and therefore limited the ability to blow and test fiber. | Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. A request for additional leased miles was submitted to NTIA for approval during the quarter. | no variance | no variance | Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. Cumulatively, 520 fiber and 8 wireless miles have been completed. NTIA approval of all remaining route modifications was received during the quarter which will enable the project move forward and complete the remaining miles. Only 4 additional miles of fiber were blown during the quarter due to construction pending route modifications which left gaps in the network and therefore limited the ability to blow and test fiber. | Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. One link is completed but pending fiber installation which was on hold pending route modification approvals. NTIA approval of all remaining route modifications was received during the quarter which will enable the project move forward and complete the remaining miles. | One tower is completed. NTIA approval of all remaining route modifications was received during the quarter which will enable the project move forward and complete the remaining miles. | Variance is also due in part to pending route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 below. NTIA approval of all remaining route modifications was received during the quarter which will enable the project move forward and complete the remaining miles. | 11 | 5 | 20 | Aero Group Inc. Adam Schulz (815) 801-3388 (O) (815) 801-9951; or Todd Fransen (sales) (815) 757-1664 CenturyLink Cameron Parker (312) 498-0390 Frontier Communications Thomas Kuschman (815) 895-1445 Heartland Cable Steve Allen (309) 432-2075 (O) (309) 275-2018 (C) IL Century Network (ICN) www.illinois.net ISI Communications Dan Howard (630) 887-2910 (O) (630)878-1325 (C) Jo-Carroll Energy/Sand Prairie Jeff Harrelson (815) 858-2207 ext. 1336 MTCO Tina Glidewell, Sales Mgr. (309) 367-4197 off. (309) 253-8009 cell NIUNet Kevin Finley (815)753-7272 Syndeo Amit Patel US Toll Free: (855) 479-6336 Local Phone: (630) 457-4218 Urban Communications Inc. Edmund G. Urban III 1-855-243-4237 | No wholesale services are being provided. Last mile providers are charged a $600 per port fee plus 15% of revenue generated. | Illinois Fiber Resources Group NFP (iFiber) - sub recipient will operate the entire network. Contact: John Lewis, Chairman (815) 753-0936 jlewis@niu.edu | 11 | 0 | 0 | 2 | no variance | no variance | no variance | 1 Gbps for 461 CAIs and 100 Mbps for 72 CAIs | 255 | 0 | 255 | 2 | Variance is due in part to recently approved route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. | no variance | Variance is due in part to recently approved route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. | 1 Gbps for 461 CAIs and 100 Mbps for 72 CAIs | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | FALSE | N/A | During the next quarter, all remaining new fiber miles (38 miles) will have conduct installed, fiber will be blown into 75 miles of the remaining 82 miles of conduit and we will be testing those miles. We will activate the remaining core network location and most remaining distribution sites. An additional 80 CAIs will be connected. Wireless tower construction will be completed at 3 sites totaling 5 links and 22 wireless miles and we will begin installing equipment and testing links. We anticipate completing Earlville/Paw Paw, Prophetstown/Erie, and Streator/Ransom. We anticipate having and additional 5 executed last-mile provider agreements in place during the next quarter. | Northern Illinois University, Inc. | 1) Incumbent providers have increased target marketing aggressiveness to sign up BTOP project CAIs in advance of our efforts. This has resulted in CAIs signing long term contracts with other providers in the past few months. This recent activity from incumbent providers may inhibit our ability to sign up anchor institutions. We have initiated extensive outreach campaigns to provide an update on the project and anticipated build plans. 2) A portion of the project region requires greater than anticipated depths for duct and fiber installation. We submitted a route modification request to address this portion of the project in June 2012 which was still pending approval in September at which time we proceeded with the original route to maintain construction schedules, despite the greater than anticipated depths. 3) FONSI. The project's environmental assessment was submitted to NTIA on 2/7/2011. The FONSI was received on 5/8/2011. This three month period delayed construction start and will have an impact on progress. 4) Expenditures. Because the progress reported in this report is based on federal draw down of funds, there will be more activities than federal dollars spent during the report period. We are working with subrecipients and contractors to ensure timely receipt of invoices for expenditures on the project. Additionally, the original baseline report was developed based on project progress not just expenditures. Actual expenditures can lag project progress by as | Contractors have blown 520 miles of fiber into 564 miles of conduit through the end of this quarter. NTIA approved the remaining route modification during Q2 2013 which will enable completion of the remaining miles by the end of Q3 2013. Once the fiber is completed, we can finish core and distribution equipment deployment as well as CAI installations. We will be requesting an extension of time thru 12/31/13 to complete the remainder of the project. We have contracts with 11 last mile providers and are actively negotiating with another 5 leased and last mile providers. We anticipate having 5 executed agreements in place during the next quarter. | TRUE
NT10BIX5570144 | 2013 | Q3 | Q3 - 2013 | ARRA 9/30/2013 Project Description/Activities - The Broadband Technology Opportunities program (BTOP) is intended to accelerate broadband deployment in unserved and underserved areas, supporting strategic institutions that are likely to create jobs or provide significant public benefits. The Northern Illinois University BTOP team has been working on or completed the following: ï· Completed final engineering design for 100% of the planned route representing 601 miles ï· Received permits for 100% of the planned route representing 601 miles ï· Completed duct installation for 99.8% of the new construction portion of the project totaling 600 miles ï· Completed fiber installation for 99.8% of the new construction portion of the project totaling 600 miles ï· Secured commitments from 86% of CAIs ï· Completed lateral building entrances and fiber installation connecting 379 CAIs ï· 4 of 5 core network connections are completed and 14 of 28 distribution locations are completed. ï· 13 wireless links totaling 38 miles are completed including 7 new towers. ï· Outreach efforts continue as communities and CAIs are scheduled for equipment installation and transition to the network. Where applicable, outreach also continues to solidify ISP providers for CAIs that have not yet selected their provider. ï· Negotiations continue with an additional 5 last mile providers interested in providing services to CAIs. | 638 | 308 | 0 | 0 | 638 | 13 | 7 | 4 | At 9/30/2013, 100% of the network is designed and 100% permitted. 600 of 601 fiber miles have been installed and blown. The last mile will be completed in the next quarter. | At 9/30/2013, 308 of 315 leased miles have been secured. One remaining IRU is pending. | no variance | no variance | At 9/30/2013, 100% of the network is designed and 100% permitted. 600 of 601 fiber miles have been installed and blown. The last mile will be completed in the next quarter. | no variance | no variance | The final core location will be active in the next quarter. | 11 | 5 | 20 | Aero Group Inc. CenturyLink Frontier Communications Heartland Cable IL Century Network (ICN) ISI Communications Jo-Carroll Energy/Sand Prairie MTCO NIUNet Syndeo Urban Communications Inc. | [REDACTED] | Illinois Fiber Resources Group NFP (iFiber) - sub recipient will operate the entire network. Contact: John Lewis, Chairman (815) 753-0936 jlewis@niu.edu | 11 | 0 | 0 | 1 | no variance | no variance | no variance | 1Gbps - 11 providers | 379 | 0 | 379 | 2 | Variance is due in part to recently approved route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. | no variance | Variance is due in part to recently approved route modifications, permitting, the delayed FONSI, and Shortened First Quarter issue noted in Q3 above. | 1 Gbps for 319 CAIs and 80 Mbps for 60 CAIs | 0 | 0 | 0 | 0 | 0 | no variance | no variance | no variance | no variance | no variance | 0 | 0 | 0 | 0 | 0 | no variance | no variance | no variance | no variance | no variance | N/A | FALSE | N/A | During the next and final quarter we will complete the last mile of duct and fiber, complete all network testing and turnover, and connect the remaining CAIs, approximately 109. We will complete the remaining core site and the remaining 14 of 28 distribution sites. We anticipate executing an additional 3 last mile provider sites during the next quarter. | Northern Illinois University, Inc. | 1) Incumbent providers have increased target marketing aggressiveness to sign up BTOP project CAIs in advance of our efforts. This has resulted in CAIs signing long term contracts with other providers in the past few months. This recent activity from incumbent providers may inhibit our ability to sign up anchor institutions. We have initiated extensive outreach campaigns to provide an update on the project and anticipated build plans. 2) A portion of the project region requires greater than anticipated depths for duct and fiber installation. We submitted a route modification request to address this portion of the project in June 2012 which was still pending approval in September at which time we proceeded with the original route to maintain construction schedules, despite the greater than anticipated depths. 3) FONSI. The project's environmental assessment was submitted to NTIA on 2/7/2011. The FONSI was received on 5/8/2011. This three month period delayed construction start and will have an impact on progress. 4) Expenditures. Because the progress reported in this report is based on federal draw down of funds, there will be more activities than federal dollars spent during the report period. We are working with subrecipients and contractors to ensure timely receipt of invoices for expenditures on the project. Additionally, the original baseline report was developed based on project progress not just expenditures. Actual expenditures can lag project progress by as | None are anticipated. | TRUE
NT10BIX5570144 | 2013 | Q4 | Q4 - 2013 | Northern Illinois University and Illinois Fiber Resources Group, NFP successfully completed the NTIA BTOP project constructing 601 new miles of fiber optic cable and 13 wireless links totaling 38 wireless miles, as well as securing 307 leased fiber miles. The infrastructure supporting the network includes 5 core network sites in addition to 28 distribution sites. The 946 mile network spans across a 9-county region in northwest Illinois serving over three dozen rural, unserved and underserved areas. With the completion of the project, 487 Community Anchor Institutions now have access to 21st century, high capacity broadband. Serving those CAIs, are 12 Internet Service Providers, providing a vast array of services. | 639 | 307 | 0 | 0 | 639 | 13 | 4 | 5 | no variance | no variance | no variance | no variance | no variance | no variance | The project was able to utilize existing towers instead of building new towers. Additionally, a few locations requiring a new tower did not participate due to facility closures. | no variance | 12 | 0 | 20 | Aero Group Inc. CenturyLink Frontier Communications Heartland Cable Hi-Hart Inc. IL Century Network (ICN) ISI Communications Jo-Carroll Energy/Sand Prairie MTCO NIUNet Syndeo Urban Communications Inc. | We are providing transport services to ISPs and other content providers at a cost of $500 per month per/port, plus 15% of monthly gross revenues earned providing network access and services to Community Anchor Institutions. We are providing dark fiber at $750 per strand mile. | Illinois Fiber Resources Group NFP (iFiber) - sub recipient will operate the network. Contact: John Lewis, Chairman (815) 753-0936 jlewis@niu.edu | 12 | 0 | 0 | 1 | no variance | no variance | no variance | 1Gbps - 11 providers | 487 | 0 | 487 | 2 | no variance | no variance | no variance | 1 Gbps for 402 CAIs and 80 Mbps for 85 CAIs | 0 | 0 | 0 | 0 | 0 | no variance | no variance | no variance | no variance | no variance | 0 | 0 | 0 | 0 | 0 | no variance | no variance | no variance | no variance | no variance | N/A | FALSE | N/A | N/A | Northern Illinois University, Inc. | N/A | N/A | TRUE
NT10BIX5570145 | 2010 | Q4 | Q4 - 2010 | Environmental assessment â€“ We have filed the required summary items to get this project started. We have received letters from the Ute Indian Tribes Natural Resource department, Fish and Wildlife Biologist, Cultural Rights, and Tribal EPA. None of these agency's believe this project will cause any detrimental environmental impacts. We have submitted this information to Bureau of Indian Affairs Environmental specialist and he also has indicated that there will be no significant impact on the environment. Thus, we believe the Environmental assessment is well on is way to being completed. Hiring a project Manager â€“ The job description has been written and posted with the Ute Tribe HR department. We have several good candidates and will fill this position early in the next quarter. Route Planning and verification â€“ As we get feedback from the ongoing environmental assessment we will be working with engineers to discuss any alternative routes or changes to routes that may be necessary. We do not for see any major changes. We are working in conjunction with engineers, and the Tribe's Environmental team as we finalize the route plan to make sure we comply with any and all environmental assessment findings. We feel this will reduce any delay should route changes be necessary. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A Still waiting on EA before beginning build. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We will be providing 100 Mbytes fiber data connections to all CAI and 10 Mbytes 802.11 wireless connections to households. | FALSE | N/A | ARRA required signs will be procured and posted. EA special award condition should be completed. Route and network design should be finalized (baring any changes due to the EA.) Equipment Procurement process should start. Contractors will be selected for fiber build out. Equipment will be installed for first leg of project. Network testing, especially pre-testing will be able to be started. | Ute Indian Tribe | The environmental assessment has proven to more work than anticipated, simply because none of the involved Tribal parties believed that the requirement was necessary. However, once that issue was resolved the process has moved right along. | Contractor's will have to comply not only with federal guidelines but also with the Ute Tribe's UTERO commission guidelines, these guidelines leave a very small population of potential contractors. We are currently working with the UTERO to make sure this will not be an issue. | TRUE
NT10BIX5570145 | 2011 | Q1 | Q1 - 2011 | Environmental assessment â€“ We have been awarded a finding of no significant impact for our Environmental assessment special award condition. This is the last Special Award Condition, thus, all have been satisfied. This was a big accomplishment in this quarter and will allow us to move forward with this project. Another significant accomplishments in this quarter is the hiring of a project manager. She will begin coming up to speed with the project and will start to coordinate the bidding process, oversee the bid selections, and make sure all the contracts are in place. She will also begin the product request for quote process and product procurements. As construction begins she will also help manage the construction phase, and provide other necessary project management services. Route Planning and verification â€“ We have surveyed, requested a route change, and finalized the route. This route has been found to be clear of any environmental issues, however; we will remain in close contact with the tribal division of natural resources and cultural rights departments. The route has been cleared with the BIA as well as with the UTE Tribe, we have also presented this route to other vendors (gas, electric company, water, sewer, and phone companies). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In the process of selecting contractor (s) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We will be providing 100 Mbytes fiber data connections to all CAI and 10 Mbytes 802.11 wireless connections to households. | FALSE | N/A | ARRA required signs will be purchased and posted. Contractor bid process and selection. Construction should begin. Project Web site will be running. Wireless portion will be started. Equipment Procurement RFQ should be completed and posted. | Ute Indian Tribe | Even though the numbers do not reflect significant change for this quarter we feel we have made positive progress. Getting the EA SAC completed took more time than originally planned. Furthermore, in order to complete the EA we had to do a route change, although this made it possible for the EA to be completed, it took time away from some of the other portions of this project. Projections were made based on assumptions that the EA would not be as significant hurdle as it proved to be. Without all of our SAC conditions completed we were not able to really begin the project. We do not feel, however, that at this time it requires us to change our projects further out, as we believe we can get back on track by the end of next quarter. | Contractor's will have to comply not only with federal guidelines but also with the Ute Tribe's UTERO commission guidelines, these guidelines leave a very small population of potential contractors. We are currently working with the UTERO to make sure this will not be an issue. | TRUE
NT10BIX5570145 | 2011 | Q2 | Q2 - 2011 | Environmental Assessment - Complete Project Manager - Hired Route planning and verification has been completed, UDOT has issued the UTE Tribe a preliminary Statewide Utility License Agreement, which will be solidified once a contractor has been selected and that contractor's application is approved. Our Web-Site is operational and the main RFP's have been completed, approved, and posted. This should allow construction to begin in this next upcoming quarter. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Will be caught up to the baseline by the end of the 4th quarter 2011. We have not currently started to dig, we expect this to happen in Q4. We originally had planned to dig a portion of the project this year and a portion next year; however, once we start to dig we will dig the entire project. This will allow us to catch up to our time line. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | Will be caught up to the projected baseline in the 4th quarter. | Will be caught up to the baseline in 4th quarter 2011. | 100 MB Fiber=0 New subscribers and 10 MB Wireless =0 new subscribers. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | We will be providing 100 MBytes fiber data connections to all Community Anchor Institutes and 10 MBytes 802.11 wireless connections to households. | FALSE | N/A | Final Equipment Procurement and Request for Proposal's (RFPs) should be completed and posted. A Contractor should be selected and construction will begin. | Ute Indian Tribe | Percent of completing is base on overall money spent, the first part of this project has consumed a lot of time, but hasn't yet accrued a lot of costs. This will change as we start to buy equipment. Next quarter's numbers should be a better reflection of where we are at on this project. | Getting selections for new hires and contractors approved by tribal leaders. Contractor's will have to comply not only with federal guidelines but also with the Ute Tribe's UTERO commission guidelines, these guidelines leave a very small population of potential contractors. We are currently working with the UTERO to make sure this will not be an issue. | TRUE
NT10BIX5570145 | 2011 | Q3 | Q3 - 2011 | QRT 3 2011- We were able to post several requests for quotes and requests for proposals on our Ute Tribe BTOP web-site (btop.utetribe.com). We had good response and during this quarter have not only posted proposals for the main fiber loop and wireless portions of our project, we have also evaluated those proposals and began discussions with the selected contractors. We were able to lock down the price and have received delivery of the the fiber for the entire project. Because of the fiber shortage this as a significant accomplishment. We have also acquired a significant portion (roughly 60%) of networking equipment as well as (100%) of the wireless equipment that we will be installing during the winter months and will expect most of the network to be well underway by spring. We have written and posted a draft for construction of our private side lateral sections (RFP 2011-250-102) as well as the Wireless install portion (RFP 2011-250-103) for our public side network. We filled the position of network wireless manager during this quarter. He has been coming up to speed on the project and has started to interact with the CIA's that will benefit the most from the wireless access services we will be able to provide; the Uintah and Ouray Police department, the Emergency Response Units, and the Conservations officers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | We will be caught up to the baseline by the end of the 4th quarter 2011 or early spring. We have not currently started to dig, we expect this to begin in Q4. We originally had planned to dig a portion of the project this year and a portion next year; however, once we start to dig we will dig the entire project. This is still our plan and this will bring us up to the numbers in our time line. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | N/A | We will be connecting 9 CIA in this next quarter, maybe more. | N/A | 100 MB Fiber=0 New subscribers and 10 MB Wireless=0 new subscribers | 0 | 0 | 0 | 0 | 0 | We are expecting to have the wireless network build complete during this next quarter, and then we will start to connect households. We should get some during the 4th quarter but we expect the majority of them in the spring time. | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | Most of the business are located in what will be the last leg of our fiber, so we are not expecting to bring them on board until spring 2012. | N/A | N/A | N/A | N/A | We will be providing 100 MBytes fiber data connection to all Community Anchor Institutes and 10 MBytes 802.11 wireless connections to households. | FALSE | N/A | The projects RFP for the fiber is completed and a contractor has been selected. We will be signing a contract during the 4Q on the fiber RFP and the Wireless RFP. We have ground breaking for fiber scheduled in Q4 and wireless construction will also begin. | Ute Indian Tribe | Everyone involved in this project is very anxious to get this project up and operational as soon as possible, because of this we submitted a very aggressive project baseline, anticipating we could finish the project in two years instead of three. However, we had not planned on it taking 2 quarters to get the EA finalized. Because of our aggressive time line we are a couple quarters behind our projections, but are moving fast in catching up. We fully expect, weather permitting to be completely back on track by spring of 2012. | We have the contractors selected for the fiber and the wireless portion of the project We feel that the project will move forward and the only obstacle that may come up is the weather. Utah has extreme weather, and Fort Duchesne is know to have some of the coldest weather in Utah, depending on the year this may keep us from catching up, but will not, over the long run, put this project in any significant jeopardy. | TRUE
NT10BIX5570145 | 2011 | Q4 | Q4 - 2011 | QRT 4 - 2011 We have purchased most of the network hardware had have began the testing, configuration, and implementation for the new network. We have selected our main contractor and are under contract negotiations for the main fiber loop of this project. We have progressed with our plans to construct some of the lateral fiber runs in house, and have connected 9 Community Anchor Institutions to the fiber network during this quarter. We have also constructed the majority of the wireless network and should begin to offer our end-mile services during the next quarter. | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | While we have not yet begun to dig the main fiber loop we have been able to connect 9 CAI (lateral connections to the fiber of leg 1). We have also began to work on the laterals on other parts of the project so that as the main fiber goes by we will be in a position to connect them with out further delays. | N/A | N/A | N/A | Lateral fiber on Leg 1. | N/A | N/A | We have contracted and set up our interconnect point for this project. | 0 | 0 | 0 | Currently the Tribe will be the only entity to act as a last mile provider. However, we hoping the by building this project that we can encourage other participation and would welcome other possibilities. | 100 Mbs fiber connection for VOIP, Data, and Internet connectivity. - (1 Service plan) $400 per month per Connection 10 Mbs 802.11 wireless connectivity for internet access. - No Charge | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 7 | 7 | 0 | 7 | 100 Mbs Fiber connection with 20 Mbs uplink feed to Internet. | We connected the 7 Community Anchor Institutes this quarter, all of which are receiving new services. | N/A | 100 MB Fiber=7 New subscribers 10 MB Wireless=0 new subscribers | 0 | 0 | 0 | 0 | 0 | We have concluded the installation of the wireless network, but have not yet offered services to the households that we have passed. Services should made available next quarter. | Services will be offered next quarter. | Services will be offered next quarter. | Services will be offered next quarter. | 10 Mbs 802.11 Wireless (Only one service offering is available and it will be the same for all households passed). | 2 | 2 | 2 | 0 | 2 | We have passed 2 businesses and connected 2. | We are currently providing services to 2 subscribers. | Both subscribers have new access. | N/A | 100 MB Fiber=2 New subscribers 10 MB Wireless=0 new subscribers | We will be providing 100 Mbs fiber connection to all Community Anchor Institutes and 10 Mbs wireless connection to all households. | FALSE | N/A | We are planning to get the wireless network connected and have a goal to connect 30 percent of available households in this quarter. This means finalizing the wireless network build, testing, and deploying the infrastructure. We are projecting that we will connect 1 new network mile with 6 CAI. We do not project any new signed agreements with broadband wholesalers or last mile providers. We hope to have most of the network design and implementation completed during this quarter. | Ute Indian Tribe | We have made good progress in getting the network equipment deployed, with the majority of the deployment being on the 802.11 last mile wireless portion of the project. We also did not anticipate the difficulty in ironing out all the minor details of the contract. Staying in-line with the Davis Bacon requirements, as well as the stipulations in the NOFA have proven more difficult than expected. However, we believe we have all those issues resolved and can now begin, weather permitting. | Utah has extreme weather, and Fort Duchesne is known to have some of the most extreme in Utah. Depending on the year this may keep us from digging until late spring, but will not cause any significant unexpected delays. | TRUE
NT10BIX5570145 | 2012 | Q1 | Q1 - 2012 | QRT 1- 2012 We have purchased most of the network hardware and have almost completed the testing, configuration, and implementation for the new network. We have selected our main contractor and have completed the necessary paperwork and obtained the paperwork for the rights-of-way and tribal council resolutions. There should be no other hurdles in front of us, so as soon as the weather permits we will be digging the main fiber loop portion of this project. We were unable to dig, which precluded us from connecting any more CAI during this quarter; however, this was an expected potential delay. | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | We have not started the dig on the main fiber loop due to weather. We are continuing to work on the laterals on other parts of the project so that as the main fiber pass we wil be able to connect them. | n/a | n/a | n/a | Lateral fiber on Leg 1. | n/a | n/a | We have contracted and set up our interconnect point for tyhis project | 0 | 0 | 0 | Currently the Tribe will be the only entity to act as a last mile provider. However, we are hoping that by building this project that we can encourage others to participate and would welcome other possibilities. | 100 Mbs fiber connection for VOIP, Data, and Internet connectivity. 10 Mbs 802.11 wireless connectivity for internet access. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 7 | 7 | 0 | 7 | N/A | Currently 9 CAI, no new ones this quarter. | N/A | 100 MB Fiber=9 New subscribers 10 MB Wireless=0 new subscribers | 180 | 0 | 0 | 0 | 1 | We have concluded the installation of the wireless network, but have not yet offered services to the households that we have passed. Services will be offered next quarter. | Services will be offered next quarter. | Services will be offered next quarter. | Services will be offered next quarter. | 10 Mbs 802.11 Wireless (Only one service offering is available and it will be the same for all households passed). | 2 | 2 | 2 | 0 | 2 | We have passed 2 businesses and connected 2. | We are currently providing services to 2 subscribers. | Both Subscribers have new access | N/A | 100 MB Fiber=2 New subscribers 10 MB Wireless=0 New subscribers | We will be providing 100 Mbs fiber connection to all Community Anchor Institutes and 10 Mbs wireless connection to all households. | FALSE | N/A | We should be close to 70 percent complete with the main fiber loop by the end of this next quarter. This will include, but is not limited to the launch of the wireless network, as well as the main fiber loop. We should also have selected the method that we are going to use for the lateral builds and be able to connect 9 more CAI to the main fiber network. Of course for this to happen we will also have the network build mostly complete with the infrastructure equipment in place and functional to accommodate the new connections. We plan to have 4 new network miles deployed We do not plan to have any additional broadband wholesalers or last mile providers during this quarter. | Ute Indian Tribe | N/A | We don't for see any major set backs for this quarter. In fact from this point forward we see the project moving with good progress. | TRUE
NT10BIX5570145 | 2012 | Q2 | Q2 - 2012 | QRT 2- 2012 We have purchased most of the network hardware and continue the testing, configuration, and implementation for the new network. The Main Loop is progressing on schedule and our Lateral contractor is in the staging process, so with the weather cooperating and with all the permits are in place we will be digging the lateral portion of this project. | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | We have construction continuing on the mail fiber loop, conduit is being installed and readied for the fiber to be blown. | N/A | N/A | N/A | Lateral fiber on Leg 1. | N/A | N/A | We have contracted and set up our interconnect point for this project | 0 | 0 | 0 | Currently the Tribe will be the only entity to act as a last mile provider. However, we are hoping that by building this project that we can encourage others to participate and would welcome other possibilities. | 100 Mbs fiber connection for VOIP, Data, and Internet connectivity. 10 Mbs 802.11 wireless connectivity for internet access. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 7 | 7 | 0 | 7 | N/A | Currently 7 CAI, no new ones this quarter. | N/A | 100 MB Fiber=7 New subscribers 10 MB Wireless=0 new subscribers | 180 | 0 | 0 | 0 | 1 | We have concluded the installation of the wireless network, but have not yet offered services to the households that we have passed. Services will be offered next quarter. | Services were made available this quarter. | Services were made available this quater. | Services were mad available this quarter. | 10 Mbs 802.11 Wireless (Only one service offering is available and it will be the same for all households passed). | 2 | 2 | 2 | 0 | 2 | We have passed 2 businesses and connected 2. | We are currently providing services to 2 subscribers. | Both Subscribers have new access | N/A | 100 MB Fiber=2 New subscribers 10 MB Wireless=0 New subscribers | We will be providing 100 Mbs fiber connection to all Community Anchor Institutes and 10 Mbs wireless connection to all households. | FALSE | N/A | We should be close to 83 percent complete with the main fiber loop by the end of this next quarter. This will include, but is not limited to the launch of the wireless network, as well as the main fiber loop. We should also have selected the method that we are going to use for the lateral builds and be able to connect more CAI to the main fiber network. Of course for this to happen we will also have the network build mostly complete with the infrastructure equipment in place and functional to accommodate the new connections. We plan to have 4 new network miles deployed We do not plan to have any additional broadband wholesalers or last mile providers during this quarter. | Ute Indian Tribe | N/A | We don't for see any major set backs for this quarter. In fact from this point forward we see the project moving with good progress. | TRUE
NT10BIX5570145 | 2012 | Q3 | Q3 - 2012 | QRT 3- 2012 We have purchased the network hardware and continue the testing, configuration, and implementation for the new network. The Main Loop is progressing on schedule the digging, trenching, conduit placement and fiber blowing are complete. The lateral contractor is in the process of digging, trenching and laying of the conduit, the fiberblowing is partially complete, so with the weather cooperating we are on schedule. | 8 | 0 | 0 | 0 | 8 | 150 | 0 | 1 | We have construction completed on the main fiber loop; that is, the main fiber loop conduit is installed and all the fiber is blown, but not terminated. The laterals are dug and the fiber is blown, but not terminated. | n/a | n/a | n/a | We have construction completed on the main fiber loop; that is, the main fiber loop conduit is installed and all the fiber is blown, but not terminated. The laterals are dug and the fiber is blown, but not terminated. | wireless is up and running | N/a | We have contracted and set up our interconnect point for this project | 0 | 0 | 0 | Currently the Tribe will be the only entity to act as a last mile provider. However, we are hoping that by building this project that we can encourage others to participate and would welcome other possibilities. | 100 Mbs fiber connection for VOIP, Data, and Internet connectivity. 10 Mbs 802.11 wireless connectivity for internet access. | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 7 | 7 | 0 | 7 | n/a | Currently 7 CAI, no new ones this quarter | n/a | 100 MB Fiber=7 New subscribers 10 MB Wireless=0 new subscribers | 180 | 150 | 150 | 0 | 1 | We have concluded the installation of the wireless network, and have 120 services to the households that we have passed. | Services were made available this quarter. | Services were mad available this quarter | Services were mad available this quarter | 10 Mbs 802.11 Wireless (Only one service offering is available and it will be the same for all households passed). | 2 | 2 | 2 | 0 | 2 | We have passed 2 businesses and connected 2. | We are currently providing services to 2 subscribers. | Both Subscribers have new access | n/a | 100 MB Fiber=2 New subscribers 10 MB Wireless=0 New subscribers | We will be providing 100 Mbs fiber connection to all Community Anchor Institutes and 10 Mbs wireless connection to all households. | FALSE | n/a | We should be close to 95 percent complete by the end of this next quarter. We plan to add 10 CAI's during this next quarter. We will be continuing to add CAI's as connections are completed. Of course for this to happen we will also have the network build mostly complete with the infrastructure equipment in place and functional to accommodate the new connections. We do not plan to have any additional broadband wholesalers or last mile providers during this quarter. | Ute Indian Tribe | n/A | We don't for see any major set backs for this quarter. | TRUE
NT10BIX5570145 | 2012 | Q4 | Q4 - 2012 | QRT 4- 2012 We spent most of our efforts on getting all of the fiber into the buildings and termination of fiber outdoors. We also spent time with network configuration, and implementation of the new network equipment. The Main Loop was completed and all the digging, trenching, conduit placement and fiber blowing is complete. The lateral digging, trenching and laying of the conduit, the fiber blowing is complete. During the 4th quarter we connected 28 new CAI's. | 9 | 0 | 0 | 0 | 9 | 150 | 0 | 1 | We have construction completed on the main fiber loop; that is, the main fiber loop conduit is installed and all the fiber is blown, but not terminated. The laterals are dug and the fiber is blown and mostly connected. | N/A | N/A | N/A | All the fiber is buried and is complete. | Wireless is up and running we still have 150 Households connected. | N/A | We only have one interconnect point for this project. | 0 | 0 | 0 | Currently the Tribe will be the only entity to act as a last mile provider. However, we are hoping that by building this project that we can encourage others to participate and would welcome other possibilities. | 100 Mbs fiber connection for VOIP, Data, and Internet connectivity. 10 Mbs 802.11 wireless connectivity for internet access. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 35 | 26 | 9 | 35 | We have connect 28 new CAI this quarter. | All new subscribers are connected using 100MB Fiber | Improved access moved from Point to Point 1024K connections to 100 MB Fiber. | 100 MB Fiber=35 subscribers 10 MB Wireless=0 new subscribers | 180 | 150 | 150 | 0 | 1 | We have mostly concluded the installation of the wireless network, and currently serving 150 households. | Services to the remaining house holds will be made available next quarter. | No new services were made available this quarter, but we have maintained 150 subscribers. | Services were made available this quarter | 10 Mbs 802.11 Wireless (Only one service offering is available and it will be the same for all households passed). | 2 | 2 | 2 | 0 | 2 | We have passed 2 businesses and connected 2. | We are currently providing services to 2 subscribers. | Both Subscribers have new access | N/A | 100 MB Fiber=2 New subscribers 10 MB Wireless=0 New subscribers | We will be providing 100 Mbs fiber connection to all Community Anchor Institutes and 10 Mbs wireless connection to all households. | FALSE | N/A | We are expecting this to be our last quarter, if not it will be close. We will be connecting the last 7 CAI and remaining businesses as well as getting the final households activated. We will also be complete payment for the invoices and be preparing for closeout. | Ute Indian Tribe | We don't for see any major set backs for this quarter. | We don't for see any major set backs for this quarter. | TRUE
NT10BIX5570145 | 2013 | Q1 | Q1 - 2013 | We finished getting the final CAI connected and the Hardware installed. We We also spent time with network configuration, and implementation of the new network equipment. | 9 | 0 | 0 | 0 | 9 | 150 | 0 | 1 | We have construction completed on the main fiber loop; the main fiber loop conduit is installed and all the fiber is blown, and terminated. The laterals are dug and the fiber is blown and connected. | N/A | N/A | N/A | All fiber is buied and complete. | Wireless is up and running we have 150 households connected. | N/A | We only hve one interconect point for this project. | 0 | 0 | 0 | Currently the Tribe will be the only entity to act as a last mile provider. However, we are hoping that by building this project that we can encourage others to participate and would welcome other possibilities. | 100 Mbs fiber connection for VOIP, Data, and Internet connectivity. 10 Mbs 802.11 wireless connectivity for internet access. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 43 | 33 | 10 | 2 | We have connected 8 new CAI this quarter. | All new subscribers are connected using 100MB Fiber | mproved access moved from Point to Point 1024K connections to 100 MB Fiber. | 100 MB Fiber=43 subscribers 10 MB Wireless=0 new subscribers | 180 | 150 | 150 | 0 | 1 | We have mostly concluded the installation of the wireless network, and currently serving 150 households. | Services to the remaining house holds will be made available next quarter. | No new services were made available this quarter, but we have maintained 150 subscribers. | Services were made available this quarter | 10 Mbs 802.11 Wireless (Only one service offering is available and it will be the same for all households passed). | 2 | 2 | 2 | 0 | 2 | We have passed 2 businesses and connected 2. | We are currently providing services to 2 subscribers. | Both Subscribers have new access | N/A | 100 MB Fiber 10 MB Wireless | We will be providing 100 Mbs fiber connection to all Community Anchor Institutes and 10 Mbs wireless connection to all households. | FALSE | N/A | Final reporting and close out. | Ute Indian Tribe | We don't for see any major set backs for this quarter. We will begin the process of final reporting. | We don't for see any major set backs for this quarter. | TRUE
NT10BIX5570145 | 2013 | Q2 | Q2 - 2013 | We finished getting all the final CAI connected and the Hardware is all installed. We also spent time with network configuration, and implementation of the new network equipment. | 9 | 0 | 0 | 0 | 9 | 180 | 0 | 1 | We have construction completed on the main fiber loop; the main fiber loop conduit is installed and all the fiber is blown, and terminated. The laterals are dug and the fiber is blown and connected. | N/A | N/A | N/A | All fiber is buried and complete | Wireless is up and running we have 180 households connected. | N/A | We only have one interconnect point for this project. | 0 | 0 | 0 | Currently the Tribe will be the only entity to act as a last mile provider. However, we are hoping that by building this project that we can encourage others to participate and would welcome other possibilities. | 100 Mbs fiber connection for VOIP, Data, and Internet connectivity. 10 Mbs 802.11 wireless connectivity for internet access. | N/A | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 43 | 33 | 10 | 2 | Complete | All new subscribers are connected using 100MB Fiber | improved access moved from Point to Point 1024K connections to 100 MB Fiber. | 100 MB Fiber=43 subscribers 10 MB Wireless=0 new subscribers | 180 | 180 | 180 | 0 | 1 | We have mostly concluded the installation of the wireless network, and currently serving 180 households. | Services to the remaining house was made available this quarter. | We connected the remaining wireless households. | Services were made available this quarter | 10 Mbs 802.11 Wireless (Only one service offering is available and it will be the same for all households passed). | 2 | 2 | 2 | 0 | 2 | We have passed 2 businesses and connected 2. | We are currently providing services to 2 subscribers. | Both Subscribers have new access | N/A | 100 MB Fiber 10 MB Wireless | We will be providing 100 Mbs fiber connection to all Community Anchor Institutes and 10 Mbs wireless connection to all households. | FALSE | N/A | Final reporting and close out. | Ute Indian Tribe | We don't for see any major set backs for this quarter. We will begin the process of final reporting. | We will be complete by the end of grant period. | TRUE
NT10BIX5570145 | 2013 | Q3 | Q3 - 2013 | Project Complete | 9 | 0 | 0 | 0 | 9 | 180 | 0 | 1 | Completed | n/a | n/a | n/a | Completed | Complete and running | n/a | Completed | 0 | 0 | 0 | Currently the Tribe will be the only entity to act as a last mile provider. However, we are hoping that by building this project that we can encourage others to participate and would welcome other possibilities. | 100 Mbs fiber connection for VOIP, Data, and Internet connectivity. 10 Mbs 802.11 wireless connectivity for internet access. | N/A | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a | 43 | 33 | 10 | 2 | Completed | All new subscribers are connected using 100MB Fiber | improved access moved from Point to Point 1024K connections to 100 MB Fiber. | 100 MB Fiber=43 subscribers 10 MB Wireless=0 new subscribers | 180 | 180 | 180 | 0 | 1 | We have concluded the installation of the wireless network, and are currently serving 180 households. | Services are available | Completed | Completed | 10 Mbs 802.11 Wireless | 2 | 2 | 2 | 0 | 2 | Completed | Completed | Completed | N/A | 100 MB Fiber 10 MB Wireless | We are providing 100 Mbs fiber connection to all Community Anchor Institutes and 10 Mbs wireless connection to all households. | FALSE | N/A | Close Out | Ute Indian Tribe | Complete | Completed | TRUE
NT10BIX5570146 | 2010 | Q4 | Q4 - 2010 | Route Design (100% Complete), Community Anchor Institutions Contact / Selection (100% Complete), Located POP building sites, Completed most of the Environmental Assessment (still waiting for Missouri SHPO consultation). Held meetings with BlueBird Media discussing overlap and project coordination. Attended BTOP Recipient Workshop in DC. Completed Davis-Bacon compliance requirements. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance | N/A | No variance | N/A | No variance | N/A | N/A | No variance | 0 | 0 | 0 | None at this time. | Pricing has not yet been finalized. | N/A | 0 | 0 | 0 | 0 | No variance | No variance | No variance | No variance | 0 | 0 | 0 | 0 | No variance | No Variance | No Variance | None available yet, construction has not commenced. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Finish Environmental Assessment and submit to NTIA for FONSI. Begin procurement and RFP process for fiber, network equipment and construction. Begin in-kind fiber valuation with selected vendor. Research permit requirements to begin Construction Phase I (April). Evaluate aerial vs. underground build options based on environmental impacts and right of way issues. | SHO-ME Technologies, L.L.C. | N/A | Missouri SHPO Consultation for the Environmental Assessment. May need to undertake additional archeological work based on preliminary discussions with Missouri SHPO office. | TRUE
NT10BIX5570146 | 2011 | Q1 | Q1 - 2011 | EA draft prepared and submitted to NTIA for review. Overlap SAC researched and determined no duplication exists. Began first open RFP processes made available online, including quotes for construction, installation and fiber valuation. Submitted orders for procurements (transport, switching, cross-connect and test equipment, NOC air handler, fiber materials, shelters) for the project. Some equipment beginning to arrive at SMT warehouse. Federal Program Officer on-site for tour of SMT operations and facilities. Began POP site location acquisition process. Began testing of existing in-kind fiber. 3.4 jobs created and 2.34 jobs retained. SMT website updated with project news and progress. Local community outreach meetings ongoing. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No variance. | N/A | No variance. | N/A | No variance. | N/A | N/A | No variance. | 0 | 0 | 0 | None at this time. | Pricing has not yet been finalized. | N/A | 0 | 0 | 0 | 0 | No variance. | No variance. | No variance. | No variance. | 0 | 0 | 0 | 0 | No variance. | No variance. | No variance. | None available yet, construction has not commenced. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Expect procured equipment arrival at SMT warehouse. After FONSI, plan to begin fiber construction and testing of in-kind fiber. | SHO-ME Technologies, L.L.C. | Began consultations with Osage and Delaware Tribes (found not initially listed by the TCNS) addressing EA concerns with NTIA guidance. | Fiber suppliers concerned of potential delays in fiber delivery due to raw material sources impacted by recent world events in Japan. | TRUE
NT10BIX5570146 | 2011 | Q2 | Q2 - 2011 | a) Special Award Condition (SAC) accomplishments. [i] Issuance, submittal and approval of American Recovery and Reinvestment Act (ARRA) Prime Recipient Report for Quarter 1 (Q1) 2011. [ii] Issuance, submittal and approval of Federal Financial Report (FFR) Standard Form 425 (SF-425) for Q1 2011. [iii] Issuance, submittal and approval of Performance Progress Report (PPR) for Q1 2011. [iv] Issuance, submittal and approval of Environmental Assessment (EA) and receipt of Finding Of No Significant Impact (FONSI). [v] Issuance, submittal and approval of Award Action Request (AAR) for lifting EA SAC. b) Overall Project Accomplishments: [i] Request For Proposal (RFP) procurement process in full cycle for budgeted test equipment, Digital Access and Cross-connect System (DACS), Dense Wavelength Division Multiplexing (DWDM), Ethernet, Network Operations Center (NOC) air handlers, fiber, innerduct, shelters, generators, construction, site preparation, gravel lot and signs. [ii] Marketing team continues Outreach Activities promoting the Sho-Me MO project to several Chambers of Commerce and Regional Technology Planning Teams around Missouri, presenting first Community Anchor Institution (CAI)s with welcome packets, live Question and Answer (Q&A) interviews via local broadcast radio stations, and communicating weekly project progress updates via social media. [iii] Pre-construction meetings held with awarded fiber contractors and review of compliance and reporting r | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Unforeseen supplier delays in delivery of procured fiber, expect delivery next quarter. However, construction of fiber innerduct conduit installation is underway on underground routes. | N/A | No variance. | N/A | Unforeseen supplier delays in delivery of procured fiber, expect delivery next quarter. However, construction of fiber innerduct conduit installation is underway on underground routes. | N/A | N/A | Unforeseen supplier delays in delivery of procured fiber, expect delivery next quarter. However, construction of fiber innerduct conduit installation is underway on underground routesy of procured fiber, expect delivery next quarter. However, construction of fiber innerduct conduit installation is underway on underground routes. | 0 | 0 | 0 | None at this time. | Pricing has not yet been finalized. | N/A | 0 | 0 | 0 | 0 | No variance. | No variance. | No variance. | No variance. | 0 | 0 | 0 | 0 | Unforeseen supplier delays in delivery of procured fiber, expect delivery next quarter. However, construction of fiber innerduct conduit installation is underway on underground routes. | No variance. | Unforeseen supplier delays in delivery of procured fiber, expect delivery next quarter. However, construction of fiber innerduct conduit installation is underway on underground routes. | No variance. | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Overall Project: Expect first CAIs connected, fiber construction continuing, start shelter delivery and installation. Rights of Way: Expect land acquisition of last of PoP sites. Construction Permits and Other Approvals: Ongoing construction. Site Preparation: Expect to complete all 15 new PoP sites preparation well in advance of shelter and generator deliveries. Equipment Procurement: Expect first arrival of new PoP equipment shelters, generators and fiber. Network Build: Expect to begin installation of DWDM equipment into new PoP shelters. Equipment Deployment: Expect connection of first CAIs. | SHO-ME Technologies, L.L.C. | Unforeseen Fiber availability issue: Fiber supplier projected delay in first delivery of our ordered fiber, expect delivery next quarter. | This quarter, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing staff size by 1,200 employees may become a potential constraint on securing timely Rights-of-Way and permitting required for fiber route construction. | TRUE
NT10BIX5570146 | 2011 | Q3 | Q3 - 2011 | a) Special Award Condition (SAC) accomplishments: [i] Issuance, submittal and approval of American Recovery and Reinvestment Act (ARRA) Prime Recipient Report for Quarter 2 (Q2) 2011. [ii] Issuance, submittal and approval of Federal Financial Report (FFR) Standard Form 425 (SF-425) for Q2 2011. [iii] Issuance, submittal and approval of Performance Progress Report (PPR) for Q2 2011. [iv] Received programmatic waiver regarding certain indefeasible rights-of-use sale or lease (IRU) SAC. b) Overall Project Accomplishments: [i] Connection of first Community Anchor Institution (CAI) at Missouri State Fair with subsequent kickoff presentation to the Governor at the 2011 Missouri State Fair event. [ii] Request For Proposal (RFP) procurement process in full cycle and awarded for budgeted fiber, construction materials, Dense Wavelength Division Multiplexing (DWDM) equipment, Ethernet equipment, shelters, generators, Point-of-Presence (PoP) site preparation and construction. Began receiving most Phase 1 orders arriving at warehouse. Orders for Phase 2 underway. [iii] Underground fiber construction contractors selected, awarded, pre-con meetings held and started underground construction on three routes of Phase 1. In the face of a critical fiber shortage, we persisted to successfully install over 130 miles of innerduct underground and made ready for swift installation of ordered fiber scheduled to arrive next quarter from an alternative fiber supplier. [iv] Fiber construction co | 3 | 0 | 457 | 0 | 3 | 0 | 0 | 18 | Below plan due to unforeseen fiber availability constraint from manufacturers. However, in the face of this fiber shortage, Sho-Me persisted with breaking ground on construction. Crews have quickly progressed in aggressive underground conduit plowing schedule on three major route builds between 9 PoP sites. Fiber orders expected to start arriving early in next Quarter and crews are prepared to promptly begin pulling fiber into the new conduits next Quarter. | N/A | More than half of in-kind fiber characterized, tested and expected to be fully contributed to the project next quarter as DWDM and Ethernet equipment is installed. Ongoing testing of remaining in-kind fiber continues toward catching up to baseline goal of 536 miles next Quarter. | N/A | Below Baseline plan due to unforeseen fiber availability constraint from manufacturers. Fiber orders expected to start arriving early in next Quarter and crews are prepared to promptly begin pulling fiber into the new conduits next Quarter. | N/A | N/A | In-kind fibers provisioned for interconnection to 15 existing PoPs plus 3 new PoP shelters. In the face of a critical fiber shortage, we persisted to successfully install underground conduit on several routes and made ready for swift installation of ordered fiber scheduled to arrive next quarter from an alternative fiber supplier. Expect to have all of new equipment shelters delivered to new PoP site interconnection points to bring us to baseline 27 next Quarterr interconnection to 15 existing PoPs plus 3 new PoP shelters. In the face of a critical fiber shortage, we persisted to successfully install underground conduit on several routes and made ready for swift installation of ordered fiber scheduled to arrive next quarter from an alternative fiber supplier. Expect to have all of new equipment shelters delivered to new PoP site interconnection points to bring us to baseline 27 next Quarter. | 4 | 13 | 12 | Missouri State Office of Administration, Missouri Research and Education Network, Missouri Office of State Courts Administrator, Jefferson City Medical Group | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presenced Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence. | N/A | 2 | 2 | 0 | 4 | Above plan due to interest from successful Community Outreach. | Above plan due to interest from successful Community Outreach. | No variance. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (1); 50 Mbps (0); 100 Mbps (2); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 13 | 13 | 0 | 3 | Slightly below planned 17 CAIs due to unforeseen fiber availability constraint, however, we persisted to successfully build to 13 new CAIs and install conduit to another 4 CAIs made ready for swift installation of ordered fiber scheduled to arrive next quarter from an alternative supplier enabling catch up to baseline 17 next Qtr. | Above plan slightly as more CAIs will actually be new vs. improved category. | Below plan slightly as more CAIs will actually be new vs. improved category. | 5 Mbps (0); 10 Mbps (0); 20 Mbps (1); 50 Mbps (0); 100 Mbps (2); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Overall Project: Continue underground construction on several routes with expected installation of 100 miles if fiber to catch up rapidly with recently installed conduits. Seasonal inclement weather is expected to slow down construction progression during the winter months which will move our job creation figure to around 30. Rights of Way: Expect land acquisition for last PoP sites. Construction Permits and Other Approvals: Expected to be secured as necessary for ongoing construction. Site Preparation: Expect to complete all 15 new sites by wrapping up the last 6 made ready for shelters delivered with generators. Equipment Procurement: Expect first delivery of fiber, receipt and payment of Phase 2 DWDM and Ethernet equipment, and delivery of remaining 6 equipment shelters with generators. Vendor/RFP/procurement activities will continue for next construction phase. Network Build: Expect to install DWDM and Ethernet into NOC and PoP site shelters as planned for next construction phase. Equipment Deployment: Expect to connect next wave of new CAIs as construction continues. Expect execution of several additional Interconnection Agreements currently in negotiation. Community Outreach: Campaign efforts continue with local media and will include participation in a Statewide Summit meeting with MoBroadbandNow initiative partners for coordination of planned broadband development, accessibility and sustainability. New network miles deployed: 100. New network miles leased: 0. Total | SHO-ME Technologies, L.L.C. | a) Last quarter, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely Rights-of-Way and permitting required for fiber route construction. b) Unforeseen fiber availability issue. Sho-Me's first fiber order was cancelled by the vendor. The second order was scheduled to be delivered in 3rd Qtr 2011, however, it was relayed to Sho-Me in August 2011 that the fiber would be delayed until February 2012. Sho-Me secured another order with a separate vendor and began receiving that fiber in October 2011. | Fiber availability: We have been working through the unforeseen constraint of procuring the necessary fiber cable on a timely basis from alternative suppliers understanding the Corning fiber supply has now been committed to the needs created by the Japan tsunami disaster. Corning rescinded their RFP quote so we placed orders with alternative bidder, Optical Fiber Systems (OFS) whose delayed delivery dates now estimated out to Q1 2012. Next order was placed to bidder CommScope with confirmed delivery Q4 2011. | TRUE
NT10BIX5570146 | 2011 | Q4 | Q4 - 2011 | a) Special Award Condition (SAC) accomplishments: [i] Issuance, submittal and approval of American Recovery and Reinvestment Act (ARRA) Prime Recipient Report for Quarter 3 (Q3) 2011. [ii] Issuance, submittal and approval of Federal Financial Report (FFR) Standard Form 425 (SF-425) for Q3 2011. [iii] Issuance, submittal and approval of Performance Progress Report (PPR) for Q3 2011. [iv] Submittal and approval of Sho-Me Technologies, LLC For-Profit Recipient Independent Audit for award year 1, as required. b) Overall Project Accomplishments: [i] Participated in Missouri Governor's MoBroadbandNow initiative Annual Summit. [ii] Attended the 2011 BTOP Mid-Course Workshop for Broadband Awardees in Cleveland, OH. [iii] 10 additional Community Anchor Institutions (CAIs) were connected bringing total to 23 Community Anchor Institutions connected through the end of 2011. [iv] Underground construction resulted in an additional 33 miles of installed conduit and 56 miles of fiber. [v] Completed delivery of 5 additional equipment shelters with emergency back-up generators directly to Point of Presence (PoP) site locations and off-loaded via crane; bringing total delivered shelters at year end to 14. One additional shelter is to be delivered 1st Qtr 2012 which will complete the shelter deliveries. [vi] Electrical contractor began installing electric service wiring into new equipment shelters, emergency back-up generators, and ground wire protection. [vii] 16 miles of optical ground wire (OPGW) was hung on electrical transmission lines. [viii] Completion of Sho-Me Technologiesâ€™ NOC air handlers and final testing. [ix] Dense Wavelength Division Multiplexing (DWDM) equipment and Ethernet equipment was installed and lit connecting 457 miles of In-kind fiber between 18 PoPs. These 457 miles of fiber were contributed to the project in 4th Qtr 2011 as an in-kind contribution. [x] Secured all known, necessary permits including but not limited to those from the USACE and Missouri DNR, Rights-of-Way with MoDOT for fiber construction of Phase 1 & 2 routes. [xi] Successful Community Outreach continuing with ongoing participation in numerous Regional Technology Planning Teams across Missouri including citizens, policy makers, business, industry, higher education, schools, healthcare, Internet Service Providers to advance broadband demand and adoption, broadband service and infrastructure availability, within the 30-county project region. Ongoing media participation including live interviews on local radio stations. Weekly newsletter updates posted to project website. [xii] Ongoing PI/PD oversight and field inspections throughout the project including weekly update team meetings. [xiii] Phase 2 DWDM and Ethernet Equipment was received during 4th Qtr 2011. Phase 3 Equipment is schedule to be ordered during 1st Qtr 2012. [xiv] A bridge crossing agreement was reached with the Missouri Department of Transportation relating to the Warsaw Bridge Crossing paving the way for completion of the Sedalia to Cross Timbers route in the 1st Qtr of 2012. [xv] Underground fiber construction contractor selected, awarded, pre-con meetings held and started underground construction on Hermann to Washington to Bem route. | 75 | 0 | 457 | 0 | 75 | 0 | 0 | 18 | Below baseline of 327 due to unforeseen fiber availability constraint from manufacturers. However, in the face of this fiber shortage, Sho-Me persisted with continued underground construction. Crews have quickly progressed in aggressive underground conduit plowing schedule on four major route builds between PoP sites. Fiber orders started arriving early in this Quarter and crews remain actively pulling fiber into the new conduits to progress towards our baseline. | N/A | Slightly below baseline of 536, however, approximately 91 miles will be contributed to the project next quarter as DWDM and Ethernet equipment is installed. Ongoing testing of remaining in-kind fiber continues toward baseline goal of 880 miles. | N/A | Below baseline of 327 due to unforeseen fiber availability constraint from manufacturers. However, in the face of this fiber shortage, Sho-Me persisted with continued underground construction. Crews have quickly progressed in aggressive underground conduit plowing schedule on four major route builds between PoP sites. Fiber orders started arriving early in this Quarter and crews remain actively pulling fiber into the new conduits to progress towards our baseline. | N/A | N/A | Below baseline of 27 due to fiber availability, however, 14 of 15 PoP shelters were delivered on schedule and 163 miles of innerduct installed. | 4 | 8 | 12 | Missouri State Office of Administration, Missouri Research and Education Network, Missouri Office of State Courts Administrator, Jefferson City Medical Group | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence. | N/A | 2 | 2 | 0 | 4 | Above plan due to more new providers receiving access than anticipated. Overall, total providers (new and improved) equals baseline projections. | Below plan due to more new providers receiving access than anticipated. Overall, total providers (new and improved) equals baseline projections. | No variance. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (1); 50 Mbps (0); 100 Mbps (2); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 23 | 16 | 7 | 5 | Above Baseline of 17. | Above plan as more CAIs will actually be new vs. improved category. | Below plan as more CAIs will actually be new vs. improved category. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (2); 50 Mbps (0); 100 Mbps (2); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Rights of Way: Land acquisition will be complete for last PoP site. Construction Permits and Other Approvals: Expected to be secured as necessary for ongoing construction. Site Preparation: Expect to complete all 15 new sites by wrapping up the last make ready for the remaining shelter to be delivered with generators. Equipment Procurement: Expect second round of delivery of fiber to commence and delivery of remaining 1 equipment shelters with generators. Vendor/RFP/procurement activities will continue for next construction phase. Begin ordering Phase 3 Ethernet and DWDM equipment in preparation for installation in construction Phase 3. Network Build: Expect to install DWDM and Ethernet into remaining PoP site shelter. Test, splice, light, and contribute 91 miles of inkind fiber to the project. Continue underground construction on several routes with expected installation of 100 miles of fiber to catch up rapidly with recently installed conduits. Seasonal inclement weather is expected to slow down construction progression during the winter months. Equipment Deployment: Expect to connect next wave of new CAIs as construction continues. Continue negotiation of additional Interconnection Agreements. Community Outreach: Campaign efforts continue with local media and will include participation with initiative partners for coordination of planned broadband development, accessibility and sustainability. Sho-Me's planned project accomplishments through Q1 2012: • New network miles deployed - 600 miles • New network miles leased - 0 miles • Total CAI subscribers served (CAIs connected) - 64 CAIs • Number of signed agreements with broadband wholesalers or last mile providers - 6 agreements | SHO-ME Technologies, L.L.C. | a) Early 2011, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely Rights-of-Way and permitting required for fiber route construction. b) Unforeseen fiber availability issue. Sho-Me's first fiber order was cancelled by the vendor. The second order was scheduled to be delivered in 3rd Qtr 2011, however, it was relayed to Sho-Me in August 2011 that the fiber would be delayed until February 2012. Sho- Me secured another order with a separate vendor. Sho-Me began receiving that fiber in October 2011 and it will have all been received by January 2012. | Fiber availability: We have been working through this unforeseen constraint of procuring the necessary fiber cable on a timely basis from alternative suppliers. We understand the Corning fiber supply appears to have been committed to the needs created by the Japan tsunami disaster. Corning rescinded their RFP quote so we placed orders with an alternative bidder, Optical Fiber Systems (OFS) whose delayed delivery dates is still estimated to be Q1 2012. | TRUE
NT10BIX5570146 | 2012 | Q1 | Q1 - 2012 | a) Special Award Condition (SAC) accomplishments: [i] Issuance, submittal and approval of American Recovery and Reinvestment Act (ARRA) Prime Recipient Report for Quarter 4 (Q4) 2011. [ii] Issuance, submittal and approval of Federal Financial Report (FFR) Standard Form 425 (SF-425) for Q4 2011. [iii] Issuance, submittal and approval of Performance Progress Report (PPR) for Q4 2011. [iv] Submittal and approval of Annual Performance Progress Report (APR) for 2011 and addenda, as required. b) Overall Project Accomplishments: [i] Prepared for NTIA's second annual visit. FPO and Booz/Allen/Hamilton consultant traveled to Sho-Me Technologies' headquarters, where they reviewed project management, policies, procedures, compliance, and toured fiber construction sites and equipment shelter PoP locations. [ii] Sho-Me prepared an Award Action Request for a change from aerial construction to purchases of IRUs. NTIA approved the AAR and acquisition of the IRUs will begin in Q2 of 2012. [iii] 25 additional Community Anchor Institutions (CAIs) were connected bringing total to 48 CAIs connected through the end of 2012's first quarter. [iv] Continued underground construction resulted in an additional 12 miles of installed conduit during the quarter bringing total miles of installed conduit to 178 for the project overall. An additional 114 miles of underground fiber was constructed during the quarter bringing total miles of underground fiber to 173 since the project's inception. 13 miles of optical ground wire (OPGW) were hung on electrical transmission lines for a total of 29 OPGW aerial route miles. The construction progress in Q1 2012 brings total underground and aerial fiber miles newly built, for the project overall, to 202. [v] Bid was awarded to contractor for preparation of last equipment shelter site. Site preparation is to be completed during Q2 of 2012. The last one of 15 equipment shelters is expected to be delivered in May 2012 which will complete the shelter procurements. [vi] Electrical contractor continues installing electric service wiring, emergency back-up generators, and ground wire protection at new equipment shelters. [vii] Began preparation of two additional Requests For Bids (RFBs), including one RFB for underground fiber construction on the "Versailles to Tuscumbia" fiber route and another RFB for 25 lateral builds for additional CAI connections for the project. . [viii] Underground fiber deliveries were completed in Q1 of 2012. Previously, fiber was ordered, but deliveries were delayed due to industry shortage. [ix] Secured all known, necessary permits including but not limited to those from the US Army Corps of Engineers (USACE) and Missouri Department of Natural Resources (MoDNR), Rights-of-Way with Missouri Department of Transportation (MoDOT) for fiber construction routes. [x] Successful Community Outreach continuing with ongoing participation in numerous Regional Technology Planning Teams across Missouri including citizens, policy makers, business, industry, higher education, schools, healthcare, Internet Service Providers to advance broadband demand and adoption, broadband service and infrastructure availability, within the 30-county project region. During Q1 of 2012, Sho-Me's marketing team attended and spoke at the annual meeting of the County Commissioners Association of Missouri. The team was well received and delivered information regarding the "Sho-Me MO" BTOP project to over 60 of Missouri's county commissioners. Ongoing media participation including live interviews on local radio stations. Weekly newsletter updates are posted to the "Sho-Me MO" project website and distributed via emails. [xi] Ongoing PI/PD oversight, including compliance oversight, field inspections of construction throughout the project, biweekly team update meetings, SF-1445 interviews of construction crews by Sho-Me personnel, and conference calls with FPO and BTOP Team. [xii] A bridge crossing agreement was reached with the MoDOT relating to the Warsaw bridge crossing in 2011. The bridge crossing construction was completed in Q1 of 2012; paving the way for completion of the "Sedalia to Cross Timbers" fiber route in Q2 of 2012. [xiii] Underground fiber construction contractor started underground construction on the "Hermann to Washington to Bem" fiber route during Q1 of 2012. | 202 | 0 | 564 | 0 | 202 | 0 | 0 | 18 | Below baseline of 370 due to unforeseen fiber availability constraint from manufacturers in 2011. However, in the face of this fiber shortage, Sho-Me persisted with continued underground construction. Crews have quickly progressed in aggressive underground conduit plowing schedule on four major route builds between PoP sites. Fiber orders started arriving last Quarter and crews remain actively pulling fiber into the new conduits to progress towards our baseline. Sho-Me anticipates catching up to baseline by the end of 2012. | N/A | Below baseline of 708, due to fiber availability delays which also offset our ability to splice in-kind segments to pending new fiber builds. However, approximately 107 miles were contributed to the project this quarter. Ongoing testing of remaining in-kind fiber continues toward baseline goal of 880 miles. Sho-Me anticipates catching up to baseline by the end of 2012. | N/A | Below baseline of 370 due to unforeseen fiber availability constraint from manufacturers in 2011. However, in the face of this fiber shortage, Sho-Me persisted with continued underground construction. Crews have quickly progressed in aggressive underground conduit plowing schedule on four major route builds between PoP sites. Fiber orders started arriving last Quarter and crews remain actively pulling fiber into the new conduits to progress towards our baseline. Sho-Me anticipates catching up to baseline by the end of 2012. | N/A | N/A | Below baseline 32 due to unforeseen fiber availability constraint from manufacturers in 2011. However, 14 of 15 PoP shelters were delivered on schedule and 175 miles of innerduct installed. Sho-Me anticipates catching up to baseline by the end of 2012. | 4 | 27 | 12 | Missouri State Office of Administration, Missouri Research and Education Network, Missouri Office of State Courts Administrator, Jefferson City Medical Group | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence. | N/A | 2 | 2 | 0 | 4 | Above plan due to more new providers receiving access than anticipated. | Below plan due to more new providers receiving access than anticipated. | No variance. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (1); 50 Mbps (0); 100 Mbps (2); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 48 | 17 | 31 | 6 | Below baseline by 16 due to delay in fiber, however Sho-Me now has received all fiber ordered for the project and plans to catch up to baseline by the end of 2012. | Above plan as more CAIs will actually be new vs. improved category and due to delay in the fiber, however, Sho-Me now has received all fiber ordered for the project and plans to catch up to baseline by the end of 2012. | Below plan as more CAIs will actually be new vs. improved category and due to delay in fiber, however, Sho-Me now has received all fiber ordered for the project and plans to catch uip to baseline by the end of 2012. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (2); 50 Mbps (0); 100 Mbps (3); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Rights of Way: Land acquisition has been finalized for last PoP site to be completed next quarter, Q2 2012. Construction Permits and Other Approvals: Expected to be secured as necessary for ongoing construction. Site Preparation: Expect to complete all 15 new sites by wrapping up the last site preparation for the remaining shelter. Shelter to be delivered with generators in Q2 2012. Equipment Procurement: Vendor/RFP/procurement activities will continue for next construction phase. Will begin ordering Phase 3 Ethernet and DWDM equipment in preparation for installation in construction Phase 3. Network Build: Expect to install DWDM and Ethernet into remaining PoP site shelter. Test, splice, light, and contribute 30 miles of in-kind fiber to the project. Continue underground construction on several routes with expected installation of 70 miles of fiber to catch up rapidly with recently installed conduits. Seasonal rainy weather is expected to offset construction progression slightly during the spring months of Quarter 2, 2012. Equipment Deployment: Expect to connect next wave of new CAIs as construction continues. Continue negotiation of additional Interconnection Agreements. Community Outreach: Campaign efforts continue with local media and will include participation with initiative partners for coordination of planned broadband development, accessibility and sustainability. Sho-Me's planned project accomplishments through Q2 2012: â€¢ New network miles deployed - bringing total new network miles to 272. â€¢ New network miles leased - 0 miles (not planned) â€¢ Total CAI subscribers connected - 64 CAIs â€¢ Number of signed agreements with broadband wholesalers or last mile providers - 4 agreements | SHO-ME Technologies, L.L.C. | In early 2011, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely Rights-of-Way and permitting required for fiber route construction. | In early 2011, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely Rights-of-Way and permitting required for fiber route construction. In previous quarters fiber availability was a concern. However, Sho-Me is pleased to report that underground fiber deliveries were completed in Q1 of 2012. Fiber availability is not longer a threat to Sho-Me's project success. | TRUE
NT10BIX5570146 | 2012 | Q2 | Q2 - 2012 | a) Special Award Condition (SAC) accomplishments: [i] Issuance, submittal and approval of American Recovery and Reinvestment Act (ARRA) Prime Recipient Report for Q1 2012. [ii] Issuance, submittal and approval of Federal Financial Report (FFR) Standard Form 425 (SF-425) for Q1 2012. [iii] Issuance, submittal and approval of Performance Progress Report (PPR) for Q1 2012. b) Overall Project Accomplishments: [i] Continued underground construction resulted in an additional 67.5 miles of installed conduit during the quarter. An additional 3.7 miles of underground fiber was constructed during the quarter. 3.5 miles of optical ground wire (OPGW) were hung on electrical transmission lines. [ii] Completed construction including splicing and testing of: "Cross Timbers to Warsaw" underground fiber route, "Linn to Vienna" underground fiber route, and "California to Hermann" underground fiber route. [iii] Sho-Me prepared an Award Action Request (AAR) for a change from aerial construction to purchases of Indefeasible Right of Use (IRU) agreements. NTIA approved the AAR and acquisition of the IRUs is underway. [iv] Sho-Me prepared an Award Action Request (AAR) for two route changes proposed; one in the city of Springfield, MO and another along the "Cabool to Houston" underground fiber route. NTIA approved the AAR in Q2 of 2012. [v] Preparation and posting of two additional Requests For Bids (RFBs), including one RFB for underground fiber construction on the "Springfield to Noble Hill" underground fiber route and another RFB for lateral fiber builds connecting 24 CAIs of the project. [vi] Awarded contractor for "Versailles to Tuscumbia" underground fiber route and started construction in Q2 of 2012. [vii] Fiber construction contractor continues on construction of the "Hermann to Washington to Bem" underground fiber route. [viii] Electrical contractor completed installing electric service wiring, connecting and testing of emergency back-up generators, and ground wire protection at new equipment shelters. [ix] The construction progress in Q2 2012 brings total of underground and aerial fiber newly built, for the project overall, to 209.2 miles. [x] Secured all known, necessary permits including but not limited to those from the US Army Corps of Engineers (USACE) and Missouri Department of Natural Resources (MoDNR), Rights-of-Way with Missouri Department of Transportation (MoDOT) for fiber construction routes. [xi] Successful Community Outreach continuing with ongoing participation in Round 2 sessions of the Regional Technology Planning Teams across Missouri which include citizens, policy makers, business, industry, higher education, schools, healthcare, Internet Service Providers to advance broadband demand and adoption, broadband service and infrastructure availability, within the 30-county project region. Ongoing media participation including two live interviews on local radio stations and local newspaper feature article covering fiber construction and local excitement of fiber availability coming to their community. Weekly newsletter updates are posted to the "Sho-Me MO" project website and distributed via e-mail. [xii] Ongoing PI/PD oversight, including compliance oversight, field inspections of construction throughout the project, biweekly team update meetings, ongoing SF-1445 labor standards interviews of construction crews by Sho-Me personnel, participation in BTOP webinars and conference calls with FPO and BTOP Team. [xiii] Marketing Manager attended NTIA-SHLB Broadband Conference in Washington, DC regarding "Creating Sustainable Broadband Solutions for Communities and Anchor Institutions". [xiv] Submitted corrections for BTOP Map and participated in Map Webinar "Visualizing BTOP's impact and Broadband availability: NTIA maps as resources for grantees". [xv] Began receiving shipments of Phase 3 and 4 DWDM and Ethernet equipment procurement at end of Q2 2012. | 209 | 0 | 564 | 0 | 209 | 0 | 0 | 18 | Below baseline of 412 due to unforeseen fiber availability constraint from manufacturers in 2011. However, in the face of this fiber shortage, Sho-Me persisted with continued underground construction. Crews have quickly progressed;resulting in an additional 67.5 miles of installed conduit during the quarter. Quarter and crews remain actively pulling fiber into the new conduits to progress towards our baseline. Sho-Me anticipates catching up to baseline by the end of 2012. | N/A | Below baseline of 708 due to fiber availability delays which also offset our ability to splice in-kind segments to pending new fiber builds. Ongoing testing of remaining in-kind fiber continues toward baseline goal of 880 miles. Sho-Me anticipates catching up to baseline by the end of 2012. | N/A | Below baseline of 412 due to unforeseen fiber availability constraint from manufacturers in 2011. However, in the face of this fiber shortage, Sho-Me persisted with continued underground construction. Crews have quickly progressed;resulting in an additional 67.5 miles of installed conduit during the quarter. Quarter and crews remain actively pulling fiber into the new conduits to progress towards our baseline. Sho-Me anticipates catching up to baseline by the end of 2012. | N/A | N/A | Below baseline 32 due to unforeseen fiber availability constraint from manufacturers in 2011. However, 15 of 15 PoP shelters were delivered on schedule, 67.5 miles of innerduct were installed. An additional 8 interconnection points will be installed and contributed next quarter and Sho-Me anticipates catching up to baseline by the end of 2012. | 7 | 30 | 12 | Missouri State Office of Administration, Missouri Research and Education Network, Missouri Office of State Courts Administrator, Jefferson City Medical Group, Missouri Wi-Fi, Mid-Missouri Broadband, Central Missouri Computer Services. | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence. | N/A | 5 | 2 | 0 | 7 | Above plan due to more providers receiving new access than anticipated. | Below plan due to more providers receiving new access than anticipated. | No variance. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (1); 40Mbps (1); 45Mbps (1); 50 Mbps (1); 100 Mbps (2); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 48 | 17 | 31 | 6 | Below baseline by 16 due to delay in fiber, however Sho-Me now has received all fiber ordered for the project and plans to catch up to baseline by the end of 2012. | Above plan as more CAIs will actually be new vs. improved category and due to delay in the fiber, however, Sho-Me now has received all fiber ordered for the project and plans to catch up to baseline by the end of 2012. | Below plan as more CAIs will actually be new vs. improved category and due to delay in fiber, however, Sho-Me now has received all fiber ordered for the project and plans to catch uip to baseline by the end of 2012. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (2); 50 Mbps (0); 100 Mbps (3); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Rights of Way: Expected to be secured as necessary for ongoing construction. Construction Permits and Other Approvals: Expected to be secured as necessary for ongoing construction. Equipment Procurement: Vendor/RFP/procurement activities will continue for next construction phase. Receiving and paying for ordered Ethernet and DWDM equipment for construction Phase 3 and 4 in preparation for installations in Q4. Network Build: Expect to install DWDM and Ethernet into remaining PoP site shelters. Test, splice, light, and contribute additional miles of in-kind fiber to the project. Continue underground construction on several routes with expected installation of 120 miles of new fiber to catch up rapidly with recently installed conduits. Equipment Deployment: Expect to connect the next wave of new CAIs after construction of fiber laterals. Continue negotiation of additional Interconnection Agreements. Community Outreach: Campaign efforts continue with local media and will include participation with initiative partners for coordination of planned broadband development, accessibility and sustainability. Sho-Me's planned project accomplishments through Q3 2012: â€¢ New network miles deployed - bringing total new network miles to 329. â€¢ New network miles leased - 0 miles (not planned) â€¢ Total CAI subscribers connected - 64 CAIs â€¢ Number of signed agreements with broadband wholesalers or last mile providers - 10 agreements | SHO-ME Technologies, L.L.C. | In early 2011, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely Rights-of-Way and permitting required for fiber route construction. | In early 2011, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely Rights-of-Way and permitting required for fiber route construction. In previous quarters fiber availability was a concern. However, Sho-Me not longer believes fiber availability poses a threat to Sho-Me's project success. | TRUE
NT10BIX5570146 | 2012 | Q3 | Q3 - 2012 | a) Special Award Condition (SAC) accomplishments: [i] Issuance, submittal and approval of American Recovery and Reinvestment Act (ARRA) Prime Recipient Report for 2nd Quarter 2012. [ii] Issuance, submittal and approval of Federal Financial Report (FFR) Standard Form 425 (SF-425) for 2nd Quarter 2012. [iii] Issuance, submittal and approval of Performance Progress Report (PPR) for 2nd Quarter 2012. [iv] Satisfied obligation of 67% substantial project completion due in 3rd Quarter 2012. b) Overall Project Accomplishments: [i] Underground construction continued resulting in an additional 91 miles of underground fiber during the quarter, of which 3 miles of optical ground wire (OPGW) were hung on electrical transmission lines, bringing our new fiber construction total to 301 miles. An additional 72 miles of in-kind fiber was contributed. The progress in 3rd Quarter 2012 brings overall project total of underground and aerial fiber to 937 miles. [ii] Completed splicing and testing of fiber as well as the installation and commissioning of dense wavelength division multiplexing (DWDM) equipment on 8 routes between Points of Presence (PoP) locations including: Marshfield to Buffalo, Preston to Warsaw, Warsaw to Sedalia, Sedalia to Tipton, Jefferson City to Linn, Linn to Hermann, Linn to Vienna, and Tipton to Jefferson City. [iii] Pre-construction meeting with contractor awarded fiber installation to 24 Community Anchor Institutions. Construction began on this project during 3rd Quarter 2012. [iv] Pre-construction meeting with contractor awarded underground fiber route between Springfield and Noble Hill. Construction began on this project during 3rd Quarter 2012. [v] Sho-Me prepared and submitted an Award Action Request (AAR) for a route modification from the â€œBakersfield to Thayerâ€ route to an alternative â€œMarshfield to Prestonâ€ route. NTIA approved the AAR in 4th Quarter 2012. [vi] Preparation of an EHP checklist for a proposed AAR to replace 12 original Community Anchor Institutions with 12 new CAIs. [vii] Fiber construction contractor continues on the 63-mile "Hermann to Washington to Bem" underground fiber route completing 62 miles of innerduct, to date, ahead of crews blowing in 46 miles of fiber. [viii] Secured all known and necessary permits for fiber construction routes within rights of way from federal, state and local agencies. [ix] Successful Community Outreach continuing with ongoing participation in final sessions of the Regional Technology Planning Teams across Missouri which include citizens, policy makers, business, industry, higher education, schools, healthcare, Internet Service Providers to advance broadband demand and adoption, broadband service and infrastructure availability, within the 30- county project region. Ongoing media participation including live interviews on local radio stations and local newspapers feature articles covering fiber construction and local excitement of fiber availability coming to various communities. Weekly newsletter updates are posted to the "Sho-Me MO" project website and distributed via e-mail. [x] Ongoing PI/PD oversight, including compliance oversight, field inspections of construction throughout the project, biweekly team update meetings, ongoing Davis-Bacon Act SF-1445 labor standards interviews of construction crews by Sho-Me personnel and conference calls with FPO and BTOP Team. PI/PDs participated in BTOP webinars covering Award Closeout Procedures, Program Income, Davis-Bacon Act, Compliance, Regional Interconnections, Effective Collaboration among CCI projects, Sustainability Needs, Interconnections, and Successful Outreach and Marketing. [xii] Received all shipments of Phase 3 and 4 DWDM and Ethernet equipment procurement at end of Q2 2012 and paid invoices received in Q3 2012. [xiii] Procured and received security equipment for the 15 new telecommunications shelters. Installation began in 3rd Quarter 2012. [xiv] As a MoBroadbandNow Partner Provider; Sho-Me Technologies completed and submitted the 2nd Qtr 2012 project tracking form as requested by the State of Missouri in accordance with its broadband initiative. | 301 | 0 | 636 | 0 | 301 | 0 | 0 | 26 | Below baseline of 456 due to unforeseen fiber availability constraints from manufacturers in 2011. However, in the face of this fiber shortage, Sho-Me persisted with continued underground construction. Crews have quickly progressed;resulting in an additional 91 miles of installed fiber during the quarter. Crews remain active; installing fiber into the new conduits to progress towards our baseline. Sho-Me anticipates catching up to baseline by 1st Quarter 2013. | N/A | Below baseline of 757 due to fiber availability delays which also offsets our ability to splice in-kind segments to pending new fiber builds. Ongoing testing of remaining in-kind fiber continues toward baseline goal of 880 miles. Sho-Me anticipates catching up to baseline by the end of 2012. | N/A | Below baseline of 456 due to unforeseen fiber availability constraints from manufacturers in 2011. However, in the face of this fiber shortage, Sho-Me persisted with continued underground construction and installed additional conduit during the quarter. Crews remain active; installing fiber into the new conduits to progress towards our baseline. Sho-Me anticipates catching up to baseline by 1st Quarter 2013. | N/A | N/A | Below baseline of 32 due to unforeseen fiber availability constraint from manufacturers in 2011. An additional 8 interconnection points were installed this quarter and Sho-Me anticipates catching up to baseline by 2nd Quarter 2013. | 7 | 33 | 12 | Missouri State Office of Administration, Missouri Research and Education Network, Missouri Office of State Courts Administrator, Jefferson City Medical Group, Missouri Wi-Fi, Mid-Missouri Broadband, Central Missouri Computer Services. Negotiations with other additional providers are in process with no final determination at this time, however, commitments are likely nearer to the project completion date. | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence. | N/A | 5 | 2 | 0 | 7 | Above plan due to more providers receiving new access than anticipated. Negotiations with other additional providers are in process with no final determination at this time, however, commitments are likely nearer to the project completion date. | Below plan due to more providers receiving new access than anticipated. Negotiations with other additional providers are in process with no final determination at this time, however, commitments are likely nearer to the project completion date. | No variance. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (1); 40Mbps (1); 45Mbps (1); 50 Mbps (1); 100 Mbps (2); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 51 | 20 | 31 | 6 | Below baseline by 28 due to delay in fiber, however Sho-Me has received all fiber ordered for the project and plans to catch up toward baseline by 1st Quarter 2013. | Above plan as more CAIs will actually be in the new vs. improved category and due to delay in the fiber, however, Sho-Me has received all fiber ordered for the project and plans to catch up to baseline by 1st Quarter 2013. | Below plan as more CAIs will actually be in the new vs. improved category and due to delay in fiber, however, Sho-Me has received all fiber ordered for the project and plans to catch up to baseline by 1st Quarter 2013. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (2); 50 Mbps (0); 100 Mbps (3); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Rights of Way: Expected to be secured as necessary for ongoing construction. Construction Permits and Other Approvals: Expected to be secured as necessary for ongoing construction. Equipment Procurement: Vendor/RFP/procurement activities will continue for next construction phase. Network Build: Expect to continue installation of DWDM and Ethernet into remaining PoP site shelters, as well as, test, splice, light, and contribute additional miles of in-kind fiber to the project. Continue underground construction on several routes with expected installation of 98 miles of new fiber to rapidly catch up with recently installed conduits. Receiving and paying for construction invoices of Phase 3 and 4 through Q4 2013. Equipment Deployment: Expect to connect the next wave of new CAIs after construction of fiber laterals. Continue negotiation of additional Interconnection Agreements. Community Outreach: Campaign efforts continue with local media and will include participation with initiative partners for coordination of planned broadband development, accessibility and sustainability. Sho-Me's planned project accomplishments through Q4 2012: â€¢ New network miles deployed - bringing total new network miles to 399. â€¢ New network miles leased - 0 miles (not planned) â€¢ Total CAI subscribers connected - 72 CAIs â€¢ Number of signed agreements with broadband wholesalers or last mile providers - 7 agreements | SHO-ME Technologies, L.L.C. | In early 2011, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely rights of way and permitting required for fiber route construction. | In early 2011, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely rights of way and permitting required for fiber route construction. In previous quarters fiber availability was a concern. However, Sho-Me not longer believes fiber availability poses a threat to Sho-Me's project success. | TRUE
NT10BIX5570146 | 2012 | Q4 | Q4 - 2012 | a) Special Award Condition (SAC) accomplishments: [i] Issuance, submittal and approval of American Recovery and Reinvestment Act (ARRA) Prime Recipient Report for 3rd Quarter 2012. [ii] Issuance, submittal and approval of Federal Financial Report (FFR) Standard Form 425 (SF-425) for 3rd Quarter 2012. [iii] Issuance, submittal and approval of Performance Progress Report (PPR) for 3rd Quarter 2012. b) Overall Project Accomplishments: [i] Fiber construction continued resulting in an additional 102 miles of fiber during the quarter, of which 20.5 miles of optical ground wire (OPGW) were hung on electrical transmission lines, bringing our new fiber construction total to 403 miles. An additional 107 miles of in-kind fiber was contributed to the BTOP Project. The progress in 4th Quarter 2012 brings overall BTOP Project total of underground and aerial fiber to 1,146 miles. [ii] Completed splicing and testing of fiber on seven routes between Points of Presence (PoP) locations. [iii] Sho-Me prepared and submitted an Award Action Request (AAR) in coordination with Sho-Me's FPO for a route modification to replace 12 original Community Anchor Institutions (CAIs) not yet constructed with 12 new CAIs along the middle-mile routes, change 500 feet of fiber construction method from underground to aerial, and consideration of existing collocations as alternative interconnect points. Sho-Me is awaiting approval of this AAR. [iv] Fiber construction contractor completed the 63-mile "Hermann to Washington to Bem" underground fiber route. [v] Fiber construction contractor continued the 28-mile build "Springfield to Bolivar" underground fiber route completing 28 miles of conduit. The route, including the fiber blow-in, will be completed in 1st Qtr 2013. [vi] Fiber construction contractor continued the 29.65-mile build "Marshfield to Preston" underground fiber route completing 29.65 miles of conduit. The route, including fiber blow-in, will be completed in 1st Qtr 2013. [vii] Secured all known and necessary permits for fiber construction routes within rights of way from federal, state and local agencies. [viii] Successful Community Outreach continuing with ongoing participation in final sessions of the Regional Technology Planning Teams across Missouri which include citizens, policy makers, business, industry, higher education, schools, healthcare, Internet Service Providers to advance broadband demand and adoption, broadband service and infrastructure availability, within the 30- county project region. Ongoing media participation including live interviews on local radio stations and local newspapers feature articles covering fiber construction and local excitement of fiber availability coming to various communities. Weekly newsletter updates are posted to the "Sho-Me MO" project website and distributed via e-mail. [ix] Ongoing PI/PD oversight, including compliance oversight, field inspections of construction throughout the project, biweekly team update meetings, ongoing Davis-Bacon Act SF-1445 labor standards interviews of construction crews by Sho-Me personnel and conference calls with FPO and BTOP Team. PI/PDs participated in BTOP webinars covering Federal Interest, Program Benefits and Reporting, Sustainability; Planning for Companies and Non-Profit Organizations, and Closeout. [x] Procured and received security equipment for the 15 new telecommunications shelters. Installation of this equipment continued in 4th Quarter 2012. [xi] As a MoBroadbandNow Partner Provider; Sho-Me Technologies completed and submitted the 3rd Qtr 2012 project tracking form as requested by the State of Missouri in accordance with its broadband initiative. | 403 | 0 | 743 | 0 | 403 | 0 | 0 | 26 | Below baseline of 500 due to unforeseen fiber availability constraints from manufacturers in 2011. However, in the face of this fiber shortage, Sho-Me persisted with continued underground construction. Crews have quickly progressed; resulting in an additional 102 miles of installed fiber during the quarter. Crews remain active; installing fiber into the new conduits to progress towards our baseline. Sho-Me anticipates catching up to baseline by 2nd Quarter 2013. | N/A | Below baseline of 757 due to unforeseen fiber availability constraints from manufacturers in 2011 which also offsets our ability to splice in-kind segments to pending new fiber builds. Ongoing testing of remaining in-kind fiber continues toward baseline goal of 880 miles. Sho-Me anticipates catching up to baseline by 2nd Quarter 2013. | N/A | Below baseline of 500 due to unforeseen fiber availability constraints from manufacturers in 2011. However, in the face of this fiber shortage, Sho-Me persisted with continued underground construction and installed additional conduit during the quarter. Crews remain active; installing fiber into the new conduits to progress towards our baseline. Sho-Me anticipates catching up to baseline by 2nd Quarter 2013. | N/A | N/A | Below baseline of 32 due to unforeseen fiber availability constraint from manufacturers in 2011. Sho-Me anticipates catching up to baseline by 2nd Quarter 2013. | 7 | 33 | 12 | Missouri State Office of Administration, Missouri Research and Education Network, Missouri Office of State Courts Administrator, Jefferson City Medical Group, Missouri Wi-Fi, Mid-Missouri Broadband, Central Missouri Computer Services. Negotiations with other additional providers are in process with no final determination at this time, however, commitments are likely nearer to the project completion date. | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence. | N/A | 5 | 2 | 0 | 7 | Above plan due to more providers receiving new access than anticipated. Negotiations with other additional providers are in process with no final determination at this time, however, commitments are likely nearer to the project completion date. | Below plan due to more providers receiving new access than anticipated. Negotiations with other additional providers are in process with no final determination at this time, however, commitments are likely nearer to the project completion date. | No variance. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (1); 40Mbps (1); 45Mbps (1); 50 Mbps (1); 100 Mbps (2); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 61 | 30 | 31 | 7 | Below baseline by 18 due to unforeseen fiber availability constraints from manufacturers in 2011, however Sho-Me has received all fiber ordered for the project. CAI installations are underway to catch up toward baseline by 2nd Quarter 2013 if AAR for 12 new CAIs is approved by the Grants Office. | Above plan as more CAIs will actually be in the new vs. improved category and due to delay in the fiber, however, Sho-Me has received all fiber ordered for the project. CAI installations are underway to catch up to baseline by 2nd Quarter 2013 if AAR for 12 new CAIs is approved by the Grants Office. | Below plan as more CAIs will actually be in the new vs. improved category and due to delay in fiber, however, Sho-Me has received all fiber ordered for the project. CAI installations are underway to catch up to baseline by 2nd Quarter 2013 if AAR for 12 new CAIs is approved by the Grants Office. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (2); 50 Mbps (0); 100 Mbps (4); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Rights of Way: Expected to be secured as necessary for ongoing construction. Construction Permits and Other Approvals: Expected to be secured as necessary for ongoing construction. Equipment Procurement: Vendor/RFP/procurement activities will continue for next construction phase. Network Build: Expect to continue installation of DWDM and Ethernet into PoP site shelters, as well as test, splice, light, and contribute additional miles of in-kind fiber to the project. Receiving and paying for construction invoices of Phase 3 and 4 through Q4 2013. Equipment Deployment: Expect to connect the next wave of new CAIs after construction of fiber laterals. Continue negotiation of additional Interconnection Agreements. Community Outreach: Campaign efforts continue with local media and will include participation with initiative partners for coordination of planned broadband development, accessibility and sustainability. Sho-Me's planned project accomplishments through Q1 2013: â€¢ New network miles deployed next quarter- 27 miles: bringing total new network miles to 430. â€¢ New network miles leased next quarter - 0 miles (not planned). â€¢ In-kind network miles upgraded - 50 miles: bringing total in-kind network miles to 793. â€¢ Total CAI subscribers connected next quarter - 20 CAIs: bringing total CAIs to 81 CAIs. â€¢ No additional signed agreements with broadband wholesalers or last mile providers are anticipated for next quarter. Total is expected to remain at 7 agreements. | SHO-ME Technologies, L.L.C. | In early 2011, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely rights of way and permitting required for fiber route construction. Sho-Me Technologies is anticipating the approval of its most recent Action Award Request (AAR) so that construction can begin on the 12 new CAIs and an aerial build that are part of this pending AAR. Sho-Me submitted the request in early December 2012 and not yet received approval as of this reporting date. | In early 2011, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely rights of way and permitting required for fiber route construction. In previous quarters fiber availability was a concern. However, Sho-Me not longer believes fiber availability poses a threat to Sho-Me's project success. Sho-Me Technologies is eagerly anticipating the approval of its most recent Action Award Request (AAR) so that construction can begin on the 12 new CAIs and the aerial build that are part of the pending AAR. Sho-Me submitted the request in early December 2012 and not yet received approval. | TRUE
NT10BIX5570146 | 2013 | Q1 | Q1 - 2013 | a) Special Award Condition (SAC) accomplishments: [i] Issuance, submittal and approval of American Recovery and Reinvestment Act (ARRA) Prime Recipient Report for 4th Quarter 2012. [ii] Issuance, submittal and approval of Federal Financial Report (FFR) Standard Form 425 (SF-425) for 4th Quarter 2012. [iii] Issuance, submittal and approval of Performance Progress Report (PPR) for 4th Quarter 2012. [iv] Issuance, submittal and approval of Annual Performance Progress Report (APR) for 2012. b) Overall Project Accomplishments: [i] Fiber construction continued resulting in an additional 88 miles of fiber during the quarter bringing our new fiber construction total to 491 miles. An additional 49 miles of in-kind fiber was contributed to the BTOP Project, bringing total in-kind miles to 792. The progress in 1st Quarter 2013 brings overall BTOP Project total of underground and aerial fiber to 1,283 miles. [ii] Completed splicing and testing of fiber on 6 routes between Points of Presence (PoP) locations. [iii] Sho-Me received approval of an Award Action Request (AAR) in coordination with Sho-Me's Federal Program Officer (FPO) for a route modification to replace 12 original Community Anchor Institutions (CAIs) not yet constructed with 12 new CAIs along the middle-mile routes, change 500 feet of fiber construction method from underground to aerial, and consideration of existing collocations as alternative interconnect points to an adjacent BTOP grant awardee. [iv] Fiber construction contractor completed the 28-mile build "Springfield to Bolivar" underground fiber route in 1st Qtr 2013. [v] Fiber construction contractor competed the 29.65-mile build "Marshfield to Preston" underground fiber route in 1st Qtr 2013. [vi] Secured all known and necessary permits for fiber construction routes within rights of way from federal, state and local agencies. [vii] Successful Community Outreach is continuing with participation in live interviews on local radio stations. Local newspapers feature articles covering fiber construction and local excitement of fiber availability coming to various communities. Weekly newsletter updates are posted to the "Sho-Me MO" Project website and are distributed via e-mail. Sho-Me assisted the State of Missouri in taping interviews with one of â€œSho-Me MOâ€ Projectâ€™s last-mile providers including testimonies from several of its new rural customers. The video is expected to be posted very soon on MO.gov and MOBroadbandNOW.com websites. Sho-Me attended the Missouri Governorâ€™s Conference on Agriculture called â€œAG Nowâ€ which included speakers, panel discussions and seminars regarding current issues and opportunities for agriculture. Sho-Me is following up with Missouri University Extension office regarding opportunities previously discussed at the â€œAG Nowâ€ conference. Sho-Me also met with regional directors of the Missouri State Department of Economic Development - Community Service to discuss the â€œSho-Me MOâ€ BTOP Project plus opportunities for the communities near the Projectâ€™s network. [viii] Ongoing PI/PD oversight, including compliance oversight, field inspections of construction throughout the project, monthly team update meetings, ongoing Davis-Bacon Act SF-1445 labor standards interviews of construction crews by Sho-Me personnel and conference calls with FPO and BTOP Team. PI/PDs participated in the BTOP webinars covering Audit Findings and Interconnection Among BTOP (Midwest). Sho-Me's marketing director also was a panelist for the Interconnection Among BTOP (Midwest) webinar. [ix] Completed and submitted the 4th Qtr 2012 project tracking form as requested by the State of Missouri as a MoBroadbandNow Partner Provider in accordance with its broadband initiative. [x] Began preparing a Request for Bid (RFB) for SMM025, for 15 of Sho-Me MO's remaining CAIs. The RFB will be let, awarded. and started in 2nd Qtr 2013. [xi] Installation of security equipment continued in 1st Qtr 2013. | 491 | 0 | 792 | 0 | 491 | 0 | 0 | 31 | Below baseline of 500 due to unforeseen fiber availability constraints from manufacturers in 2011. However, in the face of this fiber shortage, Sho-Me persisted with continued underground construction. Crews have quickly progressed;resulting in an additional 88 miles of installed fiber during the quarter. Crews remain active; installing fiber into the new conduits to progress towards our baseline. Sho-Me anticipates catching up to baseline by 2nd Quarter 2013. | N/A | Below baseline of 880 due to unforeseen fiber availability constraints from manufacturers in 2011 which also offsets our ability to splice in-kind segments to pending new fiber builds. Ongoing testing of remaining in-kind fiber continues toward baseline goal of 880 miles. Sho-Me anticipates catching up to baseline by 2nd Quarter 2013. | N/A | Below baseline of 500 due to unforeseen fiber availability constraints from manufacturers in 2011. However, in the face of this fiber shortage, Sho-Me persisted with continued underground construction. Crews have quickly progressed;resulting in an additional 88 miles of installed fiber during the quarter. Crews remain active; installing fiber into the new conduits to progress towards our baseline. Sho-Me anticipates catching up to baseline by 2nd Quarter 2013. | N/A | N/A | Below baseline of 33 due to unforeseen fiber availability constraint from manufacturers in 2011. Sho-Me anticipates catching up to baseline by 2nd Quarter 2013. | 7 | 40 | 12 | Missouri State Office of Administration, Missouri Research and Education Network, Missouri Office of State Courts Administrator, Jefferson City Medical Group, Missouri Wi-Fi, Mid-Missouri Broadband, Central Missouri Computer Services. Sho-Me has multiple agreements with many of the aforementioned providers. Negotiations with other additional providers are in process with no final determination at this time, however, commitments are likely nearer to the project completion date. | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence. | N/A | 5 | 2 | 0 | 7 | Above plan due to more providers receiving new access than anticipated. Negotiations with other additional providers are in process with no final determination at this time, however, commitments are likely nearer to the project completion date. | Below plan due to more providers receiving new access than anticipated. Negotiations with other additional providers are in process with no final determination at this time, however, commitments are likely nearer to the project completion date. | No variance. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (1); 40Mbps (1); 45Mbps (1); 50 Mbps (1); 100 Mbps (2); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 76 | 45 | 31 | 7 | Below baseline by 24 due to unforeseen fiber availability constraints from manufacturers in 2011, however Sho-Me has received all fiber ordered for the project. CAI installations are underway to catch up toward baseline by 2nd Quarter 2013. | Above plan as more CAIs will actually be in the new vs. improved category and due to delay in the fiber, however, Sho-Me has received all fiber ordered for the project. CAI installations are underway to catch up to baseline by 2nd Quarter 2013. | Below plan as more CAIs will actually be in the new vs. improved category and due to delay in fiber, however, Sho-Me has received all fiber ordered for the project. CAI installations are underway to catch up to baseline by 2nd Quarter 2013. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (2); 50 Mbps (0); 100 Mbps (4); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | Rights of Way: Expected to be secured as necessary for ongoing construction. Construction Permits and Other Approvals: Expected to be secured as necessary for ongoing construction. Equipment Procurement: Vendor/RFP/procurement activities will continue for next construction phase. Network Build: Expect to continue installation of DWDM and Ethernet into PoP site shelters, as well as test, splice, light, and contribute additional miles of in-kind fiber to the project. Receiving and paying for construction invoices of Phase 4 through Q4 2013. Equipment Deployment: Expect to connect the next wave of new CAIs after construction of fiber laterals. Continue negotiation of additional Interconnection Agreements. Community Outreach: Campaign efforts continue with local media and will include participation with initiative partners for coordination of planned broadband development, accessibility and sustainability. Sho-Me will be attending the â€œMoBroadbandNowâ€ Broadband Telemedicine Summit in St. Louis on May 20, 2013 which features interactive panel discussions on healthcare needs, rural issues, policy updates, and electronic health information systems. Sho-Me is seeking participation with the Wireless Internet Service Providers Association (WISPA) regional meetings. WISPA promotes the development, advancement and unification of the wireless Internet service provider industry. WISPA has over 600 members consisting of wireless Internet service providers, municipal wireless Internet providers, electric and telephone cooperative wireless Internet providers, equipment manufacturers, service vendors and other interested parties. Sho-Me's planned project accomplishments through Q2 2013: â€¢ New network miles deployed next quarter- 9 miles: bringing total new network miles to 500. â€¢ New network miles leased next quarter - 0 miles (not planned). â€¢ In-kind network miles upgraded - 88 miles: bringing total in-kind network miles to 880. â€¢ Total CAI subscribers connected next quarter - 26 CAIs: bringing total CAIs to 102 CAIs. â€¢ No additional signed agreements with broadband wholesalers or last mile providers are anticipated for next quarter. Total is expected to remain at 7 agreements. | SHO-ME Technologies, L.L.C. | In early 2011, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely rights of way and permitting required for fiber route construction. | In early 2011, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely rights of way and permitting required for fiber route construction. In previous quarters fiber availability was a concern. However, Sho-Me not longer believes fiber availability poses a threat to Sho-Me's project success. | TRUE
NT10BIX5570146 | 2013 | Q2 | Q2 - 2013 | a) Special Award Condition (SAC) accomplishments and reporting: [i] Issuance, submittal and approval of Section 1512 American Recovery and Reinvestment Act (ARRA) Prime Recipient Report and Sub-Recipient Report for 1st Quarter 2013. [ii] Issuance, submittal and approval of Federal Financial Report (FFR) Standard Form 425 (SF-425) for 1st Quarter 2013. [iii] Issuance, submittal and approval of Performance Progress Report (PPR) for 1st Quarter 2013. [iv] Receipt of Department of Commerce (DoC) Award Closeout Notification Packet and SAC checklist. Engagement in update discussions with FPO and BTOP Team regarding administrative processes and legal requirements. [v] BTOP Project Closeout Processes and Federal Security Interest obligations and documentation requirements started, including Asset Tracking and Tagging processes, preparation of Property Status Reports (SF-428 and SF-429), Covenants of Use and UCC-1 Statement filings. Continued participation with DoC, NTIA, and NOAA Grant Office in Closeout Process update conferences. [vi] Participation in the data collection efforts of the 'MoBroadbandNow" State Broadband Data Mapping Program in accordance with the NOFA. [vii] Submittal of 1st Quarter 2013 project tracking report as requested by the State of Missouri "MoBroadbandNow" Project in accordance with NTIA's State Broadband Initiative (SBI). [viii] Ongoing Principal Investigator (PI/PD) oversight activities, including compliance oversight, field inspections of construction throughout the project, monthly team update meetings, ongoing Davis-Bacon Act SF-1445 labor standards interviews of construction crews by Sho-Me personnel, and conference calls with FPO and BTOP Team. PI/PDs participated in the BTOP webinars covering Federal Security Interest, Award Closeout Processes, Economic Development Planning, Benefits and Impact, and Interconnection. b) Overall Project Accomplishments: [i] Fiber construction continued resulting in an additional 24 miles of fiber during the quarter bringing our new fiber construction total to 515 miles. Continued procedures for Indefeasible Rights of Use (IRU) on several fiber route segments. An additional 78 miles of in-kind fiber was contributed to the BTOP Project, bringing total in-kind miles to 870. The progress in 2nd Quarter 2013 brings overall BTOP Project total of underground and aerial fiber to 1,385 miles. [ii] Completed installation and commissioning of DWDM equipment on 4 routes between Points of Presence (PoP) locations: Rolla to Licking, Springfield AECI to Bolivar, Bolivar to Buffalo, and Cabool to Houston. [iii] Completed construction of Request for Bid (RFB) #SMM021 for installation of fiber laterals into 23 Community Anchor Institutions (CAIs) along several middle mile routes. [iv] Completed splicing and testing after construction of 28 miles of new fiber on the "Springfield to Bolivar" route and 29.65 miles of new fiber on the "Marshfield to Preston" route. [v] Installation of security equipment for telecom shelters continues at new PoP locations. [vi] An RFB #SMM025 was prepared, let, awarded, and started for construction and installation of fiber laterals into 15 remaining CAIs. [vii] Secured all known and necessary permits for fiber construction routes within rights of way from federal, state and local agencies. [viii] Successful Community Outreach is continuing with participation in live interviews on local radio stations. Weekly newsletter updates are posted to the "Sho-Me MO" Project website and are distributed via e-mail. Sho-Me actively participated in the inaugural Broadband Telemedicine Summit in St. Louis, took an active role in the Broadband Community Summit on FTTH projects in communities with "Sho-Me MO" BTOP Project PoP locations, and participated with Association of Rural Electric Cooperatives' annual event held with State Legislative Offices on the Capital lawn updating Senators and Representatives on the "Sho-Me MO" BTOP Project. Sho-Me continues serving on the task force for Regional Technology Planning Teams, participates with the State MOBroadbandNOW and Missouri's Department of Elementary and Secondary Education on the implementation of CORE in the state of Missouri, and is expanding participation with the Governor's Conference on Agriculture entitled "Ag Now" in panel discussion meeting working with other service providers and the State with the goal to expand Broadband's impact on the agricultural community of rural Missouri. | 515 | 0 | 870 | 0 | 515 | 0 | 0 | 34 | Above baseline of 500 due to previously approved route modifications. | N/A | Below baseline of 880 due to unforeseen fiber availability constraints from manufacturers in 2011 which also offset our ability to splice in-kind segments to pending new fiber builds. Ongoing testing of remaining in-kind fiber continues toward baseline goal of 880 miles. Sho-Me anticipates slightly exceeding baseline next quarter due to previously approved route modifications. | N/A | Above baseline of 500 due to previously approved route modifications. | N/A | N/A | Above baseline of 33. Sho-Me contributed an additional PoP location existing along a previously approved route modification. | 7 | 41 | 12 | Missouri State Office of Administration, Missouri Research and Education Network, Missouri Office of State Courts Administrator, Jefferson City Medical Group, Missouri Wi-Fi, Mid-Missouri Broadband, Central Missouri Computer Services. Sho-Me has multiple agreements with many of the aforementioned providers. Negotiations with other additional providers are in process with no final determination at this time, however, commitments are likely nearer to the project completion date. | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence. | N/A | 5 | 2 | 0 | 7 | Above plan due to more providers receiving new access than anticipated. Negotiations with other additional providers are in process with no final determination at this time, however, commitments are expected after the project completion date. | Below plan due to more providers receiving new access than anticipated. Negotiations with other additional providers are in process with no final determination at this time, however, commitments are expected after the project completion date. | No variance. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (1); 40Mbps (1); 45Mbps (1); 50 Mbps (1); 100 Mbps (2); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 99 | 68 | 31 | 7 | Below baseline by 1 due to unforeseen fiber availability constraints from manufacturers in 2011, however Sho-Me has received all fiber ordered for the project. CAI installations are underway to meet baseline of 101 by end of Award Period in the 3rd Quarter 2013. | Above plan as more CAIs will actually be in the new vs. improved category and due to delay in fiber, however, Sho-Me has received all fiber ordered for the project. CAI installations are underway to meet baseline of 100 by end of Award Period in 3rd Quarter 2013. | Below plan as more CAIs will actually be in the new vs. improved category and due to delay in fiber, however, Sho-Me has received all fiber ordered for the project. CAI installations are underway to meet baseline of 100 by end of Award Period in 3rd Quarter 2013. | 5 Mbps (0); 10 Mbps (1); 20 Mbps (2); 50 Mbps (0); 100 Mbps (4); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | a) Special Award Condition (SAC) accomplishments and reporting: [i] Issuance, submittal and approval of Section 1512 American Recovery and Reinvestment Act (ARRA) Prime Recipient Report and Sub-Recipient Report for 2nd Quarter 2013. [ii] Issuance, submittal and approval of Federal Financial Report (FFR) Standard Form 425 (SF-425) for 2nd Quarter 2013. [iii] Issuance, submittal and approval of Performance Progress Report (PPR) for 2nd Quarter 2013. [iv] Preparation and submittal of Department of Commerce Award Closeout Notification Packet and continued engagement in ongoing update discussions with FPO and BTOP Team regarding administrative processes and legal requirements. [v] Continuation of Closeout Processes including Asset Tracking and Tagging processes, Property Status Reports (SF-428 and 429), Covenants of Use and UCC-1 filing preparations. Ongoing participation with NTIA in Closeout Process update conferences. [vi] Participation in the data collection efforts of the 'MoBroadbandNow" State Broadband Data Mapping Program in accordance with the NOFA. [vii] Submittal of 2nd Quarter 2013 project tracking report as requested by the State of Missouri "MoBroadbandNow" Project in accordance with NTIA's State Broadband Initiative (SBI). [viii] Ongoing Principal Investigator (PI/PD) oversight activities, including compliance oversight, field inspections of construction throughout the project, monthly project team update meetings, reporting and update conferences with FPO and BTOP Team and participation in the BTOP webinar updates. b) Overall Project Accomplishments: [i] Rights of Way: Sho-Me expects no further activity in this category. [ii] Construction Permits and Other Approvals: Sho-Me expects no further activity in this category. [iii] Equipment Procurement: Sho-Me expects to complete vendor/RFP/procurement activities for last construction project. [iv] Network Build: Sho-Me expects to test, splice, light, and contribute final additional miles of in-kind fiber to the project. Expect to complete installation and commissioning of remaining procured DWDM equipment on 6 major routes between Points of Presence (PoP) locations. Sho-Me is scheduled to complete installation and commissioning of procured Ethernet equipment into remaining CAIs and PoP site shelters. Sho-Me expects to finalize receiving and paying for construction invoices of Phase 4 in post-award period in 4th Quarter 2013. [v] Equipment Deployment: Sho-Me expects to connect the last two new CAIs after construction of fiber laterals is completed in early August 2013. Sho-Me expects to continue negotiations of additional Interconnection Agreements. Sho-Me plans to complete installation of security equipment for telecom shelters at new PoP locations. [vi] Community Outreach: Sho-Me expects campaign efforts to continue with local media and to include participation with initiative partners for coordination of planned broadband development, accessibility and sustainability. Sho-Me expects Weekly newsletter updates to be posted to the "Sho-Me MO" Project website and distributed via e-mail. The Buffalo Reflex newspaper plans to release a follow-up article on the "Sho-Me MO" BTOP Project. Sho-Me will be working directly with Miller County government on opportunities for its communities to work with Wireless Internet Service Providers (WISPs) or become their own ISP to expand connectivity to remote areas of their county. Sho-Me also plans to work with a regional WISP on possible connections with the County's remote offices. Sho-Me's planned project accomplishments through 3rd Quarter 2013: â€¢ New network miles deployed next quarter - 3 miles (bringing total new network miles to 518). â€¢ New network miles leased next quarter - 0 miles (not planned). â€¢ In-kind network miles upgraded - 10 miles (bringing total in-kind network miles to 880). â€¢ Total CAI subscribers connected next quarter - 2 CAIs (bringing total CAIs to 101). â€¢ No additional signed agreements with broadband wholesalers or last mile providers are anticipated for next quarter. Total is expected to remain at 7 agreements. | SHO-ME Technologies, L.L.C. | In early 2011, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely rights of way and permitting required for fiber route construction. | In early 2011, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely rights of way and permitting required for fiber route construction. In previous quarters fiber availability was a concern. However, Sho-Me not longer believes fiber availability poses a threat to Sho-Me's project success. | TRUE
NT10BIX5570146 | 2013 | Q3 | Q3 - 2013 | a) Special Award Condition (SAC) accomplishments and reporting through end of Award period August 31, 2013: [i] Issuance, submittal and approval of Section 1512 American Recovery and Reinvestment Act (ARRA) Prime Recipient Report and Sub-Recipient Report for 2nd Quarter 2013. [ii] Issuance, submittal and approval of Federal Financial Report (FFR) Standard Form 425 (SF-425) for 2nd Quarter 2013. [iii] Issuance, submittal and approval of Performance Progress Report (PPR) for 2nd Quarter 2013. [iv] Processing of Department of Commerce (DoC) Award Closeout Notification Packet and SAC checklist. Continuous engagement in update discussions with FPO and BTOP Team regarding administrative procedures and legal requirements of Closeout. [v] BTOP Project Closeout Processes and Federal Security Interest obligations and documentation requirements started, including Asset Tracking and Tagging processes, preparation of Property Status Reports (SF-428 and SF-429), Covenants of Purpose, Use and Ownership, and UCC-1 Statement filings. Continuous participation with DoC, NTIA, and NOAA Grant Office in Closeout Process update conferences. [vi] Participation in the data collection efforts of the 'MoBroadbandNow" State Broadband Data Mapping Program in accordance with the NOFA. [vii] Submittal of 2nd Quarter 2013 project tracking report as requested by the State of Missouri "MoBroadbandNow" Project in accordance with NTIA's State Broadband Initiative (SBI). [viii] Ongoing Principal Investigator (PI/PD) oversight activities, including compliance oversight, performing field inspections of construction throughout the project, hosting monthly team update meetings, ongoing Davis-Bacon Act SF-1445 labor standards interviews of construction crews by Sho-Me personnel, and conference calls with FPO and BTOP Team. PI/PDs participated in the BTOP conferences and webinars regarding Award Closeout Processes. b) Overall Project Accomplishments through end of Award period August 31, 2013: [i] Fiber construction continued resulting in an additional 25 miles of fiber during the quarter bringing the "Sho-Me MO" BTOP Project's new fiber construction total to 540 miles. Continued procedures for Indefeasible Rights of Use (IRU) on several fiber route segments. An additional 84 miles of in-kind fiber was contributed to the Project, bringing total in-kind miles to 954. Sho-Me exceeded its original target reaching overall Project total of underground and aerial fiber to 1,494 miles. [ii] Completed installation and commissioning of DWDM equipment on remaining routes between Points of Presence (PoP) locations: Reeds Spring, Branson GFRC, Branson UG, Cuba, Washington, Nixa and Mansfield. [iii] Completed construction of Request for Bid (RFB) #SMM025 for installation of fiber laterals into 15 Community Anchor Institutions (CAIs) along several middle mile fiber routes. [iv] Installation of security equipment for telecom shelters continued at new PoP locations. [v] Performed physical asset tracking, tagging and recording of BTOP inventory into Sho-Me's property management system. [vi] Secured all known and necessary permits for fiber construction routes within rights of way from federal, state and local agencies. [vii] Successful Community Outreach is continuing with participation in live interviews on local radio stations. Weekly newsletter updates are posted to the "Sho-Me MO" BTOP Project website http://www.shometech.com and are distributed via e-mails. | 540 | 0 | 954 | 0 | 540 | 0 | 0 | 34 | Above baseline of 500 route miles due to previously approved route modifications. | N/A | Above baseline of 880 route miles. | N/A | Above baseline of 500 route miles due to previously approved route modifications. | N/A | N/A | Above baseline of 33. Sho-Me contributed an additional PoP location existing along a previously approved route modification. | 13 | 45 | 12 | Missouri State Office of Administration, Missouri Research and Education Network, Missouri Office of State Courts Administrator, Jefferson City Medical Group, Missouri Wi-Fi, Mid-Missouri Broadband, Central Missouri Computer Services, Integrated Solutions Group, Socket Telecom, Total Highspeed, Simpson Technology, Laclede County R-I School District and Your Hometown Internet. Sho-Me has multiple agreements with many of the aforementioned providers. Negotiations continue with additional providers. | Sho-Me MO project offers Dedicated Internet Access, Time Division Multiplexing (TDM) circuits available at line rates from T-1 to OC-48, native Ethernet products from 5 Mb/s to GigE, Optical Wave Services available in 2.5 Gb/s and 10 Gb/s line rates for express routes between Points of Presence (PoPs). | N/A | 11 | 2 | 0 | 14 | Above plan due to more providers receiving new access than anticipated. Negotiations with other additional providers are in process with no final determination at this time, however, commitments are expected after the project completion date. | Below plan due to more providers receiving new access than anticipated. Negotiations with other additional providers are in process with no final determination at this time, however, commitments are expected after the project completion date. | No variance. | 5 Mbps (1); 10 Mbps (4); 20 Mbps (2); 40Mbps (1); 45Mbps (1); 50 Mbps (1); 100 Mbps (4); 200 Mbps (0); 500 Mbps (0); GigE (0); DS1 (0); DS3 (0); OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 101 | 70 | 31 | 74 | Above baseline by 1 per approved Award Action Request (AAR). CAI installations meet baseline by end of Award Period in the 3rd Quarter 2013. | Above plan as more CAIs will actually be in the new vs. improved category and due to delay in fiber, however, Sho-Me has received all fiber ordered for the project. CAI installations meet baseline by end of Award Period August 31, 2013 in 3rd Quarter 2013. | Below plan as more CAIs will actually be in the new vs. improved category and due to delay in fiber, however, Sho-Me has received all fiber ordered for the project. CAI installations meet baseline by end of Award Period August 31, 2013 in 3rd Quarter 2013. | 5 Mbps (6); 10 Mbps (39); 20 Mbps (11); 50 Mbps (5); 100 Mbps (12); 200 Mbps (0); 500 Mbps (0); GigE (1); DS1 (0); DS3 (0);OC-3 (0); OC-12 (0); OC-48 (0); 2.5 Gbps (0); 10 Gbps (0) | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | None at this time. | FALSE | N/A | a) Special Award Condition (SAC) accomplishments, reporting and Closeout activities: [i] Issuance, submittal and approval of Final Section 1512 American Recovery and Reinvestment Act (ARRA) Prime Recipient Report and Sub-Recipient Report, Final Federal Financial Report (FFR) Standard Form 425 (SF-425), Final Performance Progress Report (PPR) and Annual PPR (APR) for 2013. [ii] Processing of Department of Commerce (DoC) Award Closeout Notification Packet and SAC checklist. Engagement in update discussions with FPO and BTOP Team regarding administrative processes and legal requirements. [iii] BTOP Project Closeout processes and Federal Security Interest obligations and documentation requirements started, including Asset Tracking and Tagging processes for BTOP property management, preparation of Property Status Reports (SF-428 and SF-429), Covenants of Purpose, Use and Ownership, and UCC-1 Statement filings. Continuous participation with DoC, NTIA, and NOAA Grant Office in Closeout Process update conferences. [iv] Participation in the data collection efforts of the 'MoBroadbandNow" State Broadband Data Mapping Program in accordance with the NOFA. Submittal of Final project tracking report as requested by the State of Missouri "MoBroadbandNow" Project in accordance with NTIA's State Broadband Initiative (SBI). [v] Ongoing Principal Investigator (PI/PD) oversight activities, including compliance oversight, team update meetings, and conference calls with FPO and BTOP Team. PI/PDs expect to continue to participate in the BTOP webinars regarding Award Closeout Processes. b) Technology, initial impacts and immediate benefits to rural communities upon "Sho-Me MO" BTOP Project completion: [i] The NTIA investment in the "Sho-Me MO" BTOP Project expands Broadband availability geographically to an additional 26% to 29% percent of the State of Missouri. The "Sho-Me MO" BTOP Project creates a new 1,494 mile "backbone" middle-mile network reaching 34 PoP locations across thirty counties of largely rural Missouri most in need of connectivity and reliability. [ii] This middle-mile fiber network is equipped with a state-of-the-art optical Dense Wavelength Division Multiplexing (DWDM) data transport platform with multi-degree Reconfigurable Optical Add-Drop Multiplexer (ROADM) technology, Multi Protocol Label Switching (MPLS) features, and future support of 100G. [iii] Along the middle-mile fiber routes built through rural Missouri for the BTOP Project are last-mile "lateral" fiber connections reaching 101 Community Anchor Institutions (CAIs) approved by the NTIA. These key stakeholders include 30 K-12 schools, 13 public libraries, 13 public safety entities, 28 other government agencies, 3 community colleges, 3 higher education institutions, and 11 medical and healthcare providers. [iv] This last-mile fiber network is equipped with 10G carrier-grade Ethernet transport switches with MPLS features installed at 34 PoPs designed to support 43 protected fiber spans, plus Ethernet nodes at the 101 CAIs. [v] In cooperation with the Missouri Department of Elementary and Secondary Education (DESE), the "Sho-Me MO" BTOP Project delivers Broadband connections enabling over 30 rural K-12 schools to significantly improve bandwidth as required for the State's adoption of the "Common-Core" State Standards initiative. [vi] Because of the "Sho-Me MO" BTOP Project, two rural K-12 school districts previously with only 4.5Mbps for their respective districts now have affordable 100Mbps Broadband access. Such Broadband speed and capacity are required to apply for and secure a funding to implement "One-to-One" (1:1) educational technology initiatives which according to one district superintendent are making a huge impact on the success of students. [vii] Two community colleges have expanded their reach of online course offerings enabling rural students the opportunity to access higher education because of their Broadband connection to the "Sho-Me MO" BTOP Project. [viii] Rural county courthouses connected to newly available Broadband access of the "Sho-Me MO" BTOP Project are consolidating their respective networks and providing higher speeds on a more secure and reliable network thereby improving services for and savings to their local taxpayers. [ix] Ten entities including wholesale and last-mile providers are able to expand high speed Broadband offerings to reach more remote service areas because of the "Sho-Me MO" BTOP Project presence through their rural communities. [x] Two manufacturing firms have expressed being saved from relocating their operations away from their rural communities, avoiding devastation to their local economies, saving jobs and enabling growth of their business because the arrival of affordable high-speed Broadband services considered critical for their survival are now available from the "Sho-Me MO" BTOP Project. | SHO-ME Technologies, L.L.C. | In early 2011, the Missouri Department of Transportation (MoDOT) announced closing 135 facilities and downsizing its staff size by 1,200 employees which may become a potential constraint on securing timely rights of way and permitting required for fiber route construction. | None at this time. | TRUE
NT10BIX5570148 | 2010 | Q4 | Q4 - 2010 | Specific items of equipment were identified and RFP's were issued to equipment vendors. We requested and obtained approval for our 6-month pre EA budget, on condition that we do not break ground with it. We will request that it be used for hands-on training of our new installation crews once it arrives in the Ronan Telephone Company equipment yard. We are in continuing discussions/negotiations with the two Tribes in our project regarding the Tribal Employment Rights Ordinances (TERO), which is a fee paid to the tribe in the form of a percentage of the Federal funds expended on the Reservation. Many contacts have been made and information exchanged between our two EA consultants and the appropriate agencies at the Federal, State, Tribal and County levels, with good progress being made. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baseline showed zero for this quarter | Baseline showed zero for this quarter | Baseline showed zero for this quarter | Baseline showed zero for this quarter | Baseline showed zero for this quarter | Baseline showed zero for this quarter | Baseline showed zero for this quarter | Baseline showed zero for this quarter | 0 | 2 | 0 | We have no signed agreements yet. | No services are being provided yet...plans are to offer 100Mb and 1Gb services to other providers and last mile providers. We have received requests for quotes for dark fiber IRU's along some parts of our planned route in Western Montana, and are entering into negotiations with these providers. | Cutthroat Communications in Bozeman will provide monitoring of our network at their Network Operating Center at: 7330 Shedhorn Drive, Bozeman, MT 59718 The contact for Cutthroat Communications is JP Violette, and he can be reached at 406-556-1737 They will be operating as a contractor for the purposes of this project. | 0 | 0 | 0 | 0 | No Variance. We have not installed anything yet. | No Variance. We have not installed anything yet. | No Variance. We have not installed anything yet. | No Variance. We have not installed anything yet. | 0 | 0 | 0 | 0 | No Variance. We have not installed anything yet. | No Variance. We have not installed anything yet. | No Variance. We have not installed anything yet. | No Variance. We have not installed anything yet. | 0 | 0 | 0 | 0 | 0 | No Variance. We have not installed anything yet. | No Variance. We have not installed anything yet. | No Variance. We have not installed anything yet. | No Variance. We have not installed anything yet. | No Variance. We have not installed anything yet. | 0 | 0 | 0 | 0 | 0 | No Variance. We have not installed anything yet. | No Variance. We have not installed anything yet. | No Variance. We have not installed anything yet. | No Variance. We have not installed anything yet. | No Variance. We have not installed anything yet. | We are not anticipating service offerings outside the normal telecom and ethernet offerings at this time. | FALSE | We have made no changes to our network management practices. | We are in the next quarter following the period of this report. (1/1/2011 through 3/31/2011), or Q3 year1. We anticipate finishing the EA, gaining ground on the rights of way for our first construction routes, getting some permitting so we can get started in the April 2011 timeframe, getting sub-recipient status for Montana West under RTC, so we can start a drawdown for construction equipment procurement, and hiring and training of the new installation crews from the Reservations. We continue to make progress with our negotiations with the Tribes on the TERO and easement issues. | Ronan Telephone Co. | We need to have our sub-recipient assignment request approved so that we can draw down funds from our pre EA budget for equipment procurement and training of the installation crews. We are having a hard winter here in Montana, particularly in the Mission Valley, where the snow that usually melts periodically, is staying on the ground. This may delay our start date in the Mission Valley. | The three major factors that could impact planned progress are: 1. The weather, (we are having a hard winter relative to ground freeze) 2. EA completion ..we have submitted our draft EA and expect to complete by the end of February or early March, depending on responsiveness of the appropriate Governmental agencies. 3. Equipment procurement delays relative to our ability to drawdown as Montana West...resulting in delays in training and actual construction start. That is now past us as we have received approval of our sub-recipient status for Montana West. We are anxious to start, and will begin construction as soon as these issues are resolved/completed. | TRUE
NT10BIX5570148 | 2011 | Q1 | Q1 - 2011 | We are nearing the end of the EA process, with the Cultural Resource Studies delivered to both the Salish and Kootenai and the Blackfeet Tribes, and the State Historical Preservation Officer for Montana. We are presently waiting on response from these entities to determine what if any mitigation measures they will recommend prior to approval. These studies will be delivered in 11Q2, so we expect responses by in 11Q2 at the latest. We have procured some major pieces of equipment, and are interviewing tribal applicants for the construction crew, also in Q2. We are continuing to work on rights of way and easement issues on the reservations, and are planning on shifting resources from the Blackfeet to the Mission side to the front of the construction schedule as it looks like it will take longer to obtain rights of way on the Blackfeet. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baseline projected 4. We anticipate starting in June, following receipt of a FONSI from NTIA. | N/A | No Variance | No Variance | No Variance | No Variance | N/A | Baseline projected 1. We have not started yet due to delays in the EA effort. | 0 | 2 | 0 | We have no signed agreements yet. | No services are being provided yet. Plans are to offer 100Mb and 1Gb services to other providers and last mile providers. We have responded to a major RFP for dark fiber IRU's to a major hospital consortium in Western Montana and are waiting on the results. | Cutthroat Communications in Bozeman will provide monitoring of our network at their Network Operating Center at 7330 Shedhorn Drive, Bozeman, MT 59718 Cutthroat Communications contact is JP Violette, at 406-556-1737 Cutthroat will be operating as a contractor for the purposes of this project. | 0 | 0 | 0 | 0 | No Variance. No installations yet. | No Variance. No installations yet. | No Variance. No installations yet. | No Variance. No installations yet. | 0 | 0 | 0 | 0 | No Variance. No installations yet. | No Variance. No installations yet. | No Variance. No installations yet. | No Variance. No installations yet. | 0 | 0 | 0 | 0 | 0 | No Variance. No installations yet. | No Variance. No installations yet. | No Variance. No installations yet. | No Variance. No installations yet. | No Variance. No installations yet. | 0 | 0 | 0 | 0 | 0 | No Variance. No installations yet. | No Variance. No installations yet. | No Variance. No installations yet. | No Variance. No installations yet. | No Variance. No installations yet. | We do not anticipate service offerings outside the normal telecom and ethernet offerings at this time. | FALSE | We have made no changes to our network management practices. | We are now planning on completion of the EA and obtaining a FONSI in June. Construction will start at that time. Equipment and material is being procured according to Federal Government procurement guidelines (RFPs), and construction crew interviewing and hiring is scheduled early during the month of May. Because of the delay caused by the EA process, we are taking steps to ensure that we have the equipment, personnel, material (fiber), and permits to get started as soon as we have the EA behind us. Our consultants are finalizing the specifications for the core network hardware and transport equipment and will have an RFP to release by mid-May. | Ronan Telephone Co. | We are experiencing delays in obtaining easements for our proposed fiber route on the Blackfeet Reservation, due to BIA rules regarding Tribal allotments along the State Highway right of way. There are many owners of these parcels that need to be contacted for consent to easements for the installation of new fiber. Normally utilities are allowed to use the utility corridor along State highways that are set aside for this purpose. This apparently is not the case on the Blackfeet and we are having to shift construction effort for the Blackfeet to a later time frame in the schedule, in order to meet the overall project deadline of August 2013. | The two major hurdles now are the completion of the EA process, and resolution of tribal rights of way and easements on the Blackfeet reservation fiber routes. Depending on the responses we get from the tribes on the cultural preservation studies, we may need to work out a "Programmatic Agreement" with the Blackfeet in order to get the construction started. Rights of way on the Blackfeet involves finding and contacting all of the allottees who own a parcel along the intended route, and obtaining their consent for an easement on their property. Some of the parcels have a large number of owners and this will take more time and money than we anticipated, but we are working through it with the BIA and the Tribe. | TRUE
NT10BIX5570148 | 2011 | Q2 | Q2 - 2011 | The final EA reports were turned in. We are awaiting the official word on the FONSI which should be here by 7/5/2011. We have hired 2 crews of 7 men each and will begin training on 7/11/11. Enough equipment has been purchased this quarter to put both crews to work. Most activity other than engineering and route planning was put on hold until we receive the FONSI. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Projected 73 miles--delayed by EA | No Variance | Projected 106 Redundant Loop delayed by EA | Projected 321--delayed by EA | Projected 499--delayed by EA | No Variance | N/A | Projected 7--delayed by EA | 0 | 2 | 0 | NA | No services provided yet. Plans are to offer 100 MB and 1 GB services to other providers and last mile providers. We have responded to a major RFP for dark fiber IRUs to a major hospital consortium in Western Montana and are waiting on the results. | Cutthroat Communications in Bozeman will provide monitoring of our network at their Network Operating Center at 7330 Shedhorn Drive, Bozeman, MT 59718. Contact is JP Violette at 406-556-1737. Cutthroat will be operating as a contractor for the purpose of this project. | 0 | 0 | 0 | 2 | No Variance | Projected 1--delayed by EA | No Variance | 100MB and 1 GB | 0 | 0 | 0 | 4 | Projected 1--delayed by EA | No Variance | Projected 1--delayed by EA | 10 MB, 20 MB, 50 MB, 100 MB | 0 | 0 | 0 | 0 | 3 | Projected 800--delayed by EA | Projected 188--delayed by EA | Projected 16--delayed by EA | Projected 172--delayed by EA | 1.5 MB, 2.5 MB, 4 MB | 0 | 0 | 0 | 0 | 4 | Projected 66--delayed by EA | Projected 5--delayed by EA | Projected 1--delayed by EA | Projected 4--delayed by EA | 10 MB, 20 MB, 50 MB, 100 MB | We do not anticipate any special offerings other than wholesale bandwidth and Internet connectivity to other providers and to businesses and anchor institutions. | FALSE | NA | We expect to sign up at least two major providers in Western Montana, and install 30 to 40 miles of fiber along our major route. | Ronan Telephone Co. | The EA is in the final review stage and will be approved the first week in July. Crews are hired and materials purchased. We will start full scale construction in 2 weeks. The first quarter 2011 PPR Report was completed incorrectly. We did not understand the report layout and did not tie it to the Narrative Budget. This quarter we understood the report and made the changes to the Infrastructure Budget Execution Details to coincide with the Narrative Budget. Following is a list of the changes. Changes to the Infrastructure Budget Execution Details/Activity Based Expenditures. "Budget for Entire Project"-- moved 100% of the Matching Funds to line (a) to match Detailed and Narrative Budgets. Moved $19469 reported last quarter from line (d) in Actuals to line (b) as per Narrative Budget. Moved $1,080,416 reported last quarter from line (i) in Actuals to line (a) as per Narrative Budget. Re populated the Anticipated actuals with 100% of the matching funds in line (a). Recorded 100% of the In-Kind Match in the Anticipated Actuals for next quarter. | We are still working on the resolution of Tribal right of way and easement issues on the Blackfeet reservation fiber routes. Obtaining permits may slow our progress due to the right of ways on water ways and canals. We will need additional wetland deliniations. We also have to do a cultural assessment along the Blackfeet route that may slow our progress. | TRUE
NT10BIX5570148 | 2011 | Q3 | Q3 - 2011 | We received our FONSI on July 5, 2011, and trained the tribal crews and started construction. We have completed 35 miles of fiber installation in the Mission Valley. Worked with the Montana Department of Transportation (MDOT) to establish a permitting schedule in line with our project schedule. Received authorization from the BIA to work with MDOT directly for permitting on State highways on the Blackfeet Reservation. Issued RFP's and received responses for Principal Archeological Investigator for the cultural walk-through on the Blackfeet. Ordered and received Juniper core routers for Missoula and Seattle. Negotiating contracts for Internet backhaul with upstream providers. Secured a contract with a company to provide dark fiber once in place. | 35 | 0 | 106 | 0 | 35 | 0 | 0 | 0 | Projected 109...(35 built) Overall project start delayed by the Environmental Assessment. | Projected 0..no variance | Projected 106.. (106 in kind match) | Projected 321..We will finalize the IRU contract by the end of the year 2011. | Projected 534...Delays associated with EA | Projected 2...Overall project delay associated with EA | N/A | Projected 9...Overall project delay associated with EA | 1 | 1 | 12 | Cablevision (Bresnan) | 20-year prepaid IRU for 2 dark fibers..will prepay in lump sum when installed and accepted. Contract includes interim provision of (5Gb) circuits out of Missoula to Charlo and Kalispell, which Montana West is leasing from another provider. Delivery of these interim circuits occurred on 09/27/11. | Cutthroat Communications in Bozeman will provide monitoring of the Montana West Network at their Network Operating Center at 7330 Shedhorn Drive, Bozeman, MT 59718. Contact is JP Violette at 406-556-1737. Cutthroat will be operating as a contractor for the Network monitoring of this project. | 0 | 0 | 1 | 2 | Projected 0...No variance | Projected 2..Delays with project implementation have impacted negotiations | Projected 0...A provider has agreed to buy dark fiber on an IRU when available...executed contract | 100Mb and 1Gb | 0 | 0 | 0 | 2 | Projected 2...Delays with project implementation have impacted negotiations | Projected 0..no variance | Projected 1...Delays with project implementation have impacted negotiations | 100Mb and 1Gb | 0 | 0 | 0 | 0 | 3 | Projected 950..timeline delayed by EA | Projected 233..timeline delayed by EA | Projected 24..timeline delayed by EA | Projected 209..timeline delayed by EA | 1.5Mb, 2.5Mb, 4Mb | 0 | 0 | 0 | 0 | 4 | Projected 102..timeline delayed by EA | Projected 23..timeline delayed by EA | Projected 4..timeline delayed by EA | Projected 19..timeline delayed by EA | 10Mb, 20Mb, 50Mb, 100Mb | We do not anticipate any special offerings other than wholesale bandwidth and Internet connectivity to other providers and to businesses and anchor institutions. | FALSE | N/A | We intend to complete the fiber section between Missoula and St. Ignatius, connecting to existing service in the Mission Valley at that location. We will also be able to offer bandwidth to CAI's in the Spring of 2012. Marketing activities will step up next quarter in anticipation of having a service to offer. We will have part of the route on the Blackfeet (between Cut Bank and Browning) staked, permitted and ready to go when the ground thaws and we have fiber from the manufacturers. | Ronan Telephone Co. | We had some initial equipment breakage due to the difficult rocky terrain. Permitting from the Department of Transportation has been slow and we have had to adjusts the schedule as a result. We are now ahead of the permitting procedure and this should not be a problem as long as we stay ahead (providing final road maps with plans). Fiber is scarce or not available, and we are adjusting our schedule and putting in conduit more than we anticipated. We will have to go back and pull fiber once it is available. Work on the Blackfeet has been delayed due to permitting and cultural/archeological stipulations by the BIA. We do not anticipate having fiber for the Blackfeet until February or March anyway, although work is continuing on final route designation, staking and cultural pedestrian surveys of the intended routes. We have experienced cost overruns in some categories, however the budget is sufficient to handle these overruns, and these overruns are under 10% of the overall project. We anticipated starting construction on the Blackfeet Reservation by this quarter, but delays associated with permitting and cultural issues has delayed this startup. As a result our anticipated actuals in the construction category did not change, and we do not intend to purchase the remaining equipment until the Spring of 2012. | We are entering our winter season, where construction may be halted due to ground freeze. Fiber availability may become a factor even if we were to get some extended construction time due to a warm winter. In some cases, we are installing conduit in the ground without fiber so that when we do obtain fiber we will be able to pull it into the conduit, having finished the more time consuming part of the install with available materials. | TRUE
NT10BIX5570148 | 2011 | Q4 | Q4 - 2011 | Last quarter we installed 35 miles of actual fiber in the ground. It is our understanding that this is not to be considered deployed, in that is is one isolated segment of our complete project. This quarter we installed 33 miles of fiber and conduit, again not deployed, as this is another isolated segment of our overall plan. The 33 miles this quarter included 21 miles of actual fiber in the ground and 12 miles of conduit, since we ran out of fiber. We developed an agreement to buy privately funded excess capacity from another program, and are waiting on BTOP approval for this purchase. This will save 41 miles of build time and enable our teams to concentrate on other segments of the project. We also developed an agreement with upstream providers to purchase a link to Seattle and a link between Missoula and Cut Bank, ... waiting on BTOP approval of this project modification. Started the interview process on the Blackfeet Reservation to hire a team to install the first segment in the Spring. Contracted for a cultural walk through for our first segment between Cut Bank and Browning, which is underway. | 56 | 0 | 106 | 0 | 56 | 0 | 0 | 0 | Installed 56 miles of fiber to date, and installed 12 miles of conduit, awaiting fiber to pull through. Projected 119. These are isolated segments of our final planned installation, and therefore are not deployed as they are not useable by CAI's or other customers until the project is connected to the Internet. Overall project was delayed by the EA, with some delay associated with the weather, and fiber shortage. | Projected 0, no variance from baseline. | Projected 106, no variance (106 in kind fiber match) | Projected 320. IRU contract at BTOP for budget change approval. | Projected 544. Installed 56 miles of fiber to date, and installed 12 miles of conduit, awaiting fiber to pull through. Overall project was delayed by the EA, with some delay associated with the weather, and fiber shortage. Waiting on IRU approval from BTOP. | Projected 2. Overall project was delayed by the EA, with some delay associated with the weather, and fiber shortage. | N/A | Projected 10. Overall project was delayed by the EA, with some delay associated with the weather, and fiber shortage. | 1 | 1 | 12 | CableVision (Bresnan) | We have executed a contract with Bresnan for a 20-year prepaid IRU for 2 dark fibers. They will prepay in a lump sum shen installed and accepted. Contract includes interim provision of (5Gb) circuits, which Montana West is leasing from another provider. Delivery of these interim circuits occurred on 9/27/11. | Cutthroat Communications in Bozeman will provide monitoring of the Montana West network at their Network Operating Center at 7330 Shedhorn Dr., Bozeman, MT. 59718. This activity will transition to Montana West, once Montana West establishes its own Network Operating Center. | 0 | 1 | 1 | 2 | Projected 0, no variance from baseline | Projected 2, Waiting on approval of upstream IRU budget realignment. | Projected 0, Provider has executed an IRU agreement with Montana West for dark fiber when available. (August 2012) | 100Mb and 1Gb, no variance | 0 | 0 | 0 | 2 | Projected 7. Fiber availability, permitting and weather delayed construction. We have started installing conduit while waiting for fiber delivery. | Projected 0, no variance. | Projected 7. Fiber availability, permitting and weather delayed construction. We have started installing conduit while waiting for fiber delivery. | 100Mb and 1Gb | 175 | 0 | 0 | 0 | 3 | Projected 950. Overall project delay due to late start, permitting, and fiber shortage. These are residents passed in Evaro , Arlee and Ravalli. | Projected 233. Overall project delay due to late start, permitting, and fiber shortage. | Projected 24. Overall project delay due to late start, permitting, and fiber shortage. | Projected 209. Overall project delay due to late start, permitting, and fiber shortage. | 1.5Mb, 2.5Mb, 4Mb | 12 | 0 | 0 | 0 | 4 | Projected 102. Overall project delay due to late start, permitting, and fiber shortage. These are businesses passed in Evaro, Arlee and Ravalli. | Projected 41. Overall project delay due to late start, permitting, and fiber shortage. | Projected 12. Overall project delay due to late start, permitting, and fiber shortage. | Projected 29. Overall project delay due to late start, permitting, and fiber shortage. | 10Mb, 20Mb, 50Mb, 100Mb | We do not anticipate any special offerings other than wholesale bandwidth and Internet connectivity to other providers and to busiinesses and anchor institutions. | FALSE | N/A |  | Ronan Telephone Co. | We received a budget modification through the AAR process due to a change in matching funds. It was approved in December 2011 The infrastructure Budget Execution Detail reflects these changes. The budget modification also required adjustments in the project baseline milestones. Our main challenge this quarter has been the lack of fiber. Secondary issue was the shut down of burying acitivity due to weather. We have started placing conduit when weather permits while waiting for fiber delivery. We were able to use what fiber we could get to place aerial in those segments of our route that could not be buried, while the ground was frozen. | We are waiting on the weather which has been rather mild and allowed us to keep working a little, the biggest challenge will be if the fiber does not arrive as scheduled in February. We have no indication at this time that it will be delayed. | TRUE
NT10BIX5570148 | 2012 | Q1 | Q1 - 2012 | Construction was able to continue this quarter due to mild weather conditions. We were able to keep a small crew working most of the winter as weather permitted. Normally, we would have been shut down due to snow and frozen ground. The crews were able to almost complete the section between Missoula and St. Ignatius. There is only a few short sections of aerial to complete and we can light it up. All of the fiber needed for construction this summer has arrived. We have contracted with a company to place the fiber in the conduit buried last year. We have also hired a contractor to begin putting fiber in the ground on the Blackfeet Reservation. We are on schedule and looking forward to a great construction season. | 75 | 0 | 106 | 0 | 75 | 0 | 0 | 0 | Projected 182. Our crews are presently making good headway from Big Arm through Elmo on the way to Hot Springs. We had to work a partial crew through the winter as the ground did not permit boring during the freeze. Fiber arrived late in the quarter.We expect to catch up to our projections in the next quarter, with a contractor scheduled to begin on the Blackfeet May 7th. | Projected 0 | Projected 106, no variance (106 in kind fiber match) | Projected 321, delay associated with IRU approval, we will have both the Missoula to Cut Bank lease and the Missoula to Seattle lease in place next quarter, for a total of 797 leased miles. | Projected 182,Fiber availability and winter freeze slowed us down. We have the fiber now, and have a contractor scheduled to start on the Blackfeet May 7th. | Projected 2. Wireless is scheduled at the end of the middle mile build, so was delayed by the lack of fiber and the winter freeze also. | N/A | Projected 10. We expect to increase the connection points substantially during the next quarter, with the addition of the Missoula and the Westin fiber hotels, and the leased line to Cut Bank. | 1 | 1 | 12 | CableVision (Bresnan) | We have executed a contract with Bresnan for a 20-year prepaid IRU for 2 dark fibers. They will prepay in a lump sum when installed and accepted. Contract includes interim provision of two (5) Gb circuits, which Montana West is leasing from another provider. Delivery of these interim circuits occurred on 9/27/11. | Cutthroat Communications in Bozeman will provide monitoring of the Montana West network at their Netework Operating Center at 7330 Shedhorn Drive, Bozeman, Mt. This activity will transition to Montana West, once Montana West establishes its own Network Operating Center. | 0 | 1 | 1 | 2 | Projected 0, no variance | Projected 2, These will be online in the next quarter | Projected 0, Provider has executed an IRU agreement with Montana West for dark fiber when available. (August 2012) | 100Mb and 1Gb, no variance | 0 | 0 | 0 | 2 | Projected 22, Project delay associated with fiber availability and environmental assessments. | Projected 0 | Projected 22, Project delay associated with fiber availability and environmental assessments. | 100Mb and 1Gb | 175 | 0 | 0 | 0 | 3 | Projected 1060. Overall project delay due to late start, permitting, and fiber shortage. These are residents in Evaro, Arlee and Ravalli. | Projected 273. Overall project delay due to late start, permitting, and fiber shortage. | Projected 31. Overall project delay due to late start, permitting, and fiber shortage. | Projected 242. Overall project delay due to late start, permitting, and fiber shortage. | 1.5Mb, 2.5Mb, 4Mb | 12 | 0 | 0 | 0 | 4 | Projected 102. Overall project delay due to late start, permitting, and fiber shortage. These are businesses in Evaro, Arlee and Ravalli. | Projected 56. Overall project delay due to late start, permitting, and fiber shortage. | Projected 15. Overall project delay due to late start, permitting, and fiber shortage. | Projected 41. Overall project delay due to late start, permitting, and fiber shortage. | 10Mb, 20Mb, 50Mb, 100Mb | We do not anticipate any special offerings other than wholesale bandwidth and Internet connectivity to other providers and to businesses and anchor institutions. | FALSE | N/A | We have received all of the fiber needed for this season and will have most of the fiber placed in the conduit buried last year by the end of this quarter. The segment between Missoula and Ronan will be 100% complete and have traffic by mid quarter. The crews are working on the segment between Elmo and Nirada and will have that section completed by the end of the quarter. A site has been obtained for the building in Elmo and construction of the building is underway. Work on the Blackfeet Reservation is scheduled to begin in early May, and the segment between Santa Rita through Cut Bank, through Browning and to East Glacier will be mostly completed by the end of the next quarter, (scheduled for completion by August 2012) Project estimates by end of next quarter (end of June 2012): Number of miles deployed: 95 Number of CAI's planned to connect: 5 Number of broadband wholesaler/last mile provider agreements signed: 3 | Ronan Telephone Co. | An AAR was approved in March 2012 to move funding from the Construction Budget Line Item to the Miscellaneous Budget Line Item for an IRU change. | We are waiting on permitting from the Montana Department of Transportation to start work on the Blackfeet. No other problems are anticipated and we expect to be 73% complete by the end of this second year (August 31, 2012) | TRUE
NT10BIX5570148 | 2012 | Q2 | Q2 - 2012 | Fiber has been completed and spliced between Missoula and St. Ignatius, through Evaro, Arlee, and Ravalli. Construction is continuing to complete the fiber route in the Mission Valley between Hot Springs and Lone Pine. Weather has been cooperating and we are on schedule for completion of the southern portion of the Flathead/Mission Valley network. Transport and distribution equipment for the backbone has been ordered and is being received for the nodes along the backbone between Missoula and Kalispell. An RFP has been issued for the Network management hardware and software. A network manager has been selected and training has started. Cultural studies have been completed for the East/West portion of the network on the Blackfeet reservation. Conduit installation has been completed between Santa Rita and Cut Bank directly East of the Blackfeet reservation. Permit applications have been submitted to the Department of Transportation for the East/West route on the Blackfeet. | 110 | 797 | 106 | 0 | 110 | 0 | 0 | 3 | Projected 196. Delays on the Blackfeet Reservation impacted our construction schedule. | Projected 321. Additional miles as a result of an IRU for 10Gb to Seattle. | Projected 106, no variance (106 in kind fiber match) | Projected 0. | Projected 196. Delays on the Blackfeet Reservation impacted our construction schedule. | Projected 2. Wireless is scheduled at the end of the middle mile build, so overall project slippage has impacted it. | N/A. | Projected 14. Seattle, Missoula and Ronan at this point. Interconnection points will grow substantially with the installation of the transport equipment next quarter. | 2 | 1 | 12 | Cablevision (Bresnan) Cutthroat Communications | We have executed a contract with Bresnan for a 20-year prepaid IRU for 2 dark fibers. They will prepay in a lump sum when installed and accepted. We have executed a contract with Cutthroat Communications for the provision of 2Gb ethernet from Missoula to Seattle for a monthly recurring charge of $5600, term of 36 months. | Cutthroat Communications in Bozeman is monitoring our network at their Network Operating Center. This will transition to Montana West, once Montana West establishes its own Network Operations Center. | 0 | 2 | 1 | 4 | Projected 0. | Projected 2. Cutthroat Communications and Bresnan | Projected 0. Bresnan has executed an IRU agreement with Montana West for dark fiber when available. (August 2012) | 100mb and 1Gb and 2Gb, and dark fiber | 0 | 0 | 0 | 2 | Projected 22, Project delay associated with fiber availability and environmental assessments. | Projected 0 | Projected 22, Project delay associated with fiber availability and environmental assessments. | 100mb and 1Gb | 175 | 0 | 0 | 0 | 3 | Projected 1060. Overall project delay due to late start, permitting, and fiber shortage. These are residents in Evaro, Arlee, and Ravalli. | Projected 273. Overall project delay due to late start, permitting, and fiber shortage. | Projected 31. Overall project delay due to late start, permitting, and fiber shortage. | Projected 242. Overall project delay due to late start, permitting, and fiber shortage. | 1.5Mb, 2.5Mb, 4mb | 12 | 0 | 0 | 0 | 4 | Projected 102. Overall project delay due to late start, permitting and fiber shortage. These are businesses in Evaro, Arlee and Ravalli. | Projected 65. Overall project delay due to late start, permitting, and fiber shortage. | Projected 20. Overall project delay due to late start, permitting, and fiber shortage. | Projected 45. Overall project delay due to late start, permitting, and fiber shortage. | 10Mb, 20Mb, 50Mb, 100Mb | We do not anticipate any special offerings other than wholesale bandwidth and Internet connectivity to other providers and to businesses and anchor institutions. | FALSE | N/A | The final redundancy segment between St. Ignatius and Ronan will be completed. Dark fiber will be delivered to Bresnan. The east/west route on the Blackfeet will be completed, and the cultural walk through for the Heart Butte route on the Blackfeet will be completed. Next quarter production estimates; Number of miles of fiber planned for deployment: 198 Number of CAI's planned for connection: 7 Number of broadband wholesaler/last mile provider agreements signed: 2 | Ronan Telephone Co. | Our biggest challenge has been obtaining permits from the Department of Transportation for work on the Blackfeet Reservation. Communications are being resolved and we expect to have these permits shortly. | The biggest challenge at this time is now permitting delays from the Department of Transportation. The EA work is all done, permits have been applied for, and we are waiting on issuance of the permits and cannot start work until they are released by DOT. We may need some help explaining the urgency of the permits. | TRUE
NT10BIX5570148 | 2012 | Q3 | Q3 - 2012 | All fiber and conduit are now placed, spliced and ready on the western segment from Elmo to Hot Springs. The Pablo Central Office is being prepared with power, cages for collocated customers, and the backbone is terminated from the Missoula segment at that location. All of the electronics for backbone distribution have been ordered and received for the Western section of the network. Distribution and repeater equipment has been staged in Missoula, Arlee, St. Ignatius, Ronan and Pablo for final installation next quarter. Network Management hardware and software has been ordered and received and is scheduled for installation next quarter. Interim power has been secured from Zayo in Missoula to prepare for installation of the networking hardware. On the Blackfeet reservation, conduit has been placed between East Glacier Park and Browning, and between Browning and Cut Bank. A Collocation agreement has been executed with the Northern Telephone Exchange for the Santa Rita facility. Fiber has been installed between the Northern Telephone Exchange in Santa Rita and Cut Bank. | 110 | 0 | 106 | 797 | 110 | 0 | 0 | 7 | Projected 264. Work stoppage on the Blackfeet and schedule slippage by our contractor both have impacted miles planned for completion. | Projected 0. | Projected 106, no variance (106 in kind fiber match) | Projected 321. | Projected 264. Work stoppage on the Blackfeet has impacted miles planned for completion. | Projected 3. Wireless is scheduled for the end of the middle mile build, so project slippage has impacted it. | N/A | Projected 17. Seattle, Missoula, Arlee, St. Ignatius, Ronan, Santa Rita and Pablo. Overall project slippage has impacted the number of interconnection points. | 2 | 1 | 12 | Cablevision (Bresnan) Cutthroat Communications | We have executed a contract with Bresnan for a 20-year prepaid IRU for 2 dark fibers. They will prepay in a lump sum when installed and accepted. We have executed a contract with Cutthroat Communications for the provision of 2Gb ethernet from Missoula to Seattle for a monthly recurring charge of $5600, term of 36 months. | Cutthroat Communications in Bozeman is monitoring our network at their Network Operating Center. This will transition to Montana West, once Montana West establishes its own Network Operations Center, currently scheduled for Q412. | 0 | 2 | 1 | 4 | Projected 0 | Projected 2. Cutthroat Communications and Bresnan | Projected 0. Bresnan has executed an IRU agreement with Montana West for dark fiber when available. Originally scheduled for August 2012, now scheduled for early 2013. | 100Mb, 1Gb, 2Gb, dark fiber. | 0 | 0 | 0 | 2 | Projected 32. Blackfeet work stoppage and construction delays have impacted our ability to provide planned service. | Projected 0. | Projected 32. Blackfeet work stoppage and construction delays have impacted our ability to provide planned service. | 100Mb and 1Gb. | 175 | 0 | 0 | 0 | 3 | Projected 1210. | Projected 318. Overall project slippage has impacted this planned provision of services. | Projected 42. Overall project slippage has impacted this planned provision of services. | Projected 276. Overall project slippage has impacted this planned provision of services. | 1.5Mb, 2.5Mb, 4Mb | 12 | 0 | 0 | 0 | 4 | Projected 171. Overall project slippage has impacted this planned provision of services. | Projected 67. Overall project slippage has impacted this planned provision of services. | Projected 22. Overall project slippage has impacted this planned provision of services. | Projected 45. Overall project slippage has impacted this planned provision of services. | 10Mb, 20mb, 50Mb, 100Mb | We do not anticipate any special offerings other than wholesale bandwidth and Internet connectivity to other providers and to businesses and anchor institutions. | FALSE | N/A | Montana West will install the transport electronics for the southern portion of the network between Pablo through Ronan, St. Ignatius, Arlee, Evaro, and Missoula. This will enable the provision of services to CAI's and other providers within that service area. Solarwinds network monitoring software and hardware will be installed and Montana West will transition from contracting NOC services to our own Network Operating Center. We will continue installations on the Blackfeet when negotiations are completed. Number of miles planned for deployment next quarter: 20 (Mission to Ronan) Number of CAI's planned for connection next quarter: (upgrades of existing CAI's) 7 Number of broadband wholesaler/last mile provider agreements planned for next quarter: 1 | Ronan Telephone Co. | Work stoppages on the Blackfeet Reservation have impacted the schedule. BTOP has been engaged in negotiations with the Tribe. Discussions are ongoing with expectations of a resolution of the issues and a decision to allow Montana West to move forward during the next quarter. | We will need continued negotiation assistance from BTOP to obtain permission from the Blackfeet to continue the project on the Blackfeet reservation. | TRUE